## 5 YR Pivot
| Created Yr | (All)
| MAT | (All)
| $ | (All)
| Open Weeks | (All)
| Closed Yr | Count of Orders | Average Weeks to Close | Average $ of Closed Order
| 2015 | 129 | 127.4064 | 172106.0456
| 2016 | 218 | 157.8886 | 188720.4068
| 2017 | 130 | 157.9527 | 189919.7138
| 2018 | 133 | 204.5177 | 216582.1513
| 2019 | 142 | 149.167 | 194935.2644
| 2020 | 253 | 160.7041 | 191340.9763
| OPEN | 1367 | 97.0339 | 353995.2507
| Grand Total | 2372 | 123.5561 | 285345.4046
| Row Labels | Count of Order | Average of Open Weeks | Sum of $
3 | ADER | 28 | 81.1582 | 1350635.49
4 | APPR | 3 | 111.9524 | 719061.46
12 | clsd | 987 | 159.7839 | 188773866.36
OTHER DO NOT INCLUDE | CNCL | 5 | 126.4857 | 2787.93
7 | CONS | 91 | 111.4678 | 71344124.56
OTHER DO NOT INCLUDE | DCNL | 7 | 90.6531 | 205312
8 | DOCC | 116 | 147.8732 | 233432228
2 | ESTS | 105 | 72.3959 | 4018455
10 | FICL | 83 | 156.5232 | 97731998.15
9 | MAPP | 16 | 118.6071 | 21403857.9
5 | PEND | 141 | 87.9676 | 35916858.65
11 | PREC | 18 | 155.7778 | 6489871.08
OTHER DO NOT INCLUDE | PROD | 6 | 145.2857 | 56115.94
6 | UNSC | 53 | 119.5337 | 8404325.97
1 | UNSE | 713 | 83.1571 | 6989801.2
| Grand Total | 2372 | 123.5561 | 676839299.69
| AVG CN24 INPR - DC05 COMP DAYS |  |  | 118.7993
| AVG DC05 COMP - DC10 COMP DAYS |  |  | 119.7157

## 5 YR Table & Charts
Created Yr | (All) | [5 empty] | Created Yr | (All) | [8 empty] | Created Yr | (All)
$ | (All) | [5 empty] | $ | (All) | [8 empty] | MAT | (All)
| Column Labels | [6 empty] | Column Labels | [8 empty] | Row Labels | Count of Order | Average of Open Weeks | Sum of $
| 08J |  | 08W |  | Total Count of Order | Total Sum of $ |  | 08J |  |  | 08W |  |  | Total Count of Order | Total Average of Open Weeks | Total Average of $ | UNSE | 713 | 83.1571 | 6989801.2
Row Labels | Count of Order | Sum of $ | Count of Order | Sum of $ |  |  | Row Labels | Count of Order | Average of Open Weeks | Average of $ | Count of Order | Average of Open Weeks | Average of $ |  |  |  | ESTS | 105 | 72.3959 | 4018455
2015 | 86 | 17213531.6 | 43 | 4988148.28 | 129 | 22201679.88 | 2015 | 86 | 136.2508 | 200157.3442 | 43 | 109.7176 | 116003.4484 | 129 | 127.4064 | 172106.0456 | ADER | 28 | 81.1582 | 1350635.49
2016 | 167 | 36016530.47 | 51 | 5124518.22 | 218 | 41141048.69 | 2016 | 167 | 166.5184 | 215667.8471 | 51 | 129.6303 | 100480.7494 | 218 | 157.8886 | 188720.4068 | APPR | 3 | 111.9524 | 719061.46
2017 | 98 | 20728084.85 | 32 | 3961477.94 | 130 | 24689562.79 | 2017 | 98 | 165.4286 | 211511.0699 | 32 | 135.058 | 123796.1856 | 130 | 157.9527 | 189919.7138 | PEND | 141 | 87.9676 | 35916858.65
2018 | 108 | 25798404.71 | 25 | 3007021.41 | 133 | 28805426.12 | 2018 | 108 | 219.2169 | 238874.1177 | 25 | 141.0171 | 120280.8564 | 133 | 204.5177 | 216582.1513 | UNSC | 53 | 119.5337 | 8404325.97
2019 | 75 | 15217190.8 | 67 | 12463616.74 | 142 | 27680807.54 | 2019 | 75 | 187.6571 | 202895.8773 | 67 | 106.081 | 186024.1304 | 142 | 149.167 | 194935.2644 | CONS | 91 | 111.4678 | 71344124.56
2020 | 176 | 15148162.46 | 77 | 33261104.54 | 253 | 48409267 | 2020 | 176 | 183.1266 | 86069.1049 | 77 | 109.4527 | 431962.3966 | 253 | 160.7041 | 191340.9763 | DOCC | 116 | 147.8732 | 233432228
Grand Total | 710 | 130121904.89 | 295 | 62805887.13 | 1005 | 192927792.02 | OPEN | 460 | 137.4165 | 61396.0372 | 907 | 76.5532 | 502391.7647 | 1367 | 97.0339 | 353995.2507 | MAPP | 16 | 118.6071 | 21403857.9
[7 empty] | Grand Total | 1170 | 161.4784 | 135353.9163 | 1202 | 86.6433 | 431343.7751 | 2372 | 123.5561 | 285345.4046 | FICL | 83 | 156.5232 | 97731998.15
[17 empty] | PREC | 18 | 155.7778 | 6489871.08
| Column Labels | [15 empty] | clsd | 987 | 159.7839 | 188773866.36
| 08J |  | 08W |  | Total Count of Order | Total Sum of $ | [10 empty] | PROD | 6 | 145.2857 | 56115.94
Row Labels | Count of Order | Sum of $ | Count of Order | Sum of $ | [12 empty] | DCNL | 7 | 90.6531 | 205312
UNSE | 284 | 798510.27 | 429 | 6191290.93 | 713 | 6989801.2 | [10 empty] | CNCL | 5 | 126.4857 | 2787.93
ESTS | 33 | 491291.87 | 72 | 3527163.13 | 105 | 4018455 | [10 empty] | Grand Total | 2372 | 123.5561 | 676839299.69
ADER | 5 | 148436.09 | 23 | 1202199.4 | 28 | 1350635.49
APPR | 1 | 26066.03 | 2 | 692995.43 | 3 | 719061.46
PEND | 36 | 1077931.13 | 105 | 34838927.52 | 141 | 35916858.65
UNSC | 17 | 1803048.02 | 36 | 6601277.95 | 53 | 8404325.97
CONS | 20 | 5735278.69 | 71 | 65608845.87 | 91 | 71344124.56
DOCC | 28 | 10348294.59 | 88 | 223083933.41 | 116 | 233432228
MAPP | 2 | 743827.59 | 14 | 20660030.31 | 16 | 21403857.9
FICL | 26 | 6914081.18 | 57 | 90817916.97 | 83 | 97731998.15
PREC | 16 | 3879488.46 | 2 | 2610382.62 | 18 | 6489871.08
clsd | 694 | 126242416.43 | 293 | 62531449.93 | 987 | 188773866.36
PROD | 3 | 3428.12 | 3 | 52687.82 | 6 | 56115.94
DCNL | 3 | 154085.47 | 4 | 51226.53 | 7 | 205312
CNCL | 2 | -2101.92 | 3 | 4889.85 | 5 | 2787.93
Grand Total | 1170 | 158364082.02 | 1202 | 518475217.67 | 2372 | 676839299.69
* 3430 Total orders exist for MAT codes 08J and 08W. Of the 3430 only 2605 are capital orders, 825 are planning/other.
* 233 of the 2605 were closed prior to 2015, leaving us with a population of 2372.
* The population of 2372 contains closed orders, which include those that were closed via cancellation.
* 490 of the 2372 have zero cost. Of the 490, 269 are CLSD and 221 are still open. Assuming the 269 CLSD zero cost orders are actually cancels then that would an 11.34% cancellation rate.
* Based on the user status most of cost are in DOCC, FICL, and PEND.
[7 empty] | * Based on the user status most of orders are in UNSE, PEND, and DOCC. | [9 empty] | AVG CN24 INPR - DC05 COMP DAYS |  |  | 118.7993
[7 empty] | * | [9 empty] | AVG DC05 COMP - DC10 COMP DAYS |  |  | 119.7157

## 5 YR CAPITAL ORDER DATA
Order | Order Description | Order Created On | Notification | Notif Created On | Superior Order | Superior Order Description | Status | Status Description | Status Profile | Status Profile Description | Division | Division Description | Created by LANID | Created by | Job Owner LANID | Job Owner | Estimator LANID | Estimator | ADE LANID | ADE | Baseline In-Srvc Dt | Functional Loc | Functional Loc Description | Plant section | Plant Section Description | Summarized Planning | Summarized Planning Description | Estimated Units | Actual Units | MAT | Created Yr | Closed Date | Closed Yr | Open Days | Open Weeks | User Status | Status Sequence | Order Type | MWC | MWC Description | Program | Program Description | Reason Code | Project Definition | Funding ID Category | Funding Identifier | Funding ID Level 1 | Funding Id Level 2 | Current Year Organiz | Next Year Organizati | CN24 Task Status | CN24 Task INPR Date | CN24 Task COMP Date | CN07 Task Status | CN07 Task INPR Date | CN07 Task COMP Date | DC05 Task Status | DC05 Task INPR Date | DC05 Task COMP Date | DC14 Task Status | DC14 Task INPR Date | DC14 Task COMP Date | DC15 Task Status | DC15 Task INPR Date | DC15 Task COMP Date | DC10 Task Status | DC10 Task INPR Date | DC10 Task COMP Date | CN24 INPR - DC05 COMP Days | DC05 COMP - DC10 COMP Days | $
30460800 | EP OCEANO REPL. ANNEAL OC 1101,22ND,HWY1 | 09/01/2005 | 101777091 | 09/01/2005 | # | Not assigned | 40 | Closed | ECES_070 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 11/09/2007 | E | UTILITY OPERATIONS ELECTRIC FACILITIES | # | Not assigned | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2005 | 08/18/2018 | 2018 | 4734 | 676.2857 | clsd | 12 | E070 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 815660.62
30531403 | OC4 RECONDUCT 4885 #6CU PLUMAS 1102 PH- | 10/18/2006 | 102146759 | 10/13/2006 | # | Not assigned | 40 | Closed | ECES_CAP | ECES Capital User Status | # | Not assigned | [8 empty] | 09/15/2009 | ED.15285.1104.SWIT | SWITCHES | 051 | SUTTER COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 5,001.000 | 08J | 2006 | 01/17/2015 | 2015 | 3013 | 430.4286 | clsd | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Plumas 1102 Project | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | #N/A | #N/A | #N/A | COMP | 2011-06-11 | 2010-08-04 | COMP | 2010-08-06 | 2010-08-11 | COMP | 2010-08-11 | 2010-08-23 | COMP | 2010-08-23 | 2010-10-13 | COMP | 2010-10-13 | 2010-10-28 | #N/A | 78 | 223393.04
30582041 | EP RECON 3854FT - KERN OIL 1108 BKSFLD | 06/18/2007 | 102376800 | 06/17/2007 | # | Not assigned | 40 | Closed | ECES_070 | Capital Status w/ Deferred | KE | KERN | [8 empty] | 04/08/2008 | ED.66-2827366000 | KERN MAP 2827366 | A4 | AREA 4 | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2007 | 08/08/2015 | 2015 | 2973 | 424.7143 | clsd | 12 | E070 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 244209.11
30612543 | *CANC*UPGRADE 4CWC TO 2AR ON ANTLER*CANC | 02/20/2008 | # | #N/A | 80042412 | UPGRADE 4CWC TO 2AR ON ANTLER 1101 | 40 | Closed | ECES_CAP | ECES Capital User Status | # | Not assigned | [8 empty] | # | ED.10327.1101 | ANTLER 1101 | # | Not assigned | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2008 | 01/04/2018 | 2018 | 3606 | 515.1429 | clsd | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | #N/A | #N/A | #N/A | COMP | 2018-01-04 | 2009-05-14 | INPR | 2009-05-14 | 2018-01-04 | # | 2018-01-04 | 2018-01-04 | # | 2018-01-04 | 2018-01-04 | # | 2018-01-04 | 2018-01-04 | #N/A | 0 | 0
30642535 | EM E GLORIA RD, GON=REPL WIRE | 07/09/2008 | 103141200 | 07/15/2008 | # | Not assigned | 40 | Closed | ECES_CAP | ECES Capital User Status | # | Not assigned | [8 empty] | # | ED.05-K160000000 | SALINAS MAP K16 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2008 | 07/21/2018 | 2018 | 3664 | 523.4286 | clsd | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 84204.19
30651363 | OC4 RECOND #6CU PLUMAS 1102 PH-2 | 08/14/2008 | # | #N/A | 30531403 | OC4 RECONDUCT 4885 #6CU PLUMAS 1102 PH- | 40 | Closed | ECES_CAP | ECES Capital User Status | # | Not assigned | [8 empty] | 10/15/2009 | ED.15285.1104.SWIT | SWITCHES | 051 | SUTTER COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 5,365.000 | 5,366.000 | 08J | 2008 | 01/17/2015 | 2015 | 2347 | 335.2857 | clsd | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Plumas 1102 Project | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2011-06-12 | 2011-06-12 | COMP | 2011-06-12 | 2010-08-04 | COMP | 2010-08-06 | 2010-08-11 | COMP | 2010-08-11 | 2010-08-23 | COMP | 2010-08-23 | 2010-10-13 | COMP | 2010-10-13 | 2010-10-28 | -305 | 78 | 306811.81
30652909 | RECONDUCTOR KNIGHTS LDG 1101- PHASE | 08/21/2008 | # | #N/A | 80059045 | CNCL RECONDUCTOR KNIGHTS LDG 1101- P | 40 | Closed | ECES_CAP | ECES Capital User Status | # | Not assigned | [8 empty] | # | ED.06272.1101 | KNIGHTS LANDING 1101 | # | Not assigned | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2008 | 03/03/2018 | 2018 | 3481 | 497.2857 | clsd | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | #N/A | #N/A | #N/A | COMP | 2018-03-03 | 2009-05-12 | INPR | 2009-05-12 | 2018-03-03 | COMP | 2018-03-03 | 2012-05-23 | COMP | 2012-05-23 | 2012-05-23 | COMP | 2012-05-23 | 2012-05-23 | #N/A | -2110 | 14846.8
30661627 | ARCATA 1122 REPLACE ANNEALED WIRE - | 09/26/2008 | # | #N/A | 80058638 | CNCL ARCATA 1122 REPLACE ANNEALED W*CANC | 40 | Closed | ECES_CAP | ECES Capital User Status | # | Not assigned | [8 empty] | 10/01/2014 | ED.19202.1122.SWIT | SWITCHES | # | Not assigned | 5535457 | DO 08 - Monthly Forecast Only | 2,098.000 | 740.000 | 08J | 2008 | 09/17/2016 | 2016 | 2913 | 416.1429 | clsd | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30661627_ARCATA 1122 REPLACE ANNEALED WI | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-10-21 | 2015-10-16 | COMP | 2015-10-21 | 2015-10-21 | COMP | 2015-11-05 | 2015-11-05 | COMP | 2015-11-05 | 2016-03-31 | COMP | 2016-03-31 | 2016-03-31 | COMP | 2016-03-31 | 2016-04-04 | 15 | 151 | 750642.96
30721678 | OC1 RECONDUCTOR 1,100 CKT FT ON THE D-11 | 07/14/2009 | 103903738 | 07/13/2009 | # | Not assigned | 40 | Closed | ECES_CAP | ECES Capital User Status | # | Not assigned | [8 empty] | 11/12/2009 | ED.01204.1105 | OAKLAND D 1105 | 001 | ALAMEDA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 1,100.000 | 1,100.000 | 08J | 2009 | 06/16/2018 | 2018 | 3259 | 465.5714 | clsd | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2012-08-16 | 2010-06-03 | COMP | 2010-07-27 | 2010-07-27 | COMP | 2010-08-10 | 2010-08-13 | COMP | 2010-08-13 | 2010-08-31 | COMP | 2010-08-31 | 2012-03-02 | COMP | 2012-03-02 | 2012-03-02 | -734 | 567 | 176664.86
30752681 | OC2 +RECOND 3850 FT DETER 1-0AR BV 1106 | 01/11/2010 | 103921472 | 07/28/2009 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/17/2010 | ED.18273.1102 | RESERVATION ROAD 1102 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 3,850.000 | 3,850.000 | 08J | 2010 | 03/10/2018 | 2018 | 2980 | 425.7143 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2012-03-22 | 2011-05-15 | COMP | 2011-05-15 | 2011-09-07 | COMP | 2011-09-12 | 2011-10-05 | COMP | 2011-10-05 | 2011-10-19 | COMP | 2011-10-19 | 2012-01-26 | COMP | 2012-01-26 | 2012-02-02 | -169 | 120 | 253904.54
30788135 | OC4 PLCRVILLE 2106 REPL#6 CW DET PH-1 | 07/15/2010 | 104755326 | 07/15/2010 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2011 | ED.15308.2106.RECL | RECLOSERS | 009 | EL DORADO COUN | 5517127 | DO 08 - Monthly Forecast Only | 3,370.000 | 3,403.000 | 08J | 2010 | 04/09/2016 | 2016 | 2095 | 299.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Placerville 2106 Project | Base Capital | GRC Electric Dist | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2012-05-07 | 2012-02-16 | COMP | 2012-03-05 | 2012-03-05 | COMP | 2012-03-08 | 2012-03-21 | COMP | 2012-03-21 | 2012-03-28 | COMP | 2012-03-28 | 2012-04-17 | COMP | 2012-04-17 | 2012-04-20 | -47 | 30 | 446343.68
30799823 | OC2 +RECO 3000 FT 4C/2AR W/ 397A RSRV RD | 08/31/2010 | 104799574 | 08/27/2010 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/29/2011 | ED.18273.1102 | RESERVATION ROAD 1102 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 2,734.000 | 3,000.000 | 08J | 2010 | 11/07/2015 | 2015 | 1894 | 270.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2011-07-31 | 2011-07-31 | COMP | 2011-07-31 | 2011-10-06 | COMP | 2011-10-11 | 2011-11-01 | COMP | 2011-11-01 | 2011-11-17 | COMP | 2011-11-17 | 2012-11-01 | COMP | 2012-11-01 | 2012-11-01 | 93 | 366 | 110624.94
30802035 | OC4 GEYSERVILLE1102ANNEALED 6CU,GYSVL*GC | 09/11/2010 | 104812838 | 09/10/2010 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2011 | ED.04289.1102 | GEYSERVILLE 1102 | 049 | SONOMA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 1,390.000 | 1,450.000 | 08J | 2010 | 05/14/2016 | 2016 | 2072 | 296 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2013-12-28 | 2013-04-30 | COMP | 2013-04-30 | 2013-04-30 | COMP | 2013-05-01 | 2013-05-13 | COMP | 2013-05-13 | 2013-06-01 | COMP | 2013-06-01 | 2013-06-04 | COMP | 2013-06-04 | 2013-06-04 | -229 | 22 | 127720.71
30804426 | OC2 REPL ANNEALED COND - DINUBA 1105 | 09/22/2010 | 104821609 | 09/21/2010 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/18/2011 | ED.25409.1105 | DINUBA 1105 | 054 | TULARE COUNTY | 5517127 | DO 08 - Monthly Forecast Only | 3,622.000 | 4,865.000 | 08J | 2010 | 09/12/2015 | 2015 | 1816 | 259.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | GRC Electric Dist | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2011-11-01 | 2011-10-30 | COMP | 2011-11-01 | 2012-01-19 | COMP | 2012-01-19 | 2012-01-19 | COMP | 2012-01-19 | 2012-02-02 | COMP | 2012-02-02 | 2012-07-16 | COMP | 2012-07-16 | 2012-07-31 | 79 | 194 | 117017.25
30804427 | OROSI 1103 REPL ANNEALED CONDUCTOR | 09/22/2010 | 104821632 | 09/21/2010 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/30/2012 | ED.25284.1103 | OROSI 1103 | 054 | TULARE COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 8,700.000 | 0.000 | 08J | 2010 | # | OPEN | 3726 | 532.2857 | DOCC | 8 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2012-04-24 | 2012-06-06 | COMP | 2012-06-27 | 2014-11-16 | COMP | 2014-11-16 | 2014-11-16 | COMP | 2014-05-15 | 2014-05-15 | COMP | 2014-05-15 | 2014-07-10 | COMP | 2014-07-10 | 2014-10-31 | 936 | -16 | 313768.38
30818028 | OC4 2011 NB ANNEALED CONDUCTOR 18 SPANS | 11/20/2010 | 104926411 | 11/19/2010 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/01/2011 | ED.04329.1105 | PUEBLO 1105 | 028 | NAPA COUNTY | 5535211 | CWSP SPO - SH 08 | 5,200.000 | 2,945.000 | 08J | 2010 | 09/10/2016 | 2016 | 2121 | 303 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2011-12-09 | 2011-11-03 | COMP | 2011-12-09 | 2011-12-09 | COMP | 2011-12-13 | 2011-12-15 | COMP | 2011-12-15 | 2011-12-28 | COMP | 2011-12-28 | 2012-12-07 | COMP | 2012-12-07 | 2012-12-07 | 6 | 358 | 1126135.12
30819811 | OC4 PLCRVILLE 2106 REPL#6 CW DET PH-4 | 12/01/2010 | # | #N/A | 30788135 | OC4 PLCRVILLE 2106 REPL#6 CW DET PH-1 | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | # | ED.15308.2106.RECL | RECLOSERS | 009 | EL DORADO COUN | 5517127 | DO 08 - Monthly Forecast Only | 3,403.000 | 3,405.000 | 08J | 2010 | 04/09/2016 | 2016 | 1956 | 279.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Placerville 2106 Project | Base Capital | GRC Electric Dist | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2011-08-03 | 2012-02-16 | COMP | 2012-03-07 | 2012-03-07 | COMP | 2012-03-12 | 2012-03-22 | COMP | 2012-03-22 | 2012-03-28 | COMP | 2012-03-28 | 2012-04-19 | COMP | 2012-04-19 | 2012-05-07 | 232 | 46 | 293093.07
30829819 | MARYSVILLE 1103-RECON1300' #6CU Y2017 | 01/20/2011 | 105186065 | 01/20/2011 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/28/2018 | ED.11-P230800000 | MARYSVILLE MAP P2308 | 058 | YUBA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 1,225.000 | 1,225.000 | 08J | 2011 | 04/20/2019 | 2019 | 3012 | 430.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30829819_R6 RECOND 1300' #6CU MARYSVILLE | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2018-06-06 | 2018-08-27 | COMP | 2018-08-28 | 2018-08-28 | COMP | 2018-08-28 | 2018-08-28 | COMP | 2018-08-28 | 2018-08-29 | COMP | 2018-08-29 | 2018-11-28 | COMP | 2018-11-28 | 2018-11-30 | 83 | 94 | 260614.29
30848750 | OC2 RPL3600FT ANNEALED 1-0AR W/ 715A PH2 | 04/27/2011 | 105282269 | 04/22/2011 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/30/2012 | ED.18226.1106 | BUENA VISTA 1106 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 3,870.000 | 3,870.000 | 08J | 2011 | 03/21/2015 | 2015 | 1424 | 203.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2013-01-25 | 2012-08-21 | COMP | 2012-08-21 | 2012-08-26 | COMP | 2012-08-30 | 2012-09-10 | COMP | 2012-09-10 | 2012-09-25 | COMP | 2012-09-25 | 2012-11-14 | COMP | 2012-11-14 | 2012-12-24 | -137 | 105 | 218745.23
30850243 | OCGC RECON OH DET WIRE ON KIRKER 2107 | 05/05/2011 | 105260427 | 04/05/2011 | # | Not assigned | 40 | Closed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 06/27/2014 | ED.01445.2103 | KIRKER 2103 | 007 | CONTRA COSTA C | 5535457 | DO 08 - Monthly Forecast Only | 4,142.000 | 4,132.000 | 08J | 2011 | 12/16/2017 | 2017 | 2417 | 345.2857 | CLSD | 12 | E070 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30850243_R1 RECONDUCTOR OH DETERIORATED | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-03-08 | 2015-03-08 | COMP | 2015-04-22 | 2015-05-08 | COMP | 2015-05-08 | 2015-05-08 | COMP | 2015-05-08 | 2015-05-18 | COMP | 2015-05-18 | 2015-05-21 | COMP | 2015-05-21 | 2015-05-21 | 61 | 13 | 528791.48
30858527 | OC4XRECON 3000' 4AR/4C W/4-0A,MTRY STSOL | 06/21/2011 | 105341748 | 06/20/2011 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/29/2013 | ED.18205.1114 | SOLEDAD 1114 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 3,255.000 | 0.000 | 08J | 2011 | 05/09/2015 | 2015 | 1418 | 202.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30858527_R2 RECON 3000' 4AR/4C W/4-0A,MT | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2014-09-04 | 2014-09-04 | COMP | 2014-09-16 | 2014-09-17 | COMP | 2014-09-19 | 2014-09-26 | COMP | 2014-10-15 | 2015-04-30 | INPR | 2015-04-30 | 2015-05-09 | # | 2015-05-09 | 2015-05-09 | 22 | 225 | 379688.12
30860291 | OC41106 SUNSET OH RECONDUCTORING PROJECT | 06/29/2011 | 105349355 | 06/29/2011 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2011 | ED.02264.1106 | DALY CITY 1106 | 038 | SAN FRANCISCO | 5535457 | DO 08 - Monthly Forecast Only | 2,246.000 | 2,246.000 | 08J | 2011 | 11/19/2016 | 2016 | 1970 | 281.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30860291_DC 1106 SUNSET OH RECONDUCTORIN | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2014-08-12 | 2014-07-15 | COMP | 2014-08-12 | 2014-08-12 | COMP | 2014-10-08 | 2014-10-20 | COMP | 2014-10-20 | 2015-09-08 | COMP | 2015-09-08 | 2016-04-18 | COMP | 2016-04-18 | 2016-04-25 | 69 | 553 | 617975.52
30860842 | OC2 +REC 7,100' ANNEALED 3/4AR | 07/02/2011 | 105352424 | 07/01/2011 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/28/2012 | ED.18208.2102 | LOS OSITOS 2102 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 7,160.000 | 7,160.000 | 08J | 2011 | 04/09/2016 | 2016 | 1743 | 249 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2012-08-23 | 2012-09-25 | COMP | 2012-09-25 | 2012-09-28 | COMP | 2012-10-03 | 2012-10-15 | COMP | 2012-10-15 | 2012-10-26 | COMP | 2012-10-26 | 2012-12-20 | INPR | 2012-12-20 | 2013-05-25 | 53 | 222 | 180334.63
30869889 | OC4 ANNEALEDCONDUCTOR-CORONA1101,*GC | 08/16/2011 | 105399422 | 08/15/2011 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 07/01/2012 | ED.04349.1101 | CORONA 1101 | 049 | SONOMA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 4,455.000 | 4,455.000 | 08J | 2011 | 06/13/2015 | 2015 | 1397 | 199.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2012-09-21 | 2012-09-21 | COMP | 2012-09-21 | 2012-10-08 | COMP | 2012-11-06 | 2012-11-15 | COMP | 2012-11-15 | 2012-11-17 | COMP | 2012-11-17 | 2012-12-11 | COMP | 2012-12-11 | 2012-12-11 | 55 | 26 | 487898.45
30872362 | OC4 RECOND ANNEALED OH, LINCOLN 1105 | 08/26/2011 | 105409249 | 08/25/2011 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/30/2012 | ED.15370.1105.COND | CONDUCTOR | 031 | PLACER COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 10,248.000 | 102,500.000 | 08J | 2011 | 04/09/2016 | 2016 | 1688 | 241.1429 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2012-10-02 | 2012-11-08 | COMP | 2012-12-12 | 2012-12-12 | COMP | 2012-12-14 | 2012-12-24 | COMP | 2012-12-24 | 2012-12-28 | COMP | 2012-12-28 | 2013-01-31 | COMP | 2013-01-31 | 2013-02-27 | 83 | 65 | 357096.77
30873773 | OC4HIGHLANDS 1104 ANNEALED WIRE-HELI PAD | 09/01/2011 | 105414190 | 08/30/2011 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/30/2013 | ED.04336.1104.SWIT | SWITCHES | 017 | LAKE COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 1,000.000 | 0.000 | 08J | 2011 | 03/19/2016 | 2016 | 1661 | 237.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30873773_HIGHLANDS 1104 ANNEALED WIRE-HE | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2014-03-13 | 2014-03-13 | COMP | 2014-04-10 | 2014-04-10 | COMP | 2014-04-17 | 2014-05-01 | COMP | 2014-05-01 | 2014-05-21 | COMP | 2014-05-21 | 2014-11-07 | COMP | 2014-11-07 | 2014-11-10 | 49 | 193 | 507864.89
30873864 | OC4RCNDR ANNEALED #6 AWG COPER, BAYLIS R | 09/01/2011 | 105415953 | 09/01/2011 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2013 | ED.14-X220000000 | GLENN MAP X22 | 011 | GLENN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 7,363.000 | 7,363.000 | 08J | 2011 | 01/17/2015 | 2015 | 1234 | 176.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2013-08-19 | 2013-08-15 | COMP | 2013-08-19 | 2013-10-29 | COMP | 2013-11-20 | 2013-11-27 | COMP | 2013-11-27 | 2013-12-10 | COMP | 2013-12-10 | 2014-01-07 | COMP | 2014-01-07 | 2014-01-27 | 100 | 61 | 382749.63
30881599 | OC4 EL DORADO PH 2101 DETRIORATED CONDUC | 10/05/2011 | 105494334 | 10/05/2011 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/28/2013 | ED.15276.2101.SWIT | SWITCHES | 009 | EL DORADO COUN | 5535457 | DO 08 - Monthly Forecast Only | 4,493.000 | 4,493.000 | 08J | 2011 | 12/16/2017 | 2017 | 2264 | 323.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2013-05-13 | 2013-06-26 | COMP | 2013-05-13 | 2013-08-22 | COMP | 2013-08-28 | 2013-09-06 | COMP | 2013-09-06 | 2013-09-11 | COMP | 2013-09-11 | 2013-09-13 | COMP | 2013-09-13 | 2013-10-02 | 116 | 26 | 726840.37
30886133 | OC4 ALTO 1125 REPL DET. COND LR_510 | 10/26/2011 | 105529621 | 10/25/2011 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 07/31/2012 | ED.04203.1125.RECL | RECLOSERS | 021 | MARIN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 2,910.000 | 2,184.000 | 08J | 2011 | 12/01/2018 | 2018 | 2593 | 370.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2012-10-23 | 2012-10-26 | INPR | 2012-10-29 | 2014-01-18 | COMP | 2013-09-12 | 2013-09-26 | COMP | 2013-09-26 | 2013-10-01 | COMP | 2013-10-01 | 2014-01-11 | COMP | 2014-01-11 | 2014-01-14 | 338 | 110 | 301572.7
30890664 | *CANC* FR FIGARDEN 2112 FLISR *CANC* | 11/19/2011 | 105587205 | 11/17/2011 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/09/2011 | ED.25204.1101 | AIRWAYS 1101 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2011 | 03/09/2020 | 2020 | 3033 | 433.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | GRC Electric Dist | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2020-03-09 | 2020-03-09 | # | 2020-03-09 | 2020-03-09 | # | 2020-03-09 | 2020-03-09 | COMP | 2020-02-13 | 2020-02-13 | COMP | 2020-02-13 | 2020-02-13 | COMP | 2020-02-13 | 2020-02-13 | 0 | -25 | 0
30900554 | XDIX. LAND 2102 - RECONDUCTOR 900 FT | 01/19/2012 | 105891152 | 01/19/2012 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/01/2012 | ED.01472.2102.SWIT | SWITCHES | 043 | SANTA CLARA CO | 5535457 | DO 08 - Monthly Forecast Only | 553.000 | 0.000 | 08J | 2012 | # | OPEN | 3242 | 463.1429 | CONS | 7 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 108690.02
30910151 | OC1 REP 1000' ANNEALED COND: SR2103 | 03/08/2012 | 105961196 | 03/07/2012 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/31/2013 | ED.01423.2103.SWIT | SWITCHES | 001 | ALAMEDA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 918.000 | 1,000.000 | 08J | 2012 | 09/12/2015 | 2015 | 1283 | 183.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2013-04-01 | 2013-04-01 | COMP | 2013-04-01 | 2013-04-01 | COMP | 2013-06-06 | 2013-07-22 | COMP | 2013-07-22 | 2013-08-05 | COMP | 2013-08-05 | 2013-09-24 | COMP | 2013-09-24 | 2013-09-25 | 112 | 65 | 97587.8
30912306 | OC4 RECONDUCTOR 1540' OF #6CU ON | 03/19/2012 | 105979071 | 03/19/2012 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/28/2012 | ED.06380.1104.SWIT | SWITCHES | 048 | SOLANO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 1,632.000 | 08J | 2012 | 06/16/2018 | 2018 | 2280 | 325.7143 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2013-07-13 | 2012-11-29 | COMP | 2012-11-29 | 2012-11-29 | COMP | 2012-12-07 | 2012-12-14 | COMP | 2012-12-14 | 2012-12-24 | COMP | 2012-12-24 | 2013-03-19 | COMP | 2013-03-19 | 2013-03-19 | -211 | 95 | 152264.17
30931343 | OC4 DAIRYLAND 1109: RECONDUCTOR 1MI | 06/14/2012 | 106085535 | 06/12/2012 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 05/30/2014 | ED.25242.1109 | DAIRYLAND 1109 | 020 | MADERA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 5,645.000 | 08J | 2012 | 03/18/2015 | 2015 | 1007 | 143.8571 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30931343_R2 DAIRYLAND 1109: RECONDUCTOR | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2014-02-05 | 2014-02-05 | COMP | 2014-02-05 | 2014-02-06 | COMP | 2014-02-18 | 2014-03-13 | COMP | 2014-03-13 | 2014-04-07 | COMP | 2014-04-07 | 2014-07-24 | COMP | 2014-07-24 | 2014-07-30 | 36 | 139 | 288450.28
30934498 | OC4 BH406 RECONDUCT OH LINE ISQ T | 06/29/2012 | 106086709 | 06/13/2012 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/26/2013 | ED.02402.0406.TXFR.TROH | OVERHEAD TRANSFORMERS | 041 | SAN MATEO COUN | 5505513 | PN-OH ANNEALED/DETER CNDCTR: PM MGD | 315.000 | 0.000 | 08J | 2012 | 09/12/2015 | 2015 | 1170 | 167.1429 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2014-06-05 | 2014-06-05 | COMP | 2014-06-18 | 2014-06-18 | COMP | 2014-06-26 | 2014-08-05 | COMP | 2014-08-05 | 2014-11-04 | COMP | 2014-11-04 | 2014-12-03 | COMP | 2014-12-03 | 2014-12-05 | 61 | 122 | 174827.44
30934587 | OC2 REEDLEY 1112: ORANGE COVE OH CNDCTR | 06/29/2012 | 106102919 | 06/28/2012 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/28/2013 | ED.25234.1104 | REEDLEY 1104 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 7,370.000 | 7,370.000 | 08J | 2012 | 10/31/2015 | 2015 | 1219 | 174.1429 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2013-04-05 | 2013-08-08 | COMP | 2013-04-05 | 2014-01-16 | COMP | 2014-01-23 | 2014-03-10 | COMP | 2014-03-10 | 2014-03-26 | COMP | 2014-03-26 | 2015-10-09 | COMP | 2015-10-09 | 2015-10-09 | 339 | 578 | 904244.61
30935374 | 2014 WAHTOKE 1107 RECONDUCTOR | 07/05/2012 | 106107662 | 07/03/2012 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/01/2014 | ED.25453.1107 | WAHTOKE 1107 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 2,153.000 | 2,153.000 | 08J | 2012 | 05/07/2016 | 2016 | 1402 | 200.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30935374_R2-WAHTOKE 1107: RECONDUCTR 24 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | INPR | 2014-06-23 | 2016-05-07 | INPR | 2014-06-23 | 2016-05-07 | # | 2016-05-07 | 2016-05-07 | # | 2016-05-07 | 2016-05-07 | # | 2016-05-07 | 2016-05-07 | # | 2016-05-07 | 2016-05-07 | 684 | 0 | 288007.98
30936534 | OCGC 2014 WAHTOKE 1106 RECONDUCTOR | 07/12/2012 | 106122428 | 07/11/2012 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/01/2014 | ED.25453.1106 | WAHTOKE 1106 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 1,316.000 | 1,316.000 | 08J | 2012 | 05/07/2016 | 2016 | 1395 | 199.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30936534_R2 WAHTOKE 1106: RCDTR 1090' OF | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2014-05-11 | 2014-05-11 | COMP | 2014-05-23 | 2014-07-25 | COMP | 2015-05-04 | 2015-05-04 | COMP | 2014-08-01 | 2014-08-01 | COMP | 2014-08-01 | 2016-04-14 | COMP | 2016-04-14 | 2016-04-14 | 358 | 346 | 137177.14
30939679 | EC-E 348 JENSON RD WATSONVILLE | 07/27/2012 | 106168479 | 08/14/2012 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 07/29/2012 | ED.76-R191900000 | COAST MAP R1919 | 044 | SANTA CRUZ COU | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2012 | # | OPEN | 3052 | 436 | CONS | 7 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 129910.72
30943402 | OC1 REDWOOD 402 CASSIA ST & MIDDLEFIELD, | 08/16/2012 | 106170140 | 08/15/2012 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/06/2013 | ED.02416.1104.CAPA | CAPACITORS | 041 | SAN MATEO COUN | 5505513 | PN-OH ANNEALED/DETER CNDCTR: PM MGD | 135.000 | 445.000 | 08J | 2012 | 05/13/2017 | 2017 | 1731 | 247.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2013-05-30 | 2013-05-30 | COMP | 2013-06-03 | 2013-06-03 | COMP | 2013-06-18 | 2013-07-11 | COMP | 2013-07-11 | 2013-10-10 | COMP | 2013-10-10 | 2013-10-10 | COMP | 2013-10-10 | 2013-10-10 | 42 | 91 | 28888.56
30945062 | OCCC RECOND 2200 FT 4C W/ 397A HARRIS RD | 08/25/2012 | 106181656 | 08/24/2012 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 08/30/2013 | ED.18226.1102 | BUENA VISTA 1102 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 2,258.000 | 2,258.000 | 08J | 2012 | 09/10/2016 | 2016 | 1477 | 211 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-12-14 | 2015-12-03 | COMP | 2015-12-14 | 2015-12-16 | COMP | 2015-12-16 | 2015-12-16 | COMP | 2015-12-16 | 2016-04-01 | COMP | 2016-04-01 | 2016-04-01 | COMP | 2016-04-01 | 2016-04-04 | 2 | 110 | 151307.19
30946073 | OC2 WIREDOWN - FAMOSO 1101 RECONDUCTOR | 08/29/2012 | 106186356 | 08/29/2012 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/29/2013 | ED.25246.1101.SWIT | SWITCHES | 015 | KERN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 400.000 | 397.000 | 08J | 2012 | 10/17/2015 | 2015 | 1144 | 163.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2013-01-13 | 2013-01-13 | COMP | 2013-02-15 | 2013-02-15 | COMP | 2013-02-20 | 2013-03-11 | COMP | 2013-03-11 | 2013-03-15 | COMP | 2013-03-15 | 2013-03-15 | COMP | 2013-03-15 | 2013-03-15 | 57 | 4 | 5812.75
30947120 | OCLH-CARUTHERS 1104 RECONDUCTORING | 09/05/2012 | 106191445 | 09/05/2012 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/27/2013 | ED.25237.1104 | CARUTHERS 1104 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 660.000 | 660.000 | 08J | 2012 | 12/10/2016 | 2016 | 1557 | 222.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2013-08-06 | 2014-03-22 | COMP | 2013-08-06 | 2014-04-10 | COMP | 2014-04-15 | 2014-04-15 | COMP | 2014-04-15 | 2016-10-12 | COMP | 2016-10-12 | 2016-11-17 | COMP | 2016-11-17 | 2016-11-21 | 252 | 951 | 41793.22
30948009 | OC1 2819 CURTIS AVE. RWC REPL OH | 09/13/2012 | 106202084 | 09/10/2012 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/29/2013 | ED.02402.1106.SWIT | SWITCHES | 041 | SAN MATEO COUN | 5505513 | PN-OH ANNEALED/DETER CNDCTR: PM MGD | 220.000 | 150.000 | 08J | 2012 | 12/13/2015 | 2015 | 1186 | 169.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2013-05-18 | 2013-05-18 | COMP | 2013-06-03 | 2013-06-03 | COMP | 2013-06-18 | 2013-07-11 | COMP | 2013-07-11 | 2013-10-15 | COMP | 2013-10-15 | 2013-10-15 | COMP | 2013-10-15 | 2013-10-15 | 54 | 96 | 10099.57
30948153 | OC2 REPLACE #6CU WITH 4AR, VASONA 1103 | 09/12/2012 | 106202848 | 09/11/2012 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/26/2013 | ED.08377.1103.SWIT | SWITCHES | 043 | SANTA CLARA CO | 5532479 | CWSP 08W - Monthly Forecast Only | 660.000 | 665.000 | 08W | 2012 | 12/13/2015 | 2015 | 1187 | 169.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2013-10-08 | 2015-12-13 | COMP | 2013-10-08 | 2015-12-13 | COMP | 2013-10-24 | 2013-12-06 | COMP | 2013-12-06 | 2013-12-13 | COMP | 2013-12-13 | 2014-01-03 | COMP | 2014-01-03 | 2014-01-15 | 59 | 40 | 111498.58
30948556 | OC4 E HIGGINS 1109 - RECONDUCTOR 600 | 09/14/2012 | 106207684 | 09/14/2012 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/29/2013 | ED.15269.1109.RECL | RECLOSERS | 031 | PLACER COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 827.000 | 827.000 | 08J | 2012 | 06/10/2017 | 2017 | 1730 | 247.1429 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2013-06-25 | 2013-06-23 | COMP | 2013-06-25 | 2013-06-25 | COMP | 2013-07-03 | 2013-07-17 | COMP | 2013-07-17 | 2013-07-23 | COMP | 2013-07-23 | 2013-08-02 | COMP | 2013-08-02 | 2013-08-06 | 22 | 20 | 53210.78
30949370 | OC2 REEDLEY 1112: WAKEFIELD OH CNDCTR | 09/19/2012 | 106211014 | 09/18/2012 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/01/2013 | ED.25234.1112 | REEDLEY 1112 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 5,640.000 | 5,640.000 | 08J | 2012 | 06/13/2015 | 2015 | 997 | 142.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2013-08-29 | 2013-08-28 | COMP | 2013-08-29 | 2013-08-29 | COMP | 2013-09-04 | 2013-10-02 | COMP | 2013-10-02 | 2013-10-08 | COMP | 2013-10-08 | 2013-10-28 | COMP | 2013-10-28 | 2013-12-07 | 34 | 66 | 292237.77
30949571 | OC4 GRN VALLEY 2103 WIRE DOWN NEAR 1993 | 09/20/2012 | 106213156 | 09/19/2012 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/27/2013 | ED.08319.2103 | GREEN VALLEY 2103 | 044 | SANTA CRUZ COU | 5532479 | CWSP 08W - Monthly Forecast Only | 798.000 | 0.000 | 08W | 2012 | 03/19/2016 | 2016 | 1276 | 182.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2014-02-23 | 2014-02-23 | COMP | 2014-03-10 | 2014-03-13 | COMP | 2014-03-21 | 2014-04-03 | COMP | 2014-04-03 | 2014-04-09 | COMP | 2014-04-09 | 2014-04-28 | COMP | 2014-04-28 | 2014-04-29 | 39 | 26 | 102498.69
30951870 | 2014 MALAGA 1102 RECONDUCTOR CENTRAL | 10/01/2012 | 106224406 | 10/01/2012 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/30/2013 | ED.25425.1102 | MALAGA 1102 | 010 | FRESNO COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 3,786.000 | 3,786.000 | 08W | 2012 | 11/14/2015 | 2015 | 1139 | 162.7143 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | MALAGA 1102: RECON WIREDOWN CNTRL AVE | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2013-07-26 | 2014-03-17 | COMP | 2013-07-26 | 2014-03-18 | COMP | 2014-04-02 | 2014-04-15 | COMP | 2014-04-15 | 2014-04-18 | COMP | 2014-04-18 | 2015-10-14 | COMP | 2015-10-14 | 2015-10-14 | 263 | 547 | 301521.11
30951944 | OC2 MRCD 1116-PHASE 1 RECOND 12,380' 6CU | 10/01/2012 | 106224417 | 10/01/2012 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/27/2013 | ED.25280.1116 | MERCED 1116 | 024 | MERCED COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 12,566.000 | 12,566.000 | 08J | 2012 | 09/15/2018 | 2018 | 2175 | 310.7143 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2013-09-30 | 2013-09-10 | COMP | 2013-09-25 | 2013-11-22 | COMP | 2013-12-04 | 2013-12-19 | COMP | 2013-12-19 | 2014-01-15 | COMP | 2014-01-15 | 2014-03-03 | COMP | 2014-03-03 | 2014-03-04 | 80 | 75 | 377143.56
30951945 | OC2 +TERMINOUS 1103-RECONDUCTR 13,126 FT | 10/01/2012 | 106224749 | 10/01/2012 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/27/2013 | ED.16302.1103 | TERMINOUS 1103 | 039 | SAN JOAQUIN CO | 5535457 | DO 08 - Monthly Forecast Only | 12,227.000 | 12,711.000 | 08J | 2012 | 11/14/2015 | 2015 | 1139 | 162.7143 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2013-09-11 | 2013-09-11 | COMP | 2013-10-30 | 2013-10-30 | COMP | 2013-11-07 | 2013-12-03 | COMP | 2013-12-03 | 2013-12-27 | COMP | 2013-12-27 | 2015-11-03 | COMP | 2015-11-03 | 2015-11-03 | 83 | 700 | 614137.09
30951993 | OC4 XSPRING VALLEY ROAD WIRE REPLACEMENT | 10/02/2012 | 106224516 | 10/01/2012 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/19/2013 | ED.08319.2103 | GREEN VALLEY 2103 | 044 | SANTA CRUZ COU | 5532479 | CWSP 08W - Monthly Forecast Only | 1,592.000 | 1,592.000 | 08W | 2012 | 03/19/2016 | 2016 | 1264 | 180.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2014-03-13 | 2014-04-09 | COMP | 2014-03-13 | 2014-04-17 | COMP | 2014-05-01 | 2014-05-21 | INPR | 2014-06-19 | 2016-03-19 | # | 2016-03-19 | 2016-03-19 | # | 2016-03-19 | 2016-03-19 | 69 | 668 | 74464.71
30953274 | OC4 OCGC RECOND ANNEALED 6CU-MONTE RIO 1 | 10/09/2012 | 106232601 | 10/08/2012 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/01/2014 | ED.04281.1113.SWIT | SWITCHES | 049 | SONOMA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 3,968.000 | 0.000 | 08J | 2012 | 07/23/2016 | 2016 | 1383 | 197.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30953274_R7 RECOND ANNEALED 6CU - MONTE | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2014-10-23 | 2014-10-23 | COMP | 2015-01-22 | 2015-01-22 | COMP | 2015-01-28 | 2015-02-09 | COMP | 2015-02-09 | 2015-02-24 | COMP | 2015-02-24 | 2015-03-05 | COMP | 2015-03-05 | 2015-04-28 | 109 | 78 | 353965.76
30953959 | OC4 PARADISE 1104 - REPL ANNEALED 6CU | 10/10/2012 | 106241178 | 10/10/2012 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/16/2013 | ED.01423.2102.SWIT | SWITCHES | 004 | BUTTE COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 5,191.000 | 5,191.000 | 08J | 2012 | 10/03/2015 | 2015 | 1088 | 155.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30953959_R4 PARADISE 1104 - REPL ANNEALE | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2014-07-14 | 2014-07-14 | COMP | 2014-07-18 | 2014-08-05 | COMP | 2014-08-07 | 2014-08-29 | COMP | 2014-08-29 | 2014-10-15 | COMP | 2014-10-15 | 2014-10-23 | COMP | 2014-10-23 | 2014-10-27 | 46 | 59 | 746697.63
30954118 | OC4CORNING 1101-SIMPSON RD RECOND PHSE 3 | 10/11/2012 | 106242164 | 10/11/2012 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/15/2013 | ED.85-CC32000000 | TEHEMA MAP CC32 | 052 | TEHAMA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 10,016.000 | 10,636.000 | 08J | 2012 | 05/09/2015 | 2015 | 940 | 134.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2013-04-16 | 2013-04-16 | COMP | 2013-04-24 | 2013-05-03 | COMP | 2013-05-07 | 2013-05-21 | COMP | 2013-05-21 | 2013-05-30 | COMP | 2013-05-30 | 2013-06-24 | COMP | 2013-06-24 | 2013-06-26 | 35 | 36 | 630705.93
30954262 | OC4 2014 MERCED 1116 RECONDUCTOR PH 2 | 10/12/2012 | 106242530 | 10/11/2012 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/02/2013 | ED.25280.1116 | MERCED 1116 | 024 | MERCED COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 10,655.000 | 0.000 | 08J | 2012 | 06/16/2018 | 2018 | 2073 | 296.1429 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | MERCED 1116 RECONDUCTOR PH 2 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2013-08-26 | 2014-03-17 | COMP | 2013-08-26 | 2014-09-09 | COMP | 2014-06-06 | 2014-07-14 | COMP | 2014-07-14 | 2014-07-17 | COMP | 2014-07-17 | 2014-09-12 | COMP | 2014-09-12 | 2014-10-06 | 322 | 84 | 347097.02
30954264 | OC4 2014 MERCED 1116 RECONDUCTOR PH 3 | 10/12/2012 | 106242535 | 10/11/2012 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/02/2013 | ED.25280.1116 | MERCED 1116 | 024 | MERCED COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 7,950.000 | 0.000 | 08J | 2012 | 09/15/2018 | 2018 | 2164 | 309.1429 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | MERCED 1116 RECONDUCTOR PH 3 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2014-08-26 | 2014-08-26 | COMP | 2014-09-02 | 2014-09-02 | COMP | 2014-09-12 | 2014-09-18 | COMP | 2014-09-18 | 2014-09-29 | COMP | 2014-09-29 | 2014-10-13 | COMP | 2014-10-13 | 2014-11-21 | 23 | 64 | 323620.58
30954639 | OC4 TYLER 1103 - FRANZEL ROAD RECONDUCTO | 10/16/2012 | 106243673 | 10/12/2012 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/15/2013 | ED.85-Y330200000 | TEHEMA MAP Y3302 | 052 | TEHAMA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 2,199.000 | 2,199.000 | 08J | 2012 | 06/13/2015 | 2015 | 970 | 138.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30954639_R4 TYLER 1103 - FRANZEL ROAD RE | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2014-07-28 | 2014-07-24 | COMP | 2014-07-28 | 2014-08-08 | COMP | 2014-08-12 | 2014-09-02 | COMP | 2014-09-02 | 2014-12-02 | COMP | 2014-12-02 | 2014-12-09 | COMP | 2014-12-09 | 2014-12-12 | 36 | 101 | 248947.87
30958094 | OCGC RVRBNK1711 4,200FT ANNEALED CONDU | 11/03/2012 | 106277074 | 10/31/2012 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/30/2014 | ED.16319.1711 | RIVERBANK 1711 | 050 | STANISLAUS COU | 5535457 | DO 08 - Monthly Forecast Only | 4,040.000 | 0.000 | 08J | 2012 | 03/21/2020 | 2020 | 2695 | 385 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30958094_R2 RIVERBANK1711 4,200FT ANNEAL | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2014-10-16 | 2014-12-01 | COMP | 2014-10-16 | 2015-02-17 | COMP | 2015-02-17 | 2015-02-17 | COMP | 2015-02-17 | 2017-04-05 | COMP | 2017-04-05 | 2017-04-05 | COMP | 2017-04-05 | 2017-04-05 | 124 | 778 | 211634.19
30958095 | OC4 +VIERRA 1701 ANNEALED CONDUCTR 5,400 | 11/03/2012 | 106277134 | 10/31/2012 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/30/2014 | ED.16270.1701 | VIERRA 1701 | 039 | SAN JOAQUIN CO | 5535457 | DO 08 - Monthly Forecast Only | 4,837.000 | 5,080.000 | 08J | 2012 | 02/06/2016 | 2016 | 1190 | 170 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30958095_R4E VIERRA 1701 ANNEALED CONDUC | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2014-05-08 | 2014-05-08 | COMP | 2014-05-27 | 2014-05-27 | COMP | 2014-06-06 | 2014-07-15 | COMP | 2014-07-15 | 2014-07-21 | COMP | 2014-07-21 | 2016-01-14 | COMP | 2016-01-14 | 2016-01-14 | 68 | 548 | 245864.94
30958720 | OC4 RECONDUCTOR CALISTOGA 1102_ WIRE DW | 11/06/2012 | 106304275 | 11/05/2012 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/30/2014 | ED.04271.1102 | CALISTOGA 1102 | 028 | NAPA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 2,670.000 | 2,670.000 | 08J | 2012 | 06/25/2016 | 2016 | 1327 | 189.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30958720_R7 RECONDUCTOR CALISTOGA 1102_ | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2014-06-17 | 2014-05-23 | COMP | 2014-06-17 | 2014-06-17 | COMP | 2014-06-23 | 2014-07-26 | COMP | 2014-07-26 | 2014-08-01 | COMP | 2014-08-01 | 2014-12-17 | COMP | 2014-12-17 | 2015-02-13 | 39 | 202 | 335383.76
30965676 | OCGC OTTER 1102 ANNEALED CNDCTR PH 1 | 12/11/2012 | 106577591 | 12/10/2012 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/10/2014 | ED.18294.1102 | OTTER 1102 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 4,700.000 | 4,700.000 | 08J | 2012 | 08/11/2018 | 2018 | 2069 | 295.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30965676_R2 OTTER 1102 ANNEALED CONDUCTO | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-07-09 | 2015-07-09 | COMP | 2015-07-28 | 2015-07-28 | COMP | 2015-08-19 | 2015-08-19 | COMP | 2015-08-19 | 2015-09-11 | COMP | 2015-09-11 | 2015-10-05 | COMP | 2015-10-05 | 2015-10-05 | 41 | 47 | 486696.95
30965814 | OC4 ZRECONDUCTOR BW 1101- BTWN 9579 & 95 | 12/12/2012 | 106579371 | 12/11/2012 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/29/2014 | ED.18258.1107 | GOLDTREE 1107 | 040 | SAN LUIS OBISP | 5535457 | DO 08 - Monthly Forecast Only | 4,134.000 | 0.000 | 08J | 2012 | 02/21/2015 | 2015 | 801 | 114.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30965814_R2RECONDUCTOR BW 1101 - BTWN 95 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2014-08-21 | 2014-09-16 | COMP | 2014-08-21 | 2014-09-22 | COMP | 2014-09-25 | 2014-09-30 | COMP | 2014-09-30 | 2014-10-17 | COMP | 2014-10-17 | 2014-10-17 | COMP | 2014-10-17 | 2014-10-24 | 40 | 24 | 344272.03
30965882 | +BAYWOOD RECONDUCTOR (BRIDGE/TICK) | 12/12/2012 | 106579155 | 12/11/2012 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/31/2014 | ED.18280.1101 | BAYWOOD 1101 | 040 | SAN LUIS OBISP | 5535457 | DO 08 - Monthly Forecast Only | 5,216.000 | 5,222.000 | 08J | 2012 | 04/16/2016 | 2016 | 1221 | 174.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30965882_R2 BAYWOOD RECONDUCTOR - SWT 54 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-10-07 | 2015-11-06 | COMP | 2015-10-07 | 2015-12-02 | COMP | 2015-12-02 | 2015-12-10 | COMP | 2015-12-10 | 2016-04-02 | COMP | 2016-04-02 | 2016-04-02 | COMP | 2016-04-02 | 2016-04-04 | 64 | 116 | 381234.27
30966296 | OC4 RECNDANNEALED6CU-MOLIN1102BODEGAHW | 12/14/2012 | 106582356 | 12/14/2012 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 07/01/2014 | ED.04257.1102.SWIT | SWITCHES | 049 | SONOMA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 2,020.000 | 2,020.000 | 08J | 2012 | 06/25/2016 | 2016 | 1289 | 184.1429 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30966296_R4 RECOND ANNEALED 6CU - MOLINO | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2014-06-30 | 2014-06-30 | COMP | 2014-06-30 | 2014-06-30 | COMP | 2014-07-02 | 2014-08-07 | COMP | 2014-08-07 | 2014-08-14 | COMP | 2014-08-14 | 2014-08-18 | COMP | 2014-08-18 | 2014-08-22 | 38 | 15 | 253697.51
30966682 | OCGC XMERK RD, REPL MULTI-SPLICED COND | 12/18/2012 | 106586787 | 12/17/2012 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 01/03/2014 | ED.08369.2104 | ROB ROY 2104 | 044 | SANTA CRUZ COU | 5535457 | DO 08 - Monthly Forecast Only | 1,425.000 | 1,421.000 | 08J | 2012 | 12/26/2015 | 2015 | 1103 | 157.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2014-10-09 | 2014-11-06 | COMP | 2014-10-09 | 2014-12-01 | COMP | 2014-12-10 | 2014-12-10 | COMP | 2014-12-10 | 2014-12-22 | COMP | 2014-12-22 | 2014-12-23 | COMP | 2014-12-23 | 2014-12-24 | 62 | 14 | 70673.47
30967034 | OC4 LINE DOWN - DAVIS 1107 RECON-REFRAME | 12/20/2012 | 106589550 | 12/19/2012 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2013 | ED.06204.1107.TXFR.TROH | OVERHEAD TRANSFORMERS | 057 | YOLO COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 430.000 | 430.000 | 08W | 2012 | 01/31/2015 | 2015 | 772 | 110.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2014-01-10 | 2014-01-10 | COMP | 2014-01-17 | 2014-01-31 | COMP | 2014-02-05 | 2014-02-19 | COMP | 2014-02-19 | 2014-02-24 | COMP | 2014-02-24 | 2014-03-21 | COMP | 2014-03-21 | 2014-04-10 | 40 | 50 | 30107.47
30969076 | OC4 OCGC COTATI 1103 ANNEALED CONDUCTOR | 01/04/2013 | 106614463 | 01/03/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/01/2014 | ED.04227.1103.SWIT | SWITCHES | 049 | SONOMA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 4,055.000 | 4,055.000 | 08J | 2013 | 12/26/2015 | 2015 | 1086 | 155.1429 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30969076_R7 COTATI 1103 ANNEALED CONDUC | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-02-17 | 2015-02-17 | COMP | 2015-02-20 | 2015-02-20 | COMP | 2015-02-25 | 2015-02-25 | COMP | 2015-02-25 | 2015-03-06 | COMP | 2015-03-06 | 2015-03-13 | COMP | 2015-03-13 | 2015-05-20 | 8 | 84 | 355953.62
30971722 | OC4RECNDUCT 2 SP OF WIRE @ MAPLE & CEDAR | 01/16/2013 | 106635433 | 01/14/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 07/26/2013 | ED.08325.2108 | PAUL SWEET 2108 | 044 | SANTA CRUZ COU | 5532479 | CWSP 08W - Monthly Forecast Only | 471.000 | 0.000 | 08W | 2013 | 04/09/2016 | 2016 | 1179 | 168.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2014-09-08 | 2014-09-08 | COMP | 2014-09-17 | 2014-09-22 | COMP | 2014-09-25 | 2014-09-30 | COMP | 2014-09-30 | 2014-10-09 | COMP | 2014-10-09 | 2014-10-11 | COMP | 2014-10-11 | 2014-10-13 | 22 | 13 | 38995
30971802 | OC4 RECONDUCTOR INST FUSES VACA DIXON 11 | 01/17/2013 | 106640881 | 01/17/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2013 | ED.06359.1106.TXFR.TROH | OVERHEAD TRANSFORMERS | 048 | SOLANO COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 872.000 | 900.000 | 08W | 2013 | 01/05/2015 | 2015 | 718 | 102.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2015-01-05 | 2015-01-05 | COMP | 2014-01-23 | 2014-01-23 | COMP | 2014-01-27 | 2014-02-05 | COMP | 2014-02-05 | 2014-02-07 | COMP | 2014-02-07 | 2014-02-13 | COMP | 2014-02-13 | 2014-05-02 | -334 | 86 | 51100.6
30972334 | OP-1101 RECOND_SAN PABLO & O'HATCH (R) | 01/25/2013 | 106656399 | 01/24/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/30/2014 | ED.01426.1101.SWIT | SWITCHES | 001 | ALAMEDA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 746.000 | 1,000.000 | 08W | 2013 | 09/28/2019 | 2019 | 2437 | 348.1429 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-03-16 | 2015-03-25 | COMP | 2015-03-16 | 2015-04-03 | COMP | 2015-04-03 | 2015-04-16 | COMP | 2015-04-16 | 2015-05-01 | COMP | 2015-04-16 | 2015-05-01 | COMP | 2015-04-16 | 2015-05-15 | 31 | 29 | 163292.82
30972547 | OCGC XDEL MONTE 2104 RECOND PORTOLA WD | 01/22/2013 | 106645388 | 01/22/2013 | # | Not assigned | 40 | Closed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 06/06/2014 | ED.18222.2104 | DEL MONTE 2104 | 027 | MONTEREY COUNT | 5532479 | CWSP 08W - Monthly Forecast Only | 590.000 | 0.000 | 08W | 2013 | 10/18/2015 | 2015 | 999 | 142.7143 | CLSD | 12 | E070 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2014-08-26 | 2014-09-12 | COMP | 2014-08-26 | 2014-10-29 | COMP | 2014-10-29 | 2014-10-29 | COMP | 2014-10-29 | 2014-11-03 | COMP | 2014-11-03 | 2014-11-18 | COMP | 2014-11-18 | 2014-11-19 | 64 | 21 | 121269.98
30972641 | WIREDOWN-RECOND-CALWATER 1102 | 01/23/2013 | 106645818 | 01/23/2013 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/25/2014 | ED.25545.1102.CAPA | CAPACITORS | 015 | KERN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 410.000 | 0.000 | 08J | 2013 | # | OPEN | 2872 | 410.2857 | DOCC | 8 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2014-06-06 | 2014-06-06 | INPR | 2018-08-03 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | -41796 | 0 | 16749.71
30972642 | WIREDOWN-RECOND-KERN OIL 1116 | 01/23/2013 | 106645964 | 01/23/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 07/30/2014 | ED.25272.1116.SWIT | SWITCHES | 015 | KERN COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 250.000 | 0.000 | 08W | 2013 | 10/17/2015 | 2015 | 997 | 142.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2014-08-19 | 2014-08-19 | COMP | 2014-08-20 | 2014-08-20 | COMP | 2014-08-20 | 2014-08-20 | COMP | 2014-08-20 | 2014-09-05 | COMP | 2014-09-05 | 2014-11-25 | COMP | 2014-11-25 | 2014-11-25 | 1 | 97 | 25637.52
30972743 | OC4 EL DORADO PH 2101 RELOCATE REGS | 01/23/2013 | # | #N/A | 30881599 | OC4 EL DORADO PH 2101 DETRIORATED CONDUC | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | # | ED.15276.2101.SWIT | SWITCHES | 009 | EL DORADO COUN | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 5.000 | 08J | 2013 | 12/01/2018 | 2018 | 2138 | 305.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2013-11-02 | 2013-07-25 | COMP | 2013-07-25 | 2013-08-20 | COMP | 2013-08-22 | 2013-08-30 | COMP | 2013-08-30 | 2013-09-04 | COMP | 2013-09-04 | 2013-09-15 | COMP | 2013-09-15 | 2013-09-19 | -64 | 20 | 46213.14
30974004 | OC4 DIXON 1103 RECONDUCTOR | 01/29/2013 | 106661251 | 01/29/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 05/30/2014 | ED.06206.1103.SWIT | SWITCHES | 048 | SOLANO COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 689.000 | 0.000 | 08W | 2013 | 10/15/2016 | 2016 | 1355 | 193.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2014-10-16 | 2014-10-16 | COMP | 2014-10-30 | 2014-10-30 | COMP | 2014-11-03 | 2014-11-17 | COMP | 2014-11-17 | 2014-12-01 | COMP | 2014-12-01 | 2014-12-17 | COMP | 2014-12-17 | 2014-12-20 | 32 | 33 | 119934.85
30974165 | OC4 +CABRILLO 1104 WID @ SWT 6365-12-699 | 01/30/2013 | 106662174 | 01/29/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/01/2014 | ED.18310.1104.SWIT | SWITCHES | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 1,908.000 | 0.000 | 08J | 2013 | 08/08/2015 | 2015 | 920 | 131.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30974165_R5 CABRILLO 1104 WID @ SWT 6365 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2014-07-24 | 2014-08-06 | COMP | 2014-07-24 | 2014-08-20 | COMP | 2014-08-29 | 2014-09-12 | COMP | 2014-09-12 | 2014-09-23 | COMP | 2014-09-23 | 2014-10-08 | COMP | 2014-10-08 | 2014-10-11 | 50 | 29 | 138318.46
30974166 | +SLO 1107 WIREDOWN (BOB JONES TRAIL) | 01/30/2013 | 106662171 | 01/29/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 05/02/2014 | ED.18263.1107.SWIT | SWITCHES | 040 | SAN LUIS OBISP | 5532479 | CWSP 08W - Monthly Forecast Only | 1,223.000 | 1,223.000 | 08W | 2013 | 09/03/2016 | 2016 | 1312 | 187.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30974166_R2Z SLO 1107 WIREDOWN@SWT 5041 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-09-11 | 2015-11-23 | COMP | 2015-09-11 | 2015-12-04 | COMP | 2015-12-04 | 2015-12-04 | COMP | 2015-12-04 | 2016-04-14 | COMP | 2016-04-14 | 2016-06-20 | COMP | 2016-06-20 | 2016-06-20 | 84 | 199 | 319906.12
30974168 | OC4 LLAGAS 2101 RECONDUCTOR 4 SPANS | 01/30/2013 | 106662143 | 01/29/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/28/2014 | ED.08318.2101.RECL | RECLOSERS | 043 | SANTA CLARA CO | 5532479 | CWSP 08W - Monthly Forecast Only | 1,146.000 | 0.000 | 08W | 2013 | 04/09/2016 | 2016 | 1165 | 166.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2014-07-02 | 2014-07-02 | COMP | 2014-07-31 | 2014-07-31 | COMP | 2014-08-04 | 2014-08-26 | COMP | 2014-08-26 | 2014-09-08 | COMP | 2014-09-08 | 2014-09-22 | COMP | 2014-09-22 | 2014-09-25 | 55 | 30 | 156970.5
30974172 | OCGC SM 1109 WD LS 45655-HWY 166/BONITA | 01/30/2013 | 106663297 | 01/30/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/07/2014 | ED.18267.1109 | SANTA MARIA 1109 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 2,037.000 | 2,000.000 | 08J | 2013 | 10/17/2015 | 2015 | 990 | 141.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30974172_R5 SM 1109 WD LS 45655 - 12-610 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-05-18 | 2015-05-05 | COMP | 2015-05-18 | 2015-05-18 | COMP | 2015-05-18 | 2015-05-18 | COMP | 2015-08-03 | 2015-08-14 | COMP | 2015-08-14 | 2015-08-14 | COMP | 2015-08-14 | 2015-08-14 | 0 | 88 | 96783.73
30974240 | +SISQUOC 1102 - PH 4 (PHILBRIC RD) | 01/30/2013 | 106663554 | 01/30/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2014 | ED.18281.1102 | SISQUOC 1102 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 2,896.000 | 2,900.000 | 08J | 2013 | 11/05/2016 | 2016 | 1375 | 196.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | R5 SS 1102 WD SS 46173 - 12-75554 - PH 4 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-03-31 | 2016-05-16 | COMP | 2016-03-31 | 2016-05-26 | COMP | 2016-05-26 | 2016-05-31 | COMP | 2016-05-31 | 2016-09-16 | COMP | 2016-09-16 | 2016-09-29 | COMP | 2016-09-29 | 2016-09-30 | 61 | 122 | 172180.75
30974242 | +SISQUOC 1102 - PH 3 (PHILBRIC RD) | 01/30/2013 | 106663552 | 01/30/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2014 | ED.18281.1102 | SISQUOC 1102 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 2,884.000 | 0.000 | 08J | 2013 | 12/10/2016 | 2016 | 1410 | 201.4286 | PREC | 11 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | R5 SIS 1102 WD SS 46173- 12-75554 - PH 3 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-03-31 | 2016-05-17 | COMP | 2016-03-31 | 2016-05-26 | COMP | 2016-05-26 | 2016-05-31 | COMP | 2016-05-31 | 2016-07-18 | COMP | 2016-07-18 | 2016-10-11 | COMP | 2016-10-11 | 2016-10-12 | 61 | 134 | 116395.79
30974244 | OCCC CABRILLO 1104 WD @ 2027 - 12-70056 | 01/30/2013 | 106663901 | 01/30/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/01/2014 | ED.18310.1104.SWIT | SWITCHES | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 2,156.000 | 0.000 | 08J | 2013 | 06/18/2016 | 2016 | 1235 | 176.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30974244_R5 CABRILLO 1104 WD @ 2027 - 12 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-10-25 | 2015-10-25 | COMP | 2015-10-26 | 2015-10-30 | COMP | 2015-10-30 | 2015-10-30 | COMP | 2015-10-30 | 2016-04-26 | COMP | 2016-04-26 | 2016-06-03 | COMP | 2016-06-03 | 2016-06-03 | 5 | 217 | 168651.03
30974245 | OCGC+C 1102 PH 2 (STOWELL & PHILBRIC) | 01/30/2013 | 106663407 | 01/30/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2014 | ED.18281.1102 | SISQUOC 1102 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 2,651.000 | 0.000 | 08J | 2013 | 04/02/2016 | 2016 | 1158 | 165.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30974245_R5 SIS 1102 WD SS 46173 - 12-75 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-06-15 | 2015-08-20 | COMP | 2015-06-15 | 2015-08-27 | COMP | 2015-08-27 | 2015-10-21 | COMP | 2015-10-21 | 2016-03-16 | COMP | 2016-03-16 | 2016-03-16 | COMP | 2016-03-16 | 2016-03-17 | 128 | 148 | 100520.03
30974246 | OC4 SISQUOC 1102 PH. 1 RECND 2593' OF 6C | 01/30/2013 | 106663344 | 01/30/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 05/01/2014 | ED.18281.1102 | SISQUOC 1102 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 3,074.000 | 3,100.000 | 08J | 2013 | 02/14/2015 | 2015 | 745 | 106.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30974246_R5SIS 1102 WD SS 46173 - 12-755 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2014-08-05 | 2014-09-16 | COMP | 2014-08-05 | 2014-09-25 | COMP | 2014-09-30 | 2014-10-15 | COMP | 2014-10-15 | 2014-10-20 | COMP | 2014-10-20 | 2014-11-04 | COMP | 2014-11-04 | 2014-11-10 | 71 | 26 | 98840.26
30974544 | OCGC XSTAR SFTY WK DELMONTE2103 FUSE2489 | 02/01/2013 | 106665376 | 01/31/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2014 | ED.18222.2103 | DEL MONTE 2103 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 2,396.000 | 2,396.000 | 08J | 2013 | 06/16/2018 | 2018 | 1961 | 280.1429 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30974544_R2STAR SAFETY WRK DLMONTE 2103 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2014-08-26 | 2014-10-24 | COMP | 2014-08-26 | 2014-12-15 | COMP | 2015-03-02 | 2015-03-02 | COMP | 2015-05-14 | 2016-05-23 | COMP | 2016-05-23 | 2016-05-23 | COMP | 2016-05-23 | 2016-05-23 | 188 | 448 | 381515.89
30974545 | OCGC STAR SFTY WORK VIEJO 2203 FUSE 6677 | 02/01/2013 | 106665346 | 01/31/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2014 | ED.18285.2203 | VIEJO 2203 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 2,518.000 | 2,518.000 | 08J | 2013 | 07/09/2016 | 2016 | 1254 | 179.1429 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30974545_R2 STAR SAFETY WORK VIEJO 2203 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-11-03 | 2015-11-03 | COMP | 2015-11-06 | 2015-11-16 | COMP | 2015-11-16 | 2015-11-16 | COMP | 2015-11-16 | 2016-04-14 | COMP | 2016-04-14 | 2016-06-10 | COMP | 2016-06-10 | 2016-06-10 | 13 | 207 | 232561.15
30974722 | OC4 DEL MONTE 2102 ELM WIREDWN RECONDUCT | 02/01/2013 | 106666179 | 02/01/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 02/07/2014 | ED.18222.2102 | DEL MONTE 2102 | 027 | MONTEREY COUNT | 5532479 | CWSP 08W - Monthly Forecast Only | 1,056.000 | 0.000 | 08W | 2013 | 12/10/2016 | 2016 | 1408 | 201.1429 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2014-06-23 | 2014-06-23 | COMP | 2014-08-01 | 2014-08-29 | COMP | 2014-09-04 | 2014-09-15 | COMP | 2014-09-15 | 2016-10-17 | COMP | 2016-10-17 | 2016-10-18 | COMP | 2016-10-18 | 2016-12-01 | 84 | 808 | 194520.97
30974723 | OCGC DEL MONTE 2105 VAN BURN WIRE RECON | 02/01/2013 | 106666120 | 02/01/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 02/01/2014 | ED.18222.2105 | DEL MONTE 2105 | 027 | MONTEREY COUNT | 5532479 | CWSP 08W - Monthly Forecast Only | 790.000 | 0.000 | 08W | 2013 | 04/23/2016 | 2016 | 1177 | 168.1429 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2014-07-09 | 2014-07-09 | COMP | 2014-12-03 | 2014-12-03 | COMP | 2014-12-09 | 2014-12-09 | INPR | 2014-12-09 | 2016-04-23 | # | 2016-04-23 | 2016-04-23 | # | 2016-04-23 | 2016-04-23 | 153 | 501 | 153258.33
30974724 | OCGC DEL MNTE 2104 RECTR CORRAL TIERRA | 02/01/2013 | 106665569 | 02/01/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 05/09/2014 | ED.18222.2104 | DEL MONTE 2104 | 027 | MONTEREY COUNT | 5532479 | CWSP 08W - Monthly Forecast Only | 81.000 | 81.000 | 08W | 2013 | 12/26/2015 | 2015 | 1058 | 151.1429 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2014-03-27 | 2014-11-21 | COMP | 2014-03-27 | 2014-12-19 | COMP | 2014-12-19 | 2014-12-19 | COMP | 2014-12-19 | 2014-12-27 | COMP | 2014-12-27 | 2014-12-28 | COMP | 2014-12-28 | 2014-12-29 | 267 | 10 | 24953.43
30974733 | OC2 XREPL COND, BEACH ROAD @ PALM BEACH | 02/01/2013 | 106666589 | 02/01/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/21/2014 | ED.08319.2103 | GREEN VALLEY 2103 | 044 | SANTA CRUZ COU | 5532479 | CWSP 08W - Monthly Forecast Only | 867.000 | 0.000 | 08W | 2013 | 04/11/2015 | 2015 | 799 | 114.1429 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2014-02-27 | 2014-03-25 | COMP | 2014-02-27 | 2014-03-28 | COMP | 2014-04-14 | 2014-04-26 | COMP | 2014-04-26 | 2014-05-06 | COMP | 2014-05-06 | 2014-05-21 | COMP | 2014-05-21 | 2014-05-22 | 58 | 26 | 50838.25
30975060 | OCGC MESA 1102 WD PHASE 2 (AG PUMPS) | 02/03/2013 | 106667402 | 02/02/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/01/2014 | ED.18282.1102 | MESA 1102 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 3,039.000 | 3,039.000 | 08J | 2013 | 10/17/2015 | 2015 | 986 | 140.8571 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | R5 MESA 1102 WD 8953 12-34693 PHASE 2 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-05-06 | 2015-06-01 | COMP | 2015-05-06 | 2015-06-11 | COMP | 2015-06-11 | 2015-06-11 | COMP | 2015-06-11 | 2015-09-11 | COMP | 2015-09-11 | 2015-09-19 | COMP | 2015-09-19 | 2015-09-22 | 36 | 103 | 124424.05
30975188 | OCGC+SLO 1103 WD @ 14125 - 12-70838 | 02/04/2013 | 106662176 | 01/29/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/31/2014 | ED.18263.1103 | SAN LUIS OBISPO 1103 | 040 | SAN LUIS OBISP | 5532479 | CWSP 08W - Monthly Forecast Only | 435.000 | 435.000 | 08W | 2013 | 06/13/2015 | 2015 | 859 | 122.7143 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-02-27 | 2015-02-27 | COMP | 2015-03-10 | 2015-03-10 | COMP | 2015-03-10 | 2015-03-10 | COMP | 2015-03-10 | 2015-03-11 | COMP | 2015-03-11 | 2015-05-16 | COMP | 2015-05-16 | 2015-05-16 | 11 | 67 | 56157.45
30975189 | OC4 OCGC+MESA 1102 WD PH 3 (STATE PARK) | 02/04/2013 | 106667405 | 02/02/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/28/2014 | ED.18282.1102 | MESA 1102 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 4,947.000 | 4,947.000 | 08J | 2013 | 05/14/2016 | 2016 | 1195 | 170.7143 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | R5 MESA 1102 WD 8953 12-34693 PHASE 3 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-07-29 | 2015-08-28 | COMP | 2015-07-29 | 2015-09-10 | COMP | 2015-09-10 | 2015-09-21 | COMP | 2015-09-21 | 2016-04-12 | COMP | 2016-04-12 | 2016-04-22 | COMP | 2016-04-22 | 2016-04-25 | 54 | 217 | 199350.95
30975288 | R1 RECOND.OH 120 BACK ROAD, LA HONDA | 02/08/2013 | 106590552 | 12/20/2012 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 07/02/2014 | ED.06204.1107.RECL | RECLOSERS | 041 | SAN MATEO COUN | 5505513 | PN-OH ANNEALED/DETER CNDCTR: PM MGD | 450.000 | 450.000 | 08J | 2013 | 02/20/2016 | 2016 | 1107 | 158.1429 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2014-12-10 | 2014-12-10 | COMP | 2014-12-30 | 2014-12-30 | COMP | 2015-05-14 | 2015-05-14 | COMP | 2015-05-14 | 2015-09-09 | COMP | 2015-09-09 | 2016-01-25 | COMP | 2016-01-25 | 2016-01-26 | 155 | 257 | 30400.16
30975361 | OC4 OCGC 2014 MCMULLIN 1104 RECONDUCTOR | 02/05/2013 | 106666130 | 02/01/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/14/2014 | ED.25441.1104 | MC MULLIN 1104 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 6,830.000 | 0.000 | 08J | 2013 | 03/19/2016 | 2016 | 1138 | 162.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30975361_R2 MCMULLIN 1104 RECONDUCTORING | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2014-07-22 | 2014-09-03 | COMP | 2014-07-22 | 2015-07-14 | COMP | 2015-07-14 | 2015-07-24 | COMP | 2015-07-24 | 2015-09-09 | COMP | 2015-09-09 | 2016-02-22 | COMP | 2016-02-22 | 2016-02-22 | 367 | 213 | 348379.11
30975432 | OCGC XRECNDUCTR 4 SPS OF WIRE ON WATR ST | 02/05/2013 | 106669286 | 02/05/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/11/2014 | ED.08325.2103 | PAUL SWEET 2103 | 044 | SANTA CRUZ COU | 5535457 | DO 08 - Monthly Forecast Only | 649.000 | 910.000 | 08J | 2013 | 12/26/2015 | 2015 | 1054 | 150.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2014-12-09 | 2015-01-23 | COMP | 2014-12-09 | 2015-03-02 | COMP | 2015-03-02 | 2015-03-02 | COMP | 2015-03-02 | 2015-03-10 | COMP | 2015-03-10 | 2015-03-26 | COMP | 2015-03-26 | 2015-03-27 | 83 | 25 | 90693.02
30975601 | NEWARK 2103 CKT - RECONDUCTOR OH | 02/06/2013 | 106669764 | 02/05/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/25/2013 | ED.01222.2103 | NEWARK 2103 | 001 | ALAMEDA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 400.000 | 0.000 | 08W | 2013 | 01/17/2015 | 2015 | 710 | 101.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2014-03-08 | 2014-03-28 | COMP | 2014-03-08 | 2014-04-03 | COMP | 2014-04-08 | 2014-04-08 | COMP | 2014-04-08 | 2014-04-11 | COMP | 2014-04-11 | 2014-05-12 | COMP | 2014-05-12 | 2014-05-14 | 31 | 36 | 66146.54
30975614 | OC4 HWY68-TORO CAFE 1101 WIREDOWN RECOND | 02/06/2013 | 106669814 | 02/05/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 05/16/2014 | ED.18273.1101 | RESERVATION ROAD 1101 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 280.000 | 560.000 | 08J | 2013 | 04/11/2015 | 2015 | 794 | 113.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2014-03-27 | 2014-09-23 | COMP | 2014-03-27 | 2014-09-26 | COMP | 2014-09-30 | 2014-10-15 | COMP | 2014-10-15 | 2014-10-20 | COMP | 2014-10-20 | 2014-10-23 | COMP | 2014-10-23 | 2014-10-27 | 202 | 12 | 42262.14
30975805 | OCGC XINDUSTRIAL WY ANNEALED COND,KC1102 | 02/06/2013 | 106671294 | 02/06/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2014 | ED.18203.1102 | KING CITY 1102 | 027 | MONTEREY COUNT | 5532479 | CWSP 08W - Monthly Forecast Only | 5,100.000 | 5,250.000 | 08W | 2013 | 12/26/2015 | 2015 | 1053 | 150.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30975805_R2 INDUSTRIAL WAY ANNEALED COND | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2014-11-10 | 2014-12-29 | COMP | 2014-11-10 | 2015-01-14 | COMP | 2015-01-14 | 2015-01-14 | COMP | 2015-01-14 | 2015-01-15 | COMP | 2015-01-15 | 2015-01-22 | COMP | 2015-01-22 | 2015-01-23 | 65 | 9 | 183799.96
30975864 | OC4 OCGC SLY PARK RECOND PH 2 (AH2101) 1 | 02/07/2013 | 106670778 | 02/06/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/03/2014 | ED.15276.2101.SWIT | SWITCHES | 009 | EL DORADO COUN | 5535457 | DO 08 - Monthly Forecast Only | 1,879.000 | 1,879.000 | 08J | 2013 | 08/22/2015 | 2015 | 926 | 132.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30975864_R4E RECONDUCTOR 152762101 6330' | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2014-11-20 | 2014-11-20 | COMP | 2014-12-03 | 2014-12-03 | COMP | 2014-12-08 | 2014-12-08 | COMP | 2014-12-08 | 2014-12-14 | COMP | 2014-12-14 | 2014-12-15 | COMP | 2014-12-15 | 2014-12-18 | 18 | 10 | 212233.13
30975866 | OC4 OCGC SLY PARK RECOND PH 3 (AH2101) 5 | 02/07/2013 | 106670900 | 02/06/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/03/2014 | ED.15276.2101.SWIT | SWITCHES | 009 | EL DORADO COUN | 5535457 | DO 08 - Monthly Forecast Only | 5,839.000 | 5,869.000 | 08J | 2013 | 02/28/2015 | 2015 | 751 | 107.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30975866_R4E RECONDUCTOR 152762101 7420' | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2014-11-20 | 2014-11-20 | COMP | 2014-12-03 | 2014-12-03 | COMP | 2014-12-08 | 2014-12-08 | COMP | 2014-12-08 | 2014-12-14 | COMP | 2014-12-14 | 2014-12-15 | COMP | 2014-12-15 | 2014-12-18 | 18 | 10 | 377359.07
30975871 | OC4 OCGC SLY PARK RECOND PH 1 (AH2101) 4 | 02/07/2013 | # | #N/A | 30969923 | *CANC*RECONDUCTOR15276210115,200' SLYPRK | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | # | ED.15276.2101.SWIT | SWITCHES | 009 | EL DORADO COUN | 5535457 | DO 08 - Monthly Forecast Only | 4,506.000 | 0.000 | 08J | 2013 | 12/19/2015 | 2015 | 1045 | 149.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30975871_R4E RECONDUCTOR 152762101 5,500 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2014-11-20 | 2014-11-20 | COMP | 2014-12-15 | 2014-12-15 | COMP | 2014-12-17 | 2015-01-07 | COMP | 2015-01-07 | 2015-01-16 | COMP | 2015-01-16 | 2015-02-19 | COMP | 2015-02-19 | 2015-02-19 | 48 | 43 | 702644.35
30976210 | OC4 WIREDOWN-RECOND-ELK HILLS 1106 | 02/08/2013 | 106668226 | 02/04/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/01/2013 | ED.25244.1106.CAPA | CAPACITORS | 015 | KERN COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 1,105.000 | 1,295.000 | 08W | 2013 | 04/11/2015 | 2015 | 792 | 113.1429 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2014-03-12 | 2014-03-20 | COMP | 2014-03-12 | 2014-04-02 | COMP | 2014-04-24 | 2014-05-06 | COMP | 2014-05-06 | 2014-05-26 | COMP | 2014-05-26 | 2014-12-19 | COMP | 2014-12-19 | 2014-12-19 | 55 | 227 | 57360.21
30976454 | OC4 OCGC RECON ANNEALED 6C MONTE RIO 13 | 02/09/2013 | # | #N/A | 30966085 | *CANC* R7RECON ANNEALED 6C MONTE RIO 13 | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/01/2014 | ED.04209.1101.SWIT | SWITCHES | 049 | SONOMA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 6,482.000 | 08J | 2013 | 06/25/2016 | 2016 | 1232 | 176 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30976454_R7RECON ANNEALED 6C MONTE RIO 1 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-01-15 | 2015-01-15 | COMP | 2015-01-28 | 2015-01-28 | COMP | 2015-02-06 | 2015-03-06 | COMP | 2015-03-06 | 2015-03-06 | COMP | 2015-03-06 | 2015-03-11 | COMP | 2015-03-11 | 2015-04-29 | 50 | 54 | 606628.97
30976455 | OC4 RECOND ANNEALED 6C HOPLAND 01 PHASE | 02/09/2013 | # | #N/A | 30966087 | *CANC* R7RECOND ANNEALED 6C HOPLAND 01 P | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/01/2014 | ED.04225.1101.RECL | RECLOSERS | 023 | MENDOCINO COUN | 5535457 | DO 08 - Monthly Forecast Only | 10,893.000 | 12,000.000 | 08J | 2013 | 02/18/2017 | 2017 | 1470 | 210 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30976455_R7 RECOND ANNEALED 6C HOPLAND 0 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2014-07-01 | 2014-07-01 | COMP | 2014-10-08 | 2014-10-08 | COMP | 2014-10-10 | 2014-10-27 | COMP | 2014-10-27 | 2014-11-06 | COMP | 2014-11-06 | 2014-12-12 | COMP | 2014-12-12 | 2014-12-22 | 118 | 56 | 835279.93
30976456 | OC4 RECOND DET 6C HOPLAND 01 PHASE 2 | 02/09/2013 | # | #N/A | 30966088 | *CANC* R7RECOND ANNEALED 6C HOPLAND 01 P | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/02/2014 | ED.04225.1101.SWIT | SWITCHES | 023 | MENDOCINO COUN | 5535457 | DO 08 - Monthly Forecast Only | 7,055.000 | 9,055.000 | 08J | 2013 | 06/25/2016 | 2016 | 1232 | 176 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30976456_R7 RECOND DET 6C HOPLAND 01 PHA | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2014-07-24 | 2014-07-24 | COMP | 2014-10-09 | 2014-10-09 | COMP | 2014-10-10 | 2014-10-25 | COMP | 2014-10-25 | 2014-10-29 | COMP | 2014-10-29 | 2014-11-25 | COMP | 2014-11-25 | 2014-12-13 | 93 | 49 | 490287.77
30976458 | OC4RECOND ANNLD 6CU - HOPLAND 01 PHASE 3 | 02/09/2013 | # | #N/A | 30966089 | *CANC* R7 RECOND ANNLD 6CU - HOPLAND 01 | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 08/01/2014 | ED.04225.1101.SWIT | SWITCHES | 023 | MENDOCINO COUN | 5535457 | DO 08 - Monthly Forecast Only | 5,623.000 | 5,623.000 | 08J | 2013 | 06/25/2016 | 2016 | 1232 | 176 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30976458_R7 RECOND ANNLD 6CU - HOPLAND 0 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2014-08-01 | 2014-08-01 | COMP | 2014-10-09 | 2014-10-09 | COMP | 2014-10-10 | 2014-10-25 | COMP | 2014-10-25 | 2014-11-06 | COMP | 2014-11-06 | 2014-12-11 | COMP | 2014-12-11 | 2014-12-22 | 85 | 58 | 507176.77
30976834 | OC4 WIRE DOWN-RECONDUCTOR ANNEALED 6CU | 02/12/2013 | 106684844 | 02/11/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2013 | ED.06288.1102.SWIT | SWITCHES | 006 | COLUSA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 868.000 | 868.000 | 08J | 2013 | 02/14/2015 | 2015 | 732 | 104.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2014-08-25 | 2014-08-25 | COMP | 2014-09-02 | 2014-09-02 | COMP | 2014-09-04 | 2014-09-15 | COMP | 2014-09-15 | 2014-09-19 | COMP | 2014-09-19 | 2014-11-07 | COMP | 2014-11-07 | 2014-11-17 | 21 | 63 | 52966.03
30976836 | OC4 OCGC RICE 1101- RECONDUCTOR ANNEALED | 02/12/2013 | 106684756 | 02/11/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2013 | ED.06283.1101.TXFR.TROH | OVERHEAD TRANSFORMERS | 006 | COLUSA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 2,628.000 | 2,628.000 | 08J | 2013 | 07/23/2016 | 2016 | 1257 | 179.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | RICE 1101 - RECONDUCTOR ANNEALED 4AR | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-01-05 | 2014-11-22 | COMP | 2015-01-05 | 2015-01-06 | COMP | 2015-01-08 | 2015-01-21 | COMP | 2015-01-21 | 2015-01-27 | COMP | 2015-01-27 | 2015-02-23 | COMP | 2015-02-23 | 2015-02-23 | 16 | 33 | 211583.62
30977168 | OC4 OCGC FRNCH CMP 1102 RECOND & RELOCA | 02/13/2013 | 106688549 | 02/13/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/31/2014 | ED.16329.1102 | FRENCH CAMP 1102 | 039 | SAN JOAQUIN CO | 5532479 | CWSP 08W - Monthly Forecast Only | 1,723.000 | 1,215.000 | 08W | 2013 | 02/20/2016 | 2016 | 1102 | 157.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2014-08-20 | 2014-08-20 | COMP | 2014-12-09 | 2014-12-09 | COMP | 2014-12-12 | 2015-01-06 | COMP | 2015-01-06 | 2015-01-15 | COMP | 2015-01-15 | 2016-01-21 | COMP | 2016-01-21 | 2016-01-21 | 139 | 380 | 260893.04
30977169 | OCGC LOCKEFORD 2102 RECONDUCTOR PHASE | 02/13/2013 | 106688542 | 02/13/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/31/2014 | ED.16368.2102 | LOCKEFORD 2102 | 039 | SAN JOAQUIN CO | 5535457 | DO 08 - Monthly Forecast Only | 4,878.000 | 4,880.000 | 08J | 2013 | 08/19/2017 | 2017 | 1648 | 235.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30977169_R4 LOCKEFORD 2102 RECONDUCTOR P | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-02-22 | 2016-02-22 | COMP | 2016-02-23 | 2016-02-23 | COMP | 2016-02-23 | 2016-02-23 | COMP | 2016-02-23 | 2016-04-12 | COMP | 2016-04-12 | 2016-08-17 | COMP | 2016-08-17 | 2016-08-18 | 1 | 177 | 238800.72
30977396 | OCGC XSTAR MODEL ZONE FUSE 9343 RR 2105 | 02/14/2013 | 106689108 | 02/14/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/06/2013 | ED.08369.2105 | ROB ROY 2105 | 044 | SANTA CRUZ COU | 5535457 | DO 08 - Monthly Forecast Only | 714.000 | 382.000 | 08J | 2013 | 10/17/2015 | 2015 | 975 | 139.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2014-09-04 | 2014-10-02 | COMP | 2014-09-04 | 2014-11-22 | COMP | 2014-11-26 | 2014-11-26 | COMP | 2014-11-26 | 2014-12-03 | COMP | 2014-12-03 | 2014-12-05 | COMP | 2014-12-05 | 2014-12-19 | 83 | 23 | 57810.64
30977508 | OCGC REPLACE ANNEALED CONDUCTOR, HWY. 45 | 02/14/2013 | 106685118 | 02/11/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/01/2013 | ED.14-Y230000000 | GLENN MAP Y23 | 011 | GLENN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 1,054.000 | 1,054.000 | 08J | 2013 | 12/17/2016 | 2016 | 1402 | 200.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-05-05 | 2015-05-05 | COMP | 2015-05-07 | 2015-05-07 | COMP | 2015-05-07 | 2015-05-07 | COMP | 2015-05-07 | 2015-05-15 | COMP | 2015-05-15 | 2015-07-30 | COMP | 2015-07-30 | 2015-07-30 | 2 | 84 | 110110.65
30977612 | OCGC OTTER 1102 DETERIORTD CNDUCTR PH 2 | 02/15/2013 | 106691311 | 02/15/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 08/29/2014 | ED.18294.1102 | OTTER 1102 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 3,482.000 | 3,560.000 | 08J | 2013 | 02/13/2016 | 2016 | 1093 | 156.1429 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30977612_R2 OTTER 1102 DETERIORTD CNDUCT | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-07-14 | 2015-07-14 | COMP | 2015-08-06 | 2015-08-06 | COMP | 2015-08-06 | 2015-08-06 | COMP | 2015-08-06 | 2015-09-11 | COMP | 2015-09-11 | 2016-02-03 | COMP | 2016-02-03 | 2016-02-03 | 23 | 181 | 515730.8
30977613 | WDDB OTTER 1102 PHASE 3 | 02/15/2013 | 106691313 | 02/15/2013 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/26/2015 | ED.18294.1102 | OTTER 1102 | 027 | MONTEREY COUNT | 5535211 | CWSP SPO - SH 08 | 3,700.000 | 0.000 | 08W | 2013 | # | OPEN | 2849 | 407 | PEND | 5 | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | 30977613_R2 OTTER 1102 DETERIORTD CNDUCT | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 266249.81
30977614 | WDDB OTTER 1102 PHASE 4 | 02/15/2013 | 106691314 | 02/15/2013 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/17/2015 | ED.18294.1102 | OTTER 1102 | 027 | MONTEREY COUNT | 5535211 | CWSP SPO - SH 08 | 3,681.000 | 0.000 | 08W | 2013 | # | OPEN | 2849 | 407 | UNSC | 6 | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | 30977614_R2 OTTER 1102 DETERIORTD CNDUCT | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 251685.53
30977615 | WDDB OTTER 1102 PHASE 5 | 02/15/2013 | 106691315 | 02/15/2013 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/28/2015 | ED.18294.1102 | OTTER 1102 | 027 | MONTEREY COUNT | 5535211 | CWSP SPO - SH 08 | 2,929.000 | 0.000 | 08W | 2013 | # | OPEN | 2849 | 407 | UNSC | 6 | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | 30977615_R2 OTTER 1102 DETERIORTD CNDUCT | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 195849.51
30977927 | OCGCREPL OH DET WIRE ON JERSEY ISLAND 4 | 02/19/2013 | 106689335 | 02/14/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/31/2014 | ED.01832.0401 | JERSEY ISLAND 0401 | 007 | CONTRA COSTA C | 5535457 | DO 08 - Monthly Forecast Only | 3,381.000 | 0.000 | 08J | 2013 | 06/25/2016 | 2016 | 1222 | 174.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30977927_R1 REPL OH DET WIRE ON JRSEY I | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2014-07-31 | 2014-09-14 | COMP | 2014-07-31 | 2015-01-29 | COMP | 2015-02-18 | 2015-02-18 | COMP | 2015-02-18 | 2015-03-06 | COMP | 2015-03-06 | 2015-04-01 | COMP | 2015-04-01 | 2015-04-01 | 202 | 42 | 277755.9
30978199 | OC4 HMB1102 CO5905 RECONDUCTOR 470 FT | 02/19/2013 | 106691125 | 02/15/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 02/18/2014 | ED.02410.1102.SWIT | SWITCHES | 041 | SAN MATEO COUN | 5535457 | DO 08 - Monthly Forecast Only | 1,081.000 | 1,081.000 | 08W | 2013 | 02/14/2015 | 2015 | 725 | 103.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2014-07-03 | 2014-07-03 | COMP | 2014-07-16 | 2014-07-16 | COMP | 2014-07-22 | 2014-08-22 | COMP | 2014-08-22 | 2014-11-25 | COMP | 2014-11-25 | 2014-12-22 | COMP | 2014-12-22 | 2014-12-26 | 50 | 126 | 182689.15
30978240 | OC4 HMB-1102 CO6097 RECOND 500FT REFRAME | 02/19/2013 | 106691153 | 02/15/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 02/28/2014 | ED.02410.1102.TXFR.TROH | OVERHEAD TRANSFORMERS | 041 | SAN MATEO COUN | 5505513 | PN-OH ANNEALED/DETER CNDCTR: PM MGD | 1,078.000 | 1,349.000 | 08J | 2013 | 11/07/2015 | 2015 | 991 | 141.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2014-05-19 | 2014-05-29 | COMP | 2014-05-19 | 2015-05-08 | COMP | 2014-08-18 | 2014-09-03 | COMP | 2014-09-03 | 2014-09-22 | COMP | 2014-09-22 | 2014-10-13 | COMP | 2014-10-13 | 2014-11-16 | 107 | 74 | 122061.17
30978241 | OC4 BELL HAVEN 401 RECONDUCTOR OH LINE | 02/19/2013 | 106691251 | 02/15/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 02/20/2014 | ED.02402.0401.TXFR.TROH | OVERHEAD TRANSFORMERS | 041 | SAN MATEO COUN | 5505513 | PN-OH ANNEALED/DETER CNDCTR: PM MGD | 2,560.000 | 0.000 | 08J | 2013 | 10/15/2016 | 2016 | 1334 | 190.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30978241_R1_BH-401 RECONDUCTOR 1200FT OH | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2014-08-07 | 2014-09-04 | COMP | 2014-08-07 | 2014-10-08 | COMP | 2014-10-16 | 2014-10-31 | COMP | 2014-10-31 | 2015-09-09 | COMP | 2015-09-09 | 2015-11-23 | COMP | 2015-11-23 | 2015-11-25 | 85 | 390 | 570725.9
30978331 | OCGC OH LR/FUSES <(>&<)> RECON MNLNE CL | 02/19/2013 | 106698894 | 02/19/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/30/2014 | ED.01202.1103 | CLAYTON 1103 | 007 | CONTRA COSTA C | 5535457 | DO 08 - Monthly Forecast Only | 4,807.000 | 9,846.000 | 08J | 2013 | 06/16/2018 | 2018 | 1943 | 277.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30978331_R1 INST OH LR/FUSES & RECON MNL | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2014-07-31 | 2014-10-30 | COMP | 2014-07-31 | 2014-12-29 | COMP | 2015-01-06 | 2015-01-06 | COMP | 2015-01-06 | 2015-02-06 | COMP | 2015-02-06 | 2015-02-27 | COMP | 2015-02-27 | 2015-02-27 | 159 | 52 | 795125.01
30978400 | OC2 RECOND 1100FT DETERIOR 4-0ASPRECKELS | 02/20/2013 | 106702160 | 02/19/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/22/2013 | ED.18226.1102 | BUENA VISTA 1102 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 1,260.000 | 08J | 2013 | 08/05/2017 | 2017 | 1627 | 232.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2013-03-14 | 2013-03-21 | COMP | 2013-03-28 | 2013-03-28 | COMP | 2013-04-08 | 2013-05-06 | COMP | 2013-05-06 | 2013-05-10 | COMP | 2013-05-10 | 2013-06-04 | COMP | 2013-06-04 | 2013-06-04 | 53 | 29 | 26530.79
30978775 | OC4 REPL OH DET WIRE PAST C/O 15261 | 02/22/2013 | 106708405 | 02/21/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/30/2014 | ED.01365.2109 | CONTRA COSTA 2109 | 007 | CONTRA COSTA C | 5535457 | DO 08 - Monthly Forecast Only | 802.000 | 802.000 | 08J | 2013 | 06/25/2016 | 2016 | 1219 | 174.1429 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30978775_REPL OH DET WIRE PAST C/O 1526 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2014-04-28 | 2014-04-17 | COMP | 2014-04-28 | 2014-05-05 | COMP | 2014-06-04 | 2014-06-06 | COMP | 2014-06-06 | 2014-07-14 | COMP | 2014-07-14 | 2014-07-14 | COMP | 2014-07-14 | 2014-07-14 | 39 | 38 | 75024.92
30978845 | OC4 REPL 800' OF ANNEALED 6C PAST C/O459 | 02/22/2013 | 106707433 | 02/21/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2014 | ED.06246.2225.TXFR.TROH | OVERHEAD TRANSFORMERS | 048 | SOLANO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 853.000 | 922.000 | 08J | 2013 | 07/21/2018 | 2018 | 1975 | 282.1429 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2014-12-19 | 2014-12-19 | COMP | 2014-12-19 | 2014-12-19 | COMP | 2014-12-23 | 2015-01-24 | COMP | 2015-01-24 | 2015-01-30 | COMP | 2015-01-30 | 2015-02-03 | COMP | 2015-02-03 | 2015-02-09 | 36 | 16 | 66536.21
30978886 | OCGC RECONDUCTOR TO REMOVE SPLICES | 02/22/2013 | 106713703 | 02/22/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/01/2014 | ED.08337.1106.SWIT | SWITCHES | 043 | SANTA CLARA CO | 5532479 | CWSP 08W - Monthly Forecast Only | 1,031.000 | 0.000 | 08W | 2013 | 12/26/2015 | 2015 | 1037 | 148.1429 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-05-17 | 2015-05-17 | COMP | 2015-05-21 | 2015-05-21 | COMP | 2015-05-21 | 2015-05-21 | COMP | 2015-05-21 | 2015-05-28 | COMP | 2015-05-28 | 2015-08-12 | COMP | 2015-08-12 | 2015-08-12 | 4 | 83 | 162877.11
30979240 | OCGC XRECON 4 SPS OF WR GLEENWOOD-CE2106 | 02/24/2013 | 106721990 | 02/23/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/27/2014 | ED.08362.2106 | CAMP EVERS 2106 | 044 | SANTA CRUZ COU | 5532479 | CWSP 08W - Monthly Forecast Only | 783.000 | 733.000 | 08W | 2013 | 12/13/2015 | 2015 | 1022 | 146 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2014-02-05 | 2014-02-05 | COMP | 2015-02-25 | 2015-02-25 | COMP | 2015-02-25 | 2015-02-25 | COMP | 2015-02-25 | 2015-03-05 | COMP | 2015-03-05 | 2015-03-17 | COMP | 2015-03-17 | 2015-03-17 | 385 | 20 | 132806.31
30979241 | OCGC XRECON 2 SPN@GRNITE CRK/HWY17 S VLY | 02/24/2013 | 106721991 | 02/23/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/26/2014 | ED.08362.2104 | CAMP EVERS 2104 | 044 | SANTA CRUZ COU | 5532479 | CWSP 08W - Monthly Forecast Only | 350.000 | 0.000 | 08W | 2013 | 10/17/2015 | 2015 | 965 | 137.8571 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2014-09-12 | 2014-10-17 | COMP | 2014-09-12 | 2014-11-22 | COMP | 2014-11-22 | 2014-11-22 | COMP | 2014-11-22 | 2014-12-03 | COMP | 2014-12-03 | 2014-12-10 | COMP | 2014-12-10 | 2014-12-19 | 71 | 27 | 41233.4
30979379 | +RECNDUCTR TO REMOVE SPLICES VASONA 110 | 02/25/2013 | 106723171 | 02/25/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/01/2013 | ED.08377.1105 | VASONA 1105 | 043 | SANTA CLARA CO | 5532479 | CWSP 08W - Monthly Forecast Only | 871.000 | 0.000 | 08W | 2013 | 05/14/2016 | 2016 | 1174 | 167.7143 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2014-08-08 | 2014-08-08 | COMP | 2014-08-11 | 2016-01-20 | COMP | 2016-01-20 | 2016-01-20 | COMP | 2016-01-20 | 2016-01-21 | COMP | 2016-01-21 | 2016-01-25 | COMP | 2016-01-25 | 2016-01-25 | 530 | 5 | 95309.21
30979413 | *CANC*CABRILLO 1104 WD 12-27130 *CANC | 02/26/2013 | 106729324 | 02/25/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/01/2014 | ED.18310.1104 | CABRILLO 1104 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2013 | 11/03/2018 | 2018 | 2076 | 296.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2018-11-03 | 2018-11-03 | # | 2018-11-03 | 2018-11-03 | # | 2018-11-03 | 2018-11-03 | COMP | 2018-11-02 | 2018-11-02 | COMP | 2018-11-02 | 2018-11-02 | COMP | 2018-11-02 | 2018-11-02 | 0 | -1 | 0
30979415 | +MB 1101 (MORRO BAY STATE PARK) | 02/26/2013 | 106729326 | 02/25/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/01/2014 | ED.18301.1101 | MORRO BAY 1101 | 040 | SAN LUIS OBISP | 5535457 | DO 08 - Monthly Forecast Only | 3,233.000 | 3,233.000 | 08J | 2013 | 07/02/2016 | 2016 | 1222 | 174.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | R5 MB 1101 WD 12-50404 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-12-21 | 2015-12-16 | COMP | 2015-10-29 | 2015-12-21 | COMP | 2015-12-21 | 2015-12-28 | COMP | 2015-12-28 | 2016-04-17 | COMP | 2016-04-17 | 2016-06-27 | COMP | 2016-06-27 | 2016-06-28 | 7 | 183 | 334919.66
30979416 | +CAYUCOS 1102 (PACIFIC ST - HOTELS) | 02/26/2013 | 106729328 | 02/25/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/01/2014 | ED.18255.1101 | CAYUCOS 1101 | 040 | SAN LUIS OBISP | 5535457 | DO 08 - Monthly Forecast Only | 1,268.000 | 1,200.000 | 08J | 2013 | 08/27/2016 | 2016 | 1278 | 182.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30979416_R5 CAYUCOS 1102 WD 12-69012 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-05-14 | 2016-03-17 | COMP | 2015-05-14 | 2016-03-29 | COMP | 2016-03-29 | 2016-03-29 | COMP | 2016-03-29 | 2016-04-12 | COMP | 2016-04-12 | 2016-08-16 | COMP | 2016-08-16 | 2016-08-17 | 320 | 141 | 140761.56
30979480 | X RECN 3000' OF 6CU ON GLNCANYON CE2103 | 02/25/2013 | 106721992 | 02/23/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/29/2017 | ED.08362.2103 | CAMP EVERS 2103 | 044 | SANTA CRUZ COU | 5535457 | DO 08 - Monthly Forecast Only | 3,659.000 | 3,600.000 | 08J | 2013 | 03/16/2019 | 2019 | 2210 | 315.7143 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30979480_2 RECN 3000' OF 6CU ON GLNCANY | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2017-08-27 | 2017-08-27 | COMP | 2017-09-11 | 2017-09-11 | COMP | 2017-09-11 | 2017-09-12 | COMP | 2017-09-12 | 2017-09-13 | COMP | 2017-09-13 | 2017-11-27 | COMP | 2017-11-27 | 2017-11-27 | 16 | 76 | 387990.78
30979520 | OCGC FAIRWAY 1108 RECON (LAKEVIEW & BRAD | 02/26/2013 | 106729325 | 02/25/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/01/2014 | ED.18206.1108 | FAIRWAY 1108 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 817.000 | 817.000 | 08J | 2013 | 05/14/2016 | 2016 | 1173 | 167.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | R5 FAIRWAY 1108 RECONDUCTOR SANTA MARIA | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-06-15 | 2015-07-15 | COMP | 2015-06-15 | 2015-07-16 | COMP | 2015-07-16 | 2015-07-16 | COMP | 2015-07-16 | 2015-10-08 | COMP | 2015-10-08 | 2015-10-08 | COMP | 2015-10-08 | 2015-10-16 | 31 | 92 | 142201.67
30979558 | OC4 RECONDUCTOR OH MAINLINE CL 1103 | 02/26/2013 | 106729138 | 02/25/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/30/2014 | ED.01202.1103 | CLAYTON 1103 | 007 | CONTRA COSTA C | 5535457 | DO 08 - Monthly Forecast Only | 3,100.000 | 3,100.000 | 08J | 2013 | 06/25/2016 | 2016 | 1215 | 173.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30979558_R1 RECONDUCTOR OH MAINLINE CL 1 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2014-08-26 | 2014-08-18 | COMP | 2014-08-26 | 2014-08-26 | COMP | 2014-12-16 | 2015-01-23 | COMP | 2015-01-23 | 2015-02-06 | COMP | 2015-02-06 | 2015-02-28 | COMP | 2015-02-28 | 2015-02-28 | 150 | 36 | 695075.66
30979723 | OC4 OCGC EB-R1125 RELIABILITY PROJECT ( | 02/26/2013 | 106729841 | 02/26/2013 | # | Not assigned | 40 | Closed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/22/2014 | ED.01347.1125.SWIT | SWITCHES | 007 | CONTRA COSTA C | 5535457 | DO 08 - Monthly Forecast Only | 5,000.000 | 4,866.000 | 08J | 2013 | 07/14/2018 | 2018 | 1964 | 280.5714 | CLSD | 12 | E070 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30979723_R1-EB-RELIABILITY-RECOND R1125 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-09-11 | 2015-09-11 | COMP | 2015-10-12 | 2015-10-12 | COMP | 2015-10-16 | 2015-10-16 | COMP | 2015-10-16 | 2015-11-17 | COMP | 2015-11-17 | 2016-11-10 | COMP | 2016-11-10 | 2016-11-10 | 35 | 391 | 1793122.66
30979750 | OCGC XHATTON1102 STAR XX PTRL FUSE 8947 | 02/26/2013 | 106729712 | 02/26/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2014 | ED.18229.1102 | HATTON 1102 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 1,682.000 | 2,200.000 | 08J | 2013 | 09/23/2017 | 2017 | 1670 | 238.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30979750_R2 HATTON 1102 STAR XX PATROL F | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2014-11-25 | 2015-01-16 | COMP | 2014-11-25 | 2015-02-25 | COMP | 2015-05-17 | 2015-05-17 | COMP | 2015-05-17 | 2015-06-09 | COMP | 2015-06-09 | 2015-11-24 | COMP | 2015-11-24 | 2015-12-21 | 173 | 218 | 318972.97
30979782 | OC4 ORCHARD RD RECONDUCTOR RM 1101 | 02/27/2013 | 106732361 | 02/26/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 05/31/2014 | ED.01416.1101 | ROSSMOOR 1101 | 007 | CONTRA COSTA C | 5535457 | DO 08 - Monthly Forecast Only | 1,268.000 | 1,268.000 | 08J | 2013 | 05/14/2016 | 2016 | 1172 | 167.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 2014 ORCHARD RD RECONDUCTOR RM 1101 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2014-05-30 | 2014-07-30 | COMP | 2014-05-30 | 2014-10-10 | COMP | 2014-10-15 | 2014-11-04 | COMP | 2014-11-04 | 2014-11-13 | COMP | 2014-11-13 | 2014-11-18 | COMP | 2014-11-18 | 2014-11-18 | 158 | 14 | 197758.06
30979783 | OCGC2014 HOUGH AVE OH RECONDUCTOR | 02/27/2013 | 106690945 | 02/15/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/01/2014 | ED.01416.1106 | ROSSMOOR 1106 | 007 | CONTRA COSTA C | 5535457 | DO 08 - Monthly Forecast Only | 937.000 | 937.000 | 08J | 2013 | 10/24/2016 | 2016 | 1335 | 190.7143 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30979783_R1 2014 HOUGH AVE OH RECONDUCTO | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-01-26 | 2015-01-26 | COMP | 2015-02-03 | 2015-02-03 | COMP | 2015-02-03 | 2015-02-03 | COMP | 2015-02-03 | 2015-04-11 | COMP | 2015-04-11 | 2015-04-16 | COMP | 2015-04-16 | 2015-04-16 | 8 | 72 | 490063.07
30979785 | OCGCLANCASTER RECONDUCTOR RM 1107 | 02/27/2013 | 106702142 | 02/19/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/30/2014 | ED.01416.1107 | ROSSMOOR 1107 | 007 | CONTRA COSTA C | 5535457 | DO 08 - Monthly Forecast Only | 3,249.000 | 0.000 | 08J | 2013 | 06/25/2016 | 2016 | 1214 | 173.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30979785_R1 2014 LANCASTER RECONDUCTOR R | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2014-09-02 | 2014-12-16 | COMP | 2014-09-02 | 2015-02-06 | COMP | 2015-02-06 | 2015-02-06 | COMP | 2015-02-06 | 2015-02-11 | COMP | 2015-02-11 | 2015-03-17 | COMP | 2015-03-17 | 2015-03-17 | 157 | 39 | 504045.08
30979786 | OC4 2014 SINGINGWOOD CT OH RECON RM 1103 | 02/27/2013 | 106702143 | 02/19/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/30/2014 | ED.01416.1103 | ROSSMOOR 1103 | 007 | CONTRA COSTA C | 5535457 | DO 08 - Monthly Forecast Only | 1,004.000 | 1,007.000 | 08J | 2013 | 06/25/2016 | 2016 | 1214 | 173.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30979786_R1 2014 SINGINGWOOD CT OH RECON | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2014-07-28 | 2014-08-15 | COMP | 2014-07-28 | 2014-10-20 | COMP | 2014-10-22 | 2014-11-06 | COMP | 2014-11-06 | 2014-11-13 | COMP | 2014-11-13 | 2014-11-19 | COMP | 2014-11-19 | 2014-11-19 | 101 | 13 | 230437.42
30979787 | OCGC2014 CASTLE CR RD RECONDUCTOR LW2224 | 02/27/2013 | 106731963 | 02/26/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/22/2014 | ED.01353.2224 | LAKEWOOD 2224 | 007 | CONTRA COSTA C | 5532479 | CWSP 08W - Monthly Forecast Only | 583.000 | 0.000 | 08W | 2013 | 06/25/2016 | 2016 | 1214 | 173.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30979787_R1 2014 CASTLE CR RD RECONDUCT | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2014-07-31 | 2014-09-03 | COMP | 2014-07-31 | 2015-01-29 | COMP | 2015-02-17 | 2015-02-17 | COMP | 2015-02-17 | 2015-03-06 | COMP | 2015-03-06 | 2015-03-25 | COMP | 2015-03-25 | 2015-03-25 | 201 | 36 | 146850.96
30979877 | OC4 CORNING 1101 RECONDUCTOR - PHASE 4 | 02/27/2013 | 106706600 | 02/20/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/01/2014 | ED.85-CC31000000 | TEHEMA MAP CC31 | 052 | TEHAMA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 10,642.000 | 10,642.000 | 08J | 2013 | 05/09/2015 | 2015 | 801 | 114.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30979877_CORNING 1101 RECONDUCTOR - PHAS | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2014-02-27 | 2014-02-27 | COMP | 2014-08-11 | 2014-08-11 | COMP | 2014-08-15 | 2014-09-03 | COMP | 2014-09-03 | 2014-09-05 | COMP | 2014-09-05 | 2014-10-01 | COMP | 2014-10-01 | 2014-10-02 | 188 | 29 | 732268.57
30979878 | OC4 CORNING 1101 PH 5 RECON 11684' Y2015 | 02/27/2013 | 106706620 | 02/20/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/01/2014 | ED.85-CC30000000 | TEHEMA MAP CC30 | 052 | TEHAMA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 11,856.000 | 13,281.000 | 08J | 2013 | 03/17/2018 | 2018 | 1844 | 263.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30979878_CORNING 1101 RECONDUCTOR - PHAS | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-01-21 | 2016-01-21 | COMP | 2016-02-01 | 2016-02-03 | COMP | 2016-02-05 | 2016-02-05 | COMP | 2016-02-05 | 2016-04-15 | COMP | 2016-04-15 | 2016-08-09 | COMP | 2016-08-09 | 2016-08-16 | 15 | 193 | 798799.64
30979879 | RECON 11000'-CORNING 1101 PHASE 6 Y2016 | 02/27/2013 | 106706623 | 02/20/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/01/2014 | ED.85-CC29000000 | TEHEMA MAP CC29 | 052 | TEHAMA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 231,860.000 | 11,290.000 | 08J | 2013 | 02/25/2017 | 2017 | 1459 | 208.4286 | PREC | 11 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30979879_CORNING 1101 RECONDUCTOR - PHAS | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-09-28 | 2016-09-28 | COMP | 2016-10-04 | 2016-10-04 | COMP | 2016-10-04 | 2016-10-04 | COMP | 2016-10-04 | 2016-10-07 | COMP | 2016-10-07 | 2017-02-23 | COMP | 2017-02-23 | 2017-02-23 | 6 | 142 | 492817.26
30979948 | X REPL DET COND, BEACH & SAN ANDREAS | 02/27/2013 | 106743015 | 02/27/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/25/2014 | ED.08319.2103 | GREEN VALLEY 2103 | 044 | SANTA CRUZ COU | 5535457 | DO 08 - Monthly Forecast Only | 2,240.000 | 0.000 | 08J | 2013 | 08/19/2017 | 2017 | 1634 | 233.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-11-25 | 2015-11-19 | COMP | 2015-11-25 | 2015-12-01 | COMP | 2015-12-01 | 2015-12-01 | COMP | 2015-12-01 | 2016-04-27 | COMP | 2016-04-27 | 2016-06-14 | COMP | 2016-06-14 | 2016-06-14 | 6 | 196 | 186541.52
30979950 | OC4 MIDDLE RVR 1103 RECONDUCTOR PHASE-1 | 02/27/2013 | 106741099 | 02/27/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2014 | ED.16209.1103 | MIDDLE RIVER 1103 | 039 | SAN JOAQUIN CO | 5517127 | DO 08 - Monthly Forecast Only | 9,635.000 | 9,635.000 | 08J | 2013 | 03/19/2016 | 2016 | 1116 | 159.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | R2 MIDDLE RVR RECNDUCTORING | Base Capital | GRC Distribution Common | GRC | CUSTCARE | Electric Distribution | Electric Distribution | COMP | 2014-10-08 | 2014-10-08 | COMP | 2014-10-20 | 2014-10-20 | COMP | 2014-10-27 | 2014-11-12 | COMP | 2014-11-12 | 2015-07-15 | COMP | 2015-07-15 | 2016-02-11 | COMP | 2016-02-11 | 2016-02-11 | 35 | 456 | 523898.84
30979951 | OC4 MIDDLE RVR 1103 RECNDUCTORING PHASE- | 02/27/2013 | 106741111 | 02/27/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2014 | ED.16209.1103 | MIDDLE RIVER 1103 | 039 | SAN JOAQUIN CO | 5517127 | DO 08 - Monthly Forecast Only | 6,025.000 | 6,025.000 | 08J | 2013 | 03/14/2015 | 2015 | 745 | 106.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | R2 MIDDLE RVR RECNDUCTORING | Base Capital | GRC Distribution Common | GRC | CUSTCARE | Electric Distribution | Electric Distribution | COMP | 2014-10-02 | 2014-10-02 | COMP | 2014-10-24 | 2014-10-24 | COMP | 2014-10-28 | 2014-11-12 | COMP | 2014-11-12 | 2014-11-24 | COMP | 2014-11-24 | 2015-02-25 | COMP | 2015-02-25 | 2015-02-25 | 41 | 105 | 326881
30979952 | OCGC MIDDLE RVR 1101 RECONDUCTORING | 02/27/2013 | 106741116 | 02/27/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2014 | ED.16209.1101 | MIDDLE RIVER 1101 | 039 | SAN JOAQUIN CO | 5535457 | DO 08 - Monthly Forecast Only | 5,282.000 | 5,282.000 | 08J | 2013 | 12/10/2016 | 2016 | 1382 | 197.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Middle River 1101 Reconductor | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-06-02 | 2016-06-02 | COMP | 2016-06-08 | 2016-06-08 | COMP | 2016-06-08 | 2016-06-08 | COMP | 2016-06-08 | 2016-07-29 | COMP | 2016-07-29 | 2016-10-17 | COMP | 2016-10-17 | 2016-12-01 | 6 | 176 | 362043.66
30979962 | OC4 CORNING 1102 RECONDUCTOR - PHASE 1 | 02/27/2013 | 106706629 | 02/20/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/01/2014 | ED.85-DD28000000 | TEHEMA MAP DD28 | 052 | TEHAMA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 4,793.000 | 4,793.000 | 08J | 2013 | 12/16/2017 | 2017 | 1753 | 250.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30979962_CORNING 1102 RECONDUCTOR - PHAS | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2014-03-11 | 2014-03-11 | COMP | 2014-03-28 | 2014-03-28 | COMP | 2014-04-02 | 2014-04-15 | COMP | 2014-04-15 | 2014-04-18 | COMP | 2014-04-18 | 2014-05-06 | COMP | 2014-05-06 | 2014-05-07 | 35 | 22 | 279087.95
30979968 | OCGCCORNING 1102- PH 2 REC 11,300' Y2015 | 02/27/2013 | 106706650 | 02/20/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/01/2014 | ED.85-DD29000000 | TEHEMA MAP DD29 | 052 | TEHAMA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 11,455.000 | 11,455.000 | 08J | 2013 | 01/28/2017 | 2017 | 1431 | 204.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30979968_CORNING 1102 RECONDUCTOR - PHAS | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-02-16 | 2016-02-16 | COMP | 2016-02-22 | 2016-02-22 | COMP | 2016-02-22 | 2016-02-22 | COMP | 2016-02-22 | 2016-04-13 | COMP | 2016-04-13 | 2016-08-10 | COMP | 2016-08-10 | 2016-08-11 | 6 | 171 | 770459.16
30980058 | RECON SR2108 BOLLINGER CANYON | 02/28/2013 | 106689725 | 02/14/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/26/2014 | ED.24-G121600000.STRU | MISSION MAP G1216 STRUCTURE | 007 | CONTRA COSTA C | 5535457 | DO 08 - Monthly Forecast Only | 1,967.000 | 1,966.000 | 08J | 2013 | 09/15/2018 | 2018 | 2025 | 289.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2014-10-28 | 2014-12-18 | COMP | 2014-10-28 | 2015-01-05 | COMP | 2015-12-04 | 2015-12-04 | COMP | 2015-12-04 | 2016-01-27 | COMP | 2016-01-27 | 2016-01-27 | COMP | 2016-01-27 | 2016-01-30 | 402 | 57 | 177975.67
30980068 | 285 LITTLEFIELD AVE SSF | 02/28/2013 | 106690953 | 02/15/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/25/2013 | ED.56-E041000000 | SKYLINE MAP E0410 | 041 | SAN MATEO COUN | 5535457 | DO 08 - Monthly Forecast Only | 369.000 | 352.000 | 08W | 2013 | 02/14/2015 | 2015 | 716 | 102.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2014-03-15 | 2014-03-15 | COMP | 2014-03-25 | 2014-03-25 | COMP | 2014-03-25 | 2014-03-25 | COMP | 2014-03-25 | 2014-12-22 | COMP | 2014-12-22 | 2014-12-22 | COMP | 2014-12-22 | 2014-12-22 | 10 | 272 | 25773.51
30980069 | R1 MB-1106 RECONDUCTORING | 02/28/2013 | 106690975 | 02/15/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/28/2014 | ED.56-F051200000 | SKYLINE MAP F0512 | 041 | SAN MATEO COUN | 5535457 | DO 08 - Monthly Forecast Only | 88.000 | 88.000 | 08W | 2013 | 02/20/2016 | 2016 | 1087 | 155.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2014-08-04 | 2014-08-28 | COMP | 2014-08-04 | 2014-09-17 | COMP | 2015-02-18 | 2015-02-18 | COMP | 2015-02-18 | 2015-09-09 | COMP | 2015-09-09 | 2016-01-21 | COMP | 2016-01-21 | 2016-01-22 | 198 | 338 | 40367.42
30980093 | OCGC HORSESHOE 1106 RECOND - 7585 STAR | 02/28/2013 | 106746211 | 02/28/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/13/2014 | ED.15257.1106 | HORSESHOE 1106 | 031 | PLACER COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 2,390.000 | 2,390.000 | 08J | 2013 | 04/23/2016 | 2016 | 1150 | 164.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30980093_STAR-HORSESHOE 1106 -7585_08J | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-07-01 | 2015-06-25 | COMP | 2015-07-01 | 2015-07-08 | COMP | 2015-07-08 | 2015-07-08 | COMP | 2015-07-08 | 2015-09-10 | COMP | 2015-09-10 | 2016-03-17 | COMP | 2016-03-17 | 2016-04-08 | 7 | 275 | 271105.46
30980105 | OC4ORO FINO 1102 - 727FT OF ANNEALED 2AR | 02/28/2013 | 106744320 | 02/27/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/26/2014 | ED.17-Q33G000000 | PARADISE MAP Q33G | 004 | BUTTE COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 420.000 | 420.000 | 08J | 2013 | 01/17/2015 | 2015 | 688 | 98.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2014-06-13 | 2014-06-13 | COMP | 2014-06-16 | 2014-07-01 | COMP | 2014-07-07 | 2014-08-12 | COMP | 2014-08-12 | 2014-08-14 | COMP | 2014-08-14 | 2014-08-26 | COMP | 2014-08-26 | 2014-09-05 | 60 | 24 | 62706.9
30980106 | OCGC 1102 - 5100FT ANNEAL COND 2016 | 02/28/2013 | 106744323 | 02/27/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/26/2014 | ED.17-Q330000000 | PARADISE MAP Q33 | 004 | BUTTE COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 5,357.000 | 5,357.000 | 08J | 2013 | 12/16/2017 | 2017 | 1752 | 250.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30980106_Oro Fino 1102 08J | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-09-29 | 2016-09-29 | COMP | 2016-10-10 | 2016-10-10 | COMP | 2016-10-10 | 2016-10-10 | COMP | 2016-10-10 | 2016-10-13 | COMP | 2016-10-13 | 2017-01-31 | COMP | 2017-01-31 | 2017-02-17 | 11 | 130 | 638469.21
30980124 | OC4 NORD 1104 - RECOND 5400FT OF 2CU | 02/28/2013 | 106742838 | 02/27/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/29/2014 | ED.16-T26A000000 | CHICO MAP T26A | 004 | BUTTE COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 5,475.000 | 5,475.000 | 08J | 2013 | 07/29/2017 | 2017 | 1612 | 230.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30980124_R6 NORD 1104 - RECOND 5400FT OF | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2014-06-13 | 2014-06-13 | COMP | 2014-06-16 | 2014-06-17 | COMP | 2014-06-24 | 2014-07-29 | COMP | 2014-07-29 | 2014-07-31 | COMP | 2014-07-31 | 2014-08-25 | COMP | 2014-08-25 | 2014-09-05 | 46 | 38 | 606702.08
30980127 | OC4 R4 NORD 1104 - RECOND 9300FT OF 6CU | 02/28/2013 | 106742970 | 02/27/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/25/2014 | ED.16-S260000000 | CHICO MAP S26 | 004 | BUTTE COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 9,300.000 | 08J | 2013 | 06/13/2015 | 2015 | 835 | 119.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30980127_R6 NORD 1104 - RECOND 9300FT OF | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2014-05-12 | 2014-05-12 | COMP | 2014-05-13 | 2014-05-23 | COMP | 2014-05-30 | 2014-07-01 | COMP | 2014-07-01 | 2014-07-03 | COMP | 2014-07-03 | 2014-07-11 | COMP | 2014-07-11 | 2014-07-23 | 50 | 22 | 599148.73
30980133 | OCGC DAME 1104-9300' ANNE 2AR Y2016 | 02/28/2013 | 106744327 | 02/27/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/31/2014 | ED.16-R310000000 | CHICO MAP R31 | 004 | BUTTE COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 9,300.000 | 9,300.000 | 08J | 2013 | 04/22/2017 | 2017 | 1514 | 216.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30980133_Notre Dame 1104 Recond. 9300ft_ | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-07-29 | 2016-07-29 | COMP | 2016-08-15 | 2016-08-16 | COMP | 2016-08-16 | 2016-08-16 | COMP | 2016-08-16 | 2016-08-25 | COMP | 2016-08-25 | 2017-01-31 | COMP | 2017-01-31 | 2017-02-08 | 18 | 176 | 724636.48
30980173 | OCGC RECONDUCTOR, 152561107, KING ROAD | 02/28/2013 | 106746468 | 02/28/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/13/2014 | ED.15256.1107 | PENRYN 1107 | 031 | PLACER COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 3,145.000 | 3,145.000 | 08J | 2013 | 03/03/2018 | 2018 | 1829 | 261.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30980173_R4E RECONDUCTOR, 152561107, KIN | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2014-12-12 | 2014-12-12 | COMP | 2014-12-30 | 2014-12-30 | COMP | 2015-04-22 | 2015-04-22 | COMP | 2015-01-07 | 2015-01-07 | COMP | 2015-01-07 | 2015-01-22 | COMP | 2015-01-22 | 2015-02-08 | 131 | -73 | 273732.18
30980185 | OC4 REPLACE ANNEALED CONDUCTOR, LAUREL S | 02/28/2013 | 106744758 | 02/28/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/01/2014 | ED.14-Y191200000 | GLENN MAP Y1912 | 011 | GLENN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 4,480.000 | 4,480.000 | 08J | 2013 | 10/10/2015 | 2015 | 954 | 136.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30980185_R6 REPLACE ANNEALED CONDUCTOR, | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2014-08-12 | 2014-08-12 | COMP | 2014-08-28 | 2014-08-28 | COMP | 2014-09-03 | 2014-09-12 | COMP | 2014-09-12 | 2014-09-15 | COMP | 2014-09-15 | 2014-10-20 | COMP | 2014-10-20 | 2014-11-05 | 31 | 54 | 535026.86
30980186 | OCGC CON. 5395', HWY. 45 PH. 2 Y2017 | 02/28/2013 | 106744759 | 02/28/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 05/30/2017 | ED.14-Y230000000 | GLENN MAP Y23 | 011 | GLENN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 5,395.000 | 5,395.000 | 08J | 2013 | 01/26/2019 | 2019 | 2158 | 308.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30980186_Y2016 HWY 45 PH 2 Glen County_8 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2017-05-23 | 2017-05-23 | COMP | 2017-05-23 | 2017-05-23 | COMP | 2017-05-23 | 2017-05-23 | COMP | 2017-07-20 | 2017-08-09 | COMP | 2017-08-09 | 2017-08-11 | COMP | 2017-08-11 | 2017-08-28 | 0 | 97 | 507846.96
30980187 | OC4 OCGC COND 5360' RD 34 JACINTO 1102 Y | 02/28/2013 | 106744760 | 02/28/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/01/2014 | ED.14-W220000000 | GLENN MAP W22 | 011 | GLENN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 5,007.000 | 5,007.000 | 08J | 2013 | 09/10/2016 | 2016 | 1290 | 184.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | EP REPLACE ANNEALED CONDUCTOR | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-10-13 | 2015-10-13 | COMP | 2015-10-15 | 2015-10-15 | COMP | 2015-10-15 | 2015-10-19 | COMP | 2015-10-19 | 2016-03-21 | COMP | 2016-03-21 | 2016-03-21 | COMP | 2016-03-21 | 2016-03-25 | 6 | 158 | 245343.03
30980188 | OCGC EP BIG MEADOWS 2101 ANNE COND Y2015 | 02/28/2013 | 106744761 | 02/28/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/01/2014 | ED.18-J460000000 | LAS PLUMAS MAP J46 | 032 | PLUMAS COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 5,249.000 | 5,249.000 | 08J | 2013 | 07/02/2016 | 2016 | 1220 | 174.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | EP REPLACE ANNEALED CONDUCTOR, PRATTVILL | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-12-07 | 2015-12-07 | COMP | 2015-12-10 | 2015-12-10 | COMP | 2015-12-13 | 2015-12-13 | COMP | 2015-12-13 | 2016-04-28 | COMP | 2016-04-28 | 2016-06-17 | COMP | 2016-06-17 | 2016-06-21 | 6 | 191 | 362265.96
30980189 | OCGC LOGAN CRK 2101 RECOND, ROAD D Y2016 | 02/28/2013 | 106744762 | 02/28/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/01/2014 | ED.14-Y170000000 | GLENN MAP Y17 | 011 | GLENN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 16,097.000 | 8,387.000 | 08J | 2013 | 04/22/2017 | 2017 | 1514 | 216.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | EP REPLACE ANNEALED CONDUCTOR, ROAD DEP | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-08-23 | 2016-08-23 | COMP | 2016-08-23 | 2016-08-23 | COMP | 2016-08-23 | 2016-08-23 | COMP | 2016-08-23 | 2016-08-31 | COMP | 2016-08-31 | 2017-02-21 | COMP | 2017-02-21 | 2017-03-03 | 0 | 192 | 610121.47
30980225 | OC4 RECON. 1060' NICASIO RAMONA JUAREZ | 02/28/2013 | 106747584 | 02/28/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/20/2014 | ED.04302.1101.SWIT | SWITCHES | 021 | MARIN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 2,522.000 | 2,522.000 | 08J | 2013 | 01/28/2018 | 2018 | 1795 | 256.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30980225_R7 RECON. 1060' NICASIO RAMONA | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2014-07-03 | 2014-06-04 | COMP | 2014-07-03 | 2014-07-03 | COMP | 2014-07-31 | 2014-08-25 | COMP | 2014-08-25 | 2014-09-05 | COMP | 2014-09-05 | 2014-12-24 | COMP | 2014-12-24 | 2015-05-06 | 53 | 254 | 526129.96
30980443 | XRECOND 4433/23327 @ 105 RODGERS RD | 03/01/2013 | 106760612 | 03/01/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 08/01/2014 | ED.18238.1104 | DOLAN ROAD 1104 | 027 | MONTEREY COUNT | 5532479 | CWSP 08W - Monthly Forecast Only | 351.000 | 0.000 | 08W | 2013 | 08/05/2017 | 2017 | 1618 | 231.1429 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2014-10-24 | 2014-11-12 | COMP | 2014-10-24 | 2014-11-13 | COMP | 2015-04-20 | 2015-04-20 | COMP | 2015-04-20 | 2015-09-10 | COMP | 2015-09-10 | 2016-01-25 | COMP | 2016-01-25 | 2016-01-26 | 178 | 281 | 18411.46
30980444 | OC4 XRECOND 310 FT 1-0C, LKHRN & CAST BL | 03/01/2013 | 106760583 | 03/01/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/27/2014 | ED.18238.1101 | DOLAN ROAD 1101 | 027 | MONTEREY COUNT | 5532479 | CWSP 08W - Monthly Forecast Only | 313.000 | 0.000 | 08W | 2013 | 02/14/2015 | 2015 | 715 | 102.1429 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2014-07-29 | 2014-07-29 | COMP | 2014-07-31 | 2014-10-06 | COMP | 2014-10-10 | 2014-10-23 | COMP | 2014-10-23 | 2014-11-15 | COMP | 2014-11-15 | 2014-11-18 | COMP | 2014-11-18 | 2014-11-18 | 86 | 26 | 17517.77
30980600 | COTTLE 1703 WIRE DOWN-RECOND 2400 FT | 03/03/2013 | 106765982 | 03/03/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/01/2014 | ED.16371.1703 | COTTLE 1703 | 050 | STANISLAUS COU | 5535457 | DO 08 - Monthly Forecast Only | 2,400.000 | 0.000 | 08J | 2013 | 06/16/2018 | 2018 | 1931 | 275.8571 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30980600_R2 COTTLE 1703 WIRE DOWN-RECOND | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2014-08-20 | 2014-10-01 | COMP | 2014-08-20 | 2014-12-15 | COMP | 2014-12-19 | 2014-12-19 | COMP | 2014-12-19 | 2014-12-31 | COMP | 2014-12-31 | 2016-01-22 | COMP | 2016-01-22 | 2016-01-23 | 121 | 400 | 236686.67
30980601 | OCGC VALLEY HOME1701-WRE DWN RECOND 715 | 03/03/2013 | 106766009 | 03/03/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/01/2014 | ED.16298.1701 | VALLEY HOME 1701 | 050 | STANISLAUS COU | 5535457 | DO 08 - Monthly Forecast Only | 8,485.000 | 8,589.000 | 08J | 2013 | 10/29/2016 | 2016 | 1336 | 190.8571 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30980601_R2 VALLEY HOME1701-WIRE DOWN RE | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2014-09-02 | 2014-10-14 | COMP | 2014-09-02 | 2014-10-28 | COMP | 2014-12-17 | 2014-12-17 | COMP | 2014-12-17 | 2016-10-07 | COMP | 2016-10-07 | 2016-10-08 | COMP | 2016-10-08 | 2016-10-12 | 106 | 665 | 443619.25
30981132 | 2017 RENFRO 2101 RECONDUCTOR PH 1 | 03/05/2013 | 106767393 | 03/04/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/31/2018 | ED.25457.2101.SWIT | SWITCHES | 015 | KERN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 4,475.000 | 5,000.000 | 08J | 2013 | 12/12/2018 | 2018 | 2108 | 301.1429 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | R5 RECOND 4,888' 6C&4AR-RENFRO 2101 PH.1 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2018-05-31 | 2018-08-22 | COMP | 2018-06-22 | 2018-09-18 | COMP | 2018-09-18 | 2018-09-18 | COMP | 2018-09-18 | 2018-09-19 | COMP | 2018-09-19 | 2018-09-22 | COMP | 2018-09-22 | 2018-09-25 | 110 | 7 | 398685.95
30981133 | 2016 RENFRO 2101 RECONDUCTOR PH 2 | 03/05/2013 | 106779930 | 03/05/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/27/2014 | ED.25457.2101.SWIT | SWITCHES | 015 | KERN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 5,768.000 | 5,768.000 | 08J | 2013 | 12/17/2016 | 2016 | 1383 | 197.5714 | PREC | 11 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | R5 RECOND 5,368' 6C&4AR-RENFRO 2101 PH.2 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-05-20 | 2016-06-24 | COMP | 2016-05-20 | 2016-07-13 | COMP | 2016-07-13 | 2016-07-13 | COMP | 2016-07-13 | 2016-08-16 | COMP | 2016-08-16 | 2016-11-09 | COMP | 2016-11-09 | 2016-11-09 | 54 | 119 | 434953.53
30981135 | OC4 OCGC 2104 FRUITVALE 1103 RECONDUCTOR | 03/05/2013 | 106767681 | 03/04/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/27/2014 | ED.25339.1103.TXFR.TROH | OVERHEAD TRANSFORMERS | 015 | KERN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 1,274.000 | 1,325.000 | 08J | 2013 | 02/07/2015 | 2015 | 704 | 100.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30981135_R5 RECONDUCTOR 1,300' 4AR-FRUIT | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2014-09-16 | 2014-10-15 | COMP | 2014-09-16 | 2014-11-19 | COMP | 2014-11-24 | 2014-11-25 | COMP | 2014-11-25 | 2014-12-13 | COMP | 2014-12-13 | 2015-01-16 | COMP | 2015-01-16 | 2015-01-22 | 70 | 58 | 135613.65
30981136 | OC4 OCGC2014 FRUITVALE 1103 RECONDUCTOR | 03/05/2013 | 106768129 | 03/04/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/27/2014 | ED.25339.1103.SWIT | SWITCHES | 015 | KERN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 1,457.000 | 1,457.000 | 08J | 2013 | 03/21/2015 | 2015 | 746 | 106.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30981136_R5 RECONDUCTOR 3,226' 4AR-FRUIT | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2014-09-16 | 2014-09-29 | COMP | 2014-09-16 | 2014-09-30 | COMP | 2014-10-02 | 2014-10-15 | COMP | 2014-10-15 | 2014-10-23 | COMP | 2014-10-23 | 2015-01-07 | COMP | 2015-01-07 | 2015-01-07 | 29 | 84 | 132482.87
30981137 | 2015 7TH STANDARD 1103 RECONDUCTOR | 03/05/2013 | 106769343 | 03/04/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/27/2014 | ED.25458.2103.TXFR.TROH | OVERHEAD TRANSFORMERS | 015 | KERN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 2,920.000 | 2,920.000 | 08J | 2013 | 09/12/2015 | 2015 | 921 | 131.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30981137_R5 7TH STANDARD 1103 ANNEALED C | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-01-14 | 2015-03-28 | COMP | 2015-01-14 | 2015-03-31 | COMP | 2015-03-31 | 2015-03-31 | COMP | 2015-03-31 | 2015-05-11 | COMP | 2015-05-11 | 2015-06-22 | COMP | 2015-06-22 | 2015-06-23 | 76 | 84 | 190061.11
30981190 | OC4 OCGC 2014 FRUITVALE 2108 RECONDUCTOR | 03/06/2013 | 106769348 | 03/04/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/27/2014 | ED.25339.2108.TXFR.TROH | OVERHEAD TRANSFORMERS | 015 | KERN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 1,940.000 | 2,200.000 | 08J | 2013 | 10/31/2015 | 2015 | 969 | 138.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30981190_R5 RECONDUCTOR 2,059' 4AR-FRUIT | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2014-09-16 | 2014-10-06 | COMP | 2014-09-16 | 2014-10-28 | COMP | 2014-10-31 | 2014-11-04 | COMP | 2014-11-04 | 2015-01-07 | COMP | 2015-01-07 | 2015-10-06 | COMP | 2015-10-06 | 2015-10-06 | 49 | 336 | 256153.31
30981191 | OC4 OCGC 2014 PANAMA 2101 RECONDUCTOR | 03/06/2013 | 106779571 | 03/05/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 07/01/2014 | ED.25342.2101.TXFR.TROH | OVERHEAD TRANSFORMERS | 015 | KERN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 2,772.000 | 2,772.000 | 08J | 2013 | 03/19/2016 | 2016 | 1109 | 158.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30981191_R5 RECONDUCTOR 2,381FT 6CU - PA | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2014-09-16 | 2014-09-18 | COMP | 2014-09-16 | 2014-09-29 | COMP | 2014-10-02 | 2014-10-22 | COMP | 2014-10-22 | 2014-10-29 | COMP | 2014-10-29 | 2016-02-06 | COMP | 2016-02-06 | 2016-02-06 | 36 | 472 | 123290.86
30981255 | OCGC RECOND 2040' 4C W/397A, WILLIAMS RD | 03/06/2013 | 106780764 | 03/05/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 08/29/2014 | ED.18201.1109.TXFR.TROH | OVERHEAD TRANSFORMERS | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 2,829.000 | 2,829.000 | 08J | 2013 | 06/16/2018 | 2018 | 1928 | 275.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30981255_R2RECOND 2040 FT 4CW/397A, WILL | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-09-03 | 2015-11-07 | COMP | 2015-09-03 | 2015-11-20 | COMP | 2015-12-02 | 2015-12-02 | COMP | 2015-12-02 | 2016-04-19 | COMP | 2016-04-19 | 2016-06-27 | COMP | 2016-06-27 | 2016-06-28 | 90 | 209 | 255701.51
30981268 | OCGC DUNNIGAN 1101 RECOND PH 1 - ROAD 5 | 03/06/2013 | 106787164 | 03/06/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/20/2013 | ED.06381.1101 | DUNNIGAN 1101 | 057 | YOLO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 1,355.000 | 1,355.000 | 08J | 2013 | 03/19/2016 | 2016 | 1109 | 158.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30981268_RECONDUCTOR, 063811101, ROAD 5, | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-07-17 | 2015-07-17 | COMP | 2015-07-28 | 2015-07-28 | COMP | 2015-07-28 | 2015-07-28 | COMP | 2015-07-28 | 2016-03-11 | COMP | 2016-03-11 | 2016-03-11 | COMP | 2016-03-11 | 2016-03-11 | 11 | 227 | 86172.67
30981269 | OCGC DUNNIGAN 1101 RECOND, PH 2 Y2016 | 03/06/2013 | 106787200 | 03/06/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/20/2013 | ED.06381.1101 | DUNNIGAN 1101 | 057 | YOLO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 4,600.000 | 4,600.000 | 08J | 2013 | 07/20/2019 | 2019 | 2327 | 332.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30981269_Dunnigan 1101 reconductor phase | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-11-30 | 2016-11-30 | COMP | 2016-12-05 | 2016-12-05 | COMP | 2016-12-05 | 2016-12-05 | COMP | 2016-12-05 | 2016-12-12 | COMP | 2016-12-12 | 2017-01-18 | COMP | 2017-01-18 | 2017-02-01 | 5 | 58 | 155145.96
30981321 | OC4 GC 2014 MAGUNDEN 1104 RECONDUCTOR | 03/06/2013 | 106779573 | 03/05/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/27/2014 | ED.25277.1104.SWIT | SWITCHES | 015 | KERN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 1,678.000 | 1,678.000 | 08J | 2013 | 07/18/2015 | 2015 | 864 | 123.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30981321_R5 RECON 1,890' 6CU-MAGUNDEND 1 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2014-07-11 | 2014-09-17 | COMP | 2014-07-11 | 2014-09-24 | INPR | 2014-09-24 | 2015-01-10 | COMP | 2014-10-10 | 2014-10-10 | COMP | 2014-10-10 | 2014-12-12 | COMP | 2014-12-12 | 2014-12-30 | 183 | -11 | 249863.54
30981325 | Z 2016 MAGUNDEN 1108 RECONDUCTR ANNEAL | 03/06/2013 | 106779577 | 03/05/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/31/2017 | ED.25277.1104.SWIT | SWITCHES | 015 | KERN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 1,960.000 | 2,126.000 | 08J | 2013 | 03/10/2018 | 2018 | 1830 | 261.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30981325_R5 RECON 1960'6CU-MAGUNDEN 1108 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-12-20 | 2017-03-26 | COMP | 2016-12-20 | 2017-03-27 | COMP | 2017-03-27 | 2017-03-27 | COMP | 2017-03-27 | 2017-03-30 | COMP | 2017-03-30 | 2017-04-12 | COMP | 2017-04-12 | 2017-04-28 | 97 | 32 | 118664.89
30981327 | OC4 RECON 800FT 4AR - BAKERSFIELD 1110 | 03/06/2013 | 106779775 | 03/05/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/20/2013 | ED.25337.1110.SWIT | SWITCHES | 015 | KERN COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 825.000 | 0.000 | 08W | 2013 | 02/06/2016 | 2016 | 1067 | 152.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2014-05-13 | 2014-06-24 | COMP | 2014-05-13 | 2014-06-25 | COMP | 2014-06-30 | 2014-08-06 | COMP | 2014-08-06 | 2014-08-21 | COMP | 2014-08-21 | 2016-01-15 | COMP | 2016-01-15 | 2016-01-19 | 85 | 531 | 75385.09
30981330 | 2015 MCFARLAND 1104 RECONDUCTOR | 03/06/2013 | 106779871 | 03/05/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 07/01/2015 | ED.25318.1104.SWIT | SWITCHES | 015 | KERN COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 5,909.000 | 4,909.000 | 08W | 2013 | 03/19/2016 | 2016 | 1109 | 158.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | R5 MCFARLAND 1104 RECONDUCTOR ANNEALED | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-06-19 | 2015-08-20 | COMP | 2015-06-19 | 2015-08-27 | COMP | 2015-08-27 | 2015-08-27 | COMP | 2015-08-27 | 2015-09-09 | INPR | 2015-09-09 | 2016-03-19 | # | 2016-03-19 | 2016-03-19 | 69 | 205 | 238873.48
30981339 | OC4 OCGC 2014 MAGUNDEN 1105 RECONDUCTR A | 03/06/2013 | 106779610 | 03/05/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/27/2014 | ED.25277.1101.SWIT | SWITCHES | 015 | KERN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 2,394.000 | 2,394.000 | 08J | 2013 | 08/08/2015 | 2015 | 885 | 126.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30981339_R5 MAGUNDEN 1105 ANNEALED CONDU | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2014-09-16 | 2014-10-08 | COMP | 2014-09-16 | 2014-11-04 | COMP | 2014-11-07 | 2014-11-14 | COMP | 2014-11-14 | 2014-11-20 | COMP | 2014-11-20 | 2015-01-27 | COMP | 2015-01-27 | 2015-01-28 | 59 | 75 | 230373.18
30981418 | 2017 WASCO 1102_1104 RECONDUCTOR | 03/07/2013 | 106779872 | 03/05/2013 | # | Not assigned | 40 | Closed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 09/28/2018 | ED.25296.1104.SWIT | SWITCHES | 015 | KERN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 6,138.000 | 6,138.000 | 08J | 2013 | 07/20/2019 | 2019 | 2326 | 332.2857 | CLSD | 12 | E070 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30981418_R5 RECNDCTR 6,728FT 6CU- WASCO | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2018-11-14 | 2018-09-22 | COMP | 2018-06-22 | 2018-11-14 | COMP | 2018-11-14 | 2018-11-14 | COMP | 2018-11-14 | 2018-11-15 | COMP | 2018-11-15 | 2018-11-26 | COMP | 2018-11-26 | 2018-11-27 | 0 | 13 | 921023.33
30981440 | OC4 OCGC 2014 MAGUNDEN 2109 RECNDUCTR AN | 03/06/2013 | 106779672 | 03/05/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/27/2014 | ED.25277.2108.SECT | SECTIONALIZERS | 015 | KERN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 2,650.000 | 2,643.000 | 08J | 2013 | 02/20/2016 | 2016 | 1081 | 154.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30981440_R5 RECON 2,650FT 6CU&4AR - MAGU | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2014-09-16 | 2014-09-30 | COMP | 2014-09-16 | 2014-10-07 | COMP | 2014-10-10 | 2014-10-25 | COMP | 2014-10-25 | 2014-11-04 | COMP | 2014-11-04 | 2016-01-22 | COMP | 2016-01-22 | 2016-01-26 | 39 | 458 | 361464.51
30981442 | OC4 2014 MAGUNDEN 1108 RECONDUCTOR | 03/06/2013 | 106747715 | 02/28/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 05/30/2014 | ED.25277.1108.SWIT | SWITCHES | 015 | KERN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 3,295.000 | 08J | 2013 | 10/17/2015 | 2015 | 955 | 136.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30981442_R5 RECONDUCTOR MAGUNDEN 1108_06 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2014-06-05 | 2014-06-05 | COMP | 2014-06-11 | 2014-06-11 | COMP | 2014-06-17 | 2014-07-22 | COMP | 2014-07-22 | 2014-08-07 | COMP | 2014-08-07 | 2015-10-12 | COMP | 2015-10-12 | 2015-10-12 | 47 | 447 | 249327.1
30981444 | OCGC 2015 BAKERSFIELD 2108 WIREDOWN | 03/06/2013 | 106747753 | 02/28/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/27/2015 | ED.25337.2107.SWIT | SWITCHES | 015 | KERN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 885.000 | 885.000 | 08J | 2013 | 03/19/2016 | 2016 | 1109 | 158.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30981444_R5 WIREDOWN BAKERSFIELD 2108_08 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-05-21 | 2015-06-16 | COMP | 2015-05-21 | 2015-06-18 | COMP | 2015-06-18 | 2015-06-18 | COMP | 2015-06-18 | 2015-09-11 | COMP | 2015-09-11 | 2016-03-01 | COMP | 2016-03-01 | 2016-03-07 | 28 | 263 | 85925.5
30981464 | OCGC FH 1101 2809 STAR ZONE - 21 CUTOVER | 03/06/2013 | 106786777 | 03/06/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/01/2014 | ED.18295.1101 | FOOTHILL 1101 | 040 | SAN LUIS OBISP | 5535457 | DO 08 - Monthly Forecast Only | 677.000 | 677.000 | 08J | 2013 | 11/14/2015 | 2015 | 983 | 140.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30981464_R5 Z FH 1101 2809 STAR ZONE_08J | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2014-06-10 | 2014-07-16 | COMP | 2014-06-10 | 2014-08-18 | COMP | 2015-02-19 | 2015-05-15 | COMP | 2015-05-15 | 2015-06-13 | COMP | 2015-06-13 | 2015-10-22 | COMP | 2015-10-22 | 2015-11-02 | 339 | 171 | 121478.63
30981465 | Z MB 1101 OCB STAR ZONE PHASE 1 | 03/06/2013 | 106786774 | 03/06/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/01/2014 | ED.18301.1101 | MORRO BAY 1101 | 040 | SAN LUIS OBISP | 5535457 | DO 08 - Monthly Forecast Only | 1,737.000 | 1,737.000 | 08J | 2013 | 11/07/2015 | 2015 | 976 | 139.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30981465_R5 MB 1101 OCB STAR ZONE PHASE | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2014-09-16 | 2014-10-14 | COMP | 2014-09-16 | 2014-11-10 | COMP | 2015-02-14 | 2015-02-14 | COMP | 2014-11-17 | 2014-11-17 | COMP | 2014-11-17 | 2014-12-11 | COMP | 2014-12-11 | 2014-12-12 | 151 | -64 | 275627.47
30981467 | OCGC *PERRY 1101 9185 STAR ZONE | 03/06/2013 | 106786734 | 03/06/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/01/2014 | ED.18307.1101 | PERRY 1101 | 040 | SAN LUIS OBISP | 5535457 | DO 08 - Monthly Forecast Only | 1,570.000 | 1,565.000 | 08J | 2013 | 08/08/2015 | 2015 | 885 | 126.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30981467_R5 PERRY 1101 9185 STAR ZONE_08 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2014-09-04 | 2014-10-09 | COMP | 2014-09-04 | 2014-10-28 | COMP | 2014-10-28 | 2014-10-28 | COMP | 2014-10-28 | 2014-11-06 | COMP | 2014-11-06 | 2014-11-14 | COMP | 2014-11-14 | 2014-12-01 | 54 | 34 | 178585.17
30981469 | OCGC PERRY 1101 14047 STAR ZONE | 03/06/2013 | 106786736 | 03/06/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/01/2014 | ED.18307.1101 | PERRY 1101 | 040 | SAN LUIS OBISP | 5535457 | DO 08 - Monthly Forecast Only | 2,684.000 | 0.000 | 08J | 2013 | 08/08/2015 | 2015 | 885 | 126.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30981469_R5 PERRY 1101 14047 STAR ZONE_0 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2014-09-23 | 2014-10-14 | COMP | 2014-09-23 | 2014-11-17 | COMP | 2014-11-17 | 2014-11-17 | COMP | 2014-11-17 | 2014-11-26 | COMP | 2014-11-26 | 2014-12-09 | COMP | 2014-12-09 | 2014-12-10 | 55 | 23 | 208514.07
30981484 | 2015 RIO BRAVO 1101 RECONDUCTOR | 03/07/2013 | 106779876 | 03/05/2013 | # | Not assigned | 40 | Closed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 03/27/2015 | ED.25286.1101.SWIT | SWITCHES | 015 | KERN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 5,567.000 | 0.000 | 08J | 2013 | 09/03/2016 | 2016 | 1276 | 182.2857 | CLSD | 12 | E070 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30981484_R5 RECNDCTR 5,868FT 6CU - RIO B | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-04-11 | 2015-05-15 | COMP | 2015-04-11 | 2015-05-19 | COMP | 2015-05-19 | 2015-05-19 | COMP | 2015-05-19 | 2015-06-22 | COMP | 2015-06-22 | 2015-09-04 | COMP | 2015-09-04 | 2015-09-04 | 38 | 108 | 769447.91
30981550 | OC4 OCGC 2014 WESTPARK 1108_1110 RECONDU | 03/07/2013 | 106779879 | 03/05/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/27/2014 | ED.25370.1108.SWIT | SWITCHES | 015 | KERN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 2,801.000 | 2,801.000 | 08J | 2013 | 06/10/2017 | 2017 | 1556 | 222.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30981550_R5 RECOND 2,794FT 2CU-WESTPARK | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2014-08-28 | 2014-08-28 | COMP | 2014-09-11 | 2014-10-10 | COMP | 2014-10-14 | 2014-10-30 | COMP | 2014-10-30 | 2014-11-04 | COMP | 2014-11-04 | 2016-01-29 | COMP | 2016-01-29 | 2016-01-29 | 63 | 456 | 516406.78
30981552 | 2016 WHEELER RIDGE 1101 RECONDUCTOR | 03/07/2013 | 106779978 | 03/05/2013 | # | Not assigned | 40 | Closed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 06/27/2014 | ED.25348.1101.SWIT | SWITCHES | 015 | KERN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 6,252.000 | 6,252.000 | 08J | 2013 | 06/17/2017 | 2017 | 1563 | 223.2857 | PREC | 11 | E070 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30981552_Wheeler Ridge 1101 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-04-26 | 2016-06-26 | COMP | 2016-04-26 | 2016-07-13 | COMP | 2016-07-13 | 2016-07-13 | COMP | 2016-07-13 | 2016-08-17 | COMP | 2016-08-17 | 2016-12-15 | COMP | 2016-12-15 | 2016-12-15 | 78 | 155 | 307957.17
30981553 | OCGC 2014 WHEELER RIDGE 1101 RECONDUCTOR | 03/07/2013 | 106779979 | 03/05/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/27/2014 | ED.25341.1103.SWIT | SWITCHES | 015 | KERN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 1,350.000 | 1,350.000 | 08J | 2013 | 03/07/2015 | 2015 | 730 | 104.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30981553_R5 RECOND 1,350FT 6CU-WHEELER R | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2014-11-22 | 2014-12-29 | COMP | 2014-11-22 | 2015-01-06 | COMP | 2015-01-06 | 2015-01-06 | COMP | 2015-01-06 | 2015-01-15 | COMP | 2015-01-15 | 2015-02-18 | COMP | 2015-02-18 | 2015-02-18 | 45 | 43 | 71102.92
30981557 | 2016 WHEELER RIDGE 1102 RECONDUCTOR | 03/07/2013 | 106780130 | 03/05/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/27/2014 | ED.25348.1102.SWIT | SWITCHES | 015 | KERN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 5,424.000 | 5,500.000 | 08J | 2013 | 12/17/2016 | 2016 | 1381 | 197.2857 | PREC | 11 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30981557_Wheeler Ridge 1102 Reconductor | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-04-27 | 2016-06-10 | COMP | 2016-04-27 | 2016-06-28 | COMP | 2016-06-28 | 2016-06-28 | COMP | 2016-06-28 | 2016-08-08 | COMP | 2016-08-08 | 2016-10-20 | COMP | 2016-10-20 | 2016-10-25 | 62 | 119 | 265182.44
30981558 | ARVIN 1103 RECONDUCTOR | 03/07/2013 | 106780132 | 03/05/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/27/2014 | ED.25348.1102.SWIT | SWITCHES | 015 | KERN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 5,380.000 | 5,380.000 | 08J | 2013 | 12/22/2018 | 2018 | 2116 | 302.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30981558_R5 2015 ARVIN 1103 RECONDUCTOR | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-06-24 | 2015-07-30 | COMP | 2015-06-24 | 2015-08-05 | COMP | 2015-08-05 | 2015-08-05 | COMP | 2015-08-05 | 2015-09-09 | COMP | 2015-09-09 | 2016-03-16 | COMP | 2016-03-16 | 2016-03-16 | 42 | 224 | 181240.9
30981641 | RECOND 1608FT 2CU-SAN BERNARD 1101 | 03/07/2013 | 106780135 | 03/05/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/27/2014 | ED.25319.1101.TXFR.TROH | OVERHEAD TRANSFORMERS | 015 | KERN COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 1,608.000 | 1,608.000 | 08W | 2013 | 03/19/2016 | 2016 | 1108 | 158.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | RECOND 1608FT 2CU-SAN BERNARD 1101 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-07-08 | 2015-10-23 | COMP | 2015-07-08 | 2015-10-27 | COMP | 2015-10-27 | 2015-10-27 | INPR | 2015-10-27 | 2016-03-19 | # | 2016-03-19 | 2016-03-19 | # | 2016-03-19 | 2016-03-19 | 111 | 144 | 66663.97
30981728 | OC4 OCGC BULLARD 1110 RCNDCT TAP ON SANP | 03/08/2013 | 106684670 | 02/11/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/07/2014 | ED.25396.1110 | BULLARD 1110 | 010 | FRESNO COUNTY | 5517127 | DO 08 - Monthly Forecast Only | 711.000 | 710.000 | 08J | 2013 | 04/14/2018 | 2018 | 1863 | 266.1429 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2014-07-29 | 2014-10-24 | COMP | 2014-07-29 | 2014-12-22 | COMP | 2014-12-22 | 2015-01-14 | COMP | 2015-01-14 | 2015-01-20 | COMP | 2015-01-20 | 2016-01-23 | COMP | 2016-01-23 | 2016-01-29 | 169 | 380 | 79052.51
30981763 | OCGC 2014 LAMONT 1106 RECONDUCTOR | 03/08/2013 | 106780200 | 03/05/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/27/2014 | ED.25297.1106.SWIT | SWITCHES | 015 | KERN COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 9,038.000 | 9,038.000 | 08W | 2013 | 04/11/2015 | 2015 | 764 | 109.1429 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30981763_R5 2015 LAMONT 1106 RECONDUCTO | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2014-09-16 | 2014-12-10 | COMP | 2014-09-16 | 2015-01-28 | COMP | 2015-01-28 | 2015-01-28 | COMP | 2015-01-28 | 2015-02-02 | COMP | 2015-02-02 | 2015-03-11 | COMP | 2015-03-11 | 2015-03-11 | 134 | 42 | 239261.42
30981767 | 2016 WEEDPATCH 1106 RECON DIGIORGIO | 03/08/2013 | 106780204 | 03/05/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/27/2014 | ED.25297.1106.SWIT | SWITCHES | 015 | KERN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 4,199.000 | 4,199.000 | 08J | 2013 | 03/25/2017 | 2017 | 1478 | 211.1429 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Weedpatch 1106 - Reconductor 4,150 Ft of | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-08-12 | 2016-10-31 | COMP | 2016-08-12 | 2016-11-01 | COMP | 2016-11-01 | 2016-11-01 | COMP | 2016-11-01 | 2016-11-04 | COMP | 2016-11-04 | 2017-01-19 | COMP | 2017-01-19 | 2017-02-14 | 81 | 105 | 127977.26
30981768 | 2016 WEEDPATCH 1106 RECOND VINELAND | 03/08/2013 | 106780207 | 03/05/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/27/2014 | ED.25297.1106.SWIT | SWITCHES | 015 | KERN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 5,889.000 | 5,889.000 | 08J | 2013 | 03/25/2017 | 2017 | 1478 | 211.1429 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30981768_Weedpatch 1106 Reconductor | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-05-20 | 2016-07-27 | COMP | 2016-05-20 | 2016-08-03 | COMP | 2016-08-03 | 2016-08-03 | COMP | 2016-08-03 | 2016-08-26 | COMP | 2016-08-26 | 2017-01-19 | COMP | 2017-01-19 | 2017-02-11 | 75 | 192 | 200834.72
30981770 | R5 2017 TAFT 1108 RECONDUCTOR | 03/08/2013 | 106780260 | 03/05/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 05/01/2020 | JY | JUNK YARD FL TO HOLD DELETED DATA | 015 | KERN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 3,798.000 | 3,798.000 | 08J | 2013 | 08/08/2020 | 2020 | 2710 | 387.1429 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30981770_Taft1108 RECONDUCTOR | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2020-06-05 | 2020-06-05 | COMP | 2020-01-21 | 2020-06-12 | COMP | 2020-06-12 | 2020-06-12 | COMP | 2020-06-12 | 2020-06-13 | COMP | 2020-06-13 | 2020-07-28 | COMP | 2020-07-28 | 2020-08-03 | 7 | 52 | 285896.17
30981774 | OC4 2014 POSO MNT 2101 RECONDUCTOR PH 2 | 03/08/2013 | 106746061 | 02/28/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 05/30/2014 | ED.25364.2101.CAPA | CAPACITORS | 015 | KERN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2013 | 10/31/2015 | 2015 | 967 | 138.1429 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30981774_R5 RECONDUCTR 5,270FT POSO MOUN | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2014-02-04 | 2014-04-17 | COMP | 2014-02-04 | 2014-06-20 | COMP | 2014-06-26 | 2014-08-04 | COMP | 2014-08-04 | 2014-08-27 | COMP | 2014-08-27 | 2015-10-06 | COMP | 2015-10-06 | 2015-10-06 | 181 | 428 | 159150.11
30981874 | OC4 2014 CHARCA 1103 RECONDUCTOR | 03/08/2013 | 106745328 | 02/28/2013 | # | Not assigned | 40 | Closed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 06/02/2014 | ED.25450.1103.CAPA | CAPACITORS | 015 | KERN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 6,813.000 | 0.000 | 08J | 2013 | 12/13/2015 | 2015 | 1010 | 144.2857 | CLSD | 12 | E070 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30981874_R5 RECONDUCTOR 7,500' +- CHARCA | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2014-03-05 | 2014-04-09 | COMP | 2014-03-05 | 2014-05-07 | COMP | 2014-05-14 | 2014-06-12 | COMP | 2014-06-12 | 2014-06-24 | COMP | 2014-06-24 | 2015-11-17 | COMP | 2015-11-17 | 2015-11-20 | 99 | 526 | 530005.2
30982452 | OC4 OCGC LINCOLN 2108 RECONDUCTOR, SEGO | 03/12/2013 | 106824493 | 03/12/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/26/2014 | ED.15370.2108 | LINCOLN 2108 | 031 | PLACER COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 5,005.000 | 5,005.000 | 08J | 2013 | 03/03/2018 | 2018 | 1817 | 259.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30982452_RECONDUCTOR, 153702108, SEGO LA | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-02-25 | 2016-02-25 | COMP | 2016-02-26 | 2016-02-26 | COMP | 2016-02-26 | 2016-02-26 | COMP | 2016-02-26 | 2016-04-14 | COMP | 2016-04-14 | 2016-08-15 | COMP | 2016-08-15 | 2016-08-16 | 1 | 172 | 388808.65
30982557 | *CANC*ELK 1101-REPL SPLICES STRM LN*CANC | 03/13/2013 | 106825286 | 03/12/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/27/2013 | ED.04298.1101.RECL | RECLOSERS | 023 | MENDOCINO COUN | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2013 | 08/05/2020 | 2020 | 2702 | 386 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2020-08-05 | 2020-08-05 | # | 2020-08-05 | 2020-08-05 | # | 2020-08-05 | 2020-08-05 | COMP | 2020-07-30 | 2020-07-30 | COMP | 2020-07-30 | 2020-07-30 | COMP | 2020-07-30 | 2020-07-30 | 0 | -6 | 0
30982558 | *CANC* GUALALA 1112- REPLACE MAINLINE SP | 03/13/2013 | 106825256 | 03/12/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2013 | ED.04284.1112.SWIT | SWITCHES | 023 | MENDOCINO COUN | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2013 | 07/18/2015 | 2015 | 857 | 122.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2015-07-19 | 2015-07-19 | # | 2015-07-19 | 2015-07-19 | # | 2015-07-19 | 2015-07-19 | # | 2015-07-19 | 2015-07-19 | # | 2015-07-19 | 2015-07-19 | # | 2015-07-19 | 2015-07-19 | 0 | 0 | 0
30982568 | OC4 LKVL1101RECOND3SPAN-BRWNSRDLKVLHW,PE | 03/12/2013 | 106817807 | 03/11/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2013 | ED.04337.1101 | LAKEVILLE 1101 | 049 | SONOMA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 579.000 | 0.000 | 08W | 2013 | 05/16/2015 | 2015 | 795 | 113.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2014-08-03 | 2014-08-03 | COMP | 2014-09-30 | 2014-09-30 | COMP | 2014-10-24 | 2014-10-24 | COMP | 2014-10-24 | 2014-10-30 | COMP | 2014-10-30 | 2014-11-06 | COMP | 2014-11-06 | 2014-11-19 | 82 | 26 | 54203.74
30982595 | OCGC PLUMAS 2107 RECON. FOR WIRE DOWN | 03/13/2013 | 106804321 | 03/08/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 01/03/2014 | ED.15373.2107.TXFR.TROH | OVERHEAD TRANSFORMERS | 058 | YUBA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 4,705.000 | 4,705.000 | 08J | 2013 | 06/18/2016 | 2016 | 1193 | 170.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30982595_Broadway St. Reconductor - Plum | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-10-20 | 2015-10-20 | COMP | 2015-10-21 | 2015-10-21 | COMP | 2015-10-21 | 2015-10-21 | INPR | 2015-10-21 | 2016-02-13 | # | 2016-02-13 | 2016-02-13 | # | 2016-02-13 | 2016-02-13 | 1 | 115 | 258451.57
30982596 | 0C4 OCGC MERIDIAN 1101-REC 13SPANS-SW4 | 03/13/2013 | 106825360 | 03/12/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/28/2013 | ED.06254.1101.SWIT | SWITCHES | 006 | COLUSA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 3,126.000 | 0.000 | 08J | 2013 | 02/20/2016 | 2016 | 1074 | 153.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2014-12-09 | 2014-12-09 | COMP | 2015-08-26 | 2015-08-26 | COMP | 2015-08-28 | 2015-08-28 | COMP | 2015-08-28 | 2015-09-10 | COMP | 2015-09-10 | 2016-02-01 | COMP | 2016-02-01 | 2016-02-01 | 262 | 157 | 225111.07
30982640 | OC4 OCGC INSTREEW-5600MARSHALLPTLMA,OLEM | 03/13/2013 | 106825294 | 03/12/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2013 | ED.04229.1101 | OLEMA 1101 | 049 | SONOMA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 1,170.000 | 0.000 | 08W | 2013 | 12/13/2015 | 2015 | 1005 | 143.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2014-10-27 | 2014-10-27 | COMP | 2014-12-01 | 2014-12-01 | COMP | 2014-12-05 | 2014-12-05 | COMP | 2014-12-05 | 2014-12-10 | COMP | 2014-12-10 | 2014-12-19 | COMP | 2014-12-19 | 2014-12-24 | 39 | 19 | 152959.63
30982644 | RECON 2,600' 6C W/4AR_MADERA 1119 WI | 03/13/2013 | 106817660 | 03/11/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/10/2015 | ED.25276.1119 | MADERA 1119 | 020 | MADERA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 2,622.000 | 2,622.000 | 08J | 2013 | 05/14/2016 | 2016 | 1158 | 165.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30982644_RECON 2,600' 6C W/4AR_MADERA 11 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-09-03 | 2015-09-03 | COMP | 2015-09-09 | 2015-09-09 | COMP | 2015-09-09 | 2015-09-12 | COMP | 2015-09-12 | 2015-10-09 | COMP | 2015-10-09 | 2016-04-28 | COMP | 2016-04-28 | 2016-04-28 | 9 | 229 | 87944.21
30982688 | OC4 OCGC SISQUOC 1103 PHS 1 (WHITE ROCK | 03/13/2013 | 106825530 | 03/12/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/01/2014 | ED.18263.1108 | SAN LUIS OBISPO 1108 | 040 | SAN LUIS OBISP | 5535457 | DO 08 - Monthly Forecast Only | 2,378.000 | 2,300.000 | 08J | 2013 | 10/17/2015 | 2015 | 948 | 135.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30982688_R5 SISQUOC 1103 WD 13-0013321 P | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-04-07 | 2015-06-15 | COMP | 2015-04-07 | 2015-06-22 | COMP | 2015-06-22 | 2015-06-22 | COMP | 2015-06-22 | 2015-09-03 | COMP | 2015-09-03 | 2015-09-16 | COMP | 2015-09-16 | 2015-09-16 | 76 | 86 | 226232.69
30982690 | OC4 SLO 1108 WD 12-0081243 | 03/13/2013 | 106825499 | 03/12/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/01/2014 | ED.18263.1108 | SAN LUIS OBISPO 1108 | 040 | SAN LUIS OBISP | 5535457 | DO 08 - Monthly Forecast Only | 1,717.000 | 1,717.000 | 08J | 2013 | 04/09/2016 | 2016 | 1123 | 160.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30982690_R5 SLO 1108 WD 12-0081243_08J | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2014-06-12 | 2014-08-01 | COMP | 2014-06-12 | 2014-09-09 | COMP | 2014-09-17 | 2014-09-23 | COMP | 2014-09-23 | 2014-09-27 | COMP | 2014-09-27 | 2014-10-09 | COMP | 2014-10-09 | 2014-10-11 | 103 | 18 | 280684.74
30982691 | OCGC +DIVIDE 1102 WD 13-0009119 PHS 1 | 03/13/2013 | 106825498 | 03/12/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/01/2014 | ED.18257.1101 | DIVIDE 1101 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 2,340.000 | 2,340.000 | 08J | 2013 | 02/20/2016 | 2016 | 1074 | 153.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2014-10-16 | 2015-04-27 | COMP | 2014-10-16 | 2015-05-18 | COMP | 2015-05-18 | 2015-05-18 | COMP | 2015-05-18 | 2015-06-06 | COMP | 2015-06-06 | 2015-07-23 | COMP | 2015-07-23 | 2015-07-23 | 214 | 66 | 243403.8
30982693 | OCGC SISQUOC 1102 PHS 1 (RESERVOIR) | 03/13/2013 | 106825497 | 03/12/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/01/2014 | ED.18281.1102 | SISQUOC 1102 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 1,167.000 | 1,167.000 | 08J | 2013 | 09/19/2015 | 2015 | 920 | 131.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30982693_R5 SISQUOC 1102 WD 13-0006447 P | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-03-30 | 2015-05-21 | COMP | 2015-03-30 | 2015-06-09 | COMP | 2015-06-24 | 2015-06-24 | COMP | 2015-06-24 | 2015-08-14 | COMP | 2015-08-14 | 2015-08-14 | COMP | 2015-08-14 | 2015-08-29 | 86 | 66 | 112969.91
30982694 | OCCC +Z DIVIDE 1102 WD 13-0006459 | 03/13/2013 | 106825496 | 03/12/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/01/2014 | ED.18206.1107 | FAIRWAY 1107 | 042 | SANTA BARBARA | 5532479 | CWSP 08W - Monthly Forecast Only | 745.000 | 0.000 | 08W | 2013 | 09/17/2016 | 2016 | 1284 | 183.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2014-09-18 | 2015-12-22 | COMP | 2014-09-18 | 2016-01-11 | COMP | 2016-01-11 | 2016-01-11 | COMP | 2016-01-11 | 2016-04-13 | COMP | 2016-04-13 | 2016-06-30 | COMP | 2016-06-30 | 2016-07-01 | 480 | 172 | 356128.14
30982695 | OC4 +FAIRWAY 1107 (A ST <(>&<)> SONYA) | 03/13/2013 | 106825495 | 03/12/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/01/2014 | ED.18206.1107 | FAIRWAY 1107 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 2,108.000 | 2,108.000 | 08J | 2013 | 08/27/2016 | 2016 | 1263 | 180.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30982695_R5 FAIRWAY 1107 WD 13-0005115 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-07-01 | 2015-11-20 | COMP | 2015-07-01 | 2015-11-25 | COMP | 2015-12-04 | 2015-12-09 | COMP | 2015-12-04 | 2016-05-14 | COMP | 2016-05-14 | 2016-05-14 | COMP | 2016-05-14 | 2016-05-14 | 161 | 157 | 286572.68
30982696 | +SANTA MARIA 1106 (CRESTON & MCCLELLAND) | 03/13/2013 | 106825494 | 03/12/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/01/2014 | ED.18267.1106 | SANTA MARIA 1106 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 638.000 | 0.000 | 08J | 2013 | 11/17/2018 | 2018 | 2075 | 296.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | INPR | 2017-02-10 | 2018-11-17 | INPR | 2017-02-10 | 2018-11-17 | # | 2018-11-17 | 2018-11-17 | COMP | 2018-11-07 | 2018-11-07 | COMP | 2018-11-07 | 2018-11-07 | COMP | 2018-11-07 | 2018-11-07 | 645 | -10 | 32426.86
30982697 | OCLH SANTA MARIA 1109 WD 12-0081123 | 03/13/2013 | 106825493 | 03/12/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/01/2014 | ED.18267.1109 | SANTA MARIA 1109 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 628.000 | 628.000 | 08J | 2013 | 03/19/2016 | 2016 | 1102 | 157.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-07-16 | 2015-07-08 | COMP | 2015-07-16 | 2015-07-16 | COMP | 2015-07-16 | 2015-07-19 | COMP | 2015-07-19 | 2016-02-10 | COMP | 2016-02-10 | 2016-02-10 | COMP | 2016-02-10 | 2016-02-11 | 3 | 207 | 32676.49
30982719 | OCGC XREC BYD FUSE 20183 OFF NUTTING | 03/13/2013 | 106830752 | 03/13/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 07/25/2014 | ED.18226.1103 | BUENA VISTA 1103 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 1,150.000 | 1,150.000 | 08J | 2013 | 07/23/2016 | 2016 | 1228 | 175.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-08-24 | 2015-10-06 | COMP | 2015-08-24 | 2015-10-13 | COMP | 2015-10-13 | 2015-10-13 | COMP | 2015-10-13 | 2016-04-12 | COMP | 2016-04-12 | 2016-05-10 | COMP | 2016-05-10 | 2016-05-11 | 50 | 211 | 40154.01
30982830 | OCGCFAIRHAVEN 1103 REMOVE EXCESS SPLICES | 03/14/2013 | 106831646 | 03/14/2013 | # | Not assigned | 30 | Technically Completed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 07/11/2018 | ED.19245.1103.SWIT | SWITCHES | 012 | HUMBOLDT COUNT | 5535457 | DO 08 - Monthly Forecast Only | 2,440.000 | 2,440.000 | 08J | 2013 | # | OPEN | 2822 | 403.1429 | FICL | 10 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30982830_R6 FAIRHAVEN 1103 REMOVE EXCESS | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2017-09-07 | 2019-12-12 | COMP | 2019-12-16 | 2019-12-16 | COMP | 2019-12-16 | 2019-12-16 | COMP | 2019-12-16 | 2019-12-17 | COMP | 2019-12-17 | 2020-01-03 | COMP | 2020-01-03 | 2020-01-07 | 830 | 22 | 950155.44
30982879 | OCGC REPLACE #6CU W/#2ACSR - WIREDOWN | 03/14/2013 | 106829723 | 03/13/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 08/30/2013 | ED.15230.1102.TXFR.TROH | OVERHEAD TRANSFORMERS | 031 | PLACER COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 765.000 | 765.000 | 08J | 2013 | 03/19/2016 | 2016 | 1101 | 157.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-05-26 | 2015-05-26 | COMP | 2015-06-02 | 2015-06-02 | COMP | 2015-06-02 | 2015-06-02 | COMP | 2015-06-02 | 2015-06-03 | COMP | 2015-06-03 | 2016-02-12 | COMP | 2016-02-12 | 2016-02-12 | 7 | 255 | 44320.28
30982901 | OC4 OCGC TRACY 1106 RECOND 4850' 6CU TO | 03/13/2013 | 106772687 | 03/04/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/28/2014 | ED.16288.1106 | TRACY 1106 | 039 | SAN JOAQUIN CO | 5535457 | DO 08 - Monthly Forecast Only | 5,242.000 | 5,250.000 | 08J | 2013 | 03/19/2016 | 2016 | 1102 | 157.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | R4 TRACY 1106 RECOND 4850' 6CU TO 4/0AL | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-04-23 | 2015-04-23 | COMP | 2015-04-29 | 2015-04-29 | COMP | 2015-05-04 | 2015-05-04 | COMP | 2015-05-04 | 2015-07-15 | COMP | 2015-07-15 | 2016-03-01 | COMP | 2016-03-01 | 2016-03-01 | 11 | 302 | 290291.69
30982907 | OC4 OCGC - SISQUOC 1103 PHS 2 (WHITE ROC | 03/13/2013 | 106830736 | 03/13/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 05/01/2014 | ED.18281.1103 | SISQUOC 1103 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 2,844.000 | 2,549.000 | 08J | 2013 | 03/19/2016 | 2016 | 1102 | 157.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30982907_R5 SISQUOC 1103 WD 13-0013321 P | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-05-14 | 2015-06-18 | COMP | 2015-05-14 | 2015-06-23 | COMP | 2015-06-23 | 2015-10-21 | COMP | 2015-10-21 | 2016-01-26 | COMP | 2016-01-26 | 2016-01-26 | COMP | 2016-01-26 | 2016-01-27 | 160 | 98 | 137103.15
30983000 | OCGC REPLACE #4ACSR W/#2ACSR - WIREDOWN | 03/14/2013 | 106829638 | 03/13/2013 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 08/30/2013 | ED.15308.2106.TXFR.TROH | OVERHEAD TRANSFORMERS | 009 | EL DORADO COUN | 5535457 | DO 08 - Monthly Forecast Only | 342.000 | 0.000 | 08J | 2013 | # | OPEN | 2822 | 403.1429 | DOCC | 8 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-07-14 | 2016-07-14 | COMP | 2016-07-18 | 2016-07-18 | COMP | 2016-07-18 | 2016-07-18 | COMP | 2016-07-18 | 2017-10-11 | COMP | 2017-10-11 | 2017-10-13 | COMP | 2017-10-13 | 2017-10-16 | 4 | 455 | 45230.52
30983160 | OCGC TERMINOUS 1103 CIRCUIT RECOND 6CU | 03/14/2013 | 106832253 | 03/14/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 05/31/2014 | ED.16302.1103 | TERMINOUS 1103 | 039 | SAN JOAQUIN CO | 5535457 | DO 08 - Monthly Forecast Only | 8,025.000 | 8,025.000 | 08J | 2013 | 09/10/2016 | 2016 | 1276 | 182.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30983160_R4 TERMINOUS 1103 CIRCUIT RECON | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-04-08 | 2016-04-08 | COMP | 2016-04-11 | 2016-04-11 | COMP | 2016-04-11 | 2016-04-11 | COMP | 2016-04-11 | 2016-05-10 | COMP | 2016-05-10 | 2016-08-29 | COMP | 2016-08-29 | 2016-08-29 | 3 | 140 | 336716.68
30983162 | OC4 OCGC TERMINOUS 1102 CIRCUIT-EMPIRE | 03/14/2013 | 106832208 | 03/14/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 05/31/2014 | ED.16302.1102 | TERMINOUS 1102 | 039 | SAN JOAQUIN CO | 5535457 | DO 08 - Monthly Forecast Only | 11,247.000 | 11,250.000 | 08J | 2013 | 08/13/2016 | 2016 | 1248 | 178.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | R2 TERMINOUS 1102 CIRCUIT-EMPIRE TRCT | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-12-18 | 2015-12-18 | COMP | 2016-01-20 | 2016-01-20 | COMP | 2016-01-29 | 2016-01-29 | COMP | 2016-01-29 | 2016-04-15 | COMP | 2016-04-15 | 2016-07-27 | COMP | 2016-07-27 | 2016-07-27 | 42 | 180 | 463349.71
30983238 | _PODVA_RECONDUCTOR_RESEARCH 2102 | 03/15/2013 | 106832561 | 03/14/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/21/2014 | ED.01469.2102 | RESEARCH 2102 | 007 | CONTRA COSTA C | 5535457 | DO 08 - Monthly Forecast Only | 1,380.000 | 1,380.000 | 08J | 2013 | 01/26/2019 | 2019 | 2143 | 306.1429 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30983238_R1_2014_PODVA_RECONDUCTOR_RESEA | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-02-27 | 2016-02-27 | COMP | 2016-03-01 | 2016-03-01 | COMP | 2016-03-01 | 2016-03-01 | COMP | 2016-03-01 | 2016-04-13 | COMP | 2016-04-13 | 2016-08-18 | COMP | 2016-08-18 | 2016-08-18 | 3 | 170 | 252615.07
30983264 | 2014 ANGIOLA 1104 RECONDUCTOR | 03/15/2013 | 106834086 | 03/15/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/01/2014 | ED.25215.1104 | ANGIOLA 1104 | 016 | KINGS COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 5,707.000 | 5,710.000 | 08J | 2013 | 02/20/2016 | 2016 | 1072 | 153.1429 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30983264_R2 ANGIOLA 1104 RE-CONDUCTOR_06 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2014-05-21 | 2014-05-21 | COMP | 2014-07-02 | 2014-09-09 | COMP | 2014-09-09 | 2014-09-09 | COMP | 2014-09-09 | 2014-12-02 | COMP | 2014-12-02 | 2016-01-28 | COMP | 2016-01-28 | 2016-01-28 | 111 | 506 | 439584.28
30983276 | OC4 2014 KERMAN 1102 OVERLOADS | 03/15/2013 | 106834604 | 03/15/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 05/01/2014 | ED.25271.1102 | KERMAN 1102 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 4,560.000 | 0.000 | 08J | 2013 | 12/10/2016 | 2016 | 1366 | 195.1429 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30983276_R2 KERMAN 1102 OVERLOADS_06E | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2014-04-08 | 2014-06-06 | COMP | 2014-04-08 | 2015-11-14 | COMP | 2015-11-14 | 2015-11-19 | COMP | 2015-11-14 | 2016-11-22 | COMP | 2016-11-22 | 2016-11-22 | COMP | 2016-11-22 | 2016-11-22 | 590 | 369 | 420646.88
30983299 | OCCC_BAY MEADOWS 1103 REPL ONE SPAN | 03/15/2013 | 106830681 | 03/13/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 08/28/2014 | ED.02401.1103.SWIT | SWITCHES | 041 | SAN MATEO COUN | 5505513 | PN-OH ANNEALED/DETER CNDCTR: PM MGD | 0.000 | 0.000 | 08J | 2013 | 10/21/2017 | 2017 | 1681 | 240.1429 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30983299_REPLACE ONE SPAN OH BM1103_08J | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-12-14 | 2016-12-18 | COMP | 2016-12-14 | 2016-12-30 | COMP | 2016-12-30 | 2016-12-30 | COMP | 2016-12-30 | 2017-09-25 | COMP | 2017-09-25 | 2017-10-13 | COMP | 2017-10-13 | 2017-10-16 | 16 | 290 | 112506.13
30983940 | +RECONDUCTOR 2 SPANS LEMOORE 1101 | 03/18/2013 | 106835881 | 03/18/2013 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/05/2014 | ED.25360.1101.RECL | RECLOSERS | 016 | KINGS COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 950.000 | 0.000 | 08J | 2013 | # | OPEN | 2818 | 402.5714 | DOCC | 8 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | INPR | 2014-09-04 | 0 | INPR | 2014-09-04 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | -41886 | 0 | 96283.53
30983942 | OC4 2014 JACOBS CORNER 1101 RECONDUCTOR | 03/18/2013 | 106831916 | 03/14/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/04/2014 | ED.25477.1101.RECL | RECLOSERS | 016 | KINGS COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 12,243.000 | 08J | 2013 | 12/10/2016 | 2016 | 1363 | 194.7143 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30983942_R2 RECON 13,000' OF 4AR J CORNE | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2014-04-25 | 2014-06-09 | COMP | 2014-04-25 | 2014-06-12 | COMP | 2014-06-17 | 2014-07-11 | COMP | 2016-01-07 | 2016-10-27 | COMP | 2016-10-27 | 2016-10-27 | COMP | 2016-10-27 | 2016-12-02 | 77 | 875 | 417309.56
30983944 | +MB 1101 OCB STAR ZONE PHS 2 | 03/18/2013 | 106836440 | 03/18/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/01/2014 | ED.18301.1101 | MORRO BAY 1101 | 040 | SAN LUIS OBISP | 5535457 | DO 08 - Monthly Forecast Only | 2,500.000 | 0.000 | 08J | 2013 | 08/08/2015 | 2015 | 873 | 124.7143 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | R5 MB 1101 OCB STAR ZONE PHS 2 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2014-08-21 | 2014-10-21 | COMP | 2014-08-21 | 2014-11-17 | COMP | 2014-11-17 | 2014-11-17 | COMP | 2014-11-17 | 2014-11-24 | COMP | 2014-11-24 | 2014-12-13 | COMP | 2014-12-13 | 2014-12-18 | 88 | 31 | 361989.99
30983947 | OCGC 2014 KETTLEMAN 1101 RECONDUCTOR | 03/18/2013 | 106836586 | 03/18/2013 | # | Not assigned | 40 | Closed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 09/27/2014 | ED.25273.1101 | KETTLEMAN HILLS 1101 | 016 | KINGS COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 3,300.000 | 08J | 2013 | 01/10/2015 | 2015 | 663 | 94.7143 | CLSD | 12 | E070 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30983947_R2 KETTLEMAN 1101 RE-CONDUCTOR | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2014-06-23 | 2014-08-27 | COMP | 2014-06-23 | 2014-08-28 | COMP | 2014-08-28 | 2014-08-28 | COMP | 2014-08-28 | 2014-09-08 | COMP | 2014-09-08 | 2015-01-08 | COMP | 2015-01-08 | 2015-01-08 | 66 | 133 | 96340.74
30984061 | OCGC+HOT - SISQUOC 1103 (CAMBRIA WINERY) | 03/18/2013 | 106838766 | 03/18/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/01/2014 | ED.18281.1103 | SISQUOC 1103 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 9,654.000 | 9,654.000 | 08J | 2013 | 03/19/2016 | 2016 | 1097 | 156.7143 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | R5 SISQUOC 1103 WD@7477 12-70633 PHS 1 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-05-19 | 2015-08-11 | COMP | 2015-05-19 | 2015-08-17 | COMP | 2015-08-17 | 2015-10-21 | COMP | 2015-10-21 | 2016-02-13 | COMP | 2016-02-13 | 2016-02-13 | COMP | 2016-02-13 | 2016-02-25 | 155 | 127 | 491404.85
30984065 | +SISQUOC 1103 PH 5&6 (CAMBRIA WINERY) | 03/18/2013 | 106838785 | 03/18/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/01/2014 | ED.18281.1103 | SISQUOC 1103 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 4,412.000 | 4,412.000 | 08J | 2013 | 10/03/2020 | 2020 | 2756 | 393.7143 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | R5 SISQUOC 1103 WD@7477 12-70633 PHS 6 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-05-19 | 2016-07-05 | COMP | 2016-05-19 | 2016-07-07 | COMP | 2016-07-07 | 2016-07-07 | COMP | 2016-07-07 | 2016-08-18 | COMP | 2016-08-18 | 2016-10-29 | COMP | 2016-10-29 | 2016-10-29 | 49 | 114 | 98879.04
30984220 | OC4 2014 DEVILS DEN 1101 RECONDUCTOR | 03/19/2013 | 106840105 | 03/19/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/28/2014 | ED.25345.1101 | DEVILS DEN 1101 | 016 | KINGS COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 5,700.000 | 08J | 2013 | 10/31/2015 | 2015 | 956 | 136.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30984220_R2 DEVILS DEN 1101 6CU RECONDUC | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2014-01-29 | 2014-03-08 | COMP | 2014-01-29 | 2014-03-11 | COMP | 2014-03-21 | 2014-04-01 | COMP | 2014-04-01 | 2014-04-03 | COMP | 2014-04-03 | 2015-10-09 | COMP | 2015-10-09 | 2015-10-09 | 62 | 556 | 273933.98
30984504 | *CANC* R5 DIVIDE 1102 WD 13-0009119*CANC | 03/21/2013 | 106841454 | 03/20/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/01/2014 | ED.18257.1102 | DIVIDE 1102 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2013 | 07/03/2015 | 2015 | 834 | 119.1429 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2015-07-03 | 2015-07-03 | # | 2015-07-03 | 2015-07-03 | # | 2015-07-03 | 2015-07-03 | # | 2015-07-03 | 2015-07-03 | # | 2015-07-03 | 2015-07-03 | # | 2015-07-03 | 2015-07-03 | 0 | 0 | 0
30984507 | OC4 OCG BPO+SISQUOC 1102 PHS 2 - FOXEN C | 03/21/2013 | 106841777 | 03/20/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/01/2014 | ED.18281.1102 | SISQUOC 1102 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 2,615.000 | 2,615.000 | 08J | 2013 | 02/20/2016 | 2016 | 1066 | 152.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30984507_R5 SISQUOC 1102 WD 13-0006447 P | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-04-09 | 2015-06-23 | COMP | 2015-04-09 | 2015-06-29 | COMP | 2015-06-29 | 2015-07-02 | COMP | 2015-07-02 | 2016-01-27 | COMP | 2016-01-27 | 2016-01-27 | COMP | 2016-01-27 | 2016-02-02 | 84 | 215 | 143568.91
30984641 | OCLH PARL 1103 RECON 2 SPANS 800' OF 2CU | 03/21/2013 | 106842302 | 03/21/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/13/2013 | ED.25229.1103.SWIT | SWITCHES | 010 | FRESNO COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 982.000 | 0.000 | 08W | 2013 | 02/14/2015 | 2015 | 695 | 99.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2014-06-17 | 2014-07-22 | COMP | 2014-06-17 | 2014-07-23 | COMP | 2014-07-23 | 2014-07-23 | COMP | 2014-07-23 | 2014-12-18 | COMP | 2014-12-18 | 2015-01-13 | COMP | 2015-01-13 | 2015-01-13 | 36 | 174 | 39517.24
30984679 | OC4 2014 KERMAN 1108 OVRLOAD & LOW VOLT | 03/21/2013 | 106842869 | 03/21/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/01/2014 | ED.25271.1108 | KERMAN 1108 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 5,752.000 | 5,752.000 | 08J | 2013 | 02/20/2016 | 2016 | 1066 | 152.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30984679_R2 KERMAN 1108 OVELOADS AND LOW | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2014-04-30 | 2014-06-14 | COMP | 2014-04-30 | 2014-06-16 | COMP | 2014-06-24 | 2014-07-28 | COMP | 2014-07-28 | 2014-08-05 | COMP | 2014-08-05 | 2016-01-25 | COMP | 2016-01-25 | 2016-01-25 | 89 | 546 | 416606.06
30984686 | OCGC PIERCY 2110 RECONDUCTOR | 03/21/2013 | 106842865 | 03/21/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2013 | ED.08391.2110.RECL | RECLOSERS | 043 | SANTA CLARA CO | 5535457 | DO 08 - Monthly Forecast Only | 3,060.000 | 2,310.000 | 08J | 2013 | 03/19/2016 | 2016 | 1094 | 156.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-02-04 | 2015-02-04 | COMP | 2015-03-27 | 2015-03-27 | COMP | 2015-03-27 | 2015-03-27 | COMP | 2015-03-27 | 2015-05-11 | COMP | 2015-05-11 | 2016-02-02 | COMP | 2016-02-02 | 2016-02-04 | 51 | 314 | 230606.62
30984721 | *CANC* SISQUOC 1102 WD 13-0006447 P*CANC | 03/21/2013 | 106842788 | 03/21/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/01/2014 | ED.18281.1102 | SISQUOC 1102 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2013 | 01/05/2015 | 2015 | 655 | 93.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2015-01-05 | 2015-01-05 | # | 2015-01-05 | 2015-01-05 | # | 2015-01-05 | 2015-01-05 | # | 2015-01-05 | 2015-01-05 | # | 2015-01-05 | 2015-01-05 | # | 2015-01-05 | 2015-01-05 | 0 | 0 | 0
30984722 | *CANC* SISQUOC 1102 WD 13-0006447*CANC | 03/21/2013 | 106842787 | 03/21/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/01/2014 | ED.18281.1102 | SISQUOC 1102 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2013 | 01/05/2015 | 2015 | 655 | 93.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2015-01-05 | 2015-01-05 | # | 2015-01-05 | 2015-01-05 | # | 2015-01-05 | 2015-01-05 | # | 2015-01-05 | 2015-01-05 | # | 2015-01-05 | 2015-01-05 | # | 2015-01-05 | 2015-01-05 | 0 | 0 | 0
30984775 | OCGC 93PL OH DET WIRE ON NAPA 1104 | 03/22/2013 | 106842607 | 03/21/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/31/2014 | ED.04202.1104 | NAPA 1104 | 028 | NAPA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 462.000 | 0.000 | 08W | 2013 | 08/19/2017 | 2017 | 1611 | 230.1429 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-08-23 | 2016-08-23 | COMP | 2016-09-08 | 2016-09-08 | COMP | 2016-09-08 | 2016-09-08 | COMP | 2016-09-08 | 2016-09-16 | COMP | 2016-09-16 | 2016-12-22 | COMP | 2016-12-22 | 2016-12-22 | 16 | 105 | 239082.26
30985765 | OC4 OCGC LINDEN 1103 RECONDUCTOR COMSTO | 03/27/2013 | 106849009 | 03/26/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/26/2014 | ED.16207.1103 | LINDEN 1103 | 039 | SAN JOAQUIN CO | 5535457 | DO 08 - Monthly Forecast Only | 3,260.000 | 3,260.000 | 08J | 2013 | 03/19/2016 | 2016 | 1088 | 155.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-06-18 | 2015-06-18 | COMP | 2015-07-14 | 2015-07-14 | COMP | 2015-07-14 | 2015-07-16 | COMP | 2015-07-14 | 2015-07-24 | COMP | 2015-07-24 | 2016-02-17 | COMP | 2016-02-17 | 2016-02-17 | 28 | 216 | 68964.21
30985768 | OCGC2014 DEVILS DEN 1101 RECND ANNEAL #1 | 03/27/2013 | 106848682 | 03/26/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/26/2014 | ED.25345.1101 | DEVILS DEN 1101 | 016 | KINGS COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 5,366.000 | 5,400.000 | 08J | 2013 | 01/23/2016 | 2016 | 1032 | 147.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30985768_R2 DEVILS DEN 1101 #1 ANNEALED | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2014-06-23 | 2014-07-23 | COMP | 2014-06-23 | 2014-08-05 | COMP | 2014-08-05 | 2014-08-05 | COMP | 2014-08-05 | 2014-08-08 | COMP | 2014-10-27 | 2015-12-08 | COMP | 2015-12-08 | 2015-12-09 | 43 | 491 | 131870.27
30985802 | OCGC 2014 DEVILS DEN 1101 RECON ANNEAL#2 | 03/27/2013 | 106848707 | 03/26/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/26/2014 | ED.25345.1101 | DEVILS DEN 1101 | 016 | KINGS COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 3,156.000 | 3,200.000 | 08J | 2013 | 01/23/2016 | 2016 | 1032 | 147.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30985802_R2 DEVILS DEN 1101 #2 ANNEALED | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2014-08-01 | 2014-07-22 | COMP | 2014-06-23 | 2014-08-04 | COMP | 2014-08-04 | 2014-08-04 | COMP | 2014-08-04 | 2014-08-08 | COMP | 2014-08-08 | 2015-12-08 | COMP | 2015-12-08 | 2015-12-08 | 3 | 491 | 57263.26
30985803 | OCLH BARTON 1101 4 ACSR | 03/27/2013 | 106849593 | 03/27/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/27/2013 | ED.25357.1101 | BARTON 1101 | 010 | FRESNO COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 831.000 | 0.000 | 08W | 2013 | 09/21/2019 | 2019 | 2369 | 338.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2014-12-11 | 2014-12-11 | COMP | 2014-12-17 | 2014-12-17 | COMP | 2014-12-17 | 2015-06-12 | COMP | 2015-06-12 | 2015-09-09 | COMP | 2015-09-09 | 2016-01-29 | COMP | 2016-01-29 | 2016-02-09 | 183 | 242 | 25107.25
30985827 | RELIABILITY IMPROVEMENT NOVATO 1104 | 03/27/2013 | 106850218 | 03/27/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/28/2014 | ED.04221.1104.SWIT | SWITCHES | 021 | MARIN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 462.000 | 0.000 | 08J | 2013 | 07/23/2016 | 2016 | 1214 | 173.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30985827_RELIABILITY IMPROVEMENT ON NOVA | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-10-28 | 2015-09-11 | COMP | 2015-10-28 | 2015-10-28 | COMP | 2015-10-28 | 2015-10-28 | COMP | 2015-10-28 | 2016-04-27 | COMP | 2016-04-27 | 2016-04-28 | COMP | 2016-04-28 | 2016-05-03 | 0 | 188 | 136294.69
30986367 | INSTALL FUSE ON GRAND ISLAND 2226 | 03/29/2013 | 106852994 | 03/29/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2014 | ED.06246.2226.SECT | SECTIONALIZERS | 048 | SOLANO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 390.000 | 1.000 | 08J | 2013 | 03/19/2016 | 2016 | 1086 | 155.1429 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-07-31 | 2015-09-08 | COMP | 2015-07-31 | 2015-09-09 | COMP | 2015-09-10 | 2015-09-10 | COMP | 2015-09-10 | 2016-02-18 | COMP | 2016-02-18 | 2016-02-18 | COMP | 2016-02-18 | 2016-02-23 | 41 | 166 | 14654.53
30986858 | OCGCREPL OH DET WIRE ON WILLOW PASS 2108 | 04/02/2013 | 106854571 | 04/01/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/30/2014 | ED.01445.2104 | KIRKER 2104 | 007 | CONTRA COSTA C | 5535457 | DO 08 - Monthly Forecast Only | 729.000 | 729.000 | 08J | 2013 | 09/24/2016 | 2016 | 1271 | 181.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30986858 _REPL OH DET WIRE | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-02-23 | 2016-02-23 | COMP | 2016-02-24 | 2016-02-24 | COMP | 2016-02-24 | 2016-02-24 | COMP | 2016-02-24 | 2016-04-13 | COMP | 2016-04-13 | 2016-08-09 | COMP | 2016-08-09 | 2016-08-09 | 1 | 167 | 145430.51
30987092 | *CANC* REPL DET COND, FREEDOM & PR*CANC | 04/03/2013 | 106852744 | 03/29/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/18/2014 | ED.08351.0403 | ERTA 0403 | 044 | SANTA CRUZ COU | 5535457 | DO 08 - Monthly Forecast Only | 820.000 | 0.000 | 08J | 2013 | 07/03/2015 | 2015 | 821 | 117.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2015-07-03 | 2015-07-03 | # | 2015-07-03 | 2015-07-03 | # | 2015-07-03 | 2015-07-03 | # | 2015-07-03 | 2015-07-03 | # | 2015-07-03 | 2015-07-03 | # | 2015-07-03 | 2015-07-03 | 0 | 0 | 0
30987612 | OC4 CABRILLO 1104 WD 13-1583 LOC 1 | 04/05/2013 | 106860614 | 04/05/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/01/2015 | ED.18310.1104 | CABRILLO 1104 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 1,755.000 | 0.000 | 08J | 2013 | 12/16/2017 | 2017 | 1716 | 245.1429 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30987612_R5 CABRILLO 1104 WD 13-1583 LOC | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-08-26 | 2015-08-26 | COMP | 2015-09-02 | 2015-09-02 | COMP | 2015-09-09 | 2015-09-09 | COMP | 2015-09-09 | 2016-03-25 | COMP | 2016-03-25 | 2016-03-25 | COMP | 2016-03-25 | 2016-03-28 | 14 | 201 | 101807.5
30987613 | +CABRILLO 1104 (SURF TAP) | 04/05/2013 | 106860617 | 04/05/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/01/2015 | ED.18310.1104 | CABRILLO 1104 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 2,343.000 | 2,037.000 | 08J | 2013 | 02/18/2017 | 2017 | 1415 | 202.1429 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | R5 CAB 1104 WD 13-1583 LOC 2 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-09-15 | 2016-10-06 | COMP | 2016-09-15 | 2016-11-04 | COMP | 2016-11-04 | 2016-11-07 | COMP | 2016-11-07 | 2016-11-14 | COMP | 2016-11-14 | 2017-01-19 | COMP | 2017-01-19 | 2017-02-13 | 53 | 98 | 97699.77
30987692 | OCGC IMPROVERELIABILITY ON IGNACIO-1104 | 04/05/2013 | 106856379 | 04/02/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 02/28/2014 | ED.04248.1104.COND | CONDUCTOR | 021 | MARIN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 1,755.000 | 1,755.000 | 08J | 2013 | 05/27/2017 | 2017 | 1513 | 216.1429 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30987692_RELIABILITY IMPROVEMENT ON IGNA | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-10-03 | 2016-10-03 | COMP | 2016-10-13 | 2016-10-13 | COMP | 2016-10-13 | 2016-10-13 | COMP | 2016-10-13 | 2017-02-10 | COMP | 2017-02-10 | 2017-02-21 | COMP | 2017-02-21 | 2017-02-21 | 10 | 131 | 162367.66
30987882 | 2015 OAKHURST 1101 RECNDUCTR ANEAL CD | 04/07/2013 | 106860222 | 04/05/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2014 | ED.25442.1101 | OAKHURST 1101 | 020 | MADERA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 8,402.000 | 8,402.000 | 08J | 2013 | 08/27/2016 | 2016 | 1238 | 176.8571 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30987882_REPL. ANNEALED COND. OAKHURST 1 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-10-21 | 2015-12-15 | COMP | 2015-10-21 | 2015-12-22 | COMP | 2015-12-22 | 2015-12-29 | COMP | 2015-12-29 | 2016-01-21 | COMP | 2016-01-21 | 2016-07-12 | COMP | 2016-07-12 | 2016-07-12 | 69 | 196 | 539363.1
30988779 | +CAMBRIA 1102 (CAMBRIA SUB/STATE PARK) | 04/11/2013 | 106874005 | 04/11/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 05/01/2015 | ED.18277.1102 | CAMBRIA 1102 | 040 | SAN LUIS OBISP | 5535457 | DO 08 - Monthly Forecast Only | 1,313.000 | 1,313.000 | 08J | 2013 | 06/10/2017 | 2017 | 1521 | 217.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30988779_R5 CAMBRIA 1102 WD 13-11001 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-06-13 | 2016-06-13 | COMP | 2016-06-16 | 2016-06-16 | COMP | 2016-06-16 | 2016-06-16 | COMP | 2016-06-16 | 2016-08-09 | COMP | 2016-08-09 | 2016-11-03 | COMP | 2016-11-03 | 2016-11-07 | 3 | 144 | 213776.53
30988841 | R4E REFRAME THREE POLE SS2110 AT C2044 | 04/11/2013 | 106873754 | 04/11/2013 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 08/30/2013 | ED.15365.2110.CAPA | CAPACITORS | 009 | EL DORADO COUN | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2013 | # | OPEN | 2794 | 399.1429 | UNSE | 1 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 1920.72
30989646 | OC4 E WEST SAC 1109 RECONDUCTOR 700 FEET | 04/15/2013 | 106878216 | 04/15/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/27/2014 | ED.06313.1109.TXFR.TROH | OVERHEAD TRANSFORMERS | 057 | YOLO COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 518.000 | 0.000 | 08W | 2013 | 01/31/2015 | 2015 | 656 | 93.7143 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2014-01-16 | 2014-01-16 | COMP | 2014-01-17 | 2014-01-31 | COMP | 2014-02-05 | 2014-02-19 | COMP | 2014-02-19 | 2014-02-24 | COMP | 2014-02-24 | 2014-03-24 | COMP | 2014-03-24 | 2014-07-01 | 34 | 132 | 21005.96
30989894 | OCGC ARCATA 1105 REMOVE EXCESS SPLICES | 04/16/2013 | 106880044 | 04/16/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/30/2014 | ED.19202.1105.SWIT | SWITCHES | 012 | HUMBOLDT COUNT | 5532479 | CWSP 08W - Monthly Forecast Only | 1,540.000 | 1,540.000 | 08W | 2013 | 01/26/2019 | 2019 | 2111 | 301.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30989894_ARCATA 1105 REMOVE EXCESSIVE SP | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-05-18 | 2015-06-24 | COMP | 2015-05-18 | 2015-07-29 | COMP | 2015-07-29 | 2015-07-29 | COMP | 2015-07-29 | 2015-09-09 | COMP | 2015-09-09 | 2016-01-27 | COMP | 2016-01-27 | 2016-02-01 | 72 | 187 | 126013.5
30990066 | OCGC GARBERVIL 1101REPLC EXCESIV SPLICES | 04/17/2013 | 106880093 | 04/16/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/26/2015 | ED.19222.1101.SWIT | SWITCHES | 012 | HUMBOLDT COUNT | 5535457 | DO 08 - Monthly Forecast Only | 4,400.000 | 4,723.000 | 08J | 2013 | 03/18/2017 | 2017 | 1431 | 204.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30990066_GARBERVILLE 1101 REPLC EXCESSIV | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-10-27 | 2016-10-27 | COMP | 2016-11-01 | 2016-11-01 | COMP | 2016-11-01 | 2016-11-01 | COMP | 2016-11-01 | 2016-11-08 | COMP | 2016-11-08 | 2017-01-19 | INPR | 2017-01-19 | 2017-03-18 | 5 | 137 | 852317.18
30990258 | OCGC XKING CITY 1106 RECONDUCTORING | 04/18/2013 | 106881449 | 04/17/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2015 | ED.18203.1106 | KING CITY 1106 | 027 | MONTEREY COUNT | 5532479 | CWSP 08W - Monthly Forecast Only | 3,931.000 | 4,561.000 | 08W | 2013 | 12/26/2015 | 2015 | 982 | 140.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30990258_R2 LAYOUS RANCH RECONDUCTORING | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2014-10-20 | 2014-11-21 | COMP | 2014-10-20 | 2014-12-15 | COMP | 2015-04-22 | 2015-04-22 | COMP | 2014-12-23 | 2014-12-23 | COMP | 2014-12-23 | 2014-12-24 | COMP | 2014-12-24 | 2014-12-24 | 184 | -119 | 241839.38
30991793 | OLEMA 1101 CIRCUIT IMPROVEMENT | 04/23/2013 | 106886394 | 04/23/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 08/30/2014 | ED.04229.1101.COND | CONDUCTOR | 021 | MARIN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 1,191.000 | 1,191.000 | 08J | 2013 | 07/23/2016 | 2016 | 1187 | 169.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30991793_OLEMA 1101 CIRCUIT IMPROVEMENT_ | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-10-20 | 2015-10-09 | COMP | 2015-10-20 | 2015-10-20 | COMP | 2015-10-20 | 2015-10-20 | COMP | 2015-10-20 | 2016-04-14 | COMP | 2016-04-14 | 2016-05-12 | COMP | 2016-05-12 | 2016-05-12 | 0 | 205 | 145336.33
30991794 | BOLINAS 1101 RELIABILITY+ IMPROVEMENT | 04/23/2013 | 106886472 | 04/23/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 08/30/2013 | ED.04226.1101.COND | CONDUCTOR | 021 | MARIN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 319.000 | 319.000 | 08J | 2013 | 05/14/2016 | 2016 | 1117 | 159.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-06-10 | 2015-06-10 | COMP | 2015-06-25 | 2015-06-25 | COMP | 2015-06-25 | 2015-06-25 | COMP | 2015-06-25 | 2015-09-10 | COMP | 2015-09-10 | 2016-02-02 | COMP | 2016-02-02 | 2016-02-03 | 15 | 223 | 81365.85
30991832 | OCLH SCHINDLER 1105 - REPLACE 2 SPANS 4 | 04/23/2013 | 106887082 | 04/23/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/15/2013 | ED.25289.1105 | SCHINDLER 1105 | 010 | FRESNO COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 468.000 | 468.000 | 08W | 2013 | 02/14/2015 | 2015 | 662 | 94.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2013-10-03 | 2014-09-25 | COMP | 2013-10-03 | 2014-09-26 | COMP | 2014-09-29 | 2014-09-29 | COMP | 2014-09-29 | 2014-10-05 | COMP | 2014-10-05 | 2014-12-22 | COMP | 2014-12-22 | 2014-12-29 | 361 | 91 | 14136.46
30992568 | OCGCRPLCE 400 FT OF 2ACSR ON PIT #3 2101 | 04/26/2013 | 106889846 | 04/25/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2015 | ED.87-C470000000 | SHASTA MAP C47 | 045 | SHASTA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 198.000 | 198.000 | 08J | 2013 | 05/14/2016 | 2016 | 1114 | 159.1429 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-08-27 | 2015-08-27 | COMP | 2015-09-09 | 2015-09-09 | COMP | 2015-09-09 | 2015-09-09 | COMP | 2015-09-09 | 2016-04-12 | COMP | 2016-04-12 | 2016-04-12 | COMP | 2016-04-12 | 2016-05-03 | 13 | 237 | 14026.03
30992704 | OC4 OCGC VICTOR 1102 WIRE DOWN RECONDUC | 04/26/2013 | 106890859 | 04/26/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/26/2014 | ED.16328.1102 | VICTOR 1102 | 039 | SAN JOAQUIN CO | 5535457 | DO 08 - Monthly Forecast Only | 1,979.000 | 1,979.000 | 08J | 2013 | 09/19/2015 | 2015 | 876 | 125.1429 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-05-29 | 2015-05-29 | COMP | 2015-06-04 | 2015-06-04 | COMP | 2015-06-04 | 2015-06-04 | COMP | 2015-06-04 | 2015-06-12 | COMP | 2015-06-12 | 2015-08-21 | COMP | 2015-08-21 | 2015-08-24 | 6 | 81 | 103033.12
30993111 | OC4 OCGC WYANDOTTE 1105 - BLOOMER HILL R | 04/29/2013 | 106890889 | 04/26/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/01/2015 | ED.13-D260000000 | OROVILLE MAP D26 | 004 | BUTTE COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 3,699.000 | 3,699.000 | 08J | 2013 | 10/15/2016 | 2016 | 1265 | 180.7143 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-01-15 | 2015-01-15 | COMP | 2015-02-04 | 2015-02-04 | COMP | 2015-02-26 | 2015-02-27 | COMP | 2015-02-27 | 2015-03-09 | COMP | 2015-03-09 | 2015-04-09 | COMP | 2015-04-09 | 2015-04-13 | 43 | 45 | 266980.12
30993112 | OCGC BANGOR 1101 LA PORTE RD RECON 6050' | 04/29/2013 | 106890888 | 04/26/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/01/2015 | ED.13-J270900000 | OROVILLE MAP J2709 | 004 | BUTTE COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 4,330.000 | 4,330.000 | 08J | 2013 | 01/21/2017 | 2017 | 1363 | 194.7143 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30993112 Bangor 1101 Recond 6,050ft OH_0 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-11-19 | 2015-11-19 | COMP | 2015-12-10 | 2015-12-10 | COMP | 2015-12-16 | 2015-12-16 | COMP | 2015-12-16 | 2016-04-28 | COMP | 2016-04-28 | 2016-06-22 | COMP | 2016-06-22 | 2016-07-06 | 27 | 203 | 304755.15
30993194 | MEN 402 REPL 630FT &3 PLS/219 ATHERTON A | 04/30/2013 | 106891098 | 04/26/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/18/2013 | ED.02413.0402.TXFR.TROH | OVERHEAD TRANSFORMERS | 041 | SAN MATEO COUN | 5535457 | DO 08 - Monthly Forecast Only | 665.000 | 2,750.000 | 08W | 2013 | 01/28/2018 | 2018 | 1734 | 247.7143 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2014-10-01 | 2014-10-01 | COMP | 2014-10-11 | 2014-10-11 | COMP | 2014-10-11 | 2014-10-11 | COMP | 2014-10-11 | 2015-01-14 | COMP | 2015-01-14 | 2015-01-14 | COMP | 2015-01-14 | 2015-01-14 | 10 | 95 | 78207.3
30993279 | OCLHRECOND 5 SPANS 4AR,@ 50/52 NASHUA RD | 04/30/2013 | 106910512 | 04/30/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 07/12/2014 | ED.18235.2104 | CASTROVILLE 2104 | 027 | MONTEREY COUNT | 5532479 | CWSP 08W - Monthly Forecast Only | 1,456.000 | 0.000 | 08W | 2013 | 04/11/2015 | 2015 | 711 | 101.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2014-06-05 | 2014-06-26 | COMP | 2014-06-05 | 2014-06-27 | COMP | 2014-06-27 | 2014-06-27 | COMP | 2014-06-27 | 2014-07-08 | COMP | 2014-07-08 | 2014-07-09 | COMP | 2014-07-09 | 2014-07-14 | 22 | 17 | 20761.4
30993327 | OCLHR1 RECONDUCTOR 390' OHDUMBARTON 2111 | 04/30/2013 | 106893356 | 04/29/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/25/2013 | ED.01447.2111 | DUMBARTON 2111 | 001 | ALAMEDA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 386.000 | 0.000 | 08W | 2013 | 05/09/2015 | 2015 | 739 | 105.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2014-02-20 | 2014-03-10 | COMP | 2014-02-20 | 2014-03-12 | COMP | 2014-03-14 | 2014-03-14 | COMP | 2014-03-14 | 2014-03-22 | COMP | 2014-03-22 | 2014-04-15 | COMP | 2014-04-15 | 2014-04-19 | 22 | 36 | 39185.11
30994216 | OCCC RECOND. 275 FT.NO CAMPH-GLORIA RD. | 05/03/2013 | 106916243 | 05/03/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/24/2015 | ED.18205.2101 | SOLEDAD 2101 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 666.000 | 0.000 | 08J | 2013 | 06/25/2016 | 2016 | 1149 | 164.1429 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-08-26 | 2015-08-26 | COMP | 2015-08-27 | 2015-09-11 | COMP | 2015-09-15 | 2015-09-15 | COMP | 2015-09-15 | 2016-04-11 | COMP | 2016-04-11 | 2016-04-19 | COMP | 2016-04-19 | 2016-04-19 | 20 | 217 | 49767.91
30995111 | OCGC RPL OH COND/REMOVE BUMPS ++__401C | 05/08/2013 | 106920201 | 05/07/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/29/2013 | ED.04255.0401 | VALLEJO C 0401 | 048 | SOLANO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 250.000 | 250.000 | 08J | 2013 | 11/19/2016 | 2016 | 1291 | 184.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-06-01 | 2016-06-01 | COMP | 2016-06-01 | 2016-06-01 | COMP | 2016-06-01 | 2016-06-01 | COMP | 2016-06-01 | 2016-07-27 | COMP | 2016-07-27 | 2016-10-13 | COMP | 2016-10-13 | 2016-10-17 | 0 | 138 | 22174.04
30995130 | RECONDUCTOR 4AR LAKEVIEW 1102 | 05/07/2013 | 106919977 | 05/07/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 01/28/2015 | ED.25341.1102.TXFR.TROH | OVERHEAD TRANSFORMERS | 015 | KERN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 540.000 | 540.000 | 08J | 2013 | 06/13/2015 | 2015 | 767 | 109.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-01-23 | 2015-01-23 | COMP | 2015-01-27 | 2015-01-27 | COMP | 2015-01-27 | 2015-01-27 | COMP | 2015-01-27 | 2015-02-21 | COMP | 2015-02-21 | 2015-04-16 | COMP | 2015-04-16 | 2015-04-20 | 4 | 83 | 22052.92
30995212 | OC4 OCGC RECON FT ROSS RD FTROSS 1121 4/ | 05/08/2013 | 106920851 | 05/08/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/05/2014 | ED.04285.1121.SWIT | SWITCHES | 049 | SONOMA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 7,018.000 | 7,018.000 | 08J | 2013 | 09/24/2016 | 2016 | 1235 | 176.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30995212_R7 RECON FT ROSS RD FT ROSS 112 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-12-07 | 2015-12-07 | COMP | 2015-12-10 | 2015-12-10 | COMP | 2015-12-31 | 2015-12-31 | COMP | 2015-12-31 | 2016-04-12 | COMP | 2016-04-12 | 2016-06-30 | COMP | 2016-06-30 | 2016-06-30 | 24 | 182 | 874426.13
30995405 | OCGC RECOND 500 FT W/ 2C, N/O SW 7553 | 05/09/2013 | 106921607 | 05/08/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 08/01/2014 | ED.18213.1104 | GONZALES 1104 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 644.000 | 644.000 | 08J | 2013 | 07/23/2016 | 2016 | 1171 | 167.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-11-03 | 2015-11-17 | COMP | 2015-11-03 | 2015-11-19 | COMP | 2015-11-19 | 2015-11-19 | COMP | 2015-11-19 | 2016-04-27 | COMP | 2016-04-27 | 2016-06-09 | COMP | 2016-06-09 | 2016-06-10 | 16 | 204 | 40256.83
30995407 | OCGC 2015 SCHINDLER 1114 RECONDUCTOR | 05/09/2013 | 106920682 | 05/08/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/30/2015 | ED.25289.1114 | SCHINDLER 1114 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 2,706.000 | 0.000 | 08J | 2013 | 03/10/2018 | 2018 | 1766 | 252.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | R2 SCHINDLER 1114 RE-CONDUCTOR 2015 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-02-13 | 2016-02-13 | COMP | 2016-04-25 | 2016-04-25 | COMP | 2016-04-25 | 2016-04-25 | COMP | 2016-04-26 | 2016-05-17 | COMP | 2016-05-17 | 2016-08-22 | COMP | 2016-08-22 | 2016-08-23 | 72 | 120 | 127303.66
30995416 | OCGC E 2015 PEORIA FLAT 1701 RECONDUCTOR | 05/09/2013 | 106920066 | 05/07/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/27/2014 | ED.16378.1701 | PEORIA 1701 | 055 | TUOLUMNE COUNT | 5535457 | DO 08 - Monthly Forecast Only | 2,565.000 | 2,565.000 | 08J | 2013 | 04/21/2018 | 2018 | 1808 | 258.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30995416_R2E PEORIA FLAT 1701 RECOND 485 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-01-23 | 2016-01-23 | COMP | 2016-01-27 | 2016-01-27 | COMP | 2016-01-27 | 2016-01-27 | COMP | 2016-01-27 | 2016-04-13 | COMP | 2016-04-13 | 2016-07-19 | COMP | 2016-07-19 | 2016-07-25 | 4 | 180 | 116962.14
30996729 | OC4 OCGC CALPELLA 1102 ANNEALED CONDUCTO | 05/16/2013 | 106940583 | 05/16/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/01/2014 | ED.04341.1101.SWIT | SWITCHES | 023 | MENDOCINO COUN | 5517127 | DO 08 - Monthly Forecast Only | 2,589.000 | 2,589.000 | 08J | 2013 | 06/16/2018 | 2018 | 1857 | 265.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30996729_CALPELLA 1102 ANNEALED CONDUCTO | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2014-08-27 | 2014-08-27 | COMP | 2014-12-02 | 2015-02-24 | COMP | 2015-02-27 | 2015-02-27 | COMP | 2015-02-24 | 2015-03-30 | COMP | 2015-03-30 | 2015-05-28 | COMP | 2015-05-28 | 2015-05-29 | 184 | 91 | 289794.51
30996891 | RECONDUCTOR ~605FT OH ON DUMBRTON 21 | 05/16/2013 | 106940530 | 05/16/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/27/2014 | ED.01447.2111 | DUMBARTON 2111 | 001 | ALAMEDA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 694.000 | 750.000 | 08J | 2013 | 01/28/2018 | 2018 | 1718 | 245.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-05-09 | 2016-05-09 | COMP | 2016-05-13 | 2016-05-13 | COMP | 2016-05-13 | 2016-05-13 | COMP | 2016-05-13 | 2016-07-11 | COMP | 2016-07-11 | 2016-10-04 | COMP | 2016-10-04 | 2016-10-06 | 4 | 146 | 43343.77
30997022 | X +RECONDUCTOR TO REMOVE SPLICES LG1106 | 05/17/2013 | 106942093 | 05/17/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/25/2014 | ED.08202.1106.SWIT | SWITCHES | 043 | SANTA CLARA CO | 5517127 | DO 08 - Monthly Forecast Only | 562.000 | 562.000 | 08J | 2013 | 06/16/2018 | 2018 | 1856 | 265.1429 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-09-15 | 2015-09-15 | COMP | 2015-10-07 | 2015-10-07 | COMP | 2015-10-07 | 2015-10-07 | COMP | 2015-10-07 | 2016-03-22 | COMP | 2016-03-22 | 2016-03-23 | COMP | 2016-03-23 | 2016-03-24 | 22 | 169 | 51445.46
30997023 | OCGC RECONDUC TO REMOVE SPLICES LG1106 | 05/17/2013 | 106942097 | 05/17/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/18/2014 | ED.08202.1106.SWIT | SWITCHES | 043 | SANTA CLARA CO | 5532479 | CWSP 08W - Monthly Forecast Only | 113.000 | 0.000 | 08W | 2013 | 02/20/2016 | 2016 | 1009 | 144.1429 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2014-11-18 | 2014-11-18 | COMP | 2015-01-06 | 2015-01-06 | COMP | 2015-01-06 | 2015-01-06 | COMP | 2015-01-06 | 2015-02-06 | COMP | 2015-02-06 | 2016-01-26 | COMP | 2016-01-26 | 2016-01-28 | 49 | 387 | 39645.86
30997776 | OCGC CRK 1111 - COHASSET RD RECOND 606' | 05/22/2013 | 106947720 | 05/21/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/31/2014 | ED.16-Q300200000 | CHICO MAP Q3002 | 004 | BUTTE COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 606.000 | 606.000 | 08J | 2013 | 10/15/2016 | 2016 | 1242 | 177.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-07-23 | 2015-07-23 | COMP | 2015-07-28 | 2015-07-28 | COMP | 2015-07-29 | 2015-07-29 | COMP | 2015-07-29 | 2016-01-28 | COMP | 2016-01-28 | 2016-01-28 | COMP | 2016-01-28 | 2016-02-02 | 6 | 188 | 60061.07
30997782 | *CANC* CAMBRIA LINE RECONFIG *CANC | 05/21/2013 | 106946069 | 05/20/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/30/2013 | ED.18277.1102 | CAMBRIA 1102 | 040 | SAN LUIS OBISP | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 2013 | 12/03/2017 | 2017 | 1657 | 236.7143 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2017-12-03 | 2017-12-03 | # | 2017-12-03 | 2017-12-03 | # | 2017-12-03 | 2017-12-03 | COMP | 2014-04-25 | 2014-04-25 | COMP | 2014-04-25 | 2014-04-25 | COMP | 2014-04-25 | 2014-04-25 | 0 | -1318 | 0
30999057 | RECONDUCTOR -MADISON 1105 WIRE DOWN | 05/28/2013 | 106954814 | 05/28/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2013 | ED.50-H110000000.STRU.POLE | YOLO H11 POLES | 057 | YOLO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 810.000 | 810.000 | 08J | 2013 | 08/27/2016 | 2016 | 1187 | 169.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-12-30 | 2015-12-30 | COMP | 2016-01-04 | 2016-01-04 | COMP | 2016-01-04 | 2016-01-04 | COMP | 2016-01-04 | 2016-04-12 | COMP | 2016-04-12 | 2016-07-14 | COMP | 2016-07-14 | 2016-07-15 | 5 | 193 | 24263.92
30999583 | OCGC CLOVIS 2109 RECONDUCTOR [SUNNY] | 05/30/2013 | 106957119 | 05/30/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/27/2015 | ED.25408.2109 | CLOVIS 2109 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 2,559.000 | 2,559.000 | 08J | 2013 | 07/23/2016 | 2016 | 1150 | 164.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | R2CLOVIS 2109 RECNDUCTR 2015 (SUNNYSIDE) | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-08-11 | 2015-10-07 | COMP | 2015-08-11 | 2015-10-08 | COMP | 2015-10-08 | 2015-10-08 | COMP | 2015-10-08 | 2016-04-13 | COMP | 2016-04-13 | 2016-05-26 | COMP | 2016-05-26 | 2016-05-26 | 58 | 231 | 306389.57
30999663 | 2015 BULLARD 2112 WIREDWN RECNDUCTR | 05/30/2013 | 106957565 | 05/30/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/26/2015 | ED.25396.2112 | BULLARD 2112 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 1,481.000 | 1,728.000 | 08J | 2013 | 07/23/2016 | 2016 | 1150 | 164.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | R2 BULLARD 2112 WIREDWN RECNDUCTR 2015 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-07-29 | 2015-07-29 | COMP | 2015-08-28 | 2015-09-24 | COMP | 2015-09-24 | 2015-09-24 | COMP | 2015-09-24 | 2015-10-16 | COMP | 2015-10-16 | 2015-11-02 | COMP | 2015-11-02 | 2015-11-02 | 57 | 39 | 216421.71
30999664 | OCGC 2015 CLOVIS 2109 RECONDUCTOR | 05/30/2013 | 106957561 | 05/30/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/26/2015 | ED.25408.2109 | CLOVIS 2109 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 1,587.000 | 1,586.000 | 08J | 2013 | 07/23/2016 | 2016 | 1150 | 164.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | R2 CLOVIS 2109 WIREDWN RCONDUCTR 2015 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-08-31 | 2015-08-31 | COMP | 2015-09-02 | 2015-09-02 | COMP | 2015-09-02 | 2015-09-02 | COMP | 2015-09-02 | 2015-09-09 | COMP | 2015-09-09 | 2016-04-22 | COMP | 2016-04-22 | 2016-04-22 | 2 | 233 | 108845.74
30999912 | OCGC REPL OH DET WIRE ON PUEBLO 2102 | 05/31/2013 | 106958496 | 05/30/2013 | # | Not assigned | 40 | Closed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 06/30/2014 | ED.04329.2102 | PUEBLO 2102 | 028 | NAPA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 1,775.000 | 1,800.000 | 08J | 2013 | 08/27/2016 | 2016 | 1184 | 169.1429 | CLSD | 12 | E070 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30999912_R4 REPL OH DET WIRE ON PUEBLO | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-01-27 | 2016-01-27 | COMP | 2016-02-01 | 2016-02-01 | COMP | 2016-02-01 | 2016-02-01 | COMP | 2016-02-01 | 2016-04-14 | COMP | 2016-04-14 | 2016-07-11 | COMP | 2016-07-11 | 2016-08-08 | 5 | 189 | 153706.38
31000000 | OC4 BLUE LAKE 1102 DETERIORATED CONDUCTO | 05/31/2013 | 106941452 | 05/16/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/01/2014 | ED.19218.1102.SWIT | SWITCHES | 012 | HUMBOLDT COUNT | 5535457 | DO 08 - Monthly Forecast Only | 2,905.000 | 2,905.000 | 08J | 2013 | 06/16/2018 | 2018 | 1842 | 263.1429 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31000000_BLUE LAKE 1102 DETERIORATED CON | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2014-08-07 | 2014-08-07 | COMP | 2014-08-14 | 2014-12-31 | COMP | 2014-08-18 | 2014-09-03 | COMP | 2014-09-03 | 2014-10-06 | COMP | 2014-10-06 | 2014-10-18 | COMP | 2014-10-18 | 2014-10-18 | 27 | 45 | 526402.42
31000316 | MALAGA 1104 FUSE INSTALL - POST ESTIMATE | 06/03/2013 | 106951602 | 05/24/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/27/2013 | ED.25425.1104 | MALAGA 1104 | 010 | FRESNO COUNTY | 5517127 | DO 08 - Monthly Forecast Only | 1.000 | 0.000 | 08J | 2013 | 02/16/2019 | 2019 | 2084 | 297.7143 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2019-02-16 | 2019-02-16 | # | 2019-02-16 | 2019-02-16 | # | 2019-02-16 | 2019-02-16 | # | 2019-02-16 | 2019-02-16 | # | 2019-02-16 | 2019-02-16 | # | 2019-02-16 | 2019-02-16 | 0 | 0 | 0
31000689 | OCGC UON 1101 - RECOND 453FT WIRE DOWN | 06/04/2013 | 106912356 | 05/01/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/28/2013 | ED.16-X280000000 | CHICO MAP X28 | 004 | BUTTE COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 891.000 | 900.000 | 08J | 2013 | 03/19/2016 | 2016 | 1019 | 145.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-09-03 | 2015-09-03 | COMP | 2015-09-08 | 2015-09-08 | COMP | 2015-09-09 | 2015-09-09 | COMP | 2015-09-09 | 2016-02-18 | COMP | 2016-02-18 | 2016-02-18 | COMP | 2016-02-18 | 2016-02-24 | 6 | 168 | 39933.16
31001158 | OCGCTYLER 1104-SACRAMENTO AVE RECON 610' | 06/07/2013 | 106966972 | 06/06/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/31/2014 | ED.85-Y330000000 | TEHEMA MAP Y33 | 052 | TEHAMA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 575.000 | 575.000 | 08J | 2013 | 05/16/2015 | 2015 | 708 | 101.1429 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-02-03 | 2015-02-03 | COMP | 2015-02-26 | 2015-02-26 | COMP | 2015-02-26 | 2015-02-26 | COMP | 2015-02-26 | 2015-03-03 | COMP | 2015-03-03 | 2015-04-08 | COMP | 2015-04-08 | 2015-04-08 | 23 | 41 | 29720.54
31001407 | MNLO 404_INST 2 C/O_RECND 300' W/TW | 06/08/2013 | 106968706 | 06/07/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 02/13/2014 | ED.02409.0404.SWIT | SWITCHES | 041 | SAN MATEO COUN | 5505513 | PN-OH ANNEALED/DETER CNDCTR: PM MGD | 320.000 | 320.000 | 08J | 2013 | 03/19/2016 | 2016 | 1015 | 145 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-09-02 | 2015-09-02 | COMP | 2015-09-15 | 2015-09-15 | COMP | 2015-09-15 | 2015-09-15 | COMP | 2015-09-15 | 2016-01-29 | COMP | 2016-01-29 | 2016-01-29 | COMP | 2016-01-29 | 2016-02-22 | 13 | 160 | 52550.86
31001492 | OC4 OCLH PLEASANTON RECONDUCTOR 2700' WI | 06/08/2013 | 106967955 | 06/07/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/07/2014 | ED.01450.2107.TXFR.TROH | OVERHEAD TRANSFORMERS | 001 | ALAMEDA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 1,073.000 | 5,000.000 | 08W | 2013 | 03/19/2016 | 2016 | 1015 | 145 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | R1 RECONDUCTOR 2700' WIRE, PLEASANTON | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2014-09-24 | 2014-09-24 | COMP | 2014-12-12 | 2014-12-20 | COMP | 2014-12-20 | 2015-01-14 | COMP | 2015-01-14 | 2015-01-15 | COMP | 2015-01-15 | 2015-01-29 | COMP | 2015-01-29 | 2015-01-29 | 112 | 15 | 110497.65
31001894 | OCGC XFAIRVIEW RD REPL DETERIORATED COND | 06/10/2013 | 106976905 | 06/10/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/20/2014 | ED.18249.2104 | HOLLISTER 2104 | 035 | SAN BENITO COU | 5535457 | DO 08 - Monthly Forecast Only | 1,120.000 | 1,120.000 | 08J | 2013 | 12/26/2015 | 2015 | 929 | 132.7143 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-02-24 | 2015-02-24 | COMP | 2015-03-02 | 2015-03-02 | COMP | 2015-03-02 | 2015-03-02 | COMP | 2015-03-02 | 2015-03-10 | COMP | 2015-03-10 | 2015-04-01 | COMP | 2015-04-01 | 2015-04-02 | 6 | 31 | 86426.91
31002081 | OCGC COTTONWOOD 1101-HICKORY 1280' Y2015 | 06/11/2013 | 106978015 | 06/10/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/01/2014 | ED.87-S322300000 | SHASTA MAP S3223 | 045 | SHASTA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 1,314.000 | 1,314.000 | 08J | 2013 | 04/23/2016 | 2016 | 1047 | 149.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31002081_R6 REPLACE DAMAGED CONDUCTOR, H | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-07-15 | 2015-07-15 | COMP | 2015-07-27 | 2015-07-27 | COMP | 2015-07-27 | 2015-07-27 | COMP | 2015-07-27 | 2015-09-10 | COMP | 2015-09-10 | 2016-03-18 | COMP | 2016-03-18 | 2016-03-21 | 12 | 238 | 288986.85
31002333 | MIDWAY 1104- INSTALL FUSE | 06/12/2013 | 106980179 | 06/12/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 01/31/2014 | ED.25261.1104.SWIT | SWITCHES | 015 | KERN COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 160.000 | 0.000 | 08W | 2013 | 02/14/2015 | 2015 | 612 | 87.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2014-08-07 | 2014-08-28 | COMP | 2014-08-07 | 2014-09-04 | COMP | 2014-09-15 | 2014-09-15 | COMP | 2014-09-15 | 2014-10-15 | COMP | 2014-10-15 | 2014-11-25 | COMP | 2014-11-25 | 2014-11-25 | 39 | 71 | 22883.34
31005551 | OCCCREPL OH DET WIRE ON NAPA+ 1105 | 06/27/2013 | 106996961 | 06/26/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/30/2014 | ED.04202.1105 | NAPA 1105 | 028 | NAPA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 120.000 | 120.000 | 08J | 2013 | 12/17/2016 | 2016 | 1269 | 181.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-08-17 | 2016-08-17 | COMP | 2016-08-17 | 2016-09-01 | COMP | 2016-09-01 | 2016-09-01 | COMP | 2016-09-01 | 2016-09-10 | COMP | 2016-09-10 | 2016-12-02 | COMP | 2016-12-02 | 2016-12-02 | 15 | 92 | 55410.2
31005585 | OCGC XDEL MONTE 1101 WIREDOWN MINGO | 06/27/2013 | 106996988 | 06/26/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/29/2013 | ED.18222.1101 | DEL MONTE 1101 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 500.000 | 595.000 | 08J | 2013 | 10/17/2015 | 2015 | 842 | 120.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2014-10-15 | 2014-10-15 | COMP | 2014-11-22 | 2014-11-22 | COMP | 2014-11-22 | 2014-11-22 | COMP | 2014-11-22 | 2014-12-03 | COMP | 2014-12-03 | 2014-12-10 | COMP | 2014-12-10 | 2014-12-17 | 38 | 25 | 78581.7
31006463 | OCLHXRECOND BV1102-HARKINS RD@BURTON AVE | 07/01/2013 | 107007958 | 07/01/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 05/02/2014 | ED.18226.1102 | BUENA VISTA 1102 | 027 | MONTEREY COUNT | 5532479 | CWSP 08W - Monthly Forecast Only | 884.000 | 0.000 | 08W | 2013 | 02/14/2015 | 2015 | 593 | 84.7143 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2014-09-25 | 2014-10-18 | COMP | 2014-09-25 | 2014-10-22 | COMP | 2014-10-22 | 2014-10-22 | COMP | 2014-10-22 | 2014-10-25 | COMP | 2014-10-25 | 2014-11-13 | COMP | 2014-11-13 | 2014-11-18 | 27 | 27 | 42038.75
31006807 | 2015 CALIF 1113 RECONDUCTOR WIREDOWN | 07/05/2013 | 107011084 | 07/03/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/27/2015 | ED.25228.1113 | CALIFORNIA AVE 1113 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 1,262.000 | 1,078.000 | 08J | 2013 | 04/30/2016 | 2016 | 1030 | 147.1429 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31006807_R2 CALIF 1113 RECONDUCTORING - | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-08-26 | 2015-08-26 | COMP | 2015-08-28 | 2015-09-04 | COMP | 2015-09-04 | 2015-09-04 | COMP | 2015-09-04 | 2016-04-10 | COMP | 2016-04-10 | 2016-04-18 | COMP | 2016-04-18 | 2016-04-18 | 9 | 227 | 131563.85
31008212 | OC4 RECON 1/0A W/397A MERRIL ST-BV 1103- | 07/12/2013 | 107015037 | 07/09/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/26/2014 | ED.18226.1103 | BUENA VISTA 1103 | 027 | MONTEREY COUNT | 5532479 | CWSP 08W - Monthly Forecast Only | 1,415.000 | 0.000 | 08W | 2013 | 10/17/2015 | 2015 | 827 | 118.1429 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2014-08-07 | 2014-08-28 | COMP | 2014-08-07 | 2014-10-13 | COMP | 2014-10-16 | 2014-10-31 | COMP | 2014-10-31 | 2014-11-14 | COMP | 2014-11-14 | 2014-11-15 | COMP | 2014-11-15 | 2014-11-15 | 85 | 15 | 104619.44
31008213 | XBUENA VISTA 1103 NUTTING 4AR | 07/12/2013 | 107014901 | 07/09/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 07/11/2014 | ED.18226.1103 | BUENA VISTA 1103 | 027 | MONTEREY COUNT | 5532479 | CWSP 08W - Monthly Forecast Only | 760.000 | 0.000 | 08W | 2013 | 10/17/2015 | 2015 | 827 | 118.1429 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2014-08-20 | 2014-08-20 | COMP | 2014-11-19 | 2014-11-19 | COMP | 2014-11-19 | 2014-11-19 | COMP | 2014-11-19 | 2014-11-21 | COMP | 2014-11-21 | 2014-12-15 | COMP | 2014-12-15 | 2014-12-19 | 91 | 30 | 51120.53
31009147 | OC4 E COTTLE 1703 RECOND 6,250FT 6CU W/ | 07/17/2013 | 107029479 | 07/16/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/20/2014 | ED.16371.1703 | COTTLE 1703 | 050 | STANISLAUS COU | 5535457 | DO 08 - Monthly Forecast Only | 6,855.000 | 6,567.000 | 08J | 2013 | 10/15/2016 | 2016 | 1186 | 169.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31009147_R4E COTTLE 1703 RECOND. 6,250FT | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2014-10-23 | 2014-10-23 | COMP | 2014-12-01 | 2014-12-01 | COMP | 2014-12-15 | 2015-01-08 | COMP | 2016-01-25 | 2016-10-05 | COMP | 2016-10-05 | 2016-10-06 | COMP | 2016-10-06 | 2016-10-07 | 77 | 638 | 635963.69
31009249 | RPL 800' OH CONDUCTOR GREENBRAE 1101 | 07/18/2013 | 107031442 | 07/17/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 01/13/2014 | ED.04226.1101.COND | CONDUCTOR | 021 | MARIN COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 765.000 | 765.000 | 08W | 2013 | 09/23/2017 | 2017 | 1528 | 218.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | R4 RPL 800' OH CONDUCTOR GREENBRAE 1101 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-11-12 | 2015-10-24 | COMP | 2015-11-12 | 2015-11-12 | COMP | 2015-11-12 | 2015-11-12 | COMP | 2015-11-12 | 2016-04-15 | COMP | 2016-04-15 | 2016-05-25 | COMP | 2016-05-25 | 2016-06-01 | 0 | 202 | 157965.13
31009299 | OCGCVE SPLICES FROM LINE _HWY 1103 | 07/18/2013 | 107030584 | 07/17/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2013 | ED.04265.1103 | HIGHWAY 1103 | 048 | SOLANO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 295.000 | 295.000 | 08J | 2013 | 06/25/2016 | 2016 | 1073 | 153.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-09-25 | 2015-09-25 | COMP | 2015-10-13 | 2015-10-13 | COMP | 2015-11-16 | 2015-11-16 | COMP | 2015-11-16 | 2016-04-13 | COMP | 2016-04-13 | 2016-05-03 | COMP | 2016-05-03 | 2016-05-09 | 52 | 175 | 42983.94
31009551 | OCCC HMB1103 CO9067 RECONDUCTOR OH LINE | 07/19/2013 | 107033849 | 07/19/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 05/23/2014 | ED.02410.1103.TXFR.TROH | OVERHEAD TRANSFORMERS | 041 | SAN MATEO COUN | 5505513 | PN-OH ANNEALED/DETER CNDCTR: PM MGD | 230.000 | 230.000 | 08J | 2013 | 01/28/2018 | 2018 | 1654 | 236.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-07-07 | 2015-07-07 | COMP | 2015-07-09 | 2015-07-13 | COMP | 2015-07-13 | 2015-07-13 | COMP | 2015-07-13 | 2015-07-22 | COMP | 2015-07-22 | 2015-07-22 | COMP | 2015-07-22 | 2015-07-27 | 6 | 14 | 39973.21
31009552 | _BER 404_REFRAME O.H._INST 2 FUSED CO | 07/19/2013 | 107034010 | 07/19/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 01/22/2015 | ED.02404.0404.TXFR.TROH | OVERHEAD TRANSFORMERS | 041 | SAN MATEO COUN | 5505513 | PN-OH ANNEALED/DETER CNDCTR: PM MGD | 366.000 | 0.000 | 08J | 2013 | 12/17/2016 | 2016 | 1247 | 178.1429 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-05-19 | 2016-06-09 | COMP | 2016-05-19 | 2016-06-14 | COMP | 2016-06-14 | 2016-06-14 | COMP | 2016-06-14 | 2016-06-27 | COMP | 2016-06-27 | 2016-07-08 | COMP | 2016-07-08 | 2016-07-08 | 26 | 24 | 90223.56
31009743 | OC4 OCGC PEACHTON 1101 RECON Y2015 | 07/19/2013 | 107033396 | 07/18/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/01/2015 | ED.13-K150000000 | OROVILLE MAP K15 | 004 | BUTTE COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 10,194.000 | 10,194.000 | 08J | 2013 | 05/12/2018 | 2018 | 1758 | 251.1429 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31009743 PEACHTON 1101 RECOND. 8000FT_8J | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-06-23 | 2015-06-23 | COMP | 2015-06-25 | 2015-07-30 | COMP | 2015-08-05 | 2015-08-05 | COMP | 2015-08-05 | 2016-01-28 | COMP | 2016-01-28 | 2016-01-28 | COMP | 2016-01-28 | 2016-02-02 | 43 | 181 | 687516.35
31010993 | OCGC L1102 OH RECNDUCTORNG-PHASE 1 LA PL | 07/25/2013 | 107037627 | 07/23/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/30/2015 | ED.02226.1102 | SF L 1102 | 038 | SAN FRANCISCO | 5535457 | DO 08 - Monthly Forecast Only | 5,631.000 | 5,631.000 | 08J | 2013 | 01/26/2019 | 2019 | 2011 | 287.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31010993_R2Z L1102 OH RECNDUCTORNG-PHAS | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-03-22 | 2016-03-22 | COMP | 2016-03-24 | 2016-03-24 | COMP | 2016-03-24 | 2016-03-24 | COMP | 2016-03-24 | 2017-07-12 | COMP | 2017-07-12 | 2017-08-02 | COMP | 2017-08-02 | 2017-08-03 | 2 | 497 | 734090.44
31011322 | +FOOTHILL 1101 (LOS OSOS - LOVR) | 07/27/2013 | 107048066 | 07/25/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/31/2015 | ED.18295.1101 | FOOTHILL 1101 | 040 | SAN LUIS OBISP | 5535457 | DO 08 - Monthly Forecast Only | 1,494.000 | 1,495.000 | 08J | 2013 | 08/20/2016 | 2016 | 1120 | 160 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31011322_R5 FH 1101 WD 13-44425 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-02-23 | 2016-02-23 | COMP | 2016-03-17 | 2016-03-17 | COMP | 2016-03-17 | 2016-03-17 | COMP | 2016-03-17 | 2016-04-13 | COMP | 2016-04-13 | 2016-08-08 | COMP | 2016-08-08 | 2016-08-08 | 23 | 144 | 107235.03
31011323 | CAYUCOS 1101 (VILLA CREEK) | 07/27/2013 | 107048149 | 07/25/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/30/2014 | ED.18255.1101 | CAYUCOS 1101 | 040 | SAN LUIS OBISP | 5535457 | DO 08 - Monthly Forecast Only | 695.000 | 714.000 | 08J | 2013 | 08/27/2016 | 2016 | 1127 | 161 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-01-14 | 2016-01-14 | COMP | 2016-02-03 | 2016-02-04 | COMP | 2016-02-04 | 2016-02-04 | COMP | 2016-02-04 | 2016-05-04 | COMP | 2016-05-04 | 2016-07-04 | COMP | 2016-07-04 | 2016-07-06 | 21 | 153 | 36022.5
31011324 | OCGC XREPL DETERIORTD COND SMITH RD WAT | 07/27/2013 | 107049726 | 07/26/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/27/2015 | ED.08319.2101 | GREEN VALLEY 2101 | 044 | SANTA CRUZ COU | 5532479 | CWSP 08W - Monthly Forecast Only | 1,870.000 | 1,870.000 | 08W | 2013 | 09/12/2015 | 2015 | 777 | 111 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2014-11-10 | 2015-01-13 | COMP | 2014-11-10 | 2015-02-13 | COMP | 2015-02-13 | 2015-02-13 | COMP | 2015-02-13 | 2015-02-18 | COMP | 2015-02-18 | 2015-04-02 | COMP | 2015-04-02 | 2015-04-02 | 95 | 48 | 62531.45
31013663 | OCGC LOS COCHES 1102 REPL COND LR 75272 | 08/08/2013 | 107068674 | 08/08/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/03/2015 | ED.18215.1102 | LOS COCHES 1102 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 2,004.000 | 2,004.000 | 08J | 2013 | 07/23/2016 | 2016 | 1080 | 154.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-10-12 | 2015-10-12 | COMP | 2015-10-26 | 2015-10-26 | COMP | 2015-10-26 | 2015-10-26 | COMP | 2015-10-26 | 2016-04-14 | COMP | 2016-04-14 | 2016-05-26 | COMP | 2016-05-26 | 2016-05-26 | 14 | 213 | 177172.94
31013665 | OCGC XLOS COCHES 1102 REPL COND NR 7207 | 08/08/2013 | 107068676 | 08/08/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/03/2015 | ED.18215.1102 | LOS COCHES 1102 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 1,888.000 | 3,200.000 | 08J | 2013 | 05/14/2016 | 2016 | 1010 | 144.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-07-15 | 2015-08-31 | COMP | 2015-07-15 | 2015-09-02 | COMP | 2015-09-02 | 2015-09-02 | COMP | 2015-09-02 | 2016-04-13 | COMP | 2016-04-13 | 2016-04-20 | COMP | 2016-04-20 | 2016-04-21 | 49 | 232 | 150513.09
31014122 | OCLH REPL OH COND/REMOVE BUMPS_ BAH1102 | 08/12/2013 | 107068067 | 08/07/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2013 | ED.04325.1102 | BAHIA 1102 | 048 | SOLANO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 461.000 | 460.000 | 08J | 2013 | 07/23/2016 | 2016 | 1076 | 153.7143 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-05-04 | 2015-05-04 | COMP | 2015-05-06 | 2015-05-06 | COMP | 2015-05-06 | 2015-05-06 | COMP | 2015-05-06 | 2015-05-16 | COMP | 2015-05-16 | 2015-07-01 | COMP | 2015-07-01 | 2015-07-03 | 2 | 58 | 25278
31014511 | OCLH GUERNSEY 1104 ONE SPAN RECON | 08/14/2013 | 107080669 | 08/13/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/27/2015 | ED.25371.1102 | HARDWICK 1102 | 016 | KINGS COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 601.000 | 601.000 | 08J | 2013 | 10/31/2015 | 2015 | 808 | 115.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-05-04 | 2015-06-24 | COMP | 2015-05-04 | 2015-06-25 | COMP | 2015-06-25 | 2015-06-25 | COMP | 2015-06-25 | 2015-09-10 | COMP | 2015-09-10 | 2015-09-18 | COMP | 2015-09-18 | 2015-09-24 | 52 | 91 | 26219.79
31014512 | OCGC MORMON 1101 08J RECONDUCTORING | 08/14/2013 | 107081027 | 08/13/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2014 | ED.16321.1101 | MORMON 1101 | 039 | SAN JOAQUIN CO | 5535457 | DO 08 - Monthly Forecast Only | 7,680.000 | 7,680.000 | 08J | 2013 | 09/17/2016 | 2016 | 1130 | 161.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31014512_R4 MORMON 1101 08J RECONDUCTORI | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-04-18 | 2016-04-18 | COMP | 2016-04-21 | 2016-04-21 | COMP | 2016-05-05 | 2016-05-05 | COMP | 2016-05-05 | 2016-06-03 | COMP | 2016-06-03 | 2016-08-23 | COMP | 2016-08-23 | 2016-08-26 | 17 | 113 | 228771.31
31014552 | OC4 OCGC RICE 1101 RECONDUCTOR - Y2015 | 08/13/2013 | 107081094 | 08/13/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2015 | ED.06283.1101.RECL | RECLOSERS | 006 | COLUSA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 2,955.000 | 2,900.000 | 08J | 2013 | 04/23/2016 | 2016 | 984 | 140.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31014552_RICE 1101 RECOND. WIRE DOWN_08J | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-05-26 | 2015-05-26 | COMP | 2015-06-12 | 2015-06-12 | COMP | 2015-06-17 | 2015-06-17 | COMP | 2015-06-17 | 2015-06-22 | COMP | 2015-06-22 | 2016-02-12 | COMP | 2016-02-12 | 2016-02-12 | 22 | 240 | 170301.46
31015447 | OC4 OCGC 2015 CRESSEY 2103 RECONDUCTOR | 08/16/2013 | 107084143 | 08/15/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/30/2014 | ED.25470.2103 | CRESSEY 2103 | 024 | MERCED COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 6,862.000 | 6,862.000 | 08J | 2013 | 08/19/2017 | 2017 | 1464 | 209.1429 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | CRESEY 2103-RECN 7000' OF #4CU/W 4/OAL | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-11-12 | 2015-11-20 | COMP | 2015-11-12 | 2015-12-02 | COMP | 2015-12-08 | 2015-12-08 | COMP | 2015-12-08 | 2015-12-16 | COMP | 2015-12-16 | 2016-07-19 | COMP | 2016-07-19 | 2016-08-16 | 26 | 252 | 268834.29
31015448 | OC4 OCGC CABLE REPLACEMENT -H1109- PHASE | 08/16/2013 | 107084179 | 08/15/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/30/2014 | ED.25280.1114 | MERCED 1114 | 024 | MERCED COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 6,262.000 | 6,262.000 | 08J | 2013 | 06/25/2016 | 2016 | 1044 | 149.1429 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31015448_R4MERCED 1114-RECON 6,000' 6CU | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-10-26 | 2015-10-26 | COMP | 2015-11-02 | 2015-11-02 | COMP | 2015-11-02 | 2015-11-02 | COMP | 2015-11-02 | 2015-11-24 | COMP | 2015-11-24 | 2016-06-06 | COMP | 2016-06-06 | 2016-06-09 | 7 | 220 | 233951.71
31015449 | +FOOTHILL 1101 RECONDUCTOR SLO | 08/16/2013 | 107083621 | 08/15/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/30/2015 | ED.18295.1101 | FOOTHILL 1101 | 040 | SAN LUIS OBISP | 5535457 | DO 08 - Monthly Forecast Only | 1,475.000 | 0.000 | 08J | 2013 | 03/19/2016 | 2016 | 946 | 135.1429 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31015449_R5 FOOTHILL 1101 RECONDUCTOR SL | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-06-23 | 2015-08-06 | COMP | 2015-06-23 | 2015-08-12 | COMP | 2015-08-12 | 2015-08-12 | COMP | 2015-08-12 | 2015-10-22 | COMP | 2015-10-22 | 2016-02-12 | COMP | 2016-02-12 | 2016-02-17 | 50 | 189 | 112505.12
31016170 | OCGC XRECONDUCTORING PRI @ IVERSON RD | 08/21/2013 | 107087278 | 08/19/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 01/16/2015 | ED.18213.1101 | GONZALES 1101 | 027 | MONTEREY COUNT | 5532479 | CWSP 08W - Monthly Forecast Only | 2,233.000 | 2,233.000 | 08W | 2013 | 08/27/2016 | 2016 | 1102 | 157.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2014-11-20 | 2015-01-28 | COMP | 2014-11-20 | 2015-02-13 | COMP | 2015-02-13 | 2015-02-13 | COMP | 2015-03-06 | 2016-06-22 | COMP | 2016-06-22 | 2016-07-05 | COMP | 2016-07-05 | 2016-07-11 | 85 | 514 | 140678.69
31016336 | OCGC WOODLAND 1112 RECONDUCTOR 2AR | 08/21/2013 | 107091065 | 08/21/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2014 | ED.50-J172200000.STRU.POLE | YOLO J1722 POLES | 057 | YOLO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 1,244.000 | 1,260.000 | 08J | 2013 | 07/23/2016 | 2016 | 1067 | 152.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-11-04 | 2015-11-04 | COMP | 2015-11-16 | 2015-11-17 | COMP | 2015-11-17 | 2015-11-17 | COMP | 2015-11-17 | 2016-04-12 | COMP | 2016-04-12 | 2016-06-01 | COMP | 2016-06-01 | 2016-06-03 | 13 | 199 | 40400
31016636 | OC4 OCGC CORRAL 1101 RELOCAT 4ACSR (WIR | 08/23/2013 | 107092244 | 08/22/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/26/2014 | ED.16299.1101 | CORRAL 1101 | 039 | SAN JOAQUIN CO | 5532479 | CWSP 08W - Monthly Forecast Only | 4,330.000 | 4,330.000 | 08W | 2013 | 08/20/2016 | 2016 | 1093 | 156.1429 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | R2ZE CORRAL 1101 RELOCAT 4ACSR (WIREDOWN | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-12-09 | 2015-12-09 | COMP | 2016-01-20 | 2016-01-20 | COMP | 2016-01-25 | 2016-01-25 | COMP | 2016-01-25 | 2016-04-12 | COMP | 2016-04-12 | 2016-07-19 | COMP | 2016-07-19 | 2016-07-19 | 47 | 176 | 163783.65
31017164 | RECOND 4 SPANS OF #6CU-R1123-HARBOUR | 08/26/2013 | 107100865 | 08/26/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/01/2015 | ED.01347.1123 | RICHMOND R 1123 | 007 | CONTRA COSTA C | 5535457 | DO 08 - Monthly Forecast Only | 118.000 | 400.000 | 08J | 2013 | 01/26/2019 | 2019 | 1979 | 282.7143 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2017-10-11 | 2017-10-28 | COMP | 2017-10-04 | 2017-11-14 | COMP | 2017-11-14 | 2017-11-14 | COMP | 2017-11-14 | 2017-11-15 | COMP | 2017-11-15 | 2017-11-30 | COMP | 2017-11-30 | 2017-12-01 | 34 | 17 | 62385.13
31017530 | OCGC TEVIS 2102 3 SPANS RECONDUCTOR | 08/27/2013 | 107103871 | 08/27/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/27/2015 | ED.25532.2102.TXFR.TROH | OVERHEAD TRANSFORMERS | 015 | KERN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 1,179.000 | 1,179.000 | 08J | 2013 | 01/23/2016 | 2016 | 879 | 125.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | TEVIS 2102 3 SPANS RECONDUCTOR | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-04-11 | 2015-05-26 | COMP | 2015-04-11 | 2015-05-28 | COMP | 2015-05-28 | 2015-05-28 | COMP | 2015-05-28 | 2015-08-19 | COMP | 2015-08-19 | 2015-08-19 | COMP | 2015-08-19 | 2015-08-19 | 47 | 83 | 63984.14
31017531 | OC4 OCGC KERN POWER 2103 4 SPANS RECONDU | 08/27/2013 | 107103874 | 08/27/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/27/2015 | ED.25526.2103.TXFR.TROH | OVERHEAD TRANSFORMERS | 015 | KERN COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 746.000 | 0.000 | 08W | 2013 | 05/16/2015 | 2015 | 627 | 89.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2014-11-22 | 2015-01-05 | COMP | 2014-11-22 | 2015-01-21 | COMP | 2015-01-26 | 2015-02-03 | COMP | 2015-02-03 | 2015-02-12 | COMP | 2015-02-12 | 2015-04-08 | COMP | 2015-04-08 | 2015-04-10 | 73 | 66 | 38670.81
31017690 | +R SISQUOC 1102 PH 1 RECON GAREY/TAP) | 08/28/2013 | 107101569 | 08/26/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2013 | ED.18281.1102 | SISQUOC 1102 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 1,406.000 | 1,406.000 | 08J | 2013 | 12/17/2016 | 2016 | 1207 | 172.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31017690_R5 WD SISQUOC 1102 PHASE 1 RECO | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-08-27 | 2016-02-11 | COMP | 2015-08-27 | 2016-03-02 | COMP | 2016-03-02 | 2016-03-02 | COMP | 2016-03-02 | 2016-04-11 | COMP | 2016-04-11 | 2016-08-01 | COMP | 2016-08-01 | 2016-08-03 | 188 | 154 | 101434.21
31017691 | +SISQUOC 1102 PH 2 RECON (POND/MAINLINE) | 08/28/2013 | 107101579 | 08/26/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/30/2014 | ED.18281.1102 | SISQUOC 1102 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 1,727.000 | 1,727.000 | 08J | 2013 | 08/13/2016 | 2016 | 1081 | 154.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31017691_R5 WD SISQUOC 1102 PHASE 2 RECO | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-08-17 | 2016-02-11 | COMP | 2015-08-17 | 2016-03-02 | COMP | 2016-03-02 | 2016-03-02 | COMP | 2016-03-02 | 2016-04-11 | COMP | 2016-04-11 | 2016-08-02 | COMP | 2016-08-02 | 2016-08-03 | 198 | 154 | 96301.79
31017692 | *CANC* WD SISQUOC 1102 PHASE 3A RE*CANC | 08/28/2013 | 107101631 | 08/26/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2014 | ED.18281.1102 | SISQUOC 1102 | 042 | SANTA BARBARA | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 2013 | 01/05/2015 | 2015 | 495 | 70.7143 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2015-01-05 | 2015-01-05 | # | 2015-01-05 | 2015-01-05 | # | 2015-01-05 | 2015-01-05 | # | 2015-01-05 | 2015-01-05 | # | 2015-01-05 | 2015-01-05 | # | 2015-01-05 | 2015-01-05 | 0 | 0 | 0
31017693 | *CANC* WD SISQUOC 1102 PHASE 3B RE*CANC | 08/28/2013 | 107101633 | 08/26/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2014 | ED.18281.1102 | SISQUOC 1102 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2013 | 01/05/2015 | 2015 | 495 | 70.7143 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2015-01-05 | 2015-01-05 | # | 2015-01-05 | 2015-01-05 | # | 2015-01-05 | 2015-01-05 | # | 2015-01-05 | 2015-01-05 | # | 2015-01-05 | 2015-01-05 | # | 2015-01-05 | 2015-01-05 | 0 | 0 | 0
31017867 | *CANC* WD SISQUOC 1102 PHASE 4 REC*CANC | 08/29/2013 | 107101635 | 08/26/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2014 | ED.18281.1102 | SISQUOC 1102 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2013 | 01/05/2015 | 2015 | 494 | 70.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2015-01-05 | 2015-01-05 | # | 2015-01-05 | 2015-01-05 | # | 2015-01-05 | 2015-01-05 | # | 2015-01-05 | 2015-01-05 | # | 2015-01-05 | 2015-01-05 | # | 2015-01-05 | 2015-01-05 | 0 | 0 | 0
31017905 | OCGC RPLOH COND / REMOVE BUMPS_ BAH1102 | 08/29/2013 | 107105779 | 08/28/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/31/2015 | ED.04325.1102 | BAHIA 1102 | 048 | SOLANO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 1,018.000 | 1,018.000 | 08J | 2013 | 11/19/2016 | 2016 | 1178 | 168.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-06-03 | 2016-06-03 | COMP | 2016-06-06 | 2016-06-06 | COMP | 2016-06-06 | 2016-06-06 | COMP | 2016-06-06 | 2016-07-29 | COMP | 2016-07-29 | 2016-10-14 | COMP | 2016-10-14 | 2016-10-14 | 3 | 130 | 49146.43
31018158 | OCGC BELL 10-RECOND 3 SPANS PAST SW34443 | 08/30/2013 | 107107504 | 08/29/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/27/2014 | ED.15270.1110.SWIT | SWITCHES | 031 | PLACER COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 835.000 | 835.000 | 08J | 2013 | 08/22/2015 | 2015 | 722 | 103.1429 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-04-27 | 2015-05-01 | COMP | 2015-04-27 | 2015-06-03 | COMP | 2015-06-03 | 2015-06-03 | COMP | 2015-06-03 | 2015-06-16 | COMP | 2015-06-16 | 2015-07-22 | COMP | 2015-07-22 | 2015-07-23 | 37 | 50 | 37047.26
31018225 | OC4 OCGC MESA 1103 WD - MESA & VIVA | 08/30/2013 | 107107619 | 08/30/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 05/01/2015 | ED.18282.1103 | MESA 1103 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 3,564.000 | 3,564.000 | 08J | 2013 | 06/18/2016 | 2016 | 1023 | 146.1429 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | R5 MESA 1103 WD 13-54316 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-04-16 | 2015-06-17 | COMP | 2015-04-16 | 2015-06-29 | COMP | 2015-06-29 | 2015-07-02 | COMP | 2015-07-02 | 2015-09-08 | COMP | 2015-09-08 | 2016-01-26 | COMP | 2016-01-26 | 2016-01-29 | 77 | 211 | 216765.78
31018226 | OCGC X HAMMER 1106 REPLACE 390 FT OF | 08/30/2013 | 107108005 | 08/30/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/26/2015 | ED.16330.1106 | HAMMER 1106 | 039 | SAN JOAQUIN CO | 5535457 | DO 08 - Monthly Forecast Only | 383.000 | 390.000 | 08J | 2013 | 06/16/2018 | 2018 | 1751 | 250.1429 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-07-20 | 2016-07-19 | COMP | 2016-07-20 | 2016-07-20 | COMP | 2016-07-20 | 2016-07-20 | COMP | 2016-07-20 | 2016-08-25 | COMP | 2016-08-25 | 2016-11-19 | COMP | 2016-11-19 | 2016-11-22 | 0 | 125 | 54432.84
31018911 | OC4 OCGCEB_RELIABILITY C-1114_INSTALL LR | 09/06/2013 | 107118566 | 09/05/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/01/2015 | ED.01201.1114 | OAKLAND C 1114 | 001 | ALAMEDA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 1,282.000 | 1,282.000 | 08J | 2013 | 11/07/2015 | 2015 | 792 | 113.1429 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31018911_EB_RELIABILITY C-1114_INSTALL L | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-01-29 | 2015-04-29 | COMP | 2015-01-29 | 2015-05-05 | COMP | 2015-05-15 | 2015-05-15 | COMP | 2015-05-15 | 2015-07-19 | COMP | 2015-07-19 | 2015-07-19 | COMP | 2015-07-19 | 2015-07-19 | 106 | 65 | 306786.81
31019103 | FREMONT 1108 CKT - OH RECONDUCTORING | 09/04/2013 | 107115948 | 09/04/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/31/2014 | ED.01435.1108 | FREMONT 1108 | 001 | ALAMEDA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 1,326.000 | 1,020.000 | 08J | 2013 | 09/24/2016 | 2016 | 1116 | 159.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-03-30 | 2016-03-30 | COMP | 2016-04-05 | 2016-04-05 | COMP | 2016-04-05 | 2016-04-05 | COMP | 2016-04-05 | 2016-04-14 | COMP | 2016-04-14 | 2016-07-26 | COMP | 2016-07-26 | 2016-09-01 | 6 | 149 | 159463.52
31019262 | +DIVIDE 1103 PH4 (GREKA/LONG SPAN) | 09/05/2013 | 107117151 | 09/04/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/01/2014 | ED.18257.1103 | DIVIDE 1103 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 2,079.000 | 2,079.000 | 08J | 2013 | 11/19/2016 | 2016 | 1171 | 167.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31019262_R5 WD DIVIDE 1103 RECONDUCTOR A | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-04-14 | 2016-05-31 | COMP | 2016-04-14 | 2016-06-08 | COMP | 2016-06-08 | 2016-06-08 | COMP | 2016-06-08 | 2016-07-27 | COMP | 2016-07-27 | 2016-10-28 | COMP | 2016-10-28 | 2016-10-31 | 55 | 145 | 64484.6
31019263 | OCGC DE 1103 PH2 RECON (GREKA/UNDERBUILD | 09/05/2013 | 107117152 | 09/04/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/01/2014 | ED.18257.1103 | DIVIDE 1103 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 2,800.000 | 0.000 | 08J | 2013 | 05/14/2016 | 2016 | 982 | 140.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31019263_R2 WD DIVIDE 1103 PH2 RECONDUCT | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-05-20 | 2015-07-16 | COMP | 2015-05-20 | 2015-07-27 | COMP | 2015-07-27 | 2015-07-27 | COMP | 2015-07-27 | 2016-04-22 | COMP | 2016-04-22 | 2016-04-25 | COMP | 2016-04-25 | 2016-04-25 | 68 | 273 | 121639.64
31019264 | OLCH OCGC+DIVIDE 1103 PH3 (BLACK & NTU) | 09/05/2013 | 107117155 | 09/04/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/01/2014 | ED.18257.1103 | DIVIDE 1103 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 2,116.000 | 2,116.000 | 08J | 2013 | 06/18/2016 | 2016 | 1017 | 145.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31019264_R2 WD DIVIDE 1103 PH3 RECONDUCT | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-08-27 | 2015-10-09 | COMP | 2015-08-27 | 2015-10-14 | COMP | 2015-10-14 | 2015-10-14 | COMP | 2015-10-14 | 2016-04-13 | COMP | 2016-04-13 | 2016-05-12 | COMP | 2016-05-12 | 2016-05-16 | 48 | 215 | 203745.76
31019265 | OCGC 2015 ORO LOMA 1115 RECONDUCTOR | 09/05/2013 | 107117033 | 09/04/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/25/2015 | ED.25537.1108 | ORO LOMA 1108 | 024 | MERCED COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 2,485.000 | 2,485.000 | 08J | 2013 | 04/16/2016 | 2016 | 954 | 136.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31019265_ RECONDUCTOR ORO LOMA 1108 - AN | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-07-02 | 2015-08-18 | COMP | 2015-07-02 | 2015-08-26 | COMP | 2015-08-26 | 2015-08-26 | COMP | 2015-08-26 | 2015-09-08 | COMP | 2015-09-08 | 2016-03-31 | COMP | 2016-03-31 | 2016-04-01 | 55 | 219 | 186038.91
31019298 | OCGC X2102 RE-CNDCTR 1SP 42960 METZ RD. | 09/06/2013 | 107118596 | 09/05/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2015 | ED.18208.2102 | LOS OSITOS 2102 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 377.000 | 377.000 | 08J | 2013 | 09/24/2016 | 2016 | 1114 | 159.1429 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-10-09 | 2015-10-22 | COMP | 2015-10-09 | 2015-10-22 | COMP | 2015-10-22 | 2015-10-22 | COMP | 2015-10-22 | 2016-04-15 | COMP | 2016-04-15 | 2016-09-07 | COMP | 2016-09-07 | 2016-09-07 | 13 | 321 | 21952.61
31019802 | OC4 EP REPLACE DAMAGED CONDUCT , HICKORY | 09/08/2013 | 107120230 | 09/06/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/01/2014 | ED.14-S200000000 | GLENN MAP S20 | 011 | GLENN COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 266.000 | 0.000 | 08W | 2013 | 01/31/2015 | 2015 | 510 | 72.8571 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2014-02-08 | 2014-02-27 | COMP | 2014-02-08 | 2014-03-05 | COMP | 2014-03-11 | 2014-03-18 | COMP | 2014-03-31 | 2014-03-31 | COMP | 2014-03-31 | 2014-04-22 | COMP | 2014-04-22 | 2014-04-28 | 38 | 41 | 17199.1
31020089 | OCGC COALINGA #1106 ANNEALED CND REPL & | 09/10/2013 | 107131640 | 09/10/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/31/2015 | ED.25238.1106 | COALINGA NO 2 1106 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 410.000 | 410.000 | 08J | 2013 | 07/23/2016 | 2016 | 1047 | 149.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-07-29 | 2015-12-03 | COMP | 2015-07-29 | 2015-12-08 | COMP | 2015-12-08 | 2015-12-08 | COMP | 2015-12-08 | 2016-04-15 | COMP | 2016-04-15 | 2016-06-21 | COMP | 2016-06-21 | 2016-06-28 | 132 | 203 | 87738.13
31020123 | OCGC 2015 HARDWICK 1102 RECONDUCTOR AN | 09/10/2013 | 107124961 | 09/09/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/24/2015 | ED.25371.1102 | HARDWICK 1102 | 016 | KINGS COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 5,375.000 | 5,400.000 | 08J | 2013 | 06/18/2016 | 2016 | 1012 | 144.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | HARDWICK 1102 RECONDUCTOR ANNEALED | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-08-17 | 2015-08-17 | COMP | 2015-09-01 | 2015-09-01 | COMP | 2015-09-01 | 2015-09-01 | COMP | 2015-09-01 | 2015-09-09 | COMP | 2015-09-09 | 2016-03-29 | COMP | 2016-03-29 | 2016-03-31 | 15 | 212 | 315463.03
31021152 | OC4 OCGC R2 2014 DINUBA 1105 RECONDUCTOR | 09/13/2013 | 107137513 | 09/12/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 05/05/2014 | ED.25409.1105 | DINUBA 1105 | 054 | TULARE COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 10,577.000 | 11,519.000 | 08W | 2013 | 07/18/2015 | 2015 | 673 | 96.1429 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | R2 2014 DINUBA 1105 RECONDUCTOR | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2014-08-27 | 2014-08-27 | COMP | 2014-08-29 | 2014-09-24 | COMP | 2014-09-24 | 2014-09-24 | COMP | 2014-09-24 | 2014-10-10 | COMP | 2014-10-10 | 2014-12-31 | COMP | 2014-12-31 | 2015-01-13 | 28 | 111 | 1571040.3
31022659 | OCLH RECON 1 SPAN 6C (300') S/O 7876F WD | 09/19/2013 | 107155528 | 09/19/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/04/2014 | ED.25409.1104 | DINUBA 1104 | 054 | TULARE COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 474.000 | 0.000 | 08J | 2013 | 03/19/2016 | 2016 | 912 | 130.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-05-21 | 2015-05-21 | COMP | 2015-06-01 | 2015-06-01 | COMP | 2015-06-01 | 2015-06-01 | COMP | 2015-06-01 | 2015-06-08 | COMP | 2015-06-08 | 2016-02-22 | COMP | 2016-02-22 | 2016-02-23 | 11 | 267 | 38580.58
31024860 | ARCATA 1105 EXCESSIVE SPLICES PHASE 2 | 09/28/2013 | 107165410 | 09/27/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/30/2015 | ED.19202.1105.SWIT | SWITCHES | 012 | HUMBOLDT COUNT | 5535457 | DO 08 - Monthly Forecast Only | 4,567.000 | 4,567.000 | 08J | 2013 | 07/17/2016 | 2016 | 1023 | 146.1429 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31024860_ARCATA 1105 EXCESSIVE SPLICES P | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-11-17 | 2015-11-13 | COMP | 2015-11-17 | 2015-11-17 | COMP | 2015-12-09 | 2015-12-09 | COMP | 2015-12-09 | 2016-04-13 | COMP | 2016-04-13 | 2016-06-08 | COMP | 2016-06-08 | 2016-06-09 | 22 | 183 | 386400.3
31025334 | OC4 OCCC W FRESNO 1101 RECONDUCTOR PH 1 | 10/01/2013 | 107168255 | 10/01/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/20/2015 | ED.25373.1101 | WEST FRESNO 1101 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 6,707.000 | 6,707.000 | 08J | 2013 | 09/19/2015 | 2015 | 718 | 102.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | R2 W FRESNO 1101 RECONDUCTOR - PH 1 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-06-01 | 2015-05-29 | COMP | 2015-06-01 | 2015-06-01 | COMP | 2015-06-01 | 2015-06-08 | COMP | 2015-06-01 | 2015-06-08 | COMP | 2015-06-08 | 2015-08-27 | COMP | 2015-08-27 | 2015-08-31 | 7 | 84 | 306294.72
31025335 | 2016 W FRESNO 1101 RECONDUCTOR PH 2 | 10/01/2013 | 107168258 | 10/01/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/19/2015 | ED.25373.1101 | WEST FRESNO 1101 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 1,718.000 | 1,718.000 | 08J | 2013 | 12/17/2016 | 2016 | 1173 | 167.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | R2 W FRESNO 1101 RECONDUCTORI PH 2 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-05-25 | 2016-05-25 | COMP | 2016-06-13 | 2016-06-13 | COMP | 2016-06-13 | 2016-06-13 | COMP | 2016-06-13 | 2016-07-27 | COMP | 2016-07-27 | 2016-10-17 | COMP | 2016-10-17 | 2016-10-26 | 19 | 135 | 206266.08
31027740 | KERMAN 1106 - RECONDUCTOR & REFRAME | 10/11/2013 | 107186583 | 10/10/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 05/30/2014 | ED.25271.1106 | KERMAN 1106 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 2,258.000 | 7,200.000 | 08J | 2013 | 09/24/2016 | 2016 | 1079 | 154.1429 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-03-31 | 2015-05-01 | COMP | 2015-03-31 | 2015-06-01 | COMP | 2015-06-03 | 2015-06-03 | COMP | 2015-06-03 | 2015-06-17 | COMP | 2015-06-17 | 2015-08-26 | COMP | 2015-08-26 | 2015-08-26 | 64 | 84 | 64785.58
31027748 | 2015 WRIGHT 1109 RECONDUCTOR | 10/11/2013 | 107186814 | 10/10/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/25/2015 | ED.25464.1109 | WRIGHT 1109 | 024 | MERCED COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 3,426.000 | 0.000 | 08J | 2013 | 09/10/2016 | 2016 | 1065 | 152.1429 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | WRIGHT 1109 RECOND 3497' 6CU TO 2AR | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-03-21 | 2016-03-21 | COMP | 2016-03-22 | 2016-03-22 | COMP | 2016-04-05 | 2016-04-05 | COMP | 2016-04-05 | 2016-04-20 | COMP | 2016-04-20 | 2016-08-18 | COMP | 2016-08-18 | 2016-08-22 | 15 | 139 | 168698.54
31027750 | OCLH KERMAN 1106 - RE-CONDUCTOR 1 SPAN | 10/11/2013 | 107147111 | 09/17/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 05/16/2014 | ED.25271.1106 | KERMAN 1106 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 317.000 | 951.000 | 08J | 2013 | 10/31/2015 | 2015 | 750 | 107.1429 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-06-08 | 2015-07-01 | COMP | 2015-06-08 | 2015-07-07 | COMP | 2015-07-07 | 2015-07-07 | COMP | 2015-07-07 | 2015-09-09 | COMP | 2015-09-09 | 2015-09-22 | COMP | 2015-09-22 | 2015-09-23 | 29 | 78 | 13421.56
31028127 | REPLACE 1368 FEET OF 6C WITH 2ACSR | 10/14/2013 | 107190180 | 10/14/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2015 | ED.06246.2227.TXFR.TROH | OVERHEAD TRANSFORMERS | 057 | YOLO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 1,368.000 | 1,368.000 | 08J | 2013 | 02/08/2020 | 2020 | 2308 | 329.7143 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-07-28 | 2015-07-28 | COMP | 2019-08-15 | 2019-08-15 | COMP | 2019-08-15 | 2019-08-15 | COMP | 2019-08-15 | 2019-08-16 | COMP | 2019-08-16 | 2019-08-17 | COMP | 2019-08-17 | 2019-08-20 | 1479 | 5 | 49407.07
31028173 | OC4 +OCEANO 1103 HWY 101 REC | 10/14/2013 | 107190334 | 10/14/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/01/2014 | ED.18260.1103 | OCEANO 1103 | 040 | SAN LUIS OBISP | 5532479 | CWSP 08W - Monthly Forecast Only | 1,487.000 | 0.000 | 08W | 2013 | 07/18/2015 | 2015 | 642 | 91.7143 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31028173_R2 OCEANO 1103 HWY 101 REC_08W | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2014-07-02 | 2014-09-12 | COMP | 2014-07-02 | 2014-09-18 | COMP | 2014-09-26 | 2014-10-06 | COMP | 2014-10-06 | 2014-10-20 | COMP | 2014-10-20 | 2014-11-10 | COMP | 2014-11-10 | 2014-11-14 | 96 | 39 | 230317.2
31029181 | *CANC* SLO 1101 WD 13-57792 OCB *CANC | 10/18/2013 | 107196624 | 10/17/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/01/2015 | ED.18263.1101 | SAN LUIS OBISPO 1101 | 040 | SAN LUIS OBISP | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2013 | 05/03/2018 | 2018 | 1658 | 236.8571 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2018-05-03 | 2018-05-03 | # | 2018-05-03 | 2018-05-03 | # | 2018-05-03 | 2018-05-03 | COMP | 2014-04-25 | 2014-04-25 | COMP | 2014-04-25 | 2014-04-25 | COMP | 2014-04-25 | 2014-04-25 | 0 | -1469 | 0
31029182 | SLO 1108 RECON (MORRISON & MCMILLAN) | 10/18/2013 | 107196623 | 10/17/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/01/2015 | ED.18263.1108 | SAN LUIS OBISPO 1108 | 040 | SAN LUIS OBISP | 5535457 | DO 08 - Monthly Forecast Only | 1,334.000 | 1,334.000 | 08J | 2013 | 01/07/2017 | 2017 | 1177 | 168.1429 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31029182_R5 SLO 1108 WD 13-63965 C/O 965 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-04-07 | 2016-06-27 | COMP | 2016-04-07 | 2016-06-28 | COMP | 2016-06-28 | 2016-06-29 | COMP | 2016-06-29 | 2016-08-19 | COMP | 2016-08-19 | 2016-12-28 | COMP | 2016-12-28 | 2016-12-28 | 83 | 182 | 104759.03
31030771 | OC4 OCGC AKA 1101 FORBESTWN RD 2724' Y | 10/24/2013 | 107202805 | 10/23/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/01/2015 | ED.13-G311100000 | OROVILLE MAP G3111 | 004 | BUTTE COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 2,724.000 | 2,724.000 | 08J | 2013 | 02/29/2020 | 2020 | 2319 | 331.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31030771_Kanaka 1101 Forbestown Rd | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-12-08 | 2015-12-08 | COMP | 2015-12-16 | 2015-12-16 | COMP | 2015-12-17 | 2015-12-21 | COMP | 2015-12-21 | 2016-04-14 | COMP | 2016-04-14 | 2016-06-21 | COMP | 2016-06-21 | 2016-06-22 | 13 | 184 | 441537.01
31030986 | OCLH HERDLYN 1102 REPLACE 727' 4AR | 10/24/2013 | 107203327 | 10/24/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/10/2015 | ED.16374.1102 | HERDLYN 1102 | 001 | ALAMEDA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 730.000 | 850.000 | 08J | 2013 | 12/26/2015 | 2015 | 793 | 113.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-04-01 | 2015-06-03 | COMP | 2015-04-01 | 2015-06-05 | COMP | 2015-06-05 | 2015-06-05 | COMP | 2015-06-05 | 2015-06-12 | COMP | 2015-06-12 | 2015-08-26 | COMP | 2015-08-26 | 2015-08-27 | 65 | 83 | 20789.93
31031486 | OCLH WESTLEY 1101 RECOND 1083' 4AR | 10/26/2013 | 107204195 | 10/24/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/10/2015 | ED.16267.1101 | WESTLEY 1101 | 039 | SAN JOAQUIN CO | 5535457 | DO 08 - Monthly Forecast Only | 925.000 | 925.000 | 08J | 2013 | 12/26/2015 | 2015 | 791 | 113 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-04-03 | 2015-06-23 | COMP | 2015-04-03 | 2015-06-30 | COMP | 2015-06-30 | 2015-06-30 | COMP | 2015-06-30 | 2015-07-09 | COMP | 2015-07-09 | 2015-09-17 | COMP | 2015-09-17 | 2015-09-18 | 88 | 80 | 33129.45
31032329 | OCGC WATSONVILLE, RECONDUCTOR 4 SP OH | 10/31/2013 | 107209805 | 10/30/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/30/2015 | ED.08333.2101 | WATSONVILLE 2101 | 044 | SANTA CRUZ COU | 5535457 | DO 08 - Monthly Forecast Only | 1,220.000 | 1,220.000 | 08J | 2013 | 12/26/2015 | 2015 | 786 | 112.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31032329_R2 WATSONVILLE, RECONDUCTOR 4 S | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-04-24 | 2015-04-24 | COMP | 2015-05-17 | 2015-05-17 | COMP | 2015-05-17 | 2015-05-17 | COMP | 2015-05-17 | 2015-06-09 | COMP | 2015-06-09 | 2015-07-27 | COMP | 2015-07-27 | 2015-07-27 | 23 | 71 | 72754.69
31033139 | +OCEANO 1103 RECON (S. HALCYON RD) | 11/01/2013 | 107386582 | 10/31/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/01/2015 | ED.18260.1103 | OCEANO 1103 | 040 | SAN LUIS OBISP | 5535457 | DO 08 - Monthly Forecast Only | 791.000 | 710.000 | 08J | 2013 | 01/14/2017 | 2017 | 1170 | 167.1429 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-12-09 | 2016-06-08 | COMP | 2015-12-09 | 2016-06-14 | COMP | 2016-06-14 | 2016-06-14 | COMP | 2016-06-14 | 2016-08-05 | COMP | 2016-08-05 | 2016-10-17 | COMP | 2016-10-17 | 2016-10-17 | 188 | 125 | 73517.05
31033160 | OCGC+MORRO BAY 1101 (MAIN ST) | 11/01/2013 | 107386584 | 10/31/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/01/2015 | ED.18301.1101 | MORRO BAY 1101 | 040 | SAN LUIS OBISP | 5535457 | DO 08 - Monthly Forecast Only | 497.000 | 497.000 | 08J | 2013 | 11/14/2015 | 2015 | 743 | 106.1429 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-05-14 | 2015-08-10 | COMP | 2015-05-14 | 2015-08-12 | COMP | 2015-08-12 | 2015-08-12 | COMP | 2015-08-12 | 2015-10-19 | COMP | 2015-10-19 | 2015-10-19 | COMP | 2015-10-19 | 2015-10-20 | 90 | 69 | 124362.32
31033174 | OCGC EEL RIVER1101RECOND2SPANSFERNBRIDGE | 11/01/2013 | 107386667 | 10/31/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/01/2015 | ED.19238.1101 | EEL RIVER 1101 | 012 | HUMBOLDT COUNT | 5535457 | DO 08 - Monthly Forecast Only | 495.000 | 495.000 | 08J | 2013 | 07/23/2016 | 2016 | 995 | 142.1429 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-11-05 | 2015-11-05 | COMP | 2015-11-17 | 2015-11-17 | COMP | 2015-11-17 | 2015-11-17 | COMP | 2015-11-17 | 2016-04-14 | COMP | 2016-04-14 | 2016-06-01 | COMP | 2016-06-01 | 2016-06-07 | 12 | 203 | 69515.06
31033175 | OCGC GARBERVILLE 1101 DET. CONDUCTOR | 11/01/2013 | 107386661 | 10/31/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/01/2015 | ED.19222.1101 | GARBERVILLE 1101 | 012 | HUMBOLDT COUNT | 5535457 | DO 08 - Monthly Forecast Only | 838.000 | 838.000 | 08J | 2013 | 04/21/2018 | 2018 | 1632 | 233.1429 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-06-15 | 2016-06-15 | COMP | 2016-06-25 | 2016-06-25 | COMP | 2016-06-25 | 2016-06-25 | COMP | 2016-06-25 | 2016-08-16 | COMP | 2016-08-16 | 2016-10-03 | COMP | 2016-10-03 | 2016-10-04 | 10 | 101 | 170372.15
31034172 | BH 405 CO4667 RECON 300FT OH LINE | 11/06/2013 | 107394877 | 11/05/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/29/2014 | ED.02402.0405.TXFR.TROH | OVERHEAD TRANSFORMERS | 041 | SAN MATEO COUN | 5505513 | PN-OH ANNEALED/DETER CNDCTR: PM MGD | 472.000 | 1,368.000 | 08J | 2013 | 04/01/2017 | 2017 | 1242 | 177.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-06-16 | 2016-06-12 | COMP | 2016-06-16 | 2016-06-16 | COMP | 2016-06-14 | 2016-06-14 | COMP | 2016-06-14 | 2016-06-27 | COMP | 2016-06-27 | 2016-07-11 | COMP | 2016-07-11 | 2016-07-11 | -2 | 27 | 95968.17
31034467 | XSAN ARDO 1102, 3 SP/LS OF 9093 | 11/07/2013 | 107393900 | 11/05/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/30/2015 | ED.18219.1102 | SAN ARDO 1102 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 267.000 | 267.000 | 08J | 2013 | 05/14/2016 | 2016 | 919 | 131.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-07-24 | 2015-08-31 | COMP | 2015-07-24 | 2015-09-03 | COMP | 2015-09-09 | 2015-09-09 | COMP | 2015-09-09 | 2016-04-13 | COMP | 2016-04-13 | 2016-04-19 | COMP | 2016-04-19 | 2016-04-22 | 47 | 226 | 15674.25
31034471 | +MORRO BAY 1101 WD (DENEGY PLANT) | 11/07/2013 | 107390777 | 11/04/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/01/2015 | ED.18301.1101 | MORRO BAY 1101 | 040 | SAN LUIS OBISP | 5535457 | DO 08 - Monthly Forecast Only | 525.000 | 525.000 | 08J | 2013 | 08/27/2016 | 2016 | 1024 | 146.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-12-04 | 2016-01-21 | COMP | 2015-12-04 | 2016-01-28 | COMP | 2016-01-28 | 2016-01-28 | COMP | 2016-01-28 | 2016-04-14 | COMP | 2016-04-14 | 2016-07-08 | COMP | 2016-07-08 | 2016-07-11 | 55 | 165 | 31022.82
31034472 | *CANC* PERRY 1101 WD 13-71707 *CANC | 11/07/2013 | 107391045 | 11/04/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/01/2015 | ED.18307.1101 | PERRY 1101 | 040 | SAN LUIS OBISP | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2013 | 05/03/2018 | 2018 | 1638 | 234 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2018-05-03 | 2018-05-03 | # | 2018-05-03 | 2018-05-03 | # | 2018-05-03 | 2018-05-03 | COMP | 2014-04-25 | 2014-04-25 | COMP | 2014-04-25 | 2014-04-25 | COMP | 2014-04-25 | 2014-04-25 | 0 | -1469 | 0
31036265 | R1128-RECNDUCTOR 3 SPANS,NSTALL CUT | 11/15/2013 | 107409265 | 11/13/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/30/2015 | ED.01347.1128 | RICHMOND R 1128 | 007 | CONTRA COSTA C | 5532479 | CWSP 08W - Monthly Forecast Only | 535.000 | 535.000 | 08W | 2013 | 01/28/2018 | 2018 | 1535 | 219.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-09-22 | 2015-09-11 | COMP | 2015-09-22 | 2015-11-03 | COMP | 2015-11-03 | 2015-11-03 | COMP | 2015-11-03 | 2015-11-13 | COMP | 2015-11-13 | 2016-09-12 | COMP | 2016-09-12 | 2016-09-14 | 42 | 316 | 75405.13
31036630 | OC4 OCGC RGH & READY1102 CO5297 ZONE R | 11/18/2013 | 107413679 | 11/15/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2015 | ED.16308.1102 | ROUGH AND READY IS 1102 | 039 | SAN JOAQUIN CO | 5535457 | DO 08 - Monthly Forecast Only | 4,635.000 | 4,700.000 | 08J | 2013 | 09/03/2016 | 2016 | 1020 | 145.7143 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31036630_R4 RGH & READY1102 CO5297 ZONE | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-09-01 | 2015-09-01 | COMP | 2015-09-09 | 2015-09-09 | COMP | 2015-09-11 | 2015-09-11 | COMP | 2015-09-11 | 2016-04-12 | COMP | 2016-04-12 | 2016-04-20 | COMP | 2016-04-20 | 2016-04-20 | 10 | 222 | 149286.95
31036816 | OCGC ASHLN 1112 RECNDUCTR + INSTALL RECL | 11/19/2013 | 107415600 | 11/18/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/25/2015 | ED.25205.1112 | ASHLAN AVE 1112 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 486.000 | 527.000 | 08J | 2013 | 06/25/2016 | 2016 | 949 | 135.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-07-02 | 2015-08-25 | COMP | 2015-07-02 | 2015-08-26 | COMP | 2015-08-27 | 2015-08-27 | COMP | 2015-08-27 | 2015-09-10 | COMP | 2015-09-10 | 2016-04-18 | COMP | 2016-04-18 | 2016-04-19 | 56 | 236 | 86405.64
31036817 | OCGC BARTON 1102 RECONDUCTOR | 11/19/2013 | 107415603 | 11/18/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/25/2015 | ED.25357.1102 | BARTON 1102 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 753.000 | 753.000 | 08J | 2013 | 10/28/2017 | 2017 | 1439 | 205.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-02-18 | 2016-04-07 | COMP | 2016-02-18 | 2016-04-12 | COMP | 2016-04-12 | 2016-04-12 | COMP | 2016-04-12 | 2016-05-17 | COMP | 2016-05-17 | 2016-09-08 | COMP | 2016-09-08 | 2016-09-12 | 54 | 153 | 82903.01
31036931 | OCGC PLACE ANNLD WIRE HWY 45 PH. 3 Y2017 | 11/19/2013 | 107416575 | 11/18/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 08/01/2017 | ED.14-Y230000000 | GLENN MAP Y23 | 011 | GLENN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 6,238.000 | 6,238.000 | 08J | 2013 | 09/09/2017 | 2017 | 1390 | 198.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 310369631_ HWY. 45 PH. 3_8J | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2017-05-23 | 2017-05-23 | COMP | 2017-05-23 | 2017-05-23 | COMP | 2017-05-23 | 2017-05-23 | COMP | 2017-05-23 | 2017-05-26 | COMP | 2017-05-26 | 2017-06-12 | COMP | 2017-06-12 | 2017-07-18 | 0 | 56 | 721691.79
31036932 | OCGC MEADOWS 2101 PRATTVILLE Y2016 8J | 11/19/2013 | 107416576 | 11/18/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/01/2015 | ED.18-J460000000 | LAS PLUMAS MAP J46 | 032 | PLUMAS COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 4,501.000 | 4,501.000 | 08J | 2013 | 03/25/2017 | 2017 | 1222 | 174.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31036932_ Y2016 Big Meadows 2101 Prattvi | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-10-11 | 2016-12-30 | COMP | 2016-10-11 | 2017-01-03 | COMP | 2017-01-03 | 2017-01-04 | COMP | 2017-01-04 | 2017-01-05 | COMP | 2017-01-05 | 2017-02-08 | COMP | 2017-02-08 | 2017-02-12 | 85 | 39 | 406905.24
31036933 | RECOND, ROAD D WILLOWS PH2 Y2017 | 11/19/2013 | 107416577 | 11/18/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/01/2017 | ED.14-Y170000000 | GLENN MAP Y17 | 011 | GLENN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 7,929.000 | 7,629.000 | 08J | 2013 | 04/21/2018 | 2018 | 1614 | 230.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31036933_REPL COND,ROAD D, WILLOWS PH 2 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2017-08-08 | 2017-08-08 | COMP | 2017-08-10 | 2017-08-10 | COMP | 2017-08-10 | 2017-08-10 | COMP | 2017-08-10 | 2017-08-11 | COMP | 2017-08-11 | 2017-09-01 | COMP | 2017-09-01 | 2017-09-16 | 2 | 37 | 249118.51
31037249 | OCGC LW 2112_ RECONDUCTOR W/ TREE WIRE | 11/20/2013 | 107398171 | 11/07/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/31/2014 | ED.01353.2112 | LAKEWOOD 2112 | 007 | CONTRA COSTA C | 5535457 | DO 08 - Monthly Forecast Only | 1,045.000 | 1,045.000 | 08J | 2013 | 04/14/2018 | 2018 | 1606 | 229.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2017-07-26 | 2017-07-26 | COMP | 2017-08-01 | 2017-08-01 | COMP | 2017-08-01 | 2017-08-01 | COMP | 2017-08-01 | 2017-08-02 | COMP | 2017-08-02 | 2017-11-06 | COMP | 2017-11-06 | 2017-11-06 | 6 | 97 | 80857.41
31037251 | OC4 OCGC REPL OH DET WIRE PAST C/O 8789 | 11/20/2013 | 107417959 | 11/19/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/30/2015 | ED.01365.2115 | CONTRA COSTA 2115 | 007 | CONTRA COSTA C | 5535457 | DO 08 - Monthly Forecast Only | 502.000 | 936.000 | 08J | 2013 | 11/19/2016 | 2016 | 1095 | 156.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-03-18 | 2015-03-31 | COMP | 2015-03-18 | 2015-04-21 | COMP | 2015-04-27 | 2015-04-27 | COMP | 2015-04-27 | 2015-04-28 | COMP | 2015-04-28 | 2015-04-30 | COMP | 2015-04-30 | 2015-04-30 | 40 | 3 | 148142.04
31037514 | OC4 OCGC STOCKTON A 411 RECONDUCTORING | 11/21/2013 | 107417098 | 11/19/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2015 | ED.16237.0411 | STOCKTON A 0411 | 039 | SAN JOAQUIN CO | 5535457 | DO 08 - Monthly Forecast Only | 1,253.000 | 1,200.000 | 08J | 2013 | 09/19/2015 | 2015 | 667 | 95.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-04-25 | 2015-04-25 | COMP | 2015-04-30 | 2015-04-30 | COMP | 2015-05-11 | 2015-05-11 | COMP | 2015-05-11 | 2015-05-16 | COMP | 2015-05-16 | 2015-07-22 | COMP | 2015-07-22 | 2015-07-23 | 16 | 73 | 76416.65
31037633 | OCCC X2102, RE-CONDUCTR 4 SPANS, SW 7193 | 11/21/2013 | 107417091 | 11/19/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/30/2015 | ED.18205.2102 | SOLEDAD 2102 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 861.000 | 861.000 | 08J | 2013 | 07/23/2016 | 2016 | 975 | 139.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-11-25 | 2015-11-17 | COMP | 2015-11-25 | 2015-12-01 | COMP | 2015-12-01 | 2015-12-01 | COMP | 2015-12-01 | 2016-04-28 | COMP | 2016-04-28 | 2016-06-10 | COMP | 2016-06-10 | 2016-06-13 | 6 | 195 | 92670.34
31038429 | CABRILLO 1103 (PURISIMA RD) | 11/23/2013 | 107459405 | 11/22/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/01/2015 | ED.18310.1103 | CABRILLO 1103 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 1,528.000 | 0.000 | 08J | 2013 | 12/10/2016 | 2016 | 1113 | 159 | PREC | 11 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | R5 WD CABRILLO 1103 13-0058079 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-01-14 | 2016-05-10 | COMP | 2016-01-14 | 2016-06-06 | COMP | 2016-06-06 | 2016-06-06 | COMP | 2016-06-06 | 2016-07-12 | COMP | 2016-07-12 | 2016-11-21 | COMP | 2016-11-21 | 2016-11-21 | 144 | 168 | 73989.41
31038430 | CABRILLO 1103 (HWY 246 & HAPGOOD RD) | 11/23/2013 | 107459471 | 11/22/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/01/2015 | ED.18310.1103 | CABRILLO 1103 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 1,271.000 | 0.000 | 08J | 2013 | 02/11/2017 | 2017 | 1176 | 168 | PREC | 11 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | WD CABRILLO 1103 13-0048220 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-01-14 | 2016-05-17 | COMP | 2016-01-14 | 2016-05-26 | COMP | 2016-05-26 | 2016-05-31 | COMP | 2016-05-31 | 2016-07-18 | COMP | 2016-07-18 | 2016-09-30 | COMP | 2016-09-30 | 2016-10-10 | 138 | 132 | 152895.12
31038431 | OC4 OCCC WD CABRILLO 1104 13-0056541 | 11/23/2013 | 107459475 | 11/22/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/01/2015 | ED.18310.1104 | CABRILLO 1104 | 042 | SANTA BARBARA | 5532479 | CWSP 08W - Monthly Forecast Only | 7,325.000 | 7,325.000 | 08W | 2013 | 03/19/2016 | 2016 | 847 | 121 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31038431_R2 WD CABRILLO 1104 13-0056541 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-08-07 | 2015-08-07 | COMP | 2015-08-21 | 2015-08-21 | COMP | 2015-08-28 | 2015-08-28 | COMP | 2015-08-28 | 2016-02-18 | COMP | 2016-02-18 | 2016-02-18 | COMP | 2016-02-18 | 2016-02-25 | 21 | 181 | 411819.84
31038907 | WIRE DOWN - MADISON 1105 RECOND 4 SP | 11/26/2013 | 107472748 | 11/26/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2015 | ED.06317.1105.SWIT | SWITCHES | 057 | YOLO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 987.000 | 987.000 | 08J | 2013 | 03/03/2018 | 2018 | 1558 | 222.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2017-04-26 | 2017-06-08 | COMP | 2017-04-26 | 2017-07-18 | COMP | 2017-07-18 | 2017-07-18 | COMP | 2017-07-18 | 2017-07-19 | COMP | 2017-07-19 | 2017-07-27 | COMP | 2017-07-27 | 2017-08-03 | 83 | 16 | 44301.15
31039056 | OCGC MORMON 1102 CO1911 ZONE RECOND P1 | 11/27/2013 | 107471868 | 11/26/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2015 | ED.16321.1102 | MORMON 1102 | 039 | SAN JOAQUIN CO | 5517127 | DO 08 - Monthly Forecast Only | 4,400.000 | 4,400.000 | 08J | 2013 | 09/10/2016 | 2016 | 1018 | 145.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31039056_ Mormon 1102 Reconductoring | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-04-19 | 2016-04-19 | COMP | 2016-04-27 | 2016-04-27 | COMP | 2016-04-27 | 2016-04-27 | COMP | 2016-04-27 | 2016-05-18 | COMP | 2016-05-18 | 2016-08-26 | COMP | 2016-08-26 | 2016-08-29 | 8 | 124 | 114844.19
31039795 | MABURY 1102 WIRE DOWN 13-0077162 | 12/04/2013 | 107505383 | 12/03/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/31/2015 | ED.08219.1102.CAPA | CAPACITORS | 043 | SANTA CLARA CO | 5532479 | CWSP 08W - Monthly Forecast Only | 130.000 | 276.000 | 08W | 2013 | 03/19/2016 | 2016 | 836 | 119.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-09-29 | 2015-10-05 | COMP | 2015-09-29 | 2015-10-16 | COMP | 2015-10-16 | 2015-10-16 | COMP | 2015-10-16 | 2016-03-19 | COMP | 2016-03-19 | 2016-03-19 | COMP | 2016-03-19 | 2016-03-19 | 17 | 155 | 30578.83
31040925 | RECONDUCT #4ACSR_W.JACKSON_HAYWRD | 12/06/2013 | 107508313 | 12/05/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/27/2015 | ED.24-J090900000.STRU.ENCL | MISSION J0909 ENCLOSURE | 001 | ALAMEDA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 270.000 | 270.000 | 08W | 2013 | 06/09/2018 | 2018 | 1646 | 235.1429 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-12-05 | 2015-12-05 | COMP | 2015-12-09 | 2015-12-09 | COMP | 2015-12-16 | 2015-12-16 | COMP | 2015-12-16 | 2016-04-15 | COMP | 2016-04-15 | 2016-06-17 | COMP | 2016-06-17 | 2016-06-18 | 11 | 185 | 51124.06
31041867 | OCGC X MORMON 1102 CO1911 ZONE RECOND | 12/11/2013 | 107523489 | 12/10/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2016 | ED.16321.1102 | MORMON 1102 | 039 | SAN JOAQUIN CO | 5535457 | DO 08 - Monthly Forecast Only | 2,664.000 | 2,664.000 | 08J | 2013 | 12/13/2016 | 2016 | 1098 | 156.8571 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31041867_MORMON 1102 CO1911 ZONE RECOND | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-07-28 | 2016-07-28 | COMP | 2016-08-01 | 2016-08-01 | COMP | 2016-08-02 | 2016-08-04 | COMP | 2016-08-01 | 2016-08-24 | COMP | 2016-08-24 | 2016-11-21 | COMP | 2016-11-21 | 2016-11-21 | 7 | 109 | 64407.45
31041868 | OCGC MORMON 1102 CO1911 ZONE RECOND | 12/11/2013 | 107523502 | 12/10/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2016 | ED.16321.1102 | MORMON 1102 | 039 | SAN JOAQUIN CO | 5535457 | DO 08 - Monthly Forecast Only | 3,551.000 | 3,551.000 | 08J | 2013 | 01/14/2017 | 2017 | 1130 | 161.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31041868_MORMON 1102 CO1911 ZONE RECOND | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-07-28 | 2016-07-28 | COMP | 2016-08-01 | 2016-08-01 | COMP | 2016-08-01 | 2016-08-04 | COMP | 2016-08-01 | 2016-08-24 | COMP | 2016-08-24 | 2017-01-03 | COMP | 2017-01-03 | 2017-01-03 | 7 | 152 | 88361.18
31041869 | OCGC RGH AND READY 1102 CO5297 ZONE REC | 12/11/2013 | 107523509 | 12/10/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2016 | ED.16308.1102 | ROUGH AND READY IS 1102 | 039 | SAN JOAQUIN CO | 5535457 | DO 08 - Monthly Forecast Only | 6,151.000 | 6,151.000 | 08J | 2013 | 11/05/2016 | 2016 | 1060 | 151.4286 | PREC | 11 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31041869_RGH AND READY 1102 CO5297 ZONE | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-06-01 | 2016-06-01 | COMP | 2016-06-09 | 2016-06-09 | COMP | 2016-06-15 | 2016-06-15 | COMP | 2016-06-15 | 2016-07-28 | COMP | 2016-07-28 | 2016-10-14 | COMP | 2016-10-14 | 2016-10-17 | 14 | 124 | 202858.32
31042419 | OCGC LOCKEFORD 2102 RECONDUCTOR PH2 | 12/13/2013 | 107531228 | 12/12/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2016 | ED.16368.2102 | LOCKEFORD 2102 | 039 | SAN JOAQUIN CO | 5535457 | DO 08 - Monthly Forecast Only | 3,750.000 | 3,750.000 | 08J | 2013 | 12/03/2016 | 2016 | 1086 | 155.1429 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31042419_LOCKEFORD 2102 RECONDUCTOR PHAS | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-06-22 | 2016-06-22 | COMP | 2016-06-23 | 2016-06-23 | COMP | 2016-06-23 | 2016-06-23 | COMP | 2016-06-23 | 2016-08-10 | COMP | 2016-08-10 | 2016-11-15 | COMP | 2016-11-15 | 2016-11-15 | 1 | 145 | 81559.48
31042661 | +CH 1101 WIREDOWN 11000 E HWY 46 | 12/13/2013 | 107531753 | 12/13/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/30/2015 | ED.18256.1101 | CHOLAME 1101 | 040 | SAN LUIS OBISP | 5535457 | DO 08 - Monthly Forecast Only | 2,058.000 | 2,000.000 | 08J | 2013 | 11/19/2016 | 2016 | 1072 | 153.1429 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | R5 CH 1101 WIREDOWN 11000 E HWY 46 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-04-18 | 2016-06-23 | COMP | 2016-04-18 | 2016-06-27 | COMP | 2016-06-27 | 2016-06-27 | COMP | 2016-06-27 | 2016-08-11 | COMP | 2016-08-11 | 2016-10-31 | COMP | 2016-10-31 | 2016-11-10 | 70 | 136 | 55738
31043129 | EB-RELIAIBLITY K1103-RECONDUT | 12/18/2013 | 107540000 | 12/18/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/31/2015 | ED.01210.1103 | OAKLAND K 1103 | 001 | ALAMEDA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 400.000 | 900.000 | 08W | 2013 | 11/24/2018 | 2018 | 1802 | 257.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2017-08-18 | 2017-11-03 | COMP | 2017-09-13 | 2017-11-17 | COMP | 2017-11-17 | 2017-11-17 | COMP | 2017-11-17 | 2017-11-20 | COMP | 2017-11-20 | 2017-12-07 | COMP | 2017-12-07 | 2017-12-07 | 91 | 20 | 85612.01
31043565 | OCCC -0081136 HOLL 2101 WIREDOWN | 12/18/2013 | 107537324 | 12/17/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/30/2015 | ED.18249.2101 | HOLLISTER 2101 | 035 | SAN BENITO COU | 5535457 | DO 08 - Monthly Forecast Only | 97.000 | 0.000 | 08J | 2013 | 05/18/2019 | 2019 | 1977 | 282.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-03-28 | 2016-03-28 | COMP | 2016-04-06 | 2016-04-06 | COMP | 2016-04-06 | 2016-04-06 | COMP | 2016-04-06 | 2016-05-06 | COMP | 2016-05-06 | 2016-07-22 | COMP | 2016-07-22 | 2016-07-25 | 9 | 110 | 67021.61
31043566 | OCGC XRECOND 500FT W. ZAYANTE RD CE 2105 | 12/18/2013 | 107537285 | 12/17/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/14/2014 | ED.08362.2105 | CAMP EVERS 2105 | 044 | SANTA CRUZ COU | 5532479 | CWSP 08W - Monthly Forecast Only | 510.000 | 510.000 | 08W | 2013 | 12/26/2015 | 2015 | 738 | 105.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2014-11-15 | 2015-02-02 | COMP | 2014-11-15 | 2015-02-24 | COMP | 2015-02-24 | 2015-02-24 | COMP | 2015-02-24 | 2015-03-05 | COMP | 2015-03-05 | 2015-03-11 | COMP | 2015-03-11 | 2015-03-13 | 101 | 17 | 60459
31043567 | OCGC XRECON W/675FT TW LOKHRT GL CE 2105 | 12/18/2013 | 107537288 | 12/17/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/20/2015 | ED.08362.2104 | CAMP EVERS 2104 | 044 | SANTA CRUZ COU | 5532479 | CWSP 08W - Monthly Forecast Only | 705.000 | 705.000 | 08W | 2013 | 12/26/2015 | 2015 | 738 | 105.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-01-20 | 2015-01-20 | COMP | 2015-01-28 | 2015-02-06 | COMP | 2015-02-06 | 2015-02-06 | COMP | 2015-02-06 | 2015-02-13 | COMP | 2015-02-13 | 2015-04-25 | COMP | 2015-04-25 | 2015-04-25 | 17 | 78 | 81309.75
31044254 | +SANTA MARIA 1110 (MAIN ST/8TH ST) | 12/21/2013 | 107552853 | 12/20/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/01/2014 | ED.18267.1110 | SANTA MARIA 1110 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 2,174.000 | 2,174.000 | 08J | 2013 | 12/10/2016 | 2016 | 1085 | 155 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31044254_WD SANTA MARIA 1110 13-0082788 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-03-31 | 2016-07-13 | COMP | 2016-03-31 | 2016-07-14 | COMP | 2016-07-14 | 2016-07-14 | COMP | 2016-07-14 | 2016-08-23 | COMP | 2016-08-23 | 2016-11-06 | COMP | 2016-11-06 | 2016-11-07 | 105 | 116 | 97661.49
31044708 | RECNDUCT 1/0 AL WIRE ON DOBBEL AVE HAYW | 12/23/2013 | 107554489 | 12/23/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/22/2019 | ED.24-J101400000.STRU.ENCL | MISSION J1014 ENCLOSURE | 001 | ALAMEDA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 214.000 | 214.000 | 08J | 2013 | 11/23/2019 | 2019 | 2161 | 308.7143 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-10-14 | 2019-07-16 | COMP | 2016-10-14 | 2019-08-08 | COMP | 2019-08-08 | 2019-08-08 | COMP | 2019-08-08 | 2019-08-09 | COMP | 2019-08-09 | 2019-08-12 | COMP | 2019-08-12 | 2019-08-13 | 1028 | 5 | 22083
31046155 | CALIF 1112 WIRE DOWN RECNDUCTOR | 01/02/2014 | 107564766 | 12/24/2013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/25/2016 | ED.25228.1112 | CALIFORNIA AVE 1112 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 358.000 | 358.000 | 08J | 2014 | 10/28/2017 | 2017 | 1395 | 199.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-10-05 | 2016-11-19 | COMP | 2016-10-05 | 2016-11-29 | COMP | 2016-11-29 | 2016-11-29 | COMP | 2016-11-29 | 2016-12-01 | COMP | 2016-12-01 | 2017-01-19 | COMP | 2017-01-19 | 2017-02-02 | 55 | 65 | 51084.45
31046680 | OCGC RECNDCTR 800' OF 4C ON PEABODY 2107 | 01/03/2014 | 107575429 | 01/03/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2014 | ED.06364.2107.TXFR.TROH | OVERHEAD TRANSFORMERS | 048 | SOLANO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 750.000 | 650.000 | 08J | 2014 | 11/19/2016 | 2016 | 1051 | 150.1429 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-06-17 | 2016-06-17 | COMP | 2016-06-20 | 2016-06-20 | COMP | 2016-06-20 | 2016-06-20 | COMP | 2016-06-20 | 2016-08-11 | COMP | 2016-08-11 | 2016-10-27 | COMP | 2016-10-27 | 2016-10-28 | 3 | 130 | 24216.69
31046900 | *CANC*TRACY 1106-*REF PM30982901* *CANC | 01/06/2014 | 107569903 | 01/02/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 05/29/2015 | ED.16288.1106 | TRACY 1106 | 039 | SAN JOAQUIN CO | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2014 | 03/04/2020 | 2020 | 2249 | 321.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2020-03-04 | 2020-03-04 | # | 2020-03-04 | 2020-03-04 | # | 2020-03-04 | 2020-03-04 | COMP | 2020-02-13 | 2020-02-13 | COMP | 2020-02-13 | 2020-02-13 | COMP | 2020-02-13 | 2020-02-13 | 0 | -20 | 0
31047513 | OCGC RECONDUCTOR 2 SPANS DIXON 1103 | 01/08/2014 | 107579237 | 01/08/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2015 | ED.06206.1103.SWIT | SWITCHES | 048 | SOLANO COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 509.000 | 0.000 | 08W | 2014 | 03/19/2016 | 2016 | 801 | 114.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-09-03 | 2015-09-03 | COMP | 2015-09-09 | 2015-09-09 | COMP | 2015-09-10 | 2015-09-10 | COMP | 2015-09-10 | 2016-02-17 | COMP | 2016-02-17 | 2016-02-17 | COMP | 2016-02-17 | 2016-02-23 | 7 | 166 | 31201.07
31047788 | MADERA 1104-RECNDUCTOR SUNSET AVE | 01/09/2014 | 107579859 | 01/09/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/30/2016 | ED.25276.1104 | MADERA 1104 | 020 | MADERA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 1,440.000 | 1,445.000 | 08J | 2014 | 02/08/2020 | 2020 | 2221 | 317.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-12-27 | 2017-04-12 | COMP | 2016-12-27 | 2017-04-20 | COMP | 2017-04-20 | 2017-04-20 | COMP | 2017-04-20 | 2018-10-02 | COMP | 2018-10-02 | 2018-11-16 | COMP | 2018-11-16 | 2018-11-20 | 114 | 579 | 125793.85
31048179 | OC4 OCGC SONOMA1105-WIREDWN-8TH ST EAST | 01/10/2014 | 107581053 | 01/09/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/30/2015 | ED.04272.1105.SWIT | SWITCHES | 049 | SONOMA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 1,275.000 | 0.000 | 08W | 2014 | 06/16/2018 | 2018 | 1618 | 231.1429 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2014-12-23 | 2014-12-23 | COMP | 2015-01-06 | 2015-01-06 | COMP | 2015-01-09 | 2015-01-26 | COMP | 2015-01-26 | 2015-01-29 | COMP | 2015-01-29 | 2015-01-30 | COMP | 2015-01-30 | 2015-02-02 | 34 | 7 | 101552.35
31048895 | OCGC RECONDUCT 1-SPAN -WILLITS 1103 | 01/13/2014 | 107593724 | 01/13/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/27/2015 | ED.04266.1103.SWIT | SWITCHES | 023 | MENDOCINO COUN | 5532479 | CWSP 08W - Monthly Forecast Only | 429.000 | 0.000 | 08W | 2014 | 06/25/2016 | 2016 | 894 | 127.7143 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2014-11-24 | 2015-03-17 | COMP | 2014-11-24 | 2015-07-10 | COMP | 2015-07-10 | 2015-07-10 | COMP | 2015-07-10 | 2015-09-10 | COMP | 2015-09-10 | 2016-02-04 | COMP | 2016-02-04 | 2016-02-08 | 228 | 213 | 65897.64
31049739 | MANCHESTER 1108 6C RECONDUCTOR | 01/15/2014 | 107598109 | 01/15/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/25/2016 | ED.25392.1108 | MANCHESTER 1108 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 170.000 | 420.000 | 08J | 2014 | 01/28/2018 | 2018 | 1474 | 210.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-06-30 | 2016-07-27 | COMP | 2016-06-30 | 2016-08-05 | COMP | 2016-08-05 | 2016-08-05 | COMP | 2016-08-05 | 2016-08-31 | COMP | 2016-08-31 | 2016-11-23 | COMP | 2016-11-23 | 2016-11-23 | 36 | 110 | 73978.27
31049891 | CURTIS 1704 - REPLACE 350FT OF 6CU | 01/16/2014 | 107596161 | 01/14/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 05/01/2015 | ED.16335.1704 | CURTIS 1704 | 055 | TUOLUMNE COUNT | 5535457 | DO 08 - Monthly Forecast Only | 425.000 | 440.000 | 08J | 2014 | 01/28/2017 | 2017 | 1108 | 158.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-08-23 | 2016-09-07 | COMP | 2016-08-23 | 2016-09-13 | COMP | 2016-09-13 | 2016-09-13 | COMP | 2016-09-13 | 2016-09-16 | COMP | 2016-09-16 | 2016-12-27 | COMP | 2016-12-27 | 2016-12-27 | 21 | 105 | 19467.34
31050031 | EP REPLACE DAMAGED CONDUCTOR, ROAD 19 | 01/17/2014 | 107600910 | 01/16/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/01/2015 | ED.14-T230000000 | GLENN MAP T23 | 011 | GLENN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 260.000 | 0.000 | 08J | 2014 | 01/28/2017 | 2017 | 1107 | 158.1429 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-06-30 | 2016-06-30 | COMP | 2016-07-28 | 2016-07-28 | COMP | 2016-07-05 | 2016-07-28 | COMP | 2016-07-05 | 2016-08-03 | COMP | 2016-08-03 | 2016-12-21 | COMP | 2016-12-21 | 2016-12-21 | 28 | 146 | 10529.52
31052272 | REDBUD1101 RECONDCTOR LINE BAD SPLCES | 01/27/2014 | 107776959 | 01/27/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/30/2016 | ED.04319.1101.RECL | RECLOSERS | 017 | LAKE COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 1,431.000 | 0.000 | 08J | 2014 | 06/29/2019 | 2019 | 1979 | 282.7143 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | REDBUD1101 RECONDCTOR LINE BAD SPLCES | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-08-11 | 2016-09-02 | COMP | 2016-08-11 | 2016-09-14 | COMP | 2016-09-14 | 2016-09-14 | COMP | 2016-12-06 | 2017-02-10 | COMP | 2017-02-10 | 2017-02-13 | COMP | 2017-02-13 | 2017-02-14 | 34 | 153 | 376332.01
31052323 | RECON 700' 6C DUE TO SPLICES - WD | 01/27/2014 | 107748027 | 01/24/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 01/30/2016 | ED.25235.1110 | SANGER 1110 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 882.000 | 872.000 | 08J | 2014 | 04/22/2017 | 2017 | 1181 | 168.7143 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-10-03 | 2016-12-14 | COMP | 2016-10-03 | 2017-01-03 | COMP | 2017-01-03 | 2017-01-03 | COMP | 2017-01-03 | 2017-01-05 | COMP | 2017-01-05 | 2017-01-26 | COMP | 2017-01-26 | 2017-02-01 | 92 | 29 | 64917
31052971 | RACETRACK 1704 RECOND 7,800FT OF 4CU | 01/29/2014 | 107779106 | 01/28/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/30/2017 | ED.16376.1704 | RACETRACK 1704 | 055 | TUOLUMNE COUNT | 5535457 | DO 08 - Monthly Forecast Only | 7,466.000 | 7,800.000 | 08J | 2014 | 04/21/2018 | 2018 | 1543 | 220.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | R4E RACETRACK 1704 RECOND 7,800FT OF 4CU | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2017-01-04 | 2017-09-20 | COMP | 2017-01-04 | 2017-09-25 | COMP | 2017-09-25 | 2017-09-25 | COMP | 2017-09-25 | 2017-09-26 | COMP | 2017-09-26 | 2017-10-16 | COMP | 2017-10-16 | 2017-10-18 | 264 | 23 | 853518.51
31053110 | MABURY 1102 WIRE DOWN 14-0004189 | 01/30/2014 | 107781876 | 01/29/2014 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/01/2016 | ED.08219.1106.RECL | RECLOSERS | 043 | SANTA CLARA CO | 5532479 | CWSP 08W - Monthly Forecast Only | 644.000 | 0.000 | 08W | 2014 | # | OPEN | 2500 | 357.1429 | DOCC | 8 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-01-12 | 2015-12-21 | COMP | 2015-07-06 | 2016-01-11 | COMP | 2016-01-11 | 2016-01-11 | COMP | 2016-01-11 | 2016-04-16 | COMP | 2016-04-16 | 2016-07-02 | COMP | 2016-07-02 | 2016-07-06 | -1 | 177 | 107029.25
31054560 | OCGC REPLACE 6C ON RICE 1102 - WIRE DOWN | 02/04/2014 | 107779398 | 01/28/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2015 | ED.06283.1102.TXFR.TROH | OVERHEAD TRANSFORMERS | 006 | COLUSA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 698.000 | 698.000 | 08J | 2014 | 12/17/2016 | 2016 | 1047 | 149.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-07-13 | 2016-07-19 | COMP | 2016-07-13 | 2016-07-20 | COMP | 2016-07-20 | 2016-07-20 | COMP | 2016-07-20 | 2016-08-25 | COMP | 2016-08-25 | 2016-11-19 | COMP | 2016-11-19 | 2016-11-21 | 7 | 124 | 37799.77
31054897 | OCGC BH402 LS CO10192 REPL.2 SPANS OH LI | 02/06/2014 | 107794934 | 02/06/2014 | # | Not assigned | 30 | Technically Completed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 10/23/2014 | ED.02402.0402.TXFR.TROH | OVERHEAD TRANSFORMERS | 041 | SAN MATEO COUN | 5535457 | DO 08 - Monthly Forecast Only | 686.000 | 500.000 | 08W | 2014 | # | OPEN | 2493 | 356.1429 | FICL | 10 | E070 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-03-23 | 2015-03-23 | COMP | 2015-06-03 | 2015-06-03 | COMP | 2015-06-03 | 2015-06-03 | COMP | 2015-06-03 | 2015-09-10 | COMP | 2015-09-10 | 2015-11-24 | COMP | 2015-11-24 | 2015-12-01 | 72 | 181 | 163771.09
31055014 | OC4 REP_1/0 CU PAR COND W/715 AL CL 2211 | 02/06/2014 | 107791155 | 02/04/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/01/2016 | ED.01202.2211 | CLAYTON 2211 | 007 | CONTRA COSTA C | 5535457 | DO 08 - Monthly Forecast Only | 2,395.000 | 2,395.000 | 08J | 2014 | 06/18/2016 | 2016 | 863 | 123.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2014-08-18 | 2014-09-30 | COMP | 2014-08-18 | 2014-10-29 | COMP | 2014-11-03 | 2014-11-19 | COMP | 2014-11-19 | 2014-12-02 | COMP | 2014-12-02 | 2015-01-28 | COMP | 2015-01-28 | 2015-01-28 | 93 | 70 | 263704.98
31056717 | +SLO 1101 WD14-5147 (ANDREWS & MONTEREY | 02/14/2014 | 107816841 | 02/13/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/01/2015 | ED.18263.1101 | SAN LUIS OBISPO 1101 | 040 | SAN LUIS OBISP | 5535457 | DO 08 - Monthly Forecast Only | 940.000 | 940.000 | 08J | 2014 | 04/25/2020 | 2020 | 2262 | 323.1429 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | R5 SLO 1101 WD 14-5147 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-04-13 | 2016-06-06 | COMP | 2016-04-13 | 2016-06-14 | COMP | 2016-06-14 | 2016-06-14 | COMP | 2016-06-14 | 2016-08-04 | COMP | 2016-08-04 | 2016-10-15 | COMP | 2016-10-15 | 2016-10-18 | 62 | 126 | 119259.09
31057517 | OCCCRECONDUCTOR HOWSLEY RD, CATLETT 1101 | 02/19/2014 | 107822835 | 02/19/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2015 | ED.15376.1101.TXFR.TROH | OVERHEAD TRANSFORMERS | 051 | SUTTER COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 2,096.000 | 2,100.000 | 08J | 2014 | 01/21/2017 | 2017 | 1067 | 152.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31057517_RECONDUCTOR HOWSLEY RD, CATLETT | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-06-22 | 2016-06-22 | COMP | 2016-06-27 | 2016-07-01 | COMP | 2016-07-01 | 2016-07-01 | COMP | 2016-07-01 | 2016-07-02 | COMP | 2016-07-02 | 2016-07-02 | COMP | 2016-07-02 | 2016-07-06 | 9 | 5 | 144903.33
31058659 | RECNDUCTOR CHOWCHILLA 1101 - AVE 22 | 02/25/2014 | 107826783 | 02/21/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/29/2016 | ED.25410.1101 | CHOWCHILLA 1101 | 020 | MADERA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 3,460.000 | 3,465.000 | 08J | 2014 | 02/11/2017 | 2017 | 1082 | 154.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31058659_RECONDUCTOR CHOWCHILLA 1101 - A | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-08-18 | 2016-09-21 | COMP | 2016-08-18 | 2016-09-29 | COMP | 2016-09-29 | 2016-09-29 | COMP | 2016-09-29 | 2016-10-04 | COMP | 2016-10-04 | 2017-01-18 | COMP | 2017-01-18 | 2017-01-23 | 42 | 116 | 147183.6
31059574 | 2016 GUERNSEY 1104 4CU RECONDUCTOR | 02/27/2014 | 107835946 | 02/27/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/28/2016 | ED.25266.1104 | GUERNSEY 1104 | 016 | KINGS COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 880.000 | 880.000 | 08J | 2014 | 11/19/2016 | 2016 | 996 | 142.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31059574 Guernsey 1104 Reconductor | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-01-12 | 2016-02-17 | COMP | 2016-01-12 | 2016-02-25 | COMP | 2016-02-25 | 2016-02-25 | COMP | 2016-02-25 | 2016-04-13 | COMP | 2016-04-13 | 2016-08-22 | COMP | 2016-08-22 | 2016-08-22 | 44 | 179 | 94657.53
31059794 | OCGC CLARKSVILLE 2104 RECONDUCTOR,PHASE1 | 02/28/2014 | 107836345 | 02/27/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/30/2016 | ED.15361.2104.SWIT | SWITCHES | 009 | EL DORADO COUN | 5532479 | CWSP 08W - Monthly Forecast Only | 7,438.000 | 7,438.000 | 08W | 2014 | 01/14/2017 | 2017 | 1051 | 150.1429 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31059794_Clarksville 2104 Recon Green | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-05-16 | 2016-05-16 | COMP | 2016-05-23 | 2016-05-23 | COMP | 2016-05-23 | 2016-05-23 | COMP | 2016-05-23 | 2016-07-15 | COMP | 2016-07-15 | 2016-10-19 | COMP | 2016-10-19 | 2016-10-26 | 7 | 156 | 492416.19
31060012 | RPL 325 FT OF 4AR ANDERSON 1103 | 03/03/2014 | 107838856 | 02/28/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/13/2017 | ED.87-R330200000 | SHASTA MAP R3302 | 045 | SHASTA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 325.000 | 0.000 | 08J | 2014 | 04/21/2018 | 2018 | 1510 | 215.7143 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2014-10-22 | 2014-10-30 | COMP | 2014-10-22 | 2015-01-10 | COMP | 2015-01-10 | 2015-01-10 | NOTN | 2015-01-10 | 2015-01-10 | NOTN | 2015-01-10 | 2015-01-10 | NOTN | 2015-01-10 | 2015-01-10 | 80 | 0 | 1742.96
31060016 | OCCCRECO 1 SPAN LINE SIDE FU 1829 TW2107 | 03/03/2014 | 107834516 | 02/26/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 08/01/2014 | ED.01465.2107 | TIDEWATER 2107 | 007 | CONTRA COSTA C | 5532479 | CWSP 08W - Monthly Forecast Only | 197.000 | 292.000 | 08W | 2014 | 12/26/2015 | 2015 | 663 | 94.7143 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2014-12-23 | 2014-12-20 | COMP | 2014-12-23 | 2014-12-23 | COMP | 2015-01-09 | 2015-01-09 | COMP | 2015-01-09 | 2015-01-21 | COMP | 2015-01-21 | 2015-01-31 | COMP | 2015-01-31 | 2015-01-31 | 17 | 22 | 202120.15
31060753 | GUSTINE 1102 - RECOND 585' W/2AR - WD | 03/05/2014 | 107842653 | 03/04/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 02/27/2015 | ED.16311.1102 | GUSTINE 1102 | 024 | MERCED COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 585.000 | 575.000 | 08J | 2014 | 01/20/2018 | 2018 | 1417 | 202.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-08-09 | 2016-09-25 | COMP | 2016-08-09 | 2016-09-29 | COMP | 2016-09-29 | 2016-09-29 | COMP | 2016-09-29 | 2016-10-11 | COMP | 2016-10-11 | 2017-01-19 | COMP | 2017-01-19 | 2017-01-27 | 51 | 120 | 79617.29
31061032 | OCGC REPLACE DETERIORATED #4 CU, CAPAY | 03/06/2014 | 107844181 | 03/05/2014 | # | Not assigned | 30 | Technically Completed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/01/2016 | ED.14-S210000000 | GLENN MAP S21 | 011 | GLENN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 2,343.000 | 2,343.000 | 08J | 2014 | # | OPEN | 2465 | 352.1429 | FICL | 10 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-09-15 | 2016-09-15 | COMP | 2016-09-15 | 2016-09-15 | COMP | 2016-09-15 | 2016-09-19 | COMP | 2016-09-19 | 2016-09-27 | COMP | 2016-09-27 | 2017-01-20 | COMP | 2017-01-20 | 2017-01-26 | 4 | 129 | 121478.54
31062090 | OCCC SOLED 2101: RECNDUCTR 2 SPANS OF OH | 03/11/2014 | 107874792 | 03/10/2014 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2015 | ED.18205.2101 | SOLEDAD 2101 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 785.000 | 0.000 | 08J | 2014 | # | OPEN | 2460 | 351.4286 | DOCC | 8 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-03-24 | 2016-03-24 | COMP | 2016-04-06 | 2016-04-06 | COMP | 2016-04-06 | 2016-04-06 | COMP | 2016-04-06 | 2016-04-15 | COMP | 2016-04-15 | 2016-07-23 | COMP | 2016-07-23 | 2016-07-29 | 13 | 114 | 42693.94
31062247 | OCCCE WEST SAC 1105 RECONDUCTOR 220 FEET | 03/11/2014 | 107889100 | 03/11/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2015 | ED.06313.1105.SWIT | SWITCHES | 057 | YOLO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 865.000 | 870.000 | 08J | 2014 | 08/17/2019 | 2019 | 1985 | 283.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-07-10 | 2016-07-10 | COMP | 2016-07-11 | 2016-07-22 | COMP | 2016-07-22 | 2016-07-22 | COMP | 2016-07-22 | 2016-11-09 | COMP | 2016-11-09 | 2016-11-28 | COMP | 2016-11-28 | 2016-11-28 | 12 | 129 | 80949
31062635 | ZCRESY 2103 RECN 530' OF 6CU /W 2 ACSR | 03/12/2014 | 107890135 | 03/11/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/30/2016 | ED.25470.2103 | CRESSEY 2103 | 024 | MERCED COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 370.000 | 370.000 | 08J | 2014 | 05/13/2017 | 2017 | 1158 | 165.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2017-01-31 | 2017-01-31 | COMP | 2017-02-08 | 2017-02-08 | COMP | 2017-02-08 | 2017-02-08 | COMP | 2017-02-08 | 2017-02-12 | COMP | 2017-02-12 | 2017-03-07 | COMP | 2017-03-07 | 2017-03-20 | 8 | 40 | 47477.48
31062729 | LERDO 1103 RECONDUCTOR 1,700FT WD | 03/13/2014 | 107892098 | 03/13/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/30/2016 | ED.25349.1103.TXFR.TROH | OVERHEAD TRANSFORMERS | 015 | KERN COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 1,680.000 | 1,680.000 | 08W | 2014 | 03/19/2016 | 2016 | 737 | 105.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-09-18 | 2015-10-29 | COMP | 2015-09-18 | 2015-11-02 | COMP | 2015-11-02 | 2015-11-02 | INPR | 2015-11-02 | 2016-03-19 | # | 2016-03-19 | 2016-03-19 | # | 2016-03-19 | 2016-03-19 | 45 | 138 | 71952.77
31062912 | OCLH TN 2113 1255 PARKHILL 14-0008850 | 03/13/2014 | 107892903 | 03/13/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2016 | ED.18305.2113 | TEMPLETON 2113 | 040 | SAN LUIS OBISP | 5535457 | DO 08 - Monthly Forecast Only | 1,045.000 | 1,405.000 | 08J | 2014 | 04/22/2017 | 2017 | 1136 | 162.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-06-24 | 2016-06-23 | COMP | 2016-06-24 | 2016-06-24 | COMP | 2016-06-24 | 2016-06-24 | COMP | 2016-06-24 | 2016-08-15 | COMP | 2016-08-15 | 2016-11-18 | COMP | 2016-11-18 | 2017-03-21 | 0 | 270 | 51250.15
31063598 | WEEDPATCH 1106 RECOND WIRE DOWN | 03/17/2014 | 107905576 | 03/17/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 05/30/2014 | ED.25297.1106.TXFR.TRPM | PAD MOUNTED TRANSFORMERS | 015 | KERN COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 1,093.000 | 1,093.000 | 08W | 2014 | 08/27/2016 | 2016 | 894 | 127.7143 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-10-29 | 2015-12-15 | COMP | 2015-10-29 | 2015-12-16 | COMP | 2015-12-16 | 2015-12-16 | COMP | 2015-12-16 | 2016-04-15 | COMP | 2016-04-15 | 2016-07-03 | COMP | 2016-07-03 | 2016-07-11 | 48 | 208 | 24665.35
31063935 | RECN 6 CU LINE SIDE LR 18692 TW 2105 | 03/20/2014 | 107890727 | 03/12/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/01/2015 | ED.01465.2105 | TIDEWATER 2105 | 007 | CONTRA COSTA C | 5535457 | DO 08 - Monthly Forecast Only | 263.000 | 263.000 | 08J | 2014 | 04/25/2020 | 2020 | 2228 | 318.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2017-10-31 | 2017-10-31 | COMP | 2017-07-31 | 2017-11-14 | COMP | 2017-11-14 | 2017-11-14 | COMP | 2017-11-14 | 2017-11-15 | COMP | 2017-11-15 | 2017-12-05 | COMP | 2017-12-05 | 2017-12-05 | 14 | 21 | 203552.21
31065400 | BH406 REPL.320FT OH LINE 5TH AVE RWC | 03/26/2014 | 107919207 | 03/26/2014 | # | Not assigned | 30 | Technically Completed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 01/30/2015 | ED.02416.0406.TXFR.TROH | OVERHEAD TRANSFORMERS | 041 | SAN MATEO COUN | 5517127 | DO 08 - Monthly Forecast Only | 367.000 | 510.000 | 08J | 2014 | # | OPEN | 2445 | 349.2857 | FICL | 10 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2020-05-29 | 2020-05-29 | COMP | 2020-08-19 | 2020-08-19 | COMP | 2020-08-19 | 2020-08-19 | COMP | 2020-08-19 | 2020-08-28 | COMP | 2020-08-28 | 2020-09-04 | COMP | 2020-09-04 | 2020-09-04 | 82 | 16 | 51985.15
31066170 | OCCCEP RECONDUCTOR MERIDIAN 1101 - Y2016 | 03/31/2014 | 107925832 | 03/31/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 05/06/2016 | ED.06254.1101.COND | CONDUCTOR | 051 | SUTTER COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 1,226.000 | 1,226.000 | 08J | 2014 | 02/18/2017 | 2017 | 1055 | 150.7143 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31066170_R4E EP RECONDUCTOR MERIDIAN 110 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-08-26 | 2016-08-15 | COMP | 2016-08-26 | 2016-09-06 | COMP | 2016-09-06 | 2016-09-06 | COMP | 2016-09-06 | 2016-09-15 | COMP | 2016-09-15 | 2017-01-17 | COMP | 2017-01-17 | 2017-01-21 | 11 | 137 | 221039.56
31066529 | OCGC CEDAR CRK 1101-RECOND 3528' Y2015 | 04/01/2014 | 107926906 | 03/31/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/31/2016 | ED.87-I402500000 | SHASTA MAP I4025 | 045 | SHASTA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 3,647.000 | 10,857.000 | 08W | 2014 | 12/16/2017 | 2017 | 1355 | 193.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31066529 Cedar Creek 1101 Rel/Rep 2400FT | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-10-24 | 2015-10-24 | COMP | 2015-11-06 | 2015-11-06 | COMP | 2015-11-24 | 2015-11-24 | COMP | 2015-11-24 | 2016-04-26 | COMP | 2016-04-26 | 2016-06-16 | COMP | 2016-06-16 | 2016-06-16 | 31 | 205 | 539968.45
31066739 | E RECONDUCOR PHASE7 GRAND ISLAND 222 | 04/03/2014 | 107929960 | 04/02/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 05/31/2018 | ED.06246.2227.RECL | RECLOSERS | 048 | SOLANO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 6,551.000 | 6,551.000 | 08J | 2014 | 04/20/2019 | 2019 | 1843 | 263.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31066739_RECOND PHASE7_GRAND ISLAND 222 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2017-08-08 | 2018-05-18 | COMP | 2018-06-07 | 2018-06-07 | COMP | 2018-06-07 | 2018-06-07 | COMP | 2018-06-07 | 2018-06-08 | COMP | 2018-06-08 | 2018-06-12 | COMP | 2018-06-12 | 2018-06-14 | 303 | 7 | 561842.28
31067120 | RECONDUCOR PHASE6 - GRAND ISLAND 222 | 04/03/2014 | 107929889 | 04/02/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/30/2017 | ED.06246.2227.RECL | RECLOSERS | 048 | SOLANO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 5,582.000 | 5,582.000 | 08J | 2014 | 09/22/2018 | 2018 | 1633 | 233.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31067120_ RECOND PHASE6 - GRAND ISLAND | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2017-07-28 | 2017-11-17 | COMP | 2017-12-21 | 2017-12-21 | COMP | 2017-12-21 | 2017-12-21 | COMP | 2017-12-21 | 2017-12-27 | COMP | 2017-12-27 | 2018-01-11 | COMP | 2018-01-11 | 2018-01-12 | 146 | 22 | 321506.14
31067121 | OCCCRECONDUCTOR GRAND ISLAND 2227 - PH 1 | 04/03/2014 | 107929809 | 04/02/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2015 | ED.06246.2227.RECL | RECLOSERS | 048 | SOLANO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 5,530.000 | 5,530.000 | 08J | 2014 | 11/18/2017 | 2017 | 1325 | 189.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31067121_Grand Island 2227_Ph1_08J | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-08-17 | 2016-08-17 | COMP | 2016-08-17 | 2016-09-01 | COMP | 2016-09-01 | 2016-09-01 | COMP | 2016-09-01 | 2016-09-10 | COMP | 2016-09-10 | 2017-01-24 | COMP | 2017-01-24 | 2017-02-02 | 15 | 154 | 323271.14
31067122 | RECONDUCOR PHASE4 - GRAND ISLAND 222 | 04/03/2014 | 107929886 | 04/02/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 08/30/2017 | ED.06246.2227.RECL | RECLOSERS | 048 | SOLANO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 5,797.000 | 5,800.000 | 08J | 2014 | 02/23/2019 | 2019 | 1787 | 255.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31067122_RECOND PHASE4_GRAND ISLAND 222 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2017-09-07 | 2017-08-16 | COMP | 2017-08-16 | 2017-09-07 | COMP | 2017-09-07 | 2017-09-07 | COMP | 2017-09-07 | 2017-09-08 | COMP | 2017-09-08 | 2017-11-15 | COMP | 2017-11-15 | 2017-12-05 | 0 | 89 | 436266.35
31067123 | E RECONDUCOR PHASE5 - GRAND ISLAND 222 | 04/03/2014 | 107929888 | 04/02/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/30/2017 | ED.06246.2227.RECL | RECLOSERS | 048 | SOLANO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 6,347.000 | 6,347.000 | 08J | 2014 | 05/04/2019 | 2019 | 1857 | 265.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31067123_RECOND PHASE5_GRAND ISLAND 222 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2017-09-28 | 2017-09-28 | COMP | 2017-11-15 | 2017-11-15 | COMP | 2017-11-15 | 2017-11-15 | COMP | 2017-11-15 | 2018-10-03 | COMP | 2018-10-03 | 2018-11-15 | COMP | 2018-11-15 | 2018-11-16 | 48 | 366 | 345025.71
31067124 | OCCCRECONDUCTOR GRAND ISLAND 2227 - PH 3 | 04/03/2014 | 107929883 | 04/02/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2015 | ED.06246.2227.RECL | RECLOSERS | 048 | SOLANO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 4,802.000 | 4,810.000 | 08J | 2014 | 11/18/2017 | 2017 | 1325 | 189.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31067124_Grand Island 2227_Ph3_08J | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-08-17 | 2016-08-17 | COMP | 2016-08-17 | 2016-09-01 | COMP | 2016-09-19 | 2016-09-19 | COMP | 2016-09-19 | 2016-09-28 | COMP | 2016-09-28 | 2017-01-26 | COMP | 2017-01-26 | 2017-02-13 | 33 | 147 | 234518.61
31067125 | OCCCRECONDUCTOR GRAND ISLAND 2227 - PH 2 | 04/03/2014 | 107929881 | 04/02/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2015 | ED.06246.2227.RECL | RECLOSERS | 048 | SOLANO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 5,014.000 | 5,014.000 | 08J | 2014 | 06/16/2018 | 2018 | 1535 | 219.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31067125_Grand Island 2227_08J#Phase 2 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-08-17 | 2016-08-17 | COMP | 2016-08-17 | 2016-09-01 | COMP | 2016-09-01 | 2016-09-01 | COMP | 2016-09-01 | 2016-09-10 | COMP | 2016-09-10 | 2017-01-19 | COMP | 2017-01-19 | 2017-01-28 | 15 | 149 | 282761.7
31067784 | OCGC XRECON 300' OF 4AR W/ 4/0A FORD ST | 04/07/2014 | 107931459 | 04/03/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/03/2016 | ED.08319.2102 | GREEN VALLEY 2102 | 044 | SANTA CRUZ COU | 5532479 | CWSP 08W - Monthly Forecast Only | 288.000 | 222.000 | 08W | 2014 | 06/13/2015 | 2015 | 432 | 61.7143 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2014-11-26 | 2015-03-15 | COMP | 2014-11-26 | 2015-04-02 | COMP | 2015-04-02 | 2015-04-02 | COMP | 2015-04-02 | 2015-04-18 | COMP | 2015-04-18 | 2015-05-04 | COMP | 2015-05-04 | 2015-05-04 | 127 | 32 | 37679.77
31067785 | OCCC N 400FT OF 6CU WITH 2CU-PORTOLA WA | 04/07/2014 | 107931581 | 04/03/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/24/2016 | ED.08888.0401 | LOMPICO STEP DOWN 0401 | 044 | SANTA CRUZ COU | 5535457 | DO 08 - Monthly Forecast Only | 396.000 | 0.000 | 08J | 2014 | 09/02/2017 | 2017 | 1244 | 177.7143 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-03-18 | 2016-03-18 | COMP | 2016-03-22 | 2016-03-24 | COMP | 2016-03-24 | 2016-03-24 | COMP | 2016-07-12 | 2017-07-06 | COMP | 2017-07-06 | 2017-07-07 | COMP | 2017-07-07 | 2017-07-08 | 6 | 471 | 53350.63
31068163 | OCCCRECONDUCTR HWY 65 OAKLEY LN | 04/08/2014 | 107937926 | 04/08/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2015 | ED.15290.1105.TXFR.TROH | OVERHEAD TRANSFORMERS | 058 | YUBA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 2,765.000 | 2,765.000 | 08J | 2014 | 07/29/2017 | 2017 | 1208 | 172.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31068163_Olivehurst 1105_Hwy 65/Oakley L | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-08-17 | 2016-08-17 | COMP | 2016-08-17 | 2016-08-25 | COMP | 2016-09-01 | 2016-09-01 | COMP | 2016-09-01 | 2016-09-10 | COMP | 2016-09-10 | 2016-12-02 | COMP | 2016-12-02 | 2016-12-02 | 15 | 92 | 211272.93
31068251 | 2016 EUREKA A 1107 EXCESSIVE SPLICES | 04/08/2014 | 107938198 | 04/08/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2016 | ED.19212.1107.SWIT | SWITCHES | 012 | HUMBOLDT COUNT | 5535457 | DO 08 - Monthly Forecast Only | 911.000 | 0.000 | 08J | 2014 | 12/01/2018 | 2018 | 1698 | 242.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-09-27 | 2016-09-27 | COMP | 2016-10-07 | 2016-10-07 | COMP | 2016-10-07 | 2016-10-07 | COMP | 2016-10-07 | 2016-10-11 | COMP | 2016-10-11 | 2017-01-19 | COMP | 2017-01-19 | 2017-01-27 | 10 | 112 | 199937.58
31068282 | REP OH DET WIRE TO C/O 1210_BW-2105 | 04/08/2014 | 107938667 | 04/08/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2015 | ED.01459.2105 | BRENTWOOD 2105 | 007 | CONTRA COSTA C | 5535457 | DO 08 - Monthly Forecast Only | 394.000 | 394.000 | 08J | 2014 | 10/28/2017 | 2017 | 1299 | 185.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-09-16 | 2016-10-09 | COMP | 2016-09-16 | 2016-10-25 | COMP | 2016-10-25 | 2016-10-25 | COMP | 2016-10-25 | 2016-10-28 | COMP | 2016-10-28 | 2017-01-19 | COMP | 2017-01-19 | 2017-01-27 | 39 | 94 | 85267.26
31068721 | OCCCRECONDUCTOR 200FT - WATSONVILLE 2101 | 04/11/2014 | 107948509 | 04/10/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/24/2016 | ED.08333.2101 | WATSONVILLE 2101 | 044 | SANTA CRUZ COU | 5535457 | DO 08 - Monthly Forecast Only | 251.000 | 0.000 | 08J | 2014 | 08/27/2016 | 2016 | 869 | 124.1429 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-03-10 | 2016-03-10 | COMP | 2016-03-15 | 2016-03-16 | COMP | 2016-03-16 | 2016-03-16 | COMP | 2016-03-16 | 2016-04-14 | COMP | 2016-04-14 | 2016-07-07 | COMP | 2016-07-07 | 2016-07-07 | 6 | 113 | 23058.68
31069365 | 2016 W FRSNO 1112 WIREDWN RECNDUCTOR | 04/15/2014 | 107950962 | 04/14/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/18/2016 | ED.25373.1112 | WEST FRESNO 1112 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 3,400.000 | 3,400.000 | 08J | 2014 | 07/20/2019 | 2019 | 1922 | 274.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31069365_R2 W FRESNO 1112 WIREDWN RECNDU | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-02-16 | 2016-02-16 | COMP | 2016-02-22 | 2016-02-22 | COMP | 2016-02-22 | 2016-02-22 | COMP | 2016-02-22 | 2016-05-05 | COMP | 2016-05-05 | 2016-08-08 | COMP | 2016-08-08 | 2016-08-15 | 6 | 175 | 219162.79
31069570 | X-SPENCE 1121 WIREDOWN 3779 | 04/16/2014 | 107954254 | 04/15/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/15/2016 | ED.18220.1121 | SPENCE 1121 | 027 | MONTEREY COUNT | 5532479 | CWSP 08W - Monthly Forecast Only | 1,356.000 | 1,356.000 | 08W | 2014 | 07/23/2016 | 2016 | 829 | 118.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-10-15 | 2015-12-08 | COMP | 2015-10-15 | 2015-12-09 | COMP | 2015-12-16 | 2015-12-16 | COMP | 2015-12-16 | 2016-04-13 | COMP | 2016-04-13 | 2016-06-16 | COMP | 2016-06-16 | 2016-06-16 | 62 | 183 | 52506.82
31069934 | OCGC 2016 LAMMERS 1107 RECON 4464' | 04/17/2014 | 107955758 | 04/16/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/26/2016 | ED.16277.1107 | LAMMERS 1107 | 039 | SAN JOAQUIN CO | 5535457 | DO 08 - Monthly Forecast Only | 4,754.000 | 4,754.000 | 08J | 2014 | 06/16/2018 | 2018 | 1521 | 217.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31069934_LAMMERS 1107 RECOND 4464' 6CU T | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-08-24 | 2016-09-28 | COMP | 2016-08-24 | 2016-10-04 | COMP | 2016-10-04 | 2016-10-04 | COMP | 2016-10-04 | 2016-10-11 | COMP | 2016-10-11 | 2017-01-18 | COMP | 2017-01-18 | 2017-01-28 | 41 | 116 | 241573.09
31069935 | OCGC CARBONA 1104 RECOND 3165' 6CU TO | 04/17/2014 | 107955825 | 04/16/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/02/2016 | ED.16309.1104 | CARBONA 1104 | 039 | SAN JOAQUIN CO | 5535457 | DO 08 - Monthly Forecast Only | 3,449.000 | 3,550.000 | 08J | 2014 | 11/18/2017 | 2017 | 1311 | 187.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | CARBONA 1104 RECOND 3165' 6CU TO 397AL | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-07-08 | 2016-07-08 | COMP | 2016-07-20 | 2016-07-20 | COMP | 2016-07-29 | 2016-07-29 | COMP | 2016-07-29 | 2016-08-19 | COMP | 2016-08-19 | 2016-11-16 | COMP | 2016-11-16 | 2016-11-16 | 21 | 110 | 223863.24
31069954 | OCGC RELIAIBLITY OAKLAND-REPL #6 CU-UWF | 04/17/2014 | 107954830 | 04/16/2014 | # | Not assigned | 40 | Closed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/30/2016 | ED.01254.1106 | OAKLAND X 1106 | 001 | ALAMEDA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 10,319.000 | 0.000 | 08J | 2014 | 12/09/2017 | 2017 | 1332 | 190.2857 | CLSD | 12 | E070 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31069954_R1-RELIAIBLITY OAKLAND-REPLACE | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-11-30 | 2016-11-30 | COMP | 2016-12-05 | 2016-12-05 | COMP | 2016-12-05 | 2016-12-05 | COMP | 2016-12-05 | 2016-12-09 | COMP | 2016-12-09 | 2017-02-15 | COMP | 2017-02-15 | 2017-02-16 | 5 | 73 | 875116.42
31069955 | RELIAIBLITY RICHMOND-REPL #6 CU-UWF | 04/17/2014 | 107954831 | 04/16/2014 | # | Not assigned | 40 | Closed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 08/31/2017 | ED.01250.1113 | EL CERRITO G 1113 | 001 | ALAMEDA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 4,070.000 | 4,030.000 | 08J | 2014 | 09/22/2018 | 2018 | 1619 | 231.2857 | CLSD | 12 | E070 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31069955_R1-RELIAIBLITY RICHMOND-REPL #6 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2018-01-08 | 2018-01-03 | COMP | 2017-06-19 | 2018-01-08 | COMP | 2018-01-08 | 2018-01-08 | COMP | 2018-01-08 | 2018-01-10 | COMP | 2018-01-10 | 2018-01-17 | COMP | 2018-01-17 | 2018-01-18 | 0 | 10 | 1045087.77
31070781 | FCM 1101 - OH RECNDUCTOR & COMBO C/O | 04/22/2014 | 107957443 | 04/17/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/01/2016 | ED.08387.1101.SWIT | SWITCHES | 043 | SANTA CLARA CO | 5535457 | DO 08 - Monthly Forecast Only | 817.000 | 0.000 | 08J | 2014 | 03/25/2017 | 2017 | 1068 | 152.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-09-09 | 2016-10-31 | COMP | 2016-09-09 | 2016-12-01 | COMP | 2016-12-01 | 2016-12-01 | COMP | 2016-12-01 | 2016-12-06 | COMP | 2016-12-06 | 2017-01-19 | COMP | 2017-01-19 | 2017-02-08 | 83 | 69 | 159324.48
31071248 | ORO FINO 1102 - 7700FT OF 4AR PHASE 2 | 04/24/2014 | 107962612 | 04/23/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/10/2017 | ED.17-Q330000000 | PARADISE MAP Q33 | 004 | BUTTE COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 7,049.000 | 7,049.000 | 08J | 2014 | 07/21/2018 | 2018 | 1549 | 221.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31071248_ORO FINO 1102 PH 2_08 Y2017 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2017-10-06 | 2017-11-14 | COMP | 2017-11-22 | 2017-11-27 | COMP | 2017-11-27 | 2017-11-27 | COMP | 2017-11-27 | 2017-11-30 | COMP | 2017-11-30 | 2017-12-12 | COMP | 2017-12-12 | 2017-12-14 | 52 | 17 | 934668.52
31071249 | *CANC* ORO FINO 1102 - 6500FT OF 4AR PH | 04/24/2014 | 107962614 | 04/23/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/31/2017 | ED.17-Q320000000 | PARADISE MAP Q32 | 004 | BUTTE COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2014 | 11/26/2016 | 2016 | 947 | 135.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2016-11-26 | 2016-11-26 | # | 2016-11-26 | 2016-11-26 | # | 2016-11-26 | 2016-11-26 | # | 2016-11-26 | 2016-11-26 | # | 2016-11-26 | 2016-11-26 | # | 2016-11-26 | 2016-11-26 | 0 | 0 | 0
31071455 | 2016 CALIF 1112 RECONDUCTOR WIREDOWN | 04/25/2014 | 107965661 | 04/25/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/25/2016 | ED.25228.1112 | CALIFORNIA AVE 1112 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 2,625.000 | 2,815.000 | 08J | 2014 | 12/17/2016 | 2016 | 967 | 138.1429 | PREC | 11 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31071455_R2 CALIF 1112 WIRE DOWN - PARAL | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-03-27 | 2016-03-27 | COMP | 2016-04-08 | 2016-04-08 | COMP | 2016-04-08 | 2016-04-08 | COMP | 2016-04-08 | 2016-05-18 | COMP | 2016-05-18 | 2016-08-25 | COMP | 2016-08-25 | 2016-08-25 | 12 | 139 | 282199.35
31071456 | 2016 W FRESNO 1112 WIRE DOWN-CRYSTAL | 04/25/2014 | 107965663 | 04/25/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/31/2017 | ED.25373.1112 | WEST FRESNO 1112 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 4,247.000 | 4,373.000 | 08J | 2014 | 01/28/2018 | 2018 | 1374 | 196.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31071456_W FRESNO 1112 WIRE DOWN-CRYSTAL | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-11-01 | 2017-03-31 | COMP | 2016-11-01 | 2017-04-12 | COMP | 2017-04-12 | 2017-04-12 | COMP | 2017-04-12 | 2017-04-13 | COMP | 2017-04-13 | 2017-05-02 | COMP | 2017-05-02 | 2017-05-10 | 162 | 28 | 426313.59
31071681 | OCGC 1105-JEFFREY PINE RECON 600' | 04/25/2014 | 107971152 | 04/25/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/01/2015 | ED.17-S350000000 | PARADISE MAP S35 | 004 | BUTTE COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 588.000 | 588.000 | 08W | 2014 | 03/19/2016 | 2016 | 694 | 99.1429 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-08-28 | 2015-08-28 | COMP | 2015-08-31 | 2015-08-31 | COMP | 2015-08-31 | 2015-09-02 | COMP | 2015-09-02 | 2016-02-18 | COMP | 2016-02-18 | 2016-02-18 | COMP | 2016-02-18 | 2016-02-24 | 5 | 175 | 72880.45
31071959 | *CANC* R4 MIDDLE RVR 1101 MAST CRO*CANC | 04/28/2014 | # | #N/A | 30979952 | OCGC MIDDLE RVR 1101 RECONDUCTORING | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | # | ED.16209.1101 | MIDDLE RIVER 1101 | 039 | SAN JOAQUIN CO | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2014 | 09/03/2015 | 2015 | 493 | 70.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Middle River 1101 Reconductor | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2015-09-03 | 2015-09-03 | # | 2015-09-03 | 2015-09-03 | # | 2015-09-03 | 2015-09-03 | COMP | 2015-08-17 | 2015-08-17 | COMP | 2015-08-17 | 2015-08-17 | COMP | 2015-08-17 | 2015-08-17 | 0 | -17 | 0
31071998 | OTTER 1102 WIRE DWN PT SUR LIGHTHOUSE | 04/28/2014 | 107975606 | 04/28/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 05/01/2015 | ED.18294.1102 | OTTER 1102 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 5,736.000 | 5,736.000 | 08J | 2014 | 10/28/2017 | 2017 | 1279 | 182.7143 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | R7OTTER 1102 WIRE DOWN PT SUR LIGHTHOUSE | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-02-11 | 2016-02-11 | COMP | 2016-02-17 | 2016-02-17 | COMP | 2016-02-17 | 2016-02-17 | COMP | 2016-02-17 | 2016-04-15 | COMP | 2016-04-15 | 2016-07-04 | COMP | 2016-07-04 | 2016-07-05 | 6 | 139 | 338455.07
31071999 | *CANC* REPLACE 1350' OF 4AR @ 51133 TAP | 04/28/2014 | 107975788 | 04/28/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/27/2016 | ED.18274.2102 | SAN BENITO 2102 | 035 | SAN BENITO COU | 5535457 | DO 08 - Monthly Forecast Only | 1,350.000 | 0.000 | 08J | 2014 | 11/17/2018 | 2018 | 1664 | 237.7143 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2018-11-17 | 2018-11-17 | # | 2018-11-17 | 2018-11-17 | # | 2018-11-17 | 2018-11-17 | # | 2018-11-17 | 2018-11-17 | # | 2018-11-17 | 2018-11-17 | # | 2018-11-17 | 2018-11-17 | 0 | 0 | 0
31072902 | SALINAS 1102 WIREDN RECONDUCTOR 2ND AV | 05/01/2014 | 107979024 | 04/30/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/29/2016 | ED.18201.1102 | SALINAS 1102 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 489.000 | 649.000 | 08J | 2014 | 07/29/2017 | 2017 | 1185 | 169.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-07-12 | 2016-07-24 | COMP | 2016-07-12 | 2016-08-08 | COMP | 2016-08-08 | 2016-08-08 | COMP | 2016-08-08 | 2016-08-29 | COMP | 2016-08-29 | 2016-11-16 | COMP | 2016-11-16 | 2016-11-16 | 27 | 100 | 64314.13
31072903 | XLOS OSITOS 2102 SPRECKELS RD WD RECON | 05/01/2014 | 107979246 | 04/30/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/27/2015 | ED.18208.2102 | LOS OSITOS 2102 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 483.000 | 0.000 | 08J | 2014 | 02/20/2016 | 2016 | 660 | 94.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-06-25 | 2015-07-06 | COMP | 2015-06-25 | 2015-07-07 | COMP | 2015-07-10 | 2015-07-10 | COMP | 2015-07-10 | 2015-09-11 | COMP | 2015-09-11 | 2016-02-01 | COMP | 2016-02-01 | 2016-02-02 | 15 | 207 | 16794.48
31073205 | *CANC* R6 BUENA VISTA 1102 WD RECO*CANC | 05/02/2014 | 107982363 | 05/01/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 05/01/2015 | ED.18226.1102 | BUENA VISTA 1102 | 027 | MONTEREY COUNT | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 2014 | 07/03/2015 | 2015 | 427 | 61 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2015-07-03 | 2015-07-03 | # | 2015-07-03 | 2015-07-03 | # | 2015-07-03 | 2015-07-03 | # | 2015-07-03 | 2015-07-03 | # | 2015-07-03 | 2015-07-03 | # | 2015-07-03 | 2015-07-03 | 0 | 0 | 0
31073706 | OCGC ECONDUCTR DAIRYLAND 1102-WIRE DOWN | 05/05/2014 | 107986655 | 05/02/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/30/2016 | ED.25242.1102 | DAIRYLAND 1102 | 020 | MADERA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 3,630.000 | 3,630.000 | 08J | 2014 | 03/18/2017 | 2017 | 1048 | 149.7143 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31073706_RECONDUCTR DAIRYLAND 1102-WIRE | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-11-09 | 2016-10-25 | COMP | 2016-11-09 | 2016-11-09 | COMP | 2016-11-09 | 2016-11-09 | COMP | 2016-11-09 | 2016-11-14 | COMP | 2016-11-14 | 2017-01-19 | COMP | 2017-01-19 | 2017-01-25 | 0 | 77 | 146362.79
31073707 | RECNDUCTR CHOWCHILA 1106-WIRE DOWN | 05/05/2014 | 107986657 | 05/02/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/30/2016 | ED.25410.1106 | CHOWCHILLA 1106 | 020 | MADERA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 7,311.000 | 2,285.000 | 08J | 2014 | 01/14/2017 | 2017 | 985 | 140.7143 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31073707_R2 RECNDUCTR CHOWCHILLA 1106-WI | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-08-13 | 2016-08-13 | COMP | 2016-08-16 | 2016-08-16 | COMP | 2016-08-16 | 2016-08-17 | COMP | 2016-08-17 | 2016-09-07 | COMP | 2016-09-07 | 2016-12-21 | COMP | 2016-12-21 | 2016-12-21 | 4 | 126 | 218142.75
31074033 | 2016 ASHLAN 2105 RECNDUCTOR WIREDOWN | 05/06/2014 | 107988278 | 05/05/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/26/2014 | ED.25205.2105 | ASHLAN AVE 2105 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 2,638.000 | 2,638.000 | 08J | 2014 | 10/19/2019 | 2019 | 1992 | 284.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31074033_R2 2016 ASHLAN 2105 RECONDUCTOR | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-08-05 | 2016-11-16 | COMP | 2016-08-05 | 2016-11-29 | COMP | 2016-11-29 | 2016-11-29 | COMP | 2016-11-29 | 2016-12-01 | COMP | 2016-12-01 | 2017-01-18 | COMP | 2017-01-18 | 2017-05-16 | 116 | 168 | 463284.58
31074240 | OCCC EUREKA CYN RECONDUCTOR - RR 2104 | 05/06/2014 | 107994037 | 05/06/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 05/06/2016 | ED.08369.2104 | ROB ROY 2104 | 044 | SANTA CRUZ COU | 5535457 | DO 08 - Monthly Forecast Only | 1,610.000 | 0.000 | 08J | 2014 | 09/02/2017 | 2017 | 1215 | 173.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-06-10 | 2016-06-17 | COMP | 2016-06-10 | 2016-06-22 | COMP | 2016-06-22 | 2016-06-22 | COMP | 2016-06-22 | 2016-08-15 | COMP | 2016-08-15 | 2016-11-15 | COMP | 2016-11-15 | 2016-11-15 | 12 | 146 | 173931.89
31074255 | RECON 400FT OF 4CU LOCKHRT GUL-CE 2104 | 05/06/2014 | 107994502 | 05/06/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 05/06/2016 | ED.08362.2104 | CAMP EVERS 2104 | 044 | SANTA CRUZ COU | 5535457 | DO 08 - Monthly Forecast Only | 415.000 | 500.000 | 08J | 2014 | 04/14/2018 | 2018 | 1439 | 205.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-06-21 | 2016-06-21 | COMP | 2016-06-27 | 2016-06-27 | COMP | 2016-06-27 | 2016-06-27 | COMP | 2016-06-27 | 2018-04-04 | COMP | 2018-04-04 | 2018-04-09 | COMP | 2018-04-09 | 2018-04-10 | 6 | 652 | 41948.76
31075442 | BORDEN 1103 RECONDUCTORING | 05/11/2014 | 108000066 | 05/09/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 05/01/2016 | ED.25280.1114 | MERCED 1114 | 024 | MERCED COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 2,080.000 | 2,080.000 | 08W | 2014 | 09/24/2016 | 2016 | 867 | 123.8571 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-04-04 | 2016-03-31 | COMP | 2016-04-04 | 2016-04-04 | COMP | 2016-04-04 | 2016-04-04 | COMP | 2016-04-04 | 2016-04-14 | COMP | 2016-04-14 | 2016-08-26 | COMP | 2016-08-26 | 2016-08-26 | 0 | 144 | 78861.96
31075747 | 2016 JANES CREEK 1101 EXCESSIVE SPLICES | 05/12/2014 | 107988583 | 05/05/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2016 | ED.19239.1101.SWIT | SWITCHES | 012 | HUMBOLDT COUNT | 5535457 | DO 08 - Monthly Forecast Only | 313.000 | 0.000 | 08J | 2014 | 01/28/2017 | 2017 | 992 | 141.7143 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-08-29 | 2016-09-13 | COMP | 2016-08-29 | 2016-09-20 | COMP | 2016-09-20 | 2016-09-20 | COMP | 2016-09-20 | 2016-09-28 | COMP | 2016-09-28 | 2016-12-22 | COMP | 2016-12-22 | 2016-12-22 | 22 | 93 | 47835.78
31076535 | OCGC MID. RIVR 1102 RECNDUCTR CO4875 ZO | 05/15/2014 | 108134782 | 05/13/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2016 | ED.16209.1102 | MIDDLE RIVER 1102 | 039 | SAN JOAQUIN CO | 5535457 | DO 08 - Monthly Forecast Only | 2,195.000 | 2,199.000 | 08J | 2014 | 07/20/2019 | 2019 | 1892 | 270.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | MIDDLE RIVER 1102 RECON 2370' OF 6CU | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-02-04 | 2016-02-04 | COMP | 2016-02-23 | 2016-02-23 | COMP | 2016-02-23 | 2016-02-23 | COMP | 2016-02-23 | 2016-04-15 | COMP | 2016-04-15 | 2016-08-04 | COMP | 2016-08-04 | 2016-08-04 | 19 | 163 | 143547.93
31076536 | OCGC MID. RIVR RECNDUCTR LR11476 ZONE | 05/15/2014 | 108134789 | 05/13/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2016 | ED.16209.1102 | MIDDLE RIVER 1102 | 039 | SAN JOAQUIN CO | 5535457 | DO 08 - Monthly Forecast Only | 1,696.000 | 1,700.000 | 08J | 2014 | 09/10/2016 | 2016 | 849 | 121.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | MIDDLE RIVER 1102 RECONDUCTOR | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-12-16 | 2015-12-16 | COMP | 2016-02-10 | 2016-02-22 | COMP | 2016-02-10 | 2016-02-10 | COMP | 2016-02-10 | 2016-04-12 | COMP | 2016-04-12 | 2016-07-01 | COMP | 2016-07-01 | 2016-07-07 | 56 | 148 | 102207.66
31076537 | OCGC EAST STOCKTON 402 RECONDUCTORING | 05/15/2014 | 108136334 | 05/14/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2016 | ED.16313.0402 | EAST STOCKTON 0402 | 039 | SAN JOAQUIN CO | 5535457 | DO 08 - Monthly Forecast Only | 5,665.000 | 5,665.000 | 08J | 2014 | 03/18/2017 | 2017 | 1038 | 148.2857 | PREC | 11 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | EAST STOCKTON 402 RECONDUCTORING | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-10-13 | 2016-10-13 | COMP | 2016-10-21 | 2016-10-21 | COMP | 2016-10-21 | 2016-10-21 | COMP | 2016-10-21 | 2016-10-26 | COMP | 2016-10-26 | 2017-02-22 | COMP | 2017-02-22 | 2017-02-22 | 8 | 124 | 403803.58
31076538 | OCGC AVENA 1701 RECONDUCTORING 2400' | 05/15/2014 | 108136463 | 05/14/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2016 | ED.16357.1701 | AVENA 1701 | 039 | SAN JOAQUIN CO | 5535457 | DO 08 - Monthly Forecast Only | 5,265.000 | 5,265.000 | 08J | 2014 | 12/16/2017 | 2017 | 1311 | 187.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31076538_AVENA 1701 RECONDUCTORING | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-08-25 | 2016-08-25 | COMP | 2016-09-09 | 2016-09-09 | COMP | 2016-09-09 | 2016-09-09 | COMP | 2016-09-09 | 2016-09-14 | COMP | 2016-09-14 | 2017-01-26 | COMP | 2017-01-26 | 2017-02-10 | 15 | 154 | 203384.06
31076768 | *RECONDUCTORING ON GREENBRAE 1102 | 05/16/2014 | 108137720 | 05/14/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/12/2014 | ED.04309.1102.SWIT | SWITCHES | 021 | MARIN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 266.000 | 266.000 | 08J | 2014 | 11/17/2018 | 2018 | 1646 | 235.1429 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-10-24 | 2016-10-24 | COMP | 2016-10-24 | 2016-10-24 | COMP | 2016-11-29 | 2016-11-29 | COMP | 2017-11-15 | 2018-11-13 | COMP | 2018-11-13 | 2018-11-13 | COMP | 2018-11-13 | 2018-11-13 | 36 | 714 | 88051.37
31076801 | OCCC*NAPA 1104 WIRE DOWN REC. | 05/16/2014 | 108144258 | 05/16/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/30/2016 | ED.04202.1104 | NAPA 1104 | 028 | NAPA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 738.000 | 738.000 | 08J | 2014 | 03/25/2017 | 2017 | 1044 | 149.1429 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-08-24 | 2016-12-04 | COMP | 2016-08-24 | 2016-12-19 | COMP | 2016-12-19 | 2016-12-19 | COMP | 2016-12-19 | 2016-12-23 | COMP | 2016-12-23 | 2017-01-18 | COMP | 2017-01-18 | 2017-01-18 | 117 | 30 | 130126.89
31078203 | RECONDUCTOR EL NIDO 1102 | 05/24/2014 | 108159424 | 05/23/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/29/2018 | ED.25245.1102 | EL NIDO 1102 | 024 | MERCED COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 1,501.000 | 1,501.000 | 08J | 2014 | 04/13/2019 | 2019 | 1785 | 255 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | R2 RECONDUCTOR EL NIDO 1102 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2018-04-20 | 2018-09-13 | COMP | 2018-09-20 | 2018-09-20 | COMP | 2018-09-20 | 2018-09-20 | COMP | 2018-09-20 | 2018-09-21 | COMP | 2018-09-21 | 2018-10-01 | COMP | 2018-10-01 | 2018-10-02 | 153 | 12 | 90522.52
31079018 | *CANC* BIG BEND 1102 - BLOOMER HIL *CANC | 05/28/2014 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 05/01/2016 | ED.85-CC29000000 | TEHEMA MAP CC29 | 052 | TEHAMA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2014 | 11/03/2019 | 2019 | 1985 | 283.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 2019-11-03 | 2019-11-03 | # | 2019-11-03 | 2019-11-03 | # | 2019-11-03 | 2019-11-03 | COMP | 2019-10-24 | 2019-10-24 | COMP | 2019-10-24 | 2019-10-24 | COMP | 2019-10-24 | 2019-10-24 | 0 | -10 | 0
31079172 | G1112 -RECOND 6 SPANS OF #4CU- | 05/29/2014 | 108163695 | 05/28/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/01/2016 | ED.28-C031400000.STRU.POLE | BAY C0314 POLES | 007 | CONTRA COSTA C | 5535457 | DO 08 - Monthly Forecast Only | 760.000 | 800.000 | 08J | 2014 | 06/16/2018 | 2018 | 1479 | 211.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-11-02 | 2017-06-07 | COMP | 2016-11-02 | 2017-07-18 | COMP | 2017-07-18 | 2017-07-18 | COMP | 2017-07-18 | 2017-07-19 | COMP | 2017-07-19 | 2017-08-01 | COMP | 2017-08-01 | 2017-08-03 | 258 | 16 | 191968.17
31079816 | TASSAJARA 2113 RECON (NORRIS CYN RD) | 06/03/2014 | 108171957 | 06/02/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/28/2015 | ED.01466.2113.TXFR.TROH | OVERHEAD TRANSFORMERS | 001 | ALAMEDA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 445.000 | 445.000 | 08J | 2014 | 06/16/2018 | 2018 | 1474 | 210.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-11-15 | 2016-11-15 | COMP | 2016-11-17 | 2016-11-17 | COMP | 2016-11-17 | 2016-11-17 | COMP | 2016-11-17 | 2016-11-22 | COMP | 2016-11-22 | 2017-01-20 | COMP | 2017-01-20 | 2017-01-20 | 2 | 64 | 34587.75
31080421 | 2016 CORCORAN 1106 RECONDUCTOR WD | 06/04/2014 | 108174368 | 06/03/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/01/2017 | ED.25217.1106 | CORCORAN 1106 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 7,095.000 | 7,105.000 | 08J | 2014 | 04/22/2017 | 2017 | 1053 | 150.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31080421_R2 2016 CORCORAN 1106 RECONDUCT | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-08-12 | 2016-11-08 | COMP | 2016-08-12 | 2016-11-29 | COMP | 2016-11-29 | 2016-11-29 | COMP | 2016-11-29 | 2016-12-01 | COMP | 2016-12-01 | 2017-02-07 | COMP | 2017-02-07 | 2017-02-08 | 109 | 71 | 486139.42
31080601 | RECON SPAN - BIG RIVER 1101 | 06/04/2014 | 108175487 | 06/04/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/05/2016 | ED.04308.1101.SWIT | SWITCHES | 023 | MENDOCINO COUN | 5535457 | DO 08 - Monthly Forecast Only | 222.000 | 222.000 | 08J | 2014 | 12/17/2016 | 2016 | 927 | 132.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-05-12 | 2016-06-28 | COMP | 2016-05-12 | 2016-06-29 | COMP | 2016-06-29 | 2016-06-29 | COMP | 2016-06-29 | 2016-08-17 | COMP | 2016-08-17 | 2016-11-08 | COMP | 2016-11-08 | 2016-11-08 | 48 | 132 | 18168.62
31080602 | RECON 1- SPAN GUALALA 1112 | 06/04/2014 | 108175860 | 06/04/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/07/2016 | ED.04284.1112.REGL | REGULATORS | 023 | MENDOCINO COUN | 5535457 | DO 08 - Monthly Forecast Only | 255.000 | 252.000 | 08J | 2014 | 11/19/2016 | 2016 | 899 | 128.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-05-16 | 2016-06-03 | COMP | 2016-05-16 | 2016-06-09 | COMP | 2016-06-09 | 2016-06-09 | COMP | 2016-06-09 | 2016-08-10 | COMP | 2016-08-10 | 2016-10-14 | COMP | 2016-10-14 | 2016-10-17 | 24 | 130 | 15989.91
31080688 | CAPITAN 1106-RECON 1,045' 6CU W/4/O | 06/05/2014 | 108176143 | 06/04/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 05/01/2016 | ED.25388.1106 | EL CAPITAN 1106 | 024 | MERCED COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 821.000 | 821.000 | 08J | 2014 | 02/23/2019 | 2019 | 1724 | 246.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2018-08-23 | 2018-09-24 | COMP | 2018-04-25 | 2018-10-17 | COMP | 2018-10-17 | 2018-10-17 | COMP | 2018-10-17 | 2018-10-18 | COMP | 2018-10-18 | 2018-10-19 | COMP | 2018-10-19 | 2018-10-22 | 55 | 5 | 103663.71
31081651 | +CAB 1103, E LAUREL, LOMPOC | 06/10/2014 | 108182253 | 06/09/2014 | # | Not assigned | 30 | Technically Completed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/30/2020 | ED.18310.1103 | CABRILLO 1103 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 1,389.000 | 1,389.000 | 08J | 2014 | # | OPEN | 2369 | 338.4286 | FICL | 10 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31081651_WD-RECON 1400' OF 397AL -CABRIL | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2017-09-18 | 2019-12-22 | COMP | 2017-10-04 | 2020-09-09 | COMP | 2020-09-09 | 2020-09-09 | COMP | 2020-09-09 | 2020-09-10 | COMP | 2020-09-10 | 2020-09-17 | COMP | 2020-09-17 | 2020-09-17 | 1087 | 8 | 599945.92
31081653 | REPL 815' CNDUCTOR AT 800 SALINAS RD | 06/10/2014 | 108182954 | 06/09/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/30/2016 | ED.18274.2101 | SAN BENITO 2101 | 035 | SAN BENITO COU | 5535457 | DO 08 - Monthly Forecast Only | 793.000 | 800.000 | 08J | 2014 | 05/13/2017 | 2017 | 1068 | 152.5714 | PREC | 11 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31081653_R2 REPL 815' CONDUCTOR AT 800 S | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-01-27 | 2016-01-27 | COMP | 2016-04-21 | 2016-04-22 | COMP | 2016-05-04 | 2016-05-04 | COMP | 2016-05-04 | 2016-05-14 | COMP | 2016-05-14 | 2016-05-14 | COMP | 2016-05-14 | 2016-05-14 | 98 | 10 | 92738.94
31081817 | RECONDUCTORING ON ALTO 1120 | 06/10/2014 | 108182494 | 06/09/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 02/06/2015 | ED.04203.1120.SWIT | SWITCHES | 021 | MARIN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 2,811.000 | 2,541.000 | 08J | 2014 | 05/30/2020 | 2020 | 2181 | 311.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2017-08-14 | 2017-08-14 | COMP | 2017-08-17 | 2017-08-17 | COMP | 2017-08-17 | 2017-08-17 | COMP | 2017-08-17 | 2020-03-15 | COMP | 2020-03-15 | 2020-03-26 | COMP | 2020-03-26 | 2020-03-26 | 3 | 952 | 290711.73
31081880 | NAPA 1112 WIRE DWN ML REC COOMBSVILLE RD | 06/10/2014 | 108190680 | 06/10/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 05/31/2017 | ED.04202.1112 | NAPA 1112 | 028 | NAPA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 7,747.000 | 7,747.000 | 08J | 2014 | 09/28/2019 | 2019 | 1936 | 276.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | NAPA 1112 WIRE DOWN MAIN LINE REC. | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-10-21 | 2017-04-21 | COMP | 2016-10-21 | 2017-05-18 | COMP | 2017-05-18 | 2017-05-18 | COMP | 2017-05-18 | 2017-05-24 | COMP | 2017-05-24 | 2017-07-13 | COMP | 2017-07-13 | 2017-07-13 | 209 | 56 | 1508573.88
31082152 | OCCC XRECNDUCTR 2900' HRD TAP GNZLS 1104 | 06/12/2014 | 108174138 | 06/03/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 07/03/2015 | ED.18213.1104 | GONZALES 1104 | 027 | MONTEREY COUNT | 5532479 | CWSP 08W - Monthly Forecast Only | 2,746.000 | 2,746.000 | 08W | 2014 | 07/23/2016 | 2016 | 772 | 110.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-12-14 | 2015-12-05 | COMP | 2015-12-14 | 2015-12-16 | COMP | 2015-12-16 | 2015-12-16 | COMP | 2015-12-16 | 2016-04-15 | COMP | 2016-04-15 | 2016-06-15 | COMP | 2016-06-15 | 2016-06-16 | 2 | 183 | 107419.95
31082220 | RECONDUCTOR ALTO 1125 MARIN-LIVE OAK MV | 06/12/2014 | 108193775 | 06/11/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 05/08/2015 | ED.04203.1125.SWIT | SWITCHES | 021 | MARIN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 649.000 | 659.000 | 08J | 2014 | 01/20/2018 | 2018 | 1318 | 188.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2017-08-04 | 2017-08-04 | COMP | 2017-08-28 | 2017-08-28 | COMP | 2017-08-28 | 2017-12-20 | COMP | 2017-12-20 | 2017-12-26 | COMP | 2017-12-26 | 2018-01-08 | COMP | 2018-01-08 | 2018-01-08 | 138 | 19 | 178530.76
31082390 | R7 RECON 12-SPAN GRATON RD W/RAILROAD AV | 06/12/2014 | 108194734 | 06/12/2014 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2016 | JY | JUNK YARD FL TO HOLD DELETED DATA | 049 | SONOMA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 1,865.000 | 1,835.000 | 08J | 2014 | # | OPEN | 2367 | 338.1429 | DOCC | 8 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31082390_Recond 12-Span Graton Rd | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2020-02-24 | 2020-04-24 | COMP | 2020-02-21 | 2020-08-03 | COMP | 2020-08-03 | 2020-08-03 | INPR | 2020-08-03 | 0 | # | 0 | 0 | # | 0 | 0 | 161 | -44046 | 508582.22
31082391 | RECON 4-SPANS SULLIVAN RD MOLINO 1102 | 06/12/2014 | 108194730 | 06/12/2014 | # | Not assigned | 30 | Technically Completed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2016 | ED.04257.1102.RECL | RECLOSERS | 049 | SONOMA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 730.000 | 1,059.000 | 08J | 2014 | # | OPEN | 2367 | 338.1429 | FICL | 10 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2017-10-10 | 2020-02-14 | COMP | 2018-07-12 | 2020-05-06 | COMP | 2020-05-06 | 2020-05-06 | COMP | 2020-05-06 | 2020-05-07 | COMP | 2020-05-07 | 2020-05-19 | COMP | 2020-05-19 | 2020-05-21 | 939 | 15 | 201626.22
31082393 | RECON THREE SPANS CHERRY RIDGE RD | 06/12/2014 | 108194639 | 06/12/2014 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2016 | ED.04257.1102.RECL | RECLOSERS | 049 | SONOMA COUNTY | 5535211 | CWSP SPO - SH 08 | 1,345.000 | 1,345.000 | 08W | 2014 | # | OPEN | 2367 | 338.1429 | DOCC | 8 | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2017-11-08 | 2019-08-06 | INPR | 2019-09-23 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | -43047 | 0 | 611813.45
31082394 | OCGC N SIX SPANS FRATI LN | 06/12/2014 | 108194636 | 06/12/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2016 | ED.04257.1102.SWIT | SWITCHES | 049 | SONOMA COUNTY | 5535211 | CWSP SPO - SH 08 | 1,486.000 | 1,486.000 | 08W | 2014 | 07/20/2019 | 2019 | 1864 | 266.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2017-11-13 | 2018-09-15 | COMP | 2018-09-24 | 2018-09-24 | COMP | 2018-09-24 | 2018-09-24 | COMP | 2018-09-24 | 2018-09-25 | COMP | 2018-09-25 | 2018-10-01 | COMP | 2018-10-01 | 2018-10-03 | 315 | 9 | 121250.38
31082395 | RECON TWO SPANS GRATON RD | 06/12/2014 | 108194634 | 06/12/2014 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2016 | ED.04257.1102.SWIT | SWITCHES | 049 | SONOMA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 754.000 | 0.000 | 08J | 2014 | # | OPEN | 2367 | 338.1429 | CONS | 7 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | INPR | 2017-10-02 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | -43010 | 0 | 16963.97
31082782 | +WD-RECON 4200' OF 6CU W 2CU-PERRY1101 | 06/16/2014 | 108195325 | 06/12/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/23/2016 | ED.18307.1101 | PERRY 1101 | 040 | SAN LUIS OBISP | 5535457 | DO 08 - Monthly Forecast Only | 5,046.000 | 4,200.000 | 08J | 2014 | 07/20/2019 | 2019 | 1860 | 265.7143 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | R5 WD-RECON 4200' OF 6CU W 2CU-PERRY1101 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-06-28 | 2016-12-21 | COMP | 2016-06-28 | 2017-01-03 | COMP | 2017-01-03 | 2017-01-03 | COMP | 2017-01-03 | 2017-01-05 | COMP | 2017-01-05 | 2017-02-16 | COMP | 2017-02-16 | 2017-02-16 | 189 | 44 | 364124.91
31083700 | OCCC 401 RECND 300FT OH LINE INST 1CO | 06/20/2014 | 108204496 | 06/19/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/20/2015 | ED.02403.0401.TXFR.TROH | OVERHEAD TRANSFORMERS | 041 | SAN MATEO COUN | 5505513 | PN-OH ANNEALED/DETER CNDCTR: PM MGD | 278.000 | 282.000 | 08J | 2014 | 05/13/2017 | 2017 | 1058 | 151.1429 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2017-01-27 | 2017-03-09 | COMP | 2017-01-27 | 2017-03-22 | COMP | 2017-03-22 | 2017-03-22 | COMP | 2017-03-22 | 2017-03-24 | COMP | 2017-03-24 | 2017-04-12 | COMP | 2017-04-12 | 2017-04-28 | 54 | 37 | 131038.19
31083701 | OCCC HMB-1103RECOND 400' OH PRI_INST C/O | 06/20/2014 | 108204497 | 06/19/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/16/2015 | ED.02410.1103.TXFR.TROH | OVERHEAD TRANSFORMERS | 041 | SAN MATEO COUN | 5535457 | DO 08 - Monthly Forecast Only | 273.000 | 0.000 | 08W | 2014 | 08/27/2016 | 2016 | 799 | 114.1429 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-06-13 | 2016-06-08 | COMP | 2016-06-13 | 2016-06-15 | COMP | 2016-06-15 | 2016-06-15 | COMP | 2016-06-15 | 2016-06-27 | COMP | 2016-06-27 | 2016-06-27 | COMP | 2016-06-27 | 2016-07-06 | 2 | 21 | 42079.75
31084072 | UCCOEP NAPA1112 WIRE DWN ADOBE LN RECOND | 06/23/2014 | 108205963 | 06/20/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2016 | ED.04202.1112 | NAPA 1112 | 028 | NAPA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 164.000 | 167.000 | 08J | 2014 | 06/17/2017 | 2017 | 1090 | 155.7143 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-12-19 | 2016-12-19 | COMP | 2016-12-19 | 2017-01-04 | COMP | 2017-01-04 | 2017-01-04 | COMP | 2017-01-04 | 2017-01-05 | COMP | 2017-01-05 | 2017-01-24 | COMP | 2017-01-24 | 2017-05-16 | 16 | 132 | 68869.67
31085776 | SANTA MARIA 1109 (HWY166/E/O BLACK RD) | 06/30/2014 | 108542812 | 06/27/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 08/26/2016 | ED.18267.1109 | SANTA MARIA 1109 | 042 | SANTA BARBARA | 5532479 | CWSP 08W - Monthly Forecast Only | 1,182.000 | 0.000 | 08W | 2014 | 10/28/2017 | 2017 | 1216 | 173.7143 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-12-10 | 2016-05-09 | COMP | 2015-12-10 | 2016-06-06 | COMP | 2016-06-06 | 2016-06-06 | COMP | 2016-06-06 | 2016-07-11 | COMP | 2016-07-11 | 2016-09-28 | COMP | 2016-09-28 | 2016-10-04 | 179 | 120 | 52585.81
31086638 | OCCC CABRILLO 1104 WIREDOWN 14-0036943 | 07/03/2014 | 108548136 | 07/01/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2017 | ED.18310.1104 | CABRILLO 1104 | 042 | SANTA BARBARA | 5532479 | CWSP 08W - Monthly Forecast Only | 1,268.000 | 1,268.000 | 08W | 2014 | 11/19/2016 | 2016 | 870 | 124.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31086638_R5 CABRILLO 1104 WIREDOWN 14-00 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-10-19 | 2015-10-19 | COMP | 2015-10-26 | 2015-10-30 | COMP | 2015-10-30 | 2015-10-30 | COMP | 2015-10-30 | 2016-09-22 | COMP | 2016-09-22 | 2016-09-27 | COMP | 2016-09-27 | 2016-09-27 | 11 | 333 | 114424.99
31086701 | +OCEANO 1102 WIREDOWN 14-0032745 | 07/03/2014 | 108547932 | 07/01/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2017 | ED.18260.1102 | OCEANO 1102 | 040 | SAN LUIS OBISP | 5535457 | DO 08 - Monthly Forecast Only | 622.000 | 922.000 | 08J | 2014 | 01/28/2017 | 2017 | 940 | 134.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-07-28 | 2016-08-19 | COMP | 2016-07-28 | 2016-08-22 | COMP | 2016-08-22 | 2016-08-25 | COMP | 2016-08-25 | 2016-09-10 | COMP | 2016-09-10 | 2016-12-09 | COMP | 2016-12-09 | 2016-12-09 | 28 | 106 | 38465.2
31086705 | +MORRO BAY 1101 (NAGANO RD) | 07/03/2014 | 108550033 | 07/02/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2017 | ED.18301.1101 | MORRO BAY 1101 | 040 | SAN LUIS OBISP | 5535457 | DO 08 - Monthly Forecast Only | 753.000 | 753.000 | 08J | 2014 | 11/19/2016 | 2016 | 870 | 124.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-05-16 | 2016-06-15 | COMP | 2016-05-16 | 2016-06-17 | COMP | 2016-06-17 | 2016-06-17 | COMP | 2016-06-17 | 2016-08-09 | COMP | 2016-08-09 | 2016-10-28 | COMP | 2016-10-28 | 2016-11-02 | 32 | 138 | 77535
31086824 | OC4 OCGC REPL DETERORATED 6C ON SUISUN 1 | 07/03/2014 | 108551868 | 07/03/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 07/03/2015 | ED.06213.1106.CAPA | CAPACITORS | 048 | SOLANO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 1,809.000 | 1,809.000 | 08J | 2014 | 07/02/2016 | 2016 | 730 | 104.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31086824_Suisun 1106 # Phase1_08E | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-10-23 | 2015-10-23 | COMP | 2015-11-03 | 2015-11-03 | COMP | 2015-11-05 | 2015-11-05 | COMP | 2015-11-05 | 2016-04-15 | COMP | 2016-04-15 | 2016-06-09 | COMP | 2016-06-09 | 2016-06-09 | 13 | 217 | 331940.81
31087570 | BIOLA 1104 WIREDOWN RECNDUCTOR | 07/09/2014 | 108554179 | 07/07/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/30/2016 | ED.25221.1104 | BIOLA 1104 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 482.000 | 482.000 | 08J | 2014 | 05/13/2017 | 2017 | 1039 | 148.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-06-03 | 2016-07-25 | COMP | 2016-06-03 | 2016-08-05 | COMP | 2016-08-05 | 2016-08-05 | COMP | 2016-08-05 | 2016-08-22 | COMP | 2016-08-22 | 2016-11-26 | COMP | 2016-11-26 | 2016-11-26 | 63 | 113 | 67222.26
31088838 | RECN 7047' CU W/#2 ACSR UWF AL 1105 | 07/14/2014 | 108568965 | 07/14/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/16/2017 | ED.01410.1105 | ALHAMBRA 1105 | 007 | CONTRA COSTA C | 5535457 | DO 08 - Monthly Forecast Only | 5,758.000 | 5,700.000 | 08J | 2014 | 04/25/2020 | 2020 | 2112 | 301.7143 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31088838_R4 RECON 7047' CU W/ #2 ACSR UW | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2017-02-01 | 2017-03-15 | COMP | 2017-02-01 | 2017-04-04 | COMP | 2017-04-04 | 2017-04-04 | COMP | 2017-04-04 | 2017-04-07 | COMP | 2017-04-07 | 2017-04-21 | COMP | 2017-04-21 | 2017-05-24 | 62 | 50 | 355681.3
31088894 | OCCC WIREDOWN RECONDUCTORING EG-401 | 07/18/2014 | 108566639 | 07/11/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/30/2015 | ED.02257.0401.TXFR.TROH | OVERHEAD TRANSFORMERS | 041 | SAN MATEO COUN | 5505513 | PN-OH ANNEALED/DETER CNDCTR: PM MGD | 122.000 | 0.000 | 08J | 2014 | 12/17/2016 | 2016 | 883 | 126.1429 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-09-29 | 2016-10-18 | COMP | 2016-09-29 | 2016-10-25 | COMP | 2016-10-25 | 2016-10-25 | COMP | 2016-10-25 | 2016-10-29 | COMP | 2016-10-29 | 2016-11-26 | COMP | 2016-11-26 | 2016-11-28 | 26 | 34 | 57620.82
31089263 | MOVE FUSE 1179/RECON WITH TREE WIRE | 07/16/2014 | 108573135 | 07/16/2014 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/30/2016 | ED.01467.1102 | SOBRANTE 1102 | 007 | CONTRA COSTA C | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2014 | # | OPEN | 2333 | 333.2857 | UNSE | 1 | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 10979.62
31089385 | *CANC* R5WD REPL 1 SPAN WITH 4/0AL*CANC | 07/17/2014 | 108574013 | 07/16/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 08/26/2016 | ED.18206.1108 | FAIRWAY 1108 | 042 | SANTA BARBARA | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 2014 | 01/05/2015 | 2015 | 172 | 24.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2015-01-05 | 2015-01-05 | # | 2015-01-05 | 2015-01-05 | # | 2015-01-05 | 2015-01-05 | # | 2015-01-05 | 2015-01-05 | # | 2015-01-05 | 2015-01-05 | # | 2015-01-05 | 2015-01-05 | 0 | 0 | 0
31090652 | SUISUN 1106 RECONDUCTOR - PH 2 | 07/23/2014 | 108582628 | 07/23/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/25/2016 | ED.06213.1106.CAPA | CAPACITORS | 048 | SOLANO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 2,761.000 | 2,750.000 | 08J | 2014 | 03/07/2020 | 2020 | 2054 | 293.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31090652_Suisun 1106 # Phase 2._08E | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-10-21 | 2017-03-15 | COMP | 2016-10-21 | 2017-03-23 | COMP | 2017-03-23 | 2017-03-23 | COMP | 2017-03-23 | 2017-03-28 | COMP | 2017-03-28 | 2017-04-10 | COMP | 2017-04-10 | 2017-04-20 | 153 | 28 | 340161.13
31091401 | MCCALL 1106_WIREDOWN_RECOND 608' | 07/27/2014 | 108584296 | 07/24/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/28/2017 | ED.25412.1106 | MC CALL 1106 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 916.000 | 916.000 | 08J | 2014 | 04/22/2017 | 2017 | 1000 | 142.8571 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-10-03 | 2016-12-13 | COMP | 2016-10-03 | 2017-01-03 | COMP | 2017-01-03 | 2017-01-03 | COMP | 2017-01-03 | 2017-01-05 | COMP | 2017-01-05 | 2017-01-24 | COMP | 2017-01-24 | 2017-02-01 | 92 | 29 | 95064.62
31091502 | RECON 3 SPANS END OF BIAGGI LN | 07/28/2014 | 108584245 | 07/24/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 05/31/2017 | ED.04298.1101.SWIT | SWITCHES | 023 | MENDOCINO COUN | 5535457 | DO 08 - Monthly Forecast Only | 1,720.000 | 0.000 | 08J | 2014 | 07/14/2018 | 2018 | 1447 | 206.7143 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-11-11 | 2016-11-11 | COMP | 2016-11-15 | 2016-11-15 | COMP | 2016-11-21 | 2016-11-21 | COMP | 2017-02-13 | 2017-09-20 | COMP | 2017-09-20 | 2017-12-05 | COMP | 2017-12-05 | 2017-12-05 | 10 | 379 | 99958.64
31091813 | OC4 OCGC2015 RECNDUCTR RM 1104 OUTLET 19 | 07/29/2014 | 108588666 | 07/29/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/27/2015 | ED.01416.1104 | ROSSMOOR 1104 | 007 | CONTRA COSTA C | 5535457 | DO 08 - Monthly Forecast Only | 2,107.000 | 2,107.000 | 08J | 2014 | 07/04/2015 | 2015 | 340 | 48.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-05-22 | 2015-05-22 | COMP | 2015-05-28 | 2015-06-01 | COMP | 2015-06-04 | 2015-06-04 | COMP | 2015-06-04 | 2015-06-05 | COMP | 2015-06-05 | 2015-06-09 | COMP | 2015-06-09 | 2015-06-09 | 13 | 5 | 188474.04
31092109 | SAN RAFAEL 1107 DETER COND GOODHILL RD | 07/30/2014 | 108590694 | 07/29/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 05/11/2017 | ED.04201.1107.SWIT | SWITCHES | 021 | MARIN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 6,635.000 | 5,980.000 | 08J | 2014 | 09/12/2020 | 2020 | 2236 | 319.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31092109_R4SAN RAFAEL 1107 DETER COND GO | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-11-29 | 2017-06-30 | COMP | 2016-11-29 | 2017-08-03 | COMP | 2017-08-03 | 2017-12-20 | COMP | 2018-09-13 | 2020-08-12 | COMP | 2020-08-12 | 2020-08-14 | COMP | 2020-08-14 | 2020-08-14 | 386 | 968 | 1056847.65
31092113 | OCCCSN RAFAEL1109 DETER COND JEWELL/HIGH | 07/30/2014 | 108590869 | 07/30/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2016 | ED.04201.1109.SWIT | SWITCHES | 021 | MARIN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 1,935.000 | 2,095.000 | 08J | 2014 | 12/17/2016 | 2016 | 871 | 124.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | R7SAN RAFAEL 1109 DETER COND JEWELL/HIGH | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-05-26 | 2016-05-26 | COMP | 2016-05-31 | 2016-06-09 | COMP | 2016-06-09 | 2016-06-09 | COMP | 2016-06-09 | 2016-07-25 | COMP | 2016-07-25 | 2016-10-11 | COMP | 2016-10-11 | 2016-10-11 | 14 | 124 | 287860.54
31092114 | OCGC RAFAEL 1106 DETER COND CHULA VISTA | 07/30/2014 | 108591540 | 07/30/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 07/31/2017 | ED.04201.1106.SWIT | SWITCHES | 021 | MARIN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 4,705.000 | 4,705.000 | 08J | 2014 | 02/08/2020 | 2020 | 2019 | 288.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | R7SAN RAFAEL 1106 DETER COND CHULA VISTA | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-10-11 | 2017-08-03 | COMP | 2016-10-11 | 2017-08-08 | COMP | 2017-08-08 | 2017-08-08 | COMP | 2017-08-08 | 2017-08-09 | COMP | 2017-08-09 | 2017-08-24 | COMP | 2017-08-24 | 2017-09-01 | 301 | 24 | 569532.55
31092115 | OCGC SAN RAFAEL 1108 DETER COND GLENWD | 07/30/2014 | 108591541 | 07/30/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 07/31/2017 | ED.04201.1108.SWIT | SWITCHES | 021 | MARIN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 2,400.000 | 2,600.000 | 08J | 2014 | 02/10/2018 | 2018 | 1291 | 184.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | R7SAN RAFAEL 1108 DETER COND GLENWOOD AV | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2017-07-27 | 2017-07-27 | COMP | 2017-07-27 | 2017-07-27 | COMP | 2017-07-27 | 2017-07-27 | COMP | 2017-07-27 | 2017-07-28 | COMP | 2017-07-28 | 2017-08-17 | COMP | 2017-08-17 | 2017-08-21 | 0 | 25 | 335364.65
31092222 | +WD REPL 2 SPANS WITH 2CU -MESA 1102 | 07/31/2014 | 108592290 | 07/30/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 08/26/2016 | ED.18282.1102 | MESA 1102 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 361.000 | 361.000 | 08J | 2014 | 01/28/2017 | 2017 | 912 | 130.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-08-24 | 2016-08-24 | COMP | 2016-08-24 | 2016-08-24 | COMP | 2016-08-24 | 2016-08-29 | COMP | 2016-08-29 | 2016-09-12 | COMP | 2016-09-12 | 2016-12-27 | COMP | 2016-12-27 | 2016-12-27 | 5 | 120 | 28747.58
31092787 | OCGCELIAIBLTY R1129-RECONDUCTR #6CU | 08/04/2014 | 108596022 | 08/01/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/31/2016 | ED.01347.1129 | RICHMOND R 1129 | 007 | CONTRA COSTA C | 5517127 | DO 08 - Monthly Forecast Only | 529.000 | 1,587.000 | 08J | 2014 | 08/18/2018 | 2018 | 1475 | 210.7143 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2017-10-06 | 2018-07-13 | COMP | 2018-07-16 | 2018-07-16 | COMP | 2018-07-16 | 2018-07-16 | COMP | 2018-07-16 | 2018-07-17 | COMP | 2018-07-17 | 2018-07-25 | COMP | 2018-07-25 | 2018-07-27 | 283 | 11 | 62721.45
31092788 | EB-RELIAIBLITY D1102-REPLACE #6CU | 08/04/2014 | 108595973 | 08/01/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/31/2016 | ED.01204.1102 | OAKLAND D 1102 | 001 | ALAMEDA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 275.000 | 270.000 | 08J | 2014 | 02/23/2019 | 2019 | 1664 | 237.7143 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2017-11-27 | 2018-09-08 | COMP | 2018-07-13 | 2018-10-03 | COMP | 2018-10-03 | 2018-10-03 | COMP | 2018-10-03 | 2018-10-04 | COMP | 2018-10-04 | 2018-10-08 | COMP | 2018-10-08 | 2018-10-09 | 310 | 6 | 52550.61
31092865 | OH WIREDOWN REPLACEMENT CV1104 | 08/04/2014 | 108842903 | 08/04/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2017 | ED.24-I100800000.STRU.ENCL | MISSION I1008 ENCLOSURE | 001 | ALAMEDA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 933.000 | 933.000 | 08J | 2014 | 11/18/2017 | 2017 | 1202 | 171.7143 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-10-18 | 2016-11-08 | COMP | 2016-10-18 | 2016-11-09 | COMP | 2016-11-10 | 2016-11-10 | COMP | 2016-11-10 | 2016-11-15 | COMP | 2016-11-15 | 2017-01-19 | COMP | 2017-01-19 | 2017-01-20 | 23 | 71 | 51022.83
31093044 | RECN #4AR W/ #2ACSR SSD 52485 ML2103 | 08/05/2014 | 108843559 | 08/04/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/01/2016 | ED.01430.2103 | MEADOW LANE 2103 | 007 | CONTRA COSTA C | 5535457 | DO 08 - Monthly Forecast Only | 463.000 | 463.000 | 08J | 2014 | 06/17/2018 | 2018 | 1412 | 201.7143 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-07-26 | 2016-07-26 | COMP | 2016-07-27 | 2016-07-27 | COMP | 2016-07-27 | 2016-07-27 | COMP | 2016-07-27 | 2016-08-26 | COMP | 2016-08-26 | 2016-11-16 | COMP | 2016-11-16 | 2016-11-16 | 1 | 112 | 28179.43
31093073 | XSHELL RD, REPL 450' 6CU OH CONDUCTOR | 08/05/2014 | 108843185 | 08/04/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/01/2015 | ED.08319.2103 | GREEN VALLEY 2103 | 044 | SANTA CRUZ COU | 5532479 | CWSP 08W - Monthly Forecast Only | 431.000 | 431.000 | 08W | 2014 | 07/23/2016 | 2016 | 718 | 102.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-10-23 | 2015-10-23 | COMP | 2015-10-26 | 2015-10-26 | COMP | 2015-10-26 | 2015-10-26 | COMP | 2015-10-26 | 2016-04-16 | COMP | 2016-04-16 | 2016-06-06 | COMP | 2016-06-06 | 2016-06-06 | 3 | 224 | 33388.02
31093074 | +SM 1109 RECON (HWY 166 / E/O SIMAS RD) | 08/05/2014 | 108842843 | 08/04/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 08/28/2015 | ED.18267.1109 | SANTA MARIA 1109 | 042 | SANTA BARBARA | 5532479 | CWSP 08W - Monthly Forecast Only | 671.000 | 0.000 | 08W | 2014 | 12/17/2016 | 2016 | 865 | 123.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-12-09 | 2016-06-03 | COMP | 2015-12-09 | 2016-06-14 | COMP | 2016-06-14 | 2016-06-14 | COMP | 2016-06-14 | 2016-08-01 | COMP | 2016-08-01 | 2016-10-24 | COMP | 2016-10-24 | 2016-11-15 | 188 | 154 | 34755.06
31093779 | MABURY 1104 WIRE DOWN 14-0043849 | 08/08/2014 | 108849330 | 08/07/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/01/2016 | ED.08219.1104.TXFR.TROH | OVERHEAD TRANSFORMERS | 043 | SANTA CLARA CO | 5532479 | CWSP 08W - Monthly Forecast Only | 371.000 | 0.000 | 08W | 2014 | 08/27/2016 | 2016 | 750 | 107.1429 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-12-30 | 2016-01-10 | COMP | 2015-12-30 | 2016-01-21 | COMP | 2016-01-21 | 2016-01-21 | COMP | 2016-01-21 | 2016-05-02 | COMP | 2016-05-02 | 2016-07-09 | COMP | 2016-07-09 | 2016-07-12 | 22 | 173 | 84221.13
31093840 | MESA 1102 (DIVISION @ OSO FLACO LAKE) | 08/08/2014 | 108849391 | 08/07/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/30/2016 | ED.18282.1102 | MESA 1102 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 6,822.000 | 6,822.000 | 08J | 2014 | 02/11/2017 | 2017 | 918 | 131.1429 | PREC | 11 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31093840_SBWF ACSR REPL FUSE 11181 & 457 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-06-14 | 2016-07-28 | COMP | 2016-06-14 | 2016-08-05 | COMP | 2016-08-05 | 2016-08-24 | COMP | 2016-08-24 | 2016-08-31 | COMP | 2016-08-31 | 2017-01-19 | COMP | 2017-01-19 | 2017-02-06 | 71 | 166 | 262900.2
31094451 | +SBWF ACSR REPL (BONITA SCHOOL RD) | 08/12/2014 | 108859141 | 08/11/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/30/2016 | ED.18282.1102 | MESA 1102 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 7,054.000 | 5,547.000 | 08J | 2014 | 11/19/2016 | 2016 | 830 | 118.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | R5 SBWF ACSR REPLACEMENT LR M24 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-05-19 | 2016-07-05 | COMP | 2016-05-19 | 2016-07-07 | COMP | 2016-07-07 | 2016-07-07 | COMP | 2016-07-07 | 2016-08-18 | COMP | 2016-08-18 | 2016-11-03 | COMP | 2016-11-03 | 2016-11-03 | 49 | 119 | 213506.73
31094681 | SALINAS 1109 WIREDOWN FCO23279 | 08/13/2014 | 108862554 | 08/12/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 08/14/2015 | ED.18201.1109 | SALINAS 1109 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 3,085.000 | 3,085.000 | 08J | 2014 | 07/29/2017 | 2017 | 1081 | 154.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31094681_R2 SALINAS 1109 WIREDOWN FCO232 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-07-26 | 2016-08-26 | COMP | 2016-07-26 | 2016-08-30 | COMP | 2016-08-30 | 2016-08-30 | COMP | 2016-08-30 | 2016-09-14 | COMP | 2016-09-14 | 2017-01-19 | COMP | 2017-01-19 | 2017-02-13 | 35 | 167 | 130682.89
31094780 | OH WIRE DOWN REPLACEMENT ME1110 | 08/13/2014 | 108863130 | 08/13/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2017 | ED.24-J082500000.STRU.ENCL | MISSION J0825 ENCLOSURE | 001 | ALAMEDA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 414.000 | 0.000 | 08W | 2014 | 09/21/2019 | 2019 | 1865 | 266.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-07-12 | 2016-08-06 | COMP | 2016-07-12 | 2016-08-12 | COMP | 2016-08-12 | 2016-08-12 | COMP | 2016-08-12 | 2016-09-09 | COMP | 2016-09-09 | 2017-01-17 | COMP | 2017-01-17 | 2017-01-23 | 31 | 164 | 54068.64
31095026 | REPOH DET WIRE SNSET & EDEN PLAINS | 08/14/2014 | 108864142 | 08/13/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/31/2016 | ED.01432.1101 | BALFOUR 1101 | 007 | CONTRA COSTA C | 5535457 | DO 08 - Monthly Forecast Only | 1,002.000 | 0.000 | 08J | 2014 | 02/23/2019 | 2019 | 1654 | 236.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-08-15 | 2016-08-11 | COMP | 2016-08-15 | 2016-09-01 | COMP | 2016-09-01 | 2016-09-01 | COMP | 2016-09-01 | 2016-09-10 | COMP | 2016-09-10 | 2016-12-05 | COMP | 2016-12-05 | 2016-12-05 | 17 | 95 | 23235.73
31095523 | OCGCELIAIBLITY -K1103, REPL #4ACSR W | 08/19/2014 | 108871964 | 08/18/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/31/2017 | ED.01210.1103 | OAKLAND K 1103 | 001 | ALAMEDA COUNTY | 5535211 | CWSP SPO - SH 08 | 1,800.000 | 1,838.000 | 08W | 2014 | 04/25/2020 | 2020 | 2076 | 296.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2018-06-04 | 2018-06-04 | COMP | 2018-06-07 | 2018-06-07 | COMP | 2018-06-07 | 2018-06-07 | COMP | 2018-06-07 | 2018-06-08 | COMP | 2018-06-08 | 2018-06-27 | COMP | 2018-06-27 | 2018-07-03 | 3 | 26 | 282571.51
31095687 | MANCHESTER 1110 - RECONDUCTOR TAP | 08/19/2014 | 108872542 | 08/18/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/30/2016 | ED.25392.1110 | MANCHESTER 1110 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 604.000 | 604.000 | 08J | 2014 | 07/29/2017 | 2017 | 1075 | 153.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-07-08 | 2016-07-22 | COMP | 2016-07-08 | 2016-08-09 | COMP | 2016-08-09 | 2016-08-09 | COMP | 2016-08-09 | 2016-08-25 | COMP | 2016-08-25 | 2016-11-28 | COMP | 2016-11-28 | 2016-11-28 | 32 | 111 | 113209.65
31096169 | OCGC TRACY 1106 RECOND 2157FT 6CU TO | 08/21/2014 | 108875429 | 08/20/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/29/2017 | ED.16288.1106 | TRACY 1106 | 039 | SAN JOAQUIN CO | 5535457 | DO 08 - Monthly Forecast Only | 2,152.000 | 2,152.000 | 08J | 2014 | 07/22/2017 | 2017 | 1066 | 152.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | TRACY 1106 RECOND 2157FT 6CU TO 2AR | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-09-22 | 2016-09-22 | COMP | 2016-09-27 | 2016-09-27 | COMP | 2016-09-27 | 2016-09-27 | COMP | 2016-09-27 | 2016-10-05 | COMP | 2016-10-05 | 2017-01-19 | COMP | 2017-01-19 | 2017-02-06 | 5 | 132 | 67326.96
31097449 | XPRUNEDALE 1107 WD C/O 4485 | 08/27/2014 | 108881498 | 08/25/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/04/2015 | ED.18296.1107 | PRUNEDALE 1107 | 027 | MONTEREY COUNT | 5532479 | CWSP 08W - Monthly Forecast Only | 299.000 | 0.000 | 08W | 2014 | 10/28/2017 | 2017 | 1158 | 165.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-09-18 | 2015-10-20 | COMP | 2015-09-18 | 2015-11-06 | COMP | 2015-11-06 | 2015-11-06 | INPR | 2015-11-06 | 2016-03-19 | # | 2016-03-19 | 2016-03-19 | # | 2016-03-19 | 2016-03-19 | 49 | 134 | 38548.72
31097452 | XCAMPHORA 1101 WD FCO 7091 | 08/27/2014 | 108881732 | 08/25/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/18/2015 | ED.18207.1101 | CAMPHORA 1101 | 027 | MONTEREY COUNT | 5532479 | CWSP 08W - Monthly Forecast Only | 612.000 | 612.000 | 08W | 2014 | 07/23/2016 | 2016 | 696 | 99.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-10-14 | 2015-12-17 | COMP | 2015-10-14 | 2015-12-21 | COMP | 2015-12-21 | 2015-12-21 | COMP | 2015-12-21 | 2016-04-12 | COMP | 2016-04-12 | 2016-06-17 | COMP | 2016-06-17 | 2016-06-17 | 68 | 179 | 41787.29
31097541 | MNLO 1102_RECNDUCTR_REFRAME PLES | 08/27/2014 | 108885833 | 08/27/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/19/2015 | ED.02413.1102.RECL | RECLOSERS | 041 | SAN MATEO COUN | 5505513 | PN-OH ANNEALED/DETER CNDCTR: PM MGD | 5,019.000 | 0.000 | 08J | 2014 | 12/17/2016 | 2016 | 843 | 120.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31097541_PN MENLO1102 REPL./REFRAME POLE | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-05-06 | 2016-06-08 | COMP | 2016-05-06 | 2016-06-14 | COMP | 2016-06-14 | 2016-06-14 | COMP | 2016-06-14 | 2016-06-27 | COMP | 2016-06-27 | 2016-07-07 | COMP | 2016-07-07 | 2016-07-07 | 39 | 23 | 343943.38
31098259 | OCCC SALINAS 1106 WIRE DOWN FCO56459 | 09/02/2014 | 108887306 | 08/28/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 05/29/2015 | ED.18201.1106 | SALINAS 1106 | 027 | MONTEREY COUNT | 5532479 | CWSP 08W - Monthly Forecast Only | 1,101.000 | 1,101.000 | 08W | 2014 | 07/23/2016 | 2016 | 690 | 98.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-11-19 | 2015-11-15 | COMP | 2015-11-19 | 2015-11-23 | COMP | 2015-11-23 | 2015-11-23 | COMP | 2015-11-23 | 2016-04-13 | COMP | 2016-04-13 | 2016-06-15 | COMP | 2016-06-15 | 2016-06-16 | 4 | 206 | 74307.63
31098360 | OCCC XGONZALES 1104 WIRE DOWN FCO 5005 | 09/02/2014 | 108887342 | 08/28/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/30/2015 | ED.18213.1104 | GONZALES 1104 | 027 | MONTEREY COUNT | 5532479 | CWSP 08W - Monthly Forecast Only | 2,215.000 | 2,215.000 | 08W | 2014 | 07/23/2016 | 2016 | 690 | 98.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-11-19 | 2015-11-13 | COMP | 2015-11-19 | 2015-11-23 | COMP | 2015-11-23 | 2015-11-23 | COMP | 2015-11-23 | 2016-04-14 | COMP | 2016-04-14 | 2016-06-20 | COMP | 2016-06-20 | 2016-06-20 | 4 | 210 | 99643.81
31098474 | OCCC WIREDOWN RECONDUCTORING EG-1107 | 09/05/2014 | 108889644 | 08/29/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/30/2015 | ED.56-E041800000 | SKYLINE MAP E0418 | 041 | SAN MATEO COUN | 5505513 | PN-OH ANNEALED/DETER CNDCTR: PM MGD | 331.000 | 0.000 | 08J | 2014 | 07/22/2017 | 2017 | 1051 | 150.1429 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-12-20 | 2016-12-20 | COMP | 2016-12-21 | 2016-12-22 | COMP | 2016-12-22 | 2016-12-22 | COMP | 2016-12-22 | 2016-12-28 | COMP | 2016-12-28 | 2017-01-30 | COMP | 2017-01-30 | 2017-01-31 | 2 | 40 | 76800.92
31098498 | CLARKSVILLE 2104 RECON - PH 2 Y2017 | 09/02/2014 | 108895129 | 09/02/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/29/2018 | ED.15361.2104.SWIT | SWITCHES | 009 | EL DORADO COUN | 5535457 | DO 08 - Monthly Forecast Only | 3,276.000 | 3,083.000 | 08J | 2014 | 02/23/2019 | 2019 | 1635 | 233.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31098498_CLARKSVILLE 2104 RECOND - PH 2 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2017-07-28 | 2018-05-30 | COMP | 2018-06-05 | 2018-06-05 | COMP | 2018-06-05 | 2018-06-05 | COMP | 2018-06-05 | 2018-06-06 | COMP | 2018-06-06 | 2018-06-27 | COMP | 2018-06-27 | 2018-06-28 | 312 | 23 | 253229.54
31098626 | CLARKSVILLE 2104 RECONDUCTOR -PH 3 Y2018 | 09/03/2014 | 108895192 | 09/02/2014 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2018 | ED.15361.2104.SWIT | SWITCHES | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 8,052.000 | 8,052.000 | 08W | 2014 | # | OPEN | 2284 | 326.2857 | MAPP | 9 | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | 31098626_CLARKSVILLE 2104 RECOND - PH 3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2018-06-27 | 2020-11-10 | COMP | 2020-11-20 | 2020-11-20 | COMP | 2020-11-20 | 2020-11-20 | COMP | 2020-11-20 | 2020-11-23 | INPR | 2020-11-23 | 0 | # | 0 | 0 | 877 | -44155 | 1036604.98
31098634 | +MESA 1102 WIREDOWN (OSO FLACO TAP) | 09/03/2014 | 108894937 | 09/02/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2015 | ED.18282.1102 | MESA 1102 | 040 | SAN LUIS OBISP | 5532479 | CWSP 08W - Monthly Forecast Only | 2,209.000 | 0.000 | 08W | 2014 | 06/18/2016 | 2016 | 654 | 93.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31098634_R2 MESA 1102 WIREDOWN 14-003274 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-09-03 | 2015-10-30 | COMP | 2015-09-03 | 2015-11-06 | COMP | 2015-11-06 | 2015-11-16 | COMP | 2015-11-16 | 2016-04-13 | COMP | 2016-04-13 | 2016-05-31 | COMP | 2016-05-31 | 2016-06-01 | 74 | 198 | 131072.17
31100467 | OCGC ZAMORA 1105 RECONDUCTOR 3 SPANS | 09/11/2014 | 109209466 | 09/10/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2016 | ED.06319.1105.TXFR.TROH | OVERHEAD TRANSFORMERS | 057 | YOLO COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 435.000 | 435.000 | 08W | 2014 | 02/18/2017 | 2017 | 891 | 127.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-04-11 | 2016-04-11 | COMP | 2016-04-14 | 2016-04-14 | COMP | 2016-04-14 | 2016-04-14 | COMP | 2016-04-14 | 2016-05-11 | COMP | 2016-05-11 | 2016-09-13 | COMP | 2016-09-13 | 2016-09-13 | 3 | 152 | 27304.7
31101217 | OCGC EEL RIVER 1102 EXCESSIVE SPLICES | 09/15/2014 | 109210477 | 09/11/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/30/2016 | ED.19238.1102.SWIT | SWITCHES | 012 | HUMBOLDT COUNT | 5535457 | DO 08 - Monthly Forecast Only | 588.000 | 588.000 | 08J | 2014 | 09/02/2017 | 2017 | 1083 | 154.7143 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-10-11 | 2016-11-10 | COMP | 2016-10-11 | 2016-11-17 | COMP | 2016-11-17 | 2016-11-17 | COMP | 2016-11-17 | 2016-11-22 | COMP | 2016-11-22 | 2017-01-19 | COMP | 2017-01-19 | 2017-01-19 | 37 | 63 | 39456.71
31101833 | OCCC XVIEJO 2203 WIREDAWN AGUAJITO | 09/18/2014 | 109225766 | 09/17/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/04/2015 | ED.18285.2203 | VIEJO 2203 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 1,803.000 | 1,803.000 | 08J | 2014 | 06/18/2016 | 2016 | 639 | 91.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31101833_R2 VIEJO 2203 WIREDAWN AGUAJITO | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-12-22 | 2015-12-07 | COMP | 2015-12-22 | 2015-12-22 | COMP | 2015-12-22 | 2015-12-22 | COMP | 2015-12-22 | 2016-04-28 | COMP | 2016-04-28 | 2016-06-16 | COMP | 2016-06-16 | 2016-06-16 | 0 | 177 | 148538
31102548 | OC4 COTTONWOOD 1102-RECON 918' | 09/23/2014 | 109234404 | 09/23/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/30/2017 | ED.10293.1102.REGL | REGULATORS | 045 | SHASTA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 1,021.000 | 918.000 | 08W | 2014 | 06/25/2016 | 2016 | 641 | 91.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-08-04 | 2015-08-04 | COMP | 2015-08-17 | 2015-08-17 | COMP | 2015-08-19 | 2015-08-19 | COMP | 2015-08-19 | 2015-09-09 | COMP | 2015-09-09 | 2016-03-16 | COMP | 2016-03-16 | 2016-04-04 | 15 | 229 | 67237.52
31102830 | *CANC*DONOT USE*WIREDOWN RECONDUCTO*CANC | 09/24/2014 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/26/2015 | ED.02210.1110.SWIT | SWITCHES | 041 | SAN MATEO COUN | 5517127 | DO 08 - Monthly Forecast Only | 203.000 | 0.000 | 08J | 2014 | 05/03/2020 | 2020 | 2048 | 292.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | COMP | 2020-04-08 | 2020-04-08 | COMP | 2020-04-08 | 2020-04-08 | COMP | 2020-04-08 | 2020-04-08 | 0 | -25 | 0
31102963 | +SISQUOC 1104 WD (ORCUTT-GAREY RD) | 09/24/2014 | 109231089 | 09/19/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/28/2017 | ED.18281.1104 | SISQUOC 1104 | 042 | SANTA BARBARA | 5532479 | CWSP 08W - Monthly Forecast Only | 1,229.000 | 0.000 | 08W | 2014 | 10/15/2016 | 2016 | 752 | 107.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-08-25 | 2016-04-21 | COMP | 2015-08-25 | 2016-05-06 | COMP | 2016-05-06 | 2016-05-06 | COMP | 2016-05-06 | 2016-06-03 | COMP | 2016-06-03 | 2016-09-07 | COMP | 2016-09-07 | 2016-09-08 | 255 | 125 | 42484.95
31104113 | +TEMPLETON 2113 WD 14-0047158 | 09/29/2014 | 109245610 | 09/29/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/30/2017 | ED.18305.2113 | TEMPLETON 2113 | 040 | SAN LUIS OBISP | 5535457 | DO 08 - Monthly Forecast Only | 3,285.000 | 1,095.000 | 08J | 2014 | 06/17/2018 | 2018 | 1357 | 193.8571 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | R5 TEMPLETON 2113 WD 14-0047158 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-10-07 | 2016-12-02 | COMP | 2016-10-07 | 2016-12-05 | COMP | 2016-12-05 | 2016-12-07 | COMP | 2016-12-07 | 2016-12-10 | COMP | 2016-12-10 | 2017-01-19 | COMP | 2017-01-19 | 2017-01-19 | 61 | 43 | 109472.43
31104517 | OCCCDIXON1103 RECONDCTR 950' WIRE DWN PR | 10/01/2014 | 109249326 | 10/01/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2016 | ED.48-P190000000.STRU.POLE | SOLANO P19 POLES | 048 | SOLANO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 1,102.000 | 1,150.000 | 08J | 2014 | 12/17/2016 | 2016 | 808 | 115.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-07-12 | 2016-07-12 | COMP | 2016-07-12 | 2016-08-02 | COMP | 2016-08-02 | 2016-08-02 | COMP | 2016-08-02 | 2016-08-16 | COMP | 2016-08-16 | 2016-11-04 | COMP | 2016-11-04 | 2016-11-10 | 21 | 100 | 76906.55
31109716 | 2016 GUERNSEY 1104 ANNEALED RECOND | 10/24/2014 | 109589134 | 10/23/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/30/2016 | JY | JUNK YARD FL TO HOLD DELETED DATA | 016 | KINGS COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 7,286.000 | 0.000 | 08W | 2014 | 09/12/2020 | 2020 | 2150 | 307.1429 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | R2 2016 GUERNSEY 1104 ANNEALED RECOND | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-08-22 | 2016-10-12 | COMP | 2016-08-22 | 2016-10-27 | COMP | 2016-10-27 | 2016-10-27 | COMP | 2016-10-27 | 2016-11-01 | COMP | 2016-11-01 | 2017-02-23 | COMP | 2017-02-23 | 2017-02-27 | 66 | 123 | 639358.37
31111367 | OCGC XR CONDCTR 4 SPANS @TROUT G&OSPREY | 10/29/2014 | 109598244 | 10/28/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/31/2017 | ED.08369.2105 | ROB ROY 2105 | 044 | SANTA CRUZ COU | 5532479 | CWSP 08W - Monthly Forecast Only | 788.000 | 952.000 | 08W | 2014 | 07/20/2019 | 2019 | 1725 | 246.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-10-19 | 2015-10-19 | COMP | 2015-10-21 | 2015-10-21 | COMP | 2015-10-21 | 2015-10-21 | COMP | 2015-10-21 | 2016-04-15 | COMP | 2016-04-15 | 2016-06-02 | COMP | 2016-06-02 | 2016-06-03 | 2 | 226 | 120506.2
31111958 | 2016 CAL WATER 1102 RECONDUCTOR | 10/31/2014 | 109601413 | 10/30/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/01/2017 | ED.25545.1102.SWIT | SWITCHES | 015 | KERN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 1,391.000 | 1,391.000 | 08J | 2014 | 01/28/2017 | 2017 | 820 | 117.1429 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31111958_Cal Water 1102 Reconductor | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-09-13 | 2016-10-07 | COMP | 2016-09-13 | 2016-10-10 | COMP | 2016-10-10 | 2016-10-10 | COMP | 2016-10-10 | 2016-10-13 | COMP | 2016-10-13 | 2016-12-20 | COMP | 2016-12-20 | 2016-12-20 | 27 | 71 | 101997.14
31112500 | OCGC RECON 780FT OF 4ACSR MONTE RIO 1111 | 11/03/2014 | 109607951 | 11/03/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 08/31/2016 | ED.04281.1111.RECL | RECLOSERS | 049 | SONOMA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 833.000 | 0.000 | 08W | 2014 | 11/18/2017 | 2017 | 1111 | 158.7143 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-07-27 | 2016-11-07 | COMP | 2016-07-27 | 2016-11-07 | COMP | 2016-11-07 | 2016-11-07 | COMP | 2016-11-07 | 2016-11-14 | COMP | 2016-11-14 | 2017-01-19 | COMP | 2017-01-19 | 2017-01-19 | 103 | 73 | 126799.38
31113692 | R2Z RECNDUCTR PRUNEDALE 1107 MAIN AT MAS | 11/07/2014 | 109630784 | 11/06/2014 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/04/2016 | ED.18296.1107 | PRUNEDALE 1107 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 1,352.000 | 0.000 | 08J | 2014 | # | OPEN | 2219 | 317 | DOCC | 8 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 29724.2
31113693 | OCCC DOLAN RD 1104 WIREDOWN COOPER RD | 11/07/2014 | 109612843 | 11/05/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/15/2016 | ED.18238.1104 | DOLAN ROAD 1104 | 027 | MONTEREY COUNT | 5532479 | CWSP 08W - Monthly Forecast Only | 1,571.000 | 0.000 | 08W | 2014 | 12/17/2016 | 2016 | 771 | 110.1429 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-06-09 | 2016-06-22 | COMP | 2016-06-09 | 2016-07-11 | COMP | 2016-07-11 | 2016-07-11 | COMP | 2016-07-11 | 2016-08-17 | COMP | 2016-08-17 | 2016-10-31 | COMP | 2016-10-31 | 2016-11-08 | 32 | 120 | 53990.69
31114165 | HBPP 1101 FUSE 0441 EXCESSIVE SPLICES | 11/11/2014 | 109666199 | 11/10/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/29/2017 | ED.36-Q062400000.STRU.POLE | EUREKA Q0624 POLES | 012 | HUMBOLDT COUNT | 5535457 | DO 08 - Monthly Forecast Only | 1,132.000 | 0.000 | 08J | 2014 | 02/18/2017 | 2017 | 830 | 118.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-09-09 | 2016-10-07 | COMP | 2016-09-09 | 2016-10-14 | COMP | 2016-10-14 | 2016-10-14 | COMP | 2016-10-14 | 2016-10-19 | COMP | 2016-10-19 | 2017-01-19 | COMP | 2017-01-19 | 2017-01-23 | 35 | 101 | 152742.42
31115088 | OCGC RECON 900FT 4CU/4/0ALTW FTROSS 1121 | 11/14/2014 | 109671926 | 11/14/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/29/2017 | ED.04285.1121.RECL | RECLOSERS | 049 | SONOMA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 873.000 | 0.000 | 08W | 2014 | 10/28/2017 | 2017 | 1079 | 154.1429 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-10-11 | 2016-12-05 | COMP | 2016-10-11 | 2016-12-06 | COMP | 2016-12-06 | 2016-12-06 | COMP | 2016-12-06 | 2016-12-09 | COMP | 2016-12-09 | 2017-01-20 | COMP | 2017-01-20 | 2017-01-20 | 56 | 45 | 298002.53
31115947 | EL NIDO 1103 REPLACE ANNEALTED 650FT | 11/18/2014 | 109669571 | 11/13/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/29/2017 | ED.25245.1103 | EL NIDO 1103 | 020 | MADERA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 600.000 | 0.000 | 08W | 2014 | 11/19/2016 | 2016 | 732 | 104.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-06-06 | 2016-06-17 | COMP | 2016-06-06 | 2016-06-20 | COMP | 2016-06-20 | 2016-06-20 | COMP | 2016-06-20 | 2016-06-27 | COMP | 2016-06-27 | 2016-10-27 | COMP | 2016-10-27 | 2016-10-28 | 14 | 130 | 31785.79
31118505 | RECONDUCTOR EL PECO 1106 (WIREDOWN) | 12/02/2014 | 109679194 | 11/19/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2018 | ED.25398.1106 | EL PECO 1106 | 020 | MADERA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 6,056.000 | 7,556.000 | 08J | 2014 | 12/28/2017 | 2017 | 1122 | 160.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31118505_RECONDUCTOR EL PECO 1106 (WIRED | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2017-11-21 | 2017-11-09 | COMP | 2017-10-03 | 2017-11-21 | COMP | 2017-11-21 | 2017-11-21 | COMP | 2017-11-21 | 2017-11-22 | COMP | 2017-11-22 | 2017-12-11 | COMP | 2017-12-11 | 2017-12-11 | 0 | 20 | 446481.74
31119338 | *CANC* GUERNSEY 1104 RECON 5,800' OF 6 C | 12/04/2014 | 109696001 | 12/02/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/18/2016 | ED.25266.1104.SWIT | SWITCHES | 016 | KINGS COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2014 | 01/17/2015 | 2015 | 44 | 6.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2015-01-17 | 2015-01-17 | # | 2015-01-17 | 2015-01-17 | # | 2015-01-17 | 2015-01-17 | # | 2015-01-17 | 2015-01-17 | # | 2015-01-17 | 2015-01-17 | # | 2015-01-17 | 2015-01-17 | 0 | 0 | 0
31119865 | OCCC BEL 403 REPLC200FT OH LINE INST C/O | 12/08/2014 | 109764948 | 12/05/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 08/28/2015 | ED.02403.0403.TXFR.TROH | OVERHEAD TRANSFORMERS | 041 | SAN MATEO COUN | 5535457 | DO 08 - Monthly Forecast Only | 170.000 | 0.000 | 08W | 2014 | 07/23/2016 | 2016 | 593 | 84.7143 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-04-12 | 2016-04-12 | COMP | 2016-04-13 | 2016-04-19 | COMP | 2016-04-19 | 2016-04-19 | COMP | 2016-04-19 | 2016-05-20 | COMP | 2016-05-20 | 2016-06-16 | COMP | 2016-06-16 | 2016-06-24 | 7 | 66 | 44032.73
31120189 | +MESA 1102 (DIVISION E/O BONITA SCHOOL) | 12/09/2014 | 109702934 | 12/04/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/30/2016 | ED.18282.1102 | MESA 1102 | 040 | SAN LUIS OBISP | 5535457 | DO 08 - Monthly Forecast Only | 5,491.000 | 5,491.000 | 08J | 2014 | 02/11/2017 | 2017 | 795 | 113.5714 | PREC | 11 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | R2 SBWF ACSR REPL USE 8937 & 46299 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-09-20 | 2016-11-07 | COMP | 2016-09-20 | 2016-11-09 | COMP | 2016-11-09 | 2016-11-09 | COMP | 2016-11-09 | 2016-11-14 | COMP | 2016-11-14 | 2017-01-25 | COMP | 2017-01-25 | 2017-02-01 | 50 | 84 | 169942.49
31120347 | *CANC* FIGARDEN 2110 OH RECONDUCTOR*CANC | 12/09/2014 | 109764582 | 12/05/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 05/26/2017 | ED.25455.2110 | FIGARDEN 2110 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2014 | 07/03/2015 | 2015 | 206 | 29.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2015-07-03 | 2015-07-03 | # | 2015-07-03 | 2015-07-03 | # | 2015-07-03 | 2015-07-03 | # | 2015-07-03 | 2015-07-03 | # | 2015-07-03 | 2015-07-03 | # | 2015-07-03 | 2015-07-03 | 0 | 0 | 0
31120755 | RECONDUCTOR ND2101 WIREDOWN | 12/12/2014 | 109900929 | 12/12/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/30/2015 | ED.01405.2101.SWIT | SWITCHES | 001 | ALAMEDA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 60.000 | 0.000 | 08W | 2014 | 09/02/2017 | 2017 | 995 | 142.1429 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-06-04 | 2016-06-04 | COMP | 2016-06-07 | 2016-06-07 | COMP | 2016-06-08 | 2016-06-08 | COMP | 2016-06-08 | 2016-08-10 | COMP | 2016-08-10 | 2016-10-14 | COMP | 2016-10-14 | 2016-10-14 | 4 | 128 | 11446.75
31120911 | X-DOLN RD 1104 WIREDOWN BLNCO ARMSTRNG | 12/12/2014 | 109898337 | 12/11/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/13/2015 | ED.18238.1104 | DOLAN ROAD 1104 | 027 | MONTEREY COUNT | 5532479 | CWSP 08W - Monthly Forecast Only | 1,184.000 | 0.000 | 08W | 2014 | 02/18/2017 | 2017 | 799 | 114.1429 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-08-26 | 2016-08-30 | COMP | 2016-08-26 | 2016-09-01 | COMP | 2016-09-01 | 2016-09-01 | COMP | 2016-09-01 | 2016-09-16 | COMP | 2016-09-16 | 2016-12-23 | COMP | 2016-12-23 | 2016-12-23 | 6 | 113 | 23283.16
31120912 | X-DOLAN RD 1101 WIREDWN STRAWBRRY CYN | 12/12/2014 | 109898309 | 12/11/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/04/2015 | ED.18238.1101 | DOLAN ROAD 1101 | 044 | SANTA CRUZ COU | 5532479 | CWSP 08W - Monthly Forecast Only | 1,319.000 | 1,400.000 | 08W | 2014 | 10/28/2017 | 2017 | 1051 | 150.1429 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-07-14 | 2016-09-13 | COMP | 2016-07-14 | 2016-09-21 | COMP | 2016-09-21 | 2016-09-21 | COMP | 2016-09-21 | 2016-09-28 | COMP | 2016-09-28 | 2016-12-22 | COMP | 2016-12-22 | 2016-12-22 | 69 | 92 | 106757.15
31121472 | +OCEANO 1104 WD 14-0067445 | 12/17/2014 | 109907135 | 12/16/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2017 | ED.18260.1104 | OCEANO 1104 | 040 | SAN LUIS OBISP | 5532479 | CWSP 08W - Monthly Forecast Only | 338.000 | 0.000 | 08W | 2014 | 07/21/2018 | 2018 | 1312 | 187.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-09-23 | 2016-12-06 | COMP | 2016-09-23 | 2017-09-27 | COMP | 2017-09-26 | 2017-09-27 | COMP | 2017-09-27 | 2017-09-28 | COMP | 2017-09-28 | 2017-10-11 | COMP | 2017-10-11 | 2017-10-12 | 369 | 15 | 104987.51
31121571 | REPL OH WIRE PORT CHICAGO W/O NICHOLS | 12/16/2014 | 109907190 | 12/16/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/30/2017 | ED.01391.2108 | WILLOW PASS 2108 | 007 | CONTRA COSTA C | 5532479 | CWSP 08W - Monthly Forecast Only | 2,335.000 | 2,335.000 | 08W | 2014 | 03/04/2018 | 2018 | 1174 | 167.7143 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31121571_R1_REPL OH WIRE PORT CHICAGO W/ | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2017-03-28 | 2017-05-23 | COMP | 2017-03-28 | 2017-06-30 | COMP | 2017-06-30 | 2017-06-30 | COMP | 2017-06-30 | 2017-07-03 | COMP | 2017-07-03 | 2017-07-21 | COMP | 2017-07-21 | 2017-08-09 | 94 | 40 | 279879.21
31122009 | OCCC HMB1102 LR2032 REP 300FT OF OH LINE | 12/18/2014 | 109907850 | 12/17/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/31/2016 | ED.02410.1102.TXFR.TROH | OVERHEAD TRANSFORMERS | 041 | SAN MATEO COUN | 5505513 | PN-OH ANNEALED/DETER CNDCTR: PM MGD | 411.000 | 0.000 | 08J | 2014 | 03/31/2018 | 2018 | 1199 | 171.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-05-24 | 2016-06-10 | COMP | 2016-05-24 | 2016-07-01 | COMP | 2016-07-01 | 2016-07-01 | COMP | 2016-07-01 | 2016-07-05 | COMP | 2016-07-05 | 2016-07-11 | COMP | 2016-07-11 | 2016-07-11 | 38 | 10 | 91796.51
31122088 | KINGSBRG 1114 600' RECOND WIREDOWN | 12/18/2014 | 109907708 | 12/17/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/31/2017 | ED.25224.1114 | KINGSBURG 1114 | 010 | FRESNO COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 1,090.000 | 0.000 | 08W | 2014 | 08/27/2016 | 2016 | 618 | 88.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-03-31 | 2016-03-31 | COMP | 2016-04-08 | 2016-04-08 | COMP | 2016-04-08 | 2016-04-14 | COMP | 2016-04-14 | 2016-05-09 | COMP | 2016-05-09 | 2016-07-27 | COMP | 2016-07-27 | 2016-07-27 | 14 | 104 | 97168.47
31122468 | OCGC R2Z-ROUGH READY 1102 RECONDUCTOR | 12/22/2014 | 109910742 | 12/18/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/01/2018 | ED.16308.1102 | ROUGH AND READY IS 1102 | 039 | SAN JOAQUIN CO | 5535457 | DO 08 - Monthly Forecast Only | 1,487.000 | 1,487.000 | 08J | 2014 | 04/06/2019 | 2019 | 1566 | 223.7143 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | R4-ROUGH READY 1102 RECONDUCTOR AT CO19 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2017-12-04 | 2018-09-27 | COMP | 2018-10-03 | 2018-10-03 | COMP | 2018-10-03 | 2018-10-03 | COMP | 2018-10-03 | 2018-10-04 | COMP | 2018-10-04 | 2018-10-12 | COMP | 2018-10-12 | 2018-10-15 | 303 | 12 | 110592.3
31122833 | OCCC BASALT 1106 WIRE DWN FUSE 1157 ZONE | 12/23/2014 | 109917911 | 12/23/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/31/2017 | ED.04246.1106 | BASALT 1106 | 028 | NAPA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 537.000 | 0.000 | 08W | 2014 | 12/17/2016 | 2016 | 725 | 103.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-08-17 | 2016-08-17 | COMP | 2016-08-17 | 2016-08-18 | COMP | 2016-09-01 | 2016-09-01 | COMP | 2016-09-01 | 2016-09-10 | COMP | 2016-09-10 | 2016-12-05 | COMP | 2016-12-05 | 2016-12-05 | 15 | 95 | 60064
31124815 | OCCC X-SLDD 1114 WREDWN RECND. S/O HY101 | 01/05/2015 | 109912519 | 12/19/2014 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/17/2016 | ED.18205.1114 | SOLEDAD 1114 | 027 | MONTEREY COUNT | 5532479 | CWSP 08W - Monthly Forecast Only | 2,199.000 | 0.000 | 08W | 2015 | # | OPEN | 2160 | 308.5714 | DOCC | 8 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-06-10 | 2016-06-15 | COMP | 2016-06-10 | 2016-06-20 | COMP | 2016-06-20 | 2016-06-20 | COMP | 2016-06-20 | 2016-08-16 | COMP | 2016-08-16 | 2016-10-27 | COMP | 2016-10-27 | 2016-11-01 | 10 | 134 | 84703.5
31124817 | X-VIEJO 2202 WIRE DOWN 17 MILE DR | 01/05/2015 | 109935056 | 12/30/2014 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/28/2017 | ED.18285.2202 | VIEJO 2202 | 027 | MONTEREY COUNT | 5517127 | DO 08 - Monthly Forecast Only | 190.000 | 200.000 | 08J | 2015 | # | OPEN | 2160 | 308.5714 | DOCC | 8 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2017-03-10 | 2017-03-10 | INPR | 2017-12-20 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | -42804 | 0 | 132215.55
31124819 | OCCC KING CITY 1106 WD 14-0067419 | 01/05/2015 | 109936027 | 12/31/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2017 | ED.18203.1106 | KING CITY 1106 | 027 | MONTEREY COUNT | 5532479 | CWSP 08W - Monthly Forecast Only | 1,052.000 | 0.000 | 08W | 2015 | 04/22/2017 | 2017 | 838 | 119.7143 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-08-01 | 2016-07-24 | COMP | 2016-08-01 | 2016-08-08 | COMP | 2016-08-08 | 2016-08-08 | COMP | 2016-08-08 | 2016-08-29 | COMP | 2016-08-29 | 2016-11-26 | COMP | 2016-11-26 | 2016-11-26 | 7 | 110 | 102490.36
31125000 | +SANTA MARIA 1109 (BONITA LATERAL) | 01/05/2015 | 109936065 | 12/31/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2017 | ED.18267.1109 | SANTA MARIA 1109 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 955.000 | 955.000 | 08J | 2015 | 04/13/2019 | 2019 | 1559 | 222.7143 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2018-09-28 | 2018-09-28 | COMP | 2018-10-01 | 2018-10-01 | COMP | 2018-10-01 | 2018-10-01 | COMP | 2018-10-01 | 2018-10-02 | COMP | 2018-10-02 | 2018-10-12 | COMP | 2018-10-12 | 2018-10-15 | 3 | 14 | 46074.7
31125443 | OCLH PASO ROBLES 1103 WD 14-0066395 | 01/06/2015 | 109936122 | 12/31/2014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2017 | ED.18261.1108 | PASO ROBLES 1108 | 040 | SAN LUIS OBISP | 5532479 | CWSP 08W - Monthly Forecast Only | 1,102.000 | 0.000 | 08W | 2015 | 03/25/2017 | 2017 | 809 | 115.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-10-18 | 2016-11-03 | COMP | 2016-10-18 | 2016-12-06 | COMP | 2016-12-06 | 2017-02-08 | COMP | 2017-02-08 | 2017-02-10 | COMP | 2017-02-10 | 2017-02-27 | COMP | 2017-02-27 | 2017-03-01 | 113 | 21 | 42784.41
31125646 | OCGC D 2350' EXCESS SLICES SW6041 | 01/07/2015 | 109949376 | 01/07/2015 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/29/2017 | ED.19222.1101.SWIT | SWITCHES | 012 | HUMBOLDT COUNT | 5532479 | CWSP 08W - Monthly Forecast Only | 2,323.000 | 0.000 | 08W | 2015 | 12/17/2016 | 2016 | 710 | 101.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-06-22 | 2016-06-22 | COMP | 2016-06-27 | 2016-06-27 | COMP | 2016-06-27 | 2016-06-27 | COMP | 2016-06-27 | 2016-08-11 | COMP | 2016-08-11 | 2016-11-01 | COMP | 2016-11-01 | 2016-11-02 | 5 | 128 | 107693.21
31126015 | EP RECONDUCTOR PENRYN 1105 - Y2017 | 01/07/2015 | 109949925 | 01/07/2015 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/18/2016 | ED.15256.1105.COND | CONDUCTOR | 031 | PLACER COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 1,950.000 | 08J | 2015 | 09/16/2017 | 2017 | 983 | 140.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2017-07-13 | 2017-07-13 | COMP | 2017-07-20 | 2017-07-20 | COMP | 2017-07-20 | 2017-07-20 | COMP | 2017-07-20 | 2017-07-21 | COMP | 2017-07-21 | 2017-08-11 | COMP | 2017-08-11 | 2017-08-16 | 7 | 27 | 165699.55
31126827 | OCGC EP RECONDUCTOR WILLIAMS 1102- Y2016 | 01/09/2015 | 109953711 | 01/09/2015 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/18/2016 | ED.06205.1102.COND | CONDUCTOR | 006 | COLUSA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 2,074.000 | 0.000 | 08W | 2015 | 01/28/2017 | 2017 | 750 | 107.1429 | PREC | 11 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31126827_R4 EP RECONDUCTOR WILLIAMS 1102 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-06-15 | 2016-06-15 | COMP | 2016-06-16 | 2016-06-16 | COMP | 2016-06-16 | 2016-06-16 | COMP | 2016-06-16 | 2016-08-10 | COMP | 2016-08-10 | 2016-11-03 | COMP | 2016-11-03 | 2016-11-05 | 1 | 142 | 274437.2
31127880 | R2Z-AVENA 1701 WIRE-DOWN RECONDUCTOR | 01/13/2015 | 109963359 | 01/12/2015 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/28/2018 | ED.16357.1701 | AVENA 1701 | 039 | SAN JOAQUIN CO | 5535457 | DO 08 - Monthly Forecast Only | 3,802.000 | 3,802.000 | 08J | 2015 | 09/15/2018 | 2018 | 1341 | 191.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31127880_AVENA 1701 WIRE-DOWN RECONDUCT | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2018-05-17 | 2018-08-02 | COMP | 2018-08-06 | 2018-08-06 | COMP | 2018-08-08 | 2018-08-08 | COMP | 2018-08-08 | 2018-08-09 | COMP | 2018-08-09 | 2018-08-13 | COMP | 2018-08-13 | 2018-08-14 | 83 | 6 | 135698.48
31128279 | OCGC SPAULDING 1101 WIREDOWN SS OF 6607 | 01/15/2015 | 109970034 | 01/15/2015 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/30/2016 | ED.15225.1101.SWIT | SWITCHES | 029 | NEVADA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 269.000 | 269.000 | 08W | 2015 | 01/28/2017 | 2017 | 744 | 106.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-07-20 | 2016-08-31 | COMP | 2016-07-20 | 2016-09-01 | COMP | 2016-09-01 | 2016-09-01 | COMP | 2016-09-01 | 2016-09-16 | COMP | 2016-09-16 | 2016-12-21 | COMP | 2016-12-21 | 2016-12-21 | 43 | 111 | 81697.19
31129645 | OCCCSAN RAFAEL 1106 DETER COND H<(>&<)>F | 01/21/2015 | 109970930 | 01/15/2015 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2016 | ED.04201.1106.SWIT | SWITCHES | 021 | MARIN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 1,614.000 | 1,614.000 | 08J | 2015 | 10/03/2020 | 2020 | 2082 | 297.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31129645_R7 SAN RAFAEL 1106 DETER COND H | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-10-13 | 2016-11-09 | COMP | 2016-10-13 | 2016-11-21 | COMP | 2016-12-01 | 2016-12-01 | COMP | 2016-12-01 | 2016-12-06 | COMP | 2016-12-06 | 2017-01-19 | COMP | 2017-01-19 | 2017-01-27 | 49 | 57 | 372160.67
31129648 | OCCCSN RAFAEL 1106 DETER COND G & FORBES | 01/21/2015 | 109970932 | 01/15/2015 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2016 | ED.04201.1106.SWIT | SWITCHES | 021 | MARIN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 2,240.000 | 0.000 | 08J | 2015 | 09/15/2018 | 2018 | 1333 | 190.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31129648_R7 SAN RAFAEL 1106 DETER COND G | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-10-21 | 2016-12-03 | COMP | 2016-10-21 | 2016-12-16 | COMP | 2016-12-16 | 2016-12-16 | COMP | 2016-12-16 | 2016-12-21 | COMP | 2016-12-21 | 2017-01-18 | COMP | 2017-01-18 | 2017-04-04 | 56 | 109 | 365930.37
31129793 | RECONDUCTOR WILLIAMS 1101 - Y2017 | 01/22/2015 | 109976607 | 01/20/2015 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 07/29/2017 | ED.06205.1101.COND | CONDUCTOR | 006 | COLUSA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 1,529.000 | 1,529.000 | 08J | 2015 | 07/15/2017 | 2017 | 905 | 129.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2017-03-28 | 2017-03-24 | COMP | 2017-03-28 | 2017-03-29 | COMP | 2017-03-29 | 2017-03-29 | COMP | 2017-03-29 | 2017-03-30 | COMP | 2017-03-30 | 2017-04-13 | COMP | 2017-04-13 | 2017-04-24 | 1 | 26 | 94979.57
31129830 | OCCC BIG TREES 402 _ 14-0076789 PHASE 1 | 01/22/2015 | 109992256 | 01/22/2015 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/15/2017 | ED.08305.0402 | BIG TREES 0402 | 044 | SANTA CRUZ COU | 5532479 | CWSP 08W - Monthly Forecast Only | 1,360.000 | 1,360.000 | 08W | 2015 | 03/10/2018 | 2018 | 1143 | 163.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31129830_R2 WD BIG TREES 402 PHASE 1 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-09-09 | 2016-10-22 | COMP | 2016-09-09 | 2016-10-26 | COMP | 2016-10-26 | 2016-10-26 | COMP | 2016-10-26 | 2016-11-30 | COMP | 2016-11-30 | 2017-01-19 | COMP | 2017-01-19 | 2017-01-23 | 47 | 89 | 259437.42
31130513 | VIEJO 2202 WIRE DOWN 3191 17 MI DR | 01/27/2015 | 109981458 | 01/22/2015 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/28/2017 | ED.18285.2202 | VIEJO 2202 | 027 | MONTEREY COUNT | 5517127 | DO 08 - Monthly Forecast Only | 989.000 | 440.000 | 08J | 2015 | 11/24/2018 | 2018 | 1397 | 199.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2017-10-03 | 2017-02-28 | COMP | 2016-08-12 | 2018-05-01 | COMP | 2018-05-01 | 2018-05-01 | COMP | 2018-05-01 | 2018-05-02 | COMP | 2018-05-02 | 2018-05-08 | COMP | 2018-05-08 | 2018-05-09 | 210 | 8 | 190007.86
31131282 | OCCC XMABRY 1101-OH RECONDUCTOR & COMBO | 01/29/2015 | 110012433 | 01/28/2015 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 01/31/2017 | ED.78-F182100000.STRU.POLE | SAN JOSE F1821 POLES | 043 | SANTA CLARA CO | 5535457 | DO 08 - Monthly Forecast Only | 99.000 | 0.000 | 08J | 2015 | 03/31/2018 | 2018 | 1157 | 165.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-09-06 | 2016-08-31 | COMP | 2016-09-06 | 2016-09-09 | COMP | 2016-09-09 | 2016-09-09 | COMP | 2016-09-09 | 2016-09-14 | COMP | 2016-09-14 | 2016-12-23 | COMP | 2016-12-23 | 2016-12-23 | 3 | 105 | 68072.83
31131283 | R2Z V2101 14-0076675 COWARD RD | 01/29/2015 | 110012779 | 01/28/2015 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/13/2017 | ED.08319.2101 | GREEN VALLEY 2101 | 044 | SANTA CRUZ COU | 5535457 | DO 08 - Monthly Forecast Only | 786.000 | 0.000 | 08J | 2015 | # | OPEN | 2136 | 305.1429 | UNSC | 6 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | INPR | 2017-10-04 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | -43012 | 0 | 92331.7
31131288 | R2Z WD GV2101 14-0076675 SAN JUAN RD | 01/29/2015 | 110012774 | 01/28/2015 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/24/2017 | ED.08319.2101 | GREEN VALLEY 2101 | 044 | SANTA CRUZ COU | 5535457 | DO 08 - Monthly Forecast Only | 1,331.000 | 1,277.000 | 08J | 2015 | 04/25/2020 | 2020 | 1913 | 273.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2017-11-06 | 2019-04-03 | COMP | 2019-05-18 | 2019-05-18 | COMP | 2019-05-18 | 2019-05-18 | COMP | 2019-05-18 | 2019-05-20 | COMP | 2019-05-20 | 2019-05-22 | COMP | 2019-05-22 | 2019-05-22 | 558 | 4 | 18663.72
31132477 | RELIAIBLITY OAKLAND-REPLACE 1/0 OH | 02/04/2015 | 110022784 | 02/03/2015 | # | Not assigned | 30 | Technically Completed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/30/2016 | ED.01204.1105 | OAKLAND D 1105 | 001 | ALAMEDA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 606.000 | 740.000 | 08J | 2015 | # | OPEN | 2130 | 304.2857 | FICL | 10 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2018-01-12 | 2020-01-11 | COMP | 2018-09-20 | 2020-03-04 | COMP | 2020-03-04 | 2020-03-04 | COMP | 2020-03-04 | 2020-03-05 | COMP | 2020-03-05 | 2020-03-16 | COMP | 2020-03-16 | 2020-03-18 | 782 | 14 | 180140.48
31132867 | HMB1101 REPLACE OH LINE SKYLINE BLVD | 02/05/2015 | 110026264 | 02/05/2015 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2018 | ED.02410.1101.RECL | RECLOSERS | 041 | SAN MATEO COUN | 5535211 | CWSP SPO - SH 08 | 4,638.000 | 4,638.000 | 08W | 2015 | 01/12/2019 | 2019 | 1437 | 205.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | 31132867_ REPLACE OH LINE SKYLINE BLVD | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2018-04-13 | 2018-07-30 | COMP | 2018-08-06 | 2018-08-06 | COMP | 2018-08-06 | 2018-08-06 | COMP | 2018-08-06 | 2018-08-31 | COMP | 2018-08-31 | 2018-09-01 | COMP | 2018-09-01 | 2018-09-04 | 115 | 29 | 715788.12
31133991 | OCGC WIRE DOWN-RECONDUCTOR LIVE OAK 1102 | 02/12/2015 | 110045663 | 02/11/2015 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/29/2017 | ED.15377.1102.TXFR.TROH | OVERHEAD TRANSFORMERS | 051 | SUTTER COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 430.000 | 0.000 | 08W | 2015 | 12/17/2016 | 2016 | 674 | 96.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-07-13 | 2016-07-27 | COMP | 2016-07-13 | 2016-07-28 | COMP | 2016-07-28 | 2016-07-28 | COMP | 2016-07-28 | 2016-08-26 | COMP | 2016-08-26 | 2016-11-28 | COMP | 2016-11-28 | 2016-11-28 | 15 | 123 | 45113.39
31134351 | +MESA 1102 (JOSHUA ST & ORCHARD RD) | 02/13/2015 | 110048041 | 02/12/2015 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2017 | ED.18282.1102 | MESA 1102 | 040 | SAN LUIS OBISP | 5532479 | CWSP 08W - Monthly Forecast Only | 2,038.000 | 0.000 | 08W | 2015 | 02/18/2017 | 2017 | 736 | 105.1429 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-09-29 | 2016-09-29 | COMP | 2016-06-23 | 2016-09-30 | COMP | 2016-09-30 | 2016-09-30 | COMP | 2016-09-30 | 2016-10-06 | COMP | 2016-10-06 | 2017-01-19 | COMP | 2017-01-19 | 2017-01-23 | 1 | 115 | 78373.17
31136738 | X-KING CITY 1102 WD 15-0009162 | 02/24/2015 | 110062194 | 02/24/2015 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2017 | ED.18203.1102 | KING CITY 1102 | 027 | MONTEREY COUNT | 5532479 | CWSP 08W - Monthly Forecast Only | 293.000 | 0.000 | 08W | 2015 | 09/02/2017 | 2017 | 921 | 131.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-06-03 | 2016-06-03 | COMP | 2016-06-09 | 2016-06-09 | COMP | 2016-06-09 | 2016-06-09 | COMP | 2016-06-09 | 2016-08-10 | COMP | 2016-08-10 | 2016-10-14 | COMP | 2016-10-14 | 2016-10-19 | 6 | 132 | 5000.01
31138878 | *CANC* KING CITY 1102 WD 15-0009162 | 03/05/2015 | 110077600 | 03/04/2015 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2017 | ED.18203.1102 | KING CITY 1102 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2015 | 03/21/2015 | 2015 | 16 | 2.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2015-03-22 | 2015-03-22 | # | 2015-03-22 | 2015-03-22 | # | 2015-03-22 | 2015-03-22 | # | 2015-03-22 | 2015-03-22 | # | 2015-03-22 | 2015-03-22 | # | 2015-03-22 | 2015-03-22 | 0 | 0 | 0
31139913 | +SANTA MARIA 1110 ANNEALED RIVER X-ING | 03/10/2015 | 110088290 | 03/09/2015 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/02/2015 | ED.18267.1110 | SANTA MARIA 1110 | 042 | SANTA BARBARA | 5532479 | CWSP 08W - Monthly Forecast Only | 1,282.000 | 0.000 | 08W | 2015 | 01/28/2017 | 2017 | 690 | 98.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-11-14 | 2015-11-14 | COMP | 2016-12-09 | 2016-12-09 | COMP | 2016-12-09 | 2016-12-09 | COMP | 2016-12-09 | 2016-12-10 | COMP | 2016-12-10 | 2016-12-10 | COMP | 2016-12-10 | 2016-12-13 | 391 | 4 | 69516.76
31140055 | OCGC RECONDUCTOR PUEBLO 2103 AT SW 7927 | 03/10/2015 | 110071673 | 03/02/2015 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/01/2017 | ED.04329.2103 | PUEBLO 2103 | 028 | NAPA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 727.000 | 0.000 | 08W | 2015 | 02/11/2017 | 2017 | 704 | 100.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31140055_RECONDUCTOR PUEBLO 2103 AT SW 7 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-09-22 | 2016-11-29 | COMP | 2016-09-22 | 2016-12-16 | COMP | 2016-12-16 | 2016-12-16 | COMP | 2016-12-16 | 2016-12-22 | COMP | 2016-12-22 | 2017-01-19 | COMP | 2017-01-19 | 2017-02-02 | 85 | 48 | 96664.22
31141749 | STOREY 1104 RECONDUCTORING | 03/17/2015 | 110110392 | 03/17/2015 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2017 | ED.25461.1104 | STOREY 1104 | 020 | MADERA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 2,036.000 | 2,056.000 | 08J | 2015 | 10/21/2017 | 2017 | 949 | 135.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2017-06-27 | 2017-08-23 | COMP | 2017-06-27 | 2017-08-25 | COMP | 2017-08-25 | 2017-08-25 | COMP | 2017-08-25 | 2017-08-28 | COMP | 2017-08-28 | 2017-09-14 | COMP | 2017-09-14 | 2017-09-20 | 59 | 26 | 88478.96
31142343 | R2 2017 KERMAN 1102 RECONDUCTOR WIREDOWN | 03/19/2015 | 110113851 | 03/19/2015 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.25271.1102 | KERMAN 1102 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 5,485.000 | 0.000 | 08J | 2015 | # | OPEN | 2087 | 298.1429 | CONS | 7 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31142343_Kerman 1102 Reconductor | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 319209.45
31143734 | 2016 REEDLEY 1104 WIRE DOWN RECONDUCT | 03/26/2015 | 110124138 | 03/25/2015 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/29/2017 | ED.25234.1104 | REEDLEY 1104 | 010 | FRESNO COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 1,780.000 | 0.000 | 08W | 2015 | 01/14/2017 | 2017 | 660 | 94.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31143734_R2REEDLEY 1104 WIRE DOWN RECOND | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-08-12 | 2016-09-19 | COMP | 2016-08-12 | 2016-09-29 | COMP | 2016-09-29 | 2016-09-29 | COMP | 2016-09-29 | 2016-10-05 | COMP | 2016-10-05 | 2016-12-19 | COMP | 2016-12-19 | 2016-12-19 | 48 | 81 | 112607.49
31144558 | WDN 15-0013313 CE2105-HUBBARD GULCH | 03/31/2015 | 110143726 | 03/31/2015 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 07/24/2017 | ED.08362.2105 | CAMP EVERS 2105 | 044 | SANTA CRUZ COU | 5532479 | CWSP 08W - Monthly Forecast Only | 2,413.000 | 2,500.000 | 08W | 2015 | 02/04/2017 | 2017 | 676 | 96.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | WDN 15-0013313 CE2105-HUBBARD GULCH | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-11-09 | 2016-11-09 | COMP | 2016-11-10 | 2016-11-14 | COMP | 2016-11-14 | 2016-11-14 | COMP | 2016-11-14 | 2016-11-17 | COMP | 2016-11-17 | 2017-01-25 | COMP | 2017-01-25 | 2017-02-02 | 5 | 80 | 158320.08
31144778 | OCGC TRINIDAD 1102 EXCESSIVE SPLICES | 03/31/2015 | 110143065 | 03/30/2015 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/29/2017 | ED.36-J080400000.STRU.POLE | EUREKA J0804 POLES | 012 | HUMBOLDT COUNT | 5532479 | CWSP 08W - Monthly Forecast Only | 2,062.000 | 0.000 | 08W | 2015 | 09/23/2017 | 2017 | 907 | 129.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-09-20 | 2016-09-20 | COMP | 2016-09-22 | 2016-09-22 | COMP | 2016-09-22 | 2016-09-22 | COMP | 2016-09-22 | 2016-09-28 | COMP | 2016-09-28 | 2016-12-27 | COMP | 2016-12-27 | 2016-12-27 | 2 | 96 | 179750.49
31144782 | 2017 KERNEY 1104 RECONDUCTOR WIREDOWN | 03/31/2015 | 110119842 | 03/23/2015 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/30/2017 | ED.25270.1104 | KEARNEY 1104 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 1,600.000 | 1,787.000 | 08J | 2015 | 12/16/2017 | 2017 | 991 | 141.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31144782_Kearney 1104 Reconductor | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2017-03-07 | 2017-04-12 | COMP | 2017-03-07 | 2017-04-17 | COMP | 2017-04-17 | 2017-04-17 | COMP | 2017-04-17 | 2017-04-20 | COMP | 2017-04-20 | 2017-06-27 | COMP | 2017-06-27 | 2017-07-10 | 41 | 84 | 125758.87
31145622 | OCGC 2016 CORCORAN 1108 RECOND WIREDOWN | 04/03/2015 | 110150856 | 04/03/2015 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/31/2017 | ED.25217.1108 | CORCORAN 1108 | 016 | KINGS COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 2,164.000 | 2,164.000 | 08W | 2015 | 07/14/2018 | 2018 | 1198 | 171.1429 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31145622_Corcoran 1108 Reconductor | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-10-13 | 2017-01-05 | COMP | 2016-10-13 | 2017-01-31 | COMP | 2017-02-01 | 2017-02-01 | COMP | 2017-02-01 | 2017-02-07 | COMP | 2017-02-07 | 2017-03-21 | COMP | 2017-03-21 | 2017-03-21 | 111 | 48 | 239258.71
31147897 | CAR403 REPLACE 250FT OF OH LINE | 04/14/2015 | 110172675 | 04/10/2015 | # | Not assigned | 30 | Technically Completed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 01/29/2016 | JY | JUNK YARD FL TO HOLD DELETED DATA | 041 | SAN MATEO COUN | 5505513 | PN-OH ANNEALED/DETER CNDCTR: PM MGD | 122.000 | 150.000 | 08J | 2015 | # | OPEN | 2061 | 294.4286 | FICL | 10 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2018-01-17 | 2019-09-25 | COMP | 2019-09-26 | 2019-09-26 | COMP | 2019-09-26 | 2019-09-26 | COMP | 2019-09-26 | 2019-09-27 | COMP | 2019-09-27 | 2019-11-08 | COMP | 2019-11-08 | 2019-11-12 | 617 | 47 | 64004.61
31148548 | +FAIRWAY 1106 RECONDUCTOR | 04/15/2015 | 110177529 | 04/14/2015 | # | Not assigned | 30 | Technically Completed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2017 | ED.18206.1106 | FAIRWAY 1106 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 289.000 | 289.000 | 08J | 2015 | # | OPEN | 2060 | 294.2857 | FICL | 10 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2017-08-08 | 2019-12-15 | COMP | 2017-10-04 | 2020-06-15 | COMP | 2020-06-15 | 2020-06-15 | COMP | 2020-06-15 | 2020-06-16 | COMP | 2020-06-16 | 2020-06-22 | COMP | 2020-06-22 | 2020-07-06 | 1042 | 21 | 175973.79
31150684 | MORAGA 1103 RECNDUCTOR 350' (2SPANS) | 04/24/2015 | 110292425 | 04/23/2015 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/28/2016 | ED.01380.1103 | MORAGA 1103 | 007 | CONTRA COSTA C | 5532479 | CWSP 08W - Monthly Forecast Only | 350.000 | 362.000 | 08W | 2015 | 01/29/2018 | 2018 | 1011 | 144.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2017-04-10 | 2017-03-16 | COMP | 2017-01-11 | 2017-05-05 | COMP | 2017-04-06 | 2017-04-06 | COMP | 2017-04-06 | 2017-04-11 | COMP | 2017-04-11 | 2017-05-31 | COMP | 2017-05-31 | 2017-05-31 | -4 | 55 | 95671.48
31151064 | RECONDUCT ON U1112 | 04/28/2015 | 110308182 | 04/28/2015 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2018 | ED.24-H072500000.STRU.ENCL | MISSION H0725 ENCLOSURE | 001 | ALAMEDA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 177.000 | 0.000 | 08J | 2015 | # | OPEN | 2047 | 292.4286 | PEND | 5 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | INPR | 2018-03-07 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | -43166 | 0 | 7953.86
31152787 | OCLH CLOVIS 2110 WIRE DOWN RECONDUCTOR | 05/05/2015 | 110365473 | 05/04/2015 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/29/2017 | ED.25408.2110 | CLOVIS 2110 | 010 | FRESNO COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 452.000 | 0.000 | 08W | 2015 | 07/25/2020 | 2020 | 1908 | 272.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-11-10 | 2016-12-21 | COMP | 2016-11-10 | 2016-12-27 | COMP | 2016-12-27 | 2016-12-27 | COMP | 2016-12-27 | 2017-01-03 | COMP | 2017-01-03 | 2017-01-26 | COMP | 2017-01-26 | 2017-01-26 | 47 | 30 | 62445.03
31153724 | OCGC BANTA 1103 RECOND 968FT 6CU | 05/08/2015 | 110374316 | 05/07/2015 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/14/2017 | ED.16247.1103 | BANTA 1103 | 039 | SAN JOAQUIN CO | 5532479 | CWSP 08W - Monthly Forecast Only | 940.000 | 940.000 | 08W | 2015 | 12/17/2016 | 2016 | 589 | 84.1429 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-07-14 | 2016-07-14 | COMP | 2016-07-21 | 2016-07-21 | COMP | 2016-07-21 | 2016-07-21 | COMP | 2016-07-21 | 2016-08-24 | COMP | 2016-08-24 | 2016-11-07 | COMP | 2016-11-07 | 2016-12-05 | 7 | 137 | 32756.84
31154886 | OCGC EP RECONDUCTOR ARBUCKLE 1102 -Y2016 | 05/14/2015 | 110392964 | 05/14/2015 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 07/29/2017 | ED.06208.1102.COND | CONDUCTOR | 006 | COLUSA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 212.000 | 212.000 | 08W | 2015 | 11/19/2016 | 2016 | 555 | 79.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-07-01 | 2016-07-01 | COMP | 2016-07-01 | 2016-07-01 | COMP | 2016-07-01 | 2016-07-01 | COMP | 2016-07-01 | 2016-08-19 | COMP | 2016-08-19 | 2016-11-02 | COMP | 2016-11-02 | 2016-11-03 | 0 | 125 | 26900.69
31155091 | *CANC* ACSR REPLACEMENT Q4 FUSE 894*CANC | 05/15/2015 | 110393781 | 05/14/2015 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2018 | ED.18267.1109 | SANTA MARIA 1109 | 040 | SAN LUIS OBISP | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2015 | 01/04/2018 | 2018 | 965 | 137.8571 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31155091_R5 SBWF ACSR REPLACEMENT Q4 FUS | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2018-01-04 | 2018-01-04 | # | 2018-01-04 | 2018-01-04 | # | 2018-01-04 | 2018-01-04 | # | 2018-01-04 | 2018-01-04 | # | 2018-01-04 | 2018-01-04 | # | 2018-01-04 | 2018-01-04 | 0 | 0 | 0
31155092 | R5 SBWF MESA 1102 & SM 1109, VARIOUS, SM | 05/15/2015 | 110393688 | 05/14/2015 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/30/2020 | ED.18267.1109 | SANTA MARIA 1109 | 040 | SAN LUIS OBISP | 5535457 | DO 08 - Monthly Forecast Only | 6,578.000 | 5,709.000 | 08J | 2015 | # | OPEN | 2030 | 290 | DOCC | 8 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31155092_R5 SBWF ACSR REPLACEMENT QUADRA | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2019-10-11 | 2019-10-11 | COMP | 2020-03-20 | 2020-05-15 | COMP | 2020-05-15 | 2020-05-15 | COMP | 2020-05-15 | 2020-05-18 | COMP | 2020-05-18 | 2020-06-01 | COMP | 2020-06-01 | 2020-06-09 | 217 | 25 | 319625.93
31156130 | SAN ARDO 1102 WD #15-0024843 | 05/20/2015 | 110387746 | 05/12/2015 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2017 | ED.18219.1102 | SAN ARDO 1102 | 027 | MONTEREY COUNT | 5532479 | CWSP 08W - Monthly Forecast Only | 2,410.000 | 2,415.000 | 08W | 2015 | 03/25/2017 | 2017 | 675 | 96.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-10-12 | 2016-10-12 | COMP | 2016-10-13 | 2016-10-13 | COMP | 2016-10-13 | 2016-10-13 | COMP | 2016-10-13 | 2016-10-24 | COMP | 2016-10-24 | 2017-01-20 | COMP | 2017-01-20 | 2017-01-20 | 1 | 99 | 72660.03
31156133 | 2017 DEVILS DEN 1102 6CU RECONDUCTOR | 05/20/2015 | 110399522 | 05/18/2015 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/30/2018 | ED.25345.1102 | DEVILS DEN 1102 | 015 | KERN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 1,321.000 | 1,400.000 | 08J | 2015 | 10/17/2018 | 2018 | 1246 | 178 | PREC | 11 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31156133_R2 2017 DEVILS DEN 1102 6CU REC | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2018-08-16 | 2018-07-28 | COMP | 2018-05-02 | 2018-08-16 | COMP | 2018-08-16 | 2018-08-16 | COMP | 2018-08-16 | 2018-08-17 | COMP | 2018-08-17 | 2018-08-18 | COMP | 2018-08-18 | 2018-08-21 | 0 | 5 | 89858.9
31157217 | STONE 1108 RECONDUCTOR | 05/27/2015 | 110411801 | 05/26/2015 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/01/2017 | ED.08370.1108.SWIT | SWITCHES | 043 | SANTA CLARA CO | 5535457 | DO 08 - Monthly Forecast Only | 443.000 | 0.000 | 08J | 2015 | 01/29/2018 | 2018 | 978 | 139.7143 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-09-09 | 2016-11-20 | COMP | 2016-09-09 | 2016-12-07 | COMP | 2016-12-07 | 2016-12-07 | COMP | 2016-12-07 | 2017-06-14 | COMP | 2017-06-14 | 2017-06-15 | COMP | 2017-06-15 | 2017-06-19 | 89 | 194 | 120009.54
31157301 | X-RECNDUCTR-POINT M1101_2598 SMITH GRDE | 05/27/2015 | 110411551 | 05/26/2015 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/30/2017 | ED.08293.1101 | POINT MORETTI 1101 | 044 | SANTA CRUZ COU | 5532479 | CWSP 08W - Monthly Forecast Only | 616.000 | 616.000 | 08W | 2015 | 06/17/2018 | 2018 | 1117 | 159.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-07-29 | 2016-07-29 | COMP | 2016-09-01 | 2016-09-01 | COMP | 2016-09-01 | 2016-09-01 | COMP | 2016-09-01 | 2016-09-09 | COMP | 2016-09-09 | 2017-01-19 | COMP | 2017-01-19 | 2017-02-04 | 34 | 156 | 53367.68
31157526 | OCGCEP LOGAN CREEK 2101 RECOND 3550' 6CU | 05/28/2015 | 110414106 | 05/27/2015 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/15/2018 | ED.14-Y191300000 | GLENN MAP Y1913 | 011 | GLENN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 3,122.000 | 3,122.000 | 08J | 2015 | 05/04/2019 | 2019 | 1437 | 205.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31157526_EP RECONDUCTOR 3590# #6CU, WILL | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2017-08-01 | 2018-05-24 | COMP | 2018-05-29 | 2018-05-29 | COMP | 2018-05-29 | 2018-05-29 | COMP | 2018-05-29 | 2018-06-08 | COMP | 2018-06-08 | 2018-06-14 | COMP | 2018-06-14 | 2018-06-15 | 301 | 17 | 453867.18
31157542 | OCGC CHROKEE 1102 RECNDUCTOR 1300FT | 05/28/2015 | 110413742 | 05/27/2015 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/30/2017 | ED.16365.1102 | CHEROKEE 1102 | 039 | SAN JOAQUIN CO | 5535457 | DO 08 - Monthly Forecast Only | 1,412.000 | 1,412.000 | 08J | 2015 | 01/13/2018 | 2018 | 961 | 137.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | CHROKEE 1102 RECNDUCTOR 1300FT W/4/0AL | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2017-10-24 | 2017-09-28 | COMP | 2017-11-01 | 2017-11-01 | COMP | 2017-11-01 | 2017-11-01 | COMP | 2017-11-01 | 2017-11-02 | COMP | 2017-11-02 | 2017-11-30 | COMP | 2017-11-30 | 2017-12-01 | 8 | 30 | 95513.19
31157544 | OCGC MCCALL 1106 WIREDOWN RECONDUCTOR | 05/28/2015 | 110412896 | 05/27/2015 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/29/2018 | ED.25412.1106 | MC CALL 1106 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 2,300.000 | 7,221.000 | 08J | 2015 | 11/07/2020 | 2020 | 1990 | 284.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | R2 MCCALL 1106 WIREDOWN RECONDUCTOR | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2017-10-04 | 2018-02-02 | COMP | 2017-12-15 | 2018-02-05 | COMP | 2018-02-05 | 2018-02-05 | COMP | 2018-02-05 | 2018-02-07 | COMP | 2018-02-07 | 2018-02-12 | COMP | 2018-02-12 | 2018-02-14 | 124 | 9 | 155786.85
31157545 | OCGC HARDWICK 1102 WIRE DWN RECNDUCTOR | 05/28/2015 | 110412892 | 05/27/2015 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/29/2017 | ED.25371.1102 | HARDWICK 1102 | 016 | KINGS COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 2,487.000 | 0.000 | 08W | 2015 | 02/18/2017 | 2017 | 632 | 90.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | R2 HARDWICK 1102 WIRE DOWN RECONDUCTOR | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-08-19 | 2016-09-15 | COMP | 2016-08-19 | 2016-09-20 | COMP | 2016-09-21 | 2016-09-21 | COMP | 2016-09-21 | 2016-09-27 | COMP | 2016-09-27 | 2016-12-19 | COMP | 2016-12-19 | 2016-12-19 | 33 | 89 | 144185.89
31157953 | RECON 1SPAN N/O FISH ROCK GUALALA1112 | 05/29/2015 | 110417407 | 05/29/2015 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/29/2017 | ED.04284.1112.SWIT | SWITCHES | 023 | MENDOCINO COUN | 5532479 | CWSP 08W - Monthly Forecast Only | 390.000 | 0.000 | 08W | 2015 | 01/28/2017 | 2017 | 610 | 87.1429 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-06-06 | 2016-06-20 | COMP | 2016-06-06 | 2016-06-24 | COMP | 2016-06-24 | 2016-06-24 | COMP | 2016-06-24 | 2016-08-11 | COMP | 2016-08-11 | 2016-10-28 | COMP | 2016-10-28 | 2016-11-02 | 18 | 131 | 34918.81
31158390 | +RECOND 960 FT OF 4 ACSR ON SLO 1101 | 06/02/2015 | 110421174 | 06/01/2015 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2017 | ED.18263.1101 | SAN LUIS OBISPO 1101 | 040 | SAN LUIS OBISP | 5535457 | DO 08 - Monthly Forecast Only | 994.000 | 994.000 | 08J | 2015 | # | OPEN | 2012 | 287.4286 | DOCC | 8 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2017-08-21 | 2020-02-14 | COMP | 2020-02-11 | 2020-05-27 | COMP | 2020-05-27 | 2020-05-27 | COMP | 2020-05-27 | 2020-05-28 | COMP | 2020-05-28 | 2020-06-09 | COMP | 2020-06-09 | 2020-06-10 | 1010 | 14 | 348209.58
31162678 | H-1107 RECONDUCTOR | 06/25/2015 | 110459273 | 06/17/2015 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/30/2017 | ED.02210.1107 | SF H 1107 | 038 | SAN FRANCISCO | 5535457 | DO 08 - Monthly Forecast Only | 4,151.000 | 4,100.000 | 08J | 2015 | 01/19/2019 | 2019 | 1304 | 186.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31162678_R1 H-1107 RECONDUCTOR | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2017-07-26 | 2017-06-23 | COMP | 2017-07-11 | 2017-07-11 | COMP | 2017-07-11 | 2018-09-12 | COMP | 2018-09-12 | 2018-12-12 | COMP | 2018-12-12 | 2019-01-14 | COMP | 2019-01-14 | 2019-01-14 | 413 | 124 | 1109605.59
31162833 | REPL DETERIORATED COND _MCARTHUR 1101 | 06/22/2015 | 110467479 | 06/22/2015 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/01/2017 | ED.87-D540000000 | SHASTA MAP D54 | 045 | SHASTA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 2,697.000 | 08J | 2015 | 11/25/2017 | 2017 | 887 | 126.7143 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31162833_REPL COND _MCARTHUR 1101 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2017-08-25 | 2017-08-25 | COMP | 2017-08-31 | 2017-08-31 | COMP | 2017-08-31 | 2017-08-31 | COMP | 2017-08-31 | 2017-09-01 | COMP | 2017-09-01 | 2017-09-19 | COMP | 2017-09-19 | 2017-09-21 | 6 | 21 | 263179.71
31163618 | SOLEDAD 2102 RECONDUCTORING JOB | 06/24/2015 | 110470402 | 06/23/2015 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/29/2018 | ED.18205.2102 | SOLEDAD 2102 | 027 | MONTEREY COUNT | 5532479 | CWSP 08W - Monthly Forecast Only | 2,029.000 | 2,070.000 | 08W | 2015 | # | OPEN | 1990 | 284.2857 | DOCC | 8 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2017-08-08 | 2017-08-08 | COMP | 2017-08-10 | 2017-08-10 | COMP | 2017-08-10 | 2017-08-10 | COMP | 2017-08-10 | 2017-08-11 | COMP | 2017-08-11 | 2017-09-05 | COMP | 2017-09-05 | 2017-09-14 | 2 | 35 | 105157.23
31163857 | X LOS OSITOS 2102 WDWN_15-0036239 | 06/24/2015 | 110471625 | 06/24/2015 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 07/28/2018 | ED.18208.2102 | LOS OSITOS 2102 | 027 | MONTEREY COUNT | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 931.000 | 08W | 2015 | 12/23/2017 | 2017 | 913 | 130.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2017-07-26 | 2017-07-26 | COMP | 2017-08-03 | 2017-08-07 | COMP | 2017-08-07 | 2017-08-07 | COMP | 2017-08-07 | 2017-08-07 | COMP | 2017-08-07 | 2017-11-03 | COMP | 2017-11-03 | 2017-11-10 | 12 | 95 | 71995.83
31163921 | X SALINAS 1104 RECONDUCTORING JOB | 06/24/2015 | 110472227 | 06/24/2015 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2017 | ED.18201.1104 | SALINAS 1104 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 629.000 | 629.000 | 08J | 2015 | 08/18/2018 | 2018 | 1151 | 164.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2018-01-20 | 2018-06-28 | COMP | 2018-07-30 | 2018-07-30 | COMP | 2018-07-30 | 2018-07-30 | COMP | 2018-07-30 | 2018-07-31 | COMP | 2018-07-31 | 2018-08-01 | COMP | 2018-08-01 | 2018-08-02 | 191 | 3 | 53892.17
31164796 | *CANC* EP HWY 45 ANNEALED COND PH 4*CANC | 06/29/2015 | 110474611 | 06/25/2015 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2017 | ED.14-Y230000000 | GLENN MAP Y23 | 011 | GLENN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2015 | 09/03/2020 | 2020 | 1893 | 270.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2020-09-03 | 2020-09-03 | # | 2020-09-03 | 2020-09-03 | # | 2020-09-03 | 2020-09-03 | COMP | 2020-08-13 | 2020-08-13 | COMP | 2020-08-13 | 2020-08-13 | COMP | 2020-08-13 | 2020-08-13 | 0 | -21 | 0
31164798 | *CANC* EP HWY 45 ANNEALED COND PH 5*CANC | 06/29/2015 | 110474612 | 06/25/2015 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2017 | ED.14-Z230000000 | GLENN MAP Z23 | 011 | GLENN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2015 | 09/03/2020 | 2020 | 1893 | 270.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2020-09-03 | 2020-09-03 | # | 2020-09-03 | 2020-09-03 | # | 2020-09-03 | 2020-09-03 | COMP | 2020-08-13 | 2020-08-13 | COMP | 2020-08-13 | 2020-08-13 | COMP | 2020-08-13 | 2020-08-13 | 0 | -21 | 0
31164840 | EP PRATTVILLE ANNEALED CONDUCTOR PHASE 3 | 06/29/2015 | 110474613 | 06/25/2015 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2017 | ED.18-J450000000 | LAS PLUMAS MAP J45 | 032 | PLUMAS COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2015 | # | OPEN | 1985 | 283.5714 | UNSE | 1 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 164.29
31164841 | EP PRATTVILLE ANNEALED CONDUCTOR PHASE 4 | 06/29/2015 | 110474614 | 06/25/2015 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2017 | ED.18-J450000000 | LAS PLUMAS MAP J45 | 032 | PLUMAS COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2015 | # | OPEN | 1985 | 283.5714 | UNSE | 1 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 164.29
31164842 | *CANC* EP RD D ANNEALED COND PH 3 *CANC | 06/29/2015 | 110474615 | 06/25/2015 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2017 | ED.14-Z170000000 | GLENN MAP Z17 | 011 | GLENN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2015 | 09/03/2020 | 2020 | 1893 | 270.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2020-09-03 | 2020-09-03 | # | 2020-09-03 | 2020-09-03 | # | 2020-09-03 | 2020-09-03 | COMP | 2020-08-13 | 2020-08-13 | COMP | 2020-08-13 | 2020-08-13 | COMP | 2020-08-13 | 2020-08-13 | 0 | -21 | 0
31164843 | EP CAPAY 1101 ANNEALED CONDUCTOR PHASE 2 | 06/29/2015 | 110474616 | 06/25/2015 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2017 | ED.14-S210000000 | GLENN MAP S21 | 011 | GLENN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2015 | # | OPEN | 1985 | 283.5714 | UNSE | 1 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 20650.53
31165740 | *CANC* R7 NAPA 1109 WIRE DOWN AT S *CANC | 07/02/2015 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/30/2017 | ED.04202.1109 | NAPA 1109 | 028 | NAPA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2015 | 05/03/2020 | 2020 | 1767 | 252.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | COMP | 2020-04-09 | 2020-04-09 | COMP | 2020-04-09 | 2020-04-09 | COMP | 2020-04-09 | 2020-04-09 | 0 | -24 | 0
31169728 | 2017 GRIZZLY PEAK REPL #6 CU-UWF | 07/17/2015 | 110515764 | 07/16/2015 | # | Not assigned | 40 | Closed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 09/01/2018 | ED.01204.1112 | OAKLAND D 1112 | 001 | ALAMEDA COUNTY | 5535211 | CWSP SPO - SH 08 | 5,938.000 | 4,093.000 | 08W | 2015 | 01/18/2020 | 2020 | 1646 | 235.1429 | CLSD | 12 | E070 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | 31169728_RELIAIB 2017:OAK-REPL #6 CU-UWF | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2018-04-25 | 2018-11-15 | COMP | 2018-06-07 | 2019-02-08 | COMP | 2019-02-08 | 2019-02-08 | COMP | 2019-02-08 | 2019-03-06 | COMP | 2019-03-06 | 2019-03-12 | COMP | 2019-03-12 | 2019-03-13 | 289 | 33 | 718126.93
31169729 | OCGCABILITY 2017 D1112/K1101 UWF | 07/17/2015 | 110515765 | 07/16/2015 | # | Not assigned | 40 | Closed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 03/14/2018 | ED.01250.1105 | EL CERRITO G 1105 | 001 | ALAMEDA COUNTY | 5535211 | CWSP SPO - SH 08 | 4,171.000 | 4,171.000 | 08W | 2015 | 03/23/2019 | 2019 | 1345 | 192.1429 | CLSD | 12 | E070 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | 31169729_R1-RELIAIB 2017 D1112/K1101 UWF | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2017-10-23 | 2018-07-23 | COMP | 2018-07-23 | 2018-07-23 | COMP | 2018-07-23 | 2018-07-23 | COMP | 2018-07-23 | 2018-07-24 | COMP | 2018-07-24 | 2018-08-23 | COMP | 2018-08-23 | 2018-08-23 | 273 | 31 | 685267.46
31170650 | X-SAN BENITO 2101 WIREDOWN 15-0039468 | 07/21/2015 | 110526215 | 07/21/2015 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 08/03/2018 | ED.18274.2101 | SAN BENITO 2101 | 035 | SAN BENITO COU | 5532479 | CWSP 08W - Monthly Forecast Only | 527.000 | 0.000 | 08W | 2015 | 12/17/2016 | 2016 | 515 | 73.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-06-23 | 2016-07-09 | COMP | 2016-06-23 | 2016-07-11 | COMP | 2016-07-12 | 2016-07-12 | COMP | 2016-07-12 | 2016-08-23 | COMP | 2016-08-23 | 2016-11-16 | COMP | 2016-11-16 | 2016-11-16 | 19 | 127 | 16199.08
31170652 | +RECONDUCTOR 1700 FT- FAIRWAY 1103 | 07/21/2015 | 110526754 | 07/21/2015 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/30/2017 | ED.18267.1107 | SANTA MARIA 1107 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 1,771.000 | 1,770.000 | 08J | 2015 | 04/21/2018 | 2018 | 1005 | 143.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31170652_R5 RECONDUCTR 1700 FT ON SNTA M | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-10-13 | 2017-07-11 | COMP | 2016-10-13 | 2017-07-20 | COMP | 2017-07-20 | 2017-07-20 | COMP | 2017-07-20 | 2017-07-21 | COMP | 2017-07-21 | 2017-09-02 | COMP | 2017-09-02 | 2017-09-06 | 280 | 48 | 241067.48
31171405 | OCGC TULACAY 1101 WIRE DOWN AT LR 628 | 07/24/2015 | 110532349 | 07/24/2015 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 07/24/2017 | ED.04230.1101 | TULUCAY 1101 | 028 | NAPA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 3,236.000 | 3,236.000 | 08J | 2015 | 09/28/2019 | 2019 | 1527 | 218.1429 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31171405_R7 TULACAY 1101 WIRE DOWN AT LR | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2017-08-31 | 2017-08-31 | COMP | 2017-09-07 | 2017-09-07 | COMP | 2017-09-07 | 2017-09-07 | COMP | 2017-09-07 | 2017-09-08 | COMP | 2017-09-08 | 2017-09-22 | COMP | 2017-09-22 | 2017-09-27 | 7 | 20 | 327869.07
31171820 | WYANDOTTE 1105-DEADWOOD ROAD 08J Y2017 | 07/27/2015 | 110535043 | 07/26/2015 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/16/2017 | ED.17-T360000000 | PARADISE MAP T36 | 004 | BUTTE COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 8,515.000 | 8,515.000 | 08J | 2015 | 04/21/2018 | 2018 | 999 | 142.7143 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31171820_WYANDOTTE 1105 - DEADWOOD ROAD | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2017-12-14 | 2017-12-14 | COMP | 2017-12-15 | 2017-12-15 | COMP | 2017-12-15 | 2017-12-15 | COMP | 2017-12-15 | 2017-12-29 | COMP | 2017-12-29 | 2018-01-16 | COMP | 2018-01-16 | 2018-01-17 | 1 | 33 | 626708.82
31173137 | *CANC* CANAL 1104 RECOND 269FT 4AR TO | 07/31/2015 | 110543237 | 07/30/2015 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/13/2017 | ED.25209.1104 | CANAL 1104 | 024 | MERCED COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2015 | 07/06/2019 | 2019 | 1436 | 205.1429 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2019-07-06 | 2019-07-06 | # | 2019-07-06 | 2019-07-06 | # | 2019-07-06 | 2019-07-06 | # | 2019-07-06 | 2019-07-06 | # | 2019-07-06 | 2019-07-06 | # | 2019-07-06 | 2019-07-06 | 0 | 0 | 0
31173660 | OCGC SANTA ROSA A 1108 RECOND 6SPANS | 08/04/2015 | 110545426 | 07/31/2015 | # | Not assigned | 30 | Technically Completed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 06/30/2017 | ED.04215.1108.SWIT | SWITCHES | 049 | SONOMA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 1,097.000 | 0.000 | 08W | 2015 | # | OPEN | 1949 | 278.4286 | FICL | 10 | E070 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31173660_SANTA ROSA A 1108 RECOND 6SPANS | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-07-27 | 2016-08-11 | COMP | 2016-07-27 | 2016-08-15 | COMP | 2016-08-15 | 2016-08-15 | COMP | 2016-08-15 | 2016-09-13 | COMP | 2016-09-13 | 2016-12-16 | COMP | 2016-12-16 | 2016-12-16 | 19 | 123 | 228274.06
31174512 | OCGC 6-SPANS BODEGA AVE- PETALUMA 1108 | 08/07/2015 | 110557491 | 08/07/2015 | # | Not assigned | 30 | Technically Completed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 05/26/2017 | ED.04263.1108.SWIT | SWITCHES | 049 | SONOMA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 1,630.000 | 08J | 2015 | # | OPEN | 1946 | 278 | FICL | 10 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2018-07-19 | 2018-07-19 | COMP | 2018-07-23 | 2018-07-23 | COMP | 2018-07-23 | 2018-07-23 | COMP | 2018-07-23 | 2018-07-24 | COMP | 2018-07-24 | 2018-08-02 | COMP | 2018-08-02 | 2018-08-06 | 4 | 14 | 96484.31
31175108 | *CANC* R1-EB- R1127- RECOND 1,850' *CANC | 08/11/2015 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/31/2016 | ED.01347.1127 | RICHMOND R 1127 | 007 | CONTRA COSTA C | 5517127 | DO 08 - Monthly Forecast Only | 1,850.000 | 0.000 | 08J | 2015 | 05/03/2020 | 2020 | 1727 | 246.7143 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | COMP | 2020-04-09 | 2020-04-09 | COMP | 2020-04-09 | 2020-04-09 | COMP | 2020-04-09 | 2020-04-09 | 0 | -24 | 0
31175272 | OC4 OCGC EP HWY 193 RECONDUCTOR 4 SPANS | 08/11/2015 | # | #N/A | 30958463 | OC4 OCGC EP HWY 193 RELO NEWCASTLE | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/09/2015 | ED.20-U050000000.STRU.POLE | PLACER U05 POLES | 031 | PLACER COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 1,140.000 | 1,140.000 | 08J | 2015 | 04/22/2017 | 2017 | 620 | 88.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2015-09-30 | 2015-09-29 | COMP | 2015-09-30 | 2015-09-30 | COMP | 2015-10-08 | 2015-10-08 | COMP | 2015-10-08 | 2016-04-13 | COMP | 2016-04-13 | 2016-05-05 | COMP | 2016-05-05 | 2016-05-06 | 8 | 211 | 40188.33
31175501 | OCGC MALAGA 1102 NORTH AVE. WIRE DOWN | 08/12/2015 | 110570964 | 08/11/2015 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/27/2017 | ED.25425.1102 | MALAGA 1102 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 2,982.000 | 2,982.000 | 08J | 2015 | 01/20/2018 | 2018 | 892 | 127.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31175501_R2 MALAGA 1102 NORTH AVE. WIRE | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2017-10-31 | 2017-10-31 | COMP | 2017-08-02 | 2017-11-02 | COMP | 2017-11-03 | 2017-11-03 | COMP | 2017-11-03 | 2017-11-06 | COMP | 2017-11-06 | 2017-11-29 | COMP | 2017-11-29 | 2017-12-07 | 3 | 34 | 212336.87
31175815 | *CANC* SIQUOC 1104 WIREDOWN RECOND *CANC | 08/13/2015 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.18281.1104 | SISQUOC 1104 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2015 | 05/03/2020 | 2020 | 1725 | 246.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31175815_SIQUOC 1104 WIREDOWN RECONDUCTO | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | COMP | 2020-04-10 | 2020-04-10 | COMP | 2020-04-10 | 2020-04-10 | COMP | 2020-04-10 | 2020-04-10 | 0 | -23 | 0
31175817 | +OCEANO 1108 WIREDOWN 15-0043519 | 08/13/2015 | 110574855 | 08/13/2015 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/30/2017 | ED.18260.1108 | OCEANO 1108 | 040 | SAN LUIS OBISP | 5532479 | CWSP 08W - Monthly Forecast Only | 2,177.000 | 0.000 | 08W | 2015 | 02/11/2017 | 2017 | 548 | 78.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31175817_R2 OCEANO 1108 WIREDOWN 15-0043 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-09-07 | 2016-11-17 | COMP | 2016-09-07 | 2016-11-30 | COMP | 2016-11-30 | 2016-11-30 | COMP | 2016-11-30 | 2016-12-01 | COMP | 2016-12-01 | 2017-01-18 | COMP | 2017-01-18 | 2017-01-18 | 84 | 49 | 87077.03
31177369 | R5 SBWF FW 1107 & DIV 1104, HWY 1 & BLK | 08/20/2015 | 110584979 | 08/19/2015 | # | Not assigned | 30 | Technically Completed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/30/2020 | ED.18206.1107 | FAIRWAY 1107 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 6,972.000 | 6,867.000 | 08J | 2015 | # | OPEN | 1933 | 276.1429 | FICL | 10 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31177369_R2 SBWF ACSR REPLACEMENT SS DEV | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2020-03-06 | 2020-03-06 | COMP | 2020-03-31 | 2020-05-12 | COMP | 2020-05-12 | 2020-05-12 | COMP | 2020-05-12 | 2020-05-13 | COMP | 2020-05-13 | 2020-05-26 | COMP | 2020-05-26 | 2020-05-27 | 67 | 15 | 385075.23
31178055 | SBWF SM 1105 & 1109, N/O W MAIN, SM | 08/21/2015 | 110588965 | 08/21/2015 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2019 | ED.18267.1105 | SANTA MARIA 1105 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 4,292.000 | 4,292.000 | 08J | 2015 | # | OPEN | 1932 | 276 | DOCC | 8 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31178055_R5 SBWF ACSR REPLACEMENT Q4 FUS | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2019-09-26 | 2019-09-26 | COMP | 2019-11-13 | 2019-11-13 | COMP | 2019-11-13 | 2019-11-13 | COMP | 2019-11-13 | 2019-11-14 | COMP | 2019-11-14 | 2019-11-21 | COMP | 2019-11-21 | 2019-11-25 | 48 | 12 | 235553.05
31178774 | SANTA MARIA 1109, SPLICE COUNT REDUCTION | 08/25/2015 | 110590307 | 08/22/2015 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2017 | ED.18267.1109 | SANTA MARIA 1109 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2015 | # | OPEN | 1928 | 275.4286 | UNSE | 1 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 2181.65
31178776 | +WF RECOND 6044' FSE 65535 MESA 1102 | 08/25/2015 | 110590411 | 08/22/2015 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/30/2017 | ED.18282.1102 | MESA 1102 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 6,436.000 | 6,436.000 | 08J | 2015 | 08/05/2017 | 2017 | 711 | 101.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31178776_R5 SBWF RECOND 6044' FSE 65535 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2017-06-08 | 2017-06-08 | COMP | 2017-06-13 | 2017-06-13 | COMP | 2017-06-13 | 2017-06-13 | COMP | 2017-06-13 | 2017-06-14 | COMP | 2017-06-14 | 2017-07-03 | COMP | 2017-07-03 | 2017-07-28 | 5 | 45 | 227621.57
31178777 | MESA 1102 RANCHO GAUDALUPE PRESERVE | 08/25/2015 | 110590412 | 08/22/2015 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/30/2020 | ED.18282.1102 | MESA 1102 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 3,849.000 | 3,900.000 | 08J | 2015 | # | OPEN | 1928 | 275.4286 | MAPP | 9 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31178777_R5 RECOND 3,926' AT FUCO 6147 M | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2019-12-15 | 2019-12-15 | COMP | 2020-01-27 | 2020-09-28 | COMP | 2020-09-28 | 2020-09-28 | COMP | 2020-09-28 | 2020-11-24 | INPR | 2020-11-24 | 0 | # | 0 | 0 | 288 | -44102 | 408970.73
31178778 | SBWF SM 1110 NO BROWN RD, GUADALUPE | 08/25/2015 | 110590470 | 08/22/2015 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2018 | ED.18267.1110 | SANTA MARIA 1110 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 6,801.000 | 6,801.000 | 08J | 2015 | 08/29/2020 | 2020 | 1831 | 261.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31178778_R2 SBWF NO OF BROWN RD SANTA MA | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2018-01-22 | 2018-05-15 | COMP | 2020-01-28 | 2020-02-14 | COMP | 2020-02-14 | 2020-02-14 | COMP | 2020-02-14 | 2020-02-15 | COMP | 2020-02-15 | 2020-02-24 | COMP | 2020-02-24 | 2020-02-25 | 753 | 11 | 572217.9
31178779 | TO BE CANCELLED GUERNSEY 1106 RECON | 08/25/2015 | 110591852 | 08/24/2015 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/29/2017 | ED.25266.1106 | GUERNSEY 1106 | 016 | KINGS COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 694.000 | 0.000 | 08J | 2015 | 11/10/2018 | 2018 | 1173 | 167.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2018-11-10 | 2018-11-10 | # | 2018-11-10 | 2018-11-10 | # | 2018-11-10 | 2018-11-10 | # | 2018-11-10 | 2018-11-10 | # | 2018-11-10 | 2018-11-10 | # | 2018-11-10 | 2018-11-10 | 0 | 0 | 830.34
31178822 | WEST FRESNO 1111 RECONDUCTORING | 08/25/2015 | 110592149 | 08/24/2015 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 05/31/2017 | ED.25373.1111 | WEST FRESNO 1111 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 4,615.000 | 4,615.000 | 08J | 2015 | 04/21/2018 | 2018 | 970 | 138.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31178822_WEST FRESNO 1111 RECONDUCTORING | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2017-03-21 | 2017-05-17 | COMP | 2017-03-21 | 2017-06-16 | COMP | 2017-06-16 | 2017-06-22 | COMP | 2017-06-22 | 2017-06-23 | COMP | 2017-06-23 | 2017-08-09 | COMP | 2017-08-09 | 2017-08-09 | 93 | 48 | 205713.44
31179069 | RECONDUCTR 4CU ON J1110 WIREDOWN | 08/26/2015 | 110596932 | 08/26/2015 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/30/2016 | ED.01350.1110 | JARVIS 1110 | 001 | ALAMEDA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 440.000 | 08J | 2015 | 03/30/2019 | 2019 | 1312 | 187.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2017-10-09 | 2018-11-26 | COMP | 2018-11-10 | 2018-11-27 | COMP | 2018-11-27 | 2018-11-27 | COMP | 2018-11-27 | 2018-11-28 | COMP | 2018-11-28 | 2018-12-07 | COMP | 2018-12-07 | 2018-12-10 | 414 | 13 | 18493.75
31179237 | STONE 1110 RECONDUCTOR | 08/27/2015 | 110602784 | 08/26/2015 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/01/2017 | ED.08370.1110 | STONE 1110 | 043 | SANTA CLARA CO | 5535457 | DO 08 - Monthly Forecast Only | 295.000 | 280.000 | 08J | 2015 | 12/23/2017 | 2017 | 849 | 121.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2017-10-04 | 2017-10-04 | COMP | 2017-08-30 | 2017-10-19 | COMP | 2017-10-19 | 2017-10-19 | COMP | 2017-10-19 | 2017-10-20 | COMP | 2017-10-20 | 2017-11-15 | COMP | 2017-11-15 | 2017-11-20 | 15 | 32 | 92353.49
31179810 | OCGC REPLACE 7800' OF 6C ON CATLETT 1105 | 08/28/2015 | 110605023 | 08/27/2015 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2017 | ED.15376.1101.SWIT | SWITCHES | 051 | SUTTER COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 7,753.000 | 7,753.000 | 08J | 2015 | 12/22/2018 | 2018 | 1212 | 173.1429 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31179810_REPLACE 7800' OF 6C ON CATLETT | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2017-08-28 | 2017-08-28 | COMP | 2017-08-30 | 2017-08-30 | COMP | 2017-04-24 | 2017-08-30 | COMP | 2017-08-30 | 2017-08-31 | COMP | 2017-08-31 | 2017-09-19 | COMP | 2017-09-19 | 2017-09-22 | 2 | 23 | 743550.94
31180009 | +CAB 1104 SO CENTRAL & DE WOLFF, LOMPOC | 08/28/2015 | 110604817 | 08/27/2015 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2018 | ED.18281.1104 | SISQUOC 1104 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 1,400.000 | 1,400.000 | 08J | 2015 | 11/04/2019 | 2019 | 1529 | 218.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31180009_R2CABRILO 1104 WD RECNDUCTORING | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2018-10-17 | 2018-10-17 | COMP | 2017-08-09 | 2018-10-18 | COMP | 2018-10-18 | 2018-10-22 | COMP | 2018-10-22 | 2018-10-23 | COMP | 2018-10-23 | 2018-10-24 | COMP | 2018-10-24 | 2018-10-26 | 5 | 4 | 93348.46
31180010 | +CHOLAME 1101 WD RECONDUCTORING | 08/28/2015 | 110606328 | 08/28/2015 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2019 | ED.18256.1101 | CHOLAME 1101 | 040 | SAN LUIS OBISP | 5535457 | DO 08 - Monthly Forecast Only | 1,479.000 | 1,479.000 | 08J | 2015 | 09/05/2020 | 2020 | 1835 | 262.1429 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31180010_R5 CHOLAME 1101 WD RECONDUCORIN | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2019-09-21 | 2019-09-21 | COMP | 2019-11-13 | 2019-11-13 | COMP | 2019-11-13 | 2019-11-13 | COMP | 2019-11-13 | 2019-11-14 | COMP | 2019-11-14 | 2019-11-21 | COMP | 2019-11-21 | 2019-11-22 | 53 | 9 | 123596.98
31181229 | 2017WEST FRESNO 1112 RECOND MARKS AVE | 09/02/2015 | 110612424 | 09/01/2015 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 05/31/2018 | ED.25373.1112 | WEST FRESNO 1112 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 2,485.000 | 2,942.000 | 08J | 2015 | 03/23/2019 | 2019 | 1298 | 185.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31181229_R2 2017WEST FRESNO 1112 RECOND | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2018-08-17 | 2018-07-30 | COMP | 2018-03-20 | 2018-08-17 | COMP | 2018-08-17 | 2018-08-17 | COMP | 2018-08-17 | 2018-08-20 | COMP | 2018-08-20 | 2018-08-23 | COMP | 2018-08-23 | 2018-08-27 | 0 | 10 | 413489.1
31181527 | RECONDUCTOR 4ACSR ON N1106_WIREDOWN | 09/04/2015 | 110618313 | 09/03/2015 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/30/2016 | ED.01222.1106.TXFR.TRSS | SUBSURFACE TRANSFORMERS | 001 | ALAMEDA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 429.000 | 180.000 | 08J | 2015 | 01/20/2018 | 2018 | 869 | 124.1429 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2017-10-09 | 2017-10-09 | COMP | 2017-11-02 | 2017-11-02 | COMP | 2017-11-02 | 2017-11-02 | COMP | 2017-11-02 | 2017-11-03 | COMP | 2017-11-03 | 2017-11-29 | COMP | 2017-11-29 | 2017-11-30 | 24 | 28 | 27340.1
31182216 | RECON 11-SPANS (MADISON&MARIA) PET 1105 | 09/08/2015 | 110623679 | 09/08/2015 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/03/2017 | ED.04263.1105.SWIT | SWITCHES | 049 | SONOMA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 3,924.000 | 0.000 | 08J | 2015 | # | OPEN | 1914 | 273.4286 | PEND | 5 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 82807.18
31183281 | *CANC* W FRESNO 1111 - RECOND PH II*CANC | 09/11/2015 | 110625900 | 09/09/2015 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/07/2017 | ED.25373.1111 | WEST FRESNO 1111 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2015 | 09/03/2020 | 2020 | 1819 | 259.8571 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2020-09-03 | 2020-09-03 | # | 2020-09-03 | 2020-09-03 | # | 2020-09-03 | 2020-09-03 | COMP | 2020-08-19 | 2020-08-19 | COMP | 2020-08-19 | 2020-08-19 | COMP | 2020-08-19 | 2020-08-19 | 0 | -15 | 0
31185022 | R2 WF 1111 RECONDUCTOR - VALENTINE AVE. | 09/16/2015 | 110644619 | 09/15/2015 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 07/30/2020 | ED.25373.1111 | WEST FRESNO 1111 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 2,720.000 | 2,720.000 | 08J | 2015 | # | OPEN | 1906 | 272.2857 | MAPP | 9 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31185022_R2 WF 1111 RECONDUCTOR - VALENT | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2020-07-24 | 2020-07-24 | COMP | 2020-10-14 | 2020-10-14 | COMP | 2020-10-14 | 2020-10-14 | INPR | 2020-11-02 | 0 | # | 0 | 0 | # | 0 | 0 | 82 | -44118 | 334856.86
31185480 | R2Z WDN 15-54205 PS2106-BAY AVE | 09/18/2015 | 110653012 | 09/17/2015 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/20/2017 | ED.08325.2106 | PAUL SWEET 2106 | 044 | SANTA CRUZ COU | 5535457 | DO 08 - Monthly Forecast Only | 627.000 | 0.000 | 08J | 2015 | # | OPEN | 1904 | 272 | UNSC | 6 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | INPR | 2017-09-29 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | -43007 | 0 | 31423.8
31186256 | SANTA MARIA CONDUCTOR REPLACEMENT | 09/23/2015 | 110659272 | 09/22/2015 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2017 | ED.18267.1109 | SANTA MARIA 1109 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2015 | # | OPEN | 1899 | 271.2857 | UNSE | 1 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 2804.98
31186541 | XSPENCE1121 WD INITIATED RECNDCUTORIN | 09/24/2015 | 110662679 | 09/23/2015 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/29/2017 | ED.18220.1121 | SPENCE 1121 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 713.000 | 713.000 | 08J | 2015 | 07/20/2019 | 2019 | 1395 | 199.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2018-09-26 | 2018-09-26 | COMP | 2018-10-01 | 2018-10-01 | COMP | 2018-10-01 | 2018-10-01 | COMP | 2018-10-01 | 2018-10-02 | COMP | 2018-10-02 | 2018-10-11 | COMP | 2018-10-11 | 2018-10-12 | 5 | 11 | 47402.87
31186569 | SBWF CAB 1104 UNION SGR & CNTRL, LOMPOC | 09/24/2015 | 110664322 | 09/23/2015 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/30/2020 | ED.18310.1104 | CABRILLO 1104 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 7,750.000 | 7,880.000 | 08J | 2015 | # | OPEN | 1898 | 271.1429 | DOCC | 8 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31186569_SBWF LOMPOC WEST QUADRANT, CABR | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2019-12-19 | 2019-12-19 | COMP | 2020-07-14 | 2020-07-14 | COMP | 2020-07-14 | 2020-07-14 | COMP | 2020-07-14 | 2020-07-16 | COMP | 2020-07-16 | 2020-07-21 | COMP | 2020-07-21 | 2020-07-22 | 208 | 8 | 349224.03
31187281 | ANNEAL OVRHEAD@50395 SOUTHSIDE_HL210 | 09/28/2015 | 110669987 | 09/25/2015 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 08/31/2017 | ED.18249.2106 | HOLLISTER 2106 | 035 | SAN BENITO COU | 5535457 | DO 08 - Monthly Forecast Only | 468.000 | 0.000 | 08J | 2015 | # | OPEN | 1894 | 270.5714 | CONS | 7 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | INPR | 2017-10-30 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | -43038 | 0 | 81189.24
31191256 | RECNDUCTOR 4ACSR ON EDES1111-WIREDOWN | 10/14/2015 | 110720189 | 10/13/2015 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/29/2017 | ED.01368.1111.TXFR.TRSS | SUBSURFACE TRANSFORMERS | 001 | ALAMEDA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 654.000 | 654.000 | 08J | 2015 | 09/28/2019 | 2019 | 1445 | 206.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2017-05-07 | 2017-05-07 | COMP | 2017-05-11 | 2017-05-11 | COMP | 2017-05-11 | 2017-05-11 | COMP | 2017-05-11 | 2017-05-16 | COMP | 2017-05-16 | 2017-05-16 | COMP | 2017-05-16 | 2017-05-16 | 4 | 5 | 48217.54
31193590 | +R5 DIVIDE 1102 WD RECONDUCTORING | 10/21/2015 | 110677980 | 09/28/2015 | # | Not assigned | 30 | Technically Completed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/30/2020 | ED.18282.1102 | MESA 1102 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 1,080.000 | 1,080.000 | 08J | 2015 | # | OPEN | 1871 | 267.2857 | FICL | 10 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31193590_DIVIDE 1102 WD RECONDUCTORING | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2020-02-12 | 2020-02-12 | COMP | 2020-03-31 | 2020-05-12 | COMP | 2020-05-12 | 2020-05-12 | COMP | 2020-05-12 | 2020-05-13 | COMP | 2020-05-13 | 2020-05-19 | COMP | 2020-05-19 | 2020-05-27 | 90 | 15 | 326101.26
31193592 | +SBWF-BONITA LATERAL-SANTA MARIA 1105 | 10/21/2015 | 110768828 | 10/20/2015 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 08/30/2017 | ED.18266.1105 | SAN MIGUEL 1105 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 7,318.000 | 7,316.000 | 08J | 2015 | 01/20/2018 | 2018 | 822 | 117.4286 | PREC | 11 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31193592_R5 SBWF-BONITA LATERAL -SANTA M | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2017-05-31 | 2017-08-31 | COMP | 2017-05-31 | 2017-09-11 | COMP | 2017-09-11 | 2017-09-11 | COMP | 2017-09-11 | 2017-09-12 | COMP | 2017-09-12 | 2017-11-07 | COMP | 2017-11-07 | 2017-11-15 | 103 | 65 | 307725.37
31193593 | SBWF MESA 1102 SO DIVISION ST, GUADALUPE | 10/21/2015 | 110770251 | 10/20/2015 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2018 | ED.18282.1102 | MESA 1102 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 5,814.000 | 5,750.000 | 08J | 2015 | 05/30/2020 | 2020 | 1683 | 240.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31193593_R5 SBWF-SSD: FUSE 45425 - MESA | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2018-01-19 | 2018-09-01 | COMP | 2019-03-22 | 2019-03-22 | COMP | 2019-03-22 | 2019-03-22 | COMP | 2019-05-24 | 2019-09-10 | COMP | 2019-09-10 | 2019-09-11 | COMP | 2019-09-11 | 2019-09-12 | 427 | 174 | 385299.21
31193954 | *CANC* R5 SBWF- MAIN STREET *CANC | 10/21/2015 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.18267.1109 | SANTA MARIA 1109 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 6,590.000 | 0.000 | 08J | 2015 | 05/03/2020 | 2020 | 1656 | 236.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31193954_SBWF- MAIN STREET | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | COMP | 2020-04-10 | 2020-04-10 | COMP | 2020-04-10 | 2020-04-10 | COMP | 2020-04-10 | 2020-04-10 | 0 | -23 | 0
31193955 | +SBWF MESA 1102 NO DIVISION ST, GUADALUP | 10/21/2015 | 110771720 | 10/20/2015 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 08/31/2020 | ED.18282.1102 | MESA 1102 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 12,479.000 | 12,479.000 | 08J | 2015 | # | OPEN | 1871 | 267.2857 | FICL | 10 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31193955_R5 SBWF- SSD: FUSE 6527 - MESA | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2017-12-13 | 2020-08-21 | COMP | 2017-10-03 | 2020-09-30 | COMP | 2020-09-30 | 2020-09-30 | COMP | 2020-09-30 | 2020-11-02 | COMP | 2020-11-02 | 2020-11-09 | COMP | 2020-11-09 | 2020-11-11 | 1022 | 42 | 533669.74
31193990 | MVWF NEAR 99 GREENWOOD WY,ALTO 1124 | 10/21/2015 | 110760456 | 10/19/2015 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/05/2017 | ED.04203.1124 | ALTO 1124 | 021 | MARIN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 2,656.000 | 2,660.000 | 08J | 2015 | 07/20/2019 | 2019 | 1368 | 195.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31193990_R7 ALTO 1124 MVWF CU REPLACE | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2017-08-19 | 2017-08-19 | COMP | 2017-09-08 | 2017-09-08 | COMP | 2017-09-08 | 2017-12-20 | COMP | 2017-12-20 | 2018-12-03 | COMP | 2018-12-03 | 2018-12-03 | COMP | 2018-12-03 | 2018-12-06 | 123 | 351 | 860674.8
31194557 | 2017 LAMONT 1105 WIREDWN 3 SPAN RECO | 10/24/2015 | 110808007 | 10/23/2015 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/29/2017 | ED.25391.1105.SWIT | SWITCHES | 015 | KERN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 884.000 | 884.000 | 08J | 2015 | 05/12/2018 | 2018 | 931 | 133 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2018-01-29 | 2018-02-22 | COMP | 2018-02-23 | 2018-02-23 | COMP | 2018-02-23 | 2018-02-23 | COMP | 2018-02-23 | 2018-02-26 | COMP | 2018-02-26 | 2018-03-01 | COMP | 2018-03-01 | 2018-03-02 | 25 | 7 | 68681.4
31195933 | ANITA 1106 - REPLACE 2 SPANS & RELOCATE | 10/28/2015 | 110816176 | 10/28/2015 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/30/2018 | ED.16-T280700000 | CHICO MAP T2807 | 004 | BUTTE COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 375.000 | 375.000 | 08J | 2015 | 11/21/2020 | 2020 | 1851 | 264.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-11-20 | 2019-11-14 | COMP | 2016-11-20 | 2019-11-21 | COMP | 2019-11-21 | 2019-11-21 | COMP | 2019-11-21 | 2019-11-22 | COMP | 2019-11-22 | 2019-12-12 | COMP | 2019-12-12 | 2019-12-12 | 1096 | 21 | 60717.97
31197019 | *CANC* WEBER 1102 RECONDUCTORING - *CANC | 11/03/2015 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2019 | ED.16348.1102 | WEBER 1102 | 039 | SAN JOAQUIN CO | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2015 | 04/04/2020 | 2020 | 1614 | 230.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | WEBER 1102 RECONDUCTORING - 08J | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2020-04-04 | 2020-04-04 | # | 2020-04-04 | 2020-04-04 | # | 2020-04-04 | 2020-04-04 | # | 2020-04-04 | 2020-04-04 | # | 2020-04-04 | 2020-04-04 | # | 2020-04-04 | 2020-04-04 | 0 | 0 | 0
31197080 | +SM 1109 RAY RD SO MAIN, SANTA MARIA | 11/03/2015 | 110823732 | 10/30/2015 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2019 | ED.18267.1109 | SANTA MARIA 1109 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 6,128.000 | 6,128.000 | 08J | 2015 | # | OPEN | 1858 | 265.4286 | DOCC | 8 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31197080_SANTA MARIA SPLICE COUNT REDUCT | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2019-10-18 | 2019-10-18 | COMP | 2017-08-24 | 2019-11-05 | COMP | 2019-11-05 | 2019-11-14 | COMP | 2019-11-14 | 2019-11-14 | COMP | 2019-11-14 | 2019-11-25 | COMP | 2019-11-25 | 2019-11-26 | 27 | 12 | 310674.28
31197255 | EFFEY ST-PS2108-WDW-15-0060680 | 11/03/2015 | 110828922 | 11/03/2015 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 08/26/2017 | ED.08325.2108 | PAUL SWEET 2108 | 044 | SANTA CRUZ COU | 5535457 | DO 08 - Monthly Forecast Only | 272.000 | 0.000 | 08J | 2015 | # | OPEN | 1858 | 265.4286 | CONS | 7 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | INPR | 2018-04-16 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | -43206 | 0 | 70764.03
31197256 | *CANC*SBWF LOMPOC S-QUADRANT-CABRIL*CANC | 11/03/2015 | 110829208 | 11/03/2015 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/01/2017 | ED.18310.1104 | CABRILLO 1104 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2015 | 11/03/2018 | 2018 | 1096 | 156.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2018-11-03 | 2018-11-03 | # | 2018-11-03 | 2018-11-03 | # | 2018-11-03 | 2018-11-03 | # | 2018-11-03 | 2018-11-03 | # | 2018-11-03 | 2018-11-03 | # | 2018-11-03 | 2018-11-03 | 0 | 0 | 0
31197754 | OCGC RECON4SPANS CANYON ROCK MIRABEL1101 | 11/05/2015 | 110835287 | 11/05/2015 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/29/2017 | ED.04209.1101.SWIT | SWITCHES | 049 | SONOMA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 923.000 | 1,100.000 | 08J | 2015 | 03/25/2017 | 2017 | 506 | 72.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2016-10-11 | 2016-10-24 | COMP | 2016-10-11 | 2016-10-24 | COMP | 2016-10-24 | 2016-10-24 | COMP | 2016-10-24 | 2017-02-02 | COMP | 2017-02-02 | 2017-02-24 | COMP | 2017-02-24 | 2017-02-24 | 13 | 123 | 104177.5
31200934 | MVWF CALIFRNIA<(>&<)>PRINCTON, ALTO 1125 | 11/18/2015 | 110860125 | 11/17/2015 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 08/31/2017 | ED.04203.1125 | ALTO 1125 | 021 | MARIN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 2,682.000 | 2,680.000 | 08J | 2015 | 07/21/2018 | 2018 | 976 | 139.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31200934_R7 ALTO 1125 MVWF CU REPLACE | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2017-09-16 | 2017-09-16 | COMP | 2017-09-29 | 2017-12-18 | COMP | 2017-12-18 | 2017-12-18 | COMP | 2017-12-18 | 2018-01-02 | COMP | 2018-01-02 | 2018-01-08 | COMP | 2018-01-08 | 2018-01-08 | 93 | 21 | 481511.33
31200935 | MVWF ROSEMONT & JULIA ST.ALTO 1120 | 11/18/2015 | 110852792 | 11/13/2015 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/28/2017 | ED.04203.1120 | ALTO 1120 | 021 | MARIN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 3,025.000 | 2,864.000 | 08J | 2015 | 06/17/2018 | 2018 | 942 | 134.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31200935_R7 ALTO 1120 MVWF CU REPLACE | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2017-07-26 | 2017-07-26 | COMP | 2017-08-03 | 2017-08-03 | COMP | 2017-08-03 | 2017-12-20 | COMP | 2017-12-20 | 2017-12-26 | COMP | 2017-12-26 | 2018-01-05 | COMP | 2018-01-05 | 2018-01-05 | 147 | 16 | 503819.78
31202926 | REMOVE SPLICES AND INSTALL FUSES | 11/25/2015 | 110878696 | 11/24/2015 | # | Not assigned | 30 | Technically Completed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/15/2016 | ED.02425.1105.SWIT | SWITCHES | 041 | SAN MATEO COUN | 5505513 | PN-OH ANNEALED/DETER CNDCTR: PM MGD | 419.000 | 419.000 | 08J | 2015 | # | OPEN | 1836 | 262.2857 | FICL | 10 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2018-05-23 | 2020-02-28 | COMP | 2020-03-03 | 2020-03-03 | COMP | 2020-03-03 | 2020-03-03 | COMP | 2020-03-03 | 2020-03-03 | COMP | 2020-03-03 | 2020-03-27 | COMP | 2020-03-27 | 2020-03-30 | 650 | 27 | 130470.2
31203813 | MVWF STINSON BEACH, BOLINAS 1101 | 12/02/2015 | 110890008 | 12/02/2015 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/14/2017 | ED.04226.1101 | BOLINAS 1101 | 021 | MARIN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 7,378.000 | 0.000 | 08J | 2015 | # | OPEN | 1829 | 261.2857 | CONS | 7 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31203813_R7 BOLINAS 1101, REPLACE 9600' | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 923227.52
31204479 | RECOND 3 SPANS GARDEN TRACT | 12/08/2015 | 110939159 | 12/04/2015 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/28/2016 | ED.01347.1129.TXFR.TROH | OVERHEAD TRANSFORMERS | 007 | CONTRA COSTA C | 5532479 | CWSP 08W - Monthly Forecast Only | 362.000 | 1,050.000 | 08W | 2015 | 01/20/2018 | 2018 | 774 | 110.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2017-09-22 | 2017-11-12 | COMP | 2017-09-25 | 2017-12-07 | COMP | 2017-12-07 | 2017-12-07 | COMP | 2017-12-07 | 2017-12-12 | COMP | 2017-12-12 | 2017-12-13 | COMP | 2017-12-13 | 2017-12-14 | 76 | 7 | 82415.52
31204517 | *DO NOT USE* R4E RECONDUCTOR LIBERTY ISL | 12/07/2015 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.48-R190000000.STRU.POLE | SOLANO R19 POLES | 048 | SOLANO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2015 | 03/14/2020 | 2020 | 1559 | 222.7143 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31204517_R4E RECONDUCTOR LIBERTY ISLND-D | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2020-03-14 | 2020-03-14 | # | 2020-03-14 | 2020-03-14 | # | 2020-03-14 | 2020-03-14 | # | 2020-03-14 | 2020-03-14 | # | 2020-03-14 | 2020-03-14 | # | 2020-03-14 | 2020-03-14 | 0 | 0 | -7159.11
31204706 | MVWF THROCKMORTON LANE ALTO 1124 | 12/07/2015 | 110886052 | 12/01/2015 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/12/2017 | ED.04203.1124 | ALTO 1124 | 021 | MARIN COUNTY | 5535211 | CWSP SPO - SH 08 | 1,505.000 | 1,613.000 | 08W | 2015 | 11/04/2019 | 2019 | 1428 | 204 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | 31204706_MVWF THROCKMORTON LANE ALTO 112 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2018-12-11 | 2018-08-01 | COMP | 2017-09-13 | 2018-12-11 | COMP | 2018-12-11 | 2018-12-11 | COMP | 2018-12-11 | 2018-12-12 | COMP | 2018-12-12 | 2018-12-14 | COMP | 2018-12-14 | 2018-12-17 | 0 | 6 | 528490.2
31204707 | MVWF INT KING ST<(>&<)>CORTE MADERA ALTO | 12/07/2015 | 110886059 | 12/01/2015 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/31/2017 | ED.04203.1124 | ALTO 1124 | 021 | MARIN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 1,142.000 | 1,130.000 | 08J | 2015 | 11/05/2019 | 2019 | 1429 | 204.1429 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31204707_ KING ST&CORTE MADERA ALTO 1124 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2017-08-24 | 2017-12-15 | COMP | 2017-12-20 | 2018-02-07 | COMP | 2018-02-07 | 2018-02-07 | COMP | 2018-02-07 | 2018-02-08 | COMP | 2018-02-08 | 2018-02-09 | COMP | 2018-02-09 | 2018-02-12 | 167 | 5 | 424069.61
31205198 | MVWF 206 REED ST, COUNTY, ALTO 1125 | 12/10/2015 | 110886258 | 12/01/2015 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/27/2017 | ED.04203.1125 | ALTO 1125 | 021 | MARIN COUNTY | 5535211 | CWSP SPO - SH 08 | 3,828.000 | 3,900.000 | 08W | 2015 | 11/04/2019 | 2019 | 1425 | 203.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | 31205198_MVWF NEAR 206 REED ST ALTO 1125 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2018-06-05 | 2018-07-16 | COMP | 2018-07-18 | 2018-10-02 | COMP | 2018-10-02 | 2018-10-02 | COMP | 2018-10-02 | 2018-10-03 | COMP | 2018-10-03 | 2018-10-09 | COMP | 2018-10-09 | 2018-10-17 | 119 | 15 | 962856.9
31205258 | *CANC*DONOT USE* MARYSVILLE 1107-GR*CANC | 12/10/2015 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/30/2016 | ED.15201.1107.TXFR.TROH | OVERHEAD TRANSFORMERS | 051 | SUTTER COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 1,200.000 | 0.000 | 08J | 2015 | 05/03/2020 | 2020 | 1606 | 229.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | COMP | 2020-04-09 | 2020-04-09 | COMP | 2020-04-09 | 2020-04-09 | COMP | 2020-04-09 | 2020-04-09 | 0 | -24 | 0
31205340 | MVWF RALSTON AVE ALTO 1124 | 12/10/2015 | 110886079 | 12/01/2015 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/29/2017 | ED.04203.1124 | ALTO 1124 | 021 | MARIN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 3,555.000 | 3,700.000 | 08J | 2015 | 09/12/2020 | 2020 | 1738 | 248.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31205340_R7 MVWF RALSTON AVE ALTO 1124 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2017-12-04 | 2017-12-04 | COMP | 2017-12-06 | 2017-12-27 | COMP | 2017-12-27 | 2017-12-27 | COMP | 2017-12-27 | 2020-08-11 | COMP | 2020-08-11 | 2020-08-25 | COMP | 2020-08-25 | 2020-08-26 | 23 | 973 | 869637.78
31205342 | MVWF 31083407 NEAR 397 ROSE AV ALTO 1124 | 12/10/2015 | 110886302 | 12/01/2015 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/20/2017 | ED.04203.1124 | ALTO 1124 | 021 | MARIN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 1,636.000 | 1,650.000 | 08J | 2015 | 05/12/2018 | 2018 | 884 | 126.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31205342_MVWF NEAR 397 ROSE AVE ALTO1124 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2017-08-21 | 2017-11-07 | COMP | 2017-09-25 | 2017-11-30 | COMP | 2017-11-30 | 2017-11-30 | COMP | 2017-11-30 | 2017-12-04 | COMP | 2017-12-04 | 2017-12-06 | COMP | 2017-12-06 | 2017-12-26 | 101 | 26 | 665442.42
31205343 | MVWF 388 SUMMIT AVE, CITY, ALTO 1124 | 12/10/2015 | 110886303 | 12/01/2015 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/21/2017 | ED.04203.1124 | ALTO 1124 | 021 | MARIN COUNTY | 5535211 | CWSP SPO - SH 08 | 4,941.000 | 5,006.000 | 08W | 2015 | 11/04/2019 | 2019 | 1425 | 203.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | 31205343_MVWF_388 SUMMIT AVE ALTO 1124 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2018-11-02 | 2018-09-11 | COMP | 2018-06-11 | 2018-11-02 | COMP | 2018-11-02 | 2018-11-02 | COMP | 2018-11-02 | 2018-11-05 | COMP | 2018-11-05 | 2018-11-14 | COMP | 2018-11-14 | 2018-11-15 | 0 | 13 | 1154944.07
31205418 | MVWF BROOKLINE AVE, COUNTY, ALTO 1125 | 12/11/2015 | 111076172 | 12/10/2015 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/20/2017 | ED.04203.1125 | ALTO 1125 | 021 | MARIN COUNTY | 5535211 | CWSP SPO - SH 08 | 5,485.000 | 5,480.000 | 08W | 2015 | 04/20/2019 | 2019 | 1226 | 175.1429 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | 31205418_R7 MVWF BROOKLINE AVE ALTO 1125 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2018-10-02 | 2018-07-26 | COMP | 2018-07-31 | 2018-10-02 | COMP | 2018-10-02 | 2018-10-02 | COMP | 2018-10-02 | 2018-10-03 | COMP | 2018-10-03 | 2018-10-06 | COMP | 2018-10-06 | 2018-10-11 | 0 | 9 | 994666.01
31205937 | 109 HELENS LN,CITY/CNTY,ALTO | 12/14/2015 | 110886301 | 12/01/2015 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/25/2018 | ED.04203.1125 | ALTO 1125 | 021 | MARIN COUNTY | 5535211 | CWSP SPO - SH 08 | 4,464.000 | 5,000.000 | 08W | 2015 | 03/23/2019 | 2019 | 1195 | 170.7143 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | 31205937_MVWF 109 HELENS LANE ALTO 1125 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2017-11-17 | 2018-09-16 | COMP | 2018-12-17 | 2018-12-17 | COMP | 2018-12-17 | 2018-12-17 | COMP | 2018-12-17 | 2018-12-18 | COMP | 2018-12-18 | 2018-12-20 | COMP | 2018-12-20 | 2018-12-21 | 395 | 4 | 1275048.82
31206324 | GABILAN 1101 WIREDWN RECNDUCTORIN | 12/15/2015 | 111092247 | 12/14/2015 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/16/2017 | ED.18233.1101 | GABILAN 1101 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 635.000 | 635.000 | 08J | 2015 | # | OPEN | 1816 | 259.4286 | DOCC | 8 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2017-10-12 | 2018-09-21 | INPR | 2020-06-25 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | -43020 | 0 | 70299.21
31206677 | OCGC MOHAWK AV CORTE MADERA GREENBRA | 12/16/2015 | 111097628 | 12/15/2015 | # | Not assigned | 30 | Technically Completed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 01/10/2018 | ED.04309.1103 | GREENBRAE 1103 | 021 | MARIN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 4,851.000 | 4,851.000 | 08J | 2015 | # | OPEN | 1815 | 259.2857 | FICL | 10 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31206677_CORTE MADERA CORROSION | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2017-09-13 | 2018-11-05 | COMP | 2018-11-06 | 2018-11-06 | COMP | 2018-11-06 | 2018-11-06 | COMP | 2018-11-06 | 2018-11-07 | COMP | 2018-11-07 | 2018-11-26 | COMP | 2018-11-26 | 2018-11-26 | 419 | 20 | 711641.55
31206678 | MVWF SEQUOIA VLY RD CTY/CNTY AL1125/1124 | 12/16/2015 | 111098508 | 12/15/2015 | # | Not assigned | 30 | Technically Completed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 02/22/2018 | ED.04203.1125 | ALTO 1125 | 021 | MARIN COUNTY | 5535211 | CWSP SPO - SH 08 | 2,817.000 | 0.000 | 08W | 2015 | # | OPEN | 1815 | 259.2857 | FICL | 10 | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | 31206678_SEQUOIA VALLEY RD ALTO1125/1124 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2017-08-24 | 2019-04-09 | COMP | 2019-05-15 | 2020-01-23 | COMP | 2020-01-23 | 2020-01-23 | COMP | 2020-01-23 | 2020-05-04 | COMP | 2020-05-04 | 2020-05-19 | COMP | 2020-05-19 | 2020-05-21 | 882 | 119 | 930103.48
31206912 | X WDN 15-0073161 CE2103-OLD GRAHM HL R | 12/17/2015 | 111108421 | 12/16/2015 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/24/2017 | ED.08362.2103 | CAMP EVERS 2103 | 044 | SANTA CRUZ COU | 5535211 | CWSP SPO - SH 08 | 919.000 | 705.000 | 08W | 2015 | 12/28/2019 | 2019 | 1472 | 210.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2018-05-04 | 2018-07-12 | COMP | 2018-07-30 | 2018-07-30 | COMP | 2018-07-30 | 2018-07-30 | COMP | 2018-08-01 | 2018-08-16 | COMP | 2018-08-16 | 2018-08-17 | COMP | 2018-08-17 | 2018-08-20 | 87 | 21 | 134573.17
31207089 | ESA BOULEVARD ORNE AVE, LARKSPUR GB 1103 | 12/16/2015 | 111097626 | 12/15/2015 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/15/2017 | ED.04309.1103 | GREENBRAE 1103 | 021 | MARIN COUNTY | 5535211 | CWSP SPO - SH 08 | 5,123.000 | 4,890.000 | 08W | 2015 | 06/29/2019 | 2019 | 1291 | 184.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | 31207089_LARKSPUR WF HAWTHORNE AVE | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2017-10-30 | 2018-09-25 | COMP | 2018-12-18 | 2018-12-18 | COMP | 2018-12-18 | 2018-12-18 | COMP | 2018-12-18 | 2018-12-19 | COMP | 2018-12-19 | 2018-12-20 | COMP | 2018-12-20 | 2018-12-21 | 414 | 3 | 1092736.57
31207090 | MVWF VIEWPOINT RD TENNVLY CNTY ALTO 1125 | 12/16/2015 | 111104615 | 12/16/2015 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/02/2018 | ED.04203.1125 | ALTO 1125 | 021 | MARIN COUNTY | 5535211 | CWSP SPO - SH 08 | 6,861.000 | 6,500.000 | 08W | 2015 | # | OPEN | 1815 | 259.2857 | DOCC | 8 | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | 31207090_R7 MVWF VIEWPOINT RD ALTO 1125 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2020-05-21 | 2020-05-08 | INPR | 2020-05-05 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | -43972 | 0 | 1993422.67
31207091 | MVWF BUENA VISTA AVE, CITY ALTO 1124 | 12/16/2015 | 110886251 | 12/01/2015 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/29/2017 | ED.04203.1124 | ALTO 1124 | 021 | MARIN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 2,998.000 | 2,998.000 | 08J | 2015 | # | OPEN | 1815 | 259.2857 | DOCC | 8 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31207091_ MVWF BUENA VISTA AVE ALTO 1124 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2020-03-16 | 2020-03-16 | COMP | 2020-03-17 | 2020-10-07 | COMP | 2020-10-07 | 2020-10-07 | INPR | 2020-10-07 | 0 | # | 0 | 0 | # | 0 | 0 | 205 | -44111 | 1164788.98
31207126 | MVWF PANORAMIC HWY, COUNTY, ALTO 1125 | 12/17/2015 | 111104617 | 12/16/2015 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 01/25/2018 | ED.04203.1125 | ALTO 1125 | 021 | MARIN COUNTY | 5535211 | CWSP SPO - SH 08 | 5,141.000 | 5,300.000 | 08W | 2015 | 07/20/2019 | 2019 | 1311 | 187.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | 31207126_PANORAMIC HIGHWAY ALTO 1125 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2017-10-20 | 2018-07-18 | COMP | 2018-07-19 | 2018-10-03 | COMP | 2018-10-03 | 2018-10-03 | COMP | 2018-10-03 | 2018-10-04 | COMP | 2018-10-04 | 2018-10-23 | COMP | 2018-10-23 | 2018-10-24 | 348 | 21 | 1419528.55
31207128 | *CANC* MVWF ALTO 1125 MUIR WOOD DR *CANC | 12/17/2015 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2017 | ED.04203.1125 | ALTO 1125 | 021 | MARIN COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2015 | 05/03/2020 | 2020 | 1599 | 228.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | 31207128_Alto 1125 Muir Wood | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | 0 | 0 | 0
31207160 | +SANTA MARIA 1108 WD 15-076543 | 12/17/2015 | 111102564 | 12/16/2015 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/30/2017 | ED.18267.1108 | SANTA MARIA 1108 | 042 | SANTA BARBARA | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 3,297.000 | 08W | 2015 | 12/22/2018 | 2018 | 1101 | 157.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31207160_SANTA MARIA 1108 WD 15-0076534 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2017-06-22 | 2017-09-25 | COMP | 2017-06-22 | 2017-10-10 | COMP | 2017-10-10 | 2017-10-11 | COMP | 2017-10-11 | 2017-10-11 | COMP | 2017-10-11 | 2017-11-07 | COMP | 2017-11-07 | 2017-11-13 | 111 | 33 | 210979.84
31207161 | *CANC*DONOT USE*MORRO BAY 1102 WD 1*CANC | 12/17/2015 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.18301.1102 | MORRO BAY 1102 | 040 | SAN LUIS OBISP | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2015 | 05/03/2020 | 2020 | 1599 | 228.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31207161_MORRO BAY 1102 WD 15-006745 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | 0 | 0 | 0
31207264 | BRENTWOOD 2112-RECOND 616 FEET OF | 12/17/2015 | 111109401 | 12/17/2015 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/01/2017 | ED.01459.2112 | BRENTWOOD 2112 | 007 | CONTRA COSTA C | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 595.000 | 08J | 2015 | 12/12/2018 | 2018 | 1091 | 155.8571 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2018-02-12 | 2018-08-31 | COMP | 2018-07-19 | 2018-09-21 | COMP | 2018-09-21 | 2018-09-21 | COMP | 2018-09-21 | 2018-09-24 | COMP | 2018-09-24 | 2018-09-25 | COMP | 2018-09-25 | 2018-09-26 | 221 | 5 | 66687.88
31207439 | OCCC HMB1101 CO2751 REPL 8CU CONDUCTOR | 12/18/2015 | 111110265 | 12/17/2015 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 05/31/2017 | ED.02410.1101.TXFR.TROH | OVERHEAD TRANSFORMERS | 041 | SAN MATEO COUN | 5505513 | PN-OH ANNEALED/DETER CNDCTR: PM MGD | 2,442.000 | 2,442.000 | 08J | 2015 | 10/21/2017 | 2017 | 673 | 96.1429 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31207439_HMB1101 CO2751 REPL 8CU CONDUCT | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2017-04-24 | 2017-05-20 | COMP | 2017-04-24 | 2017-07-05 | COMP | 2017-07-05 | 2017-07-05 | COMP | 2017-07-05 | 2017-07-06 | COMP | 2017-07-06 | 2017-08-08 | COMP | 2017-08-08 | 2017-08-09 | 72 | 35 | 194211.93
31208104 | EP-REPLACE TWO SPANS OF 4CU - MCA 1101 | 12/22/2015 | 111115038 | 12/21/2015 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/19/2019 | ED.87-C580000000 | SHASTA MAP C58 | 045 | SHASTA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 797.000 | 800.000 | 08J | 2015 | 04/25/2020 | 2020 | 1586 | 226.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2018-02-07 | 2018-02-07 | COMP | 2018-02-09 | 2018-02-09 | COMP | 2018-02-09 | 2018-02-09 | COMP | 2018-02-09 | 2018-02-12 | COMP | 2018-02-12 | 2018-02-20 | COMP | 2018-02-20 | 2018-02-21 | 2 | 12 | 37320.8
31208400 | OCGC 1-SPAN, SALMON CREEK 1101-BAY*CV | 12/22/2015 | 111122187 | 12/22/2015 | # | Not assigned | 30 | Technically Completed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/02/2017 | ED.04316.1101.REGL | REGULATORS | 049 | SONOMA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 405.000 | 405.000 | 08J | 2015 | # | OPEN | 1809 | 258.4286 | FICL | 10 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2017-07-27 | 2018-08-30 | COMP | 2018-09-10 | 2018-09-10 | COMP | 2018-09-10 | 2018-09-10 | COMP | 2018-09-10 | 2018-09-11 | COMP | 2018-09-11 | 2018-09-12 | COMP | 2018-09-12 | 2018-09-13 | 410 | 3 | 49427.72
31209022 | X WDN 15-76118 PS2107-FUSE 355 AREA | 12/28/2015 | 111126146 | 12/23/2015 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/10/2017 | ED.08325.2107 | PAUL SWEET 2107 | 044 | SANTA CRUZ COU | 5535457 | DO 08 - Monthly Forecast Only | 2,756.000 | 4,676.000 | 08J | 2015 | 09/22/2018 | 2018 | 999 | 142.7143 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31209022_R2 WDN 15-76118 PS2107-FUSE 355 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2017-07-11 | 2017-07-11 | COMP | 2017-08-09 | 2017-08-09 | COMP | 2017-08-09 | 2017-08-09 | INPR | 2017-09-11 | 2018-09-22 | # | 2018-09-22 | 2018-09-22 | # | 2018-09-22 | 2018-09-22 | 29 | 409 | 129390.9
31209286 | VIERRA 1707 RECONDUCTORING MANTECA | 12/29/2015 | 111134972 | 12/29/2015 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/02/2020 | ED.16270.1707 | VIERRA 1707 | 039 | SAN JOAQUIN CO | 5535457 | DO 08 - Monthly Forecast Only | 5,207.000 | 0.000 | 08J | 2015 | # | OPEN | 1802 | 257.4286 | CONS | 7 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31209286_VIERRA 1707 RECONDUCTORING-08J | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | INPR | 2018-06-25 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | -43276 | 0 | 547743.04
31209454 | *CANC*DONOT USE*KINGCITY 1102 WD RE*CANC | 12/30/2015 | 111136765 | 12/30/2015 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/02/2017 | ED.18203.1102 | KING CITY 1102 | 040 | SAN LUIS OBISP | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2015 | 05/03/2020 | 2020 | 1586 | 226.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31209454_R2 KINGCITY 1102 WD RECONDUCTOR | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | COMP | 2020-04-08 | 2020-04-08 | COMP | 2020-04-08 | 2020-04-08 | COMP | 2020-04-08 | 2020-04-08 | 0 | -25 | 0
31209455 | X 8455 AIRLINE HWY-VOO DOO CHI | 12/30/2015 | 111136505 | 12/30/2015 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 08/31/2017 | ED.18249.2105 | HOLLISTER 2105 | 035 | SAN BENITO COU | 5535457 | DO 08 - Monthly Forecast Only | 1,380.000 | 1,380.000 | 08J | 2015 | 02/23/2019 | 2019 | 1151 | 164.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31209455_AIRLINE HWY-VOO DOO CHILE | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2017-08-23 | 2018-09-19 | COMP | 2018-09-20 | 2018-09-20 | COMP | 2018-09-20 | 2018-09-20 | COMP | 2018-09-20 | 2018-09-25 | COMP | 2018-09-25 | 2018-10-08 | COMP | 2018-10-08 | 2018-10-09 | 393 | 19 | 107737.53
31209950 | R7 RECON POTTER VLY 1105 ( VAN ARSDALE) | 12/31/2015 | 111140554 | 12/31/2015 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/29/2017 | ED.04228.1105.SWIT | SWITCHES | 023 | MENDOCINO COUN | 5535211 | CWSP SPO - SH 08 | 3,008.000 | 3,008.000 | 08W | 2015 | # | OPEN | 1800 | 257.1429 | DOCC | 8 | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | 31209950_Recon Potter Valley 1105 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | INPR | 2018-08-09 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | -43321 | 0 | 1211780.39
31210862 | MANTECA 1705 RECONDUCTORING - 08J | 01/06/2016 | 111158407 | 01/05/2016 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2018 | ED.16261.1705 | MANTECA 1705 | 039 | SAN JOAQUIN CO | 5535457 | DO 08 - Monthly Forecast Only | 2,500.000 | 0.000 | 08J | 2016 | # | OPEN | 1794 | 256.2857 | CONS | 7 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31210862_MANTECA 1705 RECONDUCTORING:08J | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | INPR | 2017-09-27 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | -43005 | 0 | 96619.16
31211274 | OCGC PINEDALE 2109 - RECONDUCTOR | 01/08/2016 | 111165334 | 01/07/2016 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/29/2017 | ED.25285.2109 | PINEDALE 2109 | 010 | FRESNO COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 2,200.000 | 2,153.000 | 08W | 2016 | 04/07/2018 | 2018 | 820 | 117.1429 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 311211274_R2 PINEDALE 2109 - RECONDUCTOR | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2017-08-03 | 2017-12-16 | COMP | 2017-10-09 | 2017-12-19 | COMP | 2017-12-21 | 2017-12-21 | COMP | 2017-12-21 | 2018-01-11 | COMP | 2018-01-11 | 2018-01-18 | COMP | 2018-01-18 | 2018-01-19 | 140 | 29 | 446773.57
31211275 | OCGC CANTUNA 1103 - RECONDUCTORING | 01/08/2016 | 111164945 | 01/07/2016 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/29/2017 | ED.25344.1103 | CALFLAX 1103 | 054 | TULARE COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 1,340.000 | 4,203.000 | 08W | 2016 | 09/15/2018 | 2018 | 981 | 140.1429 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31211275_R2 CANTUNA 1103 - RECONDUCTORIN | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2017-09-05 | 2018-01-18 | COMP | 2017-11-01 | 2018-01-29 | COMP | 2018-01-29 | 2018-01-29 | COMP | 2018-01-29 | 2018-01-30 | COMP | 2018-01-30 | 2018-02-01 | COMP | 2018-02-01 | 2018-02-02 | 146 | 4 | 142440.95
31212864 | LP402 164 SELBY LN ATHERTON | 01/14/2016 | 111177610 | 01/11/2016 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/28/2017 | ED.02412.0403.TXFR.TROH | OVERHEAD TRANSFORMERS | 041 | SAN MATEO COUN | 5535457 | DO 08 - Monthly Forecast Only | 260.000 | 260.000 | 08W | 2016 | 12/23/2017 | 2017 | 709 | 101.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2017-09-07 | 2017-09-07 | COMP | 2017-09-12 | 2017-10-09 | COMP | 2017-10-09 | 2017-10-09 | COMP | 2017-10-09 | 2017-10-10 | COMP | 2017-10-10 | 2017-11-07 | COMP | 2017-11-07 | 2017-11-16 | 32 | 38 | 58281
31212877 | EP RECONDUCTOR KNIGHTS LANDING 1102 | 01/14/2016 | 111167180 | 01/08/2016 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2017 | ED.50-F190800000.STRU.POLE | YOLO MAP F1908 POLES | 051 | SUTTER COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 1,437.000 | 0.000 | 08J | 2016 | 07/13/2019 | 2019 | 1276 | 182.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2017-10-18 | 2018-11-15 | COMP | 2018-12-13 | 2018-12-13 | COMP | 2018-12-13 | 2018-12-14 | COMP | 2018-12-14 | 2018-12-17 | COMP | 2018-12-17 | 2018-12-27 | COMP | 2018-12-27 | 2018-12-27 | 422 | 13 | 90522.34
31212878 | RECONDUCTOR GRAND ISLAND 2223 | 01/14/2016 | 111166747 | 01/08/2016 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2017 | ED.48-T230600000.STRU.POLE | SOLANO T2306 POLES | 034 | SACRAMENTO COU | 5535457 | DO 08 - Monthly Forecast Only | 470.000 | 0.000 | 08J | 2016 | # | OPEN | 1786 | 255.1429 | UNSC | 6 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | INPR | 2017-11-09 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | -43048 | 0 | 26645.12
31212879 | OCGC RECONDUCTOR 6 CU ON E. NICOLAUS 11 | 01/14/2016 | 111182301 | 01/12/2016 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/29/2017 | ED.11-U250000000.STRU.POLE | MARYSVILLE U25 POLES | 051 | SUTTER COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 551.000 | 08W | 2016 | 01/20/2018 | 2018 | 737 | 105.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2017-12-02 | 2017-12-02 | COMP | 2017-12-04 | 2017-12-04 | COMP | 2017-12-04 | 2017-12-04 | COMP | 2017-12-04 | 2017-12-07 | COMP | 2017-12-07 | 2017-12-26 | COMP | 2017-12-26 | 2017-12-27 | 2 | 23 | 33747.01
31212921 | HAMMONDS 1104 REPLACE 397AL | 01/14/2016 | 111191839 | 01/14/2016 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.25340.1104 | HAMMONDS 1104 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 7,924.000 | 7,924.000 | 08J | 2016 | 07/04/2020 | 2020 | 1633 | 233.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31212921_R2 HAMMONDS 1104 REPLACE 397AL | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2020-02-08 | 2020-02-08 | COMP | 2020-05-14 | 2020-05-14 | COMP | 2020-05-14 | 2020-05-15 | COMP | 2020-05-15 | 2020-05-18 | COMP | 2020-05-18 | 2020-06-10 | COMP | 2020-06-10 | 2020-06-12 | 97 | 28 | 1085349.3
31212922 | +SISQUOC 1104 WD-15-0070918 | 01/14/2016 | 111189007 | 01/13/2016 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/30/2017 | ED.18281.1104 | SISQUOC 1104 | 042 | SANTA BARBARA | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 2,885.000 | 08W | 2016 | 09/16/2017 | 2017 | 611 | 87.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31212922_SISQUOC 1104 WD-15-0070918 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2017-06-14 | 2017-06-14 | COMP | 2017-06-28 | 2017-06-28 | COMP | 2017-06-28 | 2017-06-28 | COMP | 2017-06-28 | 2017-06-29 | COMP | 2017-06-29 | 2017-07-17 | COMP | 2017-07-17 | 2017-07-27 | 14 | 29 | 158146.28
31213040 | OCGC RECONDUCTOR 6 CU ON OLIVEHURST 1104 | 01/14/2016 | 111183617 | 01/12/2016 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/30/2017 | ED.15290.1104.TXFR.TROH | OVERHEAD TRANSFORMERS | 051 | SUTTER COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 144.000 | 08W | 2016 | 06/17/2018 | 2018 | 885 | 126.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2017-08-04 | 2017-08-04 | COMP | 2017-08-07 | 2017-08-07 | COMP | 2017-08-07 | 2017-08-07 | COMP | 2017-08-07 | 2017-08-08 | COMP | 2017-08-08 | 2017-08-25 | COMP | 2017-08-25 | 2017-08-29 | 3 | 22 | -198178.17
31214081 | OCGC 3-SPANS(PET 1108)EASTMAN LN*L | 01/21/2016 | 111204778 | 01/20/2016 | # | Not assigned | 30 | Technically Completed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/30/2017 | ED.04263.1108.RECL | RECLOSERS | 049 | SONOMA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 781.000 | 781.000 | 08J | 2016 | # | OPEN | 1779 | 254.1429 | FICL | 10 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2018-08-28 | 2018-08-28 | COMP | 2018-09-06 | 2018-09-06 | COMP | 2018-09-06 | 2018-09-06 | COMP | 2018-09-06 | 2018-09-10 | COMP | 2018-09-10 | 2018-09-11 | COMP | 2018-09-11 | 2018-09-12 | 9 | 6 | 65717.42
31214863 | +CAB 1104 NO CENTRAL & DE WOLFF, LOMPO | 01/25/2016 | 111218299 | 01/25/2016 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2018 | ED.18310.1104 | CABRILLO 1104 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 4,831.000 | 4,831.000 | 08J | 2016 | 07/20/2019 | 2019 | 1272 | 181.7143 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31214863_CABRILLO 1104 WD15-0077241 RECO | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2018-10-02 | 2018-10-02 | COMP | 2017-08-09 | 2018-10-09 | COMP | 2018-10-09 | 2018-10-10 | COMP | 2018-10-10 | 2018-10-12 | COMP | 2018-10-12 | 2018-10-17 | COMP | 2018-10-17 | 2018-10-19 | 8 | 9 | 166140.17
31214864 | OCGC KERMAN 1106 - WIRE DOWN RECOND | 01/25/2016 | 111218046 | 01/25/2016 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/28/2017 | ED.25271.1106 | KERMAN 1106 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 2,928.000 | 2,578.000 | 08J | 2016 | 05/18/2019 | 2019 | 1209 | 172.7143 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31214864_R2 KERMAN 1106 - WIRE DOWN RECO | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2017-08-23 | 2017-12-04 | COMP | 2017-09-11 | 2017-12-06 | COMP | 2017-12-06 | 2017-12-06 | COMP | 2018-07-10 | 2018-09-24 | COMP | 2018-09-24 | 2018-11-05 | COMP | 2018-11-05 | 2018-11-05 | 105 | 334 | 156789.87
31215422 | X WDN_15-86669 OLMPIA&LUCY BRWN_SB2102 | 01/27/2016 | 111300423 | 01/27/2016 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/30/2017 | ED.18274.2102 | SAN BENITO 2102 | 035 | SAN BENITO COU | 5535457 | DO 08 - Monthly Forecast Only | 2,860.000 | 2,860.000 | 08J | 2016 | 02/09/2019 | 2019 | 1109 | 158.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31215422_OLMPIA & LUCY BRWN_SB2102 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2017-09-06 | 2018-09-27 | COMP | 2018-10-01 | 2018-10-01 | COMP | 2018-10-01 | 2018-10-01 | COMP | 2018-10-15 | 2018-10-25 | COMP | 2018-10-25 | 2018-10-29 | COMP | 2018-10-29 | 2018-10-30 | 390 | 29 | 274836.11
31215461 | *CANC* SAN ARDO 1102 WD INITIATED RECON | 01/28/2016 | 111305436 | 01/28/2016 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/30/2018 | ED.18219.1102 | SAN ARDO 1102 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2016 | 03/26/2016 | 2016 | 58 | 8.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2016-03-26 | 2016-03-26 | # | 2016-03-26 | 2016-03-26 | # | 2016-03-26 | 2016-03-26 | # | 2016-03-26 | 2016-03-26 | # | 2016-03-26 | 2016-03-26 | # | 2016-03-26 | 2016-03-26 | 0 | 0 | 0
31215474 | RECONDUCTOR ROB ROY 2104-MCDONALD RD | 01/28/2016 | 111305970 | 01/28/2016 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 05/28/2018 | ED.08369.2104 | ROB ROY 2104 | 044 | SANTA CRUZ COU | 5535211 | CWSP SPO - SH 08 | 2,750.000 | 2,769.000 | 08W | 2016 | 06/20/2020 | 2020 | 1605 | 229.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | 31215474_RECOND ROB ROY 2104-MCDONALD RD | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2019-05-16 | 2019-05-16 | COMP | 2019-06-11 | 2019-07-19 | COMP | 2019-07-19 | 2019-07-19 | COMP | 2019-07-19 | 2019-07-22 | COMP | 2019-07-22 | 2019-08-05 | COMP | 2019-08-05 | 2019-08-06 | 64 | 18 | 541456.85
31216725 | X BEN LOMOND401-RIDGE RD-FUSE6295 | 02/03/2016 | 111324124 | 02/02/2016 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2017 | ED.08304.0401 | BEN LOMOND 0401 | 044 | SANTA CRUZ COU | 5532479 | CWSP 08W - Monthly Forecast Only | 1,147.000 | 1,450.000 | 08W | 2016 | 07/21/2018 | 2018 | 899 | 128.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31216725_R2 BEN LOMOND401-RIDGE RD-FUSE6 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2017-10-03 | 2017-11-08 | COMP | 2017-11-21 | 2017-11-22 | COMP | 2017-11-22 | 2017-11-22 | COMP | 2017-11-22 | 2017-11-22 | COMP | 2017-11-22 | 2017-12-12 | COMP | 2017-12-12 | 2017-12-12 | 50 | 20 | 176041
31217409 | X ROB ROY2105-SAN ANDREAS RD-2 LOCATIO | 02/05/2016 | 111331499 | 02/05/2016 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/31/2017 | ED.08369.2105 | ROB ROY 2105 | 044 | SANTA CRUZ COU | 5535457 | DO 08 - Monthly Forecast Only | 1,500.000 | 955.000 | 08J | 2016 | 11/21/2020 | 2020 | 1751 | 250.1429 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31217409_ROY2105-SAN ANDREAS RD-2 LOCAT | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2017-08-24 | 2019-08-23 | COMP | 2020-02-15 | 2020-02-15 | COMP | 2020-02-15 | 2020-02-15 | COMP | 2020-02-15 | 2020-02-18 | COMP | 2020-02-18 | 2020-03-04 | COMP | 2020-03-04 | 2020-03-04 | 905 | 18 | 188439.51
31218969 | MWC 08J EDENV 1102 RELO GIRL'S RANCH | 02/12/2016 | 111352255 | 02/11/2016 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/15/2017 | ED.08295.1102.TXFR.TROH | OVERHEAD TRANSFORMERS | 043 | SANTA CLARA CO | 5535457 | DO 08 - Monthly Forecast Only | 2,637.000 | 2,637.000 | 08J | 2016 | 03/02/2019 | 2019 | 1114 | 159.1429 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31218969 EDENV 1102 - RELO GIRL'S RANCH | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2017-09-29 | 2018-06-10 | COMP | 2018-12-27 | 2018-12-27 | COMP | 2018-12-27 | 2018-12-27 | COMP | 2018-12-27 | 2018-12-28 | COMP | 2018-12-28 | 2018-12-29 | COMP | 2018-12-29 | 2019-01-02 | 454 | 6 | 387574.42
31218981 | ER CEDAR CREEK 1101-UPGRADE 9 SPANS | 02/11/2016 | 111332938 | 02/05/2016 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/01/2016 | ED.13-I200000000 | OROVILLE MAP I20 | 004 | BUTTE COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 2,700.000 | 4,200.000 | 08J | 2016 | 06/17/2018 | 2018 | 857 | 122.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2018-05-16 | 2018-05-16 | COMP | 2018-05-30 | 2018-05-30 | COMP | 2018-05-31 | 2018-05-31 | COMP | 2018-05-31 | 2018-06-04 | COMP | 2018-06-04 | 2018-06-06 | COMP | 2018-06-06 | 2018-06-07 | 15 | 7 | 75609.82
31219439 | +SANTA MARIA 1105 WD 15-0087677 | 02/16/2016 | 111357580 | 02/16/2016 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2018 | ED.18267.1105 | SANTA MARIA 1105 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 435.000 | 0.000 | 08J | 2016 | # | OPEN | 1753 | 250.4286 | CONS | 7 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | INPR | 2017-09-29 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | -43007 | 0 | 95769.04
31219804 | GRAND ISLD 2224 RECOND 800FT 6CU W2A | 02/17/2016 | 111367123 | 02/17/2016 | # | Not assigned | 30 | Technically Completed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2017 | JY | JUNK YARD FL TO HOLD DELETED DATA | 034 | SACRAMENTO COU | 5535457 | DO 08 - Monthly Forecast Only | 883.000 | 2,601.000 | 08J | 2016 | # | OPEN | 1752 | 250.2857 | FICL | 10 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2017-10-24 | 2020-02-26 | COMP | 2020-02-13 | 2020-05-08 | COMP | 2020-05-08 | 2020-05-08 | COMP | 2020-05-08 | 2020-05-08 | COMP | 2020-05-08 | 2020-05-19 | COMP | 2020-05-19 | 2020-05-21 | 927 | 13 | 181116.59
31220265 | X DOLAN RD 1101 WD RECONDUCTORING JOB | 02/19/2016 | 111370482 | 02/18/2016 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/01/2018 | ED.18238.1101 | DOLAN ROAD 1101 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 931.000 | 08J | 2016 | 01/18/2020 | 2020 | 1429 | 204.1429 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2017-08-14 | 2019-08-14 | COMP | 2019-08-01 | 2019-08-16 | COMP | 2019-08-16 | 2019-08-16 | COMP | 2019-08-16 | 2019-08-19 | COMP | 2019-08-19 | 2019-09-14 | COMP | 2019-09-14 | 2019-09-16 | 732 | 31 | 99022.08
31220686 | XWDN_16-6334 PLUMS AV & WRING ST_DM21 | 02/22/2016 | 111373978 | 02/19/2016 | # | Not assigned | 30 | Technically Completed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/30/2018 | ED.18222.2104 | DEL MONTE 2104 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 1,285.000 | 1,285.000 | 08J | 2016 | # | OPEN | 1747 | 249.5714 | FICL | 10 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2017-09-27 | 2019-07-30 | COMP | 2019-08-06 | 2019-09-06 | COMP | 2019-08-06 | 2019-09-06 | COMP | 2019-09-06 | 2020-09-25 | COMP | 2020-09-25 | 2020-10-02 | COMP | 2020-10-02 | 2020-10-05 | 709 | 395 | 149697.95
31221409 | OCGC X TERMINOUS 1102 REPL. 800FT W/#2AR | 02/25/2016 | 111380301 | 02/23/2016 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/29/2017 | ED.16302.1102 | TERMINOUS 1102 | 039 | SAN JOAQUIN CO | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 860.000 | 08W | 2016 | 09/15/2018 | 2018 | 933 | 133.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2017-10-23 | 2018-02-03 | COMP | 2018-02-09 | 2018-02-09 | COMP | 2018-02-09 | 2018-02-09 | COMP | 2018-02-09 | 2018-02-12 | COMP | 2018-02-12 | 2018-02-14 | COMP | 2018-02-14 | 2018-02-15 | 109 | 6 | 49849.13
31221412 | PEORIA FLAT1704-RECOND1,233' OF 4ACSR | 02/25/2016 | 111386471 | 02/25/2016 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/30/2018 | ED.16378.1701 | PEORIA 1701 | 049 | SONOMA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 1,565.000 | 1,565.000 | 08J | 2016 | 03/02/2019 | 2019 | 1101 | 157.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31221412_PEORIA FLAT 1704-RECOND | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2018-03-14 | 2018-06-07 | COMP | 2018-06-12 | 2018-06-12 | COMP | 2018-06-12 | 2018-06-12 | COMP | 2018-06-12 | 2018-06-14 | COMP | 2018-06-14 | 2018-06-30 | COMP | 2018-06-30 | 2018-07-05 | 90 | 23 | 215798.61
31221652 | *CANC*DONOT USE*R7 BASALT 1106 WIRE*CANC | 02/26/2016 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/30/2017 | ED.04246.1106 | BASALT 1106 | 028 | NAPA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2016 | 05/03/2020 | 2020 | 1528 | 218.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | COMP | 2020-04-09 | 2020-04-09 | COMP | 2020-04-09 | 2020-04-09 | COMP | 2020-04-09 | 2020-04-09 | 0 | -24 | 0
31222251 | X WDN_16-09640-212 CREST RD OTTER 1101 | 03/01/2016 | 111397227 | 02/29/2016 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/31/2017 | ED.18294.1101 | OTTER 1101 | 027 | MONTEREY COUNT | 5532479 | CWSP 08W - Monthly Forecast Only | 1,554.000 | 1,554.000 | 08W | 2016 | 07/21/2018 | 2018 | 872 | 124.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31222251_212 CREST RD OTTER 1101 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2017-07-27 | 2017-11-01 | COMP | 2017-11-06 | 2017-11-06 | COMP | 2017-11-06 | 2017-11-06 | COMP | 2017-11-06 | 2017-11-07 | COMP | 2017-11-07 | 2017-11-27 | COMP | 2017-11-27 | 2017-12-05 | 102 | 29 | 104557.04
31222395 | OCGC LINDEN 1104 RECONDUCTORING | 03/01/2016 | 111399014 | 03/01/2016 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 08/28/2020 | ED.16207.1104 | LINDEN 1104 | 039 | SAN JOAQUIN CO | 5535457 | DO 08 - Monthly Forecast Only | 2,405.000 | 2,405.000 | 08J | 2016 | # | OPEN | 1739 | 248.4286 | DOCC | 8 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2017-12-06 | 2020-06-02 | COMP | 2019-04-11 | 2020-06-11 | COMP | 2020-06-11 | 2020-06-11 | COMP | 2020-06-11 | 2020-06-11 | COMP | 2020-06-11 | 2020-07-31 | COMP | 2020-07-31 | 2020-08-07 | 918 | 57 | 119116.4
31224307 | +CABRILLO 1103 WD FUSE AND RECONDUCT | 03/11/2016 | 111429579 | 03/10/2016 | # | Not assigned | 30 | Technically Completed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2018 | ED.18310.1103 | CABRILLO 1103 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 484.000 | 484.000 | 08J | 2016 | # | OPEN | 1729 | 247 | FICL | 10 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2017-10-26 | 2020-06-08 | COMP | 2020-05-20 | 2020-07-21 | COMP | 2020-07-21 | 2020-07-21 | COMP | 2020-07-21 | 2020-07-23 | COMP | 2020-07-23 | 2020-07-28 | COMP | 2020-07-28 | 2020-07-31 | 999 | 10 | 43005.52
31229986 | OCGC JACINTO 1101 RECOND 9677'OF 3-6CU | 04/08/2016 | 111520732 | 04/07/2016 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/07/2017 | ED.10285.1101.SWIT | SWITCHES | 004 | BUTTE COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 9,677.000 | 9,677.000 | 08W | 2016 | 03/31/2018 | 2018 | 722 | 103.1429 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31229986_JACINTO 1101 RECOND 8600' 3-6CU | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2017-07-27 | 2017-12-13 | COMP | 2017-12-15 | 2017-12-15 | COMP | 2017-12-15 | 2017-12-15 | COMP | 2017-12-15 | 2017-12-19 | COMP | 2017-12-19 | 2018-01-12 | COMP | 2018-01-12 | 2018-01-26 | 141 | 42 | 533892.66
31232115 | 2018 WHEELER RIDGE 1102 - RECONDUCTOR | 04/18/2016 | 111551651 | 04/18/2016 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 08/31/2018 | ED.25348.1102.SWIT | SWITCHES | 015 | KERN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 2,961.000 | 2,961.000 | 08J | 2016 | 10/17/2018 | 2018 | 912 | 130.2857 | PREC | 11 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31232115_R5 WHEELER RIDGE 1102 - RECOND | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2018-09-07 | 2018-08-21 | COMP | 2018-06-12 | 2018-09-07 | COMP | 2018-09-07 | 2018-09-07 | COMP | 2018-09-07 | 2018-09-10 | COMP | 2018-09-10 | 2018-09-12 | COMP | 2018-09-12 | 2018-09-12 | 0 | 5 | 223270.59
31232280 | ZACA 1102 LONG CYN RD, SANTA YNEZ | 04/18/2016 | 111549081 | 04/15/2016 | # | Not assigned | 30 | Technically Completed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2018 | ED.18268.1102 | ZACA 1102 | 042 | SANTA BARBARA | 5535211 | CWSP SPO - SH 08 | 5,851.000 | 5,851.000 | 08W | 2016 | # | OPEN | 1691 | 241.5714 | FICL | 10 | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Zaca 1102 Repl Det Conductor | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2019-08-06 | 2019-08-06 | COMP | 2019-08-06 | 2019-08-14 | COMP | 2019-08-14 | 2019-08-14 | COMP | 2019-08-14 | 2019-08-21 | COMP | 2019-08-21 | 2019-08-30 | COMP | 2019-08-30 | 2019-09-03 | 8 | 20 | 637321.7
31232282 | +SISQUOC 1104, 3502 TELEPHONE RD, SM | 04/18/2016 | 111549140 | 04/15/2016 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/30/2020 | ED.18281.1104 | SISQUOC 1104 | 040 | SAN LUIS OBISP | 5535457 | DO 08 - Monthly Forecast Only | 7,350.000 | 7,350.000 | 08J | 2016 | # | OPEN | 1691 | 241.5714 | DOCC | 8 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31232282_RECON 7500FT WITH #2CU_ANF FUSE | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2018-03-26 | 2020-01-30 | COMP | 2020-03-17 | 2020-06-08 | COMP | 2020-06-08 | 2020-06-08 | COMP | 2020-06-08 | 2020-06-09 | COMP | 2020-06-09 | 2020-06-19 | COMP | 2020-06-19 | 2020-06-22 | 805 | 14 | 531096.65
31232283 | SM 1105 E/O BONITA LATERAL, SM | 04/18/2016 | 111551569 | 04/18/2016 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2018 | ED.18267.1105 | SANTA MARIA 1105 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 9,851.000 | 9,851.000 | 08J | 2016 | 10/17/2020 | 2020 | 1643 | 234.7143 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Santa Maria 1105 Repl Det Conductor | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2018-01-22 | 2018-11-10 | COMP | 2020-02-06 | 2020-02-24 | COMP | 2020-02-24 | 2020-02-24 | COMP | 2020-02-24 | 2020-02-25 | COMP | 2020-02-25 | 2020-03-03 | COMP | 2020-03-03 | 2020-03-03 | 763 | 8 | 311520.58
31234871 | -RELIAIBLITY 2017 - UWF K1104/X1105/6 | 04/28/2016 | 111583297 | 04/28/2016 | # | Not assigned | 40 | Closed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 11/21/2018 | ED.01210.1104 | OAKLAND K 1104 | 001 | ALAMEDA COUNTY | 5535211 | CWSP SPO - SH 08 | 9,646.000 | 7,271.000 | 08W | 2016 | 01/18/2020 | 2020 | 1360 | 194.2857 | CLSD | 12 | E070 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | 31234871_RELIAIB 2017:UWF K1104/X1105/6 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2017-10-16 | 2018-09-25 | COMP | 2018-06-20 | 2018-10-17 | COMP | 2018-10-17 | 2018-10-17 | COMP | 2018-11-27 | 2019-02-14 | COMP | 2019-02-14 | 2019-02-21 | COMP | 2019-02-21 | 2019-02-22 | 366 | 128 | 1751641.12
31234873 | RELIAIBLITY 2017 - UWF X-1104 | 04/28/2016 | 111583299 | 04/28/2016 | # | Not assigned | 40 | Closed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 03/28/2018 | ED.01254.1104 | OAKLAND X 1104 | 001 | ALAMEDA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 2,109.000 | 2,100.000 | 08J | 2016 | 04/25/2020 | 2020 | 1458 | 208.2857 | CLSD | 12 | E070 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31234873_RELIAIBLITY 2017 - UWF X-1104 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2017-12-15 | 2018-02-13 | COMP | 2018-01-19 | 2018-03-09 | COMP | 2018-03-09 | 2018-03-09 | COMP | 2018-03-09 | 2018-03-12 | COMP | 2018-03-12 | 2018-03-15 | COMP | 2018-03-15 | 2018-03-16 | 84 | 7 | 564442.85
31234874 | RELIAIBLITY 2017 - UWF VARIOUS CKTS | 04/28/2016 | 111583370 | 04/28/2016 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 05/19/2020 | ED.01250.1105 | EL CERRITO G 1105 | 001 | ALAMEDA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 6,260.000 | 0.000 | 08J | 2016 | # | OPEN | 1681 | 240.1429 | CONS | 7 | E070 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31234874_RELIAIB 2017:UWF VARIOUS CKTS | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | INPR | 2017-10-25 | 0 | INPR | 2018-06-20 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | -43033 | 0 | 2053084.11
31236028 | OCGC TRACY 1102 RECONDUCTOR CABRILLO DR | 05/02/2016 | 111593236 | 05/02/2016 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/27/2018 | ED.16288.1102 | TRACY 1102 | 039 | SAN JOAQUIN CO | 5535457 | DO 08 - Monthly Forecast Only | 1,950.000 | 1,950.000 | 08J | 2016 | # | OPEN | 1677 | 239.5714 | DOCC | 8 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2018-07-26 | 2020-06-19 | COMP | 2020-06-25 | 2020-06-25 | COMP | 2020-06-25 | 2020-06-25 | COMP | 2020-06-25 | 2020-06-26 | COMP | 2020-06-26 | 2020-08-12 | COMP | 2020-08-12 | 2020-08-17 | 700 | 53 | 416509.09
31236820 | WOODWARD 2107-RECONDUCTORING | 05/05/2016 | 111610038 | 05/05/2016 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.25529.2107 | WOODWARD 2107 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 1,456.000 | 1,457.000 | 08J | 2016 | 08/08/2020 | 2020 | 1556 | 222.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31236820_R2 WOODWARD 2107-RECONDUCTORING | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2017-08-22 | 2020-03-06 | COMP | 2018-09-18 | 2020-03-13 | COMP | 2020-03-13 | 2020-03-13 | COMP | 2020-03-13 | 2020-03-15 | COMP | 2020-03-15 | 2020-04-30 | COMP | 2020-04-30 | 2020-04-30 | 934 | 48 | 340449.06
31237023 | *CANC* R2KINGSBURG 1116 - RECONDUTO*CANC | 05/06/2016 | 4399615 | 05/06/2016 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/29/2018 | ED.25224.1116 | KINGSBURG 1116 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2016 | 04/04/2020 | 2020 | 1429 | 204.1429 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | COMP | 2020-02-21 | 2020-02-21 | COMP | 2020-02-21 | 2020-02-21 | COMP | 2020-02-21 | 2020-02-21 | 0 | 43882 | 0
31240114 | 2018 TARGETED OH CONDUCTOR_LLAGAS 2101 | 05/17/2016 | 111643669 | 05/17/2016 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2018 | ED.08318.2101 | LLAGAS 2101 | 043 | SANTA CLARA CO | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2016 | # | OPEN | 1662 | 237.4286 | UNSE | 1 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 9510.94
31240819 | OCGC DIST WK FOR SMRTVL-NICOLAUS#2-PH#2 | 05/19/2016 | 111558040 | 04/20/2016 | # | Not assigned | 40 | Closed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/30/2016 | ED.15281.1105.SWIT | SWITCHES | 058 | YUBA COUNTY | 5517127 | DO 08 - Monthly Forecast Only | 12,270.000 | 12,270.000 | 08J | 2016 | 02/29/2020 | 2020 | 1381 | 197.2857 | CLSD | 12 | E070 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Dist. Work for Smarville-Nicolaus #2 Ph2 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2017-04-26 | 2017-04-26 | COMP | 2017-05-17 | 2017-05-17 | COMP | 2017-05-17 | 2017-05-17 | COMP | 2017-05-17 | 2018-08-27 | COMP | 2018-08-27 | 2018-11-16 | COMP | 2018-11-16 | 2018-11-20 | 21 | 552 | 111317.31
31240921 | DIST WORK FOR SMARTVILLE-NICOLAUS#2-PH#3 | 05/19/2016 | 111558046 | 04/20/2016 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/30/2016 | ED.15281.1104.SWIT | SWITCHES | 058 | YUBA COUNTY | 5517127 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2016 | # | OPEN | 1660 | 237.1429 | CONS | 7 | E070 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Dist. Work for Smartville-Nicolaus#2 PH3 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 763192.4
31242294 | RE-COND 467FT_4ACSRTO2ACSR_SANARDO1101 | 05/26/2016 | 111665612 | 05/26/2016 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/26/2018 | ED.18219.1101 | SAN ARDO 1101 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 490.000 | 490.000 | 08J | 2016 | 02/29/2020 | 2020 | 1374 | 196.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2019-03-26 | 2019-03-26 | COMP | 2019-05-18 | 2019-05-18 | COMP | 2019-05-18 | 2019-05-18 | COMP | 2019-05-18 | 2019-05-20 | COMP | 2019-05-20 | 2019-05-21 | COMP | 2019-05-21 | 2019-05-22 | 53 | 4 | 56919.52
31243374 | HARDWICK 1101 RECOND 1720FT 6CU | 06/01/2016 | 111672962 | 05/31/2016 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/28/2018 | ED.25371.1101 | HARDWICK 1101 | 016 | KINGS COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 2,121.000 | 2,121.000 | 08J | 2016 | 05/18/2019 | 2019 | 1081 | 154.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31243374_HARDWICK 1101 RECOND 1720FT 6CU | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2018-02-21 | 2018-10-15 | COMP | 2018-04-18 | 2018-10-31 | COMP | 2018-10-31 | 2018-10-31 | COMP | 2018-10-31 | 2018-11-01 | COMP | 2018-11-01 | 2018-11-07 | COMP | 2018-11-07 | 2018-11-09 | 252 | 9 | 174851.02
31245057 | R7 RECONDUCTOR STANDISH AV BELLEVUE 1102 | 06/02/2016 | 111681954 | 06/02/2016 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 07/28/2017 | ED.04318.1102.RECL | RECLOSERS | 049 | SONOMA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 2,796.000 | 0.000 | 08J | 2016 | # | OPEN | 1646 | 235.1429 | UNSC | 6 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 529745.53
31245707 | *CANC*DONOT USE*SNEATH LANE 1102 WI*CANC | 06/06/2016 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/30/2018 | ED.02272.1102.TXFR.TROH | OVERHEAD TRANSFORMERS | 041 | SAN MATEO COUN | 5505513 | PN-OH ANNEALED/DETER CNDCTR: PM MGD | 0.000 | 0.000 | 08J | 2016 | 05/03/2020 | 2020 | 1427 | 203.8571 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | COMP | 2020-04-08 | 2020-04-08 | COMP | 2020-04-08 | 2020-04-08 | COMP | 2020-04-08 | 2020-04-08 | 0 | -25 | 0
31245970 | *CANC*R2 HIGH SPLICE - VIEJO 2201 *CANC | 06/07/2016 | 111693206 | 06/07/2016 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/29/2017 | ED.18285.2201 | VIEJO 2201 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 152.000 | 0.000 | 08J | 2016 | 12/12/2018 | 2018 | 918 | 131.1429 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2018-09-06 | 2018-09-06 | # | 2018-09-06 | 2018-09-06 | # | 2018-09-06 | 2018-09-06 | COMP | 2018-08-16 | 2018-08-16 | COMP | 2018-08-16 | 2018-08-16 | COMP | 2018-08-16 | 2018-08-16 | 0 | -21 | 0
31246140 | WY1105 - RECOND 3000 FT OF 4AR W 2ARTW | 06/07/2016 | 111693075 | 06/07/2016 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/16/2018 | ED.17 | PARADISE DISTRICT | 004 | BUTTE COUNTY | 5535211 | CWSP SPO - SH 08 | 3,309.000 | 3,309.000 | 08W | 2016 | 04/13/2019 | 2019 | 1040 | 148.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | 31246140_RECOND 3000 FT - DET 4AR-WY1105 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2018-01-05 | 2018-09-12 | COMP | 2018-09-17 | 2018-09-20 | COMP | 2018-09-20 | 2018-09-20 | COMP | 2018-09-20 | 2018-09-21 | COMP | 2018-09-21 | 2018-09-26 | COMP | 2018-09-26 | 2018-09-27 | 258 | 7 | 293661.01
31246411 | R2 HIGH SPLICE - PAUL SWEET 2102 | 06/09/2016 | 111699524 | 06/08/2016 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/28/2018 | ED.08325.2102 | PAUL SWEET 2102 | 044 | SANTA CRUZ COU | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2016 | # | OPEN | 1639 | 234.1429 | UNSE | 1 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 1062.88
31246787 | RECONDUCTOR 4 SPANS - 100 DEODARA WAY | 06/10/2016 | 111710769 | 06/10/2016 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/31/2018 | ED.01410.1105 | ALHAMBRA 1105 | 007 | CONTRA COSTA C | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2016 | # | OPEN | 1638 | 234 | UNSE | 1 | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 2500.01
31247118 | +R5_SISQUOC 1104, N/O PRELL RD, SM | 06/14/2016 | 111709915 | 06/10/2016 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 08/30/2019 | ED.18281.1104 | SISQUOC 1104 | 040 | SAN LUIS OBISP | 5535457 | DO 08 - Monthly Forecast Only | 2,575.000 | 2,575.000 | 08J | 2016 | 05/30/2020 | 2020 | 1446 | 206.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Sisquoc 1104 Recon 13 spans 3400 ft | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2018-08-03 | 2019-09-19 | COMP | 2019-08-20 | 2019-09-20 | COMP | 2019-09-26 | 2019-09-26 | COMP | 2019-09-26 | 2019-09-27 | COMP | 2019-09-27 | 2019-11-07 | COMP | 2019-11-07 | 2019-11-10 | 419 | 45 | 208189.74
31247414 | RECONDUCTR OH WIRE ON CASTROVILE 2104 | 06/15/2016 | 111719948 | 06/15/2016 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/29/2018 | ED.18235.2104 | CASTROVILLE 2104 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 5,305.000 | 0.000 | 08J | 2016 | 08/31/2019 | 2019 | 1172 | 167.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31247414_R2 RECOND OH: CASTROVILE 2104 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2018-01-24 | 2018-10-24 | COMP | 2019-05-02 | 2019-05-02 | COMP | 2019-05-02 | 2019-05-02 | COMP | 2019-05-02 | 2019-05-02 | COMP | 2019-05-02 | 2019-05-06 | COMP | 2019-05-06 | 2019-05-06 | 463 | 4 | 301981.42
31247517 | R7 RECOND 2400' LAKEVILLE HWY, LKVL 1101 | 06/15/2016 | 111720820 | 06/15/2016 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/28/2018 | ED.04337.1101.REGL | REGULATORS | 049 | SONOMA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 2,479.000 | 0.000 | 08J | 2016 | # | OPEN | 1633 | 233.2857 | CONS | 7 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | INPR | 2018-05-30 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | -43250 | 0 | 157012.9
31247900 | SM 1109, OBISPO RD, GUADALUPE | 06/16/2016 | 111724673 | 06/16/2016 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/16/2018 | ED.18267.1109 | SANTA MARIA 1109 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 3,910.000 | 3,910.000 | 08J | 2016 | 10/17/2020 | 2020 | 1584 | 226.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Santa Maria 1109 Repl Det Conductor | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2018-07-18 | 2018-07-18 | COMP | 2020-02-06 | 2020-07-13 | COMP | 2020-07-13 | 2020-07-13 | COMP | 2020-07-13 | 2020-07-13 | COMP | 2020-07-13 | 2020-07-15 | COMP | 2020-07-15 | 2020-07-16 | 726 | 3 | 417467.21
31248532 | CWSP HALF MOON BAY 1101 LS CO4063 | 06/20/2016 | 111724857 | 06/16/2016 | # | Not assigned | 30 | Technically Completed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/04/2020 | JY | JUNK YARD FL TO HOLD DELETED DATA | 041 | SAN MATEO COUN | 5535211 | CWSP SPO - SH 08 | 4,816.000 | 4,816.000 | 08W | 2016 | # | OPEN | 1628 | 232.5714 | FICL | 10 | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2020-08-06 | 2020-08-06 | COMP | 2020-07-08 | 2020-09-10 | COMP | 2020-09-10 | 2020-09-10 | COMP | 2020-09-10 | 2020-09-22 | COMP | 2020-09-22 | 2020-10-07 | COMP | 2020-10-07 | 2020-10-08 | 35 | 28 | 1444525.15
31248533 | MOUNTAIN VIEW 1111 WD FUCO 665 | 06/20/2016 | 111724858 | 06/16/2016 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/26/2017 | JY | JUNK YARD FL TO HOLD DELETED DATA | DA | DE ANZA | 5505513 | PN-OH ANNEALED/DETER CNDCTR: PM MGD | 0.000 | 0.000 | 08J | 2016 | # | OPEN | 1628 | 232.5714 | UNSE | 1 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 5367.48
31248666 | OCGC MIDDLE RIVER 1103 RECONDUCTOR | 06/21/2016 | 111733338 | 06/21/2016 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/01/2020 | ED.16209.1103 | MIDDLE RIVER 1103 | 039 | SAN JOAQUIN CO | 5535457 | DO 08 - Monthly Forecast Only | 7,414.000 | 7,414.000 | 08J | 2016 | # | OPEN | 1627 | 232.4286 | DOCC | 8 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31248666_MIDDLE RIVER 1103 RECONDUCTOR | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2020-07-28 | 2020-07-28 | COMP | 2020-08-25 | 2020-08-25 | COMP | 2020-08-25 | 2020-08-25 | COMP | 2020-08-25 | 2020-10-01 | COMP | 2020-10-01 | 2020-10-16 | COMP | 2020-10-16 | 2020-10-21 | 28 | 57 | 323262.15
31249134 | REPLACE DETERIORATED CONDUCT_MABURY1103 | 06/24/2016 | 111742537 | 06/24/2016 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2018 | ED.08219.1103 | MABURY 1103 | 043 | SANTA CLARA CO | 5535457 | DO 08 - Monthly Forecast Only | 902.000 | 0.000 | 08J | 2016 | # | OPEN | 1624 | 232 | PEND | 5 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | INPR | 2018-08-16 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | -43328 | 0 | 8834.15
31251131 | PALMER 1101 WO HWY 101 NO HW 135, LOS AL | 07/07/2016 | 111769505 | 07/07/2016 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 08/31/2020 | ED.18303.1101 | PALMER 1101 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 8,816.000 | 8,060.000 | 08J | 2016 | # | OPEN | 1611 | 230.1429 | DOCC | 8 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Palmer 1101 Recon 4300 Hwy 135 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2020-07-21 | 2020-07-21 | INPR | 2020-11-04 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | -44033 | 0 | 350106.11
31251132 | *CANC* RECONUCTOR_11647FT_TO2CU_34SPAN_ | 07/07/2016 | 111769668 | 07/07/2016 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 07/07/2018 | ED.18282.1102 | MESA 1102 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2016 | 03/18/2017 | 2017 | 254 | 36.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2017-03-18 | 2017-03-18 | # | 2017-03-18 | 2017-03-18 | # | 2017-03-18 | 2017-03-18 | # | 2017-03-18 | 2017-03-18 | # | 2017-03-18 | 2017-03-18 | # | 2017-03-18 | 2017-03-18 | 0 | 0 | 0
31251133 | SM 1109, BLACK RD S/O W MAIN, SM | 07/07/2016 | 111770148 | 07/07/2016 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2019 | ED.18267.1109 | SANTA MARIA 1109 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 8,325.000 | 8,657.000 | 08J | 2016 | 09/05/2020 | 2020 | 1521 | 217.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Santa Maria 1109 Recon 805 Black Rd | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2019-09-26 | 2019-09-26 | COMP | 2020-01-06 | 2020-01-06 | COMP | 2020-01-06 | 2020-01-06 | COMP | 2020-01-06 | 2020-01-07 | COMP | 2020-01-07 | 2020-01-29 | COMP | 2020-01-29 | 2020-01-30 | 102 | 24 | 388153.22
31255863 | *CANC* *DO NOT USE* R2WATSNVILLE 2*CANC | 07/06/2016 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/30/2018 | ED.76-Q211000000.STRU.POLE | COAST Q2110 POLES | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2016 | 04/04/2020 | 2020 | 1368 | 195.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31255863_WATSNVILLE 2101 CABLE REPL | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2020-04-04 | 2020-04-04 | # | 2020-04-04 | 2020-04-04 | # | 2020-04-04 | 2020-04-04 | COMP | 2020-02-19 | 2020-02-19 | COMP | 2020-02-19 | 2020-02-19 | COMP | 2020-02-19 | 2020-02-19 | 0 | -45 | 0
31255868 | R2ROB ROY 2104 HIGH SPLICE CABLE REPLACE | 07/06/2016 | 111767989 | 07/06/2016 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/30/2018 | ED.76-O171000000.STRU.POLE | COAST O1710 POLES | 044 | SANTA CRUZ COU | 5535211 | CWSP SPO - SH 08 | 1,439.000 | 1,439.000 | 08W | 2016 | 04/13/2019 | 2019 | 1011 | 144.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | 31255868_ROB ROY 2104 CABLE REPLACE | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2018-07-16 | 2018-07-27 | COMP | 2018-08-09 | 2018-08-09 | COMP | 2018-08-09 | 2018-08-09 | COMP | 2018-08-09 | 2018-08-10 | COMP | 2018-08-10 | 2018-08-11 | COMP | 2018-08-11 | 2018-08-14 | 24 | 5 | 176947.94
31257470 | OCGC 707 RECOND. W RIPON RD | 07/15/2016 | 111797167 | 07/15/2016 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.16270.1707 | VIERRA 1707 | 039 | SAN JOAQUIN CO | 5535457 | DO 08 - Monthly Forecast Only | 5,222.000 | 5,222.000 | 08J | 2016 | # | OPEN | 1603 | 229 | DOCC | 8 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31257470_VIERRA 1707 RECOND. W. RIPON RD | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2020-03-13 | 2020-03-02 | COMP | 2020-03-13 | 2020-04-22 | COMP | 2020-04-22 | 2020-04-22 | COMP | 2020-04-22 | 2020-04-23 | COMP | 2020-04-23 | 2020-05-11 | COMP | 2020-05-11 | 2020-05-11 | 40 | 19 | 595125.36
31258120 | HARTLEY 1102 RECONDUCTOR LINE BAD SP | 07/19/2016 | 111804117 | 07/19/2016 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 07/19/2017 | ED.04321.1102.RECL | RECLOSERS | 017 | LAKE COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 3,500.000 | 4,000.000 | 08J | 2016 | # | OPEN | 1599 | 228.4286 | DOCC | 8 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2017-12-11 | 2020-10-08 | INPR | 2020-11-04 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | -43080 | 0 | 358885.12
31259321 | HONCUT 1102 RECON LINE EXCESS SPLICES | 07/25/2016 | 111816288 | 07/25/2016 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | SI | SIERRA | [8 empty] | 07/25/2017 | ED.10321.1102.SWIT | SWITCHES | 058 | YUBA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 4,458.000 | 4,458.000 | 08J | 2016 | 02/23/2019 | 2019 | 943 | 134.7143 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2017-03-14 | 2018-09-12 | COMP | 2017-03-14 | 2018-11-01 | COMP | 2018-11-01 | 2018-11-01 | COMP | 2018-11-01 | 2018-11-02 | COMP | 2018-11-02 | 2018-11-13 | COMP | 2018-11-13 | 2018-11-13 | 597 | 12 | 135223.57
31259546 | 2018 AIRWAYS 1101 RECOND 2800FT TO 715AL | 07/26/2016 | 111817984 | 07/25/2016 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 07/31/2021 | ED.25204.1101 | AIRWAYS 1101 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 2,835.000 | 0.000 | 08J | 2016 | # | OPEN | 1592 | 227.4286 | PEND | 5 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31259546_Ariways 1101 Reconductor | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 33804.96
31259547 | 2018 SANGER 1108 RECOND 5000FT TO 2AR | 07/26/2016 | 111817982 | 07/25/2016 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2018 | ED.25235.1108 | SANGER 1108 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 5,563.000 | 5,563.000 | 08J | 2016 | 07/20/2019 | 2019 | 1089 | 155.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31259547_2018 SANGER 1108 RECOND | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2018-10-05 | 2018-10-05 | COMP | 2018-09-12 | 2019-02-13 | COMP | 2019-02-13 | 2019-02-13 | COMP | 2019-02-13 | 2019-02-14 | COMP | 2019-02-14 | 2019-02-15 | COMP | 2019-02-15 | 2019-02-19 | 131 | 6 | 257116.05
31260008 | RECONDUCTR PRUNEDLE 1107- HIGH SPLICE | 07/28/2016 | 111827483 | 07/28/2016 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/28/2018 | ED.18296.1107 | PRUNEDALE 1107 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 7,400.000 | 7,400.000 | 08J | 2016 | 10/24/2020 | 2020 | 1549 | 221.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Reconductor Prunedale 1107 - High Splice | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2018-03-06 | 2018-11-05 | COMP | 2019-03-28 | 2019-03-28 | COMP | 2019-03-28 | 2019-03-28 | COMP | 2019-03-28 | 2019-03-29 | COMP | 2019-03-29 | 2019-03-30 | COMP | 2019-03-30 | 2019-03-30 | 387 | 2 | 709718.09
31260163 | SM 1109 BLACK RD NO MAIN, SANTA MARIA | 07/29/2016 | 111832381 | 07/29/2016 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2018 | ED.18267.1109 | SANTA MARIA 1109 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 2,285.000 | 2,285.000 | 08J | 2016 | 10/17/2020 | 2020 | 1541 | 220.1429 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31260163_SantaMaria 1109 Recon 2157ft-11 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2017-12-14 | 2018-06-20 | COMP | 2020-02-06 | 2020-07-10 | COMP | 2020-07-10 | 2020-07-10 | COMP | 2020-07-10 | 2020-07-11 | COMP | 2020-07-11 | 2020-07-13 | COMP | 2020-07-13 | 2020-07-14 | 939 | 4 | 218657.15
31260797 | +R2Z OCEANO 1104 RECONDUCTORING BRANCH | 08/02/2016 | 111523761 | 04/08/2016 | # | Not assigned | 40 | Closed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2019 | ED.18260.1104 | OCEANO 1104 | 040 | SAN LUIS OBISP | 5535457 | DO 08 - Monthly Forecast Only | 9,463.000 | 9,363.000 | 08J | 2016 | 10/17/2020 | 2020 | 1537 | 219.5714 | CLSD | 12 | E070 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31260797_R5 OCEANO 1104 RECONDUCTORING B | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2017-07-31 | 2019-01-02 | COMP | 2019-09-11 | 2020-01-15 | COMP | 2020-01-15 | 2020-02-03 | COMP | 2020-02-03 | 2020-02-04 | COMP | 2020-02-04 | 2020-02-18 | COMP | 2020-02-18 | 2020-02-19 | 917 | 16 | 1173286.14
31260997 | REPL 3 SECNS OF 2AR W 2AR WYANDOTTE | 08/03/2016 | 111842619 | 08/02/2016 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 08/21/2018 | ED.10375.1101.RECL | RECLOSERS | 004 | BUTTE COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 6,757.000 | 7,165.000 | 08J | 2016 | 02/23/2019 | 2019 | 934 | 133.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31260997_REPL 3 SECNS WYANDOTTE 1105 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2018-01-09 | 2018-07-13 | COMP | 2018-07-20 | 2018-07-20 | COMP | 2018-07-20 | 2018-07-20 | COMP | 2018-07-20 | 2018-07-23 | COMP | 2018-07-23 | 2018-07-25 | COMP | 2018-07-25 | 2018-07-26 | 192 | 6 | 339172.04
31261149 | STS-COND_BROK_REPL - R/O 48 GREENWOOD DR | 08/03/2016 | 112515378 | 01/17/2017 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/31/2017 | ED.56-E041600000.STRU.POLE | SKYLINE E0416 POLES | 041 | SAN MATEO COUN | 5505513 | PN-OH ANNEALED/DETER CNDCTR: PM MGD | 1,600.000 | 1,297.000 | 08J | 2016 | 08/18/2018 | 2018 | 745 | 106.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31261149_REPL: R/O 48 GREENWOOD DR | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2017-09-23 | 2017-09-23 | COMP | 2017-10-11 | 2017-12-01 | COMP | 2017-12-01 | 2017-12-01 | COMP | 2017-12-01 | 2017-12-04 | COMP | 2017-12-04 | 2017-12-13 | COMP | 2017-12-13 | 2017-12-13 | 69 | 12 | 178181.18
31262055 | SIS 1104 DOMINION RD, SANTA MARIA | 08/12/2016 | 111870803 | 08/12/2016 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2018 | ED.18281.1104 | SISQUOC 1104 | 040 | SAN LUIS OBISP | 5535457 | DO 08 - Monthly Forecast Only | 2,172.000 | 2,255.000 | 08J | 2016 | 10/17/2020 | 2020 | 1527 | 218.1429 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31262055_Sisquoc 1104 Recon 8 - 2172 ft | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2017-12-21 | 2018-07-01 | COMP | 2020-01-28 | 2020-06-15 | COMP | 2020-06-15 | 2020-06-15 | COMP | 2020-06-15 | 2020-06-16 | COMP | 2020-06-16 | 2020-06-24 | COMP | 2020-06-24 | 2020-06-25 | 907 | 10 | 297229.79
31262225 | *CANC*DONOT USE*DAVIS 1106 RECOND L*CANC | 08/09/2016 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 08/04/2017 | ED.06204.1106.SWIT | SWITCHES | 057 | YOLO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2016 | 05/03/2020 | 2020 | 1363 | 194.7143 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | COMP | 2020-04-10 | 2020-04-10 | COMP | 2020-04-10 | 2020-04-10 | COMP | 2020-04-10 | 2020-04-10 | 0 | -23 | 0
31262300 | EP KNIGHTS LANDING 1102 RECON WIRE DOWN | 08/10/2016 | 111858050 | 08/09/2016 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2017 | ED.50-G200000000.STRU.POLE | YOLO G20 POLES | 051 | SUTTER COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 2,015.000 | 0.000 | 08J | 2016 | # | OPEN | 1577 | 225.2857 | UNSC | 6 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | INPR | 2018-05-15 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | -43235 | 0 | 39765.16
31262866 | HBPP 1101 LR 898396 EXCESSIVE SPLICES | 08/12/2016 | 111868017 | 08/11/2016 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/26/2018 | JY | JUNK YARD FL TO HOLD DELETED DATA | 012 | HUMBOLDT COUNT | 5535457 | DO 08 - Monthly Forecast Only | 4,906.000 | 4,906.000 | 08J | 2016 | # | OPEN | 1575 | 225 | DOCC | 8 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31262866_HBPP 1101 LR Excessive Splices | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2018-03-14 | 2020-01-29 | INPR | 2020-02-18 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | -43173 | 0 | 645470.52
31262921 | *CANC*- RECOND SANTA RITA 1102 - WD | 08/12/2016 | 111868016 | 08/11/2016 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/14/2018 | ED.25354.1102 | SANTA RITA 1102 | 024 | MERCED COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 2,900.000 | 0.000 | 08J | 2016 | 06/29/2019 | 2019 | 1051 | 150.1429 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2019-06-29 | 2019-06-29 | # | 2019-06-29 | 2019-06-29 | # | 2019-06-29 | 2019-06-29 | # | 2019-06-29 | 2019-06-29 | # | 2019-06-29 | 2019-06-29 | # | 2019-06-29 | 2019-06-29 | 0 | 0 | 0
31264776 | PEASE 1101 RECOND LINE BAD SPLICE PM TBD | 08/24/2016 | 111899995 | 08/24/2016 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/24/2017 | ED.15375.1101.SWIT | SWITCHES | 051 | SUTTER COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 1,066.000 | 0.000 | 08J | 2016 | # | OPEN | 1563 | 223.2857 | UNSC | 6 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | INPR | 2017-03-14 | 0 | INPR | 2017-03-14 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | -42808 | 0 | 3603.86
31264915 | R7 RECONDUCTOR WILSON RD- RINCON 1103 | 08/23/2016 | 111897432 | 08/23/2016 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/29/2017 | ED.04332.1103.CAPA | CAPACITORS | 049 | SONOMA COUNTY | 5535211 | CWSP SPO - SH 08 | 957.000 | 957.000 | 08W | 2016 | 04/13/2019 | 2019 | 963 | 137.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2018-10-02 | 2018-07-25 | COMP | 2018-08-29 | 2018-10-02 | COMP | 2018-10-02 | 2018-10-02 | COMP | 2018-10-02 | 2018-10-03 | COMP | 2018-10-03 | 2018-10-04 | COMP | 2018-10-04 | 2018-10-05 | 0 | 3 | 75634.1
31265331 | RAINBOW 1106 RECOND 6600FT 6CU | 08/25/2016 | 111902703 | 08/25/2016 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/01/2020 | ED.25444.1106 | RAINBOW 1106 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 6,600.000 | 6,600.000 | 08J | 2016 | # | OPEN | 1562 | 223.1429 | DOCC | 8 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2020-02-10 | 2020-02-10 | COMP | 2019-12-04 | 2020-08-24 | COMP | 2020-08-24 | 2020-08-24 | INPR | 2020-08-24 | 0 | # | 0 | 0 | # | 0 | 0 | 196 | -44067 | 886912.33
31269259 | ZACA 1101 FOXEN CYN RD, LOS OLIVOS | 09/07/2016 | 111934659 | 09/06/2016 | # | Not assigned | 30 | Technically Completed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2018 | ED.18268.1101 | ZACA 1101 | 042 | SANTA BARBARA | 5535211 | CWSP SPO - SH 08 | 6,389.000 | 6,389.000 | 08W | 2016 | # | OPEN | 1549 | 221.2857 | FICL | 10 | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Zaca 1101 Recon 1.2 miles | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2019-08-08 | 2019-08-08 | COMP | 2019-08-09 | 2019-08-09 | COMP | 2019-08-09 | 2019-08-09 | COMP | 2019-08-09 | 2019-08-12 | COMP | 2019-08-12 | 2019-09-27 | COMP | 2019-09-27 | 2019-10-01 | 1 | 53 | 600327.32
31269333 | KERMAN 1103 RECOND 2160 FT 6CU | 09/06/2016 | 111921758 | 09/01/2016 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2018 | ED.25271.1103 | KERMAN 1103 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 2,133.000 | 2,133.000 | 08J | 2016 | 12/01/2018 | 2018 | 816 | 116.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2018-06-07 | 2018-07-02 | COMP | 2018-05-24 | 2018-08-16 | COMP | 2018-08-16 | 2018-08-16 | COMP | 2018-08-16 | 2018-08-17 | COMP | 2018-08-17 | 2018-08-18 | COMP | 2018-08-18 | 2018-08-21 | 70 | 5 | 135946.61
31271222 | *CANC*DONOT USE*SM 1109, N/O 1586 W*CANC | 09/14/2016 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.18267.1109 | SANTA MARIA 1109 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2016 | 05/03/2020 | 2020 | 1327 | 189.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31271222_Santa Maria 1109 Recond | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | COMP | 2020-04-10 | 2020-04-10 | COMP | 2020-04-10 | 2020-04-10 | COMP | 2020-04-10 | 2020-04-10 | 0 | -23 | 0
31271230 | G-1114 RECONDUCTOR 2 SPANS | 09/16/2016 | 111964777 | 09/15/2016 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 07/10/2017 | ED.28-D042100000.STRU.POLE | BAY D0421 POLES | 007 | CONTRA COSTA C | 5535457 | DO 08 - Monthly Forecast Only | 480.000 | 328.000 | 08J | 2016 | 12/28/2019 | 2019 | 1198 | 171.1429 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2018-04-23 | 2019-09-10 | COMP | 2018-09-18 | 2019-11-19 | COMP | 2019-11-19 | 2019-11-19 | COMP | 2019-11-19 | 2019-11-20 | COMP | 2019-11-20 | 2019-12-09 | COMP | 2019-12-09 | 2019-12-09 | 575 | 20 | 95132.56
31271378 | WILKINS SLOUGH 1102 RECONLINE EX SPL | 09/15/2016 | 111942689 | 09/09/2016 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/09/2017 | ED.06277.1102.SWIT | SWITCHES | 051 | SUTTER COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 5,164.000 | 5,164.000 | 08J | 2016 | 02/23/2019 | 2019 | 891 | 127.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2017-11-21 | 2018-09-11 | COMP | 2018-09-27 | 2018-10-04 | COMP | 2018-10-04 | 2018-10-04 | COMP | 2018-10-04 | 2018-10-05 | COMP | 2018-10-05 | 2018-10-08 | COMP | 2018-10-08 | 2018-10-10 | 317 | 6 | 167482
31272374 | CWSP PT. MORETTI FROM 5043 TO 5955 | 09/20/2016 | 111973964 | 09/20/2016 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/06/2020 | ED.08293.1101 | POINT MORETTI 1101 | 044 | SANTA CRUZ COU | 5535211 | CWSP SPO - SH 08 | 8,500.000 | 0.000 | 08W | 2016 | # | OPEN | 1536 | 219.4286 | PEND | 5 | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | 31272374_RECOND PT MORETTI: 5043 TO 5955 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 2282675.06
31272375 | CWSP PT. MORETTI BEYOND 5995 | 09/20/2016 | 111973967 | 09/20/2016 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/01/2022 | ED.08293.1101 | POINT MORETTI 1101 | 044 | SANTA CRUZ COU | 5535211 | CWSP SPO - SH 08 | 8,640.000 | 0.000 | 08W | 2016 | # | OPEN | 1536 | 219.4286 | PEND | 5 | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | 31272375_RECOND PT MORETTI BEYOND 5995 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 79852.39
31273284 | *CANC*DO NOT USE*D-1105 RECOND 3,26*CANC | 09/26/2016 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/23/2017 | ED.01204.1105.SWIT | SWITCHES | 001 | ALAMEDA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2016 | 05/03/2020 | 2020 | 1315 | 187.8571 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | COMP | 2020-04-09 | 2020-04-09 | COMP | 2020-04-09 | 2020-04-09 | COMP | 2020-04-09 | 2020-04-09 | 0 | -24 | 0
31273808 | RECONDUCT WD DOLAN 1104 - 16-0058680 | 09/27/2016 | 111990681 | 09/27/2016 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/28/2018 | ED.18238.1104 | DOLAN ROAD 1104 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 2,727.000 | 2,727.000 | 08J | 2016 | 02/29/2020 | 2020 | 1250 | 178.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31273808_R2 RECONDUCT WD DOLAN 1104 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2017-12-18 | 2018-07-26 | COMP | 2018-11-05 | 2018-11-05 | COMP | 2018-11-05 | 2018-11-05 | COMP | 2018-11-05 | 2018-11-06 | COMP | 2018-11-06 | 2018-11-13 | COMP | 2018-11-09 | 2018-11-09 | 322 | 4 | 205282.15
31274093 | *CANC*R2Z KETTLEMANHILLS 1101 RECO2741F | 09/29/2016 | 113311706 | 09/22/2017 | # | Not assigned | 25 | Canceled | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.25273.1101 | KETTLEMAN HILLS 1101 | 016 | KINGS COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 2,714.000 | 0.000 | 08J | 2016 | # | OPEN | 1527 | 218.1429 | CNCL | Other | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31274093_KETTLEMAN HILLS 1101 RECON | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | -1290.6
31274717 | CABRILLO 1104, SAN PASQUAL CYN RD, LOMPO | 10/04/2016 | 112010896 | 10/04/2016 | # | Not assigned | 30 | Technically Completed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2018 | ED.18310.1104 | CABRILLO 1104 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 8,806.000 | 0.000 | 08J | 2016 | # | OPEN | 1522 | 217.4286 | FICL | 10 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Cabrillo 1104 Recon 1.75 miles | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2018-02-20 | 2018-07-15 | COMP | 2020-02-06 | 2020-06-22 | COMP | 2020-06-22 | 2020-06-22 | COMP | 2020-06-22 | 2020-06-23 | COMP | 2020-06-23 | 2020-07-06 | COMP | 2020-07-06 | 2020-07-08 | 853 | 16 | 547002.95
31275384 | OCGC DUCTOR MAYS CANYON-MIRABEL 1101 | 10/05/2016 | 112013623 | 10/05/2016 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/29/2017 | ED.04209.1101.SWIT | SWITCHES | 049 | SONOMA COUNTY | 5535211 | CWSP SPO - SH 08 | 1,986.000 | 1,986.000 | 08W | 2016 | 11/21/2020 | 2020 | 1508 | 215.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2018-04-13 | 2018-10-09 | COMP | 2018-10-16 | 2018-10-16 | COMP | 2018-10-16 | 2018-10-16 | COMP | 2018-10-16 | 2018-10-24 | COMP | 2018-10-24 | 2018-10-25 | COMP | 2018-10-25 | 2018-10-26 | 186 | 10 | 167103.76
31275658 | R7 DUNBAR 1102 RECOND OH BEYOND CO 1285 | 10/07/2016 | 112015123 | 10/05/2016 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/29/2017 | JY | JUNK YARD FL TO HOLD DELETED DATA | 049 | SONOMA COUNTY | 5535211 | CWSP SPO - SH 08 | 2,580.000 | 2,580.000 | 08W | 2016 | # | OPEN | 1519 | 217 | DOCC | 8 | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2018-08-16 | 2019-08-30 | INPR | 2019-06-05 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | -43328 | 0 | 647589.94
31275749 | CHOWCHILLA 1104-RECOND 1,290' OF 4A | 10/07/2016 | 112024014 | 10/07/2016 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2018 | ED.25410.1104 | CHOWCHILLA 1104 | 020 | MADERA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 1,560.000 | 1,560.000 | 08J | 2016 | 08/28/2018 | 2018 | 690 | 98.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31275749_CHOWCHILLA 1104 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2017-12-13 | 2018-04-20 | COMP | 2018-03-20 | 2018-04-26 | COMP | 2018-04-26 | 2018-04-27 | COMP | 2018-04-27 | 2018-04-30 | COMP | 2018-04-30 | 2018-05-02 | COMP | 2018-05-02 | 2018-05-03 | 135 | 6 | 103467.77
31275750 | CHOWCHILLA 1104-RECOND 2,200' OF #6CU | 10/07/2016 | 112024150 | 10/07/2016 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/30/2019 | ED.25410.1104 | CHOWCHILLA 1104 | 020 | MADERA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 2,178.000 | 2,186.000 | 08J | 2016 | 07/18/2020 | 2020 | 1380 | 197.1429 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31275750_CHOWCHILLA 1104-RECOND | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2017-10-11 | 2019-12-30 | COMP | 2020-01-09 | 2020-01-09 | COMP | 2020-01-09 | 2020-01-09 | COMP | 2020-01-09 | 2020-01-10 | COMP | 2020-01-10 | 2020-01-23 | COMP | 2020-01-23 | 2020-01-27 | 820 | 18 | 228827.37
31276193 | 46 OCLH STS R/O 1380 RUSSELMAN RD CLAYTO | 10/11/2016 | 112033188 | 10/10/2016 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/30/2018 | ED.66-2722600000.STRU.POLE | KERN 27226 POLES | 015 | KERN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 2,513.000 | 2,513.000 | 08J | 2016 | 10/17/2018 | 2018 | 736 | 105.1429 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31276193_GOOSE LAKE 1103 - RECOND 2,388' | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2018-02-22 | 2018-06-28 | COMP | 2018-05-02 | 2018-08-21 | COMP | 2018-08-21 | 2018-08-21 | COMP | 2018-08-21 | 2018-08-30 | COMP | 2018-08-30 | 2018-08-31 | COMP | 2018-08-31 | 2018-09-04 | 180 | 14 | 154083.62
31276194 | R5 RIO BRAVO 1101 - RECONDUCTOR 1,650' | 10/11/2016 | 112033189 | 10/10/2016 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 05/01/2020 | ED.66-28254C0000.STRU.POLE | KERN 28254C POLES | 015 | KERN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 1,576.000 | 0.000 | 08J | 2016 | # | OPEN | 1515 | 216.4286 | CONS | 7 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | INPR | 2018-06-27 | 0 | INPR | 2020-01-14 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | -43278 | 0 | 46735.03
31276229 | 2018 OH COND RPLC: ARCATA 1121 | 10/11/2016 | 112033187 | 10/10/2016 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/10/2018 | ED.36-N101200000.STRU.POLE | EUREKA N1012 POLES | 012 | HUMBOLDT COUNT | 5535457 | DO 08 - Monthly Forecast Only | 5,000.000 | 0.000 | 08J | 2016 | # | OPEN | 1515 | 216.4286 | PEND | 5 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31276229_2018 OH Cond Rplc Arcata 1121 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 57452.46
31276346 | 2018 OH COND RPLC: BIG LAGOON 1101 | 10/11/2016 | 112034600 | 10/11/2016 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/29/2018 | ED.19236.1101.SWIT | SWITCHES | 012 | HUMBOLDT COUNT | 5535457 | DO 08 - Monthly Forecast Only | 3,779.000 | 0.000 | 08J | 2016 | # | OPEN | 1515 | 216.4286 | UNSC | 6 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Big Lagoon 1101 Excessive Splices | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 70906.3
31276349 | 2018 OH COND RPLC: EEL RIVER 1103 | 10/11/2016 | 112034941 | 10/11/2016 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/29/2018 | ED.19238.1103.SWIT | SWITCHES | 012 | HUMBOLDT COUNT | 5535457 | DO 08 - Monthly Forecast Only | 679.000 | 0.000 | 08J | 2016 | # | OPEN | 1515 | 216.4286 | UNSC | 6 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | INPR | 2018-08-07 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | -43319 | 0 | 2232.56
31277398 | RECONDUCTOR LIVINGSTON 1106 - WD | 10/13/2016 | 112043442 | 10/13/2016 | # | Not assigned | 30 | Technically Completed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/21/2019 | ED.25226.1106 | LIVINGSTON 1106 | 024 | MERCED COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 2,299.000 | 2,299.000 | 08J | 2016 | # | OPEN | 1513 | 216.1429 | FICL | 10 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31277398_RECOND LIVINGSTON 1106 - WD | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2020-05-15 | 2020-05-15 | COMP | 2020-05-29 | 2020-05-29 | COMP | 2020-05-29 | 2020-05-29 | COMP | 2020-05-29 | 2020-05-30 | COMP | 2020-05-30 | 2020-07-17 | COMP | 2020-07-17 | 2020-07-22 | 14 | 54 | 152457.36
31277399 | RECONDUCTOR CRESSEY 2103 - IR PATROL | 10/13/2016 | 112043492 | 10/13/2016 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/02/2018 | ED.25470.2103 | CRESSEY 2103 | 024 | MERCED COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 2,847.000 | 2,847.000 | 08J | 2016 | 10/27/2018 | 2018 | 744 | 106.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | RECONDUCTOR CRESSEY 2103 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2018-04-17 | 2018-06-05 | COMP | 2018-06-07 | 2018-06-07 | COMP | 2018-06-07 | 2018-06-07 | COMP | 2018-06-07 | 2018-06-11 | COMP | 2018-06-11 | 2018-06-23 | COMP | 2018-06-23 | 2018-06-26 | 51 | 19 | 306782.17
31278065 | RECONDUCTOR MERCED 2101-STRETCH RD | 10/17/2016 | 112045722 | 10/14/2016 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/14/2018 | ED.25280.2101 | MERCED 2101 | 024 | MERCED COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 753.000 | 0.000 | 08J | 2016 | # | OPEN | 1509 | 215.5714 | ADER | 3 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 5783.6
31278200 | +OCEANO 1102 S HALCYON & PINE RDGE | 10/17/2016 | 112052729 | 10/17/2016 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/31/2019 | ED.18260.1108 | OCEANO 1108 | 040 | SAN LUIS OBISP | 5535211 | CWSP SPO - SH 08 | 2,081.000 | 2,081.000 | 08W | 2016 | 07/04/2020 | 2020 | 1356 | 193.7143 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | 31278200_Oceano 1108 Recon 11 - 2200 ft | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2019-03-29 | 2019-03-21 | COMP | 2019-03-29 | 2019-04-10 | COMP | 2019-04-10 | 2019-04-10 | COMP | 2019-04-10 | 2019-04-10 | COMP | 2019-04-10 | 2019-04-11 | COMP | 2019-04-11 | 2019-04-14 | 12 | 4 | 453122.72
31279013 | MALAGA 1102 RECOND 1350FT 6CU | 10/20/2016 | 112060901 | 10/19/2016 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 01/31/2020 | ED.25425.1102 | MALAGA 1102 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 1,217.000 | 1,217.000 | 08J | 2016 | 04/04/2020 | 2020 | 1262 | 180.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2018-05-30 | 2020-01-16 | COMP | 2019-12-19 | 2020-01-28 | COMP | 2020-01-28 | 2020-01-28 | COMP | 2020-01-28 | 2020-01-29 | COMP | 2020-01-29 | 2020-02-06 | COMP | 2020-02-06 | 2020-02-11 | 608 | 14 | 45344.55
31280506 | R2 RECONDUCT PT. MORETTI BEYOND 8981 | 10/26/2016 | 112115009 | 10/25/2016 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/28/2018 | ED.08293.1101 | POINT MORETTI 1101 | 044 | SANTA CRUZ COU | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2016 | # | OPEN | 1500 | 214.2857 | UNSE | 1 | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | 31280506_RECOND PT. MORETTI BEYOND 8981 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 22941.03
31280730 | *CANC* R2 RECONDUCT DOLAN RD *CANC | 10/27/2016 | 112119901 | 10/27/2016 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/29/2018 | ED.18238.1101 | DOLAN ROAD 1101 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 2,800.000 | 0.000 | 08J | 2016 | 12/12/2018 | 2018 | 776 | 110.8571 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2018-10-03 | 2018-10-03 | # | 2018-10-03 | 2018-10-03 | # | 2018-10-03 | 2018-10-03 | COMP | 2018-09-25 | 2018-09-25 | COMP | 2018-09-25 | 2018-09-25 | COMP | 2018-09-25 | 2018-09-25 | 0 | -8 | 0
31280946 | R2 RECONDUCT BORONDA 1101 WD#16-0070412 | 10/27/2016 | 112121695 | 10/27/2016 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/29/2018 | ED.18246.1101 | BORONDA 1101 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2016 | # | OPEN | 1499 | 214.1429 | UNSE | 1 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 813.31
31281523 | R2 RECONDUCT RESERVATION ROAD 1102 | 10/31/2016 | 112128892 | 10/31/2016 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/29/2018 | ED.18273.1102 | RESERVATION ROAD 1102 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2016 | # | OPEN | 1495 | 213.5714 | UNSE | 1 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31281523_RECOND RESERVATION ROAD 1102 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 5201.84
31281871 | *CANC* R2 RECONDUCT DOLAN ROAD *CANC | 11/02/2016 | 112134625 | 11/02/2016 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/31/2018 | ED.18238.1104 | DOLAN ROAD 1104 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2016 | 12/05/2018 | 2018 | 763 | 109 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31281871_RECOND DOLAN ROAD 1104 #16 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2018-12-05 | 2018-12-05 | # | 2018-12-05 | 2018-12-05 | # | 2018-12-05 | 2018-12-05 | COMP | 2018-11-29 | 2018-11-29 | COMP | 2018-11-29 | 2018-11-29 | COMP | 2018-11-29 | 2018-11-29 | 0 | -6 | 0
31281966 | *CANC*DONOT USE* SUISUN 1109 RECOND*CANC | 11/02/2016 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/01/2017 | ED.06213.1107.SWIT | SWITCHES | 048 | SOLANO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2016 | 05/03/2020 | 2020 | 1278 | 182.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | COMP | 2020-04-10 | 2020-04-10 | COMP | 2020-04-10 | 2020-04-10 | COMP | 2020-04-10 | 2020-04-10 | 0 | -23 | 0
31281968 | *CANC*DONOT USE* DIXON 1103 RECOND *CANC | 11/02/2016 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/01/2017 | ED.06206.1103.SWIT | SWITCHES | 048 | SOLANO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2016 | 05/03/2020 | 2020 | 1278 | 182.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | COMP | 2020-04-10 | 2020-04-10 | COMP | 2020-04-10 | 2020-04-10 | COMP | 2020-04-10 | 2020-04-10 | 0 | -23 | 0
31281969 | RICE 1101 RECOND LINE EXCESSIVE SPLICES | 11/02/2016 | 112134526 | 11/02/2016 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/01/2017 | ED.06283.1101.SWIT | SWITCHES | 006 | COLUSA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2016 | # | OPEN | 1493 | 213.2857 | UNSE | 1 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
31282765 | *CNCL* 2018 OH COND RPLC: EUREKA E 1104 | 11/07/2016 | # | #N/A | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/10/2018 | ED.19233.1104.SWIT | SWITCHES | 012 | HUMBOLDT COUNT | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2016 | # | OPEN | 1488 | 212.5714 | UNSE | 1 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 975.84
31282826 | *CANC*DONOT USE*RECONDUCTOR PAST FU*CANC | 11/09/2016 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/09/2018 | ED.18281.1104 | SISQUOC 1104 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2016 | 05/03/2020 | 2020 | 1271 | 181.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | COMP | 2020-04-10 | 2020-04-10 | COMP | 2020-04-10 | 2020-04-10 | COMP | 2020-04-10 | 2020-04-10 | 0 | -23 | 0
31282830 | *CANC*DONOT USE*R2 SISQUOC 1104_FUS*CANC | 11/09/2016 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/09/2018 | ED.18281.1104 | SISQUOC 1104 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 10,649.000 | 0.000 | 08J | 2016 | 05/03/2020 | 2020 | 1271 | 181.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | 0 | 0 | 0
31282831 | RECONDUCTOR PALMER1101_ LS FCO 1537 | 11/09/2016 | 112149839 | 11/09/2016 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/09/2018 | ED.18303.1101 | PALMER 1101 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2016 | # | OPEN | 1486 | 212.2857 | UNSE | 1 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 1554.68
31282951 | RECONDUCTOR SIX SPANS-GRAND ISLAND 2224 | 11/08/2016 | 112135793 | 11/02/2016 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/29/2017 | JY | JUNK YARD FL TO HOLD DELETED DATA | 039 | SAN JOAQUIN CO | 5535457 | DO 08 - Monthly Forecast Only | 1,454.000 | 0.000 | 08J | 2016 | # | OPEN | 1487 | 212.4286 | UNSC | 6 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | INPR | 2018-05-30 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | -43250 | 0 | 58150.49
31284005 | RECONDUCT PIERCY 2109 | 11/15/2016 | 112164356 | 11/15/2016 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/29/2018 | ED.08391.2109 | PIERCY 2109 | 043 | SANTA CLARA CO | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2016 | # | OPEN | 1480 | 211.4286 | UNSE | 1 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31284005_RECONDUCT PIERCY 2109 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 1309.26
31284643 | Logan Creek 2101_install 12 sets of COs | 11/18/2016 | 112170125 | 11/17/2016 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2019 | ED.10314.2101.SWIT | SWITCHES | 011 | GLENN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2016 | # | OPEN | 1477 | 211 | UNSE | 1 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 562.41
31285060 | *CANC*DONOT USE* SPINGS 1103 - STRO*CANC | 11/20/2016 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/29/2017 | ED.21-J371800000 | EL DORADO MAP J3718 | 009 | EL DORADO COUN | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2016 | 05/03/2020 | 2020 | 1260 | 180 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | COMP | 2020-04-09 | 2020-04-09 | COMP | 2020-04-09 | 2020-04-09 | COMP | 2020-04-09 | 2020-04-09 | 0 | -24 | 0
31285061 | *CANC*DONOT USE*E NICOLAUS 1102 SAC*CANC | 11/20/2016 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/29/2017 | ED.11-U220000000 | MARYSVILLE MAP U22 | 051 | SUTTER COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2016 | 05/03/2020 | 2020 | 1260 | 180 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | COMP | 2020-04-09 | 2020-04-09 | COMP | 2020-04-09 | 2020-04-09 | COMP | 2020-04-09 | 2020-04-09 | 0 | -24 | 0
31285159 | *CANC*DONOT USE* RECONDUCTOR DEEPWA*CANC | 11/21/2016 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/17/2018 | ED.06362.1107.RECL | RECLOSERS | 057 | YOLO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 8,648.000 | 0.000 | 08J | 2016 | 05/03/2020 | 2020 | 1259 | 179.8571 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | COMP | 2020-04-10 | 2020-04-10 | COMP | 2020-04-10 | 2020-04-10 | COMP | 2020-04-10 | 2020-04-10 | 0 | -23 | 0
31286361 | *CNCL* FRUITLAND 42 C/O 7449 | 11/30/2016 | # | #N/A | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/10/2018 | ED.19231.1142.SWIT | SWITCHES | 012 | HUMBOLDT COUNT | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2016 | # | OPEN | 1465 | 209.2857 | UNSE | 1 | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 12258.47
31286365 | CONVERTED TO 35XX SERIES PM - CANCEL PM | 11/30/2016 | 4682552 | 11/30/2016 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/10/2018 | ED.19217.1103.SWIT | SWITCHES | 012 | HUMBOLDT COUNT | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2016 | # | OPEN | 1465 | 209.2857 | UNSE | 1 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 664
31286571 | *R4 EL DORADO PH 2102 HIGH SPLICE AREA | 12/01/2016 | 112196254 | 11/30/2016 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2018 | ED.21-H461000000 | EL DORADO MAP H4610 | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 1,928.000 | 1,928.000 | 08W | 2016 | 07/20/2019 | 2019 | 961 | 137.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | 31286571_EL DORADO PH 2102 HIGH SPLICE | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2018-06-21 | 2018-09-14 | COMP | 2018-09-17 | 2018-09-17 | COMP | 2018-09-17 | 2018-09-17 | COMP | 2018-09-17 | 2018-09-18 | COMP | 2018-09-18 | 2018-10-02 | COMP | 2018-10-02 | 2018-10-11 | 88 | 24 | 174335.72
31286573 | APPLE HILL 2102 HIGH SPLICE AREA | 12/01/2016 | 112196297 | 11/30/2016 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/30/2018 | ED.21-K432500000 | EL DORADO MAP K4325 | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 3,492.000 | 3,492.000 | 08W | 2016 | 05/09/2020 | 2020 | 1255 | 179.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2019-06-25 | 2019-05-06 | COMP | 2019-06-25 | 2019-10-21 | COMP | 2019-06-25 | 2019-10-21 | COMP | 2019-06-25 | 2019-06-26 | COMP | 2019-06-26 | 2019-08-23 | COMP | 2019-08-23 | 2019-08-28 | 118 | -54 | 543235.65
31286660 | *CANC*DO NOT USE* 6295 20 SPAN4ACSR*CANC | 12/01/2016 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/22/2018 | ED.18310.1104 | CABRILLO 1104 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2016 | 05/03/2020 | 2020 | 1249 | 178.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | COMP | 2020-04-10 | 2020-04-10 | COMP | 2020-04-10 | 2020-04-10 | COMP | 2020-04-10 | 2020-04-10 | 0 | -23 | 0
31286706 | *CNCL* FRUITLAND 42 C/O 1679 | 12/01/2016 | # | #N/A | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/29/2018 | ED.19231.1142.SWIT | SWITCHES | 012 | HUMBOLDT COUNT | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2016 | # | OPEN | 1464 | 209.1429 | UNSE | 1 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 371.53
31287794 | LIVE OAK 1104 - ROBINSON RD RECONDUCTOR | 12/07/2016 | 112386399 | 12/06/2016 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/30/2018 | ED.11-L210700000 | MARYSVILLE MAP L2107 | 051 | SUTTER COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2016 | # | OPEN | 1458 | 208.2857 | UNSE | 1 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 3696.87
31288039 | HOOPA 1101 RCOND WITH TREE WIRE | 12/08/2016 | 112390862 | 12/08/2016 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/10/2018 | ED.19240.1101 | HOOPA 1101 | 012 | HUMBOLDT COUNT | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2016 | # | OPEN | 1457 | 208.1429 | UNSE | 1 | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 795.32
31289107 | CONVERTED TO 35XX SERIES PM - CANCEL PM | 12/12/2016 | 4699117 | 12/12/2016 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/10/2018 | ED.19238.1102 | EEL RIVER 1102 | 012 | HUMBOLDT COUNT | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2016 | # | OPEN | 1453 | 207.5714 | UNSE | 1 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 646.54
31289238 | FRUITLAND 1142 INS TREE WIRE LR 6064 | 12/13/2016 | 112403535 | 12/13/2016 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/10/2018 | ED.19231.1142.SWIT | SWITCHES | 012 | HUMBOLDT COUNT | 5535211 | CWSP SPO - SH 08 | 6,266.000 | 6,271.000 | 08W | 2016 | # | OPEN | 1452 | 207.4286 | DOCC | 8 | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | 31289238_Fruitland 1142 Ins Tree Wire | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2018-08-09 | 2019-07-26 | COMP | 2019-06-10 | 2020-01-23 | COMP | 2020-01-23 | 2020-01-23 | COMP | 2020-01-23 | 2020-01-25 | COMP | 2020-01-25 | 2020-02-25 | COMP | 2020-02-25 | 2020-02-27 | 532 | 35 | 2332097.61
31289354 | *Cncl* BIG RIVER 1101 FUSE 5187 RECON | 12/14/2016 | # | #N/A | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/10/2018 | ED.04308.1101.SWIT | SWITCHES | 023 | MENDOCINO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2016 | # | OPEN | 1451 | 207.2857 | UNSE | 1 | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | -986.2
31289564 | *CANC*DONOT USE*RECONDTAP SPERRY & *CANC | 12/14/2016 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/28/2018 | ED.04257.1103.SWIT | SWITCHES | 049 | SONOMA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2016 | 05/03/2020 | 2020 | 1236 | 176.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | COMP | 2020-04-10 | 2020-04-10 | COMP | 2020-04-10 | 2020-04-10 | COMP | 2020-04-10 | 2020-04-10 | 0 | -23 | 0
31289812 | RECOND TAP W TW - LCO 5265 GUALALA 1112 | 12/15/2016 | 112409713 | 12/15/2016 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/28/2018 | ED.04284.1112.REGL | REGULATORS | 023 | MENDOCINO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2016 | # | OPEN | 1450 | 207.1429 | UNSE | 1 | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
31290144 | *CANC*DO NOT USE* SAN RAFAEL 1105 R*CANC | 12/19/2016 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/30/2017 | ED.40-TT33030000.STRU.POLE | NORTH BAY MAP TT3303 POLES | 021 | MARIN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 1,250.000 | 0.000 | 08J | 2016 | 05/03/2020 | 2020 | 1231 | 175.8571 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | COMP | 2020-04-10 | 2020-04-10 | COMP | 2020-04-10 | 2020-04-10 | COMP | 2020-04-10 | 2020-04-10 | 0 | -23 | 0
31290145 | R7 SAN RAFAEL 1107 COND REPLACEMENT | 12/19/2016 | 112416551 | 12/16/2016 | # | Not assigned | 30 | Technically Completed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/30/2017 | ED.40-TT31200000.STRU.POLE | NORTH BAY MAP TT3120 POLES | 021 | MARIN COUNTY | 5535211 | CWSP SPO - SH 08 | 801.000 | 801.000 | 08W | 2016 | # | OPEN | 1446 | 206.5714 | FICL | 10 | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2019-08-12 | 2019-08-12 | COMP | 2019-09-23 | 2019-12-18 | COMP | 2019-12-18 | 2019-12-18 | COMP | 2019-12-18 | 2019-12-19 | COMP | 2019-12-19 | 2019-12-27 | COMP | 2019-12-27 | 2020-01-02 | 128 | 15 | 402000.99
31290146 | *CANC*DONOT USE* PUEBLO 2102 RECOND*CANC | 12/19/2016 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/30/2017 | ED.40-TT31150000.STRU.POLE | NORTH BAY MAP TT3115 POLES | 021 | MARIN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 600.000 | 0.000 | 08J | 2016 | 05/03/2020 | 2020 | 1231 | 175.8571 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | COMP | 2020-04-10 | 2020-04-10 | COMP | 2020-04-10 | 2020-04-10 | COMP | 2020-04-10 | 2020-04-10 | 0 | -23 | 0
31290147 | R7 OLEMA 1101 REPLACE COND VISION RD | 12/19/2016 | 112416601 | 12/16/2016 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/30/2017 | ED.40-QQ24020000.STRU.POLE | NORTH BAY MAP QQ2402 POLES | 021 | MARIN COUNTY | 5535211 | CWSP SPO - SH 08 | 3,174.000 | 3,174.000 | 08W | 2016 | # | OPEN | 1446 | 206.5714 | DOCC | 8 | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | 31290147_Olema Reconductor | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2019-09-20 | 2019-09-20 | INPR | 2019-06-05 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | -43728 | 0 | 791229.79
31290228 | UPGRADE 230' OF 3-1/0 AL_WYANDOTTE 1109 | 12/19/2016 | 112416737 | 12/16/2016 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2019 | ED.10291.1109.SWIT | SWITCHES | 004 | BUTTE COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2016 | # | OPEN | 1446 | 206.5714 | UNSE | 1 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 872.82
31290853 | KNIGHTS LANDING 1102 RECOND LINE EX SPL | 12/20/2016 | 112407585 | 12/14/2016 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/17/2018 | ED.06272.1102.SWIT | SWITCHES | 051 | SUTTER COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2016 | # | OPEN | 1445 | 206.4286 | UNSE | 1 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
31291638 | CAB 1104 CENTRAL EO FLORADALE, LOMPOC | 12/29/2016 | 112443046 | 12/29/2016 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/30/2020 | ED.18310.1104 | CABRILLO 1104 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 3,485.000 | 3,718.000 | 08J | 2016 | 10/17/2020 | 2020 | 1388 | 198.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Cabrillo WD 16-0080322 Reconduct OH Line | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2019-12-19 | 2019-12-19 | COMP | 2020-03-11 | 2020-04-29 | COMP | 2020-04-29 | 2020-04-29 | COMP | 2020-04-29 | 2020-04-30 | COMP | 2020-04-30 | 2020-05-18 | COMP | 2020-05-18 | 2020-05-19 | 132 | 20 | 202174.43
31291639 | FH 1101 O'CONNOR WY RECOND 12 SPANS, SLO | 12/29/2016 | 112443196 | 12/29/2016 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/25/2022 | ED.18295.1101 | FOOTHILL 1101 | 040 | SAN LUIS OBISP | 5535211 | CWSP SPO - SH 08 | 3,100.000 | 0.000 | 08W | 2016 | # | OPEN | 1436 | 205.1429 | ESTS | 2 | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 105347.41
31291669 | *CANC*DO NOT USE* RECOND 10 SPAN 2*CANC | 12/28/2016 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/27/2017 | ED.18281.1103 | SISQUOC 1103 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2016 | 05/03/2020 | 2020 | 1222 | 174.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | COMP | 2020-04-10 | 2020-04-10 | COMP | 2020-04-10 | 2020-04-10 | COMP | 2020-04-10 | 2020-04-10 | 0 | -23 | 0
31291670 | *CANC*DONOT USE*RECONDUCTOR_15 SPAN*CANC | 12/28/2016 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/27/2017 | ED.18281.1102 | SISQUOC 1102 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2016 | 05/03/2020 | 2020 | 1222 | 174.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | COMP | 2020-04-10 | 2020-04-10 | COMP | 2020-04-10 | 2020-04-10 | COMP | 2020-04-10 | 2020-04-10 | 0 | -23 | 0
31291671 | *CANC*DONOT USE*RECOND 3400FT OF 4A*CANC | 12/28/2016 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 07/28/2017 | ED.18205.2102 | SOLEDAD 2102 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2016 | 05/03/2020 | 2020 | 1222 | 174.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | COMP | 2020-04-09 | 2020-04-09 | COMP | 2020-04-09 | 2020-04-09 | COMP | 2020-04-09 | 2020-04-09 | 0 | -24 | 0
31292064 | LOS ALTOS 1104 REPL 3 SPN OH LINE | 12/29/2016 | 112437674 | 12/28/2016 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/22/2017 | ED.08224.1104.TXFR.TROH | OVERHEAD TRANSFORMERS | 043 | SANTA CLARA CO | 5517127 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2016 | # | OPEN | 1436 | 205.1429 | UNSE | 1 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 872.82
31296803 | PN EG-1101 WIREDOWN 08J PROJECT | 01/17/2017 | 4740503 | 01/17/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/29/2018 | ED.02257.1101.TXFR.TROH | OVERHEAD TRANSFORMERS | 041 | SAN MATEO COUN | 5505513 | PN-OH ANNEALED/DETER CNDCTR: PM MGD | 0.000 | 0.000 | 08J | 2017 | # | OPEN | 1417 | 202.4286 | UNSE | 1 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 1726.13
31296941 | PENRYN 1105 - COLWELL TO SWETZER RD 08J | 01/18/2017 | 112477581 | 01/09/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/30/2018 | ED.20-V061200000 | PLACER MAP V0612 | 031 | PLACER COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 660.000 | 0.000 | 08J | 2017 | # | OPEN | 1416 | 202.2857 | UNSE | 1 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 2388.95
31297217 | 2019 PN RW-406 08J WIREDOWN 16-0081064 | 01/19/2017 | 112516189 | 01/17/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/28/2018 | ED.02416.0406.TXFR.TROH | OVERHEAD TRANSFORMERS | 041 | SAN MATEO COUN | 5505513 | PN-OH ANNEALED/DETER CNDCTR: PM MGD | 0.000 | 0.000 | 08J | 2017 | # | OPEN | 1415 | 202.1429 | UNSE | 1 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 538.99
31297273 | RECOND HWY1 (BY SW 92493)- GUALALA 1111 | 01/19/2017 | 112523454 | 01/19/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/28/2018 | JY | JUNK YARD FL TO HOLD DELETED DATA | 023 | MENDOCINO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2017 | # | OPEN | 1415 | 202.1429 | UNSE | 1 | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 1263.81
31297323 | REP 2000' OH COND, INST COS- BUTTE1107 | 01/19/2017 | 112520588 | 01/19/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2018 | ED.11-N211600000 | MARYSVILLE MAP N2116 | 004 | BUTTE COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2017 | # | OPEN | 1415 | 202.1429 | UNSE | 1 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 1341.22
31297367 | WHEATLAND 1104 - GALLAGHER ROAD 08J | 01/19/2017 | 112520804 | 01/19/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/30/2018 | ED.11-S260000000 | MARYSVILLE MAP S26 | 051 | SUTTER COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 4,498.000 | 0.000 | 08J | 2017 | # | OPEN | 1415 | 202.1429 | UNSE | 1 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 3185.32
31297666 | *CANC*DONOT USE* R2 RECOND19 SPANS *CANC | 01/24/2017 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/06/2017 | ED.18257.1103 | DIVIDE 1103 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 5,451.000 | 0.000 | 08J | 2017 | 05/03/2020 | 2020 | 1195 | 170.7143 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | COMP | 2020-04-10 | 2020-04-10 | COMP | 2020-04-10 | 2020-04-10 | COMP | 2020-04-10 | 2020-04-10 | 0 | -23 | 0
31304618 | REPL 1200' OF DET 3-4CU CHICO B 1101 | 02/08/2017 | 112558367 | 02/03/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2018 | ED.10249.1101.SWIT | SWITCHES | 004 | BUTTE COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2017 | # | OPEN | 1395 | 199.2857 | UNSE | 1 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 1005.91
31307406 | **DONT USE***GRAND ISLAND 2224 RECON | 02/23/2017 | # | #N/A | # | Not assigned | 30 | Technically Completed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 08/20/2019 | ED.06246.2224.RECL | RECLOSERS | 048 | SOLANO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2017 | # | OPEN | 1380 | 197.1429 | FICL | 10 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31307406_Grand Island 2224 Recon Station | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 322171.24
31308015 | *CANC* SLO 1107 RECOND 3836 FT 10S *CANC | 03/01/2017 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2019 | ED.18263.1107 | SAN LUIS OBISPO 1107 | 040 | SAN LUIS OBISP | 5535211 | CWSP SPO - SH 08 | 3,836.000 | 0.000 | 08W | 2017 | 09/05/2019 | 2019 | 918 | 131.1429 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 2019-09-05 | 2019-09-05 | # | 2019-09-05 | 2019-09-05 | # | 2019-09-05 | 2019-09-05 | # | 2019-09-05 | 2019-09-05 | # | 2019-09-05 | 2019-09-05 | # | 2019-09-05 | 2019-09-05 | 0 | 0 | 0
31308019 | *CANC*DONOT USE* RECO31SPAN4425FT4A*CANC | 03/03/2017 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/03/2019 | ED.18267.1105 | SANTA MARIA 1105 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 4,160.000 | 0.000 | 08J | 2017 | 05/03/2020 | 2020 | 1157 | 165.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | COMP | 2020-04-10 | 2020-04-10 | COMP | 2020-04-10 | 2020-04-10 | COMP | 2020-04-10 | 2020-04-10 | 0 | -23 | 0
31308789 | RECONDUCTOR WESTLEY 1101-HAMILTON RD | 03/02/2017 | 112403818 | 12/13/2016 | # | Not assigned | 30 | Technically Completed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/21/2018 | ED.16267.1101 | WESTLEY 1101 | 050 | STANISLAUS COU | 5535457 | DO 08 - Monthly Forecast Only | 13,264.000 | 13,200.000 | 08J | 2017 | # | OPEN | 1373 | 196.1429 | FICL | 10 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31308789_RECON WESTLEY 1101-HAMILTON RD | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2018-08-23 | 2020-02-04 | COMP | 2020-02-07 | 2020-02-07 | COMP | 2020-02-07 | 2020-02-07 | COMP | 2020-02-07 | 2020-02-08 | COMP | 2020-02-08 | 2020-06-12 | COMP | 2020-06-12 | 2020-06-15 | 533 | 129 | 677146.46
31308790 | *CANC*DONOT USE*CANAL 1103 RECONDUC*CANC | 03/02/2017 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.25209.1103 | CANAL 1103 | 024 | MERCED COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 7,300.000 | 0.000 | 08J | 2017 | 05/03/2020 | 2020 | 1158 | 165.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | COMP | 2020-04-08 | 2020-04-08 | COMP | 2020-04-08 | 2020-04-08 | COMP | 2020-04-08 | 2020-04-08 | 0 | -25 | 0
31308791 | *CANC*DO NOT USE* 2018 WAHTOKE RECO*CANC | 03/02/2017 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/30/2021 | ED.25453.1110 | WAHTOKE 1110 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2017 | 05/03/2020 | 2020 | 1158 | 165.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31308791_Wahtoke 1110 Reconductor | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | COMP | 2020-04-08 | 2020-04-08 | COMP | 2020-04-08 | 2020-04-08 | COMP | 2020-04-08 | 2020-04-08 | 0 | -25 | 0
31308792 | CORCORAN 1118 RECONDUCTOR | 03/02/2017 | 112410211 | 12/15/2016 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2019 | ED.25217.1118 | CORCORAN 1118 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2017 | # | OPEN | 1373 | 196.1429 | UNSE | 1 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Corcoran 1118 Reconductor | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 3559.34
31308793 | *CANC*DO NOT USE*2019 BOWLES RECON*CANC | 03/02/2017 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2019 | ED.25353.1104 | BOWLES 1104 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2017 | 05/03/2020 | 2020 | 1158 | 165.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Bowles 1104 Reconductor | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | COMP | 2020-04-08 | 2020-04-08 | COMP | 2020-04-08 | 2020-04-08 | COMP | 2020-04-08 | 2020-04-08 | 0 | -25 | 0
31311246 | *CANC* DINUBA 1104 RECOND 1,222' O*CANC | 03/08/2017 | 4797336 | 03/08/2017 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/01/2018 | ED.25234.1101 | REEDLEY 1101 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 1,222.000 | 0.000 | 08J | 2017 | 06/05/2019 | 2019 | 819 | 117 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | COMP | 2019-05-17 | 2019-05-17 | COMP | 2019-05-17 | 2019-05-17 | COMP | 2019-05-17 | 2019-05-17 | 0 | 43602 | 0
31312018 | *CANC*DONOT USE* RECONDCT CASTROVLE*CANC | 03/13/2017 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/29/2018 | ED.18235.2104 | CASTROVILLE 2104 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 2,600.000 | 0.000 | 08J | 2017 | 05/03/2020 | 2020 | 1147 | 163.8571 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | COMP | 2020-04-09 | 2020-04-09 | COMP | 2020-04-09 | 2020-04-09 | COMP | 2020-04-09 | 2020-04-09 | 0 | -24 | 0
31312019 | *CANC*DONOT USE*RECONDUCT SALINAS 1*CANC | 03/13/2017 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/30/2018 | ED.18201.1106 | SALINAS 1106 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 1,000.000 | 0.000 | 08J | 2017 | 05/03/2020 | 2020 | 1147 | 163.8571 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | COMP | 2020-04-09 | 2020-04-09 | COMP | 2020-04-09 | 2020-04-09 | COMP | 2020-04-09 | 2020-04-09 | 0 | -24 | 0
31312040 | *CANC*DONOT USE*R2 RECONDUCT DOLAN *CANC | 03/13/2017 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/30/2018 | ED.18238.1101 | DOLAN ROAD 1101 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 715.000 | 0.000 | 08J | 2017 | 05/03/2020 | 2020 | 1147 | 163.8571 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | COMP | 2020-04-09 | 2020-04-09 | COMP | 2020-04-09 | 2020-04-09 | COMP | 2020-04-09 | 2020-04-09 | 0 | -24 | 0
31313568 | R2 REPLACE OH WIRE P1107 #17-0021747 | 03/21/2017 | 112690399 | 03/17/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/30/2018 | ED.18296.1107 | PRUNEDALE 1107 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 440.000 | 0.000 | 08J | 2017 | # | OPEN | 1354 | 193.4286 | UNSE | 1 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 395.13
31314094 | *CANC* RECON 10 SPANS _3400FT 4ACSR W | 03/22/2017 | 112172026 | 11/18/2016 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 05/01/2018 | ED.18205.2102 | SOLEDAD 2102 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2017 | 04/08/2017 | 2017 | 17 | 2.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2017-04-08 | 2017-04-08 | # | 2017-04-08 | 2017-04-08 | # | 2017-04-08 | 2017-04-08 | COMP | 2017-04-08 | 2017-04-08 | COMP | 2017-04-08 | 2017-04-08 | COMP | 2017-04-08 | 2017-04-08 | 0 | 0 | 0
31314138 | *CANC*DONOT USE* NEW HOPE 1101 2,20*CANC | 03/22/2017 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/01/2018 | ED.16208.1101 | NEW HOPE 1101 | 039 | SAN JOAQUIN CO | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2017 | 05/03/2020 | 2020 | 1138 | 162.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | COMP | 2020-04-08 | 2020-04-08 | COMP | 2020-04-08 | 2020-04-08 | COMP | 2020-04-08 | 2020-04-08 | 0 | -25 | 0
31314313 | *CANC* *DO NOT USE* RECONDUCTOR ST*CANC | 03/23/2017 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/20/2019 | ED.25461.1105 | STOREY 1105 | 020 | MADERA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2017 | 06/05/2019 | 2019 | 804 | 114.8571 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31314313_Reconductor Storey 1105 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2019-06-05 | 2019-06-05 | # | 2019-06-05 | 2019-06-05 | # | 2019-06-05 | 2019-06-05 | COMP | 2019-05-17 | 2019-05-17 | COMP | 2019-05-17 | 2019-05-17 | COMP | 2019-05-17 | 2019-05-17 | 0 | -19 | 0
31314952 | *CANC*R2 RECONDCT CASTROVLE 2103 WD#17-0 | 03/27/2017 | 112709872 | 03/27/2017 | # | Not assigned | 30 | Technically Completed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/30/2018 | ED.18235.2103 | CASTROVILLE 2103 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 720.000 | 0.000 | 08J | 2017 | # | OPEN | 1348 | 192.5714 | PROD | Other | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | -49.03
31316185 | *CANC*DONOT USE* WHISTMAN1106 CO582*CANC | 04/01/2017 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/20/2019 | ED.08363.1106.TXFR.TROH | OVERHEAD TRANSFORMERS | 043 | SANTA CLARA CO | 5517127 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2017 | 05/03/2020 | 2020 | 1128 | 161.1429 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | COMP | 2020-04-08 | 2020-04-08 | COMP | 2020-04-08 | 2020-04-08 | COMP | 2020-04-08 | 2020-04-08 | 0 | -25 | 0
31316186 | *CANC* HMB1102 CO12457 #17-00290*CANC | 04/01/2017 | 112726529 | 03/31/2017 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/24/2019 | ED.02410.1102.TXFR.TROH | OVERHEAD TRANSFORMERS | 041 | SAN MATEO COUN | 5535211 | CWSP SPO - SH 08 | 4,000.000 | 0.000 | 08W | 2017 | 12/12/2018 | 2018 | 620 | 88.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 2018-12-05 | 2018-12-05 | # | 2018-12-05 | 2018-12-05 | # | 2018-12-05 | 2018-12-05 | COMP | 2018-10-17 | 2018-10-17 | COMP | 2018-10-17 | 2018-10-17 | COMP | 2018-10-17 | 2018-10-17 | 0 | -49 | 0
31316283 | *CANC* RECONDUCTOR CANAL 1104 WD *CANC | 04/03/2017 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/07/2021 | ED.25209.1104 | CANAL 1104 | 024 | MERCED COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 1,440.000 | 0.000 | 08J | 2017 | 05/03/2020 | 2020 | 1126 | 160.8571 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31316283_RECONDUCTOR CANAL 1104 WD | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | 0 | 0 | 0
31317925 | WAHTOKE 1107 RECOND 1000FT 6CU | 04/06/2017 | 112738246 | 04/05/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/28/2018 | ED.25453.1107 | WAHTOKE 1107 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 1,000.000 | 0.000 | 08J | 2017 | # | OPEN | 1338 | 191.1429 | UNSE | 1 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
31318381 | *CANC*DO NOT USE*LINDEN 1102 RECOND*CANC | 04/07/2017 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/30/2018 | ED.16207.1102 | LINDEN 1102 | 039 | SAN JOAQUIN CO | 5535457 | DO 08 - Monthly Forecast Only | 760.000 | 0.000 | 08J | 2017 | 05/03/2020 | 2020 | 1122 | 160.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | COMP | 2020-04-08 | 2020-04-08 | COMP | 2020-04-08 | 2020-04-08 | COMP | 2020-04-08 | 2020-04-08 | 0 | -25 | 0
31318944 | *CANC*DONOT USE*COND21SPANS, ALMOST*CANC | 04/11/2017 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/06/2018 | ED.18260.1106 | OCEANO 1106 | 040 | SAN LUIS OBISP | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2017 | 05/03/2020 | 2020 | 1118 | 159.7143 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | COMP | 2020-04-10 | 2020-04-10 | COMP | 2020-04-10 | 2020-04-10 | COMP | 2020-04-10 | 2020-04-10 | 0 | -23 | 0
31319329 | SAN LUIS OBISP1103 - RECOND WITH 2CU TW | 04/13/2017 | 112762682 | 04/12/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/12/2019 | ED.18263.1103 | SAN LUIS OBISPO 1103 | 040 | SAN LUIS OBISP | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2017 | # | OPEN | 1331 | 190.1429 | UNSE | 1 | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 610.78
31319443 | *CANC*DONOT USE* RECOND 7-SPANS ELY*CANC | 04/13/2017 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/28/2018 | ED.04349.1103.RECL | RECLOSERS | 049 | SONOMA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2017 | 05/03/2020 | 2020 | 1116 | 159.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | COMP | 2020-04-10 | 2020-04-10 | COMP | 2020-04-10 | 2020-04-10 | COMP | 2020-04-10 | 2020-04-10 | 0 | -23 | 0
31319444 | RECON 5-SPANS PORTER CRK RD-RINCON 1103 | 04/13/2017 | 112761026 | 04/12/2017 | # | Not assigned | 30 | Technically Completed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/28/2018 | JY | JUNK YARD FL TO HOLD DELETED DATA | 049 | SONOMA COUNTY | 5535211 | CWSP SPO - SH 08 | 1,284.000 | 1,279.000 | 08W | 2017 | # | OPEN | 1331 | 190.1429 | FICL | 10 | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2019-12-14 | 2019-12-14 | COMP | 2020-01-19 | 2020-01-19 | COMP | 2020-01-19 | 2020-01-19 | INPR | 2020-11-18 | 0 | # | 0 | 0 | # | 0 | 0 | 36 | -43849 | 3149413.62
31319901 | *CANC*DONOT USE*RECOND_5656FT 3-6CU*CANC | 04/17/2017 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 02/14/2019 | ED.18282.1102 | MESA 1102 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2017 | 05/03/2020 | 2020 | 1112 | 158.8571 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | COMP | 2020-04-10 | 2020-04-10 | COMP | 2020-04-10 | 2020-04-10 | COMP | 2020-04-10 | 2020-04-10 | 0 | -23 | 0
31320148 | *CANC*NAPA 1103 OH RECONDUCTORING P*CANC | 04/18/2017 | 112774649 | 04/17/2017 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2017 | ED.04202.1103.SWIT | SWITCHES | 028 | NAPA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2017 | 10/03/2019 | 2019 | 898 | 128.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2019-10-03 | 2019-10-03 | # | 2019-10-03 | 2019-10-03 | # | 2019-10-03 | 2019-10-03 | COMP | 2019-09-13 | 2019-09-13 | COMP | 2019-09-13 | 2019-09-13 | COMP | 2019-09-13 | 2019-09-13 | 0 | -20 | 0
31320621 | *CANC*DONOT USE* RECOND HWY 20-FTBR*CANC | 04/19/2017 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/28/2018 | ED.04276.1102.CAPA | CAPACITORS | 023 | MENDOCINO COUN | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2017 | 05/03/2020 | 2020 | 1110 | 158.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | COMP | 2020-04-08 | 2020-04-08 | COMP | 2020-04-08 | 2020-04-08 | COMP | 2020-04-08 | 2020-04-08 | 0 | -25 | 0
31321841 | *CANC* RECONDUCTORING 17-003671*CANC | 04/26/2017 | 112804988 | 04/26/2017 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/26/2019 | ED.18310.1104 | CABRILLO 1104 | 040 | SAN LUIS OBISP | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2017 | 11/03/2018 | 2018 | 556 | 79.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2018-11-03 | 2018-11-03 | # | 2018-11-03 | 2018-11-03 | # | 2018-11-03 | 2018-11-03 | COMP | 2018-10-19 | 2018-10-19 | COMP | 2018-10-19 | 2018-10-19 | COMP | 2018-10-19 | 2018-10-19 | 0 | -15 | 0
31323235 | *CANC*CABRILLIO 1103 6700FT RECON ADD 3F | 05/02/2017 | 112818395 | 04/28/2017 | # | Not assigned | 40 | Closed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 04/28/2019 | ED.18310.1103 | CABRILLO 1103 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2017 | 03/02/2019 | 2019 | 669 | 95.5714 | CLSD | 12 | E070 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2019-03-03 | 2019-03-03 | # | 2019-03-03 | 2019-03-03 | # | 2019-03-03 | 2019-03-03 | COMP | 2019-02-27 | 2019-02-27 | COMP | 2019-02-27 | 2019-02-27 | COMP | 2019-02-27 | 2019-02-27 | 0 | -4 | 0
31323676 | RECOND 1327FT OF 4ACSR W 2CU | 05/04/2017 | # | #N/A | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 05/04/2019 | ED.18267.1106 | SANTA MARIA 1106 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2017 | # | OPEN | 1310 | 187.1429 | UNSE | 1 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 913.67
31324095 | *CANC*DONOT USE* 2RPLC OH WIRE ON G*CANC | 05/05/2017 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/30/2019 | ED.18233.1101 | GABILAN 1101 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 5,675.000 | 0.000 | 08J | 2017 | 05/03/2020 | 2020 | 1094 | 156.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Gabilan 1101 OH Reconductor Project | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | COMP | 2020-04-09 | 2020-04-09 | COMP | 2020-04-09 | 2020-04-09 | COMP | 2020-04-09 | 2020-04-09 | 0 | -24 | 0
31324412 | *CANC*DONOT USE* RECONDUCTOR ATWATE*CANC | 05/08/2017 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/13/2019 | ED.25361.1106 | ATWATER 1106 | 024 | MERCED COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2017 | 05/03/2020 | 2020 | 1091 | 155.8571 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | COMP | 2020-04-09 | 2020-04-09 | COMP | 2020-04-09 | 2020-04-09 | COMP | 2020-04-09 | 2020-04-09 | 0 | -24 | 0
31324677 | *CANC* *DO NOT USE* TERMINOUS 110*CANC | 05/09/2017 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/01/2019 | ED.16302.1102 | TERMINOUS 1102 | 039 | SAN JOAQUIN CO | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2017 | 11/03/2019 | 2019 | 908 | 129.7143 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Terminous 1102 Reconductor | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2019-11-03 | 2019-11-03 | # | 2019-11-03 | 2019-11-03 | # | 2019-11-03 | 2019-11-03 | COMP | 2019-10-29 | 2019-10-29 | COMP | 2019-10-29 | 2019-10-29 | COMP | 2019-10-29 | 2019-10-29 | 0 | -5 | 0
31325844 | *CANC*DONOT USE* SF A-1115 WIRE DOW*CANC | 05/15/2017 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 08/25/2017 | ED.02203.1115.SWIT | SWITCHES | 038 | SAN FRANCISCO | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2017 | 05/03/2020 | 2020 | 1084 | 154.8571 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | COMP | 2020-04-09 | 2020-04-09 | COMP | 2020-04-09 | 2020-04-09 | COMP | 2020-04-09 | 2020-04-09 | 0 | -24 | 0
31326119 | WEIMAR 1101 - NATURE'S WAY RECONDUCTOR | 05/16/2017 | 112874571 | 05/16/2017 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/01/2019 | ED.20-R110100000 | PLACER MAP R1101 | 031 | PLACER COUNTY | 5535211 | CWSP SPO - SH 08 | 2,990.000 | 2,990.000 | 08W | 2017 | 05/30/2020 | 2020 | 1110 | 158.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | 31326119_Weimar 1101 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2018-08-16 | 2019-11-15 | COMP | 2019-11-22 | 2019-12-30 | COMP | 2019-12-30 | 2020-05-06 | COMP | 2020-05-06 | 2020-05-07 | COMP | 2020-05-07 | 2020-05-22 | COMP | 2020-05-22 | 2020-05-28 | 629 | 22 | 997479.35
31329860 | *CANC*DONOT USE* PN WIREDOWN 17-004*CANC | 06/05/2017 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/28/2018 | ED.02264.1112.SWIT | SWITCHES | 041 | SAN MATEO COUN | 5505513 | PN-OH ANNEALED/DETER CNDCTR: PM MGD | 0.000 | 0.000 | 08J | 2017 | 05/03/2020 | 2020 | 1063 | 151.8571 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | COMP | 2020-04-08 | 2020-04-08 | COMP | 2020-04-08 | 2020-04-08 | COMP | 2020-04-08 | 2020-04-08 | 0 | -25 | 0
31330242 | COLUSA 1103 RECOND 7000 FT 6C @ C/O 3557 | 06/07/2017 | 112928808 | 06/05/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/05/2019 | ED.06202.1100.RECL | RECLOSERS | 006 | COLUSA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 6,034.000 | 6,034.000 | 08J | 2017 | # | OPEN | 1276 | 182.2857 | DOCC | 8 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2020-07-24 | 2020-07-24 | INPR | 2020-07-21 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | -44036 | 0 | 579608.09
31330635 | FORESTHILL 1102 - SPRING GARDEN RD 08W | 06/09/2017 | 112939790 | 06/08/2017 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2018 | ED.20-R130000000 | PLACER MAP R13 | 031 | PLACER COUNTY | 5535211 | CWSP SPO - SH 08 | 11,308.000 | 11,308.000 | 08W | 2017 | 05/30/2020 | 2020 | 1086 | 155.1429 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | 31330635_FORESTHILL 1102 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2018-07-10 | 2018-12-03 | COMP | 2018-12-04 | 2018-12-04 | COMP | 2018-12-04 | 2018-12-04 | COMP | 2018-12-04 | 2018-12-05 | COMP | 2018-12-05 | 2018-12-11 | COMP | 2018-12-11 | 2018-12-13 | 147 | 9 | 581153.42
31334182 | *CANC*DONOT USE*REPLACE 4800'3-6CU *CANC | 06/27/2017 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/30/2018 | ED.13-K242300000.PRIM.FUSE | OROVILLE K2423 FUSES | 004 | BUTTE COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 4,800.000 | 0.000 | 08J | 2017 | 05/03/2020 | 2020 | 1041 | 148.7143 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | COMP | 2020-04-08 | 2020-04-08 | COMP | 2020-04-08 | 2020-04-08 | COMP | 2020-04-08 | 2020-04-08 | 0 | -25 | 0
31334290 | RECON 24 SPANS -ALBION RIDGE RD | 06/28/2017 | 112994612 | 06/26/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/28/2018 | ED.04298.1101.RECL | RECLOSERS | 023 | MENDOCINO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2017 | # | OPEN | 1255 | 179.2857 | UNSE | 1 | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 1413.82
31334291 | RECON-6 SPANS CAMP ONE TEN MILE FT BRAGG | 06/28/2017 | 112994395 | 06/26/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/28/2018 | ED.04276.1101.SWIT | SWITCHES | 023 | MENDOCINO COUN | 5535211 | CWSP SPO - SH 08 | 2,710.000 | 0.000 | 08W | 2017 | # | OPEN | 1255 | 179.2857 | PEND | 5 | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 291473.71
31334292 | RECON 9-SPANS, AUSTIN CREEK RD | 06/28/2017 | 112994393 | 06/26/2017 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/28/2018 | JY | JUNK YARD FL TO HOLD DELETED DATA | 049 | SONOMA COUNTY | 5535211 | CWSP SPO - SH 08 | 2,513.000 | 2,493.000 | 08W | 2017 | 11/21/2020 | 2020 | 1242 | 177.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2019-09-20 | 2019-09-20 | COMP | 2019-10-02 | 2020-01-19 | COMP | 2020-01-19 | 2020-01-19 | COMP | 2020-01-19 | 2020-09-10 | COMP | 2020-09-10 | 2020-09-17 | COMP | 2020-09-17 | 2020-09-17 | 121 | 242 | 1033385.2
31335251 | CATLETT 1102 - SANKEY ROAD RECONDUCTOR | 07/05/2017 | 113008551 | 06/29/2017 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/30/2019 | ED.11-X250400000 | MARYSVILLE MAP X2504 | 051 | SUTTER COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 11,455.000 | 10,736.000 | 08J | 2017 | 10/10/2020 | 2020 | 1193 | 170.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31335251_Catlett 1102 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2020-02-28 | 2019-10-08 | COMP | 2020-01-21 | 2020-02-28 | COMP | 2020-02-28 | 2020-02-28 | COMP | 2020-02-28 | 2020-03-02 | COMP | 2020-03-02 | 2020-03-10 | COMP | 2020-03-10 | 2020-03-10 | 0 | 11 | 1044215.47
31335358 | R1_PN WIREDOWN - LAWNDALE 402 | 07/05/2017 | 113006410 | 06/29/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/29/2019 | ED.02244.0402.CAPA | CAPACITORS | 041 | SAN MATEO COUN | 5505513 | PN-OH ANNEALED/DETER CNDCTR: PM MGD | 0.000 | 0.000 | 08J | 2017 | # | OPEN | 1248 | 178.2857 | UNSE | 1 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
31336579 | *CANC*DO NOT USE* RECONDUCTOR 7 SPA*CANC | 07/12/2017 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/01/2019 | ED.01447.1106 | DUMBARTON 1106 | 001 | ALAMEDA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2017 | 05/03/2020 | 2020 | 1026 | 146.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | COMP | 2020-04-08 | 2020-04-08 | COMP | 2020-04-08 | 2020-04-08 | COMP | 2020-04-08 | 2020-04-08 | 0 | -25 | 0
31338871 | RELIAIBLITY RICHMOND-REPL #6 CU-UWF_PH2 | 07/25/2017 | 113074026 | 07/24/2017 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/26/2018 | ED.01250.1113 | EL CERRITO G 1113 | 007 | CONTRA COSTA C | 5535211 | CWSP SPO - SH 08 | 3,505.000 | 3,505.000 | 08W | 2017 | 04/25/2020 | 2020 | 1005 | 143.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | 31338871_RELIAIBLITY RICHMOND-REPL 6 PH2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2018-10-14 | 2018-10-14 | COMP | 2018-06-26 | 2018-11-15 | COMP | 2018-11-15 | 2018-11-15 | COMP | 2018-11-15 | 2018-11-16 | COMP | 2018-11-16 | 2018-11-19 | COMP | 2018-11-19 | 2018-11-20 | 32 | 5 | 654036.73
31338877 | DUMBARTON 2111 FUSE 7809 PROJECT | 07/25/2017 | 113084224 | 07/25/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2018 | ED.01447.2111 | DUMBARTON 2111 | 001 | ALAMEDA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 5,379.000 | 0.000 | 08J | 2017 | # | OPEN | 1228 | 175.4286 | UNSC | 6 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | DUMBARTON 2111 FUSE 7809 PROJECT | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | INPR | 2018-08-06 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | -43318 | 0 | 118246.62
31338891 | BEAR VALLEY 2105-REPLAC 8MILE OH W/397AL | 07/24/2017 | 113073622 | 07/24/2017 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/11/2017 | ED.25219.2105 | BEAR VALLEY 2105 | 022 | MARIPOSA COUNT | 5535457 | DO 08 - Monthly Forecast Only | 42,240.000 | 42,240.000 | 08J | 2017 | 08/22/2020 | 2020 | 1125 | 160.7143 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2017-08-25 | 2017-08-25 | INPR | 2017-08-31 | 2020-08-22 | COMP | 2017-09-18 | 2017-09-18 | COMP | 2017-09-18 | 2020-08-06 | COMP | 2020-08-06 | 2020-08-06 | COMP | 2020-08-06 | 2020-08-06 | 24 | 1053 | 195709.3
31339501 | REPL DET COND BAGGET MARYSVILLE RD | 07/27/2017 | 113090688 | 07/27/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2018 | ED.10291.1106.SWIT | SWITCHES | 004 | BUTTE COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2017 | # | OPEN | 1226 | 175.1429 | UNSE | 1 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 1291.93
31340098 | ****CANCELLED***GRAND ISLAND 2226 RECOND | 08/01/2017 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2019 | ED.06246.2226.SWIT | SWITCHES | 048 | SOLANO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 2,600.000 | 0.000 | 08J | 2017 | 02/29/2020 | 2020 | 942 | 134.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2020-02-29 | 2020-02-29 | # | 2020-02-29 | 2020-02-29 | # | 2020-02-29 | 2020-02-29 | # | 2020-02-29 | 2020-02-29 | # | 2020-02-29 | 2020-02-29 | # | 2020-02-29 | 2020-02-29 | 0 | 0 | 886.91
31340108 | WYANDOTTE 1106 OPHIR RD 8,400'(NO WP YR) | 08/01/2017 | 4997767 | 08/01/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2019 | ED.10291.1106.RECL | RECLOSERS | 004 | BUTTE COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2017 | # | OPEN | 1221 | 174.4286 | UNSE | 1 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 2969.63
31343120 | *CANC*DONOT USE*2019 VALLEJO B 413 *CANC | 08/17/2017 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2019 | ED.04245.0413 | VALLEJO B 0413 | 048 | SOLANO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2017 | 05/03/2020 | 2020 | 990 | 141.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | COMP | 2020-04-10 | 2020-04-10 | COMP | 2020-04-10 | 2020-04-10 | COMP | 2020-04-10 | 2020-04-10 | 0 | -23 | 0
31343123 | *CANC*DO NOT USE*2019 PUEBLO HIGH *CANC | 08/17/2017 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2019 | ED.04329.1104 | PUEBLO 1104 | 028 | NAPA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2017 | 05/03/2020 | 2020 | 990 | 141.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | COMP | 2020-04-09 | 2020-04-09 | COMP | 2020-04-09 | 2020-04-09 | COMP | 2020-04-09 | 2020-04-09 | 0 | -24 | 0
31343124 | *CANC*DONOT USE*2019 WILLOW PASS 21*CANC | 08/17/2017 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2019 | ED.01391.2108 | WILLOW PASS 2108 | 007 | CONTRA COSTA C | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2017 | 05/03/2020 | 2020 | 990 | 141.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | COMP | 2020-04-07 | 2020-04-07 | COMP | 2020-04-07 | 2020-04-07 | COMP | 2020-04-07 | 2020-04-07 | 0 | -26 | 0
31343125 | *CANC*DONOT USE* 2019 NORTH TOWER 2*CANC | 08/17/2017 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2019 | ED.04204.2201 | NORTH TOWER 2201 | 048 | SOLANO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2017 | 05/03/2020 | 2020 | 990 | 141.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | COMP | 2020-04-10 | 2020-04-10 | COMP | 2020-04-10 | 2020-04-10 | COMP | 2020-04-10 | 2020-04-10 | 0 | -23 | 0
31343126 | *CANC* 2019 TARAVAL 402 HIGH SPLICE*CANC | 08/17/2017 | 5018000 | 08/17/2017 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2019 | ED.02250.0402 | TARAVAL 0402 | 038 | SAN FRANCISCO | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2017 | 04/03/2019 | 2019 | 594 | 84.8571 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | COMP | 2019-03-28 | 2019-03-28 | COMP | 2019-03-28 | 2019-03-28 | COMP | 2019-03-28 | 2019-03-28 | 0 | 43552 | 0
31343127 | 2019 WILLOW PASS 2108 HIGH SPLICE 2 | 08/17/2017 | 113163071 | 08/16/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2019 | ED.01391.2108 | WILLOW PASS 2108 | 007 | CONTRA COSTA C | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2017 | # | OPEN | 1205 | 172.1429 | UNSE | 1 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 383.53
31343236 | *CANC*DONOT USE*2019 PUEBLO HIGH S*CANC | 08/18/2017 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2019 | ED.04329.1104 | PUEBLO 1104 | 028 | NAPA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2017 | 05/03/2020 | 2020 | 989 | 141.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | COMP | 2020-04-09 | 2020-04-09 | COMP | 2020-04-09 | 2020-04-09 | COMP | 2020-04-09 | 2020-04-09 | 0 | -24 | 0
31343237 | 2019 KIRKER 2107 HIGH SPLICE COUNT | 08/18/2017 | 113163131 | 08/16/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2019 | ED.01445.2107 | KIRKER 2107 | 007 | CONTRA COSTA C | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2017 | # | OPEN | 1204 | 172 | UNSE | 1 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 2730.11
31343238 | *CANC*DONOT USE* 2019 YOSEMITE 401 *CANC | 08/18/2017 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2019 | ED.02249.0401 | YOSEMITE 0401 | 038 | SAN FRANCISCO | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2017 | 05/03/2020 | 2020 | 989 | 141.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | COMP | 2020-04-09 | 2020-04-09 | COMP | 2020-04-09 | 2020-04-09 | COMP | 2020-04-09 | 2020-04-09 | 0 | -24 | 0
31343500 | CWSP ORINDA 401 HIGH SPLICE COUNT | 08/18/2017 | 113163138 | 08/16/2017 | # | Not assigned | 30 | Technically Completed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 05/13/2020 | ED.01235.0401 | ORINDA 0401 | 007 | CONTRA COSTA C | 5535211 | CWSP SPO - SH 08 | 8,023.000 | 8,400.000 | 08W | 2017 | # | OPEN | 1204 | 172 | FICL | 10 | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2020-05-13 | 2020-05-13 | COMP | 2020-02-25 | 2020-05-15 | COMP | 2020-05-15 | 2020-05-15 | COMP | 2020-05-15 | 2020-05-19 | COMP | 2020-05-19 | 2020-07-15 | COMP | 2020-07-15 | 2020-07-17 | 2 | 63 | 1937387.23
31343501 | 2019 ACTON 401 HIGH SPLICE COUNT | 08/18/2017 | 113163201 | 08/16/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2019 | ED.02247.0401 | ACTON 0401 | 038 | SAN FRANCISCO | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2017 | # | OPEN | 1204 | 172 | UNSE | 1 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
31344013 | 2019 LAKEWOOD 2110 HIGH SPLICE COUNT | 08/22/2017 | 113163204 | 08/16/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2019 | ED.01353.2110 | LAKEWOOD 2110 | 007 | CONTRA COSTA C | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2017 | # | OPEN | 1200 | 171.4286 | UNSE | 1 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 2840.81
31344014 | 2019 RANDOLPH 403 HIGH SPLICE COUNT | 08/22/2017 | 113163206 | 08/16/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2019 | ED.02259.0403 | RANDOLPH 0403 | 038 | SAN FRANCISCO | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2017 | # | OPEN | 1200 | 171.4286 | UNSE | 1 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
31344015 | CNCL: 2019 CALISTOGA 1101 HIGH SPLICE CT | 08/22/2017 | # | #N/A | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2019 | ED.04271.1101 | CALISTOGA 1101 | 028 | NAPA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2017 | # | OPEN | 1200 | 171.4286 | DOCC | 8 | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 31733.6
31344016 | 2019 OLEMA 1101 HIGH SPLICE CNT_1 | 08/22/2017 | 113163270 | 08/16/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2019 | ED.04229.1101 | OLEMA 1101 | 021 | MARIN COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2017 | # | OPEN | 1200 | 171.4286 | UNSE | 1 | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 818.88
31344017 | 2019 OLEMA 1101 HIGH SPLICE CNT_2 | 08/22/2017 | 113163271 | 08/16/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2019 | ED.04229.1101 | OLEMA 1101 | 021 | MARIN COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2017 | # | OPEN | 1200 | 171.4286 | UNSE | 1 | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 1088.43
31344213 | ARBUCKLE 1102 8334' WIRE DOWN (NO WP YR) | 08/23/2017 | 113165945 | 08/17/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2021 | ED.06205.1102.SWIT | SWITCHES | 006 | COLUSA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2017 | # | OPEN | 1199 | 171.2857 | UNSE | 1 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 3064.22
31350280 | *CANC*DONOT USE* 2019 PN DC-1112 WI*CANC | 09/11/2017 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2019 | ED.02264.1112.SWIT | SWITCHES | 041 | SAN MATEO COUN | 5505513 | PN-OH ANNEALED/DETER CNDCTR: PM MGD | 0.000 | 0.000 | 08J | 2017 | 05/03/2020 | 2020 | 965 | 137.8571 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | COMP | 2020-04-08 | 2020-04-08 | COMP | 2020-04-08 | 2020-04-08 | COMP | 2020-04-08 | 2020-04-08 | 0 | -25 | 0
31350562 | *CANC*DONOT USE*EL CAPITAN 1104 REC*CANC | 09/12/2017 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2019 | ED.72-07131C0000.STRU.POLE | MERCED MAP 07131C POLES | 024 | MERCED COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 2,200.000 | 0.000 | 08J | 2017 | 05/03/2020 | 2020 | 964 | 137.7143 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | COMP | 2020-04-09 | 2020-04-09 | COMP | 2020-04-09 | 2020-04-09 | COMP | 2020-04-09 | 2020-04-09 | 0 | -24 | 0
31351748 | *CANC*DONOT USE*2019 08J PN SL-1107*CANC | 09/19/2017 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/27/2019 | ED.02272.1107.TXFR.TROH | OVERHEAD TRANSFORMERS | 041 | SAN MATEO COUN | 5517127 | DO 08 - Monthly Forecast Only | 1,700.000 | 0.000 | 08J | 2017 | 05/03/2020 | 2020 | 957 | 136.7143 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | COMP | 2020-04-08 | 2020-04-08 | COMP | 2020-04-08 | 2020-04-08 | COMP | 2020-04-08 | 2020-04-08 | 0 | -25 | 0
31352018 | *CANC* MALAGA 1103 RECONDUCTORING *CANC | 09/20/2017 | 5069772 | 09/20/2017 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2019 | ED.70-1421600000.STRU.POLE | FRESNO 14216 POLES | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2017 | 10/04/2017 | 2017 | 14 | 2 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | COMP | 2017-10-02 | 2017-10-02 | COMP | 2017-10-02 | 2017-10-02 | COMP | 2017-10-02 | 2017-10-02 | 0 | 43010 | 0
31352062 | L-1102 - 48TH AVE RECONDUCTORING PROJECT | 09/20/2017 | 113262162 | 09/19/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/04/2020 | ED.02226.1102 | SF L 1102 | 038 | SAN FRANCISCO | 5535457 | DO 08 - Monthly Forecast Only | 2,888.000 | 0.000 | 08J | 2017 | # | OPEN | 1171 | 167.2857 | DOCC | 8 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31352062_L-1102 48TH AVE RECONDUCTORING | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 1113164.25
31354054 | *CANC*DONOT USE* 2019 08J PN EG-110*CANC | 10/04/2017 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/27/2019 | ED.02257.1101.TXFR.TROH | OVERHEAD TRANSFORMERS | 041 | SAN MATEO COUN | 5505513 | PN-OH ANNEALED/DETER CNDCTR: PM MGD | 1,700.000 | 0.000 | 08J | 2017 | 05/03/2020 | 2020 | 942 | 134.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | COMP | 2020-04-08 | 2020-04-08 | COMP | 2020-04-08 | 2020-04-08 | COMP | 2020-04-08 | 2020-04-08 | 0 | -25 | 0
31354827 | *CANC* EIGHT MILE 2102 RECONDUCTOR *CANC | 10/05/2017 | 113674992 | 10/05/2017 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2019 | ED.93-S120000000.STRU.POLE | STOCKTON S12 POLES | 039 | SAN JOAQUIN CO | 5535457 | DO 08 - Monthly Forecast Only | 5,100.000 | 0.000 | 08J | 2017 | 05/03/2020 | 2020 | 941 | 134.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31354827_EIGHT MILE 2102 RECONDUCTORING | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | COMP | 2020-04-10 | 2020-04-10 | COMP | 2020-04-10 | 2020-04-10 | COMP | 2020-04-10 | 2020-04-10 | 0 | -23 | 0
31354872 | *CNCL* EEL RIVER 1102 FU1903 | 10/05/2017 | # | #N/A | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/11/2019 | ED.35-V070000000.STRU.POLE | FORTUNA V07 POLES | 012 | HUMBOLDT COUNT | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2017 | # | OPEN | 1156 | 165.1429 | UNSE | 1 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 547.37
31354874 | CONVERTED TO 35XX SERIES PM - CANCEL PM | 10/05/2017 | 5107375 | 10/05/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/25/2019 | ED.19238.1102 | EEL RIVER 1102 | 012 | HUMBOLDT COUNT | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2017 | # | OPEN | 1156 | 165.1429 | UNSE | 1 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 802.49
31354878 | CONVERTED TO 35XX SERIES PM - CANCEL PM | 10/05/2017 | 5107395 | 10/05/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/25/2019 | JY | JUNK YARD FL TO HOLD DELETED DATA | 012 | HUMBOLDT COUNT | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2017 | # | OPEN | 1156 | 165.1429 | UNSE | 1 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 847.34
31354988 | TULUCAY 1101 RECOND WITH TREE WIRE | 10/05/2017 | 113676059 | 10/05/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/05/2018 | ED.42-NN40000000.STRU.POLE | SILVERADO MAP NN40 POLES | 028 | NAPA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2017 | # | OPEN | 1156 | 165.1429 | UNSE | 1 | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 2877.76
31354989 | NAPA 1105 HIGH SPLICE COUNT | 10/05/2017 | 113676082 | 10/05/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/05/2018 | ED.42-LL38170000.STRU.POLE | SILVERADO MAP LL3817 POLES | 028 | NAPA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2017 | # | OPEN | 1156 | 165.1429 | UNSE | 1 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 2074.11
31354990 | TULUCAY 1101 HIGH SPLICE COUNT | 10/05/2017 | 113676289 | 10/05/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/05/2018 | ED.42-NN39000000.STRU.POLE | SILVERADO NN39 POLES | 028 | NAPA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2017 | # | OPEN | 1156 | 165.1429 | UNSE | 1 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
31354991 | PUEBLO 2102 HIGH SPLICE COUNT | 10/05/2017 | 113676470 | 10/05/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/05/2018 | ED.42-JJ36000000.STRU.POLE | SILVERADO MAP JJ36 POLES | 028 | NAPA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2017 | # | OPEN | 1156 | 165.1429 | UNSE | 1 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 3383.61
31354992 | GREENBRAE 1104 HIGH SPLICE COUNT | 10/05/2017 | 113676471 | 10/05/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/05/2018 | JY | JUNK YARD FL TO HOLD DELETED DATA | 021 | MARIN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2017 | # | OPEN | 1156 | 165.1429 | UNSE | 1 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 2231.05
31355773 | *CANC* RECOND GREEN VALLEY 2103 RE | 10/10/2017 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/29/2019 | ED.08319.2103 | GREEN VALLEY 2103 | 044 | SANTA CRUZ COU | 5535457 | DO 08 - Monthly Forecast Only | 18,420.000 | 0.000 | 08J | 2017 | 09/05/2019 | 2019 | 695 | 99.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2019-09-05 | 2019-09-05 | # | 2019-09-05 | 2019-09-05 | # | 2019-09-05 | 2019-09-05 | COMP | 2019-08-27 | 2019-08-27 | COMP | 2019-08-27 | 2019-08-27 | COMP | 2019-08-27 | 2019-08-27 | 0 | -9 | 0
31355774 | *CANC*DONOT USE*RECOND GREEN VALLEY*CANC | 10/10/2017 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/29/2019 | ED.08319.2103 | GREEN VALLEY 2103 | 044 | SANTA CRUZ COU | 5535457 | DO 08 - Monthly Forecast Only | 12,225.000 | 0.000 | 08J | 2017 | 05/03/2020 | 2020 | 936 | 133.7143 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | COMP | 2020-04-10 | 2020-04-10 | COMP | 2020-04-10 | 2020-04-10 | COMP | 2020-04-10 | 2020-04-10 | 0 | -23 | 0
31355775 | RECOND GREEN VALLEY 2103 REF# S032CC202 | 10/10/2017 | 113663968 | 10/04/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/29/2019 | ED.08319.2103 | GREEN VALLEY 2103 | 044 | SANTA CRUZ COU | 5535457 | DO 08 - Monthly Forecast Only | 25,360.000 | 0.000 | 08J | 2017 | # | OPEN | 1151 | 164.4286 | UNSE | 1 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 7028.16
31355776 | *CANC*DONOT USE*RECOND GREEN VALLEY*CANC | 10/10/2017 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/29/2019 | ED.08319.2101 | GREEN VALLEY 2101 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 2,580.000 | 0.000 | 08J | 2017 | 05/03/2020 | 2020 | 936 | 133.7143 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | COMP | 2020-04-10 | 2020-04-10 | COMP | 2020-04-10 | 2020-04-10 | COMP | 2020-04-10 | 2020-04-10 | 0 | -23 | 0
31355777 | *CANC*DONOT USE*RECOND WATSONVILLE *CANC | 10/10/2017 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/29/2019 | ED.08333.2101 | WATSONVILLE 2101 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 26,540.000 | 0.000 | 08J | 2017 | 05/03/2020 | 2020 | 936 | 133.7143 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | COMP | 2020-04-10 | 2020-04-10 | COMP | 2020-04-10 | 2020-04-10 | COMP | 2020-04-10 | 2020-04-10 | 0 | -23 | 0
31356031 | *CANC*DONOT USE*ATWATER 1103 RECOND*CANC | 10/10/2017 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2019 | ED.72-06125B0000.STRU.POLE | MERCED MAP 06125B POLES | 024 | MERCED COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 2,300.000 | 0.000 | 08J | 2017 | 05/03/2020 | 2020 | 936 | 133.7143 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | ATWATER 1103 RECONDUCTORING | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | COMP | 2020-04-09 | 2020-04-09 | COMP | 2020-04-09 | 2020-04-09 | COMP | 2020-04-09 | 2020-04-09 | 0 | -24 | 0
31358176 | *CANC*DO NOT USE*EL NIDO 1101 - TAR*CANC | 10/11/2017 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/30/2019 | ED.25245.1101 | EL NIDO 1101 | 020 | MADERA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2017 | 05/03/2020 | 2020 | 935 | 133.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | COMP | 2020-04-09 | 2020-04-09 | COMP | 2020-04-09 | 2020-04-09 | COMP | 2020-04-09 | 2020-04-09 | 0 | -24 | 0
31360749 | *CANC* RECONDUCTOR RIPON 1701 - SP *CANC | 10/12/2017 | 5161585 | 10/12/2017 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/27/2019 | ED.16380.1701 | RIPON 1701 | 039 | SAN JOAQUIN CO | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2017 | 05/03/2020 | 2020 | 934 | 133.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | RECONDUCTOR RIPON 1701 - SPLICE COUNT | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | COMP | 2020-04-08 | 2020-04-08 | COMP | 2020-04-08 | 2020-04-08 | COMP | 2020-04-08 | 2020-04-08 | 0 | 43929 | 0
31360766 | FROGTOWN 1701 RECOND 1153FTTO 1/0ACSR TW | 10/12/2017 | 113720778 | 10/11/2017 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/28/2019 | ED.16345.1701 | FROGTOWN 1701 | 005 | CALAVERAS COUN | 5535211 | CWSP SPO - SH 08 | 1,153.000 | 1,153.000 | 08W | 2017 | 02/29/2020 | 2020 | 870 | 124.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2018-08-13 | 2019-05-20 | COMP | 2019-06-18 | 2019-07-25 | COMP | 2019-08-21 | 2019-08-21 | COMP | 2019-08-21 | 2019-08-22 | COMP | 2019-08-22 | 2019-08-24 | COMP | 2019-08-24 | 2019-08-28 | 373 | 7 | 400124.86
31360838 | *CANC*DONOT USE*RPL OH WIRE ON DOLA*CANC | 10/13/2017 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/28/2019 | ED.05-E071000000.STRU.POLE | SALINAS E0710 POLES | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 9,854.000 | 0.000 | 08J | 2017 | 05/03/2020 | 2020 | 933 | 133.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | R2 RPL OH WIRE ON DOLAN RD1101 S040CC207 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | COMP | 2020-04-09 | 2020-04-09 | COMP | 2020-04-09 | 2020-04-09 | COMP | 2020-04-09 | 2020-04-09 | 0 | -24 | 0
31360980 | *CANC*DONOT USE*RPL OH WIRE ON DOLA*CANC | 10/13/2017 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/28/2019 | ED.05-D082300000.STRU.POLE | SALINAS D0823 POLES | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 992.000 | 0.000 | 08J | 2017 | 05/03/2020 | 2020 | 933 | 133.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | COMP | 2020-04-09 | 2020-04-09 | COMP | 2020-04-09 | 2020-04-09 | COMP | 2020-04-09 | 2020-04-09 | 0 | -24 | 0
31360981 | R2 OH WIRE ON BONRNDA 1102 17-0083078 | 10/13/2017 | 113725886 | 10/12/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/28/2019 | JY | JUNK YARD FL TO HOLD DELETED DATA | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2017 | # | OPEN | 1148 | 164 | UNSE | 1 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 805.27
31361056 | *CANC* KINGSBURG 1111 RECOND 12000 *CANC | 10/16/2017 | 5164356 | 10/16/2017 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/28/2019 | ED.25224.1111 | KINGSBURG 1111 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2017 | 06/05/2019 | 2019 | 597 | 85.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | COMP | 2019-05-20 | 2019-05-20 | COMP | 2019-05-20 | 2019-05-20 | COMP | 2019-05-20 | 2019-05-20 | 0 | 43605 | 0
31361057 | *CANC* KINGSBURG 1111 RECOND 4010 O*CANC | 10/16/2017 | 5164317 | 10/16/2017 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 05/31/2019 | ED.25224.1111 | KINGSBURG 1111 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2017 | 06/05/2019 | 2019 | 597 | 85.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | COMP | 2019-05-20 | 2019-05-20 | COMP | 2019-05-20 | 2019-05-20 | COMP | 2019-05-20 | 2019-05-20 | 0 | 43605 | 0
31361320 | *CANC*DONOT USE*EL CAPITAN 1104 REC*CANC | 10/17/2017 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2019 | ED.72-0713151000.STRU.POLE | MERCED MAP 0713151 POLES | 024 | MERCED COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 4,700.000 | 0.000 | 08J | 2017 | 05/03/2020 | 2020 | 929 | 132.7143 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | COMP | 2020-04-09 | 2020-04-09 | COMP | 2020-04-09 | 2020-04-09 | COMP | 2020-04-09 | 2020-04-09 | 0 | -24 | 0
31361321 | *CANC*DONOT USE* RECONDUCTOR - FUSE*CANC | 10/17/2017 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2018 | ED.18267.1106 | SANTA MARIA 1106 | 015 | KERN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 6,850.000 | 0.000 | 08J | 2017 | 05/03/2020 | 2020 | 929 | 132.7143 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | COMP | 2020-04-07 | 2020-04-07 | COMP | 2020-04-07 | 2020-04-07 | COMP | 2020-04-07 | 2020-04-07 | 0 | -26 | 0
31361322 | *CANC*DONOT USE* RECONDUCTOR - FUSE*CANC | 10/17/2017 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.18267.1109 | SANTA MARIA 1109 | 015 | KERN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 2,875.000 | 0.000 | 08J | 2017 | 05/03/2020 | 2020 | 929 | 132.7143 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | COMP | 2020-04-09 | 2020-04-09 | COMP | 2020-04-09 | 2020-04-09 | COMP | 2020-04-09 | 2020-04-09 | 0 | -24 | 0
31361488 | *CANC* RECOND 15 298 FT 6CU 4CU & *CANC | 10/18/2017 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/17/2019 | ED.42-FF30000000.STRU.POLE | SILVERADO FF30 POLES | 028 | NAPA COUNTY | 5535211 | CWSP SPO - SH 08 | 13,780.000 | 0.000 | 08W | 2017 | 10/03/2019 | 2019 | 715 | 102.1429 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | NOTN | 2019-09-23 | 2019-09-23 | # | 2019-10-03 | 2019-10-03 | # | 2019-10-03 | 2019-10-03 | # | 2019-10-03 | 2019-10-03 | # | 2019-10-03 | 2019-10-03 | # | 2019-10-03 | 2019-10-03 | 10 | 0 | 0
31361489 | OLEMA 1101 HIGH SPLICE COUNT 3 | 10/18/2017 | 113745486 | 10/18/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/18/2019 | ED.40-QQ24030000.STRU.POLE | NORTH BAY MAP QQ2403 POLES | 021 | MARIN COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2017 | # | OPEN | 1143 | 163.2857 | UNSE | 1 | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 870.75
31361625 | *CANC*DONOT USE* VALLEJO 414 HIGH S*CANC | 10/19/2017 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/19/2019 | ED.42-QQ39080000.STRU.POLE | SILVERADO QQ3908 POLES | 048 | SOLANO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2017 | 05/03/2020 | 2020 | 927 | 132.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | COMP | 2020-04-10 | 2020-04-10 | COMP | 2020-04-10 | 2020-04-10 | COMP | 2020-04-10 | 2020-04-10 | 0 | -23 | 0
31361965 | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 | 10/23/2017 | 113751296 | 10/20/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/27/2019 | ED.04307.1101.RECL | RECLOSERS | 049 | SONOMA COUNTY | 5535211 | CWSP SPO - SH 08 | 2,367.000 | 0.000 | 08W | 2017 | # | OPEN | 1138 | 162.5714 | CONS | 7 | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 172935.69
31361967 | *CANC*DONOT USE* RECON 815 FT TAP O*CANC | 10/23/2017 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/27/2019 | ED.04341.1101.RECL | RECLOSERS | 023 | MENDOCINO COUN | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2017 | 05/03/2020 | 2020 | 923 | 131.8571 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | COMP | 2020-04-10 | 2020-04-10 | COMP | 2020-04-10 | 2020-04-10 | COMP | 2020-04-10 | 2020-04-10 | 0 | -23 | 0
31361969 | RECON 9,400 FT - POINT ARENA 1101 | 10/23/2017 | 113752520 | 10/20/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/27/2019 | ED.04338.1101.RECL | RECLOSERS | 023 | MENDOCINO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2017 | # | OPEN | 1138 | 162.5714 | UNSE | 1 | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 1200.31
31362297 | *CANC*DONOT USE*ELK HILLS 1104 OH S*CANC | 10/25/2017 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/30/2019 | ED.25244.1104 | ELK HILLS 1104 | 015 | KERN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2017 | 05/03/2020 | 2020 | 921 | 131.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | COMP | 2020-04-10 | 2020-04-10 | COMP | 2020-04-10 | 2020-04-10 | COMP | 2020-04-10 | 2020-04-10 | 0 | -23 | 0
31362298 | *CANC*DONOT USE*ELK HILLS 1104 OH S*CANC | 10/25/2017 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/30/2019 | ED.25244.1104 | ELK HILLS 1104 | 020 | MADERA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2017 | 05/03/2020 | 2020 | 921 | 131.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | COMP | 2020-04-10 | 2020-04-10 | COMP | 2020-04-10 | 2020-04-10 | COMP | 2020-04-10 | 2020-04-10 | 0 | -23 | 0
31362346 | *CANC*GANSO 1104 RECOND 2900FT TO 2AR | 10/25/2017 | # | #N/A | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/28/2019 | ED.25454.1104 | GANSO 1104 | 015 | KERN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2017 | # | OPEN | 1136 | 162.2857 | UNSE | 1 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
31362454 | *CANC*GUERNSEY 1101 LR 92702 RECOND 2060 | 10/26/2017 | 113763631 | 10/26/2017 | # | Not assigned | 25 | Canceled | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/31/2021 | ED.25266.1101 | GUERNSEY 1101 | 016 | KINGS COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2017 | # | OPEN | 1135 | 162.1429 | CNCL | Other | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | COMP | 2020-11-19 | 2020-11-19 | COMP | 2020-11-19 | 2020-11-19 | COMP | 2020-11-19 | 2020-11-19 | 0 | 44154 | -811.32
31363087 | REPL 3-6CU ON NELSON SHIPPEE RD - ESQUON | 10/30/2017 | 113771716 | 10/29/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.10217.1101.SWIT | SWITCHES | 004 | BUTTE COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2017 | # | OPEN | 1131 | 161.5714 | UNSE | 1 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | REPL 3-6CU ON NELSON SHIPPEE RD - ESQUON | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 5907.76
31364170 | *CANC*DONOT USE* RECONDUCTOR 3,750'*CANC | 11/09/2017 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/15/2019 | ED.18281.1101 | SISQUOC 1101 | 040 | SAN LUIS OBISP | 5535457 | DO 08 - Monthly Forecast Only | 2,600.000 | 0.000 | 08J | 2017 | 05/03/2020 | 2020 | 906 | 129.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | COMP | 2020-04-10 | 2020-04-10 | COMP | 2020-04-10 | 2020-04-10 | COMP | 2020-04-10 | 2020-04-10 | 0 | -23 | 0
31364228 | RECOND 4490FT OF 4ACSR WITH 2CU TW | 11/07/2017 | 113782453 | 11/02/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/30/2018 | ED.18295.1101 | FOOTHILL 1101 | 040 | SAN LUIS OBISP | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2017 | # | OPEN | 1123 | 160.4286 | UNSE | 1 | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 645.06
31364252 | *CANC*DONOT USE*EIGHT MILE2101-RECO*CANC | 11/07/2017 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/29/2019 | ED.93-Q091200000.STRU.POLE | STOCKTON Q0912 POLES | 039 | SAN JOAQUIN CO | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2017 | 05/03/2020 | 2020 | 908 | 129.7143 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | COMP | 2020-04-10 | 2020-04-10 | COMP | 2020-04-10 | 2020-04-10 | COMP | 2020-04-10 | 2020-04-10 | 0 | -23 | 0
31364254 | KINGSBURG 1114 - RECONDUCTOR | 11/07/2017 | 113779647 | 11/01/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/29/2019 | ED.70-16225D0000.STRU.POLE | FRESNO 16225D POLES | 054 | TULARE COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2017 | # | OPEN | 1123 | 160.4286 | UNSE | 1 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 2241.75
31364255 | MAGUNDEN 1108 - RECONDUCTOR | 11/07/2017 | 113779668 | 11/01/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/29/2019 | ED.66-2929311000.STRU.POLE | KERN 2929311 POLES | 015 | KERN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2017 | # | OPEN | 1123 | 160.4286 | UNSE | 1 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 964.83
31364321 | STONE CORRAL 1110 - RECONDUCTOR | 11/07/2017 | 113779723 | 11/01/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/29/2019 | ED.70-1726400000.STRU.POLE | FRESNO 17264 POLES | 054 | TULARE COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2017 | # | OPEN | 1123 | 160.4286 | UNSE | 1 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 1603.26
31364323 | *CANC*DONOT USE*STOREY 1109-ECONDUC*CANC | 11/07/2017 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/29/2019 | ED.72-11182D0000.STRU.POLE | YOSEMITE MAP 11182D POLES | 020 | MADERA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2017 | 05/03/2020 | 2020 | 908 | 129.7143 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | COMP | 2020-04-08 | 2020-04-08 | COMP | 2020-04-08 | 2020-04-08 | COMP | 2020-04-08 | 2020-04-08 | 0 | -25 | 0
31364518 | 2109 CLAYTON 2217 HIGH SPLICE COUNT | 11/08/2017 | 113781102 | 11/01/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2019 | ED.01202.2217 | CLAYTON 2217 | 007 | CONTRA COSTA C | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2017 | # | OPEN | 1122 | 160.2857 | UNSE | 1 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 173.34
31364519 | 2019 BRENTWOOD 2108 HIGH SPLICE COUNT | 11/08/2017 | 113781183 | 11/01/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/30/2019 | ED.01459.2108 | BRENTWOOD 2108 | 007 | CONTRA COSTA C | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2017 | # | OPEN | 1122 | 160.2857 | UNSE | 1 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
31364941 | *CANC*DONOT USE*2019 08J PN MILLBRA*CANC | 11/10/2017 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/27/2019 | ED.02269.1102.SWIT | SWITCHES | 041 | SAN MATEO COUN | 5505513 | PN-OH ANNEALED/DETER CNDCTR: PM MGD | 0.000 | 0.000 | 08J | 2017 | 05/03/2020 | 2020 | 905 | 129.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | COMP | 2020-04-08 | 2020-04-08 | COMP | 2020-04-08 | 2020-04-08 | COMP | 2020-04-08 | 2020-04-08 | 0 | -25 | 0
31365090 | *CANC* KINGSBURG 1111 RECOND 21,880 FEE | 11/13/2017 | 113796153 | 11/08/2017 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/04/2019 | ED.25224.1111 | KINGSBURG 1111 | 054 | TULARE COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2017 | 04/14/2018 | 2018 | 152 | 21.7143 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2018-04-14 | 2018-04-14 | # | 2018-04-14 | 2018-04-14 | # | 2018-04-14 | 2018-04-14 | # | 2018-04-14 | 2018-04-14 | # | 2018-04-14 | 2018-04-14 | # | 2018-04-14 | 2018-04-14 | 0 | 0 | 0
31365702 | *CANC* *DO NOT USE* STONE CORRAL 11*CANC | 11/16/2017 | 113820041 | 11/16/2017 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 07/05/2019 | ED.25292.1110 | STONE CORRAL 1110 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2017 | 09/03/2020 | 2020 | 1022 | 146 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2020-09-03 | 2020-09-03 | # | 2020-09-03 | 2020-09-03 | # | 2020-09-03 | 2020-09-03 | COMP | 2020-08-26 | 2020-08-26 | COMP | 2020-08-26 | 2020-08-26 | COMP | 2020-08-26 | 2020-08-26 | 0 | -8 | 0
31365703 | *CANC*DONOT USE*STONE CORRAL 1110 R*CANC | 11/16/2017 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/28/2019 | ED.25292.1110 | STONE CORRAL 1110 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2017 | 05/03/2020 | 2020 | 899 | 128.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | COMP | 2020-04-08 | 2020-04-08 | COMP | 2020-04-08 | 2020-04-08 | COMP | 2020-04-08 | 2020-04-08 | 0 | -25 | 0
31366025 | *CANC*DONOT USE* NEWMAN 1106 REPLAC*CANC | 11/17/2017 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2021 | ED.16274.1106 | NEWMAN 1106 | 050 | STANISLAUS COU | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2017 | 05/03/2020 | 2020 | 898 | 128.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | COMP | 2020-04-09 | 2020-04-09 | COMP | 2020-04-09 | 2020-04-09 | COMP | 2020-04-09 | 2020-04-09 | 0 | -24 | 0
31367226 | TASSAJARA 2108 OH RECONDUCTOR | 11/27/2017 | 114031980 | 11/27/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2019 | ED.01466.2108 | TASSAJARA 2108 | 007 | CONTRA COSTA C | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2017 | # | OPEN | 1103 | 157.5714 | UNSE | 1 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 173.34
31367398 | *CANC*DONOT USE* WESTPARK 1104 RECO*CANC | 11/29/2017 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/28/2019 | ED.25370.1104 | WESTPARK 1104 | 015 | KERN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2017 | 05/03/2020 | 2020 | 886 | 126.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | COMP | 2020-04-07 | 2020-04-07 | COMP | 2020-04-07 | 2020-04-07 | COMP | 2020-04-07 | 2020-04-07 | 0 | -26 | 0
31367399 | *CANC*DONOT USE*SEMITROPIC 1110 REC*CANC | 11/29/2017 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.25290.1110 | SEMITROPIC 1110 | 015 | KERN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2017 | 05/03/2020 | 2020 | 886 | 126.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | COMP | 2020-04-07 | 2020-04-07 | COMP | 2020-04-07 | 2020-04-07 | COMP | 2020-04-07 | 2020-04-07 | 0 | -26 | 0
31368334 | KINGSBURG 1111 - RECONDUCTOR 7,800 FT | 12/05/2017 | 114045191 | 12/01/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/30/2019 | ED.70-16225C0000.STRU.POLE | FRESNO 16225C POLES | 054 | TULARE COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2017 | # | OPEN | 1095 | 156.4286 | UNSE | 1 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 1068.46
31369863 | SILVERADO 2102 RECONDUCTOR JOB | 12/14/2017 | 114106530 | 12/14/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2019 | JY | JUNK YARD FL TO HOLD DELETED DATA | 028 | NAPA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2017 | # | OPEN | 1086 | 155.1429 | UNSE | 1 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
31372445 | RE-COND 7988 FT OF 6CU & 4AC W 2CU | 01/05/2018 | 114156606 | 01/05/2018 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 01/05/2019 | ED.18263.1103 | SAN LUIS OBISPO 1103 | 040 | SAN LUIS OBISP | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2018 | # | OPEN | 1064 | 152 | UNSE | 1 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 3715.4
31374248 | *CANC*DONOT USE*RE-COND 6260 CIRCU*CANC | 01/16/2018 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 01/05/2019 | ED.18206.1104 | FAIRWAY 1104 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2018 | 05/03/2020 | 2020 | 838 | 119.7143 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | COMP | 2020-04-10 | 2020-04-10 | COMP | 2020-04-10 | 2020-04-10 | COMP | 2020-04-10 | 2020-04-10 | 0 | -23 | 0
31374249 | 14184 FT OF 4ACSR&3363 FT OF 6CUW 2CU TW | 01/16/2018 | # | #N/A | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 01/16/2020 | ED.18310.1103 | CABRILLO 1103 | 042 | SANTA BARBARA | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2018 | # | OPEN | 1053 | 150.4286 | UNSE | 1 | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 1088.43
31375924 | TUPMAN 1104 RECONDUCTOR 7,000 FEET | 01/26/2018 | 114236443 | 01/19/2018 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 05/31/2022 | ED.25456.1104 | TUPMAN 1104 | 015 | KERN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2018 | # | OPEN | 1043 | 149 | UNSE | 1 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 6661.45
31376255 | *CANC* LODI 1102 RECONDUCTORING - *CANC | 01/29/2018 | 114253974 | 01/29/2018 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.93-Q111400000.STRU.POLE | STOCKTON Q1114 POLES | 039 | SAN JOAQUIN CO | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2018 | 06/03/2020 | 2020 | 856 | 122.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2020-06-03 | 2020-06-03 | # | 2020-06-03 | 2020-06-03 | # | 2020-06-03 | 2020-06-03 | # | 2020-06-03 | 2020-06-03 | # | 2020-06-03 | 2020-06-03 | # | 2020-06-03 | 2020-06-03 | 0 | 0 | 0
31377173 | *CANC*DONOT USE*BANTA 1101 RECONDUC*CANC | 02/02/2018 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.16247.1101 | BANTA 1101 | 039 | SAN JOAQUIN CO | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2018 | 05/03/2020 | 2020 | 821 | 117.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | COMP | 2020-04-10 | 2020-04-10 | COMP | 2020-04-10 | 2020-04-10 | COMP | 2020-04-10 | 2020-04-10 | 0 | -23 | 0
31377407 | HIGGINS 1107 RECONDUCTOR 2800', AUBURN | 02/06/2018 | 114278944 | 02/06/2018 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.15269.1107.SWIT | SWITCHES | 029 | NEVADA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 4,045.000 | 0.000 | 08J | 2018 | # | OPEN | 1032 | 147.4286 | UNSC | 6 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 484098.54
31379155 | *CANC*DONOT USE*6149CIRCUIT FT(52 S*CANC | 02/14/2018 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/16/2018 | ED.18280.1101 | BAYWOOD 1101 | 040 | SAN LUIS OBISP | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2018 | 05/03/2020 | 2020 | 809 | 115.5714 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | COMP | 2020-04-10 | 2020-04-10 | COMP | 2020-04-10 | 2020-04-10 | COMP | 2020-04-10 | 2020-04-10 | 0 | -23 | 0
31380961 | RECON1285 FT OF 3-4ACSR WITH 3-2CU | 02/23/2018 | 114334072 | 02/23/2018 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 02/23/2020 | ED.18297.1101 | PURISIMA 1101 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2018 | # | OPEN | 1015 | 145 | UNSE | 1 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 878.46
31382371 | *CANC*DONOT USE* RECOMMEND 18-00156*CANC | 03/03/2018 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 08/02/2020 | ED.18281.1104 | SISQUOC 1104 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2018 | 05/03/2020 | 2020 | 792 | 113.1429 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | COMP | 2020-04-10 | 2020-04-10 | COMP | 2020-04-10 | 2020-04-10 | COMP | 2020-04-10 | 2020-04-10 | 0 | -23 | 0
31383064 | 2020 FORT BRAGG 1103 RECONDUC OUTLET | 03/07/2018 | 114367862 | 03/07/2018 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/16/2020 | ED.04276.1103 | FORT BRAGG A 1103 | 023 | MENDOCINO COUN | 5535457 | DO 08 - Monthly Forecast Only | 3,100.000 | 0.000 | 08J | 2018 | # | OPEN | 1003 | 143.2857 | ESTS | 2 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 20806.15
31387895 | *CANC* REPL 17 500' OF 4AR & 4CU I *CANC | 04/09/2018 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2019 | ED.42-GG32250000.STRU.POLE | SILVERADO GG3225 POLES | 028 | NAPA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2018 | 09/05/2019 | 2019 | 514 | 73.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | 31387895_SILVERADO 2105 WIRE DOWN | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 2019-09-05 | 2019-09-05 | # | 2019-09-05 | 2019-09-05 | # | 2019-09-05 | 2019-09-05 | # | 2019-09-05 | 2019-09-05 | # | 2019-09-05 | 2019-09-05 | # | 2019-09-05 | 2019-09-05 | 0 | 0 | 0
31389447 | PUEBLO 1105 RECONDUCTOR W TREE WIRE | 04/20/2018 | 114519107 | 04/19/2018 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/19/2020 | ED.42-JJ38000000.STRU.POLE | SILVERADO MAP JJ38 POLES | 028 | NAPA COUNTY | 5535211 | CWSP SPO - SH 08 | 6,740.000 | 6,740.000 | 08W | 2018 | # | OPEN | 959 | 137 | DOCC | 8 | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | 31389447_PUEBLO 1105 RECONDUCTOR | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2019-03-29 | 2019-03-29 | INPR | 2019-03-31 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | -43553 | 0 | 3899074.07
31389448 | *CANC* SILVERADO 2104 RECONDUCTOR*CANC | 04/20/2018 | 5361841 | 04/20/2018 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/20/2020 | ED.42-GG33050000.STRU.POLE | SILVERADO MAP GG3305 POLES | 028 | NAPA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2018 | 03/02/2019 | 2019 | 316 | 45.1429 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | COMP | 2018-12-28 | 2018-12-28 | COMP | 2018-12-28 | 2018-12-28 | COMP | 2018-12-28 | 2018-12-28 | 0 | 43462 | 0
31391219 | *CANC*DO NOT USE* RE-COND 2300FT 4A*CANC | 05/08/2018 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/26/2020 | ED.18282.1102 | MESA 1102 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2018 | 05/03/2020 | 2020 | 726 | 103.7143 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | COMP | 2020-04-10 | 2020-04-10 | COMP | 2020-04-10 | 2020-04-10 | COMP | 2020-04-10 | 2020-04-10 | 0 | -23 | 0
31392316 | *CANC* 2018MONTERIO1112/MOLINO1102WILDFI | 05/16/2018 | 5396001 | 05/16/2018 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2018 | ED.04257.1102.SWIT | SWITCHES | 049 | SONOMA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2018 | 06/09/2018 | 2018 | 24 | 3.4286 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
31393978 | *CANC* RE-COND 5245 FT 4ACSR&3876 FT | 05/29/2018 | # | #N/A | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/22/2020 | ED.18281.1102 | SISQUOC 1102 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2018 | # | OPEN | 920 | 131.4286 | UNSE | 1 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
31397184 | PETALUMA C 1108 WIREDOWN LR636 PHASE1 | 06/21/2018 | 114717374 | 06/21/2018 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/30/2020 | ED.04263.1108.SWIT | SWITCHES | 049 | SONOMA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2018 | # | OPEN | 897 | 128.1429 | UNSE | 1 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
31429487 | OTTER-1101 S030CC121 – TRANS POLES | 03/18/2019 | # | #N/A | 35060584 | RPL OH WIRE ON OTTER-1101 S030CC121 | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | # | ED.07-N031000000.STRU.POLE | MONTEREY N0310 POLES | 027 | MONTEREY COUNT | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2019 | # | OPEN | 627 | 89.5714 | PEND | 5 | E070 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 99248.53
31434881 | 0P 3100 SKYWAY RD PARADISE TUSCAN RIDGE | 04/19/2019 | 116825055 | 03/25/2019 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 08/30/2019 | ED | Electric Distribution System | # | Not assigned | 5791419 | CWSP - BUCOCAMP-SKYWAY PARADISE TIE PH1 | 4,238.000 | 0.000 | 08W | 2019 | # | OPEN | 595 | 85 | PEND | 5 | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 10626593.44
31462406 | FOOTHILL 1101 LS CO9973 RECONDUCTOR, SLO | 08/13/2019 | # | #N/A | 35066622 | FOOTHILL 1101 LS CO9973 RECONDUCTOR, SLO | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | # | ED.18295.1101.TXFR.TROH | OVERHEAD TRANSFORMERS | 040 | SAN LUIS OBISP | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2019 | # | OPEN | 479 | 68.4286 | ADER | 3 | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 14485.73
31463070 | GANSO 1104 RECOND 2900FT TO 2AR | 08/19/2019 | # | #N/A | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/28/2019 | ED.25454.1104 | GANSO 1104 | 015 | KERN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2019 | # | OPEN | 473 | 67.5714 | UNSE | 1 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
31478906 | RAISE T-LINE H-FRAME DONNELS-MI WUK 18/2 | 11/21/2019 | # | #N/A | 35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | # | ED.16366.1701 | MIWUK 1701 | 055 | TUOLUMNE COUNT | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2019 | # | OPEN | 379 | 54.1429 | UNSC | 6 | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 3295.3
31478907 | WD-EIGHT MILE2101-CO738931-ILS 180066835 | 11/21/2019 | # | #N/A | 35052976 | WD-EIGHT MILE2101-CO738931-ILS 180066835 | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | # | ED.16391.2101 | EIGHT MILE 2101 | 039 | SAN JOAQUIN CO | 5535457 | DO 08 - Monthly Forecast Only | 3,132.000 | 0.000 | 08J | 2019 | # | OPEN | 379 | 54.1429 | PEND | 5 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 22637.43
31486236 | *CANC* GRAND ISLAND 2224 RECONDUCT*CANC | 01/14/2020 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/01/2018 | ED.06246.2224.RECL | RECLOSERS | 048 | SOLANO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2020 | 02/06/2020 | 2020 | 23 | 3.2857 | CLSD | 12 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2020-02-06 | 2020-02-06 | # | 2020-02-06 | 2020-02-06 | # | 2020-02-06 | 2020-02-06 | COMP | 2020-01-22 | 2020-01-22 | COMP | 2020-01-22 | 2020-01-22 | COMP | 2020-01-22 | 2020-01-22 | 0 | -15 | 0
31513424 | BIOLA 1104 RECONDUCTOR 2,995 FT OF 6CU | 09/09/2020 | # | #N/A | 35089227 | BIOLA 1104 RECONDUCTOR 2,995 FT OF 6CU | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | # | ED.25221.1104 | BIOLA 1104 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 1,430.000 | 0.000 | 08J | 2020 | # | OPEN | 86 | 12.2857 | PEND | 5 | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 3098.47
35000302 | RECOND 4149' 6CU &4AR W/2CU SM 1110,GUAD | 06/07/2017 | 112931300 | 06/06/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2021 | ED.18282.1102 | MESA 1102 | 040 | SAN LUIS OBISP | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2017 | # | OPEN | 1276 | 182.2857 | ESTS | 2 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 4903.12
35000308 | 2022 BOWLES 1101 RECOND 5350FT TO 4/0AL | 06/08/2017 | 112938174 | 06/08/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/28/2019 | ED.25353.1101 | BOWLES 1101 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2017 | # | OPEN | 1275 | 182.1429 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 956.97
35001100 | R2 RPL OH WIRE ON SPENCE 1121 17-0051204 | 07/06/2017 | 113011449 | 06/30/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/30/2019 | ED.18220.1121 | SPENCE 1121 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 21,444.000 | 0.000 | 08J | 2017 | # | OPEN | 1247 | 178.1429 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 2691.79
35001101 | R2RPL OH WIRE ON DOLN RD 1101 17-0050152 | 07/06/2017 | 113011520 | 06/30/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/30/2019 | ED.18238.1101 | DOLAN ROAD 1101 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 3,114.000 | 0.000 | 08J | 2017 | # | OPEN | 1247 | 178.1429 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | R2RPL OH WIRE ON DOLN RD 1101 17-0050152 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 17779.97
35001302 | R2 RPL OH WIRE ON SPENCE 1121 17-0052344 | 07/20/2017 | 113063294 | 07/19/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/30/2019 | ED.05-H112200000.STRU.POLE | SALINAS H1122 POLES | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 2,325.000 | 0.000 | 08J | 2017 | # | OPEN | 1233 | 176.1429 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | R2 RPL OH WIRE ON SPENCE 1121 17-0052344 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 20739.21
35001303 | R2 RPL OH WIRE ON SALINS 1103 17-0052542 | 07/20/2017 | 113063299 | 07/19/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/30/2019 | ED.05-G090800000.STRU.POLE | SALINAS G0908 POLES | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 1,290.000 | 0.000 | 08J | 2017 | # | OPEN | 1233 | 176.1429 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 2090.98
35001436 | R2 RPL OH WIRE ON SPENCE 1122 17-0048978 | 07/27/2017 | 113090765 | 07/27/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/30/2019 | ED.05-I122100000.STRU.POLE | SALINAS I1221 POLES | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 1,515.000 | 0.000 | 08J | 2017 | # | OPEN | 1226 | 175.1429 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 1141.58
35001640 | *CANC* RECONDUCTOR WRIGHT 1110 - W *CANC | 08/11/2017 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/12/2021 | ED.25464.1110 | WRIGHT 1110 | 024 | MERCED COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2017 | 05/03/2020 | 2020 | 996 | 142.2857 | CLSD | 12 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | 0 | 0 | 0
35001641 | *CANC* RECONDUCTOR RIVERBANK 1715- *CANC | 08/11/2017 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/27/2019 | ED.16319.1715 | RIVERBANK 1715 | 050 | STANISLAUS COU | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2017 | 04/04/2020 | 2020 | 967 | 138.1429 | CLSD | 12 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2020-04-04 | 2020-04-04 | # | 2020-04-04 | 2020-04-04 | # | 2020-04-04 | 2020-04-04 | # | 2020-04-04 | 2020-04-04 | # | 2020-04-04 | 2020-04-04 | # | 2020-04-04 | 2020-04-04 | 0 | 0 | 0
35001642 | RECONDUCTOR MADERA 1119 - WIRE DOWN | 08/11/2017 | 113143589 | 08/10/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/29/2019 | ED.25276.1119 | MADERA 1119 | 020 | MADERA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2017 | # | OPEN | 1211 | 173 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35001661 | R2 2019 ASHLAN AVE 1104 RECONDUCTOR | 08/14/2017 | 113154596 | 08/14/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/31/2021 | ED.25205.1104 | ASHLAN AVE 1104 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 6,100.000 | 0.000 | 08J | 2017 | # | OPEN | 1208 | 172.5714 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 35001661_Ashlan Ave 1104 Reconductor | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 17053.89
35001680 | R2 CV - 2021 BIOLA 1103 CONDUCTOR REPLAC | 08/15/2017 | 113155616 | 08/14/2017 | # | Not assigned | 30 | Technically Completed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2022 | ED.25221.1103 | BIOLA 1103 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2017 | # | OPEN | 1207 | 172.4286 | FICL | 10 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 35001680_Boila 1103 Target OH Cond Repl | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 6122.59
35001700 | *CANC* ALPAUGH 1103 RECOND 1600FT*CANC | 08/16/2017 | 113161388 | 08/15/2017 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/27/2019 | ED.25400.1103 | ALPAUGH 1103 | 054 | TULARE COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2017 | 03/02/2019 | 2019 | 563 | 80.4286 | CLSD | 12 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2019-03-03 | 2019-03-03 | # | 2019-03-03 | 2019-03-03 | # | 2019-03-03 | 2019-03-03 | # | 2019-03-03 | 2019-03-03 | # | 2019-03-03 | 2019-03-03 | # | 2019-03-03 | 2019-03-03 | 0 | 0 | 0
35001847 | *CANC* RECONDUCTOR CHOWCHILLA 110*CANC | 08/24/2017 | 113187407 | 08/23/2017 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/29/2019 | ED.25410.1104 | CHOWCHILLA 1104 | 020 | MADERA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2017 | 05/03/2019 | 2019 | 617 | 88.1429 | CLSD | 12 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2019-05-03 | 2019-05-03 | # | 2019-05-03 | 2019-05-03 | # | 2019-05-03 | 2019-05-03 | COMP | 2018-12-19 | 2018-12-19 | COMP | 2018-12-19 | 2018-12-19 | COMP | 2018-12-19 | 2018-12-19 | 0 | -135 | 0
35001849 | *CANC*DO NOT USE* R2R OH WIRE ON DO*CANC | 08/24/2017 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/28/2019 | ED.18238.1104.SWIT | SWITCHES | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 8,997.000 | 0.000 | 08J | 2017 | 05/03/2020 | 2020 | 983 | 140.4286 | CLSD | 12 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | COMP | 2020-04-09 | 2020-04-09 | COMP | 2020-04-09 | 2020-04-09 | COMP | 2020-04-09 | 2020-04-09 | 0 | -24 | 0
35001860 | *CANCL* RECOND RIPON 1701 - SPLICE COUNT | 08/23/2017 | 5024955 | 08/23/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/27/2019 | ED.16380.1702 | RIPON 1702 | 039 | SAN JOAQUIN CO | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2017 | # | OPEN | 1199 | 171.2857 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 1210.54
35001862 | WATERLOO 1101 RECOND 4000' OH CONDUCTOR | 08/23/2017 | 113183541 | 08/22/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.16315.1101 | WATERLOO 1101 | 039 | SAN JOAQUIN CO | 5535457 | DO 08 - Monthly Forecast Only | 4,760.000 | 0.000 | 08J | 2017 | # | OPEN | 1199 | 171.2857 | PEND | 5 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 21407.88
35008420 | *CANC*2B CANC BIOLA 1104 2019 TARGE*CANC | 08/28/2017 | 113197739 | 08/28/2017 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/14/2018 | ED.25221.1104 | BIOLA 1104 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2017 | 10/03/2019 | 2019 | 766 | 109.4286 | CLSD | 12 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2019-10-03 | 2019-10-03 | # | 2019-10-03 | 2019-10-03 | # | 2019-10-03 | 2019-10-03 | COMP | 2019-09-13 | 2019-09-13 | COMP | 2019-09-13 | 2019-09-13 | COMP | 2019-09-13 | 2019-09-13 | 0 | -20 | 0
35008478 | *CANC*DO NOT USE*ATWATER 1103 RECON*CANC | 08/29/2017 | 5032846 | 08/29/2017 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2019 | ED.72-06125B0000.STRU.POLE | MERCED MAP 06125B POLES | 024 | MERCED COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 2,300.000 | 0.000 | 08J | 2017 | 05/03/2020 | 2020 | 978 | 139.7143 | CLSD | 12 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | ATWATER 1103 RECONDUCTORING | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | COMP | 2020-04-09 | 2020-04-09 | COMP | 2020-04-09 | 2020-04-09 | COMP | 2020-04-09 | 2020-04-09 | 0 | 43930 | 0
35008479 | R2 2019 AUBERRY 1101 RECONDUCTOR | 08/29/2017 | 113199104 | 08/28/2017 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2019 | JY | JUNK YARD FL TO HOLD DELETED DATA | 010 | FRESNO COUNTY | 5535211 | CWSP SPO - SH 08 | 1,619.000 | 1,619.000 | 08W | 2017 | 05/31/2020 | 2020 | 1006 | 143.7143 | CLSD | 12 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | 35008479_Auberry 1101 Reconductor | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2019-06-10 | 2019-06-10 | COMP | 2019-06-17 | 2019-09-07 | COMP | 2019-09-07 | 2019-09-07 | COMP | 2019-09-26 | 2019-11-22 | COMP | 2019-11-22 | 2019-12-04 | COMP | 2019-12-04 | 2019-12-05 | 89 | 89 | 286544.93
35008480 | *CANCEL* EIGHT MILE 2102 RECONDUCTORING | 08/29/2017 | 5032981 | 08/29/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2019 | ED.93-S120000000.STRU.POLE | STOCKTON S12 POLES | 039 | SAN JOAQUIN CO | 5535457 | DO 08 - Monthly Forecast Only | 5,100.000 | 0.000 | 08J | 2017 | # | OPEN | 1193 | 170.4286 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 35008480_EIGHT MILE 2102 RECONDUCTORING | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 241.75
35008694 | BAKERSFLD 1114 TARGETD OH RECOND | 09/01/2017 | 113212759 | 09/01/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/31/2020 | ED.25337.1114 | BAKERSFIELD 1114 | 015 | KERN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2017 | # | OPEN | 1190 | 170 | PEND | 5 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Bakersfield 1114 Targeted Conductor Repl | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 22879.72
35008700 | RECONDUCTOR RIPON 1701-VAN WYK LN | 09/05/2017 | 113213756 | 09/01/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/27/2019 | ED.16380.1701 | RIPON 1701 | 039 | SAN JOAQUIN CO | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2017 | # | OPEN | 1186 | 169.4286 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 1800.33
35008760 | 2019 KINGBURG 1113 RECONDUCTOR | 09/06/2017 | 113219171 | 09/05/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/31/2020 | ED.25224.1113 | KINGSBURG 1113 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 2,516.000 | 0.000 | 08J | 2017 | # | OPEN | 1185 | 169.2857 | CONS | 7 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Kingsburg 1113 Reconductor | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 47308.08
35008761 | *CANC*DO NOT USE* BIOLA 1104 RECOND*CANC | 09/06/2017 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/29/2019 | ED.25221.1104 | BIOLA 1104 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2017 | 05/03/2020 | 2020 | 970 | 138.5714 | CLSD | 12 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Biola 1104 Reconductor | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | COMP | 2020-04-08 | 2020-04-08 | COMP | 2020-04-08 | 2020-04-08 | COMP | 2020-04-08 | 2020-04-08 | 0 | -25 | 0
35008762 | BONITA 1101 CO 6762 RECOND | 09/06/2017 | 113219235 | 09/05/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/29/2019 | ED.25539.1101 | BONITA 1101 | 020 | MADERA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2017 | # | OPEN | 1185 | 169.2857 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 653.04
35008763 | *CANC* BONITA 1101 CO 32802 RECOND *CANC | 09/06/2017 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2021 | ED.25539.1101 | BONITA 1101 | 020 | MADERA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2017 | 05/03/2020 | 2020 | 970 | 138.5714 | CLSD | 12 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | 0 | 0 | 0
35011720 | *CANC* PT MORETTI 1101 RECOND 200 FT | 09/11/2017 | 113225530 | 09/07/2017 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/07/2019 | ED.18263.1101 | SAN LUIS OBISPO 1101 | 044 | SANTA CRUZ COU | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2017 | 10/20/2018 | 2018 | 404 | 57.7143 | CLSD | 12 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2018-10-20 | 2018-10-20 | # | 2018-10-20 | 2018-10-20 | # | 2018-10-20 | 2018-10-20 | # | 2018-10-20 | 2018-10-20 | # | 2018-10-20 | 2018-10-20 | # | 2018-10-20 | 2018-10-20 | 0 | 0 | 0
35011744 | *CANC* BIOLA 1104 6,350FT TAR*CANC | 09/12/2017 | 5058018 | 09/12/2017 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/15/2019 | ED.25221.1104 | BIOLA 1104 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2017 | 09/06/2018 | 2018 | 359 | 51.2857 | CLSD | 12 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2018-10-16 | 2018-10-16 | # | 2018-10-16 | 2018-10-16 | # | 2018-10-16 | 2018-10-16 | COMP | 2018-09-05 | 2018-09-05 | COMP | 2018-09-05 | 2018-09-05 | COMP | 2018-09-05 | 2018-09-05 | 0 | -41 | 0
35011745 | *CANC* MADERA 1119 3,770FT TARGET *CANC | 09/12/2017 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/15/2021 | ED.25221.1104 | BIOLA 1104 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2017 | 05/03/2020 | 2020 | 964 | 137.7143 | CLSD | 12 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | 0 | 0 | 0
35013233 | R2RPL OH WIRE ON GONZALS-1101 17-0063084 | 09/13/2017 | 113244215 | 09/13/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/28/2019 | ED.18213.1101.SWIT | SWITCHES | 027 | MONTEREY COUNT | 5535211 | CWSP SPO - SH 08 | 1,967.000 | 0.000 | 08W | 2017 | # | OPEN | 1178 | 168.2857 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | 35013233_R2RPL OH WIRE ON GONZALS-1101 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 3538.79
35013266 | *CANC* RECONDUCTOR KINGSBURG 1113 *CANC | 09/13/2017 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/29/2020 | ED.25224.1113 | KINGSBURG 1113 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2017 | 07/03/2020 | 2020 | 1024 | 146.2857 | CLSD | 12 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2020-07-03 | 2020-07-03 | # | 2020-07-03 | 2020-07-03 | # | 2020-07-03 | 2020-07-03 | # | 2020-07-03 | 2020-07-03 | # | 2020-07-03 | 2020-07-03 | # | 2020-07-03 | 2020-07-03 | 0 | 0 | 1230
35013267 | *CANC* RECONDUCTOR CASSIDY 2108 *CANC | 09/13/2017 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/27/2020 | ED.25427.2108 | CASSIDY 2108 | 020 | MADERA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2017 | 05/03/2020 | 2020 | 963 | 137.5714 | CLSD | 12 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | 0 | 0 | 0
35013273 | *CANC*2019 08J CC VIEJO 2201 S018CC*CANC | 09/13/2017 | 113245186 | 09/13/2017 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/27/2019 | JY | JUNK YARD FL TO HOLD DELETED DATA | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 1,500.000 | 0.000 | 08J | 2017 | 10/03/2020 | 2020 | 1116 | 159.4286 | CLSD | 12 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2020-10-03 | 2020-10-03 | # | 2020-10-03 | 2020-10-03 | # | 2020-10-03 | 2020-10-03 | COMP | 2020-09-24 | 2020-09-24 | COMP | 2020-09-24 | 2020-09-24 | COMP | 2020-09-24 | 2020-09-24 | 0 | -9 | 0
35015703 | *CANC* FOOTHILL 1101 LS CO9973 REP *CANC | 09/13/2017 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/20/2019 | ED.18295.1101.TXFR.TROH | OVERHEAD TRANSFORMERS | 040 | SAN LUIS OBISP | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2017 | 09/05/2019 | 2019 | 722 | 103.1429 | CLSD | 12 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 2019-09-05 | 2019-09-05 | # | 2019-09-05 | 2019-09-05 | # | 2019-09-05 | 2019-09-05 | # | 2019-09-05 | 2019-09-05 | # | 2019-09-05 | 2019-09-05 | # | 2019-09-05 | 2019-09-05 | 0 | 0 | 0
35015704 | OH RECONDUCTR ROB ROY 2105 -S026CC117 | 09/15/2017 | 113255603 | 09/15/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/30/2019 | ED.76-O171900000.STRU.POLE | COAST O1719 POLES | 044 | SANTA CRUZ COU | 5535211 | CWSP SPO - SH 08 | 5,300.000 | 0.000 | 08W | 2017 | # | OPEN | 1176 | 168 | PEND | 5 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 51954.16
35015705 | *CANC* R2 OH RECONDUCTR ROB ROY 21*CANC | 09/15/2017 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/30/2019 | ED.76-O171800000.STRU.POLE | COAST O1718 POLES | 044 | SANTA CRUZ COU | 5535211 | CWSP SPO - SH 08 | 4,470.000 | 0.000 | 08W | 2017 | 09/05/2019 | 2019 | 720 | 102.8571 | CLSD | 12 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 2019-09-05 | 2019-09-05 | # | 2019-09-05 | 2019-09-05 | # | 2019-09-05 | 2019-09-05 | COMP | 2019-07-11 | 2019-07-11 | COMP | 2019-07-11 | 2019-07-11 | COMP | 2019-07-11 | 2019-07-11 | 0 | -56 | 0
35015706 | *CANC* OH RECONDUCTOR - ROB ROY 210*CANC | 09/15/2017 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/30/2019 | ED.76-O162000000.STRU.POLE | COAST O1620 POLES | 044 | SANTA CRUZ COU | 5535211 | CWSP SPO - SH 08 | 1,630.000 | 0.000 | 08W | 2017 | 09/05/2019 | 2019 | 720 | 102.8571 | CLSD | 12 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 2019-09-05 | 2019-09-05 | # | 2019-09-05 | 2019-09-05 | # | 2019-09-05 | 2019-09-05 | COMP | 2019-07-10 | 2019-07-10 | COMP | 2019-07-10 | 2019-07-10 | COMP | 2019-07-10 | 2019-07-10 | 0 | -57 | 0
35015932 | *CANC*DO NOT USE* RECONDUCTOR KINGS*CANC | 09/14/2017 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.25224.1112 | KINGSBURG 1112 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2017 | 05/03/2020 | 2020 | 962 | 137.4286 | CLSD | 12 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 35015932_Kingsburg 1112 Recon 9700' | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | COMP | 2020-04-08 | 2020-04-08 | COMP | 2020-04-08 | 2020-04-08 | COMP | 2020-04-08 | 2020-04-08 | 0 | -25 | 0
35015933 | R2RPL OH WIRE ON DOLANRD-1104 17-0069754 | 09/14/2017 | 113248258 | 09/14/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/28/2019 | JY | JUNK YARD FL TO HOLD DELETED DATA | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 1,785.000 | 0.000 | 08J | 2017 | # | OPEN | 1177 | 168.1429 | DOCC | 8 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2020-11-06 | 2020-11-06 | COMP | 2020-10-08 | 2020-11-13 | COMP | 2020-11-13 | 2020-11-13 | INPR | 2020-11-13 | 0 | # | 0 | 0 | # | 0 | 0 | 7 | -44148 | 96921.8
35015934 | R2RPL OH WIRE ON DOLANRAD-1104 S021CC114 | 09/14/2017 | 113248382 | 09/14/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/28/2019 | ED.05-G081600000.STRU.POLE | SALINAS G0816 POLES | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 5,200.000 | 0.000 | 08J | 2017 | # | OPEN | 1177 | 168.1429 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 654.04
35015935 | *CANC*DO NOT USE* RPL OH WIRE ON DO*CANC | 09/14/2017 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/28/2019 | ED.05-E072400000.STRU.POLE | SALINAS E0724 POLES | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 8,950.000 | 0.000 | 08J | 2017 | 05/03/2020 | 2020 | 962 | 137.4286 | CLSD | 12 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | COMP | 2020-04-09 | 2020-04-09 | COMP | 2020-04-09 | 2020-04-09 | COMP | 2020-04-09 | 2020-04-09 | 0 | -24 | 0
35015936 | *CANC*DO NOT USE*RPL OH WIRE ON DOL*CANC | 09/14/2017 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/28/2019 | ED.05-D082000000.STRU.POLE | SALINAS D0820 POLES | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 12,552.000 | 0.000 | 08J | 2017 | 05/03/2020 | 2020 | 962 | 137.4286 | CLSD | 12 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | COMP | 2020-04-09 | 2020-04-09 | COMP | 2020-04-09 | 2020-04-09 | INPR | 2020-04-09 | 2020-05-03 | 0 | 0 | 0
35018262 | *CANC* DINUBA 1104 RECOND 3,240' OF*CANC | 09/21/2017 | 5071444 | 09/21/2017 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/03/2019 | ED.25409.1104 | DINUBA 1104 | 054 | TULARE COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2017 | 06/05/2019 | 2019 | 622 | 88.8571 | CLSD | 12 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | COMP | 2019-05-15 | 2019-05-15 | COMP | 2019-05-15 | 2019-05-15 | COMP | 2019-05-15 | 2019-05-15 | 0 | 43600 | 0
35018263 | *CANC* E STOCKTON 402-RECOND 2,80*CANC | 09/21/2017 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 07/30/2019 | ED.16313.0402 | EAST STOCKTON 0402 | 039 | SAN JOAQUIN CO | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2017 | 04/03/2019 | 2019 | 559 | 79.8571 | CLSD | 12 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2019-04-03 | 2019-04-03 | # | 2019-04-03 | 2019-04-03 | # | 2019-04-03 | 2019-04-03 | COMP | 2019-03-28 | 2019-03-28 | COMP | 2019-03-28 | 2019-03-28 | COMP | 2019-03-28 | 2019-03-28 | 0 | -6 | 0
35018550 | *CANC* RECONDUCTOR BONITA 1101 - A *CANC | 09/19/2017 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/27/2021 | ED.25539.1101 | BONITA 1101 | 020 | MADERA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2017 | 05/03/2020 | 2020 | 957 | 136.7143 | CLSD | 12 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | 0 | 0 | 0
35018551 | RECONDUCTOR LIVINGSTON 1106-D STREET | 09/19/2017 | 113249256 | 09/14/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/29/2019 | ED.25226.1106 | LIVINGSTON 1106 | 024 | MERCED COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2017 | # | OPEN | 1172 | 167.4286 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35018552 | *CANC* R2 EL NIDO 1101 RECOND 3700 *CANC | 09/19/2017 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.25245.1101 | EL NIDO 1101 | 024 | MERCED COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2017 | 05/03/2020 | 2020 | 957 | 136.7143 | CLSD | 12 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | 0 | 0 | 0
35018554 | RIO BRAVO 1106 - RECONDUCTOR | 09/20/2017 | 113258014 | 09/18/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/30/2021 | ED.66-2925200000.STRU.POLE | KERN 29252 POLES | 015 | KERN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2017 | # | OPEN | 1171 | 167.2857 | ESTS | 2 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 35018554_RIO BRAVO 1106 - RECONDUCTOR | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 14916.17
35018561 | *CANC* R2 MERCED 1116 RECONDUCTOR *CANC | 09/20/2017 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.72-0814400000.STRU.POLE | MERCED MAP 08144 POLES | 024 | MERCED COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 6,400.000 | 0.000 | 08J | 2017 | 05/03/2020 | 2020 | 956 | 136.5714 | CLSD | 12 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | 0 | 0 | 0
35018562 | *CANC* ROUGH AND READY 1102 RECOND *CANC | 09/20/2017 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/27/2019 | ED.16308.1102 | ROUGH AND READY IS 1102 | 039 | SAN JOAQUIN CO | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2017 | 04/04/2020 | 2020 | 927 | 132.4286 | CLSD | 12 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2020-04-04 | 2020-04-04 | # | 2020-04-04 | 2020-04-04 | # | 2020-04-04 | 2020-04-04 | # | 2020-04-04 | 2020-04-04 | # | 2020-04-04 | 2020-04-04 | # | 2020-04-04 | 2020-04-04 | 0 | 0 | 0
35018563 | R2 2019 MALAGA 1103 RECONDUCTORING | 09/20/2017 | 113262070 | 09/19/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/30/2021 | ED.70-1421600000.STRU.POLE | FRESNO 14216 POLES | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2017 | # | OPEN | 1171 | 167.2857 | ADER | 3 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Malaga 1103 Reconductor | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 36519.72
35018564 | *CANC*DO NOT USE*2019 MARICOPA 1102*CANC | 09/20/2017 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/30/2021 | ED.66-1123300000.STRU.POLE | KERN 11233 POLES | 015 | KERN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 9,400.000 | 0.000 | 08J | 2017 | 05/03/2020 | 2020 | 956 | 136.5714 | CLSD | 12 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Maricopa 1102 Reconductor | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | COMP | 2020-04-10 | 2020-04-10 | COMP | 2020-04-10 | 2020-04-10 | COMP | 2020-04-10 | 2020-04-10 | 0 | -23 | 0
35018566 | 2019 TAFT 1106 RECONDUCTORING | 09/20/2017 | 113264770 | 09/20/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/30/2022 | ED.66-3223123000.STRU.POLE | KERN 3223123 POLES | 015 | KERN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 6,500.000 | 0.000 | 08J | 2017 | # | OPEN | 1171 | 167.2857 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Taft 1106 Reconductoring | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 9197.99
35018620 | *CANC* RECON CAB 1104 17K FT LASAL *CANC | 09/25/2017 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/22/2019 | ED.18310.1104 | CABRILLO 1104 | 042 | SANTA BARBARA | 5535211 | CWSP SPO - SH 08 | 17,020.000 | 0.000 | 08W | 2017 | 09/05/2019 | 2019 | 710 | 101.4286 | CLSD | 12 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 2019-09-05 | 2019-09-05 | # | 2019-09-05 | 2019-09-05 | # | 2019-09-05 | 2019-09-05 | # | 2019-09-05 | 2019-09-05 | # | 2019-09-05 | 2019-09-05 | # | 2019-09-05 | 2019-09-05 | 0 | 0 | 0
35018622 | RECON 1400' 2CU,UNION SUGAR & OCEAN,LOMP | 09/26/2017 | 113260798 | 09/19/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2021 | ED.18310.1104 | CABRILLO 1104 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2017 | # | OPEN | 1165 | 166.4286 | ESTS | 2 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 3556.88
35018632 | *CANC*DO NOT USE* R2OLD RIVR 1102 R*CANC | 09/29/2017 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/30/2020 | ED.25282.1102.RECL | RECLOSERS | 015 | KERN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2017 | 05/03/2020 | 2020 | 947 | 135.2857 | CLSD | 12 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Old River 1102 Targeted OH Conductor Rep | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | COMP | 2020-04-07 | 2020-04-07 | COMP | 2020-04-07 | 2020-04-07 | COMP | 2020-04-07 | 2020-04-07 | 0 | -26 | 0
35018787 | HALSEY 1101 - S039NO112 HIGH SPLICE 08J | 09/29/2017 | 113265459 | 09/20/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/29/2019 | ED.20-R102100000 | PLACER MAP R1021 | 031 | PLACER COUNTY | 5535211 | CWSP SPO - SH 08 | 2,851.000 | 2,854.000 | 08W | 2017 | # | OPEN | 1162 | 166 | DOCC | 8 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2020-03-17 | 2019-09-09 | COMP | 2019-10-10 | 2020-03-17 | COMP | 2020-03-17 | 2020-08-21 | INPR | 2020-08-21 | 0 | # | 0 | 0 | # | 0 | 0 | 157 | -44064 | 756214.27
35018788 | APPLE HILL 1104 - S049NO119 HIGH SPLICE | 09/29/2017 | 113265480 | 09/20/2017 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/30/2019 | ED.21-H451900000 | EL DORADO MAP H4519 | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 6,399.000 | 6,121.000 | 08W | 2017 | 09/12/2020 | 2020 | 1079 | 154.1429 | CLSD | 12 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2020-01-08 | 2019-09-22 | COMP | 2019-10-08 | 2020-01-08 | COMP | 2020-01-08 | 2020-04-17 | COMP | 2020-04-17 | 2020-08-15 | COMP | 2020-08-15 | 2020-09-04 | COMP | 2020-09-04 | 2020-09-04 | 100 | 140 | 1502306.99
35018886 | *CANC* RPL OH WIRE ON GABILN 1101 *CANC | 10/03/2017 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/28/2019 | ED.05-H120700000.STRU.POLE | SALINAS H1207 POLES | 027 | MONTEREY COUNT | 5535211 | CWSP SPO - SH 08 | 11,592.000 | 0.000 | 08W | 2017 | 09/05/2019 | 2019 | 702 | 100.2857 | CLSD | 12 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 2019-09-05 | 2019-09-05 | # | 2019-09-05 | 2019-09-05 | # | 2019-09-05 | 2019-09-05 | # | 2019-09-05 | 2019-09-05 | # | 2019-09-05 | 2019-09-05 | # | 2019-09-05 | 2019-09-05 | 0 | 0 | 0
35018887 | *CANC* RPL OH WIRE ON OTTER-1101 S*CANC | 10/03/2017 | 113648853 | 10/02/2017 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/28/2019 | ED.07-N030900000.STRU.POLE | MONTEREY N0309 POLES | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2017 | 11/03/2017 | 2017 | 31 | 4.4286 | CLSD | 12 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2017-11-03 | 2017-11-03 | # | 2017-11-03 | 2017-11-03 | # | 2017-11-03 | 2017-11-03 | COMP | 2017-11-02 | 2017-11-02 | COMP | 2017-11-02 | 2017-11-02 | COMP | 2017-11-02 | 2017-11-02 | 0 | -1 | 0
35018895 | OROSI 1101 RECOND 4460FT TO 2AR | 10/05/2017 | 113674750 | 10/04/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/30/2021 | ED.25284.1101 | OROSI 1101 | 054 | TULARE COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2017 | # | OPEN | 1156 | 165.1429 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 4693.11
35019004 | PURISIMA 1101 LS SW8139 REPL OH LINE | 10/06/2017 | 113677313 | 10/05/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/05/2019 | ED.18297.1101.TXFR.TROH | OVERHEAD TRANSFORMERS | 040 | SAN LUIS OBISP | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2017 | # | OPEN | 1155 | 165 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 8820.84
35019005 | SISQUOC 1104 LR M58 REPLACE OH LINE | 10/06/2017 | 113677552 | 10/05/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/05/2019 | ED.18281.1104.TXFR.TROH | OVERHEAD TRANSFORMERS | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2017 | # | OPEN | 1155 | 165 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35019006 | ROB ROY 2104 CO11865 REPLACE OH LINE | 10/06/2017 | 113677589 | 10/05/2017 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/05/2019 | JY | JUNK YARD FL TO HOLD DELETED DATA | 044 | SANTA CRUZ COU | 5535211 | CWSP SPO - SH 08 | 9,680.000 | 8,620.000 | 08W | 2017 | 07/25/2020 | 2020 | 1023 | 146.1429 | CLSD | 12 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2019-12-11 | 2019-12-11 | COMP | 2020-01-15 | 2020-01-15 | COMP | 2020-01-15 | 2020-01-15 | COMP | 2020-02-28 | 2020-04-21 | COMP | 2020-04-21 | 2020-06-10 | COMP | 2020-06-10 | 2020-06-10 | 35 | 147 | 1004571.38
35019007 | RECON 4780', LR7024, KING CITY 1102 | 10/06/2017 | 113677628 | 10/05/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/05/2019 | ED.18203.1102.SWIT | SWITCHES | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2017 | # | OPEN | 1155 | 165 | ADER | 3 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 44332
35019122 | *CANC*R2 RE-COND 2641 FT OF 3-4ACSR*CANC | 10/10/2017 | 113632342 | 09/28/2017 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/28/2019 | ED.18310.1104 | CABRILLO 1104 | 040 | SAN LUIS OBISP | 5535457 | DO 08 - Monthly Forecast Only | 2,623.000 | 0.000 | 08J | 2017 | 01/04/2019 | 2019 | 451 | 64.4286 | CLSD | 12 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2019-01-04 | 2019-01-04 | # | 2019-01-04 | 2019-01-04 | # | 2019-01-04 | 2019-01-04 | # | 2019-01-04 | 2019-01-04 | # | 2019-01-04 | 2019-01-04 | # | 2019-01-04 | 2019-01-04 | 0 | 0 | 0
35019123 | RECONDUCTOR 3579 FT W 2CU MESA 1101 | 10/10/2017 | 113717955 | 10/10/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/10/2019 | ED.18282.1101 | MESA 1101 | 040 | SAN LUIS OBISP | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2017 | # | OPEN | 1151 | 164.4286 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 343.89
35019222 | R2 RPL OH WRE ON PRUNDLE 1107 17-0075216 | 10/10/2017 | 113703369 | 10/09/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/28/2019 | ED.05-E092000000.STRU.POLE | SALINAS E0920 POLES | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2017 | # | OPEN | 1151 | 164.4286 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 1094.77
35019354 | *CANC* GANSO 1104 RECOND 2900FT TO 2AR | 10/23/2017 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/28/2019 | ED.25454.1104 | GANSO 1104 | 015 | KERN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2017 | 11/04/2017 | 2017 | 12 | 1.7143 | CLSD | 12 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0
35019447 | +R2 RECONDUCTR 4268FT OF3-4ACSR WT3-2CU | 10/16/2017 | 113724523 | 10/12/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.18310.1104 | CABRILLO 1104 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 4,396.000 | 0.000 | 08J | 2017 | # | OPEN | 1145 | 163.5714 | CONS | 7 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 83322.08
35019453 | RECONDUCTOR 1230 FT(7 SPANS) OF 3-6CU | 10/18/2017 | 113742341 | 10/17/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/30/2019 | ED.18206.1106 | FAIRWAY 1106 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2017 | # | OPEN | 1143 | 163.2857 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35019544 | *CANC* ELK HILLS 1104 SPLICE FUSE 19082 | 10/20/2017 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/30/2019 | ED.25244.1104 | ELK HILLS 1104 | 015 | KERN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2017 | 11/04/2017 | 2017 | 15 | 2.1429 | CLSD | 12 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0
35019545 | *CANC* ELK HILLS 1104 OH SPLICE SSD1523 | 10/20/2017 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/30/2019 | ED.25244.1104 | ELK HILLS 1104 | 020 | MADERA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2017 | 11/04/2017 | 2017 | 15 | 2.1429 | CLSD | 12 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0
35020110 | 2019 08J CC SOLEDAD 1114 S060CC214 | 11/07/2017 | 113747742 | 10/19/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/27/2019 | ED.18205.1114.SWIT | SWITCHES | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 6,896.000 | 0.000 | 08J | 2017 | # | OPEN | 1123 | 160.4286 | UNSC | 6 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 207409.56
35020479 | CALIFORNIA 1103 RECOND 380FT INST 2 FUSE | 11/15/2017 | 113813608 | 11/14/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/29/2019 | ED.25228.1103 | CALIFORNIA AVE 1103 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2017 | # | OPEN | 1115 | 159.2857 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35023586 | R2 RPL OH WIRE ON SPENCE 1123 17-0094873 | 12/05/2017 | 114048528 | 12/04/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/28/2019 | ED.05-I121000000.STRU.POLE | SALINAS I1210 POLES | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 640.000 | 0.000 | 08J | 2017 | # | OPEN | 1095 | 156.4286 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35023620 | *CANC *DO NOT USE* RECONDUCTOR AR W*CANC | 12/03/2017 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.18282.1101 | MESA 1101 | 040 | SAN LUIS OBISP | 5535457 | DO 08 - Monthly Forecast Only | 11,495.000 | 0.000 | 08J | 2017 | 05/03/2020 | 2020 | 882 | 126 | CLSD | 12 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | COMP | 2020-04-10 | 2020-04-10 | COMP | 2020-04-10 | 2020-04-10 | COMP | 2020-04-10 | 2020-04-10 | 0 | -23 | 0
35023687 | R2RPL OH WIRE ON B LOMND 0401 17-0095503 | 12/06/2017 | 114063986 | 12/06/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/28/2019 | ED.08304.0401.RECL | RECLOSERS | 044 | SANTA CRUZ COU | 5535211 | CWSP SPO - SH 08 | 7,590.000 | 7,044.000 | 08W | 2017 | # | OPEN | 1094 | 156.2857 | DOCC | 8 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | 35023687_R2RPL OH WIRE ON B LOMND 0401 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2019-12-19 | 2019-12-19 | COMP | 2020-02-11 | 2020-04-10 | COMP | 2020-04-10 | 2020-04-10 | COMP | 2020-04-10 | 2020-04-13 | COMP | 2020-04-13 | 2020-04-23 | COMP | 2020-04-23 | 2020-04-27 | 113 | 17 | 3708946.88
35023873 | *CNCL* REEDLEY 1104 RECON OH SPLICE | 12/13/2017 | 5222754 | 12/13/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/31/2021 | ED.25234.1104 | REEDLEY 1104 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2017 | # | OPEN | 1087 | 155.2857 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 1416.95
35023874 | *CANC*R2 RPL OH WIRE ON SPENCE 1123 17-0 | 12/13/2017 | 114088923 | 12/13/2017 | # | Not assigned | 30 | Technically Completed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/28/2019 | JY | JUNK YARD FL TO HOLD DELETED DATA | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 937.000 | 0.000 | 08J | 2017 | # | OPEN | 1087 | 155.2857 | PROD | Other | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 1953.32
35023901 | RECONDUCTOR WILSON 1103 - GERARD AVE. | 12/11/2017 | 114068224 | 12/07/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/27/2019 | ED.25430.1103 | WILSON 1103 | 024 | MERCED COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2017 | # | OPEN | 1089 | 155.5714 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35024043 | KEARNEY 1104 RECOND 2595FT 6CU | 12/14/2017 | 114105611 | 12/14/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 07/31/2020 | ED.25270.1104 | KEARNEY 1104 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2017 | # | OPEN | 1086 | 155.1429 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 646.54
35024427 | BARRY 1103 RECONDUCTOR | 12/26/2017 | 114127297 | 12/26/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2019 | ED.15211.1103.SWIT | SWITCHES | 051 | SUTTER COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2017 | # | OPEN | 1074 | 153.4286 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 624.49
35024428 | SUMMIT 1101 RECONDUCTOR W TREE WIRE | 12/26/2017 | 114127299 | 12/26/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2019 | ED.15259.1101.SWIT | SWITCHES | 031 | PLACER COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2017 | # | OPEN | 1074 | 153.4286 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 220.19
35024625 | 2019 BRENTWOOD 2112 HIGH SPLICE COUNT | 01/02/2018 | 114143979 | 01/02/2018 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2019 | ED.01459.2112 | BRENTWOOD 2112 | 007 | CONTRA COSTA C | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2018 | # | OPEN | 1067 | 152.4286 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 11840.65
35024645 | S031CC201 - RR2105 RECONDUCT NEAR SW7387 | 01/03/2018 | 113820860 | 11/16/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/30/2019 | ED.08369.2105.SWIT | SWITCHES | 044 | SANTA CRUZ COU | 5535457 | DO 08 - Monthly Forecast Only | 368.000 | 0.000 | 08J | 2018 | # | OPEN | 1066 | 152.2857 | CONS | 7 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | INPR | 2020-10-08 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 8037.72
35024646 | S048CC209 - RR2105 RECONDUCT 9333 ZONE | 01/03/2018 | 113820882 | 11/16/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/30/2019 | JY | JUNK YARD FL TO HOLD DELETED DATA | 044 | SANTA CRUZ COU | 5535457 | DO 08 - Monthly Forecast Only | 2,753.000 | 0.000 | 08J | 2018 | # | OPEN | 1066 | 152.2857 | PEND | 5 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 35024646 S048CC209 - RR2105 RECONDUCT 9 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 34695.86
35024647 | RR 2104 RECOND 1051 ZONE W TW | 01/03/2018 | 113820887 | 11/16/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/30/2019 | ED.76-P180300000.STRU.POLE | COAST P1803 POLES | 044 | SANTA CRUZ COU | 5535211 | CWSP SPO - SH 08 | 2,717.000 | 0.000 | 08W | 2018 | # | OPEN | 1066 | 152.2857 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 326.51
35024648 | RR2105 RECONDUCTOR NEAR SW 4035 | 01/03/2018 | 113821142 | 11/16/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/30/2019 | ED.76-O172200000.STRU.POLE | COAST O1722 POLES | 044 | SANTA CRUZ COU | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2018 | # | OPEN | 1066 | 152.2857 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 335
35024926 | MARTELL 1101 RECONDCUTOR 3,700FT | 01/08/2018 | 114119281 | 12/20/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/28/2018 | ED.16301.1101 | MARTELL 1101 | 003 | AMADOR COUNTY | 5535211 | CWSP SPO - SH 08 | 4,436.000 | 4,090.000 | 08W | 2018 | # | OPEN | 1061 | 151.5714 | MAPP | 9 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2019-03-30 | 2019-03-30 | COMP | 2019-04-04 | 2019-04-05 | COMP | 2019-04-05 | 2019-04-05 | INPR | 2020-07-28 | 0 | # | 0 | 0 | # | 0 | 0 | 6 | -43560 | 537779.55
35025379 | *CANC*DO NOTUSE*REEDLEY 1110 RECOND*CANC | 01/18/2018 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/26/2020 | ED.25234.1110 | REEDLEY 1110 | 054 | TULARE COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2018 | 05/03/2020 | 2020 | 836 | 119.4286 | CLSD | 12 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | COMP | 2020-04-08 | 2020-04-08 | COMP | 2020-04-08 | 2020-04-08 | COMP | 2020-04-08 | 2020-04-08 | 0 | -25 | 0
35025961 | PEABODY 2107 PHASE 1 RECOND LINE CO 5527 | 01/29/2018 | 114231251 | 01/18/2018 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/30/2020 | ED.06364.2105.SWIT | SWITCHES | 048 | SOLANO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2018 | # | OPEN | 1040 | 148.5714 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35025962 | PEABODY 2107 PHASE 2 RECOND LINE CO 5527 | 01/29/2018 | 114231333 | 01/18/2018 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/18/2020 | ED.06364.2105.SWIT | SWITCHES | 048 | SOLANO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2018 | # | OPEN | 1040 | 148.5714 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35026093 | ALPAUGH 1106 RECOND 7,600 FEET | 02/01/2018 | 114263352 | 01/31/2018 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/26/2020 | ED.25400.1106 | ALPAUGH 1106 | 054 | TULARE COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2018 | # | OPEN | 1037 | 148.1429 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 159.96
35026245 | *CANC*DO NOT USE*R2RPL OH WIRE GON*CANC | 02/05/2018 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/28/2020 | ED.05-K132500000.STRU.POLE | SALINAS K1325 POLES | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 11,121.000 | 0.000 | 08J | 2018 | 05/03/2020 | 2020 | 818 | 116.8571 | CLSD | 12 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | COMP | 2020-04-09 | 2020-04-09 | COMP | 2020-04-09 | 2020-04-09 | COMP | 2020-04-09 | 2020-04-09 | 0 | -24 | 0
35026420 | *CANC*OAKLAND X-1104 OH RECOND SKYLINE | 02/08/2018 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 03/01/2020 | ED.26-F070700000.STRU.POLE | CENTRAL F0707 POLES | 001 | ALAMEDA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2018 | 08/05/2020 | 2020 | 909 | 129.8571 | CLSD | 12 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 2020-08-05 | 2020-08-05 | # | 2020-08-05 | 2020-08-05 | # | 2020-08-05 | 2020-08-05 | COMP | 2020-06-04 | 2020-06-04 | COMP | 2020-06-04 | 2020-06-04 | COMP | 2020-06-04 | 2020-06-04 | 0 | -62 | 1912.99
35026643 | RECONDUCTOR DIAMOND SPRINGS 1105 | 02/12/2018 | 114258488 | 01/30/2018 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2019 | ED.15226.1105.SWIT | SWITCHES | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2018 | # | OPEN | 1026 | 146.5714 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 45056.84
35026701 | *CANC*RECONDUCTOR 4901 WITH 397AL. | 02/13/2018 | 114283557 | 02/07/2018 | # | Not assigned | 30 | Technically Completed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 02/07/2019 | ED.18263.1101 | SAN LUIS OBISPO 1101 | 040 | SAN LUIS OBISP | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2018 | # | OPEN | 1025 | 146.4286 | PROD | Other | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 1523.83
35026864 | RECOND GREEN VALLEY 2103 REF# S032CC202 | 02/17/2018 | 114319113 | 02/16/2018 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 06/26/2020 | ED.08319.2103 | GREEN VALLEY 2103 | 044 | SANTA CRUZ COU | 5517128 | DO 49 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2018 | # | OPEN | 1021 | 145.8571 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | RECOND GREEN VALLEY 2103 REF# S032CC202 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 1871.96
35029270 | MORGAN HILL 2111 RECOND 13-SPANS W TW | 03/06/2018 | 114352762 | 03/02/2018 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/30/2020 | ED.08324.2111 | MORGAN HILL 2111 | 043 | SANTA CLARA CO | 5535211 | CWSP SPO - SH 08 | 3,270.000 | 0.000 | 08W | 2018 | # | OPEN | 1004 | 143.4286 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 3242.82
35029542 | BIOLA 1104 2019 TARGETED OH REPLACEMENT | 03/09/2018 | 114373073 | 03/09/2018 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/14/2019 | ED.25221.1104 | BIOLA 1104 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2018 | # | OPEN | 1001 | 143 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 241.14
35029543 | REEDLEY 1104 RECONDCUTOR OH SPLICE | 03/09/2018 | 114088517 | 12/13/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/27/2019 | ED.25234.1104 | REEDLEY 1104 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2018 | # | OPEN | 1001 | 143 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35029545 | DINUBA 1104 RECOND 3,240' OF 6CU/W 2ACSR | 03/09/2018 | 113266252 | 09/21/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/30/2020 | ED.25409.1104 | DINUBA 1104 | 054 | TULARE COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2018 | # | OPEN | 1001 | 143 | PEND | 5 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 15502.94
35029546 | BIOLA 1104 6,350FT TARGET OH REPL | 03/09/2018 | 113241721 | 09/12/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2021 | ED.25221.1104 | BIOLA 1104 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2018 | # | OPEN | 1001 | 143 | ESTS | 2 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 14324.92
35029744 | BIOLA 1104 2019 TARGETED OH REPLACEMENT | 03/13/2018 | # | #N/A | 35008420 | *CANC*2B CANC BIOLA 1104 2019 TARGE*CANC | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | # | ED.25221.1104 | BIOLA 1104 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2018 | # | OPEN | 997 | 142.4286 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35029808 | R2PLOH WIRE ON CASTROVILE2104 18-0016481 | 03/14/2018 | 114408681 | 03/14/2018 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/28/2020 | ED.05-F080600000.STRU.POLE | SALINAS F0806 POLES | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 1,974.000 | 0.000 | 08J | 2018 | # | OPEN | 996 | 142.2857 | PEND | 5 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 9343.58
35029850 | RE-COND 1328FT, CAMBRIA 1101, CAMBRIA | 03/15/2018 | 114372949 | 03/09/2018 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/09/2021 | ED.18277.1101 | CAMBRIA 1101 | 040 | SAN LUIS OBISP | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2018 | # | OPEN | 995 | 142.1429 | ESTS | 2 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 6057.1
35029942 | REPL 8400' OF ANNEALED 4CU/WYANDOTTE1106 | 03/16/2018 | 113101418 | 07/31/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2019 | ED.10291.1106.RECL | RECLOSERS | 004 | BUTTE COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2018 | # | OPEN | 994 | 142 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35030165 | ML2105 RECONDUCTOR - FUSE 9585 | 03/20/2018 | 114425767 | 03/19/2018 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/30/2020 | ED.01430.2105 | MEADOW LANE 2105 | 007 | CONTRA COSTA C | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2018 | # | OPEN | 990 | 141.4286 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 5026.05
35030422 | RE-CONDUCTOR 1482 FEET SANTA MARIA 1110 | 03/23/2018 | 114437808 | 03/23/2018 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2021 | ED.18267.1110 | SANTA MARIA 1110 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2018 | # | OPEN | 987 | 141 | ESTS | 2 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 7363.79
35030568 | CWSP HALF MOON BAY 1101 FUCO 4141 | 03/28/2018 | 114435598 | 03/22/2018 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 05/18/2022 | ED.02410.1101 | HALF MOON BAY 1101 | 041 | SAN MATEO COUN | 5535211 | CWSP SPO - SH 08 | 4,690.000 | 0.000 | 08W | 2018 | # | OPEN | 982 | 140.2857 | PEND | 5 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 68131.94
35030621 | ZAMORA 1106 RECONDUCTOR LINE BAD SPLICES | 03/26/2018 | 114435163 | 03/22/2018 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/22/2021 | ED.06319.1106.SWIT | SWITCHES | 057 | YOLO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2018 | # | OPEN | 984 | 140.5714 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35030654 | TW ON WOODSIDE1101 N/O 7573 | 03/30/2018 | 114452534 | 03/29/2018 | # | Not assigned | 30 | Technically Completed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/30/2019 | ED.02425.1101 | WOODSIDE 1101 | 041 | SAN MATEO COUN | 5535211 | CWSP SPO - SH 08 | 5,271.000 | 5,271.000 | 08W | 2018 | # | OPEN | 980 | 140 | FICL | 10 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2020-01-03 | 2019-12-06 | COMP | 2020-01-16 | 2020-01-16 | COMP | 2020-01-16 | 2020-01-16 | COMP | 2020-03-02 | 2020-03-23 | COMP | 2020-03-23 | 2020-03-25 | COMP | 2020-03-25 | 2020-03-30 | 13 | 74 | 1790090.01
35031040 | MAPLE CREEK 1101 2020 WIRE DOWN | 04/02/2018 | 114454233 | 03/29/2018 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/17/2021 | ED.19210.1101.SWIT | SWITCHES | 012 | HUMBOLDT COUNT | 5535457 | DO 08 - Monthly Forecast Only | 3,088.000 | 0.000 | 08J | 2018 | # | OPEN | 977 | 139.5714 | PEND | 5 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 26486.11
35031041 | KINGSBURG 1111 RECONDUCTOR 21,880 FEET | 04/02/2018 | 114456033 | 03/30/2018 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.25224.1111 | KINGSBURG 1111 | 054 | TULARE COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2018 | # | OPEN | 977 | 139.5714 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Kingsburg 1111 Recond 21,880' of #6CU Wi | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 6506.47
35031139 | SHADY GLEN 1102 RECONDUCTOR BEYOND 6343 | 04/04/2018 | 114446685 | 03/27/2018 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2019 | ED.15243.1102.SWIT | SWITCHES | 031 | PLACER COUNTY | 5535211 | CWSP SPO - SH 08 | 7,935.000 | 7,782.000 | 08W | 2018 | 08/08/2020 | 2020 | 857 | 122.4286 | CLSD | 12 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2019-12-30 | 2019-12-30 | COMP | 2019-12-31 | 2019-12-31 | COMP | 2019-12-31 | 2019-12-31 | COMP | 2019-12-31 | 2020-01-02 | COMP | 2020-01-02 | 2020-01-13 | COMP | 2020-01-13 | 2020-01-13 | 1 | 13 | 2407892.68
35031660 | *CANC* PH 1:REPL 14 000' OF 4AR IN *CANC | 04/10/2018 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/30/2019 | ED.08202.1106 | LOS GATOS 1106 | 043 | SANTA CLARA CO | 5535211 | CWSP SPO - SH 08 | 14,350.000 | 0.000 | 08W | 2018 | 09/05/2019 | 2019 | 513 | 73.2857 | CLSD | 12 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 2019-09-05 | 2019-09-05 | # | 2019-09-05 | 2019-09-05 | # | 2019-09-05 | 2019-09-05 | # | 2019-09-05 | 2019-09-05 | # | 2019-09-05 | 2019-09-05 | # | 2019-09-05 | 2019-09-05 | 0 | 0 | 0
35031662 | CWSP - LOS GATOS 1106 - LB44 - PHASE 2.1 | 04/10/2018 | 114474310 | 04/05/2018 | # | Not assigned | 30 | Technically Completed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 08/31/2020 | ED.08202.1106 | LOS GATOS 1106 | 043 | SANTA CLARA CO | 5535211 | CWSP SPO - SH 08 | 2,978.000 | 2,978.000 | 08W | 2018 | # | OPEN | 969 | 138.4286 | FICL | 10 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Los Gatos 1106 - LB44 - Ph 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2020-03-25 | 2020-03-25 | COMP | 2020-03-26 | 2020-03-26 | COMP | 2020-03-26 | 2020-03-26 | COMP | 2020-03-26 | 2020-03-30 | COMP | 2020-03-30 | 2020-05-21 | COMP | 2020-05-21 | 2020-05-26 | 1 | 61 | 750109.71
35031663 | CWSP - LOS GATOS 1106 - LB44 - PHASE 3.1 | 04/10/2018 | 114474316 | 04/05/2018 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 08/31/2020 | ED.08202.1106 | LOS GATOS 1106 | 043 | SANTA CLARA CO | 5535211 | CWSP SPO - SH 08 | 24,000.000 | 0.000 | 08W | 2018 | # | OPEN | 969 | 138.4286 | ESTS | 2 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Los Gatos 1106 - LB44 - Ph 3.1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 43460.11
35031714 | *CANC*DO NOT USE*COTATI 1103 RECOND*CANC | 04/12/2018 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/01/2021 | ED.04227.1103.SWIT | SWITCHES | 021 | MARIN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2018 | 05/03/2020 | 2020 | 752 | 107.4286 | CLSD | 12 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | COMP | 2020-04-10 | 2020-04-10 | COMP | 2020-04-10 | 2020-04-10 | COMP | 2020-04-10 | 2020-04-10 | 0 | -23 | 0
35032114 | GV2102 RECONDUCTOR WD | 04/18/2018 | 114503633 | 04/13/2018 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/28/2019 | ED.76-P202400000.STRU.POLE | COAST P2024 POLES | 044 | SANTA CRUZ COU | 5535457 | DO 08 - Monthly Forecast Only | 1,173.000 | 0.000 | 08J | 2018 | # | OPEN | 961 | 137.2857 | PEND | 5 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 10631.05
35032266 | APPLE HILL 1104 RECONDUCTOR | 04/18/2018 | 114514465 | 04/18/2018 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2019 | ED.15366.1104.SWIT | SWITCHES | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 877.000 | 877.000 | 08W | 2018 | 05/09/2020 | 2020 | 752 | 107.4286 | CLSD | 12 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2020-01-08 | 2019-08-01 | COMP | 2019-10-10 | 2020-01-08 | COMP | 2020-01-08 | 2020-04-14 | COMP | 2020-04-14 | 2020-04-15 | COMP | 2020-04-15 | 2020-04-22 | COMP | 2020-04-22 | 2020-04-22 | 97 | 8 | 284268.56
35039002 | OCGC 2018 CALISTOGA 1101 LEVEL 2 DEMO | 05/01/2018 | 114553028 | 05/01/2018 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/31/2018 | ED.04271.1101 | CALISTOGA 1101 | 028 | NAPA COUNTY | 5535211 | CWSP SPO - SH 08 | 6,007.000 | 6,007.000 | 08W | 2018 | 08/15/2020 | 2020 | 837 | 119.5714 | CLSD | 12 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2018-08-30 | 2019-03-29 | COMP | 2019-03-29 | 2019-04-01 | COMP | 2019-04-01 | 2019-04-01 | COMP | 2019-04-01 | 2019-04-02 | COMP | 2019-04-02 | 2019-04-05 | COMP | 2019-04-05 | 2019-04-10 | 214 | 9 | 1123231.99
35039042 | R2ATWATER 1108 RECONDUCTORING - WIREDOWN | 05/02/2018 | 114558484 | 05/02/2018 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 01/19/2022 | ED.72-06126D0000.STRU.POLE | MERCED MAP 06126D POLES | 024 | MERCED COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2018 | # | OPEN | 947 | 135.2857 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 3757.48
35039748 | CWSP-MIWUK 1702-LR 38218 | 05/07/2018 | 5381781 | 05/07/2018 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.16366.1702 | MIWUK 1702 | 055 | TUOLUMNE COUNT | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2018 | # | OPEN | 942 | 134.5714 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 13754.65
35039757 | *CANC* CWSP - BURNS 2101 - OCB - PHASE1 | 05/07/2018 | 5382422 | 05/07/2018 | # | Not assigned | 30 | Technically Completed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/28/2020 | ED.18358.2101.SWIT | SWITCHES | 044 | SANTA CRUZ COU | 5535211 | CWSP SPO - SH 08 | 40,920.000 | 0.000 | 08W | 2018 | # | OPEN | 942 | 134.5714 | PROD | Other | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | COMP | 2020-06-17 | 2020-06-17 | COMP | 2020-06-17 | 2020-06-17 | COMP | 2020-06-17 | 2020-06-17 | 0 | 43999 | 3024.03
35039957 | *CANC* CWSP - STANISLAUS 1702 LR18 *CANC | 05/09/2018 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/20/2020 | ED.16282.1702 | STANISLAUS 1702 | 005 | CALAVERAS COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2018 | 05/03/2020 | 2020 | 725 | 103.5714 | CLSD | 12 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | 0 | 0 | 0
35039982 | CWSP: MIWUK 1702_OCB WILDFIRE HARDENING | 05/09/2018 | 5383919 | 05/09/2018 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.16366.1702 | MIWUK 1702 | 055 | TUOLUMNE COUNT | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2018 | # | OPEN | 940 | 134.2857 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 1523.83
35040016 | *CANC* CWSP-SILVERADO 2104-LR 722 *CANC | 05/10/2018 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.04343.2104 | SILVERADO 2104 | 028 | NAPA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2018 | 09/05/2019 | 2019 | 483 | 69 | CLSD | 12 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 2019-09-05 | 2019-09-05 | # | 2019-09-05 | 2019-09-05 | # | 2019-09-05 | 2019-09-05 | # | 2019-09-05 | 2019-09-05 | # | 2019-09-05 | 2019-09-05 | # | 2019-09-05 | 2019-09-05 | 0 | 0 | 0
35040017 | CWSP - OAK K 1102 OCB LVL 1 HARDENING | 05/10/2018 | # | #N/A | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.01210.1102 | OAKLAND K 1102 | 001 | ALAMEDA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2018 | # | OPEN | 939 | 134.1429 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 132064.21
35040018 | CWSP - MORAGA 1101 (VARIOUS) - OCB | 05/10/2018 | # | #N/A | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.01380.1101 | MORAGA 1101 | 007 | CONTRA COSTA C | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2018 | # | OPEN | 939 | 134.1429 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 22676.04
35040118 | CWSP: MIWUK 1701_OCB WILDFIRE HARDENING | 05/11/2018 | 5390147 | 05/11/2018 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.16366.1701 | MIWUK 1701 | 055 | TUOLUMNE COUNT | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2018 | # | OPEN | 938 | 134 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 1954.21
35040225 | HIGGINS 1110 RECONDUCTOR | 05/11/2018 | 114565015 | 05/03/2018 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2019 | ED.15269.1110.SWIT | SWITCHES | 029 | NEVADA COUNTY | 5535211 | CWSP SPO - SH 08 | 8,486.000 | 8,584.000 | 08W | 2018 | 05/23/2020 | 2020 | 743 | 106.1429 | CLSD | 12 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2019-09-30 | 2019-09-30 | COMP | 2019-10-10 | 2020-03-17 | COMP | 2020-03-17 | 2020-04-30 | COMP | 2020-04-30 | 2020-05-04 | COMP | 2020-05-04 | 2020-05-19 | COMP | 2020-05-19 | 2020-05-20 | 213 | 20 | 2412478.72
35040505 | CWSP - BIG BASIN 1101 - LR 10296 - PH1 | 05/15/2018 | 5395051 | 05/15/2018 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/30/2020 | ED.76-L110300000.STRU.POLE | COAST L1103 POLES | 044 | SANTA CRUZ COU | 5535211 | CWSP SPO - SH 08 | 38,412.000 | 0.000 | 08W | 2018 | # | OPEN | 934 | 133.4286 | ESTS | 2 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 8140.43
35040506 | RR2105 RESILIENCE - 5090 ZONE STEEL & TW | 05/15/2018 | 114607613 | 05/15/2018 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/30/2018 | ED.76-O171200000.STRU.POLE | COAST O1712 POLES | 044 | SANTA CRUZ COU | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2018 | # | OPEN | 934 | 133.4286 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 2868.14
35040528 | *CANC*RECOND 8-SPANS MILPITAS 1105 *CANC | 05/16/2018 | 114605349 | 05/15/2018 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/28/2018 | ED.08283.1105 | MILPITAS 1105 | 043 | SANTA CLARA CO | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2018 | 07/04/2018 | 2018 | 49 | 7 | CLSD | 12 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2018-07-04 | 2018-07-04 | # | 2018-07-04 | 2018-07-04 | # | 2018-07-04 | 2018-07-04 | COMP | 2018-06-14 | 2018-06-14 | COMP | 2018-06-14 | 2018-06-14 | COMP | 2018-06-14 | 2018-06-14 | 0 | -20 | 0
35040742 | OCGC - 2018 MONTE RIO 1112 OH TO UG DEMO | 05/17/2018 | 114609098 | 05/16/2018 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2018 | ED.04257.1102.SWIT | SWITCHES | 049 | SONOMA COUNTY | 5535211 | CWSP SPO - SH 08 | 2,578.000 | 2,710.000 | 08W | 2018 | 11/23/2019 | 2019 | 555 | 79.2857 | CLSD | 12 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2018-07-31 | 2019-04-05 | COMP | 2019-04-09 | 2019-04-09 | COMP | 2019-04-09 | 2019-04-09 | COMP | 2019-04-12 | 2019-09-28 | COMP | 2019-09-28 | 2019-10-07 | COMP | 2019-10-07 | 2019-10-09 | 252 | 183 | 1396819.83
35040961 | CWSP: 2018 K-1102 OH TO UG DEMO | 05/21/2018 | 114610526 | 05/16/2018 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2018 | ED.01210.1102 | OAKLAND K 1102 | 007 | CONTRA COSTA C | 5535211 | CWSP SPO - SH 08 | 3,845.000 | 4,235.000 | 08W | 2018 | 12/28/2019 | 2019 | 586 | 83.7143 | CLSD | 12 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2018-08-07 | 2019-04-26 | COMP | 2019-06-18 | 2019-06-18 | COMP | 2019-06-20 | 2019-06-20 | COMP | 2019-06-20 | 2019-06-21 | COMP | 2019-06-21 | 2019-06-22 | COMP | 2019-06-22 | 2019-06-22 | 317 | 2 | 772079.48
35041157 | RECONDUCTOR 830FT (5 SPANS) OF 6CU&4AR | 05/23/2018 | 114627165 | 05/22/2018 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 07/31/2020 | ED.10291.1109 | WYANDOTTE 1109 | 004 | BUTTE COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2018 | # | OPEN | 926 | 132.2857 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 435.35
35041202 | *TRSFR* 35052732 CWSP-BB 1101 - LR *CANC | 05/23/2018 | 5402526 | 05/23/2018 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/30/2020 | ED.76-L110300000.STRU.POLE | COAST L1103 POLES | 044 | SANTA CRUZ COU | 5535211 | CWSP SPO - SH 08 | 32,717.000 | 0.000 | 08W | 2018 | 08/05/2020 | 2020 | 805 | 115 | CLSD | 12 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | COMP | 2020-06-17 | 2020-06-17 | COMP | 2020-06-17 | 2020-06-17 | COMP | 2020-06-17 | 2020-06-17 | 0 | 43999 | 6362.07
35041205 | *CANC* WSP LOS GATOS 1106 LR 60116 PHAS | 05/23/2018 | 5402561 | 05/23/2018 | # | Not assigned | 30 | Technically Completed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/28/2020 | ED.08202.1106.RECL | RECLOSERS | 043 | SANTA CLARA CO | 5535211 | CWSP SPO - SH 08 | 41,184.000 | 0.000 | 08W | 2018 | # | OPEN | 926 | 132.2857 | PROD | Other | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | COMP | 2020-06-17 | 2020-06-17 | COMP | 2020-06-17 | 2020-06-17 | COMP | 2020-06-17 | 2020-06-17 | 0 | 43999 | 2386.72
35042350 | RE-CONDUCTOR 279 FT OF 4ACSR WITH 2 CU | 05/29/2018 | 114625720 | 05/22/2018 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/22/2020 | ED.18206.1106 | FAIRWAY 1106 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2018 | # | OPEN | 920 | 131.4286 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35042365 | CWSP - CAMP EVERS 2106 - LR 60124 - PH 5 | 05/29/2018 | 114641001 | 05/29/2018 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/01/2020 | ED.08362.2106 | CAMP EVERS 2106 | 044 | SANTA CRUZ COU | 5535211 | CWSP SPO - SH 08 | 47,414.000 | 0.000 | 08W | 2018 | # | OPEN | 920 | 131.4286 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 8089.18
35042366 | CWSP - CAMP EVERS 2106 - 60124 - PHASE 4 | 05/29/2018 | 114640939 | 05/29/2018 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/01/2020 | ED.08362.2106 | CAMP EVERS 2106 | 044 | SANTA CRUZ COU | 5535211 | CWSP SPO - SH 08 | 38,110.000 | 0.000 | 08W | 2018 | # | OPEN | 920 | 131.4286 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 7261.21
35042367 | CWSP - CAMP EVERS 2106 - 60124 - PHASE 3 | 05/29/2018 | 114640938 | 05/29/2018 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/01/2020 | ED.08362.2106 | CAMP EVERS 2106 | 044 | SANTA CRUZ COU | 5535211 | CWSP SPO - SH 08 | 39,389.000 | 0.000 | 08W | 2018 | # | OPEN | 920 | 131.4286 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 22274.16
35042368 | CWSP - CAMP EVERS 2106 - 60124 - PHASE 2 | 05/29/2018 | 114640937 | 05/29/2018 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/01/2020 | ED.08362.2106 | CAMP EVERS 2106 | 044 | SANTA CRUZ COU | 5535211 | CWSP SPO - SH 08 | 38,861.000 | 0.000 | 08W | 2018 | # | OPEN | 920 | 131.4286 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 7726.66
35042369 | CWSP - CAMP EVERS 2106 - 60124 - PHASE 1 | 05/29/2018 | 114640931 | 05/29/2018 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/01/2020 | ED.08362.2106 | CAMP EVERS 2106 | 044 | SANTA CRUZ COU | 5535211 | CWSP SPO - SH 08 | 37,646.000 | 0.000 | 08W | 2018 | # | OPEN | 920 | 131.4286 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 10824.51
35042417 | *TRSFR* 35052727 CWSP LG1106 LR6011*CANC | 05/30/2018 | 5409785 | 05/30/2018 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/28/2020 | ED.08202.1106.RECL | RECLOSERS | 043 | SANTA CLARA CO | 5535211 | CWSP SPO - SH 08 | 33,147.000 | 0.000 | 08W | 2018 | 08/05/2020 | 2020 | 798 | 114 | CLSD | 12 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | COMP | 2020-06-17 | 2020-06-17 | COMP | 2020-06-17 | 2020-06-17 | COMP | 2020-06-17 | 2020-06-17 | 0 | 43999 | 10567.82
35042421 | CWSP - MIWUK 1701 - LR 8050 | 05/29/2018 | 5408388 | 05/29/2018 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.16366.1701 | MIWUK 1701 | 055 | TUOLUMNE COUNT | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2018 | # | OPEN | 920 | 131.4286 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 14674.01
35042442 | RE-CON 3040 FT OF 4ACSR&1885 6CU W 2CU | 05/29/2018 | 114639867 | 05/29/2018 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 05/29/2020 | ED.18281.1102 | SISQUOC 1102 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2018 | # | OPEN | 920 | 131.4286 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 215.2
35042445 | RE-COND 5245 FT 4ACSR&3876 FT 6CU W2CU | 05/29/2018 | 114625626 | 05/22/2018 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/22/2020 | ED.18281.1102 | SISQUOC 1102 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2018 | # | OPEN | 920 | 131.4286 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 1983.28
35042603 | DIAMOND SPRINGS 1103 RECOND 18-0029738 | 06/01/2018 | 114628116 | 05/22/2018 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2019 | ED.15226.1103.SWIT | SWITCHES | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2018 | # | OPEN | 917 | 131 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35042612 | *CANC* CWSP-ORO FINO 1101 LR-2022 *CANC | 06/01/2018 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1101 | ORO FINO 1101 | 004 | BUTTE COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2018 | 05/03/2020 | 2020 | 702 | 100.2857 | CLSD | 12 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | 0 | 0 | 0
35042631 | *CANC*DO NOT USE* CWSP-VOLTA 1102-L*CANC | 05/31/2018 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/30/2020 | ED.10254.1102.RECL | RECLOSERS | 045 | SHASTA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2018 | 05/03/2020 | 2020 | 703 | 100.4286 | CLSD | 12 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | 0 | 0 | 0
35042647 | *TRSFR* 35052733 CWSP-BB 1101 - LR *CANC | 05/31/2018 | 5411107 | 05/31/2018 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/30/2020 | ED.76-K111800000.STRU.POLE | COAST K1118 POLES | 044 | SANTA CRUZ COU | 5535211 | CWSP SPO - SH 08 | 37,795.000 | 0.000 | 08W | 2018 | 08/05/2020 | 2020 | 797 | 113.8571 | CLSD | 12 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | COMP | 2020-06-17 | 2020-06-17 | COMP | 2020-06-17 | 2020-06-17 | COMP | 2020-06-17 | 2020-06-17 | 0 | 43999 | 3175.9
35042648 | *TRSFR* 35052734 CWSP-CE 2105 - LR *CANC | 05/31/2018 | 5411145 | 05/31/2018 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/30/2020 | ED.76-M131100000.STRU.POLE | COAST M1311 POLES | 044 | SANTA CRUZ COU | 5535211 | CWSP SPO - SH 08 | 39,547.000 | 0.000 | 08W | 2018 | 08/05/2020 | 2020 | 797 | 113.8571 | CLSD | 12 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | COMP | 2020-06-17 | 2020-06-17 | COMP | 2020-06-17 | 2020-06-17 | COMP | 2020-06-17 | 2020-06-17 | 0 | 43999 | 4556.84
35042719 | CWSP-AMGWIN STEEL POLE & TW DEMO PH | 05/31/2018 | 114652824 | 05/31/2018 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/31/2018 | ED.04343.2104 | SILVERADO 2104 | 028 | NAPA COUNTY | 5535211 | CWSP SPO - SH 08 | 2,125.000 | 1,275.000 | 08W | 2018 | 11/07/2020 | 2020 | 891 | 127.2857 | CLSD | 12 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2019-10-09 | 2019-10-09 | COMP | 2020-02-06 | 2020-02-06 | COMP | 2020-02-06 | 2020-02-06 | COMP | 2019-10-29 | 2020-04-10 | COMP | 2020-04-10 | 2020-04-15 | COMP | 2020-04-15 | 2020-04-21 | 120 | 75 | 1111957.9
35042893 | *CANC* CWSP - BURNS 2101 - OCB - PH*CANC | 06/04/2018 | 5416091 | 06/04/2018 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/30/2020 | ED.18358.2101 | BURNS 2101 | 044 | SANTA CRUZ COU | 5535211 | CWSP SPO - SH 08 | 19,348.000 | 0.000 | 08W | 2018 | 07/03/2020 | 2020 | 760 | 108.5714 | CLSD | 12 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | COMP | 2020-05-22 | 2020-05-22 | COMP | 2020-05-22 | 2020-05-22 | COMP | 2020-05-22 | 2020-05-22 | 0 | 43973 | 3741.17
35042920 | *CANC*DO NOT USE*2020 FAIRHAVEN 110*CANC | 06/04/2018 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/02/2020 | ED.19245.1103.SWIT | SWITCHES | 012 | HUMBOLDT COUNT | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2018 | 05/03/2020 | 2020 | 699 | 99.8571 | CLSD | 12 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | COMP | 2020-04-08 | 2020-04-08 | COMP | 2020-04-08 | 2020-04-08 | COMP | 2020-04-08 | 2020-04-08 | 0 | -25 | 0
35042921 | *CANC*DO NOT USE*2021 FAIRHAVEN 110*CANC | 06/04/2018 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/01/2021 | ED.19245.1103.SWIT | SWITCHES | 012 | HUMBOLDT COUNT | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2018 | 05/03/2020 | 2020 | 699 | 99.8571 | CLSD | 12 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | COMP | 2020-04-08 | 2020-04-08 | COMP | 2020-04-08 | 2020-04-08 | COMP | 2020-04-08 | 2020-04-08 | 0 | -25 | 0
35042922 | 2020 EEL RIVER 1102 DET WIRE TABLE BLUFF | 06/04/2018 | 114630202 | 05/23/2018 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/02/2020 | ED.19238.1102.SWIT | SWITCHES | 012 | HUMBOLDT COUNT | 5535457 | DO 08 - Monthly Forecast Only | 5,538.000 | 0.000 | 08J | 2018 | # | OPEN | 914 | 130.5714 | ESTS | 2 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 36138.58
35042923 | *CANC* CWSP-ORO FINO 1101-LR 2022 *CANC | 06/04/2018 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1101 | ORO FINO 1101 | 004 | BUTTE COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2018 | 05/03/2020 | 2020 | 699 | 99.8571 | CLSD | 12 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | 0 | 0 | 0
35043143 | *TRSFR* 35052728 CWSP LG1107 LR6009*CANC | 06/07/2018 | 5418973 | 06/07/2018 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/28/2020 | ED.08202.1107.RECL | RECLOSERS | 043 | SANTA CLARA CO | 5535211 | CWSP SPO - SH 08 | 40,128.000 | 0.000 | 08W | 2018 | 08/05/2020 | 2020 | 790 | 112.8571 | CLSD | 12 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | COMP | 2020-06-17 | 2020-06-17 | COMP | 2020-06-17 | 2020-06-17 | COMP | 2020-06-17 | 2020-06-17 | 0 | 43999 | 10439.21
35043245 | *CANC* CWSP-ORO FINO 1101 OCB PH 1 *CANC | 06/07/2018 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1101 | ORO FINO 1101 | 004 | BUTTE COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2018 | 05/03/2020 | 2020 | 696 | 99.4286 | CLSD | 12 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | 0 | 0 | 0
35043246 | *CANC* CWSP-ORO FINO 1101 OCB PH 2 *CANC | 06/07/2018 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1101 | ORO FINO 1101 | 004 | BUTTE COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2018 | 05/03/2020 | 2020 | 696 | 99.4286 | CLSD | 12 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | 0 | 0 | 0
35043247 | *CANC* CWSP-ORO FINO 1101 OCB PH 3 *CANC | 06/07/2018 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1101 | ORO FINO 1101 | 004 | BUTTE COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2018 | 05/03/2020 | 2020 | 696 | 99.4286 | CLSD | 12 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | 0 | 0 | 0
35043280 | *CANC*DO NOT USE*CWSP-PINE GROVE 11*CANC | 06/07/2018 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.16375.1102.RECL | RECLOSERS | 003 | AMADOR COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2018 | 05/03/2020 | 2020 | 696 | 99.4286 | CLSD | 12 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | COMP | 2020-04-08 | 2020-04-08 | COMP | 2020-04-08 | 2020-04-08 | COMP | 2020-04-08 | 2020-04-08 | 0 | -25 | 0
35043291 | OCGC CWSP- PINE GROVE 1102 LR9145 PH 1.1 | 06/07/2018 | 114631479 | 05/23/2018 | # | Not assigned | 30 | Technically Completed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2019 | JY | JUNK YARD FL TO HOLD DELETED DATA | 003 | AMADOR COUNTY | 5535211 | CWSP SPO - SH 08 | 14,920.000 | 14,872.000 | 08W | 2018 | # | OPEN | 911 | 130.1429 | FICL | 10 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | 35043291_CWSP - PINE GROVE 1102-LR 9145 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2019-12-20 | 2019-12-20 | COMP | 2019-12-22 | 2019-12-22 | COMP | 2019-12-22 | 2019-12-22 | COMP | 2019-12-22 | 2019-12-23 | COMP | 2019-12-23 | 2020-01-08 | COMP | 2020-01-08 | 2020-01-13 | 2 | 22 | 2740328.85
35043296 | WDDB - WILLOW CRK 1103 LR 3090 | 06/07/2018 | 112191208 | 11/29/2016 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/10/2018 | ED.19217.1103.SWIT | SWITCHES | 012 | HUMBOLDT COUNT | 5535211 | CWSP SPO - SH 08 | 6,722.000 | 0.000 | 08W | 2018 | # | OPEN | 911 | 130.1429 | UNSC | 6 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 70268.69
35043299 | CWSP-OH COND RPLC: EEL RIVER 1102 FU1907 | 06/07/2018 | 112402122 | 12/12/2016 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/10/2018 | ED.19238.1102 | EEL RIVER 1102 | 012 | HUMBOLDT COUNT | 5535211 | CWSP SPO - SH 08 | 6,500.000 | 6,376.000 | 08W | 2018 | # | OPEN | 911 | 130.1429 | ESTS | 2 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2019-11-27 | 2019-11-27 | INPR | 2020-02-18 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | -43796 | 0 | 1211548.41
35043303 | CWSP-OH COND RPLC: EEL RIVER 1102 FU1909 | 06/07/2018 | 113664014 | 10/04/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/25/2019 | ED.19238.1102 | EEL RIVER 1102 | 012 | HUMBOLDT COUNT | 5535211 | CWSP SPO - SH 08 | 8,003.000 | 8,140.000 | 08W | 2018 | # | OPEN | 911 | 130.1429 | DOCC | 8 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2019-09-19 | 2019-09-19 | INPR | 2019-09-23 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | -43727 | 0 | 1499183.34
35043304 | *CANC* 2019 OH COND RPLC: EEL RIVE *CANC | 06/07/2018 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/25/2019 | ED.35-X050000000.STRU.POLE | FORTUNA X05 POLES | 012 | HUMBOLDT COUNT | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2018 | 09/05/2019 | 2019 | 455 | 65 | CLSD | 12 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 2019-09-05 | 2019-09-05 | # | 2019-09-05 | 2019-09-05 | # | 2019-09-05 | 2019-09-05 | # | 2019-09-05 | 2019-09-05 | # | 2019-09-05 | 2019-09-05 | # | 2019-09-05 | 2019-09-05 | 0 | 0 | 0
35043311 | CWSP - MIWUK 1701- LR8060 | 06/08/2018 | 5420388 | 06/08/2018 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.16366.1701 | MIWUK 1701 | 055 | TUOLUMNE COUNT | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2018 | # | OPEN | 910 | 130 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 13053.23
35043381 | CWSP-MIWUK 1702-LR 6018-PHASE 1 | 06/11/2018 | 5426227 | 06/11/2018 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.16366.1702 | MIWUK 1702 | 055 | TUOLUMNE COUNT | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2018 | # | OPEN | 907 | 129.5714 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 8240.73
35043384 | CWSP-CURTIS 1705 - TS843 & 10590 | 06/11/2018 | 5426746 | 06/11/2018 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.16335.1705 | CURTIS 1705 | 055 | TUOLUMNE COUNT | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2018 | # | OPEN | 907 | 129.5714 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 13471.86
35043385 | *CANC* CWSP - TASSAJARA 2112 - FUS *CANC | 06/11/2018 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2019 | ED.01466.2112 | TASSAJARA 2112 | 007 | CONTRA COSTA C | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2018 | 10/03/2019 | 2019 | 479 | 68.4286 | CLSD | 12 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 2019-10-03 | 2019-10-03 | # | 2019-10-03 | 2019-10-03 | # | 2019-10-03 | 2019-10-03 | # | 2019-10-03 | 2019-10-03 | # | 2019-10-03 | 2019-10-03 | # | 2019-10-03 | 2019-10-03 | 0 | 0 | 0
35043421 | CWSP-WEST POINT 1101-OCB&LR12256 PH1.1 | 06/11/2018 | 114676761 | 06/08/2018 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/01/2020 | ED.16320.1101.RECL | RECLOSERS | 003 | AMADOR COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2018 | # | OPEN | 907 | 129.5714 | ESTS | 2 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - WEST POINT 1101 - LR 12256 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 32559.83
35043422 | CWSP - WEST POINT 1101 -LR 13444- PH 1.1 | 06/11/2018 | 114678720 | 06/08/2018 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/01/2020 | ED.16320.1101.RECL | RECLOSERS | 003 | AMADOR COUNTY | 5535211 | CWSP SPO - SH 08 | 11,926.000 | 0.000 | 08W | 2018 | # | OPEN | 907 | 129.5714 | ESTS | 2 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-WEST POINT 1101-LR 13444-PHASE 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 35766.02
35043423 | CWSP - WEST POINT 1101 -LR 13444- PH 2.1 | 06/11/2018 | 114678726 | 06/08/2018 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/01/2020 | ED.16320.1101.SWIT | SWITCHES | 003 | AMADOR COUNTY | 5535211 | CWSP SPO - SH 08 | 6,563.000 | 0.000 | 08W | 2018 | # | OPEN | 907 | 129.5714 | PEND | 5 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-WEST POINT 1101-LR 13444-PHASE 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 27043.55
35043586 | *CANC* PACIFICA 1102 WD: INS TREE W*CANC | 06/13/2018 | 114612631 | 05/17/2018 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2019 | ED.30-STLT | DIABLO DISTRICT STREETLIGHTS | 041 | SAN MATEO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2018 | 08/05/2020 | 2020 | 784 | 112 | CLSD | 12 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | INPR | 2019-03-08 | 2020-08-05 | INPR | 2019-03-08 | 2020-08-05 | INPR | 2019-03-08 | 2020-08-05 | INPR | 2019-01-03 | 2020-08-05 | # | 2020-08-05 | 2020-08-05 | # | 2020-08-05 | 2020-08-05 | 516 | 0 | 0
35043604 | CWSP - MIWUK 1702 - LR6018 - PHASE 2 | 06/14/2018 | 5429513 | 06/14/2018 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.16366.1702 | MIWUK 1702 | 055 | TUOLUMNE COUNT | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2018 | # | OPEN | 904 | 129.1429 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 5366.6
35043763 | *CANC* CWSP - MIDDLETOWN 1101-TS 1 *CANC | 06/15/2018 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/30/2020 | ED.04314.1101.SWIT | SWITCHES | 017 | LAKE COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2018 | 10/03/2019 | 2019 | 475 | 67.8571 | CLSD | 12 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 2019-10-03 | 2019-10-03 | # | 2019-10-03 | 2019-10-03 | # | 2019-10-03 | 2019-10-03 | # | 2019-10-03 | 2019-10-03 | # | 2019-10-03 | 2019-10-03 | # | 2019-10-03 | 2019-10-03 | 0 | 0 | 0
35043830 | CWSP - MIRABEL 02 /MONTE RIO 13 - LR 652 | 06/15/2018 | # | #N/A | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/15/2020 | ED.04209.1102.RECL | RECLOSERS | 049 | SONOMA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2018 | # | OPEN | 903 | 129 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 15875.77
35043949 | *CANC*DO NOT USE*CWSP-ORO FINO 1102*CANC | 06/20/2018 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1102 | ORO FINO 1102 | 004 | BUTTE COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2018 | 05/03/2020 | 2020 | 683 | 97.5714 | CLSD | 12 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | COMP | 2020-04-08 | 2020-04-08 | COMP | 2020-04-08 | 2020-04-08 | COMP | 2020-04-08 | 2020-04-08 | 0 | -25 | 0
35043950 | CWSP - MIWUK 1701 - LR 10600 | 06/20/2018 | 5435484 | 06/20/2018 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/01/2020 | ED.16366.1701 | MIWUK 1701 | 055 | TUOLUMNE COUNT | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2018 | # | OPEN | 898 | 128.2857 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 13104.96
35043952 | CWSP - MIWUK 1702 - LR 8090 | 06/20/2018 | 5435485 | 06/20/2018 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.16366.1702 | MIWUK 1702 | 055 | TUOLUMNE COUNT | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2018 | # | OPEN | 898 | 128.2857 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 5669.86
35043953 | *CANC* CWSP-ORO FINO 1102 LR-2560 *CANC | 06/20/2018 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1102 | ORO FINO 1102 | 004 | BUTTE COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2018 | 05/03/2020 | 2020 | 683 | 97.5714 | CLSD | 12 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | 0 | 0 | 0
35043954 | *CANC*DO NOT USE* CWSP-ORO FINO 110*CANC | 06/20/2018 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1102 | ORO FINO 1102 | 004 | BUTTE COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2018 | 05/03/2020 | 2020 | 683 | 97.5714 | CLSD | 12 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | COMP | 2020-04-08 | 2020-04-08 | COMP | 2020-04-08 | 2020-04-08 | COMP | 2020-04-08 | 2020-04-08 | 0 | -25 | 0
35043955 | *CANC*DO NOT USE* CWSP-ORO FINO 110*CANC | 06/20/2018 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1102 | ORO FINO 1102 | 004 | BUTTE COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2018 | 05/03/2020 | 2020 | 683 | 97.5714 | CLSD | 12 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | COMP | 2020-04-08 | 2020-04-08 | COMP | 2020-04-08 | 2020-04-08 | COMP | 2020-04-08 | 2020-04-08 | 0 | -25 | 0
35043956 | *CANC*DO NOT USE* CWSP-ORO FINO 110*CANC | 06/20/2018 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1102 | ORO FINO 1102 | 004 | BUTTE COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2018 | 05/03/2020 | 2020 | 683 | 97.5714 | CLSD | 12 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | COMP | 2020-04-08 | 2020-04-08 | COMP | 2020-04-08 | 2020-04-08 | COMP | 2020-04-08 | 2020-04-08 | 0 | -25 | 0
35043986 | *CANC*DO NOT USE*CWSP-PINE GROVE 11*CANC | 06/19/2018 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.16375.1102.RECL | RECLOSERS | 003 | AMADOR COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2018 | 05/03/2020 | 2020 | 684 | 97.7143 | CLSD | 12 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | COMP | 2020-04-08 | 2020-04-08 | COMP | 2020-04-08 | 2020-04-08 | COMP | 2020-04-08 | 2020-04-08 | 0 | -25 | 0
35043993 | CWSP - CAMPEVERS2105 - LR 74170 - 4KVPH4 | 06/19/2018 | 114677896 | 06/08/2018 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 11/30/2020 | ED.76-M1202B0000.STRU.POLE | COAST MAP M1202B POLES | 044 | SANTA CRUZ COU | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2018 | # | OPEN | 899 | 128.4286 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 9195.34
35043994 | CWSP - CAMP EVERS 2105 - LR 11384 ZONE | 06/19/2018 | 114678021 | 06/08/2018 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 11/30/2020 | ED.76-M132300000.STRU.POLE | COAST M1323 POLES | 044 | SANTA CRUZ COU | 5535211 | CWSP SPO - SH 08 | 45,408.000 | 0.000 | 08W | 2018 | # | OPEN | 899 | 128.4286 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 8268.03
35044115 | CWSP - ROB ROY 2105 - LR 5166 | 06/19/2018 | 114712175 | 06/19/2018 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/30/2020 | ED.76-O171100000.STRU.POLE | COAST O1711 POLES | 044 | SANTA CRUZ COU | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2018 | # | OPEN | 899 | 128.4286 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 7487.87
35044117 | CWSP: LOS GATOS 1107 - LR60092 PH 2 | 06/19/2018 | 114713255 | 06/19/2018 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/29/2020 | ED.08202.1107.RECL | RECLOSERS | 043 | SANTA CLARA CO | 5535211 | CWSP SPO - SH 08 | 46,464.000 | 0.000 | 08W | 2018 | # | OPEN | 899 | 128.4286 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 23320.04
35044284 | *CANC* CWSP-KONOCTI 1102-LR 532 *CANC | 06/21/2018 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/30/2020 | ED.04331.1102.SWIT | SWITCHES | 017 | LAKE COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2018 | 09/05/2019 | 2019 | 441 | 63 | CLSD | 12 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 2019-09-05 | 2019-09-05 | # | 2019-09-05 | 2019-09-05 | # | 2019-09-05 | 2019-09-05 | # | 2019-09-05 | 2019-09-05 | # | 2019-09-05 | 2019-09-05 | # | 2019-09-05 | 2019-09-05 | 0 | 0 | 0
35045959 | *CANC*DO NOT USE* CWSP-ORO FINO 110*CANC | 06/25/2018 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1101 | ORO FINO 1101 | 004 | BUTTE COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2018 | 05/03/2020 | 2020 | 678 | 96.8571 | CLSD | 12 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | COMP | 2020-04-08 | 2020-04-08 | COMP | 2020-04-08 | 2020-04-08 | COMP | 2020-04-08 | 2020-04-08 | 0 | -25 | 0
35046211 | CWSP - GARBERVILLE 1102 HENDRIX PILOT | 06/27/2018 | 114730956 | 06/26/2018 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/25/2019 | ED.19222.1102.SWIT | SWITCHES | 012 | HUMBOLDT COUNT | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2018 | # | OPEN | 891 | 127.2857 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 22547.14
35046276 | CWSP LOS GATOS 1107-LR60092 PH 3 | 06/27/2018 | 114720357 | 06/21/2018 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/29/2020 | ED.08202.1107.RECL | RECLOSERS | 043 | SANTA CLARA CO | 5535211 | CWSP SPO - SH 08 | 34,320.000 | 0.000 | 08W | 2018 | # | OPEN | 891 | 127.2857 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 13391.61
35046278 | CWSP LOS GATOS 1107-LR60092 PH 4 | 06/27/2018 | 114720429 | 06/21/2018 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/29/2020 | ED.08202.1107.RECL | RECLOSERS | 043 | SANTA CLARA CO | 5535211 | CWSP SPO - SH 08 | 41,615.000 | 0.000 | 08W | 2018 | # | OPEN | 891 | 127.2857 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 1943.01
35046279 | CWSP - LOS GATOS 1107-LR60092 PH 5 | 06/27/2018 | 114720434 | 06/21/2018 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/29/2020 | ED.08202.1107.RECL | RECLOSERS | 043 | SANTA CLARA CO | 5535211 | CWSP SPO - SH 08 | 40,656.000 | 0.000 | 08W | 2018 | # | OPEN | 891 | 127.2857 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 8861.7
35046280 | CWSP - LOS GATOS 1107 - LR60092 PH 6 | 06/27/2018 | 114720436 | 06/21/2018 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/29/2020 | ED.08202.1107.RECL | RECLOSERS | 043 | SANTA CLARA CO | 5535211 | CWSP SPO - SH 08 | 37,294.000 | 0.000 | 08W | 2018 | # | OPEN | 891 | 127.2857 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 3944.54
35046366 | *CANC* CWSP BRUNSWICK 1105 LR-1030*CANC | 06/28/2018 | 5448615 | 06/28/2018 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.15248.1105 | BRUNSWICK 1105 | 029 | NEVADA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2018 | 06/03/2020 | 2020 | 706 | 100.8571 | CLSD | 12 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | COMP | 2020-05-26 | 2020-05-26 | COMP | 2020-05-26 | 2020-05-26 | COMP | 2020-05-26 | 2020-05-26 | 0 | 43977 | 3845.93
35046371 | ECOP - STANISLAUS 1702 LR 37276 | 06/28/2018 | 114712085 | 06/19/2018 | # | Not assigned | 30 | Technically Completed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/01/2020 | ED.16282.1702 | STANISLAUS 1702 | 005 | CALAVERAS COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2018 | # | OPEN | 890 | 127.1429 | DCNL | Other | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 54741.1
35046383 | *CANC* CWSP - MIWUK 1701 LR11800 &*CANC | 06/28/2018 | 5449376 | 06/28/2018 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/01/2020 | ED.16366.1701 | MIWUK 1701 | 055 | TUOLUMNE COUNT | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2018 | 08/06/2019 | 2019 | 404 | 57.7143 | CLSD | 12 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | COMP | 2019-07-25 | 2019-07-25 | COMP | 2019-07-25 | 2019-07-25 | COMP | 2019-07-25 | 2019-07-25 | 0 | 43671 | 0
35046726 | *CANC* CWSP - LOS GATOS 1106 - LB4 *CANC | 07/03/2018 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/30/2020 | ED.08202.1106 | LOS GATOS 1106 | 043 | SANTA CLARA CO | 5535211 | CWSP SPO - SH 08 | 23,971.000 | 0.000 | 08W | 2018 | 09/05/2019 | 2019 | 429 | 61.2857 | CLSD | 12 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 2019-09-05 | 2019-09-05 | # | 2019-09-05 | 2019-09-05 | # | 2019-09-05 | 2019-09-05 | # | 2019-09-05 | 2019-09-05 | # | 2019-09-05 | 2019-09-05 | # | 2019-09-05 | 2019-09-05 | 0 | 0 | 0
35046759 | *CANC* CWSP - VOLTA 1102 - LR 1648 *CANC | 07/04/2018 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.10254.1102.RECL | RECLOSERS | 045 | SHASTA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2018 | 09/05/2019 | 2019 | 428 | 61.1429 | CLSD | 12 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 2019-09-05 | 2019-09-05 | # | 2019-09-05 | 2019-09-05 | # | 2019-09-05 | 2019-09-05 | # | 2019-09-05 | 2019-09-05 | # | 2019-09-05 | 2019-09-05 | # | 2019-09-05 | 2019-09-05 | 0 | 0 | 0
35046771 | MAXWELL 1102 RECOND LINE EXCESS SPLICES | 07/05/2018 | 114748560 | 07/02/2018 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/27/2021 | ED.06288.1102.SWIT | SWITCHES | 006 | COLUSA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2018 | # | OPEN | 883 | 126.1429 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35046793 | *CANC* CWSP-SALT SPRINGS 2102-LR31 *CANC | 07/06/2018 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.16369.2102.RECL | RECLOSERS | 005 | CALAVERAS COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2018 | 07/03/2019 | 2019 | 362 | 51.7143 | CLSD | 12 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 2019-07-03 | 2019-07-03 | # | 2019-07-03 | 2019-07-03 | # | 2019-07-03 | 2019-07-03 | COMP | 2019-06-20 | 2019-06-20 | COMP | 2019-06-20 | 2019-06-20 | COMP | 2019-06-20 | 2019-06-20 | 0 | -13 | 0
35046896 | *CANC* CWSP - FITCH MOUNTAIN 1113 *CANC | 07/06/2018 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.04275.1113.RECL | RECLOSERS | 049 | SONOMA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2018 | 09/05/2019 | 2019 | 426 | 60.8571 | CLSD | 12 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 2019-09-05 | 2019-09-05 | # | 2019-09-05 | 2019-09-05 | # | 2019-09-05 | 2019-09-05 | # | 2019-09-05 | 2019-09-05 | # | 2019-09-05 | 2019-09-05 | # | 2019-09-05 | 2019-09-05 | 0 | 0 | 0
35047143 | *CANC*DO NOT USE* CWSP - VOLTA 1102*CANC | 07/09/2018 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | JY | JUNK YARD FL TO HOLD DELETED DATA | 045 | SHASTA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2018 | 05/03/2020 | 2020 | 664 | 94.8571 | CLSD | 12 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | COMP | 2020-04-08 | 2020-04-08 | COMP | 2020-04-08 | 2020-04-08 | COMP | 2020-04-08 | 2020-04-08 | 0 | -25 | 0
35047146 | REDBUD 1101 RELOCATE FUSE 4865 IN T*CANC | 07/09/2018 | 114756833 | 07/06/2018 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/28/2018 | ED.04319.1101.SWIT | SWITCHES | 017 | LAKE COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2018 | 02/06/2020 | 2020 | 577 | 82.4286 | CLSD | 12 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 2020-02-06 | 2020-02-06 | # | 2020-02-06 | 2020-02-06 | # | 2020-02-06 | 2020-02-06 | # | 2020-02-06 | 2020-02-06 | # | 2020-02-06 | 2020-02-06 | # | 2020-02-06 | 2020-02-06 | 0 | 0 | 0
35047311 | CWSP - CAMP EVERS 2106 - 5020 - PHASE 1 | 07/11/2018 | 114758053 | 07/06/2018 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/30/2020 | ED.08362.2106 | CAMP EVERS 2106 | 044 | SANTA CRUZ COU | 5535211 | CWSP SPO - SH 08 | 46,834.000 | 0.000 | 08W | 2018 | # | OPEN | 877 | 125.2857 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 18211.06
35047312 | *CANC*CWSP-CAMP EVERS 2106 - 5020 P*CANC | 07/11/2018 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/30/2020 | ED.08362.2106 | CAMP EVERS 2106 | 044 | SANTA CRUZ COU | 5535211 | CWSP SPO - SH 08 | 42,528.000 | 0.000 | 08W | 2018 | 09/05/2019 | 2019 | 421 | 60.1429 | CLSD | 12 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 2019-09-05 | 2019-09-05 | # | 2019-09-05 | 2019-09-05 | # | 2019-09-05 | 2019-09-05 | # | 2019-09-05 | 2019-09-05 | # | 2019-09-05 | 2019-09-05 | # | 2019-09-05 | 2019-09-05 | 0 | 0 | 0
35047314 | CWSP - CAMPEVERS2105 - LR10294 - 4KV PH1 | 07/11/2018 | 114760861 | 07/09/2018 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/30/2020 | ED.08362.2105.RECL | RECLOSERS | 044 | SANTA CRUZ COU | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2018 | # | OPEN | 877 | 125.2857 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 7785.31
35047315 | CWSP: CAMPEVERS 2105 - LR11010 - 4KV PH2 | 07/11/2018 | 114760946 | 07/09/2018 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/30/2020 | ED.08362.2105.RECL | RECLOSERS | 044 | SANTA CRUZ COU | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2018 | # | OPEN | 877 | 125.2857 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 8980.88
35047316 | CWSP - CAMPEVERS2105 - LR 5206 - 4KV PH3 | 07/11/2018 | 114760990 | 07/09/2018 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/30/2020 | ED.08304.0401.RECL | RECLOSERS | 044 | SANTA CRUZ COU | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2018 | # | OPEN | 877 | 125.2857 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 9809.56
35047317 | CWSP - CAMPEVERS2105 - LR 5300 - 4KV PH7 | 07/11/2018 | 114760995 | 07/09/2018 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/30/2020 | ED.08305.0402.RECL | RECLOSERS | 044 | SANTA CRUZ COU | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2018 | # | OPEN | 877 | 125.2857 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 4737.11
35047318 | CWSP - CAMPEVERS2105 - BT402CB - 4KV PH6 | 07/11/2018 | 114761016 | 07/09/2018 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/30/2020 | ED.08305.0402.CAPA | CAPACITORS | 044 | SANTA CRUZ COU | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2018 | # | OPEN | 877 | 125.2857 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 5576.75
35047402 | *CANC* CWSP-SALT SPRINGS 2102-LR31 *CANC | 07/11/2018 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.16369.2102.RECL | RECLOSERS | 005 | CALAVERAS COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2018 | 07/03/2019 | 2019 | 357 | 51 | CLSD | 12 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 2019-07-03 | 2019-07-03 | # | 2019-07-03 | 2019-07-03 | # | 2019-07-03 | 2019-07-03 | COMP | 2019-06-20 | 2019-06-20 | COMP | 2019-06-20 | 2019-06-20 | COMP | 2019-06-20 | 2019-06-20 | 0 | -13 | 0
35047414 | *CANC* CWSP - PARADISE 1106 - OCB *CANC | 07/11/2018 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2019 | ED.10283.1106.SWIT | SWITCHES | 004 | BUTTE COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2018 | 09/05/2019 | 2019 | 421 | 60.1429 | CLSD | 12 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 2019-09-05 | 2019-09-05 | # | 2019-09-05 | 2019-09-05 | # | 2019-09-05 | 2019-09-05 | # | 2019-09-05 | 2019-09-05 | # | 2019-09-05 | 2019-09-05 | # | 2019-09-05 | 2019-09-05 | 0 | 0 | 0
35047418 | *CANC*DO NOT USE* CWSP-EL DORADO PH*CANC | 07/11/2018 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2019 | ED.15276.2102.SWIT | SWITCHES | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2018 | 05/03/2020 | 2020 | 662 | 94.5714 | CLSD | 12 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | COMP | 2020-04-08 | 2020-04-08 | COMP | 2020-04-08 | 2020-04-08 | COMP | 2020-04-08 | 2020-04-08 | 0 | -25 | 0
35047419 | *CANC*CWSP-SHINGLE SPRINGS 2109-LR *CANC | 07/11/2018 | 114742520 | 06/29/2018 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2019 | ED.15365.2109.SWIT | SWITCHES | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2018 | 07/03/2020 | 2020 | 723 | 103.2857 | CLSD | 12 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 2020-07-03 | 2020-07-03 | # | 2020-07-03 | 2020-07-03 | # | 2020-07-03 | 2020-07-03 | COMP | 2018-12-19 | 2018-12-19 | COMP | 2018-12-19 | 2018-12-19 | COMP | 2018-12-19 | 2018-12-19 | 0 | -562 | 2474
35047420 | CWSP - BRUNSWICK 1106 - LR 51486 | 07/11/2018 | 114742521 | 06/29/2018 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2019 | ED.15248.1106.SWIT | SWITCHES | 029 | NEVADA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2018 | # | OPEN | 877 | 125.2857 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 10117.41
35047422 | CWSP - PLACERVILLE 2106 - LR 1104 | 07/11/2018 | 114742525 | 06/29/2018 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2019 | ED.15308.2106.SWIT | SWITCHES | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2018 | # | OPEN | 877 | 125.2857 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35047429 | CWSP - WILLITS 1104 - LR 34008 PH 1 | 07/11/2018 | 114742614 | 06/29/2018 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2019 | ED.04266.1104.SWIT | SWITCHES | 023 | MENDOCINO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2018 | # | OPEN | 877 | 125.2857 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 12642.73
35047557 | *CANCEL*CWSP-BRUNSWICK 1105 LR-32536 | 07/12/2018 | # | #N/A | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.15248.1105 | BRUNSWICK 1105 | 029 | NEVADA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2018 | # | OPEN | 876 | 125.1429 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 11593.27
35047601 | ECOP-BRUNSWICK 1105-H01-LR32536 ZONE PH2 | 07/13/2018 | 114780214 | 07/12/2018 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.15248.1105 | BRUNSWICK 1105 | 029 | NEVADA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2018 | # | OPEN | 875 | 125 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 19712.7
35048009 | CWSP - APPLE HILL 2102 LR97982 HARDENING | 07/18/2018 | 114790791 | 07/16/2018 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/16/2020 | ED.15366.2102.RECL | RECLOSERS | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2018 | # | OPEN | 870 | 124.2857 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35048011 | *CANC* CWSP - EL DORADO PH 2101 LR | 07/18/2018 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.15276.2101.SWIT | SWITCHES | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2018 | 09/05/2019 | 2019 | 414 | 59.1429 | CLSD | 12 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 2019-09-05 | 2019-09-05 | # | 2019-09-05 | 2019-09-05 | # | 2019-09-05 | 2019-09-05 | # | 2019-09-05 | 2019-09-05 | # | 2019-09-05 | 2019-09-05 | # | 2019-09-05 | 2019-09-05 | 0 | 0 | 0
35048058 | *CANC* CWSP-COLUMBIA HILL 1101-LR | 07/19/2018 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 11/30/2020 | ED.15247.1101.SWIT | SWITCHES | 029 | NEVADA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2018 | 09/05/2019 | 2019 | 413 | 59 | CLSD | 12 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 2019-09-05 | 2019-09-05 | # | 2019-09-05 | 2019-09-05 | # | 2019-09-05 | 2019-09-05 | # | 2019-09-05 | 2019-09-05 | # | 2019-09-05 | 2019-09-05 | # | 2019-09-05 | 2019-09-05 | 0 | 0 | 0
35048278 | STCKTN STATION A 1107 RECONDUCTOR 1 SPAN | 07/20/2018 | 114806289 | 07/20/2018 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/30/2021 | ED.93-V101400000.STRU.POLE | STOCKTON V1014 POLES | 039 | SAN JOAQUIN CO | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2018 | # | OPEN | 868 | 124 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 1085.38
35048483 | RPL OH COND. SALINAS 1104 18-0056961 | 07/24/2018 | 114809445 | 07/23/2018 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2021 | ED.05-H081400000.STRU.POLE | SALINAS H0814 POLES | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 2,516.000 | 0.000 | 08J | 2018 | # | OPEN | 864 | 123.4286 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 4116.88
35048613 | CWSP - PARADISE 1106 - LR 2084 | 07/25/2018 | 114819461 | 07/25/2018 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.10283.1106 | PARADISE 1106 | 004 | BUTTE COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2018 | # | OPEN | 863 | 123.2857 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 11828.05
35048675 | REPL ANNEALED COND SON 1105 NAPA RD*CANC | 07/25/2018 | 114971059 | 09/13/2018 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/02/2018 | ED.44-MM35130000.STRU.POLE | SANTA ROSA MM3513 POLES | 049 | SONOMA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2018 | 12/04/2019 | 2019 | 497 | 71 | CLSD | 12 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2019-12-04 | 2019-12-04 | # | 2019-12-04 | 2019-12-04 | # | 2019-12-04 | 2019-12-04 | # | 2019-12-04 | 2019-12-04 | # | 2019-12-04 | 2019-12-04 | # | 2019-12-04 | 2019-12-04 | 0 | 0 | 0
35048678 | ECOP-BRUNSWICK 1105-H01-LR32536 ZONE PH3 | 07/25/2018 | 114819747 | 07/25/2018 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.15248.1105 | BRUNSWICK 1105 | 029 | NEVADA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2018 | # | OPEN | 863 | 123.2857 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 14086.07
35049537 | CWSP - BIG BASIN 1102 - 9741 | 07/31/2018 | 114832083 | 07/30/2018 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/30/2020 | ED.08284.1102 | BIG BASIN 1102 | 043 | SANTA CLARA CO | 5535211 | CWSP SPO - SH 08 | 29,386.000 | 0.000 | 08W | 2018 | # | OPEN | 857 | 122.4286 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 5617.41
35049538 | CWSP - BIG BASIN 1102 - 12758 | 07/31/2018 | 114832089 | 07/30/2018 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/30/2020 | ED.08284.1102 | BIG BASIN 1102 | 043 | SANTA CLARA CO | 5535211 | CWSP SPO - SH 08 | 44,088.000 | 0.000 | 08W | 2018 | # | OPEN | 857 | 122.4286 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 8388.56
35049913 | *CANC* CWSP - BRUNSWICK 1103 LR220 | 07/29/2018 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.15248.1103.RECL | RECLOSERS | 029 | NEVADA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2018 | 09/05/2019 | 2019 | 403 | 57.5714 | CLSD | 12 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 2019-09-05 | 2019-09-05 | # | 2019-09-05 | 2019-09-05 | # | 2019-09-05 | 2019-09-05 | # | 2019-09-05 | 2019-09-05 | # | 2019-09-05 | 2019-09-05 | # | 2019-09-05 | 2019-09-05 | 0 | 0 | 0
35050942 | CWSP: GARBERVILLE 1101 HENDRIX PILOT | 08/02/2018 | 114848297 | 08/02/2018 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/25/2019 | ED.19222.1101.SWIT | SWITCHES | 012 | HUMBOLDT COUNT | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2018 | # | OPEN | 855 | 122.1429 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 12111.11
35050945 | CWSP - BRUNSWICK 1106 - 2143 | 08/02/2018 | 114848718 | 08/02/2018 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.15248.1106 | BRUNSWICK 1106 | 029 | NEVADA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2018 | # | OPEN | 855 | 122.1429 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 8324.37
35050947 | CWSP - BRUNSWICK 1106 - 2794 - PH 1 | 08/02/2018 | 114848737 | 08/02/2018 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.15248.1106 | BRUNSWICK 1106 | 029 | NEVADA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2018 | # | OPEN | 855 | 122.1429 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 11345.91
35050949 | CWSP - BRUNSWICK 1106 - 2794 - PH 2 | 08/02/2018 | 114848761 | 08/02/2018 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.15248.1106 | BRUNSWICK 1106 | 029 | NEVADA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2018 | # | OPEN | 855 | 122.1429 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 10092.63
35050950 | CWSP - BRUNSWICK 1106 - 2794 - PH 3 | 08/02/2018 | 114848764 | 08/02/2018 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.15248.1106 | BRUNSWICK 1106 | 029 | NEVADA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2018 | # | OPEN | 855 | 122.1429 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 5245.58
35050951 | CWSP: MONTE RIO 1113 HENDRIX CABLE | 08/02/2018 | 114848376 | 08/02/2018 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2019 | ED.04281.1113.SWIT | SWITCHES | 049 | SONOMA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2018 | # | OPEN | 855 | 122.1429 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 22359.67
35051252 | CWSP - PLACERVILLE 2106 - LR 1104 | 08/08/2018 | 114863777 | 08/08/2018 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.15308.2106 | PLACERVILLE 2106 | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2018 | # | OPEN | 849 | 121.2857 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 65.66
35051253 | R2 RECONDUCT DOLAN RD 1101 WD#16-0065306 | 08/08/2018 | 114838762 | 07/31/2018 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2018 | JY | JUNK YARD FL TO HOLD DELETED DATA | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 2,751.000 | 2,751.000 | 08J | 2018 | # | OPEN | 849 | 121.2857 | DOCC | 8 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2020-06-12 | 2020-06-12 | COMP | 2020-06-26 | 2020-06-26 | COMP | 2020-06-26 | 2020-06-26 | COMP | 2020-08-17 | 2020-09-03 | COMP | 2020-09-03 | 2020-11-04 | COMP | 2020-11-04 | 2020-11-04 | 14 | 131 | 348493.61
35051268 | CWSP - WILLITS 1104 - LR 34008 - PH 2 | 08/07/2018 | 114848768 | 08/02/2018 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.04266.1104 | WILLITS 1104 | 023 | MENDOCINO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2018 | # | OPEN | 850 | 121.4286 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 12067.32
35051356 | CWSP - EL DORADO PH 2101 LR 26000 PH 2 | 08/08/2018 | 114861944 | 08/07/2018 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.15276.2101.SWIT | SWITCHES | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2018 | # | OPEN | 849 | 121.2857 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 3785.66
35051472 | CWSP - CAMP EVERS 2106 - LR5020 - PH 3 | 08/08/2018 | 114865601 | 08/08/2018 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/30/2020 | ED.08362.2106 | CAMP EVERS 2106 | 044 | SANTA CRUZ COU | 5532479 | CWSP 08W - Monthly Forecast Only | 38,478.000 | 0.000 | 08W | 2018 | # | OPEN | 849 | 121.2857 | ESTS | 2 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 23388.97
35051484 | CWSP - MONTE RIO 1113 - 8299 | 08/08/2018 | 114779852 | 07/12/2018 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 11/01/2020 | ED.04281.1113.SWIT | SWITCHES | 049 | SONOMA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2018 | # | OPEN | 849 | 121.2857 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 9762.69
35051485 | CWSP - MONTE RIO 1111 - 1701 | 08/08/2018 | 114779853 | 07/12/2018 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 11/01/2020 | ED.04281.1111.SWIT | SWITCHES | 049 | SONOMA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2018 | # | OPEN | 849 | 121.2857 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 11084.44
35052117 | ZAMORA 1105 WIRE DOWN LR 36762 | 08/13/2018 | 114870756 | 08/09/2018 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 10/01/2021 | ED.06319.1105.RECL | RECLOSERS | 057 | YOLO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2018 | # | OPEN | 844 | 120.5714 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35052121 | *CANC* ZAMORA 1105 WIRE DOWN LR 36762 | 08/10/2018 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 10/01/2021 | ED.06319.1105.RECL | RECLOSERS | 057 | YOLO COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2018 | 08/25/2018 | 2018 | 15 | 2.1429 | CLSD | 12 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 2018-08-25 | 2018-08-25 | # | 2018-08-25 | 2018-08-25 | # | 2018-08-25 | 2018-08-25 | # | 2018-08-25 | 2018-08-25 | # | 2018-08-25 | 2018-08-25 | # | 2018-08-25 | 2018-08-25 | 0 | 0 | 0
35052128 | *CANC*DO NOT USE* CWSP-STANISLAUS17*CANC | 08/10/2018 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.16282.1702 | STANISLAUS 1702 | 005 | CALAVERAS COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2018 | 05/03/2020 | 2020 | 632 | 90.2857 | CLSD | 12 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | COMP | 2020-04-08 | 2020-04-08 | COMP | 2020-04-08 | 2020-04-08 | COMP | 2020-04-08 | 2020-04-08 | 0 | -25 | 0
35052129 | *CANC*DO NOT USE*CWSP-STANISLAUS170*CANC | 08/10/2018 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.16282.1702 | STANISLAUS 1702 | 005 | CALAVERAS COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2018 | 05/03/2020 | 2020 | 632 | 90.2857 | CLSD | 12 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | COMP | 2020-04-08 | 2020-04-08 | COMP | 2020-04-08 | 2020-04-08 | COMP | 2020-04-08 | 2020-04-08 | 0 | -25 | 0
35052327 | CWSP-PARADISE 1101 OCB ZONE | 08/15/2018 | 114884306 | 08/13/2018 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.10283.1101 | PARADISE 1101 | 004 | BUTTE COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2018 | # | OPEN | 842 | 120.2857 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 2807.79
35052328 | CALISTOGA 1101 WIRE DOWN 18-0052856 | 08/15/2018 | 114883275 | 08/13/2018 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.42-FF29000000.STRU.POLE | SILVERADO MAP FF29 POLES | 028 | NAPA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2018 | # | OPEN | 842 | 120.2857 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 1067.66
35052329 | HIGHWAY 1105 WIRE DOWN 18-0060061 | 08/15/2018 | 114883350 | 08/13/2018 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2021 | ED.42-OO39000000.STRU.POLE | SILVERADO OO39 POLES | 028 | NAPA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 2,809.000 | 0.000 | 08J | 2018 | # | OPEN | 842 | 120.2857 | PEND | 5 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 13406.05
35052718 | OCGC CWSP: ANGWIN OH TO UG DEMO - PH 2 | 08/16/2018 | 114895341 | 08/16/2018 | # | Not assigned | 40 | Closed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2018 | ED.04343.2104 | SILVERADO 2104 | 028 | NAPA COUNTY | 5535211 | CWSP SPO - SH 08 | 2,742.000 | 2,265.000 | 08W | 2018 | 04/26/2020 | 2020 | 619 | 88.4286 | CLSD | 12 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2019-07-24 | 2019-07-24 | COMP | 2019-10-29 | 2019-10-29 | COMP | 2019-10-29 | 2019-10-29 | COMP | 2019-10-29 | 2019-10-30 | COMP | 2019-10-30 | 2019-11-08 | COMP | 2019-11-08 | 2019-11-12 | 97 | 14 | 904843.05
35052726 | CWSP - LOS GATOS 1106 LR 60116 PH1 | 08/17/2018 | 114623448 | 05/21/2018 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 06/28/2020 | ED.08202.1106.RECL | RECLOSERS | 043 | SANTA CLARA CO | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2018 | # | OPEN | 840 | 120 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 25702.53
35052727 | CWSP LOS GATOS 1106 LR 1106 PHASE 2 | 08/17/2018 | 114642563 | 05/29/2018 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 06/28/2020 | ED.08202.1106.RECL | RECLOSERS | 043 | SANTA CLARA CO | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2018 | # | OPEN | 840 | 120 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 7675.84
35052728 | CWSP - LOS GATOS 1107 LR 60092 PH1 | 08/17/2018 | 114670659 | 06/06/2018 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 06/28/2020 | ED.08202.1107.RECL | RECLOSERS | 043 | SANTA CLARA CO | 5535211 | CWSP SPO - SH 08 | 40,128.000 | 0.000 | 08W | 2018 | # | OPEN | 840 | 120 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 11391.71
35052729 | CWSP - BURNS 2101 - PH 1 | 08/17/2018 | 114573040 | 05/07/2018 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 06/28/2020 | ED.18358.2101.SWIT | SWITCHES | 044 | SANTA CRUZ COU | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2018 | # | OPEN | 840 | 120 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 10587.05
35052730 | CWSP - BURNS 2101- PH 2 | 08/17/2018 | 114661267 | 06/04/2018 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 06/30/2020 | ED.18358.2101 | BURNS 2101 | 044 | SANTA CRUZ COU | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2018 | # | OPEN | 840 | 120 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 2641.44
35052731 | CWSP - BIG BASIN 1101 - 10296 - PH 1.1 | 08/17/2018 | 114607365 | 05/15/2018 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 09/30/2020 | ED.76-L110300000.STRU.POLE | COAST L1103 POLES | 044 | SANTA CRUZ COU | 5535211 | CWSP SPO - SH 08 | 7,779.000 | 0.000 | 08W | 2018 | # | OPEN | 840 | 120 | UNSC | 6 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BIG BASIN 1101 - LR 10296 - PH1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 127116.36
35052732 | CWSP - BIG BASIN 1101 5028 ZONE | 08/17/2018 | 114623764 | 05/21/2018 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 11/30/2020 | ED.76-L110300000.STRU.POLE | COAST L1103 POLES | 044 | SANTA CRUZ COU | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2018 | # | OPEN | 840 | 120 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 7839.57
35052733 | CWSP - BIG BASIN 1101 - 10296 ZONE PH2 | 08/17/2018 | 114646897 | 05/30/2018 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 11/30/2020 | ED.76-K111800000.STRU.POLE | COAST K1118 POLES | 044 | SANTA CRUZ COU | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2018 | # | OPEN | 840 | 120 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 2627.41
35052734 | CWSP - CAMP EVERS 2105 - LR 5232-33542 | 08/17/2018 | 114646899 | 05/30/2018 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 11/30/2020 | ED.76-M131100000.STRU.POLE | COAST M1311 POLES | 044 | SANTA CRUZ COU | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2018 | # | OPEN | 840 | 120 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 8466.87
35052735 | CWSP - MIWUK 1701 - LR 10600 PH 1.1 | 08/17/2018 | 114706118 | 06/15/2018 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 05/03/2021 | ED.16366.1701 | MIWUK 1701 | 055 | TUOLUMNE COUNT | 5535211 | CWSP SPO - SH 08 | 10,641.000 | 0.000 | 08W | 2018 | # | OPEN | 840 | 120 | UNSC | 6 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - MIWUK 1701 - LR 10600 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 161151.8
35052736 | CWSP - MIWUK 1701 LR11800 | 08/17/2018 | 114708583 | 06/18/2018 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/01/2020 | ED.16366.1701 | MIWUK 1701 | 055 | TUOLUMNE COUNT | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2018 | # | OPEN | 840 | 120 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-MIWUK 1701 LR11800 & 79118 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 22892.66
35052737 | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 | 08/17/2018 | 114675474 | 06/07/2018 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 07/12/2021 | ED.16366.1701 | MIWUK 1701 | 055 | TUOLUMNE COUNT | 5535211 | CWSP SPO - SH 08 | 8,378.000 | 0.000 | 08W | 2018 | # | OPEN | 840 | 120 | PEND | 5 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | MIWUK 1701 LR8060 08W WILDFIRE HARDENING | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 65909.57
35052738 | CWSP-CURTIS1705-TS843-PHASE1 | 08/17/2018 | 114688224 | 06/11/2018 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.16335.1705 | CURTIS 1705 | 055 | TUOLUMNE COUNT | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2018 | # | OPEN | 840 | 120 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35052739 | CWSP - MIWUK 1702 - LR 38218 - PH 1.1 | 08/17/2018 | 114567186 | 05/04/2018 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 01/07/2021 | ED.16366.1702 | MIWUK 1702 | 055 | TUOLUMNE COUNT | 5535211 | CWSP SPO - SH 08 | 11,546.000 | 0.000 | 08W | 2018 | # | OPEN | 840 | 120 | CONS | 7 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - MIWUK 1702_LR38218 WILDFIRE HARDE | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 190840.67
35052820 | CWSP - MIWUK 1702 - OCB - PH 1.1 | 08/17/2018 | 114580704 | 05/08/2018 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.16366.1702 | MIWUK 1702 | 055 | TUOLUMNE COUNT | 5535211 | CWSP SPO - SH 08 | 10,392.000 | 10,392.000 | 08W | 2018 | # | OPEN | 840 | 120 | FICL | 10 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - MIWUK 1702_OCB WILDFIRE HARDENING | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2020-08-04 | 2020-08-04 | COMP | 2020-08-08 | 2020-08-08 | COMP | 2020-08-08 | 2020-08-11 | COMP | 2020-08-11 | 2020-11-04 | COMP | 2020-11-04 | 2020-11-30 | COMP | 2020-11-30 | 2020-11-30 | 7 | 111 | 1793038.39
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 | 08/17/2018 | 114593976 | 05/10/2018 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.16366.1701 | MIWUK 1701 | 055 | TUOLUMNE COUNT | 5535211 | CWSP SPO - SH 08 | 10,953.000 | 0.000 | 08W | 2018 | # | OPEN | 840 | 120 | CONS | 7 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - MIWUK 1701_OCB WILDFIRE HARDENING | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | INPR | 2020-08-24 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 540121.28
35052822 | CWSP - MIWUK 1701 - LR 8050 | 08/17/2018 | 114637561 | 05/25/2018 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.16366.1701 | MIWUK 1701 | 055 | TUOLUMNE COUNT | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 2018 | # | OPEN | 840 | 120 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 597.71
35052823 | CWSP - MIWUK 1702 - LR 6018 - PH 1.1 | 08/17/2018 | 114678857 | 06/08/2018 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.16366.1702 | MIWUK 1702 | 055 | TUOLUMNE COUNT | 5535211 | CWSP SPO - SH 08 | 8,000.000 | 0.000 | 08W | 2018 | # | OPEN | 840 | 120 | UNSC | 6 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - MIWUK 1702-LR 6018-PHASE 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 34884.31
35052824 | CWSP - MIWUK 1702 - LR6018 - PH 2 | 08/17/2018 | 114697826 | 06/13/2018 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.16366.1702 | MIWUK 1702 | 055 | TUOLUMNE COUNT | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2018 | # | OPEN | 840 | 120 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-MIWUK 1702-LR6018-PHASE 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 225.71
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 | 08/17/2018 | 114701195 | 06/14/2018 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.16366.1702 | MIWUK 1702 | 055 | TUOLUMNE COUNT | 5535211 | CWSP SPO - SH 08 | 6,168.000 | 0.000 | 08W | 2018 | # | OPEN | 840 | 120 | CONS | 7 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-MIWUK 1702-LR 8090 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 430906.29
35052976 | WD-EIGHT MILE2101-CO738931-ILS 180066835 | 08/22/2018 | 114910937 | 08/22/2018 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2021 | ED.16391.2101 | EIGHT MILE 2101 | 039 | SAN JOAQUIN CO | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2018 | # | OPEN | 835 | 119.2857 | PEND | 5 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 33039.49
35053033 | CWSP - TASSAJARA 2112 - FUSE 18053 | 08/20/2018 | 114688204 | 06/11/2018 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2019 | ED.01466.2112 | TASSAJARA 2112 | 007 | CONTRA COSTA C | 5535211 | CWSP SPO - SH 08 | 31,276.000 | 31,276.000 | 08W | 2018 | # | OPEN | 837 | 119.5714 | CONS | 7 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - TASSAJARA 2112 - FUSE 18053 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 7626876.53
35053154 | PN RECONDUCTOR OVER HWY 101 S/O KEHOE | 08/22/2018 | 114909739 | 08/21/2018 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 02/05/2019 | ED.02401.1104.SWIT | SWITCHES | 041 | SAN MATEO COUN | 5505513 | PN-OH ANNEALED/DETER CNDCTR: PM MGD | 750.000 | 743.000 | 08J | 2018 | 01/11/2020 | 2020 | 507 | 72.4286 | CLSD | 12 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2019-03-24 | 2019-03-24 | COMP | 2019-04-03 | 2019-04-03 | COMP | 2019-04-03 | 2019-04-03 | COMP | 2019-04-03 | 2019-04-04 | COMP | 2019-04-04 | 2019-04-09 | COMP | 2019-04-09 | 2019-04-09 | 10 | 6 | 229361
35053429 | CWSP HALF MOON BAY 1102 FUCO 12457 | 08/28/2018 | 114921419 | 08/27/2018 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/09/2021 | ED.02410.1102.TXFR.TROH | OVERHEAD TRANSFORMERS | 041 | SAN MATEO COUN | 5535211 | CWSP SPO - SH 08 | 5,597.000 | 0.000 | 08W | 2018 | # | OPEN | 829 | 118.4286 | UNSC | 6 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 87743.47
35053430 | HALF MOON BAY 1101 WIRE REPLACET FCO4141 | 08/28/2018 | 114921459 | 08/27/2018 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2019 | ED.02410.1101.TXFR.TROH | OVERHEAD TRANSFORMERS | 041 | SAN MATEO COUN | 5505513 | PN-OH ANNEALED/DETER CNDCTR: PM MGD | 0.000 | 0.000 | 08J | 2018 | # | OPEN | 829 | 118.4286 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35053651 | RPL OH COND. SALINAS 1107 18-0066956 | 08/29/2018 | 114921397 | 08/27/2018 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/30/2021 | ED.05-H091000000.STRU.POLE | SALINAS H0910 POLES | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 3,685.000 | 0.000 | 08J | 2018 | # | OPEN | 828 | 118.2857 | PEND | 5 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 35053651 RPL OH COND. SALINAS 1107 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 50357.32
35054184 | CWSP-COLUMBIA HILL 1101-TS 8233 | 09/05/2018 | 114941996 | 09/05/2018 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 11/30/2020 | ED.15247.1101.SWIT | SWITCHES | 029 | NEVADA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2018 | # | OPEN | 821 | 117.2857 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 3728.88
35054545 | 08J SAN MATEO 2101 WIREDOWN | 09/10/2018 | 114945781 | 09/06/2018 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/29/2019 | ED.02419.2101.TXFR.TROH | OVERHEAD TRANSFORMERS | 041 | SAN MATEO COUN | 5505513 | PN-OH ANNEALED/DETER CNDCTR: PM MGD | 0.000 | 0.000 | 08J | 2018 | # | OPEN | 816 | 116.5714 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 1999.82
35054821 | RPL OH COND.RESERVATION RD.1102 18-69362 | 09/12/2018 | 114946509 | 09/06/2018 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/30/2021 | ED.05-H080000000.STRU.POLE | SALINAS H08 POLES | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 2,830.000 | 0.000 | 08J | 2018 | # | OPEN | 814 | 116.2857 | PEND | 5 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 35054821 RPL OH COND.RESERVATION RD | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 45736.44
35056195 | WD - OCEANO 1102 - 8635 ZONE RECOND | 09/21/2018 | 114988155 | 09/20/2018 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/30/2021 | ED.01-SS35050000.STRU.POLE | SANTA MARIA SS3505 POLES | 040 | SAN LUIS OBISP | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2018 | # | OPEN | 805 | 115 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 1717.58
35056269 | AIRWAYS 1105-RECOND 1,520 FT OF 2 ACSR | 09/19/2018 | 114982085 | 09/18/2018 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/31/2021 | ED.25204.1105 | AIRWAYS 1105 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2018 | # | OPEN | 807 | 115.2857 | PEND | 5 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 20930.95
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | 09/20/2018 | 114985530 | 09/19/2018 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.15308.2106 | PLACERVILLE 2106 | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2018 | # | OPEN | 806 | 115.1429 | ESTS | 2 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Placerville 2106 - LR 1104 - Ph 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 23921.09
35056433 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 2 | 09/20/2018 | 114985551 | 09/19/2018 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.15308.2106 | PLACERVILLE 2106 | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2018 | # | OPEN | 806 | 115.1429 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Placerville 2106 - LR 1104 - Phas | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 20865.44
35056434 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 3 | 09/20/2018 | 114985557 | 09/19/2018 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.15308.2106 | PLACERVILLE 2106 | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2018 | # | OPEN | 806 | 115.1429 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-PLACERVILLE 2106 LR1104 PH 3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 16804.36
35056435 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 4 | 09/20/2018 | 114985560 | 09/19/2018 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.15308.2106 | PLACERVILLE 2106 | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2018 | # | OPEN | 806 | 115.1429 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-PLACERVILLE 2106 LR1104 PH 4 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 17277.46
35056438 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 5 | 09/20/2018 | 114985561 | 09/19/2018 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.15308.2106 | PLACERVILLE 2106 | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2018 | # | OPEN | 806 | 115.1429 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-PLACERVILLE 2106 LR1104 PH 5 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 12813.39
35056439 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 6 | 09/20/2018 | 114985621 | 09/19/2018 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.15308.2106 | PLACERVILLE 2106 | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2018 | # | OPEN | 806 | 115.1429 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-PLACERVILLE 2106 LR1104 PH 6 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 11884.89
35056666 | *CANC* EST HILL 1101 LR 50486 HARDENING | 09/24/2018 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 09/20/2020 | ED.15218.1101.RECL | RECLOSERS | 031 | PLACER COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2018 | 09/29/2018 | 2018 | 5 | 0.71429 | CLSD | 12 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 2018-09-29 | 2018-09-29 | # | 2018-09-29 | 2018-09-29 | # | 2018-09-29 | 2018-09-29 | # | 2018-09-29 | 2018-09-29 | # | 2018-09-29 | 2018-09-29 | # | 2018-09-29 | 2018-09-29 | 0 | 0 | 0
35056732 | CWSP FOREST HILL 1101 LR 50486 HARDENING | 09/25/2018 | 114988838 | 09/20/2018 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 09/20/2020 | ED.15218.1101.RECL | RECLOSERS | 031 | PLACER COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2018 | # | OPEN | 801 | 114.4286 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-FOREST HILL 1101 - LR 50486 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 2972.17
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | 09/25/2018 | 114987201 | 09/20/2018 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/30/2020 | ED.15276.2101 | EL DORADO PH 2101 | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 8,064.000 | 0.000 | 08W | 2018 | # | OPEN | 801 | 114.4286 | PEND | 5 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - El Dorado 2101 - 19752 - Ph 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 410049.54
35056746 | CWSP - MIWUK 1701 OCB PHASE 2.1 | 09/25/2018 | 114996821 | 09/24/2018 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/07/2020 | ED.16366.1701 | MIWUK 1701 | 055 | TUOLUMNE COUNT | 5535211 | CWSP SPO - SH 08 | 10,737.000 | 0.000 | 08W | 2018 | # | OPEN | 801 | 114.4286 | CONS | 7 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Miwuk 1701 - OCB Zone - Phase 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 294468.06
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | 09/26/2018 | 114987251 | 09/20/2018 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/30/2020 | ED.15276.2101 | EL DORADO PH 2101 | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 59,373.000 | 0.000 | 08W | 2018 | # | OPEN | 800 | 114.2857 | APPR | 4 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - El Dorado 2101 - LR 19752 - Ph2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 89054.76
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | 09/27/2018 | 114987282 | 09/20/2018 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/30/2020 | ED.15276.2101 | EL DORADO PH 2101 | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 8,673.000 | 9,006.000 | 08W | 2018 | # | OPEN | 799 | 114.1429 | DOCC | 8 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - El Dorado 2101 - LR 19752 - Ph3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2019-12-03 | 2019-12-03 | INPR | 2019-12-26 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | -43802 | 0 | 2500136.39
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | 09/27/2018 | 114987363 | 09/20/2018 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/30/2020 | ED.15276.2101 | EL DORADO PH 2101 | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 25,090.000 | 0.000 | 08W | 2018 | # | OPEN | 799 | 114.1429 | PEND | 5 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - El Dorado 2101 - LR 19752 - Ph4 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 421168.34
35057526 | RECOND 460 CKT-FT_CASTRO VALLEY 1106 | 10/01/2018 | 115013270 | 10/01/2018 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/30/2021 | ED.01409.1106 | CASTRO VALLEY 1106 | 001 | ALAMEDA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2018 | # | OPEN | 795 | 113.5714 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 1151.35
35057802 | CWSP-CAMPEVERS2105 - LR 12590 - 4KV PH5 | 10/03/2018 | 115019871 | 10/03/2018 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 09/30/2021 | ED.76-M122400000.STRU.POLE | COAST M1224 POLES | 044 | SANTA CRUZ COU | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2018 | # | OPEN | 793 | 113.2857 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Big Trees 0402 - CB Zone - 4kV cu | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 5819.13
35057921 | PUEBLO 2103 RECOND W TW PAST FUSE 2013 | 10/04/2018 | 115025758 | 10/04/2018 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.42-KK36000000.STRU.POLE | SILVERADO MAP KK36 POLES | 028 | NAPA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2018 | # | OPEN | 792 | 113.1429 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 1329.78
35058026 | CWSP:EL DORADO PH 2101 LR 63464 OH TO UG | 10/05/2018 | 115027447 | 10/04/2018 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2019 | ED.15276.2101.SWIT | SWITCHES | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2018 | # | OPEN | 791 | 113 | ESTS | 2 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 94224.18
35058060 | SWIFT 2110 - CONDUCTOR REPL | 10/05/2018 | 115029437 | 10/05/2018 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/30/2020 | ED.08339.2110 | SWIFT 2110 | 043 | SANTA CLARA CO | 5535211 | CWSP SPO - SH 08 | 5,430.000 | 0.000 | 08W | 2018 | # | OPEN | 791 | 113 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 6920.91
35058080 | *CANC* X-1104 OH RECOND SKYLINE *CANC | 10/05/2018 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/01/2020 | ED.26-F070700000.STRU.POLE | CENTRAL F0707 POLES | 001 | ALAMEDA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2018 | 09/05/2019 | 2019 | 335 | 47.8571 | CLSD | 12 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 2019-09-05 | 2019-09-05 | # | 2019-09-05 | 2019-09-05 | # | 2019-09-05 | 2019-09-05 | # | 2019-09-05 | 2019-09-05 | # | 2019-09-05 | 2019-09-05 | # | 2019-09-05 | 2019-09-05 | 0 | 0 | 0
35058272 | CWSP- EL DORADO 2101 OCB ZONE PHASE 2 | 10/08/2018 | 114987334 | 09/20/2018 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.21-H470100000.STRU.POLE | EL DORADO H4701 POLES | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2018 | # | OPEN | 788 | 112.5714 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP- EL DORADO 2101 OCB ZONE PHASE 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 6274.26
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | 10/08/2018 | 114987127 | 09/20/2018 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.21-G460000000.STRU.POLE | EL DORADO G46 POLES | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 6,215.000 | 0.000 | 08W | 2018 | # | OPEN | 788 | 112.5714 | CONS | 7 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | INPR | 2020-04-22 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 1356466.14
35058723 | BUELLTON 1101 SW8203 REPL 300FT OH LINE | 10/09/2018 | 115004305 | 09/27/2018 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 02/12/2021 | ED.18304.1101.SWIT | SWITCHES | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2018 | # | OPEN | 787 | 112.4286 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35058794 | CWSP - APPLE HILL 2102 - 7502 - PHASE 1 | 10/11/2018 | 115036667 | 10/09/2018 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/30/2020 | ED.15366.2102 | APPLE HILL 2102 | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 46,174.000 | 0.000 | 08W | 2018 | # | OPEN | 785 | 112.1429 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Apple Hill 2102 - LR 7502 - Ph1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 6719.55
35058795 | CWSP - APPLE HILL 2102 - 7502 - PHASE 2 | 10/11/2018 | 115036706 | 10/09/2018 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/30/2020 | ED.15366.2102 | APPLE HILL 2102 | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 39,728.000 | 0.000 | 08W | 2018 | # | OPEN | 785 | 112.1429 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Apple Hill 2102 - LR 7502 - Ph2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 3389.45
35058797 | CWSP - APPLE HILL 2102 - 7502 - PHASE 3 | 10/11/2018 | 115036771 | 10/09/2018 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/30/2020 | ED.15366.2102 | APPLE HILL 2102 | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 46,057.000 | 0.000 | 08W | 2018 | # | OPEN | 785 | 112.1429 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Apple Hill 2102 - LR 7502 - Ph3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 4643.1
35058831 | MC KEE 1107 REP 9K FT OH COND WITH 2AR | 10/10/2018 | 115049352 | 10/10/2018 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/30/2021 | ED.08353.1107 | MC KEE 1107 | 043 | SANTA CLARA CO | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2018 | # | OPEN | 786 | 112.2857 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 4295.54
35058905 | CWSP - VOLTA 1102 - LR 1648 -PH 4.1 | 10/10/2018 | 115038304 | 10/09/2018 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/30/2020 | JY | JUNK YARD FL TO HOLD DELETED DATA | 045 | SHASTA COUNTY | 5535211 | CWSP SPO - SH 08 | 11,306.000 | 11,145.000 | 08W | 2018 | # | OPEN | 786 | 112.2857 | DOCC | 8 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - VOLTA 1102 - LR 1648 -PHASE 4 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2020-01-16 | 2020-01-16 | INPR | 2019-10-15 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | -43846 | 0 | 3213075.49
35059696 | ECHO SUMMIT 1101 – REPLACING TREE ATTACH | 10/18/2018 | 115061014 | 10/15/2018 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 08/01/2019 | ED.15803.1101.SWIT | SWITCHES | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2018 | # | OPEN | 778 | 111.1429 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 753.26
35059716 | HAMMER 1105 RECONDUCTORING - WIREDOWN | 10/19/2018 | 115072890 | 10/19/2018 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.93-T091000000.STRU.POLE | STOCKTON T0910 POLES | 039 | SAN JOAQUIN CO | 5535457 | DO 08 - Monthly Forecast Only | 1,582.000 | 0.000 | 08J | 2018 | # | OPEN | 777 | 111 | APPR | 4 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 26066.03
35060027 | CWSP-PARADISE 1104-TS 1571 | 10/23/2018 | 115079333 | 10/22/2018 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/30/2020 | ED.10283.1104.SWIT | SWITCHES | 004 | BUTTE COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2018 | # | OPEN | 773 | 110.4286 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 171.99
35060157 | CWSP- HENDRIX DEMO - LIVERMORE TRNG CNTR | 10/23/2018 | 115082086 | 10/23/2018 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2018 | ED.01440.2105 | LAS POSITAS 2105 | 001 | ALAMEDA COUNTY | 5535211 | CWSP SPO - SH 08 | 1,270.000 | 0.000 | 08W | 2018 | 02/29/2020 | 2020 | 494 | 70.5714 | CLSD | 12 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2019-10-15 | 2019-10-15 | COMP | 2019-06-06 | 2019-10-16 | COMP | 2019-10-16 | 2019-10-16 | COMP | 2019-10-16 | 2019-10-24 | COMP | 2019-10-24 | 2019-11-04 | COMP | 2019-11-04 | 2019-11-04 | 1 | 19 | 318548.64
35060228 | 2019 OH COND RPLC: EEL RIVER 1102 FU1903 | 10/24/2018 | 113663476 | 10/04/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/11/2019 | ED.35-V070000000.STRU.POLE | FORTUNA V07 POLES | 012 | HUMBOLDT COUNT | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2018 | # | OPEN | 772 | 110.2857 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35060229 | 2018 OH COND RPLC: FRUITLAND 42 C/O 7449 | 10/24/2018 | 112191204 | 11/29/2016 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/10/2018 | ED.19231.1142.SWIT | SWITCHES | 012 | HUMBOLDT COUNT | 5535211 | CWSP SPO - SH 08 | 6,694.000 | 6,271.000 | 08W | 2018 | 09/26/2020 | 2020 | 703 | 100.4286 | CLSD | 12 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2019-07-30 | 2019-07-30 | COMP | 2019-06-05 | 2020-06-19 | COMP | 2020-06-19 | 2020-06-19 | COMP | 2020-07-08 | 2020-09-08 | COMP | 2020-09-08 | 2020-09-10 | COMP | 2020-09-10 | 2020-09-10 | 325 | 83 | 1962512.65
35060338 | *CANC*DO NOTUSE*2018 OH COND RPLC:E*CANC | 10/24/2018 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/10/2018 | ED.19233.1104.SWIT | SWITCHES | 012 | HUMBOLDT COUNT | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2018 | 05/03/2020 | 2020 | 557 | 79.5714 | CLSD | 12 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | COMP | 2020-04-08 | 2020-04-08 | COMP | 2020-04-08 | 2020-04-08 | COMP | 2020-04-08 | 2020-04-08 | 0 | -25 | 0
35060383 | WDDB - FRUITLAND 1142CB C/O 1679 | 10/24/2018 | 112190914 | 11/29/2016 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/29/2018 | ED.19231.1142.SWIT | SWITCHES | 012 | HUMBOLDT COUNT | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2018 | # | OPEN | 772 | 110.2857 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35060387 | WDDB BIG RIVER 1101 FUSE 5187 RECONDUCTO | 10/24/2018 | 112404866 | 12/13/2016 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/10/2018 | ED.04308.1101.SWIT | SWITCHES | 023 | MENDOCINO COUN | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 2018 | # | OPEN | 772 | 110.2857 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35060580 | *CANC*BIG BEND 1102 - BLOOMER *CANC | 10/26/2018 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 05/01/2016 | ED.85-CC29000000 | TEHEMA MAP CC29 | 052 | TEHAMA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2018 | 09/05/2019 | 2019 | 314 | 44.8571 | CLSD | 12 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 2019-09-05 | 2019-09-05 | # | 2019-09-05 | 2019-09-05 | # | 2019-09-05 | 2019-09-05 | # | 2019-09-05 | 2019-09-05 | # | 2019-09-05 | 2019-09-05 | # | 2019-09-05 | 2019-09-05 | 0 | 0 | 0
35060581 | *CANC* RECONDUCT PT. MORETTI FROM 5043 | 10/26/2018 | 5625029 | 10/26/2018 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/28/2018 | ED.08293.1101 | POINT MORETTI 1101 | 044 | SANTA CRUZ COU | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2018 | 01/12/2019 | 2019 | 78 | 11.1429 | CLSD | 12 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | 31272374_RECOND PT MORETTI: 5043 TO 5955 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35060582 | SLO 1107 RECOD 3884 FT WITH 2CU TW | 10/26/2018 | 112640645 | 03/01/2017 | # | Not assigned | 30 | Technically Completed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/01/2017 | ED.18263.1107 | SAN LUIS OBISPO 1107 | 040 | SAN LUIS OBISP | 5535211 | CWSP SPO - SH 08 | 3,884.000 | 3,836.000 | 08W | 2018 | # | OPEN | 770 | 110 | FICL | 10 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2019-10-09 | 2019-10-09 | COMP | 2019-10-25 | 2019-10-25 | COMP | 2019-10-25 | 2019-10-25 | COMP | 2019-10-25 | 2019-10-28 | COMP | 2019-10-28 | 2019-11-21 | COMP | 2019-11-21 | 2019-11-22 | 16 | 28 | 815086.88
35060583 | RECONDUCTOR STOREY 1105 | 10/26/2018 | 112640449 | 03/01/2017 | # | Not assigned | 30 | Technically Completed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/20/2019 | ED.25461.1105 | STOREY 1105 | 020 | MADERA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 3,163.000 | 3,163.000 | 08J | 2018 | # | OPEN | 770 | 110 | FICL | 10 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31314313_Reconductor Storey 1105 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2020-06-02 | 2020-06-02 | COMP | 2020-03-04 | 2020-06-22 | COMP | 2020-06-22 | 2020-06-22 | COMP | 2020-06-22 | 2020-06-23 | COMP | 2020-06-23 | 2020-07-31 | COMP | 2020-07-31 | 2020-08-07 | 20 | 46 | 153130.6
35060584 | RPL OH WIRE ON OTTER-1101 S030CC121 | 10/26/2018 | 113743255 | 10/18/2017 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 06/28/2019 | ED.07-N031000000.STRU.POLE | MONTEREY N0310 POLES | 027 | MONTEREY COUNT | 5535211 | CWSP SPO - SH 08 | 24,381.000 | 0.000 | 08W | 2018 | # | OPEN | 770 | 110 | PEND | 5 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | RPL OH WIRE OTTER 1101 S030CC121 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 74968.73
35060585 | *CANC* CHOLAME 1101 WD RECONDUCORI *CANC | 10/26/2018 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2017 | ED.18256.1101 | CHOLAME 1101 | 040 | SAN LUIS OBISP | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2018 | 09/05/2019 | 2019 | 314 | 44.8571 | CLSD | 12 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2019-09-05 | 2019-09-05 | # | 2019-09-05 | 2019-09-05 | # | 2019-09-05 | 2019-09-05 | # | 2019-09-05 | 2019-09-05 | # | 2019-09-05 | 2019-09-05 | # | 2019-09-05 | 2019-09-05 | 0 | 0 | 0
35060586 | *CANC* RECONDUCTOR 5885 FT ZACA *CANC | 10/26/2018 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/01/2017 | ED.18268.1102 | ZACA 1102 | 042 | SANTA BARBARA | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2018 | 09/05/2019 | 2019 | 314 | 44.8571 | CLSD | 12 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 2019-09-05 | 2019-09-05 | # | 2019-09-05 | 2019-09-05 | # | 2019-09-05 | 2019-09-05 | # | 2019-09-05 | 2019-09-05 | # | 2019-09-05 | 2019-09-05 | # | 2019-09-05 | 2019-09-05 | 0 | 0 | 0
35060587 | *CANC* REPLACE~1.2MILES_MAINLINE_ *CANC | 10/26/2018 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2016 | ED.18268.1101 | ZACA 1101 | 042 | SANTA BARBARA | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2018 | 09/05/2019 | 2019 | 314 | 44.8571 | CLSD | 12 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 2019-09-05 | 2019-09-05 | # | 2019-09-05 | 2019-09-05 | # | 2019-09-05 | 2019-09-05 | # | 2019-09-05 | 2019-09-05 | # | 2019-09-05 | 2019-09-05 | # | 2019-09-05 | 2019-09-05 | 0 | 0 | 0
35060588 | *CANC* RECON 11 SPAN 3313FT 4CU 6 *CANC | 10/26/2018 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/30/2018 | ED.18310.1104 | CABRILLO 1104 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2018 | 09/05/2019 | 2019 | 314 | 44.8571 | CLSD | 12 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2019-09-05 | 2019-09-05 | # | 2019-09-05 | 2019-09-05 | # | 2019-09-05 | 2019-09-05 | # | 2019-09-05 | 2019-09-05 | # | 2019-09-05 | 2019-09-05 | # | 2019-09-05 | 2019-09-05 | 0 | 0 | 0
35060893 | RPL OH.CON.SPENCE 1123 18-0074972 | 10/29/2018 | # | #N/A | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2021 | ED.05-I130000000.STRU.POLE | SALINAS I13 POLES | 027 | MONTEREY COUNT | 5517128 | DO 49 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2018 | # | OPEN | 767 | 109.5714 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0
35060990 | CWSP-BRUNSWICK 1105 LR2140 ZONE-PH3.01 | 10/30/2018 | 115102251 | 10/30/2018 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.15248.1105 | BRUNSWICK 1105 | 029 | NEVADA COUNTY | 5535211 | CWSP SPO - SH 08 | 4,562.000 | 0.000 | 08W | 2018 | # | OPEN | 766 | 109.4286 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Brunswick - 1105 - LR2140 Zone-Ph | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 19609.3
35060991 | CWSP-BRUNSWICK 1105 LR2140 ZONE-PH2.01 | 10/30/2018 | 115101979 | 10/30/2018 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.15248.1105 | BRUNSWICK 1105 | 029 | NEVADA COUNTY | 5535211 | CWSP SPO - SH 08 | 2,465.000 | 0.000 | 08W | 2018 | # | OPEN | 766 | 109.4286 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Brunswick - 1105 - LR2140 Zone-Ph | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 15853.89
35060992 | CWSP-BRUNSWICK 1105 LR2140 ZONE-PH1.01 | 10/30/2018 | 115101918 | 10/30/2018 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.15248.1105 | BRUNSWICK 1105 | 029 | NEVADA COUNTY | 5535211 | CWSP SPO - SH 08 | 2,534.000 | 0.000 | 08W | 2018 | # | OPEN | 766 | 109.4286 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Brunswick - 1105 - LR2140 Zone-Ph | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 35424.29
35060993 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.1 | 10/30/2018 | 115101776 | 10/30/2018 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 04/29/2022 | ED.15248.1105 | BRUNSWICK 1105 | 029 | NEVADA COUNTY | 5535211 | CWSP SPO - SH 08 | 5,545.000 | 0.000 | 08W | 2018 | # | OPEN | 766 | 109.4286 | ESTS | 2 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Brunswick - 1105 - LR2210 Zone-Ph | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 12831.44
35060994 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.1 | 10/30/2018 | 115101557 | 10/30/2018 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.15248.1105 | BRUNSWICK 1105 | 029 | NEVADA COUNTY | 5535211 | CWSP SPO - SH 08 | 5,780.000 | 0.000 | 08W | 2018 | # | OPEN | 766 | 109.4286 | ESTS | 2 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Brunswick - 1105 - LR2210 Zone-Ph | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 33964.52
35060995 | CWSP-BRUNSWICK 1106 LR-2104 ZONE | 10/30/2018 | 115101457 | 10/30/2018 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.15248.1106 | BRUNSWICK 1106 | 029 | NEVADA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2018 | # | OPEN | 766 | 109.4286 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Brunswick - 1106 - LR2104 Zone | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 1843.09
35061041 | CWSP – MONTE RIO 1112 – TS 15401 | 10/30/2018 | 115099028 | 10/29/2018 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 11/30/2020 | ED.04281.1112.SWIT | SWITCHES | 049 | SONOMA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2018 | # | OPEN | 766 | 109.4286 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-Monte Rio 1112-TS 15401 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 415.18
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | 10/31/2018 | 115106231 | 10/31/2018 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/02/2020 | ED.15248.1103 | BRUNSWICK 1103 | 029 | NEVADA COUNTY | 5535211 | CWSP SPO - SH 08 | 9,320.000 | 0.000 | 08W | 2018 | # | OPEN | 765 | 109.2857 | CONS | 7 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Brunswick 1103 LR50070 Zone-Ph1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | INPR | 2020-05-26 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 967230.95
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | 10/31/2018 | 115106486 | 10/31/2018 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 11/06/2020 | ED.15248.1103 | BRUNSWICK 1103 | 029 | NEVADA COUNTY | 5535211 | CWSP SPO - SH 08 | 10,109.000 | 0.000 | 08W | 2018 | # | OPEN | 765 | 109.2857 | CONS | 7 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Brunswick 1103 LR50070 Zone-Ph2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 1342029.94
35061213 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH3 | 10/31/2018 | 115106582 | 10/31/2018 | # | Not assigned | 30 | Technically Completed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 10/15/2020 | ED.15248.1103 | BRUNSWICK 1103 | 029 | NEVADA COUNTY | 5535211 | CWSP SPO - SH 08 | 7,662.000 | 7,702.000 | 08W | 2018 | # | OPEN | 765 | 109.2857 | FICL | 10 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Brunswick 1103 LR50070 Zone-Ph3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2020-08-14 | 2020-08-14 | COMP | 2020-05-18 | 2020-08-20 | COMP | 2020-08-20 | 2020-08-26 | COMP | 2020-08-26 | 2020-08-28 | COMP | 2020-08-28 | 2020-10-20 | COMP | 2020-10-20 | 2020-10-26 | 12 | 61 | 1375943.3
35061709 | SILVERADO 2104 RECONDUCTOR PROJECT | 11/06/2018 | 114521755 | 04/20/2018 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 04/20/2020 | JY | JUNK YARD FL TO HOLD DELETED DATA | 028 | NAPA COUNTY | 5535211 | CWSP SPO - SH 08 | 8,638.000 | 8,003.000 | 08W | 2018 | # | OPEN | 759 | 108.4286 | DOCC | 8 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | SILVERADO 2104 RECONDUCTOR PROJECT | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 4144244.69
35061810 | CWSP - EL DORADO PH 2101 ZONE 19612 | 11/07/2018 | 115217232 | 11/05/2018 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.15276.2101.SWIT | SWITCHES | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2018 | # | OPEN | 758 | 108.2857 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - El Dorado PH 2101 Zone 19612 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 4565.17
35061811 | CWSP-EL DORADO PH 2102 LR19542 PH 1.1 | 11/07/2018 | 115217237 | 11/05/2018 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.15276.2101.SWIT | SWITCHES | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2018 | # | OPEN | 758 | 108.2857 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - El Dorado PH 2102 Zone 19542 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 7099.85
35061812 | CWSP - EL DORADO PH 2102 ZONE 6645 | 11/07/2018 | 115221464 | 11/05/2018 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.15276.2101.SWIT | SWITCHES | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2018 | # | OPEN | 758 | 108.2857 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - El Dorado PH 2102 Zone 6645 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 6487.6
35061985 | 2021 EB WD F-1105 | 11/08/2018 | 115322712 | 11/08/2018 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/30/2021 | ED.28-E041500000.STRU.POLE | BAY E0415 POLES | 001 | ALAMEDA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2018 | # | OPEN | 757 | 108.1429 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 407.19
35062042 | 2020 ACTON 401 HIGH SPLICE COUNT | 11/08/2018 | 115277939 | 11/06/2018 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 05/20/2020 | ED.02247.0401.SWIT | SWITCHES | 038 | SAN FRANCISCO | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2018 | # | OPEN | 757 | 108.1429 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 10449.36
35062173 | Cancl FIRE PADSE 1105 INST NOVA BILLE RD | 11/12/2018 | 5650494 | 11/12/2018 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/07/2018 | JY | JUNK YARD FL TO HOLD DELETED DATA | 004 | BUTTE COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2018 | # | OPEN | 753 | 107.5714 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35062374 | CWSP - SHINGLE SPRINGS 2109-LR 9372-PH1 | 11/15/2018 | 115323920 | 11/08/2018 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.15365.2109 | SHINGLE SPRINGS 2109 | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2018 | # | OPEN | 750 | 107.1429 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Shingle Springs 2109 LR 9372 Ph1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 25770.74
35062375 | CWSP - SHINGLE SPRINGS 2109-LR 9372-PH2 | 11/15/2018 | 115323921 | 11/08/2018 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.15365.2109 | SHINGLE SPRINGS 2109 | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2018 | # | OPEN | 750 | 107.1429 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Shingle Springs 2109 LR 9372 Ph2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 4175.32
35062376 | CWSP - SHINGLE SPRINGS 2109-LR 9372-PH3 | 11/15/2018 | 115323922 | 11/08/2018 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.15365.2109 | SHINGLE SPRINGS 2109 | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2018 | # | OPEN | 750 | 107.1429 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Shingle Springs 2109 LR 9372 Ph3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 1579.86
35064793 | LP RECONDUCTOR, CABRILLO 1104 S006CC102 | 11/21/2018 | 113311784 | 09/22/2017 | # | Not assigned | 30 | Technically Completed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 09/22/2019 | ED.18310.1104 | CABRILLO 1104 | 042 | SANTA BARBARA | 5535211 | CWSP SPO - SH 08 | 17,701.000 | 12,142.000 | 08W | 2018 | # | OPEN | 744 | 106.2857 | FICL | 10 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Cabrillo 1104 Reconductoring | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2019-08-26 | 2019-08-26 | COMP | 2019-09-18 | 2019-09-18 | COMP | 2019-09-18 | 2019-09-18 | COMP | 2019-10-23 | 2019-11-18 | COMP | 2019-11-18 | 2019-12-12 | COMP | 2019-12-12 | 2019-12-12 | 23 | 85 | 2447074.54
35064904 | WOODWARD 2101 RECOND 2520FT TO 1/0AR TW | 11/26/2018 | 115350189 | 11/15/2018 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2021 | ED.25529.2101 | WOODWARD 2101 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2018 | # | OPEN | 739 | 105.5714 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 3696.1
35065016 | SAN RAFAEL 1103 WIRE DOWN 18-0096220 | 11/26/2018 | 115405199 | 11/21/2018 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/30/2021 | ED.40-TT33130000.STRU.POLE | NORTH BAY MAP TT3313 POLES | 021 | MARIN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2018 | # | OPEN | 739 | 105.5714 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35065727 | *CANC* CAMP FIRE SOUTH SKYWAY EXTEN*CANC | 12/03/2018 | 115443100 | 12/03/2018 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/01/2019 | ED.17-T321300000.STRU.POLE | PARADISE T3213 POLES | 004 | BUTTE COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 2018 | 06/03/2020 | 2020 | 548 | 78.2857 | CLSD | 12 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | GRC Electric Dist | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2020-06-03 | 2020-06-03 | # | 2020-06-03 | 2020-06-03 | # | 2020-06-03 | 2020-06-03 | # | 2020-06-03 | 2020-06-03 | # | 2020-06-03 | 2020-06-03 | # | 2020-06-03 | 2020-06-03 | 0 | 0 | 0
35065842 | CWSP-EL DORADO 2101 - LR 26000 - PH3 | 12/03/2018 | 115417043 | 11/28/2018 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.15276.2101.SWIT | SWITCHES | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2018 | # | OPEN | 732 | 104.5714 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-EL DORADO 2101 - LR 26000 - PH3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 1699.6
35066029 | RPL OH.CON.SPENCE 1102 18-0074972 | 12/05/2018 | 115098143 | 10/29/2018 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.05-I130000000.STRU.POLE | SALINAS I13 POLES | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2018 | # | OPEN | 730 | 104.2857 | ESTS | 2 | E470 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | RPL OH.Con.Spence 112318-0074972 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 44784.05
35066037 | KING CHI ITY 1102 RECONDUCTOR LR7024 EOL | 12/05/2018 | 115107075 | 10/31/2018 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 10/31/2020 | ED.04-Q230000000.STRU.POLE | KING CITY Q23 POLES | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2018 | # | OPEN | 730 | 104.2857 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 19150.51
35066309 | RE-CONDUCTOR 2309 CIRCUIT FT 4ACSR W 2CU | 12/06/2018 | 115451094 | 12/06/2018 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/06/2021 | ED.06283.1100.RECL | RECLOSERS | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2018 | # | OPEN | 729 | 104.1429 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 687.8
35066622 | FOOTHILL 1101 LS CO9973 RECONDUCTOR, SLO | 12/10/2018 | 113245749 | 09/13/2017 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/20/2019 | ED.18295.1101.TXFR.TROH | OVERHEAD TRANSFORMERS | 040 | SAN LUIS OBISP | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2018 | # | OPEN | 725 | 103.5714 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | FOOTHILL 1101 LS CO9973 REPL OH LINE | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 53595.84
35066745 | BIG BEND 1102 - BLOOMER HILL 08W PHS 2 | 12/11/2018 | 108159179 | 05/23/2014 | # | Not assigned | 40 | Closed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 05/01/2016 | ED.85-CC29000000 | TEHEMA MAP CC29 | 052 | TEHAMA COUNTY | 5535211 | CWSP SPO - SH 08 | 8,900.000 | 8,900.000 | 08W | 2018 | 05/09/2020 | 2020 | 515 | 73.5714 | CLSD | 12 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2019-11-21 | 2019-11-21 | COMP | 2019-11-14 | 2020-02-27 | COMP | 2020-02-27 | 2020-02-27 | COMP | 2020-02-27 | 2020-02-28 | COMP | 2020-02-28 | 2020-03-12 | COMP | 2020-03-12 | 2020-03-12 | 98 | 14 | 3165170.7
35066933 | *CANC*WD - WATSONVILLE 2101 - 11509*CANC | 12/13/2018 | 115492297 | 12/12/2018 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 08/16/2021 | ED.76-Q211000000.STRU.POLE | COAST Q2110 POLES | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2018 | 01/04/2019 | 2019 | 22 | 3.1429 | CLSD | 12 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2019-01-04 | 2019-01-04 | # | 2019-01-04 | 2019-01-04 | # | 2019-01-04 | 2019-01-04 | # | 2019-01-04 | 2019-01-04 | # | 2019-01-04 | 2019-01-04 | # | 2019-01-04 | 2019-01-04 | 0 | 0 | 0
35067360 | SUISUN 1105 WIRE DOWN DSC 6385 TO 6473 | 12/17/2018 | 115524863 | 12/17/2018 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 10/09/2020 | ED.06213.1105.SWIT | SWITCHES | 048 | SOLANO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 5,976.000 | 0.000 | 08J | 2018 | # | OPEN | 718 | 102.5714 | PEND | 5 | E470 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 25362.67
35067449 | RECOND MESA 1103 ALONG CALLE FRESA | 12/19/2018 | 115543440 | 12/18/2018 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/30/2020 | ED.18282.1103 | MESA 1103 | 040 | SAN LUIS OBISP | 5535457 | DO 08 - Monthly Forecast Only | 3,000.000 | 0.000 | 08J | 2018 | # | OPEN | 716 | 102.2857 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 343.89
35067618 | HBPP 01 DETERIORATED CONDUCTOR HUMB HILL | 12/20/2018 | 115482752 | 12/11/2018 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/15/2021 | ED.36-Q062000000.STRU.POLE | EUREKA Q0620 POLES | 012 | HUMBOLDT COUNT | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2018 | # | OPEN | 715 | 102.1429 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 592.36
35067619 | CWSP – MONTE RIO 1112 – LR 120 | 12/21/2018 | 115098949 | 10/29/2018 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 11/30/2020 | ED.04281.1112.SWIT | SWITCHES | 049 | SONOMA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2018 | # | OPEN | 714 | 102 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-Monte Rio 1112-LR 120 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 229.01
35067716 | HMB1102 LR60703 REPLACE 400FT OF OH LINE | 12/21/2018 | 115584479 | 12/20/2018 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/26/2020 | ED.02410.1102.RECL | RECLOSERS | 041 | SAN MATEO COUN | 5517127 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2018 | # | OPEN | 714 | 102 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35068072 | SAN RAFAEL 1102 WIRE DOWN 18-0107061 | 12/28/2018 | 115606055 | 12/28/2018 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/01/2021 | ED.40-TT33090000.STRU.POLE | NORTH BAY MAP TT3309 POLES | 021 | MARIN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2018 | # | OPEN | 707 | 101 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 221.54
35068513 | MESA 1103 RECOND 2036 FT W 2CU | 01/03/2019 | 115638264 | 01/03/2019 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 01/03/2020 | ED.18282.1103 | MESA 1103 | 040 | SAN LUIS OBISP | 5535457 | DO 08 - Monthly Forecast Only | 2,036.000 | 0.000 | 08J | 2019 | # | OPEN | 701 | 100.1429 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35068516 | RECOND 1327FT OF4ACSR,197FT OF 6CU W 2CU | 01/04/2019 | 112835205 | 05/04/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 05/04/2019 | ED.18267.1106 | SANTA MARIA 1106 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2019 | # | OPEN | 700 | 100 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 30841.86
35068540 | MESA 1103 RECON 4AR WITH 397AL TREE WIRE | 01/03/2019 | 115605923 | 12/28/2018 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/03/2020 | ED.18282.1103 | MESA 1103 | 040 | SAN LUIS OBISP | 5535457 | DO 08 - Monthly Forecast Only | 6,348.000 | 0.000 | 08J | 2019 | # | OPEN | 701 | 100.1429 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 685.32
35068566 | 08J LP FAIRWAY 1103 WIREDOWN 18-0105602 | 01/03/2019 | 115597497 | 12/26/2018 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 05/28/2021 | ED.18206.1103.TXFR.TROH | OVERHEAD TRANSFORMERS | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2019 | # | OPEN | 701 | 100.1429 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 1049.6
35069872 | WD - GV2104 - 5TH ST WATSONVILLE | 01/10/2019 | 115641286 | 01/04/2019 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 08/27/2021 | ED.76-Q200300000.STRU.POLE | COAST Q2003 POLES | 044 | SANTA CRUZ COU | 5535457 | DO 08 - Monthly Forecast Only | 250.000 | 0.000 | 08J | 2019 | # | OPEN | 694 | 99.1429 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 625.7
35069909 | RPL OH.CON.DOLAN RD. 1101 18-0096302 | 01/10/2019 | 115655197 | 01/08/2019 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/30/2021 | ED.05-D070900000.STRU.POLE | SALINAS D0709 POLES | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 7,535.000 | 0.000 | 08J | 2019 | # | OPEN | 694 | 99.1429 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 35069909_RPL OH.CON.DOLAN RD. 1101 18-00 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 1368.63
35070552 | DIAMOND SPRINGS 1106 RECON BEYOND 2145 | 01/14/2019 | 115637664 | 01/03/2019 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2021 | ED.15226.1106.SWIT | SWITCHES | 009 | EL DORADO COUN | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2019 | # | OPEN | 690 | 98.5714 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35071273 | TEMPLETON 2113 RECOND 7622' OF 4AR W 715 | 01/18/2019 | 115700150 | 01/17/2019 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2021 | ED.18305.2113 | TEMPLETON 2113 | 040 | SAN LUIS OBISP | 5535457 | DO 08 - Monthly Forecast Only | 7,622.000 | 0.000 | 08J | 2019 | # | OPEN | 686 | 98 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 821.37
35071495 | RPL OH.CON.RESERVATION RD.1102 18-011072 | 01/17/2019 | 115700424 | 01/17/2019 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/30/2020 | JY | JUNK YARD FL TO HOLD DELETED DATA | 027 | MONTEREY COUNT | 5535211 | CWSP SPO - SH 08 | 6,016.000 | 0.000 | 08W | 2019 | # | OPEN | 687 | 98.1429 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | 35071495_RPL OH.CON.RESERVATION RD.1102 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 840.73
35071765 | RECOND2676 CIRCUIT FT OF 4ACSR W 2CU | 01/18/2019 | 115703224 | 01/18/2019 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2021 | ED.18297.1101 | PURISIMA 1101 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 2,676.000 | 0.000 | 08J | 2019 | # | OPEN | 686 | 98 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35072062 | RECOND WATS 2101 FUSE 11533 ZONE | 01/22/2019 | 115714387 | 01/22/2019 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/30/2020 | ED.76-Q222300000.STRU.POLE | COAST Q2223 POLES | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 4,380.000 | 0.000 | 08J | 2019 | # | OPEN | 682 | 97.4286 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 816.63
35072140 | RECOND KING CITY 1101 ALONG CANAL ST | 01/23/2019 | 115713604 | 01/22/2019 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/30/2021 | ED.18203.1101 | KING CITY 1101 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2019 | # | OPEN | 681 | 97.2857 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 6791.61
35072146 | RPL 17,500' 4AR TIER 3 SILVERADO 2105 | 01/23/2019 | 114482701 | 04/09/2018 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2019 | ED.42-GG32250000.STRU.POLE | SILVERADO GG3225 POLES | 028 | NAPA COUNTY | 5535211 | CWSP SPO - SH 08 | 3,666.000 | 3,684.000 | 08W | 2019 | # | OPEN | 681 | 97.2857 | DOCC | 8 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | REPL 17,500' of 4ar & 4cu in Tier 3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2019-12-17 | 2019-12-17 | INPR | 2020-05-13 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | -43816 | 0 | 2065251.75
35072147 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.1 | 01/23/2019 | 114474286 | 04/05/2018 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 09/30/2019 | ED.08202.1106 | LOS GATOS 1106 | 043 | SANTA CLARA CO | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2019 | # | OPEN | 681 | 97.2857 | ESTS | 2 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | PH 1:REPL 14,000' OF 4AR IN TIER 3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 136822.9
35072360 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.1 | 01/24/2019 | 114754229 | 07/05/2018 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.16369.2102.RECL | RECLOSERS | 005 | CALAVERAS COUN | 5535211 | CWSP SPO - SH 08 | 5,541.000 | 0.000 | 08W | 2019 | # | OPEN | 680 | 97.1429 | CONS | 7 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-SALT SPRINGS 2102-LR3142 ZONE-PH 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 1073255.59
35072361 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.1 | 01/24/2019 | 114754228 | 07/05/2018 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.16369.2102.RECL | RECLOSERS | 005 | CALAVERAS COUN | 5535211 | CWSP SPO - SH 08 | 7,709.000 | 0.000 | 08W | 2019 | # | OPEN | 680 | 97.1429 | ADER | 3 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-SALT SPRINGS 2102-LR3142&L491-PHA 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 94589.69
35072362 | CWSP-OH COND RPLC: EEL RIVER 1102 FU1913 | 01/24/2019 | 113676445 | 10/05/2017 | # | Not assigned | 40 | Closed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 10/25/2019 | JY | JUNK YARD FL TO HOLD DELETED DATA | 012 | HUMBOLDT COUNT | 5535211 | CWSP SPO - SH 08 | 13,991.000 | 14,292.000 | 08W | 2019 | 05/31/2020 | 2020 | 493 | 70.4286 | CLSD | 12 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | 2019 OH COND RPLC: EEL RIVER 1102 FU1913 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2019-12-21 | 2019-12-21 | COMP | 2020-02-06 | 2020-02-06 | COMP | 2020-02-06 | 2020-02-06 | COMP | 2020-02-06 | 2020-03-23 | COMP | 2020-03-23 | 2020-04-02 | COMP | 2020-04-02 | 2020-04-02 | 47 | 56 | 1887115.76
35072363 | *CANC* RECOND 15 298 FT 6CU 4CU & | 01/24/2019 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 10/17/2019 | ED.42-FF30000000.STRU.POLE | SILVERADO FF30 POLES | 028 | NAPA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2019 | 09/05/2019 | 2019 | 224 | 32 | CLSD | 12 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | RECONd 15,298 FT 6CU, 4CU & 4AR W 2CU | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 2019-09-05 | 2019-09-05 | # | 2019-09-05 | 2019-09-05 | # | 2019-09-05 | 2019-09-05 | # | 2019-09-05 | 2019-09-05 | # | 2019-09-05 | 2019-09-05 | # | 2019-09-05 | 2019-09-05 | 0 | 0 | 0
35072720 | RPL OH WIRE ON GABILN 1101 17-0077248 | 01/28/2019 | 113646462 | 10/02/2017 | # | Not assigned | 40 | Closed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 06/28/2019 | ED.05-H120700000.STRU.POLE | SALINAS H1207 POLES | 027 | MONTEREY COUNT | 5535211 | CWSP SPO - SH 08 | 11,560.000 | 11,647.000 | 08W | 2019 | 07/25/2020 | 2020 | 544 | 77.7143 | CLSD | 12 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | RPL OH WIRE ON GABILAN 1101 17-0077248 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2020-01-14 | 2020-01-14 | COMP | 2020-01-16 | 2020-02-05 | COMP | 2020-02-05 | 2020-02-05 | COMP | 2020-03-16 | 2020-03-27 | COMP | 2020-03-27 | 2020-03-30 | COMP | 2020-03-30 | 2020-03-31 | 22 | 55 | 1075018.41
35073059 | SONOMA1104 WIREDOWN | 01/31/2019 | 115768648 | 01/30/2019 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/01/2020 | ED.04272.1104 | SONOMA 1104 | 049 | SONOMA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2019 | # | OPEN | 673 | 96.1429 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 3724.58
35073637 | LOS GATOS 1107 RECOND FUSE 468855 ZONE | 02/04/2019 | 115783880 | 02/04/2019 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/15/2019 | ED.80-J151200000.STRU.POLE | DE ANZA J1512 POLES | 043 | SANTA CLARA CO | 5535211 | CWSP SPO - SH 08 | 3,730.000 | 0.000 | 08W | 2019 | # | OPEN | 669 | 95.5714 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 415.55
35074009 | ALTO 1124 WIRE DOWN ILIS 18-0109573 | 02/06/2019 | 115826672 | 02/06/2019 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 05/31/2020 | ED.40-UU32120000.STRU.POLE | NORTH BAY MAP UU3212 POLES | 021 | MARIN COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2019 | # | OPEN | 667 | 95.2857 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35074021 | RECOND-SALINAS 1101 ALONG PRADER ST | 02/08/2019 | 116157204 | 02/07/2019 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/30/2021 | ED.18201.1101 | SALINAS 1101 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 785.000 | 0.000 | 08J | 2019 | # | OPEN | 665 | 95 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35074388 | RECOND GV2101 FUSE 12347 ZONE | 02/08/2019 | 116157025 | 02/07/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 09/30/2020 | ED.76-O200300000.STRU.POLE | COAST O2003 POLES | 044 | SANTA CRUZ COU | 5535211 | CWSP SPO - SH 08 | 9,970.000 | 0.000 | 08W | 2019 | # | OPEN | 665 | 95 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Recond GV 2101 Fuse 12347 zone | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 1098.96
35075103 | FROGTOWN 1701 - 3115FT RECOND HFTD TIER2 | 02/14/2019 | 116475141 | 02/12/2019 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/30/2020 | ED.16345.1701 | FROGTOWN 1701 | 005 | CALAVERAS COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2019 | # | OPEN | 659 | 94.1429 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 3720.44
35075135 | 2019 TARAVAL 402 HIGH SPLICE COUNT | 02/14/2019 | 113145837 | 08/11/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2019 | ED.02250.0402 | TARAVAL 0402 | 038 | SAN FRANCISCO | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2019 | # | OPEN | 659 | 94.1429 | ESTS | 2 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 15406.03
35075136 | REPLACE ~1,100' OH - KING CITY 1106 CKT | 02/14/2019 | 116485471 | 02/13/2019 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/15/2021 | ED.04-R222000000.STRU.POLE | KING CITY R2220 POLES | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2019 | # | OPEN | 659 | 94.1429 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 1078.1
35075365 | RPL OH.COND.CAMP EVERS 2106 19-0015630 | 02/19/2019 | 116490172 | 02/14/2019 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/30/2020 | ED.76-N110400000.STRU.POLE | COAST N1104 POLES | 044 | SANTA CRUZ COU | 5535211 | CWSP SPO - SH 08 | 1,706.000 | 0.000 | 08W | 2019 | # | OPEN | 654 | 93.4286 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 1511.25
35075591 | SILVERADO 2105 WIRE DOWN PH 1 (CANCEL) | 02/20/2019 | 116505018 | 02/20/2019 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2019 | ED.42-GG32250000.STRU.POLE | SILVERADO GG3225 POLES | 028 | NAPA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2019 | 05/22/2019 | 2019 | 91 | 13 | CLSD | 12 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 2019-05-22 | 2019-05-22 | # | 2019-05-22 | 2019-05-22 | # | 2019-05-22 | 2019-05-22 | # | 2019-05-22 | 2019-05-22 | # | 2019-05-22 | 2019-05-22 | # | 2019-05-22 | 2019-05-22 | 0 | 0 | 0
35075594 | SILVERADO 2105 WIRE DOWN PH-2 (CANCEL) | 02/20/2019 | 116505035 | 02/20/2019 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2019 | ED.42-GG32250000.STRU.POLE | SILVERADO GG3225 POLES | 028 | NAPA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2019 | 05/22/2019 | 2019 | 91 | 13 | CLSD | 12 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 2019-05-22 | 2019-05-22 | # | 2019-05-22 | 2019-05-22 | # | 2019-05-22 | 2019-05-22 | # | 2019-05-22 | 2019-05-22 | # | 2019-05-22 | 2019-05-22 | # | 2019-05-22 | 2019-05-22 | 0 | 0 | 0
35075647 | SILVERADO 2105 WIRE DOWN PH-3 (CANCEL) | 02/20/2019 | 116505355 | 02/20/2019 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2019 | ED.42-GG32250000.STRU.POLE | SILVERADO GG3225 POLES | 028 | NAPA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2019 | 05/22/2019 | 2019 | 91 | 13 | CLSD | 12 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 2019-05-22 | 2019-05-22 | # | 2019-05-22 | 2019-05-22 | # | 2019-05-22 | 2019-05-22 | # | 2019-05-22 | 2019-05-22 | # | 2019-05-22 | 2019-05-22 | # | 2019-05-22 | 2019-05-22 | 0 | 0 | 0
35075650 | SILVERADO 2105 WIRE DOWN PH-4 (CANCEL) | 02/20/2019 | 116505462 | 02/20/2019 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2019 | ED.42-GG32250000.STRU.POLE | SILVERADO GG3225 POLES | 028 | NAPA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2019 | 05/22/2019 | 2019 | 91 | 13 | CLSD | 12 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 2019-05-22 | 2019-05-22 | # | 2019-05-22 | 2019-05-22 | # | 2019-05-22 | 2019-05-22 | # | 2019-05-22 | 2019-05-22 | # | 2019-05-22 | 2019-05-22 | # | 2019-05-22 | 2019-05-22 | 0 | 0 | 0
35076062 | *CANC* RECONDUCTOR 17547 FT OF 4AC *CANC | 02/25/2019 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/27/2020 | ED.18310.1103 | CABRILLO 1103 | 042 | SANTA BARBARA | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2019 | 10/03/2019 | 2019 | 220 | 31.4286 | CLSD | 12 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 2019-10-03 | 2019-10-03 | # | 2019-10-03 | 2019-10-03 | # | 2019-10-03 | 2019-10-03 | # | 2019-10-03 | 2019-10-03 | # | 2019-10-03 | 2019-10-03 | # | 2019-10-03 | 2019-10-03 | 0 | 0 | 0
35076064 | *CANC* 14184 FT OF 4ACSR&3363 FT OF 6CU | 02/25/2019 | 114224375 | 01/16/2018 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 01/16/2020 | ED.18310.1103 | CABRILLO 1103 | 042 | SANTA BARBARA | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2019 | 03/09/2019 | 2019 | 12 | 1.7143 | CLSD | 12 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 2019-03-09 | 2019-03-09 | # | 2019-03-09 | 2019-03-09 | # | 2019-03-09 | 2019-03-09 | # | 2019-03-09 | 2019-03-09 | # | 2019-03-09 | 2019-03-09 | # | 2019-03-09 | 2019-03-09 | 0 | 0 | 0
35076129 | DIAMOND SPRINGS 1105 RECOND WD18-0105867 | 02/26/2019 | 116489047 | 02/14/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.15226.1105.SWIT | SWITCHES | 009 | EL DORADO COUN | 5784105 | DIAMOND SPRINGS 1105 18-0105867 | 0.000 | 0.000 | 08W | 2019 | # | OPEN | 647 | 92.4286 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | DIAMOND SPRINGS 1105 18-0105867 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35076130 | TAMARACK 1101 WD 19-0011942 | 02/26/2019 | 116489079 | 02/14/2019 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.15229.1101.SWIT | SWITCHES | 029 | NEVADA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2019 | # | OPEN | 647 | 92.4286 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35076187 | E STOCKTON 402-RECOND 2,800' OF 6CU/W 2A | 02/25/2019 | 113266423 | 09/21/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 01/26/2021 | ED.16313.0402 | EAST STOCKTON 0402 | 039 | SAN JOAQUIN CO | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2019 | # | OPEN | 648 | 92.5714 | PEND | 5 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 8847.63
35077348 | RECONDUCTOR 17547 FT OF 4ACSR W 2CU TW | 03/05/2019 | 116579004 | 02/21/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 04/27/2020 | ED.18310.1103 | CABRILLO 1103 | 042 | SANTA BARBARA | 5535211 | CWSP SPO - SH 08 | 17,547.000 | 0.000 | 08W | 2019 | # | OPEN | 640 | 91.4286 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | RECONDUCTOR 17547FT 4ACSR W 2CU treewire | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 889.66
35077594 | OROSI 1101 RECOND 1140FT TO 2 ACSR | 03/07/2019 | 116678806 | 03/06/2019 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/29/2021 | ED.25284.1101 | OROSI 1101 | 054 | TULARE COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2019 | # | OPEN | 638 | 91.1429 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 1026.71
35077853 | *CANC*RECON 3269 FT OF 4ACSR WITH 2*CANC | 03/11/2019 | 116683820 | 03/07/2019 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/30/2021 | ED.18205.2102 | SOLEDAD 2102 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 3,269.000 | 0.000 | 08J | 2019 | 10/03/2020 | 2020 | 572 | 81.7143 | CLSD | 12 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2020-10-03 | 2020-10-03 | # | 2020-10-03 | 2020-10-03 | # | 2020-10-03 | 2020-10-03 | COMP | 2020-09-22 | 2020-09-22 | COMP | 2020-09-22 | 2020-09-22 | COMP | 2020-09-22 | 2020-09-22 | 0 | -11 | 0
35078713 | DIVIDE 1102 RECOND 4780 FT OF 4AR W 2CU | 03/13/2019 | 116720473 | 03/13/2019 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/30/2021 | ED.18257.1102 | DIVIDE 1102 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 4,780.000 | 0.000 | 08J | 2019 | # | OPEN | 632 | 90.2857 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 1232.04
35080227 | CALISTOGA 1101 - BENNETT LN RECONDUCTOR | 03/19/2019 | 116766403 | 03/19/2019 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2019 | ED.04271.1101 | CALISTOGA 1101 | 028 | NAPA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 1,876.000 | 08W | 2019 | # | OPEN | 626 | 89.4286 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 220053.23
35081660 | OH RECONDUCTOR - ROB ROY 2105 -S028CC119 | 03/27/2019 | # | #N/A | # | Not assigned | 30 | Technically Completed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 09/30/2019 | ED.76-O162000000.STRU.POLE | COAST O1620 POLES | 044 | SANTA CRUZ COU | 5517127 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08W | 2019 | # | OPEN | 618 | 88.2857 | DCNL | Other | E470 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Overhead Reductoring Project | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35081748 | OH RECONDUCTOR - ROB ROY 2105 -S028CC119 | 03/27/2019 | 113255642 | 09/15/2017 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/30/2019 | JY | JUNK YARD FL TO HOLD DELETED DATA | 044 | SANTA CRUZ COU | 5535211 | CWSP SPO - SH 08 | -1,617.000 | 1,425.000 | 08W | 2019 | 06/20/2020 | 2020 | 451 | 64.4286 | CLSD | 12 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | 35081748_OH RECONDUCTOR - ROB ROY 2105 - | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2020-02-19 | 2020-02-19 | COMP | 2020-02-24 | 2020-04-03 | COMP | 2020-04-03 | 2020-04-03 | COMP | 2020-04-03 | 2020-04-06 | COMP | 2020-04-06 | 2020-04-23 | COMP | 2020-04-23 | 2020-04-23 | 44 | 20 | 572757.07
35081862 | MARTELL 1101 RECOND. 4ACSR W/ 1/0AR TW | 03/28/2019 | 116833412 | 03/26/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.16301.1101 | MARTELL 1101 | 003 | AMADOR COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2019 | # | OPEN | 617 | 88.1429 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Martell 1101 Reconductor 8,034ft | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 2886.46
35082181 | WD: PENRYN 1106 19-0028718 RECON 35251 | 04/01/2019 | 116866493 | 03/29/2019 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2021 | ED.15256.1106.SWIT | SWITCHES | 031 | PLACER COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2019 | # | OPEN | 613 | 87.5714 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35084277 | PEACHTON 1101 RECON OUTAGE 19-0027596 | 04/08/2019 | 116967241 | 04/05/2019 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 08/31/2021 | ED.10324.1101 | PEACHTON 1101 | 004 | BUTTE COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2019 | # | OPEN | 606 | 86.5714 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 1003.03
35084460 | MALAGA 1102 - RECON 630FT 4CU WITH 2AR | 04/08/2019 | 116958235 | 04/04/2019 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/15/2021 | ED.25425.1102 | MALAGA 1102 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2019 | # | OPEN | 606 | 86.5714 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 401.2
35085393 | CWSP - SILVERADO 2104 - LR722 PH 1B | 04/10/2019 | 116951510 | 04/03/2019 | # | Not assigned | 30 | Technically Completed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.04343.2104 | SILVERADO 2104 | 028 | NAPA COUNTY | 5784860 | CWSP Silverado 2104 1B: Underground | 1,871.000 | 1,871.000 | 08W | 2019 | # | OPEN | 604 | 86.2857 | FICL | 10 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - NORTH BAY WILDFIRE HARDENING PROJ | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2019-10-17 | 2019-10-17 | COMP | 2020-04-01 | 2020-04-01 | COMP | 2020-04-01 | 2020-04-01 | COMP | 2020-04-01 | 2020-04-02 | COMP | 2020-04-02 | 2020-04-09 | COMP | 2020-04-09 | 2020-04-09 | 167 | 8 | 1254910.34
35085532 | CWSP - SILVERADO 2104 - LR722 PH 1C | 04/10/2019 | 116951517 | 04/03/2019 | # | Not assigned | 30 | Technically Completed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.04343.2104 | SILVERADO 2104 | 028 | NAPA COUNTY | 5786200 | CWSP - Silverado 2104 - Ph 2 | 5,936.000 | 5,948.000 | 08W | 2019 | # | OPEN | 604 | 86.2857 | FICL | 10 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - NORTH BAY WILDFIRE HARDENING PROJ | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2020-01-15 | 2020-01-15 | COMP | 2020-01-23 | 2020-04-01 | COMP | 2020-04-01 | 2020-04-01 | COMP | 2020-04-01 | 2020-10-28 | COMP | 2020-10-28 | 2020-11-09 | COMP | 2020-11-09 | 2020-11-11 | 77 | 224 | 2038180.58
35085533 | CWSP - SILVERADO 2104 - LR722 PH 1D | 04/10/2019 | 116951595 | 04/03/2019 | # | Not assigned | 30 | Technically Completed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.04343.2104 | SILVERADO 2104 | 028 | NAPA COUNTY | 5535211 | CWSP SPO - SH 08 | 5,365.000 | 5,365.000 | 08W | 2019 | # | OPEN | 604 | 86.2857 | FICL | 10 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - NORTH BAY WILDFIRE HARDENING PROJ | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2019-10-08 | 2019-10-08 | COMP | 2020-05-13 | 2020-07-31 | COMP | 2020-07-31 | 2020-07-31 | COMP | 2020-07-31 | 2020-08-04 | COMP | 2020-08-04 | 2020-08-13 | COMP | 2020-08-13 | 2020-08-17 | 297 | 17 | 1914739.98
35085534 | CWSP - SILVERADO 2104 - LR722 PH 1E | 04/10/2019 | 116951661 | 04/03/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.04343.2104 | SILVERADO 2104 | 028 | NAPA COUNTY | 5535211 | CWSP SPO - SH 08 | 4,191.000 | 4,191.000 | 08W | 2019 | # | OPEN | 604 | 86.2857 | DOCC | 8 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - NORTH BAY WILDFIRE HARDENING PROJ | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2020-05-18 | 2020-05-01 | INPR | 2020-02-21 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | -43969 | 0 | 1581062.02
35085535 | CWSP - SILVERADO 2104 - LR722 PH 1F | 04/10/2019 | 116951668 | 04/03/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.04343.2104 | SILVERADO 2104 | 028 | NAPA COUNTY | 5535211 | CWSP SPO - SH 08 | 8,793.000 | 8,793.000 | 08W | 2019 | # | OPEN | 604 | 86.2857 | DOCC | 8 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - NORTH BAY WILDFIRE HARDENING PROJ | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2020-05-18 | 2020-05-01 | INPR | 2020-02-06 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | -43969 | 0 | 2489757.73
35085536 | CWSP - SILVERADO 2104 - LR722 PH 1G | 04/10/2019 | 116951730 | 04/03/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.04343.2104 | SILVERADO 2104 | 028 | NAPA COUNTY | 5535211 | CWSP SPO - SH 08 | 6,569.000 | 7,010.000 | 08W | 2019 | # | OPEN | 604 | 86.2857 | DOCC | 8 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - NORTH BAY WILDFIRE HARDENING PROJ | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2019-12-09 | 2019-12-09 | INPR | 2019-12-11 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | -43808 | 0 | 1889152.58
35085537 | CWSP - SILVERADO 2104 - LR722 PH 1H | 04/10/2019 | 116951738 | 04/03/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.04343.2104 | SILVERADO 2104 | 028 | NAPA COUNTY | 5535211 | CWSP SPO - SH 08 | 3,442.000 | 3,442.000 | 08W | 2019 | # | OPEN | 604 | 86.2857 | DOCC | 8 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - NORTH BAY WILDFIRE HARDENING PROJ | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2020-01-17 | 2020-01-17 | INPR | 2020-05-13 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | -43847 | 0 | 1257493.91
35085538 | SILVERADO 2105 WIRE DOWN - PH 1 | 04/10/2019 | 116952145 | 04/03/2019 | # | Not assigned | 30 | Technically Completed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.04343.2105 | SILVERADO 2105 | 028 | NAPA COUNTY | 5535211 | CWSP SPO - SH 08 | 9,520.000 | 10,413.000 | 08W | 2019 | # | OPEN | 604 | 86.2857 | FICL | 10 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | REPL 17,500' of 4ar & 4cu in Tier 3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2020-08-01 | 2020-02-01 | COMP | 2020-04-29 | 2020-08-01 | COMP | 2020-08-01 | 2020-08-01 | COMP | 2020-08-01 | 2020-08-25 | COMP | 2020-08-25 | 2020-09-02 | COMP | 2020-09-02 | 2020-09-02 | 0 | 32 | 2766019.3
35085539 | SILVERADO 2105 WIRE DOWN - PH 2 | 04/10/2019 | 116952170 | 04/03/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.04343.2105 | SILVERADO 2105 | 028 | NAPA COUNTY | 5535211 | CWSP SPO - SH 08 | 34,020.000 | 34,020.000 | 08W | 2019 | # | OPEN | 604 | 86.2857 | DOCC | 8 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | REPL 17,500' of 4ar & 4cu in Tier 3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2020-05-21 | 2020-05-19 | INPR | 2020-05-13 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | -43972 | 0 | 2414483.57
35085680 | SILVERADO 2105 WIRE DOWN - PH 3 | 04/10/2019 | 116952175 | 04/03/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.04343.2105 | SILVERADO 2105 | 028 | NAPA COUNTY | 5535211 | CWSP SPO - SH 08 | 8,756.000 | 0.000 | 08W | 2019 | # | OPEN | 604 | 86.2857 | ESTS | 2 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | REPL 17,500' of 4ar & 4cu in Tier 3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 82651.74
35085681 | SILVERADO 2105 WIRE DOWN - PH 4 | 04/10/2019 | 116952176 | 04/03/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.04343.2105 | SILVERADO 2105 | 028 | NAPA COUNTY | 5535211 | CWSP SPO - SH 08 | 2,894.000 | 2,934.000 | 08W | 2019 | # | OPEN | 604 | 86.2857 | DOCC | 8 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | REPL 17,500' of 4ar & 4cu in Tier 3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2019-09-30 | 2019-09-30 | INPR | 2019-10-14 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | -43738 | 0 | 486634.62
35085847 | OH RECONDUCTOR - ROB ROY 2105 -S027CC118 | 04/11/2019 | 113255606 | 09/15/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/30/2019 | ED.76-O171800000.STRU.POLE | COAST O1718 POLES | 044 | SANTA CRUZ COU | 5535211 | CWSP SPO - SH 08 | 4,555.000 | 0.000 | 08W | 2019 | # | OPEN | 603 | 86.1429 | PEND | 5 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | 35085847_R2 OH RECONDUCTR ROB ROY 2105 S | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 62993.86
35086100 | *CANC*DO NOT USE* KINGSBURG 1111 RE*CANC | 04/15/2019 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/18/2020 | ED.25224.1111 | KINGSBURG 1111 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2019 | 05/03/2020 | 2020 | 384 | 54.8571 | CLSD | 12 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | COMP | 2020-04-08 | 2020-04-08 | COMP | 2020-04-08 | 2020-04-08 | COMP | 2020-04-08 | 2020-04-08 | 0 | -25 | 0
35086101 | KINGSBURG 1111 RECOND 4,010' OF 4 CU | 04/15/2019 | 113728913 | 10/13/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/31/2021 | ED.25224.1111 | KINGSBURG 1111 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2019 | # | OPEN | 599 | 85.5714 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 2556.85
35086535 | DINUBA 1104 RECOND 1,222' OF 1/O TO 2ACS | 04/17/2019 | 112659023 | 03/08/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/31/2021 | ED.25409.1104 | DINUBA 1104 | 054 | TULARE COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2019 | # | OPEN | 597 | 85.2857 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 951.96
35087416 | RECON7593FT OF 4ACSR W 2CU CABRILLO 1103 | 04/17/2019 | 117043109 | 04/16/2019 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/16/2021 | ED.18310.1103 | CABRILLO 1103 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 7,593.000 | 0.000 | 08J | 2019 | # | OPEN | 597 | 85.2857 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 616.02
35087857 | SM 1105 RECOND 1554 FT 4ACSR W 2CU | 04/19/2019 | 117054562 | 04/18/2019 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/30/2021 | ED.18267.1105 | SANTA MARIA 1105 | 040 | SAN LUIS OBISP | 5535457 | DO 08 - Monthly Forecast Only | 1,554.000 | 0.000 | 08J | 2019 | # | OPEN | 595 | 85 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 1012.51
35087859 | SM 1105 RECOND 2300 FT 4ACSR W 2CU | 04/19/2019 | 117054820 | 04/18/2019 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/30/2021 | ED.18267.1105 | SANTA MARIA 1105 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 2,300.000 | 0.000 | 08J | 2019 | # | OPEN | 595 | 85 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 815.45
35088357 | *CANC* RIO DELL 1101 RECNDTR FUSE 3*CANC | 04/22/2019 | 117051924 | 04/17/2019 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/29/2021 | ED.19225.1101.SWIT | SWITCHES | 012 | HUMBOLDT COUNT | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2019 | 07/03/2019 | 2019 | 72 | 10.2857 | CLSD | 12 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2019-07-03 | 2019-07-03 | # | 2019-07-03 | 2019-07-03 | # | 2019-07-03 | 2019-07-03 | COMP | 2019-06-12 | 2019-06-12 | COMP | 2019-06-12 | 2019-06-12 | COMP | 2019-06-12 | 2019-06-12 | 0 | -21 | 0
35088462 | RECOND GREEN VALLEY 2103 REF# S029CC120 | 04/26/2019 | 113663707 | 10/04/2017 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/29/2019 | ED.08319.2103 | GREEN VALLEY 2103 | 044 | SANTA CRUZ COU | 5517128 | DO 49 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2019 | # | OPEN | 588 | 84 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | RECOND GREEN VALLEY 2103 REF# S029CC120 | Base Capital | GRC Distribution Common | GRC | CUSTCARE | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35089227 | BIOLA 1104 RECONDUCTOR 2,995 FT OF 6CU | 04/25/2019 | 117090052 | 04/24/2019 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 07/30/2020 | ED.25221.1104 | BIOLA 1104 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 1,360.000 | 0.000 | 08J | 2019 | # | OPEN | 589 | 84.1429 | PEND | 5 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 33328.13
35089880 | OCGC PIH SILVERADO 2104 - ANGWIN UG_PH 2 | 04/25/2019 | 117092838 | 04/24/2019 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.04343.2104 | SILVERADO 2104 | 028 | NAPA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 2,117.000 | 08W | 2019 | 08/29/2020 | 2020 | 492 | 70.2857 | CLSD | 12 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2019-10-09 | 2019-10-09 | COMP | 2019-10-29 | 2019-10-29 | COMP | 2019-10-29 | 2019-10-29 | COMP | 2019-11-25 | 2020-04-06 | COMP | 2020-04-06 | 2020-06-05 | COMP | 2020-06-05 | 2020-06-05 | 20 | 220 | 1712851.42
35093737 | FAIRVIEW 2207-CROCKETT BLVD-WIRE DOWN | 04/30/2019 | 117123046 | 04/29/2019 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.01343.2207 | FAIRVIEW 2207 | 007 | CONTRA COSTA C | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2019 | # | OPEN | 584 | 83.4286 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 560
35094044 | REEDLEY 1106 RECOND 2403FT TO 2AR | 05/01/2019 | 117129391 | 04/30/2019 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/29/2021 | ED.25234.1106 | REEDLEY 1106 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2019 | # | OPEN | 583 | 83.2857 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35094388 | CWSP-KONOCTI 1102-LR 532 PH 1 | 05/01/2019 | 117130851 | 04/30/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 11/30/2020 | ED.04331.1102.SWIT | SWITCHES | 017 | LAKE COUNTY | 5535211 | CWSP SPO - SH 08 | 2,241.000 | 2,241.000 | 08W | 2019 | # | OPEN | 583 | 83.2857 | MAPP | 9 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-KONOCTI 1102-LR 532 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2019-09-23 | 2019-09-23 | COMP | 2019-09-23 | 2020-02-06 | COMP | 2020-02-06 | 2020-02-06 | INPR | 2020-02-12 | 0 | # | 0 | 0 | # | 0 | 0 | 136 | -43867 | 397054.5
35094389 | CWSP-KONOCTI 1102-LR 532 PH 2 | 05/01/2019 | 117130852 | 04/30/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 11/30/2020 | ED.04331.1102.SWIT | SWITCHES | 017 | LAKE COUNTY | 5535211 | CWSP SPO - SH 08 | 2,741.000 | 0.000 | 08W | 2019 | # | OPEN | 583 | 83.2857 | ESTS | 2 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-KONOCTI 1102-LR 532 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 71900.01
35094390 | CWSP-KONOCTI 1102-LR 532 PH 3 | 05/01/2019 | 117130853 | 04/30/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 11/30/2020 | ED.04331.1102.SWIT | SWITCHES | 017 | LAKE COUNTY | 5535211 | CWSP SPO - SH 08 | 2,884.000 | 2,881.000 | 08W | 2019 | # | OPEN | 583 | 83.2857 | DOCC | 8 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-KONOCTI 1102-LR 532 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2019-12-16 | 2019-12-16 | INPR | 2020-05-13 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | -43815 | 0 | 878958.2
35094391 | CWSP-KONOCTI 1102-LR 532 PH 4 | 05/01/2019 | 117130854 | 04/30/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 11/30/2020 | ED.04331.1102.SWIT | SWITCHES | 017 | LAKE COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2019 | # | OPEN | 583 | 83.2857 | UNSC | 6 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-KONOCTI 1102-LR 532 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 21880.49
35094392 | OCGC CWSP-KONOCTI 1102-LR 532 PH 5 | 05/01/2019 | 117130855 | 04/30/2019 | # | Not assigned | 30 | Technically Completed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 11/30/2020 | ED.04331.1102.SWIT | SWITCHES | 017 | LAKE COUNTY | 5535211 | CWSP SPO - SH 08 | 1,956.000 | 1,956.000 | 08W | 2019 | # | OPEN | 583 | 83.2857 | FICL | 10 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-KONOCTI 1102-LR 532 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2019-12-04 | 2019-12-04 | COMP | 2019-12-11 | 2019-12-11 | COMP | 2019-12-11 | 2019-12-11 | COMP | 2020-01-22 | 2020-02-26 | COMP | 2020-02-26 | 2020-02-27 | COMP | 2020-02-27 | 2020-03-05 | 7 | 85 | 263113.32
35094393 | OCGC KONOCTI - 1102 - LR 532 PH 6 (OH) | 05/01/2019 | 117130856 | 04/30/2019 | # | Not assigned | 30 | Technically Completed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 11/30/2020 | ED.04331.1102.SWIT | SWITCHES | 017 | LAKE COUNTY | 5535211 | CWSP SPO - SH 08 | 10,642.000 | 0.000 | 08W | 2019 | # | OPEN | 583 | 83.2857 | FICL | 10 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-KONOCTI 1102-LR 532 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2020-08-05 | 2020-08-05 | COMP | 2020-08-11 | 2020-08-11 | COMP | 2020-08-11 | 2020-08-11 | COMP | 2020-08-11 | 2020-08-12 | COMP | 2020-08-12 | 2020-09-23 | COMP | 2020-09-23 | 2020-09-23 | 6 | 43 | 1299297.67
35094394 | CWSP-KONOCTI 1102-LR 532 PH 7 | 05/01/2019 | 117130857 | 04/30/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 11/30/2020 | ED.04331.1102.SWIT | SWITCHES | 017 | LAKE COUNTY | 5535211 | CWSP SPO - SH 08 | 7,765.000 | 0.000 | 08W | 2019 | # | OPEN | 583 | 83.2857 | CONS | 7 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-KONOCTI 1102-LR 532 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 1193468.64
35094395 | CWSP-KONOCTI 1102-LR 532 PH 8 | 05/01/2019 | 117130858 | 04/30/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 11/30/2020 | ED.04331.1102.SWIT | SWITCHES | 017 | LAKE COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2019 | # | OPEN | 583 | 83.2857 | ESTS | 2 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-KONOCTI 1102-LR 532 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 55057.57
35094396 | CWSP-KONOCTI 1102-LR 532 PH 9 | 05/01/2019 | 117130859 | 04/30/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 11/30/2020 | ED.04331.1102.SWIT | SWITCHES | 017 | LAKE COUNTY | 5535211 | CWSP SPO - SH 08 | 4,351.000 | 0.000 | 08W | 2019 | # | OPEN | 583 | 83.2857 | UNSC | 6 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-KONOCTI 1102-LR 532 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 25276.49
35094397 | CWSP-KONOCTI 1102-LR 532 PH 10 | 05/01/2019 | 117131100 | 04/30/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 11/30/2020 | ED.04331.1102.SWIT | SWITCHES | 017 | LAKE COUNTY | 5535211 | CWSP SPO - SH 08 | 5,621.000 | 0.000 | 08W | 2019 | # | OPEN | 583 | 83.2857 | CONS | 7 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-KONOCTI 1102-LR 532 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 684703.36
35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 | 05/03/2019 | 114567769 | 05/04/2018 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/20/2021 | ED.16282.1702 | STANISLAUS 1702 | 005 | CALAVERAS COUN | 5535211 | CWSP SPO - SH 08 | 10,124.000 | 0.000 | 08W | 2019 | # | OPEN | 581 | 83 | PEND | 5 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | STANISLAUS 1702 LR1804 ZONE WFH LEVEL 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 139064.69
35094514 | CWSP-ORO FINO 1101 LR-2022 PH 1.1 | 05/03/2019 | 114655579 | 06/01/2018 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1101 | ORO FINO 1101 | 004 | BUTTE COUNTY | 5535211 | CWSP SPO - SH 08 | 6,367.000 | 0.000 | 08W | 2019 | # | OPEN | 581 | 83 | PEND | 5 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - ORO FINO-1101 LR-2022 PH I | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 63943.84
35094515 | CWSP-ORO FINO 1101-LR 2022 PH 2.1 | 05/03/2019 | 114656547 | 06/01/2018 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1101 | ORO FINO 1101 | 004 | BUTTE COUNTY | 5535211 | CWSP SPO - SH 08 | 7,564.000 | 0.000 | 08W | 2019 | # | OPEN | 581 | 83 | ESTS | 2 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - ORO FINO-1101 LR-2022 PH 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 10955.2
35094516 | CWSP-ORO FINO 1101 OCB PH 1.1 | 05/03/2019 | 114668686 | 06/06/2018 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1101 | ORO FINO 1101 | 004 | BUTTE COUNTY | 5535211 | CWSP SPO - SH 08 | 13,173.000 | 0.000 | 08W | 2019 | # | OPEN | 581 | 83 | PEND | 5 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-ORO FINO 1101 OCB PH 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 39163.15
35094517 | CWSP-ORO FINO 1101 OCB PH 2.1 | 05/03/2019 | 114668689 | 06/06/2018 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1101 | ORO FINO 1101 | 004 | BUTTE COUNTY | 5535211 | CWSP SPO - SH 08 | 9,840.000 | 0.000 | 08W | 2019 | # | OPEN | 581 | 83 | PEND | 5 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-ORO FINO 1101 OCB PH 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 67414.27
35094518 | CWSP-ORO FINO 1101 OCB PH 3.1 | 05/03/2019 | 114668862 | 06/06/2018 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1101 | ORO FINO 1101 | 004 | BUTTE COUNTY | 5535211 | CWSP SPO - SH 08 | 11,132.000 | 0.000 | 08W | 2019 | # | OPEN | 581 | 83 | ADER | 3 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-ORO FINO 1101 OCB PH 3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 13414.89
35094519 | CWSP-ORO FINO 1102 LR-2560 PH 1 | 05/03/2019 | 114708278 | 06/18/2018 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1102 | ORO FINO 1102 | 004 | BUTTE COUNTY | 5535211 | CWSP SPO - SH 08 | 9,589.000 | 0.000 | 08W | 2019 | # | OPEN | 581 | 83 | ADER | 3 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-ORO FINO 1102 LR-2560 PH 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 132163.69
35095160 | CWSP-ORO FINO 1102 LR-2560 PH 2.1 | 05/03/2019 | 114708381 | 06/18/2018 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1102 | ORO FINO 1102 | 004 | BUTTE COUNTY | 5535211 | CWSP SPO - SH 08 | 9,226.000 | 0.000 | 08W | 2019 | # | OPEN | 581 | 83 | ADER | 3 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-ORO FINO 1102 LR-2560 PH 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 43112.53
35095161 | CWSP-ORO FINO 1102 LR-76008 PH 1.1 | 05/03/2019 | 114708383 | 06/18/2018 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1102 | ORO FINO 1102 | 004 | BUTTE COUNTY | 5535211 | CWSP SPO - SH 08 | 4,730.000 | 0.000 | 08W | 2019 | # | OPEN | 581 | 83 | PEND | 5 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-ORO FINO 1102 LR-76008 PH 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 100820.79
35095162 | CWSP-ORO FINO 1102 LR-76008 PH 2.1 | 05/03/2019 | 114708386 | 06/18/2018 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1102 | ORO FINO 1102 | 004 | BUTTE COUNTY | 5535211 | CWSP SPO - SH 08 | 6,960.000 | 0.000 | 08W | 2019 | # | OPEN | 581 | 83 | ESTS | 2 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-ORO FINO 1102 LR-76008 PH 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 127890.51
35095163 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.1 | 05/03/2019 | 114708366 | 06/18/2018 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.16375.1102.SWIT | SWITCHES | 003 | AMADOR COUNTY | 5535211 | CWSP SPO - SH 08 | 7,554.000 | 0.000 | 08W | 2019 | # | OPEN | 581 | 83 | ADER | 3 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP: PINE GROVE 1102 LR1222 ZONE WFH PH | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 61815.48
35095164 | CWSP-ORO FINO 1101 LR-2022 PH 3.1 | 05/03/2019 | 114723712 | 06/22/2018 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1101 | ORO FINO 1101 | 004 | BUTTE COUNTY | 5535211 | CWSP SPO - SH 08 | 10,229.000 | 0.000 | 08W | 2019 | # | OPEN | 581 | 83 | UNSC | 6 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-ORO FINO 1101 LR-2022 PH 3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 184680.49
35095165 | CWSP - VOLTA 1102 - LR 1648 -PH 3.1 | 05/03/2019 | 114761296 | 07/09/2018 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | JY | JUNK YARD FL TO HOLD DELETED DATA | 045 | SHASTA COUNTY | 5535211 | CWSP SPO - SH 08 | 3,843.000 | 3,666.000 | 08W | 2019 | # | OPEN | 581 | 83 | DOCC | 8 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - VOLTA 1102 - LR 1648 -PHASE 3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2019-11-25 | 2019-11-25 | INPR | 2019-11-25 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | -43794 | 0 | 3095085.26
35095166 | CWSP - EL DORADO 2102 - LR19562 - PH 1.0 | 05/03/2019 | 114742467 | 06/29/2018 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2019 | ED.15276.2102.SWIT | SWITCHES | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 7,328.000 | 7,419.000 | 08W | 2019 | # | OPEN | 581 | 83 | DOCC | 8 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - EL DORADO PH 2102 - LR 19562 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2020-08-21 | 2020-08-21 | INPR | 2020-08-24 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | -44064 | 0 | 1317588.18
35095167 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.1 | 05/03/2019 | 114832579 | 07/30/2018 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.16282.1702 | STANISLAUS 1702 | 005 | CALAVERAS COUN | 5535211 | CWSP SPO - SH 08 | 5,899.000 | 0.000 | 08W | 2019 | # | OPEN | 581 | 83 | PEND | 5 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-STANISLAUS1702-LR1888-PH2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 135741.9
35095168 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.1 | 05/03/2019 | 114832575 | 07/30/2018 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.16282.1702 | STANISLAUS 1702 | 005 | CALAVERAS COUN | 5535211 | CWSP SPO - SH 08 | 6,718.000 | 0.000 | 08W | 2019 | # | OPEN | 581 | 83 | PEND | 5 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-STANISLAUS1702-LR1888-PH1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 206660.33
35095246 | BUCOCAMP - ERIKA DRIVE, PARADISE | 05/05/2019 | 117164122 | 05/05/2019 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/27/2019 | JY | JUNK YARD FL TO HOLD DELETED DATA | 004 | BUTTE COUNTY | 5786123 | 08W Rebuild | 0.000 | 0.000 | 08W | 2019 | # | OPEN | 579 | 82.7143 | PEND | 5 | E460 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 136580.24
35098578 | CWSP-COLUMBIA HILL 1101-LR 2212 PH2 | 05/08/2019 | 117177287 | 05/07/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 11/19/2019 | ED.15247.1101.SWIT | SWITCHES | 029 | NEVADA COUNTY | 5535211 | CWSP SPO - SH 08 | 9,457.000 | 9,470.000 | 08W | 2019 | # | OPEN | 576 | 82.2857 | DOCC | 8 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-COLUMBIA HILL 1101-LR 2212 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2020-09-22 | 2019-12-03 | COMP | 2019-12-27 | 2020-09-22 | COMP | 2020-09-22 | 2020-09-22 | COMP | 2020-09-22 | 2020-11-06 | COMP | 2020-11-06 | 2020-11-18 | COMP | 2020-11-18 | 2020-11-18 | 0 | 57 | 3489548.87
35098579 | CWSP-COLUMBIA HILL 1101-LR 2212 PH3 | 05/08/2019 | 117177288 | 05/07/2019 | # | Not assigned | 40 | Closed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 10/07/2019 | ED.15247.1101.SWIT | SWITCHES | 029 | NEVADA COUNTY | 5535211 | CWSP SPO - SH 08 | 7,417.000 | 7,573.000 | 08W | 2019 | 11/21/2020 | 2020 | 563 | 80.4286 | CLSD | 12 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-COLUMBIA HILL 1101-LR 2212 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2019-10-07 | 2019-10-07 | COMP | 2019-10-09 | 2020-02-28 | COMP | 2020-02-28 | 2020-02-28 | COMP | 2020-03-26 | 2020-11-09 | COMP | 2020-11-09 | 2020-11-12 | COMP | 2020-11-12 | 2020-11-12 | 144 | 258 | 1955970.91
35098621 | CWSP-COLUMBIA HILL 1101-LR 2212 PH4 | 05/08/2019 | 117177530 | 05/07/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 11/30/2020 | ED.15247.1101.SWIT | SWITCHES | 029 | NEVADA COUNTY | 5535211 | CWSP SPO - SH 08 | 5,642.000 | 5,706.000 | 08W | 2019 | # | OPEN | 576 | 82.2857 | CONS | 7 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-COLUMBIA HILL 1101-LR 2212 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | INPR | 2020-05-14 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 1003972.02
35098622 | CWSP-COLUMBIA HILL 1101-LR 2212 PH5 | 05/08/2019 | 117177533 | 05/07/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 11/25/2019 | ED.15247.1101.SWIT | SWITCHES | 029 | NEVADA COUNTY | 5535211 | CWSP SPO - SH 08 | 12,854.000 | 13,101.000 | 08W | 2019 | # | OPEN | 576 | 82.2857 | DOCC | 8 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-COLUMBIA HILL 1101-LR 2212 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2020-09-25 | 2019-12-09 | COMP | 2019-11-25 | 2020-09-25 | COMP | 2020-09-25 | 2020-09-25 | COMP | 2020-09-25 | 2020-09-29 | COMP | 2020-09-29 | 2020-10-09 | COMP | 2020-10-09 | 2020-10-13 | 0 | 18 | 3808676.32
35098747 | SHEPHERD 2109 RECOND 3,780FT WITH 4/O AL | 05/09/2019 | 117183017 | 05/08/2019 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/29/2021 | ED.25206.2109 | SHEPHERD 2109 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2019 | # | OPEN | 575 | 82.1429 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 2855.51
35099603 | MORRO BAY 1102 RECON 4728 FT W TW | 05/10/2019 | 117211021 | 05/10/2019 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/13/2020 | ED.18301.1102 | MORRO BAY 1102 | 040 | SAN LUIS OBISP | 5535211 | CWSP SPO - SH 08 | 4,728.000 | 0.000 | 08W | 2019 | # | OPEN | 574 | 82 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35099654 | BR-04-01-W (E) SUNSET DR PARB | 05/11/2019 | 117212284 | 05/10/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/27/2019 | ED.17-S332200000.STRU.POLE | PARADISE S3322 POLES | 004 | BUTTE COUNTY | 5786123 | 08W Rebuild | 0.000 | 0.000 | 08W | 2019 | # | OPEN | 573 | 81.8571 | DOCC | 8 | E470 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2020-02-10 | 2020-02-10 | COMP | 2020-10-28 | 2020-10-28 | COMP | 2020-10-28 | 2020-10-29 | INPR | 2020-10-29 | 0 | # | 0 | 0 | # | 0 | 0 | 262 | -44133 | 589661.72
35100323 | GRAND ISLAND 2226 RECOND 2600 FEET OF OH | 05/14/2019 | 113062127 | 07/19/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.06246.2226.SWIT | SWITCHES | 048 | SOLANO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 2,242.000 | 0.000 | 08J | 2019 | # | OPEN | 570 | 81.4286 | CONS | 7 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | INPR | 2020-08-13 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 42068.92
35101875 | BR-01-10-W (E) BILLIE & LUCKY JOHN PARB | 05/15/2019 | 117243977 | 05/15/2019 | # | Not assigned | 30 | Technically Completed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/27/2019 | JY | JUNK YARD FL TO HOLD DELETED DATA | 004 | BUTTE COUNTY | 5786123 | 08W Rebuild | 0.000 | 0.000 | 08W | 2019 | # | OPEN | 569 | 81.2857 | FICL | 10 | E460 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2020-03-19 | 2020-03-19 | COMP | 2019-09-12 | 2020-08-04 | COMP | 2020-08-04 | 2020-08-04 | COMP | 2020-08-04 | 2020-08-06 | COMP | 2020-08-06 | 2020-08-19 | COMP | 2020-08-19 | 2020-08-21 | 138 | 17 | 1062109.83
35101876 | BR-01-08-W (E) MADRONE_BILLE_GRAHAM PARB | 05/15/2019 | 117244453 | 05/15/2019 | # | Not assigned | 30 | Technically Completed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/27/2019 | JY | JUNK YARD FL TO HOLD DELETED DATA | 004 | BUTTE COUNTY | 5786123 | 08W Rebuild | 3,407.000 | 0.000 | 08W | 2019 | # | OPEN | 569 | 81.2857 | FICL | 10 | E460 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2020-03-24 | 2020-03-24 | COMP | 2020-06-16 | 2020-06-16 | COMP | 2020-06-16 | 2020-06-16 | COMP | 2020-06-16 | 2020-06-17 | COMP | 2020-06-17 | 2020-06-30 | COMP | 2020-06-30 | 2020-07-04 | 84 | 18 | 1055029.06
35101877 | BR-01-06-W (E) THOMASSON LN PARB | 05/15/2019 | 117244755 | 05/15/2019 | # | Not assigned | 30 | Technically Completed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/27/2019 | ED.17-S331800000.STRU.POLE | PARADISE S3318 POLES | 004 | BUTTE COUNTY | 5786123 | 08W Rebuild | 6,358.000 | 0.000 | 08W | 2019 | # | OPEN | 569 | 81.2857 | FICL | 10 | E460 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2020-02-02 | 2020-02-02 | COMP | 2020-07-08 | 2020-07-08 | COMP | 2020-07-08 | 2020-07-10 | COMP | 2020-07-10 | 2020-07-13 | COMP | 2020-07-13 | 2020-07-20 | COMP | 2020-07-20 | 2020-07-20 | 159 | 10 | 2341077.4
35103065 | CWSP - MORAGA 1101 - LR 108540 PH 1 | 05/16/2019 | 114592041 | 05/10/2018 | # | Not assigned | 30 | Technically Completed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/18/2019 | ED.01380.1101 | MORAGA 1101 | 007 | CONTRA COSTA C | 5535211 | CWSP SPO - SH 08 | 12,588.000 | 12,151.000 | 08W | 2019 | # | OPEN | 568 | 81.1429 | FICL | 10 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - MORAGA 1101 (VARIOUS) - OCB | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2019-12-18 | 2019-12-18 | COMP | 2019-10-04 | 2020-01-23 | COMP | 2020-01-23 | 2020-01-23 | COMP | 2020-03-09 | 2020-08-03 | COMP | 2020-08-03 | 2020-08-07 | COMP | 2020-08-07 | 2020-08-07 | 36 | 197 | 4790991.91
35103323 | CWSP - MORAGA 1101 - LR 108540 - PH 2 | 05/17/2019 | 117251172 | 05/16/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.01380.1101 | MORAGA 1101 | 007 | CONTRA COSTA C | 5535211 | CWSP SPO - SH 08 | 6,489.000 | 5,368.000 | 08W | 2019 | # | OPEN | 567 | 81 | DOCC | 8 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - MORAGA 1101 (VARIOUS) - OCB | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2020-02-25 | 2020-02-25 | COMP | 2020-05-01 | 2020-05-01 | COMP | 2020-05-01 | 2020-05-01 | COMP | 2020-06-02 | 2020-06-25 | COMP | 2020-06-25 | 2020-09-16 | COMP | 2020-09-16 | 2020-09-16 | 66 | 138 | 3091248.54
35103324 | CWSP - ROSSMOOR 1102 - OCB | 05/17/2019 | 117251430 | 05/16/2019 | # | Not assigned | 35 | Pre-Closed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.01416.1102 | ROSSMOOR 1102 | 007 | CONTRA COSTA C | 5535211 | CWSP SPO - SH 08 | 4,046.000 | 4,046.000 | 08W | 2019 | # | OPEN | 567 | 81 | PREC | 11 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - MORAGA 1101 (VARIOUS) - OCB | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2020-03-17 | 2020-03-17 | COMP | 2019-10-01 | 2020-05-11 | COMP | 2020-05-11 | 2020-05-11 | COMP | 2020-05-11 | 2020-05-12 | COMP | 2020-05-12 | 2020-05-26 | COMP | 2020-05-26 | 2020-05-27 | 55 | 16 | 2335945.42
35103325 | CWSP - MORAGA 1102 & 1104 - OCB | 05/17/2019 | 117252070 | 05/16/2019 | # | Not assigned | 30 | Technically Completed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 04/14/2020 | ED.01380.1102 | MORAGA 1102 | 007 | CONTRA COSTA C | 5535211 | CWSP SPO - SH 08 | 6,506.000 | 6,916.000 | 08W | 2019 | # | OPEN | 567 | 81 | FICL | 10 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - MORAGA 1101 (VARIOUS) - OCB | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2020-04-14 | 2020-04-14 | COMP | 2020-03-09 | 2020-06-22 | COMP | 2020-06-22 | 2020-06-22 | COMP | 2020-07-28 | 2020-10-23 | COMP | 2020-10-23 | 2020-11-02 | COMP | 2020-11-02 | 2020-11-02 | 69 | 133 | 4605839.19
35103617 | BR-07-09-W (E) WOODGLEN PARB | 05/20/2019 | 117281820 | 05/20/2019 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/27/2019 | JY | JUNK YARD FL TO HOLD DELETED DATA | 004 | BUTTE COUNTY | 5786123 | 08W Rebuild | 0.000 | 0.000 | 08W | 2019 | # | OPEN | 564 | 80.5714 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35103619 | BR-10-03-W (E) FILBERT PARB | 05/20/2019 | 117287031 | 05/20/2019 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/27/2019 | ED.17-T321500000.STRU.POLE | PARADISE T3215 POLES | 004 | BUTTE COUNTY | 5786123 | 08W Rebuild | 0.000 | 0.000 | 08W | 2019 | # | OPEN | 564 | 80.5714 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35103942 | BR-09-03-W (E) CONNIE CIR PARB | 05/20/2019 | 117288421 | 05/20/2019 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/27/2019 | ED.17-T321000000.STRU.POLE | PARADISE T3210 POLES | 004 | BUTTE COUNTY | 5786123 | 08W Rebuild | 0.000 | 0.000 | 08W | 2019 | # | OPEN | 564 | 80.5714 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35104252 | BR-05-05-W (E) CENTRAL PARK PARB | 05/21/2019 | 117292725 | 05/21/2019 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/27/2019 | ED.17-T330300000.STRU.POLE | PARADISE T3303 POLES | 004 | BUTTE COUNTY | 5786123 | 08W Rebuild | 0.000 | 0.000 | 08W | 2019 | # | OPEN | 563 | 80.4286 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35105559 | RE-CON 7128 FT OF 4ACSR W 4/0 AL | 05/22/2019 | 117291692 | 05/21/2019 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/21/2021 | ED.18304.1101 | BUELLTON 1101 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 7,128.000 | 0.000 | 08J | 2019 | # | OPEN | 562 | 80.2857 | ESTS | 2 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 3815.04
35105573 | 2021 RIO DELL 1101 RECONDUCTOR FUSE 3445 | 05/22/2019 | 117303760 | 05/22/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 10/29/2021 | ED.19225.1101.SWIT | SWITCHES | 012 | HUMBOLDT COUNT | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2019 | # | OPEN | 562 | 80.2857 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 214.68
35105646 | BR-03-05-W (E) DEAN RD, PARB | 05/23/2019 | 117306439 | 05/23/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/27/2019 | ED.17-S341300000.STRU.POLE | PARADISE S3413 POLES | 004 | BUTTE COUNTY | 5786123 | 08W Rebuild | 0.000 | 0.000 | 08W | 2019 | # | OPEN | 561 | 80.1429 | CONS | 7 | E470 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 636269.07
35105647 | BR-03-09-W (E) MERRILL RD PARB | 05/23/2019 | 117306975 | 05/23/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/27/2019 | ED.17-S341800000.STRU.POLE | PARADISE S3418 POLES | 004 | BUTTE COUNTY | 5786123 | 08W Rebuild | 0.000 | 0.000 | 08W | 2019 | # | OPEN | 561 | 80.1429 | CONS | 7 | E470 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 1698863.77
35105649 | BR-14-02-W (E) DRENDEL PARB | 05/23/2019 | 117307198 | 05/23/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/27/2019 | ED.17-T341400000.STRU.POLE | PARADISE T3414 POLES | 004 | BUTTE COUNTY | 5786123 | 08W Rebuild | 0.000 | 0.000 | 08W | 2019 | # | OPEN | 561 | 80.1429 | DOCC | 8 | E470 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2020-03-10 | 2020-03-10 | COMP | 2020-10-28 | 2020-10-28 | COMP | 2020-10-28 | 2020-10-29 | INPR | 2020-10-29 | 0 | # | 0 | 0 | # | 0 | 0 | 233 | -44133 | 857010.04
35105650 | BR-08-06-W (E) FICKETT LN PARB | 05/23/2019 | 117307360 | 05/23/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/27/2019 | JY | JUNK YARD FL TO HOLD DELETED DATA | 004 | BUTTE COUNTY | 5786123 | 08W Rebuild | 0.000 | 0.000 | 08W | 2019 | # | OPEN | 561 | 80.1429 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 210069.63
35105653 | BR-14-01-W (E) SALIDA WAY, PARB | 05/23/2019 | 117307657 | 05/23/2019 | 35127553 | BR-14-01-O (E) SALIDA WAY PARB | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/27/2019 | ED.17-T341300000.STRU.POLE | PARADISE T3413 POLES | 004 | BUTTE COUNTY | 5786123 | 08W Rebuild | 0.000 | 0.000 | 08W | 2019 | # | OPEN | 561 | 80.1429 | PEND | 5 | E470 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 392832.02
35105656 | BR-04-02-W (E) CASTLE DR PARB | 05/23/2019 | 117308283 | 05/23/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/27/2019 | JY | JUNK YARD FL TO HOLD DELETED DATA | 004 | BUTTE COUNTY | 5786123 | 08W Rebuild | 0.000 | 0.000 | 08W | 2019 | # | OPEN | 561 | 80.1429 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 13772.21
35106042 | CWSP - VOLTA 1102 - LR 1648 - PH1.2 | 05/24/2019 | 117316187 | 05/24/2019 | # | Not assigned | 30 | Technically Completed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | JY | JUNK YARD FL TO HOLD DELETED DATA | 045 | SHASTA COUNTY | 5535211 | CWSP SPO - SH 08 | 9,606.000 | 9,607.000 | 08W | 2019 | # | OPEN | 560 | 80 | FICL | 10 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Volta 1102 - LR 1648 - Ph1.1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2020-08-31 | 2020-06-08 | COMP | 2019-10-15 | 2020-08-31 | COMP | 2020-08-31 | 2020-08-31 | COMP | 2020-08-31 | 2020-09-01 | COMP | 2020-09-01 | 2020-10-09 | COMP | 2020-10-09 | 2020-10-14 | 0 | 44 | 1481678.96
35106067 | REPLC WIRE-CASTROVILLE2104 WD#19-0048862 | 05/24/2019 | 117310755 | 05/23/2019 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/30/2021 | ED.18235.2104 | CASTROVILLE 2104 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 5,895.000 | 0.000 | 08J | 2019 | # | OPEN | 560 | 80 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 401.38
35106265 | CWSP - VOLTA 1102 - LR 1648 - PH1.3 | 05/28/2019 | 117316465 | 05/24/2019 | # | Not assigned | 30 | Technically Completed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | JY | JUNK YARD FL TO HOLD DELETED DATA | 045 | SHASTA COUNTY | 5535211 | CWSP SPO - SH 08 | 10,118.000 | 9,489.000 | 08W | 2019 | # | OPEN | 556 | 79.4286 | FICL | 10 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Volta 1102 - LR 1648 - Ph1.1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2020-06-08 | 2020-06-08 | COMP | 2019-10-15 | 2020-08-31 | COMP | 2020-08-31 | 2020-08-31 | COMP | 2020-08-31 | 2020-08-31 | COMP | 2020-08-31 | 2020-09-08 | COMP | 2020-09-08 | 2020-09-08 | 84 | 8 | 1132079.03
35106267 | WEST FRESNO 1101 RECOND 1,410FT WITH 2AR | 05/28/2019 | 117328156 | 05/28/2019 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/29/2021 | ED.25373.1101 | WEST FRESNO 1101 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2019 | # | OPEN | 556 | 79.4286 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 2596.7
35106331 | CWSP - VOLTA 1102 - LR 1648 - PH1.4 | 05/28/2019 | 117316591 | 05/24/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.87-Q421500000.STRU.POLE | SHASTA Q4215 POLES | 045 | SHASTA COUNTY | 5535211 | CWSP SPO - SH 08 | 12,968.000 | 13,119.000 | 08W | 2019 | # | OPEN | 556 | 79.4286 | DOCC | 8 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Volta 1102 - LR 1648 - Ph1.1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2020-05-28 | 2020-05-28 | INPR | 2019-10-15 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | -43979 | 0 | 2815980.85
35107688 | CWSP - VOLTA 1102 - LR 1648 -PH1.1 | 05/29/2019 | 114645026 | 05/30/2018 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/30/2020 | ED.10254.1102.RECL | RECLOSERS | 045 | SHASTA COUNTY | 5535211 | CWSP SPO - SH 08 | 8,626.000 | 8,610.000 | 08W | 2019 | # | OPEN | 555 | 79.2857 | DOCC | 8 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Volta 1102 - LR 1648 - Ph1.1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2020-04-10 | 2020-04-10 | INPR | 2020-04-17 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | -43931 | 0 | 1544112.04
35107689 | OCGC CWSP - PINE GROVE 1102 - LR1222 - | 05/30/2019 | 114660964 | 06/04/2018 | # | Not assigned | 30 | Technically Completed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.16375.1102.RECL | RECLOSERS | 003 | AMADOR COUNTY | 5535211 | CWSP SPO - SH 08 | 10,648.000 | 11,292.000 | 08W | 2019 | # | OPEN | 554 | 79.1429 | FICL | 10 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP: PINE GROVE 1102 LR1222 PH 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2020-05-11 | 2020-05-11 | COMP | 2020-05-15 | 2020-05-15 | COMP | 2020-05-15 | 2020-05-15 | COMP | 2020-05-15 | 2020-05-19 | COMP | 2020-05-19 | 2020-07-13 | COMP | 2020-07-13 | 2020-07-17 | 4 | 63 | 2565589.03
35107837 | WD-WATERLOO 1102 -OCB Z -ILIS 190050626 | 05/29/2019 | 117336260 | 05/29/2019 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2021 | ED.93-T120000000.STRU.POLE | STOCKTON T12 POLES | 039 | SAN JOAQUIN CO | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2019 | # | OPEN | 555 | 79.2857 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | 06/03/2019 | 117348505 | 05/30/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/30/2020 | ED.15276.2101 | EL DORADO PH 2101 | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 7,492.000 | 7,214.000 | 08W | 2019 | # | OPEN | 550 | 78.5714 | DOCC | 8 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - El Dorado 2101 - 19752 - Ph 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2020-02-18 | 2020-02-18 | INPR | 2019-10-15 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | -43879 | 0 | 1628439.37
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | 06/03/2019 | 117348508 | 05/30/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/30/2020 | ED.15276.2101 | EL DORADO PH 2101 | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 14,086.000 | 0.000 | 08W | 2019 | # | OPEN | 550 | 78.5714 | ESTS | 2 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - El Dorado 2101 - 19752 - Ph 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 49210.61
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | 06/03/2019 | 117349210 | 05/30/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/30/2020 | ED.15276.2101 | EL DORADO PH 2101 | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 9,526.000 | 9,673.000 | 08W | 2019 | # | OPEN | 550 | 78.5714 | DOCC | 8 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - El Dorado 2101 - 19752 - Ph 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2020-08-13 | 2020-01-30 | INPR | 2019-10-10 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | -44056 | 0 | 1657539
35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | 06/03/2019 | 117349211 | 05/30/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/30/2020 | ED.15276.2101 | EL DORADO PH 2101 | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 9,506.000 | 8,922.000 | 08W | 2019 | # | OPEN | 550 | 78.5714 | DOCC | 8 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - El Dorado 2101 - 19752 - Ph 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2019-12-07 | 2019-12-07 | INPR | 2019-10-10 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | -43806 | 0 | 2454750.14
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | 06/03/2019 | 117349070 | 05/30/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/30/2020 | ED.15276.2101 | EL DORADO PH 2101 | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 12,857.000 | 12,784.000 | 08W | 2019 | # | OPEN | 550 | 78.5714 | DOCC | 8 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - El Dorado 2101 - LR 19752 - Ph2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2020-04-17 | 2020-04-17 | INPR | 2020-03-24 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | -43938 | 0 | 3091071.49
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | 06/03/2019 | 117349071 | 05/30/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/30/2020 | ED.15276.2101 | EL DORADO PH 2101 | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 14,639.000 | 0.000 | 08W | 2019 | # | OPEN | 550 | 78.5714 | ADER | 3 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - El Dorado 2101 - LR 19752 - Ph2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 158419.13
35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | 06/03/2019 | 117349072 | 05/30/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/30/2020 | ED.15276.2101 | EL DORADO PH 2101 | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 7,660.000 | 8,100.000 | 08W | 2019 | # | OPEN | 550 | 78.5714 | DOCC | 8 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - El Dorado 2101 - LR 19752 - Ph2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2020-03-13 | 2020-03-13 | INPR | 2020-04-02 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | -43903 | 0 | 2741271.64
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | 06/03/2019 | 117349073 | 05/30/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/30/2020 | ED.15276.2101 | EL DORADO PH 2101 | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 15,944.000 | 15,069.000 | 08W | 2019 | # | OPEN | 550 | 78.5714 | DOCC | 8 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - El Dorado 2101 - LR 19752 - Ph2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2020-05-22 | 2020-05-22 | INPR | 2020-05-29 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | -43973 | 0 | 3215549.07
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | 06/03/2019 | 117348822 | 05/30/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/30/2020 | ED.15276.2101 | EL DORADO PH 2101 | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 6,933.000 | 7,069.000 | 08W | 2019 | # | OPEN | 550 | 78.5714 | DOCC | 8 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - El Dorado 2101 - LR 19752 - Ph3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2020-04-17 | 2020-04-17 | INPR | 2020-05-14 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | -43938 | 0 | 2243211.21
35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | 06/03/2019 | 117348823 | 05/30/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/30/2020 | ED.15276.2101 | EL DORADO PH 2101 | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 9,563.000 | 10,305.000 | 08W | 2019 | # | OPEN | 550 | 78.5714 | DOCC | 8 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - El Dorado 2101 - LR 19752 - Ph3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2020-01-31 | 2020-01-31 | INPR | 2020-03-09 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | -43861 | 0 | 2664478.22
35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | 06/03/2019 | 117348824 | 05/30/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/30/2020 | ED.15276.2101 | EL DORADO PH 2101 | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 7,580.000 | 7,684.000 | 08W | 2019 | # | OPEN | 550 | 78.5714 | DOCC | 8 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - El Dorado 2101 - LR 19752 - Ph3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2020-04-17 | 2020-04-17 | INPR | 2020-05-01 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | -43938 | 0 | 1919920.45
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | 06/03/2019 | 117348827 | 05/30/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/30/2020 | ED.15276.2101 | EL DORADO PH 2101 | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 11,274.000 | 11,507.000 | 08W | 2019 | # | OPEN | 550 | 78.5714 | DOCC | 8 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - El Dorado 2101 - LR 19752 - Ph3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2020-02-11 | 2020-02-11 | INPR | 2020-02-11 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | -43872 | 0 | 4162683.09
35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | 06/03/2019 | 117348828 | 05/30/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/30/2020 | ED.15276.2101 | EL DORADO PH 2101 | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 14,080.000 | 13,725.000 | 08W | 2019 | # | OPEN | 550 | 78.5714 | DOCC | 8 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - El Dorado 2101 - LR 19752 - Ph3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2020-01-29 | 2020-01-29 | INPR | 2020-03-09 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | -43859 | 0 | 3648795.02
35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | 06/03/2019 | 117348366 | 05/30/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/30/2020 | ED.15276.2101 | EL DORADO PH 2101 | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 6,641.000 | 6,661.000 | 08W | 2019 | # | OPEN | 550 | 78.5714 | DOCC | 8 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - El Dorado 2101 - LR 19752 - Ph4 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2020-04-03 | 2020-04-03 | INPR | 2020-04-13 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | -43924 | 0 | 1758073.57
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | 06/03/2019 | 117348367 | 05/30/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/30/2020 | ED.15276.2101 | EL DORADO PH 2101 | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 11,685.000 | 11,318.000 | 08W | 2019 | # | OPEN | 550 | 78.5714 | DOCC | 8 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - El Dorado 2101 - LR 19752 - Ph4 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2020-02-21 | 2020-02-21 | INPR | 2020-03-09 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | -43882 | 0 | 3423982.13
35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | 06/03/2019 | 117348368 | 05/30/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/30/2020 | ED.15276.2101 | EL DORADO PH 2101 | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 1,618.000 | 1,618.000 | 08W | 2019 | # | OPEN | 550 | 78.5714 | DOCC | 8 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - El Dorado 2101 - LR 19752 - Ph4 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2020-03-06 | 2020-03-06 | INPR | 2020-04-02 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | -43896 | 0 | 774754.05
35109737 | CWSP-VOLTA 1102-LR 1648-PH2.2 | 06/04/2019 | 117380976 | 06/03/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.87-Q430800000.STRU.POLE | SHASTA Q4308 POLES | 045 | SHASTA COUNTY | 5535211 | CWSP SPO - SH 08 | 10,965.000 | 11,549.000 | 08W | 2019 | # | OPEN | 549 | 78.4286 | DOCC | 8 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - VOLTA 1102 LR 1648 PH 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2020-03-16 | 2020-03-16 | INPR | 2020-03-18 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | -43906 | 0 | 3032566.08
35109738 | CWSP-VOLTA 1102-LR 1648-PH2.3 | 06/04/2019 | 117380979 | 06/03/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.87-Q431100000.STRU.POLE | SHASTA Q4311 POLES | 045 | SHASTA COUNTY | 5535211 | CWSP SPO - SH 08 | 10,903.000 | 10,732.000 | 08W | 2019 | # | OPEN | 549 | 78.4286 | DOCC | 8 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - VOLTA 1102 LR 1648 PH 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2020-05-28 | 2020-05-28 | INPR | 2019-11-13 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | -43979 | 0 | 2608805.4
35109739 | CWSP-VOLTA 1102-LR 1648-PH2.4 | 06/04/2019 | 117381940 | 06/03/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.87-Q430300000.STRU.POLE | SHASTA Q4303 POLES | 045 | SHASTA COUNTY | 5535211 | CWSP SPO - SH 08 | 13,219.000 | 12,081.000 | 08W | 2019 | # | OPEN | 549 | 78.4286 | DOCC | 8 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - VOLTA 1102 LR 1648 PH 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2020-01-23 | 2020-01-23 | INPR | 2019-10-15 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | -43853 | 0 | 2943332.71
35109832 | BR-03-01-W (E) GATE LN PARB | 06/03/2019 | 117380789 | 06/03/2019 | # | Not assigned | 30 | Technically Completed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/27/2019 | ED.17-S340700000.STRU.POLE | PARADISE S3407 POLES | 004 | BUTTE COUNTY | 5786123 | 08W Rebuild | 0.000 | 0.000 | 08W | 2019 | # | OPEN | 550 | 78.5714 | FICL | 10 | E470 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2020-08-06 | 2020-03-24 | COMP | 2020-08-06 | 2020-10-29 | COMP | 2020-04-13 | 2020-11-03 | COMP | 2020-11-03 | 2020-11-05 | COMP | 2020-11-05 | 2020-11-24 | COMP | 2020-11-24 | 2020-11-24 | 89 | 21 | 1144522.31
35110369 | BR-03-03-W (E) GINNY_SUNRISE PARB | 06/05/2019 | 117393835 | 06/05/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/27/2019 | ED.17-S340700000.STRU.POLE | PARADISE S3407 POLES | 004 | BUTTE COUNTY | 5786123 | 08W Rebuild | 0.000 | 0.000 | 08W | 2019 | # | OPEN | 548 | 78.2857 | MAPP | 9 | E470 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2020-03-30 | 2020-03-30 | COMP | 2020-06-16 | 2020-06-16 | COMP | 2020-06-16 | 2020-06-16 | INPR | 2020-07-02 | 0 | # | 0 | 0 | # | 0 | 0 | 78 | -43998 | 1241954.74
35110372 | BR-03-04-W (E) SWEETBRIAR PARB | 06/05/2019 | 117398952 | 06/05/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/27/2019 | ED.17-S341200000.STRU.POLE | PARADISE S3412 POLES | 004 | BUTTE COUNTY | 5786123 | 08W Rebuild | 0.000 | 0.000 | 08W | 2019 | # | OPEN | 548 | 78.2857 | DOCC | 8 | E470 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2020-04-07 | 2020-04-07 | COMP | 2020-07-28 | 2020-07-28 | INPR | 2020-11-19 | 0 | INPR | 2020-11-18 | 0 | # | 0 | 0 | # | 0 | 0 | -43928 | 0 | 853245.09
35110374 | BR-03-06-W (E) LUNAR LN PARB | 06/05/2019 | 117398959 | 06/05/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/27/2019 | ED.17-S341300000.STRU.POLE | PARADISE S3413 POLES | 004 | BUTTE COUNTY | 5786123 | 08W Rebuild | 0.000 | 0.000 | 08W | 2019 | # | OPEN | 548 | 78.2857 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 450.52
35110377 | BR-03-10-W (E) SHAY LN PARB | 06/05/2019 | 117399397 | 06/05/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/27/2019 | ED.17-S341800000.STRU.POLE | PARADISE S3418 POLES | 004 | BUTTE COUNTY | 5786123 | 08W Rebuild | 0.000 | 0.000 | 08W | 2019 | # | OPEN | 548 | 78.2857 | MAPP | 9 | E470 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2020-03-20 | 2020-03-20 | COMP | 2019-09-24 | 2020-08-04 | COMP | 2020-08-04 | 2020-08-04 | INPR | 2020-08-14 | 0 | # | 0 | 0 | # | 0 | 0 | 137 | -44047 | 3154947.03
35110379 | BR-03-11-W (E) WHITAKER RD PARB | 06/05/2019 | 117399822 | 06/05/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/27/2019 | ED.17-S341700000.STRU.POLE | PARADISE S3417 POLES | 004 | BUTTE COUNTY | 5786123 | 08W Rebuild | 0.000 | 0.000 | 08W | 2019 | # | OPEN | 548 | 78.2857 | MAPP | 9 | E470 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2020-08-26 | 2020-01-08 | COMP | 2020-08-26 | 2020-11-20 | COMP | 2020-08-26 | 2020-11-20 | COMP | 2020-11-20 | 2020-11-30 | INPR | 2020-11-30 | 0 | # | 0 | 0 | 86 | -44155 | 713717.42
35110440 | CWSP-VOLTA 1102-LR 1648-PH2.5 | 06/04/2019 | 117381942 | 06/03/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.87-P432200000.STRU.POLE | SHASTA MAP P4322 POLES | 045 | SHASTA COUNTY | 5535211 | CWSP SPO - SH 08 | 15,053.000 | 13,964.000 | 08W | 2019 | # | OPEN | 549 | 78.4286 | DOCC | 8 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - VOLTA 1102 LR 1648 PH 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2020-05-08 | 2020-05-08 | INPR | 2019-10-15 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | -43959 | 0 | 2774691.52
35110441 | CWSP-VOLTA 1102-LR 1648-PH2.6 | 06/04/2019 | 117381943 | 06/03/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.87-P432100000.STRU.POLE | SHASTA P4321 POLES | 045 | SHASTA COUNTY | 5535211 | CWSP SPO - SH 08 | 11,790.000 | 11,791.000 | 08W | 2019 | # | OPEN | 549 | 78.4286 | DOCC | 8 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - VOLTA 1102 LR 1648 PH 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2020-05-04 | 2020-05-04 | INPR | 2020-04-14 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | -43955 | 0 | 2094936.26
35110442 | CWSP-VOLTA 1102-LR 1648-PH3.2 | 06/04/2019 | 117386854 | 06/04/2019 | # | Not assigned | 30 | Technically Completed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.87-Q430000000.STRU.POLE | SHASTA Q43 POLES | 045 | SHASTA COUNTY | 5535211 | CWSP SPO - SH 08 | 7,155.000 | 7,126.000 | 08W | 2019 | # | OPEN | 549 | 78.4286 | FICL | 10 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - VOLTA 1102 - LR 1648 -PHASE 3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2020-08-28 | 2020-05-28 | COMP | 2019-10-15 | 2020-08-28 | COMP | 2020-08-28 | 2020-08-28 | COMP | 2020-08-28 | 2020-08-31 | COMP | 2020-08-31 | 2020-09-08 | COMP | 2020-09-08 | 2020-09-08 | 0 | 11 | 4050264.12
35110443 | CWSP-VOLTA 1102-LR 1648-PH3.3 | 06/04/2019 | 117386950 | 06/04/2019 | # | Not assigned | 30 | Technically Completed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | JY | JUNK YARD FL TO HOLD DELETED DATA | 045 | SHASTA COUNTY | 5535211 | CWSP SPO - SH 08 | 6,468.000 | 6,433.000 | 08W | 2019 | # | OPEN | 549 | 78.4286 | FICL | 10 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - VOLTA 1102 - LR 1648 -PHASE 3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2020-11-06 | 2020-06-08 | COMP | 2020-02-07 | 2020-11-06 | COMP | 2020-11-06 | 2020-11-06 | COMP | 2020-11-06 | 2020-11-10 | COMP | 2020-11-10 | 2020-11-30 | COMP | 2020-11-30 | 2020-11-30 | 0 | 24 | 2663871.02
35110444 | CWSP-VOLTA 1102-LR 1648-PH3.4 | 06/04/2019 | 117386958 | 06/04/2019 | # | Not assigned | 30 | Technically Completed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | JY | JUNK YARD FL TO HOLD DELETED DATA | 045 | SHASTA COUNTY | 5535211 | CWSP SPO - SH 08 | 7,757.000 | 7,728.000 | 08W | 2019 | # | OPEN | 549 | 78.4286 | FICL | 10 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - VOLTA 1102 - LR 1648 -PHASE 3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2020-02-06 | 2020-02-06 | COMP | 2019-10-16 | 2020-08-21 | COMP | 2020-08-21 | 2020-08-21 | COMP | 2020-08-21 | 2020-08-24 | COMP | 2020-08-24 | 2020-09-02 | COMP | 2020-09-02 | 2020-09-02 | 197 | 12 | 2551699.56
35110445 | CWSP-VOLTA 1102-LR 1648-PH4.2 | 06/04/2019 | 117387609 | 06/04/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.87-P452200000.STRU.POLE | SHASTA P4522 POLES | 045 | SHASTA COUNTY | 5535211 | CWSP SPO - SH 08 | 10,160.000 | 9,066.000 | 08W | 2019 | # | OPEN | 549 | 78.4286 | DOCC | 8 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - VOLTA 1102 - LR 1648 -PHASE 4 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2019-12-26 | 2019-12-26 | INPR | 2019-12-26 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | -43825 | 0 | 3475953.24
35110446 | CWSP-VOLTA 1102-LR 1648-PH4.3 | 06/04/2019 | 117387798 | 06/04/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.87-P451700000.STRU.POLE | SHASTA MAP P4517 POLES | 045 | SHASTA COUNTY | 5535211 | CWSP SPO - SH 08 | 11,030.000 | 11,009.000 | 08W | 2019 | # | OPEN | 549 | 78.4286 | DOCC | 8 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - VOLTA 1102 - LR 1648 -PHASE 4 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2020-02-18 | 2020-02-18 | INPR | 2020-02-19 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | -43879 | 0 | 2799988.1
35110447 | CWSP-VOLTA 1102-LR 1648-PH4.4 | 06/04/2019 | 117387953 | 06/04/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.87-P451800000.STRU.POLE | SHASTA P4518 POLES | 045 | SHASTA COUNTY | 5535211 | CWSP SPO - SH 08 | 6,201.000 | 6,190.000 | 08W | 2019 | # | OPEN | 549 | 78.4286 | DOCC | 8 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - VOLTA 1102 - LR 1648 -PHASE 4 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2020-04-10 | 2020-04-10 | INPR | 2020-04-17 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | -43931 | 0 | 3456509.15
35110448 | CWSP-VOLTA 1102-LR 1648-PH4.5 | 06/04/2019 | 117388062 | 06/04/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.87-P451800000.STRU.POLE | SHASTA P4518 POLES | 045 | SHASTA COUNTY | 5535211 | CWSP SPO - SH 08 | 10,301.000 | 10,620.000 | 08W | 2019 | # | OPEN | 549 | 78.4286 | DOCC | 8 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - VOLTA 1102 - LR 1648 -PHASE 4 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2020-05-28 | 2020-05-28 | INPR | 2020-06-03 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | -43979 | 0 | 3385386.89
35110556 | BR-04-12-W (E) SUBSTATION/PATH PARB | 06/06/2019 | 117402466 | 06/06/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/27/2019 | ED.17-T330300000.STRU.POLE | PARADISE T3303 POLES | 004 | BUTTE COUNTY | 5786123 | 08W Rebuild | 0.000 | 0.000 | 08W | 2019 | # | OPEN | 547 | 78.1429 | ESTS | 2 | E470 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 38149.73
35111486 | BR-04-03-W (E) EDWARDS & RIPLEY PARB | 06/13/2019 | 117443527 | 06/13/2019 | # | Not assigned | 30 | Technically Completed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/27/2019 | JY | JUNK YARD FL TO HOLD DELETED DATA | 004 | BUTTE COUNTY | 5786123 | 08W Rebuild | 0.000 | 0.000 | 08W | 2019 | # | OPEN | 540 | 77.1429 | FICL | 10 | E470 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2020-03-05 | 2020-03-05 | COMP | 2020-07-27 | 2020-07-27 | COMP | 2020-07-27 | 2020-07-27 | COMP | 2020-07-27 | 2020-07-28 | COMP | 2020-07-28 | 2020-08-03 | COMP | 2020-08-03 | 2020-08-05 | 144 | 9 | 1596180.67
35111500 | CWSP-RECON UPPER LAKE 01 HUNTERS PT RD | 06/13/2019 | 117416989 | 06/07/2019 | # | Not assigned | 30 | Technically Completed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/27/2019 | ED.04287.1101.SWIT | SWITCHES | 017 | LAKE COUNTY | 5535211 | CWSP SPO - SH 08 | 3,700.000 | 1,850.000 | 08W | 2019 | # | OPEN | 540 | 77.1429 | FICL | 10 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2019-12-16 | 2019-12-16 | COMP | 2020-01-19 | 2020-01-19 | COMP | 2020-01-19 | 2020-01-19 | COMP | 2020-01-19 | 2020-01-21 | COMP | 2020-01-21 | 2020-01-28 | COMP | 2020-01-28 | 2020-01-28 | 34 | 9 | 386043.97
35112076 | OCGC FULTON 1107-OH TO UG MARK W SPG | 06/19/2019 | 117440386 | 06/12/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 03/21/2020 | ED.04256.1107 | FULTON 1107 | 049 | SONOMA COUNTY | 5786045 | CWSP - FULTON 1107 - MARK WEST SPR RD | 11,799.000 | 11,799.000 | 08W | 2019 | # | OPEN | 534 | 76.2857 | MAPP | 9 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - FULTON 1107 - MARK WEST SPR RD | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2020-04-06 | 2020-04-06 | COMP | 2020-04-16 | 2020-04-16 | COMP | 2020-04-16 | 2020-04-16 | INPR | 2020-06-08 | 0 | # | 0 | 0 | # | 0 | 0 | 10 | -43937 | 4519053.04
35112089 | BR-01-05-W (E) MEYERS PARB | 06/19/2019 | 117463088 | 06/19/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/27/2019 | ED.17-S331700000.STRU.POLE | PARADISE S3317 POLES | 004 | BUTTE COUNTY | 5786123 | 08W Rebuild | 0.000 | 0.000 | 08W | 2019 | # | OPEN | 534 | 76.2857 | DOCC | 8 | E470 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2020-02-25 | 2020-02-25 | COMP | 2020-08-04 | 2020-08-04 | COMP | 2020-08-04 | 2020-08-04 | INPR | 2020-08-04 | 0 | # | 0 | 0 | # | 0 | 0 | 161 | -44047 | 584621.18
35112090 | BR-01-07-W (E) BILLE_REGIS PARB | 06/19/2019 | 117463089 | 06/19/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/27/2019 | ED.17-S332100000.STRU.POLE | PARADISE S3321 POLES | 004 | BUTTE COUNTY | 5786123 | 08W Rebuild | 0.000 | 0.000 | 08W | 2019 | # | OPEN | 534 | 76.2857 | DOCC | 8 | E470 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2020-01-13 | 2020-01-13 | COMP | 2020-07-23 | 2020-07-23 | INPR | 2020-07-23 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | -43843 | 0 | 598122.68
35112091 | BR-01-09-W (E) FERN PARB | 06/19/2019 | 117463140 | 06/19/2019 | # | Not assigned | 30 | Technically Completed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/27/2019 | JY | JUNK YARD FL TO HOLD DELETED DATA | 004 | BUTTE COUNTY | 5786123 | 08W Rebuild | 0.000 | 0.000 | 08W | 2019 | # | OPEN | 534 | 76.2857 | FICL | 10 | E470 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2020-04-15 | 2020-04-15 | COMP | 2020-08-04 | 2020-08-04 | COMP | 2020-08-04 | 2020-08-05 | COMP | 2020-08-05 | 2020-08-06 | COMP | 2020-08-06 | 2020-08-17 | COMP | 2020-08-17 | 2020-08-19 | 112 | 14 | 349363.89
35112092 | BR-14-06 (E) BLUE DANUBE PARB | 06/19/2019 | 117463141 | 06/19/2019 | # | Not assigned | 30 | Technically Completed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/27/2019 | ED.17-T341900000.STRU.POLE | PARADISE T3419 POLES | 004 | BUTTE COUNTY | 5786123 | 08W Rebuild | 0.000 | 0.000 | 08W | 2019 | # | OPEN | 534 | 76.2857 | FICL | 10 | E470 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2020-05-01 | 2020-05-01 | COMP | 2020-08-11 | 2020-08-11 | COMP | 2020-08-11 | 2020-08-11 | COMP | 2020-08-11 | 2020-08-12 | COMP | 2020-08-12 | 2020-08-20 | COMP | 2020-08-20 | 2020-08-21 | 102 | 10 | 491760.03
35112126 | BR-01-03-W (E) PARAGALIA PARB | 06/18/2019 | 117462530 | 06/18/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/27/2019 | ED.17-S331900000.STRU.POLE | PARADISE S3319 POLES | 004 | BUTTE COUNTY | 5786123 | 08W Rebuild | 0.000 | 0.000 | 08W | 2019 | # | OPEN | 535 | 76.4286 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35112128 | BR-01-04-W (E) W. WAGSTAFF PARB | 06/18/2019 | 117462629 | 06/18/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/27/2019 | ED.17-S332100000.STRU.POLE | PARADISE S3321 POLES | 004 | BUTTE COUNTY | 5786123 | 08W Rebuild | 0.000 | 0.000 | 08W | 2019 | # | OPEN | 535 | 76.4286 | DOCC | 8 | E470 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | INPR | 2020-10-28 | 0 | INPR | 2020-10-28 | 0 | INPR | 2020-10-28 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | -44132 | 0 | 948107.87
35112157 | *CANC*CWSP - MIWUK 1701 - LR 10600 | 06/19/2019 | # | #N/A | 35052735 | CWSP - MIWUK 1701 - LR 10600 PH 1.1 | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | # | ED.16366.1701 | MIWUK 1701 | 055 | TUOLUMNE COUNT | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2019 | # | OPEN | 534 | 76.2857 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0
35112158 | *CANC*CWSP - MIWUK 1701 - LR 10600 | 06/19/2019 | # | #N/A | 35052735 | CWSP - MIWUK 1701 - LR 10600 PH 1.1 | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | # | ED.16366.1701 | MIWUK 1701 | 055 | TUOLUMNE COUNT | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2019 | # | OPEN | 534 | 76.2857 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0
35112159 | *CANC*CWSP - MIWUK 1701 - LR 10600 | 06/19/2019 | # | #N/A | 35052735 | CWSP - MIWUK 1701 - LR 10600 PH 1.1 | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | # | ED.16366.1701 | MIWUK 1701 | 055 | TUOLUMNE COUNT | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2019 | # | OPEN | 534 | 76.2857 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0
35112220 | BR-04-06-W (E) VALLEY RIDGE PARB | 06/19/2019 | 117463683 | 06/19/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/27/2019 | JY | JUNK YARD FL TO HOLD DELETED DATA | 004 | BUTTE COUNTY | 5786123 | 08W Rebuild | 0.000 | 0.000 | 08W | 2019 | # | OPEN | 534 | 76.2857 | CONS | 7 | E470 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 641535.34
35112249 | BR-04-07-W (E) CRESTMOOR PARB | 06/19/2019 | 117466069 | 06/19/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/27/2019 | JY | JUNK YARD FL TO HOLD DELETED DATA | 004 | BUTTE COUNTY | 5786123 | 08W Rebuild | 0.000 | 0.000 | 08W | 2019 | # | OPEN | 534 | 76.2857 | DOCC | 8 | E470 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2020-05-15 | 2020-05-15 | COMP | 2020-08-25 | 2020-08-25 | COMP | 2020-11-25 | 2020-11-30 | INPR | 2020-11-23 | 0 | # | 0 | 0 | # | 0 | 0 | 199 | -44165 | 2945144.94
35112340 | *CANC*CWSP - MIWUK 1701 - LR 10600 | 06/19/2019 | # | #N/A | 35052735 | CWSP - MIWUK 1701 - LR 10600 PH 1.1 | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | # | ED.16366.1701 | MIWUK 1701 | 055 | TUOLUMNE COUNT | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2019 | # | OPEN | 534 | 76.2857 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | 06/20/2019 | 117467828 | 06/19/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.21-G460000000.STRU.POLE | EL DORADO G46 POLES | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 6,653.000 | 0.000 | 08W | 2019 | # | OPEN | 533 | 76.1429 | CONS | 7 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | INPR | 2020-04-22 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 723546
35112426 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.3 | 06/20/2019 | 117467829 | 06/19/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/20/2019 | ED.21-G460000000.STRU.POLE | EL DORADO G46 POLES | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 9,368.000 | 9,077.000 | 08W | 2019 | # | OPEN | 533 | 76.1429 | DOCC | 8 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2020-07-22 | 2019-12-21 | COMP | 2019-12-26 | 2020-07-22 | COMP | 2020-07-22 | 2020-07-22 | INPR | 2020-07-22 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | -44034 | 4025163.93
35112427 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.4 | 06/20/2019 | 117467963 | 06/19/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 01/31/2020 | ED.21-G460000000.STRU.POLE | EL DORADO G46 POLES | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 5,117.000 | 5,069.000 | 08W | 2019 | # | OPEN | 533 | 76.1429 | MAPP | 9 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2020-07-22 | 2020-02-12 | COMP | 2020-02-25 | 2020-07-22 | COMP | 2020-07-22 | 2020-07-22 | COMP | 2020-07-22 | 2020-11-06 | INPR | 2020-11-06 | 0 | # | 0 | 0 | 0 | -44034 | 1730145.65
35112428 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.5 | 06/20/2019 | 117467964 | 06/19/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 02/27/2020 | ED.21-G460000000.STRU.POLE | EL DORADO G46 POLES | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 8,571.000 | 8,571.000 | 08W | 2019 | # | OPEN | 533 | 76.1429 | MAPP | 9 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2020-02-27 | 2020-02-27 | COMP | 2020-02-27 | 2020-09-18 | COMP | 2020-09-18 | 2020-09-18 | COMP | 2020-09-18 | 2020-11-16 | INPR | 2020-11-16 | 0 | # | 0 | 0 | 204 | -44092 | 2459084.13
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | 06/20/2019 | 117467966 | 06/19/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.21-G460000000.STRU.POLE | EL DORADO G46 POLES | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 7,341.000 | 0.000 | 08W | 2019 | # | OPEN | 533 | 76.1429 | CONS | 7 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 1072544.99
35112431 | CWSP - EL DORADO 2102 - LR19562 - PH 1.1 | 06/20/2019 | 117472384 | 06/20/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.15276.2102 | EL DORADO PH 2102 | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 8,118.000 | 8,117.000 | 08W | 2019 | # | OPEN | 533 | 76.1429 | MAPP | 9 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - EL DORADO PH 2102 - LR 19562 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2020-10-02 | 2020-10-02 | COMP | 2020-10-06 | 2020-11-17 | COMP | 2020-11-17 | 2020-11-17 | COMP | 2020-11-17 | 2020-11-18 | INPR | 2020-11-18 | 0 | # | 0 | 0 | 46 | -44152 | 1707343.33
35112432 | CWSP - EL DORADO 2102 - LR19562 - PH 1.2 | 06/20/2019 | 117472387 | 06/20/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.15276.2102 | EL DORADO PH 2102 | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 11,193.000 | 13,572.000 | 08W | 2019 | # | OPEN | 533 | 76.1429 | DOCC | 8 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - EL DORADO PH 2102 - LR 19562 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2020-11-18 | 2020-11-18 | INPR | 2020-11-23 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | -44153 | 0 | 1458687.39
35112433 | CWSP - EL DORADO 2102 - LR19562 - PH 1.3 | 06/20/2019 | 117472388 | 06/20/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.15276.2102 | EL DORADO PH 2102 | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 10,122.000 | 10,205.000 | 08W | 2019 | # | OPEN | 533 | 76.1429 | DOCC | 8 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - EL DORADO PH 2102 - LR 19562 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2020-06-11 | 2020-06-11 | COMP | 2020-06-30 | 2020-09-11 | COMP | 2020-09-11 | 2020-09-11 | INPR | 2020-09-11 | 0 | # | 0 | 0 | # | 0 | 0 | 92 | -44085 | 1751217.64
35112434 | CWSP - EL DORADO 2102 - LR19562 - PH 1.4 | 06/20/2019 | 117472389 | 06/20/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.15276.2102 | EL DORADO PH 2102 | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 7,924.000 | 7,924.000 | 08W | 2019 | # | OPEN | 533 | 76.1429 | DOCC | 8 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - EL DORADO PH 2102 - LR 19562 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2020-10-02 | 2020-10-02 | INPR | 2020-10-06 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | -44106 | 0 | 2128525.57
35112435 | CWSP - EL DORADO 2102 - LR19562 - PH 1.5 | 06/20/2019 | 117472561 | 06/20/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.15276.2102 | EL DORADO PH 2102 | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 7,873.000 | 7,006.000 | 08W | 2019 | # | OPEN | 533 | 76.1429 | DOCC | 8 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - EL DORADO PH 2102 - LR 19562 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2020-09-04 | 2020-09-04 | INPR | 2020-09-08 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | -44078 | 0 | 1153072.54
35112436 | CWSP - EL DORADO 2102 - LR19562 - PH 1.6 | 06/20/2019 | 117472563 | 06/20/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.15276.2102 | EL DORADO PH 2102 | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 9,210.000 | 9,867.000 | 08W | 2019 | # | OPEN | 533 | 76.1429 | DOCC | 8 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - EL DORADO PH 2102 - LR 19562 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2020-05-15 | 2020-05-15 | COMP | 2020-06-30 | 2020-08-24 | COMP | 2020-08-24 | 2020-08-24 | INPR | 2020-08-24 | 0 | # | 0 | 0 | # | 0 | 0 | 101 | -44067 | 2085213.15
35112437 | CWSP - EL DORADO 2102 - LR19562 - PH 1.7 | 06/20/2019 | 117472564 | 06/20/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.15276.2102 | EL DORADO PH 2102 | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 14,365.000 | 14,550.000 | 08W | 2019 | # | OPEN | 533 | 76.1429 | MAPP | 9 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - EL DORADO PH 2102 - LR 19562 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2020-11-17 | 2020-08-26 | COMP | 2020-05-07 | 2020-11-17 | COMP | 2020-11-17 | 2020-11-17 | COMP | 2020-11-17 | 2020-11-18 | INPR | 2020-11-18 | 0 | # | 0 | 0 | 0 | -44152 | 1202369.12
35112876 | BR-04-02-W (E) CASTLE_CLIFF DR PARB | 06/25/2019 | 117491028 | 06/25/2019 | # | Not assigned | 30 | Technically Completed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/27/2019 | JY | JUNK YARD FL TO HOLD DELETED DATA | 004 | BUTTE COUNTY | 5786123 | 08W Rebuild | 0.000 | 0.000 | 08W | 2019 | # | OPEN | 528 | 75.4286 | FICL | 10 | E470 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2020-02-12 | 2020-02-12 | COMP | 2020-04-28 | 2020-04-28 | COMP | 2020-04-30 | 2020-04-30 | COMP | 2020-04-30 | 2020-05-04 | COMP | 2020-05-04 | 2020-05-22 | COMP | 2020-06-01 | 2020-06-22 | 78 | 53 | 723044.04
35112968 | WOODSIDE 1101 RECOND FUSE 1097 ZONE | 06/26/2019 | 117474195 | 06/20/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/30/2020 | ED.58-F081100000.STRU.POLE | PENINSULA F0811 POLES | 041 | SAN MATEO COUN | 5535211 | CWSP SPO - SH 08 | 14,709.000 | 0.000 | 08W | 2019 | # | OPEN | 527 | 75.2857 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-WOODSIDE 1101-FUSE1097 TAP LINE | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 1689.6
35112972 | CWSP - WEST POINT 1101 -LR 13444- PH 1.2 | 06/26/2019 | 117491267 | 06/25/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2019 | ED.95-J291500000.STRU.POLE | MOTHER LODE J2915 POLES | 003 | AMADOR COUNTY | 5535211 | CWSP SPO - SH 08 | 6,113.000 | 0.000 | 08W | 2019 | # | OPEN | 527 | 75.2857 | ESTS | 2 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-WEST POINT 1101-LR 13444-PHASE 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 23438.75
35112973 | CWSP - WEST POINT 1101 -LR 13444- PH 1.3 | 06/26/2019 | 117491412 | 06/25/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2019 | ED.95-J291500000.STRU.POLE | MOTHER LODE J2915 POLES | 003 | AMADOR COUNTY | 5535211 | CWSP SPO - SH 08 | 3,934.000 | 0.000 | 08W | 2019 | # | OPEN | 527 | 75.2857 | PEND | 5 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-WEST POINT 1101-LR 13444-PHASE 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 82266.29
35112974 | CWSP - WEST POINT 1101 -LR 13444- PH 1.4 | 06/26/2019 | 117491414 | 06/25/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2019 | ED.95-J291500000.STRU.POLE | MOTHER LODE J2915 POLES | 003 | AMADOR COUNTY | 5535211 | CWSP SPO - SH 08 | 13,819.000 | 0.000 | 08W | 2019 | # | OPEN | 527 | 75.2857 | ADER | 3 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-WEST POINT 1101-LR 13444-PHASE 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 24202.37
35112975 | CWSP - WEST POINT 1101 -LR 13444- PH 1.5 | 06/26/2019 | 117491771 | 06/25/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2019 | ED.95-J290900000.STRU.POLE | MOTHER LODE J2909 POLES | 003 | AMADOR COUNTY | 5786004 | CWSP - WEST POINT 1101 -LR 13444- PH 1.5 | 0.000 | 0.000 | 08W | 2019 | # | OPEN | 527 | 75.2857 | ADER | 3 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-WEST POINT 1101-LR 13444-PHASE 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 15366.36
35112976 | CWSP - WEST POINT 1101 -LR 13444- PH 1.6 | 06/26/2019 | 117491849 | 06/25/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2019 | ED.95-J290500000.STRU.POLE | MOTHER LODE MAP J2905 POLES | 003 | AMADOR COUNTY | 5786005 | CWSP - WEST POINT 1101 -LR 13444- PH 1.6 | 0.000 | 0.000 | 08W | 2019 | # | OPEN | 527 | 75.2857 | ESTS | 2 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-WEST POINT 1101-LR 13444-PHASE 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 9791.75
35112977 | CWSP - WEST POINT 1101 -LR 13444- PH 1.7 | 06/26/2019 | 117491910 | 06/25/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2019 | ED.95-J300100000.STRU.POLE | MOTHER LODE J3001 POLES | 003 | AMADOR COUNTY | 5786006 | CWSP - WEST POINT 1101 -LR 13444- PH 1.7 | 5,802.000 | 0.000 | 08W | 2019 | # | OPEN | 527 | 75.2857 | PEND | 5 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-WEST POINT 1101-LR 13444-PHASE 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 10731.96
35112978 | CWSP - WEST POINT 1101 -LR 13444- PH 2.2 | 06/26/2019 | 117493902 | 06/26/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/27/2019 | ED.16320.1101 | WEST POINT 1101 | 003 | AMADOR COUNTY | 5535211 | CWSP SPO - SH 08 | 8,442.000 | 0.000 | 08W | 2019 | # | OPEN | 527 | 75.2857 | PEND | 5 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-WEST POINT 1101-LR 13444-PHASE 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 61639.03
35112979 | CWSP - WEST POINT 1101 -LR 13444- PH 2.3 | 06/26/2019 | 117494010 | 06/26/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/27/2019 | ED.16320.1101 | WEST POINT 1101 | 003 | AMADOR COUNTY | 5535211 | CWSP SPO - SH 08 | 5,324.000 | 0.000 | 08W | 2019 | # | OPEN | 527 | 75.2857 | PEND | 5 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-WEST POINT 1101-LR 13444-PHASE 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 58614.54
35113100 | CWSP - WEST POINT 1101 -LR 13444- PH 2.4 | 06/26/2019 | 117494051 | 06/26/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/27/2019 | ED.16320.1101 | WEST POINT 1101 | 003 | AMADOR COUNTY | 5786009 | CWSP - WEST POINT 1101 -LR 13444- PH 2.4 | 10,665.000 | 0.000 | 08W | 2019 | # | OPEN | 527 | 75.2857 | PEND | 5 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-WEST POINT 1101-LR 13444-PHASE 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 50176.16
35113101 | CWSP - WEST POINT 1101 -LR 13444- PH 2.5 | 06/26/2019 | 117493797 | 06/26/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/01/2020 | ED.16320.1101 | WEST POINT 1101 | 003 | AMADOR COUNTY | 5535211 | CWSP SPO - SH 08 | 10,788.000 | 0.000 | 08W | 2019 | # | OPEN | 527 | 75.2857 | CONS | 7 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-WEST POINT 1101-LR 13444-PHASE 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 1300850.84
35113102 | CWSP - WEST POINT 1101 -LR 13444- PH 2.6 | 06/26/2019 | 117493910 | 06/26/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/01/2020 | ED.16320.1101 | WEST POINT 1101 | 003 | AMADOR COUNTY | 5535211 | CWSP SPO - SH 08 | 11,757.000 | 0.000 | 08W | 2019 | # | OPEN | 527 | 75.2857 | CONS | 7 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-WEST POINT 1101-LR 13444-PHASE 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 1173578.47
35113103 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.3 | 06/26/2019 | 117492227 | 06/25/2019 | # | Not assigned | 30 | Technically Completed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.08202.1106 | LOS GATOS 1106 | 043 | SANTA CLARA CO | 5535211 | CWSP SPO - SH 08 | 1,152.000 | 1,152.000 | 08W | 2019 | # | OPEN | 527 | 75.2857 | FICL | 10 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | PH 1:REPL 14,000' OF 4AR IN TIER 3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2019-11-15 | 2019-11-15 | COMP | 2019-11-19 | 2019-11-19 | COMP | 2019-11-19 | 2019-11-19 | COMP | 2019-11-19 | 2019-11-20 | COMP | 2019-11-20 | 2019-12-16 | COMP | 2019-12-16 | 2019-12-18 | 4 | 29 | 309471.46
35113104 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.2 | 06/26/2019 | 117492198 | 06/25/2019 | # | Not assigned | 40 | Closed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.08202.1106 | LOS GATOS 1106 | 043 | SANTA CLARA CO | 5535211 | CWSP SPO - SH 08 | 1,399.000 | 1,399.000 | 08W | 2019 | 10/31/2020 | 2020 | 493 | 70.4286 | CLSD | 12 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | PH 1:REPL 14,000' OF 4AR IN TIER 3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2019-12-19 | 2019-12-19 | COMP | 2020-01-06 | 2020-01-06 | COMP | 2020-01-06 | 2020-01-06 | COMP | 2020-01-14 | 2020-05-06 | COMP | 2020-05-06 | 2020-07-09 | COMP | 2020-07-09 | 2020-07-09 | 18 | 185 | 414310.67
35113105 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.4 | 06/26/2019 | 117492229 | 06/25/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.08202.1106 | LOS GATOS 1106 | 043 | SANTA CLARA CO | 5535211 | CWSP SPO - SH 08 | 3,582.000 | 38.000 | 08W | 2019 | # | OPEN | 527 | 75.2857 | DOCC | 8 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | PH 1:REPL 14,000' OF 4AR IN TIER 3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2020-11-15 | 2020-11-15 | COMP | 2020-11-19 | 2020-11-19 | COMP | 2020-11-19 | 2020-11-19 | INPR | 2020-11-19 | 0 | # | 0 | 0 | # | 0 | 0 | 4 | -44154 | 1179135.63
35113106 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.2B | 06/26/2019 | 117492252 | 06/25/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.08202.1106 | LOS GATOS 1106 | 043 | SANTA CLARA CO | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2019 | # | OPEN | 527 | 75.2857 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Los Gatos 1106 - LB44 - Ph 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 4961.97
35113107 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.3C | 06/26/2019 | 117492254 | 06/25/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.08202.1106 | LOS GATOS 1106 | 043 | SANTA CLARA CO | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2019 | # | OPEN | 527 | 75.2857 | ESTS | 2 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Los Gatos 1106 - LB44 - Ph 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 5237.24
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D | 06/26/2019 | 117492255 | 06/25/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.08202.1106 | LOS GATOS 1106 | 043 | SANTA CLARA CO | 5535211 | CWSP SPO - SH 08 | 3,807.000 | 0.000 | 08W | 2019 | # | OPEN | 527 | 75.2857 | CONS | 7 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Los Gatos 1106 - LB44 - Ph 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 502245.85
35113109 | CWSP - LOS GATOS 1106 - LB44 - PHASE 3.2 | 06/26/2019 | 117492258 | 06/25/2019 | # | Not assigned | 40 | Closed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.08202.1106 | LOS GATOS 1106 | 043 | SANTA CLARA CO | 5535211 | CWSP SPO - SH 08 | 681.000 | 681.000 | 08W | 2019 | 10/31/2020 | 2020 | 493 | 70.4286 | CLSD | 12 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Los Gatos 1106 - LB44 - Ph 3.1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2019-12-18 | 2019-12-18 | COMP | 2019-12-09 | 2019-12-19 | COMP | 2019-12-19 | 2019-12-19 | COMP | 2020-01-07 | 2020-02-13 | COMP | 2020-02-13 | 2020-02-26 | COMP | 2020-02-26 | 2020-02-28 | 1 | 71 | 284792.26
35113110 | CWSP - LOS GATOS 1106 - LB44 - PHASE 3.3 | 06/26/2019 | 117492259 | 06/25/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.08202.1106 | LOS GATOS 1106 | 043 | SANTA CLARA CO | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2019 | # | OPEN | 527 | 75.2857 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Los Gatos 1106 - LB44 - Ph 3.1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 4616.09
35113111 | CWSP - LOS GATOS 1106 - LB44 - PHASE 3.4 | 06/26/2019 | 117492280 | 06/25/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.08202.1106 | LOS GATOS 1106 | 043 | SANTA CLARA CO | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2019 | # | OPEN | 527 | 75.2857 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Los Gatos 1106 - LB44 - Ph 3.1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 4291.67
35113871 | SILVERADO 2104 RECONDUCTOR - PHASE 2 | 07/02/2019 | 117556201 | 07/02/2019 | # | Not assigned | 30 | Technically Completed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.04343.2104 | SILVERADO 2104 | 028 | NAPA COUNTY | 5786200 | CWSP - Silverado 2104 - Ph 2 | 794.000 | 650.000 | 08W | 2019 | # | OPEN | 521 | 74.4286 | FICL | 10 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | SILVERADO 2104 RECONDUCTOR PROJECT | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2019-12-13 | 2019-12-13 | COMP | 2020-08-18 | 2020-08-18 | COMP | 2020-08-18 | 2020-08-18 | COMP | 2020-08-18 | 2020-08-19 | COMP | 2020-08-19 | 2020-08-25 | COMP | 2020-08-25 | 2020-08-25 | 249 | 7 | 64435.74
35113945 | CWSP - BRUNSWICK 1102 - LR 1010 | 07/03/2019 | 117557031 | 07/02/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/30/2020 | ED.15248.1102.RECL | RECLOSERS | 029 | NEVADA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2019 | # | OPEN | 520 | 74.2857 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BRUNSWICK 1102 - LR 1010 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 2782.78
35113946 | CWSP - WYANDOTTE 1103 – LR 1974 | 07/03/2019 | 117557032 | 07/02/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/30/2020 | ED.10291.1103.RECL | RECLOSERS | 004 | BUTTE COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2019 | # | OPEN | 520 | 74.2857 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - WYANDOTTE 1103 – LR 1974 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 846.56
35113947 | CWSP - LOS GATOS 1107 – LR 60114 | 07/03/2019 | 117557035 | 07/02/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/30/2020 | ED.08202.1107.RECL | RECLOSERS | 044 | SANTA CRUZ COU | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2019 | # | OPEN | 520 | 74.2857 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - LOS GATOS 1107 – LR 60114 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 1904.68
35113950 | CWSP - BIG BASIN 1101 - 10296 - PH 1.2 | 07/03/2019 | 117560045 | 07/03/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.76-L110300000.STRU.POLE | COAST L1103 POLES | 044 | SANTA CRUZ COU | 5535211 | CWSP SPO - SH 08 | 18,848.000 | 0.000 | 08W | 2019 | # | OPEN | 520 | 74.2857 | UNSC | 6 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BIG BASIN 1101 - LR 10296 - PH1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 100243.1
35113951 | CWSP - BIG BASIN 1101 - 10296 - PH 1.3 | 07/03/2019 | 117560047 | 07/03/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.76-L110300000.STRU.POLE | COAST L1103 POLES | 044 | SANTA CRUZ COU | 5535211 | CWSP SPO - SH 08 | 13,637.000 | 0.000 | 08W | 2019 | # | OPEN | 520 | 74.2857 | UNSC | 6 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BIG BASIN 1101 - LR 10296 - PH1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 107029.79
35113952 | *CANC* BB1101-LR10296-PH1.4 | 07/03/2019 | 117560072 | 07/03/2019 | # | Not assigned | 40 | Closed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.76-L110300000.STRU.POLE | COAST L1103 POLES | 044 | SANTA CRUZ COU | 5786126 | CWSP - BIG BASIN 1101 - LR 10296 - PH1.4 | 0.000 | 0.000 | 08W | 2019 | 11/03/2019 | 2019 | 123 | 17.5714 | CLSD | 12 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BIG BASIN 1101 - LR 10296 - PH1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 2019-11-03 | 2019-11-03 | # | 2019-11-03 | 2019-11-03 | # | 2019-11-03 | 2019-11-03 | COMP | 2019-10-29 | 2019-10-29 | COMP | 2019-10-29 | 2019-10-29 | COMP | 2019-10-29 | 2019-10-29 | 0 | -5 | 0
35113953 | *CANC* BB1101-LR10296-PH1.5 | 07/03/2019 | 117560075 | 07/03/2019 | # | Not assigned | 40 | Closed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.76-L110300000.STRU.POLE | COAST L1103 POLES | 044 | SANTA CRUZ COU | 5786127 | CWSP - BIG BASIN 1101 - LR 10296 - PH1.5 | 0.000 | 0.000 | 08W | 2019 | 11/03/2019 | 2019 | 123 | 17.5714 | CLSD | 12 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BIG BASIN 1101 - LR 10296 - PH1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 2019-11-03 | 2019-11-03 | # | 2019-11-03 | 2019-11-03 | # | 2019-11-03 | 2019-11-03 | COMP | 2019-10-29 | 2019-10-29 | COMP | 2019-10-29 | 2019-10-29 | COMP | 2019-10-29 | 2019-10-29 | 0 | -5 | 0
35113954 | *CANC* BB1101-LR10296-PH1.6 | 07/03/2019 | 117560076 | 07/03/2019 | # | Not assigned | 40 | Closed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.76-L110300000.STRU.POLE | COAST L1103 POLES | 044 | SANTA CRUZ COU | 5786129 | CWSP - BIG BASIN 1101 - LR 10296 - PH1.6 | 0.000 | 0.000 | 08W | 2019 | 11/03/2019 | 2019 | 123 | 17.5714 | CLSD | 12 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BIG BASIN 1101 - LR 10296 - PH1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 2019-11-03 | 2019-11-03 | # | 2019-11-03 | 2019-11-03 | # | 2019-11-03 | 2019-11-03 | COMP | 2019-10-29 | 2019-10-29 | COMP | 2019-10-29 | 2019-10-29 | COMP | 2019-10-29 | 2019-10-29 | 0 | -5 | 0
35113955 | *CANC* B1101-LR10296-PH1.7 | 07/03/2019 | 117560077 | 07/03/2019 | # | Not assigned | 40 | Closed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.76-L110300000.STRU.POLE | COAST L1103 POLES | 044 | SANTA CRUZ COU | 5786130 | CWSP - BIG BASIN 1101 - LR 10296 - PH1.7 | 0.000 | 0.000 | 08W | 2019 | 11/03/2019 | 2019 | 123 | 17.5714 | CLSD | 12 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BIG BASIN 1101 - LR 10296 - PH1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 2019-11-03 | 2019-11-03 | # | 2019-11-03 | 2019-11-03 | # | 2019-11-03 | 2019-11-03 | COMP | 2019-10-29 | 2019-10-29 | COMP | 2019-10-29 | 2019-10-29 | COMP | 2019-10-29 | 2019-10-29 | 0 | -5 | 0
35113993 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.2 | 07/03/2019 | 117501693 | 06/28/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/01/2020 | ED.16320.1101 | WEST POINT 1101 | 003 | AMADOR COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2019 | # | OPEN | 520 | 74.2857 | ESTS | 2 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - WEST POINT 1101 - LR 12256 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 13485.76
35113994 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.3 | 07/03/2019 | 117501694 | 06/28/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/01/2020 | ED.16320.1101 | WEST POINT 1101 | 003 | AMADOR COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2019 | # | OPEN | 520 | 74.2857 | ADER | 3 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - WEST POINT 1101 - LR 12256 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 28688.85
35113995 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.4 | 07/03/2019 | 117501695 | 06/28/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/01/2020 | ED.16320.1101 | WEST POINT 1101 | 003 | AMADOR COUNTY | 5535211 | CWSP SPO - SH 08 | 6,115.000 | 0.000 | 08W | 2019 | # | OPEN | 520 | 74.2857 | PEND | 5 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - WEST POINT 1101 - LR 12256 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 27041.17
35113996 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.5 | 07/03/2019 | 117501697 | 06/28/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/01/2020 | ED.16320.1101 | WEST POINT 1101 | 003 | AMADOR COUNTY | 5786015 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.5 | 6,536.000 | 0.000 | 08W | 2019 | # | OPEN | 520 | 74.2857 | PEND | 5 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - WEST POINT 1101 - LR 12256 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 90174.81
35113997 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.6 | 07/03/2019 | 117500608 | 06/27/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/27/2019 | ED.16320.1101 | WEST POINT 1101 | 003 | AMADOR COUNTY | 5786016 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.6 | 6,919.000 | 0.000 | 08W | 2019 | # | OPEN | 520 | 74.2857 | PEND | 5 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - WEST POINT 1101 - LR 12256 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 69252.28
35113998 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.7 | 07/03/2019 | 117500659 | 06/27/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/27/2019 | ED.16320.1101 | WEST POINT 1101 | 003 | AMADOR COUNTY | 5786017 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.7 | 5,952.000 | 0.000 | 08W | 2019 | # | OPEN | 520 | 74.2857 | PEND | 5 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - WEST POINT 1101 - LR 12256 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 108661.78
35113999 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.8 | 07/03/2019 | 117500661 | 06/27/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/27/2019 | ED.16320.1101 | WEST POINT 1101 | 003 | AMADOR COUNTY | 5786134 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.8 | 8,978.000 | 0.000 | 08W | 2019 | # | OPEN | 520 | 74.2857 | ESTS | 2 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - WEST POINT 1101 - LR 12256 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 9527.41
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 | 07/03/2019 | 117500499 | 06/27/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/06/2019 | ED.16375.1102 | PINE GROVE 1102 | 003 | AMADOR COUNTY | 5785991 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 | 7,860.000 | 0.000 | 08W | 2019 | # | OPEN | 520 | 74.2857 | CONS | 7 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP: PINE GROVE 1102 LR1222 PH 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 1073966.44
35114041 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.3 | 07/03/2019 | 117500692 | 06/27/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/17/2021 | ED.16375.1102 | PINE GROVE 1102 | 003 | AMADOR COUNTY | 5535211 | CWSP SPO - SH 08 | 6,879.000 | 0.000 | 08W | 2019 | # | OPEN | 520 | 74.2857 | CONS | 7 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP: PINE GROVE 1102 LR1222 PH 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 401762.34
35114042 | OCGC PINE GROVE 1102 - LR1222 - PH 1.4 | 07/03/2019 | 117500694 | 06/27/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 09/01/2020 | ED.16375.1102 | PINE GROVE 1102 | 003 | AMADOR COUNTY | 5535211 | CWSP SPO - SH 08 | 7,126.000 | 7,126.000 | 08W | 2019 | # | OPEN | 520 | 74.2857 | MAPP | 9 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP: PINE GROVE 1102 LR1222 PH 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2020-08-25 | 2020-08-25 | COMP | 2020-11-12 | 2020-11-12 | COMP | 2020-11-12 | 2020-11-12 | COMP | 2020-11-12 | 2020-11-16 | INPR | 2020-11-16 | 0 | # | 0 | 0 | 79 | -44147 | 1027776.85
35114043 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.5 | 07/03/2019 | 117502840 | 06/28/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/06/2019 | ED.16375.1102 | PINE GROVE 1102 | 003 | AMADOR COUNTY | 5535211 | CWSP SPO - SH 08 | 5,998.000 | 5,998.000 | 08W | 2019 | # | OPEN | 520 | 74.2857 | DOCC | 8 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP: PINE GROVE 1102 LR1222 PH 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2020-08-14 | 2020-08-14 | COMP | 2020-08-25 | 2020-08-25 | COMP | 2020-08-25 | 2020-08-25 | COMP | 2020-08-25 | 2020-09-08 | COMP | 2020-09-08 | 2020-10-09 | COMP | 2020-10-09 | 2020-10-13 | 11 | 49 | 691890.4
35114044 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.6 | 07/03/2019 | 117502841 | 06/28/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/06/2019 | ED.16375.1102 | PINE GROVE 1102 | 003 | AMADOR COUNTY | 5535211 | CWSP SPO - SH 08 | 6,126.000 | 0.000 | 08W | 2019 | # | OPEN | 520 | 74.2857 | CONS | 7 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP: PINE GROVE 1102 LR1222 PH 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 973650.22
35114045 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.7 | 07/03/2019 | 117502843 | 06/28/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/06/2019 | ED.16375.1102 | PINE GROVE 1102 | 003 | AMADOR COUNTY | 5535211 | CWSP SPO - SH 08 | 7,602.000 | 0.000 | 08W | 2019 | # | OPEN | 520 | 74.2857 | UNSC | 6 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP: PINE GROVE 1102 LR1222 PH 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 272233.82
35114046 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.2 | 07/03/2019 | 117499462 | 06/27/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2019 | ED.95-K291100000.STRU.POLE | MOTHER LODE K2911 POLES | 003 | AMADOR COUNTY | 5785996 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.2 | 6,754.000 | 0.000 | 08W | 2019 | # | OPEN | 520 | 74.2857 | PEND | 5 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP: PINE GROVE 1102 LR1222 ZONE WFH PH | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 36543.69
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 | 07/03/2019 | 117499466 | 06/27/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.95-K291100000.STRU.POLE | MOTHER LODE K2911 POLES | 003 | AMADOR COUNTY | 5785997 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 | 7,344.000 | 0.000 | 08W | 2019 | # | OPEN | 520 | 74.2857 | CONS | 7 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP: PINE GROVE 1102 LR1222 ZONE WFH PH | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 703697.08
35114049 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.4 | 07/03/2019 | 117499469 | 06/27/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.95-K291100000.STRU.POLE | MOTHER LODE K2911 POLES | 003 | AMADOR COUNTY | 5785998 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.4 | 8,392.000 | 0.000 | 08W | 2019 | # | OPEN | 520 | 74.2857 | CONS | 7 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP: PINE GROVE 1102 LR1222 ZONE WFH PH | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 969596.79
35114050 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.5 | 07/03/2019 | 117499593 | 06/27/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2019 | ED.95-K291100000.STRU.POLE | MOTHER LODE K2911 POLES | 003 | AMADOR COUNTY | 5785999 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.5 | 6,564.000 | 0.000 | 08W | 2019 | # | OPEN | 520 | 74.2857 | UNSC | 6 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP: PINE GROVE 1102 LR1222 ZONE WFH PH | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 346849.33
35114051 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.6 | 07/03/2019 | 117502234 | 06/28/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2019 | ED.95-K290800000.STRU.POLE | MOTHER LODE K2908 POLES | 003 | AMADOR COUNTY | 5786000 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.6 | 7,698.000 | 0.000 | 08W | 2019 | # | OPEN | 520 | 74.2857 | CONS | 7 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP: PINE GROVE 1102 LR1222 ZONE WFH PH | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 808640.72
35114052 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.7 | 07/03/2019 | 117502368 | 06/28/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2019 | ED.95-K291000000.STRU.POLE | MOTHER LODE K2910 POLES | 003 | AMADOR COUNTY | 5786136 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.7 | 4,291.000 | 0.000 | 08W | 2019 | # | OPEN | 520 | 74.2857 | UNSC | 6 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP: PINE GROVE 1102 LR1222 ZONE WFH PH | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 164420.81
35114053 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.8 | 07/03/2019 | 117502416 | 06/28/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2019 | ED.95-K290500000.STRU.POLE | MOTHER LODE K2905 POLES | 003 | AMADOR COUNTY | 5786137 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.8 | 8,731.000 | 0.000 | 08W | 2019 | # | OPEN | 520 | 74.2857 | ADER | 3 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP: PINE GROVE 1102 LR1222 ZONE WFH PH | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 49942.29
35114100 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.2 | 07/03/2019 | 117545617 | 07/01/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.08362.2106 | CAMP EVERS 2106 | 044 | SANTA CRUZ COU | 5535211 | CWSP SPO - SH 08 | 5,487.000 | 0.000 | 08W | 2019 | # | OPEN | 520 | 74.2857 | CONS | 7 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - CAMP EVERS 2106 - 5020 - PHASE 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | INPR | 2020-05-20 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 150708.76
35114101 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.3 | 07/03/2019 | 117545618 | 07/01/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.08362.2106 | CAMP EVERS 2106 | 044 | SANTA CRUZ COU | 5535211 | CWSP SPO - SH 08 | 6,873.000 | 0.000 | 08W | 2019 | # | OPEN | 520 | 74.2857 | MAPP | 9 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - CAMP EVERS 2106 - 5020 - PHASE 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2020-08-04 | 2020-08-04 | COMP | 2020-05-08 | 2020-11-24 | COMP | 2020-11-24 | 2020-11-24 | COMP | 2020-11-24 | 2020-11-30 | INPR | 2020-11-30 | 0 | # | 0 | 0 | 112 | -44159 | 832220.54
35114102 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.4 | 07/03/2019 | 117545619 | 07/01/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.08362.2106 | CAMP EVERS 2106 | 044 | SANTA CRUZ COU | 5535211 | CWSP SPO - SH 08 | 4,147.000 | 0.000 | 08W | 2019 | # | OPEN | 520 | 74.2857 | CONS | 7 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - CAMP EVERS 2106 - 5020 - PHASE 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | INPR | 2020-05-20 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 202886.91
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 | 07/03/2019 | 117560686 | 07/03/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.08362.2106 | CAMP EVERS 2106 | 044 | SANTA CRUZ COU | 5535211 | CWSP SPO - SH 08 | 5,963.000 | 0.000 | 08W | 2019 | # | OPEN | 520 | 74.2857 | CONS | 7 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - CAMP EVERS 2106 - 5020 - PHASE 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 500090.17
35114104 | XCWSP - CAMP EVERS 2106 - LR5020 -PH 2.6 | 07/03/2019 | 117560687 | 07/03/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.08362.2106 | CAMP EVERS 2106 | 044 | SANTA CRUZ COU | 5535211 | CWSP SPO - SH 08 | 7,619.000 | 7,962.000 | 08W | 2019 | # | OPEN | 520 | 74.2857 | CONS | 7 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - CAMP EVERS 2106 - 5020 - PHASE 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 1519241.12
35114431 | CWSP - MORAGA 1101 - LR108540 - PH5 | 07/09/2019 | 117572146 | 07/09/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/30/2020 | ED.01380.1101 | MORAGA 1101 | 007 | CONTRA COSTA C | 5535211 | CWSP SPO - SH 08 | 7,673.000 | 6,850.000 | 08W | 2019 | # | OPEN | 514 | 73.4286 | DOCC | 8 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - MORAGA 1101 (VARIOUS) - OCB | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2020-03-23 | 2020-03-23 | COMP | 2019-12-17 | 2020-04-17 | COMP | 2020-04-17 | 2020-04-17 | COMP | 2020-06-02 | 2020-06-29 | COMP | 2020-06-29 | 2020-09-16 | COMP | 2020-09-16 | 2020-09-16 | 25 | 152 | 4097004.43
35115046 | CWSP - MIWUK 1701 - LR 10600 PH 1.2 | 07/11/2019 | 117496177 | 06/26/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 07/13/2021 | ED.16366.1701 | MIWUK 1701 | 055 | TUOLUMNE COUNT | 5535211 | CWSP SPO - SH 08 | 13,219.000 | 0.000 | 08W | 2019 | # | OPEN | 512 | 73.1429 | UNSC | 6 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - MIWUK 1701 - LR 10600 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 188060.67
35115047 | CWSP - MIWUK 1701 - LR 10600 PH 1.3 | 07/11/2019 | 117496281 | 06/26/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 06/11/2021 | ED.16366.1701 | MIWUK 1701 | 055 | TUOLUMNE COUNT | 5535211 | CWSP SPO - SH 08 | 11,492.000 | 0.000 | 08W | 2019 | # | OPEN | 512 | 73.1429 | PEND | 5 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - MIWUK 1701 - LR 10600 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 175746.56
35115048 | CWSP - MIWUK 1701 - LR 10600 PH 1.4 | 07/11/2019 | 117497751 | 06/27/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 09/24/2021 | ED.16366.1701 | MIWUK 1701 | 055 | TUOLUMNE COUNT | 5535211 | CWSP SPO - SH 08 | 12,346.000 | 0.000 | 08W | 2019 | # | OPEN | 512 | 73.1429 | ADER | 3 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - MIWUK 1701 - LR 10600 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 32354.83
35115049 | CWSP - MIWUK 1701 - LR 10600 PH 1.5 | 07/11/2019 | 117497752 | 06/27/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 07/13/2021 | ED.16366.1701 | MIWUK 1701 | 055 | TUOLUMNE COUNT | 5535211 | CWSP SPO - SH 08 | 11,947.000 | 0.000 | 08W | 2019 | # | OPEN | 512 | 73.1429 | ESTS | 2 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - MIWUK 1701 - LR 10600 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 214634.21
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 | 07/11/2019 | 117495948 | 06/26/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 04/30/2021 | ED.16366.1701 | MIWUK 1701 | 055 | TUOLUMNE COUNT | 5535211 | CWSP SPO - SH 08 | 8,512.000 | 0.000 | 08W | 2019 | # | OPEN | 512 | 73.1429 | CONS | 7 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - MIWUK 1701_OCB WILDFIRE HARDENING | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 762696.42
35115051 | CWSP - MIWUK 1701_OCB - PH 1.3 | 07/11/2019 | 117495949 | 06/26/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.16366.1701 | MIWUK 1701 | 055 | TUOLUMNE COUNT | 5535211 | CWSP SPO - SH 08 | 5,484.000 | 0.000 | 08W | 2019 | # | OPEN | 512 | 73.1429 | CONS | 7 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - MIWUK 1701_OCB WILDFIRE HARDENING | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 60106.48
35115052 | CWSP - MIWUK 1701_OCB - PH 1.4 | 07/11/2019 | 117496040 | 06/26/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.16366.1701 | MIWUK 1701 | 055 | TUOLUMNE COUNT | 5535211 | CWSP SPO - SH 08 | 8,548.000 | 0.000 | 08W | 2019 | # | OPEN | 512 | 73.1429 | CONS | 7 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - MIWUK 1701_OCB WILDFIRE HARDENING | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 335729.41
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 | 07/11/2019 | # | #N/A | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.16366.1701 | MIWUK 1701 | 055 | TUOLUMNE COUNT | 5535211 | CWSP SPO - SH 08 | 9,083.000 | 0.000 | 08W | 2019 | # | OPEN | 512 | 73.1429 | CONS | 7 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - MIWUK 1701_OCB WILDFIRE HARDENING | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | INPR | 2020-08-13 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 524056.85
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 | 07/11/2019 | 117490035 | 06/25/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 04/30/2021 | ED.16366.1701 | MIWUK 1701 | 055 | TUOLUMNE COUNT | 5535211 | CWSP SPO - SH 08 | 7,529.000 | 0.000 | 08W | 2019 | # | OPEN | 512 | 73.1429 | CONS | 7 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Miwuk 1701 - OCB Zone - Phase 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 1118364.24
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 | 07/11/2019 | 117490481 | 06/25/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/04/2020 | ED.16366.1701 | MIWUK 1701 | 055 | TUOLUMNE COUNT | 5785987 | CWSP - MIWUK 1701 – OCB - PH 2.3 | 11,269.000 | 0.000 | 08W | 2019 | # | OPEN | 512 | 73.1429 | CONS | 7 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Miwuk 1701 - OCB Zone - Phase 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 736816.76
35115056 | CWSP - MIWUK 1701 – OCB - PH 2.4 | 07/11/2019 | 117490489 | 06/25/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/04/2020 | ED.16366.1701 | MIWUK 1701 | 055 | TUOLUMNE COUNT | 5535211 | CWSP SPO - SH 08 | 9,236.000 | 0.000 | 08W | 2019 | # | OPEN | 512 | 73.1429 | CONS | 7 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Miwuk 1701 - OCB Zone - Phase 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 394101.38
35115057 | CWSP - MIWUK 1701 - OCB - PH2.5 | 07/11/2019 | 117489824 | 06/25/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 03/23/2021 | ED.16366.1701 | MIWUK 1701 | 055 | TUOLUMNE COUNT | 5785989 | CWSP - MIWUK 1701 – OCB - PH 2.5 | 13,653.000 | 0.000 | 08W | 2019 | # | OPEN | 512 | 73.1429 | UNSC | 6 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Miwuk 1701 - OCB Zone - Phase 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 133033.57
35115080 | BR-02-10-W (E) HARVEY RD PARB | 07/11/2019 | 117590702 | 07/11/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/26/2020 | JY | JUNK YARD FL TO HOLD DELETED DATA | 004 | BUTTE COUNTY | 5786123 | 08W Rebuild | 0.000 | 0.000 | 08W | 2019 | # | OPEN | 512 | 73.1429 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35115084 | BR-01-11-W (E) MONTNA DR PARB | 07/11/2019 | 117591834 | 07/11/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/26/2020 | JY | JUNK YARD FL TO HOLD DELETED DATA | 004 | BUTTE COUNTY | 5786123 | 08W Rebuild | 0.000 | 0.000 | 08W | 2019 | # | OPEN | 512 | 73.1429 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35115147 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.2 | 07/12/2019 | 117496196 | 06/26/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 08/12/2020 | ED.15248.1103 | BRUNSWICK 1103 | 029 | NEVADA COUNTY | 5535211 | CWSP SPO - SH 08 | 7,076.000 | 6,200.000 | 08W | 2019 | # | OPEN | 511 | 73 | DOCC | 8 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Brunswick 1103 LR50070 Zone-Ph3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2020-08-13 | 2020-08-13 | COMP | 2020-05-12 | 2020-08-20 | COMP | 2020-08-20 | 2020-09-17 | INPR | 2020-09-17 | 0 | # | 0 | 0 | # | 0 | 0 | 35 | -44091 | 860960.53
35115148 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.3 | 07/12/2019 | 117496270 | 06/26/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 11/13/2020 | ED.15248.1103 | BRUNSWICK 1103 | 029 | NEVADA COUNTY | 5535211 | CWSP SPO - SH 08 | 11,210.000 | 0.000 | 08W | 2019 | # | OPEN | 511 | 73 | DOCC | 8 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Brunswick 1103 LR50070 Zone-Ph3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2020-11-20 | 2020-11-20 | INPR | 2020-12-01 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | -44155 | 0 | 1808409.94
35115149 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.4 | 07/12/2019 | 117496274 | 06/26/2019 | # | Not assigned | 30 | Technically Completed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 06/08/2020 | ED.15248.1103 | BRUNSWICK 1103 | 029 | NEVADA COUNTY | 5535211 | CWSP SPO - SH 08 | 6,500.000 | 6,265.000 | 08W | 2019 | # | OPEN | 511 | 73 | FICL | 10 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Brunswick 1103 LR50070 Zone-Ph3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2020-06-08 | 2020-06-08 | COMP | 2020-05-08 | 2020-06-10 | COMP | 2020-06-10 | 2020-06-10 | COMP | 2020-06-10 | 2020-06-17 | COMP | 2020-06-17 | 2020-08-05 | COMP | 2020-08-05 | 2020-08-11 | 2 | 62 | 1894895.91
35115150 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.5 | 07/12/2019 | 117496277 | 06/26/2019 | # | Not assigned | 30 | Technically Completed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 08/25/2020 | ED.15248.1103 | BRUNSWICK 1103 | 029 | NEVADA COUNTY | 5535211 | CWSP SPO - SH 08 | 6,221.000 | 6,353.000 | 08W | 2019 | # | OPEN | 511 | 73 | FICL | 10 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Brunswick 1103 LR50070 Zone-Ph3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2020-09-10 | 2020-08-25 | COMP | 2020-09-09 | 2020-09-09 | COMP | 2020-09-09 | 2020-09-10 | COMP | 2020-09-10 | 2020-09-11 | COMP | 2020-09-11 | 2020-10-15 | COMP | 2020-10-15 | 2020-10-16 | 0 | 36 | 550882.08
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | 07/12/2019 | 117493857 | 06/26/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.15248.1103 | BRUNSWICK 1103 | 029 | NEVADA COUNTY | 5535211 | CWSP SPO - SH 08 | 10,013.000 | 0.000 | 08W | 2019 | # | OPEN | 511 | 73 | CONS | 7 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Brunswick 1103 LR50070 Zone-Ph2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 913400.64
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | 07/12/2019 | 117495855 | 06/26/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.15248.1103 | BRUNSWICK 1103 | 029 | NEVADA COUNTY | 5535211 | CWSP SPO - SH 08 | 8,271.000 | 0.000 | 08W | 2019 | # | OPEN | 511 | 73 | CONS | 7 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Brunswick 1103 LR50070 Zone-Ph2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 352864.51
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | 07/12/2019 | 117495859 | 06/26/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.15248.1103 | BRUNSWICK 1103 | 029 | NEVADA COUNTY | 5535211 | CWSP SPO - SH 08 | 9,476.000 | 0.000 | 08W | 2019 | # | OPEN | 511 | 73 | CONS | 7 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Brunswick 1103 LR50070 Zone-Ph2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 396996.04
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | 07/12/2019 | 117496036 | 06/26/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.15248.1103 | BRUNSWICK 1103 | 029 | NEVADA COUNTY | 5535211 | CWSP SPO - SH 08 | 8,692.000 | 0.000 | 08W | 2019 | # | OPEN | 511 | 73 | CONS | 7 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Brunswick 1103 LR50070 Zone-Ph2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 876562.67
35115155 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.2 | 07/12/2019 | 117491298 | 06/25/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 10/30/2020 | ED.15248.1103 | BRUNSWICK 1103 | 029 | NEVADA COUNTY | 5535211 | CWSP SPO - SH 08 | 10,024.000 | 9,232.000 | 08W | 2019 | # | OPEN | 511 | 73 | CONS | 7 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Brunswick 1103 LR50070 Zone-Ph1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | INPR | 2020-05-12 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 2970484.53
35115156 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.3 | 07/12/2019 | 117491998 | 06/25/2019 | # | Not assigned | 30 | Technically Completed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 07/03/2020 | ED.15248.1103 | BRUNSWICK 1103 | 029 | NEVADA COUNTY | 5535211 | CWSP SPO - SH 08 | 10,244.000 | 9,844.000 | 08W | 2019 | # | OPEN | 511 | 73 | FICL | 10 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Brunswick 1103 LR50070 Zone-Ph1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2020-07-03 | 2020-07-03 | COMP | 2020-05-12 | 2020-07-09 | COMP | 2020-07-09 | 2020-07-09 | COMP | 2020-07-09 | 2020-07-10 | COMP | 2020-07-10 | 2020-09-08 | COMP | 2020-09-08 | 2020-09-08 | 6 | 61 | 2718471.05
35115157 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.4 | 07/12/2019 | 117492085 | 06/25/2019 | # | Not assigned | 30 | Technically Completed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 10/20/2020 | ED.15248.1103 | BRUNSWICK 1103 | 029 | NEVADA COUNTY | 5535211 | CWSP SPO - SH 08 | 15,728.000 | 10,162.000 | 08W | 2019 | # | OPEN | 511 | 73 | FICL | 10 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Brunswick 1103 LR50070 Zone-Ph1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2020-09-30 | 2020-09-30 | COMP | 2020-10-02 | 2020-10-09 | COMP | 2020-10-09 | 2020-10-09 | COMP | 2020-10-09 | 2020-10-13 | COMP | 2020-10-13 | 2020-11-24 | COMP | 2020-11-24 | 2020-11-24 | 9 | 46 | 3417547.63
35115158 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.5 | 07/12/2019 | 117492102 | 06/25/2019 | # | Not assigned | 30 | Technically Completed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 07/16/2020 | ED.15248.1103 | BRUNSWICK 1103 | 029 | NEVADA COUNTY | 5535211 | CWSP SPO - SH 08 | 11,108.000 | 10,413.000 | 08W | 2019 | # | OPEN | 511 | 73 | FICL | 10 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Brunswick 1103 LR50070 Zone-Ph1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2020-07-16 | 2020-07-16 | COMP | 2020-05-28 | 2020-07-20 | COMP | 2020-07-20 | 2020-07-20 | COMP | 2020-07-20 | 2020-07-21 | COMP | 2020-07-21 | 2020-09-08 | COMP | 2020-09-08 | 2020-09-15 | 4 | 57 | 2311078.43
35115847 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.2 | 07/16/2019 | 117602056 | 07/15/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2019 | ED.95-NN36010000.STRU.POLE | Angels Camp MAP NN3601 POLES | 005 | CALAVERAS COUN | 5786018 | CWSP-SALT SPRINGS 2102-LR3142ZONE-PH 2.2 | 9,916.000 | 0.000 | 08W | 2019 | # | OPEN | 507 | 72.4286 | ESTS | 2 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-SALT SPRINGS 2102-LR3142 ZONE-PH 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 53250.06
35115848 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.3 | 07/16/2019 | 117602057 | 07/15/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2019 | ED.95-NN36010000.STRU.POLE | Angels Camp MAP NN3601 POLES | 005 | CALAVERAS COUN | 5786019 | CWSP-SALT SPRINGS 2102-LR3142ZONE-PH 2.3 | 8,685.000 | 0.000 | 08W | 2019 | # | OPEN | 507 | 72.4286 | PEND | 5 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-SALT SPRINGS 2102-LR3142 ZONE-PH 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 136569.08
35115849 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.4 | 07/16/2019 | 117602058 | 07/15/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2019 | ED.95-NN36010000.STRU.POLE | Angels Camp MAP NN3601 POLES | 005 | CALAVERAS COUN | 5786020 | CWSP-SALT SPRINGS 2102-LR3142ZONE-PH 2.4 | 9,187.000 | 0.000 | 08W | 2019 | # | OPEN | 507 | 72.4286 | PEND | 5 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-SALT SPRINGS 2102-LR3142 ZONE-PH 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 756952.44
35115850 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.5 | 07/16/2019 | 117602059 | 07/15/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2019 | ED.95-NN36010000.STRU.POLE | Angels Camp MAP NN3601 POLES | 005 | CALAVERAS COUN | 5786021 | CWSP-SALT SPRINGS 2102-LR3142ZONE-PH 2.5 | 6,856.000 | 0.000 | 08W | 2019 | # | OPEN | 507 | 72.4286 | UNSC | 6 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-SALT SPRINGS 2102-LR3142 ZONE-PH 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 118085.26
35115851 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.6 | 07/16/2019 | 117602170 | 07/15/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2019 | ED.95-NN36010000.STRU.POLE | Angels Camp MAP NN3601 POLES | 005 | CALAVERAS COUN | 5535211 | CWSP SPO - SH 08 | 6,653.000 | 0.000 | 08W | 2019 | # | OPEN | 507 | 72.4286 | PEND | 5 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-SALT SPRINGS 2102-LR3142 ZONE-PH 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 70225.44
35115852 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.7 | 07/16/2019 | 117602171 | 07/15/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2019 | ED.95-NN36010000.STRU.POLE | Angels Camp MAP NN3601 POLES | 005 | CALAVERAS COUN | 5535211 | CWSP SPO - SH 08 | 8,590.000 | 0.000 | 08W | 2019 | # | OPEN | 507 | 72.4286 | PEND | 5 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-SALT SPRINGS 2102-LR3142 ZONE-PH 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 88300.84
35115853 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.2 | 07/16/2019 | 117601683 | 07/15/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2019 | ED.95-NN36010000.STRU.POLE | Angels Camp MAP NN3601 POLES | 005 | CALAVERAS COUN | 5535211 | CWSP SPO - SH 08 | 10,559.000 | 0.000 | 08W | 2019 | # | OPEN | 507 | 72.4286 | UNSC | 6 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-SALT SPRINGS 2102-LR3142&L491-PHA 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 316066.6
35115854 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.3 | 07/16/2019 | 117601685 | 07/15/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2019 | ED.95-NN36010000.STRU.POLE | Angels Camp MAP NN3601 POLES | 005 | CALAVERAS COUN | 5535211 | CWSP SPO - SH 08 | 5,762.000 | 0.000 | 08W | 2019 | # | OPEN | 507 | 72.4286 | CONS | 7 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-SALT SPRINGS 2102-LR3142&L491-PHA 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 97979.66
35115855 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.4 | 07/16/2019 | 117601687 | 07/15/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2019 | ED.95-NN36010000.STRU.POLE | Angels Camp MAP NN3601 POLES | 005 | CALAVERAS COUN | 5535211 | CWSP SPO - SH 08 | 6,672.000 | 0.000 | 08W | 2019 | # | OPEN | 507 | 72.4286 | CONS | 7 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-SALT SPRINGS 2102-LR3142&L491-PHA 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 1546805.02
35115856 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.5 | 07/16/2019 | 117601688 | 07/15/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2019 | ED.95-NN36010000.STRU.POLE | Angels Camp MAP NN3601 POLES | 005 | CALAVERAS COUN | 5786025 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.5 | 10,616.000 | 0.000 | 08W | 2019 | # | OPEN | 507 | 72.4286 | UNSC | 6 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-SALT SPRINGS 2102-LR3142&L491-PHA 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 153909.91
35115857 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.6 | 07/16/2019 | 117601884 | 07/15/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2019 | ED.95-NN36010000.STRU.POLE | Angels Camp MAP NN3601 POLES | 005 | CALAVERAS COUN | 5786026 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.6 | 6,445.000 | 0.000 | 08W | 2019 | # | OPEN | 507 | 72.4286 | PEND | 5 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-SALT SPRINGS 2102-LR3142&L491-PHA 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 33344.29
35115858 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.7 | 07/16/2019 | 117601885 | 07/15/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2019 | ED.95-NN36010000.STRU.POLE | Angels Camp MAP NN3601 POLES | 005 | CALAVERAS COUN | 5786027 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.7 | 6,883.000 | 0.000 | 08W | 2019 | # | OPEN | 507 | 72.4286 | PEND | 5 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-SALT SPRINGS 2102-LR3142&L491-PHA 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 93919.45
35116180 | R-1123 RECONDUCTOR PAST R9229 - WHARF ST | 07/16/2019 | 117602173 | 07/15/2019 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2021 | ED.01347.1123 | RICHMOND R 1123 | 007 | CONTRA COSTA C | 5535457 | DO 08 - Monthly Forecast Only | 1,781.000 | 0.000 | 08J | 2019 | # | OPEN | 507 | 72.4286 | PEND | 5 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 10072.94
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 | 07/17/2019 | 117604600 | 07/16/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/25/2020 | ED.16366.1701 | MIWUK 1701 | 055 | TUOLUMNE COUNT | 5535211 | CWSP SPO - SH 08 | 7,319.000 | 0.000 | 08W | 2019 | # | OPEN | 506 | 72.2857 | CONS | 7 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | MIWUK 1701 LR8060 08W WILDFIRE HARDENING | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | INPR | 2020-09-02 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 783810.24
35116384 | CWSP - MIWUK 1701 - LR 8060 - PH 1.3 | 07/17/2019 | 117604604 | 07/16/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/25/2020 | ED.16366.1701 | MIWUK 1701 | 055 | TUOLUMNE COUNT | 5535211 | CWSP SPO - SH 08 | 9,700.000 | 0.000 | 08W | 2019 | # | OPEN | 506 | 72.2857 | CONS | 7 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | MIWUK 1701 LR8060 08W WILDFIRE HARDENING | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 50045.46
35116385 | CWSP - MIWUK 1701 - LR 8060 - PH 1.4 | 07/17/2019 | 117604609 | 07/16/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 03/31/2021 | ED.16366.1701 | MIWUK 1701 | 055 | TUOLUMNE COUNT | 5535211 | CWSP SPO - SH 08 | 7,376.000 | 0.000 | 08W | 2019 | # | OPEN | 506 | 72.2857 | PEND | 5 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | MIWUK 1701 LR8060 08W WILDFIRE HARDENING | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 48183.45
35116388 | CWSP - MIWUK 1701 - LR 8060 - PH 1.5 | 07/17/2019 | 117604672 | 07/16/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/25/2020 | ED.16366.1701 | MIWUK 1701 | 055 | TUOLUMNE COUNT | 5535211 | CWSP SPO - SH 08 | 13,109.000 | 0.000 | 08W | 2019 | # | OPEN | 506 | 72.2857 | PEND | 5 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | MIWUK 1701 LR8060 08W WILDFIRE HARDENING | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 389969.86
35116389 | CWSP - MIWUK 1701 - LR 8060 - PH 1.6 | 07/17/2019 | 117604676 | 07/16/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/25/2020 | ED.16366.1701 | MIWUK 1701 | 055 | TUOLUMNE COUNT | 5535211 | CWSP SPO - SH 08 | 9,970.000 | 0.000 | 08W | 2019 | # | OPEN | 506 | 72.2857 | ESTS | 2 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | MIWUK 1701 LR8060 08W WILDFIRE HARDENING | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 47349.69
35116390 | CWSP - MIWUK 1701 - LR 8060 - PH 1.7 | 07/17/2019 | 117604678 | 07/16/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/03/2020 | ED.16366.1701 | MIWUK 1701 | 055 | TUOLUMNE COUNT | 5535211 | CWSP SPO - SH 08 | 4,715.000 | 0.000 | 08W | 2019 | # | OPEN | 506 | 72.2857 | CONS | 7 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | MIWUK 1701 LR8060 08W WILDFIRE HARDENING | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 691658.98
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 | 07/17/2019 | 117605551 | 07/16/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/27/2019 | ED.16366.1702 | MIWUK 1702 | 055 | TUOLUMNE COUNT | 5785976 | CWSP - MIWUK 1702 - OCB - PH 1.2 | 10,932.000 | 0.000 | 08W | 2019 | # | OPEN | 506 | 72.2857 | CONS | 7 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - MIWUK 1702_OCB WILDFIRE HARDENING | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | INPR | 2020-05-19 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 1051497.75
35116393 | CWSP - MIWUK 1702 - OCB - PH 1.3 | 07/17/2019 | 117605554 | 07/16/2019 | # | Not assigned | 30 | Technically Completed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/27/2019 | ED.16366.1702 | MIWUK 1702 | 055 | TUOLUMNE COUNT | 5535211 | CWSP SPO - SH 08 | 13,485.000 | 13,742.000 | 08W | 2019 | # | OPEN | 506 | 72.2857 | FICL | 10 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - MIWUK 1702_OCB WILDFIRE HARDENING | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2019-12-26 | 2020-03-20 | COMP | 2019-12-26 | 2020-03-25 | COMP | 2020-03-25 | 2020-03-25 | COMP | 2020-03-25 | 2020-03-30 | COMP | 2020-03-30 | 2020-05-13 | COMP | 2020-05-13 | 2020-05-14 | 90 | 50 | 4269376.5
35116394 | CWSP - MIWUK 1702 - OCB - PH 1.4 | 07/17/2019 | 117605556 | 07/16/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/27/2019 | ED.16366.1702 | MIWUK 1702 | 055 | TUOLUMNE COUNT | 5535211 | CWSP SPO - SH 08 | 8,790.000 | 8,790.000 | 08W | 2019 | # | OPEN | 506 | 72.2857 | FICL | 10 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - MIWUK 1702_OCB WILDFIRE HARDENING | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2020-06-23 | 2020-06-23 | COMP | 2020-02-24 | 2020-06-25 | COMP | 2020-06-25 | 2020-06-25 | COMP | 2020-06-25 | 2020-06-26 | COMP | 2020-06-26 | 2020-08-19 | COMP | 2020-08-19 | 2020-08-21 | 2 | 57 | 1467650.78
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 | 07/17/2019 | 117605558 | 07/16/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.16366.1702 | MIWUK 1702 | 055 | TUOLUMNE COUNT | 5535211 | CWSP SPO - SH 08 | 9,032.000 | 0.000 | 08W | 2019 | # | OPEN | 506 | 72.2857 | CONS | 7 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - MIWUK 1702_OCB WILDFIRE HARDENING | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 576288.21
35116396 | CWSP-MIWUK 1702-LR8090-PH 1.2 | 07/17/2019 | 117604756 | 07/16/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 11/23/2021 | ED.16366.1702 | MIWUK 1702 | 055 | TUOLUMNE COUNT | 5535211 | CWSP SPO - SH 08 | 11,216.000 | 0.000 | 08W | 2019 | # | OPEN | 506 | 72.2857 | CONS | 7 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-MIWUK 1702-LR 8090 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 512309.21
35116397 | CWSP-MIWUK 1702-LR8090-PH 1.3 | 07/17/2019 | 117604668 | 07/16/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/27/2019 | ED.16366.1702 | MIWUK 1702 | 055 | TUOLUMNE COUNT | 5535211 | CWSP SPO - SH 08 | 10,614.000 | 0.000 | 08W | 2019 | # | OPEN | 506 | 72.2857 | PEND | 5 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-MIWUK 1702-LR 8090 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 32096.92
35116398 | CWSP-MIWUK 1702-LR8090-PH 1.4 | 07/17/2019 | 117604615 | 07/16/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 07/23/2021 | ED.16366.1702 | MIWUK 1702 | 055 | TUOLUMNE COUNT | 5535211 | CWSP SPO - SH 08 | 11,376.000 | 0.000 | 08W | 2019 | # | OPEN | 506 | 72.2857 | ESTS | 2 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-MIWUK 1702-LR 8090 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 29702.1
35116399 | CWSP-MIWUK 1702-LR8090-PH 1.5 | 07/17/2019 | 117604337 | 07/16/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/27/2019 | ED.16366.1702 | MIWUK 1702 | 055 | TUOLUMNE COUNT | 5785932 | CWSP - MIWUK 1702 - LR 8090 - PH 1.5 | 9,687.000 | 0.000 | 08W | 2019 | # | OPEN | 506 | 72.2857 | UNSC | 6 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-MIWUK 1702-LR 8090 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 164288.65
35116440 | CWSP-MIWUK 1702-LR8090-PH 1.6 | 07/17/2019 | 117604512 | 07/16/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 03/04/2022 | ED.16366.1702 | MIWUK 1702 | 055 | TUOLUMNE COUNT | 5535211 | CWSP SPO - SH 08 | 9,980.000 | 0.000 | 08W | 2019 | # | OPEN | 506 | 72.2857 | ESTS | 2 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-MIWUK 1702-LR 8090 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 43176.17
35116441 | CWSP-MIWUK 1702-LR 38218-PH1.2 | 07/17/2019 | 117605164 | 07/16/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 06/22/2021 | ED.16366.1702 | MIWUK 1702 | 055 | TUOLUMNE COUNT | 5535211 | CWSP SPO - SH 08 | 17,147.000 | 0.000 | 08W | 2019 | # | OPEN | 506 | 72.2857 | ESTS | 2 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - MIWUK 1702_LR38218 WILDFIRE HARDE | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 39701.61
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 | 07/17/2019 | 117605169 | 07/16/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 11/17/2020 | ED.16366.1702 | MIWUK 1702 | 055 | TUOLUMNE COUNT | 5535211 | CWSP SPO - SH 08 | 12,386.000 | 0.000 | 08W | 2019 | # | OPEN | 506 | 72.2857 | CONS | 7 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - MIWUK 1702_LR38218 WILDFIRE HARDE | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | INPR | 2020-06-23 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 1721388.61
35116443 | CWSP-MIWUK 1702-LR 38218-PH 1.4 | 07/17/2019 | 117605181 | 07/16/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.16366.1702 | MIWUK 1702 | 055 | TUOLUMNE COUNT | 5535211 | CWSP SPO - SH 08 | 10,249.000 | 0.000 | 08W | 2019 | # | OPEN | 506 | 72.2857 | CONS | 7 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - MIWUK 1702_LR38218 WILDFIRE HARDE | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | INPR | 2020-07-25 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 690856.98
35116444 | CWSP-MIWUK 1702-LR 38218-PH 1.5 | 07/17/2019 | 117605182 | 07/16/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.16366.1702 | MIWUK 1702 | 055 | TUOLUMNE COUNT | 5785984 | CWSP - MIWUK 1702 - LR 38218 - PH 1.5 | 11,100.000 | 0.000 | 08W | 2019 | # | OPEN | 506 | 72.2857 | CONS | 7 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - MIWUK 1702_LR38218 WILDFIRE HARDE | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 855082.86
35116511 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.2 | 07/18/2019 | 117608780 | 07/17/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.16282.1702 | STANISLAUS 1702 | 005 | CALAVERAS COUN | 5535211 | CWSP SPO - SH 08 | 6,348.000 | 0.000 | 08W | 2019 | # | OPEN | 505 | 72.1429 | UNSC | 6 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-STANISLAUS1702-LR1888-PH2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 69023.19
35116512 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.3 | 07/18/2019 | 117608788 | 07/17/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.16282.1702 | STANISLAUS 1702 | 005 | CALAVERAS COUN | 5535211 | CWSP SPO - SH 08 | 9,236.000 | 0.000 | 08W | 2019 | # | OPEN | 505 | 72.1429 | PEND | 5 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-STANISLAUS1702-LR1888-PH2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 82946.79
35116513 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.4 | 07/18/2019 | 117608814 | 07/17/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.16282.1702 | STANISLAUS 1702 | 005 | CALAVERAS COUN | 5786043 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.4 | 8,690.000 | 0.000 | 08W | 2019 | # | OPEN | 505 | 72.1429 | PEND | 5 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-STANISLAUS1702-LR1888-PH2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 34430.23
35116514 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.5 | 07/18/2019 | 117608818 | 07/17/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.16282.1702 | STANISLAUS 1702 | 005 | CALAVERAS COUN | 5786044 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.5 | 10,852.000 | 0.000 | 08W | 2019 | # | OPEN | 505 | 72.1429 | PEND | 5 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-STANISLAUS1702-LR1888-PH2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 43156.24
35116515 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.2 | 07/18/2019 | 117607998 | 07/17/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.16282.1702 | STANISLAUS 1702 | 005 | CALAVERAS COUN | 5786036 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.2 | 9,222.000 | 0.000 | 08W | 2019 | # | OPEN | 505 | 72.1429 | UNSC | 6 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-STANISLAUS1702-LR1888-PH1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 122242.57
35116516 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.3 | 07/18/2019 | 117608020 | 07/17/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.16282.1702 | STANISLAUS 1702 | 005 | CALAVERAS COUN | 5786037 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.3 | 4,825.000 | 0.000 | 08W | 2019 | # | OPEN | 505 | 72.1429 | PEND | 5 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-STANISLAUS1702-LR1888-PH1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 99742.58
35116517 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.5 | 07/18/2019 | 117608185 | 07/17/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.16282.1702 | STANISLAUS 1702 | 005 | CALAVERAS COUN | 5786039 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.5 | 12,677.000 | 0.000 | 08W | 2019 | # | OPEN | 505 | 72.1429 | PEND | 5 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-STANISLAUS1702-LR1888-PH1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 86816.25
35116518 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.6 | 07/18/2019 | 117608188 | 07/17/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.16282.1702 | STANISLAUS 1702 | 005 | CALAVERAS COUN | 5786040 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.6 | 10,866.000 | 0.000 | 08W | 2019 | # | OPEN | 505 | 72.1429 | PEND | 5 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-STANISLAUS1702-LR1888-PH1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 50144.84
35116519 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.4 | 07/18/2019 | 117608026 | 07/17/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.16282.1702 | STANISLAUS 1702 | 005 | CALAVERAS COUN | 5786038 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.4 | 9,268.000 | 0.000 | 08W | 2019 | # | OPEN | 505 | 72.1429 | UNSC | 6 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-STANISLAUS1702-LR1888-PH1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 37441.53
35116800 | CWSP-MIWUK 1702-LR 6018-PHASE 1.2 | 07/18/2019 | 117605265 | 07/16/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.16366.1702 | MIWUK 1702 | 055 | TUOLUMNE COUNT | 5535211 | CWSP SPO - SH 08 | 7,525.000 | 0.000 | 08W | 2019 | # | OPEN | 505 | 72.1429 | CONS | 7 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - MIWUK 1702-LR 6018-PHASE 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 1065707.56
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 | 07/18/2019 | 117605266 | 07/16/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.16366.1702 | MIWUK 1702 | 055 | TUOLUMNE COUNT | 5535211 | CWSP SPO - SH 08 | 6,747.000 | 0.000 | 08W | 2019 | # | OPEN | 505 | 72.1429 | UNSC | 6 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - MIWUK 1702-LR 6018-PHASE 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 1283799.71
35116802 | CWSP-MIWUK 1702-LR 6018-PHASE 1.4 | 07/18/2019 | 117605267 | 07/16/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.16366.1702 | MIWUK 1702 | 055 | TUOLUMNE COUNT | 5535211 | CWSP SPO - SH 08 | 11,739.000 | 1,260.000 | 08W | 2019 | # | OPEN | 505 | 72.1429 | CONS | 7 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - MIWUK 1702-LR 6018-PHASE 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 1624834.79
35116803 | CWSP-MIWUK 1702-LR 6018-PHASE 1.5 | 07/18/2019 | 117605268 | 07/16/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.16366.1702 | MIWUK 1702 | 055 | TUOLUMNE COUNT | 5785964 | CWSP - MIWUK 1702 - LR 6018 - PH 1.5 | 12,028.000 | 0.000 | 08W | 2019 | # | OPEN | 505 | 72.1429 | PEND | 5 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - MIWUK 1702-LR 6018-PHASE 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 153912.61
35116804 | CWSP-MIWUK 1702-LR 6018-PHASE 1.6 | 07/18/2019 | 117605269 | 07/16/2019 | # | Not assigned | 30 | Technically Completed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.16366.1702 | MIWUK 1702 | 055 | TUOLUMNE COUNT | 5535211 | CWSP SPO - SH 08 | 5,387.000 | 5,340.000 | 08W | 2019 | # | OPEN | 505 | 72.1429 | FICL | 10 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - MIWUK 1702-LR 6018-PHASE 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2020-08-22 | 2020-08-22 | COMP | 2020-09-29 | 2020-10-02 | COMP | 2020-10-02 | 2020-10-02 | COMP | 2020-10-02 | 2020-10-05 | COMP | 2020-10-05 | 2020-10-27 | COMP | 2020-10-27 | 2020-10-30 | 41 | 28 | 1189745.34
35116921 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.2 | 07/19/2019 | 117605453 | 07/16/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/25/2021 | ED.16282.1702 | STANISLAUS 1702 | 005 | CALAVERAS COUN | 5786030 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.2 | 8,059.000 | 0.000 | 08W | 2019 | # | OPEN | 504 | 72 | PEND | 5 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | STANISLAUS 1702 LR1804 ZONE WFH LEVEL 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 80401.13
35116922 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.3 | 07/19/2019 | 117605456 | 07/16/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/25/2021 | ED.16282.1702 | STANISLAUS 1702 | 005 | CALAVERAS COUN | 5786031 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.3 | 6,121.000 | 0.000 | 08W | 2019 | # | OPEN | 504 | 72 | PEND | 5 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | STANISLAUS 1702 LR1804 ZONE WFH LEVEL 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 47983.06
35116923 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.4 | 07/19/2019 | 117605459 | 07/16/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/25/2021 | ED.16282.1702 | STANISLAUS 1702 | 005 | CALAVERAS COUN | 5786032 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.4 | 6,378.000 | 0.000 | 08W | 2019 | # | OPEN | 504 | 72 | ADER | 3 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | STANISLAUS 1702 LR1804 ZONE WFH LEVEL 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 128287.05
35116924 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.5 | 07/19/2019 | 117605550 | 07/16/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/25/2021 | ED.16282.1702 | STANISLAUS 1702 | 005 | CALAVERAS COUN | 5786033 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.5 | 9,032.000 | 0.000 | 08W | 2019 | # | OPEN | 504 | 72 | ADER | 3 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | STANISLAUS 1702 LR1804 ZONE WFH LEVEL 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 88313.32
35116925 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.6 | 07/19/2019 | 117605552 | 07/16/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/25/2021 | ED.16282.1702 | STANISLAUS 1702 | 005 | CALAVERAS COUN | 5786034 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.6 | 9,147.000 | 0.000 | 08W | 2019 | # | OPEN | 504 | 72 | ADER | 3 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | STANISLAUS 1702 LR1804 ZONE WFH LEVEL 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 45562.64
35116926 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.7 | 07/19/2019 | 117605553 | 07/16/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/25/2021 | ED.16282.1702 | STANISLAUS 1702 | 005 | CALAVERAS COUN | 5786035 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.7 | 7,718.000 | 0.000 | 08W | 2019 | # | OPEN | 504 | 72 | PEND | 5 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | STANISLAUS 1702 LR1804 ZONE WFH LEVEL 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 59031.1
35116930 | WD - RECONDUCTOR GV2102 - NEAR 64763 | 07/19/2019 | 117621052 | 07/19/2019 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/31/2021 | ED.76-R190900000.STRU.POLE | COAST R1909 POLES | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 1,550.000 | 0.000 | 08J | 2019 | # | OPEN | 504 | 72 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 373.7
35117007 | CWSP-ORO FINO 1102 OCB & LR2090 PH 1.1 | 07/23/2019 | 114708276 | 06/18/2018 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1102 | ORO FINO 1102 | 004 | BUTTE COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2019 | # | OPEN | 500 | 71.4286 | ESTS | 2 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-ORO FINO 1102 OCB & LR2090 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 8400.23
35117102 | LOYOLA1102 LS CO1611 REPL 300FT OH LINE | 07/22/2019 | 117626386 | 07/22/2019 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/25/2021 | ED.80-G120200000.STRU.POLE | DE ANZA G1202 POLES | 043 | SANTA CLARA CO | 5517127 | DO 08 - Monthly Forecast Only | 500.000 | 0.000 | 08J | 2019 | # | OPEN | 501 | 71.5714 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35117180 | RECOND GREEN VALLEY 2103 REF# S011CC105 | 07/22/2019 | 113663786 | 10/04/2017 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/29/2019 | ED.08319.2103 | GREEN VALLEY 2103 | 044 | SANTA CRUZ COU | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2019 | # | OPEN | 501 | 71.5714 | ESTS | 2 | E470 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 10934.87
35117354 | RECONDUCTOR LO2102 NEAR 7955 | 07/24/2019 | 117632451 | 07/23/2019 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 07/24/2021 | ED.04-Q210000000.STRU.POLE | KING CITY Q21 POLES | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 1,082.000 | 0.000 | 08J | 2019 | # | OPEN | 499 | 71.2857 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 2828.38
35117398 | BR-01-12-W (E) MYRTLE WAY, PARB | 07/24/2019 | 117636680 | 07/24/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/26/2020 | ED.17-S331500000.STRU.POLE | PARADISE S3315 POLES | 004 | BUTTE COUNTY | 5786123 | 08W Rebuild | 0.000 | 0.000 | 08W | 2019 | # | OPEN | 499 | 71.2857 | ESTS | 2 | E470 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 8973.6
35117409 | SM 1110 - RECON 650 FT W 2CU | 07/24/2019 | 117606445 | 07/16/2019 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/30/2021 | ED.18267.1110 | SANTA MARIA 1110 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2019 | # | OPEN | 499 | 71.2857 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 337.78
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | 07/24/2019 | 117634567 | 07/24/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/04/2020 | ED.15248.1103 | BRUNSWICK 1103 | 029 | NEVADA COUNTY | 5535211 | CWSP SPO - SH 08 | 11,395.000 | 0.000 | 08W | 2019 | # | OPEN | 499 | 71.2857 | CONS | 7 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Brunswick 1103 LR50070 Zone-Ph3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 1059309.24
35117444 | CWSP - VOLTA 1102 LR 1648 PH 2.1 | 07/24/2019 | 114750733 | 07/03/2018 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | JY | JUNK YARD FL TO HOLD DELETED DATA | 045 | SHASTA COUNTY | 5535211 | CWSP SPO - SH 08 | 12,656.000 | 12,656.000 | 08W | 2019 | # | OPEN | 499 | 71.2857 | DOCC | 8 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - VOLTA 1102 LR 1648 PH 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2020-09-11 | 2020-06-11 | COMP | 2019-10-15 | 2020-09-11 | COMP | 2020-09-11 | 2020-09-11 | INPR | 2020-09-11 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | -44085 | 2158472.27
35117455 | BR-02-04-W (E) HERMAN PARB | 07/25/2019 | 117637039 | 07/24/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/26/2020 | JY | JUNK YARD FL TO HOLD DELETED DATA | 004 | BUTTE COUNTY | 5786123 | 08W Rebuild | 0.000 | 0.000 | 08W | 2019 | # | OPEN | 498 | 71.1429 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35117540 | BR-02-01-W (E) CLARK RD & SAN JOSE PARB | 07/24/2019 | 117636827 | 07/24/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/26/2020 | ED.17-S340700000.STRU.POLE | PARADISE S3407 POLES | 004 | BUTTE COUNTY | 5786123 | 08W Rebuild | 0.000 | 0.000 | 08W | 2019 | # | OPEN | 499 | 71.2857 | ADER | 3 | E470 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35117544 | VIERRA 1703 RECONDUCTOR | 07/25/2019 | 117638665 | 07/25/2019 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2021 | ED.16270.1703 | VIERRA 1703 | 039 | SAN JOAQUIN CO | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2019 | # | OPEN | 498 | 71.1429 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 3992.5
35117983 | BR-02-07-W (E) DOLORES DR, PARB | 07/25/2019 | 117641061 | 07/25/2019 | 35132419 | BR-02-07-F (E) DOLORES DR PARB | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/26/2020 | ED.17-S341700000.STRU.POLE | PARADISE S3417 POLES | 004 | BUTTE COUNTY | 5786123 | 08W Rebuild | 0.000 | 0.000 | 08W | 2019 | # | OPEN | 498 | 71.1429 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 1424612.7
35117986 | BR-02-08-W (E) DIAMOND LN PARB | 07/25/2019 | 117641707 | 07/25/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/26/2020 | JY | JUNK YARD FL TO HOLD DELETED DATA | 004 | BUTTE COUNTY | 5786123 | 08W Rebuild | 0.000 | 0.000 | 08W | 2019 | # | OPEN | 498 | 71.1429 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35118422 | BR-02-13-W (E) LANCASTER DR PARB | 07/29/2019 | 117662965 | 07/29/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/26/2020 | ED.17-S342100000.STRU.POLE | PARADISE S3421 POLES | 004 | BUTTE COUNTY | 5786123 | 08W Rebuild | 0.000 | 0.000 | 08W | 2019 | # | OPEN | 494 | 70.5714 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35118425 | BR-04-04-W (E) VALLEY VIEW PARB | 07/29/2019 | 117663992 | 07/29/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/26/2020 | ED.17-S332100000.STRU.POLE | PARADISE S3321 POLES | 004 | BUTTE COUNTY | 5786123 | 08W Rebuild | 0.000 | 0.000 | 08W | 2019 | # | OPEN | 494 | 70.5714 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 207.73
35118433 | BR-04-10-W (E) CRESTVIEW PARB | 07/30/2019 | 117664813 | 07/30/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/26/2020 | ED.17-T330100000.STRU.POLE | PARADISE T3301 POLES | 004 | BUTTE COUNTY | 5786123 | 08W Rebuild | 0.000 | 0.000 | 08W | 2019 | # | OPEN | 493 | 70.4286 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35118438 | BR-11-01-W (E) FOSTER RD, PARB | 07/30/2019 | 117665053 | 07/30/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/26/2020 | ED.17-T330700000.STRU.POLE | PARADISE T3307 POLES | 004 | BUTTE COUNTY | 5786123 | 08W Rebuild | 0.000 | 0.000 | 08W | 2019 | # | OPEN | 493 | 70.4286 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 3023.83
35118502 | BR-06-01-W (E) DELIA WAY, PARB | 07/30/2019 | 117665302 | 07/30/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/26/2020 | ED.17-S342100000.STRU.POLE | PARADISE S3421 POLES | 004 | BUTTE COUNTY | 5786123 | 08W Rebuild | 0.000 | 0.000 | 08W | 2019 | # | OPEN | 493 | 70.4286 | ESTS | 2 | E470 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 79248.63
35118504 | BR-06-02-W (E) COPELAND RD PARB | 07/30/2019 | 117665914 | 07/30/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/26/2020 | ED.17-T330400000.STRU.POLE | PARADISE T3304 POLES | 004 | BUTTE COUNTY | 5786123 | 08W Rebuild | 0.000 | 0.000 | 08W | 2019 | # | OPEN | 493 | 70.4286 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35118511 | BR-06-03-W (E) DEL MAR AVE PARB | 07/30/2019 | 117666940 | 07/30/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/26/2020 | ED.17-T330500000.STRU.POLE | PARADISE T3305 POLES | 004 | BUTTE COUNTY | 5786123 | 08W Rebuild | 0.000 | 0.000 | 08W | 2019 | # | OPEN | 493 | 70.4286 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35118513 | BR-06-04-W (E) HEAVENLY PARB | 07/30/2019 | 117667199 | 07/30/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/26/2020 | JY | JUNK YARD FL TO HOLD DELETED DATA | 004 | BUTTE COUNTY | 5786123 | 08W Rebuild | 0.000 | 0.000 | 08W | 2019 | # | OPEN | 493 | 70.4286 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35118515 | BR-07-02-W (E) YOUNG AVE PARB | 07/30/2019 | 117667802 | 07/30/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/26/2020 | ED.17-S342200000.STRU.POLE | PARADISE S3422 POLES | 004 | BUTTE COUNTY | 5786123 | 08W Rebuild | 0.000 | 0.000 | 08W | 2019 | # | OPEN | 493 | 70.4286 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35118516 | BR-07-04-W_03 (E) PECK LN PARB | 07/30/2019 | 117668385 | 07/30/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/26/2020 | ED.17-T340200000.STRU.POLE | PARADISE T3402 POLES | 004 | BUTTE COUNTY | 5786123 | 08W Rebuild | 0.000 | 0.000 | 08W | 2019 | # | OPEN | 493 | 70.4286 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35118517 | BR-07-05-W (E) FLICKER LN, PARB | 07/30/2019 | 117668710 | 07/30/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/26/2020 | JY | JUNK YARD FL TO HOLD DELETED DATA | 004 | BUTTE COUNTY | 5786123 | 08W Rebuild | 0.000 | 0.000 | 08W | 2019 | # | OPEN | 493 | 70.4286 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 1115629.62
35118518 | BR-07-06-W (E) NIELSEN DR PARB | 07/30/2019 | 117668717 | 07/30/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/26/2020 | JY | JUNK YARD FL TO HOLD DELETED DATA | 004 | BUTTE COUNTY | 5786123 | 08W Rebuild | 0.000 | 0.000 | 08W | 2019 | # | OPEN | 493 | 70.4286 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 188.32
35118519 | BR-07-08-W (E) FOLAND RD PARB | 07/30/2019 | 117668843 | 07/30/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/26/2020 | ED.17-T340600000.STRU.POLE | PARADISE T3406 POLES | 004 | BUTTE COUNTY | 5786123 | 08W Rebuild | 0.000 | 0.000 | 08W | 2019 | # | OPEN | 493 | 70.4286 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 72.17
35118662 | BR-11-07-W (E) APPLE LN PARB | 07/31/2019 | 117670907 | 07/31/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/26/2020 | ED.17-T322000000.STRU.POLE | PARADISE T3220 POLES | 004 | BUTTE COUNTY | 5786123 | 08W Rebuild | 0.000 | 0.000 | 08W | 2019 | # | OPEN | 492 | 70.2857 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35118663 | BR-01-01-W (E) HEAVENS GATE PARB | 07/31/2019 | 117670940 | 07/31/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/26/2020 | ED.17-S331700000.STRU.POLE | PARADISE S3317 POLES | 004 | BUTTE COUNTY | 5786123 | 08W Rebuild | 0.000 | 0.000 | 08W | 2019 | # | OPEN | 492 | 70.2857 | UNSC | 6 | E470 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 772850.55
35118671 | BR-MG-1A-W DRAKE CT PARB | 07/31/2019 | 117673517 | 07/31/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/26/2020 | ED.17-R342100000.STRU.POLE | PARADISE R3421 POLES | 004 | BUTTE COUNTY | 5786123 | 08W Rebuild | 0.000 | 0.000 | 08W | 2019 | # | OPEN | 492 | 70.2857 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35118673 | BR-MG-4A-W WICHITA DR PARB | 07/31/2019 | 117673635 | 07/31/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/26/2020 | ED.17-S330400000.STRU.POLE | PARADISE S3304 POLES | 004 | BUTTE COUNTY | 5786123 | 08W Rebuild | 0.000 | 0.000 | 08W | 2019 | # | OPEN | 492 | 70.2857 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35118674 | BR-MG-05-W PUEBLO DR PARB | 07/31/2019 | 117673731 | 07/31/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/26/2020 | ED.17-S330500000.STRU.POLE | PARADISE S3305 POLES | 004 | BUTTE COUNTY | 5786123 | 08W Rebuild | 0.000 | 0.000 | 08W | 2019 | # | OPEN | 492 | 70.2857 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35118675 | BR-MG-05-W SHAW CIR PARB | 07/31/2019 | 117673779 | 07/31/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/26/2020 | JY | JUNK YARD FL TO HOLD DELETED DATA | 004 | BUTTE COUNTY | 5786123 | 08W Rebuild | 0.000 | 0.000 | 08W | 2019 | # | OPEN | 492 | 70.2857 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35118700 | BR-10-01-W (E) STARLIGHT CT PARB | 07/30/2019 | 117668855 | 07/30/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/26/2020 | ED.17-T321500000.STRU.POLE | PARADISE T3215 POLES | 004 | BUTTE COUNTY | 5786123 | 08W Rebuild | 0.000 | 0.000 | 08W | 2019 | # | OPEN | 493 | 70.4286 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35118701 | *CANC* BR-10-02-W (E) CIRCLEWOOD DR, PA | 07/30/2019 | 117668858 | 07/30/2019 | # | Not assigned | 40 | Closed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/26/2020 | ED.17-T321500000.STRU.POLE | PARADISE T3215 POLES | 004 | BUTTE COUNTY | 5786123 | 08W Rebuild | 0.000 | 0.000 | 08W | 2019 | 11/05/2020 | 2020 | 464 | 66.2857 | CLSD | 12 | E470 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 2020-11-05 | 2020-11-05 | # | 2020-11-05 | 2020-11-05 | # | 2020-11-05 | 2020-11-05 | COMP | 2020-10-01 | 2020-10-01 | COMP | 2020-10-01 | 2020-10-01 | COMP | 2020-10-01 | 2020-10-01 | 0 | -35 | -191.67
35118702 | BR-11-03-W (E) GREGS WAY, PARB | 07/30/2019 | 117669020 | 07/30/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/26/2020 | JY | JUNK YARD FL TO HOLD DELETED DATA | 004 | BUTTE COUNTY | 5786123 | 08W Rebuild | 0.000 | 0.000 | 08W | 2019 | # | OPEN | 493 | 70.4286 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 297541.88
35118925 | STOCKTON A 1106 WIREDOWN RECONDUCTOR | 08/01/2019 | 117697734 | 08/01/2019 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 02/02/2022 | ED.16237.1106 | STOCKTON A 1106 | 039 | SAN JOAQUIN CO | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2019 | # | OPEN | 491 | 70.1429 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 3037.29
35119401 | CWSP - CAMP EVERS 2106 - 5020 - PHASE 2 | 08/07/2019 | 114758056 | 07/06/2018 | # | Not assigned | 30 | Technically Completed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/30/2020 | ED.08362.2106 | CAMP EVERS 2106 | 044 | SANTA CRUZ COU | 5535211 | CWSP SPO - SH 08 | 5,683.000 | 5,642.000 | 08W | 2019 | # | OPEN | 485 | 69.2857 | FICL | 10 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - CAMP EVERS 2106 - 5020 - PHASE 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2020-06-15 | 2020-06-15 | COMP | 2020-07-15 | 2020-07-15 | COMP | 2020-07-15 | 2020-07-16 | COMP | 2020-07-16 | 2020-07-16 | COMP | 2020-07-16 | 2020-08-14 | COMP | 2020-08-14 | 2020-08-18 | 31 | 33 | 1276770.87
35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E | 08/07/2019 | 117721840 | 08/06/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.08202.1106 | LOS GATOS 1106 | 043 | SANTA CLARA CO | 5535211 | CWSP SPO - SH 08 | 4,483.000 | 0.000 | 08W | 2019 | # | OPEN | 485 | 69.2857 | CONS | 7 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Los Gatos 1106 - LB44 - Ph 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 294131.27
35119966 | CWSP - LOS GATOS 1106 - LB44 - PH 2.6F | 08/07/2019 | 117721841 | 08/06/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.08202.1106 | LOS GATOS 1106 | 043 | SANTA CLARA CO | 5535211 | CWSP SPO - SH 08 | 4,325.000 | 4,309.000 | 08W | 2019 | # | OPEN | 485 | 69.2857 | DOCC | 8 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Los Gatos 1106 - LB44 - Ph 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2020-03-10 | 2020-03-10 | COMP | 2020-04-02 | 2020-04-09 | COMP | 2020-04-09 | 2020-04-09 | COMP | 2020-04-09 | 2020-04-10 | COMP | 2020-04-10 | 2020-05-13 | COMP | 2020-05-13 | 2020-05-13 | 30 | 34 | 783445.01
35119967 | CWSP - LOS GATOS 1106 - LB44 - PH 3.5 | 08/07/2019 | 117721746 | 08/06/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.08202.1106 | LOS GATOS 1106 | 043 | SANTA CLARA CO | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2019 | # | OPEN | 485 | 69.2857 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Los Gatos 1106 - LB44 - Ph 3.1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 4206.33
35119968 | CWSP - LOS GATOS 1106 - LB44 - PH 3.6 | 08/07/2019 | 117721842 | 08/06/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.08202.1106 | LOS GATOS 1106 | 043 | SANTA CLARA CO | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2019 | # | OPEN | 485 | 69.2857 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Los Gatos 1106 - LB44 - Ph 3.1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 4982.5
35119969 | CWSP - LOS GATOS 1106 - LB44 - PH 4.2 | 08/07/2019 | 117721748 | 08/06/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.08202.1106 | LOS GATOS 1106 | 043 | SANTA CLARA CO | 5535211 | CWSP SPO - SH 08 | 6,777.000 | 0.000 | 08W | 2019 | # | OPEN | 485 | 69.2857 | CONS | 7 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - LOS GATOS 1106 - LB44 - PHASE 4 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 1142816.88
35119970 | CWSP - LOS GATOS 1106 - LB44 - PH 4.3 | 08/07/2019 | 117721839 | 08/06/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.08202.1106 | LOS GATOS 1106 | 043 | SANTA CLARA CO | 5535211 | CWSP SPO - SH 08 | 3,090.000 | 0.000 | 08W | 2019 | # | OPEN | 485 | 69.2857 | DOCC | 8 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - LOS GATOS 1106 - LB44 - PHASE 4 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2020-11-19 | 2020-11-19 | COMP | 2020-11-20 | 2020-11-20 | COMP | 2020-11-20 | 2020-11-20 | INPR | 2020-11-20 | 0 | # | 0 | 0 | # | 0 | 0 | 1 | -44155 | 1368128.69
35119972 | CWSP - LOS GATOS 1106 - LB44 - PHASE 4 | 08/07/2019 | 114749460 | 07/03/2018 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/30/2020 | ED.08202.1106 | LOS GATOS 1106 | 043 | SANTA CLARA CO | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2019 | # | OPEN | 485 | 69.2857 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - LOS GATOS 1106 - LB44 - PHASE 4 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 83068.5
35120949 | CWSP- BUCOCAMP - SKYWAY PARADISE TIE PH2 | 08/14/2019 | 117755982 | 08/14/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 02/28/2020 | ED.16-T312000000.STRU.POLE | CHICO MAP T3120 POLES | 004 | BUTTE COUNTY | 5790010 | CWSP - BUCOCAMP-SKYWAY PARADISE TIE PH2 | 20,644.000 | 10,150.000 | 08W | 2019 | # | OPEN | 478 | 68.2857 | PEND | 5 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 11891055.33
35121414 | KINGSBURG 1116 - RECONDUTORING 3000 FT | 08/16/2019 | 111612187 | 05/06/2016 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/29/2022 | ED.25224.1116 | KINGSBURG 1116 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2019 | # | OPEN | 476 | 68 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 4748.05
35121739 | *CANCEL* CENTERILLE REMOVAL - BUTTE 1105 | 08/21/2019 | 117781072 | 08/20/2019 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.10308.1105 | BUTTE 1105 | 004 | BUTTE COUNTY | 5786123 | 08W Rebuild | 0.000 | 0.000 | 08W | 2019 | 09/01/2019 | 2019 | 11 | 1.5714 | CLSD | 12 | E460 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 2019-09-02 | 2019-09-02 | # | 2019-09-02 | 2019-09-02 | # | 2019-09-02 | 2019-09-02 | # | 2019-09-02 | 2019-09-02 | # | 2019-09-02 | 2019-09-02 | # | 2019-09-02 | 2019-09-02 | 0 | 0 | 0
35121772 | GANSO 1104 RECOND 2900FT TO 2AR | 08/19/2019 | 113723017 | 10/11/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/30/2022 | ED.25454.1104 | GANSO 1104 | 015 | KERN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2019 | # | OPEN | 473 | 67.5714 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 14274.83
35121909 | CLOVIS 2110 RECOND 1042FT 2AR | 08/20/2019 | 117778550 | 08/19/2019 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/28/2022 | ED.25408.2110 | CLOVIS 2110 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2019 | # | OPEN | 472 | 67.4286 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 587.25
35122142 | RECON 1684 FT 6CU W 397AL | 08/21/2019 | 117781600 | 08/20/2019 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/20/2022 | ED.18301.1101 | MORRO BAY 1101 | 040 | SAN LUIS OBISP | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2019 | # | OPEN | 471 | 67.2857 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 195.75
35122447 | *CANC* CARUTHERS 1104 RECOND 5,10*CANC | 08/21/2019 | 117784137 | 08/21/2019 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/28/2022 | ED.25237.1104 | CARUTHERS 1104 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2019 | 10/03/2019 | 2019 | 43 | 6.1429 | CLSD | 12 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 2019-10-03 | 2019-10-03 | # | 2019-10-03 | 2019-10-03 | # | 2019-10-03 | 2019-10-03 | # | 2019-10-03 | 2019-10-03 | # | 2019-10-03 | 2019-10-03 | # | 2019-10-03 | 2019-10-03 | 0 | 0 | 0
35123421 | R1 WIREDOWN RECONDUCTORING H-1110 | 08/29/2019 | 109234173 | 09/23/2014 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/26/2015 | ED.02210.1110.SWIT | SWITCHES | 041 | SAN MATEO COUN | 5517127 | DO 08 - Monthly Forecast Only | 203.000 | 0.000 | 08J | 2019 | # | OPEN | 463 | 66.1429 | ESTS | 2 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 2124.3
35123422 | PUEBLO 2102 RECOND | 08/29/2019 | 112416557 | 12/16/2016 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/30/2017 | ED.42-II35240000.STRU.POLE | SILVERADO MAP II3524 POLES | 028 | NAPA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 903.000 | 0.000 | 08J | 2019 | # | OPEN | 463 | 66.1429 | UNSC | 6 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 1597.03
35123423 | +RECON BEYOND FCO 45133, SISQUOC 1104 | 08/29/2019 | 112149414 | 11/09/2016 | # | Not assigned | 30 | Technically Completed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/09/2018 | ED.18281.1104 | SISQUOC 1104 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 526.000 | 526.000 | 08J | 2019 | # | OPEN | 463 | 66.1429 | FICL | 10 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2020-09-01 | 2020-09-01 | COMP | 2020-09-02 | 2020-09-03 | COMP | 2020-09-03 | 2020-09-03 | COMP | 2020-09-03 | 2020-09-03 | COMP | 2020-09-03 | 2020-10-13 | COMP | 2020-10-13 | 2020-10-19 | 2 | 46 | 38332.34
35123424 | RECON 815 FT TAP OFF LAUGHLIN CAPELLA 01 | 08/29/2019 | 113751593 | 10/20/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/27/2019 | ED.04341.1101.RECL | RECLOSERS | 023 | MENDOCINO COUN | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2019 | # | OPEN | 463 | 66.1429 | ESTS | 2 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 13671.89
35123425 | R2 RECONDUCT SALINAS 1106 | 08/29/2019 | 112533471 | 01/24/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/30/2018 | ED.18201.1106 | SALINAS 1106 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 1,011.000 | 0.000 | 08J | 2019 | # | OPEN | 463 | 66.1429 | PEND | 5 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 535.39
35123426 | WHISMAN 1106 CO582085 REPL 1100FT OH LN | 08/29/2019 | 112726448 | 03/31/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/20/2019 | ED.08363.1106.TXFR.TROH | OVERHEAD TRANSFORMERS | 043 | SANTA CLARA CO | 5517127 | DO 08 - Monthly Forecast Only | 1,282.000 | 0.000 | 08J | 2019 | # | OPEN | 463 | 66.1429 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 3341.97
35123427 | R7 SAN RAFAEL 1105 RECOND 1,225 FT | 08/29/2019 | 112416508 | 12/16/2016 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/30/2017 | ED.40-TT33090000.STRU.POLE | NORTH BAY MAP TT3309 POLES | 021 | MARIN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2019 | # | OPEN | 463 | 66.1429 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 6449.58
35123428 | PN WIREDOWN 17-0043197 DC-1112 | 08/29/2019 | 112928898 | 06/05/2017 | # | Not assigned | 30 | Technically Completed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/28/2018 | ED.02264.1112.SWIT | SWITCHES | 041 | SAN MATEO COUN | 5505513 | PN-OH ANNEALED/DETER CNDCTR: PM MGD | 0.000 | 0.000 | 08J | 2019 | # | OPEN | 463 | 66.1429 | DCNL | Other | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 51414.66
35123429 | R2WATSNVILLE 2101 HIGH SPLICE COND REPL | 08/29/2019 | 111767919 | 07/06/2016 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/30/2018 | JY | JUNK YARD FL TO HOLD DELETED DATA | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 1,741.000 | 0.000 | 08J | 2019 | # | OPEN | 463 | 66.1429 | CONS | 7 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | INPR | 2020-10-08 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 43052.11
35123430 | 2019 08J PN EG-1101 S072CC216 | 08/29/2019 | 113227750 | 09/08/2017 | # | Not assigned | 30 | Technically Completed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/27/2019 | ED.02257.1101.TXFR.TROH | OVERHEAD TRANSFORMERS | 041 | SAN MATEO COUN | 5505513 | PN-OH ANNEALED/DETER CNDCTR: PM MGD | 0.000 | 0.000 | 08J | 2019 | # | OPEN | 463 | 66.1429 | DCNL | Other | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 50123.75
35123901 | R1-EB- R1127- RECOND 1,850' OF 6CU | 08/30/2019 | 110568251 | 08/10/2015 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/31/2016 | ED.01347.1127 | RICHMOND R 1127 | 007 | CONTRA COSTA C | 5535457 | DO 08 - Monthly Forecast Only | 1,744.000 | 0.000 | 08J | 2019 | # | OPEN | 462 | 66 | PEND | 5 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 12972.36
35123902 | RECONDUCTOR ATWATER 1106 - WIRE DOWN | 08/30/2019 | 112841452 | 05/05/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/13/2019 | ED.25361.1106 | ATWATER 1106 | 024 | MERCED COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2019 | # | OPEN | 462 | 66 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 566.81
35123903 | NEW HOPE 1101 2,200FT RECONDUCTOR | 08/30/2019 | 112421160 | 12/20/2016 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 07/09/2021 | ED.16208.1101 | NEW HOPE 1101 | 039 | SAN JOAQUIN CO | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2019 | # | OPEN | 462 | 66 | ESTS | 2 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 5259.42
35123904 | R2 ATWATER 1103 RECONDUCTORING | 08/30/2019 | 113199100 | 08/28/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/02/2021 | ED.72-06124C0000.STRU.POLE | MERCED MAP 06124C POLES | 024 | MERCED COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2019 | # | OPEN | 462 | 66 | ADER | 3 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 7955.71
35123905 | 2019 VALLEJO B 413 HIGH SPLICE COUNT | 08/30/2019 | 113144866 | 08/11/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2019 | ED.04245.0413 | VALLEJO B 0413 | 048 | SOLANO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 1,998.000 | 0.000 | 08J | 2019 | # | OPEN | 462 | 66 | PEND | 5 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 15826.86
35123906 | +RECOND 10 SPAN 2442 4ACSR W 2ACSR | 08/30/2019 | 112434990 | 12/27/2016 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/27/2020 | ED.18281.1103 | SISQUOC 1103 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 2,442.000 | 2,442.000 | 08J | 2019 | 07/04/2020 | 2020 | 309 | 44.1429 | CLSD | 12 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2020-03-09 | 2020-03-09 | COMP | 2020-02-04 | 2020-04-01 | COMP | 2020-04-01 | 2020-04-01 | COMP | 2020-04-01 | 2020-04-02 | COMP | 2020-04-02 | 2020-05-04 | COMP | 2020-05-04 | 2020-05-11 | 23 | 40 | 87833.97
35123907 | RECONDUCT CASTROVILLE 2104 WD#16-0083838 | 08/30/2019 | 112421980 | 12/20/2016 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/29/2018 | ED.18235.2104 | CASTROVILLE 2104 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 2,648.000 | 0.000 | 08J | 2019 | # | OPEN | 462 | 66 | CONS | 7 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 101379.15
35123908 | +RECONDUCTOR - FUSE ZONE - SM1109 CKT | 08/30/2019 | 113740510 | 10/17/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.18267.1109 | SANTA MARIA 1109 | 015 | KERN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 1,612.000 | 0.000 | 08J | 2019 | # | OPEN | 462 | 66 | UNSC | 6 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 27579.55
35123909 | RECOND 21SPANS,GRAND AV & LE SAGE,GROVER | 08/30/2019 | 112742262 | 04/06/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.18260.1106 | OCEANO 1106 | 040 | SAN LUIS OBISP | 5535457 | DO 08 - Monthly Forecast Only | 3,305.000 | 0.000 | 08J | 2019 | # | OPEN | 462 | 66 | PEND | 5 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 32162.86
35123910 | D-1105 RECOND 3,260 FT OF 6CU | 08/30/2019 | 111984232 | 09/23/2016 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/23/2017 | ED.01204.1105.SWIT | SWITCHES | 001 | ALAMEDA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2019 | # | OPEN | 462 | 66 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 22691.31
35124839 | RECON 3362 CIRCUIT FT OF 4ACSR WITH 2CU | 09/03/2019 | 117814362 | 08/27/2019 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/27/2022 | ED.18260.1102 | OCEANO 1102 | 040 | SAN LUIS OBISP | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2019 | # | OPEN | 458 | 65.4286 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35125400 | ELK HILLS 1104 OH SPLICE FUSE 19082 | 09/03/2019 | 113718468 | 10/10/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2021 | ED.25244.1104 | ELK HILLS 1104 | 015 | KERN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2019 | # | OPEN | 458 | 65.4286 | UNSC | 6 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 23094.03
35125401 | R7 BASALT 1106 WIRE DOWN AT LR 682 | 09/03/2019 | 111391279 | 02/26/2016 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/30/2017 | ED.04246.1106 | BASALT 1106 | 028 | NAPA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 3,142.000 | 0.000 | 08J | 2019 | # | OPEN | 458 | 65.4286 | PEND | 5 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 18473.41
35125402 | RECOND 3400FT OF 4ACSR WITH 2ACSR SOLEDA | 09/03/2019 | 112436787 | 12/28/2016 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 07/28/2017 | ED.18205.2102 | SOLEDAD 2102 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 3,417.000 | 0.000 | 08J | 2019 | # | OPEN | 458 | 65.4286 | UNSC | 6 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 35125402 RECOND 3400FT OF 4ACSR WITH 2AC | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 66946.59
35125403 | TERMINOUS 1102 RECONDUCTOR | 09/03/2019 | 112846354 | 05/09/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 05/28/2021 | ED.16302.1102 | TERMINOUS 1102 | 039 | SAN JOAQUIN CO | 5535457 | DO 08 - Monthly Forecast Only | 3,420.000 | 0.000 | 08J | 2019 | # | OPEN | 458 | 65.4286 | PEND | 5 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 16170.21
35125404 | 2019 08J PN DC-1112 WIREDOWN 17-0067848 | 09/03/2019 | 113198746 | 08/28/2017 | # | Not assigned | 30 | Technically Completed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2019 | ED.02264.1112.SWIT | SWITCHES | 041 | SAN MATEO COUN | 5505513 | PN-OH ANNEALED/DETER CNDCTR: PM MGD | 0.000 | 0.000 | 08J | 2019 | # | OPEN | 458 | 65.4286 | DCNL | Other | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 52547.06
35125405 | RECON 3,750' MESA 1101 THOMPSON,NIPOMO | 09/03/2019 | 113791781 | 11/07/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2021 | ED.18281.1101 | SISQUOC 1101 | 040 | SAN LUIS OBISP | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2019 | # | OPEN | 458 | 65.4286 | ESTS | 2 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 5470.78
35125406 | RECOND: E NICOLAUS 1102 SAC AVE @ HWY 99 | 09/03/2019 | 112171181 | 11/17/2016 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/29/2017 | ED.11-U220000000 | MARYSVILLE MAP U22 | 051 | SUTTER COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2019 | # | OPEN | 458 | 65.4286 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 10638.49
35125407 | R2 RECOND19 SPANS 5451FT | 09/03/2019 | 112534740 | 01/24/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2021 | ED.18257.1103 | DIVIDE 1103 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2019 | # | OPEN | 458 | 65.4286 | ESTS | 2 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 2866.34
35125408 | BOWLES 1104 RECONDUCTOR | 09/03/2019 | 112409769 | 12/15/2016 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 08/31/2021 | ED.25353.1104 | BOWLES 1104 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 5,536.000 | 0.000 | 08J | 2019 | # | OPEN | 458 | 65.4286 | ESTS | 2 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 28083.88
35125409 | 2019 WILLOW PASS 2108 HIGH SPLICE COUNT | 09/04/2019 | 113145564 | 08/11/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/10/2021 | ED.01391.2108 | WILLOW PASS 2108 | 007 | CONTRA COSTA C | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2019 | # | OPEN | 457 | 65.2857 | PEND | 5 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 39465.69
35125410 | RECON 6598', VARIOUS LOCATIONS W.MAIN SM | 09/04/2019 | 110770782 | 10/20/2015 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2021 | ED.18267.1109 | SANTA MARIA 1109 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2019 | # | OPEN | 457 | 65.2857 | ESTS | 2 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 18018.82
35125411 | HAMILTON A 1101 6,600' | 09/04/2019 | 112996389 | 06/27/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/30/2019 | ED.10212.1101.REGL | REGULATORS | 011 | GLENN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2019 | # | OPEN | 457 | 65.2857 | ESTS | 2 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 11005.43
35125412 | DEEPWATER 1107 RECONDUCTOR EXCESS SPLICE | 09/04/2019 | 112169821 | 11/17/2016 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 11/17/2018 | ED.06362.1107.RECL | RECLOSERS | 057 | YOLO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 8,438.000 | 0.000 | 08J | 2019 | # | OPEN | 457 | 65.2857 | ESTS | 2 | E470 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 9632.96
35125413 | R2RPL OH WIRE ON DOLN RD-1104 17-0061463 | 09/04/2019 | 113181522 | 08/21/2017 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 06/28/2019 | ED.18235.2103.SWIT | SWITCHES | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 10,056.000 | 0.000 | 08J | 2019 | # | OPEN | 457 | 65.2857 | PEND | 5 | E470 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 31049.93
35125414 | 2018 OH COND RPLC: EUREKA E 1104 | 09/04/2019 | 112143284 | 11/07/2016 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 10/10/2018 | ED.19233.1104.SWIT | SWITCHES | 012 | HUMBOLDT COUNT | 5535457 | DO 08 - Monthly Forecast Only | 9,200.000 | 0.000 | 08J | 2019 | # | OPEN | 457 | 65.2857 | ADER | 3 | E470 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 53845.06
35125680 | 2019 PUEBLO 1104 HIGH SPLICE COUNT 1 | 09/05/2019 | 113145266 | 08/11/2017 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2019 | ED.04329.1104 | PUEBLO 1104 | 028 | NAPA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2019 | # | OPEN | 456 | 65.1429 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 11294.25
35125681 | 2021 FAIRHAVEN 1103 DET WIRE PHASE 2 | 09/05/2019 | 114627401 | 05/22/2018 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 11/01/2021 | ED.19245.1103.SWIT | SWITCHES | 012 | HUMBOLDT COUNT | 5535457 | DO 08 - Monthly Forecast Only | 10,100.000 | 0.000 | 08J | 2019 | # | OPEN | 456 | 65.1429 | ESTS | 2 | E470 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 17240.5
35125682 | RECONDUCTOR KINGSBURG 1113 - AVE 368 | 09/05/2019 | 113242772 | 09/12/2017 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 06/30/2020 | ED.25224.1113 | KINGSBURG 1113 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 10,494.000 | 0.000 | 08J | 2019 | # | OPEN | 456 | 65.1429 | PEND | 5 | E470 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 34848.04
35125683 | R2 RECON 10649' SISQUOC 1104_ FUSE 46147 | 09/05/2019 | 112149755 | 11/09/2016 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.18281.1104 | SISQUOC 1104 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 13,506.000 | 0.000 | 08J | 2019 | # | OPEN | 456 | 65.1429 | ESTS | 2 | E470 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 9826.81
35125684 | R2RPL OH WIRE ON GONZALES1104 18-0003089 | 09/05/2019 | 114259452 | 01/30/2018 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 10/31/2020 | ED.05-K132500000.STRU.POLE | SALINAS K1325 POLES | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2019 | # | OPEN | 456 | 65.1429 | ESTS | 2 | E470 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 46009.29
35125685 | KINGSBURG 1111 RECOND 12,000' OF 6 CU | 09/05/2019 | 113728737 | 10/13/2017 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 03/31/2020 | ED.25224.1111 | KINGSBURG 1111 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 11,926.000 | 0.000 | 08J | 2019 | # | OPEN | 456 | 65.1429 | PEND | 5 | E470 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 64150.52
35125686 | R2 RPL OH WIRE ON DOLANRD-1101 S012CC106 | 09/05/2019 | 113249203 | 09/14/2017 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 06/28/2019 | ED.05-D082000000.STRU.POLE | SALINAS D0820 POLES | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2019 | # | OPEN | 456 | 65.1429 | ESTS | 2 | E470 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 15073.79
35125687 | 2020 FAIRHAVEN 1103 DET WIRE PHASE 1 | 09/05/2019 | 114627400 | 05/22/2018 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 11/02/2020 | ED.19245.1103.SWIT | SWITCHES | 012 | HUMBOLDT COUNT | 5535457 | DO 08 - Monthly Forecast Only | 12,800.000 | 0.000 | 08J | 2019 | # | OPEN | 456 | 65.1429 | ESTS | 2 | E470 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 12685.43
35125688 | COTATI 1103 RECONDUCTOR ON MIDDLE RD | 09/05/2019 | 114496935 | 04/11/2018 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 06/01/2021 | ED.04227.1103.SWIT | SWITCHES | 021 | MARIN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 14,256.000 | 0.000 | 08J | 2019 | # | OPEN | 456 | 65.1429 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 18629.43
35125689 | SEMITROPIC 1110 RECOND 14,921' WITH 2AR | 09/05/2019 | 113818681 | 11/15/2017 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 04/01/2021 | ED.25290.1110 | SEMITROPIC 1110 | 015 | KERN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2019 | # | OPEN | 456 | 65.1429 | ESTS | 2 | E470 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 12974.92
35125690 | BAYWOOD 1101 CUESTA COLLEGE 08J | 09/05/2019 | 113820469 | 11/16/2017 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.18280.1101 | BAYWOOD 1101 | 040 | SAN LUIS OBISP | 5517127 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2019 | # | OPEN | 456 | 65.1429 | ESTS | 2 | E470 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 16149CIRCUIT FT(52 SPANS) 4ACSR&6CU W2CU | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 16269.67
35125691 | ELK HILLS 1104 OH SPLICE SSD1523 | 09/05/2019 | 113718541 | 10/10/2017 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.25244.1104 | ELK HILLS 1104 | 020 | MADERA COUNTY | 5517127 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2019 | # | OPEN | 456 | 65.1429 | ESTS | 2 | E470 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | ELK HILLS 1104 OH SPLICE SSD1523 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 24430.37
35125692 | R2 OLD RIVER 1102 ANNEALD CONDUCTO | 09/05/2019 | 113634733 | 09/28/2017 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 08/31/2021 | ED.25282.1102.RECL | RECLOSERS | 015 | KERN COUNTY | 5517127 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2019 | # | OPEN | 456 | 65.1429 | PEND | 5 | E470 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | R2OLD RIVR 1102 REPLACE ANNEALD CONDUCTO | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 19402.6
35125693 | RECOND WATSONVILLE 2101 REF# S074CC218 | 09/05/2019 | 113665277 | 10/04/2017 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/29/2019 | ED.08333.2101 | WATSONVILLE 2101 | 027 | MONTEREY COUNT | 5517127 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2019 | # | OPEN | 456 | 65.1429 | ESTS | 2 | E470 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | RECOND WATSONVILLE 2101 REF# S074CC218 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 8986.32
35127310 | VASONA-1101 RECON 350 FT 4AR W 4/0AL | 09/16/2019 | 117886071 | 09/16/2019 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 02/19/2021 | ED.08377.1101.SECT | SECTIONALIZERS | 043 | SANTA CLARA CO | 5517127 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2019 | # | OPEN | 445 | 63.5714 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 824.72
35127412 | R2 EL CAPITAN 1104 RECON - WD | 09/17/2019 | 113740620 | 10/17/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2021 | ED.72-0713151000.STRU.POLE | MERCED MAP 0713151 POLES | 024 | MERCED COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2019 | # | OPEN | 444 | 63.4286 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 2195.12
35127413 | RECONDUCTOR_15 SPANS_3254FT IN FCO 45625 | 09/17/2019 | 112435460 | 12/27/2016 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/27/2017 | ED.18281.1102 | SISQUOC 1102 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2019 | # | OPEN | 444 | 63.4286 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 4515.82
35127414 | R2RPLC OH WIRE ON GABILN 1101 17-0026725 | 09/17/2019 | 112839904 | 05/05/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/30/2019 | ED.18233.1101 | GABILAN 1101 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2019 | # | OPEN | 444 | 63.4286 | PEND | 5 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 24781.91
35127415 | SM 1109, N/O 1586 W MAIN, SM | 09/17/2019 | 111957931 | 09/14/2016 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2021 | ED.18267.1109 | SANTA MARIA 1109 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2019 | # | OPEN | 444 | 63.4286 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 8460.49
35127416 | RE-COND 6260 CIRCUIT FT 4ACSRS W 2C | 09/17/2019 | 114155922 | 01/05/2018 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 01/05/2019 | ED.18206.1104 | FAIRWAY 1104 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2019 | # | OPEN | 444 | 63.4286 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 990.97
35127417 | CAB 1104 DOUGLASS AVE, LOMPOC | 09/17/2019 | 112180702 | 11/22/2016 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/22/2018 | ED.18310.1104 | CABRILLO 1104 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2019 | # | OPEN | 444 | 63.4286 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 2531.9
35127418 | 2019 PUEBLO 1104 HIGH SPLICE COUNT | 09/17/2019 | 113163076 | 08/16/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2019 | ED.04329.1104 | PUEBLO 1104 | 028 | NAPA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2019 | # | OPEN | 444 | 63.4286 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 2547.3
35127419 | RECONDUCTOR - FUSE ZONE - SM1106 CKT | 09/17/2019 | 113740518 | 10/17/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2018 | ED.18267.1106 | SANTA MARIA 1106 | 015 | KERN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2019 | # | OPEN | 444 | 63.4286 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 1773.27
35127620 | RECOND_5656FT 3-6CU 1231FT3-4ACSR W3 2CU | 09/17/2019 | 112769006 | 04/14/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 02/14/2019 | ED.18282.1102 | MESA 1102 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2019 | # | OPEN | 444 | 63.4286 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 871
35127710 | SAN BENITO 2104 LS CO409 REC 2600FT OH | 09/18/2019 | 117887579 | 09/16/2019 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/29/2021 | JY | JUNK YARD FL TO HOLD DELETED DATA | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2019 | # | OPEN | 443 | 63.2857 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 1274.41
35128940 | R2 CANAL 1103 RECONDUCTORING | 09/19/2019 | 112551915 | 02/01/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2021 | ED.25209.1103 | CANAL 1103 | 024 | MERCED COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2019 | # | OPEN | 442 | 63.1429 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 3889.24
35128952 | 2019 NORTH TOWER 2201 HIGH SPLICE COUNT | 09/19/2019 | 113145836 | 08/11/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2019 | ED.04204.2201 | NORTH TOWER 2201 | 048 | SOLANO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2019 | # | OPEN | 442 | 63.1429 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 5695.8
35128962 | RECOND HWY 20 - FTBRAGG 1102 | 09/19/2019 | 112779271 | 04/19/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 07/05/2022 | ED.04276.1102.CAPA | CAPACITORS | 023 | MENDOCINO COUN | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2019 | # | OPEN | 442 | 63.1429 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 2100.31
35128973 | STOREY 1109 - RECONDUCTOR | 09/19/2019 | 113779806 | 11/01/2017 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 01/12/2022 | ED.72-11182D0000.STRU.POLE | YOSEMITE MAP 11182D POLES | 020 | MADERA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2019 | # | OPEN | 442 | 63.1429 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 2572.02
35128985 | R2 NEWMAN 1106 REPLACE OH CONDUCTOR | 09/19/2019 | 113821907 | 11/16/2017 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.16274.1106 | NEWMAN 1106 | 050 | STANISLAUS COU | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2019 | # | OPEN | 442 | 63.1429 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 4211.34
35129012 | R2 BANTA 1101 RECONDUCTORING - WIREDOWN | 09/19/2019 | 114271062 | 02/02/2018 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 07/21/2021 | ED.16247.1101 | BANTA 1101 | 039 | SAN JOAQUIN CO | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2019 | # | OPEN | 442 | 63.1429 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 1459.86
35129023 | R2 RPL OH WIRE ON DOLANRD-1104 S020CC113 | 09/19/2019 | 113249064 | 09/14/2017 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 06/28/2019 | ED.05-E072400000.STRU.POLE | SALINAS E0724 POLES | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2019 | # | OPEN | 442 | 63.1429 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 410.88
35129024 | EIGHT MILE 2101 - RECONDUCTOR | 09/19/2019 | 113779436 | 11/01/2017 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 03/29/2019 | ED.93-Q091200000.STRU.POLE | STOCKTON Q0912 POLES | 039 | SAN JOAQUIN CO | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2019 | # | OPEN | 442 | 63.1429 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 7375.02
35129025 | R2 2019 MARICOPA 1102 RECONDUCTORING | 09/19/2019 | 113263505 | 09/20/2017 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 06/30/2021 | ED.66-1123300000.STRU.POLE | KERN 11233 POLES | 015 | KERN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2019 | # | OPEN | 442 | 63.1429 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 2970.43
35129026 | RECONDUCTOR KINGSBURG 1112 | 09/19/2019 | 113246468 | 09/13/2017 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 09/30/2022 | ED.25224.1112 | KINGSBURG 1112 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2019 | # | OPEN | 442 | 63.1429 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 15116.4
35129027 | R2 RPL OH WIRE ON DOLAN RD1101 S040CC207 | 09/19/2019 | 113725829 | 10/12/2017 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 06/28/2019 | ED.05-E071000000.STRU.POLE | SALINAS E0710 POLES | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2019 | # | OPEN | 442 | 63.1429 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 22908.34
35129028 | RECONDUCTOR AR W/AL - MESA 1101 | 09/19/2019 | 114036571 | 11/29/2017 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/15/2021 | ED.18282.1101 | MESA 1101 | 040 | SAN LUIS OBISP | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2019 | # | OPEN | 442 | 63.1429 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 5376.84
35129030 | REEDLEY 1110 RECONDUCTOR 12,271FT OF 6CU | 09/19/2019 | 114231286 | 01/18/2018 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 03/31/2021 | ED.25234.1110 | REEDLEY 1110 | 054 | TULARE COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2019 | # | OPEN | 442 | 63.1429 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 4499.69
35129031 | BIOLA 1104 RECONDUCTOR 13,014 FT OF 6CU | 09/19/2019 | 113219231 | 09/05/2017 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 06/30/2021 | ED.25221.1104 | BIOLA 1104 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2019 | # | OPEN | 442 | 63.1429 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 5571.82
35129032 | STONE CORRAL 1110 RECOND 19,622'/W 4/OAL | 09/19/2019 | 113817426 | 11/15/2017 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 06/28/2019 | ED.25292.1110 | STONE CORRAL 1110 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2019 | # | OPEN | 442 | 63.1429 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | STONE CORRAL 1110 RECOND 19,622'/W 4/OAL | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 408.59
35129304 | CWSP - ORO FINO 1102 - LR2560 PH 1.2 | 09/21/2019 | 117872785 | 09/11/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1102 | ORO FINO 1102 | 004 | BUTTE COUNTY | 5786759 | CWSP - ORO FINO 1102 - LR2560 PH 1.2 | 9,289.000 | 0.000 | 08W | 2019 | # | OPEN | 440 | 62.8571 | ADER | 3 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-ORO FINO 1102 LR-2560 PH 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 66823.86
35129305 | CWSP - ORO FINO 1102 - LR2560 PH 1.3 | 09/21/2019 | 117872786 | 09/11/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1102 | ORO FINO 1102 | 004 | BUTTE COUNTY | 5786760 | CWSP - ORO FINO 1102 - LR2560 PH 1.3 | 2,947.000 | 0.000 | 08W | 2019 | # | OPEN | 440 | 62.8571 | UNSC | 6 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-ORO FINO 1102 LR-2560 PH 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 162317.62
35129306 | CWSP - ORO FINO 1102 - LR2560 PH 1.4 | 09/21/2019 | 117872787 | 09/11/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1102 | ORO FINO 1102 | 004 | BUTTE COUNTY | 5786761 | CWSP - ORO FINO 1102 - LR2560 PH 1.4 | 7,124.000 | 0.000 | 08W | 2019 | # | OPEN | 440 | 62.8571 | PEND | 5 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-ORO FINO 1102 LR-2560 PH 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 47015.13
35129307 | CWSP - ORO FINO 1102 - LR2560 PH 1.5 | 09/21/2019 | 117872788 | 09/11/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1102 | ORO FINO 1102 | 004 | BUTTE COUNTY | 5786762 | CWSP - ORO FINO 1102 - LR2560 PH 1.5 | 8,419.000 | 0.000 | 08W | 2019 | # | OPEN | 440 | 62.8571 | UNSC | 6 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-ORO FINO 1102 LR-2560 PH 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 310835.74
35129308 | CWSP - ORO FINO 1102 - LR2560 PH 2.2 | 09/21/2019 | 117873010 | 09/11/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1102 | ORO FINO 1102 | 004 | BUTTE COUNTY | 5786763 | CWSP - ORO FINO 1102 - LR2560 PH 2.2 | 7,553.000 | 0.000 | 08W | 2019 | # | OPEN | 440 | 62.8571 | ESTS | 2 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-ORO FINO 1102 LR-2560 PH 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 37009.42
35129309 | CWSP - ORO FINO 1102 - LR2560 PH 2.3 | 09/21/2019 | 117873011 | 09/11/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1102 | ORO FINO 1102 | 004 | BUTTE COUNTY | 5786764 | CWSP - ORO FINO 1102 - LR2560 PH 2.3 | 8,020.000 | 0.000 | 08W | 2019 | # | OPEN | 440 | 62.8571 | UNSC | 6 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-ORO FINO 1102 LR-2560 PH 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 29762.36
35129310 | CWSP - ORO FINO 1102 - LR2560 PH 2.4 | 09/21/2019 | 117873012 | 09/11/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1102 | ORO FINO 1102 | 004 | BUTTE COUNTY | 5786765 | CWSP - ORO FINO 1102 - LR2560 PH 2.4 | 10,110.000 | 0.000 | 08W | 2019 | # | OPEN | 440 | 62.8571 | PEND | 5 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-ORO FINO 1102 LR-2560 PH 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 32261.12
35129311 | CWSP - ORO FINO 1102 - LR2560 PH 2.5 | 09/21/2019 | 117873013 | 09/11/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1102 | ORO FINO 1102 | 004 | BUTTE COUNTY | 5786766 | CWSP - ORO FINO 1102 - LR2560 PH 2.5 | 13,202.000 | 0.000 | 08W | 2019 | # | OPEN | 440 | 62.8571 | PEND | 5 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-ORO FINO 1102 LR-2560 PH 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 39401.04
35129434 | CWSP - ORO FINO 1102 - LR76008 PH 1.2 | 09/23/2019 | 117873015 | 09/11/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1102 | ORO FINO 1102 | 004 | BUTTE COUNTY | 5786767 | CWSP - ORO FINO 1102 - LR76008 PH 1.2 | 10,059.000 | 0.000 | 08W | 2019 | # | OPEN | 438 | 62.5714 | PEND | 5 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-ORO FINO 1102 LR-76008 PH 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 162370.49
35129435 | CWSP - ORO FINO 1102 - LR76008 PH 1.3 | 09/23/2019 | 117873016 | 09/11/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1102 | ORO FINO 1102 | 004 | BUTTE COUNTY | 5786768 | CWSP - ORO FINO 1102 - LR76008 PH 1.3 | 10,727.000 | 0.000 | 08W | 2019 | # | OPEN | 438 | 62.5714 | UNSC | 6 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-ORO FINO 1102 LR-76008 PH 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 110030.22
35129436 | CWSP - ORO FINO 1102 - LR76008 PH 1.4 | 09/23/2019 | 117873017 | 09/11/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1102 | ORO FINO 1102 | 004 | BUTTE COUNTY | 5786769 | CWSP - ORO FINO 1102 - LR76008 PH 1.4 | 9,426.000 | 0.000 | 08W | 2019 | # | OPEN | 438 | 62.5714 | PEND | 5 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-ORO FINO 1102 LR-76008 PH 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 108594.67
35129437 | CWSP - ORO FINO 1102 - LR76008 PH 1.5 | 09/23/2019 | 117873018 | 09/11/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1102 | ORO FINO 1102 | 004 | BUTTE COUNTY | 5786770 | CWSP - ORO FINO 1102 - LR76008 PH 1.5 | 11,288.000 | 0.000 | 08W | 2019 | # | OPEN | 438 | 62.5714 | PEND | 5 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-ORO FINO 1102 LR-76008 PH 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 115864.56
35129438 | CWSP - ORO FINO 1102 - LR76008 PH 2.2 | 09/23/2019 | 117873019 | 09/11/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1102 | ORO FINO 1102 | 004 | BUTTE COUNTY | 5786771 | CWSP - ORO FINO 1102 - LR76008 PH 2.2 | 8,582.000 | 0.000 | 08W | 2019 | # | OPEN | 438 | 62.5714 | PEND | 5 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-ORO FINO 1102 LR-76008 PH 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 124891.45
35129439 | CWSP - ORO FINO 1102 - LR76008 PH 2.3 | 09/23/2019 | 117873030 | 09/11/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1102 | ORO FINO 1102 | 004 | BUTTE COUNTY | 5786772 | CWSP - ORO FINO 1102 - LR76008 PH 2.3 | 9,426.000 | 0.000 | 08W | 2019 | # | OPEN | 438 | 62.5714 | PEND | 5 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-ORO FINO 1102 LR-76008 PH 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 123515.24
35129474 | SF A-1115 WIRE DOWN 08J PROJECT | 09/23/2019 | 112859784 | 05/11/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 08/25/2017 | ED.02203.1115.SWIT | SWITCHES | 038 | SAN FRANCISCO | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2019 | # | OPEN | 438 | 62.5714 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35129475 | S SPINGS 1103 - STROLLING HILLS RECOND | 09/23/2019 | 112171180 | 11/17/2016 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/29/2017 | ED.21-J371800000 | EL DORADO MAP J3718 | 009 | EL DORADO COUN | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2019 | # | OPEN | 438 | 62.5714 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 2543.45
35129476 | 2019 YOSEMITE 401 HIGH SPLICE COUNT | 09/23/2019 | 113163134 | 08/16/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2019 | ED.02249.0401 | YOSEMITE 0401 | 038 | SAN FRANCISCO | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2019 | # | OPEN | 438 | 62.5714 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 594.54
35129477 | R2 RECONDUCT DOLAN RD 1101 17-0016449 | 09/23/2019 | 112624835 | 02/24/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/30/2018 | ED.18238.1101 | DOLAN ROAD 1101 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2019 | # | OPEN | 438 | 62.5714 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 756.45
35129478 | SNEATH LANE 1102 WIREDOWN 16-0033827 | 09/23/2019 | 111662862 | 05/25/2016 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/31/2017 | ED.02272.1102.TXFR.TROH | OVERHEAD TRANSFORMERS | 041 | SAN MATEO COUN | 5505513 | PN-OH ANNEALED/DETER CNDCTR: PM MGD | 0.000 | 0.000 | 08J | 2019 | # | OPEN | 438 | 62.5714 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 11891.52
35129479 | SUISUN 1109 RECOND LINE EXCESS SPLICES | 09/23/2019 | 112134521 | 11/02/2016 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/01/2017 | ED.06213.1107.SWIT | SWITCHES | 048 | SOLANO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2019 | # | OPEN | 438 | 62.5714 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35129600 | CWSP - ORO FINO 1102 - LR76008 PH 2.4 | 09/23/2019 | 117873031 | 09/11/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1102 | ORO FINO 1102 | 004 | BUTTE COUNTY | 5786773 | CWSP - ORO FINO 1102 - LR76008 PH 2.4 | 5,799.000 | 0.000 | 08W | 2019 | # | OPEN | 438 | 62.5714 | PEND | 5 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-ORO FINO 1102 LR-76008 PH 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 100120.16
35129601 | CWSP - ORO FINO 1102 - LR76008 PH 2.5 | 09/23/2019 | 117873032 | 09/11/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1102 | ORO FINO 1102 | 004 | BUTTE COUNTY | 5786774 | CWSP - ORO FINO 1102 - LR76008 PH 2.5 | 7,829.000 | 0.000 | 08W | 2019 | # | OPEN | 438 | 62.5714 | PEND | 5 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-ORO FINO 1102 LR-76008 PH 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 150007.19
35129602 | CWSP - ORO FINO 1101 - OCB PH 1.2 | 09/23/2019 | 117873033 | 09/11/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1101 | ORO FINO 1101 | 004 | BUTTE COUNTY | 5786745 | CWSP - ORO FINO 1101 - OCB PH 1.2 | 6,446.000 | 0.000 | 08W | 2019 | # | OPEN | 438 | 62.5714 | PEND | 5 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-ORO FINO 1101 OCB PH 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 13286.03
35129603 | CWSP - ORO FINO 1101 - OCB PH 1.3 | 09/23/2019 | 117873034 | 09/11/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1101 | ORO FINO 1101 | 004 | BUTTE COUNTY | 5786746 | CWSP - ORO FINO 1101 - OCB PH 1.3 | 7,042.000 | 0.000 | 08W | 2019 | # | OPEN | 438 | 62.5714 | PEND | 5 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-ORO FINO 1101 OCB PH 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 16240.46
35129604 | CWSP - ORO FINO 1101 - OCB PH 1.4 | 09/23/2019 | 117873035 | 09/11/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1101 | ORO FINO 1101 | 004 | BUTTE COUNTY | 5786747 | CWSP - ORO FINO 1101 - OCB PH 1.4 | 6,845.000 | 0.000 | 08W | 2019 | # | OPEN | 438 | 62.5714 | PEND | 5 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-ORO FINO 1101 OCB PH 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 10765.21
35129605 | CWSP - ORO FINO 1101 - OCB PH 1.5 | 09/23/2019 | 117873036 | 09/11/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1101 | ORO FINO 1101 | 004 | BUTTE COUNTY | 5786748 | CWSP - ORO FINO 1101 - OCB PH 1.5 | 7,525.000 | 0.000 | 08W | 2019 | # | OPEN | 438 | 62.5714 | PEND | 5 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-ORO FINO 1101 OCB PH 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 19734.06
35129606 | CWSP - ORO FINO 1101 - OCB PH 1.6 | 09/23/2019 | 117873037 | 09/11/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1101 | ORO FINO 1101 | 004 | BUTTE COUNTY | 5786749 | CWSP - ORO FINO 1101 - OCB PH 1.6 | 5,401.000 | 0.000 | 08W | 2019 | # | OPEN | 438 | 62.5714 | PEND | 5 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-ORO FINO 1101 OCB PH 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 12782.79
35129607 | CWSP - ORO FINO 1101 - OCB PH 1.7 | 09/23/2019 | 117873038 | 09/11/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1101 | ORO FINO 1101 | 004 | BUTTE COUNTY | 5786750 | CWSP - ORO FINO 1101 - OCB PH 1.7 | 8,189.000 | 0.000 | 08W | 2019 | # | OPEN | 438 | 62.5714 | PEND | 5 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-ORO FINO 1101 OCB PH 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 13648.47
35129608 | CWSP - ORO FINO 1101 - OCB PH 2.2 | 09/23/2019 | 117873039 | 09/11/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1101 | ORO FINO 1101 | 004 | BUTTE COUNTY | 5786751 | CWSP - ORO FINO 1101 - OCB PH 2.2 | 7,762.000 | 0.000 | 08W | 2019 | # | OPEN | 438 | 62.5714 | UNSC | 6 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-ORO FINO 1101 OCB PH 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 26312.78
35129609 | CWSP - ORO FINO 1101 - OCB PH 2.3 | 09/23/2019 | 117873070 | 09/11/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1101 | ORO FINO 1101 | 004 | BUTTE COUNTY | 5786752 | CWSP - ORO FINO 1101 - OCB PH 2.3 | 5,631.000 | 0.000 | 08W | 2019 | # | OPEN | 438 | 62.5714 | PEND | 5 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-ORO FINO 1101 OCB PH 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 52836.71
35129610 | CWSP - ORO FINO 1101 - OCB PH 2.4 | 09/23/2019 | 117873071 | 09/11/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1101 | ORO FINO 1101 | 004 | BUTTE COUNTY | 5786753 | CWSP - ORO FINO 1101 - OCB PH 2.4 | 8,176.000 | 0.000 | 08W | 2019 | # | OPEN | 438 | 62.5714 | PEND | 5 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-ORO FINO 1101 OCB PH 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 41569.65
35129611 | CWSP - ORO FINO 1101 - OCB PH 2.5 | 09/23/2019 | 117873072 | 09/11/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1101 | ORO FINO 1101 | 004 | BUTTE COUNTY | 5786754 | CWSP - ORO FINO 1101 - OCB PH 2.5 | 7,159.000 | 0.000 | 08W | 2019 | # | OPEN | 438 | 62.5714 | PEND | 5 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-ORO FINO 1101 OCB PH 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 22811.85
35129612 | CWSP - ORO FINO 1101 - OCB PH 2.6 | 09/23/2019 | 117873073 | 09/11/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1101 | ORO FINO 1101 | 004 | BUTTE COUNTY | 5786755 | CWSP - ORO FINO 1101 - OCB PH 2.6 | 5,967.000 | 0.000 | 08W | 2019 | # | OPEN | 438 | 62.5714 | PEND | 5 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-ORO FINO 1101 OCB PH 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 17161.69
35129613 | CWSP - ORO FINO 1101 - OCB PH 3.2 | 09/23/2019 | 117873074 | 09/11/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1101 | ORO FINO 1101 | 004 | BUTTE COUNTY | 5786756 | CWSP - ORO FINO 1101 - OCB PH 3.2 | 6,292.000 | 0.000 | 08W | 2019 | # | OPEN | 438 | 62.5714 | PEND | 5 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-ORO FINO 1101 OCB PH 3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 39828.48
35129614 | CWSP - ORO FINO 1101 - OCB PH 3.3 | 09/23/2019 | 117873075 | 09/11/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1101 | ORO FINO 1101 | 004 | BUTTE COUNTY | 5786757 | CWSP - ORO FINO 1101 - OCB PH 3.3 | 9,276.000 | 0.000 | 08W | 2019 | # | OPEN | 438 | 62.5714 | PEND | 5 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-ORO FINO 1101 OCB PH 3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 39995.09
35129615 | CWSP - ORO FINO 1101 - OCB PH 3.4 | 09/23/2019 | 117873076 | 09/11/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1101 | ORO FINO 1101 | 004 | BUTTE COUNTY | 5786758 | CWSP - ORO FINO 1101 - OCB PH 3.4 | 10,907.000 | 0.000 | 08W | 2019 | # | OPEN | 438 | 62.5714 | PEND | 5 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-ORO FINO 1101 OCB PH 3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 1531.57
35129616 | CWSP - ORO FINO 1101 - LR2022 PH 1.2 | 09/23/2019 | 117873077 | 09/11/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1101 | ORO FINO 1101 | 004 | BUTTE COUNTY | 5786672 | CWSP - ORO FINO 1101 - LR2022 PH 1.2 | 8,807.000 | 0.000 | 08W | 2019 | # | OPEN | 438 | 62.5714 | PEND | 5 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - ORO FINO-1101 LR-2022 PH I | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 43696.7
35129617 | CWSP - ORO FINO 1101 - LR2022 PH 1.3 | 09/23/2019 | 117873078 | 09/11/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1101 | ORO FINO 1101 | 004 | BUTTE COUNTY | 5786673 | CWSP - ORO FINO 1101 - LR2022 PH 1.3 | 10,060.000 | 0.000 | 08W | 2019 | # | OPEN | 438 | 62.5714 | PEND | 5 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - ORO FINO-1101 LR-2022 PH I | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 25490.54
35129618 | CWSP - ORO FINO 1101 - LR2022 PH 1.4 | 09/23/2019 | 117873079 | 09/11/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1101 | ORO FINO 1101 | 004 | BUTTE COUNTY | 5786674 | CWSP - ORO FINO 1101 - LR2022 PH 1.4 | 10,566.000 | 0.000 | 08W | 2019 | # | OPEN | 438 | 62.5714 | PEND | 5 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - ORO FINO-1101 LR-2022 PH I | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 23405.95
35129619 | CWSP - ORO FINO 1101 - LR2022 PH 1.5 | 09/23/2019 | 117873090 | 09/11/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1101 | ORO FINO 1101 | 004 | BUTTE COUNTY | 5786675 | CWSP - ORO FINO 1101 - LR2022 PH 1.5 | 8,666.000 | 0.000 | 08W | 2019 | # | OPEN | 438 | 62.5714 | PEND | 5 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - ORO FINO-1101 LR-2022 PH I | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 80974.99
35129620 | LINDEN 1102 RECONDUCTOR D4387 | 09/23/2019 | 112682565 | 03/15/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/30/2018 | ED.16207.1102 | LINDEN 1102 | 039 | SAN JOAQUIN CO | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2019 | # | OPEN | 438 | 62.5714 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 5235.99
35129621 | R2RPL OH WIRE ON DOLAN RD 1101 S052CC211 | 09/23/2019 | 113725868 | 10/12/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/28/2019 | ED.05-D082300000.STRU.POLE | SALINAS D0823 POLES | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2019 | # | OPEN | 438 | 62.5714 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 2668.72
35129623 | RECONDUCTOR 7 SPANS - DUMBARTON 1106 | 09/23/2019 | 113038755 | 07/11/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/01/2019 | ED.01447.1106 | DUMBARTON 1106 | 001 | ALAMEDA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2019 | # | OPEN | 438 | 62.5714 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 97.79
35129624 | MARYSVILLE 1107 - GRANT WAY RECONDUCTOR | 09/23/2019 | 111053589 | 12/08/2015 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/30/2016 | ED.15201.1107.TXFR.TROH | OVERHEAD TRANSFORMERS | 051 | SUTTER COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2019 | # | OPEN | 438 | 62.5714 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 919.01
35129625 | R7 NAPA 1109 WIRE DOWN AT SW 1955 | 09/23/2019 | 110485716 | 07/02/2015 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 07/01/2016 | ED.04202.1109 | NAPA 1109 | 028 | NAPA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2019 | # | OPEN | 438 | 62.5714 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 4568.01
35129626 | RECOMMENDATION 18-0015602_SISQUOC-1104 | 09/23/2019 | 114354598 | 03/02/2018 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 08/02/2020 | ED.18281.1104 | SISQUOC 1104 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2019 | # | OPEN | 438 | 62.5714 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 911.86
35129627 | RECOND 7-SPANS ELYSIAN RD- CORONA 1103 | 09/23/2019 | 112760950 | 04/12/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/28/2018 | ED.04349.1103.RECL | RECLOSERS | 049 | SONOMA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2019 | # | OPEN | 438 | 62.5714 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 1063.92
35129628 | R5 MORRO BAY 1102 WD 15-006745 | 09/23/2019 | 111102535 | 12/16/2015 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2021 | ED.18301.1102 | MORRO BAY 1102 | 040 | SAN LUIS OBISP | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2019 | # | OPEN | 438 | 62.5714 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 391.62
35129629 | 2019 08J PN SL-1107 S025CC116 | 09/23/2019 | 113227557 | 09/08/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/27/2019 | ED.02272.1107.TXFR.TROH | OVERHEAD TRANSFORMERS | 041 | SAN MATEO COUN | 5517127 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2019 | # | OPEN | 438 | 62.5714 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 589.28
35129630 | EL NIDO 1101 - TARGETED OH SPLICE 91193 | 09/23/2019 | 113718462 | 10/10/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/30/2019 | ED.25245.1101 | EL NIDO 1101 | 020 | MADERA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2019 | # | OPEN | 438 | 62.5714 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 2053.15
35129631 | VALLEJO B0414 HIGH SPLICE COUNT | 09/23/2019 | 113747830 | 10/19/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/19/2019 | ED.42-QQ39080000.STRU.POLE | SILVERADO QQ3908 POLES | 048 | SOLANO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2019 | # | OPEN | 438 | 62.5714 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 2938.39
35129632 | DIXON 1103 RECOND LINE EXCESS SPLICES | 09/23/2019 | 112134523 | 11/02/2016 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/01/2017 | ED.06206.1103.SWIT | SWITCHES | 048 | SOLANO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2019 | # | OPEN | 438 | 62.5714 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 3025.59
35129633 | R2 EL CAPITAN 1104 RECONDUCTORING | 09/23/2019 | 113240816 | 09/12/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2021 | ED.72-07131C0000.STRU.POLE | MERCED MAP 07131C POLES | 024 | MERCED COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2019 | # | OPEN | 438 | 62.5714 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 1368.76
35129634 | SANTA MARIA 1110 RECOND 2300FT 4AR W 2CU | 09/23/2019 | 114538011 | 04/26/2018 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/26/2020 | ED.18282.1102 | MESA 1102 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2019 | # | OPEN | 438 | 62.5714 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 1126.66
35129635 | R7 RECONDTAP SPERRY & GUERNEVILLE RD | 09/23/2019 | 112407504 | 12/14/2016 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/28/2018 | ED.04257.1103.SWIT | SWITCHES | 049 | SONOMA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2019 | # | OPEN | 438 | 62.5714 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35129636 | WESTPARK 1104 RECOND 2,430' WITH 397AL | 09/23/2019 | 113817897 | 11/15/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/28/2019 | ED.25370.1104 | WESTPARK 1104 | 015 | KERN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2019 | # | OPEN | 438 | 62.5714 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35129637 | DAVIS 1106 RECOND LINE EX SPLICES | 09/23/2019 | 111855703 | 08/08/2016 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 08/04/2017 | ED.06204.1106.SWIT | SWITCHES | 057 | YOLO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2019 | # | OPEN | 438 | 62.5714 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 70.05
35129638 | 2018 WAHTOKE 1110 RECONDUCTOR | 09/23/2019 | 112410217 | 12/15/2016 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/30/2021 | ED.25453.1110 | WAHTOKE 1110 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2019 | # | OPEN | 438 | 62.5714 | ESTS | 2 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 5260.03
35129639 | RECOND GREEN VALLEY 2101 REF# S036CC205 | 09/23/2019 | 113664064 | 10/04/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/29/2019 | ED.08319.2101 | GREEN VALLEY 2101 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2019 | # | OPEN | 438 | 62.5714 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 1763.78
35129640 | CWSP - ORO FINO 1101 - LR2022 PH 1.6 | 09/23/2019 | 117873091 | 09/11/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1101 | ORO FINO 1101 | 004 | BUTTE COUNTY | 5786676 | CWSP - ORO FINO 1101 - LR2022 PH 1.6 | 7,873.000 | 0.000 | 08W | 2019 | # | OPEN | 438 | 62.5714 | PEND | 5 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - ORO FINO-1101 LR-2022 PH I | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 11894.52
35129641 | CWSP - ORO FINO 1101 - LR2022 PH 1.7 | 09/23/2019 | 117873092 | 09/11/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1101 | ORO FINO 1101 | 004 | BUTTE COUNTY | 5786677 | CWSP - ORO FINO 1101 - LR2022 PH 1.7 | 7,379.000 | 0.000 | 08W | 2019 | # | OPEN | 438 | 62.5714 | PEND | 5 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - ORO FINO-1101 LR-2022 PH I | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 37116.57
35129642 | CWSP - ORO FINO 1101 - LR2022 PH 1.8 | 09/23/2019 | 117873093 | 09/11/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1101 | ORO FINO 1101 | 004 | BUTTE COUNTY | 5786738 | CWSP - ORO FINO 1101 - LR2022 PH 1.8 | 6,394.000 | 0.000 | 08W | 2019 | # | OPEN | 438 | 62.5714 | PEND | 5 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - ORO FINO-1101 LR-2022 PH I | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 9581.72
35129643 | CWSP - ORO FINO 1101 - LR2022 PH 2.2 | 09/23/2019 | 117873094 | 09/11/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1101 | ORO FINO 1101 | 004 | BUTTE COUNTY | 5786739 | CWSP - ORO FINO 1101 - LR2022 PH 2.2 | 11,072.000 | 0.000 | 08W | 2019 | # | OPEN | 438 | 62.5714 | PEND | 5 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - ORO FINO-1101 LR-2022 PH 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 61935.38
35129644 | CWSP - ORO FINO 1101 - LR2022 PH 2.3 | 09/23/2019 | 117873095 | 09/11/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1101 | ORO FINO 1101 | 004 | BUTTE COUNTY | 5786740 | CWSP - ORO FINO 1101 - LR2022 PH 2.3 | 4,502.000 | 0.000 | 08W | 2019 | # | OPEN | 438 | 62.5714 | PEND | 5 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - ORO FINO-1101 LR-2022 PH 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 32395.16
35129645 | CWSP - ORO FINO 1101 - LR2022 PH 2.4 | 09/23/2019 | 117873096 | 09/11/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1101 | ORO FINO 1101 | 004 | BUTTE COUNTY | 5786741 | CWSP - ORO FINO 1101 - LR2022 PH 2.4 | 5,416.000 | 0.000 | 08W | 2019 | # | OPEN | 438 | 62.5714 | PEND | 5 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - ORO FINO-1101 LR-2022 PH 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 22730.22
35129646 | CWSP - ORO FINO 1101 - LR2022 PH 2.5 | 09/23/2019 | 117873097 | 09/11/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1101 | ORO FINO 1101 | 004 | BUTTE COUNTY | 5786742 | CWSP - ORO FINO 1101 - LR2022 PH 2.5 | 5,560.000 | 0.000 | 08W | 2019 | # | OPEN | 438 | 62.5714 | CONS | 7 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - ORO FINO-1101 LR-2022 PH 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 37801.45
35129647 | CWSP - ORO FINO 1101 - LR2022 PH 2.6 | 09/23/2019 | 117873098 | 09/11/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1101 | ORO FINO 1101 | 004 | BUTTE COUNTY | 5786743 | CWSP - ORO FINO 1101 - LR2022 PH 2.6 | 4,973.000 | 0.000 | 08W | 2019 | # | OPEN | 438 | 62.5714 | ESTS | 2 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - ORO FINO-1101 LR-2022 PH 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 8531.62
35129648 | CWSP - ORO FINO 1101 - LR2022 PH 3.2 | 09/23/2019 | 117873099 | 09/11/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1101 | ORO FINO 1101 | 004 | BUTTE COUNTY | 5786744 | CWSP - ORO FINO 1101 - LR2022 PH 3.2 | 6,141.000 | 0.000 | 08W | 2019 | # | OPEN | 438 | 62.5714 | ESTS | 2 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-ORO FINO 1101 LR-2022 PH 3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 12423.39
35129649 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.2 | 09/23/2019 | 117873100 | 09/11/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1102 | ORO FINO 1102 | 004 | BUTTE COUNTY | 5786775 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.2 | 8,635.000 | 0.000 | 08W | 2019 | # | OPEN | 438 | 62.5714 | ADER | 3 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-ORO FINO 1102 OCB & LR2090 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 15071.14
35129650 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.3 | 09/23/2019 | 117873101 | 09/11/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1102 | ORO FINO 1102 | 004 | BUTTE COUNTY | 5786776 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.3 | 7,706.000 | 0.000 | 08W | 2019 | # | OPEN | 438 | 62.5714 | PEND | 5 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-ORO FINO 1102 OCB & LR2090 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 92481.56
35129652 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.4 | 09/23/2019 | 117873102 | 09/11/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1102 | ORO FINO 1102 | 004 | BUTTE COUNTY | 5786777 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.4 | 5,375.000 | 0.000 | 08W | 2019 | # | OPEN | 438 | 62.5714 | PEND | 5 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-ORO FINO 1102 OCB & LR2090 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 76088.09
35129653 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.5 | 09/23/2019 | 117873103 | 09/11/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1102 | ORO FINO 1102 | 004 | BUTTE COUNTY | 5786778 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.5 | 7,280.000 | 0.000 | 08W | 2019 | # | OPEN | 438 | 62.5714 | PEND | 5 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-ORO FINO 1102 OCB & LR2090 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 488.01
35129654 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.6 | 09/23/2019 | 117873104 | 09/11/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1102 | ORO FINO 1102 | 004 | BUTTE COUNTY | 5786779 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.6 | 9,896.000 | 0.000 | 08W | 2019 | # | OPEN | 438 | 62.5714 | PEND | 5 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-ORO FINO 1102 OCB & LR2090 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 114225.81
35129655 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.7 | 09/23/2019 | 117873105 | 09/11/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1102 | ORO FINO 1102 | 004 | BUTTE COUNTY | 5786780 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.7 | 9,076.000 | 0.000 | 08W | 2019 | # | OPEN | 438 | 62.5714 | PEND | 5 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-ORO FINO 1102 OCB & LR2090 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 13079.83
35129656 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.8 | 09/23/2019 | 117873106 | 09/11/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1102 | ORO FINO 1102 | 004 | BUTTE COUNTY | 5786781 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.8 | 0.000 | 0.000 | 08W | 2019 | # | OPEN | 438 | 62.5714 | ADER | 3 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-ORO FINO 1102 OCB & LR2090 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 309.55
35129657 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.9 | 09/23/2019 | 117873107 | 09/11/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1102 | ORO FINO 1102 | 004 | BUTTE COUNTY | 5786782 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.9 | 0.000 | 0.000 | 08W | 2019 | # | OPEN | 438 | 62.5714 | ESTS | 2 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-ORO FINO 1102 OCB & LR2090 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 8894.08
35129700 | SIQUOC 1104 WIREDOWN RECONDUCTORING | 09/23/2019 | 110573078 | 08/12/2015 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2021 | ED.18281.1104 | SISQUOC 1104 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2019 | # | OPEN | 438 | 62.5714 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 16020.01
35129701 | R4E RECONDUCTOR LIBERTY ISLND-DIXON 1103 | 09/23/2019 | 110891639 | 12/03/2015 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2016 | ED.48-R190000000.STRU.POLE | SOLANO R19 POLES | 048 | SOLANO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2019 | # | OPEN | 438 | 62.5714 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 26978.86
35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | 09/24/2019 | 114810960 | 07/23/2018 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.15248.1103.RECL | RECLOSERS | 029 | NEVADA COUNTY | 5535211 | CWSP SPO - SH 08 | 13,700.000 | 0.000 | 08W | 2019 | # | OPEN | 437 | 62.4286 | ESTS | 2 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BRUNSWICK 1103 LR2200 HARDENING | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 116413.43
35129900 | WEBER 1102 RECONDUCTORING - 08J | 09/24/2019 | 110822896 | 10/30/2015 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/20/2021 | ED.16348.1102 | WEBER 1102 | 039 | SAN JOAQUIN CO | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2019 | # | OPEN | 437 | 62.4286 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 17274.72
35129901 | 2019 08J PN MILLBRAE 1102 S073CC217 | 09/24/2019 | 113747875 | 10/19/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/27/2019 | ED.02269.1102.SWIT | SWITCHES | 041 | SAN MATEO COUN | 5505513 | PN-OH ANNEALED/DETER CNDCTR: PM MGD | 0.000 | 0.000 | 08J | 2019 | # | OPEN | 437 | 62.4286 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 792.74
35129902 | RECO31SPAN4425FT4ACSR W2CUSANTAMA1105 | 09/24/2019 | 112648194 | 03/03/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/03/2019 | ED.18267.1105 | SANTA MARIA 1105 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2019 | # | OPEN | 437 | 62.4286 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 3468.26
35129944 | SILVERADO 2105 - DIST.UNDERBUILD RECON | 09/25/2019 | 117893376 | 09/18/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.04343.2105 | SILVERADO 2105 | 028 | NAPA COUNTY | 5786045 | CWSP - FULTON 1107 - MARK WEST SPR RD | 3,709.000 | 0.000 | 08W | 2019 | # | OPEN | 436 | 62.2857 | UNSC | 6 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Fulton-Calistoga 60 kV Line Reconductor | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 51895.01
35131354 | LW2111 RECONDUCTOR 1 SPAN & INSTALL FUSE | 10/04/2019 | 117957888 | 10/03/2019 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2022 | ED.01353.2111 | LAKEWOOD 2111 | 007 | CONTRA COSTA C | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2019 | # | OPEN | 427 | 61 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 612.35
35132048 | PARLIER 1102 RECOND 3773' OF 6CU W 715AL | 10/08/2019 | 117959993 | 10/04/2019 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/30/2022 | ED.25229.1102 | PARLIER 1102 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2019 | # | OPEN | 423 | 60.4286 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 244.59
35132541 | MADERA 1119 RECOND 5,770' OF 6CU W 4/OAL | 10/09/2019 | 117973778 | 10/09/2019 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 07/08/2022 | ED.25276.1119 | MADERA 1119 | 020 | MADERA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2019 | # | OPEN | 422 | 60.2857 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 5587.01
35134806 | BR-03-14-W (E) PENTZ RD, PARB | 10/21/2019 | 118057348 | 10/21/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 08/31/2020 | ED.17-S342200000.STRU.POLE | PARADISE S3422 POLES | 004 | BUTTE COUNTY | 5786123 | 08W Rebuild | 0.000 | 0.000 | 08W | 2019 | # | OPEN | 410 | 58.5714 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35134931 | RECONDUCTOR RIVERBANK 1715-SPLICE COUNT | 10/22/2019 | 113143653 | 08/10/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/02/2021 | ED.16319.1715 | RIVERBANK 1715 | 050 | STANISLAUS COU | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2019 | # | OPEN | 409 | 58.4286 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 1428.16
35134932 | ROUGH AND READY 1102 RECONDUCTOR | 10/22/2019 | 113261334 | 09/19/2017 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 02/07/2022 | ED.16308.1102 | ROUGH AND READY IS 1102 | 039 | SAN JOAQUIN CO | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2019 | # | OPEN | 409 | 58.4286 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 1211.62
35134934 | RECONDUCTOR WRIGHT 1110 - WIRE DOWN | 10/22/2019 | 113143575 | 08/10/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/12/2021 | ED.25464.1110 | WRIGHT 1110 | 024 | MERCED COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2019 | # | OPEN | 409 | 58.4286 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 4677.15
35134937 | BONITA 1101 CO 32802 RECOND | 10/22/2019 | 113219238 | 09/05/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2021 | ED.25539.1101 | BONITA 1101 | 020 | MADERA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2019 | # | OPEN | 409 | 58.4286 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 3276.65
35134938 | MADERA 1119 3,770FT TARGET OH REPL | 10/22/2019 | 113241724 | 09/12/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/30/2022 | ED.25276.1119 | MADERA 1119 | 020 | MADERA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2019 | # | OPEN | 409 | 58.4286 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 10423.98
35134979 | WD-CHANNEL 1102-CO 17151 -ILIS 190101945 | 10/22/2019 | 118085161 | 10/22/2019 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2022 | ED.93-U091900000.STRU.POLE | STOCKTON U0919 POLES | 039 | SAN JOAQUIN CO | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2019 | # | OPEN | 409 | 58.4286 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 1346.13
35135000 | RECONDUCTOR CASSIDY 2108 | 10/22/2019 | 113243462 | 09/12/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2021 | ED.25427.2108 | CASSIDY 2108 | 020 | MADERA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2019 | # | OPEN | 409 | 58.4286 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 5709.51
35135001 | RECONDUCTOR BONITA 1101 - AVE 17 | 10/22/2019 | 113248456 | 09/14/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/27/2021 | ED.25539.1101 | BONITA 1101 | 020 | MADERA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2019 | # | OPEN | 409 | 58.4286 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 5713.58
35135003 | EL NIDO 1101 RECOND 3700FT WITH #2AR | 10/22/2019 | 113260310 | 09/19/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.25245.1101 | EL NIDO 1101 | 024 | MERCED COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 3,730.000 | 0.000 | 08J | 2019 | # | OPEN | 409 | 58.4286 | UNSC | 6 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 19271.58
35135004 | MERCED 1116 RECONDUCTORING | 10/22/2019 | 113261666 | 09/19/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.72-0814400000.STRU.POLE | MERCED MAP 08144 POLES | 024 | MERCED COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2019 | # | OPEN | 409 | 58.4286 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 3891.84
35135005 | MVWF ALTO 1125 MUIR WOOD DR,MUIR BEACH | 10/22/2019 | 111104641 | 12/16/2015 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2017 | ED.04203.1125 | ALTO 1125 | 021 | MARIN COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2019 | # | OPEN | 409 | 58.4286 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 8238.33
35135006 | RECONDUCTOR CANAL 1104 WD | 10/22/2019 | 112727825 | 03/31/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/07/2021 | ED.25209.1104 | CANAL 1104 | 024 | MERCED COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2019 | # | OPEN | 409 | 58.4286 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 8754.31
35135479 | LAWNDALE 0402 19-0098539 RECON OH COND | 10/24/2019 | 118011917 | 10/16/2019 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 07/30/2022 | ED.56-E040600000.STRU.POLE | SKYLINE E0406 POLES | 041 | SAN MATEO COUN | 5505513 | PN-OH ANNEALED/DETER CNDCTR: PM MGD | 0.000 | 0.000 | 08J | 2019 | # | OPEN | 407 | 58.1429 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 1470.19
35135864 | CWSP – GRAYS FLAT 401 FUSE 3079 ZONE | 10/29/2019 | 117923638 | 09/26/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | JY | JUNK YARD FL TO HOLD DELETED DATA | 032 | PLUMAS COUNTY | 5535211 | CWSP SPO - SH 08 | 9,316.000 | 0.000 | 08W | 2019 | # | OPEN | 402 | 57.4286 | CONS | 7 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 84118.5
35135891 | RECOND SALINAS 1106 ALONG IVERSON ST | 10/29/2019 | 118119201 | 10/29/2019 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/30/2022 | ED.18201.1106.SWIT | SWITCHES | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2019 | # | OPEN | 402 | 57.4286 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 2761.18
35137590 | CWSP-ECOP-MIDDLETOWN 1101-OCB-H02 | 11/06/2019 | 118093216 | 10/23/2019 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.04314.1101.SWIT | SWITCHES | 017 | LAKE COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2019 | # | OPEN | 394 | 56.2857 | ESTS | 2 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 6111.44
35137593 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H07 | 11/06/2019 | 118125945 | 10/31/2019 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.46-Z270000000.STRU.POLE | UKIAH Z27 POLES | 017 | LAKE COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2019 | # | OPEN | 394 | 56.2857 | ESTS | 2 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 5376.42
35137596 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H08 | 11/06/2019 | 118127757 | 10/31/2019 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.46-Z260000000.STRU.POLE | UKIAH Z26 POLES | 017 | LAKE COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2019 | # | OPEN | 394 | 56.2857 | ESTS | 2 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 3348.21
35137599 | CWSP-ECOP-MIDDLETOWN 1101-LR 614-H11 | 11/06/2019 | 118142262 | 11/05/2019 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.04314.1101.RECL | RECLOSERS | 017 | LAKE COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2019 | # | OPEN | 394 | 56.2857 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 3766.11
35138215 | DIVIDE 1102 RECOND 3710 FT OF 4AR W 2 CU | 11/12/2019 | 118164913 | 11/12/2019 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/30/2022 | ED.18257.1102 | DIVIDE 1102 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2019 | # | OPEN | 388 | 55.4286 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 2136.91
35141419 | BR-03-07-W (E) TIMBER WALK PARB | 11/20/2019 | 118188125 | 11/20/2019 | 35105717 | BR-03-07-F (E) TIMBER WALK PARB | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 03/20/2020 | JY | JUNK YARD FL TO HOLD DELETED DATA | 004 | BUTTE COUNTY | 5786123 | 08W Rebuild | 0.000 | 0.000 | 08W | 2019 | # | OPEN | 380 | 54.2857 | CONS | 7 | E470 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 265571.17
35141586 | WD: MABURY 1101 - OCB - 19-0121127 | 11/20/2019 | 118187066 | 11/19/2019 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/30/2022 | ED.08219.1101.SWIT | SWITCHES | 043 | SANTA CLARA CO | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2019 | # | OPEN | 380 | 54.2857 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 1878.37
35141837 | BR-04-01-W (E) SUNSET DR PARB | 11/22/2019 | 118195513 | 11/22/2019 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/27/2019 | JY | JUNK YARD FL TO HOLD DELETED DATA | 004 | BUTTE COUNTY | 5786123 | 08W Rebuild | 0.000 | 0.000 | 08W | 2019 | # | OPEN | 378 | 54 | PEND | 5 | E460 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 184085.04
35141980 | HMB1103 CO6071 RECOND 1100FT OH LINE | 11/22/2019 | 118186909 | 11/19/2019 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 08/10/2022 | ED.58-E041600000.STRU.POLE | PENINSULA E0416 POLES | 041 | SAN MATEO COUN | 5505513 | PN-OH ANNEALED/DETER CNDCTR: PM MGD | 0.000 | 0.000 | 08J | 2019 | # | OPEN | 378 | 54 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35142198 | BR-03-08-W (E) BELLEVIEW PARB | 11/26/2019 | 118204107 | 11/26/2019 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/31/2020 | ED.17-S341700000.STRU.POLE | PARADISE S3417 POLES | 004 | BUTTE COUNTY | 5786123 | 08W Rebuild | 0.000 | 0.000 | 08W | 2019 | # | OPEN | 374 | 53.4286 | UNSC | 6 | E460 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 355398.47
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | 12/03/2019 | 118218639 | 12/02/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.15248.1103 | BRUNSWICK 1103 | 029 | NEVADA COUNTY | 5535211 | CWSP SPO - SH 08 | 8,412.000 | 0.000 | 08W | 2019 | # | OPEN | 367 | 52.4286 | CONS | 7 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BRUNSWICK 1103 LR2200 HARDENING | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 866165.94
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | 12/03/2019 | 118218951 | 12/02/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.15248.1103 | BRUNSWICK 1103 | 029 | NEVADA COUNTY | 5535211 | CWSP SPO - SH 08 | 4,547.000 | 0.000 | 08W | 2019 | # | OPEN | 367 | 52.4286 | PEND | 5 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BRUNSWICK 1103 LR2200 HARDENING | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 407447.4
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | 12/03/2019 | 118218953 | 12/02/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.15248.1103 | BRUNSWICK 1103 | 029 | NEVADA COUNTY | 5535211 | CWSP SPO - SH 08 | 2,505.000 | 0.000 | 08W | 2019 | # | OPEN | 367 | 52.4286 | CONS | 7 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BRUNSWICK 1103 LR2200 HARDENING | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 291415.35
35144588 | PSPS MITIGATION - ROSSMOOR 1106 | 12/09/2019 | 118247763 | 12/09/2019 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.01416.1108.SWIT | SWITCHES | 007 | CONTRA COSTA C | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2019 | # | OPEN | 361 | 51.5714 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35144589 | PSPS MITIGATION - MORAGA 1103 | 12/09/2019 | 118247764 | 12/09/2019 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.01380.1103.SWIT | SWITCHES | 007 | CONTRA COSTA C | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2019 | # | OPEN | 361 | 51.5714 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35144591 | PSPS MITIGATION - STAFFORD 1101 - PH1 | 12/09/2019 | 118247769 | 12/09/2019 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.04320.1102.SWIT | SWITCHES | 021 | MARIN COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2019 | # | OPEN | 361 | 51.5714 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35144592 | PSPS MITIGATION - STAFFORD 1101 - PH2 | 12/09/2019 | 118247871 | 12/09/2019 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.04320.1101.SWIT | SWITCHES | 021 | MARIN COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2019 | # | OPEN | 361 | 51.5714 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35144940 | *CANC* PSPS - HICKS 2101 – CB | 12/11/2019 | 118261651 | 12/11/2019 | # | Not assigned | 40 | Closed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/30/2020 | ED.78-I172500000.STRU.POLE | SAN JOSE I1725 POLES | 043 | SANTA CLARA CO | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2019 | 09/03/2020 | 2020 | 267 | 38.1429 | CLSD | 12 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | PSPS - Hicks 2101 – CB | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 2020-09-03 | 2020-09-03 | # | 2020-09-03 | 2020-09-03 | # | 2020-09-03 | 2020-09-03 | COMP | 2020-08-27 | 2020-08-27 | COMP | 2020-08-27 | 2020-08-27 | COMP | 2020-08-27 | 2020-08-27 | 0 | -7 | 1183.31
35144941 | PSPS - PAUL SWEET 2105 - CB PH 1 | 12/11/2019 | 118261469 | 12/11/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 11/01/2021 | ED.76-O141000000.STRU.POLE | COAST O1410 POLES | 044 | SANTA CRUZ COU | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2019 | # | OPEN | 359 | 51.2857 | ADER | 3 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | PSPS - Paul Sweet 2105 - CB PH 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 173826.53
35144942 | *CANC* PSPS - PAUL SWEET 2105 - CB | 12/11/2019 | 118261520 | 12/11/2019 | # | Not assigned | 40 | Closed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/30/2020 | ED.76-O141000000.STRU.POLE | COAST O1410 POLES | 044 | SANTA CRUZ COU | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2019 | 09/03/2020 | 2020 | 267 | 38.1429 | CLSD | 12 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | PSPS - Paul Sweet 2105 - CB PH 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 2020-09-03 | 2020-09-03 | # | 2020-09-03 | 2020-09-03 | # | 2020-09-03 | 2020-09-03 | COMP | 2020-08-20 | 2020-08-20 | COMP | 2020-08-20 | 2020-08-20 | COMP | 2020-08-20 | 2020-08-20 | 0 | -14 | 163.61
35144943 | PSPS - ROB ROY 2105 - CB | 12/11/2019 | 118261587 | 12/11/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 09/17/2021 | ED.76-O172000000.STRU.POLE | COAST O1720 POLES | 044 | SANTA CRUZ COU | 5535211 | CWSP SPO - SH 08 | 689.000 | 0.000 | 08W | 2019 | # | OPEN | 359 | 51.2857 | PEND | 5 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | PSPS - Rob Roy 2105 - CB | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 95162.93
35144944 | PSPS – SNEATH LANE 1107 – LR 48338 | 12/11/2019 | 118261958 | 12/11/2019 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/01/2021 | ED.56-E031100000.STRU.POLE | SKYLINE E0311 POLES | 041 | SAN MATEO COUN | 5535211 | CWSP SPO - SH 08 | 1,385.000 | 0.000 | 08W | 2019 | # | OPEN | 359 | 51.2857 | PEND | 5 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 104771.47
35145001 | PSPS - CLAYTON 2215 - CB | 12/12/2019 | 118259181 | 12/10/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.01202.2215 | CLAYTON 2215 | 007 | CONTRA COSTA C | 5535211 | CWSP SPO - SH 08 | 9,720.000 | 0.000 | 08W | 2019 | # | OPEN | 358 | 51.1429 | PEND | 5 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | PSPS - Clayton 2215 – CB | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 134930.93
35145002 | PSPS - IGNACIO 1101 - CB | 12/12/2019 | 118262844 | 12/11/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.04248.1101 | IGNACIO 1101 | 021 | MARIN COUNTY | 5535211 | CWSP SPO - SH 08 | 6,847.000 | 0.000 | 08W | 2019 | # | OPEN | 358 | 51.1429 | PEND | 5 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | PSPS - Ignacio 1101 - CB | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 116319.39
35145003 | PSPS CWSP - MORAGA 1103 - CB | 12/12/2019 | 118263229 | 12/11/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 04/30/2021 | ED.01380.1103 | MORAGA 1103 | 007 | CONTRA COSTA C | 5535211 | CWSP SPO - SH 08 | 1,688.000 | 0.000 | 08W | 2019 | # | OPEN | 358 | 51.1429 | PEND | 5 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | PSPS - Moraga 1103 - CB | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 88691.36
35145004 | PSPS CWSP - ROSSMOOR 1106 - CB | 12/12/2019 | 118263746 | 12/11/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 06/10/2021 | ED.01416.1106 | ROSSMOOR 1106 | 007 | CONTRA COSTA C | 5535211 | CWSP SPO - SH 08 | 5,038.000 | 0.000 | 08W | 2019 | # | OPEN | 358 | 51.1429 | PEND | 5 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | PSPS - Rossmoor 1106 – CB | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 80766.32
35145005 | *CANCELLED*CWSP - STAFFORD 1101 - CB PH1 | 12/12/2019 | 118263871 | 12/11/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.04320.1101 | STAFFORD 1101 | 021 | MARIN COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2019 | # | OPEN | 358 | 51.1429 | DOCC | 8 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | PSPS - Stafford 1101 CB PH 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 20666.53
35145006 | PSPS - STAFFORD 1101 LR 1298 | 12/12/2019 | 118263874 | 12/11/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.04320.1101 | STAFFORD 1101 | 021 | MARIN COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2019 | # | OPEN | 358 | 51.1429 | ESTS | 2 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | PSPS - Stafford 1101 - LR 1298 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 100106.91
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | 12/13/2019 | 118265394 | 12/12/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.15361.2109.SWIT | SWITCHES | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 21,381.000 | 0.000 | 08W | 2019 | # | OPEN | 357 | 51 | PEND | 5 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | PSPS - Clarksville 2104 - CB | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 139264.04
35145523 | *CANC* PSPS - FULTON 1102 HARDENING | 12/13/2019 | 118265412 | 12/12/2019 | # | Not assigned | 40 | Closed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/01/2020 | ED.04256.1102 | FULTON 1102 | 049 | SONOMA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2019 | 09/03/2020 | 2020 | 265 | 37.8571 | CLSD | 12 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | PSPS - Fulton 1102 - CB | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 2020-09-03 | 2020-09-03 | # | 2020-09-03 | 2020-09-03 | # | 2020-09-03 | 2020-09-03 | COMP | 2020-08-28 | 2020-08-28 | COMP | 2020-08-28 | 2020-08-28 | COMP | 2020-08-28 | 2020-08-28 | 0 | -6 | -72.65
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING | 12/13/2019 | 118266591 | 12/12/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/01/2020 | ED.04332.1101 | RINCON 1101 | 049 | SONOMA COUNTY | 5535211 | CWSP SPO - SH 08 | 3,000.000 | 0.000 | 08W | 2019 | # | OPEN | 357 | 51 | PEND | 5 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | PSPS - Rincon 1101 and 1103- CB | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 95281.85
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING | 12/13/2019 | 118266592 | 12/12/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/01/2020 | ED.04332.1102 | RINCON 1102 | 049 | SONOMA COUNTY | 5535211 | CWSP SPO - SH 08 | 7,760.000 | 0.000 | 08W | 2019 | # | OPEN | 357 | 51 | PEND | 5 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | PSPS - Rincon 1102 and 1104 - CB | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 72175.98
35145540 | PSPS - FROGTOWN 1702 - CB | 12/13/2019 | 118259180 | 12/10/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 09/30/2020 | ED.16345.1702 | FROGTOWN 1702 | 005 | CALAVERAS COUN | 5535211 | CWSP SPO - SH 08 | 6,718.000 | 0.000 | 08W | 2019 | # | OPEN | 357 | 51 | PEND | 5 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | PSPS - Frogtown 1702 - CB | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 144656.28
35146240 | RECONDUCTOR OH LINE - EDES 1105 CIRCUIT | 12/19/2019 | 118286149 | 12/18/2019 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/15/2021 | ED.01368.1105 | EDES 1105 | 001 | ALAMEDA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 300.000 | 0.000 | 08J | 2019 | # | OPEN | 351 | 50.1429 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 1609.34
35146639 | PS2107 RECONDUCTOR C/O 28335 | 12/27/2019 | 118363082 | 12/24/2019 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2022 | ED.08325.2107 | PAUL SWEET 2107 | 044 | SANTA CRUZ COU | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2019 | # | OPEN | 343 | 49 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 2876.27
35147003 | *CNCL* GABILAN 1101 RECON FUSE 3279 ZONE | 12/30/2019 | 13660469 | 12/30/2019 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/31/2022 | ED.18233.1101 | GABILAN 1101 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2019 | # | OPEN | 340 | 48.5714 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 2895.89
35147045 | *CANC* *DO NOT USE* PSPS - CASTRO V*CANC | 12/30/2019 | 118370183 | 12/30/2019 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.01409.1108 | CASTRO VALLEY 1108 | 001 | ALAMEDA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2019 | 10/03/2020 | 2020 | 278 | 39.7143 | CLSD | 12 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 2020-10-03 | 2020-10-03 | # | 2020-10-03 | 2020-10-03 | # | 2020-10-03 | 2020-10-03 | COMP | 2020-08-26 | 2020-08-26 | COMP | 2020-08-26 | 2020-08-26 | COMP | 2020-08-26 | 2020-08-26 | 0 | -38 | 0
35148272 | CREATED IN ERROR | 01/09/2020 | 118407947 | 01/09/2020 | # | Not assigned | 40 | Closed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/27/2019 | ED | Electric Distribution System | 005 | CALAVERAS COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2020 | 01/09/2020 | 2020 | 0 | 0 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35148810 | GRAND ISLAND 2224 RECONDUCTOR 4C | 01/14/2020 | 112609391 | 02/17/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/01/2018 | ED.06246.2224.RECL | RECLOSERS | 048 | SOLANO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2020 | # | OPEN | 325 | 46.4286 | ESTS | 2 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 38580.07
35152332 | RECOND CASTROVILLE 2104 ZONE 23829 | 01/28/2020 | 118472573 | 01/27/2020 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/31/2022 | ED.05-F091600000.STRU.POLE | SALINAS F0916 POLES | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2020 | # | OPEN | 311 | 44.4286 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 2445.85
35153986 | RECON 3441 FT OF 4ACSR W 2CU/ISTALL FCO | 02/06/2020 | 118497363 | 02/05/2020 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/30/2022 | ED.18263.1103 | SAN LUIS OBISPO 1103 | 040 | SAN LUIS OBISP | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2020 | # | OPEN | 302 | 43.1429 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35154003 | HENRIETTA 1110 RECOND 6,900' WITH 397AL | 02/06/2020 | 118499689 | 02/05/2020 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/30/2022 | ED.25268.1110 | HENRIETTA 1110 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2020 | # | OPEN | 302 | 43.1429 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35155680 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.02 | 02/07/2020 | 118499588 | 02/05/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/30/2021 | ED.15248.1105 | BRUNSWICK 1105 | 029 | NEVADA COUNTY | 5789366 | CWSP - BRUNSWICK 1105 - LR 2140 - PH 1.0 | 6,990.000 | 0.000 | 08W | 2020 | # | OPEN | 301 | 43 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BRUNSWICK 1105 LR2140 HARDENING - | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 1091.62
35155681 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.03 | 02/07/2020 | 118501195 | 02/06/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15248.1105 | BRUNSWICK 1105 | 029 | NEVADA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 1,335.000 | 0.000 | 08W | 2020 | # | OPEN | 301 | 43 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BRUNSWICK 1105 LR2140 HARDENING - | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 679.18
35155682 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.04 | 02/07/2020 | 118501438 | 02/06/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15248.1105 | BRUNSWICK 1105 | 029 | NEVADA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 1,930.000 | 0.000 | 08W | 2020 | # | OPEN | 301 | 43 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BRUNSWICK 1105 LR2140 HARDENING - | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 428.05
35155683 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.05 | 02/07/2020 | 118501439 | 02/06/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15248.1105 | BRUNSWICK 1105 | 029 | NEVADA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 6,550.000 | 0.000 | 08W | 2020 | # | OPEN | 301 | 43 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BRUNSWICK 1105 LR2140 HARDENING - | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 2006.3
35155684 | CWSP-BRUNSWICK 1105 LR2140 - PH 1.06 | 02/07/2020 | 118501730 | 02/06/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15248.1105 | BRUNSWICK 1105 | 029 | NEVADA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 3,288.000 | 0.000 | 08W | 2020 | # | OPEN | 301 | 43 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BRUNSWICK 1105 LR2140 HARDENING - | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 428.05
35155685 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.07 | 02/07/2020 | 118501731 | 02/06/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15248.1105 | BRUNSWICK 1105 | 029 | NEVADA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 3,780.000 | 0.000 | 08W | 2020 | # | OPEN | 301 | 43 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BRUNSWICK 1105 LR2140 HARDENING - | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 428.05
35155686 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.08 | 02/07/2020 | 118501733 | 02/06/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15248.1105 | BRUNSWICK 1105 | 029 | NEVADA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 3,240.000 | 0.000 | 08W | 2020 | # | OPEN | 301 | 43 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BRUNSWICK 1105 LR2140 HARDENING - | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 176.98
35155687 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.09 | 02/07/2020 | 118501735 | 02/06/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15248.1105 | BRUNSWICK 1105 | 029 | NEVADA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 8,886.000 | 0.000 | 08W | 2020 | # | OPEN | 301 | 43 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BRUNSWICK 1105 LR2140 HARDENING - | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 176.98
35155688 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.10 | 02/07/2020 | 118501736 | 02/06/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15248.1105 | BRUNSWICK 1105 | 029 | NEVADA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 2,961.000 | 0.000 | 08W | 2020 | # | OPEN | 301 | 43 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BRUNSWICK 1105 LR2140 HARDENING - | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 176.98
35155689 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.11 | 02/07/2020 | 118501737 | 02/06/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15248.1105 | BRUNSWICK 1105 | 029 | NEVADA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 4,900.000 | 0.000 | 08W | 2020 | # | OPEN | 301 | 43 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BRUNSWICK 1105 LR2140 HARDENING - | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 176.98
35155690 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.12 | 02/07/2020 | 118501738 | 02/06/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15248.1105 | BRUNSWICK 1105 | 029 | NEVADA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 5,082.000 | 0.000 | 08W | 2020 | # | OPEN | 301 | 43 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BRUNSWICK 1105 LR2140 HARDENING - | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 176.98
35155691 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.13 | 02/07/2020 | 118501739 | 02/06/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15248.1105 | BRUNSWICK 1105 | 029 | NEVADA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 3,010.000 | 0.000 | 08W | 2020 | # | OPEN | 301 | 43 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BRUNSWICK 1105 LR2140 HARDENING - | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 176.98
35155692 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.14 | 02/07/2020 | 118501873 | 02/06/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15248.1105 | BRUNSWICK 1105 | 029 | NEVADA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 5,268.000 | 0.000 | 08W | 2020 | # | OPEN | 301 | 43 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BRUNSWICK 1105 LR2140 HARDENING - | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 176.98
35155693 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.15 | 02/07/2020 | 118501874 | 02/06/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15248.1105 | BRUNSWICK 1105 | 029 | NEVADA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 6,100.000 | 0.000 | 08W | 2020 | # | OPEN | 301 | 43 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BRUNSWICK 1105 LR2140 HARDENING - | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 315.49
35155694 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.16 | 02/07/2020 | 118501875 | 02/06/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15248.1105 | BRUNSWICK 1105 | 029 | NEVADA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 5,900.000 | 0.000 | 08W | 2020 | # | OPEN | 301 | 43 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BRUNSWICK 1105 LR2140 HARDENING - | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 176.98
35155695 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.02 | 02/07/2020 | 118502200 | 02/06/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15248.1105 | BRUNSWICK 1105 | 029 | NEVADA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 5,465.000 | 0.000 | 08W | 2020 | # | OPEN | 301 | 43 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BRUNSWICK 1105 LR2140 HARDENING - | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 394.52
35155696 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.03 | 02/07/2020 | 118502205 | 02/06/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15248.1105 | BRUNSWICK 1105 | 029 | NEVADA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 2,440.000 | 0.000 | 08W | 2020 | # | OPEN | 301 | 43 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BRUNSWICK 1105 LR2140 HARDENING - | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 593.51
35155697 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.04 | 02/07/2020 | 118502207 | 02/06/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15248.1105 | BRUNSWICK 1105 | 029 | NEVADA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 2,080.000 | 0.000 | 08W | 2020 | # | OPEN | 301 | 43 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BRUNSWICK 1105 LR2140 HARDENING - | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 179.05
35155698 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.05 | 02/07/2020 | 118502208 | 02/06/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15248.1105 | BRUNSWICK 1105 | 029 | NEVADA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 6,332.000 | 0.000 | 08W | 2020 | # | OPEN | 301 | 43 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BRUNSWICK 1105 LR2140 HARDENING - | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 179.05
35155699 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.06 | 02/07/2020 | 118502271 | 02/06/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15248.1105 | BRUNSWICK 1105 | 029 | NEVADA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 2,415.000 | 0.000 | 08W | 2020 | # | OPEN | 301 | 43 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BRUNSWICK 1105 LR2140 HARDENING - | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 179.05
35155740 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.07 | 02/07/2020 | 118502272 | 02/06/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15248.1105 | BRUNSWICK 1105 | 029 | NEVADA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 3,636.000 | 0.000 | 08W | 2020 | # | OPEN | 301 | 43 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BRUNSWICK 1105 LR2140 HARDENING - | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35155741 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.08 | 02/07/2020 | 118502273 | 02/06/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15248.1105 | BRUNSWICK 1105 | 029 | NEVADA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 890.000 | 0.000 | 08W | 2020 | # | OPEN | 301 | 43 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BRUNSWICK 1105 LR2140 HARDENING - | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 179.05
35155742 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.09 | 02/07/2020 | 118502274 | 02/06/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15248.1105 | BRUNSWICK 1105 | 029 | NEVADA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 6,100.000 | 0.000 | 08W | 2020 | # | OPEN | 301 | 43 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BRUNSWICK 1105 LR2140 HARDENING - | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 593.51
35155743 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.10 | 02/07/2020 | 118502275 | 02/06/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15248.1105 | BRUNSWICK 1105 | 029 | NEVADA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 3,692.000 | 0.000 | 08W | 2020 | # | OPEN | 301 | 43 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BRUNSWICK 1105 LR2140 HARDENING - | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35155744 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.11 | 02/07/2020 | 118502276 | 02/06/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15248.1105 | BRUNSWICK 1105 | 029 | NEVADA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 2,671.000 | 0.000 | 08W | 2020 | # | OPEN | 301 | 43 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BRUNSWICK 1105 LR2140 HARDENING - | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35155746 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.12 | 02/07/2020 | 118502277 | 02/06/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15248.1105 | BRUNSWICK 1105 | 029 | NEVADA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 5,910.000 | 0.000 | 08W | 2020 | # | OPEN | 301 | 43 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BRUNSWICK 1105 LR2140 HARDENING - | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 358.05
35155747 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.13 | 02/07/2020 | 118502279 | 02/06/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15248.1105 | BRUNSWICK 1105 | 029 | NEVADA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 4,025.000 | 0.000 | 08W | 2020 | # | OPEN | 301 | 43 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BRUNSWICK 1105 LR2140 HARDENING - | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35155748 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.14 | 02/07/2020 | 118502451 | 02/06/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15248.1105 | BRUNSWICK 1105 | 029 | NEVADA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 2,740.000 | 0.000 | 08W | 2020 | # | OPEN | 301 | 43 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BRUNSWICK 1105 LR2140 HARDENING - | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35155749 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.15 | 02/07/2020 | 118502453 | 02/06/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15248.1105 | BRUNSWICK 1105 | 029 | NEVADA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 2,662.000 | 0.000 | 08W | 2020 | # | OPEN | 301 | 43 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BRUNSWICK 1105 LR2140 HARDENING - | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35155750 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.16 | 02/07/2020 | 118502455 | 02/06/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15248.1105 | BRUNSWICK 1105 | 029 | NEVADA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 8,872.000 | 0.000 | 08W | 2020 | # | OPEN | 301 | 43 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BRUNSWICK 1105 LR2140 HARDENING - | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 358.05
35155751 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.17 | 02/07/2020 | 118502456 | 02/06/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15248.1105 | BRUNSWICK 1105 | 029 | NEVADA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 2,627.000 | 0.000 | 08W | 2020 | # | OPEN | 301 | 43 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BRUNSWICK 1105 LR2140 HARDENING - | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 593.51
35155752 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.02 | 02/07/2020 | 118502580 | 02/06/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15248.1105 | BRUNSWICK 1105 | 029 | NEVADA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 2,727.000 | 0.000 | 08W | 2020 | # | OPEN | 301 | 43 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BRUNSWICK 1105 LR2140 HARDENING - | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 217.53
35155753 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.03 | 02/07/2020 | 118502582 | 02/06/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15248.1105 | BRUNSWICK 1105 | 029 | NEVADA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 5,611.000 | 0.000 | 08W | 2020 | # | OPEN | 301 | 43 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BRUNSWICK 1105 LR2140 HARDENING - | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 710.01
35155754 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.04 | 02/07/2020 | 118502583 | 02/06/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15248.1105 | BRUNSWICK 1105 | 029 | NEVADA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 6,626.000 | 0.000 | 08W | 2020 | # | OPEN | 301 | 43 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BRUNSWICK 1105 LR2140 HARDENING - | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 533
35155755 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.05 | 02/07/2020 | 118502584 | 02/06/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15248.1105 | BRUNSWICK 1105 | 029 | NEVADA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 1,431.000 | 0.000 | 08W | 2020 | # | OPEN | 301 | 43 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BRUNSWICK 1105 LR2140 HARDENING - | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 217.53
35155756 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.06 | 02/07/2020 | 118502585 | 02/06/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15248.1105 | BRUNSWICK 1105 | 029 | NEVADA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 9,214.000 | 0.000 | 08W | 2020 | # | OPEN | 301 | 43 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BRUNSWICK 1105 LR2140 HARDENING - | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 1695.01
35155757 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.07 | 02/07/2020 | 118502586 | 02/06/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15248.1105 | BRUNSWICK 1105 | 029 | NEVADA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 2,913.000 | 0.000 | 08W | 2020 | # | OPEN | 301 | 43 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BRUNSWICK 1105 LR2140 HARDENING - | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35155758 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.08 | 02/07/2020 | 118502587 | 02/06/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15248.1105 | BRUNSWICK 1105 | 029 | NEVADA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 3,510.000 | 0.000 | 08W | 2020 | # | OPEN | 301 | 43 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BRUNSWICK 1105 LR2140 HARDENING - | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 533
35155759 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.09 | 02/07/2020 | 118502588 | 02/06/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15248.1105 | BRUNSWICK 1105 | 029 | NEVADA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 3,500.000 | 0.000 | 08W | 2020 | # | OPEN | 301 | 43 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BRUNSWICK 1105 LR2140 HARDENING - | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35155840 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.10 | 02/07/2020 | 118502589 | 02/06/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15248.1105 | BRUNSWICK 1105 | 029 | NEVADA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 2,596.000 | 0.000 | 08W | 2020 | # | OPEN | 301 | 43 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BRUNSWICK 1105 LR2140 HARDENING - | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35155841 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.11 | 02/07/2020 | 118502690 | 02/06/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15248.1105 | BRUNSWICK 1105 | 029 | NEVADA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 4,491.000 | 0.000 | 08W | 2020 | # | OPEN | 301 | 43 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BRUNSWICK 1105 LR2140 HARDENING - | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 710.01
35155842 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.12 | 02/07/2020 | 118502691 | 02/06/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15248.1105 | BRUNSWICK 1105 | 029 | NEVADA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 808.000 | 0.000 | 08W | 2020 | # | OPEN | 301 | 43 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BRUNSWICK 1105 LR2140 HARDENING - | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 412.45
35157845 | SILVERADO 2105 WIRE DOWN - PH 3 | 02/20/2020 | 118548863 | 02/19/2020 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.04343.2105 | SILVERADO 2105 | 028 | NAPA COUNTY | 5535211 | CWSP SPO - SH 08 | 6,693.000 | 0.000 | 08W | 2020 | # | OPEN | 288 | 41.1429 | CONS | 7 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 367686.5
35157914 | GABILAN 1101 RECONDUCTOR FUSE 3279 ZONE | 02/20/2020 | 118367647 | 12/27/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 03/31/2022 | ED.18233.1101 | GABILAN 1101 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2020 | # | OPEN | 288 | 41.1429 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 505.63
35157947 | RICE 1102 RECOND 20,775 FT WITH 2AR | 02/20/2020 | 118551698 | 02/20/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/01/2022 | ED.06283.1102 | RICE 1102 | 006 | COLUSA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2020 | # | OPEN | 288 | 41.1429 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Rice 1102 - Reconductor 20,775 ft w 2AR | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 1264.17
35158717 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.2 | 02/26/2020 | 118531819 | 02/13/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15248.1105 | BRUNSWICK 1105 | 029 | NEVADA COUNTY | 5535211 | CWSP SPO - SH 08 | 7,952.000 | 0.000 | 08W | 2020 | # | OPEN | 282 | 40.2857 | ADER | 3 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Brunswick - 1105 - LR2210 Zone-Ph | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 5437.5
35159768 | RECONDUCTOR RIPON 1701 - SPLICE COUNT | 03/04/2020 | 113181841 | 08/21/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/27/2019 | ED.16380.1701 | RIPON 1701 | 039 | SAN JOAQUIN CO | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2020 | # | OPEN | 275 | 39.2857 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 7234.42
35160091 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.3 | 03/06/2020 | 118532310 | 02/13/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15248.1105 | BRUNSWICK 1105 | 029 | NEVADA COUNTY | 5535211 | CWSP SPO - SH 08 | 3,447.000 | 0.000 | 08W | 2020 | # | OPEN | 273 | 39 | ADER | 3 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Brunswick - 1105 - LR2210 Zone-Ph | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 4403.9
35160093 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.4 | 03/06/2020 | 118532312 | 02/13/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15248.1105 | BRUNSWICK 1105 | 029 | NEVADA COUNTY | 5535211 | CWSP SPO - SH 08 | 6,360.000 | 0.000 | 08W | 2020 | # | OPEN | 273 | 39 | ESTS | 2 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Brunswick - 1105 - LR2210 Zone-Ph | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 4711.16
35160094 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.5 | 03/06/2020 | 118532313 | 02/13/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15248.1105 | BRUNSWICK 1105 | 029 | NEVADA COUNTY | 5535211 | CWSP SPO - SH 08 | 6,145.000 | 0.000 | 08W | 2020 | # | OPEN | 273 | 39 | ESTS | 2 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Brunswick - 1105 - LR2210 Zone-Ph | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 4708.7
35160095 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.6 | 03/06/2020 | 118532315 | 02/13/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15248.1105 | BRUNSWICK 1105 | 029 | NEVADA COUNTY | 5535211 | CWSP SPO - SH 08 | 9,380.000 | 0.000 | 08W | 2020 | # | OPEN | 273 | 39 | ESTS | 2 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Brunswick - 1105 - LR2210 Zone-Ph | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 4920.88
35160096 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.7 | 03/06/2020 | 118532317 | 02/13/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15248.1105 | BRUNSWICK 1105 | 029 | NEVADA COUNTY | 5535211 | CWSP SPO - SH 08 | 5,330.000 | 0.000 | 08W | 2020 | # | OPEN | 273 | 39 | ESTS | 2 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Brunswick - 1105 - LR2210 Zone-Ph | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 5493.5
35160097 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.8 | 03/06/2020 | 118532318 | 02/13/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15248.1105 | BRUNSWICK 1105 | 029 | NEVADA COUNTY | 5535211 | CWSP SPO - SH 08 | 10,570.000 | 0.000 | 08W | 2020 | # | OPEN | 273 | 39 | ADER | 3 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Brunswick - 1105 - LR2210 Zone-Ph | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 5608.07
35160098 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.9 | 03/06/2020 | 118532430 | 02/13/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15248.1105 | BRUNSWICK 1105 | 029 | NEVADA COUNTY | 5535211 | CWSP SPO - SH 08 | 4,895.000 | 0.000 | 08W | 2020 | # | OPEN | 273 | 39 | ESTS | 2 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Brunswick - 1105 - LR2210 Zone-Ph | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 5698.34
35160341 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.2 | 03/06/2020 | 118532433 | 02/13/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15248.1105 | BRUNSWICK 1105 | 029 | NEVADA COUNTY | 5535211 | CWSP SPO - SH 08 | 8,165.000 | 0.000 | 08W | 2020 | # | OPEN | 273 | 39 | ESTS | 2 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Brunswick - 1105 - LR2210 Zone-Ph | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 3792.66
35160342 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.3 | 03/06/2020 | 118532435 | 02/13/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15248.1105 | BRUNSWICK 1105 | 029 | NEVADA COUNTY | 5535211 | CWSP SPO - SH 08 | 7,840.000 | 0.000 | 08W | 2020 | # | OPEN | 273 | 39 | ESTS | 2 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Brunswick - 1105 - LR2210 Zone-Ph | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 5456.44
35160343 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.4 | 03/06/2020 | 118532436 | 02/13/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15248.1105 | BRUNSWICK 1105 | 029 | NEVADA COUNTY | 5535211 | CWSP SPO - SH 08 | 13,875.000 | 0.000 | 08W | 2020 | # | OPEN | 273 | 39 | ESTS | 2 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Brunswick - 1105 - LR2210 Zone-Ph | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 909.53
35160344 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.5 | 03/06/2020 | 118532438 | 02/13/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15248.1105 | BRUNSWICK 1105 | 029 | NEVADA COUNTY | 5535211 | CWSP SPO - SH 08 | 14,192.000 | 0.000 | 08W | 2020 | # | OPEN | 273 | 39 | ESTS | 2 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Brunswick - 1105 - LR2210 Zone-Ph | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 1270.47
35160345 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.6 | 03/06/2020 | 118532570 | 02/13/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15248.1105 | BRUNSWICK 1105 | 029 | NEVADA COUNTY | 5535211 | CWSP SPO - SH 08 | 17,520.000 | 0.000 | 08W | 2020 | # | OPEN | 273 | 39 | ESTS | 2 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Brunswick - 1105 - LR2210 Zone-Ph | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 3276.72
35160346 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.7 | 03/06/2020 | 118532571 | 02/13/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15248.1105 | BRUNSWICK 1105 | 029 | NEVADA COUNTY | 5535211 | CWSP SPO - SH 08 | 2,960.000 | 0.000 | 08W | 2020 | # | OPEN | 273 | 39 | ESTS | 2 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Brunswick - 1105 - LR2210 Zone-Ph | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 966.62
35160669 | GRAND ISLAND 2227 RECOND 2870 FT W 2AR | 03/09/2020 | 118640219 | 03/05/2020 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/01/2022 | ED.06246.2227 | GRAND ISLAND 2227 | 057 | YOLO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2020 | # | OPEN | 270 | 38.5714 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 3520.55
35162161 | EIGHT MILE 2102 RECONDUCTORING | 03/11/2020 | 113199108 | 08/28/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2019 | ED.93-S120000000.STRU.POLE | STOCKTON S12 POLES | 039 | SAN JOAQUIN CO | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2020 | # | OPEN | 268 | 38.2857 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 10552.76
35162588 | SLO 1104 RECON 6082 FT OF 4AR W 2CU | 03/13/2020 | 118677123 | 03/10/2020 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/10/2022 | ED.18263.1104 | SAN LUIS OBISPO 1104 | 040 | SAN LUIS OBISP | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2020 | # | OPEN | 266 | 38 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 1638.01
35167136 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.2 | 03/25/2020 | 118729469 | 03/20/2020 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2021 | ED.15308.2106 | PLACERVILLE 2106 | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 254 | 36.2857 | ESTS | 2 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Placerville 2106 - LR 1104 - Ph 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 214.56
35167137 | CANCEL DUPLICATE ORDER | 03/25/2020 | # | #N/A | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2021 | ED.15308.2106 | PLACERVILLE 2106 | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 254 | 36.2857 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0
35167138 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.3 | 03/25/2020 | 118729544 | 03/20/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15308.2106 | PLACERVILLE 2106 | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 254 | 36.2857 | ESTS | 2 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Placerville 2106 - LR 1104 - Ph 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 607.15
35167433 | EVERGREEN 2103- OH RECOND AT LR 980314 | 03/30/2020 | 118755418 | 03/30/2020 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2022 | ED.08201.2103 | EVERGREEN 2103 | 043 | SANTA CLARA CO | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2020 | # | OPEN | 249 | 35.5714 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 3150.1
35168794 | GRAND ISLAND 2227 RECOND 3.7MI W 4/0-2AR | 03/27/2020 | 118738655 | 03/24/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/01/2022 | ED.06246.2227 | GRAND ISLAND 2227 | 057 | YOLO COUNTY | 5517127 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2020 | # | OPEN | 252 | 36 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Grand Island - Reconductor 19,370 feet | Base Capital | GRC Electric Dist | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 2513.21
35168820 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.4 | 03/25/2020 | 118738238 | 03/24/2020 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2021 | ED.15308.2106 | PLACERVILLE 2106 | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 254 | 36.2857 | ESTS | 2 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Placerville 2106 - LR 1104 - Ph 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35168821 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.5 | 03/25/2020 | 118738363 | 03/24/2020 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2021 | ED.15308.2106 | PLACERVILLE 2106 | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 3,934.000 | 0.000 | 08W | 2020 | # | OPEN | 254 | 36.2857 | ESTS | 2 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Placerville 2106 - LR 1104 - Ph 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 412.71
35168822 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.6 | 03/25/2020 | 118738366 | 03/24/2020 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2021 | ED.15308.2106 | PLACERVILLE 2106 | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 254 | 36.2857 | ESTS | 2 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Placerville 2106 - LR 1104 - Ph 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35168823 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.7 | 03/25/2020 | 118738440 | 03/24/2020 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2021 | ED.15308.2106 | PLACERVILLE 2106 | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 254 | 36.2857 | ESTS | 2 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Placerville 2106 - LR 1104 - Ph 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 220.94
35169499 | CASTROVILLE 2103 RECOND LOG#20-0016183 | 03/26/2020 | 118748612 | 03/26/2020 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/30/2022 | ED.18235.2103 | CASTROVILLE 2103 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2020 | # | OPEN | 253 | 36.1429 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 1501.87
35170201 | LODI 1102 RECONDUCTOR & CUTOVER TO 12KV | 04/01/2020 | 114248752 | 01/25/2018 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.93-Q111400000.STRU.POLE | STOCKTON Q1114 POLES | 039 | SAN JOAQUIN CO | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2020 | # | OPEN | 247 | 35.2857 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35170202 | CWSP - ORO FINO 1101 - LR2022 PH2.7 | 04/03/2020 | 118771067 | 04/02/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1101 | ORO FINO 1101 | 004 | BUTTE COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 245 | 35 | ESTS | 2 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - ORO FINO-1101 LR-2022 PH 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 10948.54
35171354 | CWSP - CAMP EVERS 2106 - 5020 - PHASE 2 | 04/09/2020 | 118796971 | 04/08/2020 | # | Not assigned | 30 | Technically Completed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/30/2020 | ED.08362.2106 | CAMP EVERS 2106 | 044 | SANTA CRUZ COU | 5535211 | CWSP SPO - SH 08 | 1.000 | 0.000 | 08W | 2020 | # | OPEN | 239 | 34.1429 | FICL | 10 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2020-04-29 | 2020-04-29 | COMP | 2020-04-27 | 2020-07-21 | COMP | 2020-07-21 | 2020-07-21 | COMP | 2020-07-21 | 2020-07-22 | COMP | 2020-07-22 | 2020-07-23 | COMP | 2020-07-23 | 2020-07-24 | 83 | 3 | 28419.84
35171705 | BR-03-12-W (E) PENTZ RD SRTS PARB | 04/10/2020 | 118911002 | 04/10/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.17-S341700000.STRU.POLE | PARADISE S3417 POLES | 004 | BUTTE COUNTY | 5786123 | 08W Rebuild | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 238 | 34 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 1024292.44
35172091 | R1-RELIAIBLITY SAN PABLO REPLACE 4ACSR | 04/17/2020 | 118926905 | 04/16/2020 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2022 | ED.01437.1105 | SAN PABLO 1105 | 007 | CONTRA COSTA C | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2020 | # | OPEN | 231 | 33 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 681.96
35172093 | *CANC* EL DORADO PH 2102 LR19542 P*CANC | 04/17/2020 | 13860338 | 04/17/2020 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.15276.2102.RECL | RECLOSERS | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2020 | 05/03/2020 | 2020 | 16 | 2.2857 | CLSD | 12 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35172094 | CWSP-EL DORADO PH 2102 LR19542 PH 1*CANC | 04/17/2020 | 13860383 | 04/17/2020 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.15276.2102.RECL | RECLOSERS | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2020 | 05/03/2020 | 2020 | 16 | 2.2857 | CLSD | 12 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35172521 | *CANC* EL DORADO PH 2102 LR19542 P*CANC | 04/17/2020 | 13860424 | 04/17/2020 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.15276.2102.RECL | RECLOSERS | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2020 | 05/03/2020 | 2020 | 16 | 2.2857 | CLSD | 12 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35172522 | *CANC* CWSP-EL DORADO PH 2102 LR195*CANC | 04/17/2020 | 13860394 | 04/17/2020 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.15276.2102.RECL | RECLOSERS | 046 | SIERRA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2020 | 05/03/2020 | 2020 | 16 | 2.2857 | CLSD | 12 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35173253 | CWSP-EL DORADO PH 2102 LR19542 PH 1.3 | 04/20/2020 | 118926912 | 04/16/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.15276.2102.RECL | RECLOSERS | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 228 | 32.5714 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - El Dorado PH 2102 Zone 19542 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 355.09
35173255 | CWSP-EL DORADO PH 2102 LR19542 PH 1.2 | 04/20/2020 | 118926574 | 04/16/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.15276.2102.RECL | RECLOSERS | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 228 | 32.5714 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - El Dorado PH 2102 Zone 19542 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 1071.26
35173320 | CWSP-EL DORADO PH 2102 LR19542 PH 1.5 | 04/20/2020 | 118926984 | 04/16/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.15276.2102.RECL | RECLOSERS | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 228 | 32.5714 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - El Dorado PH 2102 Zone 19542 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 355.09
35173321 | CWSP-EL DORADO PH 2102 LR19542 PH 1.4 | 04/20/2020 | 118926983 | 04/16/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.15276.2102.RECL | RECLOSERS | 046 | SIERRA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 228 | 32.5714 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - El Dorado PH 2102 Zone 19542 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 355.09
35173387 | BR-09-01-W (E) SKYWAY PH3 20A PARB | 04/21/2020 | 118935079 | 04/21/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/30/2021 | ED.17-T321300000.STRU.POLE | PARADISE T3213 POLES | 004 | BUTTE COUNTY | 5786123 | 08W Rebuild | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 227 | 32.4286 | ESTS | 2 | E470 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35173754 | ECOP-BRUNSWICK 1106-H08-LR51486 | 04/22/2020 | 118911473 | 04/10/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.22-O110900000.STRU.POLE | NEVADA O1109 POLES | 029 | NEVADA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 226 | 32.2857 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP-Brunswick 1106-H08-LR51486 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 14803.97
35173755 | ECOP-WEST POINT 1101-H02-LR36674 | 04/22/2020 | 118911674 | 04/10/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.95-I302300000.STRU.POLE | MOTHER LODE I3023 POLES | 003 | AMADOR COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 226 | 32.2857 | ESTS | 2 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP-WEST POINT 1101-H02-LR36674 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 28719.45
35173756 | ECOP-EL DORADO 2101-H02-LR6852-PH2 | 04/22/2020 | 118911791 | 04/10/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.21-H471000000.STRU.POLE | EL DORADO H4710 POLES | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 226 | 32.2857 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP-El Dorado 2101-H02-LR6852-Ph2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 8231.64
35173959 | CWSP-MIWUK 1702-LR 38218-PH 1.6 | 04/23/2020 | 118940594 | 04/22/2020 | # | Not assigned | 10 | Created | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.16366.1702 | MIWUK 1702 | 055 | TUOLUMNE COUNT | 5785985 | CWSP - MIWUK 1702 - LR 38218 - PH 1.6 | 4,747.000 | 0.000 | 08W | 2020 | # | OPEN | 225 | 32.1429 | ESTS | 2 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35173968 | GRAND ISLAND 2223 RECOND 4840FT W/ 2AR | 04/23/2020 | 118944504 | 04/23/2020 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/01/2022 | ED.06246.2223 | GRAND ISLAND 2223 | 057 | YOLO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2020 | # | OPEN | 225 | 32.1429 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 1722.66
35174085 | PSPS - FIA320 - LR @ 101269978 | 04/23/2020 | 118944585 | 04/23/2020 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/31/2020 | ED.95-R280000000.STRU.POLE | MOTHER LODE R28 POLES | 005 | CALAVERAS COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 225 | 32.1429 | UNSC | 6 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 388.21
35174174 | ECOP-STANISLAUS 1702-H03-LR1850 | 04/24/2020 | 13867552 | 04/24/2020 | # | Not assigned | 10 | Created | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.16282.1702 | STANISLAUS 1702 | 005 | CALAVERAS COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 224 | 32 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Deleted/Cancelled projects | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35174465 | ECOP-EL DORADO 2101-H02-LR6852-PH1 | 04/27/2020 | 118911790 | 04/10/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.21-H471000000.STRU.POLE | EL DORADO H4710 POLES | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 221 | 31.5714 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP-El Dorado 2101-H02-LR6852-Ph1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 19099.3
35174466 | ECOP-EL DORADO 2101-H02-LR6852-PH3 | 04/27/2020 | 118911793 | 04/10/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.21-H471000000.STRU.POLE | EL DORADO H4710 POLES | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 221 | 31.5714 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP-El Dorado 2101-H02-LR6852-Ph3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 12231.93
35174467 | ECOP-STANISLAUS 1702-H01-LR37276-PH1 | 04/27/2020 | 118912984 | 04/12/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.95-O341400000.STRU.POLE | MOTHER LODE O3414 POLES | 005 | CALAVERAS COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 221 | 31.5714 | ESTS | 2 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP-Stanislaus 1702-H01-LR37276-Ph1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 3203.12
35174468 | ECOP-STANISLAUS 1702-H01-LR37276-PH2 | 04/27/2020 | 118912985 | 04/12/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.95-O341400000.STRU.POLE | MOTHER LODE O3414 POLES | 005 | CALAVERAS COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 221 | 31.5714 | ESTS | 2 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP-Stanislaus 1702-H01-LR37276-Ph2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 2824.12
35174469 | ECOP-PINE GROVE 1102-H01-LR45292 | 04/27/2020 | 118912983 | 04/12/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.95-K290400000.STRU.POLE | MOTHER LODE K2904 POLES | 003 | AMADOR COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 221 | 31.5714 | ESTS | 2 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP-Pine Grove 1102-H01-LR45292 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 25623.19
35174470 | ECOP-MOLINO 1102-H01-LR318 | 04/27/2020 | 118912761 | 04/11/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.44-JJ22110000.STRU.POLE | SANTA ROSA JJ2211 POLES | 049 | SONOMA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 221 | 31.5714 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP-Molino 1102-H01-LR318 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 8305.71
35174471 | ECOP-MONTE RIO 1113-H07-LR180 | 04/27/2020 | 13869444 | 04/27/2020 | # | Not assigned | 10 | Created | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.04281.1113 | MONTE RIO 1113 | 049 | SONOMA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 221 | 31.5714 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Deleted/Cancelled projects | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35174472 | ECOP-CALISTOGA 1101-H02-LR43924 | 04/27/2020 | 118912499 | 04/11/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.04271.1101 | CALISTOGA 1101 | 028 | NAPA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 221 | 31.5714 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP-Calistoga 1101-H02-LR43924 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 14454.72
35174473 | ECOP-CALISTOGA 1101-H03-LR43924 | 04/27/2020 | 118912760 | 04/11/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.04271.1101 | CALISTOGA 1101 | 028 | NAPA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 221 | 31.5714 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP-Calistoga 1101-H03-LR43924 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 12664.2
35174474 | ECOP-CALISTOGA 1101-H01-LR736 PH1 | 04/27/2020 | 118912987 | 04/12/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.04271.1101 | CALISTOGA 1101 | 028 | NAPA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 221 | 31.5714 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP-Calistoga 1101-H01-LR736 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 17567.79
35174475 | ECOP-CALISTOGA 1101-H01-LR736-E_O CO3807 | 04/27/2020 | 118912988 | 04/12/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.04271.1101 | CALISTOGA 1101 | 028 | NAPA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 221 | 31.5714 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP-Calistoga 1101-H01-LR736-S_O 208157 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 4722.22
35174476 | ECOP-CALISTOGA 1101-H01-LR736-S_O 208157 | 04/27/2020 | 118913020 | 04/12/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.44-GG30000000.STRU.POLE | SANTA ROSA GG30 POLES | 049 | SONOMA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 221 | 31.5714 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP-Calistoga 1101-H01-LR736-N_O CO7729 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 5045.48
35174477 | ECOP-CALISTOGA 1101-H01-LR736-PH3 | 04/27/2020 | 118913023 | 04/12/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.04271.1101 | CALISTOGA 1101 | 028 | NAPA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 221 | 31.5714 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP-Calistoga 1101-H01-LR736-Ph3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 5633.45
35174478 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1 | 04/27/2020 | 118913024 | 04/12/2020 | # | Not assigned | 10 | Created | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.46-BB30170000.STRU.POLE | UKIAH BB3017 POLES | 017 | LAKE COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 221 | 31.5714 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | ECOP-Middletown 1101-H12-LR548-Ph1 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35174479 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2 | 04/27/2020 | 118913025 | 04/12/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.46-BB30170000.STRU.POLE | UKIAH BB3017 POLES | 017 | LAKE COUNTY | 5517127 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 221 | 31.5714 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | ECOP-Middletown 1101-H12-LR548-Ph2 | Base Capital | GRC Electric Dist | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 12673.86
35174501 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3 | 04/27/2020 | 118913026 | 04/12/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.44-KK33160000.STRU.POLE | SANTA ROSA KK3316 POLES | 017 | LAKE COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 221 | 31.5714 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP-Middletown 1101-H12-LR548-Ph3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 10792.93
35174993 | CWSP - PLACERVILLE 2106 - LR1104 - PH2.2 | 05/01/2020 | 118964445 | 04/30/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15308.2106 | PLACERVILLE 2106 | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 217 | 31 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Placerville 2106 - LR 1104 - Phas | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35175131 | *CANC* - PLACERVILLE 2106 - LR1104 - PH2 | 05/01/2020 | 13873394 | 05/01/2020 | # | Not assigned | 40 | Closed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15308.2106 | PLACERVILLE 2106 | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2020 | 06/03/2020 | 2020 | 33 | 4.7143 | CLSD | 12 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | COMP | 2020-05-22 | 2020-05-22 | COMP | 2020-05-22 | 2020-05-22 | COMP | 2020-05-22 | 2020-05-22 | 0 | 43973 | 0
35175132 | *CANC* - PLACERVILLE 2106 - LR1104 - PH | 05/01/2020 | 13873357 | 05/01/2020 | # | Not assigned | 10 | Created | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15308.2106 | PLACERVILLE 2106 | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 217 | 31 | CNCL | Other | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | COMP | 2020-05-22 | 2020-05-22 | COMP | 2020-05-22 | 2020-05-22 | COMP | 2020-05-22 | 2020-05-22 | 0 | 43973 | 0
35175549 | BR-05-07-W (E) HIGH SCHOOL MAXWELL PARB | 05/04/2020 | 118978773 | 05/04/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 09/25/2020 | ED.17-T330200000.STRU.POLE | PARADISE T3302 POLES | 004 | BUTTE COUNTY | 5786123 | 08W Rebuild | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 214 | 30.5714 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 246.63
35175560 | DC-1112 RECOND 575 FT OF 4AR 20-0040068 | 05/04/2020 | 118976222 | 05/02/2020 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/30/2022 | ED.56-D022400000.STRU.POLE | SKYLINE D0224 POLES | 041 | SAN MATEO COUN | 5505513 | PN-OH ANNEALED/DETER CNDCTR: PM MGD | 575.000 | 0.000 | 08J | 2020 | # | OPEN | 214 | 30.5714 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 173.03
35175843 | CWSP - PLACERVILLE 2106 - LR1104 - PH3.2 | 05/05/2020 | 118981826 | 05/04/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15308.2106 | PLACERVILLE 2106 | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 213 | 30.4286 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-PLACERVILLE 2106 LR1104 PH 3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35175844 | CWSP - PLACERVILLE 2106 - LR1104 - PH3.3 | 05/05/2020 | 118981828 | 05/04/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15308.2106 | PLACERVILLE 2106 | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 213 | 30.4286 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-PLACERVILLE 2106 LR1104 PH 3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35175845 | CWSP - PLACERVILLE 2106 - LR1104 - PH3.4 | 05/05/2020 | 118981829 | 05/04/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15308.2106 | PLACERVILLE 2106 | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 213 | 30.4286 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-PLACERVILLE 2106 LR1104 PH 3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35175846 | CWSP - PLACERVILLE 2106 - LR1104 - PH3.5 | 05/05/2020 | 118981890 | 05/04/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15308.2106 | PLACERVILLE 2106 | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 213 | 30.4286 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-PLACERVILLE 2106 LR1104 PH 3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35175847 | CWSP - PLACERVILLE 2106 - LR1104 - PH4.2 | 05/05/2020 | 118981893 | 05/04/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15308.2106 | PLACERVILLE 2106 | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 213 | 30.4286 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-PLACERVILLE 2106 LR1104 PH 4 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 76.87
35175848 | CWSP - PLACERVILLE 2106 - LR1104 - PH4.3 | 05/05/2020 | 118981896 | 05/04/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15308.2106 | PLACERVILLE 2106 | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 213 | 30.4286 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-PLACERVILLE 2106 LR1104 PH 4 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35175849 | CWSP - PLACERVILLE 2106 - LR1104 - PH4.4 | 05/05/2020 | 118981897 | 05/04/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15308.2106 | PLACERVILLE 2106 | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 213 | 30.4286 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-PLACERVILLE 2106 LR1104 PH 4 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35175850 | CWSP - PLACERVILLE 2106 - LR1104 - PH4.5 | 05/05/2020 | 118981898 | 05/04/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15308.2106 | PLACERVILLE 2106 | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 213 | 30.4286 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-PLACERVILLE 2106 LR1104 PH 4 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35175852 | CWSP - PLACERVILLE 2106 - LR1104 - PH5.2 | 05/05/2020 | 118981899 | 05/04/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15308.2106 | PLACERVILLE 2106 | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 213 | 30.4286 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-PLACERVILLE 2106 LR1104 PH 5 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35175853 | CWSP - PLACERVILLE 2106 - LR1104 - PH5.3 | 05/05/2020 | 118981960 | 05/04/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15308.2106 | PLACERVILLE 2106 | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 213 | 30.4286 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-PLACERVILLE 2106 LR1104 PH 5 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35175854 | CWSP - PLACERVILLE 2106 - LR1104 - PH5.4 | 05/05/2020 | 118981961 | 05/04/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15308.2106 | PLACERVILLE 2106 | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 213 | 30.4286 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-PLACERVILLE 2106 LR1104 PH 5 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35175855 | CWSP - PLACERVILLE 2106 - LR1104 - PH5.5 | 05/05/2020 | 118981962 | 05/04/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15308.2106 | PLACERVILLE 2106 | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 213 | 30.4286 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-PLACERVILLE 2106 LR1104 PH 5 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35175856 | CWSP - PLACERVILLE 2106 - LR1104 - PH6.2 | 05/05/2020 | 118981963 | 05/04/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15308.2106 | PLACERVILLE 2106 | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 213 | 30.4286 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-PLACERVILLE 2106 LR1104 PH 6 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35175857 | CWSP - PLACERVILLE 2106 - LR1104 - PH6.3 | 05/05/2020 | 118981964 | 05/04/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15308.2106 | PLACERVILLE 2106 | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 213 | 30.4286 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-PLACERVILLE 2106 LR1104 PH 6 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35175858 | CWSP - PLACERVILLE 2106 - LR1104 - PH6.4 | 05/05/2020 | 118981965 | 05/04/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15308.2106 | PLACERVILLE 2106 | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 213 | 30.4286 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-PLACERVILLE 2106 LR1104 PH 6 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35175859 | CWSP - PLACERVILLE 2106 - LR1104 - PH6.5 | 05/05/2020 | 118981966 | 05/04/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15308.2106 | PLACERVILLE 2106 | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 213 | 30.4286 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-PLACERVILLE 2106 LR1104 PH 6 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35176209 | CWSP - PLACERVILLE 2106 - LR1104 - PH2.3 | 05/07/2020 | 118964446 | 04/30/2020 | # | Not assigned | 10 | Created | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15308.2106 | PLACERVILLE 2106 | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 211 | 30.1429 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Placerville 2106 - LR 1104 - Phas | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35176210 | CWSP - PLACERVILLE 2106 - LR1104 - PH2.4 | 05/07/2020 | 118964447 | 04/30/2020 | # | Not assigned | 10 | Created | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15308.2106 | PLACERVILLE 2106 | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 211 | 30.1429 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Placerville 2106 - LR 1104 - Phas | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35176211 | CWSP - PLACERVILLE 2106 - LR1104 - PH2.5 | 05/07/2020 | 118964448 | 04/30/2020 | # | Not assigned | 10 | Created | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15308.2106 | PLACERVILLE 2106 | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 211 | 30.1429 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Placerville 2106 - LR 1104 - Phas | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35176497 | ECOP-STANISLAUS 1702-H03-LR1850 | 05/11/2020 | 118911798 | 04/10/2020 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2021 | ED.16282.1702 | STANISLAUS 1702 | 005 | CALAVERAS COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 207 | 29.5714 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Deleted/Cancelled projects | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 12724.59
35176549 | ECOP-MONTE RIO 1113-H07-LR180 | 05/12/2020 | 118912762 | 04/11/2020 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2021 | ED.04281.1113 | MONTE RIO 1113 | 049 | SONOMA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 206 | 29.4286 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Deleted/Cancelled projects | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 7406.84
35177107 | CWSP - PLACERVILLE 2106 - LR1104 - PH3.6 | 05/13/2020 | 119021512 | 05/12/2020 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2021 | ED.15308.2106 | PLACERVILLE 2106 | 009 | EL DORADO COUN | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 205 | 29.2857 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-PLACERVILLE 2106 LR1104 PH 3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35177108 | CWSP - PLACERVILLE 2106 - LR1104 - PH3.7 | 05/13/2020 | 119021513 | 05/12/2020 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2021 | ED.15308.2106 | PLACERVILLE 2106 | 009 | EL DORADO COUN | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 205 | 29.2857 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-PLACERVILLE 2106 LR1104 PH 3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35177109 | CWSP - PLACERVILLE 2106 - LR1104 - PH2.6 | 05/13/2020 | 119021498 | 05/12/2020 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2021 | ED.15308.2106 | PLACERVILLE 2106 | 009 | EL DORADO COUN | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 205 | 29.2857 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Placerville 2106 - LR 1104 - Phas | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35177110 | CWSP - PLACERVILLE 2106 - LR1104 - PH2.7 | 05/13/2020 | 119021499 | 05/12/2020 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2021 | ED.15308.2106 | PLACERVILLE 2106 | 009 | EL DORADO COUN | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 205 | 29.2857 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Placerville 2106 - LR 1104 - Phas | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35177111 | CWSP - PLACERVILLE 2106 - LR1104 - PH2.8 | 05/13/2020 | 119021511 | 05/12/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15308.2106 | PLACERVILLE 2106 | 009 | EL DORADO COUN | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 205 | 29.2857 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Placerville 2106 - LR 1104 - Phas | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35178081 | RECOUNDUCTOR 925 FT OF 4 ACSR WITH 2CU | 05/19/2020 | 119043197 | 05/19/2020 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 05/19/2023 | ED.18206.1106 | FAIRWAY 1106 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2020 | # | OPEN | 199 | 28.4286 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35178764 | SPEN-1102 REC 1,312FT OF 4AR 20-0046857 | 05/26/2020 | 119052457 | 05/21/2020 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/30/2023 | ED.05-I120900000.STRU.POLE | SALINAS I1209 POLES | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 1,312.000 | 0.000 | 08J | 2020 | # | OPEN | 192 | 27.4286 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 1024.15
35179069 | BUCOCAMPTUG WILDWOOD LN PARADISE | 05/27/2020 | 119066408 | 05/27/2020 | # | Not assigned | 30 | Technically Completed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/23/2020 | JY | JUNK YARD FL TO HOLD DELETED DATA | 004 | BUTTE COUNTY | 5791246 | Butte Rebuild UG TAP 08W | 500.000 | 0.000 | 08W | 2020 | # | OPEN | 191 | 27.2857 | FICL | 10 | E460 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2020-09-03 | 2020-09-03 | COMP | 2020-10-09 | 2020-10-09 | COMP | 2020-10-09 | 2020-10-13 | COMP | 2020-10-13 | 2020-10-14 | COMP | 2020-10-14 | 2020-10-22 | COMP | 2020-10-22 | 2020-10-28 | 40 | 15 | 110045.7
35179087 | RECONDUCTOR 400' OF 4 ASCR W/ 2 CU | 05/27/2020 | 119065385 | 05/26/2020 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2023 | ED.40-UU33150000.STRU.POLE | NORTH BAY MAP UU3315 POLES | 021 | MARIN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2020 | # | OPEN | 191 | 27.2857 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35179088 | RECOND 1400' W/ 4/0 AL | 05/27/2020 | 119065722 | 05/26/2020 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2023 | ED.42-HH34080000.STRU.POLE | SILVERADO MAP HH3408 POLES | 028 | NAPA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2020 | # | OPEN | 191 | 27.2857 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35179328 | BUCOCAMPTUG SUN RIVER CT PARADISE | 05/28/2020 | 119073514 | 05/28/2020 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.17-T331200000.STRU.POLE | PARADISE T3312 POLES | 004 | BUTTE COUNTY | 5791246 | Butte Rebuild UG TAP 08W | 751.000 | 0.000 | 08W | 2020 | # | OPEN | 190 | 27.1429 | CONS | 7 | E460 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 38983.23
35180088 | BUCOCAMPTUG 5507 ROCKFORD LN PARADISE | 06/03/2020 | 119098203 | 06/03/2020 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 08/28/2020 | ED.17-T340800000.STRU.POLE | PARADISE T3408 POLES | 004 | BUTTE COUNTY | 5791246 | Butte Rebuild UG TAP 08W | 174.000 | 0.000 | 08W | 2020 | # | OPEN | 184 | 26.2857 | CONS | 7 | E460 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 41926.64
35180245 | RPL OH COND.SAN BRUNO-0402 20-0049211 | 06/03/2020 | 119097306 | 06/02/2020 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/30/2023 | ED.56-E042300000.STRU.POLE | SKYLINE E0423 POLES | 041 | SAN MATEO COUN | 5505513 | PN-OH ANNEALED/DETER CNDCTR: PM MGD | 1,036.000 | 0.000 | 08J | 2020 | # | OPEN | 184 | 26.2857 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 682.76
35181199 | ECOP-WEST POINT 1101-H03-TS L373 | 06/10/2020 | 118991252 | 05/06/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.95-J290800000.STRU.POLE | MOTHER LODE J2908 POLES | 003 | AMADOR COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 177 | 25.2857 | ESTS | 2 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP-WEST POINT 1101-H03-TS L373 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 6724.7
35181318 | BUCOCAMPTUG 6650 WHITTALL LN PARADISE | 06/10/2020 | 119141713 | 06/10/2020 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/27/2020 | ED.17-S331900000.STRU.POLE | PARADISE S3319 POLES | 004 | BUTTE COUNTY | 5791246 | Butte Rebuild UG TAP 08W | 356.000 | 0.000 | 08W | 2020 | # | OPEN | 177 | 25.2857 | CONS | 7 | E460 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | INPR | 2020-11-19 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 27096.47
35181319 | BUCOCAMPTUG STINSON LN PARADISE | 06/10/2020 | 119142173 | 06/10/2020 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/27/2020 | ED.17-S332400000.STRU.POLE | PARADISE S3324 POLES | 004 | BUTTE COUNTY | 5791246 | Butte Rebuild UG TAP 08W | 534.000 | 0.000 | 08W | 2020 | # | OPEN | 177 | 25.2857 | CONS | 7 | E460 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 40701.9
35181576 | CWSP- BUCOCAMP - SKYWAY PARADISE TIE PH1 | 06/12/2020 | 119159304 | 06/12/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 09/25/2020 | ED.16-U291400000.STRU.POLE | CHICO MAP U2914 POLES | 004 | BUTTE COUNTY | 5791419 | CWSP - BUCOCAMP-SKYWAY PARADISE TIE PH1 | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 175 | 25 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35181764 | PEABODY 2105 RECOND 630FT W 2AR | 06/15/2020 | 119159904 | 06/12/2020 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/01/2023 | ED.48-S120500000.STRU.POLE | SOLANO S1205 POLES | 048 | SOLANO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2020 | # | OPEN | 172 | 24.5714 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 341.4
35181924 | BUCOCAMPTUG ROE RD/WILSON LN PARADISE | 06/15/2020 | 119165277 | 06/15/2020 | 35174758 | R4 (G) 14D BR-10-05 ROE RD, PARD | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 08/28/2020 | ED.17-T321500000.STRU.POLE | PARADISE T3215 POLES | 004 | BUTTE COUNTY | 5791246 | Butte Rebuild UG TAP 08W | 1.000 | 0.000 | 08W | 2020 | # | OPEN | 172 | 24.5714 | MAPP | 9 | E460 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2020-07-10 | 2020-07-10 | COMP | 2020-11-18 | 2020-11-18 | COMP | 2020-11-18 | 2020-11-19 | COMP | 2020-11-19 | 2020-11-20 | INPR | 2020-11-20 | 0 | # | 0 | 0 | 132 | -44154 | 99979.43
35181939 | WD RECONDUCTORING ON WYANDOTTE 1103 | 06/16/2020 | 119146963 | 06/11/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2022 | ED.10291.1103 | WYANDOTTE 1103 | 004 | BUTTE COUNTY | 5532077 | ED MAT 08W (Rate Case) | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 171 | 24.4286 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Other Capital | Other | # | # | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35183226 | GRAND ISLAND 2225 RECOND 2.4MI (PH1) | 06/23/2020 | 119184799 | 06/18/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/01/2021 | ED.48-T220000000.STRU.POLE | SOLANO T22 POLES | 034 | SACRAMENTO COU | 5517127 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2020 | # | OPEN | 164 | 23.4286 | ESTS | 2 | E470 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Grand Island 2224/2225 Outlet Ph1 | Base Capital | GRC Electric Dist | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 4814.15
35184050 | KETTLEMAN HILLS 1101 RECOND 2741FT 4AR | 06/29/2020 | 111994672 | 09/28/2016 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.25273.1101 | KETTLEMAN HILLS 1101 | 016 | KINGS COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 5,356.000 | 0.000 | 08J | 2020 | # | OPEN | 158 | 22.5714 | PEND | 5 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 169474.08
35184468 | WOODLAND 1108 - RECOND 230FT - OCB | 07/01/2020 | 119293564 | 07/01/2020 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/01/2023 | ED.50-I172500000.STRU.POLE | YOLO I1725 POLES | 057 | YOLO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2020 | # | OPEN | 156 | 22.2857 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 924.55
35185714 | WDDB - OTTER 1102 - LR 2002 | 07/09/2020 | 119231992 | 06/29/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 06/30/2022 | ED.18294.1102.SWIT | SWITCHES | 027 | MONTEREY COUNT | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 148 | 21.1429 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Otter 1102 - OH Line Replc - #19-0131557 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 1801.54
35187368 | RECOND 11,356 FT OF 6CU AND 4ACSR W 4/0 | 07/21/2020 | 119318336 | 07/07/2020 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2023 | ED.01-VV40080000.STRU.POLE | SANTA MARIA VV4008 POLES | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2020 | # | OPEN | 136 | 19.4286 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35191130 | ECOP - CALISTOGA 1101 - H01 - LR 736-PH5 | 08/03/2020 | 119536531 | 07/31/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.42-FF29000000.STRU.POLE | SILVERADO MAP FF29 POLES | 049 | SONOMA COUNTY | 5517127 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 123 | 17.5714 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | ECOP-CALISTOGA 1101-H01-LR736-Ph4 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 5081.85
35191311 | ECOP - MONTE RIO 1113 - H06-LR8299 | 08/04/2020 | 119518125 | 07/28/2020 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2022 | ED.44-HH20030000.STRU.POLE | SANTA ROSA HH2003 POLES | 049 | SONOMA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 122 | 17.4286 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - MONTE RIO 1113 - H06-LR8299 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 1554.09
35191313 | ECOP - MONTE RIO 1113 - H06-LR8299 | 08/04/2020 | 119518128 | 07/28/2020 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2022 | ED.44-GG19020000.STRU.POLE | SANTA ROSA GG1902 POLES | 049 | SONOMA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 122 | 17.4286 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - MONTE RIO 1111 - H01-LR64758 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 2569
35191316 | ECOP - OAKHURST 1103 - H01-LR10190 | 08/04/2020 | 119518129 | 07/28/2020 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2022 | ED.72-0521236000.STRU.POLE | MERCED MAP 0521236 POLES | 022 | MARIPOSA COUNT | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 122 | 17.4286 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - OAKHURST 1103 - H01-LR10190 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 2763.86
35191317 | ECOP - BRUNSWICK 1106 - H03 - LR4639 | 08/04/2020 | 119518394 | 07/28/2020 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2023 | ED.22-O090400000.STRU.POLE | NEVADA O0904 POLES | 029 | NEVADA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 122 | 17.4286 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - BRUNSWICK 1106 - H03 - LR4639 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 1529.29
35191318 | ECOP - SILVERADO 2102 - H02-LR58626 | 08/04/2020 | 119518390 | 07/28/2020 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2022 | ED.42-HH36000000.STRU.POLE | SILVERADO HH36 POLES | 028 | NAPA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 122 | 17.4286 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - SILVERADO 2102 - H02-LR58626 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 3000.96
35191319 | ECOP - LAS GALLINAS A 1105 - H01-LR99904 | 08/04/2020 | 119518398 | 07/28/2020 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2023 | ED.40-RR29200000.STRU.POLE | NORTH BAY MAP RR2920 POLES | 021 | MARIN COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 122 | 17.4286 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - LAS GALLINAS A 1105 - H01-LR99904 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 2633.96
35191380 | ECOP - MIWUK 1702 - H02-LR9270 | 08/04/2020 | 119518524 | 07/28/2020 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2023 | ED.91-T361400000.STRU.POLE | STANISLAUS T3614 POLES | 055 | TUOLUMNE COUNT | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 122 | 17.4286 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - MIWUK 1702 - H02-LR9270 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 1529.29
35191381 | ECOP - MIWUK 1702 - H03-LR9270 | 08/04/2020 | 119518525 | 07/28/2020 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2023 | ED.91-T361900000.STRU.POLE | STANISLAUS T3619 POLES | 055 | TUOLUMNE COUNT | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 122 | 17.4286 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - MIWUK 1702 - H03-LR9270 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 1529.29
35191382 | ECOP - MORAGA 1105 - H01-CB | 08/04/2020 | 119518526 | 07/28/2020 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2023 | ED.30-F070900000.STRU.POLE | DIABLO F0709 POLES | 007 | CONTRA COSTA C | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 122 | 17.4286 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - MORAGA 1105 - H01-CB | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 1529.29
35191383 | ECOP - SILVERADO 2102 - H01-LR58626 | 08/04/2020 | 119518528 | 07/28/2020 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2023 | ED.42-HH36000000.STRU.POLE | SILVERADO HH36 POLES | 028 | NAPA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 122 | 17.4286 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - SILVERADO 2102 - H01-LR58626 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 1529.29
35191520 | STONE CORRAL 1110 RECOND 1,585 FEET | 08/04/2020 | 113817663 | 11/15/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 07/05/2019 | ED.25292.1110 | STONE CORRAL 1110 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2020 | # | OPEN | 122 | 17.4286 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 594.44
35191553 | BR-13-01-W (E) LIGHTFOOT WAY PARB | 08/05/2020 | 119560543 | 08/05/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 07/30/2021 | ED.17-T330400000.STRU.POLE | PARADISE T3304 POLES | 004 | BUTTE COUNTY | 5786123 | 08W Rebuild | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 121 | 17.2857 | ESTS | 2 | E470 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 7987.57
35191930 | ECOP - WOODACRE 1101 - H01-LR404 PH1 | 08/07/2020 | 119553788 | 08/03/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2022 | ED.40-SS29080000.STRU.POLE | NORTH BAY MAP SS2908 POLES | 021 | MARIN COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 119 | 17 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - WOODACRE 1101 - H01-LR404 Ph1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 4571.5
35191934 | ECOP - WOODACRE 1101 - H01-LR404 PH2 | 08/07/2020 | 119553797 | 08/03/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2022 | ED.40-SS29080000.STRU.POLE | NORTH BAY MAP SS2908 POLES | 021 | MARIN COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 119 | 17 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - WOODACRE 1101 - H01-LR404 Ph2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 3286.59
35191937 | ECOP - PUEBLO 2102 - H01-LR792 | 08/07/2020 | 119553837 | 08/03/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2022 | ED.42-JJ34000000.STRU.POLE | SILVERADO JJ34 POLES | 028 | NAPA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 119 | 17 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - PUEBLO 2102 - H01-LR792 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 3215.84
35192021 | ECOP - SILVERADO 2104 - H02-LR78268 | 08/07/2020 | 119553918 | 08/03/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2022 | ED.42-GG35020000.STRU.POLE | SILVERADO GG3502 POLES | 028 | NAPA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 119 | 17 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - SILVERADO 2104 - H02-LR78268 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 8949.41
35192025 | ECOP - FORESTHILL 1101 - H02-LR1802 PH1 | 08/07/2020 | 119550890 | 08/03/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2022 | ED.20-R142000000.STRU.POLE | PLACER R1420 POLES | 031 | PLACER COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 119 | 17 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - FORESTHILL 1101 - H02-LR1802 Ph1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 2883.25
35192028 | ECOP - FORESTHILL 1101 - H02-LR1802 PH2 | 08/07/2020 | 119550898 | 08/03/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2022 | ED.20-R142000000.STRU.POLE | PLACER R1420 POLES | 031 | PLACER COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 119 | 17 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - FORESTHILL 1101 - H02-LR1802 Ph2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 1562.04
35192029 | ECOP - FORESTHILL 1101 - H02-LR1802 PH3 | 08/07/2020 | 119551168 | 08/03/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2022 | ED.20-R142000000.STRU.POLE | PLACER R1420 POLES | 031 | PLACER COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 119 | 17 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - FORESTHILL 1101 - H02-LR1802 Ph3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 1990.36
35192031 | ECOP - COLUMBIA HILL 1101 - H01-LR35424 | 08/07/2020 | 119553917 | 08/03/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2022 | ED.22-K070000000.STRU.POLE | NEVADA K07 POLES | 029 | NEVADA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 119 | 17 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - COLUMBIA HILL 1101 - H01-LR35424 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 3217.75
35192034 | ECOP-APPLE HILL 1104-H01-LR13512 | 08/07/2020 | 119554053 | 08/03/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2022 | ED.21-H452000000.STRU.POLE | EL DORADO H4520 POLES | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 119 | 17 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP-APPLE HILL 1104-H01-LR13512 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 2139.98
35192035 | ECOP - MIRABEL 1101 - H01-LR298 | 08/07/2020 | 119553910 | 08/03/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2022 | ED.44-HH22110000.STRU.POLE | SANTA ROSA HH2211 POLES | 049 | SONOMA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 119 | 17 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - MIRABEL 1101 - H01-LR298 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 1545.51
35192036 | ECOP - RINCON 1103 - H01-LR474 | 08/07/2020 | 119553915 | 08/03/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2022 | ED.44-HH30010000.STRU.POLE | SANTA ROSA HH3001 POLES | 049 | SONOMA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 119 | 17 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - RINCON 1103 - H01-LR474 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 4146.91
35192037 | ECOP - SILVERADO 2105 - H01-LR1421 | 08/07/2020 | 119554055 | 08/03/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2022 | ED.44-HH32000000.STRU.POLE | SANTA ROSA MAP HH32 POLES | 049 | SONOMA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 119 | 17 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - SILVERADO 2105 - H01-LR1421 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 7325.76
35192039 | ECOP - MONTE RIO 1113 - H04-LR320 | 08/07/2020 | 119554057 | 08/03/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2022 | ED.44-HH20090000.STRU.POLE | SANTA ROSA HH2009 POLES | 049 | SONOMA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 119 | 17 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - MONTE RIO 1113 - H04-LR320 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 2341.42
35192040 | ECOP - MONTE RIO 1113 - H08-LR477 | 08/07/2020 | 119554091 | 08/03/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2022 | ED.44-HH20150000.STRU.POLE | SANTA ROSA HH2015 POLES | 049 | SONOMA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 119 | 17 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - MONTE RIO 1113 - H08-LR477 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 2181.4
35192041 | ECOP - WEST POINT 1101 - H01-LR4706 | 08/07/2020 | 119552184 | 08/03/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2022 | ED.95-J292400000.STRU.POLE | MOTHER LODE J2924 POLES | 003 | AMADOR COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 119 | 17 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - WEST POINT 1101 - H01-LR4706 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 7260.49
35192043 | ECOP - PINE GROVE 1102 - H03-LR13438 PH1 | 08/07/2020 | 119553911 | 08/03/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2022 | ED.95-J271700000.STRU.POLE | MOTHER LODE J2717 POLES | 003 | AMADOR COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 119 | 17 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - PINE GROVE 1102 - H03-LR13438 Ph1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 4267.49
35192044 | ECOP - PINE GROVE 1102 - H03-LR13438 PH2 | 08/07/2020 | 119553912 | 08/03/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2022 | ED.95-J271700000.STRU.POLE | MOTHER LODE J2717 POLES | 003 | AMADOR COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 119 | 17 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - PINE GROVE 1102 - H03-LR13438 Ph2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 4635.04
35192045 | ECOP - STANISLAUS 1702 - H02-LR75348 | 08/07/2020 | 119553913 | 08/03/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2022 | ED.95-O340500000.STRU.POLE | MOTHER LODE O3405 POLES | 005 | CALAVERAS COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 119 | 17 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - STANISLAUS 1702 - H02-LR75348 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 3454.98
35192046 | ECOP - PINE GROVE 1102 - H04-LR3172 PH1 | 08/07/2020 | 119553919 | 08/03/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2022 | ED.95-L260900000.STRU.POLE | MOTHER LODE L2609 POLES | 003 | AMADOR COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 119 | 17 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - PINE GROVE 1102 - H04-LR3172 Ph1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 5065.23
35192047 | ECOP - PINE GROVE 1102 - H04-LR3172 PH2 | 08/07/2020 | 119554050 | 08/03/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2022 | ED.95-L260900000.STRU.POLE | MOTHER LODE L2609 POLES | 003 | AMADOR COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 119 | 17 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - PINE GROVE 1102 - H04-LR3172 Ph2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 5658.69
35192048 | ECOP - PINE GROVE 1102 - H04-LR3172 PH3 | 08/07/2020 | 119554051 | 08/03/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2022 | ED.95-L260900000.STRU.POLE | MOTHER LODE L2609 POLES | 003 | AMADOR COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 119 | 17 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - PINE GROVE 1102 - H04-LR3172 Ph3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 5288.13
35192049 | ECOP - PINE GROVE 1102 - H04-LR3172 PH4 | 08/07/2020 | 119554052 | 08/03/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2022 | ED.95-L260900000.STRU.POLE | MOTHER LODE L2609 POLES | 003 | AMADOR COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 119 | 17 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - PINE GROVE 1102 - H04-LR3172 Ph4 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 4867.44
35192050 | ECOP - WEST POINT 1102 - H01-TS1303 | 08/07/2020 | 119554054 | 08/03/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2022 | ED.95-KK30000000.STRU.POLE | Angels Camp MAP KK30 POLES | 005 | CALAVERAS COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 119 | 17 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - WEST POINT 1102 - H01-TS1303 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 1797.34
35192051 | ECOP - SALT SPRINGS 2102 - H01-LR4796 | 08/07/2020 | 119554056 | 08/03/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2022 | ED.95-MM36200000.STRU.POLE | Angels Camp MAP MM3620 POLES | 005 | CALAVERAS COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 119 | 17 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - SALT SPRINGS 2102 - H01-LR4796 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 2337.96
35192052 | ECOP - WEST POINT 1102 - H05-LR34416 | 08/07/2020 | 119554058 | 08/03/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2022 | ED.95-KK30000000.STRU.POLE | Angels Camp MAP KK30 POLES | 005 | CALAVERAS COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 119 | 17 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - WEST POINT 1102 - H05-LR34416 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 2069.3
35192053 | ECOP-OAKHURST 1103-LR 5120 | 08/07/2020 | 119554059 | 08/03/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2022 | ED.72-0521234000.STRU.POLE | MERCED MAP 0521234 POLES | 022 | MARIPOSA COUNT | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 119 | 17 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP-OAKHURST 1103-LR 5120 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 6333.47
35192054 | ECOP-OAKHURST 1103-LR 5470 | 08/07/2020 | 119554090 | 08/03/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2022 | ED.72-0521100000.STRU.POLE | MERCED MAP 05211 POLES | 022 | MARIPOSA COUNT | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 119 | 17 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP-OAKHURST 1103-LR 5470 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 5841.29
35192280 | ECOP - CLAYTON 2212 - H01-LR2951 | 08/09/2020 | 119556070 | 08/04/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2023 | ED.30-E151800000.STRU.POLE | DIABLO E1518 POLES | 007 | CONTRA COSTA C | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 117 | 16.7143 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - CLAYTON 2212 - H01-LR2951 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 1912.42
35192281 | ECOP - MIDDLETOWN 1101 - H16-LR48212 PH1 | 08/09/2020 | 119556250 | 08/04/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2023 | ED.46-CC30000000.STRU.POLE | UKIAH CC30 POLES | 017 | LAKE COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 117 | 16.7143 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - MIDDLETOWN 1101 - H16-LR48212 Ph1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 1541.97
35192282 | ECOP - MIDDLETOWN 1101 - H16-LR48212 PH2 | 08/09/2020 | 119556300 | 08/04/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2023 | ED.46-CC30000000.STRU.POLE | UKIAH CC30 POLES | 017 | LAKE COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 117 | 16.7143 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - MIDDLETOWN 1101 - H16-LR48212 Ph2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 1541.97
35192283 | ECOP - CALISTOGA 1101 - H04-LR1087 | 08/09/2020 | 119556064 | 08/04/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2023 | ED.42-FF29000000.STRU.POLE | SILVERADO MAP FF29 POLES | 049 | SONOMA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 117 | 16.7143 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - CALISTOGA 1101 - H04-LR1087 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 1541.97
35192284 | ECOP - SILVERADO 2104 - H05-LR726 | 08/09/2020 | 119556691 | 08/04/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2023 | ED.42-EE35170000.STRU.POLE | NAPA MAP EE3517 POLES | 028 | NAPA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 117 | 16.7143 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - SILVERADO 2104 - H05-LR726 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 4329.13
35192285 | ECOP - BRUNSWICK 1106 - H01 - LR2796 PH1 | 08/09/2020 | 119555791 | 08/04/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2023 | ED.22-N101600000.STRU.POLE | NEVADA N1016 POLES | 029 | NEVADA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 117 | 16.7143 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - BRUNSWICK 1106 - H01 - LR2796 Ph | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 1541.97
35192286 | ECOP - BRUNSWICK 1106 - H01 - LR2796 PH2 | 08/09/2020 | 119555811 | 08/04/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2023 | ED.22-N101600000.STRU.POLE | NEVADA N1016 POLES | 029 | NEVADA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 117 | 16.7143 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - BRUNSWICK 1106 - H01 - LR2796 Ph | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 1541.97
35192287 | ECOP - BRUNSWICK 1106 - H02 - CB | 08/09/2020 | 119555883 | 08/04/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2023 | ED.22-N100700000.STRU.POLE | NEVADA N1007 POLES | 029 | NEVADA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 117 | 16.7143 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - BRUNSWICK 1106 - H02 - CB | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 1541.97
35192288 | ECOP - BRUNSWICK 1106 - H04 - LR2416 | 08/09/2020 | 119555953 | 08/04/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2023 | ED.22-O090400000.STRU.POLE | NEVADA O0904 POLES | 029 | NEVADA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 117 | 16.7143 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - BRUNSWICK 1106 - H04 - LR2416 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 1541.97
35192289 | ECOP - BRUNSWICK 1106 - H07 - LR 51484 | 08/09/2020 | 119555969 | 08/04/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2023 | ED.22-O111200000.STRU.POLE | NEVADA O1112 POLES | 029 | NEVADA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 117 | 16.7143 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - BRUNSWICK 1106 - H07 - LR 51484 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35192290 | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 | 08/09/2020 | 119556075 | 08/04/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2023 | ED.21-H392200000.STRU.POLE | EL DORADO H3922 POLES | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 117 | 16.7143 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 1553.55
35192291 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 | 08/09/2020 | 119556091 | 08/04/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2023 | ED.21-I400600000.STRU.POLE | EL DORADO I4006 POLES | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 117 | 16.7143 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 1553.55
35192292 | ECOP - FULTON 1107 - H02-LR604 | 08/09/2020 | 119556108 | 08/04/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2023 | ED.44-GG28000000.STRU.POLE | SANTA ROSA GG28 POLES | 049 | SONOMA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 117 | 16.7143 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - FULTON 1107 - H02-LR604 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 1541.97
35192293 | ECOP - MOLINO 1102 - H03-LR396 PH1 | 08/09/2020 | 119556357 | 08/04/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2023 | ED.44-JJ22090000.STRU.POLE | SANTA ROSA JJ2209 POLES | 049 | SONOMA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 117 | 16.7143 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - MOLINO 1102 - H03-LR396 Ph1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 1573.52
35192294 | ECOP - MOLINO 1102 - H03-LR396 PH2 | 08/09/2020 | 119556373 | 08/04/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2023 | ED.44-JJ22090000.STRU.POLE | SANTA ROSA JJ2209 POLES | 049 | SONOMA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 117 | 16.7143 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - MOLINO 1102 - H03-LR396 Ph2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 1541.97
35192295 | ECOP - RINCON 1103 - H02-LR198 | 08/09/2020 | 119556481 | 08/04/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2023 | ED.44-HH29100000.STRU.POLE | SANTA ROSA HH2910 POLES | 049 | SONOMA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 117 | 16.7143 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - RINCON 1103 - H02-LR198 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 1551.6
35192296 | ECOP - PINE GROVE 1102 - H06-LR83098 | 08/09/2020 | 119556406 | 08/04/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2023 | ED.95-L280100000.STRU.POLE | MOTHER LODE L2801 POLES | 003 | AMADOR COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 117 | 16.7143 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - PINE GROVE 1102 - H06-LR83098 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 1706.73
35192297 | ECOP - PINE GROVE 1102 - H07-CB | 08/09/2020 | 119556415 | 08/04/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2023 | ED.95-L261200000.STRU.POLE | MOTHER LODE L2612 POLES | 003 | AMADOR COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 117 | 16.7143 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - PINE GROVE 1102 - H07-CB | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 1703.51
35192298 | ECOP - SALT SPRINGS 2102 - H02-LR37300 | 08/09/2020 | 119556492 | 08/04/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2023 | ED.95-NN36010000.STRU.POLE | Angels Camp MAP NN3601 POLES | 005 | CALAVERAS COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 117 | 16.7143 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - SALT SPRINGS 2102 - H02-LR37300 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 1549.69
35192299 | ECOP - SALT SPRINGS 2102 - H04-LR97924 | 08/09/2020 | 119556522 | 08/04/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2023 | ED.95-MM36190000.STRU.POLE | Angels Camp MAP MM3619 POLES | 005 | CALAVERAS COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 117 | 16.7143 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - SALT SPRINGS 2102 - H04-LR97924 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 1541.97
35192300 | ECOP - WEST POINT 1101 - H04-TSL3355 | 08/09/2020 | 119556696 | 08/04/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2023 | ED.95-I302300000.STRU.POLE | MOTHER LODE I3023 POLES | 003 | AMADOR COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 117 | 16.7143 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - WEST POINT 1101 - H04-TSL3355 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 1950.41
35192301 | ECOP - WEST POINT 1102 - H06-LR36676 | 08/09/2020 | 119556698 | 08/04/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2023 | ED.95-L301300000.STRU.POLE | MOTHER LODE L3013 POLES | 005 | CALAVERAS COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 117 | 16.7143 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - WEST POINT 1102 - H06-LR36676 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 1541.97
35192302 | ECOP - WEST POINT 1102 - H07-LR93116 | 08/09/2020 | 119556928 | 08/04/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2023 | ED.95-LL29000000.STRU.POLE | MOTHER LODE MAP LL29 POLES | 005 | CALAVERAS COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 117 | 16.7143 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - WEST POINT 1102 - H07-LR93116 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 1541.97
35192303 | ECOP - MARIPOSA 2101 - H01-LR10170 PH1 | 08/09/2020 | 119556206 | 08/04/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2023 | ED.72-05202A0000.STRU.POLE | MERCED MAP 05202A POLES | 022 | MARIPOSA COUNT | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 117 | 16.7143 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - MARIPOSA 2101 - H01-LR10170 Ph1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 1541.97
35192304 | ECOP - MARIPOSA 2101 - H01-LR10170 PH2 | 08/09/2020 | 119556233 | 08/04/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2023 | ED.72-05202A0000.STRU.POLE | MERCED MAP 05202A POLES | 022 | MARIPOSA COUNT | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 117 | 16.7143 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - MARIPOSA 2101 - H01-LR10170 Ph2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 1541.97
35192305 | ECOP - MIWUK 1702 - H01-LR8130 | 08/09/2020 | 119556333 | 08/04/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2023 | ED.91-T360900000.STRU.POLE | STANISLAUS T3609 POLES | 055 | TUOLUMNE COUNT | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 117 | 16.7143 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - MIWUK 1702 - H01-LR8130 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 1541.97
35192683 | BR-05-15-W CLARK-5 PARB | 08/11/2020 | 119601767 | 08/11/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 08/27/2021 | ED.17-T330400000.STRU.POLE | PARADISE T3304 POLES | 004 | BUTTE COUNTY | 5786123 | 08W Rebuild | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 115 | 16.4286 | ESTS | 2 | E470 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 68678.89
35193679 | GUERNSEY 1101 LR 92702 RECOND 2060FT | 08/20/2020 | 113763315 | 10/25/2017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/31/2021 | ED.25266.1101 | GUERNSEY 1101 | 016 | KINGS COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2020 | # | OPEN | 106 | 15.1429 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 6752.9
35193844 | MAGUNDEN 1105 - RECONDUCTOR | 08/20/2020 | 119637556 | 08/19/2020 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/30/2022 | ED.66-2928351000.STRU.POLE | KERN 2928351 POLES | 015 | KERN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2020 | # | OPEN | 106 | 15.1429 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 1019.94
35193883 | BUCOCAMPTUG 622 PEARSON RD PARADISE | 08/19/2020 | 119640259 | 08/19/2020 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/27/2020 | ED.17-T330900000.STRU.POLE | PARADISE T3309 POLES | 004 | BUTTE COUNTY | 5791246 | Butte Rebuild UG TAP 08W | 310.000 | 0.000 | 08W | 2020 | # | OPEN | 107 | 15.2857 | UNSC | 6 | E460 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | INPR | 2020-10-28 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 40926.04
35199560 | ECOP-WEST POINT 1101-H02-LR36674-PH2 | 09/10/2020 | 119666808 | 08/25/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.95-I302400000.STRU.POLE | MOTHER LODE I3024 POLES | 003 | AMADOR COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 85 | 12.1429 | ESTS | 2 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP-WEST POINT 1101-H02-LR36674 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 1541.97
35200008 | BUCOCAMPTUG MOORE RD PARADISE UG SHORT | 09/14/2020 | 119762792 | 09/14/2020 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 01/08/2021 | ED.17-S341100000.STRU.POLE | PARADISE S3411 POLES | 004 | BUTTE COUNTY | 5791246 | Butte Rebuild UG TAP 08W | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 81 | 11.5714 | ESTS | 2 | E460 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 4336.23
35200127 | ECOP - FORESTHILL 1101 - H03-LR50486 | 09/15/2020 | 119768637 | 09/15/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2022 | ED.20-S130400000.STRU.POLE | PLACER S1304 POLES | 031 | PLACER COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 80 | 11.4286 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - FORESTHILL 1101 - H03-LR50486 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 1870.34
35206134 | CWSP - CAMP EVERS 2106 - LR5020 - PH 3.2 | 10/13/2020 | 119896242 | 10/13/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.76-M140800000.STRU.POLE | COAST M1408 POLES | 044 | SANTA CRUZ COU | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 52 | 7.4286 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - CAMP EVERS 2106 - 5020 - PHASE 3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35206135 | CWSP - CAMP EVERS 2106 - LR5020 - PH 3.3 | 10/13/2020 | 119896249 | 10/13/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.76-M140300000.STRU.POLE | COAST M1403 POLES | 044 | SANTA CRUZ COU | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 52 | 7.4286 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - CAMP EVERS 2106 - 5020 - PHASE 3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35206136 | CWSP - CAMP EVERS 2106 - LR5020 - PH 3.4 | 10/13/2020 | 119896480 | 10/13/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.76-M140700000.STRU.POLE | COAST M1407 POLES | 044 | SANTA CRUZ COU | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 52 | 7.4286 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - CAMP EVERS 2106 - 5020 - PHASE 3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35206138 | CWSP - CAMP EVERS 2106 - LR5020 - PH 3.5 | 10/13/2020 | 119896482 | 10/13/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.76-M141600000.STRU.POLE | COAST M1416 POLES | 044 | SANTA CRUZ COU | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 52 | 7.4286 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - CAMP EVERS 2106 - 5020 - PHASE 3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35207102 | KIRKER 2104 - RECONDCUTOR 570 FT | 10/20/2020 | 119921836 | 10/19/2020 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/16/2022 | ED.01445.2104 | KIRKER 2104 | 007 | CONTRA COSTA C | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2020 | # | OPEN | 45 | 6.4286 | UNSE | 1 | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 214.25
35212401 | FRRB - MONTICELLO 1101 CB | 11/08/2020 | 119933522 | 10/21/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.04305.1101 | MONTICELLO 1101 | 028 | NAPA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 26 | 3.7143 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | FRRB - NB NAPA COUNTY | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35212402 | FRRB - MONTICELLO 1101 LR 666 | 11/08/2020 | 119982885 | 11/04/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.04305.1101.RECL | RECLOSERS | 028 | NAPA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 26 | 3.7143 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | FRRB - NB NAPA COUNTY | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35212403 | FRRB - MONTICELLO 1101 LR 654 | 11/08/2020 | 119982889 | 11/04/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.04305.1101.RECL | RECLOSERS | 028 | NAPA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 26 | 3.7143 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | FRRB - NB NAPA COUNTY | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35212404 | FRRB - MONTICELLO 1101 LR 630 | 11/08/2020 | 119982981 | 11/04/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.04305.1101.RECL | RECLOSERS | 028 | NAPA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 26 | 3.7143 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | FRRB - NB NAPA COUNTY | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35212405 | FRRB - MONTICELLO 1101 LR 93384 | 11/08/2020 | 119982987 | 11/04/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.04305.1101.RECL | RECLOSERS | 028 | NAPA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 26 | 3.7143 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | FRRB - NB NAPA COUNTY | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35212406 | FRRB - MONTICELLO 1101 LR 37384 | 11/08/2020 | 119983061 | 11/04/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.04305.1101.RECL | RECLOSERS | 028 | NAPA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 26 | 3.7143 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | FRRB - NB NAPA COUNTY | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35212407 | FRRB - SILVERADO 2102 LR 636 | 11/08/2020 | 119983066 | 11/04/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.04343.2102.RECL | RECLOSERS | 028 | NAPA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 26 | 3.7143 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | FRRB - NB NAPA COUNTY | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35212408 | FRRB - SILVERADO 2102 LR 34959 | 11/08/2020 | 119983069 | 11/04/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.04343.2102.RECL | RECLOSERS | 028 | NAPA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 26 | 3.7143 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | FRRB - NB NAPA COUNTY | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35212409 | FRRB - SILVERADO 2104 LR 645 | 11/08/2020 | 119983129 | 11/04/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.04343.2104.RECL | RECLOSERS | 028 | NAPA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 26 | 3.7143 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | FRRB - NB NAPA COUNTY | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35212410 | FRRB - SILVERADO 2104 LR 708 | 11/08/2020 | 119983145 | 11/04/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.04343.2104.RECL | RECLOSERS | 028 | NAPA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 26 | 3.7143 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | FRRB - NB NAPA COUNTY | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35212411 | FRRB - SILVERADO 2104 LR 722 | 11/08/2020 | 119983147 | 11/04/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.04343.2104.RECL | RECLOSERS | 028 | NAPA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 26 | 3.7143 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | FRRB - NB NAPA COUNTY | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35212412 | FRRB - SILVERADO 2104 LR 37632 | 11/08/2020 | 119983231 | 11/04/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.04343.2104.RECL | RECLOSERS | 028 | NAPA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 26 | 3.7143 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | FRRB - NB NAPA COUNTY | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35212413 | FRRB - SILVERADO 2105 LR 658898 | 11/08/2020 | 119983363 | 11/04/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.04343.2105.RECL | RECLOSERS | 028 | NAPA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 26 | 3.7143 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | FRRB - NB NAPA COUNTY | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35212414 | FRRB - SILVERADO 2105 LR 131568 | 11/08/2020 | 119983432 | 11/04/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.04343.2105.RECL | RECLOSERS | 028 | NAPA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 26 | 3.7143 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | FRRB - NB NAPA COUNTY | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35212415 | FRRB - SILVERADO 2105 LR 167360 | 11/08/2020 | 119983433 | 11/04/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.04343.2105.RECL | RECLOSERS | 028 | NAPA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 26 | 3.7143 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | FRRB - NB NAPA COUNTY | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35212416 | FRRB - CALISTOGA 1102 LR 634 | 11/08/2020 | 119983454 | 11/04/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.04271.1102.RECL | RECLOSERS | 028 | NAPA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 26 | 3.7143 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | FRRB - NB NAPA COUNTY | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35212417 | FRRB - CALISTOGA 1102 LR 769230 | 11/08/2020 | 119983463 | 11/04/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.04271.1102.RECL | RECLOSERS | 028 | NAPA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 26 | 3.7143 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | FRRB - NB NAPA COUNTY | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35212418 | FRRB - FITCH MOUNTAIN 1113 LR 6751 | 11/08/2020 | 119933523 | 10/21/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.04275.1113.RECL | RECLOSERS | 049 | SONOMA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 26 | 3.7143 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | FRRB - SO SONOMA COUNTY | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35212419 | FRRB - DUNBAR 1101 - LR 416 | 11/08/2020 | 119983560 | 11/04/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.04307.1101.RECL | RECLOSERS | 049 | SONOMA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 26 | 3.7143 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | FRRB - SO SONOMA COUNTY | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35212460 | FRRB - RINCON 1101 LR 14605 | 11/08/2020 | 119983565 | 11/04/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.04332.1101.RECL | RECLOSERS | 049 | SONOMA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 26 | 3.7143 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | FRRB - SO SONOMA COUNTY | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35212461 | FRRB - RINCON 1101 LR 663641 | 11/08/2020 | 119983567 | 11/04/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.04332.1101.RECL | RECLOSERS | 049 | SONOMA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 26 | 3.7143 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | FRRB - SO SONOMA COUNTY | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35212462 | FRRB - RINCON 1103 LR 198 | 11/08/2020 | 119983580 | 11/04/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.04332.1103.RECL | RECLOSERS | 049 | SONOMA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 26 | 3.7143 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | FRRB - SO SONOMA COUNTY | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35212463 | FRRB - RINCON 1103 LR 474 | 11/08/2020 | 119983582 | 11/04/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.04332.1103.RECL | RECLOSERS | 049 | SONOMA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 26 | 3.7143 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | FRRB - SO SONOMA COUNTY | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35212464 | FRRB - CALISTOGA 1101 LR 886282 | 11/08/2020 | 119983588 | 11/04/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.44-GG30000000.STRU.POLE | SANTA ROSA GG30 POLES | 049 | SONOMA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 26 | 3.7143 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | FRRB - SO SONOMA COUNTY | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35212465 | FRRB - VACAVILLE 1108 LR 38316 | 11/08/2020 | 119933526 | 10/21/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.06360.1108.RECL | RECLOSERS | 048 | SOLANO COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 26 | 3.7143 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | FRRB - SAC SOLANO COUNTY | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35212466 | FRRB - VACAVILLE 1108 LR 8762 | 11/08/2020 | 119984990 | 11/05/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.06360.1108.RECL | RECLOSERS | 048 | SOLANO COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 26 | 3.7143 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | FRRB - SAC SOLANO COUNTY | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35212467 | FRRB - LAURELES 1111 LR 2020 | 11/08/2020 | 119933604 | 10/21/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.18237.1111.RECL | RECLOSERS | 027 | MONTEREY COUNT | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 26 | 3.7143 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | FRRB - CC MONTEREY COUNTY | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35212468 | FRRB - POINT MORETTI 1101 LR36516 | 11/08/2020 | 119933606 | 10/21/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.08293.1101.RECL | RECLOSERS | 044 | SANTA CRUZ COU | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 26 | 3.7143 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | FRRB - CC SANTA CRUZ COUNTY | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35212469 | FRRB - POINT MORETTI 1101 LR12122 | 11/08/2020 | 119983626 | 11/04/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.08293.1101.RECL | RECLOSERS | 044 | SANTA CRUZ COU | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 26 | 3.7143 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | FRRB - CC SANTA CRUZ COUNTY | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35212470 | FRRB - POINT MORETTI 1101 LR83716 | 11/08/2020 | 119983627 | 11/04/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.08293.1101.RECL | RECLOSERS | 044 | SANTA CRUZ COU | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 26 | 3.7143 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | FRRB - CC SANTA CRUZ COUNTY | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35212471 | FRRB - POINT MORETTI 1101 LR5076 | 11/08/2020 | 119983629 | 11/04/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.08293.1101.SWIT | SWITCHES | 044 | SANTA CRUZ COU | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 26 | 3.7143 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | FRRB - CC SANTA CRUZ COUNTY | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35212472 | FRRB - BIG BASIN 1102 LR5066 | 11/08/2020 | 119983702 | 11/04/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.08284.1102.RECL | RECLOSERS | 044 | SANTA CRUZ COU | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 26 | 3.7143 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | FRRB - CC SANTA CRUZ COUNTY | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35212473 | FRRB - BIG BASIN 1102 LR10254 | 11/08/2020 | 119983704 | 11/04/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.08284.1102.RECL | RECLOSERS | 044 | SANTA CRUZ COU | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 26 | 3.7143 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | FRRB - CC SANTA CRUZ COUNTY | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35212474 | FRRB - BIG BASIN 1102 LR12758 | 11/08/2020 | 119983709 | 11/04/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.08284.1102.RECL | RECLOSERS | 044 | SANTA CRUZ COU | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 26 | 3.7143 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | FRRB - CC SANTA CRUZ COUNTY | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35212475 | FRRB - BIG BASIN 1101 CB | 11/08/2020 | 119983868 | 11/04/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.08284.1101 | BIG BASIN 1101 | 044 | SANTA CRUZ COU | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 26 | 3.7143 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | FRRB - CC SANTA CRUZ COUNTY | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35212476 | FRRB - BIG BASIN 1101 LR5000 | 11/08/2020 | 119985051 | 11/05/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.76-L110000000.STRU.POLE | COAST L11 POLES | 044 | SANTA CRUZ COU | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 26 | 3.7143 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | FRRB - CC SANTA CRUZ COUNTY | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35212477 | FRRB - BIG BASIN 1101 LR10720 | 11/08/2020 | 119983869 | 11/04/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.08284.1101.RECL | RECLOSERS | 044 | SANTA CRUZ COU | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 26 | 3.7143 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | FRRB - CC SANTA CRUZ COUNTY | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35212478 | FRRB - SWIFT 2110 XR332 | 11/08/2020 | 119933730 | 10/21/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.08339.2110.RECL | RECLOSERS | 043 | SANTA CLARA CO | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 26 | 3.7143 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | FRRB - SJ SANTA CLARA COUNTY | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35212479 | FRRB - BIG BEND 1102 CB | 11/08/2020 | 119933732 | 10/21/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.10375.1102 | BIG BEND 1102 | 004 | BUTTE COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 26 | 3.7143 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | FRRB - NV BUTTE COUNTY | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35212480 | FRRB - BIG BEND 1102 LR1972 | 11/08/2020 | 119983950 | 11/04/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.10375.1102.RECL | RECLOSERS | 004 | BUTTE COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 26 | 3.7143 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | FRRB - NV BUTTE COUNTY | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35212481 | FRRB - WYANDOTTE 1103 LR1508 | 11/08/2020 | 119983951 | 11/04/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.10291.1103.RECL | RECLOSERS | 004 | BUTTE COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 26 | 3.7143 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | FRRB - NV BUTTE COUNTY | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35212483 | FRRB - WYANDOTTE 1103 LR1974 | 11/08/2020 | 119983953 | 11/04/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.10291.1103.RECL | RECLOSERS | 004 | BUTTE COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 26 | 3.7143 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | FRRB - NV BUTTE COUNTY | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35212486 | FRRB - KANAKA 1101 CB | 11/08/2020 | 119983955 | 11/04/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.10322.1101 | KANAKA 1101 | 004 | BUTTE COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 26 | 3.7143 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | FRRB - NV BUTTE COUNTY | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35212487 | FRRB - KANAKA 1101 LR1034 | 11/08/2020 | 119983959 | 11/04/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.10322.1101.RECL | RECLOSERS | 004 | BUTTE COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 26 | 3.7143 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | FRRB - NV BUTTE COUNTY | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35212488 | FRRB - KANAKA 1101 LR1406 | 11/08/2020 | 119984001 | 11/04/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.10322.1101.RECL | RECLOSERS | 004 | BUTTE COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 26 | 3.7143 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | FRRB - NV BUTTE COUNTY | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35212489 | FRRB - GIRVAN 1101 LR1330 | 11/08/2020 | 119933733 | 10/21/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.10340.1101.RECL | RECLOSERS | 045 | SHASTA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 26 | 3.7143 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | FRRB - NV SHASTA COUNTY | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35212490 | FRRB - GIRVAN 1101 LR323094 | 11/08/2020 | 119984003 | 11/04/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.10340.1101.RECL | RECLOSERS | 045 | SHASTA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 26 | 3.7143 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | FRRB - NV SHASTA COUNTY | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35212491 | FRRB - SAN JOAQUIN #3 1103 LR5100 | 11/08/2020 | 119933734 | 10/21/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.25253.1103.RECL | RECLOSERS | 020 | MADERA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 26 | 3.7143 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | FRRB - YO MADERA COUNTY | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35212492 | FRRB - AUBERRY 1101 R2845 | 11/08/2020 | 119933735 | 10/21/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.25415.1101.RECL | RECLOSERS | 010 | FRESNO COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 26 | 3.7143 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | FRRB - FR FRESNO COUNTY | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35212493 | FRRB - AUBERRY 1101 R324 | 11/08/2020 | 119984006 | 11/04/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.25415.1101.RECL | RECLOSERS | 010 | FRESNO COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 26 | 3.7143 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | FRRB - FR FRESNO COUNTY | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35212494 | FRRB - AUBERRY 1101 LR37536 | 11/08/2020 | 119984007 | 11/04/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.25415.1101.SWIT | SWITCHES | 010 | FRESNO COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 26 | 3.7143 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | FRRB - FR FRESNO COUNTY | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35212495 | FRRB - AUBERRY 1101 LR233716 | 11/08/2020 | 119985141 | 11/05/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.25415.1101.RECL | RECLOSERS | 010 | FRESNO COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 26 | 3.7143 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | FRRB - FR FRESNO COUNTY | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35212496 | FRRB - HB TRINITY COUNTY | 11/08/2020 | 119933736 | 10/21/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.19241 | LOW GAP | 053 | TRINITY COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 26 | 3.7143 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | FRRB - HB TRINITY COUNTY | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35217267 | TITLE: SH - MARIPOSA 2102 LR 241564 | 11/23/2020 | 120047657 | 11/17/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.25445.2102.RECL | RECLOSERS | 022 | MARIPOSA COUNT | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 11 | 1.5714 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | SH - Mariposa 2102 LR 241564 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35217268 | SH - BUCKS CREEK 1101 CB | 11/23/2020 | 120047659 | 11/17/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.10221.1101 | BUCKS CREEK 1101 | 032 | PLUMAS COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 11 | 1.5714 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | SH - Bucks Creek 1101 CB | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35217269 | SH - MIDDLETOWN 1102 CB | 11/23/2020 | 120048011 | 11/17/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.04314.1102.RECL | RECLOSERS | 017 | LAKE COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 11 | 1.5714 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | SH - Middletown 1102 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35217270 | SH - KONOCTI 1102 LR 965078 | 11/23/2020 | 120048013 | 11/17/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.04331.1102.RECL | RECLOSERS | 017 | LAKE COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 11 | 1.5714 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | SH - Konocti 1101 LR 965078 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35217271 | SH - MIDDLETOWN 1103 LR 830 | 11/23/2020 | 120048017 | 11/17/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.04314.1103.RECL | RECLOSERS | 017 | LAKE COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 11 | 1.5714 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | SH - Middletown 1103 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35217272 | SH - KESWICK 1101 LR 1586 | 11/23/2020 | 120048018 | 11/17/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.10345.1101.RECL | RECLOSERS | 045 | SHASTA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 11 | 1.5714 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | SH - Keswick 1101 LR 1586 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35217273 | SH - UPPER LAKE 1101 CB | 11/23/2020 | 120048019 | 11/17/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.04287.1101 | UPPER LAKE 1101 | 017 | LAKE COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 11 | 1.5714 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | SH - Upper Lake 1101 CB | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35217274 | FRRB - PN DIVISION SAN MATEO COUNTY | 11/23/2020 | 120048101 | 11/17/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.02410.1103 | HALF MOON BAY 1103 | 041 | SAN MATEO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 11 | 1.5714 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | FRRB - PN Division San Mateo County | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
35217275 | FRRB - PN DIVISION SANTA CRUZ COUNTY | 11/23/2020 | 120048103 | 11/17/2020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.02410.1103 | HALF MOON BAY 1103 | 044 | SANTA CRUZ COU | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2020 | # | OPEN | 11 | 1.5714 | UNSE | 1 | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | FRRB - PN Division Santa Cruz County | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
74004771 | DIST WORK FOR SMARTVILLE-NICOLAUS#2-PH#2 | 04/20/2016 | # | #N/A | # | Not assigned | 10 | Created | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/30/2016 | ED.15281.1105.SWIT | SWITCHES | 058 | YUBA COUNTY | 5517127 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 2016 | # | OPEN | 1689 | 241.2857 | UNSE | 1 | E570 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
74007103 | CRESSEY 2104 RECONDUCTOR 2ACSR | 08/08/2016 | 111855150 | 08/08/2016 | # | Not assigned | 40 | Closed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2018 | ED.25470.2104 | CRESSEY 2104 | 024 | MERCED COUNTY | 5517127 | DO 08 - Monthly Forecast Only | 0.000 | 14,792.000 | 08J | 2016 | 09/22/2018 | 2018 | 775 | 110.7143 | CLSD | 12 | E570 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | CRESSEY 2104 RECONDUCTOR PROJECT | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | COMP | 2018-02-05 | 2018-02-05 | COMP | 2018-02-07 | 2018-02-07 | COMP | 2018-02-07 | 2018-02-07 | COMP | 2018-02-07 | 2018-02-08 | COMP | 2018-02-08 | 2018-04-17 | COMP | 2018-04-17 | 2018-04-19 | 2 | 71 | 1132069.33
74011865 | PH.3 - RECON. ECHO SUMMIT 1101 11,600' | 04/26/2017 | 112804948 | 04/26/2017 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 01/29/2020 | ED.15803.1101.SWIT | SWITCHES | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2017 | # | OPEN | 1318 | 188.2857 | UNSE | 1 | E570 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Reconductor Echo Summit 1101 11,600' | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 105886.4
74014860 | R2 REPL OH COND/ ALTERNTE BACKTIE CE2104 | 09/12/2017 | 113241363 | 09/12/2017 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 06/30/2020 | ED.08362.2104 | CAMP EVERS 2104 | 044 | SANTA CRUZ COU | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2017 | # | OPEN | 1179 | 168.4286 | UNSE | 1 | E570 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Repl OH Cond/ Alternate Backtie CE2104 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 13896.52
74015668 | *CANC* RPL OH WIRE ON OTTER-1101 S | 10/19/2017 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 06/28/2019 | ED.07-N031000000.STRU.POLE | MONTEREY N0310 POLES | 027 | MONTEREY COUNT | 5535211 | CWSP SPO - SH 08 | 23,884.000 | 0.000 | 08W | 2017 | 09/05/2019 | 2019 | 686 | 98 | CLSD | 12 | E570 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Deleted/Cancelled projects | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 2019-09-05 | 2019-09-05 | # | 2019-09-05 | 2019-09-05 | # | 2019-09-05 | 2019-09-05 | # | 2019-09-05 | 2019-09-05 | # | 2019-09-05 | 2019-09-05 | # | 2019-09-05 | 2019-09-05 | 0 | 0 | 0
74021903 | CWSP-BRUNSWICK 1105 LR-1030 ZONE | 10/04/2018 | 114736235 | 06/28/2018 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.15248.1105 | BRUNSWICK 1105 | 029 | NEVADA COUNTY | 5535211 | CWSP SPO - SH 08 | 25,191.000 | 25,191.000 | 08W | 2018 | # | OPEN | 792 | 113.1429 | DOCC | 8 | E570 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-BRUNSWICK 1105 LR-1030 ZONE | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2019-07-19 | 2019-07-19 | INPR | 2019-10-10 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | -43665 | 0 | 12418648.93
74021960 | CWSP-BRUNSWICK 1105 LR-32536 ZONE # PH 1 | 10/04/2018 | 114778704 | 07/12/2018 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.15248.1105 | BRUNSWICK 1105 | 029 | NEVADA COUNTY | 5535211 | CWSP SPO - SH 08 | 29,601.000 | 31,023.000 | 08W | 2018 | # | OPEN | 792 | 113.1429 | DOCC | 8 | E570 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-BRUNSWICK 1105 LR-32536 ZONE # PH 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2019-08-02 | 2019-08-02 | INPR | 2019-08-02 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | -43679 | 0 | 15460487
74021961 | CWSP - MIRABEL 02/MONTE RIO 13 - LR 652 | 10/04/2018 | 114705149 | 06/15/2018 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/15/2020 | ED.04209.1102.RECL | RECLOSERS | 049 | SONOMA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 25,170.000 | 08W | 2018 | # | OPEN | 792 | 113.1429 | DOCC | 8 | E570 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP: MIRABEL 1102 / MONTE RIO 1113 LR 6 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 20553477.14
74021962 | *DO NOT USE* CWSP: DIABLO WILDFIRE HARDE | 10/04/2018 | # | #N/A | # | Not assigned | 30 | Technically Completed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/23/2019 | ED.01380.1101 | MORAGA 1101 | 007 | CONTRA COSTA C | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2018 | # | OPEN | 792 | 113.1429 | DCNL | Other | E570 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Deleted/Cancelled projects | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | -3514.57
74021963 | CWSP - OAKLAND K 1102 OCB ZONE | 10/04/2018 | 114592093 | 05/10/2018 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 02/06/2020 | ED.01210.1102 | OAKLAND K 1102 | 001 | ALAMEDA COUNTY | 5535211 | CWSP SPO - SH 08 | 15,088.000 | 14,748.000 | 08W | 2018 | # | OPEN | 792 | 113.1429 | DOCC | 8 | E570 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | 74021963_CWSP OAKLAND K 1102 OCB | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2020-06-02 | 2020-06-02 | COMP | 2020-03-09 | 2020-08-14 | COMP | 2020-08-14 | 2020-08-14 | INPR | 2020-08-14 | 0 | # | 0 | 0 | # | 0 | 0 | 73 | -44057 | 7279881.94
74021964 | X-1104 OH RECOND SKYLINE | 10/04/2018 | # | #N/A | # | Not assigned | 10 | Created | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 03/01/2020 | ED.26-F070700000.STRU.POLE | CENTRAL F0707 POLES | 001 | ALAMEDA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08W | 2018 | # | OPEN | 792 | 113.1429 | DOCC | 8 | E570 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
74022040 | 2019 CALISTOGA 1101 HIGH SPLICE COUNT | 10/08/2018 | 113163209 | 08/16/2017 | # | Not assigned | 30 | Technically Completed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2019 | ED.04271.1101 | CALISTOGA 1101 | 028 | NAPA COUNTY | 5535211 | CWSP SPO - SH 08 | 6,677.000 | 6,677.000 | 08W | 2018 | # | OPEN | 788 | 112.5714 | FICL | 10 | E570 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | 2019 CALISTOGA 1101 HIGH SPLICE COUNT | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2019-03-29 | 2019-03-29 | COMP | 2019-03-31 | 2020-01-23 | COMP | 2020-01-23 | 2020-01-23 | COMP | 2020-01-23 | 2020-01-24 | COMP | 2020-01-24 | 2020-02-25 | COMP | 2020-02-25 | 2020-03-03 | 300 | 40 | 1777051.53
74022302 | ECHO SUMMIT 1101 – REPLACING TREE ATTACH | 10/17/2018 | # | #N/A | # | Not assigned | 10 | Created | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 08/01/2019 | ED.15803.1101.SWIT | SWITCHES | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2018 | # | OPEN | 779 | 111.2857 | UNSE | 1 | E570 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
74022380 | *CANC* BRUNSWICK 1103 LR2200 | 10/22/2018 | 5619362 | 10/22/2018 | # | Not assigned | 25 | Canceled | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | JY | JUNK YARD FL TO HOLD DELETED DATA | 029 | NEVADA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2018 | # | OPEN | 774 | 110.5714 | CNCL | Other | E570 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BRUNSWICK 1103 LR2200 HARDENING | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | COMP | 2020-10-07 | 2020-10-07 | COMP | 2020-10-07 | 2020-10-07 | COMP | 2020-10-07 | 2020-10-07 | 0 | 44111 | 178.07
74022381 | *CANC* CWSP - CAMP EVERS 2106 - 50 | 10/22/2018 | # | #N/A | # | Not assigned | 40 | Closed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/30/2020 | ED.08362.2106 | CAMP EVERS 2106 | 044 | SANTA CRUZ COU | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2018 | 05/03/2020 | 2020 | 559 | 79.8571 | CLSD | 12 | E570 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Deleted/Cancelled projects | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | # | 2020-05-03 | 2020-05-03 | COMP | 2020-04-10 | 2020-04-10 | COMP | 2020-04-10 | 2020-04-10 | COMP | 2020-04-10 | 2020-04-10 | 0 | -23 | 559.82
74022382 | CWSP-COLUMBIA HILL 1101-LR 2212 PH1 | 10/22/2018 | 114798646 | 07/18/2018 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 05/21/2020 | ED.15247.1101.SWIT | SWITCHES | 029 | NEVADA COUNTY | 5535211 | CWSP SPO - SH 08 | 12,627.000 | 12,378.000 | 08W | 2018 | # | OPEN | 774 | 110.5714 | DOCC | 8 | E570 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-COLUMBIA HILL 1101-LR 2212 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2020-05-28 | 2019-12-20 | COMP | 2019-12-27 | 2020-05-28 | COMP | 2020-05-28 | 2020-06-16 | COMP | 2020-06-16 | 2020-06-17 | COMP | 2020-06-17 | 2020-07-01 | COMP | 2020-07-01 | 2020-07-03 | 19 | 17 | 4356544.28
74022383 | CWSP-EL DORADO PH 2102 LR19542 PH 1.0 | 10/22/2018 | 114791963 | 07/17/2018 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.15276.2101.SWIT | SWITCHES | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2018 | # | OPEN | 774 | 110.5714 | UNSE | 1 | E570 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - EL DORADO PH 2101 LR 26000 PH 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 33731.28
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | 10/22/2018 | 114753320 | 07/05/2018 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 03/12/2021 | ED.04275.1113.RECL | RECLOSERS | 049 | SONOMA COUNTY | 5535211 | CWSP SPO - SH 08 | 28,754.000 | 4,200.000 | 08W | 2018 | # | OPEN | 774 | 110.5714 | CONS | 7 | E570 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 5450464.95
74022385 | ECEIVED SIZE CATCWSP-KONOCTI 1102-LR 532 | 10/22/2018 | 114691436 | 06/12/2018 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 11/30/2020 | ED.04331.1102.SWIT | SWITCHES | 017 | LAKE COUNTY | 5535211 | CWSP SPO - SH 08 | 14,918.000 | 0.000 | 08W | 2018 | # | OPEN | 774 | 110.5714 | APPR | 4 | E570 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-KONOCTI 1102-LR 532 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 603940.67
74022386 | *CANC* CWSP - LOS GATOS 1106 - LB4 | 10/22/2018 | 5619500 | 10/22/2018 | # | Not assigned | 30 | Technically Completed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/30/2020 | ED.08202.1106 | LOS GATOS 1106 | 043 | SANTA CLARA CO | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2018 | # | OPEN | 774 | 110.5714 | PROD | Other | E570 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Deleted/Cancelled projects | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | COMP | 2020-06-04 | 2020-06-04 | COMP | 2020-06-04 | 2020-06-04 | COMP | 2020-06-04 | 2020-06-04 | 0 | 43986 | 47277.07
74022387 | CWSP-MIDDLETOWN 1101-TS 1079 | 10/22/2018 | 114701413 | 06/14/2018 | # | Not assigned | 30 | Technically Completed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 11/30/2020 | ED.04314.1101.SWIT | SWITCHES | 017 | LAKE COUNTY | 5535211 | CWSP SPO - SH 08 | 21,915.000 | 20,962.000 | 08W | 2018 | # | OPEN | 774 | 110.5714 | FICL | 10 | E570 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP: MIDDLETOWN 1101 TS 1079 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2019-04-30 | 2019-04-30 | COMP | 2020-04-05 | 2020-04-05 | COMP | 2020-04-05 | 2020-04-05 | COMP | 2020-04-05 | 2020-04-07 | COMP | 2020-04-07 | 2020-04-21 | COMP | 2020-04-21 | 2020-05-04 | 341 | 29 | 5585990.23
74022388 | OCGC CWSP: X-1104 OH RECOND SKYLINE | 10/22/2018 | 114266765 | 02/01/2018 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 03/01/2020 | ED.26-F070700000.STRU.POLE | CENTRAL F0707 POLES | 001 | ALAMEDA COUNTY | 5537523 | X-1104 OH RECOND SKYLINE | 3,677.000 | 8,409.000 | 08W | 2018 | # | OPEN | 774 | 110.5714 | DOCC | 8 | E570 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | OAKLAND X-1104 OH RECOND SKYLINE | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2020-11-05 | 2020-11-05 | COMP | 2020-11-13 | 2020-11-13 | COMP | 2020-11-13 | 2020-11-13 | INPR | 2020-11-13 | 0 | # | 0 | 0 | # | 0 | 0 | 8 | -44148 | 3188269.54
74022389 | CWSP - PARADISE 1106 - OCB & LR 2234 | 10/22/2018 | 114742450 | 06/29/2018 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2019 | ED.10283.1106.SWIT | SWITCHES | 004 | BUTTE COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2018 | # | OPEN | 774 | 110.5714 | UNSE | 1 | E570 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - PARADISE 1106 - OCB & LR 2234 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 21364.3
74022390 | CWSP - SILVERADO 2104- LR722-PH 1A | 10/22/2018 | 114592131 | 05/10/2018 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.04343.2104 | SILVERADO 2104 | 028 | NAPA COUNTY | 5535211 | CWSP SPO - SH 08 | 5,124.000 | 5,124.000 | 08W | 2018 | # | OPEN | 774 | 110.5714 | DOCC | 8 | E570 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - NORTH BAY WILDFIRE HARDENING PROJ | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2020-05-21 | 2020-05-19 | INPR | 2020-05-20 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | -43972 | 0 | 2659331.41
74022391 | *CANC* **DO NOT USE**CWSP - VOLTA 1102 | 10/22/2018 | 12008970 | 05/21/2019 | # | Not assigned | 25 | Canceled | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | JY | JUNK YARD FL TO HOLD DELETED DATA | 045 | SHASTA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2018 | # | OPEN | 774 | 110.5714 | CNCL | Other | E570 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Deleted/Cancelled projects | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | COMP | 2020-10-21 | 2020-10-21 | COMP | 2020-10-21 | 2020-10-21 | COMP | 2020-10-21 | 2020-10-21 | 0 | 44125 | 4711.78
74022614 | CWSP - CAMP FIRE PADSE 1105 QUAIL RD | 11/12/2018 | 115340065 | 11/12/2018 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/07/2018 | JY | JUNK YARD FL TO HOLD DELETED DATA | 004 | BUTTE COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2018 | # | OPEN | 753 | 107.5714 | UNSE | 1 | E570 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Paradise 1105 Rebuild Qual Rd | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
74022615 | CWSP - CAMP FIRE PADSE 1105 PENTZ RD | 11/12/2018 | 115340017 | 11/12/2018 | # | Not assigned | 30 | Technically Completed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/07/2018 | ED.10283.1105.SWIT | SWITCHES | 004 | BUTTE COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2018 | # | OPEN | 753 | 107.5714 | FICL | 10 | E570 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Paradise 1105 Rebuild Pentz Rd | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 551.58
74022620 | *DO NOT USE* RPL OH WIRE ON OTTER-1101 S | 11/07/2018 | # | #N/A | # | Not assigned | 10 | Created | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 06/28/2019 | ED.07-N031000000.STRU.POLE | MONTEREY N0310 POLES | 027 | MONTEREY COUNT | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 2018 | # | OPEN | 758 | 108.2857 | DCNL | Other | E570 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | GRC Electric Dist | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
74022663 | CAMP FIRE RECOND LINE HONEY RN BUTTE 05 | 11/14/2018 | 115345680 | 11/14/2018 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/07/2018 | JY | JUNK YARD FL TO HOLD DELETED DATA | 004 | BUTTE COUNTY | 5535211 | CWSP SPO - SH 08 | 24,559.000 | 0.000 | 08W | 2018 | # | OPEN | 751 | 107.2857 | DOCC | 8 | E570 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Camp Fire Recond Line Honey Rn Butte 05 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2019-05-11 | 2019-05-11 | COMP | 2019-07-11 | 2019-07-11 | COMP | 2019-07-11 | 2019-07-11 | INPR | 2019-07-11 | 0 | # | 0 | 0 | # | 0 | 0 | 61 | -43657 | -978992.66
74022664 | CAMP FIRE RECONDUCTOR LINE DEPOT RD | 11/14/2018 | 115344105 | 11/13/2018 | # | Not assigned | 30 | Technically Completed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/14/2018 | ED.10283.1104.RECL | RECLOSERS | 004 | BUTTE COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 3,000.000 | 08W | 2018 | # | OPEN | 751 | 107.2857 | FICL | 10 | E570 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Camp Fire Reconductor Line Depot Rd | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2020-08-11 | 2020-08-11 | COMP | 2020-08-11 | 2020-08-11 | COMP | 2020-08-11 | 2020-08-11 | COMP | 2020-08-11 | 2020-08-13 | COMP | 2020-08-13 | 2020-09-23 | COMP | 2020-09-23 | 2020-09-23 | 0 | 43 | 95196.57
74022720 | CWSP-CAMP FIRE PADSE 1105 INST BIKE PATH | 11/13/2018 | 115340074 | 11/12/2018 | # | Not assigned | 30 | Technically Completed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/07/2018 | JY | JUNK YARD FL TO HOLD DELETED DATA | 004 | BUTTE COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2018 | # | OPEN | 752 | 107.4286 | FICL | 10 | E570 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Paradise 1106 Rebuild Bike Path | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2019-05-11 | 2019-05-11 | COMP | 2019-06-27 | 2019-06-27 | COMP | 2019-06-27 | 2019-06-27 | INPR | 2020-07-13 | 0 | # | 0 | 0 | # | 0 | 0 | 47 | -43643 | 18134.2
74022721 | CWSP - CAMP FIRE PADSE 1106 BILLIE RD | 11/13/2018 | 115339958 | 11/12/2018 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/07/2018 | JY | JUNK YARD FL TO HOLD DELETED DATA | 004 | BUTTE COUNTY | 5535211 | CWSP SPO - SH 08 | 9,477.000 | 0.000 | 08W | 2018 | # | OPEN | 752 | 107.4286 | DOCC | 8 | E570 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Paradise 1105 Rebuild Bille Rd | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2019-05-14 | 2019-05-14 | COMP | 2019-07-09 | 2019-07-09 | COMP | 2019-07-09 | 2019-07-09 | INPR | 2020-01-15 | 0 | # | 0 | 0 | # | 0 | 0 | 56 | -43655 | 56372.34
74022722 | CWSP-CAMP FIRE PDSE 1104 PEARSON RD | 11/13/2018 | 115342410 | 11/13/2018 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/15/2018 | ED.10283.1105.RECL | RECLOSERS | 004 | BUTTE COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2018 | # | OPEN | 752 | 107.4286 | ESTS | 2 | E570 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Paradise 1104 Rebuild Pearson Rd | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2019-05-12 | 2019-05-12 | COMP | 2019-05-28 | 2019-05-28 | COMP | 2019-05-28 | 2019-05-28 | INPR | 2019-05-28 | 0 | # | 0 | 0 | # | 0 | 0 | 16 | -43613 | 241992.16
74022723 | CWSP - CAMP FIRE PDSE 1106 PONDEROSA WAY | 11/13/2018 | 115342359 | 11/13/2018 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/15/2018 | ED.10283.1105.RECL | RECLOSERS | 004 | BUTTE COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2018 | # | OPEN | 752 | 107.4286 | PEND | 5 | E570 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Paradise 1106 Rebuild South Park Dr | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 62992.31
74024171 | CALISTOGA 1101 HIGH SPLICE COUNT | 02/14/2019 | 113742411 | 10/17/2017 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 10/17/2019 | ED.42-FF30000000.STRU.POLE | SILVERADO FF30 POLES | 028 | NAPA COUNTY | 5535211 | CWSP SPO - SH 08 | 13,780.000 | 13,780.000 | 08W | 2019 | # | OPEN | 659 | 94.1429 | DOCC | 8 | E570 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CALISTOGA 1101 HIGH SPLICE COUNT | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | COMP | 2020-05-13 | 2020-05-13 | INPR | 2020-05-14 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | -43964 | 0 | 3324851.52
74024660 | 2019 CALISTOGA 1101 SUB ORDER | 03/04/2019 | # | #N/A | 74022040 | 2019 CALISTOGA 1101 HIGH SPLICE COUNT | 10 | Created | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | # | ED.04271.1101 | CALISTOGA 1101 | 028 | NAPA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2019 | # | OPEN | 641 | 91.5714 | UNSE | 1 | E570 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
74024661 | CWSP-BRUNSWICK 1105 LR32536 PH1 SUBORDER | 03/04/2019 | # | #N/A | 74021960 | CWSP-BRUNSWICK 1105 LR-32536 ZONE # PH 1 | 10 | Created | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | # | ED.15248.1105 | BRUNSWICK 1105 | 029 | NEVADA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 2019 | # | OPEN | 641 | 91.5714 | UNSE | 1 | E570 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 0
74028021 | CWSP - MIRABEL 02/MONTE RIO 13-LR652 PH2 | 08/14/2019 | 117755928 | 08/14/2019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 02/16/2021 | ED.04209.1102.RECL | RECLOSERS | 049 | SONOMA COUNTY | 5535211 | CWSP SPO - SH 08 | 13,421.000 | 0.000 | 08W | 2019 | # | OPEN | 478 | 68.2857 | CONS | 7 | E570 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP: MIRABEL 1102 / MONTE RIO 1113 LR 6 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | # | 0 | 0 | 0 | 0 | 2959261.08

## ALL CAPITAL ORDERS DATA
Order | Order Description | Notification | Superior Order | Superior Order Description | Status | Status Description | Status Profile | Status Profile Description | Division | Division Description | Created by LANID | Created by | Job Owner LANID | Job Owner | Estimator LANID | Estimator | ADE LANID | ADE | Baseline In-Srvc Dt | Functional Loc | Functional Loc Description | Plant section | Plant Section Description | Summarized Planning | Summarized Planning Description | Estimated Units | Actual Units | MAT | Created On | Created Yr | Closed Date | Closed Yr | User Status | Order Type | MWC | MWC Description | Program | Program Description | Reason Code | Project Definition | Funding ID Category | Funding Identifier | Funding ID Level 1 | Funding Id Level 2 | Current Year Organiz | Next Year Organizati | $
30265250 | *CANC* E 7NXEPCM100685794 RECOND/15*CANC | # | # | Not assigned | 40 | Closed | ECES_CAP | ECES Capital User Status | NU | NORTH COAST | [8 empty] | # | ED | Electric Distribution System | # | Not assigned | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 06/14/2002 | 2002 | 09/05/2007 | 2007 | clsd | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
30293906 | EP G-1110 REPL.12KV, RICH. & EL CERRITO | 100863334 | # | Not assigned | 40 | Closed | ECES_070 | Capital Status w/ Deferred | EB | EAST BAY | [8 empty] | 04/26/2003 | ED.28-D042400000.PRIM.SWIT | BAY D0424 SWITCHES | A2 | AREA 2 | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 12/19/2002 | 2002 | 03/31/2007 | 2007 | clsd | E070 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 457252.74
30296303 | EP LGN CRK2101 RECON 1400' 6C-4/0AL POST | 101218900 | # | Not assigned | 40 | Closed | ECES_CAP | ECES Capital User Status | NV | NORTH VALLEY | [8 empty] | # | ED.14-X210000000.PRIM.SWIT | GLENN X21 SWITCHES | A6 | AREA 6 | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 01/08/2003 | 2003 | 04/09/2005 | 2005 | clsd | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 14977.19
30344683 | E-ANLD WIRE REPLMNT PCKT CANYN GVLE | 101154821 | # | Not assigned | 40 | Closed | ECES_CAP | ECES Capital User Status | NC | NORTH COAST | [8 empty] | # | ED.44-HH21080000.PRIM.RECL | SANTA ROSA HH2108 RECLOSERS | A7 | AREA 7 | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 10/30/2003 | 2003 | 01/29/2005 | 2005 | clsd | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 74527.48
30353232 | EP RECONDUCTOR OCEANO 1106 70 SERIES R | # | 30327286 | THE DOLLARS IN THIS PM HAVE BEEN *CANC | 40 | Closed | ECES_070 | Capital Status w/ Deferred | LP | LOS PADRES | [8 empty] | # | E | UTILITY OPERATIONS ELECTRIC FACILITIES | # | Not assigned | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 12/16/2003 | 2003 | 11/27/2004 | 2004 | clsd | E070 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 571109.08
30353980 | EP REPLACE ANNEALED WIRE ON WILLIAMS1102 | 101243348 | # | Not assigned | 40 | Closed | ECES_CAP | ECES Capital User Status | SA | SACRAMENTO | [8 empty] | # | ED.06205.1102.SWIT | SWITCHES | 006 | COLUSA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 12/19/2003 | 2003 | 02/14/2009 | 2009 | clsd | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 12867.68
30360721 | EP ANNEALED CONDUCTOR - COLLECT SAMPLES | 101268439 | # | Not assigned | 40 | Closed | ECES_CAP | ECES Capital User Status | FR | FRESNO | [8 empty] | # | ED.70-3203110000.PRIM.CAPA | FRESNO 320311 CAPACITOR | A4 | AREA 4 | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 02/02/2004 | 2004 | 12/25/2004 | 2004 | clsd | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | -91.39
30361893 | ROSSMOOR 1101 ANNEALED WIRE,LAF | 101281057 | # | Not assigned | 40 | Closed | ECES_CAP | ECES Capital User Status | DI | DIABLO | [8 empty] | 10/01/2004 | ED.30-D092100000.PRIM.SWIT | DIABLO D0921 SWITCHES | A2 | AREA 2 | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 02/09/2004 | 2004 | 03/26/2005 | 2005 | clsd | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 310446.29
30364024 | EP RECON ANNEALED COND - GRAND ISL 2222 | 101292175 | # | Not assigned | 40 | Closed | ECES_CAP | ECES Capital User Status | SA | SACRAMENTO | [8 empty] | # | ED.50-O220000000.PRIM.SWIT | YOLO O22 SWITCHES | A6 | AREA 6 | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 02/23/2004 | 2004 | 12/30/2006 | 2006 | clsd | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 33977.81
30369586 | EP-BRITTON 1107 KIFER RECONDUCTOR. | 101316648 | # | Not assigned | 40 | Closed | ECES_CAP | ECES Capital User Status | DA | DE ANZA | [8 empty] | # | ED.80-F151600000.PRIM.SWIT | DE ANZA F1516 SWITCHES | A3 | AREA 3 | 5517127 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 03/24/2004 | 2004 | 11/05/2005 | 2005 | clsd | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 7196.02
30370292 | EP GUSTINE 1101 ANNEALED #6CU RECON. | # | # | Not assigned | 40 | Closed | ECES_CAP | ECES Capital User Status | YO | YOSEMITE | [8 empty] | # | ED.91-JJ16000000.PRIM.SWIT | STANISLAUS JJ16 SWITCHES | A5 | AREA 5 | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 03/27/2004 | 2004 | 04/02/2005 | 2005 | clsd | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 21677.72
30371702 | EP TRACY 1106 - REPLACE #6 CU | 101320551 | # | Not assigned | 40 | Closed | ECES_CAP | ECES Capital User Status | ST | STOCKTON | [8 empty] | 06/11/2004 | ED | Electric Distribution System | # | Not assigned | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 04/03/2004 | 2004 | 04/02/2005 | 2005 | clsd | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 27515.75
30372759 | EP - MARTEL 1101 - RECOND 1000' OF 6 CU | 101321730 | # | Not assigned | 40 | Closed | ECES_CAP | ECES Capital User Status | ST | STOCKTON | [8 empty] | 07/02/2004 | ED.95-M232000000.PRIM.FUSE | MOTHER LODE M2320 FUSES | A5 | AREA 5 | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 04/09/2004 | 2004 | 04/02/2005 | 2005 | clsd | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 22948.63
30382513 | EP CALIF. 1112 - RECOND ANNEALED #4C | 101374358 | # | Not assigned | 40 | Closed | ECES_CAP | ECES Capital User Status | FR | FRESNO | [8 empty] | # | ED.70-1420104000.PRIM.SWIT | FRESNO 1420104 SWITCHES | A4 | AREA 4 | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 06/03/2004 | 2004 | 02/10/2007 | 2007 | clsd | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 42762.59
30384168 | EP REPL 250C-715A/W.4TH ST.NORMAL-CHERRY | 101384390 | # | Not assigned | 40 | Closed | ECES_CAP | ECES Capital User Status | NV | NORTH VALLEY | [8 empty] | # | ED.16-T272500000.PRIM.FUSE | CHICO T2725 FUSES | A6 | AREA 6 | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 06/14/2004 | 2004 | 07/29/2006 | 2006 | clsd | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 92486.66
30388338 | EP, RECONDUCTORING PROJECT ON SIL 2105+ | 101403804 | # | Not assigned | 40 | Closed | ECES_CAP | ECES Capital User Status | NB | NORTH BAY | [8 empty] | # | ED | Electric Distribution System | # | Not assigned | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 07/10/2004 | 2004 | 08/11/2007 | 2007 | clsd | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 64624.22
30389521 | EP RECON ANNEALED OH - GRAND ISL 2222 | 101409121 | # | Not assigned | 40 | Closed | ECES_CAP | ECES Capital User Status | SA | SACRAMENTO | [8 empty] | # | ED.50-O220000000.PRIM.FUSE | YOLO O22 FUSES | A6 | AREA 6 | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 07/16/2004 | 2004 | 05/12/2007 | 2007 | clsd | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 26145.63
30391196 | EP ASHLAN 1106 ANNEALED WIRE REPLACEMENT | 101404039 | # | Not assigned | 40 | Closed | ECES_CAP | ECES Capital User Status | FR | FRESNO | [8 empty] | # | ED.70-3203110000.PRIM.SWIT | FRESNO 320311 SWITCHES | A4 | AREA 4 | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 07/27/2004 | 2004 | 09/23/2006 | 2006 | clsd | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 47528.55
30391241 | EP BULLARD 1101 ANNEALED WIRE REPLACEMEN | 101412094 | # | Not assigned | 40 | Closed | ECES_CAP | ECES Capital User Status | FR | FRESNO | [8 empty] | # | ED.70-3211850000.PRIM.CAPA | FRESNO 321185 CAPACITOR | A4 | AREA 4 | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 07/27/2004 | 2004 | 06/25/2005 | 2005 | clsd | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 8499.98
30402965 | EP 400 AIRPORT BLVD, WATSONVILLE | 101443450 | # | Not assigned | 40 | Closed | ECES_CAP | ECES Capital User Status | CC | CENTRAL COAST | [8 empty] | # | ED.76-P192000000.PRIM.SWIT | COAST P1920 SWITCHES | A3 | AREA 3 | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 10/01/2004 | 2004 | 08/05/2006 | 2006 | clsd | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 19604.99
30406987 | EP RECON ANNEALED OH -VACAVILLE 1110 | # | 30389521 | EP RECON ANNEALED OH - GRAND ISL 2222 | 40 | Closed | ECES_CAP | ECES Capital User Status | SA | SACRAMENTO | [8 empty] | # | ED.50-O220000000.PRIM.FUSE | YOLO O22 FUSES | A6 | AREA 6 | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 10/25/2004 | 2004 | 02/10/2007 | 2007 | clsd | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 38971.46
30412095 | 30412095 | 101513616 | # | Not assigned | 40 | Closed | ECES_CAP | ECES Capital User Status | YO | YOSEMITE | [8 empty] | # | ED.91-JJ17000000.PRIM.SWIT | STANISLAUS JJ17 SWITCHES | A5 | AREA 5 | # | Not assigned | 0.000 | 0.000 | 08J | 11/19/2004 | 2004 | 06/17/2006 | 2006 | clsd | E060 | 08 | E Dist Replace OH Asset | CAPRELUG | Capacity/Reliability/Underground Assets | 99 Non IT Program | Not assigned | # | Not assigned | # | # | Not assigned | Not assigned | 16863.9
30414629 | EP TRACY 1106 RECOND 6CU BETHANY RD. | 101566252 | # | Not assigned | 40 | Closed | ECES_070 | Capital Status w/ Deferred | ST | STOCKTON | [8 empty] | 03/18/2005 | ED | Electric Distribution System | # | Not assigned | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 12/09/2004 | 2004 | 02/11/2007 | 2007 | clsd | E070 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 96946.33
30416273 | EP RECOND 6C/LAS PLUMAS RD&LOWER WYANDOT | 101572070 | # | Not assigned | 40 | Closed | ECES_CAP | ECES Capital User Status | NV | NORTH VALLEY | [8 empty] | # | ED.13-H240800000.PRIM.SWIT | OROVILLE H2408 SWITCHES | A6 | AREA 6 | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 12/16/2004 | 2004 | 09/30/2006 | 2006 | clsd | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 55486.71
30419085 | EP, AVENA 1701 1000' RECONDUCTORING | 101579375 | # | Not assigned | 40 | Closed | ECES_CAP | ECES Capital User Status | ST | STOCKTON | [8 empty] | 08/12/2005 | ED | Electric Distribution System | # | Not assigned | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 01/07/2005 | 2005 | 06/17/2006 | 2006 | clsd | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 18941.1
30419539 | EP - RPL ANNEALED COND - PINE GROVE 1102 | 101575011 | # | Not assigned | 40 | Closed | ECES_CAP | ECES Capital User Status | ST | STOCKTON | [8 empty] | # | ED.16375.1102.SWIT | SWITCHES | 003 | AMADOR COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 01/06/2005 | 2005 | 01/26/2008 | 2008 | clsd | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 16769.84
30420618 | HMB AREA OH LINE RECONDUCTORING CO 4155 | 101561093 | # | Not assigned | 40 | Closed | ECES_CAP | ECES Capital User Status | PN | PENINSULA | [8 empty] | # | ED.58-B012000000.PRIM.FUSE | PENINSULA B0120 FUSES | A1 | AREA 1 | 5505513 | PN-OH ANNEALED/DETER CNDCTR: PM MGD | 0.000 | 0.000 | 08J | 01/12/2005 | 2005 | 04/15/2006 | 2006 | clsd | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 22279.32
30420619 | HMB AREA OH LINE RECONDUCTORING CO*CANC | # | 30420618 | HMB AREA OH LINE RECONDUCTORING CO 4155 | 40 | Closed | ECES_CAP | ECES Capital User Status | PN | PENINSULA | [8 empty] | # | ED | Electric Distribution System | # | Not assigned | 5505513 | PN-OH ANNEALED/DETER CNDCTR: PM MGD | 0.000 | 0.000 | 08J | 01/12/2005 | 2005 | 07/02/2005 | 2005 | clsd | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
30420720 | HMB AREA OH LINE RECONDUCTORING CO*CANC | # | 30420618 | HMB AREA OH LINE RECONDUCTORING CO 4155 | 40 | Closed | ECES_070 | Capital Status w/ Deferred | PN | PENINSULA | [8 empty] | # | ED | Electric Distribution System | # | Not assigned | 5505513 | PN-OH ANNEALED/DETER CNDCTR: PM MGD | 0.000 | 0.000 | 08J | 01/12/2005 | 2005 | 07/02/2005 | 2005 | clsd | E070 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
30420721 | HMB AREA OH LINE RECONDUCTORING CO*CANC | # | 30420618 | HMB AREA OH LINE RECONDUCTORING CO 4155 | 40 | Closed | ECES_CAP | ECES Capital User Status | PN | PENINSULA | [8 empty] | # | ED | Electric Distribution System | # | Not assigned | 5505513 | PN-OH ANNEALED/DETER CNDCTR: PM MGD | 0.000 | 0.000 | 08J | 01/12/2005 | 2005 | 07/02/2005 | 2005 | clsd | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
30420722 | HMB AREA OH LINE RECONDUCTORING CO*CANC | # | 30420618 | HMB AREA OH LINE RECONDUCTORING CO 4155 | 40 | Closed | ECES_070 | Capital Status w/ Deferred | PN | PENINSULA | [8 empty] | # | ED | Electric Distribution System | # | Not assigned | 5505513 | PN-OH ANNEALED/DETER CNDCTR: PM MGD | 0.000 | 0.000 | 08J | 01/12/2005 | 2005 | 07/02/2005 | 2005 | clsd | E070 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
30420723 | HMB AREA OH LINE RECONDUCTORING CO*CANC | # | 30420618 | HMB AREA OH LINE RECONDUCTORING CO 4155 | 40 | Closed | ECES_CAP | ECES Capital User Status | PN | PENINSULA | [8 empty] | # | ED | Electric Distribution System | # | Not assigned | 5505513 | PN-OH ANNEALED/DETER CNDCTR: PM MGD | 0.000 | 0.000 | 08J | 01/12/2005 | 2005 | 07/02/2005 | 2005 | clsd | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
30423225 | EP SPRINGFIELD RD REP CU WELD WATSONVILL | 101600084 | # | Not assigned | 40 | Closed | ECES_CAP | ECES Capital User Status | CC | CENTRAL COAST | [8 empty] | 05/27/2005 | ED.76-R201600000 | COAST MAP R2016 | # | Not assigned | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 01/26/2005 | 2005 | 05/15/2010 | 2010 | clsd | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 51033.25
30423284 | EP 78 LOGAN LN,ATH ANNEALED COND | 101600112 | # | Not assigned | 40 | Closed | ECES_CAP | ECES Capital User Status | PN | PENINSULA | [8 empty] | # | ED.58-D091700000.PRIM.SWIT | PENINSULA D0917 SWITCHES | A1 | AREA 1 | 5505513 | PN-OH ANNEALED/DETER CNDCTR: PM MGD | 0.000 | 0.000 | 08J | 01/26/2005 | 2005 | 03/04/2006 | 2006 | clsd | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 5033.79
30428902 | EP REPL ANNEALED 6C W 4/0AL/LEORA CRT CH | 101622988 | # | Not assigned | 40 | Closed | ECES_CAP | ECES Capital User Status | NV | NORTH VALLEY | [8 empty] | # | ED.16-S262000000.PRIM.FUSE | CHICO S2620 FUSES | A6 | AREA 6 | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 02/28/2005 | 2005 | 02/10/2007 | 2007 | clsd | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 38969.1
30428913 | E-RECOND. ANNEALED 6C OH CHALK HL + | 101622462 | # | Not assigned | 40 | Closed | ECES_070 | Capital Status w/ Deferred | NC | NORTH COAST | [8 empty] | 09/01/2005 | ED.44-FF26A00000.PRIM.FUSE | SANTA ROSA FF26A FUSES | A7 | AREA 7 | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 7,300.000 | 08J | 02/28/2005 | 2005 | 05/15/2010 | 2010 | clsd | E070 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 224228.69
30430681 | MENLO 402 REPLACE ANNEALED OH LINE | 101631257 | # | Not assigned | 40 | Closed | ECES_CAP | ECES Capital User Status | PN | PENINSULA | [8 empty] | # | ED.58-E090100000.PRIM.SWIT | PENINSULA E0901 SWITCHES | A1 | AREA 1 | 5505513 | PN-OH ANNEALED/DETER CNDCTR: PM MGD | 0.000 | 0.000 | 08J | 03/09/2005 | 2005 | 04/29/2006 | 2006 | clsd | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 95117.07
30435799 | EP ANNEALED WIRE REPL. COALINGA #1 1107 | 101615019 | # | Not assigned | 40 | Closed | ECES_CAP | ECES Capital User Status | FR | FRESNO | [8 empty] | # | ED.70 | FRESNO DISTRICT | A4 | AREA 4 | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 04/07/2005 | 2005 | 04/07/2007 | 2007 | clsd | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 14866.18
30435840 | EP REPL. ANNEALED WIRE COALINGA # 1105 | 101615574 | # | Not assigned | 40 | Closed | ECES_CAP | ECES Capital User Status | FR | FRESNO | [8 empty] | # | ED.70 | FRESNO DISTRICT | A4 | AREA 4 | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 04/07/2005 | 2005 | 08/25/2007 | 2007 | clsd | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 16662.16
30438790 | EP CAMBRIA 1101 REPL. ANNEALED CONDUCTOR | 101666037 | # | Not assigned | 40 | Closed | ECES_070 | Capital Status w/ Deferred | LP | LOS PADRES | [8 empty] | # | E | UTILITY OPERATIONS ELECTRIC FACILITIES | # | Not assigned | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 04/21/2005 | 2005 | 08/11/2007 | 2007 | clsd | E070 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 397930.96
30438845 | EP GUSTINE 1102 RECONDUCTOR #6 CU | 101619504 | # | Not assigned | 40 | Closed | ECES_CAP | ECES Capital User Status | YO | YOSEMITE | [8 empty] | # | ED.91-KK17190000.PRIM.SWIT | STANISLAUS KK1719 SWITCHES | A5 | AREA 5 | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 04/21/2005 | 2005 | 12/30/2006 | 2006 | clsd | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 38561.52
30439189 | TREE WIRE, FTBRAGG 1101, FUSE 3841 | 101667207 | # | Not assigned | 40 | Closed | ECES_CAP | ECES Capital User Status | NU | NORTH COAST | [8 empty] | # | ED | Electric Distribution System | # | Not assigned | 5517128 | DO 49 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 04/25/2005 | 2005 | 05/09/2009 | 2009 | clsd | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | GRC Electric Dist | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 60348.97
30439506 | E HIGGINS 1109 RECONDUCTOR 3104 FT - GV | 101667018 | # | Not assigned | 40 | Closed | ECES_CAP | ECES Capital User Status | SI | SIERRA | [8 empty] | # | ED.22-Q070000000.PRIM.FUSE | NEVADA Q07 FUSES | A6 | AREA 6 | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 04/26/2005 | 2005 | 07/29/2006 | 2006 | clsd | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 82305.99
30448977 | $76253 RECON ANNEALED # 6C CARNERAS 1103 | 101713393 | # | Not assigned | 40 | Closed | ECES_CAP | ECES Capital User Status | KE | KERN | [8 empty] | # | ED.66-2720500000.PRIM.RECL | KERN 27205 RECLOSERS | A4 | AREA 4 | 5517127 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 06/21/2005 | 2005 | 08/25/2007 | 2007 | clsd | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | GRC Electric Dist | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 43229.8
30454780 | EP RECON 4AR TO 2AR PINION ANDERSON | 101747366 | # | Not assigned | 40 | Closed | ECES_CAP | ECES Capital User Status | NV | NORTH VALLEY | [8 empty] | # | ED.87-R312000000 | SHASTA MAP R3120 | 045 | SHASTA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 07/28/2005 | 2005 | 07/05/2008 | 2008 | clsd | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 63828.16
30460045 | EP TRACY 1106 RECOND ANNEALED 6CU PH #2 | 101746118 | # | Not assigned | 40 | Closed | ECES_070 | Capital Status w/ Deferred | ST | STOCKTON | [8 empty] | 03/17/2006 | ED.93 | STOCKTON DISTRICT | A5 | AREA 5 | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 08/29/2005 | 2005 | 01/20/2007 | 2007 | clsd | E070 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 101296.66
30460698 | R ELM, RECOND., 60681 HWY 271 + | 101777457 | # | Not assigned | 40 | Closed | ECES_CAP | ECES Capital User Status | NN | NORTH COAST | [8 empty] | # | ED.34-LL20000000.PRIM.COND | GARBERVILLE LL20 CONDUCTOR | A7 | AREA 7 | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 09/01/2005 | 2005 | 02/10/2007 | 2007 | clsd | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 24450.34
30460800 | EP OCEANO REPL. ANNEAL OC 1101,22ND,HWY1 | 101777091 | # | Not assigned | 40 | Closed | ECES_070 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 11/09/2007 | E | UTILITY OPERATIONS ELECTRIC FACILITIES | # | Not assigned | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 09/01/2005 | 2005 | 08/18/2018 | 2018 | clsd | E070 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 815660.62
30460890 | HARRINGTON RD RECON #8CW W /6C WATS | 101752364 | # | Not assigned | 40 | Closed | ECES_CAP | ECES Capital User Status | # | Not assigned | [8 empty] | 03/28/2008 | ED.76-R210300000 | COAST MAP R2103 | # | Not assigned | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 09/02/2005 | 2005 | 08/27/2011 | 2011 | clsd | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 110849.36
30460892 | RECONDUC LR 5028 ZONE,1500', OC 1101R | 101777102 | # | Not assigned | 40 | Closed | ECES_070 | Capital Status w/ Deferred | LP | LOS PADRES | [8 empty] | # | E | UTILITY OPERATIONS ELECTRIC FACILITIES | # | Not assigned | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 09/02/2005 | 2005 | 07/29/2006 | 2006 | clsd | E070 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 26296.05
30461360 | HMB AREA OH LINE RECONDUCTORING CO 4155 | # | 30420618 | HMB AREA OH LINE RECONDUCTORING CO 4155 | 40 | Closed | ECES_CAP | ECES Capital User Status | PN | PENINSULA | [8 empty] | # | ED.58-F040200000.PRIM.FUSE | PENINSULA F0402 FUSES | A1 | AREA 1 | 5505513 | PN-OH ANNEALED/DETER CNDCTR: PM MGD | 0.000 | 0.000 | 08J | 09/07/2005 | 2005 | 03/17/2007 | 2007 | clsd | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 48398.85
30461361 | HMB AREA OH LINE RECONDUCTORING CO 6129 | # | 30420618 | HMB AREA OH LINE RECONDUCTORING CO 4155 | 40 | Closed | ECES_070 | Capital Status w/ Deferred | PN | PENINSULA | [8 empty] | # | ED | Electric Distribution System | # | Not assigned | 5505513 | PN-OH ANNEALED/DETER CNDCTR: PM MGD | 0.000 | 0.000 | 08J | 09/07/2005 | 2005 | 12/11/2010 | 2010 | clsd | E070 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 87175.74
30461362 | HMB AREA OH LINE RECONDUCTORING CO 4155 | # | 30420618 | HMB AREA OH LINE RECONDUCTORING CO 4155 | 40 | Closed | ECES_070 | Capital Status w/ Deferred | PN | PENINSULA | [8 empty] | # | ED.58-B021700000.PRIM.FUSE | PENINSULA B0217 FUSES | A1 | AREA 1 | 5505513 | PN-OH ANNEALED/DETER CNDCTR: PM MGD | 0.000 | 0.000 | 08J | 09/07/2005 | 2005 | 05/19/2007 | 2007 | clsd | E070 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 45992.87
30461363 | HMB AREA OH LINE RECONDUCTORING CO 6127 | # | 30420618 | HMB AREA OH LINE RECONDUCTORING CO 4155 | 40 | Closed | ECES_070 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | # | ED | Electric Distribution System | # | Not assigned | 5505513 | PN-OH ANNEALED/DETER CNDCTR: PM MGD | 0.000 | 0.000 | 08J | 09/07/2005 | 2005 | 01/16/2010 | 2010 | clsd | E070 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 136221.93
30461364 | OC1 HMB AREA OH LINE RECONDCTRG CO 6075 | # | 30420618 | HMB AREA OH LINE RECONDUCTORING CO 4155 | 40 | Closed | ECES_070 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | # | ED | Electric Distribution System | # | Not assigned | 5505513 | PN-OH ANNEALED/DETER CNDCTR: PM MGD | 0.000 | 0.000 | 08J | 09/07/2005 | 2005 | 06/25/2011 | 2011 | clsd | E070 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 181445.69
30461758 | (RS) EP REFRAME GI 2223 PHASE 4 (K) | 101780377 | # | Not assigned | 40 | Closed | ECES_CAP | ECES Capital User Status | SA | SACRAMENTO | [8 empty] | # | ED.50-P230000000.PRIM.FUSE | YOLO P23 FUSES | A6 | AREA 6 | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 09/09/2005 | 2005 | 11/03/2007 | 2007 | clsd | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 52441.28
30461759 | (RS) EP REFRAME GI 2223 PHASE 5 | 101782334 | # | Not assigned | 40 | Closed | ECES_CAP | ECES Capital User Status | SA | SACRAMENTO | [8 empty] | # | ED.50-P230000000.PRIM.SWIT | YOLO P23 SWITCHES | A6 | AREA 6 | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 09/09/2005 | 2005 | 11/03/2007 | 2007 | clsd | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 90206.42
30461826 | (RS) EP REFRAME GI 2223 PHASE 6 | 101782353 | # | Not assigned | 40 | Closed | ECES_CAP | ECES Capital User Status | SA | SACRAMENTO | [8 empty] | # | ED.06246.2222.SWIT | SWITCHES | # | Not assigned | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 09/09/2005 | 2005 | 05/10/2008 | 2008 | clsd | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 68786.8
30461829 | (RS) EP FRAME GI 2223 PHASE 7 (K) | 101782425 | # | Not assigned | 40 | Closed | ECES_CAP | ECES Capital User Status | SA | SACRAMENTO | [8 empty] | # | ED.50-P230400000.PRIM.SWIT | YOLO P2304 SWITCHES | A6 | AREA 6 | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 09/09/2005 | 2005 | 12/01/2007 | 2007 | clsd | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 73425.61
30462775 | 9G REPL ANNEALED 6C/RD "R"&RD41 WILLOWS | 101791418 | # | Not assigned | 40 | Closed | ECES_CAP | ECES Capital User Status | NV | NORTH VALLEY | [8 empty] | # | ED.14-X210000000.PRIM.SWIT | GLENN X21 SWITCHES | A6 | AREA 6 | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 09/15/2005 | 2005 | 04/07/2007 | 2007 | clsd | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 190959.99
30466930 | RECONDUCTOR FIREBAUGH 1102 | 101807108 | # | Not assigned | 40 | Closed | ECES_CAP | ECES Capital User Status | YO | YOSEMITE | [8 empty] | # | ED.72-1114000000 | YOSEMITE MAP 1114 | # | Not assigned | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 10/11/2005 | 2005 | 07/05/2008 | 2008 | clsd | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 54407.12
30472372 | RECONDUCTOR ANNEALED #2 COPPER | 101834989 | # | Not assigned | 40 | Closed | ECES_CAP | ECES Capital User Status | YO | YOSEMITE | [8 empty] | # | ED.72 | YOSEMITE DISTRICT | A5 | AREA 5 | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 11/10/2005 | 2005 | 04/21/2007 | 2007 | clsd | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 84009.82
30474502 | *CANC*E RECONDUCTOR 3200-FT #6CU CA*CANC | # | # | Not assigned | 40 | Closed | ECES_CAP | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2010 | ED.11-O2125D0000.PRIM.SWIT | MARYSVILLE O2125D SWITCHES | A6 | AREA 6 | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 11/28/2005 | 2005 | 11/03/2010 | 2010 | clsd | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
30475296 | REPL ANNEALED CU ATW 1106, BUHACH, ATW | # | 30324189 | *CANC* REPL ANNEALED CU ATW 1106, B*CANC | 40 | Closed | ECES_CAP | ECES Capital User Status | YO | YOSEMITE | [8 empty] | # | ED.72 | YOSEMITE DISTRICT | A5 | AREA 5 | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 12/01/2005 | 2005 | 06/25/2011 | 2011 | clsd | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 64080.06
30477342 | $86766 RECON 5340FT 4C MIDWAY 1102 | 101906463 | # | Not assigned | 40 | Closed | ECES_070 | Capital Status w/ Deferred | KE | KERN | [8 empty] | # | ED.66-2923500000.PRIM.SWIT | KERN 29235 SWITCHES | A4 | AREA 4 | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 12/14/2005 | 2005 | 05/19/2007 | 2007 | clsd | E070 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 70578.26
30480222 | E HIGGINS 1109 RECONDUCTOR 9600 FT | 101885038 | # | Not assigned | 40 | Closed | ECES_CAP | ECES Capital User Status | SI | SIERRA | [8 empty] | # | ED.22-P070000000.PRIM.SWIT | NEVADA P07 SWITCHES | A6 | AREA 6 | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 01/06/2006 | 2006 | 04/28/2007 | 2007 | clsd | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 189621.8
30484485 | EP RECOND 1460FT OH WAYFARER CT GV | 101934949 | # | Not assigned | 40 | Closed | ECES_CAP | ECES Capital User Status | SI | SIERRA | [8 empty] | # | ED.22-Q081900000.PRIM.RECL | NEVADA Q0819 RECLOSERS | A6 | AREA 6 | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 01/25/2006 | 2006 | 08/25/2007 | 2007 | clsd | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 71214.94
30485248 | RECONDUCTOR MENDOTA 1104 | 101934207 | # | Not assigned | 40 | Closed | ECES_CAP | ECES Capital User Status | YO | YOSEMITE | [8 empty] | # | ED.72-1220000000.PRIM.SWIT | YOSEMITE 1220 SWITCHES | A5 | AREA 5 | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 01/30/2006 | 2006 | 04/07/2007 | 2007 | clsd | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 64051.41
30486357 | FQ REPLACE 3800' 6C,LAS PLUMAS RD,ORO | 101943972 | # | Not assigned | 40 | Closed | ECES_CAP | ECES Capital User Status | NV | NORTH VALLEY | [8 empty] | 03/24/2006 | ED.13-H240800000.PRIM.FUSE | OROVILLE H2408 FUSES | A6 | AREA 6 | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 02/02/2006 | 2006 | 03/17/2007 | 2007 | clsd | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 115102.05
30507042 | FB RECOND 1100' 6C -4/0A,GUYNN AVE,CHICO | 102031609 | # | Not assigned | 40 | Closed | ECES_CAP | ECES Capital User Status | NV | NORTH VALLEY | [8 empty] | # | ED.16-T261000000.PRIM.FUSE | CHICO T2610 FUSES | A6 | AREA 6 | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 05/23/2006 | 2006 | 05/19/2007 | 2007 | clsd | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 23496.78
30509191 | EP-EB-RECONDUCTOR G-1107 | # | 30507090 | EP OEC ACTIV 5-23-06 RICHMOND MAJ OUTAGE | 40 | Closed | ECES_CAP | ECES Capital User Status | EB | EAST BAY | [8 empty] | 07/13/2007 | ED.28-D041800000 | BAY MAP D0418 | 007 | CONTRA COSTA C | 5725741 | 08-Reconductr G-1107 El Cerrito/Richmond | 0.000 | 0.000 | 08J | 06/06/2006 | 2006 | 12/06/2014 | 2014 | clsd | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | GRC Electric Dist | GRC | ELEC_DIST | Not assigned | Not assigned | 2939707.38
30514054 | KERMAN 1108 ANNLD WIRE, WHITESBR-BELMT | 102061666 | # | Not assigned | 40 | Closed | ECES_070 | Capital Status w/ Deferred | FR | FRESNO | [8 empty] | 11/22/2006 | ED.25271.1108.SWIT | SWITCHES | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 07/06/2006 | 2006 | 10/04/2008 | 2008 | clsd | E070 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 146569.62
30514502 | E HIGGINS 1109 - RECONDUCTOR 1100 FEET | 102053031 | # | Not assigned | 40 | Closed | ECES_CAP | ECES Capital User Status | SI | SIERRA | [8 empty] | # | ED.22-Q070000000.PRIM.RECL | NEVADA Q07 RECLOSERS | A6 | AREA 6 | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 07/09/2006 | 2006 | 08/11/2007 | 2007 | clsd | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 21105.12
30516457 | KERMAN 1108 ANNLD WIRE, BELMT-MCKINLEY | # | 30514054 | KERMAN 1108 ANNLD WIRE, WHITESBR-BELMT | 40 | Closed | ECES_070 | Capital Status w/ Deferred | FR | FRESNO | [8 empty] | # | ED.25271.1108.SWIT | SWITCHES | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 07/20/2006 | 2006 | 09/20/2008 | 2008 | clsd | E070 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 101139.61
30516458 | KRMN 1108 ANNLD WIRE, MCKINLY-SHIELDS | # | 30514054 | KERMAN 1108 ANNLD WIRE, WHITESBR-BELMT | 40 | Closed | ECES_070 | Capital Status w/ Deferred | FR | FRESNO | [8 empty] | # | ED.25271.1108.SWIT | SWITCHES | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 07/20/2006 | 2006 | 12/20/2008 | 2008 | clsd | E070 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 154315.51
30523775 | E, RECOND. ANNL'D 12KV PHILLIPSVILLE + | 102111937 | # | Not assigned | 40 | Closed | ECES_CAP | ECES Capital User Status | NN | NORTH COAST | [8 empty] | # | ED.34 | GARBERVILLE DISTRICT | A7 | AREA 7 | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 08/31/2006 | 2006 | 08/11/2007 | 2007 | clsd | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 63821.21
30525201 | E PC REPLACE ANNEAL WIRE ON TL 1106 | 102120051 | # | Not assigned | 40 | Closed | ECES_CAP | ECES Capital User Status | FR | FRESNO | [8 empty] | # | ED.70 | FRESNO DISTRICT | A4 | AREA 4 | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 09/12/2006 | 2006 | 11/03/2007 | 2007 | clsd | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 41090.55
30527173 | EP RECND 3000' OH 6C & INSTAL 3 FUSES | 102126665 | # | Not assigned | 40 | Closed | ECES_070 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2006 | ED | Electric Distribution System | # | Not assigned | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 09/21/2006 | 2006 | 10/04/2008 | 2008 | clsd | E070 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 61819.06
30529923 | ANNEALED COPPER 08J MWJ CG 2104 | 102141389 | # | Not assigned | 40 | Closed | ECES_CAP | ECES Capital User Status | # | Not assigned | [8 empty] | 02/26/2008 | ED.72 | YOSEMITE DISTRICT | A5 | AREA 5 | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 10/09/2006 | 2006 | 09/01/2012 | 2012 | clsd | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 298318.6
30531403 | OC4 RECONDUCT 4885 #6CU PLUMAS 1102 PH- | 102146759 | # | Not assigned | 40 | Closed | ECES_CAP | ECES Capital User Status | # | Not assigned | [8 empty] | 09/15/2009 | ED.15285.1104.SWIT | SWITCHES | 051 | SUTTER COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 5,001.000 | 08J | 10/18/2006 | 2006 | 01/17/2015 | 2015 | clsd | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Plumas 1102 Project | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 223393.04
30553898 | E PINE GROVE 1102 REPL NG 4CU | 102270521 | # | Not assigned | 40 | Closed | ECES_CAP | ECES Capital User Status | # | Not assigned | [8 empty] | 12/14/2007 | ED.16375.1102.RECL | RECLOSERS | 003 | AMADOR COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 01/31/2007 | 2007 | 11/08/2008 | 2008 | clsd | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 118476.8
30557444 | OC4 E REPL ANNEALD CONDUCTOR GARBERVIL + | 102284237 | # | Not assigned | 40 | Closed | ECES_CAP | ECES Capital User Status | NN | NORTH COAST | [8 empty] | 06/05/2009 | ED | Electric Distribution System | # | Not assigned | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 1,559.000 | 08J | 02/15/2007 | 2007 | 10/16/2010 | 2010 | clsd | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 92724.12
30560340 | PART 1 - ANNEALED #6 MERCED 1114 | 102295549 | # | Not assigned | 40 | Closed | ECES_CAP | ECES Capital User Status | YO | YOSEMITE | [8 empty] | 05/17/2007 | ED.72-0347000000.PRIM.SWIT | YOSEMITE 0347 SWITCHES | # | Not assigned | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 03/02/2007 | 2007 | 01/16/2010 | 2010 | clsd | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 45899.06
30564617 | E RECONDUCTOR OAKHURST 1103 | # | # | Not assigned | 40 | Closed | ECES_070 | Capital Status w/ Deferred | YO | YOSEMITE | [8 empty] | # | ED.25442.1103.SWIT | SWITCHES | # | Not assigned | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 03/22/2007 | 2007 | 04/05/2008 | 2008 | clsd | E070 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
30569593 | E HIGGINS 1109 RECONDUCTOR 3,000 FT. | 102328966 | # | Not assigned | 40 | Closed | ECES_CAP | ECES Capital User Status | # | Not assigned | [8 empty] | # | ED.15269.1109.SWIT | SWITCHES | 029 | NEVADA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 04/13/2007 | 2007 | 11/08/2008 | 2008 | clsd | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 74960.26
30569934 | E REPLACE DETERIORATED CONDUCTOR | 102329661 | # | Not assigned | 40 | Closed | ECES_CAP | ECES Capital User Status | # | Not assigned | [8 empty] | 09/24/2007 | ED | Electric Distribution System | # | Not assigned | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 04/16/2007 | 2007 | 06/25/2011 | 2011 | clsd | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 37153.42
30569936 | *CANC* E REPLACE DETERIORATED CONDU*CANC | 102330186 | # | Not assigned | 40 | Closed | ECES_CAP | ECES Capital User Status | SI | SIERRA | [8 empty] | # | ED | Electric Distribution System | # | Not assigned | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 04/16/2007 | 2007 | 02/02/2008 | 2008 | clsd | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
30570203 | E RECOND BTWN SUISUN & PACIFICA | 102258211 | # | Not assigned | 40 | Closed | ECES_CAP | ECES Capital User Status | # | Not assigned | [8 empty] | 06/01/2007 | ED.08348.1107.SWIT | SWITCHES | 043 | SANTA CLARA CO | 5517127 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 04/17/2007 | 2007 | 01/16/2010 | 2010 | clsd | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 37646.5
30582041 | EP RECON 3854FT - KERN OIL 1108 BKSFLD | 102376800 | # | Not assigned | 40 | Closed | ECES_070 | Capital Status w/ Deferred | KE | KERN | [8 empty] | 04/08/2008 | ED.66-2827366000 | KERN MAP 2827366 | A4 | AREA 4 | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 06/18/2007 | 2007 | 08/08/2015 | 2015 | clsd | E070 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 244209.11
30582504 | *CANC* R2 E RECOND ANNEALED 2C.SHA*CANC | 102377865 | # | Not assigned | 40 | Closed | ECES_CAP | ECES Capital User Status | KE | KERN | [8 empty] | # | ED | Electric Distribution System | # | Not assigned | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 06/20/2007 | 2007 | 11/02/2007 | 2007 | clsd | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
30590158 | E RECONDUCTORING PART OF TAPLIN RD | # | # | Not assigned | 40 | Closed | ECES_CAP | ECES Capital User Status | NB | NORTH BAY | [8 empty] | # | ED | Electric Distribution System | # | Not assigned | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 07/29/2007 | 2007 | 11/20/2007 | 2007 | clsd | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
30590246 | OC4 E REPLACE 6C CONDUCTOR HARTER 1102 | 102409386 | # | Not assigned | 40 | Closed | ECES_CAP | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2007 | ED | Electric Distribution System | # | Not assigned | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 07/29/2007 | 2007 | 05/15/2010 | 2010 | clsd | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 147414.99
30595122 | E BACKTIE BET WOLFE1105&STELL1107 | 102425880 | # | Not assigned | 40 | Closed | ECES_CAP | ECES Capital User Status | # | Not assigned | [8 empty] | 08/21/2009 | ED | Electric Distribution System | # | Not assigned | 5517127 | DO 08 - Monthly Forecast Only | 1,650.000 | 1,650.000 | 08J | 08/23/2007 | 2007 | 12/11/2011 | 2011 | clsd | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 200130.6
30599005 | OC4 E RECONDUCTOR OH PLACERVILLE 1109 | 102437046 | # | Not assigned | 40 | Closed | ECES_CAP | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2008 | ED | Electric Distribution System | # | Not assigned | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 09/11/2007 | 2007 | 12/11/2010 | 2010 | clsd | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 77135.5
30611263 | OC4 RECONDUCTOR ANNLD WIRE - PT REYES - | # | 80041569 | R7 RECONDUCTOR ANNLD WIRE - PT REYE*CANC | 40 | Closed | ECES_070 | Capital Status w/ Deferred | NB | NORTH BAY | [8 empty] | 10/31/2008 | ED.04229.1101 | OLEMA 1101 | # | Not assigned | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 02/13/2008 | 2008 | 05/15/2010 | 2010 | clsd | E070 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 445709.99
30612543 | *CANC*UPGRADE 4CWC TO 2AR ON ANTLER*CANC | # | 80042412 | UPGRADE 4CWC TO 2AR ON ANTLER 1101 | 40 | Closed | ECES_CAP | ECES Capital User Status | # | Not assigned | [8 empty] | # | ED.10327.1101 | ANTLER 1101 | # | Not assigned | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 02/20/2008 | 2008 | 01/04/2018 | 2018 | clsd | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
30613253 | *CANC* UPGRADE 4CWC TO 2AR ON ANTLE*CANC | # | 80042412 | UPGRADE 4CWC TO 2AR ON ANTLER 1101 | 40 | Closed | ECES_CAP | ECES Capital User Status | NV | NORTH VALLEY | [8 empty] | # | ED.10327.1101 | ANTLER 1101 | # | Not assigned | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 02/26/2008 | 2008 | 04/02/2008 | 2008 | clsd | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
30614573 | ES 1102 REPL 5420FT DETER'D 4AR TO397 | # | 80041275 | (UNC) RES 1102 REPL 5420 FT DETERIOR | 40 | Closed | ECES_CAP | ECES Capital User Status | # | Not assigned | [8 empty] | 09/12/2008 | ED.18273.1102.SWIT | SWITCHES | # | Not assigned | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 03/02/2008 | 2008 | 04/26/2014 | 2014 | clsd | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 150573.24
30616393 | OC4 REPLACE ANNEALED COND -CALPELLA 1 | 102878921 | 80048631 | REPLACE ANNEALED COND -CALPELLA 1 | 40 | Closed | ECES_CAP | ECES Capital User Status | NU | NORTH COAST | [8 empty] | 04/24/2009 | ED | Electric Distribution System | # | Not assigned | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 1,923.000 | 08J | 03/07/2008 | 2008 | 10/16/2010 | 2010 | clsd | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 82195.15
30617747 | OC4 PET A 413 REPL ANNEALED CONDUCTOR | # | 80047407 | PET A 413 REPL ANNEALED CONDUCTOR | 40 | Closed | ECES_CAP | ECES Capital User Status | NC | NORTH COAST | [8 empty] | # | ED.04212.0411.SWIT | SWITCHES | # | Not assigned | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 03/13/2008 | 2008 | 06/25/2011 | 2011 | clsd | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 122386
30622211 | RECON CAMBRIA 1101 &HEARST CASTLE | # | 80053008 | C *CANC | 40 | Closed | ECES_070 | Capital Status w/ Deferred | LP | LOS PADRES | [8 empty] | 12/30/2008 | ED.18277.1101 | CAMBRIA 1101 | # | Not assigned | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 04/04/2008 | 2008 | 03/13/2010 | 2010 | clsd | E070 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 414350.83
30625574 | OC4 E RECONDUCTORING PART OF TAPLIN RD | # | 80005579 | E RECONDUCTORING PART OF TAPLIN RD *CANC | 40 | Closed | ECES_CAP | ECES Capital User Status | NB | NORTH BAY | [8 empty] | 08/04/2009 | ED | Electric Distribution System | # | Not assigned | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 840.000 | 08J | 04/21/2008 | 2008 | 05/15/2010 | 2010 | clsd | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 92929.51
30626409 | OC4 PET A 413 REPL ANNEALED CONDUCTOR+ | # | 80047407 | PET A 413 REPL ANNEALED CONDUCTOR | 40 | Closed | ECES_CAP | ECES Capital User Status | NC | NORTH COAST | [8 empty] | # | ED.04212.0411.SWIT | SWITCHES | # | Not assigned | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 04/25/2008 | 2008 | 11/07/2009 | 2009 | clsd | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 116403.53
30627077 | OC2 MABURY 1102 RECONDUCTOR 1600-FT | # | 80037349 | R2 MABURY 1102 RECONDUCTOR 1600-FT | 40 | Closed | ECES_CAP | ECES Capital User Status | # | Not assigned | [8 empty] | 12/18/2009 | ED.08219.1102 | MABURY 1102 | # | Not assigned | 5535457 | DO 08 - Monthly Forecast Only | 1,724.000 | 1,725.000 | 08J | 04/29/2008 | 2008 | 11/17/2012 | 2012 | clsd | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 332973.49
30630834 | PART 2 OF 2 ANNEALED #6 MERCED 1114 | # | 80055653 | PART 2 OF 2 ANNEALED #6 *CANC | 40 | Closed | ECES_CAP | ECES Capital User Status | # | Not assigned | [8 empty] | # | ED.25280.1114.SWIT | SWITCHES | # | Not assigned | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 05/16/2008 | 2008 | 02/06/2010 | 2010 | clsd | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 60502
30640930 | OC4 REPLACE ANNEALED CONDUCTOR + | # | 80059231 | CNCL R7 REPLACE ANNEALED CONDUCTOR*CANC | 40 | Closed | ECES_CAP | ECES Capital User Status | # | Not assigned | [8 empty] | 10/02/2008 | ED.04256.1102.REGL | REGULATORS | 049 | SONOMA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 3,882.000 | 08J | 07/01/2008 | 2008 | 08/14/2010 | 2010 | clsd | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 166746.64
30642535 | EM E GLORIA RD, GON=REPL WIRE | 103141200 | # | Not assigned | 40 | Closed | ECES_CAP | ECES Capital User Status | # | Not assigned | [8 empty] | # | ED.05-K160000000 | SALINAS MAP K16 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 07/09/2008 | 2008 | 07/21/2018 | 2018 | clsd | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 84204.19
30643381 | OC2 GUADALUPE ANNEALED CNDUCTR | # | 80059937 | CNCL GUADALUPE RELIABILITY | 40 | Closed | ECES_070 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2009 | ED.18267 | SANTA MARIA | # | Not assigned | 5535457 | DO 08 - Monthly Forecast Only | 1,844.000 | 1,844.000 | 08J | 07/11/2008 | 2008 | 07/23/2012 | 2012 | clsd | E070 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 515701.74
30644530 | OC1 REPL ANNEALED CONDUCTOR @ C/O 6125 | # | 80057706 | R1 REPL ANNEALED CONDUCTOR @ C/O 6125 | 40 | Closed | ECES_CAP | ECES Capital User Status | # | Not assigned | [8 empty] | 11/20/2009 | ED.02413.0401.SWIT | SWITCHES | 041 | SAN MATEO COUN | 5505513 | PN-OH ANNEALED/DETER CNDCTR: PM MGD | 3,068.000 | 3,068.000 | 08J | 07/17/2008 | 2008 | 11/13/2010 | 2010 | clsd | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 104239.69
30646198 | OC4 ST TREE WIRE -LITTLE RIVER AIR - | # | 80060211 | CNCL R* INST TREE WIRE -LITTLE RIV*CANC | 40 | Closed | ECES_CAP | ECES Capital User Status | # | Not assigned | [8 empty] | 10/16/2009 | ED.04308.1101.BOOS | BOOSTERS | # | Not assigned | 5517128 | DO 49 - Monthly Forecast Only | 0.000 | 12,228.000 | 08J | 07/24/2008 | 2008 | 08/14/2010 | 2010 | clsd | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | GRC Electric Dist | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 222449.93
30647447 | OC4 REDBUD 1101 & 1102 RECONDUCTOR A - | # | 80060333 | CNCL R* REDBUD 1101 & 1102 RECONDU*CANC | 40 | Closed | ECES_CAP | ECES Capital User Status | # | Not assigned | [8 empty] | 09/04/2009 | ED.04319.1101.SWIT | SWITCHES | 017 | LAKE COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 2,275.000 | 08J | 07/29/2008 | 2008 | 11/10/2012 | 2012 | clsd | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 220516.17
30650204 | OC4 RECOND., PUTAH CREEK 1102-PH 1,2,3 | # | 80058495 | CNCL R4E RECONDUCT ON PUTAH CREEK *CANC | 40 | Closed | ECES_CAP | ECES Capital User Status | # | Not assigned | [8 empty] | 08/17/2009 | ED.06368.1102 | PUTAH CREEK 1102 | # | Not assigned | 5535457 | DO 08 - Monthly Forecast Only | 5,000.000 | 5,000.000 | 08J | 08/11/2008 | 2008 | 12/11/2010 | 2010 | clsd | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 86421.82
30650667 | *CANC* RECONDUCTOR ON PUTAH CREEK *CANC | # | 80058498 | CNCL R4 RECONDUCT PUTAH CREEK 1102-*CANC | 40 | Closed | ECES_CAP | ECES Capital User Status | # | Not assigned | [8 empty] | 07/29/2009 | ED.06368.1102 | PUTAH CREEK 1102 | # | Not assigned | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 08/12/2008 | 2008 | 10/05/2010 | 2010 | clsd | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
30650668 | OC4 RECOND. PUTAH CREEK 1102-PHASE 4,5 | # | 80058499 | CNCL RECONDUCT ON PUTAH CREEK 1102-*CANC | 40 | Closed | ECES_CAP | ECES Capital User Status | # | Not assigned | [8 empty] | 07/23/2009 | ED.06368.1102 | PUTAH CREEK 1102 | # | Not assigned | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 1,800.000 | 08J | 08/12/2008 | 2008 | 10/16/2010 | 2010 | clsd | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 78918.97
30650669 | *CANC* RECONDUCTOR ON PUTAH CREEK *CANC | # | 80058560 | R4E RECONDUCT PUTAH CREEK 1102-PHA*CANC | 40 | Closed | ECES_CAP | ECES Capital User Status | # | Not assigned | [8 empty] | 08/24/2009 | ED.06368.1102 | PUTAH CREEK 1102 | # | Not assigned | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 08/12/2008 | 2008 | 10/05/2010 | 2010 | clsd | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
30650671 | OC4 RECONDUCTOR KNIGHTS LDG 1101- PH-1 | # | 80058762 | CNCL RECONDUCTOR KNIGHTS LDG 1101- *CANC | 40 | Closed | ECES_CAP | ECES Capital User Status | # | Not assigned | [8 empty] | # | ED.06272.1101 | KNIGHTS LANDING 1101 | # | Not assigned | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 08/12/2008 | 2008 | 01/16/2010 | 2010 | clsd | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 22786.67
30650672 | OC4 RECONDUCTOR KNIGHTS LDG 1101-PHASE 2 | # | 80058763 | CNCL RECONDUCTOR KNIGHTS LDG 1101-P*CANC | 40 | Closed | ECES_CAP | ECES Capital User Status | # | Not assigned | [8 empty] | # | ED.06272.1101 | KNIGHTS LANDING 1101 | # | Not assigned | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 08/12/2008 | 2008 | 05/15/2010 | 2010 | clsd | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 30320.88
30650673 | OC4 RECONDUCTOR KNIGHTS LDG 1101-PH-3 | # | 80058764 | CNCL RECONDUCTOR KNIGHTS LDG 1101-P*CANC | 40 | Closed | ECES_CAP | ECES Capital User Status | # | Not assigned | [8 empty] | # | ED.06272.1101 | KNIGHTS LANDING 1101 | # | Not assigned | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 08/12/2008 | 2008 | 12/05/2009 | 2009 | clsd | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 18328.55
30651363 | OC4 RECOND #6CU PLUMAS 1102 PH-2 | # | 30531403 | OC4 RECONDUCT 4885 #6CU PLUMAS 1102 PH- | 40 | Closed | ECES_CAP | ECES Capital User Status | # | Not assigned | [8 empty] | 10/15/2009 | ED.15285.1104.SWIT | SWITCHES | 051 | SUTTER COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 5,365.000 | 5,366.000 | 08J | 08/14/2008 | 2008 | 01/17/2015 | 2015 | clsd | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Plumas 1102 Project | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 306811.81
30651836 | *CANC*R6 RECOND. 2900' 6C,MCARTHUR1*CANC | 103203623 | # | Not assigned | 40 | Closed | ECES_CAP | ECES Capital User Status | # | Not assigned | [8 empty] | 12/22/2008 | ED.87-D510000000 | SHASTA MAP D51 | 045 | SHASTA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 08/18/2008 | 2008 | 12/03/2010 | 2010 | clsd | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
30652301 | OC4 RECOND. 2130' 8C,LOGAN CRK 2101 | 103204608 | # | Not assigned | 40 | Closed | ECES_CAP | ECES Capital User Status | # | Not assigned | [8 empty] | 11/26/2008 | ED.14-X200000000 | GLENN MAP X20 | 011 | GLENN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 2,130.000 | 2,130.000 | 08J | 08/19/2008 | 2008 | 03/20/2010 | 2010 | clsd | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 42045.31
30652909 | RECONDUCTOR KNIGHTS LDG 1101- PHASE | # | 80059045 | CNCL RECONDUCTOR KNIGHTS LDG 1101- P | 40 | Closed | ECES_CAP | ECES Capital User Status | # | Not assigned | [8 empty] | # | ED.06272.1101 | KNIGHTS LANDING 1101 | # | Not assigned | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 08/21/2008 | 2008 | 03/03/2018 | 2018 | clsd | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 14846.8
30661627 | ARCATA 1122 REPLACE ANNEALED WIRE - | # | 80058638 | CNCL ARCATA 1122 REPLACE ANNEALED W*CANC | 40 | Closed | ECES_CAP | ECES Capital User Status | # | Not assigned | [8 empty] | 10/01/2014 | ED.19202.1122.SWIT | SWITCHES | # | Not assigned | 5535457 | DO 08 - Monthly Forecast Only | 2,098.000 | 740.000 | 08J | 09/26/2008 | 2008 | 09/17/2016 | 2016 | clsd | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30661627_ARCATA 1122 REPLACE ANNEALED WI | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 750642.96
30675822 | OC2 RECONDUCTOR PINE GROVE 1102 6250' | # | 80064228 | CNCL PINE GROVE 1102 REPL 6280' ANN*CANC | 40 | Closed | ECES_CAP | ECES Capital User Status | # | Not assigned | [8 empty] | 03/31/2009 | ED.16375.1102 | PINE GROVE 1102 | # | Not assigned | 5535457 | DO 08 - Monthly Forecast Only | 7,164.000 | 6,350.000 | 08J | 12/02/2008 | 2008 | 10/15/2011 | 2011 | clsd | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 479439.78
30676699 | OC2 +REPL COND - GLORIA RD, GONZALES | 103577777 | # | Not assigned | 40 | Closed | ECES_CAP | ECES Capital User Status | # | Not assigned | [8 empty] | 07/01/2010 | ED.18205.2101 | SOLEDAD 2101 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 3,800.000 | 3,800.000 | 08J | 12/05/2008 | 2008 | 10/15/2011 | 2011 | clsd | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 148336.69
30677411 | OC2 +OTTER 1102 - OLD COAST RD, BIG SUR | 103582136 | # | Not assigned | 40 | Closed | ECES_CAP | ECES Capital User Status | # | Not assigned | [8 empty] | 11/06/2009 | ED.18294.1102 | OTTER 1102 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 3,864.000 | 3,864.000 | 08J | 12/09/2008 | 2008 | 04/07/2012 | 2012 | clsd | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 480339.47
30678930 | OC4 BUTTE 1105 - RECOND. 400' W 4/0AL | 103598453 | # | Not assigned | 40 | Closed | ECES_CAP | ECES Capital User Status | # | Not assigned | [8 empty] | 07/14/2009 | ED.10204.1104.SWIT | SWITCHES | 004 | BUTTE COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 326.000 | 0.000 | 08J | 12/16/2008 | 2008 | 05/15/2010 | 2010 | clsd | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 20324.63
30682077 | +OTTER 1102 REP COND PHASE 2 | 103614337 | # | Not assigned | 40 | Closed | ECES_070 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 09/04/2009 | ED.18294.1102 | OTTER 1102 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 4,719.000 | 4,719.000 | 08J | 01/06/2009 | 2009 | 05/27/2012 | 2012 | clsd | E070 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 231632.22
30682629 | OC1 R1 RECONDUCTOR 2000 FT VV1106 SP DAM | 103619072 | # | Not assigned | 40 | Closed | ECES_CAP | ECES Capital User Status | # | Not assigned | [8 empty] | 05/31/2009 | ED.01434.1106 | VALLEY VIEW 1106 | 007 | CONTRA COSTA C | 5535457 | DO 08 - Monthly Forecast Only | 2,000.000 | 2,000.000 | 08J | 01/08/2009 | 2009 | 12/31/2011 | 2011 | clsd | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 220480.4
30685756 | OC4 REPL DET COND ON BELL 1101KEMPER RD | 103656495 | # | Not assigned | 40 | Closed | ECES_CAP | ECES Capital User Status | # | Not assigned | [8 empty] | 06/26/2009 | ED.20-T081800000 | PLACER MAP T0818 | 031 | PLACER COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 4,200.000 | 4,920.000 | 08J | 01/21/2009 | 2009 | 07/02/2011 | 2011 | clsd | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 138337.62
30696477 | OC2 RPLCE ANNEALED CNDUCTR - OROSI 1104 | 103716819 | # | Not assigned | 40 | Closed | ECES_070 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 09/24/2009 | ED.25284.1104.SWIT | SWITCHES | 054 | TULARE COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 1,599.000 | 1,662.000 | 08J | 03/06/2009 | 2009 | 02/09/2013 | 2013 | clsd | E070 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 125681.34
30699459 | OC4 RECONDUCT ANNEALED #6CU CONDUCTOR | 103732805 | # | Not assigned | 40 | Closed | ECES_CAP | ECES Capital User Status | # | Not assigned | [8 empty] | 09/24/2009 | ED.20-W052300000 | PLACER MAP W0523 | 031 | PLACER COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 1,126.000 | 1,126.000 | 08J | 03/19/2009 | 2009 | 08/14/2010 | 2010 | clsd | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 53387.26
30704683 | OC4 REPLACE ANNEALED CNDCTR - PHILO 11 | 103756138 | # | Not assigned | 40 | Closed | ECES_070 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 09/04/2009 | ED.04260.1102.SWIT | SWITCHES | 023 | MENDOCINO COUN | 5535457 | DO 08 - Monthly Forecast Only | 2,380.000 | 2,380.000 | 08J | 04/10/2009 | 2009 | 10/16/2011 | 2011 | clsd | E070 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 187026.37
30706641 | OSOFLACO RD RECONDUCTOR 3500FT | 103766764 | # | Not assigned | 40 | Closed | ECES_CAP | ECES Capital User Status | # | Not assigned | [8 empty] | 07/21/2009 | ED.18267.1109 | SANTA MARIA 1109 | 040 | SAN LUIS OBISP | 5535457 | DO 08 - Monthly Forecast Only | 3,515.000 | 3,515.000 | 08J | 04/21/2009 | 2009 | 03/27/2010 | 2010 | clsd | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 37109.3
30713973 | OC1 REPL COND - AMARILLO RD & SILVERGATE | 103844112 | # | Not assigned | 40 | Closed | ECES_CAP | ECES Capital User Status | # | Not assigned | [8 empty] | 07/30/2009 | ED.24-I130700000.STRU.POLE | MISSION I1307 POLES | 001 | ALAMEDA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 4,740.000 | 08J | 05/29/2009 | 2009 | 08/02/2014 | 2014 | clsd | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 981702.11
30721678 | OC1 RECONDUCTOR 1,100 CKT FT ON THE D-11 | 103903738 | # | Not assigned | 40 | Closed | ECES_CAP | ECES Capital User Status | # | Not assigned | [8 empty] | 11/12/2009 | ED.01204.1105 | OAKLAND D 1105 | 001 | ALAMEDA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 1,100.000 | 1,100.000 | 08J | 07/14/2009 | 2009 | 06/16/2018 | 2018 | clsd | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 176664.86
30726896 | OC4 RECOND. LAKE XING,WYAN 1103 | 103947705 | # | Not assigned | 40 | Closed | ECES_CAP | ECES Capital User Status | # | Not assigned | [8 empty] | 12/17/2009 | ED.10291.1103.SWIT | SWITCHES | 004 | BUTTE COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 2,000.000 | 2,200.000 | 08J | 08/17/2009 | 2009 | 05/14/2011 | 2011 | clsd | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 222163.75
30732184 | OC2 RECONDUCTOR FLORADALE AVE | 103954556 | # | Not assigned | 40 | Closed | ECES_070 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/30/2009 | ED.18310.1104 | CABRILLO 1104 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 7,442.000 | 7,288.000 | 08J | 09/16/2009 | 2009 | 10/16/2011 | 2011 | clsd | E070 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 415305.82
30732615 | INSTALL BACK-TIE FLORADALE AVE LMPC | # | 30732184 | OC2 RECONDUCTOR FLORADALE AVE | 40 | Closed | ECES_CAP | ECES Capital User Status | # | Not assigned | [8 empty] | 12/29/2009 | ED.18310.1104 | CABRILLO 1104 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 1,200.000 | 0.000 | 08J | 09/21/2009 | 2009 | 05/15/2010 | 2010 | clsd | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 56299.32
30733101 | OC2 RECOND. ANNEALED 6CU VIERRA1702D6811 | 103983663 | # | Not assigned | 40 | Closed | ECES_CAP | ECES Capital User Status | # | Not assigned | [8 empty] | 04/29/2010 | ED.16270.1702 | VIERRA 1702 | 039 | SAN JOAQUIN CO | 5535457 | DO 08 - Monthly Forecast Only | 1,316.000 | 1,400.000 | 08J | 09/22/2009 | 2009 | 05/26/2012 | 2012 | clsd | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 21624.75
30743876 | OC4 REPL. ANNEALED WIRE - GARBERVILE 11 | 104134113 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/30/2010 | ED.19222.1102.SWIT | SWITCHES | 012 | HUMBOLDT COUNT | 5535457 | DO 08 - Monthly Forecast Only | 1,985.000 | 1,985.000 | 08J | 11/18/2009 | 2009 | 04/26/2014 | 2014 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 116234.88
30746346 | OC4 SHADY GLEN 1101 #6CW RECONDUCTOR | 104353046 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2010 | ED.15243.1101.SWIT | SWITCHES | 031 | PLACER COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 6,995.000 | 6,995.000 | 08J | 12/02/2009 | 2009 | 08/27/2011 | 2011 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Shady Glen-Weimar 1101 Reconductoring | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 424862.2
30752681 | OC2 +RECOND 3850 FT DETER 1-0AR BV 1106 | 103921472 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/17/2010 | ED.18273.1102 | RESERVATION ROAD 1102 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 3,850.000 | 3,850.000 | 08J | 01/11/2010 | 2010 | 03/10/2018 | 2018 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 253904.54
30755381 | OC4 WEIMAR 1101 #6CW RECONDUCTOR | # | 30746346 | OC4 SHADY GLEN 1101 #6CW RECONDUCTOR | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | # | ED.15243.1101.SWIT | SWITCHES | 031 | PLACER COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 4,809.000 | 5,022.000 | 08J | 01/26/2010 | 2010 | 07/02/2011 | 2011 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Shady Glen-Weimar 1101 Reconductoring | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 308808.17
30760595 | OC2 WAWONA TAPLINE RECON - REPL 716' 4AR | 104592452 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 05/28/2010 | ED.25529.2104 | WOODWARD 2104 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 548.000 | 548.000 | 08J | 02/25/2010 | 2010 | 10/16/2010 | 2010 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 19751.92
30761631 | OC4 RECONDUCTOR 1040' CLARK RD 1102 | 104605364 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/30/2010 | ED.17-T350000000 | PARADISE MAP T35 | 004 | BUTTE COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 1,040.000 | 1,106.000 | 08J | 03/03/2010 | 2010 | 10/15/2011 | 2011 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 34632.92
30765778 | OC2 RECONDUCTOR SHAFTER 1102 SHAFTER | 104631710 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 05/31/2010 | ED.25365.1102.SWIT | SWITCHES | 015 | KERN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 4,233.000 | 4,233.000 | 08J | 03/24/2010 | 2010 | 11/05/2011 | 2011 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 149188.62
30777995 | OC4 CORNING 1101-SIMPSON RD. RECONDUCTO | 104706550 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2010 | ED.85-CC32000000 | TEHEMA MAP CC32 | 052 | TEHAMA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 2,949.000 | 2,949.000 | 08J | 06/01/2010 | 2010 | 05/26/2012 | 2012 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 142478.35
30781580 | OC2 +REPL ANNEALED 6CU-WEBER 1103-PHASE | 104728286 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2010 | ED.16348.1103 | WEBER 1103 | 039 | SAN JOAQUIN CO | 5535457 | DO 08 - Monthly Forecast Only | 7,580.000 | 7,990.000 | 08J | 06/18/2010 | 2010 | 03/15/2014 | 2014 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Weber 1103 Project | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 587235.38
30781597 | OC2+REPL ANNEALED 6CU-WEBER 1103-PHASE 2 | # | 30781580 | OC2 +REPL ANNEALED 6CU-WEBER 1103-PHASE | 40 | Closed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | # | ED.16348.1103 | WEBER 1103 | 039 | SAN JOAQUIN CO | 5535457 | DO 08 - Monthly Forecast Only | 6,000.000 | 0.000 | 08J | 06/18/2010 | 2010 | 08/24/2013 | 2013 | CLSD | E070 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Weber 1103 Project | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 331289.75
30788135 | OC4 PLCRVILLE 2106 REPL#6 CW DET PH-1 | 104755326 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2011 | ED.15308.2106.RECL | RECLOSERS | 009 | EL DORADO COUN | 5517127 | DO 08 - Monthly Forecast Only | 3,370.000 | 3,403.000 | 08J | 07/15/2010 | 2010 | 04/09/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Placerville 2106 Project | Base Capital | GRC Electric Dist | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 446343.68
30798385 | OC4 HARTLEY 1101 ANNEALED COND | 104795051 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2011 | ED.04321.1101 | HARTLEY 1101 | 017 | LAKE COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 771.000 | 771.000 | 08J | 08/25/2010 | 2010 | 05/10/2014 | 2014 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 189265.91
30799823 | OC2 +RECO 3000 FT 4C/2AR W/ 397A RSRV RD | 104799574 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/29/2011 | ED.18273.1102 | RESERVATION ROAD 1102 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 2,734.000 | 3,000.000 | 08J | 08/31/2010 | 2010 | 11/07/2015 | 2015 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 110624.94
30802035 | OC4 GEYSERVILLE1102ANNEALED 6CU,GYSVL*GC | 104812838 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2011 | ED.04289.1102 | GEYSERVILLE 1102 | 049 | SONOMA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 1,390.000 | 1,450.000 | 08J | 09/11/2010 | 2010 | 05/14/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 127720.71
30804426 | OC2 REPL ANNEALED COND - DINUBA 1105 | 104821609 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/18/2011 | ED.25409.1105 | DINUBA 1105 | 054 | TULARE COUNTY | 5517127 | DO 08 - Monthly Forecast Only | 3,622.000 | 4,865.000 | 08J | 09/22/2010 | 2010 | 09/12/2015 | 2015 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | GRC Electric Dist | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 117017.25
30804427 | OROSI 1103 REPL ANNEALED CONDUCTOR | 104821632 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/30/2012 | ED.25284.1103 | OROSI 1103 | 054 | TULARE COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 8,700.000 | 0.000 | 08J | 09/22/2010 | 2010 | # | #VALUE! | DOCC | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 313768.38
30804428 | OC2 RPL ANNEALED CONDUCTOR-KINGSBRG 1116 | 104821634 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/26/2011 | ED.25224.1116 | KINGSBURG 1116 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 2,000.000 | 5,600.000 | 08J | 09/22/2010 | 2010 | 08/17/2013 | 2013 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 280572.22
30805839 | OC2 KINGSBURG 1112ANNEALED WIRE RPLCEMNT | 104825716 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/15/2012 | ED.25224.1112.SWIT | SWITCHES | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 5,495.000 | 5,495.000 | 08J | 09/28/2010 | 2010 | 11/16/2013 | 2013 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 242666.1
30815883 | OC4 RCNDR 4000' ANEALED 6CU LGN CRK 210 | 104920601 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 08/26/2011 | ED.14-X220000000 | GLENN MAP X22 | 011 | GLENN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 3,487.000 | 3,487.000 | 08J | 11/12/2010 | 2010 | 11/10/2012 | 2012 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 140873.72
30815989 | OC4 CORNING 1101-ROLLING HILLS RECONDUC | 104920955 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 05/30/2013 | ED.85-EE34000000 | TEHEMA MAP EE34 | 052 | TEHAMA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 5,141.000 | 08J | 11/12/2010 | 2010 | 06/21/2014 | 2014 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 381369.73
30818028 | OC4 2011 NB ANNEALED CONDUCTOR 18 SPANS | 104926411 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/01/2011 | ED.04329.1105 | PUEBLO 1105 | 028 | NAPA COUNTY | 5535211 | CWSP SPO - SH 08 | 5,200.000 | 2,945.000 | 08J | 11/20/2010 | 2010 | 09/10/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 1126135.12
30819808 | OC4 PLCRVILLE 2106 REPL#6 CW DET PH-2 | # | 30788135 | OC4 PLCRVILLE 2106 REPL#6 CW DET PH-1 | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | # | ED.15308.2106.RECL | RECLOSERS | 009 | EL DORADO COUN | 5517127 | DO 08 - Monthly Forecast Only | 3,403.000 | 3,165.000 | 08J | 12/01/2010 | 2010 | 11/24/2012 | 2012 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Placerville 2106 Project | Base Capital | GRC Electric Dist | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 335212.18
30819809 | OC4 PLCRVILLE 2106 REPL#6 CW DET PH-3 | # | 30788135 | OC4 PLCRVILLE 2106 REPL#6 CW DET PH-1 | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | # | ED.15308.2106.RECL | RECLOSERS | 009 | EL DORADO COUN | 5517127 | DO 08 - Monthly Forecast Only | 3,605.000 | 3,185.000 | 08J | 12/01/2010 | 2010 | 07/13/2013 | 2013 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Placerville 2106 Project | Base Capital | GRC Electric Dist | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 612383.73
30819811 | OC4 PLCRVILLE 2106 REPL#6 CW DET PH-4 | # | 30788135 | OC4 PLCRVILLE 2106 REPL#6 CW DET PH-1 | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | # | ED.15308.2106.RECL | RECLOSERS | 009 | EL DORADO COUN | 5517127 | DO 08 - Monthly Forecast Only | 3,403.000 | 3,405.000 | 08J | 12/01/2010 | 2010 | 04/09/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Placerville 2106 Project | Base Capital | GRC Electric Dist | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 293093.07
30829819 | MARYSVILLE 1103-RECON1300' #6CU Y2017 | 105186065 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/28/2018 | ED.11-P230800000 | MARYSVILLE MAP P2308 | 058 | YUBA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 1,225.000 | 1,225.000 | 08J | 01/20/2011 | 2011 | 04/20/2019 | 2019 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30829819_R6 RECOND 1300' #6CU MARYSVILLE | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 260614.29
30839342 | OC1 REP 2600' ANNEALED21KV CAYETANO 2109 | 105229251 | # | Not assigned | 40 | Closed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 11/16/2012 | ED.01442.2109.SWIT | SWITCHES | 001 | ALAMEDA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 2,600.000 | 2,598.000 | 08J | 03/07/2011 | 2011 | 09/21/2013 | 2013 | CLSD | E070 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 108029.85
30848750 | OC2 RPL3600FT ANNEALED 1-0AR W/ 715A PH2 | 105282269 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/30/2012 | ED.18226.1106 | BUENA VISTA 1106 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 3,870.000 | 3,870.000 | 08J | 04/27/2011 | 2011 | 03/21/2015 | 2015 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 218745.23
30849708 | OC2 SANTA MRIA 1109 REPL ANNEALED CONDR. | 105292298 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/28/2011 | ED.18267.1106.SWIT | SWITCHES | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 4,012.000 | 4,100.000 | 08J | 05/02/2011 | 2011 | 12/22/2012 | 2012 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 548791.6
30850243 | OCGC RECON OH DET WIRE ON KIRKER 2107 | 105260427 | # | Not assigned | 40 | Closed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 06/27/2014 | ED.01445.2103 | KIRKER 2103 | 007 | CONTRA COSTA C | 5535457 | DO 08 - Monthly Forecast Only | 4,142.000 | 4,132.000 | 08J | 05/05/2011 | 2011 | 12/16/2017 | 2017 | CLSD | E070 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30850243_R1 RECONDUCTOR OH DETERIORATED | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 528791.48
30858527 | OC4XRECON 3000' 4AR/4C W/4-0A,MTRY STSOL | 105341748 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/29/2013 | ED.18205.1114 | SOLEDAD 1114 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 3,255.000 | 0.000 | 08J | 06/21/2011 | 2011 | 05/09/2015 | 2015 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30858527_R2 RECON 3000' 4AR/4C W/4-0A,MT | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 379688.12
30860291 | OC41106 SUNSET OH RECONDUCTORING PROJECT | 105349355 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2011 | ED.02264.1106 | DALY CITY 1106 | 038 | SAN FRANCISCO | 5535457 | DO 08 - Monthly Forecast Only | 2,246.000 | 2,246.000 | 08J | 06/29/2011 | 2011 | 11/19/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30860291_DC 1106 SUNSET OH RECONDUCTORIN | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 617975.52
30860842 | OC2 +REC 7,100' ANNEALED 3/4AR | 105352424 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/28/2012 | ED.18208.2102 | LOS OSITOS 2102 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 7,160.000 | 7,160.000 | 08J | 07/02/2011 | 2011 | 04/09/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 180334.63
30869889 | OC4 ANNEALEDCONDUCTOR-CORONA1101,*GC | 105399422 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 07/01/2012 | ED.04349.1101 | CORONA 1101 | 049 | SONOMA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 4,455.000 | 4,455.000 | 08J | 08/16/2011 | 2011 | 06/13/2015 | 2015 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 487898.45
30871484 | OC4 RECOND ANNEALED CONDUCTOR - PHILO 11 | 105406001 | # | Not assigned | 40 | Closed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 07/01/2012 | ED.04260.1102.SWIT | SWITCHES | 023 | MENDOCINO COUN | 5517127 | DO 08 - Monthly Forecast Only | 12,200.000 | 12,000.000 | 08J | 08/23/2011 | 2011 | 07/27/2013 | 2013 | CLSD | E070 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 842237.96
30872351 | OC4 GARBERVLE1102 ANEALED WIRE 2012: 4/ | 105409229 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 05/31/2013 | ED.19222.1102.SWIT | SWITCHES | 012 | HUMBOLDT COUNT | 5535457 | DO 08 - Monthly Forecast Only | 2,444.000 | 2,444.000 | 08J | 08/26/2011 | 2011 | 07/12/2014 | 2014 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 288699.42
30872353 | OC4GARBERVILE 1102 ANEALED WIRE 2012: 5/ | 105409260 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/28/2013 | ED.19222.1102.SWIT | SWITCHES | 012 | HUMBOLDT COUNT | 5535457 | DO 08 - Monthly Forecast Only | 2,404.000 | 2,095.000 | 08J | 08/26/2011 | 2011 | 06/28/2014 | 2014 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 222452.26
30872362 | OC4 RECOND ANNEALED OH, LINCOLN 1105 | 105409249 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/30/2012 | ED.15370.1105.COND | CONDUCTOR | 031 | PLACER COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 10,248.000 | 102,500.000 | 08J | 08/26/2011 | 2011 | 04/09/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 357096.77
30872486 | OC2 LOCKHEED2 1108RECONDUCTOR OFF CARL | 105409193 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/30/2012 | ED.08300.1108.SWIT | SWITCHES | 043 | SANTA CLARA CO | 5517127 | DO 08 - Monthly Forecast Only | 2,266.000 | 2,266.000 | 08J | 08/26/2011 | 2011 | 07/13/2013 | 2013 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 71719.55
30873773 | OC4HIGHLANDS 1104 ANNEALED WIRE-HELI PAD | 105414190 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/30/2013 | ED.04336.1104.SWIT | SWITCHES | 017 | LAKE COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 1,000.000 | 0.000 | 08J | 09/01/2011 | 2011 | 03/19/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30873773_HIGHLANDS 1104 ANNEALED WIRE-HE | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 507864.89
30873864 | OC4RCNDR ANNEALED #6 AWG COPER, BAYLIS R | 105415953 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2013 | ED.14-X220000000 | GLENN MAP X22 | 011 | GLENN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 7,363.000 | 7,363.000 | 08J | 09/01/2011 | 2011 | 01/17/2015 | 2015 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 382749.63
30874931 | OC2 REPL CONDUCTOR MULT SPLICES BAY | 105421018 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/28/2012 | ED.18280.1101 | BAYWOOD 1101 | 040 | SAN LUIS OBISP | 5535457 | DO 08 - Monthly Forecast Only | 4,195.000 | 4,195.000 | 08J | 09/08/2011 | 2011 | 10/26/2013 | 2013 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 301792.96
30881599 | OC4 EL DORADO PH 2101 DETRIORATED CONDUC | 105494334 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/28/2013 | ED.15276.2101.SWIT | SWITCHES | 009 | EL DORADO COUN | 5535457 | DO 08 - Monthly Forecast Only | 4,493.000 | 4,493.000 | 08J | 10/05/2011 | 2011 | 12/16/2017 | 2017 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 726840.37
30886133 | OC4 ALTO 1125 REPL DET. COND LR_510 | 105529621 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 07/31/2012 | ED.04203.1125.RECL | RECLOSERS | 021 | MARIN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 2,910.000 | 2,184.000 | 08J | 10/26/2011 | 2011 | 12/01/2018 | 2018 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 301572.7
30890664 | *CANC* FR FIGARDEN 2112 FLISR *CANC* | 105587205 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/09/2011 | ED.25204.1101 | AIRWAYS 1101 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 11/19/2011 | 2011 | 03/09/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | GRC Electric Dist | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
30898341 | OC2 OTTER 1102 RPL ANNEALED AR CONCUTC | 105823250 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/28/2013 | ED.18294.1102 | OTTER 1102 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 1,575.000 | 1,575.000 | 08J | 01/11/2012 | 2012 | 06/28/2014 | 2014 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 73318.44
30900554 | XDIX. LAND 2102 - RECONDUCTOR 900 FT | 105891152 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/01/2012 | ED.01472.2102.SWIT | SWITCHES | 043 | SANTA CLARA CO | 5535457 | DO 08 - Monthly Forecast Only | 553.000 | 0.000 | 08J | 01/19/2012 | 2012 | # | #VALUE! | CONS | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 108690.02
30910151 | OC1 REP 1000' ANNEALED COND: SR2103 | 105961196 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/31/2013 | ED.01423.2103.SWIT | SWITCHES | 001 | ALAMEDA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 918.000 | 1,000.000 | 08J | 03/08/2012 | 2012 | 09/12/2015 | 2015 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 97587.8
30912208 | OC4 APPL HILL 2102 850' DETRIORATED WIRE | 105978953 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/29/2013 | ED.15366.2102.SWIT | SWITCHES | 009 | EL DORADO COUN | 5535457 | DO 08 - Monthly Forecast Only | 847.000 | 847.000 | 08J | 03/19/2012 | 2012 | 12/22/2012 | 2012 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 108825.42
30912306 | OC4 RECONDUCTOR 1540' OF #6CU ON | 105979071 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/28/2012 | ED.06380.1104.SWIT | SWITCHES | 048 | SOLANO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 1,632.000 | 08J | 03/19/2012 | 2012 | 06/16/2018 | 2018 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 152264.17
30916072 | OC2 FAIRWAY 1108 - RECOND 4AR WITH 4/0AL | 105998924 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 07/06/2012 | ED.18206.1108.SWIT | SWITCHES | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 4,540.000 | 5,200.000 | 08J | 04/05/2012 | 2012 | 08/02/2014 | 2014 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 183402.78
30925868 | OC4 INSTALL RECL RECON 14 SPNS VD 1103 | 106055388 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/31/2012 | ED.06359.1103.CAPA | CAPACITORS | 048 | SOLANO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 3,876.000 | 3,800.000 | 08J | 05/17/2012 | 2012 | 06/28/2014 | 2014 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 229770.8
30927751 | *CANC* R2 REC 800' 4AR W/397A <(>&<*CANC | 106060104 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 05/01/2013 | ED.18226.1103 | BUENA VISTA 1103 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 05/25/2012 | 2012 | 11/04/2013 | 2013 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
30929941 | OC2 MCKITTRICK 1101 RECONDUCTOR | 106074964 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/28/2013 | ED.66-30213B0000.STRU.POLE | KERN 30213B POLES | 015 | KERN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 1,083.000 | 1,033.000 | 08J | 06/06/2012 | 2012 | 06/29/2013 | 2013 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 26839.87
30930367 | OC2 RECONDUCTOR FUSE 12045 ZONE | 106077910 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/28/2012 | ED.18282.1102 | MESA 1102 | 040 | SAN LUIS OBISP | 5535457 | DO 08 - Monthly Forecast Only | 7,805.000 | 7,805.000 | 08J | 06/08/2012 | 2012 | 03/22/2014 | 2014 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 394557.18
30931343 | OC4 DAIRYLAND 1109: RECONDUCTOR 1MI | 106085535 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 05/30/2014 | ED.25242.1109 | DAIRYLAND 1109 | 020 | MADERA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 5,645.000 | 08J | 06/14/2012 | 2012 | 03/18/2015 | 2015 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30931343_R2 DAIRYLAND 1109: RECONDUCTOR | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 288450.28
30931350 | OC2EL PECO 1102:RECONDUCTOR 5670' OF 2CU | 106086563 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 05/30/2014 | ED.25398.1102 | EL PECO 1102 | 020 | MADERA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 5,463.000 | 08J | 06/14/2012 | 2012 | 09/06/2014 | 2014 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30931350_R2EL PECO 1102: RECONDUCTOR 567 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 301707.02
30934498 | OC4 BH406 RECONDUCT OH LINE ISQ T | 106086709 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/26/2013 | ED.02402.0406.TXFR.TROH | OVERHEAD TRANSFORMERS | 041 | SAN MATEO COUN | 5505513 | PN-OH ANNEALED/DETER CNDCTR: PM MGD | 315.000 | 0.000 | 08J | 06/29/2012 | 2012 | 09/12/2015 | 2015 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 174827.44
30934587 | OC2 REEDLEY 1112: ORANGE COVE OH CNDCTR | 106102919 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/28/2013 | ED.25234.1104 | REEDLEY 1104 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 7,370.000 | 7,370.000 | 08J | 06/29/2012 | 2012 | 10/31/2015 | 2015 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 904244.61
30935374 | 2014 WAHTOKE 1107 RECONDUCTOR | 106107662 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/01/2014 | ED.25453.1107 | WAHTOKE 1107 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 2,153.000 | 2,153.000 | 08J | 07/05/2012 | 2012 | 05/07/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30935374_R2-WAHTOKE 1107: RECONDUCTR 24 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 288007.98
30936534 | OCGC 2014 WAHTOKE 1106 RECONDUCTOR | 106122428 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/01/2014 | ED.25453.1106 | WAHTOKE 1106 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 1,316.000 | 1,316.000 | 08J | 07/12/2012 | 2012 | 05/07/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30936534_R2 WAHTOKE 1106: RCDTR 1090' OF | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 137177.14
30939679 | EC-E 348 JENSON RD WATSONVILLE | 106168479 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 07/29/2012 | ED.76-R191900000 | COAST MAP R1919 | 044 | SANTA CRUZ COU | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 07/27/2012 | 2012 | # | #VALUE! | CONS | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 129910.72
30942894 | *CANC* REPL ANNEALED #4CU JENSEN RD - WA | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/26/2012 | ED.08333.2101 | WATSONVILLE 2101 | 044 | SANTA CRUZ COU | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 08/14/2012 | 2012 | 09/15/2012 | 2012 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
30943402 | OC1 REDWOOD 402 CASSIA ST & MIDDLEFIELD, | 106170140 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/06/2013 | ED.02416.1104.CAPA | CAPACITORS | 041 | SAN MATEO COUN | 5505513 | PN-OH ANNEALED/DETER CNDCTR: PM MGD | 135.000 | 445.000 | 08J | 08/16/2012 | 2012 | 05/13/2017 | 2017 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 28888.56
30945062 | OCCC RECOND 2200 FT 4C W/ 397A HARRIS RD | 106181656 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 08/30/2013 | ED.18226.1102 | BUENA VISTA 1102 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 2,258.000 | 2,258.000 | 08J | 08/25/2012 | 2012 | 09/10/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 151307.19
30946073 | OC2 WIREDOWN - FAMOSO 1101 RECONDUCTOR | 106186356 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/29/2013 | ED.25246.1101.SWIT | SWITCHES | 015 | KERN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 400.000 | 397.000 | 08J | 08/29/2012 | 2012 | 10/17/2015 | 2015 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 5812.75
30947120 | OCLH-CARUTHERS 1104 RECONDUCTORING | 106191445 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/27/2013 | ED.25237.1104 | CARUTHERS 1104 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 660.000 | 660.000 | 08J | 09/05/2012 | 2012 | 12/10/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 41793.22
30948009 | OC1 2819 CURTIS AVE. RWC REPL OH | 106202084 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/29/2013 | ED.02402.1106.SWIT | SWITCHES | 041 | SAN MATEO COUN | 5505513 | PN-OH ANNEALED/DETER CNDCTR: PM MGD | 220.000 | 150.000 | 08J | 09/13/2012 | 2012 | 12/13/2015 | 2015 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 10099.57
30948153 | OC2 REPLACE #6CU WITH 4AR, VASONA 1103 | 106202848 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/26/2013 | ED.08377.1103.SWIT | SWITCHES | 043 | SANTA CLARA CO | 5532479 | CWSP 08W - Monthly Forecast Only | 660.000 | 665.000 | 08W | 09/12/2012 | 2012 | 12/13/2015 | 2015 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 111498.58
30948556 | OC4 E HIGGINS 1109 - RECONDUCTOR 600 | 106207684 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/29/2013 | ED.15269.1109.RECL | RECLOSERS | 031 | PLACER COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 827.000 | 827.000 | 08J | 09/14/2012 | 2012 | 06/10/2017 | 2017 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 53210.78
30949370 | OC2 REEDLEY 1112: WAKEFIELD OH CNDCTR | 106211014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/01/2013 | ED.25234.1112 | REEDLEY 1112 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 5,640.000 | 5,640.000 | 08J | 09/19/2012 | 2012 | 06/13/2015 | 2015 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 292237.77
30949371 | OC2 REEDLEY 1112: ADAMS OH CONDUCTOR | 106211015 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 07/31/2013 | ED.25234.1112 | REEDLEY 1112 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 10,537.000 | 10,537.000 | 08J | 09/19/2012 | 2012 | 07/12/2014 | 2014 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 493832.44
30949571 | OC4 GRN VALLEY 2103 WIRE DOWN NEAR 1993 | 106213156 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/27/2013 | ED.08319.2103 | GREEN VALLEY 2103 | 044 | SANTA CRUZ COU | 5532479 | CWSP 08W - Monthly Forecast Only | 798.000 | 0.000 | 08W | 09/20/2012 | 2012 | 03/19/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 102498.69
30951870 | 2014 MALAGA 1102 RECONDUCTOR CENTRAL | 106224406 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/30/2013 | ED.25425.1102 | MALAGA 1102 | 010 | FRESNO COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 3,786.000 | 3,786.000 | 08W | 10/01/2012 | 2012 | 11/14/2015 | 2015 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | MALAGA 1102: RECON WIREDOWN CNTRL AVE | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 301521.11
30951871 | OC4 2014 MALAGA 1102 RECONDUCTOR AMERICA | 106224510 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/30/2013 | ED.25425.1102 | MALAGA 1102 | 010 | FRESNO COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 5,103.000 | 5,103.000 | 08W | 10/01/2012 | 2012 | 07/12/2014 | 2014 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | MALAGA 1102: RECON WIREDOWN AMERICAN | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 320537.91
30951944 | OC2 MRCD 1116-PHASE 1 RECOND 12,380' 6CU | 106224417 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/27/2013 | ED.25280.1116 | MERCED 1116 | 024 | MERCED COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 12,566.000 | 12,566.000 | 08J | 10/01/2012 | 2012 | 09/15/2018 | 2018 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 377143.56
30951945 | OC2 +TERMINOUS 1103-RECONDUCTR 13,126 FT | 106224749 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/27/2013 | ED.16302.1103 | TERMINOUS 1103 | 039 | SAN JOAQUIN CO | 5535457 | DO 08 - Monthly Forecast Only | 12,227.000 | 12,711.000 | 08J | 10/01/2012 | 2012 | 11/14/2015 | 2015 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 614137.09
30951993 | OC4 XSPRING VALLEY ROAD WIRE REPLACEMENT | 106224516 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/19/2013 | ED.08319.2103 | GREEN VALLEY 2103 | 044 | SANTA CRUZ COU | 5532479 | CWSP 08W - Monthly Forecast Only | 1,592.000 | 1,592.000 | 08W | 10/02/2012 | 2012 | 03/19/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 74464.71
30953274 | OC4 OCGC RECOND ANNEALED 6CU-MONTE RIO 1 | 106232601 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/01/2014 | ED.04281.1113.SWIT | SWITCHES | 049 | SONOMA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 3,968.000 | 0.000 | 08J | 10/09/2012 | 2012 | 07/23/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30953274_R7 RECOND ANNEALED 6CU - MONTE | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 353965.76
30953814 | OC4 JACOBS COR 1101 WIREDOWN RECONDUCTOR | 106232084 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/30/2013 | ED.25477.1101 | JACOBS CORNER 1101 | 016 | KINGS COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 1,465.000 | 4,265.000 | 08J | 10/10/2012 | 2012 | 12/06/2014 | 2014 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 91365.54
30953959 | OC4 PARADISE 1104 - REPL ANNEALED 6CU | 106241178 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/16/2013 | ED.01423.2102.SWIT | SWITCHES | 004 | BUTTE COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 5,191.000 | 5,191.000 | 08J | 10/10/2012 | 2012 | 10/03/2015 | 2015 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30953959_R4 PARADISE 1104 - REPL ANNEALE | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 746697.63
30954009 | OC4 PARADISE 1103- REPL ANNEALED 6CU | 106241223 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/16/2013 | ED.10283.1103.SWIT | SWITCHES | 004 | BUTTE COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 3,800.000 | 3,800.000 | 08J | 10/11/2012 | 2012 | 08/02/2014 | 2014 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 381159.17
30954118 | OC4CORNING 1101-SIMPSON RD RECOND PHSE 3 | 106242164 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/15/2013 | ED.85-CC32000000 | TEHEMA MAP CC32 | 052 | TEHAMA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 10,016.000 | 10,636.000 | 08J | 10/11/2012 | 2012 | 05/09/2015 | 2015 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 630705.93
30954262 | OC4 2014 MERCED 1116 RECONDUCTOR PH 2 | 106242530 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/02/2013 | ED.25280.1116 | MERCED 1116 | 024 | MERCED COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 10,655.000 | 0.000 | 08J | 10/12/2012 | 2012 | 06/16/2018 | 2018 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | MERCED 1116 RECONDUCTOR PH 2 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 347097.02
30954264 | OC4 2014 MERCED 1116 RECONDUCTOR PH 3 | 106242535 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/02/2013 | ED.25280.1116 | MERCED 1116 | 024 | MERCED COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 7,950.000 | 0.000 | 08J | 10/12/2012 | 2012 | 09/15/2018 | 2018 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | MERCED 1116 RECONDUCTOR PH 3 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 323620.58
30954639 | OC4 TYLER 1103 - FRANZEL ROAD RECONDUCTO | 106243673 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/15/2013 | ED.85-Y330200000 | TEHEMA MAP Y3302 | 052 | TEHAMA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 2,199.000 | 2,199.000 | 08J | 10/16/2012 | 2012 | 06/13/2015 | 2015 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30954639_R4 TYLER 1103 - FRANZEL ROAD RE | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 248947.87
30954934 | OC4 REPL 3255 FT OF 4AR W/2A MINERAL AVE | 106247935 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/15/2013 | ED.85-T482500000 | TEHEMA MAP T4825 | 052 | TEHAMA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 3,255.000 | 3,144.000 | 08J | 10/17/2012 | 2012 | 07/12/2014 | 2014 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 413368.79
30958094 | OCGC RVRBNK1711 4,200FT ANNEALED CONDU | 106277074 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/30/2014 | ED.16319.1711 | RIVERBANK 1711 | 050 | STANISLAUS COU | 5535457 | DO 08 - Monthly Forecast Only | 4,040.000 | 0.000 | 08J | 11/03/2012 | 2012 | 03/21/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30958094_R2 RIVERBANK1711 4,200FT ANNEAL | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 211634.19
30958095 | OC4 +VIERRA 1701 ANNEALED CONDUCTR 5,400 | 106277134 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/30/2014 | ED.16270.1701 | VIERRA 1701 | 039 | SAN JOAQUIN CO | 5535457 | DO 08 - Monthly Forecast Only | 4,837.000 | 5,080.000 | 08J | 11/03/2012 | 2012 | 02/06/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30958095_R4E VIERRA 1701 ANNEALED CONDUC | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 245864.94
30958720 | OC4 RECONDUCTOR CALISTOGA 1102_ WIRE DW | 106304275 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/30/2014 | ED.04271.1102 | CALISTOGA 1102 | 028 | NAPA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 2,670.000 | 2,670.000 | 08J | 11/06/2012 | 2012 | 06/25/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30958720_R7 RECONDUCTOR CALISTOGA 1102_ | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 335383.76
30965676 | OCGC OTTER 1102 ANNEALED CNDCTR PH 1 | 106577591 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/10/2014 | ED.18294.1102 | OTTER 1102 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 4,700.000 | 4,700.000 | 08J | 12/11/2012 | 2012 | 08/11/2018 | 2018 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30965676_R2 OTTER 1102 ANNEALED CONDUCTO | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 486696.95
30965813 | OC4 +MESA 1102 WIREDOWN - C/O 8953 | 106579444 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/31/2014 | ED.18282.1102 | MESA 1102 | 042 | SANTA BARBARA | 5532479 | CWSP 08W - Monthly Forecast Only | 8,235.000 | 0.000 | 08W | 12/12/2012 | 2012 | 12/13/2014 | 2014 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 332834.17
30965814 | OC4 ZRECONDUCTOR BW 1101- BTWN 9579 & 95 | 106579371 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/29/2014 | ED.18258.1107 | GOLDTREE 1107 | 040 | SAN LUIS OBISP | 5535457 | DO 08 - Monthly Forecast Only | 4,134.000 | 0.000 | 08J | 12/12/2012 | 2012 | 02/21/2015 | 2015 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30965814_R2RECONDUCTOR BW 1101 - BTWN 95 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 344272.03
30965882 | +BAYWOOD RECONDUCTOR (BRIDGE/TICK) | 106579155 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/31/2014 | ED.18280.1101 | BAYWOOD 1101 | 040 | SAN LUIS OBISP | 5535457 | DO 08 - Monthly Forecast Only | 5,216.000 | 5,222.000 | 08J | 12/12/2012 | 2012 | 04/16/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30965882_R2 BAYWOOD RECONDUCTOR - SWT 54 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 381234.27
30966085 | *CANC* R7RECON ANNEALED 6C MONTE RIO 13 | 106580360 | # | Not assigned | 40 | Closed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 03/30/2014 | ED.04209.1101.SWIT | SWITCHES | 049 | SONOMA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 5,500.000 | 0.000 | 08J | 12/13/2012 | 2012 | 03/09/2013 | 2013 | CLSD | E070 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
30966087 | *CANC* R7RECOND ANNEALED 6C HOPLAND 01 P | 106581204 | # | Not assigned | 40 | Closed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 03/28/2014 | ED.04225.1101.RECL | RECLOSERS | 023 | MENDOCINO COUN | 5535457 | DO 08 - Monthly Forecast Only | 8,000.000 | 0.000 | 08J | 12/13/2012 | 2012 | 03/09/2013 | 2013 | CLSD | E070 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
30966088 | *CANC* R7RECOND ANNEALED 6C HOPLAND 01 P | 106581206 | # | Not assigned | 40 | Closed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 03/28/2014 | ED.04225.1101.SWIT | SWITCHES | 023 | MENDOCINO COUN | 5535457 | DO 08 - Monthly Forecast Only | 8,000.000 | 0.000 | 08J | 12/13/2012 | 2012 | 03/09/2013 | 2013 | CLSD | E070 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
30966089 | *CANC* R7 RECOND ANNLD 6CU - HOPLAND 01 | 106581209 | # | Not assigned | 40 | Closed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 03/28/2014 | ED.04225.1101.SWIT | SWITCHES | 023 | MENDOCINO COUN | 5535457 | DO 08 - Monthly Forecast Only | 5,000.000 | 0.000 | 08J | 12/13/2012 | 2012 | 03/09/2013 | 2013 | CLSD | E070 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
30966296 | OC4 RECNDANNEALED6CU-MOLIN1102BODEGAHW | 106582356 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 07/01/2014 | ED.04257.1102.SWIT | SWITCHES | 049 | SONOMA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 2,020.000 | 2,020.000 | 08J | 12/14/2012 | 2012 | 06/25/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30966296_R4 RECOND ANNEALED 6CU - MOLINO | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 253697.51
30966682 | OCGC XMERK RD, REPL MULTI-SPLICED COND | 106586787 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 01/03/2014 | ED.08369.2104 | ROB ROY 2104 | 044 | SANTA CRUZ COU | 5535457 | DO 08 - Monthly Forecast Only | 1,425.000 | 1,421.000 | 08J | 12/18/2012 | 2012 | 12/26/2015 | 2015 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 70673.47
30967034 | OC4 LINE DOWN - DAVIS 1107 RECON-REFRAME | 106589550 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2013 | ED.06204.1107.TXFR.TROH | OVERHEAD TRANSFORMERS | 057 | YOLO COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 430.000 | 430.000 | 08W | 12/20/2012 | 2012 | 01/31/2015 | 2015 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 30107.47
30968294 | OC2 2013, BAKERSFIELD 2104, RE-CONDUCTOR | 106590826 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/29/2013 | ED.25337.2108.SWIT | SWITCHES | 015 | KERN COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 342.000 | 0.000 | 08W | 12/28/2012 | 2012 | 10/13/2014 | 2014 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 69966.47
30968888 | GARBERVILLE 1102 HENDRIX CABLE PILO*CANC | 106607213 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 08/03/2015 | ED.19222.1102.SWIT | SWITCHES | 012 | HUMBOLDT COUNT | 5535457 | DO 08 - Monthly Forecast Only | 3,000.000 | 0.000 | 08J | 01/03/2013 | 2013 | 10/04/2013 | 2013 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
30969076 | OC4 OCGC COTATI 1103 ANNEALED CONDUCTOR | 106614463 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/01/2014 | ED.04227.1103.SWIT | SWITCHES | 049 | SONOMA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 4,055.000 | 4,055.000 | 08J | 01/04/2013 | 2013 | 12/26/2015 | 2015 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30969076_R7 COTATI 1103 ANNEALED CONDUC | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 355953.62
30969923 | *CANC*RECONDUCTOR15276210115,200' SLYPRK | 106619911 | # | Not assigned | 40 | Closed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2014 | ED.15276.2101.SWIT | SWITCHES | 009 | EL DORADO COUN | 5535457 | DO 08 - Monthly Forecast Only | 15,200.000 | 0.000 | 08J | 01/08/2013 | 2013 | 02/23/2013 | 2013 | CLSD | E070 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
30971722 | OC4RECNDUCT 2 SP OF WIRE @ MAPLE & CEDAR | 106635433 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 07/26/2013 | ED.08325.2108 | PAUL SWEET 2108 | 044 | SANTA CRUZ COU | 5532479 | CWSP 08W - Monthly Forecast Only | 471.000 | 0.000 | 08W | 01/16/2013 | 2013 | 04/09/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 38995
30971802 | OC4 RECONDUCTOR INST FUSES VACA DIXON 11 | 106640881 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2013 | ED.06359.1106.TXFR.TROH | OVERHEAD TRANSFORMERS | 048 | SOLANO COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 872.000 | 900.000 | 08W | 01/17/2013 | 2013 | 01/05/2015 | 2015 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 51100.6
30972334 | OP-1101 RECOND_SAN PABLO & O'HATCH (R) | 106656399 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/30/2014 | ED.01426.1101.SWIT | SWITCHES | 001 | ALAMEDA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 746.000 | 1,000.000 | 08W | 01/25/2013 | 2013 | 09/28/2019 | 2019 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 163292.82
30972547 | OCGC XDEL MONTE 2104 RECOND PORTOLA WD | 106645388 | # | Not assigned | 40 | Closed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 06/06/2014 | ED.18222.2104 | DEL MONTE 2104 | 027 | MONTEREY COUNT | 5532479 | CWSP 08W - Monthly Forecast Only | 590.000 | 0.000 | 08W | 01/22/2013 | 2013 | 10/18/2015 | 2015 | CLSD | E070 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 121269.98
30972641 | WIREDOWN-RECOND-CALWATER 1102 | 106645818 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/25/2014 | ED.25545.1102.CAPA | CAPACITORS | 015 | KERN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 410.000 | 0.000 | 08J | 01/23/2013 | 2013 | # | #VALUE! | DOCC | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 16749.71
30972642 | WIREDOWN-RECOND-KERN OIL 1116 | 106645964 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 07/30/2014 | ED.25272.1116.SWIT | SWITCHES | 015 | KERN COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 250.000 | 0.000 | 08W | 01/23/2013 | 2013 | 10/17/2015 | 2015 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 25637.52
30972743 | OC4 EL DORADO PH 2101 RELOCATE REGS | # | 30881599 | OC4 EL DORADO PH 2101 DETRIORATED CONDUC | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | # | ED.15276.2101.SWIT | SWITCHES | 009 | EL DORADO COUN | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 5.000 | 08J | 01/23/2013 | 2013 | 12/01/2018 | 2018 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 46213.14
30974004 | OC4 DIXON 1103 RECONDUCTOR | 106661251 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 05/30/2014 | ED.06206.1103.SWIT | SWITCHES | 048 | SOLANO COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 689.000 | 0.000 | 08W | 01/29/2013 | 2013 | 10/15/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 119934.85
30974165 | OC4 +CABRILLO 1104 WID @ SWT 6365-12-699 | 106662174 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/01/2014 | ED.18310.1104.SWIT | SWITCHES | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 1,908.000 | 0.000 | 08J | 01/30/2013 | 2013 | 08/08/2015 | 2015 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30974165_R5 CABRILLO 1104 WID @ SWT 6365 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 138318.46
30974166 | +SLO 1107 WIREDOWN (BOB JONES TRAIL) | 106662171 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 05/02/2014 | ED.18263.1107.SWIT | SWITCHES | 040 | SAN LUIS OBISP | 5532479 | CWSP 08W - Monthly Forecast Only | 1,223.000 | 1,223.000 | 08W | 01/30/2013 | 2013 | 09/03/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30974166_R2Z SLO 1107 WIREDOWN@SWT 5041 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 319906.12
30974168 | OC4 LLAGAS 2101 RECONDUCTOR 4 SPANS | 106662143 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/28/2014 | ED.08318.2101.RECL | RECLOSERS | 043 | SANTA CLARA CO | 5532479 | CWSP 08W - Monthly Forecast Only | 1,146.000 | 0.000 | 08W | 01/30/2013 | 2013 | 04/09/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 156970.5
30974172 | OCGC SM 1109 WD LS 45655-HWY 166/BONITA | 106663297 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/07/2014 | ED.18267.1109 | SANTA MARIA 1109 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 2,037.000 | 2,000.000 | 08J | 01/30/2013 | 2013 | 10/17/2015 | 2015 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30974172_R5 SM 1109 WD LS 45655 - 12-610 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 96783.73
30974240 | +SISQUOC 1102 - PH 4 (PHILBRIC RD) | 106663554 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2014 | ED.18281.1102 | SISQUOC 1102 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 2,896.000 | 2,900.000 | 08J | 01/30/2013 | 2013 | 11/05/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | R5 SS 1102 WD SS 46173 - 12-75554 - PH 4 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 172180.75
30974242 | +SISQUOC 1102 - PH 3 (PHILBRIC RD) | 106663552 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2014 | ED.18281.1102 | SISQUOC 1102 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 2,884.000 | 0.000 | 08J | 01/30/2013 | 2013 | 12/10/2016 | 2016 | PREC | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | R5 SIS 1102 WD SS 46173- 12-75554 - PH 3 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 116395.79
30974244 | OCCC CABRILLO 1104 WD @ 2027 - 12-70056 | 106663901 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/01/2014 | ED.18310.1104.SWIT | SWITCHES | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 2,156.000 | 0.000 | 08J | 01/30/2013 | 2013 | 06/18/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30974244_R5 CABRILLO 1104 WD @ 2027 - 12 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 168651.03
30974245 | OCGC+C 1102 PH 2 (STOWELL & PHILBRIC) | 106663407 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2014 | ED.18281.1102 | SISQUOC 1102 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 2,651.000 | 0.000 | 08J | 01/30/2013 | 2013 | 04/02/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30974245_R5 SIS 1102 WD SS 46173 - 12-75 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 100520.03
30974246 | OC4 SISQUOC 1102 PH. 1 RECND 2593' OF 6C | 106663344 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 05/01/2014 | ED.18281.1102 | SISQUOC 1102 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 3,074.000 | 3,100.000 | 08J | 01/30/2013 | 2013 | 02/14/2015 | 2015 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30974246_R5SIS 1102 WD SS 46173 - 12-755 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 98840.26
30974544 | OCGC XSTAR SFTY WK DELMONTE2103 FUSE2489 | 106665376 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2014 | ED.18222.2103 | DEL MONTE 2103 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 2,396.000 | 2,396.000 | 08J | 02/01/2013 | 2013 | 06/16/2018 | 2018 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30974544_R2STAR SAFETY WRK DLMONTE 2103 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 381515.89
30974545 | OCGC STAR SFTY WORK VIEJO 2203 FUSE 6677 | 106665346 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2014 | ED.18285.2203 | VIEJO 2203 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 2,518.000 | 2,518.000 | 08J | 02/01/2013 | 2013 | 07/09/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30974545_R2 STAR SAFETY WORK VIEJO 2203 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 232561.15
30974722 | OC4 DEL MONTE 2102 ELM WIREDWN RECONDUCT | 106666179 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 02/07/2014 | ED.18222.2102 | DEL MONTE 2102 | 027 | MONTEREY COUNT | 5532479 | CWSP 08W - Monthly Forecast Only | 1,056.000 | 0.000 | 08W | 02/01/2013 | 2013 | 12/10/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 194520.97
30974723 | OCGC DEL MONTE 2105 VAN BURN WIRE RECON | 106666120 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 02/01/2014 | ED.18222.2105 | DEL MONTE 2105 | 027 | MONTEREY COUNT | 5532479 | CWSP 08W - Monthly Forecast Only | 790.000 | 0.000 | 08W | 02/01/2013 | 2013 | 04/23/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 153258.33
30974724 | OCGC DEL MNTE 2104 RECTR CORRAL TIERRA | 106665569 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 05/09/2014 | ED.18222.2104 | DEL MONTE 2104 | 027 | MONTEREY COUNT | 5532479 | CWSP 08W - Monthly Forecast Only | 81.000 | 81.000 | 08W | 02/01/2013 | 2013 | 12/26/2015 | 2015 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 24953.43
30974733 | OC2 XREPL COND, BEACH ROAD @ PALM BEACH | 106666589 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/21/2014 | ED.08319.2103 | GREEN VALLEY 2103 | 044 | SANTA CRUZ COU | 5532479 | CWSP 08W - Monthly Forecast Only | 867.000 | 0.000 | 08W | 02/01/2013 | 2013 | 04/11/2015 | 2015 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 50838.25
30975060 | OCGC MESA 1102 WD PHASE 2 (AG PUMPS) | 106667402 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/01/2014 | ED.18282.1102 | MESA 1102 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 3,039.000 | 3,039.000 | 08J | 02/03/2013 | 2013 | 10/17/2015 | 2015 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | R5 MESA 1102 WD 8953 12-34693 PHASE 2 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 124424.05
30975188 | OCGC+SLO 1103 WD @ 14125 - 12-70838 | 106662176 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/31/2014 | ED.18263.1103 | SAN LUIS OBISPO 1103 | 040 | SAN LUIS OBISP | 5532479 | CWSP 08W - Monthly Forecast Only | 435.000 | 435.000 | 08W | 02/04/2013 | 2013 | 06/13/2015 | 2015 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 56157.45
30975189 | OC4 OCGC+MESA 1102 WD PH 3 (STATE PARK) | 106667405 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/28/2014 | ED.18282.1102 | MESA 1102 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 4,947.000 | 4,947.000 | 08J | 02/04/2013 | 2013 | 05/14/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | R5 MESA 1102 WD 8953 12-34693 PHASE 3 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 199350.95
30975288 | R1 RECOND.OH 120 BACK ROAD, LA HONDA | 106590552 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 07/02/2014 | ED.06204.1107.RECL | RECLOSERS | 041 | SAN MATEO COUN | 5505513 | PN-OH ANNEALED/DETER CNDCTR: PM MGD | 450.000 | 450.000 | 08J | 02/08/2013 | 2013 | 02/20/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 30400.16
30975361 | OC4 OCGC 2014 MCMULLIN 1104 RECONDUCTOR | 106666130 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/14/2014 | ED.25441.1104 | MC MULLIN 1104 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 6,830.000 | 0.000 | 08J | 02/05/2013 | 2013 | 03/19/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30975361_R2 MCMULLIN 1104 RECONDUCTORING | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 348379.11
30975432 | OCGC XRECNDUCTR 4 SPS OF WIRE ON WATR ST | 106669286 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/11/2014 | ED.08325.2103 | PAUL SWEET 2103 | 044 | SANTA CRUZ COU | 5535457 | DO 08 - Monthly Forecast Only | 649.000 | 910.000 | 08J | 02/05/2013 | 2013 | 12/26/2015 | 2015 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 90693.02
30975601 | NEWARK 2103 CKT - RECONDUCTOR OH | 106669764 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/25/2013 | ED.01222.2103 | NEWARK 2103 | 001 | ALAMEDA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 400.000 | 0.000 | 08W | 02/06/2013 | 2013 | 01/17/2015 | 2015 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 66146.54
30975614 | OC4 HWY68-TORO CAFE 1101 WIREDOWN RECOND | 106669814 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 05/16/2014 | ED.18273.1101 | RESERVATION ROAD 1101 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 280.000 | 560.000 | 08J | 02/06/2013 | 2013 | 04/11/2015 | 2015 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 42262.14
30975805 | OCGC XINDUSTRIAL WY ANNEALED COND,KC1102 | 106671294 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2014 | ED.18203.1102 | KING CITY 1102 | 027 | MONTEREY COUNT | 5532479 | CWSP 08W - Monthly Forecast Only | 5,100.000 | 5,250.000 | 08W | 02/06/2013 | 2013 | 12/26/2015 | 2015 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30975805_R2 INDUSTRIAL WAY ANNEALED COND | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 183799.96
30975864 | OC4 OCGC SLY PARK RECOND PH 2 (AH2101) 1 | 106670778 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/03/2014 | ED.15276.2101.SWIT | SWITCHES | 009 | EL DORADO COUN | 5535457 | DO 08 - Monthly Forecast Only | 1,879.000 | 1,879.000 | 08J | 02/07/2013 | 2013 | 08/22/2015 | 2015 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30975864_R4E RECONDUCTOR 152762101 6330' | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 212233.13
30975866 | OC4 OCGC SLY PARK RECOND PH 3 (AH2101) 5 | 106670900 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/03/2014 | ED.15276.2101.SWIT | SWITCHES | 009 | EL DORADO COUN | 5535457 | DO 08 - Monthly Forecast Only | 5,839.000 | 5,869.000 | 08J | 02/07/2013 | 2013 | 02/28/2015 | 2015 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30975866_R4E RECONDUCTOR 152762101 7420' | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 377359.07
30975871 | OC4 OCGC SLY PARK RECOND PH 1 (AH2101) 4 | # | 30969923 | *CANC*RECONDUCTOR15276210115,200' SLYPRK | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | # | ED.15276.2101.SWIT | SWITCHES | 009 | EL DORADO COUN | 5535457 | DO 08 - Monthly Forecast Only | 4,506.000 | 0.000 | 08J | 02/07/2013 | 2013 | 12/19/2015 | 2015 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30975871_R4E RECONDUCTOR 152762101 5,500 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 702644.35
30976210 | OC4 WIREDOWN-RECOND-ELK HILLS 1106 | 106668226 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/01/2013 | ED.25244.1106.CAPA | CAPACITORS | 015 | KERN COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 1,105.000 | 1,295.000 | 08W | 02/08/2013 | 2013 | 04/11/2015 | 2015 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 57360.21
30976454 | OC4 OCGC RECON ANNEALED 6C MONTE RIO 13 | # | 30966085 | *CANC* R7RECON ANNEALED 6C MONTE RIO 13 | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/01/2014 | ED.04209.1101.SWIT | SWITCHES | 049 | SONOMA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 6,482.000 | 08J | 02/09/2013 | 2013 | 06/25/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30976454_R7RECON ANNEALED 6C MONTE RIO 1 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 606628.97
30976455 | OC4 RECOND ANNEALED 6C HOPLAND 01 PHASE | # | 30966087 | *CANC* R7RECOND ANNEALED 6C HOPLAND 01 P | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/01/2014 | ED.04225.1101.RECL | RECLOSERS | 023 | MENDOCINO COUN | 5535457 | DO 08 - Monthly Forecast Only | 10,893.000 | 12,000.000 | 08J | 02/09/2013 | 2013 | 02/18/2017 | 2017 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30976455_R7 RECOND ANNEALED 6C HOPLAND 0 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 835279.93
30976456 | OC4 RECOND DET 6C HOPLAND 01 PHASE 2 | # | 30966088 | *CANC* R7RECOND ANNEALED 6C HOPLAND 01 P | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/02/2014 | ED.04225.1101.SWIT | SWITCHES | 023 | MENDOCINO COUN | 5535457 | DO 08 - Monthly Forecast Only | 7,055.000 | 9,055.000 | 08J | 02/09/2013 | 2013 | 06/25/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30976456_R7 RECOND DET 6C HOPLAND 01 PHA | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 490287.77
30976458 | OC4RECOND ANNLD 6CU - HOPLAND 01 PHASE 3 | # | 30966089 | *CANC* R7 RECOND ANNLD 6CU - HOPLAND 01 | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 08/01/2014 | ED.04225.1101.SWIT | SWITCHES | 023 | MENDOCINO COUN | 5535457 | DO 08 - Monthly Forecast Only | 5,623.000 | 5,623.000 | 08J | 02/09/2013 | 2013 | 06/25/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30976458_R7 RECOND ANNLD 6CU - HOPLAND 0 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 507176.77
30976834 | OC4 WIRE DOWN-RECONDUCTOR ANNEALED 6CU | 106684844 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2013 | ED.06288.1102.SWIT | SWITCHES | 006 | COLUSA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 868.000 | 868.000 | 08J | 02/12/2013 | 2013 | 02/14/2015 | 2015 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 52966.03
30976836 | OC4 OCGC RICE 1101- RECONDUCTOR ANNEALED | 106684756 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2013 | ED.06283.1101.TXFR.TROH | OVERHEAD TRANSFORMERS | 006 | COLUSA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 2,628.000 | 2,628.000 | 08J | 02/12/2013 | 2013 | 07/23/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | RICE 1101 - RECONDUCTOR ANNEALED 4AR | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 211583.62
30977168 | OC4 OCGC FRNCH CMP 1102 RECOND & RELOCA | 106688549 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/31/2014 | ED.16329.1102 | FRENCH CAMP 1102 | 039 | SAN JOAQUIN CO | 5532479 | CWSP 08W - Monthly Forecast Only | 1,723.000 | 1,215.000 | 08W | 02/13/2013 | 2013 | 02/20/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 260893.04
30977169 | OCGC LOCKEFORD 2102 RECONDUCTOR PHASE | 106688542 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/31/2014 | ED.16368.2102 | LOCKEFORD 2102 | 039 | SAN JOAQUIN CO | 5535457 | DO 08 - Monthly Forecast Only | 4,878.000 | 4,880.000 | 08J | 02/13/2013 | 2013 | 08/19/2017 | 2017 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30977169_R4 LOCKEFORD 2102 RECONDUCTOR P | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 238800.72
30977396 | OCGC XSTAR MODEL ZONE FUSE 9343 RR 2105 | 106689108 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/06/2013 | ED.08369.2105 | ROB ROY 2105 | 044 | SANTA CRUZ COU | 5535457 | DO 08 - Monthly Forecast Only | 714.000 | 382.000 | 08J | 02/14/2013 | 2013 | 10/17/2015 | 2015 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 57810.64
30977508 | OCGC REPLACE ANNEALED CONDUCTOR, HWY. 45 | 106685118 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/01/2013 | ED.14-Y230000000 | GLENN MAP Y23 | 011 | GLENN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 1,054.000 | 1,054.000 | 08J | 02/14/2013 | 2013 | 12/17/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 110110.65
30977612 | OCGC OTTER 1102 DETERIORTD CNDUCTR PH 2 | 106691311 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 08/29/2014 | ED.18294.1102 | OTTER 1102 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 3,482.000 | 3,560.000 | 08J | 02/15/2013 | 2013 | 02/13/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30977612_R2 OTTER 1102 DETERIORTD CNDUCT | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 515730.8
30977613 | WDDB OTTER 1102 PHASE 3 | 106691313 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/26/2015 | ED.18294.1102 | OTTER 1102 | 027 | MONTEREY COUNT | 5535211 | CWSP SPO - SH 08 | 3,700.000 | 0.000 | 08W | 02/15/2013 | 2013 | # | #VALUE! | PEND | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | 30977613_R2 OTTER 1102 DETERIORTD CNDUCT | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 266249.81
30977614 | WDDB OTTER 1102 PHASE 4 | 106691314 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/17/2015 | ED.18294.1102 | OTTER 1102 | 027 | MONTEREY COUNT | 5535211 | CWSP SPO - SH 08 | 3,681.000 | 0.000 | 08W | 02/15/2013 | 2013 | # | #VALUE! | UNSC | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | 30977614_R2 OTTER 1102 DETERIORTD CNDUCT | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 251685.53
30977615 | WDDB OTTER 1102 PHASE 5 | 106691315 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/28/2015 | ED.18294.1102 | OTTER 1102 | 027 | MONTEREY COUNT | 5535211 | CWSP SPO - SH 08 | 2,929.000 | 0.000 | 08W | 02/15/2013 | 2013 | # | #VALUE! | UNSC | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | 30977615_R2 OTTER 1102 DETERIORTD CNDUCT | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 195849.51
30977927 | OCGCREPL OH DET WIRE ON JERSEY ISLAND 4 | 106689335 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/31/2014 | ED.01832.0401 | JERSEY ISLAND 0401 | 007 | CONTRA COSTA C | 5535457 | DO 08 - Monthly Forecast Only | 3,381.000 | 0.000 | 08J | 02/19/2013 | 2013 | 06/25/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30977927_R1 REPL OH DET WIRE ON JRSEY I | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 277755.9
30978199 | OC4 HMB1102 CO5905 RECONDUCTOR 470 FT | 106691125 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 02/18/2014 | ED.02410.1102.SWIT | SWITCHES | 041 | SAN MATEO COUN | 5535457 | DO 08 - Monthly Forecast Only | 1,081.000 | 1,081.000 | 08W | 02/19/2013 | 2013 | 02/14/2015 | 2015 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 182689.15
30978240 | OC4 HMB-1102 CO6097 RECOND 500FT REFRAME | 106691153 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 02/28/2014 | ED.02410.1102.TXFR.TROH | OVERHEAD TRANSFORMERS | 041 | SAN MATEO COUN | 5505513 | PN-OH ANNEALED/DETER CNDCTR: PM MGD | 1,078.000 | 1,349.000 | 08J | 02/19/2013 | 2013 | 11/07/2015 | 2015 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 122061.17
30978241 | OC4 BELL HAVEN 401 RECONDUCTOR OH LINE | 106691251 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 02/20/2014 | ED.02402.0401.TXFR.TROH | OVERHEAD TRANSFORMERS | 041 | SAN MATEO COUN | 5505513 | PN-OH ANNEALED/DETER CNDCTR: PM MGD | 2,560.000 | 0.000 | 08J | 02/19/2013 | 2013 | 10/15/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30978241_R1_BH-401 RECONDUCTOR 1200FT OH | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 570725.9
30978331 | OCGC OH LR/FUSES <(>&<)> RECON MNLNE CL | 106698894 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/30/2014 | ED.01202.1103 | CLAYTON 1103 | 007 | CONTRA COSTA C | 5535457 | DO 08 - Monthly Forecast Only | 4,807.000 | 9,846.000 | 08J | 02/19/2013 | 2013 | 06/16/2018 | 2018 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30978331_R1 INST OH LR/FUSES & RECON MNL | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 795125.01
30978400 | OC2 RECOND 1100FT DETERIOR 4-0ASPRECKELS | 106702160 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/22/2013 | ED.18226.1102 | BUENA VISTA 1102 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 1,260.000 | 08J | 02/20/2013 | 2013 | 08/05/2017 | 2017 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 26530.79
30978775 | OC4 REPL OH DET WIRE PAST C/O 15261 | 106708405 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/30/2014 | ED.01365.2109 | CONTRA COSTA 2109 | 007 | CONTRA COSTA C | 5535457 | DO 08 - Monthly Forecast Only | 802.000 | 802.000 | 08J | 02/22/2013 | 2013 | 06/25/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30978775_REPL OH DET WIRE PAST C/O 1526 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 75024.92
30978845 | OC4 REPL 800' OF ANNEALED 6C PAST C/O459 | 106707433 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2014 | ED.06246.2225.TXFR.TROH | OVERHEAD TRANSFORMERS | 048 | SOLANO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 853.000 | 922.000 | 08J | 02/22/2013 | 2013 | 07/21/2018 | 2018 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 66536.21
30978886 | OCGC RECONDUCTOR TO REMOVE SPLICES | 106713703 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/01/2014 | ED.08337.1106.SWIT | SWITCHES | 043 | SANTA CLARA CO | 5532479 | CWSP 08W - Monthly Forecast Only | 1,031.000 | 0.000 | 08W | 02/22/2013 | 2013 | 12/26/2015 | 2015 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 162877.11
30979240 | OCGC XRECON 4 SPS OF WR GLEENWOOD-CE2106 | 106721990 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/27/2014 | ED.08362.2106 | CAMP EVERS 2106 | 044 | SANTA CRUZ COU | 5532479 | CWSP 08W - Monthly Forecast Only | 783.000 | 733.000 | 08W | 02/24/2013 | 2013 | 12/13/2015 | 2015 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 132806.31
30979241 | OCGC XRECON 2 SPN@GRNITE CRK/HWY17 S VLY | 106721991 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/26/2014 | ED.08362.2104 | CAMP EVERS 2104 | 044 | SANTA CRUZ COU | 5532479 | CWSP 08W - Monthly Forecast Only | 350.000 | 0.000 | 08W | 02/24/2013 | 2013 | 10/17/2015 | 2015 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 41233.4
30979379 | +RECNDUCTR TO REMOVE SPLICES VASONA 110 | 106723171 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/01/2013 | ED.08377.1105 | VASONA 1105 | 043 | SANTA CLARA CO | 5532479 | CWSP 08W - Monthly Forecast Only | 871.000 | 0.000 | 08W | 02/25/2013 | 2013 | 05/14/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 95309.21
30979412 | *CANC* PURISMA 1101 WD 12-24063 | 106729323 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/01/2014 | ED.18297.1101 | PURISIMA 1101 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 02/26/2013 | 2013 | 12/21/2013 | 2013 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
30979413 | *CANC*CABRILLO 1104 WD 12-27130 *CANC | 106729324 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/01/2014 | ED.18310.1104 | CABRILLO 1104 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 02/26/2013 | 2013 | 11/03/2018 | 2018 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
30979415 | +MB 1101 (MORRO BAY STATE PARK) | 106729326 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/01/2014 | ED.18301.1101 | MORRO BAY 1101 | 040 | SAN LUIS OBISP | 5535457 | DO 08 - Monthly Forecast Only | 3,233.000 | 3,233.000 | 08J | 02/26/2013 | 2013 | 07/02/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | R5 MB 1101 WD 12-50404 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 334919.66
30979416 | +CAYUCOS 1102 (PACIFIC ST - HOTELS) | 106729328 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/01/2014 | ED.18255.1101 | CAYUCOS 1101 | 040 | SAN LUIS OBISP | 5535457 | DO 08 - Monthly Forecast Only | 1,268.000 | 1,200.000 | 08J | 02/26/2013 | 2013 | 08/27/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30979416_R5 CAYUCOS 1102 WD 12-69012 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 140761.56
30979417 | *CANC* SM 1110 WD 12-68271 | 106729327 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/01/2014 | ED.18267.1110 | SANTA MARIA 1110 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 02/26/2013 | 2013 | 12/14/2013 | 2013 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
30979480 | X RECN 3000' OF 6CU ON GLNCANYON CE2103 | 106721992 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/29/2017 | ED.08362.2103 | CAMP EVERS 2103 | 044 | SANTA CRUZ COU | 5535457 | DO 08 - Monthly Forecast Only | 3,659.000 | 3,600.000 | 08J | 02/25/2013 | 2013 | 03/16/2019 | 2019 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30979480_2 RECN 3000' OF 6CU ON GLNCANY | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 387990.78
30979520 | OCGC FAIRWAY 1108 RECON (LAKEVIEW & BRAD | 106729325 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/01/2014 | ED.18206.1108 | FAIRWAY 1108 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 817.000 | 817.000 | 08J | 02/26/2013 | 2013 | 05/14/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | R5 FAIRWAY 1108 RECONDUCTOR SANTA MARIA | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 142201.67
30979558 | OC4 RECONDUCTOR OH MAINLINE CL 1103 | 106729138 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/30/2014 | ED.01202.1103 | CLAYTON 1103 | 007 | CONTRA COSTA C | 5535457 | DO 08 - Monthly Forecast Only | 3,100.000 | 3,100.000 | 08J | 02/26/2013 | 2013 | 06/25/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30979558_R1 RECONDUCTOR OH MAINLINE CL 1 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 695075.66
30979723 | OC4 OCGC EB-R1125 RELIABILITY PROJECT ( | 106729841 | # | Not assigned | 40 | Closed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/22/2014 | ED.01347.1125.SWIT | SWITCHES | 007 | CONTRA COSTA C | 5535457 | DO 08 - Monthly Forecast Only | 5,000.000 | 4,866.000 | 08J | 02/26/2013 | 2013 | 07/14/2018 | 2018 | CLSD | E070 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30979723_R1-EB-RELIABILITY-RECOND R1125 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 1793122.66
30979750 | OCGC XHATTON1102 STAR XX PTRL FUSE 8947 | 106729712 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2014 | ED.18229.1102 | HATTON 1102 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 1,682.000 | 2,200.000 | 08J | 02/26/2013 | 2013 | 09/23/2017 | 2017 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30979750_R2 HATTON 1102 STAR XX PATROL F | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 318972.97
30979782 | OC4 ORCHARD RD RECONDUCTOR RM 1101 | 106732361 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 05/31/2014 | ED.01416.1101 | ROSSMOOR 1101 | 007 | CONTRA COSTA C | 5535457 | DO 08 - Monthly Forecast Only | 1,268.000 | 1,268.000 | 08J | 02/27/2013 | 2013 | 05/14/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 2014 ORCHARD RD RECONDUCTOR RM 1101 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 197758.06
30979783 | OCGC2014 HOUGH AVE OH RECONDUCTOR | 106690945 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/01/2014 | ED.01416.1106 | ROSSMOOR 1106 | 007 | CONTRA COSTA C | 5535457 | DO 08 - Monthly Forecast Only | 937.000 | 937.000 | 08J | 02/27/2013 | 2013 | 10/24/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30979783_R1 2014 HOUGH AVE OH RECONDUCTO | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 490063.07
30979785 | OCGCLANCASTER RECONDUCTOR RM 1107 | 106702142 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/30/2014 | ED.01416.1107 | ROSSMOOR 1107 | 007 | CONTRA COSTA C | 5535457 | DO 08 - Monthly Forecast Only | 3,249.000 | 0.000 | 08J | 02/27/2013 | 2013 | 06/25/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30979785_R1 2014 LANCASTER RECONDUCTOR R | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 504045.08
30979786 | OC4 2014 SINGINGWOOD CT OH RECON RM 1103 | 106702143 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/30/2014 | ED.01416.1103 | ROSSMOOR 1103 | 007 | CONTRA COSTA C | 5535457 | DO 08 - Monthly Forecast Only | 1,004.000 | 1,007.000 | 08J | 02/27/2013 | 2013 | 06/25/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30979786_R1 2014 SINGINGWOOD CT OH RECON | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 230437.42
30979787 | OCGC2014 CASTLE CR RD RECONDUCTOR LW2224 | 106731963 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/22/2014 | ED.01353.2224 | LAKEWOOD 2224 | 007 | CONTRA COSTA C | 5532479 | CWSP 08W - Monthly Forecast Only | 583.000 | 0.000 | 08W | 02/27/2013 | 2013 | 06/25/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30979787_R1 2014 CASTLE CR RD RECONDUCT | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 146850.96
30979877 | OC4 CORNING 1101 RECONDUCTOR - PHASE 4 | 106706600 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/01/2014 | ED.85-CC31000000 | TEHEMA MAP CC31 | 052 | TEHAMA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 10,642.000 | 10,642.000 | 08J | 02/27/2013 | 2013 | 05/09/2015 | 2015 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30979877_CORNING 1101 RECONDUCTOR - PHAS | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 732268.57
30979878 | OC4 CORNING 1101 PH 5 RECON 11684' Y2015 | 106706620 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/01/2014 | ED.85-CC30000000 | TEHEMA MAP CC30 | 052 | TEHAMA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 11,856.000 | 13,281.000 | 08J | 02/27/2013 | 2013 | 03/17/2018 | 2018 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30979878_CORNING 1101 RECONDUCTOR - PHAS | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 798799.64
30979879 | RECON 11000'-CORNING 1101 PHASE 6 Y2016 | 106706623 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/01/2014 | ED.85-CC29000000 | TEHEMA MAP CC29 | 052 | TEHAMA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 231,860.000 | 11,290.000 | 08J | 02/27/2013 | 2013 | 02/25/2017 | 2017 | PREC | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30979879_CORNING 1101 RECONDUCTOR - PHAS | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 492817.26
30979948 | X REPL DET COND, BEACH & SAN ANDREAS | 106743015 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/25/2014 | ED.08319.2103 | GREEN VALLEY 2103 | 044 | SANTA CRUZ COU | 5535457 | DO 08 - Monthly Forecast Only | 2,240.000 | 0.000 | 08J | 02/27/2013 | 2013 | 08/19/2017 | 2017 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 186541.52
30979949 | *CANC* REPLACE DET COND, VANONI RD CANC | 106742703 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/25/2014 | ED.08319.2101 | GREEN VALLEY 2101 | 044 | SANTA CRUZ COU | 5535457 | DO 08 - Monthly Forecast Only | 5,294.000 | 0.000 | 08J | 02/27/2013 | 2013 | 12/28/2013 | 2013 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
30979950 | OC4 MIDDLE RVR 1103 RECONDUCTOR PHASE-1 | 106741099 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2014 | ED.16209.1103 | MIDDLE RIVER 1103 | 039 | SAN JOAQUIN CO | 5517127 | DO 08 - Monthly Forecast Only | 9,635.000 | 9,635.000 | 08J | 02/27/2013 | 2013 | 03/19/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | R2 MIDDLE RVR RECNDUCTORING | Base Capital | GRC Distribution Common | GRC | CUSTCARE | Electric Distribution | Electric Distribution | 523898.84
30979951 | OC4 MIDDLE RVR 1103 RECNDUCTORING PHASE- | 106741111 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2014 | ED.16209.1103 | MIDDLE RIVER 1103 | 039 | SAN JOAQUIN CO | 5517127 | DO 08 - Monthly Forecast Only | 6,025.000 | 6,025.000 | 08J | 02/27/2013 | 2013 | 03/14/2015 | 2015 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | R2 MIDDLE RVR RECNDUCTORING | Base Capital | GRC Distribution Common | GRC | CUSTCARE | Electric Distribution | Electric Distribution | 326881
30979952 | OCGC MIDDLE RVR 1101 RECONDUCTORING | 106741116 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2014 | ED.16209.1101 | MIDDLE RIVER 1101 | 039 | SAN JOAQUIN CO | 5535457 | DO 08 - Monthly Forecast Only | 5,282.000 | 5,282.000 | 08J | 02/27/2013 | 2013 | 12/10/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Middle River 1101 Reconductor | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 362043.66
30979962 | OC4 CORNING 1102 RECONDUCTOR - PHASE 1 | 106706629 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/01/2014 | ED.85-DD28000000 | TEHEMA MAP DD28 | 052 | TEHAMA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 4,793.000 | 4,793.000 | 08J | 02/27/2013 | 2013 | 12/16/2017 | 2017 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30979962_CORNING 1102 RECONDUCTOR - PHAS | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 279087.95
30979968 | OCGCCORNING 1102- PH 2 REC 11,300' Y2015 | 106706650 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/01/2014 | ED.85-DD29000000 | TEHEMA MAP DD29 | 052 | TEHAMA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 11,455.000 | 11,455.000 | 08J | 02/27/2013 | 2013 | 01/28/2017 | 2017 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30979968_CORNING 1102 RECONDUCTOR - PHAS | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 770459.16
30980058 | RECON SR2108 BOLLINGER CANYON | 106689725 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/26/2014 | ED.24-G121600000.STRU | MISSION MAP G1216 STRUCTURE | 007 | CONTRA COSTA C | 5535457 | DO 08 - Monthly Forecast Only | 1,967.000 | 1,966.000 | 08J | 02/28/2013 | 2013 | 09/15/2018 | 2018 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 177975.67
30980061 | *CANC* RECONDUCTOR 1 SP @ THOMPSON*CANC | 106743079 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 08/01/2014 | ED.08325.2104 | PAUL SWEET 2104 | 044 | SANTA CRUZ COU | 5532479 | CWSP 08W - Monthly Forecast Only | 235.000 | 0.000 | 08W | 02/27/2013 | 2013 | 04/03/2014 | 2014 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
30980068 | 285 LITTLEFIELD AVE SSF | 106690953 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/25/2013 | ED.56-E041000000 | SKYLINE MAP E0410 | 041 | SAN MATEO COUN | 5535457 | DO 08 - Monthly Forecast Only | 369.000 | 352.000 | 08W | 02/28/2013 | 2013 | 02/14/2015 | 2015 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 25773.51
30980069 | R1 MB-1106 RECONDUCTORING | 106690975 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/28/2014 | ED.56-F051200000 | SKYLINE MAP F0512 | 041 | SAN MATEO COUN | 5535457 | DO 08 - Monthly Forecast Only | 88.000 | 88.000 | 08W | 02/28/2013 | 2013 | 02/20/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 40367.42
30980093 | OCGC HORSESHOE 1106 RECOND - 7585 STAR | 106746211 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/13/2014 | ED.15257.1106 | HORSESHOE 1106 | 031 | PLACER COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 2,390.000 | 2,390.000 | 08J | 02/28/2013 | 2013 | 04/23/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30980093_STAR-HORSESHOE 1106 -7585_08J | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 271105.46
30980105 | OC4ORO FINO 1102 - 727FT OF ANNEALED 2AR | 106744320 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/26/2014 | ED.17-Q33G000000 | PARADISE MAP Q33G | 004 | BUTTE COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 420.000 | 420.000 | 08J | 02/28/2013 | 2013 | 01/17/2015 | 2015 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 62706.9
30980106 | OCGC 1102 - 5100FT ANNEAL COND 2016 | 106744323 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/26/2014 | ED.17-Q330000000 | PARADISE MAP Q33 | 004 | BUTTE COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 5,357.000 | 5,357.000 | 08J | 02/28/2013 | 2013 | 12/16/2017 | 2017 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30980106_Oro Fino 1102 08J | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 638469.21
30980124 | OC4 NORD 1104 - RECOND 5400FT OF 2CU | 106742838 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/29/2014 | ED.16-T26A000000 | CHICO MAP T26A | 004 | BUTTE COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 5,475.000 | 5,475.000 | 08J | 02/28/2013 | 2013 | 07/29/2017 | 2017 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30980124_R6 NORD 1104 - RECOND 5400FT OF | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 606702.08
30980127 | OC4 R4 NORD 1104 - RECOND 9300FT OF 6CU | 106742970 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/25/2014 | ED.16-S260000000 | CHICO MAP S26 | 004 | BUTTE COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 9,300.000 | 08J | 02/28/2013 | 2013 | 06/13/2015 | 2015 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30980127_R6 NORD 1104 - RECOND 9300FT OF | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 599148.73
30980133 | OCGC DAME 1104-9300' ANNE 2AR Y2016 | 106744327 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/31/2014 | ED.16-R310000000 | CHICO MAP R31 | 004 | BUTTE COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 9,300.000 | 9,300.000 | 08J | 02/28/2013 | 2013 | 04/22/2017 | 2017 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30980133_Notre Dame 1104 Recond. 9300ft_ | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 724636.48
30980173 | OCGC RECONDUCTOR, 152561107, KING ROAD | 106746468 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/13/2014 | ED.15256.1107 | PENRYN 1107 | 031 | PLACER COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 3,145.000 | 3,145.000 | 08J | 02/28/2013 | 2013 | 03/03/2018 | 2018 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30980173_R4E RECONDUCTOR, 152561107, KIN | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 273732.18
30980185 | OC4 REPLACE ANNEALED CONDUCTOR, LAUREL S | 106744758 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/01/2014 | ED.14-Y191200000 | GLENN MAP Y1912 | 011 | GLENN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 4,480.000 | 4,480.000 | 08J | 02/28/2013 | 2013 | 10/10/2015 | 2015 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30980185_R6 REPLACE ANNEALED CONDUCTOR, | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 535026.86
30980186 | OCGC CON. 5395', HWY. 45 PH. 2 Y2017 | 106744759 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 05/30/2017 | ED.14-Y230000000 | GLENN MAP Y23 | 011 | GLENN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 5,395.000 | 5,395.000 | 08J | 02/28/2013 | 2013 | 01/26/2019 | 2019 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30980186_Y2016 HWY 45 PH 2 Glen County_8 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 507846.96
30980187 | OC4 OCGC COND 5360' RD 34 JACINTO 1102 Y | 106744760 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/01/2014 | ED.14-W220000000 | GLENN MAP W22 | 011 | GLENN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 5,007.000 | 5,007.000 | 08J | 02/28/2013 | 2013 | 09/10/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | EP REPLACE ANNEALED CONDUCTOR | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 245343.03
30980188 | OCGC EP BIG MEADOWS 2101 ANNE COND Y2015 | 106744761 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/01/2014 | ED.18-J460000000 | LAS PLUMAS MAP J46 | 032 | PLUMAS COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 5,249.000 | 5,249.000 | 08J | 02/28/2013 | 2013 | 07/02/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | EP REPLACE ANNEALED CONDUCTOR, PRATTVILL | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 362265.96
30980189 | OCGC LOGAN CRK 2101 RECOND, ROAD D Y2016 | 106744762 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/01/2014 | ED.14-Y170000000 | GLENN MAP Y17 | 011 | GLENN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 16,097.000 | 8,387.000 | 08J | 02/28/2013 | 2013 | 04/22/2017 | 2017 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | EP REPLACE ANNEALED CONDUCTOR, ROAD DEP | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 610121.47
30980225 | OC4 RECON. 1060' NICASIO RAMONA JUAREZ | 106747584 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/20/2014 | ED.04302.1101.SWIT | SWITCHES | 021 | MARIN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 2,522.000 | 2,522.000 | 08J | 02/28/2013 | 2013 | 01/28/2018 | 2018 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30980225_R7 RECON. 1060' NICASIO RAMONA | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 526129.96
30980443 | XRECOND 4433/23327 @ 105 RODGERS RD | 106760612 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 08/01/2014 | ED.18238.1104 | DOLAN ROAD 1104 | 027 | MONTEREY COUNT | 5532479 | CWSP 08W - Monthly Forecast Only | 351.000 | 0.000 | 08W | 03/01/2013 | 2013 | 08/05/2017 | 2017 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 18411.46
30980444 | OC4 XRECOND 310 FT 1-0C, LKHRN & CAST BL | 106760583 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/27/2014 | ED.18238.1101 | DOLAN ROAD 1101 | 027 | MONTEREY COUNT | 5532479 | CWSP 08W - Monthly Forecast Only | 313.000 | 0.000 | 08W | 03/01/2013 | 2013 | 02/14/2015 | 2015 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 17517.77
30980600 | COTTLE 1703 WIRE DOWN-RECOND 2400 FT | 106765982 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/01/2014 | ED.16371.1703 | COTTLE 1703 | 050 | STANISLAUS COU | 5535457 | DO 08 - Monthly Forecast Only | 2,400.000 | 0.000 | 08J | 03/03/2013 | 2013 | 06/16/2018 | 2018 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30980600_R2 COTTLE 1703 WIRE DOWN-RECOND | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 236686.67
30980601 | OCGC VALLEY HOME1701-WRE DWN RECOND 715 | 106766009 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/01/2014 | ED.16298.1701 | VALLEY HOME 1701 | 050 | STANISLAUS COU | 5535457 | DO 08 - Monthly Forecast Only | 8,485.000 | 8,589.000 | 08J | 03/03/2013 | 2013 | 10/29/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30980601_R2 VALLEY HOME1701-WIRE DOWN RE | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 443619.25
30981132 | 2017 RENFRO 2101 RECONDUCTOR PH 1 | 106767393 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/31/2018 | ED.25457.2101.SWIT | SWITCHES | 015 | KERN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 4,475.000 | 5,000.000 | 08J | 03/05/2013 | 2013 | 12/12/2018 | 2018 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | R5 RECOND 4,888' 6C&4AR-RENFRO 2101 PH.1 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 398685.95
30981133 | 2016 RENFRO 2101 RECONDUCTOR PH 2 | 106779930 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/27/2014 | ED.25457.2101.SWIT | SWITCHES | 015 | KERN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 5,768.000 | 5,768.000 | 08J | 03/05/2013 | 2013 | 12/17/2016 | 2016 | PREC | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | R5 RECOND 5,368' 6C&4AR-RENFRO 2101 PH.2 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 434953.53
30981135 | OC4 OCGC 2104 FRUITVALE 1103 RECONDUCTOR | 106767681 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/27/2014 | ED.25339.1103.TXFR.TROH | OVERHEAD TRANSFORMERS | 015 | KERN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 1,274.000 | 1,325.000 | 08J | 03/05/2013 | 2013 | 02/07/2015 | 2015 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30981135_R5 RECONDUCTOR 1,300' 4AR-FRUIT | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 135613.65
30981136 | OC4 OCGC2014 FRUITVALE 1103 RECONDUCTOR | 106768129 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/27/2014 | ED.25339.1103.SWIT | SWITCHES | 015 | KERN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 1,457.000 | 1,457.000 | 08J | 03/05/2013 | 2013 | 03/21/2015 | 2015 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30981136_R5 RECONDUCTOR 3,226' 4AR-FRUIT | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 132482.87
30981137 | 2015 7TH STANDARD 1103 RECONDUCTOR | 106769343 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/27/2014 | ED.25458.2103.TXFR.TROH | OVERHEAD TRANSFORMERS | 015 | KERN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 2,920.000 | 2,920.000 | 08J | 03/05/2013 | 2013 | 09/12/2015 | 2015 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30981137_R5 7TH STANDARD 1103 ANNEALED C | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 190061.11
30981190 | OC4 OCGC 2014 FRUITVALE 2108 RECONDUCTOR | 106769348 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/27/2014 | ED.25339.2108.TXFR.TROH | OVERHEAD TRANSFORMERS | 015 | KERN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 1,940.000 | 2,200.000 | 08J | 03/06/2013 | 2013 | 10/31/2015 | 2015 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30981190_R5 RECONDUCTOR 2,059' 4AR-FRUIT | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 256153.31
30981191 | OC4 OCGC 2014 PANAMA 2101 RECONDUCTOR | 106779571 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 07/01/2014 | ED.25342.2101.TXFR.TROH | OVERHEAD TRANSFORMERS | 015 | KERN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 2,772.000 | 2,772.000 | 08J | 03/06/2013 | 2013 | 03/19/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30981191_R5 RECONDUCTOR 2,381FT 6CU - PA | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 123290.86
30981255 | OCGC RECOND 2040' 4C W/397A, WILLIAMS RD | 106780764 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 08/29/2014 | ED.18201.1109.TXFR.TROH | OVERHEAD TRANSFORMERS | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 2,829.000 | 2,829.000 | 08J | 03/06/2013 | 2013 | 06/16/2018 | 2018 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30981255_R2RECOND 2040 FT 4CW/397A, WILL | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 255701.51
30981268 | OCGC DUNNIGAN 1101 RECOND PH 1 - ROAD 5 | 106787164 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/20/2013 | ED.06381.1101 | DUNNIGAN 1101 | 057 | YOLO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 1,355.000 | 1,355.000 | 08J | 03/06/2013 | 2013 | 03/19/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30981268_RECONDUCTOR, 063811101, ROAD 5, | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 86172.67
30981269 | OCGC DUNNIGAN 1101 RECOND, PH 2 Y2016 | 106787200 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/20/2013 | ED.06381.1101 | DUNNIGAN 1101 | 057 | YOLO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 4,600.000 | 4,600.000 | 08J | 03/06/2013 | 2013 | 07/20/2019 | 2019 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30981269_Dunnigan 1101 reconductor phase | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 155145.96
30981321 | OC4 GC 2014 MAGUNDEN 1104 RECONDUCTOR | 106779573 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/27/2014 | ED.25277.1104.SWIT | SWITCHES | 015 | KERN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 1,678.000 | 1,678.000 | 08J | 03/06/2013 | 2013 | 07/18/2015 | 2015 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30981321_R5 RECON 1,890' 6CU-MAGUNDEND 1 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 249863.54
30981325 | Z 2016 MAGUNDEN 1108 RECONDUCTR ANNEAL | 106779577 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/31/2017 | ED.25277.1104.SWIT | SWITCHES | 015 | KERN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 1,960.000 | 2,126.000 | 08J | 03/06/2013 | 2013 | 03/10/2018 | 2018 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30981325_R5 RECON 1960'6CU-MAGUNDEN 1108 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 118664.89
30981327 | OC4 RECON 800FT 4AR - BAKERSFIELD 1110 | 106779775 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/20/2013 | ED.25337.1110.SWIT | SWITCHES | 015 | KERN COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 825.000 | 0.000 | 08W | 03/06/2013 | 2013 | 02/06/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 75385.09
30981330 | 2015 MCFARLAND 1104 RECONDUCTOR | 106779871 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 07/01/2015 | ED.25318.1104.SWIT | SWITCHES | 015 | KERN COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 5,909.000 | 4,909.000 | 08W | 03/06/2013 | 2013 | 03/19/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | R5 MCFARLAND 1104 RECONDUCTOR ANNEALED | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 238873.48
30981339 | OC4 OCGC 2014 MAGUNDEN 1105 RECONDUCTR A | 106779610 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/27/2014 | ED.25277.1101.SWIT | SWITCHES | 015 | KERN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 2,394.000 | 2,394.000 | 08J | 03/06/2013 | 2013 | 08/08/2015 | 2015 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30981339_R5 MAGUNDEN 1105 ANNEALED CONDU | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 230373.18
30981418 | 2017 WASCO 1102_1104 RECONDUCTOR | 106779872 | # | Not assigned | 40 | Closed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 09/28/2018 | ED.25296.1104.SWIT | SWITCHES | 015 | KERN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 6,138.000 | 6,138.000 | 08J | 03/07/2013 | 2013 | 07/20/2019 | 2019 | CLSD | E070 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30981418_R5 RECNDCTR 6,728FT 6CU- WASCO | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 921023.33
30981440 | OC4 OCGC 2014 MAGUNDEN 2109 RECNDUCTR AN | 106779672 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/27/2014 | ED.25277.2108.SECT | SECTIONALIZERS | 015 | KERN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 2,650.000 | 2,643.000 | 08J | 03/06/2013 | 2013 | 02/20/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30981440_R5 RECON 2,650FT 6CU&4AR - MAGU | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 361464.51
30981442 | OC4 2014 MAGUNDEN 1108 RECONDUCTOR | 106747715 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 05/30/2014 | ED.25277.1108.SWIT | SWITCHES | 015 | KERN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 3,295.000 | 08J | 03/06/2013 | 2013 | 10/17/2015 | 2015 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30981442_R5 RECONDUCTOR MAGUNDEN 1108_06 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 249327.1
30981444 | OCGC 2015 BAKERSFIELD 2108 WIREDOWN | 106747753 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/27/2015 | ED.25337.2107.SWIT | SWITCHES | 015 | KERN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 885.000 | 885.000 | 08J | 03/06/2013 | 2013 | 03/19/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30981444_R5 WIREDOWN BAKERSFIELD 2108_08 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 85925.5
30981464 | OCGC FH 1101 2809 STAR ZONE - 21 CUTOVER | 106786777 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/01/2014 | ED.18295.1101 | FOOTHILL 1101 | 040 | SAN LUIS OBISP | 5535457 | DO 08 - Monthly Forecast Only | 677.000 | 677.000 | 08J | 03/06/2013 | 2013 | 11/14/2015 | 2015 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30981464_R5 Z FH 1101 2809 STAR ZONE_08J | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 121478.63
30981465 | Z MB 1101 OCB STAR ZONE PHASE 1 | 106786774 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/01/2014 | ED.18301.1101 | MORRO BAY 1101 | 040 | SAN LUIS OBISP | 5535457 | DO 08 - Monthly Forecast Only | 1,737.000 | 1,737.000 | 08J | 03/06/2013 | 2013 | 11/07/2015 | 2015 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30981465_R5 MB 1101 OCB STAR ZONE PHASE | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 275627.47
30981466 | OCLH+BPO PERRY 1101 9209 STAR ZONE | 106786738 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/01/2014 | ED.18307.1101 | PERRY 1101 | 040 | SAN LUIS OBISP | 5535457 | DO 08 - Monthly Forecast Only | 891.000 | 0.000 | 08J | 03/06/2013 | 2013 | 10/04/2014 | 2014 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 30359.7
30981467 | OCGC *PERRY 1101 9185 STAR ZONE | 106786734 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/01/2014 | ED.18307.1101 | PERRY 1101 | 040 | SAN LUIS OBISP | 5535457 | DO 08 - Monthly Forecast Only | 1,570.000 | 1,565.000 | 08J | 03/06/2013 | 2013 | 08/08/2015 | 2015 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30981467_R5 PERRY 1101 9185 STAR ZONE_08 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 178585.17
30981469 | OCGC PERRY 1101 14047 STAR ZONE | 106786736 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/01/2014 | ED.18307.1101 | PERRY 1101 | 040 | SAN LUIS OBISP | 5535457 | DO 08 - Monthly Forecast Only | 2,684.000 | 0.000 | 08J | 03/06/2013 | 2013 | 08/08/2015 | 2015 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30981469_R5 PERRY 1101 14047 STAR ZONE_0 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 208514.07
30981484 | 2015 RIO BRAVO 1101 RECONDUCTOR | 106779876 | # | Not assigned | 40 | Closed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 03/27/2015 | ED.25286.1101.SWIT | SWITCHES | 015 | KERN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 5,567.000 | 0.000 | 08J | 03/07/2013 | 2013 | 09/03/2016 | 2016 | CLSD | E070 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30981484_R5 RECNDCTR 5,868FT 6CU - RIO B | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 769447.91
30981550 | OC4 OCGC 2014 WESTPARK 1108_1110 RECONDU | 106779879 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/27/2014 | ED.25370.1108.SWIT | SWITCHES | 015 | KERN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 2,801.000 | 2,801.000 | 08J | 03/07/2013 | 2013 | 06/10/2017 | 2017 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30981550_R5 RECOND 2,794FT 2CU-WESTPARK | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 516406.78
30981552 | 2016 WHEELER RIDGE 1101 RECONDUCTOR | 106779978 | # | Not assigned | 40 | Closed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 06/27/2014 | ED.25348.1101.SWIT | SWITCHES | 015 | KERN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 6,252.000 | 6,252.000 | 08J | 03/07/2013 | 2013 | 06/17/2017 | 2017 | PREC | E070 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30981552_Wheeler Ridge 1101 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 307957.17
30981553 | OCGC 2014 WHEELER RIDGE 1101 RECONDUCTOR | 106779979 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/27/2014 | ED.25341.1103.SWIT | SWITCHES | 015 | KERN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 1,350.000 | 1,350.000 | 08J | 03/07/2013 | 2013 | 03/07/2015 | 2015 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30981553_R5 RECOND 1,350FT 6CU-WHEELER R | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 71102.92
30981557 | 2016 WHEELER RIDGE 1102 RECONDUCTOR | 106780130 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/27/2014 | ED.25348.1102.SWIT | SWITCHES | 015 | KERN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 5,424.000 | 5,500.000 | 08J | 03/07/2013 | 2013 | 12/17/2016 | 2016 | PREC | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30981557_Wheeler Ridge 1102 Reconductor | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 265182.44
30981558 | ARVIN 1103 RECONDUCTOR | 106780132 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/27/2014 | ED.25348.1102.SWIT | SWITCHES | 015 | KERN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 5,380.000 | 5,380.000 | 08J | 03/07/2013 | 2013 | 12/22/2018 | 2018 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30981558_R5 2015 ARVIN 1103 RECONDUCTOR | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 181240.9
30981641 | RECOND 1608FT 2CU-SAN BERNARD 1101 | 106780135 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/27/2014 | ED.25319.1101.TXFR.TROH | OVERHEAD TRANSFORMERS | 015 | KERN COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 1,608.000 | 1,608.000 | 08W | 03/07/2013 | 2013 | 03/19/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | RECOND 1608FT 2CU-SAN BERNARD 1101 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 66663.97
30981728 | OC4 OCGC BULLARD 1110 RCNDCT TAP ON SANP | 106684670 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/07/2014 | ED.25396.1110 | BULLARD 1110 | 010 | FRESNO COUNTY | 5517127 | DO 08 - Monthly Forecast Only | 711.000 | 710.000 | 08J | 03/08/2013 | 2013 | 04/14/2018 | 2018 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 79052.51
30981763 | OCGC 2014 LAMONT 1106 RECONDUCTOR | 106780200 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/27/2014 | ED.25297.1106.SWIT | SWITCHES | 015 | KERN COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 9,038.000 | 9,038.000 | 08W | 03/08/2013 | 2013 | 04/11/2015 | 2015 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30981763_R5 2015 LAMONT 1106 RECONDUCTO | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 239261.42
30981767 | 2016 WEEDPATCH 1106 RECON DIGIORGIO | 106780204 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/27/2014 | ED.25297.1106.SWIT | SWITCHES | 015 | KERN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 4,199.000 | 4,199.000 | 08J | 03/08/2013 | 2013 | 03/25/2017 | 2017 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Weedpatch 1106 - Reconductor 4,150 Ft of | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 127977.26
30981768 | 2016 WEEDPATCH 1106 RECOND VINELAND | 106780207 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/27/2014 | ED.25297.1106.SWIT | SWITCHES | 015 | KERN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 5,889.000 | 5,889.000 | 08J | 03/08/2013 | 2013 | 03/25/2017 | 2017 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30981768_Weedpatch 1106 Reconductor | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 200834.72
30981770 | R5 2017 TAFT 1108 RECONDUCTOR | 106780260 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 05/01/2020 | JY | JUNK YARD FL TO HOLD DELETED DATA | 015 | KERN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 3,798.000 | 3,798.000 | 08J | 03/08/2013 | 2013 | 08/08/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30981770_Taft1108 RECONDUCTOR | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 285896.17
30981774 | OC4 2014 POSO MNT 2101 RECONDUCTOR PH 2 | 106746061 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 05/30/2014 | ED.25364.2101.CAPA | CAPACITORS | 015 | KERN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 03/08/2013 | 2013 | 10/31/2015 | 2015 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30981774_R5 RECONDUCTR 5,270FT POSO MOUN | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 159150.11
30981874 | OC4 2014 CHARCA 1103 RECONDUCTOR | 106745328 | # | Not assigned | 40 | Closed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 06/02/2014 | ED.25450.1103.CAPA | CAPACITORS | 015 | KERN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 6,813.000 | 0.000 | 08J | 03/08/2013 | 2013 | 12/13/2015 | 2015 | CLSD | E070 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30981874_R5 RECONDUCTOR 7,500' +- CHARCA | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 530005.2
30982452 | OC4 OCGC LINCOLN 2108 RECONDUCTOR, SEGO | 106824493 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/26/2014 | ED.15370.2108 | LINCOLN 2108 | 031 | PLACER COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 5,005.000 | 5,005.000 | 08J | 03/12/2013 | 2013 | 03/03/2018 | 2018 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30982452_RECONDUCTOR, 153702108, SEGO LA | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 388808.65
30982557 | *CANC*ELK 1101-REPL SPLICES STRM LN*CANC | 106825286 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/27/2013 | ED.04298.1101.RECL | RECLOSERS | 023 | MENDOCINO COUN | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 03/13/2013 | 2013 | 08/05/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
30982558 | *CANC* GUALALA 1112- REPLACE MAINLINE SP | 106825256 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2013 | ED.04284.1112.SWIT | SWITCHES | 023 | MENDOCINO COUN | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 03/13/2013 | 2013 | 07/18/2015 | 2015 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
30982568 | OC4 LKVL1101RECOND3SPAN-BRWNSRDLKVLHW,PE | 106817807 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2013 | ED.04337.1101 | LAKEVILLE 1101 | 049 | SONOMA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 579.000 | 0.000 | 08W | 03/12/2013 | 2013 | 05/16/2015 | 2015 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 54203.74
30982595 | OCGC PLUMAS 2107 RECON. FOR WIRE DOWN | 106804321 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 01/03/2014 | ED.15373.2107.TXFR.TROH | OVERHEAD TRANSFORMERS | 058 | YUBA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 4,705.000 | 4,705.000 | 08J | 03/13/2013 | 2013 | 06/18/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30982595_Broadway St. Reconductor - Plum | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 258451.57
30982596 | 0C4 OCGC MERIDIAN 1101-REC 13SPANS-SW4 | 106825360 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/28/2013 | ED.06254.1101.SWIT | SWITCHES | 006 | COLUSA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 3,126.000 | 0.000 | 08J | 03/13/2013 | 2013 | 02/20/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 225111.07
30982640 | OC4 OCGC INSTREEW-5600MARSHALLPTLMA,OLEM | 106825294 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2013 | ED.04229.1101 | OLEMA 1101 | 049 | SONOMA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 1,170.000 | 0.000 | 08W | 03/13/2013 | 2013 | 12/13/2015 | 2015 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 152959.63
30982644 | RECON 2,600' 6C W/4AR_MADERA 1119 WI | 106817660 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/10/2015 | ED.25276.1119 | MADERA 1119 | 020 | MADERA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 2,622.000 | 2,622.000 | 08J | 03/13/2013 | 2013 | 05/14/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30982644_RECON 2,600' 6C W/4AR_MADERA 11 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 87944.21
30982688 | OC4 OCGC SISQUOC 1103 PHS 1 (WHITE ROCK | 106825530 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/01/2014 | ED.18263.1108 | SAN LUIS OBISPO 1108 | 040 | SAN LUIS OBISP | 5535457 | DO 08 - Monthly Forecast Only | 2,378.000 | 2,300.000 | 08J | 03/13/2013 | 2013 | 10/17/2015 | 2015 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30982688_R5 SISQUOC 1103 WD 13-0013321 P | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 226232.69
30982690 | OC4 SLO 1108 WD 12-0081243 | 106825499 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/01/2014 | ED.18263.1108 | SAN LUIS OBISPO 1108 | 040 | SAN LUIS OBISP | 5535457 | DO 08 - Monthly Forecast Only | 1,717.000 | 1,717.000 | 08J | 03/13/2013 | 2013 | 04/09/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30982690_R5 SLO 1108 WD 12-0081243_08J | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 280684.74
30982691 | OCGC +DIVIDE 1102 WD 13-0009119 PHS 1 | 106825498 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/01/2014 | ED.18257.1101 | DIVIDE 1101 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 2,340.000 | 2,340.000 | 08J | 03/13/2013 | 2013 | 02/20/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 243403.8
30982693 | OCGC SISQUOC 1102 PHS 1 (RESERVOIR) | 106825497 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/01/2014 | ED.18281.1102 | SISQUOC 1102 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 1,167.000 | 1,167.000 | 08J | 03/13/2013 | 2013 | 09/19/2015 | 2015 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30982693_R5 SISQUOC 1102 WD 13-0006447 P | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 112969.91
30982694 | OCCC +Z DIVIDE 1102 WD 13-0006459 | 106825496 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/01/2014 | ED.18206.1107 | FAIRWAY 1107 | 042 | SANTA BARBARA | 5532479 | CWSP 08W - Monthly Forecast Only | 745.000 | 0.000 | 08W | 03/13/2013 | 2013 | 09/17/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 356128.14
30982695 | OC4 +FAIRWAY 1107 (A ST <(>&<)> SONYA) | 106825495 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/01/2014 | ED.18206.1107 | FAIRWAY 1107 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 2,108.000 | 2,108.000 | 08J | 03/13/2013 | 2013 | 08/27/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30982695_R5 FAIRWAY 1107 WD 13-0005115 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 286572.68
30982696 | +SANTA MARIA 1106 (CRESTON & MCCLELLAND) | 106825494 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/01/2014 | ED.18267.1106 | SANTA MARIA 1106 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 638.000 | 0.000 | 08J | 03/13/2013 | 2013 | 11/17/2018 | 2018 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 32426.86
30982697 | OCLH SANTA MARIA 1109 WD 12-0081123 | 106825493 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/01/2014 | ED.18267.1109 | SANTA MARIA 1109 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 628.000 | 628.000 | 08J | 03/13/2013 | 2013 | 03/19/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 32676.49
30982698 | *CANC* SISQUOC 1104 WD 12-79277 *CANC | 106825492 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/01/2014 | ED.18281.1104 | SISQUOC 1104 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 03/13/2013 | 2013 | 07/03/2014 | 2014 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
30982719 | OCGC XREC BYD FUSE 20183 OFF NUTTING | 106830752 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 07/25/2014 | ED.18226.1103 | BUENA VISTA 1103 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 1,150.000 | 1,150.000 | 08J | 03/13/2013 | 2013 | 07/23/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 40154.01
30982830 | OCGCFAIRHAVEN 1103 REMOVE EXCESS SPLICES | 106831646 | # | Not assigned | 30 | Technically Completed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 07/11/2018 | ED.19245.1103.SWIT | SWITCHES | 012 | HUMBOLDT COUNT | 5535457 | DO 08 - Monthly Forecast Only | 2,440.000 | 2,440.000 | 08J | 03/14/2013 | 2013 | # | #VALUE! | FICL | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30982830_R6 FAIRHAVEN 1103 REMOVE EXCESS | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 950155.44
30982879 | OCGC REPLACE #6CU W/#2ACSR - WIREDOWN | 106829723 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 08/30/2013 | ED.15230.1102.TXFR.TROH | OVERHEAD TRANSFORMERS | 031 | PLACER COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 765.000 | 765.000 | 08J | 03/14/2013 | 2013 | 03/19/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 44320.28
30982901 | OC4 OCGC TRACY 1106 RECOND 4850' 6CU TO | 106772687 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/28/2014 | ED.16288.1106 | TRACY 1106 | 039 | SAN JOAQUIN CO | 5535457 | DO 08 - Monthly Forecast Only | 5,242.000 | 5,250.000 | 08J | 03/13/2013 | 2013 | 03/19/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | R4 TRACY 1106 RECOND 4850' 6CU TO 4/0AL | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 290291.69
30982907 | OC4 OCGC - SISQUOC 1103 PHS 2 (WHITE ROC | 106830736 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 05/01/2014 | ED.18281.1103 | SISQUOC 1103 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 2,844.000 | 2,549.000 | 08J | 03/13/2013 | 2013 | 03/19/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30982907_R5 SISQUOC 1103 WD 13-0013321 P | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 137103.15
30983000 | OCGC REPLACE #4ACSR W/#2ACSR - WIREDOWN | 106829638 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 08/30/2013 | ED.15308.2106.TXFR.TROH | OVERHEAD TRANSFORMERS | 009 | EL DORADO COUN | 5535457 | DO 08 - Monthly Forecast Only | 342.000 | 0.000 | 08J | 03/14/2013 | 2013 | # | #VALUE! | DOCC | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 45230.52
30983160 | OCGC TERMINOUS 1103 CIRCUIT RECOND 6CU | 106832253 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 05/31/2014 | ED.16302.1103 | TERMINOUS 1103 | 039 | SAN JOAQUIN CO | 5535457 | DO 08 - Monthly Forecast Only | 8,025.000 | 8,025.000 | 08J | 03/14/2013 | 2013 | 09/10/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30983160_R4 TERMINOUS 1103 CIRCUIT RECON | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 336716.68
30983162 | OC4 OCGC TERMINOUS 1102 CIRCUIT-EMPIRE | 106832208 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 05/31/2014 | ED.16302.1102 | TERMINOUS 1102 | 039 | SAN JOAQUIN CO | 5535457 | DO 08 - Monthly Forecast Only | 11,247.000 | 11,250.000 | 08J | 03/14/2013 | 2013 | 08/13/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | R2 TERMINOUS 1102 CIRCUIT-EMPIRE TRCT | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 463349.71
30983238 | _PODVA_RECONDUCTOR_RESEARCH 2102 | 106832561 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/21/2014 | ED.01469.2102 | RESEARCH 2102 | 007 | CONTRA COSTA C | 5535457 | DO 08 - Monthly Forecast Only | 1,380.000 | 1,380.000 | 08J | 03/15/2013 | 2013 | 01/26/2019 | 2019 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30983238_R1_2014_PODVA_RECONDUCTOR_RESEA | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 252615.07
30983264 | 2014 ANGIOLA 1104 RECONDUCTOR | 106834086 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/01/2014 | ED.25215.1104 | ANGIOLA 1104 | 016 | KINGS COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 5,707.000 | 5,710.000 | 08J | 03/15/2013 | 2013 | 02/20/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30983264_R2 ANGIOLA 1104 RE-CONDUCTOR_06 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 439584.28
30983276 | OC4 2014 KERMAN 1102 OVERLOADS | 106834604 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 05/01/2014 | ED.25271.1102 | KERMAN 1102 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 4,560.000 | 0.000 | 08J | 03/15/2013 | 2013 | 12/10/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30983276_R2 KERMAN 1102 OVERLOADS_06E | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 420646.88
30983299 | OCCC_BAY MEADOWS 1103 REPL ONE SPAN | 106830681 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 08/28/2014 | ED.02401.1103.SWIT | SWITCHES | 041 | SAN MATEO COUN | 5505513 | PN-OH ANNEALED/DETER CNDCTR: PM MGD | 0.000 | 0.000 | 08J | 03/15/2013 | 2013 | 10/21/2017 | 2017 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30983299_REPLACE ONE SPAN OH BM1103_08J | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 112506.13
30983940 | +RECONDUCTOR 2 SPANS LEMOORE 1101 | 106835881 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/05/2014 | ED.25360.1101.RECL | RECLOSERS | 016 | KINGS COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 950.000 | 0.000 | 08J | 03/18/2013 | 2013 | # | #VALUE! | DOCC | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 96283.53
30983942 | OC4 2014 JACOBS CORNER 1101 RECONDUCTOR | 106831916 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/04/2014 | ED.25477.1101.RECL | RECLOSERS | 016 | KINGS COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 12,243.000 | 08J | 03/18/2013 | 2013 | 12/10/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30983942_R2 RECON 13,000' OF 4AR J CORNE | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 417309.56
30983944 | +MB 1101 OCB STAR ZONE PHS 2 | 106836440 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/01/2014 | ED.18301.1101 | MORRO BAY 1101 | 040 | SAN LUIS OBISP | 5535457 | DO 08 - Monthly Forecast Only | 2,500.000 | 0.000 | 08J | 03/18/2013 | 2013 | 08/08/2015 | 2015 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | R5 MB 1101 OCB STAR ZONE PHS 2 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 361989.99
30983947 | OCGC 2014 KETTLEMAN 1101 RECONDUCTOR | 106836586 | # | Not assigned | 40 | Closed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 09/27/2014 | ED.25273.1101 | KETTLEMAN HILLS 1101 | 016 | KINGS COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 3,300.000 | 08J | 03/18/2013 | 2013 | 01/10/2015 | 2015 | CLSD | E070 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30983947_R2 KETTLEMAN 1101 RE-CONDUCTOR | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 96340.74
30984061 | OCGC+HOT - SISQUOC 1103 (CAMBRIA WINERY) | 106838766 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/01/2014 | ED.18281.1103 | SISQUOC 1103 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 9,654.000 | 9,654.000 | 08J | 03/18/2013 | 2013 | 03/19/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | R5 SISQUOC 1103 WD@7477 12-70633 PHS 1 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 491404.85
30984062 | *CANC* R5 SISQUOC 1103 WD@7477 12-7*CANC | 106838768 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/01/2014 | ED.18281.1103 | SISQUOC 1103 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 03/18/2013 | 2013 | 11/05/2014 | 2014 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | R5 SISQUOC 1103 WD@7477 12-70633 PHS 2 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
30984063 | *CANC* R5 SISQUOC 1103 WD@7477 12-7*CANC | 106838780 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/01/2014 | ED.18281.1103 | SISQUOC 1103 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 03/18/2013 | 2013 | 11/05/2014 | 2014 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | R5 SISQUOC 1103 WD@7477 12-70633 PHS 3 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
30984064 | *CANC* R5 SISQUOC 1103 WD@7477 12-7*CANC | 106838782 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/01/2014 | ED.18281.1103 | SISQUOC 1103 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 03/18/2013 | 2013 | 11/05/2014 | 2014 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | R5 SISQUOC 1103 WD@7477 12-70633 PHS 4 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
30984065 | +SISQUOC 1103 PH 5&6 (CAMBRIA WINERY) | 106838785 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/01/2014 | ED.18281.1103 | SISQUOC 1103 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 4,412.000 | 4,412.000 | 08J | 03/18/2013 | 2013 | 10/03/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | R5 SISQUOC 1103 WD@7477 12-70633 PHS 6 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 98879.04
30984066 | *CANC* R5 SISQUOC 1103 WD@7477 12-7*CANC | 106838784 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/01/2014 | ED.18281.1103 | SISQUOC 1103 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 03/18/2013 | 2013 | 11/05/2014 | 2014 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | R5 SISQUOC 1103 WD@7477 12-70633 PHS 5 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
30984220 | OC4 2014 DEVILS DEN 1101 RECONDUCTOR | 106840105 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/28/2014 | ED.25345.1101 | DEVILS DEN 1101 | 016 | KINGS COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 5,700.000 | 08J | 03/19/2013 | 2013 | 10/31/2015 | 2015 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30984220_R2 DEVILS DEN 1101 6CU RECONDUC | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 273933.98
30984501 | *CANC* DIVIDE 1102 WD 13-0009119 PHS2 | 106840348 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/01/2014 | ED.18257.1102 | DIVIDE 1102 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 03/21/2013 | 2013 | 11/29/2014 | 2014 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
30984504 | *CANC* R5 DIVIDE 1102 WD 13-0009119*CANC | 106841454 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/01/2014 | ED.18257.1102 | DIVIDE 1102 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 03/21/2013 | 2013 | 07/03/2015 | 2015 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
30984505 | *CANC* DIVIDE 1102 WD 13-0009119 PHS3 | 106841455 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/01/2014 | ED.18257.1102 | DIVIDE 1102 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 03/21/2013 | 2013 | 10/04/2014 | 2014 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
30984507 | OC4 OCG BPO+SISQUOC 1102 PHS 2 - FOXEN C | 106841777 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/01/2014 | ED.18281.1102 | SISQUOC 1102 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 2,615.000 | 2,615.000 | 08J | 03/21/2013 | 2013 | 02/20/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30984507_R5 SISQUOC 1102 WD 13-0006447 P | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 143568.91
30984641 | OCLH PARL 1103 RECON 2 SPANS 800' OF 2CU | 106842302 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/13/2013 | ED.25229.1103.SWIT | SWITCHES | 010 | FRESNO COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 982.000 | 0.000 | 08W | 03/21/2013 | 2013 | 02/14/2015 | 2015 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 39517.24
30984679 | OC4 2014 KERMAN 1108 OVRLOAD & LOW VOLT | 106842869 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/01/2014 | ED.25271.1108 | KERMAN 1108 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 5,752.000 | 5,752.000 | 08J | 03/21/2013 | 2013 | 02/20/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30984679_R2 KERMAN 1108 OVELOADS AND LOW | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 416606.06
30984686 | OCGC PIERCY 2110 RECONDUCTOR | 106842865 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2013 | ED.08391.2110.RECL | RECLOSERS | 043 | SANTA CLARA CO | 5535457 | DO 08 - Monthly Forecast Only | 3,060.000 | 2,310.000 | 08J | 03/21/2013 | 2013 | 03/19/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 230606.62
30984721 | *CANC* SISQUOC 1102 WD 13-0006447 P*CANC | 106842788 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/01/2014 | ED.18281.1102 | SISQUOC 1102 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 03/21/2013 | 2013 | 01/05/2015 | 2015 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
30984722 | *CANC* SISQUOC 1102 WD 13-0006447*CANC | 106842787 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/01/2014 | ED.18281.1102 | SISQUOC 1102 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 03/21/2013 | 2013 | 01/05/2015 | 2015 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
30984725 | *CANC* CAY 1102 WD 12-69012 PHS 2 | 106842669 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/01/2014 | ED.18255.1102 | CAYUCOS 1102 | 040 | SAN LUIS OBISP | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 03/21/2013 | 2013 | 12/14/2013 | 2013 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
30984775 | OCGC 93PL OH DET WIRE ON NAPA 1104 | 106842607 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/31/2014 | ED.04202.1104 | NAPA 1104 | 028 | NAPA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 462.000 | 0.000 | 08W | 03/22/2013 | 2013 | 08/19/2017 | 2017 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 239082.26
30985042 | *CANC* REPL OH DET WIRE ON PUEBLO 2103 | 106844998 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/31/2014 | ED.04329.2103 | PUEBLO 2103 | 028 | NAPA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 03/23/2013 | 2013 | 08/17/2013 | 2013 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
30985765 | OC4 OCGC LINDEN 1103 RECONDUCTOR COMSTO | 106849009 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/26/2014 | ED.16207.1103 | LINDEN 1103 | 039 | SAN JOAQUIN CO | 5535457 | DO 08 - Monthly Forecast Only | 3,260.000 | 3,260.000 | 08J | 03/27/2013 | 2013 | 03/19/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 68964.21
30985768 | OCGC2014 DEVILS DEN 1101 RECND ANNEAL #1 | 106848682 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/26/2014 | ED.25345.1101 | DEVILS DEN 1101 | 016 | KINGS COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 5,366.000 | 5,400.000 | 08J | 03/27/2013 | 2013 | 01/23/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30985768_R2 DEVILS DEN 1101 #1 ANNEALED | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 131870.27
30985802 | OCGC 2014 DEVILS DEN 1101 RECON ANNEAL#2 | 106848707 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/26/2014 | ED.25345.1101 | DEVILS DEN 1101 | 016 | KINGS COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 3,156.000 | 3,200.000 | 08J | 03/27/2013 | 2013 | 01/23/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30985802_R2 DEVILS DEN 1101 #2 ANNEALED | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 57263.26
30985803 | OCLH BARTON 1101 4 ACSR | 106849593 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/27/2013 | ED.25357.1101 | BARTON 1101 | 010 | FRESNO COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 831.000 | 0.000 | 08W | 03/27/2013 | 2013 | 09/21/2019 | 2019 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 25107.25
30985827 | RELIABILITY IMPROVEMENT NOVATO 1104 | 106850218 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/28/2014 | ED.04221.1104.SWIT | SWITCHES | 021 | MARIN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 462.000 | 0.000 | 08J | 03/27/2013 | 2013 | 07/23/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30985827_RELIABILITY IMPROVEMENT ON NOVA | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 136294.69
30986140 | *CANC* LH FULTON 1106 REMOVE IDLE TX | 106851818 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/04/2013 | ED.04256.1106.SWIT | SWITCHES | 049 | SONOMA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 03/28/2013 | 2013 | 10/12/2013 | 2013 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
30986367 | INSTALL FUSE ON GRAND ISLAND 2226 | 106852994 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2014 | ED.06246.2226.SECT | SECTIONALIZERS | 048 | SOLANO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 390.000 | 1.000 | 08J | 03/29/2013 | 2013 | 03/19/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 14654.53
30986858 | OCGCREPL OH DET WIRE ON WILLOW PASS 2108 | 106854571 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/30/2014 | ED.01445.2104 | KIRKER 2104 | 007 | CONTRA COSTA C | 5535457 | DO 08 - Monthly Forecast Only | 729.000 | 729.000 | 08J | 04/02/2013 | 2013 | 09/24/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30986858 _REPL OH DET WIRE | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 145430.51
30986859 | *CANC* R1 REP OH DET WIRE LELAND <*CANC | 106854570 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/31/2015 | ED.01445.2104 | KIRKER 2104 | 007 | CONTRA COSTA C | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 04/02/2013 | 2013 | 06/04/2014 | 2014 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30986859_R1 REP OH DET WIRE LELAND & WI | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
30987092 | *CANC* REPL DET COND, FREEDOM & PR*CANC | 106852744 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/18/2014 | ED.08351.0403 | ERTA 0403 | 044 | SANTA CRUZ COU | 5535457 | DO 08 - Monthly Forecast Only | 820.000 | 0.000 | 08J | 04/03/2013 | 2013 | 07/03/2015 | 2015 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
30987612 | OC4 CABRILLO 1104 WD 13-1583 LOC 1 | 106860614 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/01/2015 | ED.18310.1104 | CABRILLO 1104 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 1,755.000 | 0.000 | 08J | 04/05/2013 | 2013 | 12/16/2017 | 2017 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30987612_R5 CABRILLO 1104 WD 13-1583 LOC | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 101807.5
30987613 | +CABRILLO 1104 (SURF TAP) | 106860617 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/01/2015 | ED.18310.1104 | CABRILLO 1104 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 2,343.000 | 2,037.000 | 08J | 04/05/2013 | 2013 | 02/18/2017 | 2017 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | R5 CAB 1104 WD 13-1583 LOC 2 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 97699.77
30987692 | OCGC IMPROVERELIABILITY ON IGNACIO-1104 | 106856379 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 02/28/2014 | ED.04248.1104.COND | CONDUCTOR | 021 | MARIN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 1,755.000 | 1,755.000 | 08J | 04/05/2013 | 2013 | 05/27/2017 | 2017 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30987692_RELIABILITY IMPROVEMENT ON IGNA | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 162367.66
30987882 | 2015 OAKHURST 1101 RECNDUCTR ANEAL CD | 106860222 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2014 | ED.25442.1101 | OAKHURST 1101 | 020 | MADERA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 8,402.000 | 8,402.000 | 08J | 04/07/2013 | 2013 | 08/27/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30987882_REPL. ANNEALED COND. OAKHURST 1 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 539363.1
30988779 | +CAMBRIA 1102 (CAMBRIA SUB/STATE PARK) | 106874005 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 05/01/2015 | ED.18277.1102 | CAMBRIA 1102 | 040 | SAN LUIS OBISP | 5535457 | DO 08 - Monthly Forecast Only | 1,313.000 | 1,313.000 | 08J | 04/11/2013 | 2013 | 06/10/2017 | 2017 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30988779_R5 CAMBRIA 1102 WD 13-11001 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 213776.53
30988841 | R4E REFRAME THREE POLE SS2110 AT C2044 | 106873754 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 08/30/2013 | ED.15365.2110.CAPA | CAPACITORS | 009 | EL DORADO COUN | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 04/11/2013 | 2013 | # | #VALUE! | UNSE | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 1920.72
30989646 | OC4 E WEST SAC 1109 RECONDUCTOR 700 FEET | 106878216 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/27/2014 | ED.06313.1109.TXFR.TROH | OVERHEAD TRANSFORMERS | 057 | YOLO COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 518.000 | 0.000 | 08W | 04/15/2013 | 2013 | 01/31/2015 | 2015 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 21005.96
30989894 | OCGC ARCATA 1105 REMOVE EXCESS SPLICES | 106880044 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/30/2014 | ED.19202.1105.SWIT | SWITCHES | 012 | HUMBOLDT COUNT | 5532479 | CWSP 08W - Monthly Forecast Only | 1,540.000 | 1,540.000 | 08W | 04/16/2013 | 2013 | 01/26/2019 | 2019 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30989894_ARCATA 1105 REMOVE EXCESSIVE SP | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 126013.5
30990066 | OCGC GARBERVIL 1101REPLC EXCESIV SPLICES | 106880093 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/26/2015 | ED.19222.1101.SWIT | SWITCHES | 012 | HUMBOLDT COUNT | 5535457 | DO 08 - Monthly Forecast Only | 4,400.000 | 4,723.000 | 08J | 04/17/2013 | 2013 | 03/18/2017 | 2017 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30990066_GARBERVILLE 1101 REPLC EXCESSIV | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 852317.18
30990258 | OCGC XKING CITY 1106 RECONDUCTORING | 106881449 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2015 | ED.18203.1106 | KING CITY 1106 | 027 | MONTEREY COUNT | 5532479 | CWSP 08W - Monthly Forecast Only | 3,931.000 | 4,561.000 | 08W | 04/18/2013 | 2013 | 12/26/2015 | 2015 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30990258_R2 LAYOUS RANCH RECONDUCTORING | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 241839.38
30991793 | OLEMA 1101 CIRCUIT IMPROVEMENT | 106886394 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 08/30/2014 | ED.04229.1101.COND | CONDUCTOR | 021 | MARIN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 1,191.000 | 1,191.000 | 08J | 04/23/2013 | 2013 | 07/23/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30991793_OLEMA 1101 CIRCUIT IMPROVEMENT_ | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 145336.33
30991794 | BOLINAS 1101 RELIABILITY+ IMPROVEMENT | 106886472 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 08/30/2013 | ED.04226.1101.COND | CONDUCTOR | 021 | MARIN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 319.000 | 319.000 | 08J | 04/23/2013 | 2013 | 05/14/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 81365.85
30991832 | OCLH SCHINDLER 1105 - REPLACE 2 SPANS 4 | 106887082 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/15/2013 | ED.25289.1105 | SCHINDLER 1105 | 010 | FRESNO COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 468.000 | 468.000 | 08W | 04/23/2013 | 2013 | 02/14/2015 | 2015 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 14136.46
30992568 | OCGCRPLCE 400 FT OF 2ACSR ON PIT #3 2101 | 106889846 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2015 | ED.87-C470000000 | SHASTA MAP C47 | 045 | SHASTA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 198.000 | 198.000 | 08J | 04/26/2013 | 2013 | 05/14/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 14026.03
30992704 | OC4 OCGC VICTOR 1102 WIRE DOWN RECONDUC | 106890859 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/26/2014 | ED.16328.1102 | VICTOR 1102 | 039 | SAN JOAQUIN CO | 5535457 | DO 08 - Monthly Forecast Only | 1,979.000 | 1,979.000 | 08J | 04/26/2013 | 2013 | 09/19/2015 | 2015 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 103033.12
30992890 | OC4 XRECNDUCTOR 2 SPOF 4AR TW-PRESCOTT R | 106891792 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 07/18/2014 | ED.08325.2106 | PAUL SWEET 2106 | 044 | SANTA CRUZ COU | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 04/29/2013 | 2013 | 08/16/2014 | 2014 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 14571.08
30993111 | OC4 OCGC WYANDOTTE 1105 - BLOOMER HILL R | 106890889 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/01/2015 | ED.13-D260000000 | OROVILLE MAP D26 | 004 | BUTTE COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 3,699.000 | 3,699.000 | 08J | 04/29/2013 | 2013 | 10/15/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 266980.12
30993112 | OCGC BANGOR 1101 LA PORTE RD RECON 6050' | 106890888 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/01/2015 | ED.13-J270900000 | OROVILLE MAP J2709 | 004 | BUTTE COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 4,330.000 | 4,330.000 | 08J | 04/29/2013 | 2013 | 01/21/2017 | 2017 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30993112 Bangor 1101 Recond 6,050ft OH_0 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 304755.15
30993186 | *CANC* REC 400 FT 1-0C <(>&<)> REPL SW | 106893523 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 05/22/2015 | ED.18208.2102 | LOS OSITOS 2102 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 04/29/2013 | 2013 | 05/17/2014 | 2014 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
30993194 | MEN 402 REPL 630FT &3 PLS/219 ATHERTON A | 106891098 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/18/2013 | ED.02413.0402.TXFR.TROH | OVERHEAD TRANSFORMERS | 041 | SAN MATEO COUN | 5535457 | DO 08 - Monthly Forecast Only | 665.000 | 2,750.000 | 08W | 04/30/2013 | 2013 | 01/28/2018 | 2018 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 78207.3
30993279 | OCLHRECOND 5 SPANS 4AR,@ 50/52 NASHUA RD | 106910512 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 07/12/2014 | ED.18235.2104 | CASTROVILLE 2104 | 027 | MONTEREY COUNT | 5532479 | CWSP 08W - Monthly Forecast Only | 1,456.000 | 0.000 | 08W | 04/30/2013 | 2013 | 04/11/2015 | 2015 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 20761.4
30993327 | OCLHR1 RECONDUCTOR 390' OHDUMBARTON 2111 | 106893356 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/25/2013 | ED.01447.2111 | DUMBARTON 2111 | 001 | ALAMEDA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 386.000 | 0.000 | 08W | 04/30/2013 | 2013 | 05/09/2015 | 2015 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 39185.11
30994216 | OCCC RECOND. 275 FT.NO CAMPH-GLORIA RD. | 106916243 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/24/2015 | ED.18205.2101 | SOLEDAD 2101 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 666.000 | 0.000 | 08J | 05/03/2013 | 2013 | 06/25/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 49767.91
30995111 | OCGC RPL OH COND/REMOVE BUMPS ++__401C | 106920201 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/29/2013 | ED.04255.0401 | VALLEJO C 0401 | 048 | SOLANO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 250.000 | 250.000 | 08J | 05/08/2013 | 2013 | 11/19/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 22174.04
30995130 | RECONDUCTOR 4AR LAKEVIEW 1102 | 106919977 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 01/28/2015 | ED.25341.1102.TXFR.TROH | OVERHEAD TRANSFORMERS | 015 | KERN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 540.000 | 540.000 | 08J | 05/07/2013 | 2013 | 06/13/2015 | 2015 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 22052.92
30995212 | OC4 OCGC RECON FT ROSS RD FTROSS 1121 4/ | 106920851 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/05/2014 | ED.04285.1121.SWIT | SWITCHES | 049 | SONOMA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 7,018.000 | 7,018.000 | 08J | 05/08/2013 | 2013 | 09/24/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30995212_R7 RECON FT ROSS RD FT ROSS 112 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 874426.13
30995405 | OCGC RECOND 500 FT W/ 2C, N/O SW 7553 | 106921607 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 08/01/2014 | ED.18213.1104 | GONZALES 1104 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 644.000 | 644.000 | 08J | 05/09/2013 | 2013 | 07/23/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 40256.83
30995407 | OCGC 2015 SCHINDLER 1114 RECONDUCTOR | 106920682 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/30/2015 | ED.25289.1114 | SCHINDLER 1114 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 2,706.000 | 0.000 | 08J | 05/09/2013 | 2013 | 03/10/2018 | 2018 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | R2 SCHINDLER 1114 RE-CONDUCTOR 2015 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 127303.66
30995416 | OCGC E 2015 PEORIA FLAT 1701 RECONDUCTOR | 106920066 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/27/2014 | ED.16378.1701 | PEORIA 1701 | 055 | TUOLUMNE COUNT | 5535457 | DO 08 - Monthly Forecast Only | 2,565.000 | 2,565.000 | 08J | 05/09/2013 | 2013 | 04/21/2018 | 2018 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30995416_R2E PEORIA FLAT 1701 RECOND 485 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 116962.14
30996406 | OC4 WIRE DOWN PROJ KNIGHTS LANDING 1102 | 106936067 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/30/2014 | ED.50-F180000000.STRU.POLE | YOLO F18 POLES | 057 | YOLO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 1,313.000 | 1,415.000 | 08J | 05/14/2013 | 2013 | 12/13/2014 | 2014 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 103647.08
30996729 | OC4 OCGC CALPELLA 1102 ANNEALED CONDUCTO | 106940583 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/01/2014 | ED.04341.1101.SWIT | SWITCHES | 023 | MENDOCINO COUN | 5517127 | DO 08 - Monthly Forecast Only | 2,589.000 | 2,589.000 | 08J | 05/16/2013 | 2013 | 06/16/2018 | 2018 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30996729_CALPELLA 1102 ANNEALED CONDUCTO | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 289794.51
30996891 | RECONDUCTOR ~605FT OH ON DUMBRTON 21 | 106940530 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/27/2014 | ED.01447.2111 | DUMBARTON 2111 | 001 | ALAMEDA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 694.000 | 750.000 | 08J | 05/16/2013 | 2013 | 01/28/2018 | 2018 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 43343.77
30997022 | X +RECONDUCTOR TO REMOVE SPLICES LG1106 | 106942093 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/25/2014 | ED.08202.1106.SWIT | SWITCHES | 043 | SANTA CLARA CO | 5517127 | DO 08 - Monthly Forecast Only | 562.000 | 562.000 | 08J | 05/17/2013 | 2013 | 06/16/2018 | 2018 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 51445.46
30997023 | OCGC RECONDUC TO REMOVE SPLICES LG1106 | 106942097 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/18/2014 | ED.08202.1106.SWIT | SWITCHES | 043 | SANTA CLARA CO | 5532479 | CWSP 08W - Monthly Forecast Only | 113.000 | 0.000 | 08W | 05/17/2013 | 2013 | 02/20/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 39645.86
30997578 | *CANC* RECOND W/ TREE WIRE, INST LR*CANC | 106945877 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/20/2013 | ED.01430.2110 | MEADOW LANE 2110 | 007 | CONTRA COSTA C | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 05/22/2013 | 2013 | 07/03/2014 | 2014 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
30997776 | OCGC CRK 1111 - COHASSET RD RECOND 606' | 106947720 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/31/2014 | ED.16-Q300200000 | CHICO MAP Q3002 | 004 | BUTTE COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 606.000 | 606.000 | 08J | 05/22/2013 | 2013 | 10/15/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 60061.07
30997782 | *CANC* CAMBRIA LINE RECONFIG *CANC | 106946069 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/30/2013 | ED.18277.1102 | CAMBRIA 1102 | 040 | SAN LUIS OBISP | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 05/21/2013 | 2013 | 12/03/2017 | 2017 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
30997783 | OC4+RECONDUCTOR FAIRWY 1107 AT FUCO 1219 | 106946061 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/31/2013 | ED.18206.1107 | FAIRWAY 1107 | 042 | SANTA BARBARA | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 05/21/2013 | 2013 | 11/08/2014 | 2014 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 107671.18
30999057 | RECONDUCTOR -MADISON 1105 WIRE DOWN | 106954814 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2013 | ED.50-H110000000.STRU.POLE | YOLO H11 POLES | 057 | YOLO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 810.000 | 810.000 | 08J | 05/28/2013 | 2013 | 08/27/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 24263.92
30999583 | OCGC CLOVIS 2109 RECONDUCTOR [SUNNY] | 106957119 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/27/2015 | ED.25408.2109 | CLOVIS 2109 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 2,559.000 | 2,559.000 | 08J | 05/30/2013 | 2013 | 07/23/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | R2CLOVIS 2109 RECNDUCTR 2015 (SUNNYSIDE) | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 306389.57
30999663 | 2015 BULLARD 2112 WIREDWN RECNDUCTR | 106957565 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/26/2015 | ED.25396.2112 | BULLARD 2112 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 1,481.000 | 1,728.000 | 08J | 05/30/2013 | 2013 | 07/23/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | R2 BULLARD 2112 WIREDWN RECNDUCTR 2015 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 216421.71
30999664 | OCGC 2015 CLOVIS 2109 RECONDUCTOR | 106957561 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/26/2015 | ED.25408.2109 | CLOVIS 2109 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 1,587.000 | 1,586.000 | 08J | 05/30/2013 | 2013 | 07/23/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | R2 CLOVIS 2109 WIREDWN RCONDUCTR 2015 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 108845.74
30999912 | OCGC REPL OH DET WIRE ON PUEBLO 2102 | 106958496 | # | Not assigned | 40 | Closed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 06/30/2014 | ED.04329.2102 | PUEBLO 2102 | 028 | NAPA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 1,775.000 | 1,800.000 | 08J | 05/31/2013 | 2013 | 08/27/2016 | 2016 | CLSD | E070 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 30999912_R4 REPL OH DET WIRE ON PUEBLO | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 153706.38
31000000 | OC4 BLUE LAKE 1102 DETERIORATED CONDUCTO | 106941452 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/01/2014 | ED.19218.1102.SWIT | SWITCHES | 012 | HUMBOLDT COUNT | 5535457 | DO 08 - Monthly Forecast Only | 2,905.000 | 2,905.000 | 08J | 05/31/2013 | 2013 | 06/16/2018 | 2018 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31000000_BLUE LAKE 1102 DETERIORATED CON | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 526402.42
31000316 | MALAGA 1104 FUSE INSTALL - POST ESTIMATE | 106951602 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/27/2013 | ED.25425.1104 | MALAGA 1104 | 010 | FRESNO COUNTY | 5517127 | DO 08 - Monthly Forecast Only | 1.000 | 0.000 | 08J | 06/03/2013 | 2013 | 02/16/2019 | 2019 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31000689 | OCGC UON 1101 - RECOND 453FT WIRE DOWN | 106912356 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/28/2013 | ED.16-X280000000 | CHICO MAP X28 | 004 | BUTTE COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 891.000 | 900.000 | 08J | 06/04/2013 | 2013 | 03/19/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 39933.16
31001158 | OCGCTYLER 1104-SACRAMENTO AVE RECON 610' | 106966972 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/31/2014 | ED.85-Y330000000 | TEHEMA MAP Y33 | 052 | TEHAMA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 575.000 | 575.000 | 08J | 06/07/2013 | 2013 | 05/16/2015 | 2015 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 29720.54
31001407 | MNLO 404_INST 2 C/O_RECND 300' W/TW | 106968706 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 02/13/2014 | ED.02409.0404.SWIT | SWITCHES | 041 | SAN MATEO COUN | 5505513 | PN-OH ANNEALED/DETER CNDCTR: PM MGD | 320.000 | 320.000 | 08J | 06/08/2013 | 2013 | 03/19/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 52550.86
31001492 | OC4 OCLH PLEASANTON RECONDUCTOR 2700' WI | 106967955 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/07/2014 | ED.01450.2107.TXFR.TROH | OVERHEAD TRANSFORMERS | 001 | ALAMEDA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 1,073.000 | 5,000.000 | 08W | 06/08/2013 | 2013 | 03/19/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | R1 RECONDUCTOR 2700' WIRE, PLEASANTON | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 110497.65
31001894 | OCGC XFAIRVIEW RD REPL DETERIORATED COND | 106976905 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/20/2014 | ED.18249.2104 | HOLLISTER 2104 | 035 | SAN BENITO COU | 5535457 | DO 08 - Monthly Forecast Only | 1,120.000 | 1,120.000 | 08J | 06/10/2013 | 2013 | 12/26/2015 | 2015 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 86426.91
31002081 | OCGC COTTONWOOD 1101-HICKORY 1280' Y2015 | 106978015 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/01/2014 | ED.87-S322300000 | SHASTA MAP S3223 | 045 | SHASTA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 1,314.000 | 1,314.000 | 08J | 06/11/2013 | 2013 | 04/23/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31002081_R6 REPLACE DAMAGED CONDUCTOR, H | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 288986.85
31002333 | MIDWAY 1104- INSTALL FUSE | 106980179 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 01/31/2014 | ED.25261.1104.SWIT | SWITCHES | 015 | KERN COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 160.000 | 0.000 | 08W | 06/12/2013 | 2013 | 02/14/2015 | 2015 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 22883.34
31005551 | OCCCREPL OH DET WIRE ON NAPA+ 1105 | 106996961 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/30/2014 | ED.04202.1105 | NAPA 1105 | 028 | NAPA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 120.000 | 120.000 | 08J | 06/27/2013 | 2013 | 12/17/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 55410.2
31005585 | OCGC XDEL MONTE 1101 WIREDOWN MINGO | 106996988 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/29/2013 | ED.18222.1101 | DEL MONTE 1101 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 500.000 | 595.000 | 08J | 06/27/2013 | 2013 | 10/17/2015 | 2015 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 78581.7
31006463 | OCLHXRECOND BV1102-HARKINS RD@BURTON AVE | 107007958 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 05/02/2014 | ED.18226.1102 | BUENA VISTA 1102 | 027 | MONTEREY COUNT | 5532479 | CWSP 08W - Monthly Forecast Only | 884.000 | 0.000 | 08W | 07/01/2013 | 2013 | 02/14/2015 | 2015 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 42038.75
31006807 | 2015 CALIF 1113 RECONDUCTOR WIREDOWN | 107011084 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/27/2015 | ED.25228.1113 | CALIFORNIA AVE 1113 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 1,262.000 | 1,078.000 | 08J | 07/05/2013 | 2013 | 04/30/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31006807_R2 CALIF 1113 RECONDUCTORING - | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 131563.85
31007718 | *CANC* WIRE DOWN SERVICE REL JOB *CANC | 107022713 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/01/2014 | ED.50-N180000000.STRU.POLE | YOLO N18 POLES | 057 | YOLO COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 07/11/2013 | 2013 | 09/06/2013 | 2013 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31008212 | OC4 RECON 1/0A W/397A MERRIL ST-BV 1103- | 107015037 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/26/2014 | ED.18226.1103 | BUENA VISTA 1103 | 027 | MONTEREY COUNT | 5532479 | CWSP 08W - Monthly Forecast Only | 1,415.000 | 0.000 | 08W | 07/12/2013 | 2013 | 10/17/2015 | 2015 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 104619.44
31008213 | XBUENA VISTA 1103 NUTTING 4AR | 107014901 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 07/11/2014 | ED.18226.1103 | BUENA VISTA 1103 | 027 | MONTEREY COUNT | 5532479 | CWSP 08W - Monthly Forecast Only | 760.000 | 0.000 | 08W | 07/12/2013 | 2013 | 10/17/2015 | 2015 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 51120.53
31009147 | OC4 E COTTLE 1703 RECOND 6,250FT 6CU W/ | 107029479 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/20/2014 | ED.16371.1703 | COTTLE 1703 | 050 | STANISLAUS COU | 5535457 | DO 08 - Monthly Forecast Only | 6,855.000 | 6,567.000 | 08J | 07/17/2013 | 2013 | 10/15/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31009147_R4E COTTLE 1703 RECOND. 6,250FT | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 635963.69
31009249 | RPL 800' OH CONDUCTOR GREENBRAE 1101 | 107031442 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 01/13/2014 | ED.04226.1101.COND | CONDUCTOR | 021 | MARIN COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 765.000 | 765.000 | 08W | 07/18/2013 | 2013 | 09/23/2017 | 2017 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | R4 RPL 800' OH CONDUCTOR GREENBRAE 1101 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 157965.13
31009299 | OCGCVE SPLICES FROM LINE _HWY 1103 | 107030584 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2013 | ED.04265.1103 | HIGHWAY 1103 | 048 | SOLANO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 295.000 | 295.000 | 08J | 07/18/2013 | 2013 | 06/25/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 42983.94
31009461 | *CANC* REPLACE OH CABLE _HWY 1102 *CANC | 107030483 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/06/2013 | ED.04265.1102 | HIGHWAY 1102 | 049 | SONOMA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 07/18/2013 | 2013 | 06/04/2014 | 2014 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31009551 | OCCC HMB1103 CO9067 RECONDUCTOR OH LINE | 107033849 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 05/23/2014 | ED.02410.1103.TXFR.TROH | OVERHEAD TRANSFORMERS | 041 | SAN MATEO COUN | 5505513 | PN-OH ANNEALED/DETER CNDCTR: PM MGD | 230.000 | 230.000 | 08J | 07/19/2013 | 2013 | 01/28/2018 | 2018 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 39973.21
31009552 | _BER 404_REFRAME O.H._INST 2 FUSED CO | 107034010 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 01/22/2015 | ED.02404.0404.TXFR.TROH | OVERHEAD TRANSFORMERS | 041 | SAN MATEO COUN | 5505513 | PN-OH ANNEALED/DETER CNDCTR: PM MGD | 366.000 | 0.000 | 08J | 07/19/2013 | 2013 | 12/17/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 90223.56
31009743 | OC4 OCGC PEACHTON 1101 RECON Y2015 | 107033396 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/01/2015 | ED.13-K150000000 | OROVILLE MAP K15 | 004 | BUTTE COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 10,194.000 | 10,194.000 | 08J | 07/19/2013 | 2013 | 05/12/2018 | 2018 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31009743 PEACHTON 1101 RECOND. 8000FT_8J | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 687516.35
31010993 | OCGC L1102 OH RECNDUCTORNG-PHASE 1 LA PL | 107037627 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/30/2015 | ED.02226.1102 | SF L 1102 | 038 | SAN FRANCISCO | 5535457 | DO 08 - Monthly Forecast Only | 5,631.000 | 5,631.000 | 08J | 07/25/2013 | 2013 | 01/26/2019 | 2019 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31010993_R2Z L1102 OH RECNDUCTORNG-PHAS | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 734090.44
31011322 | +FOOTHILL 1101 (LOS OSOS - LOVR) | 107048066 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/31/2015 | ED.18295.1101 | FOOTHILL 1101 | 040 | SAN LUIS OBISP | 5535457 | DO 08 - Monthly Forecast Only | 1,494.000 | 1,495.000 | 08J | 07/27/2013 | 2013 | 08/20/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31011322_R5 FH 1101 WD 13-44425 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 107235.03
31011323 | CAYUCOS 1101 (VILLA CREEK) | 107048149 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/30/2014 | ED.18255.1101 | CAYUCOS 1101 | 040 | SAN LUIS OBISP | 5535457 | DO 08 - Monthly Forecast Only | 695.000 | 714.000 | 08J | 07/27/2013 | 2013 | 08/27/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 36022.5
31011324 | OCGC XREPL DETERIORTD COND SMITH RD WAT | 107049726 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/27/2015 | ED.08319.2101 | GREEN VALLEY 2101 | 044 | SANTA CRUZ COU | 5532479 | CWSP 08W - Monthly Forecast Only | 1,870.000 | 1,870.000 | 08W | 07/27/2013 | 2013 | 09/12/2015 | 2015 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 62531.45
31013663 | OCGC LOS COCHES 1102 REPL COND LR 75272 | 107068674 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/03/2015 | ED.18215.1102 | LOS COCHES 1102 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 2,004.000 | 2,004.000 | 08J | 08/08/2013 | 2013 | 07/23/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 177172.94
31013665 | OCGC XLOS COCHES 1102 REPL COND NR 7207 | 107068676 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/03/2015 | ED.18215.1102 | LOS COCHES 1102 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 1,888.000 | 3,200.000 | 08J | 08/08/2013 | 2013 | 05/14/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 150513.09
31014122 | OCLH REPL OH COND/REMOVE BUMPS_ BAH1102 | 107068067 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2013 | ED.04325.1102 | BAHIA 1102 | 048 | SOLANO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 461.000 | 460.000 | 08J | 08/12/2013 | 2013 | 07/23/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 25278
31014511 | OCLH GUERNSEY 1104 ONE SPAN RECON | 107080669 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/27/2015 | ED.25371.1102 | HARDWICK 1102 | 016 | KINGS COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 601.000 | 601.000 | 08J | 08/14/2013 | 2013 | 10/31/2015 | 2015 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 26219.79
31014512 | OCGC MORMON 1101 08J RECONDUCTORING | 107081027 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2014 | ED.16321.1101 | MORMON 1101 | 039 | SAN JOAQUIN CO | 5535457 | DO 08 - Monthly Forecast Only | 7,680.000 | 7,680.000 | 08J | 08/14/2013 | 2013 | 09/17/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31014512_R4 MORMON 1101 08J RECONDUCTORI | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 228771.31
31014552 | OC4 OCGC RICE 1101 RECONDUCTOR - Y2015 | 107081094 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2015 | ED.06283.1101.RECL | RECLOSERS | 006 | COLUSA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 2,955.000 | 2,900.000 | 08J | 08/13/2013 | 2013 | 04/23/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31014552_RICE 1101 RECOND. WIRE DOWN_08J | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 170301.46
31015447 | OC4 OCGC 2015 CRESSEY 2103 RECONDUCTOR | 107084143 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/30/2014 | ED.25470.2103 | CRESSEY 2103 | 024 | MERCED COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 6,862.000 | 6,862.000 | 08J | 08/16/2013 | 2013 | 08/19/2017 | 2017 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | CRESEY 2103-RECN 7000' OF #4CU/W 4/OAL | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 268834.29
31015448 | OC4 OCGC CABLE REPLACEMENT -H1109- PHASE | 107084179 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/30/2014 | ED.25280.1114 | MERCED 1114 | 024 | MERCED COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 6,262.000 | 6,262.000 | 08J | 08/16/2013 | 2013 | 06/25/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31015448_R4MERCED 1114-RECON 6,000' 6CU | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 233951.71
31015449 | +FOOTHILL 1101 RECONDUCTOR SLO | 107083621 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/30/2015 | ED.18295.1101 | FOOTHILL 1101 | 040 | SAN LUIS OBISP | 5535457 | DO 08 - Monthly Forecast Only | 1,475.000 | 0.000 | 08J | 08/16/2013 | 2013 | 03/19/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31015449_R5 FOOTHILL 1101 RECONDUCTOR SL | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 112505.12
31016170 | OCGC XRECONDUCTORING PRI @ IVERSON RD | 107087278 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 01/16/2015 | ED.18213.1101 | GONZALES 1101 | 027 | MONTEREY COUNT | 5532479 | CWSP 08W - Monthly Forecast Only | 2,233.000 | 2,233.000 | 08W | 08/21/2013 | 2013 | 08/27/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 140678.69
31016336 | OCGC WOODLAND 1112 RECONDUCTOR 2AR | 107091065 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2014 | ED.50-J172200000.STRU.POLE | YOLO J1722 POLES | 057 | YOLO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 1,244.000 | 1,260.000 | 08J | 08/21/2013 | 2013 | 07/23/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 40400
31016636 | OC4 OCGC CORRAL 1101 RELOCAT 4ACSR (WIR | 107092244 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/26/2014 | ED.16299.1101 | CORRAL 1101 | 039 | SAN JOAQUIN CO | 5532479 | CWSP 08W - Monthly Forecast Only | 4,330.000 | 4,330.000 | 08W | 08/23/2013 | 2013 | 08/20/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | R2ZE CORRAL 1101 RELOCAT 4ACSR (WIREDOWN | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 163783.65
31017122 | *CANC* RECONDUCTOR SARATOGA 1107, B*CANC | 107095934 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 08/22/2014 | ED.08337.1107.RECL | RECLOSERS | 043 | SANTA CLARA CO | 5517127 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 08/26/2013 | 2013 | 10/04/2013 | 2013 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31017164 | RECOND 4 SPANS OF #6CU-R1123-HARBOUR | 107100865 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/01/2015 | ED.01347.1123 | RICHMOND R 1123 | 007 | CONTRA COSTA C | 5535457 | DO 08 - Monthly Forecast Only | 118.000 | 400.000 | 08J | 08/26/2013 | 2013 | 01/26/2019 | 2019 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 62385.13
31017530 | OCGC TEVIS 2102 3 SPANS RECONDUCTOR | 107103871 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/27/2015 | ED.25532.2102.TXFR.TROH | OVERHEAD TRANSFORMERS | 015 | KERN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 1,179.000 | 1,179.000 | 08J | 08/27/2013 | 2013 | 01/23/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | TEVIS 2102 3 SPANS RECONDUCTOR | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 63984.14
31017531 | OC4 OCGC KERN POWER 2103 4 SPANS RECONDU | 107103874 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/27/2015 | ED.25526.2103.TXFR.TROH | OVERHEAD TRANSFORMERS | 015 | KERN COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 746.000 | 0.000 | 08W | 08/27/2013 | 2013 | 05/16/2015 | 2015 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 38670.81
31017690 | +R SISQUOC 1102 PH 1 RECON GAREY/TAP) | 107101569 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2013 | ED.18281.1102 | SISQUOC 1102 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 1,406.000 | 1,406.000 | 08J | 08/28/2013 | 2013 | 12/17/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31017690_R5 WD SISQUOC 1102 PHASE 1 RECO | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 101434.21
31017691 | +SISQUOC 1102 PH 2 RECON (POND/MAINLINE) | 107101579 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/30/2014 | ED.18281.1102 | SISQUOC 1102 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 1,727.000 | 1,727.000 | 08J | 08/28/2013 | 2013 | 08/13/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31017691_R5 WD SISQUOC 1102 PHASE 2 RECO | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 96301.79
31017692 | *CANC* WD SISQUOC 1102 PHASE 3A RE*CANC | 107101631 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2014 | ED.18281.1102 | SISQUOC 1102 | 042 | SANTA BARBARA | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 08/28/2013 | 2013 | 01/05/2015 | 2015 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31017693 | *CANC* WD SISQUOC 1102 PHASE 3B RE*CANC | 107101633 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2014 | ED.18281.1102 | SISQUOC 1102 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 08/28/2013 | 2013 | 01/05/2015 | 2015 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31017694 | +BPO WD SANTA MARIA 1109 RECNDUCTR & FU | 107101848 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/01/2014 | ED.18267.1109 | SANTA MARIA 1109 | 042 | SANTA BARBARA | 5532479 | CWSP 08W - Monthly Forecast Only | 438.000 | 438.000 | 08W | 08/28/2013 | 2013 | 12/13/2014 | 2014 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 75371.23
31017867 | *CANC* WD SISQUOC 1102 PHASE 4 REC*CANC | 107101635 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2014 | ED.18281.1102 | SISQUOC 1102 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 08/29/2013 | 2013 | 01/05/2015 | 2015 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31017905 | OCGC RPLOH COND / REMOVE BUMPS_ BAH1102 | 107105779 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/31/2015 | ED.04325.1102 | BAHIA 1102 | 048 | SOLANO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 1,018.000 | 1,018.000 | 08J | 08/29/2013 | 2013 | 11/19/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 49146.43
31018158 | OCGC BELL 10-RECOND 3 SPANS PAST SW34443 | 107107504 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/27/2014 | ED.15270.1110.SWIT | SWITCHES | 031 | PLACER COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 835.000 | 835.000 | 08J | 08/30/2013 | 2013 | 08/22/2015 | 2015 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 37047.26
31018225 | OC4 OCGC MESA 1103 WD - MESA & VIVA | 107107619 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 05/01/2015 | ED.18282.1103 | MESA 1103 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 3,564.000 | 3,564.000 | 08J | 08/30/2013 | 2013 | 06/18/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | R5 MESA 1103 WD 13-54316 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 216765.78
31018226 | OCGC X HAMMER 1106 REPLACE 390 FT OF | 107108005 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/26/2015 | ED.16330.1106 | HAMMER 1106 | 039 | SAN JOAQUIN CO | 5535457 | DO 08 - Monthly Forecast Only | 383.000 | 390.000 | 08J | 08/30/2013 | 2013 | 06/16/2018 | 2018 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 54432.84
31018911 | OC4 OCGCEB_RELIABILITY C-1114_INSTALL LR | 107118566 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/01/2015 | ED.01201.1114 | OAKLAND C 1114 | 001 | ALAMEDA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 1,282.000 | 1,282.000 | 08J | 09/06/2013 | 2013 | 11/07/2015 | 2015 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31018911_EB_RELIABILITY C-1114_INSTALL L | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 306786.81
31019103 | FREMONT 1108 CKT - OH RECONDUCTORING | 107115948 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/31/2014 | ED.01435.1108 | FREMONT 1108 | 001 | ALAMEDA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 1,326.000 | 1,020.000 | 08J | 09/04/2013 | 2013 | 09/24/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 159463.52
31019262 | +DIVIDE 1103 PH4 (GREKA/LONG SPAN) | 107117151 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/01/2014 | ED.18257.1103 | DIVIDE 1103 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 2,079.000 | 2,079.000 | 08J | 09/05/2013 | 2013 | 11/19/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31019262_R5 WD DIVIDE 1103 RECONDUCTOR A | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 64484.6
31019263 | OCGC DE 1103 PH2 RECON (GREKA/UNDERBUILD | 107117152 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/01/2014 | ED.18257.1103 | DIVIDE 1103 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 2,800.000 | 0.000 | 08J | 09/05/2013 | 2013 | 05/14/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31019263_R2 WD DIVIDE 1103 PH2 RECONDUCT | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 121639.64
31019264 | OLCH OCGC+DIVIDE 1103 PH3 (BLACK & NTU) | 107117155 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/01/2014 | ED.18257.1103 | DIVIDE 1103 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 2,116.000 | 2,116.000 | 08J | 09/05/2013 | 2013 | 06/18/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31019264_R2 WD DIVIDE 1103 PH3 RECONDUCT | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 203745.76
31019265 | OCGC 2015 ORO LOMA 1115 RECONDUCTOR | 107117033 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/25/2015 | ED.25537.1108 | ORO LOMA 1108 | 024 | MERCED COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 2,485.000 | 2,485.000 | 08J | 09/05/2013 | 2013 | 04/16/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31019265_ RECONDUCTOR ORO LOMA 1108 - AN | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 186038.91
31019298 | OCGC X2102 RE-CNDCTR 1SP 42960 METZ RD. | 107118596 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2015 | ED.18208.2102 | LOS OSITOS 2102 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 377.000 | 377.000 | 08J | 09/06/2013 | 2013 | 09/24/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 21952.61
31019802 | OC4 EP REPLACE DAMAGED CONDUCT , HICKORY | 107120230 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/01/2014 | ED.14-S200000000 | GLENN MAP S20 | 011 | GLENN COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 266.000 | 0.000 | 08W | 09/08/2013 | 2013 | 01/31/2015 | 2015 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 17199.1
31020089 | OCGC COALINGA #1106 ANNEALED CND REPL & | 107131640 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/31/2015 | ED.25238.1106 | COALINGA NO 2 1106 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 410.000 | 410.000 | 08J | 09/10/2013 | 2013 | 07/23/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 87738.13
31020123 | OCGC 2015 HARDWICK 1102 RECONDUCTOR AN | 107124961 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/24/2015 | ED.25371.1102 | HARDWICK 1102 | 016 | KINGS COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 5,375.000 | 5,400.000 | 08J | 09/10/2013 | 2013 | 06/18/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | HARDWICK 1102 RECONDUCTOR ANNEALED | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 315463.03
31021152 | OC4 OCGC R2 2014 DINUBA 1105 RECONDUCTOR | 107137513 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 05/05/2014 | ED.25409.1105 | DINUBA 1105 | 054 | TULARE COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 10,577.000 | 11,519.000 | 08W | 09/13/2013 | 2013 | 07/18/2015 | 2015 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | R2 2014 DINUBA 1105 RECONDUCTOR | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 1571040.3
31022659 | OCLH RECON 1 SPAN 6C (300') S/O 7876F WD | 107155528 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/04/2014 | ED.25409.1104 | DINUBA 1104 | 054 | TULARE COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 474.000 | 0.000 | 08J | 09/19/2013 | 2013 | 03/19/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 38580.58
31024860 | ARCATA 1105 EXCESSIVE SPLICES PHASE 2 | 107165410 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/30/2015 | ED.19202.1105.SWIT | SWITCHES | 012 | HUMBOLDT COUNT | 5535457 | DO 08 - Monthly Forecast Only | 4,567.000 | 4,567.000 | 08J | 09/28/2013 | 2013 | 07/17/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31024860_ARCATA 1105 EXCESSIVE SPLICES P | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 386400.3
31025322 | *CANC* RESOLVE I2T PROBLEM ON JARVIS 1 | 107168373 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2014 | ED.01350.1112 | JARVIS 1112 | 001 | ALAMEDA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 10/01/2013 | 2013 | 11/23/2013 | 2013 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31025334 | OC4 OCCC W FRESNO 1101 RECONDUCTOR PH 1 | 107168255 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/20/2015 | ED.25373.1101 | WEST FRESNO 1101 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 6,707.000 | 6,707.000 | 08J | 10/01/2013 | 2013 | 09/19/2015 | 2015 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | R2 W FRESNO 1101 RECONDUCTOR - PH 1 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 306294.72
31025335 | 2016 W FRESNO 1101 RECONDUCTOR PH 2 | 107168258 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/19/2015 | ED.25373.1101 | WEST FRESNO 1101 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 1,718.000 | 1,718.000 | 08J | 10/01/2013 | 2013 | 12/17/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | R2 W FRESNO 1101 RECONDUCTORI PH 2 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 206266.08
31027740 | KERMAN 1106 - RECONDUCTOR & REFRAME | 107186583 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 05/30/2014 | ED.25271.1106 | KERMAN 1106 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 2,258.000 | 7,200.000 | 08J | 10/11/2013 | 2013 | 09/24/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 64785.58
31027748 | 2015 WRIGHT 1109 RECONDUCTOR | 107186814 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/25/2015 | ED.25464.1109 | WRIGHT 1109 | 024 | MERCED COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 3,426.000 | 0.000 | 08J | 10/11/2013 | 2013 | 09/10/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | WRIGHT 1109 RECOND 3497' 6CU TO 2AR | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 168698.54
31027750 | OCLH KERMAN 1106 - RE-CONDUCTOR 1 SPAN | 107147111 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 05/16/2014 | ED.25271.1106 | KERMAN 1106 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 317.000 | 951.000 | 08J | 10/11/2013 | 2013 | 10/31/2015 | 2015 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 13421.56
31028127 | REPLACE 1368 FEET OF 6C WITH 2ACSR | 107190180 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2015 | ED.06246.2227.TXFR.TROH | OVERHEAD TRANSFORMERS | 057 | YOLO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 1,368.000 | 1,368.000 | 08J | 10/14/2013 | 2013 | 02/08/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 49407.07
31028173 | OC4 +OCEANO 1103 HWY 101 REC | 107190334 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/01/2014 | ED.18260.1103 | OCEANO 1103 | 040 | SAN LUIS OBISP | 5532479 | CWSP 08W - Monthly Forecast Only | 1,487.000 | 0.000 | 08W | 10/14/2013 | 2013 | 07/18/2015 | 2015 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31028173_R2 OCEANO 1103 HWY 101 REC_08W | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 230317.2
31029181 | *CANC* SLO 1101 WD 13-57792 OCB *CANC | 107196624 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/01/2015 | ED.18263.1101 | SAN LUIS OBISPO 1101 | 040 | SAN LUIS OBISP | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 10/18/2013 | 2013 | 05/03/2018 | 2018 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31029182 | SLO 1108 RECON (MORRISON & MCMILLAN) | 107196623 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/01/2015 | ED.18263.1108 | SAN LUIS OBISPO 1108 | 040 | SAN LUIS OBISP | 5535457 | DO 08 - Monthly Forecast Only | 1,334.000 | 1,334.000 | 08J | 10/18/2013 | 2013 | 01/07/2017 | 2017 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31029182_R5 SLO 1108 WD 13-63965 C/O 965 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 104759.03
31030771 | OC4 OCGC AKA 1101 FORBESTWN RD 2724' Y | 107202805 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/01/2015 | ED.13-G311100000 | OROVILLE MAP G3111 | 004 | BUTTE COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 2,724.000 | 2,724.000 | 08J | 10/24/2013 | 2013 | 02/29/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31030771_Kanaka 1101 Forbestown Rd | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 441537.01
31030986 | OCLH HERDLYN 1102 REPLACE 727' 4AR | 107203327 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/10/2015 | ED.16374.1102 | HERDLYN 1102 | 001 | ALAMEDA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 730.000 | 850.000 | 08J | 10/24/2013 | 2013 | 12/26/2015 | 2015 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 20789.93
31031486 | OCLH WESTLEY 1101 RECOND 1083' 4AR | 107204195 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/10/2015 | ED.16267.1101 | WESTLEY 1101 | 039 | SAN JOAQUIN CO | 5535457 | DO 08 - Monthly Forecast Only | 925.000 | 925.000 | 08J | 10/26/2013 | 2013 | 12/26/2015 | 2015 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 33129.45
31032329 | OCGC WATSONVILLE, RECONDUCTOR 4 SP OH | 107209805 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/30/2015 | ED.08333.2101 | WATSONVILLE 2101 | 044 | SANTA CRUZ COU | 5535457 | DO 08 - Monthly Forecast Only | 1,220.000 | 1,220.000 | 08J | 10/31/2013 | 2013 | 12/26/2015 | 2015 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31032329_R2 WATSONVILLE, RECONDUCTOR 4 S | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 72754.69
31033139 | +OCEANO 1103 RECON (S. HALCYON RD) | 107386582 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/01/2015 | ED.18260.1103 | OCEANO 1103 | 040 | SAN LUIS OBISP | 5535457 | DO 08 - Monthly Forecast Only | 791.000 | 710.000 | 08J | 11/01/2013 | 2013 | 01/14/2017 | 2017 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 73517.05
31033160 | OCGC+MORRO BAY 1101 (MAIN ST) | 107386584 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/01/2015 | ED.18301.1101 | MORRO BAY 1101 | 040 | SAN LUIS OBISP | 5535457 | DO 08 - Monthly Forecast Only | 497.000 | 497.000 | 08J | 11/01/2013 | 2013 | 11/14/2015 | 2015 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 124362.32
31033174 | OCGC EEL RIVER1101RECOND2SPANSFERNBRIDGE | 107386667 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/01/2015 | ED.19238.1101 | EEL RIVER 1101 | 012 | HUMBOLDT COUNT | 5535457 | DO 08 - Monthly Forecast Only | 495.000 | 495.000 | 08J | 11/01/2013 | 2013 | 07/23/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 69515.06
31033175 | OCGC GARBERVILLE 1101 DET. CONDUCTOR | 107386661 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/01/2015 | ED.19222.1101 | GARBERVILLE 1101 | 012 | HUMBOLDT COUNT | 5535457 | DO 08 - Monthly Forecast Only | 838.000 | 838.000 | 08J | 11/01/2013 | 2013 | 04/21/2018 | 2018 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 170372.15
31034172 | BH 405 CO4667 RECON 300FT OH LINE | 107394877 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/29/2014 | ED.02402.0405.TXFR.TROH | OVERHEAD TRANSFORMERS | 041 | SAN MATEO COUN | 5505513 | PN-OH ANNEALED/DETER CNDCTR: PM MGD | 472.000 | 1,368.000 | 08J | 11/06/2013 | 2013 | 04/01/2017 | 2017 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 95968.17
31034467 | XSAN ARDO 1102, 3 SP/LS OF 9093 | 107393900 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/30/2015 | ED.18219.1102 | SAN ARDO 1102 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 267.000 | 267.000 | 08J | 11/07/2013 | 2013 | 05/14/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 15674.25
31034470 | *CANC* SLO 1102 WD 13-69048 | 107390773 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/01/2015 | ED.18263.1102 | SAN LUIS OBISPO 1102 | 040 | SAN LUIS OBISP | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 11/07/2013 | 2013 | 05/10/2014 | 2014 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31034471 | +MORRO BAY 1101 WD (DENEGY PLANT) | 107390777 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/01/2015 | ED.18301.1101 | MORRO BAY 1101 | 040 | SAN LUIS OBISP | 5535457 | DO 08 - Monthly Forecast Only | 525.000 | 525.000 | 08J | 11/07/2013 | 2013 | 08/27/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 31022.82
31034472 | *CANC* PERRY 1101 WD 13-71707 *CANC | 107391045 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/01/2015 | ED.18307.1101 | PERRY 1101 | 040 | SAN LUIS OBISP | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 11/07/2013 | 2013 | 05/03/2018 | 2018 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31036265 | R1128-RECNDUCTOR 3 SPANS,NSTALL CUT | 107409265 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/30/2015 | ED.01347.1128 | RICHMOND R 1128 | 007 | CONTRA COSTA C | 5532479 | CWSP 08W - Monthly Forecast Only | 535.000 | 535.000 | 08W | 11/15/2013 | 2013 | 01/28/2018 | 2018 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 75405.13
31036630 | OC4 OCGC RGH & READY1102 CO5297 ZONE R | 107413679 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2015 | ED.16308.1102 | ROUGH AND READY IS 1102 | 039 | SAN JOAQUIN CO | 5535457 | DO 08 - Monthly Forecast Only | 4,635.000 | 4,700.000 | 08J | 11/18/2013 | 2013 | 09/03/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31036630_R4 RGH & READY1102 CO5297 ZONE | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 149286.95
31036816 | OCGC ASHLN 1112 RECNDUCTR + INSTALL RECL | 107415600 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/25/2015 | ED.25205.1112 | ASHLAN AVE 1112 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 486.000 | 527.000 | 08J | 11/19/2013 | 2013 | 06/25/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 86405.64
31036817 | OCGC BARTON 1102 RECONDUCTOR | 107415603 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/25/2015 | ED.25357.1102 | BARTON 1102 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 753.000 | 753.000 | 08J | 11/19/2013 | 2013 | 10/28/2017 | 2017 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 82903.01
31036931 | OCGC PLACE ANNLD WIRE HWY 45 PH. 3 Y2017 | 107416575 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 08/01/2017 | ED.14-Y230000000 | GLENN MAP Y23 | 011 | GLENN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 6,238.000 | 6,238.000 | 08J | 11/19/2013 | 2013 | 09/09/2017 | 2017 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 310369631_ HWY. 45 PH. 3_8J | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 721691.79
31036932 | OCGC MEADOWS 2101 PRATTVILLE Y2016 8J | 107416576 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/01/2015 | ED.18-J460000000 | LAS PLUMAS MAP J46 | 032 | PLUMAS COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 4,501.000 | 4,501.000 | 08J | 11/19/2013 | 2013 | 03/25/2017 | 2017 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31036932_ Y2016 Big Meadows 2101 Prattvi | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 406905.24
31036933 | RECOND, ROAD D WILLOWS PH2 Y2017 | 107416577 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/01/2017 | ED.14-Y170000000 | GLENN MAP Y17 | 011 | GLENN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 7,929.000 | 7,629.000 | 08J | 11/19/2013 | 2013 | 04/21/2018 | 2018 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31036933_REPL COND,ROAD D, WILLOWS PH 2 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 249118.51
31037249 | OCGC LW 2112_ RECONDUCTOR W/ TREE WIRE | 107398171 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/31/2014 | ED.01353.2112 | LAKEWOOD 2112 | 007 | CONTRA COSTA C | 5535457 | DO 08 - Monthly Forecast Only | 1,045.000 | 1,045.000 | 08J | 11/20/2013 | 2013 | 04/14/2018 | 2018 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 80857.41
31037251 | OC4 OCGC REPL OH DET WIRE PAST C/O 8789 | 107417959 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/30/2015 | ED.01365.2115 | CONTRA COSTA 2115 | 007 | CONTRA COSTA C | 5535457 | DO 08 - Monthly Forecast Only | 502.000 | 936.000 | 08J | 11/20/2013 | 2013 | 11/19/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 148142.04
31037514 | OC4 OCGC STOCKTON A 411 RECONDUCTORING | 107417098 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2015 | ED.16237.0411 | STOCKTON A 0411 | 039 | SAN JOAQUIN CO | 5535457 | DO 08 - Monthly Forecast Only | 1,253.000 | 1,200.000 | 08J | 11/21/2013 | 2013 | 09/19/2015 | 2015 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 76416.65
31037633 | OCCC X2102, RE-CONDUCTR 4 SPANS, SW 7193 | 107417091 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/30/2015 | ED.18205.2102 | SOLEDAD 2102 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 861.000 | 861.000 | 08J | 11/21/2013 | 2013 | 07/23/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 92670.34
31038429 | CABRILLO 1103 (PURISIMA RD) | 107459405 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/01/2015 | ED.18310.1103 | CABRILLO 1103 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 1,528.000 | 0.000 | 08J | 11/23/2013 | 2013 | 12/10/2016 | 2016 | PREC | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | R5 WD CABRILLO 1103 13-0058079 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 73989.41
31038430 | CABRILLO 1103 (HWY 246 & HAPGOOD RD) | 107459471 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/01/2015 | ED.18310.1103 | CABRILLO 1103 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 1,271.000 | 0.000 | 08J | 11/23/2013 | 2013 | 02/11/2017 | 2017 | PREC | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | WD CABRILLO 1103 13-0048220 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 152895.12
31038431 | OC4 OCCC WD CABRILLO 1104 13-0056541 | 107459475 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/01/2015 | ED.18310.1104 | CABRILLO 1104 | 042 | SANTA BARBARA | 5532479 | CWSP 08W - Monthly Forecast Only | 7,325.000 | 7,325.000 | 08W | 11/23/2013 | 2013 | 03/19/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31038431_R2 WD CABRILLO 1104 13-0056541 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 411819.84
31038907 | WIRE DOWN - MADISON 1105 RECOND 4 SP | 107472748 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2015 | ED.06317.1105.SWIT | SWITCHES | 057 | YOLO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 987.000 | 987.000 | 08J | 11/26/2013 | 2013 | 03/03/2018 | 2018 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 44301.15
31039056 | OCGC MORMON 1102 CO1911 ZONE RECOND P1 | 107471868 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2015 | ED.16321.1102 | MORMON 1102 | 039 | SAN JOAQUIN CO | 5517127 | DO 08 - Monthly Forecast Only | 4,400.000 | 4,400.000 | 08J | 11/27/2013 | 2013 | 09/10/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31039056_ Mormon 1102 Reconductoring | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 114844.19
31039795 | MABURY 1102 WIRE DOWN 13-0077162 | 107505383 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/31/2015 | ED.08219.1102.CAPA | CAPACITORS | 043 | SANTA CLARA CO | 5532479 | CWSP 08W - Monthly Forecast Only | 130.000 | 276.000 | 08W | 12/04/2013 | 2013 | 03/19/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 30578.83
31040925 | RECONDUCT #4ACSR_W.JACKSON_HAYWRD | 107508313 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/27/2015 | ED.24-J090900000.STRU.ENCL | MISSION J0909 ENCLOSURE | 001 | ALAMEDA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 270.000 | 270.000 | 08W | 12/06/2013 | 2013 | 06/09/2018 | 2018 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 51124.06
31041867 | OCGC X MORMON 1102 CO1911 ZONE RECOND | 107523489 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2016 | ED.16321.1102 | MORMON 1102 | 039 | SAN JOAQUIN CO | 5535457 | DO 08 - Monthly Forecast Only | 2,664.000 | 2,664.000 | 08J | 12/11/2013 | 2013 | 12/13/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31041867_MORMON 1102 CO1911 ZONE RECOND | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 64407.45
31041868 | OCGC MORMON 1102 CO1911 ZONE RECOND | 107523502 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2016 | ED.16321.1102 | MORMON 1102 | 039 | SAN JOAQUIN CO | 5535457 | DO 08 - Monthly Forecast Only | 3,551.000 | 3,551.000 | 08J | 12/11/2013 | 2013 | 01/14/2017 | 2017 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31041868_MORMON 1102 CO1911 ZONE RECOND | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 88361.18
31041869 | OCGC RGH AND READY 1102 CO5297 ZONE REC | 107523509 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2016 | ED.16308.1102 | ROUGH AND READY IS 1102 | 039 | SAN JOAQUIN CO | 5535457 | DO 08 - Monthly Forecast Only | 6,151.000 | 6,151.000 | 08J | 12/11/2013 | 2013 | 11/05/2016 | 2016 | PREC | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31041869_RGH AND READY 1102 CO5297 ZONE | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 202858.32
31042419 | OCGC LOCKEFORD 2102 RECONDUCTOR PH2 | 107531228 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2016 | ED.16368.2102 | LOCKEFORD 2102 | 039 | SAN JOAQUIN CO | 5535457 | DO 08 - Monthly Forecast Only | 3,750.000 | 3,750.000 | 08J | 12/13/2013 | 2013 | 12/03/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31042419_LOCKEFORD 2102 RECONDUCTOR PHAS | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 81559.48
31042661 | +CH 1101 WIREDOWN 11000 E HWY 46 | 107531753 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/30/2015 | ED.18256.1101 | CHOLAME 1101 | 040 | SAN LUIS OBISP | 5535457 | DO 08 - Monthly Forecast Only | 2,058.000 | 2,000.000 | 08J | 12/13/2013 | 2013 | 11/19/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | R5 CH 1101 WIREDOWN 11000 E HWY 46 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 55738
31043129 | EB-RELIAIBLITY K1103-RECONDUT | 107540000 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/31/2015 | ED.01210.1103 | OAKLAND K 1103 | 001 | ALAMEDA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 400.000 | 900.000 | 08W | 12/18/2013 | 2013 | 11/24/2018 | 2018 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 85612.01
31043565 | OCCC -0081136 HOLL 2101 WIREDOWN | 107537324 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/30/2015 | ED.18249.2101 | HOLLISTER 2101 | 035 | SAN BENITO COU | 5535457 | DO 08 - Monthly Forecast Only | 97.000 | 0.000 | 08J | 12/18/2013 | 2013 | 05/18/2019 | 2019 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 67021.61
31043566 | OCGC XRECOND 500FT W. ZAYANTE RD CE 2105 | 107537285 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/14/2014 | ED.08362.2105 | CAMP EVERS 2105 | 044 | SANTA CRUZ COU | 5532479 | CWSP 08W - Monthly Forecast Only | 510.000 | 510.000 | 08W | 12/18/2013 | 2013 | 12/26/2015 | 2015 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 60459
31043567 | OCGC XRECON W/675FT TW LOKHRT GL CE 2105 | 107537288 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/20/2015 | ED.08362.2104 | CAMP EVERS 2104 | 044 | SANTA CRUZ COU | 5532479 | CWSP 08W - Monthly Forecast Only | 705.000 | 705.000 | 08W | 12/18/2013 | 2013 | 12/26/2015 | 2015 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 81309.75
31044254 | +SANTA MARIA 1110 (MAIN ST/8TH ST) | 107552853 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/01/2014 | ED.18267.1110 | SANTA MARIA 1110 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 2,174.000 | 2,174.000 | 08J | 12/21/2013 | 2013 | 12/10/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31044254_WD SANTA MARIA 1110 13-0082788 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 97661.49
31044708 | RECNDUCT 1/0 AL WIRE ON DOBBEL AVE HAYW | 107554489 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/22/2019 | ED.24-J101400000.STRU.ENCL | MISSION J1014 ENCLOSURE | 001 | ALAMEDA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 214.000 | 214.000 | 08J | 12/23/2013 | 2013 | 11/23/2019 | 2019 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 22083
31046155 | CALIF 1112 WIRE DOWN RECNDUCTOR | 107564766 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/25/2016 | ED.25228.1112 | CALIFORNIA AVE 1112 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 358.000 | 358.000 | 08J | 01/02/2014 | 2014 | 10/28/2017 | 2017 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 51084.45
31046680 | OCGC RECNDCTR 800' OF 4C ON PEABODY 2107 | 107575429 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2014 | ED.06364.2107.TXFR.TROH | OVERHEAD TRANSFORMERS | 048 | SOLANO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 750.000 | 650.000 | 08J | 01/03/2014 | 2014 | 11/19/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 24216.69
31046900 | *CANC*TRACY 1106-*REF PM30982901* *CANC | 107569903 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 05/29/2015 | ED.16288.1106 | TRACY 1106 | 039 | SAN JOAQUIN CO | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 01/06/2014 | 2014 | 03/04/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31047513 | OCGC RECONDUCTOR 2 SPANS DIXON 1103 | 107579237 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2015 | ED.06206.1103.SWIT | SWITCHES | 048 | SOLANO COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 509.000 | 0.000 | 08W | 01/08/2014 | 2014 | 03/19/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 31201.07
31047788 | MADERA 1104-RECNDUCTOR SUNSET AVE | 107579859 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/30/2016 | ED.25276.1104 | MADERA 1104 | 020 | MADERA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 1,440.000 | 1,445.000 | 08J | 01/09/2014 | 2014 | 02/08/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 125793.85
31048179 | OC4 OCGC SONOMA1105-WIREDWN-8TH ST EAST | 107581053 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/30/2015 | ED.04272.1105.SWIT | SWITCHES | 049 | SONOMA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 1,275.000 | 0.000 | 08W | 01/10/2014 | 2014 | 06/16/2018 | 2018 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 101552.35
31048895 | OCGC RECONDUCT 1-SPAN -WILLITS 1103 | 107593724 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/27/2015 | ED.04266.1103.SWIT | SWITCHES | 023 | MENDOCINO COUN | 5532479 | CWSP 08W - Monthly Forecast Only | 429.000 | 0.000 | 08W | 01/13/2014 | 2014 | 06/25/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 65897.64
31049739 | MANCHESTER 1108 6C RECONDUCTOR | 107598109 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/25/2016 | ED.25392.1108 | MANCHESTER 1108 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 170.000 | 420.000 | 08J | 01/15/2014 | 2014 | 01/28/2018 | 2018 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 73978.27
31049891 | CURTIS 1704 - REPLACE 350FT OF 6CU | 107596161 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 05/01/2015 | ED.16335.1704 | CURTIS 1704 | 055 | TUOLUMNE COUNT | 5535457 | DO 08 - Monthly Forecast Only | 425.000 | 440.000 | 08J | 01/16/2014 | 2014 | 01/28/2017 | 2017 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 19467.34
31050031 | EP REPLACE DAMAGED CONDUCTOR, ROAD 19 | 107600910 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/01/2015 | ED.14-T230000000 | GLENN MAP T23 | 011 | GLENN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 260.000 | 0.000 | 08J | 01/17/2014 | 2014 | 01/28/2017 | 2017 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 10529.52
31052272 | REDBUD1101 RECONDCTOR LINE BAD SPLCES | 107776959 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/30/2016 | ED.04319.1101.RECL | RECLOSERS | 017 | LAKE COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 1,431.000 | 0.000 | 08J | 01/27/2014 | 2014 | 06/29/2019 | 2019 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | REDBUD1101 RECONDCTOR LINE BAD SPLCES | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 376332.01
31052323 | RECON 700' 6C DUE TO SPLICES - WD | 107748027 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 01/30/2016 | ED.25235.1110 | SANGER 1110 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 882.000 | 872.000 | 08J | 01/27/2014 | 2014 | 04/22/2017 | 2017 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 64917
31052971 | RACETRACK 1704 RECOND 7,800FT OF 4CU | 107779106 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/30/2017 | ED.16376.1704 | RACETRACK 1704 | 055 | TUOLUMNE COUNT | 5535457 | DO 08 - Monthly Forecast Only | 7,466.000 | 7,800.000 | 08J | 01/29/2014 | 2014 | 04/21/2018 | 2018 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | R4E RACETRACK 1704 RECOND 7,800FT OF 4CU | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 853518.51
31053110 | MABURY 1102 WIRE DOWN 14-0004189 | 107781876 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/01/2016 | ED.08219.1106.RECL | RECLOSERS | 043 | SANTA CLARA CO | 5532479 | CWSP 08W - Monthly Forecast Only | 644.000 | 0.000 | 08W | 01/30/2014 | 2014 | # | #VALUE! | DOCC | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 107029.25
31054560 | OCGC REPLACE 6C ON RICE 1102 - WIRE DOWN | 107779398 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2015 | ED.06283.1102.TXFR.TROH | OVERHEAD TRANSFORMERS | 006 | COLUSA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 698.000 | 698.000 | 08J | 02/04/2014 | 2014 | 12/17/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 37799.77
31054897 | OCGC BH402 LS CO10192 REPL.2 SPANS OH LI | 107794934 | # | Not assigned | 30 | Technically Completed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 10/23/2014 | ED.02402.0402.TXFR.TROH | OVERHEAD TRANSFORMERS | 041 | SAN MATEO COUN | 5535457 | DO 08 - Monthly Forecast Only | 686.000 | 500.000 | 08W | 02/06/2014 | 2014 | # | #VALUE! | FICL | E070 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 163771.09
31055014 | OC4 REP_1/0 CU PAR COND W/715 AL CL 2211 | 107791155 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/01/2016 | ED.01202.2211 | CLAYTON 2211 | 007 | CONTRA COSTA C | 5535457 | DO 08 - Monthly Forecast Only | 2,395.000 | 2,395.000 | 08J | 02/06/2014 | 2014 | 06/18/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 263704.98
31056717 | +SLO 1101 WD14-5147 (ANDREWS & MONTEREY | 107816841 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/01/2015 | ED.18263.1101 | SAN LUIS OBISPO 1101 | 040 | SAN LUIS OBISP | 5535457 | DO 08 - Monthly Forecast Only | 940.000 | 940.000 | 08J | 02/14/2014 | 2014 | 04/25/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | R5 SLO 1101 WD 14-5147 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 119259.09
31057517 | OCCCRECONDUCTOR HOWSLEY RD, CATLETT 1101 | 107822835 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2015 | ED.15376.1101.TXFR.TROH | OVERHEAD TRANSFORMERS | 051 | SUTTER COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 2,096.000 | 2,100.000 | 08J | 02/19/2014 | 2014 | 01/21/2017 | 2017 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31057517_RECONDUCTOR HOWSLEY RD, CATLETT | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 144903.33
31058659 | RECNDUCTOR CHOWCHILLA 1101 - AVE 22 | 107826783 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/29/2016 | ED.25410.1101 | CHOWCHILLA 1101 | 020 | MADERA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 3,460.000 | 3,465.000 | 08J | 02/25/2014 | 2014 | 02/11/2017 | 2017 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31058659_RECONDUCTOR CHOWCHILLA 1101 - A | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 147183.6
31059574 | 2016 GUERNSEY 1104 4CU RECONDUCTOR | 107835946 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/28/2016 | ED.25266.1104 | GUERNSEY 1104 | 016 | KINGS COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 880.000 | 880.000 | 08J | 02/27/2014 | 2014 | 11/19/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31059574 Guernsey 1104 Reconductor | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 94657.53
31059794 | OCGC CLARKSVILLE 2104 RECONDUCTOR,PHASE1 | 107836345 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/30/2016 | ED.15361.2104.SWIT | SWITCHES | 009 | EL DORADO COUN | 5532479 | CWSP 08W - Monthly Forecast Only | 7,438.000 | 7,438.000 | 08W | 02/28/2014 | 2014 | 01/14/2017 | 2017 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31059794_Clarksville 2104 Recon Green | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 492416.19
31060012 | RPL 325 FT OF 4AR ANDERSON 1103 | 107838856 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/13/2017 | ED.87-R330200000 | SHASTA MAP R3302 | 045 | SHASTA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 325.000 | 0.000 | 08J | 03/03/2014 | 2014 | 04/21/2018 | 2018 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 1742.96
31060016 | OCCCRECO 1 SPAN LINE SIDE FU 1829 TW2107 | 107834516 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 08/01/2014 | ED.01465.2107 | TIDEWATER 2107 | 007 | CONTRA COSTA C | 5532479 | CWSP 08W - Monthly Forecast Only | 197.000 | 292.000 | 08W | 03/03/2014 | 2014 | 12/26/2015 | 2015 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 202120.15
31060753 | GUSTINE 1102 - RECOND 585' W/2AR - WD | 107842653 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 02/27/2015 | ED.16311.1102 | GUSTINE 1102 | 024 | MERCED COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 585.000 | 575.000 | 08J | 03/05/2014 | 2014 | 01/20/2018 | 2018 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 79617.29
31061032 | OCGC REPLACE DETERIORATED #4 CU, CAPAY | 107844181 | # | Not assigned | 30 | Technically Completed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/01/2016 | ED.14-S210000000 | GLENN MAP S21 | 011 | GLENN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 2,343.000 | 2,343.000 | 08J | 03/06/2014 | 2014 | # | #VALUE! | FICL | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 121478.54
31061297 | *CANC* PACIFIC GROVE 424 WIREDOWN UG ES | 107836666 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 08/26/2016 | ED.18244.0424 | PACIFIC GROVE 0424 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 03/06/2014 | 2014 | 04/05/2014 | 2014 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31062090 | OCCC SOLED 2101: RECNDUCTR 2 SPANS OF OH | 107874792 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2015 | ED.18205.2101 | SOLEDAD 2101 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 785.000 | 0.000 | 08J | 03/11/2014 | 2014 | # | #VALUE! | DOCC | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 42693.94
31062092 | *CANC* DOLAN RD.1101 RE-CONDUCOTR 2 SPA | 107874843 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2015 | ED.18238.1101 | DOLAN ROAD 1101 | 044 | SANTA CRUZ COU | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 03/11/2014 | 2014 | 10/04/2014 | 2014 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31062247 | OCCCE WEST SAC 1105 RECONDUCTOR 220 FEET | 107889100 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2015 | ED.06313.1105.SWIT | SWITCHES | 057 | YOLO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 865.000 | 870.000 | 08J | 03/11/2014 | 2014 | 08/17/2019 | 2019 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 80949
31062635 | ZCRESY 2103 RECN 530' OF 6CU /W 2 ACSR | 107890135 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/30/2016 | ED.25470.2103 | CRESSEY 2103 | 024 | MERCED COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 370.000 | 370.000 | 08J | 03/12/2014 | 2014 | 05/13/2017 | 2017 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 47477.48
31062729 | LERDO 1103 RECONDUCTOR 1,700FT WD | 107892098 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/30/2016 | ED.25349.1103.TXFR.TROH | OVERHEAD TRANSFORMERS | 015 | KERN COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 1,680.000 | 1,680.000 | 08W | 03/13/2014 | 2014 | 03/19/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 71952.77
31062912 | OCLH TN 2113 1255 PARKHILL 14-0008850 | 107892903 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2016 | ED.18305.2113 | TEMPLETON 2113 | 040 | SAN LUIS OBISP | 5535457 | DO 08 - Monthly Forecast Only | 1,045.000 | 1,405.000 | 08J | 03/13/2014 | 2014 | 04/22/2017 | 2017 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 51250.15
31063598 | WEEDPATCH 1106 RECOND WIRE DOWN | 107905576 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 05/30/2014 | ED.25297.1106.TXFR.TRPM | PAD MOUNTED TRANSFORMERS | 015 | KERN COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 1,093.000 | 1,093.000 | 08W | 03/17/2014 | 2014 | 08/27/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 24665.35
31063935 | RECN 6 CU LINE SIDE LR 18692 TW 2105 | 107890727 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/01/2015 | ED.01465.2105 | TIDEWATER 2105 | 007 | CONTRA COSTA C | 5535457 | DO 08 - Monthly Forecast Only | 263.000 | 263.000 | 08J | 03/20/2014 | 2014 | 04/25/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 203552.21
31065400 | BH406 REPL.320FT OH LINE 5TH AVE RWC | 107919207 | # | Not assigned | 30 | Technically Completed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 01/30/2015 | ED.02416.0406.TXFR.TROH | OVERHEAD TRANSFORMERS | 041 | SAN MATEO COUN | 5517127 | DO 08 - Monthly Forecast Only | 367.000 | 510.000 | 08J | 03/26/2014 | 2014 | # | #VALUE! | FICL | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 51985.15
31066170 | OCCCEP RECONDUCTOR MERIDIAN 1101 - Y2016 | 107925832 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 05/06/2016 | ED.06254.1101.COND | CONDUCTOR | 051 | SUTTER COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 1,226.000 | 1,226.000 | 08J | 03/31/2014 | 2014 | 02/18/2017 | 2017 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31066170_R4E EP RECONDUCTOR MERIDIAN 110 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 221039.56
31066529 | OCGC CEDAR CRK 1101-RECOND 3528' Y2015 | 107926906 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/31/2016 | ED.87-I402500000 | SHASTA MAP I4025 | 045 | SHASTA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 3,647.000 | 10,857.000 | 08W | 04/01/2014 | 2014 | 12/16/2017 | 2017 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31066529 Cedar Creek 1101 Rel/Rep 2400FT | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 539968.45
31066739 | E RECONDUCOR PHASE7 GRAND ISLAND 222 | 107929960 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 05/31/2018 | ED.06246.2227.RECL | RECLOSERS | 048 | SOLANO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 6,551.000 | 6,551.000 | 08J | 04/03/2014 | 2014 | 04/20/2019 | 2019 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31066739_RECOND PHASE7_GRAND ISLAND 222 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 561842.28
31067120 | RECONDUCOR PHASE6 - GRAND ISLAND 222 | 107929889 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/30/2017 | ED.06246.2227.RECL | RECLOSERS | 048 | SOLANO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 5,582.000 | 5,582.000 | 08J | 04/03/2014 | 2014 | 09/22/2018 | 2018 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31067120_ RECOND PHASE6 - GRAND ISLAND | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 321506.14
31067121 | OCCCRECONDUCTOR GRAND ISLAND 2227 - PH 1 | 107929809 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2015 | ED.06246.2227.RECL | RECLOSERS | 048 | SOLANO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 5,530.000 | 5,530.000 | 08J | 04/03/2014 | 2014 | 11/18/2017 | 2017 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31067121_Grand Island 2227_Ph1_08J | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 323271.14
31067122 | RECONDUCOR PHASE4 - GRAND ISLAND 222 | 107929886 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 08/30/2017 | ED.06246.2227.RECL | RECLOSERS | 048 | SOLANO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 5,797.000 | 5,800.000 | 08J | 04/03/2014 | 2014 | 02/23/2019 | 2019 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31067122_RECOND PHASE4_GRAND ISLAND 222 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 436266.35
31067123 | E RECONDUCOR PHASE5 - GRAND ISLAND 222 | 107929888 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/30/2017 | ED.06246.2227.RECL | RECLOSERS | 048 | SOLANO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 6,347.000 | 6,347.000 | 08J | 04/03/2014 | 2014 | 05/04/2019 | 2019 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31067123_RECOND PHASE5_GRAND ISLAND 222 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 345025.71
31067124 | OCCCRECONDUCTOR GRAND ISLAND 2227 - PH 3 | 107929883 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2015 | ED.06246.2227.RECL | RECLOSERS | 048 | SOLANO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 4,802.000 | 4,810.000 | 08J | 04/03/2014 | 2014 | 11/18/2017 | 2017 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31067124_Grand Island 2227_Ph3_08J | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 234518.61
31067125 | OCCCRECONDUCTOR GRAND ISLAND 2227 - PH 2 | 107929881 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2015 | ED.06246.2227.RECL | RECLOSERS | 048 | SOLANO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 5,014.000 | 5,014.000 | 08J | 04/03/2014 | 2014 | 06/16/2018 | 2018 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31067125_Grand Island 2227_08J#Phase 2 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 282761.7
31067784 | OCGC XRECON 300' OF 4AR W/ 4/0A FORD ST | 107931459 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/03/2016 | ED.08319.2102 | GREEN VALLEY 2102 | 044 | SANTA CRUZ COU | 5532479 | CWSP 08W - Monthly Forecast Only | 288.000 | 222.000 | 08W | 04/07/2014 | 2014 | 06/13/2015 | 2015 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 37679.77
31067785 | OCCC N 400FT OF 6CU WITH 2CU-PORTOLA WA | 107931581 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/24/2016 | ED.08888.0401 | LOMPICO STEP DOWN 0401 | 044 | SANTA CRUZ COU | 5535457 | DO 08 - Monthly Forecast Only | 396.000 | 0.000 | 08J | 04/07/2014 | 2014 | 09/02/2017 | 2017 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 53350.63
31068163 | OCCCRECONDUCTR HWY 65 OAKLEY LN | 107937926 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2015 | ED.15290.1105.TXFR.TROH | OVERHEAD TRANSFORMERS | 058 | YUBA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 2,765.000 | 2,765.000 | 08J | 04/08/2014 | 2014 | 07/29/2017 | 2017 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31068163_Olivehurst 1105_Hwy 65/Oakley L | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 211272.93
31068251 | 2016 EUREKA A 1107 EXCESSIVE SPLICES | 107938198 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2016 | ED.19212.1107.SWIT | SWITCHES | 012 | HUMBOLDT COUNT | 5535457 | DO 08 - Monthly Forecast Only | 911.000 | 0.000 | 08J | 04/08/2014 | 2014 | 12/01/2018 | 2018 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 199937.58
31068282 | REP OH DET WIRE TO C/O 1210_BW-2105 | 107938667 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2015 | ED.01459.2105 | BRENTWOOD 2105 | 007 | CONTRA COSTA C | 5535457 | DO 08 - Monthly Forecast Only | 394.000 | 394.000 | 08J | 04/08/2014 | 2014 | 10/28/2017 | 2017 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 85267.26
31068721 | OCCCRECONDUCTOR 200FT - WATSONVILLE 2101 | 107948509 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/24/2016 | ED.08333.2101 | WATSONVILLE 2101 | 044 | SANTA CRUZ COU | 5535457 | DO 08 - Monthly Forecast Only | 251.000 | 0.000 | 08J | 04/11/2014 | 2014 | 08/27/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 23058.68
31069365 | 2016 W FRSNO 1112 WIREDWN RECNDUCTOR | 107950962 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/18/2016 | ED.25373.1112 | WEST FRESNO 1112 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 3,400.000 | 3,400.000 | 08J | 04/15/2014 | 2014 | 07/20/2019 | 2019 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31069365_R2 W FRESNO 1112 WIREDWN RECNDU | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 219162.79
31069570 | X-SPENCE 1121 WIREDOWN 3779 | 107954254 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/15/2016 | ED.18220.1121 | SPENCE 1121 | 027 | MONTEREY COUNT | 5532479 | CWSP 08W - Monthly Forecast Only | 1,356.000 | 1,356.000 | 08W | 04/16/2014 | 2014 | 07/23/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 52506.82
31069934 | OCGC 2016 LAMMERS 1107 RECON 4464' | 107955758 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/26/2016 | ED.16277.1107 | LAMMERS 1107 | 039 | SAN JOAQUIN CO | 5535457 | DO 08 - Monthly Forecast Only | 4,754.000 | 4,754.000 | 08J | 04/17/2014 | 2014 | 06/16/2018 | 2018 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31069934_LAMMERS 1107 RECOND 4464' 6CU T | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 241573.09
31069935 | OCGC CARBONA 1104 RECOND 3165' 6CU TO | 107955825 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/02/2016 | ED.16309.1104 | CARBONA 1104 | 039 | SAN JOAQUIN CO | 5535457 | DO 08 - Monthly Forecast Only | 3,449.000 | 3,550.000 | 08J | 04/17/2014 | 2014 | 11/18/2017 | 2017 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | CARBONA 1104 RECOND 3165' 6CU TO 397AL | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 223863.24
31069954 | OCGC RELIAIBLITY OAKLAND-REPL #6 CU-UWF | 107954830 | # | Not assigned | 40 | Closed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/30/2016 | ED.01254.1106 | OAKLAND X 1106 | 001 | ALAMEDA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 10,319.000 | 0.000 | 08J | 04/17/2014 | 2014 | 12/09/2017 | 2017 | CLSD | E070 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31069954_R1-RELIAIBLITY OAKLAND-REPLACE | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 875116.42
31069955 | RELIAIBLITY RICHMOND-REPL #6 CU-UWF | 107954831 | # | Not assigned | 40 | Closed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 08/31/2017 | ED.01250.1113 | EL CERRITO G 1113 | 001 | ALAMEDA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 4,070.000 | 4,030.000 | 08J | 04/17/2014 | 2014 | 09/22/2018 | 2018 | CLSD | E070 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31069955_R1-RELIAIBLITY RICHMOND-REPL #6 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 1045087.77
31070781 | FCM 1101 - OH RECNDUCTOR & COMBO C/O | 107957443 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/01/2016 | ED.08387.1101.SWIT | SWITCHES | 043 | SANTA CLARA CO | 5535457 | DO 08 - Monthly Forecast Only | 817.000 | 0.000 | 08J | 04/22/2014 | 2014 | 03/25/2017 | 2017 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 159324.48
31071248 | ORO FINO 1102 - 7700FT OF 4AR PHASE 2 | 107962612 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/10/2017 | ED.17-Q330000000 | PARADISE MAP Q33 | 004 | BUTTE COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 7,049.000 | 7,049.000 | 08J | 04/24/2014 | 2014 | 07/21/2018 | 2018 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31071248_ORO FINO 1102 PH 2_08 Y2017 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 934668.52
31071249 | *CANC* ORO FINO 1102 - 6500FT OF 4AR PH | 107962614 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/31/2017 | ED.17-Q320000000 | PARADISE MAP Q32 | 004 | BUTTE COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 04/24/2014 | 2014 | 11/26/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31071455 | 2016 CALIF 1112 RECONDUCTOR WIREDOWN | 107965661 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/25/2016 | ED.25228.1112 | CALIFORNIA AVE 1112 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 2,625.000 | 2,815.000 | 08J | 04/25/2014 | 2014 | 12/17/2016 | 2016 | PREC | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31071455_R2 CALIF 1112 WIRE DOWN - PARAL | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 282199.35
31071456 | 2016 W FRESNO 1112 WIRE DOWN-CRYSTAL | 107965663 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/31/2017 | ED.25373.1112 | WEST FRESNO 1112 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 4,247.000 | 4,373.000 | 08J | 04/25/2014 | 2014 | 01/28/2018 | 2018 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31071456_W FRESNO 1112 WIRE DOWN-CRYSTAL | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 426313.59
31071681 | OCGC 1105-JEFFREY PINE RECON 600' | 107971152 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/01/2015 | ED.17-S350000000 | PARADISE MAP S35 | 004 | BUTTE COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 588.000 | 588.000 | 08W | 04/25/2014 | 2014 | 03/19/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 72880.45
31071959 | *CANC* R4 MIDDLE RVR 1101 MAST CRO*CANC | # | 30979952 | OCGC MIDDLE RVR 1101 RECONDUCTORING | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | # | ED.16209.1101 | MIDDLE RIVER 1101 | 039 | SAN JOAQUIN CO | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 04/28/2014 | 2014 | 09/03/2015 | 2015 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Middle River 1101 Reconductor | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31071998 | OTTER 1102 WIRE DWN PT SUR LIGHTHOUSE | 107975606 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 05/01/2015 | ED.18294.1102 | OTTER 1102 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 5,736.000 | 5,736.000 | 08J | 04/28/2014 | 2014 | 10/28/2017 | 2017 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | R7OTTER 1102 WIRE DOWN PT SUR LIGHTHOUSE | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 338455.07
31071999 | *CANC* REPLACE 1350' OF 4AR @ 51133 TAP | 107975788 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/27/2016 | ED.18274.2102 | SAN BENITO 2102 | 035 | SAN BENITO COU | 5535457 | DO 08 - Monthly Forecast Only | 1,350.000 | 0.000 | 08J | 04/28/2014 | 2014 | 11/17/2018 | 2018 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31072902 | SALINAS 1102 WIREDN RECONDUCTOR 2ND AV | 107979024 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/29/2016 | ED.18201.1102 | SALINAS 1102 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 489.000 | 649.000 | 08J | 05/01/2014 | 2014 | 07/29/2017 | 2017 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 64314.13
31072903 | XLOS OSITOS 2102 SPRECKELS RD WD RECON | 107979246 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/27/2015 | ED.18208.2102 | LOS OSITOS 2102 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 483.000 | 0.000 | 08J | 05/01/2014 | 2014 | 02/20/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 16794.48
31073205 | *CANC* R6 BUENA VISTA 1102 WD RECO*CANC | 107982363 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 05/01/2015 | ED.18226.1102 | BUENA VISTA 1102 | 027 | MONTEREY COUNT | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 05/02/2014 | 2014 | 07/03/2015 | 2015 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31073706 | OCGC ECONDUCTR DAIRYLAND 1102-WIRE DOWN | 107986655 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/30/2016 | ED.25242.1102 | DAIRYLAND 1102 | 020 | MADERA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 3,630.000 | 3,630.000 | 08J | 05/05/2014 | 2014 | 03/18/2017 | 2017 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31073706_RECONDUCTR DAIRYLAND 1102-WIRE | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 146362.79
31073707 | RECNDUCTR CHOWCHILA 1106-WIRE DOWN | 107986657 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/30/2016 | ED.25410.1106 | CHOWCHILLA 1106 | 020 | MADERA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 7,311.000 | 2,285.000 | 08J | 05/05/2014 | 2014 | 01/14/2017 | 2017 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31073707_R2 RECNDUCTR CHOWCHILLA 1106-WI | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 218142.75
31074033 | 2016 ASHLAN 2105 RECNDUCTOR WIREDOWN | 107988278 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/26/2014 | ED.25205.2105 | ASHLAN AVE 2105 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 2,638.000 | 2,638.000 | 08J | 05/06/2014 | 2014 | 10/19/2019 | 2019 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31074033_R2 2016 ASHLAN 2105 RECONDUCTOR | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 463284.58
31074240 | OCCC EUREKA CYN RECONDUCTOR - RR 2104 | 107994037 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 05/06/2016 | ED.08369.2104 | ROB ROY 2104 | 044 | SANTA CRUZ COU | 5535457 | DO 08 - Monthly Forecast Only | 1,610.000 | 0.000 | 08J | 05/06/2014 | 2014 | 09/02/2017 | 2017 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 173931.89
31074255 | RECON 400FT OF 4CU LOCKHRT GUL-CE 2104 | 107994502 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 05/06/2016 | ED.08362.2104 | CAMP EVERS 2104 | 044 | SANTA CRUZ COU | 5535457 | DO 08 - Monthly Forecast Only | 415.000 | 500.000 | 08J | 05/06/2014 | 2014 | 04/14/2018 | 2018 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 41948.76
31075442 | BORDEN 1103 RECONDUCTORING | 108000066 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 05/01/2016 | ED.25280.1114 | MERCED 1114 | 024 | MERCED COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 2,080.000 | 2,080.000 | 08W | 05/11/2014 | 2014 | 09/24/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 78861.96
31075747 | 2016 JANES CREEK 1101 EXCESSIVE SPLICES | 107988583 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2016 | ED.19239.1101.SWIT | SWITCHES | 012 | HUMBOLDT COUNT | 5535457 | DO 08 - Monthly Forecast Only | 313.000 | 0.000 | 08J | 05/12/2014 | 2014 | 01/28/2017 | 2017 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 47835.78
31076535 | OCGC MID. RIVR 1102 RECNDUCTR CO4875 ZO | 108134782 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2016 | ED.16209.1102 | MIDDLE RIVER 1102 | 039 | SAN JOAQUIN CO | 5535457 | DO 08 - Monthly Forecast Only | 2,195.000 | 2,199.000 | 08J | 05/15/2014 | 2014 | 07/20/2019 | 2019 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | MIDDLE RIVER 1102 RECON 2370' OF 6CU | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 143547.93
31076536 | OCGC MID. RIVR RECNDUCTR LR11476 ZONE | 108134789 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2016 | ED.16209.1102 | MIDDLE RIVER 1102 | 039 | SAN JOAQUIN CO | 5535457 | DO 08 - Monthly Forecast Only | 1,696.000 | 1,700.000 | 08J | 05/15/2014 | 2014 | 09/10/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | MIDDLE RIVER 1102 RECONDUCTOR | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 102207.66
31076537 | OCGC EAST STOCKTON 402 RECONDUCTORING | 108136334 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2016 | ED.16313.0402 | EAST STOCKTON 0402 | 039 | SAN JOAQUIN CO | 5535457 | DO 08 - Monthly Forecast Only | 5,665.000 | 5,665.000 | 08J | 05/15/2014 | 2014 | 03/18/2017 | 2017 | PREC | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | EAST STOCKTON 402 RECONDUCTORING | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 403803.58
31076538 | OCGC AVENA 1701 RECONDUCTORING 2400' | 108136463 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2016 | ED.16357.1701 | AVENA 1701 | 039 | SAN JOAQUIN CO | 5535457 | DO 08 - Monthly Forecast Only | 5,265.000 | 5,265.000 | 08J | 05/15/2014 | 2014 | 12/16/2017 | 2017 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31076538_AVENA 1701 RECONDUCTORING | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 203384.06
31076768 | *RECONDUCTORING ON GREENBRAE 1102 | 108137720 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/12/2014 | ED.04309.1102.SWIT | SWITCHES | 021 | MARIN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 266.000 | 266.000 | 08J | 05/16/2014 | 2014 | 11/17/2018 | 2018 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 88051.37
31076801 | OCCC*NAPA 1104 WIRE DOWN REC. | 108144258 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/30/2016 | ED.04202.1104 | NAPA 1104 | 028 | NAPA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 738.000 | 738.000 | 08J | 05/16/2014 | 2014 | 03/25/2017 | 2017 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 130126.89
31078203 | RECONDUCTOR EL NIDO 1102 | 108159424 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/29/2018 | ED.25245.1102 | EL NIDO 1102 | 024 | MERCED COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 1,501.000 | 1,501.000 | 08J | 05/24/2014 | 2014 | 04/13/2019 | 2019 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | R2 RECONDUCTOR EL NIDO 1102 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 90522.52
31079018 | *CANC* BIG BEND 1102 - BLOOMER HIL *CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 05/01/2016 | ED.85-CC29000000 | TEHEMA MAP CC29 | 052 | TEHAMA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 05/28/2014 | 2014 | 11/03/2019 | 2019 | CLSD | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
31079172 | G1112 -RECOND 6 SPANS OF #4CU- | 108163695 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/01/2016 | ED.28-C031400000.STRU.POLE | BAY C0314 POLES | 007 | CONTRA COSTA C | 5535457 | DO 08 - Monthly Forecast Only | 760.000 | 800.000 | 08J | 05/29/2014 | 2014 | 06/16/2018 | 2018 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 191968.17
31079816 | TASSAJARA 2113 RECON (NORRIS CYN RD) | 108171957 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/28/2015 | ED.01466.2113.TXFR.TROH | OVERHEAD TRANSFORMERS | 001 | ALAMEDA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 445.000 | 445.000 | 08J | 06/03/2014 | 2014 | 06/16/2018 | 2018 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 34587.75
31080421 | 2016 CORCORAN 1106 RECONDUCTOR WD | 108174368 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/01/2017 | ED.25217.1106 | CORCORAN 1106 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 7,095.000 | 7,105.000 | 08J | 06/04/2014 | 2014 | 04/22/2017 | 2017 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31080421_R2 2016 CORCORAN 1106 RECONDUCT | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 486139.42
31080601 | RECON SPAN - BIG RIVER 1101 | 108175487 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/05/2016 | ED.04308.1101.SWIT | SWITCHES | 023 | MENDOCINO COUN | 5535457 | DO 08 - Monthly Forecast Only | 222.000 | 222.000 | 08J | 06/04/2014 | 2014 | 12/17/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 18168.62
31080602 | RECON 1- SPAN GUALALA 1112 | 108175860 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/07/2016 | ED.04284.1112.REGL | REGULATORS | 023 | MENDOCINO COUN | 5535457 | DO 08 - Monthly Forecast Only | 255.000 | 252.000 | 08J | 06/04/2014 | 2014 | 11/19/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 15989.91
31080688 | CAPITAN 1106-RECON 1,045' 6CU W/4/O | 108176143 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 05/01/2016 | ED.25388.1106 | EL CAPITAN 1106 | 024 | MERCED COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 821.000 | 821.000 | 08J | 06/05/2014 | 2014 | 02/23/2019 | 2019 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 103663.71
31081651 | +CAB 1103, E LAUREL, LOMPOC | 108182253 | # | Not assigned | 30 | Technically Completed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/30/2020 | ED.18310.1103 | CABRILLO 1103 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 1,389.000 | 1,389.000 | 08J | 06/10/2014 | 2014 | # | #VALUE! | FICL | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31081651_WD-RECON 1400' OF 397AL -CABRIL | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 599945.92
31081653 | REPL 815' CNDUCTOR AT 800 SALINAS RD | 108182954 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/30/2016 | ED.18274.2101 | SAN BENITO 2101 | 035 | SAN BENITO COU | 5535457 | DO 08 - Monthly Forecast Only | 793.000 | 800.000 | 08J | 06/10/2014 | 2014 | 05/13/2017 | 2017 | PREC | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31081653_R2 REPL 815' CONDUCTOR AT 800 S | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 92738.94
31081817 | RECONDUCTORING ON ALTO 1120 | 108182494 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 02/06/2015 | ED.04203.1120.SWIT | SWITCHES | 021 | MARIN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 2,811.000 | 2,541.000 | 08J | 06/10/2014 | 2014 | 05/30/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 290711.73
31081880 | NAPA 1112 WIRE DWN ML REC COOMBSVILLE RD | 108190680 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 05/31/2017 | ED.04202.1112 | NAPA 1112 | 028 | NAPA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 7,747.000 | 7,747.000 | 08J | 06/10/2014 | 2014 | 09/28/2019 | 2019 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | NAPA 1112 WIRE DOWN MAIN LINE REC. | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 1508573.88
31082152 | OCCC XRECNDUCTR 2900' HRD TAP GNZLS 1104 | 108174138 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 07/03/2015 | ED.18213.1104 | GONZALES 1104 | 027 | MONTEREY COUNT | 5532479 | CWSP 08W - Monthly Forecast Only | 2,746.000 | 2,746.000 | 08W | 06/12/2014 | 2014 | 07/23/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 107419.95
31082220 | RECONDUCTOR ALTO 1125 MARIN-LIVE OAK MV | 108193775 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 05/08/2015 | ED.04203.1125.SWIT | SWITCHES | 021 | MARIN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 649.000 | 659.000 | 08J | 06/12/2014 | 2014 | 01/20/2018 | 2018 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 178530.76
31082390 | R7 RECON 12-SPAN GRATON RD W/RAILROAD AV | 108194734 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2016 | JY | JUNK YARD FL TO HOLD DELETED DATA | 049 | SONOMA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 1,865.000 | 1,835.000 | 08J | 06/12/2014 | 2014 | # | #VALUE! | DOCC | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31082390_Recond 12-Span Graton Rd | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 508582.22
31082391 | RECON 4-SPANS SULLIVAN RD MOLINO 1102 | 108194730 | # | Not assigned | 30 | Technically Completed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2016 | ED.04257.1102.RECL | RECLOSERS | 049 | SONOMA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 730.000 | 1,059.000 | 08J | 06/12/2014 | 2014 | # | #VALUE! | FICL | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 201626.22
31082393 | RECON THREE SPANS CHERRY RIDGE RD | 108194639 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2016 | ED.04257.1102.RECL | RECLOSERS | 049 | SONOMA COUNTY | 5535211 | CWSP SPO - SH 08 | 1,345.000 | 1,345.000 | 08W | 06/12/2014 | 2014 | # | #VALUE! | DOCC | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 611813.45
31082394 | OCGC N SIX SPANS FRATI LN | 108194636 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2016 | ED.04257.1102.SWIT | SWITCHES | 049 | SONOMA COUNTY | 5535211 | CWSP SPO - SH 08 | 1,486.000 | 1,486.000 | 08W | 06/12/2014 | 2014 | 07/20/2019 | 2019 | CLSD | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 121250.38
31082395 | RECON TWO SPANS GRATON RD | 108194634 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2016 | ED.04257.1102.SWIT | SWITCHES | 049 | SONOMA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 754.000 | 0.000 | 08J | 06/12/2014 | 2014 | # | #VALUE! | CONS | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 16963.97
31082782 | +WD-RECON 4200' OF 6CU W 2CU-PERRY1101 | 108195325 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/23/2016 | ED.18307.1101 | PERRY 1101 | 040 | SAN LUIS OBISP | 5535457 | DO 08 - Monthly Forecast Only | 5,046.000 | 4,200.000 | 08J | 06/16/2014 | 2014 | 07/20/2019 | 2019 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | R5 WD-RECON 4200' OF 6CU W 2CU-PERRY1101 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 364124.91
31083700 | OCCC 401 RECND 300FT OH LINE INST 1CO | 108204496 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/20/2015 | ED.02403.0401.TXFR.TROH | OVERHEAD TRANSFORMERS | 041 | SAN MATEO COUN | 5505513 | PN-OH ANNEALED/DETER CNDCTR: PM MGD | 278.000 | 282.000 | 08J | 06/20/2014 | 2014 | 05/13/2017 | 2017 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 131038.19
31083701 | OCCC HMB-1103RECOND 400' OH PRI_INST C/O | 108204497 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/16/2015 | ED.02410.1103.TXFR.TROH | OVERHEAD TRANSFORMERS | 041 | SAN MATEO COUN | 5535457 | DO 08 - Monthly Forecast Only | 273.000 | 0.000 | 08W | 06/20/2014 | 2014 | 08/27/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 42079.75
31084072 | UCCOEP NAPA1112 WIRE DWN ADOBE LN RECOND | 108205963 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2016 | ED.04202.1112 | NAPA 1112 | 028 | NAPA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 164.000 | 167.000 | 08J | 06/23/2014 | 2014 | 06/17/2017 | 2017 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 68869.67
31085776 | SANTA MARIA 1109 (HWY166/E/O BLACK RD) | 108542812 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 08/26/2016 | ED.18267.1109 | SANTA MARIA 1109 | 042 | SANTA BARBARA | 5532479 | CWSP 08W - Monthly Forecast Only | 1,182.000 | 0.000 | 08W | 06/30/2014 | 2014 | 10/28/2017 | 2017 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 52585.81
31086638 | OCCC CABRILLO 1104 WIREDOWN 14-0036943 | 108548136 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2017 | ED.18310.1104 | CABRILLO 1104 | 042 | SANTA BARBARA | 5532479 | CWSP 08W - Monthly Forecast Only | 1,268.000 | 1,268.000 | 08W | 07/03/2014 | 2014 | 11/19/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31086638_R5 CABRILLO 1104 WIREDOWN 14-00 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 114424.99
31086701 | +OCEANO 1102 WIREDOWN 14-0032745 | 108547932 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2017 | ED.18260.1102 | OCEANO 1102 | 040 | SAN LUIS OBISP | 5535457 | DO 08 - Monthly Forecast Only | 622.000 | 922.000 | 08J | 07/03/2014 | 2014 | 01/28/2017 | 2017 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 38465.2
31086705 | +MORRO BAY 1101 (NAGANO RD) | 108550033 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2017 | ED.18301.1101 | MORRO BAY 1101 | 040 | SAN LUIS OBISP | 5535457 | DO 08 - Monthly Forecast Only | 753.000 | 753.000 | 08J | 07/03/2014 | 2014 | 11/19/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 77535
31086824 | OC4 OCGC REPL DETERORATED 6C ON SUISUN 1 | 108551868 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 07/03/2015 | ED.06213.1106.CAPA | CAPACITORS | 048 | SOLANO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 1,809.000 | 1,809.000 | 08J | 07/03/2014 | 2014 | 07/02/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31086824_Suisun 1106 # Phase1_08E | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 331940.81
31087570 | BIOLA 1104 WIREDOWN RECNDUCTOR | 108554179 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/30/2016 | ED.25221.1104 | BIOLA 1104 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 482.000 | 482.000 | 08J | 07/09/2014 | 2014 | 05/13/2017 | 2017 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 67222.26
31088838 | RECN 7047' CU W/#2 ACSR UWF AL 1105 | 108568965 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/16/2017 | ED.01410.1105 | ALHAMBRA 1105 | 007 | CONTRA COSTA C | 5535457 | DO 08 - Monthly Forecast Only | 5,758.000 | 5,700.000 | 08J | 07/14/2014 | 2014 | 04/25/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31088838_R4 RECON 7047' CU W/ #2 ACSR UW | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 355681.3
31088894 | OCCC WIREDOWN RECONDUCTORING EG-401 | 108566639 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/30/2015 | ED.02257.0401.TXFR.TROH | OVERHEAD TRANSFORMERS | 041 | SAN MATEO COUN | 5505513 | PN-OH ANNEALED/DETER CNDCTR: PM MGD | 122.000 | 0.000 | 08J | 07/18/2014 | 2014 | 12/17/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 57620.82
31089263 | MOVE FUSE 1179/RECON WITH TREE WIRE | 108573135 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/30/2016 | ED.01467.1102 | SOBRANTE 1102 | 007 | CONTRA COSTA C | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 07/16/2014 | 2014 | # | #VALUE! | UNSE | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 10979.62
31089385 | *CANC* R5WD REPL 1 SPAN WITH 4/0AL*CANC | 108574013 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 08/26/2016 | ED.18206.1108 | FAIRWAY 1108 | 042 | SANTA BARBARA | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 07/17/2014 | 2014 | 01/05/2015 | 2015 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31090652 | SUISUN 1106 RECONDUCTOR - PH 2 | 108582628 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/25/2016 | ED.06213.1106.CAPA | CAPACITORS | 048 | SOLANO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 2,761.000 | 2,750.000 | 08J | 07/23/2014 | 2014 | 03/07/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31090652_Suisun 1106 # Phase 2._08E | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 340161.13
31091401 | MCCALL 1106_WIREDOWN_RECOND 608' | 108584296 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/28/2017 | ED.25412.1106 | MC CALL 1106 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 916.000 | 916.000 | 08J | 07/27/2014 | 2014 | 04/22/2017 | 2017 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 95064.62
31091502 | RECON 3 SPANS END OF BIAGGI LN | 108584245 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 05/31/2017 | ED.04298.1101.SWIT | SWITCHES | 023 | MENDOCINO COUN | 5535457 | DO 08 - Monthly Forecast Only | 1,720.000 | 0.000 | 08J | 07/28/2014 | 2014 | 07/14/2018 | 2018 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 99958.64
31091813 | OC4 OCGC2015 RECNDUCTR RM 1104 OUTLET 19 | 108588666 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/27/2015 | ED.01416.1104 | ROSSMOOR 1104 | 007 | CONTRA COSTA C | 5535457 | DO 08 - Monthly Forecast Only | 2,107.000 | 2,107.000 | 08J | 07/29/2014 | 2014 | 07/04/2015 | 2015 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 188474.04
31092109 | SAN RAFAEL 1107 DETER COND GOODHILL RD | 108590694 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 05/11/2017 | ED.04201.1107.SWIT | SWITCHES | 021 | MARIN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 6,635.000 | 5,980.000 | 08J | 07/30/2014 | 2014 | 09/12/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31092109_R4SAN RAFAEL 1107 DETER COND GO | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 1056847.65
31092113 | OCCCSN RAFAEL1109 DETER COND JEWELL/HIGH | 108590869 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2016 | ED.04201.1109.SWIT | SWITCHES | 021 | MARIN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 1,935.000 | 2,095.000 | 08J | 07/30/2014 | 2014 | 12/17/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | R7SAN RAFAEL 1109 DETER COND JEWELL/HIGH | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 287860.54
31092114 | OCGC RAFAEL 1106 DETER COND CHULA VISTA | 108591540 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 07/31/2017 | ED.04201.1106.SWIT | SWITCHES | 021 | MARIN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 4,705.000 | 4,705.000 | 08J | 07/30/2014 | 2014 | 02/08/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | R7SAN RAFAEL 1106 DETER COND CHULA VISTA | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 569532.55
31092115 | OCGC SAN RAFAEL 1108 DETER COND GLENWD | 108591541 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 07/31/2017 | ED.04201.1108.SWIT | SWITCHES | 021 | MARIN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 2,400.000 | 2,600.000 | 08J | 07/30/2014 | 2014 | 02/10/2018 | 2018 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | R7SAN RAFAEL 1108 DETER COND GLENWOOD AV | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 335364.65
31092222 | +WD REPL 2 SPANS WITH 2CU -MESA 1102 | 108592290 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 08/26/2016 | ED.18282.1102 | MESA 1102 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 361.000 | 361.000 | 08J | 07/31/2014 | 2014 | 01/28/2017 | 2017 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 28747.58
31092787 | OCGCELIAIBLTY R1129-RECONDUCTR #6CU | 108596022 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/31/2016 | ED.01347.1129 | RICHMOND R 1129 | 007 | CONTRA COSTA C | 5517127 | DO 08 - Monthly Forecast Only | 529.000 | 1,587.000 | 08J | 08/04/2014 | 2014 | 08/18/2018 | 2018 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 62721.45
31092788 | EB-RELIAIBLITY D1102-REPLACE #6CU | 108595973 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/31/2016 | ED.01204.1102 | OAKLAND D 1102 | 001 | ALAMEDA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 275.000 | 270.000 | 08J | 08/04/2014 | 2014 | 02/23/2019 | 2019 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 52550.61
31092865 | OH WIREDOWN REPLACEMENT CV1104 | 108842903 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2017 | ED.24-I100800000.STRU.ENCL | MISSION I1008 ENCLOSURE | 001 | ALAMEDA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 933.000 | 933.000 | 08J | 08/04/2014 | 2014 | 11/18/2017 | 2017 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 51022.83
31093044 | RECN #4AR W/ #2ACSR SSD 52485 ML2103 | 108843559 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/01/2016 | ED.01430.2103 | MEADOW LANE 2103 | 007 | CONTRA COSTA C | 5535457 | DO 08 - Monthly Forecast Only | 463.000 | 463.000 | 08J | 08/05/2014 | 2014 | 06/17/2018 | 2018 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 28179.43
31093073 | XSHELL RD, REPL 450' 6CU OH CONDUCTOR | 108843185 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/01/2015 | ED.08319.2103 | GREEN VALLEY 2103 | 044 | SANTA CRUZ COU | 5532479 | CWSP 08W - Monthly Forecast Only | 431.000 | 431.000 | 08W | 08/05/2014 | 2014 | 07/23/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 33388.02
31093074 | +SM 1109 RECON (HWY 166 / E/O SIMAS RD) | 108842843 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 08/28/2015 | ED.18267.1109 | SANTA MARIA 1109 | 042 | SANTA BARBARA | 5532479 | CWSP 08W - Monthly Forecast Only | 671.000 | 0.000 | 08W | 08/05/2014 | 2014 | 12/17/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 34755.06
31093779 | MABURY 1104 WIRE DOWN 14-0043849 | 108849330 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/01/2016 | ED.08219.1104.TXFR.TROH | OVERHEAD TRANSFORMERS | 043 | SANTA CLARA CO | 5532479 | CWSP 08W - Monthly Forecast Only | 371.000 | 0.000 | 08W | 08/08/2014 | 2014 | 08/27/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 84221.13
31093840 | MESA 1102 (DIVISION @ OSO FLACO LAKE) | 108849391 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/30/2016 | ED.18282.1102 | MESA 1102 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 6,822.000 | 6,822.000 | 08J | 08/08/2014 | 2014 | 02/11/2017 | 2017 | PREC | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31093840_SBWF ACSR REPL FUSE 11181 & 457 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 262900.2
31094451 | +SBWF ACSR REPL (BONITA SCHOOL RD) | 108859141 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/30/2016 | ED.18282.1102 | MESA 1102 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 7,054.000 | 5,547.000 | 08J | 08/12/2014 | 2014 | 11/19/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | R5 SBWF ACSR REPLACEMENT LR M24 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 213506.73
31094681 | SALINAS 1109 WIREDOWN FCO23279 | 108862554 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 08/14/2015 | ED.18201.1109 | SALINAS 1109 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 3,085.000 | 3,085.000 | 08J | 08/13/2014 | 2014 | 07/29/2017 | 2017 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31094681_R2 SALINAS 1109 WIREDOWN FCO232 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 130682.89
31094780 | OH WIRE DOWN REPLACEMENT ME1110 | 108863130 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2017 | ED.24-J082500000.STRU.ENCL | MISSION J0825 ENCLOSURE | 001 | ALAMEDA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 414.000 | 0.000 | 08W | 08/13/2014 | 2014 | 09/21/2019 | 2019 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 54068.64
31095026 | REPOH DET WIRE SNSET & EDEN PLAINS | 108864142 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/31/2016 | ED.01432.1101 | BALFOUR 1101 | 007 | CONTRA COSTA C | 5535457 | DO 08 - Monthly Forecast Only | 1,002.000 | 0.000 | 08J | 08/14/2014 | 2014 | 02/23/2019 | 2019 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 23235.73
31095523 | OCGCELIAIBLITY -K1103, REPL #4ACSR W | 108871964 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/31/2017 | ED.01210.1103 | OAKLAND K 1103 | 001 | ALAMEDA COUNTY | 5535211 | CWSP SPO - SH 08 | 1,800.000 | 1,838.000 | 08W | 08/19/2014 | 2014 | 04/25/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 282571.51
31095687 | MANCHESTER 1110 - RECONDUCTOR TAP | 108872542 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/30/2016 | ED.25392.1110 | MANCHESTER 1110 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 604.000 | 604.000 | 08J | 08/19/2014 | 2014 | 07/29/2017 | 2017 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 113209.65
31096169 | OCGC TRACY 1106 RECOND 2157FT 6CU TO | 108875429 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/29/2017 | ED.16288.1106 | TRACY 1106 | 039 | SAN JOAQUIN CO | 5535457 | DO 08 - Monthly Forecast Only | 2,152.000 | 2,152.000 | 08J | 08/21/2014 | 2014 | 07/22/2017 | 2017 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | TRACY 1106 RECOND 2157FT 6CU TO 2AR | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 67326.96
31097449 | XPRUNEDALE 1107 WD C/O 4485 | 108881498 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/04/2015 | ED.18296.1107 | PRUNEDALE 1107 | 027 | MONTEREY COUNT | 5532479 | CWSP 08W - Monthly Forecast Only | 299.000 | 0.000 | 08W | 08/27/2014 | 2014 | 10/28/2017 | 2017 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 38548.72
31097452 | XCAMPHORA 1101 WD FCO 7091 | 108881732 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/18/2015 | ED.18207.1101 | CAMPHORA 1101 | 027 | MONTEREY COUNT | 5532479 | CWSP 08W - Monthly Forecast Only | 612.000 | 612.000 | 08W | 08/27/2014 | 2014 | 07/23/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 41787.29
31097541 | MNLO 1102_RECNDUCTR_REFRAME PLES | 108885833 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/19/2015 | ED.02413.1102.RECL | RECLOSERS | 041 | SAN MATEO COUN | 5505513 | PN-OH ANNEALED/DETER CNDCTR: PM MGD | 5,019.000 | 0.000 | 08J | 08/27/2014 | 2014 | 12/17/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31097541_PN MENLO1102 REPL./REFRAME POLE | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 343943.38
31098259 | OCCC SALINAS 1106 WIRE DOWN FCO56459 | 108887306 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 05/29/2015 | ED.18201.1106 | SALINAS 1106 | 027 | MONTEREY COUNT | 5532479 | CWSP 08W - Monthly Forecast Only | 1,101.000 | 1,101.000 | 08W | 09/02/2014 | 2014 | 07/23/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 74307.63
31098360 | OCCC XGONZALES 1104 WIRE DOWN FCO 5005 | 108887342 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/30/2015 | ED.18213.1104 | GONZALES 1104 | 027 | MONTEREY COUNT | 5532479 | CWSP 08W - Monthly Forecast Only | 2,215.000 | 2,215.000 | 08W | 09/02/2014 | 2014 | 07/23/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 99643.81
31098474 | OCCC WIREDOWN RECONDUCTORING EG-1107 | 108889644 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/30/2015 | ED.56-E041800000 | SKYLINE MAP E0418 | 041 | SAN MATEO COUN | 5505513 | PN-OH ANNEALED/DETER CNDCTR: PM MGD | 331.000 | 0.000 | 08J | 09/05/2014 | 2014 | 07/22/2017 | 2017 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 76800.92
31098498 | CLARKSVILLE 2104 RECON - PH 2 Y2017 | 108895129 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/29/2018 | ED.15361.2104.SWIT | SWITCHES | 009 | EL DORADO COUN | 5535457 | DO 08 - Monthly Forecast Only | 3,276.000 | 3,083.000 | 08J | 09/02/2014 | 2014 | 02/23/2019 | 2019 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31098498_CLARKSVILLE 2104 RECOND - PH 2 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 253229.54
31098626 | CLARKSVILLE 2104 RECONDUCTOR -PH 3 Y2018 | 108895192 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2018 | ED.15361.2104.SWIT | SWITCHES | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 8,052.000 | 8,052.000 | 08W | 09/03/2014 | 2014 | # | #VALUE! | MAPP | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | 31098626_CLARKSVILLE 2104 RECOND - PH 3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 1036604.98
31098634 | +MESA 1102 WIREDOWN (OSO FLACO TAP) | 108894937 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2015 | ED.18282.1102 | MESA 1102 | 040 | SAN LUIS OBISP | 5532479 | CWSP 08W - Monthly Forecast Only | 2,209.000 | 0.000 | 08W | 09/03/2014 | 2014 | 06/18/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31098634_R2 MESA 1102 WIREDOWN 14-003274 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 131072.17
31100467 | OCGC ZAMORA 1105 RECONDUCTOR 3 SPANS | 109209466 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2016 | ED.06319.1105.TXFR.TROH | OVERHEAD TRANSFORMERS | 057 | YOLO COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 435.000 | 435.000 | 08W | 09/11/2014 | 2014 | 02/18/2017 | 2017 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 27304.7
31101217 | OCGC EEL RIVER 1102 EXCESSIVE SPLICES | 109210477 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/30/2016 | ED.19238.1102.SWIT | SWITCHES | 012 | HUMBOLDT COUNT | 5535457 | DO 08 - Monthly Forecast Only | 588.000 | 588.000 | 08J | 09/15/2014 | 2014 | 09/02/2017 | 2017 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 39456.71
31101833 | OCCC XVIEJO 2203 WIREDAWN AGUAJITO | 109225766 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/04/2015 | ED.18285.2203 | VIEJO 2203 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 1,803.000 | 1,803.000 | 08J | 09/18/2014 | 2014 | 06/18/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31101833_R2 VIEJO 2203 WIREDAWN AGUAJITO | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 148538
31102548 | OC4 COTTONWOOD 1102-RECON 918' | 109234404 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/30/2017 | ED.10293.1102.REGL | REGULATORS | 045 | SHASTA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 1,021.000 | 918.000 | 08W | 09/23/2014 | 2014 | 06/25/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 67237.52
31102830 | *CANC*DONOT USE*WIREDOWN RECONDUCTO*CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/26/2015 | ED.02210.1110.SWIT | SWITCHES | 041 | SAN MATEO COUN | 5517127 | DO 08 - Monthly Forecast Only | 203.000 | 0.000 | 08J | 09/24/2014 | 2014 | 05/03/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31102963 | +SISQUOC 1104 WD (ORCUTT-GAREY RD) | 109231089 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/28/2017 | ED.18281.1104 | SISQUOC 1104 | 042 | SANTA BARBARA | 5532479 | CWSP 08W - Monthly Forecast Only | 1,229.000 | 0.000 | 08W | 09/24/2014 | 2014 | 10/15/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 42484.95
31104113 | +TEMPLETON 2113 WD 14-0047158 | 109245610 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/30/2017 | ED.18305.2113 | TEMPLETON 2113 | 040 | SAN LUIS OBISP | 5535457 | DO 08 - Monthly Forecast Only | 3,285.000 | 1,095.000 | 08J | 09/29/2014 | 2014 | 06/17/2018 | 2018 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | R5 TEMPLETON 2113 WD 14-0047158 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 109472.43
31104517 | OCCCDIXON1103 RECONDCTR 950' WIRE DWN PR | 109249326 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2016 | ED.48-P190000000.STRU.POLE | SOLANO P19 POLES | 048 | SOLANO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 1,102.000 | 1,150.000 | 08J | 10/01/2014 | 2014 | 12/17/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 76906.55
31109716 | 2016 GUERNSEY 1104 ANNEALED RECOND | 109589134 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/30/2016 | JY | JUNK YARD FL TO HOLD DELETED DATA | 016 | KINGS COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 7,286.000 | 0.000 | 08W | 10/24/2014 | 2014 | 09/12/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | R2 2016 GUERNSEY 1104 ANNEALED RECOND | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 639358.37
31111367 | OCGC XR CONDCTR 4 SPANS @TROUT G&OSPREY | 109598244 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/31/2017 | ED.08369.2105 | ROB ROY 2105 | 044 | SANTA CRUZ COU | 5532479 | CWSP 08W - Monthly Forecast Only | 788.000 | 952.000 | 08W | 10/29/2014 | 2014 | 07/20/2019 | 2019 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 120506.2
31111958 | 2016 CAL WATER 1102 RECONDUCTOR | 109601413 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/01/2017 | ED.25545.1102.SWIT | SWITCHES | 015 | KERN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 1,391.000 | 1,391.000 | 08J | 10/31/2014 | 2014 | 01/28/2017 | 2017 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31111958_Cal Water 1102 Reconductor | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 101997.14
31112500 | OCGC RECON 780FT OF 4ACSR MONTE RIO 1111 | 109607951 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 08/31/2016 | ED.04281.1111.RECL | RECLOSERS | 049 | SONOMA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 833.000 | 0.000 | 08W | 11/03/2014 | 2014 | 11/18/2017 | 2017 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 126799.38
31113692 | R2Z RECNDUCTR PRUNEDALE 1107 MAIN AT MAS | 109630784 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/04/2016 | ED.18296.1107 | PRUNEDALE 1107 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 1,352.000 | 0.000 | 08J | 11/07/2014 | 2014 | # | #VALUE! | DOCC | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 29724.2
31113693 | OCCC DOLAN RD 1104 WIREDOWN COOPER RD | 109612843 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/15/2016 | ED.18238.1104 | DOLAN ROAD 1104 | 027 | MONTEREY COUNT | 5532479 | CWSP 08W - Monthly Forecast Only | 1,571.000 | 0.000 | 08W | 11/07/2014 | 2014 | 12/17/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 53990.69
31114165 | HBPP 1101 FUSE 0441 EXCESSIVE SPLICES | 109666199 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/29/2017 | ED.36-Q062400000.STRU.POLE | EUREKA Q0624 POLES | 012 | HUMBOLDT COUNT | 5535457 | DO 08 - Monthly Forecast Only | 1,132.000 | 0.000 | 08J | 11/11/2014 | 2014 | 02/18/2017 | 2017 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 152742.42
31115088 | OCGC RECON 900FT 4CU/4/0ALTW FTROSS 1121 | 109671926 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/29/2017 | ED.04285.1121.RECL | RECLOSERS | 049 | SONOMA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 873.000 | 0.000 | 08W | 11/14/2014 | 2014 | 10/28/2017 | 2017 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 298002.53
31115947 | EL NIDO 1103 REPLACE ANNEALTED 650FT | 109669571 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/29/2017 | ED.25245.1103 | EL NIDO 1103 | 020 | MADERA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 600.000 | 0.000 | 08W | 11/18/2014 | 2014 | 11/19/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 31785.79
31118505 | RECONDUCTOR EL PECO 1106 (WIREDOWN) | 109679194 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2018 | ED.25398.1106 | EL PECO 1106 | 020 | MADERA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 6,056.000 | 7,556.000 | 08J | 12/02/2014 | 2014 | 12/28/2017 | 2017 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31118505_RECONDUCTOR EL PECO 1106 (WIRED | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 446481.74
31119338 | *CANC* GUERNSEY 1104 RECON 5,800' OF 6 C | 109696001 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/18/2016 | ED.25266.1104.SWIT | SWITCHES | 016 | KINGS COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 12/04/2014 | 2014 | 01/17/2015 | 2015 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31119865 | OCCC BEL 403 REPLC200FT OH LINE INST C/O | 109764948 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 08/28/2015 | ED.02403.0403.TXFR.TROH | OVERHEAD TRANSFORMERS | 041 | SAN MATEO COUN | 5535457 | DO 08 - Monthly Forecast Only | 170.000 | 0.000 | 08W | 12/08/2014 | 2014 | 07/23/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 44032.73
31120189 | +MESA 1102 (DIVISION E/O BONITA SCHOOL) | 109702934 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/30/2016 | ED.18282.1102 | MESA 1102 | 040 | SAN LUIS OBISP | 5535457 | DO 08 - Monthly Forecast Only | 5,491.000 | 5,491.000 | 08J | 12/09/2014 | 2014 | 02/11/2017 | 2017 | PREC | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | R2 SBWF ACSR REPL USE 8937 & 46299 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 169942.49
31120347 | *CANC* FIGARDEN 2110 OH RECONDUCTOR*CANC | 109764582 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 05/26/2017 | ED.25455.2110 | FIGARDEN 2110 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 12/09/2014 | 2014 | 07/03/2015 | 2015 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31120755 | RECONDUCTOR ND2101 WIREDOWN | 109900929 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/30/2015 | ED.01405.2101.SWIT | SWITCHES | 001 | ALAMEDA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 60.000 | 0.000 | 08W | 12/12/2014 | 2014 | 09/02/2017 | 2017 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 11446.75
31120911 | X-DOLN RD 1104 WIREDOWN BLNCO ARMSTRNG | 109898337 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/13/2015 | ED.18238.1104 | DOLAN ROAD 1104 | 027 | MONTEREY COUNT | 5532479 | CWSP 08W - Monthly Forecast Only | 1,184.000 | 0.000 | 08W | 12/12/2014 | 2014 | 02/18/2017 | 2017 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 23283.16
31120912 | X-DOLAN RD 1101 WIREDWN STRAWBRRY CYN | 109898309 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/04/2015 | ED.18238.1101 | DOLAN ROAD 1101 | 044 | SANTA CRUZ COU | 5532479 | CWSP 08W - Monthly Forecast Only | 1,319.000 | 1,400.000 | 08W | 12/12/2014 | 2014 | 10/28/2017 | 2017 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 106757.15
31121472 | +OCEANO 1104 WD 14-0067445 | 109907135 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2017 | ED.18260.1104 | OCEANO 1104 | 040 | SAN LUIS OBISP | 5532479 | CWSP 08W - Monthly Forecast Only | 338.000 | 0.000 | 08W | 12/17/2014 | 2014 | 07/21/2018 | 2018 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 104987.51
31121571 | REPL OH WIRE PORT CHICAGO W/O NICHOLS | 109907190 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/30/2017 | ED.01391.2108 | WILLOW PASS 2108 | 007 | CONTRA COSTA C | 5532479 | CWSP 08W - Monthly Forecast Only | 2,335.000 | 2,335.000 | 08W | 12/16/2014 | 2014 | 03/04/2018 | 2018 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31121571_R1_REPL OH WIRE PORT CHICAGO W/ | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 279879.21
31122009 | OCCC HMB1102 LR2032 REP 300FT OF OH LINE | 109907850 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/31/2016 | ED.02410.1102.TXFR.TROH | OVERHEAD TRANSFORMERS | 041 | SAN MATEO COUN | 5505513 | PN-OH ANNEALED/DETER CNDCTR: PM MGD | 411.000 | 0.000 | 08J | 12/18/2014 | 2014 | 03/31/2018 | 2018 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 91796.51
31122088 | KINGSBRG 1114 600' RECOND WIREDOWN | 109907708 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/31/2017 | ED.25224.1114 | KINGSBURG 1114 | 010 | FRESNO COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 1,090.000 | 0.000 | 08W | 12/18/2014 | 2014 | 08/27/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 97168.47
31122468 | OCGC R2Z-ROUGH READY 1102 RECONDUCTOR | 109910742 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/01/2018 | ED.16308.1102 | ROUGH AND READY IS 1102 | 039 | SAN JOAQUIN CO | 5535457 | DO 08 - Monthly Forecast Only | 1,487.000 | 1,487.000 | 08J | 12/22/2014 | 2014 | 04/06/2019 | 2019 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | R4-ROUGH READY 1102 RECONDUCTOR AT CO19 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 110592.3
31122833 | OCCC BASALT 1106 WIRE DWN FUSE 1157 ZONE | 109917911 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/31/2017 | ED.04246.1106 | BASALT 1106 | 028 | NAPA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 537.000 | 0.000 | 08W | 12/23/2014 | 2014 | 12/17/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 60064
31124815 | OCCC X-SLDD 1114 WREDWN RECND. S/O HY101 | 109912519 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/17/2016 | ED.18205.1114 | SOLEDAD 1114 | 027 | MONTEREY COUNT | 5532479 | CWSP 08W - Monthly Forecast Only | 2,199.000 | 0.000 | 08W | 01/05/2015 | 2015 | # | #VALUE! | DOCC | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 84703.5
31124817 | X-VIEJO 2202 WIRE DOWN 17 MILE DR | 109935056 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/28/2017 | ED.18285.2202 | VIEJO 2202 | 027 | MONTEREY COUNT | 5517127 | DO 08 - Monthly Forecast Only | 190.000 | 200.000 | 08J | 01/05/2015 | 2015 | # | #VALUE! | DOCC | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 132215.55
31124819 | OCCC KING CITY 1106 WD 14-0067419 | 109936027 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2017 | ED.18203.1106 | KING CITY 1106 | 027 | MONTEREY COUNT | 5532479 | CWSP 08W - Monthly Forecast Only | 1,052.000 | 0.000 | 08W | 01/05/2015 | 2015 | 04/22/2017 | 2017 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 102490.36
31125000 | +SANTA MARIA 1109 (BONITA LATERAL) | 109936065 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2017 | ED.18267.1109 | SANTA MARIA 1109 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 955.000 | 955.000 | 08J | 01/05/2015 | 2015 | 04/13/2019 | 2019 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 46074.7
31125443 | OCLH PASO ROBLES 1103 WD 14-0066395 | 109936122 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2017 | ED.18261.1108 | PASO ROBLES 1108 | 040 | SAN LUIS OBISP | 5532479 | CWSP 08W - Monthly Forecast Only | 1,102.000 | 0.000 | 08W | 01/06/2015 | 2015 | 03/25/2017 | 2017 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 42784.41
31125646 | OCGC D 2350' EXCESS SLICES SW6041 | 109949376 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/29/2017 | ED.19222.1101.SWIT | SWITCHES | 012 | HUMBOLDT COUNT | 5532479 | CWSP 08W - Monthly Forecast Only | 2,323.000 | 0.000 | 08W | 01/07/2015 | 2015 | 12/17/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 107693.21
31126015 | EP RECONDUCTOR PENRYN 1105 - Y2017 | 109949925 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/18/2016 | ED.15256.1105.COND | CONDUCTOR | 031 | PLACER COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 1,950.000 | 08J | 01/07/2015 | 2015 | 09/16/2017 | 2017 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 165699.55
31126827 | OCGC EP RECONDUCTOR WILLIAMS 1102- Y2016 | 109953711 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/18/2016 | ED.06205.1102.COND | CONDUCTOR | 006 | COLUSA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 2,074.000 | 0.000 | 08W | 01/09/2015 | 2015 | 01/28/2017 | 2017 | PREC | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31126827_R4 EP RECONDUCTOR WILLIAMS 1102 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 274437.2
31127880 | R2Z-AVENA 1701 WIRE-DOWN RECONDUCTOR | 109963359 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/28/2018 | ED.16357.1701 | AVENA 1701 | 039 | SAN JOAQUIN CO | 5535457 | DO 08 - Monthly Forecast Only | 3,802.000 | 3,802.000 | 08J | 01/13/2015 | 2015 | 09/15/2018 | 2018 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31127880_AVENA 1701 WIRE-DOWN RECONDUCT | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 135698.48
31128279 | OCGC SPAULDING 1101 WIREDOWN SS OF 6607 | 109970034 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/30/2016 | ED.15225.1101.SWIT | SWITCHES | 029 | NEVADA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 269.000 | 269.000 | 08W | 01/15/2015 | 2015 | 01/28/2017 | 2017 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 81697.19
31129645 | OCCCSAN RAFAEL 1106 DETER COND H<(>&<)>F | 109970930 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2016 | ED.04201.1106.SWIT | SWITCHES | 021 | MARIN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 1,614.000 | 1,614.000 | 08J | 01/21/2015 | 2015 | 10/03/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31129645_R7 SAN RAFAEL 1106 DETER COND H | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 372160.67
31129648 | OCCCSN RAFAEL 1106 DETER COND G & FORBES | 109970932 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2016 | ED.04201.1106.SWIT | SWITCHES | 021 | MARIN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 2,240.000 | 0.000 | 08J | 01/21/2015 | 2015 | 09/15/2018 | 2018 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31129648_R7 SAN RAFAEL 1106 DETER COND G | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 365930.37
31129793 | RECONDUCTOR WILLIAMS 1101 - Y2017 | 109976607 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 07/29/2017 | ED.06205.1101.COND | CONDUCTOR | 006 | COLUSA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 1,529.000 | 1,529.000 | 08J | 01/22/2015 | 2015 | 07/15/2017 | 2017 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 94979.57
31129830 | OCCC BIG TREES 402 _ 14-0076789 PHASE 1 | 109992256 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/15/2017 | ED.08305.0402 | BIG TREES 0402 | 044 | SANTA CRUZ COU | 5532479 | CWSP 08W - Monthly Forecast Only | 1,360.000 | 1,360.000 | 08W | 01/22/2015 | 2015 | 03/10/2018 | 2018 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31129830_R2 WD BIG TREES 402 PHASE 1 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 259437.42
31130513 | VIEJO 2202 WIRE DOWN 3191 17 MI DR | 109981458 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/28/2017 | ED.18285.2202 | VIEJO 2202 | 027 | MONTEREY COUNT | 5517127 | DO 08 - Monthly Forecast Only | 989.000 | 440.000 | 08J | 01/27/2015 | 2015 | 11/24/2018 | 2018 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 190007.86
31131282 | OCCC XMABRY 1101-OH RECONDUCTOR & COMBO | 110012433 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 01/31/2017 | ED.78-F182100000.STRU.POLE | SAN JOSE F1821 POLES | 043 | SANTA CLARA CO | 5535457 | DO 08 - Monthly Forecast Only | 99.000 | 0.000 | 08J | 01/29/2015 | 2015 | 03/31/2018 | 2018 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 68072.83
31131283 | R2Z V2101 14-0076675 COWARD RD | 110012779 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/13/2017 | ED.08319.2101 | GREEN VALLEY 2101 | 044 | SANTA CRUZ COU | 5535457 | DO 08 - Monthly Forecast Only | 786.000 | 0.000 | 08J | 01/29/2015 | 2015 | # | #VALUE! | UNSC | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 92331.7
31131288 | R2Z WD GV2101 14-0076675 SAN JUAN RD | 110012774 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/24/2017 | ED.08319.2101 | GREEN VALLEY 2101 | 044 | SANTA CRUZ COU | 5535457 | DO 08 - Monthly Forecast Only | 1,331.000 | 1,277.000 | 08J | 01/29/2015 | 2015 | 04/25/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 18663.72
31132477 | RELIAIBLITY OAKLAND-REPLACE 1/0 OH | 110022784 | # | Not assigned | 30 | Technically Completed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/30/2016 | ED.01204.1105 | OAKLAND D 1105 | 001 | ALAMEDA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 606.000 | 740.000 | 08J | 02/04/2015 | 2015 | # | #VALUE! | FICL | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 180140.48
31132867 | HMB1101 REPLACE OH LINE SKYLINE BLVD | 110026264 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2018 | ED.02410.1101.RECL | RECLOSERS | 041 | SAN MATEO COUN | 5535211 | CWSP SPO - SH 08 | 4,638.000 | 4,638.000 | 08W | 02/05/2015 | 2015 | 01/12/2019 | 2019 | CLSD | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | 31132867_ REPLACE OH LINE SKYLINE BLVD | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 715788.12
31133991 | OCGC WIRE DOWN-RECONDUCTOR LIVE OAK 1102 | 110045663 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/29/2017 | ED.15377.1102.TXFR.TROH | OVERHEAD TRANSFORMERS | 051 | SUTTER COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 430.000 | 0.000 | 08W | 02/12/2015 | 2015 | 12/17/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 45113.39
31134351 | +MESA 1102 (JOSHUA ST & ORCHARD RD) | 110048041 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2017 | ED.18282.1102 | MESA 1102 | 040 | SAN LUIS OBISP | 5532479 | CWSP 08W - Monthly Forecast Only | 2,038.000 | 0.000 | 08W | 02/13/2015 | 2015 | 02/18/2017 | 2017 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 78373.17
31136738 | X-KING CITY 1102 WD 15-0009162 | 110062194 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2017 | ED.18203.1102 | KING CITY 1102 | 027 | MONTEREY COUNT | 5532479 | CWSP 08W - Monthly Forecast Only | 293.000 | 0.000 | 08W | 02/24/2015 | 2015 | 09/02/2017 | 2017 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 5000.01
31138878 | *CANC* KING CITY 1102 WD 15-0009162 | 110077600 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2017 | ED.18203.1102 | KING CITY 1102 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 03/05/2015 | 2015 | 03/21/2015 | 2015 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31139913 | +SANTA MARIA 1110 ANNEALED RIVER X-ING | 110088290 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/02/2015 | ED.18267.1110 | SANTA MARIA 1110 | 042 | SANTA BARBARA | 5532479 | CWSP 08W - Monthly Forecast Only | 1,282.000 | 0.000 | 08W | 03/10/2015 | 2015 | 01/28/2017 | 2017 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 69516.76
31140055 | OCGC RECONDUCTOR PUEBLO 2103 AT SW 7927 | 110071673 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/01/2017 | ED.04329.2103 | PUEBLO 2103 | 028 | NAPA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 727.000 | 0.000 | 08W | 03/10/2015 | 2015 | 02/11/2017 | 2017 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31140055_RECONDUCTOR PUEBLO 2103 AT SW 7 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 96664.22
31141749 | STOREY 1104 RECONDUCTORING | 110110392 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2017 | ED.25461.1104 | STOREY 1104 | 020 | MADERA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 2,036.000 | 2,056.000 | 08J | 03/17/2015 | 2015 | 10/21/2017 | 2017 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 88478.96
31142343 | R2 2017 KERMAN 1102 RECONDUCTOR WIREDOWN | 110113851 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.25271.1102 | KERMAN 1102 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 5,485.000 | 0.000 | 08J | 03/19/2015 | 2015 | # | #VALUE! | CONS | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31142343_Kerman 1102 Reconductor | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 319209.45
31143734 | 2016 REEDLEY 1104 WIRE DOWN RECONDUCT | 110124138 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/29/2017 | ED.25234.1104 | REEDLEY 1104 | 010 | FRESNO COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 1,780.000 | 0.000 | 08W | 03/26/2015 | 2015 | 01/14/2017 | 2017 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31143734_R2REEDLEY 1104 WIRE DOWN RECOND | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 112607.49
31144558 | WDN 15-0013313 CE2105-HUBBARD GULCH | 110143726 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 07/24/2017 | ED.08362.2105 | CAMP EVERS 2105 | 044 | SANTA CRUZ COU | 5532479 | CWSP 08W - Monthly Forecast Only | 2,413.000 | 2,500.000 | 08W | 03/31/2015 | 2015 | 02/04/2017 | 2017 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | WDN 15-0013313 CE2105-HUBBARD GULCH | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 158320.08
31144778 | OCGC TRINIDAD 1102 EXCESSIVE SPLICES | 110143065 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/29/2017 | ED.36-J080400000.STRU.POLE | EUREKA J0804 POLES | 012 | HUMBOLDT COUNT | 5532479 | CWSP 08W - Monthly Forecast Only | 2,062.000 | 0.000 | 08W | 03/31/2015 | 2015 | 09/23/2017 | 2017 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 179750.49
31144782 | 2017 KERNEY 1104 RECONDUCTOR WIREDOWN | 110119842 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/30/2017 | ED.25270.1104 | KEARNEY 1104 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 1,600.000 | 1,787.000 | 08J | 03/31/2015 | 2015 | 12/16/2017 | 2017 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31144782_Kearney 1104 Reconductor | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 125758.87
31145622 | OCGC 2016 CORCORAN 1108 RECOND WIREDOWN | 110150856 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/31/2017 | ED.25217.1108 | CORCORAN 1108 | 016 | KINGS COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 2,164.000 | 2,164.000 | 08W | 04/03/2015 | 2015 | 07/14/2018 | 2018 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31145622_Corcoran 1108 Reconductor | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 239258.71
31147897 | CAR403 REPLACE 250FT OF OH LINE | 110172675 | # | Not assigned | 30 | Technically Completed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 01/29/2016 | JY | JUNK YARD FL TO HOLD DELETED DATA | 041 | SAN MATEO COUN | 5505513 | PN-OH ANNEALED/DETER CNDCTR: PM MGD | 122.000 | 150.000 | 08J | 04/14/2015 | 2015 | # | #VALUE! | FICL | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 64004.61
31148548 | +FAIRWAY 1106 RECONDUCTOR | 110177529 | # | Not assigned | 30 | Technically Completed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2017 | ED.18206.1106 | FAIRWAY 1106 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 289.000 | 289.000 | 08J | 04/15/2015 | 2015 | # | #VALUE! | FICL | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 175973.79
31150684 | MORAGA 1103 RECNDUCTOR 350' (2SPANS) | 110292425 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/28/2016 | ED.01380.1103 | MORAGA 1103 | 007 | CONTRA COSTA C | 5532479 | CWSP 08W - Monthly Forecast Only | 350.000 | 362.000 | 08W | 04/24/2015 | 2015 | 01/29/2018 | 2018 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 95671.48
31151064 | RECONDUCT ON U1112 | 110308182 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2018 | ED.24-H072500000.STRU.ENCL | MISSION H0725 ENCLOSURE | 001 | ALAMEDA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 177.000 | 0.000 | 08J | 04/28/2015 | 2015 | # | #VALUE! | PEND | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 7953.86
31152787 | OCLH CLOVIS 2110 WIRE DOWN RECONDUCTOR | 110365473 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/29/2017 | ED.25408.2110 | CLOVIS 2110 | 010 | FRESNO COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 452.000 | 0.000 | 08W | 05/05/2015 | 2015 | 07/25/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 62445.03
31153724 | OCGC BANTA 1103 RECOND 968FT 6CU | 110374316 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/14/2017 | ED.16247.1103 | BANTA 1103 | 039 | SAN JOAQUIN CO | 5532479 | CWSP 08W - Monthly Forecast Only | 940.000 | 940.000 | 08W | 05/08/2015 | 2015 | 12/17/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 32756.84
31154886 | OCGC EP RECONDUCTOR ARBUCKLE 1102 -Y2016 | 110392964 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 07/29/2017 | ED.06208.1102.COND | CONDUCTOR | 006 | COLUSA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 212.000 | 212.000 | 08W | 05/14/2015 | 2015 | 11/19/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 26900.69
31155091 | *CANC* ACSR REPLACEMENT Q4 FUSE 894*CANC | 110393781 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2018 | ED.18267.1109 | SANTA MARIA 1109 | 040 | SAN LUIS OBISP | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 05/15/2015 | 2015 | 01/04/2018 | 2018 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31155091_R5 SBWF ACSR REPLACEMENT Q4 FUS | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31155092 | R5 SBWF MESA 1102 & SM 1109, VARIOUS, SM | 110393688 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/30/2020 | ED.18267.1109 | SANTA MARIA 1109 | 040 | SAN LUIS OBISP | 5535457 | DO 08 - Monthly Forecast Only | 6,578.000 | 5,709.000 | 08J | 05/15/2015 | 2015 | # | #VALUE! | DOCC | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31155092_R5 SBWF ACSR REPLACEMENT QUADRA | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 319625.93
31156130 | SAN ARDO 1102 WD #15-0024843 | 110387746 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2017 | ED.18219.1102 | SAN ARDO 1102 | 027 | MONTEREY COUNT | 5532479 | CWSP 08W - Monthly Forecast Only | 2,410.000 | 2,415.000 | 08W | 05/20/2015 | 2015 | 03/25/2017 | 2017 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 72660.03
31156133 | 2017 DEVILS DEN 1102 6CU RECONDUCTOR | 110399522 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/30/2018 | ED.25345.1102 | DEVILS DEN 1102 | 015 | KERN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 1,321.000 | 1,400.000 | 08J | 05/20/2015 | 2015 | 10/17/2018 | 2018 | PREC | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31156133_R2 2017 DEVILS DEN 1102 6CU REC | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 89858.9
31157217 | STONE 1108 RECONDUCTOR | 110411801 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/01/2017 | ED.08370.1108.SWIT | SWITCHES | 043 | SANTA CLARA CO | 5535457 | DO 08 - Monthly Forecast Only | 443.000 | 0.000 | 08J | 05/27/2015 | 2015 | 01/29/2018 | 2018 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 120009.54
31157301 | X-RECNDUCTR-POINT M1101_2598 SMITH GRDE | 110411551 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/30/2017 | ED.08293.1101 | POINT MORETTI 1101 | 044 | SANTA CRUZ COU | 5532479 | CWSP 08W - Monthly Forecast Only | 616.000 | 616.000 | 08W | 05/27/2015 | 2015 | 06/17/2018 | 2018 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 53367.68
31157526 | OCGCEP LOGAN CREEK 2101 RECOND 3550' 6CU | 110414106 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/15/2018 | ED.14-Y191300000 | GLENN MAP Y1913 | 011 | GLENN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 3,122.000 | 3,122.000 | 08J | 05/28/2015 | 2015 | 05/04/2019 | 2019 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31157526_EP RECONDUCTOR 3590# #6CU, WILL | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 453867.18
31157542 | OCGC CHROKEE 1102 RECNDUCTOR 1300FT | 110413742 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/30/2017 | ED.16365.1102 | CHEROKEE 1102 | 039 | SAN JOAQUIN CO | 5535457 | DO 08 - Monthly Forecast Only | 1,412.000 | 1,412.000 | 08J | 05/28/2015 | 2015 | 01/13/2018 | 2018 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | CHROKEE 1102 RECNDUCTOR 1300FT W/4/0AL | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 95513.19
31157544 | OCGC MCCALL 1106 WIREDOWN RECONDUCTOR | 110412896 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/29/2018 | ED.25412.1106 | MC CALL 1106 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 2,300.000 | 7,221.000 | 08J | 05/28/2015 | 2015 | 11/07/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | R2 MCCALL 1106 WIREDOWN RECONDUCTOR | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 155786.85
31157545 | OCGC HARDWICK 1102 WIRE DWN RECNDUCTOR | 110412892 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/29/2017 | ED.25371.1102 | HARDWICK 1102 | 016 | KINGS COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 2,487.000 | 0.000 | 08W | 05/28/2015 | 2015 | 02/18/2017 | 2017 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | R2 HARDWICK 1102 WIRE DOWN RECONDUCTOR | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 144185.89
31157953 | RECON 1SPAN N/O FISH ROCK GUALALA1112 | 110417407 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/29/2017 | ED.04284.1112.SWIT | SWITCHES | 023 | MENDOCINO COUN | 5532479 | CWSP 08W - Monthly Forecast Only | 390.000 | 0.000 | 08W | 05/29/2015 | 2015 | 01/28/2017 | 2017 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 34918.81
31158390 | +RECOND 960 FT OF 4 ACSR ON SLO 1101 | 110421174 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2017 | ED.18263.1101 | SAN LUIS OBISPO 1101 | 040 | SAN LUIS OBISP | 5535457 | DO 08 - Monthly Forecast Only | 994.000 | 994.000 | 08J | 06/02/2015 | 2015 | # | #VALUE! | DOCC | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 348209.58
31162678 | H-1107 RECONDUCTOR | 110459273 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/30/2017 | ED.02210.1107 | SF H 1107 | 038 | SAN FRANCISCO | 5535457 | DO 08 - Monthly Forecast Only | 4,151.000 | 4,100.000 | 08J | 06/25/2015 | 2015 | 01/19/2019 | 2019 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31162678_R1 H-1107 RECONDUCTOR | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 1109605.59
31162833 | REPL DETERIORATED COND _MCARTHUR 1101 | 110467479 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/01/2017 | ED.87-D540000000 | SHASTA MAP D54 | 045 | SHASTA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 2,697.000 | 08J | 06/22/2015 | 2015 | 11/25/2017 | 2017 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31162833_REPL COND _MCARTHUR 1101 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 263179.71
31163618 | SOLEDAD 2102 RECONDUCTORING JOB | 110470402 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/29/2018 | ED.18205.2102 | SOLEDAD 2102 | 027 | MONTEREY COUNT | 5532479 | CWSP 08W - Monthly Forecast Only | 2,029.000 | 2,070.000 | 08W | 06/24/2015 | 2015 | # | #VALUE! | DOCC | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 105157.23
31163857 | X LOS OSITOS 2102 WDWN_15-0036239 | 110471625 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 07/28/2018 | ED.18208.2102 | LOS OSITOS 2102 | 027 | MONTEREY COUNT | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 931.000 | 08W | 06/24/2015 | 2015 | 12/23/2017 | 2017 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 71995.83
31163921 | X SALINAS 1104 RECONDUCTORING JOB | 110472227 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2017 | ED.18201.1104 | SALINAS 1104 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 629.000 | 629.000 | 08J | 06/24/2015 | 2015 | 08/18/2018 | 2018 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 53892.17
31164796 | *CANC* EP HWY 45 ANNEALED COND PH 4*CANC | 110474611 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2017 | ED.14-Y230000000 | GLENN MAP Y23 | 011 | GLENN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 06/29/2015 | 2015 | 09/03/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31164798 | *CANC* EP HWY 45 ANNEALED COND PH 5*CANC | 110474612 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2017 | ED.14-Z230000000 | GLENN MAP Z23 | 011 | GLENN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 06/29/2015 | 2015 | 09/03/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31164840 | EP PRATTVILLE ANNEALED CONDUCTOR PHASE 3 | 110474613 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2017 | ED.18-J450000000 | LAS PLUMAS MAP J45 | 032 | PLUMAS COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 06/29/2015 | 2015 | # | #VALUE! | UNSE | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 164.29
31164841 | EP PRATTVILLE ANNEALED CONDUCTOR PHASE 4 | 110474614 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2017 | ED.18-J450000000 | LAS PLUMAS MAP J45 | 032 | PLUMAS COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 06/29/2015 | 2015 | # | #VALUE! | UNSE | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 164.29
31164842 | *CANC* EP RD D ANNEALED COND PH 3 *CANC | 110474615 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2017 | ED.14-Z170000000 | GLENN MAP Z17 | 011 | GLENN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 06/29/2015 | 2015 | 09/03/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31164843 | EP CAPAY 1101 ANNEALED CONDUCTOR PHASE 2 | 110474616 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2017 | ED.14-S210000000 | GLENN MAP S21 | 011 | GLENN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 06/29/2015 | 2015 | # | #VALUE! | UNSE | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 20650.53
31165740 | *CANC* R7 NAPA 1109 WIRE DOWN AT S *CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/30/2017 | ED.04202.1109 | NAPA 1109 | 028 | NAPA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 07/02/2015 | 2015 | 05/03/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31169728 | 2017 GRIZZLY PEAK REPL #6 CU-UWF | 110515764 | # | Not assigned | 40 | Closed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 09/01/2018 | ED.01204.1112 | OAKLAND D 1112 | 001 | ALAMEDA COUNTY | 5535211 | CWSP SPO - SH 08 | 5,938.000 | 4,093.000 | 08W | 07/17/2015 | 2015 | 01/18/2020 | 2020 | CLSD | E070 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | 31169728_RELIAIB 2017:OAK-REPL #6 CU-UWF | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 718126.93
31169729 | OCGCABILITY 2017 D1112/K1101 UWF | 110515765 | # | Not assigned | 40 | Closed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 03/14/2018 | ED.01250.1105 | EL CERRITO G 1105 | 001 | ALAMEDA COUNTY | 5535211 | CWSP SPO - SH 08 | 4,171.000 | 4,171.000 | 08W | 07/17/2015 | 2015 | 03/23/2019 | 2019 | CLSD | E070 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | 31169729_R1-RELIAIB 2017 D1112/K1101 UWF | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 685267.46
31170650 | X-SAN BENITO 2101 WIREDOWN 15-0039468 | 110526215 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 08/03/2018 | ED.18274.2101 | SAN BENITO 2101 | 035 | SAN BENITO COU | 5532479 | CWSP 08W - Monthly Forecast Only | 527.000 | 0.000 | 08W | 07/21/2015 | 2015 | 12/17/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 16199.08
31170652 | +RECONDUCTOR 1700 FT- FAIRWAY 1103 | 110526754 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/30/2017 | ED.18267.1107 | SANTA MARIA 1107 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 1,771.000 | 1,770.000 | 08J | 07/21/2015 | 2015 | 04/21/2018 | 2018 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31170652_R5 RECONDUCTR 1700 FT ON SNTA M | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 241067.48
31171405 | OCGC TULACAY 1101 WIRE DOWN AT LR 628 | 110532349 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 07/24/2017 | ED.04230.1101 | TULUCAY 1101 | 028 | NAPA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 3,236.000 | 3,236.000 | 08J | 07/24/2015 | 2015 | 09/28/2019 | 2019 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31171405_R7 TULACAY 1101 WIRE DOWN AT LR | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 327869.07
31171820 | WYANDOTTE 1105-DEADWOOD ROAD 08J Y2017 | 110535043 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/16/2017 | ED.17-T360000000 | PARADISE MAP T36 | 004 | BUTTE COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 8,515.000 | 8,515.000 | 08J | 07/27/2015 | 2015 | 04/21/2018 | 2018 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31171820_WYANDOTTE 1105 - DEADWOOD ROAD | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 626708.82
31173137 | *CANC* CANAL 1104 RECOND 269FT 4AR TO | 110543237 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/13/2017 | ED.25209.1104 | CANAL 1104 | 024 | MERCED COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 07/31/2015 | 2015 | 07/06/2019 | 2019 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31173660 | OCGC SANTA ROSA A 1108 RECOND 6SPANS | 110545426 | # | Not assigned | 30 | Technically Completed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 06/30/2017 | ED.04215.1108.SWIT | SWITCHES | 049 | SONOMA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 1,097.000 | 0.000 | 08W | 08/04/2015 | 2015 | # | #VALUE! | FICL | E070 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31173660_SANTA ROSA A 1108 RECOND 6SPANS | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 228274.06
31174512 | OCGC 6-SPANS BODEGA AVE- PETALUMA 1108 | 110557491 | # | Not assigned | 30 | Technically Completed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 05/26/2017 | ED.04263.1108.SWIT | SWITCHES | 049 | SONOMA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 1,630.000 | 08J | 08/07/2015 | 2015 | # | #VALUE! | FICL | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 96484.31
31175108 | *CANC* R1-EB- R1127- RECOND 1,850' *CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/31/2016 | ED.01347.1127 | RICHMOND R 1127 | 007 | CONTRA COSTA C | 5517127 | DO 08 - Monthly Forecast Only | 1,850.000 | 0.000 | 08J | 08/11/2015 | 2015 | 05/03/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31175272 | OC4 OCGC EP HWY 193 RECONDUCTOR 4 SPANS | # | 30958463 | OC4 OCGC EP HWY 193 RELO NEWCASTLE | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/09/2015 | ED.20-U050000000.STRU.POLE | PLACER U05 POLES | 031 | PLACER COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 1,140.000 | 1,140.000 | 08J | 08/11/2015 | 2015 | 04/22/2017 | 2017 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 40188.33
31175501 | OCGC MALAGA 1102 NORTH AVE. WIRE DOWN | 110570964 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/27/2017 | ED.25425.1102 | MALAGA 1102 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 2,982.000 | 2,982.000 | 08J | 08/12/2015 | 2015 | 01/20/2018 | 2018 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31175501_R2 MALAGA 1102 NORTH AVE. WIRE | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 212336.87
31175815 | *CANC* SIQUOC 1104 WIREDOWN RECOND *CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.18281.1104 | SISQUOC 1104 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 08/13/2015 | 2015 | 05/03/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31175815_SIQUOC 1104 WIREDOWN RECONDUCTO | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31175817 | +OCEANO 1108 WIREDOWN 15-0043519 | 110574855 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/30/2017 | ED.18260.1108 | OCEANO 1108 | 040 | SAN LUIS OBISP | 5532479 | CWSP 08W - Monthly Forecast Only | 2,177.000 | 0.000 | 08W | 08/13/2015 | 2015 | 02/11/2017 | 2017 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31175817_R2 OCEANO 1108 WIREDOWN 15-0043 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 87077.03
31177369 | R5 SBWF FW 1107 & DIV 1104, HWY 1 & BLK | 110584979 | # | Not assigned | 30 | Technically Completed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/30/2020 | ED.18206.1107 | FAIRWAY 1107 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 6,972.000 | 6,867.000 | 08J | 08/20/2015 | 2015 | # | #VALUE! | FICL | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31177369_R2 SBWF ACSR REPLACEMENT SS DEV | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 385075.23
31178055 | SBWF SM 1105 & 1109, N/O W MAIN, SM | 110588965 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2019 | ED.18267.1105 | SANTA MARIA 1105 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 4,292.000 | 4,292.000 | 08J | 08/21/2015 | 2015 | # | #VALUE! | DOCC | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31178055_R5 SBWF ACSR REPLACEMENT Q4 FUS | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 235553.05
31178774 | SANTA MARIA 1109, SPLICE COUNT REDUCTION | 110590307 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2017 | ED.18267.1109 | SANTA MARIA 1109 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 08/25/2015 | 2015 | # | #VALUE! | UNSE | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 2181.65
31178776 | +WF RECOND 6044' FSE 65535 MESA 1102 | 110590411 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/30/2017 | ED.18282.1102 | MESA 1102 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 6,436.000 | 6,436.000 | 08J | 08/25/2015 | 2015 | 08/05/2017 | 2017 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31178776_R5 SBWF RECOND 6044' FSE 65535 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 227621.57
31178777 | MESA 1102 RANCHO GAUDALUPE PRESERVE | 110590412 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/30/2020 | ED.18282.1102 | MESA 1102 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 3,849.000 | 3,900.000 | 08J | 08/25/2015 | 2015 | # | #VALUE! | MAPP | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31178777_R5 RECOND 3,926' AT FUCO 6147 M | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 408970.73
31178778 | SBWF SM 1110 NO BROWN RD, GUADALUPE | 110590470 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2018 | ED.18267.1110 | SANTA MARIA 1110 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 6,801.000 | 6,801.000 | 08J | 08/25/2015 | 2015 | 08/29/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31178778_R2 SBWF NO OF BROWN RD SANTA MA | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 572217.9
31178779 | TO BE CANCELLED GUERNSEY 1106 RECON | 110591852 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/29/2017 | ED.25266.1106 | GUERNSEY 1106 | 016 | KINGS COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 694.000 | 0.000 | 08J | 08/25/2015 | 2015 | 11/10/2018 | 2018 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 830.34
31178822 | WEST FRESNO 1111 RECONDUCTORING | 110592149 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 05/31/2017 | ED.25373.1111 | WEST FRESNO 1111 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 4,615.000 | 4,615.000 | 08J | 08/25/2015 | 2015 | 04/21/2018 | 2018 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31178822_WEST FRESNO 1111 RECONDUCTORING | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 205713.44
31179069 | RECONDUCTR 4CU ON J1110 WIREDOWN | 110596932 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/30/2016 | ED.01350.1110 | JARVIS 1110 | 001 | ALAMEDA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 440.000 | 08J | 08/26/2015 | 2015 | 03/30/2019 | 2019 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 18493.75
31179237 | STONE 1110 RECONDUCTOR | 110602784 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/01/2017 | ED.08370.1110 | STONE 1110 | 043 | SANTA CLARA CO | 5535457 | DO 08 - Monthly Forecast Only | 295.000 | 280.000 | 08J | 08/27/2015 | 2015 | 12/23/2017 | 2017 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 92353.49
31179810 | OCGC REPLACE 7800' OF 6C ON CATLETT 1105 | 110605023 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2017 | ED.15376.1101.SWIT | SWITCHES | 051 | SUTTER COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 7,753.000 | 7,753.000 | 08J | 08/28/2015 | 2015 | 12/22/2018 | 2018 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31179810_REPLACE 7800' OF 6C ON CATLETT | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 743550.94
31180009 | +CAB 1104 SO CENTRAL & DE WOLFF, LOMPOC | 110604817 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2018 | ED.18281.1104 | SISQUOC 1104 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 1,400.000 | 1,400.000 | 08J | 08/28/2015 | 2015 | 11/04/2019 | 2019 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31180009_R2CABRILO 1104 WD RECNDUCTORING | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 93348.46
31180010 | +CHOLAME 1101 WD RECONDUCTORING | 110606328 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2019 | ED.18256.1101 | CHOLAME 1101 | 040 | SAN LUIS OBISP | 5535457 | DO 08 - Monthly Forecast Only | 1,479.000 | 1,479.000 | 08J | 08/28/2015 | 2015 | 09/05/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31180010_R5 CHOLAME 1101 WD RECONDUCORIN | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 123596.98
31181229 | 2017WEST FRESNO 1112 RECOND MARKS AVE | 110612424 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 05/31/2018 | ED.25373.1112 | WEST FRESNO 1112 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 2,485.000 | 2,942.000 | 08J | 09/02/2015 | 2015 | 03/23/2019 | 2019 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31181229_R2 2017WEST FRESNO 1112 RECOND | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 413489.1
31181527 | RECONDUCTOR 4ACSR ON N1106_WIREDOWN | 110618313 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/30/2016 | ED.01222.1106.TXFR.TRSS | SUBSURFACE TRANSFORMERS | 001 | ALAMEDA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 429.000 | 180.000 | 08J | 09/04/2015 | 2015 | 01/20/2018 | 2018 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 27340.1
31182216 | RECON 11-SPANS (MADISON&MARIA) PET 1105 | 110623679 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/03/2017 | ED.04263.1105.SWIT | SWITCHES | 049 | SONOMA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 3,924.000 | 0.000 | 08J | 09/08/2015 | 2015 | # | #VALUE! | PEND | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 82807.18
31183281 | *CANC* W FRESNO 1111 - RECOND PH II*CANC | 110625900 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/07/2017 | ED.25373.1111 | WEST FRESNO 1111 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 09/11/2015 | 2015 | 09/03/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31185022 | R2 WF 1111 RECONDUCTOR - VALENTINE AVE. | 110644619 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 07/30/2020 | ED.25373.1111 | WEST FRESNO 1111 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 2,720.000 | 2,720.000 | 08J | 09/16/2015 | 2015 | # | #VALUE! | MAPP | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31185022_R2 WF 1111 RECONDUCTOR - VALENT | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 334856.86
31185480 | R2Z WDN 15-54205 PS2106-BAY AVE | 110653012 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/20/2017 | ED.08325.2106 | PAUL SWEET 2106 | 044 | SANTA CRUZ COU | 5535457 | DO 08 - Monthly Forecast Only | 627.000 | 0.000 | 08J | 09/18/2015 | 2015 | # | #VALUE! | UNSC | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 31423.8
31186256 | SANTA MARIA CONDUCTOR REPLACEMENT | 110659272 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2017 | ED.18267.1109 | SANTA MARIA 1109 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 09/23/2015 | 2015 | # | #VALUE! | UNSE | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 2804.98
31186541 | XSPENCE1121 WD INITIATED RECNDCUTORIN | 110662679 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/29/2017 | ED.18220.1121 | SPENCE 1121 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 713.000 | 713.000 | 08J | 09/24/2015 | 2015 | 07/20/2019 | 2019 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 47402.87
31186569 | SBWF CAB 1104 UNION SGR & CNTRL, LOMPOC | 110664322 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/30/2020 | ED.18310.1104 | CABRILLO 1104 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 7,750.000 | 7,880.000 | 08J | 09/24/2015 | 2015 | # | #VALUE! | DOCC | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31186569_SBWF LOMPOC WEST QUADRANT, CABR | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 349224.03
31187281 | ANNEAL OVRHEAD@50395 SOUTHSIDE_HL210 | 110669987 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 08/31/2017 | ED.18249.2106 | HOLLISTER 2106 | 035 | SAN BENITO COU | 5535457 | DO 08 - Monthly Forecast Only | 468.000 | 0.000 | 08J | 09/28/2015 | 2015 | # | #VALUE! | CONS | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 81189.24
31191256 | RECNDUCTOR 4ACSR ON EDES1111-WIREDOWN | 110720189 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/29/2017 | ED.01368.1111.TXFR.TRSS | SUBSURFACE TRANSFORMERS | 001 | ALAMEDA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 654.000 | 654.000 | 08J | 10/14/2015 | 2015 | 09/28/2019 | 2019 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 48217.54
31193590 | +R5 DIVIDE 1102 WD RECONDUCTORING | 110677980 | # | Not assigned | 30 | Technically Completed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/30/2020 | ED.18282.1102 | MESA 1102 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 1,080.000 | 1,080.000 | 08J | 10/21/2015 | 2015 | # | #VALUE! | FICL | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31193590_DIVIDE 1102 WD RECONDUCTORING | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 326101.26
31193592 | +SBWF-BONITA LATERAL-SANTA MARIA 1105 | 110768828 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 08/30/2017 | ED.18266.1105 | SAN MIGUEL 1105 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 7,318.000 | 7,316.000 | 08J | 10/21/2015 | 2015 | 01/20/2018 | 2018 | PREC | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31193592_R5 SBWF-BONITA LATERAL -SANTA M | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 307725.37
31193593 | SBWF MESA 1102 SO DIVISION ST, GUADALUPE | 110770251 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2018 | ED.18282.1102 | MESA 1102 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 5,814.000 | 5,750.000 | 08J | 10/21/2015 | 2015 | 05/30/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31193593_R5 SBWF-SSD: FUSE 45425 - MESA | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 385299.21
31193954 | *CANC* R5 SBWF- MAIN STREET *CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.18267.1109 | SANTA MARIA 1109 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 6,590.000 | 0.000 | 08J | 10/21/2015 | 2015 | 05/03/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31193954_SBWF- MAIN STREET | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31193955 | +SBWF MESA 1102 NO DIVISION ST, GUADALUP | 110771720 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 08/31/2020 | ED.18282.1102 | MESA 1102 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 12,479.000 | 12,479.000 | 08J | 10/21/2015 | 2015 | # | #VALUE! | FICL | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31193955_R5 SBWF- SSD: FUSE 6527 - MESA | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 533669.74
31193990 | MVWF NEAR 99 GREENWOOD WY,ALTO 1124 | 110760456 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/05/2017 | ED.04203.1124 | ALTO 1124 | 021 | MARIN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 2,656.000 | 2,660.000 | 08J | 10/21/2015 | 2015 | 07/20/2019 | 2019 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31193990_R7 ALTO 1124 MVWF CU REPLACE | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 860674.8
31194557 | 2017 LAMONT 1105 WIREDWN 3 SPAN RECO | 110808007 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/29/2017 | ED.25391.1105.SWIT | SWITCHES | 015 | KERN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 884.000 | 884.000 | 08J | 10/24/2015 | 2015 | 05/12/2018 | 2018 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 68681.4
31195933 | ANITA 1106 - REPLACE 2 SPANS & RELOCATE | 110816176 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/30/2018 | ED.16-T280700000 | CHICO MAP T2807 | 004 | BUTTE COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 375.000 | 375.000 | 08J | 10/28/2015 | 2015 | 11/21/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 60717.97
31197019 | *CANC* WEBER 1102 RECONDUCTORING - *CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2019 | ED.16348.1102 | WEBER 1102 | 039 | SAN JOAQUIN CO | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 11/03/2015 | 2015 | 04/04/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | WEBER 1102 RECONDUCTORING - 08J | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31197080 | +SM 1109 RAY RD SO MAIN, SANTA MARIA | 110823732 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2019 | ED.18267.1109 | SANTA MARIA 1109 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 6,128.000 | 6,128.000 | 08J | 11/03/2015 | 2015 | # | #VALUE! | DOCC | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31197080_SANTA MARIA SPLICE COUNT REDUCT | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 310674.28
31197255 | EFFEY ST-PS2108-WDW-15-0060680 | 110828922 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 08/26/2017 | ED.08325.2108 | PAUL SWEET 2108 | 044 | SANTA CRUZ COU | 5535457 | DO 08 - Monthly Forecast Only | 272.000 | 0.000 | 08J | 11/03/2015 | 2015 | # | #VALUE! | CONS | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 70764.03
31197256 | *CANC*SBWF LOMPOC S-QUADRANT-CABRIL*CANC | 110829208 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/01/2017 | ED.18310.1104 | CABRILLO 1104 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 11/03/2015 | 2015 | 11/03/2018 | 2018 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31197754 | OCGC RECON4SPANS CANYON ROCK MIRABEL1101 | 110835287 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/29/2017 | ED.04209.1101.SWIT | SWITCHES | 049 | SONOMA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 923.000 | 1,100.000 | 08J | 11/05/2015 | 2015 | 03/25/2017 | 2017 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 104177.5
31200934 | MVWF CALIFRNIA<(>&<)>PRINCTON, ALTO 1125 | 110860125 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 08/31/2017 | ED.04203.1125 | ALTO 1125 | 021 | MARIN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 2,682.000 | 2,680.000 | 08J | 11/18/2015 | 2015 | 07/21/2018 | 2018 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31200934_R7 ALTO 1125 MVWF CU REPLACE | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 481511.33
31200935 | MVWF ROSEMONT & JULIA ST.ALTO 1120 | 110852792 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/28/2017 | ED.04203.1120 | ALTO 1120 | 021 | MARIN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 3,025.000 | 2,864.000 | 08J | 11/18/2015 | 2015 | 06/17/2018 | 2018 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31200935_R7 ALTO 1120 MVWF CU REPLACE | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 503819.78
31202926 | REMOVE SPLICES AND INSTALL FUSES | 110878696 | # | Not assigned | 30 | Technically Completed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/15/2016 | ED.02425.1105.SWIT | SWITCHES | 041 | SAN MATEO COUN | 5505513 | PN-OH ANNEALED/DETER CNDCTR: PM MGD | 419.000 | 419.000 | 08J | 11/25/2015 | 2015 | # | #VALUE! | FICL | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 130470.2
31203813 | MVWF STINSON BEACH, BOLINAS 1101 | 110890008 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/14/2017 | ED.04226.1101 | BOLINAS 1101 | 021 | MARIN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 7,378.000 | 0.000 | 08J | 12/02/2015 | 2015 | # | #VALUE! | CONS | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31203813_R7 BOLINAS 1101, REPLACE 9600' | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 923227.52
31204479 | RECOND 3 SPANS GARDEN TRACT | 110939159 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/28/2016 | ED.01347.1129.TXFR.TROH | OVERHEAD TRANSFORMERS | 007 | CONTRA COSTA C | 5532479 | CWSP 08W - Monthly Forecast Only | 362.000 | 1,050.000 | 08W | 12/08/2015 | 2015 | 01/20/2018 | 2018 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 82415.52
31204517 | *DO NOT USE* R4E RECONDUCTOR LIBERTY ISL | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.48-R190000000.STRU.POLE | SOLANO R19 POLES | 048 | SOLANO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 12/07/2015 | 2015 | 03/14/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31204517_R4E RECONDUCTOR LIBERTY ISLND-D | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | -7159.11
31204706 | MVWF THROCKMORTON LANE ALTO 1124 | 110886052 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/12/2017 | ED.04203.1124 | ALTO 1124 | 021 | MARIN COUNTY | 5535211 | CWSP SPO - SH 08 | 1,505.000 | 1,613.000 | 08W | 12/07/2015 | 2015 | 11/04/2019 | 2019 | CLSD | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | 31204706_MVWF THROCKMORTON LANE ALTO 112 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 528490.2
31204707 | MVWF INT KING ST<(>&<)>CORTE MADERA ALTO | 110886059 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/31/2017 | ED.04203.1124 | ALTO 1124 | 021 | MARIN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 1,142.000 | 1,130.000 | 08J | 12/07/2015 | 2015 | 11/05/2019 | 2019 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31204707_ KING ST&CORTE MADERA ALTO 1124 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 424069.61
31205198 | MVWF 206 REED ST, COUNTY, ALTO 1125 | 110886258 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/27/2017 | ED.04203.1125 | ALTO 1125 | 021 | MARIN COUNTY | 5535211 | CWSP SPO - SH 08 | 3,828.000 | 3,900.000 | 08W | 12/10/2015 | 2015 | 11/04/2019 | 2019 | CLSD | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | 31205198_MVWF NEAR 206 REED ST ALTO 1125 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 962856.9
31205258 | *CANC*DONOT USE* MARYSVILLE 1107-GR*CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/30/2016 | ED.15201.1107.TXFR.TROH | OVERHEAD TRANSFORMERS | 051 | SUTTER COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 1,200.000 | 0.000 | 08J | 12/10/2015 | 2015 | 05/03/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31205340 | MVWF RALSTON AVE ALTO 1124 | 110886079 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/29/2017 | ED.04203.1124 | ALTO 1124 | 021 | MARIN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 3,555.000 | 3,700.000 | 08J | 12/10/2015 | 2015 | 09/12/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31205340_R7 MVWF RALSTON AVE ALTO 1124 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 869637.78
31205342 | MVWF 31083407 NEAR 397 ROSE AV ALTO 1124 | 110886302 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/20/2017 | ED.04203.1124 | ALTO 1124 | 021 | MARIN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 1,636.000 | 1,650.000 | 08J | 12/10/2015 | 2015 | 05/12/2018 | 2018 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31205342_MVWF NEAR 397 ROSE AVE ALTO1124 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 665442.42
31205343 | MVWF 388 SUMMIT AVE, CITY, ALTO 1124 | 110886303 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/21/2017 | ED.04203.1124 | ALTO 1124 | 021 | MARIN COUNTY | 5535211 | CWSP SPO - SH 08 | 4,941.000 | 5,006.000 | 08W | 12/10/2015 | 2015 | 11/04/2019 | 2019 | CLSD | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | 31205343_MVWF_388 SUMMIT AVE ALTO 1124 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 1154944.07
31205418 | MVWF BROOKLINE AVE, COUNTY, ALTO 1125 | 111076172 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/20/2017 | ED.04203.1125 | ALTO 1125 | 021 | MARIN COUNTY | 5535211 | CWSP SPO - SH 08 | 5,485.000 | 5,480.000 | 08W | 12/11/2015 | 2015 | 04/20/2019 | 2019 | CLSD | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | 31205418_R7 MVWF BROOKLINE AVE ALTO 1125 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 994666.01
31205937 | 109 HELENS LN,CITY/CNTY,ALTO | 110886301 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/25/2018 | ED.04203.1125 | ALTO 1125 | 021 | MARIN COUNTY | 5535211 | CWSP SPO - SH 08 | 4,464.000 | 5,000.000 | 08W | 12/14/2015 | 2015 | 03/23/2019 | 2019 | CLSD | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | 31205937_MVWF 109 HELENS LANE ALTO 1125 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 1275048.82
31206324 | GABILAN 1101 WIREDWN RECNDUCTORIN | 111092247 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/16/2017 | ED.18233.1101 | GABILAN 1101 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 635.000 | 635.000 | 08J | 12/15/2015 | 2015 | # | #VALUE! | DOCC | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 70299.21
31206677 | OCGC MOHAWK AV CORTE MADERA GREENBRA | 111097628 | # | Not assigned | 30 | Technically Completed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 01/10/2018 | ED.04309.1103 | GREENBRAE 1103 | 021 | MARIN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 4,851.000 | 4,851.000 | 08J | 12/16/2015 | 2015 | # | #VALUE! | FICL | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31206677_CORTE MADERA CORROSION | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 711641.55
31206678 | MVWF SEQUOIA VLY RD CTY/CNTY AL1125/1124 | 111098508 | # | Not assigned | 30 | Technically Completed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 02/22/2018 | ED.04203.1125 | ALTO 1125 | 021 | MARIN COUNTY | 5535211 | CWSP SPO - SH 08 | 2,817.000 | 0.000 | 08W | 12/16/2015 | 2015 | # | #VALUE! | FICL | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | 31206678_SEQUOIA VALLEY RD ALTO1125/1124 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 930103.48
31206912 | X WDN 15-0073161 CE2103-OLD GRAHM HL R | 111108421 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/24/2017 | ED.08362.2103 | CAMP EVERS 2103 | 044 | SANTA CRUZ COU | 5535211 | CWSP SPO - SH 08 | 919.000 | 705.000 | 08W | 12/17/2015 | 2015 | 12/28/2019 | 2019 | CLSD | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 134573.17
31207089 | ESA BOULEVARD ORNE AVE, LARKSPUR GB 1103 | 111097626 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/15/2017 | ED.04309.1103 | GREENBRAE 1103 | 021 | MARIN COUNTY | 5535211 | CWSP SPO - SH 08 | 5,123.000 | 4,890.000 | 08W | 12/16/2015 | 2015 | 06/29/2019 | 2019 | CLSD | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | 31207089_LARKSPUR WF HAWTHORNE AVE | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 1092736.57
31207090 | MVWF VIEWPOINT RD TENNVLY CNTY ALTO 1125 | 111104615 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/02/2018 | ED.04203.1125 | ALTO 1125 | 021 | MARIN COUNTY | 5535211 | CWSP SPO - SH 08 | 6,861.000 | 6,500.000 | 08W | 12/16/2015 | 2015 | # | #VALUE! | DOCC | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | 31207090_R7 MVWF VIEWPOINT RD ALTO 1125 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 1993422.67
31207091 | MVWF BUENA VISTA AVE, CITY ALTO 1124 | 110886251 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/29/2017 | ED.04203.1124 | ALTO 1124 | 021 | MARIN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 2,998.000 | 2,998.000 | 08J | 12/16/2015 | 2015 | # | #VALUE! | DOCC | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31207091_ MVWF BUENA VISTA AVE ALTO 1124 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 1164788.98
31207126 | MVWF PANORAMIC HWY, COUNTY, ALTO 1125 | 111104617 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 01/25/2018 | ED.04203.1125 | ALTO 1125 | 021 | MARIN COUNTY | 5535211 | CWSP SPO - SH 08 | 5,141.000 | 5,300.000 | 08W | 12/17/2015 | 2015 | 07/20/2019 | 2019 | CLSD | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | 31207126_PANORAMIC HIGHWAY ALTO 1125 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 1419528.55
31207128 | *CANC* MVWF ALTO 1125 MUIR WOOD DR *CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2017 | ED.04203.1125 | ALTO 1125 | 021 | MARIN COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 12/17/2015 | 2015 | 05/03/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | 31207128_Alto 1125 Muir Wood | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
31207160 | +SANTA MARIA 1108 WD 15-076543 | 111102564 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/30/2017 | ED.18267.1108 | SANTA MARIA 1108 | 042 | SANTA BARBARA | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 3,297.000 | 08W | 12/17/2015 | 2015 | 12/22/2018 | 2018 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31207160_SANTA MARIA 1108 WD 15-0076534 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 210979.84
31207161 | *CANC*DONOT USE*MORRO BAY 1102 WD 1*CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.18301.1102 | MORRO BAY 1102 | 040 | SAN LUIS OBISP | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 12/17/2015 | 2015 | 05/03/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31207161_MORRO BAY 1102 WD 15-006745 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31207264 | BRENTWOOD 2112-RECOND 616 FEET OF | 111109401 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/01/2017 | ED.01459.2112 | BRENTWOOD 2112 | 007 | CONTRA COSTA C | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 595.000 | 08J | 12/17/2015 | 2015 | 12/12/2018 | 2018 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 66687.88
31207439 | OCCC HMB1101 CO2751 REPL 8CU CONDUCTOR | 111110265 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 05/31/2017 | ED.02410.1101.TXFR.TROH | OVERHEAD TRANSFORMERS | 041 | SAN MATEO COUN | 5505513 | PN-OH ANNEALED/DETER CNDCTR: PM MGD | 2,442.000 | 2,442.000 | 08J | 12/18/2015 | 2015 | 10/21/2017 | 2017 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31207439_HMB1101 CO2751 REPL 8CU CONDUCT | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 194211.93
31208104 | EP-REPLACE TWO SPANS OF 4CU - MCA 1101 | 111115038 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/19/2019 | ED.87-C580000000 | SHASTA MAP C58 | 045 | SHASTA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 797.000 | 800.000 | 08J | 12/22/2015 | 2015 | 04/25/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 37320.8
31208400 | OCGC 1-SPAN, SALMON CREEK 1101-BAY*CV | 111122187 | # | Not assigned | 30 | Technically Completed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/02/2017 | ED.04316.1101.REGL | REGULATORS | 049 | SONOMA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 405.000 | 405.000 | 08J | 12/22/2015 | 2015 | # | #VALUE! | FICL | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 49427.72
31209022 | X WDN 15-76118 PS2107-FUSE 355 AREA | 111126146 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/10/2017 | ED.08325.2107 | PAUL SWEET 2107 | 044 | SANTA CRUZ COU | 5535457 | DO 08 - Monthly Forecast Only | 2,756.000 | 4,676.000 | 08J | 12/28/2015 | 2015 | 09/22/2018 | 2018 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31209022_R2 WDN 15-76118 PS2107-FUSE 355 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 129390.9
31209286 | VIERRA 1707 RECONDUCTORING MANTECA | 111134972 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/02/2020 | ED.16270.1707 | VIERRA 1707 | 039 | SAN JOAQUIN CO | 5535457 | DO 08 - Monthly Forecast Only | 5,207.000 | 0.000 | 08J | 12/29/2015 | 2015 | # | #VALUE! | CONS | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31209286_VIERRA 1707 RECONDUCTORING-08J | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 547743.04
31209454 | *CANC*DONOT USE*KINGCITY 1102 WD RE*CANC | 111136765 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/02/2017 | ED.18203.1102 | KING CITY 1102 | 040 | SAN LUIS OBISP | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 12/30/2015 | 2015 | 05/03/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31209454_R2 KINGCITY 1102 WD RECONDUCTOR | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31209455 | X 8455 AIRLINE HWY-VOO DOO CHI | 111136505 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 08/31/2017 | ED.18249.2105 | HOLLISTER 2105 | 035 | SAN BENITO COU | 5535457 | DO 08 - Monthly Forecast Only | 1,380.000 | 1,380.000 | 08J | 12/30/2015 | 2015 | 02/23/2019 | 2019 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31209455_AIRLINE HWY-VOO DOO CHILE | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 107737.53
31209950 | R7 RECON POTTER VLY 1105 ( VAN ARSDALE) | 111140554 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/29/2017 | ED.04228.1105.SWIT | SWITCHES | 023 | MENDOCINO COUN | 5535211 | CWSP SPO - SH 08 | 3,008.000 | 3,008.000 | 08W | 12/31/2015 | 2015 | # | #VALUE! | DOCC | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | 31209950_Recon Potter Valley 1105 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 1211780.39
31210862 | MANTECA 1705 RECONDUCTORING - 08J | 111158407 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2018 | ED.16261.1705 | MANTECA 1705 | 039 | SAN JOAQUIN CO | 5535457 | DO 08 - Monthly Forecast Only | 2,500.000 | 0.000 | 08J | 01/06/2016 | 2016 | # | #VALUE! | CONS | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31210862_MANTECA 1705 RECONDUCTORING:08J | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 96619.16
31211274 | OCGC PINEDALE 2109 - RECONDUCTOR | 111165334 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/29/2017 | ED.25285.2109 | PINEDALE 2109 | 010 | FRESNO COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 2,200.000 | 2,153.000 | 08W | 01/08/2016 | 2016 | 04/07/2018 | 2018 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 311211274_R2 PINEDALE 2109 - RECONDUCTOR | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 446773.57
31211275 | OCGC CANTUNA 1103 - RECONDUCTORING | 111164945 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/29/2017 | ED.25344.1103 | CALFLAX 1103 | 054 | TULARE COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 1,340.000 | 4,203.000 | 08W | 01/08/2016 | 2016 | 09/15/2018 | 2018 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31211275_R2 CANTUNA 1103 - RECONDUCTORIN | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 142440.95
31212864 | LP402 164 SELBY LN ATHERTON | 111177610 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/28/2017 | ED.02412.0403.TXFR.TROH | OVERHEAD TRANSFORMERS | 041 | SAN MATEO COUN | 5535457 | DO 08 - Monthly Forecast Only | 260.000 | 260.000 | 08W | 01/14/2016 | 2016 | 12/23/2017 | 2017 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 58281
31212877 | EP RECONDUCTOR KNIGHTS LANDING 1102 | 111167180 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2017 | ED.50-F190800000.STRU.POLE | YOLO MAP F1908 POLES | 051 | SUTTER COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 1,437.000 | 0.000 | 08J | 01/14/2016 | 2016 | 07/13/2019 | 2019 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 90522.34
31212878 | RECONDUCTOR GRAND ISLAND 2223 | 111166747 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2017 | ED.48-T230600000.STRU.POLE | SOLANO T2306 POLES | 034 | SACRAMENTO COU | 5535457 | DO 08 - Monthly Forecast Only | 470.000 | 0.000 | 08J | 01/14/2016 | 2016 | # | #VALUE! | UNSC | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 26645.12
31212879 | OCGC RECONDUCTOR 6 CU ON E. NICOLAUS 11 | 111182301 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/29/2017 | ED.11-U250000000.STRU.POLE | MARYSVILLE U25 POLES | 051 | SUTTER COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 551.000 | 08W | 01/14/2016 | 2016 | 01/20/2018 | 2018 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 33747.01
31212921 | HAMMONDS 1104 REPLACE 397AL | 111191839 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.25340.1104 | HAMMONDS 1104 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 7,924.000 | 7,924.000 | 08J | 01/14/2016 | 2016 | 07/04/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31212921_R2 HAMMONDS 1104 REPLACE 397AL | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 1085349.3
31212922 | +SISQUOC 1104 WD-15-0070918 | 111189007 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/30/2017 | ED.18281.1104 | SISQUOC 1104 | 042 | SANTA BARBARA | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 2,885.000 | 08W | 01/14/2016 | 2016 | 09/16/2017 | 2017 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31212922_SISQUOC 1104 WD-15-0070918 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 158146.28
31213040 | OCGC RECONDUCTOR 6 CU ON OLIVEHURST 1104 | 111183617 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/30/2017 | ED.15290.1104.TXFR.TROH | OVERHEAD TRANSFORMERS | 051 | SUTTER COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 144.000 | 08W | 01/14/2016 | 2016 | 06/17/2018 | 2018 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | -198178.17
31214081 | OCGC 3-SPANS(PET 1108)EASTMAN LN*L | 111204778 | # | Not assigned | 30 | Technically Completed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/30/2017 | ED.04263.1108.RECL | RECLOSERS | 049 | SONOMA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 781.000 | 781.000 | 08J | 01/21/2016 | 2016 | # | #VALUE! | FICL | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 65717.42
31214863 | +CAB 1104 NO CENTRAL & DE WOLFF, LOMPO | 111218299 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2018 | ED.18310.1104 | CABRILLO 1104 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 4,831.000 | 4,831.000 | 08J | 01/25/2016 | 2016 | 07/20/2019 | 2019 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31214863_CABRILLO 1104 WD15-0077241 RECO | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 166140.17
31214864 | OCGC KERMAN 1106 - WIRE DOWN RECOND | 111218046 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/28/2017 | ED.25271.1106 | KERMAN 1106 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 2,928.000 | 2,578.000 | 08J | 01/25/2016 | 2016 | 05/18/2019 | 2019 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31214864_R2 KERMAN 1106 - WIRE DOWN RECO | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 156789.87
31215422 | X WDN_15-86669 OLMPIA&LUCY BRWN_SB2102 | 111300423 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/30/2017 | ED.18274.2102 | SAN BENITO 2102 | 035 | SAN BENITO COU | 5535457 | DO 08 - Monthly Forecast Only | 2,860.000 | 2,860.000 | 08J | 01/27/2016 | 2016 | 02/09/2019 | 2019 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31215422_OLMPIA & LUCY BRWN_SB2102 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 274836.11
31215461 | *CANC* SAN ARDO 1102 WD INITIATED RECON | 111305436 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/30/2018 | ED.18219.1102 | SAN ARDO 1102 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 01/28/2016 | 2016 | 03/26/2016 | 2016 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31215474 | RECONDUCTOR ROB ROY 2104-MCDONALD RD | 111305970 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 05/28/2018 | ED.08369.2104 | ROB ROY 2104 | 044 | SANTA CRUZ COU | 5535211 | CWSP SPO - SH 08 | 2,750.000 | 2,769.000 | 08W | 01/28/2016 | 2016 | 06/20/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | 31215474_RECOND ROB ROY 2104-MCDONALD RD | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 541456.85
31216725 | X BEN LOMOND401-RIDGE RD-FUSE6295 | 111324124 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2017 | ED.08304.0401 | BEN LOMOND 0401 | 044 | SANTA CRUZ COU | 5532479 | CWSP 08W - Monthly Forecast Only | 1,147.000 | 1,450.000 | 08W | 02/03/2016 | 2016 | 07/21/2018 | 2018 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31216725_R2 BEN LOMOND401-RIDGE RD-FUSE6 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 176041
31217409 | X ROB ROY2105-SAN ANDREAS RD-2 LOCATIO | 111331499 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/31/2017 | ED.08369.2105 | ROB ROY 2105 | 044 | SANTA CRUZ COU | 5535457 | DO 08 - Monthly Forecast Only | 1,500.000 | 955.000 | 08J | 02/05/2016 | 2016 | 11/21/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31217409_ROY2105-SAN ANDREAS RD-2 LOCAT | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 188439.51
31218969 | MWC 08J EDENV 1102 RELO GIRL'S RANCH | 111352255 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/15/2017 | ED.08295.1102.TXFR.TROH | OVERHEAD TRANSFORMERS | 043 | SANTA CLARA CO | 5535457 | DO 08 - Monthly Forecast Only | 2,637.000 | 2,637.000 | 08J | 02/12/2016 | 2016 | 03/02/2019 | 2019 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31218969 EDENV 1102 - RELO GIRL'S RANCH | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 387574.42
31218981 | ER CEDAR CREEK 1101-UPGRADE 9 SPANS | 111332938 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/01/2016 | ED.13-I200000000 | OROVILLE MAP I20 | 004 | BUTTE COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 2,700.000 | 4,200.000 | 08J | 02/11/2016 | 2016 | 06/17/2018 | 2018 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 75609.82
31219439 | +SANTA MARIA 1105 WD 15-0087677 | 111357580 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2018 | ED.18267.1105 | SANTA MARIA 1105 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 435.000 | 0.000 | 08J | 02/16/2016 | 2016 | # | #VALUE! | CONS | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 95769.04
31219804 | GRAND ISLD 2224 RECOND 800FT 6CU W2A | 111367123 | # | Not assigned | 30 | Technically Completed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2017 | JY | JUNK YARD FL TO HOLD DELETED DATA | 034 | SACRAMENTO COU | 5535457 | DO 08 - Monthly Forecast Only | 883.000 | 2,601.000 | 08J | 02/17/2016 | 2016 | # | #VALUE! | FICL | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 181116.59
31220265 | X DOLAN RD 1101 WD RECONDUCTORING JOB | 111370482 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/01/2018 | ED.18238.1101 | DOLAN ROAD 1101 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 931.000 | 08J | 02/19/2016 | 2016 | 01/18/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 99022.08
31220686 | XWDN_16-6334 PLUMS AV & WRING ST_DM21 | 111373978 | # | Not assigned | 30 | Technically Completed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/30/2018 | ED.18222.2104 | DEL MONTE 2104 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 1,285.000 | 1,285.000 | 08J | 02/22/2016 | 2016 | # | #VALUE! | FICL | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 149697.95
31221409 | OCGC X TERMINOUS 1102 REPL. 800FT W/#2AR | 111380301 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/29/2017 | ED.16302.1102 | TERMINOUS 1102 | 039 | SAN JOAQUIN CO | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 860.000 | 08W | 02/25/2016 | 2016 | 09/15/2018 | 2018 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 49849.13
31221412 | PEORIA FLAT1704-RECOND1,233' OF 4ACSR | 111386471 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/30/2018 | ED.16378.1701 | PEORIA 1701 | 049 | SONOMA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 1,565.000 | 1,565.000 | 08J | 02/25/2016 | 2016 | 03/02/2019 | 2019 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31221412_PEORIA FLAT 1704-RECOND | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 215798.61
31221652 | *CANC*DONOT USE*R7 BASALT 1106 WIRE*CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/30/2017 | ED.04246.1106 | BASALT 1106 | 028 | NAPA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 02/26/2016 | 2016 | 05/03/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31222251 | X WDN_16-09640-212 CREST RD OTTER 1101 | 111397227 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/31/2017 | ED.18294.1101 | OTTER 1101 | 027 | MONTEREY COUNT | 5532479 | CWSP 08W - Monthly Forecast Only | 1,554.000 | 1,554.000 | 08W | 03/01/2016 | 2016 | 07/21/2018 | 2018 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31222251_212 CREST RD OTTER 1101 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 104557.04
31222395 | OCGC LINDEN 1104 RECONDUCTORING | 111399014 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 08/28/2020 | ED.16207.1104 | LINDEN 1104 | 039 | SAN JOAQUIN CO | 5535457 | DO 08 - Monthly Forecast Only | 2,405.000 | 2,405.000 | 08J | 03/01/2016 | 2016 | # | #VALUE! | DOCC | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 119116.4
31224307 | +CABRILLO 1103 WD FUSE AND RECONDUCT | 111429579 | # | Not assigned | 30 | Technically Completed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2018 | ED.18310.1103 | CABRILLO 1103 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 484.000 | 484.000 | 08J | 03/11/2016 | 2016 | # | #VALUE! | FICL | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 43005.52
31229986 | OCGC JACINTO 1101 RECOND 9677'OF 3-6CU | 111520732 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/07/2017 | ED.10285.1101.SWIT | SWITCHES | 004 | BUTTE COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 9,677.000 | 9,677.000 | 08W | 04/08/2016 | 2016 | 03/31/2018 | 2018 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31229986_JACINTO 1101 RECOND 8600' 3-6CU | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 533892.66
31232115 | 2018 WHEELER RIDGE 1102 - RECONDUCTOR | 111551651 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 08/31/2018 | ED.25348.1102.SWIT | SWITCHES | 015 | KERN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 2,961.000 | 2,961.000 | 08J | 04/18/2016 | 2016 | 10/17/2018 | 2018 | PREC | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31232115_R5 WHEELER RIDGE 1102 - RECOND | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 223270.59
31232280 | ZACA 1102 LONG CYN RD, SANTA YNEZ | 111549081 | # | Not assigned | 30 | Technically Completed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2018 | ED.18268.1102 | ZACA 1102 | 042 | SANTA BARBARA | 5535211 | CWSP SPO - SH 08 | 5,851.000 | 5,851.000 | 08W | 04/18/2016 | 2016 | # | #VALUE! | FICL | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Zaca 1102 Repl Det Conductor | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 637321.7
31232282 | +SISQUOC 1104, 3502 TELEPHONE RD, SM | 111549140 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/30/2020 | ED.18281.1104 | SISQUOC 1104 | 040 | SAN LUIS OBISP | 5535457 | DO 08 - Monthly Forecast Only | 7,350.000 | 7,350.000 | 08J | 04/18/2016 | 2016 | # | #VALUE! | DOCC | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31232282_RECON 7500FT WITH #2CU_ANF FUSE | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 531096.65
31232283 | SM 1105 E/O BONITA LATERAL, SM | 111551569 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2018 | ED.18267.1105 | SANTA MARIA 1105 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 9,851.000 | 9,851.000 | 08J | 04/18/2016 | 2016 | 10/17/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Santa Maria 1105 Repl Det Conductor | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 311520.58
31234871 | -RELIAIBLITY 2017 - UWF K1104/X1105/6 | 111583297 | # | Not assigned | 40 | Closed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 11/21/2018 | ED.01210.1104 | OAKLAND K 1104 | 001 | ALAMEDA COUNTY | 5535211 | CWSP SPO - SH 08 | 9,646.000 | 7,271.000 | 08W | 04/28/2016 | 2016 | 01/18/2020 | 2020 | CLSD | E070 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | 31234871_RELIAIB 2017:UWF K1104/X1105/6 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 1751641.12
31234873 | RELIAIBLITY 2017 - UWF X-1104 | 111583299 | # | Not assigned | 40 | Closed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 03/28/2018 | ED.01254.1104 | OAKLAND X 1104 | 001 | ALAMEDA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 2,109.000 | 2,100.000 | 08J | 04/28/2016 | 2016 | 04/25/2020 | 2020 | CLSD | E070 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31234873_RELIAIBLITY 2017 - UWF X-1104 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 564442.85
31234874 | RELIAIBLITY 2017 - UWF VARIOUS CKTS | 111583370 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 05/19/2020 | ED.01250.1105 | EL CERRITO G 1105 | 001 | ALAMEDA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 6,260.000 | 0.000 | 08J | 04/28/2016 | 2016 | # | #VALUE! | CONS | E070 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31234874_RELIAIB 2017:UWF VARIOUS CKTS | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 2053084.11
31236028 | OCGC TRACY 1102 RECONDUCTOR CABRILLO DR | 111593236 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/27/2018 | ED.16288.1102 | TRACY 1102 | 039 | SAN JOAQUIN CO | 5535457 | DO 08 - Monthly Forecast Only | 1,950.000 | 1,950.000 | 08J | 05/02/2016 | 2016 | # | #VALUE! | DOCC | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 416509.09
31236820 | WOODWARD 2107-RECONDUCTORING | 111610038 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.25529.2107 | WOODWARD 2107 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 1,456.000 | 1,457.000 | 08J | 05/05/2016 | 2016 | 08/08/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31236820_R2 WOODWARD 2107-RECONDUCTORING | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 340449.06
31237023 | *CANC* R2KINGSBURG 1116 - RECONDUTO*CANC | 4399615 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/29/2018 | ED.25224.1116 | KINGSBURG 1116 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 05/06/2016 | 2016 | 04/04/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31240114 | 2018 TARGETED OH CONDUCTOR_LLAGAS 2101 | 111643669 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2018 | ED.08318.2101 | LLAGAS 2101 | 043 | SANTA CLARA CO | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 05/17/2016 | 2016 | # | #VALUE! | UNSE | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 9510.94
31240819 | OCGC DIST WK FOR SMRTVL-NICOLAUS#2-PH#2 | 111558040 | # | Not assigned | 40 | Closed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/30/2016 | ED.15281.1105.SWIT | SWITCHES | 058 | YUBA COUNTY | 5517127 | DO 08 - Monthly Forecast Only | 12,270.000 | 12,270.000 | 08J | 05/19/2016 | 2016 | 02/29/2020 | 2020 | CLSD | E070 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Dist. Work for Smarville-Nicolaus #2 Ph2 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 111317.31
31240921 | DIST WORK FOR SMARTVILLE-NICOLAUS#2-PH#3 | 111558046 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/30/2016 | ED.15281.1104.SWIT | SWITCHES | 058 | YUBA COUNTY | 5517127 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 05/19/2016 | 2016 | # | #VALUE! | CONS | E070 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Dist. Work for Smartville-Nicolaus#2 PH3 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 763192.4
31242294 | RE-COND 467FT_4ACSRTO2ACSR_SANARDO1101 | 111665612 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/26/2018 | ED.18219.1101 | SAN ARDO 1101 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 490.000 | 490.000 | 08J | 05/26/2016 | 2016 | 02/29/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 56919.52
31243374 | HARDWICK 1101 RECOND 1720FT 6CU | 111672962 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/28/2018 | ED.25371.1101 | HARDWICK 1101 | 016 | KINGS COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 2,121.000 | 2,121.000 | 08J | 06/01/2016 | 2016 | 05/18/2019 | 2019 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31243374_HARDWICK 1101 RECOND 1720FT 6CU | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 174851.02
31245057 | R7 RECONDUCTOR STANDISH AV BELLEVUE 1102 | 111681954 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 07/28/2017 | ED.04318.1102.RECL | RECLOSERS | 049 | SONOMA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 2,796.000 | 0.000 | 08J | 06/02/2016 | 2016 | # | #VALUE! | UNSC | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 529745.53
31245707 | *CANC*DONOT USE*SNEATH LANE 1102 WI*CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/30/2018 | ED.02272.1102.TXFR.TROH | OVERHEAD TRANSFORMERS | 041 | SAN MATEO COUN | 5505513 | PN-OH ANNEALED/DETER CNDCTR: PM MGD | 0.000 | 0.000 | 08J | 06/06/2016 | 2016 | 05/03/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31245970 | *CANC*R2 HIGH SPLICE - VIEJO 2201 *CANC | 111693206 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/29/2017 | ED.18285.2201 | VIEJO 2201 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 152.000 | 0.000 | 08J | 06/07/2016 | 2016 | 12/12/2018 | 2018 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31246140 | WY1105 - RECOND 3000 FT OF 4AR W 2ARTW | 111693075 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/16/2018 | ED.17 | PARADISE DISTRICT | 004 | BUTTE COUNTY | 5535211 | CWSP SPO - SH 08 | 3,309.000 | 3,309.000 | 08W | 06/07/2016 | 2016 | 04/13/2019 | 2019 | CLSD | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | 31246140_RECOND 3000 FT - DET 4AR-WY1105 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 293661.01
31246411 | R2 HIGH SPLICE - PAUL SWEET 2102 | 111699524 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/28/2018 | ED.08325.2102 | PAUL SWEET 2102 | 044 | SANTA CRUZ COU | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 06/09/2016 | 2016 | # | #VALUE! | UNSE | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 1062.88
31246787 | RECONDUCTOR 4 SPANS - 100 DEODARA WAY | 111710769 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/31/2018 | ED.01410.1105 | ALHAMBRA 1105 | 007 | CONTRA COSTA C | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 06/10/2016 | 2016 | # | #VALUE! | UNSE | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 2500.01
31247118 | +R5_SISQUOC 1104, N/O PRELL RD, SM | 111709915 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 08/30/2019 | ED.18281.1104 | SISQUOC 1104 | 040 | SAN LUIS OBISP | 5535457 | DO 08 - Monthly Forecast Only | 2,575.000 | 2,575.000 | 08J | 06/14/2016 | 2016 | 05/30/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Sisquoc 1104 Recon 13 spans 3400 ft | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 208189.74
31247414 | RECONDUCTR OH WIRE ON CASTROVILE 2104 | 111719948 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/29/2018 | ED.18235.2104 | CASTROVILLE 2104 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 5,305.000 | 0.000 | 08J | 06/15/2016 | 2016 | 08/31/2019 | 2019 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31247414_R2 RECOND OH: CASTROVILE 2104 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 301981.42
31247517 | R7 RECOND 2400' LAKEVILLE HWY, LKVL 1101 | 111720820 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/28/2018 | ED.04337.1101.REGL | REGULATORS | 049 | SONOMA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 2,479.000 | 0.000 | 08J | 06/15/2016 | 2016 | # | #VALUE! | CONS | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 157012.9
31247900 | SM 1109, OBISPO RD, GUADALUPE | 111724673 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/16/2018 | ED.18267.1109 | SANTA MARIA 1109 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 3,910.000 | 3,910.000 | 08J | 06/16/2016 | 2016 | 10/17/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Santa Maria 1109 Repl Det Conductor | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 417467.21
31248532 | CWSP HALF MOON BAY 1101 LS CO4063 | 111724857 | # | Not assigned | 30 | Technically Completed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/04/2020 | JY | JUNK YARD FL TO HOLD DELETED DATA | 041 | SAN MATEO COUN | 5535211 | CWSP SPO - SH 08 | 4,816.000 | 4,816.000 | 08W | 06/20/2016 | 2016 | # | #VALUE! | FICL | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 1444525.15
31248533 | MOUNTAIN VIEW 1111 WD FUCO 665 | 111724858 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/26/2017 | JY | JUNK YARD FL TO HOLD DELETED DATA | DA | DE ANZA | 5505513 | PN-OH ANNEALED/DETER CNDCTR: PM MGD | 0.000 | 0.000 | 08J | 06/20/2016 | 2016 | # | #VALUE! | UNSE | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 5367.48
31248666 | OCGC MIDDLE RIVER 1103 RECONDUCTOR | 111733338 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/01/2020 | ED.16209.1103 | MIDDLE RIVER 1103 | 039 | SAN JOAQUIN CO | 5535457 | DO 08 - Monthly Forecast Only | 7,414.000 | 7,414.000 | 08J | 06/21/2016 | 2016 | # | #VALUE! | DOCC | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31248666_MIDDLE RIVER 1103 RECONDUCTOR | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 323262.15
31249134 | REPLACE DETERIORATED CONDUCT_MABURY1103 | 111742537 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2018 | ED.08219.1103 | MABURY 1103 | 043 | SANTA CLARA CO | 5535457 | DO 08 - Monthly Forecast Only | 902.000 | 0.000 | 08J | 06/24/2016 | 2016 | # | #VALUE! | PEND | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 8834.15
31251131 | PALMER 1101 WO HWY 101 NO HW 135, LOS AL | 111769505 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 08/31/2020 | ED.18303.1101 | PALMER 1101 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 8,816.000 | 8,060.000 | 08J | 07/07/2016 | 2016 | # | #VALUE! | DOCC | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Palmer 1101 Recon 4300 Hwy 135 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 350106.11
31251132 | *CANC* RECONUCTOR_11647FT_TO2CU_34SPAN_ | 111769668 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 07/07/2018 | ED.18282.1102 | MESA 1102 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 07/07/2016 | 2016 | 03/18/2017 | 2017 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31251133 | SM 1109, BLACK RD S/O W MAIN, SM | 111770148 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2019 | ED.18267.1109 | SANTA MARIA 1109 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 8,325.000 | 8,657.000 | 08J | 07/07/2016 | 2016 | 09/05/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Santa Maria 1109 Recon 805 Black Rd | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 388153.22
31255863 | *CANC* *DO NOT USE* R2WATSNVILLE 2*CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/30/2018 | ED.76-Q211000000.STRU.POLE | COAST Q2110 POLES | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 07/06/2016 | 2016 | 04/04/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31255863_WATSNVILLE 2101 CABLE REPL | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31255868 | R2ROB ROY 2104 HIGH SPLICE CABLE REPLACE | 111767989 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/30/2018 | ED.76-O171000000.STRU.POLE | COAST O1710 POLES | 044 | SANTA CRUZ COU | 5535211 | CWSP SPO - SH 08 | 1,439.000 | 1,439.000 | 08W | 07/06/2016 | 2016 | 04/13/2019 | 2019 | CLSD | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | 31255868_ROB ROY 2104 CABLE REPLACE | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 176947.94
31257470 | OCGC 707 RECOND. W RIPON RD | 111797167 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.16270.1707 | VIERRA 1707 | 039 | SAN JOAQUIN CO | 5535457 | DO 08 - Monthly Forecast Only | 5,222.000 | 5,222.000 | 08J | 07/15/2016 | 2016 | # | #VALUE! | DOCC | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31257470_VIERRA 1707 RECOND. W. RIPON RD | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 595125.36
31258120 | HARTLEY 1102 RECONDUCTOR LINE BAD SP | 111804117 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 07/19/2017 | ED.04321.1102.RECL | RECLOSERS | 017 | LAKE COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 3,500.000 | 4,000.000 | 08J | 07/19/2016 | 2016 | # | #VALUE! | DOCC | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 358885.12
31259321 | HONCUT 1102 RECON LINE EXCESS SPLICES | 111816288 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | SI | SIERRA | [8 empty] | 07/25/2017 | ED.10321.1102.SWIT | SWITCHES | 058 | YUBA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 4,458.000 | 4,458.000 | 08J | 07/25/2016 | 2016 | 02/23/2019 | 2019 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 135223.57
31259546 | 2018 AIRWAYS 1101 RECOND 2800FT TO 715AL | 111817984 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 07/31/2021 | ED.25204.1101 | AIRWAYS 1101 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 2,835.000 | 0.000 | 08J | 07/26/2016 | 2016 | # | #VALUE! | PEND | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31259546_Ariways 1101 Reconductor | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 33804.96
31259547 | 2018 SANGER 1108 RECOND 5000FT TO 2AR | 111817982 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2018 | ED.25235.1108 | SANGER 1108 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 5,563.000 | 5,563.000 | 08J | 07/26/2016 | 2016 | 07/20/2019 | 2019 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31259547_2018 SANGER 1108 RECOND | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 257116.05
31260008 | RECONDUCTR PRUNEDLE 1107- HIGH SPLICE | 111827483 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/28/2018 | ED.18296.1107 | PRUNEDALE 1107 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 7,400.000 | 7,400.000 | 08J | 07/28/2016 | 2016 | 10/24/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Reconductor Prunedale 1107 - High Splice | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 709718.09
31260163 | SM 1109 BLACK RD NO MAIN, SANTA MARIA | 111832381 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2018 | ED.18267.1109 | SANTA MARIA 1109 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 2,285.000 | 2,285.000 | 08J | 07/29/2016 | 2016 | 10/17/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31260163_SantaMaria 1109 Recon 2157ft-11 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 218657.15
31260797 | +R2Z OCEANO 1104 RECONDUCTORING BRANCH | 111523761 | # | Not assigned | 40 | Closed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2019 | ED.18260.1104 | OCEANO 1104 | 040 | SAN LUIS OBISP | 5535457 | DO 08 - Monthly Forecast Only | 9,463.000 | 9,363.000 | 08J | 08/02/2016 | 2016 | 10/17/2020 | 2020 | CLSD | E070 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31260797_R5 OCEANO 1104 RECONDUCTORING B | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 1173286.14
31260997 | REPL 3 SECNS OF 2AR W 2AR WYANDOTTE | 111842619 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 08/21/2018 | ED.10375.1101.RECL | RECLOSERS | 004 | BUTTE COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 6,757.000 | 7,165.000 | 08J | 08/03/2016 | 2016 | 02/23/2019 | 2019 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31260997_REPL 3 SECNS WYANDOTTE 1105 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 339172.04
31261149 | STS-COND_BROK_REPL - R/O 48 GREENWOOD DR | 112515378 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/31/2017 | ED.56-E041600000.STRU.POLE | SKYLINE E0416 POLES | 041 | SAN MATEO COUN | 5505513 | PN-OH ANNEALED/DETER CNDCTR: PM MGD | 1,600.000 | 1,297.000 | 08J | 08/03/2016 | 2016 | 08/18/2018 | 2018 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31261149_REPL: R/O 48 GREENWOOD DR | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 178181.18
31262055 | SIS 1104 DOMINION RD, SANTA MARIA | 111870803 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2018 | ED.18281.1104 | SISQUOC 1104 | 040 | SAN LUIS OBISP | 5535457 | DO 08 - Monthly Forecast Only | 2,172.000 | 2,255.000 | 08J | 08/12/2016 | 2016 | 10/17/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31262055_Sisquoc 1104 Recon 8 - 2172 ft | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 297229.79
31262225 | *CANC*DONOT USE*DAVIS 1106 RECOND L*CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 08/04/2017 | ED.06204.1106.SWIT | SWITCHES | 057 | YOLO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 08/09/2016 | 2016 | 05/03/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31262300 | EP KNIGHTS LANDING 1102 RECON WIRE DOWN | 111858050 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2017 | ED.50-G200000000.STRU.POLE | YOLO G20 POLES | 051 | SUTTER COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 2,015.000 | 0.000 | 08J | 08/10/2016 | 2016 | # | #VALUE! | UNSC | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 39765.16
31262866 | HBPP 1101 LR 898396 EXCESSIVE SPLICES | 111868017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/26/2018 | JY | JUNK YARD FL TO HOLD DELETED DATA | 012 | HUMBOLDT COUNT | 5535457 | DO 08 - Monthly Forecast Only | 4,906.000 | 4,906.000 | 08J | 08/12/2016 | 2016 | # | #VALUE! | DOCC | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31262866_HBPP 1101 LR Excessive Splices | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 645470.52
31262921 | *CANC*- RECOND SANTA RITA 1102 - WD | 111868016 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/14/2018 | ED.25354.1102 | SANTA RITA 1102 | 024 | MERCED COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 2,900.000 | 0.000 | 08J | 08/12/2016 | 2016 | 06/29/2019 | 2019 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31264776 | PEASE 1101 RECOND LINE BAD SPLICE PM TBD | 111899995 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/24/2017 | ED.15375.1101.SWIT | SWITCHES | 051 | SUTTER COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 1,066.000 | 0.000 | 08J | 08/24/2016 | 2016 | # | #VALUE! | UNSC | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 3603.86
31264915 | R7 RECONDUCTOR WILSON RD- RINCON 1103 | 111897432 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/29/2017 | ED.04332.1103.CAPA | CAPACITORS | 049 | SONOMA COUNTY | 5535211 | CWSP SPO - SH 08 | 957.000 | 957.000 | 08W | 08/23/2016 | 2016 | 04/13/2019 | 2019 | CLSD | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 75634.1
31265331 | RAINBOW 1106 RECOND 6600FT 6CU | 111902703 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/01/2020 | ED.25444.1106 | RAINBOW 1106 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 6,600.000 | 6,600.000 | 08J | 08/25/2016 | 2016 | # | #VALUE! | DOCC | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 886912.33
31269259 | ZACA 1101 FOXEN CYN RD, LOS OLIVOS | 111934659 | # | Not assigned | 30 | Technically Completed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2018 | ED.18268.1101 | ZACA 1101 | 042 | SANTA BARBARA | 5535211 | CWSP SPO - SH 08 | 6,389.000 | 6,389.000 | 08W | 09/07/2016 | 2016 | # | #VALUE! | FICL | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Zaca 1101 Recon 1.2 miles | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 600327.32
31269333 | KERMAN 1103 RECOND 2160 FT 6CU | 111921758 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2018 | ED.25271.1103 | KERMAN 1103 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 2,133.000 | 2,133.000 | 08J | 09/06/2016 | 2016 | 12/01/2018 | 2018 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 135946.61
31271222 | *CANC*DONOT USE*SM 1109, N/O 1586 W*CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.18267.1109 | SANTA MARIA 1109 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 09/14/2016 | 2016 | 05/03/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31271222_Santa Maria 1109 Recond | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31271230 | G-1114 RECONDUCTOR 2 SPANS | 111964777 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 07/10/2017 | ED.28-D042100000.STRU.POLE | BAY D0421 POLES | 007 | CONTRA COSTA C | 5535457 | DO 08 - Monthly Forecast Only | 480.000 | 328.000 | 08J | 09/16/2016 | 2016 | 12/28/2019 | 2019 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 95132.56
31271378 | WILKINS SLOUGH 1102 RECONLINE EX SPL | 111942689 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/09/2017 | ED.06277.1102.SWIT | SWITCHES | 051 | SUTTER COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 5,164.000 | 5,164.000 | 08J | 09/15/2016 | 2016 | 02/23/2019 | 2019 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 167482
31272374 | CWSP PT. MORETTI FROM 5043 TO 5955 | 111973964 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/06/2020 | ED.08293.1101 | POINT MORETTI 1101 | 044 | SANTA CRUZ COU | 5535211 | CWSP SPO - SH 08 | 8,500.000 | 0.000 | 08W | 09/20/2016 | 2016 | # | #VALUE! | PEND | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | 31272374_RECOND PT MORETTI: 5043 TO 5955 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 2282675.06
31272375 | CWSP PT. MORETTI BEYOND 5995 | 111973967 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/01/2022 | ED.08293.1101 | POINT MORETTI 1101 | 044 | SANTA CRUZ COU | 5535211 | CWSP SPO - SH 08 | 8,640.000 | 0.000 | 08W | 09/20/2016 | 2016 | # | #VALUE! | PEND | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | 31272375_RECOND PT MORETTI BEYOND 5995 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 79852.39
31273284 | *CANC*DO NOT USE*D-1105 RECOND 3,26*CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/23/2017 | ED.01204.1105.SWIT | SWITCHES | 001 | ALAMEDA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 09/26/2016 | 2016 | 05/03/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31273808 | RECONDUCT WD DOLAN 1104 - 16-0058680 | 111990681 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/28/2018 | ED.18238.1104 | DOLAN ROAD 1104 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 2,727.000 | 2,727.000 | 08J | 09/27/2016 | 2016 | 02/29/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31273808_R2 RECONDUCT WD DOLAN 1104 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 205282.15
31274093 | *CANC*R2Z KETTLEMANHILLS 1101 RECO2741F | 113311706 | # | Not assigned | 25 | Canceled | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.25273.1101 | KETTLEMAN HILLS 1101 | 016 | KINGS COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 2,714.000 | 0.000 | 08J | 09/29/2016 | 2016 | # | #VALUE! | CNCL | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31274093_KETTLEMAN HILLS 1101 RECON | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | -1290.6
31274717 | CABRILLO 1104, SAN PASQUAL CYN RD, LOMPO | 112010896 | # | Not assigned | 30 | Technically Completed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2018 | ED.18310.1104 | CABRILLO 1104 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 8,806.000 | 0.000 | 08J | 10/04/2016 | 2016 | # | #VALUE! | FICL | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Cabrillo 1104 Recon 1.75 miles | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 547002.95
31275384 | OCGC DUCTOR MAYS CANYON-MIRABEL 1101 | 112013623 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/29/2017 | ED.04209.1101.SWIT | SWITCHES | 049 | SONOMA COUNTY | 5535211 | CWSP SPO - SH 08 | 1,986.000 | 1,986.000 | 08W | 10/05/2016 | 2016 | 11/21/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 167103.76
31275658 | R7 DUNBAR 1102 RECOND OH BEYOND CO 1285 | 112015123 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/29/2017 | JY | JUNK YARD FL TO HOLD DELETED DATA | 049 | SONOMA COUNTY | 5535211 | CWSP SPO - SH 08 | 2,580.000 | 2,580.000 | 08W | 10/07/2016 | 2016 | # | #VALUE! | DOCC | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 647589.94
31275749 | CHOWCHILLA 1104-RECOND 1,290' OF 4A | 112024014 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2018 | ED.25410.1104 | CHOWCHILLA 1104 | 020 | MADERA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 1,560.000 | 1,560.000 | 08J | 10/07/2016 | 2016 | 08/28/2018 | 2018 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31275749_CHOWCHILLA 1104 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 103467.77
31275750 | CHOWCHILLA 1104-RECOND 2,200' OF #6CU | 112024150 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/30/2019 | ED.25410.1104 | CHOWCHILLA 1104 | 020 | MADERA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 2,178.000 | 2,186.000 | 08J | 10/07/2016 | 2016 | 07/18/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31275750_CHOWCHILLA 1104-RECOND | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 228827.37
31276193 | 46 OCLH STS R/O 1380 RUSSELMAN RD CLAYTO | 112033188 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/30/2018 | ED.66-2722600000.STRU.POLE | KERN 27226 POLES | 015 | KERN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 2,513.000 | 2,513.000 | 08J | 10/11/2016 | 2016 | 10/17/2018 | 2018 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31276193_GOOSE LAKE 1103 - RECOND 2,388' | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 154083.62
31276194 | R5 RIO BRAVO 1101 - RECONDUCTOR 1,650' | 112033189 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 05/01/2020 | ED.66-28254C0000.STRU.POLE | KERN 28254C POLES | 015 | KERN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 1,576.000 | 0.000 | 08J | 10/11/2016 | 2016 | # | #VALUE! | CONS | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 46735.03
31276229 | 2018 OH COND RPLC: ARCATA 1121 | 112033187 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/10/2018 | ED.36-N101200000.STRU.POLE | EUREKA N1012 POLES | 012 | HUMBOLDT COUNT | 5535457 | DO 08 - Monthly Forecast Only | 5,000.000 | 0.000 | 08J | 10/11/2016 | 2016 | # | #VALUE! | PEND | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31276229_2018 OH Cond Rplc Arcata 1121 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 57452.46
31276346 | 2018 OH COND RPLC: BIG LAGOON 1101 | 112034600 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/29/2018 | ED.19236.1101.SWIT | SWITCHES | 012 | HUMBOLDT COUNT | 5535457 | DO 08 - Monthly Forecast Only | 3,779.000 | 0.000 | 08J | 10/11/2016 | 2016 | # | #VALUE! | UNSC | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Big Lagoon 1101 Excessive Splices | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 70906.3
31276349 | 2018 OH COND RPLC: EEL RIVER 1103 | 112034941 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/29/2018 | ED.19238.1103.SWIT | SWITCHES | 012 | HUMBOLDT COUNT | 5535457 | DO 08 - Monthly Forecast Only | 679.000 | 0.000 | 08J | 10/11/2016 | 2016 | # | #VALUE! | UNSC | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 2232.56
31277398 | RECONDUCTOR LIVINGSTON 1106 - WD | 112043442 | # | Not assigned | 30 | Technically Completed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/21/2019 | ED.25226.1106 | LIVINGSTON 1106 | 024 | MERCED COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 2,299.000 | 2,299.000 | 08J | 10/13/2016 | 2016 | # | #VALUE! | FICL | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31277398_RECOND LIVINGSTON 1106 - WD | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 152457.36
31277399 | RECONDUCTOR CRESSEY 2103 - IR PATROL | 112043492 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/02/2018 | ED.25470.2103 | CRESSEY 2103 | 024 | MERCED COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 2,847.000 | 2,847.000 | 08J | 10/13/2016 | 2016 | 10/27/2018 | 2018 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | RECONDUCTOR CRESSEY 2103 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 306782.17
31278065 | RECONDUCTOR MERCED 2101-STRETCH RD | 112045722 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/14/2018 | ED.25280.2101 | MERCED 2101 | 024 | MERCED COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 753.000 | 0.000 | 08J | 10/17/2016 | 2016 | # | #VALUE! | ADER | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 5783.6
31278200 | +OCEANO 1102 S HALCYON & PINE RDGE | 112052729 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/31/2019 | ED.18260.1108 | OCEANO 1108 | 040 | SAN LUIS OBISP | 5535211 | CWSP SPO - SH 08 | 2,081.000 | 2,081.000 | 08W | 10/17/2016 | 2016 | 07/04/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | 31278200_Oceano 1108 Recon 11 - 2200 ft | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 453122.72
31279013 | MALAGA 1102 RECOND 1350FT 6CU | 112060901 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 01/31/2020 | ED.25425.1102 | MALAGA 1102 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 1,217.000 | 1,217.000 | 08J | 10/20/2016 | 2016 | 04/04/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 45344.55
31280506 | R2 RECONDUCT PT. MORETTI BEYOND 8981 | 112115009 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/28/2018 | ED.08293.1101 | POINT MORETTI 1101 | 044 | SANTA CRUZ COU | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 10/26/2016 | 2016 | # | #VALUE! | UNSE | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | 31280506_RECOND PT. MORETTI BEYOND 8981 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 22941.03
31280730 | *CANC* R2 RECONDUCT DOLAN RD *CANC | 112119901 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/29/2018 | ED.18238.1101 | DOLAN ROAD 1101 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 2,800.000 | 0.000 | 08J | 10/27/2016 | 2016 | 12/12/2018 | 2018 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31280946 | R2 RECONDUCT BORONDA 1101 WD#16-0070412 | 112121695 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/29/2018 | ED.18246.1101 | BORONDA 1101 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 10/27/2016 | 2016 | # | #VALUE! | UNSE | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 813.31
31281523 | R2 RECONDUCT RESERVATION ROAD 1102 | 112128892 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/29/2018 | ED.18273.1102 | RESERVATION ROAD 1102 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 10/31/2016 | 2016 | # | #VALUE! | UNSE | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31281523_RECOND RESERVATION ROAD 1102 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 5201.84
31281871 | *CANC* R2 RECONDUCT DOLAN ROAD *CANC | 112134625 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/31/2018 | ED.18238.1104 | DOLAN ROAD 1104 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 11/02/2016 | 2016 | 12/05/2018 | 2018 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31281871_RECOND DOLAN ROAD 1104 #16 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31281966 | *CANC*DONOT USE* SUISUN 1109 RECOND*CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/01/2017 | ED.06213.1107.SWIT | SWITCHES | 048 | SOLANO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 11/02/2016 | 2016 | 05/03/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31281968 | *CANC*DONOT USE* DIXON 1103 RECOND *CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/01/2017 | ED.06206.1103.SWIT | SWITCHES | 048 | SOLANO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 11/02/2016 | 2016 | 05/03/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31281969 | RICE 1101 RECOND LINE EXCESSIVE SPLICES | 112134526 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/01/2017 | ED.06283.1101.SWIT | SWITCHES | 006 | COLUSA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 11/02/2016 | 2016 | # | #VALUE! | UNSE | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31282765 | *CNCL* 2018 OH COND RPLC: EUREKA E 1104 | # | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/10/2018 | ED.19233.1104.SWIT | SWITCHES | 012 | HUMBOLDT COUNT | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 11/07/2016 | 2016 | # | #VALUE! | UNSE | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 975.84
31282826 | *CANC*DONOT USE*RECONDUCTOR PAST FU*CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/09/2018 | ED.18281.1104 | SISQUOC 1104 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 11/09/2016 | 2016 | 05/03/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31282830 | *CANC*DONOT USE*R2 SISQUOC 1104_FUS*CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/09/2018 | ED.18281.1104 | SISQUOC 1104 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 10,649.000 | 0.000 | 08J | 11/09/2016 | 2016 | 05/03/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31282831 | RECONDUCTOR PALMER1101_ LS FCO 1537 | 112149839 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/09/2018 | ED.18303.1101 | PALMER 1101 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 11/09/2016 | 2016 | # | #VALUE! | UNSE | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 1554.68
31282951 | RECONDUCTOR SIX SPANS-GRAND ISLAND 2224 | 112135793 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/29/2017 | JY | JUNK YARD FL TO HOLD DELETED DATA | 039 | SAN JOAQUIN CO | 5535457 | DO 08 - Monthly Forecast Only | 1,454.000 | 0.000 | 08J | 11/08/2016 | 2016 | # | #VALUE! | UNSC | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 58150.49
31284005 | RECONDUCT PIERCY 2109 | 112164356 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/29/2018 | ED.08391.2109 | PIERCY 2109 | 043 | SANTA CLARA CO | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 11/15/2016 | 2016 | # | #VALUE! | UNSE | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31284005_RECONDUCT PIERCY 2109 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 1309.26
31284643 | Logan Creek 2101_install 12 sets of COs | 112170125 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2019 | ED.10314.2101.SWIT | SWITCHES | 011 | GLENN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 11/18/2016 | 2016 | # | #VALUE! | UNSE | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 562.41
31285060 | *CANC*DONOT USE* SPINGS 1103 - STRO*CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/29/2017 | ED.21-J371800000 | EL DORADO MAP J3718 | 009 | EL DORADO COUN | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 11/20/2016 | 2016 | 05/03/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31285061 | *CANC*DONOT USE*E NICOLAUS 1102 SAC*CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/29/2017 | ED.11-U220000000 | MARYSVILLE MAP U22 | 051 | SUTTER COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 11/20/2016 | 2016 | 05/03/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31285159 | *CANC*DONOT USE* RECONDUCTOR DEEPWA*CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/17/2018 | ED.06362.1107.RECL | RECLOSERS | 057 | YOLO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 8,648.000 | 0.000 | 08J | 11/21/2016 | 2016 | 05/03/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31286361 | *CNCL* FRUITLAND 42 C/O 7449 | # | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/10/2018 | ED.19231.1142.SWIT | SWITCHES | 012 | HUMBOLDT COUNT | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 11/30/2016 | 2016 | # | #VALUE! | UNSE | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 12258.47
31286365 | CONVERTED TO 35XX SERIES PM - CANCEL PM | 4682552 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/10/2018 | ED.19217.1103.SWIT | SWITCHES | 012 | HUMBOLDT COUNT | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 11/30/2016 | 2016 | # | #VALUE! | UNSE | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 664
31286571 | *R4 EL DORADO PH 2102 HIGH SPLICE AREA | 112196254 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2018 | ED.21-H461000000 | EL DORADO MAP H4610 | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 1,928.000 | 1,928.000 | 08W | 12/01/2016 | 2016 | 07/20/2019 | 2019 | CLSD | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | 31286571_EL DORADO PH 2102 HIGH SPLICE | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 174335.72
31286573 | APPLE HILL 2102 HIGH SPLICE AREA | 112196297 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/30/2018 | ED.21-K432500000 | EL DORADO MAP K4325 | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 3,492.000 | 3,492.000 | 08W | 12/01/2016 | 2016 | 05/09/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 543235.65
31286660 | *CANC*DO NOT USE* 6295 20 SPAN4ACSR*CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/22/2018 | ED.18310.1104 | CABRILLO 1104 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 12/01/2016 | 2016 | 05/03/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31286706 | *CNCL* FRUITLAND 42 C/O 1679 | # | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/29/2018 | ED.19231.1142.SWIT | SWITCHES | 012 | HUMBOLDT COUNT | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 12/01/2016 | 2016 | # | #VALUE! | UNSE | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 371.53
31287794 | LIVE OAK 1104 - ROBINSON RD RECONDUCTOR | 112386399 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/30/2018 | ED.11-L210700000 | MARYSVILLE MAP L2107 | 051 | SUTTER COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 12/07/2016 | 2016 | # | #VALUE! | UNSE | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 3696.87
31288039 | HOOPA 1101 RCOND WITH TREE WIRE | 112390862 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/10/2018 | ED.19240.1101 | HOOPA 1101 | 012 | HUMBOLDT COUNT | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 12/08/2016 | 2016 | # | #VALUE! | UNSE | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 795.32
31289107 | CONVERTED TO 35XX SERIES PM - CANCEL PM | 4699117 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/10/2018 | ED.19238.1102 | EEL RIVER 1102 | 012 | HUMBOLDT COUNT | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 12/12/2016 | 2016 | # | #VALUE! | UNSE | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 646.54
31289238 | FRUITLAND 1142 INS TREE WIRE LR 6064 | 112403535 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/10/2018 | ED.19231.1142.SWIT | SWITCHES | 012 | HUMBOLDT COUNT | 5535211 | CWSP SPO - SH 08 | 6,266.000 | 6,271.000 | 08W | 12/13/2016 | 2016 | # | #VALUE! | DOCC | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | 31289238_Fruitland 1142 Ins Tree Wire | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 2332097.61
31289354 | *Cncl* BIG RIVER 1101 FUSE 5187 RECON | # | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/10/2018 | ED.04308.1101.SWIT | SWITCHES | 023 | MENDOCINO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 12/14/2016 | 2016 | # | #VALUE! | UNSE | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | -986.2
31289564 | *CANC*DONOT USE*RECONDTAP SPERRY & *CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/28/2018 | ED.04257.1103.SWIT | SWITCHES | 049 | SONOMA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 12/14/2016 | 2016 | 05/03/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31289812 | RECOND TAP W TW - LCO 5265 GUALALA 1112 | 112409713 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/28/2018 | ED.04284.1112.REGL | REGULATORS | 023 | MENDOCINO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 12/15/2016 | 2016 | # | #VALUE! | UNSE | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
31290144 | *CANC*DO NOT USE* SAN RAFAEL 1105 R*CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/30/2017 | ED.40-TT33030000.STRU.POLE | NORTH BAY MAP TT3303 POLES | 021 | MARIN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 1,250.000 | 0.000 | 08J | 12/19/2016 | 2016 | 05/03/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31290145 | R7 SAN RAFAEL 1107 COND REPLACEMENT | 112416551 | # | Not assigned | 30 | Technically Completed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/30/2017 | ED.40-TT31200000.STRU.POLE | NORTH BAY MAP TT3120 POLES | 021 | MARIN COUNTY | 5535211 | CWSP SPO - SH 08 | 801.000 | 801.000 | 08W | 12/19/2016 | 2016 | # | #VALUE! | FICL | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 402000.99
31290146 | *CANC*DONOT USE* PUEBLO 2102 RECOND*CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/30/2017 | ED.40-TT31150000.STRU.POLE | NORTH BAY MAP TT3115 POLES | 021 | MARIN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 600.000 | 0.000 | 08J | 12/19/2016 | 2016 | 05/03/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31290147 | R7 OLEMA 1101 REPLACE COND VISION RD | 112416601 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/30/2017 | ED.40-QQ24020000.STRU.POLE | NORTH BAY MAP QQ2402 POLES | 021 | MARIN COUNTY | 5535211 | CWSP SPO - SH 08 | 3,174.000 | 3,174.000 | 08W | 12/19/2016 | 2016 | # | #VALUE! | DOCC | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | 31290147_Olema Reconductor | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 791229.79
31290228 | UPGRADE 230' OF 3-1/0 AL_WYANDOTTE 1109 | 112416737 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2019 | ED.10291.1109.SWIT | SWITCHES | 004 | BUTTE COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 12/19/2016 | 2016 | # | #VALUE! | UNSE | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 872.82
31290853 | KNIGHTS LANDING 1102 RECOND LINE EX SPL | 112407585 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/17/2018 | ED.06272.1102.SWIT | SWITCHES | 051 | SUTTER COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 12/20/2016 | 2016 | # | #VALUE! | UNSE | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31291638 | CAB 1104 CENTRAL EO FLORADALE, LOMPOC | 112443046 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/30/2020 | ED.18310.1104 | CABRILLO 1104 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 3,485.000 | 3,718.000 | 08J | 12/29/2016 | 2016 | 10/17/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Cabrillo WD 16-0080322 Reconduct OH Line | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 202174.43
31291639 | FH 1101 O'CONNOR WY RECOND 12 SPANS, SLO | 112443196 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/25/2022 | ED.18295.1101 | FOOTHILL 1101 | 040 | SAN LUIS OBISP | 5535211 | CWSP SPO - SH 08 | 3,100.000 | 0.000 | 08W | 12/29/2016 | 2016 | # | #VALUE! | ESTS | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 105347.41
31291669 | *CANC*DO NOT USE* RECOND 10 SPAN 2*CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/27/2017 | ED.18281.1103 | SISQUOC 1103 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 12/28/2016 | 2016 | 05/03/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31291670 | *CANC*DONOT USE*RECONDUCTOR_15 SPAN*CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/27/2017 | ED.18281.1102 | SISQUOC 1102 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 12/28/2016 | 2016 | 05/03/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31291671 | *CANC*DONOT USE*RECOND 3400FT OF 4A*CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 07/28/2017 | ED.18205.2102 | SOLEDAD 2102 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 12/28/2016 | 2016 | 05/03/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31292064 | LOS ALTOS 1104 REPL 3 SPN OH LINE | 112437674 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/22/2017 | ED.08224.1104.TXFR.TROH | OVERHEAD TRANSFORMERS | 043 | SANTA CLARA CO | 5517127 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 12/29/2016 | 2016 | # | #VALUE! | UNSE | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 872.82
31296803 | PN EG-1101 WIREDOWN 08J PROJECT | 4740503 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/29/2018 | ED.02257.1101.TXFR.TROH | OVERHEAD TRANSFORMERS | 041 | SAN MATEO COUN | 5505513 | PN-OH ANNEALED/DETER CNDCTR: PM MGD | 0.000 | 0.000 | 08J | 01/17/2017 | 2017 | # | #VALUE! | UNSE | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 1726.13
31296941 | PENRYN 1105 - COLWELL TO SWETZER RD 08J | 112477581 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/30/2018 | ED.20-V061200000 | PLACER MAP V0612 | 031 | PLACER COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 660.000 | 0.000 | 08J | 01/18/2017 | 2017 | # | #VALUE! | UNSE | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 2388.95
31297217 | 2019 PN RW-406 08J WIREDOWN 16-0081064 | 112516189 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/28/2018 | ED.02416.0406.TXFR.TROH | OVERHEAD TRANSFORMERS | 041 | SAN MATEO COUN | 5505513 | PN-OH ANNEALED/DETER CNDCTR: PM MGD | 0.000 | 0.000 | 08J | 01/19/2017 | 2017 | # | #VALUE! | UNSE | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 538.99
31297273 | RECOND HWY1 (BY SW 92493)- GUALALA 1111 | 112523454 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/28/2018 | JY | JUNK YARD FL TO HOLD DELETED DATA | 023 | MENDOCINO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 01/19/2017 | 2017 | # | #VALUE! | UNSE | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 1263.81
31297323 | REP 2000' OH COND, INST COS- BUTTE1107 | 112520588 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2018 | ED.11-N211600000 | MARYSVILLE MAP N2116 | 004 | BUTTE COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 01/19/2017 | 2017 | # | #VALUE! | UNSE | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 1341.22
31297367 | WHEATLAND 1104 - GALLAGHER ROAD 08J | 112520804 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/30/2018 | ED.11-S260000000 | MARYSVILLE MAP S26 | 051 | SUTTER COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 4,498.000 | 0.000 | 08J | 01/19/2017 | 2017 | # | #VALUE! | UNSE | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 3185.32
31297666 | *CANC*DONOT USE* R2 RECOND19 SPANS *CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/06/2017 | ED.18257.1103 | DIVIDE 1103 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 5,451.000 | 0.000 | 08J | 01/24/2017 | 2017 | 05/03/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31304618 | REPL 1200' OF DET 3-4CU CHICO B 1101 | 112558367 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2018 | ED.10249.1101.SWIT | SWITCHES | 004 | BUTTE COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 02/08/2017 | 2017 | # | #VALUE! | UNSE | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 1005.91
31307406 | **DONT USE***GRAND ISLAND 2224 RECON | # | # | Not assigned | 30 | Technically Completed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 08/20/2019 | ED.06246.2224.RECL | RECLOSERS | 048 | SOLANO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 02/23/2017 | 2017 | # | #VALUE! | FICL | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31307406_Grand Island 2224 Recon Station | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 322171.24
31308015 | *CANC* SLO 1107 RECOND 3836 FT 10S *CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2019 | ED.18263.1107 | SAN LUIS OBISPO 1107 | 040 | SAN LUIS OBISP | 5535211 | CWSP SPO - SH 08 | 3,836.000 | 0.000 | 08W | 03/01/2017 | 2017 | 09/05/2019 | 2019 | CLSD | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
31308019 | *CANC*DONOT USE* RECO31SPAN4425FT4A*CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/03/2019 | ED.18267.1105 | SANTA MARIA 1105 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 4,160.000 | 0.000 | 08J | 03/03/2017 | 2017 | 05/03/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31308789 | RECONDUCTOR WESTLEY 1101-HAMILTON RD | 112403818 | # | Not assigned | 30 | Technically Completed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/21/2018 | ED.16267.1101 | WESTLEY 1101 | 050 | STANISLAUS COU | 5535457 | DO 08 - Monthly Forecast Only | 13,264.000 | 13,200.000 | 08J | 03/02/2017 | 2017 | # | #VALUE! | FICL | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31308789_RECON WESTLEY 1101-HAMILTON RD | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 677146.46
31308790 | *CANC*DONOT USE*CANAL 1103 RECONDUC*CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.25209.1103 | CANAL 1103 | 024 | MERCED COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 7,300.000 | 0.000 | 08J | 03/02/2017 | 2017 | 05/03/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31308791 | *CANC*DO NOT USE* 2018 WAHTOKE RECO*CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/30/2021 | ED.25453.1110 | WAHTOKE 1110 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 03/02/2017 | 2017 | 05/03/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31308791_Wahtoke 1110 Reconductor | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31308792 | CORCORAN 1118 RECONDUCTOR | 112410211 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2019 | ED.25217.1118 | CORCORAN 1118 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 03/02/2017 | 2017 | # | #VALUE! | UNSE | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Corcoran 1118 Reconductor | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 3559.34
31308793 | *CANC*DO NOT USE*2019 BOWLES RECON*CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2019 | ED.25353.1104 | BOWLES 1104 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 03/02/2017 | 2017 | 05/03/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Bowles 1104 Reconductor | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31311246 | *CANC* DINUBA 1104 RECOND 1,222' O*CANC | 4797336 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/01/2018 | ED.25234.1101 | REEDLEY 1101 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 1,222.000 | 0.000 | 08J | 03/08/2017 | 2017 | 06/05/2019 | 2019 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31312018 | *CANC*DONOT USE* RECONDCT CASTROVLE*CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/29/2018 | ED.18235.2104 | CASTROVILLE 2104 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 2,600.000 | 0.000 | 08J | 03/13/2017 | 2017 | 05/03/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31312019 | *CANC*DONOT USE*RECONDUCT SALINAS 1*CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/30/2018 | ED.18201.1106 | SALINAS 1106 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 1,000.000 | 0.000 | 08J | 03/13/2017 | 2017 | 05/03/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31312040 | *CANC*DONOT USE*R2 RECONDUCT DOLAN *CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/30/2018 | ED.18238.1101 | DOLAN ROAD 1101 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 715.000 | 0.000 | 08J | 03/13/2017 | 2017 | 05/03/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31313568 | R2 REPLACE OH WIRE P1107 #17-0021747 | 112690399 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/30/2018 | ED.18296.1107 | PRUNEDALE 1107 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 440.000 | 0.000 | 08J | 03/21/2017 | 2017 | # | #VALUE! | UNSE | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 395.13
31314094 | *CANC* RECON 10 SPANS _3400FT 4ACSR W | 112172026 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 05/01/2018 | ED.18205.2102 | SOLEDAD 2102 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 03/22/2017 | 2017 | 04/08/2017 | 2017 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31314138 | *CANC*DONOT USE* NEW HOPE 1101 2,20*CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/01/2018 | ED.16208.1101 | NEW HOPE 1101 | 039 | SAN JOAQUIN CO | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 03/22/2017 | 2017 | 05/03/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31314313 | *CANC* *DO NOT USE* RECONDUCTOR ST*CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/20/2019 | ED.25461.1105 | STOREY 1105 | 020 | MADERA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 03/23/2017 | 2017 | 06/05/2019 | 2019 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31314313_Reconductor Storey 1105 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31314952 | *CANC*R2 RECONDCT CASTROVLE 2103 WD#17-0 | 112709872 | # | Not assigned | 30 | Technically Completed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/30/2018 | ED.18235.2103 | CASTROVILLE 2103 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 720.000 | 0.000 | 08J | 03/27/2017 | 2017 | # | #VALUE! | PROD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | -49.03
31316185 | *CANC*DONOT USE* WHISTMAN1106 CO582*CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/20/2019 | ED.08363.1106.TXFR.TROH | OVERHEAD TRANSFORMERS | 043 | SANTA CLARA CO | 5517127 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 04/01/2017 | 2017 | 05/03/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31316186 | *CANC* HMB1102 CO12457 #17-00290*CANC | 112726529 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/24/2019 | ED.02410.1102.TXFR.TROH | OVERHEAD TRANSFORMERS | 041 | SAN MATEO COUN | 5535211 | CWSP SPO - SH 08 | 4,000.000 | 0.000 | 08W | 04/01/2017 | 2017 | 12/12/2018 | 2018 | CLSD | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
31316283 | *CANC* RECONDUCTOR CANAL 1104 WD *CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/07/2021 | ED.25209.1104 | CANAL 1104 | 024 | MERCED COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 1,440.000 | 0.000 | 08J | 04/03/2017 | 2017 | 05/03/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31316283_RECONDUCTOR CANAL 1104 WD | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31317925 | WAHTOKE 1107 RECOND 1000FT 6CU | 112738246 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/28/2018 | ED.25453.1107 | WAHTOKE 1107 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 1,000.000 | 0.000 | 08J | 04/06/2017 | 2017 | # | #VALUE! | UNSE | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31318381 | *CANC*DO NOT USE*LINDEN 1102 RECOND*CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/30/2018 | ED.16207.1102 | LINDEN 1102 | 039 | SAN JOAQUIN CO | 5535457 | DO 08 - Monthly Forecast Only | 760.000 | 0.000 | 08J | 04/07/2017 | 2017 | 05/03/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31318944 | *CANC*DONOT USE*COND21SPANS, ALMOST*CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/06/2018 | ED.18260.1106 | OCEANO 1106 | 040 | SAN LUIS OBISP | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 04/11/2017 | 2017 | 05/03/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31319329 | SAN LUIS OBISP1103 - RECOND WITH 2CU TW | 112762682 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/12/2019 | ED.18263.1103 | SAN LUIS OBISPO 1103 | 040 | SAN LUIS OBISP | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 04/13/2017 | 2017 | # | #VALUE! | UNSE | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 610.78
31319443 | *CANC*DONOT USE* RECOND 7-SPANS ELY*CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/28/2018 | ED.04349.1103.RECL | RECLOSERS | 049 | SONOMA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 04/13/2017 | 2017 | 05/03/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31319444 | RECON 5-SPANS PORTER CRK RD-RINCON 1103 | 112761026 | # | Not assigned | 30 | Technically Completed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/28/2018 | JY | JUNK YARD FL TO HOLD DELETED DATA | 049 | SONOMA COUNTY | 5535211 | CWSP SPO - SH 08 | 1,284.000 | 1,279.000 | 08W | 04/13/2017 | 2017 | # | #VALUE! | FICL | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 3149413.62
31319901 | *CANC*DONOT USE*RECOND_5656FT 3-6CU*CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 02/14/2019 | ED.18282.1102 | MESA 1102 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 04/17/2017 | 2017 | 05/03/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31320148 | *CANC*NAPA 1103 OH RECONDUCTORING P*CANC | 112774649 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2017 | ED.04202.1103.SWIT | SWITCHES | 028 | NAPA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 04/18/2017 | 2017 | 10/03/2019 | 2019 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31320621 | *CANC*DONOT USE* RECOND HWY 20-FTBR*CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/28/2018 | ED.04276.1102.CAPA | CAPACITORS | 023 | MENDOCINO COUN | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 04/19/2017 | 2017 | 05/03/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31321841 | *CANC* RECONDUCTORING 17-003671*CANC | 112804988 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/26/2019 | ED.18310.1104 | CABRILLO 1104 | 040 | SAN LUIS OBISP | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 04/26/2017 | 2017 | 11/03/2018 | 2018 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31323235 | *CANC*CABRILLIO 1103 6700FT RECON ADD 3F | 112818395 | # | Not assigned | 40 | Closed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 04/28/2019 | ED.18310.1103 | CABRILLO 1103 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 05/02/2017 | 2017 | 03/02/2019 | 2019 | CLSD | E070 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31323676 | RECOND 1327FT OF 4ACSR W 2CU | # | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 05/04/2019 | ED.18267.1106 | SANTA MARIA 1106 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 05/04/2017 | 2017 | # | #VALUE! | UNSE | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 913.67
31324095 | *CANC*DONOT USE* 2RPLC OH WIRE ON G*CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/30/2019 | ED.18233.1101 | GABILAN 1101 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 5,675.000 | 0.000 | 08J | 05/05/2017 | 2017 | 05/03/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Gabilan 1101 OH Reconductor Project | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31324412 | *CANC*DONOT USE* RECONDUCTOR ATWATE*CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/13/2019 | ED.25361.1106 | ATWATER 1106 | 024 | MERCED COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 05/08/2017 | 2017 | 05/03/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31324677 | *CANC* *DO NOT USE* TERMINOUS 110*CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/01/2019 | ED.16302.1102 | TERMINOUS 1102 | 039 | SAN JOAQUIN CO | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 05/09/2017 | 2017 | 11/03/2019 | 2019 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Terminous 1102 Reconductor | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31325844 | *CANC*DONOT USE* SF A-1115 WIRE DOW*CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 08/25/2017 | ED.02203.1115.SWIT | SWITCHES | 038 | SAN FRANCISCO | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 05/15/2017 | 2017 | 05/03/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31326119 | WEIMAR 1101 - NATURE'S WAY RECONDUCTOR | 112874571 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/01/2019 | ED.20-R110100000 | PLACER MAP R1101 | 031 | PLACER COUNTY | 5535211 | CWSP SPO - SH 08 | 2,990.000 | 2,990.000 | 08W | 05/16/2017 | 2017 | 05/30/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | 31326119_Weimar 1101 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 997479.35
31329860 | *CANC*DONOT USE* PN WIREDOWN 17-004*CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/28/2018 | ED.02264.1112.SWIT | SWITCHES | 041 | SAN MATEO COUN | 5505513 | PN-OH ANNEALED/DETER CNDCTR: PM MGD | 0.000 | 0.000 | 08J | 06/05/2017 | 2017 | 05/03/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31330242 | COLUSA 1103 RECOND 7000 FT 6C @ C/O 3557 | 112928808 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/05/2019 | ED.06202.1100.RECL | RECLOSERS | 006 | COLUSA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 6,034.000 | 6,034.000 | 08J | 06/07/2017 | 2017 | # | #VALUE! | DOCC | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 579608.09
31330635 | FORESTHILL 1102 - SPRING GARDEN RD 08W | 112939790 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2018 | ED.20-R130000000 | PLACER MAP R13 | 031 | PLACER COUNTY | 5535211 | CWSP SPO - SH 08 | 11,308.000 | 11,308.000 | 08W | 06/09/2017 | 2017 | 05/30/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | 31330635_FORESTHILL 1102 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 581153.42
31334182 | *CANC*DONOT USE*REPLACE 4800'3-6CU *CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/30/2018 | ED.13-K242300000.PRIM.FUSE | OROVILLE K2423 FUSES | 004 | BUTTE COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 4,800.000 | 0.000 | 08J | 06/27/2017 | 2017 | 05/03/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31334290 | RECON 24 SPANS -ALBION RIDGE RD | 112994612 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/28/2018 | ED.04298.1101.RECL | RECLOSERS | 023 | MENDOCINO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 06/28/2017 | 2017 | # | #VALUE! | UNSE | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 1413.82
31334291 | RECON-6 SPANS CAMP ONE TEN MILE FT BRAGG | 112994395 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/28/2018 | ED.04276.1101.SWIT | SWITCHES | 023 | MENDOCINO COUN | 5535211 | CWSP SPO - SH 08 | 2,710.000 | 0.000 | 08W | 06/28/2017 | 2017 | # | #VALUE! | PEND | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 291473.71
31334292 | RECON 9-SPANS, AUSTIN CREEK RD | 112994393 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/28/2018 | JY | JUNK YARD FL TO HOLD DELETED DATA | 049 | SONOMA COUNTY | 5535211 | CWSP SPO - SH 08 | 2,513.000 | 2,493.000 | 08W | 06/28/2017 | 2017 | 11/21/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 1033385.2
31335251 | CATLETT 1102 - SANKEY ROAD RECONDUCTOR | 113008551 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/30/2019 | ED.11-X250400000 | MARYSVILLE MAP X2504 | 051 | SUTTER COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 11,455.000 | 10,736.000 | 08J | 07/05/2017 | 2017 | 10/10/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31335251_Catlett 1102 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 1044215.47
31335358 | R1_PN WIREDOWN - LAWNDALE 402 | 113006410 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/29/2019 | ED.02244.0402.CAPA | CAPACITORS | 041 | SAN MATEO COUN | 5505513 | PN-OH ANNEALED/DETER CNDCTR: PM MGD | 0.000 | 0.000 | 08J | 07/05/2017 | 2017 | # | #VALUE! | UNSE | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31336579 | *CANC*DO NOT USE* RECONDUCTOR 7 SPA*CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/01/2019 | ED.01447.1106 | DUMBARTON 1106 | 001 | ALAMEDA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 07/12/2017 | 2017 | 05/03/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31338871 | RELIAIBLITY RICHMOND-REPL #6 CU-UWF_PH2 | 113074026 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/26/2018 | ED.01250.1113 | EL CERRITO G 1113 | 007 | CONTRA COSTA C | 5535211 | CWSP SPO - SH 08 | 3,505.000 | 3,505.000 | 08W | 07/25/2017 | 2017 | 04/25/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | 31338871_RELIAIBLITY RICHMOND-REPL 6 PH2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 654036.73
31338877 | DUMBARTON 2111 FUSE 7809 PROJECT | 113084224 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2018 | ED.01447.2111 | DUMBARTON 2111 | 001 | ALAMEDA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 5,379.000 | 0.000 | 08J | 07/25/2017 | 2017 | # | #VALUE! | UNSC | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | DUMBARTON 2111 FUSE 7809 PROJECT | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 118246.62
31338891 | BEAR VALLEY 2105-REPLAC 8MILE OH W/397AL | 113073622 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/11/2017 | ED.25219.2105 | BEAR VALLEY 2105 | 022 | MARIPOSA COUNT | 5535457 | DO 08 - Monthly Forecast Only | 42,240.000 | 42,240.000 | 08J | 07/24/2017 | 2017 | 08/22/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 195709.3
31339501 | REPL DET COND BAGGET MARYSVILLE RD | 113090688 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2018 | ED.10291.1106.SWIT | SWITCHES | 004 | BUTTE COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 07/27/2017 | 2017 | # | #VALUE! | UNSE | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 1291.93
31340098 | ****CANCELLED***GRAND ISLAND 2226 RECOND | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2019 | ED.06246.2226.SWIT | SWITCHES | 048 | SOLANO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 2,600.000 | 0.000 | 08J | 08/01/2017 | 2017 | 02/29/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 886.91
31340108 | WYANDOTTE 1106 OPHIR RD 8,400'(NO WP YR) | 4997767 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2019 | ED.10291.1106.RECL | RECLOSERS | 004 | BUTTE COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 08/01/2017 | 2017 | # | #VALUE! | UNSE | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 2969.63
31343120 | *CANC*DONOT USE*2019 VALLEJO B 413 *CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2019 | ED.04245.0413 | VALLEJO B 0413 | 048 | SOLANO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 08/17/2017 | 2017 | 05/03/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31343123 | *CANC*DO NOT USE*2019 PUEBLO HIGH *CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2019 | ED.04329.1104 | PUEBLO 1104 | 028 | NAPA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 08/17/2017 | 2017 | 05/03/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31343124 | *CANC*DONOT USE*2019 WILLOW PASS 21*CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2019 | ED.01391.2108 | WILLOW PASS 2108 | 007 | CONTRA COSTA C | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 08/17/2017 | 2017 | 05/03/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31343125 | *CANC*DONOT USE* 2019 NORTH TOWER 2*CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2019 | ED.04204.2201 | NORTH TOWER 2201 | 048 | SOLANO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 08/17/2017 | 2017 | 05/03/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31343126 | *CANC* 2019 TARAVAL 402 HIGH SPLICE*CANC | 5018000 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2019 | ED.02250.0402 | TARAVAL 0402 | 038 | SAN FRANCISCO | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 08/17/2017 | 2017 | 04/03/2019 | 2019 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31343127 | 2019 WILLOW PASS 2108 HIGH SPLICE 2 | 113163071 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2019 | ED.01391.2108 | WILLOW PASS 2108 | 007 | CONTRA COSTA C | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 08/17/2017 | 2017 | # | #VALUE! | UNSE | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 383.53
31343236 | *CANC*DONOT USE*2019 PUEBLO HIGH S*CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2019 | ED.04329.1104 | PUEBLO 1104 | 028 | NAPA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 08/18/2017 | 2017 | 05/03/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31343237 | 2019 KIRKER 2107 HIGH SPLICE COUNT | 113163131 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2019 | ED.01445.2107 | KIRKER 2107 | 007 | CONTRA COSTA C | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 08/18/2017 | 2017 | # | #VALUE! | UNSE | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 2730.11
31343238 | *CANC*DONOT USE* 2019 YOSEMITE 401 *CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2019 | ED.02249.0401 | YOSEMITE 0401 | 038 | SAN FRANCISCO | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 08/18/2017 | 2017 | 05/03/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31343500 | CWSP ORINDA 401 HIGH SPLICE COUNT | 113163138 | # | Not assigned | 30 | Technically Completed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 05/13/2020 | ED.01235.0401 | ORINDA 0401 | 007 | CONTRA COSTA C | 5535211 | CWSP SPO - SH 08 | 8,023.000 | 8,400.000 | 08W | 08/18/2017 | 2017 | # | #VALUE! | FICL | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 1937387.23
31343501 | 2019 ACTON 401 HIGH SPLICE COUNT | 113163201 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2019 | ED.02247.0401 | ACTON 0401 | 038 | SAN FRANCISCO | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 08/18/2017 | 2017 | # | #VALUE! | UNSE | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31344013 | 2019 LAKEWOOD 2110 HIGH SPLICE COUNT | 113163204 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2019 | ED.01353.2110 | LAKEWOOD 2110 | 007 | CONTRA COSTA C | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 08/22/2017 | 2017 | # | #VALUE! | UNSE | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 2840.81
31344014 | 2019 RANDOLPH 403 HIGH SPLICE COUNT | 113163206 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2019 | ED.02259.0403 | RANDOLPH 0403 | 038 | SAN FRANCISCO | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 08/22/2017 | 2017 | # | #VALUE! | UNSE | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31344015 | CNCL: 2019 CALISTOGA 1101 HIGH SPLICE CT | # | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2019 | ED.04271.1101 | CALISTOGA 1101 | 028 | NAPA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 08/22/2017 | 2017 | # | #VALUE! | DOCC | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 31733.6
31344016 | 2019 OLEMA 1101 HIGH SPLICE CNT_1 | 113163270 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2019 | ED.04229.1101 | OLEMA 1101 | 021 | MARIN COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 08/22/2017 | 2017 | # | #VALUE! | UNSE | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 818.88
31344017 | 2019 OLEMA 1101 HIGH SPLICE CNT_2 | 113163271 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2019 | ED.04229.1101 | OLEMA 1101 | 021 | MARIN COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 08/22/2017 | 2017 | # | #VALUE! | UNSE | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 1088.43
31344213 | ARBUCKLE 1102 8334' WIRE DOWN (NO WP YR) | 113165945 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2021 | ED.06205.1102.SWIT | SWITCHES | 006 | COLUSA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 08/23/2017 | 2017 | # | #VALUE! | UNSE | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 3064.22
31350280 | *CANC*DONOT USE* 2019 PN DC-1112 WI*CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2019 | ED.02264.1112.SWIT | SWITCHES | 041 | SAN MATEO COUN | 5505513 | PN-OH ANNEALED/DETER CNDCTR: PM MGD | 0.000 | 0.000 | 08J | 09/11/2017 | 2017 | 05/03/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31350562 | *CANC*DONOT USE*EL CAPITAN 1104 REC*CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2019 | ED.72-07131C0000.STRU.POLE | MERCED MAP 07131C POLES | 024 | MERCED COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 2,200.000 | 0.000 | 08J | 09/12/2017 | 2017 | 05/03/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31351748 | *CANC*DONOT USE*2019 08J PN SL-1107*CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/27/2019 | ED.02272.1107.TXFR.TROH | OVERHEAD TRANSFORMERS | 041 | SAN MATEO COUN | 5517127 | DO 08 - Monthly Forecast Only | 1,700.000 | 0.000 | 08J | 09/19/2017 | 2017 | 05/03/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31352018 | *CANC* MALAGA 1103 RECONDUCTORING *CANC | 5069772 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2019 | ED.70-1421600000.STRU.POLE | FRESNO 14216 POLES | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 09/20/2017 | 2017 | 10/04/2017 | 2017 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31352062 | L-1102 - 48TH AVE RECONDUCTORING PROJECT | 113262162 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/04/2020 | ED.02226.1102 | SF L 1102 | 038 | SAN FRANCISCO | 5535457 | DO 08 - Monthly Forecast Only | 2,888.000 | 0.000 | 08J | 09/20/2017 | 2017 | # | #VALUE! | DOCC | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31352062_L-1102 48TH AVE RECONDUCTORING | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 1113164.25
31354054 | *CANC*DONOT USE* 2019 08J PN EG-110*CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/27/2019 | ED.02257.1101.TXFR.TROH | OVERHEAD TRANSFORMERS | 041 | SAN MATEO COUN | 5505513 | PN-OH ANNEALED/DETER CNDCTR: PM MGD | 1,700.000 | 0.000 | 08J | 10/04/2017 | 2017 | 05/03/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31354827 | *CANC* EIGHT MILE 2102 RECONDUCTOR *CANC | 113674992 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2019 | ED.93-S120000000.STRU.POLE | STOCKTON S12 POLES | 039 | SAN JOAQUIN CO | 5535457 | DO 08 - Monthly Forecast Only | 5,100.000 | 0.000 | 08J | 10/05/2017 | 2017 | 05/03/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31354827_EIGHT MILE 2102 RECONDUCTORING | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31354872 | *CNCL* EEL RIVER 1102 FU1903 | # | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/11/2019 | ED.35-V070000000.STRU.POLE | FORTUNA V07 POLES | 012 | HUMBOLDT COUNT | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 10/05/2017 | 2017 | # | #VALUE! | UNSE | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 547.37
31354874 | CONVERTED TO 35XX SERIES PM - CANCEL PM | 5107375 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/25/2019 | ED.19238.1102 | EEL RIVER 1102 | 012 | HUMBOLDT COUNT | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 10/05/2017 | 2017 | # | #VALUE! | UNSE | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 802.49
31354878 | CONVERTED TO 35XX SERIES PM - CANCEL PM | 5107395 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/25/2019 | JY | JUNK YARD FL TO HOLD DELETED DATA | 012 | HUMBOLDT COUNT | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 10/05/2017 | 2017 | # | #VALUE! | UNSE | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 847.34
31354988 | TULUCAY 1101 RECOND WITH TREE WIRE | 113676059 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/05/2018 | ED.42-NN40000000.STRU.POLE | SILVERADO MAP NN40 POLES | 028 | NAPA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 10/05/2017 | 2017 | # | #VALUE! | UNSE | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 2877.76
31354989 | NAPA 1105 HIGH SPLICE COUNT | 113676082 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/05/2018 | ED.42-LL38170000.STRU.POLE | SILVERADO MAP LL3817 POLES | 028 | NAPA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 10/05/2017 | 2017 | # | #VALUE! | UNSE | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 2074.11
31354990 | TULUCAY 1101 HIGH SPLICE COUNT | 113676289 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/05/2018 | ED.42-NN39000000.STRU.POLE | SILVERADO NN39 POLES | 028 | NAPA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 10/05/2017 | 2017 | # | #VALUE! | UNSE | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31354991 | PUEBLO 2102 HIGH SPLICE COUNT | 113676470 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/05/2018 | ED.42-JJ36000000.STRU.POLE | SILVERADO MAP JJ36 POLES | 028 | NAPA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 10/05/2017 | 2017 | # | #VALUE! | UNSE | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 3383.61
31354992 | GREENBRAE 1104 HIGH SPLICE COUNT | 113676471 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/05/2018 | JY | JUNK YARD FL TO HOLD DELETED DATA | 021 | MARIN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 10/05/2017 | 2017 | # | #VALUE! | UNSE | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 2231.05
31355773 | *CANC* RECOND GREEN VALLEY 2103 RE | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/29/2019 | ED.08319.2103 | GREEN VALLEY 2103 | 044 | SANTA CRUZ COU | 5535457 | DO 08 - Monthly Forecast Only | 18,420.000 | 0.000 | 08J | 10/10/2017 | 2017 | 09/05/2019 | 2019 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31355774 | *CANC*DONOT USE*RECOND GREEN VALLEY*CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/29/2019 | ED.08319.2103 | GREEN VALLEY 2103 | 044 | SANTA CRUZ COU | 5535457 | DO 08 - Monthly Forecast Only | 12,225.000 | 0.000 | 08J | 10/10/2017 | 2017 | 05/03/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31355775 | RECOND GREEN VALLEY 2103 REF# S032CC202 | 113663968 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/29/2019 | ED.08319.2103 | GREEN VALLEY 2103 | 044 | SANTA CRUZ COU | 5535457 | DO 08 - Monthly Forecast Only | 25,360.000 | 0.000 | 08J | 10/10/2017 | 2017 | # | #VALUE! | UNSE | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 7028.16
31355776 | *CANC*DONOT USE*RECOND GREEN VALLEY*CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/29/2019 | ED.08319.2101 | GREEN VALLEY 2101 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 2,580.000 | 0.000 | 08J | 10/10/2017 | 2017 | 05/03/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31355777 | *CANC*DONOT USE*RECOND WATSONVILLE *CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/29/2019 | ED.08333.2101 | WATSONVILLE 2101 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 26,540.000 | 0.000 | 08J | 10/10/2017 | 2017 | 05/03/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31356031 | *CANC*DONOT USE*ATWATER 1103 RECOND*CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2019 | ED.72-06125B0000.STRU.POLE | MERCED MAP 06125B POLES | 024 | MERCED COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 2,300.000 | 0.000 | 08J | 10/10/2017 | 2017 | 05/03/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | ATWATER 1103 RECONDUCTORING | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31358176 | *CANC*DO NOT USE*EL NIDO 1101 - TAR*CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/30/2019 | ED.25245.1101 | EL NIDO 1101 | 020 | MADERA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 10/11/2017 | 2017 | 05/03/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31360749 | *CANC* RECONDUCTOR RIPON 1701 - SP *CANC | 5161585 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/27/2019 | ED.16380.1701 | RIPON 1701 | 039 | SAN JOAQUIN CO | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 10/12/2017 | 2017 | 05/03/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | RECONDUCTOR RIPON 1701 - SPLICE COUNT | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31360766 | FROGTOWN 1701 RECOND 1153FTTO 1/0ACSR TW | 113720778 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/28/2019 | ED.16345.1701 | FROGTOWN 1701 | 005 | CALAVERAS COUN | 5535211 | CWSP SPO - SH 08 | 1,153.000 | 1,153.000 | 08W | 10/12/2017 | 2017 | 02/29/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 400124.86
31360838 | *CANC*DONOT USE*RPL OH WIRE ON DOLA*CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/28/2019 | ED.05-E071000000.STRU.POLE | SALINAS E0710 POLES | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 9,854.000 | 0.000 | 08J | 10/13/2017 | 2017 | 05/03/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | R2 RPL OH WIRE ON DOLAN RD1101 S040CC207 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31360980 | *CANC*DONOT USE*RPL OH WIRE ON DOLA*CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/28/2019 | ED.05-D082300000.STRU.POLE | SALINAS D0823 POLES | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 992.000 | 0.000 | 08J | 10/13/2017 | 2017 | 05/03/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31360981 | R2 OH WIRE ON BONRNDA 1102 17-0083078 | 113725886 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/28/2019 | JY | JUNK YARD FL TO HOLD DELETED DATA | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 10/13/2017 | 2017 | # | #VALUE! | UNSE | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 805.27
31361056 | *CANC* KINGSBURG 1111 RECOND 12000 *CANC | 5164356 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/28/2019 | ED.25224.1111 | KINGSBURG 1111 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 10/16/2017 | 2017 | 06/05/2019 | 2019 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31361057 | *CANC* KINGSBURG 1111 RECOND 4010 O*CANC | 5164317 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 05/31/2019 | ED.25224.1111 | KINGSBURG 1111 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 10/16/2017 | 2017 | 06/05/2019 | 2019 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31361320 | *CANC*DONOT USE*EL CAPITAN 1104 REC*CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2019 | ED.72-0713151000.STRU.POLE | MERCED MAP 0713151 POLES | 024 | MERCED COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 4,700.000 | 0.000 | 08J | 10/17/2017 | 2017 | 05/03/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31361321 | *CANC*DONOT USE* RECONDUCTOR - FUSE*CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2018 | ED.18267.1106 | SANTA MARIA 1106 | 015 | KERN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 6,850.000 | 0.000 | 08J | 10/17/2017 | 2017 | 05/03/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31361322 | *CANC*DONOT USE* RECONDUCTOR - FUSE*CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.18267.1109 | SANTA MARIA 1109 | 015 | KERN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 2,875.000 | 0.000 | 08J | 10/17/2017 | 2017 | 05/03/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31361488 | *CANC* RECOND 15 298 FT 6CU 4CU & *CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/17/2019 | ED.42-FF30000000.STRU.POLE | SILVERADO FF30 POLES | 028 | NAPA COUNTY | 5535211 | CWSP SPO - SH 08 | 13,780.000 | 0.000 | 08W | 10/18/2017 | 2017 | 10/03/2019 | 2019 | CLSD | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
31361489 | OLEMA 1101 HIGH SPLICE COUNT 3 | 113745486 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/18/2019 | ED.40-QQ24030000.STRU.POLE | NORTH BAY MAP QQ2403 POLES | 021 | MARIN COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 10/18/2017 | 2017 | # | #VALUE! | UNSE | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 870.75
31361625 | *CANC*DONOT USE* VALLEJO 414 HIGH S*CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/19/2019 | ED.42-QQ39080000.STRU.POLE | SILVERADO QQ3908 POLES | 048 | SOLANO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 10/19/2017 | 2017 | 05/03/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31361965 | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 | 113751296 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/27/2019 | ED.04307.1101.RECL | RECLOSERS | 049 | SONOMA COUNTY | 5535211 | CWSP SPO - SH 08 | 2,367.000 | 0.000 | 08W | 10/23/2017 | 2017 | # | #VALUE! | CONS | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 172935.69
31361967 | *CANC*DONOT USE* RECON 815 FT TAP O*CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/27/2019 | ED.04341.1101.RECL | RECLOSERS | 023 | MENDOCINO COUN | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 10/23/2017 | 2017 | 05/03/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31361969 | RECON 9,400 FT - POINT ARENA 1101 | 113752520 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/27/2019 | ED.04338.1101.RECL | RECLOSERS | 023 | MENDOCINO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 10/23/2017 | 2017 | # | #VALUE! | UNSE | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 1200.31
31362297 | *CANC*DONOT USE*ELK HILLS 1104 OH S*CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/30/2019 | ED.25244.1104 | ELK HILLS 1104 | 015 | KERN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 10/25/2017 | 2017 | 05/03/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31362298 | *CANC*DONOT USE*ELK HILLS 1104 OH S*CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/30/2019 | ED.25244.1104 | ELK HILLS 1104 | 020 | MADERA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 10/25/2017 | 2017 | 05/03/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31362346 | *CANC*GANSO 1104 RECOND 2900FT TO 2AR | # | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/28/2019 | ED.25454.1104 | GANSO 1104 | 015 | KERN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 10/25/2017 | 2017 | # | #VALUE! | UNSE | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31362454 | *CANC*GUERNSEY 1101 LR 92702 RECOND 2060 | 113763631 | # | Not assigned | 25 | Canceled | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/31/2021 | ED.25266.1101 | GUERNSEY 1101 | 016 | KINGS COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 10/26/2017 | 2017 | # | #VALUE! | CNCL | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | -811.32
31363087 | REPL 3-6CU ON NELSON SHIPPEE RD - ESQUON | 113771716 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.10217.1101.SWIT | SWITCHES | 004 | BUTTE COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 10/30/2017 | 2017 | # | #VALUE! | UNSE | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | REPL 3-6CU ON NELSON SHIPPEE RD - ESQUON | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 5907.76
31364170 | *CANC*DONOT USE* RECONDUCTOR 3,750'*CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/15/2019 | ED.18281.1101 | SISQUOC 1101 | 040 | SAN LUIS OBISP | 5535457 | DO 08 - Monthly Forecast Only | 2,600.000 | 0.000 | 08J | 11/09/2017 | 2017 | 05/03/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31364228 | RECOND 4490FT OF 4ACSR WITH 2CU TW | 113782453 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/30/2018 | ED.18295.1101 | FOOTHILL 1101 | 040 | SAN LUIS OBISP | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 11/07/2017 | 2017 | # | #VALUE! | UNSE | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 645.06
31364252 | *CANC*DONOT USE*EIGHT MILE2101-RECO*CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/29/2019 | ED.93-Q091200000.STRU.POLE | STOCKTON Q0912 POLES | 039 | SAN JOAQUIN CO | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 11/07/2017 | 2017 | 05/03/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31364254 | KINGSBURG 1114 - RECONDUCTOR | 113779647 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/29/2019 | ED.70-16225D0000.STRU.POLE | FRESNO 16225D POLES | 054 | TULARE COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 11/07/2017 | 2017 | # | #VALUE! | UNSE | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 2241.75
31364255 | MAGUNDEN 1108 - RECONDUCTOR | 113779668 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/29/2019 | ED.66-2929311000.STRU.POLE | KERN 2929311 POLES | 015 | KERN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 11/07/2017 | 2017 | # | #VALUE! | UNSE | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 964.83
31364321 | STONE CORRAL 1110 - RECONDUCTOR | 113779723 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/29/2019 | ED.70-1726400000.STRU.POLE | FRESNO 17264 POLES | 054 | TULARE COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 11/07/2017 | 2017 | # | #VALUE! | UNSE | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 1603.26
31364323 | *CANC*DONOT USE*STOREY 1109-ECONDUC*CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/29/2019 | ED.72-11182D0000.STRU.POLE | YOSEMITE MAP 11182D POLES | 020 | MADERA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 11/07/2017 | 2017 | 05/03/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31364518 | 2109 CLAYTON 2217 HIGH SPLICE COUNT | 113781102 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2019 | ED.01202.2217 | CLAYTON 2217 | 007 | CONTRA COSTA C | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 11/08/2017 | 2017 | # | #VALUE! | UNSE | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 173.34
31364519 | 2019 BRENTWOOD 2108 HIGH SPLICE COUNT | 113781183 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/30/2019 | ED.01459.2108 | BRENTWOOD 2108 | 007 | CONTRA COSTA C | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 11/08/2017 | 2017 | # | #VALUE! | UNSE | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31364941 | *CANC*DONOT USE*2019 08J PN MILLBRA*CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/27/2019 | ED.02269.1102.SWIT | SWITCHES | 041 | SAN MATEO COUN | 5505513 | PN-OH ANNEALED/DETER CNDCTR: PM MGD | 0.000 | 0.000 | 08J | 11/10/2017 | 2017 | 05/03/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31365090 | *CANC* KINGSBURG 1111 RECOND 21,880 FEE | 113796153 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/04/2019 | ED.25224.1111 | KINGSBURG 1111 | 054 | TULARE COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 11/13/2017 | 2017 | 04/14/2018 | 2018 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31365702 | *CANC* *DO NOT USE* STONE CORRAL 11*CANC | 113820041 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 07/05/2019 | ED.25292.1110 | STONE CORRAL 1110 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 11/16/2017 | 2017 | 09/03/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31365703 | *CANC*DONOT USE*STONE CORRAL 1110 R*CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/28/2019 | ED.25292.1110 | STONE CORRAL 1110 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 11/16/2017 | 2017 | 05/03/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31366025 | *CANC*DONOT USE* NEWMAN 1106 REPLAC*CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2021 | ED.16274.1106 | NEWMAN 1106 | 050 | STANISLAUS COU | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 11/17/2017 | 2017 | 05/03/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31367226 | TASSAJARA 2108 OH RECONDUCTOR | 114031980 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2019 | ED.01466.2108 | TASSAJARA 2108 | 007 | CONTRA COSTA C | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 11/27/2017 | 2017 | # | #VALUE! | UNSE | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 173.34
31367398 | *CANC*DONOT USE* WESTPARK 1104 RECO*CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/28/2019 | ED.25370.1104 | WESTPARK 1104 | 015 | KERN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 11/29/2017 | 2017 | 05/03/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31367399 | *CANC*DONOT USE*SEMITROPIC 1110 REC*CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.25290.1110 | SEMITROPIC 1110 | 015 | KERN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 11/29/2017 | 2017 | 05/03/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31368334 | KINGSBURG 1111 - RECONDUCTOR 7,800 FT | 114045191 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/30/2019 | ED.70-16225C0000.STRU.POLE | FRESNO 16225C POLES | 054 | TULARE COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 12/05/2017 | 2017 | # | #VALUE! | UNSE | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 1068.46
31369863 | SILVERADO 2102 RECONDUCTOR JOB | 114106530 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2019 | JY | JUNK YARD FL TO HOLD DELETED DATA | 028 | NAPA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 12/14/2017 | 2017 | # | #VALUE! | UNSE | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31372445 | RE-COND 7988 FT OF 6CU & 4AC W 2CU | 114156606 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 01/05/2019 | ED.18263.1103 | SAN LUIS OBISPO 1103 | 040 | SAN LUIS OBISP | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 01/05/2018 | 2018 | # | #VALUE! | UNSE | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 3715.4
31374248 | *CANC*DONOT USE*RE-COND 6260 CIRCU*CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 01/05/2019 | ED.18206.1104 | FAIRWAY 1104 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 01/16/2018 | 2018 | 05/03/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31374249 | 14184 FT OF 4ACSR&3363 FT OF 6CUW 2CU TW | # | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 01/16/2020 | ED.18310.1103 | CABRILLO 1103 | 042 | SANTA BARBARA | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 01/16/2018 | 2018 | # | #VALUE! | UNSE | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 1088.43
31375924 | TUPMAN 1104 RECONDUCTOR 7,000 FEET | 114236443 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 05/31/2022 | ED.25456.1104 | TUPMAN 1104 | 015 | KERN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 01/26/2018 | 2018 | # | #VALUE! | UNSE | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 6661.45
31376255 | *CANC* LODI 1102 RECONDUCTORING - *CANC | 114253974 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.93-Q111400000.STRU.POLE | STOCKTON Q1114 POLES | 039 | SAN JOAQUIN CO | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 01/29/2018 | 2018 | 06/03/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31377173 | *CANC*DONOT USE*BANTA 1101 RECONDUC*CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.16247.1101 | BANTA 1101 | 039 | SAN JOAQUIN CO | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 02/02/2018 | 2018 | 05/03/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31377407 | HIGGINS 1107 RECONDUCTOR 2800', AUBURN | 114278944 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.15269.1107.SWIT | SWITCHES | 029 | NEVADA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 4,045.000 | 0.000 | 08J | 02/06/2018 | 2018 | # | #VALUE! | UNSC | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 484098.54
31379155 | *CANC*DONOT USE*6149CIRCUIT FT(52 S*CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/16/2018 | ED.18280.1101 | BAYWOOD 1101 | 040 | SAN LUIS OBISP | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 02/14/2018 | 2018 | 05/03/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31380961 | RECON1285 FT OF 3-4ACSR WITH 3-2CU | 114334072 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 02/23/2020 | ED.18297.1101 | PURISIMA 1101 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 02/23/2018 | 2018 | # | #VALUE! | UNSE | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 878.46
31382371 | *CANC*DONOT USE* RECOMMEND 18-00156*CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 08/02/2020 | ED.18281.1104 | SISQUOC 1104 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 03/03/2018 | 2018 | 05/03/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31383064 | 2020 FORT BRAGG 1103 RECONDUC OUTLET | 114367862 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/16/2020 | ED.04276.1103 | FORT BRAGG A 1103 | 023 | MENDOCINO COUN | 5535457 | DO 08 - Monthly Forecast Only | 3,100.000 | 0.000 | 08J | 03/07/2018 | 2018 | # | #VALUE! | ESTS | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 20806.15
31387895 | *CANC* REPL 17 500' OF 4AR & 4CU I *CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2019 | ED.42-GG32250000.STRU.POLE | SILVERADO GG3225 POLES | 028 | NAPA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 04/09/2018 | 2018 | 09/05/2019 | 2019 | CLSD | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | 31387895_SILVERADO 2105 WIRE DOWN | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
31389447 | PUEBLO 1105 RECONDUCTOR W TREE WIRE | 114519107 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/19/2020 | ED.42-JJ38000000.STRU.POLE | SILVERADO MAP JJ38 POLES | 028 | NAPA COUNTY | 5535211 | CWSP SPO - SH 08 | 6,740.000 | 6,740.000 | 08W | 04/20/2018 | 2018 | # | #VALUE! | DOCC | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | 31389447_PUEBLO 1105 RECONDUCTOR | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 3899074.07
31389448 | *CANC* SILVERADO 2104 RECONDUCTOR*CANC | 5361841 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/20/2020 | ED.42-GG33050000.STRU.POLE | SILVERADO MAP GG3305 POLES | 028 | NAPA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 04/20/2018 | 2018 | 03/02/2019 | 2019 | CLSD | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
31391219 | *CANC*DO NOT USE* RE-COND 2300FT 4A*CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/26/2020 | ED.18282.1102 | MESA 1102 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 05/08/2018 | 2018 | 05/03/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31392316 | *CANC* 2018MONTERIO1112/MOLINO1102WILDFI | 5396001 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2018 | ED.04257.1102.SWIT | SWITCHES | 049 | SONOMA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 05/16/2018 | 2018 | 06/09/2018 | 2018 | CLSD | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
31393978 | *CANC* RE-COND 5245 FT 4ACSR&3876 FT | # | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/22/2020 | ED.18281.1102 | SISQUOC 1102 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 05/29/2018 | 2018 | # | #VALUE! | UNSE | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31397184 | PETALUMA C 1108 WIREDOWN LR636 PHASE1 | 114717374 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/30/2020 | ED.04263.1108.SWIT | SWITCHES | 049 | SONOMA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 06/21/2018 | 2018 | # | #VALUE! | UNSE | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31429487 | OTTER-1101 S030CC121 – TRANS POLES | # | 35060584 | RPL OH WIRE ON OTTER-1101 S030CC121 | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | # | ED.07-N031000000.STRU.POLE | MONTEREY N0310 POLES | 027 | MONTEREY COUNT | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 03/18/2019 | 2019 | # | #VALUE! | PEND | E070 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 99248.53
31434881 | 0P 3100 SKYWAY RD PARADISE TUSCAN RIDGE | 116825055 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 08/30/2019 | ED | Electric Distribution System | # | Not assigned | 5791419 | CWSP - BUCOCAMP-SKYWAY PARADISE TIE PH1 | 4,238.000 | 0.000 | 08W | 04/19/2019 | 2019 | # | #VALUE! | PEND | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 10626593.44
31462406 | FOOTHILL 1101 LS CO9973 RECONDUCTOR, SLO | # | 35066622 | FOOTHILL 1101 LS CO9973 RECONDUCTOR, SLO | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | # | ED.18295.1101.TXFR.TROH | OVERHEAD TRANSFORMERS | 040 | SAN LUIS OBISP | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 08/13/2019 | 2019 | # | #VALUE! | ADER | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 14485.73
31463070 | GANSO 1104 RECOND 2900FT TO 2AR | # | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/28/2019 | ED.25454.1104 | GANSO 1104 | 015 | KERN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 08/19/2019 | 2019 | # | #VALUE! | UNSE | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31478906 | RAISE T-LINE H-FRAME DONNELS-MI WUK 18/2 | # | 35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | # | ED.16366.1701 | MIWUK 1701 | 055 | TUOLUMNE COUNT | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 11/21/2019 | 2019 | # | #VALUE! | UNSC | E060 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 3295.3
31478907 | WD-EIGHT MILE2101-CO738931-ILS 180066835 | # | 35052976 | WD-EIGHT MILE2101-CO738931-ILS 180066835 | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | # | ED.16391.2101 | EIGHT MILE 2101 | 039 | SAN JOAQUIN CO | 5535457 | DO 08 - Monthly Forecast Only | 3,132.000 | 0.000 | 08J | 11/21/2019 | 2019 | # | #VALUE! | PEND | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 22637.43
31486236 | *CANC* GRAND ISLAND 2224 RECONDUCT*CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/01/2018 | ED.06246.2224.RECL | RECLOSERS | 048 | SOLANO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 01/14/2020 | 2020 | 02/06/2020 | 2020 | CLSD | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
31513424 | BIOLA 1104 RECONDUCTOR 2,995 FT OF 6CU | # | 35089227 | BIOLA 1104 RECONDUCTOR 2,995 FT OF 6CU | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | # | ED.25221.1104 | BIOLA 1104 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 1,430.000 | 0.000 | 08J | 09/09/2020 | 2020 | # | #VALUE! | PEND | E060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 3098.47
35000302 | RECOND 4149' 6CU &4AR W/2CU SM 1110,GUAD | 112931300 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2021 | ED.18282.1102 | MESA 1102 | 040 | SAN LUIS OBISP | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 06/07/2017 | 2017 | # | #VALUE! | ESTS | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 4903.12
35000308 | 2022 BOWLES 1101 RECOND 5350FT TO 4/0AL | 112938174 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/28/2019 | ED.25353.1101 | BOWLES 1101 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 06/08/2017 | 2017 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 956.97
35001100 | R2 RPL OH WIRE ON SPENCE 1121 17-0051204 | 113011449 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/30/2019 | ED.18220.1121 | SPENCE 1121 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 21,444.000 | 0.000 | 08J | 07/06/2017 | 2017 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 2691.79
35001101 | R2RPL OH WIRE ON DOLN RD 1101 17-0050152 | 113011520 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/30/2019 | ED.18238.1101 | DOLAN ROAD 1101 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 3,114.000 | 0.000 | 08J | 07/06/2017 | 2017 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | R2RPL OH WIRE ON DOLN RD 1101 17-0050152 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 17779.97
35001302 | R2 RPL OH WIRE ON SPENCE 1121 17-0052344 | 113063294 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/30/2019 | ED.05-H112200000.STRU.POLE | SALINAS H1122 POLES | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 2,325.000 | 0.000 | 08J | 07/20/2017 | 2017 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | R2 RPL OH WIRE ON SPENCE 1121 17-0052344 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 20739.21
35001303 | R2 RPL OH WIRE ON SALINS 1103 17-0052542 | 113063299 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/30/2019 | ED.05-G090800000.STRU.POLE | SALINAS G0908 POLES | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 1,290.000 | 0.000 | 08J | 07/20/2017 | 2017 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 2090.98
35001436 | R2 RPL OH WIRE ON SPENCE 1122 17-0048978 | 113090765 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/30/2019 | ED.05-I122100000.STRU.POLE | SALINAS I1221 POLES | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 1,515.000 | 0.000 | 08J | 07/27/2017 | 2017 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 1141.58
35001640 | *CANC* RECONDUCTOR WRIGHT 1110 - W *CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/12/2021 | ED.25464.1110 | WRIGHT 1110 | 024 | MERCED COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 08/11/2017 | 2017 | 05/03/2020 | 2020 | CLSD | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
35001641 | *CANC* RECONDUCTOR RIVERBANK 1715- *CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/27/2019 | ED.16319.1715 | RIVERBANK 1715 | 050 | STANISLAUS COU | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 08/11/2017 | 2017 | 04/04/2020 | 2020 | CLSD | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
35001642 | RECONDUCTOR MADERA 1119 - WIRE DOWN | 113143589 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/29/2019 | ED.25276.1119 | MADERA 1119 | 020 | MADERA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 08/11/2017 | 2017 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
35001661 | R2 2019 ASHLAN AVE 1104 RECONDUCTOR | 113154596 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/31/2021 | ED.25205.1104 | ASHLAN AVE 1104 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 6,100.000 | 0.000 | 08J | 08/14/2017 | 2017 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 35001661_Ashlan Ave 1104 Reconductor | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 17053.89
35001680 | R2 CV - 2021 BIOLA 1103 CONDUCTOR REPLAC | 113155616 | # | Not assigned | 30 | Technically Completed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2022 | ED.25221.1103 | BIOLA 1103 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 08/15/2017 | 2017 | # | #VALUE! | FICL | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 35001680_Boila 1103 Target OH Cond Repl | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 6122.59
35001700 | *CANC* ALPAUGH 1103 RECOND 1600FT*CANC | 113161388 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/27/2019 | ED.25400.1103 | ALPAUGH 1103 | 054 | TULARE COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 08/16/2017 | 2017 | 03/02/2019 | 2019 | CLSD | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
35001847 | *CANC* RECONDUCTOR CHOWCHILLA 110*CANC | 113187407 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/29/2019 | ED.25410.1104 | CHOWCHILLA 1104 | 020 | MADERA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 08/24/2017 | 2017 | 05/03/2019 | 2019 | CLSD | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
35001849 | *CANC*DO NOT USE* R2R OH WIRE ON DO*CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/28/2019 | ED.18238.1104.SWIT | SWITCHES | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 8,997.000 | 0.000 | 08J | 08/24/2017 | 2017 | 05/03/2020 | 2020 | CLSD | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
35001860 | *CANCL* RECOND RIPON 1701 - SPLICE COUNT | 5024955 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/27/2019 | ED.16380.1702 | RIPON 1702 | 039 | SAN JOAQUIN CO | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 08/23/2017 | 2017 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 1210.54
35001862 | WATERLOO 1101 RECOND 4000' OH CONDUCTOR | 113183541 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.16315.1101 | WATERLOO 1101 | 039 | SAN JOAQUIN CO | 5535457 | DO 08 - Monthly Forecast Only | 4,760.000 | 0.000 | 08J | 08/23/2017 | 2017 | # | #VALUE! | PEND | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 21407.88
35008420 | *CANC*2B CANC BIOLA 1104 2019 TARGE*CANC | 113197739 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/14/2018 | ED.25221.1104 | BIOLA 1104 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 08/28/2017 | 2017 | 10/03/2019 | 2019 | CLSD | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
35008478 | *CANC*DO NOT USE*ATWATER 1103 RECON*CANC | 5032846 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2019 | ED.72-06125B0000.STRU.POLE | MERCED MAP 06125B POLES | 024 | MERCED COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 2,300.000 | 0.000 | 08J | 08/29/2017 | 2017 | 05/03/2020 | 2020 | CLSD | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | ATWATER 1103 RECONDUCTORING | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
35008479 | R2 2019 AUBERRY 1101 RECONDUCTOR | 113199104 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2019 | JY | JUNK YARD FL TO HOLD DELETED DATA | 010 | FRESNO COUNTY | 5535211 | CWSP SPO - SH 08 | 1,619.000 | 1,619.000 | 08W | 08/29/2017 | 2017 | 05/31/2020 | 2020 | CLSD | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | 35008479_Auberry 1101 Reconductor | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 286544.93
35008480 | *CANCEL* EIGHT MILE 2102 RECONDUCTORING | 5032981 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2019 | ED.93-S120000000.STRU.POLE | STOCKTON S12 POLES | 039 | SAN JOAQUIN CO | 5535457 | DO 08 - Monthly Forecast Only | 5,100.000 | 0.000 | 08J | 08/29/2017 | 2017 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 35008480_EIGHT MILE 2102 RECONDUCTORING | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 241.75
35008694 | BAKERSFLD 1114 TARGETD OH RECOND | 113212759 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/31/2020 | ED.25337.1114 | BAKERSFIELD 1114 | 015 | KERN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 09/01/2017 | 2017 | # | #VALUE! | PEND | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Bakersfield 1114 Targeted Conductor Repl | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 22879.72
35008700 | RECONDUCTOR RIPON 1701-VAN WYK LN | 113213756 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/27/2019 | ED.16380.1701 | RIPON 1701 | 039 | SAN JOAQUIN CO | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 09/05/2017 | 2017 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 1800.33
35008760 | 2019 KINGBURG 1113 RECONDUCTOR | 113219171 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/31/2020 | ED.25224.1113 | KINGSBURG 1113 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 2,516.000 | 0.000 | 08J | 09/06/2017 | 2017 | # | #VALUE! | CONS | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Kingsburg 1113 Reconductor | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 47308.08
35008761 | *CANC*DO NOT USE* BIOLA 1104 RECOND*CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/29/2019 | ED.25221.1104 | BIOLA 1104 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 09/06/2017 | 2017 | 05/03/2020 | 2020 | CLSD | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Biola 1104 Reconductor | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
35008762 | BONITA 1101 CO 6762 RECOND | 113219235 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/29/2019 | ED.25539.1101 | BONITA 1101 | 020 | MADERA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 09/06/2017 | 2017 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 653.04
35008763 | *CANC* BONITA 1101 CO 32802 RECOND *CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2021 | ED.25539.1101 | BONITA 1101 | 020 | MADERA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 09/06/2017 | 2017 | 05/03/2020 | 2020 | CLSD | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
35011720 | *CANC* PT MORETTI 1101 RECOND 200 FT | 113225530 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/07/2019 | ED.18263.1101 | SAN LUIS OBISPO 1101 | 044 | SANTA CRUZ COU | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 09/11/2017 | 2017 | 10/20/2018 | 2018 | CLSD | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
35011744 | *CANC* BIOLA 1104 6,350FT TAR*CANC | 5058018 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/15/2019 | ED.25221.1104 | BIOLA 1104 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 09/12/2017 | 2017 | 09/06/2018 | 2018 | CLSD | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
35011745 | *CANC* MADERA 1119 3,770FT TARGET *CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/15/2021 | ED.25221.1104 | BIOLA 1104 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 09/12/2017 | 2017 | 05/03/2020 | 2020 | CLSD | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
35013233 | R2RPL OH WIRE ON GONZALS-1101 17-0063084 | 113244215 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/28/2019 | ED.18213.1101.SWIT | SWITCHES | 027 | MONTEREY COUNT | 5535211 | CWSP SPO - SH 08 | 1,967.000 | 0.000 | 08W | 09/13/2017 | 2017 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | 35013233_R2RPL OH WIRE ON GONZALS-1101 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 3538.79
35013266 | *CANC* RECONDUCTOR KINGSBURG 1113 *CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/29/2020 | ED.25224.1113 | KINGSBURG 1113 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 09/13/2017 | 2017 | 07/03/2020 | 2020 | CLSD | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 1230
35013267 | *CANC* RECONDUCTOR CASSIDY 2108 *CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/27/2020 | ED.25427.2108 | CASSIDY 2108 | 020 | MADERA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 09/13/2017 | 2017 | 05/03/2020 | 2020 | CLSD | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
35013273 | *CANC*2019 08J CC VIEJO 2201 S018CC*CANC | 113245186 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/27/2019 | JY | JUNK YARD FL TO HOLD DELETED DATA | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 1,500.000 | 0.000 | 08J | 09/13/2017 | 2017 | 10/03/2020 | 2020 | CLSD | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
35015703 | *CANC* FOOTHILL 1101 LS CO9973 REP *CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/20/2019 | ED.18295.1101.TXFR.TROH | OVERHEAD TRANSFORMERS | 040 | SAN LUIS OBISP | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 09/13/2017 | 2017 | 09/05/2019 | 2019 | CLSD | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35015704 | OH RECONDUCTR ROB ROY 2105 -S026CC117 | 113255603 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/30/2019 | ED.76-O171900000.STRU.POLE | COAST O1719 POLES | 044 | SANTA CRUZ COU | 5535211 | CWSP SPO - SH 08 | 5,300.000 | 0.000 | 08W | 09/15/2017 | 2017 | # | #VALUE! | PEND | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 51954.16
35015705 | *CANC* R2 OH RECONDUCTR ROB ROY 21*CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/30/2019 | ED.76-O171800000.STRU.POLE | COAST O1718 POLES | 044 | SANTA CRUZ COU | 5535211 | CWSP SPO - SH 08 | 4,470.000 | 0.000 | 08W | 09/15/2017 | 2017 | 09/05/2019 | 2019 | CLSD | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35015706 | *CANC* OH RECONDUCTOR - ROB ROY 210*CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/30/2019 | ED.76-O162000000.STRU.POLE | COAST O1620 POLES | 044 | SANTA CRUZ COU | 5535211 | CWSP SPO - SH 08 | 1,630.000 | 0.000 | 08W | 09/15/2017 | 2017 | 09/05/2019 | 2019 | CLSD | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35015932 | *CANC*DO NOT USE* RECONDUCTOR KINGS*CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.25224.1112 | KINGSBURG 1112 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 09/14/2017 | 2017 | 05/03/2020 | 2020 | CLSD | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 35015932_Kingsburg 1112 Recon 9700' | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
35015933 | R2RPL OH WIRE ON DOLANRD-1104 17-0069754 | 113248258 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/28/2019 | JY | JUNK YARD FL TO HOLD DELETED DATA | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 1,785.000 | 0.000 | 08J | 09/14/2017 | 2017 | # | #VALUE! | DOCC | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 96921.8
35015934 | R2RPL OH WIRE ON DOLANRAD-1104 S021CC114 | 113248382 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/28/2019 | ED.05-G081600000.STRU.POLE | SALINAS G0816 POLES | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 5,200.000 | 0.000 | 08J | 09/14/2017 | 2017 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 654.04
35015935 | *CANC*DO NOT USE* RPL OH WIRE ON DO*CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/28/2019 | ED.05-E072400000.STRU.POLE | SALINAS E0724 POLES | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 8,950.000 | 0.000 | 08J | 09/14/2017 | 2017 | 05/03/2020 | 2020 | CLSD | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
35015936 | *CANC*DO NOT USE*RPL OH WIRE ON DOL*CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/28/2019 | ED.05-D082000000.STRU.POLE | SALINAS D0820 POLES | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 12,552.000 | 0.000 | 08J | 09/14/2017 | 2017 | 05/03/2020 | 2020 | CLSD | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
35018262 | *CANC* DINUBA 1104 RECOND 3,240' OF*CANC | 5071444 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/03/2019 | ED.25409.1104 | DINUBA 1104 | 054 | TULARE COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 09/21/2017 | 2017 | 06/05/2019 | 2019 | CLSD | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
35018263 | *CANC* E STOCKTON 402-RECOND 2,80*CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 07/30/2019 | ED.16313.0402 | EAST STOCKTON 0402 | 039 | SAN JOAQUIN CO | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 09/21/2017 | 2017 | 04/03/2019 | 2019 | CLSD | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
35018550 | *CANC* RECONDUCTOR BONITA 1101 - A *CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/27/2021 | ED.25539.1101 | BONITA 1101 | 020 | MADERA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 09/19/2017 | 2017 | 05/03/2020 | 2020 | CLSD | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
35018551 | RECONDUCTOR LIVINGSTON 1106-D STREET | 113249256 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/29/2019 | ED.25226.1106 | LIVINGSTON 1106 | 024 | MERCED COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 09/19/2017 | 2017 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
35018552 | *CANC* R2 EL NIDO 1101 RECOND 3700 *CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.25245.1101 | EL NIDO 1101 | 024 | MERCED COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 09/19/2017 | 2017 | 05/03/2020 | 2020 | CLSD | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
35018554 | RIO BRAVO 1106 - RECONDUCTOR | 113258014 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/30/2021 | ED.66-2925200000.STRU.POLE | KERN 29252 POLES | 015 | KERN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 09/20/2017 | 2017 | # | #VALUE! | ESTS | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 35018554_RIO BRAVO 1106 - RECONDUCTOR | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 14916.17
35018561 | *CANC* R2 MERCED 1116 RECONDUCTOR *CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.72-0814400000.STRU.POLE | MERCED MAP 08144 POLES | 024 | MERCED COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 6,400.000 | 0.000 | 08J | 09/20/2017 | 2017 | 05/03/2020 | 2020 | CLSD | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
35018562 | *CANC* ROUGH AND READY 1102 RECOND *CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/27/2019 | ED.16308.1102 | ROUGH AND READY IS 1102 | 039 | SAN JOAQUIN CO | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 09/20/2017 | 2017 | 04/04/2020 | 2020 | CLSD | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
35018563 | R2 2019 MALAGA 1103 RECONDUCTORING | 113262070 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/30/2021 | ED.70-1421600000.STRU.POLE | FRESNO 14216 POLES | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 09/20/2017 | 2017 | # | #VALUE! | ADER | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Malaga 1103 Reconductor | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 36519.72
35018564 | *CANC*DO NOT USE*2019 MARICOPA 1102*CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/30/2021 | ED.66-1123300000.STRU.POLE | KERN 11233 POLES | 015 | KERN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 9,400.000 | 0.000 | 08J | 09/20/2017 | 2017 | 05/03/2020 | 2020 | CLSD | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Maricopa 1102 Reconductor | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
35018566 | 2019 TAFT 1106 RECONDUCTORING | 113264770 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/30/2022 | ED.66-3223123000.STRU.POLE | KERN 3223123 POLES | 015 | KERN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 6,500.000 | 0.000 | 08J | 09/20/2017 | 2017 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Taft 1106 Reconductoring | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 9197.99
35018620 | *CANC* RECON CAB 1104 17K FT LASAL *CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/22/2019 | ED.18310.1104 | CABRILLO 1104 | 042 | SANTA BARBARA | 5535211 | CWSP SPO - SH 08 | 17,020.000 | 0.000 | 08W | 09/25/2017 | 2017 | 09/05/2019 | 2019 | CLSD | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35018622 | RECON 1400' 2CU,UNION SUGAR & OCEAN,LOMP | 113260798 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2021 | ED.18310.1104 | CABRILLO 1104 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 09/26/2017 | 2017 | # | #VALUE! | ESTS | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 3556.88
35018632 | *CANC*DO NOT USE* R2OLD RIVR 1102 R*CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/30/2020 | ED.25282.1102.RECL | RECLOSERS | 015 | KERN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 09/29/2017 | 2017 | 05/03/2020 | 2020 | CLSD | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Old River 1102 Targeted OH Conductor Rep | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
35018787 | HALSEY 1101 - S039NO112 HIGH SPLICE 08J | 113265459 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/29/2019 | ED.20-R102100000 | PLACER MAP R1021 | 031 | PLACER COUNTY | 5535211 | CWSP SPO - SH 08 | 2,851.000 | 2,854.000 | 08W | 09/29/2017 | 2017 | # | #VALUE! | DOCC | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 756214.27
35018788 | APPLE HILL 1104 - S049NO119 HIGH SPLICE | 113265480 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/30/2019 | ED.21-H451900000 | EL DORADO MAP H4519 | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 6,399.000 | 6,121.000 | 08W | 09/29/2017 | 2017 | 09/12/2020 | 2020 | CLSD | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 1502306.99
35018886 | *CANC* RPL OH WIRE ON GABILN 1101 *CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/28/2019 | ED.05-H120700000.STRU.POLE | SALINAS H1207 POLES | 027 | MONTEREY COUNT | 5535211 | CWSP SPO - SH 08 | 11,592.000 | 0.000 | 08W | 10/03/2017 | 2017 | 09/05/2019 | 2019 | CLSD | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35018887 | *CANC* RPL OH WIRE ON OTTER-1101 S*CANC | 113648853 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/28/2019 | ED.07-N030900000.STRU.POLE | MONTEREY N0309 POLES | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 10/03/2017 | 2017 | 11/03/2017 | 2017 | CLSD | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
35018895 | OROSI 1101 RECOND 4460FT TO 2AR | 113674750 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/30/2021 | ED.25284.1101 | OROSI 1101 | 054 | TULARE COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 10/05/2017 | 2017 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 4693.11
35019004 | PURISIMA 1101 LS SW8139 REPL OH LINE | 113677313 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/05/2019 | ED.18297.1101.TXFR.TROH | OVERHEAD TRANSFORMERS | 040 | SAN LUIS OBISP | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 10/06/2017 | 2017 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 8820.84
35019005 | SISQUOC 1104 LR M58 REPLACE OH LINE | 113677552 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/05/2019 | ED.18281.1104.TXFR.TROH | OVERHEAD TRANSFORMERS | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 10/06/2017 | 2017 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
35019006 | ROB ROY 2104 CO11865 REPLACE OH LINE | 113677589 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/05/2019 | JY | JUNK YARD FL TO HOLD DELETED DATA | 044 | SANTA CRUZ COU | 5535211 | CWSP SPO - SH 08 | 9,680.000 | 8,620.000 | 08W | 10/06/2017 | 2017 | 07/25/2020 | 2020 | CLSD | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 1004571.38
35019007 | RECON 4780', LR7024, KING CITY 1102 | 113677628 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/05/2019 | ED.18203.1102.SWIT | SWITCHES | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 10/06/2017 | 2017 | # | #VALUE! | ADER | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 44332
35019122 | *CANC*R2 RE-COND 2641 FT OF 3-4ACSR*CANC | 113632342 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/28/2019 | ED.18310.1104 | CABRILLO 1104 | 040 | SAN LUIS OBISP | 5535457 | DO 08 - Monthly Forecast Only | 2,623.000 | 0.000 | 08J | 10/10/2017 | 2017 | 01/04/2019 | 2019 | CLSD | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
35019123 | RECONDUCTOR 3579 FT W 2CU MESA 1101 | 113717955 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/10/2019 | ED.18282.1101 | MESA 1101 | 040 | SAN LUIS OBISP | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 10/10/2017 | 2017 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 343.89
35019222 | R2 RPL OH WRE ON PRUNDLE 1107 17-0075216 | 113703369 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/28/2019 | ED.05-E092000000.STRU.POLE | SALINAS E0920 POLES | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 10/10/2017 | 2017 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 1094.77
35019354 | *CANC* GANSO 1104 RECOND 2900FT TO 2AR | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/28/2019 | ED.25454.1104 | GANSO 1104 | 015 | KERN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 10/23/2017 | 2017 | 11/04/2017 | 2017 | CLSD | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
35019447 | +R2 RECONDUCTR 4268FT OF3-4ACSR WT3-2CU | 113724523 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.18310.1104 | CABRILLO 1104 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 4,396.000 | 0.000 | 08J | 10/16/2017 | 2017 | # | #VALUE! | CONS | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 83322.08
35019453 | RECONDUCTOR 1230 FT(7 SPANS) OF 3-6CU | 113742341 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/30/2019 | ED.18206.1106 | FAIRWAY 1106 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 10/18/2017 | 2017 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
35019544 | *CANC* ELK HILLS 1104 SPLICE FUSE 19082 | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/30/2019 | ED.25244.1104 | ELK HILLS 1104 | 015 | KERN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 10/20/2017 | 2017 | 11/04/2017 | 2017 | CLSD | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
35019545 | *CANC* ELK HILLS 1104 OH SPLICE SSD1523 | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/30/2019 | ED.25244.1104 | ELK HILLS 1104 | 020 | MADERA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 10/20/2017 | 2017 | 11/04/2017 | 2017 | CLSD | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
35020110 | 2019 08J CC SOLEDAD 1114 S060CC214 | 113747742 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/27/2019 | ED.18205.1114.SWIT | SWITCHES | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 6,896.000 | 0.000 | 08J | 11/07/2017 | 2017 | # | #VALUE! | UNSC | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 207409.56
35020479 | CALIFORNIA 1103 RECOND 380FT INST 2 FUSE | 113813608 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/29/2019 | ED.25228.1103 | CALIFORNIA AVE 1103 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 11/15/2017 | 2017 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
35023586 | R2 RPL OH WIRE ON SPENCE 1123 17-0094873 | 114048528 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/28/2019 | ED.05-I121000000.STRU.POLE | SALINAS I1210 POLES | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 640.000 | 0.000 | 08J | 12/05/2017 | 2017 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
35023620 | *CANC *DO NOT USE* RECONDUCTOR AR W*CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.18282.1101 | MESA 1101 | 040 | SAN LUIS OBISP | 5535457 | DO 08 - Monthly Forecast Only | 11,495.000 | 0.000 | 08J | 12/03/2017 | 2017 | 05/03/2020 | 2020 | CLSD | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
35023687 | R2RPL OH WIRE ON B LOMND 0401 17-0095503 | 114063986 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/28/2019 | ED.08304.0401.RECL | RECLOSERS | 044 | SANTA CRUZ COU | 5535211 | CWSP SPO - SH 08 | 7,590.000 | 7,044.000 | 08W | 12/06/2017 | 2017 | # | #VALUE! | DOCC | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | 35023687_R2RPL OH WIRE ON B LOMND 0401 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 3708946.88
35023873 | *CNCL* REEDLEY 1104 RECON OH SPLICE | 5222754 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/31/2021 | ED.25234.1104 | REEDLEY 1104 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 12/13/2017 | 2017 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 1416.95
35023874 | *CANC*R2 RPL OH WIRE ON SPENCE 1123 17-0 | 114088923 | # | Not assigned | 30 | Technically Completed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/28/2019 | JY | JUNK YARD FL TO HOLD DELETED DATA | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 937.000 | 0.000 | 08J | 12/13/2017 | 2017 | # | #VALUE! | PROD | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 1953.32
35023901 | RECONDUCTOR WILSON 1103 - GERARD AVE. | 114068224 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/27/2019 | ED.25430.1103 | WILSON 1103 | 024 | MERCED COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 12/11/2017 | 2017 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
35024043 | KEARNEY 1104 RECOND 2595FT 6CU | 114105611 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 07/31/2020 | ED.25270.1104 | KEARNEY 1104 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 12/14/2017 | 2017 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 646.54
35024427 | BARRY 1103 RECONDUCTOR | 114127297 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2019 | ED.15211.1103.SWIT | SWITCHES | 051 | SUTTER COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 12/26/2017 | 2017 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 624.49
35024428 | SUMMIT 1101 RECONDUCTOR W TREE WIRE | 114127299 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2019 | ED.15259.1101.SWIT | SWITCHES | 031 | PLACER COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 12/26/2017 | 2017 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 220.19
35024625 | 2019 BRENTWOOD 2112 HIGH SPLICE COUNT | 114143979 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2019 | ED.01459.2112 | BRENTWOOD 2112 | 007 | CONTRA COSTA C | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 01/02/2018 | 2018 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 11840.65
35024645 | S031CC201 - RR2105 RECONDUCT NEAR SW7387 | 113820860 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/30/2019 | ED.08369.2105.SWIT | SWITCHES | 044 | SANTA CRUZ COU | 5535457 | DO 08 - Monthly Forecast Only | 368.000 | 0.000 | 08J | 01/03/2018 | 2018 | # | #VALUE! | CONS | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 8037.72
35024646 | S048CC209 - RR2105 RECONDUCT 9333 ZONE | 113820882 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/30/2019 | JY | JUNK YARD FL TO HOLD DELETED DATA | 044 | SANTA CRUZ COU | 5535457 | DO 08 - Monthly Forecast Only | 2,753.000 | 0.000 | 08J | 01/03/2018 | 2018 | # | #VALUE! | PEND | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 35024646 S048CC209 - RR2105 RECONDUCT 9 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 34695.86
35024647 | RR 2104 RECOND 1051 ZONE W TW | 113820887 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/30/2019 | ED.76-P180300000.STRU.POLE | COAST P1803 POLES | 044 | SANTA CRUZ COU | 5535211 | CWSP SPO - SH 08 | 2,717.000 | 0.000 | 08W | 01/03/2018 | 2018 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 326.51
35024648 | RR2105 RECONDUCTOR NEAR SW 4035 | 113821142 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/30/2019 | ED.76-O172200000.STRU.POLE | COAST O1722 POLES | 044 | SANTA CRUZ COU | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 01/03/2018 | 2018 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 335
35024926 | MARTELL 1101 RECONDCUTOR 3,700FT | 114119281 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/28/2018 | ED.16301.1101 | MARTELL 1101 | 003 | AMADOR COUNTY | 5535211 | CWSP SPO - SH 08 | 4,436.000 | 4,090.000 | 08W | 01/08/2018 | 2018 | # | #VALUE! | MAPP | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 537779.55
35025379 | *CANC*DO NOTUSE*REEDLEY 1110 RECOND*CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/26/2020 | ED.25234.1110 | REEDLEY 1110 | 054 | TULARE COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 01/18/2018 | 2018 | 05/03/2020 | 2020 | CLSD | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
35025961 | PEABODY 2107 PHASE 1 RECOND LINE CO 5527 | 114231251 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/30/2020 | ED.06364.2105.SWIT | SWITCHES | 048 | SOLANO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 01/29/2018 | 2018 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
35025962 | PEABODY 2107 PHASE 2 RECOND LINE CO 5527 | 114231333 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/18/2020 | ED.06364.2105.SWIT | SWITCHES | 048 | SOLANO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 01/29/2018 | 2018 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
35026093 | ALPAUGH 1106 RECOND 7,600 FEET | 114263352 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/26/2020 | ED.25400.1106 | ALPAUGH 1106 | 054 | TULARE COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 02/01/2018 | 2018 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 159.96
35026245 | *CANC*DO NOT USE*R2RPL OH WIRE GON*CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/28/2020 | ED.05-K132500000.STRU.POLE | SALINAS K1325 POLES | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 11,121.000 | 0.000 | 08J | 02/05/2018 | 2018 | 05/03/2020 | 2020 | CLSD | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
35026420 | *CANC*OAKLAND X-1104 OH RECOND SKYLINE | # | # | Not assigned | 40 | Closed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 03/01/2020 | ED.26-F070700000.STRU.POLE | CENTRAL F0707 POLES | 001 | ALAMEDA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 02/08/2018 | 2018 | 08/05/2020 | 2020 | CLSD | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 1912.99
35026643 | RECONDUCTOR DIAMOND SPRINGS 1105 | 114258488 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2019 | ED.15226.1105.SWIT | SWITCHES | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 02/12/2018 | 2018 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 45056.84
35026701 | *CANC*RECONDUCTOR 4901 WITH 397AL. | 114283557 | # | Not assigned | 30 | Technically Completed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 02/07/2019 | ED.18263.1101 | SAN LUIS OBISPO 1101 | 040 | SAN LUIS OBISP | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 02/13/2018 | 2018 | # | #VALUE! | PROD | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 1523.83
35026864 | RECOND GREEN VALLEY 2103 REF# S032CC202 | 114319113 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 06/26/2020 | ED.08319.2103 | GREEN VALLEY 2103 | 044 | SANTA CRUZ COU | 5517128 | DO 49 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 02/17/2018 | 2018 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | RECOND GREEN VALLEY 2103 REF# S032CC202 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 1871.96
35029270 | MORGAN HILL 2111 RECOND 13-SPANS W TW | 114352762 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/30/2020 | ED.08324.2111 | MORGAN HILL 2111 | 043 | SANTA CLARA CO | 5535211 | CWSP SPO - SH 08 | 3,270.000 | 0.000 | 08W | 03/06/2018 | 2018 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 3242.82
35029542 | BIOLA 1104 2019 TARGETED OH REPLACEMENT | 114373073 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/14/2019 | ED.25221.1104 | BIOLA 1104 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 03/09/2018 | 2018 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 241.14
35029543 | REEDLEY 1104 RECONDCUTOR OH SPLICE | 114088517 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/27/2019 | ED.25234.1104 | REEDLEY 1104 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 03/09/2018 | 2018 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
35029545 | DINUBA 1104 RECOND 3,240' OF 6CU/W 2ACSR | 113266252 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/30/2020 | ED.25409.1104 | DINUBA 1104 | 054 | TULARE COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 03/09/2018 | 2018 | # | #VALUE! | PEND | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 15502.94
35029546 | BIOLA 1104 6,350FT TARGET OH REPL | 113241721 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2021 | ED.25221.1104 | BIOLA 1104 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 03/09/2018 | 2018 | # | #VALUE! | ESTS | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 14324.92
35029744 | BIOLA 1104 2019 TARGETED OH REPLACEMENT | # | 35008420 | *CANC*2B CANC BIOLA 1104 2019 TARGE*CANC | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | # | ED.25221.1104 | BIOLA 1104 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 03/13/2018 | 2018 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
35029808 | R2PLOH WIRE ON CASTROVILE2104 18-0016481 | 114408681 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/28/2020 | ED.05-F080600000.STRU.POLE | SALINAS F0806 POLES | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 1,974.000 | 0.000 | 08J | 03/14/2018 | 2018 | # | #VALUE! | PEND | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 9343.58
35029850 | RE-COND 1328FT, CAMBRIA 1101, CAMBRIA | 114372949 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/09/2021 | ED.18277.1101 | CAMBRIA 1101 | 040 | SAN LUIS OBISP | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 03/15/2018 | 2018 | # | #VALUE! | ESTS | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 6057.1
35029942 | REPL 8400' OF ANNEALED 4CU/WYANDOTTE1106 | 113101418 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2019 | ED.10291.1106.RECL | RECLOSERS | 004 | BUTTE COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 03/16/2018 | 2018 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
35030165 | ML2105 RECONDUCTOR - FUSE 9585 | 114425767 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/30/2020 | ED.01430.2105 | MEADOW LANE 2105 | 007 | CONTRA COSTA C | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 03/20/2018 | 2018 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 5026.05
35030422 | RE-CONDUCTOR 1482 FEET SANTA MARIA 1110 | 114437808 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2021 | ED.18267.1110 | SANTA MARIA 1110 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 03/23/2018 | 2018 | # | #VALUE! | ESTS | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 7363.79
35030568 | CWSP HALF MOON BAY 1101 FUCO 4141 | 114435598 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 05/18/2022 | ED.02410.1101 | HALF MOON BAY 1101 | 041 | SAN MATEO COUN | 5535211 | CWSP SPO - SH 08 | 4,690.000 | 0.000 | 08W | 03/28/2018 | 2018 | # | #VALUE! | PEND | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 68131.94
35030621 | ZAMORA 1106 RECONDUCTOR LINE BAD SPLICES | 114435163 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/22/2021 | ED.06319.1106.SWIT | SWITCHES | 057 | YOLO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 03/26/2018 | 2018 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
35030654 | TW ON WOODSIDE1101 N/O 7573 | 114452534 | # | Not assigned | 30 | Technically Completed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/30/2019 | ED.02425.1101 | WOODSIDE 1101 | 041 | SAN MATEO COUN | 5535211 | CWSP SPO - SH 08 | 5,271.000 | 5,271.000 | 08W | 03/30/2018 | 2018 | # | #VALUE! | FICL | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 1790090.01
35031040 | MAPLE CREEK 1101 2020 WIRE DOWN | 114454233 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/17/2021 | ED.19210.1101.SWIT | SWITCHES | 012 | HUMBOLDT COUNT | 5535457 | DO 08 - Monthly Forecast Only | 3,088.000 | 0.000 | 08J | 04/02/2018 | 2018 | # | #VALUE! | PEND | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 26486.11
35031041 | KINGSBURG 1111 RECONDUCTOR 21,880 FEET | 114456033 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.25224.1111 | KINGSBURG 1111 | 054 | TULARE COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 04/02/2018 | 2018 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Kingsburg 1111 Recond 21,880' of #6CU Wi | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 6506.47
35031139 | SHADY GLEN 1102 RECONDUCTOR BEYOND 6343 | 114446685 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2019 | ED.15243.1102.SWIT | SWITCHES | 031 | PLACER COUNTY | 5535211 | CWSP SPO - SH 08 | 7,935.000 | 7,782.000 | 08W | 04/04/2018 | 2018 | 08/08/2020 | 2020 | CLSD | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 2407892.68
35031660 | *CANC* PH 1:REPL 14 000' OF 4AR IN *CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/30/2019 | ED.08202.1106 | LOS GATOS 1106 | 043 | SANTA CLARA CO | 5535211 | CWSP SPO - SH 08 | 14,350.000 | 0.000 | 08W | 04/10/2018 | 2018 | 09/05/2019 | 2019 | CLSD | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35031662 | CWSP - LOS GATOS 1106 - LB44 - PHASE 2.1 | 114474310 | # | Not assigned | 30 | Technically Completed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 08/31/2020 | ED.08202.1106 | LOS GATOS 1106 | 043 | SANTA CLARA CO | 5535211 | CWSP SPO - SH 08 | 2,978.000 | 2,978.000 | 08W | 04/10/2018 | 2018 | # | #VALUE! | FICL | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Los Gatos 1106 - LB44 - Ph 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 750109.71
35031663 | CWSP - LOS GATOS 1106 - LB44 - PHASE 3.1 | 114474316 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 08/31/2020 | ED.08202.1106 | LOS GATOS 1106 | 043 | SANTA CLARA CO | 5535211 | CWSP SPO - SH 08 | 24,000.000 | 0.000 | 08W | 04/10/2018 | 2018 | # | #VALUE! | ESTS | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Los Gatos 1106 - LB44 - Ph 3.1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 43460.11
35031714 | *CANC*DO NOT USE*COTATI 1103 RECOND*CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/01/2021 | ED.04227.1103.SWIT | SWITCHES | 021 | MARIN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 04/12/2018 | 2018 | 05/03/2020 | 2020 | CLSD | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
35032114 | GV2102 RECONDUCTOR WD | 114503633 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/28/2019 | ED.76-P202400000.STRU.POLE | COAST P2024 POLES | 044 | SANTA CRUZ COU | 5535457 | DO 08 - Monthly Forecast Only | 1,173.000 | 0.000 | 08J | 04/18/2018 | 2018 | # | #VALUE! | PEND | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 10631.05
35032266 | APPLE HILL 1104 RECONDUCTOR | 114514465 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2019 | ED.15366.1104.SWIT | SWITCHES | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 877.000 | 877.000 | 08W | 04/18/2018 | 2018 | 05/09/2020 | 2020 | CLSD | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 284268.56
35039002 | OCGC 2018 CALISTOGA 1101 LEVEL 2 DEMO | 114553028 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/31/2018 | ED.04271.1101 | CALISTOGA 1101 | 028 | NAPA COUNTY | 5535211 | CWSP SPO - SH 08 | 6,007.000 | 6,007.000 | 08W | 05/01/2018 | 2018 | 08/15/2020 | 2020 | CLSD | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 1123231.99
35039042 | R2ATWATER 1108 RECONDUCTORING - WIREDOWN | 114558484 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 01/19/2022 | ED.72-06126D0000.STRU.POLE | MERCED MAP 06126D POLES | 024 | MERCED COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 05/02/2018 | 2018 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 3757.48
35039748 | CWSP-MIWUK 1702-LR 38218 | 5381781 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.16366.1702 | MIWUK 1702 | 055 | TUOLUMNE COUNT | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 05/07/2018 | 2018 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 13754.65
35039757 | *CANC* CWSP - BURNS 2101 - OCB - PHASE1 | 5382422 | # | Not assigned | 30 | Technically Completed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/28/2020 | ED.18358.2101.SWIT | SWITCHES | 044 | SANTA CRUZ COU | 5535211 | CWSP SPO - SH 08 | 40,920.000 | 0.000 | 08W | 05/07/2018 | 2018 | # | #VALUE! | PROD | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 3024.03
35039957 | *CANC* CWSP - STANISLAUS 1702 LR18 *CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/20/2020 | ED.16282.1702 | STANISLAUS 1702 | 005 | CALAVERAS COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 05/09/2018 | 2018 | 05/03/2020 | 2020 | CLSD | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35039982 | CWSP: MIWUK 1702_OCB WILDFIRE HARDENING | 5383919 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.16366.1702 | MIWUK 1702 | 055 | TUOLUMNE COUNT | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 05/09/2018 | 2018 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 1523.83
35040016 | *CANC* CWSP-SILVERADO 2104-LR 722 *CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.04343.2104 | SILVERADO 2104 | 028 | NAPA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 05/10/2018 | 2018 | 09/05/2019 | 2019 | CLSD | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35040017 | CWSP - OAK K 1102 OCB LVL 1 HARDENING | # | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.01210.1102 | OAKLAND K 1102 | 001 | ALAMEDA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 05/10/2018 | 2018 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 132064.21
35040018 | CWSP - MORAGA 1101 (VARIOUS) - OCB | # | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.01380.1101 | MORAGA 1101 | 007 | CONTRA COSTA C | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 05/10/2018 | 2018 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 22676.04
35040118 | CWSP: MIWUK 1701_OCB WILDFIRE HARDENING | 5390147 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.16366.1701 | MIWUK 1701 | 055 | TUOLUMNE COUNT | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 05/11/2018 | 2018 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 1954.21
35040225 | HIGGINS 1110 RECONDUCTOR | 114565015 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2019 | ED.15269.1110.SWIT | SWITCHES | 029 | NEVADA COUNTY | 5535211 | CWSP SPO - SH 08 | 8,486.000 | 8,584.000 | 08W | 05/11/2018 | 2018 | 05/23/2020 | 2020 | CLSD | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 2412478.72
35040505 | CWSP - BIG BASIN 1101 - LR 10296 - PH1 | 5395051 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/30/2020 | ED.76-L110300000.STRU.POLE | COAST L1103 POLES | 044 | SANTA CRUZ COU | 5535211 | CWSP SPO - SH 08 | 38,412.000 | 0.000 | 08W | 05/15/2018 | 2018 | # | #VALUE! | ESTS | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 8140.43
35040506 | RR2105 RESILIENCE - 5090 ZONE STEEL & TW | 114607613 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/30/2018 | ED.76-O171200000.STRU.POLE | COAST O1712 POLES | 044 | SANTA CRUZ COU | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 05/15/2018 | 2018 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 2868.14
35040528 | *CANC*RECOND 8-SPANS MILPITAS 1105 *CANC | 114605349 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/28/2018 | ED.08283.1105 | MILPITAS 1105 | 043 | SANTA CLARA CO | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 05/16/2018 | 2018 | 07/04/2018 | 2018 | CLSD | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
35040742 | OCGC - 2018 MONTE RIO 1112 OH TO UG DEMO | 114609098 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2018 | ED.04257.1102.SWIT | SWITCHES | 049 | SONOMA COUNTY | 5535211 | CWSP SPO - SH 08 | 2,578.000 | 2,710.000 | 08W | 05/17/2018 | 2018 | 11/23/2019 | 2019 | CLSD | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 1396819.83
35040961 | CWSP: 2018 K-1102 OH TO UG DEMO | 114610526 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2018 | ED.01210.1102 | OAKLAND K 1102 | 007 | CONTRA COSTA C | 5535211 | CWSP SPO - SH 08 | 3,845.000 | 4,235.000 | 08W | 05/21/2018 | 2018 | 12/28/2019 | 2019 | CLSD | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 772079.48
35041157 | RECONDUCTOR 830FT (5 SPANS) OF 6CU&4AR | 114627165 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 07/31/2020 | ED.10291.1109 | WYANDOTTE 1109 | 004 | BUTTE COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 05/23/2018 | 2018 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 435.35
35041202 | *TRSFR* 35052732 CWSP-BB 1101 - LR *CANC | 5402526 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/30/2020 | ED.76-L110300000.STRU.POLE | COAST L1103 POLES | 044 | SANTA CRUZ COU | 5535211 | CWSP SPO - SH 08 | 32,717.000 | 0.000 | 08W | 05/23/2018 | 2018 | 08/05/2020 | 2020 | CLSD | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 6362.07
35041205 | *CANC* WSP LOS GATOS 1106 LR 60116 PHAS | 5402561 | # | Not assigned | 30 | Technically Completed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/28/2020 | ED.08202.1106.RECL | RECLOSERS | 043 | SANTA CLARA CO | 5535211 | CWSP SPO - SH 08 | 41,184.000 | 0.000 | 08W | 05/23/2018 | 2018 | # | #VALUE! | PROD | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 2386.72
35042350 | RE-CONDUCTOR 279 FT OF 4ACSR WITH 2 CU | 114625720 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/22/2020 | ED.18206.1106 | FAIRWAY 1106 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 05/29/2018 | 2018 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
35042365 | CWSP - CAMP EVERS 2106 - LR 60124 - PH 5 | 114641001 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/01/2020 | ED.08362.2106 | CAMP EVERS 2106 | 044 | SANTA CRUZ COU | 5535211 | CWSP SPO - SH 08 | 47,414.000 | 0.000 | 08W | 05/29/2018 | 2018 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 8089.18
35042366 | CWSP - CAMP EVERS 2106 - 60124 - PHASE 4 | 114640939 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/01/2020 | ED.08362.2106 | CAMP EVERS 2106 | 044 | SANTA CRUZ COU | 5535211 | CWSP SPO - SH 08 | 38,110.000 | 0.000 | 08W | 05/29/2018 | 2018 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 7261.21
35042367 | CWSP - CAMP EVERS 2106 - 60124 - PHASE 3 | 114640938 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/01/2020 | ED.08362.2106 | CAMP EVERS 2106 | 044 | SANTA CRUZ COU | 5535211 | CWSP SPO - SH 08 | 39,389.000 | 0.000 | 08W | 05/29/2018 | 2018 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 22274.16
35042368 | CWSP - CAMP EVERS 2106 - 60124 - PHASE 2 | 114640937 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/01/2020 | ED.08362.2106 | CAMP EVERS 2106 | 044 | SANTA CRUZ COU | 5535211 | CWSP SPO - SH 08 | 38,861.000 | 0.000 | 08W | 05/29/2018 | 2018 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 7726.66
35042369 | CWSP - CAMP EVERS 2106 - 60124 - PHASE 1 | 114640931 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/01/2020 | ED.08362.2106 | CAMP EVERS 2106 | 044 | SANTA CRUZ COU | 5535211 | CWSP SPO - SH 08 | 37,646.000 | 0.000 | 08W | 05/29/2018 | 2018 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 10824.51
35042417 | *TRSFR* 35052727 CWSP LG1106 LR6011*CANC | 5409785 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/28/2020 | ED.08202.1106.RECL | RECLOSERS | 043 | SANTA CLARA CO | 5535211 | CWSP SPO - SH 08 | 33,147.000 | 0.000 | 08W | 05/30/2018 | 2018 | 08/05/2020 | 2020 | CLSD | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 10567.82
35042421 | CWSP - MIWUK 1701 - LR 8050 | 5408388 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.16366.1701 | MIWUK 1701 | 055 | TUOLUMNE COUNT | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 05/29/2018 | 2018 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 14674.01
35042442 | RE-CON 3040 FT OF 4ACSR&1885 6CU W 2CU | 114639867 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 05/29/2020 | ED.18281.1102 | SISQUOC 1102 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 05/29/2018 | 2018 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 215.2
35042445 | RE-COND 5245 FT 4ACSR&3876 FT 6CU W2CU | 114625626 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/22/2020 | ED.18281.1102 | SISQUOC 1102 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 05/29/2018 | 2018 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 1983.28
35042603 | DIAMOND SPRINGS 1103 RECOND 18-0029738 | 114628116 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2019 | ED.15226.1103.SWIT | SWITCHES | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 06/01/2018 | 2018 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35042612 | *CANC* CWSP-ORO FINO 1101 LR-2022 *CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1101 | ORO FINO 1101 | 004 | BUTTE COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 06/01/2018 | 2018 | 05/03/2020 | 2020 | CLSD | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35042631 | *CANC*DO NOT USE* CWSP-VOLTA 1102-L*CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/30/2020 | ED.10254.1102.RECL | RECLOSERS | 045 | SHASTA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 05/31/2018 | 2018 | 05/03/2020 | 2020 | CLSD | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35042647 | *TRSFR* 35052733 CWSP-BB 1101 - LR *CANC | 5411107 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/30/2020 | ED.76-K111800000.STRU.POLE | COAST K1118 POLES | 044 | SANTA CRUZ COU | 5535211 | CWSP SPO - SH 08 | 37,795.000 | 0.000 | 08W | 05/31/2018 | 2018 | 08/05/2020 | 2020 | CLSD | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 3175.9
35042648 | *TRSFR* 35052734 CWSP-CE 2105 - LR *CANC | 5411145 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/30/2020 | ED.76-M131100000.STRU.POLE | COAST M1311 POLES | 044 | SANTA CRUZ COU | 5535211 | CWSP SPO - SH 08 | 39,547.000 | 0.000 | 08W | 05/31/2018 | 2018 | 08/05/2020 | 2020 | CLSD | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 4556.84
35042719 | CWSP-AMGWIN STEEL POLE & TW DEMO PH | 114652824 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/31/2018 | ED.04343.2104 | SILVERADO 2104 | 028 | NAPA COUNTY | 5535211 | CWSP SPO - SH 08 | 2,125.000 | 1,275.000 | 08W | 05/31/2018 | 2018 | 11/07/2020 | 2020 | CLSD | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 1111957.9
35042893 | *CANC* CWSP - BURNS 2101 - OCB - PH*CANC | 5416091 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/30/2020 | ED.18358.2101 | BURNS 2101 | 044 | SANTA CRUZ COU | 5535211 | CWSP SPO - SH 08 | 19,348.000 | 0.000 | 08W | 06/04/2018 | 2018 | 07/03/2020 | 2020 | CLSD | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 3741.17
35042920 | *CANC*DO NOT USE*2020 FAIRHAVEN 110*CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/02/2020 | ED.19245.1103.SWIT | SWITCHES | 012 | HUMBOLDT COUNT | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 06/04/2018 | 2018 | 05/03/2020 | 2020 | CLSD | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
35042921 | *CANC*DO NOT USE*2021 FAIRHAVEN 110*CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/01/2021 | ED.19245.1103.SWIT | SWITCHES | 012 | HUMBOLDT COUNT | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 06/04/2018 | 2018 | 05/03/2020 | 2020 | CLSD | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
35042922 | 2020 EEL RIVER 1102 DET WIRE TABLE BLUFF | 114630202 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/02/2020 | ED.19238.1102.SWIT | SWITCHES | 012 | HUMBOLDT COUNT | 5535457 | DO 08 - Monthly Forecast Only | 5,538.000 | 0.000 | 08J | 06/04/2018 | 2018 | # | #VALUE! | ESTS | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 36138.58
35042923 | *CANC* CWSP-ORO FINO 1101-LR 2022 *CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1101 | ORO FINO 1101 | 004 | BUTTE COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 06/04/2018 | 2018 | 05/03/2020 | 2020 | CLSD | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35043143 | *TRSFR* 35052728 CWSP LG1107 LR6009*CANC | 5418973 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/28/2020 | ED.08202.1107.RECL | RECLOSERS | 043 | SANTA CLARA CO | 5535211 | CWSP SPO - SH 08 | 40,128.000 | 0.000 | 08W | 06/07/2018 | 2018 | 08/05/2020 | 2020 | CLSD | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 10439.21
35043245 | *CANC* CWSP-ORO FINO 1101 OCB PH 1 *CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1101 | ORO FINO 1101 | 004 | BUTTE COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 06/07/2018 | 2018 | 05/03/2020 | 2020 | CLSD | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35043246 | *CANC* CWSP-ORO FINO 1101 OCB PH 2 *CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1101 | ORO FINO 1101 | 004 | BUTTE COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 06/07/2018 | 2018 | 05/03/2020 | 2020 | CLSD | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35043247 | *CANC* CWSP-ORO FINO 1101 OCB PH 3 *CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1101 | ORO FINO 1101 | 004 | BUTTE COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 06/07/2018 | 2018 | 05/03/2020 | 2020 | CLSD | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35043280 | *CANC*DO NOT USE*CWSP-PINE GROVE 11*CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.16375.1102.RECL | RECLOSERS | 003 | AMADOR COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 06/07/2018 | 2018 | 05/03/2020 | 2020 | CLSD | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35043291 | OCGC CWSP- PINE GROVE 1102 LR9145 PH 1.1 | 114631479 | # | Not assigned | 30 | Technically Completed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2019 | JY | JUNK YARD FL TO HOLD DELETED DATA | 003 | AMADOR COUNTY | 5535211 | CWSP SPO - SH 08 | 14,920.000 | 14,872.000 | 08W | 06/07/2018 | 2018 | # | #VALUE! | FICL | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | 35043291_CWSP - PINE GROVE 1102-LR 9145 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 2740328.85
35043296 | WDDB - WILLOW CRK 1103 LR 3090 | 112191208 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/10/2018 | ED.19217.1103.SWIT | SWITCHES | 012 | HUMBOLDT COUNT | 5535211 | CWSP SPO - SH 08 | 6,722.000 | 0.000 | 08W | 06/07/2018 | 2018 | # | #VALUE! | UNSC | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 70268.69
35043299 | CWSP-OH COND RPLC: EEL RIVER 1102 FU1907 | 112402122 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/10/2018 | ED.19238.1102 | EEL RIVER 1102 | 012 | HUMBOLDT COUNT | 5535211 | CWSP SPO - SH 08 | 6,500.000 | 6,376.000 | 08W | 06/07/2018 | 2018 | # | #VALUE! | ESTS | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 1211548.41
35043303 | CWSP-OH COND RPLC: EEL RIVER 1102 FU1909 | 113664014 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/25/2019 | ED.19238.1102 | EEL RIVER 1102 | 012 | HUMBOLDT COUNT | 5535211 | CWSP SPO - SH 08 | 8,003.000 | 8,140.000 | 08W | 06/07/2018 | 2018 | # | #VALUE! | DOCC | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 1499183.34
35043304 | *CANC* 2019 OH COND RPLC: EEL RIVE *CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/25/2019 | ED.35-X050000000.STRU.POLE | FORTUNA X05 POLES | 012 | HUMBOLDT COUNT | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 06/07/2018 | 2018 | 09/05/2019 | 2019 | CLSD | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35043311 | CWSP - MIWUK 1701- LR8060 | 5420388 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.16366.1701 | MIWUK 1701 | 055 | TUOLUMNE COUNT | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 06/08/2018 | 2018 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 13053.23
35043381 | CWSP-MIWUK 1702-LR 6018-PHASE 1 | 5426227 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.16366.1702 | MIWUK 1702 | 055 | TUOLUMNE COUNT | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 06/11/2018 | 2018 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 8240.73
35043384 | CWSP-CURTIS 1705 - TS843 & 10590 | 5426746 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.16335.1705 | CURTIS 1705 | 055 | TUOLUMNE COUNT | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 06/11/2018 | 2018 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 13471.86
35043385 | *CANC* CWSP - TASSAJARA 2112 - FUS *CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2019 | ED.01466.2112 | TASSAJARA 2112 | 007 | CONTRA COSTA C | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 06/11/2018 | 2018 | 10/03/2019 | 2019 | CLSD | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35043421 | CWSP-WEST POINT 1101-OCB&LR12256 PH1.1 | 114676761 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/01/2020 | ED.16320.1101.RECL | RECLOSERS | 003 | AMADOR COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 06/11/2018 | 2018 | # | #VALUE! | ESTS | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - WEST POINT 1101 - LR 12256 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 32559.83
35043422 | CWSP - WEST POINT 1101 -LR 13444- PH 1.1 | 114678720 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/01/2020 | ED.16320.1101.RECL | RECLOSERS | 003 | AMADOR COUNTY | 5535211 | CWSP SPO - SH 08 | 11,926.000 | 0.000 | 08W | 06/11/2018 | 2018 | # | #VALUE! | ESTS | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-WEST POINT 1101-LR 13444-PHASE 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 35766.02
35043423 | CWSP - WEST POINT 1101 -LR 13444- PH 2.1 | 114678726 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/01/2020 | ED.16320.1101.SWIT | SWITCHES | 003 | AMADOR COUNTY | 5535211 | CWSP SPO - SH 08 | 6,563.000 | 0.000 | 08W | 06/11/2018 | 2018 | # | #VALUE! | PEND | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-WEST POINT 1101-LR 13444-PHASE 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 27043.55
35043586 | *CANC* PACIFICA 1102 WD: INS TREE W*CANC | 114612631 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2019 | ED.30-STLT | DIABLO DISTRICT STREETLIGHTS | 041 | SAN MATEO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 06/13/2018 | 2018 | 08/05/2020 | 2020 | CLSD | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35043604 | CWSP - MIWUK 1702 - LR6018 - PHASE 2 | 5429513 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.16366.1702 | MIWUK 1702 | 055 | TUOLUMNE COUNT | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 06/14/2018 | 2018 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 5366.6
35043763 | *CANC* CWSP - MIDDLETOWN 1101-TS 1 *CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/30/2020 | ED.04314.1101.SWIT | SWITCHES | 017 | LAKE COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 06/15/2018 | 2018 | 10/03/2019 | 2019 | CLSD | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35043830 | CWSP - MIRABEL 02 /MONTE RIO 13 - LR 652 | # | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/15/2020 | ED.04209.1102.RECL | RECLOSERS | 049 | SONOMA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 06/15/2018 | 2018 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 15875.77
35043949 | *CANC*DO NOT USE*CWSP-ORO FINO 1102*CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1102 | ORO FINO 1102 | 004 | BUTTE COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 06/20/2018 | 2018 | 05/03/2020 | 2020 | CLSD | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35043950 | CWSP - MIWUK 1701 - LR 10600 | 5435484 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/01/2020 | ED.16366.1701 | MIWUK 1701 | 055 | TUOLUMNE COUNT | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 06/20/2018 | 2018 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 13104.96
35043952 | CWSP - MIWUK 1702 - LR 8090 | 5435485 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.16366.1702 | MIWUK 1702 | 055 | TUOLUMNE COUNT | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 06/20/2018 | 2018 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 5669.86
35043953 | *CANC* CWSP-ORO FINO 1102 LR-2560 *CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1102 | ORO FINO 1102 | 004 | BUTTE COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 06/20/2018 | 2018 | 05/03/2020 | 2020 | CLSD | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35043954 | *CANC*DO NOT USE* CWSP-ORO FINO 110*CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1102 | ORO FINO 1102 | 004 | BUTTE COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 06/20/2018 | 2018 | 05/03/2020 | 2020 | CLSD | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35043955 | *CANC*DO NOT USE* CWSP-ORO FINO 110*CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1102 | ORO FINO 1102 | 004 | BUTTE COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 06/20/2018 | 2018 | 05/03/2020 | 2020 | CLSD | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35043956 | *CANC*DO NOT USE* CWSP-ORO FINO 110*CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1102 | ORO FINO 1102 | 004 | BUTTE COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 06/20/2018 | 2018 | 05/03/2020 | 2020 | CLSD | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35043986 | *CANC*DO NOT USE*CWSP-PINE GROVE 11*CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.16375.1102.RECL | RECLOSERS | 003 | AMADOR COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 06/19/2018 | 2018 | 05/03/2020 | 2020 | CLSD | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35043993 | CWSP - CAMPEVERS2105 - LR 74170 - 4KVPH4 | 114677896 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 11/30/2020 | ED.76-M1202B0000.STRU.POLE | COAST MAP M1202B POLES | 044 | SANTA CRUZ COU | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 06/19/2018 | 2018 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 9195.34
35043994 | CWSP - CAMP EVERS 2105 - LR 11384 ZONE | 114678021 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 11/30/2020 | ED.76-M132300000.STRU.POLE | COAST M1323 POLES | 044 | SANTA CRUZ COU | 5535211 | CWSP SPO - SH 08 | 45,408.000 | 0.000 | 08W | 06/19/2018 | 2018 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 8268.03
35044115 | CWSP - ROB ROY 2105 - LR 5166 | 114712175 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/30/2020 | ED.76-O171100000.STRU.POLE | COAST O1711 POLES | 044 | SANTA CRUZ COU | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 06/19/2018 | 2018 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 7487.87
35044117 | CWSP: LOS GATOS 1107 - LR60092 PH 2 | 114713255 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/29/2020 | ED.08202.1107.RECL | RECLOSERS | 043 | SANTA CLARA CO | 5535211 | CWSP SPO - SH 08 | 46,464.000 | 0.000 | 08W | 06/19/2018 | 2018 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 23320.04
35044284 | *CANC* CWSP-KONOCTI 1102-LR 532 *CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/30/2020 | ED.04331.1102.SWIT | SWITCHES | 017 | LAKE COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 06/21/2018 | 2018 | 09/05/2019 | 2019 | CLSD | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35045959 | *CANC*DO NOT USE* CWSP-ORO FINO 110*CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1101 | ORO FINO 1101 | 004 | BUTTE COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 06/25/2018 | 2018 | 05/03/2020 | 2020 | CLSD | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35046211 | CWSP - GARBERVILLE 1102 HENDRIX PILOT | 114730956 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/25/2019 | ED.19222.1102.SWIT | SWITCHES | 012 | HUMBOLDT COUNT | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 06/27/2018 | 2018 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 22547.14
35046276 | CWSP LOS GATOS 1107-LR60092 PH 3 | 114720357 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/29/2020 | ED.08202.1107.RECL | RECLOSERS | 043 | SANTA CLARA CO | 5535211 | CWSP SPO - SH 08 | 34,320.000 | 0.000 | 08W | 06/27/2018 | 2018 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 13391.61
35046278 | CWSP LOS GATOS 1107-LR60092 PH 4 | 114720429 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/29/2020 | ED.08202.1107.RECL | RECLOSERS | 043 | SANTA CLARA CO | 5535211 | CWSP SPO - SH 08 | 41,615.000 | 0.000 | 08W | 06/27/2018 | 2018 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 1943.01
35046279 | CWSP - LOS GATOS 1107-LR60092 PH 5 | 114720434 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/29/2020 | ED.08202.1107.RECL | RECLOSERS | 043 | SANTA CLARA CO | 5535211 | CWSP SPO - SH 08 | 40,656.000 | 0.000 | 08W | 06/27/2018 | 2018 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 8861.7
35046280 | CWSP - LOS GATOS 1107 - LR60092 PH 6 | 114720436 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/29/2020 | ED.08202.1107.RECL | RECLOSERS | 043 | SANTA CLARA CO | 5535211 | CWSP SPO - SH 08 | 37,294.000 | 0.000 | 08W | 06/27/2018 | 2018 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 3944.54
35046366 | *CANC* CWSP BRUNSWICK 1105 LR-1030*CANC | 5448615 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.15248.1105 | BRUNSWICK 1105 | 029 | NEVADA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 06/28/2018 | 2018 | 06/03/2020 | 2020 | CLSD | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 3845.93
35046371 | ECOP - STANISLAUS 1702 LR 37276 | 114712085 | # | Not assigned | 30 | Technically Completed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/01/2020 | ED.16282.1702 | STANISLAUS 1702 | 005 | CALAVERAS COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 06/28/2018 | 2018 | # | #VALUE! | DCNL | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 54741.1
35046383 | *CANC* CWSP - MIWUK 1701 LR11800 &*CANC | 5449376 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/01/2020 | ED.16366.1701 | MIWUK 1701 | 055 | TUOLUMNE COUNT | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 06/28/2018 | 2018 | 08/06/2019 | 2019 | CLSD | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35046726 | *CANC* CWSP - LOS GATOS 1106 - LB4 *CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/30/2020 | ED.08202.1106 | LOS GATOS 1106 | 043 | SANTA CLARA CO | 5535211 | CWSP SPO - SH 08 | 23,971.000 | 0.000 | 08W | 07/03/2018 | 2018 | 09/05/2019 | 2019 | CLSD | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35046759 | *CANC* CWSP - VOLTA 1102 - LR 1648 *CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.10254.1102.RECL | RECLOSERS | 045 | SHASTA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 07/04/2018 | 2018 | 09/05/2019 | 2019 | CLSD | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35046771 | MAXWELL 1102 RECOND LINE EXCESS SPLICES | 114748560 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/27/2021 | ED.06288.1102.SWIT | SWITCHES | 006 | COLUSA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 07/05/2018 | 2018 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
35046793 | *CANC* CWSP-SALT SPRINGS 2102-LR31 *CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.16369.2102.RECL | RECLOSERS | 005 | CALAVERAS COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 07/06/2018 | 2018 | 07/03/2019 | 2019 | CLSD | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35046896 | *CANC* CWSP - FITCH MOUNTAIN 1113 *CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.04275.1113.RECL | RECLOSERS | 049 | SONOMA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 07/06/2018 | 2018 | 09/05/2019 | 2019 | CLSD | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35047143 | *CANC*DO NOT USE* CWSP - VOLTA 1102*CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | JY | JUNK YARD FL TO HOLD DELETED DATA | 045 | SHASTA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 07/09/2018 | 2018 | 05/03/2020 | 2020 | CLSD | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35047146 | REDBUD 1101 RELOCATE FUSE 4865 IN T*CANC | 114756833 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/28/2018 | ED.04319.1101.SWIT | SWITCHES | 017 | LAKE COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 07/09/2018 | 2018 | 02/06/2020 | 2020 | CLSD | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35047311 | CWSP - CAMP EVERS 2106 - 5020 - PHASE 1 | 114758053 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/30/2020 | ED.08362.2106 | CAMP EVERS 2106 | 044 | SANTA CRUZ COU | 5535211 | CWSP SPO - SH 08 | 46,834.000 | 0.000 | 08W | 07/11/2018 | 2018 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 18211.06
35047312 | *CANC*CWSP-CAMP EVERS 2106 - 5020 P*CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/30/2020 | ED.08362.2106 | CAMP EVERS 2106 | 044 | SANTA CRUZ COU | 5535211 | CWSP SPO - SH 08 | 42,528.000 | 0.000 | 08W | 07/11/2018 | 2018 | 09/05/2019 | 2019 | CLSD | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35047314 | CWSP - CAMPEVERS2105 - LR10294 - 4KV PH1 | 114760861 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/30/2020 | ED.08362.2105.RECL | RECLOSERS | 044 | SANTA CRUZ COU | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 07/11/2018 | 2018 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 7785.31
35047315 | CWSP: CAMPEVERS 2105 - LR11010 - 4KV PH2 | 114760946 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/30/2020 | ED.08362.2105.RECL | RECLOSERS | 044 | SANTA CRUZ COU | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 07/11/2018 | 2018 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 8980.88
35047316 | CWSP - CAMPEVERS2105 - LR 5206 - 4KV PH3 | 114760990 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/30/2020 | ED.08304.0401.RECL | RECLOSERS | 044 | SANTA CRUZ COU | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 07/11/2018 | 2018 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 9809.56
35047317 | CWSP - CAMPEVERS2105 - LR 5300 - 4KV PH7 | 114760995 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/30/2020 | ED.08305.0402.RECL | RECLOSERS | 044 | SANTA CRUZ COU | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 07/11/2018 | 2018 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 4737.11
35047318 | CWSP - CAMPEVERS2105 - BT402CB - 4KV PH6 | 114761016 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/30/2020 | ED.08305.0402.CAPA | CAPACITORS | 044 | SANTA CRUZ COU | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 07/11/2018 | 2018 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 5576.75
35047402 | *CANC* CWSP-SALT SPRINGS 2102-LR31 *CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.16369.2102.RECL | RECLOSERS | 005 | CALAVERAS COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 07/11/2018 | 2018 | 07/03/2019 | 2019 | CLSD | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35047414 | *CANC* CWSP - PARADISE 1106 - OCB *CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2019 | ED.10283.1106.SWIT | SWITCHES | 004 | BUTTE COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 07/11/2018 | 2018 | 09/05/2019 | 2019 | CLSD | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35047418 | *CANC*DO NOT USE* CWSP-EL DORADO PH*CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2019 | ED.15276.2102.SWIT | SWITCHES | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 07/11/2018 | 2018 | 05/03/2020 | 2020 | CLSD | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35047419 | *CANC*CWSP-SHINGLE SPRINGS 2109-LR *CANC | 114742520 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2019 | ED.15365.2109.SWIT | SWITCHES | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 07/11/2018 | 2018 | 07/03/2020 | 2020 | CLSD | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 2474
35047420 | CWSP - BRUNSWICK 1106 - LR 51486 | 114742521 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2019 | ED.15248.1106.SWIT | SWITCHES | 029 | NEVADA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 07/11/2018 | 2018 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 10117.41
35047422 | CWSP - PLACERVILLE 2106 - LR 1104 | 114742525 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2019 | ED.15308.2106.SWIT | SWITCHES | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 07/11/2018 | 2018 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35047429 | CWSP - WILLITS 1104 - LR 34008 PH 1 | 114742614 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2019 | ED.04266.1104.SWIT | SWITCHES | 023 | MENDOCINO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 07/11/2018 | 2018 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 12642.73
35047557 | *CANCEL*CWSP-BRUNSWICK 1105 LR-32536 | # | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.15248.1105 | BRUNSWICK 1105 | 029 | NEVADA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 07/12/2018 | 2018 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 11593.27
35047601 | ECOP-BRUNSWICK 1105-H01-LR32536 ZONE PH2 | 114780214 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.15248.1105 | BRUNSWICK 1105 | 029 | NEVADA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 07/13/2018 | 2018 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 19712.7
35048009 | CWSP - APPLE HILL 2102 LR97982 HARDENING | 114790791 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/16/2020 | ED.15366.2102.RECL | RECLOSERS | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 07/18/2018 | 2018 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35048011 | *CANC* CWSP - EL DORADO PH 2101 LR | # | # | Not assigned | 40 | Closed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.15276.2101.SWIT | SWITCHES | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 07/18/2018 | 2018 | 09/05/2019 | 2019 | CLSD | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35048058 | *CANC* CWSP-COLUMBIA HILL 1101-LR | # | # | Not assigned | 40 | Closed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 11/30/2020 | ED.15247.1101.SWIT | SWITCHES | 029 | NEVADA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 07/19/2018 | 2018 | 09/05/2019 | 2019 | CLSD | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35048278 | STCKTN STATION A 1107 RECONDUCTOR 1 SPAN | 114806289 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/30/2021 | ED.93-V101400000.STRU.POLE | STOCKTON V1014 POLES | 039 | SAN JOAQUIN CO | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 07/20/2018 | 2018 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 1085.38
35048483 | RPL OH COND. SALINAS 1104 18-0056961 | 114809445 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2021 | ED.05-H081400000.STRU.POLE | SALINAS H0814 POLES | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 2,516.000 | 0.000 | 08J | 07/24/2018 | 2018 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 4116.88
35048613 | CWSP - PARADISE 1106 - LR 2084 | 114819461 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.10283.1106 | PARADISE 1106 | 004 | BUTTE COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 07/25/2018 | 2018 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 11828.05
35048675 | REPL ANNEALED COND SON 1105 NAPA RD*CANC | 114971059 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/02/2018 | ED.44-MM35130000.STRU.POLE | SANTA ROSA MM3513 POLES | 049 | SONOMA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 07/25/2018 | 2018 | 12/04/2019 | 2019 | CLSD | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
35048678 | ECOP-BRUNSWICK 1105-H01-LR32536 ZONE PH3 | 114819747 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.15248.1105 | BRUNSWICK 1105 | 029 | NEVADA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 07/25/2018 | 2018 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 14086.07
35049537 | CWSP - BIG BASIN 1102 - 9741 | 114832083 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/30/2020 | ED.08284.1102 | BIG BASIN 1102 | 043 | SANTA CLARA CO | 5535211 | CWSP SPO - SH 08 | 29,386.000 | 0.000 | 08W | 07/31/2018 | 2018 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 5617.41
35049538 | CWSP - BIG BASIN 1102 - 12758 | 114832089 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/30/2020 | ED.08284.1102 | BIG BASIN 1102 | 043 | SANTA CLARA CO | 5535211 | CWSP SPO - SH 08 | 44,088.000 | 0.000 | 08W | 07/31/2018 | 2018 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 8388.56
35049913 | *CANC* CWSP - BRUNSWICK 1103 LR220 | # | # | Not assigned | 40 | Closed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.15248.1103.RECL | RECLOSERS | 029 | NEVADA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 07/29/2018 | 2018 | 09/05/2019 | 2019 | CLSD | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35050942 | CWSP: GARBERVILLE 1101 HENDRIX PILOT | 114848297 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/25/2019 | ED.19222.1101.SWIT | SWITCHES | 012 | HUMBOLDT COUNT | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 08/02/2018 | 2018 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 12111.11
35050945 | CWSP - BRUNSWICK 1106 - 2143 | 114848718 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.15248.1106 | BRUNSWICK 1106 | 029 | NEVADA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 08/02/2018 | 2018 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 8324.37
35050947 | CWSP - BRUNSWICK 1106 - 2794 - PH 1 | 114848737 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.15248.1106 | BRUNSWICK 1106 | 029 | NEVADA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 08/02/2018 | 2018 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 11345.91
35050949 | CWSP - BRUNSWICK 1106 - 2794 - PH 2 | 114848761 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.15248.1106 | BRUNSWICK 1106 | 029 | NEVADA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 08/02/2018 | 2018 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 10092.63
35050950 | CWSP - BRUNSWICK 1106 - 2794 - PH 3 | 114848764 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.15248.1106 | BRUNSWICK 1106 | 029 | NEVADA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 08/02/2018 | 2018 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 5245.58
35050951 | CWSP: MONTE RIO 1113 HENDRIX CABLE | 114848376 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2019 | ED.04281.1113.SWIT | SWITCHES | 049 | SONOMA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 08/02/2018 | 2018 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 22359.67
35051252 | CWSP - PLACERVILLE 2106 - LR 1104 | 114863777 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.15308.2106 | PLACERVILLE 2106 | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 08/08/2018 | 2018 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 65.66
35051253 | R2 RECONDUCT DOLAN RD 1101 WD#16-0065306 | 114838762 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2018 | JY | JUNK YARD FL TO HOLD DELETED DATA | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 2,751.000 | 2,751.000 | 08J | 08/08/2018 | 2018 | # | #VALUE! | DOCC | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 348493.61
35051268 | CWSP - WILLITS 1104 - LR 34008 - PH 2 | 114848768 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.04266.1104 | WILLITS 1104 | 023 | MENDOCINO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 08/07/2018 | 2018 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 12067.32
35051356 | CWSP - EL DORADO PH 2101 LR 26000 PH 2 | 114861944 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.15276.2101.SWIT | SWITCHES | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 08/08/2018 | 2018 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 3785.66
35051472 | CWSP - CAMP EVERS 2106 - LR5020 - PH 3 | 114865601 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/30/2020 | ED.08362.2106 | CAMP EVERS 2106 | 044 | SANTA CRUZ COU | 5532479 | CWSP 08W - Monthly Forecast Only | 38,478.000 | 0.000 | 08W | 08/08/2018 | 2018 | # | #VALUE! | ESTS | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 23388.97
35051484 | CWSP - MONTE RIO 1113 - 8299 | 114779852 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 11/01/2020 | ED.04281.1113.SWIT | SWITCHES | 049 | SONOMA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 08/08/2018 | 2018 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 9762.69
35051485 | CWSP - MONTE RIO 1111 - 1701 | 114779853 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 11/01/2020 | ED.04281.1111.SWIT | SWITCHES | 049 | SONOMA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 08/08/2018 | 2018 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 11084.44
35052117 | ZAMORA 1105 WIRE DOWN LR 36762 | 114870756 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 10/01/2021 | ED.06319.1105.RECL | RECLOSERS | 057 | YOLO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 08/13/2018 | 2018 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
35052121 | *CANC* ZAMORA 1105 WIRE DOWN LR 36762 | # | # | Not assigned | 40 | Closed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 10/01/2021 | ED.06319.1105.RECL | RECLOSERS | 057 | YOLO COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 08/10/2018 | 2018 | 08/25/2018 | 2018 | CLSD | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35052128 | *CANC*DO NOT USE* CWSP-STANISLAUS17*CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.16282.1702 | STANISLAUS 1702 | 005 | CALAVERAS COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 08/10/2018 | 2018 | 05/03/2020 | 2020 | CLSD | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35052129 | *CANC*DO NOT USE*CWSP-STANISLAUS170*CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.16282.1702 | STANISLAUS 1702 | 005 | CALAVERAS COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 08/10/2018 | 2018 | 05/03/2020 | 2020 | CLSD | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35052327 | CWSP-PARADISE 1101 OCB ZONE | 114884306 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.10283.1101 | PARADISE 1101 | 004 | BUTTE COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 08/15/2018 | 2018 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 2807.79
35052328 | CALISTOGA 1101 WIRE DOWN 18-0052856 | 114883275 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.42-FF29000000.STRU.POLE | SILVERADO MAP FF29 POLES | 028 | NAPA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 08/15/2018 | 2018 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 1067.66
35052329 | HIGHWAY 1105 WIRE DOWN 18-0060061 | 114883350 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2021 | ED.42-OO39000000.STRU.POLE | SILVERADO OO39 POLES | 028 | NAPA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 2,809.000 | 0.000 | 08J | 08/15/2018 | 2018 | # | #VALUE! | PEND | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 13406.05
35052718 | OCGC CWSP: ANGWIN OH TO UG DEMO - PH 2 | 114895341 | # | Not assigned | 40 | Closed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2018 | ED.04343.2104 | SILVERADO 2104 | 028 | NAPA COUNTY | 5535211 | CWSP SPO - SH 08 | 2,742.000 | 2,265.000 | 08W | 08/16/2018 | 2018 | 04/26/2020 | 2020 | CLSD | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 904843.05
35052726 | CWSP - LOS GATOS 1106 LR 60116 PH1 | 114623448 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 06/28/2020 | ED.08202.1106.RECL | RECLOSERS | 043 | SANTA CLARA CO | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 08/17/2018 | 2018 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 25702.53
35052727 | CWSP LOS GATOS 1106 LR 1106 PHASE 2 | 114642563 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 06/28/2020 | ED.08202.1106.RECL | RECLOSERS | 043 | SANTA CLARA CO | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 08/17/2018 | 2018 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 7675.84
35052728 | CWSP - LOS GATOS 1107 LR 60092 PH1 | 114670659 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 06/28/2020 | ED.08202.1107.RECL | RECLOSERS | 043 | SANTA CLARA CO | 5535211 | CWSP SPO - SH 08 | 40,128.000 | 0.000 | 08W | 08/17/2018 | 2018 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 11391.71
35052729 | CWSP - BURNS 2101 - PH 1 | 114573040 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 06/28/2020 | ED.18358.2101.SWIT | SWITCHES | 044 | SANTA CRUZ COU | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 08/17/2018 | 2018 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 10587.05
35052730 | CWSP - BURNS 2101- PH 2 | 114661267 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 06/30/2020 | ED.18358.2101 | BURNS 2101 | 044 | SANTA CRUZ COU | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 08/17/2018 | 2018 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 2641.44
35052731 | CWSP - BIG BASIN 1101 - 10296 - PH 1.1 | 114607365 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 09/30/2020 | ED.76-L110300000.STRU.POLE | COAST L1103 POLES | 044 | SANTA CRUZ COU | 5535211 | CWSP SPO - SH 08 | 7,779.000 | 0.000 | 08W | 08/17/2018 | 2018 | # | #VALUE! | UNSC | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BIG BASIN 1101 - LR 10296 - PH1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 127116.36
35052732 | CWSP - BIG BASIN 1101 5028 ZONE | 114623764 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 11/30/2020 | ED.76-L110300000.STRU.POLE | COAST L1103 POLES | 044 | SANTA CRUZ COU | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 08/17/2018 | 2018 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 7839.57
35052733 | CWSP - BIG BASIN 1101 - 10296 ZONE PH2 | 114646897 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 11/30/2020 | ED.76-K111800000.STRU.POLE | COAST K1118 POLES | 044 | SANTA CRUZ COU | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 08/17/2018 | 2018 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 2627.41
35052734 | CWSP - CAMP EVERS 2105 - LR 5232-33542 | 114646899 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 11/30/2020 | ED.76-M131100000.STRU.POLE | COAST M1311 POLES | 044 | SANTA CRUZ COU | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 08/17/2018 | 2018 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 8466.87
35052735 | CWSP - MIWUK 1701 - LR 10600 PH 1.1 | 114706118 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 05/03/2021 | ED.16366.1701 | MIWUK 1701 | 055 | TUOLUMNE COUNT | 5535211 | CWSP SPO - SH 08 | 10,641.000 | 0.000 | 08W | 08/17/2018 | 2018 | # | #VALUE! | UNSC | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - MIWUK 1701 - LR 10600 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 161151.8
35052736 | CWSP - MIWUK 1701 LR11800 | 114708583 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/01/2020 | ED.16366.1701 | MIWUK 1701 | 055 | TUOLUMNE COUNT | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 08/17/2018 | 2018 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-MIWUK 1701 LR11800 & 79118 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 22892.66
35052737 | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 | 114675474 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 07/12/2021 | ED.16366.1701 | MIWUK 1701 | 055 | TUOLUMNE COUNT | 5535211 | CWSP SPO - SH 08 | 8,378.000 | 0.000 | 08W | 08/17/2018 | 2018 | # | #VALUE! | PEND | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | MIWUK 1701 LR8060 08W WILDFIRE HARDENING | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 65909.57
35052738 | CWSP-CURTIS1705-TS843-PHASE1 | 114688224 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.16335.1705 | CURTIS 1705 | 055 | TUOLUMNE COUNT | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 08/17/2018 | 2018 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35052739 | CWSP - MIWUK 1702 - LR 38218 - PH 1.1 | 114567186 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 01/07/2021 | ED.16366.1702 | MIWUK 1702 | 055 | TUOLUMNE COUNT | 5535211 | CWSP SPO - SH 08 | 11,546.000 | 0.000 | 08W | 08/17/2018 | 2018 | # | #VALUE! | CONS | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - MIWUK 1702_LR38218 WILDFIRE HARDE | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 190840.67
35052820 | CWSP - MIWUK 1702 - OCB - PH 1.1 | 114580704 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.16366.1702 | MIWUK 1702 | 055 | TUOLUMNE COUNT | 5535211 | CWSP SPO - SH 08 | 10,392.000 | 10,392.000 | 08W | 08/17/2018 | 2018 | # | #VALUE! | FICL | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - MIWUK 1702_OCB WILDFIRE HARDENING | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 1793038.39
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 | 114593976 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.16366.1701 | MIWUK 1701 | 055 | TUOLUMNE COUNT | 5535211 | CWSP SPO - SH 08 | 10,953.000 | 0.000 | 08W | 08/17/2018 | 2018 | # | #VALUE! | CONS | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - MIWUK 1701_OCB WILDFIRE HARDENING | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 540121.28
35052822 | CWSP - MIWUK 1701 - LR 8050 | 114637561 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.16366.1701 | MIWUK 1701 | 055 | TUOLUMNE COUNT | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 08/17/2018 | 2018 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 597.71
35052823 | CWSP - MIWUK 1702 - LR 6018 - PH 1.1 | 114678857 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.16366.1702 | MIWUK 1702 | 055 | TUOLUMNE COUNT | 5535211 | CWSP SPO - SH 08 | 8,000.000 | 0.000 | 08W | 08/17/2018 | 2018 | # | #VALUE! | UNSC | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - MIWUK 1702-LR 6018-PHASE 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 34884.31
35052824 | CWSP - MIWUK 1702 - LR6018 - PH 2 | 114697826 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.16366.1702 | MIWUK 1702 | 055 | TUOLUMNE COUNT | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 08/17/2018 | 2018 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-MIWUK 1702-LR6018-PHASE 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 225.71
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 | 114701195 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.16366.1702 | MIWUK 1702 | 055 | TUOLUMNE COUNT | 5535211 | CWSP SPO - SH 08 | 6,168.000 | 0.000 | 08W | 08/17/2018 | 2018 | # | #VALUE! | CONS | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-MIWUK 1702-LR 8090 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 430906.29
35052976 | WD-EIGHT MILE2101-CO738931-ILS 180066835 | 114910937 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2021 | ED.16391.2101 | EIGHT MILE 2101 | 039 | SAN JOAQUIN CO | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 08/22/2018 | 2018 | # | #VALUE! | PEND | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 33039.49
35053033 | CWSP - TASSAJARA 2112 - FUSE 18053 | 114688204 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2019 | ED.01466.2112 | TASSAJARA 2112 | 007 | CONTRA COSTA C | 5535211 | CWSP SPO - SH 08 | 31,276.000 | 31,276.000 | 08W | 08/20/2018 | 2018 | # | #VALUE! | CONS | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - TASSAJARA 2112 - FUSE 18053 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 7626876.53
35053154 | PN RECONDUCTOR OVER HWY 101 S/O KEHOE | 114909739 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 02/05/2019 | ED.02401.1104.SWIT | SWITCHES | 041 | SAN MATEO COUN | 5505513 | PN-OH ANNEALED/DETER CNDCTR: PM MGD | 750.000 | 743.000 | 08J | 08/22/2018 | 2018 | 01/11/2020 | 2020 | CLSD | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 229361
35053429 | CWSP HALF MOON BAY 1102 FUCO 12457 | 114921419 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/09/2021 | ED.02410.1102.TXFR.TROH | OVERHEAD TRANSFORMERS | 041 | SAN MATEO COUN | 5535211 | CWSP SPO - SH 08 | 5,597.000 | 0.000 | 08W | 08/28/2018 | 2018 | # | #VALUE! | UNSC | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 87743.47
35053430 | HALF MOON BAY 1101 WIRE REPLACET FCO4141 | 114921459 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2019 | ED.02410.1101.TXFR.TROH | OVERHEAD TRANSFORMERS | 041 | SAN MATEO COUN | 5505513 | PN-OH ANNEALED/DETER CNDCTR: PM MGD | 0.000 | 0.000 | 08J | 08/28/2018 | 2018 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
35053651 | RPL OH COND. SALINAS 1107 18-0066956 | 114921397 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/30/2021 | ED.05-H091000000.STRU.POLE | SALINAS H0910 POLES | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 3,685.000 | 0.000 | 08J | 08/29/2018 | 2018 | # | #VALUE! | PEND | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 35053651 RPL OH COND. SALINAS 1107 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 50357.32
35054184 | CWSP-COLUMBIA HILL 1101-TS 8233 | 114941996 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 11/30/2020 | ED.15247.1101.SWIT | SWITCHES | 029 | NEVADA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 09/05/2018 | 2018 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 3728.88
35054545 | 08J SAN MATEO 2101 WIREDOWN | 114945781 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/29/2019 | ED.02419.2101.TXFR.TROH | OVERHEAD TRANSFORMERS | 041 | SAN MATEO COUN | 5505513 | PN-OH ANNEALED/DETER CNDCTR: PM MGD | 0.000 | 0.000 | 08J | 09/10/2018 | 2018 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 1999.82
35054821 | RPL OH COND.RESERVATION RD.1102 18-69362 | 114946509 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/30/2021 | ED.05-H080000000.STRU.POLE | SALINAS H08 POLES | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 2,830.000 | 0.000 | 08J | 09/12/2018 | 2018 | # | #VALUE! | PEND | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 35054821 RPL OH COND.RESERVATION RD | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 45736.44
35056195 | WD - OCEANO 1102 - 8635 ZONE RECOND | 114988155 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/30/2021 | ED.01-SS35050000.STRU.POLE | SANTA MARIA SS3505 POLES | 040 | SAN LUIS OBISP | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 09/21/2018 | 2018 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 1717.58
35056269 | AIRWAYS 1105-RECOND 1,520 FT OF 2 ACSR | 114982085 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/31/2021 | ED.25204.1105 | AIRWAYS 1105 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 09/19/2018 | 2018 | # | #VALUE! | PEND | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 20930.95
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | 114985530 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.15308.2106 | PLACERVILLE 2106 | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 09/20/2018 | 2018 | # | #VALUE! | ESTS | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Placerville 2106 - LR 1104 - Ph 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 23921.09
35056433 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 2 | 114985551 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.15308.2106 | PLACERVILLE 2106 | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 09/20/2018 | 2018 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Placerville 2106 - LR 1104 - Phas | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 20865.44
35056434 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 3 | 114985557 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.15308.2106 | PLACERVILLE 2106 | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 09/20/2018 | 2018 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-PLACERVILLE 2106 LR1104 PH 3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 16804.36
35056435 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 4 | 114985560 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.15308.2106 | PLACERVILLE 2106 | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 09/20/2018 | 2018 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-PLACERVILLE 2106 LR1104 PH 4 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 17277.46
35056438 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 5 | 114985561 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.15308.2106 | PLACERVILLE 2106 | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 09/20/2018 | 2018 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-PLACERVILLE 2106 LR1104 PH 5 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 12813.39
35056439 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 6 | 114985621 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.15308.2106 | PLACERVILLE 2106 | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 09/20/2018 | 2018 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-PLACERVILLE 2106 LR1104 PH 6 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 11884.89
35056666 | *CANC* EST HILL 1101 LR 50486 HARDENING | # | # | Not assigned | 40 | Closed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 09/20/2020 | ED.15218.1101.RECL | RECLOSERS | 031 | PLACER COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 09/24/2018 | 2018 | 09/29/2018 | 2018 | CLSD | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35056732 | CWSP FOREST HILL 1101 LR 50486 HARDENING | 114988838 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 09/20/2020 | ED.15218.1101.RECL | RECLOSERS | 031 | PLACER COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 09/25/2018 | 2018 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-FOREST HILL 1101 - LR 50486 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 2972.17
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | 114987201 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/30/2020 | ED.15276.2101 | EL DORADO PH 2101 | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 8,064.000 | 0.000 | 08W | 09/25/2018 | 2018 | # | #VALUE! | PEND | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - El Dorado 2101 - 19752 - Ph 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 410049.54
35056746 | CWSP - MIWUK 1701 OCB PHASE 2.1 | 114996821 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/07/2020 | ED.16366.1701 | MIWUK 1701 | 055 | TUOLUMNE COUNT | 5535211 | CWSP SPO - SH 08 | 10,737.000 | 0.000 | 08W | 09/25/2018 | 2018 | # | #VALUE! | CONS | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Miwuk 1701 - OCB Zone - Phase 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 294468.06
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | 114987251 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/30/2020 | ED.15276.2101 | EL DORADO PH 2101 | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 59,373.000 | 0.000 | 08W | 09/26/2018 | 2018 | # | #VALUE! | APPR | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - El Dorado 2101 - LR 19752 - Ph2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 89054.76
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | 114987282 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/30/2020 | ED.15276.2101 | EL DORADO PH 2101 | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 8,673.000 | 9,006.000 | 08W | 09/27/2018 | 2018 | # | #VALUE! | DOCC | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - El Dorado 2101 - LR 19752 - Ph3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 2500136.39
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | 114987363 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/30/2020 | ED.15276.2101 | EL DORADO PH 2101 | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 25,090.000 | 0.000 | 08W | 09/27/2018 | 2018 | # | #VALUE! | PEND | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - El Dorado 2101 - LR 19752 - Ph4 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 421168.34
35057526 | RECOND 460 CKT-FT_CASTRO VALLEY 1106 | 115013270 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/30/2021 | ED.01409.1106 | CASTRO VALLEY 1106 | 001 | ALAMEDA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 10/01/2018 | 2018 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 1151.35
35057802 | CWSP-CAMPEVERS2105 - LR 12590 - 4KV PH5 | 115019871 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 09/30/2021 | ED.76-M122400000.STRU.POLE | COAST M1224 POLES | 044 | SANTA CRUZ COU | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 10/03/2018 | 2018 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Big Trees 0402 - CB Zone - 4kV cu | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 5819.13
35057921 | PUEBLO 2103 RECOND W TW PAST FUSE 2013 | 115025758 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.42-KK36000000.STRU.POLE | SILVERADO MAP KK36 POLES | 028 | NAPA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 10/04/2018 | 2018 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 1329.78
35058026 | CWSP:EL DORADO PH 2101 LR 63464 OH TO UG | 115027447 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2019 | ED.15276.2101.SWIT | SWITCHES | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 10/05/2018 | 2018 | # | #VALUE! | ESTS | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 94224.18
35058060 | SWIFT 2110 - CONDUCTOR REPL | 115029437 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/30/2020 | ED.08339.2110 | SWIFT 2110 | 043 | SANTA CLARA CO | 5535211 | CWSP SPO - SH 08 | 5,430.000 | 0.000 | 08W | 10/05/2018 | 2018 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 6920.91
35058080 | *CANC* X-1104 OH RECOND SKYLINE *CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/01/2020 | ED.26-F070700000.STRU.POLE | CENTRAL F0707 POLES | 001 | ALAMEDA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 10/05/2018 | 2018 | 09/05/2019 | 2019 | CLSD | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35058272 | CWSP- EL DORADO 2101 OCB ZONE PHASE 2 | 114987334 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.21-H470100000.STRU.POLE | EL DORADO H4701 POLES | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 10/08/2018 | 2018 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP- EL DORADO 2101 OCB ZONE PHASE 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 6274.26
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | 114987127 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.21-G460000000.STRU.POLE | EL DORADO G46 POLES | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 6,215.000 | 0.000 | 08W | 10/08/2018 | 2018 | # | #VALUE! | CONS | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 1356466.14
35058723 | BUELLTON 1101 SW8203 REPL 300FT OH LINE | 115004305 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 02/12/2021 | ED.18304.1101.SWIT | SWITCHES | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 10/09/2018 | 2018 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
35058794 | CWSP - APPLE HILL 2102 - 7502 - PHASE 1 | 115036667 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/30/2020 | ED.15366.2102 | APPLE HILL 2102 | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 46,174.000 | 0.000 | 08W | 10/11/2018 | 2018 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Apple Hill 2102 - LR 7502 - Ph1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 6719.55
35058795 | CWSP - APPLE HILL 2102 - 7502 - PHASE 2 | 115036706 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/30/2020 | ED.15366.2102 | APPLE HILL 2102 | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 39,728.000 | 0.000 | 08W | 10/11/2018 | 2018 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Apple Hill 2102 - LR 7502 - Ph2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 3389.45
35058797 | CWSP - APPLE HILL 2102 - 7502 - PHASE 3 | 115036771 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/30/2020 | ED.15366.2102 | APPLE HILL 2102 | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 46,057.000 | 0.000 | 08W | 10/11/2018 | 2018 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Apple Hill 2102 - LR 7502 - Ph3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 4643.1
35058831 | MC KEE 1107 REP 9K FT OH COND WITH 2AR | 115049352 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/30/2021 | ED.08353.1107 | MC KEE 1107 | 043 | SANTA CLARA CO | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 10/10/2018 | 2018 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 4295.54
35058905 | CWSP - VOLTA 1102 - LR 1648 -PH 4.1 | 115038304 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/30/2020 | JY | JUNK YARD FL TO HOLD DELETED DATA | 045 | SHASTA COUNTY | 5535211 | CWSP SPO - SH 08 | 11,306.000 | 11,145.000 | 08W | 10/10/2018 | 2018 | # | #VALUE! | DOCC | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - VOLTA 1102 - LR 1648 -PHASE 4 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 3213075.49
35059696 | ECHO SUMMIT 1101 – REPLACING TREE ATTACH | 115061014 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 08/01/2019 | ED.15803.1101.SWIT | SWITCHES | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 10/18/2018 | 2018 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 753.26
35059716 | HAMMER 1105 RECONDUCTORING - WIREDOWN | 115072890 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.93-T091000000.STRU.POLE | STOCKTON T0910 POLES | 039 | SAN JOAQUIN CO | 5535457 | DO 08 - Monthly Forecast Only | 1,582.000 | 0.000 | 08J | 10/19/2018 | 2018 | # | #VALUE! | APPR | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 26066.03
35060027 | CWSP-PARADISE 1104-TS 1571 | 115079333 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/30/2020 | ED.10283.1104.SWIT | SWITCHES | 004 | BUTTE COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 10/23/2018 | 2018 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 171.99
35060157 | CWSP- HENDRIX DEMO - LIVERMORE TRNG CNTR | 115082086 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2018 | ED.01440.2105 | LAS POSITAS 2105 | 001 | ALAMEDA COUNTY | 5535211 | CWSP SPO - SH 08 | 1,270.000 | 0.000 | 08W | 10/23/2018 | 2018 | 02/29/2020 | 2020 | CLSD | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 318548.64
35060228 | 2019 OH COND RPLC: EEL RIVER 1102 FU1903 | 113663476 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/11/2019 | ED.35-V070000000.STRU.POLE | FORTUNA V07 POLES | 012 | HUMBOLDT COUNT | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 10/24/2018 | 2018 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35060229 | 2018 OH COND RPLC: FRUITLAND 42 C/O 7449 | 112191204 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/10/2018 | ED.19231.1142.SWIT | SWITCHES | 012 | HUMBOLDT COUNT | 5535211 | CWSP SPO - SH 08 | 6,694.000 | 6,271.000 | 08W | 10/24/2018 | 2018 | 09/26/2020 | 2020 | CLSD | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 1962512.65
35060338 | *CANC*DO NOTUSE*2018 OH COND RPLC:E*CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/10/2018 | ED.19233.1104.SWIT | SWITCHES | 012 | HUMBOLDT COUNT | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 10/24/2018 | 2018 | 05/03/2020 | 2020 | CLSD | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
35060383 | WDDB - FRUITLAND 1142CB C/O 1679 | 112190914 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/29/2018 | ED.19231.1142.SWIT | SWITCHES | 012 | HUMBOLDT COUNT | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 10/24/2018 | 2018 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35060387 | WDDB BIG RIVER 1101 FUSE 5187 RECONDUCTO | 112404866 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/10/2018 | ED.04308.1101.SWIT | SWITCHES | 023 | MENDOCINO COUN | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 10/24/2018 | 2018 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
35060580 | *CANC*BIG BEND 1102 - BLOOMER *CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 05/01/2016 | ED.85-CC29000000 | TEHEMA MAP CC29 | 052 | TEHAMA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 10/26/2018 | 2018 | 09/05/2019 | 2019 | CLSD | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35060581 | *CANC* RECONDUCT PT. MORETTI FROM 5043 | 5625029 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/28/2018 | ED.08293.1101 | POINT MORETTI 1101 | 044 | SANTA CRUZ COU | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 10/26/2018 | 2018 | 01/12/2019 | 2019 | CLSD | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | 31272374_RECOND PT MORETTI: 5043 TO 5955 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35060582 | SLO 1107 RECOD 3884 FT WITH 2CU TW | 112640645 | # | Not assigned | 30 | Technically Completed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/01/2017 | ED.18263.1107 | SAN LUIS OBISPO 1107 | 040 | SAN LUIS OBISP | 5535211 | CWSP SPO - SH 08 | 3,884.000 | 3,836.000 | 08W | 10/26/2018 | 2018 | # | #VALUE! | FICL | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 815086.88
35060583 | RECONDUCTOR STOREY 1105 | 112640449 | # | Not assigned | 30 | Technically Completed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/20/2019 | ED.25461.1105 | STOREY 1105 | 020 | MADERA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 3,163.000 | 3,163.000 | 08J | 10/26/2018 | 2018 | # | #VALUE! | FICL | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 31314313_Reconductor Storey 1105 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 153130.6
35060584 | RPL OH WIRE ON OTTER-1101 S030CC121 | 113743255 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 06/28/2019 | ED.07-N031000000.STRU.POLE | MONTEREY N0310 POLES | 027 | MONTEREY COUNT | 5535211 | CWSP SPO - SH 08 | 24,381.000 | 0.000 | 08W | 10/26/2018 | 2018 | # | #VALUE! | PEND | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | RPL OH WIRE OTTER 1101 S030CC121 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 74968.73
35060585 | *CANC* CHOLAME 1101 WD RECONDUCORI *CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2017 | ED.18256.1101 | CHOLAME 1101 | 040 | SAN LUIS OBISP | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 10/26/2018 | 2018 | 09/05/2019 | 2019 | CLSD | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
35060586 | *CANC* RECONDUCTOR 5885 FT ZACA *CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/01/2017 | ED.18268.1102 | ZACA 1102 | 042 | SANTA BARBARA | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 10/26/2018 | 2018 | 09/05/2019 | 2019 | CLSD | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35060587 | *CANC* REPLACE~1.2MILES_MAINLINE_ *CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2016 | ED.18268.1101 | ZACA 1101 | 042 | SANTA BARBARA | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 10/26/2018 | 2018 | 09/05/2019 | 2019 | CLSD | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35060588 | *CANC* RECON 11 SPAN 3313FT 4CU 6 *CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/30/2018 | ED.18310.1104 | CABRILLO 1104 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 10/26/2018 | 2018 | 09/05/2019 | 2019 | CLSD | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
35060893 | RPL OH.CON.SPENCE 1123 18-0074972 | # | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2021 | ED.05-I130000000.STRU.POLE | SALINAS I13 POLES | 027 | MONTEREY COUNT | 5517128 | DO 49 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 10/29/2018 | 2018 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
35060990 | CWSP-BRUNSWICK 1105 LR2140 ZONE-PH3.01 | 115102251 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.15248.1105 | BRUNSWICK 1105 | 029 | NEVADA COUNTY | 5535211 | CWSP SPO - SH 08 | 4,562.000 | 0.000 | 08W | 10/30/2018 | 2018 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Brunswick - 1105 - LR2140 Zone-Ph | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 19609.3
35060991 | CWSP-BRUNSWICK 1105 LR2140 ZONE-PH2.01 | 115101979 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.15248.1105 | BRUNSWICK 1105 | 029 | NEVADA COUNTY | 5535211 | CWSP SPO - SH 08 | 2,465.000 | 0.000 | 08W | 10/30/2018 | 2018 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Brunswick - 1105 - LR2140 Zone-Ph | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 15853.89
35060992 | CWSP-BRUNSWICK 1105 LR2140 ZONE-PH1.01 | 115101918 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.15248.1105 | BRUNSWICK 1105 | 029 | NEVADA COUNTY | 5535211 | CWSP SPO - SH 08 | 2,534.000 | 0.000 | 08W | 10/30/2018 | 2018 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Brunswick - 1105 - LR2140 Zone-Ph | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 35424.29
35060993 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.1 | 115101776 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 04/29/2022 | ED.15248.1105 | BRUNSWICK 1105 | 029 | NEVADA COUNTY | 5535211 | CWSP SPO - SH 08 | 5,545.000 | 0.000 | 08W | 10/30/2018 | 2018 | # | #VALUE! | ESTS | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Brunswick - 1105 - LR2210 Zone-Ph | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 12831.44
35060994 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.1 | 115101557 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.15248.1105 | BRUNSWICK 1105 | 029 | NEVADA COUNTY | 5535211 | CWSP SPO - SH 08 | 5,780.000 | 0.000 | 08W | 10/30/2018 | 2018 | # | #VALUE! | ESTS | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Brunswick - 1105 - LR2210 Zone-Ph | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 33964.52
35060995 | CWSP-BRUNSWICK 1106 LR-2104 ZONE | 115101457 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.15248.1106 | BRUNSWICK 1106 | 029 | NEVADA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 10/30/2018 | 2018 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Brunswick - 1106 - LR2104 Zone | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 1843.09
35061041 | CWSP – MONTE RIO 1112 – TS 15401 | 115099028 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 11/30/2020 | ED.04281.1112.SWIT | SWITCHES | 049 | SONOMA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 10/30/2018 | 2018 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-Monte Rio 1112-TS 15401 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 415.18
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | 115106231 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/02/2020 | ED.15248.1103 | BRUNSWICK 1103 | 029 | NEVADA COUNTY | 5535211 | CWSP SPO - SH 08 | 9,320.000 | 0.000 | 08W | 10/31/2018 | 2018 | # | #VALUE! | CONS | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Brunswick 1103 LR50070 Zone-Ph1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 967230.95
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | 115106486 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 11/06/2020 | ED.15248.1103 | BRUNSWICK 1103 | 029 | NEVADA COUNTY | 5535211 | CWSP SPO - SH 08 | 10,109.000 | 0.000 | 08W | 10/31/2018 | 2018 | # | #VALUE! | CONS | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Brunswick 1103 LR50070 Zone-Ph2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 1342029.94
35061213 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH3 | 115106582 | # | Not assigned | 30 | Technically Completed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 10/15/2020 | ED.15248.1103 | BRUNSWICK 1103 | 029 | NEVADA COUNTY | 5535211 | CWSP SPO - SH 08 | 7,662.000 | 7,702.000 | 08W | 10/31/2018 | 2018 | # | #VALUE! | FICL | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Brunswick 1103 LR50070 Zone-Ph3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 1375943.3
35061709 | SILVERADO 2104 RECONDUCTOR PROJECT | 114521755 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 04/20/2020 | JY | JUNK YARD FL TO HOLD DELETED DATA | 028 | NAPA COUNTY | 5535211 | CWSP SPO - SH 08 | 8,638.000 | 8,003.000 | 08W | 11/06/2018 | 2018 | # | #VALUE! | DOCC | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | SILVERADO 2104 RECONDUCTOR PROJECT | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 4144244.69
35061810 | CWSP - EL DORADO PH 2101 ZONE 19612 | 115217232 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.15276.2101.SWIT | SWITCHES | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 11/07/2018 | 2018 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - El Dorado PH 2101 Zone 19612 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 4565.17
35061811 | CWSP-EL DORADO PH 2102 LR19542 PH 1.1 | 115217237 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.15276.2101.SWIT | SWITCHES | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 11/07/2018 | 2018 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - El Dorado PH 2102 Zone 19542 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 7099.85
35061812 | CWSP - EL DORADO PH 2102 ZONE 6645 | 115221464 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.15276.2101.SWIT | SWITCHES | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 11/07/2018 | 2018 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - El Dorado PH 2102 Zone 6645 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 6487.6
35061985 | 2021 EB WD F-1105 | 115322712 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/30/2021 | ED.28-E041500000.STRU.POLE | BAY E0415 POLES | 001 | ALAMEDA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 11/08/2018 | 2018 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 407.19
35062042 | 2020 ACTON 401 HIGH SPLICE COUNT | 115277939 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 05/20/2020 | ED.02247.0401.SWIT | SWITCHES | 038 | SAN FRANCISCO | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 11/08/2018 | 2018 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 10449.36
35062173 | Cancl FIRE PADSE 1105 INST NOVA BILLE RD | 5650494 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/07/2018 | JY | JUNK YARD FL TO HOLD DELETED DATA | 004 | BUTTE COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 11/12/2018 | 2018 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35062374 | CWSP - SHINGLE SPRINGS 2109-LR 9372-PH1 | 115323920 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.15365.2109 | SHINGLE SPRINGS 2109 | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 11/15/2018 | 2018 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Shingle Springs 2109 LR 9372 Ph1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 25770.74
35062375 | CWSP - SHINGLE SPRINGS 2109-LR 9372-PH2 | 115323921 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.15365.2109 | SHINGLE SPRINGS 2109 | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 11/15/2018 | 2018 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Shingle Springs 2109 LR 9372 Ph2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 4175.32
35062376 | CWSP - SHINGLE SPRINGS 2109-LR 9372-PH3 | 115323922 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.15365.2109 | SHINGLE SPRINGS 2109 | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 11/15/2018 | 2018 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Shingle Springs 2109 LR 9372 Ph3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 1579.86
35064793 | LP RECONDUCTOR, CABRILLO 1104 S006CC102 | 113311784 | # | Not assigned | 30 | Technically Completed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 09/22/2019 | ED.18310.1104 | CABRILLO 1104 | 042 | SANTA BARBARA | 5535211 | CWSP SPO - SH 08 | 17,701.000 | 12,142.000 | 08W | 11/21/2018 | 2018 | # | #VALUE! | FICL | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Cabrillo 1104 Reconductoring | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 2447074.54
35064904 | WOODWARD 2101 RECOND 2520FT TO 1/0AR TW | 115350189 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2021 | ED.25529.2101 | WOODWARD 2101 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 11/26/2018 | 2018 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 3696.1
35065016 | SAN RAFAEL 1103 WIRE DOWN 18-0096220 | 115405199 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/30/2021 | ED.40-TT33130000.STRU.POLE | NORTH BAY MAP TT3313 POLES | 021 | MARIN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 11/26/2018 | 2018 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
35065727 | *CANC* CAMP FIRE SOUTH SKYWAY EXTEN*CANC | 115443100 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/01/2019 | ED.17-T321300000.STRU.POLE | PARADISE T3213 POLES | 004 | BUTTE COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 12/03/2018 | 2018 | 06/03/2020 | 2020 | CLSD | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | GRC Electric Dist | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
35065842 | CWSP-EL DORADO 2101 - LR 26000 - PH3 | 115417043 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.15276.2101.SWIT | SWITCHES | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 12/03/2018 | 2018 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-EL DORADO 2101 - LR 26000 - PH3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 1699.6
35066029 | RPL OH.CON.SPENCE 1102 18-0074972 | 115098143 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.05-I130000000.STRU.POLE | SALINAS I13 POLES | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 12/05/2018 | 2018 | # | #VALUE! | ESTS | E470 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | RPL OH.Con.Spence 112318-0074972 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 44784.05
35066037 | KING CHI ITY 1102 RECONDUCTOR LR7024 EOL | 115107075 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 10/31/2020 | ED.04-Q230000000.STRU.POLE | KING CITY Q23 POLES | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 12/05/2018 | 2018 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 19150.51
35066309 | RE-CONDUCTOR 2309 CIRCUIT FT 4ACSR W 2CU | 115451094 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/06/2021 | ED.06283.1100.RECL | RECLOSERS | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 12/06/2018 | 2018 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 687.8
35066622 | FOOTHILL 1101 LS CO9973 RECONDUCTOR, SLO | 113245749 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/20/2019 | ED.18295.1101.TXFR.TROH | OVERHEAD TRANSFORMERS | 040 | SAN LUIS OBISP | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 12/10/2018 | 2018 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | FOOTHILL 1101 LS CO9973 REPL OH LINE | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 53595.84
35066745 | BIG BEND 1102 - BLOOMER HILL 08W PHS 2 | 108159179 | # | Not assigned | 40 | Closed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 05/01/2016 | ED.85-CC29000000 | TEHEMA MAP CC29 | 052 | TEHAMA COUNTY | 5535211 | CWSP SPO - SH 08 | 8,900.000 | 8,900.000 | 08W | 12/11/2018 | 2018 | 05/09/2020 | 2020 | CLSD | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 3165170.7
35066933 | *CANC*WD - WATSONVILLE 2101 - 11509*CANC | 115492297 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 08/16/2021 | ED.76-Q211000000.STRU.POLE | COAST Q2110 POLES | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 12/13/2018 | 2018 | 01/04/2019 | 2019 | CLSD | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
35067360 | SUISUN 1105 WIRE DOWN DSC 6385 TO 6473 | 115524863 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 10/09/2020 | ED.06213.1105.SWIT | SWITCHES | 048 | SOLANO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 5,976.000 | 0.000 | 08J | 12/17/2018 | 2018 | # | #VALUE! | PEND | E470 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 25362.67
35067449 | RECOND MESA 1103 ALONG CALLE FRESA | 115543440 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/30/2020 | ED.18282.1103 | MESA 1103 | 040 | SAN LUIS OBISP | 5535457 | DO 08 - Monthly Forecast Only | 3,000.000 | 0.000 | 08J | 12/19/2018 | 2018 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 343.89
35067618 | HBPP 01 DETERIORATED CONDUCTOR HUMB HILL | 115482752 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/15/2021 | ED.36-Q062000000.STRU.POLE | EUREKA Q0620 POLES | 012 | HUMBOLDT COUNT | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 12/20/2018 | 2018 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 592.36
35067619 | CWSP – MONTE RIO 1112 – LR 120 | 115098949 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 11/30/2020 | ED.04281.1112.SWIT | SWITCHES | 049 | SONOMA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 12/21/2018 | 2018 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-Monte Rio 1112-LR 120 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 229.01
35067716 | HMB1102 LR60703 REPLACE 400FT OF OH LINE | 115584479 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/26/2020 | ED.02410.1102.RECL | RECLOSERS | 041 | SAN MATEO COUN | 5517127 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 12/21/2018 | 2018 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
35068072 | SAN RAFAEL 1102 WIRE DOWN 18-0107061 | 115606055 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/01/2021 | ED.40-TT33090000.STRU.POLE | NORTH BAY MAP TT3309 POLES | 021 | MARIN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 12/28/2018 | 2018 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 221.54
35068513 | MESA 1103 RECOND 2036 FT W 2CU | 115638264 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 01/03/2020 | ED.18282.1103 | MESA 1103 | 040 | SAN LUIS OBISP | 5535457 | DO 08 - Monthly Forecast Only | 2,036.000 | 0.000 | 08J | 01/03/2019 | 2019 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
35068516 | RECOND 1327FT OF4ACSR,197FT OF 6CU W 2CU | 112835205 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 05/04/2019 | ED.18267.1106 | SANTA MARIA 1106 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 01/04/2019 | 2019 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 30841.86
35068540 | MESA 1103 RECON 4AR WITH 397AL TREE WIRE | 115605923 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/03/2020 | ED.18282.1103 | MESA 1103 | 040 | SAN LUIS OBISP | 5535457 | DO 08 - Monthly Forecast Only | 6,348.000 | 0.000 | 08J | 01/03/2019 | 2019 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 685.32
35068566 | 08J LP FAIRWAY 1103 WIREDOWN 18-0105602 | 115597497 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 05/28/2021 | ED.18206.1103.TXFR.TROH | OVERHEAD TRANSFORMERS | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 01/03/2019 | 2019 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 1049.6
35069872 | WD - GV2104 - 5TH ST WATSONVILLE | 115641286 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 08/27/2021 | ED.76-Q200300000.STRU.POLE | COAST Q2003 POLES | 044 | SANTA CRUZ COU | 5535457 | DO 08 - Monthly Forecast Only | 250.000 | 0.000 | 08J | 01/10/2019 | 2019 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 625.7
35069909 | RPL OH.CON.DOLAN RD. 1101 18-0096302 | 115655197 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/30/2021 | ED.05-D070900000.STRU.POLE | SALINAS D0709 POLES | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 7,535.000 | 0.000 | 08J | 01/10/2019 | 2019 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 35069909_RPL OH.CON.DOLAN RD. 1101 18-00 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 1368.63
35070552 | DIAMOND SPRINGS 1106 RECON BEYOND 2145 | 115637664 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2021 | ED.15226.1106.SWIT | SWITCHES | 009 | EL DORADO COUN | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 01/14/2019 | 2019 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
35071273 | TEMPLETON 2113 RECOND 7622' OF 4AR W 715 | 115700150 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2021 | ED.18305.2113 | TEMPLETON 2113 | 040 | SAN LUIS OBISP | 5535457 | DO 08 - Monthly Forecast Only | 7,622.000 | 0.000 | 08J | 01/18/2019 | 2019 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 821.37
35071495 | RPL OH.CON.RESERVATION RD.1102 18-011072 | 115700424 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/30/2020 | JY | JUNK YARD FL TO HOLD DELETED DATA | 027 | MONTEREY COUNT | 5535211 | CWSP SPO - SH 08 | 6,016.000 | 0.000 | 08W | 01/17/2019 | 2019 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | 35071495_RPL OH.CON.RESERVATION RD.1102 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 840.73
35071765 | RECOND2676 CIRCUIT FT OF 4ACSR W 2CU | 115703224 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2021 | ED.18297.1101 | PURISIMA 1101 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 2,676.000 | 0.000 | 08J | 01/18/2019 | 2019 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
35072062 | RECOND WATS 2101 FUSE 11533 ZONE | 115714387 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/30/2020 | ED.76-Q222300000.STRU.POLE | COAST Q2223 POLES | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 4,380.000 | 0.000 | 08J | 01/22/2019 | 2019 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 816.63
35072140 | RECOND KING CITY 1101 ALONG CANAL ST | 115713604 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/30/2021 | ED.18203.1101 | KING CITY 1101 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 01/23/2019 | 2019 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 6791.61
35072146 | RPL 17,500' 4AR TIER 3 SILVERADO 2105 | 114482701 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2019 | ED.42-GG32250000.STRU.POLE | SILVERADO GG3225 POLES | 028 | NAPA COUNTY | 5535211 | CWSP SPO - SH 08 | 3,666.000 | 3,684.000 | 08W | 01/23/2019 | 2019 | # | #VALUE! | DOCC | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | REPL 17,500' of 4ar & 4cu in Tier 3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 2065251.75
35072147 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.1 | 114474286 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 09/30/2019 | ED.08202.1106 | LOS GATOS 1106 | 043 | SANTA CLARA CO | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 01/23/2019 | 2019 | # | #VALUE! | ESTS | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | PH 1:REPL 14,000' OF 4AR IN TIER 3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 136822.9
35072360 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.1 | 114754229 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.16369.2102.RECL | RECLOSERS | 005 | CALAVERAS COUN | 5535211 | CWSP SPO - SH 08 | 5,541.000 | 0.000 | 08W | 01/24/2019 | 2019 | # | #VALUE! | CONS | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-SALT SPRINGS 2102-LR3142 ZONE-PH 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 1073255.59
35072361 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.1 | 114754228 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.16369.2102.RECL | RECLOSERS | 005 | CALAVERAS COUN | 5535211 | CWSP SPO - SH 08 | 7,709.000 | 0.000 | 08W | 01/24/2019 | 2019 | # | #VALUE! | ADER | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-SALT SPRINGS 2102-LR3142&L491-PHA 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 94589.69
35072362 | CWSP-OH COND RPLC: EEL RIVER 1102 FU1913 | 113676445 | # | Not assigned | 40 | Closed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 10/25/2019 | JY | JUNK YARD FL TO HOLD DELETED DATA | 012 | HUMBOLDT COUNT | 5535211 | CWSP SPO - SH 08 | 13,991.000 | 14,292.000 | 08W | 01/24/2019 | 2019 | 05/31/2020 | 2020 | CLSD | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | 2019 OH COND RPLC: EEL RIVER 1102 FU1913 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 1887115.76
35072363 | *CANC* RECOND 15 298 FT 6CU 4CU & | # | # | Not assigned | 40 | Closed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 10/17/2019 | ED.42-FF30000000.STRU.POLE | SILVERADO FF30 POLES | 028 | NAPA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 01/24/2019 | 2019 | 09/05/2019 | 2019 | CLSD | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | RECONd 15,298 FT 6CU, 4CU & 4AR W 2CU | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35072720 | RPL OH WIRE ON GABILN 1101 17-0077248 | 113646462 | # | Not assigned | 40 | Closed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 06/28/2019 | ED.05-H120700000.STRU.POLE | SALINAS H1207 POLES | 027 | MONTEREY COUNT | 5535211 | CWSP SPO - SH 08 | 11,560.000 | 11,647.000 | 08W | 01/28/2019 | 2019 | 07/25/2020 | 2020 | CLSD | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | RPL OH WIRE ON GABILAN 1101 17-0077248 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 1075018.41
35073059 | SONOMA1104 WIREDOWN | 115768648 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/01/2020 | ED.04272.1104 | SONOMA 1104 | 049 | SONOMA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 01/31/2019 | 2019 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 3724.58
35073637 | LOS GATOS 1107 RECOND FUSE 468855 ZONE | 115783880 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/15/2019 | ED.80-J151200000.STRU.POLE | DE ANZA J1512 POLES | 043 | SANTA CLARA CO | 5535211 | CWSP SPO - SH 08 | 3,730.000 | 0.000 | 08W | 02/04/2019 | 2019 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 415.55
35074009 | ALTO 1124 WIRE DOWN ILIS 18-0109573 | 115826672 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 05/31/2020 | ED.40-UU32120000.STRU.POLE | NORTH BAY MAP UU3212 POLES | 021 | MARIN COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 02/06/2019 | 2019 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35074021 | RECOND-SALINAS 1101 ALONG PRADER ST | 116157204 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/30/2021 | ED.18201.1101 | SALINAS 1101 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 785.000 | 0.000 | 08J | 02/08/2019 | 2019 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
35074388 | RECOND GV2101 FUSE 12347 ZONE | 116157025 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 09/30/2020 | ED.76-O200300000.STRU.POLE | COAST O2003 POLES | 044 | SANTA CRUZ COU | 5535211 | CWSP SPO - SH 08 | 9,970.000 | 0.000 | 08W | 02/08/2019 | 2019 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Recond GV 2101 Fuse 12347 zone | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 1098.96
35075103 | FROGTOWN 1701 - 3115FT RECOND HFTD TIER2 | 116475141 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/30/2020 | ED.16345.1701 | FROGTOWN 1701 | 005 | CALAVERAS COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 02/14/2019 | 2019 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 3720.44
35075135 | 2019 TARAVAL 402 HIGH SPLICE COUNT | 113145837 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2019 | ED.02250.0402 | TARAVAL 0402 | 038 | SAN FRANCISCO | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 02/14/2019 | 2019 | # | #VALUE! | ESTS | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 15406.03
35075136 | REPLACE ~1,100' OH - KING CITY 1106 CKT | 116485471 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/15/2021 | ED.04-R222000000.STRU.POLE | KING CITY R2220 POLES | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 02/14/2019 | 2019 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 1078.1
35075365 | RPL OH.COND.CAMP EVERS 2106 19-0015630 | 116490172 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/30/2020 | ED.76-N110400000.STRU.POLE | COAST N1104 POLES | 044 | SANTA CRUZ COU | 5535211 | CWSP SPO - SH 08 | 1,706.000 | 0.000 | 08W | 02/19/2019 | 2019 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 1511.25
35075591 | SILVERADO 2105 WIRE DOWN PH 1 (CANCEL) | 116505018 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2019 | ED.42-GG32250000.STRU.POLE | SILVERADO GG3225 POLES | 028 | NAPA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 02/20/2019 | 2019 | 05/22/2019 | 2019 | CLSD | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35075594 | SILVERADO 2105 WIRE DOWN PH-2 (CANCEL) | 116505035 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2019 | ED.42-GG32250000.STRU.POLE | SILVERADO GG3225 POLES | 028 | NAPA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 02/20/2019 | 2019 | 05/22/2019 | 2019 | CLSD | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35075647 | SILVERADO 2105 WIRE DOWN PH-3 (CANCEL) | 116505355 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2019 | ED.42-GG32250000.STRU.POLE | SILVERADO GG3225 POLES | 028 | NAPA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 02/20/2019 | 2019 | 05/22/2019 | 2019 | CLSD | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35075650 | SILVERADO 2105 WIRE DOWN PH-4 (CANCEL) | 116505462 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2019 | ED.42-GG32250000.STRU.POLE | SILVERADO GG3225 POLES | 028 | NAPA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 02/20/2019 | 2019 | 05/22/2019 | 2019 | CLSD | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35076062 | *CANC* RECONDUCTOR 17547 FT OF 4AC *CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/27/2020 | ED.18310.1103 | CABRILLO 1103 | 042 | SANTA BARBARA | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 02/25/2019 | 2019 | 10/03/2019 | 2019 | CLSD | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35076064 | *CANC* 14184 FT OF 4ACSR&3363 FT OF 6CU | 114224375 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 01/16/2020 | ED.18310.1103 | CABRILLO 1103 | 042 | SANTA BARBARA | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 02/25/2019 | 2019 | 03/09/2019 | 2019 | CLSD | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35076129 | DIAMOND SPRINGS 1105 RECOND WD18-0105867 | 116489047 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.15226.1105.SWIT | SWITCHES | 009 | EL DORADO COUN | 5784105 | DIAMOND SPRINGS 1105 18-0105867 | 0.000 | 0.000 | 08W | 02/26/2019 | 2019 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | DIAMOND SPRINGS 1105 18-0105867 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35076130 | TAMARACK 1101 WD 19-0011942 | 116489079 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.15229.1101.SWIT | SWITCHES | 029 | NEVADA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 02/26/2019 | 2019 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35076187 | E STOCKTON 402-RECOND 2,800' OF 6CU/W 2A | 113266423 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 01/26/2021 | ED.16313.0402 | EAST STOCKTON 0402 | 039 | SAN JOAQUIN CO | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 02/25/2019 | 2019 | # | #VALUE! | PEND | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 8847.63
35077348 | RECONDUCTOR 17547 FT OF 4ACSR W 2CU TW | 116579004 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 04/27/2020 | ED.18310.1103 | CABRILLO 1103 | 042 | SANTA BARBARA | 5535211 | CWSP SPO - SH 08 | 17,547.000 | 0.000 | 08W | 03/05/2019 | 2019 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | RECONDUCTOR 17547FT 4ACSR W 2CU treewire | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 889.66
35077594 | OROSI 1101 RECOND 1140FT TO 2 ACSR | 116678806 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/29/2021 | ED.25284.1101 | OROSI 1101 | 054 | TULARE COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 03/07/2019 | 2019 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 1026.71
35077853 | *CANC*RECON 3269 FT OF 4ACSR WITH 2*CANC | 116683820 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/30/2021 | ED.18205.2102 | SOLEDAD 2102 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 3,269.000 | 0.000 | 08J | 03/11/2019 | 2019 | 10/03/2020 | 2020 | CLSD | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
35078713 | DIVIDE 1102 RECOND 4780 FT OF 4AR W 2CU | 116720473 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/30/2021 | ED.18257.1102 | DIVIDE 1102 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 4,780.000 | 0.000 | 08J | 03/13/2019 | 2019 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 1232.04
35080227 | CALISTOGA 1101 - BENNETT LN RECONDUCTOR | 116766403 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2019 | ED.04271.1101 | CALISTOGA 1101 | 028 | NAPA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 1,876.000 | 08W | 03/19/2019 | 2019 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 220053.23
35081660 | OH RECONDUCTOR - ROB ROY 2105 -S028CC119 | # | # | Not assigned | 30 | Technically Completed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 09/30/2019 | ED.76-O162000000.STRU.POLE | COAST O1620 POLES | 044 | SANTA CRUZ COU | 5517127 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08W | 03/27/2019 | 2019 | # | #VALUE! | DCNL | E470 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Overhead Reductoring Project | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
35081748 | OH RECONDUCTOR - ROB ROY 2105 -S028CC119 | 113255642 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/30/2019 | JY | JUNK YARD FL TO HOLD DELETED DATA | 044 | SANTA CRUZ COU | 5535211 | CWSP SPO - SH 08 | -1,617.000 | 1,425.000 | 08W | 03/27/2019 | 2019 | 06/20/2020 | 2020 | CLSD | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | 35081748_OH RECONDUCTOR - ROB ROY 2105 - | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 572757.07
35081862 | MARTELL 1101 RECOND. 4ACSR W/ 1/0AR TW | 116833412 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.16301.1101 | MARTELL 1101 | 003 | AMADOR COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 03/28/2019 | 2019 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Martell 1101 Reconductor 8,034ft | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 2886.46
35082181 | WD: PENRYN 1106 19-0028718 RECON 35251 | 116866493 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2021 | ED.15256.1106.SWIT | SWITCHES | 031 | PLACER COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 04/01/2019 | 2019 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
35084277 | PEACHTON 1101 RECON OUTAGE 19-0027596 | 116967241 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 08/31/2021 | ED.10324.1101 | PEACHTON 1101 | 004 | BUTTE COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 04/08/2019 | 2019 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 1003.03
35084460 | MALAGA 1102 - RECON 630FT 4CU WITH 2AR | 116958235 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/15/2021 | ED.25425.1102 | MALAGA 1102 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 04/08/2019 | 2019 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 401.2
35085393 | CWSP - SILVERADO 2104 - LR722 PH 1B | 116951510 | # | Not assigned | 30 | Technically Completed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.04343.2104 | SILVERADO 2104 | 028 | NAPA COUNTY | 5784860 | CWSP Silverado 2104 1B: Underground | 1,871.000 | 1,871.000 | 08W | 04/10/2019 | 2019 | # | #VALUE! | FICL | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - NORTH BAY WILDFIRE HARDENING PROJ | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 1254910.34
35085532 | CWSP - SILVERADO 2104 - LR722 PH 1C | 116951517 | # | Not assigned | 30 | Technically Completed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.04343.2104 | SILVERADO 2104 | 028 | NAPA COUNTY | 5786200 | CWSP - Silverado 2104 - Ph 2 | 5,936.000 | 5,948.000 | 08W | 04/10/2019 | 2019 | # | #VALUE! | FICL | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - NORTH BAY WILDFIRE HARDENING PROJ | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 2038180.58
35085533 | CWSP - SILVERADO 2104 - LR722 PH 1D | 116951595 | # | Not assigned | 30 | Technically Completed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.04343.2104 | SILVERADO 2104 | 028 | NAPA COUNTY | 5535211 | CWSP SPO - SH 08 | 5,365.000 | 5,365.000 | 08W | 04/10/2019 | 2019 | # | #VALUE! | FICL | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - NORTH BAY WILDFIRE HARDENING PROJ | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 1914739.98
35085534 | CWSP - SILVERADO 2104 - LR722 PH 1E | 116951661 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.04343.2104 | SILVERADO 2104 | 028 | NAPA COUNTY | 5535211 | CWSP SPO - SH 08 | 4,191.000 | 4,191.000 | 08W | 04/10/2019 | 2019 | # | #VALUE! | DOCC | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - NORTH BAY WILDFIRE HARDENING PROJ | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 1581062.02
35085535 | CWSP - SILVERADO 2104 - LR722 PH 1F | 116951668 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.04343.2104 | SILVERADO 2104 | 028 | NAPA COUNTY | 5535211 | CWSP SPO - SH 08 | 8,793.000 | 8,793.000 | 08W | 04/10/2019 | 2019 | # | #VALUE! | DOCC | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - NORTH BAY WILDFIRE HARDENING PROJ | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 2489757.73
35085536 | CWSP - SILVERADO 2104 - LR722 PH 1G | 116951730 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.04343.2104 | SILVERADO 2104 | 028 | NAPA COUNTY | 5535211 | CWSP SPO - SH 08 | 6,569.000 | 7,010.000 | 08W | 04/10/2019 | 2019 | # | #VALUE! | DOCC | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - NORTH BAY WILDFIRE HARDENING PROJ | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 1889152.58
35085537 | CWSP - SILVERADO 2104 - LR722 PH 1H | 116951738 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.04343.2104 | SILVERADO 2104 | 028 | NAPA COUNTY | 5535211 | CWSP SPO - SH 08 | 3,442.000 | 3,442.000 | 08W | 04/10/2019 | 2019 | # | #VALUE! | DOCC | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - NORTH BAY WILDFIRE HARDENING PROJ | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 1257493.91
35085538 | SILVERADO 2105 WIRE DOWN - PH 1 | 116952145 | # | Not assigned | 30 | Technically Completed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.04343.2105 | SILVERADO 2105 | 028 | NAPA COUNTY | 5535211 | CWSP SPO - SH 08 | 9,520.000 | 10,413.000 | 08W | 04/10/2019 | 2019 | # | #VALUE! | FICL | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | REPL 17,500' of 4ar & 4cu in Tier 3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 2766019.3
35085539 | SILVERADO 2105 WIRE DOWN - PH 2 | 116952170 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.04343.2105 | SILVERADO 2105 | 028 | NAPA COUNTY | 5535211 | CWSP SPO - SH 08 | 34,020.000 | 34,020.000 | 08W | 04/10/2019 | 2019 | # | #VALUE! | DOCC | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | REPL 17,500' of 4ar & 4cu in Tier 3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 2414483.57
35085680 | SILVERADO 2105 WIRE DOWN - PH 3 | 116952175 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.04343.2105 | SILVERADO 2105 | 028 | NAPA COUNTY | 5535211 | CWSP SPO - SH 08 | 8,756.000 | 0.000 | 08W | 04/10/2019 | 2019 | # | #VALUE! | ESTS | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | REPL 17,500' of 4ar & 4cu in Tier 3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 82651.74
35085681 | SILVERADO 2105 WIRE DOWN - PH 4 | 116952176 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.04343.2105 | SILVERADO 2105 | 028 | NAPA COUNTY | 5535211 | CWSP SPO - SH 08 | 2,894.000 | 2,934.000 | 08W | 04/10/2019 | 2019 | # | #VALUE! | DOCC | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | REPL 17,500' of 4ar & 4cu in Tier 3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 486634.62
35085847 | OH RECONDUCTOR - ROB ROY 2105 -S027CC118 | 113255606 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/30/2019 | ED.76-O171800000.STRU.POLE | COAST O1718 POLES | 044 | SANTA CRUZ COU | 5535211 | CWSP SPO - SH 08 | 4,555.000 | 0.000 | 08W | 04/11/2019 | 2019 | # | #VALUE! | PEND | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | 35085847_R2 OH RECONDUCTR ROB ROY 2105 S | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 62993.86
35086100 | *CANC*DO NOT USE* KINGSBURG 1111 RE*CANC | # | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/18/2020 | ED.25224.1111 | KINGSBURG 1111 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 04/15/2019 | 2019 | 05/03/2020 | 2020 | CLSD | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
35086101 | KINGSBURG 1111 RECOND 4,010' OF 4 CU | 113728913 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/31/2021 | ED.25224.1111 | KINGSBURG 1111 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 04/15/2019 | 2019 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 2556.85
35086535 | DINUBA 1104 RECOND 1,222' OF 1/O TO 2ACS | 112659023 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/31/2021 | ED.25409.1104 | DINUBA 1104 | 054 | TULARE COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 04/17/2019 | 2019 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 951.96
35087416 | RECON7593FT OF 4ACSR W 2CU CABRILLO 1103 | 117043109 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/16/2021 | ED.18310.1103 | CABRILLO 1103 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 7,593.000 | 0.000 | 08J | 04/17/2019 | 2019 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 616.02
35087857 | SM 1105 RECOND 1554 FT 4ACSR W 2CU | 117054562 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/30/2021 | ED.18267.1105 | SANTA MARIA 1105 | 040 | SAN LUIS OBISP | 5535457 | DO 08 - Monthly Forecast Only | 1,554.000 | 0.000 | 08J | 04/19/2019 | 2019 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 1012.51
35087859 | SM 1105 RECOND 2300 FT 4ACSR W 2CU | 117054820 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/30/2021 | ED.18267.1105 | SANTA MARIA 1105 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 2,300.000 | 0.000 | 08J | 04/19/2019 | 2019 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 815.45
35088357 | *CANC* RIO DELL 1101 RECNDTR FUSE 3*CANC | 117051924 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/29/2021 | ED.19225.1101.SWIT | SWITCHES | 012 | HUMBOLDT COUNT | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 04/22/2019 | 2019 | 07/03/2019 | 2019 | CLSD | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
35088462 | RECOND GREEN VALLEY 2103 REF# S029CC120 | 113663707 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/29/2019 | ED.08319.2103 | GREEN VALLEY 2103 | 044 | SANTA CRUZ COU | 5517128 | DO 49 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 04/26/2019 | 2019 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | RECOND GREEN VALLEY 2103 REF# S029CC120 | Base Capital | GRC Distribution Common | GRC | CUSTCARE | Electric Distribution | Electric Distribution | 0
35089227 | BIOLA 1104 RECONDUCTOR 2,995 FT OF 6CU | 117090052 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 07/30/2020 | ED.25221.1104 | BIOLA 1104 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 1,360.000 | 0.000 | 08J | 04/25/2019 | 2019 | # | #VALUE! | PEND | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 33328.13
35089880 | OCGC PIH SILVERADO 2104 - ANGWIN UG_PH 2 | 117092838 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.04343.2104 | SILVERADO 2104 | 028 | NAPA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 2,117.000 | 08W | 04/25/2019 | 2019 | 08/29/2020 | 2020 | CLSD | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 1712851.42
35093737 | FAIRVIEW 2207-CROCKETT BLVD-WIRE DOWN | 117123046 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.01343.2207 | FAIRVIEW 2207 | 007 | CONTRA COSTA C | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 04/30/2019 | 2019 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 560
35094044 | REEDLEY 1106 RECOND 2403FT TO 2AR | 117129391 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/29/2021 | ED.25234.1106 | REEDLEY 1106 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 05/01/2019 | 2019 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
35094388 | CWSP-KONOCTI 1102-LR 532 PH 1 | 117130851 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 11/30/2020 | ED.04331.1102.SWIT | SWITCHES | 017 | LAKE COUNTY | 5535211 | CWSP SPO - SH 08 | 2,241.000 | 2,241.000 | 08W | 05/01/2019 | 2019 | # | #VALUE! | MAPP | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-KONOCTI 1102-LR 532 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 397054.5
35094389 | CWSP-KONOCTI 1102-LR 532 PH 2 | 117130852 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 11/30/2020 | ED.04331.1102.SWIT | SWITCHES | 017 | LAKE COUNTY | 5535211 | CWSP SPO - SH 08 | 2,741.000 | 0.000 | 08W | 05/01/2019 | 2019 | # | #VALUE! | ESTS | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-KONOCTI 1102-LR 532 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 71900.01
35094390 | CWSP-KONOCTI 1102-LR 532 PH 3 | 117130853 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 11/30/2020 | ED.04331.1102.SWIT | SWITCHES | 017 | LAKE COUNTY | 5535211 | CWSP SPO - SH 08 | 2,884.000 | 2,881.000 | 08W | 05/01/2019 | 2019 | # | #VALUE! | DOCC | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-KONOCTI 1102-LR 532 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 878958.2
35094391 | CWSP-KONOCTI 1102-LR 532 PH 4 | 117130854 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 11/30/2020 | ED.04331.1102.SWIT | SWITCHES | 017 | LAKE COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 05/01/2019 | 2019 | # | #VALUE! | UNSC | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-KONOCTI 1102-LR 532 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 21880.49
35094392 | OCGC CWSP-KONOCTI 1102-LR 532 PH 5 | 117130855 | # | Not assigned | 30 | Technically Completed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 11/30/2020 | ED.04331.1102.SWIT | SWITCHES | 017 | LAKE COUNTY | 5535211 | CWSP SPO - SH 08 | 1,956.000 | 1,956.000 | 08W | 05/01/2019 | 2019 | # | #VALUE! | FICL | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-KONOCTI 1102-LR 532 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 263113.32
35094393 | OCGC KONOCTI - 1102 - LR 532 PH 6 (OH) | 117130856 | # | Not assigned | 30 | Technically Completed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 11/30/2020 | ED.04331.1102.SWIT | SWITCHES | 017 | LAKE COUNTY | 5535211 | CWSP SPO - SH 08 | 10,642.000 | 0.000 | 08W | 05/01/2019 | 2019 | # | #VALUE! | FICL | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-KONOCTI 1102-LR 532 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 1299297.67
35094394 | CWSP-KONOCTI 1102-LR 532 PH 7 | 117130857 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 11/30/2020 | ED.04331.1102.SWIT | SWITCHES | 017 | LAKE COUNTY | 5535211 | CWSP SPO - SH 08 | 7,765.000 | 0.000 | 08W | 05/01/2019 | 2019 | # | #VALUE! | CONS | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-KONOCTI 1102-LR 532 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 1193468.64
35094395 | CWSP-KONOCTI 1102-LR 532 PH 8 | 117130858 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 11/30/2020 | ED.04331.1102.SWIT | SWITCHES | 017 | LAKE COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 05/01/2019 | 2019 | # | #VALUE! | ESTS | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-KONOCTI 1102-LR 532 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 55057.57
35094396 | CWSP-KONOCTI 1102-LR 532 PH 9 | 117130859 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 11/30/2020 | ED.04331.1102.SWIT | SWITCHES | 017 | LAKE COUNTY | 5535211 | CWSP SPO - SH 08 | 4,351.000 | 0.000 | 08W | 05/01/2019 | 2019 | # | #VALUE! | UNSC | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-KONOCTI 1102-LR 532 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 25276.49
35094397 | CWSP-KONOCTI 1102-LR 532 PH 10 | 117131100 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 11/30/2020 | ED.04331.1102.SWIT | SWITCHES | 017 | LAKE COUNTY | 5535211 | CWSP SPO - SH 08 | 5,621.000 | 0.000 | 08W | 05/01/2019 | 2019 | # | #VALUE! | CONS | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-KONOCTI 1102-LR 532 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 684703.36
35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 | 114567769 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/20/2021 | ED.16282.1702 | STANISLAUS 1702 | 005 | CALAVERAS COUN | 5535211 | CWSP SPO - SH 08 | 10,124.000 | 0.000 | 08W | 05/03/2019 | 2019 | # | #VALUE! | PEND | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | STANISLAUS 1702 LR1804 ZONE WFH LEVEL 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 139064.69
35094514 | CWSP-ORO FINO 1101 LR-2022 PH 1.1 | 114655579 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1101 | ORO FINO 1101 | 004 | BUTTE COUNTY | 5535211 | CWSP SPO - SH 08 | 6,367.000 | 0.000 | 08W | 05/03/2019 | 2019 | # | #VALUE! | PEND | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - ORO FINO-1101 LR-2022 PH I | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 63943.84
35094515 | CWSP-ORO FINO 1101-LR 2022 PH 2.1 | 114656547 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1101 | ORO FINO 1101 | 004 | BUTTE COUNTY | 5535211 | CWSP SPO - SH 08 | 7,564.000 | 0.000 | 08W | 05/03/2019 | 2019 | # | #VALUE! | ESTS | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - ORO FINO-1101 LR-2022 PH 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 10955.2
35094516 | CWSP-ORO FINO 1101 OCB PH 1.1 | 114668686 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1101 | ORO FINO 1101 | 004 | BUTTE COUNTY | 5535211 | CWSP SPO - SH 08 | 13,173.000 | 0.000 | 08W | 05/03/2019 | 2019 | # | #VALUE! | PEND | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-ORO FINO 1101 OCB PH 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 39163.15
35094517 | CWSP-ORO FINO 1101 OCB PH 2.1 | 114668689 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1101 | ORO FINO 1101 | 004 | BUTTE COUNTY | 5535211 | CWSP SPO - SH 08 | 9,840.000 | 0.000 | 08W | 05/03/2019 | 2019 | # | #VALUE! | PEND | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-ORO FINO 1101 OCB PH 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 67414.27
35094518 | CWSP-ORO FINO 1101 OCB PH 3.1 | 114668862 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1101 | ORO FINO 1101 | 004 | BUTTE COUNTY | 5535211 | CWSP SPO - SH 08 | 11,132.000 | 0.000 | 08W | 05/03/2019 | 2019 | # | #VALUE! | ADER | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-ORO FINO 1101 OCB PH 3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 13414.89
35094519 | CWSP-ORO FINO 1102 LR-2560 PH 1 | 114708278 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1102 | ORO FINO 1102 | 004 | BUTTE COUNTY | 5535211 | CWSP SPO - SH 08 | 9,589.000 | 0.000 | 08W | 05/03/2019 | 2019 | # | #VALUE! | ADER | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-ORO FINO 1102 LR-2560 PH 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 132163.69
35095160 | CWSP-ORO FINO 1102 LR-2560 PH 2.1 | 114708381 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1102 | ORO FINO 1102 | 004 | BUTTE COUNTY | 5535211 | CWSP SPO - SH 08 | 9,226.000 | 0.000 | 08W | 05/03/2019 | 2019 | # | #VALUE! | ADER | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-ORO FINO 1102 LR-2560 PH 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 43112.53
35095161 | CWSP-ORO FINO 1102 LR-76008 PH 1.1 | 114708383 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1102 | ORO FINO 1102 | 004 | BUTTE COUNTY | 5535211 | CWSP SPO - SH 08 | 4,730.000 | 0.000 | 08W | 05/03/2019 | 2019 | # | #VALUE! | PEND | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-ORO FINO 1102 LR-76008 PH 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 100820.79
35095162 | CWSP-ORO FINO 1102 LR-76008 PH 2.1 | 114708386 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1102 | ORO FINO 1102 | 004 | BUTTE COUNTY | 5535211 | CWSP SPO - SH 08 | 6,960.000 | 0.000 | 08W | 05/03/2019 | 2019 | # | #VALUE! | ESTS | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-ORO FINO 1102 LR-76008 PH 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 127890.51
35095163 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.1 | 114708366 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.16375.1102.SWIT | SWITCHES | 003 | AMADOR COUNTY | 5535211 | CWSP SPO - SH 08 | 7,554.000 | 0.000 | 08W | 05/03/2019 | 2019 | # | #VALUE! | ADER | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP: PINE GROVE 1102 LR1222 ZONE WFH PH | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 61815.48
35095164 | CWSP-ORO FINO 1101 LR-2022 PH 3.1 | 114723712 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1101 | ORO FINO 1101 | 004 | BUTTE COUNTY | 5535211 | CWSP SPO - SH 08 | 10,229.000 | 0.000 | 08W | 05/03/2019 | 2019 | # | #VALUE! | UNSC | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-ORO FINO 1101 LR-2022 PH 3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 184680.49
35095165 | CWSP - VOLTA 1102 - LR 1648 -PH 3.1 | 114761296 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | JY | JUNK YARD FL TO HOLD DELETED DATA | 045 | SHASTA COUNTY | 5535211 | CWSP SPO - SH 08 | 3,843.000 | 3,666.000 | 08W | 05/03/2019 | 2019 | # | #VALUE! | DOCC | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - VOLTA 1102 - LR 1648 -PHASE 3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 3095085.26
35095166 | CWSP - EL DORADO 2102 - LR19562 - PH 1.0 | 114742467 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2019 | ED.15276.2102.SWIT | SWITCHES | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 7,328.000 | 7,419.000 | 08W | 05/03/2019 | 2019 | # | #VALUE! | DOCC | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - EL DORADO PH 2102 - LR 19562 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 1317588.18
35095167 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.1 | 114832579 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.16282.1702 | STANISLAUS 1702 | 005 | CALAVERAS COUN | 5535211 | CWSP SPO - SH 08 | 5,899.000 | 0.000 | 08W | 05/03/2019 | 2019 | # | #VALUE! | PEND | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-STANISLAUS1702-LR1888-PH2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 135741.9
35095168 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.1 | 114832575 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.16282.1702 | STANISLAUS 1702 | 005 | CALAVERAS COUN | 5535211 | CWSP SPO - SH 08 | 6,718.000 | 0.000 | 08W | 05/03/2019 | 2019 | # | #VALUE! | PEND | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-STANISLAUS1702-LR1888-PH1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 206660.33
35095246 | BUCOCAMP - ERIKA DRIVE, PARADISE | 117164122 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/27/2019 | JY | JUNK YARD FL TO HOLD DELETED DATA | 004 | BUTTE COUNTY | 5786123 | 08W Rebuild | 0.000 | 0.000 | 08W | 05/05/2019 | 2019 | # | #VALUE! | PEND | E460 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 136580.24
35098578 | CWSP-COLUMBIA HILL 1101-LR 2212 PH2 | 117177287 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 11/19/2019 | ED.15247.1101.SWIT | SWITCHES | 029 | NEVADA COUNTY | 5535211 | CWSP SPO - SH 08 | 9,457.000 | 9,470.000 | 08W | 05/08/2019 | 2019 | # | #VALUE! | DOCC | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-COLUMBIA HILL 1101-LR 2212 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 3489548.87
35098579 | CWSP-COLUMBIA HILL 1101-LR 2212 PH3 | 117177288 | # | Not assigned | 40 | Closed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 10/07/2019 | ED.15247.1101.SWIT | SWITCHES | 029 | NEVADA COUNTY | 5535211 | CWSP SPO - SH 08 | 7,417.000 | 7,573.000 | 08W | 05/08/2019 | 2019 | 11/21/2020 | 2020 | CLSD | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-COLUMBIA HILL 1101-LR 2212 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 1955970.91
35098621 | CWSP-COLUMBIA HILL 1101-LR 2212 PH4 | 117177530 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 11/30/2020 | ED.15247.1101.SWIT | SWITCHES | 029 | NEVADA COUNTY | 5535211 | CWSP SPO - SH 08 | 5,642.000 | 5,706.000 | 08W | 05/08/2019 | 2019 | # | #VALUE! | CONS | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-COLUMBIA HILL 1101-LR 2212 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 1003972.02
35098622 | CWSP-COLUMBIA HILL 1101-LR 2212 PH5 | 117177533 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 11/25/2019 | ED.15247.1101.SWIT | SWITCHES | 029 | NEVADA COUNTY | 5535211 | CWSP SPO - SH 08 | 12,854.000 | 13,101.000 | 08W | 05/08/2019 | 2019 | # | #VALUE! | DOCC | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-COLUMBIA HILL 1101-LR 2212 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 3808676.32
35098747 | SHEPHERD 2109 RECOND 3,780FT WITH 4/O AL | 117183017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/29/2021 | ED.25206.2109 | SHEPHERD 2109 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 05/09/2019 | 2019 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 2855.51
35099603 | MORRO BAY 1102 RECON 4728 FT W TW | 117211021 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/13/2020 | ED.18301.1102 | MORRO BAY 1102 | 040 | SAN LUIS OBISP | 5535211 | CWSP SPO - SH 08 | 4,728.000 | 0.000 | 08W | 05/10/2019 | 2019 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35099654 | BR-04-01-W (E) SUNSET DR PARB | 117212284 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/27/2019 | ED.17-S332200000.STRU.POLE | PARADISE S3322 POLES | 004 | BUTTE COUNTY | 5786123 | 08W Rebuild | 0.000 | 0.000 | 08W | 05/11/2019 | 2019 | # | #VALUE! | DOCC | E470 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 589661.72
35100323 | GRAND ISLAND 2226 RECOND 2600 FEET OF OH | 113062127 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.06246.2226.SWIT | SWITCHES | 048 | SOLANO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 2,242.000 | 0.000 | 08J | 05/14/2019 | 2019 | # | #VALUE! | CONS | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 42068.92
35101875 | BR-01-10-W (E) BILLIE & LUCKY JOHN PARB | 117243977 | # | Not assigned | 30 | Technically Completed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/27/2019 | JY | JUNK YARD FL TO HOLD DELETED DATA | 004 | BUTTE COUNTY | 5786123 | 08W Rebuild | 0.000 | 0.000 | 08W | 05/15/2019 | 2019 | # | #VALUE! | FICL | E460 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 1062109.83
35101876 | BR-01-08-W (E) MADRONE_BILLE_GRAHAM PARB | 117244453 | # | Not assigned | 30 | Technically Completed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/27/2019 | JY | JUNK YARD FL TO HOLD DELETED DATA | 004 | BUTTE COUNTY | 5786123 | 08W Rebuild | 3,407.000 | 0.000 | 08W | 05/15/2019 | 2019 | # | #VALUE! | FICL | E460 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 1055029.06
35101877 | BR-01-06-W (E) THOMASSON LN PARB | 117244755 | # | Not assigned | 30 | Technically Completed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/27/2019 | ED.17-S331800000.STRU.POLE | PARADISE S3318 POLES | 004 | BUTTE COUNTY | 5786123 | 08W Rebuild | 6,358.000 | 0.000 | 08W | 05/15/2019 | 2019 | # | #VALUE! | FICL | E460 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 2341077.4
35103065 | CWSP - MORAGA 1101 - LR 108540 PH 1 | 114592041 | # | Not assigned | 30 | Technically Completed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/18/2019 | ED.01380.1101 | MORAGA 1101 | 007 | CONTRA COSTA C | 5535211 | CWSP SPO - SH 08 | 12,588.000 | 12,151.000 | 08W | 05/16/2019 | 2019 | # | #VALUE! | FICL | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - MORAGA 1101 (VARIOUS) - OCB | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 4790991.91
35103323 | CWSP - MORAGA 1101 - LR 108540 - PH 2 | 117251172 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.01380.1101 | MORAGA 1101 | 007 | CONTRA COSTA C | 5535211 | CWSP SPO - SH 08 | 6,489.000 | 5,368.000 | 08W | 05/17/2019 | 2019 | # | #VALUE! | DOCC | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - MORAGA 1101 (VARIOUS) - OCB | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 3091248.54
35103324 | CWSP - ROSSMOOR 1102 - OCB | 117251430 | # | Not assigned | 35 | Pre-Closed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.01416.1102 | ROSSMOOR 1102 | 007 | CONTRA COSTA C | 5535211 | CWSP SPO - SH 08 | 4,046.000 | 4,046.000 | 08W | 05/17/2019 | 2019 | # | #VALUE! | PREC | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - MORAGA 1101 (VARIOUS) - OCB | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 2335945.42
35103325 | CWSP - MORAGA 1102 & 1104 - OCB | 117252070 | # | Not assigned | 30 | Technically Completed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 04/14/2020 | ED.01380.1102 | MORAGA 1102 | 007 | CONTRA COSTA C | 5535211 | CWSP SPO - SH 08 | 6,506.000 | 6,916.000 | 08W | 05/17/2019 | 2019 | # | #VALUE! | FICL | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - MORAGA 1101 (VARIOUS) - OCB | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 4605839.19
35103617 | BR-07-09-W (E) WOODGLEN PARB | 117281820 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/27/2019 | JY | JUNK YARD FL TO HOLD DELETED DATA | 004 | BUTTE COUNTY | 5786123 | 08W Rebuild | 0.000 | 0.000 | 08W | 05/20/2019 | 2019 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35103619 | BR-10-03-W (E) FILBERT PARB | 117287031 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/27/2019 | ED.17-T321500000.STRU.POLE | PARADISE T3215 POLES | 004 | BUTTE COUNTY | 5786123 | 08W Rebuild | 0.000 | 0.000 | 08W | 05/20/2019 | 2019 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35103942 | BR-09-03-W (E) CONNIE CIR PARB | 117288421 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/27/2019 | ED.17-T321000000.STRU.POLE | PARADISE T3210 POLES | 004 | BUTTE COUNTY | 5786123 | 08W Rebuild | 0.000 | 0.000 | 08W | 05/20/2019 | 2019 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35104252 | BR-05-05-W (E) CENTRAL PARK PARB | 117292725 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/27/2019 | ED.17-T330300000.STRU.POLE | PARADISE T3303 POLES | 004 | BUTTE COUNTY | 5786123 | 08W Rebuild | 0.000 | 0.000 | 08W | 05/21/2019 | 2019 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35105559 | RE-CON 7128 FT OF 4ACSR W 4/0 AL | 117291692 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/21/2021 | ED.18304.1101 | BUELLTON 1101 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 7,128.000 | 0.000 | 08J | 05/22/2019 | 2019 | # | #VALUE! | ESTS | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 3815.04
35105573 | 2021 RIO DELL 1101 RECONDUCTOR FUSE 3445 | 117303760 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 10/29/2021 | ED.19225.1101.SWIT | SWITCHES | 012 | HUMBOLDT COUNT | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 05/22/2019 | 2019 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 214.68
35105646 | BR-03-05-W (E) DEAN RD, PARB | 117306439 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/27/2019 | ED.17-S341300000.STRU.POLE | PARADISE S3413 POLES | 004 | BUTTE COUNTY | 5786123 | 08W Rebuild | 0.000 | 0.000 | 08W | 05/23/2019 | 2019 | # | #VALUE! | CONS | E470 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 636269.07
35105647 | BR-03-09-W (E) MERRILL RD PARB | 117306975 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/27/2019 | ED.17-S341800000.STRU.POLE | PARADISE S3418 POLES | 004 | BUTTE COUNTY | 5786123 | 08W Rebuild | 0.000 | 0.000 | 08W | 05/23/2019 | 2019 | # | #VALUE! | CONS | E470 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 1698863.77
35105649 | BR-14-02-W (E) DRENDEL PARB | 117307198 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/27/2019 | ED.17-T341400000.STRU.POLE | PARADISE T3414 POLES | 004 | BUTTE COUNTY | 5786123 | 08W Rebuild | 0.000 | 0.000 | 08W | 05/23/2019 | 2019 | # | #VALUE! | DOCC | E470 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 857010.04
35105650 | BR-08-06-W (E) FICKETT LN PARB | 117307360 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/27/2019 | JY | JUNK YARD FL TO HOLD DELETED DATA | 004 | BUTTE COUNTY | 5786123 | 08W Rebuild | 0.000 | 0.000 | 08W | 05/23/2019 | 2019 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 210069.63
35105653 | BR-14-01-W (E) SALIDA WAY, PARB | 117307657 | 35127553 | BR-14-01-O (E) SALIDA WAY PARB | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/27/2019 | ED.17-T341300000.STRU.POLE | PARADISE T3413 POLES | 004 | BUTTE COUNTY | 5786123 | 08W Rebuild | 0.000 | 0.000 | 08W | 05/23/2019 | 2019 | # | #VALUE! | PEND | E470 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 392832.02
35105656 | BR-04-02-W (E) CASTLE DR PARB | 117308283 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/27/2019 | JY | JUNK YARD FL TO HOLD DELETED DATA | 004 | BUTTE COUNTY | 5786123 | 08W Rebuild | 0.000 | 0.000 | 08W | 05/23/2019 | 2019 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 13772.21
35106042 | CWSP - VOLTA 1102 - LR 1648 - PH1.2 | 117316187 | # | Not assigned | 30 | Technically Completed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | JY | JUNK YARD FL TO HOLD DELETED DATA | 045 | SHASTA COUNTY | 5535211 | CWSP SPO - SH 08 | 9,606.000 | 9,607.000 | 08W | 05/24/2019 | 2019 | # | #VALUE! | FICL | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Volta 1102 - LR 1648 - Ph1.1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 1481678.96
35106067 | REPLC WIRE-CASTROVILLE2104 WD#19-0048862 | 117310755 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/30/2021 | ED.18235.2104 | CASTROVILLE 2104 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 5,895.000 | 0.000 | 08J | 05/24/2019 | 2019 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 401.38
35106265 | CWSP - VOLTA 1102 - LR 1648 - PH1.3 | 117316465 | # | Not assigned | 30 | Technically Completed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | JY | JUNK YARD FL TO HOLD DELETED DATA | 045 | SHASTA COUNTY | 5535211 | CWSP SPO - SH 08 | 10,118.000 | 9,489.000 | 08W | 05/28/2019 | 2019 | # | #VALUE! | FICL | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Volta 1102 - LR 1648 - Ph1.1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 1132079.03
35106267 | WEST FRESNO 1101 RECOND 1,410FT WITH 2AR | 117328156 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/29/2021 | ED.25373.1101 | WEST FRESNO 1101 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 05/28/2019 | 2019 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 2596.7
35106331 | CWSP - VOLTA 1102 - LR 1648 - PH1.4 | 117316591 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.87-Q421500000.STRU.POLE | SHASTA Q4215 POLES | 045 | SHASTA COUNTY | 5535211 | CWSP SPO - SH 08 | 12,968.000 | 13,119.000 | 08W | 05/28/2019 | 2019 | # | #VALUE! | DOCC | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Volta 1102 - LR 1648 - Ph1.1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 2815980.85
35107688 | CWSP - VOLTA 1102 - LR 1648 -PH1.1 | 114645026 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/30/2020 | ED.10254.1102.RECL | RECLOSERS | 045 | SHASTA COUNTY | 5535211 | CWSP SPO - SH 08 | 8,626.000 | 8,610.000 | 08W | 05/29/2019 | 2019 | # | #VALUE! | DOCC | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Volta 1102 - LR 1648 - Ph1.1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 1544112.04
35107689 | OCGC CWSP - PINE GROVE 1102 - LR1222 - | 114660964 | # | Not assigned | 30 | Technically Completed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.16375.1102.RECL | RECLOSERS | 003 | AMADOR COUNTY | 5535211 | CWSP SPO - SH 08 | 10,648.000 | 11,292.000 | 08W | 05/30/2019 | 2019 | # | #VALUE! | FICL | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP: PINE GROVE 1102 LR1222 PH 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 2565589.03
35107837 | WD-WATERLOO 1102 -OCB Z -ILIS 190050626 | 117336260 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2021 | ED.93-T120000000.STRU.POLE | STOCKTON T12 POLES | 039 | SAN JOAQUIN CO | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 05/29/2019 | 2019 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | 117348505 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/30/2020 | ED.15276.2101 | EL DORADO PH 2101 | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 7,492.000 | 7,214.000 | 08W | 06/03/2019 | 2019 | # | #VALUE! | DOCC | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - El Dorado 2101 - 19752 - Ph 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 1628439.37
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | 117348508 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/30/2020 | ED.15276.2101 | EL DORADO PH 2101 | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 14,086.000 | 0.000 | 08W | 06/03/2019 | 2019 | # | #VALUE! | ESTS | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - El Dorado 2101 - 19752 - Ph 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 49210.61
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | 117349210 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/30/2020 | ED.15276.2101 | EL DORADO PH 2101 | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 9,526.000 | 9,673.000 | 08W | 06/03/2019 | 2019 | # | #VALUE! | DOCC | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - El Dorado 2101 - 19752 - Ph 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 1657539
35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | 117349211 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/30/2020 | ED.15276.2101 | EL DORADO PH 2101 | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 9,506.000 | 8,922.000 | 08W | 06/03/2019 | 2019 | # | #VALUE! | DOCC | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - El Dorado 2101 - 19752 - Ph 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 2454750.14
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | 117349070 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/30/2020 | ED.15276.2101 | EL DORADO PH 2101 | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 12,857.000 | 12,784.000 | 08W | 06/03/2019 | 2019 | # | #VALUE! | DOCC | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - El Dorado 2101 - LR 19752 - Ph2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 3091071.49
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | 117349071 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/30/2020 | ED.15276.2101 | EL DORADO PH 2101 | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 14,639.000 | 0.000 | 08W | 06/03/2019 | 2019 | # | #VALUE! | ADER | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - El Dorado 2101 - LR 19752 - Ph2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 158419.13
35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | 117349072 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/30/2020 | ED.15276.2101 | EL DORADO PH 2101 | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 7,660.000 | 8,100.000 | 08W | 06/03/2019 | 2019 | # | #VALUE! | DOCC | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - El Dorado 2101 - LR 19752 - Ph2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 2741271.64
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | 117349073 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/30/2020 | ED.15276.2101 | EL DORADO PH 2101 | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 15,944.000 | 15,069.000 | 08W | 06/03/2019 | 2019 | # | #VALUE! | DOCC | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - El Dorado 2101 - LR 19752 - Ph2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 3215549.07
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | 117348822 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/30/2020 | ED.15276.2101 | EL DORADO PH 2101 | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 6,933.000 | 7,069.000 | 08W | 06/03/2019 | 2019 | # | #VALUE! | DOCC | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - El Dorado 2101 - LR 19752 - Ph3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 2243211.21
35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | 117348823 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/30/2020 | ED.15276.2101 | EL DORADO PH 2101 | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 9,563.000 | 10,305.000 | 08W | 06/03/2019 | 2019 | # | #VALUE! | DOCC | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - El Dorado 2101 - LR 19752 - Ph3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 2664478.22
35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | 117348824 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/30/2020 | ED.15276.2101 | EL DORADO PH 2101 | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 7,580.000 | 7,684.000 | 08W | 06/03/2019 | 2019 | # | #VALUE! | DOCC | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - El Dorado 2101 - LR 19752 - Ph3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 1919920.45
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | 117348827 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/30/2020 | ED.15276.2101 | EL DORADO PH 2101 | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 11,274.000 | 11,507.000 | 08W | 06/03/2019 | 2019 | # | #VALUE! | DOCC | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - El Dorado 2101 - LR 19752 - Ph3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 4162683.09
35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | 117348828 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/30/2020 | ED.15276.2101 | EL DORADO PH 2101 | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 14,080.000 | 13,725.000 | 08W | 06/03/2019 | 2019 | # | #VALUE! | DOCC | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - El Dorado 2101 - LR 19752 - Ph3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 3648795.02
35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | 117348366 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/30/2020 | ED.15276.2101 | EL DORADO PH 2101 | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 6,641.000 | 6,661.000 | 08W | 06/03/2019 | 2019 | # | #VALUE! | DOCC | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - El Dorado 2101 - LR 19752 - Ph4 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 1758073.57
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | 117348367 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/30/2020 | ED.15276.2101 | EL DORADO PH 2101 | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 11,685.000 | 11,318.000 | 08W | 06/03/2019 | 2019 | # | #VALUE! | DOCC | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - El Dorado 2101 - LR 19752 - Ph4 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 3423982.13
35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | 117348368 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/30/2020 | ED.15276.2101 | EL DORADO PH 2101 | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 1,618.000 | 1,618.000 | 08W | 06/03/2019 | 2019 | # | #VALUE! | DOCC | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - El Dorado 2101 - LR 19752 - Ph4 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 774754.05
35109737 | CWSP-VOLTA 1102-LR 1648-PH2.2 | 117380976 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.87-Q430800000.STRU.POLE | SHASTA Q4308 POLES | 045 | SHASTA COUNTY | 5535211 | CWSP SPO - SH 08 | 10,965.000 | 11,549.000 | 08W | 06/04/2019 | 2019 | # | #VALUE! | DOCC | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - VOLTA 1102 LR 1648 PH 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 3032566.08
35109738 | CWSP-VOLTA 1102-LR 1648-PH2.3 | 117380979 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.87-Q431100000.STRU.POLE | SHASTA Q4311 POLES | 045 | SHASTA COUNTY | 5535211 | CWSP SPO - SH 08 | 10,903.000 | 10,732.000 | 08W | 06/04/2019 | 2019 | # | #VALUE! | DOCC | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - VOLTA 1102 LR 1648 PH 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 2608805.4
35109739 | CWSP-VOLTA 1102-LR 1648-PH2.4 | 117381940 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.87-Q430300000.STRU.POLE | SHASTA Q4303 POLES | 045 | SHASTA COUNTY | 5535211 | CWSP SPO - SH 08 | 13,219.000 | 12,081.000 | 08W | 06/04/2019 | 2019 | # | #VALUE! | DOCC | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - VOLTA 1102 LR 1648 PH 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 2943332.71
35109832 | BR-03-01-W (E) GATE LN PARB | 117380789 | # | Not assigned | 30 | Technically Completed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/27/2019 | ED.17-S340700000.STRU.POLE | PARADISE S3407 POLES | 004 | BUTTE COUNTY | 5786123 | 08W Rebuild | 0.000 | 0.000 | 08W | 06/03/2019 | 2019 | # | #VALUE! | FICL | E470 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 1144522.31
35110369 | BR-03-03-W (E) GINNY_SUNRISE PARB | 117393835 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/27/2019 | ED.17-S340700000.STRU.POLE | PARADISE S3407 POLES | 004 | BUTTE COUNTY | 5786123 | 08W Rebuild | 0.000 | 0.000 | 08W | 06/05/2019 | 2019 | # | #VALUE! | MAPP | E470 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 1241954.74
35110372 | BR-03-04-W (E) SWEETBRIAR PARB | 117398952 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/27/2019 | ED.17-S341200000.STRU.POLE | PARADISE S3412 POLES | 004 | BUTTE COUNTY | 5786123 | 08W Rebuild | 0.000 | 0.000 | 08W | 06/05/2019 | 2019 | # | #VALUE! | DOCC | E470 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 853245.09
35110374 | BR-03-06-W (E) LUNAR LN PARB | 117398959 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/27/2019 | ED.17-S341300000.STRU.POLE | PARADISE S3413 POLES | 004 | BUTTE COUNTY | 5786123 | 08W Rebuild | 0.000 | 0.000 | 08W | 06/05/2019 | 2019 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 450.52
35110377 | BR-03-10-W (E) SHAY LN PARB | 117399397 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/27/2019 | ED.17-S341800000.STRU.POLE | PARADISE S3418 POLES | 004 | BUTTE COUNTY | 5786123 | 08W Rebuild | 0.000 | 0.000 | 08W | 06/05/2019 | 2019 | # | #VALUE! | MAPP | E470 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 3154947.03
35110379 | BR-03-11-W (E) WHITAKER RD PARB | 117399822 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/27/2019 | ED.17-S341700000.STRU.POLE | PARADISE S3417 POLES | 004 | BUTTE COUNTY | 5786123 | 08W Rebuild | 0.000 | 0.000 | 08W | 06/05/2019 | 2019 | # | #VALUE! | MAPP | E470 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 713717.42
35110440 | CWSP-VOLTA 1102-LR 1648-PH2.5 | 117381942 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.87-P432200000.STRU.POLE | SHASTA MAP P4322 POLES | 045 | SHASTA COUNTY | 5535211 | CWSP SPO - SH 08 | 15,053.000 | 13,964.000 | 08W | 06/04/2019 | 2019 | # | #VALUE! | DOCC | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - VOLTA 1102 LR 1648 PH 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 2774691.52
35110441 | CWSP-VOLTA 1102-LR 1648-PH2.6 | 117381943 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.87-P432100000.STRU.POLE | SHASTA P4321 POLES | 045 | SHASTA COUNTY | 5535211 | CWSP SPO - SH 08 | 11,790.000 | 11,791.000 | 08W | 06/04/2019 | 2019 | # | #VALUE! | DOCC | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - VOLTA 1102 LR 1648 PH 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 2094936.26
35110442 | CWSP-VOLTA 1102-LR 1648-PH3.2 | 117386854 | # | Not assigned | 30 | Technically Completed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.87-Q430000000.STRU.POLE | SHASTA Q43 POLES | 045 | SHASTA COUNTY | 5535211 | CWSP SPO - SH 08 | 7,155.000 | 7,126.000 | 08W | 06/04/2019 | 2019 | # | #VALUE! | FICL | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - VOLTA 1102 - LR 1648 -PHASE 3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 4050264.12
35110443 | CWSP-VOLTA 1102-LR 1648-PH3.3 | 117386950 | # | Not assigned | 30 | Technically Completed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | JY | JUNK YARD FL TO HOLD DELETED DATA | 045 | SHASTA COUNTY | 5535211 | CWSP SPO - SH 08 | 6,468.000 | 6,433.000 | 08W | 06/04/2019 | 2019 | # | #VALUE! | FICL | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - VOLTA 1102 - LR 1648 -PHASE 3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 2663871.02
35110444 | CWSP-VOLTA 1102-LR 1648-PH3.4 | 117386958 | # | Not assigned | 30 | Technically Completed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | JY | JUNK YARD FL TO HOLD DELETED DATA | 045 | SHASTA COUNTY | 5535211 | CWSP SPO - SH 08 | 7,757.000 | 7,728.000 | 08W | 06/04/2019 | 2019 | # | #VALUE! | FICL | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - VOLTA 1102 - LR 1648 -PHASE 3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 2551699.56
35110445 | CWSP-VOLTA 1102-LR 1648-PH4.2 | 117387609 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.87-P452200000.STRU.POLE | SHASTA P4522 POLES | 045 | SHASTA COUNTY | 5535211 | CWSP SPO - SH 08 | 10,160.000 | 9,066.000 | 08W | 06/04/2019 | 2019 | # | #VALUE! | DOCC | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - VOLTA 1102 - LR 1648 -PHASE 4 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 3475953.24
35110446 | CWSP-VOLTA 1102-LR 1648-PH4.3 | 117387798 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.87-P451700000.STRU.POLE | SHASTA MAP P4517 POLES | 045 | SHASTA COUNTY | 5535211 | CWSP SPO - SH 08 | 11,030.000 | 11,009.000 | 08W | 06/04/2019 | 2019 | # | #VALUE! | DOCC | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - VOLTA 1102 - LR 1648 -PHASE 4 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 2799988.1
35110447 | CWSP-VOLTA 1102-LR 1648-PH4.4 | 117387953 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.87-P451800000.STRU.POLE | SHASTA P4518 POLES | 045 | SHASTA COUNTY | 5535211 | CWSP SPO - SH 08 | 6,201.000 | 6,190.000 | 08W | 06/04/2019 | 2019 | # | #VALUE! | DOCC | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - VOLTA 1102 - LR 1648 -PHASE 4 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 3456509.15
35110448 | CWSP-VOLTA 1102-LR 1648-PH4.5 | 117388062 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.87-P451800000.STRU.POLE | SHASTA P4518 POLES | 045 | SHASTA COUNTY | 5535211 | CWSP SPO - SH 08 | 10,301.000 | 10,620.000 | 08W | 06/04/2019 | 2019 | # | #VALUE! | DOCC | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - VOLTA 1102 - LR 1648 -PHASE 4 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 3385386.89
35110556 | BR-04-12-W (E) SUBSTATION/PATH PARB | 117402466 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/27/2019 | ED.17-T330300000.STRU.POLE | PARADISE T3303 POLES | 004 | BUTTE COUNTY | 5786123 | 08W Rebuild | 0.000 | 0.000 | 08W | 06/06/2019 | 2019 | # | #VALUE! | ESTS | E470 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 38149.73
35111486 | BR-04-03-W (E) EDWARDS & RIPLEY PARB | 117443527 | # | Not assigned | 30 | Technically Completed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/27/2019 | JY | JUNK YARD FL TO HOLD DELETED DATA | 004 | BUTTE COUNTY | 5786123 | 08W Rebuild | 0.000 | 0.000 | 08W | 06/13/2019 | 2019 | # | #VALUE! | FICL | E470 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 1596180.67
35111500 | CWSP-RECON UPPER LAKE 01 HUNTERS PT RD | 117416989 | # | Not assigned | 30 | Technically Completed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/27/2019 | ED.04287.1101.SWIT | SWITCHES | 017 | LAKE COUNTY | 5535211 | CWSP SPO - SH 08 | 3,700.000 | 1,850.000 | 08W | 06/13/2019 | 2019 | # | #VALUE! | FICL | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 386043.97
35112076 | OCGC FULTON 1107-OH TO UG MARK W SPG | 117440386 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 03/21/2020 | ED.04256.1107 | FULTON 1107 | 049 | SONOMA COUNTY | 5786045 | CWSP - FULTON 1107 - MARK WEST SPR RD | 11,799.000 | 11,799.000 | 08W | 06/19/2019 | 2019 | # | #VALUE! | MAPP | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - FULTON 1107 - MARK WEST SPR RD | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 4519053.04
35112089 | BR-01-05-W (E) MEYERS PARB | 117463088 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/27/2019 | ED.17-S331700000.STRU.POLE | PARADISE S3317 POLES | 004 | BUTTE COUNTY | 5786123 | 08W Rebuild | 0.000 | 0.000 | 08W | 06/19/2019 | 2019 | # | #VALUE! | DOCC | E470 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 584621.18
35112090 | BR-01-07-W (E) BILLE_REGIS PARB | 117463089 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/27/2019 | ED.17-S332100000.STRU.POLE | PARADISE S3321 POLES | 004 | BUTTE COUNTY | 5786123 | 08W Rebuild | 0.000 | 0.000 | 08W | 06/19/2019 | 2019 | # | #VALUE! | DOCC | E470 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 598122.68
35112091 | BR-01-09-W (E) FERN PARB | 117463140 | # | Not assigned | 30 | Technically Completed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/27/2019 | JY | JUNK YARD FL TO HOLD DELETED DATA | 004 | BUTTE COUNTY | 5786123 | 08W Rebuild | 0.000 | 0.000 | 08W | 06/19/2019 | 2019 | # | #VALUE! | FICL | E470 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 349363.89
35112092 | BR-14-06 (E) BLUE DANUBE PARB | 117463141 | # | Not assigned | 30 | Technically Completed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/27/2019 | ED.17-T341900000.STRU.POLE | PARADISE T3419 POLES | 004 | BUTTE COUNTY | 5786123 | 08W Rebuild | 0.000 | 0.000 | 08W | 06/19/2019 | 2019 | # | #VALUE! | FICL | E470 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 491760.03
35112126 | BR-01-03-W (E) PARAGALIA PARB | 117462530 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/27/2019 | ED.17-S331900000.STRU.POLE | PARADISE S3319 POLES | 004 | BUTTE COUNTY | 5786123 | 08W Rebuild | 0.000 | 0.000 | 08W | 06/18/2019 | 2019 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35112128 | BR-01-04-W (E) W. WAGSTAFF PARB | 117462629 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/27/2019 | ED.17-S332100000.STRU.POLE | PARADISE S3321 POLES | 004 | BUTTE COUNTY | 5786123 | 08W Rebuild | 0.000 | 0.000 | 08W | 06/18/2019 | 2019 | # | #VALUE! | DOCC | E470 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 948107.87
35112157 | *CANC*CWSP - MIWUK 1701 - LR 10600 | # | 35052735 | CWSP - MIWUK 1701 - LR 10600 PH 1.1 | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | # | ED.16366.1701 | MIWUK 1701 | 055 | TUOLUMNE COUNT | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 06/19/2019 | 2019 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35112158 | *CANC*CWSP - MIWUK 1701 - LR 10600 | # | 35052735 | CWSP - MIWUK 1701 - LR 10600 PH 1.1 | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | # | ED.16366.1701 | MIWUK 1701 | 055 | TUOLUMNE COUNT | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 06/19/2019 | 2019 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35112159 | *CANC*CWSP - MIWUK 1701 - LR 10600 | # | 35052735 | CWSP - MIWUK 1701 - LR 10600 PH 1.1 | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | # | ED.16366.1701 | MIWUK 1701 | 055 | TUOLUMNE COUNT | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 06/19/2019 | 2019 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35112220 | BR-04-06-W (E) VALLEY RIDGE PARB | 117463683 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/27/2019 | JY | JUNK YARD FL TO HOLD DELETED DATA | 004 | BUTTE COUNTY | 5786123 | 08W Rebuild | 0.000 | 0.000 | 08W | 06/19/2019 | 2019 | # | #VALUE! | CONS | E470 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 641535.34
35112249 | BR-04-07-W (E) CRESTMOOR PARB | 117466069 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/27/2019 | JY | JUNK YARD FL TO HOLD DELETED DATA | 004 | BUTTE COUNTY | 5786123 | 08W Rebuild | 0.000 | 0.000 | 08W | 06/19/2019 | 2019 | # | #VALUE! | DOCC | E470 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 2945144.94
35112340 | *CANC*CWSP - MIWUK 1701 - LR 10600 | # | 35052735 | CWSP - MIWUK 1701 - LR 10600 PH 1.1 | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | # | ED.16366.1701 | MIWUK 1701 | 055 | TUOLUMNE COUNT | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 06/19/2019 | 2019 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | 117467828 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.21-G460000000.STRU.POLE | EL DORADO G46 POLES | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 6,653.000 | 0.000 | 08W | 06/20/2019 | 2019 | # | #VALUE! | CONS | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 723546
35112426 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.3 | 117467829 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/20/2019 | ED.21-G460000000.STRU.POLE | EL DORADO G46 POLES | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 9,368.000 | 9,077.000 | 08W | 06/20/2019 | 2019 | # | #VALUE! | DOCC | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 4025163.93
35112427 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.4 | 117467963 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 01/31/2020 | ED.21-G460000000.STRU.POLE | EL DORADO G46 POLES | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 5,117.000 | 5,069.000 | 08W | 06/20/2019 | 2019 | # | #VALUE! | MAPP | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 1730145.65
35112428 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.5 | 117467964 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 02/27/2020 | ED.21-G460000000.STRU.POLE | EL DORADO G46 POLES | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 8,571.000 | 8,571.000 | 08W | 06/20/2019 | 2019 | # | #VALUE! | MAPP | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 2459084.13
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | 117467966 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.21-G460000000.STRU.POLE | EL DORADO G46 POLES | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 7,341.000 | 0.000 | 08W | 06/20/2019 | 2019 | # | #VALUE! | CONS | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 1072544.99
35112431 | CWSP - EL DORADO 2102 - LR19562 - PH 1.1 | 117472384 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.15276.2102 | EL DORADO PH 2102 | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 8,118.000 | 8,117.000 | 08W | 06/20/2019 | 2019 | # | #VALUE! | MAPP | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - EL DORADO PH 2102 - LR 19562 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 1707343.33
35112432 | CWSP - EL DORADO 2102 - LR19562 - PH 1.2 | 117472387 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.15276.2102 | EL DORADO PH 2102 | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 11,193.000 | 13,572.000 | 08W | 06/20/2019 | 2019 | # | #VALUE! | DOCC | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - EL DORADO PH 2102 - LR 19562 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 1458687.39
35112433 | CWSP - EL DORADO 2102 - LR19562 - PH 1.3 | 117472388 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.15276.2102 | EL DORADO PH 2102 | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 10,122.000 | 10,205.000 | 08W | 06/20/2019 | 2019 | # | #VALUE! | DOCC | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - EL DORADO PH 2102 - LR 19562 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 1751217.64
35112434 | CWSP - EL DORADO 2102 - LR19562 - PH 1.4 | 117472389 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.15276.2102 | EL DORADO PH 2102 | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 7,924.000 | 7,924.000 | 08W | 06/20/2019 | 2019 | # | #VALUE! | DOCC | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - EL DORADO PH 2102 - LR 19562 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 2128525.57
35112435 | CWSP - EL DORADO 2102 - LR19562 - PH 1.5 | 117472561 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.15276.2102 | EL DORADO PH 2102 | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 7,873.000 | 7,006.000 | 08W | 06/20/2019 | 2019 | # | #VALUE! | DOCC | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - EL DORADO PH 2102 - LR 19562 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 1153072.54
35112436 | CWSP - EL DORADO 2102 - LR19562 - PH 1.6 | 117472563 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.15276.2102 | EL DORADO PH 2102 | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 9,210.000 | 9,867.000 | 08W | 06/20/2019 | 2019 | # | #VALUE! | DOCC | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - EL DORADO PH 2102 - LR 19562 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 2085213.15
35112437 | CWSP - EL DORADO 2102 - LR19562 - PH 1.7 | 117472564 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.15276.2102 | EL DORADO PH 2102 | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 14,365.000 | 14,550.000 | 08W | 06/20/2019 | 2019 | # | #VALUE! | MAPP | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - EL DORADO PH 2102 - LR 19562 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 1202369.12
35112876 | BR-04-02-W (E) CASTLE_CLIFF DR PARB | 117491028 | # | Not assigned | 30 | Technically Completed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/27/2019 | JY | JUNK YARD FL TO HOLD DELETED DATA | 004 | BUTTE COUNTY | 5786123 | 08W Rebuild | 0.000 | 0.000 | 08W | 06/25/2019 | 2019 | # | #VALUE! | FICL | E470 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 723044.04
35112968 | WOODSIDE 1101 RECOND FUSE 1097 ZONE | 117474195 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/30/2020 | ED.58-F081100000.STRU.POLE | PENINSULA F0811 POLES | 041 | SAN MATEO COUN | 5535211 | CWSP SPO - SH 08 | 14,709.000 | 0.000 | 08W | 06/26/2019 | 2019 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-WOODSIDE 1101-FUSE1097 TAP LINE | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 1689.6
35112972 | CWSP - WEST POINT 1101 -LR 13444- PH 1.2 | 117491267 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2019 | ED.95-J291500000.STRU.POLE | MOTHER LODE J2915 POLES | 003 | AMADOR COUNTY | 5535211 | CWSP SPO - SH 08 | 6,113.000 | 0.000 | 08W | 06/26/2019 | 2019 | # | #VALUE! | ESTS | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-WEST POINT 1101-LR 13444-PHASE 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 23438.75
35112973 | CWSP - WEST POINT 1101 -LR 13444- PH 1.3 | 117491412 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2019 | ED.95-J291500000.STRU.POLE | MOTHER LODE J2915 POLES | 003 | AMADOR COUNTY | 5535211 | CWSP SPO - SH 08 | 3,934.000 | 0.000 | 08W | 06/26/2019 | 2019 | # | #VALUE! | PEND | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-WEST POINT 1101-LR 13444-PHASE 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 82266.29
35112974 | CWSP - WEST POINT 1101 -LR 13444- PH 1.4 | 117491414 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2019 | ED.95-J291500000.STRU.POLE | MOTHER LODE J2915 POLES | 003 | AMADOR COUNTY | 5535211 | CWSP SPO - SH 08 | 13,819.000 | 0.000 | 08W | 06/26/2019 | 2019 | # | #VALUE! | ADER | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-WEST POINT 1101-LR 13444-PHASE 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 24202.37
35112975 | CWSP - WEST POINT 1101 -LR 13444- PH 1.5 | 117491771 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2019 | ED.95-J290900000.STRU.POLE | MOTHER LODE J2909 POLES | 003 | AMADOR COUNTY | 5786004 | CWSP - WEST POINT 1101 -LR 13444- PH 1.5 | 0.000 | 0.000 | 08W | 06/26/2019 | 2019 | # | #VALUE! | ADER | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-WEST POINT 1101-LR 13444-PHASE 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 15366.36
35112976 | CWSP - WEST POINT 1101 -LR 13444- PH 1.6 | 117491849 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2019 | ED.95-J290500000.STRU.POLE | MOTHER LODE MAP J2905 POLES | 003 | AMADOR COUNTY | 5786005 | CWSP - WEST POINT 1101 -LR 13444- PH 1.6 | 0.000 | 0.000 | 08W | 06/26/2019 | 2019 | # | #VALUE! | ESTS | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-WEST POINT 1101-LR 13444-PHASE 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 9791.75
35112977 | CWSP - WEST POINT 1101 -LR 13444- PH 1.7 | 117491910 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2019 | ED.95-J300100000.STRU.POLE | MOTHER LODE J3001 POLES | 003 | AMADOR COUNTY | 5786006 | CWSP - WEST POINT 1101 -LR 13444- PH 1.7 | 5,802.000 | 0.000 | 08W | 06/26/2019 | 2019 | # | #VALUE! | PEND | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-WEST POINT 1101-LR 13444-PHASE 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 10731.96
35112978 | CWSP - WEST POINT 1101 -LR 13444- PH 2.2 | 117493902 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/27/2019 | ED.16320.1101 | WEST POINT 1101 | 003 | AMADOR COUNTY | 5535211 | CWSP SPO - SH 08 | 8,442.000 | 0.000 | 08W | 06/26/2019 | 2019 | # | #VALUE! | PEND | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-WEST POINT 1101-LR 13444-PHASE 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 61639.03
35112979 | CWSP - WEST POINT 1101 -LR 13444- PH 2.3 | 117494010 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/27/2019 | ED.16320.1101 | WEST POINT 1101 | 003 | AMADOR COUNTY | 5535211 | CWSP SPO - SH 08 | 5,324.000 | 0.000 | 08W | 06/26/2019 | 2019 | # | #VALUE! | PEND | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-WEST POINT 1101-LR 13444-PHASE 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 58614.54
35113100 | CWSP - WEST POINT 1101 -LR 13444- PH 2.4 | 117494051 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/27/2019 | ED.16320.1101 | WEST POINT 1101 | 003 | AMADOR COUNTY | 5786009 | CWSP - WEST POINT 1101 -LR 13444- PH 2.4 | 10,665.000 | 0.000 | 08W | 06/26/2019 | 2019 | # | #VALUE! | PEND | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-WEST POINT 1101-LR 13444-PHASE 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 50176.16
35113101 | CWSP - WEST POINT 1101 -LR 13444- PH 2.5 | 117493797 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/01/2020 | ED.16320.1101 | WEST POINT 1101 | 003 | AMADOR COUNTY | 5535211 | CWSP SPO - SH 08 | 10,788.000 | 0.000 | 08W | 06/26/2019 | 2019 | # | #VALUE! | CONS | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-WEST POINT 1101-LR 13444-PHASE 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 1300850.84
35113102 | CWSP - WEST POINT 1101 -LR 13444- PH 2.6 | 117493910 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/01/2020 | ED.16320.1101 | WEST POINT 1101 | 003 | AMADOR COUNTY | 5535211 | CWSP SPO - SH 08 | 11,757.000 | 0.000 | 08W | 06/26/2019 | 2019 | # | #VALUE! | CONS | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-WEST POINT 1101-LR 13444-PHASE 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 1173578.47
35113103 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.3 | 117492227 | # | Not assigned | 30 | Technically Completed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.08202.1106 | LOS GATOS 1106 | 043 | SANTA CLARA CO | 5535211 | CWSP SPO - SH 08 | 1,152.000 | 1,152.000 | 08W | 06/26/2019 | 2019 | # | #VALUE! | FICL | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | PH 1:REPL 14,000' OF 4AR IN TIER 3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 309471.46
35113104 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.2 | 117492198 | # | Not assigned | 40 | Closed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.08202.1106 | LOS GATOS 1106 | 043 | SANTA CLARA CO | 5535211 | CWSP SPO - SH 08 | 1,399.000 | 1,399.000 | 08W | 06/26/2019 | 2019 | 10/31/2020 | 2020 | CLSD | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | PH 1:REPL 14,000' OF 4AR IN TIER 3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 414310.67
35113105 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.4 | 117492229 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.08202.1106 | LOS GATOS 1106 | 043 | SANTA CLARA CO | 5535211 | CWSP SPO - SH 08 | 3,582.000 | 38.000 | 08W | 06/26/2019 | 2019 | # | #VALUE! | DOCC | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | PH 1:REPL 14,000' OF 4AR IN TIER 3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 1179135.63
35113106 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.2B | 117492252 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.08202.1106 | LOS GATOS 1106 | 043 | SANTA CLARA CO | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 06/26/2019 | 2019 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Los Gatos 1106 - LB44 - Ph 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 4961.97
35113107 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.3C | 117492254 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.08202.1106 | LOS GATOS 1106 | 043 | SANTA CLARA CO | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 06/26/2019 | 2019 | # | #VALUE! | ESTS | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Los Gatos 1106 - LB44 - Ph 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 5237.24
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D | 117492255 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.08202.1106 | LOS GATOS 1106 | 043 | SANTA CLARA CO | 5535211 | CWSP SPO - SH 08 | 3,807.000 | 0.000 | 08W | 06/26/2019 | 2019 | # | #VALUE! | CONS | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Los Gatos 1106 - LB44 - Ph 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 502245.85
35113109 | CWSP - LOS GATOS 1106 - LB44 - PHASE 3.2 | 117492258 | # | Not assigned | 40 | Closed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.08202.1106 | LOS GATOS 1106 | 043 | SANTA CLARA CO | 5535211 | CWSP SPO - SH 08 | 681.000 | 681.000 | 08W | 06/26/2019 | 2019 | 10/31/2020 | 2020 | CLSD | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Los Gatos 1106 - LB44 - Ph 3.1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 284792.26
35113110 | CWSP - LOS GATOS 1106 - LB44 - PHASE 3.3 | 117492259 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.08202.1106 | LOS GATOS 1106 | 043 | SANTA CLARA CO | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 06/26/2019 | 2019 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Los Gatos 1106 - LB44 - Ph 3.1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 4616.09
35113111 | CWSP - LOS GATOS 1106 - LB44 - PHASE 3.4 | 117492280 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.08202.1106 | LOS GATOS 1106 | 043 | SANTA CLARA CO | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 06/26/2019 | 2019 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Los Gatos 1106 - LB44 - Ph 3.1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 4291.67
35113871 | SILVERADO 2104 RECONDUCTOR - PHASE 2 | 117556201 | # | Not assigned | 30 | Technically Completed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.04343.2104 | SILVERADO 2104 | 028 | NAPA COUNTY | 5786200 | CWSP - Silverado 2104 - Ph 2 | 794.000 | 650.000 | 08W | 07/02/2019 | 2019 | # | #VALUE! | FICL | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | SILVERADO 2104 RECONDUCTOR PROJECT | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 64435.74
35113945 | CWSP - BRUNSWICK 1102 - LR 1010 | 117557031 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/30/2020 | ED.15248.1102.RECL | RECLOSERS | 029 | NEVADA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 07/03/2019 | 2019 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BRUNSWICK 1102 - LR 1010 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 2782.78
35113946 | CWSP - WYANDOTTE 1103 – LR 1974 | 117557032 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/30/2020 | ED.10291.1103.RECL | RECLOSERS | 004 | BUTTE COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 07/03/2019 | 2019 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - WYANDOTTE 1103 – LR 1974 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 846.56
35113947 | CWSP - LOS GATOS 1107 – LR 60114 | 117557035 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/30/2020 | ED.08202.1107.RECL | RECLOSERS | 044 | SANTA CRUZ COU | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 07/03/2019 | 2019 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - LOS GATOS 1107 – LR 60114 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 1904.68
35113950 | CWSP - BIG BASIN 1101 - 10296 - PH 1.2 | 117560045 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.76-L110300000.STRU.POLE | COAST L1103 POLES | 044 | SANTA CRUZ COU | 5535211 | CWSP SPO - SH 08 | 18,848.000 | 0.000 | 08W | 07/03/2019 | 2019 | # | #VALUE! | UNSC | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BIG BASIN 1101 - LR 10296 - PH1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 100243.1
35113951 | CWSP - BIG BASIN 1101 - 10296 - PH 1.3 | 117560047 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.76-L110300000.STRU.POLE | COAST L1103 POLES | 044 | SANTA CRUZ COU | 5535211 | CWSP SPO - SH 08 | 13,637.000 | 0.000 | 08W | 07/03/2019 | 2019 | # | #VALUE! | UNSC | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BIG BASIN 1101 - LR 10296 - PH1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 107029.79
35113952 | *CANC* BB1101-LR10296-PH1.4 | 117560072 | # | Not assigned | 40 | Closed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.76-L110300000.STRU.POLE | COAST L1103 POLES | 044 | SANTA CRUZ COU | 5786126 | CWSP - BIG BASIN 1101 - LR 10296 - PH1.4 | 0.000 | 0.000 | 08W | 07/03/2019 | 2019 | 11/03/2019 | 2019 | CLSD | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BIG BASIN 1101 - LR 10296 - PH1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35113953 | *CANC* BB1101-LR10296-PH1.5 | 117560075 | # | Not assigned | 40 | Closed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.76-L110300000.STRU.POLE | COAST L1103 POLES | 044 | SANTA CRUZ COU | 5786127 | CWSP - BIG BASIN 1101 - LR 10296 - PH1.5 | 0.000 | 0.000 | 08W | 07/03/2019 | 2019 | 11/03/2019 | 2019 | CLSD | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BIG BASIN 1101 - LR 10296 - PH1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35113954 | *CANC* BB1101-LR10296-PH1.6 | 117560076 | # | Not assigned | 40 | Closed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.76-L110300000.STRU.POLE | COAST L1103 POLES | 044 | SANTA CRUZ COU | 5786129 | CWSP - BIG BASIN 1101 - LR 10296 - PH1.6 | 0.000 | 0.000 | 08W | 07/03/2019 | 2019 | 11/03/2019 | 2019 | CLSD | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BIG BASIN 1101 - LR 10296 - PH1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35113955 | *CANC* B1101-LR10296-PH1.7 | 117560077 | # | Not assigned | 40 | Closed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.76-L110300000.STRU.POLE | COAST L1103 POLES | 044 | SANTA CRUZ COU | 5786130 | CWSP - BIG BASIN 1101 - LR 10296 - PH1.7 | 0.000 | 0.000 | 08W | 07/03/2019 | 2019 | 11/03/2019 | 2019 | CLSD | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BIG BASIN 1101 - LR 10296 - PH1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35113993 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.2 | 117501693 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/01/2020 | ED.16320.1101 | WEST POINT 1101 | 003 | AMADOR COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 07/03/2019 | 2019 | # | #VALUE! | ESTS | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - WEST POINT 1101 - LR 12256 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 13485.76
35113994 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.3 | 117501694 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/01/2020 | ED.16320.1101 | WEST POINT 1101 | 003 | AMADOR COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 07/03/2019 | 2019 | # | #VALUE! | ADER | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - WEST POINT 1101 - LR 12256 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 28688.85
35113995 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.4 | 117501695 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/01/2020 | ED.16320.1101 | WEST POINT 1101 | 003 | AMADOR COUNTY | 5535211 | CWSP SPO - SH 08 | 6,115.000 | 0.000 | 08W | 07/03/2019 | 2019 | # | #VALUE! | PEND | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - WEST POINT 1101 - LR 12256 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 27041.17
35113996 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.5 | 117501697 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/01/2020 | ED.16320.1101 | WEST POINT 1101 | 003 | AMADOR COUNTY | 5786015 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.5 | 6,536.000 | 0.000 | 08W | 07/03/2019 | 2019 | # | #VALUE! | PEND | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - WEST POINT 1101 - LR 12256 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 90174.81
35113997 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.6 | 117500608 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/27/2019 | ED.16320.1101 | WEST POINT 1101 | 003 | AMADOR COUNTY | 5786016 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.6 | 6,919.000 | 0.000 | 08W | 07/03/2019 | 2019 | # | #VALUE! | PEND | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - WEST POINT 1101 - LR 12256 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 69252.28
35113998 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.7 | 117500659 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/27/2019 | ED.16320.1101 | WEST POINT 1101 | 003 | AMADOR COUNTY | 5786017 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.7 | 5,952.000 | 0.000 | 08W | 07/03/2019 | 2019 | # | #VALUE! | PEND | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - WEST POINT 1101 - LR 12256 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 108661.78
35113999 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.8 | 117500661 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/27/2019 | ED.16320.1101 | WEST POINT 1101 | 003 | AMADOR COUNTY | 5786134 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.8 | 8,978.000 | 0.000 | 08W | 07/03/2019 | 2019 | # | #VALUE! | ESTS | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - WEST POINT 1101 - LR 12256 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 9527.41
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 | 117500499 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/06/2019 | ED.16375.1102 | PINE GROVE 1102 | 003 | AMADOR COUNTY | 5785991 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 | 7,860.000 | 0.000 | 08W | 07/03/2019 | 2019 | # | #VALUE! | CONS | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP: PINE GROVE 1102 LR1222 PH 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 1073966.44
35114041 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.3 | 117500692 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/17/2021 | ED.16375.1102 | PINE GROVE 1102 | 003 | AMADOR COUNTY | 5535211 | CWSP SPO - SH 08 | 6,879.000 | 0.000 | 08W | 07/03/2019 | 2019 | # | #VALUE! | CONS | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP: PINE GROVE 1102 LR1222 PH 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 401762.34
35114042 | OCGC PINE GROVE 1102 - LR1222 - PH 1.4 | 117500694 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 09/01/2020 | ED.16375.1102 | PINE GROVE 1102 | 003 | AMADOR COUNTY | 5535211 | CWSP SPO - SH 08 | 7,126.000 | 7,126.000 | 08W | 07/03/2019 | 2019 | # | #VALUE! | MAPP | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP: PINE GROVE 1102 LR1222 PH 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 1027776.85
35114043 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.5 | 117502840 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/06/2019 | ED.16375.1102 | PINE GROVE 1102 | 003 | AMADOR COUNTY | 5535211 | CWSP SPO - SH 08 | 5,998.000 | 5,998.000 | 08W | 07/03/2019 | 2019 | # | #VALUE! | DOCC | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP: PINE GROVE 1102 LR1222 PH 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 691890.4
35114044 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.6 | 117502841 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/06/2019 | ED.16375.1102 | PINE GROVE 1102 | 003 | AMADOR COUNTY | 5535211 | CWSP SPO - SH 08 | 6,126.000 | 0.000 | 08W | 07/03/2019 | 2019 | # | #VALUE! | CONS | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP: PINE GROVE 1102 LR1222 PH 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 973650.22
35114045 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.7 | 117502843 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/06/2019 | ED.16375.1102 | PINE GROVE 1102 | 003 | AMADOR COUNTY | 5535211 | CWSP SPO - SH 08 | 7,602.000 | 0.000 | 08W | 07/03/2019 | 2019 | # | #VALUE! | UNSC | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP: PINE GROVE 1102 LR1222 PH 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 272233.82
35114046 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.2 | 117499462 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2019 | ED.95-K291100000.STRU.POLE | MOTHER LODE K2911 POLES | 003 | AMADOR COUNTY | 5785996 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.2 | 6,754.000 | 0.000 | 08W | 07/03/2019 | 2019 | # | #VALUE! | PEND | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP: PINE GROVE 1102 LR1222 ZONE WFH PH | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 36543.69
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 | 117499466 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.95-K291100000.STRU.POLE | MOTHER LODE K2911 POLES | 003 | AMADOR COUNTY | 5785997 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 | 7,344.000 | 0.000 | 08W | 07/03/2019 | 2019 | # | #VALUE! | CONS | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP: PINE GROVE 1102 LR1222 ZONE WFH PH | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 703697.08
35114049 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.4 | 117499469 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.95-K291100000.STRU.POLE | MOTHER LODE K2911 POLES | 003 | AMADOR COUNTY | 5785998 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.4 | 8,392.000 | 0.000 | 08W | 07/03/2019 | 2019 | # | #VALUE! | CONS | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP: PINE GROVE 1102 LR1222 ZONE WFH PH | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 969596.79
35114050 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.5 | 117499593 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2019 | ED.95-K291100000.STRU.POLE | MOTHER LODE K2911 POLES | 003 | AMADOR COUNTY | 5785999 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.5 | 6,564.000 | 0.000 | 08W | 07/03/2019 | 2019 | # | #VALUE! | UNSC | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP: PINE GROVE 1102 LR1222 ZONE WFH PH | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 346849.33
35114051 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.6 | 117502234 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2019 | ED.95-K290800000.STRU.POLE | MOTHER LODE K2908 POLES | 003 | AMADOR COUNTY | 5786000 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.6 | 7,698.000 | 0.000 | 08W | 07/03/2019 | 2019 | # | #VALUE! | CONS | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP: PINE GROVE 1102 LR1222 ZONE WFH PH | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 808640.72
35114052 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.7 | 117502368 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2019 | ED.95-K291000000.STRU.POLE | MOTHER LODE K2910 POLES | 003 | AMADOR COUNTY | 5786136 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.7 | 4,291.000 | 0.000 | 08W | 07/03/2019 | 2019 | # | #VALUE! | UNSC | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP: PINE GROVE 1102 LR1222 ZONE WFH PH | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 164420.81
35114053 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.8 | 117502416 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2019 | ED.95-K290500000.STRU.POLE | MOTHER LODE K2905 POLES | 003 | AMADOR COUNTY | 5786137 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.8 | 8,731.000 | 0.000 | 08W | 07/03/2019 | 2019 | # | #VALUE! | ADER | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP: PINE GROVE 1102 LR1222 ZONE WFH PH | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 49942.29
35114100 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.2 | 117545617 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.08362.2106 | CAMP EVERS 2106 | 044 | SANTA CRUZ COU | 5535211 | CWSP SPO - SH 08 | 5,487.000 | 0.000 | 08W | 07/03/2019 | 2019 | # | #VALUE! | CONS | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - CAMP EVERS 2106 - 5020 - PHASE 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 150708.76
35114101 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.3 | 117545618 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.08362.2106 | CAMP EVERS 2106 | 044 | SANTA CRUZ COU | 5535211 | CWSP SPO - SH 08 | 6,873.000 | 0.000 | 08W | 07/03/2019 | 2019 | # | #VALUE! | MAPP | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - CAMP EVERS 2106 - 5020 - PHASE 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 832220.54
35114102 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.4 | 117545619 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.08362.2106 | CAMP EVERS 2106 | 044 | SANTA CRUZ COU | 5535211 | CWSP SPO - SH 08 | 4,147.000 | 0.000 | 08W | 07/03/2019 | 2019 | # | #VALUE! | CONS | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - CAMP EVERS 2106 - 5020 - PHASE 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 202886.91
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 | 117560686 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.08362.2106 | CAMP EVERS 2106 | 044 | SANTA CRUZ COU | 5535211 | CWSP SPO - SH 08 | 5,963.000 | 0.000 | 08W | 07/03/2019 | 2019 | # | #VALUE! | CONS | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - CAMP EVERS 2106 - 5020 - PHASE 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 500090.17
35114104 | XCWSP - CAMP EVERS 2106 - LR5020 -PH 2.6 | 117560687 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.08362.2106 | CAMP EVERS 2106 | 044 | SANTA CRUZ COU | 5535211 | CWSP SPO - SH 08 | 7,619.000 | 7,962.000 | 08W | 07/03/2019 | 2019 | # | #VALUE! | CONS | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - CAMP EVERS 2106 - 5020 - PHASE 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 1519241.12
35114431 | CWSP - MORAGA 1101 - LR108540 - PH5 | 117572146 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/30/2020 | ED.01380.1101 | MORAGA 1101 | 007 | CONTRA COSTA C | 5535211 | CWSP SPO - SH 08 | 7,673.000 | 6,850.000 | 08W | 07/09/2019 | 2019 | # | #VALUE! | DOCC | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - MORAGA 1101 (VARIOUS) - OCB | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 4097004.43
35115046 | CWSP - MIWUK 1701 - LR 10600 PH 1.2 | 117496177 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 07/13/2021 | ED.16366.1701 | MIWUK 1701 | 055 | TUOLUMNE COUNT | 5535211 | CWSP SPO - SH 08 | 13,219.000 | 0.000 | 08W | 07/11/2019 | 2019 | # | #VALUE! | UNSC | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - MIWUK 1701 - LR 10600 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 188060.67
35115047 | CWSP - MIWUK 1701 - LR 10600 PH 1.3 | 117496281 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 06/11/2021 | ED.16366.1701 | MIWUK 1701 | 055 | TUOLUMNE COUNT | 5535211 | CWSP SPO - SH 08 | 11,492.000 | 0.000 | 08W | 07/11/2019 | 2019 | # | #VALUE! | PEND | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - MIWUK 1701 - LR 10600 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 175746.56
35115048 | CWSP - MIWUK 1701 - LR 10600 PH 1.4 | 117497751 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 09/24/2021 | ED.16366.1701 | MIWUK 1701 | 055 | TUOLUMNE COUNT | 5535211 | CWSP SPO - SH 08 | 12,346.000 | 0.000 | 08W | 07/11/2019 | 2019 | # | #VALUE! | ADER | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - MIWUK 1701 - LR 10600 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 32354.83
35115049 | CWSP - MIWUK 1701 - LR 10600 PH 1.5 | 117497752 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 07/13/2021 | ED.16366.1701 | MIWUK 1701 | 055 | TUOLUMNE COUNT | 5535211 | CWSP SPO - SH 08 | 11,947.000 | 0.000 | 08W | 07/11/2019 | 2019 | # | #VALUE! | ESTS | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - MIWUK 1701 - LR 10600 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 214634.21
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 | 117495948 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 04/30/2021 | ED.16366.1701 | MIWUK 1701 | 055 | TUOLUMNE COUNT | 5535211 | CWSP SPO - SH 08 | 8,512.000 | 0.000 | 08W | 07/11/2019 | 2019 | # | #VALUE! | CONS | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - MIWUK 1701_OCB WILDFIRE HARDENING | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 762696.42
35115051 | CWSP - MIWUK 1701_OCB - PH 1.3 | 117495949 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.16366.1701 | MIWUK 1701 | 055 | TUOLUMNE COUNT | 5535211 | CWSP SPO - SH 08 | 5,484.000 | 0.000 | 08W | 07/11/2019 | 2019 | # | #VALUE! | CONS | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - MIWUK 1701_OCB WILDFIRE HARDENING | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 60106.48
35115052 | CWSP - MIWUK 1701_OCB - PH 1.4 | 117496040 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.16366.1701 | MIWUK 1701 | 055 | TUOLUMNE COUNT | 5535211 | CWSP SPO - SH 08 | 8,548.000 | 0.000 | 08W | 07/11/2019 | 2019 | # | #VALUE! | CONS | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - MIWUK 1701_OCB WILDFIRE HARDENING | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 335729.41
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 | # | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.16366.1701 | MIWUK 1701 | 055 | TUOLUMNE COUNT | 5535211 | CWSP SPO - SH 08 | 9,083.000 | 0.000 | 08W | 07/11/2019 | 2019 | # | #VALUE! | CONS | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - MIWUK 1701_OCB WILDFIRE HARDENING | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 524056.85
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 | 117490035 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 04/30/2021 | ED.16366.1701 | MIWUK 1701 | 055 | TUOLUMNE COUNT | 5535211 | CWSP SPO - SH 08 | 7,529.000 | 0.000 | 08W | 07/11/2019 | 2019 | # | #VALUE! | CONS | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Miwuk 1701 - OCB Zone - Phase 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 1118364.24
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 | 117490481 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/04/2020 | ED.16366.1701 | MIWUK 1701 | 055 | TUOLUMNE COUNT | 5785987 | CWSP - MIWUK 1701 – OCB - PH 2.3 | 11,269.000 | 0.000 | 08W | 07/11/2019 | 2019 | # | #VALUE! | CONS | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Miwuk 1701 - OCB Zone - Phase 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 736816.76
35115056 | CWSP - MIWUK 1701 – OCB - PH 2.4 | 117490489 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/04/2020 | ED.16366.1701 | MIWUK 1701 | 055 | TUOLUMNE COUNT | 5535211 | CWSP SPO - SH 08 | 9,236.000 | 0.000 | 08W | 07/11/2019 | 2019 | # | #VALUE! | CONS | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Miwuk 1701 - OCB Zone - Phase 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 394101.38
35115057 | CWSP - MIWUK 1701 - OCB - PH2.5 | 117489824 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 03/23/2021 | ED.16366.1701 | MIWUK 1701 | 055 | TUOLUMNE COUNT | 5785989 | CWSP - MIWUK 1701 – OCB - PH 2.5 | 13,653.000 | 0.000 | 08W | 07/11/2019 | 2019 | # | #VALUE! | UNSC | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Miwuk 1701 - OCB Zone - Phase 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 133033.57
35115080 | BR-02-10-W (E) HARVEY RD PARB | 117590702 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/26/2020 | JY | JUNK YARD FL TO HOLD DELETED DATA | 004 | BUTTE COUNTY | 5786123 | 08W Rebuild | 0.000 | 0.000 | 08W | 07/11/2019 | 2019 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35115084 | BR-01-11-W (E) MONTNA DR PARB | 117591834 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/26/2020 | JY | JUNK YARD FL TO HOLD DELETED DATA | 004 | BUTTE COUNTY | 5786123 | 08W Rebuild | 0.000 | 0.000 | 08W | 07/11/2019 | 2019 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35115147 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.2 | 117496196 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 08/12/2020 | ED.15248.1103 | BRUNSWICK 1103 | 029 | NEVADA COUNTY | 5535211 | CWSP SPO - SH 08 | 7,076.000 | 6,200.000 | 08W | 07/12/2019 | 2019 | # | #VALUE! | DOCC | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Brunswick 1103 LR50070 Zone-Ph3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 860960.53
35115148 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.3 | 117496270 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 11/13/2020 | ED.15248.1103 | BRUNSWICK 1103 | 029 | NEVADA COUNTY | 5535211 | CWSP SPO - SH 08 | 11,210.000 | 0.000 | 08W | 07/12/2019 | 2019 | # | #VALUE! | DOCC | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Brunswick 1103 LR50070 Zone-Ph3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 1808409.94
35115149 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.4 | 117496274 | # | Not assigned | 30 | Technically Completed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 06/08/2020 | ED.15248.1103 | BRUNSWICK 1103 | 029 | NEVADA COUNTY | 5535211 | CWSP SPO - SH 08 | 6,500.000 | 6,265.000 | 08W | 07/12/2019 | 2019 | # | #VALUE! | FICL | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Brunswick 1103 LR50070 Zone-Ph3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 1894895.91
35115150 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.5 | 117496277 | # | Not assigned | 30 | Technically Completed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 08/25/2020 | ED.15248.1103 | BRUNSWICK 1103 | 029 | NEVADA COUNTY | 5535211 | CWSP SPO - SH 08 | 6,221.000 | 6,353.000 | 08W | 07/12/2019 | 2019 | # | #VALUE! | FICL | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Brunswick 1103 LR50070 Zone-Ph3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 550882.08
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | 117493857 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.15248.1103 | BRUNSWICK 1103 | 029 | NEVADA COUNTY | 5535211 | CWSP SPO - SH 08 | 10,013.000 | 0.000 | 08W | 07/12/2019 | 2019 | # | #VALUE! | CONS | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Brunswick 1103 LR50070 Zone-Ph2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 913400.64
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | 117495855 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.15248.1103 | BRUNSWICK 1103 | 029 | NEVADA COUNTY | 5535211 | CWSP SPO - SH 08 | 8,271.000 | 0.000 | 08W | 07/12/2019 | 2019 | # | #VALUE! | CONS | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Brunswick 1103 LR50070 Zone-Ph2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 352864.51
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | 117495859 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.15248.1103 | BRUNSWICK 1103 | 029 | NEVADA COUNTY | 5535211 | CWSP SPO - SH 08 | 9,476.000 | 0.000 | 08W | 07/12/2019 | 2019 | # | #VALUE! | CONS | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Brunswick 1103 LR50070 Zone-Ph2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 396996.04
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | 117496036 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.15248.1103 | BRUNSWICK 1103 | 029 | NEVADA COUNTY | 5535211 | CWSP SPO - SH 08 | 8,692.000 | 0.000 | 08W | 07/12/2019 | 2019 | # | #VALUE! | CONS | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Brunswick 1103 LR50070 Zone-Ph2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 876562.67
35115155 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.2 | 117491298 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 10/30/2020 | ED.15248.1103 | BRUNSWICK 1103 | 029 | NEVADA COUNTY | 5535211 | CWSP SPO - SH 08 | 10,024.000 | 9,232.000 | 08W | 07/12/2019 | 2019 | # | #VALUE! | CONS | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Brunswick 1103 LR50070 Zone-Ph1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 2970484.53
35115156 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.3 | 117491998 | # | Not assigned | 30 | Technically Completed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 07/03/2020 | ED.15248.1103 | BRUNSWICK 1103 | 029 | NEVADA COUNTY | 5535211 | CWSP SPO - SH 08 | 10,244.000 | 9,844.000 | 08W | 07/12/2019 | 2019 | # | #VALUE! | FICL | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Brunswick 1103 LR50070 Zone-Ph1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 2718471.05
35115157 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.4 | 117492085 | # | Not assigned | 30 | Technically Completed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 10/20/2020 | ED.15248.1103 | BRUNSWICK 1103 | 029 | NEVADA COUNTY | 5535211 | CWSP SPO - SH 08 | 15,728.000 | 10,162.000 | 08W | 07/12/2019 | 2019 | # | #VALUE! | FICL | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Brunswick 1103 LR50070 Zone-Ph1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 3417547.63
35115158 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.5 | 117492102 | # | Not assigned | 30 | Technically Completed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 07/16/2020 | ED.15248.1103 | BRUNSWICK 1103 | 029 | NEVADA COUNTY | 5535211 | CWSP SPO - SH 08 | 11,108.000 | 10,413.000 | 08W | 07/12/2019 | 2019 | # | #VALUE! | FICL | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Brunswick 1103 LR50070 Zone-Ph1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 2311078.43
35115847 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.2 | 117602056 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2019 | ED.95-NN36010000.STRU.POLE | Angels Camp MAP NN3601 POLES | 005 | CALAVERAS COUN | 5786018 | CWSP-SALT SPRINGS 2102-LR3142ZONE-PH 2.2 | 9,916.000 | 0.000 | 08W | 07/16/2019 | 2019 | # | #VALUE! | ESTS | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-SALT SPRINGS 2102-LR3142 ZONE-PH 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 53250.06
35115848 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.3 | 117602057 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2019 | ED.95-NN36010000.STRU.POLE | Angels Camp MAP NN3601 POLES | 005 | CALAVERAS COUN | 5786019 | CWSP-SALT SPRINGS 2102-LR3142ZONE-PH 2.3 | 8,685.000 | 0.000 | 08W | 07/16/2019 | 2019 | # | #VALUE! | PEND | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-SALT SPRINGS 2102-LR3142 ZONE-PH 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 136569.08
35115849 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.4 | 117602058 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2019 | ED.95-NN36010000.STRU.POLE | Angels Camp MAP NN3601 POLES | 005 | CALAVERAS COUN | 5786020 | CWSP-SALT SPRINGS 2102-LR3142ZONE-PH 2.4 | 9,187.000 | 0.000 | 08W | 07/16/2019 | 2019 | # | #VALUE! | PEND | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-SALT SPRINGS 2102-LR3142 ZONE-PH 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 756952.44
35115850 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.5 | 117602059 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2019 | ED.95-NN36010000.STRU.POLE | Angels Camp MAP NN3601 POLES | 005 | CALAVERAS COUN | 5786021 | CWSP-SALT SPRINGS 2102-LR3142ZONE-PH 2.5 | 6,856.000 | 0.000 | 08W | 07/16/2019 | 2019 | # | #VALUE! | UNSC | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-SALT SPRINGS 2102-LR3142 ZONE-PH 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 118085.26
35115851 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.6 | 117602170 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2019 | ED.95-NN36010000.STRU.POLE | Angels Camp MAP NN3601 POLES | 005 | CALAVERAS COUN | 5535211 | CWSP SPO - SH 08 | 6,653.000 | 0.000 | 08W | 07/16/2019 | 2019 | # | #VALUE! | PEND | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-SALT SPRINGS 2102-LR3142 ZONE-PH 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 70225.44
35115852 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.7 | 117602171 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2019 | ED.95-NN36010000.STRU.POLE | Angels Camp MAP NN3601 POLES | 005 | CALAVERAS COUN | 5535211 | CWSP SPO - SH 08 | 8,590.000 | 0.000 | 08W | 07/16/2019 | 2019 | # | #VALUE! | PEND | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-SALT SPRINGS 2102-LR3142 ZONE-PH 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 88300.84
35115853 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.2 | 117601683 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2019 | ED.95-NN36010000.STRU.POLE | Angels Camp MAP NN3601 POLES | 005 | CALAVERAS COUN | 5535211 | CWSP SPO - SH 08 | 10,559.000 | 0.000 | 08W | 07/16/2019 | 2019 | # | #VALUE! | UNSC | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-SALT SPRINGS 2102-LR3142&L491-PHA 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 316066.6
35115854 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.3 | 117601685 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2019 | ED.95-NN36010000.STRU.POLE | Angels Camp MAP NN3601 POLES | 005 | CALAVERAS COUN | 5535211 | CWSP SPO - SH 08 | 5,762.000 | 0.000 | 08W | 07/16/2019 | 2019 | # | #VALUE! | CONS | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-SALT SPRINGS 2102-LR3142&L491-PHA 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 97979.66
35115855 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.4 | 117601687 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2019 | ED.95-NN36010000.STRU.POLE | Angels Camp MAP NN3601 POLES | 005 | CALAVERAS COUN | 5535211 | CWSP SPO - SH 08 | 6,672.000 | 0.000 | 08W | 07/16/2019 | 2019 | # | #VALUE! | CONS | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-SALT SPRINGS 2102-LR3142&L491-PHA 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 1546805.02
35115856 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.5 | 117601688 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2019 | ED.95-NN36010000.STRU.POLE | Angels Camp MAP NN3601 POLES | 005 | CALAVERAS COUN | 5786025 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.5 | 10,616.000 | 0.000 | 08W | 07/16/2019 | 2019 | # | #VALUE! | UNSC | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-SALT SPRINGS 2102-LR3142&L491-PHA 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 153909.91
35115857 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.6 | 117601884 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2019 | ED.95-NN36010000.STRU.POLE | Angels Camp MAP NN3601 POLES | 005 | CALAVERAS COUN | 5786026 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.6 | 6,445.000 | 0.000 | 08W | 07/16/2019 | 2019 | # | #VALUE! | PEND | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-SALT SPRINGS 2102-LR3142&L491-PHA 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 33344.29
35115858 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.7 | 117601885 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2019 | ED.95-NN36010000.STRU.POLE | Angels Camp MAP NN3601 POLES | 005 | CALAVERAS COUN | 5786027 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.7 | 6,883.000 | 0.000 | 08W | 07/16/2019 | 2019 | # | #VALUE! | PEND | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-SALT SPRINGS 2102-LR3142&L491-PHA 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 93919.45
35116180 | R-1123 RECONDUCTOR PAST R9229 - WHARF ST | 117602173 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2021 | ED.01347.1123 | RICHMOND R 1123 | 007 | CONTRA COSTA C | 5535457 | DO 08 - Monthly Forecast Only | 1,781.000 | 0.000 | 08J | 07/16/2019 | 2019 | # | #VALUE! | PEND | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 10072.94
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 | 117604600 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/25/2020 | ED.16366.1701 | MIWUK 1701 | 055 | TUOLUMNE COUNT | 5535211 | CWSP SPO - SH 08 | 7,319.000 | 0.000 | 08W | 07/17/2019 | 2019 | # | #VALUE! | CONS | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | MIWUK 1701 LR8060 08W WILDFIRE HARDENING | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 783810.24
35116384 | CWSP - MIWUK 1701 - LR 8060 - PH 1.3 | 117604604 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/25/2020 | ED.16366.1701 | MIWUK 1701 | 055 | TUOLUMNE COUNT | 5535211 | CWSP SPO - SH 08 | 9,700.000 | 0.000 | 08W | 07/17/2019 | 2019 | # | #VALUE! | CONS | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | MIWUK 1701 LR8060 08W WILDFIRE HARDENING | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 50045.46
35116385 | CWSP - MIWUK 1701 - LR 8060 - PH 1.4 | 117604609 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 03/31/2021 | ED.16366.1701 | MIWUK 1701 | 055 | TUOLUMNE COUNT | 5535211 | CWSP SPO - SH 08 | 7,376.000 | 0.000 | 08W | 07/17/2019 | 2019 | # | #VALUE! | PEND | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | MIWUK 1701 LR8060 08W WILDFIRE HARDENING | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 48183.45
35116388 | CWSP - MIWUK 1701 - LR 8060 - PH 1.5 | 117604672 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/25/2020 | ED.16366.1701 | MIWUK 1701 | 055 | TUOLUMNE COUNT | 5535211 | CWSP SPO - SH 08 | 13,109.000 | 0.000 | 08W | 07/17/2019 | 2019 | # | #VALUE! | PEND | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | MIWUK 1701 LR8060 08W WILDFIRE HARDENING | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 389969.86
35116389 | CWSP - MIWUK 1701 - LR 8060 - PH 1.6 | 117604676 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/25/2020 | ED.16366.1701 | MIWUK 1701 | 055 | TUOLUMNE COUNT | 5535211 | CWSP SPO - SH 08 | 9,970.000 | 0.000 | 08W | 07/17/2019 | 2019 | # | #VALUE! | ESTS | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | MIWUK 1701 LR8060 08W WILDFIRE HARDENING | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 47349.69
35116390 | CWSP - MIWUK 1701 - LR 8060 - PH 1.7 | 117604678 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/03/2020 | ED.16366.1701 | MIWUK 1701 | 055 | TUOLUMNE COUNT | 5535211 | CWSP SPO - SH 08 | 4,715.000 | 0.000 | 08W | 07/17/2019 | 2019 | # | #VALUE! | CONS | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | MIWUK 1701 LR8060 08W WILDFIRE HARDENING | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 691658.98
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 | 117605551 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/27/2019 | ED.16366.1702 | MIWUK 1702 | 055 | TUOLUMNE COUNT | 5785976 | CWSP - MIWUK 1702 - OCB - PH 1.2 | 10,932.000 | 0.000 | 08W | 07/17/2019 | 2019 | # | #VALUE! | CONS | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - MIWUK 1702_OCB WILDFIRE HARDENING | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 1051497.75
35116393 | CWSP - MIWUK 1702 - OCB - PH 1.3 | 117605554 | # | Not assigned | 30 | Technically Completed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/27/2019 | ED.16366.1702 | MIWUK 1702 | 055 | TUOLUMNE COUNT | 5535211 | CWSP SPO - SH 08 | 13,485.000 | 13,742.000 | 08W | 07/17/2019 | 2019 | # | #VALUE! | FICL | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - MIWUK 1702_OCB WILDFIRE HARDENING | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 4269376.5
35116394 | CWSP - MIWUK 1702 - OCB - PH 1.4 | 117605556 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/27/2019 | ED.16366.1702 | MIWUK 1702 | 055 | TUOLUMNE COUNT | 5535211 | CWSP SPO - SH 08 | 8,790.000 | 8,790.000 | 08W | 07/17/2019 | 2019 | # | #VALUE! | FICL | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - MIWUK 1702_OCB WILDFIRE HARDENING | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 1467650.78
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 | 117605558 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.16366.1702 | MIWUK 1702 | 055 | TUOLUMNE COUNT | 5535211 | CWSP SPO - SH 08 | 9,032.000 | 0.000 | 08W | 07/17/2019 | 2019 | # | #VALUE! | CONS | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - MIWUK 1702_OCB WILDFIRE HARDENING | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 576288.21
35116396 | CWSP-MIWUK 1702-LR8090-PH 1.2 | 117604756 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 11/23/2021 | ED.16366.1702 | MIWUK 1702 | 055 | TUOLUMNE COUNT | 5535211 | CWSP SPO - SH 08 | 11,216.000 | 0.000 | 08W | 07/17/2019 | 2019 | # | #VALUE! | CONS | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-MIWUK 1702-LR 8090 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 512309.21
35116397 | CWSP-MIWUK 1702-LR8090-PH 1.3 | 117604668 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/27/2019 | ED.16366.1702 | MIWUK 1702 | 055 | TUOLUMNE COUNT | 5535211 | CWSP SPO - SH 08 | 10,614.000 | 0.000 | 08W | 07/17/2019 | 2019 | # | #VALUE! | PEND | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-MIWUK 1702-LR 8090 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 32096.92
35116398 | CWSP-MIWUK 1702-LR8090-PH 1.4 | 117604615 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 07/23/2021 | ED.16366.1702 | MIWUK 1702 | 055 | TUOLUMNE COUNT | 5535211 | CWSP SPO - SH 08 | 11,376.000 | 0.000 | 08W | 07/17/2019 | 2019 | # | #VALUE! | ESTS | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-MIWUK 1702-LR 8090 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 29702.1
35116399 | CWSP-MIWUK 1702-LR8090-PH 1.5 | 117604337 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/27/2019 | ED.16366.1702 | MIWUK 1702 | 055 | TUOLUMNE COUNT | 5785932 | CWSP - MIWUK 1702 - LR 8090 - PH 1.5 | 9,687.000 | 0.000 | 08W | 07/17/2019 | 2019 | # | #VALUE! | UNSC | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-MIWUK 1702-LR 8090 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 164288.65
35116440 | CWSP-MIWUK 1702-LR8090-PH 1.6 | 117604512 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 03/04/2022 | ED.16366.1702 | MIWUK 1702 | 055 | TUOLUMNE COUNT | 5535211 | CWSP SPO - SH 08 | 9,980.000 | 0.000 | 08W | 07/17/2019 | 2019 | # | #VALUE! | ESTS | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-MIWUK 1702-LR 8090 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 43176.17
35116441 | CWSP-MIWUK 1702-LR 38218-PH1.2 | 117605164 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 06/22/2021 | ED.16366.1702 | MIWUK 1702 | 055 | TUOLUMNE COUNT | 5535211 | CWSP SPO - SH 08 | 17,147.000 | 0.000 | 08W | 07/17/2019 | 2019 | # | #VALUE! | ESTS | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - MIWUK 1702_LR38218 WILDFIRE HARDE | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 39701.61
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 | 117605169 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 11/17/2020 | ED.16366.1702 | MIWUK 1702 | 055 | TUOLUMNE COUNT | 5535211 | CWSP SPO - SH 08 | 12,386.000 | 0.000 | 08W | 07/17/2019 | 2019 | # | #VALUE! | CONS | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - MIWUK 1702_LR38218 WILDFIRE HARDE | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 1721388.61
35116443 | CWSP-MIWUK 1702-LR 38218-PH 1.4 | 117605181 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.16366.1702 | MIWUK 1702 | 055 | TUOLUMNE COUNT | 5535211 | CWSP SPO - SH 08 | 10,249.000 | 0.000 | 08W | 07/17/2019 | 2019 | # | #VALUE! | CONS | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - MIWUK 1702_LR38218 WILDFIRE HARDE | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 690856.98
35116444 | CWSP-MIWUK 1702-LR 38218-PH 1.5 | 117605182 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.16366.1702 | MIWUK 1702 | 055 | TUOLUMNE COUNT | 5785984 | CWSP - MIWUK 1702 - LR 38218 - PH 1.5 | 11,100.000 | 0.000 | 08W | 07/17/2019 | 2019 | # | #VALUE! | CONS | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - MIWUK 1702_LR38218 WILDFIRE HARDE | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 855082.86
35116511 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.2 | 117608780 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.16282.1702 | STANISLAUS 1702 | 005 | CALAVERAS COUN | 5535211 | CWSP SPO - SH 08 | 6,348.000 | 0.000 | 08W | 07/18/2019 | 2019 | # | #VALUE! | UNSC | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-STANISLAUS1702-LR1888-PH2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 69023.19
35116512 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.3 | 117608788 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.16282.1702 | STANISLAUS 1702 | 005 | CALAVERAS COUN | 5535211 | CWSP SPO - SH 08 | 9,236.000 | 0.000 | 08W | 07/18/2019 | 2019 | # | #VALUE! | PEND | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-STANISLAUS1702-LR1888-PH2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 82946.79
35116513 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.4 | 117608814 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.16282.1702 | STANISLAUS 1702 | 005 | CALAVERAS COUN | 5786043 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.4 | 8,690.000 | 0.000 | 08W | 07/18/2019 | 2019 | # | #VALUE! | PEND | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-STANISLAUS1702-LR1888-PH2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 34430.23
35116514 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.5 | 117608818 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.16282.1702 | STANISLAUS 1702 | 005 | CALAVERAS COUN | 5786044 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.5 | 10,852.000 | 0.000 | 08W | 07/18/2019 | 2019 | # | #VALUE! | PEND | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-STANISLAUS1702-LR1888-PH2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 43156.24
35116515 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.2 | 117607998 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.16282.1702 | STANISLAUS 1702 | 005 | CALAVERAS COUN | 5786036 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.2 | 9,222.000 | 0.000 | 08W | 07/18/2019 | 2019 | # | #VALUE! | UNSC | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-STANISLAUS1702-LR1888-PH1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 122242.57
35116516 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.3 | 117608020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.16282.1702 | STANISLAUS 1702 | 005 | CALAVERAS COUN | 5786037 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.3 | 4,825.000 | 0.000 | 08W | 07/18/2019 | 2019 | # | #VALUE! | PEND | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-STANISLAUS1702-LR1888-PH1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 99742.58
35116517 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.5 | 117608185 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.16282.1702 | STANISLAUS 1702 | 005 | CALAVERAS COUN | 5786039 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.5 | 12,677.000 | 0.000 | 08W | 07/18/2019 | 2019 | # | #VALUE! | PEND | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-STANISLAUS1702-LR1888-PH1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 86816.25
35116518 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.6 | 117608188 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.16282.1702 | STANISLAUS 1702 | 005 | CALAVERAS COUN | 5786040 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.6 | 10,866.000 | 0.000 | 08W | 07/18/2019 | 2019 | # | #VALUE! | PEND | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-STANISLAUS1702-LR1888-PH1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 50144.84
35116519 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.4 | 117608026 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.16282.1702 | STANISLAUS 1702 | 005 | CALAVERAS COUN | 5786038 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.4 | 9,268.000 | 0.000 | 08W | 07/18/2019 | 2019 | # | #VALUE! | UNSC | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-STANISLAUS1702-LR1888-PH1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 37441.53
35116800 | CWSP-MIWUK 1702-LR 6018-PHASE 1.2 | 117605265 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.16366.1702 | MIWUK 1702 | 055 | TUOLUMNE COUNT | 5535211 | CWSP SPO - SH 08 | 7,525.000 | 0.000 | 08W | 07/18/2019 | 2019 | # | #VALUE! | CONS | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - MIWUK 1702-LR 6018-PHASE 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 1065707.56
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 | 117605266 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.16366.1702 | MIWUK 1702 | 055 | TUOLUMNE COUNT | 5535211 | CWSP SPO - SH 08 | 6,747.000 | 0.000 | 08W | 07/18/2019 | 2019 | # | #VALUE! | UNSC | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - MIWUK 1702-LR 6018-PHASE 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 1283799.71
35116802 | CWSP-MIWUK 1702-LR 6018-PHASE 1.4 | 117605267 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.16366.1702 | MIWUK 1702 | 055 | TUOLUMNE COUNT | 5535211 | CWSP SPO - SH 08 | 11,739.000 | 1,260.000 | 08W | 07/18/2019 | 2019 | # | #VALUE! | CONS | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - MIWUK 1702-LR 6018-PHASE 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 1624834.79
35116803 | CWSP-MIWUK 1702-LR 6018-PHASE 1.5 | 117605268 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.16366.1702 | MIWUK 1702 | 055 | TUOLUMNE COUNT | 5785964 | CWSP - MIWUK 1702 - LR 6018 - PH 1.5 | 12,028.000 | 0.000 | 08W | 07/18/2019 | 2019 | # | #VALUE! | PEND | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - MIWUK 1702-LR 6018-PHASE 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 153912.61
35116804 | CWSP-MIWUK 1702-LR 6018-PHASE 1.6 | 117605269 | # | Not assigned | 30 | Technically Completed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.16366.1702 | MIWUK 1702 | 055 | TUOLUMNE COUNT | 5535211 | CWSP SPO - SH 08 | 5,387.000 | 5,340.000 | 08W | 07/18/2019 | 2019 | # | #VALUE! | FICL | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - MIWUK 1702-LR 6018-PHASE 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 1189745.34
35116921 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.2 | 117605453 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/25/2021 | ED.16282.1702 | STANISLAUS 1702 | 005 | CALAVERAS COUN | 5786030 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.2 | 8,059.000 | 0.000 | 08W | 07/19/2019 | 2019 | # | #VALUE! | PEND | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | STANISLAUS 1702 LR1804 ZONE WFH LEVEL 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 80401.13
35116922 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.3 | 117605456 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/25/2021 | ED.16282.1702 | STANISLAUS 1702 | 005 | CALAVERAS COUN | 5786031 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.3 | 6,121.000 | 0.000 | 08W | 07/19/2019 | 2019 | # | #VALUE! | PEND | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | STANISLAUS 1702 LR1804 ZONE WFH LEVEL 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 47983.06
35116923 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.4 | 117605459 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/25/2021 | ED.16282.1702 | STANISLAUS 1702 | 005 | CALAVERAS COUN | 5786032 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.4 | 6,378.000 | 0.000 | 08W | 07/19/2019 | 2019 | # | #VALUE! | ADER | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | STANISLAUS 1702 LR1804 ZONE WFH LEVEL 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 128287.05
35116924 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.5 | 117605550 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/25/2021 | ED.16282.1702 | STANISLAUS 1702 | 005 | CALAVERAS COUN | 5786033 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.5 | 9,032.000 | 0.000 | 08W | 07/19/2019 | 2019 | # | #VALUE! | ADER | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | STANISLAUS 1702 LR1804 ZONE WFH LEVEL 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 88313.32
35116925 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.6 | 117605552 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/25/2021 | ED.16282.1702 | STANISLAUS 1702 | 005 | CALAVERAS COUN | 5786034 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.6 | 9,147.000 | 0.000 | 08W | 07/19/2019 | 2019 | # | #VALUE! | ADER | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | STANISLAUS 1702 LR1804 ZONE WFH LEVEL 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 45562.64
35116926 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.7 | 117605553 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/25/2021 | ED.16282.1702 | STANISLAUS 1702 | 005 | CALAVERAS COUN | 5786035 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.7 | 7,718.000 | 0.000 | 08W | 07/19/2019 | 2019 | # | #VALUE! | PEND | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | STANISLAUS 1702 LR1804 ZONE WFH LEVEL 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 59031.1
35116930 | WD - RECONDUCTOR GV2102 - NEAR 64763 | 117621052 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/31/2021 | ED.76-R190900000.STRU.POLE | COAST R1909 POLES | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 1,550.000 | 0.000 | 08J | 07/19/2019 | 2019 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 373.7
35117007 | CWSP-ORO FINO 1102 OCB & LR2090 PH 1.1 | 114708276 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1102 | ORO FINO 1102 | 004 | BUTTE COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 07/23/2019 | 2019 | # | #VALUE! | ESTS | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-ORO FINO 1102 OCB & LR2090 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 8400.23
35117102 | LOYOLA1102 LS CO1611 REPL 300FT OH LINE | 117626386 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/25/2021 | ED.80-G120200000.STRU.POLE | DE ANZA G1202 POLES | 043 | SANTA CLARA CO | 5517127 | DO 08 - Monthly Forecast Only | 500.000 | 0.000 | 08J | 07/22/2019 | 2019 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
35117180 | RECOND GREEN VALLEY 2103 REF# S011CC105 | 113663786 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/29/2019 | ED.08319.2103 | GREEN VALLEY 2103 | 044 | SANTA CRUZ COU | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 07/22/2019 | 2019 | # | #VALUE! | ESTS | E470 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 10934.87
35117354 | RECONDUCTOR LO2102 NEAR 7955 | 117632451 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 07/24/2021 | ED.04-Q210000000.STRU.POLE | KING CITY Q21 POLES | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 1,082.000 | 0.000 | 08J | 07/24/2019 | 2019 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 2828.38
35117398 | BR-01-12-W (E) MYRTLE WAY, PARB | 117636680 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/26/2020 | ED.17-S331500000.STRU.POLE | PARADISE S3315 POLES | 004 | BUTTE COUNTY | 5786123 | 08W Rebuild | 0.000 | 0.000 | 08W | 07/24/2019 | 2019 | # | #VALUE! | ESTS | E470 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 8973.6
35117409 | SM 1110 - RECON 650 FT W 2CU | 117606445 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/30/2021 | ED.18267.1110 | SANTA MARIA 1110 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 07/24/2019 | 2019 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 337.78
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | 117634567 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/04/2020 | ED.15248.1103 | BRUNSWICK 1103 | 029 | NEVADA COUNTY | 5535211 | CWSP SPO - SH 08 | 11,395.000 | 0.000 | 08W | 07/24/2019 | 2019 | # | #VALUE! | CONS | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Brunswick 1103 LR50070 Zone-Ph3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 1059309.24
35117444 | CWSP - VOLTA 1102 LR 1648 PH 2.1 | 114750733 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | JY | JUNK YARD FL TO HOLD DELETED DATA | 045 | SHASTA COUNTY | 5535211 | CWSP SPO - SH 08 | 12,656.000 | 12,656.000 | 08W | 07/24/2019 | 2019 | # | #VALUE! | DOCC | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - VOLTA 1102 LR 1648 PH 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 2158472.27
35117455 | BR-02-04-W (E) HERMAN PARB | 117637039 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/26/2020 | JY | JUNK YARD FL TO HOLD DELETED DATA | 004 | BUTTE COUNTY | 5786123 | 08W Rebuild | 0.000 | 0.000 | 08W | 07/25/2019 | 2019 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35117540 | BR-02-01-W (E) CLARK RD & SAN JOSE PARB | 117636827 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/26/2020 | ED.17-S340700000.STRU.POLE | PARADISE S3407 POLES | 004 | BUTTE COUNTY | 5786123 | 08W Rebuild | 0.000 | 0.000 | 08W | 07/24/2019 | 2019 | # | #VALUE! | ADER | E470 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35117544 | VIERRA 1703 RECONDUCTOR | 117638665 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2021 | ED.16270.1703 | VIERRA 1703 | 039 | SAN JOAQUIN CO | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 07/25/2019 | 2019 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 3992.5
35117983 | BR-02-07-W (E) DOLORES DR, PARB | 117641061 | 35132419 | BR-02-07-F (E) DOLORES DR PARB | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/26/2020 | ED.17-S341700000.STRU.POLE | PARADISE S3417 POLES | 004 | BUTTE COUNTY | 5786123 | 08W Rebuild | 0.000 | 0.000 | 08W | 07/25/2019 | 2019 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 1424612.7
35117986 | BR-02-08-W (E) DIAMOND LN PARB | 117641707 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/26/2020 | JY | JUNK YARD FL TO HOLD DELETED DATA | 004 | BUTTE COUNTY | 5786123 | 08W Rebuild | 0.000 | 0.000 | 08W | 07/25/2019 | 2019 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35118422 | BR-02-13-W (E) LANCASTER DR PARB | 117662965 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/26/2020 | ED.17-S342100000.STRU.POLE | PARADISE S3421 POLES | 004 | BUTTE COUNTY | 5786123 | 08W Rebuild | 0.000 | 0.000 | 08W | 07/29/2019 | 2019 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35118425 | BR-04-04-W (E) VALLEY VIEW PARB | 117663992 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/26/2020 | ED.17-S332100000.STRU.POLE | PARADISE S3321 POLES | 004 | BUTTE COUNTY | 5786123 | 08W Rebuild | 0.000 | 0.000 | 08W | 07/29/2019 | 2019 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 207.73
35118433 | BR-04-10-W (E) CRESTVIEW PARB | 117664813 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/26/2020 | ED.17-T330100000.STRU.POLE | PARADISE T3301 POLES | 004 | BUTTE COUNTY | 5786123 | 08W Rebuild | 0.000 | 0.000 | 08W | 07/30/2019 | 2019 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35118438 | BR-11-01-W (E) FOSTER RD, PARB | 117665053 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/26/2020 | ED.17-T330700000.STRU.POLE | PARADISE T3307 POLES | 004 | BUTTE COUNTY | 5786123 | 08W Rebuild | 0.000 | 0.000 | 08W | 07/30/2019 | 2019 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 3023.83
35118502 | BR-06-01-W (E) DELIA WAY, PARB | 117665302 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/26/2020 | ED.17-S342100000.STRU.POLE | PARADISE S3421 POLES | 004 | BUTTE COUNTY | 5786123 | 08W Rebuild | 0.000 | 0.000 | 08W | 07/30/2019 | 2019 | # | #VALUE! | ESTS | E470 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 79248.63
35118504 | BR-06-02-W (E) COPELAND RD PARB | 117665914 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/26/2020 | ED.17-T330400000.STRU.POLE | PARADISE T3304 POLES | 004 | BUTTE COUNTY | 5786123 | 08W Rebuild | 0.000 | 0.000 | 08W | 07/30/2019 | 2019 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35118511 | BR-06-03-W (E) DEL MAR AVE PARB | 117666940 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/26/2020 | ED.17-T330500000.STRU.POLE | PARADISE T3305 POLES | 004 | BUTTE COUNTY | 5786123 | 08W Rebuild | 0.000 | 0.000 | 08W | 07/30/2019 | 2019 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35118513 | BR-06-04-W (E) HEAVENLY PARB | 117667199 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/26/2020 | JY | JUNK YARD FL TO HOLD DELETED DATA | 004 | BUTTE COUNTY | 5786123 | 08W Rebuild | 0.000 | 0.000 | 08W | 07/30/2019 | 2019 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35118515 | BR-07-02-W (E) YOUNG AVE PARB | 117667802 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/26/2020 | ED.17-S342200000.STRU.POLE | PARADISE S3422 POLES | 004 | BUTTE COUNTY | 5786123 | 08W Rebuild | 0.000 | 0.000 | 08W | 07/30/2019 | 2019 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35118516 | BR-07-04-W_03 (E) PECK LN PARB | 117668385 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/26/2020 | ED.17-T340200000.STRU.POLE | PARADISE T3402 POLES | 004 | BUTTE COUNTY | 5786123 | 08W Rebuild | 0.000 | 0.000 | 08W | 07/30/2019 | 2019 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35118517 | BR-07-05-W (E) FLICKER LN, PARB | 117668710 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/26/2020 | JY | JUNK YARD FL TO HOLD DELETED DATA | 004 | BUTTE COUNTY | 5786123 | 08W Rebuild | 0.000 | 0.000 | 08W | 07/30/2019 | 2019 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 1115629.62
35118518 | BR-07-06-W (E) NIELSEN DR PARB | 117668717 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/26/2020 | JY | JUNK YARD FL TO HOLD DELETED DATA | 004 | BUTTE COUNTY | 5786123 | 08W Rebuild | 0.000 | 0.000 | 08W | 07/30/2019 | 2019 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 188.32
35118519 | BR-07-08-W (E) FOLAND RD PARB | 117668843 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/26/2020 | ED.17-T340600000.STRU.POLE | PARADISE T3406 POLES | 004 | BUTTE COUNTY | 5786123 | 08W Rebuild | 0.000 | 0.000 | 08W | 07/30/2019 | 2019 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 72.17
35118662 | BR-11-07-W (E) APPLE LN PARB | 117670907 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/26/2020 | ED.17-T322000000.STRU.POLE | PARADISE T3220 POLES | 004 | BUTTE COUNTY | 5786123 | 08W Rebuild | 0.000 | 0.000 | 08W | 07/31/2019 | 2019 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35118663 | BR-01-01-W (E) HEAVENS GATE PARB | 117670940 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/26/2020 | ED.17-S331700000.STRU.POLE | PARADISE S3317 POLES | 004 | BUTTE COUNTY | 5786123 | 08W Rebuild | 0.000 | 0.000 | 08W | 07/31/2019 | 2019 | # | #VALUE! | UNSC | E470 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 772850.55
35118671 | BR-MG-1A-W DRAKE CT PARB | 117673517 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/26/2020 | ED.17-R342100000.STRU.POLE | PARADISE R3421 POLES | 004 | BUTTE COUNTY | 5786123 | 08W Rebuild | 0.000 | 0.000 | 08W | 07/31/2019 | 2019 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35118673 | BR-MG-4A-W WICHITA DR PARB | 117673635 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/26/2020 | ED.17-S330400000.STRU.POLE | PARADISE S3304 POLES | 004 | BUTTE COUNTY | 5786123 | 08W Rebuild | 0.000 | 0.000 | 08W | 07/31/2019 | 2019 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35118674 | BR-MG-05-W PUEBLO DR PARB | 117673731 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/26/2020 | ED.17-S330500000.STRU.POLE | PARADISE S3305 POLES | 004 | BUTTE COUNTY | 5786123 | 08W Rebuild | 0.000 | 0.000 | 08W | 07/31/2019 | 2019 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35118675 | BR-MG-05-W SHAW CIR PARB | 117673779 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/26/2020 | JY | JUNK YARD FL TO HOLD DELETED DATA | 004 | BUTTE COUNTY | 5786123 | 08W Rebuild | 0.000 | 0.000 | 08W | 07/31/2019 | 2019 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35118700 | BR-10-01-W (E) STARLIGHT CT PARB | 117668855 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/26/2020 | ED.17-T321500000.STRU.POLE | PARADISE T3215 POLES | 004 | BUTTE COUNTY | 5786123 | 08W Rebuild | 0.000 | 0.000 | 08W | 07/30/2019 | 2019 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35118701 | *CANC* BR-10-02-W (E) CIRCLEWOOD DR, PA | 117668858 | # | Not assigned | 40 | Closed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/26/2020 | ED.17-T321500000.STRU.POLE | PARADISE T3215 POLES | 004 | BUTTE COUNTY | 5786123 | 08W Rebuild | 0.000 | 0.000 | 08W | 07/30/2019 | 2019 | 11/05/2020 | 2020 | CLSD | E470 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | -191.67
35118702 | BR-11-03-W (E) GREGS WAY, PARB | 117669020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/26/2020 | JY | JUNK YARD FL TO HOLD DELETED DATA | 004 | BUTTE COUNTY | 5786123 | 08W Rebuild | 0.000 | 0.000 | 08W | 07/30/2019 | 2019 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 297541.88
35118925 | STOCKTON A 1106 WIREDOWN RECONDUCTOR | 117697734 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 02/02/2022 | ED.16237.1106 | STOCKTON A 1106 | 039 | SAN JOAQUIN CO | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 08/01/2019 | 2019 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 3037.29
35119401 | CWSP - CAMP EVERS 2106 - 5020 - PHASE 2 | 114758056 | # | Not assigned | 30 | Technically Completed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/30/2020 | ED.08362.2106 | CAMP EVERS 2106 | 044 | SANTA CRUZ COU | 5535211 | CWSP SPO - SH 08 | 5,683.000 | 5,642.000 | 08W | 08/07/2019 | 2019 | # | #VALUE! | FICL | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - CAMP EVERS 2106 - 5020 - PHASE 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 1276770.87
35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E | 117721840 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.08202.1106 | LOS GATOS 1106 | 043 | SANTA CLARA CO | 5535211 | CWSP SPO - SH 08 | 4,483.000 | 0.000 | 08W | 08/07/2019 | 2019 | # | #VALUE! | CONS | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Los Gatos 1106 - LB44 - Ph 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 294131.27
35119966 | CWSP - LOS GATOS 1106 - LB44 - PH 2.6F | 117721841 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.08202.1106 | LOS GATOS 1106 | 043 | SANTA CLARA CO | 5535211 | CWSP SPO - SH 08 | 4,325.000 | 4,309.000 | 08W | 08/07/2019 | 2019 | # | #VALUE! | DOCC | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Los Gatos 1106 - LB44 - Ph 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 783445.01
35119967 | CWSP - LOS GATOS 1106 - LB44 - PH 3.5 | 117721746 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.08202.1106 | LOS GATOS 1106 | 043 | SANTA CLARA CO | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 08/07/2019 | 2019 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Los Gatos 1106 - LB44 - Ph 3.1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 4206.33
35119968 | CWSP - LOS GATOS 1106 - LB44 - PH 3.6 | 117721842 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.08202.1106 | LOS GATOS 1106 | 043 | SANTA CLARA CO | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 08/07/2019 | 2019 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Los Gatos 1106 - LB44 - Ph 3.1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 4982.5
35119969 | CWSP - LOS GATOS 1106 - LB44 - PH 4.2 | 117721748 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.08202.1106 | LOS GATOS 1106 | 043 | SANTA CLARA CO | 5535211 | CWSP SPO - SH 08 | 6,777.000 | 0.000 | 08W | 08/07/2019 | 2019 | # | #VALUE! | CONS | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - LOS GATOS 1106 - LB44 - PHASE 4 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 1142816.88
35119970 | CWSP - LOS GATOS 1106 - LB44 - PH 4.3 | 117721839 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.08202.1106 | LOS GATOS 1106 | 043 | SANTA CLARA CO | 5535211 | CWSP SPO - SH 08 | 3,090.000 | 0.000 | 08W | 08/07/2019 | 2019 | # | #VALUE! | DOCC | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - LOS GATOS 1106 - LB44 - PHASE 4 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 1368128.69
35119972 | CWSP - LOS GATOS 1106 - LB44 - PHASE 4 | 114749460 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/30/2020 | ED.08202.1106 | LOS GATOS 1106 | 043 | SANTA CLARA CO | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 08/07/2019 | 2019 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - LOS GATOS 1106 - LB44 - PHASE 4 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 83068.5
35120949 | CWSP- BUCOCAMP - SKYWAY PARADISE TIE PH2 | 117755982 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 02/28/2020 | ED.16-T312000000.STRU.POLE | CHICO MAP T3120 POLES | 004 | BUTTE COUNTY | 5790010 | CWSP - BUCOCAMP-SKYWAY PARADISE TIE PH2 | 20,644.000 | 10,150.000 | 08W | 08/14/2019 | 2019 | # | #VALUE! | PEND | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 11891055.33
35121414 | KINGSBURG 1116 - RECONDUTORING 3000 FT | 111612187 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/29/2022 | ED.25224.1116 | KINGSBURG 1116 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 08/16/2019 | 2019 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 4748.05
35121739 | *CANCEL* CENTERILLE REMOVAL - BUTTE 1105 | 117781072 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.10308.1105 | BUTTE 1105 | 004 | BUTTE COUNTY | 5786123 | 08W Rebuild | 0.000 | 0.000 | 08W | 08/21/2019 | 2019 | 09/01/2019 | 2019 | CLSD | E460 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35121772 | GANSO 1104 RECOND 2900FT TO 2AR | 113723017 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/30/2022 | ED.25454.1104 | GANSO 1104 | 015 | KERN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 08/19/2019 | 2019 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 14274.83
35121909 | CLOVIS 2110 RECOND 1042FT 2AR | 117778550 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/28/2022 | ED.25408.2110 | CLOVIS 2110 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 08/20/2019 | 2019 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 587.25
35122142 | RECON 1684 FT 6CU W 397AL | 117781600 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/20/2022 | ED.18301.1101 | MORRO BAY 1101 | 040 | SAN LUIS OBISP | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 08/21/2019 | 2019 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 195.75
35122447 | *CANC* CARUTHERS 1104 RECOND 5,10*CANC | 117784137 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/28/2022 | ED.25237.1104 | CARUTHERS 1104 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 08/21/2019 | 2019 | 10/03/2019 | 2019 | CLSD | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
35123421 | R1 WIREDOWN RECONDUCTORING H-1110 | 109234173 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/26/2015 | ED.02210.1110.SWIT | SWITCHES | 041 | SAN MATEO COUN | 5517127 | DO 08 - Monthly Forecast Only | 203.000 | 0.000 | 08J | 08/29/2019 | 2019 | # | #VALUE! | ESTS | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 2124.3
35123422 | PUEBLO 2102 RECOND | 112416557 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/30/2017 | ED.42-II35240000.STRU.POLE | SILVERADO MAP II3524 POLES | 028 | NAPA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 903.000 | 0.000 | 08J | 08/29/2019 | 2019 | # | #VALUE! | UNSC | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 1597.03
35123423 | +RECON BEYOND FCO 45133, SISQUOC 1104 | 112149414 | # | Not assigned | 30 | Technically Completed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/09/2018 | ED.18281.1104 | SISQUOC 1104 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 526.000 | 526.000 | 08J | 08/29/2019 | 2019 | # | #VALUE! | FICL | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 38332.34
35123424 | RECON 815 FT TAP OFF LAUGHLIN CAPELLA 01 | 113751593 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/27/2019 | ED.04341.1101.RECL | RECLOSERS | 023 | MENDOCINO COUN | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 08/29/2019 | 2019 | # | #VALUE! | ESTS | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 13671.89
35123425 | R2 RECONDUCT SALINAS 1106 | 112533471 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/30/2018 | ED.18201.1106 | SALINAS 1106 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 1,011.000 | 0.000 | 08J | 08/29/2019 | 2019 | # | #VALUE! | PEND | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 535.39
35123426 | WHISMAN 1106 CO582085 REPL 1100FT OH LN | 112726448 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/20/2019 | ED.08363.1106.TXFR.TROH | OVERHEAD TRANSFORMERS | 043 | SANTA CLARA CO | 5517127 | DO 08 - Monthly Forecast Only | 1,282.000 | 0.000 | 08J | 08/29/2019 | 2019 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 3341.97
35123427 | R7 SAN RAFAEL 1105 RECOND 1,225 FT | 112416508 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/30/2017 | ED.40-TT33090000.STRU.POLE | NORTH BAY MAP TT3309 POLES | 021 | MARIN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 08/29/2019 | 2019 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 6449.58
35123428 | PN WIREDOWN 17-0043197 DC-1112 | 112928898 | # | Not assigned | 30 | Technically Completed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/28/2018 | ED.02264.1112.SWIT | SWITCHES | 041 | SAN MATEO COUN | 5505513 | PN-OH ANNEALED/DETER CNDCTR: PM MGD | 0.000 | 0.000 | 08J | 08/29/2019 | 2019 | # | #VALUE! | DCNL | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 51414.66
35123429 | R2WATSNVILLE 2101 HIGH SPLICE COND REPL | 111767919 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/30/2018 | JY | JUNK YARD FL TO HOLD DELETED DATA | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 1,741.000 | 0.000 | 08J | 08/29/2019 | 2019 | # | #VALUE! | CONS | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 43052.11
35123430 | 2019 08J PN EG-1101 S072CC216 | 113227750 | # | Not assigned | 30 | Technically Completed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/27/2019 | ED.02257.1101.TXFR.TROH | OVERHEAD TRANSFORMERS | 041 | SAN MATEO COUN | 5505513 | PN-OH ANNEALED/DETER CNDCTR: PM MGD | 0.000 | 0.000 | 08J | 08/29/2019 | 2019 | # | #VALUE! | DCNL | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 50123.75
35123901 | R1-EB- R1127- RECOND 1,850' OF 6CU | 110568251 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/31/2016 | ED.01347.1127 | RICHMOND R 1127 | 007 | CONTRA COSTA C | 5535457 | DO 08 - Monthly Forecast Only | 1,744.000 | 0.000 | 08J | 08/30/2019 | 2019 | # | #VALUE! | PEND | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 12972.36
35123902 | RECONDUCTOR ATWATER 1106 - WIRE DOWN | 112841452 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/13/2019 | ED.25361.1106 | ATWATER 1106 | 024 | MERCED COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 08/30/2019 | 2019 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 566.81
35123903 | NEW HOPE 1101 2,200FT RECONDUCTOR | 112421160 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 07/09/2021 | ED.16208.1101 | NEW HOPE 1101 | 039 | SAN JOAQUIN CO | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 08/30/2019 | 2019 | # | #VALUE! | ESTS | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 5259.42
35123904 | R2 ATWATER 1103 RECONDUCTORING | 113199100 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 04/02/2021 | ED.72-06124C0000.STRU.POLE | MERCED MAP 06124C POLES | 024 | MERCED COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 08/30/2019 | 2019 | # | #VALUE! | ADER | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 7955.71
35123905 | 2019 VALLEJO B 413 HIGH SPLICE COUNT | 113144866 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2019 | ED.04245.0413 | VALLEJO B 0413 | 048 | SOLANO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 1,998.000 | 0.000 | 08J | 08/30/2019 | 2019 | # | #VALUE! | PEND | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 15826.86
35123906 | +RECOND 10 SPAN 2442 4ACSR W 2ACSR | 112434990 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/27/2020 | ED.18281.1103 | SISQUOC 1103 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 2,442.000 | 2,442.000 | 08J | 08/30/2019 | 2019 | 07/04/2020 | 2020 | CLSD | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 87833.97
35123907 | RECONDUCT CASTROVILLE 2104 WD#16-0083838 | 112421980 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/29/2018 | ED.18235.2104 | CASTROVILLE 2104 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 2,648.000 | 0.000 | 08J | 08/30/2019 | 2019 | # | #VALUE! | CONS | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 101379.15
35123908 | +RECONDUCTOR - FUSE ZONE - SM1109 CKT | 113740510 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.18267.1109 | SANTA MARIA 1109 | 015 | KERN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 1,612.000 | 0.000 | 08J | 08/30/2019 | 2019 | # | #VALUE! | UNSC | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 27579.55
35123909 | RECOND 21SPANS,GRAND AV & LE SAGE,GROVER | 112742262 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.18260.1106 | OCEANO 1106 | 040 | SAN LUIS OBISP | 5535457 | DO 08 - Monthly Forecast Only | 3,305.000 | 0.000 | 08J | 08/30/2019 | 2019 | # | #VALUE! | PEND | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 32162.86
35123910 | D-1105 RECOND 3,260 FT OF 6CU | 111984232 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/23/2017 | ED.01204.1105.SWIT | SWITCHES | 001 | ALAMEDA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 08/30/2019 | 2019 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 22691.31
35124839 | RECON 3362 CIRCUIT FT OF 4ACSR WITH 2CU | 117814362 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/27/2022 | ED.18260.1102 | OCEANO 1102 | 040 | SAN LUIS OBISP | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 09/03/2019 | 2019 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
35125400 | ELK HILLS 1104 OH SPLICE FUSE 19082 | 113718468 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2021 | ED.25244.1104 | ELK HILLS 1104 | 015 | KERN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 09/03/2019 | 2019 | # | #VALUE! | UNSC | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 23094.03
35125401 | R7 BASALT 1106 WIRE DOWN AT LR 682 | 111391279 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/30/2017 | ED.04246.1106 | BASALT 1106 | 028 | NAPA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 3,142.000 | 0.000 | 08J | 09/03/2019 | 2019 | # | #VALUE! | PEND | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 18473.41
35125402 | RECOND 3400FT OF 4ACSR WITH 2ACSR SOLEDA | 112436787 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 07/28/2017 | ED.18205.2102 | SOLEDAD 2102 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 3,417.000 | 0.000 | 08J | 09/03/2019 | 2019 | # | #VALUE! | UNSC | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 35125402 RECOND 3400FT OF 4ACSR WITH 2AC | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 66946.59
35125403 | TERMINOUS 1102 RECONDUCTOR | 112846354 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 05/28/2021 | ED.16302.1102 | TERMINOUS 1102 | 039 | SAN JOAQUIN CO | 5535457 | DO 08 - Monthly Forecast Only | 3,420.000 | 0.000 | 08J | 09/03/2019 | 2019 | # | #VALUE! | PEND | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 16170.21
35125404 | 2019 08J PN DC-1112 WIREDOWN 17-0067848 | 113198746 | # | Not assigned | 30 | Technically Completed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2019 | ED.02264.1112.SWIT | SWITCHES | 041 | SAN MATEO COUN | 5505513 | PN-OH ANNEALED/DETER CNDCTR: PM MGD | 0.000 | 0.000 | 08J | 09/03/2019 | 2019 | # | #VALUE! | DCNL | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 52547.06
35125405 | RECON 3,750' MESA 1101 THOMPSON,NIPOMO | 113791781 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2021 | ED.18281.1101 | SISQUOC 1101 | 040 | SAN LUIS OBISP | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 09/03/2019 | 2019 | # | #VALUE! | ESTS | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 5470.78
35125406 | RECOND: E NICOLAUS 1102 SAC AVE @ HWY 99 | 112171181 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/29/2017 | ED.11-U220000000 | MARYSVILLE MAP U22 | 051 | SUTTER COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 09/03/2019 | 2019 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 10638.49
35125407 | R2 RECOND19 SPANS 5451FT | 112534740 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2021 | ED.18257.1103 | DIVIDE 1103 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 09/03/2019 | 2019 | # | #VALUE! | ESTS | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 2866.34
35125408 | BOWLES 1104 RECONDUCTOR | 112409769 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 08/31/2021 | ED.25353.1104 | BOWLES 1104 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 5,536.000 | 0.000 | 08J | 09/03/2019 | 2019 | # | #VALUE! | ESTS | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 28083.88
35125409 | 2019 WILLOW PASS 2108 HIGH SPLICE COUNT | 113145564 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/10/2021 | ED.01391.2108 | WILLOW PASS 2108 | 007 | CONTRA COSTA C | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 09/04/2019 | 2019 | # | #VALUE! | PEND | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 39465.69
35125410 | RECON 6598', VARIOUS LOCATIONS W.MAIN SM | 110770782 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2021 | ED.18267.1109 | SANTA MARIA 1109 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 09/04/2019 | 2019 | # | #VALUE! | ESTS | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 18018.82
35125411 | HAMILTON A 1101 6,600' | 112996389 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/30/2019 | ED.10212.1101.REGL | REGULATORS | 011 | GLENN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 09/04/2019 | 2019 | # | #VALUE! | ESTS | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 11005.43
35125412 | DEEPWATER 1107 RECONDUCTOR EXCESS SPLICE | 112169821 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 11/17/2018 | ED.06362.1107.RECL | RECLOSERS | 057 | YOLO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 8,438.000 | 0.000 | 08J | 09/04/2019 | 2019 | # | #VALUE! | ESTS | E470 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 9632.96
35125413 | R2RPL OH WIRE ON DOLN RD-1104 17-0061463 | 113181522 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 06/28/2019 | ED.18235.2103.SWIT | SWITCHES | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 10,056.000 | 0.000 | 08J | 09/04/2019 | 2019 | # | #VALUE! | PEND | E470 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 31049.93
35125414 | 2018 OH COND RPLC: EUREKA E 1104 | 112143284 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 10/10/2018 | ED.19233.1104.SWIT | SWITCHES | 012 | HUMBOLDT COUNT | 5535457 | DO 08 - Monthly Forecast Only | 9,200.000 | 0.000 | 08J | 09/04/2019 | 2019 | # | #VALUE! | ADER | E470 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 53845.06
35125680 | 2019 PUEBLO 1104 HIGH SPLICE COUNT 1 | 113145266 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2019 | ED.04329.1104 | PUEBLO 1104 | 028 | NAPA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 09/05/2019 | 2019 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 11294.25
35125681 | 2021 FAIRHAVEN 1103 DET WIRE PHASE 2 | 114627401 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 11/01/2021 | ED.19245.1103.SWIT | SWITCHES | 012 | HUMBOLDT COUNT | 5535457 | DO 08 - Monthly Forecast Only | 10,100.000 | 0.000 | 08J | 09/05/2019 | 2019 | # | #VALUE! | ESTS | E470 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 17240.5
35125682 | RECONDUCTOR KINGSBURG 1113 - AVE 368 | 113242772 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 06/30/2020 | ED.25224.1113 | KINGSBURG 1113 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 10,494.000 | 0.000 | 08J | 09/05/2019 | 2019 | # | #VALUE! | PEND | E470 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 34848.04
35125683 | R2 RECON 10649' SISQUOC 1104_ FUSE 46147 | 112149755 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.18281.1104 | SISQUOC 1104 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 13,506.000 | 0.000 | 08J | 09/05/2019 | 2019 | # | #VALUE! | ESTS | E470 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 9826.81
35125684 | R2RPL OH WIRE ON GONZALES1104 18-0003089 | 114259452 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 10/31/2020 | ED.05-K132500000.STRU.POLE | SALINAS K1325 POLES | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 09/05/2019 | 2019 | # | #VALUE! | ESTS | E470 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 46009.29
35125685 | KINGSBURG 1111 RECOND 12,000' OF 6 CU | 113728737 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 03/31/2020 | ED.25224.1111 | KINGSBURG 1111 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 11,926.000 | 0.000 | 08J | 09/05/2019 | 2019 | # | #VALUE! | PEND | E470 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 64150.52
35125686 | R2 RPL OH WIRE ON DOLANRD-1101 S012CC106 | 113249203 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 06/28/2019 | ED.05-D082000000.STRU.POLE | SALINAS D0820 POLES | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 09/05/2019 | 2019 | # | #VALUE! | ESTS | E470 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 15073.79
35125687 | 2020 FAIRHAVEN 1103 DET WIRE PHASE 1 | 114627400 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 11/02/2020 | ED.19245.1103.SWIT | SWITCHES | 012 | HUMBOLDT COUNT | 5535457 | DO 08 - Monthly Forecast Only | 12,800.000 | 0.000 | 08J | 09/05/2019 | 2019 | # | #VALUE! | ESTS | E470 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 12685.43
35125688 | COTATI 1103 RECONDUCTOR ON MIDDLE RD | 114496935 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 06/01/2021 | ED.04227.1103.SWIT | SWITCHES | 021 | MARIN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 14,256.000 | 0.000 | 08J | 09/05/2019 | 2019 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 18629.43
35125689 | SEMITROPIC 1110 RECOND 14,921' WITH 2AR | 113818681 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 04/01/2021 | ED.25290.1110 | SEMITROPIC 1110 | 015 | KERN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 09/05/2019 | 2019 | # | #VALUE! | ESTS | E470 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 12974.92
35125690 | BAYWOOD 1101 CUESTA COLLEGE 08J | 113820469 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.18280.1101 | BAYWOOD 1101 | 040 | SAN LUIS OBISP | 5517127 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 09/05/2019 | 2019 | # | #VALUE! | ESTS | E470 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 16149CIRCUIT FT(52 SPANS) 4ACSR&6CU W2CU | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 16269.67
35125691 | ELK HILLS 1104 OH SPLICE SSD1523 | 113718541 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.25244.1104 | ELK HILLS 1104 | 020 | MADERA COUNTY | 5517127 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 09/05/2019 | 2019 | # | #VALUE! | ESTS | E470 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | ELK HILLS 1104 OH SPLICE SSD1523 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 24430.37
35125692 | R2 OLD RIVER 1102 ANNEALD CONDUCTO | 113634733 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 08/31/2021 | ED.25282.1102.RECL | RECLOSERS | 015 | KERN COUNTY | 5517127 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 09/05/2019 | 2019 | # | #VALUE! | PEND | E470 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | R2OLD RIVR 1102 REPLACE ANNEALD CONDUCTO | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 19402.6
35125693 | RECOND WATSONVILLE 2101 REF# S074CC218 | 113665277 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/29/2019 | ED.08333.2101 | WATSONVILLE 2101 | 027 | MONTEREY COUNT | 5517127 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 09/05/2019 | 2019 | # | #VALUE! | ESTS | E470 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | RECOND WATSONVILLE 2101 REF# S074CC218 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 8986.32
35127310 | VASONA-1101 RECON 350 FT 4AR W 4/0AL | 117886071 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 02/19/2021 | ED.08377.1101.SECT | SECTIONALIZERS | 043 | SANTA CLARA CO | 5517127 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 09/16/2019 | 2019 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 824.72
35127412 | R2 EL CAPITAN 1104 RECON - WD | 113740620 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2021 | ED.72-0713151000.STRU.POLE | MERCED MAP 0713151 POLES | 024 | MERCED COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 09/17/2019 | 2019 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 2195.12
35127413 | RECONDUCTOR_15 SPANS_3254FT IN FCO 45625 | 112435460 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/27/2017 | ED.18281.1102 | SISQUOC 1102 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 09/17/2019 | 2019 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 4515.82
35127414 | R2RPLC OH WIRE ON GABILN 1101 17-0026725 | 112839904 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/30/2019 | ED.18233.1101 | GABILAN 1101 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 09/17/2019 | 2019 | # | #VALUE! | PEND | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 24781.91
35127415 | SM 1109, N/O 1586 W MAIN, SM | 111957931 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2021 | ED.18267.1109 | SANTA MARIA 1109 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 09/17/2019 | 2019 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 8460.49
35127416 | RE-COND 6260 CIRCUIT FT 4ACSRS W 2C | 114155922 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 01/05/2019 | ED.18206.1104 | FAIRWAY 1104 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 09/17/2019 | 2019 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 990.97
35127417 | CAB 1104 DOUGLASS AVE, LOMPOC | 112180702 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/22/2018 | ED.18310.1104 | CABRILLO 1104 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 09/17/2019 | 2019 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 2531.9
35127418 | 2019 PUEBLO 1104 HIGH SPLICE COUNT | 113163076 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2019 | ED.04329.1104 | PUEBLO 1104 | 028 | NAPA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 09/17/2019 | 2019 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 2547.3
35127419 | RECONDUCTOR - FUSE ZONE - SM1106 CKT | 113740518 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2018 | ED.18267.1106 | SANTA MARIA 1106 | 015 | KERN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 09/17/2019 | 2019 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 1773.27
35127620 | RECOND_5656FT 3-6CU 1231FT3-4ACSR W3 2CU | 112769006 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 02/14/2019 | ED.18282.1102 | MESA 1102 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 09/17/2019 | 2019 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 871
35127710 | SAN BENITO 2104 LS CO409 REC 2600FT OH | 117887579 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/29/2021 | JY | JUNK YARD FL TO HOLD DELETED DATA | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 09/18/2019 | 2019 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 1274.41
35128940 | R2 CANAL 1103 RECONDUCTORING | 112551915 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2021 | ED.25209.1103 | CANAL 1103 | 024 | MERCED COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 09/19/2019 | 2019 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 3889.24
35128952 | 2019 NORTH TOWER 2201 HIGH SPLICE COUNT | 113145836 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2019 | ED.04204.2201 | NORTH TOWER 2201 | 048 | SOLANO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 09/19/2019 | 2019 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 5695.8
35128962 | RECOND HWY 20 - FTBRAGG 1102 | 112779271 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 07/05/2022 | ED.04276.1102.CAPA | CAPACITORS | 023 | MENDOCINO COUN | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 09/19/2019 | 2019 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 2100.31
35128973 | STOREY 1109 - RECONDUCTOR | 113779806 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 01/12/2022 | ED.72-11182D0000.STRU.POLE | YOSEMITE MAP 11182D POLES | 020 | MADERA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 09/19/2019 | 2019 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 2572.02
35128985 | R2 NEWMAN 1106 REPLACE OH CONDUCTOR | 113821907 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.16274.1106 | NEWMAN 1106 | 050 | STANISLAUS COU | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 09/19/2019 | 2019 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 4211.34
35129012 | R2 BANTA 1101 RECONDUCTORING - WIREDOWN | 114271062 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 07/21/2021 | ED.16247.1101 | BANTA 1101 | 039 | SAN JOAQUIN CO | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 09/19/2019 | 2019 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 1459.86
35129023 | R2 RPL OH WIRE ON DOLANRD-1104 S020CC113 | 113249064 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 06/28/2019 | ED.05-E072400000.STRU.POLE | SALINAS E0724 POLES | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 09/19/2019 | 2019 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 410.88
35129024 | EIGHT MILE 2101 - RECONDUCTOR | 113779436 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 03/29/2019 | ED.93-Q091200000.STRU.POLE | STOCKTON Q0912 POLES | 039 | SAN JOAQUIN CO | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 09/19/2019 | 2019 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 7375.02
35129025 | R2 2019 MARICOPA 1102 RECONDUCTORING | 113263505 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 06/30/2021 | ED.66-1123300000.STRU.POLE | KERN 11233 POLES | 015 | KERN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 09/19/2019 | 2019 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 2970.43
35129026 | RECONDUCTOR KINGSBURG 1112 | 113246468 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 09/30/2022 | ED.25224.1112 | KINGSBURG 1112 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 09/19/2019 | 2019 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 15116.4
35129027 | R2 RPL OH WIRE ON DOLAN RD1101 S040CC207 | 113725829 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 06/28/2019 | ED.05-E071000000.STRU.POLE | SALINAS E0710 POLES | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 09/19/2019 | 2019 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 22908.34
35129028 | RECONDUCTOR AR W/AL - MESA 1101 | 114036571 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/15/2021 | ED.18282.1101 | MESA 1101 | 040 | SAN LUIS OBISP | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 09/19/2019 | 2019 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 5376.84
35129030 | REEDLEY 1110 RECONDUCTOR 12,271FT OF 6CU | 114231286 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 03/31/2021 | ED.25234.1110 | REEDLEY 1110 | 054 | TULARE COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 09/19/2019 | 2019 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 4499.69
35129031 | BIOLA 1104 RECONDUCTOR 13,014 FT OF 6CU | 113219231 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 06/30/2021 | ED.25221.1104 | BIOLA 1104 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 09/19/2019 | 2019 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 5571.82
35129032 | STONE CORRAL 1110 RECOND 19,622'/W 4/OAL | 113817426 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 06/28/2019 | ED.25292.1110 | STONE CORRAL 1110 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 09/19/2019 | 2019 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | STONE CORRAL 1110 RECOND 19,622'/W 4/OAL | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 408.59
35129304 | CWSP - ORO FINO 1102 - LR2560 PH 1.2 | 117872785 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1102 | ORO FINO 1102 | 004 | BUTTE COUNTY | 5786759 | CWSP - ORO FINO 1102 - LR2560 PH 1.2 | 9,289.000 | 0.000 | 08W | 09/21/2019 | 2019 | # | #VALUE! | ADER | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-ORO FINO 1102 LR-2560 PH 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 66823.86
35129305 | CWSP - ORO FINO 1102 - LR2560 PH 1.3 | 117872786 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1102 | ORO FINO 1102 | 004 | BUTTE COUNTY | 5786760 | CWSP - ORO FINO 1102 - LR2560 PH 1.3 | 2,947.000 | 0.000 | 08W | 09/21/2019 | 2019 | # | #VALUE! | UNSC | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-ORO FINO 1102 LR-2560 PH 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 162317.62
35129306 | CWSP - ORO FINO 1102 - LR2560 PH 1.4 | 117872787 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1102 | ORO FINO 1102 | 004 | BUTTE COUNTY | 5786761 | CWSP - ORO FINO 1102 - LR2560 PH 1.4 | 7,124.000 | 0.000 | 08W | 09/21/2019 | 2019 | # | #VALUE! | PEND | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-ORO FINO 1102 LR-2560 PH 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 47015.13
35129307 | CWSP - ORO FINO 1102 - LR2560 PH 1.5 | 117872788 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1102 | ORO FINO 1102 | 004 | BUTTE COUNTY | 5786762 | CWSP - ORO FINO 1102 - LR2560 PH 1.5 | 8,419.000 | 0.000 | 08W | 09/21/2019 | 2019 | # | #VALUE! | UNSC | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-ORO FINO 1102 LR-2560 PH 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 310835.74
35129308 | CWSP - ORO FINO 1102 - LR2560 PH 2.2 | 117873010 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1102 | ORO FINO 1102 | 004 | BUTTE COUNTY | 5786763 | CWSP - ORO FINO 1102 - LR2560 PH 2.2 | 7,553.000 | 0.000 | 08W | 09/21/2019 | 2019 | # | #VALUE! | ESTS | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-ORO FINO 1102 LR-2560 PH 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 37009.42
35129309 | CWSP - ORO FINO 1102 - LR2560 PH 2.3 | 117873011 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1102 | ORO FINO 1102 | 004 | BUTTE COUNTY | 5786764 | CWSP - ORO FINO 1102 - LR2560 PH 2.3 | 8,020.000 | 0.000 | 08W | 09/21/2019 | 2019 | # | #VALUE! | UNSC | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-ORO FINO 1102 LR-2560 PH 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 29762.36
35129310 | CWSP - ORO FINO 1102 - LR2560 PH 2.4 | 117873012 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1102 | ORO FINO 1102 | 004 | BUTTE COUNTY | 5786765 | CWSP - ORO FINO 1102 - LR2560 PH 2.4 | 10,110.000 | 0.000 | 08W | 09/21/2019 | 2019 | # | #VALUE! | PEND | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-ORO FINO 1102 LR-2560 PH 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 32261.12
35129311 | CWSP - ORO FINO 1102 - LR2560 PH 2.5 | 117873013 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1102 | ORO FINO 1102 | 004 | BUTTE COUNTY | 5786766 | CWSP - ORO FINO 1102 - LR2560 PH 2.5 | 13,202.000 | 0.000 | 08W | 09/21/2019 | 2019 | # | #VALUE! | PEND | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-ORO FINO 1102 LR-2560 PH 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 39401.04
35129434 | CWSP - ORO FINO 1102 - LR76008 PH 1.2 | 117873015 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1102 | ORO FINO 1102 | 004 | BUTTE COUNTY | 5786767 | CWSP - ORO FINO 1102 - LR76008 PH 1.2 | 10,059.000 | 0.000 | 08W | 09/23/2019 | 2019 | # | #VALUE! | PEND | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-ORO FINO 1102 LR-76008 PH 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 162370.49
35129435 | CWSP - ORO FINO 1102 - LR76008 PH 1.3 | 117873016 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1102 | ORO FINO 1102 | 004 | BUTTE COUNTY | 5786768 | CWSP - ORO FINO 1102 - LR76008 PH 1.3 | 10,727.000 | 0.000 | 08W | 09/23/2019 | 2019 | # | #VALUE! | UNSC | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-ORO FINO 1102 LR-76008 PH 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 110030.22
35129436 | CWSP - ORO FINO 1102 - LR76008 PH 1.4 | 117873017 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1102 | ORO FINO 1102 | 004 | BUTTE COUNTY | 5786769 | CWSP - ORO FINO 1102 - LR76008 PH 1.4 | 9,426.000 | 0.000 | 08W | 09/23/2019 | 2019 | # | #VALUE! | PEND | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-ORO FINO 1102 LR-76008 PH 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 108594.67
35129437 | CWSP - ORO FINO 1102 - LR76008 PH 1.5 | 117873018 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1102 | ORO FINO 1102 | 004 | BUTTE COUNTY | 5786770 | CWSP - ORO FINO 1102 - LR76008 PH 1.5 | 11,288.000 | 0.000 | 08W | 09/23/2019 | 2019 | # | #VALUE! | PEND | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-ORO FINO 1102 LR-76008 PH 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 115864.56
35129438 | CWSP - ORO FINO 1102 - LR76008 PH 2.2 | 117873019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1102 | ORO FINO 1102 | 004 | BUTTE COUNTY | 5786771 | CWSP - ORO FINO 1102 - LR76008 PH 2.2 | 8,582.000 | 0.000 | 08W | 09/23/2019 | 2019 | # | #VALUE! | PEND | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-ORO FINO 1102 LR-76008 PH 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 124891.45
35129439 | CWSP - ORO FINO 1102 - LR76008 PH 2.3 | 117873030 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1102 | ORO FINO 1102 | 004 | BUTTE COUNTY | 5786772 | CWSP - ORO FINO 1102 - LR76008 PH 2.3 | 9,426.000 | 0.000 | 08W | 09/23/2019 | 2019 | # | #VALUE! | PEND | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-ORO FINO 1102 LR-76008 PH 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 123515.24
35129474 | SF A-1115 WIRE DOWN 08J PROJECT | 112859784 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 08/25/2017 | ED.02203.1115.SWIT | SWITCHES | 038 | SAN FRANCISCO | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 09/23/2019 | 2019 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
35129475 | S SPINGS 1103 - STROLLING HILLS RECOND | 112171180 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/29/2017 | ED.21-J371800000 | EL DORADO MAP J3718 | 009 | EL DORADO COUN | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 09/23/2019 | 2019 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 2543.45
35129476 | 2019 YOSEMITE 401 HIGH SPLICE COUNT | 113163134 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2019 | ED.02249.0401 | YOSEMITE 0401 | 038 | SAN FRANCISCO | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 09/23/2019 | 2019 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 594.54
35129477 | R2 RECONDUCT DOLAN RD 1101 17-0016449 | 112624835 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/30/2018 | ED.18238.1101 | DOLAN ROAD 1101 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 09/23/2019 | 2019 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 756.45
35129478 | SNEATH LANE 1102 WIREDOWN 16-0033827 | 111662862 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/31/2017 | ED.02272.1102.TXFR.TROH | OVERHEAD TRANSFORMERS | 041 | SAN MATEO COUN | 5505513 | PN-OH ANNEALED/DETER CNDCTR: PM MGD | 0.000 | 0.000 | 08J | 09/23/2019 | 2019 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 11891.52
35129479 | SUISUN 1109 RECOND LINE EXCESS SPLICES | 112134521 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/01/2017 | ED.06213.1107.SWIT | SWITCHES | 048 | SOLANO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 09/23/2019 | 2019 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
35129600 | CWSP - ORO FINO 1102 - LR76008 PH 2.4 | 117873031 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1102 | ORO FINO 1102 | 004 | BUTTE COUNTY | 5786773 | CWSP - ORO FINO 1102 - LR76008 PH 2.4 | 5,799.000 | 0.000 | 08W | 09/23/2019 | 2019 | # | #VALUE! | PEND | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-ORO FINO 1102 LR-76008 PH 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 100120.16
35129601 | CWSP - ORO FINO 1102 - LR76008 PH 2.5 | 117873032 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1102 | ORO FINO 1102 | 004 | BUTTE COUNTY | 5786774 | CWSP - ORO FINO 1102 - LR76008 PH 2.5 | 7,829.000 | 0.000 | 08W | 09/23/2019 | 2019 | # | #VALUE! | PEND | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-ORO FINO 1102 LR-76008 PH 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 150007.19
35129602 | CWSP - ORO FINO 1101 - OCB PH 1.2 | 117873033 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1101 | ORO FINO 1101 | 004 | BUTTE COUNTY | 5786745 | CWSP - ORO FINO 1101 - OCB PH 1.2 | 6,446.000 | 0.000 | 08W | 09/23/2019 | 2019 | # | #VALUE! | PEND | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-ORO FINO 1101 OCB PH 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 13286.03
35129603 | CWSP - ORO FINO 1101 - OCB PH 1.3 | 117873034 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1101 | ORO FINO 1101 | 004 | BUTTE COUNTY | 5786746 | CWSP - ORO FINO 1101 - OCB PH 1.3 | 7,042.000 | 0.000 | 08W | 09/23/2019 | 2019 | # | #VALUE! | PEND | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-ORO FINO 1101 OCB PH 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 16240.46
35129604 | CWSP - ORO FINO 1101 - OCB PH 1.4 | 117873035 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1101 | ORO FINO 1101 | 004 | BUTTE COUNTY | 5786747 | CWSP - ORO FINO 1101 - OCB PH 1.4 | 6,845.000 | 0.000 | 08W | 09/23/2019 | 2019 | # | #VALUE! | PEND | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-ORO FINO 1101 OCB PH 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 10765.21
35129605 | CWSP - ORO FINO 1101 - OCB PH 1.5 | 117873036 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1101 | ORO FINO 1101 | 004 | BUTTE COUNTY | 5786748 | CWSP - ORO FINO 1101 - OCB PH 1.5 | 7,525.000 | 0.000 | 08W | 09/23/2019 | 2019 | # | #VALUE! | PEND | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-ORO FINO 1101 OCB PH 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 19734.06
35129606 | CWSP - ORO FINO 1101 - OCB PH 1.6 | 117873037 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1101 | ORO FINO 1101 | 004 | BUTTE COUNTY | 5786749 | CWSP - ORO FINO 1101 - OCB PH 1.6 | 5,401.000 | 0.000 | 08W | 09/23/2019 | 2019 | # | #VALUE! | PEND | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-ORO FINO 1101 OCB PH 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 12782.79
35129607 | CWSP - ORO FINO 1101 - OCB PH 1.7 | 117873038 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1101 | ORO FINO 1101 | 004 | BUTTE COUNTY | 5786750 | CWSP - ORO FINO 1101 - OCB PH 1.7 | 8,189.000 | 0.000 | 08W | 09/23/2019 | 2019 | # | #VALUE! | PEND | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-ORO FINO 1101 OCB PH 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 13648.47
35129608 | CWSP - ORO FINO 1101 - OCB PH 2.2 | 117873039 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1101 | ORO FINO 1101 | 004 | BUTTE COUNTY | 5786751 | CWSP - ORO FINO 1101 - OCB PH 2.2 | 7,762.000 | 0.000 | 08W | 09/23/2019 | 2019 | # | #VALUE! | UNSC | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-ORO FINO 1101 OCB PH 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 26312.78
35129609 | CWSP - ORO FINO 1101 - OCB PH 2.3 | 117873070 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1101 | ORO FINO 1101 | 004 | BUTTE COUNTY | 5786752 | CWSP - ORO FINO 1101 - OCB PH 2.3 | 5,631.000 | 0.000 | 08W | 09/23/2019 | 2019 | # | #VALUE! | PEND | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-ORO FINO 1101 OCB PH 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 52836.71
35129610 | CWSP - ORO FINO 1101 - OCB PH 2.4 | 117873071 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1101 | ORO FINO 1101 | 004 | BUTTE COUNTY | 5786753 | CWSP - ORO FINO 1101 - OCB PH 2.4 | 8,176.000 | 0.000 | 08W | 09/23/2019 | 2019 | # | #VALUE! | PEND | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-ORO FINO 1101 OCB PH 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 41569.65
35129611 | CWSP - ORO FINO 1101 - OCB PH 2.5 | 117873072 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1101 | ORO FINO 1101 | 004 | BUTTE COUNTY | 5786754 | CWSP - ORO FINO 1101 - OCB PH 2.5 | 7,159.000 | 0.000 | 08W | 09/23/2019 | 2019 | # | #VALUE! | PEND | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-ORO FINO 1101 OCB PH 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 22811.85
35129612 | CWSP - ORO FINO 1101 - OCB PH 2.6 | 117873073 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1101 | ORO FINO 1101 | 004 | BUTTE COUNTY | 5786755 | CWSP - ORO FINO 1101 - OCB PH 2.6 | 5,967.000 | 0.000 | 08W | 09/23/2019 | 2019 | # | #VALUE! | PEND | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-ORO FINO 1101 OCB PH 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 17161.69
35129613 | CWSP - ORO FINO 1101 - OCB PH 3.2 | 117873074 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1101 | ORO FINO 1101 | 004 | BUTTE COUNTY | 5786756 | CWSP - ORO FINO 1101 - OCB PH 3.2 | 6,292.000 | 0.000 | 08W | 09/23/2019 | 2019 | # | #VALUE! | PEND | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-ORO FINO 1101 OCB PH 3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 39828.48
35129614 | CWSP - ORO FINO 1101 - OCB PH 3.3 | 117873075 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1101 | ORO FINO 1101 | 004 | BUTTE COUNTY | 5786757 | CWSP - ORO FINO 1101 - OCB PH 3.3 | 9,276.000 | 0.000 | 08W | 09/23/2019 | 2019 | # | #VALUE! | PEND | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-ORO FINO 1101 OCB PH 3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 39995.09
35129615 | CWSP - ORO FINO 1101 - OCB PH 3.4 | 117873076 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1101 | ORO FINO 1101 | 004 | BUTTE COUNTY | 5786758 | CWSP - ORO FINO 1101 - OCB PH 3.4 | 10,907.000 | 0.000 | 08W | 09/23/2019 | 2019 | # | #VALUE! | PEND | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-ORO FINO 1101 OCB PH 3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 1531.57
35129616 | CWSP - ORO FINO 1101 - LR2022 PH 1.2 | 117873077 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1101 | ORO FINO 1101 | 004 | BUTTE COUNTY | 5786672 | CWSP - ORO FINO 1101 - LR2022 PH 1.2 | 8,807.000 | 0.000 | 08W | 09/23/2019 | 2019 | # | #VALUE! | PEND | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - ORO FINO-1101 LR-2022 PH I | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 43696.7
35129617 | CWSP - ORO FINO 1101 - LR2022 PH 1.3 | 117873078 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1101 | ORO FINO 1101 | 004 | BUTTE COUNTY | 5786673 | CWSP - ORO FINO 1101 - LR2022 PH 1.3 | 10,060.000 | 0.000 | 08W | 09/23/2019 | 2019 | # | #VALUE! | PEND | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - ORO FINO-1101 LR-2022 PH I | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 25490.54
35129618 | CWSP - ORO FINO 1101 - LR2022 PH 1.4 | 117873079 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1101 | ORO FINO 1101 | 004 | BUTTE COUNTY | 5786674 | CWSP - ORO FINO 1101 - LR2022 PH 1.4 | 10,566.000 | 0.000 | 08W | 09/23/2019 | 2019 | # | #VALUE! | PEND | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - ORO FINO-1101 LR-2022 PH I | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 23405.95
35129619 | CWSP - ORO FINO 1101 - LR2022 PH 1.5 | 117873090 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1101 | ORO FINO 1101 | 004 | BUTTE COUNTY | 5786675 | CWSP - ORO FINO 1101 - LR2022 PH 1.5 | 8,666.000 | 0.000 | 08W | 09/23/2019 | 2019 | # | #VALUE! | PEND | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - ORO FINO-1101 LR-2022 PH I | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 80974.99
35129620 | LINDEN 1102 RECONDUCTOR D4387 | 112682565 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/30/2018 | ED.16207.1102 | LINDEN 1102 | 039 | SAN JOAQUIN CO | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 09/23/2019 | 2019 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 5235.99
35129621 | R2RPL OH WIRE ON DOLAN RD 1101 S052CC211 | 113725868 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/28/2019 | ED.05-D082300000.STRU.POLE | SALINAS D0823 POLES | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 09/23/2019 | 2019 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 2668.72
35129623 | RECONDUCTOR 7 SPANS - DUMBARTON 1106 | 113038755 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/01/2019 | ED.01447.1106 | DUMBARTON 1106 | 001 | ALAMEDA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 09/23/2019 | 2019 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 97.79
35129624 | MARYSVILLE 1107 - GRANT WAY RECONDUCTOR | 111053589 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/30/2016 | ED.15201.1107.TXFR.TROH | OVERHEAD TRANSFORMERS | 051 | SUTTER COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 09/23/2019 | 2019 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 919.01
35129625 | R7 NAPA 1109 WIRE DOWN AT SW 1955 | 110485716 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 07/01/2016 | ED.04202.1109 | NAPA 1109 | 028 | NAPA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 09/23/2019 | 2019 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 4568.01
35129626 | RECOMMENDATION 18-0015602_SISQUOC-1104 | 114354598 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 08/02/2020 | ED.18281.1104 | SISQUOC 1104 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 09/23/2019 | 2019 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 911.86
35129627 | RECOND 7-SPANS ELYSIAN RD- CORONA 1103 | 112760950 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/28/2018 | ED.04349.1103.RECL | RECLOSERS | 049 | SONOMA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 09/23/2019 | 2019 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 1063.92
35129628 | R5 MORRO BAY 1102 WD 15-006745 | 111102535 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2021 | ED.18301.1102 | MORRO BAY 1102 | 040 | SAN LUIS OBISP | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 09/23/2019 | 2019 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 391.62
35129629 | 2019 08J PN SL-1107 S025CC116 | 113227557 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/27/2019 | ED.02272.1107.TXFR.TROH | OVERHEAD TRANSFORMERS | 041 | SAN MATEO COUN | 5517127 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 09/23/2019 | 2019 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 589.28
35129630 | EL NIDO 1101 - TARGETED OH SPLICE 91193 | 113718462 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/30/2019 | ED.25245.1101 | EL NIDO 1101 | 020 | MADERA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 09/23/2019 | 2019 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 2053.15
35129631 | VALLEJO B0414 HIGH SPLICE COUNT | 113747830 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/19/2019 | ED.42-QQ39080000.STRU.POLE | SILVERADO QQ3908 POLES | 048 | SOLANO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 09/23/2019 | 2019 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 2938.39
35129632 | DIXON 1103 RECOND LINE EXCESS SPLICES | 112134523 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/01/2017 | ED.06206.1103.SWIT | SWITCHES | 048 | SOLANO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 09/23/2019 | 2019 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 3025.59
35129633 | R2 EL CAPITAN 1104 RECONDUCTORING | 113240816 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2021 | ED.72-07131C0000.STRU.POLE | MERCED MAP 07131C POLES | 024 | MERCED COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 09/23/2019 | 2019 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 1368.76
35129634 | SANTA MARIA 1110 RECOND 2300FT 4AR W 2CU | 114538011 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/26/2020 | ED.18282.1102 | MESA 1102 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 09/23/2019 | 2019 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 1126.66
35129635 | R7 RECONDTAP SPERRY & GUERNEVILLE RD | 112407504 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/28/2018 | ED.04257.1103.SWIT | SWITCHES | 049 | SONOMA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 09/23/2019 | 2019 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
35129636 | WESTPARK 1104 RECOND 2,430' WITH 397AL | 113817897 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/28/2019 | ED.25370.1104 | WESTPARK 1104 | 015 | KERN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 09/23/2019 | 2019 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
35129637 | DAVIS 1106 RECOND LINE EX SPLICES | 111855703 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 08/04/2017 | ED.06204.1106.SWIT | SWITCHES | 057 | YOLO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 09/23/2019 | 2019 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 70.05
35129638 | 2018 WAHTOKE 1110 RECONDUCTOR | 112410217 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/30/2021 | ED.25453.1110 | WAHTOKE 1110 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 09/23/2019 | 2019 | # | #VALUE! | ESTS | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 5260.03
35129639 | RECOND GREEN VALLEY 2101 REF# S036CC205 | 113664064 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/29/2019 | ED.08319.2101 | GREEN VALLEY 2101 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 09/23/2019 | 2019 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 1763.78
35129640 | CWSP - ORO FINO 1101 - LR2022 PH 1.6 | 117873091 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1101 | ORO FINO 1101 | 004 | BUTTE COUNTY | 5786676 | CWSP - ORO FINO 1101 - LR2022 PH 1.6 | 7,873.000 | 0.000 | 08W | 09/23/2019 | 2019 | # | #VALUE! | PEND | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - ORO FINO-1101 LR-2022 PH I | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 11894.52
35129641 | CWSP - ORO FINO 1101 - LR2022 PH 1.7 | 117873092 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1101 | ORO FINO 1101 | 004 | BUTTE COUNTY | 5786677 | CWSP - ORO FINO 1101 - LR2022 PH 1.7 | 7,379.000 | 0.000 | 08W | 09/23/2019 | 2019 | # | #VALUE! | PEND | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - ORO FINO-1101 LR-2022 PH I | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 37116.57
35129642 | CWSP - ORO FINO 1101 - LR2022 PH 1.8 | 117873093 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1101 | ORO FINO 1101 | 004 | BUTTE COUNTY | 5786738 | CWSP - ORO FINO 1101 - LR2022 PH 1.8 | 6,394.000 | 0.000 | 08W | 09/23/2019 | 2019 | # | #VALUE! | PEND | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - ORO FINO-1101 LR-2022 PH I | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 9581.72
35129643 | CWSP - ORO FINO 1101 - LR2022 PH 2.2 | 117873094 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1101 | ORO FINO 1101 | 004 | BUTTE COUNTY | 5786739 | CWSP - ORO FINO 1101 - LR2022 PH 2.2 | 11,072.000 | 0.000 | 08W | 09/23/2019 | 2019 | # | #VALUE! | PEND | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - ORO FINO-1101 LR-2022 PH 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 61935.38
35129644 | CWSP - ORO FINO 1101 - LR2022 PH 2.3 | 117873095 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1101 | ORO FINO 1101 | 004 | BUTTE COUNTY | 5786740 | CWSP - ORO FINO 1101 - LR2022 PH 2.3 | 4,502.000 | 0.000 | 08W | 09/23/2019 | 2019 | # | #VALUE! | PEND | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - ORO FINO-1101 LR-2022 PH 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 32395.16
35129645 | CWSP - ORO FINO 1101 - LR2022 PH 2.4 | 117873096 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1101 | ORO FINO 1101 | 004 | BUTTE COUNTY | 5786741 | CWSP - ORO FINO 1101 - LR2022 PH 2.4 | 5,416.000 | 0.000 | 08W | 09/23/2019 | 2019 | # | #VALUE! | PEND | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - ORO FINO-1101 LR-2022 PH 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 22730.22
35129646 | CWSP - ORO FINO 1101 - LR2022 PH 2.5 | 117873097 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1101 | ORO FINO 1101 | 004 | BUTTE COUNTY | 5786742 | CWSP - ORO FINO 1101 - LR2022 PH 2.5 | 5,560.000 | 0.000 | 08W | 09/23/2019 | 2019 | # | #VALUE! | CONS | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - ORO FINO-1101 LR-2022 PH 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 37801.45
35129647 | CWSP - ORO FINO 1101 - LR2022 PH 2.6 | 117873098 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1101 | ORO FINO 1101 | 004 | BUTTE COUNTY | 5786743 | CWSP - ORO FINO 1101 - LR2022 PH 2.6 | 4,973.000 | 0.000 | 08W | 09/23/2019 | 2019 | # | #VALUE! | ESTS | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - ORO FINO-1101 LR-2022 PH 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 8531.62
35129648 | CWSP - ORO FINO 1101 - LR2022 PH 3.2 | 117873099 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1101 | ORO FINO 1101 | 004 | BUTTE COUNTY | 5786744 | CWSP - ORO FINO 1101 - LR2022 PH 3.2 | 6,141.000 | 0.000 | 08W | 09/23/2019 | 2019 | # | #VALUE! | ESTS | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-ORO FINO 1101 LR-2022 PH 3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 12423.39
35129649 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.2 | 117873100 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1102 | ORO FINO 1102 | 004 | BUTTE COUNTY | 5786775 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.2 | 8,635.000 | 0.000 | 08W | 09/23/2019 | 2019 | # | #VALUE! | ADER | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-ORO FINO 1102 OCB & LR2090 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 15071.14
35129650 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.3 | 117873101 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1102 | ORO FINO 1102 | 004 | BUTTE COUNTY | 5786776 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.3 | 7,706.000 | 0.000 | 08W | 09/23/2019 | 2019 | # | #VALUE! | PEND | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-ORO FINO 1102 OCB & LR2090 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 92481.56
35129652 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.4 | 117873102 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1102 | ORO FINO 1102 | 004 | BUTTE COUNTY | 5786777 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.4 | 5,375.000 | 0.000 | 08W | 09/23/2019 | 2019 | # | #VALUE! | PEND | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-ORO FINO 1102 OCB & LR2090 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 76088.09
35129653 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.5 | 117873103 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1102 | ORO FINO 1102 | 004 | BUTTE COUNTY | 5786778 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.5 | 7,280.000 | 0.000 | 08W | 09/23/2019 | 2019 | # | #VALUE! | PEND | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-ORO FINO 1102 OCB & LR2090 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 488.01
35129654 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.6 | 117873104 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1102 | ORO FINO 1102 | 004 | BUTTE COUNTY | 5786779 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.6 | 9,896.000 | 0.000 | 08W | 09/23/2019 | 2019 | # | #VALUE! | PEND | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-ORO FINO 1102 OCB & LR2090 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 114225.81
35129655 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.7 | 117873105 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1102 | ORO FINO 1102 | 004 | BUTTE COUNTY | 5786780 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.7 | 9,076.000 | 0.000 | 08W | 09/23/2019 | 2019 | # | #VALUE! | PEND | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-ORO FINO 1102 OCB & LR2090 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 13079.83
35129656 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.8 | 117873106 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1102 | ORO FINO 1102 | 004 | BUTTE COUNTY | 5786781 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.8 | 0.000 | 0.000 | 08W | 09/23/2019 | 2019 | # | #VALUE! | ADER | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-ORO FINO 1102 OCB & LR2090 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 309.55
35129657 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.9 | 117873107 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1102 | ORO FINO 1102 | 004 | BUTTE COUNTY | 5786782 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.9 | 0.000 | 0.000 | 08W | 09/23/2019 | 2019 | # | #VALUE! | ESTS | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-ORO FINO 1102 OCB & LR2090 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 8894.08
35129700 | SIQUOC 1104 WIREDOWN RECONDUCTORING | 110573078 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2021 | ED.18281.1104 | SISQUOC 1104 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 09/23/2019 | 2019 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 16020.01
35129701 | R4E RECONDUCTOR LIBERTY ISLND-DIXON 1103 | 110891639 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2016 | ED.48-R190000000.STRU.POLE | SOLANO R19 POLES | 048 | SOLANO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 09/23/2019 | 2019 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 26978.86
35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | 114810960 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.15248.1103.RECL | RECLOSERS | 029 | NEVADA COUNTY | 5535211 | CWSP SPO - SH 08 | 13,700.000 | 0.000 | 08W | 09/24/2019 | 2019 | # | #VALUE! | ESTS | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BRUNSWICK 1103 LR2200 HARDENING | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 116413.43
35129900 | WEBER 1102 RECONDUCTORING - 08J | 110822896 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/20/2021 | ED.16348.1102 | WEBER 1102 | 039 | SAN JOAQUIN CO | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 09/24/2019 | 2019 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 17274.72
35129901 | 2019 08J PN MILLBRAE 1102 S073CC217 | 113747875 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/27/2019 | ED.02269.1102.SWIT | SWITCHES | 041 | SAN MATEO COUN | 5505513 | PN-OH ANNEALED/DETER CNDCTR: PM MGD | 0.000 | 0.000 | 08J | 09/24/2019 | 2019 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 792.74
35129902 | RECO31SPAN4425FT4ACSR W2CUSANTAMA1105 | 112648194 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/03/2019 | ED.18267.1105 | SANTA MARIA 1105 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 09/24/2019 | 2019 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 3468.26
35129944 | SILVERADO 2105 - DIST.UNDERBUILD RECON | 117893376 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.04343.2105 | SILVERADO 2105 | 028 | NAPA COUNTY | 5786045 | CWSP - FULTON 1107 - MARK WEST SPR RD | 3,709.000 | 0.000 | 08W | 09/25/2019 | 2019 | # | #VALUE! | UNSC | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Fulton-Calistoga 60 kV Line Reconductor | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 51895.01
35131354 | LW2111 RECONDUCTOR 1 SPAN & INSTALL FUSE | 117957888 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2022 | ED.01353.2111 | LAKEWOOD 2111 | 007 | CONTRA COSTA C | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 10/04/2019 | 2019 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 612.35
35132048 | PARLIER 1102 RECOND 3773' OF 6CU W 715AL | 117959993 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/30/2022 | ED.25229.1102 | PARLIER 1102 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 10/08/2019 | 2019 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 244.59
35132541 | MADERA 1119 RECOND 5,770' OF 6CU W 4/OAL | 117973778 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 07/08/2022 | ED.25276.1119 | MADERA 1119 | 020 | MADERA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 10/09/2019 | 2019 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 5587.01
35134806 | BR-03-14-W (E) PENTZ RD, PARB | 118057348 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 08/31/2020 | ED.17-S342200000.STRU.POLE | PARADISE S3422 POLES | 004 | BUTTE COUNTY | 5786123 | 08W Rebuild | 0.000 | 0.000 | 08W | 10/21/2019 | 2019 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35134931 | RECONDUCTOR RIVERBANK 1715-SPLICE COUNT | 113143653 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/02/2021 | ED.16319.1715 | RIVERBANK 1715 | 050 | STANISLAUS COU | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 10/22/2019 | 2019 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 1428.16
35134932 | ROUGH AND READY 1102 RECONDUCTOR | 113261334 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 02/07/2022 | ED.16308.1102 | ROUGH AND READY IS 1102 | 039 | SAN JOAQUIN CO | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 10/22/2019 | 2019 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 1211.62
35134934 | RECONDUCTOR WRIGHT 1110 - WIRE DOWN | 113143575 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/12/2021 | ED.25464.1110 | WRIGHT 1110 | 024 | MERCED COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 10/22/2019 | 2019 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 4677.15
35134937 | BONITA 1101 CO 32802 RECOND | 113219238 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2021 | ED.25539.1101 | BONITA 1101 | 020 | MADERA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 10/22/2019 | 2019 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 3276.65
35134938 | MADERA 1119 3,770FT TARGET OH REPL | 113241724 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/30/2022 | ED.25276.1119 | MADERA 1119 | 020 | MADERA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 10/22/2019 | 2019 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 10423.98
35134979 | WD-CHANNEL 1102-CO 17151 -ILIS 190101945 | 118085161 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2022 | ED.93-U091900000.STRU.POLE | STOCKTON U0919 POLES | 039 | SAN JOAQUIN CO | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 10/22/2019 | 2019 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 1346.13
35135000 | RECONDUCTOR CASSIDY 2108 | 113243462 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2021 | ED.25427.2108 | CASSIDY 2108 | 020 | MADERA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 10/22/2019 | 2019 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 5709.51
35135001 | RECONDUCTOR BONITA 1101 - AVE 17 | 113248456 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/27/2021 | ED.25539.1101 | BONITA 1101 | 020 | MADERA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 10/22/2019 | 2019 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 5713.58
35135003 | EL NIDO 1101 RECOND 3700FT WITH #2AR | 113260310 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.25245.1101 | EL NIDO 1101 | 024 | MERCED COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 3,730.000 | 0.000 | 08J | 10/22/2019 | 2019 | # | #VALUE! | UNSC | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 19271.58
35135004 | MERCED 1116 RECONDUCTORING | 113261666 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.72-0814400000.STRU.POLE | MERCED MAP 08144 POLES | 024 | MERCED COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 10/22/2019 | 2019 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 3891.84
35135005 | MVWF ALTO 1125 MUIR WOOD DR,MUIR BEACH | 111104641 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2017 | ED.04203.1125 | ALTO 1125 | 021 | MARIN COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 10/22/2019 | 2019 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 8238.33
35135006 | RECONDUCTOR CANAL 1104 WD | 112727825 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/07/2021 | ED.25209.1104 | CANAL 1104 | 024 | MERCED COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 10/22/2019 | 2019 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 8754.31
35135479 | LAWNDALE 0402 19-0098539 RECON OH COND | 118011917 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 07/30/2022 | ED.56-E040600000.STRU.POLE | SKYLINE E0406 POLES | 041 | SAN MATEO COUN | 5505513 | PN-OH ANNEALED/DETER CNDCTR: PM MGD | 0.000 | 0.000 | 08J | 10/24/2019 | 2019 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 1470.19
35135864 | CWSP – GRAYS FLAT 401 FUSE 3079 ZONE | 117923638 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | JY | JUNK YARD FL TO HOLD DELETED DATA | 032 | PLUMAS COUNTY | 5535211 | CWSP SPO - SH 08 | 9,316.000 | 0.000 | 08W | 10/29/2019 | 2019 | # | #VALUE! | CONS | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 84118.5
35135891 | RECOND SALINAS 1106 ALONG IVERSON ST | 118119201 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/30/2022 | ED.18201.1106.SWIT | SWITCHES | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 10/29/2019 | 2019 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 2761.18
35137590 | CWSP-ECOP-MIDDLETOWN 1101-OCB-H02 | 118093216 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.04314.1101.SWIT | SWITCHES | 017 | LAKE COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 11/06/2019 | 2019 | # | #VALUE! | ESTS | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 6111.44
35137593 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H07 | 118125945 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.46-Z270000000.STRU.POLE | UKIAH Z27 POLES | 017 | LAKE COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 11/06/2019 | 2019 | # | #VALUE! | ESTS | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 5376.42
35137596 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H08 | 118127757 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.46-Z260000000.STRU.POLE | UKIAH Z26 POLES | 017 | LAKE COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 11/06/2019 | 2019 | # | #VALUE! | ESTS | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 3348.21
35137599 | CWSP-ECOP-MIDDLETOWN 1101-LR 614-H11 | 118142262 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.04314.1101.RECL | RECLOSERS | 017 | LAKE COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 11/06/2019 | 2019 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 3766.11
35138215 | DIVIDE 1102 RECOND 3710 FT OF 4AR W 2 CU | 118164913 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/30/2022 | ED.18257.1102 | DIVIDE 1102 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 11/12/2019 | 2019 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 2136.91
35141419 | BR-03-07-W (E) TIMBER WALK PARB | 118188125 | 35105717 | BR-03-07-F (E) TIMBER WALK PARB | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 03/20/2020 | JY | JUNK YARD FL TO HOLD DELETED DATA | 004 | BUTTE COUNTY | 5786123 | 08W Rebuild | 0.000 | 0.000 | 08W | 11/20/2019 | 2019 | # | #VALUE! | CONS | E470 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 265571.17
35141586 | WD: MABURY 1101 - OCB - 19-0121127 | 118187066 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 09/30/2022 | ED.08219.1101.SWIT | SWITCHES | 043 | SANTA CLARA CO | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 11/20/2019 | 2019 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 1878.37
35141837 | BR-04-01-W (E) SUNSET DR PARB | 118195513 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/27/2019 | JY | JUNK YARD FL TO HOLD DELETED DATA | 004 | BUTTE COUNTY | 5786123 | 08W Rebuild | 0.000 | 0.000 | 08W | 11/22/2019 | 2019 | # | #VALUE! | PEND | E460 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 184085.04
35141980 | HMB1103 CO6071 RECOND 1100FT OH LINE | 118186909 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 08/10/2022 | ED.58-E041600000.STRU.POLE | PENINSULA E0416 POLES | 041 | SAN MATEO COUN | 5505513 | PN-OH ANNEALED/DETER CNDCTR: PM MGD | 0.000 | 0.000 | 08J | 11/22/2019 | 2019 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
35142198 | BR-03-08-W (E) BELLEVIEW PARB | 118204107 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/31/2020 | ED.17-S341700000.STRU.POLE | PARADISE S3417 POLES | 004 | BUTTE COUNTY | 5786123 | 08W Rebuild | 0.000 | 0.000 | 08W | 11/26/2019 | 2019 | # | #VALUE! | UNSC | E460 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 355398.47
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | 118218639 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.15248.1103 | BRUNSWICK 1103 | 029 | NEVADA COUNTY | 5535211 | CWSP SPO - SH 08 | 8,412.000 | 0.000 | 08W | 12/03/2019 | 2019 | # | #VALUE! | CONS | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BRUNSWICK 1103 LR2200 HARDENING | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 866165.94
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | 118218951 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.15248.1103 | BRUNSWICK 1103 | 029 | NEVADA COUNTY | 5535211 | CWSP SPO - SH 08 | 4,547.000 | 0.000 | 08W | 12/03/2019 | 2019 | # | #VALUE! | PEND | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BRUNSWICK 1103 LR2200 HARDENING | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 407447.4
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | 118218953 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.15248.1103 | BRUNSWICK 1103 | 029 | NEVADA COUNTY | 5535211 | CWSP SPO - SH 08 | 2,505.000 | 0.000 | 08W | 12/03/2019 | 2019 | # | #VALUE! | CONS | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BRUNSWICK 1103 LR2200 HARDENING | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 291415.35
35144588 | PSPS MITIGATION - ROSSMOOR 1106 | 118247763 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.01416.1108.SWIT | SWITCHES | 007 | CONTRA COSTA C | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 12/09/2019 | 2019 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35144589 | PSPS MITIGATION - MORAGA 1103 | 118247764 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.01380.1103.SWIT | SWITCHES | 007 | CONTRA COSTA C | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 12/09/2019 | 2019 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35144591 | PSPS MITIGATION - STAFFORD 1101 - PH1 | 118247769 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.04320.1102.SWIT | SWITCHES | 021 | MARIN COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 12/09/2019 | 2019 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35144592 | PSPS MITIGATION - STAFFORD 1101 - PH2 | 118247871 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.04320.1101.SWIT | SWITCHES | 021 | MARIN COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 12/09/2019 | 2019 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35144940 | *CANC* PSPS - HICKS 2101 – CB | 118261651 | # | Not assigned | 40 | Closed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/30/2020 | ED.78-I172500000.STRU.POLE | SAN JOSE I1725 POLES | 043 | SANTA CLARA CO | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 12/11/2019 | 2019 | 09/03/2020 | 2020 | CLSD | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | PSPS - Hicks 2101 – CB | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 1183.31
35144941 | PSPS - PAUL SWEET 2105 - CB PH 1 | 118261469 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 11/01/2021 | ED.76-O141000000.STRU.POLE | COAST O1410 POLES | 044 | SANTA CRUZ COU | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 12/11/2019 | 2019 | # | #VALUE! | ADER | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | PSPS - Paul Sweet 2105 - CB PH 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 173826.53
35144942 | *CANC* PSPS - PAUL SWEET 2105 - CB | 118261520 | # | Not assigned | 40 | Closed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/30/2020 | ED.76-O141000000.STRU.POLE | COAST O1410 POLES | 044 | SANTA CRUZ COU | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 12/11/2019 | 2019 | 09/03/2020 | 2020 | CLSD | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | PSPS - Paul Sweet 2105 - CB PH 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 163.61
35144943 | PSPS - ROB ROY 2105 - CB | 118261587 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 09/17/2021 | ED.76-O172000000.STRU.POLE | COAST O1720 POLES | 044 | SANTA CRUZ COU | 5535211 | CWSP SPO - SH 08 | 689.000 | 0.000 | 08W | 12/11/2019 | 2019 | # | #VALUE! | PEND | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | PSPS - Rob Roy 2105 - CB | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 95162.93
35144944 | PSPS – SNEATH LANE 1107 – LR 48338 | 118261958 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/01/2021 | ED.56-E031100000.STRU.POLE | SKYLINE E0311 POLES | 041 | SAN MATEO COUN | 5535211 | CWSP SPO - SH 08 | 1,385.000 | 0.000 | 08W | 12/11/2019 | 2019 | # | #VALUE! | PEND | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 104771.47
35145001 | PSPS - CLAYTON 2215 - CB | 118259181 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.01202.2215 | CLAYTON 2215 | 007 | CONTRA COSTA C | 5535211 | CWSP SPO - SH 08 | 9,720.000 | 0.000 | 08W | 12/12/2019 | 2019 | # | #VALUE! | PEND | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | PSPS - Clayton 2215 – CB | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 134930.93
35145002 | PSPS - IGNACIO 1101 - CB | 118262844 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.04248.1101 | IGNACIO 1101 | 021 | MARIN COUNTY | 5535211 | CWSP SPO - SH 08 | 6,847.000 | 0.000 | 08W | 12/12/2019 | 2019 | # | #VALUE! | PEND | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | PSPS - Ignacio 1101 - CB | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 116319.39
35145003 | PSPS CWSP - MORAGA 1103 - CB | 118263229 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 04/30/2021 | ED.01380.1103 | MORAGA 1103 | 007 | CONTRA COSTA C | 5535211 | CWSP SPO - SH 08 | 1,688.000 | 0.000 | 08W | 12/12/2019 | 2019 | # | #VALUE! | PEND | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | PSPS - Moraga 1103 - CB | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 88691.36
35145004 | PSPS CWSP - ROSSMOOR 1106 - CB | 118263746 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 06/10/2021 | ED.01416.1106 | ROSSMOOR 1106 | 007 | CONTRA COSTA C | 5535211 | CWSP SPO - SH 08 | 5,038.000 | 0.000 | 08W | 12/12/2019 | 2019 | # | #VALUE! | PEND | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | PSPS - Rossmoor 1106 – CB | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 80766.32
35145005 | *CANCELLED*CWSP - STAFFORD 1101 - CB PH1 | 118263871 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.04320.1101 | STAFFORD 1101 | 021 | MARIN COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 12/12/2019 | 2019 | # | #VALUE! | DOCC | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | PSPS - Stafford 1101 CB PH 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 20666.53
35145006 | PSPS - STAFFORD 1101 LR 1298 | 118263874 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.04320.1101 | STAFFORD 1101 | 021 | MARIN COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 12/12/2019 | 2019 | # | #VALUE! | ESTS | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | PSPS - Stafford 1101 - LR 1298 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 100106.91
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | 118265394 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.15361.2109.SWIT | SWITCHES | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 21,381.000 | 0.000 | 08W | 12/13/2019 | 2019 | # | #VALUE! | PEND | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | PSPS - Clarksville 2104 - CB | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 139264.04
35145523 | *CANC* PSPS - FULTON 1102 HARDENING | 118265412 | # | Not assigned | 40 | Closed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/01/2020 | ED.04256.1102 | FULTON 1102 | 049 | SONOMA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 12/13/2019 | 2019 | 09/03/2020 | 2020 | CLSD | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | PSPS - Fulton 1102 - CB | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | -72.65
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING | 118266591 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/01/2020 | ED.04332.1101 | RINCON 1101 | 049 | SONOMA COUNTY | 5535211 | CWSP SPO - SH 08 | 3,000.000 | 0.000 | 08W | 12/13/2019 | 2019 | # | #VALUE! | PEND | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | PSPS - Rincon 1101 and 1103- CB | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 95281.85
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING | 118266592 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/01/2020 | ED.04332.1102 | RINCON 1102 | 049 | SONOMA COUNTY | 5535211 | CWSP SPO - SH 08 | 7,760.000 | 0.000 | 08W | 12/13/2019 | 2019 | # | #VALUE! | PEND | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | PSPS - Rincon 1102 and 1104 - CB | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 72175.98
35145540 | PSPS - FROGTOWN 1702 - CB | 118259180 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 09/30/2020 | ED.16345.1702 | FROGTOWN 1702 | 005 | CALAVERAS COUN | 5535211 | CWSP SPO - SH 08 | 6,718.000 | 0.000 | 08W | 12/13/2019 | 2019 | # | #VALUE! | PEND | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | PSPS - Frogtown 1702 - CB | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 144656.28
35146240 | RECONDUCTOR OH LINE - EDES 1105 CIRCUIT | 118286149 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/15/2021 | ED.01368.1105 | EDES 1105 | 001 | ALAMEDA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 300.000 | 0.000 | 08J | 12/19/2019 | 2019 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 1609.34
35146639 | PS2107 RECONDUCTOR C/O 28335 | 118363082 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2022 | ED.08325.2107 | PAUL SWEET 2107 | 044 | SANTA CRUZ COU | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 12/27/2019 | 2019 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 2876.27
35147003 | *CNCL* GABILAN 1101 RECON FUSE 3279 ZONE | 13660469 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/31/2022 | ED.18233.1101 | GABILAN 1101 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 12/30/2019 | 2019 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 2895.89
35147045 | *CANC* *DO NOT USE* PSPS - CASTRO V*CANC | 118370183 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.01409.1108 | CASTRO VALLEY 1108 | 001 | ALAMEDA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 12/30/2019 | 2019 | 10/03/2020 | 2020 | CLSD | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35148272 | CREATED IN ERROR | 118407947 | # | Not assigned | 40 | Closed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/27/2019 | ED | Electric Distribution System | 005 | CALAVERAS COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 01/09/2020 | 2020 | 01/09/2020 | 2020 | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35148810 | GRAND ISLAND 2224 RECONDUCTOR 4C | 112609391 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/01/2018 | ED.06246.2224.RECL | RECLOSERS | 048 | SOLANO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 01/14/2020 | 2020 | # | #VALUE! | ESTS | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 38580.07
35152332 | RECOND CASTROVILLE 2104 ZONE 23829 | 118472573 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/31/2022 | ED.05-F091600000.STRU.POLE | SALINAS F0916 POLES | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 01/28/2020 | 2020 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 2445.85
35153986 | RECON 3441 FT OF 4ACSR W 2CU/ISTALL FCO | 118497363 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/30/2022 | ED.18263.1103 | SAN LUIS OBISPO 1103 | 040 | SAN LUIS OBISP | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 02/06/2020 | 2020 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
35154003 | HENRIETTA 1110 RECOND 6,900' WITH 397AL | 118499689 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/30/2022 | ED.25268.1110 | HENRIETTA 1110 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 02/06/2020 | 2020 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
35155680 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.02 | 118499588 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/30/2021 | ED.15248.1105 | BRUNSWICK 1105 | 029 | NEVADA COUNTY | 5789366 | CWSP - BRUNSWICK 1105 - LR 2140 - PH 1.0 | 6,990.000 | 0.000 | 08W | 02/07/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BRUNSWICK 1105 LR2140 HARDENING - | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 1091.62
35155681 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.03 | 118501195 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15248.1105 | BRUNSWICK 1105 | 029 | NEVADA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 1,335.000 | 0.000 | 08W | 02/07/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BRUNSWICK 1105 LR2140 HARDENING - | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 679.18
35155682 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.04 | 118501438 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15248.1105 | BRUNSWICK 1105 | 029 | NEVADA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 1,930.000 | 0.000 | 08W | 02/07/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BRUNSWICK 1105 LR2140 HARDENING - | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 428.05
35155683 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.05 | 118501439 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15248.1105 | BRUNSWICK 1105 | 029 | NEVADA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 6,550.000 | 0.000 | 08W | 02/07/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BRUNSWICK 1105 LR2140 HARDENING - | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 2006.3
35155684 | CWSP-BRUNSWICK 1105 LR2140 - PH 1.06 | 118501730 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15248.1105 | BRUNSWICK 1105 | 029 | NEVADA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 3,288.000 | 0.000 | 08W | 02/07/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BRUNSWICK 1105 LR2140 HARDENING - | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 428.05
35155685 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.07 | 118501731 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15248.1105 | BRUNSWICK 1105 | 029 | NEVADA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 3,780.000 | 0.000 | 08W | 02/07/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BRUNSWICK 1105 LR2140 HARDENING - | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 428.05
35155686 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.08 | 118501733 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15248.1105 | BRUNSWICK 1105 | 029 | NEVADA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 3,240.000 | 0.000 | 08W | 02/07/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BRUNSWICK 1105 LR2140 HARDENING - | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 176.98
35155687 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.09 | 118501735 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15248.1105 | BRUNSWICK 1105 | 029 | NEVADA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 8,886.000 | 0.000 | 08W | 02/07/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BRUNSWICK 1105 LR2140 HARDENING - | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 176.98
35155688 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.10 | 118501736 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15248.1105 | BRUNSWICK 1105 | 029 | NEVADA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 2,961.000 | 0.000 | 08W | 02/07/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BRUNSWICK 1105 LR2140 HARDENING - | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 176.98
35155689 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.11 | 118501737 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15248.1105 | BRUNSWICK 1105 | 029 | NEVADA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 4,900.000 | 0.000 | 08W | 02/07/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BRUNSWICK 1105 LR2140 HARDENING - | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 176.98
35155690 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.12 | 118501738 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15248.1105 | BRUNSWICK 1105 | 029 | NEVADA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 5,082.000 | 0.000 | 08W | 02/07/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BRUNSWICK 1105 LR2140 HARDENING - | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 176.98
35155691 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.13 | 118501739 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15248.1105 | BRUNSWICK 1105 | 029 | NEVADA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 3,010.000 | 0.000 | 08W | 02/07/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BRUNSWICK 1105 LR2140 HARDENING - | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 176.98
35155692 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.14 | 118501873 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15248.1105 | BRUNSWICK 1105 | 029 | NEVADA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 5,268.000 | 0.000 | 08W | 02/07/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BRUNSWICK 1105 LR2140 HARDENING - | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 176.98
35155693 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.15 | 118501874 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15248.1105 | BRUNSWICK 1105 | 029 | NEVADA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 6,100.000 | 0.000 | 08W | 02/07/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BRUNSWICK 1105 LR2140 HARDENING - | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 315.49
35155694 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.16 | 118501875 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15248.1105 | BRUNSWICK 1105 | 029 | NEVADA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 5,900.000 | 0.000 | 08W | 02/07/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BRUNSWICK 1105 LR2140 HARDENING - | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 176.98
35155695 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.02 | 118502200 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15248.1105 | BRUNSWICK 1105 | 029 | NEVADA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 5,465.000 | 0.000 | 08W | 02/07/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BRUNSWICK 1105 LR2140 HARDENING - | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 394.52
35155696 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.03 | 118502205 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15248.1105 | BRUNSWICK 1105 | 029 | NEVADA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 2,440.000 | 0.000 | 08W | 02/07/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BRUNSWICK 1105 LR2140 HARDENING - | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 593.51
35155697 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.04 | 118502207 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15248.1105 | BRUNSWICK 1105 | 029 | NEVADA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 2,080.000 | 0.000 | 08W | 02/07/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BRUNSWICK 1105 LR2140 HARDENING - | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 179.05
35155698 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.05 | 118502208 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15248.1105 | BRUNSWICK 1105 | 029 | NEVADA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 6,332.000 | 0.000 | 08W | 02/07/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BRUNSWICK 1105 LR2140 HARDENING - | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 179.05
35155699 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.06 | 118502271 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15248.1105 | BRUNSWICK 1105 | 029 | NEVADA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 2,415.000 | 0.000 | 08W | 02/07/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BRUNSWICK 1105 LR2140 HARDENING - | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 179.05
35155740 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.07 | 118502272 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15248.1105 | BRUNSWICK 1105 | 029 | NEVADA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 3,636.000 | 0.000 | 08W | 02/07/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BRUNSWICK 1105 LR2140 HARDENING - | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35155741 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.08 | 118502273 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15248.1105 | BRUNSWICK 1105 | 029 | NEVADA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 890.000 | 0.000 | 08W | 02/07/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BRUNSWICK 1105 LR2140 HARDENING - | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 179.05
35155742 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.09 | 118502274 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15248.1105 | BRUNSWICK 1105 | 029 | NEVADA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 6,100.000 | 0.000 | 08W | 02/07/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BRUNSWICK 1105 LR2140 HARDENING - | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 593.51
35155743 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.10 | 118502275 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15248.1105 | BRUNSWICK 1105 | 029 | NEVADA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 3,692.000 | 0.000 | 08W | 02/07/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BRUNSWICK 1105 LR2140 HARDENING - | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35155744 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.11 | 118502276 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15248.1105 | BRUNSWICK 1105 | 029 | NEVADA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 2,671.000 | 0.000 | 08W | 02/07/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BRUNSWICK 1105 LR2140 HARDENING - | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35155746 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.12 | 118502277 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15248.1105 | BRUNSWICK 1105 | 029 | NEVADA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 5,910.000 | 0.000 | 08W | 02/07/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BRUNSWICK 1105 LR2140 HARDENING - | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 358.05
35155747 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.13 | 118502279 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15248.1105 | BRUNSWICK 1105 | 029 | NEVADA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 4,025.000 | 0.000 | 08W | 02/07/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BRUNSWICK 1105 LR2140 HARDENING - | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35155748 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.14 | 118502451 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15248.1105 | BRUNSWICK 1105 | 029 | NEVADA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 2,740.000 | 0.000 | 08W | 02/07/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BRUNSWICK 1105 LR2140 HARDENING - | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35155749 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.15 | 118502453 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15248.1105 | BRUNSWICK 1105 | 029 | NEVADA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 2,662.000 | 0.000 | 08W | 02/07/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BRUNSWICK 1105 LR2140 HARDENING - | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35155750 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.16 | 118502455 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15248.1105 | BRUNSWICK 1105 | 029 | NEVADA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 8,872.000 | 0.000 | 08W | 02/07/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BRUNSWICK 1105 LR2140 HARDENING - | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 358.05
35155751 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.17 | 118502456 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15248.1105 | BRUNSWICK 1105 | 029 | NEVADA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 2,627.000 | 0.000 | 08W | 02/07/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BRUNSWICK 1105 LR2140 HARDENING - | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 593.51
35155752 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.02 | 118502580 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15248.1105 | BRUNSWICK 1105 | 029 | NEVADA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 2,727.000 | 0.000 | 08W | 02/07/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BRUNSWICK 1105 LR2140 HARDENING - | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 217.53
35155753 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.03 | 118502582 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15248.1105 | BRUNSWICK 1105 | 029 | NEVADA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 5,611.000 | 0.000 | 08W | 02/07/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BRUNSWICK 1105 LR2140 HARDENING - | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 710.01
35155754 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.04 | 118502583 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15248.1105 | BRUNSWICK 1105 | 029 | NEVADA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 6,626.000 | 0.000 | 08W | 02/07/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BRUNSWICK 1105 LR2140 HARDENING - | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 533
35155755 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.05 | 118502584 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15248.1105 | BRUNSWICK 1105 | 029 | NEVADA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 1,431.000 | 0.000 | 08W | 02/07/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BRUNSWICK 1105 LR2140 HARDENING - | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 217.53
35155756 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.06 | 118502585 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15248.1105 | BRUNSWICK 1105 | 029 | NEVADA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 9,214.000 | 0.000 | 08W | 02/07/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BRUNSWICK 1105 LR2140 HARDENING - | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 1695.01
35155757 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.07 | 118502586 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15248.1105 | BRUNSWICK 1105 | 029 | NEVADA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 2,913.000 | 0.000 | 08W | 02/07/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BRUNSWICK 1105 LR2140 HARDENING - | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35155758 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.08 | 118502587 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15248.1105 | BRUNSWICK 1105 | 029 | NEVADA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 3,510.000 | 0.000 | 08W | 02/07/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BRUNSWICK 1105 LR2140 HARDENING - | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 533
35155759 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.09 | 118502588 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15248.1105 | BRUNSWICK 1105 | 029 | NEVADA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 3,500.000 | 0.000 | 08W | 02/07/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BRUNSWICK 1105 LR2140 HARDENING - | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35155840 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.10 | 118502589 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15248.1105 | BRUNSWICK 1105 | 029 | NEVADA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 2,596.000 | 0.000 | 08W | 02/07/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BRUNSWICK 1105 LR2140 HARDENING - | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35155841 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.11 | 118502690 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15248.1105 | BRUNSWICK 1105 | 029 | NEVADA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 4,491.000 | 0.000 | 08W | 02/07/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BRUNSWICK 1105 LR2140 HARDENING - | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 710.01
35155842 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.12 | 118502691 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15248.1105 | BRUNSWICK 1105 | 029 | NEVADA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 808.000 | 0.000 | 08W | 02/07/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BRUNSWICK 1105 LR2140 HARDENING - | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 412.45
35157845 | SILVERADO 2105 WIRE DOWN - PH 3 | 118548863 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.04343.2105 | SILVERADO 2105 | 028 | NAPA COUNTY | 5535211 | CWSP SPO - SH 08 | 6,693.000 | 0.000 | 08W | 02/20/2020 | 2020 | # | #VALUE! | CONS | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 367686.5
35157914 | GABILAN 1101 RECONDUCTOR FUSE 3279 ZONE | 118367647 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 03/31/2022 | ED.18233.1101 | GABILAN 1101 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 02/20/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 505.63
35157947 | RICE 1102 RECOND 20,775 FT WITH 2AR | 118551698 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/01/2022 | ED.06283.1102 | RICE 1102 | 006 | COLUSA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 02/20/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Rice 1102 - Reconductor 20,775 ft w 2AR | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 1264.17
35158717 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.2 | 118531819 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15248.1105 | BRUNSWICK 1105 | 029 | NEVADA COUNTY | 5535211 | CWSP SPO - SH 08 | 7,952.000 | 0.000 | 08W | 02/26/2020 | 2020 | # | #VALUE! | ADER | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Brunswick - 1105 - LR2210 Zone-Ph | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 5437.5
35159768 | RECONDUCTOR RIPON 1701 - SPLICE COUNT | 113181841 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/27/2019 | ED.16380.1701 | RIPON 1701 | 039 | SAN JOAQUIN CO | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 03/04/2020 | 2020 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 7234.42
35160091 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.3 | 118532310 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15248.1105 | BRUNSWICK 1105 | 029 | NEVADA COUNTY | 5535211 | CWSP SPO - SH 08 | 3,447.000 | 0.000 | 08W | 03/06/2020 | 2020 | # | #VALUE! | ADER | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Brunswick - 1105 - LR2210 Zone-Ph | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 4403.9
35160093 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.4 | 118532312 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15248.1105 | BRUNSWICK 1105 | 029 | NEVADA COUNTY | 5535211 | CWSP SPO - SH 08 | 6,360.000 | 0.000 | 08W | 03/06/2020 | 2020 | # | #VALUE! | ESTS | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Brunswick - 1105 - LR2210 Zone-Ph | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 4711.16
35160094 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.5 | 118532313 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15248.1105 | BRUNSWICK 1105 | 029 | NEVADA COUNTY | 5535211 | CWSP SPO - SH 08 | 6,145.000 | 0.000 | 08W | 03/06/2020 | 2020 | # | #VALUE! | ESTS | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Brunswick - 1105 - LR2210 Zone-Ph | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 4708.7
35160095 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.6 | 118532315 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15248.1105 | BRUNSWICK 1105 | 029 | NEVADA COUNTY | 5535211 | CWSP SPO - SH 08 | 9,380.000 | 0.000 | 08W | 03/06/2020 | 2020 | # | #VALUE! | ESTS | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Brunswick - 1105 - LR2210 Zone-Ph | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 4920.88
35160096 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.7 | 118532317 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15248.1105 | BRUNSWICK 1105 | 029 | NEVADA COUNTY | 5535211 | CWSP SPO - SH 08 | 5,330.000 | 0.000 | 08W | 03/06/2020 | 2020 | # | #VALUE! | ESTS | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Brunswick - 1105 - LR2210 Zone-Ph | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 5493.5
35160097 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.8 | 118532318 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15248.1105 | BRUNSWICK 1105 | 029 | NEVADA COUNTY | 5535211 | CWSP SPO - SH 08 | 10,570.000 | 0.000 | 08W | 03/06/2020 | 2020 | # | #VALUE! | ADER | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Brunswick - 1105 - LR2210 Zone-Ph | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 5608.07
35160098 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.9 | 118532430 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15248.1105 | BRUNSWICK 1105 | 029 | NEVADA COUNTY | 5535211 | CWSP SPO - SH 08 | 4,895.000 | 0.000 | 08W | 03/06/2020 | 2020 | # | #VALUE! | ESTS | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Brunswick - 1105 - LR2210 Zone-Ph | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 5698.34
35160341 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.2 | 118532433 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15248.1105 | BRUNSWICK 1105 | 029 | NEVADA COUNTY | 5535211 | CWSP SPO - SH 08 | 8,165.000 | 0.000 | 08W | 03/06/2020 | 2020 | # | #VALUE! | ESTS | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Brunswick - 1105 - LR2210 Zone-Ph | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 3792.66
35160342 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.3 | 118532435 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15248.1105 | BRUNSWICK 1105 | 029 | NEVADA COUNTY | 5535211 | CWSP SPO - SH 08 | 7,840.000 | 0.000 | 08W | 03/06/2020 | 2020 | # | #VALUE! | ESTS | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Brunswick - 1105 - LR2210 Zone-Ph | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 5456.44
35160343 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.4 | 118532436 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15248.1105 | BRUNSWICK 1105 | 029 | NEVADA COUNTY | 5535211 | CWSP SPO - SH 08 | 13,875.000 | 0.000 | 08W | 03/06/2020 | 2020 | # | #VALUE! | ESTS | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Brunswick - 1105 - LR2210 Zone-Ph | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 909.53
35160344 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.5 | 118532438 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15248.1105 | BRUNSWICK 1105 | 029 | NEVADA COUNTY | 5535211 | CWSP SPO - SH 08 | 14,192.000 | 0.000 | 08W | 03/06/2020 | 2020 | # | #VALUE! | ESTS | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Brunswick - 1105 - LR2210 Zone-Ph | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 1270.47
35160345 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.6 | 118532570 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15248.1105 | BRUNSWICK 1105 | 029 | NEVADA COUNTY | 5535211 | CWSP SPO - SH 08 | 17,520.000 | 0.000 | 08W | 03/06/2020 | 2020 | # | #VALUE! | ESTS | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Brunswick - 1105 - LR2210 Zone-Ph | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 3276.72
35160346 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.7 | 118532571 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15248.1105 | BRUNSWICK 1105 | 029 | NEVADA COUNTY | 5535211 | CWSP SPO - SH 08 | 2,960.000 | 0.000 | 08W | 03/06/2020 | 2020 | # | #VALUE! | ESTS | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Brunswick - 1105 - LR2210 Zone-Ph | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 966.62
35160669 | GRAND ISLAND 2227 RECOND 2870 FT W 2AR | 118640219 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/01/2022 | ED.06246.2227 | GRAND ISLAND 2227 | 057 | YOLO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 03/09/2020 | 2020 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 3520.55
35162161 | EIGHT MILE 2102 RECONDUCTORING | 113199108 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2019 | ED.93-S120000000.STRU.POLE | STOCKTON S12 POLES | 039 | SAN JOAQUIN CO | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 03/11/2020 | 2020 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 10552.76
35162588 | SLO 1104 RECON 6082 FT OF 4AR W 2CU | 118677123 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/10/2022 | ED.18263.1104 | SAN LUIS OBISPO 1104 | 040 | SAN LUIS OBISP | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 03/13/2020 | 2020 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 1638.01
35167136 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.2 | 118729469 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2021 | ED.15308.2106 | PLACERVILLE 2106 | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 03/25/2020 | 2020 | # | #VALUE! | ESTS | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Placerville 2106 - LR 1104 - Ph 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 214.56
35167137 | CANCEL DUPLICATE ORDER | # | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2021 | ED.15308.2106 | PLACERVILLE 2106 | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 03/25/2020 | 2020 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35167138 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.3 | 118729544 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15308.2106 | PLACERVILLE 2106 | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 03/25/2020 | 2020 | # | #VALUE! | ESTS | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Placerville 2106 - LR 1104 - Ph 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 607.15
35167433 | EVERGREEN 2103- OH RECOND AT LR 980314 | 118755418 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2022 | ED.08201.2103 | EVERGREEN 2103 | 043 | SANTA CLARA CO | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 03/30/2020 | 2020 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 3150.1
35168794 | GRAND ISLAND 2227 RECOND 3.7MI W 4/0-2AR | 118738655 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/01/2022 | ED.06246.2227 | GRAND ISLAND 2227 | 057 | YOLO COUNTY | 5517127 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 03/27/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Grand Island - Reconductor 19,370 feet | Base Capital | GRC Electric Dist | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 2513.21
35168820 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.4 | 118738238 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2021 | ED.15308.2106 | PLACERVILLE 2106 | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 03/25/2020 | 2020 | # | #VALUE! | ESTS | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Placerville 2106 - LR 1104 - Ph 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35168821 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.5 | 118738363 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2021 | ED.15308.2106 | PLACERVILLE 2106 | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 3,934.000 | 0.000 | 08W | 03/25/2020 | 2020 | # | #VALUE! | ESTS | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Placerville 2106 - LR 1104 - Ph 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 412.71
35168822 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.6 | 118738366 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2021 | ED.15308.2106 | PLACERVILLE 2106 | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 03/25/2020 | 2020 | # | #VALUE! | ESTS | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Placerville 2106 - LR 1104 - Ph 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35168823 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.7 | 118738440 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2021 | ED.15308.2106 | PLACERVILLE 2106 | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 03/25/2020 | 2020 | # | #VALUE! | ESTS | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Placerville 2106 - LR 1104 - Ph 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 220.94
35169499 | CASTROVILLE 2103 RECOND LOG#20-0016183 | 118748612 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/30/2022 | ED.18235.2103 | CASTROVILLE 2103 | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 03/26/2020 | 2020 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 1501.87
35170201 | LODI 1102 RECONDUCTOR & CUTOVER TO 12KV | 114248752 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.93-Q111400000.STRU.POLE | STOCKTON Q1114 POLES | 039 | SAN JOAQUIN CO | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 04/01/2020 | 2020 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
35170202 | CWSP - ORO FINO 1101 - LR2022 PH2.7 | 118771067 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.10303.1101 | ORO FINO 1101 | 004 | BUTTE COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 04/03/2020 | 2020 | # | #VALUE! | ESTS | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - ORO FINO-1101 LR-2022 PH 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 10948.54
35171354 | CWSP - CAMP EVERS 2106 - 5020 - PHASE 2 | 118796971 | # | Not assigned | 30 | Technically Completed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/30/2020 | ED.08362.2106 | CAMP EVERS 2106 | 044 | SANTA CRUZ COU | 5535211 | CWSP SPO - SH 08 | 1.000 | 0.000 | 08W | 04/09/2020 | 2020 | # | #VALUE! | FICL | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 28419.84
35171705 | BR-03-12-W (E) PENTZ RD SRTS PARB | 118911002 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.17-S341700000.STRU.POLE | PARADISE S3417 POLES | 004 | BUTTE COUNTY | 5786123 | 08W Rebuild | 0.000 | 0.000 | 08W | 04/10/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 1024292.44
35172091 | R1-RELIAIBLITY SAN PABLO REPLACE 4ACSR | 118926905 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2022 | ED.01437.1105 | SAN PABLO 1105 | 007 | CONTRA COSTA C | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 04/17/2020 | 2020 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 681.96
35172093 | *CANC* EL DORADO PH 2102 LR19542 P*CANC | 13860338 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.15276.2102.RECL | RECLOSERS | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 04/17/2020 | 2020 | 05/03/2020 | 2020 | CLSD | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35172094 | CWSP-EL DORADO PH 2102 LR19542 PH 1*CANC | 13860383 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.15276.2102.RECL | RECLOSERS | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 04/17/2020 | 2020 | 05/03/2020 | 2020 | CLSD | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35172521 | *CANC* EL DORADO PH 2102 LR19542 P*CANC | 13860424 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.15276.2102.RECL | RECLOSERS | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 04/17/2020 | 2020 | 05/03/2020 | 2020 | CLSD | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35172522 | *CANC* CWSP-EL DORADO PH 2102 LR195*CANC | 13860394 | # | Not assigned | 40 | Closed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.15276.2102.RECL | RECLOSERS | 046 | SIERRA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 04/17/2020 | 2020 | 05/03/2020 | 2020 | CLSD | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35173253 | CWSP-EL DORADO PH 2102 LR19542 PH 1.3 | 118926912 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.15276.2102.RECL | RECLOSERS | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 04/20/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - El Dorado PH 2102 Zone 19542 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 355.09
35173255 | CWSP-EL DORADO PH 2102 LR19542 PH 1.2 | 118926574 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.15276.2102.RECL | RECLOSERS | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 04/20/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - El Dorado PH 2102 Zone 19542 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 1071.26
35173320 | CWSP-EL DORADO PH 2102 LR19542 PH 1.5 | 118926984 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.15276.2102.RECL | RECLOSERS | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 04/20/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - El Dorado PH 2102 Zone 19542 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 355.09
35173321 | CWSP-EL DORADO PH 2102 LR19542 PH 1.4 | 118926983 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.15276.2102.RECL | RECLOSERS | 046 | SIERRA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 04/20/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - El Dorado PH 2102 Zone 19542 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 355.09
35173387 | BR-09-01-W (E) SKYWAY PH3 20A PARB | 118935079 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/30/2021 | ED.17-T321300000.STRU.POLE | PARADISE T3213 POLES | 004 | BUTTE COUNTY | 5786123 | 08W Rebuild | 0.000 | 0.000 | 08W | 04/21/2020 | 2020 | # | #VALUE! | ESTS | E470 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35173754 | ECOP-BRUNSWICK 1106-H08-LR51486 | 118911473 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.22-O110900000.STRU.POLE | NEVADA O1109 POLES | 029 | NEVADA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 04/22/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP-Brunswick 1106-H08-LR51486 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 14803.97
35173755 | ECOP-WEST POINT 1101-H02-LR36674 | 118911674 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.95-I302300000.STRU.POLE | MOTHER LODE I3023 POLES | 003 | AMADOR COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 04/22/2020 | 2020 | # | #VALUE! | ESTS | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP-WEST POINT 1101-H02-LR36674 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 28719.45
35173756 | ECOP-EL DORADO 2101-H02-LR6852-PH2 | 118911791 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.21-H471000000.STRU.POLE | EL DORADO H4710 POLES | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 04/22/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP-El Dorado 2101-H02-LR6852-Ph2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 8231.64
35173959 | CWSP-MIWUK 1702-LR 38218-PH 1.6 | 118940594 | # | Not assigned | 10 | Created | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.16366.1702 | MIWUK 1702 | 055 | TUOLUMNE COUNT | 5785985 | CWSP - MIWUK 1702 - LR 38218 - PH 1.6 | 4,747.000 | 0.000 | 08W | 04/23/2020 | 2020 | # | #VALUE! | ESTS | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35173968 | GRAND ISLAND 2223 RECOND 4840FT W/ 2AR | 118944504 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/01/2022 | ED.06246.2223 | GRAND ISLAND 2223 | 057 | YOLO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 04/23/2020 | 2020 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 1722.66
35174085 | PSPS - FIA320 - LR @ 101269978 | 118944585 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/31/2020 | ED.95-R280000000.STRU.POLE | MOTHER LODE R28 POLES | 005 | CALAVERAS COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 04/23/2020 | 2020 | # | #VALUE! | UNSC | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 388.21
35174174 | ECOP-STANISLAUS 1702-H03-LR1850 | 13867552 | # | Not assigned | 10 | Created | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.16282.1702 | STANISLAUS 1702 | 005 | CALAVERAS COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 04/24/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Deleted/Cancelled projects | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35174465 | ECOP-EL DORADO 2101-H02-LR6852-PH1 | 118911790 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.21-H471000000.STRU.POLE | EL DORADO H4710 POLES | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 04/27/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP-El Dorado 2101-H02-LR6852-Ph1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 19099.3
35174466 | ECOP-EL DORADO 2101-H02-LR6852-PH3 | 118911793 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.21-H471000000.STRU.POLE | EL DORADO H4710 POLES | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 04/27/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP-El Dorado 2101-H02-LR6852-Ph3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 12231.93
35174467 | ECOP-STANISLAUS 1702-H01-LR37276-PH1 | 118912984 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.95-O341400000.STRU.POLE | MOTHER LODE O3414 POLES | 005 | CALAVERAS COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 04/27/2020 | 2020 | # | #VALUE! | ESTS | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP-Stanislaus 1702-H01-LR37276-Ph1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 3203.12
35174468 | ECOP-STANISLAUS 1702-H01-LR37276-PH2 | 118912985 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.95-O341400000.STRU.POLE | MOTHER LODE O3414 POLES | 005 | CALAVERAS COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 04/27/2020 | 2020 | # | #VALUE! | ESTS | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP-Stanislaus 1702-H01-LR37276-Ph2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 2824.12
35174469 | ECOP-PINE GROVE 1102-H01-LR45292 | 118912983 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.95-K290400000.STRU.POLE | MOTHER LODE K2904 POLES | 003 | AMADOR COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 04/27/2020 | 2020 | # | #VALUE! | ESTS | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP-Pine Grove 1102-H01-LR45292 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 25623.19
35174470 | ECOP-MOLINO 1102-H01-LR318 | 118912761 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.44-JJ22110000.STRU.POLE | SANTA ROSA JJ2211 POLES | 049 | SONOMA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 04/27/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP-Molino 1102-H01-LR318 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 8305.71
35174471 | ECOP-MONTE RIO 1113-H07-LR180 | 13869444 | # | Not assigned | 10 | Created | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.04281.1113 | MONTE RIO 1113 | 049 | SONOMA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 04/27/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Deleted/Cancelled projects | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35174472 | ECOP-CALISTOGA 1101-H02-LR43924 | 118912499 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.04271.1101 | CALISTOGA 1101 | 028 | NAPA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 04/27/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP-Calistoga 1101-H02-LR43924 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 14454.72
35174473 | ECOP-CALISTOGA 1101-H03-LR43924 | 118912760 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.04271.1101 | CALISTOGA 1101 | 028 | NAPA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 04/27/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP-Calistoga 1101-H03-LR43924 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 12664.2
35174474 | ECOP-CALISTOGA 1101-H01-LR736 PH1 | 118912987 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.04271.1101 | CALISTOGA 1101 | 028 | NAPA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 04/27/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP-Calistoga 1101-H01-LR736 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 17567.79
35174475 | ECOP-CALISTOGA 1101-H01-LR736-E_O CO3807 | 118912988 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.04271.1101 | CALISTOGA 1101 | 028 | NAPA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 04/27/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP-Calistoga 1101-H01-LR736-S_O 208157 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 4722.22
35174476 | ECOP-CALISTOGA 1101-H01-LR736-S_O 208157 | 118913020 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.44-GG30000000.STRU.POLE | SANTA ROSA GG30 POLES | 049 | SONOMA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 04/27/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP-Calistoga 1101-H01-LR736-N_O CO7729 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 5045.48
35174477 | ECOP-CALISTOGA 1101-H01-LR736-PH3 | 118913023 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.04271.1101 | CALISTOGA 1101 | 028 | NAPA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 04/27/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP-Calistoga 1101-H01-LR736-Ph3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 5633.45
35174478 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1 | 118913024 | # | Not assigned | 10 | Created | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.46-BB30170000.STRU.POLE | UKIAH BB3017 POLES | 017 | LAKE COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08W | 04/27/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | ECOP-Middletown 1101-H12-LR548-Ph1 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
35174479 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2 | 118913025 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.46-BB30170000.STRU.POLE | UKIAH BB3017 POLES | 017 | LAKE COUNTY | 5517127 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08W | 04/27/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | ECOP-Middletown 1101-H12-LR548-Ph2 | Base Capital | GRC Electric Dist | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 12673.86
35174501 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3 | 118913026 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.44-KK33160000.STRU.POLE | SANTA ROSA KK3316 POLES | 017 | LAKE COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 04/27/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP-Middletown 1101-H12-LR548-Ph3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 10792.93
35174993 | CWSP - PLACERVILLE 2106 - LR1104 - PH2.2 | 118964445 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15308.2106 | PLACERVILLE 2106 | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 05/01/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Placerville 2106 - LR 1104 - Phas | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35175131 | *CANC* - PLACERVILLE 2106 - LR1104 - PH2 | 13873394 | # | Not assigned | 40 | Closed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15308.2106 | PLACERVILLE 2106 | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 05/01/2020 | 2020 | 06/03/2020 | 2020 | CLSD | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35175132 | *CANC* - PLACERVILLE 2106 - LR1104 - PH | 13873357 | # | Not assigned | 10 | Created | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15308.2106 | PLACERVILLE 2106 | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 05/01/2020 | 2020 | # | #VALUE! | CNCL | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35175549 | BR-05-07-W (E) HIGH SCHOOL MAXWELL PARB | 118978773 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 09/25/2020 | ED.17-T330200000.STRU.POLE | PARADISE T3302 POLES | 004 | BUTTE COUNTY | 5786123 | 08W Rebuild | 0.000 | 0.000 | 08W | 05/04/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 246.63
35175560 | DC-1112 RECOND 575 FT OF 4AR 20-0040068 | 118976222 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/30/2022 | ED.56-D022400000.STRU.POLE | SKYLINE D0224 POLES | 041 | SAN MATEO COUN | 5505513 | PN-OH ANNEALED/DETER CNDCTR: PM MGD | 575.000 | 0.000 | 08J | 05/04/2020 | 2020 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 173.03
35175843 | CWSP - PLACERVILLE 2106 - LR1104 - PH3.2 | 118981826 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15308.2106 | PLACERVILLE 2106 | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 05/05/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-PLACERVILLE 2106 LR1104 PH 3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35175844 | CWSP - PLACERVILLE 2106 - LR1104 - PH3.3 | 118981828 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15308.2106 | PLACERVILLE 2106 | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 05/05/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-PLACERVILLE 2106 LR1104 PH 3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35175845 | CWSP - PLACERVILLE 2106 - LR1104 - PH3.4 | 118981829 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15308.2106 | PLACERVILLE 2106 | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 05/05/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-PLACERVILLE 2106 LR1104 PH 3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35175846 | CWSP - PLACERVILLE 2106 - LR1104 - PH3.5 | 118981890 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15308.2106 | PLACERVILLE 2106 | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 05/05/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-PLACERVILLE 2106 LR1104 PH 3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35175847 | CWSP - PLACERVILLE 2106 - LR1104 - PH4.2 | 118981893 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15308.2106 | PLACERVILLE 2106 | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 05/05/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-PLACERVILLE 2106 LR1104 PH 4 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 76.87
35175848 | CWSP - PLACERVILLE 2106 - LR1104 - PH4.3 | 118981896 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15308.2106 | PLACERVILLE 2106 | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 05/05/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-PLACERVILLE 2106 LR1104 PH 4 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35175849 | CWSP - PLACERVILLE 2106 - LR1104 - PH4.4 | 118981897 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15308.2106 | PLACERVILLE 2106 | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 05/05/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-PLACERVILLE 2106 LR1104 PH 4 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35175850 | CWSP - PLACERVILLE 2106 - LR1104 - PH4.5 | 118981898 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15308.2106 | PLACERVILLE 2106 | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 05/05/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-PLACERVILLE 2106 LR1104 PH 4 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35175852 | CWSP - PLACERVILLE 2106 - LR1104 - PH5.2 | 118981899 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15308.2106 | PLACERVILLE 2106 | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 05/05/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-PLACERVILLE 2106 LR1104 PH 5 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35175853 | CWSP - PLACERVILLE 2106 - LR1104 - PH5.3 | 118981960 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15308.2106 | PLACERVILLE 2106 | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 05/05/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-PLACERVILLE 2106 LR1104 PH 5 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35175854 | CWSP - PLACERVILLE 2106 - LR1104 - PH5.4 | 118981961 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15308.2106 | PLACERVILLE 2106 | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 05/05/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-PLACERVILLE 2106 LR1104 PH 5 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35175855 | CWSP - PLACERVILLE 2106 - LR1104 - PH5.5 | 118981962 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15308.2106 | PLACERVILLE 2106 | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 05/05/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-PLACERVILLE 2106 LR1104 PH 5 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35175856 | CWSP - PLACERVILLE 2106 - LR1104 - PH6.2 | 118981963 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15308.2106 | PLACERVILLE 2106 | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 05/05/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-PLACERVILLE 2106 LR1104 PH 6 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35175857 | CWSP - PLACERVILLE 2106 - LR1104 - PH6.3 | 118981964 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15308.2106 | PLACERVILLE 2106 | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 05/05/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-PLACERVILLE 2106 LR1104 PH 6 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35175858 | CWSP - PLACERVILLE 2106 - LR1104 - PH6.4 | 118981965 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15308.2106 | PLACERVILLE 2106 | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 05/05/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-PLACERVILLE 2106 LR1104 PH 6 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35175859 | CWSP - PLACERVILLE 2106 - LR1104 - PH6.5 | 118981966 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15308.2106 | PLACERVILLE 2106 | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 05/05/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-PLACERVILLE 2106 LR1104 PH 6 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35176209 | CWSP - PLACERVILLE 2106 - LR1104 - PH2.3 | 118964446 | # | Not assigned | 10 | Created | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15308.2106 | PLACERVILLE 2106 | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 05/07/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Placerville 2106 - LR 1104 - Phas | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35176210 | CWSP - PLACERVILLE 2106 - LR1104 - PH2.4 | 118964447 | # | Not assigned | 10 | Created | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15308.2106 | PLACERVILLE 2106 | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 05/07/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Placerville 2106 - LR 1104 - Phas | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35176211 | CWSP - PLACERVILLE 2106 - LR1104 - PH2.5 | 118964448 | # | Not assigned | 10 | Created | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15308.2106 | PLACERVILLE 2106 | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 05/07/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Placerville 2106 - LR 1104 - Phas | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35176497 | ECOP-STANISLAUS 1702-H03-LR1850 | 118911798 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2021 | ED.16282.1702 | STANISLAUS 1702 | 005 | CALAVERAS COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 05/11/2020 | 2020 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Deleted/Cancelled projects | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 12724.59
35176549 | ECOP-MONTE RIO 1113-H07-LR180 | 118912762 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2021 | ED.04281.1113 | MONTE RIO 1113 | 049 | SONOMA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 05/12/2020 | 2020 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Deleted/Cancelled projects | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 7406.84
35177107 | CWSP - PLACERVILLE 2106 - LR1104 - PH3.6 | 119021512 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2021 | ED.15308.2106 | PLACERVILLE 2106 | 009 | EL DORADO COUN | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 05/13/2020 | 2020 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-PLACERVILLE 2106 LR1104 PH 3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35177108 | CWSP - PLACERVILLE 2106 - LR1104 - PH3.7 | 119021513 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2021 | ED.15308.2106 | PLACERVILLE 2106 | 009 | EL DORADO COUN | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 05/13/2020 | 2020 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-PLACERVILLE 2106 LR1104 PH 3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35177109 | CWSP - PLACERVILLE 2106 - LR1104 - PH2.6 | 119021498 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2021 | ED.15308.2106 | PLACERVILLE 2106 | 009 | EL DORADO COUN | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 05/13/2020 | 2020 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Placerville 2106 - LR 1104 - Phas | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35177110 | CWSP - PLACERVILLE 2106 - LR1104 - PH2.7 | 119021499 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2021 | ED.15308.2106 | PLACERVILLE 2106 | 009 | EL DORADO COUN | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 05/13/2020 | 2020 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Placerville 2106 - LR 1104 - Phas | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35177111 | CWSP - PLACERVILLE 2106 - LR1104 - PH2.8 | 119021511 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.15308.2106 | PLACERVILLE 2106 | 009 | EL DORADO COUN | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 05/13/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Placerville 2106 - LR 1104 - Phas | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35178081 | RECOUNDUCTOR 925 FT OF 4 ACSR WITH 2CU | 119043197 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 05/19/2023 | ED.18206.1106 | FAIRWAY 1106 | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 05/19/2020 | 2020 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
35178764 | SPEN-1102 REC 1,312FT OF 4AR 20-0046857 | 119052457 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/30/2023 | ED.05-I120900000.STRU.POLE | SALINAS I1209 POLES | 027 | MONTEREY COUNT | 5535457 | DO 08 - Monthly Forecast Only | 1,312.000 | 0.000 | 08J | 05/26/2020 | 2020 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 1024.15
35179069 | BUCOCAMPTUG WILDWOOD LN PARADISE | 119066408 | # | Not assigned | 30 | Technically Completed | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 10/23/2020 | JY | JUNK YARD FL TO HOLD DELETED DATA | 004 | BUTTE COUNTY | 5791246 | Butte Rebuild UG TAP 08W | 500.000 | 0.000 | 08W | 05/27/2020 | 2020 | # | #VALUE! | FICL | E460 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 110045.7
35179087 | RECONDUCTOR 400' OF 4 ASCR W/ 2 CU | 119065385 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2023 | ED.40-UU33150000.STRU.POLE | NORTH BAY MAP UU3315 POLES | 021 | MARIN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 05/27/2020 | 2020 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
35179088 | RECOND 1400' W/ 4/0 AL | 119065722 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2023 | ED.42-HH34080000.STRU.POLE | SILVERADO MAP HH3408 POLES | 028 | NAPA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 05/27/2020 | 2020 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
35179328 | BUCOCAMPTUG SUN RIVER CT PARADISE | 119073514 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.17-T331200000.STRU.POLE | PARADISE T3312 POLES | 004 | BUTTE COUNTY | 5791246 | Butte Rebuild UG TAP 08W | 751.000 | 0.000 | 08W | 05/28/2020 | 2020 | # | #VALUE! | CONS | E460 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 38983.23
35180088 | BUCOCAMPTUG 5507 ROCKFORD LN PARADISE | 119098203 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 08/28/2020 | ED.17-T340800000.STRU.POLE | PARADISE T3408 POLES | 004 | BUTTE COUNTY | 5791246 | Butte Rebuild UG TAP 08W | 174.000 | 0.000 | 08W | 06/03/2020 | 2020 | # | #VALUE! | CONS | E460 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 41926.64
35180245 | RPL OH COND.SAN BRUNO-0402 20-0049211 | 119097306 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 06/30/2023 | ED.56-E042300000.STRU.POLE | SKYLINE E0423 POLES | 041 | SAN MATEO COUN | 5505513 | PN-OH ANNEALED/DETER CNDCTR: PM MGD | 1,036.000 | 0.000 | 08J | 06/03/2020 | 2020 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 682.76
35181199 | ECOP-WEST POINT 1101-H03-TS L373 | 118991252 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.95-J290800000.STRU.POLE | MOTHER LODE J2908 POLES | 003 | AMADOR COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 06/10/2020 | 2020 | # | #VALUE! | ESTS | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP-WEST POINT 1101-H03-TS L373 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 6724.7
35181318 | BUCOCAMPTUG 6650 WHITTALL LN PARADISE | 119141713 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/27/2020 | ED.17-S331900000.STRU.POLE | PARADISE S3319 POLES | 004 | BUTTE COUNTY | 5791246 | Butte Rebuild UG TAP 08W | 356.000 | 0.000 | 08W | 06/10/2020 | 2020 | # | #VALUE! | CONS | E460 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 27096.47
35181319 | BUCOCAMPTUG STINSON LN PARADISE | 119142173 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/27/2020 | ED.17-S332400000.STRU.POLE | PARADISE S3324 POLES | 004 | BUTTE COUNTY | 5791246 | Butte Rebuild UG TAP 08W | 534.000 | 0.000 | 08W | 06/10/2020 | 2020 | # | #VALUE! | CONS | E460 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 40701.9
35181576 | CWSP- BUCOCAMP - SKYWAY PARADISE TIE PH1 | 119159304 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 09/25/2020 | ED.16-U291400000.STRU.POLE | CHICO MAP U2914 POLES | 004 | BUTTE COUNTY | 5791419 | CWSP - BUCOCAMP-SKYWAY PARADISE TIE PH1 | 0.000 | 0.000 | 08W | 06/12/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35181764 | PEABODY 2105 RECOND 630FT W 2AR | 119159904 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/01/2023 | ED.48-S120500000.STRU.POLE | SOLANO S1205 POLES | 048 | SOLANO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 06/15/2020 | 2020 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 341.4
35181924 | BUCOCAMPTUG ROE RD/WILSON LN PARADISE | 119165277 | 35174758 | R4 (G) 14D BR-10-05 ROE RD, PARD | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 08/28/2020 | ED.17-T321500000.STRU.POLE | PARADISE T3215 POLES | 004 | BUTTE COUNTY | 5791246 | Butte Rebuild UG TAP 08W | 1.000 | 0.000 | 08W | 06/15/2020 | 2020 | # | #VALUE! | MAPP | E460 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 99979.43
35181939 | WD RECONDUCTORING ON WYANDOTTE 1103 | 119146963 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2022 | ED.10291.1103 | WYANDOTTE 1103 | 004 | BUTTE COUNTY | 5532077 | ED MAT 08W (Rate Case) | 0.000 | 0.000 | 08W | 06/16/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Other Capital | Other | # | # | Electric Distribution | Electric Distribution | 0
35183226 | GRAND ISLAND 2225 RECOND 2.4MI (PH1) | 119184799 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/01/2021 | ED.48-T220000000.STRU.POLE | SOLANO T22 POLES | 034 | SACRAMENTO COU | 5517127 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 06/23/2020 | 2020 | # | #VALUE! | ESTS | E470 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Grand Island 2224/2225 Outlet Ph1 | Base Capital | GRC Electric Dist | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 4814.15
35184050 | KETTLEMAN HILLS 1101 RECOND 2741FT 4AR | 111994672 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2020 | ED.25273.1101 | KETTLEMAN HILLS 1101 | 016 | KINGS COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 5,356.000 | 0.000 | 08J | 06/29/2020 | 2020 | # | #VALUE! | PEND | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 169474.08
35184468 | WOODLAND 1108 - RECOND 230FT - OCB | 119293564 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/01/2023 | ED.50-I172500000.STRU.POLE | YOLO I1725 POLES | 057 | YOLO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 07/01/2020 | 2020 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 924.55
35185714 | WDDB - OTTER 1102 - LR 2002 | 119231992 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 06/30/2022 | ED.18294.1102.SWIT | SWITCHES | 027 | MONTEREY COUNT | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 07/09/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Otter 1102 - OH Line Replc - #19-0131557 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 1801.54
35187368 | RECOND 11,356 FT OF 6CU AND 4ACSR W 4/0 | 119318336 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2023 | ED.01-VV40080000.STRU.POLE | SANTA MARIA VV4008 POLES | 042 | SANTA BARBARA | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 07/21/2020 | 2020 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
35191130 | ECOP - CALISTOGA 1101 - H01 - LR 736-PH5 | 119536531 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.42-FF29000000.STRU.POLE | SILVERADO MAP FF29 POLES | 049 | SONOMA COUNTY | 5517127 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08W | 08/03/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | ECOP-CALISTOGA 1101-H01-LR736-Ph4 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 5081.85
35191311 | ECOP - MONTE RIO 1113 - H06-LR8299 | 119518125 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2022 | ED.44-HH20030000.STRU.POLE | SANTA ROSA HH2003 POLES | 049 | SONOMA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 08/04/2020 | 2020 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - MONTE RIO 1113 - H06-LR8299 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 1554.09
35191313 | ECOP - MONTE RIO 1113 - H06-LR8299 | 119518128 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2022 | ED.44-GG19020000.STRU.POLE | SANTA ROSA GG1902 POLES | 049 | SONOMA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 08/04/2020 | 2020 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - MONTE RIO 1111 - H01-LR64758 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 2569
35191316 | ECOP - OAKHURST 1103 - H01-LR10190 | 119518129 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2022 | ED.72-0521236000.STRU.POLE | MERCED MAP 0521236 POLES | 022 | MARIPOSA COUNT | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 08/04/2020 | 2020 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - OAKHURST 1103 - H01-LR10190 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 2763.86
35191317 | ECOP - BRUNSWICK 1106 - H03 - LR4639 | 119518394 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2023 | ED.22-O090400000.STRU.POLE | NEVADA O0904 POLES | 029 | NEVADA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 08/04/2020 | 2020 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - BRUNSWICK 1106 - H03 - LR4639 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 1529.29
35191318 | ECOP - SILVERADO 2102 - H02-LR58626 | 119518390 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2022 | ED.42-HH36000000.STRU.POLE | SILVERADO HH36 POLES | 028 | NAPA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 08/04/2020 | 2020 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - SILVERADO 2102 - H02-LR58626 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 3000.96
35191319 | ECOP - LAS GALLINAS A 1105 - H01-LR99904 | 119518398 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2023 | ED.40-RR29200000.STRU.POLE | NORTH BAY MAP RR2920 POLES | 021 | MARIN COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 08/04/2020 | 2020 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - LAS GALLINAS A 1105 - H01-LR99904 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 2633.96
35191380 | ECOP - MIWUK 1702 - H02-LR9270 | 119518524 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2023 | ED.91-T361400000.STRU.POLE | STANISLAUS T3614 POLES | 055 | TUOLUMNE COUNT | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 08/04/2020 | 2020 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - MIWUK 1702 - H02-LR9270 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 1529.29
35191381 | ECOP - MIWUK 1702 - H03-LR9270 | 119518525 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2023 | ED.91-T361900000.STRU.POLE | STANISLAUS T3619 POLES | 055 | TUOLUMNE COUNT | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 08/04/2020 | 2020 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - MIWUK 1702 - H03-LR9270 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 1529.29
35191382 | ECOP - MORAGA 1105 - H01-CB | 119518526 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2023 | ED.30-F070900000.STRU.POLE | DIABLO F0709 POLES | 007 | CONTRA COSTA C | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 08/04/2020 | 2020 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - MORAGA 1105 - H01-CB | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 1529.29
35191383 | ECOP - SILVERADO 2102 - H01-LR58626 | 119518528 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/31/2023 | ED.42-HH36000000.STRU.POLE | SILVERADO HH36 POLES | 028 | NAPA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 08/04/2020 | 2020 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - SILVERADO 2102 - H01-LR58626 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 1529.29
35191520 | STONE CORRAL 1110 RECOND 1,585 FEET | 113817663 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 07/05/2019 | ED.25292.1110 | STONE CORRAL 1110 | 010 | FRESNO COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 08/04/2020 | 2020 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 594.44
35191553 | BR-13-01-W (E) LIGHTFOOT WAY PARB | 119560543 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 07/30/2021 | ED.17-T330400000.STRU.POLE | PARADISE T3304 POLES | 004 | BUTTE COUNTY | 5786123 | 08W Rebuild | 0.000 | 0.000 | 08W | 08/05/2020 | 2020 | # | #VALUE! | ESTS | E470 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 7987.57
35191930 | ECOP - WOODACRE 1101 - H01-LR404 PH1 | 119553788 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2022 | ED.40-SS29080000.STRU.POLE | NORTH BAY MAP SS2908 POLES | 021 | MARIN COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 08/07/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - WOODACRE 1101 - H01-LR404 Ph1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 4571.5
35191934 | ECOP - WOODACRE 1101 - H01-LR404 PH2 | 119553797 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2022 | ED.40-SS29080000.STRU.POLE | NORTH BAY MAP SS2908 POLES | 021 | MARIN COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 08/07/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - WOODACRE 1101 - H01-LR404 Ph2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 3286.59
35191937 | ECOP - PUEBLO 2102 - H01-LR792 | 119553837 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2022 | ED.42-JJ34000000.STRU.POLE | SILVERADO JJ34 POLES | 028 | NAPA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 08/07/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - PUEBLO 2102 - H01-LR792 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 3215.84
35192021 | ECOP - SILVERADO 2104 - H02-LR78268 | 119553918 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2022 | ED.42-GG35020000.STRU.POLE | SILVERADO GG3502 POLES | 028 | NAPA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 08/07/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - SILVERADO 2104 - H02-LR78268 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 8949.41
35192025 | ECOP - FORESTHILL 1101 - H02-LR1802 PH1 | 119550890 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2022 | ED.20-R142000000.STRU.POLE | PLACER R1420 POLES | 031 | PLACER COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 08/07/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - FORESTHILL 1101 - H02-LR1802 Ph1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 2883.25
35192028 | ECOP - FORESTHILL 1101 - H02-LR1802 PH2 | 119550898 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2022 | ED.20-R142000000.STRU.POLE | PLACER R1420 POLES | 031 | PLACER COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 08/07/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - FORESTHILL 1101 - H02-LR1802 Ph2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 1562.04
35192029 | ECOP - FORESTHILL 1101 - H02-LR1802 PH3 | 119551168 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2022 | ED.20-R142000000.STRU.POLE | PLACER R1420 POLES | 031 | PLACER COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 08/07/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - FORESTHILL 1101 - H02-LR1802 Ph3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 1990.36
35192031 | ECOP - COLUMBIA HILL 1101 - H01-LR35424 | 119553917 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2022 | ED.22-K070000000.STRU.POLE | NEVADA K07 POLES | 029 | NEVADA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 08/07/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - COLUMBIA HILL 1101 - H01-LR35424 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 3217.75
35192034 | ECOP-APPLE HILL 1104-H01-LR13512 | 119554053 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2022 | ED.21-H452000000.STRU.POLE | EL DORADO H4520 POLES | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 08/07/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP-APPLE HILL 1104-H01-LR13512 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 2139.98
35192035 | ECOP - MIRABEL 1101 - H01-LR298 | 119553910 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2022 | ED.44-HH22110000.STRU.POLE | SANTA ROSA HH2211 POLES | 049 | SONOMA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 08/07/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - MIRABEL 1101 - H01-LR298 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 1545.51
35192036 | ECOP - RINCON 1103 - H01-LR474 | 119553915 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2022 | ED.44-HH30010000.STRU.POLE | SANTA ROSA HH3001 POLES | 049 | SONOMA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 08/07/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - RINCON 1103 - H01-LR474 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 4146.91
35192037 | ECOP - SILVERADO 2105 - H01-LR1421 | 119554055 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2022 | ED.44-HH32000000.STRU.POLE | SANTA ROSA MAP HH32 POLES | 049 | SONOMA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 08/07/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - SILVERADO 2105 - H01-LR1421 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 7325.76
35192039 | ECOP - MONTE RIO 1113 - H04-LR320 | 119554057 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2022 | ED.44-HH20090000.STRU.POLE | SANTA ROSA HH2009 POLES | 049 | SONOMA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 08/07/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - MONTE RIO 1113 - H04-LR320 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 2341.42
35192040 | ECOP - MONTE RIO 1113 - H08-LR477 | 119554091 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2022 | ED.44-HH20150000.STRU.POLE | SANTA ROSA HH2015 POLES | 049 | SONOMA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 08/07/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - MONTE RIO 1113 - H08-LR477 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 2181.4
35192041 | ECOP - WEST POINT 1101 - H01-LR4706 | 119552184 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2022 | ED.95-J292400000.STRU.POLE | MOTHER LODE J2924 POLES | 003 | AMADOR COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 08/07/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - WEST POINT 1101 - H01-LR4706 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 7260.49
35192043 | ECOP - PINE GROVE 1102 - H03-LR13438 PH1 | 119553911 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2022 | ED.95-J271700000.STRU.POLE | MOTHER LODE J2717 POLES | 003 | AMADOR COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 08/07/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - PINE GROVE 1102 - H03-LR13438 Ph1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 4267.49
35192044 | ECOP - PINE GROVE 1102 - H03-LR13438 PH2 | 119553912 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2022 | ED.95-J271700000.STRU.POLE | MOTHER LODE J2717 POLES | 003 | AMADOR COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 08/07/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - PINE GROVE 1102 - H03-LR13438 Ph2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 4635.04
35192045 | ECOP - STANISLAUS 1702 - H02-LR75348 | 119553913 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2022 | ED.95-O340500000.STRU.POLE | MOTHER LODE O3405 POLES | 005 | CALAVERAS COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 08/07/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - STANISLAUS 1702 - H02-LR75348 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 3454.98
35192046 | ECOP - PINE GROVE 1102 - H04-LR3172 PH1 | 119553919 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2022 | ED.95-L260900000.STRU.POLE | MOTHER LODE L2609 POLES | 003 | AMADOR COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 08/07/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - PINE GROVE 1102 - H04-LR3172 Ph1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 5065.23
35192047 | ECOP - PINE GROVE 1102 - H04-LR3172 PH2 | 119554050 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2022 | ED.95-L260900000.STRU.POLE | MOTHER LODE L2609 POLES | 003 | AMADOR COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 08/07/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - PINE GROVE 1102 - H04-LR3172 Ph2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 5658.69
35192048 | ECOP - PINE GROVE 1102 - H04-LR3172 PH3 | 119554051 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2022 | ED.95-L260900000.STRU.POLE | MOTHER LODE L2609 POLES | 003 | AMADOR COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 08/07/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - PINE GROVE 1102 - H04-LR3172 Ph3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 5288.13
35192049 | ECOP - PINE GROVE 1102 - H04-LR3172 PH4 | 119554052 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2022 | ED.95-L260900000.STRU.POLE | MOTHER LODE L2609 POLES | 003 | AMADOR COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 08/07/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - PINE GROVE 1102 - H04-LR3172 Ph4 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 4867.44
35192050 | ECOP - WEST POINT 1102 - H01-TS1303 | 119554054 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2022 | ED.95-KK30000000.STRU.POLE | Angels Camp MAP KK30 POLES | 005 | CALAVERAS COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 08/07/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - WEST POINT 1102 - H01-TS1303 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 1797.34
35192051 | ECOP - SALT SPRINGS 2102 - H01-LR4796 | 119554056 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2022 | ED.95-MM36200000.STRU.POLE | Angels Camp MAP MM3620 POLES | 005 | CALAVERAS COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 08/07/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - SALT SPRINGS 2102 - H01-LR4796 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 2337.96
35192052 | ECOP - WEST POINT 1102 - H05-LR34416 | 119554058 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2022 | ED.95-KK30000000.STRU.POLE | Angels Camp MAP KK30 POLES | 005 | CALAVERAS COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 08/07/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - WEST POINT 1102 - H05-LR34416 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 2069.3
35192053 | ECOP-OAKHURST 1103-LR 5120 | 119554059 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2022 | ED.72-0521234000.STRU.POLE | MERCED MAP 0521234 POLES | 022 | MARIPOSA COUNT | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 08/07/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP-OAKHURST 1103-LR 5120 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 6333.47
35192054 | ECOP-OAKHURST 1103-LR 5470 | 119554090 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2022 | ED.72-0521100000.STRU.POLE | MERCED MAP 05211 POLES | 022 | MARIPOSA COUNT | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 08/07/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP-OAKHURST 1103-LR 5470 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 5841.29
35192280 | ECOP - CLAYTON 2212 - H01-LR2951 | 119556070 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2023 | ED.30-E151800000.STRU.POLE | DIABLO E1518 POLES | 007 | CONTRA COSTA C | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 08/09/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - CLAYTON 2212 - H01-LR2951 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 1912.42
35192281 | ECOP - MIDDLETOWN 1101 - H16-LR48212 PH1 | 119556250 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2023 | ED.46-CC30000000.STRU.POLE | UKIAH CC30 POLES | 017 | LAKE COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 08/09/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - MIDDLETOWN 1101 - H16-LR48212 Ph1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 1541.97
35192282 | ECOP - MIDDLETOWN 1101 - H16-LR48212 PH2 | 119556300 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2023 | ED.46-CC30000000.STRU.POLE | UKIAH CC30 POLES | 017 | LAKE COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 08/09/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - MIDDLETOWN 1101 - H16-LR48212 Ph2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 1541.97
35192283 | ECOP - CALISTOGA 1101 - H04-LR1087 | 119556064 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2023 | ED.42-FF29000000.STRU.POLE | SILVERADO MAP FF29 POLES | 049 | SONOMA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 08/09/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - CALISTOGA 1101 - H04-LR1087 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 1541.97
35192284 | ECOP - SILVERADO 2104 - H05-LR726 | 119556691 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2023 | ED.42-EE35170000.STRU.POLE | NAPA MAP EE3517 POLES | 028 | NAPA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 08/09/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - SILVERADO 2104 - H05-LR726 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 4329.13
35192285 | ECOP - BRUNSWICK 1106 - H01 - LR2796 PH1 | 119555791 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2023 | ED.22-N101600000.STRU.POLE | NEVADA N1016 POLES | 029 | NEVADA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 08/09/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - BRUNSWICK 1106 - H01 - LR2796 Ph | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 1541.97
35192286 | ECOP - BRUNSWICK 1106 - H01 - LR2796 PH2 | 119555811 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2023 | ED.22-N101600000.STRU.POLE | NEVADA N1016 POLES | 029 | NEVADA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 08/09/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - BRUNSWICK 1106 - H01 - LR2796 Ph | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 1541.97
35192287 | ECOP - BRUNSWICK 1106 - H02 - CB | 119555883 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2023 | ED.22-N100700000.STRU.POLE | NEVADA N1007 POLES | 029 | NEVADA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 08/09/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - BRUNSWICK 1106 - H02 - CB | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 1541.97
35192288 | ECOP - BRUNSWICK 1106 - H04 - LR2416 | 119555953 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2023 | ED.22-O090400000.STRU.POLE | NEVADA O0904 POLES | 029 | NEVADA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 08/09/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - BRUNSWICK 1106 - H04 - LR2416 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 1541.97
35192289 | ECOP - BRUNSWICK 1106 - H07 - LR 51484 | 119555969 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2023 | ED.22-O111200000.STRU.POLE | NEVADA O1112 POLES | 029 | NEVADA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 08/09/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - BRUNSWICK 1106 - H07 - LR 51484 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35192290 | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 | 119556075 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2023 | ED.21-H392200000.STRU.POLE | EL DORADO H3922 POLES | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 08/09/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 1553.55
35192291 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 | 119556091 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2023 | ED.21-I400600000.STRU.POLE | EL DORADO I4006 POLES | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 08/09/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 1553.55
35192292 | ECOP - FULTON 1107 - H02-LR604 | 119556108 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2023 | ED.44-GG28000000.STRU.POLE | SANTA ROSA GG28 POLES | 049 | SONOMA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 08/09/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - FULTON 1107 - H02-LR604 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 1541.97
35192293 | ECOP - MOLINO 1102 - H03-LR396 PH1 | 119556357 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2023 | ED.44-JJ22090000.STRU.POLE | SANTA ROSA JJ2209 POLES | 049 | SONOMA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 08/09/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - MOLINO 1102 - H03-LR396 Ph1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 1573.52
35192294 | ECOP - MOLINO 1102 - H03-LR396 PH2 | 119556373 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2023 | ED.44-JJ22090000.STRU.POLE | SANTA ROSA JJ2209 POLES | 049 | SONOMA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 08/09/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - MOLINO 1102 - H03-LR396 Ph2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 1541.97
35192295 | ECOP - RINCON 1103 - H02-LR198 | 119556481 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2023 | ED.44-HH29100000.STRU.POLE | SANTA ROSA HH2910 POLES | 049 | SONOMA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 08/09/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - RINCON 1103 - H02-LR198 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 1551.6
35192296 | ECOP - PINE GROVE 1102 - H06-LR83098 | 119556406 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2023 | ED.95-L280100000.STRU.POLE | MOTHER LODE L2801 POLES | 003 | AMADOR COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 08/09/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - PINE GROVE 1102 - H06-LR83098 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 1706.73
35192297 | ECOP - PINE GROVE 1102 - H07-CB | 119556415 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2023 | ED.95-L261200000.STRU.POLE | MOTHER LODE L2612 POLES | 003 | AMADOR COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 08/09/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - PINE GROVE 1102 - H07-CB | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 1703.51
35192298 | ECOP - SALT SPRINGS 2102 - H02-LR37300 | 119556492 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2023 | ED.95-NN36010000.STRU.POLE | Angels Camp MAP NN3601 POLES | 005 | CALAVERAS COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 08/09/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - SALT SPRINGS 2102 - H02-LR37300 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 1549.69
35192299 | ECOP - SALT SPRINGS 2102 - H04-LR97924 | 119556522 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2023 | ED.95-MM36190000.STRU.POLE | Angels Camp MAP MM3619 POLES | 005 | CALAVERAS COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 08/09/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - SALT SPRINGS 2102 - H04-LR97924 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 1541.97
35192300 | ECOP - WEST POINT 1101 - H04-TSL3355 | 119556696 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2023 | ED.95-I302300000.STRU.POLE | MOTHER LODE I3023 POLES | 003 | AMADOR COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 08/09/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - WEST POINT 1101 - H04-TSL3355 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 1950.41
35192301 | ECOP - WEST POINT 1102 - H06-LR36676 | 119556698 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2023 | ED.95-L301300000.STRU.POLE | MOTHER LODE L3013 POLES | 005 | CALAVERAS COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 08/09/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - WEST POINT 1102 - H06-LR36676 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 1541.97
35192302 | ECOP - WEST POINT 1102 - H07-LR93116 | 119556928 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2023 | ED.95-LL29000000.STRU.POLE | MOTHER LODE MAP LL29 POLES | 005 | CALAVERAS COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 08/09/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - WEST POINT 1102 - H07-LR93116 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 1541.97
35192303 | ECOP - MARIPOSA 2101 - H01-LR10170 PH1 | 119556206 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2023 | ED.72-05202A0000.STRU.POLE | MERCED MAP 05202A POLES | 022 | MARIPOSA COUNT | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 08/09/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - MARIPOSA 2101 - H01-LR10170 Ph1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 1541.97
35192304 | ECOP - MARIPOSA 2101 - H01-LR10170 PH2 | 119556233 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2023 | ED.72-05202A0000.STRU.POLE | MERCED MAP 05202A POLES | 022 | MARIPOSA COUNT | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 08/09/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - MARIPOSA 2101 - H01-LR10170 Ph2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 1541.97
35192305 | ECOP - MIWUK 1702 - H01-LR8130 | 119556333 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2023 | ED.91-T360900000.STRU.POLE | STANISLAUS T3609 POLES | 055 | TUOLUMNE COUNT | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 08/09/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - MIWUK 1702 - H01-LR8130 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 1541.97
35192683 | BR-05-15-W CLARK-5 PARB | 119601767 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 08/27/2021 | ED.17-T330400000.STRU.POLE | PARADISE T3304 POLES | 004 | BUTTE COUNTY | 5786123 | 08W Rebuild | 0.000 | 0.000 | 08W | 08/11/2020 | 2020 | # | #VALUE! | ESTS | E470 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 68678.89
35193679 | GUERNSEY 1101 LR 92702 RECOND 2060FT | 113763315 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 03/31/2021 | ED.25266.1101 | GUERNSEY 1101 | 016 | KINGS COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 08/20/2020 | 2020 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 6752.9
35193844 | MAGUNDEN 1105 - RECONDUCTOR | 119637556 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/30/2022 | ED.66-2928351000.STRU.POLE | KERN 2928351 POLES | 015 | KERN COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 08/20/2020 | 2020 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 1019.94
35193883 | BUCOCAMPTUG 622 PEARSON RD PARADISE | 119640259 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 11/27/2020 | ED.17-T330900000.STRU.POLE | PARADISE T3309 POLES | 004 | BUTTE COUNTY | 5791246 | Butte Rebuild UG TAP 08W | 310.000 | 0.000 | 08W | 08/19/2020 | 2020 | # | #VALUE! | UNSC | E460 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 40926.04
35199560 | ECOP-WEST POINT 1101-H02-LR36674-PH2 | 119666808 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.95-I302400000.STRU.POLE | MOTHER LODE I3024 POLES | 003 | AMADOR COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 09/10/2020 | 2020 | # | #VALUE! | ESTS | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP-WEST POINT 1101-H02-LR36674 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 1541.97
35200008 | BUCOCAMPTUG MOORE RD PARADISE UG SHORT | 119762792 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 01/08/2021 | ED.17-S341100000.STRU.POLE | PARADISE S3411 POLES | 004 | BUTTE COUNTY | 5791246 | Butte Rebuild UG TAP 08W | 0.000 | 0.000 | 08W | 09/14/2020 | 2020 | # | #VALUE! | ESTS | E460 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 4336.23
35200127 | ECOP - FORESTHILL 1101 - H03-LR50486 | 119768637 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2022 | ED.20-S130400000.STRU.POLE | PLACER S1304 POLES | 031 | PLACER COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 09/15/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - FORESTHILL 1101 - H03-LR50486 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 1870.34
35206134 | CWSP - CAMP EVERS 2106 - LR5020 - PH 3.2 | 119896242 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.76-M140800000.STRU.POLE | COAST M1408 POLES | 044 | SANTA CRUZ COU | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 10/13/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - CAMP EVERS 2106 - 5020 - PHASE 3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35206135 | CWSP - CAMP EVERS 2106 - LR5020 - PH 3.3 | 119896249 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.76-M140300000.STRU.POLE | COAST M1403 POLES | 044 | SANTA CRUZ COU | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 10/13/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - CAMP EVERS 2106 - 5020 - PHASE 3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35206136 | CWSP - CAMP EVERS 2106 - LR5020 - PH 3.4 | 119896480 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.76-M140700000.STRU.POLE | COAST M1407 POLES | 044 | SANTA CRUZ COU | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 10/13/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - CAMP EVERS 2106 - 5020 - PHASE 3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35206138 | CWSP - CAMP EVERS 2106 - LR5020 - PH 3.5 | 119896482 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.76-M141600000.STRU.POLE | COAST M1416 POLES | 044 | SANTA CRUZ COU | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 10/13/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - CAMP EVERS 2106 - 5020 - PHASE 3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35207102 | KIRKER 2104 - RECONDCUTOR 570 FT | 119921836 | # | Not assigned | 20 | Released | ECES_CA1 | ECES Capital User Status | # | Not assigned | [8 empty] | 12/16/2022 | ED.01445.2104 | KIRKER 2104 | 007 | CONTRA COSTA C | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 10/20/2020 | 2020 | # | #VALUE! | UNSE | E460 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 214.25
35212401 | FRRB - MONTICELLO 1101 CB | 119933522 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.04305.1101 | MONTICELLO 1101 | 028 | NAPA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 11/08/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | FRRB - NB NAPA COUNTY | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35212402 | FRRB - MONTICELLO 1101 LR 666 | 119982885 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.04305.1101.RECL | RECLOSERS | 028 | NAPA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 11/08/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | FRRB - NB NAPA COUNTY | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35212403 | FRRB - MONTICELLO 1101 LR 654 | 119982889 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.04305.1101.RECL | RECLOSERS | 028 | NAPA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 11/08/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | FRRB - NB NAPA COUNTY | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35212404 | FRRB - MONTICELLO 1101 LR 630 | 119982981 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.04305.1101.RECL | RECLOSERS | 028 | NAPA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 11/08/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | FRRB - NB NAPA COUNTY | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35212405 | FRRB - MONTICELLO 1101 LR 93384 | 119982987 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.04305.1101.RECL | RECLOSERS | 028 | NAPA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 11/08/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | FRRB - NB NAPA COUNTY | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35212406 | FRRB - MONTICELLO 1101 LR 37384 | 119983061 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.04305.1101.RECL | RECLOSERS | 028 | NAPA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 11/08/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | FRRB - NB NAPA COUNTY | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35212407 | FRRB - SILVERADO 2102 LR 636 | 119983066 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.04343.2102.RECL | RECLOSERS | 028 | NAPA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 11/08/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | FRRB - NB NAPA COUNTY | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35212408 | FRRB - SILVERADO 2102 LR 34959 | 119983069 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.04343.2102.RECL | RECLOSERS | 028 | NAPA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 11/08/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | FRRB - NB NAPA COUNTY | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35212409 | FRRB - SILVERADO 2104 LR 645 | 119983129 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.04343.2104.RECL | RECLOSERS | 028 | NAPA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 11/08/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | FRRB - NB NAPA COUNTY | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35212410 | FRRB - SILVERADO 2104 LR 708 | 119983145 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.04343.2104.RECL | RECLOSERS | 028 | NAPA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 11/08/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | FRRB - NB NAPA COUNTY | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35212411 | FRRB - SILVERADO 2104 LR 722 | 119983147 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.04343.2104.RECL | RECLOSERS | 028 | NAPA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 11/08/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | FRRB - NB NAPA COUNTY | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35212412 | FRRB - SILVERADO 2104 LR 37632 | 119983231 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.04343.2104.RECL | RECLOSERS | 028 | NAPA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 11/08/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | FRRB - NB NAPA COUNTY | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35212413 | FRRB - SILVERADO 2105 LR 658898 | 119983363 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.04343.2105.RECL | RECLOSERS | 028 | NAPA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 11/08/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | FRRB - NB NAPA COUNTY | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35212414 | FRRB - SILVERADO 2105 LR 131568 | 119983432 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.04343.2105.RECL | RECLOSERS | 028 | NAPA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 11/08/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | FRRB - NB NAPA COUNTY | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35212415 | FRRB - SILVERADO 2105 LR 167360 | 119983433 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.04343.2105.RECL | RECLOSERS | 028 | NAPA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 11/08/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | FRRB - NB NAPA COUNTY | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35212416 | FRRB - CALISTOGA 1102 LR 634 | 119983454 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.04271.1102.RECL | RECLOSERS | 028 | NAPA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 11/08/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | FRRB - NB NAPA COUNTY | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35212417 | FRRB - CALISTOGA 1102 LR 769230 | 119983463 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.04271.1102.RECL | RECLOSERS | 028 | NAPA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 11/08/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | FRRB - NB NAPA COUNTY | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35212418 | FRRB - FITCH MOUNTAIN 1113 LR 6751 | 119933523 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.04275.1113.RECL | RECLOSERS | 049 | SONOMA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 11/08/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | FRRB - SO SONOMA COUNTY | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35212419 | FRRB - DUNBAR 1101 - LR 416 | 119983560 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.04307.1101.RECL | RECLOSERS | 049 | SONOMA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 11/08/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | FRRB - SO SONOMA COUNTY | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35212460 | FRRB - RINCON 1101 LR 14605 | 119983565 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.04332.1101.RECL | RECLOSERS | 049 | SONOMA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 11/08/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | FRRB - SO SONOMA COUNTY | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35212461 | FRRB - RINCON 1101 LR 663641 | 119983567 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.04332.1101.RECL | RECLOSERS | 049 | SONOMA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 11/08/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | FRRB - SO SONOMA COUNTY | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35212462 | FRRB - RINCON 1103 LR 198 | 119983580 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.04332.1103.RECL | RECLOSERS | 049 | SONOMA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 11/08/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | FRRB - SO SONOMA COUNTY | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35212463 | FRRB - RINCON 1103 LR 474 | 119983582 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.04332.1103.RECL | RECLOSERS | 049 | SONOMA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 11/08/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | FRRB - SO SONOMA COUNTY | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35212464 | FRRB - CALISTOGA 1101 LR 886282 | 119983588 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.44-GG30000000.STRU.POLE | SANTA ROSA GG30 POLES | 049 | SONOMA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 11/08/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | FRRB - SO SONOMA COUNTY | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35212465 | FRRB - VACAVILLE 1108 LR 38316 | 119933526 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.06360.1108.RECL | RECLOSERS | 048 | SOLANO COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 11/08/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | FRRB - SAC SOLANO COUNTY | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35212466 | FRRB - VACAVILLE 1108 LR 8762 | 119984990 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.06360.1108.RECL | RECLOSERS | 048 | SOLANO COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 11/08/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | FRRB - SAC SOLANO COUNTY | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35212467 | FRRB - LAURELES 1111 LR 2020 | 119933604 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.18237.1111.RECL | RECLOSERS | 027 | MONTEREY COUNT | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 11/08/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | FRRB - CC MONTEREY COUNTY | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35212468 | FRRB - POINT MORETTI 1101 LR36516 | 119933606 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.08293.1101.RECL | RECLOSERS | 044 | SANTA CRUZ COU | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 11/08/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | FRRB - CC SANTA CRUZ COUNTY | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35212469 | FRRB - POINT MORETTI 1101 LR12122 | 119983626 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.08293.1101.RECL | RECLOSERS | 044 | SANTA CRUZ COU | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 11/08/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | FRRB - CC SANTA CRUZ COUNTY | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35212470 | FRRB - POINT MORETTI 1101 LR83716 | 119983627 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.08293.1101.RECL | RECLOSERS | 044 | SANTA CRUZ COU | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 11/08/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | FRRB - CC SANTA CRUZ COUNTY | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35212471 | FRRB - POINT MORETTI 1101 LR5076 | 119983629 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.08293.1101.SWIT | SWITCHES | 044 | SANTA CRUZ COU | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 11/08/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | FRRB - CC SANTA CRUZ COUNTY | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35212472 | FRRB - BIG BASIN 1102 LR5066 | 119983702 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.08284.1102.RECL | RECLOSERS | 044 | SANTA CRUZ COU | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 11/08/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | FRRB - CC SANTA CRUZ COUNTY | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35212473 | FRRB - BIG BASIN 1102 LR10254 | 119983704 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.08284.1102.RECL | RECLOSERS | 044 | SANTA CRUZ COU | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 11/08/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | FRRB - CC SANTA CRUZ COUNTY | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35212474 | FRRB - BIG BASIN 1102 LR12758 | 119983709 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.08284.1102.RECL | RECLOSERS | 044 | SANTA CRUZ COU | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 11/08/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | FRRB - CC SANTA CRUZ COUNTY | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35212475 | FRRB - BIG BASIN 1101 CB | 119983868 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.08284.1101 | BIG BASIN 1101 | 044 | SANTA CRUZ COU | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 11/08/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | FRRB - CC SANTA CRUZ COUNTY | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35212476 | FRRB - BIG BASIN 1101 LR5000 | 119985051 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.76-L110000000.STRU.POLE | COAST L11 POLES | 044 | SANTA CRUZ COU | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 11/08/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | FRRB - CC SANTA CRUZ COUNTY | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35212477 | FRRB - BIG BASIN 1101 LR10720 | 119983869 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.08284.1101.RECL | RECLOSERS | 044 | SANTA CRUZ COU | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 11/08/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | FRRB - CC SANTA CRUZ COUNTY | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35212478 | FRRB - SWIFT 2110 XR332 | 119933730 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.08339.2110.RECL | RECLOSERS | 043 | SANTA CLARA CO | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 11/08/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | FRRB - SJ SANTA CLARA COUNTY | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35212479 | FRRB - BIG BEND 1102 CB | 119933732 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.10375.1102 | BIG BEND 1102 | 004 | BUTTE COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 11/08/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | FRRB - NV BUTTE COUNTY | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35212480 | FRRB - BIG BEND 1102 LR1972 | 119983950 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.10375.1102.RECL | RECLOSERS | 004 | BUTTE COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 11/08/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | FRRB - NV BUTTE COUNTY | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35212481 | FRRB - WYANDOTTE 1103 LR1508 | 119983951 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.10291.1103.RECL | RECLOSERS | 004 | BUTTE COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 11/08/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | FRRB - NV BUTTE COUNTY | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35212483 | FRRB - WYANDOTTE 1103 LR1974 | 119983953 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.10291.1103.RECL | RECLOSERS | 004 | BUTTE COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 11/08/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | FRRB - NV BUTTE COUNTY | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35212486 | FRRB - KANAKA 1101 CB | 119983955 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.10322.1101 | KANAKA 1101 | 004 | BUTTE COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 11/08/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | FRRB - NV BUTTE COUNTY | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35212487 | FRRB - KANAKA 1101 LR1034 | 119983959 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.10322.1101.RECL | RECLOSERS | 004 | BUTTE COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 11/08/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | FRRB - NV BUTTE COUNTY | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35212488 | FRRB - KANAKA 1101 LR1406 | 119984001 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.10322.1101.RECL | RECLOSERS | 004 | BUTTE COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 11/08/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | FRRB - NV BUTTE COUNTY | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35212489 | FRRB - GIRVAN 1101 LR1330 | 119933733 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.10340.1101.RECL | RECLOSERS | 045 | SHASTA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 11/08/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | FRRB - NV SHASTA COUNTY | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35212490 | FRRB - GIRVAN 1101 LR323094 | 119984003 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.10340.1101.RECL | RECLOSERS | 045 | SHASTA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 11/08/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | FRRB - NV SHASTA COUNTY | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35212491 | FRRB - SAN JOAQUIN #3 1103 LR5100 | 119933734 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.25253.1103.RECL | RECLOSERS | 020 | MADERA COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 11/08/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | FRRB - YO MADERA COUNTY | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35212492 | FRRB - AUBERRY 1101 R2845 | 119933735 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.25415.1101.RECL | RECLOSERS | 010 | FRESNO COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 11/08/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | FRRB - FR FRESNO COUNTY | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35212493 | FRRB - AUBERRY 1101 R324 | 119984006 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.25415.1101.RECL | RECLOSERS | 010 | FRESNO COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 11/08/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | FRRB - FR FRESNO COUNTY | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35212494 | FRRB - AUBERRY 1101 LR37536 | 119984007 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.25415.1101.SWIT | SWITCHES | 010 | FRESNO COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 11/08/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | FRRB - FR FRESNO COUNTY | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35212495 | FRRB - AUBERRY 1101 LR233716 | 119985141 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.25415.1101.RECL | RECLOSERS | 010 | FRESNO COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 11/08/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | FRRB - FR FRESNO COUNTY | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35212496 | FRRB - HB TRINITY COUNTY | 119933736 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.19241 | LOW GAP | 053 | TRINITY COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 11/08/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | FRRB - HB TRINITY COUNTY | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35217267 | TITLE: SH - MARIPOSA 2102 LR 241564 | 120047657 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.25445.2102.RECL | RECLOSERS | 022 | MARIPOSA COUNT | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 11/23/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | SH - Mariposa 2102 LR 241564 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35217268 | SH - BUCKS CREEK 1101 CB | 120047659 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.10221.1101 | BUCKS CREEK 1101 | 032 | PLUMAS COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 11/23/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | SH - Bucks Creek 1101 CB | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35217269 | SH - MIDDLETOWN 1102 CB | 120048011 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.04314.1102.RECL | RECLOSERS | 017 | LAKE COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 11/23/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | SH - Middletown 1102 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35217270 | SH - KONOCTI 1102 LR 965078 | 120048013 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.04331.1102.RECL | RECLOSERS | 017 | LAKE COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 11/23/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | SH - Konocti 1101 LR 965078 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35217271 | SH - MIDDLETOWN 1103 LR 830 | 120048017 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.04314.1103.RECL | RECLOSERS | 017 | LAKE COUNTY | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 11/23/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | SH - Middletown 1103 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35217272 | SH - KESWICK 1101 LR 1586 | 120048018 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.10345.1101.RECL | RECLOSERS | 045 | SHASTA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 11/23/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | SH - Keswick 1101 LR 1586 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35217273 | SH - UPPER LAKE 1101 CB | 120048019 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.04287.1101 | UPPER LAKE 1101 | 017 | LAKE COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 11/23/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | SH - Upper Lake 1101 CB | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35217274 | FRRB - PN DIVISION SAN MATEO COUNTY | 120048101 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.02410.1103 | HALF MOON BAY 1103 | 041 | SAN MATEO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 11/23/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | FRRB - PN Division San Mateo County | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
35217275 | FRRB - PN DIVISION SANTA CRUZ COUNTY | 120048103 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2021 | ED.02410.1103 | HALF MOON BAY 1103 | 044 | SANTA CRUZ COU | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 11/23/2020 | 2020 | # | #VALUE! | UNSE | E470 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | FRRB - PN Division Santa Cruz County | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
74004771 | DIST WORK FOR SMARTVILLE-NICOLAUS#2-PH#2 | # | # | Not assigned | 10 | Created | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/30/2016 | ED.15281.1105.SWIT | SWITCHES | 058 | YUBA COUNTY | 5517127 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 04/20/2016 | 2016 | # | #VALUE! | UNSE | E570 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
74007103 | CRESSEY 2104 RECONDUCTOR 2ACSR | 111855150 | # | Not assigned | 40 | Closed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2018 | ED.25470.2104 | CRESSEY 2104 | 024 | MERCED COUNTY | 5517127 | DO 08 - Monthly Forecast Only | 0.000 | 14,792.000 | 08J | 08/08/2016 | 2016 | 09/22/2018 | 2018 | CLSD | E570 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | CRESSEY 2104 RECONDUCTOR PROJECT | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 1132069.33
74011865 | PH.3 - RECON. ECHO SUMMIT 1101 11,600' | 112804948 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 01/29/2020 | ED.15803.1101.SWIT | SWITCHES | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 04/26/2017 | 2017 | # | #VALUE! | UNSE | E570 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Reconductor Echo Summit 1101 11,600' | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 105886.4
74014860 | R2 REPL OH COND/ ALTERNTE BACKTIE CE2104 | 113241363 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 06/30/2020 | ED.08362.2104 | CAMP EVERS 2104 | 044 | SANTA CRUZ COU | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 09/12/2017 | 2017 | # | #VALUE! | UNSE | E570 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Repl OH Cond/ Alternate Backtie CE2104 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 13896.52
74015668 | *CANC* RPL OH WIRE ON OTTER-1101 S | # | # | Not assigned | 40 | Closed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 06/28/2019 | ED.07-N031000000.STRU.POLE | MONTEREY N0310 POLES | 027 | MONTEREY COUNT | 5535211 | CWSP SPO - SH 08 | 23,884.000 | 0.000 | 08W | 10/19/2017 | 2017 | 09/05/2019 | 2019 | CLSD | E570 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Deleted/Cancelled projects | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
74021903 | CWSP-BRUNSWICK 1105 LR-1030 ZONE | 114736235 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.15248.1105 | BRUNSWICK 1105 | 029 | NEVADA COUNTY | 5535211 | CWSP SPO - SH 08 | 25,191.000 | 25,191.000 | 08W | 10/04/2018 | 2018 | # | #VALUE! | DOCC | E570 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-BRUNSWICK 1105 LR-1030 ZONE | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 12418648.93
74021960 | CWSP-BRUNSWICK 1105 LR-32536 ZONE # PH 1 | 114778704 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.15248.1105 | BRUNSWICK 1105 | 029 | NEVADA COUNTY | 5535211 | CWSP SPO - SH 08 | 29,601.000 | 31,023.000 | 08W | 10/04/2018 | 2018 | # | #VALUE! | DOCC | E570 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-BRUNSWICK 1105 LR-32536 ZONE # PH 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 15460487
74021961 | CWSP - MIRABEL 02/MONTE RIO 13 - LR 652 | 114705149 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/15/2020 | ED.04209.1102.RECL | RECLOSERS | 049 | SONOMA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 25,170.000 | 08W | 10/04/2018 | 2018 | # | #VALUE! | DOCC | E570 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP: MIRABEL 1102 / MONTE RIO 1113 LR 6 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 20553477.14
74021962 | *DO NOT USE* CWSP: DIABLO WILDFIRE HARDE | # | # | Not assigned | 30 | Technically Completed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/23/2019 | ED.01380.1101 | MORAGA 1101 | 007 | CONTRA COSTA C | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 10/04/2018 | 2018 | # | #VALUE! | DCNL | E570 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Deleted/Cancelled projects | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | -3514.57
74021963 | CWSP - OAKLAND K 1102 OCB ZONE | 114592093 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 02/06/2020 | ED.01210.1102 | OAKLAND K 1102 | 001 | ALAMEDA COUNTY | 5535211 | CWSP SPO - SH 08 | 15,088.000 | 14,748.000 | 08W | 10/04/2018 | 2018 | # | #VALUE! | DOCC | E570 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | 74021963_CWSP OAKLAND K 1102 OCB | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 7279881.94
74021964 | X-1104 OH RECOND SKYLINE | # | # | Not assigned | 10 | Created | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 03/01/2020 | ED.26-F070700000.STRU.POLE | CENTRAL F0707 POLES | 001 | ALAMEDA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08W | 10/04/2018 | 2018 | # | #VALUE! | DOCC | E570 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
74022040 | 2019 CALISTOGA 1101 HIGH SPLICE COUNT | 113163209 | # | Not assigned | 30 | Technically Completed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2019 | ED.04271.1101 | CALISTOGA 1101 | 028 | NAPA COUNTY | 5535211 | CWSP SPO - SH 08 | 6,677.000 | 6,677.000 | 08W | 10/08/2018 | 2018 | # | #VALUE! | FICL | E570 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | 2019 CALISTOGA 1101 HIGH SPLICE COUNT | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 1777051.53
74022302 | ECHO SUMMIT 1101 – REPLACING TREE ATTACH | # | # | Not assigned | 10 | Created | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 08/01/2019 | ED.15803.1101.SWIT | SWITCHES | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 10/17/2018 | 2018 | # | #VALUE! | UNSE | E570 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
74022380 | *CANC* BRUNSWICK 1103 LR2200 | 5619362 | # | Not assigned | 25 | Canceled | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | JY | JUNK YARD FL TO HOLD DELETED DATA | 029 | NEVADA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 10/22/2018 | 2018 | # | #VALUE! | CNCL | E570 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BRUNSWICK 1103 LR2200 HARDENING | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 178.07
74022381 | *CANC* CWSP - CAMP EVERS 2106 - 50 | # | # | Not assigned | 40 | Closed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/30/2020 | ED.08362.2106 | CAMP EVERS 2106 | 044 | SANTA CRUZ COU | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 10/22/2018 | 2018 | 05/03/2020 | 2020 | CLSD | E570 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Deleted/Cancelled projects | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 559.82
74022382 | CWSP-COLUMBIA HILL 1101-LR 2212 PH1 | 114798646 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 05/21/2020 | ED.15247.1101.SWIT | SWITCHES | 029 | NEVADA COUNTY | 5535211 | CWSP SPO - SH 08 | 12,627.000 | 12,378.000 | 08W | 10/22/2018 | 2018 | # | #VALUE! | DOCC | E570 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-COLUMBIA HILL 1101-LR 2212 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 4356544.28
74022383 | CWSP-EL DORADO PH 2102 LR19542 PH 1.0 | 114791963 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.15276.2101.SWIT | SWITCHES | 009 | EL DORADO COUN | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 10/22/2018 | 2018 | # | #VALUE! | UNSE | E570 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - EL DORADO PH 2101 LR 26000 PH 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 33731.28
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | 114753320 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 03/12/2021 | ED.04275.1113.RECL | RECLOSERS | 049 | SONOMA COUNTY | 5535211 | CWSP SPO - SH 08 | 28,754.000 | 4,200.000 | 08W | 10/22/2018 | 2018 | # | #VALUE! | CONS | E570 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 5450464.95
74022385 | ECEIVED SIZE CATCWSP-KONOCTI 1102-LR 532 | 114691436 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 11/30/2020 | ED.04331.1102.SWIT | SWITCHES | 017 | LAKE COUNTY | 5535211 | CWSP SPO - SH 08 | 14,918.000 | 0.000 | 08W | 10/22/2018 | 2018 | # | #VALUE! | APPR | E570 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-KONOCTI 1102-LR 532 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 603940.67
74022386 | *CANC* CWSP - LOS GATOS 1106 - LB4 | 5619500 | # | Not assigned | 30 | Technically Completed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/30/2020 | ED.08202.1106 | LOS GATOS 1106 | 043 | SANTA CLARA CO | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 10/22/2018 | 2018 | # | #VALUE! | PROD | E570 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Deleted/Cancelled projects | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 47277.07
74022387 | CWSP-MIDDLETOWN 1101-TS 1079 | 114701413 | # | Not assigned | 30 | Technically Completed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 11/30/2020 | ED.04314.1101.SWIT | SWITCHES | 017 | LAKE COUNTY | 5535211 | CWSP SPO - SH 08 | 21,915.000 | 20,962.000 | 08W | 10/22/2018 | 2018 | # | #VALUE! | FICL | E570 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP: MIDDLETOWN 1101 TS 1079 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 5585990.23
74022388 | OCGC CWSP: X-1104 OH RECOND SKYLINE | 114266765 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 03/01/2020 | ED.26-F070700000.STRU.POLE | CENTRAL F0707 POLES | 001 | ALAMEDA COUNTY | 5537523 | X-1104 OH RECOND SKYLINE | 3,677.000 | 8,409.000 | 08W | 10/22/2018 | 2018 | # | #VALUE! | DOCC | E570 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | OAKLAND X-1104 OH RECOND SKYLINE | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 3188269.54
74022389 | CWSP - PARADISE 1106 - OCB & LR 2234 | 114742450 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2019 | ED.10283.1106.SWIT | SWITCHES | 004 | BUTTE COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 10/22/2018 | 2018 | # | #VALUE! | UNSE | E570 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - PARADISE 1106 - OCB & LR 2234 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 21364.3
74022390 | CWSP - SILVERADO 2104- LR722-PH 1A | 114592131 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | ED.04343.2104 | SILVERADO 2104 | 028 | NAPA COUNTY | 5535211 | CWSP SPO - SH 08 | 5,124.000 | 5,124.000 | 08W | 10/22/2018 | 2018 | # | #VALUE! | DOCC | E570 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - NORTH BAY WILDFIRE HARDENING PROJ | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 2659331.41
74022391 | *CANC* **DO NOT USE**CWSP - VOLTA 1102 | 12008970 | # | Not assigned | 25 | Canceled | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/31/2020 | JY | JUNK YARD FL TO HOLD DELETED DATA | 045 | SHASTA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 10/22/2018 | 2018 | # | #VALUE! | CNCL | E570 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Deleted/Cancelled projects | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 4711.78
74022614 | CWSP - CAMP FIRE PADSE 1105 QUAIL RD | 115340065 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/07/2018 | JY | JUNK YARD FL TO HOLD DELETED DATA | 004 | BUTTE COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 11/12/2018 | 2018 | # | #VALUE! | UNSE | E570 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Paradise 1105 Rebuild Qual Rd | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
74022615 | CWSP - CAMP FIRE PADSE 1105 PENTZ RD | 115340017 | # | Not assigned | 30 | Technically Completed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/07/2018 | ED.10283.1105.SWIT | SWITCHES | 004 | BUTTE COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 11/12/2018 | 2018 | # | #VALUE! | FICL | E570 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Paradise 1105 Rebuild Pentz Rd | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 551.58
74022620 | *DO NOT USE* RPL OH WIRE ON OTTER-1101 S | # | # | Not assigned | 10 | Created | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 06/28/2019 | ED.07-N031000000.STRU.POLE | MONTEREY N0310 POLES | 027 | MONTEREY COUNT | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 11/07/2018 | 2018 | # | #VALUE! | DCNL | E570 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | GRC Electric Dist | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
74022663 | CAMP FIRE RECOND LINE HONEY RN BUTTE 05 | 115345680 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/07/2018 | JY | JUNK YARD FL TO HOLD DELETED DATA | 004 | BUTTE COUNTY | 5535211 | CWSP SPO - SH 08 | 24,559.000 | 0.000 | 08W | 11/14/2018 | 2018 | # | #VALUE! | DOCC | E570 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Camp Fire Recond Line Honey Rn Butte 05 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | -978992.66
74022664 | CAMP FIRE RECONDUCTOR LINE DEPOT RD | 115344105 | # | Not assigned | 30 | Technically Completed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/14/2018 | ED.10283.1104.RECL | RECLOSERS | 004 | BUTTE COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 3,000.000 | 08W | 11/14/2018 | 2018 | # | #VALUE! | FICL | E570 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Camp Fire Reconductor Line Depot Rd | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 95196.57
74022720 | CWSP-CAMP FIRE PADSE 1105 INST BIKE PATH | 115340074 | # | Not assigned | 30 | Technically Completed | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/07/2018 | JY | JUNK YARD FL TO HOLD DELETED DATA | 004 | BUTTE COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 11/13/2018 | 2018 | # | #VALUE! | FICL | E570 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Paradise 1106 Rebuild Bike Path | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 18134.2
74022721 | CWSP - CAMP FIRE PADSE 1106 BILLIE RD | 115339958 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/07/2018 | JY | JUNK YARD FL TO HOLD DELETED DATA | 004 | BUTTE COUNTY | 5535211 | CWSP SPO - SH 08 | 9,477.000 | 0.000 | 08W | 11/13/2018 | 2018 | # | #VALUE! | DOCC | E570 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Paradise 1105 Rebuild Bille Rd | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 56372.34
74022722 | CWSP-CAMP FIRE PDSE 1104 PEARSON RD | 115342410 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/15/2018 | ED.10283.1105.RECL | RECLOSERS | 004 | BUTTE COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 11/13/2018 | 2018 | # | #VALUE! | ESTS | E570 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Paradise 1104 Rebuild Pearson Rd | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 241992.16
74022723 | CWSP - CAMP FIRE PDSE 1106 PONDEROSA WAY | 115342359 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 12/15/2018 | ED.10283.1105.RECL | RECLOSERS | 004 | BUTTE COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 11/13/2018 | 2018 | # | #VALUE! | PEND | E570 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Paradise 1106 Rebuild South Park Dr | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 62992.31
74024171 | CALISTOGA 1101 HIGH SPLICE COUNT | 113742411 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 10/17/2019 | ED.42-FF30000000.STRU.POLE | SILVERADO FF30 POLES | 028 | NAPA COUNTY | 5535211 | CWSP SPO - SH 08 | 13,780.000 | 13,780.000 | 08W | 02/14/2019 | 2019 | # | #VALUE! | DOCC | E570 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CALISTOGA 1101 HIGH SPLICE COUNT | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 3324851.52
74024660 | 2019 CALISTOGA 1101 SUB ORDER | # | 74022040 | 2019 CALISTOGA 1101 HIGH SPLICE COUNT | 10 | Created | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | # | ED.04271.1101 | CALISTOGA 1101 | 028 | NAPA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 03/04/2019 | 2019 | # | #VALUE! | UNSE | E570 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
74024661 | CWSP-BRUNSWICK 1105 LR32536 PH1 SUBORDER | # | 74021960 | CWSP-BRUNSWICK 1105 LR-32536 ZONE # PH 1 | 10 | Created | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | # | ED.15248.1105 | BRUNSWICK 1105 | 029 | NEVADA COUNTY | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 03/04/2019 | 2019 | # | #VALUE! | UNSE | E570 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
74028021 | CWSP - MIRABEL 02/MONTE RIO 13-LR652 PH2 | 117755928 | # | Not assigned | 20 | Released | ECES_CA2 | Capital Status w/ Deferred | # | Not assigned | [8 empty] | 02/16/2021 | ED.04209.1102.RECL | RECLOSERS | 049 | SONOMA COUNTY | 5535211 | CWSP SPO - SH 08 | 13,421.000 | 0.000 | 08W | 08/14/2019 | 2019 | # | #VALUE! | CONS | E570 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP: MIRABEL 1102 / MONTE RIO 1113 LR 6 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 2959261.08
80000813 | *CANC* E RECONDUCTOR OAKHURST 1103*CANC | 102310692 | # | Not assigned | 40 | Closed | ZWRMSTAT | WRM order status profile | # | Not assigned | [8 empty] | 12/31/2012 | ED.72-5212340000.PRIM.SWIT | YOSEMITE MAP 521234 SWITCHES | 022 | MARIPOSA COUNT | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 10/08/2007 | 2007 | 08/04/2013 | 2013 | CLSD | EIMA | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
80003462 | E REPL ANNEALD CNDCTR GARBERVILLE *CANC | # | # | Not assigned | 40 | Closed | ZWRMSTAT | WRM order status profile | # | Not assigned | [8 empty] | 11/30/2007 | ED | Electric Distribution System | # | Not assigned | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 10/08/2007 | 2007 | 08/04/2010 | 2010 | CLSD | EIMA | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
80005579 | E RECONDUCTORING PART OF TAPLIN RD *CANC | 102408949 | # | Not assigned | 40 | Closed | ZWRMSTAT | WRM order status profile | # | Not assigned | [8 empty] | 03/28/2008 | ED | Electric Distribution System | # | Not assigned | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 10/08/2007 | 2007 | 10/02/2008 | 2008 | CLSD | EIMA | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
80005607 | *CANC*E RECONDUCTOR 3200-FT #6CU CA*CANC | 101850543 | # | Not assigned | 40 | Closed | ZWRMSTAT | WRM order status profile | # | Not assigned | [8 empty] | # | ED.11-O2125D0000.PRIM.SWIT | MARYSVILLE O2125D SWITCHES | 051 | SUTTER COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 10/08/2007 | 2007 | 11/03/2010 | 2010 | CLSD | EIMA | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
80006405 | R4E E RECONDUC 10000-FT #6CU PLUMAS 1 | # | # | Not assigned | 40 | Closed | ZWRMSTAT | WRM order status profile | # | Not assigned | [8 empty] | # | ED.11-O2125D0000.PRIM.SWIT | MARYSVILLE O2125D SWITCHES | 051 | SUTTER COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 10/08/2007 | 2007 | 06/23/2012 | 2012 | CLSD | EIMA | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
80007786 | R* E ANNEALED #6 MERCED 14 *CANC | # | # | Not assigned | 40 | Closed | ZWRMSTAT | WRM order status profile | # | Not assigned | [8 empty] | 10/24/2008 | ED.72-0347000000.PRIM.SWIT | YOSEMITE 0347 SWITCHES | # | Not assigned | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 10/08/2007 | 2007 | 09/02/2009 | 2009 | CLSD | EIMA | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
80009542 | R5EP RECON 3854FT - KERN OIL 1108 B*CANC | 100116377 | # | Not assigned | 40 | Closed | ZWRMSTAT | WRM order status profile | # | Not assigned | [8 empty] | 12/31/1999 | ED.66-2827366000 | KERN MAP 2827366 | A4 | AREA 4 | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 10/08/2007 | 2007 | 06/24/2013 | 2013 | CLSD | EIMA | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
80009637 | E RECONDUCTOR OH PLACERVILE 110 *CANC | # | # | Not assigned | 40 | Closed | ZWRMSTAT | WRM order status profile | # | Not assigned | [8 empty] | # | ED | Electric Distribution System | # | Not assigned | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 10/08/2007 | 2007 | 07/02/2008 | 2008 | CLSD | EIMA | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
80009960 | R4E E REPLACE 6C CNDUCTOR HARTER 11*CANC | # | # | Not assigned | 40 | Closed | ZWRMSTAT | WRM order status profile | # | Not assigned | [8 empty] | 07/25/2008 | ED | Electric Distribution System | # | Not assigned | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 10/08/2007 | 2007 | 09/02/2009 | 2009 | CLSD | EIMA | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
80041275 | (UNC) RES 1102 REPL 5420 FT DETERIOR | 102806100 | # | Not assigned | 40 | Closed | ZWRMSTAT | WRM order status profile | # | Not assigned | [8 empty] | 05/23/2008 | ED.18273.1102.SWIT | SWITCHES | # | Not assigned | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 01/29/2008 | 2008 | 09/12/2013 | 2013 | CLSD | EIMA | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | -2.1
80042412 | UPGRADE 4CWC TO 2AR ON ANTLER 1101 | 102814375 | # | Not assigned | 40 | Closed | ZWRMSTAT | WRM order status profile | # | Not assigned | [8 empty] | 03/28/2008 | ED.10327.1101 | ANTLER 1101 | # | Not assigned | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 02/03/2008 | 2008 | 09/12/2013 | 2013 | CLSD | EIMA | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | -2.1
80047407 | PET A 413 REPL ANNEALED CONDUCTOR | 102870854 | # | Not assigned | 40 | Closed | ZWRMSTAT | WRM order status profile | NC | NORTH COAST | [8 empty] | 04/04/2008 | ED.04212.0411.SWIT | SWITCHES | # | Not assigned | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 02/28/2008 | 2008 | 06/05/2012 | 2012 | CLSD | EIMA | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
80048631 | REPLACE ANNEALED COND -CALPELLA 1 | # | # | Not assigned | 40 | Closed | ZWRMSTAT | WRM order status profile | # | Not assigned | [8 empty] | # | ED.04341.1101.SWIT | SWITCHES | 023 | MENDOCINO COUN | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 03/05/2008 | 2008 | 06/02/2012 | 2012 | CLSD | EIMA | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
80053008 | C *CANC | 102944673 | # | Not assigned | 40 | Closed | ZWRMSTAT | WRM order status profile | # | Not assigned | [8 empty] | # | ED.18277.1101 | CAMBRIA 1101 | # | Not assigned | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 03/25/2008 | 2008 | 06/04/2008 | 2008 | CLSD | EIMA | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
80055653 | PART 2 OF 2 ANNEALED #6 *CANC | 102983715 | # | Not assigned | 40 | Closed | ZWRMSTAT | WRM order status profile | # | Not assigned | [8 empty] | # | ED.25280.1114.SWIT | SWITCHES | # | Not assigned | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 04/22/2008 | 2008 | 08/04/2008 | 2008 | CLSD | EIMA | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
80058495 | CNCL R4E RECONDUCT ON PUTAH CREEK *CANC | 103094331 | # | Not assigned | 40 | Closed | ZWRMSTAT | WRM order status profile | # | Not assigned | [8 empty] | 12/31/2008 | ED.06368.1102 | PUTAH CREEK 1102 | # | Not assigned | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 06/06/2008 | 2008 | 08/03/2010 | 2010 | CLSD | EIMA | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
80058496 | R4 RECONDUCT PUTAH CREEK 1102-PHASE*CANC | 103094338 | # | Not assigned | 40 | Closed | ZWRMSTAT | WRM order status profile | # | Not assigned | [8 empty] | 12/31/2008 | ED.06368.1102 | PUTAH CREEK 1102 | # | Not assigned | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 06/06/2008 | 2008 | 08/03/2010 | 2010 | CLSD | EIMA | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
80058498 | CNCL R4 RECONDUCT PUTAH CREEK 1102-*CANC | 103094373 | # | Not assigned | 40 | Closed | ZWRMSTAT | WRM order status profile | # | Not assigned | [8 empty] | 12/31/2008 | ED.06368.1102 | PUTAH CREEK 1102 | # | Not assigned | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 06/06/2008 | 2008 | 08/03/2010 | 2010 | CLSD | EIMA | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
80058499 | CNCL RECONDUCT ON PUTAH CREEK 1102-*CANC | 103094374 | # | Not assigned | 40 | Closed | ZWRMSTAT | WRM order status profile | # | Not assigned | [8 empty] | 12/31/2008 | ED.06368.1102 | PUTAH CREEK 1102 | # | Not assigned | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 06/06/2008 | 2008 | 08/03/2010 | 2010 | CLSD | EIMA | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
80058560 | R4E RECONDUCT PUTAH CREEK 1102-PHA*CANC | 103094375 | # | Not assigned | 40 | Closed | ZWRMSTAT | WRM order status profile | # | Not assigned | [8 empty] | 12/31/2008 | ED.06368.1102 | PUTAH CREEK 1102 | # | Not assigned | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 06/06/2008 | 2008 | 08/03/2010 | 2010 | CLSD | EIMA | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
80058638 | CNCL ARCATA 1122 REPLACE ANNEALED W*CANC | 103099064 | # | Not assigned | 40 | Closed | ZWRMSTAT | WRM order status profile | # | Not assigned | [8 empty] | 10/31/2008 | ED | Electric Distribution System | # | Not assigned | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 06/11/2008 | 2008 | 08/03/2010 | 2010 | CLSD | EIMA | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
80058762 | CNCL RECONDUCTOR KNIGHTS LDG 1101- *CANC | 103099669 | # | Not assigned | 40 | Closed | ZWRMSTAT | WRM order status profile | # | Not assigned | [8 empty] | 12/30/2008 | ED.06272.1101 | KNIGHTS LANDING 1101 | # | Not assigned | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 06/11/2008 | 2008 | 08/03/2010 | 2010 | CLSD | EIMA | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
80058763 | CNCL RECONDUCTOR KNIGHTS LDG 1101-P*CANC | 103099685 | # | Not assigned | 40 | Closed | ZWRMSTAT | WRM order status profile | # | Not assigned | [8 empty] | 12/30/2008 | ED.06272.1101 | KNIGHTS LANDING 1101 | # | Not assigned | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 06/11/2008 | 2008 | 08/03/2010 | 2010 | CLSD | EIMA | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
80058764 | CNCL RECONDUCTOR KNIGHTS LDG 1101-P*CANC | 103099688 | # | Not assigned | 40 | Closed | ZWRMSTAT | WRM order status profile | # | Not assigned | [8 empty] | 12/30/2008 | ED.06272.1101 | KNIGHTS LANDING 1101 | # | Not assigned | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 06/11/2008 | 2008 | 08/03/2010 | 2010 | CLSD | EIMA | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
80059045 | CNCL RECONDUCTOR KNIGHTS LDG 1101- P | 103106965 | # | Not assigned | 40 | Closed | ZWRMSTAT | WRM order status profile | # | Not assigned | [8 empty] | 12/30/2008 | ED.06272.1101 | KNIGHTS LANDING 1101 | # | Not assigned | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 06/17/2008 | 2008 | 06/05/2012 | 2012 | CLSD | EIMA | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
80059231 | CNCL R7 REPLACE ANNEALED CONDUCTOR*CANC | 103115595 | # | Not assigned | 40 | Closed | ZWRMSTAT | WRM order status profile | # | Not assigned | [8 empty] | 10/03/2008 | ED.04256.1102.REGL | REGULATORS | 049 | SONOMA COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 06/24/2008 | 2008 | 08/03/2010 | 2010 | CLSD | EIMA | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
80060333 | CNCL R* REDBUD 1101 & 1102 RECONDU*CANC | 103163267 | # | Not assigned | 40 | Closed | ZWRMSTAT | WRM order status profile | # | Not assigned | [8 empty] | 04/01/2009 | ED.04319.1101.SWIT | SWITCHES | 017 | LAKE COUNTY | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 07/21/2008 | 2008 | 08/03/2010 | 2010 | CLSD | EIMA | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
80064228 | CNCL PINE GROVE 1102 REPL 6280' ANN*CANC | 103568710 | # | Not assigned | 40 | Closed | ZWRMSTAT | WRM order status profile | # | Not assigned | [8 empty] | 04/01/2009 | ED.16375.1102 | PINE GROVE 1102 | # | Not assigned | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 11/26/2008 | 2008 | 08/03/2010 | 2010 | CLSD | EIMA | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0

## OTHER ORDERS DATA
Order | Order Description | Notification | Superior Order | Superior Order Description | Status | Status Description | Status Profile | Status Profile Description | Division | Division Description | Created by LANID | Created by | Job Owner LANID | Job Owner | Estimator LANID | Estimator | ADE LANID | ADE | Baseline In-Srvc Dt | Functional Loc | Functional Loc Description | Plant section | Plant Section Description | Summarized Planning | Summarized Planning Description | Estimated Units | Actual Units | MAT | Created On | Closed Date | User Status | Order Type | MWC | MWC Description | Program | Program Description | Reason Code | Project Definition | Funding ID Category | Funding Identifier | Funding ID Level 1 | Funding Id Level 2 | Current Year Organiz | Next Year Organizati | $
1014895 | Contract Estimating 08W Planning | # | # | Not assigned | 20 | Released | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5786123 | 08W Rebuild | 0.000 | 0.000 | 08W | 09/16/2020 | # | Not assigned | 0010 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 1669995.86
5505499 | EB-OH ANNEALED/DETER CNDCTR: PM MGD | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 08/27/2003 | # | Not assigned | 0055 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
5505501 | SI-OH ANNEALED/DETER CNDCTR: PM MGD | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 08/27/2003 | # | Not assigned | 0055 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
5505502 | CC-OH ANNEALED/DETER CNDCTR: PM MGD | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 08/27/2003 | # | Not assigned | 0055 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
5505503 | SF-OH Annealed/Deterioratd Cndctr | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 08/27/2003 | # | Not assigned | 0055 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
5505504 | YO-OH ANNEALED/DETER CNDCTR: PM MGD | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 08/27/2003 | # | Not assigned | 0055 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
5505505 | 08J - OH Annealed/Det Cond - E - SO | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 08/27/2003 | # | Not assigned | 0055 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
5505506 | MI-OH Annealed/Deterioratd Cndctr | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 08/27/2003 | # | Not assigned | 0055 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
5505507 | NV-OH ANNEALED/DETER CNDCTR: PM MGD | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 08/27/2003 | # | Not assigned | 0055 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
5505508 | DA-OH Annealed/Deterioratd Cndctr | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5517127 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 08/27/2003 | # | Not assigned | 0055 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
5505509 | NB-OH ANNEALED/DETER CNDCTR: PM MGD | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 08/27/2003 | # | Not assigned | 0055 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
5505510 | KE-OH Annealed/Deterioratd Cndctr | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 08/27/2003 | # | Not assigned | 0055 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
5505511 | FR-OH ANNEALED/DETER CNDCTR: PM MGD | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 08/27/2003 | # | Not assigned | 0055 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
5505512 | SA-OH ANNEALED/DETER CNDCTR: PM MGD | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 08/27/2003 | # | Not assigned | 0055 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
5505513 | PN-OH ANNEALED/DETER CNDCTR: PM MGD | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5505513 | PN-OH ANNEALED/DETER CNDCTR: PM MGD | 0.000 | 0.000 | 08J | 08/27/2003 | # | Not assigned | 0055 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
5505514 | LP-OH ANNEALED/DETER CNDCTR: PM MGD | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 08/27/2003 | # | Not assigned | 0055 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
5505515 | SJ-OH Annealed/Deterioratd Cndctr | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 08/27/2003 | # | Not assigned | 0055 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
5505516 | ST-OH Annealed/Deterioratd Cndctr | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 08/27/2003 | # | Not assigned | 0055 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
5505517 | DI-OH ANNEALED/DETER CNDCTR: PM MGD | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 08/27/2003 | # | Not assigned | 0055 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
5507900 | 08-Annealed Conductor Program | # | # | Not assigned | 40 | Closed | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5517127 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 09/10/2007 | 05/01/2019 | Not assigned | 0055 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | GRC Electric Dist | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
5508971 | 08J - OH ANNEAL/DET COND - E-HB: PM MGD | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 10/13/2009 | # | Not assigned | 0055 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
5511430 | MWC 08J Escalation | # | # | Not assigned | 40 | Closed | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5511430 | MWC 08J Escalation | 0.000 | 0.000 | 08J | 03/30/2012 | 04/23/2019 | Not assigned | 0055 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | GRC Electric Dist | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
5513259 | 08J- WIRE DOWN GEN PROJ - CC: PM MGD | # | # | Not assigned | 40 | Closed | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08J | 04/04/2013 | 07/18/2018 | Not assigned | 0055 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
5513260 | 08W - Wire Down Generated Projects - DA | # | # | Not assigned | 40 | Closed | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 04/04/2013 | 07/12/2018 | Not assigned | 0055 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
5513261 | 08J- WIRE DOWN GEN PROJ - DI: PM MGD | # | # | Not assigned | 40 | Closed | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08J | 04/04/2013 | 07/12/2018 | Not assigned | 0055 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
5513262 | 08J- Wire Down Generated Projects - EB | # | # | Not assigned | 40 | Closed | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08J | 04/04/2013 | 07/12/2018 | Not assigned | 0055 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
5513263 | 08J- WIRE DOWN GEN PROJ - FR: PM MGD | # | # | Not assigned | 40 | Closed | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08J | 04/04/2013 | 07/18/2018 | Not assigned | 0055 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
5513264 | 08W - Wire Down Generated Projects - HB | # | # | Not assigned | 40 | Closed | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 04/04/2013 | 05/01/2019 | Not assigned | 0055 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
5513265 | 08W - Wire Down Generated Projects - KE | # | # | Not assigned | 40 | Closed | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 04/04/2013 | 07/12/2018 | Not assigned | 0055 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
5513266 | 08J- Wire Down Generated Projects - LP | # | # | Not assigned | 40 | Closed | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08J | 04/04/2013 | 07/18/2018 | Not assigned | 0055 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
5513267 | 08J- Wire Down Generated Projects - MI | # | # | Not assigned | 40 | Closed | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08J | 04/04/2013 | 07/12/2018 | Not assigned | 0055 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
5513268 | 08W - WIRE DOWN GEN PROJ - NB: PM MGD | # | # | Not assigned | 40 | Closed | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 04/04/2013 | 07/12/2018 | Not assigned | 0055 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
5513269 | 08J- Wire Down Generated Projects - NV | # | # | Not assigned | 40 | Closed | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08J | 04/04/2013 | 07/12/2018 | Not assigned | 0055 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
5513270 | 08J- Wire Down Generated Projects - PN | # | # | Not assigned | 40 | Closed | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 04/04/2013 | 07/18/2018 | Not assigned | 0055 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
5513271 | 08J- Wire Down Generated Projects - SA | # | # | Not assigned | 40 | Closed | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08J | 04/04/2013 | 07/18/2018 | Not assigned | 0055 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
5513272 | 08J- Wire Down Generated Projects - SF | # | # | Not assigned | 40 | Closed | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5517127 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 04/04/2013 | 07/18/2018 | Not assigned | 0055 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | GRC Electric Dist | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
5513273 | 08J- Wire Down Generated Projects - SI | # | # | Not assigned | 40 | Closed | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08J | 04/04/2013 | 07/12/2018 | Not assigned | 0055 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
5513274 | 08J- Wire Down Generated Projects - SJ | # | # | Not assigned | 40 | Closed | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08J | 04/04/2013 | 07/12/2018 | Not assigned | 0055 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
5513275 | 08J- WIRE DOWN GEN PROJ - SO: PM MGD | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 04/04/2013 | # | Not assigned | 0055 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
5513276 | 08J Wire Down Generated Projects - ST | # | # | Not assigned | 40 | Closed | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08J | 04/04/2013 | 07/18/2018 | Not assigned | 0055 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
5513277 | 08J Wire Down Generated Projects - YO | # | # | Not assigned | 40 | Closed | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08J | 04/04/2013 | 07/12/2018 | Not assigned | 0055 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
5515843 | 08W - Emergent Work | # | # | Not assigned | 40 | Closed | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5517127 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08W | 09/15/2014 | 05/01/2019 | Not assigned | 0055 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | GRC Electric Dist | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
5515863 | 08J - Emergent Work | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 09/18/2014 | # | Not assigned | 0055 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
5516384 | SYSPLN-08J-Replace Deteriorated OH Condu | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5516384 | SYSPLN-08J-Replace Deteriorated OH Condu | 0.000 | 0.000 | 08J | 11/19/2014 | # | Not assigned | 0055 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | GRC Electric Dist | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
5516386 | SYSPLN-08W- System Rebuild (RAMP/CWSP) | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5516386 | SYSPLN-08W- System Rebuild (RAMP/CWSP) | 0.000 | 0.000 | 08W | 11/19/2014 | # | Not assigned | 0055 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Base Capital | GRC Electric Dist | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
5518029 | SYSPLN-08J-ESCALATION | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5518029 | SYSPLN-08J-ESCALATION | 0.000 | 0.000 | 08J | 04/23/2015 | # | Not assigned | 0055 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | GRC Electric Dist | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
5518031 | SYSPLN-08W-ESCALATION | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5518031 | SYSPLN-08W-ESCALATION | 0.000 | 0.000 | 08W | 04/23/2015 | # | Not assigned | 0055 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | GRC Electric Dist | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
5519544 | EB-OH ANNEAL/DETER CNDCTR: NON-PM MGD | # | # | Not assigned | 40 | Closed | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5517127 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 10/15/2015 | 05/01/2019 | Not assigned | 0055 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
5519545 | SI-OH ANNEAL/DETER CNDCTR: NON-PM MGD | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 10/15/2015 | # | Not assigned | 0055 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
5519546 | CC-OH ANNEAL/DETER CNDCTR: NON-PM MGD | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5517127 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 10/15/2015 | # | Not assigned | 0055 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Overhead Reductoring Project | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
5519548 | NV-OH ANNEAL/DETER CNDCTR: NON-PM MGD | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 10/15/2015 | # | Not assigned | 0055 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
5519558 | 08J- WIRE DOWN GEN PROJ - CC: NON-PM MG | # | # | Not assigned | 40 | Closed | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08J | 10/15/2015 | 07/18/2018 | Not assigned | 0055 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
5519882 | 2015 Carryover: SI-OH ANNEALED/DETER CND | # | # | Not assigned | 40 | Closed | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5517127 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 10/26/2015 | 05/01/2019 | Not assigned | 0055 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | GRC Electric Dist | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
5519883 | 2015 Carryover: CC-OH ANNEALED/DETER CND | # | # | Not assigned | 40 | Closed | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5517127 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 10/26/2015 | 05/01/2019 | Not assigned | 0055 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | GRC Electric Dist | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
5519884 | 2015 Carryover: LP-OH ANNEALED/DETER CND | # | # | Not assigned | 40 | Closed | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5517127 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 10/26/2015 | 05/01/2019 | Not assigned | 0055 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | GRC Electric Dist | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
5522750 | Cost Model Adjustment-08J | # | # | Not assigned | 40 | Closed | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5517127 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 06/23/2016 | 05/02/2019 | Not assigned | 0055 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | GRC Electric Dist | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
5522752 | Cost Model Adjustment-08W | # | # | Not assigned | 40 | Closed | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 06/23/2016 | 05/01/2019 | Not assigned | 0055 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | GRC Electric Dist | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
5528522 | SYSPLN-08J-Rplc Deterior OH Condu (RAMP) | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5528522 | SYSPLN-08J-Rplc Deterior OH Condu (RAMP) | 0.000 | 0.000 | 08J | 11/29/2017 | # | Not assigned | 0055 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | GRC Electric Dist | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
5530159 | 08W - WILDFIRE RESILIENCY - CC | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 03/13/2018 | # | Not assigned | 0055 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5530160 | 08W - WILDFIRE RESILIENCY - DA | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 03/13/2018 | # | Not assigned | 0055 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5530161 | 08W - WILDFIRE RESILIENCY - DI | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 03/13/2018 | # | Not assigned | 0055 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5530162 | 08W - WILDFIRE RESILIENCY - EB | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 03/13/2018 | # | Not assigned | 0055 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5530163 | 08W - WILDFIRE RESILIENCY - FR | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 03/13/2018 | # | Not assigned | 0055 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | 35008479_Auberry 1101 Reconductor | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5530164 | 08W - WILDFIRE RESILIENCY - HB | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 03/13/2018 | # | Not assigned | 0055 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5530165 | 08W - WILDFIRE RESILIENCY - KE | # | # | Not assigned | 40 | Closed | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 03/13/2018 | 05/01/2019 | Not assigned | 0055 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Base Capital | GRC Electric Dist | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
5530166 | 08W - WILDFIRE RESILIENCY - LP | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 03/13/2018 | # | Not assigned | 0055 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5530167 | 08W - WILDFIRE RESILIENCY - MI | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 03/13/2018 | # | Not assigned | 0055 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5530168 | 08W - WILDFIRE RESILIENCY - NB | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 03/13/2018 | # | Not assigned | 0055 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5530169 | 08W - WILDFIRE RESILIENCY - NV | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 03/13/2018 | # | Not assigned | 0055 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5530170 | 08W - WILDFIRE RESILIENCY - PN | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 03/13/2018 | # | Not assigned | 0055 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5530171 | 08W - WILDFIRE RESILIENCY - SA | # | # | Not assigned | 40 | Closed | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 03/13/2018 | 05/01/2019 | Not assigned | 0055 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5530172 | 08W - WILDFIRE RESILIENCY - SF | # | # | Not assigned | 40 | Closed | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5517127 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08W | 03/13/2018 | 05/01/2019 | Not assigned | 0055 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Base Capital | GRC Electric Dist | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
5530173 | 08W - WILDFIRE RESILIENCY - SI | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 03/13/2018 | # | Not assigned | 0055 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5530174 | 08W - WILDFIRE RESILIENCY - SJ | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 03/13/2018 | # | Not assigned | 0055 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5530175 | 08W - WILDFIRE RESILIENCY - SO | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 03/13/2018 | # | Not assigned | 0055 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5530176 | 08W - WILDFIRE RESILIENCY - ST | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 03/13/2018 | # | Not assigned | 0055 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5530177 | 08W - WILDFIRE RESILIENCY - SYSTEM | # | # | Not assigned | 40 | Closed | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 03/13/2018 | 05/01/2019 | Not assigned | 0055 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Base Capital | GRC Electric Dist | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
5530178 | 08W - WILDFIRE RESILIENCY - YO | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 03/13/2018 | # | Not assigned | 0055 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5530362 | SYSPLN-08W-System Rebuild (CWSP) | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5530362 | SYSPLN-08W-System Rebuild (CWSP) | 0.000 | 0.000 | 08W | 04/05/2018 | # | Not assigned | 0055 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | GRC Electric Dist | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
5531041 | 08W - WILDFIRE RESILIENCY PMO | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 05/25/2018 | # | Not assigned | 0055 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5531042 | 08W - WILDFIRE RESILIENCY PMO | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 05/25/2018 | # | Not assigned | 0055 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5532075 | ED MAT 08J (Rate Case) | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5532075 | ED MAT 08J (Rate Case) | 0.000 | 0.000 | 08J | 08/15/2018 | # | Not assigned | 0055 | 08 | E Dist Replace OH Asset | DISTSPT | Distribution Support | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
5532077 | ED MAT 08W (Rate Case) | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5532077 | ED MAT 08W (Rate Case) | 0.000 | 0.000 | 08W | 08/15/2018 | # | Not assigned | 0055 | 08 | E Dist Replace OH Asset | DISTSPT | Distribution Support | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
5532463 | 08W - WILDFIRE 2019 PMO Wedge | # | # | Not assigned | 40 | Closed | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 09/07/2018 | 05/01/2019 | Not assigned | 0055 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | GRC Electric Dist | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5532479 | CWSP 08W - Monthly Forecast Only | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 09/09/2018 | # | Not assigned | 0055 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5532910 | 08J Wave Affordability | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 10/12/2018 | # | Not assigned | 0055 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | GRC Electric Dist | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
5532911 | 08J Efficiency Commitment | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 10/12/2018 | # | Not assigned | 0055 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | GRC Electric Dist | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
5533019 | 08J 2019 Wedge | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 10/16/2018 | # | Not assigned | 0055 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | GRC Electric Dist | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
5533122 | X-1104 OH RECOND SKYLINE | # | # | Not assigned | 40 | Closed | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 10/31/2018 | 05/01/2019 | Not assigned | 0055 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | GRC Electric Dist | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
5533125 | 08J 2019 35 Series Forecast | # | # | Not assigned | 40 | Closed | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5533125 | 08J 2019 35 Series Forecast | 0.000 | 0.000 | 08J | 10/31/2018 | 04/23/2019 | Not assigned | 0055 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | GRC Electric Dist | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
5533127 | 08W 2019 35 Series Forecast | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5533127 | 08W 2019 35 Series Forecast | 0.000 | 0.000 | 08W | 10/31/2018 | # | Not assigned | 0055 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | GRC Electric Dist | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
5533157 | EO-SYSPLN 08J - ED Rep OH Asset | # | # | Not assigned | 40 | Closed | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5533157 | EO-SYSPLN 08J - ED Rep OH Asset | 0.000 | 0.000 | 08J | 10/30/2018 | 04/23/2019 | Not assigned | 0055 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | GRC Electric Dist | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
5533376 | 08J 2021 Planning Wedge | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 11/02/2018 | # | Not assigned | 0055 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | GRC Electric Dist | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
5533378 | 08W 2019 Seasonality Adj | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5533378 | 08W 2019 Seasonality Adj | 0.000 | 0.000 | 08W | 11/02/2018 | # | Not assigned | 0055 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | GRC Electric Dist | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
5533599 | 08W - CWSP Materials | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 11/05/2018 | # | Not assigned | 0055 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5533607 | FRMMA - 08W - WILDFIRE 2019 PMO Wedge | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 11/19/2018 | # | Not assigned | 0055 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5533644 | 08W - WILDFIRE RESILIENCY - CC (PLAN) | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 11/13/2018 | # | Not assigned | 0055 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | 35085847_R2 OH RECONDUCTR ROB ROY 2105 S | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5533645 | 08W - WILDFIRE RESILIENCY - DA (PLAN) | # | # | Not assigned | 40 | Closed | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 11/13/2018 | 05/01/2019 | Not assigned | 0055 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | GRC Electric Dist | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
5533646 | 08W - WILDFIRE RESILIENCY - DI (PLAN) | # | # | Not assigned | 40 | Closed | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 11/13/2018 | 05/01/2019 | Not assigned | 0055 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | GRC Electric Dist | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
5533647 | 08W - WILDFIRE RESILIENCY - EB (PLAN) | # | # | Not assigned | 40 | Closed | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 11/13/2018 | 05/01/2019 | Not assigned | 0055 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | GRC Electric Dist | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
5533648 | 08W - WILDFIRE RESILIENCY - FR (PLAN) | # | # | Not assigned | 40 | Closed | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 11/13/2018 | 05/01/2019 | Not assigned | 0055 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 35008479_Auberry 1101 Reconductor | Base Capital | GRC Electric Dist | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
5533649 | 08W - WILDFIRE RESILIENCY - HB (PLAN) | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 11/13/2018 | # | Not assigned | 0055 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5533650 | 08W - WILDFIRE RESILIENCY - LP (PLAN) | # | # | Not assigned | 40 | Closed | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5517127 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08W | 11/13/2018 | 05/01/2019 | Not assigned | 0055 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | GRC Electric Dist | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
5533651 | 08W - WILDFIRE RESILIENCY - NB (PLAN) | # | # | Not assigned | 40 | Closed | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 11/13/2018 | 05/01/2019 | Not assigned | 0055 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | GRC Electric Dist | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
5533652 | 08W - WILDFIRE RESILIENCY - NV (PLAN) | # | # | Not assigned | 40 | Closed | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 11/13/2018 | 05/01/2019 | Not assigned | 0055 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | GRC Electric Dist | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
5533653 | 08W - WILDFIRE RESILIENCY - PN (PLAN) | # | # | Not assigned | 40 | Closed | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 11/13/2018 | 05/01/2019 | Not assigned | 0055 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | GRC Electric Dist | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
5533654 | 08W - WILDFIRE RESILIENCY - SI (PLAN) | # | # | Not assigned | 40 | Closed | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 11/13/2018 | 05/01/2019 | Not assigned | 0055 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | GRC Electric Dist | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
5533655 | 08W - WILDFIRE RESILIENCY - ST (PLAN) | # | # | Not assigned | 40 | Closed | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 11/13/2018 | 05/01/2019 | Not assigned | 0055 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | GRC Electric Dist | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
5533664 | 08W - WILDFIRE 2019 PMO Wedge (PLAN) | # | # | Not assigned | 40 | Closed | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 11/13/2018 | 05/01/2019 | Not assigned | 0055 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | GRC Electric Dist | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
5533679 | FRMMA - 08W - WILDFIRE RESILIENCY - CC | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5533679 | FRMMA - 08W - WILDFIRE RESILIENCY - CC | 0.000 | 0.000 | 08W | 11/14/2018 | # | Not assigned | 0055 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5533680 | FRMMA - 08W - WILDFIRE RESILIENCY - D | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 11/14/2018 | # | Not assigned | 0055 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5533681 | FRMMA - 08W - WILDFIRE RESILIENCY - DI | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 11/14/2018 | # | Not assigned | 0055 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5533682 | FRMMA - 08W - WILDFIRE RESILIENCY - EB | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 11/14/2018 | # | Not assigned | 0055 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5533683 | FRMMA - 08W - WILDFIRE RESILIENCY - FR | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 11/14/2018 | # | Not assigned | 0055 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5533684 | FRMMA - 08W - WILDFIRE RESILIENCY - HB | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 11/14/2018 | # | Not assigned | 0055 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5533685 | FRMMA - 08W - WILDFIRE RESILIENCY - LP | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 11/14/2018 | # | Not assigned | 0055 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5533686 | FRMMA - 08W - WILDFIRE RESILIENCY - NB | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 11/14/2018 | # | Not assigned | 0055 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5533687 | FRMMA - 08W - WILDFIRE RESILIENCY - NV | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 11/14/2018 | # | Not assigned | 0055 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5533688 | FRMMA - 08W - WILDFIRE RESILIENCY - PN | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 11/14/2018 | # | Not assigned | 0055 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5533689 | FRMMA - 08W - WILDFIRE RESILIENCY - SI | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 11/14/2018 | # | Not assigned | 0055 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5533690 | FRMMA - 08W - WILDFIRE RESILIENCY - ST | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 11/14/2018 | # | Not assigned | 0055 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5535211 | CWSP SPO - SH 08 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 04/01/2019 | # | Not assigned | 0055 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5537523 | X-1104 OH RECOND SKYLINE | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5537523 | X-1104 OH RECOND SKYLINE | 0.000 | 0.000 | 08W | 10/04/2019 | # | Not assigned | 0055 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | OAKLAND X-1104 OH RECOND SKYLINE | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5538096 | SYSPLN-DIST-08W-Wildfire Resiliency proj | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5538096 | SYSPLN-DIST-08W-Wildfire Resiliency proj | 0.000 | 0.000 | 08W | 11/21/2019 | # | Not assigned | 0055 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | GRC Electric Dist | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
5538400 | MWC 08 2020 Non-PM Planning | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 12/04/2019 | # | Not assigned | 0055 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
5539421 | ECOP-STANISLAUS 1702-H03-LR1850 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 03/03/2020 | # | Not assigned | 0055 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5539422 | ECOP-MONTE RIO 1113-H07-LR180 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 03/03/2020 | # | Not assigned | 0055 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5539424 | CWSP-PLACERVILLE 2106-LR1104-PH 1.4 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 03/05/2020 | # | Not assigned | 0055 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Placerville 2106 - LR 1104 - Ph 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5539425 | CWSP-PLACERVILLE 2106-LR1104-PH 1.5 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 03/05/2020 | # | Not assigned | 0055 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Placerville 2106 - LR 1104 - Ph 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5539426 | CWSP-PLACERVILLE 2106-LR1104-PH 1.6 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 03/05/2020 | # | Not assigned | 0055 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Placerville 2106 - LR 1104 - Ph 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5539427 | CWSP-PLACERVILLE 2106-LR1104-PH 1.7 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 03/05/2020 | # | Not assigned | 0055 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Placerville 2106 - LR 1104 - Ph 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5539442 | CWSP-PLACERVILLE 2106-LR1104-PH 1.2 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 03/04/2020 | # | Not assigned | 0055 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Placerville 2106 - LR 1104 - Ph 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5539678 | 08J 2020 PLANS | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 03/23/2020 | # | Not assigned | 0055 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | GRC Electric Dist | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
5540299 | CWSP-PLACERVILLE 2106 LR1104 PH 3.6 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 05/12/2020 | # | Not assigned | 0055 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-PLACERVILLE 2106 LR1104 PH 3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5540300 | CWSP-PLACERVILLE 2106 LR1104 PH 3.7 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 05/12/2020 | # | Not assigned | 0055 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-PLACERVILLE 2106 LR1104 PH 3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5540306 | CWSP-PLACERVILLE 2106 LR1104 PH 2.6 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 05/12/2020 | # | Not assigned | 0055 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Placerville 2106 - LR 1104 - Phas | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5540307 | CWSP-PLACERVILLE 2106 LR1104 PH 2.7 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 05/12/2020 | # | Not assigned | 0055 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Placerville 2106 - LR 1104 - Phas | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5540925 | 08W Rebuild - 3rd Party Trench (Cap JE) | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5540925 | 08W Rebuild - 3rd Party Trench (Cap JE) | 0.000 | 0.000 | 08W | 06/24/2020 | # | Not assigned | 0055 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5540989 | 08J PRJ Input | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 07/01/2020 | # | Not assigned | 0055 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
5541242 | Community Resilience Program | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5541242 | Community Resilience Program | 0.000 | 0.000 | 08J | 07/14/2020 | # | Not assigned | 0055 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
5541247 | CWSP-PLACERVILLE 2106 LR1104 PH 2.6 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 07/16/2020 | # | Not assigned | 0055 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5541300 | ECOP - MONTE RIO 1113 - H06-LR8299 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 07/20/2020 | # | Not assigned | 0055 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - MONTE RIO 1113 - H06-LR8299 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5541301 | ECOP - MONTE RIO 1111 - H01-LR64758 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 07/20/2020 | # | Not assigned | 0055 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - MONTE RIO 1111 - H01-LR64758 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5541302 | ECOP - OAKHURST 1103 - H01-LR10190 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 07/20/2020 | # | Not assigned | 0055 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - OAKHURST 1103 - H01-LR10190 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5541303 | ECOP - SILVERADO 2102 - H02-LR58626 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 07/20/2020 | # | Not assigned | 0055 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - SILVERADO 2102 - H02-LR58626 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5541304 | ECOP - BRUNSWICK 1106 - H03 - LR4639 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 07/20/2020 | # | Not assigned | 0055 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - BRUNSWICK 1106 - H03 - LR4639 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5541305 | ECOP - LAS GALLINAS A 1105 - H01-LR99904 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 07/20/2020 | # | Not assigned | 0055 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - LAS GALLINAS A 1105 - H01-LR99904 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5541306 | ECOP - MIWUK 1702 - H02-LR9270 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 07/20/2020 | # | Not assigned | 0055 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - MIWUK 1702 - H02-LR9270 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5541307 | ECOP - MIWUK 1702 - H03-LR9270 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 07/20/2020 | # | Not assigned | 0055 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - MIWUK 1702 - H03-LR9270 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5541308 | ECOP - MORAGA 1105 - H01-CB | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 07/20/2020 | # | Not assigned | 0055 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - MORAGA 1105 - H01-CB | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5541309 | ECOP - SILVERADO 2102 - H01-LR58626 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 07/20/2020 | # | Not assigned | 0055 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - SILVERADO 2102 - H01-LR58626 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5541785 | MAT 08J – 2021 Planning | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 09/03/2020 | # | Not assigned | 0055 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
5541918 | Contract Estimating 08W Planning | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5786123 | 08W Rebuild | 0.000 | 0.000 | 08W | 09/16/2020 | # | Not assigned | 0055 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5542041 | 08J - Base | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5517127 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 09/16/2020 | # | Not assigned | 0055 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | GRC Electric Dist | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
5542446 | ECOP-STANISLAUS 1702-H03-LR1850 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 10/23/2020 | # | Not assigned | 0055 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5542447 | ECOP-STANISLAUS 1702-H03-LR1850 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 10/23/2020 | # | Not assigned | 0055 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5734558 | 08-Guadalupe Reliability | # | # | Not assigned | 40 | Closed | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5517127 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 03/16/2009 | 05/01/2019 | Not assigned | 0057 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | GRC Electric Dist | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
5743253 | Econ Stim - NB-OH Annealed/Det Cndctr | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 05/03/2011 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CALISTOGA 1101 HIGH SPLICE COUNT | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5743254 | Econ Stim - FR-OH Annealed/Det Cndctr | # | # | Not assigned | 40 | Closed | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5517127 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 05/03/2011 | 05/01/2019 | Not assigned | 0057 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | GRC Electric Dist | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
5743257 | Econ Stim - HB-OH Annealed/Det Cndctr | # | # | Not assigned | 40 | Closed | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5517127 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 05/03/2011 | 05/01/2019 | Not assigned | 0057 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | GRC Electric Dist | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
5743278 | Econ Stim - SI-OH Annealed/Det Cndctr | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5517127 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 05/03/2011 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | GRC Electric Dist | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
5748179 | 08J-HB-Philo1102-Hwy128&GrnwdRd | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5517127 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 04/09/2012 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
5753403 | Middle River 1101 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 06/26/2013 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
5753443 | Middle River 1103 Phase 1 | # | # | Not assigned | 40 | Closed | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5517127 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 06/26/2013 | 05/01/2019 | Not assigned | 0057 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | GRC Distribution Common | GRC | CUSTCARE | Electric Distribution | Electric Distribution | 0
5753444 | Middle River 1103 Phase 2 | # | # | Not assigned | 40 | Closed | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5753444 | Middle River 1103 Phase 2 | 0.000 | 0.000 | 08J | 06/26/2013 | 07/16/2013 | Not assigned | 0057 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | GRC Distribution Common | GRC | CUSTCARE | Not assigned | Not assigned | 0
5756611 | 2014 Expense Reduction | # | # | Not assigned | 40 | Closed | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5517127 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 01/16/2014 | 05/01/2019 | Not assigned | 0057 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | GRC Distribution Common | GRC | CUSTCARE | Electric Distribution | Electric Distribution | 0
5756612 | 2014 Expense Reduction | # | # | Not assigned | 40 | Closed | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 01/16/2014 | 05/01/2019 | Not assigned | 0057 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | GRC Electric Dist | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
5760343 | Mormon 1102 Reconductoring | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5517127 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 09/10/2014 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
5770432 | Dist. Wrk Smartville-Nicolaus#2 60K P#3 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5517127 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 05/18/2016 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
5770433 | Dist. Wrk Smartville-Nicolaus#2 60K P#2 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5517127 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 05/18/2016 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
5775246 | Reconductor Echo Summit 1101 11600 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 04/26/2017 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Reconductor Echo Summit 1101 11,600' | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5777180 | Reinforce Cressey 2104 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5517127 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 08/29/2017 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | CRESSEY 2104 RECONDUCTOR PROJECT | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
5777380 | 08 - Rpl Deter Condctr and Alt fd analys | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 09/11/2017 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Repl OH Cond/ Alternate Backtie CE2104 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5777898 | 08 - Rpl OH Wire on OTTER-1101 S030CC121 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 10/12/2017 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-COLUMBIA HILL 1101-LR 2212 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5780557 | Kingsburg 1111 recond 21,880 ft #6CU | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 03/29/2018 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Kingsburg 1111 Recond 21,880' of #6CU Wi | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
5780841 | Reconductoring Los Gatos Part 2 of 3 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 04/17/2018 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Los Gatos 1106 - LB44 - Ph 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5780842 | Reconductoring Los Gatos Part 3 of 3 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 04/17/2018 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Los Gatos 1106 - LB44 - Ph 3.1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5782239 | CWSP: Angwin Steel Pole & TW Demo - PH2 | # | # | Not assigned | 40 | Closed | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 08/20/2018 | 05/01/2019 | Not assigned | 0057 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | GRC Electric Dist | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
5782526 | 2019 OH COND RPLC: EEL RIVER 1102 FU1913 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 09/19/2018 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | 2019 OH COND RPLC: EEL RIVER 1102 FU1913 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5782527 | CWSP - Apple Hill 2102 - LR 7502 - Ph1 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 09/19/2018 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Apple Hill 2102 - LR 7502 - Ph1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5782528 | CWSP - Apple Hill 2102 - LR 7502 - Ph2 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 09/19/2018 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Apple Hill 2102 - LR 7502 - Ph2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5782529 | CWSP - Apple Hill 2102 - LR 7502 - Ph3 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 09/19/2018 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Apple Hill 2102 - LR 7502 - Ph3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5782530 | CWSP - BIG BASIN 1101 - 10296 ZONE PH1 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 09/19/2018 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BIG BASIN 1101 - LR 10296 - PH1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5782531 | CWSP - Big Trees 0402 - CB Zone - Ph6 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 09/19/2018 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Big Trees 0402 - CB Zone - 4kV cu | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5782532 | CWSP - El Dorado 2101 - LR 19752 - Ph1 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 09/19/2018 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - El Dorado 2101 - 19752 - Ph 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5782533 | CWSP - El Dorado 2101 - LR 19752 - Ph2 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 09/19/2018 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - El Dorado 2101 - LR 19752 - Ph2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5782534 | CWSP - El Dorado 2101 - LR 19752 - Ph3 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 09/19/2018 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - El Dorado 2101 - LR 19752 - Ph3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5782535 | CWSP - El Dorado 2101 - LR 19752 - Ph4 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 09/19/2018 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - El Dorado 2101 - LR 19752 - Ph4 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5782536 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 09/19/2018 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | PH 1:REPL 14,000' OF 4AR IN TIER 3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5782537 | CWSP - Miwuk 1701 - OCB Zone - Phase 2 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 09/19/2018 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Miwuk 1701 - OCB Zone - Phase 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5782578 | CWSP - MORAGA 1101 (VARIOUS) - OCB | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 09/19/2018 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Deleted/Cancelled projects | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5782579 | CWSP - OAK K 1102 OCB LVL 1 HARDENING | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 09/19/2018 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | 74021963_CWSP OAKLAND K 1102 OCB | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5782580 | CWSP - Placerville 2106 - LR 1104 - Ph 1 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 09/19/2018 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Placerville 2106 - LR 1104 - Ph 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5782581 | CWSP - Placerville 2106 - LR 1104 - Ph 2 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 09/19/2018 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Placerville 2106 - LR 1104 - Phas | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5782582 | CWSP - Placerville 2106 - LR 1104 - Ph3 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 09/19/2018 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-PLACERVILLE 2106 LR1104 PH 3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5782583 | CWSP - Placerville 2106 - LR 1104 - Ph4 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 09/19/2018 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-PLACERVILLE 2106 LR1104 PH 4 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5782584 | CWSP - Placerville 2106 - LR 1104 - Ph5 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 09/19/2018 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-PLACERVILLE 2106 LR1104 PH 5 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5782585 | CWSP - Placerville 2106 - LR 1104 - Ph6 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 09/19/2018 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-PLACERVILLE 2106 LR1104 PH 6 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5782586 | CWSP - TASSAJARA 2112 - FUSE 18053 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 09/19/2018 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - TASSAJARA 2112 - FUSE 18053 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5782587 | CWSP - VOLTA 1102 - LR 1648 -PHASE 4 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 09/19/2018 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - VOLTA 1102 - LR 1648 -PHASE 4 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5782588 | CWSP - El Dorado 2101 - OCBZone - Ph 1.1 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 09/19/2018 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5782589 | CWSP- EL DORADO 2101 OCB ZONE PHASE 2 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 09/19/2018 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP- EL DORADO 2101 OCB ZONE PHASE 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5782590 | CWSP - Pine Grove 1102 LR9145 Ph 1.1 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 09/19/2018 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | 35043291_CWSP - PINE GROVE 1102-LR 9145 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5782591 | CWSP-EL DORADO 2101 - LR 26000 - PH3 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 09/19/2018 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-EL DORADO 2101 - LR 26000 - PH3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5782592 | CWSP-FOREST HILL 1101 - LR 50486 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 09/19/2018 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-FOREST HILL 1101 - LR 50486 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5782593 | CWSP-FOREST HILL 1101 - LR 50486 | # | # | Not assigned | 40 | Closed | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 09/19/2018 | 09/19/2018 | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Base Capital | GRC Electric Dist | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
5782594 | RPL OH WIRE ON OTTER-1101 S030CC121 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 09/19/2018 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | RPL OH WIRE OTTER 1101 S030CC121 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5782595 | SILVERADO 2105 WIRE DOWN | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 09/19/2018 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | REPL 17,500' of 4ar & 4cu in Tier 3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5782596 | 2019 Calistoga 1101 High Splice Count | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 09/19/2018 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | 2019 CALISTOGA 1101 HIGH SPLICE COUNT | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5782597 | Calistoga 1101 High Splice Count | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 09/19/2018 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | RECONd 15,298 FT 6CU, 4CU & 4AR W 2CU | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5782598 | CWSP: Monte Rio 1113 Hendrix Demo | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 09/19/2018 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP: MIRABEL 1102 / MONTE RIO 1113 LR 6 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5782600 | CWSP: Garberville 1101 Hendrix Demo | # | # | Not assigned | 40 | Closed | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 09/19/2018 | 05/01/2019 | Not assigned | 0057 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | GRC Electric Dist | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
5782601 | LP Cabrillo 1104 S006CC102 | # | # | Not assigned | 40 | Closed | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5517127 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 09/19/2018 | 05/01/2019 | Not assigned | 0057 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | GRC Electric Dist | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
5782761 | CWSP - Monte Rio 1112-LR 120 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 10/05/2018 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-Monte Rio 1112-LR 120 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5782762 | CWSP - Monte Rio 1112-TS 15401 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 10/05/2018 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-Monte Rio 1112-TS 15401 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5782763 | RPL OH.Con.Spence 112318-0074972 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 10/05/2018 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | RPL OH.Con.Spence 112318-0074972 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
5782833 | CWSP - MIRABEL 02 /MONTE RIO 13 - LR 652 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 10/05/2018 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP: MIRABEL 1102 / MONTE RIO 1113 LR 6 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5782834 | CWSP-BRUNSWICK 1105 LR-32536 ZONE # PH 1 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 10/05/2018 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-BRUNSWICK 1105 LR-32536 ZONE # PH 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5782835 | CWSP - BRUNSWICK 1105 LR-1030 ZONE | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 10/05/2018 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-BRUNSWICK 1105 LR-1030 ZONE | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5782839 | CWSP - CAMP EVERS 2106 - 5020 - PHASE 2 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 10/08/2018 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Deleted/Cancelled projects | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5782840 | EL DORADO PH 2101 2600 PH 1 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 10/08/2018 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - EL DORADO PH 2101 LR 26000 PH 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5782841 | CWSP - COLUMBIA HILL 1101 - LR 2212 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 10/08/2018 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5782842 | CWSP-MIDDLETOWN 1101-TS 1079 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 10/08/2018 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP: MIDDLETOWN 1101 TS 1079 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5782843 | CWSP - LOS GATOS 1106 - LB44 - PHASE 4 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 10/08/2018 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Deleted/Cancelled projects | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5782858 | CWSP-SILVERADO 2104-LR 722 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 10/08/2018 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - NORTH BAY WILDFIRE HARDENING PROJ | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5782859 | CWSP-KONOCTI 1102-LR 532 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 10/08/2018 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-KONOCTI 1102-LR 532 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5782860 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 10/08/2018 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5782906 | CWSP - BRUNSWICK 1103 LR2200 HARDENING | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 10/18/2018 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BRUNSWICK 1103 LR2200 HARDENING | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5782907 | CWSP - PARADISE 1106 - OCB & LR 2234 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 10/18/2018 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - PARADISE 1106 - OCB & LR 2234 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5782908 | CWSP - VOLTA 1102 LR 1648 PH 2 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 10/18/2018 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Deleted/Cancelled projects | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5783059 | CWSP - Brunswick - 1106 - LR2104 Zone | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 10/29/2018 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Brunswick - 1106 - LR2104 Zone | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5783060 | CWSP - Brunswick 1105 LR2210 Zone-Ph1 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 10/29/2018 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Brunswick - 1105 - LR2210 Zone-Ph | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5783061 | CWSP - Brunswick 1105 LR2210 Zone-Ph2 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 10/29/2018 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Brunswick - 1105 - LR2210 Zone-Ph | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5783062 | CWSP - Brunswick 1105 LR2140 Zone-Ph3 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 10/29/2018 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Brunswick - 1105 - LR2140 Zone-Ph | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5783063 | CWSP - Brunswick 1105 LR2140 Zone-Ph2 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 10/29/2018 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Brunswick - 1105 - LR2140 Zone-Ph | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5783064 | CWSP - Brunswick 1105 LR2140 Zone-Ph1 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 10/29/2018 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Brunswick - 1105 - LR2140 Zone-Ph | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5783065 | Cabrillo 1104 Reconductoring | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 10/29/2018 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Cabrillo 1104 Reconductoring | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5783066 | X-1104 OH RECOND SKYLINE | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08W | 10/29/2018 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Base Capital | GRC Electric Dist | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
5783067 | CWSP - Shingle Springs 2109 LR9372 Ph1 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 10/31/2018 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Shingle Springs 2109 LR 9372 Ph1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5783068 | CWSP - Shingle Springs 2109 LR9372 Ph2 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 10/31/2018 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Shingle Springs 2109 LR 9372 Ph2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5783069 | CWSP - Shingle Springs 2109 LR9372 Ph3 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 10/31/2018 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Shingle Springs 2109 LR 9372 Ph3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5783070 | CWSP-Brunswick 1103 LR50070 ZONE-PH 1.1 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 10/31/2018 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Brunswick 1103 LR50070 Zone-Ph1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5783071 | CWSP-Brunswick 1103 LR50070 ZONE-PH 2.1 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 10/31/2018 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Brunswick 1103 LR50070 Zone-Ph2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5783072 | CWSP-Brunswick 1103 LR50070 ZONE-PH 3.1 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 10/31/2018 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Brunswick 1103 LR50070 Zone-Ph3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5783177 | CWSP - El Dorado PH 2101 Zone 19612 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 11/02/2018 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - El Dorado PH 2101 Zone 19612 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5783198 | CWSP - El Dorado PH 2102 Zone 19542 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 11/02/2018 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - El Dorado PH 2102 Zone 19542 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5783199 | CWSP - El Dorado PH 2102 Zone 6645 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 11/02/2018 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - El Dorado PH 2102 Zone 6645 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5783222 | FRMMA - 08W - WILDFIRE RESILIENCY - CC | # | # | Not assigned | 40 | Closed | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 11/14/2018 | 07/01/2019 | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5783235 | FRMMA - 08W Reconductoring Los Gatos P 2 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 11/14/2018 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5783236 | FRMMA - 08W Reconductoring Los Gatos P 3 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 11/14/2018 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5783248 | FRMMA - 08W Reconductor Echo Summit 1101 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 11/19/2018 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5783283 | Paradise 1105 Rebuild Bille Rd | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 11/13/2018 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Paradise 1105 Rebuild Bille Rd | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5783284 | Paradise 1105 Rebuild Pentz Rd | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 11/13/2018 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Paradise 1105 Rebuild Pentz Rd | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5783285 | Paradise 1105 Rebuild Qual Rd | # | # | Not assigned | 40 | Closed | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 11/13/2018 | 05/01/2019 | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Paradise 1105 Rebuild Qual Rd | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5783286 | Paradise 1106 Rebuild Bike Path | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 11/13/2018 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Paradise 1106 Rebuild Bike Path | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5783287 | Paradise 1106 Rebuild South Park Dr | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 11/13/2018 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Paradise 1106 Rebuild South Park Dr | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5783288 | Paradise 1104 Rebuild Pearson Rd | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 11/13/2018 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Paradise 1104 Rebuild Pearson Rd | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5783289 | FOOTHILL 1101 LS CO9973 REPL OH LINE | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 11/13/2018 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | FOOTHILL 1101 LS CO9973 REPL OH LINE | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5783290 | RPL OH WIRE ON GABILAN 1101 17-0077248 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 11/13/2018 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | RPL OH WIRE ON GABILAN 1101 17-0077248 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5783317 | 08 - Rpl OH Wire on OTTER-1101 (PLAN) | # | # | Not assigned | 40 | Closed | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 11/13/2018 | 05/01/2019 | Not assigned | 0057 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | GRC Electric Dist | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
5783318 | Reconductoring Los Gatos Part 2 of 3 (PL | # | # | Not assigned | 40 | Closed | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 11/13/2018 | 05/01/2019 | Not assigned | 0057 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | GRC Electric Dist | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
5783319 | Reconductoring Los Gatos Part 3 of 3 (PL | # | # | Not assigned | 40 | Closed | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 11/13/2018 | 05/01/2019 | Not assigned | 0057 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | GRC Electric Dist | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
5783320 | CWSP - TASSAJARA 2112 - FUSE 18053 (PLAN | # | # | Not assigned | 40 | Closed | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 11/13/2018 | 05/01/2019 | Not assigned | 0057 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | GRC Electric Dist | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
5783322 | Camp Fire Reconductor Line Depot Rd | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 11/14/2018 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Camp Fire Reconductor Line Depot Rd | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5783323 | Camp Fire Reconductor Line Cypress Rd | # | # | Not assigned | 40 | Closed | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 11/14/2018 | 05/01/2019 | Not assigned | 0057 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | GRC Electric Dist | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
5783324 | Camp Fire Recond Line Honey Rn Butte 05 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 11/14/2018 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Camp Fire Recond Line Honey Rn Butte 05 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5783338 | FRMMA - 08W CWSP - TASSAJARA 2112 - FUSE | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 11/14/2018 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5783905 | CWSP - MIWUK 1701-LR 10600 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 01/22/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - MIWUK 1701 - LR 10600 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5783906 | CWSP-SALT SPRINGS 2102-LR3142 ZONE-PH 2 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 01/22/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-SALT SPRINGS 2102-LR3142 ZONE-PH 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5783907 | CWSP-SALT SPRINGS 2102-LR3142&L491-PH 1 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 01/22/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-SALT SPRINGS 2102-LR3142&L491-PHA 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5784105 | DIAMOND SPRINGS 1105 18-0105867 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5784105 | DIAMOND SPRINGS 1105 18-0105867 | 0.000 | 0.000 | 08W | 02/07/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | DIAMOND SPRINGS 1105 18-0105867 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5784143 | Recond GV 2101 Fuse 12347 zone | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 02/07/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Recond GV 2101 Fuse 12347 zone | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5784376 | RECONDUCTOR 17547FT 4ACSR W 2CU treewire | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 03/01/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | RECONDUCTOR 17547FT 4ACSR W 2CU treewire | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5784645 | CWSP - MIWUK 1701 LR11800 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 03/20/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-MIWUK 1701 LR11800 & 79118 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5784646 | CWSP - MIWUK 1701_OCB - PH 1 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 03/20/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - MIWUK 1701_OCB WILDFIRE HARDENING | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5784647 | CWSP - WEST POINT 1101 - OCB & LR 12256 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 03/20/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - WEST POINT 1101 - LR 12256 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5784648 | CWSP - Martell 1101 Reconductor 8,034ft | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 03/20/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Martell 1101 Reconductor 8,034ft | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5784860 | CWSP Silverado 2104 1B: Underground | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5784860 | CWSP Silverado 2104 1B: Underground | 0.000 | 0.000 | 08W | 04/09/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - NORTH BAY WILDFIRE HARDENING PROJ | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5784861 | CWSP Silverado 2104 1C:Harden OH InPlace | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5786200 | CWSP - Silverado 2104 - Ph 2 | 0.000 | 0.000 | 08W | 04/09/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - NORTH BAY WILDFIRE HARDENING PROJ | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5784862 | CWSP Silverado 2104 1D: Underground | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 04/09/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - NORTH BAY WILDFIRE HARDENING PROJ | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5784863 | CWSP Silverado 2104 1E:Harden OH InPlace | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 04/09/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - NORTH BAY WILDFIRE HARDENING PROJ | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5784864 | CWSP Silverado 2104 1F:Harden OH InPlace | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 04/09/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - NORTH BAY WILDFIRE HARDENING PROJ | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5784865 | CWSP Silverado 2104 1G: Underground | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 04/09/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - NORTH BAY WILDFIRE HARDENING PROJ | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5784866 | CWSP Silverado 2104 1H: Underground | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 04/09/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - NORTH BAY WILDFIRE HARDENING PROJ | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5784867 | SILVERADO 2105 WIRE DOWN PH 1 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 04/09/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | REPL 17,500' of 4ar & 4cu in Tier 3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5784868 | SILVERADO 2105 WIRE DOWN PH 2 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 04/09/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | REPL 17,500' of 4ar & 4cu in Tier 3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5784869 | SILVERADO 2105 WIRE DOWN PH 3 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 04/09/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | REPL 17,500' of 4ar & 4cu in Tier 3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5784870 | SILVERADO 2105 WIRE DOWN PH 4 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 04/09/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | REPL 17,500' of 4ar & 4cu in Tier 3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785039 | RECOND GREEN VALLEY 2103_REF#S032CC202 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5517128 | DO 49 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 04/19/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | RECOND GREEN VALLEY 2103 REF# S032CC202 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
5785078 | RECOND GREEN VALLEY 2103_REF#S029CC120 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5517128 | DO 49 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 04/22/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | RECOND GREEN VALLEY 2103 REF# S029CC120 | Base Capital | GRC Distribution Common | GRC | CUSTCARE | Electric Distribution | Electric Distribution | 0
5785158 | CWSP Konocti-1102 Phase 1 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 04/29/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-KONOCTI 1102-LR 532 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785159 | CWSP Konocti-1102 Phase 2 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 04/29/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-KONOCTI 1102-LR 532 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785160 | CWSP Konocti-1102 Phase 3 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 04/29/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-KONOCTI 1102-LR 532 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785161 | CWSP Konocti-1102 Phase 4 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 04/29/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-KONOCTI 1102-LR 532 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785162 | CWSP Konocti-1102 Phase 5 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 04/29/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-KONOCTI 1102-LR 532 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785163 | CWSP Konocti-1102 Phase 6 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 04/29/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-KONOCTI 1102-LR 532 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785164 | CWSP Konocti-1102 Phase 7 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 04/29/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-KONOCTI 1102-LR 532 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785165 | CWSP Konocti-1102 Phase 8 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 04/29/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-KONOCTI 1102-LR 532 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785166 | CWSP Konocti-1102 Phase 9 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 04/29/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-KONOCTI 1102-LR 532 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785167 | CWSP Konocti-1102 Phase 10 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 04/29/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-KONOCTI 1102-LR 532 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785218 | CWSP - El Dorado 2102 - LR19562 - Ph 1.0 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 05/01/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - EL DORADO PH 2102 - LR 19562 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785219 | CWSP - MIWUK 1702-LR 38218 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 05/01/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - MIWUK 1702_LR38218 WILDFIRE HARDE | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785220 | CWSP - MIWUK 1702-LR 6018-PHASE 1 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 05/01/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785221 | CWSP - MIWUK 1702-LR 8090 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 05/01/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-MIWUK 1702-LR 8090 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785222 | CWSP - MIWUK 1702-OCB | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 05/01/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - MIWUK 1702_OCB WILDFIRE HARDENING | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785223 | CWSP - Oro Fino 1102 LR 2560 Ph 1 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 05/01/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-ORO FINO 1102 LR-2560 PH 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785224 | CWSP - Oro Fino 1102 LR 2560 Ph 2 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 05/01/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-ORO FINO 1102 LR-2560 PH 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785225 | CWSP - Oro Fino 1102 LR 76008 Ph 1 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 05/01/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-ORO FINO 1102 LR-76008 PH 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785226 | CWSP - Oro Fino 1102 LR 76008 Ph 2 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 05/01/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-ORO FINO 1102 LR-76008 PH 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785227 | CWSP - Pine Grove 1102 LR1222 Phase 2 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 05/01/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP: PINE GROVE 1102 LR1222 ZONE WFH PH | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785228 | CWSP - Volta 1102 LR 1648 Ph 3 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 05/01/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - VOLTA 1102 - LR 1648 -PHASE 3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785229 | CWSP - WEST POINT 1101-LR 13444-PHASE 1 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 05/01/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-WEST POINT 1101-LR 13444-PHASE 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785230 | CWSP - WEST POINT 1101-LR 13444-PHASE 2 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 05/01/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-WEST POINT 1101-LR 13444-PHASE 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785238 | CWSP MIIWUK 1701 LR 8060 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 05/01/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | MIWUK 1701 LR8060 08W WILDFIRE HARDENING | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785239 | CWSP-ORO FINO 1101 LR-2022 PH 3 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 05/01/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-ORO FINO 1101 LR-2022 PH 3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785240 | CWSP-ORO FINO 1101 OCB PH 3 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 05/01/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-ORO FINO 1101 OCB PH 3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785241 | CWSP-ORO FINO 1101 OCB PH 2 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 05/01/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-ORO FINO 1101 OCB PH 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785242 | CWSP-ORO FINO 1101 OCB PH 1 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 05/01/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-ORO FINO 1101 OCB PH 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785243 | CWSP-ORO FINO 1101-LR 2022 PH 2 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 05/01/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - ORO FINO-1101 LR-2022 PH 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785244 | CWSP-ORO FINO 1101 LR-2022 PH 1 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 05/01/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - ORO FINO-1101 LR-2022 PH I | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785245 | CWSP - STANISLAUS 1702 LR1804 & 4905 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 05/01/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | STANISLAUS 1702 LR1804 ZONE WFH LEVEL 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785246 | CWSP-STANISLAUS1702-LR1888-PH2 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 05/01/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-STANISLAUS1702-LR1888-PH2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785247 | CWSP-STANISLAUS1702-LR1888-PH1 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 05/01/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-STANISLAUS1702-LR1888-PH1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785301 | CWSP-COLUMBIA HILL 1101-LR 2212 Ph 2 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 05/07/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-COLUMBIA HILL 1101-LR 2212 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785302 | CWSP-COLUMBIA HILL 1101-LR 2212 Ph 3 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 05/07/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-COLUMBIA HILL 1101-LR 2212 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785303 | CWSP-COLUMBIA HILL 1101-LR 2212 Ph 4 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 05/07/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-COLUMBIA HILL 1101-LR 2212 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785304 | CWSP-COLUMBIA HILL 1101-LR 2212 Ph 5 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 05/07/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-COLUMBIA HILL 1101-LR 2212 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785380 | CWSP – Moraga 1102 and 1104 OCB | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 05/14/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - MORAGA 1101 (VARIOUS) - OCB | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785418 | CWSP - Diablo Rossmoor 1102 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 05/14/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - MORAGA 1101 (VARIOUS) - OCB | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785419 | CWSP - Diablo Moraga 1102 1104 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 05/14/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - MORAGA 1101 (VARIOUS) - OCB | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785512 | CWSP - El Dorado 2101 - 19752 - Ph 1.2 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 05/24/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - El Dorado 2101 - 19752 - Ph 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785513 | CWSP - El Dorado 2101 - 19752 - Ph 1.3 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 05/24/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - El Dorado 2101 - 19752 - Ph 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785514 | CWSP - El Dorado 2101 - 19752 - Ph 1.4 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 05/24/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - El Dorado 2101 - 19752 - Ph 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785515 | CWSP - El Dorado 2101 - 19752 - Ph 1.5 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 05/24/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - El Dorado 2101 - 19752 - Ph 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785516 | CWSP - El Dorado 2101 - 19752 - Ph 2.2 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 05/24/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - El Dorado 2101 - LR 19752 - Ph2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785517 | CWSP - El Dorado 2101 - 19752 - Ph 2.3 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 05/24/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - El Dorado 2101 - LR 19752 - Ph2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785578 | CWSP - Volta 1102 - LR 1648 - Ph1.1 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 05/23/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Volta 1102 - LR 1648 - Ph1.1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785579 | CWSP - Volta 1102 - LR 1648 - Ph1.2 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 05/23/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Volta 1102 - LR 1648 - Ph1.1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785580 | CWSP - Volta 1102 - LR 1648 - Ph1.3 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 05/23/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Volta 1102 - LR 1648 - Ph1.1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785581 | CWSP - Volta 1102 - LR 1648 - Ph1.4 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 05/23/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Volta 1102 - LR 1648 - Ph1.1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785598 | CWSP - El Dorado 2101 - 19752 - Ph 2.4 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 05/24/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - El Dorado 2101 - LR 19752 - Ph2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785599 | CWSP - El Dorado 2101 - 19752 - Ph 2.5 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 05/24/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - El Dorado 2101 - LR 19752 - Ph2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785600 | CWSP - El Dorado 2101 - 19752 - Ph 3.2 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 05/24/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - El Dorado 2101 - LR 19752 - Ph3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785601 | CWSP - El Dorado 2101 - 19752 - Ph 3.3 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 05/24/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - El Dorado 2101 - LR 19752 - Ph3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785602 | CWSP - El Dorado 2101 - 19752 - Ph 3.4 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 05/24/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - El Dorado 2101 - LR 19752 - Ph3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785603 | CWSP - El Dorado 2101 - 19752 - Ph 3.5 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 05/24/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - El Dorado 2101 - LR 19752 - Ph3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785604 | CWSP - El Dorado 2101 - 19752 - Ph 3.6 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 05/24/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - El Dorado 2101 - LR 19752 - Ph3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785605 | CWSP - El Dorado 2101 - 19752 - Ph. 4.2 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 05/24/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - El Dorado 2101 - LR 19752 - Ph4 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785606 | CWSP - El Dorado 2101 - 19752 - Ph. 4.3 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 05/24/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - El Dorado 2101 - LR 19752 - Ph4 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785607 | CWSP - El Dorado 2101 - 19752 - Ph. 4.4 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 05/24/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - El Dorado 2101 - LR 19752 - Ph4 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785608 | CWSP - Volta 1102 - LR 1648 - Ph 2.2 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 05/24/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - VOLTA 1102 LR 1648 PH 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785609 | CWSP - Volta 1102 - LR 1648 - Ph 2.3 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 05/24/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - VOLTA 1102 LR 1648 PH 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785610 | CWSP - Volta 1102 - LR 1648 - Ph 2.4 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 05/24/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - VOLTA 1102 LR 1648 PH 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785611 | CWSP - Volta 1102 - LR 1648 - Ph 2.5 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 05/24/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - VOLTA 1102 LR 1648 PH 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785612 | CWSP - Volta 1102 - LR 1648 - Ph 2.6 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 05/24/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - VOLTA 1102 LR 1648 PH 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785613 | CWSP - Volta 1102 - LR 1648 - Ph 3.2 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 05/24/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - VOLTA 1102 - LR 1648 -PHASE 3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785614 | CWSP - Volta 1102 - LR 1648 - Ph 3.3 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 05/24/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - VOLTA 1102 - LR 1648 -PHASE 3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785615 | CWSP - Volta 1102 - LR 1648 - Ph 3.4 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 05/24/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - VOLTA 1102 - LR 1648 -PHASE 3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785616 | CWSP - Volta 1102 - LR 1648 - Ph 4.2 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 05/24/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - VOLTA 1102 - LR 1648 -PHASE 4 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785617 | CWSP - Volta 1102 - LR 1648 - Ph 4.3 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 05/24/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - VOLTA 1102 - LR 1648 -PHASE 4 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785618 | CWSP - Volta 1102 - LR 1648 - Ph 4.4 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 05/24/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - VOLTA 1102 - LR 1648 -PHASE 4 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785619 | CWSP - Volta 1102 - LR 1648 - Ph 4.5 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 05/24/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - VOLTA 1102 - LR 1648 -PHASE 4 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785645 | CWSP - El Dorado 2102 - LR19562 - Ph 1.1 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 05/30/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - EL DORADO PH 2102 - LR 19562 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785646 | CWSP - El Dorado 2102 - LR19562 - Ph 1.2 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 05/30/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - EL DORADO PH 2102 - LR 19562 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785647 | CWSP - El Dorado 2102 - LR19562 - Ph 1.3 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 05/30/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - EL DORADO PH 2102 - LR 19562 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785648 | CWSP - El Dorado 2102 - LR19562 - Ph 1.4 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 05/30/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - EL DORADO PH 2102 - LR 19562 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785649 | CWSP - El Dorado 2102 - LR19562 - Ph 1.5 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 05/30/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - EL DORADO PH 2102 - LR 19562 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785650 | CWSP - El Dorado 2102 - LR19562 - Ph 1.6 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 05/30/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - EL DORADO PH 2102 - LR 19562 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785651 | CWSP - El Dorado 2102 - LR19562 - Ph 1.7 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 05/30/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - EL DORADO PH 2102 - LR 19562 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785652 | CWSP - El Dorado 2101 - OCBZone - Ph 1.2 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 05/30/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785653 | CWSP - El Dorado 2101 - OCBZone - Ph 1.3 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 05/30/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785654 | CWSP - El Dorado 2101 - OCBZone - Ph 1.4 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 05/30/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785655 | CWSP - El Dorado 2101 - OCBZone - Ph 1.5 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 05/30/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785656 | CWSP - El Dorado 2101 - OCBZone - Ph 1.6 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 05/30/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785657 | CWSP-Brunswick 1103 LR50070 ZONE-PH 1.2 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 05/30/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Brunswick 1103 LR50070 Zone-Ph1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785658 | CWSP - Pine Grove 1102 LR9145 Ph 1.2 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 05/28/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785659 | CWSP - Pine Grove 1102 - LR 1222 Ph 1 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 05/29/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP: PINE GROVE 1102 LR1222 PH 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785718 | CWSP-Brunswick 1103 LR50070 ZONE-PH 1.3 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 05/30/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Brunswick 1103 LR50070 Zone-Ph1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785719 | CWSP-Brunswick 1103 LR50070 ZONE-PH 1.4 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 05/30/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Brunswick 1103 LR50070 Zone-Ph1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785720 | CWSP-Brunswick 1103 LR50070 ZONE-PH 1.5 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 05/30/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Brunswick 1103 LR50070 Zone-Ph1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785721 | CWSP-Brunswick 1103 LR50070 ZONE-PH 2.2 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 05/30/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Brunswick 1103 LR50070 Zone-Ph2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785722 | CWSP-Brunswick 1103 LR50070 ZONE-PH 2.3 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 05/30/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Brunswick 1103 LR50070 Zone-Ph2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785723 | CWSP-Brunswick 1103 LR50070 ZONE-PH 2.4 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 05/30/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Brunswick 1103 LR50070 Zone-Ph2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785724 | CWSP-Brunswick 1103 LR50070 ZONE-PH 2.5 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 05/30/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Brunswick 1103 LR50070 Zone-Ph2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785725 | CWSP-Brunswick 1103 LR50070 ZONE-PH 3.2 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 05/30/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Brunswick 1103 LR50070 Zone-Ph3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785726 | CWSP-Brunswick 1103 LR50070 ZONE-PH 3.3 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 05/30/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Brunswick 1103 LR50070 Zone-Ph3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785727 | CWSP-Brunswick 1103 LR50070 ZONE-PH 3.4 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 05/30/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Brunswick 1103 LR50070 Zone-Ph3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785728 | CWSP-Brunswick 1103 LR50070 ZONE-PH 3.5 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 05/30/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Brunswick 1103 LR50070 Zone-Ph3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785929 | CWSP - MIWUK 1702 - LR 8090 - PH 1.2 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 06/19/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-MIWUK 1702-LR 8090 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785930 | CWSP - MIWUK 1702 - LR 8090 - PH 1.3 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 06/19/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-MIWUK 1702-LR 8090 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785931 | CWSP - MIWUK 1702 - LR 8090 - PH 1.4 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 06/19/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-MIWUK 1702-LR 8090 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785932 | CWSP - MIWUK 1702 - LR 8090 - PH 1.5 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5785932 | CWSP - MIWUK 1702 - LR 8090 - PH 1.5 | 0.000 | 0.000 | 08W | 06/19/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-MIWUK 1702-LR 8090 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785933 | CWSP - MIWUK 1702 - LR 8090 - PH 1.6 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 06/19/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-MIWUK 1702-LR 8090 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785934 | CWSP - MIWUK 1702 - LR 8090 - PH 1.7 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5785934 | CWSP - MIWUK 1702 - LR 8090 - PH 1.7 | 0.000 | 0.000 | 08W | 06/19/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785935 | CWSP - MIWUK 1701 - LR 10600 PH 1.2 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 06/19/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - MIWUK 1701 - LR 10600 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785936 | CWSP - MIWUK 1701 - LR 10600 PH 1.3 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 06/19/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - MIWUK 1701 - LR 10600 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785937 | CWSP - MIWUK 1701 - LR 10600 PH 1.4 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 06/19/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - MIWUK 1701 - LR 10600 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785958 | CWSP - MIWUK 1701 - LR 10600 PH 1.5 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 06/19/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - MIWUK 1701 - LR 10600 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785959 | CWSP - MIWUK 1701 - LR 10600 PH 1.6 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5785959 | CWSP - MIWUK 1701 - LR 10600 PH 1.6 | 0.000 | 0.000 | 08W | 06/19/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785960 | CWSP - MIWUK 1701 - LR 10600 PH 1.7 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5785960 | CWSP - MIWUK 1701 - LR 10600 PH 1.7 | 0.000 | 0.000 | 08W | 06/19/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785961 | CWSP - MIWUK 1702 - LR 6018 - PH 1.2 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 06/19/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - MIWUK 1702-LR 6018-PHASE 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785962 | CWSP - MIWUK 1702 - LR 6018 - PH 1.3 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 06/19/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - MIWUK 1702-LR 6018-PHASE 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785963 | CWSP - MIWUK 1702 - LR 6018 - PH 1.4 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 06/19/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - MIWUK 1702-LR 6018-PHASE 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785964 | CWSP - MIWUK 1702 - LR 6018 - PH 1.5 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5785964 | CWSP - MIWUK 1702 - LR 6018 - PH 1.5 | 0.000 | 0.000 | 08W | 06/19/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - MIWUK 1702-LR 6018-PHASE 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785965 | CWSP - MIWUK 1702 - LR 6018 - PH 1.6 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 06/19/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - MIWUK 1702-LR 6018-PHASE 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785966 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 06/19/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | MIWUK 1701 LR8060 08W WILDFIRE HARDENING | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785967 | CWSP - MIWUK 1701 - LR 8060 - PH 1.3 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 06/19/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | MIWUK 1701 LR8060 08W WILDFIRE HARDENING | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785968 | CWSP - MIWUK 1701 - LR 8060 - PH 1.4 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 06/19/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | MIWUK 1701 LR8060 08W WILDFIRE HARDENING | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785969 | CWSP - MIWUK 1701 - LR 8060 - PH 1.5 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 06/19/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | MIWUK 1701 LR8060 08W WILDFIRE HARDENING | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785970 | CWSP - MIWUK 1701 - LR 8060 - PH 1.6 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 06/19/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | MIWUK 1701 LR8060 08W WILDFIRE HARDENING | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785971 | CWSP - MIWUK 1701 - LR 8060 - PH 1.7 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 06/19/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | MIWUK 1701 LR8060 08W WILDFIRE HARDENING | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785972 | CWSP - MIWUK 1701 – OCB - PH 1.2 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 06/19/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - MIWUK 1701_OCB WILDFIRE HARDENING | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785973 | CWSP - MIWUK 1701 – OCB - PH 1.3 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 06/19/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - MIWUK 1701_OCB WILDFIRE HARDENING | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785974 | CWSP - MIWUK 1701 – OCB - PH 1.4 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 06/19/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - MIWUK 1701_OCB WILDFIRE HARDENING | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785975 | CWSP - MIWUK 1701 – OCB - PH 1.5 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 06/19/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - MIWUK 1701_OCB WILDFIRE HARDENING | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785976 | CWSP - MIWUK 1702 - OCB - PH 1.2 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5785976 | CWSP - MIWUK 1702 - OCB - PH 1.2 | 0.000 | 0.000 | 08W | 06/19/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - MIWUK 1702_OCB WILDFIRE HARDENING | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785977 | CWSP - MIWUK 1702 - OCB - PH 1.3 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 06/19/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - MIWUK 1702_OCB WILDFIRE HARDENING | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785978 | CWSP - MIWUK 1702 - OCB - PH 1.4 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 06/19/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - MIWUK 1702_OCB WILDFIRE HARDENING | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785979 | CWSP - MIWUK 1702 - OCB - PH 1.5 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 06/19/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - MIWUK 1702_OCB WILDFIRE HARDENING | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785980 | CWSP - MIWUK 1702 - OCB - PH 1.6 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5785980 | CWSP - MIWUK 1702 - OCB - PH 1.6 | 0.000 | 0.000 | 08W | 06/19/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785981 | CWSP - MIWUK 1702 - LR 38218 - PH 1.2 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 06/19/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - MIWUK 1702_LR38218 WILDFIRE HARDE | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785982 | CWSP - MIWUK 1702 - LR 38218 - PH 1.3 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 06/19/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - MIWUK 1702_LR38218 WILDFIRE HARDE | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785983 | CWSP - MIWUK 1702 - LR 38218 - PH 1.4 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 06/19/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - MIWUK 1702_LR38218 WILDFIRE HARDE | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785984 | CWSP - MIWUK 1702 - LR 38218 - PH 1.5 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5785984 | CWSP - MIWUK 1702 - LR 38218 - PH 1.5 | 0.000 | 0.000 | 08W | 06/19/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - MIWUK 1702_LR38218 WILDFIRE HARDE | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785985 | CWSP - MIWUK 1702 - LR 38218 - PH 1.6 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5785985 | CWSP - MIWUK 1702 - LR 38218 - PH 1.6 | 0.000 | 0.000 | 08W | 06/19/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785986 | CWSP - MIWUK 1701 – OCB - PH 2.2 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 06/19/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Miwuk 1701 - OCB Zone - Phase 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785987 | CWSP - MIWUK 1701 – OCB - PH 2.3 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5785987 | CWSP - MIWUK 1701 – OCB - PH 2.3 | 0.000 | 0.000 | 08W | 06/19/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Miwuk 1701 - OCB Zone - Phase 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785988 | CWSP - MIWUK 1701 – OCB - PH 2.4 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 06/19/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Miwuk 1701 - OCB Zone - Phase 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785989 | CWSP - MIWUK 1701 – OCB - PH 2.5 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5785989 | CWSP - MIWUK 1701 – OCB - PH 2.5 | 0.000 | 0.000 | 08W | 06/19/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Miwuk 1701 - OCB Zone - Phase 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785990 | CWSP - MIWUK 1701 – OCB - PH 2.6 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5785990 | CWSP - MIWUK 1701 – OCB - PH 2.6 | 0.000 | 0.000 | 08W | 06/19/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785991 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5785991 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 | 0.000 | 0.000 | 08W | 06/19/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP: PINE GROVE 1102 LR1222 PH 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785992 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.3 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 06/19/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP: PINE GROVE 1102 LR1222 PH 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785993 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.4 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 06/19/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP: PINE GROVE 1102 LR1222 PH 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785994 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.5 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 06/19/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP: PINE GROVE 1102 LR1222 PH 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785995 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.6 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 06/19/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP: PINE GROVE 1102 LR1222 PH 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785996 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.2 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5785996 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.2 | 0.000 | 0.000 | 08W | 06/19/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP: PINE GROVE 1102 LR1222 ZONE WFH PH | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785997 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5785997 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 | 0.000 | 0.000 | 08W | 06/19/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP: PINE GROVE 1102 LR1222 ZONE WFH PH | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785998 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.4 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5785998 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.4 | 0.000 | 0.000 | 08W | 06/19/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP: PINE GROVE 1102 LR1222 ZONE WFH PH | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5785999 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.5 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5785999 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.5 | 0.000 | 0.000 | 08W | 06/19/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP: PINE GROVE 1102 LR1222 ZONE WFH PH | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786000 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.6 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5786000 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.6 | 0.000 | 0.000 | 08W | 06/19/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP: PINE GROVE 1102 LR1222 ZONE WFH PH | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786001 | CWSP - WEST POINT 1101 -LR 13444- PH 1.2 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 06/19/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-WEST POINT 1101-LR 13444-PHASE 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786002 | CWSP - WEST POINT 1101 -LR 13444- PH 1.3 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 06/19/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-WEST POINT 1101-LR 13444-PHASE 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786003 | CWSP - WEST POINT 1101 -LR 13444- PH 1.4 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 06/19/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-WEST POINT 1101-LR 13444-PHASE 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786004 | CWSP - WEST POINT 1101 -LR 13444- PH 1.5 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5786004 | CWSP - WEST POINT 1101 -LR 13444- PH 1.5 | 0.000 | 0.000 | 08W | 06/19/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-WEST POINT 1101-LR 13444-PHASE 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786005 | CWSP - WEST POINT 1101 -LR 13444- PH 1.6 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5786005 | CWSP - WEST POINT 1101 -LR 13444- PH 1.6 | 0.000 | 0.000 | 08W | 06/19/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-WEST POINT 1101-LR 13444-PHASE 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786006 | CWSP - WEST POINT 1101 -LR 13444- PH 1.7 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5786006 | CWSP - WEST POINT 1101 -LR 13444- PH 1.7 | 0.000 | 0.000 | 08W | 06/19/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-WEST POINT 1101-LR 13444-PHASE 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786007 | CWSP - WEST POINT 1101 -LR 13444- PH 2.2 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 06/19/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-WEST POINT 1101-LR 13444-PHASE 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786008 | CWSP - WEST POINT 1101 -LR 13444- PH 2.3 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 06/19/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-WEST POINT 1101-LR 13444-PHASE 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786009 | CWSP - WEST POINT 1101 -LR 13444- PH 2.4 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5786009 | CWSP - WEST POINT 1101 -LR 13444- PH 2.4 | 0.000 | 0.000 | 08W | 06/19/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-WEST POINT 1101-LR 13444-PHASE 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786010 | CWSP - WEST POINT 1101 -LR 13444- PH 2.5 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 06/19/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-WEST POINT 1101-LR 13444-PHASE 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786011 | CWSP - WEST POINT 1101 -LR 13444- PH 2.6 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 06/19/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-WEST POINT 1101-LR 13444-PHASE 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786012 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.2 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 06/19/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - WEST POINT 1101 - LR 12256 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786013 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.3 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 06/19/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - WEST POINT 1101 - LR 12256 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786014 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.4 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 06/19/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - WEST POINT 1101 - LR 12256 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786015 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.5 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5786015 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.5 | 0.000 | 0.000 | 08W | 06/19/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - WEST POINT 1101 - LR 12256 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786016 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.6 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5786016 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.6 | 0.000 | 0.000 | 08W | 06/19/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - WEST POINT 1101 - LR 12256 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786017 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.7 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5786017 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.7 | 0.000 | 0.000 | 08W | 06/19/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - WEST POINT 1101 - LR 12256 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786018 | CWSP-SALT SPRINGS 2102-LR3142ZONE-PH 2.2 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5786018 | CWSP-SALT SPRINGS 2102-LR3142ZONE-PH 2.2 | 0.000 | 0.000 | 08W | 06/19/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-SALT SPRINGS 2102-LR3142 ZONE-PH 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786019 | CWSP-SALT SPRINGS 2102-LR3142ZONE-PH 2.3 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5786019 | CWSP-SALT SPRINGS 2102-LR3142ZONE-PH 2.3 | 0.000 | 0.000 | 08W | 06/19/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-SALT SPRINGS 2102-LR3142 ZONE-PH 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786020 | CWSP-SALT SPRINGS 2102-LR3142ZONE-PH 2.4 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5786020 | CWSP-SALT SPRINGS 2102-LR3142ZONE-PH 2.4 | 0.000 | 0.000 | 08W | 06/19/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-SALT SPRINGS 2102-LR3142 ZONE-PH 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786021 | CWSP-SALT SPRINGS 2102-LR3142ZONE-PH 2.5 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5786021 | CWSP-SALT SPRINGS 2102-LR3142ZONE-PH 2.5 | 0.000 | 0.000 | 08W | 06/19/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-SALT SPRINGS 2102-LR3142 ZONE-PH 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786022 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.2 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 06/19/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-SALT SPRINGS 2102-LR3142&L491-PHA 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786023 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.3 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 06/19/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-SALT SPRINGS 2102-LR3142&L491-PHA 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786024 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.4 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 06/19/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-SALT SPRINGS 2102-LR3142&L491-PHA 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786025 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.5 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5786025 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.5 | 0.000 | 0.000 | 08W | 06/19/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-SALT SPRINGS 2102-LR3142&L491-PHA 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786026 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.6 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5786026 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.6 | 0.000 | 0.000 | 08W | 06/19/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-SALT SPRINGS 2102-LR3142&L491-PHA 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786027 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.7 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5786027 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.7 | 0.000 | 0.000 | 08W | 06/19/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-SALT SPRINGS 2102-LR3142&L491-PHA 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786028 | CWSP-SALT SPRINGS 2102-LR3142ZONE-PH 2.6 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 06/19/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-SALT SPRINGS 2102-LR3142 ZONE-PH 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786029 | CWSP-SALT SPRINGS 2102-LR3142ZONE-PH 2.7 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 06/19/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-SALT SPRINGS 2102-LR3142 ZONE-PH 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786030 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.2 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5786030 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.2 | 0.000 | 0.000 | 08W | 06/19/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | STANISLAUS 1702 LR1804 ZONE WFH LEVEL 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786031 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.3 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5786031 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.3 | 0.000 | 0.000 | 08W | 06/19/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | STANISLAUS 1702 LR1804 ZONE WFH LEVEL 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786032 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.4 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5786032 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.4 | 0.000 | 0.000 | 08W | 06/19/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | STANISLAUS 1702 LR1804 ZONE WFH LEVEL 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786033 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.5 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5786033 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.5 | 0.000 | 0.000 | 08W | 06/19/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | STANISLAUS 1702 LR1804 ZONE WFH LEVEL 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786034 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.6 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5786034 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.6 | 0.000 | 0.000 | 08W | 06/19/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | STANISLAUS 1702 LR1804 ZONE WFH LEVEL 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786035 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.7 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5786035 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.7 | 0.000 | 0.000 | 08W | 06/19/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | STANISLAUS 1702 LR1804 ZONE WFH LEVEL 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786036 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.2 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5786036 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.2 | 0.000 | 0.000 | 08W | 06/19/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-STANISLAUS1702-LR1888-PH1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786037 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.3 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5786037 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.3 | 0.000 | 0.000 | 08W | 06/19/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-STANISLAUS1702-LR1888-PH1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786038 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.4 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5786038 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.4 | 0.000 | 0.000 | 08W | 06/19/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-STANISLAUS1702-LR1888-PH1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786039 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.5 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5786039 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.5 | 0.000 | 0.000 | 08W | 06/19/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-STANISLAUS1702-LR1888-PH1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786040 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.6 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5786040 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.6 | 0.000 | 0.000 | 08W | 06/19/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-STANISLAUS1702-LR1888-PH1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786041 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.2 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 06/19/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-STANISLAUS1702-LR1888-PH2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786042 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.3 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 06/19/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-STANISLAUS1702-LR1888-PH2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786043 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.4 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5786043 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.4 | 0.000 | 0.000 | 08W | 06/19/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-STANISLAUS1702-LR1888-PH2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786044 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.5 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5786044 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.5 | 0.000 | 0.000 | 08W | 06/19/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-STANISLAUS1702-LR1888-PH2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786045 | CWSP - FULTON 1107 - MARK WEST SPR RD | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5786045 | CWSP - FULTON 1107 - MARK WEST SPR RD | 0.000 | 0.000 | 08W | 06/19/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - FULTON 1107 - MARK WEST SPR RD | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786049 | CWSP - Los Gatos 1106 - LB44 - Ph 1.2 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 06/20/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | PH 1:REPL 14,000' OF 4AR IN TIER 3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786050 | CWSP - Los Gatos 1106 - LB44 - Ph 1.3 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 06/20/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | PH 1:REPL 14,000' OF 4AR IN TIER 3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786051 | CWSP - Los Gatos 1106 - LB44 - Ph 1.4 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 06/20/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | PH 1:REPL 14,000' OF 4AR IN TIER 3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786052 | CWSP - Los Gatos 1106 - LB44 - Ph 2.2 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 06/20/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Los Gatos 1106 - LB44 - Ph 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786053 | CWSP - Los Gatos 1106 - LB44 - Ph 2.3 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 06/20/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Los Gatos 1106 - LB44 - Ph 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786054 | CWSP - Los Gatos 1106 - LB44 - Ph 2.4 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 06/20/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Los Gatos 1106 - LB44 - Ph 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786055 | CWSP - Los Gatos 1106 - LB44 - Ph 3.2 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 06/20/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Los Gatos 1106 - LB44 - Ph 3.1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786056 | CWSP - Los Gatos 1106 - LB44 - Ph 3.3 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 06/20/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Los Gatos 1106 - LB44 - Ph 3.1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786057 | CWSP - Los Gatos 1106 - LB44 - Ph 3.4 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 06/20/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Los Gatos 1106 - LB44 - Ph 3.1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786098 | CWSP-Woodside 1101-Fuse 1097 Tap Line | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 06/20/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-WOODSIDE 1101-FUSE1097 TAP LINE | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786121 | 08W Rebuild | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5786121 | 08W Rebuild | 0.000 | 0.000 | 08W | 06/25/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | GRC Electric Dist | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
5786123 | 08W Rebuild | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5786123 | 08W Rebuild | 0.000 | 0.000 | 08W | 06/25/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786124 | CWSP - BIG BASIN 1101 - LR 10296 - PH1.2 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 06/26/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BIG BASIN 1101 - LR 10296 - PH1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786125 | CWSP - BIG BASIN 1101 - LR 10296 - PH1.3 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 06/26/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BIG BASIN 1101 - LR 10296 - PH1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786126 | CWSP - BIG BASIN 1101 - LR 10296 - PH1.4 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5786126 | CWSP - BIG BASIN 1101 - LR 10296 - PH1.4 | 0.000 | 0.000 | 08W | 06/26/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BIG BASIN 1101 - LR 10296 - PH1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786127 | CWSP - BIG BASIN 1101 - LR 10296 - PH1.5 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5786127 | CWSP - BIG BASIN 1101 - LR 10296 - PH1.5 | 0.000 | 0.000 | 08W | 06/26/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BIG BASIN 1101 - LR 10296 - PH1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786129 | CWSP - BIG BASIN 1101 - LR 10296 - PH1.6 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5786129 | CWSP - BIG BASIN 1101 - LR 10296 - PH1.6 | 0.000 | 0.000 | 08W | 06/26/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BIG BASIN 1101 - LR 10296 - PH1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786130 | CWSP - BIG BASIN 1101 - LR 10296 - PH1.7 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5786130 | CWSP - BIG BASIN 1101 - LR 10296 - PH1.7 | 0.000 | 0.000 | 08W | 06/26/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BIG BASIN 1101 - LR 10296 - PH1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786131 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.2 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 06/26/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - CAMP EVERS 2106 - 5020 - PHASE 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786132 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.3 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 06/26/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - CAMP EVERS 2106 - 5020 - PHASE 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786133 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.4 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 06/26/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - CAMP EVERS 2106 - 5020 - PHASE 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786134 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.8 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5786134 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.8 | 0.000 | 0.000 | 08W | 06/26/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - WEST POINT 1101 - LR 12256 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786135 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.7 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 06/26/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP: PINE GROVE 1102 LR1222 PH 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786136 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.7 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5786136 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.7 | 0.000 | 0.000 | 08W | 06/26/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP: PINE GROVE 1102 LR1222 ZONE WFH PH | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786137 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.8 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5786137 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.8 | 0.000 | 0.000 | 08W | 06/26/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP: PINE GROVE 1102 LR1222 ZONE WFH PH | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786199 | CWSP - Silverado 2104 - Ph 1 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 07/02/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | SILVERADO 2104 RECONDUCTOR PROJECT | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786200 | CWSP - Silverado 2104 - Ph 2 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5786200 | CWSP - Silverado 2104 - Ph 2 | 0.000 | 0.000 | 08W | 07/02/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | SILVERADO 2104 RECONDUCTOR PROJECT | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786201 | CWSP - MORAGA 1101 - LR 108540 - PH 5 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 07/02/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - MORAGA 1101 (VARIOUS) - OCB | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786203 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 07/03/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - CAMP EVERS 2106 - 5020 - PHASE 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786204 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.6 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 07/03/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - CAMP EVERS 2106 - 5020 - PHASE 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786218 | CWSP - BRUNSWICK 1102 - LR 1010 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 07/02/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BRUNSWICK 1102 - LR 1010 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786219 | CWSP - WYANDOTTE 1103 – LR 1974 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 07/02/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - WYANDOTTE 1103 – LR 1974 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786220 | CWSP - LOS GATOS 1107 – LR 60114 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 07/02/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - LOS GATOS 1107 – LR 60114 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786325 | DIABLO WILDFIRE HARDENING PROJECT | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 07/10/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - MORAGA 1101 (VARIOUS) - OCB | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786326 | CWSP-MIWUK 1702-LR6018-PHASE 2 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 07/10/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786327 | CWSP-ORO FINO 1102 OCB & LR2090 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 07/10/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-ORO FINO 1102 OCB & LR2090 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786460 | CWSP - MIWUK 1702 - LR6018 - PH 2 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 07/22/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-MIWUK 1702-LR6018-PHASE 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786461 | CWSP - El Dorado 2101 - 19752 - Ph. 4.1 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 07/23/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786479 | CWSP - VOLTA 1102 LR 1648 PH 2.1 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 07/24/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - VOLTA 1102 LR 1648 PH 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786480 | CWSP - BRUNSWICK 1103 LR2200 HARDENING | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 07/26/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BRUNSWICK 1103 LR2200 HARDENING | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786518 | CWSP-Brunswick 1103 LR50070 ZONE-PH 3.6 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 07/24/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Brunswick 1103 LR50070 Zone-Ph3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786587 | CWSP - Los Gatos 1106 - LB44 Ph 4.3 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 08/02/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - LOS GATOS 1106 - LB44 - PHASE 4 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786588 | CWSP - Los Gatos 1106 - LB44 Ph 4.2 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 08/02/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - LOS GATOS 1106 - LB44 - PHASE 4 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786589 | CWSP - Los Gatos 1106 - LB44 Ph 4.1 u/g | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 08/02/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - LOS GATOS 1106 - LB44 - PHASE 4 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786602 | CWSP - Los Gatos 1106 - LB44 - Ph 2.4D | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 08/02/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Los Gatos 1106 - LB44 - Ph 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786603 | CWSP - Los Gatos 1106 - LB44 - Ph 2.4D | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 08/02/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Los Gatos 1106 - LB44 - Ph 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786604 | CWSP - Los Gatos 1106 - LB44 - Ph 3.6 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 08/02/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Los Gatos 1106 - LB44 - Ph 3.1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786605 | CWSP - Los Gatos 1106 - LB44 - Ph 3.5 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 08/02/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Los Gatos 1106 - LB44 - Ph 3.1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786638 | RPL OH WIRE ON OTTER-1101 S | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 08/01/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Deleted/Cancelled projects | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786658 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.1 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 08/05/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - CAMP EVERS 2106 - 5020 - PHASE 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786672 | CWSP - ORO FINO 1101 - LR2022 PH 1.2 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5786672 | CWSP - ORO FINO 1101 - LR2022 PH 1.2 | 0.000 | 0.000 | 08W | 08/09/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - ORO FINO-1101 LR-2022 PH I | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786673 | CWSP - ORO FINO 1101 - LR2022 PH 1.3 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5786673 | CWSP - ORO FINO 1101 - LR2022 PH 1.3 | 0.000 | 0.000 | 08W | 08/09/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - ORO FINO-1101 LR-2022 PH I | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786674 | CWSP - ORO FINO 1101 - LR2022 PH 1.4 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5786674 | CWSP - ORO FINO 1101 - LR2022 PH 1.4 | 0.000 | 0.000 | 08W | 08/09/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - ORO FINO-1101 LR-2022 PH I | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786675 | CWSP - ORO FINO 1101 - LR2022 PH 1.5 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5786675 | CWSP - ORO FINO 1101 - LR2022 PH 1.5 | 0.000 | 0.000 | 08W | 08/09/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - ORO FINO-1101 LR-2022 PH I | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786676 | CWSP - ORO FINO 1101 - LR2022 PH 1.6 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5786676 | CWSP - ORO FINO 1101 - LR2022 PH 1.6 | 0.000 | 0.000 | 08W | 08/09/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - ORO FINO-1101 LR-2022 PH I | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786677 | CWSP - ORO FINO 1101 - LR2022 PH 1.7 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5786677 | CWSP - ORO FINO 1101 - LR2022 PH 1.7 | 0.000 | 0.000 | 08W | 08/09/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - ORO FINO-1101 LR-2022 PH I | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786698 | CWSP - MIRABEL 02/MONTE RIO 13-LR652 Ph2 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 08/07/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786738 | CWSP - ORO FINO 1101 - LR2022 PH 1.8 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5786738 | CWSP - ORO FINO 1101 - LR2022 PH 1.8 | 0.000 | 0.000 | 08W | 08/09/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - ORO FINO-1101 LR-2022 PH I | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786739 | CWSP - ORO FINO 1101 - LR2022 PH 2.2 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5786739 | CWSP - ORO FINO 1101 - LR2022 PH 2.2 | 0.000 | 0.000 | 08W | 08/09/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - ORO FINO-1101 LR-2022 PH 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786740 | CWSP - ORO FINO 1101 - LR2022 PH 2.3 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5786740 | CWSP - ORO FINO 1101 - LR2022 PH 2.3 | 0.000 | 0.000 | 08W | 08/09/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - ORO FINO-1101 LR-2022 PH 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786741 | CWSP - ORO FINO 1101 - LR2022 PH 2.4 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5786741 | CWSP - ORO FINO 1101 - LR2022 PH 2.4 | 0.000 | 0.000 | 08W | 08/09/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - ORO FINO-1101 LR-2022 PH 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786742 | CWSP - ORO FINO 1101 - LR2022 PH 2.5 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5786742 | CWSP - ORO FINO 1101 - LR2022 PH 2.5 | 0.000 | 0.000 | 08W | 08/09/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - ORO FINO-1101 LR-2022 PH 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786743 | CWSP - ORO FINO 1101 - LR2022 PH 2.6 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5786743 | CWSP - ORO FINO 1101 - LR2022 PH 2.6 | 0.000 | 0.000 | 08W | 08/09/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - ORO FINO-1101 LR-2022 PH 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786744 | CWSP - ORO FINO 1101 - LR2022 PH 3.2 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5786744 | CWSP - ORO FINO 1101 - LR2022 PH 3.2 | 0.000 | 0.000 | 08W | 08/09/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-ORO FINO 1101 LR-2022 PH 3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786745 | CWSP - ORO FINO 1101 - OCB PH 1.2 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5786745 | CWSP - ORO FINO 1101 - OCB PH 1.2 | 0.000 | 0.000 | 08W | 08/09/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-ORO FINO 1101 OCB PH 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786746 | CWSP - ORO FINO 1101 - OCB PH 1.3 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5786746 | CWSP - ORO FINO 1101 - OCB PH 1.3 | 0.000 | 0.000 | 08W | 08/09/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-ORO FINO 1101 OCB PH 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786747 | CWSP - ORO FINO 1101 - OCB PH 1.4 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5786747 | CWSP - ORO FINO 1101 - OCB PH 1.4 | 0.000 | 0.000 | 08W | 08/09/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-ORO FINO 1101 OCB PH 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786748 | CWSP - ORO FINO 1101 - OCB PH 1.5 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5786748 | CWSP - ORO FINO 1101 - OCB PH 1.5 | 0.000 | 0.000 | 08W | 08/09/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-ORO FINO 1101 OCB PH 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786749 | CWSP - ORO FINO 1101 - OCB PH 1.6 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5786749 | CWSP - ORO FINO 1101 - OCB PH 1.6 | 0.000 | 0.000 | 08W | 08/09/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-ORO FINO 1101 OCB PH 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786750 | CWSP - ORO FINO 1101 - OCB PH 1.7 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5786750 | CWSP - ORO FINO 1101 - OCB PH 1.7 | 0.000 | 0.000 | 08W | 08/09/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-ORO FINO 1101 OCB PH 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786751 | CWSP - ORO FINO 1101 - OCB PH 2.2 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5786751 | CWSP - ORO FINO 1101 - OCB PH 2.2 | 0.000 | 0.000 | 08W | 08/09/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-ORO FINO 1101 OCB PH 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786752 | CWSP - ORO FINO 1101 - OCB PH 2.3 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5786752 | CWSP - ORO FINO 1101 - OCB PH 2.3 | 0.000 | 0.000 | 08W | 08/09/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-ORO FINO 1101 OCB PH 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786753 | CWSP - ORO FINO 1101 - OCB PH 2.4 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5786753 | CWSP - ORO FINO 1101 - OCB PH 2.4 | 0.000 | 0.000 | 08W | 08/09/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-ORO FINO 1101 OCB PH 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786754 | CWSP - ORO FINO 1101 - OCB PH 2.5 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5786754 | CWSP - ORO FINO 1101 - OCB PH 2.5 | 0.000 | 0.000 | 08W | 08/09/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-ORO FINO 1101 OCB PH 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786755 | CWSP - ORO FINO 1101 - OCB PH 2.6 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5786755 | CWSP - ORO FINO 1101 - OCB PH 2.6 | 0.000 | 0.000 | 08W | 08/09/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-ORO FINO 1101 OCB PH 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786756 | CWSP - ORO FINO 1101 - OCB PH 3.2 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5786756 | CWSP - ORO FINO 1101 - OCB PH 3.2 | 0.000 | 0.000 | 08W | 08/09/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-ORO FINO 1101 OCB PH 3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786757 | CWSP - ORO FINO 1101 - OCB PH 3.3 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5786757 | CWSP - ORO FINO 1101 - OCB PH 3.3 | 0.000 | 0.000 | 08W | 08/09/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-ORO FINO 1101 OCB PH 3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786758 | CWSP - ORO FINO 1101 - OCB PH 3.4 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5786758 | CWSP - ORO FINO 1101 - OCB PH 3.4 | 0.000 | 0.000 | 08W | 08/09/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-ORO FINO 1101 OCB PH 3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786759 | CWSP - ORO FINO 1102 - LR2560 PH 1.2 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5786759 | CWSP - ORO FINO 1102 - LR2560 PH 1.2 | 0.000 | 0.000 | 08W | 08/09/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-ORO FINO 1102 LR-2560 PH 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786760 | CWSP - ORO FINO 1102 - LR2560 PH 1.3 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5786760 | CWSP - ORO FINO 1102 - LR2560 PH 1.3 | 0.000 | 0.000 | 08W | 08/09/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-ORO FINO 1102 LR-2560 PH 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786761 | CWSP - ORO FINO 1102 - LR2560 PH 1.4 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5786761 | CWSP - ORO FINO 1102 - LR2560 PH 1.4 | 0.000 | 0.000 | 08W | 08/09/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-ORO FINO 1102 LR-2560 PH 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786762 | CWSP - ORO FINO 1102 - LR2560 PH 1.5 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5786762 | CWSP - ORO FINO 1102 - LR2560 PH 1.5 | 0.000 | 0.000 | 08W | 08/09/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-ORO FINO 1102 LR-2560 PH 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786763 | CWSP - ORO FINO 1102 - LR2560 PH 2.2 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5786763 | CWSP - ORO FINO 1102 - LR2560 PH 2.2 | 0.000 | 0.000 | 08W | 08/09/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-ORO FINO 1102 LR-2560 PH 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786764 | CWSP - ORO FINO 1102 - LR2560 PH 2.3 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5786764 | CWSP - ORO FINO 1102 - LR2560 PH 2.3 | 0.000 | 0.000 | 08W | 08/09/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-ORO FINO 1102 LR-2560 PH 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786765 | CWSP - ORO FINO 1102 - LR2560 PH 2.4 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5786765 | CWSP - ORO FINO 1102 - LR2560 PH 2.4 | 0.000 | 0.000 | 08W | 08/09/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-ORO FINO 1102 LR-2560 PH 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786766 | CWSP - ORO FINO 1102 - LR2560 PH 2.5 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5786766 | CWSP - ORO FINO 1102 - LR2560 PH 2.5 | 0.000 | 0.000 | 08W | 08/09/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-ORO FINO 1102 LR-2560 PH 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786767 | CWSP - ORO FINO 1102 - LR76008 PH 1.2 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5786767 | CWSP - ORO FINO 1102 - LR76008 PH 1.2 | 0.000 | 0.000 | 08W | 08/09/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-ORO FINO 1102 LR-76008 PH 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786768 | CWSP - ORO FINO 1102 - LR76008 PH 1.3 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5786768 | CWSP - ORO FINO 1102 - LR76008 PH 1.3 | 0.000 | 0.000 | 08W | 08/09/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-ORO FINO 1102 LR-76008 PH 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786769 | CWSP - ORO FINO 1102 - LR76008 PH 1.4 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5786769 | CWSP - ORO FINO 1102 - LR76008 PH 1.4 | 0.000 | 0.000 | 08W | 08/09/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-ORO FINO 1102 LR-76008 PH 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786770 | CWSP - ORO FINO 1102 - LR76008 PH 1.5 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5786770 | CWSP - ORO FINO 1102 - LR76008 PH 1.5 | 0.000 | 0.000 | 08W | 08/09/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-ORO FINO 1102 LR-76008 PH 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786771 | CWSP - ORO FINO 1102 - LR76008 PH 2.2 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5786771 | CWSP - ORO FINO 1102 - LR76008 PH 2.2 | 0.000 | 0.000 | 08W | 08/09/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-ORO FINO 1102 LR-76008 PH 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786772 | CWSP - ORO FINO 1102 - LR76008 PH 2.3 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5786772 | CWSP - ORO FINO 1102 - LR76008 PH 2.3 | 0.000 | 0.000 | 08W | 08/09/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-ORO FINO 1102 LR-76008 PH 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786773 | CWSP - ORO FINO 1102 - LR76008 PH 2.4 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5786773 | CWSP - ORO FINO 1102 - LR76008 PH 2.4 | 0.000 | 0.000 | 08W | 08/09/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-ORO FINO 1102 LR-76008 PH 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786774 | CWSP - ORO FINO 1102 - LR76008 PH 2.5 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5786774 | CWSP - ORO FINO 1102 - LR76008 PH 2.5 | 0.000 | 0.000 | 08W | 08/09/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-ORO FINO 1102 LR-76008 PH 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786775 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.2 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5786775 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.2 | 0.000 | 0.000 | 08W | 08/09/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-ORO FINO 1102 OCB & LR2090 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786776 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.3 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5786776 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.3 | 0.000 | 0.000 | 08W | 08/09/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-ORO FINO 1102 OCB & LR2090 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786777 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.4 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5786777 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.4 | 0.000 | 0.000 | 08W | 08/09/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-ORO FINO 1102 OCB & LR2090 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786778 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.5 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5786778 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.5 | 0.000 | 0.000 | 08W | 08/09/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-ORO FINO 1102 OCB & LR2090 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786779 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.6 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5786779 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.6 | 0.000 | 0.000 | 08W | 08/09/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-ORO FINO 1102 OCB & LR2090 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786780 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.7 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5786780 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.7 | 0.000 | 0.000 | 08W | 08/09/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-ORO FINO 1102 OCB & LR2090 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786781 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.8 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5786781 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.8 | 0.000 | 0.000 | 08W | 08/09/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-ORO FINO 1102 OCB & LR2090 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786782 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.9 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5786782 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.9 | 0.000 | 0.000 | 08W | 08/09/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-ORO FINO 1102 OCB & LR2090 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786800 | *DUMMY*CWSP -TASSAJARA 2112 - FUSE 18053 | # | # | Not assigned | 40 | Closed | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 08/13/2019 | 08/13/2019 | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5786801 | *DUMMY*CWSP -TASSAJARA 2112 - FUSE 18053 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 08/13/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5787047 | CWSP Fulton-Calistoga Tx-Dist | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5786045 | CWSP - FULTON 1107 - MARK WEST SPR RD | 0.000 | 0.000 | 08W | 08/20/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Fulton-Calistoga 60 kV Line Reconductor | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5787200 | 16149CIRCUIT FT(52 SPANS) 4ACSR&6CU W2CU | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5517127 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 08/28/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | 16149CIRCUIT FT(52 SPANS) 4ACSR&6CU W2CU | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
5787201 | ELK HILLS 1104 OH SPLICE SSD1523 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5517127 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 08/28/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | ELK HILLS 1104 OH SPLICE SSD1523 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
5787202 | R2OLD RIVR 1102 REPLACE ANNEALD CONDUCTO | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5517127 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 08/28/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | R2OLD RIVR 1102 REPLACE ANNEALD CONDUCTO | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
5787203 | RECOND WATSONVILLE 2101 REF# S074CC218 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5517127 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 08/28/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | RECOND WATSONVILLE 2101 REF# S074CC218 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
5787438 | STONE CORRAL 1110 RECOND 19,622/W 4/OAL | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 09/16/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | STONE CORRAL 1110 RECOND 19,622'/W 4/OAL | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
5788460 | CWSP - MIWUK 1702 - LR 38218 - PH 1.2 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 11/14/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5788622 | CWSP - BRUNSWICK 1103 LR2200 HARDENING 2 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 11/26/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BRUNSWICK 1103 LR2200 HARDENING | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5788623 | CWSP - BRUNSWICK 1103 LR2200 HARDENING 3 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 11/26/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BRUNSWICK 1103 LR2200 HARDENING | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5788624 | CWSP - BRUNSWICK 1103 LR2200 HARDENING 4 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 11/26/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BRUNSWICK 1103 LR2200 HARDENING | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5788628 | CWSP-ORO FINO 1101 LR-2022 PH 1.2 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08W | 11/26/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | GRC Electric Dist | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
5788629 | CWSP-ORO FINO 1101 LR-2022 PH 1.3 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08W | 11/26/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | GRC Electric Dist | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
5788630 | CWSP-ORO FINO 1101 LR-2022 PH 1.4 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08W | 11/26/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | GRC Electric Dist | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
5788631 | CWSP-ORO FINO 1101 LR-2022 PH 1.5 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08W | 11/26/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | GRC Electric Dist | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
5788632 | CWSP-ORO FINO 1101 LR-2022 PH 1.6 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08W | 11/26/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | GRC Electric Dist | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
5788684 | CWSP-ORO FINO 1101 LR-2022 PH 1.8 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 12/02/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5788685 | CWSP-ORO FINO 1101 LR-2022 PH 1.7 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 12/02/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5788778 | PSPS - Clayton 2215 - CB | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 12/09/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | PSPS - Clayton 2215 – CB | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5788779 | PSPS - Frogtown 1702 - CB | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 12/09/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | PSPS - Frogtown 1702 - CB | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5788780 | PSPS - Ignacio 1101 - CB | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 12/09/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | PSPS - Ignacio 1101 - CB | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5788781 | PSPS - Moraga 1103 - CB | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 12/09/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | PSPS - Moraga 1103 - CB | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5788782 | PSPS - Rossmoor 1106 - CB | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 12/09/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | PSPS - Rossmoor 1106 – CB | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5788783 | PSPS - Clarksville 2104 - CB | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 12/09/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | PSPS - Clarksville 2104 - CB | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5788784 | PSPS - Fulton 1102 - CB | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 12/09/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | PSPS - Fulton 1102 - CB | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5788785 | PSPS-Stafford 1101 CB PH 1 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 12/09/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | PSPS - Stafford 1101 CB PH 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5788786 | PSPS - Rincon 1101 and 1103- CB | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 12/09/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | PSPS - Rincon 1101 and 1103- CB | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5788787 | PSPS - Rincon 1102 and 1104 - CB | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 12/09/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | PSPS - Rincon 1102 and 1104 - CB | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5788788 | PSPS - Stafford 1101 - LR 1298 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 12/09/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | PSPS - Stafford 1101 - LR 1298 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5788789 | PSPS - Paul Sweet 2105 - CB PH 2 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 12/09/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | PSPS - Paul Sweet 2105 - CB PH 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5788790 | PSPS - Hicks 2101 - CB | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 12/09/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | PSPS - Hicks 2101 – CB | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5788791 | PSPS - Rob Roy 2105 - CB | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 12/09/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | PSPS - Rob Roy 2105 - CB | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5788792 | PSPS - Paul Sweet 2105 - CB PH 1 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 12/09/2019 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | PSPS - Paul Sweet 2105 - CB PH 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5789366 | CWSP - BRUNSWICK 1105 - LR 2140 - PH 1.0 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5789366 | CWSP - BRUNSWICK 1105 - LR 2140 - PH 1.0 | 0.000 | 0.000 | 08W | 01/22/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BRUNSWICK 1105 LR2140 HARDENING - | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5789378 | CWSP - BRUNSWICK 1105 - LR 2140 - PH 1.0 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 01/22/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BRUNSWICK 1105 LR2140 HARDENING - | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5789379 | CWSP - BRUNSWICK 1105 - LR 2140 - PH 1.0 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 01/22/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BRUNSWICK 1105 LR2140 HARDENING - | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5789380 | CWSP - BRUNSWICK 1105 - LR 2140 - PH 1.0 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 01/22/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BRUNSWICK 1105 LR2140 HARDENING - | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5789381 | CWSP - BRUNSWICK 1105 - LR 2140 - PH 1.0 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 01/22/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BRUNSWICK 1105 LR2140 HARDENING - | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5789382 | CWSP - BRUNSWICK 1105 - LR 2140 - PH 1.0 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 01/22/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BRUNSWICK 1105 LR2140 HARDENING - | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5789383 | CWSP - BRUNSWICK 1105 - LR 2140 - PH 1.0 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 01/22/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BRUNSWICK 1105 LR2140 HARDENING - | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5789384 | CWSP - BRUNSWICK 1105 - LR 2140 - PH 1.0 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 01/22/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BRUNSWICK 1105 LR2140 HARDENING - | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5789385 | CWSP - BRUNSWICK 1105 - LR 2140 - PH 1.1 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 01/22/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BRUNSWICK 1105 LR2140 HARDENING - | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5789386 | CWSP - BRUNSWICK 1105 - LR 2140 - PH 1.1 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 01/22/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BRUNSWICK 1105 LR2140 HARDENING - | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5789387 | CWSP - BRUNSWICK 1105 - LR 2140 - PH 1.1 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 01/22/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BRUNSWICK 1105 LR2140 HARDENING - | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5789388 | CWSP - BRUNSWICK 1105 - LR 2140 - PH 1.1 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 01/22/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BRUNSWICK 1105 LR2140 HARDENING - | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5789389 | CWSP - BRUNSWICK 1105 - LR 2140 - PH 1.1 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 01/22/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BRUNSWICK 1105 LR2140 HARDENING - | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5789390 | CWSP - BRUNSWICK 1105 - LR 2140 - PH 1.1 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 01/22/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BRUNSWICK 1105 LR2140 HARDENING - | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5789391 | CWSP - BRUNSWICK 1105 - LR 2140 - PH 1.1 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 01/22/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BRUNSWICK 1105 LR2140 HARDENING - | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5789392 | CWSP - BRUNSWICK 1105 - LR 2140 - PH 2.0 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 01/22/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BRUNSWICK 1105 LR2140 HARDENING - | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5789393 | CWSP - BRUNSWICK 1105 - LR 2140 - PH 2.0 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 01/22/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BRUNSWICK 1105 LR2140 HARDENING - | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5789394 | CWSP - BRUNSWICK 1105 - LR 2140 - PH 2.0 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 01/22/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BRUNSWICK 1105 LR2140 HARDENING - | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5789395 | CWSP - BRUNSWICK 1105 - LR 2140 - PH 2.0 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 01/22/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BRUNSWICK 1105 LR2140 HARDENING - | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5789396 | CWSP - BRUNSWICK 1105 - LR 2140 - PH 2.0 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 01/22/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BRUNSWICK 1105 LR2140 HARDENING - | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5789397 | CWSP - BRUNSWICK 1105 - LR 2140 - PH 2.0 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 01/22/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BRUNSWICK 1105 LR2140 HARDENING - | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5789398 | CWSP - BRUNSWICK 1105 - LR 2140 - PH 2.0 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 01/22/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BRUNSWICK 1105 LR2140 HARDENING - | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5789399 | CWSP - BRUNSWICK 1105 - LR 2140 - PH 2.0 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 01/22/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BRUNSWICK 1105 LR2140 HARDENING - | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5789400 | CWSP - BRUNSWICK 1105 - LR 2140 - PH 2.1 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 01/22/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BRUNSWICK 1105 LR2140 HARDENING - | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5789401 | CWSP - BRUNSWICK 1105 - LR 2140 - PH 2.1 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 01/22/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BRUNSWICK 1105 LR2140 HARDENING - | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5789402 | CWSP - BRUNSWICK 1105 - LR 2140 - PH 2.1 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 01/22/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BRUNSWICK 1105 LR2140 HARDENING - | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5789403 | CWSP - BRUNSWICK 1105 - LR 2140 - PH 2.1 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 01/22/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BRUNSWICK 1105 LR2140 HARDENING - | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5789404 | CWSP - BRUNSWICK 1105 - LR 2140 - PH 2.1 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 01/22/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BRUNSWICK 1105 LR2140 HARDENING - | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5789405 | CWSP - BRUNSWICK 1105 - LR 2140 - PH 2.1 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 01/22/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BRUNSWICK 1105 LR2140 HARDENING - | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5789406 | CWSP - BRUNSWICK 1105 - LR 2140 - PH 2.1 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 01/22/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BRUNSWICK 1105 LR2140 HARDENING - | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5789407 | CWSP - BRUNSWICK 1105 - LR 2140 - PH 2.1 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 01/22/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BRUNSWICK 1105 LR2140 HARDENING - | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5789408 | CWSP - BRUNSWICK 1105 - LR 2140 - PH 3.0 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 01/22/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BRUNSWICK 1105 LR2140 HARDENING - | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5789409 | CWSP - BRUNSWICK 1105 - LR 2140 - PH 3.0 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 01/22/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BRUNSWICK 1105 LR2140 HARDENING - | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5789410 | CWSP - BRUNSWICK 1105 - LR 2140 - PH 3.0 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 01/22/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BRUNSWICK 1105 LR2140 HARDENING - | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5789411 | CWSP - BRUNSWICK 1105 - LR 2140 - PH 3.0 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 01/22/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BRUNSWICK 1105 LR2140 HARDENING - | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5789412 | CWSP - BRUNSWICK 1105 - LR 2140 - PH 3.0 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 01/22/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BRUNSWICK 1105 LR2140 HARDENING - | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5789413 | CWSP - BRUNSWICK 1105 - LR 2140 - PH 3.0 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 01/22/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BRUNSWICK 1105 LR2140 HARDENING - | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5789414 | CWSP - BRUNSWICK 1105 - LR 2140 - PH 3.0 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 01/22/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BRUNSWICK 1105 LR2140 HARDENING - | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5789415 | CWSP - BRUNSWICK 1105 - LR 2140 - PH 3.0 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 01/22/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BRUNSWICK 1105 LR2140 HARDENING - | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5789416 | CWSP - BRUNSWICK 1105 - LR 2140 - PH 3.1 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 01/22/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BRUNSWICK 1105 LR2140 HARDENING - | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5789417 | CWSP - BRUNSWICK 1105 - LR 2140 - PH 3.1 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 01/22/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BRUNSWICK 1105 LR2140 HARDENING - | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5789418 | CWSP - BRUNSWICK 1105 - LR 2140 - PH 3.1 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 01/22/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - BRUNSWICK 1105 LR2140 HARDENING - | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5789678 | Rice 1102 - Reconductor 20,775 FT w 2AR | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 02/10/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Rice 1102 - Reconductor 20,775 ft w 2AR | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
5789698 | CWSP-BRUNSWICK1105-LR2210-PH1.2 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 02/10/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Brunswick - 1105 - LR2210 Zone-Ph | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5789699 | CWSP-BRUNSWICK1105-LR2210-PH1.3 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 02/10/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Brunswick - 1105 - LR2210 Zone-Ph | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5789700 | CWSP-BRUNSWICK1105-LR2210-PH1.4 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 02/10/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Brunswick - 1105 - LR2210 Zone-Ph | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5789701 | CWSP-BRUNSWICK1105-LR2210-PH1.5 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 02/10/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Brunswick - 1105 - LR2210 Zone-Ph | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5789702 | CWSP-BRUNSWICK1105-LR2210-PH1.6 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 02/10/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Brunswick - 1105 - LR2210 Zone-Ph | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5789703 | CWSP-BRUNSWICK1105-LR2210-PH1.7 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 02/10/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Brunswick - 1105 - LR2210 Zone-Ph | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5789704 | CWSP-BRUNSWICK1105-LR2210-PH1.8 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 02/10/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Brunswick - 1105 - LR2210 Zone-Ph | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5789705 | CWSP-BRUNSWICK1105-LR2210-PH1.9 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 02/10/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Brunswick - 1105 - LR2210 Zone-Ph | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5789706 | CWSP-BRUNSWICK1105-LR2210-PH2.2 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 02/10/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Brunswick - 1105 - LR2210 Zone-Ph | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5789707 | CWSP-BRUNSWICK1105-LR2210-PH2.3 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 02/10/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Brunswick - 1105 - LR2210 Zone-Ph | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5789708 | CWSP-BRUNSWICK1105-LR2210-PH2.4 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 02/10/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Brunswick - 1105 - LR2210 Zone-Ph | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5789709 | CWSP-BRUNSWICK1105-LR2210-PH2.5 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 02/10/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Brunswick - 1105 - LR2210 Zone-Ph | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5789710 | CWSP-BRUNSWICK1105-LR2210-PH2.6 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 02/10/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Brunswick - 1105 - LR2210 Zone-Ph | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5789711 | CWSP-BRUNSWICK1105-LR2210-PH2.7 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 02/10/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Brunswick - 1105 - LR2210 Zone-Ph | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5790001 | ECOP-BRUNSWICK 1106-LR51486 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 03/03/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP-Brunswick 1106-H08-LR51486 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5790002 | ECOP-EL DORADO 2101-H02-LR6852-Ph1 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 03/03/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP-El Dorado 2101-H02-LR6852-Ph1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5790003 | ECOP-EL DORADO 2101-H02-LR6852-Ph2 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 03/03/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP-El Dorado 2101-H02-LR6852-Ph2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5790004 | ECOP-EL DORADO 2101-H02-LR6852-Ph3 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 03/03/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP-El Dorado 2101-H02-LR6852-Ph3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5790005 | ECOP-WEST POINT 1101-H02-LR36674 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 03/03/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP-WEST POINT 1101-H02-LR36674 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5790006 | ECOP-CALISTOGA 1101-H02-LR43924 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 03/03/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP-Calistoga 1101-H02-LR43924 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5790007 | ECOP-CALISTOGA 1101-H03-LR43924 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 03/03/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP-Calistoga 1101-H03-LR43924 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5790008 | ECOP-MOLINO 1102-H01-LR318 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 03/03/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP-Molino 1102-H01-LR318 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5790010 | CWSP - BUCOCAMP-SKYWAY PARADISE TIE PH2 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5790010 | CWSP - BUCOCAMP-SKYWAY PARADISE TIE PH2 | 0.000 | 0.000 | 08W | 03/04/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5790011 | CWSP-PLACERVILLE 2106-LR1104-PH 1.3 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 03/05/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Placerville 2106 - LR 1104 - Ph 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5790104 | ECOP-PINE GROVE 1102-H01-LR45292 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 03/11/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP-Calistoga 1101-H01-LR736 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5790105 | ECOP-PINE GROVE 1102-H01-LR45292 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 03/11/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP-Pine Grove 1102-H01-LR45292 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5790106 | ECOP-STANISLAUS 1702-H01-LR37276-Ph1 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 03/11/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP-Stanislaus 1702-H01-LR37276-Ph1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5790107 | ECOP-STANISLAUS 1702-H01-LR37276-Ph2 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 03/11/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP-Stanislaus 1702-H01-LR37276-Ph2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5790108 | ECOP-CALISTOGA 1101-H01-LR736-E_O CO 380 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 03/11/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP-Calistoga 1101-H01-LR736-S_O 208157 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5790109 | ECOP-CALISTOGA 1101-H01-LR736-N_O CO 772 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 03/11/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP-Calistoga 1101-H01-LR736-N_O CO7729 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5790110 | ECOP-CALISTOGA 1101-H01-LR736-Ph3 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 03/11/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP-Calistoga 1101-H01-LR736-Ph3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5790111 | ECOP-MIDDLETOWN 1101-H12-LR548-Ph1 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08W | 03/11/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
5790112 | ECOP-MIDDLETOWN 1101-H12-LR548-Ph1 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 03/11/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP-Middletown 1101-H12-LR548-Ph3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5790119 | ECOP-MIDDLETOWN 1101-H12-LR548-Ph1 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5517127 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08W | 03/11/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | ECOP-Middletown 1101-H12-LR548-Ph2 | Base Capital | GRC Electric Dist | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
5790199 | VM,Est 2021 jobs in PEND stat by EOY2020 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5790199 | VM,Est 2021 jobs in PEND stat by EOY2020 | 0.000 | 0.000 | 08W | 03/16/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5790319 | Grand Island 2227 - Reconductor 19,370ft | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5517127 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 03/23/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Grand Island - Reconductor 19,370 feet | Base Capital | GRC Electric Dist | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
5790364 | CWSP-ORO FINO 1101-LR2022-Ph2.7 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 03/31/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - ORO FINO-1101 LR-2022 PH 2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5790443 | CWSP-MIWUK 1702-LR 38218-PH1.6 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 04/09/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5790507 | 08W Rebuild Earnings Plug | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5790507 | 08W Rebuild Earnings Plug | 0.000 | 0.000 | 08W | 04/13/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5790538 | CWSP-EL DORADO PH 2102 LR19542 PH 1.5 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 04/14/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - El Dorado PH 2102 Zone 19542 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5790539 | CWSP-EL DORADO PH 2102 LR19542 PH 1.4 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 04/14/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - El Dorado PH 2102 Zone 19542 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5790541 | CWSP-PLACERVILLE 2106 LR1104 PH 2.2 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 04/15/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Placerville 2106 - LR 1104 - Phas | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5790542 | CWSP-PLACERVILLE 2106 LR1104 PH 2.3 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 04/15/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5790543 | CWSP-PLACERVILLE 2106 LR1104 PH 2.4 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 04/15/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5790544 | CWSP-PLACERVILLE 2106 LR1104 PH 2.5 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 04/15/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5790545 | CWSP-PLACERVILLE 2106 LR1104 PH 3.2 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 04/15/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-PLACERVILLE 2106 LR1104 PH 3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5790546 | CWSP-PLACERVILLE 2106 LR1104 PH 3.3 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 04/15/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-PLACERVILLE 2106 LR1104 PH 3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5790547 | CWSP-PLACERVILLE 2106 LR1104 PH 3.4 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 04/15/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-PLACERVILLE 2106 LR1104 PH 3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5790548 | CWSP-PLACERVILLE 2106 LR1104 PH 3.5 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 04/15/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-PLACERVILLE 2106 LR1104 PH 3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5790549 | CWSP-PLACERVILLE 2106 LR1104 PH 4.2 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 04/15/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-PLACERVILLE 2106 LR1104 PH 4 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5790550 | CWSP-PLACERVILLE 2106 LR1104 PH 4.3 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 04/15/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-PLACERVILLE 2106 LR1104 PH 4 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5790551 | CWSP-PLACERVILLE 2106 LR1104 PH 4.4 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 04/15/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-PLACERVILLE 2106 LR1104 PH 4 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5790552 | CWSP-PLACERVILLE 2106 LR1104 PH 4.5 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 04/15/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-PLACERVILLE 2106 LR1104 PH 4 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5790553 | CWSP-PLACERVILLE 2106 LR1104 PH 5.2 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 04/15/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-PLACERVILLE 2106 LR1104 PH 5 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5790554 | CWSP-PLACERVILLE 2106 LR1104 PH 5.3 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 04/15/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-PLACERVILLE 2106 LR1104 PH 5 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5790555 | CWSP-PLACERVILLE 2106 LR1104 PH 5.4 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 04/15/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-PLACERVILLE 2106 LR1104 PH 5 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5790556 | CWSP-PLACERVILLE 2106 LR1104 PH 5.5 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 04/15/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-PLACERVILLE 2106 LR1104 PH 5 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5790557 | CWSP-PLACERVILLE 2106 LR1104 PH 6.2 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 04/15/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-PLACERVILLE 2106 LR1104 PH 6 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5790578 | CWSP-PLACERVILLE 2106 LR1104 PH 6.3 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 04/15/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-PLACERVILLE 2106 LR1104 PH 6 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5790579 | CWSP-PLACERVILLE 2106 LR1104 PH 6.4 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 04/15/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-PLACERVILLE 2106 LR1104 PH 6 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5790580 | CWSP-PLACERVILLE 2106 LR1104 PH 6.5 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 04/15/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP-PLACERVILLE 2106 LR1104 PH 6 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5790581 | CWSP-EL DORADO PH 2102 LR19542 PH 1.2 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 04/15/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - El Dorado PH 2102 Zone 19542 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5790582 | CWSP-EL DORADO PH 2102 LR19542 PH 1.3 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 04/15/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - El Dorado PH 2102 Zone 19542 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5790907 | ECOP-West Point 1101-TS L373 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 05/06/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP-WEST POINT 1101-H03-TS L373 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5791027 | CWSP-PLACERVILLE 2106 LR1104 PH 2.8 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 05/12/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - Placerville 2106 - LR 1104 - Phas | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5791246 | Butte Rebuild UG TAP 08W | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5791246 | Butte Rebuild UG TAP 08W | 0.000 | 0.000 | 08W | 05/28/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5791278 | Wyandotte 1103 - Wiredown OH Conductor R | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5532077 | ED MAT 08W (Rate Case) | 0.000 | 0.000 | 08W | 05/28/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Other Capital | Other | # | # | Electric Distribution | Electric Distribution | 0
5791419 | CWSP - BUCOCAMP-SKYWAY PARADISE TIE PH1 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5791419 | CWSP - BUCOCAMP-SKYWAY PARADISE TIE PH1 | 0.000 | 0.000 | 08W | 06/08/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5791523 | Grand Island 2224 PH1 - Reconductor 24,9 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5517127 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 06/16/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Grand Island 2224/2225 Outlet Ph1 | Base Capital | GRC Electric Dist | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
5791660 | Otter 1102 - OH Line Replc - WD #19-013 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 06/24/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Otter 1102 - OH Line Replc - #19-0131557 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5791727 | CWSP - MiWuk 1702 - LR 6018 - PH 1.1 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 07/02/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - MIWUK 1702-LR 6018-PHASE 1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5792023 | Community Resilience Program | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5792023 | Community Resilience Program | 0.000 | 0.000 | 08J | 07/16/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | OPERPRAC | Operational Practices | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5792058 | ECOP - FORESTHILL 1101 - H02-LR1802 Ph1 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 07/20/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - FORESTHILL 1101 - H02-LR1802 Ph1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5792059 | ECOP - FORESTHILL 1101 - H02-LR1802 Ph2 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 07/20/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - FORESTHILL 1101 - H02-LR1802 Ph2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5792060 | ECOP - FORESTHILL 1101 - H02-LR1802 Ph3 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 07/20/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - FORESTHILL 1101 - H02-LR1802 Ph3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5792061 | ECOP - WEST POINT 1101 - H01-LR4706 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 07/20/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - WEST POINT 1101 - H01-LR4706 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5792062 | ECOP - WOODACRE 1101 - H01-LR404 Ph1 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 07/20/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - WOODACRE 1101 - H01-LR404 Ph1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5792063 | ECOP - WOODACRE 1101 - H01-LR404 Ph2 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 07/20/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - WOODACRE 1101 - H01-LR404 Ph2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5792064 | ECOP - PUEBLO 2102 - H01-LR792 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 07/20/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - PUEBLO 2102 - H01-LR792 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5792065 | ECOP - MIRABEL 1101 - H01-LR298 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 07/20/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - MIRABEL 1101 - H01-LR298 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5792066 | ECOP - PINE GROVE 1102 - H03-LR13438 Ph1 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 07/20/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - PINE GROVE 1102 - H03-LR13438 Ph1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5792067 | ECOP - PINE GROVE 1102 - H03-LR13438 Ph2 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 07/20/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - PINE GROVE 1102 - H03-LR13438 Ph2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5792068 | ECOP - STANISLAUS 1702 - H02-LR75348 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 07/20/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - STANISLAUS 1702 - H02-LR75348 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5792069 | ECOP - RINCON 1103 - H01-LR474 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 07/20/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - RINCON 1103 - H01-LR474 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5792070 | ECOP - COLUMBIA HILL 1101 - H01-LR35424 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 07/20/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - COLUMBIA HILL 1101 - H01-LR35424 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5792071 | ECOP - SILVERADO 2104 - H02-LR78268 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 07/20/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - SILVERADO 2104 - H02-LR78268 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5792072 | ECOP - PINE GROVE 1102 - H04-LR3172 Ph1 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 07/20/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - PINE GROVE 1102 - H04-LR3172 Ph1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5792073 | ECOP - PINE GROVE 1102 - H04-LR3172 Ph2 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 07/20/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - PINE GROVE 1102 - H04-LR3172 Ph2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5792074 | ECOP - PINE GROVE 1102 - H04-LR3172 Ph3 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 07/20/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - PINE GROVE 1102 - H04-LR3172 Ph3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5792075 | ECOP - PINE GROVE 1102 - H04-LR3172 Ph4 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 07/20/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - PINE GROVE 1102 - H04-LR3172 Ph4 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5792076 | ECOP-APPLE HILL 1104-H01-LR13512 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 07/20/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP-APPLE HILL 1104-H01-LR13512 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5792077 | ECOP - WEST POINT 1102 - H01-TS1303 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 07/20/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - WEST POINT 1102 - H01-TS1303 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5792078 | ECOP - SILVERADO 2105 - H01-LR1421 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 07/20/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - SILVERADO 2105 - H01-LR1421 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5792079 | ECOP - SALT SPRINGS 2102 - H01-LR4796 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 07/20/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - SALT SPRINGS 2102 - H01-LR4796 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5792080 | ECOP - MONTE RIO 1113 - H04-LR320 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 07/20/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - MONTE RIO 1113 - H04-LR320 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5792081 | ECOP - WEST POINT 1102 - H05-LR34416 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 07/20/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - WEST POINT 1102 - H05-LR34416 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5792082 | ECOP-OAKHURST 1103-LR 5120 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 07/20/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP-OAKHURST 1103-LR 5120 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5792083 | ECOP-OAKHURST 1103-LR 5470 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 07/20/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP-OAKHURST 1103-LR 5470 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5792084 | ECOP - MONTE RIO 1113 - H08-LR477 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 07/20/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - MONTE RIO 1113 - H08-LR477 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5792085 | ECOP - BRUNSWICK 1106 - H01-LR2796 Ph 1 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 07/20/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - BRUNSWICK 1106 - H01 - LR2796 Ph | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5792086 | ECOP - BRUNSWICK 1106 - H01-LR2796 Ph 2 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 07/20/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - BRUNSWICK 1106 - H01 - LR2796 Ph | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5792087 | ECOP - BRUNSWICK 1106 - H02 - CB | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 07/20/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - BRUNSWICK 1106 - H02 - CB | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5792088 | ECOP - BRUNSWICK 1106 - H04 - LR2416 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 07/20/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - BRUNSWICK 1106 - H04 - LR2416 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5792089 | ECOP - BRUNSWICK 1106 - H07 - LR 51484 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 07/20/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - BRUNSWICK 1106 - H07 - LR 51484 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5792090 | ECOP - CALISTOGA 1101 - H04-LR1087 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 07/20/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - CALISTOGA 1101 - H04-LR1087 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5792091 | ECOP - CLAYTON 2212 - H01-LR2951 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 07/20/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - CLAYTON 2212 - H01-LR2951 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5792092 | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 07/20/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5792093 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 07/20/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5792094 | ECOP - FULTON 1107 - H02-LR604 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 07/20/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - FULTON 1107 - H02-LR604 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5792095 | ECOP - MARIPOSA 2101 - H01-LR10170 Ph1 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 07/20/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - MARIPOSA 2101 - H01-LR10170 Ph1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5792096 | ECOP - MARIPOSA 2101 - H01-LR10170 Ph2 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 07/20/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - MARIPOSA 2101 - H01-LR10170 Ph2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5792097 | ECOP - MIDDLETOWN 1101 - H16-LR48212 Ph1 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 07/20/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - MIDDLETOWN 1101 - H16-LR48212 Ph1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5792098 | ECOP - MIDDLETOWN 1101 - H16-LR48212 Ph2 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 07/20/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - MIDDLETOWN 1101 - H16-LR48212 Ph2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5792099 | ECOP - MIWUK 1702 - H01-LR8130 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 07/20/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - MIWUK 1702 - H01-LR8130 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5792100 | ECOP - MOLINO 1102 - H03-LR396 Ph1 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 07/20/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - MOLINO 1102 - H03-LR396 Ph1 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5792101 | ECOP - MOLINO 1102 - H03-LR396 Ph2 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 07/20/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - MOLINO 1102 - H03-LR396 Ph2 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5792102 | ECOP - PINE GROVE 1102 - H06-LR83098 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 07/20/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - PINE GROVE 1102 - H06-LR83098 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5792103 | ECOP - PINE GROVE 1102 - H07-CB | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 07/20/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - PINE GROVE 1102 - H07-CB | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5792104 | ECOP - RINCON 1103 - H02-LR198 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 07/20/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - RINCON 1103 - H02-LR198 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5792105 | ECOP - SALT SPRINGS 2102 - H02-LR37300 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 07/20/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - SALT SPRINGS 2102 - H02-LR37300 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5792106 | ECOP - SALT SPRINGS 2102 - H04-LR97924 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 07/20/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - SALT SPRINGS 2102 - H04-LR97924 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5792107 | ECOP - SILVERADO 2104 - H05-LR726 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 07/20/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - SILVERADO 2104 - H05-LR726 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5792108 | ECOP - WEST POINT 1101 - H04-TSL3355 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 07/20/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - WEST POINT 1101 - H04-TSL3355 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5792109 | ECOP - WEST POINT 1102 - H06-LR36676 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 07/20/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - WEST POINT 1102 - H06-LR36676 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5792110 | ECOP - WEST POINT 1102 - H07-LR93116 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 07/20/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - WEST POINT 1102 - H07-LR93116 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5792200 | ECOP-CALISTOGA 1101-H01-LR736-Ph4 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5517127 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08W | 07/31/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | ECOP-CALISTOGA 1101-H01-LR736-Ph4 | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
5792231 | SH-Active Reserve | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5792231 | SH-Active Reserve | 0.000 | 0.000 | 08W | 08/07/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5792513 | ECOP - FORESTHILL 1101 - H03-LR50486 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 08/28/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | ECOP - FORESTHILL 1101 - H03-LR50486 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5792793 | MAT 08W – 2021 Planning | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5517127 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08W | 09/03/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
5792797 | System Hardening 2021 planning only | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5792797 | System Hardening 2021 planning only | 0.000 | 0.000 | 08W | 09/03/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5792923 | Syst Hard - Restoration work | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5792923 | Syst Hard - Restoration work | 0.000 | 0.000 | 08W | 09/11/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5793698 | Butte Rebuild 08W - Planning only | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5793698 | Butte Rebuild 08W - Planning only | 0.000 | 0.000 | 08W | 10/05/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5793703 | CWSP - CAMP EVERS 2106 - LR5020 - PH 3 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 10/05/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | CWSP - CAMP EVERS 2106 - 5020 - PHASE 3 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5793711 | CWSP-MIWUK 1701-LR 8050 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 10/06/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5793892 | FRRB - NB NAPA COUNTY | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 10/16/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | FRRB - NB NAPA COUNTY | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5793893 | FRRB - SO SONOMA COUNTY | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 10/16/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | FRRB - SO SONOMA COUNTY | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5793894 | FRRB - SAC SOLANO COUNTY | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 10/16/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | FRRB - SAC SOLANO COUNTY | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5793895 | FRRB - CC MONTEREY COUNTY | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 10/16/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | FRRB - CC MONTEREY COUNTY | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5793896 | FRRB - CC SANTA CRUZ COUNTY | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 10/16/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | FRRB - CC SANTA CRUZ COUNTY | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5793897 | FRRB - SJ SANTA CLARA COUNTY | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 10/16/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | FRRB - SJ SANTA CLARA COUNTY | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5793918 | FRRB - NV BUTTE COUNTY | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 10/16/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | FRRB - NV BUTTE COUNTY | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5793919 | FRRB - NV SHASTA COUNTY | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 10/16/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | FRRB - NV SHASTA COUNTY | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5793920 | FRRB - YO MADERA COUNTY | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 10/16/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | FRRB - YO MADERA COUNTY | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5793921 | FRRB - FR FRESNO COUNTY | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 10/16/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | FRRB - FR FRESNO COUNTY | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5793922 | FRRB - HB TRINITY COUNTY | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 10/16/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | FRRB - HB TRINITY COUNTY | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5794201 | FRRB - PN Division Santa Cruz County | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 11/12/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | FRRB - PN Division Santa Cruz County | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5794202 | FRRB - PN Division San Mateo County | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 11/12/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | FRRB - PN Division San Mateo County | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5794203 | System Hardening - Upper Lake 1101 CB | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 11/12/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | SH - Upper Lake 1101 CB | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5794204 | System Hardening - Keswick 1101 LR 1586 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 11/12/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | SH - Keswick 1101 LR 1586 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5794205 | System Hardening - Middletown 1103 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 11/12/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | SH - Middletown 1103 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5794206 | System Hardening - Konocti 1101 LR 96507 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 11/12/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | SH - Konocti 1101 LR 965078 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5794207 | System Hardening - Middletown 1102 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 11/12/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | SH - Middletown 1102 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5794208 | System Hardening - Bucks Creek 1101 CB | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 11/12/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | SH - Bucks Creek 1101 CB | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
5794209 | System Hardening - Mariposa 2102 LR 2415 | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 11/12/2020 | # | Not assigned | 0057 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | SH - Mariposa 2102 LR 241564 | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0
6124553 | Cost Model Adjustment-08J | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5517127 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 06/24/2016 | # | Not assigned | 0060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | GRC Electric Dist | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
6124555 | Cost Model Adjustment-08W | # | # | Not assigned | 10 | Created | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5532479 | CWSP 08W - Monthly Forecast Only | 0.000 | 0.000 | 08W | 06/24/2016 | # | Not assigned | 0060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | GRC Electric Dist | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 0
6130623 | WIREDOWN DATABASE | # | # | Not assigned | 20 | Released | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535457 | DO 08 - Monthly Forecast Only | 0.000 | 0.000 | 08J | 03/27/2019 | # | Not assigned | 0060 | 08 | E Dist Replace OH Asset | ERELIABT | Electric Reliability | 99 Non IT Program | Not assigned | Base Capital | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | Electric Distribution | Electric Distribution | 56503.43
6134203 | 08W Rebuild - 3rd Party Trench (Cap JE) | # | # | Not assigned | 20 | Released | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5540925 | 08W Rebuild - 3rd Party Trench (Cap JE) | 0.000 | 0.000 | 08W | 06/24/2020 | # | Not assigned | 0060 | 08 | E Dist Replace OH Asset | BUTERBLD | Butte Rebuild | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | ED - Distribution Overhead System Harden | GRC | ELEC_DIST | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 887612.42
7093505 | 08W - WILDFIRE RESILIENCY PMO | # | # | Not assigned | 20 | Released | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 05/25/2018 | # | Not assigned | 0070 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 3345032.33
7094406 | 08W - CWSP Materials | # | # | Not assigned | 20 | Released | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 11/05/2018 | # | Not assigned | 0070 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 1080.74
7094445 | 08W - Scotts Valley Winterization | # | # | Not assigned | 20 | Released | # | Not assigned | # | Not assigned |  |  | # | # | # | # | # | # | # | # | Not assigned | # | Not assigned | 5535211 | CWSP SPO - SH 08 | 0.000 | 0.000 | 08W | 11/15/2018 | # | Not assigned | 0070 | 08 | E Dist Replace OH Asset | SYSTHARD | System Hardening | 99 Non IT Program | Not assigned | Cap Bal/Memo Accts | Other | # | # | FRMMA/WMPMA - Electric | FRMMA/WMPMA - Electric | 0

## Delinked Notifs
Order Number | Table Key | Field Name | New value | Old value
30474502 | 820000030474502 | QMNUM |  | 000101849695
30564617 | 820000030564617 | QMNUM |  | 000102310692
30590158 | 820000030590158 | QMNUM |  | 000102408949
30617747 | 820000030617747 | QMNUM | 000102988291
30617747 | 820000030617747 | QMNUM |  | 000102988291
30942894 | 820000030942894 | QMNUM |  | 000106168479
31079018 | 820000031079018 | QMNUM |  | 000108159179
31102830 | 820000031102830 | QMNUM |  | 000109234173
31165740 | 820000031165740 | QMNUM |  | 000110485716
31175108 | 820000031175108 | QMNUM |  | 000110568251
31175815 | 820000031175815 | QMNUM |  | 000110573078
31193954 | 820000031193954 | QMNUM |  | 000110770782
31197019 | 820000031197019 | QMNUM |  | 000110822896
31204517 | 820000031204517 | QMNUM |  | 000110891639
31205258 | 820000031205258 | QMNUM |  | 000111053589
31207128 | 820000031207128 | QMNUM |  | 000111104641
31207161 | 820000031207161 | QMNUM |  | 000111102535
31221652 | 820000031221652 | QMNUM |  | 000111391279
31245707 | 820000031245707 | QMNUM |  | 000111662862
31255863 | 820000031255863 | QMNUM |  | 000111767919
31262225 | 820000031262225 | QMNUM |  | 000111855703
31271222 | 820000031271222 | QMNUM |  | 000111957931
31273284 | 820000031273284 | QMNUM |  | 000111984232
31281966 | 820000031281966 | QMNUM |  | 000112134521
31281968 | 820000031281968 | QMNUM |  | 000112134523
31282765 | 820000031282765 | QMNUM |  | 000112143284
31282826 | 820000031282826 | QMNUM |  | 000112149414
31282830 | 820000031282830 | QMNUM |  | 000112149755
31285060 | 820000031285060 | QMNUM |  | 000112171180
31285061 | 820000031285061 | QMNUM |  | 000112171181
31285159 | 820000031285159 | QMNUM |  | 000112169821
31286361 | 820000031286361 | QMNUM |  | 000112191204
31286660 | 820000031286660 | QMNUM |  | 000112180702
31286706 | 820000031286706 | QMNUM |  | 000112190914
31289354 | 820000031289354 | QMNUM |  | 000112404866
31289564 | 820000031289564 | QMNUM |  | 000112407504
31290144 | 820000031290144 | QMNUM |  | 000112416508
31290146 | 820000031290146 | QMNUM |  | 000112416557
31291669 | 820000031291669 | QMNUM |  | 000112434990
31291670 | 820000031291670 | QMNUM |  | 000112435460
31291671 | 820000031291671 | QMNUM |  | 000112436787
31297666 | 820000031297666 | QMNUM |  | 000112534740
31307406 | 820000031307406 | QMNUM |  | 000112609391
31308015 | 820000031308015 | QMNUM |  | 000112640645
31308019 | 820000031308019 | QMNUM |  | 000112648194
31308790 | 820000031308790 | QMNUM |  | 000112551915
31308791 | 820000031308791 | QMNUM |  | 000112410217
31308793 | 820000031308793 | QMNUM |  | 000112409769
31312018 | 820000031312018 | QMNUM |  | 000112421980
31312019 | 820000031312019 | QMNUM |  | 000112533471
31312040 | 820000031312040 | QMNUM |  | 000112624835
31314138 | 820000031314138 | QMNUM |  | 000112421160
31314313 | 820000031314313 | QMNUM |  | 000112640449
31316185 | 820000031316185 | QMNUM |  | 000112726448
31316283 | 820000031316283 | QMNUM |  | 000112727825
31316283 | 820000031316283 | QMNUM | 000112727825
31316283 | 820000031316283 | QMNUM |  | 000112727825
31318381 | 820000031318381 | QMNUM |  | 000112682565
31318944 | 820000031318944 | QMNUM |  | 000112742262
31319443 | 820000031319443 | QMNUM |  | 000112760950
31319901 | 820000031319901 | QMNUM |  | 000112769006
31320621 | 820000031320621 | QMNUM |  | 000112779271
31323676 | 820000031323676 | QMNUM |  | 000112835205
31324095 | 820000031324095 | QMNUM |  | 000112839904
31324412 | 820000031324412 | QMNUM |  | 000112841452
31324677 | 820000031324677 | QMNUM |  | 000112846354
31325844 | 820000031325844 | QMNUM |  | 000112859784
31329860 | 820000031329860 | QMNUM |  | 000112928898
31334182 | 820000031334182 | QMNUM |  | 000112996389
31336579 | 820000031336579 | QMNUM |  | 000113038755
31340098 | 820000031340098 | QMNUM |  | 000113062127
31343120 | 820000031343120 | QMNUM |  | 000113144866
31343123 | 820000031343123 | QMNUM |  | 000113145266
31343124 | 820000031343124 | QMNUM |  | 000113145564
31343125 | 820000031343125 | QMNUM |  | 000113145836
31343236 | 820000031343236 | QMNUM |  | 000113163076
31343238 | 820000031343238 | QMNUM |  | 000113163134
31344015 | 820000031344015 | QMNUM |  | 000113163209
31350280 | 820000031350280 | QMNUM |  | 000113198746
31350562 | 820000031350562 | QMNUM |  | 000113240816
31351748 | 820000031351748 | QMNUM |  | 000113227557
31354054 | 820000031354054 | QMNUM |  | 000113227750
31354872 | 820000031354872 | QMNUM |  | 000113663476
31355773 | 820000031355773 | QMNUM |  | 000113663707
31355774 | 820000031355774 | QMNUM |  | 000113663786
31355776 | 820000031355776 | QMNUM |  | 000113664064
31355777 | 820000031355777 | QMNUM |  | 000113665277
31356031 | 820000031356031 | QMNUM |  | 000113199100
31358176 | 820000031358176 | QMNUM |  | 000113718462
31360838 | 820000031360838 | QMNUM |  | 000113725829
31360980 | 820000031360980 | QMNUM |  | 000113725868
31361320 | 820000031361320 | QMNUM |  | 000113740620
31361321 | 820000031361321 | QMNUM |  | 000113740518
31361322 | 820000031361322 | QMNUM |  | 000113740510
31361488 | 820000031361488 | QMNUM |  | 000113742411
31361625 | 820000031361625 | QMNUM |  | 000113747830
31361967 | 820000031361967 | QMNUM |  | 000113751593
31362297 | 820000031362297 | QMNUM |  | 000113718468
31362298 | 820000031362298 | QMNUM |  | 000113718541
31362346 | 820000031362346 | QMNUM |  | 000113723017
31364170 | 820000031364170 | QMNUM |  | 000113791781
31364252 | 820000031364252 | QMNUM |  | 000113779436
31364323 | 820000031364323 | QMNUM |  | 000113779806
31364941 | 820000031364941 | QMNUM |  | 000113747875
31365703 | 820000031365703 | QMNUM |  | 000113817426
31366025 | 820000031366025 | QMNUM |  | 000113821907
31367398 | 820000031367398 | QMNUM |  | 000113817897
31367399 | 820000031367399 | QMNUM |  | 000113818681
31374248 | 820000031374248 | QMNUM |  | 000114155922
31374249 | 820000031374249 | QMNUM |  | 000114224375
31377173 | 820000031377173 | QMNUM |  | 000114271062
31379155 | 820000031379155 | QMNUM |  | 000113820469
31382371 | 820000031382371 | QMNUM |  | 000114354598
31387895 | 820000031387895 | QMNUM |  | 000114482701
31391219 | 820000031391219 | QMNUM |  | 000114538011
31393978 | 820000031393978 | QMNUM |  | 000114625626
31463070 | 820000031463070 | QMNUM |  | 000113723017
31486236 | 820000031486236 | QMNUM |  | 000112609391
35001640 | 820000035001640 | QMNUM |  | 000113143575
35001641 | 820000035001641 | QMNUM |  | 000113143653
35001849 | 820000035001849 | QMNUM |  | 000113181522
35008761 | 820000035008761 | QMNUM |  | 000113219231
35008763 | 820000035008763 | QMNUM |  | 000113219238
35011745 | 820000035011745 | QMNUM |  | 000113241724
35013266 | 820000035013266 | QMNUM |  | 000113242772
35013267 | 820000035013267 | QMNUM |  | 000113243462
35015703 | 820000035015703 | QMNUM |  | 000113245749
35015705 | 820000035015705 | QMNUM |  | 000113255606
35015706 | 820000035015706 | QMNUM |  | 000113255642
35015932 | 820000035015932 | QMNUM |  | 000113246468
35015935 | 820000035015935 | QMNUM |  | 000113249064
35015936 | 820000035015936 | QMNUM |  | 000113249203
35018263 | 820000035018263 | QMNUM |  | 000113266423
35018550 | 820000035018550 | QMNUM |  | 000113248456
35018552 | 820000035018552 | QMNUM |  | 000113260310
35018561 | 820000035018561 | QMNUM |  | 000113261666
35018562 | 820000035018562 | QMNUM |  | 000113261334
35018564 | 820000035018564 | QMNUM |  | 000113263505
35018620 | 820000035018620 | QMNUM |  | 000113311784
35018632 | 820000035018632 | QMNUM |  | 000113634733
35018886 | 820000035018886 | QMNUM |  | 000113646462
35019354 | 820000035019354 | QMNUM |  | 000113723017
35019544 | 820000035019544 | QMNUM |  | 000113718468
35019545 | 820000035019545 | QMNUM |  | 000113718541
35023620 | 820000035023620 | QMNUM |  | 000114036571
35025379 | 820000035025379 | QMNUM |  | 000114231286
35026245 | 820000035026245 | QMNUM |  | 000114259452
35026420 | 820000035026420 | QMNUM |  | 000114266765
35031660 | 820000035031660 | QMNUM |  | 000114474286
35031714 | 820000035031714 | QMNUM |  | 000114496935
35039957 | 820000035039957 | QMNUM |  | 000114567769
35040016 | 820000035040016 | QMNUM |  | 000114592131
35040017 | 820000035040017 | QMNUM |  | 000114592093
35040018 | 820000035040018 | QMNUM |  | 000114592041
35042612 | 820000035042612 | QMNUM |  | 000114655579
35042631 | 820000035042631 | QMNUM |  | 000114645026
35042631 | 820000035042631 | QMNUM | 000114645026
35042631 | 820000035042631 | QMNUM |  | 000114645026
35042920 | 820000035042920 | QMNUM |  | 000114627400
35042921 | 820000035042921 | QMNUM |  | 000114627401
35042923 | 820000035042923 | QMNUM |  | 000114656547
35043245 | 820000035043245 | QMNUM |  | 000114668686
35043246 | 820000035043246 | QMNUM |  | 000114668689
35043247 | 820000035043247 | QMNUM |  | 000114668862
35043280 | 820000035043280 | QMNUM |  | 000114660964
35043304 | 820000035043304 | QMNUM |  | 000113676445
35043385 | 820000035043385 | QMNUM |  | 000114688204
35043763 | 820000035043763 | QMNUM |  | 000114701413
35043830 | 820000035043830 | QMNUM |  | 000114705149
35043949 | 820000035043949 | QMNUM |  | 000114708276
35043953 | 820000035043953 | QMNUM |  | 000114708278
35043954 | 820000035043954 | QMNUM |  | 000114708381
35043955 | 820000035043955 | QMNUM |  | 000114708383
35043956 | 820000035043956 | QMNUM |  | 000114708386
35043986 | 820000035043986 | QMNUM |  | 000114708366
35044284 | 820000035044284 | QMNUM |  | 000114691436
35045959 | 820000035045959 | QMNUM |  | 000114723712
35046726 | 820000035046726 | QMNUM |  | 000114749460
35046759 | 820000035046759 | QMNUM |  | 000114750733
35046793 | 820000035046793 | QMNUM |  | 000114754228
35046896 | 820000035046896 | QMNUM |  | 000114753320
35047143 | 820000035047143 | QMNUM |  | 000114761296
35047312 | 820000035047312 | QMNUM |  | 000114758056
35047402 | 820000035047402 | QMNUM |  | 000114754229
35047414 | 820000035047414 | QMNUM |  | 000114742450
35047418 | 820000035047418 | QMNUM |  | 000114742467
35047557 | 820000035047557 | QMNUM |  | 000114778704
35048011 | 820000035048011 | QMNUM |  | 000114791963
35048058 | 820000035048058 | QMNUM |  | 000114798646
35049913 | 820000035049913 | QMNUM |  | 000114810960
35052121 | 820000035052121 | QMNUM |  | 000114870756
35052128 | 820000035052128 | QMNUM |  | 000114832579
35052129 | 820000035052129 | QMNUM |  | 000114832575
35056666 | 820000035056666 | QMNUM |  | 000114988838
35058080 | 820000035058080 | QMNUM |  | 000114266765
35058080 | 820000035058080 | QMNUM | 000114266765
35058080 | 820000035058080 | QMNUM |  | 000114266765
35060338 | 820000035060338 | QMNUM |  | 000112143284
35060580 | 820000035060580 | QMNUM |  | 000108159179
35060585 | 820000035060585 | QMNUM |  | 000110606328
35060586 | 820000035060586 | QMNUM |  | 000111549081
35060587 | 820000035060587 | QMNUM |  | 000111934659
35060588 | 820000035060588 | QMNUM |  | 000112443046
35060893 | 820000035060893 | QMNUM |  | 000115098143
35072363 | 820000035072363 | QMNUM |  | 000113742411
35076062 | 820000035076062 | QMNUM |  | 000116579004
35081660 | 820000035081660 | QMNUM |  | 000113255642
35086100 | 820000035086100 | QMNUM |  | 000113728737
35115053 | 820000035115053 | QMNUM |  | 000117496041
35167137 | 820000035167137 | QMNUM |  | 000118729544
74004771 | 820000074004771 | QMNUM |  | 000111558040
74015668 | 820000074015668 | QMNUM |  | 000113743255
74021962 | 820000074021962 | QMNUM |  | 000114592041
74021964 | 820000074021964 | QMNUM |  | 000114266765
74022302 | 820000074022302 | QMNUM |  | 000115061014
74022381 | 820000074022381 | QMNUM |  | 000114758056
74022381 | 820000074022381 | QMNUM | 000114758056
74022381 | 820000074022381 | QMNUM |  | 000114758056
74022620 | 820000074022620 | QMNUM |  | 000113743255
80003462 | 820000080003462 | QMNUM | 000102284237
80003462 | 820000080003462 | QMNUM |  | 000102284237
80006405 | 820000080006405 | QMNUM | 000102307705
80006405 | 820000080006405 | QMNUM | 000102146759 | 000102307705
80006405 | 820000080006405 | QMNUM |  | 000102146759
80007786 | 820000080007786 | QMNUM | 000102295549
80007786 | 820000080007786 | QMNUM |  | 000102295549
80009637 | 820000080009637 | QMNUM | 000102437046
80009637 | 820000080009637 | QMNUM |  | 000102437046
80009960 | 820000080009960 | QMNUM | 000102409386
80009960 | 820000080009960 | QMNUM |  | 000102409386