## Sheet1
[74 empty] | 903466.99 | 171.1112 | 733304.76 | 138.8835
Order | Job Owner Name | Planned Construction Complete Year | Sub-Category | Order Description | Job Owner | SAP Status | Circuit Feet from Planning | UG Feet | OH Feet | Planned Conductor Feet | Planned Conductor Miles | 2020 Forecast Feet | 2020 Forecast Miles | 2021 Forecast Feet | 2021 Forecast Miles | 2022 Forecast Feet | 2022 Forecast Miles | Unallocated Forecast Miles | SAP Plan Units | SAP Plan Miles | Div | MAT | Program | Ready to Break Ground | EOD Forecast | SAP Est Out Date | Previous EOD Forecast | Prelim Dwg Forecast | Previous Prelim Dwg Forecast | Prelim Dwg Out | PEND IN Date | Estimating Comments | Estimating Team | Estimating Manager | ADE | Priority | Status | T-Line Conflict | Composite Poles | Wood Poles | Comp Poles | Expected Joint Pole Date | Joint Pole Complete | Joint Pole Coordinator | Joint Pole Notes | LCE | Land Clear Date | Previous Land Clear Date | Land Complete | ERTC Planned Date | Previous ERTC Date | ERTC Complete | Land Planner | Envrionmental Lead PGE Contact | Notes | L and ERTC Complete | Expected Permit Date | Permits Complete | Permit Expire Date | Permit Coordinator | Permitting Notes | Veg Complete | Veg Completed | Veg Start | ERTC Call Date | Veg Management | Veg Notes | MPP Resource | Contractor | Contract Ready Date | Contract Status | SAP Actual Units | SAP Actual Miles | 2019 Feet Installed | 2019 Miles Installed | 2020 Feet Installed | 2020 Miles Installed | Total Installed Miles | Remaining Planned Miles | QA Pass | QA Fix | Total QA Span Length | QA Remaining | QA Trailing Installed | IA Pass | Span Notes | Construction Notes | P6 Business Case Date | BC Complete | DS24 Status | P6 Construction Start | P6 Operative | P6 Forecast In Service | CLICK Construction Start | CLICK Construction End | CN24 Out Date | Materials Ready Date | Materials Ready | Readiness Notes | Auth Amt without Contingency (Expected Case) | Total EAC | MPP Approved Budget (2021) | Auth Amt with Contingency (High Case) | Remaining Contingency | Expected - (Actuals + Committed) | Total EAC / Expected Case | ITD Actual | Open Commitments | Total Act + Com | Credits and Reimbursements | Expected Unit Cost | Planned Num of Poles | Planning Engineer | General Comments | Scoping Status | Scoping Notes | DLT | Telecom | SCADA Specialist | SWPPP Status | FE Primary or Support | City | County | Latitude | Longitude | Schedule ID | Mainline or Tapline | Hardening Method | Rank Number | CompYR | QTR | Work Plan EOD Baseline | Construction Start Baseline | Construction Complete Baseline | Blended IDs | Project Managed | Circuit Protection Zone | Risk Assessment CPZ | County codes | In scope?
30748101 |  | 2020 | 220 Mile Plan | OCGC R7 EP ED WRO - HWY 29 - KELSEYVILLE |  | FICL |  | 0 | 17499 | 17499 | 3.3142 | 17499 | 3.3142 | 0 | 0 | 0 | 0 | 0 |  |  |  | 10L | SH | 2019-07-18 | [18 empty] | Yes | [5 empty] | Full |  |  | Full |  |  |  | Full |  | Yes |  |  |  |  | Y | [10 empty] | 0 | 0 | 17499 | 3.3142 | 3.3142 | 0 | 3.3142 | 0 | 3.3142 | 0 | 0 | 3.3142 |  |  | 2019-07-18 | Yes | N/A | 2019-10-07 | 2020-04-22 | 2020-04-30 17:00 |  |  | 2020-06-08 |  | Yes | Shovel Ready | 2414558.4 | 1004393.6 |  | 5340502 | 2925943.6 | -1113416.6 | 41.59% | 3498527.7 | 29447.3 | 3527975 | -3348795 | 303057.2152 | [12 empty] | 0 | 0 |  |  |  |  | 2020 | [5 empty] | Y |  |  | LAKE COUNTY | Yes
30962842 |  |  |  | REM OH FAC -408 MILL RD. FEATHER FA |  | FICL |  | 0 | 7000 | 7000 | 1.3258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2AF | [51 empty] | 7000 | 1.3258 | 0 | 0 | 1.3258 | 0 | 1.3258 | 0 | 1.3258 | 0 | 0 | 1.3258 |  |  |  |  | N/A | [5 empty] | 2019-06-06 | [25 empty] | Feather Falls | Butte | 39.3567 | -121.1428 | [13 empty] | BUTTE COUNTY | Yes
31048050 |  |  |  | STS-OFAC_IDLE_REMV-WENTWORTH SPRINGS |  | CLSD |  | 0 | 1185 | 1185 | 0.22443 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2AF | [51 empty] | 1185 | 0.22443 | 0 | 0 | 0.22443 | 0 | 0.22443 | 0 | 0.22443 | 0 | 0 | 0.22443 |  |  |  |  | N/A | [5 empty] | 2018-06-16 | [27 empty] | 38.9288 | -120.77 | [13 empty] | EL DORADO COUNTY | Yes
31048480 |  |  |  | STS-POLE_IDLE_REMV-S/O 21604 DONNER P |  | CLSD |  | 0 | 230 | 230 | 0.043561 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2AF | [51 empty] | 230 | 0.043561 | 0 | 0 | 0.043561 | 0 | 0.043561 | 0 | 0.043561 | 0 | 0 | 0.043561 |  |  |  |  | N/A | [5 empty] | 2018-06-07 | [27 empty] | 39.3233 | -120.3816 | [13 empty] | PLACER COUNTY | Yes
31081464 |  |  |  | STS-REMV IDLE FAC 8110 DICK COOK RD |  | CLSD |  | 0 | 819 | 819 | 0.15511 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2AF | [51 empty] | 819 | 0.15511 | 0 | 0 | 0.15511 | 0 | 0.15511 | 0 | 0.15511 | 0 | 0 | 0.15511 |  |  |  |  | N/A | [5 empty] | 2018-03-24 | [27 empty] | 38.7924 | -121.1522 | [13 empty] | PLACER COUNTY | Yes
31082393 |  |  |  | RECON THREE SPANS CHERRY RIDGE RD |  | DOCC | 686.4 | 0 | 1345 | 1345 | 0.25473 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SO | 08W | SH | 2019-03-15 17:00 | 2019-02-21 |  | 2019-02-21 |  |  | Yes | 2019-02-21 | [6 empty] | No | 15/50 | 50 | 15 | [7 empty] | Full |  |  | Full |  |  | Need laydown | Full |  |  |  |  | Annual see long text 3/12 | 1980-01-01 | Y | [10 empty] | 1345 | 0.25473 | 0 | 0 | 0.25473 | 0 | 0.25473 | 0 | 0.25473 | 0 | 4.3063e-17 | 0.25473 |  |  | 2019-03-15 17:00 |  | N/A | 2019-08-05 | 2019-08-06 | 2019-08-06 |  |  | 2019-08-06 |  |  |  | 635752 | 610646 |  | 635752 | 0 | 25106 | 96.05% | 610646 | 0 | 610646 | -366 | 2397182.8104 | 8 | [9 empty] | Sebastopol | Sonoma | 38.4061 | -122.8917 | 31082393 |  |  |  | 2019 | Q2 |  |  |  |  | Y | MOLINO 1102178 | 321 | SONOMA COUNTY | Yes
31088475 |  |  |  | CCM REM IDLE LINE^ 17171 SFD BVD INVERV |  | CLSD |  | 0 | 3673 | 3673 | 0.69564 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2AF | [51 empty] | 3673 | 0.69564 | 0 | 0 | 0.69564 | 0 | 0.69564 | 0 | 0.69564 | 0 | 0 | 0.69564 |  |  |  |  | N/A | [5 empty] | 2018-08-29 | [27 empty] | 38.0493 | -122.5592 | [13 empty] | MARIN COUNTY | Yes
31098626 |  | 2020 | 220 Mile Plan | CLARKSVILLE 2104 RECONDUCTOR -PH 3 Y2018 |  | MAPP | 3400 | 0 | 8038 | 8038 | 1.5223 | 8038 | 1.5223 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | SH | 2018-07-03 | [6 empty] | 2018-06-24 | [11 empty] | Yes |  |  |  | 2018-05-16 | 2018-05-16 | Full | 2018-05-03 | 2018-05-03 | Full |  |  |  | Full |  | Yes |  |  |  |  | Y | [10 empty] | 0 | 0 | 8038 | 1.5223 | 1.5223 | -1.7225e-16 | 1.525 | 0 | 1.525 | 0 | -0.0026515 | 1.525 |  | Keep | 2018-07-03 | Yes | COMP | 2018-07-16 | 2020-06-26 | 2021-03-05 17:00 |  |  | 2020-11-10 |  | Yes | Shovel Ready | 1301220 | 1209799.7 |  | 1543425 | 242205 | 781615.1 | 92.97% | 519604.9 | 0 | 519604.9 | -32478 | 794693.0102 | [10 empty] | El Dorado Hills | El Dorado | 38.6997 | -121.0284 | P.11129 |  |  |  | 2020 | Q3 |  |  |  |  | Y | CLARKSVILLE 210413352 | 274 | EL DORADO COUNTY | Yes
31102666 |  |  |  | REMV IDLE FAC 6 LOCS WO C/O5095 NAP+++++ |  | CONS |  | 0 | 1245 | 1245 | 0.2358 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2AF | [51 empty] | 1245 | 0.2358 | 0 | 0 | 0.2358 | 0 | 0.2358 | 0 | 0.2358 | 0 | 0 | 0.2358 |  |  |  |  | N/A |  |  |  | 2021-02-19 07:08 | 2021-02-19 10:46 | [26 empty] | Napa | Napa | 38.2542 | -122.3808 | [13 empty] | NAPA COUNTY | Yes
31153500 |  |  |  | STS-COND_IDLE_REMV-27534 GRANDVIEW |  | CLSD |  | 0 | 1365 | 1365 | 0.25852 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2AF |  |  |  | 2018-11-26 | [47 empty] | 1365 | 0.25852 | 0 | 0 | 0.25852 | 0 | 0.25852 | 0 | 0.25852 | 0 | 0 | 0.25852 |  |  |  |  | N/A | [5 empty] | 2019-05-29 | [25 empty] | Hayward | Alameda | 37.6511 | -122.0462 | [13 empty] | ALAMEDA COUNTY | Yes
31159701 |  |  |  | +TRAN_IDLE_REMV-KLAU MINE RD |  | CLSD |  | 0 | 710 | 710 | 0.13447 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2AF |  |  |  | 2019-06-19 | [47 empty] | 710 | 0.13447 | 0 | 0 | 0.13447 | 0 | 0.13447 | 0 | 0.13447 | 0 | 0 | 0.13447 |  |  |  |  | N/A | [5 empty] | 2019-05-28 | [27 empty] | 35.6253 | 120.6945 | [13 empty] | San Luis Obispo County | Yes
31159702 |  |  |  | TRAN_IDLE_REMV-CHIMNEY ROCK RD |  | CLSD |  | 0 | 380 | 380 | 0.07197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2AF |  |  |  | 2019-06-19 | [47 empty] | 380 | 0.07197 | 0 | 0 | 0.07197 | 0 | 0.07197 | 0 | 0.07197 | 0 | 0 | 0.07197 |  |  |  |  | N/A | [5 empty] | 2019-05-07 | [27 empty] | 35.659 | 120.9226 | [13 empty] | San Luis Obispo County | Yes
31207090 |  | 2020 | 220 Mile Plan | MVWF VIEWPOINT RD TENNVLY CNTY ALTO 1125 |  | DOCC | 6861 | 0 | 9487 | 9487 | 1.7968 | 9487 | 1.7968 | 0 | 0 | 0 | 0 | 0 |  |  | NB | 08W | SH | 2019-06-13 | 2019-06-13 |  | 2019-06-13 |  |  | Yes | 2019-06-13 |  | SANTA ROSA |  |  |  | 100 | No |  |  |  |  | Yes | [5 empty] | Full |  |  | Full |  |  | Need plans - No land constraints at high level review | Full |  | Yes |  |  | Expires 9/13/19 | 1980-01-01 | Y | [10 empty] | 0 | 0 | 9487 | 1.7968 | 1.7968 | 3.1006e-15 | 1.7968 | 0 | 1.7968 | 0 | -3.1006e-15 | 1.7968 |  | Keep |  | Yes | N/A | [5 empty] | 2020-05-08 |  | Yes | Shovel Ready | 3466319 | 1961880 |  | 3466319 | 0 | 3352546.6 | 56.59% | 113772.4 | 0 | 113772.4 | 0 | 1091886.413 | 50 | [9 empty] | Mill Valley | Marin | 0 | 0 | P.11104 |  |  |  | 2020 | Q2 | 2019-06-07 | 2020-04-15 | 2020-06-28 |  | Y | ALTO 1125935 | 634 | MARIN COUNTY | Yes
31209950 |  |  |  | R7 RECON POTTER VLY 1105 ( VAN ARSDALE) |  | DOCC | 3000 | 0 | 3008 | 3008 | 0.5697 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2019-06-11 | 2019-04-19 | 2019-03-17 | 2019-04-19 |  |  | Yes | 2019-04-19 | 1/14: Job moved back to ESTS to update per standard - Updated submittal for 1/181/23: Job has been resubmitted - waiting for 1st review. [REDACTED]1/28: Resubmitted for ADE review 1/182/3 & 2/11: Pending ADE -ReReview [REDACTED] asked for update on 1/30.2/11: 1st Corrections sent back2/13/4: 2nd ADE submittal and recieved feedback from ADE. Additional poles may need to be added due to 200' interset poles2/18: Pending if additional work is necessary2/20: Scope changed. Pending Easements and Land to move forward2/25: 2nd review on track to be submitted on 2/272/27: follow up with LAND to see if easment is need for interset pole - follow up next week3/4: Pending response from LAND3/6: Land confirmed. QUES in process of fielding3/11: Onsite today, should have by 3/153/13: pending 2nd Submittal shoul be on 3/153/20: 2nd submittal on 3/223/21: 2nd ADE submittal3/27: waiting second corrections4/3: waiting second corrections4/8: Minor corrections and EDRS for approval when complete - [REDACTED]4/11: from ADE Change was not made to joint pole intent for location 23, Also it appears FAA process was not completed for the new interset poles4/17: APPR Status | QUES |  |  | Completed | COMPLETED | No |  | 0 | 0 | [7 empty] | Full |  |  | Full |  |  | Bald Eagel - Need laydown yard location, equipment to be used and durations. If construction will start after August then environmental can be released. | Full |  |  |  |  | Annual | 1980-01-01 | Y | [10 empty] | 3008 | 0.5697 | 0 | 0 | 0.5697 | 0 | 0.5697 | 0 | 0.5697 | 0 | 0 | 0.5697 |  |  | 2019-06-11 |  | N/A | 2019-08-19 | 2019-08-22 | 2019-08-22 | [6 empty] | 1031917.9 | 1474193.4 |  | 273660 | -758257.9 | -442275.5 | 142.9% | 1474193.4 | 0 | 1474193.4 | -71537 | 2587679.9043 | 13 | [9 empty] | Potter Valley | Mendocino | 39.3808 | -123.1149 | P.11913 |  |  |  | 2019 | Q3 |  |  |  |  | Y | POTTER VALLEY P H 110576498 | 2098 | MENDOCINO COUNTY | Yes
31215474 |  |  |  | RECONDUCTOR ROB ROY 2104-MCDONALD RD |  | CLSD | 2719 | 0 | 2719 | 2719 | 0.51496 | 26.2 | 0.0049621 | 0 | 0 | 0 | 0 | 6.7286e-19 |  |  | CC | 08W | SH | 2019-02-08 | 2019-02-08 |  | 2019-02-08 |  |  | Yes | 2019-02-08 | [6 empty] | No | [10 empty] | Full |  |  | Full |  |  | In Construction, ERTC issued | Full |  |  |  |  | Annual permit uploaded 2/22 | 1980-01-01 | Y | [10 empty] | 2692.8 | 0.51 | 0 | 0 | 0.51 | 0.0049621 | 0.51496 | 0 | 0.51496 | 0 | -0.0049621 | 0.51496 |  |  |  |  | N/A | [5 empty] | 2019-05-16 | [15 empty] | 19 | [9 empty] | Aptos | Santa Cruz | 36.9875 | -121.8608 | P.11413 |  |  |  | 2019 | Q2 |  |  |  |  | Y | ROB ROY 210410954 | 1532 | SANTA CRUZ COUNTY | Yes
31232280 |  |  |  | ZACA 1102 LONG CYN RD, SANTA YNEZ |  | FICL | 5851 | 0 | 5851 | 5851 | 1.1081 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | LP | 08W | SH | 2019-05-22 | 2019-04-01 |  | 2019-04-01 |  |  | Yes | 2019-04-01 | [6 empty] | No | [10 empty] | Full |  |  | Full |  |  | ERTC released | Full | [5 empty] | 1980-01-01 | Y | [10 empty] | 5851 | 1.1081 | 0 | 0 | 1.1081 | 0 | 1.1081 | 0 | 1.1081 | 0 | 0 | 1.1081 |  |  | 2019-05-22 |  | N/A | 2019-05-23 08:00 | 2019-06-30 17:00 | 2019-06-30 17:00 |  |  | 2019-08-06 | [15 empty] | 24 | [9 empty] | Santa Ynez | Santa Barbara | 34.6544 | -120.074 | P.11690 |  |  |  | 2019 | Q2 | [5 empty] | ZACA 1102Y54 | 1154 | SANTA BARBARA COUNTY | Yes
31248532 |  | 2020 | 220 Mile Plan | CWSP HALF MOON BAY 1101 LS CO4063 |  | FICL | 1900 | 0 | 3896 | 3896 | 0.73788 | 3896 | 0.73788 | 0 | 0 | 0 | 0 | 0 |  |  | PN | 08W | SH | 2020-06-05 08:00 | 2019-07-09 | 2019-07-09 | 2019-07-09 |  |  | Yes | 2019-07-09 | 4/17 Corrections sent to QUES5/1: job being refielded. Next submittal 5/105/8: added additional locaitons + refield - next submittal will be 5/105/15: job had to be refielded again. Waiting on PE Stamps. Sent in by 5/175/21: submitted for 2nd submittal5/29: waiting for 2nd corrections - ADE pulled for B-Tags5/31: [REDACTED] on vacation. [REDACTED] to take on review6/5: waiting for 2nd corrections. [REDACTED] back from vacation6/7: [REDACTED] sent a note for renumbering alignment issue6/12: QUES to follow with [REDACTED] and provide update6/18: 2nd submittal sent6/26: waiting for corrections back7/3: 3rd submittal sent7/9: Approved and in PEND | QUES |  |  | Completed | COMPLETED | No |  | 0 | 0 |  | Yes |  |  |  | 2020-04-06 | 2020-04-06 | Full | 2020-04-06 | 2020-04-06 | Full |  |  | Coastal exemption process applies as per San Mateo County on 2/11/2020 - waiting for confirmation of Caltrans permit extension | Full | 2020-03-31 | Yes |  |  | Waiting on ERTC | 2020-07-17 | Y | 2020-06-01 | [9 empty] | 0 | 0 | 3896 | 0.73788 | 0.73788 | 0 | 0.73788 | 0 | 0.73788 | 0 | 0 | 0.73788 |  | Keep | 2020-06-05 08:00 | Yes | COMP | 2020-06-22 | 2020-08-06 | 2020-08-06 |  |  | 2020-08-06 |  | Yes | Shovel Ready | 1840346.3 | 2488010.4 |  | 2610184 | 769837.7 | 1793821.1 | 135.2% | 46525.2 | 0 | 46525.2 | 0 | 3371841.6099 | 17 | [9 empty] | Half Moon Bay | San Mateo | 37.4891 | -122.3917 | P.12008.01 |  |  | 2020-086 | 2020 | Q3 | 2019-07-09 | 2022-01-19 |  |  | Y | HALF MOON BAY 11018902 | 1203 | SAN MATEO COUNTY | Yes
31252335 |  |  |  | 0611POLE_IDLE_REMV-12398 SHALE RIDGE LN |  | CLSD |  | 0 | 499 | 499 | 0.094508 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2AF | [51 empty] | 499 | 0.094508 | 0 | 0 | 0.094508 | 0 | 0.094508 | 0 | 0.094508 | 0 | 0 | 0.094508 |  |  |  |  | N/A | [5 empty] | 2017-08-11 | [25 empty] | Auburn | Placer | 38.953 | -121.0896 | [13 empty] | PLACER COUNTY | Yes
31254545 |  |  |  | POLE_IDLE_REMV-SEWER TREATMENT PLANT |  | CLSD |  | 0 | 857 | 857 | 0.16231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2AF | [51 empty] | 857 | 0.16231 | 0 | 0 | 0.16231 | 0 | 0.16231 | 0 | 0.16231 | 0 | 0 | 0.16231 |  |  |  |  | N/A | [5 empty] | 2018-06-28 | [27 empty] | 40.649 | -122.6135 | [13 empty] | SHASTA COUNTY | Yes
31254690 |  |  |  | CCM COND_IDLE_REMV+-3640 HWY 128 |  | CLSD |  | 0 | 300 | 300 | 0.056818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2AF | [51 empty] | 300 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0.056818 | 0 | 0.056818 | 0 | 0 | 0.056818 |  |  |  |  | N/A | [5 empty] | 2018-04-04 | [27 empty] | 38.6063 | -122.6299 | [13 empty] | NAPA COUNTY | Yes
31254945 |  |  |  | 4/30/18 REMV IF -750 CHILENO VALLEY*OCLH |  | CLSD |  | 0 | 270 | 270 | 0.051136 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2AF | [51 empty] | 270 | 0.051136 | 0 | 0 | 0.051136 | 0 | 0.051136 | 0 | 0.051136 | 0 | 0 | 0.051136 |  |  |  |  | N/A | [5 empty] | 2018-04-02 | [25 empty] | Petaluma | Sonoma | 38.2092 | -122.6767 | [13 empty] | SONOMA COUNTY | Yes
31257161 |  |  |  | STS-POLE_IDLE_REMV-R/O 7652 WARREN RD |  | CLSD |  | 0 | 490 | 490 | 0.092803 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2AF |  |  |  | 2019-03-12 | [47 empty] | 490 | 0.092803 | 0 | 0 | 0.092803 | 0 | 0.092803 | 0 | 0.092803 | 0 | 0 | 0.092803 |  |  |  |  | N/A | [5 empty] | 2019-09-06 | [27 empty] | 38.1373 | -120.9225 | [13 empty] | CALAVERAS COUNTY | Yes
31269259 |  |  |  | ZACA 1101 FOXEN CYN RD, LOS OLIVOS |  | FICL | 6336 | 0 | 6386 | 6386 | 1.2095 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | LP | 08W | SH | 2019-06-20 17:00 | 2019-04-01 |  | 2019-04-01 |  |  | Yes | 2019-04-01 | [6 empty] | No | [10 empty] | Full |  |  | Full |  |  | ERTC released | Full |  | Yes |  |  |  | 1980-01-01 | Y | [10 empty] | 6386 | 1.2095 | 0 | 0 | 1.2095 | 0 | 1.2095 | 0 | 1.2095 | 0 | 0 | 1.2095 |  |  | 2019-06-20 17:00 |  | N/A | 2019-03-11 08:00 | 2019-09-26 | 2019-09-26 17:00 |  |  | 2019-08-08 | [15 empty] | 22 | [9 empty] | Los Olivos | Santa Barbara | 34.6997 | -120.1495 | P.11693 |  |  |  | 2019 | Q2 | [5 empty] | ZACA 1101CB | 2754 | SANTA BARBARA COUNTY | Yes
31275658 |  |  |  | R7 DUNBAR 1102 RECOND OH BEYOND CO 1285 |  | DOCC | 1700 | 0 | 2580 | 2580 | 0.48864 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SO | 08W | SH | 2019-09-27 | 2019-02-28 |  | 2019-02-28 |  |  | Yes | 2019-02-28 | [6 empty] | No | [10 empty] | Full |  |  | Full |  |  | Need laydown. | Full |  | Yes |  |  | Private property. No tasks are activated. | 1980-01-01 | Y | [10 empty] | 2580 | 0.48864 | 0 | 0 | 0.48864 | 0 | 0.48864 | 0 | 0.48864 | 0 | 0 | 0.48864 |  |  | 2019-09-27 |  | N/A | 2019-08-06 | 2019-08-30 | 2019-08-30 |  |  | 2019-08-30 |  |  |  | 775316.6 | 882312.4 |  | 1092540 | 317223.4 | -106995.8 | 113.8% | 882312.4 | 0 | 882312.4 | -1494 | 1805662.586 | 11 | [9 empty] | Sonoma | Sonoma | 38.3327 | -122.5266 | 31275658 |  |  |  | 2019 | Q2 |  |  |  |  | Y | DUNBAR 11021285 | 449 | SONOMA COUNTY | Yes
31278200 |  |  |  | +OCEANO 1102 S HALCYON & PINE RDGE |  | CLSD | 2081 | 0 | 2081 | 2081 | 0.39413 | 21.8 | 0.0041288 | 0 | 0 | 0 | 0 | 0 |  |  | LP | 08W | SH | 2019-02-08 | 2019-02-08 |  | 2019-02-08 |  |  | Yes | 2019-02-08 | 2/3: Approved on 1/17 | QUES |  |  | Completed | COMPLETED | No |  | 0 | 0 | [7 empty] | Full |  |  | Full |  |  |  | Full |  | Yes |  |  |  | 1980-01-01 | Y | [10 empty] | 2059.2 | 0.39 | 0 | 0 | 0.39 | 0.0041288 | 0.39 | 0 | 0.39 | 0 | 0 | 0.39 |  |  |  |  | N/A | [5 empty] | 2019-03-21 | [15 empty] | 12 | [9 empty] | Arroyo Grande | San Luis Obispo | 35.0696 | -120.5679 | P.11685 |  |  |  | 2019 | Q2 |  |  |  |  | Y | OCEANO 1102V56 | 1779 | San Luis Obispo County | Yes
31286573 |  |  |  | APPLE HILL 2102 HIGH SPLICE AREA |  | CLSD | 3700 | 0 | 3492 | 3492 | 0.66136 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | SH | 2019-01-30 | 2019-01-30 |  | 2019-01-30 |  |  | Yes | 2019-01-30 | 1/30: job was approved and EDRS | QUES |  |  | Completed | COMPLETED | No |  | 0 | 0 | [7 empty] | Full |  |  | Full |  |  |  | Full |  | Yes |  |  |  | 1980-01-01 | Y | [10 empty] | 3492 | 0.66136 | 0 | 0 | 0.66136 | 0 | 0.66136 | 0 | 0.66136 | 0 | 0 | 0.66136 |  |  |  |  | N/A | [5 empty] | 2019-05-06 | [15 empty] | 14 | [9 empty] | Somerset | El Dorado | 0 | 0 | 31286573 |  |  |  | 2019 | Q2 |  |  |  |  | Y | APPLE HILL 2102186912 | 1461 | EL DORADO COUNTY | Yes
31289238 |  |  |  | FRUITLAND 1142 INS TREE WIRE LR 6064 |  | DOCC | 6200 | 0 | 6271 | 6271 | 1.1877 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2019-03-13 | 2019-03-13 | 2019-04-14 | 2019-03-13 |  |  | Yes | 2019-03-13 | 3/11: Pending review of the Ocalc stamp | EEI |  |  | Completed | COMPLETED | No |  | 0 | 0 | [7 empty] | Full |  |  | Full |  |  | need future ERTC call | Full |  | Yes |  |  | Annual | 1980-01-01 | Y | [10 empty] | 6271 | 1.1877 | 0 | 0 | 1.1877 | 0 | 1.1877 | 0 | 1.1877 | 0 | 0 | 1.1877 |  |  | 2018-06-12 08:00 |  | N/A | 2019-07-15 | 2019-07-26 | 2019-07-26 |  |  | 2019-07-26 |  |  |  | 2031468.9 | 2317373 |  | 2725374 | 693905.1 | -285904.1 | 114.1% | 2317373 | 0 | 2317373 | -212189 | 1951160.8101 | 27 | [9 empty] | Myers Flat | Humboldt | 40.2734 | -123.7722 | P.11908 |  |  |  | 2019 | Q2 |  |  |  |  | Y | FRUITLAND 11426064 | 786 | HUMBOLDT COUNTY | Yes
31290145 |  |  |  | R7 SAN RAFAEL 1107 COND REPLACEMENT |  | FICL | 370 | 0 | 801 | 801 | 0.1517 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NB | 08W | SH | 2019-04-19 | 2019-02-26 |  | 2019-02-26 |  |  | Yes | 2019-02-26 | [6 empty] | No | [10 empty] | Full |  |  | Full |  |  | Need laydown | Full |  | Yes |  |  | Extended on 3/20/19 | 1980-01-01 | Y | [10 empty] | 801 | 0.1517 | 0 | 0 | 0.1517 | 0 | 0.1517 | 0 | 0.1517 | 0 | 0 | 0.1517 |  |  | 2019-04-19 |  | N/A | 2019-08-07 | 2019-08-12 | 2019-08-12 |  |  | 2019-08-12 |  |  |  | 312207 | 387553.9 |  | 848080 | 535873 | -75346.9 | 124.1% | 387553.9 | 0 | 387553.9 | 0 | 2554662.412 | 6 | [9 empty] | Greenbrae | Marin | 37.9468 | -122.5599 | 31290145 |  |  |  | 2019 | Q2 |  |  |  |  | Y | SAN RAFAEL 11071166 | 818 | MARIN COUNTY | Yes
31290147 |  |  |  | OCCCR7 OLEMA 1101 REPLACE COND VISION RD |  | DOCC | 3280 | 0 | 3174 | 3174 | 0.60114 | 0 | 0 | 0 | 0 | 0 | 0 | -8.6126e-17 |  |  | NB | 08W | SH | 2019-02-20 | 2019-02-20 |  | 2019-02-20 |  |  | Yes | 2019-02-20 | [6 empty] | No | [10 empty] | Full |  |  | Full |  |  | Coastal Commission / No Heli work before August | Full |  | Yes |  |  | Not a county maintainted road | 1980-01-01 | Y | [10 empty] | 3174 | 0.60114 | 0 | 0 | 0.60114 | -8.6126e-17 | 0.60114 | 0 | 0.60114 | 0 | 8.6126e-17 | 0.60114 |  |  |  |  | N/A | [5 empty] | 2019-09-20 |  |  |  | 1017323 | 771996.8 |  | 1563621 | 546298 | 245326.2 | 75.88% | 771996.8 | 0 | 771996.8 | 0 | 1284229.0813 | 14 | [9 empty] | Inverness | Marin | 38.0994 | -122.8752 | P.11781 |  |  |  | 2019 | Q3 |  |  |  |  | Y | OLEMA 110150396 | 357 | MARIN COUNTY | Yes
31291071 |  |  |  | OCGC 14043533 WRO - HWY 175 MIDDLETOWN |  | FICL |  | 0 | 6583 | 6583 | 1.2468 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 10J |  | 2019-03-28 | [49 empty] | 6583 | 1.2468 | 0 | 0 | 1.2468 | 0 | 1.2468 | 0 | 1.2468 | 0 | 0 | 1.2468 |  |  | 2019-03-28 |  | N/A | 2019-05-31 08:00 | 2019-09-16 | 2019-09-16 |  |  | 2019-09-16 |  |  |  | 2011886.5 | 1792154.2 |  | 2347862.6 | 335976.1 | -116640.7 | 89.07% | 2128527.2 | 0 | 2128527.2 | -1278080 | 1437425.8204 | [12 empty] | 39.5848 | -123.4602 |  |  |  |  | 2019 | [5 empty] | Y |  |  | LAKE COUNTY | Yes
31297994 |  |  |  | 12/31/18-T2-PLE_IDL_REM-1E/O 16N/O C/O P |  | CLSD |  | 0 | 895 | 895 | 0.16951 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2AF | [51 empty] | 895 | 0.16951 | 0 | 0 | 0.16951 | 0 | 0.16951 | 0 | 0.16951 | 0 | 0 | 0.16951 |  |  |  |  | N/A | [5 empty] | 2018-10-02 | [27 empty] | 41.3249 | -123.5155 | [13 empty] | HUMBOLDT COUNTY | Yes
31298793 |  |  |  | OFAC_IDLE_REMV - 2 S/O 5 W/O 5245 HWY 49 |  | CLSD |  | 0 | 285 | 285 | 0.053977 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2AF | [51 empty] | 285 | 0.053977 | 0 | 0 | 0.053977 | 0 | 0.053977 | 0 | 0.053977 | 0 | 0 | 0.053977 |  |  |  |  | N/A | [5 empty] | 2018-08-22 | [25 empty] | Auburn | Placer | 38.9816 | -121.1133 | [13 empty] | PLACER COUNTY | Yes
31319444 |  |  |  | RECON 5-SPANS PORTER CRK RD-RINCON 1103 |  | FICL | 1100 | 0 | 1284 | 1284 | 0.24318 | 5 | 0.00094697 | 0 | 0 | 0 | 0 | 0 |  |  | SO | 08W | SH | 2019-02-19 | 2019-02-19 |  | 2019-02-19 |  |  | Yes | 2019-02-19 | 2/20: Approved | QUES |  |  | Completed | COMPLETED | No |  | 0 | 0 | [7 empty] | Full |  |  | Full |  |  | Need laydown | Full |  | Yes |  |  | Using Annual | 1980-01-01 | Y | [10 empty] | 1279 | 0.24223 | 0 | 0 | 0.24223 | 0.00094697 | 0.24223 | 0 | 0.24223 | 0 | 0 | 0.24223 |  |  |  |  | N/A | [5 empty] | 2019-12-14 |  |  |  | 3500000 | 629043.4 |  | 3500000 | 0 | 2870956.6 | 17.97% | 629043.4 | 0 | 629043.4 | 0 | 2586720.5234 | 6 | [9 empty] | Santa Rosa | Sonoma | 38.5541 | -122.6551 | 31319444 |  |  |  | 2019 | Q3 |  |  |  |  | Y | RINCON 11035152 | 440 | SONOMA COUNTY | Yes
31326034 |  |  |  | STS-POLE_IDLE_REMV - 27218 FAIRVIEW AVE |  | CLSD |  | 0 | 134 | 134 | 0.025379 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2AF | [51 empty] | 134 | 0.025379 | 0 | 0 | 0.025379 | 0 | 0.025379 | 0 | 0.025379 | 0 | 0 | 0.025379 |  |  |  |  | N/A | [5 empty] | 2019-04-24 | [27 empty] | 37.6665 | -122.0274 | [13 empty] | ALAMEDA COUNTY | Yes
31326119 |  |  |  | WEIMAR 1101 - NATURE'S WAY RECONDUCTOR |  | CLSD | 2813 | 0 | 2990 | 2990 | 0.56629 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | SH | 2019-06-24 | 2019-06-24 | 2019-04-11 | 2019-06-24 |  |  | Yes | 2019-06-24 | 4/8: Still Pending response from transmission - QUES to send a follow up email cc'ing myself and [REDACTED]. [REDACTED] to follow up with Transmission4/17 - 5/1: still waiting for transmission5/8: On Hold - Transmission underbuild5/21: submitted for 1st ADE for review5/29: waiting for 1st corrections - ADE was pulled to review B-Tags5/30: Need review from [REDACTED] by 6/6 to try and make EOD of 6/146/4: Are preliminary drawings good to go? Or should we wait for transmission response6/5: waiting on 1st corrections, corrections should be completd by 6/76/11: 1st corrections sent6/12: QUES needs clarification between engineer and ADE - pushed EOD to 6/216/18: EDRS routed6/24: APPROVED | QUES |  |  | Completed | COMPLETED | Yes |  | 0 | 0 | [7 empty] | Full |  |  | Full |  |  | Need laydown. Updated estimation being reviewed | Full |  | Yes |  |  | Private - Ray to note in SAP | 1980-01-01 | Y | [10 empty] | 2990 | 0.56629 | 0 | 0 | 0.56629 | 0 | 0.56629 | 0 | 0.56629 | 0 | 0 | 0.56629 |  |  |  |  | N/A | [5 empty] | 2019-11-15 | [15 empty] | 17 | [9 empty] | Colfax | Placer | 39.0375 | -120.9882 | P.11895 |  |  |  | 2019 | Q4 |  |  |  |  | Y | WEIMAR 1101CB | 1889 | PLACER COUNTY | Yes
31334292 |  |  |  | RECON 9-SPANS, AUSTIN CREEK RD |  | CLSD | 2550 | 0 | 2513 | 2513 | 0.47595 | 20 | 0.0037879 | 0 | 0 | 0 | 0 | 0 |  |  | SO | 08W | SH | 2019-02-25 | 2019-02-25 |  | 2019-02-25 |  |  | Yes | 2019-02-25 | [6 empty] | No | [10 empty] | Full |  |  | Full |  |  | Need laydown | Full |  | Yes |  |  | Annual | 1980-01-01 | Y | [10 empty] | 2493 | 0.47216 | 0 | 0 | 0.47216 | 0.0037879 | 0.47216 | 0 | 0.47216 | 0 | 0 | 0.47216 |  |  |  |  | N/A | [5 empty] | 2019-09-20 | [15 empty] | 13 | [9 empty] | Cazadero | Sonoma | 38.49 | -123.0599 | 31334292 |  |  |  | 2019 | Q3 |  |  |  |  | Y | MONTE RIO 111123916 | 312 | SONOMA COUNTY | Yes
31343500 |  | 2020 | 220 Mile Plan | CWSP ORINDA 401 HIGH SPLICE COUNT |  | FICL | 8023 | 0 | 7959 | 7959 | 1.5074 | 7959 | 1.5074 | 0 | 0 | 0 | 0 | 0 |  |  | DI | 08W | SH | 2020-03-31 | 2019-12-16 | 2019-12-16 | 2019-12-16 |  |  | Yes | 2019-12-16 | 12/11: Can EDRS meet 12/12 EOD?12/05 EEI submitted for 6th ADE Rvw - ADE rtn 6th corrections to contractor (change top/side tiers per UB Td-015195-B001) - EEI submitted changes - ADE approved for EDRS12/04: EEI submitted for 5th ADE rvw - ADE rtn 5th corrections to contractor12/02: On Track for 4th sub11/27: EOD pushed to apply corrections and route11/23: ADE rtn 4th corrections to contractor11/20: EOD pushed 1 wk - EEI to update on progress11/13: Push 1wk - Finalize review and processing EDRS11/12: EEI submitted for 4th ADE rvw11/08: ADE returned 3rd corrections to contractor11/07: EEI submitted for 3rd ADE rvw11/06: Contractor working with ADE on clarifying information, Voltage drops/updates11/01: ADE returned corrections to Contractor10/30: In rvw with [REDACTED]10/29: EEI submitted for 2nd ADE rvw [PRELIM DWG ready]10/23: On track (EOW)10/18: ADE rtn 1st corrections to contractor10/16: Check with ADE - ADE finalizing other projects10/09: ADE on target for 1st review completion (finding alot of errors)10/04: Rvw initiated - EEI uploaded revised OCalcs per ADE request10/02: In review9/26: ADE assigned [REDACTED] (2nd rvw set at 2wks)9/23: Scope update submitted for ADE rvw; Change order approved9/18: Additional Change Order [B] in process9/11 - 9/18: On Target for 1st submittal 9/23--> [RCC Issue]9/04: Missing Scope in change - Change Order [A] to be submitted by EEI - On Track for 9/238/22: NTP issued - EEI Est target completion date set at 9/237/29: Scope change initiated*Original ADE for pre-redesign - [REDACTED]5/2: APPROVED | EEI |  |  | Completed | COMPLETED | No |  | 0 | 0 |  | Yes | [5 empty] | Full |  |  | Full |  |  | Scope change due to veg conflicts - needs to be reestimated. 7/23 | Full |  | Yes |  |  | Received 7/11 | 1980-01-01 | Y | [10 empty] | 0 | 0 | 7959 | 1.5074 | 1.5074 | 0 | 1.5074 | 0 | 1.5074 | 0 | 0 | 1.5074 |  | Keep | 2020-03-31 | Yes | COMP | 2020-02-24 08:00 | 2020-05-13 | 2020-05-13 |  |  | 2020-05-13 |  | Yes | Shovel Ready | 2998329.3 | 3365479.5 |  | 4611914 | 1613584.7 | 2939840.7 | 112.2% | 55488.6 | 3000 | 58488.6 | 0 | 2232658.8466 | 77 | [9 empty] | Orinda | Contra Costa | 37.8861 | -122.1985 | 31343500 |  |  |  | 2020 | Q1 | 2019-12-16 | 2020-02-17 | 2020-05-17 |  | Y | ORINDA 0401N545R | 1632 | CONTRA COSTA COUNTY | Yes
31360766 |  |  |  | FROGTOWN 1701 RECOND 1153FTTO 1/0ACSR TW |  | CLSD | 31360766 | 0 | 1161.6 | 1161.6 | 0.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | ST | 08W | SH | 2019-04-09 | 2019-03-18 |  | 2019-03-18 |  |  | Yes | 2019-03-18 | [6 empty] | No | [10 empty] | Full |  |  | Full |  |  | Released in march | Full |  | Yes |  |  |  | 1980-01-01 | Y | [10 empty] | 1161.6 | 0.22 | 0 | 0 | 0.22 | 0 | 0.21837 | 0 | 0.21837 | 0 | 0.0016288 | 0.21837 |  |  | 2019-04-09 |  | COMP | 2019-05-14 08:00 | 2019-06-18 | 2019-06-18 |  |  | 2019-05-20 | [15 empty] | 31360766 | [9 empty] | Murphys | Calaveras | 38.1373 | -120.4594 | 31360766 |  |  |  | 2019 | Q2 |  |  |  |  | Y | FROGTOWN 170113412 | 921 | CALAVERAS COUNTY | Yes
31364361 |  |  |  | 0428OFAC_IDLE_REMV 12310 OLD AUBURN 4TA |  | FICL |  | 0 | 394 | 394 | 0.074621 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2AF | [51 empty] | 394 | 0.074621 | 0 | 0 | 0.074621 | 0 | 0.074621 | 0 | 0.074621 | 0 | 0 | 0.074621 |  |  |  |  | N/A | [5 empty] | 2018-06-22 | [27 empty] | 39.193 | -121.079 | [13 empty] | NEVADA COUNTY | Yes
31366453 |  |  |  | STS-COND_BROK_REPL - LANDERGEN RD HONEYD |  | CLSD |  | 0 | 205 | 205 | 0.038826 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2AF | [51 empty] | 205 | 0.038826 | 0 | 0 | 0.038826 | 0 | 0.038826 | 0 | 0.038826 | 0 | 0 | 0.038826 |  |  |  |  | N/A | [33 empty] | 40.2264 | -124.1108 | [13 empty] | HUMBOLDT COUNTY | Yes
31389447 |  |  |  | PUEBLO 1105 RECONDUCTOR W TREE WIRE |  | DOCC | 6740 | 0 | 6705.6 | 6705.6 | 1.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NB | 08W | SH | 2019-01-01 | 2019-01-01 |  | 2019-01-01 |  |  | Yes | 2019-01-01 | [6 empty] | No | [10 empty] | Full |  |  | Full |  |  |  | Full |  | Yes |  |  |  | 1980-01-01 | Y | [10 empty] | 6705.6 | 1.27 | 0 | 0 | 1.27 | 0 | 1.27 | 0 | 1.27 | 0 | 0 | 1.27 |  |  |  |  | N/A | [5 empty] | 2019-03-29 |  |  |  | 3937382 | 3325368.7 |  | 3937382 | 0 | 612013.3 | 84.45% | 3325368.7 | 0 | 3325368.7 | 0 | 2618400.5512 | 36 | [9 empty] | Napa | Napa | 38.3812 | -122.2913 | P.11939 |  |  |  | 2019 | Q2 |  |  |  |  | Y | PUEBLO 1105696 | 1210 | NAPA COUNTY | Yes
31401029 |  | 2020 | T1 A Tag | NO-NV-SHASTA CO-07/23/18 CARR FIRE |  | POST | 16868 | 0 | 16389.09 | 16389.09 | 3.104 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 95A | [51 empty] | 16389.09 | 3.104 | 0 | 0 | 3.104 | 0 | 3.104 | 0 | 3.104 | 0 | -4.8149e-08 | 3.104 |  |  |  |  | N/A | 2019-01-02 08:00 | 2019-08-30 17:00 | 2019-08-30 17:00 | 2021-04-05 07:00 | 2021-04-09 16:00 | [16 empty] | 88 | [11 empty] | 40.6866 | -122.6412 |  |  |  |  | 2019 | [8 empty] | SHASTA COUNTY | Yes
31406815 |  |  |  | POD REMV IDLE FAC 4800 MUNIZ RANCH*W |  | FICL |  | 0 | 381 | 381 | 0.072159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2AF |  |  |  | 2019-10-14 | [47 empty] | 381 | 0.072159 | 0 | 0 | 0.072159 | 0 | 0.072159 | 0 | 0.072159 | 0 | 0 | 0.072159 |  |  |  |  | N/A | [31 empty] | Cazadero | Sonoma | 38.5104 | -123.14 | [13 empty] | SONOMA COUNTY | Yes
31415330 |  |  |  | NO-NV-BUTTE-11/08/18 CAMP FIRE |  | ESTS |  | 0 | 24356.2 | 24356.2 | 4.6129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 95A | [51 empty] | 24356.2 | 4.6129 | 0 | 0 | 4.6129 | 0 | 4.6129 | 0 | 4.6129 | 0 | 0 | 4.6129 |  |  |  |  | N/A | 2019-01-02 | 2019-12-31 17:00 | 2019-12-31 17:00 | [30 empty] | 0 | 0 |  |  |  |  | 2019 | [8 empty] | BUTTE COUNTY | Yes
31420416 |  |  |  | BUCOCAMP - 675 SUNSET DR PARADISE |  | CLSD |  | 0 | 883 | 883 | 0.16723 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 95A | [51 empty] | 883 | 0.16723 | 0 | 0 | 0.16723 | 0 | 0.16723 | 0 | 0.16723 | 0 | 0 | 0.16723 |  |  |  |  | N/A | [5 empty] | 2019-03-08 | [25 empty] | Paradise | Butte | 39.7688 | -121.6265 |  |  |  |  | 2019 | [8 empty] | BUTTE COUNTY | Yes
31420810 |  |  |  | BUCOCAMP-6160 FORTY OAKS LN PARADISE |  | CLSD |  | 0 | 827 | 827 | 0.15663 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 95A | [51 empty] | 827 | 0.15663 | 0 | 0 | 0.15663 | 0 | 0.15663 | 0 | 0.15663 | 0 | -2.1532e-17 | 0.15663 |  |  |  |  | N/A | [5 empty] | 2019-01-12 | [25 empty] | Paradise | Butte | 39.7705 | -121.6338 |  |  |  |  | 2019 | [8 empty] | BUTTE COUNTY | Yes
31422565 |  |  |  | BUCOCAMP -6250 MOUNTAIN VIEW DR PARADISE |  | CLSD |  | 0 | 356 | 356 | 0.067424 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 95A | [51 empty] | 356 | 0.067424 | 739 | 0.13996 | 0.20739 | -0.13996 | 0.13902 | 0 | 0.13902 | 0 | 0.068371 | 0.13902 |  |  |  |  | N/A | [5 empty] | 2019-02-09 | [27 empty] | 39.7743 | -121.57 |  |  |  |  | 2019 | [8 empty] | BUTTE COUNTY | Yes
31422566 |  |  |  | BUCOCAMP -6250 MOUNTAIN VIEW DR PARADISE |  | CLSD |  | 0 | 356 | 356 | 0.067424 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 95F | [51 empty] | 356 | 0.067424 | 0 | 0 | 0.067424 | 0 | 0 | 0 |  | 0 | 0.067424 | 0 |  |  |  |  | N/A | [5 empty] | 2019-02-09 | [27 empty] | 39.7724 | -121.5689 |  |  |  |  | 2019 | [8 empty] | BUTTE COUNTY | Yes
31422838 |  |  |  | BUCOCAMP -7057 MOLOKAI DR PARADISE |  | CLSD |  | 0 | 83.5 | 83.5 | 0.015814 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 95A | [51 empty] | 83.5 | 0.015814 | 158 | 0.029924 | 0.045739 | -0.029924 | 0.031629 | 0 | 0.031629 | 0 | 0.01411 | 0.031629 |  |  |  |  | N/A | [5 empty] | 2019-02-07 | [25 empty] | Paradise | Butte | 39.7836 | -121.6044 |  |  |  |  | 2019 | [8 empty] | BUTTE COUNTY | Yes
31422901 |  |  |  | BUCOCAMP -7057 MOLOKAI DR PARADISE |  | CLSD |  | 0 | 83.5 | 83.5 | 0.015814 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 95B | [51 empty] | 83.5 | 0.015814 | 0 | 0 | 0.015814 | 0 | 0 | 0 |  | 0 | 0.015814 | 0 |  |  |  |  | N/A | [5 empty] | 2019-02-07 | [27 empty] | 39.7836 | -121.6048 |  |  |  |  | 2019 | [8 empty] | BUTTE COUNTY | Yes
31422902 |  |  |  | BUCOCAMP -5295 S LIBBY RD PARADISE |  | CLSD |  | 0 | 255 | 255 | 0.048295 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 95A | [51 empty] | 255 | 0.048295 | 0 | 0 | 0.048295 | 0 | 0.045644 | 0 | 0.045644 | 0 | 0.0026515 | 0.045644 |  |  |  |  | N/A | [5 empty] | 2019-02-23 | [27 empty] | 39.7405 | -121.5938 |  |  |  |  | 2019 | [8 empty] | BUTTE COUNTY | Yes
31422909 |  |  |  | BUCOCAMP - 874 BUSCHMANN RD PARADISE |  | FICL |  | 0 | 905 | 905 | 0.1714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 95A | [51 empty] | 905 | 0.1714 | 0 | 0 | 0.1714 | 0 | 0.1714 | 0 | 0.1714 | 0 | -2.1532e-17 | 0.1714 |  |  |  |  | N/A | [5 empty] | 2020-02-13 | [27 empty] | 39.7466 | -121.6137 |  |  |  |  | 2019 | [8 empty] | BUTTE COUNTY | Yes
31423331 |  |  |  | BUCOCAMP - 6168 TWIN LN PARADISE |  | CLSD |  | 0 | 420 | 420 | 0.079545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 95A | [51 empty] | 420 | 0.079545 | 0 | 0 | 0.079545 | 0 | 0.079545 | 0 | 0.079545 | 0 | 0 | 0.079545 |  |  |  |  | N/A | [5 empty] | 2019-03-22 | [27 empty] | 39.7703 | -121.6074 |  |  |  |  | 2019 | [8 empty] | BUTTE COUNTY | Yes
31425506 |  |  |  | BUCOCAMP - 5541 VISTA WAY PARADISE |  | CLSD |  | 0 | 264 | 264 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 95A | [51 empty] | 264 | 0.05 | 0 | 0 | 0.05 | 0 | 0.05 | 0 | 0.05 | 0 | 0 | 0.05 |  |  |  |  | N/A | 2019-01-02 17:00 | 2019-03-15 | 2019-03-15 |  |  | 2019-03-07 | [27 empty] | 39.7482 | -121.636 |  |  |  |  | 2019 | [8 empty] | BUTTE COUNTY | Yes
31425508 |  |  |  | BUCOCAMP - 6097 LAUREL DR PARADISE |  | CLSD |  | 0 | 422 | 422 | 0.079924 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 95A | [51 empty] | 422 | 0.079924 | 0 | 0 | 0.079924 | 0 | 0.08 | 0 | 0.08 | 0 | -7.5758e-05 | 0.08 |  |  |  |  | N/A | 2019-01-02 08:00 | 2019-03-15 17:00 | 2019-03-15 17:00 |  |  | 2019-03-06 | [27 empty] | 39.7672 | -121.6339 |  |  |  |  | 2019 | [8 empty] | BUTTE COUNTY | Yes
31425894 |  |  |  | BUCOCAMP - REBUILD CHAPARRAL DR PARADISE |  | DOCC |  | 0 | 2017 | 2017 | 0.38201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 95A | [51 empty] | 2017 | 0.38201 | 0 | 0 | 0.38201 | 0 | 0.38314 | 0 | 0.38314 | 0 | -0.0011364 | 0.38314 |  |  |  |  | N/A | [5 empty] | 2019-03-12 | [27 empty] | 39.7324 | -121.6496 |  |  |  |  | 2019 | [8 empty] | BUTTE COUNTY | Yes
31426083 |  |  |  | BUCOCAMP 5720 ACADEMY DR PARADISE |  | CLSD |  | 0 | 174 | 174 | 0.032955 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 95A | [51 empty] | 174 | 0.032955 | 0 | 0 | 0.032955 | 0 | 0.032955 | 0 | 0.032955 | 0 | -5.3829e-18 | 0.032955 |  |  |  |  | N/A | [5 empty] | 2019-03-21 | [25 empty] | Paradise | Butte | 39.7546 | -121.6173 |  |  |  |  | 2019 | [8 empty] | BUTTE COUNTY | Yes
31426086 |  |  |  | BUCOCAMP - 5250 FOSTER RD PARADISE |  | CLSD |  | 0 | 50 | 50 | 0.0094697 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 95A | [51 empty] | 50 | 0.0094697 | 0 | 0 | 0.0094697 | 0 | 0.0094697 | 0 | 0.0094697 | 0 | 0 | 0.0094697 |  |  |  |  | N/A | [5 empty] | 2019-04-01 | [27 empty] | 39.7386 | -121.6299 |  |  |  |  | 2019 | [8 empty] | BUTTE COUNTY | Yes
31426416 |  |  |  | BUCOCAMP - 6452 RIX LN PARADISE |  | CLSD |  | 0 | 578 | 578 | 0.10947 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 95A | [51 empty] | 578 | 0.10947 | 0 | 0 | 0.10947 | 0 | 0.10076 | 0 | 0.10076 | 0 | 0.0087121 | 0.10076 |  |  |  |  | N/A | [5 empty] | 2019-04-26 | [27 empty] | 39.7777 | -121.5924 |  |  |  |  | 2019 | [8 empty] | BUTTE COUNTY | Yes
31426417 |  |  |  | BUCOCAMP - 13797 SUGAR PINE DR MAGALIA |  | CLSD |  | 0 | 756 | 756 | 0.14318 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 95F | [51 empty] | 756 | 0.14318 | 0 | 0 | 0.14318 | 0 | 0.14318 | 0 | 0.14318 | 0 | 0 | 0.14318 |  |  |  |  | N/A | [5 empty] | 2019-05-02 | [27 empty] | 39.8095 | -121.5816 |  |  |  |  | 2019 | [8 empty] | BUTTE COUNTY | Yes
31426519 |  |  |  | BUCOCAMP - 5250 CALIFORNIA WAY PARADISE |  | CLSD |  | 0 | 742 | 742 | 0.14053 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 95A | [51 empty] | 742 | 0.14053 | 0 | 0 | 0.14053 | 0 | 0.14053 | 0 | 0.14053 | 0 | 0 | 0.14053 |  |  |  |  | N/A | [5 empty] | 2019-05-07 | [27 empty] | 39.7376 | -121.5957 |  |  |  |  | 2019 | [8 empty] | BUTTE COUNTY | Yes
31427127 |  |  |  | BUCOCAMP-COMCAST-FOREST SERVICE RD PARAD |  | CLSD |  | 0 | 792 | 792 | 0.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 95A | [51 empty] | 792 | 0.15 | 0 | 0 | 0.15 | 0 | 0.15 | 0 | 0.15 | 0 | 0 | 0.15 |  |  |  |  | N/A | [5 empty] | 2019-03-13 | [27 empty] | 39.7849 | -121.5889 |  |  |  |  | 2019 | [8 empty] | BUTTE COUNTY | Yes
31429487 |  |  |  | OTTER-1101 S030CC121 - TRANS POLES |  | PEND |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | CC | 08W | SH | 2021-12-21 | [6 empty] | 2019-10-17 | [11 empty] | Yes |  |  |  | 2021-12-21 | 2021-12-21 |  | 2021-12-21 | 2021-12-21 | [22 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | Remove |  |  | N/A |  |  |  | 2022-01-04 07:00 | 2022-01-28 16:00 |  |  | Yes |  | 0 | 452586.1 |  | 55000 | 55000 | -45023.6 |  | 45023.6 | 0 | 45023.6 | 0 |  |  |  |  | Complete | [11 empty] | MX |  | 2021-146 | 2022 | [5 empty] | Y | OTTER 11017611 | 1092 | MONTEREY COUNTY | Yes
31433961 |  |  |  | BUCOCAMP 1700 SONOMA CT PARADISE |  | CLSD |  | 0 | 263 | 263 | 0.049811 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 95B | [51 empty] | 263 | 0.049811 | 0 | 0 | 0.049811 | 0 | 0.04053 | 0 | 0.04053 | 0 | 0.0092803 | 0.04053 |  |  |  |  | N/A | [5 empty] | 2019-04-26 | [27 empty] | 39.7805 | -121.5804 |  |  |  |  | 2019 | [8 empty] | BUTTE COUNTY | Yes
31434881 |  |  |  | 0P 3100 SKYWAY RD PARADISE TUSCAN RIDGE |  | PEND |  | 0 | 17735 | 17735 | 3.3589 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 08W | SH | [7 empty] | 2019-06-11 | [17 empty] | Full |  |  | Full |  |  | Project is pre-DOT, and is complete | Full | [17 empty] | 17735 | 3.3589 | 0 | 0 | 3.3589 | 0 | 3.3589 | 0 | 3.3589 | 0 | 0 | 3.3589 |  |  |  |  | N/A | [33 empty] | 0 | 0 |  |  |  |  | 2019 | [8 empty] | Not assigned | Yes
31475979 |  |  |  | NC-SO-SONOMA 10/23/19 KINCADE FIRE UG CA |  | POST |  | 0 | 5276 | 5276 | 0.99924 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 95B | [51 empty] | 5276 | 0.99924 | 0 | 0 | 0.99924 | 0 | 0.99924 | 0 | 0.99924 | 0 | 0 | 0.99924 |  |  |  |  | N/A | [5 empty] | 2020-05-04 | [27 empty] | 0 | 0 |  |  |  |  | 2019 | [8 empty] | SONOMA COUNTY | Yes
35008479 |  |  |  | R2 2019 AUBERRY 1101 RECONDUCTOR |  | CLSD | 1800 | 0 | 1636.8 | 1636.8 | 0.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | FR | 08W | SH | 2019-03-12 | 2019-03-04 |  | 2019-03-04 |  |  | Yes | 2019-03-04 | 3/4: Pending EDRS Approval | QUES |  |  | Completed | COMPLETED | No |  | 0 | 0 | [7 empty] | Full |  |  | Full |  |  | ERTC released | Full |  | Yes |  |  |  | 1980-01-01 | Y | [10 empty] | 1636.8 | 0.31 | 0 | 0 | 0.31 | 0 | 0 | 0 |  | 0 | 0.31 | 0 |  |  | 2019-03-12 |  | N/A | 2019-06-03 08:00 | 2019-06-07 17:00 | 2019-06-07 17:00 |  |  | 2019-06-10 | [15 empty] | 5 | [9 empty] | Tollhouse | Fresno | 37.006 | -119.4065 | P.11678 |  |  |  | 2019 | Q2 | [5 empty] | AUBERRY 1101R2578 | 1685 | FRESNO COUNTY | Yes
35009046 |  |  |  | CCM POLE_IDLE+_REMV-2E/O 8S/O 4890 CHILE |  | CONS |  | 0 | 891 | 891 | 0.16875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2AF | [51 empty] | 891 | 0.16875 | 0 | 0 | 0.16875 | 0 | 0.16875 | 0 | 0.16875 | 0 | 0 | 0.16875 |  |  |  |  | N/A | [31 empty] | Saint Helena | Napa | 38.5783 | -122.3939 | [13 empty] | NAPA COUNTY | Yes
35010118 |  |  |  | STS-COND_IDLE_REMV - 695 ORCHARD AVE SON |  | CLSD |  | 0 | 150 | 150 | 0.028409 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2AF | [51 empty] | 150 | 0.028409 | 0 | 0 | 0.028409 | 0 | 0.028409 | 0 | 0.028409 | 0 | 0 | 0.028409 |  |  |  |  | N/A | [5 empty] | 2018-04-19 | [27 empty] | 37.9942 | -120.3876 | [13 empty] | TUOLUMNE COUNTY | Yes
35010356 |  |  |  | X*FT-OFAC_IDLE_REMV-OLD ADOBE RD 13 POLE |  | CLSD |  | 0 | 337 | 337 | 0.063826 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2AF | [51 empty] | 337 | 0.063826 | 0 | 0 | 0.063826 | 0 | 0.063826 | 0 | 0.063826 | 0 | 0 | 0.063826 |  |  |  |  | N/A | [5 empty] | 2018-07-02 | [27 empty] | 36.9511 | -121.8189 | [13 empty] | SANTA CRUZ COUNTY | Yes
35010358 |  |  |  | X STS-COND_IDLE_REMV-OLD GIRL SCOUT |  | CLSD |  | 0 | 516 | 516 | 0.097727 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2AF | [51 empty] | 516 | 0.097727 | 0 | 0 | 0.097727 | 0 | 0.097727 | 0 | 0.097727 | 0 | 0 | 0.097727 |  |  |  |  | N/A | [5 empty] | 2018-05-30 | [27 empty] | 37.1219 | -122.1673 | [13 empty] | SANTA CRUZ COUNTY | Yes
35011247 |  |  |  | STS-COND_IDLE_REMV-3054 CALAVERITAS RD ( |  | CLSD |  | 0 | 1090 | 1090 | 0.20644 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2AF | [51 empty] | 1090 | 0.20644 | 0 | 0 | 0.20644 | 0 | 0.20644 | 0 | 0.20644 | 0 | 0 | 0.20644 |  |  |  |  | N/A | [5 empty] | 2019-10-23 | [25 empty] | San Andreas | Calaveras | 38.1713 | -120.6326 | [13 empty] | CALAVERAS COUNTY | Yes
35011253 |  |  |  | STS-POLE_IDLE_REMV-OPP 5865 POOLE STATIO |  | CLSD |  | 0 | 800 | 800 | 0.15152 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2AF | [51 empty] | 800 | 0.15152 | 0 | 0 | 0.15152 | 0 | 0.15152 | 0 | 0.15152 | 0 | 0 | 0.15152 |  |  |  |  | N/A | [5 empty] | 2019-09-16 | [27 empty] | 38.1415 | -120.6643 | [13 empty] | CALAVERAS COUNTY | Yes
35011254 |  |  |  | STS-TRAN_IDLE_REMV-OLD BULK OIL PLANT 1/ |  | CLSD |  | 0 | 350 | 350 | 0.066288 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2AF | [51 empty] | 350 | 0.066288 | 0 | 0 | 0.066288 | 0 | 0.066288 | 0 | 0.066288 | 0 | 0 | 0.066288 |  |  |  |  | N/A | [5 empty] | 2019-09-12 | [25 empty] | San Andreas | Calaveras | 38.1675 | -120.6727 | [13 empty] | CALAVERAS COUNTY | Yes
35011295 |  |  |  | *FT-OFAC_IDLE_REMV-6301 ECHO LN |  | CLSD |  | 0 | 1583 | 1583 | 0.29981 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2AF | [51 empty] | 1583 | 0.29981 | 0 | 0 | 0.29981 | 0 | 0.29981 | 0 | 0.29981 | 0 | 0 | 0.29981 |  |  |  |  | N/A | [5 empty] | 2018-06-22 | [27 empty] | 38.7048 | -120.8618 | [13 empty] | EL DORADO COUNTY | Yes
35012324 |  |  |  | STS-TRAN_IDLE_REMV-2 POLES EAST OF C/O'S |  | CLSD |  | 0 | 263 | 263 | 0.049811 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2AF | [51 empty] | 263 | 0.049811 | 0 | 0 | 0.049811 | 0 | 0.049811 | 0 | 0.049811 | 0 | 0 | 0.049811 |  |  |  |  | N/A | [5 empty] | 2018-05-31 | [27 empty] | 40.6316 | -122.2544 | [13 empty] | SHASTA COUNTY | Yes
35012964 |  |  |  | 7/9-STS-COND_IDLE_REMV-CRN ELM DR |  | CLSD |  | 0 | 1234 | 1234 | 0.23371 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2AF | [51 empty] | 1234 | 0.23371 | 0 | 0 | 0.23371 | 0 | 0.23371 | 0 | 0.23371 | 0 | 0 | 0.23371 |  |  |  |  | N/A | [5 empty] | 2018-06-15 | [25 empty] | Clearlake | Lake | 39.0076 | -122.6699 | [13 empty] | LAKE COUNTY | Yes
35014742 |  |  |  | 0628 IDLE FACIREPL - 1S/O 16823 COLEMAN |  | FICL |  | 0 | 803 | 803 | 0.15208 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2AF |  |  |  | 2018-11-20 | [47 empty] | 803 | 0.15208 | 0 | 0 | 0.15208 | 0 | 0.15208 | 0 | 0.15208 | 0 | 0 | 0.15208 |  |  |  |  | N/A | [5 empty] | 2018-08-03 | [25 empty] | Grass Valley | Nevada | 39.1269 | -121.1702 | [13 empty] | NEVADA COUNTY | Yes
35014889 |  |  |  | STS-POLE_DECA_REPL - #1E ON LINE @ R/O 2 |  | CLSD |  | 0 | 552 | 552 | 0.10455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2AF | [51 empty] | 552 | 0.10455 | 0 | 0 | 0.10455 | 0 | 0.10455 | 0 | 0.10455 | 0 | 0 | 0.10455 |  |  |  |  | N/A | [5 empty] | 2018-07-06 | [25 empty] | North San Juan | Nevada | 39.3722 | -121.1011 | [13 empty] | NEVADA COUNTY | Yes
35016357 |  |  |  | STS-COND_IDLE_REMV-LCO 2961 DENNY RD |  | CLSD |  | 0 | 647 | 647 | 0.12254 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2AF | [51 empty] | 647 | 0.12254 | 0 | 0 | 0.12254 | 0 | 0.12254 | 0 | 0.12254 | 0 | 0 | 0.12254 |  |  |  |  | N/A | [5 empty] | 2018-03-26 | [27 empty] | 40.8705 | -123.5211 | [13 empty] | HUMBOLDT COUNTY | Yes
35016855 |  |  |  | 10/31-ST-POLE_IDLE_REMV-43451 EUREKA HIL |  | CLSD |  | 0 | 214 | 214 | 0.04053 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2AF | [51 empty] | 214 | 0.04053 | 0 | 0 | 0.04053 | 0 | 0.04053 | 0 | 0.04053 | 0 | 0 | 0.04053 |  |  |  |  | N/A | [5 empty] | 2018-06-12 | [27 empty] | 38.9098 | -123.6856 | [13 empty] | MENDOCINO COUNTY | Yes
35018047 |  |  |  | +STS-POLE_IDLE_REMV - TABLE MTNSAN MIGUE |  | CLSD |  | 0 | 839 | 839 | 0.1589 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2AF | [51 empty] | 839 | 0.1589 | 0 | 0 | 0.1589 | 0 | 0.1589 | 0 | 0.1589 | 0 | 0 | 0.1589 |  |  |  |  | N/A | [5 empty] | 2018-10-20 | [27 empty] | 35.9272 | -120.3825 | [13 empty] | San Luis Obispo County | Yes
35018539 |  |  |  | 6/30-STS-POLE_IDLE_REMV-#1S/O 3000GUIDIV |  | CLSD |  | 0 | 252 | 252 | 0.047727 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2AF | [51 empty] | 252 | 0.047727 | 0 | 0 | 0.047727 | 0 | 0.047727 | 0 | 0.047727 | 0 | 0 | 0.047727 |  |  |  |  | N/A | [5 empty] | 2018-04-24 | [27 empty] | 39.139 | -123.1476 | [13 empty] | MENDOCINO COUNTY | Yes
35018787 |  |  |  | HALSEY 1101 - S039NO112 HIGH SPLICE 08J |  | MAPP | 1621 | 0 | 2854 | 2854 | 0.54053 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | SH | 2019-08-05 | 2019-06-26 | 2019-03-13 | 2019-06-26 |  |  | Yes | 2019-06-26 | 4/17: 2nd submittal to ED by 4/254/19: 4th ADE submittal5/15: waiting on 1st corrections from [REDACTED]5/22: waiting on 1st corrections from [REDACTED]5/29: 2nd submittal (7th total) due to renumbering by 6/5 with EOD by 6/75/31: 2nd submittal sent6/5: EDRS soon6/12: EDRS will be ready tomorrow6/19: ADE on vacation - updated EOD to 6/286/26: APPROVED | CAL |  |  | Completed | COMPLETED | No |  | 0 | 0 | [7 empty] | Full |  |  | Full |  |  | ERTC is Complete | Full |  | Yes |  |  | Annual | 1980-01-01 | Y | [10 empty] | 2854 | 0.54053 | 0 | 0 | 0.54053 | 0 | 0.54053 | 0 | 0.54053 | 0 | 0 | 0.54053 |  |  | 2019-08-05 |  | N/A | 2019-07-23 | 2019-08-28 | 2019-08-28 |  |  | 2019-09-09 |  |  |  | 866575 | 806580.7 |  | 873318 | 6743 | 60514.8 | 93.07% | 806060.2 | 0 | 806060.2 | -137927 | 1492202.5564 | 16 | [9 empty] | Meadow Vista | Placer | 0 | 0 | 35018787 |  |  |  | 2019 | Q3 |  |  |  |  | Y | HALSEY 110176178 | 1629 | PLACER COUNTY | Yes
35018788 |  |  |  | APPLE HILL 1104 - S049NO119 HIGH SPLICE |  | CLSD | 3769 | 0 | 6121 | 6121 | 1.1593 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | SH | 2019-05-28 | 2019-05-28 | 2019-03-17 | 2019-05-28 |  |  | Yes | 2019-05-28 | 5/28: Complete | CAL |  |  | Completed | COMPLETED | No |  | 0 | 0 | [7 empty] | Full |  |  | Full |  |  |  | Full |  | Yes |  |  | Contractor nootified to obtain their own no-fee permit 6/28/19 | 1980-01-01 | Y | [10 empty] | 6121 | 1.1593 | 0 | 0 | 1.1593 | 0 | 1.1593 | 0 | 1.1593 | 0 | -1.7225e-16 | 1.1593 |  |  |  |  | N/A | [5 empty] | 2019-09-22 | [15 empty] | 38 | [9 empty] | Camino | El Dorado | 0 | 0 | 35018788 |  |  |  | 2019 | Q3 |  |  |  |  | Y | APPLE HILL 110412842 | 320 | EL DORADO COUNTY | Yes
35019006 |  |  |  | ROB ROY 2104 CO11865 REPLACE OH LINE |  | CLSD | 9680 | 0 | 9525 | 9525 | 1.804 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | CC | 08W | SH | 2019-06-20 | 2019-06-20 |  | 2019-06-20 |  |  | Yes | 2019-06-20 | [6 empty] | No | [10 empty] | Full |  |  | Full |  |  | walkdown 7/24 - Potental for 1 pole to require an easement & 1 guy connect confirmation | Full |  | Yes |  |  | County states that work may be completed under Annual permit. | 1980-01-01 | Y | [10 empty] | 9525 | 1.804 | 0 | 0 | 1.804 | 0 | 1.804 | 0 | 1.804 | 0 | 0 | 1.804 |  |  |  |  | N/A | [5 empty] | 2019-12-11 | [15 empty] | 35 | [9 empty] | Watsonville | Santa Cruz | 37.0261 | -121.7749 | 35019006 |  |  |  | 2019 | Q3 |  |  |  |  | Y | GREEN VALLEY 210111054 | 778 | SANTA CRUZ COUNTY | Yes
35022707 |  |  |  | XSTS-COND_IDLE_REMV-HWY 1 (AREA 3 SPANS |  | FICL |  | 0 | 395 | 395 | 0.074811 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2AF | [51 empty] | 395 | 0.074811 | 0 | 0 | 0.074811 | 0 | 0.074811 | 0 | 0.074811 | 0 | 0 | 0.074811 |  |  |  |  | N/A | [5 empty] | 2018-07-23 | [27 empty] | 36.4215 | -121.9117 | [13 empty] | MONTEREY COUNTY | Yes
35022860 |  |  |  | STS-POLE_IDLE_REMV-END OF CALDERWOOD RD |  | DOCC |  | 0 | 368 | 368 | 0.069697 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2AF | [51 empty] | 368 | 0.069697 | 0 | 0 | 0.069697 | 0 | 0.069697 | 0 | 0.069697 | 0 | 0 | 0.069697 |  |  |  |  | N/A | [5 empty] | 2019-09-11 | [27 empty] | 38.6675 | -120.9541 | [13 empty] | EL DORADO COUNTY | Yes
35022861 |  |  |  | STS-POLE_IDLE_REMV-CHURCH MINE RD |  | DOCC |  | 0 | 2168 | 2168 | 0.41061 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2AF |  |  |  | 2019-01-03 | [47 empty] | 2168 | 0.41061 | 0 | 0 | 0.41061 | 0 | 0.41061 | 0 | 0.41061 | 0 | 0 | 0.41061 |  |  |  |  | N/A | [5 empty] | 2019-09-17 | [27 empty] | 38.6537 | -120.8271 | [13 empty] | EL DORADO COUNTY | Yes
35023234 |  |  |  | STS-OFAC_IDLE_REMV-34039 HIGHWAY 44 |  | CLSD |  | 0 | 380 | 380 | 0.07197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2AF |  |  |  | 2018-11-10 | [47 empty] | 380 | 0.07197 | 0 | 0 | 0.07197 | 0 | 0.07197 | 0 | 0.07197 | 0 | 0 | 0.07197 |  |  |  |  | N/A | [5 empty] | 2019-04-26 | [25 empty] | Shingletown | Shasta | 40.5129 | -121.772 | [13 empty] | SHASTA COUNTY | Yes
35023526 |  |  |  | 1/6/19-STS-POLE_IDLE_REMV-7050 BOGGS KEL |  | CLSD |  | 0 | 410 | 410 | 0.077652 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2AF | [51 empty] | 410 | 0.077652 | 0 | 0 | 0.077652 | 0 | 0.077652 | 0 | 0.077652 | 0 | 0 | 0.077652 |  |  |  |  | N/A | [5 empty] | 2018-10-23 | [27 empty] | 38.9498 | -122.879 | [13 empty] | LAKE COUNTY | Yes
35023687 |  |  |  | R2RPL OH WIRE ON B LOMND 0401 17-0095503 |  | DOCC | 7590 | 0 | 7044 | 7044 | 1.3341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | CC | 08W | SH | 2019-10-15 | 2019-10-15 |  | 2019-10-15 |  |  | Yes | 2019-10-15 | 4/8: On track for 1st submittal 4/304/17: On track for 4/30 submittal4/29: Submitted 1st ADE submittal5/8: 1st correction received today5/14: 2nd submittal sent5/21: 3rd submittal sent5/29: ADE on vacation - job on 3rd review6/4: 3rd Review submitted6/5: approved by [REDACTED], EDRS shortly. Uploading issues with SAP, but IT has been contacted6/12: Approved and in PEND | EEI |  |  | Completed | COMPLETED | No |  | 0 | 0 | [7 empty] | Full |  |  | Full |  |  | Additional issues found on job walk that delayed ERTC - Partial release scheduled for 8/30/19 | Full |  | Yes |  |  | Annual will cover work - no road closers longer than 15 minutes | 1980-01-01 | Y | [10 empty] | 7044 | 1.3341 | 0 | 0 | 1.3341 | 0 | 1.3341 | 0 | 1.3341 | 0 | -1.7225e-16 | 1.3341 |  |  |  |  | N/A | [5 empty] | 2019-12-19 |  |  |  | 4004352 | 4162806.1 |  | 4004352 | 0 | 126109.6 | 104% | 3878242.4 | 0 | 3878242.4 | 0 | 3120331.6593 | 58 | [9 empty] | Ben Lomond | Santa Cruz | 37.0955 | -122.0857 | P.11844 |  |  |  | 2019 | Q4 |  |  |  |  | Y | BEN LOMOND 04015206 | 401 | SANTA CRUZ COUNTY | Yes
35024926 |  |  |  | MARTELL 1101 RECONDCUTOR 3,700FT |  | FICL | 686.4 | 0 | 686.4 | 686.4 | 0.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | ST | 08W | SH | 2019-03-08 | 2019-02-21 |  | 2019-02-21 |  |  | Yes | 2019-02-21 | 2/20: Pending EDRS approval - SAP is now showing ESTS | CAL |  |  | Completed | COMPLETED | No |  | 0 | 0 | [7 empty] | Full |  |  | Full |  |  |  | Full |  | Yes |  |  |  | 1980-01-01 | Y | [10 empty] | 686.4 | 0.13 | 0 | 0 | 0.13 | 0 | 0.13 | 0 | 0.13 | 0 | 0 | 0.13 |  |  | 2019-03-08 |  | COMP | 2019-03-18 08:00 | 2019-03-30 | 2019-03-30 |  |  | 2019-03-30 |  |  |  | 703057 | 537779.5 |  | 824970 | 121913 | 165277.5 | 76.49% | 537779.5 | 0 | 537779.5 | 0 | 4136765.3846 | 20 | [9 empty] | Sutter Creek | Amador | 38.3951 | -120.8017 | 35024926 |  |  |  | 2019 | Q2 |  |  |  |  | Y | MARTELL 1101CB | 2357 | AMADOR COUNTY | Yes
35025977 |  |  |  | REMV 4 IDLE POLES 12099 HWY 12 KEN*OCLH |  | CLSD |  | 0 | 712 | 712 | 0.13485 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2AF | [51 empty] | 712 | 0.13485 | 0 | 0 | 0.13485 | 0 | 0.13485 | 0 | 0.13485 | 0 | 0 | 0.13485 |  |  |  |  | N/A | [5 empty] | 2018-07-19 | [25 empty] | Kenwood | Sonoma | 38.3948 | -122.5147 | [13 empty] | SONOMA COUNTY | Yes
35026735 |  |  |  | X STS-COND_BROK_REPA - NEAR 19145 BIG |  | CLSD |  | 0 | 420 | 420 | 0.079545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2AF | [51 empty] | 420 | 0.079545 | 0 | 0 | 0.079545 | 0 | 0.079545 | 0 | 0.079545 | 0 | 0 | 0.079545 |  |  |  |  | N/A | [5 empty] | 2018-07-31 | [27 empty] | 37.1717 | -122.1761 | [13 empty] | SANTA CRUZ COUNTY | Yes
35026994 |  |  |  | STS-POLE_IDLE_REMV - 7140 KELSEY CREEK D |  | CLSD |  | 0 | 390 | 390 | 0.073864 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2AF | [51 empty] | 390 | 0.073864 | 0 | 0 | 0.073864 | 0 | 0.073864 | 0 | 0.073864 | 0 | 0 | 0.073864 |  |  |  |  | N/A | [5 empty] | 2018-10-22 | [27 empty] | 38.9517 | -122.8384 | [13 empty] | LAKE COUNTY | Yes
35030654 |  |  |  | TW ON WOODSIDE1101 N/O 7573 |  | FICL | 5271 | 0 | 5271 | 5271 | 0.9983 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | PN | 08W | SH | 2019-03-06 | 2019-03-06 |  | 2019-03-06 |  |  | Yes | 2019-03-06 | 3/4: ADE approved pending EDRS approval | EEI |  |  | Completed | COMPLETED | No |  | 0 | 0 | [7 empty] | Full |  |  | Full |  |  |  | Full |  | Yes |  |  |  | 1980-01-01 | Y | [10 empty] | 5271 | 0.9983 | 0 | 0 | 0.9983 | 0 | 0.9983 | 0 | 0.9983 | 0 | 0 | 0.9983 |  |  |  |  | N/A | [5 empty] | 2019-12-06 |  |  |  | 1864935 | 1527107.5 |  | 1864935 | 0 | 433292.2 | 81.88% | 1431642.8 | 0 | 1431642.8 | 0 | 1529714.9687 | 26 | [9 empty] | Redwood City | San Mateo | 37.3792 | -122.2831 | 35030654 |  |  |  | 2019 | Q3 |  |  |  |  | Y | WOODSIDE 11018974 | 59 | SAN MATEO COUNTY | Yes
35030877 |  |  |  | 12/31 REMV IDLE 5 PLS 25050 HWY 1 C*OCLH |  | CLSD |  | 0 | 796 | 796 | 0.15076 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2AF | [51 empty] | 796 | 0.15076 | 0 | 0 | 0.15076 | 0 | 0.15076 | 0 | 0.15076 | 0 | 0 | 0.15076 |  |  |  |  | N/A | [5 empty] | 2018-08-06 | [25 empty] | Jenner | Sonoma | 38.6005 | -123.3488 | [13 empty] | SONOMA COUNTY | Yes
35031139 |  |  |  | SHADY GLEN 1102 RECONDUCTOR BEYOND 6343 |  | CLSD | 7900 | 0 | 8016 | 8016 | 1.5182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | SH | 2019-07-11 | 2019-07-11 | 2020-10-31 | 2019-07-11 |  |  | Yes | 2019-07-11 | 4/8: Working Job Packages4/10: Updated Scope for QUES to review4/17: waiting for Updated Scope4/24: waiting for updated change order5/15: QUES to follow up. Waiting on UG inspection ([REDACTED] to follow up)5/22: [REDACTED] to provide map and explaination for why not to UG. QUES to provide 1st ADE submittal timeframe 6/115/29: [REDACTED] to follow up with [REDACTED]6/5: 1st submittal by 6/186/12: on track for 6/18 submittal6/19:1st ADE submittal sent - assigned to [REDACTED]6/25: corrections back from [REDACTED]7/1: got clarification7/3: 7/12 2nd submittal7/9: 2nd submittal send7/11: APPROVED | QUES |  |  | Completed | COMPLETED | No |  | 0 | 0 | [7 empty] | Full |  |  | Full |  |  |  | Full |  | Yes |  |  | Placer County Annual | 2019-12-19 | [11 empty] | 8016 | 1.5182 | 0 | 0 | 1.5182 | 0 | 1.5182 | 0 | 1.5182 | 0 | -3.4451e-16 | 1.5182 |  |  |  |  | N/A | [5 empty] | 2019-12-30 | [15 empty] | 29 | [9 empty] | Colfax | Placer | 39.1479 | -120.9087 | 35031139 |  |  |  | 2019 | Q3 |  |  |  |  | Y | SHADY GLEN 1102CB | 349 | PLACER COUNTY | Yes
35031662 |  | 2020 | 220 Mile Plan | CWSP - LOS GATOS 1106 - LB44 - PHASE 2.1 |  | FICL | 2978 | 511 | 2467 | 2978 | 0.56402 | 2978 | 0.56402 | 0 | 0 | 0 | 0 | 8.6126e-17 |  |  | DA | 08W | SH | 2020-02-18 17:00 | 2019-10-07 |  | 2019-10-07 |  |  | Yes | 2019-10-07 | waiting on GC review | SANTA ROSA |  |  |  | 100 | No |  |  |  |  | Yes | [5 empty] | Full |  |  | Full |  |  | [REDACTED] to check on CIF - EOD 7/30/19; SJ Waterworks (notification only); Midpeninsula Open Space | Full |  | Yes |  |  | Santa Clara County | 1980-01-01 | Y | [10 empty] | 0 | 0 | 2978 | 0.56402 | 0.56402 | 5.1676e-16 | 0.56402 | 0 | 0.56402 | 0 | -5.1676e-16 | 0.56402 |  | Keep | 2020-02-18 17:00 | Yes | N/A | 2020-02-12 | 2020-03-25 | 2020-03-25 17:00 |  |  | 2020-03-25 |  | Yes | Shovel Ready | 1109989 | 1400256.8 | 19735.7 | 1363100.7 | 253111.7 | 1053093.5 | 126.2% | 50787.3 | 6108.2 | 56895.5 | 0 | 2482658.1276 | 13 |  | 6/21 - next week will have additional PM numbers to add tohe list for new segments | [7 empty] | Los Gatos | Santa Clara | 37.1933 | -122.0204 | E.0000130.01 |  |  | 2020-079 | 2020 | Q1 | 2019-10-04 | 2020-02-02 | 2020-03-23 |  | Y | LOS GATOS 1106LB44 | 841 | SANTA CLARA COUNTY | Yes
35032266 |  |  |  | APPLE HILL 1104 RECONDUCTOR |  | CLSD | 1060 | 0 | 877 | 877 | 0.1661 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | SH | 2019-06-13 | 2019-06-13 |  | 2019-06-13 |  |  | Yes | 2019-06-13 | 5/22: on track for 6/3 submittal 6/3: 1st ADE submitted 6/5: 1st corrections 6/12: EEI to follow up with 2nd submittal 6/13: APPROVED | EEI |  |  | Completed | COMPLETED | No |  | 0 | 0 | [7 empty] | Full |  |  | Full |  |  | Received on 6/17 No contraints identified | Full |  | Yes |  |  |  | 1980-01-01 | Y | [10 empty] | 877 | 0.1661 | 0 | 0 | 0.1661 | 0 | 0.1661 | 0 | 0.1661 | 0 | 0 | 0.1661 |  |  |  |  | N/A | [5 empty] | 2019-08-01 | [15 empty] | 7 | [9 empty] | Pollock Pines | El Dorado | 38.7632 | -120.5756 | 35032266 |  |  |  | 2019 | Q3 |  |  |  |  | Y | APPLE HILL 110413512 | 99 | EL DORADO COUNTY | Yes
35037345 |  |  |  | STS-OFAC_IDLE_REMV-6645 E. HWY 246 |  | CLSD |  | 0 | 250 | 250 | 0.047348 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2AF |  |  |  | 2019-04-28 | [47 empty] | 250 | 0.047348 | 0 | 0 | 0.047348 | 0 | 0.047348 | 0 | 0.047348 | 0 | 0 | 0.047348 |  |  |  |  | N/A | [5 empty] | 2019-08-12 | [25 empty] | Los Osos | San Luis Obispo | 34.6385 | -120.2903 | [13 empty] | SANTA BARBARA COUNTY | Yes
35037594 |  |  |  | COND_IDLE_REMV-JUNCTION @ HWY 36 & R |  | FICL |  | 0 | 497 | 497 | 0.094129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2AF |  |  |  | 2019-07-06 | [47 empty] | 497 | 0.094129 | 0 | 0 | 0.094129 | 0 | 0.094129 | 0 | 0.094129 | 0 | 0 | 0.094129 |  |  |  |  | N/A | [5 empty] | 2019-11-14 | [27 empty] | 40.3012 | 123.5944 | [13 empty] | HUMBOLDT COUNTY | Yes
35037647 |  |  |  | STS-POLE_IDLE_REMV-44141 LITTLE LAKE RD |  | FICL |  | 0 | 527 | 527 | 0.099811 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2AF |  |  |  | 2019-06-12 | [47 empty] | 527 | 0.099811 | 0 | 0 | 0.099811 | 0 | 0.099811 | 0 | 0.099811 | 0 | 0 | 0.099811 |  |  |  |  | N/A | [5 empty] | 2019-08-09 | [27 empty] | 39.3122 | -123.783 | [13 empty] | MENDOCINO COUNTY | Yes
35038059 |  |  |  | STS-COND_IDLE_REMV-11648 LA PORTE ROAD |  | CLSD |  | 0 | 115 | 115 | 0.02178 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2AF |  |  |  | 2019-06-30 | [47 empty] | 115 | 0.02178 | 0 | 0 | 0.02178 | 0 | 0.02178 | 0 | 0.02178 | 0 | 0 | 0.02178 |  |  |  |  | N/A | [5 empty] | 2019-06-19 | [27 empty] | 39.5224 | -121.1819 | [13 empty] | BUTTE COUNTY | Yes
35038141 |  |  |  | STS-COND_IDLE_REMV-BRUSH CREEL LANE |  | CLSD |  | 0 | 323 | 323 | 0.061174 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2AF |  |  |  | 2019-06-19 | [47 empty] | 323 | 0.061174 | 0 | 0 | 0.061174 | 0 | 0.061174 | 0 | 0.061174 | 0 | 0 | 0.061174 |  |  |  |  | N/A | [5 empty] | 2019-07-27 | [25 empty] | Shingletown | Shasta | 40.4947 | 121.8665 | [13 empty] | SHASTA COUNTY | Yes
35038190 |  |  |  | X-STS-TRAN_IDLE_REMV-A/O 30445 CHUALAR |  | FICL |  | 0 | 515 | 515 | 0.097538 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2AF |  |  |  | 2019-02-21 | [47 empty] | 515 | 0.097538 | 0 | 0 | 0.097538 | 0 | 0.097538 | 0 | 0.097538 | 0 | 0 | 0.097538 |  |  |  |  | N/A | [5 empty] | 2019-04-12 | [27 empty] | 36.603 | -121.429 | [13 empty] | MONTEREY COUNTY | Yes
35038312 |  |  |  | +STS-COND_IDLE_REMV-S OF 7100 FOXEN CYN |  | CLSD |  | 0 | 320 | 320 | 0.060606 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2AF |  |  |  | 2019-04-24 | [47 empty] | 320 | 0.060606 | 0 | 0 | 0.060606 | 0 | 0.060606 | 0 | 0.060606 | 0 | 0 | 0.060606 |  |  |  |  | N/A | [5 empty] | 2019-08-22 | [27 empty] | 34.8318 | -120.2326 | [13 empty] | SANTA BARBARA COUNTY | Yes
35038502 |  |  |  | STS-TRAN_IDLE_REMV-CHOLAME VALLEY RD |  | CLSD |  | 0 | 866 | 866 | 0.16402 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2AF |  |  |  | 2019-05-26 | [47 empty] | 866 | 0.16402 | 0 | 0 | 0.16402 | 0 | 0.16402 | 0 | 0.16402 | 0 | 0 | 0.16402 |  |  |  |  | N/A | [5 empty] | 2019-06-05 | [27 empty] | 35.8493 | -120.3944 | [13 empty] | MONTEREY COUNTY | Yes
35038571 |  |  |  | POLE_IDLE_REMV-NEXT TO BUSCH CR |  | CLSD |  | 0 | 273 | 273 | 0.051705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2AF |  |  |  | 2019-07-20 | [47 empty] | 273 | 0.051705 | 0 | 0 | 0.051705 | 0 | 0.051705 | 0 | 0.051705 | 0 | 0 | 0.051705 |  |  |  |  | N/A | [5 empty] | 2019-09-08 | [27 empty] | 39.2075 | -123.0845 | [13 empty] | MENDOCINO COUNTY | Yes
35038608 |  |  |  | STS-COND_IDLE_REMV-8100 PLEASANTS VALLEY |  | CLSD |  | 0 | 1140 | 1140 | 0.21591 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2AF |  |  |  | 2019-04-24 | [47 empty] | 1140 | 0.21591 | 0 | 0 | 0.21591 | 0 | 0.21591 | 0 | 0.21591 | 0 | 0 | 0.21591 |  |  |  |  | N/A | [5 empty] | 2019-09-10 | [27 empty] | 38.4603 | -122.0547 | [13 empty] | SOLANO COUNTY | Yes
35038685 |  |  |  | REMV IDLE TAP-X ST FROM 2997 RD. 30 |  | CLSD |  | 0 | 624 | 624 | 0.11818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2AF |  |  |  | 2019-05-11 | [47 empty] | 624 | 0.11818 | 0 | 0 | 0.11818 | 0 | 0.11818 | 0 | 0.11818 | 0 | 0 | 0.11818 |  |  |  |  | N/A | [5 empty] | 2019-10-16 | [25 empty] | Elk Creek | Glenn | 39.587 | -122.5887 | [13 empty] | GLENN COUNTY | Yes
35039002 |  |  |  | OCGC 2018 CALISTOGA 1101 LEVEL 2 DEMO |  | CLSD | 6336 | 0 | 6007 | 6007 | 1.1377 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NB | 08W | SH | 2019-01-01 | 2019-01-01 |  | 2019-01-01 |  |  | Yes | 2019-01-01 | [6 empty] | No | [10 empty] | Full |  |  | Full |  |  |  | Full |  | Yes |  |  |  | 1980-01-01 | Y | [10 empty] | 6007 | 1.1377 | 0 | 0 | 1.1377 | 0 | 1.14 | 0 | 1.14 | 0 | -0.0023106 | 1.14 |  |  |  |  | N/A | [5 empty] | 2019-03-29 | [15 empty] | 22 | [9 empty] | Calistoga | Napa | 0 | 0 | 35039002 |  |  |  | 2019 | Q2 |  |  |  |  | Y | CALISTOGA 1101736 | 24 | NAPA COUNTY | Yes
35040225 |  |  |  | HIGGINS 1110 RECONDUCTOR |  | CLSD | 7400 | 0 | 8584 | 8584 | 1.6258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | SH | 2019-07-01 | 2019-07-01 |  | 2019-07-01 |  |  | Yes | 2019-07-01 | 5/22: on track for 6/3 submittal6/5: 1st submittal by 6/76/7: 1st ADE submittal - assigned to [REDACTED]6/13: 1st correction received6/19: EEI to follow up on 2nd submittal6/20: 2nd submittal sent6/21: 2nd corrections sent6/26: ADE on vacation6/28: APPROVED | EEI |  |  | Completed | COMPLETED | No |  | 0 | 0 | [7 empty] | Full |  |  | Full |  |  | ERTC COmpleted | Full |  | Yes |  |  | Private Property - No Permit Needed | 1980-01-01 | Y | [10 empty] | 8584 | 1.6258 | 0 | 0 | 1.6258 | 0 | 1.6258 | 0 | 1.6258 | 0 | 0 | 1.6258 |  |  |  |  | N/A | [5 empty] | 2019-09-30 | [15 empty] | 29 | [9 empty] | Grass Valley | Nevada | 0 | 0 | 35040225 |  |  |  | 2019 | Q3 |  |  |  |  | Y | HIGGINS 11102408 | 1188 | NEVADA COUNTY | Yes
35040742 |  |  |  | OCGC - 2018 MONTE RIO 1112 OH TO UG DEMO |  | CLSD | 2710 | 0 | 2798.4 | 2798.4 | 0.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SO | 08W | SH | 2019-01-01 | 2019-01-01 |  | 2019-01-01 |  |  | Yes | 2019-01-01 | [6 empty] | No | [10 empty] | Full |  |  | Full |  |  |  | Full |  | Yes |  |  |  | 1980-01-01 | Y | [10 empty] | 2798.4 | 0.53 | 0 | 0 | 0.53 | 0 | 0.53 | 0 | 0.53 | 0 | 0 | 0.53 |  |  |  |  | N/A | [5 empty] | 2019-04-05 | [15 empty] | 12.0444 | [9 empty] | Occidental | Sonoma | 38.4146 | -122.9514 | 35040742 |  |  |  | 2019 | Q2 |  |  |  |  | Y | MONTE RIO 1112120 | 54 | SONOMA COUNTY | Yes
35042365 |  |  |  | CWSP - CAMP EVERS 2106 - LR 60124 - PH 5 |  | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | CC | 08W | [51 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [31 empty] | Los Gatos | Santa Clara | 37.0639 | -121.797 | [11 empty] | CAMP EVERS 210660124 | 57 | SANTA CRUZ COUNTY | Yes
35042366 |  |  |  | CWSP - CAMP EVERS 2106 - 60124 - PHASE 4 |  | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | CC | 08W | [51 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [31 empty] | Los Gatos | Santa Clara | 37.0639 | -121.797 | [11 empty] | CAMP EVERS 210660124 | 57 | SANTA CRUZ COUNTY | Yes
35042368 |  |  |  | CWSP - CAMP EVERS 2106 - 60124 - PHASE 2 |  | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | CC | 08W | [51 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [31 empty] | Los Gatos | Santa Clara | 37.0639 | -121.797 | [11 empty] | CAMP EVERS 210660124 | 57 | SANTA CRUZ COUNTY | Yes
35042369 |  |  |  | CWSP - CAMP EVERS 2106 - 60124 - PHASE 1 |  | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | CC | 08W | [51 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [31 empty] | Los Gatos | Santa Clara | 37.0639 | -121.797 | [11 empty] | CAMP EVERS 210660124 | 57 | SANTA CRUZ COUNTY | Yes
35042670 |  |  |  | STS-POLE_DECA_REPL - 4300 SOFAR RD PLACE |  | CLSD |  | 0 | 467 | 467 | 0.088447 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2AF | [51 empty] | 467 | 0.088447 | 0 | 0 | 0.088447 | 0 | 0.088447 | 0 | 0.088447 | 0 | 0 | 0.088447 |  |  |  |  | N/A | [5 empty] | 2018-09-10 | [27 empty] | 38.7026 | -120.7902 | [13 empty] | EL DORADO COUNTY | Yes
35042719 |  |  |  | CWSP-AMGWIN STEEL POLE & TW DEMO PH |  | CLSD | 2112 | 0 | 1275 | 1275 | 0.24148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NB | 08W | SH | 2019-01-15 | 2019-01-15 |  | 2019-01-15 |  |  | Yes | 2019-01-15 | [6 empty] | No | [10 empty] | Full |  |  | Full |  |  | total mess | Full |  | Yes |  |  |  | 1980-01-01 | Y | [10 empty] | 1275 | 0.24148 | 0 | 0 | 0.24148 | 0 | 0.24148 | 0 | 0.24148 | 0 | 0 | 0.24148 |  |  |  |  | N/A | [5 empty] | 2019-10-09 | [15 empty] | 9.3867 | [9 empty] | Angwin | Napa | 0 | 0 | 35042719 |  |  |  | 2019 | Q2 |  |  |  |  | Y | SILVERADO 210478268 | 64 | NAPA COUNTY | Yes
35043291 |  | 2020 | 220 Mile Plan | OCGC CWSP- PINE GROVE 1102 LR9145 PH 1.1 |  | FICL | 15523 | 0 | 15171 | 15171 | 2.8733 | 0 | 0 | 0 | 0 | 0 | 0 | -3.4451e-16 |  |  | ST | 08W | SH | 2019-10-18 | 2019-09-20 |  | 2019-09-20 |  |  | Yes | 2019-09-20 | 5/29: 1st ADE submittal on 6/14 6/11: on track for 6/14 submittal 7/8: partial 2nd corrections received 7/16: Directed to work Version 9 - seeking confirmation, or still waiting for remaining corrections,ETA requested 7/16 7/22: Approved for Version 9; Change Order to be Submitted 7/23, w/ New 1st ADE Submittal date (apprx 8/13) 7/24: Via Email - Change Order defined; confirmed 1st ADE submittal date of 8/9 7/30 - 8/6: on track for 8/9 8/9: BCF submitted for 1st ADE Rvw 8/13: In Review - Adding/Add field notes 8/15: In Review - going to keep Loc 1 as is, redlining to have you show this is an existing 55'-H1 pole. The calc will need to be corrected 8/20: 1st ADE Rvw completion scheduled for 8/23 8/26: 1st ADE corrections returned to contractor 9/03: Correction submittal targeted for 9/05 (Thurs) --> [RCC Issue] 9/05: BCF submitted for 2nd ADE Rvw [PRELIM DWG ready] 9/10: In Review 9/14: 2nd ADE corrections rtn to contractor 9/17: Finishing ADE coordination - firmed up target for corrections 9/18 | BCF |  |  | Completed | COMPLETED | No |  | 0 | 0 |  | Yes | [5 empty] | Full |  |  | Full |  |  | Scenic Hwy - Dwg received - Need to consider partial release | Full |  | Yes |  |  | Revised DWG week of 9/3/19. TCP Requested | 1980-01-01 | Y | [10 empty] | 15171 | 2.8733 | 0 | 0 | 2.8733 | -3.4451e-16 | 2.8735 | 0 | 2.8735 | 0 | -0.00018939 | 2.8735 |  | Keep | 2019-10-18 | Yes | COMP | 2019-10-21 11:00 | 2019-12-20 | 2019-12-20 |  |  | 2019-12-20 |  | Yes | Shovel Ready | 3227548.7 | 2630736.1 |  | 3988433.58 | 760884.88 | 596812.6 | 81.5% | 2630736.1 | 0 | 2630736.1 | 0 | 915581.4783 | 93 | [9 empty] | Pine Grove | Amador | 38.4082 | -120.6204 | E.5014680.01 |  |  |  | 2019 | Q1 |  |  |  |  | Y | PINE GROVE 11029145 | 156 | AMADOR COUNTY | Yes
35043299 |  |  |  | CWSP-OH COND RPLC: EEL RIVER 1102 FU1907 |  | ESTS | 6500 | 0 | 6376 | 6376 | 1.2076 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2019-07-11 | 2019-06-20 |  | 2019-06-20 |  |  | Yes | 2019-06-20 | 4/8: Working Job Packages - 4/30 1st ADE submittal target4/17: On track for 4/304/24: 1st ADE submitted5/8: waiting for 1st corrections5/15: waiting for 1st corrections5/22: 1st corrections will be submitted today 5/225/29: waiting for 2nd submittal6/3: 2nd submittal 6/5: waiting for 2nd corrections6/12: ready to route - need to clear DCNL Status6/14: routed, [REDACTED] cannot see approvers on EES6/20: APPROVED | QUES |  |  | Completed | COMPLETED | No |  | 0 | 0 | [7 empty] | Full |  |  | Full |  |  | Prelim drawings provided to ENV - ERTC Received and uploaded | Full |  | Yes |  |  | Annual | 1980-01-01 | Y | [10 empty] | 6376 | 1.2076 | 0 | 0 | 1.2076 | 0 | 1.2076 | 0 | 1.2076 | 0 | 0 | 1.2076 |  |  | 2019-07-11 |  | N/A | 2019-09-09 | 2019-11-27 | 2019-11-27 |  |  | 2019-11-27 |  |  |  | 1224410.6 | 1200956.6 |  | 1224411 | 0.4 | 23454 | 98.08% | 1200956.6 | 0 | 1200956.6 | 0 | 994518.6399 | 9 | [9 empty] | Ferndale | Humboldt | 0 | 0 | 35043299 |  |  |  | 2019 | Q3 |  |  |  |  | Y | EEL RIVER 11024814 | 936 | HUMBOLDT COUNTY | Yes
35043303 |  |  |  | CWSP-OH COND RPLC: EEL RIVER 1102 FU1909 |  | DOCC | 8500 | 0 | 8140 | 8140 | 1.5417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2019-08-02 | 2019-06-04 |  | 2019-06-04 |  |  | Yes | 2019-06-04 | 6/3: APPROVED | QUES |  |  | Completed | COMPLETED | No |  | 0 | 0 | [7 empty] | Full |  |  | Full |  |  | Design sent to enviro in June | Full |  | Yes |  |  | Annual | 1980-01-01 | Y | [10 empty] | 8140 | 1.5417 | 0 | 0 | 1.5417 | 0 | 1.5417 | 0 | 1.5417 | 0 | 0 | 1.5417 |  |  | 2019-08-02 |  | N/A | 2019-08-12 | 2019-09-19 | 2019-09-19 |  |  | 2019-09-19 |  |  |  | 1611982.2 | 1496471.1 |  | 582585.35 | -1029396.85 | 115511.1 | 92.83% | 1496471.1 | 0 | 1496471.1 | 0 | 970683.9568 | 34 | [9 empty] | Ferndale | Humboldt | 40.5118 | -124.1573 | 35043303 |  |  |  | 2019 | Q3 |  |  |  |  | Y | EEL RIVER 1102530 | 2931 | HUMBOLDT COUNTY | Yes
35046371 |  |  |  | ECOP - STANISLAUS 1702 LR 37276 |  | DCNL |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | ST | 08W | [51 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | Remove |  |  | N/A | [31 empty] | Arnold | Calaveras | 0 | 0 | [11 empty] | STANISLAUS 170237276 | 37 | CALAVERAS COUNTY | Yes
35047429 |  |  |  | CWSP - WILLITS 1104 - LR 34008 PH 1 |  | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | HB | 08W | [51 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [31 empty] | Willits | Mendocino | 39.3986 | -123.342 | [11 empty] | WILLITS 110434008 | 50 | MENDOCINO COUNTY | Yes
35049537 |  |  |  | CWSP - BIG BASIN 1102 - 9741 |  | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | CC | 08W | [51 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [31 empty] | Boulder Creek | Santa Cruz | 0 | 0 | [11 empty] | BIG BASIN 11029741 | 419 | SANTA CLARA COUNTY | Yes
35051268 |  |  |  | CWSP - WILLITS 1104 - LR 34008 - PH 2 |  | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | HB | 08W | [51 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [31 empty] | Willits | Mendocino | 39.437 | -123.3898 | [11 empty] | WILLITS 110434008 | 50 | MENDOCINO COUNTY | Yes
35051827 |  |  |  | STS-POLE_DECA_REMV - 44243 ROAD 619AHWAH |  | CLSD |  | 0 | 634 | 634 | 0.12008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2AF |  |  |  | 2019-01-01 | [47 empty] | 634 | 0.12008 | 0 | 0 | 0.12008 | 0 | 0.12008 | 0 | 0.12008 | 0 | 0 | 0.12008 |  |  |  |  | N/A | [5 empty] | 2019-07-01 | [27 empty] | 37.3614 | -119.7348 | [13 empty] | MADERA COUNTY | Yes
35052718 |  |  |  | OCGC CWSP: ANGWIN OH TO UG DEMO - PH 2 |  | CLSD | 0 | 0 | 2265 | 2265 | 0.42898 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NB | 08W | SH | 2019-01-11 | 2019-01-11 |  | 2019-01-11 |  |  | Yes | 2019-01-11 | [6 empty] | No | [10 empty] | Full |  |  | Full |  |  |  | Full |  | Yes |  |  |  | 1980-01-01 | Y | [10 empty] | 2265 | 0.42898 | 0 | 0 | 0.42898 | 0 | 0.42898 | 0 | 0.42898 | 0 | 0 | 0.42898 |  |  |  |  | N/A | [5 empty] | 2019-07-24 | [15 empty] | 0 | [9 empty] | Angwin | Napa | 38.5653 | -122.4416 | 35052718 |  |  |  | 2019 | Q2 |  |  |  |  | Y | SILVERADO 210478268 | 64 | NAPA COUNTY | Yes
35052820 |  | 2020 | 220 Mile Plan | CWSP - MIWUK 1702 - OCB - PH 1.1 |  | FICL | 10715 | 0 | 10619 | 10619 | 2.0112 | 10619 | 2.0112 | 0 | 0 | 0 | 0 | 0 | 10392 | 1.9682 | YO | 08W | SH | 2020-04-15 | 2020-03-19 | 2020-03-19 | 2020-03-19 | 2020-01-10 | 2020-01-10 | Yes | 2020-03-19 | 03/19: ADE rvw - OK TO CONCUR- INTO PEND03/18: QUES submitted for 9th ADE rvw03/13: QUES submitted for 8th ADE rvw; ADE rtn 8th corrections to CO03/11: ADE rtn 8th correction to CO (Standard change, req to move to new standard)03/04: QUES to review for next submittal - coordinating on corrections03/03: QUES submitted for 7th ADE rvw; ADE rtn 7th corrections to CO02/26: ADE/EST checking with [REDACTED] to change to Recloser or stay with SW. OCalc software made slight changes (89.7% to 89.6%) so stamped PDF will not match PPLX files (Change Order to revise and restamp); This is the one with Older version Ocalcs, need instructions from [REDACTED] on how to go back to old version02/26: ADE rtn 6th corrections to CO02/19: Impacted by OCalc upload issue; (numbers being changed in background)02/13: QUES submitted for 6th ADE rvw; ADE request stamped OCALCs to compare02/12: QUES submitted for 5th rvw; ADE return 5th corrections to CO02/08: ADE rtn corrections to CO 02/04: QUES submitted for 4th rvw01/30: ADE rtn 3rd corrections to CO01/28: QUES submitted for 3rd rvw01/22: EST to provide update - push to 1/28..01/17: ADE rtn 2nd corrections to CO01/09: QUES submitted for 2nd rvw - [PRELIM DWG ready]; ADE noted missing some OCALCs, uploaded 1/1001/08: Push to EOW 1/10; EST bandwith (correcting 2 large PMs)12/18 <-- 12/11: Push - Computer Crash/1 week down time - Workload Balance/Priorities12/04: On Track 2nd sub11/27: EST - Prioritizations (est. to firm up sub. date)11/21: ADE rtn 1st corrections to contractor11/12: Design collaboration with ADE/EST ([***] constructability 35116395) - at risk to be pulled back11/06: ADE assigned [REDACTED]10/30: Push 1mth - ADE availabilities10/30: QUES submitted for 1st ADE rvw10/23: On Track 10/16: Push- Resource availability (Stamping 1 PE)10/02: Low RISK of push - estimator added; may mitigate RISK9/25: On Track 1st ADE submittal 10/7Potential Pole Composite Standard Impact - Can remain wood; Some already converted - confirming with ADE whether to convert back or remain as is | QUES |  |  | 2020 - Q1- M2 [R44] | COMPLETED |  | Obsolete (CONS+) | 0 | 0 |  | Yes | [5 empty] | Full |  |  | Full |  |  | CIF submitted on 10/21/19 | Full |  | Yes |  |  | Annual | 1980-01-01 | Y | [10 empty] | 0 | 0 | 10619 | 2.0112 | 2.0112 | 0 | 2.0112 | 0 | 2.015 | 0.0037879 | 0 | 2.0112 |  | Keep | 2020-04-15 | Yes | N/A | 2020-04-24 | 2020-06-11 | 2020-06-11 |  |  | 2020-08-04 |  | Yes | Shovel Ready | 3516246.7 | 5734193.6 |  | 3585097 | 68850.3 | 3399980.9 | 163.1% | 20952.2 | 95313.6 | 116265.8 | 0 | 2851166.9845 | 54 |  | Estimatros computer crashed | [7 empty] | Twain Harte | Tuolumne | 38.0528 | -120.2183 | E.5014773.01 |  |  | 2020-044 | 2020 | Q2 | 2020-02-29 | 2020-06-29 | 2020-08-12 |  | Y | MIWUK 1702CB | 25 | TUOLUMNE COUNTY | Yes
35052822 |  |  |  | CWSP - MIWUK 1701 - LR 8050 |  | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | YO | 08W | [51 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [31 empty] | Twain Harte | Tuolumne | 38.0569 | -120.203 | [11 empty] | MIWUK 17018050 | 45 | TUOLUMNE COUNTY | Yes
35052824 |  |  |  | CWSP - MIWUK 1702 - LR6018 - PH 2 |  | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | YO | 08W | [51 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [31 empty] | Twain Harte | Tuolumne | 38.0594 | -120.268 | [11 empty] | MIWUK 17026018 | 23 | TUOLUMNE COUNTY | Yes
35053033 |  | 2020 | 220 Mile Plan | CWSP - TASSAJARA 2112 - FUSE 18053 |  | CONS | 37377 | 0 | 31154 | 31154 | 5.9004 | 31154 | 5.9004 | 0 | 0 | 0 | 0 | 0 |  |  | DI | 08W | SH | 2019-12-11 | 2019-05-22 | 2021-02-28 | 2019-05-22 |  |  | Yes | 2019-05-22 |  | CONCORD |  |  |  |  | No |  |  |  |  | Yes | [5 empty] | Full |  |  | Full |  |  | State Park Permit Delay - Critical Habbitat | Full |  | Yes |  |  | Received message from CCC that this is a private road so no permit is needed. | 1980-01-01 | Y | [10 empty] | 0 | 0 | 31154 | 5.9004 | 5.9004 | 0 | 5.9042 | 0 | 5.9042 | 0 | -0.0037879 | 5.9042 |  | Keep | 2019-12-11 | Yes | N/A | 2019-12-03 | 2020-06-04 | 2020-06-04 | 2021-01-13 07:00 | 2021-01-13 16:00 |  |  | Yes | Shovel Ready | 9709000 | 6700482.1 |  | 9709000 | 0 | 8905742 | 69.01% | 783087.3 | 20170.7 | 803258 | 0 | 1135602.025 | 113 | [9 empty] | Danville | Contra Costa | 37.8359 | -121.9505 | E.5014753.01 |  |  | 2020-091 | 2020 | Q1 | 2019-05-22 | 2020-12-18 | 2021-06-30 |  | Y | TASSAJARA 2112D514R | 1556 | CONTRA COSTA COUNTY | Yes
35054959 |  |  |  | STS-POLE_IDLE_REMV - 4215 HOLLIS LN FIDD |  | CLSD |  | 0 | 406 | 406 | 0.076894 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2AF | [51 empty] | 406 | 0.076894 | 0 | 0 | 0.076894 | 0 | 0.076894 | 0 | 0.076894 | 0 | 0 | 0.076894 |  |  |  |  | N/A | [5 empty] | 2019-01-12 | [27 empty] | 38.5424 | -120.693 | [13 empty] | AMADOR COUNTY | Yes
35055289 |  |  |  | STS-POLE_DECA_REPL - 6999 ARROYO RDLIVER |  | CONS |  | 0 | 314 | 314 | 0.05947 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2AF |  |  |  | 2019-04-13 | [47 empty] | 314 | 0.05947 | 0 | 0 | 0.05947 | 0 | 0.05947 | 0 | 0.05947 | 0 | 0 | 0.05947 |  |  |  |  | N/A | [31 empty] | Livermore | Alameda | 37.6057 | -121.7497 | [13 empty] | ALAMEDA COUNTY | Yes
35055474 |  |  |  | OCGC REDBUD 1101 RECONDUCTOR FOR NB LOAD |  | CLSD | 7186 | 0 | 7555 | 7555 | 1.4309 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | HB | 06H | SH | 2019-06-20 | 2019-06-20 |  | 2019-06-20 |  |  | Yes | 2019-06-20 | [6 empty] | No | [10 empty] | Full |  |  | Full |  |  | Enviro fielding week of 7/15 | Full |  | Yes |  |  |  | 1980-01-01 | Y | [10 empty] | 7555 | 1.4309 | 0 | 0 | 1.4309 | 0 | 1.4309 | 0 | 1.4309 | 0 | 0 | 1.4309 |  |  |  |  | N/A | [5 empty] | 2019-12-13 |  | Yes | [13 empty] | 25 | [9 empty] | Clearlake Oaks | Lake | 39.024 | -122.6783 | 35055474 |  |  |  | 2019 | Q3 |  |  |  |  | Y |  |  | LAKE COUNTY | Yes
35056433 |  |  |  | CWSP - PLACERVILLE 2106 - LR 1104 - PH 2 |  | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | [51 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [9 empty] | 0 | 14741.2 |  | 1 | 1 | -14741.2 |  | 14741.2 | 0 | 14741.2 | 0 | [11 empty] | Georgetown | El Dorado | 38.8989 | -120.7975 | [10 empty] | Y | PLACERVILLE 21061104 | 16 | EL DORADO COUNTY | Yes
35056434 |  |  |  | CWSP - PLACERVILLE 2106 - LR 1104 - PH 3 |  | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | [51 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [31 empty] | Georgetown | El Dorado | 38.8989 | -120.7975 | [11 empty] | PLACERVILLE 21061104 | 16 | EL DORADO COUNTY | Yes
35056435 |  |  |  | CWSP - PLACERVILLE 2106 - LR 1104 - PH 4 |  | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | [51 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [31 empty] | Georgetown | El Dorado | 38.8989 | -120.7975 | [11 empty] | PLACERVILLE 21061104 | 16 | EL DORADO COUNTY | Yes
35056438 |  |  |  | CWSP - PLACERVILLE 2106 - LR 1104 - PH 5 |  | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | [51 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [31 empty] | Georgetown | El Dorado | 38.8989 | -120.7975 | [11 empty] | PLACERVILLE 21061104 | 16 | EL DORADO COUNTY | Yes
35056439 |  |  |  | CWSP - PLACERVILLE 2106 - LR 1104 - PH 6 |  | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | [51 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [31 empty] | Georgetown | El Dorado | 38.8989 | -120.7975 | [11 empty] | PLACERVILLE 21061104 | 16 | EL DORADO COUNTY | Yes
35057017 |  |  |  | CWSP - EL DORADO 2101 - 19752 - PH 3.1 |  | DOCC | 8569 | 0 | 9006 | 9006 | 1.7057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | SH | 2019-09-18 | 2019-08-27 | 2020-10-31 | 2019-08-27 |  |  | Yes | 2019-08-27 | 8/6: [REDACTED] - I have it in to me for approval, but there is an issue with the JP credits in EES , call into estimating support to resolve. When resolved it will be put through.8/20: No response from support entities to-date8/22: 16 LOCs exhibiting errors/ OCALC/ Est. issues - to be corrected and PE stamped8/26: BCF submitted for 2nd ADE rvw [PRELIM DWG ready]8/27:APPROVED - PEND | BCF |  |  | Completed | COMPLETED | No |  | 0 | 0 | [7 empty] | Full |  |  | Full |  |  | CIF Submitted 8/1/19. Expedite if OH | Full |  | Yes | 2019-12-30 |  | Permit Request sent 8/1/19 | 1980-01-01 | Y | [10 empty] | 9006 | 1.7057 | 0 | 0 | 1.7057 | 0 | 1.7057 | 0 | 1.7057 | 0 | 0 | 1.7057 |  |  | 2019-09-18 |  | N/A | 2019-09-19 | 2019-12-03 | 2019-12-03 |  |  | 2019-12-03 |  |  |  | 3201494.4 | 3116530.6 |  | 3201494 | -0.4 | 195429.5 | 97.34% | 2818543.8 | 187521.1 | 3006064.9 | 0 | 1827146.521 | 43 | [9 empty] | Pollock Pines | El Dorado | 38.7821 | -120.6094 | E.5015415.01 | ML |  |  | 2019 | Q4 |  |  |  |  | Y | EL DORADO PH 210119752 | 13 | EL DORADO COUNTY | Yes
35058267 |  |  |  | IDLE FACILITY-R/O15140 GOLD DUST VOLCANO |  | CLSD |  | 0 | 610 | 610 | 0.11553 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2AF | [51 empty] | 610 | 0.11553 | 0 | 0 | 0.11553 | 0 | 0.11553 | 0 | 0.11553 | 0 | 0 | 0.11553 |  |  |  |  | N/A | [5 empty] | 2018-10-24 | [25 empty] | Kit Carson | Amador | 38.4252 | -120.611 | [13 empty] | AMADOR COUNTY | Yes
35058273 |  |  |  | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 |  | CONS | 6215 | 0 | 6215 | 6215 | 1.1771 | 6215 | 1.1771 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | SH | 2020-04-09 | 2019-09-17 | 2019-09-21 | 2019-09-17 |  |  | Yes | 2019-09-17 | (Moved into 2019) 7/10 - 8/14: on with 8/16 submittal 8/16: EEI submitted for 1st ADE rvw 9/04: ADE TBD 9/10: ADE review returned to contractor 9/12: EEI submitted for 2nd ADE review [PRELIM DWG ready] 9/12: ADE approved | EEI |  |  | Completed | COMPLETED | No |  | 0 | 0 |  | Yes | [5 empty] | Full |  |  | Full |  |  | Submitted to forest service week of 12/10 | Full |  | Yes |  |  | No permit needed | 1980-01-01 | Y |  |  |  | Complete | [6 empty] | 0 | 0 | 6215 | 1.1771 | 1.1771 | 0 | 1.1771 | 0 | 1.1771 | 0 | 0 | 1.1771 |  | Keep | 2020-04-09 | Yes | N/A | 2020-03-09 08:00 | 2020-06-26 08:00 | 2021-01-15 17:00 |  |  |  |  | Yes | Shovel Ready | 3559342.7 | 3956055.8 |  | 4515047 | 955704.3 | 3154279.8 | 111.1% | 39900.3 | 365162.6 | 405062.9 | 0 | 3360896.9628 | 32 | [6 empty] | No SCADA |  |  | Pollock Pines | El Dorado | 38.7883 | -120.6157 | E.5015420.01 |  |  |  | 2020 | Q2 | 2019-09-17 | 2020-03-16 | 2020-06-20 |  | Y | EL DORADO PH 2101CB | 76 | EL DORADO COUNTY | Yes
35058905 |  | 2020 | 220 Mile Plan | CWSP - VOLTA 1102 - LR 1648 -PH 4.1 |  | DOCC | 11306 | 0 | 11145 | 11145 | 2.1108 | 3971 | 0.75208 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 08W | SH | 2020-03-10 17:00 | 2019-08-30 | 2019-09-14 | 2019-08-30 |  |  | Yes | 2019-08-30 | (Moved into 2019)7/3 - 7/24: On track for 8/98/9: EEI Submitted fr 1st ADE Review - ADE [REDACTED]8/14: ADE assigned - [REDACTED]8/19: 1st ADE corrections rtn to contractor8/21: EEI submitted for 2nd ADE rvw [PRELIM DWG ready]8/26: 2nd ADE corrections rtn to contractor - (minor corrections) | EEI |  |  | Completed | COMPLETED | No |  | 0 | 0 |  | Yes | [5 empty] | Full |  |  | Full |  |  | CIF submitted 8/16/19. Caltrans Permit | Full |  | Yes |  |  | Shasta County Annual | 1980-01-01 | Y | [10 empty] | 7174 | 1.3587 | 3971 | 0.75208 | 2.1108 | 0 | 2.1108 | 0 | 2.1108 | 0 | 0 | 2.1108 |  | Keep | 2020-03-10 17:00 | Yes | N/A | 2019-11-05 | 2020-01-16 | 2020-01-16 |  |  | 2020-01-16 |  | Yes | Shovel Ready | 5085298 | 4158869.3 |  | 5418545 | 333247 | 978173.7 | 81.78% | 4008922.6 | 98201.7 | 4107124.3 | 0 | 1970285.3211 | 57 | [9 empty] | Shingletown | Shasta | 40.518 | -121.7552 | E.5015428.01 |  |  | 2020-186 | 2020 | Q1 | 2019-08-30 | 2019-11-19 | 2020-01-16 |  | Y | VOLTA 11029742 | 229 | SHASTA COUNTY | Yes
35060229 |  |  |  | 2018 OH COND RPLC: FRUITLAND 42 C/O 7449 |  | CLSD | 8300 | 0 | 6529 | 6529 | 1.2366 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2019-03-11 | 2019-03-06 |  | 2019-03-06 |  |  | Yes | 2019-03-06 | 3/4: Pending Ocals to be signed then will route for EDRS approval | EEI |  |  | Completed | COMPLETED | No |  | 0 | 0 | [7 empty] | Full |  |  | Full |  |  |  | Full |  | Yes |  |  | Annual | 1980-01-01 | Y | [10 empty] | 6529 | 1.2366 | 0 | 0 | 1.2366 | 0 | 1.2366 | 0 | 1.2366 | 0 | 0 | 1.2366 |  |  | 2019-03-11 |  | N/A | 2019-07-22 | 2019-07-29 | 2019-07-29 |  |  | 2019-07-30 | [15 empty] | 38 | [9 empty] | Miranda | Humboldt | 0 | 0 | 35060229 |  |  |  | 2019 | Q2 |  |  |  |  | Y | FRUITLAND 11422006 | 1841 | HUMBOLDT COUNTY | Yes
35060582 |  |  |  | SLO 1107 RECOD 3884 FT WITH 2CU TW |  | FICL | 3836 | 0 | 3884 | 3884 | 0.73561 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | LP | 08W | SH | 2019-03-06 | 2019-03-06 |  | 2019-03-06 |  |  | Yes | 2019-03-06 | 3/6: 3rd ADE Submitted | CAL |  |  | Completed | COMPLETED | No |  | 0 | 0 | [7 empty] | Full |  |  | Full |  |  | ERTC released | Full |  | Yes |  |  | [REDACTED] to confirm that annual should cover this work | 1980-01-01 | Y | [10 empty] | 3884 | 0.73561 | 0 | 0 | 0.73561 | 0 | 0.73561 | 0 | 0.73561 | 0 | 0 | 0.73561 |  |  |  |  | N/A | [5 empty] | 2019-10-09 | [15 empty] | 13 | [9 empty] | Oceano | San Luis Obispo | 35.1938 | -120.6781 | 35060582 |  |  |  | 2019 | Q3 | [5 empty] | SAN LUIS OBISPO 1107V02 | 1250 | San Luis Obispo County | Yes
35061213 |  | 2020 | 220 Mile Plan | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH3 |  | FICL | 10043 | 0 | 7099 | 7099 | 1.3445 | 7099 | 1.3445 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | SH | 2020-05-01 | 2020-02-14 | 2020-02-14 | 2020-02-14 | 2019-11-04 | 2019-11-04 | Yes | 2020-02-14 | 03/02: INTO PEND02/13: still shows a high validation error in EES that prevents me from routing for approval; submitted a mapping correction to ED WebViewer; told they cannot correct issues related to PLDBIDs 02/05: PIKE submitted final corrections02/03: Final corrections rtn to CO01/30: EES validation error resolved01/28: Another ticket submitted 1/24 - reappearance of error01/21: EN to forward communications to [REDACTED] for assistance. IT shifting back and forth between grps for support.01/14: Push 1wk EOD: EST SPPT in progress01/06: EES validations issues - escalating to EST support to resolve.12/17: QC - inconsistencies with sequences - Coordinated with ADE, refielding: Routing by EOD 12/1812/06: ADE rtn 4th corrections to contractor - apply and route.12/05: PIKE submitted for 4th ADE rvw12/05:ADE rtn 3rd corrections to contractor11/20: PIKE submitted for 3rd ADE rvw11/19: On Track (or earlier) - ADE heading to vaca11/15: ADE rtn 2nd corrections to contractor11/12: Follow up with ADE on target11/04: PIKE submitted for 2nd ADE rvw10/29: On Track for 11/01; clearing up comment (Pole/High wind load...) w/ [REDACTED].10/22: Push 1 week - Est workload/prioritization10/18: ADE returned 1st corrections to contractor10/09: ADE assigned [REDACTED] - push 1wk for rvw duration (2wk)10/08: ADE to be assigned10/01: PIKE to forward submittal to [REDACTED] - To confirm ADE and availabilities9/23: PIKE submitted for 1st ADE rvw8/27 - 9/17: On track8/20: 1st Submittal push 2wks - Priorities/Equip-Resource Availabilities8/13: PIKE communicated potential pressures on 1st ADE submittal targets, due to computer availabilities and technical issues: (IE: Token malfunctions; SAP Access issues) - working through issues with TSC on case by case basis 7/23 - 8/6: On Track for 9/67/19: Vendor Provided 1st ADE Sub dates7/16: Vendor Request for 1st ADE Submittal7/15: Sub Order issued[Version 8] | PIKE |  |  | 2020 - Q1- M2 [R138] | COMPLETED | No | Obsolete (CONS+) | 0 | 0 |  | Yes | [5 empty] | Full |  |  | Full |  |  | ERTC Call 1/10/2020 | Full |  | Yes |  |  | Drawings submitted 1/7/2020 & 1/14/2020 | 2020-06-17 | Y | 2020-05-01 |  |  | Started | [6 empty] | 0 | 0 | 7099 | 1.3445 | 1.3445 | 0 | 1.3445 | 0 | 1.4511 | 0.10663 | 0 | 1.3445 |  | Keep | 2020-05-01 | Yes | N/A | 2020-05-18 | 2020-08-14 | 2020-08-14 |  |  | 2020-08-14 |  | Yes | Shovel Ready | 4177343.8 | 1672181 | -212915 | 6076529 | 1899185.2 | 4164232.2 | 40.02% | 13111.6 | 0 | 13111.6 | 0 | 1243712.5905 | 51 | [9 empty] | Nevada City | Nevada | 0 | 0 | E.5015567.01 |  |  | 2020-138 | 2020 | Q3 | 2020-02-29 | 2020-06-01 | 2020-07-24 |  | Y | BRUNSWICK 110350070 | 7 | NEVADA COUNTY | Yes
35061709 |  |  |  | SILVERADO 2104 RECONDUCTOR PROJECT |  | DOCC | 8800 | 0 | 8003 | 8003 | 1.5157 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NB | 08W | SH | 2019-08-15 | 2019-02-26 |  | 2019-02-26 |  |  | Yes | 2019-02-26 | [6 empty] | No | [10 empty] | Full |  |  | Full |  |  | Undergrounding redesign in process. Once completed will provide to ENV team / Need laydown | Full |  | Yes |  |  | Approved through May 2020 | 1980-01-01 | Y | [10 empty] | 8003 | 1.5157 | 0 | 0 | 1.5157 | 0 | 1.5157 | 0 | 1.6388 | 0.12311 | 0 | 1.5157 |  |  | 2019-08-15 |  | N/A | 2019-10-23 | 2019-12-14 | 2019-12-14 | [6 empty] | 50000 | 6182513.4 |  | 583061.25 | 533061.25 | -4162528.7 | 12365% | 4212528.7 | 0 | 4212528.7 | 0 | 4078929.2455 | 35 | [9 empty] | Angwin | Napa | 38.5567 | -122.4932 | 35061709 |  |  |  | 2019 | Q2 |  |  |  |  | Y | SILVERADO 2104563322 | 295 | NAPA COUNTY | Yes
35061811 |  |  |  | CWSP-EL DORADO PH 2102 LR19542 PH 1.1 |  | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | [51 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | INPR | [9 empty] | 100000 | 6647.5 |  | 100000 | 0 | 93352.5 | 6.64% | 6647.5 | 0 | 6647.5 | 0 | [13 empty] | 0 | 0 |  |  |  |  | 999 | [5 empty] | Y | EL DORADO PH 210219542 | 41 | EL DORADO COUNTY | Yes
35062127 |  |  |  | *FT-OFAC_IDLE_REMV - 5000 HWY 49COOL |  | FICL |  | 0 | 6011 | 6011 | 1.1384 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2AF | [51 empty] | 6011 | 1.1384 | 0 | 0 | 1.1384 | 0 | 1.1384 | 0 | 1.1384 | 0 | 0 | 1.1384 |  |  |  |  | N/A | [5 empty] | 2019-09-15 | [27 empty] | 38.85 | -120.9828 | [13 empty] | EL DORADO COUNTY | Yes
35064793 |  |  |  | LP RECONDUCTOR, CABRILLO 1104 S006CC102 |  | FICL | 17020 | 0 | 12142 | 12142 | 2.2996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | LP | 08W | SH | 2019-06-25 | 2019-02-25 |  | 2019-02-25 |  |  | Yes | 2019-02-25 | [6 empty] | No | [10 empty] | Full |  |  | Full |  |  | ERTC released, need land task completion. Need ERTC call | Full |  | Yes |  |  | Permit expires 10/12 | 1980-01-01 | Y | [10 empty] | 12142 | 2.2996 | 0 | 0 | 2.2996 | 0 | 2.2996 | 0 | 2.2996 | 0 | 0 | 2.2996 |  |  | 2019-06-25 |  | N/A | 2019-07-12 08:00 | 2019-08-26 | 2019-08-26 17:00 |  |  | 2019-08-26 | [15 empty] | 75.6444 | [9 empty] | Lompoc | Santa Barbara | 34.6451 | -120.5194 | E.5015545.01 |  |  |  | 2019 | Q2 | [5 empty] | CABRILLO 1104Y22 | 2531 | SANTA BARBARA COUNTY | Yes
35065058 |  |  |  | STS-POLE_IDLE_REMV - BETWEEN 1860 & 1850 |  | CLSD |  | 0 | 530 | 530 | 0.10038 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2AF |  |  |  | 2019-05-10 | [47 empty] | 530 | 0.10038 | 0 | 0 | 0.10038 | 0 | 0.10038 | 0 | 0.10038 | 0 | 0 | 0.10038 |  |  |  |  | N/A | [5 empty] | 2019-08-23 | [27 empty] | 38.6055 | -120.8122 | [13 empty] | EL DORADO COUNTY | Yes
35066689 |  |  |  | OCLH STS-OFAC_IDLE_REMV-16275 HWY 88 |  | CLSD |  | 0 | 103 | 103 | 0.019508 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2AF |  |  |  | 2019-01-17 | [47 empty] | 103 | 0.019508 | 0 | 0 | 0.019508 | 0 | 0.019508 | 0 | 0.019508 | 0 | 0 | 0.019508 |  |  |  |  | N/A | [5 empty] | 2019-04-29 | [27 empty] | 38.3643 | -120.7245 | [13 empty] | AMADOR COUNTY | Yes
35066745 |  |  |  | BIG BEND 1102 - BLOOMER HILL 08W PHS 2 |  | CLSD | 9160 | 0 | 8900 | 8900 | 1.6856 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 08W | SH | 2019-05-25 | 2019-05-25 | 2019-04-12 | 2019-05-25 |  |  | Yes | 2019-05-25 | 5/25: COMPLETED6/5: minor corrections needed to be made after approval. [REDACTED] moved back into ESTS for CAL to complete by 6/5. Job was in PEND, and will be in PEND again by 6/76/12: Approved and in PEND Status | CAL |  |  | Completed | COMPLETED | No |  | 0 | 0 | [7 empty] | Full |  |  | Full |  |  | Poles 1 - 17 are in DWR. SSSP provided. Partial ERTC released 7/17/19 | Full |  | Yes |  |  | Not required - See long text 2/20 | 1980-01-01 | Y | [10 empty] | 8900 | 1.6856 | 0 | 0 | 1.6856 | 0 | 1.6856 | 0 | 1.6856 | 0 | 0 | 1.6856 |  |  |  |  | N/A | [5 empty] | 2019-11-21 | [15 empty] | 36 | [9 empty] | Corning | Tehama | 0 | 0 | 35066745 |  |  |  | 2019 | Q4 |  |  |  |  | Y | BIG BEND 1102CB | 1094 | TEHAMA COUNTY | Yes
35067619 |  |  |  | CWSP - MONTE RIO 1112 - LR 120 |  | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 08W | [51 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [31 empty] | Monte Rio | Sonoma | 0 | 0 | [11 empty] | MONTE RIO 1112120 | 54 | SONOMA COUNTY | Yes
35072146 |  |  |  | RPL 17,500' 4AR TIER 3 SILVERADO 2105 |  | DOCC | 3654 | 0 | 3684 | 3684 | 0.69773 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NB | 08W | SH | 2019-06-12 | 2019-06-12 |  | 2019-06-12 |  |  | Yes | 2019-06-12 | [5 empty] | 100 | No | [10 empty] | Full |  |  | Full |  |  | estimation received. Currently under review | Full |  | Yes | 2020-12-31 |  | Submitted Permit Req & Dwg on 6/25. Permit App sent on 7/9/2019 Napa Co approved, St. Helena pending as of 7/23 | 1980-01-01 | Y | [10 empty] | 3684 | 0.69773 | 0 | 0 | 0.69773 | 0 | 0.69773 | 0 | 0.69773 | 0 | 0 | 0.69773 |  |  |  |  | N/A | [5 empty] | 2019-12-17 |  |  |  | 2410000.1 | 4320878.8 |  | 2410000 | -0.1 | 657117.4 | 179.3% | 1752882.7 | 0 | 1752882.7 | 0 | 6192790.4625 | 18 | [9 empty] | Saint Helena | Napa | 38.5229 | -122.5312 | E.5014317.01 |  |  |  | 2019 | Q3 |  |  |  |  | Y | SILVERADO 2105658898 | 104 | NAPA COUNTY | Yes
35072362 |  |  |  | CWSP-OH COND RPLC: EEL RIVER 1102 FU1913 |  | CLSD | 15000 | 0 | 14292 | 14292 | 2.7068 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2019-08-30 | 2019-08-30 | 2019-08-20 | 2019-08-30 |  |  | Yes | 2019-08-30 | 5/22: 1st ADE submittal by 6/146/12: majority of the work have been completed for 1st submittal. A small portion of the job is inaccessible due to river depth and flow - will push 1st submittal6/19: still access issue with the river - may delay to late fall7/3: QUES to follow up on access issues7/16: QUES Fielded - Submittal planned for 7/197/22: 1st ADE Submitted for review7/31: Awaiting ADE Review/corrections - [REDACTED]; 7/29 1st ADE review completed and returned to Vendor8/6: Contractor working through correction items with ADE8/7: Corrections returned to contractor8/20: 2nd ADE Submitted for review [PRELIM DWG ready]8/20: 2nd ADE corrections rtn to contractor8/23 QUES submitted for 3rd ADE rvw9/04: IN PEND | QUES |  |  | Completed | COMPLETED | No |  | 0 | 0 | [7 empty] | Full |  |  | Full |  |  |  | Full |  | Yes |  |  | Annual | 1980-01-01 | Y | [10 empty] | 14292 | 2.7068 | 0 | 0 | 2.7068 | 0 | 2.7068 | 0 | 2.7068 | 0 | 3.4451e-16 | 2.7068 |  |  |  |  | N/A | [5 empty] | 2019-12-21 | [15 empty] | 45 | [9 empty] | Ferndale | Humboldt | 40.4516 | -124.2697 | E.5014735.01 |  |  |  | 2019 | Q4 |  |  |  |  | Y | EEL RIVER 11024814 | 936 | HUMBOLDT COUNTY | Yes
35072720 |  |  |  | RPL OH WIRE ON GABILN 1101 17-0077248 |  | CLSD | 11795 | 0 | 11745 | 11745 | 2.2244 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | CC | 08W | SH | 2019-06-20 | 2019-06-20 |  | 2019-06-20 |  |  | Yes | 2019-06-20 | 2/25: QUES working on Job, fielding this week3/4: Fielding completed last week3/7: ADE assigned3/11: QUES working on Job package3/20 - 4/3: 4/11 1st ADE submittal date - on track4/8: On track for 1st ADE submittal on 4/114/11: 1st ADE submitted - [REDACTED] to review5/1: [REDACTED] to send corrections any day5/8: waiting on 1st corrections- 1st corrections estimated by 5/105/15: 1st correction 5/10. Job needs to be refielded due 200' interset spec. QUES to follow up on 2nd submittal5/22: QUES to follow up on 2nd submittal - waiting for [REDACTED] to approve locations for interset5/29: Recevied answer on refield on 5/24, estimator will start working on today5/31: submitted6/4: 2nd corrections sent by [REDACTED]6/5: EDRS ready6/10: Rerouted6/19: [REDACTED] to approve EDRS reroute6/20: APPROVED | QUES |  |  | Completed | COMPLETED | No |  | 0 | 0 | [7 empty] | Full |  |  | Full |  |  | Bio review of 4 poles in water way. [REDACTED] will be talking to [REDACTED] to review. Walkdown 7/23/19. [REDACTED] to review | Full |  | Yes |  |  | Annual permit | 1980-01-01 | Y | [10 empty] | 11745 | 2.2244 | 0 | 0 | 2.2244 | 0 | 2.2244 | 0 | 2.2244 | 0 | 0 | 2.2244 |  |  |  |  | N/A | [5 empty] | 2020-01-14 | [15 empty] | 61 | [9 empty] | Salinas | Monterey | 36.6615 | -121.5473 | E.5015593.01 |  |  |  | 2019 | Q4 |  |  |  |  | Y | GABILAN 11013090 | 747 | MONTEREY COUNTY | Yes
35073525 |  | 2020 |  | BUCOCAMP - 6265 AZALEA LN PARADISE |  | CLSD |  | 0 | 2027 | 2027 | 0.3839 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 95F | [51 empty] | 2027 | 0.3839 | 2112 | 0.4 | 0.7839 | -0.4 | 0.40284 | 0 | 0.40284 | 0 | 0.38106 | 0.40284 |  |  |  |  | N/A | [5 empty] | 2019-03-14 | [27 empty] | 39.7719 | -121.6019 |  |  |  |  | 2019 | [8 empty] | BUTTE COUNTY | Yes
35076188 |  | 2020 |  | BUCOCAMP - 5275 SKYWAY PARADISE |  | FICL |  | 0 | 229 | 229 | 0.043371 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 95F | [51 empty] | 229 | 0.043371 | 0 | 0 | 0.043371 | 0 | 0.039205 | 0 | 0.039205 | 0 | 0.0041667 | 0.039205 |  |  |  |  | N/A | [5 empty] | 2019-05-27 | [27 empty] | 39.7477 | -121.6375 |  |  |  |  | 2019 | [8 empty] | BUTTE COUNTY | Yes
35077252 |  | 2020 |  | BUCOCAMP - 1658 HUCKA LN PARADISE |  | CLSD |  | 0 | 563 | 563 | 0.10663 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 95F | [51 empty] | 563 | 0.10663 | 0 | 0 | 0.10663 | 0 | 0.10663 | 0 | 0.10663 | 0 | 0 | 0.10663 |  |  |  |  | N/A | [5 empty] | 2019-04-11 | [27 empty] | 39.7916 | -121.5854 |  |  |  |  | 2019 | [8 empty] | BUTTE COUNTY | Yes
35077480 |  | 2020 |  | BUCOCAMP - 5220 FOSTER RD PARADISE |  | CLSD |  | 0 | 1165 | 1165 | 0.22064 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 95F | [51 empty] | 1165 | 0.22064 | 0 | 0 | 0.22064 | 0 | 0.22064 | 0 | 0.22064 | 0 | 0 | 0.22064 |  |  |  |  | N/A | [5 empty] | 2019-03-30 | [27 empty] | 39.738 | -121.6306 |  |  |  |  | 2019 | [8 empty] | BUTTE COUNTY | Yes
35077549 |  | 2020 |  | BUCOCAMP - 1797 STARK LN PARADISE |  | CLSD |  | 0 | 270 | 270 | 0.051136 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 95F | [51 empty] | 270 | 0.051136 | 0 | 0 | 0.051136 | 0 | 0.051136 | 0 | 0.051136 | 0 | 0 | 0.051136 |  |  |  |  | N/A | [5 empty] | 2019-04-11 | [27 empty] | 39.7742 | -121.5764 |  |  |  |  | 2019 | [8 empty] | BUTTE COUNTY | Yes
35078144 |  |  |  | STS-TRAN_IDLE_REMV - SIERRA NATIONAL FOR |  | CLSD |  | 0 | 450 | 450 | 0.085227 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2AF | [51 empty] | 450 | 0.085227 | 0 | 0 | 0.085227 | 0 | 0.085227 | 0 | 0.085227 | 0 | 0 | 0.085227 |  |  |  |  | N/A | [5 empty] | 2019-09-16 | [27 empty] | 37.0566 | -119.3751 | [13 empty] | FRESNO COUNTY | Yes
35078728 |  |  |  | COND_IDLE_REMV-17351 TRINITY MOUNTAI |  | CLSD |  | 0 | 193 | 193 | 0.036553 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2AF | [51 empty] | 193 | 0.036553 | 0 | 0 | 0.036553 | 0 | 0.036553 | 0 | 0.036553 | 0 | 0 | 0.036553 |  |  |  |  | N/A | [5 empty] | 2019-08-30 | [27 empty] | 40.7906 | -122.6151 | [13 empty] | SHASTA COUNTY | Yes
35078734 |  |  |  | COND_IDLE_REMV-16333 TRINITY MOUNTAI |  | FICL |  | 0 | 337 | 337 | 0.063826 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2AF | [51 empty] | 337 | 0.063826 | 0 | 0 | 0.063826 | 0 | 0.063826 | 0 | 0.063826 | 0 | 0 | 0.063826 |  |  |  |  | N/A | [5 empty] | 2019-08-30 | [27 empty] | 40.7634 | -122.6102 | [13 empty] | SHASTA COUNTY | Yes
35078820 |  | 2020 |  | BUCOCAMP - 820 COLLEGE HILL RD PARADISE |  | CLSD |  | 0 | 462 | 462 | 0.0875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 95F | [51 empty] | 462 | 0.0875 | 0 | 0 | 0.0875 | 0 | 0.0875 | 0 | 0.0875 | 0 | -1.0766e-17 | 0.0875 |  |  |  |  | N/A | [5 empty] | 2019-04-10 | [27 empty] | 39.7509 | -121.6182 |  |  |  |  | 2019 | [8 empty] | BUTTE COUNTY | Yes
35080227 |  |  |  | CALISTOGA 1101 - BENNETT LN RECONDUCTOR |  | UNSE |  | 0 | 1876 | 1876 | 0.3553 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NB | 08W | SH | [50 empty] | 1876 | 0.3553 | 0 | 0 | 0.3553 | 0 | 0.3553 | 0 | 0.3553 | 0 | 0 | 0.3553 |  |  |  |  | N/A | [31 empty] | Calistoga | Napa | 0 | 0 |  |  |  |  | 2019 | [6 empty] | CALISTOGA 1101734 | 882 | NAPA COUNTY | Yes
35080391 |  | 2020 |  | BUCOCAMP - 6650 PENTZ RD PARADISE |  | CLSD |  | 0 | 1159 | 1159 | 0.21951 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 95F | [51 empty] | 1159 | 0.21951 | 0 | 0 | 0.21951 | 0 | 0.21951 | 0 | 0.21951 | 0 | 0 | 0.21951 |  |  |  |  | N/A | [5 empty] | 2019-05-14 | [27 empty] | 39.7778 | -121.5799 |  |  |  |  | 2019 | [8 empty] | BUTTE COUNTY | Yes
35081535 |  |  |  | BUCOCAMP - 785 SECLUDED LN PARADIS*COMP* |  | CLSD |  | 0 | 556 | 556 | 0.1053 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 95F | [51 empty] | 556 | 0.1053 | 0 | 0 | 0.1053 | 0 | 0.074242 | 0 | 0.074242 | 0 | 0.031061 | 0.074242 |  |  |  |  | N/A | [5 empty] | 2019-09-23 | [27 empty] | 39.7755 | -121.6221 |  |  |  |  | 2019 | [8 empty] | BUTTE COUNTY | Yes
35081665 |  | 2020 |  | BUCOCAMP - 732 WILLOW ST PARADISE |  | CLSD |  | 0 | 137 | 137 | 0.025947 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 95F | [51 empty] | 137 | 0.025947 | 0 | 0 | 0.025947 | 0 | 0.025947 | 0 | 0.025947 | 0 | 0 | 0.025947 |  |  |  |  | N/A | [5 empty] | 2019-04-23 | [27 empty] | 39.7572 | -121.6223 |  |  |  |  | 2019 | [8 empty] | BUTTE COUNTY | Yes
35081674 |  | 2020 |  | BUCOCAMPT 5615 NEWLAND RD PARADISE*ILB |  | MAPP |  | 0 | 254 | 254 | 0.048106 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 95F | [51 empty] | 254 | 0.048106 | 158 | 0.029924 | 0.07803 | -0.029924 | 0.076136 | 0 | 0.076136 | 0 | 0.0018939 | 0.076136 |  |  |  |  | N/A | [5 empty] | 2019-12-07 | [27 empty] | 39.7523 | -121.6026 |  |  |  |  | 2019 | [8 empty] | BUTTE COUNTY | Yes
35081676 |  | 2020 |  | BUCOCAMP 5708 ROUND TREE DR PARADISE |  | CLSD |  | 0 | 504 | 504 | 0.095455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 95F | [51 empty] | 504 | 0.095455 | 0 | 0 | 0.095455 | 0 | 0.095455 | 0 | 0.095455 | 0 | 0 | 0.095455 |  |  |  |  | N/A | [5 empty] | 2019-06-18 | [25 empty] | Paradise | Butte | 39.7544 | -121.5962 |  |  |  |  | 2019 | [8 empty] | BUTTE COUNTY | Yes
35081748 |  | 2020 | 220 Mile Plan | OH RECONDUCTOR - ROB ROY 2105 -S028CC119 |  | CLSD | 1617 | 0 | 850 | 850 | 0.16098 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | CC | 08W | SH | 2019-03-20 | 2019-03-20 |  | 2019-03-20 |  |  | Yes | 2019-03-20 | [6 empty] | No |  |  |  |  | Yes | [5 empty] | Full |  |  | Full |  |  | Partial ERTC released. Redwood tree conflict | Full |  | Yes |  |  | Sent follow up to PF re permit status. Site specific TCP requested. Caltrans - No Encroachment needed | 1980-01-01 | Y | [10 empty] | 850 | 0.16098 | 0 | 0 | 0.16098 | 0 | 0.16098 | 0 | 0.16098 | 0 | 0 | 0.16098 |  | Keep |  | Yes | N/A | [5 empty] | 2020-02-19 |  | Yes | Shovel Ready | 632820 | 608138.6 |  | 713114 | 80294 | 24681.4 | 96.09% | 608138.6 | 0 | 608138.6 | 0 | 3777613.8918 | 9 | [9 empty] | Aptos | Santa Cruz | 36.9734 | -121.9038 | 35081748 |  |  |  | 2020 | Q1 | 2019-03-20 | 2020-02-10 | 2020-02-28 |  | Y | ROB ROY 210538430 | 1439 | SANTA CRUZ COUNTY | Yes
35082172 |  | 2020 |  | BUCOCAMP 5150 S LIBBY RD PARADISE |  | CLSD |  | 0 | 860 | 860 | 0.16288 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 95F | [51 empty] | 860 | 0.16288 | 0 | 0 | 0.16288 | 0 | 0.16288 | 0 | 0.16288 | 0 | 0 | 0.16288 |  |  |  |  | N/A | [5 empty] | 2019-04-22 | [25 empty] | Paradise | Butte | 39.7372 | -121.5938 |  |  |  |  | 2019 | [8 empty] | BUTTE COUNTY | Yes
35083751 |  |  |  | STS-COND_IDLE_REMV-1355 TULE RD/FAMOSO L |  | UNSE |  | 0 | 600 | 600 | 0.11364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2AF | [51 empty] | 600 | 0.11364 | 0 | 0 | 0.11364 | 0 | 0.11364 | 0 | 0.11364 | 0 | 0 | 0.11364 |  |  |  |  | N/A | [33 empty] | 35.6211 | -118.9583 | [13 empty] | KERN COUNTY | Yes
35085393 |  |  |  | CWSP - SILVERADO 2104 - LR722 PH 1B |  | FICL | 2150 | 0 | 1871 | 1871 | 0.35436 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NB | 08W | SH | 2019-06-25 | 2019-06-25 |  | 2019-06-25 |  |  | Yes | 2019-06-25 | [5 empty] | 100 | No | [10 empty] | Full |  |  | Full |  |  | estimation released last week 7/12 | Full |  | Yes | 2020-12-31 |  | expires 7/15/20 | 1980-01-01 | Y | [10 empty] | 1871 | 0.35436 | 0 | 0 | 0.35436 | 0 | 0.35436 | 0 | 0.35436 | 0 | 0 | 0.35436 |  |  |  |  | N/A | [5 empty] | 2019-10-17 |  |  |  | 1299999.5 | 1529760.3 |  | 1300000 | 0.5 | -216898.7 | 117.7% | 1516898.2 | 0 | 1516898.2 | 0 | 4317014.636 | 11 | [9 empty] | Deer Park | Napa | 0 | 0 | E.5014772.02 |  |  |  | 2019 | Q3 |  |  |  |  | Y | SILVERADO 2104722 | 160 | NAPA COUNTY | Yes
35085532 |  |  |  | CWSP - SILVERADO 2104 - LR722 PH 1C |  | FICL | 6000 | 0 | 5948 | 5948 | 1.1265 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NB | 08W | SH | 2019-06-24 | 2019-06-10 |  | 2019-06-10 |  |  | Yes | 2019-06-10 | [5 empty] | 100 | No | [10 empty] | Full |  |  | Full |  |  | ERTC released | Full |  | Yes | 2020-12-31 |  | expires 7/15/20 | 1980-01-01 | Y | [10 empty] | 5948 | 1.1265 | 0 | 0 | 1.1265 | 0 | 1.1265 | 0 | 1.1265 | 0 | 0 | 1.1265 |  |  | 2019-06-24 |  | N/A | 2019-09-13 | 2020-01-15 | 2020-01-15 17:00 |  |  | 2020-01-15 |  |  |  | 2099999.8 | 1487070.4 |  | 2100000 | 0.2 | 717003.1 | 70.81% | 1382996.7 | 0 | 1382996.7 | 0 | 1320062.4936 | 30 | [9 empty] | Deer Park | Napa | 0 | 0 | E.5014772.03 |  |  |  | 2019 | Q3 |  |  |  |  | Y | SILVERADO 2104722 | 160 | NAPA COUNTY | Yes
35085533 |  |  |  | CWSP - SILVERADO 2104 - LR722 PH 1D |  | FICL | 4400 | 0 | 5365 | 5365 | 1.0161 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NB | 08W | SH | 2019-09-10 | 2019-09-10 |  | 2019-09-10 |  |  | Yes | 2019-09-10 | [5 empty] | 100 | No | [10 empty] | Full |  |  | Full |  |  | Drawing received | Full |  | Yes | 2020-12-31 |  | Verbal Approval on 8/26, should issue by end of week | 1980-01-01 | Y | [10 empty] | 5365 | 1.0161 | 0 | 0 | 1.0161 | 0 | 1.0161 | 0 | 1.0161 | 0 | 0 | 1.0161 |  |  | 2019-08-21 |  | N/A | 2019-09-23 | 2019-10-08 | 2019-10-08 |  |  | 2019-10-08 |  |  |  | 2100000 | 1791769.8 |  | 2100000 | 0 | 308230.2 | 85.32% | 1791769.8 | 0 | 1791769.8 | 0 | 1763382.0212 | 22 | [9 empty] | Deer Park | Napa | 0 | 0 | E.5014772.04 |  |  |  | 2019 | Q4 |  |  |  |  | Y | SILVERADO 2104722 | 160 | NAPA COUNTY | Yes
35085534 |  | 2020 | 220 Mile Plan | CWSP - SILVERADO 2104 - LR722 PH 1E |  | DOCC | 4048 | 0 | 4191 | 4191 | 0.79375 | 3823 | 0.72405 | 0 | 0 | 0 | 0 | 8.6126e-17 |  |  | NB | 08W | SH | 2019-08-16 | 2019-08-16 |  | 2019-08-16 |  |  | Yes | 2019-08-16 | [5 empty] | 100 | [5 empty] | Yes | [5 empty] | Full |  |  | Full |  |  | Drawings received 8/12 | Full |  | Yes | 2020-12-31 |  | Verbal Approval on 8/26, should issue by end of week | 1980-01-01 | Y | [10 empty] | 368 | 0.069697 | 3823 | 0.72405 | 0.79375 | 0 | 0.79375 | 0 | 0.79375 | 0 | 0 | 0.79375 |  | Keep | 2019-08-14 | Yes | N/A | 2019-11-20 | 2020-05-01 | 2020-05-01 |  |  | 2020-05-01 |  | Yes | Shovel Ready | 2118489.8 | 383006.7 |  | 2126590 | 8100.2 | 1756526 | 18.07% | 361963.8 | 0 | 361963.8 | 0 | 482528.126 | 21 | [9 empty] | Deer Park | Napa | 0 | 0 | E.5014772.05 |  |  |  | 2020 | Q1 | 2019-08-16 | 2020-01-02 | 2020-01-26 |  | Y | SILVERADO 2104722 | 160 | NAPA COUNTY | Yes
35085535 |  | 2020 | 220 Mile Plan | CWSP - SILVERADO 2104 - LR722 PH 1F |  | DOCC | 8793 | 0 | 8793 | 8793 | 1.6653 | 8793 | 1.6653 | 0 | 0 | 0 | 0 | 0 |  |  | NB | 08W | SH | 2019-08-01 | 2019-08-01 |  | 2019-08-01 |  |  | Yes | 2019-08-01 | [5 empty] | 100 | No |  |  |  |  | Yes | [5 empty] | Full |  |  | Full |  |  | Drawing to be sent on 7/30/19 | Full |  | Yes | 2020-12-31 |  | Verbal Approval on 8/26, should issue by end of week | 1980-01-01 | Y | [10 empty] | 0 | 0 | 8793 | 1.6653 | 1.6653 | 0 | 1.6653 | 0 | 1.6653 | 0 | 0 | 1.6653 |  | Keep | 2019-07-26 | Yes | N/A | 2020-01-06 | 2020-05-18 | 2020-05-18 |  |  | 2020-05-01 |  | Yes | Shovel Ready | 2963631.1 | 538640 |  | 2979682 | 16050.9 | 2440347.7 | 18.17% | 523283.4 | 0 | 523283.4 | 0 | 323441.2828 | 44 | [9 empty] | Deer Park | Napa | 0 | 0 | E.5014772.06 |  |  |  | 2020 | Q1 | 2019-08-01 | 2020-01-02 | 2020-02-09 |  | Y | SILVERADO 2104722 | 160 | NAPA COUNTY | Yes
35085536 |  |  |  | CWSP - SILVERADO 2104 - LR722 PH 1G |  | DOCC | 4850 | 0 | 7010 | 7010 | 1.3277 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NB | 08W | SH | 2019-08-13 | 2019-08-13 |  | 2019-08-13 |  |  | Yes | 2019-08-13 | [5 empty] | 100 | No | [10 empty] | Full |  |  | Full |  |  |  | Full |  | Yes | 2020-12-31 |  | was submitted to Napa County on 8/12/19, should be approved by 9/12/19 | 1980-01-01 | Y | [10 empty] | 7010 | 1.3277 | 0 | 0 | 1.3277 | 0 | 1.3277 | 0 | 1.3277 | 0 | 0 | 1.3277 |  |  |  |  | N/A | [5 empty] | 2019-12-09 |  |  |  | 1949999.6 | 1807398.7 |  | 1950000 | 0.4 | 211188.4 | 92.68% | 1738811.2 | 0 | 1738811.2 | 0 | 1361350.2334 | 25 | [9 empty] | Deer Park | Napa | 0 | 0 | E.5014772.07 |  |  |  | 2019 | Q4 |  |  |  |  | Y | SILVERADO 2104722 | 160 | NAPA COUNTY | Yes
35085537 |  | 2020 | 220 Mile Plan | CWSP - SILVERADO 2104 - LR722 PH 1H |  | DOCC | 4053 | 0 | 3752 | 3752 | 0.71061 | 628 | 0.11894 | 0 | 0 | 0 | 0 | 0 |  |  | NB | 08W | SH | 2019-09-02 | 2019-07-09 |  | 2019-07-09 |  |  | Yes | 2019-07-09 |  | SANTA ROSA |  |  |  | 100 | No |  |  |  |  | Yes | [5 empty] | Full |  |  | Full |  |  | CIF submitted 7/23 - Dwg received currently being reviewed - [REDACTED] to complete land task | Full |  | Yes | 2020-12-31 |  | expires 7/15/20 | 1980-01-01 | Y | [10 empty] | 3124 | 0.59167 | 628 | 0.11894 | 0.71061 | 0 | 0.71061 | 0 | 0.71061 | 0 | 0 | 0.71061 |  | Keep | 2019-09-02 | Yes | N/A | 2019-10-07 | 2020-01-17 | 2020-01-17 |  |  | 2020-01-17 |  | Yes | Shovel Ready | 1350000.2 | 1054999.8 |  | 1350000 | -0.2 | 295000.4 | 78.14% | 1054999.8 | 0 | 1054999.8 | 0 | 1484647.9062 | 21 | [9 empty] | Deer Park | Napa | 0 | 0 | E.5014772.08 |  |  |  | 2020 | Q1 | 2019-06-30 | 2020-01-02 | 2020-01-17 |  | Y | SILVERADO 2104722 | 160 | NAPA COUNTY | Yes
35085538 |  | 2020 | 220 Mile Plan | SILVERADO 2105 WIRE DOWN - PH 1 |  | FICL | 10194 | 0 | 10413 | 10413 | 1.9722 | 5327 | 1.0089 | 0 | 0 | 0 | 0 | 1.7225e-16 |  |  | NB | 08W | SH | 2019-08-19 | 2019-08-01 |  | 2019-08-01 |  |  | Yes | 2019-08-01 | [5 empty] | 100 | No |  |  |  |  | Yes | [5 empty] | Full |  |  | Full |  |  |  | Full |  | Yes | 2020-12-31 |  |  | 1980-01-01 | Y | [10 empty] | 5086 | 0.96326 | 5327 | 1.0089 | 1.9722 | 0 | 1.9722 | 0 | 1.9722 | 0 | 0 | 1.9722 |  | Keep | 2019-08-19 | Yes | N/A | 2019-10-07 | 2020-05-18 | 2020-05-18 |  |  | 2020-02-01 |  | Yes | Shovel Ready | 2950000.4 | 1767115.2 |  | 2950000 | -0.4 | 1496830.3 | 59.9% | 1453170.1 | 0 | 1453170.1 | 0 | 896030.7554 | 26 | [9 empty] | Saint Helena | Napa | 0 | 0 | E.5014317.02 |  |  |  | 2020 | Q1 | 2019-07-26 | 2020-01-02 | 2020-01-31 |  | Y | SILVERADO 2105658898 | 104 | NAPA COUNTY | Yes
35085539 |  | 2020 | 220 Mile Plan | SILVERADO 2105 WIRE DOWN - PH 2 |  | DOCC | 10424 | 0 | 10260 | 10260 | 1.9432 | 4405 | 0.83428 | 0 | 0 | 0 | 0 | 0 |  |  | NB | 08W | SH | 2019-08-21 | 2019-08-09 |  | 2019-08-09 |  |  | Yes | 2019-08-09 | [5 empty] | 100 | No |  |  |  |  | Yes | [5 empty] | Full |  |  | Full |  |  |  | Full |  | Yes | 2020-12-31 |  | Verbal Approval on 8/26, should issue by end of week | 1980-01-01 | Y | [10 empty] | 5855 | 1.1089 | 4405 | 0.83428 | 1.9432 | 0 | 1.9432 | 0 | 1.9432 | 0 | 0 | 1.9432 |  | Keep | 2019-08-21 | Yes | N/A | 2019-11-08 | 2020-05-21 | 2020-05-21 |  |  | 2020-05-19 |  | Yes | Shovel Ready | 2569999.8 | 1396454.5 |  | 2570000 | 0.2 | 1298939.9 | 54.33% | 1271059.9 | 0 | 1271059.9 | 0 | 718643.2515 | 28 | [9 empty] | Saint Helena | Napa | 0 | 0 | E.5014317.03 |  |  |  | 2020 | Q1 | 2019-08-02 | 2020-01-02 | 2020-01-31 |  | Y | SILVERADO 2105658898 | 104 | NAPA COUNTY | Yes
35085680 |  |  |  | SILVERADO 2105 WIRE DOWN - PH 3 |  | ESTS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NB | 08W | [36 empty] | 2020-12-31 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6538 | 1.6538 | 0 | 0 |  |  |  |  | N/A | [9 empty] | 10000 | 85677.5 |  | 2298281.08 | 2288281.08 | -75677.5 | 856.8% | 85677.5 | 0 | 85677.5 | 0 | [11 empty] | Saint Helena | Napa | 0 | 0 | [10 empty] | Y |  |  | NAPA COUNTY | Yes
35085681 |  |  |  | SILVERADO 2105 WIRE DOWN - PH 4 |  | DOCC | 2947 | 0 | 2947 | 2947 | 0.55814 | 13 | 0.0024621 | 0 | 0 | 0 | 0 | 3.3643e-19 |  |  | NB | 08W | SH | 2019-08-19 | 2019-06-07 |  | 2019-06-07 |  |  | Yes | 2019-06-07 | [5 empty] | 100 | No | [10 empty] | Full |  |  | Full |  |  | Envro review starting 6/25/19. CIF Sent on 6/28/2019 | Full |  | Yes | 2020-12-31 |  | Verbal Approval on 8/26, should issue by end of week | 1980-01-01 | Y | [10 empty] | 2934 | 0.55568 | 0 | 0 | 0.55568 | 0.0024621 | 0.55568 | 0 | 0.55568 | 0 | 0 | 0.55568 |  |  | 2019-08-19 |  | N/A | 2019-09-06 | 2019-09-24 | 2019-09-24 |  |  | 2019-09-30 |  |  |  | 500000.5 | 427511.9 |  | 500000 | -0.5 | 73662.9 | 85.5% | 426337.6 | 0 | 426337.6 | 0 | 765952.7764 | 15 | [9 empty] | Saint Helena | Napa | 0 | 0 | E.5014317.05 |  |  |  | 2019 | Q3 |  |  |  |  | Y | SILVERADO 2105658898 | 104 | NAPA COUNTY | Yes
35087207 |  |  |  | STS-REPL POLE 16E/O 2S/O CO 19161 BLA |  | DOCC |  | 0 | 1065 | 1065 | 0.2017 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2AF | [51 empty] | 1065 | 0.2017 | 0 | 0 | 0.2017 | 0 | 0.2017 | 0 | 0.2017 | 0 | 0 | 0.2017 |  |  |  |  | N/A | [5 empty] | 2019-06-28 | [27 empty] | 37.9397 | -121.911 | [13 empty] | CONTRA COSTA COUNTY | Yes
35087462 |  |  |  | STS-OFAC_IDLE_DEEN - 6 N/O 2 W/O R/O 930 |  | FICL |  | 0 | 1538 | 1538 | 0.29129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2AF | [51 empty] | 1538 | 0.29129 | 0 | 0 | 0.29129 | 0 | 0.29129 | 0 | 0.29129 | 0 | 0 | 0.29129 |  |  |  |  | N/A | [5 empty] | 2019-06-26 | [27 empty] | 39.0461 | -121.3037 | [13 empty] | PLACER COUNTY | Yes
35087685 |  | 2020 |  | BUCOCAMP 5000 BLUE BALATON LN PARADISE |  | CLSD |  | 0 | 272 | 272 | 0.051515 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 95F | [51 empty] | 272 | 0.051515 | 0 | 0 | 0.051515 | 0 | 0.051515 | 0 | 0.051515 | 0 | 0 | 0.051515 |  |  |  |  | N/A | [5 empty] | 2019-05-14 | [27 empty] | 39.727 | -121.5755 |  |  |  |  | 2019 | [8 empty] | BUTTE COUNTY | Yes
35087693 |  | 2020 | (blank) | BUCOCAMP 13524 HOG RANCH RD ORO COMP |  | UNSC |  | 0 | 666 | 666 | 0.12614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 95F | [51 empty] | 666 | 0.12614 | 0 | 0 | 0.12614 | 0 | 0.12614 | 0 | 0.12614 | 0 | 0 | 0.12614 |  |  |  |  | N/A | [9 empty] | 0 | 75047 |  | 42615.71 | 42615.71 | -75047 |  | 75047 | 0 | 75047 | 0 | 594967.2072 | [10 empty] | Paradise | Butte | 39.7882 | -121.5303 |  |  |  |  | 2019 | [5 empty] | Y |  |  | BUTTE COUNTY | Yes
35088308 |  | 2020 |  | BUCOCAMP 1445 KELLER LANE PARADISE |  | CLSD |  | 0 | 486 | 486 | 0.092045 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 95F | [51 empty] | 486 | 0.092045 | 0 | 0 | 0.092045 | 0 | 0.092045 | 0 | 0.092045 | 0 | 0 | 0.092045 |  |  |  |  | N/A | [5 empty] | 2019-05-25 | [25 empty] | Paradise | Butte | 39.7413 | -121.5938 |  |  |  |  | 2019 | [8 empty] | BUTTE COUNTY | Yes
35088309 |  | 2020 |  | BUCOCAMP 1426 W DOTTIE LANE PARADISE |  | CLSD |  | 0 | 530 | 530 | 0.10038 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 95F | [51 empty] | 530 | 0.10038 | 0 | 0 | 0.10038 | 0 | 0.10038 | 0 | 0.10038 | 0 | 0 | 0.10038 |  |  |  |  | N/A | [5 empty] | 2019-05-22 | [27 empty] | 39.7449 | -121.5937 |  |  |  |  | 2019 | [8 empty] | BUTTE COUNTY | Yes
35089880 |  |  |  | OCGC PIH SILVERADO 2104 - ANGWIN UG_PH 2 |  | CLSD |  | 0 | 2117 | 2117 | 0.40095 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NB | 08W | SH | [50 empty] | 2117 | 0.40095 | 0 | 0 | 0.40095 | 0 | 0.40095 | 0 | 0.40095 | 0 | 0 | 0.40095 |  |  |  |  | N/A | [5 empty] | 2019-10-09 | [25 empty] | Angwin | Napa | 0 | 0 |  |  |  |  | 2019 | [5 empty] | Y | SILVERADO 210437632 | 720 | NAPA COUNTY | Yes
35091861 |  | 2020 |  | BUCOCAMP 628 MORRIS LANE PARADISE |  | CLSD |  | 0 | 238 | 238 | 0.045076 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 95F | [51 empty] | 238 | 0.045076 | 0 | 0 | 0.045076 | 0 | 0.045076 | 0 | 0.045076 | 0 | 0 | 0.045076 |  |  |  |  | N/A | [5 empty] | 2019-05-03 | [27 empty] | 39.7437 | -121.6267 |  |  |  |  | 2019 | [8 empty] | BUTTE COUNTY | Yes
35094082 |  |  |  | STS-POLE_IDLE_REMV - 5549 GLEN DR#1PNPAR |  | CLSD |  | 0 | 566 | 566 | 0.1072 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2AF | [51 empty] | 566 | 0.1072 | 0 | 0 | 0.1072 | 0 | 0.1072 | 0 | 0.1072 | 0 | 0 | 0.1072 |  |  |  |  | N/A | [5 empty] | 2019-08-31 | [27 empty] | 39.7491 | -121.6026 | [13 empty] | BUTTE COUNTY | Yes
35094321 |  |  |  | XSTS-POLE_IDLE-REMOV - 6PSE1PSW 6700 CRO |  | CLSD |  | 0 | 545 | 545 | 0.10322 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2AF | [51 empty] | 545 | 0.10322 | 0 | 0 | 0.10322 | 0 | 0.10322 | 0 | 0.10322 | 0 | 0 | 0.10322 |  |  |  |  | N/A | [5 empty] | 2019-06-13 | [27 empty] | 37.0834 | -121.7524 | [13 empty] | SANTA CLARA COUNTY | Yes
35094363 |  | 2020 |  | BUCOCAMP 13764 CANYON RD MAGALIA |  | CLSD |  | 0 | 555 | 555 | 0.10511 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 95F | [51 empty] | 555 | 0.10511 | 0 | 0 | 0.10511 | 0 | 0.10511 | 0 | 0.10511 | 0 | 0 | 0.10511 |  |  |  |  | N/A | [5 empty] | 2019-06-20 | [27 empty] | 39.8088 | -121.5822 |  |  |  |  | 2019 | [8 empty] | BUTTE COUNTY | Yes
35094388 |  |  |  | CWSP-KONOCTI 1102-LR 532 PH 1 |  | MAPP | 2741 | 0 | 2241 | 2241 | 0.42443 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2019-07-19 | 2019-07-03 |  | 2019-07-03 |  |  | Yes | 2019-07-03 | [5 empty] | 100 | No | [10 empty] | Full |  |  | Full |  |  | Caltrans encroachment permit submitted on 8/13 | Full |  | Yes | 2020-12-31 |  | Annual | 1980-01-01 | Y | [10 empty] | 2241 | 0.42443 | 0 | 0 | 0.42443 | 0 | 0.42443 | 0 | 0.42443 | 0 | 0 | 0.42443 |  |  | 2019-07-19 |  | N/A | 2019-09-16 | 2019-09-23 | 2019-09-23 |  |  | 2019-09-23 |  |  |  | 400000.2 | 445783 |  | 400000 | -0.2 | -45782.8 | 111.4% | 445783 | 0 | 445783 | 0 | 1050305.328 | 14 | [9 empty] | Kelseyville | Lake | 38.9024 | -122.7519 | E.5015029.02 |  |  |  | 2019 | Q3 |  |  |  |  | Y | KONOCTI 1102532 | 153 | LAKE COUNTY | Yes
35094390 |  |  |  | CWSP-KONOCTI 1102-LR 532 PH 3 |  | DOCC | 2237 | 0 | 2881 | 2881 | 0.54564 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2019-08-27 | 2019-07-31 |  | 2019-07-31 |  |  | Yes | 2019-07-31 | [5 empty] | 100 | No | [10 empty] | Full |  |  | Full |  |  | Drawing received 7/29 - Potential forest conflicts | Full |  | Yes | 2020-12-31 |  | Annual | 1980-01-01 | Y | [10 empty] | 2881 | 0.54564 | 0 | 0 | 0.54564 | 0 | 0.54564 | 0 | 0.54564 | 0 | 0 | 0.54564 |  |  | 2019-08-27 |  | N/A | 2019-11-21 | 2019-12-16 | 2018-12-16 |  |  | 2019-12-16 |  |  |  | 900000.3 | 850845.8 |  | 900000 | -0.3 | 62635.1 | 94.53% | 837365.2 | 0 | 837365.2 | 0 | 1559342.5283 | 12 | [9 empty] | Kelseyville | Lake | 38.9024 | -122.7519 | E.5015029.04 |  |  | 2020-060 | 2019 | Q4 |  |  |  |  | Y | KONOCTI 1102532 | 153 | LAKE COUNTY | Yes
35094392 |  |  |  | OCGC CWSP-KONOCTI 1102-LR 532 PH 5 |  | FICL | 3625 | 0 | 1956 | 1956 | 0.37045 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2019-08-29 | 2019-08-29 |  | 2019-08-29 |  |  | Yes | 2019-08-29 | [5 empty] | 100 | No | [10 empty] | Full |  |  | Full |  |  | CIF Submitted on 9/5/19 | Full |  | Yes | 2020-12-31 |  | Annual | 1980-01-01 | Y | [10 empty] | 1956 | 0.37045 | 0 | 0 | 0.37045 | 0 | 0.37045 | 0 | 0.37045 | 0 | 0 | 0.37045 |  |  | 2019-08-16 |  | N/A | 2019-10-28 | 2019-12-04 | 2019-12-04 |  |  | 2019-12-04 |  |  |  | 270000 | 264079.1 |  | 270000 | 0 | 5920.9 | 97.8% | 264079.1 | 0 | 264079.1 | 0 | 712851.5583 | 19 | [9 empty] | Kelseyville | Lake | 38.9024 | -122.7519 | E.5015029.06 |  |  | 2020-062 | 2019 | Q4 |  |  |  |  | Y | KONOCTI 1102532 | 153 | LAKE COUNTY | Yes
35094393 |  | 2020 | 220 Mile Plan | OCGC KONOCTI - 1102 - LR 532 PH 6 (OH) |  | FICL | 10459 | 0 | 10641 | 10641 | 2.0153 | 10641 | 2.0153 | 0 | 0 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2020-05-25 | 2019-12-19 |  | 2019-12-19 |  |  | Yes | 2019-12-19 |  | SANTA ROSA |  |  |  | 100 | No |  |  |  |  | Yes | [5 empty] | Full |  |  | Full |  |  | CIF Submitted on 12/17/19 | Full |  | Yes | 2020-12-31 |  | Annual | 2020-06-09 | Y | 2020-05-01 |  |  | Started | [6 empty] | 0 | 0 | 10641 | 2.0153 | 2.0153 | 3.4451e-16 | 2.0153 | 0 | 2.0153 | 0 | -3.4451e-16 | 2.0153 |  | Keep | 2020-02-11 | Yes | N/A | 2020-06-01 08:00 | 2020-08-20 | 2020-08-20 |  |  | 2020-08-05 | 2020-05-25 | Yes | Shovel Ready | 2815032.1 | 3497101.7 |  | 3335231 | 520198.9 | 2291824.3 | 124.2% | 3208.6 | 519999.2 | 523207.8 | 0 | 1735240.7646 | 53 | [9 empty] | Kelseyville | Lake | 38.9024 | -122.7519 | E.5015029.07 |  |  | 2020-063 | 2020 | Q2 | 2019-12-13 | 2020-05-02 | 2020-06-14 |  | Y | KONOCTI 1102532 | 153 | LAKE COUNTY | Yes
35094394 |  | 2020 | 220 Mile Plan | CWSP-KONOCTI 1102-LR 532 PH 7 |  | DOCC | 7765 | 0 | 7765 | 7765 | 1.4706 | 7765 | 1.4706 | 0 | 0 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2019-12-11 | 2019-12-11 |  | 2019-12-11 |  |  | Yes | 2019-12-11 |  | SANTA ROSA |  |  |  | 100 | No |  |  |  |  | Yes | [5 empty] | Full |  |  | Full |  |  |  | Full |  | Yes | 2020-12-31 |  | Annual | 1980-01-01 | Y | [10 empty] | 0 | 0 | 7765 | 1.4706 | 1.4706 | 0 | 1.4706 | 0 | 1.4706 | 0 | 0 | 1.4706 |  | Keep | 2019-11-05 | Yes | N/A | 2020-03-09 | 2020-11-19 | 2020-11-19 |  |  | 2020-05-01 |  | Yes | Shovel Ready | 1670654.3 | 4142905.9 | 216687.4 | 1708101 | 37446.7 | 1498441.9 | 248% | 3645.6 | 168566.8 | 172212.4 | 0 | 2817069.3048 | 39 | [9 empty] | Kelseyville | Lake | 38.9024 | -122.7519 | E.5015029.08 |  |  | 2020-064 | 2020 | Q1 | 2019-11-05 | 2020-02-28 | 2020-05-01 |  | Y | KONOCTI 1102532 | 153 | LAKE COUNTY | Yes
35095165 |  |  |  | CWSP - VOLTA 1102 - LR 1648 -PH 3.1 |  | DOCC | 3825 | 0 | 3666 | 3666 | 0.69432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 08W | SH | 2019-09-12 | 2019-07-22 | 2019-12-29 | 2019-07-22 |  |  | Yes | 2019-07-22 | 7/3 - 7/16: On track for 8/2 Submitted 7/10, ADE Assigned 7/15 7/22: Moved into PEND | EEI |  |  | Completed | COMPLETED | No |  | 0 | 0 | [7 empty] | Full |  |  | Full |  |  | CIF Submitted 7/22/19 | Full |  | Yes |  |  | permit request submitted 7/22/19 | 1980-01-01 | Y | [10 empty] | 3666 | 0.69432 | 0 | 0 | 0.69432 | 0 | 0.69432 | 0 | 0.69432 | 0 | 0 | 0.69432 |  |  | 2019-09-12 |  | N/A | 2019-09-17 | 2019-11-25 | 2019-11-25 |  |  | 2019-11-25 |  |  |  | 3352028.5 | 3347334 |  | 3514354 | 162325.5 | 275488.8 | 99.85% | 3070446.3 | 6093.4 | 3076539.7 | 0 | 4821037.5123 | 20 | [9 empty] | Shingletown | Shasta | 40.5069 | -121.8183 | E.5015704.01 |  |  |  | 2019 | Q3 |  |  |  |  | Y | VOLTA 11021648 | 283 | SHASTA COUNTY | Yes
35095166 |  | 2020 | 220 Mile Plan | CWSP - EL DORADO 2102 - LR19562 - PH 1.0 |  | MAPP | 7329 | 0 | 7542 | 7542 | 1.4284 | 7542 | 1.4284 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | SH | 2020-05-01 | 2020-03-10 | 2020-03-10 | 2020-03-10 | 2020-12-16 | 2020-12-16 | Yes | 2020-03-10 | 03/09: INTO PEND 03/04: QUES routed for Approval 02/26: ADE Status? EOD RISK 02/22 QUES submitted for 3rd ADE rvw 02/19 - 01/29: 2nd round stamping; High volume of stamping (restamping); Finalizing stamping 01/22: EST on track if restamping is at a minimum 01/18 QUES submitted for another (3rd?) ADE rvw 01/13: ADE Status- ADE unexpected time off - on track for this week (1/17) 12/16: QUES submitted for 2nd ADE rvw - [PRELIM DWGs ready] 12/11 <-- 12/04: On Track 11/27: Ocalcs changing (85%); additional changes (+3wk) - EEI to review implementation 11/20: ADE rtn 1st corrections for ADE rvw 11/13: On Target 11/06:Estimator on vacation - ADE on partial vacation - Rvw expected to be done next week. 10/29: Checking in with ADE (1st 08W rvw, working with new laptop/issues) 10/23: Rvw Inprogress 10/14 QUES submitted for 1st Rvw 10/09: Originally went off straight pole count - Larger amount of poles - require additional time to complete 10/02: 1st Submittal push to 10/07; Estimator bandwith - volume of work - Resource impacts (down to 1 PE for stamping) 9/25: 1st Submittal on target 9/30 9/18: Push to 9/30 - Training/New Hire ramp up 9/11: 1st Submittal push to 9/20 - --> [RCC Issue] 9/04: Push to 9/9 - Reprioritized to resolve corrections, resource shift 7/16 - 8/21: On track 7/3: QUES to review to provide review on 1st ADE Submital | QUES |  |  | 2020 - Q1- M2 [R0] | COMPLETED | No | Obsolete (CONS+) | 0 | 0 |  | Yes | [5 empty] | Full |  |  | Full |  |  | CIF Submitted 12/18/19 | Full |  | Yes |  |  | Drawings submitted 12/18/19 | 2020-05-22 | Y | 2020-05-01 |  |  | Started | [6 empty] | 0 | 0 | 7542 | 1.4284 | 1.4284 | 0 | 1.4284 | 0 | 1.4284 | 0 | 0 | 1.4284 |  | Keep | 2020-04-23 17:00 | Yes | N/A | 2020-05-01 | 2020-08-14 08:00 | 2020-08-14 |  |  | 2020-08-21 |  | Yes | Shovel Ready | 2398892.7 | 2948841.1 |  | 3293522 | 894629.3 | 2380746.2 | 122.9% | 18146.5 | 0 | 18146.5 | 0 | 2064423.3636 | 37 | [9 empty] | Pollock Pines | El Dorado | 38.7717 | -120.5878 | E.5015687.01 |  |  |  | 2020 | Q2 | 2020-02-29 | 2020-05-18 | 2020-08-06 |  | Y | EL DORADO PH 210219562 | 52 | EL DORADO COUNTY | Yes
35096604 |  | 2020 |  | BUCOCAMPT 678 MEMORIAL WAY PARADISE |  | CLSD |  | 0 | 218 | 218 | 0.041288 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 95F | [51 empty] | 218 | 0.041288 | 475 | 0.089962 | 0.13125 | -0.089962 | 0.13011 | 0 | 0.13011 | 0 | 0.0011364 | 0.13011 |  |  |  |  | N/A | [5 empty] | 2019-09-27 |  |  |  | 0 | 77958.6 |  | 67539.78 | 67539.78 | -77958.6 |  | 77958.6 | 0 | 77958.6 | 0 | 1888171.5963 | [12 empty] | 39.7611 | -121.6241 |  |  |  |  | 2019 | [5 empty] | Y |  |  | BUTTE COUNTY | Yes
35098264 |  |  |  | FT-POLE_IDLE_REMV - NE/O ENTR. 5756 RAI |  | CLSD |  | 0 | 545 | 545 | 0.10322 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2AF | [51 empty] | 545 | 0.10322 | 0 | 0 | 0.10322 | 0 | 0.10322 | 0 | 0.10322 | 0 | 0 | 0.10322 |  |  |  |  | N/A | [5 empty] | 2019-06-26 | [27 empty] | 38.2657 | -120.5096 | [13 empty] | CALAVERAS COUNTY | Yes
35098578 |  |  |  | CWSP-COLUMBIA HILL 1101-LR 2212 PH2 |  | CLSD | 10112 | 0 | 9480 | 9480 | 1.7955 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | SH | 2019-09-16 | 2019-09-16 |  | 2019-09-16 |  |  | Yes | 2019-09-16 | Section 21st ADE Submittal - 7/30/197/3 - 7/24: on track 7/307/31: Friday Submittal8/5: QUES submitted for 1st ADE Review8/7: [REDACTED] assigned & OCalc uploaded to SAP8/21: 1st ADE review scheduled to complete by 8/238/22: Corrections returned to contractors (Prt1, Prt 2, Prt3)8/23: 2nd ADE review communicated to contractor - Need the OU attachment height to be shown on the DWG8/23: Moved into AUG 8/30 priority list (Gap Fill)8/27: QUES submitted for 2nd ADE Rvw8/28: Corrections done - review for ready to route - Routed in EES PRELIM DWG (Done)9/04 - 9/11: [RCC Issues] 9/27 EOD push | QUES |  |  | Completed | COMPLETED | No |  | 0 | 0 | [7 empty] | Full |  |  | Full |  |  | CIF submitted 7/15/19 | Full |  | Yes |  |  | Request sent - No permit required | 1980-01-01 | Y | [10 empty] | 9480 | 1.7955 | 0 | 0 | 1.7955 | 0 | 1.7955 | 0 | 1.7955 | 0 | 0 | 1.7955 |  |  |  |  | N/A | [5 empty] | 2019-12-03 | [15 empty] | 50.56 | [9 empty] | North San Juan | Nevada | 0 | 0 | E.5015491.02 |  |  |  | 2019 | Q4 |  |  |  |  | Y | COLUMBIA HILL 11012212 | 198 | NEVADA COUNTY | Yes
35098579 |  |  |  | CWSP-COLUMBIA HILL 1101-LR 2212 PH3 |  | CLSD | 7417 | 0 | 7573 | 7573 | 1.4343 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | SH | 2019-08-12 | 2019-08-12 | 2019-07-30 | 2019-08-12 |  |  | Yes | 2019-08-12 | Section 31st ADE Submittal - 6/30/19. Refielded needed. Submittal 7/12 for 1st ADE submittal7/16: 7/10 Submitted7/24 - 7/31: Waiting for PGE review completion; ADE [REDACTED]8/5: 1st ADE review complete, returned to contractor. 8/6: ADE returned corrections to vendor [Prelim DWG ready]8/12: Approved into PEND 7417' of 1/OAR tree wire. Again, lots of errors showing in EES, which might be due to the SAP issues IT is working on | QUES |  |  | Completed | COMPLETED | No |  | 0 | 0 | [7 empty] | Full |  |  | Full |  |  | CIF submitted 6/27/19. KMZ received. Currently reviewing | Full |  | Yes |  |  | Request sent to SIDIVPGEPERMITS 8/6/19 - Private Property No permit required | 1980-01-01 | Y | [10 empty] | 7573 | 1.4343 | 0 | 0 | 1.4343 | 0 | 1.4343 | 0 | 1.4343 | 0 | 0 | 1.4343 |  |  |  |  | N/A | [5 empty] | 2019-10-07 | [15 empty] | 37.085 | [9 empty] | North San Juan | Nevada | 0 | 0 | E.5015491.03 |  |  |  | 2019 | Q3 |  |  |  |  | Y | COLUMBIA HILL 11012212 | 198 | NEVADA COUNTY | Yes
35098622 |  |  |  | CWSP-COLUMBIA HILL 1101-LR 2212 PH5 |  | DOCC | 12854 | 0 | 13101 | 13101 | 2.4813 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | SH | 2019-08-08 | 2019-08-08 | 2019-08-20 | 2019-08-08 |  |  | Yes | 2019-08-08 | Section 5 1st ADE Submittal - 7/15/19. 7/3: On track for 7/15 7/16: 1st ADE Submitted on 7/15 7/24 - 7/31: QUES waiting for ADE corrections; ADE Carlos 7/31: Review completed, corrections being applied 8/6: * Correct Location 11 Ocalc, used existing pole load case. * All Zip file Ocalcs should match signed PE calculations. Correction in progress [PRELIM DWG ready] 8/8: JOB APPROVED and into PEND | QUES |  |  | Completed | COMPLETED | No |  | 0 | 0 | [7 empty] | Full |  |  | Full |  |  | CIF submitted 6/27/19 - Will try to expedite ERTC | Full |  | Yes |  |  | Nevada Co. - Sub permit acquired but only last 30 days (9/30) | 1980-01-01 | Y | [10 empty] | 13101 | 2.4813 | 0 | 0 | 2.4813 | 0 | 2.4813 | 0 | 2.4813 | 0 | 3.4451e-16 | 2.4813 |  |  |  |  | N/A | [5 empty] | 2019-12-09 |  |  |  | 4154524.4 | 3822083.6 |  | 4936253 | 781728.6 | 268986.8 | 91.99% | 3885537.6 | 0 | 3885537.6 | 0 | 1540386.3375 | 64.27 | [9 empty] | North San Juan | Nevada | 0 | 0 | E.5015491.05 |  |  |  | 2019 | Q3 |  |  |  |  | Y | COLUMBIA HILL 11012212 | 198 | NEVADA COUNTY | Yes
35099113 |  | 2020 |  | BUCOCAMP 1793 EL TORO CT PARADISE |  | CLSD |  | 0 | 282 | 282 | 0.053409 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 95F | [51 empty] | 282 | 0.053409 | 0 | 0 | 0.053409 | 0 | 0.053409 | 0 | 0.053409 | 0 | 0 | 0.053409 |  |  |  |  | N/A | [5 empty] | 2019-06-05 | [25 empty] | Paradise | Butte | 39.7854 | -121.5758 |  |  |  |  | 2019 | [8 empty] | BUTTE COUNTY | Yes
35099740 |  | 2020 |  | BUCOCAMPT 1361 PEACEFUL OAKS LN PARADISE |  | CLSD |  | 0 | 1929 | 1929 | 0.36534 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 95F | [51 empty] | 1929 | 0.36534 | 0 | 0 | 0.36534 | 0 | 0.042803 | 0 | 0.042803 | 0 | 0.32254 | 0.042803 |  |  |  |  | N/A | [5 empty] | 2019-09-10 | [27 empty] | 39.7423 | -121.5937 |  |  |  |  | 2019 | [8 empty] | BUTTE COUNTY | Yes
35100238 |  |  |  | STS-COND_IDLE_REMV-3750 SUNRISE RIDGE |  | DOCC |  | 0 | 665 | 665 | 0.12595 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2AF | [51 empty] | 665 | 0.12595 | 0 | 0 | 0.12595 | 0 | 0.12595 | 0 | 0.12595 | 0 | 0 | 0.12595 |  |  |  |  | N/A | [5 empty] | 2019-08-02 | [27 empty] | 35.5212 | -120.7973 | [13 empty] | San Luis Obispo County | Yes
35100240 |  | 2020 |  | BUCOCAMPT 6285 OAK WAY PARADISE |  | FICL |  | 0 | 96 | 96 | 0.018182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 95F | [51 empty] | 96 | 0.018182 | 1003 | 0.18996 | 0.20814 | -0.18996 | 0.21231 | 0 | 0.21231 | 0 | -0.0041667 | 0.21231 |  |  |  |  | N/A | [5 empty] | 2019-09-06 |  |  |  | 0 | 98618.8 |  | 71314.13 | 71314.13 | -98618.8 |  | 98618.8 | 0 | 98618.8 | 0 | 5424034 | [10 empty] | Paradise | Butte | 39.7726 | -121.6031 |  |  |  |  | 2019 | [5 empty] | Y |  |  | BUTTE COUNTY | Yes
35100244 |  |  |  | BUCOCAMPT 1411 RAMADA LN PARADISE |  | CLSD |  | 0 | 380 | 380 | 0.07197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 95F | [51 empty] | 380 | 0.07197 | 0 | 0 | 0.07197 | 0 | 0.055303 | 0 | 0.055303 | 0 | 0.016667 | 0.055303 |  |  |  |  | N/A | [5 empty] | 2019-09-13 | [27 empty] | 39.7539 | -121.5925 |  |  |  |  | 2019 | [8 empty] | BUTTE COUNTY | Yes
35100245 |  | 2020 |  | BUCOCAMP 5706 PARADISE AVE PARADISE |  | DOCC |  | 0 | 412 | 412 | 0.07803 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 95F | [51 empty] | 412 | 0.07803 | 0 | 0 | 0.07803 | 0 | 0.07803 | 0 | 0.07803 | 0 | 0 | 0.07803 |  |  |  |  | N/A | [5 empty] | 2019-07-19 | [25 empty] | Paradise | Butte | 39.7536 | -121.5971 |  |  |  |  | 2019 | [8 empty] | BUTTE COUNTY | Yes
35100980 |  | 2020 |  | BUCOCAMPT 1736 PINEY RIDGE DR PARADISE |  | DOCC |  | 0 | 510 | 510 | 0.096591 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 95F | [51 empty] | 510 | 0.096591 | 370 | 0.070076 | 0.16667 | -0.070076 | 0.16799 | 0 | 0.16799 | 0 | -0.0013258 | 0.16799 |  |  |  |  | N/A | [5 empty] | 2019-10-18 |  |  |  | 0 | 105236.6 |  | 67102.33 | 67102.33 | -105236.6 |  | 105236.6 | 0 | 105236.6 | 0 | 1089508.3294 | [10 empty] | Paradise | Butte | 39.7951 | -121.5797 |  |  |  |  | 2019 | [5 empty] | Y |  |  | BUTTE COUNTY | Yes
35100982 |  | 2020 |  | BUCOCAMPT 1428 JUNIPER LN PARADISE |  | CLSD |  | 0 | 853 | 853 | 0.16155 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 95F | [51 empty] | 853 | 0.16155 | 0 | 0 | 0.16155 | 0 | 0.043371 | 0 | 0.043371 | 0 | 0.11818 | 0.043371 |  |  |  |  | N/A | [5 empty] | 2019-08-28 |  |  |  | 0 | 30774.1 |  | 23678.41 | 23678.41 | -30774.1 |  | 30774.1 | 0 | 30774.1 | 0 | 190489.1536 | [10 empty] | Paradise | Butte | 39.7744 | -121.5937 |  |  |  |  | 2019 | [5 empty] | Y |  |  | BUTTE COUNTY | Yes
35101036 |  | 2020 |  | BUCOCAMP POLE_BURN - BARDEES BAR RD OROV |  | UNSC |  | 0 | 21684 | 21684 | 4.1068 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 95F | [51 empty] | 21684 | 4.1068 | 0 | 0 | 4.1068 | 0 | 4.1068 | 0 | 4.1068 | 0 | 0 | 4.1068 |  |  |  |  | N/A | [31 empty] | Paradise | Butte | 39.7378 | -121.4774 |  |  |  |  | 2019 | [8 empty] | BUTTE COUNTY | Yes
35101860 |  | 2020 |  | BUCOCAMP POLE_BURN HWY 70 OROVILLE |  | FICL |  | 0 | 25058 | 25058 | 4.7458 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 95F | [51 empty] | 25058 | 4.7458 | 0 | 0 | 4.7458 | 0 | 4.7458 | 0 | 4.7458 | 0 | 0 | 4.7458 |  |  |  |  | N/A | [5 empty] | 2019-06-21 | [25 empty] | Paradise | Butte | 39.7839 | -121.4494 |  |  |  |  | 2019 | [8 empty] | BUTTE COUNTY | Yes
35101861 |  | 2020 |  | BUCOCAMP POLE BURN -CAMP CRK RD OROVILLE |  | UNSC |  | 0 | 22283 | 22283 | 4.2203 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 95F | [51 empty] | 22283 | 4.2203 | 0 | 0 | 4.2203 | 0 | 4.2203 | 0 | 4.2203 | 0 | 6.8901e-16 | 4.2203 |  |  |  |  | N/A | [33 empty] | 39.8741 | -121.3788 |  |  |  |  | 2019 | [8 empty] | PLUMAS COUNTY | Yes
35102732 |  | 2020 |  | BUCOCAMPT 2543 HONEY RUN RD CHICO |  | CLSD |  | 0 | 5147 | 5147 | 0.97481 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 95F | [51 empty] | 5147 | 0.97481 | 0 | 0 | 0.97481 | 0 | 0.97481 | 0 | 0.97481 | 0 | 0 | 0.97481 |  |  |  |  | N/A | [5 empty] | 2019-07-16 |  |  |  | 0 | 480388.7 |  | 187168.5 | 187168.5 | -480388.7 |  | 480388.7 | 0 | 480388.7 | 0 | 492802.0859 | [12 empty] | 39.7482 | -121.6698 |  |  |  |  | 2019 | [5 empty] | Y |  |  | BUTTE COUNTY | Yes
35103065 |  | 2020 | 220 Mile Plan | CWSP - MORAGA 1101 - LR 108540 PH 1 |  | FICL | 12588 | 0 | 12599 | 12599 | 2.3862 | 369 | 0.069886 | 0 | 0 | 0 | 0 | 0 |  |  | DI | 08W | SH | 2020-01-31 | 2019-07-26 |  | 2019-07-26 |  |  | Yes | 2019-07-26 |  | Concord |  |  |  | COMPLETED | No | No |  |  |  | Yes | [5 empty] | Full |  |  | Full |  |  | Just received as of 8/2 | Full |  | Yes |  |  | 43830 | 1980-01-01 | Y | [10 empty] | 12230 | 2.3163 | 369 | 0.069886 | 2.3862 | 0 | 2.3862 | 0 | 2.3862 | 0 | 0 | 2.3862 |  | Keep | 2020-01-31 | Yes | COMP | 2019-08-26 08:00 | 2019-12-18 | 2019-12-18 |  |  | 2019-12-18 |  | Yes | Shovel Ready | 5151556.1 | 6403966.9 |  | 5151555 | -1.1 | 256240.6 | 124.3% | 4895315.5 | 0 | 4895315.5 | 0 | 2683780.0803 | 78 | [9 empty] | Orinda | Contra Costa | 37.852 | -122.1681 | E.5014544.01 |  |  |  | 2020 | Q1 | 2019-07-26 | 2020-01-02 | 2020-01-17 |  | Y | MORAGA 1101108540 | 319 | CONTRA COSTA COUNTY | Yes
35103323 |  | 2020 | 220 Mile Plan | CWSP - MORAGA 1101 - LR 108540 - PH 2 |  | DOCC | 6489 | 0 | 5875 | 5875 | 1.1127 | 5875 | 1.1127 | 0 | 0 | 0 | 0 | 1.7225e-16 |  |  | DI | 08W | SH | 2019-11-05 | 2019-11-05 |  | 2019-11-05 |  |  | Yes | 2019-11-05 |  | Concord |  |  |  |  | No |  |  |  |  | Yes | [5 empty] | Full |  |  | Full |  |  | Bio AMMs for Alameda Whipsnake required | Full |  | Yes |  |  | Need extention of programatic permit | 1980-01-01 | Y | [10 empty] | 0 | 0 | 5875 | 1.1127 | 1.1127 | 0 | 1.1127 | 0 | 1.1127 | 0 | 1.7225e-16 | 1.1127 |  | Keep | 2019-11-05 | Yes | N/A | 2020-01-02 | 2020-02-25 | 2020-02-25 |  |  | 2020-02-25 |  | Yes | Shovel Ready | 3798645.9 | 3744710.1 |  | 4408478 | 609832.1 | 3303531.8 | 98.58% | 495114.1 | 0 | 495114.1 | 0 | 3365458.609 | 48 | [9 empty] | Orinda | Contra Costa | 0 | 0 | E.5014544.02 |  |  |  | 2020 | Q1 | 2019-11-05 | 2020-01-02 | 2020-04-01 |  | Y | MORAGA 1101108540 | 319 | CONTRA COSTA COUNTY | Yes
35103324 |  | 2020 | 220 Mile Plan | CWSP - ROSSMOOR 1102 - OCB |  | CLSD | 4046 | 0 | 4046 | 4046 | 0.76629 | 1639 | 0.31042 | 0 | 0 | 0 | 0 | 0 |  |  | DI | 08W | SH | 2019-11-16 | 2019-08-02 |  | 2019-08-02 |  |  | Yes | 2019-08-02 | [6 empty] | No |  |  |  |  | Yes | [5 empty] | Full |  |  | Full |  |  | Trying to release early | Full |  | Yes |  |  | On private property - no encroachment permit needed. | 1980-01-01 | Y | [10 empty] | 2407 | 0.45587 | 1639 | 0.31042 | 0.76629 | 4.3063e-17 | 0.76629 | 0 | 0.76629 | 0 | 0 | 0.76629 |  | Keep | 2019-11-16 | Yes | N/A | 2019-10-14 | 2020-03-17 | 2020-03-17 |  |  | 2020-03-17 |  | Yes | Shovel Ready | 2510809 | 0 |  | 2510809 | 0 | 2510809 | 0% | 0 | 0 | 0 | 0 | 0 | 21 | [9 empty] | Lafayette | Contra Costa | 0 | 0 | E.5014544.03 |  |  |  | 2020 | Q1 | 2019-08-02 | 2020-04-01 | 2020-04-19 |  | Y | ROSSMOOR 1102CB | 560 | CONTRA COSTA COUNTY | Yes
35103325 |  | 2020 | 220 Mile Plan | CWSP - MORAGA 1102 & 1104 - OCB |  | CLSD | 6506 | 3755 | 3159 | 6914 | 1.3095 | 6914 | 1.3095 | 0 | 0 | 0 | 0 | 0 |  |  | DI | 08W | SH | 2020-03-17 | 2019-09-04 |  | 2019-09-04 |  |  | Yes | 2019-09-04 |  | Concord |  |  |  | COMPLETED | No | YES |  |  |  | Yes | [5 empty] | Full |  |  | Full |  |  | [REDACTED] to coordinate with [REDACTED] | Full |  | Yes |  |  | Submitted on 8/1 to Orinda. Need SSSP | 1980-01-01 | Y | [10 empty] | 0 | 0 | 6914 | 1.3095 | 1.3095 | -1.7225e-16 | 1.3095 | 0 | 1.3095 | 0 | 1.7225e-16 | 1.3095 |  | Keep | 2020-03-17 | Yes | COMP | 2019-11-04 | 2020-04-14 | 2020-04-14 |  |  | 2020-04-14 |  | Yes | Shovel Ready | [12 empty] | 20 | [9 empty] | Orinda | Contra Costa | 0 | 0 | E.5014544.04 |  |  |  | 2020 | Q1 | 2019-09-04 | 2020-01-25 | 2020-03-20 |  | Y | MORAGA 1102CB | 1024 | CONTRA COSTA COUNTY | Yes
35103767 |  | 2020 |  | BUCOCAMPT 5428 PRINCETON WY PARADISE |  | CLSD |  | 0 | 251 | 251 | 0.047538 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 95F | [51 empty] | 251 | 0.047538 | 581 | 0.11004 | 0.15758 | -0.11004 | 0.16288 | 0 | 0.16288 | 0 | -0.005303 | 0.16288 |  |  |  |  | N/A | [5 empty] | 2019-08-10 |  |  |  | 0 | 86462.2 |  | 46473.7 | 46473.7 | -86462.2 |  | 86462.2 | 0 | 86462.2 | 0 | 1818806.4382 | [10 empty] | Paradise | Butte | 39.7457 | -121.644 |  |  |  |  | 2019 | [5 empty] | Y |  |  | BUTTE COUNTY | Yes
35105132 |  | 2020 |  | BUCOCAMPT 3681 DION ROAD OROVILLE |  | FICL |  | 0 | 450 | 450 | 0.085227 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 95F |  |  |  | 2019-07-31 | [47 empty] | 450 | 0.085227 | 581 | 0.11004 | 0.19527 | -0.11004 | 0.19602 | 0 | 0.19602 | 0 | -0.00075758 | 0.19602 |  |  |  |  | N/A | [5 empty] | 2019-09-12 | [25 empty] | Oroville | Butte | 39.7218 | -121.5237 |  |  |  |  | 2019 | [8 empty] | BUTTE COUNTY | Yes
35106022 |  | 2020 |  | BUCOCAMPT 5548 KEMLYN LN PARADISE |  | FICL |  | 0 | 493 | 493 | 0.093371 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 95F | [51 empty] | 493 | 0.093371 | 0 | 0 | 0.093371 | 0 | 0.060606 | 0 | 0.060606 | 0 | 0.032765 | 0.060606 |  |  |  |  | N/A | [5 empty] | 2019-09-18 |  |  |  | 0 | 36118.1 |  | 36237.9 | 36237.9 | -36118.1 |  | 36118.1 | 0 | 36118.1 | 0 | 386822.6531 | [10 empty] | Paradise | Butte | 39.7484 | -121.625 |  |  |  |  | 2019 | [5 empty] | Y |  |  | BUTTE COUNTY | Yes
35106025 |  | 2020 |  | BUCOCAMP 5389 NEWLAND ROAD PARADISE |  | CLSD |  | 0 | 734 | 734 | 0.13902 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 95F | [51 empty] | 734 | 0.13902 | 0 | 0 | 0.13902 | 0 | 0.13902 | 0 | 0.13902 | 0 | 0 | 0.13902 |  |  |  |  | N/A | [5 empty] | 2019-07-20 | [25 empty] | Paradise | Butte | 39.7485 | -121.5952 |  |  |  |  | 2019 | [8 empty] | BUTTE COUNTY | Yes
35106027 |  | 2020 |  | BUCOCAMPT 6709 CHAPMAN LN PARADISE |  | CLSD |  | 0 | 325 | 325 | 0.061553 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 95F | [51 empty] | 325 | 0.061553 | 0 | 0 | 0.061553 | 0 | 0.061553 | 0 | 0.061553 | 0 | 0 | 0.061553 |  |  |  |  | N/A | [5 empty] | 2019-07-05 | [25 empty] | Paradise | Butte | 39.787 | -121.5726 |  |  |  |  | 2019 | [8 empty] | BUTTE COUNTY | Yes
35106042 |  | 2020 | 220 Mile Plan | CWSP - VOLTA 1102 - LR 1648 - PH1.2 |  | FICL | 9801 | 0 | 9606 | 9606 | 1.8193 | 5727 | 1.0847 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 08W | SH | 2019-12-19 | 2019-08-27 | 2019-09-07 | 2019-08-27 |  |  | Yes | 2019-08-27 | (Moved into 2019)7/3 - 7/31: On track for 8/28/2: EEI submitted for 1st ADE Review - ADE TBD8/13: Request for [REDACTED] to assign ADE8/20: 1st ADE correction rtn to contractor8/22: EEI submitted for 2nd rvw [PRELIM DWG ready]8/22: ADE PPROVED - IN PEND | EEI |  |  | Completed | COMPLETED | No |  | 0 | 0 |  | Yes | [5 empty] | Full |  |  | Full |  |  | CIF submitted 8/1/19. Caltrans Permit | Full |  | Yes |  |  | Shasta County Annual | 1980-01-01 | Y | [10 empty] | 3879 | 0.73466 | 5727 | 1.0847 | 1.8193 | 0 | 1.8193 | 0 | 1.8193 | 0 | 0 | 1.8193 |  | Keep | 2019-12-19 | Yes | N/A | 2019-11-14 | 2020-05-14 17:00 | 2020-05-14 08:00 |  |  | 2020-06-08 |  | Yes | Shovel Ready | 4332872.1 | 4370207.4 |  | 4524488 | 191615.9 | 1358748.3 | 100.9% | 2974123.8 | 0 | 2974123.8 | -27670 | 2402112.7495 | 50 | [9 empty] | Shingletown | Shasta | 40.4951 | -121.8557 | E.5014759.02 |  |  | 2020-071 | 2020 | Q1 | 2019-08-27 | 2019-11-14 | 2020-01-31 |  | Y | VOLTA 11021502 | 293 | SHASTA COUNTY | Yes
35106265 |  | 2020 | 220 Mile Plan | CWSP - VOLTA 1102 - LR 1648 - PH1.3 |  | FICL | 10118 | 0 | 9489 | 9489 | 1.7972 | 9033 | 1.7108 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 08W | SH | 2020-03-12 | 2019-08-27 | 2019-09-14 | 2019-08-27 |  |  | Yes | 2019-08-27 | (Moved into 2019)7/3 - 7/31: On track for 8/98/7: EEI submitted for 1st ADE Review - ADE TBD8/13: Request for [REDACTED] to assign ADE8/20: 1st ADE correction rtn to contractor8/22: EEI submitted for 2nd ADE rvw [PRELIM DWG ready]8/22: ADE Approved - IN PEND | EEI |  |  | Completed | COMPLETED | No |  | 0 | 0 |  | Yes | [5 empty] | Full |  |  | Full |  |  | PERTC Requested 10/8/19CIF submitted 8/22/19. Caltrans Annual | Full |  | Yes |  |  | Shasta County Annual | 1980-01-01 | Y | [10 empty] | 456 | 0.086364 | 9033 | 1.7108 | 1.7972 | 0 | 1.7972 | 0 | 1.7972 | 0 | 0 | 1.7972 |  | Keep | 2020-03-12 | Yes | N/A | 2019-10-05 08:00 | 2020-02-17 | 2020-02-17 |  |  | 2020-06-08 |  | Yes | Shovel Ready | 3742002.6 | 2045668.5 |  | 4257794 | 515791.4 | 1857097.7 | 54.66% | 1884904.9 | 0 | 1884904.9 | 0 | 1138279.0262 | 51 | [9 empty] | Shingletown | Shasta | 40.493 | -121.8591 | E.5014759.02 |  |  | 2020-072 | 2020 | Q1 | 2019-08-27 | 2019-11-25 | 2020-02-17 |  | Y | VOLTA 11021502 | 293 | SHASTA COUNTY | Yes
35106277 |  | 2020 |  | BUCOCAMP 1895 MARYWOOD DR PARADISE |  | FICL |  | 0 | 291 | 291 | 0.055114 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 95F | [51 empty] | 291 | 0.055114 | 0 | 0 | 0.055114 | 0 | 0.055114 | 0 | 0.055114 | 0 | 0 | 0.055114 |  |  |  |  | N/A | [5 empty] | 2019-09-17 | [27 empty] | 39.74 | -121.5727 |  |  |  |  | 2019 | [8 empty] | BUTTE COUNTY | Yes
35106331 |  | 2020 | 220 Mile Plan | CWSP - VOLTA 1102 - LR 1648 - PH1.4 |  | DOCC | 12968 | 0 | 12286 | 12286 | 2.3269 | 12286 | 2.3269 | 0 | 0 | 0 | 0 | -3.4451e-16 |  |  | NV | 08W | SH | 2020-03-04 | 2019-08-27 | 2019-09-21 | 2019-08-27 |  |  | Yes | 2019-08-27 | (Moved into 2019) 7/3 - 8/14: On track for 8/16 8/19: EEI submitted for 1st ADE rvw 8/19: 1st ADE corrections rtn to contractor 8/21: EEI submitted for 2nd ADE rvw [PRELIM DWG ready] 8/22: 2nd ADE review complete - routing for approval 8/28: reported to be IN PEND --> [RCC Issue] 9/27 EOD push | EEI |  |  | Completed | COMPLETED | No |  | 0 | 0 |  | Yes | [5 empty] | Full |  |  | Full |  |  | PERTC Requested 10/8/19 CIF submitted 8/23/19 | Full |  | Yes |  |  |  | 1980-01-01 | Y | [10 empty] | 0 | 0 | 12286 | 2.3269 | 2.3269 | 0 | 2.3269 | 0.15909 | 2.486 | 0 | -3.4451e-16 | 2.3269 |  | Keep | 2020-03-04 | Yes | N/A | 2019-11-22 | 2020-05-28 08:00 | 2020-05-28 |  |  | 2020-05-28 |  | Yes | Shovel Ready | 4901211.5 | 6360805.9 |  | 6122412 | 1221200.5 | 3079720.1 | 129.8% | 1819984.5 | 1506.9 | 1821491.4 | 0 | 2733603.7076 | 65 | [9 empty] | Shingletown | Shasta | 40.4974 | -121.8473 | E.5014759.02 |  |  | 2020-073 | 2020 | Q1 | 2019-08-27 | 2020-01-31 | 2020-03-08 |  | Y | VOLTA 11021502 | 293 | SHASTA COUNTY | Yes
35107688 |  | 2020 | 220 Mile Plan | CWSP - VOLTA 1102 - LR 1648 -PH1.1 |  | DOCC | 8915 | 0 | 8626 | 8626 | 1.6337 | 8626 | 1.6337 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 08W | SH | 2019-12-19 | 2019-11-04 | 2019-11-04 | 2019-11-04 |  |  | Yes | 2019-11-04 | (Moved into 2019)7/3 - 7/10: On track for 8/97/10 - 7/16: fielding issue with locked gate and dogs. Received new customer contact7/24 - 7/31: Access issues 8/07: Access issues continue - ALL date push 1 wk for resolution activity8/14 - 8/21: Still in progress of resolving Access issue, w/ PGE support8/21: Will submit for review in 2 parts (part 1 ready/ part 2 3 Locs - Access issues) - EEI to forward Part2 information for PGE support8/22: EEI PT1 submitted for 1st ADE rvw - pending PT2: Access issues x3 LOC (16 17 18) -working with Electric Outreach and it sounds like the contact information we have on record is incorrect (Dogs & Locked Gates)9/04: On Track for 9/30 - fielding to be concluded tomorrow.9/09: EEI PT2 submitted for 1st ADE rvw9/11 - 9/18: ADE to be assigned (push)9/25: Owner ADE coming online - ADE to be assigned this week - Holding target dates - UPDATE: ADE assigned to [REDACTED] 9/2510/02: In Review - 1st ADE target set to 2wk from assignment10/03: ADE 1st rvw corrections rtn to contractor - requesting HFTD peak wind load case. The estimator is saying they were directed to use GO95 load case. (V8 vs V9)10/08: EEI did start and complete this estimate back in July and August, PGE just now getting around to checking the job. Move forward with the estimate as designed unless directed from standards or construction that to update the estimate [REDACTED]; [REDACTED] concurred, in progress ok to finish V8.10/09: 1st rvw target moved to 10/11 - [REDACTED] to confirm 1st review with ADE Ver810/14: ADE returned 1st rvw corrections to contractor - revise and resub10/16: PGE - Areas needing helicopter - inquires in about using composite poles, answers expected by EOW for contractor10/16: EEI submitted for 2nd ADE rvw10/21: ADE rtn from vacation - target 10/23 for rvw completion10/25: ADE rtn 2nd corrections to contractor; EEI submitted for 3rd ADE rvw10/28: ADE approve for routing; contractor to check 2 minor items (Est for enviro consutlants & Loc 24 - request land to rvw easement)- EEI routed | EEI |  |  | Completed | COMPLETED | No |  | 0 | 0 |  | Yes | [5 empty] | Full |  |  | Full |  |  | CIF Submitted 8/21/19. Caltrans Permit | Full |  | Yes |  |  | Shasta County Annual | 1980-01-01 | Y | [10 empty] | 0 | 0 | 8626 | 1.6337 | 1.6337 | 0 | 1.6337 | 0 | 1.6337 | 0 | 0 | 1.6337 |  | Keep | 2019-12-19 | Yes | N/A | 2020-01-07 | 2020-04-10 08:00 | 2020-04-10 08:00 |  |  | 2020-04-10 |  | Yes | Shovel Ready | 3932634.5 | 3347425 |  | 4120715 | 188080.5 | 2053126 | 85.11% | 1879508.5 | 0 | 1879508.5 | 0 | 2048968.6993 | 45 | [9 empty] | Shingletown | Shasta | 40.4948 | -121.873 | E.5014759.01 |  |  | 2020-070 | 2020 | Q1 | 2019-11-04 | 2020-02-17 | 2020-03-12 |  | Y | VOLTA 11021502 | 293 | SHASTA COUNTY | Yes
35107689 |  | 2020 | 220 Mile Plan | OCGC CWSP - PINE GROVE 1102 - LR1222 - |  | FICL | 10853 | 0 | 10737 | 10737 | 2.0335 | 10737 | 2.0335 | 0 | 0 | 0 | 0 | 0 |  |  | ST | 08W | SH | 2020-04-30 | 2019-11-30 | 2019-11-18 | 2019-11-30 |  |  | Yes | 2019-11-18 | 12/25: SAP Export - PEND11/14: ADE APPROVED FOR routing11/13: EN submitted for 2nd ADe rvw11/05: Team assigned to corrections - Volta 2.4 prioritized; Push to EOW [11/08]10/29: Target to submit by Friday10/22 <-- 10/15: Push - EN requesting clarity on differing approach information from PGE (ADE/Planner - CMCS..Construction Notes...); and remaining correction information from ADE10/10: 1st ADE corrections rtn to contractor10/09: ADE assigned [REDACTED]10-08 <-- 9/24: ADE to be assigned9/18: EN submitted for 1st ADE rvw9-17 <-- 9/10: Working with ADE to ensure quality is what ADE is looking for (Elevation Standards), Push to Monday 9/16; 9/189/03: On Track for 9/108/13 Fielding planned for EOM (Aug) | EN |  |  | Normal | COMPLETED | No | Obsolete (CONS+) | 0 | 0 |  | Yes |  |  |  | 2020-04-30 | 2020-04-30 | Full |  |  | Full |  |  | PERTC released - Caltrans due on 4/20 - Dist. 10 - ERTC to be issued before this date. Received Caltrans permit and are releasing an ERTC for a GC yard as well. | Full |  | Yes |  |  |  | 1980-01-01 | Y | [10 empty] | 0 | 0 | 10737 | 2.0335 | 2.0335 | 0 | 2.0942 | 0 | 2.0942 | 0 | -0.060644 | 2.0336 |  | Keep | 2020-02-06 17:00 | Yes | COMP | 2020-02-19 08:00 | 2020-05-11 | 2020-05-11 |  |  | 2020-05-11 |  | Yes | Shovel Ready | 4631785.2 | 4652155 |  | 5851741 | 1219955.8 | 4620834.4 | 100.4% | 10569.3 | 381.5 | 10950.8 | 0 | 2287731.9922 | 55 | [9 empty] | Pioneer | Amador | 38.436 | -120.5561 | E.5014745.01 |  |  | 2020-023 | 2020 | Q1 | 2019-11-18 | 2020-02-07 | 2020-04-30 |  | Y | PINE GROVE 11021222 | 20 | AMADOR COUNTY | Yes
35109540 |  | 2020 | 220 Mile Plan | CWSP-EL DORADO 2101-19752- PHASE 1.2 |  | DOCC | 7717 | 0 | 7065 | 7065 | 1.3381 | 7065 | 1.3381 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | SH | 2019-10-09 | 2019-10-09 | 2019-10-09 | 2019-10-09 |  |  | Yes | 2019-10-09 | 7/3: QUES to review to provide review on 1st ADE Submital7/16 - 8/7 : On track8/14: Finishing internal rvw - 8/168/21: Finalizing Internal QUES rvw - 8/238/21: QUES submitted for 1st ADE rvw8/22: ADE assigned - [REDACTED]8/23: 1st ADE corrections rtn to contractor9/03: ADE returned (Final) review for corrections9/04: Target submittal 9/5 --> [RCC Issue]9/11: Working through final request (ADE needs pictures), looking at options avoid refielding in order to submit this week. If field activity is avoidable - target EOW submittal.9/18: QUES submitted for 2nd ADE rvw9/20: Rvw rtn to Contractor; QUES submitted for 3rd ADE rvw9/24: Rvw completed by ADE; Ready for routing9/25: Target for routing - EOW 9/2710/02: pending routing10/09: Status? Complete by 10/08? - [REDACTED] approved on 10/04 - SAP glitch-tag submitted to correct status | QUES |  |  | Completed | COMPLETED | No |  | 0 | 0 |  | Yes | [5 empty] | Full |  |  | Full |  |  | CIF submitted 7/30/19. Expedite if OH | Full |  | Yes |  |  | No permit needed | 1980-01-01 | Y | [10 empty] | 0 | 0 | 7065 | 1.3381 | 1.3381 | 0 | 1.3381 | 0 | 1.3381 | 0 | 0 | 1.3381 |  | Keep | 2019-10-03 | Yes | N/A | 2019-10-16 | 2020-02-18 | 2020-02-18 |  |  | 2020-02-18 |  | Yes | Shovel Ready | 3189967 | 735209.6 |  | 4228889 | 1038922 | 2860553.8 | 23.04% | 185160.1 | 144253.1 | 329413.2 | -186606 | 549456.0068 | 39 | [9 empty] | Pollock Pines | El Dorado | 0 | 0 | E.5015417.02 |  |  |  | 2020 | Q1 | 2019-10-09 | 2020-01-02 | 2020-02-20 |  | Y | EL DORADO PH 210119752 | 13 | EL DORADO COUNTY | Yes
35109542 |  |  |  | CWSP-EL DORADO 2101-19752- PHASE 1.4 |  | DOCC | 9724 | 0 | 9673 | 9673 | 1.832 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | SH | 2019-11-20 | 2019-08-23 | 2019-09-27 | 2019-08-23 |  |  | Yes | 2019-08-23 | 7/3: QUES to review to provide review on 1st ADE Submital7/16 - 8/7 : On track8/8: QUES Submitted for 1st ADE rvw - ADE [REDACTED]8/20: Corrections rtn to contractor[PRELIM DWG ready]8/23: Approved - PEND (per [REDACTED]) | QUES |  |  | Completed | COMPLETED | No |  | 0 | 0 | [7 empty] | Full |  |  | Full |  |  | CIF submitted 7/30/19 - Expedite if OH | Full |  | Yes |  |  | No permit needed | 1980-01-01 | Y | [10 empty] | 9673 | 1.832 | 0 | 0 | 1.832 | 0 | 1.832 | 0 | 1.832 | 0 | 0 | 1.832 |  |  | 2019-11-20 |  | N/A | 2019-09-16 | 2019-11-09 | 2019-11-09 |  |  | 2020-01-30 |  |  |  | 2785685.9 | 2098669.5 |  | 3529311 | 743625.1 | 544129.2 | 75.33% | 2084656.3 | 156900.4 | 2241556.7 | -200608 | 1145557.217 | 49 | [9 empty] | Pollock Pines | El Dorado | 0 | 0 | E.5015417.04 | MX |  |  | 2019 | Q4 |  |  |  |  | Y | EL DORADO PH 210119752 | 13 | EL DORADO COUNTY | Yes
35109543 |  |  |  | CWSP-EL DORADO 2101-19752- PHASE 1.5 |  | DOCC | 9909 | 0 | 8922 | 8922 | 1.6898 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | SH | 2019-11-20 | 2019-09-12 | 2019-09-27 | 2019-09-12 |  |  | Yes | 2019-09-12 | 7/3: QUES to review to provide review on 1st ADE Submital7/16: Request submitted for Job Walk w/ Construction; AB Loop terrain concerns (inclines and hvy vegetation)7/19: QUES Waiting for Construction to confirm a date [REDACTED]7/31: Completed walk - Engineer submitting change - Dates to be reviewed upon receipt8/7 - 8/14 On Track for 8/168/15: QUES submitted for 1st ADE rvw - ADE TBD8/21: ADE [REDACTED] assigned8/22: ADE target for 1st Rvw Completion 8/26 latest8/23 ADE Review STARTED8/25: 1st ADE corrections returned to contractor9/04: QUES submitted for 2nd ADE rvw, [PRELIM DWG ready]; QUES to confirm copy sent to PM - RCC Issue9/11: RCC issue reported as resolved - [REDACTED] approved - need to finalize processing | QUES |  |  | Completed | COMPLETED | No |  | 0 | 0 | [7 empty] | Full |  |  | Full |  |  | CIF submitted 7/30/19 - Expedite if OH | Full |  | Yes |  |  | No permit needed | 1980-01-01 | Y | [10 empty] | 8922 | 1.6898 | 0 | 0 | 1.6898 | 0 | 1.6898 | 0 | 1.6898 | 0 | 0 | 1.6898 |  |  | 2019-11-20 |  | N/A | 2019-10-03 | 2020-03-06 | 2020-03-06 |  |  | 2019-12-07 |  |  |  | 3151028.8 | 3063735.7 |  | 3608462 | 457433.2 | -298412.7 | 97.22% | 3218762.5 | 230679 | 3449441.5 | -196902 | 1813105.189 | 50 | [9 empty] | Pollock Pines | El Dorado | 0 | 0 | E.5015417.05 | MX |  |  | 2019 | Q4 |  |  |  |  | Y | EL DORADO PH 210119752 | 13 | EL DORADO COUNTY | Yes
35109545 |  | 2020 | 220 Mile Plan | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 |  | DOCC | 12893 | 0 | 12821 | 12821 | 2.4282 | 12821 | 2.4282 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | SH | 2019-12-19 17:00 | 2019-11-08 |  | 2019-11-08 |  |  | Yes | 2019-11-08 | 11/12: APPROVED - PEND11/08: In Routing - Kicked back for corrections11/06: On Track for EOW10/31: CAL reviewed and relinked - ready for rvw10/30: Re-review QC check; cursory rvw surfaced errors - ADE on vacation10/23: Routed - awaiting approval10/18: ADE 2nd corrections rtn to contractor10/16: Check in with ADE - Starting Tomorrow; completing another project10/10: CAL Submitted for 2nd ADE Rvw [PRELIM DWG ready]10/09: On Track for 10/10: 2nd submittal10/03: ADE 1st corrections returned to contractor10/02 <-- 9/04: in Review; ADE Workload Impact - 10/02 [REDACTED] to follow up on status with ADE--> [RCC Issue]8/21: ADE Rvw still in progress - target 8/23 correction rtn to contractor8/2: CAL submitted for 1st ADE review - [REDACTED]7/31 <-- 7/3: On track for 8/5; 1st submittal | CAL |  |  | Completed | COMPLETED | No |  | 0 | 0 |  | Yes | [5 empty] | Full |  |  | Full |  |  | CIF submitted 8/5/19. Expedite if OH | Full |  | Yes |  |  | No permit needed | 1980-01-01 | Y | [10 empty] | 0 | 0 | 12821 | 2.4282 | 2.4282 | -3.1006e-15 | 2.4282 | 0 | 2.4282 | 0 | 3.1006e-15 | 2.4282 |  | Keep | 2019-12-19 17:00 | Yes | N/A | 2019-12-02 08:00 | 2020-04-17 | 2020-04-17 |  |  | 2020-04-17 |  | Yes | Shovel Ready | 4499650.7 | 2578576 |  | 4499650 | -0.7 | 3871765.2 | 57.3% | 531278.5 | 96607 | 627885.5 | 0 | 1061920.3869 | 65 | [9 empty] | Pollock Pines | El Dorado | 0 | 0 | E.5015416.02 |  |  |  | 2020 | Q1 | 2019-11-08 | 2019-12-02 | 2020-04-03 |  | Y | EL DORADO ph 210119752 | 13 | EL DORADO COUNTY | Yes
35109547 |  | 2020 | 220 Mile Plan | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 |  | DOCC | 8196 | 0 | 8058 | 8058 | 1.5261 | 8058 | 1.5261 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | SH | 2019-10-17 | 2019-10-16 |  | 2019-10-16 |  |  | Yes | 2019-10-16 | 10//16 IN PEND10/14: ADE approved- Routed by CO10/14: CAL submitted for 2nd ADE rvw [PRELIM DWG ready]10/09: ADE 1st corrections rtn to contractor10/08: ADE assigned [REDACTED] - 1st Rvw Set at 2 wks9/04 - 10/02: in Review; ADE Workload impact - 10/02 (push 2 wks)--> [RCC Issue]8/21: 1st Submittal in - (Potential AUG Priority GAP FILL)ADE assigned [REDACTED]8/11: CAL submitted for 1st ADE rvw7/3 - 8/7: On track for 8/12 | CAL |  |  | Completed | COMPLETED | No |  | 0 | 0 |  | Yes | [5 empty] | Full |  |  | Full |  |  | CIF submitted 8/9/19 | Full |  | Yes | 2020-12-31 |  | Shasta County Annual | 1980-01-01 | Y | [10 empty] | 0 | 0 | 8058 | 1.5261 | 1.5261 | 0 | 1.5261 | 0 | 1.5261 | 0 | 0 | 1.5261 |  | Keep | 2019-10-17 | Yes | N/A | 2020-01-06 | 2020-03-13 | 2020-03-13 17:00 |  |  | 2020-03-13 |  | Yes | Shovel Ready | 3530636.4 | 684137.7 |  | 3530637 | 0.6 | 3177040.3 | 19.37% | 275303 | 78293.1 | 353596.1 | 0 | 448280.8459 | 41 | [9 empty] | Pollock Pines | El Dorado | 0 | 0 | E.5015416.04 |  |  |  | 2020 | Q1 | 2019-10-16 | 2020-01-02 | 2020-03-10 |  | Y | EL DORADO ph 210119752 | 13 | EL DORADO COUNTY | Yes
35109548 |  | 2020 | 220 Mile Plan | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 |  | DOCC | 16324 | 0 | 15058 | 15058 | 2.8519 | 15058 | 2.8519 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | SH | 2020-02-19 17:00 | 2020-01-15 |  | 2020-01-15 | 2019-11-04 | 2019-11-04 | Yes | 2020-01-06 | 04/22: Reaffirmed - pole/change post est. per field request; direct/forward to [REDACTED] (Internal) Team03/11: Est time & rcpt of wood pole places availability at about same time as composite - EST on hold for a final decision; Forward information to [REDACTED] for review and assess for internal assignment.03/04: EST rcv'd req to move to wood poles; per Construction - breaking ground - EST to review and advise on submittal date.*****12/31: Estimator change - to be stamped and uploaded upon OCalc completion12/30: Approval Rejected - for final corrections12/18: push 2wk: 133 PLCs - request for restamp - target EOW to complete/submit12/13: ADE rtn 3rd corrections to contractor - Doc Electronically signed.12/11: EOD Push - ADE notified 3rd rvw started 12/09 - Working in tandum with EST - target Friday 12/06: CAL submitted for 3rd ADE rvw12/04 - 11/27: On Track for 12/0611/20: Held - Composite pole impact; changes needed11/12: Push 1wk - ADE corrections returned to contractor (3rd rvw anticipated - qty of errors) - EST transferring to more Sr. estimator.11/04: CAL submitted for 2nd ADE rvw10/31: CAL - EES ade redlines corrections is taking longer than expected due to 133 locations slowing down the software. Target Monday/Tuesday submissionminor changes in Ocalc & JPA 25 pole limit on the intents for segment 5. 10/30: submittal on track10/18: ADE rtn 1st corrections to contractor10/16: 1st Review - On Track for EOW10/09: ADE update - attempting 10 poles/day; finding many issues10/02: ADE status update - 1st rvw 25% [130 Poles] (1st rvw set at 2 wk)9/26: ADE reassigned to [REDACTED] 9/25: ADE workload - tied up w/ other Rvws - Rvw not started9/04 - 09/24: in Review; --> [RCC Issue]8/26: EES issues resolved8/23: CAL Submitted for 1st ADE rvw8/21: CAL UD - EES issues/bottleneck - slowing progress - push to 8/26 Focus for target of 8/23 in meeting8/14: Focus will be on completing 2.5 targeted for early-mid next week and then move into 2.1 & 2.3 completions8/7: Push 1wk ALL dates to allow time for 2.1 resolution; potential resource availabilty impacts base on resolution timing7/31: [**] 1st Submittal dependent on 2.1 completion - resource assignment7/3 - 7/16: On track for 8/16 | CAL |  |  | 2020 - Q1- M3 [R0] | COMPLETED | No | Obsolete (CONS+) | 0 | 0 |  | Yes | [5 empty] | Full |  |  | Full |  |  | ? Partial Release received. Only 1 pole not released. Easement acquired. 1 pole on USFS | Full |  | Yes | 2020-12-31 |  | Permit Request sent 8/16/19 | 1980-01-01 | Y | [10 empty] | 0 | 0 | 15058 | 2.8519 | 2.8519 | 0 | 2.8519 | 0 | 2.8519 | 0 | 0 | 2.8519 |  | Keep | 2020-02-19 17:00 | Yes | N/A | 2020-01-27 | 2020-05-22 | 2020-05-22 |  |  | 2020-05-22 |  | Yes | Shovel Ready | 5480368 | 4908749 |  | 7082947 | 1602579 | 5412542 | 89.56% | 67826 | 0 | 67826 | 0 | 1721224.2476 | 82 |  | ADE Bandwidth | [7 empty] | Pollock Pines | El Dorado | 0 | 0 | E.5015416.05 |  |  |  | 2020 | Q1 | 2020-01-06 | 2020-01-02 | 2020-04-01 |  | Y | EL DORADO ph 210119752 | 13 | EL DORADO COUNTY | Yes
35109549 |  | 2020 | 220 Mile Plan | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 |  | DOCC | 6898 | 0 | 7062 | 7062 | 1.3375 | 3446 | 0.65265 | 0 | 0 | 0 | 0 | -1.7225e-16 |  |  | SI | 08W | SH | 2019-11-20 | 2019-09-18 | 2019-09-18 | 2019-09-18 |  |  | Yes | 2019-09-18 | 7/9: on track 7/197/16: on track 7/197/19: BCF submitted for 1st ADE Rvw7/26: ADE returned corrections to Vendor8/2: 2nd ADE review for this project was not required. Comments from the 1st ADE review have been addressed and the project has been routed for approval [Prelim DWG ready]8/27: [REDACTED] - ready for approval8/28: Concurrance req surfaced correction needs - [REDACTED] to submit for corrective action with Contractor8/30: Approvals for 35109549 have been successfully routed through EES8/27: ADER - Kicked back for corrections8/30: BCF Submitted for 3rd ADE Rvw--> [RCC Issue] 9/27 EOD push9/10: RCC Issues corrected9/16: Applying corections, Applied LATs & LONGs9/17: Ocalc change/Stamp - then ready to route9/18: In PEND | BCF |  |  | Completed | COMPLETED | No |  | 0 | 0 |  | Yes | [5 empty] | Full |  |  | Full |  |  | Partial Release. Veg scope provided 8/29/19. The poles are NOT on USFS. Since we are close to the USFS boundary, some tree removal or tree trimming may affect USFS lands, we need to notify FS for veg work that is happening adjacent to poles 22-25. | Full |  | Yes | 2020-12-31 |  | Permit request sent 7/24/19 | 1980-01-01 | Y | [10 empty] | 3616 | 0.68485 | 3446 | 0.65265 | 1.3375 | 0 | 1.3375 | 0 | 1.3375 | 0 | -1.7225e-16 | 1.3375 |  | Keep | 2019-11-20 | Yes | N/A | 2019-10-04 | 2020-04-17 | 2020-04-17 17:00 |  |  | 2020-04-17 |  | Yes | Shovel Ready | 3123544.1 | 3188289.9 |  | 3123544 | -0.1 | 641917.2 | 102.1% | 2357709.6 | 123917.3 | 2481626.9 | 0 | 2383768.1495 | 35 | [9 empty] | Pollock Pines | El Dorado | 0 | 0 | E.5015415.02 |  |  |  | 2020 | Q1 | 2019-09-18 | 2020-01-02 | 2020-03-20 |  | Y | EL DORADO ph 210119752 | 13 | EL DORADO COUNTY | Yes
35109550 |  | 2020 | 220 Mile Plan | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 |  | DOCC | 9612 | 0 | 10111 | 10111 | 1.915 | 1537 | 0.2911 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | SH | 2019-11-20 | 2019-09-18 |  | 2019-09-18 |  |  | Yes | 2019-09-18 | 7/9 - 7/22: on track 7/267/26: BCF submitted for 1st ADE Rvw7/30: ADE [REDACTED] assigned8/6: ADE corrections returned to Contractor8/9: BCF submitted for 2nd ADE Rvw - corrections applied [Prelim DWG ready]8/9: Corrections addressed - routed for approval8/15: Routed for Approval [REDACTED] 8/29: Stamp/OCALCs uploaded to SAP9/03: Corrections (3rd round), sent to BCF - target completion 9/03 for correction submittal--> [RCC ISSUE] 9/27 EOD push9/10: BCF submitted for 3rd Rvw - RCC Issue corrected9/16: BCF - reported 'ready to route' - resolving validation error9/17: Error cleared - Adding LATs & LONGs; RCC issue to be corrected by 9/189/18: Moved into PEND/UNSC | BCF |  |  | Completed | COMPLETED | No |  | 0 | 0 |  | Yes | [5 empty] | Full |  |  | Full |  |  | CIF submitted 8/1/19. Expedite if OH | Full |  | Yes | 2019-12-31 |  | Permit Request sent 8/1/19 | 1980-01-01 | Y | [10 empty] | 8574 | 1.6239 | 1537 | 0.2911 | 1.915 | 0 | 1.915 | 0 | 1.915 | 0 | 0 | 1.915 |  | Keep | 2019-11-20 | Yes | N/A | 2019-10-04 | 2020-01-31 | 2020-01-31 |  |  | 2020-01-31 |  | Yes | Shovel Ready | 3044148 | 3249755 |  | 3044150 | 2 | -130745.2 | 106.7% | 3070771.7 | 104121.5 | 3174893.2 | 0 | 1697033.5674 | 49 | [9 empty] | Pollock Pines | El Dorado | 0 | 0 | E.5015415.03 |  |  |  | 2020 | Q1 | 2019-09-18 | 2020-01-02 | 2020-01-31 |  | Y | EL DORADO ph 210119752 | 13 | EL DORADO COUNTY | Yes
35109551 |  | 2020 | 220 Mile Plan | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 |  | DOCC | 7659 | 0 | 7579 | 7579 | 1.4354 | 1810 | 0.3428 | 0 | 0 | 0 | 0 | -1.7225e-16 |  |  | SI | 08W | SH | 2019-09-30 | 2019-09-12 | 2019-09-12 | 2019-09-12 |  |  | Yes | 2019-09-12 | 8/01: BCF submitted for 1st ADE Rvw8/2: ADE [REDACTED] assigned8/12: 1st ADE corrections rtn to contractor8/21: Target 1st correction submittal 8/228/22:BCF submitted for 2nd ADE Rvw - ISSUE - Issue of EES joint utility credits, [REDACTED] to support in resolution [Prelim DWG ready]8/29: issue in EES with the approvals screen being blank. I have submitted a ticket to estimating support 8/29: 2nd ADE Corrections rtn to contractor8/30: ADER - Kick Back for corrections9/03: Corrections targeted for completion and submittal 9/039/10: BCF Submitted for 3rd ADE rvw - RCC Issue corrected | BCF |  |  | Completed | COMPLETED | No |  | 0 | 0 |  | Yes | [5 empty] | Full |  |  | Full |  |  | Partial ERTC Received. Poles on USFS Loc 15, 16, 40 | Full |  | Yes | 2020-12-31 |  | Permit Request sent 8/1/19 | 1980-01-01 | Y | [10 empty] | 5769 | 1.0926 | 1810 | 0.3428 | 1.4354 | 0 | 1.4354 | 0 | 1.4354 | 0 | -1.7225e-16 | 1.4354 |  | Keep | 2019-09-30 | Yes | N/A | 2019-10-02 | 2020-04-17 | 2020-04-17 17:00 |  |  | 2020-04-17 |  | Yes | Shovel Ready | 3172297.8 | 2607655.2 |  | 3172299 | 1.2 | 381764.3 | 82.2% | 2646447.2 | 144086.3 | 2790533.5 | 0 | 1816653.8403 | 39 | [9 empty] | Pollock Pines | El Dorado | 0 | 0 | E.5015415.04 |  |  |  | 2020 | Q1 | 2019-09-12 | 2020-01-02 | 2020-03-20 |  | Y | EL DORADO ph 210119752 | 13 | EL DORADO COUNTY | Yes
35109552 |  | 2020 | 220 Mile Plan | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 |  | DOCC | 11277 | 0 | 11175 | 11175 | 2.1165 | 1491 | 0.28239 | 0 | 0 | 0 | 0 | 3.4451e-16 |  |  | SI | 08W | SH | 2019-09-30 | 2019-08-29 | 2019-09-25 | 2019-08-29 |  |  | Yes | 2019-08-29 | 8/21: ADE 1st corrections rtn to contractor (minor corrections) 8/27: BCF target submittal 8/30 - will check to verify for earlier submittal (8/29) 8/27: BCF submitted corrections for 2nd ADE rvw [PRELIM DWG ready] 8/27: APPROVED by ADE - BCF routing through EDRS --> [RCC Issue] 9/27 EOD push 9/10: RCC Issue corrrected - Routed for Approval 9/17: On target - routing | BCF |  |  | Completed | COMPLETED | No |  | 0 | 0 |  | Yes | [5 empty] | Full |  |  | Full |  |  | CIF submitted 8/8/19. Expedite if OH | Full |  | Yes | 2020-12-31 |  | Permit Request sent 8/8/19 | 1980-01-01 | Y | [10 empty] | 9684 | 1.8341 | 1491 | 0.28239 | 2.1165 | 0 | 2.1165 | 0 | 2.1165 | 0 | 3.4451e-16 | 2.1165 |  | Keep | 2019-09-30 | Yes | N/A | 2019-10-07 | 2020-02-11 | 2020-02-11 |  |  | 2020-02-11 |  | Yes | Shovel Ready | 5804262.1 | 4704317.4 |  | 5804263 | 0.9 | 1234241.7 | 81.04% | 4523869.9 | 46150.5 | 4570020.4 | -298999 | 2222711.04 | 57 | [9 empty] | Pollock Pines | El Dorado | 0 | 0 | E.5015415.05 |  |  |  | 2020 | Q1 | 2019-08-29 | 2020-01-02 | 2020-02-07 |  | Y | EL DORADO ph 210119752 | 13 | EL DORADO COUNTY | Yes
35109553 |  | 2020 | 220 Mile Plan | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 |  | DOCC | 14414 | 0 | 14080 | 14080 | 2.6667 | 6611 | 1.2521 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | SH | 2019-11-20 | 2019-09-26 | 2019-09-26 | 2019-09-26 |  |  | Yes | 2019-09-26 | 7/9 - 8/13: on track 8/198/20: BCF submitted for 1st ADE rvw - ADE TBD8/22: ADE Assigned - [REDACTED]9/03: Still in ADE Review--> [RCC Issue]9/10 RCC Issue corrected - Still in review9/13: 1st ADE corrections rtn to contractor9/16: BCF Applying corrections9/17: Corrections on target9/19: BCR submitted for 2nd ADE rvw9/23: 2nd Rvw corrections Rtn to Contractor (Some OCalcs incorrect)9/23: BCR submitted for 3rd ADE rvw | BCF |  |  | Completed | COMPLETED | No |  | 0 | 0 |  | Yes | [5 empty] | Full |  |  | Full |  |  | CIF Submitted 8/20/19 | Full |  | Yes | 2021-04-29 |  | Permit Request sent 8/20/19 | 1980-01-01 | Y | [10 empty] | 7469 | 1.4146 | 6611 | 1.2521 | 2.6667 | 0 | 2.6667 | 0 | 2.6667 | 0 | 0 | 2.6667 |  | Keep | 2019-11-20 | Yes | N/A | 2019-10-21 | 2020-01-29 | 2020-01-29 |  |  | 2020-01-29 |  | Yes | Shovel Ready | 4009924.5 | 2954658.2 |  | 4009924 | -0.5 | 1353889.5 | 73.68% | 2545093.1 | 110941.9 | 2656035 | 0 | 1107996.825 | 73 | [9 empty] | Pollock Pines | El Dorado | 0 | 0 | E.5015415.06 |  |  |  | 2020 | Q1 | 2019-09-26 | 2020-01-02 | 2020-01-29 |  | Y | EL DORADO ph 210119752 | 13 | EL DORADO COUNTY | Yes
35109554 |  | 2020 | 220 Mile Plan | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 |  | DOCC | 7044 | 0 | 6641 | 6641 | 1.2578 | 6641 | 1.2578 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | SH | 2020-05-05 | 2020-01-17 | 2020-01-17 | 2020-01-17 | 2019-09-04 | 2019-09-04 | Yes | 2020-01-17 | 03/26 pole needed to be moved about 10' out of the gully it's currently in 01/15: Routed - reviewed; request for final corrections01/14: QUES submitted for ADE final check01/13: QUES submitted for 5th ADE rvw - ADE rtn 5ht corrections; fix loc and route01/03: ADE rtn 4th corrections to contractor - large amount of corrections12/20: QUES submitted for 4th ADE rvw (2) - applied v8 adjustments12/18: On Track for submittal12/11: EOD push to apply ADE design change request12/10: ADE review on hold for EST to correct pole classes (-008 Fire Rebuild Design Guidance)12/09 QUES submitted for 4th ADE rvw11/27: Applying additional corrections from last review 11/20: Design change impact extended rvw process11/14: ADE rtn 3rd corrections to contractor11/13: Check target with ADE - Target by EOW11/06: Redesign/ADE - Resourcing Push for rvw timing.11/05: Submitted for 3rd ADE rvw10/29: In stamping: Target by EOW10/23: Resolution being finalized - Submittal target 10/2510/17: Est - No option to select PLDBID, believe this must be because job was set up in EES prior to the update on EES which brought in the Estimate Structure Builder. - Estimator seeking assistance for a fix.10/17: Per ADE - this job was not approved before the deadline of the implementation of the new PLDBID requirements in EES, this information is required to be inputted before it can be approved by ADE's 10/16: Redoing OCALCS, ADE requested change/information - Wens 23rd target for submittal10/09: Can EOD be held for final processing? (4day push otherwise)10/08: Working Tie-ins with 35057018 - 2nd corrections rtn to contractor9/24 - 10/02: In Review; 10/02 [REDACTED] reached out for status update (waiting on joint pole)9/16: ADE was pulled for previously scheduled work, returned to review.9/11: In Review--> [RCC Issue]9/04: QUES submitted for 2nd ADE rvw - [PRELIM DWG ready]8/27: ADE assigned8/23: QUES submitted for 1st ADE rvw8/21: CAD completed - submittal by 8/23 - Assign ADE [REDACTED] when rcv'd8/16: Submitting Friday - stuck in CAD 8/167/24 - 8/07: On Track7/3 - 7/16: QUES to review to provide review on 1st ADE Submital | QUES |  |  | Completed | COMPLETED | No | Obsolete (CONS+) | 0 | 0 |  | Yes | [5 empty] | Full |  |  | Full |  |  | CIF submitted 8/23/19. Expedite if OH | Full |  | Yes | 2020-12-31 |  | Desiree to review on 8/20. Permit request sent 8/23/19 | 1980-01-01 | Y | [10 empty] | 0 | 0 | 6641 | 1.2578 | 1.2578 | 0 | 1.2578 | 0 | 1.2578 | 0 | 0 | 1.2578 |  | Keep | 2020-05-05 | Yes | COMP | 2020-02-13 | 2020-04-03 | 2020-04-03 |  |  | 2020-04-03 |  | Yes | Shovel Ready | 2276638 | 1226972.7 |  | 2287663 | 11025 | 2095587.7 | 53.89% | 27262.3 | 153788 | 181050.3 | 0 | 975518.1232 | 36 |  | Veg Started | [7 empty] | Pollock Pines | El Dorado | 0 | 0 | E.5015414.02 |  |  |  | 2020 | Q1 | 2020-01-17 | 2020-02-13 | 2020-03-31 |  | Y | EL DORADO ph 210119752 | 13 | EL DORADO COUNTY | Yes
35109555 |  | 2020 | 220 Mile Plan | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 |  | DOCC | 11846 | 0 | 11678 | 11678 | 2.2117 | 7702 | 1.4587 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | SH | 2019-11-08 | 2019-11-08 | 2019-11-08 | 2019-11-08 |  |  | Yes | 2019-11-08 | 11/06: ADE unable to 'concur' - working with EES team to resolve issue - [REDACTED] working Rvw and directed on work around to clear EES errors.11/01: QUES submitted for EES approval - corrections in process10/29: Reassigned Estimator: corrections and routing targeted for EOW10/25 ADE rtn 2nd correction to contractor - correct for routing10/22: ADE rtn from vaca - targeting rvw 10/2310/16: Check in with ADE - push 5day10/08: QUES submitted for 2nd ADE rvw - [PRELIM DWG ready]10/02: 2nd submittal target - 10/11; volume of changes - Wood conversion, internal changes9/25: Target for submittal 9/27 - QUES to advise of change9/18: Email to leave as Version 8 / not worry about composite poles: Est. to be converted back to wood.9/11:on target9/09: 1st review returned to contractor--> [RCC Issue]9/04: in Review8/21: ADE assigned8/13: QUES submitted for 1st ADE rvw8/07: On Track for 8/97/31: AutoCAD issues resolved, anticipated to submit by end of week.7/24: AutoCAD issues; Risk of push7/16: May push 1wk for Internal Review7/3: QUES to review to provide review on 1st ADE Submital | QUES |  |  | Completed | COMPLETED | No |  | 0 | 0 |  | Yes | [5 empty] | Full |  |  | Full |  |  | CIF submitted 8/5/19. Expedite if OH | Full |  | Yes | 2020-12-31 |  | Permit request sent 8/5/49 | 1980-01-01 | Y | [10 empty] | 3976 | 0.75303 | 7702 | 1.4587 | 2.2117 | 0 | 2.2117 | 0 | 2.2117 | 0 | 0 | 2.2117 |  | Keep | 2019-11-08 | Yes | N/A | 2019-12-09 | 2020-02-21 | 2020-02-21 |  |  | 2020-02-21 |  | Yes | Shovel Ready | 4471950.5 | 5733985.2 |  | 4477708 | 5757.5 | 1456983.1 | 128.2% | 2824429.5 | 190537.9 | 3014967.4 | -390892 | 2592519.4259 | 60 | [9 empty] | Pollock Pines | El Dorado | 0 | 0 | E.5015414.03 |  |  |  | 2020 | Q1 | 2019-11-08 | 2020-01-02 | 2020-02-21 |  | Y | EL DORADO ph 210119752 | 13 | EL DORADO COUNTY | Yes
35109556 |  | 2020 | 220 Mile Plan | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 |  | DOCC | 2783 | 0 | 1618 | 1618 | 0.30644 | 1618 | 0.30644 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | SH | 2019-10-16 | 2019-08-26 | 2019-09-05 | 2019-08-26 |  |  | Yes | 2019-08-26 | 7/3 - 7/16: QUES to review to provide review on 1st ADE Submital7/24 - 7/31: On Track for 7/318/6: QUES submitted for 1st ADE Review - ADE TBD; Holding EOD8/1: ADE Assigned - [REDACTED]8/15: 1st ADE corrections rtn to contractor8/21: 2nd submittal scheduled for 8/21 (today)[PRELIM DWG ready]8/26: Approved - PEND | QUES |  |  | Completed | COMPLETED | No |  | 0 | 0 |  | Yes | [5 empty] | Full |  |  | Full |  |  | Partial ERTC Received. Poles loc 20-26 | Full |  | Yes | 2020-12-31 |  | Permit Request sent 8/1/19 | 1980-01-01 | Y | [10 empty] | 0 | 0 | 1618 | 0.30644 | 0.30644 | 0 | 0.30644 | 0 | 0.30644 | 0 | 0 | 0.30644 |  | Keep | 2019-10-16 | Yes | N/A | 2019-10-21 | 2020-03-06 | 2020-03-06 |  |  | 2020-03-06 |  | Yes | Shovel Ready | 1116465.6 | 591539.4 |  | 1197284 | 80818.4 | 340211.5 | 52.98% | 689326.4 | 86927.7 | 776254.1 | -47181 | 1930363.4314 | 14 | [9 empty] | Pollock Pines | El Dorado | 0 | 0 | E.5015414.04 |  |  |  | 2020 | Q1 | 2019-08-26 | 2020-01-02 | 2020-03-13 |  | Y | EL DORADO ph 210119752 | 13 | EL DORADO COUNTY | Yes
35109737 |  | 2020 | 220 Mile Plan | CWSP-VOLTA 1102-LR 1648-PH2.2 |  | MAPP | 11274 | 0 | 11610 | 11610 | 2.1989 | 9642 | 1.8261 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 08W | SH | 2019-11-23 | 2019-11-08 | 2019-11-08 | 2019-11-08 |  |  | Yes | 2019-11-08 | 11/05: ADE workload- in progress11/01: EN submitted for 3rd ADE rvw10/29: ADE requesting full OCALC report - Report is a consolidation of information, vs individual breakout for specific items. - Req support/feedback from OCALC grp.10/23: ADE rtn 3rd corrections to contractor10/22: ADE returned - requested to progress10/16: ADE to finalize processing10/10: Routed per EN - [REDACTED] on vacation this week (push)10/01 - 10/08: Minor corrections - EN Target for routing by 10/04 - How to Proceed? - ADE requested elevations late in processing (new standards implementation).9/25: ADE 2nd Rvw corrections rtn to Contractor9/10: EN Submitted for 2nd Review - [PRELIM DWG ready]9/10: Corrections complete - System planner on vaca (pending review)--> [RCC Issue]9/03: On Target for mid to EOW correction submittal8/27: Finializing correction - on track8/21: 1st ADE rvw sent to contractor8/20: 1st ADE review scheduled for completed and send to CO8/06: ADE que'd for review, in review process of another 08W - Target date requested - [REDACTED]7/22: EN Submitted for 1st ADE Review7/16 <-- 7/9: on track for 7/18 | EN |  |  | Completed | COMPLETED | No |  | 0 | 0 |  | Yes | [5 empty] | Full |  |  | Full |  |  | CIF submitted 8/8/19. | Full |  | Yes |  |  | Shasta County Annual | 1980-01-01 | Y | [10 empty] | 1968 | 0.37273 | 9642 | 1.8261 | 2.1989 | 0 | 2.1989 | 0 | 2.1989 | 0 | 0 | 2.1989 |  | Keep | 2019-11-23 | Yes | N/A | 2019-11-15 | 2020-03-16 08:00 | 2020-03-16 08:00 |  |  | 2020-03-16 |  | Yes | Shovel Ready | 5216877.5 | 3789139.7 |  | 5442195 | 225317.5 | 1970151.7 | 72.63% | 3246725.8 | 0 | 3246725.8 | 0 | 1723226.3235 | 57 | [9 empty] | Shingletown | Shasta | 40.5069 | -121.8223 | E.5015533.02 |  |  |  | 2020 | Q1 | 2019-11-08 |  | 2020-02-09 |  | Y | VOLTA 110253130 | 107 | SHASTA COUNTY | Yes
35109738 |  | 2020 | 220 Mile Plan | CWSP-VOLTA 1102-LR 1648-PH2.3 |  | FICL | 9616 | 0 | 10959 | 10959 | 2.0756 | 10959 | 2.0756 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 08W | SH | 2019-12-19 | 2019-10-02 | 2019-10-03 | 2019-10-02 |  |  | Yes | 2019-10-02 | 7/9 - 8/13: on track for 8/288/20: BCF anticipates 8/22 for 1st ADE submittal8/27: Submitting today8/28: EEI Submitted for 1st ADE rvw9/03: On Target (potentially mid to EOW correction submittal)--> [RCC Issue]9/10: Pending ADE Assignment and review9/17: ADE assigned - [REDACTED] - EOD pushed/ADE resource availability9/17: ADE 1st Rvw corrections rtn to ContractorSecond Rvw - .... [PRELIM DWG ready]10/1: Will route when system planner routes for EDRS. Target 10/1-2 | EN |  |  | Completed | COMPLETED | No |  | 0 | 0 |  | Yes | [5 empty] | Full |  |  | Full |  |  | CIF submitted 8/28/19. Caltrans Permit. ERTC pushed due to land - 10/1 poles located in wetland may cause a delay if it cannot be redesigned. | Full |  | Yes |  |  | Shasta County Annual | 1980-01-01 | Y | [10 empty] | 0 | 0 | 10959 | 2.0756 | 2.0756 | 0 | 2.0756 | 0 | 2.0756 | 0 | 0 | 2.0756 |  | Keep | 2019-12-19 | Yes | N/A | 2020-01-06 | 2020-05-28 08:00 | 2020-05-28 |  |  | 2020-06-17 |  | Yes | Shovel Ready | 4484183.1 | 2260186.9 |  | 4773512 | 289328.9 | 2414195 | 50.4% | 2069988.1 | 0 | 2069988.1 | 0 | 1088948.5201 | 49 | [9 empty] | Shingletown | Shasta | 40.499 | -121.8389 | E.5015533.03 |  |  |  | 2020 | Q1 | 2019-10-02 | 2020-02-20 | 2020-03-31 |  | Y | VOLTA 110253130 | 107 | SHASTA COUNTY | Yes
35109739 |  | 2020 | 220 Mile Plan | CWSP-VOLTA 1102-LR 1648-PH2.4 |  | DOCC | 12487 | 0 | 12344 | 12344 | 2.3379 | 5807 | 1.0998 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 08W | SH | 2020-01-11 | 2019-09-20 | 2019-09-20 | 2019-09-20 |  |  | Yes | 2019-09-20 | 7/9: submitted for 1st review7/22: Pending ADE corrections, Target 7/267/30: Corrections Pending7/31: 1st ADE Review Completed, corrections in progress8/1: EN req the Job Story/scope of work including units of conductor to install to submit the CIF for this project 8/07: Response received and corrections being applied - EN followed up w/ 2nd submitted - PRELIM DWG (Done)8/15: ADE submitted for corrections - Vendor submittal 2nd ADE review scheduled for 8/238/27: Per EN - Submitting corrections8/30 EN submitted for 3rd ADE review9/01: Resent9/03: CO corrections target submittal by EOW (3rd)--> [RCC Issue] 9/27 EOD push9/9: EN routed for approval9/10: EN/ADE workthough Q&A9/17: Need update on ADE targets and EOD | EN |  |  | Completed | COMPLETED | No |  | 0 | 0 |  | Yes | [5 empty] | Full |  |  | Full |  |  | CIF submitted 8/7/19. | Full |  | Yes |  |  | Permit request sent 8/6/19 | 1980-01-01 | Y | [10 empty] | 6537 | 1.2381 | 5807 | 1.0998 | 2.3379 | 0 | 2.3379 | 0 | 2.3379 | 0 | 0 | 2.3379 |  | Keep | 2020-01-11 | Yes | N/A | 2019-10-19 | 2020-01-23 | 2020-01-23 |  |  | 2020-01-23 |  | Yes | Shovel Ready | 5522835.9 | 3564118.2 |  | 5748253 | 225417.1 | 2028774.2 | 64.53% | 3494061.7 | 0 | 3494061.7 | 0 | 1524509.4051 | 63 | [9 empty] | Shingletown | Shasta | 40.5126 | -121.822 | E.5015533.04 |  |  |  | 2020 | Q1 | 2019-09-20 |  | 2020-02-02 |  | Y | VOLTA 110253130 | 107 | SHASTA COUNTY | Yes
35110440 |  | 2020 | 220 Mile Plan | CWSP-VOLTA 1102-LR 1648-PH2.5 |  | DOCC | 14440 | 0 | 13964 | 13964 | 2.6447 | 13964 | 2.6447 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 08W | SH | 2020-01-05 | 2019-09-13 | 2019-09-25 | 2019-09-13 |  |  | Yes | 2019-09-13 | 7/9 - 8/06: on track for 8/208/20: Submitting Tomorrow8/21: EN submitted for 1st ADE rvw9/03: On Target for mid to EOW correction submittal--> [RCC Issue]9/10: In Review9/11: ADE assigned to [REDACTED] - 1st ADE Corrections sent to [REDACTED] - In Review | EN |  |  | Completed | COMPLETED | No |  | 0 | 0 |  | Yes | [5 empty] | Full |  |  | Full |  |  | CIF submitted 8/21/19. | Full |  | Yes |  |  | Shasta County Annual | 1980-01-01 | Y | [10 empty] | 0 | 0 | 13964 | 2.6447 | 2.6447 | 0 | 2.6447 | 0 | 2.6447 | 0 | 0 | 2.6447 |  | Keep | 2020-01-05 | Yes | N/A | 2020-02-01 | 2020-05-08 | 2020-05-08 08:00 |  |  | 2020-05-08 |  | Yes | Shovel Ready | 5259268 | 4361636.2 |  | 5859212 | 599944 | 3100448.6 | 82.93% | 2158819.4 | 0 | 2158819.4 | 0 | 1649200.7402 | 73 | [9 empty] | Shingletown | Shasta | 40.522 | -121.8311 | E.5015533.05 |  |  |  | 2020 | Q1 | 2019-09-13 | 2020-02-20 | 2020-03-31 |  | Y | VOLTA 110253130 | 107 | SHASTA COUNTY | Yes
35110441 |  | 2020 | 220 Mile Plan | CWSP-VOLTA 1102-LR 1648-PH2.6 |  | DOCC | 11600 | 0 | 11791 | 11791 | 2.2331 | 11791 | 2.2331 | 0 | 0 | 0 | 0 | -3.4451e-16 |  |  | NV | 08W | SH | 2019-12-20 | 2019-10-03 | 2019-10-03 | 2019-10-03 |  |  | Yes | 2019-10-03 | 7/9 - 8/06: on track for 8/9 8/09: EEI Submitted for 1st ADE Rvw 8/20: ADE verified as assigned 8/23: 1st ADE corrections rtn to contractor 8/30: Estimator in field for week; review in progress 9/03: CO corrections target submittal by EOW --> [RCC Issue] 9/10: Corrections complete - System planner on vaca (pending review) 9/11: EEI submitted for 2nd Rvw - adding some corrections 9/12: EEI submitted for 2nd Rvw - final 9/14: 2nd ADE corrections rtn to contractor (completed the second review for this job. Please make minor corrections, upload job to SAP and route for approval. Also, please verify that the issues regarding 119-125 ) 9/17: EN route for approval target 9/17 (today) 9/17: EN submitted for 3rd ADE rvw 10/1: EN Routing for approval | EN |  |  | Completed | COMPLETED | No |  | 0 | 0 |  | Yes | [5 empty] | Full |  |  | Full |  |  | CIF submitted 8/9/19. | Full |  | Yes |  |  | Shasta County Annual | 1980-01-01 | Y | [10 empty] | 0 | 0 | 11791 | 2.2331 | 2.2331 | 0 | 2.2331 | 0 | 2.2331 | 0 | -3.4451e-16 | 2.2331 |  | Keep | 2019-12-20 | Yes | COMP | 2020-02-01 | 2020-05-04 | 2020-05-04 |  |  | 2020-05-04 |  | Yes | Shovel Ready | 4221227 | 1210240.2 |  | 4651895 | 430668 | 3263519.7 | 28.67% | 418997.1 | 538710.2 | 957707.3 | 0 | 541944.5557 | 58 | [9 empty] | Shingletown | Shasta | 40.5274 | -121.8352 | E.5015533.06 |  |  |  | 2020 | Q1 | 2019-10-03 | 2020-02-17 | 2020-03-31 |  | Y | VOLTA 110253130 | 107 | SHASTA COUNTY | Yes
35110442 |  | 2020 | 220 Mile Plan | CWSP-VOLTA 1102-LR 1648-PH3.2 |  | FICL | 7345 | 0 | 7155 | 7155 | 1.3551 | 162 | 0.030682 | 0 | 0 | 0 | 0 | 1.7225e-16 |  |  | NV | 08W | SH | 2019-11-20 | 2019-08-19 | 2019-09-12 | 2019-08-19 |  |  | Yes | 2019-08-19 | (Moved into 2019)7/3 - 7/31: On track for 8/27/31: EEI submitted for 1st ADE Review[PRELIM DWG ready]8/19: In PEND - settlement errors and mapping errors as all other 08W jobs. AP10 will not clear etc.. [REDACTED] is aware.9/11: Pushing EOD to clear issue--> [RCC Issue] 9/27 EOD push | EEI |  |  | Completed | COMPLETED | No |  | 0 | 0 |  | Yes | [5 empty] | Full |  |  | Full |  |  | CIF Submitted 8/19/19 | Full |  | Yes |  |  | Permit requested 8/19/19 | 1980-01-01 | Y | [10 empty] | 6993 | 1.3244 | 162 | 0.030682 | 1.3551 | 0 | 1.3551 | 0 | 1.3551 | 0 | 1.7225e-16 | 1.3551 |  | Keep | 2019-11-20 | Yes | N/A | 2019-12-02 | 2019-12-26 | 2019-12-26 |  |  | 2020-05-28 |  | Yes | Shovel Ready | 4645014.2 | 4524122.4 |  | 4820085 | 175070.8 | 541829.3 | 97.39% | 4103184.9 | 0 | 4103184.9 | 0 | 3338555.7333 | 37 | [9 empty] | Shingletown | Shasta | 40.5122 | -121.8041 | E.5015704.02 |  |  |  | 2020 | Q1 | 2019-08-19 | 2020-01-02 | 2020-01-16 |  | Y | VOLTA 11021648 | 283 | SHASTA COUNTY | Yes
35110443 |  | 2020 | 220 Mile Plan | CWSP-VOLTA 1102-LR 1648-PH3.3 |  | FICL | 6545 | 0 | 6630 | 6630 | 1.2557 | 845 | 0.16004 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 08W | SH | 2019-12-23 | 2019-09-12 | 2019-09-10 | 2019-09-12 |  |  | Yes | 2019-09-12 | (Moved into 2019) 7/3 - 7/31: On track for 8/2 8/2: EEI submitted for 1st ADE Review [PRELIM DWG ready] 8/19: IN PEND - Volta PH 3.3 approved and into PEND. Same Settlement errors as the others and did not clear AP10 9/11: Pushing dates to clear issue | EEI |  |  | Completed | COMPLETED | No |  | 0 | 0 |  | Yes | [5 empty] | Full |  |  | Full |  |  | CIF submitted 8/21/19 | Full |  | Yes |  |  |  | 1980-01-01 | Y | [10 empty] | 5785 | 1.0956 | 845 | 0.16004 | 1.2557 | 0 | 1.2557 | 0 | 1.2557 | 0 | 0 | 1.2557 |  | Keep | 2019-12-23 | Yes | N/A | 2019-12-03 | 2020-01-30 | 2020-01-30 |  |  | 2020-06-08 |  | Yes | Shovel Ready | 4028438.4 | 3921309.7 |  | 4241038 | 212599.6 | 395169.5 | 97.34% | 3633268.9 | 0 | 3633268.9 | 0 | 3122852.9738 | 33 | [9 empty] | Shingletown | Shasta | 40.5043 | -121.814 | E.5015704.03 |  |  |  | 2020 | Q1 | 2019-09-12 |  | 2020-02-16 |  | Y | VOLTA 11021648 | 283 | SHASTA COUNTY | Yes
35110444 |  | 2020 | 220 Mile Plan | CWSP-VOLTA 1102-LR 1648-PH3.4 |  | FICL | 8204 | 0 | 7783 | 7783 | 1.4741 | 3634 | 0.68826 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 08W | SH | 2020-01-11 | 2019-09-12 | 2019-09-14 | 2019-09-12 |  |  | Yes | 2019-09-12 | (Moved into 2019)7/3 - 7/31: On track for 8/97/31: EEI submitted for 1st ADE Review8/2: ADE [REDACTED] assigned8/7: ADE [REDACTED] corrections returned to Contractor; EEI to review timeline to complete corrections8/21: 2nd submittal scheduled for this week, 8/23 latest8/21: EEI submitted OCALC ADE Rvw - 8/22: ADE in approval; once ConDWG & CMCS corrected - ok to concur this job. 9/04 - 9/11: Good to go - RCC issue [PRELIM DWG ready] | EEI |  |  | Completed | COMPLETED | No |  | 0 | 0 |  | Yes | [5 empty] | Full |  |  | Full |  |  | CIF submitted 7/11/19 | Full |  | Yes |  |  |  | 1980-01-01 | Y | [10 empty] | 4149 | 0.7858 | 3634 | 0.68826 | 1.4741 | 0 | 1.4741 | 0 | 1.4741 | 0 | 0 | 1.4741 |  | Keep | 2020-01-11 | Yes | N/A | 2019-10-05 | 2020-02-06 17:00 | 2020-02-06 08:00 |  |  | 2020-02-06 |  | Yes | Shovel Ready | 4369138.9 | 3336885.9 |  | 4551984 | 182845.1 | 1244102.9 | 76.37% | 3069940.6 | 55095.4 | 3125036 | 0 | 2263748.8824 | 42 | [9 empty] | Shingletown | Shasta | 40.5086 | -121.8083 | E.5015704.04 |  |  |  | 2020 | Q1 | 2019-09-12 |  | 2020-02-24 |  | Y | VOLTA 11021648 | 283 | SHASTA COUNTY | Yes
35110445 |  | 2020 | 220 Mile Plan | CWSP-VOLTA 1102-LR 1648-PH4.2 |  | DOCC | 10160 | 0 | 8668 | 8668 | 1.6417 | 1008 | 0.19091 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 08W | SH | 2019-11-20 | 2019-08-27 | 2019-09-21 | 2019-08-27 |  |  | Yes | 2019-08-27 | (Moved into 2019)7/3 - 7/31: On track for 8/168/6: EEI submitted for 1st ADE review - ADE [REDACTED]8/20: 1st ADE corrections rtn to contractor8/27: In PEND | EEI |  |  | Completed | COMPLETED | No |  | 0 | 0 |  | Yes | [5 empty] | Full |  |  | Full |  |  | CIF submitted 8/13/19 | Full |  | Yes |  |  | Shasta County Annual | 1980-01-01 | Y | [10 empty] | 7660 | 1.4508 | 1008 | 0.19091 | 1.6417 | 0 | 1.6417 | 0 | 1.6417 | 0 | 0 | 1.6417 |  | Keep | 2019-11-20 | Yes | N/A | 2019-10-16 08:00 | 2019-12-26 | 2019-12-26 |  |  | 2019-12-26 |  | Yes | Shovel Ready | 5440289.1 | 3805387.5 |  | 5440290 | 0.9 | 909658.3 | 69.94% | 4039029.7 | 491601.1 | 4530630.8 | -38488 | 2318002.5381 | 51 | [9 empty] | Shingletown | Shasta | 40.5264 | -121.747 | E.5015428.02 |  |  | 2020-182 | 2020 | Q1 | 2019-08-27 | 2020-01-02 | 2020-01-18 |  | Y | VOLTA 11029742 | 229 | SHASTA COUNTY | Yes
35110446 |  | 2020 | 220 Mile Plan | CWSP-VOLTA 1102-LR 1648-PH4.3 |  | FICL | 11030 | 0 | 11401 | 11401 | 2.1593 | 11401 | 2.1593 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 08W | SH | 2020-01-11 | 2019-08-27 | 2019-09-21 | 2019-08-27 |  |  | Yes | 2019-08-27 | (Moved into 2019) 7/3 - 8/06: On track for 8/16 8/16: EEI submitted for 1st ADE rvw 8/20: 1st Corrections rtn to contractor 8/27: In PEND | EEI |  |  | Completed | COMPLETED | No |  | 0 | 0 |  | Yes | [5 empty] | Full |  |  | Full |  |  | CIF submitted 8/21/19 | Full |  | Yes |  |  | Shasta County Annual | 1980-01-01 | Y | [10 empty] | 0 | 0 | 11401 | 2.1593 | 2.1593 | 0 | 2.1593 | 0 | 2.1593 | 0 | 0 | 2.1593 |  | Keep | 2020-01-11 | Yes | N/A | 2020-01-13 08:00 | 2020-02-18 | 2020-02-18 17:00 |  |  | 2020-07-01 |  | Yes | Shovel Ready | 4812157 | 1761178 |  | 4988877 | 176720 | 3081805.5 | 36.59% | 1730351.5 | 0 | 1730351.5 | -9524 | 815631.9481 | 56 | [9 empty] | Shingletown | Shasta | 40.5305 | -121.7454 | E.5015428.03 |  |  | 2020-183 | 2020 | Q1 | 2019-08-27 | 2020-01-13 | 2020-02-16 |  | Y | VOLTA 11029742 | 229 | SHASTA COUNTY | Yes
35110447 |  | 2020 | 220 Mile Plan | CWSP-VOLTA 1102-LR 1648-PH4.4 |  | FICL | 6000 | 0 | 6198 | 6198 | 1.1739 | 6198 | 1.1739 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 08W | SH | 2020-01-11 | 2019-09-18 | 2019-09-21 | 2019-09-18 |  |  | Yes | 2019-09-18 | (Moved into 2019)7/3 - 8/06: On track for 8/168/07: EEI Submitted for 1st ADE review - Request for [REDACTED] to assign ADE8/20: ADE reassigned to [REDACTED]8/25: 1st ADE corrections rtn to contractor8/26 EEI Submitted for 2nd ADE rvw8/28: 2nd ADE corrections rtn to contractor - Waiting on PM stamp to route for approval--> [RCC Issue] 9/27 EOD push9/4 - 9/11: EEI cleared - ok to route - PRELIM DWG (Done)9/18 - RCC issue corrected | EEI |  |  | Completed | COMPLETED | No |  | 0 | 0 |  | Yes | [5 empty] | Full |  |  | Full |  |  | CIF submitted 9/5/19 | Full |  | Yes |  |  | Shasta County Annual | 1980-01-01 | Y | [10 empty] | 0 | 0 | 6198 | 1.1739 | 1.1739 | 0 | 1.1739 | 0 | 1.1739 | 0 | 0 | 1.1739 |  | Keep | 2020-01-11 | Yes | N/A | 2020-01-27 | 2020-04-10 17:00 | 2020-04-10 08:00 |  |  | 2020-07-01 |  | Yes | Shovel Ready | 4129565.6 | 4115199.9 |  | 4129566 | 0.4 | 2166758.2 | 99.65% | 1962807.4 | 0 | 1962807.4 | 0 | 3505688.2014 | 40 | [9 empty] | Shingletown | Shasta | 40.5334 | -121.7392 | E.5015428.04 |  |  | 2020-184 | 2020 | Q1 | 2019-09-18 | 2020-01-27 | 2020-02-21 |  | Y | VOLTA 11029742 | 229 | SHASTA COUNTY | Yes
35110448 |  | 2020 | 220 Mile Plan | CWSP-VOLTA 1102-LR 1648-PH4.5 |  | DOCC | 10000 | 0 | 10503 | 10503 | 1.9892 | 10503 | 1.9892 | 0 | 0 | 0 | 0 | 0 | 10301 | 1.9509 | NV | 08W | SH | 2020-03-13 08:00 | 2019-09-16 | 2019-09-23 | 2019-09-16 |  |  | Yes | 2019-09-16 | (Moved into 2019)7/3 - 8/06: On track for 8/168/08 -8/14: EEI Submitted for 1st ADE review - Request for [REDACTED] to assign ADEADE assigned8/23: EEI submitted for 1st ADE rvw (1-4 of 4)8/23: 1st corrections rtn to contractor - email 1-4 of 28/28: EEI submitted for 2nd ADE rvw (1-2 of 2)8/29: 2nd Rvw return to contractor - close enough now that when you make the corrections, please P.E. stamp the OCalc's, attach to SAP, and EDRS9/04: Routing Issues (EES?) - EEI has reached out to EES team for resolution support - PRELIM DWG (Done)--> [RCC Issue] 9/27 EOD push9/11: 3rd review return to contractor - very minor corrections. Once corrected, please go ahead and start the approval process through EES. | EEI |  |  | Completed | COMPLETED | No |  | 0 | 0 |  | Yes | [5 empty] | Full |  |  | Full |  |  | CIF submitted 9/5/19 | Full |  | Yes |  |  | Shasta County Annual | 1980-01-01 | Y | [10 empty] | 0 | 0 | 10503 | 1.9892 | 1.9892 | 0 | 1.9892 | 0 | 1.9892 | 0 | 0 | 1.9892 |  | Keep | 2020-03-13 08:00 | Yes | N/A | 2020-02-03 08:00 | 2020-05-28 | 2020-05-28 |  |  | 2020-05-28 |  | Yes | Shovel Ready | 5551376.3 | 6184406.7 |  | 6475096 | 923719.7 | 3013727.3 | 111.4% | 2017962.8 | 519686.2 | 2537649 | 0 | 3108984.8021 | 85 | [9 empty] | Shingletown | Shasta | 40.5326 | -121.7349 | E.5015428.05 |  |  | 2020-185 | 2020 | Q1 | 2019-09-16 | 2020-02-14 | 2020-03-28 |  | Y | VOLTA 11029742 | 229 | SHASTA COUNTY | Yes
35110712 |  | 2020 |  | BUCOCAMPT 6359 OAK WAY PARADISE |  | CLSD |  | 0 | 2404 | 2404 | 0.4553 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 95F |  |  |  | 2019-07-31 | [47 empty] | 2404 | 0.4553 | 0 | 0 | 0.4553 | 0 | 0.12841 | 0 | 0.12841 | 0 | 0.32689 | 0.12841 |  |  |  |  | N/A | [5 empty] | 2019-09-07 | [25 empty] | Paradise | Butte | 39.7776 | -121.6031 |  |  |  |  | 2019 | [5 empty] | Y |  |  | BUTTE COUNTY | Yes
35110725 |  | 2020 |  | BUCOCAMPT 11521 AUREOLE WAY OROVILLE* |  | FICL |  | 0 | 281 | 281 | 0.05322 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 95F | [51 empty] | 281 | 0.05322 | 1109 | 0.21004 | 0.26326 | -0.21004 | 0.26117 | 0 | 0.26117 | 0 | 0.0020833 | 0.26117 |  |  |  |  | N/A | [5 empty] | 2019-10-18 | [25 empty] | Oroville | Butte | 39.7256 | -121.5108 |  |  |  |  | 2019 | [8 empty] | BUTTE COUNTY | Yes
35110795 |  | 2020 |  | BUCOCAMPT 5150 CIRCLE LN PARADISE*ILB |  | DOCC |  | 0 | 936 | 936 | 0.17727 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 95F | [51 empty] | 936 | 0.17727 | 0 | 0 | 0.17727 | 0 | 0.16742 | 0 | 0.16742 | 0 | 0.0098485 | 0.16742 |  |  |  |  | N/A | [5 empty] | 2019-09-30 | [25 empty] | Paradise | Butte | 39.7378 | 121.5959 |  |  |  |  | 2019 | [8 empty] | BUTTE COUNTY | Yes
35110799 |  | 2020 |  | BUCOCAMPT 1643 ALEXIS LN PARADISE |  | CLSD |  | 0 | 222 | 222 | 0.042045 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 95F |  |  |  | 2019-07-31 | [47 empty] | 222 | 0.042045 | 0 | 0 | 0.042045 | 0 | 0.0094697 | 0 | 0.0094697 | 0 | 0.032576 | 0.0094697 |  |  |  |  | N/A | [5 empty] | 2019-10-16 | [27 empty] | 39.757 | -121.582 |  |  |  |  | 2019 | [8 empty] | BUTTE COUNTY | Yes
35110843 |  | 2020 |  | BUCOCAMPT 1068 MAPLE PARK DR PARADISE |  | DOCC |  | 0 | 377 | 377 | 0.071402 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 95F | [51 empty] | 377 | 0.071402 | 792 | 0.15 | 0.2214 | -0.15 | 0.21534 | 0 | 0.21534 | 0 | 0.0060606 | 0.21534 |  |  |  |  | N/A | [5 empty] | 2019-08-10 | [27 empty] | 39.7609 | -121.6094 |  |  |  |  | 2019 | [8 empty] | BUTTE COUNTY | Yes
35110849 |  | 2020 |  | BUCOCAMPT 5200 HEATHROW RD PARADISE |  | CLSD |  | 0 | 341 | 341 | 0.064583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 95F | [51 empty] | 341 | 0.064583 | 0 | 0 | 0.064583 | 0 | 0.048485 | 0 | 0.048485 | 0 | 0.016098 | 0.048485 |  |  |  |  | N/A | [5 empty] | 2019-08-31 |  |  |  | 0 | 69887.5 |  | 30515.83 | 30515.83 | -69887.5 |  | 69887.5 | 0 | 69887.5 | 0 | 1082129.0323 | [10 empty] | Paradise | Butte | 39.7377 | -121.5972 |  |  |  |  | 2019 | [5 empty] | Y |  |  | BUTTE COUNTY | Yes
35110916 |  | 2020 |  | BUCOCAMPT 12994 MOHAWK WAY OROVILLE |  | DOCC |  | 0 | 503 | 503 | 0.095265 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 95F |  |  |  | 2019-07-31 | [47 empty] | 503 | 0.095265 | 0 | 0 | 0.095265 | 0 | 0.10076 | 0 | 0.10076 | 0 | -0.0054924 | 0.10076 |  |  |  |  | N/A | [5 empty] | 2019-10-07 |  |  |  | 0 | 79508.8 |  | 67284.57 | 67284.57 | -79508.8 |  | 79508.8 | 0 | 79508.8 | 0 | 834605.2962 | [12 empty] | 39.7735 | -121.4995 |  |  |  |  | 2019 | [5 empty] | Y |  |  | BUTTE COUNTY | Yes
35110919 |  | 2020 |  | BUCOCAMPT 1290 LUCKY LADY LN PARADISE |  | DOCC |  | 0 | 480 | 480 | 0.090909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 95F |  |  |  | 2019-07-31 | [47 empty] | 480 | 0.090909 | 0 | 0 | 0.090909 | 0 | 0.054924 | 0 | 0.054924 | 0 | 0.035985 | 0.054924 |  |  |  |  | N/A | [5 empty] | 2019-09-12 | [27 empty] | 39.7749 | -121.5995 |  |  |  |  | 2019 | [8 empty] | BUTTE COUNTY | Yes
35111038 |  |  |  | +STS-COND_IDLE_REMV-11010 FUENTEDS R |  | DOCC |  | 0 | 4875 | 4875 | 0.9233 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2AF | [51 empty] | 4875 | 0.9233 | 0 | 0 | 0.9233 | 0 | 0.9233 | 0 | 0.9233 | 0 | 0 | 0.9233 |  |  |  |  | N/A | [5 empty] | 2020-01-06 | [27 empty] | 35.4927 | -120.7772 | [13 empty] | San Luis Obispo County | Yes
35111096 |  | 2020 |  | BUCOCAMPT 1398 FOREST SERVICE RD PARADIS |  | CLSD |  | 0 | 136 | 136 | 0.025758 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 95F | [51 empty] | 136 | 0.025758 | 792 | 0.15 | 0.17576 | -0.15 | 0.18182 | 0 | 0.18182 | 0 | -0.0060606 | 0.18182 |  |  |  |  | N/A | [5 empty] | 2019-08-27 | [27 empty] | 39.7849 | -121.5916 |  |  |  |  | 2019 | [8 empty] | BUTTE COUNTY | Yes
35111500 |  |  |  | CWSP-RECON UPPER LAKE 01 HUNTERS PT RD |  | CLSD | 3700 | 0 | 1850 | 1850 | 0.35038 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2019-07-03 | 2019-07-03 |  | 2019-07-03 |  |  | Yes | 2019-07-03 | [17 empty] | Full |  |  | Full |  |  | 8/27/19 - Veg Scope submitted 8/29/19 | Full |  | Yes |  |  |  | 1980-01-01 | Y | [10 empty] | 1850 | 0.35038 | 0 | 0 | 0.35038 | 0 | 0.35038 | 0 | 0.35038 | 0 | 0 | 0.35038 |  |  |  |  | N/A | [5 empty] | 2019-12-16 | [25 empty] | Lakeport | Lake | 0 | 0 | 35111500 |  |  |  | 2019 | Q1 |  |  |  |  | Y | UPPER LAKE 11016663 | 871 | LAKE COUNTY | Yes
35112076 |  | 2020 | 220 Mile Plan | OCGC FULTON 1107-OH TO UG MARK W SPG |  | MAPP | 7980 | 3657 | 7969 | 11626 | 2.2019 | 10736 | 2.0333 | 0 | 0 | 0 | 0 | 0 |  |  | SO | 08W | SH | 2019-09-30 | 2019-09-30 |  | 2019-09-30 |  |  | Yes | 2019-09-30 |  | SANTA ROSA |  |  |  | 100 | Yes |  |  |  |  | Yes | [5 empty] | Full |  |  | Full |  |  | CIF submitted Week of 8/12. Veg Scope Needed. CDFW requirements | Full |  | Yes |  |  | 10/1/2019 - working on permit revisions | 1980-01-01 | Y | [10 empty] | 890 | 0.16856 | 10736 | 2.0333 | 2.2019 | 3.4451e-16 | 2.2019 | 0 | 2.2019 | 0 | -3.4451e-16 | 2.2019 |  | Keep |  | Yes | N/A | [5 empty] | 2020-04-06 |  | Yes | Shovel Ready | 5749999.7 | 4164946.9 |  | 5750000 | 0.3 | 4249799.2 | 72.43% | 1497548.9 | 2651.6 | 1500200.5 | 0 | 1891529.2992 | 46 |  | Underground | [7 empty] | Santa Rosa | Sonoma | 0 | 0 | E.5024097.01 |  |  |  | 2020 | Q1 | 2019-09-27 | 2019-11-24 | 2020-03-23 |  | Y | FULTON 1107214 | 178 | SONOMA COUNTY | Yes
35112425 |  |  |  | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 |  | CONS | 6744 | 0 | 6871 | 6871 | 1.3013 | 6871 | 1.3013 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | SH | 2020-03-10 | 2019-10-23 | 2019-10-23 | 2019-10-23 |  |  | Yes | 2019-10-23 | (Moved into 2019) 7/10 - 8/14: on with 8/16 submittal 8/17: EEI submitted for 1st ADE rvw 9/04: ADE TBD --> [RCC Issue] 9/11 - 9/18: In Review; Change Order being submitted for 'composite change' *Job updated to composit poles 9/13: 1st ADE rvw rtn to contractor 9/23: EEI Submitted for 2nd ADE rvw 10/02: In Review 10/03 ADE 2nd rvw corrections rtn to contractor; submit for approval via EES, verify the appropriate tasks and dependencies are activated in the job 10/09: Routed on 10/08 - PGE to close for EOD target 10/11: ADE requested corrections to comments - EEI completed 10/15: Additional corrections provided to EEI in final review - updated dwg uploaded. 10/23: IN PEND | EEI |  |  | Completed | COMPLETED | No |  | 0 | 0 |  | Yes | [5 empty] | Full |  |  | Full |  |  | Submitted to forest service week of 12/10 | Full |  | Yes |  |  | No permit needed | 1980-01-01 | Y |  |  |  | Complete | [6 empty] | 0 | 0 | 6871 | 1.3013 | 1.3013 | 0 | 1.3013 | 0 | 1.3013 | 0 | 0 | 1.3013 |  | Keep | 2020-03-10 | Yes | N/A | 2020-05-04 | 2020-07-13 | 2021-01-15 17:00 |  |  |  |  | Yes | Shovel Ready | 2963552.3 | 4246805.9 |  | 5238478 | 2274925.7 | 2840035.5 | 143.3% | 58059.4 | 65457.4 | 123516.8 | 0 | 3263445.6632 | 34 | [9 empty] | Pollock Pines | El Dorado | 38.7883 | -120.6157 | E.5015420.02 |  |  |  | 2020 | Q2 | 2019-10-23 | 2020-03-16 | 2020-06-20 |  | Y | EL DORADO PH 2101CB | 76 | EL DORADO COUNTY | Yes
35112426 |  | 2020 | 220 Mile Plan | CWSP - EL DORADO 2101 - OCBZONE - PH 1.3 |  | MAPP | 9368 | 0 | 9077 | 9077 | 1.7191 | 39 | 0.0073864 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | SH | 2019-09-09 | 2019-09-09 | 2019-09-21 | 2019-09-09 |  |  | Yes | 2019-09-09 | (Moved into 2019) 7/10 - 8/14: on with 8/16 submittal 8/16: EEI submitted for 1st ADE rvw 9/04: In Review 9/11: IN PEND | EEI |  |  | Completed | COMPLETED | No |  | 0 | 0 |  | Yes | [5 empty] | Full |  |  | Full |  |  | PERTC Out in October, Partial Release. Forest service review in process starting 11/27 | Full |  | Yes |  |  | Drawings submitted 9/11/19 | 1980-01-01 | Y | [10 empty] | 9038 | 1.7117 | 39 | 0.0073864 | 1.7191 | -2.1639e-15 | 1.7191 | 0 | 1.7191 | 0 | 2.067e-15 | 1.7191 |  | Keep |  | Yes | N/A | [5 empty] | 2019-12-21 |  | Yes | Shovel Ready | 4309820.4 | 3678594.5 | -259218 | 3754403 | -555417.4 | 372007.9 | 85.35% | 3937812.5 | 0 | 3937812.5 | -259218 | 2139801.582 | 47 | [6 empty] | No SCADA |  |  | Pollock Pines | El Dorado | 38.7883 | -120.6157 | E.5015420.03 |  |  |  | 2020 | Q1 | 2019-09-09 | 2020-01-02 | 2020-01-17 |  | Y | EL DORADO PH 2101CB | 76 | EL DORADO COUNTY | Yes
35112427 |  | 2020 | 220 Mile Plan | CWSP - EL DORADO 2101 - OCBZONE - PH 1.4 |  | CLSD | 5221 | 0 | 5069 | 5069 | 0.96004 | 4692 | 0.88864 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | SH | 2019-11-26 | 2019-11-13 | 2019-11-13 | 2019-11-13 |  |  | Yes | 2019-11-13 | (Moved into 2019) 7/10 - 8/14: on with 8/16 submittal8/13: EEI submitted for 1st ADE rvw8/28: ADE Assigned [REDACTED]9/04: In Review9/04: ADE returned review - need more information - Contractor working with ADE on new information standards being requested. (Method to support req under review -OCALC cannot support request). Request will impact multiple projects.--> [RCC Issue]9/18: Completing corrections - target date for submittal to be submitted by EEI9/25: Corrections complete and submitted -Confirm statusx/xx: [REDACTED] requested class update to all poles/ all passing10/01: EEI Submitted for 2nd ADE Review 10/09: Review in process - [REDACTED] to advise on status for completion date (SAP shows construction DEC 2020)10/16: Rvw target EOW - per [REDACTED]10/17: ADE rtn 2nd corrections to contractor10/29 <-- 10/23: EEI - submitting change order; poles converting to composite for inaccessibility purposes. EEI to update on new submittal target.10/31: EEI Submitted for 3rd rvw11/05: ADE rtn 3rd corrections to contractor - correct and route for approval11/07: Flagged Pole change out11/13: On Track for 11/15 | EEI |  |  | Completed | COMPLETED | No |  | 0 | 0 |  | Yes | [5 empty] | Full |  |  | Full |  |  | ERCT Call Complete | Full |  | Yes |  |  |  | 1980-01-01 | Y | [10 empty] | 377 | 0.071402 | 4692 | 0.88864 | 0.96004 | 0 | 0.96004 | 0 | 0.96004 | 0 | 0 | 0.96004 |  | Keep | 2019-11-26 | Yes | N/A | 2020-01-02 | 2020-02-12 | 2020-02-12 |  |  | 2020-02-12 |  | Yes | Shovel Ready |  |  | -231631 | [9 empty] | 27 | [6 empty] | No SCADA |  |  | Pollock Pines | El Dorado | 38.7883 | -120.6157 | E.5015420.04 |  |  |  | 2020 | Q1 | 2019-11-13 | 2019-12-18 | 2020-01-31 |  | Y | EL DORADO PH 2101CB | 76 | EL DORADO COUNTY | Yes
35112428 |  | 2020 | 220 Mile Plan | CWSP - EL DORADO 2101 - OCBZONE - PH 1.5 |  | FICL | 8571 | 0 | 8571 | 8571 | 1.6233 | 8571 | 1.6233 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | SH | 2019-12-03 | 2019-09-28 | 2019-09-28 | 2019-09-28 |  |  | Yes | 2019-09-28 | (Moved into 2019) 7/10 - 8/14: on with 8/16 submittal 8/16: EEI submitted for 1st ADE rvw 9/04: ADE TBD 9/06: ADE review returned to contractor --> [RCC Issue] 9/11: In Review 9/17: ADE approved, Ocalcs being stamped - scheduled to route by EOW 9/25: Check on rerouting for approval - RCC issues resolved | EEI |  |  | Completed | COMPLETED | No |  | 0 | 0 |  | Yes | [5 empty] | Full |  |  | Full |  |  | ERTC Call Complete | Full |  | Yes |  |  | Drawings submitted 10/1/19 | 1980-01-01 | Y | [10 empty] | 0 | 0 | 8571 | 1.6233 | 1.6233 | 0 | 1.6233 | 0 | 1.6233 | 0 | 0 | 1.6233 |  | Keep | 2019-12-03 | Yes | N/A | 2019-12-18 | 2020-02-27 | 2020-02-27 |  |  | 2020-02-27 |  | Yes | Shovel Ready | 2756022.3 | 2060687.6 | -340669 | 3809898 | 1053875.7 | 2460748.9 | 74.77% | 295273.4 | 0 | 295273.4 | -340669 | 1269447.034 | 43 | [6 empty] | No SCADA |  |  | Pollock Pines | El Dorado | 38.7883 | -120.6157 | E.5015420.05 |  |  |  | 2020 | Q1 | 2019-09-28 | 2020-01-06 | 2020-02-13 |  | Y | EL DORADO PH 2101CB | 76 | EL DORADO COUNTY | Yes
35112431 |  | 2020 | 220 Mile Plan | CWSP - EL DORADO 2102 - LR19562 - PH 1.1 |  | FICL | 8057 | 0 | 8118 | 8118 | 1.5375 | 8118 | 1.5375 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | SH | 2020-07-24 | 2020-07-24 | 2020-07-31 | 2020-07-24 |  |  | Yes | 2020-07-01 | 7/3: QUES to review to provide review on 1st ADE Submital7/16 - 9/11: On track for 9/30; Note: EOD Nov--> [RCC Issue]9/17: Hold at 9/30 - Potential 1 week push - Training/New Hire ramp up impact - tbd9/25: Move to 10/8 - Composite Pole conversions10/02: On track for 10/08; RISK of delay - Resource impact (down to 1 PE for stamping)10/09: QUES submitted for 1st ADE Rvw10/16: ADE to be assigned10/21: ADE assigned [REDACTED] - Push 2wk - ADE 1st rvw duration10/29: ADE rtn 1st corrections to contractor10/30: Power outage impacts - EEI to follow up with status UD/confirm target date(s); Stamped OCALC for loc92 uploaded11/06: QUES - still working through power issues; Est finalizing11/13: QUES submitted for 2nd ADE rvw11/16: ADE return 2nd corrections to contractor11/25: QUES submitted for 3rd ADE rvw111/27: ADE rtn 3rd corrections to contractor11/27:QUES submitted fro 4th ADE rvw12/02: ADE apprv'd 12/04: Concur rtn - Correction (Txt size & DWG length not match OCalc and Fld Note)12/11: Push to meet EOW completion | QUES |  |  | Completed | COMPLETED | No | Obsolete (CONS+) | 0 | 0 |  | Yes | [5 empty] | Full |  |  | Full |  |  | ERTC Call 1/7/2020 | Full |  | Yes | 2021-03-01 |  | 2-12-2020. 2019 annual previously uploaded. Task should be reset until 2020 permit obtained. | 2020-08-14 | Y | 2020-06-16 |  |  | 90% complete as of 7/28 | [6 empty] | 0 | 0 | 8117 | 1.5373 | 1.5373 | 0.00018939 | 1.5373 | 0 | 1.5373 | 0 | 0 | 1.5373 |  | Keep | 2020-03-26 | Yes | N/A | 2020-06-05 08:00 | 2020-10-02 | 2020-10-02 |  |  | 2020-10-02 |  | Yes | Shovel Ready | 3012691.7 | 4213443.2 |  | 4166416 | 1153724.3 | 3009251.8 | 139.8% | 3439.9 | 0 | 3439.9 | 0 | 2740450.8618 | 41 | [9 empty] | Pollock Pines | El Dorado | 0 | 0 | E.5015687.02 |  |  |  | 2020 | Q3 | 2019-12-12 | 2020-04-21 | 2020-05-27 |  | Y | EL DORADO PH 210219562 | 52 | EL DORADO COUNTY | Yes
35112432 |  | 2020 | 220 Mile Plan | CWSP - EL DORADO 2102 - LR19562 - PH 1.2 |  | DOCC | 12968 | 0 | 11193 | 11193 | 2.1199 | 11193 | 2.1199 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | SH | 2020-07-21 | 2020-07-21 | 2020-07-31 | 2020-07-21 | 2019-10-15 | 2019-10-15 | Yes | 2020-07-21 | 07/29: 1] [REDACTED] lead with AT&T, has a call setup tomorrow to discuss; 2] project has been revised and now need a 95' class H3 pole. Can you check on availability 07/22: PEND: Last communication was Vendor/[REDACTED] look into AT&T solution --> Joint Pole is going to vette issue with AT&T07/15: On Track07/14: EST routed for approval07/10: Issue flagged [redesign] - an AT&T line that will be too close in proximity to our 21kv line as it crosses a canyon once the new conductor is installed; calc'd location 87 for 55' pole due to construction determining clearance to phone was inadequate. need a 55'-H3 and a 20M anchor instead of a 45' pole and 15M anchor07/08 - 07/01: redesign - EOD (7/24) Original redesign changes applied and completed; Additional changes being requested.6/26/20: Into ESTS [REDACTED] - estimate returned to ESTS status and new version created to make changes per planning******7/3: QUES to review to provide review on 1st ADE Submital7/16 - 8/07: On track for 8/318/16-8/21: Q&A - Pole Spans/Guying8/21: Laptop hardware issues/loss - not enough RAM & Display drivers - sending in for upgrades - QUES looking into alternative work-arounds9/04: Additional fielding required - reevaluate information from initial fielding9/11: Target submittal for 9/139/18: Refielding completed and additional photos required to complete Est.9/24: QUES submitted for 1st ADE rvw10/02: In Review - rvw dates set at 2wk mark from submittal10/08: ADE returned 1st corrections to contractor - Estimator getting to a stopping point on another project and will implement corrections 10/09: QUES checking on schedule impact10/15: QUES submitted for 2nd ADE rvw10/23: ADE rtn 2nd corrections to contractor10/30: QUES submitted for 3rd ADE rvw10/31: ADE returned corrections to contractor 1] Ensure all attachments are uploaded and most current 2] OK to route for approval11/06: FAA error issues being addressed11/12: Push 1 wk - Routed for approval - Rejected for final correction | QUES |  |  | 2020- M7 [RRD-2020_Redesign] | COMPLETED | No | Obsolete (CONS+) | 0 | 0 |  | yes | [5 empty] | Full |  |  | Full |  |  | ERTC Call 1/7/2020 | Full |  | Yes | 2021-03-01 |  | 2-12-2020. 2019 annual previously uploaded. Task should be reset until 2020 permit obtained. | 2020-06-26 | Y | 2020-04-19 |  |  | Started | [6 empty] | 0 | 0 | 13572 | 2.5705 | 2.5705 | -0.45057 | 2.5053 | 0 | 2.5053 | 0 | 0.065152 | 2.5053 |  | Keep | 2020-03-26 | Yes | N/A | 2020-05-08 08:00 | 2020-11-18 | 2020-11-18 |  |  | 2020-11-18 |  | Yes | Shovel Ready | 3480529.7 | 5689560.8 |  | 5345911 | 1865381.3 | 3364806.2 | 163.5% | 14247 | 101476.5 | 115723.5 | 0 | 2683898.9568 | 65 | [9 empty] | Pollock Pines | El Dorado | 0 | 0 | E.5015687.03 |  |  |  | 2020 | Q2 | 2019-11-13 | 2020-04-27 | 2020-07-02 |  | Y | EL DORADO PH 210219562 | 52 | EL DORADO COUNTY | Yes
35112433 |  | 2020 | 220 Mile Plan | CWSP - EL DORADO 2102 - LR19562 - PH 1.3 |  | DOCC | 10344 | 0 | 10560 | 10560 | 2 | 10560 | 2 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | SH | 2020-03-26 | 2019-10-11 | 2019-10-11 | 2019-10-11 |  |  | Yes | 2019-10-11 | 7/3: QUES to review to provide review on 1st ADE Submital7/16 - 8/21: On track for 8/319/04: Push to 9/9 - Reprioritized to resolve corrections, resource shift9/04: QUES submitted for 1st ADE rvw--> [RCC Issue]9/11 - 9/25: ADE to be assigned9/26: ADE assigned to [REDACTED]9/30: ADE 1st corrections rtn to contractor10/09: On tailend of revisions - stamping | QUES |  |  | Completed | COMPLETED | No |  | 0 | 0 |  | Yes | [5 empty] | Full |  |  | Full |  |  | ERTC Call 1/7/2020 | Full |  | Yes |  |  | 2-12-2020. 2019 annual previously uploaded. Task should be reset until 2020 permit obtained. | 1980-01-01 | Y | [10 empty] | 0 | 0 | 10560 | 2 | 2 | 0 | 1.9968 | 0 | 1.9968 | 0 | 0.0032197 | 1.9968 |  | Keep | 2020-03-26 | Yes | N/A | 2020-03-27 | 2020-05-01 | 2020-05-01 |  |  | 2020-06-11 |  | Yes | Shovel Ready | 2867736.1 | 3566793.2 |  | 4151673 | 1283936.9 | 2856134.8 | 124.4% | 11601.3 | 0 | 11601.3 | 0 | 1783396.6 | 52 | [9 empty] | Pollock Pines | El Dorado | 0 | 0 | E.5015687.04 |  |  |  | 2020 | Q1 | 2019-10-11 | 2020-04-27 | 2020-06-09 |  | Y | EL DORADO PH 210219562 | 52 | EL DORADO COUNTY | Yes
35112434 |  | 2020 | 220 Mile Plan | CWSP - EL DORADO 2102 - LR19562 - PH 1.4 |  | DOCC | 7971 | 0 | 8078 | 8078 | 1.5299 | 8078 | 1.5299 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | SH | 2020-07-24 | 2020-07-24 | 2020-07-31 | 2020-07-24 | 2020-01-14 | 2020-01-14 | Yes | 2020-07-28 | 07/31: PMgr noted Redesign completed; moved back to CONS07/29 - 07/22: Pending response from Summit; anticipate rtn feedback by EOW; EOD set 8/707/16: errors in design efforts for theses re-design tasks. Errors primarily effect phases 1.4 and 1.5 (see [REDACTED] email)07/15: QUES provided DWG/COST PDF07/15: Version 2 created; User Status change (EES - [REDACTED]); [REDACTED] to follow up with reasons for Status changes.07/13: Changes Completed; uploaded to SAP; sent over to Summit - 07/08: On Track07/01: Internal Ocalc'd poles not in EES; EST unable to put into EES - seeking direction on how to apply - Construction redline? apprx 42 Poles/15 need material - EOD soft target (7/24)6/22 - ??: [Redesign] Wood Pole Conversion*****04/10: INTO PEND04/03: ADE rtn minor corrections - EST to apply and route04/02: QUES submitted for 4th ADE rvw - PMgr advised walkdown not required04/01: EST Status (4/4) - Waiting for JO response (2wk)03/18: Waiting on GC rvw03/11: Waiting on Veg & Land - On Track w/ some RISK03/10: ADE rtn 3rd corrections to CO - route for approval02/28: QUES submitted for 3rd ADE rvw1/29: Push - Scope change impact/Stamping 6wk1/22: Scope change initiated by the ADE - section of 2 wire conductor that is being changed to 3 wire, agreed upon by engineer. Extensive - ADE is asking to do things PG&E doesn't normally do Calls and emails into [REDACTED] to help address.01/22: ADE rtn corrections to CO02/05: Redesign approved, finalizing stamping1/16: Per ADE: To proceed with 3rd Rvw; EST - 1) All comments addressed below in red, 2) Both load cases (GO95 & HFTD) need to be shown with worse case used in OCalcs, 3) All OCalcs quality checked for heights and span lengths, as well as PE Stamped (not rubber stamped), 4) All corrected files uploaded to the folder, For 3rd ADE Review01/16: Paused for Priority alignment - OK to proceed01/14: EST/ADE coordinating on corrections01/09: ADE rejected 2nd submittal (not all corrections applied)12/19: QUES submitted for 2nd ADE rvw (2) - Clarifications12/18: QUES will confirm DWGs sent12/17: ADE rtn 2nd corrections to contractor12/16: QUES submitted for 2nd ADE review - [PRELIM DWGs ready]12/11 <-- 12/04: Ontrack for 12/2011/27: ADE redesign (pole locations/easements/landrights) and OCalc 85% - to review implementation of standard11-20 <-- 11/07: Push - 'new' ADE, qty of fixes11/06: On Track fr 2nd submittal11/05: ADE returned 1st corrections to contractor10/24: Estimator provided link for info10/21: ADE assigned [REDACTED] - Push 2wk - ADE 1st rvw duration10/16: QUES submitted for 1st ADE rvw10/09: In stamping, anticipate EOW or 10/1410/02: On track for 10/08; RISK of delay due to 1 PE to stamp (covering tapline, pole, 08W)9/25: 1st submittal push to 10/8 - Composite pole conversion--> [RCC Issue]7/16 -9/18: On track for 9/30; Note: EOD Nov7/3: QUES to review to provide review on 1st ADE Submital | QUES |  |  | 2020- M8 [RRD-2020_Redesign] | COMPLETED | No | Obsolete (CONS+) | 0 | 0 |  | yes | [5 empty] | Full |  |  | Full |  |  | CIF Submitted 12/18/19 | Full |  | Yes | 2021-03-01 |  | Drawings submitted 12/18/19 | 2020-08-19 | Y | 2020-06-25 | [9 empty] | 0 | 0 | 8078 | 1.5299 | 1.5299 | 0 | 1.5008 | 0 | 1.5008 | 0 | 0.029167 | 1.5008 |  | Keep | 2020-05-20 | Yes | N/A | 2020-07-27 08:00 | 2020-10-02 | 2020-10-02 |  |  | 2020-10-02 |  | Yes | Shovel Ready | 2743160 | 4906092.7 |  | 3756886 | 1013726 | 2739607.9 | 178.8% | 3552.1 | 0 | 3552.1 | 0 | 3206755.3177 | 40 | [9 empty] | Pollock Pines | El Dorado | 0 | 0 | E.5015687.05 |  |  |  | 2020 | Q3 | 2020-03-31 | 2020-05-11 | 2020-08-06 |  | Y | EL DORADO PH 210219562 | 52 | EL DORADO COUNTY | Yes
35112435 |  | 2020 | 220 Mile Plan | CWSP - EL DORADO 2102 - LR19562 - PH 1.5 |  | MAPP | 7185 | 0 | 7006 | 7006 | 1.3269 | 7006 | 1.3269 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | SH | 2020-07-24 | 2020-07-24 | 2020-08-31 | 2020-07-24 | 2019-10-16 | 2019-10-16 | Yes | 2020-07-24 | 07/06: ADER pre-Final corrections communicated - QUES applied corrections07/02: QUES submitted for ADE review07/01: redesign - EST applied redesign - EST routed - EOD (7/17)Redesign******7/3: QUES to review to provide review on 1st ADE Submital7/16 - 8/21: On track for 8/319/04: Push to 9/9 - Reprioritized to resolve corrections, resource shift--> [RCC Issue]9/11: 1st Submittal push to 9/20 - 9/18: Push to 9/30 - Training/New Hire ramp up 9/25: On track for 9/30 1st submittal10/02: QUES submitted for 1st ADE rvw - ADE assigned [REDACTED]10/03: ADE return 1st corrections to contractor10/09: Resource availability - in stamping - push to mid following week10/14: QUES submitted for 2nd ADE rvw [PRELIM DWG ready]10/14: ADE approved10/15: Routed | QUES |  |  | Redesign | EDRS - Pending EDRS approval | No | Obsolete (CONS+) | 0 | 0 |  | yes | [5 empty] | Full |  |  | Full |  |  | ERTC Call 1/7/2020 | Full |  | Yes |  |  | 2-12-2020. 2019 annual previously uploaded. Task should be reset until 2020 permit obtained. | 1980-01-01 | Y | [10 empty] | 0 | 0 | 7006 | 1.3269 | 1.3269 | 0 | 1.1434 | 0 | 1.3525 | 0.20909 | 0.18352 | 1.1434 |  | Keep | 2020-03-06 | Yes | N/A | 2020-04-20 | 2020-08-04 | 2020-09-04 |  |  | 2020-09-04 |  | Yes | Shovel Ready | 2874678.8 | 4110577.9 |  | 4061849 | 1187170.2 | 2855912.6 | 143% | 9454.8 | 9311.4 | 18766.2 | 0 | 3097894.849 | 36 | [9 empty] | Pollock Pines | El Dorado | 0 | 0 | E.5015687.06 |  |  |  | 2020 | Q1 | 2019-10-16 | 2020-04-27 | 2020-05-31 |  | Y | EL DORADO PH 210219562 | 52 | EL DORADO COUNTY | Yes
35112436 |  | 2020 | 220 Mile Plan | CWSP - EL DORADO 2102 - LR19562 - PH 1.6 |  | MAPP | 9210 | 0 | 9504 | 9504 | 1.8 | 9504 | 1.8 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | SH | 2020-03-10 | 2019-09-28 | 2019-10-06 | 2019-09-28 |  |  | Yes | 2019-09-28 | 7/3: QUES to review to provide review on 1st ADE Submital 7/16 - 8/21: On track for 8/31 9/04: QUES submitted for 1st ADE rvw --> [RCC Issue] 9/11 -9/18: ADE to be assigned 9/23: Corrections rtn to contractor | QUES |  |  | Completed | COMPLETED | No |  | 0 | 0 |  | Yes | [5 empty] | Full |  |  | Full |  |  | ERTC Call 1/7/2020 | Full |  | Yes |  |  |  | 1980-01-01 | Y | [10 empty] | 0 | 0 | 9504 | 1.8 | 1.8 | 0 | 1.8047 | 0 | 1.8047 | 0 | -0.0047348 | 1.8047 |  | Keep | 2020-03-10 | Yes | N/A | 2020-03-09 | 2020-05-08 | 2020-05-08 |  |  | 2020-05-15 |  | Yes | Shovel Ready | 2767806.4 | 1695660.9 |  | 3899347 | 1131540.6 | 2760194.9 | 61.26% | 7611.5 | 0 | 7611.5 | 0 | 942033.8333 | 47 | [9 empty] | Pollock Pines | El Dorado | 0 | 0 | E.5015687.07 |  |  |  | 2020 | Q1 | 2019-09-28 | 2020-04-27 | 2020-06-07 |  | Y | EL DORADO PH 210219562 | 52 | EL DORADO COUNTY | Yes
35112437 |  | 2020 | 220 Mile Plan | CWSP - EL DORADO 2102 - LR19562 - PH 1.7 |  | FICL | 14893 | 0 | 14550 | 14550 | 2.7557 | 14550 | 2.7557 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | SH | 2020-04-19 | 2019-10-24 | 2019-10-24 | 2019-10-24 |  |  | Yes | 2019-10-24 | 7/3: QUES to review to provide review on 1st ADE Submital7/16 - 8/21: On track for 8/319/04: Push to 9/9 - Reprioritized to resolve corrections, resource shift--> [RCC Issue]9/11: QUES Partial 1st submittal for ADE Rvw - Target for OCALC stamped and submit for 9/11 (for full review) - Large Project, 179 Loc.9/15: QUES 1st submittal for ADE Rvw final9/18: ADE assigned - [REDACTED]9/25: ADE targeting rvw completion by EOW9/30: ADE 1st rvw corrections rtn to contractor10/02: 2nd submittal at RISK of delay due to 1 PE to stamp10/07: QUES submitted for 2nd ADE rvw10/08: ADE 2nd corrections rtn to contractor10/08: QUES submitted for 3rd ADE rvw10/09: QUES to route for approval10/16: Check in with ADE - giving the FAA validation issue. Submitted another ticket since the previous one was closed because they thought it was fixed - Push 1wk10/18: Estimator made adjustments in attempt to clear issues - reached out to [REDACTED] for further support. Error still occurs. | QUES |  |  | Completed | COMPLETED | No |  | 0 | 0 |  | Yes | [5 empty] | Full |  |  | Full |  |  | ERTC Call 1/7/2020 | Full |  | Yes |  |  |  | 2020-06-30 | Y | 2020-04-19 |  |  | Started | [6 empty] | 0 | 0 | 14550 | 2.7557 | 2.7557 | 0 | 2.6938 | 0 | 2.6938 | 0 | 0.061932 | 2.6655 |  | Keep | 2020-03-18 | Yes | N/A | 2020-05-07 | 2020-07-29 | 2020-07-29 |  |  | 2020-08-26 |  | Yes | Shovel Ready | 3380647.7 | 3513496.8 |  | 5431839 | 2051191.3 | 3369921.8 | 103.9% | 10725.9 | 0 | 10725.9 | 0 | 1275000.9006 | 75 | [9 empty] | Pollock Pines | El Dorado | 0 | 0 | E.5015687.08 |  |  |  | 2020 | Q2 | 2019-10-24 | 2020-04-27 | 2020-07-08 |  | Y | EL DORADO PH 210219562 | 52 | EL DORADO COUNTY | Yes
35112504 |  | 2020 |  | BUCOCAMPT 12700 CENTERVILLE RD CHICO |  | DOCC |  | 0 | 528 | 528 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 95F | [51 empty] | 528 | 0.1 | 0 | 0 | 0.1 | 0 | 0.068561 | 0 | 0.068561 | 0 | 0.031439 | 0.068561 |  |  |  |  | N/A | [5 empty] | 2019-08-05 |  |  |  | 0 | 80011.7 |  | 24692.78 | 24692.78 | -80011.7 |  | 80011.7 | 0 | 80011.7 | 0 | 800117 | [10 empty] | Chico | Butte | 39.7631 | -121.6756 |  |  |  |  | 2019 | [5 empty] | Y |  |  | BUTTE COUNTY | Yes
35112698 |  | 2020 |  | BUCOCAMPT 5036 EDGEWOOD LN PARADISE |  | CLSD |  | 0 | 1164 | 1164 | 0.22045 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 95F | [51 empty] | 1164 | 0.22045 | 211 | 0.039962 | 0.26042 | -0.039962 | 0.2642 | 0 | 0.2642 | 0 | -0.0037879 | 0.2642 |  |  |  |  | N/A | [5 empty] | 2019-09-17 |  |  |  | 0 | 159464.6 |  | 65672.54 | 65672.54 | -159464.6 |  | 159464.6 | 0 | 159464.6 | 0 | 723344.5773 | [12 empty] | 39.7312 | -121.5844 |  |  |  |  | 2019 | [5 empty] | Y |  |  | BUTTE COUNTY | Yes
35112699 |  | 2020 |  | BUCOCAMPT 5210 PARKWAY DR PARADISE |  | FICL |  | 0 | 299 | 299 | 0.056629 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 95F | [51 empty] | 299 | 0.056629 | 0 | 0 | 0.056629 | 0 | 0.062121 | 0 | 0.062121 | 0 | -0.0054924 | 0.062121 |  |  |  |  | N/A | [5 empty] | 2019-08-20 |  |  |  | 0 | 21002.8 |  | 32195.84 | 32195.84 | -21002.8 |  | 21002.8 | 0 | 21002.8 | 0 | 370885.5652 | [12 empty] | 39.7376 | -121.5945 |  |  |  |  | 2019 | [5 empty] | Y |  |  | BUTTE COUNTY | Yes
35112770 |  | 2020 |  | BUCOCAMPT 456 GREEN OAKS DR PARADISE |  | DOCC |  | 0 | 369 | 369 | 0.069886 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 95F | [51 empty] | 369 | 0.069886 | 53 | 0.010038 | 0.079924 | -0.010038 | 0.076326 | 0 | 0.076326 | 0 | 0.0035985 | 0.076326 |  |  |  |  | N/A | [5 empty] | 2019-07-27 | [27 empty] | 39.7424 | -121.634 |  |  |  |  | 2019 | [8 empty] | BUTTE COUNTY | Yes
35112822 |  | 2020 |  | BUCOCAMPT 13949 ANDOVER DR MAGALIA*ILB |  | FICL |  | 0 | 1264 | 1264 | 0.23939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 95F | [51 empty] | 1264 | 0.23939 | 0 | 0 | 0.23939 | 0 | 0.11023 | 0 | 0.11023 | 0 | 0.12917 | 0.11023 |  |  |  |  | N/A | [5 empty] | 2019-11-03 |  |  |  | 0 | 46660.6 |  | 33544.57 | 33544.57 | -46660.6 |  | 46660.6 | 0 | 46660.6 | 0 | 194911.3671 | [12 empty] | 39.8172 | -121.5971 |  |  |  |  | 2019 | [5 empty] | Y |  |  | BUTTE COUNTY | Yes
35112837 |  | 2020 |  | BUCOCAMP 6037 SHADOW MTN LN PARADIS |  | CLSD |  | 0 | 410 | 410 | 0.077652 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 95F | [51 empty] | 410 | 0.077652 | 0 | 0 | 0.077652 | 0 | 0.049432 | 0 | 0.049432 | 0 | 0.02822 | 0.049432 |  |  |  |  | N/A | [5 empty] | 2019-09-25 | [27 empty] | 39.764 | -121.6391 |  |  |  |  | 2019 | [8 empty] | BUTTE COUNTY | Yes
35112838 |  | 2020 |  | BUCOCAMPT 1409 JESSIE LN PARADISE*ILB |  | CLSD |  | 0 | 167 | 167 | 0.031629 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 95F | [51 empty] | 167 | 0.031629 | 0 | 0 | 0.031629 | 0 | 0.029735 | 0 | 0.029735 | 0 | 0.0018939 | 0.029735 |  |  |  |  | N/A | [5 empty] | 2019-11-05 |  |  |  | 0 | 69952.6 |  | 28953.3 | 28953.3 | -69952.6 |  | 69952.6 | 0 | 69952.6 | 0 | 2211675.018 | [10 empty] | Paradise | Butte | 39.7516 | -121.5937 |  |  |  |  | 2019 | [5 empty] | Y |  |  | BUTTE COUNTY | Yes
35113072 |  | 2020 |  | BUCOCAMPT 485 LEISURE LANE PARADISE |  | DOCC |  | 0 | 366 | 366 | 0.069318 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 95F | [51 empty] | 366 | 0.069318 | 106 | 0.020076 | 0.089394 | -0.020076 | 0.093371 | 0 | 0.093371 | 0 | -0.0039773 | 0.093371 |  |  |  |  | N/A | [5 empty] | 2019-08-17 | [27 empty] | 39.7366 | -121.6324 |  |  |  |  | 2019 | [8 empty] | BUTTE COUNTY | Yes
35113075 |  | 2020 |  | BUCOCAMPT 5577 NEWLAND RD PARADISE |  | DOCC |  | 0 | 392 | 392 | 0.074242 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 95F | [51 empty] | 392 | 0.074242 | 739 | 0.13996 | 0.2142 | -0.13996 | 0.20739 | 0 | 0.20739 | 0 | 0.0068182 | 0.20739 |  |  |  |  | N/A | [5 empty] | 2019-09-27 |  |  |  | 0 | 245911.9 |  | 44943.96 | 44943.96 | -245911.9 |  | 245911.9 | 0 | 245911.9 | 0 | 3312282.7347 | [12 empty] | 39.7523 | -121.6009 |  |  |  |  | 2019 | [5 empty] | Y |  |  | BUTTE COUNTY | Yes
35113101 |  | 2020 | 220 Mile Plan | CWSP - WEST POINT 1101 -LR 13444- PH 2.5 |  | CONS | 11056 | 0 | 10788 | 10788 | 2.0432 | 7552 | 1.4303 | 3236 | 0.61288 | 0 | 0 | 0 | 10788 | 2.0432 | ST | 08W | SH | 2020-07-27 | 2020-03-30 | 2020-03-26 | 2020-03-30 | 2020-03-16 | 2020-03-16 | Yes | 2020-03-26 | 03/30: INTO PEND03/25: EST firm up sub date??03/23: ADE rtn 2nd corrections to CO03/16: QUES submitted for 2nd ADE rvw03/04: QUES provided 2nd sub to PMgr; Est - Waiting on Tree Trimming information (dependency) - will submit upon rcpt.02/26: EST confirm 2nd sub date (3/4)02/22: ADE rtn 1st corrections to CO02/06: ADE assigned [REDACTED]; EST - link updated12/06: QUES submitted for 1st ADE rvw9/19: EEI stop; QUES assigned11/20 <-- 9/11: On Track09/04: On Track for 1st Submittal 12/30 | QUES |  |  | 2020 - Q4- M10 [R316] | COMPLETED |  | Obsolete (CONS+) | 0 | 0 |  | Yes | [5 empty] | Full |  |  | Full |  |  |  | Full | 2020-07-27 | Yes |  |  | Revising TCP will submit by 6/26 | 2020-07-31 | Y | 2020-06-29 | [9 empty] | 0 | 0 | 10830 | 2.0511 | 2.0511 | -0.0079545 | 2.0487 | 0 | 2.1036 | 0.054924 | 0.0024621 | 0.9911 |  | Keep | 2020-06-05 | Yes | COMP | 2020-08-24 | 2020-10-13 17:00 | 2020-10-13 17:00 |  |  |  | 2020-07-17 | yes | Shovel Ready | 3128068.2 | 3861222.5 |  | 2715235.15 | -412833.05 | 2935206.2 | 123.4% | 2339.9 | 190522.1 | 192862 | 0 | 1889808.5651 | 58 | [9 empty] | Volcano | Amador | 0 | 0 | E.5014726.05 |  |  |  | 2020 | Q4 | 2020-10-31 | 2020-11-30 |  |  | Y | WEST POINT 110113444 | 63 | AMADOR COUNTY | Yes
35113102 |  | 2020 | 220 Mile Plan | CWSP - WEST POINT 1101 -LR 13444- PH 2.6 |  | CONS | 11533 | 0 | 11757 | 11757 | 2.2267 | 8309 | 1.5737 | 3448 | 0.65303 | 0 | 0 | 0 |  |  | ST | 08W | SH | 2020-07-17 | 2020-03-20 | 2020-03-20 | 2020-03-20 | 2020-02-25 | 2020-02-25 | Yes | 2020-03-20 | 03/20: INTO PEND3/20: EST - Per new requirement, need a note added to CMCS Purpose of work with the Planned units footage; target correction (3/20)03/18: ADE approved for routing - final corrections rtn to CO03/16: ADE rejected (adding the GC review costs to the estimate )03/10: EST request rejection of routing - adding the GC review costs to the estimate 03/04: PUsh to 3/13 (1wk) Waiting on planning approval attachment and planner to complete DS73. Estimator has reached out again to planner this morning. (Who is Planner??)02/26: QUES routed 2/25 in EES, awaiting approval02/19: EST to confirm target date??02/13: ADE rtn 1st corrections to CO02/05: ADE assigned [REDACTED]12/03: QUES submitted for 1st ADE rvw9/19: EEI stop; QUES assigned11/20 <-- 9/11: On Track09/04: On Track for 1st Submittal 12/30 | QUES |  |  | 2020 - Q1- M3 [R317] | COMPLETED |  | Obsolete (CONS+) | 0 | 0 |  | Yes | [5 empty] | Full |  |  | Full |  |  |  | Full |  | Yes |  |  | App submitted | 2020-07-10 | Y | 2020-06-29 | [9 empty] | 0 | 0 | 11880 | 2.25 | 2.25 | -0.023295 | 2.1784 | 0 | 2.2267 | 0.048295 | 0.071591 | 2.1784 |  | Keep | 2020-05-19 | Yes | COMP | 2020-08-24 | 2020-09-10 | 2020-10-03 |  |  |  |  | Yes | Shovel Ready | 3198327 | 4688739.1 |  | 4620298 | 1421971 | 2927186.6 | 146.6% | 1292.8 | 269847.6 | 271140.4 | 0 | 2105685.332 | 58 | [9 empty] | Volcano | Amador | 0 | 0 | E.5014726.06 |  |  |  | 2020 | Q2 | 2020-03-31 | 2020-05-01 | 2020-06-23 |  | Y | WEST POINT 110113444 | 63 | AMADOR COUNTY | Yes
35113103 |  |  |  | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.3 |  | CLSD | 1152 | 0 | 1152 | 1152 | 0.21818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | DA | 08W | SH | 2019-07-26 | 2019-07-26 |  | 2019-07-26 |  |  | Yes | 2019-07-26 | [5 empty] | 100 | [11 empty] | Full |  |  | Full |  |  | CIF Submitted as of 8/20 | Full |  | Yes |  |  |  | 1980-01-01 | Y | [10 empty] | 1152 | 0.21818 | 0 | 0 | 0.21818 | 0 | 0.21818 | 0 | 0.21818 | 0 | 0 | 0.21818 |  |  |  |  | N/A | [5 empty] | 2019-11-15 | [15 empty] | 7 | [9 empty] | Los Gatos | Santa Clara | 0 | 0 | E.5014319.03 |  |  | 2020-077 | 2019 | Q4 |  |  |  |  | Y | LOS GATOS 1106LB44 | 841 | SANTA CLARA COUNTY | Yes
35113104 |  |  |  | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.2 |  | CLSD |  | 0 | 1324.3 | 1324.3 | 0.25081 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | DA | 08W | SH | 2019-10-30 | [38 empty] | y | [10 empty] | 1324.3 | 0.25081 | 0 | 0 | 0.25081 | 0 | 0.25081 | 0 | 0.25081 | 0 | 0 | 0.25081 |  |  | 2019-10-30 |  | N/A | 2019-11-08 08:00 | 2019-12-19 | 2019-12-19 |  |  | 2019-12-19 | [25 empty] | Los Gatos | Santa Clara | 0 | 0 |  |  |  |  | 2019 | [5 empty] | Y | LOS GATOS 1106LB44 | 841 | SANTA CLARA COUNTY | Yes
35113105 |  | 2020 | 220 Mile Plan | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.4 |  | FICL | 3582 | 0 | 3782 | 3782 | 0.71629 | 3782 | 0.71629 | 0 | 0 | 0 | 0 | 0 |  |  | DA | 08W | SH | 2019-12-17 | 2019-09-12 |  | 2019-09-12 |  |  | Yes | 2019-09-12 | [5 empty] | 100 | [5 empty] | Yes | [5 empty] | Full |  |  | Full |  |  | CIF Submitted 9/23/19 | Full |  | Yes |  |  |  | 1980-01-01 | Y | [10 empty] | 0 | 0 | 3782 | 0.71629 | 0.71629 | 0 | 0.71629 | 0 | 0.71629 | 0 | 0 | 0.71629 |  | Keep | 2019-12-17 | Yes | N/A | 2020-02-13 | 2020-06-26 08:00 | 2020-06-26 08:00 |  |  | 2020-11-15 |  | Yes | Shovel Ready | 1403671 | 1148834.9 |  | 1425671 | 22000 | 1232233.9 | 81.84% | 171437.1 | 0 | 171437.1 | 0 | 1603873.1549 | 21 | [9 empty] | Los Gatos | Santa Clara | 0 | 0 | E.5014319.04 |  |  | 2020-078 | 2020 | Q1 | 2019-09-12 | 2020-02-02 | 2020-03-23 |  | Y | LOS GATOS 1106LB44 | 841 | SANTA CLARA COUNTY | Yes
35113109 |  |  |  | CWSP - LOS GATOS 1106 - LB44 - PHASE 3.2 |  | CLSD |  | 0 | 681 | 681 | 0.12898 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | DA | 08W | SH | [39 empty] | Y | [10 empty] | 681 | 0.12898 | 0 | 0 | 0.12898 | 0 | 0.12898 | 0 | 0.12898 | 0 | 0 | 0.12898 |  |  |  |  | N/A | [5 empty] | 2019-12-18 | [25 empty] | Los Gatos | Santa Clara | 0 | 0 |  |  |  |  | 2019 | [5 empty] | Y | LOS GATOS 1106LB44 | 841 | SANTA CLARA COUNTY | Yes
35113520 |  | 2020 |  | BUCOCAMPT 1395 SALISBURY LN PARADISE |  | DOCC |  | 0 | 337 | 337 | 0.063826 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 95F | [51 empty] | 337 | 0.063826 | 211 | 0.039962 | 0.10379 | -0.039962 | 0.099432 | 0 | 0.099432 | 0 | 0.0043561 | 0.099432 |  |  |  |  | N/A | [5 empty] | 2019-10-18 |  |  |  | 0 | 602590.3 |  | 50574.19 | 50574.19 | -602590.3 |  | 602590.3 | 0 | 602590.3 | 0 | 9441177.4006 | [12 empty] | 39.7814 | -121.5947 |  |  |  |  | 2019 | [5 empty] | Y |  |  | BUTTE COUNTY | Yes
35113521 |  | 2020 |  | BUCOCAMPT 1651 LIGHTLY LN PARADISE*ILB |  | DOCC |  | 0 | 1130 | 1130 | 0.21402 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 95F | [51 empty] | 1130 | 0.21402 | 0 | 0 | 0.21402 | 0 | 0.087689 | 0 | 0.087689 | 0 | 0.12633 | 0.087689 |  |  |  |  | N/A | [5 empty] | 2019-10-02 |  |  |  | 0 | 81975.7 |  | 42363.79 | 42363.79 | -81975.7 |  | 81975.7 | 0 | 81975.7 | 0 | 383036.8991 | [12 empty] | 39.7582 | -121.582 |  |  |  |  | 2019 | [5 empty] | Y |  |  | BUTTE COUNTY | Yes
35113522 |  | 2020 |  | BUCOCAMPT 13832 TULSA CT MAGALIA |  | CLSD |  | 0 | 784 | 784 | 0.14848 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 95F | [51 empty] | 784 | 0.14848 | 0 | 0 | 0.14848 | 0 | 0.13258 | 0 | 0.13258 | 0 | 0.015909 | 0.13258 |  |  |  |  | N/A | [5 empty] | 2019-10-02 |  |  |  | 0 | 72364.6 |  | 42560.78 | 42560.78 | -72364.6 |  | 72364.6 | 0 | 72364.6 | 0 | 487353.4286 | [12 empty] | 39.8121 | -121.5961 |  |  |  |  | 2019 | [5 empty] | Y |  |  | BUTTE COUNTY | Yes
35113524 |  | 2020 |  | BUCOCAMPT 1308 DEODARA WAY PARADISE* |  | DOCC |  | 0 | 185 | 185 | 0.035038 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 95F | [51 empty] | 185 | 0.035038 | 475 | 0.089962 | 0.125 | -0.089962 | 0.12917 | 0 | 0.12917 | 0 | -0.0041667 | 0.12917 |  |  |  |  | N/A | [5 empty] | 2019-10-19 |  |  |  | 0 | 114505.4 |  | 44821.11 | 44821.11 | -114505.4 |  | 114505.4 | 0 | 114505.4 | 0 | 3268046.0108 | [12 empty] | 39.7578 | -121.5984 |  |  |  |  | 2019 | [5 empty] | Y |  |  | BUTTE COUNTY | Yes
35113526 |  | 2020 |  | BUCOCAMPT 5601 CAMPUS DR PARADISE |  | CLSD |  | 0 | 387 | 387 | 0.073295 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 95F | [51 empty] | 387 | 0.073295 | 158 | 0.029924 | 0.10322 | -0.029924 | 0.10152 | 0 | 0.10152 | 0 | 0.0017045 | 0.10152 |  |  |  |  | N/A | [5 empty] | 2019-09-14 |  |  |  | 0 | 61877.2 |  | 55724.41 | 55724.41 | -61877.2 |  | 61877.2 | 0 | 61877.2 | 0 | 844216.062 | [12 empty] | 39.7522 | -121.62 |  |  |  |  | 2019 | [5 empty] | Y |  |  | BUTTE COUNTY | Yes
35113528 |  | 2020 |  | BUCOCAMPT 1056 FAIRVIEW DR PARADISE |  | DOCC |  | 0 | 200 | 200 | 0.037879 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 95F | [51 empty] | 200 | 0.037879 | 792 | 0.15 | 0.18788 | -0.15 | 0.18561 | 0 | 0.18561 | 0 | 0.0022727 | 0.18561 |  |  |  |  | N/A | [5 empty] | 2019-09-19 | [25 empty] | Paradise | Butte | 39.7635 | -121.6125 |  |  |  |  | 2019 | [8 empty] | BUTTE COUNTY | Yes
35113871 |  |  |  | SILVERADO 2104 RECONDUCTOR - PHASE 2 |  | CLSD | 8976 | 650 | 0 | 650 | 0.12311 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NB | 08W | SH | 2019-08-08 | 2019-02-26 |  | 2019-02-26 |  |  | Yes | 2019-02-26 |  | SANTA ROSA |  |  |  | 100 | No | [10 empty] | Full |  |  | Full |  |  | Undergrounding redesign in process. Once completed will provide to ENV team / Need laydown | Full |  | Yes |  |  | Approved through May 2020 | 1980-01-01 | Y | [10 empty] | 650 | 0.12311 | 0 | 0 | 0.12311 | 0 | 0.12311 | 0 | 0.12311 | 0 | 0 | 0.12311 |  |  | 2019-08-08 |  | N/A | 2019-10-01 | 2019-12-14 | 2019-12-14 |  |  | 2019-12-13 | [15 empty] | 35 | [9 empty] | Angwin | Napa | 0 | 0 | E.5014537.02 |  |  |  | 2019 | Q1 |  |  |  |  | Y | SILVERADO 2104563322 | 295 | NAPA COUNTY | Yes
35113925 |  | 2020 |  | BUCOCAMPT 6466 LONE CEDAR LN PARADISE |  | DOCC |  | 0 | 167 | 167 | 0.031629 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 95F | [51 empty] | 167 | 0.031629 | 1003 | 0.18996 | 0.22159 | -0.18996 | 0.21591 | 0 | 0.21591 | 0 | 0.0056818 | 0.21591 |  |  |  |  | N/A | [5 empty] | 2019-09-21 |  |  |  | 0 | 184154 |  | 79712.38 | 79712.38 | -184154 |  | 184154 | 0 | 184154 | 0 | 5822354.012 | [12 empty] | 39.7813 | -121.5982 |  |  |  |  | 2019 | [5 empty] | Y |  |  | BUTTE COUNTY | Yes
35114042 |  | 2020 | 220 Mile Plan | OCGC PINE GROVE 1102 - LR1222 - PH 1.4 |  | DOCC | 7522 | 0 | 7123 | 7123 | 1.3491 | 7126 | 1.3496 | 0 | 0 | 0 | 0 | -0.00056818 |  |  | ST | 08W | SH | 2020-06-13 | 2020-04-08 | 2020-04-08 | 2020-04-08 | 2020-03-06 | 2020-03-06 | Yes | 2020-04-08 | 04/08: IN TO PEND04/07:Final approv corrections sent to CO; 03/31: Routing for approval03/25: EN submitted correction; ADE advised correct03/24: EN submitted for 5ht ADE rvw - ADE rtn 5th correction; Loc-86, OCalc was change to Grade "C" construction? It should be Grade "B" construction.03/24: ADE rtn 4th corrections to CO - Please save all OCalc and it will autosave in SAP as a zip OCalc file for ADE to compare.03/23: EN submitted for 4th ADE rvw03/19: ADE rtn 3rd corrections to CO03/18: EN submitted for 3rd ADE rvw03/17: EST on track03/10: EST set sub date 3/18 - Estimator working 3 Pine Grove03/07: ADE rtn 2nd corrections to CO03/04: EN submitted for 2nd ADE rvw03/24: EST to firm up sub ??03/03: EST Confirm ON TRACK02/25: Redlines done - completing fld walk with for any final changes02/18: EST confirm target date02/15: ADE rtn 1st corrections to CO02/10: ADE assigned [REDACTED]01/28: Push Prelim date due to new Priority Alignments01/07 <-- 12/03: ADE 1st rvw holding for resource availability & assignment11/19 <-- 10/01: ADE to be assigned - waiting on 2020 priority list; [11/19] 2nd push 1 10/23: EN submitted for 1st ADE rvw10/22 <-- 9/03: On Track - Targeting earlier submittal8/13 Fielding planned for EOM (Aug) | EN |  |  | 2020 - Q2- M6 [R26] | COMPLETED |  | Obsolete (CONS+) | 0 | 0 |  | Yes |  |  |  | 2020-06-12 | 2020-06-12 | Full | 2020-06-12 | 2020-06-12 | Full |  |  | ERTC issued 4/13/20- no Caltrans permit required (due 6/12/2020) | Full | 2020-06-13 | Yes | 2021-11-30 |  | 5/18/20 Permit not required, Requested 3/5/20 | 2020-06-26 | Y | 2020-06-03 | 2020-05-15 |  | preinspection 100% complete 6/17 | [6 empty] | 0 | 0 | 7126 | 1.3496 | 1.3496 | -0.00056818 | 1.172 | 0 | 1.3803 | 0.20833 | 0.17765 | 1.172 |  | Keep | 2020-05-19 | Yes | COMP | 2020-06-18 | 2020-08-25 17:00 | 2020-08-25 17:00 |  |  | 2020-08-25 | 2020-06-12 | Yes | Shovel Ready | 2039341.3 | 3879536.4 |  | 2867650 | 828308.7 | 1986299.1 | 190.2% | 676.8 | 52365.4 | 53042.2 | 0 | 2875747.886 | 53 |  |  | Complete | [6 empty] | Kit Carson | Amador | 0 | 0 | E.5014745.04 |  |  |  | 2020 | Q3 | 2020-06-30 | 2020-12-27 |  |  | Y | PINE GROVE 11021222 | 20 | AMADOR COUNTY | Yes
35114043 |  | 2020 | 220 Mile Plan | CWSP - PINE GROVE 1102 - LR1222 - PH 1.5 |  | DOCC | 5763 | 0 | 5542 | 5542 | 1.0496 | 5542 | 1.0496 | 0 | 0 | 0 | 0 | 0 |  |  | ST | 08W | SH | 2020-06-15 | 2020-04-24 | 2020-04-24 | 2020-04-24 | 2020-01-23 | 2020-01-23 | Yes | 2020-04-24 | 04/24: APPROVED - INTO PEND04/17: EST routed - (To be confirmed)04/16: ADE rtn 5th corrections to CO04/14: EN submitted for 5th ADE rvw - target approval EOW04/07: EST to firm up sub date (04/03) - 4/1003/31: ADE rtn 4th corrections to CO - We do not have a 5' rule for uplift strain03/26: EN submitted for 4 ADE rvw03/24 - 03/17: Est - Site walk scheduled (next week); rvw if sched is to be cancel - if cancelled; ready to submit. PM request walk.03/10: EST confirmed sub (3/13)03/05: ADE rnt 4th corrections to CO03/03: ADE target EOW; 3rd rvw02/26: EN submitted for 3rd ADE rvw02/18: In stamping (target MID/EOW)02/15: EST/ADE post Field Meet - corrections/change coordination (loc 47-80 span ommission?/ DWG updates)02/11: EST/ADE coordinating on corrections - Target sub 3 EOW02/07: ADE to rtn 2nd correction to CO02/03: ADE rtn from Vaca 1/24: Per ADE OCalcs need to be stamped1/23: EN submitted for 2nd ADE rvw1/21: EST/ADE coordinating correction; resolving conflicting information - Target EOW01/14: EST Clarified some ADE correction requests01/07: ADE rtn 1st corrections to contractor12/03: ADE 1st rvw holding for resource availability & assignment11/19: ADE to be assigned - 1mth push to align11/06: EN Submitted for 1st ADE rvw11/05: Internal QC - Tomorrow submittal10/29 <-- 9/03: On Track8/13 Fielding planned for EOM (Aug) | EN |  |  | 2020 - Q2- M5 [R27] | COMPLETED |  | Obsolete (CONS+) | 0 | 0 |  | Yes | [5 empty] | Full |  |  | Full |  |  |  | Full | 2020-05-15 | Yes | 2020-12-31 |  | Submitted | 2020-07-10 | Y | 2020-06-15 | 2020-06-03 | [8 empty] | 0 | 0 | 5542 | 1.0496 | 1.0496 | 0 | 1.0496 | 0 | 1.1271 | 0.077462 | 0 | 1.0496 |  | Keep | 2020-06-09 17:00 | Yes | N/A | 2020-06-17 08:00 | 2020-08-14 | 2020-08-14 17:00 |  |  | 2020-08-14 |  | Yes | Shovel Ready | 1947510.4 | 1841719.7 |  | 2617141 | 669630.6 | 1895208.7 | 94.56% | 213.7 | 52088 | 52301.7 | 0 | 1754651.7532 | 39 | [9 empty] | Kit Carson | Amador | 0 | 0 | E.5014745.05 |  |  |  | 2020 | Q3 | 2020-05-31 | 2020-09-01 | 2020-09-30 |  | Y | PINE GROVE 11021222 | 20 | AMADOR COUNTY | Yes
35114101 |  | 2020 | 220 Mile Plan | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.3 |  | FICL | 6671 | 0 | 6873 | 6873 | 1.3017 | 6873 | 1.3017 | 0 | 0 | 0 | 0 | 0 |  |  | CC | 08W | SH | 2020-05-19 | 2020-04-28 | 2020-04-28 | 2020-04-28 | 2019-11-15 | 2019-11-15 | Yes | 2020-04-28 | 04/28: APPROVED - INTO PEND04/24: ADE rtn corrections to CO - minor; Final corrections approved - ready for routing.04/22: CAL submitted for 6th ADE rvw04/18: ADE rtn corrections to CO04/10: CAL submittted for 5th ADE rvw - redesigns03/31: EST - will require the re-design of 18 pole units + 1 additional recloser pole (location TBD by Planner) so 18 pole units @ $470.81/unit + 1 new pole03/18: ADE status update??03/13: CAL submitted for 4th ADE rvw - possible redesign coming.03/11: Submitting by end of day today03/03: ADE sent in prelim corrections (last week); to receive updates today; target early next week.02/19: Push; ADE Status??02/12: CAL submitted for 3rd ADE rvw; ADE confirmed1/23: ADE rtn 2nd corrections to CO01/15: Per [REDACTED] - EST corrections ready by Friday (1/17) (moved to Lead position, slowed est., implemented request from JO)12/04 - 11/27: ADE Status?11/14: CAL submitted for 2nd ADE rvw 11/13: EST - firmed up 2nd submittal date11/05: Est recv'ng requests for wood to composite (proj initiated prior to 9/5 issuing of standard) - holding for response10/26: ADE return 1st corrections to contractor10/23 <-- 10/16: Check in with ADE (target dates for staggering submittal)10/02 - 9/25: In review8/12: CAL submitted for 1st ADE rvw8/07: Late week changes required rework (Framing issues); pushed submittals 4 days out7/31 <- 7/10: 8/5 1st ADE submittal(v9) | CAL |  |  | 2020 - Q1- M2 [R301] | COMPLETED |  | Obsolete (CONS+) | 0 | 0 |  | Yes | [5 empty] | Full | 2020-05-08 | 2020-05-08 | Full |  |  | PERTC received - Full expected in June | Full |  | Yes |  |  | Need start date for Santa Cruz county to issue permit | 2020-07-14 | Y | 2020-05-15 |  |  | Additional trimming required | [6 empty] | 0 | 0 | 6873 | 1.3017 | 1.3017 | 0 | 1.3017 | 0 | 1.3017 | 0 | 0 | 1.3017 |  | Keep | 2020-05-19 | Yes | N/A | 2020-05-14 | 2020-07-30 | 2020-07-30 |  |  | 2020-08-04 |  | Yes | Shovel Ready | 2217035.6 | 2378026.5 |  | 2641148 | 424112.4 | 2166854.4 | 107.3% | 633.6 | 49547.6 | 50181.2 | 0 | 1826855.801 | 40 | [9 empty] | Scotts Valley | Santa Cruz | 0 | 0 | E.5015489.03 |  |  |  | 2020 | Q2 | 2020-02-29 | 2020-05-01 | 2020-06-04 |  | Y | CAMP EVERS 21065020 | 46 | SANTA CRUZ COUNTY | Yes
35114104 |  | 2020 | 220 Mile Plan | XCWSP - CAMP EVERS 2106 - LR5020 -PH 2.6 |  | CONS | 7619 | 0 | 7772.19 | 7772.19 | 1.472 | 7772.16 | 1.472 | 0 | 0 | 0 | 0 | 5.6818e-06 |  |  | CC | 08W | SH | 2020-06-01 | 2019-11-30 | 2019-11-04 | 2019-11-30 |  |  | Yes | 2019-11-04 | IN PEND10/25: CAL routed10/24: Approved for routing10/23: CAL submitted for 4th ADE rvw10/22: ADE rtn 1st corrections to Contractor10/18: CAL submitted for 3rd ADE rvw10/16: Cal On Track for 3rd corrections10/14: ADE rtn 2nd rvw corrections to contractor10/14: CAL provided docs for 2nd rvw to ADE10/08: CAL submitted for 2nd ADE rvw [PRELIM DWG ready]10/02: ADE requesting adjustment to be applied throughout Est, conflicts with previous ADE requests.10/9/30: ADE 1st correction rtn to contractor - correction for only 1 poleADE reassigned9/27: ADE assigned [REDACTED]9/25 <- 9/04: ADE to be assigned8/29: CAL submitted for 1st ADE rvw8/21: Push 8/30 - 2.1 Review comment impacts - held to apply to this section8/14 <- 7/10: 8/26 1st ADE submittal(v9) | CAL |  |  | Normal | COMPLETED | No | Obsolete (CONS+) | 0 | 0 |  | Yes | [5 empty] | Full |  |  | Full |  |  | [REDACTED] to submit CIF | Full |  | Yes |  |  | Everyting submitted waiting on agency | 2020-12-14 |  | 2020-06-01 |  |  | waiting on line clearance to complete | [6 empty] | 0 | 0 | 7772.16 | 1.472 | 1.472 | 5.6818e-06 | 1.4725 | 0 | 1.4725 | 0 | -0.00053788 | 1.4725 |  | Keep | 2020-02-25 | Yes | N/A | 2020-02-14 08:00 | 2020-06-11 | 2020-06-11 | 2021-01-11 06:53 | 2021-01-11 14:40 |  |  | Yes | Shovel Ready | 2938512 | 2702760.5 |  | 3424639 | 486127 | 2814948.2 | 91.97% | 2239.3 | 121324.5 | 123563.8 | 0 | 1836107.3829 | 60 | [9 empty] | Scotts Valley | Santa Cruz | 0 | 0 | E.5015489.06 |  |  |  | 2020 | Q1 | 2019-11-04 | 2020-02-15 | 2020-03-22 |  | Y | CAMP EVERS 21065020 | 46 | SANTA CRUZ COUNTY | Yes
35114431 |  | 2020 | 220 Mile Plan | CWSP - MORAGA 1101 - LR108540 - PH5 |  | DOCC | 7673 | 166 | 7421 | 7587 | 1.4369 | 7587 | 1.4369 | 0 | 0 | 0 | 0 | 0 |  |  | DI | 08W | SH | 2020-01-15 | 2019-12-06 |  | 2019-12-06 |  |  | Yes | 2019-12-06 |  | Concord | [9 empty] | Yes | [5 empty] | Full |  |  | Full |  |  | Waiting on land - estimating redesigning around land issue - EOD 12/5 | Full |  | Yes |  |  | PM submitted request on 9/5. Need Cons dates to submit road closure request | 1980-01-01 | Y | [10 empty] | 0 | 0 | 7587 | 1.4369 | 1.4369 | -1.8948e-15 | 1.4369 | 0 | 1.4369 | 0 | 1.8948e-15 | 1.4369 |  | Keep | 2020-01-15 | Yes | N/A | 2020-01-15 08:00 | 2020-03-23 | 2020-03-23 |  |  | 2020-03-23 |  | Yes | Shovel Ready | 4623344.8 | 4189137.2 |  | 5279014 | 655669.2 | 4058091 | 90.6% | 565253.8 | 0 | 565253.8 | -206182 | 2915334.7062 | 66 | [9 empty] | Concord | Contra Costa | 0 | 0 | E.5014544.05 |  |  |  | 2020 | Q1 | 2019-12-06 | 2020-01-02 | 2020-03-31 |  | Y | MORAGA 1101108540 | 319 | CONTRA COSTA COUNTY | Yes
35114629 |  | 2020 |  | BUCOCAMPT 6114 N LIBBY RD PARADISE |  | CLSD |  | 0 | 511 | 511 | 0.09678 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 95F | [51 empty] | 511 | 0.09678 | 53 | 0.010038 | 0.10682 | -0.010038 | 0.10758 | 0 | 0.10758 | 0 | -0.00075758 | 0.10758 |  |  |  |  | N/A | [5 empty] | 2019-09-11 |  |  |  | 0 | 36019.8 |  | 27198.46 | 27198.46 | -36019.8 |  | 36019.8 | 0 | 36019.8 | 0 | 372181.1037 | [12 empty] | 39.7675 | -121.5938 |  | MX |  |  | 2019 | [5 empty] | Y |  |  | BUTTE COUNTY | Yes
35115147 |  | 2020 | 220 Mile Plan | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.2 |  | DOCC | 8690 | 0 | 6478 | 6478 | 1.2269 | 6478 | 1.2269 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | SH | 2020-05-01 | 2020-02-25 | 2020-02-25 | 2020-02-25 | 2020-01-17 | 2020-01-17 | Yes | 2020-02-25 | 02/25: IN PEND 02/24: Final corrections requested for approval - PIKE completed and routed 02/18: ADE Status?? 1/28: EST target?? 01/24: ADE rtn 2nd corrections to CO 11/17: PIKE submitted for 2nd rvw - [PRELIM DWG ready] 01/14: Additional fielding completed 1/13; QTY correction and some backtrack adjustments required. 01/06: ADE rtn 1st corrections to contractor 12/31: Large amount of corrections - ADE still in progress 12/17: ADE On track 12/10: ADE working Backlog PMs - reprioritized to 08W 11/26: ADE vacation/Holiday - Push 10/19: Check with ADE on target 10/22: Push 1month (Nov) - ADE Resourcing 10/15: ADE to be assigned - waiting for 2020 priority list 10/08 ADE to be assigned 10/02: PIKE submitted for 1st ADE rvw 10/01: Implementing further adjustments - submitting 10/01 9/17 - 9/24: On Track 9/10: Swap 1st submittal with 3.3 8/27 - 9/03: On track (may swap with another) 8/20: 1st Submittal push 2wks - Priorities/Equip-Resource Availabilities 8/13: PIKE communicated potential pressures on 1st ADE submittal target, due to computer limitations and technical issues (Highlights: Token malfunctions; SAP Access issues) - working through isssues with TSC on case by case basis 7/23 - 8/6: On Track for 9/6 7/19: Vendor Provided 1st ADE Sub dates 7/16: Vendor Request for 1st ADE Submittal 7/15: Sub Order issued [Version 8] | PIKE |  |  | 2020 - Q1- M3 [R138] | COMPLETED | No | Obsolete (CONS+) | 0 | 0 |  | Yes | [5 empty] | Full |  |  | Full |  |  | CIF Submitted 1/7/2020 | Full |  | Yes |  |  | Permit not required per SAP No permits needed. | 2020-05-29 | Y | 2020-05-01 |  |  | Started 5/1/20 | [6 empty] | 0 | 0 | 6478 | 1.2269 | 1.2269 | 0 | 1.2269 | 0 | 1.2269 | 0 | 0 | 1.2269 |  | Keep | 2020-02-17 | Yes | N/A | 2020-05-05 | 2020-08-13 | 2020-08-13 |  |  | 2020-08-13 |  | Yes | Shovel Ready | 3614964.3 | 2252024.4 | -233251 | 5398830 | 1783865.7 | 3612233.1 | 62.29% | 2731.2 | 0 | 2731.2 | 0 | 1835549.372 | 44 | [9 empty] | Nevada City | Nevada | 0 | 0 | E.5015567.02 |  |  | 2020-138 | 2020 | Q2 | 2020-03-31 | 2020-08-01 | 2020-09-07 |  | Y | BRUNSWICK 110350070 | 7 | NEVADA COUNTY | Yes
35115148 |  | 2020 | 220 Mile Plan | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.3 |  | MAPP | 12685 | 0 | 11320 | 11320 | 2.1439 | 11320 | 2.1439 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | SH | 2020-05-01 | 2020-04-24 | 2020-04-24 | 2020-04-24 | 2020-03-31 | 2020-03-31 | Yes | 2020-04-24 | 04/24: APPROVED - INTO PEND 04/23: EST submitted corrections 04/22: ADE approval req minor correction 04/21: EST routing for approval 4/16: ADE rtn corrections; ready for concur 04/14: Applying corrections (target today- 4/17 latest) 04/13: ADE rtn 3rd corrections to CO 04/07: EST sub date (4/10) 04/01: ADE rtn 2nd corrections to CO 03/31: PIKE submitted for 2nd ADE rvw; PRj Mgr request completion; GC planning to start construction on this phase 5/18/2020 03/24: EST status - in PE stamping 03/17: EST on track 03/11: EST seeking clarification on comments; used FRD Guide TD9001B-008 REV1 (earlier project) 03/10: ADE rtn 1st corrections to CO 03/03 - 02/25: ADE Status/Target date?? <requested> Pushed 01/27: PIKE reSubmitted for 1st ADE rvw; Tie-ins resolved and stamping completed 01/14: No Tie Required, PE Stamping - With Est to adjust and submit; 2nd sub set for 1/24 11/19: Push 1 month - ADE Resourcing 11/05: Tie-in "out of scope" 2ph/3ph?? 10/22: PUSH 1 month - ADE Resourcing 10/15: ADE to be assigned - holding for 2020 priority list 9/24 - 10/08: ADE to be assigned 9/20: PIKE Submitted for 1st ADE rvw 9/17: On track 9/10: Swap 1st submittal with 3.2 8/27 - 9/03: On track 8/13: PIKE communicated potential pressures on 1st ADE submittal target, due to computer limitations and technical issues (Highlights: Token malfunctions; SAP Access issues) - working through isssues with TSC on case by case basis 7/23 - 8/6: On Track for 9/13 7/19: Vendor Provided 1st ADE Sub dates 7/16: Vendor Request for 1st ADE Submittal 7/15: Sub Order issued [Version 8] | PIKE |  |  | 2020 - Q1- M3 [R138] | COMPLETED | No | Obsolete (CONS+) | 0 | 0 |  | Yes | [5 empty] | Full |  |  | Full |  |  | CIF Submitted 11/27/19 | Full |  | Yes | 2020-12-31 |  | Project is complete, waiting for GC to submit As-buillts | 2020-07-10 | y | 2020-05-01 |  |  | 14 Units remaining - Started | [6 empty] | 0 | 0 | 11320 | 2.1439 | 2.1439 | 0 | 2.0127 | 0 | 2.1231 | 0.11042 | 0.13125 | 2.0127 |  | Keep | 2020-04-13 | Yes | N/A | 2020-06-02 | 2020-07-23 | 2020-11-20 |  |  | 2020-11-20 |  | Yes | Shovel Ready | 3793181.4 | 2503173.2 | -387334 | 5062019 | 1268837.6 | 3760212.2 | 65.99% | 3669.6 | 29299.6 | 32969.2 | 0 | 1167557.8177 | 64 | [9 empty] | Nevada City | Nevada | 0 | 0 | E.5015567.03 |  |  | 2020-138 | 2020 | Q3 | 2020-03-31 | 2020-06-01 | 2020-07-08 |  | Y | BRUNSWICK 110350070 | 7 | NEVADA COUNTY | Yes
35115149 |  | 2020 | 220 Mile Plan | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.4 |  | CLSD | 9091 | 0 | 6692 | 6692 | 1.2674 | 6692 | 1.2674 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | SH | 2020-03-06 | 2019-11-30 | 2019-11-25 | 2019-11-30 |  |  | Yes | 2019-11-27 | 02/04: Engineer communicated no change to design. Reduction in design.01/28: Back to Est/Needing additional EST - Scope changes reroute driven by Customer, move to end of property vs. through. (New PM)01/06: Land feedback - existing line through property - Owner requesting line move to edge of property.11/25: SAP Export - UNSC11/19: Rcv'd clarification - Stay with original; EST Bandwith - working [REDACTED]; [REDACTED] prioritize (EOW)11/12: Pending ADE clarification - tie in; inconsistent with scope: [REDACTED] assisting on followup for clarification on how to proceed - contacted [REDACTED] Last week 11/05: Working through implementation/scheduling10/29: At Risk for push - Last minute reroute - PIKE/[REDACTED] to take offline to discusss implementing reroute and schedule impacts10/22: On Track (10/31)10/15: A] Minor corrections (original scope) on track B] CMCS feedback (new information/scope change): Tie-in needing to be 3-wire.10/11: 1st ADE corrections rtn to contractor10/09: PIKE submitted for 1st ADE rvw10/08 <-9/03: On Track8/27 <-- 8/20: 1st Submittal push 2wks - Priorities (Bruns PH1 & Pole Req)/Equip-Resource Availabilities7/23 - 8/6: On Track for 9/277/19: Vendor Provided 1st ADE Sub dates7/16: Vendor Request for 1st ADE Submittal7/15: Sub Order issued[Version 8] | PIKE |  |  | Unassigned | COMPLETED | No | Obsolete (CONS+) | 0 | 0 |  | Yes | [5 empty] | Full |  |  | Full |  |  | Easements are no longer needed, project was re-designed to avoid new easements, 2 easements needed. Docs sent to acquisition on 1/13. - Looking at redesign to avoid an easement | Full |  | Yes |  |  | Drawings submitted 1/7/2020 | 1980-01-01 | Y | [10 empty] | 0 | 0 | 6692 | 1.2674 | 1.2674 | 0 | 1.2674 | 0 | 1.2674 | 0 | 0 | 1.2674 |  | Keep | 2020-03-06 | Yes | N/A | 2020-04-21 | 2020-06-08 | 2020-06-08 |  |  | 2020-06-08 |  | Yes | Shovel Ready |  |  | -213318 | [9 empty] | 46 | [9 empty] | Nevada City | Nevada | 0 | 0 | E.5015567.04 |  |  | 2020-138 | 2020 | Q2 | 2019-11-27 | 2020-08-08 | 2020-09-14 |  | Y | BRUNSWICK 110350070 | 7 | NEVADA COUNTY | Yes
35115150 |  | 2020 | 220 Mile Plan | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.5 |  | FICL | 6046 | 0 | 6241 | 6241 | 1.182 | 6241 | 1.182 | 0 | 0 | 0 | 0 | 1.7225e-16 |  |  | SI | 08W | SH | 2020-06-26 | 2020-06-01 | 2020-06-01 | 2020-06-01 | 2020-02-01 | 2020-02-01 | Yes | 2020-06-01 | 06/01: APPROVED - INTO PEND05/29: Est Routed in EES05/26: Completing stamping; Target (5/29)05/19: On Track05/05: Completing Construction adjust to alternate PM; Target sub to (5/20); apply corrections and stampgin04/28: EST sub target (5/08)04/27: ADE rtn 2nd corrections to CO04/15: ADE reassigned [REDACTED]04/14: [REDACTED]; back on PSPS; Review for reassignment (rvw may need to be restarted)03/31: [REDACTED] (out sick); following up with status update03/24: PSPS wrapping up - [REDACTED] to rtn to 08W03/17 - 02/25: push[2] ADE Status/Target date?? ([REDACTED] on PSPS)03/09: EST - has been updated to reflect the design changes and additions asked for by [REDACTED] (added locations)02/11: ADE Status??02/01: PIKE submitted for 2nd ADE rvw - [Prelim DWG ready]01/28: On Track01/08: ADE rtn 1st Corrections to contractor12/06: ADE assigned [REDACTED]11/19 & 10/22: PUSH 1 month (NOV, DEC) - ADE Resourcing10/15: ADE to be assigned - holding for 2020 priority list10/11: PIKE submitted for 1st ADE rvw9/03 - 10/08: On Track8/20 - 8/27: 1st Submittal push 2wks - Priorities/Equip-Resource Availabilities7/23 - 8/6: On Track for 9/277/19: Vendor Provided 1st ADE Sub dates7/16: Vendor Request for 1st ADE Submittal7/15: Sub Order issued[Version 8] | PIKE |  |  | 2020 - Q1- M3 [R138] | COMPLETED | No | Obsolete (CONS+) | 0 | 0 |  | Yes | [5 empty] | Full |  |  | Full |  |  | ERTC Call 1/10/2020 | Full |  | Yes |  |  | Drawing submitted 1/7/2020 | 2020-07-13 | y | 2020-06-08 |  |  | 13 Units remaining - Starting 6/24/20 | [6 empty] | 0 | 0 | 6241 | 1.182 | 1.182 | 0 | 1.182 | 0 | 1.2155 | 0.033523 | 1.7225e-16 | 1.182 |  | Keep | 2020-06-26 | Yes | N/A | 2020-06-29 | 2020-08-25 | 2020-08-25 |  |  | 2020-08-25 |  | Yes | Shovel Ready | 3214155.4 | 2836266.3 | -266072 | 4212019 | 997863.6 | 3211415.1 | 88.24% | 2740.3 | 0 | 2740.3 | 0 | 2399533.0979 | 31 | [9 empty] | Nevada City | Nevada | 0 | 0 | E.5015567.05 |  |  | 2020-138 | 2020 | Q3 | 2020-03-31 | 2020-06-01 | 2020-07-08 |  | Y | BRUNSWICK 110350070 | 7 | NEVADA COUNTY | Yes
35115156 |  | 2020 | 220 Mile Plan | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.3 |  | FICL | 11386 | 0 | 10035 | 10035 | 1.9006 | 10035 | 1.9006 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | SH | 2020-03-24 | 2020-01-15 | 2020-06-09 | 2020-01-15 | 2019-11-20 | 2019-11-20 | Yes | 2020-01-15 | 01/14: Finalizing Approval (APPR)01/07: ADE Status??12/30: PIKE submitted for 4th ADE rvw (rerouted for EES)12/19: ADE submitted further corrections to contractor (OCALCs)12/17: Planning Eng and ADE disconnect - tie in not being implemented. EST Routed Yesterday. EOD at Risk12/5: ADE submitted further corrections to contractor (tie in changes/design change)11/21: Routed per EST11/19: EST finalizing corrects - ADE directed to route upon completion11/15: ADE rtn corrections to contractor11/12: Recv'd Land feedback, pending ADE rvw/input11/05: New Target? easments for back ties needed from land dept10/30: Per ADE - 1] [REDACTED] handles permitting; 2] need to verify with land dept easements for back tie, before we can finalize estimate.Contact Project Manager10/28: Correction Ready pending ADE response - Est. checking with ADE on who handles permitting (Job Owner)10/22: Est. tied up on another project for submittal10/15 <-- 10/08: 2nd rvw submittal - target mid next week (10/18)10/03: ADE returned 1st corrections to contractor9/12: ADE assigned [REDACTED]8/27: PIKE submitted for 1st ADE Rvw8/20: Push 1 wk8/13: PIKE communicated potential push of 1st ADE submittal into early following week. due to computer technical impacts: (IE: Token malfunctions; SAP Access issues) - working through isssues with TSC on case by case basis - may push submittal into early following week.7/23 - 8/6: On Track for 8/167/19: Vendor Provided 1st ADE Sub dates7/16: Vendor Request for 1st ADE Submittal7/15: Sub Order issued[Version 8] | PIKE |  |  | 2020 - Q1 | COMPLETED | No | Obsolete (CONS+) | 0 | 0 |  | Yes | [5 empty] | Full |  |  | Full |  |  | ERTC Call 1/10/2020 | Full |  | Yes |  |  |  | 1980-01-01 | Y | [10 empty] | 0 | 0 | 10035 | 1.9006 | 1.9006 | 0 | 1.9006 | 0 | 1.9006 | 0 | 0 | 1.9006 |  | Keep | 2020-03-24 | Yes | N/A | 2020-04-01 | 2020-06-03 | 2020-07-03 |  |  | 2020-07-03 |  | Yes | Shovel Ready | 4488676.2 | 2159062.4 | -174482 | 1357699.57 | -3130976.63 | 4197988 | 48.1% | 290688.2 | 0 | 290688.2 | 0 | 1136008.916 | 57 | [6 empty] | No SCADA |  |  | Nevada City | Nevada | 0 | 0 | E.5015569.02 |  |  | 2020-136 | 2020 | Q1 | 2020-01-15 | 2020-05-01 | 2020-06-12 |  | Y | BRUNSWICK 110350070 | 7 | NEVADA COUNTY | Yes
35115157 |  | 2020 | 220 Mile Plan | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.4 |  | FICL | 15728 | 0 | 10454.4 | 10454.4 | 1.98 | 10454.4 | 1.98 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | SH | 2020-01-15 | 2019-11-30 | 2019-11-14 | 2019-11-30 |  |  | Yes | 2019-11-14 | 01/06: CNCS conflicts - had to amend and was resubmitted11/12: Waiting for JO Cost [REDACTED]11/05: Status? Routed?10/29: CMCS approval provided 10/19; Sealing OCALCs - Routing Targeted 10/3010/21: ADE Approved for routing10/21: PIKE submitted for 4th ADE rvw10/15: PIKE to provide communication to [REDACTED], regarding changes - PGE followup on clarity of how CMCS's are to be conducted.10/14: 3rd ADE corrections Rtn to contractor (Minor-missing the circuitry within the CMCS)10/14: PIKE submitted for 3rd ADE rvw10/14: 2nd ADE corrections Rtn to contractor10/14: PIKE submitted for 2nd ADE rvw10/08- 2nd submittal target for Friday9/24 - 10/01: Correction in progress9/16: ADE returned 1st corrections to contractor9/13: ADE assigned [REDACTED]9/10: Pending ADE assignment (Reviewing Resource loading) - Target dates subject to push8/27: PIKE submitted for 1st ADE Rvw8/20: Push 1 wk8/13: PIKE communicated potential push of 1st ADE submittal into early following week. due to computer technical impacts: (IE: Token malfunctions; SAP Access issues) - working through isssues with TSC on case by case basis - may push submittal into early following week.8/13: Confirmed date swaps - moved to 8/16 Target.7/23 - 8/6: On Target (CO Reviewing a possible date swap with PH 1.2 or 1.3), per discussion with [REDACTED].7/19: Vendor Provided 1st ADE Sub dates7/16: Vendor Request for 1st ADE Submittal7/15: Sub Order issuedVersion 8] | PIKE |  |  | Normal | COMPLETED | No | Obsolete (CONS+) | 0 | 0 |  | Yes | [5 empty] | Full |  |  | Full |  |  | ERTC Call 1/10/2020 | Full |  | Yes | 2020-05-30 |  | Project complete | 1980-01-01 | Y |  |  |  | Started | [6 empty] | 0 | 0 | 10454.4 | 1.98 | 1.98 | 0 | 1.9803 | 0 | 1.9803 | 0 | -0.00030303 | 1.9803 |  | Keep | 2020-01-15 | Yes | N/A | 2020-02-18 08:00 | 2020-06-03 | 2020-09-30 |  |  | 2020-09-30 |  | Yes | Shovel Ready | 4249051.4 | 5193354.5 | -314994 | 1580553.38 | -2668498.02 | 4247066.4 | 122.2% | 1985 | 0 | 1985 | 0 | 2622906.3131 | 79 | [6 empty] | No SCADA |  |  | Nevada City | Nevada | 0 | 0 | E.5015569.04 |  |  | 2020-136 | 2020 | Q1 | 2019-11-14 | 2020-02-17 | 2020-04-15 |  | Y | BRUNSWICK 110350070 | 7 | NEVADA COUNTY | Yes
35115158 |  | 2020 | 220 Mile Plan | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.5 |  | CLSD | 13177 | 0 | 11332 | 11332 | 2.1462 | 11332 | 2.1462 | 0 | 0 | 0 | 0 | -3.4451e-16 |  |  | SI | 08W | SH | 2020-03-06 | 2019-11-30 | 2020-05-22 | 2019-11-30 |  |  | Yes | 2019-11-14 | 03/03: EST target EOD today for feedback03/02: 1.5 is already in PEND and EES is locked so I would suggest an update to the CMCS/Construction Drawings eliminating the recloser and updating O'calc for the impacted pole03/02: The updated are being finalized and will be completed by EOD for 1.5 tomorrow. The G&W Viper recloser has been moved to PH 1.1. The changes for 1.5 will be download into SAP after updating O'calc, Map, CMCS with removing the recloser information from all files/saving/ combining and uploading. 11/12: Waiting for JO Cost [REDACTED]11/05: Status? Routed?10/29: FInal uploads; Sealing OCALCs; to be routed by 11/0110/21: ADE approved for routing10/21: PIKE submitted for 3rd ADE rvw10/21: ADE 2nd corrections rtn to contractor10/21: PIKE submitted for 2nd ADE rvw10/15: PIKE to provide communication to [REDACTED], regarding changes - PGE followup on clarity of how CMCS's are to be conducted.10/08: 2nd submittal targeted for next Friday9/30: Rejected - Rtn To contractor (Rejected) - Access to uploaded doc issues (EES)9/20: Pike Submitted for 1st ADE rvw8/27 - 9/17: On track8/20: 1st Submittal push 2wks - Priorities/Equip-Resource Availabilities7/23 - 8/6: On Track for 9/67/19: Vendor Provided 1st ADE Sub dates7/16: Vendor Request for 1st ADE Submittal7/15: Sub Order issued[Version 8] | PIKE |  |  | Normal | COMPLETED | No | Obsolete (CONS+) | 0 | 0 |  | Yes | [5 empty] | Full |  |  | Full |  |  | ERTC Call 1/10/2020 | Full |  | Yes |  |  |  | 1980-01-01 | Y |  |  |  | Started | [6 empty] | 0 | 0 | 11332 | 2.1462 | 2.1462 | 0 | 2.1462 | 0 | 2.1462 | 0 | -3.4451e-16 | 2.1462 |  | Keep | 2020-03-06 | Yes | N/A | 2020-03-09 08:00 | 2020-07-16 | 2020-07-16 |  |  | 2020-07-16 |  | Yes | Shovel Ready |  |  | -233648 | [9 empty] | 66 | [6 empty] | SCADA |  |  | Nevada City | Nevada | 0 | 0 | E.5015569.05 |  |  | 2020-136 | 2020 | Q1 | 2019-11-14 | 2020-04-01 | 2020-05-29 |  | Y | BRUNSWICK 110350070 | 7 | NEVADA COUNTY | Yes
35116390 |  | 2020 | 220 Mile Plan | CWSP - MIWUK 1701 - LR 8060 - PH 1.7 |  | CONS | 5100 | 0 | 4715 | 4715 | 0.89299 | 4715 | 0.89299 | 0 | 0 | 0 | 0 | 0 |  |  | YO | 08W | SH | 2020-09-01 | 2020-01-15 | 2020-01-10 | 2020-01-15 | 2019-12-23 | 2019-12-23 | Yes | 2020-01-10 | 01/08: Routed today12/30: add all updated docs & stamping, ADE approved for routing12/23: EEI submitted for 2nd rvw - [PRELIM DWG ready]12/18: Est set target 2nd sub 12/2012/13: ADE rtn 1st corrections to contractor12/11 - 11/27: ADE priority/workload11/20: Composite Pole change (2 pols/ 1hr)11/19: ADE assigned [REDACTED]11/18: EEI submitted for 1st ADE rvw11/06: Waiting to field - Veg clearing and PSPS impact10/29: PSPS impact to fielding10/23: In accessible locations - working through fielding on 2 locations - Push 1wk10/16: On track 1st sub for 10/14 (EOW)10/09: Push - 1wk; Impacted by numerous scope updates to previously approved key unit jobs.10/02: EEI 1st submittal target update to 10/079/04: EEI to supply new target dates (push) | EEI |  |  | Priority Q2 | COMPLETED | No | Wood | 29 | 2 |  | Yes |  |  |  | 2020-04-09 | 2020-04-09 | Full | 2020-09-01 | 2020-09-01 | Full |  |  | Full ERTC issued 9/1 ** Caltrans Dist. 10 delay to 9/11/20. | Full |  | Yes | 2021-01-09 |  |  | 2020-09-04 | Y | 2020-08-11 | 2020-08-11 |  | Veg complete, Pending post inspect. | [6 empty] | 0 | 0 | 4752 | 0.9 | 0.9 | -0.0070076 | 0.9036 | 0 | 0.95606 | 0.052462 | -0.0035985 | 0.9036 |  | Keep | 2020-07-09 | Yes | COMP | 2020-10-05 08:00 | 2020-10-12 17:00 | 2020-10-12 17:00 |  |  |  | 2020-08-03 | Yes | Shovel Ready | 1195542 | 1699887.9 |  | 1195542 | 0 | 1008134.7 | 142.2% | 29384.9 | 158022.4 | 187407.3 | 0 | 1903586.0259 | 26 |  | ADE Bandwidth | [7 empty] | Twain Harte | Tuolumne | 0 | 0 | E.5014733.07 - JM | TL |  | 2020-022 | 2020 | Q3 | 2020-01-10 | 2020-04-24 | 2020-06-07 |  | Y | MIWUK 17018060 | 12 | TUOLUMNE COUNTY | Yes
35116393 |  | 2020 | 220 Mile Plan | CWSP - MIWUK 1702 - OCB - PH 1.3 |  | FICL | 13485 | 0 | 13572 | 13572 | 2.5705 | 13572 | 2.5705 | 0 | 0 | 0 | 0 | 0 |  |  | YO | 08W | SH | 2019-11-21 | 2019-10-31 | 2019-11-21 | 2019-10-31 |  |  | Yes | 2019-10-04 | 01/09: QUES submitted Temp pole information01/03: PM back into redesign - minimize number of shutdowns to customers. New temp pole add and a back-tie.11/15: ADE in approval of redesign11/14: Land redesign; waiting for stamping10/07: IN PEND10/03: QUES submitted for 2nd ADE rvw - APPROVED for routing by ADE10/02: ADE 1st rvw corrections rtn to contractor9/30 ADE assigned [REDACTED]9/27: QUES submitted for 1st ADE rvw9/25: On Track 1st ADE submittal 9/30Potential Pole Composite Standard Impact - Can remain wood; Some already converted - confirming with ADE whether to convert back or remain as is | QUES |  |  | Priority B | COMPLETED | No | Obsolete (CONS+) | 0 | 0 |  | Yes | [5 empty] | Full |  |  | Full |  |  |  | Full |  | Yes |  |  | [REDACTED] to follow up with [REDACTED] | 1980-01-01 | Y | [10 empty] | 0 | 0 | 13572 | 2.5705 | 2.5705 | 0 | 2.5705 | 0 | 2.5705 | 0 | 0 | 2.5705 |  | Keep | 2019-11-21 | Yes | N/A | 2020-01-06 | 2020-03-20 | 2020-03-20 |  |  | 2020-03-20 |  | Yes | Shovel Ready | 4302368 | 2957780.8 |  | 4302367 | -1 | 3491941.4 | 68.74% | 810426.6 | 0 | 810426.6 | -407188 | 1150683.954 | 94 |  | Veg Started | [7 empty] | Twain Harte | Tuolumne | 38.0498 | -120.2241 | E.5014773.03 - JM |  |  | 2020-046 | 2020 | Q1 | 2019-10-04 | 2020-01-25 | 2020-03-25 |  | Y | MIWUK 1702CB | 25 | TUOLUMNE COUNTY | Yes
35116394 |  | 2020 | 220 Mile Plan | CWSP - MIWUK 1702 - OCB - PH 1.4 |  | FICL | 8790 | 0 | 8858 | 8858 | 1.6777 | 8858 | 1.6777 | 0 | 0 | 0 | 0 | 0 |  |  | YO | 08W | SH | 2020-03-17 | 2020-02-19 | 2020-02-19 | 2020-02-19 | 2019-11-26 | 2019-11-26 | Yes | 2020-02-19 | 02/19: IN PEND02/19: Per [REDACTED] - to be notified of final resolution confirmation, expecting shortly - ready to approve02/05: QUES submitted for 4th ADE for review (new design)1/23: Per [REDACTED] (EES TEAM) needs to hold until [REDACTED] gives us the all clear the 252 Planning Orders RCC 15932 being changed to the correct RCC's.1/22: Land approved new design, refield completed last week - 01/08: Customer Hold/Review - VEG mgmnt to pull out Tree/Pole relocation01/06: ADE rtn corrections - ready to route12/16: QUES submitted for 3rd ADE rvw12/11: ADE rtn 2nd correction to contractor12/04: Rvw in progress11/26: QUES submitted for 2nd ADE rvw11/20: New submittal target date?11/13: Corrections Ready - Held for scheduled Construcability mtg impact - to advise on new submittal date11/13: ADE retruned 1st corrections to contractor10/31: ADE assigned to [REDACTED] C10/30: Push 1mth - ADE availabilities10/23 <-- 10/16: ADE to be assigned (waiting for priority list) - push for assignment10/09: Stamps submitted - ready for ADE assignment10/02: ADE to be assigned - "waiting for PE stamping" --> QUES reported stamping complete; Estimator to send update email9/27: QUES submitted for 1st ADE rvw (waiting for PE stamping)*9/25: On Track 1st ADE submittal 9/25Potential Pole Composite Standard Impact - Can remain wood; Some already converted - confirming with ADE whether to convert back or remain as is | QUES |  |  | 2020 - Q2- M4 [R47] | COMPLETED |  | Obsolete (CONS+) | 0 | 0 |  | Yes | [5 empty] | Full |  |  | Full |  |  | CIF submitted 9/29 | Full |  | Yes |  |  | Submitted on 12/26 | 1980-01-01 | Y | [10 empty] | 0 | 0 | 8858 | 1.6777 | 1.6777 | -4.8231e-15 | 1.6777 | 0 | 1.6777 | 0 | 4.8231e-15 | 1.6777 |  | Keep | 2020-03-17 | Yes | N/A | 2020-03-24 | 2020-05-01 | 2020-05-01 |  |  | 2020-06-23 |  | Yes | Shovel Ready | 1990074.8 | 1199916 |  | 2102204 | 112129.2 | 1859250.3 | 60.29% | 130824.5 | 0 | 130824.5 | 0 | 715235.5475 | 44 |  | Veg Started | [7 empty] | Twain Harte | Tuolumne | 38.0531 | -120.237 | E.5014773.04 - JM |  |  | 2020-047 | 2020 | Q2 | 2020-04-30 | 2020-04-30 | 2020-06-07 |  | Y | MIWUK 1702CB | 25 | TUOLUMNE COUNTY | Yes
35116802 |  | 2020 | 220 Mile Plan | CWSP-MIWUK 1702-LR 6018-PHASE 1.4 |  | DOCC | 10855 | 0 | 12725 | 12725 | 2.41 | 12725 | 2.41 | 0 | 0 | 0 | 0 | 0 |  |  | YO | 08W | SH | 2020-05-01 | 2020-02-20 | 2020-02-20 | 2020-02-20 | 2020-02-12 | 2020-02-12 | Yes | 2020-02-20 | 02/19: ADE concurring job - issues clearing the FAA screen - sent a Ticket for assistance02/13: ADE rtn 2nd corrections to CO; minor items02/12: EEI submitted for 2nd ADE rvw - [PRELIM DWG ready]02/10: ADE rtn 1st corrections to CO01/27: ADE assigned [REDACTED]01/15 <-- 01/08: ADE to be assigned1/03: EEI submitted for 1st ADE rvw12/18: EST Priority shifts11/20: Push to 12/23 - Composite Pole Impact (40 pols/40 hrs)11/13: On Track11/06: Pushe - PSPS/Fielding impact10/29 <-- 10/16: On track 1st sub for 11/2810/09: Push 1wk; Impacted by numerous scope updates to previously approved key unit jobs.10/02 <-- 9/11: On Track09/04: On Track for 1st Submittal 11/12 | EEI |  |  | 2020 - Q2- M5 [R41] | COMPLETED |  | Obsolete (CONS+) | 0 | 0 |  | Yes | [5 empty] | Full | 2020-04-09 | 2020-04-09 | Full |  |  |  | Full |  | Yes |  |  | RP56 cleared 3/31 | 2020-06-19 | Y | 2020-05-01 |  |  | Veg confirmed TT 100% complete (6/29) | [6 empty] | 0 | 0 | 12725 | 2.41 | 2.41 | 0 | 2.4061 | 0 | 2.4131 | 0.0070076 | 0.0039773 | 2.4061 |  | Keep | 2020-04-15 | Yes | NOTN | 2020-06-16 | 2020-09-17 | 2020-09-17 |  |  | 2020-12-15 |  | Yes | Shovel Ready | 2559279.3 | 3461896.9 |  | 2559279 | -0.3 | 2496409.8 | 135.3% | 331.3 | 62538.2 | 62869.5 | 0 | 1436449.1656 | 86 | [9 empty] | Twain Harte | Tuolumne | 38.0441 | -120.2479 | E.5014730.04 - JM |  |  | 2020-041 | 2020 | Q2 | 2020-05-31 | 2020-08-14 | 2020-09-27 |  | Y | MIWUK 17026018 | 23 | TUOLUMNE COUNTY | Yes
35116804 |  | 2020 | 220 Mile Plan | CWSP-MIWUK 1702-LR 6018-PHASE 1.6 |  | FICL | 5340 | 0 | 5415 | 5415 | 1.0256 | 5415 | 1.0256 | 0 | 0 | 0 | 0 | 0 |  |  | YO | 08W | SH | 2020-05-01 | 2020-04-23 | 2020-04-23 | 2020-04-23 | 2020-01-02 | 2020-01-02 | Yes | 2020-04-23 | 04/23: APPROVED - INTO PEND04/22: Final approval corrections rtn to CO04/21: Routed with associated changes04/20: ADE/EST coordinated on resolution04/17: Routing issues04/15: ADE to advise should be done - EST should be routing04/08: On Track ***no records of activities 2.3 to3.3; Dates applied per EEI update list04/01: ADE rtn 2nd corrections to CO03/25: ADE Status??02/19: Need EST status02/19: ADE update - need to send full pkg (2nd sub); waiting on the planner to review (previous planner has retired and the new one said he will be reviewing all the Miwuk phases )02/07: EEI submitted for 3rd ADE rvw - Incomplete/Partial02/05: Received feed back, EST applying corrections01/29: EST/ADE/JO - coordinating corrections; EEI to firm up submittal target01/22: EST/ADE coordination on corrections01/14: ADE rtn 2nd corrections to CO (pt2) - coordination with EST01/08: Est Target 1/1701/06: ADE rtn 2nd corrections to contractor - attached a document that's attached to sap, it's from planning. only reviewed what I've attached so far, I wanted to get this info to you quickly in case you hadn't heard from the planner.1/03: EEI submitted for 2nd ADE rvw - [PRELIM DWG ready]12/16: ADE rtn 1st corrections to contractor12/11: Pushed 2 wk; ADE status?11/21: ADE assigned [REDACTED]11/20 <-- 11/06: ADE to be assigned11/01: EEI submitted for 1st ADE rvw10/29 <-- 10/16: On track 1st sub for 10/1810/09: Push 1wk; Impacted by numerous scope updates to previously approved key unit jobs.10/02 <-- 9/11: On Track09/04: On Track for 1st Submittal 11/12 | EEI |  |  | 2020 - Q1- M3 [R43] | COMPLETED |  | Obsolete (CONS+) | 0 | 0 |  | Yes | [5 empty] | Full |  |  | Full |  |  |  | Full |  | Yes |  |  |  | 2020-05-26 | Y | 2020-05-01 |  |  | 100% complete | [6 empty] | 0 | 0 | 5415 | 1.0256 | 1.0256 | 0 | 1.0256 | 0 | 1.0256 | 0 | 0 | 1.0256 |  | Keep | 2020-04-20 | Yes | N/A | 2020-06-23 | 2020-08-19 | 2020-08-19 |  |  | 2020-08-22 |  | Yes | Shovel Ready | 1868186.8 | 1992154.5 |  | 1868187 | 0.2 | 1866536.7 | 106.6% | 1650.1 | 0 | 1650.1 | 0 | 1942488.5983 | 39 | [9 empty] | Twain Harte | Tuolumne | 38.0441 | -120.2479 | E.5014730.06 - JM |  |  | 2020-043 | 2020 | Q3 | 2020-03-31 | 2020-03-30 | 2020-04-28 |  | Y | MIWUK 17026018 | 23 | TUOLUMNE COUNTY | Yes
35116861 |  | 2020 |  | BUCOCAMPT 546 HILLCREST DR PARADISE*ILB |  | DOCC |  | 0 | 1089 | 1089 | 0.20625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 95F | [51 empty] | 1089 | 0.20625 | 0 | 0 | 0.20625 | 0 | 0.050189 | 0 | 0.050189 | 0 | 0.15606 | 0.050189 |  |  |  |  | N/A | [5 empty] | 2019-10-14 | [27 empty] | 39.7469 | -121.629 |  |  |  |  | 2019 | [8 empty] | BUTTE COUNTY | Yes
35116863 |  | 2020 |  | BUCOCAMPT 5721 BONNIE LN PARADISE*ILB |  | FICL |  | 0 | 540 | 540 | 0.10227 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 95F | [51 empty] | 540 | 0.10227 | 0 | 0 | 0.10227 | 0 | 0.10227 | 0 | 0.10227 | 0 | 0 | 0.10227 |  |  |  |  | N/A | [5 empty] | 2019-11-16 |  |  |  | 0 | 56619 |  | 35823.57 | 35823.57 | -56619 |  | 56619 | 0 | 56619 | 0 | 553608 | [12 empty] | 39.7558 | -121.5948 |  |  |  |  | 2019 | [5 empty] | Y |  |  | BUTTE COUNTY | Yes
35116866 |  | 2020 |  | BUCOCAMPT 5594 SIERRA PARK DR PARADISE |  | DOCC |  | 0 | 265 | 265 | 0.050189 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 95F | [51 empty] | 265 | 0.050189 | 845 | 0.16004 | 0.21023 | -0.16004 | 0.20625 | 0 | 0.20625 | 0 | 0.0039773 | 0.20625 |  |  |  |  | N/A | [5 empty] | 2019-10-18 | [27 empty] | 39.7484 | -121.6256 |  |  |  |  | 2019 | [8 empty] | BUTTE COUNTY | Yes
35117031 |  | 2020 |  | BUCOCAMPT 1710 RYAN RD PARADISE* |  | FICL |  | 0 | 568 | 568 | 0.10758 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 95F | [51 empty] | 568 | 0.10758 | 0 | 0 | 0.10758 | 0 | 0.09678 | 0 | 0.09678 | 0 | 0.010795 | 0.09678 |  |  |  |  | N/A | [5 empty] | 2019-10-21 |  |  |  | 0 | 92333.5 |  | 45011.42 | 45011.42 | -92333.5 |  | 92333.5 | 0 | 92333.5 | 0 | 858311.4085 | [12 empty] | 39.7632 | -121.582 |  |  |  |  | 2019 | [5 empty] | Y |  |  | BUTTE COUNTY | Yes
35117121 |  | 2020 |  | BUCOCAMPT 5765 DEANNA WAY PARADISE |  | FICL |  | 0 | 1140 | 1140 | 0.21591 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 95F | [51 empty] | 1140 | 0.21591 | 0 | 0 | 0.21591 | 0 | 0.031629 | 0 | 0.031629 | 0 | 0.18428 | 0.031629 |  |  |  |  | N/A | [5 empty] | 2019-09-13 |  |  |  | 0 | 17602.4 |  | 20766.73 | 20766.73 | -17602.4 |  | 17602.4 | 0 | 17602.4 | 0 | 81526.9053 | [12 empty] | 39.7558 | -121.592 |  |  |  |  | 2019 | [5 empty] | Y |  |  | BUTTE COUNTY | Yes
35117126 |  | 2020 |  | BUCOCAMPT 7070 PENTZ RD PARADISE |  | DOCC |  | 0 | 980 | 980 | 0.18561 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 95F | [51 empty] | 980 | 0.18561 | 0 | 0 | 0.18561 | 0 | 0.037879 | 0 | 0.037879 | 0 | 0.14773 | 0.037879 |  |  |  |  | N/A | [5 empty] | 2019-09-16 | [27 empty] | 39.7914 | -121.5797 |  |  |  |  | 2019 | [8 empty] | BUTTE COUNTY | Yes
35117128 |  | 2020 |  | BUCOCAMPT 627 SCOTT DR PARADISE* |  | CLSD |  | 0 | 536 | 536 | 0.10152 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 95F | [51 empty] | 536 | 0.10152 | 0 | 0 | 0.10152 | 0 | 0.073295 | 0 | 0.073295 | 0 | 0.02822 | 0.073295 |  |  |  |  | N/A | [5 empty] | 2019-10-16 |  |  |  | 0 | 47816.7 |  | 29613.91 | 29613.91 | -47816.7 |  | 47816.7 | 0 | 47816.7 | 0 | 471030.1791 | [12 empty] | 39.7481 | -121.6266 |  |  |  |  | 2019 | [5 empty] | Y |  |  | BUTTE COUNTY | Yes
35117130 |  | 2020 |  | BUCOCAMPT 1659 NELSON LN PARADISE*ILB |  | FICL |  | 0 | 682 | 682 | 0.12917 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 95F | [51 empty] | 682 | 0.12917 | 0 | 0 | 0.12917 | 0 | 0.035038 | 0 | 0.035038 | 0 | 0.094129 | 0.035038 |  |  |  |  | N/A | [5 empty] | 2019-11-03 |  |  |  | 0 | 72404.5 |  | 48785.69 | 48785.69 | -72404.5 |  | 72404.5 | 0 | 72404.5 | 0 | 560550.9677 | [12 empty] | 39.7638 | -121.582 |  |  |  |  | 2019 | [5 empty] | Y |  |  | BUTTE COUNTY | Yes
35117218 |  | 2020 |  | BUCOCAMPT 840 CENTRAL PARK DR PRDSE*ILB |  | CLSD |  | 0 | 700 | 700 | 0.13258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 95F | [51 empty] | 700 | 0.13258 | 106 | 0.020076 | 0.15265 | -0.020076 | 0.14848 | 0 | 0.14848 | 0 | 0.0041667 | 0.14848 |  |  |  |  | N/A | [5 empty] | 2019-11-03 |  |  |  | 0 | 100141 |  | 55272.31 | 55272.31 | -100141 |  | 100141 | 0 | 100141 | 0 | 755349.2571 | [12 empty] | 39.7659 | -121.6094 |  |  |  |  | 2019 | [5 empty] | Y |  |  | BUTTE COUNTY | Yes
35117219 |  | 2020 |  | BUCOCAMPT 4239 SCHWYHART LN OROVILLE |  | DOCC |  | 0 | 463 | 463 | 0.087689 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 95F | [51 empty] | 463 | 0.087689 | 634 | 0.12008 | 0.20777 | -0.12008 | 0.21402 | 0 | 0.21402 | 0 | -0.00625 | 0.21402 |  |  |  |  | N/A | [5 empty] | 2019-11-19 |  |  |  | 0 | 119387.1 |  | 74772.4 | 74772.4 | -119387.1 |  | 119387.1 | 0 | 119387.1 | 0 | 1361477.0799 | [12 empty] | 39.7908 | -121.4981 |  |  |  |  | 2019 | [5 empty] | Y |  |  | BUTTE COUNTY | Yes
35117381 |  | 2020 |  | BUCOCAMPT 2459 HONEY RUN RD CHICO |  | CLSD |  | 0 | 525 | 525 | 0.099432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 95F | [51 empty] | 525 | 0.099432 | 0 | 0 | 0.099432 | 0 | 0.063826 | 0 | 0.063826 | 0 | 0.035606 | 0.063826 |  |  |  |  | N/A | [5 empty] | 2019-09-26 | [27 empty] | 39.7422 | -121.6763 |  |  |  |  | 2019 | [8 empty] | BUTTE COUNTY | Yes
35117406 |  | 2020 |  | BUCOCAMPT 5050 EDEN RD PARADISE |  | FICL |  | 0 | 1095 | 1095 | 0.20739 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 95F | [51 empty] | 1095 | 0.20739 | 0 | 0 | 0.20739 | 0 | 0.074242 | 0 | 0.074242 | 0 | 0.13314 | 0.074242 |  |  |  |  | N/A | [5 empty] | 2019-09-14 | [27 empty] | 39.7331 | -121.6265 |  |  |  |  | 2019 | [8 empty] | BUTTE COUNTY | Yes
35117411 |  | 2020 |  | BUCOCAMPT 1524 FOREST CIR PARADISE* |  | CLSD |  | 0 | 493 | 493 | 0.093371 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 95F | [51 empty] | 493 | 0.093371 | 0 | 0 | 0.093371 | 0 | 0.069318 | 0 | 0.069318 | 0 | 0.024053 | 0.069318 |  |  |  |  | N/A | [5 empty] | 2019-10-15 |  |  |  | 0 | 64791.5 |  | 41580.26 | 41580.26 | -64791.5 |  | 64791.5 | 0 | 64791.5 | 0 | 693913.0223 | [12 empty] | 39.7741 | -121.5871 |  |  |  |  | 2019 | [5 empty] | Y |  |  | BUTTE COUNTY | Yes
35117444 |  | 2020 | 220 Mile Plan | CWSP - VOLTA 1102 LR 1648 PH 2.1 |  | MAPP | 12151 | 0 | 12656 | 12656 | 2.397 | 12656 | 2.397 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 08W | SH | 2020-03-26 | 2019-08-30 | 2019-09-05 | 2019-08-30 |  |  | Yes | 2019-08-30 | 7/9: on track for 7/317/24: PM change from 700-Series [74022391] to 300-Series [35117444]; EES not functioning with 700-Series7/30: On track to submit for 7/318/1: EN submitted for 1st ADE review; ADE TBD8/13 - Request for [REDACTED] to assign ADE8/20: Accessibility issues to documents, resolved - initiating review - EOD pushed 1wk8/21: 1st ADE corrections rtn to contractor8/27: EN routing for approval - today?[PRELIM DWG ready]IN PEND | EN |  |  | Completed | COMPLETED | No |  | 0 | 0 |  | Yes | [5 empty] | Full |  |  | Full |  |  | CIF submitted 8/6/19. Caltrans Annual | Full |  | Yes |  |  | Permit request sent 8/5/19 | 1980-01-01 | Y | [10 empty] | 0 | 0 | 12656 | 2.397 | 2.397 | -3.1006e-15 | 2.397 | 0 | 2.397 | 0 | 3.1006e-15 | 2.397 |  | Keep | 2020-03-26 | Yes | N/A | 2019-12-05 | 2020-04-29 | 2020-04-29 |  |  | 2020-06-11 |  | Yes | Shovel Ready | 4798184.2 | 3862033.2 |  | 6272666 | 1474481.8 | 3535709.8 | 80.48% | 1210655.5 | 51818.9 | 1262474.4 | 0 | 1611214.8622 | 61 |  | 35117444 - new order, old was 74022391 6/27 Long to provide update on 6/28 | [7 empty] | Shingletown | Shasta | 40.5069 | -121.8183 | E.5015533.01 |  |  |  | 2020 | Q1 | 2019-08-30 | 2020-02-17 | 2020-03-23 |  | Y | VOLTA 110253130 | 107 | SHASTA COUNTY | Yes
35118170 |  | 2020 |  | BUCOCAMPT 5732 PACHECO LN PARADISE* |  | FICL |  | 0 | 157 | 157 | 0.029735 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 95F | [51 empty] | 157 | 0.029735 | 0 | 0 | 0.029735 | 0 | 0.031629 | 0 | 0.031629 | 0 | -0.0018939 | 0.031629 |  |  |  |  | N/A | [5 empty] | 2019-10-21 |  |  |  | 0 | 105281.2 |  | 43782.53 | 43782.53 | -105281.2 |  | 105281.2 | 0 | 105281.2 | 0 | 3540667.1083 | [12 empty] | 39.7559 | -121.5981 |  |  |  |  | 2019 | [5 empty] | Y |  |  | BUTTE COUNTY | Yes
35118171 |  | 2020 |  | BUCOCAMPT 528 BARBARA WAY PARADISE* |  | DOCC |  | 0 | 261 | 261 | 0.049432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 95F | [51 empty] | 261 | 0.049432 | 158 | 0.029924 | 0.079356 | -0.029924 | 0.077652 | 0 | 0.077652 | 0 | 0.0017045 | 0.077652 |  |  |  |  | N/A | [5 empty] | 2020-01-24 |  |  |  | 0 | 117893.7 |  | 60434.97 | 60434.97 | -117893.7 |  | 117893.7 | 0 | 117893.7 | 0 | 2384976 | [12 empty] | 39.7555 | -121.6298 |  |  |  |  | 2019 | [5 empty] | Y |  |  | BUTTE COUNTY | Yes
35118663 |  | 2021 |  | BR-01-01-W (E) HEAVENS GATE PARB |  | CONS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 08W |  |  |  | 2020-09-30 | [47 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | COMP | 2020-07-06 | 2020-11-20 17:00 | [7 empty] | 915291 | 1937376.8 |  | 1772954.66 | 857663.66 | 837653.8 | 211.7% | 4747.7 | 72889.5 | 77637.2 | 0 | [11 empty] | Paradise | Butte | 39.7794 | -121.6222 | [10 empty] | Y |  |  | BUTTE COUNTY | Yes
35119401 |  | 2020 | 220 Mile Plan | CWSP - CAMP EVERS 2106 - 5020 - PHASE 2 |  | FICL | 5642 | 0 | 5702 | 5702 | 1.0799 | 5702.4 | 1.08 | 0 | 0 | 0 | 0 | -7.5758e-05 |  |  | CC | 08W | SH | 2020-04-06 | 2019-12-31 | 2019-12-04 | 2019-12-31 |  |  | Yes | 2019-12-04 | 03/31: will require the re-design of 4 pole units 12/04: INTO PEND12/04: Routed pending final approval11/27: ADE advised Ready to route for approval11/25: Final Corrections communicated to ADE11/22: ADE advised ready for approval11/20: Composite Pole change impact - dates to be adjusted11/13: ADE returned 2nd corrections to contractor; 3rd submittal target 11/1411/06: ADE out sick10/30: Check in with ADE10/23: Push - ADE rvw10/16: ADE will work back in with other Camp Evers - priorities were on 2019 reviews10/09 <- 9/04: In Review; CAL to send submittal communication email to [REDACTED] for followup - [REDACTED] requested status update w/ ADE8/27: CAL submitted for 2nd ADE rvw [PRELIM DWG ready]8/21: 2nd ADE corrections submittal targeted for 8/268/14: 1st ADE corrections rtn to contractor8/9: ADE Rvw target mvd to 8/12 - reprioritized to for proj approved last year that is returning to Est.8/9: Long Text: 35119401 replaces 740223818/7: ADE targeting a 8/9 review completion; EST in good condition, expects quick 2nd submital turnaround7/31: Awating ADE Review/Corrections7/23: CAL submitted for 1st ADE review - [REDACTED]7/16 <- 7/10: 7/29 1st ADE submittal on track7/03 <- 5/01: waiting for order to be created4/17: On hold until sub-orders created4/8: Still pending the breakup of this job and if it will occur. 3/18: Working on fielding and estimating will start today, this will also pending on the break down of this job3/4: Currently working on how they will section this job out, by 3/6(Version 9) [35051472] | CAL |  |  | Normal | COMPLETED | No | Obsolete (CONS+) | 0 | 0 |  | Yes | [5 empty] | Full |  |  | Full |  |  | May need 1601 permit or redesign - 2/28/2020 - requesting that a pole be relocated to avoid permitting (or date is at risk) | Full |  | Yes |  |  | Submitted on 12/13 | 2020-11-30 | Y | [10 empty] | 0 | 0 | 5702.4 | 1.08 | 1.08 | -7.5758e-05 | 1.0763 | 0 | 1.0763 | 0 | 0.0036742 | 1.0763 |  | Keep | 2020-04-06 | Yes | N/A | 2020-03-12 | 2020-05-07 | 2020-05-07 |  |  | 2020-06-15 |  | Yes | Shovel Ready | 2134802 | 1747411.7 |  | 2570791 | 435989 | 2055652.6 | 81.85% | 29415.8 | 49733.6 | 79149.4 | 0 | 1618087.2985 | 41 | [9 empty] | Scotts Valley | Santa Cruz | 37.1013 | -121.979 | E.5015489.01 |  |  |  | 2020 | Q1 | 2019-12-04 | 2020-04-01 | 2020-05-05 |  | Y | CAMP EVERS 21065020 | 46 | SANTA CRUZ COUNTY | Yes
35119487 |  | 2020 |  | BUCOCAMPT 6486 SHAW CIRCLE MAGALIA* |  | CLSD |  | 0 | 582 | 582 | 0.11023 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 95F | [51 empty] | 582 | 0.11023 | 686 | 0.12992 | 0.24015 | -0.12992 | 0.23939 | 0 | 0.23939 | 0 | 0.00075758 | 0.23939 |  |  |  |  | N/A | [5 empty] | 2019-10-22 |  |  |  | 0 | 162102 |  | 58102.96 | 58102.96 | -162102 |  | 162102 | 0 | 162102 | 0 | 1470616.0825 | [12 empty] | 39.8116 | -121.5972 |  |  |  |  | 2019 | [5 empty] | Y |  |  | BUTTE COUNTY | Yes
35119726 |  | 2020 |  | BUCOCAMPT 1692 YOUNG AVE PARADISE*ILB |  | DOCC |  | 0 | 403 | 403 | 0.076326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 95F | [51 empty] | 403 | 0.076326 | 0 | 0 | 0.076326 | 0 | 0.069886 | 0 | 0.069886 | 0 | 0.0064394 | 0.069886 |  |  |  |  | N/A | [5 empty] | 2019-10-23 |  |  |  | 0 | 109411.8 |  | 28684.35 | 28684.35 | -109411.8 |  | 109411.8 | 0 | 109411.8 | 0 | 1433484.6253 | [12 empty] | 39.7667 | -121.5819 |  |  |  |  | 2019 | [5 empty] | Y |  |  | BUTTE COUNTY | Yes
35119966 |  | 2020 | 220 Mile Plan | CWSP - LOS GATOS 1106 - LB44 - PH 2.6F |  | FICL | 4325 | 0 | 4325 | 4325 | 0.81913 | 4325 | 0.81913 | 0 | 0 | 0 | 0 | 0 |  |  | DA | 08W | SH | 2020-03-03 17:00 | 2019-11-22 |  | 2019-11-22 |  |  | Yes | 2019-11-22 |  | SANTA ROSA |  |  |  | 100 | [5 empty] | Yes | [5 empty] | Full |  |  | Full |  |  | ** Caltrans DSDD - Pilot Project CIF Submitted on 12/3 | Full |  | Yes |  |  | N/A | 1980-01-01 | Y | [10 empty] | 0 | 0 | 4325 | 0.81913 | 0.81913 | 0 | 0.81913 | 0 | 0.81913 | 0 | 0 | 0.81913 |  | Keep | 2020-03-03 17:00 | Yes | N/A | 2020-02-14 | 2020-03-10 | 2020-03-10 |  |  | 2020-03-10 |  | Yes | Shovel Ready | 1136000 | 846094.5 |  | 1552000 | 416000 | 1095308.6 | 74.48% | 585.8 | 40105.6 | 40691.4 | 0 | 1032919.9908 | 18 | [9 empty] | Los Gatos | Santa Clara | 0 | 0 | E.5014534.06 |  |  | 2020-083 | 2020 | Q1 | 2019-12-06 | 2020-02-14 | 2020-02-28 |  | Y | LOS GATOS 1106LB44 | 841 | SANTA CLARA COUNTY | Yes
35119969 |  | 2020 | 220 Mile Plan | CWSP - LOS GATOS 1106 - LB44 - PH 4.2 |  | DOCC | 6777 | 0 | 6777 | 6777 | 1.2835 | 6758 | 1.2799 | 0 | 0 | 0 | 0 | 0.0035985 |  |  | DA | 08W | SH | 2020-05-01 | 2019-12-02 |  | 2019-12-02 |  |  | Yes | 2019-12-02 | [5 empty] | 100 | [5 empty] | Yes | [5 empty] | Full |  |  | Full |  |  | caltrans due on 1/30/20 | Full |  | Yes |  |  | TCP Received - Santa Clara County submitted 12/3 | 2020-07-31 | Y | 2020-05-01 |  |  | Additonal work identified by construction | [6 empty] | 0 | 0 | 6758 | 1.2799 | 1.2799 | 0.0035985 | 1.2835 | 0 | 1.2835 | 0 | -0.0035985 | 1.2835 |  | Keep | 2020-03-23 | Yes | N/A | 2020-04-04 | 2020-08-14 | 2020-08-14 |  |  | 2020-11-18 |  | yes | Shovel Ready | 2027153 | 2331959.4 |  | 2027153 | 0 | 2001709.7 | 115% | 4382 | 21061.3 | 25443.3 | 0 | 1816843.0916 | 28 | [9 empty] | Los Gatos | Santa Clara | 0 | 0 | E.5015493.02 |  |  | 2020-197 | 2020 | Q2 | 2019-11-27 | 2020-03-01 | 2020-03-21 |  | Y | LOS GATOS 1106LB44 | 841 | SANTA CLARA COUNTY | Yes
35119970 |  | 2020 | 220 Mile Plan | CWSP - LOS GATOS 1106 - LB44 - PH 4.3 |  | DOCC | 3090 | 0 | 3090 | 3090 | 0.58523 | 3090 | 0.58523 | 0 | 0 | 0 | 0 | 0 |  |  | DA | 08W | SH | 2020-03-27 | 2019-12-03 |  | 2019-12-03 |  |  | Yes | 2019-12-03 | [5 empty] | 100 | [5 empty] | Yes | [5 empty] | Full |  |  | Full |  |  |  | Full |  | Yes |  |  | Submitted to county on 12/16 + 60-90 days | 2020-06-30 | Y | [10 empty] | 0 | 0 | 3090 | 0.58523 | 0.58523 | 0 | 0.58523 | 0 | 0.58523 | 0 | 0 | 0.58523 |  | Keep | 2020-03-27 | Yes | N/A | 2020-02-22 | 2020-08-09 | 2020-08-09 |  |  | 2020-11-19 |  | yes | Shovel Ready | 1829999.7 | 1912119.6 |  | 1850000 | 20000.3 | 1828395 | 104.5% | 1604.7 | 0 | 1604.7 | 0 | 3267311.1612 | 19 | [9 empty] | Los Gatos | Santa Clara | 0 | 0 | E.5015493.03 |  |  | 2020-198 | 2020 | Q1 | 2019-11-22 | 2020-06-01 | 2020-06-24 |  | Y | LOS GATOS 1106LB44 | 841 | SANTA CLARA COUNTY | Yes
35120063 |  | 2020 |  | BUCOCAMPT 1600 CARSON LN PARADISE* |  | FICL |  | 0 | 328 | 328 | 0.062121 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 95F | [51 empty] | 328 | 0.062121 | 0 | 0 | 0.062121 | 0 | 0.056629 | 0 | 0.056629 | 0 | 0.0054924 | 0.056629 |  |  |  |  | N/A | [5 empty] | 2019-10-18 |  |  |  | 0 | 61442.9 |  | 32928.88 | 32928.88 | -61442.9 |  | 61442.9 | 0 | 61442.9 | 0 | 989080.8293 | [12 empty] | 39.7748 | -121.5866 |  |  |  |  | 2019 | [5 empty] | Y |  |  | BUTTE COUNTY | Yes
35120069 |  | 2020 |  | BUCOCAMPT 4569 RIM VIEW DR CHICO* |  | DOCC |  | 0 | 1395 | 1395 | 0.2642 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 95F | [51 empty] | 1395 | 0.2642 | 0 | 0 | 0.2642 | 0 | 0.22045 | 0 | 0.22045 | 0 | 0.04375 | 0.22045 |  |  |  |  | N/A | [5 empty] | 2019-11-01 |  |  |  | 0 | 211468.4 |  | 59948.38 | 59948.38 | -211468.4 |  | 211468.4 | 0 | 211468.4 | 0 | 800396.5247 | [12 empty] | 39.7539 | -121.6833 |  |  |  |  | 2019 | [5 empty] | Y |  |  | BUTTE COUNTY | Yes
35120368 |  | 2020 |  | BUCOCAMPT 5021 RUSSEL DR PARADISE* |  | CLSD |  | 0 | 362 | 362 | 0.068561 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 95F | [51 empty] | 362 | 0.068561 | 158 | 0.029924 | 0.098485 | -0.029924 | 0.1 | 0 | 0.1 | 0 | -0.0015152 | 0.1 |  |  |  |  | N/A | [5 empty] | 2019-10-14 |  |  |  | 0 | 158137.3 |  | 45363.2 | 45363.2 | -158137.3 |  | 158137.3 | 0 | 158137.3 | 0 | 2306532.9945 | [12 empty] | 39.7446 | -121.6528 |  |  |  |  | 2019 | [5 empty] | Y |  |  | BUTTE COUNTY | Yes
35120507 |  |  |  | BUCOCAMPT 766 WILLOW ST PARADISE* |  | FICL |  | 0 | 960 | 960 | 0.18182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 95F | [51 empty] | 960 | 0.18182 | 0 | 0 | 0.18182 | 0 | 0.025758 | 0 | 0.025758 | 0 | 0.15606 | 0.025758 |  |  |  |  | N/A | [5 empty] | 2019-10-17 |  |  |  | 0 | 76945.5 |  | 37269.96 | 37269.96 | -76945.5 |  | 76945.5 | 0 | 76945.5 | 0 | 423200.25 | [12 empty] | 39.7574 | -121.6229 |  |  |  |  | 2019 | [5 empty] | Y |  |  | BUTTE COUNTY | Yes
35120508 |  | 2020 |  | BUCOCAMPT 14786 COUTOLENC RD MAGALIA* |  | DOCC |  | 0 | 290 | 290 | 0.054924 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 95F | [51 empty] | 290 | 0.054924 | 211 | 0.039962 | 0.094886 | -0.039962 | 0.090909 | 0 | 0.090909 | 0 | 0.0039773 | 0.090909 |  |  |  |  | N/A | [5 empty] | 2019-10-17 |  |  |  | 0 | 179265.4 |  | 49991.48 | 49991.48 | -179265.4 |  | 179265.4 | 0 | 179265.4 | 0 | 3263866.5931 | [12 empty] | 39.843 | -121.5704 |  |  |  |  | 2019 | [5 empty] | Y |  |  | BUTTE COUNTY | Yes
35120949 |  | 2020 |  | CWSP- BUCOCAMP - SKYWAY PARADISE TIE PH2 |  | PEND |  | 0 | 10150 | 10150 | 1.9223 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | SH | 2020-05-11 |  | 2020-09-30 |  |  |  |  | 2019-10-24 | [11 empty] | Yes | [5 empty] | Full |  |  | Full |  |  |  | Full |  | Yes |  |  |  |  | Y | [10 empty] | 10150 | 1.9223 | 0 | 0 | 1.9223 | 0 | 1.9223 | 0 | 1.9223 | 0 | 0 | 1.9223 |  |  | 2020-05-11 | Yes | COMP | 2019-10-14 | 2020-06-26 08:00 | 2020-06-26 |  |  |  |  | yes | Shovel Ready | 13429644.2 | 17855393.5 |  | 14251728 | 822083.8 | 2981043.1 | 132.9% | 10448601.1 | 0 | 10448601.1 | -1431862 | 9288322.9241 |  |  |  | Complete | [6 empty] | Paradise | Butte | 0 | 0 |  |  |  |  | 2019 | [5 empty] | Y | PARADISE 11032488 | 1123 | BUTTE COUNTY | Yes
35121259 |  | 2020 |  | BUCOCAMPT 6419 DORA LEE LN PARADISE* |  | CLSD |  | 0 | 532 | 532 | 0.10076 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 95F | [51 empty] | 532 | 0.10076 | 0 | 0 | 0.10076 | 0 | 0.095265 | 0 | 0.095265 | 0 | 0.0054924 | 0.095265 |  |  |  |  | N/A | [5 empty] | 2019-11-07 |  |  |  | 0 | 80542.2 |  | 33327.31 | 33327.31 | -80542.2 |  | 80542.2 | 0 | 80542.2 | 0 | 799366.1955 | [12 empty] | 39.7776 | -121.5937 |  |  |  |  | 2019 | [5 empty] | Y |  |  | BUTTE COUNTY | Yes
35121380 |  | 2020 |  | BUCOCAMPT 1412 ANDREA LN PARADISE* |  | CLSD |  | 0 | 256 | 256 | 0.048485 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 95F | [51 empty] | 256 | 0.048485 | 53 | 0.010038 | 0.058523 | -0.010038 | 0.064583 | 0 | 0.064583 | 0 | -0.0060606 | 0.064583 |  |  |  |  | N/A | [5 empty] | 2019-11-02 |  |  |  | 0 | 108589 |  | 24425.56 | 24425.56 | -108589 |  | 108589 | 0 | 108589 | 0 | 2239648.125 | [12 empty] | 39.7813 | -121.594 |  |  |  |  | 2019 | [5 empty] | Y |  |  | BUTTE COUNTY | Yes
35122641 |  | 2020 | (blank) | BUCOCAMP - CENTERVILLE CNYN TIE LINE RMV |  | UNSC |  | 0 | 21995.1 | 21995.1 | 4.1657 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 95F | [51 empty] | 21995.1 | 4.1657 | 0 | 0 | 4.1657 | 0 | 4.1657 | 0 | 4.1657 | 0 | -6.8901e-16 | 4.1657 |  |  |  |  | N/A | [31 empty] | Magalia | Butte | 39.7982 | -121.604 |  |  |  |  | 2019 | [8 empty] | BUTTE COUNTY | Yes
35123182 |  | 2020 |  | BUCOCAMPT 1608 HEMLOCK LN PARADISE* |  | FICL |  | 0 | 1137 | 1137 | 0.21534 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 95F |  |  |  | 2019-09-26 | [47 empty] | 1137 | 0.21534 | 0 | 0 | 0.21534 | 0 | 0.071402 | 0 | 0.071402 | 0 | 0.14394 | 0.071402 |  |  |  |  | N/A | [5 empty] | 2019-10-22 |  |  |  | 0 | 81381.8 |  | 52364.9 | 52364.9 | -81381.8 |  | 81381.8 | 0 | 81381.8 | 0 | 377920.7599 | [12 empty] | 39.7531 | -121.5844 |  |  |  |  | 2019 | [5 empty] | Y |  |  | BUTTE COUNTY | Yes
35123195 |  | 2020 |  | BUCOCAMPT 686 MARVIN DR PARADISE* |  | DOCC |  | 0 | 50 | 50 | 0.0094697 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 95F |  |  |  | 2019-09-13 | [47 empty] | 50 | 0.0094697 | 158 | 0.029924 | 0.039394 | -0.029924 | 0.042045 | 0 | 0.042045 | 0 | -0.0026515 | 0.042045 |  |  |  |  | N/A | [5 empty] | 2019-11-16 |  |  |  | 0 | 148305.2 |  | 37318.8 | 37318.8 | -148305.2 |  | 148305.2 | 0 | 148305.2 | 0 | 15661029.12 | [12 empty] | 39.7465 | -121.6266 |  |  |  |  | 2019 | [5 empty] | Y |  |  | BUTTE COUNTY | Yes
35123202 |  | 2020 |  | BUCOCAMPT HOG RANCH RD OROVILLE*ILB |  | FICL |  | 0 | 884 | 884 | 0.16742 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 95F |  |  |  | 2019-10-07 | [47 empty] | 884 | 0.16742 | 53 | 0.010038 | 0.17746 | -0.010038 | 0.17727 | 0 | 0.17727 | 0 | 0.00018939 | 0.17727 |  |  |  |  | N/A | [5 empty] | 2019-11-13 |  |  |  | 0 | 89037.8 |  | 38428.6 | 38428.6 | -89037.8 |  | 89037.8 | 0 | 89037.8 | 0 | 531809.4842 | [12 empty] | 39.7872 | -121.5308 |  |  |  |  | 2019 | [5 empty] | Y |  |  | BUTTE COUNTY | Yes
35123825 |  | 2020 |  | BUCOCAMPT 1486 MAGADON RD PARADISE* |  | FICL |  | 0 | 1379 | 1379 | 0.26117 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 95F | [51 empty] | 1379 | 0.26117 | 0 | 0 | 0.26117 | 0 | 0.05322 | 0 | 0.05322 | 0 | 0.20795 | 0.05322 |  |  |  |  | N/A | [5 empty] | 2019-10-26 |  |  |  | 0 | 78465.3 |  | 30125.98 | 30125.98 | -78465.3 |  | 78465.3 | 0 | 78465.3 | 0 | 300432.7658 | [12 empty] | 39.7418 | -121.5892 |  |  |  |  | 2019 | [5 empty] | Y |  |  | BUTTE COUNTY | Yes
35126057 |  | 2020 |  | BUCOCAMPT 643 CIRCLEWOOD DR PARADISE |  | FICL |  | 0 | 678 | 678 | 0.12841 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 95F | [51 empty] | 678 | 0.12841 | 1742 | 0.32992 | 0.45833 | -0.32992 | 0.4553 | 0 | 0.4553 | 0 | 0.0030303 | 0.4553 |  |  |  |  | N/A | [5 empty] | 2019-11-03 |  |  |  | 0 | 187420.2 |  | 102564.34 | 102564.34 | -187420.2 |  | 187420.2 | 0 | 187420.2 | 0 | 1459555.5398 | [12 empty] | 39.7444 | -121.6316 |  |  |  |  | 2019 | [5 empty] | Y |  |  | BUTTE COUNTY | Yes
35126138 |  | 2020 |  | BUCOCAMPT 1420 PINE CRK WY PARADISE*ILB |  | CLSD |  | 0 | 320 | 320 | 0.060606 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 95F | [51 empty] | 320 | 0.060606 | 158 | 0.029924 | 0.09053 | -0.029924 | 0.093371 | 0 | 0.093371 | 0 | -0.0028409 | 0.093371 |  |  |  |  | N/A | [5 empty] | 2019-11-19 |  |  |  | 0 | 91370.4 |  | 23000.82 | 23000.82 | -91370.4 |  | 91370.4 | 0 | 91370.4 | 0 | 1507611.6 | [12 empty] | 39.766 | -121.5936 |  |  |  |  | 2019 | [5 empty] | Y |  |  | BUTTE COUNTY | Yes
35126139 |  | 2020 |  | BUCOCAMPT 6562 MILTON DR MAGALIA |  | FICL |  | 0 | 1035 | 1035 | 0.19602 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 95F | [51 empty] | 1035 | 0.19602 | 0 | 0 | 0.19602 | 0 | 0.085227 | 0 | 0.085227 | 0 | 0.1108 | 0.085227 |  |  |  |  | N/A | [5 empty] | 2019-11-18 |  |  |  | 0 | 94975.6 |  | 40192.73 | 40192.73 | -94975.6 |  | 94975.6 | 0 | 94975.6 | 0 | 484513.2058 | [12 empty] | 39.8098 | -121.5925 |  |  |  |  | 2019 | [5 empty] | Y |  |  | BUTTE COUNTY | Yes
35126588 |  | 2020 |  | BUCOCAMPT 1652 KINGS ROW PARADISE*ILB |  | DOCC |  | 0 | 860 | 860 | 0.16288 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 95F |  |  |  | 2019-09-30 | [47 empty] | 860 | 0.16288 | 0 | 0 | 0.16288 | 0 | 0.047538 | 0 | 0.047538 | 0 | 0.11534 | 0.047538 |  |  |  |  | N/A | [5 empty] | 2019-11-01 |  |  |  | 0 | 50837.9 |  | 49529.11 | 49529.11 | -50837.9 |  | 50837.9 | 0 | 50837.9 | 0 | 312121.0605 | [12 empty] | 39.7727 | -121.5798 |  |  |  |  | 2019 | [5 empty] | Y |  |  | BUTTE COUNTY | Yes
35126592 |  | 2020 |  | BUCOCAMPT 6381 CALVIN DR MAGALIA*ILB |  | FICL |  | 0 | 229 | 229 | 0.043371 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 95F |  |  |  | 2019-10-07 | [47 empty] | 229 | 0.043371 | 634 | 0.12008 | 0.16345 | -0.12008 | 0.16155 | 0 | 0.16155 | 0 | 0.0018939 | 0.16155 |  |  |  |  | N/A | [5 empty] | 2019-11-16 |  |  |  | 0 | 129526 |  | 68293 | 68293 | -129526 |  | 129526 | 0 | 129526 | 0 | 2986451.0044 | [12 empty] | 39.8078 | -121.5998 |  |  |  |  | 2019 | [5 empty] | Y |  |  | BUTTE COUNTY | Yes
35126607 |  | 2020 |  | BUCOCAMPT 6904 DEAN PL PARADISE*ILB |  | CLSD |  | 0 | 887 | 887 | 0.16799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 95F |  |  |  | 2019-09-30 | [47 empty] | 887 | 0.16799 | 0 | 0 | 0.16799 | 0 | 0.096591 | 0 | 0.096591 | 0 | 0.071402 | 0.096591 |  |  |  |  | N/A | [5 empty] | 2019-12-05 |  |  |  | 0 | 67730.1 |  | 28871.21 | 28871.21 | -67730.1 |  | 67730.1 | 0 | 67730.1 | 0 | 403173.5378 | [12 empty] | 39.7869 | -121.5704 |  |  |  |  | 2019 | [5 empty] | Y |  |  | BUTTE COUNTY | Yes
35126879 |  | 2020 |  | BUCOCAMPT 5771 BONNIE LN PARADISE*ILB |  | CLSD |  | 0 | 292 | 292 | 0.055303 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 95F |  |  |  | 2019-09-30 | [47 empty] | 292 | 0.055303 | 53 | 0.010038 | 0.065341 | -0.010038 | 0.07197 | 0 | 0.07197 | 0 | -0.0066288 | 0.07197 |  |  |  |  | N/A | [5 empty] | 2019-11-16 | [27 empty] | 39.7558 | -121.5948 |  |  |  |  | 2019 | [5 empty] | Y |  |  | BUTTE COUNTY | Yes
35126986 |  | 2020 |  | BUCOCAMPT 6050 MAXWOOD DR PARADISE*ILB |  | DOCC |  | 0 | 1121 | 1121 | 0.21231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 95F | [51 empty] | 1121 | 0.21231 | 0 | 0 | 0.21231 | 0 | 0.018182 | 0 | 0.018182 | 0 | 0.19413 | 0.018182 |  |  |  |  | N/A | [5 empty] | 2019-11-11 |  |  |  | 0 | 58003.2 |  | 36203.27 | 36203.27 | -58003.2 |  | 58003.2 | 0 | 58003.2 | 0 | 273199.7288 | [12 empty] | 39.7665 | -121.585 |  |  |  |  | 2019 | [5 empty] | Y |  |  | BUTTE COUNTY | Yes
35127511 |  | 2020 |  | BUCOCAMPT 5548 NEWLAND RD PARADISE* |  | DOCC |  | 0 | 226 | 226 | 0.042803 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 95F |  |  |  | 2019-10-11 | [47 empty] | 226 | 0.042803 | 1742 | 0.32992 | 0.37273 | -0.32992 | 0.36534 | 0 | 0.36534 | 0 | 0.0073864 | 0.36534 |  |  |  |  | N/A | [5 empty] | 2019-12-21 |  |  |  | 0 | 130590.6 |  | 100771.22 | 100771.22 | -130590.6 |  | 130590.6 | 0 | 130590.6 | 0 | 3050966.2301 | [12 empty] | 39.7493 | -121.6009 |  |  |  |  | 2019 | [5 empty] | Y |  |  | BUTTE COUNTY | Yes
35129370 |  | 2020 |  | BUCOCAMPT 5784 HOMESTEAD PL PARADISE*ILB |  | FICL |  | 0 | 687 | 687 | 0.13011 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 95F |  |  |  | 2019-10-11 | [47 empty] | 687 | 0.13011 | 0 | 0 | 0.13011 | 0 | 0.041288 | 0 | 0.041288 | 0 | 0.088826 | 0.041288 |  |  |  |  | N/A | [5 empty] | 2019-11-09 |  |  |  | 0 | 39476 |  | 25467.84 | 25467.84 | -39476 |  | 39476 | 0 | 39476 | 0 | 303396.3319 | [12 empty] | 39.756 | -121.5804 |  |  |  |  | 2019 | [5 empty] | Y |  |  | BUTTE COUNTY | Yes
35131034 |  | 2020 |  | BUCOCAMPT 2903 NEAL RD PARADISE |  | CLSD |  | 0 | 402 | 402 | 0.076136 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 95F |  |  |  | 2019-10-21 | [47 empty] | 402 | 0.076136 | 0 | 0 | 0.076136 | 0 | 0.048106 | 0 | 0.048106 | 0 | 0.02803 | 0.048106 |  |  |  |  | N/A | [5 empty] | 2019-11-20 |  |  |  | 0 | 61004.7 |  | 31237.77 | 31237.77 | -61004.7 |  | 61004.7 | 0 | 61004.7 | 0 | 801255.7612 | [12 empty] | 39.7161 | -121.6613 |  |  |  |  | 2019 | [5 empty] | Y |  |  | BUTTE COUNTY | Yes
35131804 |  | 2020 |  | BUCOCAMPT 13869 TULSA CT MAGALIA*ILB |  | FICL |  | 0 | 392 | 392 | 0.074242 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 95F |  |  |  | 2019-10-26 | [47 empty] | 392 | 0.074242 | 211 | 0.039962 | 0.1142 | -0.039962 | 0.1053 | 0 | 0.1053 | 0 | 0.0089015 | 0.1053 |  |  |  |  | N/A | [5 empty] | 2020-01-18 |  |  |  | 0 | 39482 |  | 36191.6 | 36191.6 | -39482 |  | 39482 | 0 | 39482 | 0 | 531798.3673 | [12 empty] | 39.811 | -121.5942 |  |  |  |  | 2019 | [5 empty] | Y |  |  | BUTTE COUNTY | Yes
35135864 |  | 2020 | 220 Mile Plan | CWSP - GRAYS FLAT 401 FUSE 3079 ZONE |  | CONS |  | 0 | 9316 | 9316 | 1.7644 | 9316 | 1.7644 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 08W | SH | 2020-06-05 | 2020-02-10 |  | 2020-02-10 |  |  |  | 2020-02-10 | [11 empty] | Yes | [5 empty] | Full |  |  | Full |  |  |  | Full |  | Yes |  |  | Expires 10/1 | 1980-01-01 | Y | [10 empty] | 0 | 0 | 9316 | 1.7644 | 1.7644 | 0 | 1.7492 | 0 | 1.7492 | 0 | 0.015152 | 1.7492 |  | Keep | 2020-06-05 | Yes | COMP | 2020-05-26 | 2020-08-05 | 2020-08-05 |  |  |  |  | Yes | Shovel Ready | 347534 | 145118.9 |  | 347534 | 0 | 346892.9 | 41.75% | 641.1 | 0 | 641.1 | 0 | 82248.5822 | [10 empty] | Twain | Plumas | 40.018 | -121.0405 | 35135864 |  |  |  | 2020 | Q3 | 0 |  | 0 |  | Y | GRAYS FLAT 0401CB | 1833 | PLUMAS COUNTY | Yes
35144940 |  |  |  | *CANC* PSPS - HICKS 2101 - CB |  | CLSD | 7145.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SJ | 08W |  |  |  | 2020-10-31 | [5 empty] | Cancelled | [12 empty] | PSPS - Cancled | [28 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [5 empty] | 2020-09-03 | [18 empty] | Complete | Install 2 PSPS devices only | [5 empty] | San Jose | Santa Clara | 37.232 | -121.8718 | E.5025645.01 |  |  |  | 1980 | Q3 |  |  | 2020-09-01 |  | Y | HICKS 2101XR250 | 621 | SANTA CLARA COUNTY | Yes
35144942 |  |  |  | *CANC* PSPS - PAUL SWEET 2105 - CB |  | CLSD | 3960 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | CC | 08W |  |  |  | 2020-10-31 | [5 empty] | Cancelled | Fresno | [11 empty] | PSPS - Cancled | [28 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [5 empty] | 2020-09-03 | [18 empty] | Complete | Scope to be updated to be switching and PSPS devices | [5 empty] | Santa Cruz | Santa Cruz | 36.9924 | -121.9827 | E.5025647.01 |  |  |  | 1980 | Q3 |  |  | 2020-09-01 |  | Y | PAUL SWEET 210212850 | 2907 | SANTA CRUZ COUNTY | Yes
35145005 |  |  |  | *CANCELLED*CWSP - STAFFORD 1101 - CB PH1 |  | DOCC | 2481.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NB | 08W |  |  |  | 2020-10-31 | [6 empty] | Santa Rosa | [11 empty] | PSPS - Cancled | [28 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [25 empty] | Base map provided. Need onsite meeting to finalize scope | [5 empty] | Novato | Marin | 0 | 0 | E.5025643.01 |  |  |  | 1980 |  |  |  | 2020-09-01 |  |  | STAFFORD 1101CB | 2382 | MARIN COUNTY | Yes
35145523 |  |  |  | *CANC* PSPS - FULTON 1102 HARDENING |  | CLSD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SO | 08W |  |  |  | 2020-10-31 | [6 empty] | Santa Rosa | [11 empty] | PSPS - Cancled | [28 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [5 empty] | 2020-09-03 | [19 empty] | Most likely to be canceleled once PSS final approval or revised Fire threat district | [5 empty] | Santa Rosa | Sonoma | 38.5187 | -122.7576 | E.5025636.01 |  |  |  | 1980 |  |  |  | 2020-09-01 |  |  | FULTON 1102CB | 2036 | SONOMA COUNTY | Yes
35168820 |  |  |  | CWSP - PLACERVILLE 2106 - LR1104 - PH1.4 |  | ESTS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W |  | 2021-02-28 | 2021-02-28 | 2021-03-31 | 2021-02-28 | 2021-01-24 | 2021-01-24 |  |  | 08/10: Issued to Vendor | EEI |  |  | 2021 - Q1- M2 [R2021_148] | R0.0 - Estimating |  | Wood (QTY TBD) | 0 | 0 | [32 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [31 empty] | Georgetown | El Dorado | 38.9354 | -120.7461 | [13 empty] | EL DORADO COUNTY | Yes
35168821 |  |  |  | CWSP - PLACERVILLE 2106 - LR1104 - PH1.5 |  | ESTS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W |  | 2021-02-28 | 2021-02-28 | 2021-03-31 | 2021-02-28 | 2021-01-24 | 2021-01-24 |  |  | 08/10: Issued to Vendor | EEI |  |  | 2021 - Q1- M2 [R2021_148] | R0.0 - Estimating |  | Wood (QTY TBD) | 0 | 0 | [32 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [31 empty] | Georgetown | El Dorado | 38.9354 | -120.7461 | [13 empty] | EL DORADO COUNTY | Yes
35168822 |  |  |  | CWSP - PLACERVILLE 2106 - LR1104 - PH1.6 |  | ESTS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W |  | 2021-01-31 | 2021-01-31 | 2021-03-31 | 2021-01-31 | 2020-12-27 | 2020-12-27 |  |  | 08/10: Issued to Vendor | EEI |  |  | 2021 - Q1- M1 [R2021_148] | R0.0 - Estimating |  | Wood (QTY TBD) | 0 | 0 | [32 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [31 empty] | Georgetown | El Dorado | 38.9354 | -120.7461 | [13 empty] | EL DORADO COUNTY | Yes
35168823 |  |  |  | CWSP - PLACERVILLE 2106 - LR1104 - PH1.7 |  | ESTS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W |  | 2021-01-31 | 2021-01-31 | 2021-03-31 | 2021-01-31 | 2020-12-27 | 2020-12-27 |  |  | 08/10: Issued to Vendor | EEI |  |  | 2021 - Q1- M1 [R2021_148] | R0.0 - Estimating |  | Wood (QTY TBD) | 0 | 0 | [32 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [31 empty] | Georgetown | El Dorado | 38.9354 | -120.7461 | [13 empty] | EL DORADO COUNTY | Yes
35170202 |  |  |  | CWSP - ORO FINO 1101 - LR2022 PH2.7 |  | ESTS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 08W |  | 2022-02-04 17:00 | 2021-01-31 |  | 2021-01-31 | 2021-01-01 | 2021-01-01 |  |  | 11/04 - 10/28: EOD Push [REDACTED]; Easement being drawn up; Land avg 2-3 months to process10/21 - 10/21: Survey complete; easement being drawn up. Will start design upon completion.10/14: Fires cleared; survey map sent in; clearing up some Q&A - may need refielding, survey identified a more optimal location.10/07: Fielding held up due to fires 09/02: On Track08/26: Push Est sub Sept to Nov; With Land to write up easement (potential to take 90days)08/19: On track - meeting08/12: Meeting next Wens (1hr) and Del Oro Water08/05: Meeting sched next coming week(s) with PID to iron out details08/05: USER STATUS - UNSE ??07/29 - 07/08: EST sub (9/18); Round 2 PID 07/01 - 06/24: EST On Track06/17: 1st sub set (7/24); PID06/10 - 05/13: Still waiting on response; push 1st sub05/06 - 04/15: On Track; PID - EST waiting on version to use; will submit once advised.04/08: 1st sub date; in review on 'how' to design/execute04/03: requested to avoid delaying of PM#35094515 (Oro Fino 1101 – LR2022 PH1.1) due to dependencies for circuit reroute inside Paradise Irrigation district | QUES |  |  | 2021 - Q1- M1 [R2022(+)_14] | R0.0 - Estimating |  | Wood (QTY TBD) | 0 | 0 | [32 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 2022-02-04 17:00 |  | INPR | 2022-05-02 08:00 | 2022-11-07 17:00 | 2022-12-05 17:00 | [6 empty] | 271429 | 131380.6 |  | 271429 | 0 | 271429 | 48.4% | 0 | 0 | 0 | 0 |  |  |  |  | Complete | [6 empty] | Magalia | Butte | 0 | 0 |  | ML | OH | [7 empty] | Y |  |  | BUTTE COUNTY | Yes
35171354 |  | 2020 | 220 Mile Plan | CWSP - CAMP EVERS 2106 - 5020 - PHASE 2 |  | CLSD |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | CC | 08W | SH | [50 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  | Yes | N/A | [5 empty] | 2020-04-29 |  |  | Shovel Ready | [22 empty] | Scotts Valley | Santa Cruz | 37.1013 | -121.979 | [10 empty] | Y |  |  | SANTA CRUZ COUNTY | Yes
35173253 |  |  |  | CWSP-EL DORADO PH 2102 LR19542 PH 1.3 |  | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | [51 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | INPR | [9 empty] | 100000 | 0 |  | 100000 | 0 | 100000 | 0% | 0 | 0 | 0 | 0 | [11 empty] | El Dorado Hills | El Dorado | 0 | 0 |  |  |  |  | 999 | [5 empty] | Y |  |  | EL DORADO COUNTY | Yes
35173255 |  |  |  | CWSP-EL DORADO PH 2102 LR19542 PH 1.2 |  | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | [51 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | INPR | [9 empty] | 100000 | 0 |  | 100000 | 0 | 100000 | 0% | 0 | 0 | 0 | 0 | [11 empty] | El Dorado Hills | El Dorado | 0 | 0 |  |  |  |  | 999 | [5 empty] | Y |  |  | EL DORADO COUNTY | Yes
35173320 |  |  |  | CWSP-EL DORADO PH 2102 LR19542 PH 1.5 |  | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | [51 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | INPR | [9 empty] | 100000 | 0 |  | 100000 | 0 | 100000 | 0% | 0 | 0 | 0 | 0 | [11 empty] | El Dorado Hills | El Dorado | 0 | 0 |  |  |  |  | 999 | [5 empty] | Y |  |  | EL DORADO COUNTY | Yes
35173321 |  |  |  | CWSP-EL DORADO PH 2102 LR19542 PH 1.4 |  | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | [51 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | INPR | [9 empty] | 100000 | 0 |  | 100000 | 0 | 100000 | 0% | 0 | 0 | 0 | 0 | [11 empty] | El Dorado Hills | El Dorado | 0 | 0 |  |  |  |  | 999 | [5 empty] | Y |  |  | SIERRA COUNTY | Yes
35173959 |  |  |  | CWSP-MIWUK 1702-LR 38218-PH 1.6 |  | ESTS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | YO | 08W |  | 2020-12-31 | 2020-12-31 |  | 2020-12-31 | 2020-10-28 | 2020-10-28 |  |  | 11/04: ADE in rvw; priority based; target mid wk (11/11)10/28: QUES submitted corrections for 2nd ADE rvw10/21; Working with Planner for solution to ADE question10/14 - 10/07: Submittal by 10/2309/25: ADE rtn 1st corrections to CO09/15: QUES submitted for 1st ADE rvw; ADE assigned [REDACTED]09/02: EST sub (9/11); Transformer items require refield09/01 - 08/26: EST target sub (9/8); finish stampting08/19: On Track08/12: EST target sub (8/31); going into EST internal rvw08/05: EST to follow up, rvw if 1.2 change impacts this pc08/05 - 07/08: Dependant on 1.2; Estimator going on leave to be reassigned07/01 - 06/17: EST 1st sub set (07/31)06/10- 05/13: EST working 1.2 priority; EST push 1st sub (6/05)05/06: EST reviewing scope of activities - Sub to be firmed up.04/29: EST reassignment - new EST coming up to speed, review current state and action items; 1 Sub TBD; ADE pre-assigned [REDACTED] to align with 35116441 reviews4/23: PM created for segment coming from PM 35116441; EST working on resource assignment and fielding; 1st sub date TBD | QUES |  |  | 2020 - Q4- M12 [R2022(+)_] | R2.2 - ADE Review in Progress |  | Wood | 50 | 9 | [32 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [31 empty] | Twain Harte | Tuolumne | 38.0486 | -120.2438 | [13 empty] | TUOLUMNE COUNTY | Yes
35174993 |  |  |  | CWSP - PLACERVILLE 2106 - LR1104 - PH2.2 |  | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | [51 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [31 empty] | Georgetown | El Dorado | 38.9354 | -120.7461 | [13 empty] | EL DORADO COUNTY | Yes
35175843 |  |  |  | CWSP - PLACERVILLE 2106 - LR1104 - PH3.2 |  | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | [51 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [31 empty] | Georgetown | El Dorado | 0 | 0 | [13 empty] | EL DORADO COUNTY | Yes
35175844 |  |  |  | CWSP - PLACERVILLE 2106 - LR1104 - PH3.3 |  | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | [51 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [31 empty] | Georgetown | El Dorado | 0 | 0 | [13 empty] | EL DORADO COUNTY | Yes
35175845 |  |  |  | CWSP - PLACERVILLE 2106 - LR1104 - PH3.4 |  | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | [51 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [31 empty] | Georgetown | El Dorado | 0 | 0 | [13 empty] | EL DORADO COUNTY | Yes
35175846 |  |  |  | CWSP - PLACERVILLE 2106 - LR1104 - PH3.5 |  | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | [51 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [31 empty] | Georgetown | El Dorado | 0 | 0 | [13 empty] | EL DORADO COUNTY | Yes
35175847 |  |  |  | CWSP - PLACERVILLE 2106 - LR1104 - PH4.2 |  | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | [51 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [31 empty] | Georgetown | El Dorado | 0 | 0 | [13 empty] | EL DORADO COUNTY | Yes
35175848 |  |  |  | CWSP - PLACERVILLE 2106 - LR1104 - PH4.3 |  | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | [51 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [31 empty] | Georgetown | El Dorado | 0 | 0 | [13 empty] | EL DORADO COUNTY | Yes
35175849 |  |  |  | CWSP - PLACERVILLE 2106 - LR1104 - PH4.4 |  | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | [51 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [31 empty] | Georgetown | El Dorado | 0 | 0 | [13 empty] | EL DORADO COUNTY | Yes
35175850 |  |  |  | CWSP - PLACERVILLE 2106 - LR1104 - PH4.5 |  | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | [51 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [31 empty] | Georgetown | El Dorado | 0 | 0 | [13 empty] | EL DORADO COUNTY | Yes
35175852 |  |  |  | CWSP - PLACERVILLE 2106 - LR1104 - PH5.2 |  | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | [51 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [31 empty] | Georgetown | El Dorado | 0 | 0 | [13 empty] | EL DORADO COUNTY | Yes
35175853 |  |  |  | CWSP - PLACERVILLE 2106 - LR1104 - PH5.3 |  | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | [51 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [31 empty] | Georgetown | El Dorado | 0 | 0 | [13 empty] | EL DORADO COUNTY | Yes
35175854 |  |  |  | CWSP - PLACERVILLE 2106 - LR1104 - PH5.4 |  | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | [51 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [31 empty] | Georgetown | El Dorado | 0 | 0 | [13 empty] | EL DORADO COUNTY | Yes
35175855 |  |  |  | CWSP - PLACERVILLE 2106 - LR1104 - PH5.5 |  | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | [51 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [31 empty] | Georgetown | El Dorado | 0 | 0 | [13 empty] | EL DORADO COUNTY | Yes
35175856 |  |  |  | CWSP - PLACERVILLE 2106 - LR1104 - PH6.2 |  | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | [51 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [31 empty] | Georgetown | El Dorado | 0 | 0 | [13 empty] | EL DORADO COUNTY | Yes
35175857 |  |  |  | CWSP - PLACERVILLE 2106 - LR1104 - PH6.3 |  | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | [51 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [31 empty] | Georgetown | El Dorado | 0 | 0 | [13 empty] | EL DORADO COUNTY | Yes
35175858 |  |  |  | CWSP - PLACERVILLE 2106 - LR1104 - PH6.4 |  | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | [51 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [31 empty] | Georgetown | El Dorado | 0 | 0 | [13 empty] | EL DORADO COUNTY | Yes
35175859 |  |  |  | CWSP - PLACERVILLE 2106 - LR1104 - PH6.5 |  | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | [51 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [31 empty] | Georgetown | El Dorado | 0 | 0 | [13 empty] | EL DORADO COUNTY | Yes
35176209 |  |  |  | CWSP - PLACERVILLE 2106 - LR1104 - PH2.3 |  | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | [51 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [31 empty] | Georgetown | El Dorado | 38.9354 | -120.7461 | [13 empty] | EL DORADO COUNTY | Yes
35176210 |  |  |  | CWSP - PLACERVILLE 2106 - LR1104 - PH2.4 |  | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | [51 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [31 empty] | Georgetown | El Dorado | 38.9354 | -120.7461 | [13 empty] | EL DORADO COUNTY | Yes
35176211 |  |  |  | CWSP - PLACERVILLE 2106 - LR1104 - PH2.5 |  | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | [51 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [31 empty] | Georgetown | El Dorado | 0 | 0 | [13 empty] | EL DORADO COUNTY | Yes
35176497 |  |  |  | ECOP-STANISLAUS 1702-H03-LR1850 |  | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | ST | 08W | [51 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [31 empty] | Arnold | Calaveras | 38.2656 | -120.3398 | [13 empty] | CALAVERAS COUNTY | Yes
35176549 |  |  |  | ECOP-MONTE RIO 1113-H07-LR180 |  | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 08W | [51 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [31 empty] | Guerneville | Sonoma | 38.4999 | -123.022 | [13 empty] | SONOMA COUNTY | Yes
35177107 |  |  |  | CWSP - PLACERVILLE 2106 - LR1104 - PH3.6 |  | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | [51 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [31 empty] | Georgetown | El Dorado | 0 | 0 | [11 empty] | PLACERVILLE 21061104 | 16 | EL DORADO COUNTY | Yes
35177108 |  |  |  | CWSP - PLACERVILLE 2106 - LR1104 - PH3.7 |  | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | [51 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [31 empty] | Georgetown | El Dorado | 0 | 0 | [11 empty] | PLACERVILLE 21061104 | 16 | EL DORADO COUNTY | Yes
35177109 |  |  |  | CWSP - PLACERVILLE 2106 - LR1104 - PH2.6 |  | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | [51 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [31 empty] | Georgetown | El Dorado | 0 | 0 | [11 empty] | PLACERVILLE 21061104 | 16 | EL DORADO COUNTY | Yes
35177110 |  |  |  | CWSP - PLACERVILLE 2106 - LR1104 - PH2.7 |  | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | [51 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [31 empty] | Georgetown | El Dorado | 0 | 0 | [11 empty] | PLACERVILLE 21061104 | 16 | EL DORADO COUNTY | Yes
35177111 |  |  |  | CWSP - PLACERVILLE 2106 - LR1104 - PH2.8 |  | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | [51 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [31 empty] | Georgetown | El Dorado | 0 | 0 | [11 empty] | PLACERVILLE 21061104 | 16 | EL DORADO COUNTY | Yes
35191318 |  | 2021 |  | ECOP - SILVERADO 2102 - H02-LR58626 |  | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 08W | [51 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [31 empty] | Saint Helena | Napa | 38.5095 | -122.386 | [13 empty] | NAPA COUNTY | Yes
35191319 |  | 2021 |  | ECOP - LAS GALLINAS A 1105 - H01-LR99904 |  | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 08W | [51 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [31 empty] | Nicasio | Marin | 38.046 | -122.646 | [13 empty] | MARIN COUNTY | Yes
35191383 |  | 2021 |  | ECOP - SILVERADO 2102 - H01-LR58626 |  | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 08W | [51 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [31 empty] | Saint Helena | Napa | 38.5057 | -122.401 | [13 empty] | NAPA COUNTY | Yes
35192043 |  |  |  | ECOP - PINE GROVE 1102 - H03-LR13438 PH1 |  | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 08W | [51 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [31 empty] | Volcano | Amador | 38.4744 | -120.6272 | [13 empty] | AMADOR COUNTY | Yes
35192280 |  | 2021 |  | ECOP - CLAYTON 2212 - H01-LR2951 |  | ESTS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 08W | [51 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A |  |  |  | 2021-12-31 07:00 | 2021-12-31 16:00 | [26 empty] | Clayton | Contra Costa | 37.8682 | -121.8573 | [13 empty] | CONTRA COSTA COUNTY | Yes
35192281 |  | 2021 |  | ECOP - MIDDLETOWN 1101 - H16-LR48212 PH1 |  | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 08W | [51 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [31 empty] | Middletown | Lake | 38.7238 | -122.6197 | [13 empty] | LAKE COUNTY | Yes
35192282 |  | 2021 |  | ECOP - MIDDLETOWN 1101 - H16-LR48212 PH2 |  | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 08W | [51 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [31 empty] | Middletown | Lake | 38.7238 | -122.6197 | [13 empty] | LAKE COUNTY | Yes
35192284 |  | 2021 |  | ECOP - SILVERADO 2104 - H05-LR726 |  | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 08W | [51 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [31 empty] | Pope Valley | Napa | 38.6154 | -122.4315 | [13 empty] | NAPA COUNTY | Yes
35192292 |  | 2021 |  | ECOP - FULTON 1107 - H02-LR604 |  | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 08W | [51 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [31 empty] | Santa Rosa | Sonoma | 38.5527 | -122.7132 | [13 empty] | SONOMA COUNTY | Yes
35193574 |  | 2020 | T2/T3 A Tag | SR-CC-SANTA CRUZ-08-16-20 CZU AUG FIRE |  | ESTS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 95A | [51 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [33 empty] | 36.9747 | -122.0309 | [13 empty] | SANTA CRUZ COUNTY | Yes
35198909 |  |  |  | CV-YO-MADERA CNTY- 9-6-20 CREEK FIRE EVE |  | ESTS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 95A | [51 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [31 empty] | Oakhurst | Madera | 0 | 0 | [13 empty] | MADERA COUNTY | Yes
35199234 |  | 2020 | T1 A Tag | NO-NV-BUTTE 9/8/20- NORTH COMPLEX FIRE |  | ESTS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 95A | [51 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [31 empty] | Feather Falls | Butte | 39.6422 | -121.4233 | [13 empty] | BUTTE COUNTY | Yes
35199565 |  | 2020 | T1 A Tag | NO-NV-BUTTE 9/8/20- N. CMPLX FIRE SYS H |  | ESTS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 95A | [51 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [31 empty] | Feather Falls | Butte | 39.5439 | -121.4323 | [13 empty] | BUTTE COUNTY | Yes
35199649 |  |  |  | CV-YO-MADERA - 9/10/20 CREEK FIRE SYS H |  | POST |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 95A | [51 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [5 empty] | 2020-09-18 | [27 empty] | 37.1025 | -119.7907 | [13 empty] | MADERA COUNTY | Yes
35199922 |  |  |  | CV-FR - CREEK 9/13/20 - CREEK FIRE SYS H |  | ESTS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 95A | [51 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [33 empty] | 37.0441 | -119.3666 | [13 empty] | MADERA COUNTY | Yes
35200051 |  | 2020 | T1 A Tag | NO-NV-BUTTE 9/8/20- N. CMPLX FIRE SYS H |  | ESTS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 95B | [51 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [33 empty] | 39.5752 | -121.3055 | [13 empty] | BUTTE COUNTY | Yes
35204191 |  | 2020 | T1 A Tag | NO-NV- SHASTA 9/27/20 ZOGG FIRE SYS HRDN |  | ESTS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 95A | [51 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [33 empty] | 0 | 0 | [13 empty] | SHASTA COUNTY | Yes
35204225 |  | 2020 | T1 A Tag | NR-SO-SONOMA- 9/28/20- GLASS FIRE SYS H |  | ESTS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 95A | [51 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [33 empty] | 0 | 0 | [13 empty] | SONOMA COUNTY | Yes
35204446 |  | 2020 | T1 A Tag | NR-NB-NAPA- 9/27/20- GLASS FIRE SYS HARD |  | ESTS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 95A | [51 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [33 empty] | 0 | 0 | [13 empty] | NAPA COUNTY | Yes
35206134 |  |  |  | CWSP - CAMP EVERS 2106 - LR5020 - PH 3.2 |  | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 08W | [51 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | Remove |  |  | N/A | [31 empty] | Scotts Valley | Santa Cruz | 37.083 | -122.0061 | [13 empty] | SANTA CRUZ COUNTY | Yes
35206135 |  |  |  | CWSP - CAMP EVERS 2106 - LR5020 - PH 3.3 |  | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 08W | [51 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | Remove |  |  | N/A | [31 empty] | Scotts Valley | Santa Cruz | 37.0846 | -122.0061 | [13 empty] | SANTA CRUZ COUNTY | Yes
35206136 |  |  |  | CWSP - CAMP EVERS 2106 - LR5020 - PH 3.4 |  | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 08W | [51 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | Remove |  |  | N/A | [31 empty] | Scotts Valley | Santa Cruz | 37.0779 | -122.0106 | [13 empty] | SANTA CRUZ COUNTY | Yes
35206138 |  |  |  | CWSP - CAMP EVERS 2106 - LR5020 - PH 3.5 |  | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 08W | [51 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | Remove |  |  | N/A | [31 empty] | Scotts Valley | Santa Cruz | 37.0651 | -122.0174 | [13 empty] | SANTA CRUZ COUNTY | Yes
35212409 |  |  |  | FRRB - SILVERADO 2104 LR 645 |  | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 08W | [51 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [31 empty] | Saint Helena | Napa | 38.5379 | -122.4706 | [13 empty] | NAPA COUNTY | Yes
35212411 |  |  |  | FRRB - SILVERADO 2104 LR 722 |  | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 08W | [51 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [31 empty] | Deer Park | Napa | 38.545 | -122.4756 | [13 empty] | NAPA COUNTY | Yes
35217267 |  | 2021 |  | TITLE: SH - MARIPOSA 2102 LR 241564 |  | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 08W | [51 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [31 empty] | Mariposa | Mariposa | 37.4871 | -119.9619 | [13 empty] | MARIPOSA COUNTY | Yes
35217268 |  | 2021 |  | SH - BUCKS CREEK 1101 CB |  | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 08W | [51 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [31 empty] | Belden | Plumas | 0 | 0 | [13 empty] | PLUMAS COUNTY | Yes
35217269 |  | 2021 |  | SH - MIDDLETOWN 1102 - LR 302610 |  | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 08W | [51 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [31 empty] | Middletown | Lake | 38.7573 | -122.606 | [13 empty] | LAKE COUNTY | Yes
35217270 |  | 2021 |  | SH - KONOCTI 1102 LR 965078 |  | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 08W | [51 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [31 empty] | Kelseyville | Lake | 38.9301 | -122.7429 | [13 empty] | LAKE COUNTY | Yes
35217271 |  | 2021 |  | SH - MIDDLETOWN 1103 LR 830 |  | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 08W | [51 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [31 empty] | Middletown | Lake | 38.7561 | -122.6052 | [13 empty] | LAKE COUNTY | Yes
35217272 |  | 2021 |  | SH - KESWICK 1101 LR 1586 |  | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 08W | [51 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [31 empty] | Redding | Shasta | 40.6253 | -122.4633 | [13 empty] | SHASTA COUNTY | Yes
35217273 |  | 2021 |  | SH - UPPER LAKE 1101 CB |  | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 08W | [51 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [31 empty] | Upper Lake | Lake | 39.353 | -122.7722 | [13 empty] | LAKE COUNTY | Yes
35217274 |  | 2021 |  | FRRB - PN DIVISION SAN MATEO COUNTY |  | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 08W | [51 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [31 empty] | Pescadero | San Mateo | 37.2551 | -122.3815 | [13 empty] | SAN MATEO COUNTY | Yes
35217275 |  | 2021 |  | FRRB - PN DIVISION SANTA CRUZ COUNTY |  | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 08W | [51 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [31 empty] | Pescadero | San Mateo | 37.2551 | -122.3815 | [13 empty] | SANTA CRUZ COUNTY | Yes
74021903 |  |  |  | CWSP-BRUNSWICK 1105 LR-1030 ZONE |  | DOCC | 27264 | 0 | 25191 | 25191 | 4.771 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | SH | 2019-06-12 | 2019-06-12 |  | 2019-06-12 |  |  | Yes | 2019-06-12 | [6 empty] | No | [10 empty] | Full |  |  | Full |  |  |  | Full |  | Yes |  |  | covers both jobs | 1980-01-01 | Y | [10 empty] | 25191 | 4.771 | 0 | 0 | 4.771 | 0 | 4.771 | 0 | 4.771 | 0 | 6.8901e-16 | 4.5693 |  |  | 2019-02-08 |  | N/A | 2019-05-06 | 2019-07-19 | 2019-07-19 17:00 |  |  | 2019-07-19 |  |  |  | 12463097 | 12105671.3 |  | 12463097 | 0 | 386796.5 | 97.13% | 12076300.5 | 0 | 12076300.5 | 0 | 2537332.5578 | 180 | [9 empty] | Nevada City | Nevada | 0 | 0 | E.5015036.01 |  |  |  | 2019 | Q2 |  |  |  |  | Y | BRUNSWICK 11051030 | 351 | NEVADA COUNTY | Yes
74021960 |  |  |  | CWSP-BRUNSWICK 1105 LR-32536 ZONE # PH 1 |  | DOCC | 31000 | 0 | 31023 | 31023 | 5.8756 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | SH | 2019-02-08 | 2019-01-01 | 2020-10-31 | 2019-01-01 |  |  | Yes | 2019-01-01 | [6 empty] | No | [10 empty] | Full |  |  | Full |  |  | [REDACTED] completing BLM request - Expected to be clear by 4/8/19 | Full |  | Yes |  |  |  | 1980-01-01 | Y | [10 empty] | 31023 | 5.8756 | 0 | 0 | 5.8756 | 0 | 5.8756 | 0 | 5.8756 | 0 | 6.8901e-16 | 5.2926 |  |  | 2019-02-08 |  | N/A | 2019-01-25 | 2019-06-21 17:00 | 2019-06-21 |  |  | 2019-08-02 |  |  |  | 15621955 | 15860272.1 |  | 15621955 | 0 | -171023.8 | 101.5% | 15773766 | 19212.8 | 15792978.8 | 0 | 2699359.723 | 220 | [9 empty] | Nevada City | Nevada | 0 | 0 | E.5015470.01 |  |  |  | 2019 | Q2 |  |  |  |  | Y | BRUNSWICK 110532536 | 9 | NEVADA COUNTY | Yes
74021961 |  |  |  | CWSP - MIRABEL 02/MONTE RIO 13 - LR 652 |  | DOCC | 35410 | 0 | 25170 | 25170 | 4.767 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SO | 08W | SH | 2019-02-08 | 2019-01-01 |  | 2019-01-01 |  |  | Yes | 2019-01-01 | [6 empty] | No | [10 empty] | Full |  |  | Full |  |  | Land issues - [REDACTED] to handle | Full |  | Yes |  |  | Received and under review 7/23 | 1980-01-01 | Y | [10 empty] | 25170 | 4.767 | 0 | 0 | 4.767 | 0 | 4.767 | 0 | 8.0506 | 3.2835 | -6.8901e-16 | 4.767 |  |  | 2019-02-08 |  | NOTN | 2019-04-11 | 2019-10-07 | 2019-10-07 | [6 empty] | 6996439 | 25638572.1 |  | 6996439 | 0 | -15853560.4 | 366.4% | 22090646.5 | 759352.9 | 22849999.4 | 0 | 5378294.0281 | 390 | [9 empty] | Forestville | Sonoma | 38.5056 | -122.9307 | E.5014743.01 |  |  |  | 2019 | Q3 |  |  |  |  | Y | MONTE RIO 1113652 | 115 | SONOMA COUNTY | Yes
74021963 |  | 2020 | 220 Mile Plan | CWSP - OAKLAND K 1102 OCB ZONE |  | DOCC | 14784 | 0 | 14577.5 | 14577.5 | 2.7609 | 1505.8 | 0.28519 | 0 | 0 | 0 | 0 | 0.00041667 |  |  | EB | 08W | SH | 2019-05-20 | 2019-05-20 |  | 2019-05-20 |  |  | Yes | 2019-05-20 | [5 empty] | COMPLETED | No | No |  |  |  | Yes | [5 empty] | Full |  |  | Full |  |  | Waiting on access routes for EB Park, Looking into partial release. | Full |  | Yes |  |  | [REDACTED] to check if permits need to be renewed past 10/16 | 1980-01-01 | Y | [10 empty] | 13069.5 | 2.4753 | 1505.8 | 0.28519 | 2.7605 | 0.00041667 | 2.7609 | 0 | 2.7609 | 0 | -0.00041667 | 2.7609 |  | Keep | 2019-04-22 | Yes | N/A | 2019-08-26 08:00 | 2020-06-02 | 2020-06-02 |  |  | 2020-06-02 |  | Yes | Shovel Ready | 8217834 | 13689123.2 |  | 8217834 | 0 | 581983 | 166.6% | 7452358.4 | 183492.6 | 7635851 | 0 | 4958228.1253 | 86 | [9 empty] | Oakland | Alameda | 37.8027 | -122.272 | E.5014543.01 |  |  |  | 2020 | Q1 | 2019-05-20 | 2020-01-02 | 2020-06-05 |  | Y | OAKLAND K 1102CB | 265 | ALAMEDA COUNTY | Yes
74022040 |  |  |  | 2019 CALISTOGA 1101 HIGH SPLICE COUNT |  | FICL | 5438.4 | 0 | 6677 | 6677 | 1.2646 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NB | 08W | SH | 2019-03-01 | 2019-03-01 |  | 2019-03-01 |  |  | Yes | 2019-03-01 | [6 empty] | No | [10 empty] | Full |  |  | Full |  |  |  | Full |  | Yes |  |  | expires 12/4/19 | 1980-01-01 | Y | [10 empty] | 6677 | 1.2646 | 0 | 0 | 1.2646 | 0 | 1.26 | 0 | 1.26 | 0 | 0.0045833 | 1.26 |  |  |  |  | N/A | [5 empty] | 2019-03-29 |  |  |  | 1438800 | 2478341.5 |  | 2157000 | 718200 | -1039541.5 | 172.2% | 2478341.5 | 0 | 2478341.5 | 0 | 1959808.7644 | 45 | [9 empty] | Calistoga | Napa | 38.5985 | -122.6193 | E.5013428.01 |  |  |  | 2019 | Q2 |  |  |  |  | Y | CALISTOGA 1101734 | 882 | NAPA COUNTY | Yes
74022382 |  |  |  | CWSP-COLUMBIA HILL 1101-LR 2212 PH1 |  | DOCC | 12627 | 0 | 12389 | 12389 | 2.3464 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | SH | 2019-09-12 | 2019-09-12 |  | 2019-09-12 |  |  | Yes | 2019-09-12 | Section 11st ADE Submittal - sched for 7/30/197/3 - 7/24: on track 7/307/31: Friday Submittal8/5: QUES submitted for 1st ADE Review8/6 [REDACTED] assigned & Estimate uploaded to SAP8/20: Go ahead for EDRS - [PRELIM DWG ready]9/04 - 9/11: Approved - RCC Issues | QUES |  |  | Completed | COMPLETED | No |  | 0 | 0 | [7 empty] | Full |  |  | Full |  |  | CIF submitted 8/7/19. KMZ received. Currently reviewing | Full |  | Yes |  |  | Private - no permit needed | 1980-01-01 | Y | [10 empty] | 12389 | 2.3464 | 0 | 0 | 2.3464 | 0 | 2.3464 | 0 | 2.3464 | 0 | -3.4451e-16 | 2.3464 |  |  |  |  | N/A | [5 empty] | 2019-12-20 |  |  |  | 5790314.7 | 5843435.1 |  | 4292425 | -1497889.7 | 854966 | 100.9% | 4912662.3 | 22686.4 | 4935348.7 | -163216 | 2490381.5746 | 59 | [9 empty] | North San Juan | Nevada | 0 | 0 | E.5015491.01 |  |  |  | 2019 | Q4 |  |  |  |  | Y | COLUMBIA HILL 11012212 | 198 | NEVADA COUNTY | Yes
74022387 |  |  |  | CWSP-MIDDLETOWN 1101-TS 1079 |  | FICL | 20445 | 0 | 20962 | 20962 | 3.9701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2019-01-01 | 2019-01-01 |  | 2019-01-01 |  |  | Yes | 2019-01-01 | [6 empty] | No | [10 empty] | Full |  |  | Full |  |  |  | Full |  | Yes |  |  |  | 1980-01-01 | Y | [10 empty] | 20962 | 3.9701 | 0 | 0 | 3.9701 | 0 | 3.9701 | 0 | 3.9701 | 0 | 0 | 3.9701 |  |  |  |  | N/A | [5 empty] | 2019-04-30 |  |  |  | 5829000 | 5739117.3 |  | 5829000 | 0 | 100686.9 | 98.45% | 5631708.3 | 96604.8 | 5728313.1 | 0 | 1445593.9006 | 135 | [9 empty] | Middletown | Lake | 38.9024 | -122.7519 | E.5014744.01 |  |  |  | 2019 | Q2 |  |  |  |  | Y | MIDDLETOWN 11011079 | 127 | LAKE COUNTY | Yes
74022388 |  | 2020 | 220 Mile Plan | OCGC CWSP: X-1104 OH RECOND SKYLINE |  | DOCC | 3677 | 4475 | 0 | 4475 | 0.84754 | 4475 | 0.84754 | 0 | 0 | 0 | 0 | 0 |  |  | EB | 08W | SH | 2019-12-16 | 2019-10-08 |  | 2019-10-08 |  |  | Yes | 2019-10-08 |  | SANTA ROSA |  |  |  | 100 | No |  |  |  |  | Yes | [5 empty] | Full |  |  | Full |  |  | CIF submitted 8/21 | Full |  | Yes |  |  | Submitted request on 8/20. No response from [REDACTED] | 1980-01-01 | Y | [10 empty] | 0 | 0 | 4475 | 0.84754 | 0.84754 | 0 | 0.72159 | 0 | 0.72159 | 0 | 0.12595 | 0.72159 |  | Keep | 2019-12-16 | Yes | N/A | 2020-02-14 | 2020-12-01 | 2020-12-01 |  |  | 2020-11-05 |  | Yes | Shovel Ready | 5318809.2 | 6761152.6 |  | 5476214 | 157404.8 | 4718955.9 | 127.1% | 595277.4 | 4575.9 | 599853.3 | 0 | 7977404.632 | 23 |  | MSO Hold | [7 empty] | Oakland | Alameda | 37.8317 | -122.1857 | E.5014312.01 |  | UG |  | 2020 | Q1 | 2019-09-27 | 2020-04-01 | 2020-09-30 |  | Y | OAKLAND X 1104CR022 | 435 | ALAMEDA COUNTY | Yes
74022389 |  |  |  | *CANC* CWSP - PARADISE 1106 - OCB & LR 2 |  | CNCL |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | [51 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [31 empty] | Paradise | Butte | 39.761 | -121.6181 | [10 empty] | Y | PARADISE 11062234 | 28 | BUTTE COUNTY | Yes
74022390 |  | 2020 | 220 Mile Plan | CWSP - SILVERADO 2104- LR722-PH 1A |  | DOCC | 4150 | 0 | 5108 | 5108 | 0.96742 | 5108 | 0.96742 | 0 | 0 | 0 | 0 | 0 |  |  | NB | 08W | SH | 2019-08-22 | 2019-08-08 |  | 2019-08-08 |  |  | Yes | 2019-08-08 |  | SANTA ROSA |  |  |  | 100 | No |  |  |  |  | Yes | [5 empty] | Full |  |  | Full |  |  | Drawing received 7/29/19 Spotted Owl LOP | Full |  | Yes | 2020-12-31 |  | Verbal Approval on 8/26, should issue by end of week | 1980-01-01 | Y | [10 empty] | 0 | 0 | 5108 | 0.96742 | 0.96742 | 0 | 0.96742 | 0 | 0.96742 | 0 | 0 | 0.96742 |  | Keep | 2019-08-22 | Yes | N/A | 2019-12-02 | 2020-05-21 | 2020-05-21 |  |  | 2020-05-19 |  | Yes | Shovel Ready | 2849999.6 | 751868 |  | 2850000 | 0.4 | 2516497.8 | 26.38% | 325773.4 | 7728.4 | 333501.8 | 0 | 777185.4033 | 21 | [9 empty] | Saint Helena | Napa | 38.4989 | -122.4616 | E.5014772.01 |  |  |  | 2020 | Q1 | 2019-08-09 | 2020-01-02 | 2020-01-30 |  | Y | SILVERADO 2104722 | 160 | NAPA COUNTY | Yes
74024171 |  |  |  | CALISTOGA 1101 HIGH SPLICE COUNT |  | DOCC | 14098 | 0 | 13781 | 13781 | 2.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NB | 08W | SH | 2019-08-12 | 2019-06-10 |  | 2019-06-10 |  |  | Yes | 2019-06-10 | [5 empty] | 100 | No | [10 empty] | Full |  |  | Full |  |  | Caltrans permit, possible partial release. TCP needed for land release - Partial Released 8/16/19 | Full |  | Yes |  |  | Received all remaining permits on 1/3/2019. Uploaded to SAP Docs | 1980-01-01 | Y | [10 empty] | 13781 | 2.61 | 0 | 0 | 2.61 | 0 | 2.6098 | 0 | 2.6098 | 0 | 0.00018939 | 2.6098 |  |  | 2019-08-12 |  | N/A | 2019-09-03 | 2020-05-13 | 2020-05-13 |  |  | 2020-05-13 |  |  |  | 0 | 3130905 |  | 1714904 | 1714904 | -3130905 |  | 3130905 | 0 | 3130905 | 0 | 1199563.0506 | 72 | [9 empty] | Calistoga | Napa | 38.5767 | -122.6204 | E.5019956.01 |  |  |  | 2019 | Q3 |  |  |  |  | Y | CALISTOGA 1101736 | 24 | NAPA COUNTY | Yes
74028021 |  | 2020 | 220 Mile Plan | CWSP - MIRABEL 02/MONTE RIO 13-LR652 PH2 |  | CONS |  | 0 | 9716 | 9716 | 1.8402 | 9716 | 1.8402 | 0 | 0 | 0 | 0 | 0 |  |  | SO | 08W | SH | 2020-03-13 | 2020-01-30 |  | 2020-01-30 | 2020-03-05 | 2020-03-05 | Yes | 2020-01-30 | 01/15: Added to CO Est tracking; Dates unconfirmed; set 1st submittal T+30 from [REDACTED] notification he would prioritize.1/8 Email driven completion request - priority; [REDACTED] to prioritize | EEI |  |  | 2020 - Q1- M2 [R0] | COMPLETED | No | Obsolete (CONS+) | 0 | 0 |  | Yes |  |  |  | 2020-03-13 | 2020-03-13 | Partial | 2020-03-13 | 2020-03-13 | Partial |  |  | Legal Issue must be resolved regarding land rights. Partial land release. | Partial |  | Yes |  |  | Will need to review. | 1980-01-01 | Y | [10 empty] | 0 | 0 | 9716 | 1.8402 | 1.8402 | 0 | 1.8402 | 0 | 1.8402 | 0 | 0 | 1.8402 |  | Keep | 2020-02-17 | Yes | N/A | 2020-05-05 | 2021-02-04 17:00 | 2021-03-02 17:00 |  |  |  |  | Yes | Shovel Ready | 6996439 | 2014330.2 |  | 10389714 | 3393275 | 5205215.1 | 28.79% | 664270.2 | 1126953.7 | 1791223.9 | 0 | 1094654.5344 | [10 empty] | Forestville | Sonoma | 38.5056 | -122.9307 | E.5014743.02 |  |  |  | 2020 | Q2 | 2020-01-30 | 2020-03-15 | 2020-04-28 |  | Y | MONTE RIO 1113652 | 115 | SONOMA COUNTY | Yes