## 2021 Exec Status
488.6418
| 2021 | [5 empty] | Circuit Name | Division | Miles
Status | Mileage | Projects |  |  |  |  | ALLEGHANY 1101 | Sierra | 1.74
0. PG&E Responsibility to Design | 31.8 | 1 |  |  |  |  | BANGOR 1101 | Sierra | 0.57
1. PM Not Created | 11.93 | 2 |  |  |  |  | BIG BASIN 1101 | Central Coast | 1.47
2. PM Created (UNSE) | 92.9574 | 19 |  |  |  |  | BIG BEND 1102 | North Valley | 7.36
3. Design in Progress | 9.33 | 4 |  |  |  |  | BRUNSWICK 1103 | Sierra | 7.62
4. Preliminary Scope Review | 18.6 | 1 |  |  |  |  | BRUNSWICK 1110 | Sierra | 0.18939
5. Return to Engineer | 5.27 | 2 |  |  |  |  | BUCKS CREEK 1101 | North Valley | 4.06
6. AA Submitted/Field Desktop Meeting Scheduled | 125.5934 | 35 |  |  |  |  | CALISTOGA 1102 | North Bay | 0
7. AA Approved/Field Desktop Meeting Scheduled | 65.282 | 13 |  |  |  |  | CAMP EVERS 2106 | Central Coast | 1.04
8. Field Desktop Meeting Complete | 0 | 0 |  |  |  |  | CLAYTON 2212 | Diablo | 2.73
9. Estimating Preliminary Field Check | 43.9 | 8 |  |  |  |  | COARSEGOLD 2104 | Yosemite | 8.58
10. Field Review Incorporated | 9.59 | 8 |  |  |  |  | COLUMBIA HILL 1101 | Sierra | 4.9
11. Sent for Final Approval | 0 | 0 |  |  |  |  | CRESTA 1101 | North Valley | 0.9
12. Final Approval Comments | 0 | 0 | Scoped Miles |  |  |  | DESCHUTES 1104 | North Valley | 18.6
13. Project Scope Approved | 0 | 0 | Overhead | Underground | Removal | Remote Grid | DIAMOND SPRINGS 1105 | Sierra | 1.402
14. In Estimating (ESTS) | 2.88 | 3 | 2.8841 | 0 | 0 | 0 | DIAMOND SPRINGS 1107 | Sierra | 8.1
15. ADE Review (ADER) | 0 | 0 | 0 | 0 | 0 | 0 | DUNBAR 1101 | Sonoma | 1.93
16. CMCS Approved (DS73) | 0 | 0 | 0 | 0 | 0 | 0 | DUNLAP 1102 | Fresno | 2.6
17. Estimate Approval (APPR) | 0 | 0 | 0 | 0 | 0 | 0 | ELK CREEK 1101 |  | 7.9
18. Pending Dependencies (PEND) | 29.391 | 9 | 12.7779 | 15.7603 | 0.84356 | 0 | FITCH MOUNTAIN 1113 | Sonoma | 8.516
19. Construction Ready (UNSC) | 1.47 | 1 | 1.4733 | 0 | 0 | 0 | FROGTOWN 1701 | Stockton | 0.59
20. In-Construction (CONS) | 40.646 | 25 | 45.2165 | 0 | 0 | 0 | FROGTOWN 1702 | Stockton | 1.274
| 488.6398 | 131 | 62.3518 | 15.7603 | 0.84356 | 0 | FULTON 1107 | Sonoma | 3.75
[7 empty] | HALF MOON BAY 1103 | Peninsula | 6.22
[7 empty] | HIGHLANDS 1102 | Humboldt | 17.3
[7 empty] | KESWICK 1101 | North Valley | 8.13
[7 empty] | KIRKER 2104 | Diablo | 5.75
[7 empty] | KONOCTI 1102 | Humboldt | 3.16
[7 empty] | LAS GALLINAS A 1105 | North Bay | 0.76
[7 empty] | LOS GATOS 1106 | De Anza | 0.85
[7 empty] | MARIPOSA 2101 | Yosemite | 5.59
[7 empty] | MARIPOSA 2102 | Yosemite | 14.54
[7 empty] | MIDDLETOWN 1101 | Humboldt | 41.79
[7 empty] | MIDDLETOWN 1102 | Humboldt | 4.98
[7 empty] | MIDDLETOWN 1103 | Humboldt | 20.84
[7 empty] | MIWUK 1701 | Yosemite | 15.597
[7 empty] | MIWUK 1702 | Yosemite | 7.425
[7 empty] | MOUNTAIN QUARRIES 2101 | Sierra | 5.71
[7 empty] | NORTH DUBLIN 2101 | Mission | 1.82
[7 empty] | OAKHURST 1101 | Yosemite | 2.62
[7 empty] | OLETA 1101 | Stockton | 2.88
[7 empty] | OREGON TRAIL 1103 | North Valley | 57.16
[7 empty] | PINE GROVE 1102 | Stockton | 2.875
[7 empty] | PLACERVILLE 1112 | Sierra | 0.36
[7 empty] | PLACERVILLE 2106 | Sierra | 1.27
[7 empty] | POSO MOUNTAIN 2103 | Kern | 2.33
[7 empty] | POSO MOUNTAIN 2104 | Kern | 5.35
[7 empty] | POTTER VALLEY P H 1105 | Humboldt | 1.86
[7 empty] | PUEBLO 2102 | North Bay | 3.34
[7 empty] | PUTAH CREEK 1102 | Sacramento | 0.52
[7 empty] | RINCON 1103 | Sonoma | 1.5
[7 empty] | RINCON 1104 | Sonoma | 1.78
[7 empty] | SHINGLE SPRINGS 2109 | Sierra | 31.56
[7 empty] | SILVERADO 2102 | North Bay | 3
[7 empty] | SILVERADO 2104 | North Bay | 5.89
[7 empty] | SILVERADO 2105 | North Bay | 1.27
[7 empty] | STANISLAUS 1702 | Stockton | 1.92
[7 empty] | TIDEWATER 2106 | Diablo | 3.67
[7 empty] | TULUCAY 1101 | North Bay | 1.9034
[7 empty] | UPPER LAKE 1101 | North Coast | 1.11
[7 empty] | VACA DIXON 1101 | Sacramento | 0.4
[7 empty] | VACA DIXON 1105 | Sacramento | 23.92
[7 empty] | VACAVILLE 1104 | Sacramento | 14.64
[7 empty] | VARIOUS | Various | 31.8
[7 empty] | VOLTA 1101 | North Valley | 3.48
[7 empty] | WILDWOOD 1101 | North Valley | 7.9
[7 empty] | WYANDOTTE 1103 | North Valley | 13.97
[7 empty] | WYANDOTTE 1109 | North Valley | 2.08

## Project List
Order | KEEP | Exec. Status | Plan Status | Priority | Planned Units (SAP EST) | Residual Miles (SAP EST) | Primary Planned Year | Miles Primary Year | Miles Secondary Year | Completed Units (SAP ACT) | Actual Cost ($) | Order Status | Circuit | Circuit Name | Circuit Protection Zone | Pixel(s) | Total HFTD Zone Miles | Mean MAVF Core Risk Rank | Total MAVF Core Risk Value | Mean MAVF Core Risk Value | mavf_consequence_rank | Risk Reduction Per Project | CPZ Rank | HFTD Tier | Project Type | City | County | Division | Region | Planning Order | WBS Element | Notification | Order | Short Text | OH | UG | Remove | Remote Grid | Prelim Scope (Link) | AA (Link) | Targeted Units (ckt Ft) | Targeted Units (miles) | Unit Cost (Class 5) | Field Scoping (Link) | Removal (ckt ft) | UG (ckt ft) | OH (ckt ft) | Scoped Units (ckt ft) | Scoped (miles) | Unit Cost (Class 5) | CMCS (Link) | BC (Link) | Removal (ckt ft) | UG (ckt ft) | OH (ckt ft) | PLANNED Units (SAP EST) | Planned Units (miles) | Expected Case (Class 2) | High Case (Class 2) | Unit Cost (per ft) | Cont. Release (Link) | Re-auth (Link) | Re-Auth (SK) | Completed Units (SAP ACT) | Actuals ($K) | Final Unit Cost
35212495 | FRRB - 2020 |  | PLAN | 2020999 | 7.65 | 0 | 2020 |  |  | 7.65 | 0 | UNSE | 254151101 | AUBERRY 1101 | AUBERRY 1101233716 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! |  |  | FRRB | AUBERRY | Fresno | Fresno | Central Valley | 5793921 | E.5034575.01.04 | 119985141 | 35212495 | FRRB - AUBERRY 1101 LR233716 | - | - | - | - | [9 empty] | 0 | 0
35212464 | FRRB - 2020 |  | PLAN | 2020999 | 0.48 | 0 | 2020 |  |  | 0.48 | 0 | UNSE | 42711101 | CALISTOGA 1101 | CALISTOGA 1101886282 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! |  |  | FRRB | CALISTOGA | Napa | North Bay | Bay Area | 5793893 | E.5034566.01.07 | 119983588 | 35212464 | FRRB - CALISTOGA 1101 LR 886282 | - | - | - | - | [9 empty] | 0 | 0
35212487 | FRRB - 2020 |  | PLAN | 2020999 | 1.82 | 0 | 2020 |  |  | 1.82 | 0 | UNSE | 103221101 | KANAKA 1101 | KANAKA 11011034 | 80 | 11.1511 | 1566 | 1.9751 | 0.024689 | 1434 | #VALUE! |  |  | FRRB | OROVILLE | Butte | North Valley | Northern | 5793918 | E.5034572.01.06 | 119983959 | 35212487 | FRRB - KANAKA 1101 LR1034 | - | - | - | - | [9 empty] | 0 | 0
35212460 | FRRB - 2020 |  | PLAN | 2020999 | 17.43 | 3 | 2020 |  |  | 14.43 | 0 | UNSE | 43321101 | RINCON 1101 | RINCON 110114605 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! |  |  | FRRB | SANTA ROSA | Sonoma | Sonoma | Northern | 5793893 | E.5034566.01.03 | 119983565 | 35212460 | FRRB - RINCON 1101 LR 14605 | - | - | - | - | [9 empty] | 0 | 0
35212466 | FRRB - 2020 |  | PLAN | 2020999 | 8.94 | 0.68 | 2020 |  |  | 8.26 | 0 | UNSE | 63601108 | VACAVILLE 1108 | VACAVILLE 11088762 | 147 | 13.8344 | 64 | 57.5327 | 0.39138 | 108 | #VALUE! |  |  | FRRB | VACAVILLE | Solano | Sacramento | Northern | 5793894 | E.5034567.01.02 | 119984990 | 35212466 | FRRB - VACAVILLE 1108 LR 8762 | - | - | - | - | [9 empty] | 0 | 0
35212490 | FRRB - 2020 |  | PLAN | 2020999 | 5.44 | 0.72 | 2020 |  |  | 4.72 | 0 | UNSE | 103401101 | GIRVAN 1101 | GIRVAN 1101323094 | 208 | 36.1569 | 117 | 66.6373 | 0.32037 | 234 | #VALUE! |  |  | FRRB | IGO | Shasta | North Valley | Northern | 5793919 | E.5034573.01.02 | 119984003 | 35212490 | FRRB - GIRVAN 1101 LR323094 | - | - | - | - | [9 empty] | 0 | 0
35212465 | FRRB - 2020 |  | PLAN | 2020999 | 6.34 | 0 | 2020 |  |  | 6.34 | 0 | UNSE | 63601108 | VACAVILLE 1108 | VACAVILLE 110838316 | 232 | 15.9209 | 122 | 73.4796 | 0.31672 | 99 | #VALUE! |  |  | FRRB | VACAVILLE | Solano | Sacramento | Northern | 5793894 | E.5034567.01.01 | 119933526 | 35212465 | FRRB - VACAVILLE 1108 LR 38316 | - | - | - | - | [9 empty] | 0 | 0
35212406 | FRRB - 2020 |  | PLAN | 2020999 |  | 0 | 2020 |  |  |  | 0 | UNSE | 43051101 | MONTICELLO 1101 | MONTICELLO 110137384 | 71 | 9.3736 | 557 | 10.17 | 0.14324 | 391 | #VALUE! |  |  | FRRB | NAPA | Napa | North Bay | Bay Area | 5793892 | E.5034565.01.06 | 119983061 | 35212406 | FRRB - MONTICELLO 1101 LR 37384 | - | - | - | - |  |  |  | 0 | [5 empty] | 0 | 0
35212408 | FRRB - 2020 |  | PLAN | 2020999 | 1.58 | 0 | 2020 |  |  | 1.58 | 0 | UNSE | 43432102 | SILVERADO 2102 | SILVERADO 210234959 | 205 | 25.7758 | 579 | 27.9958 | 0.13657 | 473 | #VALUE! |  |  | FRRB | SAINT HELENA | Napa | North Bay | Bay Area | 5793892 | E.5034565.01.08 | 119983069 | 35212408 | FRRB - SILVERADO 2102 LR 34959 | - | - | - | - |  |  |  | 0 | [5 empty] | 0 | 0
35212489 | FRRB - 2020 |  | PLAN | 2020999 | 4.16 | -2.24 | 2020 |  |  | 6.4 | 0 | UNSE | 103401101 | GIRVAN 1101 | GIRVAN 11011330 | 264 | 31.0696 | 624 | 33.0087 | 0.12503 | 651 | #VALUE! |  |  | FRRB | REDDING | Shasta | North Valley | Northern | 5793919 | E.5034573.01.01 | 119933733 | 35212489 | FRRB - GIRVAN 1101 LR1330 | - | - | - | - | [9 empty] | 0 | 0
35212411 | FRRB - 2020 |  | PLAN | 2020999 | 0.17 | 0 | 2020 |  |  | 0.17 | 0 | UNSE | 43432104 | SILVERADO 2104 | SILVERADO 2104722 | 99 | 7.8964 | 690 | 11.1613 | 0.11274 | 1130 | #VALUE! |  |  | FRRB | DEER PARK | Napa | North Bay | Bay Area | 5793892 | E.5034565.01.11 | 119983147 | 35212411 | FRRB - SILVERADO 2104 LR 722 | - | - | - | - |  |  |  | 0 | [5 empty] | 0 | 0
35212404 | FRRB - 2020 |  | PLAN | 2020999 | 5 | 0 | 2020 |  |  | 5 | 0 | UNSE | 43051101 | MONTICELLO 1101 | MONTICELLO 1101630 | 93 | 18.7154 | 732 | 9.7794 | 0.10515 | 552 | #VALUE! |  |  | FRRB | NAPA | Napa | North Bay | Bay Area | 5793892 | E.5034565.01.04 | 119982981 | 35212404 | FRRB - MONTICELLO 1101 LR 630 | - | - | - | - |  |  |  | 0 | [5 empty] | 0 | 0
35122401 | FRRB - 2020 |  | PLAN | 2020999 | 7.31 | 0 | 2020 |  |  | 7.31 | 0 | UNSE | 43051101 | MONTICELLO 1101 | MONTICELLO 1101CB | 5 | 0.53443 | 775 | 0.49137 | 0.098274 | 904 | #VALUE! |  |  | FRRB | STRAWBERRY VALLEY | Yuba | North Valley | Northern | 5793892 | E.5034565.01.01 | 119933522 | 35122401 | FRRB - MONTICELLO 1101 CB | - | - | - | - |  |  |  | 0 |  | 2019-39360 |  |  |  | 0 | 0
35212402 | FRRB - 2020 |  | PLAN | 2020999 | 2.42 | 0 | 2020 |  |  | 2.42 | 0 | UNSE | 43051101 | MONTICELLO 1101 | MONTICELLO 1101666 | 90 | 12.0959 | 815 | 8.2843 | 0.092048 | 588 | #VALUE! |  |  | FRRB | NAPA | Napa | North Bay | Bay Area | 5793892 | E.5034565.01.02 | 119982885 | 35212402 | FRRB - MONTICELLO 1101 LR 666 | - | - | - | - |  |  |  | 0 | [5 empty] | 0 | 0
35212491 | FRRB - 2020 |  | PLAN | 2020999 | 0.96 | 0 | 2020 |  |  | 0.96 | 0 | UNSE | 252531103 | SAN JOAQUIN #3 | SAN JOAQUIN #3 11035100 | 204 | 21.334 | 829 | 18.2004 | 0.089218 | 667 | #VALUE! |  |  | FRRB | NORTH FORK | Madera | Yosemite | Central Valley | 5793920 | E.5034574.01.01 | 119933734 | 35212491 | FRRB - SAN JOAQUIN #3 1103 LR5100 | - | - | - | - | [9 empty] | 0 | 0
35212479 | FRRB - 2020 |  | PLAN | 2020999 | 7 | 3.84 | 2020 |  |  | 3.16 | 0 | UNSE | 103751102 | BIG BEND 1102 | BIG BEND 1102CB | 139 | 17.0366 | 865 | 11.7994 | 0.084888 | 1081 | #VALUE! |  |  | FRRB | OROVILLE | Butte | North Valley | Northern | 5793918 | E.5034572.01.01 | 119933732 | 35212479 | FRRB - BIG BEND 1102 CB | - | - | - | - | [9 empty] | 0 | 0
35212405 | FRRB - 2020 |  | PLAN | 2020999 | 11.9 | 0 | 2020 |  |  | 11.9 | 0 | UNSE | 43051101 | MONTICELLO 1101 | MONTICELLO 110193384 | 101 | 16.1387 | 914 | 7.9369 | 0.078583 | 632 | #VALUE! |  |  | FRRB | NAPA | Napa | North Bay | Bay Area | 5793892 | E.5034565.01.05 | 119982987 | 35212405 | FRRB - MONTICELLO 1101 LR 93384 | - | - | - | - |  |  |  | 0 | [5 empty] | 0 | 0
35212494 | FRRB - 2020 |  | PLAN | 2020999 | 1.38 | 0 | 2020 |  |  | 1.38 | 0 | UNSE | 254151101 | AUBERRY 1101 | AUBERRY 110137536 | 60 | 5.3994 | 934 | 4.5309 | 0.075515 | 511 | #VALUE! |  |  | FRRB | AUBERRY | Fresno | Fresno | Central Valley | 5793921 | E.5034575.01.03 | 119984007 | 35212494 | FRRB - AUBERRY 1101 LR37536 | - | - | - | - | [9 empty] | 0 | 0
35212418 | FRRB - 2020 |  | PLAN | 2020999 | 13.7 | 0 | 2020 |  |  | 13.7 | 0 | UNSE | 42751113 | FITCH MOUNTAIN 1113 | FITCH MOUNTAIN 11136751 | 139 | 22.6749 | 945 | 10.2759 | 0.073927 | 1284 | #VALUE! |  |  | FRRB | HEALDSBURG | Sonoma | Sonoma | Northern | 5793893 | E.5034566.01.01 | 119933523 | 35212418 | FRRB - FITCH MOUNTAIN 1113 LR 6751 | - | - | - | - | [9 empty] | 0 | 0
35212481 | FRRB - 2020 |  | PLAN | 2020999 | 11.52 | 0.87 | 2020 |  |  | 10.65 | 0 | UNSE | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031508 | 249 | 27.2173 | 1176 | 12.4656 | 0.050062 | 1498 | #VALUE! |  |  | FRRB | OROVILLE | Butte | North Valley | Northern | 5793918 | E.5034572.01.03 | 119983951 | 35212481 | FRRB - WYANDOTTE 1103 LR1508 | - | - | - | - | [9 empty] | 0 | 0
35212492 | FRRB - 2020 |  | PLAN | 2020999 | 3.05 | 0 | 2020 |  |  | 3.05 | 0 | UNSE | 254151101 | AUBERRY 1101 | AUBERRY 1101R2845 | 172 | 17.8248 | 1209 | 8.1154 | 0.047182 | 811 | #VALUE! |  |  | FRRB | AUBERRY | Fresno | Fresno | Central Valley | 5793921 | E.5034575.01.01 | 119933735 | 35212492 | FRRB - AUBERRY 1101 R2845 | - | - | - | - | [9 empty] | 0 | 0
35212403 | FRRB - 2020 |  | PLAN | 2020999 | 3.58 | 0 | 2020 |  |  | 3.58 | 0 | UNSE | 43051101 | MONTICELLO 1101 | MONTICELLO 1101654 | 71 | 8.2164 | 1227 | 3.2338 | 0.045547 | 1126 | #VALUE! |  |  | FRRB | NAPA | Napa | North Bay | Bay Area | 5793892 | E.5034565.01.03 | 119982889 | 35212403 | FRRB - MONTICELLO 1101 LR 654 | - | - | - | - |  |  |  | 0 | [5 empty] | 0 | 0
35212412 | FRRB - 2020 |  | PLAN | 2020999 | 4.13 | -0.58 | 2020 |  |  | 4.71 | 0 | UNSE | 43432104 | SILVERADO 2104 | SILVERADO 210437632 | 304 | 26.5819 | 1235 | 13.5588 | 0.044601 | 1426 | #VALUE! |  |  | FRRB | SAINT HELENA | Napa | North Bay | Bay Area | 5793892 | E.5034565.01.12 | 119983231 | 35212412 | FRRB - SILVERADO 2104 LR 37632 | - | - | - | - |  |  |  | 0 | [5 empty] | 0 | 0
35212480 | FRRB - 2020 |  | PLAN | 2020999 | 6.12 | 3.74 | 2020 |  |  | 2.38 | 0 | UNSE | 103751102 | BIG BEND 1102 | BIG BEND 11021972 | 177 | 21.2964 | 1288 | 7.25 | 0.040961 | 1326 | #VALUE! |  |  | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5793918 | E.5034572.01.02 | 119983950 | 35212480 | FRRB - BIG BEND 1102 LR1972 | - | - | - | - | [9 empty] | 0 | 0
35212463 | FRRB - 2020 |  | PLAN | 2020999 | 7.5 | 0 | 2020 |  |  | 7.5 | 0 | UNSE | 43321103 | RINCON 1103 | RINCON 1103474 | 174 | 18.3351 | 1342 | 6.4055 | 0.036813 | 1399 | #VALUE! |  |  | FRRB | SANTA ROSA | Sonoma | Sonoma | Northern | 5793893 | E.5034566.01.06 | 119983582 | 35212463 | FRRB - RINCON 1103 LR 474 | - | - | - | - | [9 empty] | 0 | 0
35212413 | FRRB - 2020 |  | PLAN | 2020999 | 1.38 | -2.25 | 2020 |  |  | 3.63 | 0 | UNSE | 43432105 | SILVERADO 2105 | SILVERADO 2105658898 | 151 | 17.1737 | 1361 | 5.4002 | 0.035763 | 1546 | #VALUE! |  |  | FRRB | SAINT HELENA | Napa | North Bay | Bay Area | 5793892 | E.5034565.01.13 | 119983363 | 35212413 | FRRB - SILVERADO 2105 LR 658898 | - | - | - | - |  |  |  | 0 | [5 empty] | 0 | 0
35212496 | FRRB - 2020 |  | PLAN | 2020999 | 2.26 | -0.37 | 2020 |  |  | 2.63 | 0 | UNSE | 192411101 | LOW GAP 1101 | LOW GAP 1101CB | 23 | 2.1692 | 1385 | 0.78267 | 0.034029 | 1600 | #VALUE! |  |  | FRRB | ZENIA | Trinity | Humboldt | Northern | 5793922 | E.5034576.01.01 | 119933736 | 35212496 | FRRB - LOW GAP 1101 | - | - | - | - | [9 empty] | 0 | 0
35212471 | FRRB - 2020 |  | PLAN | 2020999 | 1.83 | 0 | 2020 |  |  | 1.83 | 0 | UNSE | 82931101 | POINT MORETTI 1101 | POINT MORETTI 11015076 | 67 | 7.4948 | 1393 | 2.2618 | 0.033758 | 1508 | #VALUE! |  |  | FRRB | DAVENPORT | Santa Cruz | Central Coast | Central Coast | 5793896 | E.5034569.01.04 | 119983629 | 35212471 | FRRB - POINT MORETTI 1101 LR5076 | - | - | - | - | [9 empty] | 0 | 0
35212473 | FRRB - 2020 |  | PLAN | 2020999 | 2.21 | 0 | 2020 |  |  | 2.21 | 0 | UNSE | 82841102 | BIG BASIN 1102 | BIG BASIN 110210254 | 11 | 2.1441 | 1421 | 0.35552 | 0.03232 | 1814 | #VALUE! |  |  | FRRB | SANTA CRUZ | Santa Cruz | Central Coast | Central Coast | 5793896 | E.5034569.01.06 | 119983704 | 35212473 | FRRB - BIG BASIN 1102 LR10254 | - | - | - | - | [9 empty] | 0 | 0
35212416 | FRRB - 2020 |  | PLAN | 2020999 | 1.252 | 0 | 2020 |  |  | 1.252 | 0 | UNSE | 42711102 | CALISTOGA 1102 | CALISTOGA 1102634 | 178 | 11.216 | 1477 | 5.2284 | 0.029373 | 1599 | #VALUE! |  |  | FRRB | CALISTOGA | Napa | North Bay | Bay Area | 5793892 | E.5034565.01.16 | 119983454 | 35212416 | FRRB - CALISTOGA 1102 LR 634 | - | - | - | - | [9 empty] | 0 | 0
35212486 | FRRB - 2020 |  | PLAN | 2020999 | 9.46 | 5.02 | 2020 |  |  | 4.44 | 0 | UNSE | 103221101 | KANAKA 1101 | KANAKA 1101CB | 37 | 4.7271 | 1480 | 1.0834 | 0.029281 | 1533 | #VALUE! |  |  | FRRB | OROVILLE | Butte | North Valley | Northern | 5793918 | E.5034572.01.05 | 119983955 | 35212486 | FRRB - KANAKA 1101 CB | - | - | - | - | [9 empty] | 0 | 0
35212407 | FRRB - 2020 |  | PLAN | 2020999 | 0.96 | -0.19 | 2020 |  |  | 1.15 | 0 | UNSE | 43432102 | SILVERADO 2102 | SILVERADO 2102636 | 81 | 5.465 | 1550 | 2.0483 | 0.025287 | 1827 | #VALUE! |  |  | FRRB | SAINT HELENA | Napa | North Bay | Bay Area | 5793892 | E.5034565.01.07 | 119983066 | 35212407 | FRRB - SILVERADO 2102 LR 636 | - | - | - | - |  |  |  | 0 | [5 empty] | 0 | 0
35212462 | FRRB - 2020 |  | PLAN | 2020999 | 12.16 | -0.35 | 2020 |  |  | 12.51 | 0 | UNSE | 43321103 | RINCON 1103 | RINCON 1103198 | 62 | 6.4238 | 1618 | 1.3987 | 0.02256 | 1658 | #VALUE! |  |  | FRRB | SANTA ROSA | Sonoma | Sonoma | Northern | 5793893 | E.5034566.01.05 | 119983580 | 35212462 | FRRB - RINCON 1103 LR 198 | - | - | - | - | [9 empty] | 0 | 0
35212417 | FRRB - 2020 |  | PLAN | 2020999 | 4.2 | 0.18 | 2020 |  |  | 4.02 | 0 | UNSE | 42711102 | CALISTOGA 1102 | CALISTOGA 1102769230 | 160 | 11.021 | 1624 | 3.574 | 0.022338 | 1749 | #VALUE! |  |  | FRRB | CALISTOGA | Napa | North Bay | Bay Area | 5793892 | E.5034565.01.17 | 119983463 | 35212417 | FRRB - CALISTOGA 1102 LR 769230 | - | - | - | - | [9 empty] | 0 | 0
35212410 | FRRB - 2020 |  | PLAN | 2020999 | 0.41 | 0 | 2020 |  |  | 0.41 | 0 | UNSE | 43432104 | SILVERADO 2104 | SILVERADO 2104708 | 61 | 3.7544 | 1648 | 1.292 | 0.02118 | 1771 | #VALUE! |  |  | FRRB | SAINT HELENA | Napa | North Bay | Bay Area | 5793892 | E.5034565.01.10 | 119983145 | 35212410 | FRRB - SILVERADO 2104 LR 708 | - | - | - | - |  |  |  | 0 | [5 empty] | 0 | 0
35212419 | FRRB - 2020 |  | PLAN | 2020999 |  | 0 | 2020 |  |  |  | 0 | UNSE | 43071101 | DUNBAR 1101 | DUNBAR 1101416 | 28 | 2.6414 | 1684 | 0.54085 | 0.019316 | 1689 | #VALUE! |  |  | FRRB | KENWOOD | Sonoma | Sonoma | Northern | 5793893 | E.5034566.01.02 | 119983560 | 35212419 | FRRB - DUNBAR 1101 - LR 416 | - | - | - | - | [9 empty] | 0 | 0
35212488 | FRRB - 2020 |  | PLAN | 2020999 | 4.74 | 0.34 | 2020 |  |  | 4.4 | 0 | UNSE | 103221101 | KANAKA 1101 | KANAKA 11011406 | 204 | 27.2731 | 1728 | 3.5397 | 0.017352 | 1755 | #VALUE! |  |  | FRRB | OROVILLE | Butte | North Valley | Northern | 5793918 | E.5034572.01.07 | 119984001 | 35212488 | FRRB - KANAKA 1101 LR1406 | - | - | - | - | [9 empty] | 0 | 0
35212478 | FRRB - 2020 |  | PLAN | 2020999 | 7.99 | 0 | 2020 |  |  | 7.99 | 0 | UNSE | 83392110 | SWIFT 2110 | SWIFT 2110XR332 | 83 | 18.4582 | 1769 | 1.2892 | 0.015532 | 1452 | #VALUE! |  |  | FRRB | LIVERMORE | Santa Clara | San Jose | Central Coast | 5793897 | E.5034571.01.01 | 119933730 | 35212478 | FRRB - SWIFT 2110 XR332 | - | - | - | - | [9 empty] | 0 | 0
35212483 | FRRB - 2020 |  | PLAN | 2020999 | 12.53 | 11 | 2020 |  |  | 1.53 | 0 | UNSE | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 259 | 22.4168 | 1849 | 3.3188 | 0.012814 | 1756 | #VALUE! |  |  | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5793918 | E.5034572.01.04 | 119983953 | 35212483 | FRRB - WYANDOTTE 1103 LR1974 | - | - | - | - | [9 empty] | 0 | 0
35212414 | FRRB - 2020 |  | PLAN | 2020999 | 1.22 | 0.24 | 2020 |  |  | 0.98 | 0 | UNSE | 43432105 | SILVERADO 2105 | SILVERADO 2105131568 | 57 | 4.1385 | 1947 | 0.58604 | 0.010281 | 2060 | #VALUE! |  |  | FRRB | SAINT HELENA | Napa | North Bay | Bay Area | 5793892 | E.5034565.01.14 | 119983432 | 35212414 | FRRB - SILVERADO 2105 LR 131568 | - | - | - | - |  |  |  | 0 | [5 empty] | 0 | 0
35212409 | FRRB - 2020 |  | PLAN | 2020999 | 0.97 | 0 | 2020 |  |  | 0.97 | 0 | UNSE | 43432104 | SILVERADO 2104 | SILVERADO 2104645 | 13 | 1.0111 | 2117 | 0.085285 | 0.0065604 | 2103 | #VALUE! |  |  | FRRB | SAINT HELENA | Napa | North Bay | Bay Area | 5793892 | E.5034565.01.09 | 119983129 | 35212409 | FRRB - SILVERADO 2104 LR 645 | - | - | - | - |  |  |  | 0 | [5 empty] | 0 | 0
35212415 | FRRB - 2020 |  | PLAN | 2020999 | 2.31 | 0 | 2020 |  |  | 2.31 | 0 | UNSE | 43432105 | SILVERADO 2105 | SILVERADO 2105167360 | 70 | 9.5796 | 2174 | 0.39281 | 0.0056116 | 2203 | #VALUE! |  |  | FRRB | SAINT HELENA | Napa | North Bay | Bay Area | 5793892 | E.5034565.01.15 | 119983433 | 35212415 | FRRB - SILVERADO 2105 LR 167360 | - | - | - | - |  |  |  | 0 | [5 empty] | 0 | 0
35212467 | FRRB - 2020 |  | PLAN | 2020999 | 1.22 | 0 | 2020 |  |  | 1.22 | 0 | UNSE | 182371111 | LAURELES 1111 | LAURELES 11112020 | 281 | 34.3538 | 2187 | 1.5107 | 0.005376 | 2260 | #VALUE! |  |  | FRRB | CARMEL VALLEY | Monterey | Central Coast | Central Coast | 5793895 | E.5034568.01.01 | 119933604 | 35212467 | FRRB - LAURELES 1111 LR 2020 | - | - | - | - | [9 empty] | 0 | 0
35212469 | FRRB - 2020 |  | PLAN | 2020999 | 5.23 | 2.95 | 2020 |  |  | 2.28 | 0 | UNSE | 82931101 | POINT MORETTI 1101 | POINT MORETTI 110112122 | 63 | 6.5695 | 2199 | 0.32133 | 0.0051004 | 2205 | #VALUE! |  |  | FRRB | DAVENPORT | Santa Cruz | Central Coast | Central Coast | 5793896 | E.5034569.01.02 | 119983626 | 35212469 | FRRB - POINT MORETTI 1101 LR12122 | - | - | - | - | [9 empty] | 0 | 0
35212493 | FRRB - 2020 |  | PLAN | 2020999 | 8.92 | 3.6 | 2020 |  |  | 5.32 | 0 | UNSE | 254151101 | AUBERRY 1101 | AUBERRY 1101R324 | 119 | 10.7137 | 2209 | 0.5799 | 0.0048731 | 1904 | #VALUE! |  |  | FRRB | AUBERRY | Fresno | Fresno | Central Valley | 5793921 | E.5034575.01.02 | 119984006 | 35212493 | FRRB - AUBERRY 1101 R324 | - | - | - | - | [9 empty] | 0 | 0
35212470 | FRRB - 2020 |  | PLAN | 2020999 | 0.77 | 0 | 2020 |  |  | 0.77 | 0 | UNSE | 82931101 | POINT MORETTI 1101 | POINT MORETTI 110183716 | 22 | 2.503 | 2210 | 0.10689 | 0.0048588 | 2187 | #VALUE! |  |  | FRRB | SANTA CRUZ | Santa Cruz | Central Coast | Central Coast | 5793896 | E.5034569.01.03 | 119983627 | 35212470 | FRRB - POINT MORETTI 1101 LR83716 | - | - | - | - | [9 empty] | 0 | 0
35212461 | FRRB - 2020 |  | PLAN | 2020999 |  | 0 | 2020 |  |  |  | 0 | UNSE | 43321101 | RINCON 1101 | RINCON 1101663641 | 13 | 0.72937 | 2309 | 0.043609 | 0.0033545 | 2307 | #VALUE! |  |  | FRRB | SANTA ROSA | Sonoma | Sonoma | Northern | 5793893 | E.5034566.01.04 | 119983567 | 35212461 | FRRB - RINCON 1101 LR 663641 | - | - | - | - | [9 empty] | 0 | 0
35212474 | FRRB - 2020 |  | PLAN | 2020999 | 0.52 | 0 | 2020 |  |  | 0.52 | 0 | UNSE | 82841102 | BIG BASIN 1102 | BIG BASIN 110212758 | 70 | 5.982 | 2358 | 0.20629 | 0.002947 | 2611 | #VALUE! |  |  | FRRB | BOULDER CREEK | Santa Cruz | Central Coast | Central Coast | 5793896 | E.5034569.01.07 | 119983709 | 35212474 | FRRB - BIG BASIN 1102 LR12758 | - | - | - | - | [9 empty] | 0 | 0
35212472 | FRRB - 2020 |  | PLAN | 2020999 | 2.51 | 1.37 | 2020 |  |  | 1.14 | 0 | UNSE | 82841102 | BIG BASIN 1102 | BIG BASIN 11025066 | 121 | 13.7481 | 2359 | 0.35169 | 0.0029066 | 2514 | #VALUE! |  |  | FRRB | BOULDER CREEK | Santa Cruz | Central Coast | Central Coast | 5793896 | E.5034569.01.05 | 119983702 | 35212472 | FRRB - BIG BASIN 1102 LR5066 | - | - | - | - | [9 empty] | 0 | 0
35212475 | FRRB - 2020 |  | PLAN | 2020999 | 3.09 | 0 | 2020 |  |  | 3.09 | 0 | UNSE | 82841101 | BIG BASIN 1101 | BIG BASIN 1101CB | 45 | 4.6531 | 2398 | 0.11632 | 0.0025849 | 2594 | #VALUE! |  |  | FRRB | SANTA CRUZ | Santa Cruz | Central Coast | Central Coast | 5793896 | E.5034569.01.08 | 119983868 | 35212475 | FRRB - BIG BASIN 1101 CB | - | - | - | - | [9 empty] | 0 | 0
35212477 | FRRB - 2020 |  | PLAN | 2020999 | 0.59 | 0 | 2020 |  |  | 0.59 | 0 | UNSE | 82841101 | BIG BASIN 1101 | BIG BASIN 110110720 | 44 | 4.71 | 2435 | 0.10045 | 0.002283 | 2730 | #VALUE! |  |  | FRRB | SANTA CRUZ | Santa Cruz | Central Coast | Central Coast | 5793896 | E.5034569.01.10 | 119983869 | 35212477 | FRRB - BIG BASIN 1101 LR10720 | - | - | - | - | [9 empty] | 0 | 0
35212468 | FRRB - 2020 |  | PLAN | 2020999 | 0.89 | 0 | 2020 |  |  | 0.89 | 0 | UNSE | 82931101 | POINT MORETTI 1101 | POINT MORETTI 110136516 | 53 | 4.1639 | 2542 | 0.08431 | 0.0015908 | 2704 | #VALUE! |  |  | FRRB | SANTA CRUZ | Santa Cruz | Central Coast | Central Coast | 5793896 | E.5034569.01.01 | 119933606 | 35212468 | FRRB - POINT MORETTI 1101 LR36516 | - | - | - | - | [9 empty] | 0 | 0
35212476 | FRRB - 2020 |  | PLAN | 2020999 | 2.58 | 0 | 2020 |  |  | 2.58 | 0 | UNSE | 82841101 | BIG BASIN 1101 | BIG BASIN 11015000 | 23 | 1.9571 | 2579 | 0.031772 | 0.0013814 | 2834 | #VALUE! |  |  | FRRB | SANTA CRUZ | Santa Cruz | Central Coast | Central Coast | 5793896 | E.5034569.01.09 | 119985051 | 35212476 | FRRB - BIG BASIN 1101 LR5000 | - | - | - | - | [9 empty] | 0 | 0
35223060 | PSPS - Community Resiliency | 6 | PLAN | 2021088 | 1.74 | 1.74 | 2021 |  |  | 0 | 0 | UNSE | 152101101 | ALLEGHANY 1101 | ALLEGHANY 1101VR816 | 49 | 4.1491 | 2010 | 0.43385 | 0.0088541 | 2312 | #DIV/0! |  |  | PSPS | DOWNIEVILLE | Sierra | Sierra | Northern | 5794984 | E.5034760.01.01 | 120242671 | 35223060 | PSPS - Alleghany 1101VR816 | [5 empty] | 2021-01568 | 9187.2 | 1.74 | 4040000 |  |  |  |  | 0
35223030 | PSPS - Community Resiliency | 6 | PLAN | 2021084 | 0.57 | 0.57 | 2021 |  |  | 0 | 0 | UNSE | 103191101 | BANGOR 1101 | BANGOR 1101CB | 171 | 18.7561 | 355 | 33.1366 | 0.19378 | 565 | #DIV/0! |  |  | PSPS | BANGOR | Butte | Sierra | Northern | 5794981 | E.5034757.01.01 | 120242544 | 35223030 | PSPS - Bangor 1101CB | [5 empty] | 2021-01574 | 3009.6 | 0.57 | 1556240 |  |  |  |  | 0
35052731 | DSDD | 19 | PLAN | 2021026 | 1.47 | 1.47 | 2020 | 0 |  | 0 | 135172.96 | UNSC | 82841101 | BIG BASIN 1101 | BIG BASIN 110110296 | 181 | 14.4211 | 2456 | 0.3928 | 0.0021702 | 2657 | 0.026827 | 354 | Tier 3 | CWSP | BOULDER CREEK | Santa Cruz | Central Coast | Central Coast | 5782530 | E.5014542.01 | 114607365 | 35052731 | CWSP-BIG BASIN 1101-LR10296-PH 1.1 | 7779 | 0 | 0 | 0 |  | 2018-42216 | 12830.4 | 2.43 | 3837000 | N/A |  |  |  | 0 | 0 |  | 2020-46872 | 2020-54946 | 0 | 0 | 7779 | 7779 | 1.4733 | 3391041 | 4994628 | 435.9225
35199565 | FRRB - OH - 2021 | 18 | PLAN | 2021073 | 2.56 | 2.56 | 2021 |  |  | 0 | 7339371.72 | ESTS | 103751102 | BIG BEND 1102 | BIG BEND 11021972 | 177 | 21.2964 | 1288 | 7.25 | 0.040961 | 1326 | 0.58391 |  |  | FRRB | OROVILLE | Butte | North Valley | Northern | 5541890 |  | 119750044 | 35199565 | NO-NV-BUTTE 9/8/20- N. CMPLX FIRE SYS H | 13516.8 | 0 | 0 | 0 | [9 empty] | 0
35200051 | FRRB - UG - 2021 | 18 | PLAN | 2021074 | 4.8 | 4.8 | 2021 |  |  | 0 | 3333378.58 | ESTS | 103751102 | BIG BEND 1102 | BIG BEND 11021972 | 177 | 21.2964 | 1288 | 7.25 | 0.040961 | 1326 | 1.6177 |  |  | FRRB | OROVILLE | Butte | North Valley | Northern | 5541890 |  | 119765913 | 35200051 | NO-NV-BUTTE 9/8/20- N. CMPLX FIRE SYS H | 0 | 25344 | 0 | 0 | [9 empty] | 0
35223343 | FRRB - UG - 2021 | 2 | PLAN | [8 empty] | UNSE | 103751102 | BIG BEND 1102 | BIG BEND 11021972 | 177 | 21.2964 | 1288 | 7.25 | 0.040961 | 1326 | #DIV/0! |  |  | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5793918 | E.5034572.01.08 | 120255838 | 35223343 | FRRB - BIG BEND 1102 - LR 1972 UG
35061206 | In-Construction | 20 | PLAN | 2021005 | 1.77 | 1.77 | 2020 | 0 |  | 0 | 1996303.4 | CONS | 152481103 | BRUNSWICK 1103 | BRUNSWICK 110350070 | 201 | 17.7473 | 2144 | 1.2469 | 0.0062036 | 2255 | 0.083322 | 7 | Tier 3 | PRE | NEVADA CITY | Nevada | Sierra | Northern | 5783070 | E.5015569.01 | 115106231 | 35061206 | CWSP-BRUNSWICK 1103-LR50070-PH 1.1 | 9320 | 0 | 0 | 0 |  | 2018-85016 | 10380.48 | 1.966 | 2108720 | 2019-76345 | 0 | 0 | 9320 | 9320 | 1.7652 | 3389090.9091 | 2020-03978 | 2020-30766 | 0 | 0 | 9320 | 9320 | 1.7652 | 3459498 | 4711641 | 371.1908
35117443 | In-Construction | 20 | PLAN | 2021006 | 2.16 | 2.16 | 2020 | 0 |  | 0 | 1775373.41 | CONS | 152481103 | BRUNSWICK 1103 | BRUNSWICK 110350070 | 201 | 17.7473 | 2144 | 1.2469 | 0.0062036 | 2255 | 0.10168 | 7 | Tier 3 | PRE | NEVADA CITY | Nevada | Sierra | Northern | 5786518 | E.5015567.06 | 117634567 | 35117443 | CWSP-BRUNSWICK 1103-LR50070-PH 3.6 | 11395 | 0 | 0 | 0 |  | 2018-85051 | 8147.04 | 1.543 | 1630650 | 2019-76353 | 0 | 0 | 11395 | 11395 | 2.1581 | 4143636.3636 | 2020-32576 | 2020-42958 | 0 | 0 | 11395 | 11395 | 2.1581 | 4475708 | 5778810 | 392.7782
35061212 | In-Construction | 20 | PLAN | 2021007 | 1.79 | 1.79 | 2020 | 0 |  | 0 | 1360026.68 | CONS | 152481103 | BRUNSWICK 1103 | BRUNSWICK 110350070 | 201 | 17.7473 | 2144 | 1.2469 | 0.0062036 | 2255 | 0.084263 | 7 | Tier 3 | PRE | NEVADA CITY | Nevada | Sierra | Northern | 5783071 | E.5015568.01 | 115106486 | 35061212 | CWSP-BRUNSWICK 1103-LR50070-PH 2.1 | 9445 | 0 | 0 | 0 |  | 2018-85027 | 47520 | 9 | 9533800 | 2019-76348 | 0 | 0 | 9445 | 9445 | 1.7888 | 3434545.4545 | 2020-06702 | 2020-46891 | 0 | 0 | 9445 | 9445 | 1.7888 | 3890031 | 4913095 | 411.8614 |  | 2020-04589
35115151 | In-Construction | 20 | PLAN | 2021008 | 1.9 | 1.9 | 2020 | 0 |  | 0 | 976798.02 | CONS | 152481103 | BRUNSWICK 1103 | BRUNSWICK 110350070 | 201 | 17.7473 | 2144 | 1.2469 | 0.0062036 | 2255 | 0.089441 | 7 | Tier 3 | PRE | NEVADA CITY | Nevada | Sierra | Northern | 5785721 | E.5015568.02 | 117493857 | 35115151 | CWSP-BRUNSWICK 1103-LR50070-PH 2.2 | 10013 | 0 | 0 | 0 |  | 2018-85027 | 11880 | 2.25 | 2383450 | 2019-76348 | 0 | 0 | 10013 | 10013 | 1.8964 | 3641090.9091 | 2020-23454 | 2020-46448 | 0 | 0 | 10013 | 10013 | 1.8964 | 4025667 | 5273989 | 402.044 |  | 2020-38642
35223036 | PSPS - Community Resiliency | 2 | PLAN | 2021083 | 0.18939 | 0.18939 | 2021 |  |  | 0 | 0 | UNSE | 152481110 | BRUNSWICK 1110 | BRUNSWICK 1110CB | 26 | 0.0034177 | 2134 | 0.16685 | 0.0064174 | 2454 | 9.1537 |  |  | PSPS | GRASS VALLEY | Nevada | Sierra | Northern | 5794983 | E.5034759.01.01 | 120242599 | 35223036 | PSPS - Brunswick 1110CB |  | 1000 | [11 empty] | 0
35217268 | Top 50 Miles | 7 | PLAN | 2021055 | 4.06 | 4.06 | 2021 |  |  | 0 | 0 | UNSE | 102211101 | BUCKS CREEK 1101 | BUCKS CREEK 1101CB | 13 | 4.8008 | 11 | 9.5539 | 0.73491 | 200 | 6.5787 |  | Tier 2 & 3 | CWSP | BELDEN | Plumas | North Valley | Northern | 5794208 | E.5034607.01.01 | 120047659 | 35217268 | CWSP - BUCKS CREEK 1101 CB | 11774.4 | 9662.4 |  |  | 2020-81775 | 2020-81782 | 21436.8 | 4.06 | 6144137 |  |  | 9662.4 | 11774.4 | 21436.8 | 4.06
35223062 | PSPS - Community Resiliency | 2 | PLAN | 2021085 |  | 0 | 2021 |  |  | 0 | 0 | UNSE | 42711102 | CALISTOGA 1102 | CALISTOGA 1102184814 | 20 | 0.42402 | 3098 | 0.00017414 | 8.707e-06 | 3379 | #DIV/0! |  |  | PSPS | CALISTOGA | Napa | North Bay | Bay Area | 5794986 | E.5034762.01.01 | 120242676 | 35223062 | PSPS - Calistoga 1102184814 | [13 empty] | 0
35223061 | PSPS - Community Resiliency | 2 | PLAN | 2021087 |  | 0 | 2021 |  |  | 0 | 0 | UNSE | 42711102 | CALISTOGA 1102 | CALISTOGA 1102634 | 178 | 11.216 | 1477 | 5.2284 | 0.029373 | 1599 | #DIV/0! |  |  | PSPS | CALISTOGA | Napa | North Bay | Bay Area | 5794986 | E.5034762.01.02 | 120242677 | 35223061 | PSPS - Calistoga 1102634 | [13 empty] | 0
35114100 | In-Construction | 20 | PLAN | 2021022 | 1.04 | 1.04 | 2020 | 0 |  | 0 | 384877.49 | CONS | 83622106 | CAMP EVERS 2106 | CAMP EVERS 21065020 | 185 | 15.0734 | 2464 | 0.3934 | 0.0021265 | 2540 | 0.018186 | 46 | Tier 3 | PRE | SCOTTS VALLEY | Santa Cruz | Central Coast | Central Coast | 5786131 | E.5015489.02 | 117545617 | 35114100 | CWSP-CAMP EVERS 2106-LR5020-PH2.2 | 5487 | 0 | 0 | 0 |  | 2018-64516 | 8500.8 | 1.61 | 1747200 | N/A | 0 | 0 | 5491.2 | 5491.2 | 1.04 | 1996800 | 2019-82353 | 2020-34359 | 0 | 0 | 5487 | 5487 | 1.0392 | 2119397 | 2502285 | 386.2579
35192280 | ECOP - Top 20% | 9 | PLAN | 2021037 | 2.73 | 2.73 | 2021 |  |  | 0 | 3068.26 | UNSE | 12022212 | CLAYTON 2212 | CLAYTON 221296224 | 174 | 19.3992 | 377 | 32.6329 | 0.18755 | 281 | 3.7767 | 267 | Tier 3 | ECOP | CONCORD | Contra Costa | Diablo | Bay Area | 5792091 | E.5034400.01 | 119556070 | 35192280 | ECOP - CLAYTON 2212 - H01-LR2951 | 7550.4 | 6864 | 0 | 0 | 2020-77593 | 2020-77594 | 14414.4 | 2.73 | 4538638 |  | 5227.2 | 6864 | 7550.4 | 19641.6 | 3.72
35219097 | Top 250 Miles | 6 | PLAN | 2021203 | 8.58 | 8.58 | 2021 |  |  | 0 | 0 | UNSE | 254432104 | COARSEGOLD 2104 | COARSEGOLD 2104CB | 27 | 2.4277 | 22 | 16.0848 | 0.59573 | 95 | #DIV/0! |  |  | CWSP | COARSEGOLD | Madera | Yosemite | Central Valley | 5794546 | E.5034695.01.01 | 120141762 | 35219097 | CWSP - COARSEGOLD 2104CB |  |  |  |  | 2021-01-07 | 2021-01581 | 45302.4 | 8.58 | 7867593 |  |  |  |  | 0 | 0
35054184 | Top 20% MAVF CPZ | 7 | PLAN | 2021064 | 4.9 | 4.9 | 2021 |  |  | 0 | 3334.77 | UNSE | 152471101 | COLUMBIA HILL 1101 | COLUMBIA HILL 11012212 | 76 | 9.1336 | 606 | 9.8207 | 0.12922 | 1358 | 3.53 | 198 | Tier 3 | PRE | NEVADA CITY | Nevada | Sierra | Northern | 5530173 |  | 114941996 | 35054184 | CWSP-COLUMBIA HILL 1101-TS8233-PH1.1 | 25872 | 0 | 0 | 0 | 2018-69650 | 2018-72909 | 25872 | 4.9 | 5227500 |  |  |  |  | 0 | 0
35219265 | Top 250 Miles | 6 | PLAN | 2021208 | 0.9 | 0.9 | 2021 |  |  | 0 | 0 | UNSE | 102251101 | CRESTA 1101 | CRESTA 1101546650 | 6 | 0.89694 | 33 | 3.0174 | 0.50291 | 845 | #DIV/0! |  |  | CWSP | OROVILLE | Butte | North Valley | Northern | 5543353 | E.5034700.01.01 | 120141941 | 35219265 | CWSP - CRESTA 1101546650 |  |  |  |  | 2020-12-31 | 2021-00911 | 2323.2 | 0.44 | 500000 |  |  |  |  | 0 | 0
35219286 | Top 250 Miles | 4 | PLAN | 2021220 | 18.6 | 18.6 | 2021 |  |  | 0 | 0 | UNSE | 103351104 | DESCHUTES 1104 | DESCHUTES 11049718 | 357 | 18.6049 | 48 | 151.8163 | 0.42526 | 94 | #DIV/0! |  |  | CWSP | PALO CEDRO | Shasta | North Valley | Northern | 5794554 | E.5034713.01.01 | 120142352 | 35219286 | CWSP - DESCHUTES 11049718 |  |  |  |  | 2021-01-08 | [8 empty] | 0 | 0
35026643 | Top 20% MAVF CPZ | 7 | PLAN | 2021065 | 1.402 | 1.402 | 2021 |  |  | 0 | 46082.68 | UNSE | 152261105 | DIAMOND SPRINGS 1105 | DIAMOND SPRINGS 11052102 | 417 | 37.4816 | 666 | 48.4576 | 0.11621 | 755 | 1.2144 | 957 | Tier 2 | WDDB | DIAMOND SPRINGS | El Dorado | Sierra | Northern | 5530173 |  | 114258488 | 35026643 | RECONDUCTOR DIAMOND SPRINGS 1105 | 7400 | 0 | 0 | 0 |  | 2018-38234 | 7400 | 1.4015 | 740000 |  |  |  |  | 0 | 0
35192290 | ECOP | 7 | PLAN | 2021046 | 5 | 5 | 2021 |  |  | 0 | 1956.63 | UNSE | 152261107 | DIAMOND SPRINGS 1107 | DIAMOND SPRINGS 11071402 | 541 | 44.1915 | 811 | 49.924 | 0.092281 | 726 | 3.7846 | 244 | Tier 3 | ECOP | PLACERVILLE | El Dorado | Sierra | Northern | 5792092 | E.5034401.01 | 119556075 | 35192290 | ECOP - DIAMOND SPRINGS 1101 - H01-LR1402 | 26402 | 0 | 0 | 0 |  | 2020-66261 | 26400 | 5 | 5575214 | - |  |  |  | 0 | 0
35192291 | ECOP | 7 | PLAN | 2021047 | 3.1 | 3.1 | 2021 |  |  | 0 | 1742.96 | UNSE | 152261107 | DIAMOND SPRINGS 1107 | DIAMOND SPRINGS 11071402 | 541 | 44.1915 | 811 | 49.924 | 0.092281 | 726 | 2.3464 | 244 | Tier 3 | ECOP | PLACERVILLE | El Dorado | Sierra | Northern | 5792093 | E.5034402.01 | 119556091 | 35192291 | ECOP - DIAMOND SPRINGS 1101 - H02-LR1402 | 15109 | 0 | 0 | 0 |  | 2020-69602 | 15100.8 | 2.86 | 3208863 | - |  |  |  | 0 | 0
35223063 | PSPS - Community Resiliency | 6 | PLAN | 2021089 | 1.93 | 1.93 | 2021 |  |  | 0 | 0 | UNSE | 43071101 | DUNBAR 1101 | DUNBAR 1101CB | 191 | 3.1203 | 2048 | 1.5267 | 0.007993 | 2185 | 0.93484 |  |  | PSPS | SANTA ROSA | Sonoma | Sonoma |  | 5794985 | E.5034761.01.01 | 120242673 | 35223063 | PSPS - Dunbar 1101CB |  | 10560 |  |  |  | 2021-01566 | 10190.4 | 1.93 | 4690000 |  |  |  |  | 0
35222235 | Remote Grid Pilot | 6 | PLAN | 2021081 | 2.6 | 2.6 | 2021 |  |  | 0 | 0 | UNSE | 254061102 | DUNLAP 1102 | DUNLAP 1102778286 | 5 | 2.6029 | 2738 | 0.0024545 | 0.0004909 | 2461 | #DIV/0! |  |  | REMG | BADGER | Tulare | Fresno | Central Valley | 5794900 | E.5034754.01.01 | 120236988 | 35222235 | REMG - DUNLAP 1102778286 | [5 empty] | 2020-88308 | 13728 | 2.6 | 613214 |  |  |  |  | 0
77779999 | FRRB - REMG - 2021 | 1 | PLAN | 2021069 | 7.9 | 7.9 | 2021 |  |  | 0 | 0 | UNSE | 102781101 | ELK CREEK 1101 | ELK CREEK 11012106 | 67 | 13.2402 | 340 | 13.1388 | 0.1961 | 40 | 7.7611 |  |  | FRRB | [8 empty] | FRRB - ELK CREEK 1101 LR 2106 | 0 | 0 | 0 | 41712 | [9 empty] | 0 | 0
74022384 | In-Construction | 20 | PLAN | 2021001 | 5.446 | 4.486 | 2020 | 0.96 |  | 0.96 | 6621813.64 | CONS | 42751113 | FITCH MOUNTAIN 1113 | FITCH MOUNTAIN 111324918 | 49 | 5.4965 | 481 | 7.7177 | 0.1575 | 799 | 5.1234 | 209 | Tier 3 | PRE | GEYSERVILLE | Sonoma | Sonoma | Northern | 5782860 | E.5015487.01 | 114753320 | 74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | 28754 | 0 | 0 | 0 |  | 2018-55406 | 29568 | 5.6 | 5959500 | N/A | 0 | 0 | 29040 | 29040 | 5.5 | 10560000 | 2019-34744 | 2019-02348 |  |  | 28754 | 28754 | 5.4458
77779999 | FRRB - REMG - 2021 | 1 | PLAN | 2021072 | 4.03 | 4.03 | 2021 |  |  | 0 | 0 | UNSE | 42751113 | FITCH MOUNTAIN 1113 | FITCH MOUNTAIN 11136751 | 139 | 22.6749 | 945 | 10.2759 | 0.073927 | 1284 | 1.8081 |  |  | FRRB | [8 empty] | FRRB - FITCH MOUNTAIN 1113 LR 6751 | 0 | 0 | 0 | 21278.4 | [9 empty] | 0
35075103 | Top 20% MAVF CPZ | 7 | PLAN | 2021067 | 0.59 | 0.59 | 2021 |  |  | 0 | 3720.44 | UNSE | 163451701 | FROGTOWN 1701 | FROGTOWN 17011623 | 152 | 15.2605 | 721 | 16.3546 | 0.1076 | 564 | 0.42364 | 1409 | Tier 3 | WDDB | MURPHYS | Calaveras | Stockton | Central Valley | 5530176 |  | 116475141 | 35075103 | FROGTOWN 1701 - 3115FT RECOND HFTD TIER2 | 3115 | 0 | 0 | 0 |  | 2019-20625 | 3115 | 0.58996 | 623000 |  |  |  |  | 0 | 0
35145540 | PSPS - Scoped | 18 | PLAN | 2021027 | 1.274 | 1.274 | 2020 | 0 |  | 0 | 175026.03 | PEND | 163451702 | FROGTOWN 1702 | FROGTOWN 1702CB | 47 | 1.4614 | 1316 | 1.844 | 0.039234 | 1692 | 1.6021 | 3052 | Tier 3 | PSPS | Angels | Calaveras | Stockton | Central Valley | 5788779 | E.5025634 | 118259180 | 35145540 | PSPS – Frogtown 1702 – CB | 0 | 2272 | 4454 | 0 |  | 2019-80603 | 2640 | 0.5 | 3900000 | N/A | 4454 | 2272 | 0 | 6726 | 1.2739 | 2100000 | 2020-42690
35192292 | ECOP - Top 20% | 9 | PLAN | 2021041 | 3.75 | 3.75 | 2021 |  |  | 0 | 2449.47 | UNSE | 42561107 | FULTON 1107 | FULTON 1107604 | 169 | 17.4386 | 637 | 20.5661 | 0.12169 | 641 | 3.326 | 225 | Tier 3 | ECOP | SANTA ROSA | Sonoma | Sonoma | Northern | 5792094 | E.5034403.01 | 119556108 | 35192292 | ECOP - FULTON 1107 - H02-LR604 | 15593 | 5377 | 0 | 0 | 2020-78732 | 2020-78779 | 19800 | 3.75 | 4686150 | - |  | 5377 | 15593 | 20970 | 3.9716
35217274 | FRRB - UG - 2021 | 5 | PLAN | 2021070 | 2.52 | 2.52 | 2021 |  |  | 0 | 0 | UNSE | 24101103 | HALF MOON BAY 1103 | HALF MOON BAY 110369412 | 150 | 15.5679 | 2055 | 1.1767 | 0.0078448 | 1975 | 0.18857 |  |  | FRRB | PESCADERO | San Mateo | Peninsula | Central Coast | 5794202 | E.5034613.01.01 | 120048101 | 35217274 | FRRB - PN DIVISION SAN MATEO COUNTY | 0 | 133050.6 |  |  |  | 2020-84558 | 13305.6 | 2.52 | 4621000 |  |  | 13305.6 | 0 | 13305.6 | 2.52
35217275 | FRRB - UG - 2021 | 5 | PLAN | 2021071 | 2.75 | 2.75 | 2021 |  |  | 0 | 0 | UNSE | 24101103 | HALF MOON BAY 1103 | HALF MOON BAY 110369412 | 150 | 15.5679 | 2055 | 1.1767 | 0.0078448 | 1975 | #DIV/0! |  |  | FRRB | PESCADERO | Santa Cruz | Peninsula | Central Coast | 5794201 | E.5034614.01.01 | 120048103 | 35217275 | FRRB - PN DIVISION SANTA CRUZ COUNTY | [13 empty] | 0 | 0
35220936 | FRRB - OH - 2021 | 2 | PLAN | 2021077 | 0.95 | 0.95 | 2021 |  |  | 0 | 0 | UNSE | 24101103 | HALF MOON BAY 1103 | HALF MOON BAY 11036012 | 79 | 6.6683 | 2186 | 0.42722 | 0.0054078 | 2095 | #DIV/0! |  |  | FRRB | PESCADERO | Santa Cruz | Peninsula | Central Coast | 5794202 | E.5034613.01.02 | 120224375 | 35220936 | FRRB - BUTANO STATE PARK - PN SM
35219099 | Top 250 Miles | 6 | PLAN | 2021205 | 17.3 | 17.3 | 2021 |  |  | 0 | 0 | UNSE | 43361102 | HIGHLANDS 1102 | HIGHLANDS 1102628 | 51 | 14.2224 | 27 | 27.9838 | 0.5487 | 33 | #DIV/0! |  |  | CWSP | CLEARLAKE | Lake | Humboldt | Northern | 5794549 | E.5034697.01.01 | 120141849 | 35219099 | CWSP - HIGHLANDS 1102628 | [5 empty] | 2021-00785 | 91344 | 17.3 | 25150000 |  |  |  |  | 0 | 0
35217272 | Top 50 Miles | 7 | PLAN | 2021051 | 8.13 | 8.13 | 2021 |  |  | 0 | 0 | UNSE | 103451101 | KESWICK 1101 | KESWICK 11011586 | 39 | 7.4478 | 7 | 48.8434 | 1.2524 | 233 | 49.3004 |  | Tier 3 | CWSP | REDDING | Shasta | North Valley | Northern | 5794204 | E.5034611.01.01 | 120048018 | 35217272 | CWSP - KESWICK 1101 LR 1586 | 8764.8 | 34162 |  |  | 2020-81561 | 2020-82753 | 42926.4 | 8.13 | 22711843 |  |  | 34161.6 | 8764.8 | 42926.4 | 8.13
35219096 | Top 250 Miles | 6 | PLAN | 2021202 | 5.75 | 5.75 | 2021 |  |  | 0 | 0 | UNSE | 14452104 | KIRKER 2104 | KIRKER 2104442850 | 30 | 5.7542 | 21 | 18.4361 | 0.61454 | 21 | #DIV/0! |  |  | CWSP | PITTSBURG | Contra Costa | Diablo | Bay Area | 5794544 | E.5034694.01.01 | 120141671 | 35219096 | CWSP - KIRKER 2104442850 |  |  |  |  | 2021-01-08 | 2021-01226 | 9240 | 1.75 | 4945020 |  |  |  |  | 0 | 0
35094397 | In-Construction | 20 | PLAN | 2021004 | 1.07 | 1.07 | 2020 | 0 |  | 0 | 993818.26 | CONS | 43311102 | KONOCTI 1102 | KONOCTI 1102532 | 124 | 9.7315 | 1999 | 1.1234 | 0.0090595 | 2215 | 0.082757 | 153 | Tier 3 | PRE | KELSEYVILLE | Lake | Humboldt | Northern | 5785167 | E.5015029.11 | 117131100 | 35094397 | CWSP-KONOCTI 1102-LR 532-PH10 | 5621 | 0 | 0 | 0 |  | 2018-50209 | 4593.6 | 0.87 | 930690 | N/A | 0 | 0 | 5649.6 | 5649.6 | 1.07 | 2054400 | 2019-62948 | 2020-36368 | 0 | 0 | 5621 | 5621 | 1.0646 | 1438986 | 1733017 | 256.0018
35217270 | Top 50 Miles | 7 | PLAN | 2021053 | 2.09 | 2.09 | 2021 |  |  | 0 | 1419.27 | UNSE | 43311101 | KONOCTI 1102 | KONOCTI 1102965078 | 59 | 6.2704 | 9 | 51.7008 | 0.87629 | 220 | 11.5458 |  | Tier 3 | CWSP | KELSEYVILLE | Lake | Humboldt | Northern | 5794206 | E.5034609.01.01 | 120048013 | 35217270 | CWSP - KONOCTI 1102 LR 965078 | 11035.2 |  |  |  | 2020-81626 | 2020-81645 | 11035.2 | 2.09 | 2458800 |  |  |  | 11035.2 | 11035.2 | 2.09
35191319 | ECOP - Top 20% | 9 | PLAN | 2021035 | 0.76 | 0.76 | 2021 |  |  | 0 | 3102.71 | UNSE | 42991105 | LAS GALLINAS A 1105 | LAS GALLINAS A 110599904 | 54 | 5.5621 | 215 | 13.5032 | 0.25006 | 739 | 1.5882 | 213 | Tier 3 | ECOP | NICASIO | Marin | North Bay | Northern | 5541305 | E.5034355.01 | 119518398 | 35191319 | ECOP - LAS GALLINAS A 1105 - H01-LR99904 | 2217.6 | 3273.6 | 0 | 0 |  | 2020-76901 | 5491.2 | 1.04 | 1673104 | - |  | 3273.6 | 2217.6 | 5491.2 | 1.04
35223615 | ECOP - Top 20% |  | PLAN |  |  |  | 2021 |  |  |  |  | UNSE | 42991105 | LAS GALLINAS A 1105 | LAS GALLINAS A 110599904 | 54 | 5.5621 | 215 | 13.5032 | 0.25006 | 739 | #DIV/0! | 213 | Tier 3 | ECOP | NICASIO | Marin | North Bay | Northern | 5795129 | E.5034355.02 | 120401360 | 35223615 | ECOP - LAS GALLINAS A 1105 - H01-LR99904 PH2
35119965 | In-Construction | 20 | PLAN | 2021003 | 0.85 | 0.85 | 2020 | 0 |  | 0 | 730782.41 | CONS | 82021106 | LOS GATOS 1106 | LOS GATOS 1106LB44 | 213 | 19.3536 | 1864 | 2.6623 | 0.012499 | 1950 | 0.07834 | 841 | Tier 3 | PRE | LOS GATOS | Santa Clara | De Anza | Central Coast | 5786602 | E.5014534.05 | 117721840 | 35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E | 4483 | 0 | 0 | 0 |  | 2018-31656 | 8077 | 1.5297 | 903333 | 2018-53540 | 0 | 0 | 1584 | 1584 | 0.3 | 576000 | 2019-78779 | 2020-24016 | 4483 | 0 | 4483 | 4483 | 0.84905 | 1435425 | 1924210 | 320.193
35222236 | Remote Grid Pilot | 6 | PLAN | 2021079 | 0.99 | 0.99 | 2021 |  |  | 0 | 0 | UNSE | 254452101 | MARIPOSA 2101 | MARIPOSA 210135244 | 146 | 17.4635 | 428 | 25.237 | 0.17286 | 468 | #DIV/0! |  |  | REMG | MARIPOSA | Mariposa | Yosemite | Central Valley | 5543983 | E.5034753.01.01 | 120237131 | 35222236 | REMG - MARIPOSA 210135244 | [5 empty] | 2020-88214 | 5227.2 | 0.99 | 780759 |  |  |  |  | 0
35219268 | Top 250 Miles | 6 | PLAN | 2021210 | 4.6 | 4.6 | 2021 |  |  | 0 | 0 | UNSE | 254452101 | MARIPOSA 2101 | MARIPOSA 210197142 | 40 | 4.6029 | 36 | 18.8487 | 0.47122 | 66 | #DIV/0! |  |  | CWSP | MARIPOSA | Mariposa | Yosemite | Central Valley | 5794541 | E.5034703.01.01 | 120142035 | 35219268 | CWSP - MARIPOSA 210197142 |  |  |  |  | 2021-01-07 | 2021-01027 | 24288 | 4.6 | 7389000 |  |  |  |  | 0 | 0
35217267 | Top 50 Miles | 6 | PLAN | 2021054 | 0.71 | 0.71 | 2021 |  |  | 0 | 3293.6 | UNSE | 254452102 | MARIPOSA 2102 | MARIPOSA 2102241564 | 14 | 0.71281 | 10 | 10.8148 | 0.77248 | 26 | 7.2174 |  | Tier 2 & 3 | CWSP | MARIPOSA | Mariposa | Yosemite | Central Valley | 5794209 | E.5034606.01.01 | 120047657 | 35217267 | CWSP - MARIPOSA 2102 LR 241564 | 3748.8 |  |  |  |  | 2020-83810 | 3748.8 | 0.71 | 804541 |  |  |  | 3748.8 | 3748.8 | 0.71
35219266 | Top 250 Miles | 6 | PLAN | 2021209 | 5.25 | 5.25 | 2021 |  |  | 0 | 0 | UNSE | 254452102 | MARIPOSA 2102 | MARIPOSA 2102CB | 31 | 5.2539 | 35 | 14.6212 | 0.47165 | 205 | #DIV/0! |  |  | CWSP | MARIPOSA | Mariposa | Yosemite | Central Valley | 5794552 | E.5034702.01.01 | 120141949 | 35219266 | CWSP - MARIPOSA 2102CB |  |  |  |  | 2021-01-07 | 2021-01236 | 27720 | 5.25 | 8003586 |  |  |  |  | 0 | 0
35219267 | Top 250 Miles | 3 | PLAN | 2021223 | 4.27 | 4.27 | 2021 |  |  | 0 | 0 | UNSE | 254452102 | MARIPOSA 2102 | MARIPOSA 2102440236 | 38 | 4.2727 | 50 | 15.979 | 0.4205 | 157 | #DIV/0! |  |  | CWSP | MARIPOSA | Mariposa | Yosemite | Central Valley | 5794552 | E.5034702.01.02 | 120142033 | 35219267 | CWSP - MARIPOSA 2102440236 PH 1 |  |  |  |  | 2021-01-07 | [8 empty] | 0 | 0
35219587 | Top 250 Miles | 3 | PLAN | 2021224 | 2.155 | 2.155 | 2021 |  |  | 0 | 0 | UNSE | 254452102 | MARIPOSA 2102 | MARIPOSA 2102440236 | 38 | 4.2727 | 50 | 15.979 | 0.4205 | 157 | #DIV/0! |  |  | CWSP | MARIPOSA | Mariposa | Yosemite | Central Valley | 5794552 | E.5034702.01.03 | 120165147 | 35219587 | CWSP - MARIPOSA 2102440236 PH 2 |  |  |  |  | 2021-01-07
35219588 | Top 250 Miles | 3 | PLAN | 2021225 | 2.155 | 2.155 | 2021 |  |  | 0 | 0 | UNSE | 254452102 | MARIPOSA 2102 | MARIPOSA 2102440236 | 38 | 4.2727 | 50 | 15.979 | 0.4205 | 157 | #DIV/0! |  |  | CWSP | MARIPOSA | Mariposa | Yosemite | Central Valley | 5794552 | E.5034702.01.04 | 120165148 | 35219588 | CWSP - MARIPOSA 2102440236 PH 3 |  |  |  |  | 2021-01-07
35137590 | ECOP - Top 20% | 14 | PLAN | 2021032 | 0.53 | 0.53 | 2021 |  |  | 0 | 9882.02 | ESTS | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101CB | 146 | 4.731 | 86 | 52.8144 | 0.36174 | 335 | 3.9642 | 413 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5530164 |  | 118093216 | 35137590 | ECOP-MIDDLETOWN 1101-H02-CB | 2824 | 0 | 0 | 0 |  | 2019-73180 | 2798 | 0.52992 | 564800 | 2020-03-04 | 0 | 0 | 2824 | 2824 | 0.53485 | 1026909.0909
35137593 | ECOP - Top 20% | 14 | PLAN | 2021033 | 1.38 | 1.38 | 2021 |  |  | 0 | 5873.88 | ESTS | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 11014646 | 165 | 18.5633 | 328 | 32.9712 | 0.19983 | 415 | 1.6422 | 235 | Tier 3 | ECOP | COBB | Lake | Humboldt | Northern | 5530164 |  | 118125945 | 35137593 | ECOP-MIDDLETOWN 1101-H07-LR4646 | 7273 | 0 | 0 | 0 |  | 2019-73200 | 7286 | 1.3799 | 1454600 | 2020-03-04 | 0 | 0 | 7273 | 7273 | 1.3775 | 2644727.2727
35137596 | ECOP - Top 20% | 14 | PLAN | 2021034 | 0.97 | 0.97 | 2021 |  |  | 0 | 3845.67 | ESTS | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 11014646 | 165 | 18.5633 | 328 | 32.9712 | 0.19983 | 415 | 1.1543 | 235 | Tier 3 | ECOP | COBB | Lake | Humboldt | Northern | 5530164 |  | 118127757 | 35137596 | ECOP-MIDDLETOWN 1101-H08-LR4646 | 5131 | 0 | 0 | 0 |  | 2019-73285 | 5121 | 0.96989 | 1026000 | 2020-03-04 | 0 | 0 | 5131 | 5131 | 0.97178 | 1865818.1818
35192282 | ECOP - Top 20% | 9 | PLAN | 2021038 | 7.75 | 7.75 | 2021 |  |  | 0 | 4121.46 | UNSE | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 110148212 | 110 | 10.6994 | 468 | 17.6327 | 0.1603 | 729 | 10.7565 | 375 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5792098 | E.5034407.01 | 119556300 | 35192282 | ECOP - MIDDLETOWN 1101 - H16-LR48212 - PH 2 | 18902.4 | 22018 | 0 | 0 | 2020-78129 | 2020-78306 | 40920 | 7.75 | 11896580 | - |  | 22017.6 | 18902.4 | 40920 | 7.75
35192281 | ECOP - Top 20% | 9 | PLAN | 2021039 | 5.94 | 5.94 | 2021 |  |  | 0 | 3077.69 | UNSE | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 110148212 | 110 | 10.6994 | 468 | 17.6327 | 0.1603 | 729 | 7.9457 | 375 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5792097 | E.5034406.01 | 119556250 | 35192281 | ECOP - MIDDLETOWN 1101 - H16-LR48212 - PH 1 | 17476.8 | 13886 | 0 | 0 | 2020-78060 | 2020-78081 | 31363.2 | 5.94 | 8593932 | - |  | 13886.4 | 17476.8 | 31363.2 | 5.94
35174479 | ECOP - Top 20% | 9 | PLAN | 2021040 | 9.25 | 9.25 | 2021 |  |  | 0 | 12588.16 | UNSE | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | 1108 | 12.0574 | 30 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5790119 | E.5033918.01 | 118913025 | 35174479 | ECOP - MIDDLETOWN 1101 - H12 - LR548-PH2 | 36273.6 | 12566 | 0 | 0 | 2020-53217 | 2020-53670 | 48840 | 9.25 | 13481516 | 2020-09-24 | 0 | 12566.4 | 36273.6 | 48840 | 9.25 | 20851272.7273
35174501 | ECOP - Top 20% | 9 | PLAN | 2021042 | 9.65 | 9.65 | 2021 |  |  | 0 | 10730.63 | UNSE | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | 1108 | 14.3925 | 30 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5790112 | E.5033919.01 | 118913026 | 35174501 | ECOP - MIDDLETOWN 1101 - H12 - LR548-PH3 | 27609.1 | 23348 | 16177.9 | 0 | 2020-53723 | 2020-53724 | 50952 | 9.65 | 16768361 | 2020-09-24 | 16177.92 | 23348.16 | 27609.12 | 67135.2 | 12.715 | 18931272.7273
35174478 | ECOP - Top 20% | 9 | PLAN | 2021044 | 4.07 | 4.07 | 2021 |  |  | 0 | 0 | UNSE | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | 1108 | 5.4343 | 30 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5790111 | E.5033917.01 | 118913024 | 35174478 | ECOP - MIDDLETOWN 1101 - H12 - LR548-PH1 | 17534.9 | 3933.6 | 3931 | 0 | 2020-51635 | 2020-51816 | 21489.6 | 4.07 | 6162189 | 2020-09-24 | 3931 | 3933.6 | 17534.88 | 25399.48 | 4.8105 | 12326545.4545
35219098 | Top 250 Miles | 6 | PLAN | 2021204 | 1.33 | 1.33 | 2021 |  |  | 0 | 0 | UNSE | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101118494 | 12 | 1.0659 | 23 | 6.971 | 0.58092 | 79 | #DIV/0! |  |  | CWSP | MIDDLETOWN | Lake | Humboldt | Northern | 5794547 | E.5034696.01.01 | 120141805 | 35219098 | CWSP - MIDDLETOWN 1101118494 |  |  |  |  | 2020-12-31 | 2020-88310 | 7022.4 | 1.33 | 1830000 |  |  |  |  | 0 | 0
35219272 | Top 250 Miles | 6 | PLAN | 2021212 | 0.92 | 0.92 | 2021 |  |  | 0 | 0 | UNSE | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101481876 | 14 | 0.8534 | 38 | 6.5476 | 0.46769 | 46 | #DIV/0! |  |  | CWSP | MIDDLETOWN | Lake | Humboldt | Northern | 5794547 | E.5034696.01.02 | 120142171 | 35219272 | CWSP - MIDDLETOWN 1101481876 |  |  |  |  | 2020-12-31 | 2020-88311 | 4857.6 | 0.92 | 1280000 |  |  |  |  | 0 | 0
35217269 | Top 50 Miles | 6 | PLAN | 2021052 | 4.98 | 4.98 | 2021 |  |  | 0 | 2136.42 | UNSE | 43141102 | MIDDLETOWN 1102 | MIDDLETOWN 1102302610 | 53 | 4.7058 | 8 | 48.565 | 0.91632 | 121 | 40.2141 |  | Tier 2 | CWSP | MIDDLETOWN | Lake | Humboldt | Northern | 5794207 | E.5034608.01.01 | 120048011 | 35217269 | SH - MIDDLETOWN 1102 LR 302610 | 17054.4 | 9240 |  |  | 2020-81207 | 2020-81139 | 26294.4 | 4.98 | 6542572 |  |  | 9240 | 17054.4 | 26294.4 | 4.98
35217271 | Top 50 Miles | 6 | PLAN | 2021056 | 7.23 | 7.23 | 2021 |  |  | 0 | 8653.69 | UNSE | 43141103 | MIDDLETOWN 1103 | MIDDLETOWN 1103830 | 212 | 27.7328 | 14 | 151.8291 | 0.71618 | 102 | #DIV/0! |  |  | CWSP | MIDDLETOWN | Lake | Humboldt | Northern | 5794205 | E.5034610.01.01 | 120048017 | 35217271 | CWSP - MIDDLETOWN 1103 LR 830 PH1 | [5 empty] | 2020-87776 | 38016 | 7.2 | 11000000 |  |  |  |  | 0 | 0
35220895 | Top 50 Miles | 6 | PLAN | 2021057 | 9.22 | 9.22 | 2021 |  |  | 0 |  | UNSE | 43141103 | MIDDLETOWN 1103 | MIDDLETOWN 1103830 | 212 | 27.7328 | 14 | 151.8291 | 0.71618 | 102 | #DIV/0! |  |  | CWSP | MIDDLETOWN | Lake | Humboldt | Northern | 5794205 | E.5034610.01.02 | 120221891 | 35220895 | CWSP - MIDDLETOWN 1103 LR 830 PH2 | [5 empty] | 2020-87780 | 48681.6 | 9.22 | 7050000
35220896 | Top 50 Miles | 6 | PLAN | 2021058 | 3.64 | 3.64 | 2021 |  |  | 0 |  | UNSE | 43141103 | MIDDLETOWN 1103 | MIDDLETOWN 1103830 | 212 | 27.7328 | 14 | 151.8291 | 0.71618 | 102 | #DIV/0! |  |  | CWSP | MIDDLETOWN | Lake | Humboldt | Northern | 5794205 | E.5034610.01.03 | 120222356 | 35220896 | CWSP - MIDDLETOWN 1103 LR 830 PH3 | [5 empty] | 2020-87782 | 19219.2 | 3.64 | 3976000
35222045 | Top 50 Miles | 6 | PLAN | 2021059 | 0.75 | 0.75 | 2021 |  |  | 0 |  | UNSE | 43141103 | MIDDLETOWN 1103 | MIDDLETOWN 1103830 | 212 | 27.7328 | 14 | 151.8291 | 0.71618 | 102 | #DIV/0! |  |  | CWSP | MIDDLETOWN | Napa | Humboldt | Northern | 5794898 | E.5034741.01.01 | 120233319 | 35222045 | CWSP - MIDDLETOWN 1103 LR 830 PH4 | [5 empty] | 2020-87784 | 3907.2 | 0.74 | 808000
35116383 | In-Construction | 20 | PLAN | 2021009 | 1.38 | 1.38 | 2020 | 0 |  | 0 | 800339.36 | CONS | 163661701 | MIWUK 1701 | MIWUK 1701953336 | 132 | 11.8581 | 2267 | 0.50381 | 0.0038168 | 2336 | 0.039283 | 12 | Tier 3 | PRE | TWAIN HARTE | Tuolumne | Yosemite | Central Valley | 5785966 | E.5014733.02 | 117604600 | 35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 | 7319 | 0 | 0 | 0 |  | 2018-59382 | 10401.6 | 1.97 | 2126216 | 2019-35887 | 0 | 0 | 7080 | 7080 | 1.3409 | 2574545.4545 | 2019-60218 | 2020-25651 | 0 | 0 | 7319 | 7319 | 1.3862 | 2547023 | 3758449 | 348.0015
35116384 | In-Construction | 20 | PART | 2021010 | 1.84 | 1.67 | 2020 | 0.17 |  | 0.17 | 91160.36 | CONS | 163661701 | MIWUK 1701 | MIWUK 1701953336 | 132 | 11.8581 | 2267 | 0.50381 | 0.0038168 | 2336 | 0.052378 | 12 | Tier 3 | PRE | TWAIN HARTE | Tuolumne | Yosemite | Central Valley | 5785967 | E.5014733.03 | 117604604 | 35116384 | CWSP - MIWUK 1701 - LR 8060 - PH 1.3 | 9700 | 0 | 0 | 0 |  | 2018-59382 | 10401.6 | 1.97 | 2126216 | 2019-35887 | 0 | 0 | 9715 | 9715 | 1.84 | 3532727.2727 | 2020-00930 | 2020-48509 | 0 | 0 | 9700 | 9700 | 1.8371 | 3239382 | 4624169 | 333.9569
35115054 | In-Construction | 20 | PART | 2021013 | 1.43 | 1.4 | 2020 | 0.03 |  | 0.03 | 870749.78 | CONS | 163661701 | MIWUK 1701 | MIWUK 1701CB | 187 | 16.2494 | 2353 | 0.55914 | 0.0029901 | 2128 | 0.032968 | 2 | Tier 3 | PRE | TWAIN HARTE | Tuolumne | Yosemite | Central Valley | 5785986 | E.5015427.02 | 117490035 | 35115054 | CWSP-MIWUK 1701-OCB-PH 2.2 | 7529 | 0 | 0 | 0 |  | 2018-83316 | 10348.8 | 1.96 | 2137840 | 2019-35903 | 0 | 0 | 7255 | 7255 | 1.3741 | 2638181.8182 | 2019-53298 | 2020-44293 | 0 | 0 | 7529 | 7529 | 1.4259 | 2482662 | 3789178 | 329.7466
35115050 | In-Construction | 20 | PLAN | 2021014 | 1.61 | 1.61 | 2020 | 0 |  | 0 | 773237.52 | CONS | 163661701 | MIWUK 1701 | MIWUK 1701CB | 187 | 16.2494 | 2353 | 0.55914 | 0.0029901 | 2128 | 0.037118 | 2 | Tier 3 | PRE | TWAIN HARTE | Tuolumne | Yosemite | Central Valley | 5785972 | E.5014771.02 | 117495948 | 35115050 | CWSP-MIWUK 1701–OCB-PH 1.2 | 8512 | 0 | 0 | 0 |  | 2018-75405 | 12165.12 | 2.304 | 2436520 | 2019-35897 | 0 | 0 | 8270 | 8270 | 1.5663 | 3007272.7273 | 2019-79491 | 2020-40482 | 0 | 0 | 8512 | 8512 | 1.6121 | 2809593 | 4091239 | 330.0744
35115055 | In-Construction | 20 | PLAN | 2021015 | 2.13 | 2.13 | 2020 | 0 |  | 0 | 732981.14 | CONS | 163661701 | MIWUK 1701 | MIWUK 1701CB | 187 | 16.2494 | 2353 | 0.55914 | 0.0029901 | 2128 | 0.049107 | 2 | Tier 2 | PRE | TWAIN HARTE | Tuolumne | Yosemite | Central Valley | 5785987 | E.5015427.03 | 117490481 | 35115055 | CWSP-MIWUK 1701-OCB-PH 2.3 | 11269 | 0 | 0 | 0 |  | 2018-83316 | 10348.8 | 1.96 | 2137840 | 2019-35903 | 0 | 0 | 11088 | 11088 | 2.1 | 4032000 | 2019-68750 | 2020-34644 | 0 | 0 | 11269 | 11269 | 2.1343 | 2901359 | 3784068 | 257.4638
35115053 | In-Construction | 20 | PLAN | 2021016 | 1.72 | 1.72 | 2020 | 0 |  | 0 | 603358.67 | CONS | 163661701 | MIWUK 1701 | MIWUK 1701CB | 187 | 16.2494 | 2353 | 0.55914 | 0.0029901 | 2128 | 0.039654 | 2 | Tier 3 | PRE | TWAIN HARTE | Tuolumne | Yosemite | Central Valley | 5785975 | E.5014771.05 | 117496041 | 35115053 | CWSP-MIWUK 1701–OCB-PH 1.5 | 9083 | 0 | 0 | 0 |  | 2018-75405 | 12165.12 | 2.304 | 2436520 | 2019-35897 | 0 | 0 | 9571 | 9571 | 1.8127 | 3480363.6364 | 2020-56266 | 2020-27365 | 0 | 0 | 9083 | 9083 | 1.7203 | 1670418 | 2296559 | 183.906
35052821 | In-Construction | 20 | PLAN | 2021017 | 2.07 | 2.07 | 2020 | 0 |  | 0 | 540223.35 | CONS | 163661701 | MIWUK 1701 | MIWUK 1701CB | 187 | 16.2494 | 2353 | 0.55914 | 0.0029901 | 2128 | 0.047723 | 2 | Tier 3 | PRE | TWAIN HARTE | Tuolumne | Yosemite | Central Valley | 5784646 | E.5014771.01 | 114593976 | 35052821 | CWSP-MIWUK 1701–OCB-PH 1.1 | 10953 | 0 | 0 | 0 |  | 2018-75405 | 12165.12 | 2.304 | 2436520 | 2019-35897 | 0 | 0 | 9750 | 9750 | 1.8466 | 3545454.5455 | 2019-52652 | 2020-46847 | 0 | 0 | 10953 | 10953 | 2.0744 | 3322975 | 4765282 | 303.3849
35056746 | In-Construction | 20 | PLAN | 2021018 | 2.03 | 2.03 | 2020 | 0 |  | 0 | 351759.86 | CONS | 163661701 | MIWUK 1701 | MIWUK 1701CB | 187 | 16.2494 | 2353 | 0.55914 | 0.0029901 | 2128 | 0.046801 | 2 | Tier 3 | PRE | MI WUK VLG | Tuolumne | Yosemite | Central Valley | 5782537 | E.5015427.01 | 114996821 | 35056746 | CWSP-MIWUK 1701-OCB-PH 2.1 | 10737 | 0 | 0 | 0 |  | 2018-83316 | 10348.8 | 1.96 | 2137840 | 2019-35903 | 0 | 0 | 10615 | 10615 | 2.0104 | 3860000 | 2019-65579 | 2020-47773 | 0 | 0 | 10737 | 10737 | 2.0335 | 2950902 | 3642331 | 274.8349
35052737 | DSDD | 18 | PLAN | 2021028 | 1.587 | 1.587 | 2020 | 0 |  | 0 | 79871.92 | PEND | 163661701 | MIWUK 1701 | MIWUK 1701953336 | 132 | 11.8581 | 2267 | 0.50381 | 0.0038168 | 2336 | 0.045176 | 12 | Tier 3 | CWSP | LONG BARN | Tuolumne | Yosemite | Central Valley | 5785238 | E.5014733.01 | 114675474 | 35052737 | CWSP-MIWUK 1701-LR8060-PH 1.1 | 8378 | 0 | 0 | 0 |  | 2018-59382 | 10401.6 | 1.97 | 2126216 | 2019-35887 | 0 | 0 | 8605 | 8605 | 1.6297 | 3129090.9091 | 2019-63683 | 2020-27366 | 0 | 0 | 8378 | 8378 | 1.5867 | 2060222 | 2768676 | 245.9086
35116391 | In-Construction | 20 | PART | 2021019 | 2.09 | 0.71 | 2020 | 1.38 |  | 1.38 | 1379456.04 | CONS | 163661702 | MIWUK 1702 | MIWUK 1702CB | 110 | 9.055 | 2369 | 0.30977 | 0.0028161 | 2489 | 0.047904 | 25 | Tier 3 | PRE | TWAIN HARTE | Tuolumne | Yosemite | Central Valley | 5785976 | E.5014773.02 | 117605551 | 35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 | 11036 | 0 | 0 | 0 |  | 2018-71642 | 10771.2 | 2.04 | 2205280 | 2019-35893 | 0 | 0 | 10840 | 10840 | 2.053 | 3941818.1818 | 2019-64313 | 2020-18345 | 0 | 0 | 11036 | 11036 | 2.0902 | 3920204 | 5835429 | 355.2196
35116395 | In-Construction | 20 | PLAN | 2021020 | 1.71 | 1.71 | 2020 | 0 |  | 0 | 589389.02 | CONS | 163661702 | MIWUK 1702 | MIWUK 1702CB | 110 | 9.055 | 2369 | 0.30977 | 0.0028161 | 2489 | 0.039194 | 25 | Tier 3 | PRE | TWAIN HARTE | Tuolumne | Yosemite | Central Valley | 5785979 | E.5014773.05 | 117605558 | 35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 | 9032 | 0 | 0 | 0 |  | 2018-71642 | 10771.2 | 2.04 | 2205280 | 2019-35893 | 0 | 0 | 7500 | 7500 | 1.4205 | 2727272.7273 | 2019-57777 | 2020-44284 | 0 | 0 | 9032 | 9032 | 1.7106 | 2479935 | 3714853 | 274.5721
35116800 | In-Construction | 20 | PART | 2021021 | 1.425 | 1.175 | 2020 | 0.25 |  | 0.25 | 1151378.16 | CONS | 163661702 | MIWUK 1702 | MIWUK 1702823548 | 231 | 19.7318 | 2411 | 0.57976 | 0.0025098 | 2266 | 0.028052 | 23 | Tier 3 | PRE | TWAIN HARTE | Tuolumne | Yosemite | Central Valley | 5785961 | E.5014730.02 | 117605265 | 35116800 | CWSP-MIWUK 1702-LR 6018-PH1.2 | 7525 | 0 | 0 | 0 |  | 2018-55685 | 9398.4 | 1.78 | 1921966 | 2019-35900 | 0 | 0 | 6695 | 6695 | 1.268 | 2434545.4545 | 2020-45856 | 2020-18449 | 0 | 0 | 7525 | 7525 | 1.4252 | 2704457 | 4030625 | 359.3963
35116442 | In-Construction | 20 | PART | 2021023 | 2.35 | 0.56 | 2020 | 1.79 |  | 1.79 | 1643733.98 | CONS | 163661702 | MIWUK 1702 | MIWUK 170238218 | 132 | 10.9416 | 2678 | 0.098599 | 0.00074696 | 2665 | 0.014188 | 32 | Tier 3 | PRE | TWAIN HARTE | Tuolumne | Yosemite | Central Valley | 5785982 | E.5014776.03 | 117605169 | 35116442 | CWSP-MIWUK 1702-LR38218-PH1.3 | 12386 | 0 | 0 | 0 |  | 2018-60918 | 9768 | 1.85 | 1963016 | 2019-35889 | 0 | 0 | 11065 | 11065 | 2.0956 | 4023636.3636 | 2020-11921 | 2020-34785 | 0 | 0 | 12386 | 12386 | 2.3458 | 2994831 | 3849738 | 241.7916
35116444 | In-Construction | 20 | PLAN | 2021024 | 2.1 | 2.1 | 2020 | 0 |  | 0 | 750572.79 | CONS | 163661702 | MIWUK 1702 | MIWUK 170238218 | 132 | 10.9416 | 2678 | 0.098599 | 0.00074696 | 2665 | 0.012679 | 32 | Tier 3 | PRE | TWAIN HARTE | Tuolumne | Yosemite | Central Valley | 5785984 | E.5014776.05 | 117605182 | 35116444 | CWSP-MIWUK 1702-LR38218-PH1.5 | 11100 | 0 | 0 | 0 |  | 2018-60918 | 9768 | 1.85 | 1963016 | 2019-35889 | 0 | 0 | 9600 | 9600 | 1.8182 | 3490909.0909 | 2019-57736 | 2020-27703 | 0 | 0 | 11100 | 11100 | 2.1023 | 2648178 | 3531134 | 238.5746
35052825 | In-Construction | 20 | PLAN | 2021025 | 1.17 | 1.17 | 2020 | 0 |  | 0 | 450269.57 | CONS | 163661702 | MIWUK 1702 | MIWUK 1702S2247 | 21 | 1.4879 | 2737 | 0.010338 | 0.00049228 | 2641 | 0.0054466 | 26 | Tier 3 | PRE | TWAIN HARTE | Tuolumne | Yosemite | Central Valley | 5785221 | E.5014722.01 | 114701195 | 35052825 | CWSP-MIWUK 1702-LR 8090-PH 1.1 | 6168 | 0 | 0 | 0 |  | 2018-63127 | 10296 | 1.95 | 2134266 | 2019-35902 | 0 | 0 | 5785 | 5785 | 1.0956 | 2103636.3636 | 2019-54146 | 2020-43899 | 0 | 0 | 6168 | 6168 | 1.1682 | 2342292 | 3544410 | 379.749
35223032 | PSPS - Community Resiliency | 2 | PLAN | 2021090 |  | 0 | 2021 |  |  | 0 | 0 | UNSE | 152282102 | MOUNTAIN QUARRIES 2101 | MOUNTAIN QUARRIES 2101CB | 262 | 24.9941 | 68 | 101.3032 | 0.38665 | 328 | #DIV/0! |  |  | PSPS | COOL | El Dorado | Sierra | Northern | 5794982 | E.5034758.01.01 | 120242546 | 35223032 | PSPS - Mounatin Quarries 2101CB | [13 empty] | 0
35219281 | Top 250 Miles | 6 | PLAN | 2021217 | 5.71 | 5.71 | 2021 |  |  | 0 | 0 | UNSE | 152282101 | MOUNTAIN QUARRIES 2101 | MOUNTAIN QUARRIES 21016953 | 58 | 5.7104 | 45 | 25.2473 | 0.4353 | 135 | #DIV/0! |  |  | CWSP | COOL | El Dorado | Sierra | Northern | 5794551 | E.5034710.01.01 | 120142240 | 35219281 | CWSP - MOUNTAIN QUARRIES 21016953 |  |  |  |  | 2020-12-31 | 2021-00875 | 30940.8 | 5.86 | 8236794 |  |  |  |  | 0 | 0
35219282 | Top 250 Miles | 6 | PLAN | 2021218 | 1 | 1 | 2021 |  |  | 0 | 0 | UNSE | 14052101 | NORTH DUBLIN 2101 | NORTH DUBLIN 2101CB | 23 | 1.7629 | 47 | 9.8576 | 0.42859 | 388 | #DIV/0! |  |  | CWSP | DUBLIN | Alameda | Mission | Central Coast | 5543349 | E.5034711.01.01 | 120142312 | 35219282 | CWSP - NORTH DUBLIN 2101 CB |  |  |  |  | 2020-12-31 | 2020-88260 | 5280 | 1 | 1699520 |  |  |  |  | 0 | 0
35219283 | Top 250 Miles | 6 | PLAN | 2021219 | 0.82 | 0.82 | 2021 |  |  | 0 | 0 | UNSE | 14052101 | NORTH DUBLIN 2101 | NORTH DUBLIN 2101CB | 23 | 1.7629 | 47 | 9.8576 | 0.42859 | 388 | #DIV/0! |  |  | CWSP | PLEASANTON | Contra Costa | Mission | Central Coast | 5543351 | E.5034712.01.01 | 120142316 | 35219283 | CWSP - NORTH DUBLIN 2101 CB |  |  |  |  | 2020-12-31 | 2020-88250 | 4329.6 | 0.82 | 1370560 |  |  |  |  | 0 | 0
35222234 | Remote Grid Pilot | 6 | PLAN | 2021078 | 2.62 | 2.62 | 2021 |  |  | 0 | 0 | UNSE | 254421101 | OAKHURST 1101 | OAKHURST 110110090 | 435 | 44.0886 | 421 | 75.8506 | 0.17437 | 167 | #DIV/0! |  |  | REMG | OAKHURST | Mariposa | Yosemite | Central Valley | 5543982 | E.5034752.01.01 | 120237130 | 35222234 | REMG - OAKHURST 110110090 | [5 empty] | 2021-00557 | 13833.6 | 2.62 | 4816500 |  |  |  |  | 0
35223037 | PSPS - Community Resiliency | 2 | PLAN | 2021091 |  | 0 | 2021 |  |  | 0 | 0 | UNSE | 254421101 | OAKHURST 1101 | OAKHURST 1101CB | 47 | 2.3149 | 847 | 4.0694 | 0.086583 | 802 | #DIV/0! |  |  | PSPS | OAKHURST | Madera | Yosemite | Central Valley | 5794989 | E.5034765.01.01 | 120242694 | 35223037 | PSPS - Oakhurst 1101CB | [13 empty] | 0
35223038 | PSPS - Community Resiliency | 2 | PLAN | 2021086 |  | 0 | 2021 |  |  | 0 | 0 | UNSE | 163541101 | OLETA 1101 | OLETA 1101CB | 2 | 0.084664 | 95 | 0.70277 | 0.35138 | 461 | #DIV/0! |  |  | PSPS | SUTTER CREEK | Amador | Stockton | Central Valley | 5794988 | E.5034764.01.01 | 120242693 | 35223038 | PSPS - Oleta 1101CB | [13 empty] | 0
35219591 | Top 250 Miles | 2 | PLAN | 2021228 | 2.88 | 2.88 | 2021 |  |  | 0 | 0 | UNSE | 163541101 | OLETA 1101 | OLETA 1101754718 | 29 | 2.8841 | 54 | 11.8066 | 0.40712 | 306 | #DIV/0! |  |  | CWSP | PLYMOUTH | Amador | Stockton | Central Valley | 5794611 | E.5034721.01.01 | 120173637 | 35219591 | CWSP - OLETA 1101754718 |  |  |  |  | 2021-01-07
35219287 | Top 250 Miles | 2 | PLAN | 2021221 | 0.02 | 0.02 | 2021 |  |  | 0 | 0 | UNSE | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 1103CUS391 | 1 | 0.022596 | 1 | 3.1639 | 3.1639 | 5 | #DIV/0! |  |  | CWSP | REDDING | Shasta | North Valley | Northern | 5794555 | E.5034714.01.01 | 120142356 | 35219287 | CWSP - OREGON TRAIL 1103CUS391 | [13 empty] | 0 | 0
35219289 | Top 250 Miles | 2 | PLAN | 2021222 | 57.14 | 57.14 | 2021 |  |  | 0 | 0 | UNSE | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 | 153 | #DIV/0! |  |  | CWSP | REDDING | Shasta | North Valley | Northern | 5794555 | E.5034714.01.02 | 120142359 | 35219289 | CWSP - OREGON TRAIL 110335002 | [13 empty] | 0 | 0
35114040 | In-Construction | 20 | PLAN | 2021011 | 1.485 | 1.485 | 2020 | 0 |  | 0 | 1109516.38 | CONS | 163751102 | PINE GROVE 1102 | PINE GROVE 11021222 | 218 | 17.2598 | 2271 | 0.81905 | 0.0037571 | 2414 | 0.047214 | 20 | Tier 3 | PRE | PIONEER | Amador | Stockton | Central Valley | 5785991 | E.5014745.02 | 117500499 | 35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 | 7839 | 0 | 0 | 0 |  | 2018-49722 | 27456 | 5.2 | 5674800 | 2019-35977 | 0 | 0 | 7188 | 7188 | 1.3614 | 2613818.1818 | 2020-20653 | 2020-39428 | 0 | 0 | 7839 | 7839 | 1.4847 | 3107232 | 4232854 | 396.3812
35114048 | In-Construction | 20 | PLAN | 2021012 | 1.39 | 1.39 | 2020 | 0 |  | 0 | 699201.22 | CONS | 163751102 | PINE GROVE 1102 | PINE GROVE 11021222 | 218 | 17.2598 | 2271 | 0.81905 | 0.0037571 | 2414 | 0.044194 | 20 | Tier 3 | PRE | PIONEER | Amador | Stockton | Central Valley | 5785997 | E.5014742.03 | 117499466 | 35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 | 7344 | 0 | 0 | 0 |  | 2018-54633 | 83964.72 | 1.59 | 1718171.43 | 2019-35972 | 0 | 0 | 7382 | 7382 | 1.3981 | 2684363.6364 | 2019-73207 | 2020-43723 | 0 | 0 | 7344 | 7344 | 1.3909 | 3133899 | 4178929 | 426.7292
35219543 | PSPS - Community Resiliency | 2 | PLAN | 2021082 | 0.20833 | 0.20833 | 2021 |  |  | 0 | 0 | UNSE | 153081112 | PLACERVILLE 1112 | PLACERVILLE 1112CB | 117 | 8.513 | 2123 | 0.76223 | 0.0065148 | 2310 | #DIV/0! |  |  | PSPS | PLACERVILLE | El Dorado | Sierra | Northern | 5543321 | E.5034715.01.02 | 120135657 | 35219543 | PSPS - West Main St / Reservoir St | [13 empty] | 0
35219542 | PSPS - Community Resiliency | 2 | PLAN | 2021094 | 0.15152 | 0.15152 | 2021 |  |  | 0 | 0 | UNSE | 153081112 | PLACERVILLE 1112 | PLACERVILLE 1112CB | 117 | 8.513 | 2123 | 0.76223 | 0.0065148 | 2310 | #DIV/0! |  |  | PSPS | PLACERVILLE | El Dorado | Sierra | Northern | 5543321 | E.5034715.01.01 | 120135655 | 35219542 | PSPS - Eskaton Village | [13 empty] | 0
35175853 | Remote Grid Pilot | 10 | PLAN | 2021080 | 0.7 | 0.7 | 2021 |  |  | 0 | 0 | UNSE | 153082106 | PLACERVILLE 2106 | PLACERVILLE 21061104 | 462 | 49.4989 | 2131 | 2.9785 | 0.0064469 | 2171 | #DIV/0! |  |  | REMG | GEORGETOWN | El Dorado | Sierra | Northern | 5790554 | E.5015422.03 | 118981960 | 35175853 | REMG - PLACERVILLE 21061104 | [13 empty] | 0
35224377 | PSPS - Community Resiliency | 2 | PLAN | 2021093 | 0.56818 | 0.56818 | 2021 |  |  | 0 | 0 | UNSE | 153082106 | PLACERVILLE 2106 | PLACERVILLE 21067522 | 745 | 67.3656 | 1363 | 26.4689 | 0.035529 | 1360 | 0.22101 |  |  | PSPS | PLACERVILLE | El Dorado | Sierra | Northern | 5795018 | E.5034778.01.01 | 120360607 | 35224377 | PSPS - Placerville 21067522 |  | 3000 | [11 empty] | 0
35219264 | Top 250 Miles | 2 | PLAN | 2021207 | 2.33 | 2.33 | 2021 |  |  | 0 | 0 | UNSE | 253642103 | POSO MOUNTAIN 2103 | POSO MOUNTAIN 2103CB | 10 | 2.3287 | 30 | 5.1619 | 0.51619 | 2 | #DIV/0! |  |  | CWSP | BAKERSFIELD | Kern | Kern | Central Valley | 5794550 | E.5034699.01.01 | 120141886 | 35219264 | CWSP - POSO MOUNTAIN 2103CB | [13 empty] | 0 | 0
35219092 | Top 250 Miles | 2 | PLAN | 2021200 | 5.35 | 5.35 | 2021 |  |  | 0 | 299.9 | UNSE | 253642104 | POSO MOUNTAIN 2104 | POSO MOUNTAIN 2104CB | 38 | 5.3534 | 15 | 26.7607 | 0.70423 | 51 | #DIV/0! |  |  | CWSP | BAKERSFIELD | Kern | Kern | Central Valley | 5794539 | E.5034691.01.01 | 120141620 | 35219092 | CWSP - POSO MOUNTAIN 2104CB | [13 empty] | 0 | 0
35219280 | Top 250 Miles | 6 | PLAN | 2021216 | 1.86 | 1.86 | 2021 |  |  | 0 | 0 | UNSE | 42281105 | POTTER VALLEY P H 1105 | POTTER VALLEY P H 110564118 | 101 | 1.6451 | 43 | 44.7046 | 0.44262 | 427 | #DIV/0! |  |  | CWSP | POTTER VALLEY | Mendoino | Humboldt | Northern | 5794548 | E.5034709.01.01 | 120142216 | 35219280 | CWSP - POTTER VALLEY P H 110564118 |  |  |  |  | 2020-12-31 | 2020-88312 | 9820.8 | 1.86 | 2340000 |  |  |  |  | 0 | 0
35191937 | ECOP | 7 | PLAN | 2021048 | 3.34 | 3.34 | 2021 |  |  | 0 | 3713.28 | UNSE | 43292102 | PUEBLO 2102 | PUEBLO 2102792 | 180 | 19.3407 | 951 | 13.2101 | 0.073389 | 1012 | 1.7166 | 40 | Tier 3 | ECOP | NAPA | Napa | North Bay | Bay Area | 5792064 | E.5034372.01 | 119553837 | 35191937 | ECOP - PUEBLO 2102 - H01-LR792 | 13092 | 4546 | 0 | 0 | 2020-61147 | 2020-61154 | 17635.2 | 3.34 | 3777700 | - |  | 4540.8 | 13094.4 | 17635.2 | 3.34
35219275 | Top 250 Miles | 6 | PLAN | 2021214 | 0.52 | 0.52 | 2021 |  |  | 0 | 0 | UNSE | 63681102 | PUTAH CREEK 1102 | PUTAH CREEK 110246012 | 38 | 0.63713 | 41 | 17.3115 | 0.45557 | 96 | #DIV/0! |  |  | CWSP | WINTERS | Solano | Sacramento | Northern | 5543347 | E.5034706.01.01 | 120142210 | 35219275 | CWSP - PUTAH CREEK 110246012 |  |  |  |  | 2021-12-31 | 2020-88233 | 2745.6 | 0.52 | 566066 |  |  |  |  | 0 | 0
35145524 | PSPS - Scoped | 18 | PLAN | 2021031 | 1.5 | 1.5 | 2020 | 0 |  | 0 | 155682.88 | PEND | 43321103 | RINCON 1103 | RINCON 1103CB | 41 | 2.4433 | 1755 | 0.67489 | 0.016461 | 2033 | 0.41019 | 628 | Tier 3 | PSPS | SANTA ROSA | Sonoma | Sonoma | Northern | 5788786 | E.5025637 | 118266591 | 35145524 | PSPS - Rincon 1101 and 1103- CB | 0 | 7920 | 0 | 0 |  | 2019-82381 | 7920 | 1.5 | 14953636 | N/A | 0 | 7920 | 0 | 7920 | 1.5 | 6300000 | 2020-48279
35145525 | PSPS - Scoped | 18 | PLAN | 2021030 | 1.78 | 1.78 | 2020 | 0 |  | 0 | 140676.48 | PEND | 43321104 | RINCON 1104 | RINCON 1104CB | 34 | 0.56024 | 3302 | 0.00014935 | 4.3928e-06 | 2944 | 0.00046978 | 1522 | Tier 2 | PSPS | Santa Rosa | Sonoma | Sonoma | Northern | 5788787 | E.5025638.01 | 118266592 | 35145525 | PSPS - Rincon 1102 and 1104 - CB | 0 | 9398.4 | 0 | 0 |  | 2019-82382 | 9398.4 | 1.78 | 17891818 | N/A | 0 | 9398.4 | 0 | 9398.4 | 1.78 | 7476000 | 2020-50683 | [10 empty] | 2020-28718
35062376 | Top 20% MAVF CPZ | 7 | PLAN | 2021060 | 11 | 11 | 2021 |  |  | 0 | 1425.11 | UNSE | 153652109 | SHINGLE SPRINGS 2109 | SHINGLE SPRINGS 210935598 | 122 | 10.847 | 159 | 33.9836 | 0.27855 | 443 | 23.0902 | 554 | Tier 3 | PRE | SHINGLE SPRINGS | El Dorado | Sierra | Northern | 5783069 | E.5015570.01 | 115323922 | 35062376 | CWSP - SHINGLE SPRINGS 2109-LR 9372-PH3 | 58080 | 0 | 0 | 0 |  | 2018-89227 | 58080 | 11 | 11965840 |  |  |  |  | 0 | 0
35062374 | Top 20% MAVF CPZ | 7 | PLAN | 2021061 | 8.53 | 8.53 | 2021 |  |  | 0 | 25808.23 | UNSE | 153652109 | SHINGLE SPRINGS 2109 | SHINGLE SPRINGS 21099372 | 190 | 17.8687 | 227 | 46.1342 | 0.24281 | 487 | 14.7555 | 554 | Tier 3 | PRE | SHINGLE SPRINGS | El Dorado | Sierra | Northern | 5783067 | E.5015572.01 | 115323920 | 35062374 | CWSP - SHINGLE SPRINGS 2109-LR 9372-PH1 | 45038.4 | 0 | 0 | 0 |  | 2018-89221 | 45038.4 | 8.53 | 9171850 |  |  |  |  | 0 | 0
35062375 | Top 20% MAVF CPZ | 7 | PLAN | 2021062 | 12.03 | 12.03 | 2021 |  |  | 0 | 3790.03 | UNSE | 153652109 | SHINGLE SPRINGS 2109 | SHINGLE SPRINGS 21099372 | 190 | 17.8687 | 227 | 46.1342 | 0.24281 | 487 | 20.81 | 554 | Tier 3 | PRE | SHINGLE SPRINGS | El Dorado | Sierra | Northern | 5783068 | E.5015571.01 | 115323921 | 35062375 | CWSP - SHINGLE SPRINGS 2109-LR 9372-PH2 | 63518.4 | 0 | 0 | 0 |  | 2018-89225 | 63518.4 | 12.03 | 13033162 |  |  |  |  | 0 | 0
35191318 | ECOP - Top 20% | 10 | PLAN | 2021043 | 1.78 | 1.78 | 2021 |  |  | 0 | 4167.82 | UNSE | 43432102 | SILVERADO 2102 | SILVERADO 210258626 | 125 | 15.2217 | 663 | 14.6249 | 0.117 | 627 | 1.1458 | 250 | Tier 3 | ECOP | SAINT HELENA | Napa | North Bay | Bay Area | 5541303 | E.5034352.01 | 119518390 | 35191318 | ECOP - SILVERADO 2102 - H02-LR58626 | 9398.4 | 0 | 0 | 0 | 2020-76797 | 2020-76801 | 9398.4 | 1.78 | 1685400 | - |  |  |  | 0 | 0
35191383 | ECOP - Top 20% | 10 | PLAN | 2021045 | 1.22 | 1.22 | 2021 |  |  | 0 | 1636.1 | UNSE | 43432102 | SILVERADO 2102 | SILVERADO 210258626 | 125 | 15.2217 | 663 | 14.6249 | 0.117 | 627 | 0.78535 | 250 | Tier 3 | ECOP | SAINT HELENA | Napa | North Bay | Bay Area | 5541309 | E.5034359.01 | 119518528 | 35191383 | ECOP - SILVERADO 2102 - H01-LR58626 | 6438 | 0 | 0 | 0 |  | 2020-78168 | 6441.6 | 1.22 | 1143750 | - |  |  |  | 0 | 0
35192284 | ECOP - Top 20% | 10 | PLAN | 2021036 | 5.89 | 5.89 | 2021 |  |  | 0 | 5596.71 | UNSE | 43432104 | SILVERADO 2104 | SILVERADO 2104726 | 263 | 30.3762 | 279 | 58.7725 | 0.22347 | 368 | 7.6354 | 582 | Tier 3 | ECOP | POPE VALLEY | Napa | North Bay | Bay Area | 5792107 | E.5034416.01 | 119556691 | 35192284 | ECOP - SILVERADO 2104 - H05-LR726 PH1 | 34008 | 0 | 0 | 0 |  | 2020-77337 |  | 0 |  | - |  |  |  | 0 | 0
| ECOP - Top 20% | 10 | PLAN | [8 empty] | UNSE | 43432104 | SILVERADO 2104 | SILVERADO 2104726 | 263 | 30.3762 | 279 | 58.7725 | 0.22347 | 368 | #DIV/0! | 582 | Tier 3 | ECOP | POPE VALLEY | Napa | North Bay | Bay Area | 5794998 | E.5034767.01.01 | 120245076 |  | ECOP - SILVERADO 2104 - H05-LR726 PH2 | [5 empty] | 2020-77337
| ECOP - Top 20% | 10 | PLAN | [8 empty] | UNSE | 43432104 | SILVERADO 2104 | SILVERADO 2104726 | 263 | 30.3762 | 279 | 58.7725 | 0.22347 | 368 | #DIV/0! | 582 | Tier 3 | ECOP | POPE VALLEY | Napa | North Bay | Bay Area | 5794998 | E.5034767.01.02 | 120245190 |  | ECOP - SILVERADO 2104 - H05-LR726 PH3 | [5 empty] | 2020-77337
| ECOP - Top 20% | 10 | PLAN | [8 empty] | UNSE | 43432104 | SILVERADO 2104 | SILVERADO 2104726 | 263 | 30.3762 | 279 | 58.7725 | 0.22347 | 368 | #DIV/0! | 582 | Tier 3 | ECOP | POPE VALLEY | Napa | North Bay | Bay Area | 5794998 | E.5034767.01.03 | 120245192 |  | ECOP - SILVERADO 2104 - H05-LR726 PH4 | [5 empty] | 2020-77337
| ECOP - Top 20% | 10 | PLAN | [8 empty] | UNSE | 43432104 | SILVERADO 2104 | SILVERADO 2104726 | 263 | 30.3762 | 279 | 58.7725 | 0.22347 | 368 | #DIV/0! | 582 | Tier 3 | ECOP | POPE VALLEY | Napa | North Bay | Bay Area | 5794998 | E.5034767.01.04 | 120245193 |  | ECOP - SILVERADO 2104 - H05-LR726 PH5 | [5 empty] | 2020-77337
35157845 | In-Construction | 20 | PLAN | 2021002 | 1.27 | 1.27 | 2020 | 0 |  | 0 | 415082.18 | CONS | 43432105 | SILVERADO 2105 | SILVERADO 2105658898 | 151 | 17.1737 | 1361 | 5.4002 | 0.035763 | 1546 | 0.26756 | 104 | Tier 2 | WDDB | SAINT HELENA | Napa | North Bay | Bay Area | 5784869 | E.5014317.04 | 116952175 | 35157845 | SILVERADO 2105 WIRE DOWN - PH 3 | 6693 | 0 | 0 | 0 |  | N/A |  |  |  | N/A | 0 | 0 | 6705.6 | 6705.6 | 1.27 | 2438400 | 2020-03939 | 2020-42595 | 0 | 0 | 6693 | 6693 | 1.2676 | 1404334 | 1800634 | 209.8213
35094513 | DSDD | 18 | PLAN | 2021029 | 1.92 | 1.92 | 2020 | 0 |  | 0 | 162001.21 | PEND | 162821702 | STANISLAUS 1702 | STANISLAUS 17021804 | 118 | 8.3797 | 2712 | 0.069602 | 0.00058985 | 2706 | 0.010685 | 19 | Tier 3 | CWSP | ARNOLD | Calaveras | Stockton | Central Valley | 5785245 | E.5014540.01 | 114567769 | 35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 | 10091 | 0 | 0 | 0 |  | 2018-52369 | 8131.2 | 1.54 | 1660057.143 | 2019-35971 | 0 | 0 | 10091 | 10091 | 1.9112 | 3669454.5455 | 2020-43006
35219093 | Top 50 Miles | 6 | PLAN | 2021049 | 3.67 | 3.67 | 2021 |  |  | 0 | 0 | UNSE | 14652106 | TIDEWATER 2106 | TIDEWATER 210614072 | 30 | 3.6652 | 18 | 19.5994 | 0.65331 | 59 | #DIV/0! |  |  | CWSP | CONCORD | Contra Costa | Diablo | Bay Area | 5794540 | E.5034692.01.01 | 120141622 | 35219093 | CWSP - TIDEWATER 210614072 | [5 empty] | 2020-87771 | 25396.8 | 4.81 | 8092656 |  |  |  |  | 0 | 0
35224320 | Top 20% MAVF CPZ | 6 | PLAN | 2021063 | 1.9034 | 1.9034 | 2021 |  |  | 0 | 2877.76 | UNSE | 42301101 | TULUCAY 1101 | TULUCAY 1101628 | 98 | 4.1726 | 338 | 19.2923 | 0.19686 | 448 | 5.8964 | 2350 | Tier 2 | WDDB | NAPA | Napa | North Bay | Bay Area | 5530168 |  | 113676059 | 31354988 | TULUCAY 1101 RECOND WITH TREE WIRE | 10050 | 0 | 0 | 0 |  | 2020-88272 | 7392 | 1.4 | 2360320 |  |  |  |  | 0 | 0
35217273 | Top 50 Miles | 7 | PLAN | 2021050 | 1.11 | 1.11 | 2021 |  |  | 0 | 213.67 | UNSE | 42871101 | UPPER LAKE 1101 | UPPER LAKE 1101CB | 3 | 1.1133 | 6 | 3.7676 | 1.2559 | 90 | 3.7114 |  | Tier 2 | CWSP | UPPER LAKE | Lake | North Coast | Northern | 5794203 | E.5034612.01.01 | 120048019 | 35217273 | CWSP - UPPER LAKE 1101 CB | 211.2 | 0 | 5596.8 | 0 | 2020-81991 | 2020-82007 | 211.2 | 0.04 | 970000 |  | 5596.8 |  | 211.2 | 5808 | 1.1
35219291 | Top 250 Miles | 6 | PLAN | 2021201 | 0.4 | 0.4 | 2021 |  |  | 0 | 0 | UNSE | 63591101 | VACA DIXON 1101 | VACA DIXON 1101126774 | 11 | 0.78766 | 20 | 6.8232 | 0.62029 | 24 | #DIV/0! |  |  | CWSP | VACAVILLE | Solano | Sacramento | Northern | 5543350 | E.5034693.01.01 | 120141627 | 35219291 | CWSP - VACA DIXON 1101126774 |  |  |  |  | 2021-01-07 | 2021-01500 | 2112 | 0.4 | 1561600 |  |  |  |  | 0 | 0
35219269 | Top 250 Miles | 2 | PLAN | 2021211 | 23.17 | 23.17 | 2021 |  |  | 0 | 0 | UNSE | 63591105 | VACA DIXON 1105 | VACA DIXON 110540092 | 464 | 23.1653 | 37 | 217.022 | 0.46772 | 100 | #DIV/0! |  |  | CWSP | VACAVILLE | Solano | Sacramento | Northern | 5794542 | E.5034704.01.01 | 120142106 | 35219269 | CWSP - VACA DIXON 110540092 |  |  |  |  | 2021-01-07 | [8 empty] | 0 | 0
35219590 | Top 250 Miles | 3 | PLAN | 2021227 | 0.75 | 0.75 | 2021 |  |  | 0 | 0 | UNSE | 63591105 | VACA DIXON 1105 | VACA DIXON 1105965390 | 21 | 0.75147 | 53 | 8.6971 | 0.41415 | 91 | #DIV/0! |  |  | CWSP | VACAVILLE | Solano | Sacramento | Northern | 5794542 | E.5034704.01.02 | 120165232 | 35219590 | CWSP - VACA DIXON 1105965390 |  |  |  |  | 2021-01-07
35219276 | Top 250 Miles | 6 | PLAN | 2021215 | 7.66 | 7.66 | 2021 |  |  | 0 | 0 | UNSE | 63601104 | VACAVILLE 1104 | VACAVILLE 11046542 | 140 | 14.6602 | 42 | 62.4985 | 0.44642 | 86 | #DIV/0! |  |  | CWSP | VACAVILLE | Solano | Sacramento | Northern | 5794545 | E.5034707.01.01 | 120142212 | 35219276 | CWSP - VACAVILLE 11046542 PH1 |  |  |  |  | 2021-01-08 | 2021-01037 | 40444.8 | 7.66 | 11826060 |  |  |  |  | 0 | 0
35224378 | Top 250 Miles | 6 | PLAN |  | 6.98 | 6.98 | 2021 |  |  | 0 |  | UNSE | 63601104 | VACAVILLE 1104 | VACAVILLE 11046542 | 140 | 14.6602 | 42 | 62.4985 | 0.44642 | 86 | #DIV/0! |  |  | CWSP | VACAVILLE | Solano | Sacramento | Northern | 5794545 | E.5034707.01.02 | 120406213 | 35224378 | CWSP - VACAVILLE 11046542 PH2 | [5 empty] | 2021-01589 | 36854.4 | 6.98 | 8840920
77799999 | Line Removal | 0 | PLAN | 2021068 | 31.8 | 31.8 | 2021 |  |  | 0 | 0 | UNSE | Various | VARIOUS | VARIOUS | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! |  |  |  | Various | Various | Various | Various |  |  |  |  | VARIOUS | [13 empty] | 0
35219273 | Top 250 Miles | 6 | PLAN | 2021213 | 3.48 | 3.48 | 2021 |  |  | 0 | 0 | UNSE | 102541101 | VOLTA 1101 | VOLTA 110149742 | 28 | 3.4766 | 39 | 13.0013 | 0.46433 | 6 | #DIV/0! |  |  | CWSP | MANTON | Tehama | North Valley | Northern | 5794543 | E.5034705.01.01 | 120142173 | 35219273 | CWSP - VOLTA 110149742 |  |  |  |  | 2020-12-31 | 2021-00903 | 18374.4 | 3.48 | 8182317 |  |  |  |  | 0 | 0
35219589 | Top 250 Miles | 6 | PLAN | 2021226 | 2.85 | 2.85 | 2021 |  |  | 0 | 0 | UNSE | 103611101 | WILDWOOD 1101 | WILDWOOD 11011454 | 31 | 7.8323 | 52 | 12.9837 | 0.41883 | 68 | #DIV/0! |  |  | CWSP | PLATINA | Shasta | North Valley | Northern | 5794561 | E.5034719.01.01 | 120165231 | 35219589 | CWSP - WILDWOOD 11011454 |  |  |  |  | 2021-01-08 | 2021-01188 | 15048 | 2.85 | 2940110
35224321 | Top 250 Miles | 6 | PLAN |  | 5.05 | 5.05 | 2021 |  |  | 0 |  | UNSE | 103611101 | WILDWOOD 1101 | WILDWOOD 11011454 | 31 | 7.8323 | 52 | 12.9837 | 0.41883 | 68 | #DIV/0! |  |  | CWSP | PLATINA | Tehama | North Valley | Northern | 5795128 | E.5034784.01.01 | 120401277 | 35224321 | CWSP - WILDWOOD 11011454 TEHAMA CO | [5 empty] | 2021-01193 | 26664 | 5.05 | 7710294
35199565 | FRRB - OH - 2021 | 18 | PLAN | 2021075 | 6.72 | 6.72 | 2021 |  |  | 0 | 7339371.72 | ESTS | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031508 | 249 | 27.2173 | 1176 | 12.4656 | 0.050062 | 1498 | 2.0621 |  |  | FRRB | OROVILLE | Butte | North Valley | Northern | 5541890 |  | 119750044 | 35199565 | NO-NV-BUTTE 9/8/20- N. CMPLX FIRE SYS H | 35481.6 | 0 | 0 | 0 | [9 empty] | 0
35200051 | FRRB - UG - 2021 | 18 | PLAN | 2021076 | 7.25 | 7.25 | 2021 |  |  | 0 | 3333378.58 | ESTS | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031508 | 249 | 27.2173 | 1176 | 12.4656 | 0.050062 | 1498 | 3.2873 |  |  | FRRB | OROVILLE | Butte | North Valley | Northern | 5541890 |  | 119765913 | 35200051 | NO-NV-BUTTE 9/8/20- N. CMPLX FIRE SYS H | 0 | 38280 | 0 | 0 | [9 empty] | 0
35223344 | FRRB - UG - 2021 | 2 | PLAN | [8 empty] | UNSE | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 259 | 22.4168 | 1849 | 3.3188 | 0.012814 | 1756 | #DIV/0! |  |  | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5793918 | E.5034572.01.09 | 120255980 | 35223344 | FRRB - WYANDOTTE 1103 - LR 1974 UG
35223345 | FRRB - UG - 2021 | 2 | PLAN | [8 empty] | UNSE | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031976 | 217 | 23.7815 | 1299 | 8.7412 | 0.040282 | 1128 | #DIV/0! |  |  | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5793918 | E.5034572.01.10 | 120255982 | 35223345 | FRRB - WYANDOTTE 1103 - LR 1976 UG
35223039 | PSPS - Community Resiliency | 6 | PLAN | 2021092 | 0.77 | 0.77 | 2021 |  |  | 0 | 0 | UNSE | 102911109 | WYANDOTTE 1109 | WYANDOTTE 1109702710 | 49 | 2.6641 | 218 | 12.174 | 0.24845 | 672 | 3.4834 |  |  | PSPS | OROVILLE | Butte | North Valley | Northern | 5794987 | E.5034763.01.01 | 120242691 | 35223039 | PSPS - Wyandotte 1109702710 |  | 1600 |  |  |  | 2021-01576 | 4065.6 | 0.77 | 1517740 |  |  |  |  | 0
35219260 | Top 250 Miles | 6 | PLAN | 2021206 | 1.31 | 1.31 | 2021 |  |  | 0 | 0 | UNSE | 102911109 | WYANDOTTE 1109 | WYANDOTTE 110932586 | 15 | 1.3417 | 29 | 7.9481 | 0.52987 | 260 | #DIV/0! |  |  | CWSP | OROVILLE | Butte | North Valley | Northern | 5543352 | E.5034698.01.01 | 120141880 | 35219260 | CWSP - WYANDOTTE 110932586 |  |  |  |  | 2021-01-07 | 2021-01235 | 6916.8 | 1.31 | 2194368 |  |  |  |  | 0 | 0
31361965 | In-Construction - PEND |  | HOLD | 2021777 | 0.45 | 0.45 | 2021 |  |  |  | 130197.7 | CONS | 43071101 | DUNBAR 1101 | DUNBAR 110147964 | 68 | 6.5107 | 1794 | 0.99704 | 0.014662 | 1845 | 0.068224 | 1151 | Tier 3 | WDDB | KENWOOD | Sonoma | Sonoma | Northern | 5530175 |  | 113751296 | 31361965 | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 |  | 2367 | 0 | 0 | 0 | 2018-69430 | 2300 | 0.43561 | 345000 | N/A |  |  |  | 0 | 0 | 0 | 2019-35371 | 2019-34365 | 0 | 0 | 2367 | 2367 | 0.4483 | 797947 | 1245293 | 337.1132
35098621 | Completed |  | COMP |  | 1.07 | 0 | 2020 | 1.07 |  | 1.07 | 1372204.3 | DOCC | 152471101 | COLUMBIA HILL 1101 | COLUMBIA HILL 11012212 | 76 | 9.1336 | 606 | 9.8207 | 0.12922 | 1358 | 1.0162 | 198 | Tier 3 | PRE | NORTH SAN JUAN | Nevada | Sierra | Northern | 5785303 | E.5015491.04 | 117177530 | 35098621 | CWSP-COLUMBIA HILL 1101-LR2212-PH4 | 1881 | 3761 | 0 | 0 |  | 2018-57269 | 9820.8 | 1.86 | 1975040 | 2019-28761 | 0 | 0 | 5649.6 | 5649.6 | 1.07 | 2054400 | 2019-39374 | 2020-25928 | 0 | 3761 | 1881 | 5642 | 1.0686 | 2185500 | 2927538 | 387.3626
35145001 | PSPS - HOLD |  | HOLD |  | 1.6 | 1.6 | 2021 |  |  |  | 146558.55 | PEND | 12022215 | CLAYTON 2215 | CLAYTON 2215184604 | 106 | 2.0891 | 1739 | 1.7951 | 0.016935 | 1716 | 1.3512 | 1165 | Tier 3 | PSPS | CONCORD | CONTRA COSTA | Diablo | Bay Area | 5788778 | E.5025639 | 118259181 | 35145001 | PSPS - Clayton 2215 – CB | 475.2 | 20592 | 0 | 0 |  | 2019-79149 | 11616 | 2.2 | 19530000 | N/A | 0 | 20592 | 475.2 | 21067.2 | 3.99 | 16758000
35144944 | PSPS - HOLD |  | HOLD |  | 0.26 | 0.26 | 2021 |  |  |  | 118187.81 | PEND | 22721107 | SNEATH LANE 1107 | SNEATH LANE 1107CB | 45 | 1.0038 | 2336 | 0.14045 | 0.003121 | 2144 | 0.036015 | 2845 | Tier 3 | PSPS | SOUTH SAN FRANCISO | SAN MATEO | Peninsula | Central Coast | 5530170 |  | 118261958 | 35144944 | PSPS – Sneath Lane 1107 – CB | 0 | 739.2 | 0 | 0 |  | 2019-78877 | 739.2 | 0.14 | 738936 | N/A | 0 | 739.2 | 0 | 739.2 | 0.14 | 588000 | 2020-18832
35145002 | PSPS - HOLD |  | HOLD |  | 0.68 | 0.68 | 2021 |  |  |  | 115275.8 | APPR | 42481101 | IGNACIO 1101 | IGNACIO 1101CB | 19 | 1.6722 | 2448 | 0.042331 | 0.0022279 | 2447 | 0.017042 | 2421 | Tier 3 | PSPS | NOVATO | MARIN | North Bay | Bay Area | 5788780 | E.5025640 | 118262844 | 35145002 | PSPS - Ignacio 1101 - CB | 0 | 3590.4 | 0 | 0 |  | 2019-78952 | 3585.12 | 0.679 | 2194800 | N/A | 0 | 3590.4 | 0 | 3590.4 | 0.68 | 2856000
35145003 | PSPS - HOLD |  | HOLD |  | 0.28 | 0.28 | 2021 |  |  |  | 92273.67 | PEND | 13801103 | MORAGA 1103 | MORAGA 1103CB | 82 | 1.3309 | 2631 | 0.082476 | 0.0010058 | 2698 | 0.017178 | 2231 | Tier 3 | PSPS | ORINDA | CONTRA COSTA | Diablo | Bay Area | 5788781 | E.5025641 | 118263229 | 35145003 | PSPS - Moraga 1103 - CB | 0 | 1161.6 | 0 | 0 |  | 2019-78960 | 1161.6 | 0.22 | 2050000 | N/A | 0 | 1161.6 | 0 | 1161.6 | 0.22 | 924000 | 2020-33628
35144941 | PSPS - HOLD |  | HOLD |  | 2.59 | 2.59 | 2021 |  |  |  | 180088.06 | ADER | 83252105 | PAUL SWEET 2105 | PAUL SWEET 2105CB | 86 | 7.4461 | 2633 | 0.086208 | 0.0010024 | 2727 | 0.020645 | 1376 | Tier 3 | PSPS | SANTA CRUZ | SANTA CRUZ | Central Coast | Central Coast | 5788792 | E.5025646 | 118261469 | 35144941 | PSPS - Paul Sweet 2105 - CB PH 1 | 17212.8 | 1056 | 0 | 0 |  | 2020-07355 | 16737.6 | 3.17 | 4786588 | N/A | 0 | 1056 | 17212.8 | 18268.8 | 3.46 | 14532000 | 2020-45854
35144943 | PSPS - HOLD |  | HOLD |  | 0.63 | 0.63 | 2021 |  |  |  | 95498.4 | ESTS | 83692105 | ROB ROY 2105 | ROB ROY 2105CB | 17 | 0.73407 | 2781 | 0.0058961 | 0.00034683 | 2817 | 0.0050096 | 2564 | Tier 3 | PSPS | APTOS | SANTA CRUZ | Central Coast | Central Coast | 5788791 | E.5025648 | 118261587 | 35144943 | PSPS - Rob Roy 2105 - CB | 0 | 2851.2 | 0 | 0 |  | 2020-03578 | 3326.4 | 0.63 | 1574100 | N/A | 0 | 2851.2 | 0 | 2851.2 | 0.54 | 2268000
35145004 | PSPS - HOLD |  | HOLD |  | 0.62 | 0.62 | 2021 |  |  |  | 86709.38 | PEND | 14161106 | ROSSMOOR 1106 | ROSSMOOR 1106CB | 60 | 1.8254 | 3259 | 0.00030957 | 5.1594e-06 | 2856 | 0.00010409 | 1372 | Tier 3 | PSPS | LAFAYETTE | CONTRA COSTA | Diablo | Bay Area | 5788782 | E.5025642 | 118263746 | 35145004 | PSPS - Rossmoor 1106 – CB | 0 | 4171.2 | 0 | 0 |  | 2019-79022 | 2112 | 0.4 | 3720000 | N/A | 0 | 4171.2 | 0 | 4171.2 | 0.79 | 3318000 | 2020-31291
35145006 | PSPS - HOLD |  | HOLD |  | 0.27 | 0.27 | 2021 |  |  |  | 126808.89 | ESTS | 43201101 | STAFFORD 1101 | STAFFORD 1101902998 | 81 | 1.0766 | 3483 | 0.00018615 | 2.2981e-06 | 3428 | 4.6216e-05 | 2388 | Tier 3 | PSPS | NOVATO | MARIN | North Bay | Bay Area | 5788788 | E.5025644 | 118263874 | 35145006 | PSPS - Stafford 1101 - LR 1298 | 0 | 1425.6 | 0 | 0 |  | 2019-79042 | 1425.6 | 0.27 | 2500000 | N/A | 0 | 1425.6 | 0 | 1425.6 | 0.27 | 1134000 | 2020-51115
35145522 | PSPS - HOLD |  | HOLD |  | 3.95 | 3.95 | 2021 |  |  |  | 142609.46 | PEND | 153612104 | CLARKSVILLE 2104 | CLARKSVILLE 2104CB | 107 | 8.8028 | 134 | 32.5187 | 0.30391 | 385 | 14.4458 | 541 | Tier 3 | PSPS | El Dorado Hills | El Dorado | Sierra | Northern | 5788783 | E.5025635.01 | 118265394 | 35145522 | PSPS - Clarksville 2104 - CB | 0 | 13464 | 0 | 0 |  | 2019-80671 | 13464 | 2.55 | 23720000 | N/A | 0 | 13464 | 0 | 13464 | 2.55 | 10710000 | 2020-38602
|  |  | CNCL |  | 0.04 | 0.04 | 2021 |  |  |  | 0 | CNCL | 48011144 | CALPINE 1144 | CALPINE 1144304 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! |  |  | CWSP |  |  |  |  | 5543354 | E.5034701.01.01 |  | CNCL | CWSP - CALPINE 1144304 | [13 empty] | 0 | 0
35072360 | In-Construction - HOLD |  | HOLD |  | 1.05 | 1.05 | 2021 |  |  |  | 718998.64 | CONS | 163692102 | SALT SPRINGS 2102 | SALT SPRINGS 21023142 | 256 | 17.9625 | 2659 | 0.22061 | 0.00086175 | 2600 | 0.0086401 | 8 | Tier 3 | PRE | ARNOLD | Calaveras | Stockton | Central Valley | 5783906 | E.5015236.01 | 114754229 | 35072360 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.1 | 5541 | 0 | 0 | 0 |  | 2018-60542 | 7708.8 | 1.46 | 1574171 | 2019-35904 | 0 | 0 | 5305 | 5305 | 1.0047 | 1929090.9091 | 2019-64378 | 2020-45688 | 0 | 0 | 5541 | 5541 | 1.0494 | 1932059 | 2583069 | 348.6842

## conductor_pz_summary_hftd_23_re
PZ_idx | circuit_protection_zone_id | feeder_id | feeder_name | device_operating_number | hftd_23_primary_length_under_1km | primary_length_m | primary_length_m_hftd_23 | Miles | pixel_count | mean_ignition_probability | ignition_rank | mean_mavf_core | mavf_consequence_rank | mean_mavf_core_risk | Total Risk Value | mean_mavf_core_risk_rank | kpmg_Consolidated Risk Score | KPMG_rank
10544 | OREGON TRAIL 1103CUS391 | 103521103 | OREGON TRAIL 1103 | CUS391 | TRUE | 36.3577 | 36.3577 | 0.022596 | 1 | 0.00039685 | 69 | 7972.4858 | 5 | 3.1639 | 3.1639 | 1 |  | 3570
11024 | CALPINE 1144276-G | 48011144 | CALPINE 1144 | 276-G | TRUE | 23.7478 | 23.7478 | 0.014759 | 1 | 0.00025382 | 208 | 7401.5283 | 7 | 1.8786 | 1.8786 | 2 | 0.16 | 1261
9665 | MARIPOSA 210190130 | 254452101 | MARIPOSA 2101 | 90130 | TRUE | 151.1499 | 151.1499 | 0.09394 | 1 | 0.00016255 | 619 | 10411.5469 | 1 | 1.6924 | 1.6924 | 3 | 2.44 | 603
9783 | SHEPHERD 2111688294 | 252062111 | SHEPHERD 2111 | 688294 | TRUE | 24.3604 | 24.3604 | 0.01514 | 1 | 0.0001714 | 553 | 8415.9766 | 3 | 1.4425 | 1.4425 | 4 |  | 3420
10354 | MIDDLETOWN 1103CB | 43141103 | MIDDLETOWN 1103 | CB | TRUE | 289.8399 | 85.2366 | 0.052975 | 4 | 0.00035401 | 88 | 3206.0204 | 240 | 1.3006 | 5.2026 | 5 | 0.29 | 1032
10600 | UPPER LAKE 1101CB | 42871101 | UPPER LAKE 1101 | CB | FALSE | 1791.2622 | 1791.2622 | 1.1133 | 3 | 0.0002511 | 214 | 4819.6954 | 90 | 1.2559 | 3.7676 | 6 | 0.09 | 1534
8894 | KESWICK 11011586 | 103451101 | KESWICK 1101 | 1586 | FALSE | 11983.5348 | 11983.5348 | 7.4478 | 39 | 0.00044628 | 48 | 3225.6011 | 233 | 1.2524 | 48.8434 | 7 | 0.24 | 1102
6776 | MIDDLETOWN 1102302610 | 43141102 | MIDDLETOWN 1102 | 302610 | FALSE | 9188.9357 | 7571.5921 | 4.7058 | 53 | 0.00021011 | 357 | 4327.9371 | 121 | 0.91632 | 48.565 | 8 |  | 3061
2373 | KONOCTI 1102965078 | 43311102 | KONOCTI 1102 | 965078 | FALSE | 11264.1399 | 10089.0761 | 6.2704 | 59 | 0.00026416 | 185 | 3338.3605 | 220 | 0.87629 | 51.7008 | 9 |  | 2774
5527 | MARIPOSA 2102241564 | 254452102 | MARIPOSA 2102 | 241564 | FALSE | 1774.1526 | 1146.9072 | 0.71281 | 14 | 0.0001265 | 1073 | 6191.5313 | 26 | 0.77248 | 10.8148 | 10 |  | 2961
7968 | BUCKS CREEK 1101CB | 102211101 | BUCKS CREEK 1101 | CB | FALSE | 7724.4676 | 7724.4676 | 4.8008 | 13 | 0.00026518 | 181 | 3512.0536 | 200 | 0.73491 | 9.5539 | 11 | 0.13 | 1365
10918 | DEL MAR 2109378446 | 152582109 | DEL MAR 2109 | 378446 | TRUE | 173.2196 | 157.9488 | 0.098166 | 3 | 0.00015629 | 683 | 4122.2296 | 142 | 0.73151 | 2.1945 | 12 |  | 3619
6966 | MIDDLETOWN 1102CB | 43141102 | MIDDLETOWN 1102 | CB | TRUE | 1420.4117 | 752.0336 | 0.46739 | 12 | 0.00032056 | 109 | 1676.5244 | 530 | 0.72481 | 8.6977 | 13 | 0.71 | 802
3511 | MIDDLETOWN 1103830 | 43141103 | MIDDLETOWN 1103 | 830 | FALSE | 62803.2175 | 44622.1036 | 27.7328 | 212 | 0.00015679 | 675 | 4619.5228 | 102 | 0.71618 | 151.8291 | 14 | 0.14 | 1322
9537 | POSO MOUNTAIN 2104CB | 253642104 | POSO MOUNTAIN 2104 | CB | FALSE | 12231.0905 | 8613.688 | 5.3534 | 38 | 0.00011189 | 1370 | 5318.8037 | 51 | 0.70423 | 26.7607 | 15 | 0.04 | 2163
10827 | INDIAN FLAT 11044440 | 252691104 | INDIAN FLAT 1104 | 4440 | TRUE | 376.2849 | 376.2849 | 0.23386 | 4 | 0.00015164 | 724 | 3234.1311 | 230 | 0.68656 | 2.7463 | 16 | 1.05 | 722
10242 | ELK CREEK 1101CB | 102781101 | ELK CREEK 1101 | CB | TRUE | 135.534 | 135.534 | 0.084235 | 1 | 9.9283e-05 | 1662 | 6756.3685 | 11 | 0.67079 | 0.67079 | 17 | 2.37 | 609
5791 | TIDEWATER 210614072 | 14652106 | TIDEWATER 2106 | 14072 | FALSE | 6206.8729 | 5897.3117 | 3.6652 | 30 | 0.0001306 | 999 | 5236.689 | 59 | 0.65331 | 19.5994 | 18 | 0.05 | 2003
10735 | HARTLEY 1101980662 | 43211101 | HARTLEY 1101 | 980662 | TRUE | 366.2635 | 366.2635 | 0.22763 | 3 | 0.00014325 | 821 | 4824.4797 | 89 | 0.64187 | 1.9256 | 19 |  | 3599
10532 | VACA DIXON 1101126774 | 63591101 | VACA DIXON 1101 | 126774 | FALSE | 1267.3386 | 1267.3386 | 0.78766 | 11 | 9.3598e-05 | 1808 | 6310.2508 | 24 | 0.62029 | 6.8232 | 20 |  | 3568
10277 | KIRKER 2104442850 | 14452104 | KIRKER 2104 | 442850 | FALSE | 9258.545 | 9258.545 | 5.7542 | 30 | 9.1768e-05 | 1852 | 6349.6612 | 21 | 0.61454 | 18.4361 | 21 | 0.08 | 1644
8742 | COARSEGOLD 2104CB | 254432104 | COARSEGOLD 2104 | CB | FALSE | 3906.143 | 3906.143 | 2.4277 | 27 | 0.00013159 | 989 | 4767.3932 | 95 | 0.59573 | 16.0848 | 22 | 2.54 | 600
8905 | MIDDLETOWN 1101118494 | 43141101 | MIDDLETOWN 1101 | 118494 | FALSE | 1737.509 | 1714.9565 | 1.0659 | 12 | 0.00012542 | 1091 | 4982.7835 | 79 | 0.58092 | 6.971 | 23 |  | 3276
10515 | STAFFORD 1102784704 | 43201102 | STAFFORD 1102 | 784704 | TRUE | 43.8835 | 43.8835 | 0.027274 | 1 | 0.00019096 | 437 | 2953.5029 | 279 | 0.564 | 0.564 | 24 | 1.81 | 641
10181 | PEABODY 2108113684 | 63642108 | PEABODY 2108 | 113684 | TRUE | 748.9574 | 590.6521 | 0.36709 | 4 | 9.2988e-05 | 1823 | 6848.1417 | 10 | 0.55276 | 2.211 | 25 |  | 3509
7688 | PEABODY 2106250154 | 63642106 | PEABODY 2106 | 250154 | TRUE | 458.5489 | 458.5489 | 0.28499 | 4 | 0.00011419 | 1315 | 5210.7292 | 61 | 0.55243 | 2.2097 | 26 |  | 3150
7743 | HIGHLANDS 1102628 | 43361102 | HIGHLANDS 1102 | 628 | FALSE | 22883.905 | 22883.905 | 14.2224 | 51 | 0.00010064 | 1633 | 5903.6105 | 33 | 0.5487 | 27.9838 | 27 | 5.08 | 496
6480 | TASSAJARA 21123202 | 14662112 | TASSAJARA 2112 | 3202 | TRUE | 630.3021 | 630.3021 | 0.39174 | 9 | 8.3995e-05 | 2093 | 6312.7784 | 23 | 0.53731 | 4.8358 | 28 | 9.63 | 406
10043 | WYANDOTTE 110932586 | 102911109 | WYANDOTTE 1109 | 32586 | FALSE | 2375.6773 | 2158.8587 | 1.3417 | 15 | 0.00014236 | 834 | 3072.9006 | 260 | 0.52987 | 7.9481 | 29 | 1.13 | 712
10052 | POSO MOUNTAIN 2103CB | 253642103 | POSO MOUNTAIN 2103 | CB | FALSE | 3746.9222 | 3746.9222 | 2.3287 | 10 | 5.421e-05 | 2939 | 9615.8541 | 2 | 0.51619 | 5.1619 | 30 | 0.05 | 1951
10924 | CALPINE 1146200-G | 48011146 | CALPINE 1146 | 200-G | TRUE | 13.7161 | 13.7161 | 0.0085246 | 1 | 0.00015982 | 645 | 3189.8253 | 242 | 0.50979 | 0.50979 | 31 | 18.16 | 324
11090 | CALPINE 1146394G | 48011146 | CALPINE 1146 | 394G | TRUE | 18.1683 | 18.1683 | 0.011292 | 1 | 0.00015982 | 646 | 3189.8253 | 243 | 0.50979 | 0.50979 | 32 | 18.15 | 325
4828 | CRESTA 1101546650 | 102251101 | CRESTA 1101 | 546650 | FALSE | 1443.177 | 1443.177 | 0.89694 | 6 | 0.00052979 | 27 | 978.3256 | 845 | 0.50291 | 3.0174 | 33 |  | 2920
9923 | CLOVERDALE 110247214 | 42821102 | CLOVERDALE 1102 | 47214 | TRUE | 43.972 | 43.972 | 0.027329 | 1 | 5.8357e-05 | 2823 | 8298.4728 | 4 | 0.48427 | 0.48427 | 34 | 2.46 | 602
8034 | MARIPOSA 2102CB | 254452102 | MARIPOSA 2102 | CB | FALSE | 8571.1084 | 8453.5074 | 5.2539 | 31 | 0.00011156 | 1382 | 3466.6155 | 205 | 0.47165 | 14.6212 | 35 | 0.06 | 1807
7873 | MARIPOSA 210197142 | 254452101 | MARIPOSA 2101 | 97142 | FALSE | 7406.0615 | 7406.0615 | 4.6029 | 40 | 0.00010428 | 1545 | 5130.9585 | 66 | 0.47122 | 18.8487 | 36 | 0.05 | 1966
4526 | VACA DIXON 110540092 | 63591105 | VACA DIXON 1105 | 40092 | FALSE | 68288.9427 | 37272.9556 | 23.1653 | 464 | 0.00010079 | 1627 | 4668.9585 | 100 | 0.46772 | 217.022 | 37 | 5.23 | 493
2215 | MIDDLETOWN 1101481876 | 43141101 | MIDDLETOWN 1101 | 481876 | FALSE | 2559.0375 | 1373.1162 | 0.8534 | 14 | 8.3175e-05 | 2127 | 5568.7809 | 46 | 0.46769 | 6.5476 | 38 |  | 2766
9655 | VOLTA 110149742 | 102541101 | VOLTA 1101 | 49742 | FALSE | 5593.8568 | 5593.8568 | 3.4766 | 28 | 5.8016e-05 | 2835 | 7932.3948 | 6 | 0.46433 | 13.0013 | 39 | 0.05 | 1993
10699 | SUNOL 110148180 | 14241101 | SUNOL 1101 | 48180 | TRUE | 21.1502 | 21.1502 | 0.013145 | 2 | 8.1559e-05 | 2167 | 5130.0926 | 67 | 0.46103 | 0.92206 | 40 | 0.05 | 1938
7414 | PUTAH CREEK 110246012 | 63681102 | PUTAH CREEK 1102 | 46012 | FALSE | 4834.6736 | 1025.1447 | 0.63713 | 38 | 9.4944e-05 | 1768 | 4755.8708 | 96 | 0.45557 | 17.3115 | 41 |  | 3124
4076 | VACAVILLE 11046542 | 63601104 | VACAVILLE 1104 | 6542 | FALSE | 23588.1989 | 23588.1989 | 14.6602 | 140 | 0.00010109 | 1623 | 4849.1896 | 86 | 0.44642 | 62.4985 | 42 | 0.1 | 1469
7056 | POTTER VALLEY P H 110564118 | 42281105 | POTTER VALLEY P H 1105 | 64118 | FALSE | 15416.9418 | 2646.9433 | 1.6451 | 101 | 0.00019755 | 406 | 2096.5335 | 427 | 0.44262 | 44.7046 | 43 | 0.02 | 2515
10934 | POINT MORETTI 1101CB | 82931101 | POINT MORETTI 1101 | CB | TRUE | 20.574 | 20.574 | 0.012787 | 1 | 0.00031529 | 111 | 1402.4592 | 637 | 0.44218 | 0.44218 | 44 | 0.04 | 2165
5032 | MOUNTAIN QUARRIES 21016953 | 152282101 | MOUNTAIN QUARRIES 2101 | 6953 | FALSE | 9187.973 | 9187.973 | 5.7104 | 58 | 0.00011159 | 1378 | 4228.1533 | 135 | 0.4353 | 25.2473 | 45 | 4.2 | 525
9729 | BRENTWOOD 210596324 | 14592105 | BRENTWOOD 2105 | 96324 | TRUE | 775.7684 | 775.7684 | 0.48214 | 6 | 0.00013262 | 970 | 3560.1407 | 193 | 0.4317 | 2.5902 | 46 | 0.03 | 2285
6662 | NORTH DUBLIN 2101CB | 14052101 | NORTH DUBLIN 2101 | CB | FALSE | 2942.9352 | 2836.5864 | 1.7629 | 23 | 0.00018049 | 510 | 2272.276 | 388 | 0.42859 | 9.8576 | 47 | 0.07 | 1708
1690 | DESCHUTES 11049718 | 103351104 | DESCHUTES 1104 | 9718 | FALSE | 56853.1165 | 29935.2858 | 18.6049 | 357 | 8.8629e-05 | 1967 | 4802.059 | 94 | 0.42526 | 151.8163 | 48 | 0.07 | 1758
193 | OREGON TRAIL 110335002 | 103521103 | OREGON TRAIL 1103 | 35002 | FALSE | 91942.988 | 91942.988 | 57.1429 | 641 | 0.00011631 | 1264 | 3934.2214 | 153 | 0.42185 | 270.4028 | 49 | 0.4 | 943
7274 | MARIPOSA 2102440236 | 254452102 | MARIPOSA 2102 | 440236 | FALSE | 6874.8043 | 6874.8043 | 4.2727 | 38 | 0.00016814 | 575 | 3899.3651 | 157 | 0.4205 | 15.979 | 50 |  | 3110
10024 | CLEAR LAKE 1101881362 | 42141101 | CLEAR LAKE 1101 | 881362 | TRUE | 1747.5089 | 480.0321 | 0.29834 | 10 | 0.00010401 | 1552 | 3804.2183 | 168 | 0.41959 | 4.1959 | 51 |  | 3475
7141 | WILDWOOD 11011454 | 103611101 | WILDWOOD 1101 | 1454 | FALSE | 12602.1173 | 12602.1173 | 7.8323 | 31 | 9.3126e-05 | 1817 | 5114.2446 | 68 | 0.41883 | 12.9837 | 52 | 0.03 | 2353
7033 | VACA DIXON 1105965390 | 63591105 | VACA DIXON 1105 | 965390 | FALSE | 2587.1085 | 1209.1092 | 0.75147 | 21 | 9.949e-05 | 1657 | 4819.484 | 91 | 0.41415 | 8.6971 | 53 |  | 3088
9936 | OLETA 1101754718 | 163541101 | OLETA 1101 | 754718 | FALSE | 4640.5633 | 4640.5633 | 2.8841 | 29 | 0.00013445 | 936 | 2737.1841 | 306 | 0.40712 | 11.8066 | 54 |  | 3456
10113 | CALISTOGA 1101CB | 42711101 | CALISTOGA 1101 | CB | TRUE | 1122.2361 | 221.6704 | 0.13777 | 9 | 0.00036283 | 82 | 802.2368 | 941 | 0.40561 | 3.6505 | 55 | 0.11 | 1412
9252 | STANISLAUS 1701CB | 162821701 | STANISLAUS 1701 | CB | FALSE | 11032.7196 | 11032.7196 | 6.8569 | 54 | 0.00014918 | 748 | 2134.6994 | 416 | 0.40353 | 21.7909 | 56 | 0.11 | 1422
9014 | MARIPOSA 2101CB | 254452101 | MARIPOSA 2101 | CB | FALSE | 4029.4321 | 4029.4321 | 2.5043 | 34 | 0.00017446 | 532 | 2332.9065 | 378 | 0.39837 | 13.5444 | 57 | 0.04 | 2081
4909 | HARTLEY 1101698 | 43211101 | HARTLEY 1101 | 698 | FALSE | 16605.929 | 11071.0466 | 6.8807 | 97 | 9.4179e-05 | 1790 | 4392.8078 | 115 | 0.39723 | 38.5312 | 58 | 0.06 | 1832
9239 | BANGOR 1101979830 | 103191101 | BANGOR 1101 | 979830 | TRUE | 696.7531 | 680.7511 | 0.42309 | 7 | 7.12e-05 | 2441 | 5107.124 | 69 | 0.3972 | 2.7804 | 59 |  | 3328
4242 | POTTER VALLEY P H 110495878 | 42281104 | POTTER VALLEY P H 1104 | 95878 | FALSE | 30094.5573 | 9856.7705 | 6.126 | 191 | 0.00017374 | 535 | 2217.9989 | 398 | 0.3965 | 75.7306 | 60 | 0.02 | 2524
2058 | COARSEGOLD 21045310 | 254432104 | COARSEGOLD 2104 | 5310 | FALSE | 45195.5088 | 45195.5088 | 28.0892 | 299 | 6.7329e-05 | 2551 | 6694.8526 | 15 | 0.39401 | 117.8076 | 61 | 19.51 | 312
8298 | STAFFORD 1102361952 | 43201102 | STAFFORD 1102 | 361952 | FALSE | 2196.587 | 2196.587 | 1.3652 | 9 | 0.00011545 | 1290 | 3151.4111 | 248 | 0.39288 | 3.536 | 62 | 1.9 | 631
1488 | AUBERRY 1101CB | 254151101 | AUBERRY 1101 | CB | FALSE | 29229.2172 | 29229.2172 | 18.1661 | 204 | 8.2084e-05 | 2150 | 5306.8686 | 52 | 0.39206 | 79.9801 | 63 | 0.11 | 1431
3596 | VACAVILLE 11088762 | 63601108 | VACAVILLE 1108 | 8762 | FALSE | 26274.6884 | 22259.6162 | 13.8344 | 147 | 7.8661e-05 | 2244 | 4502.8739 | 108 | 0.39138 | 57.5327 | 64 | 0.12 | 1395
6014 | OREGON TRAIL 11041634 | 103521104 | OREGON TRAIL 1104 | 1634 | FALSE | 29441.3626 | 29110.7694 | 18.0925 | 192 | 8.4909e-05 | 2064 | 4929.5026 | 80 | 0.39094 | 75.0607 | 65 | 0.18 | 1222
6392 | COARSEGOLD 210410335 | 254432104 | COARSEGOLD 2104 | 10335 | FALSE | 9369.0411 | 9369.0411 | 5.8229 | 69 | 9.5888e-05 | 1732 | 4247.144 | 133 | 0.39082 | 26.9663 | 66 | 1.53 | 668
7352 | JAMESON 1102865502 | 63801102 | JAMESON 1102 | 865502 | TRUE | 4467.1172 | 644.9532 | 0.40084 | 27 | 0.00011299 | 1344 | 3613.4467 | 189 | 0.38957 | 10.5185 | 67 |  | 3119
3943 | MOUNTAIN QUARRIES 2101CB | 152282101 | MOUNTAIN QUARRIES 2101 | CB | FALSE | 40215.5467 | 40215.5467 | 24.9941 | 262 | 0.00012902 | 1029 | 2606.3425 | 328 | 0.38665 | 101.3032 | 68 | 9.11 | 412
2633 | PASO ROBLES 1103N54 | 182611103 | PASO ROBLES 1103 | N54 | FALSE | 34748.7236 | 32201.1783 | 20.0132 | 221 | 9.3045e-05 | 1819 | 4184.3432 | 138 | 0.38568 | 85.2354 | 69 | 3.07 | 564
6808 | PHILO 110137222 | 42601101 | PHILO 1101 | 37222 | FALSE | 40893.1758 | 40893.1758 | 25.4153 | 152 | 0.00011309 | 1341 | 3498.721 | 202 | 0.3839 | 58.3523 | 70 | 0.05 | 2044
8006 | RISING RIVER 11011532 | 103551101 | RISING RIVER 1101 | 1532 | FALSE | 7926.8978 | 6133.1893 | 3.8118 | 27 | 6.5114e-05 | 2606 | 6536.3281 | 17 | 0.38077 | 10.2807 | 71 | 0.01 | 2591
10120 | DEL MAR 210975802 | 152582109 | DEL MAR 2109 | 75802 | TRUE | 680.0226 | 576.1553 | 0.35808 | 6 | 0.0002061 | 377 | 1316.5155 | 676 | 0.37901 | 2.2741 | 72 | 3.09 | 563
8754 | NOTRE DAME 11042408 | 102041104 | NOTRE DAME 1104 | 2408 | FALSE | 22439.0865 | 18541.2413 | 11.5235 | 76 | 0.00027566 | 167 | 1710.6647 | 521 | 0.37815 | 28.7393 | 73 | 0.15 | 1306
5603 | HIGHLANDS 1102623120 | 43361102 | HIGHLANDS 1102 | 623120 | FALSE | 12233.579 | 10535.1094 | 6.5476 | 67 | 0.00013171 | 986 | 3211.1058 | 239 | 0.3774 | 25.2855 | 74 |  | 2966
2079 | POTTER VALLEY P H 11051904 | 42281105 | POTTER VALLEY P H 1105 | 1904 | FALSE | 64429.3728 | 51242.8521 | 31.8476 | 332 | 0.00018482 | 475 | 1914.8501 | 471 | 0.37685 | 125.1141 | 75 | 0.11 | 1439
8836 | VOLTA 1101CB | 102541101 | VOLTA 1101 | CB | FALSE | 14817.1823 | 14817.1823 | 9.2089 | 80 | 0.00011233 | 1359 | 3549.008 | 194 | 0.37545 | 30.036 | 76 | 0.07 | 1694
10966 | HICKS 2101984788 | 83432101 | HICKS 2101 | 984788 | TRUE | 5.0644 | 5.0644 | 0.0031475 | 1 | 7.6238e-05 | 2303 | 4898.9282 | 84 | 0.37348 | 0.37348 | 77 |  | 3623
6191 | COARSEGOLD 2104570682 | 254432104 | COARSEGOLD 2104 | 570682 | FALSE | 3264.3372 | 3264.3372 | 2.0288 | 26 | 9.6836e-05 | 1718 | 4471.4183 | 111 | 0.37306 | 9.6995 | 78 | 5.65 | 481
8841 | NORTH DUBLIN 210311101 | 14052103 | NORTH DUBLIN 2103 | 11101 | FALSE | 5931.2678 | 5931.2678 | 3.6863 | 37 | 6.6475e-05 | 2575 | 6042.3197 | 28 | 0.36793 | 13.6135 | 79 | 5.36 | 488
7776 | NORTH DUBLIN 21039473 | 14052103 | NORTH DUBLIN 2103 | 9473 | FALSE | 4735.3386 | 3890.479 | 2.4179 | 27 | 9.0946e-05 | 1883 | 3855.297 | 162 | 0.36547 | 9.8678 | 80 | 1.5 | 669
9266 | WILLOW PASS 2107445650 | 13912107 | WILLOW PASS 2107 | 445650 | FALSE | 1066.4109 | 1066.4109 | 0.66278 | 5 | 6.0341e-05 | 2764 | 6011.651 | 29 | 0.36477 | 1.8239 | 81 |  | 3333
2272 | MIDDLETOWN 1102414 | 43141102 | MIDDLETOWN 1102 | 414 | FALSE | 18899.455 | 9544.4247 | 5.9319 | 114 | 0.00014586 | 791 | 3081.157 | 259 | 0.36434 | 41.5353 | 82 | 1.22 | 699
3625 | CAYETANO 2109884904 | 14422109 | CAYETANO 2109 | 884904 | FALSE | 18739.6016 | 18723.6816 | 11.6368 | 77 | 0.0001019 | 1605 | 3934.604 | 152 | 0.36326 | 27.9711 | 83 |  | 2842
10903 | PEABODY 2106592742 | 63642106 | PEABODY 2106 | 592742 | TRUE | 684.4552 | 546.7453 | 0.3398 | 5 | 6.9919e-05 | 2474 | 5228.5371 | 60 | 0.36227 | 1.8113 | 84 |  | 3618
5260 | VOLTA 11011568 | 102541101 | VOLTA 1101 | 1568 | FALSE | 37176.4968 | 37176.4968 | 23.1053 | 136 | 9.0935e-05 | 1885 | 3456.9848 | 206 | 0.36191 | 49.2203 | 85 | 0.1 | 1479
4693 | MIDDLETOWN 1101CB | 43141101 | MIDDLETOWN 1101 | CB | FALSE | 22365.4615 | 7612.1604 | 4.731 | 146 | 0.00014565 | 795 | 2568.6158 | 335 | 0.36174 | 52.8144 | 86 | 14.97 | 351
10547 | PASO ROBLES 1103N02 | 182611103 | PASO ROBLES 1103 | N02 | TRUE | 70.934 | 70.934 | 0.044086 | 1 | 0.00025248 | 210 | 1429.5746 | 625 | 0.36094 | 0.36094 | 87 | 2.56 | 597
2088 | COARSEGOLD 21035020 | 254432103 | COARSEGOLD 2103 | 5020 | FALSE | 26887.6514 | 26064.8634 | 16.1994 | 159 | 8.5726e-05 | 2036 | 4882.5801 | 85 | 0.36009 | 57.2543 | 88 | 0.1 | 1468
7913 | JESSUP 11023105 | 103441102 | JESSUP 1102 | 3105 | FALSE | 9965.2703 | 9659.0441 | 6.0031 | 65 | 6.4265e-05 | 2635 | 5852.1243 | 38 | 0.35978 | 23.3856 | 89 | 2.42 | 605
10257 | CAYETANO 2111389190 | 14422111 | CAYETANO 2111 | 389190 | FALSE | 4452.7835 | 3542.8058 | 2.2019 | 18 | 0.00010318 | 1566 | 3658.7668 | 184 | 0.35946 | 6.4703 | 90 |  | 3524
10351 | VACAVILLE 1109799940 | 63601109 | VACAVILLE 1109 | 799940 | TRUE | 1340.3375 | 954.7701 | 0.59339 | 9 | 9.2053e-05 | 1842 | 3744.3748 | 176 | 0.35844 | 3.2259 | 91 |  | 3537
745 | PUTAH CREEK 110267858 | 63681102 | PUTAH CREEK 1102 | 67858 | FALSE | 18377.3415 | 18377.3415 | 11.4216 | 107 | 6.8002e-05 | 2535 | 5416.4769 | 50 | 0.35702 | 38.201 | 92 | 2.79 | 581
10611 | PEABODY 2113945670 | 63642113 | PEABODY 2113 | 945670 | TRUE | 403.0974 | 334.4297 | 0.20785 | 3 | 6.3935e-05 | 2648 | 5860.0064 | 36 | 0.35536 | 1.0661 | 93 |  | 3578
835 | ZACA 1102Y54 | 182681102 | ZACA 1102 | Y54 | FALSE | 55238.5351 | 54847.9366 | 34.0882 | 296 | 8.0013e-05 | 2204 | 4332.6246 | 120 | 0.35181 | 104.1359 | 94 | 0.39 | 950
9806 | OLETA 1101CB | 163541101 | OLETA 1101 | CB | TRUE | 169.7516 | 136.2242 | 0.084664 | 2 | 0.00017127 | 555 | 1962.7321 | 461 | 0.35138 | 0.70277 | 95 | 2.89 | 573
7864 | SISQUOC 1103867486 | 182811103 | SISQUOC 1103 | 867486 | FALSE | 5219.4397 | 3405.4305 | 2.1165 | 20 | 7.3948e-05 | 2361 | 3380.0089 | 213 | 0.35061 | 7.0121 | 96 |  | 3172
10173 | CALPINE 1146400 | 48011146 | CALPINE 1146 | 400 | FALSE | 5057.3021 | 5057.3021 | 3.1431 | 8 | 9.5474e-05 | 1743 | 3849.0683 | 163 | 0.34896 | 2.7917 | 97 | 0.31 | 1006
615 | KERCKHOFF 1101CB | 252561101 | KERCKHOFF 1101 | CB | FALSE | 27398.7529 | 27398.7529 | 17.0284 | 154 | 6.9314e-05 | 2496 | 5271.5559 | 56 | 0.348 | 53.5915 | 98 | 0.07 | 1725
1695 | DESCHUTES 110449024 | 103351104 | DESCHUTES 1104 | 49024 | FALSE | 26972.4504 | 26707.9675 | 16.5991 | 209 | 8.4768e-05 | 2071 | 4699.5815 | 98 | 0.34786 | 72.7038 | 99 | 9.03 | 415
3728 | DESCHUTES 11041370 | 103351104 | DESCHUTES 1104 | 1370 | FALSE | 35764.2 | 21861.3958 | 13.5869 | 272 | 0.00010359 | 1559 | 3756.8301 | 175 | 0.34561 | 94.0068 | 100 | 0.05 | 1954
10316 | CORNING 110135974 | 103331101 | CORNING 1101 | 35974 | TRUE | 1338.7863 | 398.8739 | 0.2479 | 11 | 7.6845e-05 | 2289 | 4333.8495 | 119 | 0.34404 | 3.7844 | 101 | 0.03 | 2393
10256 | VACAVILLE 1104874798 | 63601104 | VACAVILLE 1104 | 874798 | TRUE | 662.24 | 662.24 | 0.41158 | 3 | 6.6045e-05 | 2587 | 6079.8606 | 27 | 0.33623 | 1.0087 | 102 |  | 3523
6277 | WILLITS 1103964 | 42661103 | WILLITS 1103 | 964 | FALSE | 8651.6925 | 4999.6692 | 3.1073 | 41 | 0.00013223 | 977 | 2706.926 | 309 | 0.33456 | 13.717 | 103 | 0.45 | 917
6777 | BELL 11085703 | 152701108 | BELL 1108 | 5703 | FALSE | 12751.5705 | 8525.0586 | 5.2984 | 96 | 0.00012007 | 1186 | 2775.9092 | 303 | 0.33328 | 31.9947 | 104 | 0.07 | 1684
10040 | PANORAMA 11021632 | 103461102 | PANORAMA 1102 | 1632 | FALSE | 13751.6318 | 13751.6318 | 8.5467 | 19 | 8.8891e-05 | 1954 | 4338.5101 | 118 | 0.33244 | 6.3164 | 105 | 0.05 | 1948
9960 | WILLITS 1103CB | 42661103 | WILLITS 1103 | CB | FALSE | 6348.7863 | 4804 | 2.9857 | 44 | 0.00014557 | 797 | 1870.2515 | 482 | 0.32751 | 14.4105 | 106 | 0.03 | 2238
6501 | SAN MIGUEL 1104895760 | 182661104 | SAN MIGUEL 1104 | 895760 | FALSE | 19502.5171 | 14756.3663 | 9.1711 | 96 | 9.5565e-05 | 1740 | 3633.0115 | 188 | 0.32643 | 31.3373 | 107 |  | 3035
4461 | SANTA YNEZ 1104Y04 | 182721104 | SANTA YNEZ 1104 | Y04 | FALSE | 35997.3396 | 25194.6309 | 15.6586 | 238 | 6.6358e-05 | 2580 | 5141.1422 | 64 | 0.32463 | 77.261 | 108 | 2.84 | 576
10609 | PEABODY 2106CB | 63642106 | PEABODY 2106 | CB | TRUE | 1275.2265 | 525.8096 | 0.32679 | 9 | 0.00013923 | 884 | 1814.5621 | 503 | 0.32442 | 2.9197 | 109 | 0.04 | 2217
3147 | HOPLAND 1101768 | 42251101 | HOPLAND 1101 | 768 | FALSE | 31882.0115 | 27234.0747 | 16.9261 | 115 | 9.5052e-05 | 1764 | 3417.6208 | 210 | 0.32431 | 37.2953 | 110 | 0.05 | 2000
6991 | COVELO 1101478952 | 43061101 | COVELO 1101 | 478952 | FALSE | 5727.3171 | 1143.6662 | 0.71079 | 39 | 0.00011288 | 1347 | 2674.3103 | 318 | 0.32368 | 12.6234 | 111 |  | 3082
9010 | STAFFORD 11021202 | 43201102 | STAFFORD 1102 | 1202 | FALSE | 12713.8882 | 12713.8882 | 7.9017 | 41 | 0.00015857 | 657 | 2432.9018 | 355 | 0.32328 | 13.2544 | 112 | 2.4 | 607
5081 | RED BLUFF 11041566 | 103541104 | RED BLUFF 1104 | 1566 | FALSE | 24740.5736 | 19451.0946 | 12.0889 | 94 | 8.022e-05 | 2199 | 4262.1109 | 129 | 0.3225 | 30.3149 | 113 | 0.05 | 2042
9508 | ANDERSON 1101426745 | 103261101 | ANDERSON 1101 | 426745 | TRUE | 328.8561 | 328.8561 | 0.20439 | 3 | 0.00020048 | 394 | 1570.5843 | 571 | 0.32224 | 0.96673 | 114 |  | 3365
10637 | SYCAMORE CREEK 1111153260 | 102971111 | SYCAMORE CREEK 1111 | 153260 | TRUE | 424.4592 | 424.4592 | 0.2638 | 2 | 9.6022e-05 | 1729 | 3917.3903 | 154 | 0.32186 | 0.64373 | 115 |  | 3584
3800 | DESCHUTES 11049726 | 103351104 | DESCHUTES 1104 | 9726 | FALSE | 27359.7494 | 25257.4681 | 15.6976 | 197 | 8.9511e-05 | 1931 | 4058.7556 | 145 | 0.32131 | 63.2977 | 116 | 3.58 | 541
4142 | GIRVAN 1101323094 | 103401101 | GIRVAN 1101 | 323094 | FALSE | 58176.4815 | 58176.4815 | 36.1569 | 208 | 0.00010508 | 1524 | 3224.7709 | 234 | 0.32037 | 66.6373 | 117 | 0.08 | 1636
4869 | BELL 11082202 | 152701108 | BELL 1108 | 2202 | FALSE | 53635.0932 | 52339.4363 | 32.5292 | 363 | 0.0001269 | 1065 | 2599.5441 | 330 | 0.32016 | 116.2183 | 118 | 0.16 | 1264
9492 | OLETA 1101296804 | 163541101 | OLETA 1101 | 296804 | FALSE | 5287.5044 | 5287.5044 | 3.2862 | 12 | 0.00014395 | 815 | 2252.1128 | 392 | 0.31954 | 3.8345 | 119 |  | 3361
10541 | CLARKSVILLE 2105CB | 153612105 | CLARKSVILLE 2105 | CB | FALSE | 1481.3738 | 1293.943 | 0.80419 | 9 | 0.00018563 | 469 | 1193.2799 | 733 | 0.31824 | 2.8642 | 120 | 0.39 | 953
5372 | TEMPLETON 2113A20 | 183052113 | TEMPLETON 2113 | A20 | FALSE | 12666.4228 | 11999.0835 | 7.4575 | 92 | 8.3458e-05 | 2117 | 4208.4041 | 137 | 0.3179 | 29.2466 | 121 | 0.09 | 1561
8293 | VACAVILLE 110838316 | 63601108 | VACAVILLE 1108 | 38316 | FALSE | 36512.8123 | 25616.7426 | 15.9209 | 232 | 7.2587e-05 | 2403 | 4684.5531 | 99 | 0.31672 | 73.4796 | 122 | 3 | 569
907 | COTTONWOOD 1102544790 | 102931102 | COTTONWOOD 1102 | 544790 | FALSE | 27462.4335 | 26342.4042 | 16.3719 | 185 | 8.3921e-05 | 2097 | 3941.9662 | 151 | 0.31273 | 57.8548 | 123 |  | 2696
6176 | COARSEGOLD 21045525 | 254432104 | COARSEGOLD 2104 | 5525 | FALSE | 21152.7165 | 21152.7165 | 13.1465 | 175 | 5.9719e-05 | 2783 | 5306.8404 | 53 | 0.31171 | 54.5497 | 124 | 0.17 | 1227
3989 | MIDDLETOWN 1102878 | 43141102 | MIDDLETOWN 1102 | 878 | FALSE | 9206.6572 | 5430.6654 | 3.3752 | 49 | 0.00017681 | 519 | 2682.7456 | 315 | 0.31109 | 15.2435 | 125 | 0.63 | 834
2201 | RACETRACK 1704CB | 163761704 | RACETRACK 1704 | CB | FALSE | 36834.5436 | 36834.5436 | 22.8928 | 193 | 0.00011343 | 1334 | 2972.4937 | 272 | 0.31093 | 60.0095 | 126 | 10.25 | 399
4707 | HIGHLANDS 1103828 | 43361103 | HIGHLANDS 1103 | 828 | FALSE | 17153.3338 | 13828.9706 | 8.5948 | 112 | 8.3934e-05 | 2094 | 3831.1552 | 164 | 0.31086 | 34.8164 | 127 | 5.94 | 476
8759 | KERCKHOFF 1101R308 | 252561101 | KERCKHOFF 1101 | R308 | FALSE | 6217.3701 | 6217.3701 | 3.8641 | 22 | 6.1262e-05 | 2743 | 4314.2777 | 123 | 0.30901 | 6.7983 | 128 | 0.04 | 2136
7918 | FORESTHILL 1102CB | 152181102 | FORESTHILL 1102 | CB | FALSE | 2646.4634 | 2646.4634 | 1.6448 | 13 | 0.00028983 | 139 | 1109.8091 | 772 | 0.30873 | 4.0135 | 129 | 5.34 | 489
9076 | SYCAMORE CREEK 1111976428 | 102971111 | SYCAMORE CREEK 1111 | 976428 | FALSE | 16955.2499 | 14081.5812 | 8.7518 | 82 | 0.00013702 | 908 | 2148.1965 | 412 | 0.30752 | 25.2165 | 130 |  | 3305
6711 | PUTAH CREEK 110396792 | 63681103 | PUTAH CREEK 1103 | 96792 | FALSE | 8212.3137 | 6394.0351 | 3.9739 | 30 | 7.1793e-05 | 2425 | 5020.5256 | 72 | 0.30689 | 9.2067 | 131 |  | 3057
9779 | COARSEGOLD 21046210 | 254432104 | COARSEGOLD 2104 | 6210 | FALSE | 17177.2503 | 17177.2503 | 10.6757 | 49 | 4.8609e-05 | 3072 | 5877.8631 | 34 | 0.30465 | 14.9278 | 132 | 0.06 | 1874
7407 | TEMPLETON 2113A12 | 183052113 | TEMPLETON 2113 | A12 | FALSE | 64854.5144 | 64854.5144 | 40.3073 | 180 | 9.1245e-05 | 1867 | 3289.4433 | 226 | 0.30414 | 54.7453 | 133 | 0.11 | 1446
6929 | CLARKSVILLE 2104CB | 153612104 | CLARKSVILLE 2104 | CB | FALSE | 16489.2317 | 14163.76 | 8.8028 | 107 | 0.00015725 | 671 | 2292.759 | 385 | 0.30391 | 32.5187 | 134 | 6.82 | 459
8076 | NORTH DUBLIN 2103CB | 14052103 | NORTH DUBLIN 2103 | CB | FALSE | 24190.4571 | 22339.3117 | 13.884 | 147 | 0.00012222 | 1145 | 2373.5412 | 366 | 0.30349 | 44.6134 | 135 | 0.16 | 1273
9798 | BALCH NO 1 1101CB | 252501101 | BALCH NO 1 1101 | CB | FALSE | 16978.5039 | 16978.5039 | 10.5522 | 33 | 8.5557e-05 | 2039 | 4275.4303 | 128 | 0.30244 | 9.9805 | 136 | 0.03 | 2265
8821 | SANTA YNEZ 1104CB | 182721104 | SANTA YNEZ 1104 | CB | TRUE | 12832.3568 | 56.5182 | 0.035126 | 105 | 9.1038e-05 | 1880 | 3530.2398 | 198 | 0.30185 | 31.6947 | 137 | 0.03 | 2249
12 | PASO ROBLES 1103N50 | 182611103 | PASO ROBLES 1103 | N50 | FALSE | 3586.1974 | 3586.1974 | 2.2288 | 24 | 0.00020174 | 390 | 1403.0605 | 636 | 0.30039 | 7.2094 | 138 | 6.6 | 465
461 | KONOCTI 1102354890 | 43311102 | KONOCTI 1102 | 354890 | FALSE | 19596.9379 | 15016.4864 | 9.3328 | 131 | 0.00011262 | 1350 | 1727.5671 | 518 | 0.29712 | 38.9233 | 139 |  | 2675
4081 | OREGON TRAIL 11021382 | 103521102 | OREGON TRAIL 1102 | 1382 | FALSE | 8797.2782 | 8797.2782 | 5.4675 | 67 | 0.00010202 | 1603 | 2904.98 | 289 | 0.29503 | 19.7671 | 140 | 0.07 | 1732
207 | AUBERRY 1102CB | 254151102 | AUBERRY 1102 | CB | FALSE | 55860.8325 | 55860.8325 | 34.7177 | 368 | 5.1188e-05 | 3010 | 6445.9013 | 19 | 0.29173 | 107.3565 | 141 | 0.21 | 1150
929 | CORRAL 1101CB | 162991101 | CORRAL 1101 | CB | FALSE | 44193.7001 | 42311.3503 | 26.2967 | 280 | 7.4699e-05 | 2339 | 3983.5914 | 150 | 0.29054 | 81.3506 | 142 | 18.05 | 326
3287 | ANDERSON 11031600 | 103261103 | ANDERSON 1103 | 1600 | FALSE | 17254.9785 | 7231.4682 | 4.4944 | 106 | 9.3311e-05 | 1813 | 3227.6771 | 231 | 0.2889 | 30.6232 | 143 | 0.04 | 2087
1107 | COARSEGOLD 210410030 | 254432104 | COARSEGOLD 2104 | 10030 | FALSE | 59186.5885 | 54599.1868 | 33.9336 | 227 | 5.1982e-05 | 2993 | 5711.1735 | 43 | 0.28655 | 65.0478 | 144 | 0.04 | 2223
9519 | ARBUCKLE 1104669720 | 62081104 | ARBUCKLE 1104 | 669720 | FALSE | 7831.1318 | 3612.2461 | 2.245 | 22 | 8.813e-05 | 1979 | 4178.9611 | 140 | 0.28655 | 6.3042 | 145 |  | 3370
3809 | WISE 11022230 | 152271102 | WISE 1102 | 2230 | FALSE | 40267.1112 | 38210.8819 | 23.7482 | 278 | 9.8822e-05 | 1674 | 3101.6196 | 254 | 0.28438 | 79.0585 | 146 | 8.79 | 420
2464 | SHEPHERD 2111327814 | 252062111 | SHEPHERD 2111 | 327814 | FALSE | 23697.2526 | 18621.0587 | 11.5731 | 119 | 5.813e-05 | 2832 | 5439.3493 | 48 | 0.28428 | 33.8288 | 147 |  | 2778
3815 | PANORAMA 1102280170 | 103461102 | PANORAMA 1102 | 280170 | FALSE | 24945.6136 | 20943.3132 | 13.0164 | 102 | 0.00011005 | 1411 | 2725.4901 | 307 | 0.28426 | 28.9943 | 148 |  | 2855
10166 | TEMPLETON 21132949 | 183052113 | TEMPLETON 2113 | 2949 | TRUE | 766.5719 | 766.5719 | 0.47643 | 6 | 4.9947e-05 | 3039 | 6323.2739 | 22 | 0.28416 | 1.7049 | 149 | 2.67 | 590
6611 | DESCHUTES 1101CB | 103351101 | DESCHUTES 1101 | CB | FALSE | 17940.9873 | 8017.5323 | 4.9829 | 118 | 0.00011905 | 1205 | 2481.2226 | 344 | 0.28403 | 33.5157 | 150 | 0.04 | 2142
195 | COARSEGOLD 21045300 | 254432104 | COARSEGOLD 2104 | 5300 | FALSE | 89782.9365 | 89782.9365 | 55.8005 | 507 | 6.1292e-05 | 2742 | 5197.3797 | 62 | 0.28372 | 143.8456 | 151 | 0.2 | 1159
5871 | FLINT 1101750 | 152531101 | FLINT 1101 | 750 | FALSE | 14900.5272 | 7342.9025 | 4.5636 | 93 | 0.00015288 | 720 | 2183.6202 | 404 | 0.28318 | 26.3354 | 152 | 3.16 | 559
952 | SANTA YNEZ 1104Y66 | 182721104 | SANTA YNEZ 1104 | Y66 | FALSE | 29410.1773 | 27268.3855 | 16.9474 | 138 | 5.9163e-05 | 2801 | 4926.5491 | 81 | 0.28279 | 39.0253 | 153 | 8.36 | 431
1401 | SAN JOAQUIN #2 110310320 | 252521103 | SAN JOAQUIN #2 1103 | 10320 | FALSE | 18962.0898 | 18962.0898 | 11.785 | 133 | 7.3548e-05 | 2380 | 3652.1529 | 186 | 0.28179 | 37.4782 | 154 | 0.06 | 1810
10123 | FULTON 110258990 | 42561102 | FULTON 1102 | 58990 | TRUE | 971.5045 | 427.9744 | 0.26599 | 6 | 0.00011359 | 1330 | 3017.9754 | 266 | 0.28025 | 1.6815 | 155 |  | 3495
3591 | SANTA YNEZ 1101277014 | 182721101 | SANTA YNEZ 1101 | 277014 | FALSE | 26491.1541 | 8850.8283 | 5.5008 | 149 | 7.4914e-05 | 2333 | 3435.5989 | 208 | 0.28002 | 41.7232 | 156 |  | 2840
2737 | VOLTA 110153118 | 102541101 | VOLTA 1101 | 53118 | FALSE | 15490.2629 | 15490.2629 | 9.6273 | 47 | 5.9428e-05 | 2792 | 5134.3568 | 65 | 0.27952 | 13.1375 | 157 | 0.08 | 1618
9393 | PUTAH CREEK 1103654021 | 63681103 | PUTAH CREEK 1103 | 654021 | TRUE | 1396.0557 | 329.1954 | 0.2046 | 12 | 6.2033e-05 | 2719 | 5297.9521 | 54 | 0.27878 | 3.3454 | 158 |  | 3351
5717 | SHINGLE SPRINGS 210935598 | 153652109 | SHINGLE SPRINGS 2109 | 35598 | FALSE | 17452.8092 | 17452.8092 | 10.847 | 122 | 0.00012105 | 1163 | 2054.3578 | 443 | 0.27855 | 33.9836 | 159 | 2.42 | 604
1630 | OREGON TRAIL 11041574 | 103521104 | OREGON TRAIL 1104 | 1574 | FALSE | 30217.612 | 27209.5234 | 16.9108 | 221 | 9.7752e-05 | 1698 | 3321.0394 | 222 | 0.27852 | 61.5533 | 160 | 0.1 | 1499
2168 | HOPLAND 11014626 | 42251101 | HOPLAND 1101 | 4626 | FALSE | 50138.0738 | 43527.4256 | 27.0525 | 238 | 9.7355e-05 | 1704 | 2906.275 | 288 | 0.27841 | 66.2609 | 161 | 0.08 | 1626
10275 | SAN MIGUEL 1105873457 | 182661105 | SAN MIGUEL 1105 | 873457 | FALSE | 3228.1461 | 2440.6531 | 1.5169 | 18 | 6.4601e-05 | 2620 | 3816.6955 | 166 | 0.27723 | 4.9901 | 162 |  | 3525
5141 | AUBERRY 1101R2578 | 254151101 | AUBERRY 1101 | R2578 | FALSE | 74560.0099 | 74560.0099 | 46.3393 | 506 | 5.751e-05 | 2848 | 5003.4373 | 77 | 0.27714 | 140.2335 | 163 | 0.12 | 1377
710 | COARSEGOLD 2103CB | 254432103 | COARSEGOLD 2103 | CB | FALSE | 61825.449 | 61825.449 | 38.4248 | 420 | 0.00010575 | 1502 | 2969.029 | 273 | 0.27679 | 116.2539 | 164 | 0.1 | 1498
9397 | BEAR VALLEY 21059570 | 252192105 | BEAR VALLEY 2105 | 9570 | FALSE | 12951.7997 | 12951.7997 | 8.0496 | 59 | 6.9285e-05 | 2498 | 4812.6159 | 92 | 0.27669 | 16.3249 | 165 | 0.03 | 2273
4772 | COARSEGOLD 2102CB | 254432102 | COARSEGOLD 2102 | CB | FALSE | 22596.9807 | 22596.9807 | 14.0441 | 79 | 8.9146e-05 | 1941 | 3040.7048 | 264 | 0.2766 | 21.851 | 166 | 0.05 | 2045
11028 | NARROWS PH 1151CB | 153131151 | NARROWS PH 1151 | CB | TRUE | 286.9891 | 286.9891 | 0.17836 | 2 | 0.00034143 | 96 | 952.1877 | 859 | 0.27613 | 0.55227 | 167 |  | 3629
5439 | KONOCTI 110264664 | 43311102 | KONOCTI 1102 | 64664 | FALSE | 46084.8025 | 44670.3665 | 27.7628 | 263 | 0.00011497 | 1301 | 2595.543 | 331 | 0.27567 | 72.501 | 168 | 7.76 | 441
307 | MOUNTAIN QUARRIES 21011350 | 152282101 | MOUNTAIN QUARRIES 2101 | 1350 | FALSE | 34999.9271 | 34999.9271 | 21.7526 | 212 | 0.00015371 | 714 | 2128.0484 | 418 | 0.27537 | 58.3793 | 169 | 0.14 | 1328
8396 | NORTH DUBLIN 2101MR765 | 14052101 | NORTH DUBLIN 2101 | MR765 | FALSE | 3411.7079 | 3330.9197 | 2.0702 | 15 | 0.00016258 | 618 | 1924.3853 | 466 | 0.2736 | 4.104 | 170 |  | 3219
6379 | PUTAH CREEK 11028352 | 63681102 | PUTAH CREEK 1102 | 8352 | FALSE | 19103.6731 | 10298.4219 | 6.4005 | 133 | 7.7051e-05 | 2286 | 3533.4319 | 197 | 0.27308 | 36.3202 | 171 | 0.04 | 2110
7979 | KONOCTI 1102716 | 43311102 | KONOCTI 1102 | 716 | FALSE | 27459.7262 | 24685.2253 | 15.342 | 109 | 0.00010173 | 1611 | 2445.3377 | 351 | 0.27295 | 29.7514 | 172 | 0.09 | 1540
1249 | PENRYN 11032198 | 152561103 | PENRYN 1103 | 2198 | FALSE | 33673.9837 | 32552.0609 | 20.2312 | 248 | 0.00015745 | 669 | 1901.3176 | 477 | 0.27291 | 67.6807 | 173 | 5.01 | 498
10021 | OLETA 1101400470 | 163541101 | OLETA 1101 | 400470 | TRUE | 475.2183 | 334.0108 | 0.20759 | 3 | 0.0001432 | 822 | 1757.1387 | 513 | 0.27287 | 0.81862 | 174 |  | 3474
3674 | AUBERRY 1102R309 | 254151102 | AUBERRY 1102 | R309 | FALSE | 13825.8859 | 13825.8859 | 8.5928 | 92 | 4.4689e-05 | 3170 | 5876.5086 | 35 | 0.27286 | 25.1032 | 175 | 0.07 | 1734
1420 | MIDDLETOWN 1102998 | 43141102 | MIDDLETOWN 1102 | 998 | FALSE | 27408.0031 | 23900.855 | 14.8545 | 205 | 0.00011619 | 1266 | 2601.6522 | 329 | 0.27124 | 55.6044 | 176 | 9.39 | 410
6398 | CAYETANO 2109MR572 | 14422109 | CAYETANO 2109 | MR572 | FALSE | 19863.5833 | 13342.8208 | 8.2926 | 80 | 8.353e-05 | 2113 | 3855.5003 | 161 | 0.27121 | 21.6967 | 177 | 0.06 | 1900
6361 | APPLE HILL 21026552 | 153662102 | APPLE HILL 2102 | 6552 | FALSE | 20088.9562 | 20088.9562 | 12.4854 | 139 | 0.00023194 | 279 | 1458.479 | 613 | 0.2712 | 37.6964 | 178 | 0.07 | 1674
5677 | BANGOR 110180670 | 103191101 | BANGOR 1101 | 80670 | FALSE | 26435.3887 | 23201.6685 | 14.4199 | 158 | 9.3264e-05 | 1814 | 3120.2999 | 252 | 0.27059 | 42.753 | 179 | 0.07 | 1687
7666 | JAMESON 1103118944 | 63801103 | JAMESON 1103 | 118944 | FALSE | 8499.846 | 3772.9974 | 2.3449 | 41 | 7.2601e-05 | 2402 | 3739.9482 | 177 | 0.27039 | 11.0862 | 180 |  | 3148
5313 | HIGHLANDS 1103482 | 43361103 | HIGHLANDS 1103 | 482 | FALSE | 41604.9679 | 39433.4736 | 24.5081 | 188 | 8.3389e-05 | 2120 | 3402.5308 | 212 | 0.26975 | 50.7128 | 181 | 0.11 | 1426
5299 | HIGGINS 1109CB | 152691109 | HIGGINS 1109 | CB | FALSE | 37179.8547 | 36440.0989 | 22.6477 | 254 | 0.00012368 | 1127 | 2336.1435 | 377 | 0.26784 | 68.0313 | 182 | 0.11 | 1411
7848 | OAKHURST 1101636114 | 254421101 | OAKHURST 1101 | 636114 | FALSE | 32974.1643 | 32974.1643 | 20.4936 | 153 | 5.0431e-05 | 3029 | 5596.4616 | 45 | 0.26702 | 40.8546 | 183 |  | 3171
10324 | SANTA YNEZ 1104564710 | 182721104 | SANTA YNEZ 1104 | 564710 | TRUE | 541.7371 | 273.7323 | 0.17013 | 7 | 4.7515e-05 | 3102 | 4812.031 | 93 | 0.26624 | 1.8637 | 184 |  | 3533
10018 | LINCOLN 1104275986 | 153701104 | LINCOLN 1104 | 275986 | TRUE | 934.5883 | 934.5883 | 0.58085 | 5 | 8.2974e-05 | 2131 | 2938.8625 | 283 | 0.26526 | 1.3263 | 185 |  | 3473
5709 | HIGGINS 110950072 | 152691109 | HIGGINS 1109 | 50072 | FALSE | 68212.3656 | 68212.3656 | 42.3943 | 424 | 8.3823e-05 | 2099 | 2904.6654 | 290 | 0.26524 | 112.4633 | 186 | 0.17 | 1228
3710 | MARIPOSA 210110070 | 254452101 | MARIPOSA 2101 | 10070 | FALSE | 42054.457 | 42054.457 | 26.137 | 249 | 5.9269e-05 | 2796 | 3802.6518 | 169 | 0.2644 | 65.835 | 187 | 0.16 | 1265
3891 | MARIPOSA 210210880 | 254452102 | MARIPOSA 2102 | 10880 | FALSE | 64212.5757 | 63861.6467 | 39.6903 | 362 | 5.4719e-05 | 2925 | 5019.3026 | 74 | 0.2637 | 95.458 | 188 | 0.25 | 1077
1822 | BELL 110750172 | 152701107 | BELL 1107 | 50172 | FALSE | 30233.9103 | 28142.3136 | 17.4906 | 210 | 8.9513e-05 | 1930 | 3226.5987 | 232 | 0.2635 | 55.3341 | 189 | 3.07 | 565
7084 | VACAVILLE 111113652 | 63601111 | VACAVILLE 1111 | 13652 | FALSE | 6914.8485 | 6914.8485 | 4.2976 | 58 | 0.00011431 | 1311 | 2370.7576 | 367 | 0.26339 | 15.2768 | 190 | 4.89 | 502
3429 | CLOVERDALE 1101399855 | 42821101 | CLOVERDALE 1101 | 399855 | FALSE | 4438.9669 | 4409.9199 | 2.7408 | 19 | 0.00012846 | 1040 | 1799.172 | 506 | 0.26331 | 5.0028 | 191 |  | 2826
9762 | HARTLEY 11014710 | 43211101 | HARTLEY 1101 | 4710 | FALSE | 2414.0517 | 2414.0517 | 1.5003 | 18 | 7.3983e-05 | 2359 | 3402.6996 | 211 | 0.26308 | 4.7355 | 192 | 0.06 | 1858
2103 | DOBBINS 11011808 | 153741101 | DOBBINS 1101 | 1808 | FALSE | 25003.3757 | 25003.3757 | 15.5397 | 171 | 0.00012923 | 1021 | 2096.2914 | 428 | 0.26282 | 44.9426 | 193 | 0.09 | 1564
3817 | DESCHUTES 11011380 | 103351101 | DESCHUTES 1101 | 1380 | FALSE | 37070.8959 | 28672.6173 | 17.8201 | 204 | 0.00010398 | 1553 | 2782.7866 | 301 | 0.26207 | 53.462 | 194 | 0.07 | 1696
1392 | SAND CREEK 110345190 | 254601103 | SAND CREEK 1103 | 45190 | FALSE | 60483.5997 | 60483.5997 | 37.5908 | 416 | 4.4054e-05 | 3190 | 5858.6509 | 37 | 0.26095 | 108.5552 | 195 | 0.15 | 1301
4741 | BRENTWOOD 2105B504R | 14592105 | BRENTWOOD 2105 | B504R | FALSE | 18129.2647 | 14074.6887 | 8.7475 | 97 | 9.8714e-05 | 1676 | 3474.2779 | 204 | 0.26071 | 25.289 | 196 | 0.1 | 1494
7636 | VACA DIXON 110118292 | 63591101 | VACA DIXON 1101 | 18292 | TRUE | 8145.543 | 73.0344 | 0.045391 | 73 | 0.00010766 | 1460 | 2089.0547 | 431 | 0.26015 | 18.9907 | 197 | 4.97 | 499
4859 | OREGON TRAIL 1102CB | 103521102 | OREGON TRAIL 1102 | CB | FALSE | 15377.0316 | 15053.0301 | 9.3555 | 98 | 0.00013609 | 918 | 2689.4423 | 314 | 0.25991 | 25.4708 | 198 | 1.45 | 674
1063 | MARIPOSA 210110990 | 254452101 | MARIPOSA 2101 | 10990 | FALSE | 64432.5092 | 64432.5092 | 40.0451 | 390 | 6.2843e-05 | 2688 | 4452.3041 | 112 | 0.25971 | 101.2865 | 199 | 0.23 | 1118
9382 | CORNING 110185162 | 103331101 | CORNING 1101 | 85162 | FALSE | 9267.4821 | 9267.4821 | 5.7598 | 28 | 4.8495e-05 | 3077 | 5246.1165 | 57 | 0.2589 | 7.2492 | 200 | 0.09 | 1512
1035 | CORRAL 110136652 | 162991101 | CORRAL 1101 | 36652 | FALSE | 58152.9177 | 58152.9177 | 36.1423 | 357 | 6.9107e-05 | 2503 | 3912.9423 | 155 | 0.25884 | 92.4048 | 201 | 2.74 | 586
4603 | UPPER LAKE 1101660 | 42871101 | UPPER LAKE 1101 | 660 | FALSE | 15616.9486 | 9914.559 | 6.1619 | 91 | 0.00011219 | 1361 | 2640.3198 | 322 | 0.25883 | 23.5531 | 202 | 0.02 | 2506
521 | WILLITS 1103696 | 42661103 | WILLITS 1103 | 696 | FALSE | 15381.4122 | 10464.5667 | 6.5038 | 87 | 0.00011584 | 1275 | 2155.4593 | 411 | 0.25793 | 22.4395 | 203 | 0.04 | 2141
134 | SAN JOAQUIN #2 1103CB | 252521103 | SAN JOAQUIN #2 1103 | CB | FALSE | 109280.4349 | 109280.4349 | 67.9182 | 589 | 7.6086e-05 | 2305 | 3828.8466 | 165 | 0.25597 | 150.7655 | 204 | 0.64 | 828
3686 | UKIAH 1111534 | 42771111 | UKIAH 1111 | 534 | FALSE | 33775.8497 | 30432.3399 | 18.9138 | 142 | 8.2307e-05 | 2145 | 3212.6445 | 237 | 0.25577 | 36.3189 | 205 | 0.12 | 1397
8712 | ELK CREEK 110193504 | 102781101 | ELK CREEK 1101 | 93504 | FALSE | 4036.8011 | 3461.2366 | 2.1512 | 15 | 6.0933e-05 | 2750 | 4082.5968 | 144 | 0.25426 | 3.8139 | 206 | 0.06 | 1896
10786 | PEABODY 2113873304 | 63642113 | PEABODY 2113 | 873304 | FALSE | 1312.9508 | 1312.9508 | 0.816 | 5 | 6.945e-05 | 2489 | 4833.6394 | 88 | 0.25419 | 1.2709 | 207 |  | 3605
9423 | CLAY 110359714 | 163341103 | CLAY 1103 | 59714 | FALSE | 7503.916 | 7503.916 | 4.6637 | 34 | 9.4275e-05 | 1786 | 2408.1592 | 360 | 0.25391 | 8.6328 | 208 | 0.04 | 2176
9267 | POTTER VALLEY P H 1105990354 | 42281105 | POTTER VALLEY P H 1105 | 990354 | TRUE | 170.3854 | 170.3854 | 0.1059 | 2 | 0.00030725 | 122 | 583.9962 | 1119 | 0.25341 | 0.50682 | 209 | 0.02 | 2532
4480 | LUCERNE 1106526 | 43351106 | LUCERNE 1106 | 526 | FALSE | 17461.3012 | 16256.6321 | 10.1036 | 100 | 0.00011252 | 1356 | 2700.181 | 312 | 0.25318 | 25.318 | 210 | 0.07 | 1679
3034 | HOPLAND 1101558 | 42251101 | HOPLAND 1101 | 558 | FALSE | 15006.3638 | 4818.3603 | 2.9946 | 72 | 0.00022789 | 291 | 857.3477 | 909 | 0.25266 | 18.1915 | 211 | 0.01 | 2601
4451 | HIGHLANDS 1103568 | 43361103 | HIGHLANDS 1103 | 568 | FALSE | 14789.9903 | 12940.6184 | 8.0426 | 118 | 0.00012911 | 1024 | 2034.9748 | 449 | 0.25222 | 29.7625 | 212 | 0.1 | 1493
5062 | AUBERRY 1102R902 | 254151102 | AUBERRY 1102 | R902 | FALSE | 24261.144 | 24261.144 | 15.0784 | 156 | 6.3332e-05 | 2666 | 4129.7341 | 141 | 0.25137 | 39.2136 | 213 | 0.07 | 1688
5371 | SUNOL 1101MR169 | 14241101 | SUNOL 1101 | MR169 | FALSE | 15006.414 | 4976.4795 | 3.0929 | 96 | 9.4566e-05 | 1776 | 2310.912 | 383 | 0.25044 | 24.0426 | 214 | 0.02 | 2435
8139 | LAS GALLINAS A 110599904 | 42991105 | LAS GALLINAS A 1105 | 99904 | FALSE | 8949.4853 | 8949.4853 | 5.5621 | 54 | 0.00018177 | 500 | 1184.3918 | 739 | 0.25006 | 13.5032 | 215 | 39.72 | 187
4462 | WILLITS 110337504 | 42661103 | WILLITS 1103 | 37504 | FALSE | 5704.6998 | 1890.9339 | 1.1752 | 41 | 0.00013442 | 938 | 1727.1376 | 519 | 0.24974 | 10.2392 | 216 | 0.02 | 2505
4593 | POSO MOUNTAIN 2101CB | 253642101 | POSO MOUNTAIN 2101 | CB | FALSE | 6924.1001 | 6924.1001 | 4.3034 | 22 | 5.902e-05 | 2806 | 4006.0392 | 149 | 0.24862 | 5.4697 | 217 | 0.07 | 1691
6909 | WYANDOTTE 1109702710 | 102911109 | WYANDOTTE 1109 | 702710 | FALSE | 7335.7671 | 4286.5556 | 2.6641 | 49 | 0.00021702 | 330 | 1323.547 | 672 | 0.24845 | 12.174 | 218 |  | 3072
9944 | WYANDOTTE 110366146 | 102911103 | WYANDOTTE 1103 | 66146 | TRUE | 252.3083 | 252.3083 | 0.15681 | 4 | 0.00010984 | 1414 | 2698.6732 | 313 | 0.24793 | 0.99171 | 219 | 0.12 | 1382
10031 | SOLEDAD 2102346006 | 182052102 | SOLEDAD 2102 | 346006 | FALSE | 3918.3073 | 3650.4625 | 2.2688 | 5 | 7.7555e-05 | 2277 | 3061.2643 | 262 | 0.24765 | 1.2382 | 220 |  | 3479
905 | CORNING 110290036 | 103331102 | CORNING 1102 | 90036 | FALSE | 23187.5221 | 21561.1762 | 13.4004 | 87 | 7.3822e-05 | 2364 | 4520.2585 | 105 | 0.24724 | 21.5103 | 221 | 0.1 | 1505
5847 | OAKHURST 11035732 | 254421103 | OAKHURST 1103 | 5732 | FALSE | 5445.3198 | 5445.3198 | 3.3843 | 37 | 5.3285e-05 | 2956 | 4484.9828 | 109 | 0.24719 | 9.1461 | 222 | 0.14 | 1324
5505 | MARIPOSA 210237282 | 254452102 | MARIPOSA 2102 | 37282 | FALSE | 96262.8931 | 86430.7687 | 53.7171 | 498 | 6.5439e-05 | 2602 | 4244.8756 | 134 | 0.24522 | 122.1205 | 223 | 0.36 | 969
4841 | OAKHURST 110363334 | 254421103 | OAKHURST 1103 | 63334 | FALSE | 27819.9713 | 27819.9713 | 17.2902 | 154 | 5.0298e-05 | 3032 | 5273.9392 | 55 | 0.24446 | 37.6467 | 224 | 10.23 | 400
8342 | BANGOR 110131502 | 103191101 | BANGOR 1101 | 31502 | FALSE | 19104.3686 | 19104.3686 | 11.8734 | 102 | 0.00014287 | 828 | 1982.4694 | 459 | 0.24429 | 24.9173 | 225 | 0.08 | 1616
9205 | POINT MORETTI 110135874 | 82931101 | POINT MORETTI 1101 | 35874 | TRUE | 329.4831 | 329.4831 | 0.20478 | 4 | 0.0002322 | 276 | 974.717 | 846 | 0.24298 | 0.97191 | 226 | 0.03 | 2258
2854 | SHINGLE SPRINGS 21099372 | 153652109 | SHINGLE SPRINGS 2109 | 9372 | FALSE | 28750.7098 | 28750.7098 | 17.8687 | 190 | 0.00012144 | 1159 | 1860.3939 | 487 | 0.24281 | 46.1342 | 227 | 6.15 | 472
10573 | GEYSERVILLE 1102756 | 42891102 | GEYSERVILLE 1102 | 756 | TRUE | 948.4078 | 948.4078 | 0.58944 | 7 | 0.00037409 | 76 | 1141.7089 | 757 | 0.24238 | 1.6966 | 228 | 0.02 | 2431
6313 | SAN MIGUEL 1104N60 | 182661104 | SAN MIGUEL 1104 | N60 | FALSE | 14171.0101 | 13316.658 | 8.2764 | 66 | 6.3749e-05 | 2655 | 3875.817 | 160 | 0.24236 | 15.9958 | 229 | 0.04 | 2143
2085 | LINCOLN 1104685276 | 153701104 | LINCOLN 1104 | 685276 | FALSE | 34821.9656 | 10432.3869 | 6.4838 | 216 | 7.8086e-05 | 2256 | 3212.4401 | 238 | 0.24208 | 52.2897 | 230 |  | 2761
7825 | HORSESHOE 1101416226 | 152571101 | HORSESHOE 1101 | 416226 | TRUE | 397.9238 | 186.6616 | 0.11601 | 5 | 8.4899e-05 | 2065 | 2680.4211 | 316 | 0.24182 | 1.2091 | 231 |  | 3167
9295 | BROWNS VALLEY 110117011 | 152921101 | BROWNS VALLEY 1101 | 17011 | FALSE | 3005.3172 | 3005.3172 | 1.8678 | 22 | 9.7443e-05 | 1702 | 2978.7374 | 270 | 0.24153 | 5.3136 | 232 | 0.07 | 1747
1428 | ZACA 1102Y02 | 182681102 | ZACA 1102 | Y02 | FALSE | 21138.3499 | 16812.4916 | 10.449 | 158 | 6.2768e-05 | 2691 | 3729.2174 | 180 | 0.24142 | 38.1442 | 233 | 0.07 | 1717
6825 | OLETA 1102186326 | 163541102 | OLETA 1102 | 186326 | FALSE | 20743.7329 | 19088.8539 | 11.8638 | 123 | 0.00011431 | 1312 | 2157.6907 | 410 | 0.24114 | 29.6596 | 234 |  | 3066
7670 | STANISLAUS 1702CB | 162821702 | STANISLAUS 1702 | CB | FALSE | 13066.3244 | 13066.3244 | 8.1208 | 67 | 0.00015785 | 665 | 1253.7272 | 700 | 0.24096 | 16.1444 | 235 | 0.13 | 1360
9773 | MADISON 2101117644 | 63172101 | MADISON 2101 | 117644 | FALSE | 3757.3782 | 1080.3525 | 0.67144 | 12 | 9.3021e-05 | 1820 | 2949.3645 | 280 | 0.23987 | 2.8784 | 236 |  | 3416
10170 | PUTAH CREEK 1105617260 | 63681105 | PUTAH CREEK 1105 | 617260 | FALSE | 4545.7003 | 1876.8402 | 1.1665 | 15 | 9.4125e-05 | 1791 | 3143.4533 | 249 | 0.2396 | 3.5941 | 237 |  | 3506
10828 | BUELLTON 110163389 | 183041101 | BUELLTON 1101 | 63389 | TRUE | 391.5938 | 0 | 0 | 2 | 0.00010287 | 1573 | 1639.5129 | 547 | 0.23935 | 0.47871 | 238 |  | 3610
8291 | CLEAR LAKE 1102904 | 42141102 | CLEAR LAKE 1102 | 904 | FALSE | 5777.0339 | 5445.6493 | 3.3845 | 30 | 9.2995e-05 | 1822 | 2564.652 | 336 | 0.23862 | 7.1587 | 239 | 1.48 | 670
6235 | SHINGLE SPRINGS 210519522 | 153652105 | SHINGLE SPRINGS 2105 | 19522 | FALSE | 16493.1882 | 15565.1755 | 9.6738 | 113 | 8.878e-05 | 1959 | 3187.9029 | 244 | 0.23827 | 26.9251 | 240 | 34.17 | 216
9843 | SUNOL 1101MR387 | 14241101 | SUNOL 1101 | MR387 | FALSE | 8072.5307 | 8065.9096 | 5.013 | 24 | 6.2945e-05 | 2681 | 3500.2914 | 201 | 0.23776 | 5.7062 | 241 | 0.06 | 1882
109 | WISE 11022054 | 152271102 | WISE 1102 | 2054 | FALSE | 20940.0353 | 20940.0353 | 13.0143 | 147 | 0.00010429 | 1544 | 2815.7078 | 298 | 0.23735 | 34.8898 | 242 | 3.46 | 547
9387 | ANTELOPE 1101318686 | 252021101 | ANTELOPE 1101 | 318686 | FALSE | 4853.6414 | 2345.6024 | 1.4578 | 7 | 6.5096e-05 | 2607 | 3652.241 | 185 | 0.23683 | 1.6578 | 243 |  | 3349
2465 | JESSUP 11021314 | 103441102 | JESSUP 1102 | 1314 | FALSE | 23311.1376 | 9677.7607 | 6.0148 | 161 | 8.2165e-05 | 2148 | 3017.906 | 267 | 0.23664 | 38.0983 | 244 | 1.18 | 703
4610 | KERCKHOFF 1101R353 | 252561101 | KERCKHOFF 1101 | R353 | FALSE | 22190.5443 | 22190.5443 | 13.7915 | 53 | 3.7075e-05 | 3313 | 6512.8186 | 18 | 0.23576 | 12.4952 | 245 | 0.07 | 1773
7566 | CORRAL 110112608 | 162991101 | CORRAL 1101 | 12608 | FALSE | 27131.1027 | 27131.1027 | 16.8621 | 187 | 6.2935e-05 | 2683 | 3772.462 | 174 | 0.23545 | 44.029 | 246 | 11.8 | 381
5704 | SHEPHERD 2111707358 | 252062111 | SHEPHERD 2111 | 707358 | FALSE | 37001.2559 | 30537.9753 | 18.9795 | 219 | 4.1347e-05 | 3238 | 5721.8442 | 41 | 0.23489 | 51.4409 | 247 |  | 2974
10861 | PEORIA 170492888 | 163781704 | PEORIA 1704 | 92888 | TRUE | 765.3621 | 400.6025 | 0.24898 | 4 | 0.00010691 | 1480 | 2347.6932 | 375 | 0.23471 | 0.93885 | 248 | 0.01 | 2581
5055 | FROGTOWN 17028482 | 163451702 | FROGTOWN 1702 | 8482 | FALSE | 23390.9929 | 23390.9929 | 14.5376 | 117 | 0.00010252 | 1587 | 2287.3259 | 386 | 0.23437 | 27.4214 | 249 | 0.05 | 2057
10192 | MADISON 2101725408 | 63172101 | MADISON 2101 | 725408 | FALSE | 2105.6406 | 1530.1897 | 0.95102 | 9 | 9.3021e-05 | 1821 | 2838.0743 | 294 | 0.23427 | 2.1085 | 250 |  | 3511
852 | PASO ROBLES 1104R56 | 182611104 | PASO ROBLES 1104 | R56 | FALSE | 19965.7505 | 18526.1855 | 11.5141 | 117 | 9.8997e-05 | 1669 | 2922.3966 | 284 | 0.2342 | 27.401 | 251 | 1.75 | 644
9420 | FRENCH GULCH 11011892 | 103381101 | FRENCH GULCH 1101 | 1892 | FALSE | 5154.3447 | 5154.3447 | 3.2034 | 12 | 0.00011418 | 1317 | 1393.5299 | 640 | 0.23339 | 2.8006 | 252 | 0.06 | 1887
2713 | ELK CREEK 110137334 | 102781101 | ELK CREEK 1101 | 37334 | FALSE | 15392.9848 | 15392.9848 | 9.5668 | 70 | 5.2877e-05 | 2973 | 4838.4242 | 87 | 0.23311 | 16.3175 | 253 | 0.07 | 1730
8722 | POSO MOUNTAIN 21033988 | 253642103 | POSO MOUNTAIN 2103 | 3988 | FALSE | 29512.4633 | 27217.7374 | 16.9159 | 68 | 4.0141e-05 | 3264 | 5944.554 | 32 | 0.23303 | 15.8463 | 254 | 0.1 | 1471
6130 | OREGON TRAIL 1104CB | 103521104 | OREGON TRAIL 1104 | CB | FALSE | 23543.7827 | 17030.244 | 10.5844 | 164 | 0.00014109 | 852 | 1638.3807 | 548 | 0.23182 | 38.0188 | 255 | 0.08 | 1577
6781 | PALMER 1101M84 | 183031101 | PALMER 1101 | M84 | FALSE | 39352.9214 | 37718.995 | 23.4425 | 145 | 7.1467e-05 | 2434 | 3431.3832 | 209 | 0.23169 | 33.5958 | 256 | 0.05 | 2018
7251 | PASO ROBLES 1103N58 | 182611103 | PASO ROBLES 1103 | N58 | FALSE | 11929.7838 | 7319.6094 | 4.5492 | 91 | 8.9683e-05 | 1923 | 2958.7213 | 277 | 0.23099 | 21.0205 | 257 | 1.43 | 676
9345 | CHOLAME 21025597 | 182562102 | CHOLAME 2102 | 5597 | FALSE | 8229.9238 | 8229.9238 | 5.1149 | 22 | 5.7292e-05 | 2855 | 4008.4187 | 148 | 0.23009 | 5.062 | 258 | 0.06 | 1847
6582 | UPPER LAKE 1101412 | 42871101 | UPPER LAKE 1101 | 412 | FALSE | 27547.3528 | 16599.9817 | 10.317 | 152 | 9.7196e-05 | 1709 | 2705.0187 | 311 | 0.23008 | 34.9724 | 259 | 0.04 | 2122
7180 | PASO ROBLES 11032731 | 182611103 | PASO ROBLES 1103 | 2731 | FALSE | 2630.6286 | 2630.6286 | 1.6349 | 13 | 8.1626e-05 | 2166 | 3132.5166 | 251 | 0.2296 | 2.9847 | 260 | 0.25 | 1088
6731 | DEL MAR 2109CB | 152582109 | DEL MAR 2109 | CB | FALSE | 9780.4489 | 2376.9126 | 1.4773 | 72 | 0.00018501 | 472 | 1136.289 | 760 | 0.22956 | 16.5281 | 261 | 0.02 | 2474
4193 | ANDERSON 1103226050 | 103261103 | ANDERSON 1103 | 226050 | FALSE | 24153.2004 | 7845.4549 | 4.876 | 160 | 0.00012494 | 1099 | 1958.1377 | 463 | 0.22913 | 36.6601 | 262 |  | 2875
2449 | COARSEGOLD 210410400 | 254432104 | COARSEGOLD 2104 | 10400 | FALSE | 72169.1615 | 68567.3531 | 42.6149 | 539 | 6.3171e-05 | 2673 | 4382.9111 | 117 | 0.22826 | 123.0305 | 263 | 0.67 | 815
6456 | HIGGINS 110950078 | 152691109 | HIGGINS 1109 | 50078 | FALSE | 77925.0015 | 77925.0015 | 48.4307 | 427 | 6.6516e-05 | 2573 | 3492.1838 | 203 | 0.22791 | 97.3194 | 264 | 0.18 | 1215
6171 | WYANDOTTE 110737472 | 102911107 | WYANDOTTE 1107 | 37472 | FALSE | 23988.0552 | 14935.9015 | 9.2827 | 157 | 0.00012968 | 1013 | 1878.4311 | 481 | 0.22739 | 35.7007 | 265 | 0.05 | 2001
1604 | COARSEGOLD 210310820 | 254432103 | COARSEGOLD 2103 | 10820 | FALSE | 46507.9226 | 46392.4448 | 28.8331 | 327 | 6.2605e-05 | 2698 | 4312.1018 | 124 | 0.2269 | 74.1966 | 266 | 0.19 | 1188
3581 | JESSUP 110296554 | 103441102 | JESSUP 1102 | 96554 | FALSE | 23931.0858 | 12987.3897 | 8.0717 | 172 | 7.0376e-05 | 2458 | 3307.1204 | 223 | 0.22645 | 38.9486 | 267 | 1.68 | 653
10176 | CLARK ROAD 1102CB | 103091102 | CLARK ROAD 1102 | CB | FALSE | 2444.9029 | 1435.1005 | 0.89192 | 20 | 0.0002022 | 389 | 1029.6753 | 809 | 0.22632 | 4.5263 | 268 | 0.01 | 2599
1714 | BUELLTON 1102Y50 | 183041102 | BUELLTON 1102 | Y50 | FALSE | 20651.346 | 17101.0403 | 10.6284 | 147 | 6.643e-05 | 2578 | 3157.5997 | 246 | 0.22624 | 33.2573 | 269 | 4.23 | 523
2661 | CLAY 11031230 | 163341103 | CLAY 1103 | 1230 | FALSE | 31242.042 | 27069.5791 | 16.8239 | 136 | 8.4359e-05 | 2080 | 2820.2882 | 297 | 0.22608 | 30.7471 | 270 | 0.08 | 1627
511 | COTTONWOOD 11029026 | 102931102 | COTTONWOOD 1102 | 9026 | FALSE | 39327.0742 | 20154.6992 | 12.5262 | 282 | 7.3532e-05 | 2382 | 3010.4191 | 268 | 0.22599 | 63.7295 | 271 | 0.04 | 2131
5682 | CLOVERDALE 1102672 | 42821102 | CLOVERDALE 1102 | 672 | FALSE | 35787.4101 | 35088.8854 | 21.8079 | 140 | 0.00010502 | 1528 | 2485.285 | 343 | 0.22571 | 31.5995 | 272 | 0.66 | 819
920 | RED BLUFF 11041630 | 103541104 | RED BLUFF 1104 | 1630 | FALSE | 22751.2492 | 4020.9242 | 2.499 | 152 | 5.7083e-05 | 2858 | 3897.064 | 159 | 0.22562 | 34.2944 | 273 | 0.02 | 2518
6155 | AUBERRY 1101R2839 | 254151101 | AUBERRY 1101 | R2839 | FALSE | 20608.9537 | 20608.9537 | 12.8085 | 121 | 6.3713e-05 | 2657 | 3802.0162 | 170 | 0.22501 | 27.2266 | 274 | 0.07 | 1746
252 | CLARK ROAD 11022582 | 103091102 | CLARK ROAD 1102 | 2582 | FALSE | 33578.71 | 32011.0943 | 19.895 | 186 | 8.3332e-05 | 2124 | 2966.3342 | 275 | 0.22449 | 41.7559 | 275 | 0.31 | 999
5168 | CORNING 11021622 | 103331102 | CORNING 1102 | 1622 | FALSE | 54701.9644 | 54701.9644 | 33.9975 | 126 | 4.7554e-05 | 3098 | 5068.1116 | 70 | 0.22413 | 28.2406 | 276 | 0.15 | 1289
2620 | AUBERRY 1101R2579 | 254151101 | AUBERRY 1101 | R2579 | FALSE | 56162.7607 | 56162.7607 | 34.9054 | 286 | 4.3679e-05 | 3195 | 4995.9654 | 78 | 0.22394 | 64.0469 | 277 | 0.05 | 1982
7109 | AUBERRY 1102R1013 | 254151102 | AUBERRY 1102 | R1013 | FALSE | 20054.4308 | 20054.4308 | 12.4639 | 132 | 5.2064e-05 | 2991 | 4310.3961 | 125 | 0.22385 | 29.5483 | 278 | 0.08 | 1599
1039 | SILVERADO 2104726 | 43432104 | SILVERADO 2104 | 726 | FALSE | 56301.3396 | 48875.2274 | 30.3762 | 263 | 0.00010365 | 1558 | 2367.3738 | 368 | 0.22347 | 58.7725 | 279 | 5.19 | 495
8364 | PEORIA 1705CB | 163781705 | PEORIA 1705 | CB | FALSE | 11342.4728 | 11342.4728 | 7.0494 | 33 | 9.1397e-05 | 1864 | 1823.5922 | 499 | 0.22294 | 7.3571 | 280 | 1.24 | 696
42 | CEDAR CREEK 11011664 | 103321101 | CEDAR CREEK 1101 | 1664 | FALSE | 47581.2918 | 47581.2918 | 29.572 | 244 | 0.00016153 | 624 | 1257.5627 | 697 | 0.22209 | 54.1896 | 281 | 0.09 | 1544
8613 | ZACA 1101Y72 | 182681101 | ZACA 1101 | Y72 | FALSE | 10347.4182 | 10265.6354 | 6.3801 | 36 | 7.4862e-05 | 2335 | 2941.2416 | 282 | 0.2213 | 7.967 | 282 | 0.05 | 1994
5656 | PANORAMA 1102508502 | 103461102 | PANORAMA 1102 | 508502 | FALSE | 25902.2253 | 18917.893 | 11.7575 | 115 | 8.1215e-05 | 2178 | 2793.3826 | 300 | 0.22043 | 25.3491 | 283 |  | 2971
2018 | SMARTVILLE 1101CB | 153791101 | SMARTVILLE 1101 | CB | FALSE | 26399.8993 | 26026.0287 | 16.1753 | 152 | 0.00012844 | 1042 | 2226.2508 | 395 | 0.21931 | 33.3354 | 284 | 0.08 | 1659
8459 | CAYETANO 21099504 | 14422109 | CAYETANO 2109 | 9504 | FALSE | 23288.5561 | 23283.8699 | 14.471 | 97 | 5.1866e-05 | 2997 | 4524.1542 | 104 | 0.21922 | 21.2645 | 285 | 0.67 | 812
3475 | SO. CAL. EDISON #3 1101CB | 258861101 | SO. CAL. EDISON #3 1101 | CB | FALSE | 13738.3645 | 13738.3645 | 8.5384 | 32 | 4.0322e-05 | 3260 | 5713.5203 | 42 | 0.21869 | 6.998 | 286 | 0.06 | 1881
5637 | NARROWS 2101CB | 153132101 | NARROWS 2101 | CB | FALSE | 25047.8448 | 25047.8448 | 15.5673 | 65 | 0.00013384 | 945 | 2147.2351 | 413 | 0.21823 | 14.185 | 287 | 0.06 | 1867
8049 | BROWNS VALLEY 110136622 | 152921101 | BROWNS VALLEY 1101 | 36622 | FALSE | 15095.8174 | 8277.82 | 5.1447 | 42 | 0.00010696 | 1475 | 1906.2139 | 474 | 0.21771 | 9.1438 | 288 | 0.01 | 2620
5251 | WYANDOTTE 110313018 | 102911103 | WYANDOTTE 1103 | 13018 | FALSE | 2657.2717 | 1090.3862 | 0.67768 | 20 | 0.00024176 | 241 | 916.9696 | 877 | 0.21662 | 4.3325 | 289 | 0.04 | 2205
7438 | OREGON TRAIL 1103CB | 103521103 | OREGON TRAIL 1103 | CB | FALSE | 4716.8976 | 4354.341 | 2.7062 | 38 | 0.00020157 | 391 | 1548.9969 | 580 | 0.21644 | 8.2246 | 290 | 0.07 | 1689
9233 | PASO ROBLES 1103N52 | 182611103 | PASO ROBLES 1103 | N52 | FALSE | 10571.3698 | 10571.3698 | 6.5701 | 32 | 0.00016961 | 565 | 1370.1644 | 652 | 0.21643 | 6.9258 | 291 | 0.06 | 1851
5544 | TYLER 11051536 | 103571105 | TYLER 1105 | 1536 | FALSE | 29066.1076 | 28603.8149 | 17.7774 | 79 | 4.6575e-05 | 3124 | 4923.7257 | 83 | 0.21608 | 17.0703 | 292 | 0.07 | 1705
8708 | PUTAH CREEK 1105665952 | 63681105 | PUTAH CREEK 1105 | 665952 | TRUE | 1521.662 | 243.3824 | 0.15126 | 13 | 7.1774e-05 | 2427 | 3135.666 | 250 | 0.21591 | 2.8069 | 293 |  | 3252
9580 | SUMMIT 110147786 | 152591101 | SUMMIT 1101 | 47786 | FALSE | 2915.7036 | 2915.7036 | 1.8121 | 13 | 8.7369e-05 | 2003 | 2875.37 | 291 | 0.21513 | 2.7967 | 294 | 0.01 | 2571
10253 | CLOVERDALE 1102736078 | 42821102 | CLOVERDALE 1102 | 736078 | TRUE | 432.8669 | 373.6781 | 0.23224 | 3 | 6.8384e-05 | 2526 | 3199.3848 | 241 | 0.2146 | 0.64381 | 295 |  | 3522
10589 | DEL MAR 2109306972 | 152582109 | DEL MAR 2109 | 306972 | TRUE | 120.3234 | 83.4407 | 0.051859 | 2 | 0.00015818 | 661 | 1356.3524 | 660 | 0.21455 | 0.4291 | 296 |  | 3576
9314 | CALPINE 1146CB | 48011146 | CALPINE 1146 | CB | FALSE | 4947.493 | 4947.493 | 3.0749 | 21 | 0.00013269 | 965 | 2090.7818 | 430 | 0.21399 | 4.4937 | 297 | 0.32 | 995
5389 | BEAR VALLEY 210511210 | 252192105 | BEAR VALLEY 2105 | 11210 | FALSE | 27492.7886 | 27492.7886 | 17.0869 | 139 | 4.899e-05 | 3064 | 4555.1801 | 103 | 0.21387 | 29.7273 | 298 | 0.02 | 2413
9003 | HARTLEY 1102385838 | 43211102 | HARTLEY 1102 | 385838 | FALSE | 2645.3497 | 2006.1588 | 1.2468 | 11 | 9.3256e-05 | 1815 | 1869.8054 | 483 | 0.21349 | 2.3484 | 299 |  | 3295
4243 | CLAYTON 22122944 | 12022212 | CLAYTON 2212 | 2944 | FALSE | 24391.9365 | 24262.4198 | 15.0792 | 148 | 5.6051e-05 | 2885 | 4103.8075 | 143 | 0.21331 | 31.5694 | 300 | 0.08 | 1576
3022 | DESCHUTES 11041582 | 103351104 | DESCHUTES 1104 | 1582 | FALSE | 24298.6245 | 10265.1395 | 6.3798 | 173 | 8.393e-05 | 2096 | 2774.3491 | 305 | 0.21327 | 36.8955 | 301 | 0.05 | 1927
5186 | DUNLAP 11027360 | 254061102 | DUNLAP 1102 | 7360 | FALSE | 14342.2552 | 14342.2552 | 8.9138 | 83 | 5.7731e-05 | 2844 | 3097.6367 | 256 | 0.21272 | 17.6557 | 302 | 0 | 2643
7188 | UPPER LAKE 1101472084 | 42871101 | UPPER LAKE 1101 | 472084 | FALSE | 11718.4795 | 7454.711 | 4.6331 | 66 | 0.00014287 | 829 | 1759.7585 | 512 | 0.21229 | 14.0108 | 303 | 0.03 | 2360
1958 | CURTIS 170411290 | 163351704 | CURTIS 1704 | 11290 | FALSE | 12662.0411 | 12662.0411 | 7.8695 | 75 | 8.7993e-05 | 1982 | 2545.3939 | 339 | 0.21224 | 15.9178 | 304 | 0.1 | 1455
10301 | SCE VEGAS 1701CB | 188881701 | SCE VEGAS 1701 | CB | TRUE | 168.4127 | 168.4127 | 0.10467 | 1 | 9.0971e-05 | 1882 | 2332.6265 | 379 | 0.2122 | 0.2122 | 305 | 0.27 | 1058
4384 | AUBERRY 110237466 | 254151102 | AUBERRY 1102 | 37466 | FALSE | 50978.0825 | 50460.2287 | 31.3612 | 345 | 3.2323e-05 | 3395 | 6743.7065 | 13 | 0.21127 | 72.8874 | 306 | 0.08 | 1598
2676 | BUELLTON 1102CB | 183041102 | BUELLTON 1102 | CB | FALSE | 22068.3915 | 11401.8921 | 7.0863 | 148 | 5.6901e-05 | 2864 | 2830.5359 | 295 | 0.21085 | 31.2055 | 307 | 1.66 | 655
5276 | SANTA YNEZ 110477098 | 182721104 | SANTA YNEZ 1104 | 77098 | FALSE | 20978.2648 | 19250.5668 | 11.9643 | 112 | 5.0472e-05 | 3025 | 4289.2504 | 127 | 0.21042 | 23.5673 | 308 | 2.69 | 589
7565 | SILVERADO 2104806 | 43432104 | SILVERADO 2104 | 806 | FALSE | 55052.2104 | 33831.6044 | 21.0265 | 229 | 9.1806e-05 | 1850 | 2097.6482 | 426 | 0.21008 | 48.1076 | 309 | 0.15 | 1276
1159 | LONE TREE 210521210 | 13232105 | LONE TREE 2105 | 21210 | FALSE | 26056.9931 | 20686.2377 | 12.8566 | 111 | 5.4908e-05 | 2916 | 4309.2408 | 126 | 0.20896 | 23.1943 | 310 | 0.06 | 1808
1515 | WYANDOTTE 110979932 | 102911109 | WYANDOTTE 1109 | 79932 | FALSE | 52854.9374 | 35504.8505 | 22.0664 | 345 | 8.0348e-05 | 2196 | 2706.2696 | 310 | 0.20828 | 71.8562 | 311 | 0.1 | 1497
4727 | REDBUD 1101454 | 43191101 | REDBUD 1101 | 454 | FALSE | 8909.2195 | 8909.2195 | 5.5371 | 54 | 6.6514e-05 | 2574 | 3069.2553 | 261 | 0.20738 | 11.1984 | 312 | 0.38 | 962
2411 | MARIPOSA 210190180 | 254452101 | MARIPOSA 2101 | 90180 | FALSE | 7976.0066 | 7976.0066 | 4.9571 | 49 | 5.4502e-05 | 2932 | 3678.4222 | 183 | 0.20688 | 10.1373 | 313 | 0.02 | 2514
6630 | MIDDLETOWN 1101644756 | 43141101 | MIDDLETOWN 1101 | 644756 | FALSE | 31848.1753 | 27875.8932 | 17.325 | 163 | 0.00011577 | 1279 | 1915.4825 | 470 | 0.20636 | 33.6372 | 314 |  | 3049
8301 | ELK CREEK 11012002 | 102781101 | ELK CREEK 1101 | 2002 | FALSE | 48391.7593 | 35045.7729 | 21.7811 | 109 | 5.5059e-05 | 2908 | 4261.2835 | 130 | 0.20473 | 22.3155 | 315 | 0.05 | 1965
1537 | BELL 11072400 | 152701107 | BELL 1107 | 2400 | FALSE | 44680.5549 | 41414.8349 | 25.7395 | 320 | 0.00010832 | 1445 | 2117.8289 | 423 | 0.20423 | 65.3543 | 316 | 10.83 | 393
2016 | PETALUMA C 1108296 | 42631108 | PETALUMA C 1108 | 296 | FALSE | 23764.0701 | 23764.0701 | 14.7695 | 123 | 8.734e-05 | 2004 | 2337.6554 | 376 | 0.20401 | 25.0928 | 317 | 6.9 | 457
1327 | DESCHUTES 1104CB | 103351104 | DESCHUTES 1104 | CB | FALSE | 39932.7775 | 21735.4144 | 13.5086 | 273 | 0.00010469 | 1537 | 2355.7077 | 371 | 0.20316 | 55.4629 | 318 | 0.09 | 1519
10175 | JESSUP 1102936897 | 103441102 | JESSUP 1102 | 936897 | TRUE | 1562.7499 | 665.5519 | 0.41364 | 12 | 0.00014733 | 769 | 1798.1732 | 507 | 0.20267 | 2.432 | 319 |  | 3507
2512 | CLAY 110334338 | 163341103 | CLAY 1103 | 34338 | FALSE | 16775.5793 | 15726.6133 | 9.7742 | 66 | 6.79e-05 | 2539 | 3085.8385 | 258 | 0.2022 | 13.3455 | 320 | 0.08 | 1669
3530 | AUBERRY 1102R2850 | 254151102 | AUBERRY 1102 | R2850 | FALSE | 42428.4265 | 42428.4265 | 26.3694 | 222 | 3.6057e-05 | 3337 | 5548.3018 | 47 | 0.20166 | 44.7693 | 321 | 0.17 | 1244
4238 | NORTH BRANCH 1101CB | 163231101 | NORTH BRANCH 1101 | CB | FALSE | 32934.7957 | 25410.3119 | 15.7926 | 114 | 0.00011157 | 1381 | 1859.3886 | 488 | 0.20132 | 22.9503 | 322 | 0.04 | 2202
11083 | NARROWS 2104CB | 153132104 | NARROWS 2104 | CB | TRUE | 4.572 | 4.572 | 0.0028415 | 1 | 0.00012264 | 1138 | 1641.5431 | 545 | 0.20132 | 0.20132 | 323 | 0.02 | 2423
389 | VASCO 1102MR176 | 13751102 | VASCO 1102 | MR176 | FALSE | 68684.3236 | 62474.1803 | 38.828 | 256 | 5.5783e-05 | 2894 | 3634.7993 | 187 | 0.20121 | 51.5086 | 324 | 0.19 | 1184
7455 | SAN MIGUEL 1104514987 | 182661104 | SAN MIGUEL 1104 | 514987 | FALSE | 21614.682 | 13379.7927 | 8.3156 | 63 | 4.6195e-05 | 3132 | 4320.4063 | 122 | 0.20048 | 12.6303 | 325 |  | 3128
7507 | NORTH BRANCH 110111158 | 163231101 | NORTH BRANCH 1101 | 11158 | FALSE | 47609.4929 | 20499.8935 | 12.7408 | 229 | 9.6418e-05 | 1721 | 2379.6196 | 364 | 0.20008 | 45.8175 | 326 | 0.06 | 1777
3193 | AUBERRY 1101R314 | 254151101 | AUBERRY 1101 | R314 | FALSE | 71701.2396 | 68245.5324 | 42.4149 | 390 | 3.2526e-05 | 3393 | 6228.9607 | 25 | 0.20004 | 78.017 | 327 | 0.11 | 1437
1293 | MIDDLETOWN 11014646 | 43141101 | MIDDLETOWN 1101 | 4646 | FALSE | 29868.2951 | 29868.2951 | 18.5633 | 165 | 0.00010487 | 1531 | 2139.2524 | 415 | 0.19983 | 32.9712 | 328 | 36.87 | 205
9642 | LUCERNE 11034200 | 43351103 | LUCERNE 1103 | 4200 | FALSE | 7940.3444 | 6495.7462 | 4.0371 | 37 | 0.00011057 | 1400 | 2908.2309 | 287 | 0.19927 | 7.3729 | 329 | 0.05 | 1995
7729 | AUBERRY 110149122 | 254151101 | AUBERRY 1101 | 49122 | FALSE | 6376.3554 | 6376.3554 | 3.9629 | 40 | 4.9196e-05 | 3060 | 3584.6164 | 191 | 0.19907 | 7.9627 | 330 | 1.33 | 682
464 | WOODACRE 110196844 | 43021101 | WOODACRE 1101 | 96844 | FALSE | 9556.2941 | 9556.2941 | 5.9393 | 63 | 0.00023552 | 260 | 862.5947 | 906 | 0.19881 | 12.5249 | 331 | 46.48 | 142
4726 | SHINGLE SPRINGS 210985766 | 153652109 | SHINGLE SPRINGS 2109 | 85766 | FALSE | 29746.7523 | 29746.7523 | 18.4877 | 166 | 0.00013073 | 996 | 2062.5576 | 442 | 0.19865 | 32.9759 | 332 | 0.1 | 1495
9424 | VINEYARD 2110391250 | 14502110 | VINEYARD 2110 | 391250 | FALSE | 1481.3226 | 1481.3226 | 0.92065 | 3 | 0.00010172 | 1612 | 1985.1612 | 457 | 0.19841 | 0.59524 | 333 |  | 3356
308 | CALPINE 1144CB | 48011144 | CALPINE 1144 | CB | FALSE | 42270.0145 | 42270.0145 | 26.271 | 131 | 0.00014762 | 766 | 1407.8483 | 633 | 0.19817 | 25.9607 | 334 | 0.25 | 1086
7335 | UPPER LAKE 11011276 | 42871101 | UPPER LAKE 1101 | 1276 | FALSE | 20806.9121 | 20806.9121 | 12.9316 | 116 | 9.8156e-05 | 1687 | 2220.124 | 397 | 0.19794 | 22.9608 | 335 | 0.05 | 1931
3179 | CHOLAME 2102796386 | 182562102 | CHOLAME 2102 | 796386 | FALSE | 64232.6683 | 57391.9753 | 35.6693 | 159 | 5.7453e-05 | 2849 | 3563.2207 | 192 | 0.19792 | 31.4686 | 336 |  | 2815
9031 | SAND CREEK 1103CB | 254601103 | SAND CREEK 1103 | CB | FALSE | 20983.2028 | 20983.2028 | 13.0411 | 77 | 2.8008e-05 | 3460 | 6753.7935 | 12 | 0.19768 | 15.2216 | 337 | 0.07 | 1765
6545 | TULUCAY 1101628 | 42301101 | TULUCAY 1101 | 628 | FALSE | 14091.1105 | 6713.6414 | 4.1726 | 98 | 0.00010294 | 1570 | 2036.6122 | 448 | 0.19686 | 19.2923 | 338 | 0.05 | 2063
4963 | BEAR VALLEY 210190550 | 252192101 | BEAR VALLEY 2101 | 90550 | FALSE | 12911.2772 | 12911.2772 | 8.0244 | 47 | 5.1033e-05 | 3014 | 3547.8361 | 195 | 0.19624 | 9.2235 | 339 | 0.02 | 2486
8575 | ELK CREEK 11012106 | 102781101 | ELK CREEK 1101 | 2106 | FALSE | 21303.4581 | 21303.4581 | 13.2402 | 67 | 3.7752e-05 | 3302 | 5722.5441 | 40 | 0.1961 | 13.1388 | 340 | 0.03 | 2286
3500 | DUNLAP 11037040 | 254061103 | DUNLAP 1103 | 7040 | FALSE | 39870.081 | 39870.081 | 24.7794 | 230 | 4.8475e-05 | 3079 | 4388.1035 | 116 | 0.19605 | 45.0921 | 341 | 0.07 | 1719
2568 | LAYTONVILLE 1102500 | 42681102 | LAYTONVILLE 1102 | 500 | FALSE | 47144.6891 | 34375.7452 | 21.3647 | 214 | 0.00018229 | 495 | 1298.6787 | 684 | 0.19576 | 41.8921 | 342 | 2.86 | 574
2190 | DIAMOND SPRINGS 110519910 | 152261105 | DIAMOND SPRINGS 1105 | 19910 | FALSE | 33304.7006 | 33304.7006 | 20.699 | 226 | 0.00010076 | 1629 | 2072.4287 | 435 | 0.19568 | 44.2238 | 343 | 0.32 | 994
9927 | FITCH MOUNTAIN 1111555644 | 42751111 | FITCH MOUNTAIN 1111 | 555644 | TRUE | 5004.528 | 268.6791 | 0.16699 | 19 | 0.00011733 | 1240 | 1847.862 | 491 | 0.19539 | 3.7125 | 344 |  | 3453
41 | REDBUD 1101708166 | 43191101 | REDBUD 1101 | 708166 | FALSE | 33499.3555 | 18511.1854 | 11.5048 | 162 | 7.986e-05 | 2209 | 2528.2807 | 340 | 0.19539 | 31.6535 | 345 | 9.62 | 407
8428 | CALPELLA 11013419 | 43411101 | CALPELLA 1101 | 3419 | FALSE | 12848.2917 | 12848.2917 | 7.9853 | 38 | 9.3996e-05 | 1794 | 2318.7771 | 381 | 0.19531 | 7.4218 | 346 | 0.08 | 1610
4645 | OLETA 110241396 | 163541102 | OLETA 1102 | 41396 | FALSE | 11819.9639 | 10868.1559 | 6.7546 | 75 | 0.00014922 | 747 | 1168.3526 | 746 | 0.19503 | 14.6272 | 347 | 0.08 | 1642
1354 | CORRAL 1102CB | 162991102 | CORRAL 1102 | CB | FALSE | 34280.1417 | 27168.7986 | 16.8855 | 236 | 7.8906e-05 | 2237 | 2954.5395 | 278 | 0.19501 | 46.0213 | 348 | 0.13 | 1353
6647 | TIVY VALLEY 1107584840 | 252941107 | TIVY VALLEY 1107 | 584840 | FALSE | 72531.1064 | 72531.1064 | 45.0784 | 449 | 3.4014e-05 | 3370 | 5963.8827 | 31 | 0.19446 | 87.311 | 349 | 0.16 | 1267
4112 | JESSUP 110141356 | 103441101 | JESSUP 1101 | 41356 | FALSE | 52238.1569 | 52238.1569 | 32.4662 | 318 | 8.9642e-05 | 1926 | 2383.6073 | 362 | 0.19445 | 61.8351 | 350 | 1.05 | 720
1219 | APPLE HILL 21021532 | 153662102 | APPLE HILL 2102 | 1532 | FALSE | 68074.9976 | 62691.3369 | 38.9629 | 465 | 0.00014754 | 767 | 1398.4344 | 638 | 0.19412 | 90.2637 | 351 | 0.07 | 1756
4008 | OLETA 11011208 | 163541101 | OLETA 1101 | 1208 | FALSE | 61463.0017 | 53098.4432 | 33.0009 | 334 | 7.3226e-05 | 2389 | 2975.7795 | 271 | 0.19404 | 64.811 | 352 | 0.06 | 1784
9763 | WISHON 1101CB | 251511101 | WISHON 1101 | CB | FALSE | 12293.5283 | 12293.5283 | 7.6405 | 36 | 4.9465e-05 | 3052 | 3520.3689 | 199 | 0.19398 | 6.9834 | 353 | 0.13 | 1346
4721 | COPPERMINE 1104613086 | 252411104 | COPPERMINE 1104 | 613086 | FALSE | 14704.7375 | 8243.1424 | 5.1231 | 63 | 2.9814e-05 | 3430 | 6359.1487 | 20 | 0.19391 | 12.2166 | 354 |  | 2913
8166 | BANGOR 1101CB | 103191101 | BANGOR 1101 | CB | FALSE | 34332.3301 | 30178.5623 | 18.7561 | 171 | 0.00012918 | 1023 | 1585.4725 | 565 | 0.19378 | 33.1366 | 355 | 0.08 | 1606
10364 | MADISON 2101745850 | 63172101 | MADISON 2101 | 745850 | TRUE | 1558.6923 | 771.4701 | 0.47947 | 7 | 5.3176e-05 | 2960 | 3897.9708 | 158 | 0.19369 | 1.3558 | 356 |  | 3539
10620 | OLETA 1102793776 | 163541102 | OLETA 1102 | 793776 | FALSE | 1956.9595 | 1956.9595 | 1.2163 | 6 | 0.00010286 | 1574 | 1821.9134 | 500 | 0.19328 | 1.1597 | 357 |  | 3579
1881 | PENRYN 1103604 | 152561103 | PENRYN 1103 | 604 | FALSE | 42817.3578 | 42516.8793 | 26.4244 | 240 | 0.00012061 | 1176 | 1665.6014 | 537 | 0.19315 | 46.357 | 358 | 8.39 | 428
10174 | LAS GALLINAS A 1105532 | 42991105 | LAS GALLINAS A 1105 | 532 | FALSE | 7102.1777 | 7099.179 | 4.4122 | 34 | 0.00016574 | 585 | 1247.6791 | 702 | 0.19264 | 6.5497 | 359 | 0.65 | 824
9563 | ELK CREEK 11012032 | 102781101 | ELK CREEK 1101 | 2032 | FALSE | 15248.6713 | 14097.676 | 8.7618 | 52 | 6.4621e-05 | 2618 | 3297.3647 | 225 | 0.19237 | 10.0031 | 360 | 0.06 | 1841
7617 | WYANDOTTE 110213044 | 102911102 | WYANDOTTE 1102 | 13044 | FALSE | 9652.7072 | 7674.8454 | 4.7699 | 51 | 0.00014015 | 867 | 1674.4804 | 533 | 0.19229 | 9.8065 | 361 | 0.05 | 1986
3855 | SAND CREEK 11037140 | 254601103 | SAND CREEK 1103 | 7140 | FALSE | 42300.5526 | 42300.5526 | 26.29 | 296 | 2.8237e-05 | 3453 | 6738.8921 | 14 | 0.19202 | 56.8394 | 362 | 3.46 | 546
5056 | BANGOR 110182350 | 103191101 | BANGOR 1101 | 82350 | FALSE | 33588.8136 | 31579.2765 | 19.6266 | 230 | 8.9019e-05 | 1948 | 2107.591 | 425 | 0.19196 | 44.1515 | 363 | 0.3 | 1019
523 | DUNLAP 11037220 | 254061103 | DUNLAP 1103 | 7220 | FALSE | 39952.2483 | 39952.2483 | 24.8305 | 188 | 4.2565e-05 | 3217 | 4516.9217 | 107 | 0.19171 | 36.0414 | 364 | 0.06 | 1901
8426 | FORT ROSS 1121CB | 42851121 | FORT ROSS 1121 | CB | TRUE | 25.9334 | 25.9334 | 0.016118 | 1 | 0.00013855 | 888 | 1382.2827 | 648 | 0.19152 | 0.19152 | 365 | 0.05 | 1929
8629 | FOOTHILL 1101645910 | 182951101 | FOOTHILL 1101 | 645910 | TRUE | 3990.9244 | 774.6277 | 0.48143 | 14 | 0.00012447 | 1110 | 1323.2798 | 673 | 0.19134 | 2.6788 | 366 |  | 3245
7469 | PALMER 110198478 | 183031101 | PALMER 1101 | 98478 | FALSE | 9678.6987 | 9678.6987 | 6.0154 | 34 | 6.1513e-05 | 2732 | 3101.9251 | 253 | 0.19124 | 6.5022 | 367 | 0.06 | 1824
5366 | WYANDOTTE 11095607 | 102911109 | WYANDOTTE 1109 | 5607 | FALSE | 10708.8001 | 7265.9446 | 4.5158 | 71 | 6.7647e-05 | 2544 | 3213.7492 | 235 | 0.19115 | 13.5714 | 368 | 0.05 | 2002
9473 | HARTLEY 1102524 | 43211102 | HARTLEY 1102 | 524 | TRUE | 4106.6103 | 399.4552 | 0.24826 | 31 | 8.7723e-05 | 1992 | 2173.4374 | 408 | 0.19015 | 5.8946 | 369 | 0.71 | 803
6494 | WISE 1102697216 | 152271102 | WISE 1102 | 697216 | FALSE | 21374.2842 | 21374.2842 | 13.2842 | 145 | 8.8971e-05 | 1951 | 1998.7247 | 456 | 0.18992 | 27.5378 | 370 | 1.72 | 648
4257 | REDBUD 1102CB | 43191102 | REDBUD 1102 | CB | FALSE | 32077.0701 | 28146.4256 | 17.4931 | 170 | 9.0631e-05 | 1893 | 2204.8048 | 402 | 0.18973 | 32.2538 | 371 | 5.76 | 479
9558 | BRENTWOOD 21056512 | 14592105 | BRENTWOOD 2105 | 6512 | FALSE | 1047.7996 | 1047.7996 | 0.65121 | 5 | 6.0555e-05 | 2761 | 1094.509 | 777 | 0.18909 | 0.94545 | 372 | 0.08 | 1593
10458 | DEL MAR 2109805882 | 152582109 | DEL MAR 2109 | 805882 | TRUE | 497.9369 | 477.3024 | 0.29665 | 6 | 0.00016012 | 642 | 1125.8811 | 766 | 0.18904 | 1.1343 | 373 |  | 3553
2068 | OLETA 11021228 | 163541102 | OLETA 1102 | 1228 | FALSE | 69440.241 | 17449.9174 | 10.8452 | 368 | 0.00011636 | 1263 | 1613.8231 | 557 | 0.18877 | 69.4681 | 374 | 0.04 | 2078
2280 | DESCHUTES 11011580 | 103351101 | DESCHUTES 1101 | 1580 | FALSE | 80785.153 | 76365.8976 | 47.4617 | 383 | 0.00012062 | 1174 | 1821.2183 | 501 | 0.18779 | 71.9249 | 375 | 0.11 | 1451
6271 | COTTONWOOD 110131500 | 102931101 | COTTONWOOD 1101 | 31500 | FALSE | 18887.7142 | 7501.4293 | 4.6622 | 111 | 5.0427e-05 | 3030 | 3238.0724 | 229 | 0.18759 | 20.823 | 376 | 0.02 | 2550
449 | CLAYTON 221296224 | 12022212 | CLAYTON 2212 | 96224 | FALSE | 31213.3049 | 31213.3049 | 19.3992 | 174 | 6.6243e-05 | 2582 | 2944.2439 | 281 | 0.18755 | 32.6329 | 377 | 0.79 | 777
9225 | BUCKS CREEK 1102CB | 102211102 | BUCKS CREEK 1102 | CB | FALSE | 47599.3495 | 47599.3495 | 29.5832 | 121 | 0.00014957 | 743 | 1075.8896 | 783 | 0.1873 | 22.6633 | 378 | 0.07 | 1739
4556 | MARIPOSA 210237288 | 254452102 | MARIPOSA 2102 | 37288 | FALSE | 137232.3506 | 137232.3506 | 85.2905 | 678 | 4.4383e-05 | 3179 | 4408.5685 | 114 | 0.18718 | 126.9051 | 379 | 0.6 | 850
9851 | PANORAMA 1101885215 | 103461101 | PANORAMA 1101 | 885215 | FALSE | 3239.6899 | 3225.5678 | 2.0047 | 23 | 4.5966e-05 | 3138 | 3739.8152 | 178 | 0.18705 | 4.3021 | 380 |  | 3435
1129 | PETALUMA C 1109128 | 42631109 | PETALUMA C 1109 | 128 | FALSE | 60127.5406 | 56205.3694 | 34.9319 | 269 | 9.706e-05 | 1712 | 2077.9375 | 434 | 0.18687 | 50.2671 | 381 | 0.3 | 1014
5974 | DOBBINS 110169722 | 153741101 | DOBBINS 1101 | 69722 | FALSE | 10673.4289 | 10673.4289 | 6.6336 | 68 | 0.00014836 | 760 | 1483.0501 | 601 | 0.18675 | 12.6993 | 382 | 0.34 | 983
6088 | TYLER 110585132 | 103571105 | TYLER 1105 | 85132 | FALSE | 50093.0189 | 50093.0189 | 31.133 | 217 | 4.257e-05 | 3216 | 4662.7247 | 101 | 0.18633 | 40.4342 | 383 | 0.13 | 1354
6487 | STILLWATER 110248952 | 103561102 | STILLWATER 1102 | 48952 | FALSE | 17050.5619 | 17050.5619 | 10.597 | 123 | 0.00010175 | 1609 | 2266.9677 | 389 | 0.18561 | 22.8305 | 384 | 0.07 | 1722
7029 | PENRYN 1106212772 | 152561106 | PENRYN 1106 | 212772 | FALSE | 1753.1585 | 1609.198 | 1.0001 | 11 | 0.00010227 | 1596 | 1767.7041 | 510 | 0.18554 | 2.041 | 385 |  | 3087
7958 | GEYSERVILLE 110179788 | 42891101 | GEYSERVILLE 1101 | 79788 | FALSE | 67378.0299 | 63661.5746 | 39.5659 | 157 | 0.00011886 | 1209 | 1546.745 | 582 | 0.18551 | 29.1256 | 386 | 0.12 | 1399
2772 | WYANDOTTE 110913052 | 102911109 | WYANDOTTE 1109 | 13052 | FALSE | 31493.7185 | 31480.1828 | 19.5651 | 213 | 9.5258e-05 | 1758 | 2083.3172 | 433 | 0.18514 | 39.4358 | 387 | 0.12 | 1398
9699 | LOGAN CREEK 2102795010 | 103142102 | LOGAN CREEK 2102 | 795010 | FALSE | 6022.8068 | 5964.9276 | 3.7072 | 12 | 3.8042e-05 | 3300 | 5006.5635 | 76 | 0.18505 | 2.2206 | 388 |  | 3401
2290 | JESSUP 11021550 | 103441102 | JESSUP 1102 | 1550 | FALSE | 35703.4386 | 31009.474 | 19.2725 | 237 | 9.1451e-05 | 1860 | 2378.2716 | 365 | 0.18396 | 43.5983 | 389 | 0.06 | 1796
881 | RED BLUFF 11011556 | 103541101 | RED BLUFF 1101 | 1556 | FALSE | 64601.0138 | 61930.0824 | 38.4898 | 411 | 5.2815e-05 | 2977 | 3779.2145 | 173 | 0.18357 | 75.4478 | 390 | 0.18 | 1205
11061 | SAN LUIS OBISPO 1103365572 | 182631103 | SAN LUIS OBISPO 1103 | 365572 | TRUE | 696.8465 | 611.8589 | 0.38027 | 2 | 9.4733e-05 | 1772 | 2195.1828 | 403 | 0.18299 | 0.36597 | 391 |  | 3633
6935 | CEDAR CREEK 1101CB | 103321101 | CEDAR CREEK 1101 | CB | FALSE | 24813.8274 | 24813.8274 | 15.4219 | 127 | 0.00010514 | 1517 | 1354.0744 | 662 | 0.18254 | 23.1832 | 392 | 0.07 | 1749
3564 | JAMESON 1105466348 | 63801105 | JAMESON 1105 | 466348 | FALSE | 48812.3964 | 26039.2723 | 16.1835 | 294 | 9.3721e-05 | 1802 | 2063.8243 | 440 | 0.18223 | 53.5743 | 393 |  | 2838
2550 | COTTONWOOD 110335470 | 102931103 | COTTONWOOD 1103 | 35470 | FALSE | 40109.7772 | 33111.1919 | 20.5787 | 174 | 7.9998e-05 | 2205 | 2635.2321 | 323 | 0.18214 | 31.6926 | 394 | 1.26 | 692
2265 | BELL 1108CB | 152701108 | BELL 1108 | CB | TRUE | 9628.7582 | 0 | 0 | 83 | 0.00016581 | 584 | 955.774 | 856 | 0.18213 | 15.1167 | 395 | 0.04 | 2098
6694 | POTTER VALLEY P H 110537476 | 42281105 | POTTER VALLEY P H 1105 | 37476 | FALSE | 14076.4929 | 4231.6102 | 2.63 | 82 | 0.0001427 | 830 | 1332.1225 | 666 | 0.18107 | 14.8479 | 396 | 0.03 | 2366
2442 | CORRAL 110112612 | 162991101 | CORRAL 1101 | 12612 | FALSE | 32502.2662 | 31091.451 | 19.3235 | 195 | 7.8143e-05 | 2254 | 2667.8797 | 319 | 0.18095 | 35.2855 | 397 | 3.37 | 549
2325 | COTTONWOOD 11011510 | 102931101 | COTTONWOOD 1101 | 1510 | TRUE | 5333.1807 | 613.4018 | 0.38123 | 35 | 9.6024e-05 | 1728 | 1460.1171 | 611 | 0.18088 | 6.3309 | 398 | 0.5 | 894
6987 | TEMPLETON 2113641367 | 183052113 | TEMPLETON 2113 | 641367 | FALSE | 63879.2901 | 63879.2901 | 39.7012 | 278 | 6.9782e-05 | 2482 | 2628.7284 | 324 | 0.18079 | 50.2607 | 399 |  | 3081
1077 | CLAYTON 2212Y504R | 12022212 | CLAYTON 2212 | Y504R | FALSE | 18910.1435 | 18838.2347 | 11.708 | 112 | 7.2579e-05 | 2404 | 2414.4364 | 358 | 0.18021 | 20.1836 | 400 | 0.36 | 972
6538 | DUNLAP 11027060 | 254061102 | DUNLAP 1102 | 7060 | FALSE | 28760.1957 | 28760.1957 | 17.8746 | 162 | 4.1619e-05 | 3231 | 4251.992 | 132 | 0.18019 | 29.1914 | 401 | 0.05 | 2062
8223 | POSO MOUNTAIN 210448268 | 253642104 | POSO MOUNTAIN 2104 | 48268 | FALSE | 8165.6241 | 8152.5339 | 5.0668 | 30 | 2.8075e-05 | 3458 | 6541.9938 | 16 | 0.17977 | 5.3932 | 402 | 0.03 | 2409
7847 | OILFIELDS 11032757 | 182391103 | OILFIELDS 1103 | 2757 | FALSE | 4222.897 | 4222.897 | 2.6245 | 16 | 7.3477e-05 | 2384 | 2563.9177 | 338 | 0.1791 | 2.8656 | 403 | 0.07 | 1748
1905 | TIVY VALLEY 1107R1817 | 252941107 | TIVY VALLEY 1107 | R1817 | FALSE | 31029.2187 | 31029.2187 | 19.2848 | 145 | 3.1982e-05 | 3401 | 5976.6981 | 30 | 0.17888 | 25.9373 | 404 | 0.08 | 1648
3840 | SAND CREEK 11037070 | 254601103 | SAND CREEK 1103 | 7070 | FALSE | 28250.671 | 28250.671 | 17.5579 | 103 | 3.6129e-05 | 3333 | 5058.188 | 71 | 0.17873 | 18.4097 | 405 | 0.06 | 1902
1011 | CALISTOGA 1101890 | 42711101 | CALISTOGA 1101 | 890 | FALSE | 39539.8399 | 39211.6931 | 24.3702 | 203 | 0.00013749 | 903 | 1564.6167 | 573 | 0.17857 | 36.2505 | 406 | 0.6 | 852
1851 | KONOCTI 1102CB | 43311102 | KONOCTI 1102 | CB | FALSE | 15262.2312 | 6326.3363 | 3.9318 | 97 | 0.0001432 | 823 | 1232.8613 | 712 | 0.1779 | 17.2565 | 407 | 0.04 | 2123
7708 | COLUMBIA HILL 110190730 | 152471101 | COLUMBIA HILL 1101 | 90730 | FALSE | 13402.9331 | 13402.9331 | 8.33 | 77 | 0.00022241 | 309 | 801.5027 | 942 | 0.17712 | 13.6383 | 408 | 0.07 | 1738
10514 | SCE TEHACHAPI 1101CB | 258131101 | SCE TEHACHAPI 1101 | CB | FALSE | 1862.134 | 1862.134 | 1.1573 | 2 | 2.6503e-05 | 3479 | 5012.0663 | 75 | 0.17665 | 0.3533 | 409 | 0.11 | 1430
5375 | TASSAJARA 2109CB | 14662109 | TASSAJARA 2109 | CB | FALSE | 3124.8792 | 3111.1631 | 1.9336 | 12 | 0.00016891 | 568 | 1033.5651 | 803 | 0.17607 | 2.1128 | 410 | 0.03 | 2391
8181 | APPLE HILL 210289934 | 153662102 | APPLE HILL 2102 | 89934 | FALSE | 8917.9013 | 8917.9013 | 5.5425 | 56 | 0.00022642 | 301 | 791.9341 | 950 | 0.17581 | 9.8455 | 411 | 0.04 | 2125
3827 | HIGGINS 1109594 | 152691109 | HIGGINS 1109 | 594 | FALSE | 23079.0447 | 23079.0447 | 14.3437 | 155 | 0.00011929 | 1200 | 1640.4713 | 546 | 0.17563 | 27.2219 | 412 | 0.16 | 1253
329 | CORNING 110253184 | 103331102 | CORNING 1102 | 53184 | FALSE | 51204.6527 | 51204.6527 | 31.8239 | 123 | 4.4635e-05 | 3174 | 4517.1008 | 106 | 0.17544 | 21.5791 | 413 | 0.06 | 1844
6969 | PETALUMA C 1108208 | 42631108 | PETALUMA C 1108 | 208 | FALSE | 20077.9466 | 20077.9466 | 12.4785 | 95 | 9.3548e-05 | 1810 | 1783.8562 | 508 | 0.1754 | 16.663 | 414 | 11.75 | 382
8229 | GARBERVILLE 11012026 | 192221101 | GARBERVILLE 1101 | 2026 | FALSE | 10220.4249 | 10220.4249 | 6.352 | 26 | 0.00034659 | 95 | 363.8152 | 1347 | 0.17512 | 4.5532 | 415 | 0.84 | 768
8173 | ZACA 1101CB | 182681101 | ZACA 1101 | CB | FALSE | 17435.9444 | 12032.4791 | 7.4782 | 60 | 6.3071e-05 | 2678 | 1838.5396 | 494 | 0.17499 | 10.4995 | 416 | 0.03 | 2401
5131 | PHILO 11013700 | 42601101 | PHILO 1101 | 3700 | FALSE | 29156.0449 | 29156.0449 | 18.1206 | 116 | 0.00013347 | 952 | 1560.5823 | 576 | 0.17472 | 20.2673 | 417 | 0.06 | 1905
908 | PUTAH CREEK 1102710384 | 63681102 | PUTAH CREEK 1102 | 710384 | FALSE | 15468.9282 | 8584.2298 | 5.3351 | 84 | 5.8195e-05 | 2830 | 3710.5415 | 182 | 0.17469 | 14.6739 | 418 |  | 2697
9983 | JAMESON 1105913400 | 63801105 | JAMESON 1105 | 913400 | TRUE | 1667.834 | 172.3529 | 0.10712 | 14 | 0.00011832 | 1223 | 1563.2661 | 575 | 0.17457 | 2.444 | 419 |  | 3465
6899 | FORT SEWARD 11211690 | 192321121 | FORT SEWARD 1121 | 1690 | FALSE | 26217.8201 | 17377.7027 | 10.8003 | 77 | 0.0001954 | 415 | 901.067 | 883 | 0.17449 | 13.4358 | 420 | 7.44 | 444
2810 | OAKHURST 110110090 | 254421101 | OAKHURST 1101 | 10090 | FALSE | 70938.5406 | 70938.5406 | 44.0886 | 435 | 5.7014e-05 | 2861 | 3810.3636 | 167 | 0.17437 | 75.8506 | 421 | 0.3 | 1021
8488 | BROWNS VALLEY 1101CB | 152921101 | BROWNS VALLEY 1101 | CB | FALSE | 4580.4088 | 3639.3631 | 2.2619 | 17 | 0.00012727 | 1059 | 1563.9973 | 574 | 0.1743 | 2.9631 | 422 |  | 3230
1886 | REDBUD 1101323962 | 43191101 | REDBUD 1101 | 323962 | FALSE | 46007.9913 | 33116.5425 | 20.5821 | 282 | 7.3879e-05 | 2363 | 2674.5475 | 317 | 0.17389 | 49.0357 | 423 | 22.52 | 293
7655 | SHINGLE SPRINGS 210851476 | 153652108 | SHINGLE SPRINGS 2108 | 51476 | FALSE | 10437.2128 | 7926.327 | 4.9262 | 74 | 9.4268e-05 | 1787 | 2122.2216 | 419 | 0.1736 | 12.8462 | 424 | 14.32 | 355
6143 | OILFIELDS 1103N64 | 182391103 | OILFIELDS 1103 | N64 | FALSE | 20207.5385 | 17721.3198 | 11.0139 | 101 | 0.00011489 | 1302 | 1611.5581 | 558 | 0.17314 | 17.4874 | 425 | 0.05 | 2025
3312 | OLETA 11011217 | 163541101 | OLETA 1101 | 1217 | FALSE | 27736.9205 | 22843.3853 | 14.1973 | 116 | 5.896e-05 | 2808 | 3212.896 | 236 | 0.17295 | 20.0623 | 426 | 2.25 | 617
10420 | SANTA YNEZ 1101673618 | 182721101 | SANTA YNEZ 1101 | 673618 | TRUE | 533.16 | 171.3788 | 0.10651 | 4 | 5.0101e-05 | 3035 | 3451.8103 | 207 | 0.17294 | 0.69175 | 427 |  | 3547
50 | MARIPOSA 210135244 | 254452101 | MARIPOSA 2101 | 35244 | FALSE | 28098.7686 | 28098.7686 | 17.4635 | 146 | 7.6076e-05 | 2306 | 1918.8043 | 468 | 0.17286 | 25.237 | 428 | 0.1 | 1464
6824 | MARIPOSA 21021960 | 254452102 | MARIPOSA 2102 | 1960 | FALSE | 39696.7204 | 39696.7204 | 24.6717 | 223 | 4.465e-05 | 3171 | 4411.9471 | 113 | 0.17242 | 38.4488 | 429 | 0.42 | 933
7293 | WISE 11022234 | 152271102 | WISE 1102 | 2234 | FALSE | 24349.9914 | 24349.9914 | 15.1336 | 179 | 8.3357e-05 | 2123 | 2208.9033 | 401 | 0.17198 | 30.784 | 430 | 1.04 | 723
6103 | CALPELLA 1102421412 | 43411102 | CALPELLA 1102 | 421412 | FALSE | 5653.9032 | 1616.3093 | 1.0045 | 38 | 0.00012063 | 1173 | 1137.8972 | 758 | 0.17127 | 6.5083 | 431 |  | 3003
8262 | DESCHUTES 11019722 | 103351101 | DESCHUTES 1101 | 9722 | FALSE | 7647.7388 | 5139.2872 | 3.1941 | 55 | 9.2715e-05 | 1828 | 2011.1796 | 454 | 0.17084 | 9.3959 | 432 | 2.06 | 625
3350 | OAKHURST 110310570 | 254421103 | OAKHURST 1103 | 10570 | FALSE | 15440.8056 | 15440.8056 | 9.5965 | 92 | 5.2246e-05 | 2985 | 3374.5233 | 214 | 0.17053 | 15.6885 | 433 | 0.28 | 1043
7252 | OILFIELDS 1103N42 | 182391103 | OILFIELDS 1103 | N42 | FALSE | 9607.0794 | 5997.3144 | 3.7274 | 30 | 9.7321e-05 | 1705 | 2091.1209 | 429 | 0.17017 | 5.105 | 434 | 0 | 2631
2738 | SAN BENITO 2101221165 | 182742101 | SAN BENITO 2101 | 221165 | FALSE | 7814.4254 | 7056.9288 | 4.3859 | 39 | 7.1264e-05 | 2439 | 2286.9555 | 387 | 0.17016 | 6.6364 | 435 |  | 2797
10162 | MADISON 210113372 | 63172101 | MADISON 2101 | 13372 | FALSE | 6191.0561 | 6152.1597 | 3.8236 | 5 | 3.5403e-05 | 3342 | 4181.8896 | 139 | 0.17014 | 0.85069 | 436 | 1.32 | 686
4788 | COTTONWOOD 11039072 | 102931103 | COTTONWOOD 1103 | 9072 | FALSE | 46343.9208 | 46343.9208 | 28.8029 | 279 | 4.9258e-05 | 3057 | 3602.3143 | 190 | 0.1698 | 47.3736 | 437 | 4.2 | 524
10660 | CLAYTON 2212334476 | 12022212 | CLAYTON 2212 | 334476 | TRUE | 102.0354 | 89.9428 | 0.0559 | 2 | 3.6826e-05 | 3318 | 3174.6241 | 245 | 0.16961 | 0.33922 | 438 |  | 3587
5708 | HARTLEY 1101658 | 43211101 | HARTLEY 1101 | 658 | FALSE | 21722.426 | 4561.1197 | 2.8348 | 136 | 9.6216e-05 | 1727 | 1846.2822 | 492 | 0.16943 | 23.042 | 439 | 0.53 | 882
52 | HIGHLANDS 1103520 | 43361103 | HIGHLANDS 1103 | 520 | FALSE | 75123.246 | 75123.246 | 46.6894 | 437 | 8.2363e-05 | 2144 | 2644.041 | 320 | 0.16915 | 73.9165 | 440 | 35.85 | 210
5485 | ZACA 1102CB | 182681102 | ZACA 1102 | CB | FALSE | 33441.4577 | 25226.3338 | 15.6783 | 190 | 6.5983e-05 | 2589 | 2246.0111 | 394 | 0.16908 | 32.1248 | 441 | 5.92 | 477
2709 | CHOLAME 2102X10 | 182562102 | CHOLAME 2102 | X10 | FALSE | 70912.2192 | 34475.596 | 21.4267 | 156 | 7.3071e-05 | 2393 | 2615.2408 | 327 | 0.16893 | 26.3532 | 442 | 0 | 2634
2509 | HIGGINS 111051794 | 152691110 | HIGGINS 1110 | 51794 | FALSE | 6308.4167 | 6303.8446 | 3.9179 | 32 | 0.00021523 | 339 | 651.61 | 1061 | 0.16883 | 5.4026 | 443 | 0.05 | 1924
3144 | MORGAN HILL 2105XR564 | 83242105 | MORGAN HILL 2105 | XR564 | FALSE | 11653.8006 | 9126.8572 | 5.6724 | 81 | 0.0001173 | 1241 | 1539.4612 | 583 | 0.16792 | 13.6018 | 444 | 0.06 | 1891
8832 | PEORIA 17046090 | 163781704 | PEORIA 1704 | 6090 | TRUE | 1284.821 | 879.5421 | 0.54664 | 10 | 0.00015776 | 667 | 641.9698 | 1070 | 0.16726 | 1.6726 | 445 | 0.04 | 2133
6712 | CORNING 110182846 | 103331101 | CORNING 1101 | 82846 | FALSE | 8140.1207 | 7626.8316 | 4.7401 | 61 | 4.657e-05 | 3125 | 3781.4967 | 171 | 0.16626 | 10.1421 | 446 | 0.09 | 1543
3069 | NARROWS 21052228 | 153132105 | NARROWS 2105 | 2228 | FALSE | 34201.7241 | 33727.1471 | 20.9616 | 199 | 0.0001094 | 1423 | 1826.2902 | 498 | 0.16595 | 33.0243 | 447 | 0.19 | 1187
10116 | SANTA YNEZ 1104117616 | 182721104 | SANTA YNEZ 1104 | 117616 | TRUE | 584.7856 | 298.3487 | 0.18542 | 5 | 0.00010782 | 1453 | 3364.4337 | 215 | 0.16564 | 0.82819 | 448 |  | 3494
10070 | SILVERADO 2102772792 | 43432102 | SILVERADO 2102 | 772792 | FALSE | 4440.4408 | 3782.0495 | 2.3506 | 19 | 0.00011586 | 1274 | 1705.2974 | 522 | 0.16509 | 3.1366 | 449 |  | 3485
6113 | MIDDLETOWN 1101439572 | 43141101 | MIDDLETOWN 1101 | 439572 | FALSE | 2069.8545 | 1977.3978 | 1.229 | 18 | 0.00012277 | 1136 | 1750.9686 | 514 | 0.16479 | 2.9663 | 450 |  | 3004
1940 | NORTH BRANCH 1101TS1115 | 163231101 | NORTH BRANCH 1101 | TS1115 | FALSE | 28340.5083 | 28340.5083 | 17.6137 | 147 | 6.6142e-05 | 2584 | 2220.2472 | 396 | 0.16462 | 24.1996 | 451 | 0.06 | 1872
7043 | ANDERSON 1101514412 | 103261101 | ANDERSON 1101 | 514412 | FALSE | 1675.5188 | 1659.5168 | 1.0314 | 5 | 8.0594e-05 | 2190 | 2318.4458 | 382 | 0.16405 | 0.82024 | 452 |  | 3090
7318 | PUEBLO 2102226562 | 43292102 | PUEBLO 2102 | 226562 | FALSE | 1660.7794 | 1371.9928 | 0.8527 | 7 | 8.6131e-05 | 2031 | 1632.6529 | 550 | 0.16403 | 1.1482 | 453 |  | 3116
9693 | WILDWOOD 110198896 | 103611101 | WILDWOOD 1101 | 98896 | FALSE | 8090.5275 | 8090.5275 | 5.0283 | 25 | 7.975e-05 | 2213 | 2478.9758 | 348 | 0.16402 | 4.1004 | 454 | 0.04 | 2181
8907 | SHINGLE SPRINGS 1103CB | 153651103 | SHINGLE SPRINGS 1103 | CB | FALSE | 19101.7778 | 10648.1095 | 6.6178 | 143 | 0.00016037 | 641 | 1368.6904 | 653 | 0.16378 | 23.42 | 455 | 0.24 | 1101
3737 | KESWICK 110148480 | 103451101 | KESWICK 1101 | 48480 | FALSE | 16927.9852 | 16927.9852 | 10.5208 | 125 | 0.00013445 | 937 | 1828.9756 | 497 | 0.16355 | 20.4433 | 456 | 0.7 | 806
9178 | CORNING 1102915324 | 103331102 | CORNING 1102 | 915324 | FALSE | 5487.5306 | 3584.8296 | 2.228 | 27 | 4.7601e-05 | 3097 | 3729.4821 | 179 | 0.16319 | 4.406 | 457 |  | 3321
9985 | BOLINAS 1101530 | 42261101 | BOLINAS 1101 | 530 | FALSE | 17644.1656 | 17644.1656 | 10.9659 | 23 | 0.00014892 | 752 | 1687.6433 | 526 | 0.16273 | 3.7427 | 458 | 0.71 | 801
10086 | NAPA 1102561208 | 42021102 | NAPA 1102 | 561208 | FALSE | 4547.6852 | 1347.5454 | 0.8375 | 15 | 0.0001103 | 1407 | 1867.3968 | 484 | 0.1626 | 2.439 | 459 |  | 3487
7995 | HOPLAND 110194006 | 42251101 | HOPLAND 1101 | 94006 | FALSE | 24566.5609 | 22341.6897 | 13.8855 | 112 | 0.00010255 | 1585 | 1667.7925 | 536 | 0.1626 | 18.2107 | 460 | 0.05 | 1968
5192 | HIGHLANDS 1103CB | 43361103 | HIGHLANDS 1103 | CB | FALSE | 19725.7628 | 17048.207 | 10.5955 | 144 | 0.00010337 | 1563 | 1745.3469 | 516 | 0.16238 | 23.3827 | 461 | 0.11 | 1421
10927 | SCE REFUGIO 1701CB | 188071701 | SCE REFUGIO 1701 | CB | TRUE | 3.6129 | 3.6129 | 0.0022454 | 1 | 3.2861e-05 | 3387 | 4925.3659 | 82 | 0.16185 | 0.16185 | 462 |  | 3620
1961 | NARROWS 210534069 | 153132105 | NARROWS 2105 | 34069 | FALSE | 25331.8473 | 25331.8473 | 15.7438 | 156 | 6.2676e-05 | 2694 | 2622.4246 | 326 | 0.16138 | 25.1758 | 463 | 0.09 | 1525
11018 | CLAY 110398680 | 163341103 | CLAY 1103 | 98680 | TRUE | 46.5973 | 46.5973 | 0.02896 | 1 | 7.2821e-05 | 2397 | 2215.7621 | 399 | 0.16135 | 0.16135 | 464 |  | 3628
5283 | ANDERSON 11011752 | 103261101 | ANDERSON 1101 | 1752 | FALSE | 16018.6134 | 13551.3973 | 8.4222 | 96 | 9.1598e-05 | 1854 | 2012.9288 | 453 | 0.16096 | 15.4521 | 465 | 0.04 | 2161
4672 | LOW GAP 110137498 | 192411101 | LOW GAP 1101 | 37498 | FALSE | 26197.7415 | 26197.7415 | 16.282 | 129 | 0.00018072 | 507 | 890.6369 | 887 | 0.16073 | 20.7336 | 466 | 0.07 | 1723
1841 | NARROWS 21057203 | 153132105 | NARROWS 2105 | 7203 | FALSE | 30305.2229 | 29904.6733 | 18.5859 | 197 | 9.5139e-05 | 1761 | 1859.3118 | 489 | 0.16043 | 31.6051 | 467 | 0.19 | 1194
652 | MIDDLETOWN 110148212 | 43141101 | MIDDLETOWN 1101 | 48212 | FALSE | 17385.8137 | 17215.2669 | 10.6994 | 110 | 0.00014482 | 804 | 1204.0224 | 729 | 0.1603 | 17.6327 | 468 | 18.57 | 319
1128 | SAN MIGUEL 1106605393 | 182661106 | SAN MIGUEL 1106 | 605393 | FALSE | 40299.6716 | 33375.8865 | 20.7432 | 119 | 6.0131e-05 | 2768 | 2777.2648 | 302 | 0.15998 | 19.0373 | 469 |  | 2710
3473 | COTTONWOOD 11011610 | 102931101 | COTTONWOOD 1101 | 1610 | FALSE | 61821.9357 | 61821.9357 | 38.4226 | 295 | 4.3413e-05 | 3203 | 3907.4677 | 156 | 0.15996 | 47.1875 | 470 | 0.13 | 1340
1571 | SAN MIGUEL 1106428314 | 182661106 | SAN MIGUEL 1106 | 428314 | FALSE | 29650.5939 | 23673.0872 | 14.7129 | 73 | 6.2949e-05 | 2680 | 2640.9062 | 321 | 0.15993 | 11.675 | 471 |  | 2732
6359 | FROGTOWN 1702592404 | 163451702 | FROGTOWN 1702 | 592404 | FALSE | 2658.3381 | 2642.3361 | 1.6422 | 20 | 0.00017009 | 563 | 1297.0483 | 685 | 0.15963 | 3.1926 | 472 |  | 3024
7337 | WYANDOTTE 110738438 | 102911107 | WYANDOTTE 1107 | 38438 | FALSE | 27128.309 | 27128.309 | 16.8604 | 181 | 9.156e-05 | 1855 | 1679.673 | 529 | 0.15947 | 28.8637 | 473 | 0.08 | 1665
932 | MIDDLETOWN 1101548 | 43141101 | MIDDLETOWN 1101 | 548 | FALSE | 45554.629 | 44099.7789 | 27.4082 | 298 | 0.00022053 | 318 | 593.8352 | 1108 | 0.15935 | 47.4878 | 474 | 94.8 | 26
9379 | SUNOL 11018721 | 14241101 | SUNOL 1101 | 8721 | FALSE | 4901.8588 | 4400.8399 | 2.7351 | 29 | 5.0888e-05 | 3017 | 2918.1731 | 285 | 0.1593 | 4.6198 | 475 | 0.04 | 2186
1763 | RED BLUFF 110451238 | 103541104 | RED BLUFF 1104 | 51238 | FALSE | 63137.7388 | 63137.7388 | 39.2404 | 335 | 5.1642e-05 | 3004 | 2984.3431 | 269 | 0.15926 | 53.3509 | 476 | 2.31 | 614
1814 | CLOVERDALE 110184088 | 42821101 | CLOVERDALE 1101 | 84088 | FALSE | 28026.8017 | 25963.7603 | 16.1366 | 127 | 0.00012489 | 1101 | 1457.8018 | 614 | 0.15858 | 20.1391 | 477 |  | 2748
4306 | RAWSON 1103428534 | 103531103 | RAWSON 1103 | 428534 | FALSE | 8740.0932 | 7301.7326 | 4.5381 | 18 | 6.0557e-05 | 2760 | 3052.7595 | 263 | 0.15819 | 2.8474 | 478 |  | 2880
8922 | CLOVERDALE 1101964556 | 42821101 | CLOVERDALE 1101 | 964556 | FALSE | 8160.0956 | 8116.5647 | 5.0445 | 31 | 0.00010503 | 1527 | 1599.6673 | 562 | 0.15803 | 4.8988 | 479 |  | 3279
7447 | BELL 1109CB | 152701109 | BELL 1109 | CB | TRUE | 5601.5402 | 484.8416 | 0.30133 | 53 | 0.00031144 | 116 | 533.425 | 1167 | 0.15794 | 8.3708 | 480 | 0.06 | 1805
5391 | FITCH MOUNTAIN 111324918 | 42751113 | FITCH MOUNTAIN 1113 | 24918 | FALSE | 8843.8557 | 8843.8557 | 5.4965 | 49 | 0.00017491 | 529 | 1042.2333 | 799 | 0.1575 | 7.7177 | 481 | 40.7 | 183
6800 | GEYSERVILLE 1101705777 | 42891101 | GEYSERVILLE 1101 | 705777 | FALSE | 9890.0744 | 9890.0744 | 6.1467 | 46 | 0.00010551 | 1505 | 1615.1994 | 555 | 0.15746 | 7.2434 | 482 |  | 3062
29 | CALPELLA 1101542 | 43411101 | CALPELLA 1101 | 542 | FALSE | 54014.7834 | 53958.2006 | 33.5352 | 311 | 0.00010864 | 1433 | 1525.8914 | 585 | 0.15746 | 48.9707 | 483 | 0.08 | 1662
9538 | PIT NO 1 1101CB | 103721101 | PIT NO 1 1101 | CB | FALSE | 10535.3716 | 10535.3716 | 6.5478 | 40 | 5.8247e-05 | 2827 | 2851.4073 | 292 | 0.15705 | 6.2822 | 484 | 0.03 | 2244
7813 | CLOVERDALE 1102383183 | 42821102 | CLOVERDALE 1102 | 383183 | FALSE | 23681.1054 | 23566.6207 | 14.6467 | 53 | 0.0001153 | 1293 | 1780.7074 | 509 | 0.15687 | 8.3141 | 485 |  | 3164
8188 | LAKEVILLE 1102152632 | 43371102 | LAKEVILLE 1102 | 152632 | FALSE | 3427.183 | 3099.3949 | 1.9263 | 13 | 5.6437e-05 | 2875 | 2775.5237 | 304 | 0.15681 | 2.0385 | 486 |  | 3200
5065 | WOODACRE 11011456 | 43021101 | WOODACRE 1101 | 1456 | FALSE | 6155.4627 | 6155.4627 | 3.8256 | 46 | 0.00024152 | 242 | 701.6004 | 1021 | 0.15596 | 7.1739 | 487 | 25.79 | 270
5726 | POINT MORETTI 11015104 | 82931101 | POINT MORETTI 1101 | 5104 | FALSE | 2898.3737 | 2898.3737 | 1.8014 | 11 | 0.00010952 | 1422 | 1407.1508 | 634 | 0.15579 | 1.7137 | 488 | 0.08 | 1654
3142 | MOLINO 110279306 | 42571102 | MOLINO 1102 | 79306 | FALSE | 13157.0108 | 6087.9659 | 3.7837 | 73 | 0.00011173 | 1374 | 1345.2863 | 664 | 0.15551 | 11.352 | 489 | 5.6 | 482
10072 | BALCH NO 1 1101R372 | 252501101 | BALCH NO 1 1101 | R372 | FALSE | 6703.9319 | 6703.9319 | 4.1665 | 14 | 2.9441e-05 | 3432 | 4227.7566 | 136 | 0.15539 | 2.1754 | 490 | 0 | 2626
1776 | TIVY VALLEY 1107869946 | 252941107 | TIVY VALLEY 1107 | 869946 | FALSE | 47850.9 | 47850.9 | 29.7395 | 197 | 2.1689e-05 | 3527 | 7360.2383 | 8 | 0.15534 | 30.6024 | 491 | 4.76 | 507
9099 | BELL 1110946229 | 152701110 | BELL 1110 | 946229 | TRUE | 3345.1938 | 352.3912 | 0.21901 | 27 | 9.1153e-05 | 1875 | 1903.3963 | 476 | 0.15489 | 4.1819 | 492 |  | 3308
11045 | CLARK ROAD 1101CB | 103091101 | CLARK ROAD 1101 | CB | TRUE | 33.3215 | 28.7495 | 0.017868 | 2 | 0.00010268 | 1578 | 1672.4211 | 534 | 0.15464 | 0.30929 | 493 |  | 3632
1243 | SHINGLE SPRINGS 110419502 | 153651104 | SHINGLE SPRINGS 1104 | 19502 | FALSE | 92686.5675 | 72356.9682 | 44.9701 | 672 | 0.00010455 | 1541 | 1716.1429 | 520 | 0.15447 | 103.8019 | 494 | 25.98 | 269
3579 | WILLITS 1102CB | 42661102 | WILLITS 1102 | CB | FALSE | 15673.7726 | 8550.61 | 5.3142 | 114 | 0.00011244 | 1357 | 1000.9631 | 834 | 0.15412 | 17.5695 | 495 | 0.03 | 2253
6413 | UKIAH 1114408 | 42771114 | UKIAH 1114 | 408 | FALSE | 61335.3992 | 60046.2209 | 37.319 | 280 | 0.00011339 | 1336 | 1624.3846 | 553 | 0.15401 | 43.1236 | 496 | 0.16 | 1258
4125 | SAND CREEK 11037420 | 254601103 | SAND CREEK 1103 | 7420 | FALSE | 37320.8645 | 37320.8645 | 23.1951 | 263 | 2.746e-05 | 3465 | 5752.6874 | 39 | 0.15397 | 40.4954 | 497 | 0.11 | 1450
6897 | SALMON CREEK 110188998 | 43161101 | SALMON CREEK 1101 | 88998 | FALSE | 22218.0314 | 12794.9324 | 7.9521 | 116 | 8.749e-05 | 2000 | 1675.3538 | 531 | 0.15352 | 17.8079 | 498 | 12.75 | 368
4452 | SILVERADO 2102942170 | 43432102 | SILVERADO 2102 | 942170 | FALSE | 14564.2628 | 5038.647 | 3.1315 | 99 | 8.0364e-05 | 2195 | 1848.528 | 490 | 0.15348 | 15.1945 | 499 |  | 2892
59 | VACAVILLE 1111CB | 63601111 | VACAVILLE 1111 | CB | FALSE | 19525.0238 | 11777.3852 | 7.3197 | 154 | 0.00010262 | 1582 | 1549.2867 | 579 | 0.15336 | 23.6178 | 500 | 0.1 | 1453
5605 | SANTA YNEZ 1101Y52 | 182721101 | SANTA YNEZ 1101 | Y52 | FALSE | 33466.442 | 31529.2091 | 19.5955 | 141 | 6.2219e-05 | 2713 | 2469.9036 | 349 | 0.15332 | 21.6184 | 501 | 0.22 | 1124
4437 | STILLWATER 1102CB | 103561102 | STILLWATER 1102 | CB | FALSE | 40316.4241 | 40301.3395 | 25.0474 | 275 | 0.00012985 | 1011 | 1360.5287 | 658 | 0.15318 | 42.1242 | 502 | 0.14 | 1317
3264 | BEAR VALLEY 21059480 | 252192105 | BEAR VALLEY 2105 | 9480 | FALSE | 19971.3977 | 19971.3977 | 12.4123 | 80 | 7.4134e-05 | 2352 | 2457.1272 | 350 | 0.15314 | 12.251 | 503 | 0.05 | 1946
1519 | FROGTOWN 17021573 | 163451702 | FROGTOWN 1702 | 1573 | FALSE | 29066.997 | 29066.997 | 18.0653 | 156 | 6.9197e-05 | 2500 | 1984.6936 | 458 | 0.15282 | 23.8402 | 504 | 0.09 | 1514
1732 | NARROWS 21022220 | 153132102 | NARROWS 2102 | 2220 | FALSE | 45533.9477 | 44226.4373 | 27.4869 | 266 | 0.00015667 | 676 | 1115.795 | 768 | 0.15235 | 40.5244 | 505 | 0.28 | 1037
2529 | FULTON 1102287172 | 42561102 | FULTON 1102 | 287172 | FALSE | 42975.8424 | 32888.5181 | 20.4403 | 258 | 0.00014341 | 820 | 1064.6586 | 789 | 0.15216 | 39.2578 | 506 | 0.11 | 1432
9038 | OTTER 11022012 | 182941102 | OTTER 1102 | 2012 | FALSE | 16177.0749 | 14813.8509 | 9.2069 | 64 | 7.8985e-05 | 2236 | 2049.1767 | 445 | 0.15189 | 9.7211 | 507 | 0.03 | 2261
6205 | OILFIELDS 1103N48 | 182391103 | OILFIELDS 1103 | N48 | FALSE | 76703.6711 | 76703.6711 | 47.6716 | 292 | 5.999e-05 | 2778 | 2624.8703 | 325 | 0.15188 | 44.3489 | 508 | 0.11 | 1419
6912 | BANGOR 1101301886 | 103191101 | BANGOR 1101 | 301886 | FALSE | 12466.9499 | 4239.6365 | 2.635 | 90 | 8.8332e-05 | 1976 | 1844.2972 | 493 | 0.15165 | 13.6484 | 509 |  | 3073
10865 | PASO ROBLES 1103N04 | 182611103 | PASO ROBLES 1103 | N04 | TRUE | 859.5841 | 859.5841 | 0.53424 | 4 | 0.00013464 | 932 | 1420.9296 | 631 | 0.1516 | 0.60641 | 510 | 10.35 | 398
10126 | WINDSOR 1103701650 | 43501103 | WINDSOR 1103 | 701650 | FALSE | 1191.0562 | 1191.0562 | 0.74025 | 12 | 0.00018462 | 478 | 500.0347 | 1199 | 0.15159 | 1.8191 | 511 |  | 3496
2118 | LUCERNE 11031280 | 43351103 | LUCERNE 1103 | 1280 | FALSE | 37796.6985 | 12933.8174 | 8.0384 | 238 | 0.00011562 | 1283 | 1326.8732 | 670 | 0.1512 | 35.9845 | 512 | 0.03 | 2282
7467 | CORRAL 110214026 | 162991102 | CORRAL 1102 | 14026 | FALSE | 16308.5206 | 16308.5206 | 10.1358 | 101 | 6.4324e-05 | 2633 | 2347.8148 | 374 | 0.15084 | 15.2344 | 513 | 3.03 | 567
2447 | SAN LUIS OBISPO 110342344 | 182631103 | SAN LUIS OBISPO 1103 | 42344 | FALSE | 17541.9825 | 15185.6709 | 9.438 | 123 | 6.005e-05 | 2772 | 2518.1117 | 341 | 0.15077 | 18.5441 | 514 | 5.29 | 491
9162 | PUTAH CREEK 1105748272 | 63681105 | PUTAH CREEK 1105 | 748272 | FALSE | 6311.5498 | 1206.1255 | 0.74961 | 26 | 6.9164e-05 | 2501 | 2825.842 | 296 | 0.15028 | 3.9074 | 515 |  | 3317
6146 | PETALUMA C 1108618 | 42631108 | PETALUMA C 1108 | 618 | FALSE | 17470.7407 | 13890.2601 | 8.6329 | 119 | 8.8705e-05 | 1961 | 1646.4565 | 544 | 0.15 | 17.8498 | 516 | 3.18 | 555
7759 | BUELLTON 1101Y26 | 183041101 | BUELLTON 1101 | Y26 | FALSE | 25494.2608 | 24411.1885 | 15.1717 | 133 | 6.226e-05 | 2711 | 2408.6488 | 359 | 0.14946 | 19.8785 | 517 | 0.08 | 1586
8614 | WILLOW CREEK 110237374 | 192171102 | WILLOW CREEK 1102 | 37374 | FALSE | 3616.7474 | 3616.7474 | 2.2478 | 9 | 0.00024971 | 217 | 652.1813 | 1060 | 0.14938 | 1.3444 | 518 | 10.97 | 392
1351 | FULTON 11024522 | 42561102 | FULTON 1102 | 4522 | FALSE | 19482.3353 | 14178.9489 | 8.8123 | 128 | 0.00013265 | 968 | 1211.0142 | 727 | 0.14919 | 19.0963 | 519 | 1.62 | 661
5116 | APPLE HILL 210251792 | 153662102 | APPLE HILL 2102 | 51792 | FALSE | 15055.1772 | 15055.1772 | 9.3569 | 99 | 0.00012104 | 1164 | 1431.6373 | 622 | 0.14914 | 14.7646 | 520 | 0.08 | 1632
2803 | ZACA 1102Y48 | 182681102 | ZACA 1102 | Y48 | FALSE | 19054.6896 | 7064.3192 | 4.3905 | 157 | 6.9914e-05 | 2475 | 2423.7326 | 357 | 0.14907 | 23.4041 | 521 | 0.03 | 2278
453 | GARBERVILLE 11011604 | 192221101 | GARBERVILLE 1101 | 1604 | FALSE | 29168.7634 | 6733.9297 | 4.1852 | 166 | 0.00022087 | 316 | 698.8592 | 1023 | 0.14905 | 24.7419 | 522 | 0.05 | 1969
10386 | CALISTOGA 1101537148 | 42711101 | CALISTOGA 1101 | 537148 | TRUE | 2468.9992 | 923.0762 | 0.5737 | 14 | 8.9697e-05 | 1921 | 711.3098 | 1014 | 0.14902 | 2.0863 | 523 |  | 3541
1087 | GRASS VALLEY 11032180 | 152031103 | GRASS VALLEY 1103 | 2180 | FALSE | 71112.0664 | 71112.0664 | 44.1964 | 444 | 8.9044e-05 | 1947 | 1832.2635 | 495 | 0.1487 | 66.0238 | 524 | 0.31 | 1000
6232 | POSO MOUNTAIN 21012181 | 253642101 | POSO MOUNTAIN 2101 | 2181 | FALSE | 38165.6009 | 27116.6383 | 16.8531 | 120 | 3.7006e-05 | 3315 | 4260.274 | 131 | 0.14869 | 17.8426 | 525 | 0.05 | 2017
1083 | CLARK ROAD 11022044 | 103091102 | CLARK ROAD 1102 | 2044 | FALSE | 20271.6961 | 13688.923 | 8.5077 | 67 | 0.00011519 | 1295 | 1533.5317 | 584 | 0.14865 | 9.9595 | 526 | 0.03 | 2330
1119 | MERCED FALLS 110287352 | 252811102 | MERCED FALLS 1102 | 87352 | FALSE | 42830.7404 | 42830.7404 | 26.6195 | 215 | 7.6529e-05 | 2294 | 2120.5795 | 420 | 0.14862 | 31.9523 | 527 | 0.03 | 2333
3359 | WISE 1102307494 | 152271102 | WISE 1102 | 307494 | FALSE | 54418.6325 | 49958.7477 | 31.0496 | 279 | 7.0522e-05 | 2454 | 2167.8038 | 409 | 0.14841 | 41.4062 | 528 | 3.66 | 537
8461 | PUTAH CREEK 110264044 | 63681102 | PUTAH CREEK 1102 | 64044 | FALSE | 11992.1979 | 9649.0485 | 5.9969 | 46 | 6.4018e-05 | 2645 | 2318.9503 | 380 | 0.14834 | 6.8236 | 529 | 0.92 | 747
7436 | MENLO 110212249 | 24131102 | MENLO 1102 | 12249 | FALSE | 3869.5175 | 3869.5175 | 2.4049 | 25 | 0.0001396 | 877 | 1383.6803 | 645 | 0.14826 | 3.7065 | 530 | 0.06 | 1811
170 | NORTH BRANCH 110111206 | 163231101 | NORTH BRANCH 1101 | 11206 | FALSE | 28786.4552 | 28782.1678 | 17.8882 | 146 | 5.7399e-05 | 2853 | 3353.7714 | 217 | 0.14787 | 21.5893 | 531 | 7.09 | 451
2440 | VOLTA 110180454 | 102541101 | VOLTA 1101 | 80454 | FALSE | 51836.245 | 51220.5161 | 31.8338 | 254 | 8.7906e-05 | 1985 | 1652.3048 | 542 | 0.14786 | 37.5574 | 532 | 0.09 | 1550
6322 | SALMON CREEK 1101196 | 43161101 | SALMON CREEK 1101 | 196 | FALSE | 11699.1957 | 9030.0657 | 5.6122 | 36 | 5.8544e-05 | 2820 | 2429.7049 | 356 | 0.14755 | 5.3118 | 533 | 1.88 | 635
6558 | MOLINO 110266006 | 42571102 | MOLINO 1102 | 66006 | FALSE | 14550.7056 | 14550.7056 | 9.0433 | 98 | 0.00016119 | 629 | 1078.2399 | 782 | 0.14747 | 14.4519 | 534 | 51.49 | 116
6860 | GARBERVILLE 1101CB | 192221101 | GARBERVILLE 1101 | CB | FALSE | 14152.8775 | 11300.0596 | 7.023 | 87 | 0.00030831 | 120 | 452.1633 | 1245 | 0.14742 | 12.8257 | 535 | 0.09 | 1511
2892 | WYANDOTTE 11071026 | 102911107 | WYANDOTTE 1107 | 1026 | FALSE | 44906.7347 | 36171.5421 | 22.4808 | 273 | 7.2065e-05 | 2414 | 2265.0826 | 390 | 0.14732 | 40.2177 | 536 | 0.08 | 1587
1817 | COARSEGOLD 210410110 | 254432104 | COARSEGOLD 2104 | 10110 | FALSE | 79840.1784 | 79840.1784 | 49.621 | 518 | 7.1892e-05 | 2423 | 1946.3474 | 464 | 0.1471 | 76.1986 | 537 | 0.85 | 766
5315 | GIRVAN 11011636 | 103401101 | GIRVAN 1101 | 1636 | FALSE | 29887.6303 | 29071.18 | 18.0679 | 200 | 0.00012911 | 1025 | 1282.4693 | 688 | 0.14693 | 29.387 | 538 | 0.42 | 935
7739 | OILFIELDS 1103N40 | 182391103 | OILFIELDS 1103 | N40 | FALSE | 4749.4542 | 4628.046 | 2.8763 | 23 | 7.224e-05 | 2412 | 1911.8815 | 472 | 0.14681 | 3.3766 | 539 | 0.92 | 746
1598 | COTTONWOOD 11031348 | 102931103 | COTTONWOOD 1103 | 1348 | FALSE | 51267.8367 | 46964.6472 | 29.1887 | 357 | 6.4485e-05 | 2628 | 2847.109 | 293 | 0.14666 | 52.3583 | 540 | 0.1 | 1507
2008 | OAKHURST 11015490 | 254421101 | OAKHURST 1101 | 5490 | FALSE | 40241.3391 | 40241.3391 | 25.0102 | 276 | 5.4815e-05 | 2921 | 3287.8025 | 227 | 0.14657 | 40.4521 | 541 | 31.17 | 233
6294 | OLETA 1101239062 | 163541101 | OLETA 1101 | 239062 | FALSE | 22613.4239 | 19618.6008 | 12.193 | 113 | 7.6414e-05 | 2296 | 2401.1977 | 361 | 0.14634 | 16.5367 | 542 |  | 3021
6920 | LAYTONVILLE 110268436 | 42681102 | LAYTONVILLE 1102 | 68436 | FALSE | 14664.9715 | 14664.9715 | 9.1143 | 45 | 0.00011581 | 1278 | 1690.836 | 525 | 0.14627 | 6.582 | 543 | 3.52 | 544
1698 | GARBERVILLE 11022010 | 192221102 | GARBERVILLE 1102 | 2010 | FALSE | 10727.9171 | 10727.9171 | 6.6674 | 39 | 0.00053737 | 26 | 277.3564 | 1477 | 0.14585 | 5.6882 | 544 | 0.08 | 1579
2911 | SHINGLE SPRINGS 210819762 | 153652108 | SHINGLE SPRINGS 2108 | 19762 | FALSE | 8713.8007 | 7078.7756 | 4.3995 | 72 | 0.00017135 | 554 | 1134.0874 | 762 | 0.14549 | 10.4755 | 545 | 0.25 | 1082
2598 | ELK CREEK 11012008 | 102781101 | ELK CREEK 1101 | 2008 | FALSE | 29196.2282 | 9225.9589 | 5.734 | 154 | 5.6038e-05 | 2886 | 2966.3445 | 274 | 0.14517 | 22.3567 | 546 | 2.46 | 601
2127 | OILFIELDS 1103N44 | 182391103 | OILFIELDS 1103 | N44 | FALSE | 29207.7388 | 29207.7388 | 18.1527 | 109 | 8.2092e-05 | 2149 | 1862.5151 | 486 | 0.14496 | 15.8008 | 547 | 0.19 | 1171
381 | MOUNTAIN QUARRIES 21011102 | 152282101 | MOUNTAIN QUARRIES 2101 | 1102 | FALSE | 69889.6015 | 69889.6015 | 43.4367 | 431 | 0.00010803 | 1451 | 1375.9559 | 650 | 0.14479 | 62.4048 | 548 | 0.21 | 1154
3913 | CORNING 110164090 | 103331101 | CORNING 1101 | 64090 | FALSE | 21993.72 | 21993.72 | 13.6692 | 170 | 4.4336e-05 | 3181 | 3248.9701 | 228 | 0.1444 | 24.5486 | 549 | 4.94 | 501
2481 | BROWNS VALLEY 11011268 | 152921101 | BROWNS VALLEY 1101 | 1268 | FALSE | 17550.3384 | 17538.5447 | 10.9003 | 106 | 8.5846e-05 | 2035 | 1744.856 | 517 | 0.14435 | 15.3013 | 550 | 0.13 | 1351
948 | MARIPOSA 21029590 | 254452102 | MARIPOSA 2102 | 9590 | FALSE | 58387.0707 | 58387.0707 | 36.2878 | 387 | 6.1765e-05 | 2727 | 2433.9636 | 353 | 0.144 | 55.7277 | 551 | 0.28 | 1045
4109 | TEMPLETON 2113A60 | 183052113 | TEMPLETON 2113 | A60 | FALSE | 14423.3233 | 11709.0954 | 7.2773 | 88 | 8.0147e-05 | 2202 | 2043.3402 | 447 | 0.14391 | 12.6644 | 552 | 1.69 | 651
9361 | CLOVERDALE 1102429006 | 42821102 | CLOVERDALE 1102 | 429006 | FALSE | 3229.4467 | 3213.4446 | 1.9972 | 23 | 0.00015434 | 701 | 805.9602 | 934 | 0.1436 | 3.3029 | 553 | 0.04 | 2192
429 | COTTONWOOD 11021578 | 102931102 | COTTONWOOD 1102 | 1578 | FALSE | 56424.6884 | 48498.4276 | 30.142 | 269 | 5.3137e-05 | 2963 | 2721.7009 | 308 | 0.14355 | 38.6147 | 554 | 0.07 | 1761
3755 | INDIAN FLAT 1104CB | 252691104 | INDIAN FLAT 1104 | CB | FALSE | 20557.4413 | 20557.4413 | 12.7765 | 85 | 0.0001276 | 1055 | 1467.6776 | 609 | 0.14347 | 12.1951 | 555 | 0.15 | 1305
5039 | OREGON TRAIL 11031448 | 103521103 | OREGON TRAIL 1103 | 1448 | FALSE | 49484.9793 | 49484.9793 | 30.7551 | 232 | 9.5357e-05 | 1749 | 1437.1719 | 620 | 0.14347 | 33.2848 | 556 | 0.06 | 1912
5385 | MONTICELLO 110137384 | 43051101 | MONTICELLO 1101 | 37384 | FALSE | 15082.1187 | 15082.1187 | 9.3736 | 71 | 6.7163e-05 | 2554 | 2257.655 | 391 | 0.14324 | 10.17 | 557 | 0.13 | 1350
9323 | POSO MOUNTAIN 21013990 | 253642101 | POSO MOUNTAIN 2101 | 3990 | FALSE | 8945.4958 | 6963.5326 | 4.3279 | 25 | 3.4486e-05 | 3361 | 3780.3852 | 172 | 0.14297 | 3.5744 | 558 | 0.05 | 1957
8609 | PETALUMA C 1108636 | 42631108 | PETALUMA C 1108 | 636 | FALSE | 15178.9816 | 15178.9816 | 9.4338 | 108 | 0.00010078 | 1628 | 1486.0094 | 600 | 0.14279 | 15.4213 | 559 | 5.46 | 486
9301 | VOLTA 110165764 | 102541101 | VOLTA 1101 | 65764 | FALSE | 16669.4005 | 16669.4005 | 10.3601 | 34 | 4.7811e-05 | 3096 | 3350.0688 | 218 | 0.1423 | 4.8382 | 560 | 0.03 | 2268
10478 | STONE CORRAL 1110189488 | 252921110 | STONE CORRAL 1110 | 189488 | FALSE | 1343.2605 | 1327.2585 | 0.8249 | 8 | 2.6518e-05 | 3478 | 5673.1262 | 44 | 0.14211 | 1.1369 | 561 |  | 3556
1096 | CABRILLO 1103Y12 | 183101103 | CABRILLO 1103 | Y12 | FALSE | 49636.2362 | 42701.7878 | 26.5393 | 274 | 4.9026e-05 | 3063 | 2917.17 | 286 | 0.14205 | 38.9225 | 562 | 31.53 | 230
9878 | CEDAR CREEK 1101451856 | 103321101 | CEDAR CREEK 1101 | 451856 | TRUE | 105.147 | 105.147 | 0.065349 | 2 | 5.0483e-05 | 3022 | 2807.0375 | 299 | 0.14172 | 0.28345 | 563 |  | 3442
9745 | TASSAJARA 21126392 | 14662112 | TASSAJARA 2112 | 6392 | FALSE | 8838.9848 | 8838.9848 | 5.4935 | 37 | 7.9657e-05 | 2215 | 1801.3357 | 505 | 0.14162 | 5.2399 | 564 | 16.9 | 336
4697 | CALISTOGA 1101242919 | 42711101 | CALISTOGA 1101 | 242919 | FALSE | 2111.493 | 2111.493 | 1.3123 | 15 | 0.00019735 | 407 | 815.191 | 928 | 0.14151 | 2.1226 | 565 |  | 2911
5376 | FORT SEWARD 1121CB | 192321121 | FORT SEWARD 1121 | CB | FALSE | 14807.5224 | 14807.5224 | 9.2029 | 54 | 0.00019854 | 400 | 804.6312 | 935 | 0.14139 | 7.6353 | 566 | 0.07 | 1742
4876 | SISQUOC 1102M54 | 182811102 | SISQUOC 1102 | M54 | FALSE | 48740.6445 | 31884.2274 | 19.8162 | 166 | 5.3034e-05 | 2966 | 2348.1035 | 373 | 0.14114 | 23.4289 | 567 | 0.02 | 2478
4881 | LINCOLN 11042070 | 153701104 | LINCOLN 1104 | 2070 | FALSE | 46879.1188 | 28951.6433 | 17.9936 | 303 | 7.9201e-05 | 2227 | 1863.8372 | 485 | 0.14111 | 42.7554 | 568 | 2.76 | 584
8866 | SAN RAMON 2101CB | 14232101 | SAN RAMON 2101 | CB | FALSE | 1579.2012 | 1277.3495 | 0.79388 | 11 | 0.0001171 | 1244 | 1362.5146 | 655 | 0.14108 | 1.5519 | 569 | 0.61 | 848
10487 | HIGGINS 1107746082 | 152691107 | HIGGINS 1107 | 746082 | FALSE | 1306.1318 | 1306.1318 | 0.81177 | 6 | 0.00011547 | 1287 | 1442.5612 | 617 | 0.14016 | 0.84097 | 570 | 0.11 | 1442
3139 | WILLITS 11044650 | 42661104 | WILLITS 1104 | 4650 | FALSE | 9890.161 | 6190.488 | 3.8474 | 80 | 0.0001146 | 1305 | 915.7398 | 878 | 0.14007 | 11.2058 | 571 | 0.03 | 2344
474 | COTTONWOOD 11031616 | 102931103 | COTTONWOOD 1103 | 1616 | FALSE | 79228.8196 | 75536.2374 | 46.9461 | 454 | 5.1839e-05 | 2998 | 2965.2949 | 276 | 0.13915 | 63.1735 | 572 | 3.66 | 538
4424 | POSO MOUNTAIN 21014456 | 253642101 | POSO MOUNTAIN 2101 | 4456 | FALSE | 37862.2156 | 37862.2156 | 23.5315 | 102 | 2.7821e-05 | 3462 | 5239.6007 | 58 | 0.13881 | 14.1582 | 573 | 0.11 | 1440
7546 | LAYTONVILLE 11022502 | 42681102 | LAYTONVILLE 1102 | 2502 | FALSE | 28650.0789 | 28650.0789 | 17.8061 | 80 | 0.00011917 | 1201 | 1243.1177 | 705 | 0.13859 | 11.0874 | 574 | 0.04 | 2183
7849 | BEAR VALLEY 21014160 | 252192101 | BEAR VALLEY 2101 | 4160 | FALSE | 36723.9834 | 36723.9834 | 22.8241 | 192 | 7.1016e-05 | 2443 | 2062.9169 | 441 | 0.13839 | 26.57 | 575 | 0.07 | 1759
10064 | WILLOW PASS 1101152874 | 13911101 | WILLOW PASS 1101 | 152874 | TRUE | 1306.3422 | 982.3028 | 0.61051 | 10 | 6.4919e-05 | 2611 | 2044.3409 | 446 | 0.13803 | 1.3803 | 576 |  | 3483
2621 | LINCOLN 1101186060 | 153701101 | LINCOLN 1101 | 186060 | FALSE | 24068.765 | 17542.5963 | 10.9028 | 161 | 0.00011716 | 1242 | 1235.1524 | 709 | 0.13732 | 22.1085 | 577 |  | 2791
5254 | SHINGLE SPRINGS 21092679 | 153652109 | SHINGLE SPRINGS 2109 | 2679 | FALSE | 11435.2637 | 11435.2637 | 7.1071 | 70 | 6.4611e-05 | 2619 | 2176.5839 | 406 | 0.13732 | 9.6123 | 578 | 23.85 | 281
3959 | SILVERADO 210234959 | 43432102 | SILVERADO 2102 | 34959 | FALSE | 42625.8356 | 41473.2756 | 25.7758 | 205 | 7.1759e-05 | 2428 | 1907.4668 | 473 | 0.13657 | 27.9958 | 579 | 0.46 | 910
4389 | VOLTA 11011516 | 102541101 | VOLTA 1101 | 1516 | FALSE | 41402.7558 | 40856.6045 | 25.3925 | 123 | 9.2444e-05 | 1832 | 1638.3577 | 549 | 0.13616 | 16.7471 | 580 | 0.06 | 1821
9812 | CURTIS 170411300 | 163351704 | CURTIS 1704 | 11300 | FALSE | 5912.6947 | 5912.6947 | 3.6748 | 41 | 0.00013924 | 881 | 1480.6406 | 604 | 0.1361 | 5.5803 | 581 | 0.19 | 1177
4676 | NARROWS 210551582 | 153132105 | NARROWS 2105 | 51582 | FALSE | 15330.2671 | 15330.2671 | 9.5278 | 105 | 0.00014185 | 842 | 981.2465 | 843 | 0.13574 | 14.2523 | 582 | 0.04 | 2150
430 | TEJON 1102732836 | 252931102 | TEJON 1102 | 732836 | FALSE | 24952.5776 | 18788.6293 | 11.6772 | 154 | 4.1312e-05 | 3239 | 3303.5879 | 224 | 0.1353 | 20.8364 | 583 |  | 2673
4932 | MONTICELLO 1101720 | 43051101 | MONTICELLO 1101 | 720 | FALSE | 13087.7745 | 10923.6575 | 6.7891 | 70 | 6.3429e-05 | 2663 | 2299.4316 | 384 | 0.1353 | 9.4707 | 584 | 2.79 | 580
6310 | RIO DELL 11024230 | 192251102 | RIO DELL 1102 | 4230 | FALSE | 36923.3874 | 36847.6248 | 22.9009 | 59 | 0.00036561 | 80 | 373.6796 | 1331 | 0.13512 | 7.9721 | 585 | 0.02 | 2536
517 | CLARKSVILLE 210413352 | 153612104 | CLARKSVILLE 2104 | 13352 | FALSE | 58907.8743 | 55896.819 | 34.7401 | 409 | 0.00012489 | 1100 | 1100.974 | 774 | 0.13486 | 55.1568 | 586 | 30.41 | 238
7402 | MARIPOSA 2102594143 | 254452102 | MARIPOSA 2102 | 594143 | TRUE | 6633.044 | 814.5641 | 0.50625 | 60 | 9.5762e-05 | 1734 | 729.5737 | 990 | 0.13461 | 8.0769 | 587 |  | 3123
19 | CLEAR LAKE 1101406 | 42141101 | CLEAR LAKE 1101 | 406 | FALSE | 53036.2911 | 19984.6537 | 12.4205 | 312 | 8.8388e-05 | 1975 | 1508.2873 | 594 | 0.1343 | 41.9011 | 588 | 0.13 | 1362
4720 | DUNLAP 11027849F | 254061102 | DUNLAP 1102 | 7849F | FALSE | 13949.6344 | 13949.6344 | 8.6698 | 61 | 3.1633e-05 | 3406 | 5019.3612 | 73 | 0.13395 | 8.1711 | 589 | 0.04 | 2222
6125 | JESSUP 1103348657 | 103441103 | JESSUP 1103 | 348657 | FALSE | 3761.8937 | 3253.8359 | 2.0223 | 29 | 8.3622e-05 | 2107 | 2006.4651 | 455 | 0.13388 | 3.8825 | 590 |  | 3007
9100 | BANGOR 1101870548 | 103191101 | BANGOR 1101 | 870548 | FALSE | 8185.9487 | 8185.9487 | 5.0876 | 56 | 0.00010519 | 1515 | 1377.0688 | 649 | 0.13326 | 7.4625 | 591 |  | 3309
7774 | RED BLUFF 110176020 | 103541101 | RED BLUFF 1101 | 76020 | FALSE | 23407.8426 | 15031.7581 | 9.3423 | 137 | 5.4998e-05 | 2910 | 2512.6527 | 342 | 0.13318 | 18.2456 | 592 | 0.45 | 918
5975 | HARTLEY 11011306 | 43211101 | HARTLEY 1101 | 1306 | FALSE | 19638.9419 | 15260.277 | 9.4843 | 117 | 9.0495e-05 | 1898 | 1507.2616 | 595 | 0.13303 | 15.5648 | 593 | 0.07 | 1743
3100 | GARBERVILLE 11022540 | 192221102 | GARBERVILLE 1102 | 2540 | FALSE | 28748.5934 | 26122.3431 | 16.2351 | 135 | 0.00054969 | 24 | 203.3955 | 1636 | 0.13296 | 17.9496 | 594 | 0.02 | 2424
9542 | OLETA 1102CB | 163541102 | OLETA 1102 | CB | TRUE | 1312.9371 | 596.6183 | 0.3708 | 11 | 0.00014984 | 739 | 1023.6412 | 812 | 0.13274 | 1.4601 | 595 | 0.08 | 1591
6900 | SALT SPRINGS 210110416 | 163692101 | SALT SPRINGS 2101 | 10416 | FALSE | 1110.1976 | 1110.1976 | 0.68999 | 7 | 0.00010788 | 1452 | 1426.8175 | 628 | 0.1325 | 0.92748 | 596 | 0.02 | 2491
1019 | HOPLAND 1101770 | 42251101 | HOPLAND 1101 | 770 | FALSE | 24751.8286 | 13838.1959 | 8.6005 | 110 | 0.00012303 | 1134 | 1361.4118 | 656 | 0.13217 | 14.5382 | 597 | 0.02 | 2513
9774 | WILDWOOD 1101384582 | 103611101 | WILDWOOD 1101 | 384582 | FALSE | 7304.3535 | 7304.3535 | 4.5397 | 8 | 5.1941e-05 | 2994 | 4044.7807 | 147 | 0.13184 | 1.0547 | 598 |  | 3417
6290 | WYANDOTTE 110796390 | 102911107 | WYANDOTTE 1107 | 96390 | FALSE | 16282.4885 | 13753.525 | 8.5479 | 124 | 0.00016254 | 620 | 924.5376 | 871 | 0.13125 | 16.2749 | 599 | 0.12 | 1378
8217 | VINEYARD 2110CB | 14502110 | VINEYARD 2110 | CB | FALSE | 16260.0032 | 8994.5064 | 5.5901 | 86 | 9.3599e-05 | 1807 | 1513.1588 | 589 | 0.1308 | 11.2491 | 600 | 0.04 | 2129
7155 | PEORIA 1701CB | 163781701 | PEORIA 1701 | CB | FALSE | 14117.7933 | 14117.7933 | 8.7743 | 70 | 8.3932e-05 | 2095 | 1625.1549 | 551 | 0.13063 | 9.1442 | 601 | 0.03 | 2355
1707 | HIGGINS 11039753 | 152691103 | HIGGINS 1103 | 9753 | FALSE | 3306.1166 | 3306.1166 | 2.0548 | 23 | 6.1494e-05 | 2733 | 2174.098 | 407 | 0.13059 | 3.0036 | 602 | 0.08 | 1584
10679 | COVELO 1101627416 | 43061101 | COVELO 1101 | 627416 | TRUE | 5034.3822 | 971.5124 | 0.6038 | 14 | 9.4498e-05 | 1779 | 1192.7699 | 735 | 0.13024 | 1.8234 | 603 |  | 3590
2248 | CORRAL 110313474 | 162991103 | CORRAL 1103 | 13474 | FALSE | 11606.5963 | 4726.1259 | 2.9373 | 99 | 9.8916e-05 | 1672 | 1472.7962 | 605 | 0.13001 | 12.8713 | 604 | 1.54 | 666
6056 | MARIPOSA 2101309438 | 254452101 | MARIPOSA 2101 | 309438 | FALSE | 13011.7309 | 5938.6322 | 3.6909 | 93 | 0.00010698 | 1474 | 1153.73 | 754 | 0.12966 | 12.0584 | 605 |  | 3000
5806 | COLUMBIA HILL 11012212 | 152471101 | COLUMBIA HILL 1101 | 2212 | FALSE | 14695.9754 | 14695.9754 | 9.1336 | 76 | 0.00022108 | 315 | 358.4844 | 1358 | 0.12922 | 9.8207 | 606 | 41.81 | 174
5628 | PUEBLO 11041304 | 43291104 | PUEBLO 1104 | 1304 | FALSE | 30935.6957 | 30935.6957 | 19.2267 | 175 | 7.3325e-05 | 2386 | 1973.0848 | 460 | 0.12902 | 22.578 | 607 | 0.29 | 1031
5578 | VASCO 1102886522 | 13751102 | VASCO 1102 | 886522 | FALSE | 30828.6552 | 10908.527 | 6.7797 | 154 | 6.1458e-05 | 2736 | 2215.6632 | 400 | 0.12899 | 19.8644 | 608 |  | 2965
2390 | WYANDOTTE 11091520 | 102911109 | WYANDOTTE 1109 | 1520 | FALSE | 31725.4009 | 6700.2969 | 4.1643 | 230 | 0.00011878 | 1212 | 1243.3344 | 704 | 0.1287 | 29.6011 | 609 | 0.04 | 2162
2104 | LINCOLN 11045391 | 153701104 | LINCOLN 1104 | 5391 | FALSE | 1530.1829 | 1530.1829 | 0.95101 | 7 | 4.9284e-05 | 3055 | 2595.0683 | 333 | 0.12868 | 0.90075 | 610 | 2.85 | 575
826 | TASSAJARA 210419042 | 14662104 | TASSAJARA 2104 | 19042 | FALSE | 13701.0778 | 10069.7209 | 6.2584 | 89 | 0.00010259 | 1584 | 1548.81 | 581 | 0.12861 | 11.4466 | 611 | 0.17 | 1229
7172 | FITCH MOUNTAIN 1113356 | 42751113 | FITCH MOUNTAIN 1113 | 356 | FALSE | 24352.0152 | 17245.1485 | 10.7179 | 136 | 0.00012922 | 1022 | 991.1123 | 839 | 0.12847 | 17.4723 | 612 | 8.54 | 423
761 | BANGOR 11017446 | 103191101 | BANGOR 1101 | 7446 | FALSE | 69991.8942 | 69991.8942 | 43.5002 | 427 | 0.00013367 | 949 | 983.1088 | 842 | 0.12828 | 54.7764 | 613 | 0.18 | 1220
9800 | CALISTOGA 110135588 | 42711101 | CALISTOGA 1101 | 35588 | FALSE | 4954.8551 | 4954.8551 | 3.0795 | 18 | 9.2798e-05 | 1827 | 1278.0574 | 690 | 0.12786 | 2.3016 | 614 | 0.6 | 851
9664 | PASO ROBLES 110359763 | 182611103 | PASO ROBLES 1103 | 59763 | FALSE | 4532.1933 | 4532.1933 | 2.8168 | 30 | 5.4981e-05 | 2912 | 2480.207 | 346 | 0.12716 | 3.8149 | 615 | 2.26 | 616
5583 | RED BLUFF 11031702 | 103541103 | RED BLUFF 1103 | 1702 | FALSE | 29294.348 | 26958.2044 | 16.7546 | 177 | 4.2191e-05 | 3220 | 3360.288 | 216 | 0.12716 | 22.5069 | 616 | 0.14 | 1332
4955 | WILLITS 1104188268 | 42661104 | WILLITS 1104 | 188268 | FALSE | 8709.5262 | 6867.4982 | 4.2682 | 66 | 0.00013545 | 924 | 756.6199 | 968 | 0.1264 | 8.3425 | 617 |  | 2932
9342 | SAND CREEK 11037823F | 254601103 | SAND CREEK 1103 | 7823F | FALSE | 7527.4054 | 7527.4054 | 4.6783 | 49 | 2.6117e-05 | 3486 | 5142.2922 | 63 | 0.12636 | 6.1917 | 618 | 0.06 | 1848
7895 | PEORIA 1704877670 | 163781704 | PEORIA 1704 | 877670 | FALSE | 10595.2996 | 10595.2996 | 6.585 | 28 | 7.9345e-05 | 2225 | 1606.4027 | 561 | 0.12626 | 3.5352 | 619 | 0.06 | 1803
1593 | MENLO 1102W80 | 24131102 | MENLO 1102 | W80 | FALSE | 30507.2399 | 30491.2345 | 18.9504 | 129 | 0.00012461 | 1105 | 990.5879 | 840 | 0.12598 | 16.2519 | 620 | 0.26 | 1062
9134 | SAN LUIS OBISPO 1104350030 | 182631104 | SAN LUIS OBISPO 1104 | 350030 | FALSE | 14009.015 | 9325.238 | 5.7957 | 107 | 0.00012847 | 1039 | 957.5657 | 855 | 0.12598 | 13.4795 | 621 |  | 3314
10634 | EDENVALE 2107288980 | 82952107 | EDENVALE 2107 | 288980 | TRUE | 1137.5268 | 532.3299 | 0.33085 | 6 | 5.3751e-05 | 2947 | 2359.4228 | 370 | 0.12531 | 0.75188 | 622 |  | 3583
8835 | SOLEDAD 2102955138 | 182052102 | SOLEDAD 2102 | 955138 | FALSE | 4475.7732 | 4227.5124 | 2.6274 | 16 | 6.7551e-05 | 2548 | 1883.3994 | 478 | 0.12515 | 2.0024 | 623 |  | 3270
6170 | GIRVAN 11011330 | 103401101 | GIRVAN 1101 | 1330 | FALSE | 50161.9849 | 49990.913 | 31.0696 | 264 | 0.00011447 | 1308 | 1373.7242 | 651 | 0.12503 | 33.0087 | 624 | 0.19 | 1173
9760 | RINCON 11035152 | 43321103 | RINCON 1103 | 5152 | FALSE | 2685.0442 | 2685.0442 | 1.6688 | 17 | 0.00018787 | 456 | 675.7903 | 1038 | 0.1239 | 2.1064 | 625 | 12.52 | 374
6631 | HIGHLANDS 11031282 | 43361103 | HIGHLANDS 1103 | 1282 | FALSE | 26604.6713 | 22934.9277 | 14.2542 | 164 | 7.8872e-05 | 2239 | 1748.6654 | 515 | 0.12376 | 20.2971 | 626 | 4.57 | 514
7124 | SANTA YNEZ 1102CB | 182721102 | SANTA YNEZ 1102 | CB | FALSE | 14342.9846 | 2348.085 | 1.4593 | 124 | 5.5469e-05 | 2900 | 1580.4692 | 569 | 0.12375 | 15.3456 | 627 | 0.03 | 2351
547 | STILLWATER 11021644 | 103561102 | STILLWATER 1102 | 1644 | FALSE | 36747.479 | 36747.479 | 22.8387 | 244 | 0.00010131 | 1620 | 1382.8849 | 646 | 0.12375 | 30.1941 | 628 | 0.08 | 1604
6046 | WOODWARD 210878448 | 255292108 | WOODWARD 2108 | 78448 | FALSE | 47671.1997 | 31387.7639 | 19.5076 | 188 | 3.1679e-05 | 3405 | 4051.9056 | 146 | 0.12365 | 23.2453 | 629 | 0.05 | 2059
7443 | GARBERVILLE 11011770 | 192221101 | GARBERVILLE 1101 | 1770 | FALSE | 13849.8333 | 13849.8333 | 8.6077 | 66 | 0.00044353 | 51 | 343.9532 | 1380 | 0.12342 | 8.1457 | 630 | 0.02 | 2504
2056 | BUELLTON 1101Y06 | 183041101 | BUELLTON 1101 | Y06 | FALSE | 63281.543 | 48855.5405 | 30.3639 | 304 | 5.4903e-05 | 2917 | 2033.2985 | 450 | 0.12317 | 37.4433 | 631 | 0.14 | 1333
1863 | DIAMOND SPRINGS 110610587 | 152261106 | DIAMOND SPRINGS 1106 | 10587 | FALSE | 35336.5514 | 35336.5514 | 21.9618 | 212 | 8.4096e-05 | 2092 | 1469.4238 | 607 | 0.12297 | 26.0703 | 632 | 0.13 | 1334
5060 | CLOVERDALE 1102156 | 42821102 | CLOVERDALE 1102 | 156 | FALSE | 18958.8699 | 9919.8336 | 6.1652 | 110 | 0.00012453 | 1107 | 875.9596 | 896 | 0.12268 | 13.4944 | 633 | 0.21 | 1144
8874 | BRIDGEVILLE 110169866 | 192461101 | BRIDGEVILLE 1101 | 69866 | FALSE | 10571.2356 | 10571.2356 | 6.5701 | 46 | 0.00023172 | 281 | 514.4343 | 1188 | 0.12256 | 5.6379 | 634 | 3.53 | 543
7200 | DIAMOND SPRINGS 1104705100 | 152261104 | DIAMOND SPRINGS 1104 | 705100 | FALSE | 13322.8036 | 11885.1942 | 7.3867 | 78 | 0.00013638 | 915 | 900.0548 | 884 | 0.12223 | 9.5341 | 635 |  | 3106
5273 | SAND CREEK 11037110 | 254601103 | SAND CREEK 1103 | 7110 | FALSE | 29983.2616 | 29983.2616 | 18.6347 | 132 | 4.0372e-05 | 3258 | 3332.8764 | 221 | 0.12197 | 16.0996 | 636 | 0.03 | 2230
3234 | FULTON 1107604 | 42561107 | FULTON 1107 | 604 | FALSE | 28058.6741 | 28058.6741 | 17.4386 | 169 | 0.00010038 | 1638 | 1390.9913 | 641 | 0.12169 | 20.5661 | 637 | 38.24 | 196
8992 | TIDEWATER 2106781445 | 14652106 | TIDEWATER 2106 | 781445 | TRUE | 577.8877 | 405.5365 | 0.25204 | 6 | 0.00010546 | 1508 | 1075.6001 | 784 | 0.12145 | 0.72871 | 638 |  | 3291
9503 | SAN LUIS OBISPO 1103153199 | 182631103 | SAN LUIS OBISPO 1103 | 153199 | FALSE | 8788.2197 | 4750.5459 | 2.9525 | 53 | 4.9986e-05 | 3037 | 2588.0496 | 334 | 0.1214 | 6.4339 | 639 |  | 3364
8489 | LAYTONVILLE 1102572 | 42681102 | LAYTONVILLE 1102 | 572 | FALSE | 34429.3225 | 34429.3225 | 21.398 | 155 | 0.00020812 | 372 | 588.4642 | 1115 | 0.12097 | 18.7503 | 640 | 5.06 | 497
1408 | ATASCADERO 1103A16 | 182541103 | ATASCADERO 1103 | A16 | FALSE | 32308.0619 | 31835.9088 | 19.7861 | 122 | 9.9134e-05 | 1665 | 1262.4628 | 693 | 0.12088 | 14.7476 | 641 | 0.07 | 1702
68 | TEJON 11022455 | 252931102 | TEJON 1102 | 2455 | FALSE | 10165.5764 | 10165.5764 | 6.3179 | 84 | 3.5175e-05 | 3348 | 3535.7199 | 196 | 0.12034 | 10.1082 | 642 | 0.08 | 1657
6764 | MAXWELL 11053008 | 62881105 | MAXWELL 1105 | 3008 | FALSE | 24475.225 | 13636.9493 | 8.4754 | 55 | 6.8766e-05 | 2515 | 2119.5029 | 421 | 0.1202 | 6.6112 | 643 | 0.01 | 2614
3997 | APPLE HILL 2102CB | 153662102 | APPLE HILL 2102 | CB | FALSE | 66423.2503 | 66423.2503 | 41.2823 | 448 | 0.00014731 | 770 | 1022.0989 | 813 | 0.12006 | 53.7868 | 644 | 29.66 | 239
4706 | WYANDOTTE 11031504 | 102911103 | WYANDOTTE 1103 | 1504 | FALSE | 23629.2409 | 17735.4007 | 11.0226 | 186 | 0.00021184 | 352 | 618.3499 | 1084 | 0.12006 | 22.3307 | 645 | 0.12 | 1402
8185 | CLARKSVILLE 2109CB | 153612109 | CLARKSVILLE 2109 | CB | FALSE | 1831.3319 | 1593.4993 | 0.99037 | 15 | 0.00021275 | 345 | 713.5234 | 1009 | 0.11989 | 1.7983 | 646 | 0.07 | 1726
5862 | HOLLISTER 2102855412 | 182492102 | HOLLISTER 2102 | 855412 | FALSE | 50683.3516 | 45702.3865 | 28.4042 | 108 | 6.4443e-05 | 2629 | 1812.7947 | 504 | 0.11956 | 12.9123 | 647 | 0.05 | 2051
2833 | MARTELL 11033152 | 163011103 | MARTELL 1103 | 3152 | FALSE | 27364.6036 | 26923.3255 | 16.733 | 134 | 8.4438e-05 | 2079 | 1552.0849 | 578 | 0.11956 | 16.0208 | 648 | 0.08 | 1624
3141 | DIAMOND SPRINGS 11057722 | 152261105 | DIAMOND SPRINGS 1105 | 7722 | FALSE | 100229.7186 | 96782.5255 | 60.1507 | 572 | 0.00010462 | 1540 | 1087.3028 | 779 | 0.11928 | 68.2291 | 649 | 0.25 | 1084
501 | DOBBINS 11011264 | 153741101 | DOBBINS 1101 | 1264 | FALSE | 56286.9636 | 56286.9636 | 34.9826 | 307 | 0.00011647 | 1260 | 1094.5256 | 776 | 0.11917 | 36.585 | 650 | 0.39 | 957
855 | HIGGINS 1103CB | 152691103 | HIGGINS 1103 | CB | FALSE | 45692.926 | 45174.6839 | 28.0762 | 315 | 0.00014305 | 825 | 1166.4722 | 747 | 0.11916 | 37.536 | 651 | 0.25 | 1090
491 | TIVY VALLEY 1107822606 | 252941107 | TIVY VALLEY 1107 | 822606 | FALSE | 29230.0954 | 21701.9466 | 13.4878 | 144 | 3.2057e-05 | 3400 | 3717.2296 | 181 | 0.11894 | 17.1275 | 652 |  | 2678
8121 | CAYETANO 2109MR186 | 14422109 | CAYETANO 2109 | MR186 | TRUE | 4135.7533 | 818.8837 | 0.50894 | 27 | 8.9465e-05 | 1933 | 1490.2334 | 599 | 0.11874 | 3.2061 | 653 | 0.02 | 2461
2634 | APPLE HILL 21028372 | 153662102 | APPLE HILL 2102 | 8372 | FALSE | 101264.4904 | 94481.7777 | 58.7208 | 629 | 0.00011802 | 1229 | 985.1922 | 841 | 0.11858 | 74.5861 | 654 | 0.21 | 1139
1440 | MARIPOSA 21019400 | 254452101 | MARIPOSA 2101 | 9400 | FALSE | 101537.78 | 101537.78 | 63.1061 | 667 | 6.6859e-05 | 2561 | 1882.7942 | 479 | 0.11849 | 79.0304 | 655 | 1.17 | 705
8059 | OILFIELDS 1103N62 | 182391103 | OILFIELDS 1103 | N62 | FALSE | 8948.1922 | 8948.1922 | 5.5613 | 39 | 7.0521e-05 | 2455 | 1674.5706 | 532 | 0.11842 | 4.6183 | 656 | 0.13 | 1344
1860 | SHINGLE SPRINGS 2105CB | 153652105 | SHINGLE SPRINGS 2105 | CB | FALSE | 30610.8387 | 30610.8387 | 19.0248 | 245 | 0.00018342 | 484 | 745.8005 | 978 | 0.11812 | 28.9401 | 657 | 0.61 | 844
1237 | NARROWS 2102CB | 153132102 | NARROWS 2102 | CB | FALSE | 39248.3153 | 36287.6403 | 22.5529 | 243 | 0.00015786 | 664 | 1177.1526 | 742 | 0.11807 | 28.6917 | 658 | 0.1 | 1491
9931 | CORTINA 1101528460 | 63121101 | CORTINA 1101 | 528460 | FALSE | 6121.8319 | 3043.5918 | 1.8916 | 12 | 3.9909e-05 | 3271 | 3097.7847 | 255 | 0.11792 | 1.415 | 659 |  | 3454
6877 | COARSEGOLD 21036110 | 254432103 | COARSEGOLD 2103 | 6110 | FALSE | 47929.948 | 17714.3763 | 11.0096 | 179 | 4.1885e-05 | 3228 | 2595.4532 | 332 | 0.11737 | 21.0097 | 660 | 0.03 | 2313
3126 | HORSESHOE 110150140 | 152571101 | HORSESHOE 1101 | 50140 | FALSE | 10038.7802 | 6357.3386 | 3.9511 | 82 | 0.0001527 | 722 | 724.1364 | 995 | 0.11734 | 9.6215 | 661 | 0.07 | 1721
9916 | SAN LUIS OBISPO 1104777686 | 182631104 | SAN LUIS OBISPO 1104 | 777686 | FALSE | 3079.762 | 2707.2733 | 1.6826 | 17 | 6.1974e-05 | 2721 | 2050.5492 | 444 | 0.11731 | 1.9944 | 662 |  | 3452
8080 | SILVERADO 210258626 | 43432102 | SILVERADO 2102 | 58626 | FALSE | 24491.7338 | 24491.7338 | 15.2217 | 125 | 9.1234e-05 | 1869 | 1427.3169 | 627 | 0.117 | 14.6249 | 663 | 33.89 | 218
4277 | SAN JOAQUIN #2 1103157026 | 252521103 | SAN JOAQUIN #2 1103 | 157026 | FALSE | 5200.077 | 5200.077 | 3.2319 | 44 | 6.6096e-05 | 2586 | 1923.6933 | 467 | 0.11682 | 5.1403 | 664 | 0.05 | 1989
6827 | PEORIA 170411232 | 163781704 | PEORIA 1704 | 11232 | FALSE | 27747.6591 | 20505.608 | 12.7443 | 222 | 7.7668e-05 | 2269 | 1686.0292 | 527 | 0.11656 | 25.8772 | 665 | 3.3 | 550
772 | DIAMOND SPRINGS 11052102 | 152261105 | DIAMOND SPRINGS 1105 | 2102 | FALSE | 62912.0633 | 60307.8799 | 37.4816 | 417 | 0.00013035 | 1002 | 1146.8943 | 755 | 0.11621 | 48.4576 | 666 | 0.75 | 787
1946 | WILLITS 1104CB | 42661104 | WILLITS 1104 | CB | FALSE | 12241.4218 | 6260.0525 | 3.8906 | 90 | 0.00013491 | 927 | 773.6055 | 956 | 0.11609 | 10.4477 | 667 | 0.03 | 2310
2370 | GEYSERVILLE 1102484 | 42891102 | GEYSERVILLE 1102 | 484 | FALSE | 78528.1935 | 53688.8082 | 33.3678 | 379 | 0.00011833 | 1222 | 896.8187 | 885 | 0.11607 | 43.9888 | 668 | 0.17 | 1225
7186 | HIGGINS 1104CB | 152691104 | HIGGINS 1104 | CB | FALSE | 18716.511 | 18050.1072 | 11.2182 | 124 | 0.00013241 | 974 | 792.6979 | 948 | 0.11592 | 14.3743 | 669 | 0.08 | 1643
9814 | PENRYN 1105119949 | 152561105 | PENRYN 1105 | 119949 | FALSE | 3756.7927 | 2221.8702 | 1.3809 | 25 | 7.5613e-05 | 2320 | 1497.9784 | 598 | 0.11529 | 2.8822 | 670 |  | 3429
7423 | CLAY 1103CB | 163341103 | CLAY 1103 | CB | FALSE | 21668.4067 | 9680.057 | 6.0162 | 110 | 0.00011397 | 1323 | 734.8074 | 989 | 0.11521 | 12.6729 | 671 | 0.03 | 2334
7292 | TIDEWATER 2106745811 | 14652106 | TIDEWATER 2106 | 745811 | TRUE | 780.426 | 641.2916 | 0.39857 | 8 | 7.9022e-05 | 2235 | 1106.1185 | 773 | 0.11506 | 0.92047 | 672 |  | 3113
8864 | WOODACRE 110191900 | 43021101 | WOODACRE 1101 | 91900 | FALSE | 22248.6035 | 14519.294 | 9.0238 | 91 | 0.00012885 | 1031 | 1012.5441 | 824 | 0.11491 | 10.4566 | 673 | 1.72 | 650
9782 | SAND CREEK 110397354 | 254601103 | SAND CREEK 1103 | 97354 | FALSE | 16339.8299 | 14168.242 | 8.8056 | 59 | 2.3546e-05 | 3509 | 5418.3509 | 49 | 0.11488 | 6.7778 | 674 | 0.06 | 1885
7321 | CLARKSVILLE 210619642 | 153612106 | CLARKSVILLE 2106 | 19642 | FALSE | 2579.2739 | 1246.4399 | 0.77467 | 17 | 0.00024874 | 219 | 453.1258 | 1242 | 0.11477 | 1.9511 | 675 | 0.96 | 739
1291 | MERCED FALLS 11029470 | 252811102 | MERCED FALLS 1102 | 9470 | FALSE | 36749.5976 | 36749.5976 | 22.84 | 277 | 8.8658e-05 | 1964 | 1395.4992 | 639 | 0.11474 | 31.7833 | 676 | 0.01 | 2586
10278 | PUEBLO 2102943820 | 43292102 | PUEBLO 2102 | 943820 | FALSE | 3953.9711 | 3039.5845 | 1.8891 | 13 | 9.0029e-05 | 1913 | 1434.295 | 621 | 0.11464 | 1.4903 | 677 |  | 3527
2358 | WHITMORE 11011594 | 103601101 | WHITMORE 1101 | 1594 | FALSE | 39042.2093 | 39042.2093 | 24.2649 | 160 | 0.00012552 | 1089 | 1126.4421 | 765 | 0.11449 | 18.3178 | 678 | 0.12 | 1390
892 | MARIPOSA 210110240 | 254452101 | MARIPOSA 2101 | 10240 | FALSE | 34689.059 | 34689.059 | 21.5594 | 189 | 7.4292e-05 | 2350 | 1439.7612 | 619 | 0.11431 | 21.6045 | 679 | 0.31 | 1009
4813 | CLOVERDALE 1102674 | 42821102 | CLOVERDALE 1102 | 674 | FALSE | 32462.2926 | 27296.9382 | 16.9652 | 122 | 0.00011908 | 1203 | 1499.689 | 597 | 0.11401 | 13.9092 | 680 | 0.15 | 1285
4778 | SHINGLE SPRINGS 210961892 | 153652109 | SHINGLE SPRINGS 2109 | 61892 | FALSE | 48456.6488 | 48456.6488 | 30.116 | 318 | 8.0969e-05 | 2183 | 1584.3018 | 567 | 0.11372 | 36.1635 | 681 | 38.89 | 193
9093 | BANGOR 110155206 | 103191101 | BANGOR 1101 | 55206 | TRUE | 3467.0084 | 0 | 0 | 28 | 0.00010976 | 1415 | 967.1576 | 851 | 0.11351 | 3.1783 | 682 | 0.04 | 2213
395 | CALISTOGA 1101734 | 42711101 | CALISTOGA 1101 | 734 | FALSE | 26724.941 | 22050.8989 | 13.7047 | 162 | 0.00015037 | 732 | 885.8837 | 889 | 0.11348 | 18.3842 | 683 | 1.06 | 719
7143 | COTATI 1103CB | 42271103 | COTATI 1103 | CB | FALSE | 19422.567 | 19422.567 | 12.0712 | 106 | 0.00011506 | 1297 | 1154.679 | 753 | 0.11341 | 12.0218 | 684 | 5.58 | 484
2744 | WHITMORE 110145262 | 103601101 | WHITMORE 1101 | 45262 | FALSE | 46333.9347 | 46333.9347 | 28.7967 | 221 | 0.00010272 | 1577 | 1038.3077 | 800 | 0.11334 | 25.0485 | 685 | 0.06 | 1915
4167 | COTTONWOOD 11031344 | 102931103 | COTTONWOOD 1103 | 1344 | FALSE | 20065.0071 | 16285.3354 | 10.1214 | 152 | 6.9299e-05 | 2497 | 2362.2491 | 369 | 0.11327 | 17.2178 | 686 | 4.34 | 522
9035 | CLEAR LAKE 1101699062 | 42141101 | CLEAR LAKE 1101 | 699062 | FALSE | 3006.4235 | 1359.6473 | 0.84503 | 20 | 8.6499e-05 | 2024 | 1257.9802 | 696 | 0.11322 | 2.2645 | 687 |  | 3300
2015 | SHINGLE SPRINGS 210912392 | 153652109 | SHINGLE SPRINGS 2109 | 12392 | FALSE | 23572.5391 | 23572.5391 | 14.6504 | 178 | 0.00010936 | 1424 | 1246.8521 | 703 | 0.11309 | 20.1293 | 688 | 55.71 | 101
2546 | PLACERVILLE 1110421358 | 153081110 | PLACERVILLE 1110 | 421358 | FALSE | 23870.6711 | 23870.6711 | 14.8357 | 169 | 0.00012254 | 1140 | 802.5537 | 940 | 0.11286 | 19.0733 | 689 |  | 2784
6240 | SILVERADO 2104722 | 43432104 | SILVERADO 2104 | 722 | FALSE | 12705.3582 | 12705.3582 | 7.8964 | 99 | 0.00026082 | 194 | 569.6012 | 1130 | 0.11274 | 11.1613 | 690 | 46.62 | 140
6314 | TEJON 11023751 | 252931102 | TEJON 1102 | 3751 | FALSE | 16451.1737 | 15802.8651 | 9.8215 | 65 | 4.4896e-05 | 3163 | 3153.8117 | 247 | 0.11269 | 7.325 | 691 | 0.03 | 2272
8377 | CAYETANO 2111CB | 14422111 | CAYETANO 2111 | CB | FALSE | 14665.1565 | 5449.7896 | 3.3871 | 81 | 0.00012146 | 1157 | 1050.3758 | 796 | 0.11258 | 9.1187 | 692 | 0.04 | 2099
84 | LINCOLN 110451756 | 153701104 | LINCOLN 1104 | 51756 | FALSE | 56082.3102 | 17440.8058 | 10.8395 | 264 | 8.4998e-05 | 2060 | 1131.9939 | 763 | 0.11252 | 29.7041 | 693 | 1.15 | 707
4410 | MC ARTHUR 1101501106 | 103491101 | MC ARTHUR 1101 | 501106 | FALSE | 16962.6839 | 16083.896 | 9.9962 | 86 | 2.2874e-05 | 3513 | 4753.376 | 97 | 0.11248 | 9.6734 | 694 |  | 2889
1376 | CLARKSVILLE 210419772 | 153612104 | CLARKSVILLE 2104 | 19772 | FALSE | 29712.1582 | 28840.3765 | 17.9244 | 185 | 0.00010637 | 1489 | 1084.3194 | 780 | 0.11233 | 20.7806 | 695 | 41.36 | 177
138 | CLARKSVILLE 2103593454 | 153612103 | CLARKSVILLE 2103 | 593454 | FALSE | 65282.8123 | 51502.8241 | 32.0092 | 324 | 8.6965e-05 | 2012 | 1565.5344 | 572 | 0.11221 | 36.3549 | 696 |  | 2656
6028 | RISING RIVER 11011530 | 103551101 | RISING RIVER 1101 | 1530 | FALSE | 28483.8521 | 18168.0106 | 11.2915 | 167 | 5.6107e-05 | 2884 | 2176.9842 | 405 | 0.11218 | 18.7349 | 697 | 0.01 | 2573
6687 | CLARK ROAD 110281296 | 103091102 | CLARK ROAD 1102 | 81296 | FALSE | 24680.7336 | 17571.0511 | 10.9205 | 124 | 0.00010636 | 1490 | 869.9858 | 899 | 0.11218 | 13.9107 | 698 | 0.05 | 2005
2672 | APPLE HILL 210277546 | 153662102 | APPLE HILL 2102 | 77546 | FALSE | 69346.9327 | 69346.9327 | 43.0994 | 403 | 9.5092e-05 | 1762 | 1309.4241 | 678 | 0.11214 | 45.1922 | 699 | 0.19 | 1189
4377 | MARIPOSA 2101752630 | 254452101 | MARIPOSA 2101 | 752630 | FALSE | 30558.9663 | 30558.9663 | 18.9925 | 154 | 6.484e-05 | 2614 | 1699.6449 | 523 | 0.11205 | 17.2553 | 700 |  | 2886
5474 | COTATI 1105213984 | 42271105 | COTATI 1105 | 213984 | FALSE | 11162.845 | 11162.845 | 6.9378 | 47 | 9.4494e-05 | 1780 | 1225.6338 | 715 | 0.11198 | 5.263 | 701 |  | 2957
6448 | MERCED FALLS 110238748 | 252811102 | MERCED FALLS 1102 | 38748 | FALSE | 24704.6186 | 24704.6186 | 15.354 | 178 | 7.1784e-05 | 2426 | 1618.5371 | 554 | 0.11192 | 19.9215 | 702 | 0.01 | 2604
1645 | COTATI 110599720 | 42271105 | COTATI 1105 | 99720 | FALSE | 19787.8115 | 14780.8133 | 9.1863 | 134 | 8.8188e-05 | 1977 | 1157.381 | 751 | 0.11177 | 14.9768 | 703 | 7.05 | 453
439 | HIGGINS 1110CB | 152691110 | HIGGINS 1110 | CB | FALSE | 17394.4702 | 14019.0952 | 8.7129 | 134 | 0.00023184 | 280 | 615.3789 | 1088 | 0.11172 | 14.9707 | 704 | 0.06 | 1909
6646 | UPPER LAKE 110175370 | 42871101 | UPPER LAKE 1101 | 75370 | FALSE | 23702.8229 | 17823.7139 | 11.0775 | 133 | 0.0001129 | 1346 | 1122.5953 | 767 | 0.11161 | 14.8441 | 705 | 0.05 | 2009
3320 | LAYTONVILLE 110237586 | 42681102 | LAYTONVILLE 1102 | 37586 | FALSE | 22457.0278 | 22457.0278 | 13.9571 | 72 | 0.00013607 | 919 | 959.2045 | 854 | 0.11137 | 8.0187 | 706 | 0.07 | 1736
8527 | HIGGINS 11097831 | 152691109 | HIGGINS 1109 | 7831 | FALSE | 14300.9674 | 14300.9674 | 8.8881 | 86 | 5.8164e-05 | 2831 | 1904.4724 | 475 | 0.1113 | 9.5719 | 707 | 0.1 | 1473
8404 | TEMPLETON 2110317796 | 183052110 | TEMPLETON 2110 | 317796 | FALSE | 11760.0744 | 8148.5566 | 5.0644 | 65 | 7.0178e-05 | 2466 | 1382.5193 | 647 | 0.11087 | 7.2063 | 708 |  | 3222
9399 | CALAVERAS CEMENT 1101585 | 162211101 | CALAVERAS CEMENT 1101 | 585 | FALSE | 22730.6203 | 22730.6203 | 14.1272 | 95 | 6.2212e-05 | 2714 | 1313.2645 | 677 | 0.11082 | 10.5283 | 709 | 0.1 | 1490
9168 | CAL WATER 1102690954 | 255451102 | CAL WATER 1102 | 690954 | FALSE | 6889.4894 | 6410.0397 | 3.9839 | 12 | 1.5494e-05 | 3583 | 7160.5307 | 9 | 0.11057 | 1.3268 | 710 |  | 3318
1850 | OAKHURST 1103CB | 254421103 | OAKHURST 1103 | CB | FALSE | 53866.9528 | 51789.1777 | 32.1872 | 417 | 0.00011056 | 1401 | 1269.855 | 691 | 0.11044 | 46.0525 | 711 | 0.78 | 780
4124 | CALPELLA 1102CB | 43411102 | CALPELLA 1102 | CB | TRUE | 7260.7146 | 263.08 | 0.16351 | 61 | 0.00011907 | 1204 | 713.2367 | 1010 | 0.1104 | 6.7341 | 712 | 0.02 | 2463
10720 | OCEANO 1103839302 | 182601103 | OCEANO 1103 | 839302 | FALSE | 1806.4039 | 1806.4039 | 1.1227 | 8 | 4.4881e-05 | 3164 | 2564.3756 | 337 | 0.11001 | 0.88007 | 713 |  | 3595
2355 | OLETA 11021204 | 163541102 | OLETA 1102 | 1204 | FALSE | 47393.9854 | 41374.6655 | 25.7145 | 233 | 8.8982e-05 | 1950 | 1305.1155 | 679 | 0.10989 | 25.6033 | 714 | 0.09 | 1553
635 | BRUNSWICK 11062790 | 152481106 | BRUNSWICK 1106 | 2790 | FALSE | 17696.042 | 16028.2028 | 9.9616 | 115 | 0.00014264 | 831 | 967.5085 | 850 | 0.10954 | 12.5971 | 715 | 0.18 | 1201
6919 | COTTONWOOD 110168190 | 102931101 | COTTONWOOD 1101 | 68190 | FALSE | 40559.778 | 38588.9503 | 23.9832 | 238 | 3.6266e-05 | 3328 | 3033.8848 | 265 | 0.10937 | 26.0311 | 716 | 0.06 | 1813
10335 | PETALUMA C 1109664732 | 42631109 | PETALUMA C 1109 | 664732 | FALSE | 1437.8147 | 1437.8147 | 0.89361 | 6 | 9.0941e-05 | 1884 | 1650.3416 | 543 | 0.10842 | 0.65051 | 717 | 1.72 | 649
4157 | CALPELLA 1101600 | 43411101 | CALPELLA 1101 | 600 | FALSE | 39281.1533 | 30870.3 | 19.186 | 164 | 0.00011588 | 1272 | 1083.2564 | 781 | 0.10818 | 17.7408 | 718 | 0.15 | 1297
3546 | LUCERNE 1103CB | 43351103 | LUCERNE 1103 | CB | FALSE | 7158.565 | 3619.1597 | 2.2493 | 59 | 0.00018211 | 497 | 299.7205 | 1447 | 0.10789 | 6.3658 | 719 | 0.1 | 1483
6463 | SONOMA 1105229588 | 42721105 | SONOMA 1105 | 229588 | FALSE | 21565.3961 | 15531.0208 | 9.6526 | 149 | 8.8674e-05 | 1963 | 1224.4513 | 716 | 0.10786 | 16.0708 | 720 |  | 3033
2133 | FROGTOWN 17011623 | 163451701 | FROGTOWN 1701 | 1623 | FALSE | 24554.2111 | 24554.2111 | 15.2605 | 152 | 7.6286e-05 | 2301 | 1590.8242 | 564 | 0.1076 | 16.3546 | 721 | 0.2 | 1165
10925 | GOLDTREE 1105551904 | 182581105 | GOLDTREE 1105 | 551904 | TRUE | 35.7178 | 35.7178 | 0.022199 | 1 | 0.00014066 | 859 | 763.0871 | 960 | 0.10733 | 0.10733 | 722 | 0.87 | 755
9605 | NOTRE DAME 1104937710 | 102041104 | NOTRE DAME 1104 | 937710 | FALSE | 2292.7758 | 1372.1379 | 0.85279 | 8 | 9.5377e-05 | 1748 | 1144.507 | 756 | 0.10733 | 0.85862 | 723 |  | 3387
3953 | JAMESON 11059472 | 63801105 | JAMESON 1105 | 9472 | FALSE | 11800.3384 | 4934.5741 | 3.0669 | 90 | 8.6625e-05 | 2018 | 1503.1801 | 596 | 0.10731 | 9.6577 | 724 | 0.04 | 2109
6952 | OLETA 110151740 | 163541101 | OLETA 1101 | 51740 | FALSE | 34181.0044 | 25031.397 | 15.5571 | 129 | 6.4996e-05 | 2610 | 1615.1565 | 556 | 0.107 | 13.8028 | 725 | 0.06 | 1828
4360 | CORRAL 110236666 | 162991102 | CORRAL 1102 | 36666 | FALSE | 29026.438 | 27295.7526 | 16.9644 | 207 | 7.008e-05 | 2471 | 1591.1088 | 563 | 0.10683 | 22.1131 | 726 | 0.11 | 1436
10467 | BIG BEND 11011704 | 103751101 | BIG BEND 1101 | 1704 | FALSE | 4825.0456 | 4825.0456 | 2.9988 | 9 | 0.00018499 | 473 | 1060.4778 | 792 | 0.1065 | 0.95854 | 727 | 1.47 | 671
2963 | KONOCTI 110275382 | 43311102 | KONOCTI 1102 | 75382 | FALSE | 37601.9152 | 37336.0999 | 23.2045 | 198 | 0.00010957 | 1420 | 1232.3374 | 713 | 0.10636 | 21.0588 | 728 | 11.14 | 387
7719 | GEYSERVILLE 1102220154 | 42891102 | GEYSERVILLE 1102 | 220154 | TRUE | 4466.0624 | 427.7941 | 0.26588 | 30 | 0.00014785 | 765 | 533.1924 | 1168 | 0.10579 | 3.1738 | 729 |  | 3155
4276 | NARROWS 2105CB | 153132105 | NARROWS 2105 | CB | FALSE | 58448.7227 | 58073.6402 | 36.093 | 382 | 0.00010807 | 1450 | 1111.2712 | 769 | 0.10567 | 40.3677 | 730 | 0.26 | 1065
4123 | MARIPOSA 21014410 | 254452101 | MARIPOSA 2101 | 4410 | FALSE | 36702.381 | 36702.381 | 22.8107 | 232 | 6.2011e-05 | 2720 | 1654.2525 | 541 | 0.10548 | 24.471 | 731 | 0.16 | 1272
5996 | MONTICELLO 1101630 | 43051101 | MONTICELLO 1101 | 630 | FALSE | 31341.2103 | 30113.0466 | 18.7154 | 93 | 5.6908e-05 | 2863 | 1625.0866 | 552 | 0.10515 | 9.7794 | 732 | 0.15 | 1293
7010 | WILLITS 1103966 | 42661103 | WILLITS 1103 | 966 | FALSE | 3670.4356 | 1555.849 | 0.96697 | 34 | 0.00012939 | 1020 | 514.9608 | 1186 | 0.10505 | 3.5716 | 733 | 0.33 | 984
6094 | PARADISE 110443008 | 102831104 | PARADISE 1104 | 43008 | FALSE | 20752.8612 | 20697.7732 | 12.8637 | 145 | 0.00024315 | 238 | 866.3217 | 903 | 0.10501 | 15.2269 | 734 |  | 3002
6540 | MORGAN HILL 2105XR070 | 83242105 | MORGAN HILL 2105 | XR070 | FALSE | 13972.8614 | 10519.5514 | 6.5379 | 90 | 8.0053e-05 | 2203 | 1459.1172 | 612 | 0.10473 | 9.4261 | 735 | 0.15 | 1280
1104 | BRUNSWICK 11042112 | 152481104 | BRUNSWICK 1104 | 2112 | FALSE | 31201.9016 | 31201.9016 | 19.3921 | 222 | 0.00012958 | 1016 | 755.541 | 969 | 0.1046 | 23.2211 | 736 | 9 | 416
3331 | NARROWS 21052216 | 153132105 | NARROWS 2105 | 2216 | FALSE | 93046.0132 | 91192.0768 | 56.6762 | 663 | 0.00017534 | 526 | 744.5838 | 980 | 0.10438 | 69.2068 | 737 | 0.89 | 752
10962 | POINT ARENA 1101CB | 43381101 | POINT ARENA 1101 | CB | TRUE | 64.9169 | 64.9169 | 0.040346 | 2 | 8.2597e-05 | 2140 | 1260.6413 | 694 | 0.10413 | 0.20825 | 738 | 0.04 | 2172
7695 | JAMESON 110265516 | 63801102 | JAMESON 1102 | 65516 | FALSE | 18264.4613 | 12394.5836 | 7.7033 | 137 | 9.0277e-05 | 1904 | 1198.218 | 730 | 0.104 | 14.2484 | 739 | 1.33 | 685
4131 | CURTIS 170565908 | 163351705 | CURTIS 1705 | 65908 | FALSE | 26966.3027 | 22380.0869 | 13.9093 | 205 | 0.00010013 | 1641 | 1026.2121 | 810 | 0.10393 | 21.3052 | 740 | 0.11 | 1441
386 | CORRAL 110112606 | 162991101 | CORRAL 1101 | 12606 | FALSE | 36144.366 | 36144.366 | 22.4639 | 216 | 6.3081e-05 | 2677 | 1680.4042 | 528 | 0.10392 | 22.4476 | 741 | 3.18 | 556
1298 | DESCHUTES 11011652 | 103351101 | DESCHUTES 1101 | 1652 | FALSE | 39344.5137 | 33895.2642 | 21.066 | 170 | 8.6737e-05 | 2017 | 1367.2683 | 654 | 0.10352 | 17.5982 | 742 | 0.06 | 1779
10344 | CLARKSVILLE 210319572 | 153612103 | CLARKSVILLE 2103 | 19572 | TRUE | 4463.6596 | 595.3794 | 0.37003 | 12 | 8.8886e-05 | 1956 | 995.992 | 836 | 0.10348 | 1.2418 | 743 | 0.4 | 947
2338 | CLAY 110113442 | 163341101 | CLAY 1101 | 13442 | FALSE | 49960.437 | 40749.3903 | 25.3259 | 272 | 6.9011e-05 | 2508 | 1672.073 | 535 | 0.10338 | 28.1191 | 744 | 0.16 | 1269
1080 | PLACER 1103284874 | 152461103 | PLACER 1103 | 284874 | FALSE | 7928.0423 | 3450.771 | 2.1447 | 56 | 0.00016281 | 613 | 825.2112 | 923 | 0.10322 | 5.7804 | 745 |  | 2708
2572 | VACA DIXON 11059792 | 63591105 | VACA DIXON 1105 | 9792 | FALSE | 44037.0343 | 1255.3676 | 0.78022 | 329 | 0.00010469 | 1536 | 1266.1791 | 692 | 0.10322 | 33.9591 | 746 | 1.85 | 639
10829 | MILPITAS 110962157 | 82831109 | MILPITAS 1109 | 62157 | TRUE | 72.1015 | 72.1015 | 0.044811 | 3 | 0.00013141 | 991 | 794.5095 | 944 | 0.10257 | 0.30771 | 747 | 0.04 | 2185
9526 | DOBBINS 110191464 | 153741101 | DOBBINS 1101 | 91464 | FALSE | 11314.1038 | 11314.1038 | 7.0318 | 81 | 0.00016471 | 590 | 737.1972 | 986 | 0.10229 | 8.2855 | 748 | 0.15 | 1286
4686 | ELK CREEK 11012212 | 102781101 | ELK CREEK 1101 | 2212 | FALSE | 54144.6309 | 25107.5196 | 15.6044 | 136 | 5.0479e-05 | 3023 | 1941.9065 | 465 | 0.10222 | 13.9025 | 749 | 0.05 | 2020
2703 | COTATI 110536536 | 42271105 | COTATI 1105 | 36536 | FALSE | 31849.3061 | 27701.0415 | 17.2163 | 206 | 9.0039e-05 | 1912 | 1240.3355 | 706 | 0.10219 | 21.0515 | 750 | 6.79 | 460
261 | CLARK ROAD 11022584 | 103091102 | CLARK ROAD 1102 | 2584 | FALSE | 15108.9141 | 14615.3184 | 9.0835 | 83 | 7.5728e-05 | 2313 | 1697.4775 | 524 | 0.1019 | 8.4581 | 751 | 0.06 | 1883
6202 | COARSEGOLD 210490356 | 254432104 | COARSEGOLD 2104 | 90356 | FALSE | 27619.1431 | 7749.0513 | 4.8161 | 148 | 4.5741e-05 | 3146 | 2250.7696 | 393 | 0.10189 | 15.079 | 752 | 0.02 | 2540
10164 | CALPELLA 1101345230 | 43411101 | CALPELLA 1101 | 345230 | FALSE | 4014.2831 | 1908.1944 | 1.186 | 22 | 0.00013065 | 997 | 832.9519 | 920 | 0.10181 | 2.2398 | 753 |  | 3505
10372 | CLOVERDALE 11024646 | 42821102 | CLOVERDALE 1102 | 4646 | TRUE | 480.2865 | 242.399 | 0.15065 | 8 | 0.00023752 | 255 | 1510.1147 | 591 | 0.10163 | 0.81301 | 754 | 0.12 | 1368
10615 | STAFFORD 1102CB | 43201102 | STAFFORD 1102 | CB | TRUE | 993.1092 | 957.3027 | 0.59497 | 10 | 0.00022667 | 299 | 666.0518 | 1045 | 0.10116 | 1.0116 | 755 | 1.11 | 714
10097 | GARBERVILLE 110256048 | 192221102 | GARBERVILLE 1102 | 56048 | FALSE | 8009.5026 | 8009.5026 | 4.9779 | 27 | 0.00051047 | 29 | 201.585 | 1638 | 0.10102 | 2.7275 | 756 | 0.04 | 2118
2214 | MONTICELLO 11014360 | 43051101 | MONTICELLO 1101 | 4360 | FALSE | 14899.0043 | 12170.4858 | 7.564 | 76 | 4.8295e-05 | 3087 | 2072.1488 | 436 | 0.10101 | 7.6765 | 757 | 0.1 | 1496
2869 | NARROWS 21011202 | 153132101 | NARROWS 2101 | 1202 | FALSE | 73649.8789 | 73649.8789 | 45.7737 | 459 | 9.3805e-05 | 1798 | 1469.356 | 608 | 0.10087 | 46.3007 | 758 | 0.24 | 1107
2918 | JESSUP 110338864 | 103441103 | JESSUP 1103 | 38864 | FALSE | 12167.5887 | 2907.107 | 1.8068 | 94 | 9.1373e-05 | 1865 | 1176.5294 | 743 | 0.10076 | 9.4715 | 759 | 0.03 | 2406
8434 | FORT ROSS 1121204 | 42851121 | FORT ROSS 1121 | 204 | FALSE | 31553.8482 | 31553.8482 | 19.6108 | 107 | 0.00017266 | 545 | 673.9659 | 1039 | 0.10067 | 10.7713 | 760 | 11.03 | 390
9462 | BEAR VALLEY 210110019 | 252192101 | BEAR VALLEY 2101 | 10019 | FALSE | 3187.4941 | 3187.4941 | 1.981 | 11 | 5.9517e-05 | 2788 | 1607.8644 | 559 | 0.10052 | 1.1057 | 761 | 0.01 | 2577
3132 | MORGAN HILL 210542348 | 83242105 | MORGAN HILL 2105 | 42348 | FALSE | 5997.998 | 2160.8096 | 1.343 | 53 | 6.8961e-05 | 2511 | 1015.3292 | 819 | 0.10037 | 5.3194 | 762 | 0.49 | 895
10415 | SAN LUIS OBISPO 1103934355 | 182631103 | SAN LUIS OBISPO 1103 | 934355 | TRUE | 1942.6666 | 915.6706 | 0.56909 | 12 | 8.3455e-05 | 2118 | 1431.4244 | 623 | 0.10029 | 1.2035 | 763 |  | 3546
800 | NARROWS 210248484 | 153132102 | NARROWS 2102 | 48484 | FALSE | 67054.8672 | 67054.8672 | 41.6749 | 450 | 0.00013313 | 956 | 878.6779 | 893 | 0.09998 | 44.991 | 764 | 0.43 | 927
3794 | HIGGINS 11077559 | 152691107 | HIGGINS 1107 | 7559 | FALSE | 7193.5229 | 7193.5229 | 4.4708 | 52 | 6.8486e-05 | 2522 | 1663.4994 | 538 | 0.099807 | 5.1899 | 765 | 0.1 | 1474
4136 | MONTICELLO 1101718 | 43051101 | MONTICELLO 1101 | 718 | FALSE | 47250.4225 | 43463.4041 | 27.0127 | 247 | 6.3139e-05 | 2675 | 1440.3304 | 618 | 0.099744 | 24.6369 | 766 | 0.18 | 1211
2696 | OLETA 110163500 | 163541101 | OLETA 1101 | 63500 | TRUE | 5562.1132 | 327.1501 | 0.20333 | 46 | 0.00011792 | 1230 | 448.3626 | 1251 | 0.099652 | 4.584 | 767 | 1.81 | 642
3595 | CEDAR CREEK 11011608 | 103321101 | CEDAR CREEK 1101 | 1608 | FALSE | 53827.5719 | 53827.5719 | 33.4541 | 252 | 0.00019009 | 441 | 523.0258 | 1180 | 0.099644 | 25.1102 | 768 | 0.06 | 1838
80 | WHEATLAND 1105248490 | 152811105 | WHEATLAND 1105 | 248490 | FALSE | 43282.2287 | 17726.6224 | 11.0172 | 228 | 9.8358e-05 | 1682 | 1137.7994 | 759 | 0.099611 | 22.7114 | 769 |  | 2654
24 | FITCH MOUNTAIN 1113443164 | 42751113 | FITCH MOUNTAIN 1113 | 443164 | FALSE | 15151.4475 | 4499.5872 | 2.7965 | 111 | 0.00012907 | 1027 | 720.9883 | 997 | 0.099321 | 11.0246 | 770 |  | 2651
6194 | CLARK ROAD 110292622 | 103091102 | CLARK ROAD 1102 | 92622 | FALSE | 50349.3756 | 50311.0535 | 31.2685 | 257 | 0.00011545 | 1291 | 1017.6191 | 817 | 0.098498 | 25.314 | 771 | 0.07 | 1774
643 | PENRYN 1105154362 | 152561105 | PENRYN 1105 | 154362 | FALSE | 11970.1824 | 3480.2712 | 2.163 | 90 | 0.00011044 | 1403 | 797.5542 | 943 | 0.098415 | 8.8574 | 772 |  | 2686
10663 | SAN RAMON 2102CB | 14232102 | SAN RAMON 2102 | CB | FALSE | 3412.1639 | 2836.6716 | 1.763 | 16 | 0.00010435 | 1543 | 961.0572 | 853 | 0.098349 | 1.5736 | 773 | 0.87 | 758
7571 | BROWNS VALLEY 110193870 | 152921101 | BROWNS VALLEY 1101 | 93870 | FALSE | 54990.4582 | 29826.9597 | 18.5376 | 342 | 6.6942e-05 | 2559 | 1508.5624 | 593 | 0.098287 | 33.6143 | 774 | 0.09 | 1545
9322 | MONTICELLO 1101CB | 43051101 | MONTICELLO 1101 | CB | TRUE | 859.9008 | 859.9008 | 0.53443 | 5 | 0.00010841 | 1440 | 866.0652 | 904 | 0.098274 | 0.49137 | 775 | 0.05 | 1958
5943 | TEMPLETON 2113A10 | 183052113 | TEMPLETON 2113 | A10 | FALSE | 49945.6996 | 49945.6996 | 31.0415 | 264 | 7.3622e-05 | 2377 | 1325.7939 | 671 | 0.098002 | 25.8725 | 776 | 7.4 | 446
5478 | PENRYN 11072706 | 152561107 | PENRYN 1107 | 2706 | FALSE | 23999.9081 | 9304.8867 | 5.783 | 190 | 0.0001407 | 858 | 837.755 | 918 | 0.09785 | 18.5915 | 777 | 0.94 | 743
3757 | WILLITS 1104934 | 42661104 | WILLITS 1104 | 934 | FALSE | 49660.3767 | 49660.3767 | 30.8641 | 279 | 9.3799e-05 | 1799 | 1233.6573 | 711 | 0.097599 | 27.2301 | 778 | 35.78 | 211
7329 | CORRAL 110213498 | 162991102 | CORRAL 1102 | 13498 | FALSE | 1603.6406 | 1585.9579 | 0.98568 | 13 | 0.00013812 | 892 | 567.2293 | 1131 | 0.097071 | 1.2619 | 779 | 0.06 | 1831
6184 | PEORIA 170190090 | 163781701 | PEORIA 1701 | 90090 | FALSE | 48332.111 | 48332.111 | 30.0386 | 168 | 9.2359e-05 | 1833 | 1129.7718 | 764 | 0.09692 | 16.2826 | 780 | 0.05 | 2011
1027 | OILFIELDS 110383158 | 182391103 | OILFIELDS 1103 | 83158 | FALSE | 31398.3782 | 28429.994 | 17.6694 | 132 | 6.3068e-05 | 2679 | 1552.5213 | 577 | 0.09689 | 12.7894 | 781 | 0.06 | 1781
3208 | WILLITS 11032500 | 42661103 | WILLITS 1103 | 2500 | FALSE | 48136.3959 | 48136.3959 | 29.917 | 143 | 8.5236e-05 | 2049 | 1216.4356 | 720 | 0.096773 | 13.8385 | 782 | 0.21 | 1155
9576 | LLAGAS 2104603392 | 83182104 | LLAGAS 2104 | 603392 | FALSE | 5227.4341 | 4685.9835 | 2.9124 | 17 | 5.2363e-05 | 2983 | 1917.7994 | 469 | 0.096621 | 1.6426 | 783 |  | 3382
211 | APPLE HILL 110313312 | 153661103 | APPLE HILL 1103 | 13312 | FALSE | 28501.0245 | 21155.7388 | 13.1484 | 190 | 0.00021994 | 321 | 408.8559 | 1287 | 0.096554 | 18.3453 | 784 | 0.12 | 1376
1106 | BANGOR 11011958 | 103191101 | BANGOR 1101 | 1958 | FALSE | 54465.3426 | 54465.3426 | 33.8504 | 353 | 0.00011848 | 1218 | 944.1299 | 865 | 0.096142 | 33.9382 | 785 | 0.29 | 1022
5073 | LAYTONVILLE 1102CB | 42681102 | LAYTONVILLE 1102 | CB | FALSE | 20899.9329 | 19267.3702 | 11.9747 | 95 | 0.00020717 | 375 | 574.8898 | 1127 | 0.095782 | 9.0993 | 786 | 5.57 | 485
7859 | MOUNTAIN QUARRIES 210135466 | 152282101 | MOUNTAIN QUARRIES 2101 | 35466 | FALSE | 11836.6618 | 11836.6618 | 7.3565 | 82 | 0.00016771 | 578 | 531.3358 | 1171 | 0.095562 | 7.8361 | 787 | 0.06 | 1799
871 | PEORIA 17019811 | 163781701 | PEORIA 1701 | 9811 | FALSE | 14351.9184 | 5776.4657 | 3.5901 | 92 | 8.2868e-05 | 2133 | 845.358 | 914 | 0.095333 | 8.7707 | 788 | 0.03 | 2316
669 | CABRILLO 1103CB | 183101103 | CABRILLO 1103 | CB | TRUE | 7060.6838 | 875.6492 | 0.54422 | 45 | 5.6384e-05 | 2879 | 1585.2096 | 566 | 0.095165 | 4.2824 | 789 | 0.89 | 750
3438 | CALISTOGA 1102CB | 42711102 | CALISTOGA 1102 | CB | TRUE | 3890.2841 | 517.8814 | 0.32187 | 37 | 0.00015375 | 712 | 238.7834 | 1569 | 0.095153 | 3.5207 | 790 | 0.1 | 1501
8923 | SUNOL 1101CB | 14241101 | SUNOL 1101 | CB | FALSE | 9278.0237 | 5281.0095 | 3.2822 | 53 | 6.9821e-05 | 2480 | 949.0975 | 862 | 0.095135 | 5.0422 | 791 | 0.02 | 2553
5883 | SILVERADO 2104632 | 43432104 | SILVERADO 2104 | 632 | FALSE | 29843.7661 | 29492.7895 | 18.3299 | 193 | 0.00011902 | 1207 | 950.7759 | 861 | 0.094959 | 18.327 | 792 | 90.53 | 32
5762 | CHALLENGE 11021064 | 103201102 | CHALLENGE 1102 | 1064 | FALSE | 31650.7422 | 31650.7422 | 19.6711 | 179 | 9.295e-05 | 1824 | 1110.3932 | 771 | 0.094905 | 16.9879 | 793 | 64.19 | 79
847 | CURTIS 17026008 | 163351702 | CURTIS 1702 | 6008 | FALSE | 37504.3181 | 37504.3181 | 23.3091 | 236 | 8.3382e-05 | 2122 | 1032.7499 | 806 | 0.094797 | 22.3721 | 794 | 0.31 | 1010
7905 | CAYETANO 2109CB | 14422109 | CAYETANO 2109 | CB | FALSE | 8828.3789 | 2269.8172 | 1.4107 | 51 | 8.6513e-05 | 2023 | 1197.2249 | 732 | 0.094773 | 4.8334 | 795 | 0.08 | 1602
6145 | OAKHURST 110210100 | 254421102 | OAKHURST 1102 | 10100 | FALSE | 18902.6869 | 16723.3035 | 10.3936 | 142 | 0.0001056 | 1504 | 1406.8011 | 635 | 0.094733 | 13.4521 | 796 | 0.13 | 1337
6083 | MILPITAS 1109XR524 | 82831109 | MILPITAS 1109 | XR524 | FALSE | 17990.142 | 17523.6666 | 10.891 | 59 | 7.365e-05 | 2373 | 1425.9142 | 629 | 0.09443 | 5.5714 | 797 | 0.13 | 1349
370 | UKIAH 1114CB | 42771114 | UKIAH 1114 | CB | FALSE | 14024.7064 | 1067.201 | 0.66327 | 93 | 0.00014666 | 778 | 560.4187 | 1134 | 0.094346 | 8.7742 | 798 | 0.02 | 2531
7085 | MESA 1103854149 | 182821103 | MESA 1103 | 854149 | FALSE | 1703.8848 | 1563.4443 | 0.97169 | 12 | 3.9219e-05 | 3281 | 2116.0059 | 424 | 0.094333 | 1.132 | 799 |  | 3095
8026 | PEORIA 1704CB | 163781704 | PEORIA 1704 | CB | FALSE | 14181.9325 | 13470.2412 | 8.3718 | 64 | 8.6926e-05 | 2014 | 1158.1157 | 750 | 0.094159 | 6.0262 | 800 | 0.04 | 2092
4910 | PUEBLO 2103373667 | 43292103 | PUEBLO 2103 | 373667 | FALSE | 6861.5817 | 5269.4021 | 3.275 | 45 | 0.00010834 | 1444 | 757.3214 | 967 | 0.09414 | 4.2363 | 801 |  | 2927
3504 | MOLINO 1102396 | 42571102 | MOLINO 1102 | 396 | FALSE | 25908.1895 | 25908.1895 | 16.102 | 182 | 0.00013862 | 887 | 571.5533 | 1129 | 0.093951 | 17.099 | 802 | 46.49 | 141
8266 | LAS POSITAS 2108MR182 | 14402108 | LAS POSITAS 2108 | MR182 | FALSE | 11548.6884 | 10768.7759 | 6.6928 | 56 | 6.1377e-05 | 2738 | 1819.6137 | 502 | 0.093921 | 5.2596 | 803 | 0.09 | 1515
6506 | CALAVERAS CEMENT 11014786 | 162211101 | CALAVERAS CEMENT 1101 | 4786 | FALSE | 28973.985 | 28973.985 | 18.0074 | 173 | 9.6661e-05 | 1720 | 894.0898 | 886 | 0.09378 | 16.224 | 804 | 0.23 | 1115
1161 | WYANDOTTE 110777578 | 102911107 | WYANDOTTE 1107 | 77578 | FALSE | 51848.8987 | 34427.9014 | 21.3971 | 389 | 0.00014958 | 742 | 862.3434 | 907 | 0.09328 | 36.2858 | 805 | 0.14 | 1325
5393 | GARBERVILLE 11024744 | 192221102 | GARBERVILLE 1102 | 4744 | FALSE | 32972.1771 | 27938.0536 | 17.3636 | 161 | 0.00026417 | 184 | 386.3695 | 1311 | 0.093231 | 15.0101 | 806 | 0.03 | 2396
5755 | PENRYN 11072704 | 152561107 | PENRYN 1107 | 2704 | FALSE | 9132.5937 | 2300.3426 | 1.4297 | 76 | 0.00016088 | 633 | 611.8282 | 1093 | 0.093023 | 7.0698 | 807 | 0.54 | 874
8038 | WILLITS 1103826 | 42661103 | WILLITS 1103 | 826 | FALSE | 12455.7726 | 12455.7726 | 7.7413 | 89 | 0.00010691 | 1478 | 923.3771 | 872 | 0.092902 | 8.2683 | 808 | 15.71 | 347
5718 | PETALUMA C 1108233646 | 42631108 | PETALUMA C 1108 | 233646 | FALSE | 18091.6284 | 15102.5612 | 9.3863 | 127 | 8.2168e-05 | 2147 | 1174.21 | 744 | 0.092653 | 11.7669 | 809 |  | 2976
7314 | CLARKSVILLE 210575884 | 153612105 | CLARKSVILLE 2105 | 75884 | FALSE | 18035.3275 | 17165.4943 | 10.6684 | 94 | 0.00017444 | 533 | 718.5697 | 1003 | 0.09258 | 8.7025 | 810 | 3.43 | 548
837 | DIAMOND SPRINGS 11071402 | 152261107 | DIAMOND SPRINGS 1107 | 1402 | FALSE | 71104.0432 | 71104.0432 | 44.1915 | 541 | 9.1419e-05 | 1862 | 1211.8423 | 726 | 0.092281 | 49.924 | 811 | 35.4 | 214
1640 | JESSUP 1101CB | 103441101 | JESSUP 1101 | CB | FALSE | 9345.3494 | 2462.2686 | 1.5303 | 66 | 0.00012054 | 1177 | 1190.2745 | 738 | 0.092174 | 6.0835 | 812 | 0.04 | 2090
2558 | PENRYN 1103660 | 152561103 | PENRYN 1103 | 660 | FALSE | 31347.0514 | 16353.7146 | 10.1639 | 233 | 0.00011883 | 1211 | 1011.3875 | 826 | 0.092166 | 21.4747 | 813 | 0.63 | 835
9244 | KERN OIL 110646960 | 252721106 | KERN OIL 1106 | 46960 | FALSE | 3112.6164 | 1465.0556 | 0.91054 | 14 | 5.4278e-05 | 2938 | 2071.3937 | 437 | 0.092145 | 1.29 | 814 | 0.02 | 2539
4181 | MONTICELLO 1101666 | 43051101 | MONTICELLO 1101 | 666 | FALSE | 21923.7063 | 19462.335 | 12.0959 | 90 | 5.9029e-05 | 2805 | 1514.7635 | 588 | 0.092048 | 8.2843 | 815 | 0.87 | 754
8910 | BRIDGEVILLE 110255612 | 192461102 | BRIDGEVILLE 1102 | 55612 | FALSE | 35781.5314 | 35781.5314 | 22.2384 | 93 | 0.00015401 | 707 | 611.9681 | 1092 | 0.090894 | 8.4532 | 816 | 0.12 | 1370
3415 | PARADISE 1104409622 | 102831104 | PARADISE 1104 | 409622 | FALSE | 20757.639 | 20534.7896 | 12.7625 | 156 | 0.00034981 | 90 | 622.0881 | 1080 | 0.090831 | 14.1696 | 817 |  | 2825
4056 | CALAVERAS CEMENT 110113424 | 162211101 | CALAVERAS CEMENT 1101 | 13424 | FALSE | 5801.6622 | 2404.2277 | 1.4942 | 43 | 0.00013059 | 1000 | 649.8195 | 1066 | 0.090714 | 3.9007 | 818 | 0.03 | 2394
345 | COTTONWOOD 1101384360 | 102931101 | COTTONWOOD 1101 | 384360 | FALSE | 10034.7798 | 7892.4211 | 4.9052 | 70 | 9.2299e-05 | 1835 | 1163.0519 | 748 | 0.090426 | 6.3298 | 819 |  | 2667
287 | WHITMORE 11011598 | 103601101 | WHITMORE 1101 | 1598 | FALSE | 53928.0023 | 53928.0023 | 33.5165 | 251 | 9.7528e-05 | 1700 | 806.3409 | 933 | 0.09042 | 22.6955 | 820 | 22.35 | 294
8279 | LOW GAP 110186816 | 192411101 | LOW GAP 1101 | 86816 | FALSE | 7103.5026 | 7103.5026 | 4.4149 | 51 | 0.00023289 | 272 | 393.4562 | 1304 | 0.090319 | 4.6062 | 821 | 6.82 | 458
7426 | SANTA MARIA 1108M18 | 182671108 | SANTA MARIA 1108 | M18 | FALSE | 28757.9291 | 24562.1098 | 15.2655 | 81 | 5.4886e-05 | 2918 | 1831.3141 | 496 | 0.090027 | 7.2922 | 822 | 0.57 | 861
7586 | KONOCTI 1102948 | 43311102 | KONOCTI 1102 | 948 | FALSE | 12598.6878 | 10159.6075 | 6.3142 | 73 | 6.6707e-05 | 2564 | 1385.8323 | 644 | 0.089784 | 6.5542 | 823 | 0.06 | 1788
8787 | GIRVAN 1102212096 | 103401102 | GIRVAN 1102 | 212096 | FALSE | 6500.9175 | 4124.0159 | 2.5631 | 42 | 6.3229e-05 | 2670 | 1654.3016 | 540 | 0.089733 | 3.7688 | 824 |  | 3265
10586 | LOS MOLINOS 1101297862 | 103481101 | LOS MOLINOS 1101 | 297862 | TRUE | 519.2262 | 503.2242 | 0.31276 | 4 | 7.9187e-05 | 2228 | 3345.084 | 219 | 0.089567 | 0.35827 | 825 |  | 3575
6573 | SISQUOC 1103858898 | 182811103 | SISQUOC 1103 | 858898 | FALSE | 31911.4059 | 31551.7735 | 19.6096 | 152 | 4.9929e-05 | 3040 | 1510.095 | 592 | 0.089508 | 13.6052 | 826 |  | 3043
10830 | PETALUMA C 1109373772 | 42631109 | PETALUMA C 1109 | 373772 | TRUE | 28.6691 | 28.6691 | 0.017818 | 2 | 0.00012505 | 1097 | 655.2599 | 1058 | 0.089417 | 0.17883 | 827 | 1.87 | 637
817 | CLOVERDALE 1102570 | 42821102 | CLOVERDALE 1102 | 570 | FALSE | 34272.8021 | 28557.0384 | 17.7483 | 199 | 0.00010582 | 1500 | 921.351 | 874 | 0.089292 | 17.7691 | 828 | 0.22 | 1129
5781 | SAN JOAQUIN #3 11035100 | 252531103 | SAN JOAQUIN #3 1103 | 5100 | FALSE | 34326.3844 | 34326.3844 | 21.334 | 204 | 8.9144e-05 | 1942 | 1331.1763 | 667 | 0.089218 | 18.2004 | 829 | 0.33 | 989
6729 | SAN LUIS OBISPO 110788962 | 182631107 | SAN LUIS OBISPO 1107 | 88962 | FALSE | 6442.5415 | 3996.9259 | 2.4841 | 45 | 4.8649e-05 | 3070 | 1156.9132 | 752 | 0.089174 | 4.0128 | 830 | 0.04 | 2070
5238 | DIAMOND SPRINGS 110656026 | 152261106 | DIAMOND SPRINGS 1106 | 56026 | FALSE | 24339.1905 | 24339.1905 | 15.1269 | 158 | 0.00012905 | 1028 | 717.5714 | 1005 | 0.089061 | 14.0716 | 831 | 0.07 | 1750
4137 | UKIAH 1114528 | 42771114 | UKIAH 1114 | 528 | FALSE | 19817.3234 | 6048.4547 | 3.7591 | 110 | 0.00013971 | 873 | 614.5051 | 1089 | 0.08906 | 9.7966 | 832 | 0.03 | 2395
2145 | CALISTOGA 1101736 | 42711101 | CALISTOGA 1101 | 736 | FALSE | 55772.0682 | 55772.0682 | 34.6626 | 350 | 0.00013305 | 957 | 690.2141 | 1030 | 0.088841 | 31.0945 | 833 | 98.57 | 21
8817 | WYANDOTTE 1105CB | 102911105 | WYANDOTTE 1105 | CB | FALSE | 21689.1163 | 18499.2196 | 11.4973 | 14 | 0.00021618 | 336 | 754.1992 | 970 | 0.088539 | 1.2395 | 834 | 0.04 | 2124
3899 | PEORIA 170510580 | 163781705 | PEORIA 1705 | 10580 | FALSE | 18949.2019 | 12416.9837 | 7.7172 | 129 | 0.00010187 | 1606 | 1422.4147 | 630 | 0.088489 | 11.415 | 835 | 0.05 | 1984
5666 | WOODSIDE 110147872 | 24251101 | WOODSIDE 1101 | 47872 | FALSE | 6709.5897 | 6709.5897 | 4.17 | 52 | 0.00017338 | 538 | 451.2799 | 1248 | 0.088422 | 4.5979 | 836 | 1.21 | 701
7241 | ATASCADERO 1103A14 | 182541103 | ATASCADERO 1103 | A14 | FALSE | 40416.4237 | 40416.4237 | 25.119 | 152 | 7.4204e-05 | 2351 | 1301.8625 | 681 | 0.088418 | 13.4395 | 837 | 0.07 | 1686
878 | FROGTOWN 170275252 | 163451702 | FROGTOWN 1702 | 75252 | FALSE | 98047.1456 | 93174.0996 | 57.9081 | 401 | 7.7651e-05 | 2271 | 1110.9654 | 770 | 0.088153 | 35.3494 | 838 | 0.18 | 1204
4836 | GRASS VALLEY 11031700 | 152031103 | GRASS VALLEY 1103 | 1700 | FALSE | 35014.8434 | 34930.2373 | 21.7093 | 255 | 0.00014818 | 762 | 706.0979 | 1016 | 0.087918 | 22.4191 | 839 | 0.15 | 1281
7987 | BELL 1108339792 | 152701108 | BELL 1108 | 339792 | FALSE | 5788.3897 | 4221.2236 | 2.6235 | 43 | 0.00011358 | 1331 | 632.6218 | 1077 | 0.087729 | 3.7723 | 840 |  | 3181
8725 | LLAGAS 2101984552 | 83182101 | LLAGAS 2101 | 984552 | FALSE | 9221.3481 | 7304.6852 | 4.5399 | 53 | 7.8725e-05 | 2243 | 1388.9327 | 642 | 0.087511 | 4.6381 | 841 |  | 3254
4715 | GIRVAN 110280726 | 103401102 | GIRVAN 1102 | 80726 | FALSE | 29692.476 | 12661.4918 | 7.8692 | 217 | 0.00011841 | 1219 | 698.1741 | 1024 | 0.087369 | 18.9591 | 842 | 0.05 | 2014
5678 | SAN LUIS OBISPO 1102348318 | 182631102 | SAN LUIS OBISPO 1102 | 348318 | TRUE | 597.0392 | 597.0392 | 0.37106 | 6 | 4.521e-05 | 3156 | 2033.0031 | 451 | 0.087346 | 0.52408 | 843 |  | 2972
8497 | BEAR VALLEY 210576694 | 252192105 | BEAR VALLEY 2105 | 76694 | FALSE | 7317.351 | 7317.351 | 4.5478 | 37 | 7.2614e-05 | 2401 | 1607.6376 | 560 | 0.087295 | 3.2299 | 844 | 0.06 | 1907
4933 | RACETRACK 17039190 | 163761703 | RACETRACK 1703 | 9190 | FALSE | 14438.9195 | 14438.9195 | 8.9738 | 104 | 0.00015927 | 649 | 560.2186 | 1135 | 0.087115 | 9.06 | 845 | 0.12 | 1405
10437 | RIO DELL 110275970 | 192251102 | RIO DELL 1102 | 75970 | FALSE | 11378.8384 | 11378.8384 | 7.072 | 33 | 0.0002301 | 284 | 549.4916 | 1145 | 0.08694 | 2.869 | 846 | 0.07 | 1700
3279 | OAKHURST 1101CB | 254421101 | OAKHURST 1101 | CB | FALSE | 4772.9739 | 3724.6766 | 2.3149 | 47 | 0.00012677 | 1067 | 1037.4258 | 802 | 0.086583 | 4.0694 | 847 | 3.02 | 568
6810 | KESWICK 11011590 | 103451101 | KESWICK 1101 | 1590 | FALSE | 10388.8945 | 10388.8945 | 6.4567 | 63 | 0.00013775 | 898 | 828.3749 | 922 | 0.086534 | 5.4516 | 848 | 0.58 | 859
2304 | SAN JOAQUIN #3 1103CB | 252531103 | SAN JOAQUIN #3 1103 | CB | FALSE | 45670.4217 | 45670.4217 | 28.3844 | 294 | 9.5334e-05 | 1751 | 1012.9872 | 821 | 0.086354 | 25.3881 | 849 | 0.47 | 909
7373 | TIVY VALLEY 11077380 | 252941107 | TIVY VALLEY 1107 | 7380 | FALSE | 45386.7416 | 20845.5533 | 12.9556 | 240 | 4.451e-05 | 3175 | 2480.8683 | 345 | 0.086218 | 20.6923 | 850 | 0.07 | 1707
1492 | STILLWATER 110148950 | 103561101 | STILLWATER 1101 | 48950 | FALSE | 20081.7793 | 20081.7793 | 12.4809 | 145 | 0.00013937 | 880 | 612.4235 | 1091 | 0.085979 | 12.467 | 851 | 0.08 | 1608
3172 | RED BLUFF 1105161818 | 103541105 | RED BLUFF 1105 | 161818 | TRUE | 7658.7384 | 212.3638 | 0.13198 | 59 | 5.7073e-05 | 2859 | 1511.2201 | 590 | 0.08588 | 5.0669 | 852 | 0.02 | 2419
5834 | SANTA YNEZ 1102320270 | 182721102 | SANTA YNEZ 1102 | 320270 | FALSE | 27707.7793 | 13648.6049 | 8.4827 | 137 | 5.4419e-05 | 2934 | 1519.0093 | 586 | 0.08574 | 11.7464 | 853 | 0.03 | 2384
742 | MORGAN HILL 2105XR176 | 83242105 | MORGAN HILL 2105 | XR176 | FALSE | 44222.2898 | 36252.5852 | 22.5311 | 309 | 8.4526e-05 | 2077 | 1005.2282 | 831 | 0.085689 | 26.478 | 854 | 0.3 | 1018
8450 | MARTELL 1102CB | 163011102 | MARTELL 1102 | CB | FALSE | 10972.0561 | 9142.0744 | 5.6818 | 69 | 0.00014429 | 809 | 861.7339 | 908 | 0.08567 | 5.9113 | 855 | 0.08 | 1609
3883 | COTATI 1102167726 | 42271102 | COTATI 1102 | 167726 | FALSE | 6114.3744 | 6114.3744 | 3.8001 | 50 | 7.7871e-05 | 2262 | 1006.5075 | 830 | 0.08544 | 4.272 | 856 |  | 2859
10186 | CLAYTON 22159765 | 12022215 | CLAYTON 2215 | 9765 | TRUE | 1507.3257 | 425.4979 | 0.26445 | 16 | 4.0376e-05 | 3257 | 1304.4493 | 680 | 0.085394 | 1.3663 | 857 | 1.11 | 715
5425 | CORNING 110187304 | 103331101 | CORNING 1101 | 87304 | FALSE | 23764.1584 | 4634.8119 | 2.8806 | 100 | 0.00010497 | 1530 | 1066.2761 | 788 | 0.085339 | 8.5339 | 858 | 0.01 | 2567
4113 | PHILO 1101CB | 42601101 | PHILO 1101 | CB | FALSE | 79932.4071 | 51306.3985 | 31.8871 | 469 | 0.00011158 | 1379 | 802.5661 | 939 | 0.085283 | 39.9976 | 859 | 0.15 | 1300
10106 | GEYSERVILLE 1102537096 | 42891102 | GEYSERVILLE 1102 | 537096 | TRUE | 844.1463 | 775.9765 | 0.48227 | 6 | 0.00013769 | 900 | 635.9861 | 1072 | 0.085228 | 0.51137 | 860 |  | 3492
9409 | CLAY 1102CB | 163341102 | CLAY 1102 | CB | FALSE | 3161.2302 | 1492.4904 | 0.92759 | 19 | 0.00014572 | 793 | 421.9203 | 1271 | 0.085217 | 1.6191 | 861 | 0.04 | 2178
6247 | ELK CREEK 11012004 | 102781101 | ELK CREEK 1101 | 2004 | FALSE | 86935.2431 | 40225.06 | 25 | 174 | 5.0473e-05 | 3024 | 1960.2216 | 462 | 0.085175 | 14.8204 | 862 | 0.02 | 2549
2719 | SAN LUIS OBISPO 1104V10 | 182631104 | SAN LUIS OBISPO 1104 | V10 | FALSE | 7811.0705 | 3504.8307 | 2.1783 | 54 | 0.00010776 | 1457 | 473.6801 | 1219 | 0.085103 | 4.5956 | 863 |  | 2796
541 | TEMPLETON 2113R82 | 183052113 | TEMPLETON 2113 | R82 | FALSE | 111857.9563 | 61789.4025 | 38.4024 | 563 | 6.819e-05 | 2530 | 1317.1207 | 675 | 0.084913 | 47.806 | 864 | 0.03 | 2235
7060 | BIG BEND 1102CB | 103751102 | BIG BEND 1102 | CB | FALSE | 27411.8293 | 27411.8293 | 17.0366 | 139 | 0.00012425 | 1113 | 619.8955 | 1081 | 0.084888 | 11.7994 | 865 | 0.48 | 900
7634 | IONE 1101L3141 | 163881101 | IONE 1101 | L3141 | FALSE | 22528.5486 | 22255.8256 | 13.8321 | 97 | 7.5574e-05 | 2322 | 1221.0879 | 717 | 0.084539 | 8.2002 | 866 | 0.09 | 1535
1449 | FORT SEWARD 1122CB | 192321122 | FORT SEWARD 1122 | CB | FALSE | 35287.6178 | 28413.1031 | 17.6589 | 111 | 0.00022836 | 290 | 382.0524 | 1317 | 0.084457 | 9.3748 | 867 | 0.06 | 1910
3137 | MOLINO 1102104 | 42571102 | MOLINO 1102 | 104 | FALSE | 34991.65 | 34991.65 | 21.7475 | 235 | 0.00014639 | 782 | 473.3298 | 1220 | 0.084332 | 19.818 | 868 | 67.59 | 72
4967 | NARROWS 21052748 | 153132105 | NARROWS 2105 | 2748 | FALSE | 31538.4076 | 20831.4864 | 12.9469 | 245 | 0.00018393 | 480 | 692.2861 | 1029 | 0.084145 | 20.6156 | 869 | 0.1 | 1477
9631 | EDENVALE 2107739448 | 82952107 | EDENVALE 2107 | 739448 | FALSE | 3763.2993 | 2860.1443 | 1.7776 | 12 | 4.5704e-05 | 3149 | 1064.5547 | 790 | 0.084104 | 1.0093 | 870 |  | 3393
5449 | PENRYN 110351658 | 152561103 | PENRYN 1103 | 51658 | FALSE | 14039.3789 | 13140.1209 | 8.1666 | 108 | 0.00011684 | 1253 | 818.1348 | 925 | 0.084002 | 9.0722 | 871 | 1.43 | 677
9940 | MILPITAS 110598568 | 82831105 | MILPITAS 1105 | 98568 | TRUE | 2444.4926 | 168.1421 | 0.1045 | 7 | 7.0182e-05 | 2465 | 834.7615 | 919 | 0.083995 | 0.58797 | 872 |  | 3457
4281 | PUEBLO 1105637242 | 43291105 | PUEBLO 1105 | 637242 | FALSE | 35417.2163 | 27085.716 | 16.8339 | 193 | 7.1873e-05 | 2424 | 1184.0184 | 740 | 0.083893 | 16.1913 | 873 |  | 2879
9696 | LAS GALLINAS A 1104507389 | 42991104 | LAS GALLINAS A 1104 | 507389 | TRUE | 305.6652 | 212.3341 | 0.13197 | 4 | 8.9376e-05 | 1934 | 719.0918 | 1002 | 0.083842 | 0.33537 | 874 |  | 3399
3446 | ELK CREEK 11012228 | 102781101 | ELK CREEK 1101 | 2228 | FALSE | 16654.619 | 5410.2105 | 3.3625 | 80 | 5.6416e-05 | 2878 | 1582.2639 | 568 | 0.082955 | 6.6364 | 875 | 0.03 | 2232
2644 | WILLITS 110391948 | 42661103 | WILLITS 1103 | 91948 | FALSE | 11942.5868 | 11942.5868 | 7.4224 | 69 | 0.00010599 | 1494 | 1019.808 | 815 | 0.082927 | 5.7219 | 876 | 0.99 | 733
2263 | SWIFT 2110XR366 | 83392110 | SWIFT 2110 | XR366 | FALSE | 17766.1133 | 13567.8022 | 8.4324 | 129 | 7.1306e-05 | 2437 | 1012.8648 | 822 | 0.082848 | 10.6874 | 877 | 0.21 | 1134
9623 | SANTA YNEZ 1104685160 | 182721104 | SANTA YNEZ 1104 | 685160 | TRUE | 2780.4715 | 943.7591 | 0.58655 | 17 | 5.0437e-05 | 3028 | 1467.3789 | 610 | 0.082766 | 1.407 | 878 |  | 3392
7942 | FULTON 11024994 | 42561102 | FULTON 1102 | 4994 | FALSE | 6920.6464 | 2185.8295 | 1.3585 | 45 | 0.00012652 | 1071 | 520.9041 | 1182 | 0.082765 | 3.7244 | 879 | 0.64 | 830
4041 | FROGTOWN 1702737236 | 163451702 | FROGTOWN 1702 | 737236 | FALSE | 14223.4405 | 14101.6239 | 8.7642 | 88 | 0.00012645 | 1074 | 720.3446 | 999 | 0.082425 | 7.2534 | 880 |  | 2868
4759 | COTATI 110379140 | 42271103 | COTATI 1103 | 79140 | FALSE | 19909.2046 | 15742.3512 | 9.7839 | 154 | 9.382e-05 | 1797 | 973.1017 | 848 | 0.082367 | 12.6845 | 881 | 7.99 | 438
1164 | BEAR VALLEY 2105454432 | 252192105 | BEAR VALLEY 2105 | 454432 | FALSE | 23226.2401 | 23226.2401 | 14.4352 | 112 | 5.5708e-05 | 2898 | 1234.8209 | 710 | 0.08233 | 9.221 | 882 |  | 2714
4634 | SHINGLE SPRINGS 211051790 | 153652110 | SHINGLE SPRINGS 2110 | 51790 | FALSE | 13931.0144 | 12725.5168 | 7.909 | 106 | 0.00015838 | 659 | 660.4485 | 1052 | 0.082229 | 8.7163 | 883 | 0.33 | 990
4491 | CALPELLA 1102144510 | 43411102 | CALPELLA 1102 | 144510 | FALSE | 8266.8346 | 5010.1846 | 3.1138 | 41 | 8.3654e-05 | 2104 | 950.8265 | 860 | 0.08218 | 3.3694 | 884 |  | 2896
3945 | DOBBINS 11015202 | 153741101 | DOBBINS 1101 | 5202 | FALSE | 27474.7329 | 26267.8985 | 16.3256 | 162 | 8.8527e-05 | 1973 | 910.6874 | 881 | 0.082155 | 13.3091 | 885 | 0.12 | 1403
5174 | CALAVERAS CEMENT 110111236 | 162211101 | CALAVERAS CEMENT 1101 | 11236 | FALSE | 31777.9091 | 31777.9091 | 19.7501 | 143 | 0.00011636 | 1262 | 616.8333 | 1086 | 0.081838 | 11.7029 | 886 | 0.05 | 2012
4695 | SILVERADO 21043485 | 43432104 | SILVERADO 2104 | 3485 | FALSE | 2803.9876 | 2803.9876 | 1.7427 | 23 | 0.00011552 | 1286 | 723.112 | 996 | 0.081749 | 1.8802 | 887 |  | 2910
5312 | PETALUMA C 1108632 | 42631108 | PETALUMA C 1108 | 632 | FALSE | 23697.8024 | 23697.8024 | 14.7283 | 81 | 6.7966e-05 | 2537 | 1288.5976 | 686 | 0.081559 | 6.6063 | 888 | 0.05 | 2027
8333 | BEAR VALLEY 21054609 | 252192105 | BEAR VALLEY 2105 | 4609 | FALSE | 7321.9227 | 7321.9227 | 4.5506 | 41 | 3.728e-05 | 3310 | 2145.8949 | 414 | 0.081381 | 3.3366 | 889 | 0.06 | 1911
7354 | JOLON 11027004 | 182981102 | JOLON 1102 | 7004 | FALSE | 31981.9475 | 12745.3246 | 7.9213 | 128 | 5.8428e-05 | 2822 | 1357.6846 | 659 | 0.081062 | 10.3759 | 890 | 0.03 | 2338
4785 | MORGAN HILL 2111XR398 | 83242111 | MORGAN HILL 2111 | XR398 | FALSE | 63835.5147 | 60665.5292 | 37.7039 | 341 | 8.3663e-05 | 2103 | 945.2451 | 864 | 0.080766 | 27.5412 | 891 | 0.67 | 814
9589 | CLAY 11031821 | 163341103 | CLAY 1103 | 1821 | FALSE | 6061.921 | 5767.6056 | 3.5846 | 33 | 6.9086e-05 | 2504 | 1429.8724 | 624 | 0.080483 | 2.6559 | 892 | 0.08 | 1594
1075 | LINCOLN 110195756 | 153701101 | LINCOLN 1101 | 95756 | FALSE | 29109.9093 | 11950.3804 | 7.4272 | 200 | 7.0248e-05 | 2461 | 1033.0935 | 805 | 0.080379 | 16.0759 | 893 | 0.03 | 2343
3754 | PALMER 1101M82 | 183031101 | PALMER 1101 | M82 | FALSE | 23986.1463 | 17447.2632 | 10.8435 | 149 | 4.471e-05 | 3168 | 1573.1869 | 570 | 0.080327 | 11.9687 | 894 | 0.04 | 2147
5126 | CRESCENT MILLS 21012056 | 103132101 | CRESCENT MILLS 2101 | 2056 | FALSE | 10443.0868 | 8069.9513 | 5.0155 | 70 | 0.00011546 | 1289 | 677.9317 | 1037 | 0.080308 | 5.6215 | 895 | 3.29 | 551
7701 | SILVERADO 2102808 | 43432102 | SILVERADO 2102 | 808 | FALSE | 8110.4608 | 4081.7731 | 2.5368 | 39 | 8.0754e-05 | 2186 | 1061.2531 | 791 | 0.0803 | 3.1317 | 896 | 0.09 | 1528
1034 | HOOPA 11013290 | 192401101 | HOOPA 1101 | 3290 | FALSE | 21820.8937 | 21820.8937 | 13.5618 | 135 | 0.00032761 | 105 | 278.5419 | 1474 | 0.080281 | 10.8379 | 897 | 0.08 | 1641
7166 | GANSNER 1101372132 | 103021101 | GANSNER 1101 | 372132 | TRUE | 2259.794 | 673.2222 | 0.41841 | 13 | 0.00010261 | 1583 | 1099.8675 | 775 | 0.08025 | 1.0433 | 898 |  | 3103
9769 | UKIAH 1111807988 | 42771111 | UKIAH 1111 | 807988 | FALSE | 6722.2779 | 6706.2477 | 4.168 | 15 | 0.00010987 | 1413 | 855.2361 | 912 | 0.080023 | 1.2003 | 899 |  | 3415
6682 | OILFIELDS 1103643162 | 182391103 | OILFIELDS 1103 | 643162 | FALSE | 9798.1377 | 5532.3244 | 3.4384 | 41 | 6.7079e-05 | 2555 | 1192.2958 | 736 | 0.079941 | 3.2776 | 900 |  | 3054
10896 | CMC 1102CB | 183111102 | CMC 1102 | CB | TRUE | 581.8342 | 581.8342 | 0.36161 | 5 | 0.00015983 | 644 | 548.9355 | 1146 | 0.079905 | 0.39953 | 901 | 0.03 | 2328
2989 | KONOCTI 11024300 | 43311102 | KONOCTI 1102 | 4300 | FALSE | 43675.508 | 43384.1036 | 26.9634 | 268 | 0.00011959 | 1194 | 736.9291 | 987 | 0.079811 | 21.3893 | 902 | 28.67 | 249
10408 | POSO MOUNTAIN 21011703 | 253642101 | POSO MOUNTAIN 2101 | 1703 | FALSE | 3959.9015 | 1455.5285 | 0.90462 | 7 | 2.6035e-05 | 3487 | 3088.567 | 257 | 0.079525 | 0.55668 | 903 | 0.01 | 2618
6364 | PLACERVILLE 2106935216 | 153082106 | PLACERVILLE 2106 | 935216 | FALSE | 33848.7529 | 33848.7529 | 21.0371 | 204 | 0.00011214 | 1365 | 509.4897 | 1191 | 0.079474 | 16.2127 | 904 |  | 3025
4098 | WYANDOTTE 11071510 | 102911107 | WYANDOTTE 1107 | 1510 | FALSE | 41028.1557 | 41028.1557 | 25.4992 | 243 | 8.893e-05 | 1952 | 939.2458 | 866 | 0.079411 | 19.297 | 905 | 0.18 | 1216
7076 | CLARKSVILLE 210419632 | 153612104 | CLARKSVILLE 2104 | 19632 | FALSE | 14659.9971 | 8997.9268 | 5.5922 | 110 | 0.00013387 | 944 | 1009.1241 | 828 | 0.07935 | 8.7285 | 906 | 23.44 | 286
1230 | TEMPLETON 2113A08 | 183052113 | TEMPLETON 2113 | A08 | FALSE | 39406.6597 | 16842.5186 | 10.4677 | 257 | 7.6018e-05 | 2308 | 953.5418 | 857 | 0.079335 | 20.3891 | 907 | 0.05 | 2006
5155 | FOOTHILL 1101CB | 182951101 | FOOTHILL 1101 | CB | FALSE | 35256.7174 | 21554.4713 | 13.3962 | 149 | 5.7418e-05 | 2852 | 1255.3202 | 698 | 0.079316 | 11.8181 | 908 | 3.17 | 557
2049 | FRUITLAND 1141CB | 192311141 | FRUITLAND 1141 | CB | FALSE | 5135.5453 | 5135.5453 | 3.1918 | 17 | 0.00032833 | 104 | 166.3867 | 1733 | 0.079299 | 1.3481 | 909 | 0.73 | 794
4771 | OCEANO 1104Q12 | 182601104 | OCEANO 1104 | Q12 | FALSE | 25798.2458 | 18203.0478 | 11.3133 | 142 | 5.3235e-05 | 2958 | 1483.0103 | 602 | 0.079257 | 11.2544 | 910 | 0.12 | 1401
10844 | SPRING GAP 1702188426 | 162831702 | SPRING GAP 1702 | 188426 | TRUE | 4.572 | 4.572 | 0.0028415 | 1 | 0.00011833 | 1221 | 665.6862 | 1046 | 0.078773 | 0.078773 | 911 |  | 3613
1175 | HIGGINS 11044281 | 152691104 | HIGGINS 1104 | 4281 | FALSE | 21439.832 | 21439.832 | 13.3249 | 138 | 8.4234e-05 | 2085 | 980.9559 | 844 | 0.078646 | 10.8532 | 912 | 0.09 | 1527
9778 | HIGGINS 11097863 | 152691109 | HIGGINS 1109 | 7863 | FALSE | 6797.0988 | 6797.0988 | 4.2244 | 42 | 6.1162e-05 | 2744 | 1254.5183 | 699 | 0.078616 | 3.3019 | 913 | 0.06 | 1859
6230 | MONTICELLO 110193384 | 43051101 | MONTICELLO 1101 | 93384 | FALSE | 27406.0322 | 25967.2197 | 16.1387 | 101 | 6.3629e-05 | 2660 | 1407.9794 | 632 | 0.078583 | 7.9369 | 914 | 0.06 | 1857
9152 | MIDDLETOWN 11011314 | 43141101 | MIDDLETOWN 1101 | 1314 | FALSE | 1489.219 | 1489.219 | 0.92556 | 13 | 0.00014408 | 813 | 554.638 | 1141 | 0.078235 | 1.0171 | 915 | 7.88 | 439
10292 | BIG MEADOWS 21012248 | 102812101 | BIG MEADOWS 2101 | 2248 | FALSE | 14727.9744 | 14727.9744 | 9.1535 | 28 | 6.5811e-05 | 2594 | 1037.9427 | 801 | 0.077859 | 2.18 | 916 | 0.05 | 1922
3275 | OCEANO 1104Q10 | 182601104 | OCEANO 1104 | Q10 | FALSE | 38031.0006 | 38031.0006 | 23.6364 | 289 | 6.4596e-05 | 2621 | 1216.6013 | 719 | 0.077836 | 22.4946 | 917 | 7.07 | 452
5179 | HARTLEY 1102CB | 43211102 | HARTLEY 1102 | CB | FALSE | 18838.7982 | 5515.7018 | 3.428 | 135 | 0.00010957 | 1419 | 752.8216 | 973 | 0.077778 | 10.5 | 918 | 0.02 | 2544
8256 | MORGAN HILL 2105XR268 | 83242105 | MORGAN HILL 2105 | XR268 | FALSE | 12802.5937 | 12802.5937 | 7.9569 | 61 | 0.00011557 | 1284 | 557.5427 | 1138 | 0.077596 | 4.7333 | 919 | 0.46 | 913
1037 | MIDDLETOWN 11021312 | 43141102 | MIDDLETOWN 1102 | 1312 | FALSE | 15822.8795 | 15822.8795 | 9.834 | 120 | 0.00013526 | 925 | 772.6153 | 957 | 0.077577 | 9.3092 | 920 | 0.15 | 1291
3607 | OCEANO 1104V38 | 182601104 | OCEANO 1104 | V38 | FALSE | 27926.3564 | 19405.5321 | 12.0606 | 212 | 7.3599e-05 | 2379 | 651.082 | 1062 | 0.077544 | 16.4392 | 921 | 0.17 | 1245
9877 | CLOVERDALE 1102307342 | 42821102 | CLOVERDALE 1102 | 307342 | TRUE | 573.1034 | 354.0238 | 0.22003 | 6 | 0.00013565 | 923 | 341.2059 | 1386 | 0.077416 | 0.46449 | 922 |  | 3441
3974 | FITCH MOUNTAIN 111324550 | 42751113 | FITCH MOUNTAIN 1113 | 24550 | FALSE | 34688.2788 | 17797.4846 | 11.0612 | 203 | 9.3917e-05 | 1795 | 616.7423 | 1087 | 0.077338 | 15.6996 | 923 | 0.07 | 1711
962 | MIDDLETOWN 1102514 | 43141102 | MIDDLETOWN 1102 | 514 | FALSE | 8494.876 | 5391.2208 | 3.3507 | 71 | 0.00014873 | 755 | 482.2809 | 1214 | 0.077302 | 5.4884 | 924 | 0.09 | 1537
10365 | CURTIS 170349746 | 163351703 | CURTIS 1703 | 49746 | TRUE | 601.9007 | 601.9007 | 0.37408 | 3 | 0.00034014 | 97 | 221.8686 | 1601 | 0.077172 | 0.23152 | 925 | 0.04 | 2076
3098 | PETALUMA C 1108630 | 42631108 | PETALUMA C 1108 | 630 | FALSE | 6902.8394 | 2654.0652 | 1.6495 | 55 | 7.7866e-05 | 2263 | 873.6447 | 897 | 0.077168 | 4.2442 | 926 | 0.03 | 2363
6234 | SAN JUSTO 1101201311 | 183181101 | SAN JUSTO 1101 | 201311 | FALSE | 17668.9636 | 12645.7551 | 7.8594 | 108 | 6.4312e-05 | 2634 | 1215.4291 | 722 | 0.077053 | 8.3218 | 927 |  | 3015
6221 | GARBERVILLE 110135706 | 192221101 | GARBERVILLE 1101 | 35706 | FALSE | 16269.027 | 16269.027 | 10.1113 | 97 | 0.00041981 | 62 | 185.2954 | 1670 | 0.076898 | 7.4591 | 928 | 4.82 | 505
2802 | PENRYN 11072410 | 152561107 | PENRYN 1107 | 2410 | FALSE | 12099.1952 | 5248.3008 | 3.2618 | 96 | 0.00011208 | 1366 | 705.3971 | 1019 | 0.076748 | 7.3678 | 929 | 0.05 | 1959
8295 | COTATI 110387402 | 42271103 | COTATI 1103 | 87402 | FALSE | 18273.7697 | 18273.7697 | 11.3572 | 42 | 9.1928e-05 | 1846 | 973.3911 | 847 | 0.07664 | 3.2189 | 930 | 1.23 | 698
10268 | TEJON 11023760 | 252931102 | TEJON 1102 | 3760 | FALSE | 10446.6343 | 10415.8967 | 6.4735 | 6 | 4.6244e-05 | 3131 | 4483.9501 | 110 | 0.076506 | 0.45904 | 931 | 0.03 | 2370
10279 | VOLTA 1102CB | 102541102 | VOLTA 1102 | CB | FALSE | 5307.8327 | 5307.8327 | 3.2988 | 25 | 0.0001265 | 1072 | 430.0286 | 1260 | 0.076253 | 1.9063 | 932 | 12.67 | 370
9092 | FORT ROSS 11214614 | 42851121 | FORT ROSS 1121 | 4614 | FALSE | 20206.8972 | 20206.8972 | 12.5587 | 95 | 0.00011071 | 1396 | 701.2564 | 1022 | 0.075773 | 7.1985 | 933 |  | 3306
3923 | AUBERRY 110137536 | 254151101 | AUBERRY 1101 | 37536 | FALSE | 8687.6907 | 8687.6907 | 5.3994 | 60 | 4.0037e-05 | 3267 | 1761.4133 | 511 | 0.075515 | 4.5309 | 934 | 0.07 | 1729
5756 | CABRILLO 11031437 | 183101103 | CABRILLO 1103 | 1437 | FALSE | 7854.9148 | 4577.3445 | 2.8448 | 39 | 5.9276e-05 | 2795 | 1361.2842 | 657 | 0.075332 | 2.9379 | 935 | 0.03 | 2404
6109 | FITCH MOUNTAIN 1113583202 | 42751113 | FITCH MOUNTAIN 1113 | 583202 | FALSE | 15783.8472 | 7874.8461 | 4.8942 | 106 | 0.00010066 | 1631 | 594.6514 | 1106 | 0.075101 | 7.9607 | 936 | 0.05 | 2004
4163 | WILLITS 1103538 | 42661103 | WILLITS 1103 | 538 | FALSE | 10176.8073 | 10176.8073 | 6.3249 | 48 | 6.409e-05 | 2642 | 1480.7363 | 603 | 0.074937 | 3.597 | 937 | 2.14 | 620
9780 | SONOMA 1107854266 | 42721107 | SONOMA 1107 | 854266 | TRUE | 966.2653 | 321.4105 | 0.19976 | 6 | 9.5722e-05 | 1736 | 1072.2651 | 785 | 0.074827 | 0.44896 | 938 |  | 3418
260 | BRUNSWICK 11067099 | 152481106 | BRUNSWICK 1106 | 7099 | FALSE | 12439.4387 | 12439.4387 | 7.7312 | 83 | 0.00011588 | 1273 | 664.3931 | 1047 | 0.074794 | 6.2079 | 939 | 0.28 | 1036
3084 | GEYSERVILLE 1102274 | 42891102 | GEYSERVILLE 1102 | 274 | FALSE | 29743.739 | 10398.2127 | 6.4625 | 173 | 0.00011599 | 1270 | 494.2707 | 1207 | 0.074787 | 12.9382 | 940 | 1.24 | 695
6342 | MADISON 21011606 | 63172101 | MADISON 2101 | 1606 | TRUE | 42761.0948 | 254.3531 | 0.15808 | 280 | 7.0898e-05 | 2446 | 1248.3017 | 701 | 0.074511 | 20.863 | 941 | 0.02 | 2551
10492 | DRUM 1101CB | 152321101 | DRUM 1101 | CB | FALSE | 3483.5782 | 3483.5782 | 2.1651 | 16 | 0.00013085 | 995 | 558.6934 | 1136 | 0.074456 | 1.1913 | 942 | 21.08 | 302
874 | RISING RIVER 1101CB | 103551101 | RISING RIVER 1101 | CB | FALSE | 21509.9694 | 15956.2359 | 9.9169 | 121 | 5.192e-05 | 2995 | 1288.0652 | 687 | 0.074106 | 8.9669 | 943 | 0.03 | 2320
8386 | PEORIA 1705999 | 163781705 | PEORIA 1705 | 999 | FALSE | 3715.0604 | 3715.0604 | 2.3089 | 22 | 0.00010639 | 1488 | 1017.494 | 818 | 0.074075 | 1.6297 | 944 | 0.09 | 1529
7502 | FITCH MOUNTAIN 11136751 | 42751113 | FITCH MOUNTAIN 1113 | 6751 | FALSE | 36483.9202 | 36483.9202 | 22.6749 | 139 | 0.00018185 | 499 | 410.6545 | 1284 | 0.073927 | 10.2759 | 945 | 39.14 | 190
5338 | SAN JOAQUIN #3 1102CB | 252531102 | SAN JOAQUIN #3 1102 | CB | FALSE | 15601.4012 | 15601.4012 | 9.6963 | 97 | 0.00011323 | 1340 | 789.9349 | 952 | 0.073848 | 7.1632 | 946 | 0.18 | 1203
7052 | CALISTOGA 1101134232 | 42711101 | CALISTOGA 1101 | 134232 | FALSE | 11553.3534 | 2618.9112 | 1.6277 | 89 | 0.0001535 | 717 | 426.3987 | 1264 | 0.0737 | 6.5593 | 947 |  | 3092
10249 | SILVERADO 2102CB | 43432102 | SILVERADO 2102 | CB | TRUE | 2722.4304 | 952.8122 | 0.59218 | 22 | 0.00019758 | 405 | 236.9089 | 1576 | 0.073682 | 1.621 | 948 | 0.13 | 1352
6791 | CABRILLO 1104Y24 | 183101104 | CABRILLO 1104 | Y24 | FALSE | 31605.3339 | 30845.6135 | 19.1707 | 91 | 6.8807e-05 | 2514 | 1387.2959 | 643 | 0.073569 | 6.6947 | 949 | 0.26 | 1061
3606 | HORSESHOE 1101CB | 152571101 | HORSESHOE 1101 | CB | TRUE | 6455.7985 | 567.3027 | 0.35258 | 55 | 0.00018028 | 511 | 272.2112 | 1489 | 0.073561 | 4.0458 | 950 | 0.64 | 831
2673 | PUEBLO 2102792 | 43292102 | PUEBLO 2102 | 792 | FALSE | 33585.8452 | 31119.1615 | 19.3407 | 180 | 9.905e-05 | 1667 | 711.86 | 1012 | 0.073389 | 13.2101 | 951 | 87.74 | 36
4637 | SAN LUIS OBISPO 1104V40 | 182631104 | SAN LUIS OBISPO 1104 | V40 | FALSE | 37151.701 | 23652.2282 | 14.7 | 194 | 7.9558e-05 | 2220 | 1050.089 | 797 | 0.073389 | 14.2374 | 952 | 0.06 | 1795
2241 | CURTIS 170247488 | 163351702 | CURTIS 1702 | 47488 | FALSE | 33425.2179 | 30588.7641 | 19.011 | 207 | 0.00011402 | 1320 | 706.1851 | 1015 | 0.07338 | 15.1897 | 953 | 0.19 | 1176
9651 | PURISIMA 1101Y44 | 182971101 | PURISIMA 1101 | Y44 | FALSE | 18687.8674 | 16745.9311 | 10.4077 | 45 | 6.0111e-05 | 2770 | 1213.3424 | 724 | 0.073295 | 3.2983 | 954 | 0.1 | 1484
1008 | TEMPLETON 2113A70 | 183052113 | TEMPLETON 2113 | A70 | FALSE | 107377.7331 | 39764.0285 | 24.7135 | 659 | 6.9565e-05 | 2486 | 1197.409 | 731 | 0.073157 | 48.2106 | 955 | 3.57 | 542
3782 | AUBERRY 1101R322 | 254151101 | AUBERRY 1101 | R322 | FALSE | 12336.4699 | 12336.4699 | 7.6672 | 44 | 3.5123e-05 | 3349 | 2118.7775 | 422 | 0.073065 | 3.2149 | 956 | 0.06 | 1886
700 | MERCED FALLS 11029460 | 252811102 | MERCED FALLS 1102 | 9460 | FALSE | 18052.5322 | 17926.192 | 11.1412 | 91 | 8.3561e-05 | 2112 | 856.971 | 910 | 0.073014 | 6.6443 | 957 | 0.01 | 2611
1286 | CURTIS 170384944 | 163351703 | CURTIS 1703 | 84944 | FALSE | 93674.3078 | 93674.3078 | 58.219 | 439 | 7.7782e-05 | 2268 | 921.9165 | 873 | 0.072725 | 31.9262 | 958 |  | 2719
8476 | ALTO 1124810594 | 42031124 | ALTO 1124 | 810594 | TRUE | 1080.6364 | 899.4073 | 0.55899 | 6 | 0.0001145 | 1307 | 459.6008 | 1235 | 0.072684 | 0.4361 | 959 |  | 3228
1350 | PENRYN 1107CB | 152561107 | PENRYN 1107 | CB | FALSE | 25933.7558 | 8735.2446 | 5.429 | 200 | 0.00014636 | 784 | 521.6714 | 1181 | 0.072647 | 14.5295 | 960 | 0.55 | 869
10196 | SANTA YNEZ 1101980192 | 182721101 | SANTA YNEZ 1101 | 980192 | FALSE | 6178.6453 | 6178.6453 | 3.8401 | 19 | 3.4326e-05 | 3362 | 2382.3266 | 363 | 0.072592 | 1.3793 | 961 |  | 3513
4126 | VACAVILLE 1104CB | 63601104 | VACAVILLE 1104 | CB | TRUE | 4213.006 | 696.6837 | 0.43299 | 36 | 6.8096e-05 | 2534 | 412.1878 | 1283 | 0.07222 | 2.5999 | 962 | 0.06 | 1816
6142 | JOLON 1103CB | 182981103 | JOLON 1103 | CB | FALSE | 29664.4521 | 21174.1488 | 13.1598 | 91 | 0.00013717 | 905 | 720.7685 | 998 | 0.072102 | 6.5613 | 963 | 0.02 | 2565
4505 | LOW GAP 11014086 | 192411101 | LOW GAP 1101 | 4086 | FALSE | 18494.2051 | 18494.2051 | 11.4942 | 66 | 0.00012787 | 1052 | 634.8288 | 1073 | 0.072098 | 4.7585 | 964 | 0.12 | 1393
5220 | COTATI 1103132 | 42271103 | COTATI 1103 | 132 | FALSE | 40702.0776 | 40702.0776 | 25.2965 | 184 | 7.3728e-05 | 2369 | 1030.4196 | 808 | 0.071994 | 13.2468 | 965 | 4.02 | 529
2886 | VOLTA 11011596 | 102541101 | VOLTA 1101 | 1596 | FALSE | 35104.5465 | 35104.5465 | 21.8176 | 132 | 6.0424e-05 | 2763 | 1180.3203 | 741 | 0.071922 | 9.4937 | 966 | 0.01 | 2583
7748 | PEORIA 170413490 | 163781704 | PEORIA 1704 | 13490 | FALSE | 8773.504 | 6875.4256 | 4.2731 | 49 | 0.00015838 | 660 | 538.4381 | 1161 | 0.071878 | 3.522 | 967 | 0.05 | 1975
1885 | OREGON TRAIL 110249144 | 103521102 | OREGON TRAIL 1102 | 49144 | FALSE | 34128.6869 | 29574.1503 | 18.3805 | 169 | 0.00016343 | 606 | 803.7485 | 937 | 0.071512 | 12.0855 | 968 | 0.08 | 1646
3676 | COTTONWOOD 1101CB | 102931101 | COTTONWOOD 1101 | CB | TRUE | 26588.5909 | 184.0196 | 0.11437 | 188 | 9.7905e-05 | 1694 | 539.3221 | 1159 | 0.0715 | 13.442 | 969 | 0.02 | 2564
7714 | FROGTOWN 17027134 | 163451702 | FROGTOWN 1702 | 7134 | FALSE | 37777.9012 | 32518.1243 | 20.2101 | 172 | 9.5256e-05 | 1759 | 696.6949 | 1025 | 0.071297 | 12.2631 | 970 | 0.09 | 1546
4319 | MESA 11016111 | 182821101 | MESA 1101 | 6111 | FALSE | 41513.5486 | 39023.9015 | 24.2535 | 202 | 4.9757e-05 | 3042 | 1337.456 | 665 | 0.071153 | 14.3729 | 971 | 9.09 | 413
5571 | CLEAR LAKE 1101740076 | 42141101 | CLEAR LAKE 1101 | 740076 | TRUE | 14283.4902 | 632.3767 | 0.39302 | 106 | 0.00010531 | 1512 | 793.8066 | 947 | 0.071071 | 7.5335 | 972 |  | 2963
9268 | OLETA 1102799924 | 163541102 | OLETA 1102 | 799924 | TRUE | 621.6151 | 621.6151 | 0.38634 | 4 | 0.00011059 | 1397 | 1327.4203 | 669 | 0.070818 | 0.28327 | 973 |  | 3334
1141 | BELL 1109724884 | 152701109 | BELL 1109 | 724884 | FALSE | 22726.0215 | 22589.092 | 14.0392 | 167 | 0.00017254 | 546 | 443.793 | 1254 | 0.070791 | 11.822 | 974 |  | 2712
9406 | EDENVALE 2107469810 | 82952107 | EDENVALE 2107 | 469810 | FALSE | 9545.8932 | 3464.1714 | 2.153 | 14 | 8.3298e-05 | 2125 | 778.0104 | 955 | 0.070672 | 0.98941 | 975 |  | 3354
2788 | WYANDOTTE 1110980944 | 102911110 | WYANDOTTE 1110 | 980944 | FALSE | 26900.3072 | 16783.2453 | 10.4309 | 198 | 0.00019807 | 404 | 366.1605 | 1345 | 0.070566 | 13.9721 | 976 |  | 2798
3339 | JESSUP 110276068 | 103441102 | JESSUP 1102 | 76068 | FALSE | 31093.7701 | 27642.9269 | 17.1802 | 232 | 7.7128e-05 | 2284 | 1055.6938 | 794 | 0.070348 | 16.3207 | 977 | 6.25 | 470
6626 | CLAY 1101CB | 163341101 | CLAY 1101 | CB | TRUE | 4411.9174 | 914.1112 | 0.56812 | 33 | 8.0383e-05 | 2194 | 401.4638 | 1294 | 0.070136 | 2.3145 | 978 |  | 3048
9158 | COVELO 1101306476 | 43061101 | COVELO 1101 | 306476 | FALSE | 16292.4669 | 3106.377 | 1.9306 | 49 | 0.00010648 | 1486 | 598.7531 | 1101 | 0.069853 | 3.4228 | 979 |  | 3316
5752 | MONTICELLO 110165454 | 43051101 | MONTICELLO 1101 | 65454 | FALSE | 3114.2101 | 2176.3172 | 1.3526 | 23 | 6.0844e-05 | 2754 | 1192.0123 | 737 | 0.069594 | 1.6007 | 980 | 2.09 | 622
2727 | OREGON TRAIL 11031500 | 103521103 | OREGON TRAIL 1103 | 1500 | FALSE | 41880.4686 | 41880.4686 | 26.0289 | 261 | 0.00012847 | 1038 | 750.2992 | 975 | 0.069495 | 18.1383 | 981 | 0.21 | 1153
10741 | HALF MOON BAY 11038920 | 24101103 | HALF MOON BAY 1103 | 8920 | TRUE | 158.1242 | 158.1242 | 0.098275 | 2 | 0.00017718 | 518 | 499.4912 | 1200 | 0.069477 | 0.13895 | 982 | 0.19 | 1196
2684 | BEAR VALLEY 210110000 | 252192101 | BEAR VALLEY 2101 | 10000 | FALSE | 53656.1229 | 47097.1904 | 29.2711 | 230 | 6.3422e-05 | 2664 | 1330.8242 | 668 | 0.069198 | 15.9156 | 983 | 0.02 | 2464
1190 | OCEANO 1104V36 | 182601104 | OCEANO 1104 | V36 | FALSE | 21377.0625 | 18028.895 | 11.205 | 150 | 6.1929e-05 | 2723 | 1033.145 | 804 | 0.069118 | 10.3677 | 984 | 6.65 | 464
9260 | DIAMOND SPRINGS 110777086 | 152261107 | DIAMOND SPRINGS 1107 | 77086 | FALSE | 6051.2822 | 4371.5846 | 2.717 | 47 | 0.00020917 | 363 | 405.3593 | 1291 | 0.068998 | 3.2429 | 985 |  | 3331
87 | CORNING 110185152 | 103331101 | CORNING 1101 | 85152 | FALSE | 37332.1384 | 37332.1384 | 23.2021 | 279 | 4.413e-05 | 3188 | 1657.8134 | 539 | 0.068983 | 19.2463 | 986 | 8.2 | 433
2893 | UKIAH 1114544 | 42771114 | UKIAH 1114 | 544 | TRUE | 16214.8056 | 786.2676 | 0.48867 | 98 | 8.9779e-05 | 1918 | 761.7873 | 963 | 0.068781 | 6.7406 | 987 |  | 2803
69 | BROWNS VALLEY 110197188 | 152921101 | BROWNS VALLEY 1101 | 97188 | FALSE | 10919.7899 | 10919.7899 | 6.7867 | 71 | 0.00011852 | 1217 | 794.0069 | 946 | 0.068613 | 4.8715 | 988 | 0.06 | 1870
1342 | AUBERRY 1101R2838 | 254151101 | AUBERRY 1101 | R2838 | FALSE | 32896.73 | 32896.73 | 20.4455 | 210 | 3.7309e-05 | 3308 | 2069.6718 | 438 | 0.068544 | 14.3942 | 989 | 0.21 | 1136
9647 | GARCIA 0401CB | 43040401 | GARCIA 0401 | CB | TRUE | 46.711 | 46.711 | 0.029031 | 1 | 0.00015165 | 723 | 451.5011 | 1247 | 0.068469 | 0.068469 | 990 | 4.71 | 509
2407 | FROGTOWN 1702835115 | 163451702 | FROGTOWN 1702 | 835115 | FALSE | 29192.1081 | 29192.1081 | 18.143 | 191 | 7.8182e-05 | 2253 | 868.4883 | 902 | 0.068398 | 13.0639 | 991 |  | 2775
3939 | ZACA 1101Y70 | 182681101 | ZACA 1101 | Y70 | FALSE | 13947.1347 | 10839.1211 | 6.7366 | 61 | 5.1111e-05 | 3011 | 1300.1446 | 683 | 0.068291 | 4.1658 | 992 | 0.02 | 2489
3966 | SAN BENITO 2101295566 | 182742101 | SAN BENITO 2101 | 295566 | TRUE | 3409.6411 | 751.534 | 0.46708 | 18 | 5.22e-05 | 2987 | 1215.0443 | 723 | 0.068263 | 1.2287 | 993 |  | 2864
1800 | BANGOR 11011804 | 103191101 | BANGOR 1101 | 1804 | FALSE | 69024.1301 | 69024.1301 | 42.8988 | 394 | 0.00011734 | 1239 | 495.1119 | 1205 | 0.068197 | 26.8697 | 994 | 0.15 | 1295
1078 | BIG MEADOWS 21012260 | 102812101 | BIG MEADOWS 2101 | 2260 | FALSE | 36303.3353 | 25414.2279 | 15.795 | 185 | 7.1484e-05 | 2433 | 1004.259 | 833 | 0.067786 | 12.5404 | 995 | 0.08 | 1667
8083 | ANDERSON 1101583708 | 103261101 | ANDERSON 1101 | 583708 | FALSE | 1263.0794 | 1011.3641 | 0.62857 | 11 | 9.3798e-05 | 1800 | 952.2243 | 858 | 0.067762 | 0.74538 | 996 |  | 3189
6638 | SAN RAMON 2117CB | 14232117 | SAN RAMON 2117 | CB | FALSE | 2698.3212 | 1098.894 | 0.68297 | 23 | 9.8521e-05 | 1678 | 430.579 | 1258 | 0.067722 | 1.5576 | 997 | 0.47 | 908
7538 | CABRILLO 1103Y46 | 183101103 | CABRILLO 1103 | Y46 | FALSE | 76660.9296 | 50653.8838 | 31.4816 | 277 | 4.2068e-05 | 3223 | 1429.3656 | 626 | 0.067522 | 18.7037 | 998 | 0.13 | 1364
4175 | MARTELL 1101CB | 163011101 | MARTELL 1101 | CB | FALSE | 21488.1146 | 9459.2642 | 5.879 | 171 | 0.00014623 | 785 | 382.8028 | 1314 | 0.067405 | 11.5263 | 999 | 0.05 | 1971
9619 | PETALUMA C 1108456397 | 42631108 | PETALUMA C 1108 | 456397 | FALSE | 2239.0721 | 2239.0721 | 1.3916 | 19 | 9.783e-05 | 1696 | 785.4652 | 954 | 0.067328 | 1.2792 | 1000 |  | 3391
3701 | FRENCH GULCH 1101CB | 103381101 | FRENCH GULCH 1101 | CB | FALSE | 3697.5337 | 3697.5337 | 2.298 | 32 | 0.00012582 | 1082 | 762.0604 | 962 | 0.067293 | 2.1534 | 1001 | 0.05 | 1960
4093 | RED BLUFF 1105146070 | 103541105 | RED BLUFF 1105 | 146070 | FALSE | 22680.3921 | 20479.5896 | 12.7281 | 167 | 6.6917e-05 | 2560 | 1071.9697 | 786 | 0.067012 | 11.191 | 1002 |  | 2871
1562 | LAYTONVILLE 110264908 | 42681102 | LAYTONVILLE 1102 | 64908 | FALSE | 10254.7707 | 6238.0239 | 3.877 | 84 | 0.00035803 | 84 | 246.1325 | 1550 | 0.066995 | 5.6276 | 1003 | 0.84 | 767
7452 | SAN RAMON 210853732 | 14232108 | SAN RAMON 2108 | 53732 | FALSE | 12542.8 | 12542.8 | 7.7954 | 77 | 9.701e-05 | 1714 | 766.0355 | 959 | 0.066862 | 5.1484 | 1004 | 17.55 | 332
509 | CALISTOGA 110143924 | 42711101 | CALISTOGA 1101 | 43924 | FALSE | 15096.7446 | 12523.7999 | 7.7836 | 107 | 0.00015399 | 708 | 446.2971 | 1252 | 0.066852 | 7.1532 | 1005 | 91.99 | 30
2808 | PASO ROBLES 1104P02 | 182611104 | PASO ROBLES 1104 | P02 | TRUE | 11656.6661 | 515.0322 | 0.32009 | 93 | 5.0919e-05 | 3016 | 803.9256 | 936 | 0.06682 | 6.2143 | 1006 | 0.32 | 993
6977 | CLOVERDALE 1102172096 | 42821102 | CLOVERDALE 1102 | 172096 | TRUE | 1240.5827 | 425.5098 | 0.26446 | 12 | 0.00013435 | 939 | 425.6324 | 1267 | 0.06657 | 0.79884 | 1007 |  | 3077
6400 | PHILO 1102CB | 42601102 | PHILO 1102 | CB | FALSE | 20191.5411 | 12387.7147 | 7.699 | 131 | 0.00018717 | 460 | 356.2256 | 1362 | 0.06648 | 8.7089 | 1008 | 0.06 | 1904
1390 | CURTIS 170539256 | 163351705 | CURTIS 1705 | 39256 | FALSE | 42581.0612 | 42581.0612 | 26.4643 | 287 | 0.00012638 | 1077 | 694.1209 | 1026 | 0.066296 | 19.0271 | 1009 | 0.26 | 1068
9080 | SUMMIT 110249484 | 152591102 | SUMMIT 1102 | 49484 | FALSE | 4257.4421 | 4257.4421 | 2.646 | 27 | 0.000124 | 1121 | 880.5018 | 890 | 0.06627 | 1.7893 | 1010 | 0.02 | 2543
493 | BRUNSWICK 11102664 | 152481110 | BRUNSWICK 1110 | 2664 | FALSE | 17552.7674 | 12910.8902 | 8.0242 | 132 | 0.00019724 | 409 | 283.8161 | 1468 | 0.066185 | 8.7364 | 1011 | 7.85 | 440
6828 | SILVERADO 210298998 | 43432102 | SILVERADO 2102 | 98998 | TRUE | 20001.4994 | 118.1019 | 0.073401 | 136 | 8.5457e-05 | 2044 | 370.2201 | 1337 | 0.066014 | 8.9779 | 1012 | 0.02 | 2466
828 | ATASCADERO 1103A18 | 182541103 | ATASCADERO 1103 | A18 | FALSE | 29115.6622 | 14189.3642 | 8.8187 | 188 | 6.7022e-05 | 2556 | 932.8875 | 868 | 0.065994 | 12.4068 | 1013 | 1.58 | 663
7881 | CALISTOGA 1102141073 | 42711102 | CALISTOGA 1102 | 141073 | FALSE | 3422.9373 | 1996.4523 | 1.2408 | 27 | 0.00018845 | 450 | 208.8541 | 1621 | 0.065722 | 1.7745 | 1014 |  | 3174
5591 | CURTIS 17029220 | 163351702 | CURTIS 1702 | 9220 | FALSE | 18356.5403 | 17704.0281 | 11.0031 | 123 | 0.00012861 | 1036 | 658.7055 | 1055 | 0.065661 | 8.0763 | 1015 | 0.19 | 1191
1187 | PENRYN 11051342 | 152561105 | PENRYN 1105 | 1342 | FALSE | 62297.5033 | 33351.1972 | 20.7279 | 440 | 0.00011151 | 1385 | 593.3765 | 1111 | 0.065366 | 28.7609 | 1016 | 1.74 | 645
8143 | CLAYTON 2215W531R | 12022215 | CLAYTON 2215 | W531R | FALSE | 17380.2917 | 10443.673 | 6.4908 | 100 | 6.9698e-05 | 2483 | 735.723 | 988 | 0.065356 | 6.5356 | 1017 | 0.07 | 1731
2291 | SHINGLE SPRINGS 210913322 | 153652109 | SHINGLE SPRINGS 2109 | 13322 | FALSE | 66617.6825 | 66617.6825 | 41.4032 | 490 | 6.243e-05 | 2708 | 1047.9717 | 798 | 0.065331 | 32.0124 | 1018 | 0.31 | 1005
2286 | BEAR VALLEY 210521160 | 252192105 | BEAR VALLEY 2105 | 21160 | FALSE | 38269.4773 | 38269.4773 | 23.7846 | 194 | 4.477e-05 | 3167 | 1259.0438 | 695 | 0.065187 | 12.6462 | 1019 | 0.07 | 1757
9841 | MESA 1103126697 | 182821103 | MESA 1103 | 126697 | FALSE | 1766.1223 | 1641.863 | 1.0204 | 10 | 6.1082e-05 | 2745 | 1011.3761 | 827 | 0.065062 | 0.65062 | 1020 |  | 3433
9670 | FRENCH GULCH 1102CB | 103381102 | FRENCH GULCH 1102 | CB | FALSE | 2729.0129 | 2729.0129 | 1.6961 | 12 | 0.00018833 | 451 | 298.7993 | 1449 | 0.06474 | 0.77689 | 1021 | 0.03 | 2234
2589 | FORT ROSS 1121124 | 42851121 | FORT ROSS 1121 | 124 | FALSE | 29762.4384 | 29762.4384 | 18.4975 | 99 | 0.00011564 | 1282 | 546.7406 | 1151 | 0.064597 | 6.3951 | 1022 | 4.64 | 511
2518 | OCEANO 1104Q08 | 182601104 | OCEANO 1104 | Q08 | FALSE | 19981.628 | 19981.628 | 12.4187 | 148 | 5.6432e-05 | 2876 | 1236.4827 | 708 | 0.064559 | 9.5547 | 1023 | 4.37 | 521
10030 | MC ARTHUR 1102542920 | 103491102 | MC ARTHUR 1102 | 542920 | FALSE | 2484.216 | 2034.8319 | 1.2647 | 10 | 2.943e-05 | 3433 | 2350.3357 | 372 | 0.064427 | 0.64427 | 1024 |  | 3478
4185 | PASO ROBLES 1104R12 | 182611104 | PASO ROBLES 1104 | R12 | FALSE | 64632.5351 | 52796.2686 | 32.8131 | 278 | 5.1483e-05 | 3005 | 1212.0624 | 725 | 0.064341 | 17.8868 | 1025 | 0.1 | 1470
7956 | JESSUP 11011993 | 103441101 | JESSUP 1101 | 1993 | FALSE | 4771.9686 | 4470.3512 | 2.7783 | 39 | 6.0989e-05 | 2747 | 818.0593 | 926 | 0.064212 | 2.5043 | 1026 | 3.17 | 558
10640 | CALISTOGA 110266730 | 42711102 | CALISTOGA 1102 | 66730 | FALSE | 1703.3079 | 1703.3079 | 1.0586 | 6 | 0.00011857 | 1215 | 919.8595 | 875 | 0.064035 | 0.38421 | 1027 | 0.49 | 897
9262 | LAKEVILLE 110287432 | 43371102 | LAKEVILLE 1102 | 87432 | FALSE | 21925.1583 | 15708.5355 | 9.7629 | 81 | 7.1409e-05 | 2436 | 994.1805 | 837 | 0.063901 | 5.176 | 1028 | 0.09 | 1521
6678 | MIDDLETOWN 11011325 | 43141101 | MIDDLETOWN 1101 | 1325 | FALSE | 13829.5499 | 13829.5499 | 8.5951 | 80 | 0.00012793 | 1047 | 449.2232 | 1249 | 0.063613 | 5.0891 | 1029 | 12.01 | 378
5737 | UKIAH 11151216 | 42771115 | UKIAH 1115 | 1216 | FALSE | 30877.2329 | 21628.5531 | 13.4422 | 182 | 0.00012873 | 1035 | 525.6183 | 1178 | 0.063522 | 11.561 | 1030 | 0.07 | 1733
1518 | DIAMOND SPRINGS 110518935 | 152261105 | DIAMOND SPRINGS 1105 | 18935 | FALSE | 10773.8274 | 10773.8274 | 6.696 | 76 | 0.00011327 | 1337 | 910.0927 | 882 | 0.063224 | 4.805 | 1031 | 8.29 | 432
8962 | TEMPLETON 2110N30 | 183052110 | TEMPLETON 2110 | N30 | FALSE | 32768.3238 | 32768.3238 | 20.3656 | 120 | 6.3151e-05 | 2674 | 927.1943 | 870 | 0.063152 | 7.5782 | 1032 | 0.09 | 1530
5800 | CLARK ROAD 11022070 | 103091102 | CLARK ROAD 1102 | 2070 | FALSE | 15059.4591 | 14786.6222 | 9.1899 | 72 | 0.00014395 | 814 | 498.0458 | 1203 | 0.063106 | 4.5436 | 1033 | 0.07 | 1760
1728 | TEMPLETON 2112116402 | 183052112 | TEMPLETON 2112 | 116402 | FALSE | 11255.0357 | 3810.8828 | 2.3685 | 64 | 5.7437e-05 | 2850 | 1320.2856 | 674 | 0.062979 | 4.0307 | 1034 |  | 2740
727 | APPLE HILL 2102186912 | 153662102 | APPLE HILL 2102 | 186912 | FALSE | 97116.525 | 94273.5723 | 58.5914 | 606 | 9.5424e-05 | 1747 | 711.7437 | 1013 | 0.06292 | 38.1293 | 1035 | 0.18 | 1223
7181 | BEAR VALLEY 21054170 | 252192105 | BEAR VALLEY 2105 | 4170 | FALSE | 15319.6405 | 15319.6405 | 9.5212 | 45 | 4.2938e-05 | 3210 | 1356.0496 | 661 | 0.062779 | 2.8251 | 1036 | 0.03 | 2358
8856 | GARBERVILLE 11028189 | 192221102 | GARBERVILLE 1102 | 8189 | FALSE | 1685.4401 | 1685.4401 | 1.0475 | 11 | 0.00035454 | 86 | 166.396 | 1732 | 0.062553 | 0.68809 | 1037 | 0.02 | 2537
1917 | PANORAMA 1101CB | 103461101 | PANORAMA 1101 | CB | FALSE | 27174.1674 | 1828.844 | 1.1366 | 175 | 0.0001054 | 1510 | 467.1503 | 1226 | 0.062374 | 10.9155 | 1038 | 0.02 | 2425
9789 | TASSAJARA 2106203380 | 14662106 | TASSAJARA 2106 | 203380 | TRUE | 3178.2991 | 809.5956 | 0.50317 | 26 | 0.00010239 | 1592 | 687.7534 | 1032 | 0.062335 | 1.6207 | 1039 |  | 3423
8449 | VACAVILLE 111112342 | 63601111 | VACAVILLE 1111 | 12342 | TRUE | 1750.136 | 352.0949 | 0.21883 | 16 | 0.00013409 | 942 | 663.7688 | 1049 | 0.062293 | 0.99668 | 1040 | 0.32 | 996
3572 | OLETA 110113478 | 163541101 | OLETA 1101 | 13478 | FALSE | 24836.1056 | 19846.6513 | 12.3348 | 169 | 0.0001203 | 1180 | 594.448 | 1107 | 0.062159 | 10.5049 | 1041 | 0.09 | 1570
1028 | LOW GAP 11012094 | 192411101 | LOW GAP 1101 | 2094 | FALSE | 27452.3558 | 25248.6295 | 15.6921 | 139 | 0.00021404 | 343 | 379.7853 | 1321 | 0.062103 | 8.6323 | 1042 | 3.85 | 533
3105 | NOTRE DAME 11042028 | 102041104 | NOTRE DAME 1104 | 2028 | FALSE | 17437.7183 | 17437.7183 | 10.8376 | 86 | 0.00015423 | 702 | 243.285 | 1559 | 0.062015 | 5.3333 | 1043 | 0.41 | 939
2667 | FROGTOWN 170212282 | 163451702 | FROGTOWN 1702 | 12282 | FALSE | 58482.1143 | 58482.1143 | 36.3469 | 261 | 0.00011986 | 1190 | 718.4403 | 1004 | 0.061928 | 16.1631 | 1044 | 0.18 | 1206
7606 | NOTRE DAME 11042537 | 102041104 | NOTRE DAME 1104 | 2537 | FALSE | 8030.1143 | 8030.1143 | 4.9907 | 37 | 9.2031e-05 | 1844 | 618.6971 | 1083 | 0.061762 | 2.2852 | 1045 | 0.2 | 1156
2093 | ATASCADERO 1103A46 | 182541103 | ATASCADERO 1103 | A46 | TRUE | 13904.7944 | 633.1098 | 0.39348 | 94 | 8.1941e-05 | 2157 | 550.2411 | 1144 | 0.06175 | 5.8045 | 1046 | 0.02 | 2447
7485 | SHINGLE SPRINGS 210551738 | 153652105 | SHINGLE SPRINGS 2105 | 51738 | TRUE | 1844.3225 | 26.6806 | 0.016582 | 19 | 0.00013923 | 882 | 441.8941 | 1255 | 0.061564 | 1.1697 | 1047 | 17.24 | 335
284 | PERRY 1101V78 | 183071101 | PERRY 1101 | V78 | FALSE | 47471.3302 | 47471.3302 | 29.5036 | 164 | 6.8753e-05 | 2516 | 918.2768 | 876 | 0.061453 | 10.0783 | 1048 | 0.19 | 1179
10468 | CALPINE 1144962 | 48011144 | CALPINE 1144 | 962 | TRUE | 63.3636 | 63.3636 | 0.039381 | 1 | 0.00010321 | 1565 | 595.1616 | 1105 | 0.061428 | 0.061428 | 1049 | 8.51 | 425
8597 | ORO FINO 1102127563 | 103031102 | ORO FINO 1102 | 127563 | FALSE | 11105.9314 | 11105.9314 | 6.9024 | 63 | 7.2173e-05 | 2413 | 803.5682 | 938 | 0.061336 | 3.8642 | 1050 | 23.56 | 283
6425 | MADISON 2101351038 | 63172101 | MADISON 2101 | 351038 | FALSE | 22506.9662 | 2661.6552 | 1.6542 | 130 | 7.0209e-05 | 2462 | 1068.3127 | 787 | 0.061316 | 7.971 | 1051 |  | 3029
5524 | JESSUP 11011496 | 103441101 | JESSUP 1101 | 1496 | FALSE | 26084.969 | 23526.9728 | 14.6221 | 201 | 7.6403e-05 | 2297 | 864.7228 | 905 | 0.06121 | 12.3032 | 1052 | 0.06 | 1790
10127 | SPAULDING 1101CB | 152251101 | SPAULDING 1101 | CB | TRUE | 56.7484 | 56.7484 | 0.035269 | 1 | 0.0001609 | 632 | 380.3958 | 1320 | 0.061207 | 0.061207 | 1053 |  | 3497
4318 | HIGGINS 11102408 | 152691110 | HIGGINS 1110 | 2408 | FALSE | 18614.5661 | 18614.5661 | 11.569 | 124 | 0.000106 | 1493 | 623.6203 | 1079 | 0.060864 | 7.5471 | 1054 | 0.34 | 981
7906 | PIT NO 7 1101CB | 103501101 | PIT NO 7 1101 | CB | FALSE | 4357.8457 | 4357.8457 | 2.7084 | 3 | 0.00010885 | 1430 | 808.7175 | 931 | 0.060819 | 0.18246 | 1055 | 0.02 | 2472
7035 | SYCAMORE CREEK 1111CB | 102971111 | SYCAMORE CREEK 1111 | CB | TRUE | 11952.1608 | 777.7423 | 0.48337 | 85 | 0.00011707 | 1245 | 452.6669 | 1244 | 0.060715 | 5.1608 | 1056 | 0.06 | 1775
4688 | UPPER LAKE 1101452 | 42871101 | UPPER LAKE 1101 | 452 | FALSE | 31530.7427 | 8129.076 | 5.0523 | 207 | 0.00010226 | 1598 | 743.369 | 981 | 0.060708 | 12.5666 | 1057 | 0.67 | 816
7853 | CLOVERDALE 1102670 | 42821102 | CLOVERDALE 1102 | 670 | TRUE | 4937.5444 | 587.1475 | 0.36491 | 43 | 0.00012733 | 1058 | 393.8186 | 1302 | 0.06056 | 2.6041 | 1058 | 0.03 | 2292
9980 | BRIDGEVILLE 1101CB | 192461101 | BRIDGEVILLE 1101 | CB | FALSE | 13703.2012 | 13703.2012 | 8.5166 | 51 | 0.00018978 | 443 | 315.2875 | 1424 | 0.060495 | 3.0852 | 1059 | 2.08 | 624
3075 | REDBUD 11022013 | 43191102 | REDBUD 1102 | 2013 | TRUE | 7412.4545 | 238.9679 | 0.14852 | 51 | 5.2169e-05 | 2988 | 888.4761 | 888 | 0.06048 | 3.0845 | 1060 | 0.44 | 923
377 | FROGTOWN 1702L5407 | 163451702 | FROGTOWN 1702 | L5407 | FALSE | 29410.8857 | 29410.8857 | 18.279 | 153 | 4.5895e-05 | 3142 | 1349.9596 | 663 | 0.060463 | 9.2508 | 1061 | 0.09 | 1522
599 | CURTIS 170356972 | 163351703 | CURTIS 1703 | 56972 | FALSE | 13791.0471 | 13791.0471 | 8.5712 | 57 | 0.00011753 | 1234 | 612.4545 | 1090 | 0.060186 | 3.4306 | 1062 | 0.04 | 2114
9546 | COTATI 1102CB | 42271102 | COTATI 1102 | CB | FALSE | 3229.2079 | 2904.3184 | 1.805 | 19 | 0.00016629 | 580 | 366.1668 | 1344 | 0.05984 | 1.137 | 1063 | 0.04 | 2199
9754 | CALPELLA 1102708161 | 43411102 | CALPELLA 1102 | 708161 | FALSE | 1824.6356 | 1615.0007 | 1.0037 | 12 | 0.00012306 | 1133 | 461.5277 | 1234 | 0.059606 | 0.71527 | 1064 |  | 3411
7941 | FRUITLAND 11426064 | 192311142 | FRUITLAND 1142 | 6064 | FALSE | 13322.7276 | 10776.9352 | 6.6979 | 66 | 0.00027944 | 157 | 244.0042 | 1557 | 0.059515 | 3.928 | 1065 | 1.74 | 646
1172 | CORRAL 110336680 | 162991103 | CORRAL 1103 | 36680 | FALSE | 32219.8242 | 15055.3944 | 9.357 | 265 | 8.2363e-05 | 2143 | 715.9031 | 1008 | 0.059472 | 15.7601 | 1066 | 2.94 | 572
7127 | SONOMA 1107844168 | 42721107 | SONOMA 1107 | 844168 | FALSE | 18710.7045 | 7309.0201 | 4.5426 | 100 | 5.7956e-05 | 2836 | 877.0353 | 894 | 0.059437 | 5.9437 | 1067 |  | 3097
2372 | GRASS VALLEY 11032110 | 152031103 | GRASS VALLEY 1103 | 2110 | FALSE | 32283.1191 | 31798.2221 | 19.7627 | 224 | 0.00013772 | 899 | 464.9832 | 1230 | 0.059423 | 13.3106 | 1068 | 0.21 | 1147
2173 | PUEBLO 1105696 | 43291105 | PUEBLO 1105 | 696 | FALSE | 11659.1184 | 6037.9333 | 3.7526 | 79 | 7.4535e-05 | 2343 | 617.4166 | 1085 | 0.059025 | 4.663 | 1069 | 0.32 | 991
2604 | JESSUP 11031540 | 103441103 | JESSUP 1103 | 1540 | TRUE | 20738.5879 | 256.3874 | 0.15935 | 157 | 0.00010932 | 1426 | 527.982 | 1175 | 0.058865 | 9.2418 | 1070 | 0.04 | 2210
8024 | PENRYN 11072708 | 152561107 | PENRYN 1107 | 2708 | FALSE | 17128.5396 | 15094.9992 | 9.3816 | 124 | 0.00011703 | 1249 | 634.212 | 1074 | 0.058775 | 7.2881 | 1071 | 0.09 | 1533
660 | GABILAN 1101460414 | 182331101 | GABILAN 1101 | 460414 | FALSE | 10774.9077 | 8655.1604 | 5.3792 | 38 | 8.546e-05 | 2043 | 785.6181 | 953 | 0.058719 | 2.2313 | 1072 |  | 2688
2838 | MENDOCINO 110148750 | 42951101 | MENDOCINO 1101 | 48750 | FALSE | 28839.2375 | 28839.2375 | 17.9237 | 165 | 9.931e-05 | 1660 | 705.0697 | 1020 | 0.058621 | 9.6724 | 1073 | 19.06 | 315
5642 | ALHAMBRA 110582622 | 14101105 | ALHAMBRA 1105 | 82622 | FALSE | 41703.3816 | 41703.3816 | 25.9188 | 254 | 8.8106e-05 | 1980 | 753.4327 | 972 | 0.058508 | 14.8609 | 1074 | 0.2 | 1166
5965 | JOLON 1102CB | 182981102 | JOLON 1102 | CB | FALSE | 38608.5003 | 37939.8486 | 23.5798 | 181 | 6.1591e-05 | 2729 | 1004.6328 | 832 | 0.058399 | 10.5701 | 1075 | 0.03 | 2280
5646 | SANTA YNEZ 1104512912 | 182721104 | SANTA YNEZ 1104 | 512912 | FALSE | 3140.8885 | 1435.1217 | 0.89193 | 23 | 6.2939e-05 | 2682 | 742.0792 | 982 | 0.058383 | 1.3428 | 1076 |  | 2970
1584 | COLUMBIA HILL 1101CB | 152471101 | COLUMBIA HILL 1101 | CB | FALSE | 63324.3345 | 63324.3345 | 39.3563 | 375 | 0.00014192 | 841 | 477.8627 | 1217 | 0.058367 | 21.8875 | 1077 | 0.76 | 785
8255 | CRESCENT MILLS 21012562 | 103132101 | CRESCENT MILLS 2101 | 2562 | FALSE | 55111.7044 | 31122.7322 | 19.3429 | 222 | 5.835e-05 | 2824 | 1193.0263 | 734 | 0.057915 | 12.8572 | 1078 | 0.05 | 1950
2533 | MOLINO 1101338 | 42571101 | MOLINO 1101 | 338 | FALSE | 23338.4107 | 12496.8829 | 7.7669 | 176 | 0.00010195 | 1604 | 593.3845 | 1110 | 0.05791 | 10.1921 | 1079 | 7.05 | 454
9899 | LLAGAS 21014523 | 83182101 | LLAGAS 2101 | 4523 | FALSE | 4420.7892 | 1471.0588 | 0.91427 | 28 | 9.5345e-05 | 1750 | 593.4447 | 1109 | 0.057806 | 1.6186 | 1080 |  | 3449
10017 | PASO ROBLES 1107289947 | 182611107 | PASO ROBLES 1107 | 289947 | TRUE | 3212.1673 | 447.6357 | 0.27821 | 21 | 8.5184e-05 | 2054 | 855.7073 | 911 | 0.057658 | 1.2108 | 1081 |  | 3472
451 | CALISTOGA 11011087 | 42711101 | CALISTOGA 1101 | 1087 | FALSE | 3157.1282 | 3157.1282 | 1.9622 | 22 | 0.00010484 | 1532 | 532.5062 | 1170 | 0.05764 | 1.2681 | 1082 | 7.64 | 443
90 | TYLER 1105816852 | 103571105 | TYLER 1105 | 816852 | FALSE | 70141.7466 | 20545.6876 | 12.7692 | 423 | 4.2631e-05 | 3214 | 1516.9463 | 587 | 0.057549 | 24.3431 | 1083 |  | 2655
67 | WOODACRE 1102CB | 43021102 | WOODACRE 1102 | CB | FALSE | 20142.5456 | 20085.8093 | 12.4834 | 141 | 0.00015851 | 658 | 382.2019 | 1316 | 0.057543 | 8.1136 | 1084 | 0.64 | 827
3103 | JOLON 11027070 | 182981102 | JOLON 1102 | 7070 | FALSE | 26486.1632 | 10307.0829 | 6.4059 | 132 | 5.0065e-05 | 3036 | 1217.7073 | 718 | 0.057494 | 7.5892 | 1085 | 0.03 | 2323
6894 | DESCHUTES 11011654 | 103351101 | DESCHUTES 1101 | 1654 | FALSE | 28221.2564 | 28221.2564 | 17.5396 | 168 | 8.908e-05 | 1943 | 662.2613 | 1051 | 0.057486 | 9.6576 | 1086 | 0.1 | 1492
1819 | ALTO 11243745 | 42031124 | ALTO 1124 | 3745 | FALSE | 7247.2343 | 7247.2343 | 4.5042 | 52 | 0.00018327 | 486 | 535.7815 | 1164 | 0.057415 | 2.9856 | 1087 | 1.01 | 730
1989 | ELECTRA 1101CB | 162161101 | ELECTRA 1101 | CB | FALSE | 50985.8349 | 50985.8349 | 31.6879 | 293 | 8.4764e-05 | 2072 | 750.5824 | 974 | 0.05741 | 16.8213 | 1088 | 0.1 | 1456
994 | BUTTE 1105751990 | 103081105 | BUTTE 1105 | 751990 | FALSE | 39452.6049 | 39436.6029 | 24.51 | 243 | 0.00013521 | 926 | 355.8632 | 1363 | 0.057382 | 13.9439 | 1089 |  | 2702
7429 | MOUNTAIN QUARRIES 210151584 | 152282101 | MOUNTAIN QUARRIES 2101 | 51584 | FALSE | 35041.5534 | 35041.5534 | 21.7785 | 224 | 7.7619e-05 | 2272 | 869.1368 | 901 | 0.057318 | 12.8393 | 1090 | 0.08 | 1655
7628 | WISE 11011404 | 152271101 | WISE 1101 | 1404 | FALSE | 5740.3584 | 2402.8891 | 1.4934 | 47 | 0.0001882 | 452 | 397.9556 | 1298 | 0.057199 | 2.6884 | 1091 | 0.03 | 2347
7386 | SAN RAMON 2108CB | 14232108 | SAN RAMON 2108 | CB | FALSE | 15329.2524 | 14012.7161 | 8.709 | 102 | 8.2611e-05 | 2139 | 748.7975 | 976 | 0.057183 | 5.8326 | 1092 | 18.75 | 318
9327 | CALISTOGA 110189150 | 42711101 | CALISTOGA 1101 | 89150 | FALSE | 15332.2939 | 15332.2939 | 9.5291 | 88 | 0.00012195 | 1149 | 582.7266 | 1121 | 0.057148 | 5.029 | 1093 | 0.48 | 905
4436 | SAN RAMON 2119CB | 14232119 | SAN RAMON 2119 | CB | FALSE | 2345.4974 | 1187.935 | 0.73831 | 21 | 7.6681e-05 | 2290 | 471.5803 | 1223 | 0.057097 | 1.199 | 1094 | 0.67 | 818
4471 | ELECTRA 11024756 | 162161102 | ELECTRA 1102 | 4756 | FALSE | 18962.2338 | 15139.4165 | 9.4092 | 95 | 0.000145 | 802 | 459.0245 | 1236 | 0.057032 | 5.4181 | 1095 | 0.05 | 1943
10516 | GARBERVILLE 11022124 | 192221102 | GARBERVILLE 1102 | 2124 | FALSE | 5026.2322 | 5026.2322 | 3.1238 | 6 | 0.00058653 | 20 | 170.3508 | 1714 | 0.057006 | 0.34203 | 1096 | 1.87 | 636
10428 | ANNAPOLIS 1101CB | 42861101 | ANNAPOLIS 1101 | CB | FALSE | 1058.7166 | 1058.7166 | 0.658 | 7 | 0.00022337 | 306 | 221.0499 | 1604 | 0.057005 | 0.39904 | 1097 | 0.06 | 1873
5436 | TEMPLETON 2110901690 | 183052110 | TEMPLETON 2110 | 901690 | FALSE | 63574.4496 | 60028.2631 | 37.3078 | 306 | 5.6692e-05 | 2868 | 1011.6278 | 825 | 0.056927 | 17.4196 | 1098 | 0.62 | 841
1208 | HOPLAND 1101CB | 42251101 | HOPLAND 1101 | CB | FALSE | 36057.8693 | 23579.7024 | 14.6549 | 190 | 0.00011058 | 1399 | 511.8263 | 1189 | 0.056867 | 10.8047 | 1099 | 0.02 | 2512
582 | SWIFT 2110853720 | 83392110 | SWIFT 2110 | 853720 | FALSE | 50276.8108 | 50276.8108 | 31.2472 | 140 | 6.2471e-05 | 2705 | 1012.617 | 823 | 0.056625 | 7.9275 | 1100 |  | 2684
6471 | SALMON CREEK 110137368 | 43161101 | SALMON CREEK 1101 | 37368 | FALSE | 9786.5772 | 9786.5772 | 6.0824 | 48 | 7.032e-05 | 2459 | 880.1307 | 892 | 0.056596 | 2.7166 | 1101 | 0.06 | 1898
7036 | WOODACRE 1101CB | 43021101 | WOODACRE 1101 | CB | FALSE | 4540.438 | 4454.6417 | 2.7686 | 35 | 0.00019479 | 417 | 248.765 | 1543 | 0.056508 | 1.9778 | 1102 | 0.3 | 1017
9354 | FRUITLAND 114137410 | 192311141 | FRUITLAND 1141 | 37410 | FALSE | 8875.6069 | 8413.1179 | 5.2288 | 42 | 0.00021128 | 354 | 348.1422 | 1375 | 0.056472 | 2.3718 | 1103 | 0.04 | 2173
8408 | GOLDTREE 1105CB | 182581105 | GOLDTREE 1105 | CB | FALSE | 15108.5071 | 11908.479 | 7.4012 | 76 | 7.9073e-05 | 2231 | 565.89 | 1132 | 0.056447 | 4.29 | 1104 | 0.45 | 919
1036 | FRUITLAND 1142CB | 192311142 | FRUITLAND 1142 | CB | FALSE | 24719.9919 | 16900.9683 | 10.504 | 116 | 0.0002473 | 224 | 245.6875 | 1552 | 0.056321 | 6.5332 | 1105 | 3.13 | 561
5437 | FITCH MOUNTAIN 1113775992 | 42751113 | FITCH MOUNTAIN 1113 | 775992 | FALSE | 5059.1291 | 3381.5311 | 2.1016 | 34 | 0.00012419 | 1115 | 374.1489 | 1330 | 0.056251 | 1.9125 | 1106 |  | 2954
8868 | SALMON CREEK 1101461703 | 43161101 | SALMON CREEK 1101 | 461703 | FALSE | 1414.65 | 1414.65 | 0.87921 | 8 | 7.7835e-05 | 2265 | 327.199 | 1402 | 0.05614 | 0.44912 | 1107 |  | 3274
1882 | SHINGLE SPRINGS 211051800 | 153652110 | SHINGLE SPRINGS 2110 | 51800 | FALSE | 15718.5986 | 14796.5287 | 9.1961 | 128 | 0.00016264 | 616 | 342.7814 | 1383 | 0.05603 | 7.1719 | 1108 | 3.81 | 534
3611 | SANTA MARIA 1108M80 | 182671108 | SANTA MARIA 1108 | M80 | FALSE | 93735.5013 | 93735.5013 | 58.257 | 397 | 4.5707e-05 | 3147 | 1161.6823 | 749 | 0.055911 | 22.1966 | 1109 | 0.42 | 930
6376 | MONTE RIO 11131991 | 42811113 | MONTE RIO 1113 | 1991 | FALSE | 11465.3295 | 11465.3295 | 7.1257 | 51 | 0.00016331 | 608 | 395.6046 | 1299 | 0.055786 | 2.8451 | 1110 | 56.35 | 99
1111 | PEORIA 17056697 | 163781705 | PEORIA 1705 | 6697 | FALSE | 6657.3541 | 6657.3541 | 4.1376 | 46 | 0.00010476 | 1534 | 551.7785 | 1143 | 0.055767 | 2.5653 | 1111 | 0.1 | 1462
3012 | RACETRACK 170311270 | 163761703 | RACETRACK 1703 | 11270 | FALSE | 20312.1456 | 20312.1456 | 12.6241 | 123 | 0.00012756 | 1056 | 499.3074 | 1201 | 0.055685 | 6.8493 | 1112 | 0.11 | 1443
722 | MONTE RIO 11125040 | 42811112 | MONTE RIO 1112 | 5040 | FALSE | 6507.5662 | 6507.5662 | 4.0445 | 46 | 0.0002406 | 244 | 218.6982 | 1609 | 0.055628 | 2.5589 | 1113 | 20.75 | 304
9716 | WINDSOR 1103171410 | 43501103 | WINDSOR 1103 | 171410 | FALSE | 7035.3214 | 2217.9639 | 1.3785 | 40 | 0.00011961 | 1192 | 536.0514 | 1163 | 0.055603 | 2.2241 | 1114 |  | 3405
15 | MENDOCINO 1101450 | 42951101 | MENDOCINO 1101 | 450 | FALSE | 30451.6805 | 9311.1997 | 5.7869 | 208 | 0.00012825 | 1043 | 484.352 | 1210 | 0.055438 | 11.531 | 1115 | 0.04 | 2211
6036 | PLACER 1103CB | 152461103 | PLACER 1103 | CB | FALSE | 14529.9116 | 11213.2305 | 6.9691 | 99 | 0.00015794 | 663 | 471.1517 | 1224 | 0.05535 | 5.4797 | 1116 | 0.06 | 1842
6178 | GEYSERVILLE 110135492 | 42891101 | GEYSERVILLE 1101 | 35492 | FALSE | 34847.1678 | 16074.976 | 9.9907 | 219 | 9.7259e-05 | 1708 | 426.1888 | 1265 | 0.055239 | 12.0973 | 1117 | 0.03 | 2257
6625 | WYANDOTTE 1107829470 | 102911107 | WYANDOTTE 1107 | 829470 | FALSE | 16595.0205 | 16595.0205 | 10.3139 | 93 | 0.00011788 | 1231 | 515.0682 | 1185 | 0.055226 | 5.136 | 1118 |  | 3047
7721 | CURTIS 17058110 | 163351705 | CURTIS 1705 | 8110 | FALSE | 13110.3306 | 13110.3306 | 8.1481 | 99 | 0.0001169 | 1252 | 657.3966 | 1057 | 0.055185 | 5.4634 | 1119 | 0.15 | 1283
8806 | CLAYTON 2212859443 | 12022212 | CLAYTON 2212 | 859443 | TRUE | 777.6394 | 475.2837 | 0.29539 | 5 | 4.9574e-05 | 3047 | 1445.6352 | 616 | 0.055167 | 0.27584 | 1120 |  | 3268
8792 | DUNLAP 1103CB | 254061103 | DUNLAP 1103 | CB | FALSE | 9029.352 | 9029.352 | 5.6118 | 38 | 3.4574e-05 | 3359 | 1447.0842 | 615 | 0.055113 | 2.0943 | 1121 | 0 | 2649
4534 | MERCED FALLS 110285002 | 252811102 | MERCED FALLS 1102 | 85002 | FALSE | 57093.5104 | 57093.5104 | 35.4838 | 394 | 7.6265e-05 | 2302 | 729.1639 | 992 | 0.055026 | 21.6802 | 1122 | 0.87 | 759
2247 | FROGTOWN 170113412 | 163451701 | FROGTOWN 1701 | 13412 | FALSE | 62439.7255 | 62439.7255 | 38.8065 | 333 | 0.00011911 | 1202 | 811.1905 | 930 | 0.055018 | 18.321 | 1123 | 0.87 | 756
3205 | COTATI 110361736 | 42271103 | COTATI 1103 | 61736 | FALSE | 26875.6469 | 19558.6498 | 12.1558 | 129 | 6.0018e-05 | 2773 | 726.4231 | 994 | 0.054986 | 7.0932 | 1124 | 0.05 | 1936
9516 | WILDWOOD 11011576 | 103611101 | WILDWOOD 1101 | 1576 | FALSE | 12974.577 | 12974.577 | 8.0638 | 51 | 7.9987e-05 | 2206 | 832.2405 | 921 | 0.054922 | 2.801 | 1125 | 0.07 | 1744
4729 | FITCH MOUNTAIN 1113352 | 42751113 | FITCH MOUNTAIN 1113 | 352 | FALSE | 19238.6019 | 9086.2434 | 5.6471 | 123 | 0.00014867 | 757 | 547.944 | 1149 | 0.054876 | 6.7498 | 1126 | 0.04 | 2196
6906 | IONE 1101CB | 163881101 | IONE 1101 | CB | FALSE | 22613.9915 | 2970.8687 | 1.8464 | 85 | 0.00012529 | 1093 | 646.6464 | 1068 | 0.054859 | 4.663 | 1127 | 0.02 | 2492
1910 | FROGTOWN 17016807 | 163451701 | FROGTOWN 1701 | 6807 | FALSE | 7894.5527 | 7894.5527 | 4.9065 | 49 | 0.00014837 | 759 | 586.6523 | 1116 | 0.054517 | 2.6713 | 1128 | 0.08 | 1650
1099 | HIGHLANDS 110275140 | 43361102 | HIGHLANDS 1102 | 75140 | FALSE | 32224.0105 | 13968.9875 | 8.6818 | 238 | 4.9487e-05 | 3050 | 824.0667 | 924 | 0.054483 | 12.967 | 1129 | 0.07 | 1713
9073 | CORRAL 1103831781 | 162991103 | CORRAL 1103 | 831781 | FALSE | 2564.8738 | 1186.1396 | 0.73719 | 19 | 7.3782e-05 | 2367 | 806.9369 | 932 | 0.054336 | 1.0324 | 1130 |  | 3304
1018 | APPLE HILL 21029722 | 153662102 | APPLE HILL 2102 | 9722 | FALSE | 62437.5165 | 62437.5165 | 38.8052 | 359 | 0.00010174 | 1610 | 529.226 | 1174 | 0.054308 | 19.4965 | 1131 | 0.52 | 890
882 | MORGAN HILL 2105XR152 | 83242105 | MORGAN HILL 2105 | XR152 | FALSE | 20635.5048 | 14045.9028 | 8.7296 | 156 | 8.0844e-05 | 2185 | 646.2065 | 1069 | 0.054285 | 8.4685 | 1132 | 0.08 | 1583
7464 | CLARKSVILLE 2106CB | 153612106 | CLARKSVILLE 2106 | CB | TRUE | 830.42 | 224.6189 | 0.1396 | 9 | 0.00020912 | 364 | 241.4035 | 1563 | 0.054215 | 0.48794 | 1133 | 0.02 | 2507
8313 | RED BLUFF 1104135854 | 103541104 | RED BLUFF 1104 | 135854 | FALSE | 4250.0634 | 2325.1244 | 1.4451 | 34 | 6.0566e-05 | 2759 | 1134.6908 | 761 | 0.053974 | 1.8351 | 1134 |  | 3213
8191 | KESWICK 11011588 | 103451101 | KESWICK 1101 | 1588 | FALSE | 13991.4401 | 13991.4401 | 8.6957 | 33 | 0.00018106 | 503 | 584.74 | 1118 | 0.053968 | 1.7809 | 1135 | 0.19 | 1195
5209 | OLETA 11022642 | 163541102 | OLETA 1102 | 2642 | FALSE | 7497.8568 | 7497.8568 | 4.6599 | 27 | 9.0401e-05 | 1902 | 716.2407 | 1006 | 0.053841 | 1.4537 | 1136 | 0.03 | 2270
2961 | SYCAMORE CREEK 11112014 | 102971111 | SYCAMORE CREEK 1111 | 2014 | FALSE | 35984.1335 | 35984.1335 | 22.3643 | 181 | 0.00010418 | 1548 | 602.3767 | 1097 | 0.053762 | 9.731 | 1137 | 0.2 | 1157
5221 | EL DORADO PH 210163464 | 152762101 | EL DORADO PH 2101 | 63464 | FALSE | 21920.8692 | 21920.8692 | 13.6239 | 70 | 0.00012137 | 1160 | 659.6276 | 1053 | 0.05356 | 3.7492 | 1138 | 0.13 | 1359
1685 | WILLOW CREEK 110347966 | 192171103 | WILLOW CREEK 1103 | 47966 | FALSE | 27271.3222 | 27271.3222 | 16.9492 | 167 | 0.00020988 | 360 | 215.8045 | 1610 | 0.053445 | 8.9254 | 1139 | 0.13 | 1355
1361 | RED BLUFF 11051564 | 103541105 | RED BLUFF 1105 | 1564 | FALSE | 17092.5832 | 1891.6003 | 1.1756 | 133 | 7.329e-05 | 2387 | 869.3002 | 900 | 0.053412 | 7.1038 | 1140 | 0.62 | 839
566 | MORGAN HILL 2110814616 | 83242110 | MORGAN HILL 2110 | 814616 | TRUE | 3902.6921 | 157.4015 | 0.097826 | 28 | 8.7257e-05 | 2006 | 602.3323 | 1098 | 0.053409 | 1.4955 | 1141 |  | 2683
9804 | FROGTOWN 1702694042 | 163451702 | FROGTOWN 1702 | 694042 | TRUE | 972.0471 | 972.0471 | 0.60413 | 8 | 0.00011883 | 1210 | 338.8363 | 1389 | 0.053395 | 0.42716 | 1142 |  | 3427
548 | SHINGLE SPRINGS 21107742 | 153652110 | SHINGLE SPRINGS 2110 | 7742 | FALSE | 73623.591 | 73535.6671 | 45.7027 | 475 | 9.9171e-05 | 1663 | 595.5649 | 1104 | 0.053392 | 25.3612 | 1143 | 1.43 | 675
4014 | CURTIS 1704CB | 163351704 | CURTIS 1704 | CB | FALSE | 22863.3142 | 22355.1304 | 13.8938 | 170 | 0.0001075 | 1464 | 527.7867 | 1176 | 0.053282 | 9.058 | 1144 | 0.12 | 1366
5744 | WOODSIDE 11018974 | 24251101 | WOODSIDE 1101 | 8974 | FALSE | 21278.6691 | 21278.6691 | 13.2248 | 149 | 0.00020534 | 378 | 324.7416 | 1406 | 0.05299 | 7.8956 | 1145 | 76.03 | 55
4200 | MOLINO 1101322 | 42571101 | MOLINO 1101 | 322 | FALSE | 23201.9813 | 22860.7646 | 14.2081 | 167 | 0.00013802 | 893 | 458.1425 | 1238 | 0.052976 | 8.847 | 1146 | 35.69 | 212
7680 | PALMER 1101M88 | 183031101 | PALMER 1101 | M88 | FALSE | 24723.9577 | 4969.351 | 3.0885 | 85 | 4.85e-05 | 3076 | 599.8118 | 1100 | 0.052933 | 4.4993 | 1147 | 0.01 | 2589
2401 | WOODSIDE 11018884 | 24251101 | WOODSIDE 1101 | 8884 | FALSE | 12033.5669 | 12033.5669 | 7.4789 | 74 | 0.00017464 | 530 | 305.5705 | 1438 | 0.052785 | 3.9061 | 1148 | 48.31 | 129
5333 | GARBERVILLE 11022500 | 192221102 | GARBERVILLE 1102 | 2500 | FALSE | 25777.1884 | 25777.1884 | 16.0206 | 106 | 0.00032433 | 107 | 205.0308 | 1627 | 0.052654 | 5.5813 | 1149 | 11.96 | 380
3787 | BEAR VALLEY 21014500 | 252192101 | BEAR VALLEY 2101 | 4500 | FALSE | 132540.1743 | 38902.9544 | 24.1783 | 516 | 4.6379e-05 | 3128 | 1229.9776 | 714 | 0.052537 | 27.1089 | 1150 | 0.03 | 2255
8553 | RED BLUFF 11041302 | 103541104 | RED BLUFF 1104 | 1302 | FALSE | 23388.5169 | 22389.9711 | 13.9155 | 113 | 5.0169e-05 | 3034 | 1215.8532 | 721 | 0.052453 | 5.9272 | 1151 | 0.06 | 1889
10783 | BEAR VALLEY 2105CB | 252192105 | BEAR VALLEY 2105 | CB | FALSE | 6175.4075 | 6175.4075 | 3.838 | 9 | 9.2622e-05 | 1830 | 515.1474 | 1184 | 0.052345 | 0.4711 | 1152 | 0.01 | 2588
10429 | BUTTE 1105244246 | 103081105 | BUTTE 1105 | 244246 | FALSE | 1936.2709 | 1936.2709 | 1.2034 | 11 | 0.00016313 | 610 | 330.8536 | 1396 | 0.052269 | 0.57496 | 1153 |  | 3548
1753 | BRUNSWICK 110651484 | 152481106 | BRUNSWICK 1106 | 51484 | FALSE | 26385.5393 | 24741.7275 | 15.3771 | 195 | 0.0001406 | 862 | 372.49 | 1333 | 0.052211 | 10.1812 | 1154 | 0.17 | 1239
7841 | STONE CORRAL 1110975698 | 252921110 | STONE CORRAL 1110 | 975698 | FALSE | 7671.0517 | 1441.7984 | 0.89608 | 44 | 4.3563e-05 | 3200 | 962.1828 | 852 | 0.052194 | 2.2966 | 1155 |  | 3170
10305 | MIDDLETOWN 1101612 | 43141101 | MIDDLETOWN 1101 | 612 | FALSE | 6362.7002 | 6362.7002 | 3.9544 | 25 | 8.4863e-05 | 2067 | 719.6048 | 1000 | 0.05213 | 1.3033 | 1156 | 0.42 | 931
9510 | PUEBLO 2103776244 | 43292103 | PUEBLO 2103 | 776244 | TRUE | 783.9385 | 274.5802 | 0.17065 | 5 | 5.5048e-05 | 2909 | 540.4117 | 1158 | 0.052117 | 0.26059 | 1157 |  | 3366
2874 | FORT ROSS 11214947 | 42851121 | FORT ROSS 1121 | 4947 | FALSE | 16652.8009 | 16652.8009 | 10.3498 | 56 | 0.00016312 | 611 | 298.2938 | 1450 | 0.052018 | 2.913 | 1158 | 9.04 | 414
5370 | FROGTOWN 17027108 | 163451702 | FROGTOWN 1702 | 7108 | FALSE | 20715.9427 | 15478.9307 | 9.6202 | 99 | 5.144e-05 | 3007 | 993.4887 | 838 | 0.05186 | 5.1341 | 1159 | 0.06 | 1876
7742 | WEST POINT 110272036 | 163201102 | WEST POINT 1102 | 72036 | FALSE | 21135.8241 | 20864.4611 | 12.9673 | 105 | 8.1485e-05 | 2168 | 844.1543 | 916 | 0.051819 | 5.441 | 1160 | 14.82 | 354
8013 | WILLITS 110337506 | 42661103 | WILLITS 1103 | 37506 | FALSE | 18602.139 | 18602.139 | 11.5613 | 77 | 0.00015655 | 678 | 345.7654 | 1377 | 0.051705 | 3.9812 | 1161 | 4.56 | 516
8123 | OTTER 1102CB | 182941102 | OTTER 1102 | CB | FALSE | 10891.762 | 10891.762 | 6.7693 | 40 | 7.3648e-05 | 2374 | 760.2437 | 965 | 0.051564 | 2.0626 | 1162 | 0.19 | 1197
7649 | HARTLEY 1101CB | 43211101 | HARTLEY 1101 | CB | FALSE | 4864.6418 | 2361.7078 | 1.4678 | 33 | 0.00010062 | 1634 | 651.0467 | 1063 | 0.051416 | 1.6967 | 1163 | 0.02 | 2516
4094 | HOPLAND 1101960 | 42251101 | HOPLAND 1101 | 960 | FALSE | 8826.9021 | 6237.2835 | 3.8765 | 33 | 0.00010013 | 1642 | 470.8479 | 1225 | 0.051413 | 1.6966 | 1164 | 0.04 | 2083
7517 | PENRYN 110790970 | 152561107 | PENRYN 1107 | 90970 | FALSE | 6924.4221 | 2317.6472 | 1.4404 | 45 | 0.00014799 | 763 | 359.43 | 1356 | 0.051234 | 2.3055 | 1165 | 0.91 | 749
371 | CURTIS 1701CB | 163351701 | CURTIS 1701 | CB | FALSE | 20034.2871 | 12973.5363 | 8.0631 | 159 | 0.00012464 | 1103 | 555.1824 | 1140 | 0.051116 | 8.1275 | 1166 | 0.08 | 1582
8728 | CORRAL 1103569005 | 162991103 | CORRAL 1103 | 569005 | FALSE | 3858.1769 | 1152.5978 | 0.71634 | 38 | 7.7445e-05 | 2278 | 606.2479 | 1095 | 0.051027 | 1.939 | 1167 |  | 3255
3664 | PLACERVILLE 2106CB | 153082106 | PLACERVILLE 2106 | CB | FALSE | 10545.3693 | 10545.3693 | 6.554 | 31 | 0.00031506 | 112 | 137.2983 | 1822 | 0.050873 | 1.5771 | 1168 | 0.17 | 1226
10993 | MESA 1103737698 | 182821103 | MESA 1103 | 737698 | TRUE | 340.8251 | 324.8619 | 0.2019 | 3 | 4.5459e-05 | 3153 | 1051.0501 | 795 | 0.050749 | 0.15225 | 1169 |  | 3626
7973 | PENRYN 110550548 | 152561105 | PENRYN 1105 | 50548 | TRUE | 7824.3085 | 154.2272 | 0.095853 | 58 | 0.00014087 | 856 | 418.2026 | 1274 | 0.050695 | 2.9403 | 1170 | 1.85 | 638
9859 | CUYAMA 1103684566 | 253141103 | CUYAMA 1103 | 684566 | FALSE | 4872.6951 | 4856.693 | 3.0185 | 4 | 3.3492e-05 | 3376 | 2480.1079 | 347 | 0.050626 | 0.20251 | 1171 |  | 3437
7777 | GANSNER 11012424 | 103021101 | GANSNER 1101 | 2424 | FALSE | 30415.1718 | 30186.9031 | 18.7613 | 141 | 6.6531e-05 | 2572 | 747.4809 | 977 | 0.050559 | 7.1288 | 1172 | 0.17 | 1231
10622 | TEJON 1103286542 | 252931103 | TEJON 1103 | 286542 | FALSE | 9381.8687 | 3501.8559 | 2.1764 | 25 | 2.3634e-05 | 3508 | 2087.6942 | 432 | 0.050527 | 1.2632 | 1173 |  | 3581
2224 | COTATI 1103148 | 42271103 | COTATI 1103 | 148 | FALSE | 24974.2018 | 24850.3478 | 15.4446 | 107 | 5.3405e-05 | 2952 | 932.2932 | 869 | 0.050374 | 5.39 | 1174 | 0.13 | 1343
2728 | MESA 1103M72 | 182821103 | MESA 1103 | M72 | FALSE | 24045.3968 | 13551.8371 | 8.4225 | 180 | 5.9996e-05 | 2776 | 772.2065 | 958 | 0.050224 | 9.0403 | 1175 | 0.09 | 1574
4743 | WYANDOTTE 11031508 | 102911103 | WYANDOTTE 1103 | 1508 | FALSE | 43792.5733 | 43792.5733 | 27.2173 | 249 | 0.00022481 | 303 | 269.7872 | 1498 | 0.050062 | 12.4656 | 1176 | 0.5 | 893
1729 | LUCERNE 1106664 | 43351106 | LUCERNE 1106 | 664 | FALSE | 17972.9054 | 15503.1919 | 9.6353 | 140 | 0.00013278 | 964 | 291.1861 | 1461 | 0.050043 | 7.006 | 1177 | 0.12 | 1389
1094 | HIGGINS 110332120 | 152691103 | HIGGINS 1103 | 32120 | FALSE | 65924.4872 | 65394.3269 | 40.6428 | 485 | 0.00015495 | 695 | 454.7289 | 1240 | 0.049959 | 24.23 | 1178 | 0.23 | 1120
1827 | BELL 11082226 | 152701108 | BELL 1108 | 2226 | FALSE | 41003.1194 | 38762.6482 | 24.0911 | 329 | 0.00015086 | 729 | 321.4507 | 1412 | 0.049738 | 16.3638 | 1179 | 0.14 | 1330
971 | KANAKA 110183288 | 103221101 | KANAKA 1101 | 83288 | FALSE | 27936.7507 | 27936.7507 | 17.3628 | 140 | 0.00010219 | 1600 | 523.0336 | 1179 | 0.049736 | 6.9631 | 1180 | 56.24 | 100
6396 | MC ARTHUR 11011490 | 103491101 | MC ARTHUR 1101 | 1490 | FALSE | 24262.143 | 16986.9503 | 10.5575 | 122 | 4.6732e-05 | 3120 | 1014.4444 | 820 | 0.0497 | 6.0634 | 1181 | 0.01 | 2607
1501 | PIERCY 2110XR258 | 83912110 | PIERCY 2110 | XR258 | FALSE | 42613.4021 | 35307.703 | 21.9439 | 117 | 7.1286e-05 | 2438 | 813.0901 | 929 | 0.049692 | 5.814 | 1182 | 0.07 | 1728
4371 | BELLEVUE 2103552 | 43182103 | BELLEVUE 2103 | 552 | FALSE | 24092.9744 | 15233.6156 | 9.4678 | 172 | 0.00013239 | 975 | 420.6103 | 1272 | 0.049565 | 8.5251 | 1183 | 2.64 | 591
774 | MORGAN HILL 2110654924 | 83242110 | MORGAN HILL 2110 | 654924 | FALSE | 8067.2123 | 4423.0701 | 2.749 | 61 | 8.0217e-05 | 2200 | 663.8303 | 1048 | 0.049343 | 3.0099 | 1184 |  | 2692
4796 | SISQUOC 1102M52 | 182811102 | SISQUOC 1102 | M52 | FALSE | 56469.342 | 54530.2399 | 33.8908 | 131 | 6.7691e-05 | 2540 | 719.2711 | 1001 | 0.04915 | 6.4386 | 1185 | 0.09 | 1551
899 | RACETRACK 170455798 | 163761704 | RACETRACK 1704 | 55798 | FALSE | 37886.6196 | 37886.6196 | 23.5467 | 246 | 0.00011154 | 1383 | 632.8382 | 1075 | 0.049086 | 12.0752 | 1186 | 6.76 | 461
8632 | STELLING 11102243 | 83481110 | STELLING 1110 | 2243 | FALSE | 3051.2175 | 3051.2175 | 1.8963 | 16 | 0.00019188 | 434 | 257.113 | 1528 | 0.049051 | 0.78482 | 1187 | 4.86 | 503
4409 | HIGGINS 11071070 | 152691107 | HIGGINS 1107 | 1070 | FALSE | 13188.3135 | 12735.6646 | 7.9153 | 100 | 8.36e-05 | 2108 | 545.0696 | 1153 | 0.048737 | 4.8737 | 1188 | 0.08 | 1639
2076 | SAN JUSTO 110136902 | 183181101 | SAN JUSTO 1101 | 36902 | FALSE | 23754.9885 | 19990.5557 | 12.4242 | 147 | 6.372e-05 | 2656 | 753.8177 | 971 | 0.048735 | 7.1641 | 1189 | 0.05 | 2037
6423 | TASSAJARA 2113MR276 | 14662113 | TASSAJARA 2113 | MR276 | FALSE | 6265.9535 | 6199.9698 | 3.8533 | 42 | 0.00011011 | 1409 | 507.3387 | 1193 | 0.048684 | 2.0447 | 1190 | 0.45 | 920
7009 | PENRYN 110551676 | 152561105 | PENRYN 1105 | 51676 | FALSE | 18975.7232 | 12910.4516 | 8.0239 | 145 | 0.00015332 | 718 | 372.9974 | 1332 | 0.048603 | 7.0475 | 1191 | 1.53 | 667
9522 | STONE CORRAL 1110894956 | 252921110 | STONE CORRAL 1110 | 894956 | FALSE | 2635.3424 | 1243.2231 | 0.77267 | 16 | 4.142e-05 | 3237 | 1280.1289 | 689 | 0.048471 | 0.77554 | 1192 |  | 3371
4908 | DIVIDE 1103567884 | 182571103 | DIVIDE 1103 | 567884 | FALSE | 4535.2993 | 4025.5628 | 2.5019 | 27 | 5.6021e-05 | 2887 | 815.5904 | 927 | 0.048164 | 1.3004 | 1193 |  | 2926
537 | FORT SEWARD 11211602 | 192321121 | FORT SEWARD 1121 | 1602 | FALSE | 36538.7848 | 29307.7542 | 18.2149 | 109 | 0.00014214 | 837 | 344.2493 | 1379 | 0.048111 | 5.244 | 1194 | 0.07 | 1681
522 | MONTE RIO 1111292 | 42811111 | MONTE RIO 1111 | 292 | FALSE | 31568.6739 | 25055.0465 | 15.5718 | 165 | 0.00011528 | 1294 | 534.9666 | 1165 | 0.048057 | 7.9294 | 1195 | 0.1 | 1486
6679 | LAYTONVILLE 11011760 | 42681101 | LAYTONVILLE 1101 | 1760 | FALSE | 20336.5883 | 15610.272 | 9.7018 | 73 | 0.00026452 | 183 | 220.0765 | 1605 | 0.048043 | 3.5072 | 1196 | 0 | 2647
7262 | LOW GAP 11014160 | 192411101 | LOW GAP 1101 | 4160 | FALSE | 34990.3559 | 34990.3559 | 21.7466 | 194 | 0.00015367 | 716 | 332.5299 | 1395 | 0.047994 | 9.3109 | 1197 | 0.11 | 1435
2115 | GARBERVILLE 1102CB | 192221102 | GARBERVILLE 1102 | CB | FALSE | 26803.1335 | 19300.4618 | 11.9953 | 191 | 0.00043617 | 57 | 153.1917 | 1768 | 0.047992 | 9.1665 | 1198 | 0.08 | 1590
859 | SALT SPRINGS 21011216 | 163692101 | SALT SPRINGS 2101 | 1216 | FALSE | 8821.9491 | 8821.9491 | 5.4829 | 32 | 4.4432e-05 | 3178 | 673.2647 | 1041 | 0.04796 | 1.5347 | 1199 | 0.02 | 2470
4717 | CAMBRIA 1101V76 | 182771101 | CAMBRIA 1101 | V76 | FALSE | 30510.6388 | 30510.6388 | 18.9625 | 59 | 6.8997e-05 | 2510 | 662.2635 | 1050 | 0.047925 | 2.8276 | 1200 | 0.05 | 2034
3890 | KANAKA 110165606 | 103221101 | KANAKA 1101 | 65606 | FALSE | 20505.679 | 20505.679 | 12.7444 | 145 | 0.00013634 | 916 | 329.1085 | 1398 | 0.047918 | 6.9481 | 1201 | 65.5 | 77
11044 | SAN LUIS OBISPO 1104753254 | 182631104 | SAN LUIS OBISPO 1104 | 753254 | TRUE | 576.081 | 561.1486 | 0.34876 | 2 | 0.0001316 | 988 | 1237.8633 | 707 | 0.047657 | 0.095314 | 1202 |  | 3631
868 | PEORIA 170459596 | 163781704 | PEORIA 1704 | 59596 | FALSE | 58128.5973 | 33598.813 | 20.8818 | 294 | 6.8689e-05 | 2517 | 659.4011 | 1054 | 0.047553 | 13.9806 | 1203 | 0.08 | 1603
5643 | CLEAR LAKE 1102991285 | 42141102 | CLEAR LAKE 1102 | 991285 | TRUE | 2786.1304 | 525.9001 | 0.32685 | 24 | 8.6607e-05 | 2019 | 543.9338 | 1154 | 0.047469 | 1.1393 | 1204 |  | 2968
2996 | BURNEY 11012402 | 103311101 | BURNEY 1101 | 2402 | FALSE | 6035.4639 | 2411.6802 | 1.4989 | 18 | 6.5093e-05 | 2608 | 759.0384 | 966 | 0.047353 | 0.85235 | 1205 | 0.04 | 2096
982 | WEST POINT 11024788 | 163201102 | WEST POINT 1102 | 4788 | FALSE | 111874.9537 | 111874.9537 | 69.5307 | 673 | 7.0255e-05 | 2460 | 791.3267 | 951 | 0.047319 | 31.8454 | 1206 | 1.08 | 718
6337 | MIWUK 170219772 | 163661702 | MIWUK 1702 | 19772 | FALSE | 6198.5938 | 6198.5938 | 3.8525 | 41 | 7.7179e-05 | 2283 | 525.9561 | 1177 | 0.047283 | 1.9386 | 1207 | 48.67 | 125
1317 | MOLINO 1102178 | 42571102 | MOLINO 1102 | 178 | FALSE | 21896.763 | 19626.441 | 12.1979 | 182 | 0.0001498 | 741 | 376.3772 | 1328 | 0.047227 | 8.5954 | 1208 | 24.56 | 276
2756 | AUBERRY 1101R2845 | 254151101 | AUBERRY 1101 | R2845 | FALSE | 28680.0593 | 28680.0593 | 17.8248 | 172 | 4.0941e-05 | 3246 | 1025.9007 | 811 | 0.047182 | 8.1154 | 1209 | 0.19 | 1180
1878 | JESSUP 110168362 | 103441101 | JESSUP 1101 | 68362 | FALSE | 11797.2095 | 8312.3827 | 5.1662 | 96 | 0.00012657 | 1070 | 343.9077 | 1382 | 0.047076 | 4.5193 | 1210 |  | 2751
1899 | SAN BENITO 2104785888 | 182742104 | SAN BENITO 2104 | 785888 | FALSE | 11268.8078 | 7730.7085 | 4.8047 | 49 | 7.806e-05 | 2258 | 321.3673 | 1413 | 0.047021 | 2.304 | 1211 |  | 2753
1312 | MOUNTAIN QUARRIES 210192474 | 152282101 | MOUNTAIN QUARRIES 2101 | 92474 | FALSE | 25104.6477 | 24305.4181 | 15.1059 | 173 | 0.00013452 | 934 | 428.2739 | 1261 | 0.046937 | 8.12 | 1212 | 0.26 | 1060
9280 | FREMONT 1104MR339 | 14351104 | FREMONT 1104 | MR339 | FALSE | 11213.6735 | 1921.2331 | 1.1941 | 73 | 5.8956e-05 | 2809 | 692.7863 | 1028 | 0.046887 | 3.4227 | 1213 | 1 | 731
10367 | PEORIA 170488630 | 163781704 | PEORIA 1704 | 88630 | FALSE | 1252.5971 | 1252.5971 | 0.77849 | 6 | 6.5372e-05 | 2605 | 876.4135 | 895 | 0.046842 | 0.28105 | 1214 | 0.03 | 2399
3920 | LLAGAS 2107XR178 | 83182107 | LLAGAS 2107 | XR178 | FALSE | 20866.1928 | 9493.9491 | 5.9005 | 138 | 8.7818e-05 | 1989 | 483.5128 | 1211 | 0.04683 | 6.4625 | 1215 | 0.94 | 744
9293 | DUNLAP 110239190 | 254061102 | DUNLAP 1102 | 39190 | FALSE | 2877.2566 | 2877.2566 | 1.7882 | 17 | 6.3388e-05 | 2665 | 760.9398 | 964 | 0.046743 | 0.79463 | 1216 | 0 | 2644
9995 | GEYSERVILLE 1102180193 | 42891102 | GEYSERVILLE 1102 | 180193 | FALSE | 3981.725 | 3477.0858 | 2.161 | 23 | 0.00010067 | 1630 | 430.5545 | 1259 | 0.046684 | 1.0737 | 1217 |  | 3467
2795 | BELL 1108467470 | 152701108 | BELL 1108 | 467470 | FALSE | 4805.9002 | 2987.9 | 1.857 | 40 | 0.00023296 | 271 | 103.254 | 1936 | 0.046424 | 1.857 | 1218 |  | 2799
6866 | EDENVALE 1102XR064 | 82951102 | EDENVALE 1102 | XR064 | FALSE | 6026.8923 | 1175.6095 | 0.73065 | 35 | 8.4777e-05 | 2070 | 462.9277 | 1232 | 0.046387 | 1.6236 | 1219 |  | 3069
2884 | MC ARTHUR 110137388 | 103491101 | MC ARTHUR 1101 | 37388 | FALSE | 20103.5682 | 13050.4067 | 8.1109 | 56 | 2.1126e-05 | 3533 | 2437.488 | 352 | 0.046193 | 2.5868 | 1220 | 0 | 2639
8090 | PENRYN 1105817491 | 152561105 | PENRYN 1105 | 817491 | FALSE | 3153.3616 | 2279.4584 | 1.4167 | 24 | 0.00010509 | 1523 | 532.8427 | 1169 | 0.046183 | 1.1084 | 1221 |  | 3191
196 | MILPITAS 1109XR082 | 82831109 | MILPITAS 1109 | XR082 | FALSE | 32889.5484 | 31674.5025 | 19.6858 | 186 | 6.2383e-05 | 2710 | 716.1395 | 1007 | 0.046133 | 8.5807 | 1222 | 0.21 | 1151
9874 | JARVIS 1108767280 | 13501108 | JARVIS 1108 | 767280 | TRUE | 1164.558 | 816.4039 | 0.5074 | 11 | 4.3875e-05 | 3191 | 579.646 | 1124 | 0.046117 | 0.50728 | 1223 |  | 3440
3653 | PUEBLO 2103678 | 43292103 | PUEBLO 2103 | 678 | FALSE | 57111.2211 | 56857.8795 | 35.3374 | 325 | 0.00011031 | 1406 | 496.7562 | 1204 | 0.046077 | 14.9751 | 1224 | 2.05 | 626
4529 | MC ARTHUR 110138998 | 103491101 | MC ARTHUR 1101 | 38998 | TRUE | 9317.0359 | 189.4976 | 0.11777 | 61 | 3.5e-05 | 3353 | 912.9133 | 879 | 0.046064 | 2.8099 | 1225 | 0.01 | 2570
9562 | MOLINO 1101600112 | 42571101 | MOLINO 1101 | 600112 | FALSE | 2016.2056 | 1283.9759 | 0.798 | 18 | 0.00016569 | 586 | 185.2798 | 1671 | 0.045774 | 0.82393 | 1226 |  | 3379
8471 | MONTICELLO 1101654 | 43051101 | MONTICELLO 1101 | 654 | FALSE | 14047.9314 | 13220.1574 | 8.2164 | 71 | 8.6928e-05 | 2013 | 576.6406 | 1126 | 0.045547 | 3.2338 | 1227 | 0.06 | 1895
9084 | SWIFT 2110XR254 | 83392110 | SWIFT 2110 | XR254 | FALSE | 40510.5344 | 40510.5344 | 25.1775 | 134 | 6.9418e-05 | 2490 | 745.0432 | 979 | 0.045544 | 6.1028 | 1228 | 0.31 | 1003
5247 | MOLINO 1102658 | 42571102 | MOLINO 1102 | 658 | FALSE | 17510.52 | 17510.52 | 10.8829 | 107 | 0.00014355 | 818 | 343.9435 | 1381 | 0.045341 | 4.8515 | 1229 | 50.23 | 119
1624 | CLAY 11037124 | 163341103 | CLAY 1103 | 7124 | FALSE | 51663.5431 | 17797.9944 | 11.0615 | 286 | 6.2921e-05 | 2684 | 727.3308 | 993 | 0.045279 | 12.9498 | 1230 | 0.05 | 2026
6683 | UKIAH 11143606 | 42771114 | UKIAH 1114 | 3606 | FALSE | 26641.1753 | 17219.5096 | 10.702 | 129 | 8.6419e-05 | 2025 | 738.4699 | 985 | 0.045178 | 5.828 | 1231 | 0.09 | 1541
6114 | GANSNER 110137550 | 103021101 | GANSNER 1101 | 37550 | TRUE | 5259.0816 | 590.535 | 0.36702 | 33 | 6.5837e-05 | 2592 | 741.2586 | 983 | 0.045042 | 1.4864 | 1232 | 1.25 | 693
10276 | LAKEVILLE 1102367100 | 43371102 | LAKEVILLE 1102 | 367100 | TRUE | 1041.0726 | 900.8036 | 0.55985 | 6 | 8.144e-05 | 2169 | 654.3693 | 1059 | 0.04493 | 0.26958 | 1233 |  | 3526
3592 | CURTIS 17039330 | 163351703 | CURTIS 1703 | 9330 | FALSE | 66516.2766 | 66516.2766 | 41.3401 | 345 | 4.8089e-05 | 3091 | 936.7226 | 867 | 0.044648 | 15.4037 | 1234 | 0.27 | 1056
1338 | SILVERADO 210437632 | 43432104 | SILVERADO 2104 | 37632 | FALSE | 42770.2942 | 42770.2942 | 26.5819 | 304 | 0.0001591 | 651 | 314.3513 | 1426 | 0.044601 | 13.5588 | 1235 | 2.55 | 599
9592 | BELL 1107912460 | 152701107 | BELL 1107 | 912460 | TRUE | 716.9415 | 226.2188 | 0.1406 | 6 | 0.0002094 | 362 | 319.3069 | 1418 | 0.044495 | 0.26697 | 1236 |  | 3384
9543 | GARBERVILLE 110237054 | 192221102 | GARBERVILLE 1102 | 37054 | FALSE | 14849.4038 | 14394.233 | 8.9461 | 76 | 0.00045585 | 46 | 99.7602 | 1954 | 0.044439 | 3.3774 | 1237 | 0.04 | 2218
528 | PLACERVILLE 210692012 | 153082106 | PLACERVILLE 2106 | 92012 | FALSE | 29794.6367 | 29794.6367 | 18.5175 | 219 | 0.00021006 | 358 | 266.7744 | 1505 | 0.044304 | 9.7026 | 1238 | 27.19 | 260
2289 | PASO ROBLES 1103351084 | 182611103 | PASO ROBLES 1103 | 351084 | FALSE | 14339.9461 | 3813.7275 | 2.3702 | 91 | 6.4148e-05 | 2639 | 844.8485 | 915 | 0.044255 | 4.0272 | 1239 |  | 2770
4151 | SHINGLE SPRINGS 2109CB | 153652109 | SHINGLE SPRINGS 2109 | CB | FALSE | 44653.7534 | 44000.0643 | 27.3462 | 341 | 0.00012378 | 1124 | 546.8562 | 1150 | 0.044085 | 15.0331 | 1240 | 0.94 | 742
8694 | MC ARTHUR 11011544 | 103491101 | MC ARTHUR 1101 | 1544 | FALSE | 44972.2866 | 27291.0085 | 16.9615 | 135 | 2.4864e-05 | 3497 | 2130.6474 | 417 | 0.044056 | 5.9476 | 1241 | 0 | 2640
5303 | STONE CORRAL 11087100 | 252921108 | STONE CORRAL 1108 | 7100 | FALSE | 29355.7923 | 3757.8694 | 2.3355 | 130 | 3.9155e-05 | 3282 | 1207.5405 | 728 | 0.04396 | 5.7148 | 1242 | 0.01 | 2576
5138 | SUMMIT 11022302 | 152591102 | SUMMIT 1102 | 2302 | FALSE | 2152.9343 | 2152.9343 | 1.3381 | 19 | 6.3222e-05 | 2671 | 648.1357 | 1067 | 0.043905 | 0.8342 | 1243 | 0.01 | 2616
3403 | PENRYN 11051378 | 152561105 | PENRYN 1105 | 1378 | FALSE | 3084.1467 | 1447.5189 | 0.89964 | 25 | 0.00011131 | 1388 | 372.4728 | 1334 | 0.043839 | 1.096 | 1244 | 0.02 | 2452
5562 | GARBERVILLE 110139524 | 192221101 | GARBERVILLE 1101 | 39524 | FALSE | 24862.4083 | 8232.0089 | 5.1162 | 138 | 0.00038497 | 72 | 130.5694 | 1844 | 0.04372 | 6.0334 | 1245 | 0.03 | 2332
3303 | BIG BEND 1101180398 | 103751101 | BIG BEND 1101 | 180398 | FALSE | 8946.0191 | 8946.0191 | 5.56 | 48 | 0.0002082 | 371 | 244.7887 | 1555 | 0.04366 | 2.0957 | 1246 | 24.5 | 278
5481 | VACAVILLE 110847860 | 63601108 | VACAVILLE 1108 | 47860 | TRUE | 6236.9476 | 466.0192 | 0.28963 | 54 | 7.3661e-05 | 2372 | 319.7615 | 1416 | 0.043573 | 2.353 | 1247 | 0.02 | 2411
8994 | SAN LUIS OBISPO 1104982992 | 182631104 | SAN LUIS OBISPO 1104 | 982992 | FALSE | 14390.2086 | 14390.2086 | 8.9436 | 52 | 4.6115e-05 | 3136 | 911.2189 | 880 | 0.043526 | 2.2633 | 1248 |  | 3292
6482 | UKIAH 1113691436 | 42771113 | UKIAH 1113 | 691436 | FALSE | 3576.8147 | 1680.7069 | 1.0446 | 28 | 0.00012089 | 1165 | 323.1464 | 1409 | 0.043449 | 1.2166 | 1249 |  | 3034
7283 | COVELO 1101112804 | 43061101 | COVELO 1101 | 112804 | FALSE | 30691.3669 | 16512.5111 | 10.2626 | 67 | 9.7484e-05 | 1701 | 651.0362 | 1064 | 0.043443 | 2.9107 | 1250 |  | 3111
2688 | STILLWATER 11021466 | 103561102 | STILLWATER 1102 | 1466 | FALSE | 33154.3349 | 33039.7041 | 20.5343 | 211 | 0.0001572 | 672 | 705.5165 | 1017 | 0.043245 | 9.1248 | 1251 | 0.07 | 1677
6122 | EEL RIVER 11024814 | 192381102 | EEL RIVER 1102 | 4814 | FALSE | 44262.9015 | 43433.15 | 26.9939 | 117 | 0.00018022 | 512 | 271.8858 | 1490 | 0.043216 | 5.0562 | 1252 | 0.83 | 769
8658 | MENLO 11037902 | 24131103 | MENLO 1103 | 7902 | FALSE | 26218.9532 | 18823.9554 | 11.6992 | 143 | 0.00018704 | 461 | 146.5682 | 1787 | 0.043162 | 6.1722 | 1253 | 0.06 | 1892
5986 | SILVERADO 210478268 | 43432104 | SILVERADO 2104 | 78268 | FALSE | 15647.3206 | 15647.3206 | 9.7249 | 114 | 0.00016165 | 623 | 303.7186 | 1445 | 0.043133 | 4.9171 | 1254 | 73.54 | 60
3705 | ALTO 11221212 | 42031122 | ALTO 1122 | 1212 | FALSE | 3797.0171 | 2977.1941 | 1.8503 | 25 | 0.00010853 | 1436 | 197.8244 | 1646 | 0.043056 | 1.0764 | 1255 | 28.71 | 247
565 | CALPELLA 1101CB | 43411101 | CALPELLA 1101 | CB | FALSE | 32987.4913 | 18947.9362 | 11.7762 | 226 | 0.00012255 | 1139 | 327.7945 | 1401 | 0.043018 | 9.722 | 1256 | 0.04 | 2117
1815 | OTTER 110298036 | 182941102 | OTTER 1102 | 98036 | FALSE | 14803.9566 | 14803.9566 | 9.2007 | 64 | 0.00012504 | 1098 | 294.291 | 1456 | 0.042868 | 2.7435 | 1257 | 0.04 | 2216
5821 | HIGHLANDS 11034630 | 43361103 | HIGHLANDS 1103 | 4630 | FALSE | 5558.0773 | 1729.1767 | 1.0747 | 42 | 7.7824e-05 | 2266 | 548.6975 | 1148 | 0.042814 | 1.7982 | 1258 | 0.05 | 2061
1927 | HIGGINS 1110166282 | 152691110 | HIGGINS 1110 | 166282 | FALSE | 38601.364 | 38601.364 | 23.9909 | 256 | 0.00012662 | 1069 | 425.8459 | 1266 | 0.042498 | 10.8796 | 1259 |  | 2757
6705 | GIRVAN 11021028 | 103401102 | GIRVAN 1102 | 1028 | FALSE | 28404.1063 | 28404.1063 | 17.6533 | 208 | 0.00012459 | 1106 | 555.8921 | 1139 | 0.042483 | 8.8364 | 1260 | 8.08 | 437
3470 | OILFIELDS 1103370932 | 182391103 | OILFIELDS 1103 | 370932 | TRUE | 2172.9579 | 619.9296 | 0.38529 | 6 | 3.0451e-05 | 3423 | 729.2934 | 991 | 0.042464 | 0.25478 | 1261 |  | 2828
9825 | GIRVAN 1101CB | 103401101 | GIRVAN 1101 | CB | FALSE | 5303.193 | 2471.5392 | 1.5361 | 31 | 0.0001612 | 628 | 200.4454 | 1640 | 0.042406 | 1.3146 | 1262 | 0.01 | 2593
4531 | CRESCENT MILLS 21013113 | 103132101 | CRESCENT MILLS 2101 | 3113 | FALSE | 1919.7007 | 1919.7007 | 1.1931 | 9 | 5.1754e-05 | 2999 | 970.9306 | 849 | 0.042389 | 0.3815 | 1263 | 12.05 | 376
4502 | WILLITS 1103968 | 42661103 | WILLITS 1103 | 968 | FALSE | 44551.6644 | 42969.09 | 26.7055 | 283 | 0.00010481 | 1533 | 381.6576 | 1318 | 0.042383 | 11.9944 | 1264 | 33.68 | 221
293 | MENDOCINO 110131322 | 42951101 | MENDOCINO 1101 | 31322 | FALSE | 46269.6305 | 9420.014 | 5.8546 | 310 | 0.00011583 | 1276 | 412.2583 | 1282 | 0.04237 | 13.1348 | 1265 | 0.05 | 1992
332 | MESA 1101CB | 182821101 | MESA 1101 | CB | FALSE | 40952.4168 | 22299.6831 | 13.8593 | 230 | 5.1221e-05 | 3009 | 603.2532 | 1096 | 0.042367 | 9.7444 | 1266 | 0.03 | 2242
6761 | HORSESHOE 11011682 | 152571101 | HORSESHOE 1101 | 1682 | TRUE | 14763.8266 | 326.6132 | 0.20299 | 112 | 0.00012357 | 1130 | 359.4666 | 1355 | 0.042324 | 4.7402 | 1267 | 0.48 | 906
4789 | APPLE HILL 110412842 | 153661104 | APPLE HILL 1104 | 12842 | FALSE | 27066.2595 | 25454.1408 | 15.8199 | 209 | 0.00018752 | 457 | 122.8933 | 1862 | 0.042311 | 8.8429 | 1268 | 24.93 | 275
5435 | SUNOL 1101MR299 | 14241101 | SUNOL 1101 | MR299 | FALSE | 7955.2462 | 7955.2462 | 4.9442 | 58 | 9.0049e-05 | 1910 | 452.8222 | 1243 | 0.042276 | 2.452 | 1269 | 0.4 | 946
5875 | MESA 11016113 | 182821101 | MESA 1101 | 6113 | FALSE | 15649.5972 | 2800.3205 | 1.7404 | 100 | 5.0937e-05 | 3015 | 1017.9876 | 816 | 0.042268 | 4.2268 | 1270 | 0.86 | 762
6536 | PINE GROVE 11026080 | 163751102 | PINE GROVE 1102 | 6080 | FALSE | 55307.7629 | 55307.7629 | 34.374 | 322 | 0.00011497 | 1300 | 414.8336 | 1277 | 0.042249 | 13.6042 | 1271 | 0.17 | 1242
10453 | RIO DELL 11027124 | 192251102 | RIO DELL 1102 | 7124 | FALSE | 1081.3743 | 1081.3743 | 0.67208 | 5 | 0.0002308 | 283 | 190.3883 | 1663 | 0.042229 | 0.21114 | 1272 | 0.05 | 1941
9767 | SAN BERNARD 1101641042 | 253191101 | SAN BERNARD 1101 | 641042 | FALSE | 10558.7861 | 2300.7684 | 1.4299 | 22 | 2.7605e-05 | 3464 | 1880.7413 | 480 | 0.042194 | 0.92827 | 1273 |  | 3414
7173 | OTTER 110237132 | 182941102 | OTTER 1102 | 37132 | FALSE | 9343.2123 | 9343.2123 | 5.8068 | 50 | 0.00010209 | 1601 | 598.7122 | 1102 | 0.042173 | 2.1086 | 1274 |  | 3104
7839 | FROGTOWN 1702204480 | 163451702 | FROGTOWN 1702 | 204480 | TRUE | 3182.9165 | 807.68 | 0.50198 | 28 | 0.00015459 | 699 | 296.133 | 1455 | 0.04209 | 1.1785 | 1275 |  | 3169
1556 | HOPLAND 110180620 | 42251101 | HOPLAND 1101 | 80620 | FALSE | 8949.87 | 1997.9252 | 1.2417 | 51 | 7.4695e-05 | 2340 | 506.899 | 1194 | 0.04205 | 2.1446 | 1276 | 0.61 | 849
796 | MESA 1101M86 | 182821101 | MESA 1101 | M86 | FALSE | 33517.8054 | 20500.8716 | 12.7414 | 217 | 4.9333e-05 | 3053 | 762.6869 | 961 | 0.041844 | 9.0801 | 1277 | 0.04 | 2086
4020 | CABRILLO 1103Y10 | 183101103 | CABRILLO 1103 | Y10 | FALSE | 24460.4132 | 7788.8369 | 4.8408 | 122 | 3.6552e-05 | 3322 | 632.6734 | 1076 | 0.041779 | 5.0971 | 1278 | 0.05 | 1949
4294 | FITCH MOUNTAIN 11134566 | 42751113 | FITCH MOUNTAIN 1113 | 4566 | FALSE | 28160.2778 | 20128.0864 | 12.5097 | 180 | 0.00011406 | 1319 | 393.9766 | 1301 | 0.041761 | 7.5169 | 1279 | 0.11 | 1420
3368 | PEORIA 17051834 | 163781705 | PEORIA 1705 | 1834 | FALSE | 38353.1383 | 37922.7084 | 23.5691 | 217 | 8.1071e-05 | 2182 | 531.0758 | 1172 | 0.041581 | 9.0231 | 1280 | 0.17 | 1247
4811 | CALAVERAS CEMENT 1101502 | 162211101 | CALAVERAS CEMENT 1101 | 502 | FALSE | 65884.6113 | 60591.0346 | 37.6576 | 331 | 9.3364e-05 | 1812 | 435.9933 | 1257 | 0.041554 | 13.7543 | 1281 | 0.21 | 1137
8493 | COTATI 1102282 | 42271102 | COTATI 1102 | 282 | FALSE | 8222.1189 | 4475.09 | 2.7813 | 62 | 8.3509e-05 | 2115 | 543.5705 | 1155 | 0.041526 | 2.5746 | 1282 | 2.35 | 612
3229 | WISE 1102CB | 152271102 | WISE 1102 | CB | FALSE | 23260.435 | 22633.2401 | 14.0667 | 177 | 0.00014209 | 838 | 392.5466 | 1305 | 0.041442 | 7.3353 | 1283 | 0.11 | 1427
2423 | APPLE HILL 110413512 | 153661104 | APPLE HILL 1104 | 13512 | FALSE | 49131.7705 | 45791.8869 | 28.4598 | 345 | 0.00019634 | 412 | 199.5912 | 1642 | 0.041392 | 14.2801 | 1284 | 59.2 | 89
3013 | BIG MEADOWS 21012586 | 102812101 | BIG MEADOWS 2101 | 2586 | FALSE | 17615.5168 | 10070.6101 | 6.2589 | 91 | 4.8503e-05 | 3075 | 1089.5717 | 778 | 0.041237 | 3.7526 | 1285 | 0.09 | 1567
6401 | COPPERMINE 1104556430 | 252411104 | COPPERMINE 1104 | 556430 | FALSE | 26122.847 | 7792.8441 | 4.8433 | 122 | 1.6369e-05 | 3574 | 2433.0686 | 354 | 0.041063 | 5.0096 | 1286 |  | 3028
9989 | ORO FINO 11022236 | 103031102 | ORO FINO 1102 | 2236 | FALSE | 4120.4561 | 4120.4561 | 2.5609 | 11 | 0.00027956 | 156 | 116.7508 | 1889 | 0.040994 | 0.45093 | 1287 | 0.26 | 1069
3633 | BIG BEND 11021972 | 103751102 | BIG BEND 1102 | 1972 | FALSE | 34265.9827 | 34265.9827 | 21.2964 | 177 | 0.00011711 | 1243 | 377.3246 | 1326 | 0.040961 | 7.25 | 1288 | 73.04 | 64
7419 | MARTELL 110299214 | 163011102 | MARTELL 1102 | 99214 | FALSE | 3296.9506 | 2953.539 | 1.8356 | 21 | 0.00014798 | 764 | 541.677 | 1157 | 0.040838 | 0.85759 | 1289 | 0.04 | 2193
5589 | BUELLTON 1101Y36 | 183041101 | BUELLTON 1101 | Y36 | FALSE | 73124.8896 | 60717.9561 | 37.7365 | 283 | 4.3104e-05 | 3207 | 946.8115 | 863 | 0.0408 | 11.5464 | 1290 | 0.14 | 1321
2824 | GEYSERVILLE 1101166 | 42891101 | GEYSERVILLE 1101 | 166 | FALSE | 15936.7517 | 9969.1209 | 6.1958 | 110 | 0.00012238 | 1141 | 339.9187 | 1388 | 0.040759 | 4.4835 | 1291 | 0.03 | 2283
612 | DIAMOND SPRINGS 11062100 | 152261106 | DIAMOND SPRINGS 1106 | 2100 | FALSE | 62879.0761 | 62879.0761 | 39.0796 | 403 | 0.00011682 | 1254 | 355.7448 | 1364 | 0.040696 | 16.4004 | 1292 | 0.14 | 1318
4758 | LAYTONVILLE 1101402 | 42681101 | LAYTONVILLE 1101 | 402 | FALSE | 37926.2925 | 37584.6138 | 23.359 | 151 | 0.0001662 | 581 | 293.7692 | 1458 | 0.040695 | 6.145 | 1293 | 0.07 | 1764
7625 | ATASCADERO 1103440856 | 182541103 | ATASCADERO 1103 | 440856 | FALSE | 56881.4108 | 56011.6123 | 34.8114 | 349 | 6.3248e-05 | 2669 | 673.5389 | 1040 | 0.040647 | 14.1857 | 1294 |  | 3143
3291 | FRUITLAND 11426054 | 192311142 | FRUITLAND 1142 | 6054 | FALSE | 11579.672 | 11579.672 | 7.1968 | 58 | 0.00029784 | 132 | 184.0031 | 1677 | 0.040642 | 2.3572 | 1295 | 0.09 | 1573
2753 | CALPELLA 11011204 | 43411101 | CALPELLA 1101 | 1204 | FALSE | 18353.2445 | 15255.8356 | 9.4816 | 124 | 0.00012564 | 1084 | 378.7617 | 1322 | 0.040535 | 5.0263 | 1296 | 0.06 | 1888
6226 | FULTON 1107214 | 42561107 | FULTON 1107 | 214 | FALSE | 18868.3768 | 18868.3768 | 11.7268 | 142 | 0.0001516 | 725 | 205.0666 | 1626 | 0.040503 | 5.7514 | 1297 | 44.57 | 157
6297 | PEORIA 170176030 | 163781701 | PEORIA 1701 | 76030 | FALSE | 10072.8355 | 8222.4339 | 5.1103 | 55 | 9.557e-05 | 1739 | 498.7327 | 1202 | 0.040366 | 2.2201 | 1298 | 0.02 | 2538
4946 | WYANDOTTE 11031976 | 102911103 | WYANDOTTE 1103 | 1976 | FALSE | 38264.4277 | 38264.4277 | 23.7815 | 217 | 7.4462e-05 | 2346 | 572.7278 | 1128 | 0.040282 | 8.7412 | 1299 | 81.96 | 47
3803 | CALAVERAS CEMENT 1101CB | 162211101 | CALAVERAS CEMENT 1101 | CB | FALSE | 29408.7196 | 16846.5197 | 10.4702 | 203 | 0.00013798 | 894 | 318.5868 | 1420 | 0.040232 | 8.1671 | 1300 | 0.05 | 1952
601 | FORESTHILL 11022106 | 152181102 | FORESTHILL 1102 | 2106 | FALSE | 44861.5543 | 44861.5543 | 27.8816 | 264 | 0.00012115 | 1162 | 368.597 | 1341 | 0.040196 | 10.6117 | 1301 | 51.56 | 115
3937 | AUBERRY 1101176050 | 254151101 | AUBERRY 1101 | 176050 | FALSE | 33994.9384 | 33994.9384 | 21.128 | 168 | 3.5007e-05 | 3352 | 1021.4734 | 814 | 0.040157 | 6.7464 | 1302 |  | 2863
3563 | SHINGLE SPRINGS 21092053 | 153652109 | SHINGLE SPRINGS 2109 | 2053 | FALSE | 9238.0472 | 9238.0472 | 5.7415 | 74 | 7.8295e-05 | 2252 | 578.9534 | 1125 | 0.040131 | 2.9697 | 1303 | 18.91 | 317
639 | LAYTONVILLE 1101CB | 42681101 | LAYTONVILLE 1101 | CB | FALSE | 14777.824 | 9580.003 | 5.954 | 90 | 0.00019434 | 422 | 250.1874 | 1539 | 0.040116 | 3.6104 | 1304 | 6.07 | 474
8583 | UKIAH 1111168892 | 42771111 | UKIAH 1111 | 168892 | TRUE | 1078.2209 | 264.3207 | 0.16428 | 8 | 7.0494e-05 | 2456 | 277.1976 | 1478 | 0.040099 | 0.32079 | 1305 |  | 3240
6071 | SHINGLE SPRINGS 210981390 | 153652109 | SHINGLE SPRINGS 2109 | 81390 | FALSE | 29957.8137 | 29957.8137 | 18.6189 | 208 | 0.00014065 | 861 | 348.4797 | 1374 | 0.039915 | 8.3022 | 1306 | 0.15 | 1288
5271 | WILLITS 1104504 | 42661104 | WILLITS 1104 | 504 | FALSE | 36253.1832 | 36253.1832 | 22.5315 | 205 | 0.00010544 | 1509 | 471.8115 | 1221 | 0.039748 | 8.1484 | 1307 | 47.4 | 133
8156 | PIKE CITY 1102CB | 152201102 | PIKE CITY 1102 | CB | FALSE | 15315.8587 | 15315.8587 | 9.5189 | 44 | 0.00010811 | 1449 | 444.7581 | 1253 | 0.03956 | 1.7406 | 1308 | 15.25 | 349
1834 | CASTRO VALLEY 1110MR748 | 14091110 | CASTRO VALLEY 1110 | MR748 | FALSE | 10026.1125 | 10026.1125 | 6.2313 | 86 | 9.5898e-05 | 1731 | 353.7631 | 1368 | 0.039516 | 3.3984 | 1309 |  | 2749
4232 | GABILAN 1101989608 | 182331101 | GABILAN 1101 | 989608 | FALSE | 3673.9458 | 1209.612 | 0.75178 | 6 | 0.00015502 | 693 | 503.7259 | 1195 | 0.039513 | 0.23708 | 1310 |  | 2877
2029 | OCEANO 1102V56 | 182601102 | OCEANO 1102 | V56 | FALSE | 15985.6627 | 15022.8264 | 9.3367 | 115 | 6.4252e-05 | 2636 | 557.9025 | 1137 | 0.039442 | 4.5359 | 1311 | 0.1 | 1460
6282 | MOLINO 1101891 | 42571101 | MOLINO 1101 | 891 | FALSE | 5070.4899 | 5070.4899 | 3.1513 | 41 | 0.00012462 | 1104 | 268.5604 | 1501 | 0.03939 | 1.615 | 1312 | 2.7 | 588
7224 | MIRABEL 1101116 | 42091101 | MIRABEL 1101 | 116 | FALSE | 17433.6477 | 16625.8808 | 10.3331 | 112 | 0.00017861 | 515 | 262.5016 | 1515 | 0.039363 | 4.4087 | 1313 | 33.71 | 220
3752 | MONTE RIO 1113539938 | 42811113 | MONTE RIO 1113 | 539938 | FALSE | 4460.237 | 4460.237 | 2.7721 | 26 | 0.00021663 | 334 | 141.7664 | 1805 | 0.039354 | 1.0232 | 1314 |  | 2851
8901 | BRIDGEVILLE 110237486 | 192461102 | BRIDGEVILLE 1102 | 37486 | FALSE | 12199.5088 | 11162.2658 | 6.9374 | 85 | 0.00018807 | 454 | 224.247 | 1597 | 0.039237 | 3.3351 | 1315 | 0 | 2623
3640 | FROGTOWN 1702CB | 163451702 | FROGTOWN 1702 | CB | FALSE | 6932.7551 | 2351.3614 | 1.4614 | 47 | 0.00016197 | 622 | 176.7445 | 1692 | 0.039234 | 1.844 | 1316 | 0.02 | 2556
4627 | SAN LUIS OBISPO 1107V02 | 182631107 | SAN LUIS OBISPO 1107 | V02 | FALSE | 29266.1566 | 29266.1566 | 18.189 | 202 | 6.7472e-05 | 2550 | 602.2374 | 1099 | 0.039184 | 7.9151 | 1317 | 0.29 | 1026
2477 | CEDAR CREEK 11011656 | 103321101 | CEDAR CREEK 1101 | 1656 | FALSE | 51859.3271 | 51859.3271 | 32.2308 | 208 | 0.00010206 | 1602 | 466.1612 | 1228 | 0.039176 | 8.1485 | 1318 | 0.07 | 1727
6350 | NAPA 11121302 | 42021112 | NAPA 1112 | 1302 | FALSE | 55353.0299 | 32333.7369 | 20.0955 | 317 | 6.346e-05 | 2662 | 792.5298 | 949 | 0.039053 | 12.3798 | 1319 | 0.08 | 1620
798 | HIGGINS 1107CB | 152691107 | HIGGINS 1107 | CB | FALSE | 30614.8922 | 9216.7854 | 5.7283 | 243 | 0.00023355 | 268 | 176.6871 | 1693 | 0.03873 | 9.4114 | 1320 | 0.04 | 2075
10498 | CLAYTON 2212158138 | 12022212 | CLAYTON 2212 | 158138 | TRUE | 1490.1049 | 829.4376 | 0.5155 | 10 | 2.484e-05 | 3499 | 1008.6051 | 829 | 0.038704 | 0.38704 | 1321 |  | 3560
9150 | SPANISH CREEK 4401CB | 103104401 | SPANISH CREEK 4401 | CB | FALSE | 12760.2493 | 12447.7538 | 7.7363 | 22 | 0.00012371 | 1125 | 391.2799 | 1306 | 0.038702 | 0.85144 | 1322 | 6.72 | 462
561 | ALTO 11221260 | 42031122 | ALTO 1122 | 1260 | FALSE | 4901.8674 | 4807.0969 | 2.9876 | 36 | 0.00023996 | 246 | 168.4314 | 1724 | 0.038665 | 1.3919 | 1323 |  | 2682
2054 | PUEBLO 1104580658 | 43291104 | PUEBLO 1104 | 580658 | FALSE | 16767.5085 | 15111.3604 | 9.3918 | 107 | 6.1348e-05 | 2739 | 693.004 | 1027 | 0.038518 | 4.1214 | 1324 |  | 2759
3362 | REDBUD 110191960 | 43191101 | REDBUD 1101 | 91960 | FALSE | 11326.1042 | 10487.6883 | 6.5181 | 90 | 7.983e-05 | 2210 | 850.9359 | 913 | 0.038488 | 3.4639 | 1325 | 0.06 | 1880
3879 | WILLITS 11032506 | 42661103 | WILLITS 1103 | 2506 | FALSE | 20286.2385 | 20286.2385 | 12.608 | 89 | 0.00011138 | 1386 | 409.6677 | 1285 | 0.038425 | 3.4198 | 1326 | 0.12 | 1404
2472 | SANTA ROSA A 1104220 | 42151104 | SANTA ROSA A 1104 | 220 | FALSE | 15438.0154 | 15438.0154 | 9.5948 | 105 | 0.00011441 | 1309 | 311.3432 | 1429 | 0.038284 | 4.0198 | 1327 | 9.46 | 408
2655 | TEMPLETON 2110R90 | 183052110 | TEMPLETON 2110 | R90 | FALSE | 56951.1784 | 48580.6781 | 30.1931 | 259 | 6.3209e-05 | 2672 | 705.4586 | 1018 | 0.038279 | 9.9144 | 1328 | 0.16 | 1275
4442 | OCEANO 1104Q06 | 182601104 | OCEANO 1104 | Q06 | FALSE | 20064.3385 | 20064.3385 | 12.4701 | 154 | 5.9491e-05 | 2790 | 680.2301 | 1036 | 0.038111 | 5.8691 | 1329 | 0.24 | 1099
3161 | MARTELL 110368192 | 163011103 | MARTELL 1103 | 68192 | FALSE | 10168.9958 | 4402.6894 | 2.7363 | 72 | 0.00012081 | 1168 | 238.5636 | 1570 | 0.037972 | 2.734 | 1330 | 0.05 | 1932
7038 | MIRABEL 1102334 | 42091102 | MIRABEL 1102 | 334 | FALSE | 14855.8514 | 9584.4637 | 5.9568 | 84 | 0.00013014 | 1009 | 232.8142 | 1581 | 0.037896 | 3.1833 | 1331 | 0.12 | 1407
6568 | GEYSERVILLE 110137454 | 42891101 | GEYSERVILLE 1101 | 37454 | FALSE | 19681.6074 | 10482.9729 | 6.5152 | 114 | 0.00010014 | 1640 | 404.6575 | 1292 | 0.037721 | 4.3002 | 1332 | 0.03 | 2377
9085 | SAN LUIS OBISPO 1107V62 | 182631107 | SAN LUIS OBISPO 1107 | V62 | FALSE | 11154.8311 | 11108.5021 | 6.904 | 50 | 5.5981e-05 | 2890 | 671.7711 | 1042 | 0.037409 | 1.8704 | 1333 | 0.29 | 1023
3181 | SONOMA 110478372 | 42721104 | SONOMA 1104 | 78372 | FALSE | 27765.2096 | 26751.8084 | 16.6264 | 198 | 9.64e-05 | 1722 | 422.9319 | 1270 | 0.037304 | 7.3862 | 1334 | 0.18 | 1212
296 | TASSAJARA 2112D514R | 14662112 | TASSAJARA 2112 | D514R | FALSE | 7698.3807 | 5032.0091 | 3.1274 | 73 | 0.00011281 | 1348 | 304.6429 | 1441 | 0.037278 | 2.7213 | 1335 | 0.15 | 1282
5732 | SWIFT 2107XR526 | 83392107 | SWIFT 2107 | XR526 | FALSE | 8725.9018 | 3365.6589 | 2.0918 | 64 | 8.9522e-05 | 1929 | 366.774 | 1343 | 0.037122 | 2.3758 | 1336 | 0.07 | 1699
4671 | PURISIMA 1101Y42 | 182971101 | PURISIMA 1101 | Y42 | FALSE | 26985.4956 | 5628.4599 | 3.4981 | 127 | 5.2153e-05 | 2990 | 480.936 | 1215 | 0.037118 | 4.714 | 1337 | 0.03 | 2346
7642 | PENRYN 1105168616 | 152561105 | PENRYN 1105 | 168616 | FALSE | 13634.7639 | 5078.9905 | 3.1566 | 102 | 0.00012703 | 1064 | 319.4815 | 1417 | 0.03705 | 3.7791 | 1338 |  | 3144
2287 | OCEANO 1104104102 | 182601104 | OCEANO 1104 | 104102 | FALSE | 5954.6843 | 5329.5584 | 3.3123 | 32 | 7.2705e-05 | 2398 | 458.1953 | 1237 | 0.03704 | 1.1853 | 1339 |  | 2769
9499 | OILFIELDS 1103N46 | 182391103 | OILFIELDS 1103 | N46 | FALSE | 9360.6261 | 9360.6261 | 5.8177 | 29 | 8.7946e-05 | 1983 | 551.9562 | 1142 | 0.036988 | 1.0726 | 1340 | 4.74 | 508
5619 | NARROWS 21052426 | 153132105 | NARROWS 2105 | 2426 | FALSE | 27934.4989 | 13782.7728 | 8.566 | 226 | 0.00017076 | 559 | 240.3744 | 1566 | 0.036874 | 8.3335 | 1341 | 0.09 | 1513
3889 | RINCON 1103474 | 43321103 | RINCON 1103 | 474 | FALSE | 29501.1448 | 29501.1448 | 18.3351 | 174 | 9.7853e-05 | 1695 | 328.9251 | 1399 | 0.036813 | 6.4055 | 1342 | 75.79 | 56
6070 | CRESCENT MILLS 21012230 | 103132101 | CRESCENT MILLS 2101 | 2230 | FALSE | 17863.1589 | 10972.6709 | 6.8196 | 112 | 5.685e-05 | 2866 | 738.5033 | 984 | 0.036587 | 4.0978 | 1343 | 1.14 | 710
7395 | HALF MOON BAY 11018902 | 24101101 | HALF MOON BAY 1101 | 8902 | FALSE | 29281.8886 | 22787.1296 | 14.1623 | 145 | 9.4843e-05 | 1771 | 290.9381 | 1462 | 0.036496 | 5.2919 | 1344 | 0.33 | 986
8155 | PIT NO 5 11011606 | 101321101 | PIT NO 5 1101 | 1606 | FALSE | 8892.9459 | 8892.9459 | 5.527 | 40 | 0.00014678 | 776 | 232.8508 | 1580 | 0.036482 | 1.4593 | 1345 | 0.01 | 2612
6340 | ELECTRA 11011238 | 162161101 | ELECTRA 1101 | 1238 | FALSE | 11344.0767 | 5824.674 | 3.6201 | 81 | 0.00010773 | 1458 | 597.355 | 1103 | 0.036431 | 2.9509 | 1346 | 1.29 | 689
988 | FROGTOWN 1701CB | 163451701 | FROGTOWN 1701 | CB | FALSE | 18045.0473 | 16189.7881 | 10.062 | 76 | 0.00014573 | 792 | 355.2175 | 1365 | 0.036334 | 2.7614 | 1347 | 0.04 | 2159
6703 | POTTER VALLEY P H 110576498 | 42281105 | POTTER VALLEY P H 1105 | 76498 | FALSE | 23942.9529 | 23942.9529 | 14.8806 | 119 | 0.00014996 | 736 | 219.4832 | 1606 | 0.036331 | 4.3234 | 1348 | 0.07 | 1718
10138 | LLAGAS 2107870396 | 83182107 | LLAGAS 2107 | 870396 | FALSE | 4752.0973 | 1326.4884 | 0.82442 | 40 | 7.7997e-05 | 2259 | 529.8735 | 1173 | 0.036327 | 1.4531 | 1349 |  | 3499
7528 | LAYTONVILLE 110189606 | 42681101 | LAYTONVILLE 1101 | 89606 | FALSE | 19260.5468 | 18716.1946 | 11.6322 | 100 | 0.00018082 | 506 | 280.3009 | 1471 | 0.036226 | 3.6226 | 1350 | 2.6 | 595
1489 | CURTIS 1702CB | 163351702 | CURTIS 1702 | CB | FALSE | 36887.0265 | 35506.5152 | 22.0674 | 293 | 0.00013284 | 960 | 388.0347 | 1309 | 0.036175 | 10.5993 | 1351 | 0.18 | 1199
3159 | SALMON CREEK 1101194 | 43161101 | SALMON CREEK 1101 | 194 | FALSE | 13676.557 | 10907.7439 | 6.7792 | 62 | 5.7737e-05 | 2843 | 536.066 | 1162 | 0.03614 | 2.2407 | 1352 | 0.13 | 1363
5649 | MORGAN HILL 2111XR186 | 83242111 | MORGAN HILL 2111 | XR186 | FALSE | 25721.3505 | 4651.2538 | 2.8908 | 191 | 7.0623e-05 | 2453 | 451.6726 | 1246 | 0.036035 | 6.8827 | 1353 | 0.23 | 1109
972 | BRUNSWICK 11062392 | 152481106 | BRUNSWICK 1106 | 2392 | FALSE | 14284.081 | 9811.7074 | 6.098 | 111 | 0.0001898 | 442 | 159.9243 | 1747 | 0.036 | 3.996 | 1354 |  | 2700
4961 | TEMPLETON 2110R94 | 183052110 | TEMPLETON 2110 | R94 | FALSE | 33827.9009 | 22380.6586 | 13.9097 | 179 | 5.5341e-05 | 2903 | 687.195 | 1033 | 0.035946 | 6.4343 | 1355 | 0.08 | 1614
2592 | CAYUCOS 11014701 | 182551101 | CAYUCOS 1101 | 4701 | FALSE | 14095.9599 | 3388.7478 | 2.1061 | 65 | 6.2737e-05 | 2693 | 533.9217 | 1166 | 0.035932 | 2.3356 | 1356 | 0.03 | 2301
160 | MOUNTAIN QUARRIES 21011346 | 152282101 | MOUNTAIN QUARRIES 2101 | 1346 | FALSE | 49591.6622 | 49591.6622 | 30.8214 | 410 | 0.00012199 | 1148 | 241.2851 | 1564 | 0.035841 | 14.6948 | 1357 | 0.17 | 1232
3187 | SAN MIGUEL 1104R58 | 182661104 | SAN MIGUEL 1104 | R58 | TRUE | 19359.8745 | 870.4973 | 0.54102 | 130 | 8.6053e-05 | 2033 | 466.191 | 1227 | 0.035811 | 4.6554 | 1358 | 0.03 | 2357
8179 | LOS OSITOS 21037062 | 182082103 | LOS OSITOS 2103 | 7062 | FALSE | 19664.1429 | 19664.1429 | 12.2213 | 53 | 5.2216e-05 | 2986 | 685.2904 | 1034 | 0.035805 | 1.8977 | 1359 | 0.1 | 1452
7911 | OAKLAND K 110217430 | 12101102 | OAKLAND K 1102 | 17430 | FALSE | 2364.8217 | 2364.8217 | 1.4697 | 15 | 0.00011951 | 1195 | 247.4437 | 1547 | 0.035767 | 0.5365 | 1360 | 32.76 | 224
88 | SILVERADO 2105658898 | 43432105 | SILVERADO 2105 | 658898 | FALSE | 27632.4579 | 27632.4579 | 17.1737 | 151 | 0.00015549 | 689 | 248.309 | 1546 | 0.035763 | 5.4002 | 1361 | 57.88 | 94
2757 | BURNEY 11011358 | 103311101 | BURNEY 1101 | 1358 | FALSE | 15167.5785 | 13566.1241 | 8.4314 | 51 | 5.9055e-05 | 2804 | 689.2289 | 1031 | 0.035574 | 1.8143 | 1362 | 0.06 | 1890
2335 | PLACERVILLE 21067522 | 153082106 | PLACERVILLE 2106 | 7522 | FALSE | 108391.3301 | 108391.3301 | 67.3656 | 745 | 0.00012077 | 1170 | 356.6073 | 1360 | 0.035529 | 26.4689 | 1363 | 0.39 | 959
10054 | GARBERVILLE 110197300 | 192221101 | GARBERVILLE 1101 | 97300 | FALSE | 5161.3802 | 5161.3802 | 3.2078 | 32 | 0.00052613 | 28 | 106.2466 | 1924 | 0.035439 | 1.1341 | 1364 | 0 | 2624
2680 | SAN RAMON 2107MR284 | 14232107 | SAN RAMON 2107 | MR284 | FALSE | 24162.974 | 23633.8875 | 14.6886 | 134 | 7.4599e-05 | 2342 | 581.0664 | 1123 | 0.035373 | 4.7399 | 1365 | 0.73 | 795
6323 | FORT ROSS 112170288 | 42851121 | FORT ROSS 1121 | 70288 | FALSE | 18879.7984 | 18879.7984 | 11.7339 | 94 | 0.00019388 | 426 | 228.6007 | 1590 | 0.035369 | 3.3247 | 1366 | 36.18 | 207
4070 | CLAYTON 2213CB | 12022213 | CLAYTON 2213 | CB | FALSE | 9981.732 | 6230.9216 | 3.8725 | 51 | 2.7369e-05 | 3466 | 650.8554 | 1065 | 0.03535 | 1.8029 | 1367 |  | 2870
5947 | GARCIA 0401666 | 43040401 | GARCIA 0401 | 666 | FALSE | 3872.5577 | 3872.5577 | 2.4068 | 12 | 9.2943e-05 | 1825 | 378.2419 | 1323 | 0.035311 | 0.42373 | 1368 | 4.95 | 500
8699 | UKIAH 1113548420 | 42771113 | UKIAH 1113 | 548420 | FALSE | 8380.7958 | 8369.7684 | 5.2018 | 54 | 8.6035e-05 | 2034 | 589.6218 | 1114 | 0.035261 | 1.9041 | 1369 |  | 3251
7081 | NOVATO 110455398 | 42211104 | NOVATO 1104 | 55398 | FALSE | 18355.8501 | 5879.4418 | 3.6541 | 82 | 9.9295e-05 | 1661 | 371.6607 | 1336 | 0.035221 | 2.8881 | 1370 | 0.05 | 2019
2938 | PETALUMA C 110948000 | 42631109 | PETALUMA C 1109 | 48000 | FALSE | 21345.6496 | 15284.0145 | 9.4991 | 115 | 8.6887e-05 | 2015 | 388.2741 | 1308 | 0.035167 | 4.0442 | 1371 | 0.07 | 1767
9847 | PENRYN 1105CB | 152561105 | PENRYN 1105 | CB | TRUE | 1663.8056 | 978.5043 | 0.60814 | 7 | 0.00029336 | 136 | 117.5975 | 1884 | 0.035133 | 0.24593 | 1372 | 0.22 | 1130
1921 | WYANDOTTE 110641650 | 102911106 | WYANDOTTE 1106 | 41650 | FALSE | 26091.6846 | 1862.3816 | 1.1575 | 152 | 9.0143e-05 | 1906 | 368.6652 | 1340 | 0.035126 | 5.3392 | 1373 | 1.15 | 706
7481 | OTTER 11012052 | 182941101 | OTTER 1101 | 2052 | FALSE | 7781.6967 | 7781.6967 | 4.8364 | 53 | 0.00010975 | 1416 | 342.2139 | 1385 | 0.034981 | 1.854 | 1374 | 16.17 | 340
3295 | REDBUD 1102510 | 43191102 | REDBUD 1102 | 510 | FALSE | 13083.2788 | 6767.6989 | 4.2062 | 101 | 7.5461e-05 | 2323 | 619.5024 | 1082 | 0.03495 | 3.5299 | 1375 | 0.06 | 1875
4887 | WOODSIDE 11018972 | 24251101 | WOODSIDE 1101 | 8972 | FALSE | 10000.1577 | 10000.1577 | 6.2151 | 60 | 0.00015146 | 726 | 262.3952 | 1516 | 0.034933 | 2.096 | 1376 | 24.19 | 280
9433 | JAMESON 11028842 | 63801102 | JAMESON 1102 | 8842 | TRUE | 4786.8365 | 241.1115 | 0.14985 | 42 | 6.9889e-05 | 2476 | 340.0317 | 1387 | 0.03478 | 1.4608 | 1377 | 1.42 | 678
5225 | SHADY GLEN 110248894 | 152431102 | SHADY GLEN 1102 | 48894 | FALSE | 16156.7591 | 14293.1803 | 8.8833 | 119 | 0.00018242 | 493 | 147.0551 | 1786 | 0.034658 | 4.1244 | 1378 | 4.42 | 518
4594 | WEIMAR 11012058 | 152491101 | WEIMAR 1101 | 2058 | FALSE | 34315.2065 | 34315.2065 | 21.327 | 256 | 0.00016588 | 583 | 212.3054 | 1613 | 0.034582 | 8.853 | 1379 | 0.1 | 1472
10315 | CLAYTON 2212523764 | 12022212 | CLAYTON 2212 | 523764 | TRUE | 581.2133 | 177.5745 | 0.11036 | 5 | 5.3526e-05 | 2949 | 454.5614 | 1241 | 0.034478 | 0.17239 | 1380 |  | 3531
4872 | SUNOL 1101MR196 | 14241101 | SUNOL 1101 | MR196 | FALSE | 21187.4678 | 6333.1478 | 3.9361 | 96 | 5.2612e-05 | 2979 | 626.9753 | 1078 | 0.034417 | 3.304 | 1381 | 0.62 | 842
1388 | MIWUK 170193062 | 163661701 | MIWUK 1701 | 93062 | FALSE | 13326.2559 | 13326.2559 | 8.2823 | 84 | 5.3764e-05 | 2946 | 519.6534 | 1183 | 0.034301 | 2.8813 | 1382 | 47.16 | 137
10333 | SAN ARDO 1101650772 | 182191101 | SAN ARDO 1101 | 650772 | FALSE | 4368.3364 | 1261.3702 | 0.78395 | 10 | 8.4256e-05 | 2083 | 361.8664 | 1350 | 0.03426 | 0.3426 | 1383 |  | 3534
132 | APPLE HILL 1103CB | 153661103 | APPLE HILL 1103 | CB | FALSE | 36721.9242 | 31128.549 | 19.3465 | 268 | 0.00025192 | 213 | 162.0895 | 1742 | 0.034245 | 9.1777 | 1384 | 0.18 | 1200
7451 | LOW GAP 1101CB | 192411101 | LOW GAP 1101 | CB | FALSE | 3490.2509 | 3490.2509 | 2.1692 | 23 | 0.00020947 | 361 | 222.197 | 1600 | 0.034029 | 0.78267 | 1385 | 9.67 | 405
10038 | JESSUP 110194468 | 103441101 | JESSUP 1101 | 94468 | FALSE | 2757.0604 | 2757.0604 | 1.7135 | 21 | 6.6616e-05 | 2567 | 514.9233 | 1187 | 0.033993 | 0.71385 | 1386 |  | 3480
3608 | PIT NO 1 11011552 | 103721101 | PIT NO 1 1101 | 1552 | FALSE | 42573.1939 | 23841.5992 | 14.8177 | 221 | 3.5304e-05 | 3346 | 839.4452 | 917 | 0.033912 | 7.4946 | 1387 | 0.02 | 2427
5359 | SAN LUIS OBISPO 1104CB | 182631104 | SAN LUIS OBISPO 1104 | CB | TRUE | 10585.951 | 124.2488 | 0.077221 | 65 | 0.00011177 | 1373 | 315.2576 | 1425 | 0.033863 | 2.2011 | 1388 | 0.02 | 2451
9613 | REEDLEY 1112477952 | 252341112 | REEDLEY 1112 | 477952 | TRUE | 2593.1423 | 282.8465 | 0.17579 | 14 | 3.3616e-05 | 3374 | 2064.1113 | 439 | 0.033843 | 0.47381 | 1389 |  | 3390
6901 | JESSUP 11019752 | 103441101 | JESSUP 1101 | 9752 | FALSE | 6185.1828 | 6137.4536 | 3.8145 | 41 | 8.5187e-05 | 2053 | 359.3768 | 1357 | 0.033837 | 1.3873 | 1390 | 0.08 | 1592
8898 | RACETRACK 17036014 | 163761703 | RACETRACK 1703 | 6014 | FALSE | 11167.2532 | 11167.2532 | 6.9405 | 73 | 0.00012645 | 1075 | 322.1745 | 1410 | 0.033829 | 2.4695 | 1391 | 0.11 | 1416
7674 | LLAGAS 21011451 | 83182101 | LLAGAS 2101 | 1451 | FALSE | 14799.0551 | 9963.2757 | 6.1922 | 61 | 7.7841e-05 | 2264 | 590.7109 | 1112 | 0.03381 | 2.0624 | 1392 | 0.07 | 1693
5880 | POINT MORETTI 11015076 | 82931101 | POINT MORETTI 1101 | 5076 | FALSE | 14477.3637 | 12059.1468 | 7.4948 | 67 | 0.00010771 | 1459 | 265.797 | 1508 | 0.033758 | 2.2618 | 1393 | 0.04 | 2127
8948 | CLARKSVILLE 2109102734 | 153612109 | CLARKSVILLE 2109 | 102734 | TRUE | 954.1374 | 954.1374 | 0.593 | 7 | 8.9773e-05 | 1919 | 197.0875 | 1650 | 0.033754 | 0.23628 | 1394 |  | 3280
10958 | CURTIS 170511790 | 163351705 | CURTIS 1705 | 11790 | TRUE | 22.8988 | 22.8988 | 0.014232 | 1 | 0.00070892 | 7 | 47.5828 | 2227 | 0.033732 | 0.033732 | 1395 | 0.2 | 1164
10247 | MILPITAS 1108342498 | 82831108 | MILPITAS 1108 | 342498 | TRUE | 1151.7336 | 49.0072 | 0.030458 | 9 | 7.9908e-05 | 2207 | 500.2762 | 1198 | 0.033722 | 0.3035 | 1396 |  | 3521
5434 | MADISON 1105495270 | 63171105 | MADISON 1105 | 495270 | TRUE | 13307.7021 | 863.3194 | 0.53656 | 50 | 9.0841e-05 | 1888 | 589.9667 | 1113 | 0.033688 | 1.6844 | 1397 |  | 2953
5420 | PETALUMA C 1108600 | 42631108 | PETALUMA C 1108 | 600 | FALSE | 11716.5391 | 5966.5276 | 3.7082 | 107 | 8.5491e-05 | 2040 | 380.66 | 1319 | 0.033514 | 3.586 | 1398 | 2.36 | 611
5203 | HALSEY 11012414 | 152241101 | HALSEY 1101 | 2414 | FALSE | 23793.415 | 23793.415 | 14.7877 | 168 | 0.00014567 | 794 | 312.3629 | 1427 | 0.033489 | 5.6261 | 1399 | 0.1 | 1503
322 | PIKE CITY 11011730 | 152201101 | PIKE CITY 1101 | 1730 | FALSE | 13645.4759 | 13645.4759 | 8.4807 | 73 | 0.00014065 | 860 | 278.461 | 1475 | 0.033438 | 2.441 | 1400 | 45.96 | 146
5994 | RED BLUFF 11011334 | 103541101 | RED BLUFF 1101 | 1334 | FALSE | 25612.9912 | 2886.1165 | 1.7937 | 155 | 6.0867e-05 | 2753 | 682.7098 | 1035 | 0.033359 | 5.1706 | 1401 | 1.21 | 700
3212 | HALF MOON BAY 1103H82 | 24101103 | HALF MOON BAY 1103 | H82 | FALSE | 58651.4755 | 52489.3402 | 32.6223 | 262 | 9.3414e-05 | 1811 | 388.9088 | 1307 | 0.033242 | 8.7095 | 1402 | 0.77 | 782
1462 | GIRVAN 11029012 | 103401102 | GIRVAN 1102 | 9012 | FALSE | 25166.2142 | 25166.2142 | 15.6409 | 176 | 0.00013267 | 966 | 372.3651 | 1335 | 0.033219 | 5.8466 | 1403 | 0.42 | 934
10706 | GONZALES 1104807000 | 182131104 | GONZALES 1104 | 807000 | FALSE | 1709.8584 | 1354.2941 | 0.8417 | 7 | 3.235e-05 | 3394 | 880.4035 | 891 | 0.033203 | 0.23242 | 1404 |  | 3594
5652 | CORRAL 110214028 | 162991102 | CORRAL 1102 | 14028 | FALSE | 12751.8037 | 6133.5417 | 3.812 | 103 | 0.00010822 | 1447 | 214.1406 | 1611 | 0.033074 | 3.4066 | 1405 | 0.04 | 2224
7408 | KANAKA 11011044 | 103221101 | KANAKA 1101 | 1044 | FALSE | 9889.843 | 9889.843 | 6.1466 | 17 | 0.00010748 | 1465 | 324.5037 | 1407 | 0.033036 | 0.56161 | 1406 | 18.93 | 316
2114 | WYANDOTTE 11091040 | 102911109 | WYANDOTTE 1109 | 1040 | FALSE | 9753.1063 | 1682.9824 | 1.046 | 62 | 0.00011564 | 1281 | 448.3969 | 1250 | 0.032999 | 2.0459 | 1407 | 0.73 | 796
9307 | LINCOLN 11012310 | 153701101 | LINCOLN 1101 | 2310 | FALSE | 4180.455 | 1304.6994 | 0.81088 | 34 | 0.00013671 | 911 | 509.3332 | 1192 | 0.032911 | 1.119 | 1408 | 0.05 | 1962
4870 | BEAR VALLEY 2101CB | 252192101 | BEAR VALLEY 2101 | CB | FALSE | 30214.013 | 30214.013 | 18.7781 | 154 | 0.00013214 | 980 | 326.6135 | 1403 | 0.03289 | 5.065 | 1409 | 0.04 | 2085
3833 | APPLE HILL 110412832 | 153661104 | APPLE HILL 1104 | 12832 | FALSE | 24421.2649 | 23234.3604 | 14.4402 | 166 | 0.00017093 | 557 | 211.8635 | 1615 | 0.032787 | 5.4427 | 1410 | 28.99 | 245
10090 | TIVY VALLEY 1107599142 | 252941107 | TIVY VALLEY 1107 | 599142 | TRUE | 3668.6338 | 573.3105 | 0.35631 | 19 | 2.2881e-05 | 3512 | 2022.5531 | 452 | 0.03274 | 0.62205 | 1411 |  | 3488
2297 | STANISLAUS 17011812 | 162821701 | STANISLAUS 1701 | 1812 | FALSE | 30912.6745 | 30912.6745 | 19.2124 | 234 | 0.0001396 | 878 | 157.2117 | 1758 | 0.032657 | 7.6418 | 1412 | 0.91 | 748
8485 | HOLLISTER 2102113634 | 182492102 | HOLLISTER 2102 | 113634 | FALSE | 13932.988 | 2941.0752 | 1.8279 | 76 | 7.4759e-05 | 2338 | 364.1214 | 1346 | 0.032654 | 2.4817 | 1413 |  | 3229
7193 | ELECTRA 1102CB | 162161102 | ELECTRA 1102 | CB | FALSE | 4270.3268 | 4270.3268 | 2.654 | 7 | 0.000239 | 249 | 194.5881 | 1655 | 0.032515 | 0.22761 | 1414 | 0.03 | 2354
5731 | PLACERVILLE 21062224 | 153082106 | PLACERVILLE 2106 | 2224 | FALSE | 16910.6519 | 16910.6519 | 10.51 | 123 | 0.00022231 | 310 | 204.3067 | 1631 | 0.032512 | 3.999 | 1415 | 31.55 | 229
4312 | MENDOCINO 110137462 | 42951101 | MENDOCINO 1101 | 37462 | FALSE | 7845.6326 | 3795.803 | 2.3591 | 63 | 0.00014083 | 857 | 230.0252 | 1586 | 0.032457 | 2.0448 | 1416 | 0.04 | 2166
8959 | OLETA 1101894006 | 163541101 | OLETA 1101 | 894006 | TRUE | 1042.8451 | 627.9545 | 0.39028 | 8 | 7.1494e-05 | 2432 | 670.4008 | 1043 | 0.03239 | 0.25912 | 1417 |  | 3282
4513 | SAN LUIS OBISPO 1104V14 | 182631104 | SAN LUIS OBISPO 1104 | V14 | FALSE | 13117.1277 | 13103.4117 | 8.1438 | 69 | 5.3161e-05 | 2961 | 462.6018 | 1233 | 0.03238 | 2.2342 | 1418 | 0.07 | 1714
4357 | APPLE HILL 11038412 | 153661103 | APPLE HILL 1103 | 8412 | FALSE | 31508.6751 | 31508.6751 | 19.5828 | 201 | 0.00012406 | 1118 | 308.2082 | 1435 | 0.032352 | 6.5027 | 1419 | 0.24 | 1093
2717 | JOLON 11027002 | 182981102 | JOLON 1102 | 7002 | FALSE | 29669.7133 | 13447.6997 | 8.3578 | 117 | 6.5838e-05 | 2591 | 548.8506 | 1147 | 0.032323 | 3.7818 | 1420 | 0.03 | 2407
5768 | BIG BASIN 110210254 | 82841102 | BIG BASIN 1102 | 10254 | FALSE | 3449.8351 | 3449.8351 | 2.1441 | 11 | 0.00025218 | 212 | 138.3979 | 1814 | 0.03232 | 0.35552 | 1421 | 0.29 | 1030
5734 | APPLE HILL 1104CB | 153661104 | APPLE HILL 1104 | CB | FALSE | 6578.3972 | 6578.3972 | 4.0885 | 51 | 0.00035059 | 89 | 89.0767 | 2007 | 0.032289 | 1.6467 | 1422 | 4 | 530
7601 | JARVIS 1111907698 | 13501111 | JARVIS 1111 | 907698 | FALSE | 3034.3117 | 2466.4182 | 1.5329 | 14 | 0.00012445 | 1111 | 261.4537 | 1520 | 0.03225 | 0.4515 | 1423 |  | 3140
7801 | HALF MOON BAY 11012500 | 24101101 | HALF MOON BAY 1101 | 2500 | FALSE | 11167.0911 | 10490.7768 | 6.5201 | 74 | 0.00015128 | 727 | 218.7989 | 1608 | 0.032243 | 2.3859 | 1424 | 57.37 | 96
4135 | BRUNSWICK 11041020 | 152481104 | BRUNSWICK 1104 | 1020 | FALSE | 46299.321 | 46299.321 | 28.7752 | 311 | 9.6344e-05 | 1725 | 368.887 | 1339 | 0.032187 | 10.0103 | 1425 | 69 | 71
7772 | FRUITLAND 11422006 | 192311142 | FRUITLAND 1142 | 2006 | FALSE | 14941.7424 | 13398.0902 | 8.327 | 75 | 0.00034661 | 94 | 97.9891 | 1968 | 0.03216 | 2.412 | 1426 | 0.09 | 1508
10311 | MADISON 2101760730 | 63172101 | MADISON 2101 | 760730 | TRUE | 4317.2275 | 964.21 | 0.59926 | 17 | 7.566e-05 | 2318 | 407.7093 | 1289 | 0.032096 | 0.54562 | 1427 |  | 3530
1525 | CHALLENGE 11025462 | 103201102 | CHALLENGE 1102 | 5462 | FALSE | 37447.0905 | 37447.0905 | 23.2735 | 248 | 0.00016384 | 602 | 227.1186 | 1593 | 0.032082 | 7.9564 | 1428 | 37.76 | 199
7510 | FRUITLAND 114263170 | 192311142 | FRUITLAND 1142 | 63170 | FALSE | 21717.2784 | 20031.3406 | 12.4496 | 86 | 0.00032558 | 106 | 126.7281 | 1853 | 0.031951 | 2.7478 | 1429 | 0.11 | 1410
8635 | MOLINO 11026917 | 42571102 | MOLINO 1102 | 6917 | FALSE | 11229.1017 | 11229.1017 | 6.9789 | 58 | 0.00011705 | 1246 | 334.9674 | 1393 | 0.031941 | 1.8526 | 1430 | 28.69 | 248
5301 | REEDLEY 1104887932 | 252341104 | REEDLEY 1104 | 887932 | FALSE | 7830.582 | 2732.0868 | 1.698 | 34 | 3.8049e-05 | 3299 | 1172.2774 | 745 | 0.031896 | 1.0845 | 1431 |  | 2945
8600 | CALPELLA 1101619542 | 43411101 | CALPELLA 1101 | 619542 | FALSE | 2424.259 | 2408.2569 | 1.4967 | 21 | 0.00013244 | 972 | 252.7945 | 1536 | 0.031874 | 0.66935 | 1432 |  | 3241
145 | MOUNTAIN QUARRIES 21011130 | 152282101 | MOUNTAIN QUARRIES 2101 | 1130 | FALSE | 32234.9294 | 32234.9294 | 20.0341 | 231 | 8.1217e-05 | 2177 | 401.3828 | 1295 | 0.031834 | 7.3538 | 1433 | 0.19 | 1198
8867 | FORESTHILL 110137238 | 152181101 | FORESTHILL 1101 | 37238 | FALSE | 18384.2813 | 18384.2813 | 11.4259 | 79 | 9.076e-05 | 1890 | 274.1817 | 1485 | 0.031693 | 2.5038 | 1434 | 39.57 | 188
10121 | COARSEGOLD 210210610 | 254432102 | COARSEGOLD 2102 | 10610 | FALSE | 2196.7777 | 2196.7777 | 1.3653 | 22 | 7.4106e-05 | 2354 | 439.5957 | 1256 | 0.031595 | 0.6951 | 1435 | 0.3 | 1012
8481 | PERRY 110185870 | 183071101 | PERRY 1101 | 85870 | FALSE | 27055.9571 | 18409.1169 | 11.4413 | 109 | 5.897e-05 | 2807 | 581.2408 | 1122 | 0.031502 | 3.4337 | 1436 | 0.05 | 1923
3885 | BELLEVUE 2103478 | 43182103 | BELLEVUE 2103 | 478 | FALSE | 32233.0286 | 13396.6859 | 8.3261 | 213 | 9.7957e-05 | 1693 | 387.6512 | 1310 | 0.031296 | 6.6661 | 1437 | 6.33 | 468
1942 | UKIAH 1113CB | 42771113 | UKIAH 1113 | CB | TRUE | 9680.979 | 75.4379 | 0.046885 | 69 | 8.4474e-05 | 2078 | 195.8633 | 1653 | 0.031266 | 2.1574 | 1438 | 3.69 | 536
10742 | GEYSERVILLE 1101463260 | 42891101 | GEYSERVILLE 1101 | 463260 | TRUE | 886.169 | 873.7132 | 0.54302 | 6 | 9.5911e-05 | 1730 | 333.1332 | 1394 | 0.031168 | 0.18701 | 1439 |  | 3601
8417 | CURTIS 1703CB | 163351703 | CURTIS 1703 | CB | FALSE | 17669.2412 | 14555.9213 | 9.0466 | 119 | 0.00013143 | 990 | 316.505 | 1422 | 0.031137 | 3.7053 | 1440 | 0.06 | 1894
1279 | ORO FINO 11022556 | 103031102 | ORO FINO 1102 | 2556 | FALSE | 10719.4797 | 10719.4797 | 6.6622 | 41 | 0.00022017 | 320 | 170.5273 | 1713 | 0.031032 | 1.2723 | 1441 | 40.37 | 184
1200 | OCEANO 1106CB | 182601106 | OCEANO 1106 | CB | FALSE | 7207.9497 | 1811.9234 | 1.1261 | 57 | 3.6174e-05 | 3330 | 275.7036 | 1484 | 0.03103 | 1.7687 | 1442 | 0.02 | 2494
766 | SISQUOC 1103M98 | 182811103 | SISQUOC 1103 | M98 | FALSE | 15843.0204 | 12614.6664 | 7.8401 | 56 | 2.6579e-05 | 3477 | 870.0926 | 898 | 0.030988 | 1.7353 | 1443 | 0.06 | 1829
8592 | STELLING 11109265 | 83481110 | STELLING 1110 | 9265 | FALSE | 8915.672 | 8915.672 | 5.5411 | 45 | 9.8e-05 | 1691 | 342.4629 | 1384 | 0.03098 | 1.3941 | 1444 | 0.08 | 1605
5933 | MIRABEL 1102524356 | 42091102 | MIRABEL 1102 | 524356 | FALSE | 4107.6805 | 2088.1166 | 1.2978 | 29 | 0.00010421 | 1547 | 511.0846 | 1190 | 0.030872 | 0.89528 | 1445 |  | 2991
802 | ALLEGHANY 1101806 | 152101101 | ALLEGHANY 1101 | 806 | FALSE | 18143.3915 | 18143.3915 | 11.2762 | 65 | 0.00012168 | 1154 | 338.7274 | 1390 | 0.030867 | 2.0063 | 1446 | 48.53 | 127
1506 | GARBERVILLE 11011750 | 192221101 | GARBERVILLE 1101 | 1750 | FALSE | 13589.0424 | 13584.4704 | 8.4428 | 62 | 0.00032404 | 108 | 98.8868 | 1959 | 0.030822 | 1.911 | 1447 | 0.13 | 1338
4004 | COARSEGOLD 21025380 | 254432102 | COARSEGOLD 2102 | 5380 | FALSE | 22971.0374 | 22971.0374 | 14.2766 | 143 | 7.8304e-05 | 2250 | 414.5903 | 1278 | 0.030806 | 4.4053 | 1448 | 0.46 | 911
1308 | RINCON 1101578 | 43321101 | RINCON 1101 | 578 | FALSE | 29556.6676 | 27517.4977 | 17.1022 | 170 | 8.7604e-05 | 1997 | 393.466 | 1303 | 0.030756 | 5.2285 | 1449 | 37.08 | 203
10309 | BOLINAS 1101806 | 42261101 | BOLINAS 1101 | 806 | FALSE | 4898.4533 | 4898.4533 | 3.0444 | 17 | 0.00027974 | 154 | 135.7877 | 1828 | 0.030667 | 0.52134 | 1450 | 0.55 | 868
6983 | BASALT 1106657038 | 42461106 | BASALT 1106 | 657038 | FALSE | 16275.5331 | 4182.6167 | 2.5995 | 72 | 4.9064e-05 | 3062 | 415.5682 | 1276 | 0.030657 | 2.2073 | 1451 |  | 3078
3194 | DIAMOND SPRINGS 1103467046 | 152261103 | DIAMOND SPRINGS 1103 | 467046 | FALSE | 34550.7467 | 24654.328 | 15.3228 | 266 | 0.00018345 | 482 | 166.8005 | 1729 | 0.030581 | 8.1346 | 1452 |  | 2816
4703 | WISE 1101CB | 152271101 | WISE 1101 | CB | FALSE | 14435.5526 | 7662.7202 | 4.7624 | 112 | 0.00015887 | 652 | 243.3221 | 1558 | 0.030561 | 3.4229 | 1453 | 0.05 | 2032
6843 | DUNBAR 11033127 | 43071103 | DUNBAR 1103 | 3127 | FALSE | 15418.4131 | 15054.5807 | 9.3565 | 78 | 0.00010691 | 1479 | 266.083 | 1507 | 0.030422 | 2.3729 | 1454 | 0.62 | 840
3373 | VOLTA 11021646 | 102541102 | VOLTA 1102 | 1646 | FALSE | 38843.3191 | 38535.0265 | 23.9497 | 215 | 6.2043e-05 | 2718 | 560.4541 | 1133 | 0.030417 | 6.5396 | 1455 | 13.62 | 364
9167 | WILDWOOD 1101CB | 103611101 | WILDWOOD 1101 | CB | TRUE | 200.8618 | 200.8618 | 0.12484 | 2 | 9.0416e-05 | 1899 | 309.1042 | 1433 | 0.030413 | 0.060827 | 1456 | 0.72 | 797
1377 | FROGTOWN 170211212 | 163451702 | FROGTOWN 1702 | 11212 | FALSE | 35943.9954 | 35943.9954 | 22.3393 | 155 | 8.85e-05 | 1974 | 349.3135 | 1372 | 0.030264 | 4.691 | 1457 | 0.06 | 1822
2196 | ATASCADERO 1101A02 | 182541101 | ATASCADERO 1101 | A02 | FALSE | 41006.5742 | 41006.5742 | 25.4858 | 253 | 5.864e-05 | 2818 | 542.8818 | 1156 | 0.030233 | 7.649 | 1458 | 2.41 | 606
6596 | STELLING 111060090 | 83481110 | STELLING 1110 | 60090 | FALSE | 10545.4488 | 10545.4488 | 6.554 | 62 | 0.00016362 | 604 | 206.0102 | 1623 | 0.030171 | 1.8706 | 1459 | 0.06 | 1906
6029 | PANORAMA 1101713592 | 103461101 | PANORAMA 1101 | 713592 | FALSE | 16948.2792 | 16715.2405 | 10.3886 | 152 | 6.2494e-05 | 2704 | 490.9201 | 1208 | 0.030005 | 4.5608 | 1460 |  | 2997
3261 | CRESCENT MILLS 2101CB | 103132101 | CRESCENT MILLS 2101 | CB | FALSE | 9227.3447 | 4545.9264 | 2.8253 | 60 | 7.4812e-05 | 2336 | 409.6387 | 1286 | 0.029932 | 1.7959 | 1461 | 5.21 | 494
4399 | PLACERVILLE 210619552 | 153082106 | PLACERVILLE 2106 | 19552 | FALSE | 34339.9089 | 34339.9089 | 21.3424 | 238 | 0.0001768 | 520 | 361.0634 | 1351 | 0.029928 | 7.123 | 1462 | 0.45 | 915
10240 | LLAGAS 2105534019 | 83182105 | LLAGAS 2105 | 534019 | FALSE | 1193.5001 | 1147.9573 | 0.71346 | 5 | 0.0001111 | 1391 | 269.5494 | 1499 | 0.029893 | 0.14947 | 1463 |  | 3519
5361 | HOOPA 11013174 | 192401101 | HOOPA 1101 | 3174 | FALSE | 35498.7494 | 29750.1978 | 18.4899 | 162 | 0.00035838 | 83 | 115.2454 | 1894 | 0.029875 | 4.8397 | 1464 | 0.13 | 1336
5027 | PEORIA 17048040 | 163781704 | PEORIA 1704 | 8040 | FALSE | 41434.2849 | 11785.9847 | 7.325 | 145 | 5.9131e-05 | 2803 | 495.056 | 1206 | 0.02987 | 4.3312 | 1465 | 0.01 | 2600
9000 | CASTRO VALLEY 11088971 | 14091108 | CASTRO VALLEY 1108 | 8971 | FALSE | 12716.2407 | 12716.2407 | 7.9032 | 72 | 0.00010597 | 1496 | 268.1837 | 1504 | 0.029749 | 2.1419 | 1466 |  | 3293
3972 | CORRAL 1103936674 | 162991103 | CORRAL 1103 | 936674 | FALSE | 6354.8382 | 1063.5848 | 0.66102 | 56 | 8.2565e-05 | 2141 | 408.407 | 1288 | 0.029729 | 1.6648 | 1467 |  | 2866
5038 | MOLINO 110241392 | 42571102 | MOLINO 1102 | 41392 | FALSE | 23588.435 | 7062.7077 | 4.3895 | 171 | 0.00011368 | 1327 | 289.7407 | 1465 | 0.029696 | 5.078 | 1468 | 3.21 | 554
8758 | PUTAH CREEK 11033783 | 63681103 | PUTAH CREEK 1103 | 3783 | TRUE | 16200.7401 | 142.5109 | 0.088571 | 96 | 9.2314e-05 | 1834 | 351.5102 | 1370 | 0.029685 | 2.8498 | 1469 |  | 3259
10009 | OREGON TRAIL 110346860 | 103521103 | OREGON TRAIL 1103 | 46860 | FALSE | 5362.8484 | 1149.598 | 0.71448 | 15 | 0.0001367 | 912 | 145.8531 | 1790 | 0.029648 | 0.44471 | 1470 | 0.03 | 2247
944 | CURTIS 17036064 | 163351703 | CURTIS 1703 | 6064 | FALSE | 31643.7207 | 30550.9366 | 18.9875 | 199 | 7.5696e-05 | 2315 | 471.6661 | 1222 | 0.029564 | 5.8832 | 1471 | 0.2 | 1167
5754 | SANTA YNEZ 1102Y18 | 182721102 | SANTA YNEZ 1102 | Y18 | FALSE | 12113.6185 | 7856.8971 | 4.8831 | 60 | 4.1779e-05 | 3229 | 658.0763 | 1056 | 0.029555 | 1.7733 | 1472 | 0.08 | 1647
1748 | CLAY 110113450 | 163341101 | CLAY 1101 | 13450 | FALSE | 7994.7686 | 1509.284 | 0.93803 | 42 | 7.6415e-05 | 2295 | 360.8067 | 1352 | 0.029532 | 1.2403 | 1473 |  | 2741
2073 | WILLOW CREEK 11032936 | 192171103 | WILLOW CREEK 1103 | 2936 | FALSE | 53378.6829 | 53378.6829 | 33.1751 | 249 | 0.00014373 | 817 | 191.382 | 1659 | 0.029513 | 7.3486 | 1474 | 0.15 | 1299
3589 | MIRABEL 1101688780 | 42091101 | MIRABEL 1101 | 688780 | TRUE | 2079.7156 | 922.8958 | 0.57358 | 14 | 0.00019275 | 430 | 228.6665 | 1589 | 0.029456 | 0.41239 | 1475 |  | 2839
4182 | GARBERVILLE 11021510 | 192221102 | GARBERVILLE 1102 | 1510 | FALSE | 21171.8285 | 21171.8285 | 13.1584 | 107 | 0.00046286 | 44 | 80.26 | 2047 | 0.029417 | 3.1476 | 1476 | 0.13 | 1358
3154 | CALISTOGA 1102634 | 42711102 | CALISTOGA 1102 | 634 | FALSE | 27022.9414 | 18046.5459 | 11.216 | 178 | 0.00012722 | 1060 | 223.109 | 1599 | 0.029373 | 5.2284 | 1477 | 0.7 | 808
133 | GEYSERVILLE 1102522 | 42891102 | GEYSERVILLE 1102 | 522 | FALSE | 17218.2435 | 12875.7792 | 8.0023 | 109 | 8.4103e-05 | 2091 | 350.0759 | 1371 | 0.029361 | 3.2003 | 1478 | 0.06 | 1861
10360 | OLEMA 110175686 | 42291101 | OLEMA 1101 | 75686 | FALSE | 8282.1233 | 7450.4021 | 4.6305 | 31 | 0.00011699 | 1250 | 264.1333 | 1511 | 0.029281 | 0.90772 | 1479 | 0.04 | 2067
9801 | KANAKA 1101CB | 103221101 | KANAKA 1101 | CB | FALSE | 7605.9803 | 7605.9803 | 4.7271 | 37 | 0.00011114 | 1390 | 255.7947 | 1533 | 0.029281 | 1.0834 | 1480 | 0.23 | 1113
4062 | WHITMORE 1101CB | 103601101 | WHITMORE 1101 | CB | FALSE | 9497.7631 | 9497.7631 | 5.9029 | 69 | 0.00021208 | 351 | 141.7322 | 1806 | 0.029248 | 2.0181 | 1481 | 0.04 | 2126
1547 | WILLITS 110391810 | 42661103 | WILLITS 1103 | 91810 | FALSE | 47379.4324 | 47379.4324 | 29.4465 | 296 | 0.00010548 | 1507 | 312.0704 | 1428 | 0.029203 | 8.6442 | 1482 | 44.17 | 160
8861 | GEYSERVILLE 1102331444 | 42891102 | GEYSERVILLE 1102 | 331444 | FALSE | 7051.4008 | 3579.9474 | 2.225 | 44 | 0.00010727 | 1466 | 260.3745 | 1523 | 0.029048 | 1.2781 | 1483 |  | 3273
3080 | PIKE CITY 1101CB | 152201101 | PIKE CITY 1101 | CB | FALSE | 31622.6384 | 31622.6384 | 19.6536 | 162 | 0.00011093 | 1392 | 299.4116 | 1448 | 0.029034 | 4.7034 | 1484 | 78.02 | 52
9245 | FRUITLAND 1142899734 | 192311142 | FRUITLAND 1142 | 899734 | FALSE | 5471.5337 | 5471.5337 | 3.4006 | 36 | 0.00048435 | 35 | 103.6873 | 1931 | 0.028754 | 1.0351 | 1485 |  | 3329
2842 | SAN LUIS OBISPO 1101CB | 182631101 | SAN LUIS OBISPO 1101 | CB | FALSE | 10872.4032 | 5779.9667 | 3.5923 | 75 | 4.9567e-05 | 3048 | 502.0965 | 1196 | 0.028742 | 2.1556 | 1486 | 0.7 | 805
8606 | PUEBLO 1105684564 | 43291105 | PUEBLO 1105 | 684564 | TRUE | 4176.2924 | 443.3906 | 0.27557 | 28 | 6.665e-05 | 2566 | 311.0083 | 1430 | 0.02858 | 0.80024 | 1487 |  | 3243
3749 | VINEYARD 2107978364 | 14502107 | VINEYARD 2107 | 978364 | FALSE | 4026.4295 | 1557.6573 | 0.96809 | 36 | 4.8923e-05 | 3067 | 319.1206 | 1419 | 0.028543 | 1.0276 | 1488 |  | 2850
1264 | TEMPLETON 2113CB | 183052113 | TEMPLETON 2113 | CB | FALSE | 41366.5121 | 1446.4903 | 0.899 | 288 | 7.2635e-05 | 2400 | 424.917 | 1268 | 0.028499 | 8.2077 | 1489 | 0.17 | 1224
6493 | POINT ARENA 11013702 | 43381101 | POINT ARENA 1101 | 3702 | FALSE | 7962.9538 | 7864.1375 | 4.8876 | 35 | 5.5767e-05 | 2896 | 546.4749 | 1152 | 0.028477 | 0.99668 | 1490 | 0.03 | 2383
2973 | TEMPLETON 2111R86 | 183052111 | TEMPLETON 2111 | R86 | FALSE | 23197.4547 | 17574.2947 | 10.9225 | 160 | 5.7553e-05 | 2847 | 490.6496 | 1209 | 0.028407 | 4.5451 | 1491 | 0.08 | 1637
2170 | MC KEE 1111711900 | 83531111 | MC KEE 1111 | 711900 | FALSE | 20250.2667 | 14456.1594 | 8.9846 | 116 | 7.6946e-05 | 2288 | 301.111 | 1446 | 0.028347 | 3.2883 | 1492 | 0.24 | 1097
7676 | JARVIS 1108289662 | 13501108 | JARVIS 1108 | 289662 | TRUE | 1302.884 | 533.3553 | 0.33148 | 11 | 2.7822e-05 | 3461 | 483.4846 | 1212 | 0.028227 | 0.31049 | 1493 |  | 3149
5235 | BELLEVUE 2103648 | 43182103 | BELLEVUE 2103 | 648 | FALSE | 26216.5179 | 6117.4965 | 3.802 | 187 | 9.6901e-05 | 1716 | 305.0125 | 1439 | 0.028161 | 5.2662 | 1494 | 2.81 | 578
10298 | PIT NO 5 11011618 | 101321101 | PIT NO 5 1101 | 1618 | FALSE | 9746.1598 | 9746.1598 | 6.0573 | 15 | 0.00010839 | 1441 | 237.7895 | 1574 | 0.028087 | 0.42131 | 1495 | 0 | 2632
5972 | TASSAJARA 2104CB | 14662104 | TASSAJARA 2104 | CB | TRUE | 1951.9603 | 159.1645 | 0.098921 | 22 | 5.9141e-05 | 2802 | 153.2438 | 1767 | 0.028017 | 0.61638 | 1496 | 0.28 | 1038
2469 | ELECTRA 11026014 | 162161102 | ELECTRA 1102 | 6014 | FALSE | 8043.0218 | 8043.0218 | 4.9988 | 50 | 0.000124 | 1120 | 242.0554 | 1562 | 0.027926 | 1.3963 | 1497 | 0.1 | 1478
1225 | SUNOL 1101MR298 | 14241101 | SUNOL 1101 | MR298 | FALSE | 8473.8006 | 8244.1822 | 5.1238 | 39 | 7.0694e-05 | 2452 | 586.0273 | 1117 | 0.027925 | 1.0891 | 1498 | 0.26 | 1070
739 | COTATI 1105CB | 42271105 | COTATI 1105 | CB | FALSE | 4309.0759 | 4309.0759 | 2.6781 | 35 | 0.00011326 | 1338 | 266.28 | 1506 | 0.027854 | 0.97488 | 1499 | 11.62 | 384
1612 | CABRILLO 1104Y22 | 183101104 | CABRILLO 1104 | Y22 | FALSE | 40867.3286 | 16721.66 | 10.3926 | 178 | 4.3833e-05 | 3193 | 413.6922 | 1281 | 0.027743 | 4.9383 | 1500 | 0.04 | 2132
2769 | ANNAPOLIS 110176842 | 42861101 | ANNAPOLIS 1101 | 76842 | FALSE | 9156.7064 | 9156.7064 | 5.6909 | 33 | 0.00012448 | 1109 | 276.9184 | 1479 | 0.027724 | 0.91488 | 1501 | 0.08 | 1635
2631 | TEMPLETON 2111A66 | 183052111 | TEMPLETON 2111 | A66 | FALSE | 54313.8381 | 54313.8381 | 33.7563 | 429 | 6.1474e-05 | 2734 | 473.9679 | 1218 | 0.027639 | 11.8573 | 1502 | 0.27 | 1052
2379 | SAN LUIS OBISPO 1103CB | 182631103 | SAN LUIS OBISPO 1103 | CB | TRUE | 10934.0811 | 0 | 0 | 68 | 0.00011128 | 1389 | 204.9489 | 1629 | 0.027594 | 1.8764 | 1503 | 0.03 | 2305
4288 | SAN LUIS OBISPO 1103V82 | 182631103 | SAN LUIS OBISPO 1103 | V82 | FALSE | 22558.9801 | 14130.1147 | 8.7819 | 174 | 7.4918e-05 | 2332 | 326.0495 | 1404 | 0.027572 | 4.7975 | 1504 | 0.06 | 1792
3496 | APPLE HILL 21027502 | 153662102 | APPLE HILL 2102 | 7502 | FALSE | 36933.3454 | 36933.3454 | 22.9542 | 267 | 0.00011381 | 1324 | 264.2675 | 1509 | 0.027532 | 7.351 | 1505 | 38.11 | 197
3795 | SAN LUIS OBISPO 1101V12 | 182631101 | SAN LUIS OBISPO 1101 | V12 | FALSE | 33868.1694 | 33868.1694 | 21.0492 | 127 | 8.411e-05 | 2090 | 399.923 | 1297 | 0.027414 | 3.4815 | 1506 | 0.24 | 1100
5816 | PAUL SWEET 210710986 | 83252107 | PAUL SWEET 2107 | 10986 | FALSE | 31785.0255 | 14988.5933 | 9.3155 | 180 | 9.4351e-05 | 1785 | 282.1821 | 1470 | 0.027411 | 4.9339 | 1507 | 0.19 | 1190
9709 | LAYTONVILLE 1102682 | 42681102 | LAYTONVILLE 1102 | 682 | FALSE | 23844.5349 | 23844.5349 | 14.8195 | 97 | 0.00016349 | 605 | 167.4124 | 1727 | 0.027282 | 2.6464 | 1508 | 2.58 | 596
1461 | LOS OSITOS 21033010 | 182082103 | LOS OSITOS 2103 | 3010 | FALSE | 50085.8598 | 50061.44 | 31.1134 | 229 | 6.2602e-05 | 2699 | 457.2691 | 1239 | 0.027281 | 6.2474 | 1509 | 0.11 | 1434
6161 | HIGHLANDS 1102556 | 43361102 | HIGHLANDS 1102 | 556 | TRUE | 12171.5187 | 285.9131 | 0.1777 | 90 | 6.0969e-05 | 2748 | 422.9587 | 1269 | 0.027227 | 2.4505 | 1510 | 1.68 | 652
8442 | MARTELL 11016074 | 163011101 | MARTELL 1101 | 6074 | FALSE | 5923.6574 | 5923.6574 | 3.6816 | 34 | 0.00013034 | 1003 | 156.7867 | 1759 | 0.027132 | 0.92248 | 1511 | 1.63 | 660
7912 | HALF MOON BAY 1101818874 | 24101101 | HALF MOON BAY 1101 | 818874 | FALSE | 10865.8424 | 9148.5425 | 5.6859 | 42 | 8.8075e-05 | 1981 | 323.2606 | 1408 | 0.02708 | 1.1374 | 1512 |  | 3177
5790 | HIGGINS 1110869408 | 152691110 | HIGGINS 1110 | 869408 | TRUE | 710.7103 | 710.7103 | 0.44171 | 6 | 0.00016423 | 597 | 150.5967 | 1775 | 0.027041 | 0.16225 | 1513 |  | 2977
9590 | OILFIELDS 11037006 | 182391103 | OILFIELDS 1103 | 7006 | TRUE | 11204.5058 | 0 | 0 | 42 | 6.1931e-05 | 2722 | 240.1753 | 1567 | 0.027015 | 1.1346 | 1514 | 0 | 2622
9570 | SWIFT 2102889948 | 83392102 | SWIFT 2102 | 889948 | TRUE | 2120.3673 | 706.8877 | 0.43933 | 8 | 7.9649e-05 | 2217 | 479.8183 | 1216 | 0.026886 | 0.21509 | 1515 |  | 3380
9335 | SAN MIGUEL 1106N34 | 182661106 | SAN MIGUEL 1106 | N34 | FALSE | 22008.9702 | 6041.6356 | 3.7549 | 62 | 9.4539e-05 | 1778 | 242.6816 | 1560 | 0.02675 | 1.6585 | 1516 | 0 | 2638
8060 | MONTE RIO 1112120 | 42811112 | MONTE RIO 1112 | 120 | FALSE | 10326.1868 | 10326.1868 | 6.4178 | 67 | 0.00021509 | 341 | 93.788 | 1989 | 0.026687 | 1.788 | 1517 | 79.25 | 50
2780 | HIGHLANDS 1102CB | 43361102 | HIGHLANDS 1102 | CB | FALSE | 11922.4207 | 11922.4207 | 7.4098 | 78 | 6.4644e-05 | 2617 | 270.2338 | 1497 | 0.026652 | 2.0789 | 1518 | 0.11 | 1413
5253 | HOOPA 110182542 | 192401101 | HOOPA 1101 | 82542 | FALSE | 24330.9579 | 19513.0606 | 12.1274 | 150 | 0.00024689 | 227 | 125.8806 | 1856 | 0.026646 | 3.9969 | 1519 | 0.25 | 1073
9493 | BRUNSWICK 1103904574 | 152481103 | BRUNSWICK 1103 | 904574 | FALSE | 2518.7659 | 2518.7659 | 1.5654 | 25 | 0.0002218 | 312 | 119.8467 | 1870 | 0.026628 | 0.6657 | 1520 |  | 3362
2834 | WILLOW PASS 1101CB | 13911101 | WILLOW PASS 1101 | CB | FALSE | 10055.4219 | 1899.3733 | 1.1805 | 75 | 5.022e-05 | 3033 | 198.6367 | 1643 | 0.026552 | 1.9914 | 1521 | 0.04 | 2084
4322 | WYANDOTTE 11095973 | 102911109 | WYANDOTTE 1109 | 5973 | TRUE | 3972.7876 | 138.2354 | 0.085914 | 35 | 0.00011259 | 1351 | 248.9959 | 1541 | 0.026544 | 0.92904 | 1522 |  | 2881
9896 | PUEBLO 2102773926 | 43292102 | PUEBLO 2102 | 773926 | TRUE | 3395.2146 | 706.7417 | 0.43924 | 25 | 7.9069e-05 | 2232 | 668.6259 | 1044 | 0.026524 | 0.66311 | 1523 |  | 3448
7392 | WINDSOR 1103CB | 43501103 | WINDSOR 1103 | CB | TRUE | 8832.9668 | 0 | 0 | 64 | 0.00011152 | 1384 | 254.8686 | 1534 | 0.026458 | 1.6933 | 1524 |  | 3122
7312 | PEABODY 2113CB | 63642113 | PEABODY 2113 | CB | TRUE | 8317.4057 | 587.3881 | 0.36506 | 40 | 7.0186e-05 | 2464 | 270.6989 | 1494 | 0.026426 | 1.057 | 1525 | 2.37 | 608
5020 | BONNIE NOOK 1101CB | 152301101 | BONNIE NOOK 1101 | CB | FALSE | 23251.1044 | 23251.1044 | 14.4507 | 153 | 0.00019229 | 432 | 98.7244 | 1962 | 0.026396 | 4.0386 | 1526 | 44.02 | 163
2080 | NEWBURG 11313446 | 192151131 | NEWBURG 1131 | 3446 | TRUE | 13148.5405 | 475.0126 | 0.29522 | 87 | 0.00014693 | 773 | 117.907 | 1882 | 0.026372 | 2.2944 | 1527 | 0.23 | 1108
5621 | FORT ROSS 112137326 | 42851121 | FORT ROSS 1121 | 37326 | FALSE | 8213.253 | 8213.253 | 5.1046 | 31 | 5.9994e-05 | 2777 | 369.1163 | 1338 | 0.026358 | 0.8171 | 1528 | 0.04 | 2195
7707 | SUMMIT 110148632 | 152591101 | SUMMIT 1101 | 48632 | FALSE | 4391.6286 | 4391.6286 | 2.7294 | 38 | 0.00010681 | 1483 | 115.1661 | 1895 | 0.026323 | 1.0003 | 1529 | 0.07 | 1766
4086 | WEST POINT 110236676 | 163201102 | WEST POINT 1102 | 36676 | FALSE | 27305.8877 | 27305.8877 | 16.9707 | 173 | 8.1258e-05 | 2175 | 346.1968 | 1376 | 0.026145 | 4.5232 | 1530 | 34.1 | 217
3634 | CHALLENGE 11021902 | 103201102 | CHALLENGE 1102 | 1902 | FALSE | 7840.3138 | 7840.3138 | 4.8728 | 44 | 0.00013679 | 909 | 253.4699 | 1535 | 0.026064 | 1.1468 | 1531 | 31.9 | 227
5849 | HOPLAND 11011100 | 42251101 | HOPLAND 1101 | 1100 | FALSE | 10937.7288 | 5979.935 | 3.7166 | 68 | 8.9766e-05 | 1920 | 293.7962 | 1457 | 0.026059 | 1.772 | 1532 | 0.03 | 2389
9887 | NOVATO 1104676060 | 42211104 | NOVATO 1104 | 676060 | TRUE | 1407.162 | 722.7771 | 0.44921 | 9 | 0.00025905 | 197 | 109.1 | 1913 | 0.026046 | 0.23441 | 1533 |  | 3446
6186 | CALAVERAS CEMENT 110111188 | 162211101 | CALAVERAS CEMENT 1101 | 11188 | FALSE | 48202.5217 | 48202.5217 | 29.9581 | 294 | 0.00012846 | 1041 | 211.2891 | 1617 | 0.02599 | 7.641 | 1534 | 0.06 | 1852
6575 | CLARK ROAD 110247006 | 103091102 | CLARK ROAD 1102 | 47006 | FALSE | 7194.664 | 7194.664 | 4.4715 | 51 | 0.00041526 | 65 | 106.8362 | 1923 | 0.025936 | 1.3227 | 1535 | 0.13 | 1347
5041 | MARTELL 1103CB | 163011103 | MARTELL 1103 | CB | FALSE | 10088.6649 | 2844.8661 | 1.7681 | 76 | 0.00011862 | 1213 | 152.4537 | 1770 | 0.025924 | 1.9702 | 1536 | 0.01 | 2606
7535 | PARADISE 11042034 | 102831104 | PARADISE 1104 | 2034 | FALSE | 17672.0047 | 17659.7087 | 10.9756 | 99 | 0.00023619 | 258 | 172.9141 | 1707 | 0.025842 | 2.5583 | 1537 | 0.4 | 942
3586 | PENRYN 1107346 | 152561107 | PENRYN 1107 | 346 | FALSE | 40386.1099 | 22629.4944 | 14.0643 | 309 | 0.00013985 | 869 | 232.58 | 1582 | 0.025706 | 7.9433 | 1538 | 0.07 | 1770
8624 | JESSUP 11012839 | 103441101 | JESSUP 1101 | 2839 | FALSE | 2358.3859 | 2358.3859 | 1.4657 | 20 | 0.00011836 | 1220 | 279.5294 | 1473 | 0.02569 | 0.5138 | 1539 | 0.07 | 1683
2763 | GOLDTREE 1108CB | 182581108 | GOLDTREE 1108 | CB | FALSE | 7803.1232 | 3646.1026 | 2.2661 | 50 | 6.1558e-05 | 2731 | 249.9677 | 1540 | 0.025673 | 1.2836 | 1540 | 0.06 | 1893
9750 | COVELO 1101430286 | 43061101 | COVELO 1101 | 430286 | FALSE | 8696.3655 | 5942.5051 | 3.6933 | 13 | 7.0159e-05 | 2468 | 482.818 | 1213 | 0.025652 | 0.33348 | 1541 |  | 3410
8494 | BRENTWOOD 2105502672 | 14592105 | BRENTWOOD 2105 | 502672 | FALSE | 30486.256 | 2285.3291 | 1.4203 | 127 | 5.9745e-05 | 2781 | 641.4967 | 1071 | 0.025636 | 3.2558 | 1542 | 0.03 | 2388
5780 | GREEN VALLEY 210111054 | 83192101 | GREEN VALLEY 2101 | 11054 | FALSE | 41601.4757 | 39167.0021 | 24.3425 | 272 | 0.00015629 | 682 | 157.984 | 1754 | 0.025605 | 6.9646 | 1543 | 1.82 | 640
5526 | LLAGAS 2107XR188 | 83182107 | LLAGAS 2107 | XR188 | TRUE | 5000.7034 | 608.151 | 0.37797 | 43 | 0.00010266 | 1579 | 145.3531 | 1791 | 0.025596 | 1.1006 | 1544 | 0.05 | 1999
3427 | COTATI 1105616 | 42271105 | COTATI 1105 | 616 | FALSE | 49320.745 | 4247.523 | 2.6399 | 198 | 8.18e-05 | 2160 | 268.44 | 1503 | 0.025585 | 5.0659 | 1545 | 0.02 | 2449
9956 | CLARKSVILLE 2109781566 | 153612109 | CLARKSVILLE 2109 | 781566 | FALSE | 1246.3402 | 1113.5139 | 0.69205 | 11 | 0.00014318 | 824 | 155.6264 | 1762 | 0.025518 | 0.28069 | 1546 |  | 3459
1199 | BEAR VALLEY 21059560 | 252192105 | BEAR VALLEY 2105 | 9560 | FALSE | 35435.963 | 35435.963 | 22.0236 | 226 | 5.282e-05 | 2976 | 582.977 | 1120 | 0.025353 | 5.7297 | 1547 | 0.31 | 1001
4849 | ELECTRA 11017104 | 162161101 | ELECTRA 1101 | 7104 | FALSE | 19430.6652 | 19430.6652 | 12.0762 | 148 | 0.0001151 | 1296 | 163.538 | 1738 | 0.025302 | 3.7447 | 1548 | 13.46 | 365
4914 | JESSUP 11019002 | 103441101 | JESSUP 1101 | 9002 | FALSE | 9863.4451 | 1568.4919 | 0.97482 | 74 | 0.0001072 | 1468 | 178.96 | 1685 | 0.025292 | 1.8716 | 1549 | 0.04 | 2144
6329 | SILVERADO 2102636 | 43432102 | SILVERADO 2102 | 636 | FALSE | 10208.6635 | 8793.2474 | 5.465 | 81 | 0.00012369 | 1126 | 135.9278 | 1827 | 0.025287 | 2.0483 | 1550 | 0.41 | 940
7235 | BRIDGEVILLE 110137484 | 192461101 | BRIDGEVILLE 1101 | 37484 | FALSE | 15938.0756 | 12688.6958 | 7.8861 | 74 | 0.0001949 | 416 | 197.6391 | 1647 | 0.025267 | 1.8698 | 1551 | 3.58 | 540
4335 | UKIAH 1114844294 | 42771114 | UKIAH 1114 | 844294 | FALSE | 9847.8884 | 3879.784 | 2.4113 | 55 | 0.0001067 | 1485 | 276.8057 | 1480 | 0.025242 | 1.3883 | 1552 |  | 2882
5817 | TIVY VALLEY 110737522 | 252941107 | TIVY VALLEY 1107 | 37522 | TRUE | 4999.5672 | 833.6297 | 0.5181 | 43 | 3.7339e-05 | 3307 | 997.9464 | 835 | 0.025221 | 1.0845 | 1553 | 0.42 | 937
402 | REDBUD 1102922 | 43191102 | REDBUD 1102 | 922 | FALSE | 12634.8407 | 12589.4258 | 7.8244 | 84 | 5.9231e-05 | 2798 | 352.2884 | 1369 | 0.025187 | 2.1157 | 1554 | 0.06 | 1854
4837 | SAN LUIS OBISPO 1104V46 | 182631104 | SAN LUIS OBISPO 1104 | V46 | FALSE | 33477.4498 | 32077.3964 | 19.9362 | 206 | 6.5385e-05 | 2604 | 359.6086 | 1354 | 0.025184 | 5.1879 | 1555 | 0.58 | 860
6418 | DUNLAP 1102CB | 254061102 | DUNLAP 1102 | CB | FALSE | 10840.0956 | 10840.0956 | 6.7372 | 79 | 5.5221e-05 | 2906 | 463.403 | 1231 | 0.025156 | 1.9873 | 1556 | 0 | 2629
8607 | ANNAPOLIS 1101608 | 42861101 | ANNAPOLIS 1101 | 608 | FALSE | 28658.1175 | 28658.1175 | 17.8111 | 74 | 9.5295e-05 | 1755 | 248.4816 | 1545 | 0.025135 | 1.86 | 1557 | 0.18 | 1210
8805 | FRUITLAND 114293234 | 192311142 | FRUITLAND 1142 | 93234 | FALSE | 18471.7273 | 18471.7273 | 11.4803 | 96 | 0.0002481 | 222 | 135.7036 | 1830 | 0.025062 | 2.4059 | 1558 | 7.72 | 442
3300 | FULTON 1102CB | 42561102 | FULTON 1102 | CB | TRUE | 6358.3504 | 326.8592 | 0.20314 | 48 | 0.00010128 | 1621 | 121.8474 | 1865 | 0.025061 | 1.2029 | 1559 | 0.07 | 1754
4515 | GIRVAN 11019732 | 103401101 | GIRVAN 1101 | 9732 | FALSE | 33758.8908 | 33758.8908 | 20.9813 | 267 | 0.00010167 | 1613 | 282.8705 | 1469 | 0.025046 | 6.6872 | 1560 | 4.84 | 504
602 | STAFFORD 1102524 | 43201102 | STAFFORD 1102 | 524 | FALSE | 20718.9245 | 9871.5042 | 6.1352 | 162 | 9.4892e-05 | 1769 | 289.834 | 1464 | 0.02502 | 4.0533 | 1561 | 3.23 | 553
6121 | OTTER 110263868 | 182941102 | OTTER 1102 | 63868 | FALSE | 25546.2406 | 25546.2406 | 15.8771 | 171 | 8.8626e-05 | 1968 | 190.8082 | 1660 | 0.024964 | 4.2689 | 1562 | 0.04 | 2158
4102 | SPAULDING 1101578852 | 152251101 | SPAULDING 1101 | 578852 | FALSE | 38890.7673 | 33210.6867 | 20.6406 | 173 | 9.1712e-05 | 1853 | 190.7466 | 1661 | 0.024946 | 4.3156 | 1563 | 0 | 2630
9390 | COAST RD 04015134 | 88820401 | COAST RD 0401 | 5134 | FALSE | 4886.1695 | 1018.6198 | 0.63308 | 23 | 6.0194e-05 | 2767 | 173.1479 | 1703 | 0.024922 | 0.57321 | 1564 | 0.02 | 2554
9959 | BRIDGEVILLE 1102384530 | 192461102 | BRIDGEVILLE 1102 | 384530 | FALSE | 6144.6716 | 6144.6716 | 3.8189 | 12 | 0.00011661 | 1259 | 223.8048 | 1598 | 0.024779 | 0.29735 | 1565 |  | 3460
2322 | KANAKA 11011034 | 103221101 | KANAKA 1101 | 1034 | FALSE | 17942.0463 | 17942.0463 | 11.1511 | 80 | 8.3104e-05 | 2129 | 308.8782 | 1434 | 0.024689 | 1.9751 | 1566 | 37.44 | 201
5230 | BANGOR 11011806 | 103191101 | BANGOR 1101 | 1806 | FALSE | 6482.8365 | 6482.8365 | 4.0291 | 17 | 0.00015564 | 687 | 310.6981 | 1431 | 0.024567 | 0.41764 | 1567 | 0.08 | 1588
4084 | JOLON 11027040 | 182981102 | JOLON 1102 | 7040 | FALSE | 36891.8795 | 33515.8907 | 20.8303 | 119 | 0.00010008 | 1645 | 276.795 | 1481 | 0.02433 | 2.8953 | 1568 | 0.03 | 2398
7751 | MIWUK 17018050 | 163661701 | MIWUK 1701 | 8050 | FALSE | 19488.3045 | 19488.3045 | 12.1121 | 137 | 6.4562e-05 | 2624 | 296.266 | 1454 | 0.024311 | 3.3307 | 1569 | 82.85 | 41
10676 | KERN OIL 1106397902 | 252721106 | KERN OIL 1106 | 397902 | TRUE | 2608.3236 | 717.5326 | 0.44595 | 9 | 1.8967e-05 | 3553 | 1301.6353 | 682 | 0.024302 | 0.21872 | 1570 |  | 3589
5615 | ELECTRA 110161816 | 162161101 | ELECTRA 1101 | 61816 | FALSE | 37826.9874 | 37826.9874 | 23.5096 | 228 | 9.0781e-05 | 1889 | 261.0762 | 1521 | 0.0243 | 5.5405 | 1571 | 0.1 | 1458
801 | OCEANO 1102CB | 182601102 | OCEANO 1102 | CB | FALSE | 26239.5079 | 25449.7716 | 15.8171 | 183 | 5.9389e-05 | 2793 | 407.261 | 1290 | 0.024236 | 4.4352 | 1572 | 0.24 | 1103
8403 | MOLINO 1101472660 | 42571101 | MOLINO 1101 | 472660 | FALSE | 2333.6937 | 2333.6937 | 1.4504 | 18 | 0.00011189 | 1371 | 307.8995 | 1436 | 0.024226 | 0.43606 | 1573 |  | 3221
4244 | BRUNSWICK 1104CB | 152481104 | BRUNSWICK 1104 | CB | TRUE | 2139.8633 | 621.7387 | 0.38641 | 28 | 0.00025903 | 198 | 63.383 | 2133 | 0.024194 | 0.67743 | 1574 | 1.36 | 681
10152 | SPENCE 1102321000 | 182201102 | SPENCE 1102 | 321000 | FALSE | 4053.5113 | 2330.3266 | 1.4483 | 13 | 3.5425e-05 | 3341 | 465.5516 | 1229 | 0.024187 | 0.31443 | 1575 |  | 3503
3391 | COTATI 1105734248 | 42271105 | COTATI 1105 | 734248 | TRUE | 774.6582 | 774.6582 | 0.48145 | 9 | 9.7301e-05 | 1706 | 238.3995 | 1571 | 0.024166 | 0.2175 | 1576 |  | 2824
9545 | WYANDOTTE 110942650 | 102911109 | WYANDOTTE 1109 | 42650 | FALSE | 4322.5083 | 1459.6214 | 0.90716 | 37 | 0.00018107 | 502 | 100.7676 | 1951 | 0.024082 | 0.89104 | 1577 | 0.04 | 2229
4392 | CLARK ROAD 110290548 | 103091102 | CLARK ROAD 1102 | 90548 | FALSE | 28870.4925 | 28870.4925 | 17.9431 | 168 | 0.00013973 | 872 | 196.9334 | 1651 | 0.024003 | 4.0325 | 1578 | 0.67 | 811
9548 | FROGTOWN 1702224708 | 163451702 | FROGTOWN 1702 | 224708 | FALSE | 1049.1603 | 1033.1582 | 0.64211 | 9 | 0.00015636 | 681 | 235.0194 | 1578 | 0.02399 | 0.21591 | 1579 |  | 3374
2473 | COLUMBIA HILL 110135424 | 152471101 | COLUMBIA HILL 1101 | 35424 | FALSE | 22308.0719 | 22308.0719 | 13.8646 | 147 | 0.00020736 | 374 | 171.1392 | 1711 | 0.023757 | 3.4923 | 1580 | 74.11 | 58
3207 | SHADY GLEN 110151696 | 152431101 | SHADY GLEN 1101 | 51696 | FALSE | 32551.2584 | 28077.2635 | 17.4501 | 238 | 0.00017871 | 514 | 165.4297 | 1734 | 0.023753 | 5.6532 | 1581 | 0.86 | 763
7684 | PETALUMA C 1109738866 | 42631109 | PETALUMA C 1109 | 738866 | FALSE | 4335.7412 | 3280.2516 | 2.0387 | 28 | 6.3795e-05 | 2653 | 268.4844 | 1502 | 0.023732 | 0.66451 | 1582 | 0.1 | 1506
10885 | MORGAN HILL 2111940112 | 83242111 | MORGAN HILL 2111 | 940112 | TRUE | 489.7385 | 455.0253 | 0.2828 | 2 | 5.8767e-05 | 2813 | 268.9489 | 1500 | 0.023701 | 0.047401 | 1583 |  | 3616
10683 | SAN BERNARD 1101438074 | 253191101 | SAN BERNARD 1101 | 438074 | TRUE | 2039.2275 | 516.2478 | 0.32085 | 6 | 3.2276e-05 | 3397 | 1470.0727 | 606 | 0.023646 | 0.14187 | 1584 |  | 3592
274 | GEYSERVILLE 1102350 | 42891102 | GEYSERVILLE 1102 | 350 | FALSE | 31334.246 | 8365.2365 | 5.199 | 194 | 8.9262e-05 | 1940 | 270.3135 | 1496 | 0.023632 | 4.5846 | 1585 | 0.09 | 1536
6780 | FOOTHILL 1102CB | 182951102 | FOOTHILL 1102 | CB | FALSE | 15763.1114 | 12699.351 | 7.8927 | 97 | 5.9509e-05 | 2789 | 274.1428 | 1486 | 0.023627 | 2.2918 | 1586 | 0.1 | 1488
5469 | FROGTOWN 1701L3361 | 163451701 | FROGTOWN 1701 | L3361 | FALSE | 3015.6838 | 3015.6838 | 1.8743 | 21 | 6.3649e-05 | 2658 | 377.9344 | 1325 | 0.023616 | 0.49595 | 1587 | 0.09 | 1563
279 | GEYSERVILLE 1101122 | 42891101 | GEYSERVILLE 1101 | 122 | FALSE | 11125.688 | 2112.7276 | 1.3131 | 54 | 6.2796e-05 | 2689 | 203.6365 | 1635 | 0.023602 | 1.2745 | 1588 | 0.03 | 2263
1737 | FORT BRAGG A 110195294 | 42761101 | FORT BRAGG A 1101 | 95294 | FALSE | 43494.7194 | 43494.7194 | 27.0321 | 186 | 0.00012237 | 1142 | 194.7256 | 1654 | 0.023449 | 4.3615 | 1589 | 0.05 | 2049
1091 | COLUMBIA HILL 1101764 | 152471101 | COLUMBIA HILL 1101 | 764 | FALSE | 23643.468 | 23643.468 | 14.6945 | 146 | 0.00012366 | 1128 | 171.5032 | 1710 | 0.023389 | 3.4148 | 1590 | 57.88 | 95
9377 | COVELO 1101516510 | 43061101 | COVELO 1101 | 516510 | FALSE | 13673.0725 | 6073.3479 | 3.7746 | 73 | 9.3061e-05 | 1818 | 270.871 | 1493 | 0.02337 | 1.706 | 1591 |  | 3347
2700 | PINE GROVE 11023172 | 163751102 | PINE GROVE 1102 | 3172 | FALSE | 60635.9905 | 60635.9905 | 37.6855 | 448 | 0.00020312 | 385 | 59.0594 | 2161 | 0.023346 | 10.4588 | 1592 | 67.49 | 73
10187 | LLAGAS 2105154256 | 83182105 | LLAGAS 2105 | 154256 | TRUE | 446.5228 | 430.6088 | 0.26763 | 2 | 0.00011705 | 1248 | 293.424 | 1459 | 0.023318 | 0.046636 | 1593 |  | 3510
8561 | FROGTOWN 1702307998 | 163451702 | FROGTOWN 1702 | 307998 | TRUE | 911.4775 | 895.4026 | 0.5565 | 6 | 0.00010251 | 1588 | 237.8428 | 1573 | 0.023314 | 0.13989 | 1594 |  | 3235
4078 | PENNGROVE 1101170 | 43471101 | PENNGROVE 1101 | 170 | FALSE | 33470.2158 | 28905.2433 | 17.9647 | 223 | 9.0997e-05 | 1881 | 278.3702 | 1476 | 0.023285 | 5.1925 | 1595 | 10.49 | 396
7270 | LAKEVILLE 1102347280 | 43371102 | LAKEVILLE 1102 | 347280 | FALSE | 20187.7037 | 12761.9341 | 7.9316 | 99 | 7.6036e-05 | 2307 | 290.5041 | 1463 | 0.023256 | 2.3024 | 1596 |  | 3109
2895 | ALHAMBRA 11058302 | 14101105 | ALHAMBRA 1105 | 8302 | FALSE | 13154.2224 | 13154.2224 | 8.1754 | 83 | 9.5232e-05 | 1760 | 244.7794 | 1556 | 0.023206 | 1.9261 | 1597 | 0.09 | 1552
9502 | WILLOW CREEK 11033090 | 192171103 | WILLOW CREEK 1103 | 3090 | FALSE | 17393.6531 | 17393.6531 | 10.8102 | 58 | 0.00018901 | 447 | 142.6437 | 1798 | 0.023177 | 1.3443 | 1598 | 0.06 | 1843
6394 | ORO FINO 11022040 | 103031102 | ORO FINO 1102 | 2040 | FALSE | 14724.8662 | 14724.8662 | 9.1516 | 21 | 0.00015655 | 679 | 141.5532 | 1807 | 0.023168 | 0.48652 | 1599 | 17.99 | 328
2990 | HICKS 2101XR548 | 83432101 | HICKS 2101 | XR548 | FALSE | 14288.8839 | 2708.1629 | 1.6831 | 95 | 8.7871e-05 | 1987 | 271.2652 | 1492 | 0.023159 | 2.2001 | 1600 | 0.04 | 2088
633 | RACETRACK 170310870 | 163761703 | RACETRACK 1703 | 10870 | FALSE | 4188.8092 | 3071.5505 | 1.909 | 28 | 0.00010127 | 1622 | 246.1327 | 1549 | 0.023077 | 0.64616 | 1601 | 0.04 | 2108
4692 | PINE GROVE 11023168 | 163751102 | PINE GROVE 1102 | 3168 | FALSE | 48228.3961 | 48228.3961 | 29.9741 | 285 | 0.00015583 | 684 | 176.2133 | 1695 | 0.023045 | 6.5678 | 1602 | 0.24 | 1095
10488 | HALF MOON BAY 1103531594 | 24101103 | HALF MOON BAY 1103 | 531594 | FALSE | 4284.5499 | 3998.7287 | 2.4852 | 25 | 5.9727e-05 | 2782 | 338.5434 | 1391 | 0.022917 | 0.57293 | 1603 |  | 3558
1419 | CURTIS 17048140 | 163351704 | CURTIS 1704 | 8140 | FALSE | 42456.9039 | 42456.9039 | 26.3871 | 260 | 8.2014e-05 | 2153 | 273.2886 | 1487 | 0.022915 | 5.958 | 1604 | 41.27 | 178
5050 | ATASCADERO 1101A22 | 182541101 | ATASCADERO 1101 | A22 | TRUE | 21048.1737 | 0 | 0 | 167 | 6.0117e-05 | 2769 | 362.8063 | 1349 | 0.022889 | 3.8224 | 1605 | 0.03 | 2288
10722 | TASSAJARA 2103557000 | 14662103 | TASSAJARA 2103 | 557000 | TRUE | 398.6933 | 335.0317 | 0.20822 | 3 | 0.00012959 | 1015 | 348.9375 | 1373 | 0.022855 | 0.068564 | 1606 |  | 3596
4033 | GANSNER 11012006 | 103021101 | GANSNER 1101 | 2006 | FALSE | 27571.1883 | 27571.1883 | 17.1356 | 151 | 6.0918e-05 | 2751 | 384.5024 | 1313 | 0.022834 | 3.4479 | 1607 | 0.22 | 1125
5518 | BIG BEND 1101641808 | 103751101 | BIG BEND 1101 | 641808 | FALSE | 41435.7029 | 41435.7029 | 25.7525 | 234 | 0.00014735 | 768 | 181.2789 | 1681 | 0.022822 | 5.3404 | 1608 | 0.36 | 973
8814 | CLAY 11037142 | 163341103 | CLAY 1103 | 7142 | FALSE | 24816.4121 | 6275.5413 | 3.9003 | 100 | 7.7237e-05 | 2282 | 356.2375 | 1361 | 0.022773 | 2.2773 | 1609 | 0.03 | 2276
9514 | HALF MOON BAY 110258448 | 24101102 | HALF MOON BAY 1102 | 58448 | FALSE | 7774.1256 | 7141.1012 | 4.4382 | 22 | 8.8643e-05 | 1966 | 261.6309 | 1519 | 0.022766 | 0.50086 | 1610 |  | 3368
4404 | EEL RIVER 1102630456 | 192381102 | EEL RIVER 1102 | 630456 | FALSE | 8616.6169 | 8616.6169 | 5.3553 | 37 | 0.00023208 | 277 | 84.9164 | 2030 | 0.022761 | 0.84216 | 1611 |  | 2888
9626 | SAUSALITO 110284278 | 42491102 | SAUSALITO 1102 | 84278 | FALSE | 2506.1692 | 2490.1671 | 1.5476 | 18 | 7.3083e-05 | 2392 | 245.6104 | 1553 | 0.022717 | 0.4089 | 1612 | 2.62 | 594
5345 | ELK 11011300 | 42981101 | ELK 1101 | 1300 | FALSE | 15995.4516 | 5711.2619 | 3.5496 | 64 | 8.5201e-05 | 2052 | 259.4524 | 1525 | 0.02261 | 1.447 | 1613 | 0.01 | 2613
3272 | KESWICK 11019712 | 103451101 | KESWICK 1101 | 9712 | FALSE | 29909.7326 | 29909.7326 | 18.589 | 214 | 0.00017251 | 547 | 156.1721 | 1761 | 0.022607 | 4.838 | 1614 | 0.65 | 825
7529 | EEL RIVER 11021902 | 192381102 | EEL RIVER 1102 | 1902 | FALSE | 11685.375 | 10562.7391 | 6.5648 | 43 | 0.00014928 | 746 | 134.194 | 1834 | 0.022585 | 0.97115 | 1615 | 0.08 | 1666
9292 | PUEBLO 2102895310 | 43292102 | PUEBLO 2102 | 895310 | TRUE | 4366.1321 | 592.9592 | 0.36853 | 31 | 6.4236e-05 | 2637 | 241.124 | 1565 | 0.022565 | 0.69951 | 1616 |  | 3336
3684 | VASCO 1102MR178 | 13751102 | VASCO 1102 | MR178 | FALSE | 21546.6859 | 2579.6297 | 1.6033 | 117 | 6.7557e-05 | 2547 | 427.86 | 1263 | 0.022562 | 2.6398 | 1617 |  | 2847
6059 | RINCON 1103198 | 43321103 | RINCON 1103 | 198 | FALSE | 10335.8179 | 10335.8179 | 6.4238 | 62 | 0.0001183 | 1224 | 193.0004 | 1658 | 0.02256 | 1.3987 | 1618 | 41.1 | 181
8232 | FOOTHILL 1101251688 | 182951101 | FOOTHILL 1101 | 251688 | FALSE | 12475.4445 | 11233.7101 | 6.9818 | 68 | 7.4101e-05 | 2355 | 394.4035 | 1300 | 0.022486 | 1.5291 | 1619 |  | 3207
9659 | CAMBRIA 1101858200 | 182771101 | CAMBRIA 1101 | 858200 | FALSE | 9571.0308 | 9200.2096 | 5.718 | 31 | 6.601e-05 | 2588 | 330.1244 | 1397 | 0.022446 | 0.69582 | 1620 |  | 3395
5819 | COTTONWOOD 110359128 | 102931103 | COTTONWOOD 1103 | 59128 | FALSE | 11301.2737 | 1201.9482 | 0.74702 | 65 | 0.00010017 | 1639 | 414.1368 | 1279 | 0.022397 | 1.4558 | 1621 |  | 2980
9234 | WILDWOOD 110185112 | 103611101 | WILDWOOD 1101 | 85112 | FALSE | 10932.2503 | 10932.2503 | 6.7944 | 54 | 7.2027e-05 | 2417 | 306.4662 | 1437 | 0.022386 | 1.2088 | 1622 | 0.07 | 1740
2051 | LAYTONVILLE 1101518 | 42681101 | LAYTONVILLE 1101 | 518 | FALSE | 36303.8238 | 4840.0159 | 3.0081 | 165 | 0.0001564 | 680 | 133.4232 | 1837 | 0.02237 | 3.6911 | 1623 | 0.31 | 1002
4400 | CALISTOGA 1102769230 | 42711102 | CALISTOGA 1102 | 769230 | FALSE | 27505.7293 | 17732.852 | 11.021 | 160 | 0.00011179 | 1372 | 159.0323 | 1749 | 0.022338 | 3.574 | 1624 | 0.28 | 1034
1232 | VOLTA 110237350 | 102541102 | VOLTA 1102 | 37350 | FALSE | 39069.9006 | 39069.9006 | 24.2821 | 255 | 7.6956e-05 | 2287 | 360.2031 | 1353 | 0.02227 | 5.6788 | 1625 | 13.94 | 359
1076 | MC ARTHUR 1101648698 | 103491101 | MC ARTHUR 1101 | 648698 | FALSE | 30462.3699 | 17135.0454 | 10.6495 | 173 | 2.2209e-05 | 3516 | 1031.0161 | 807 | 0.022255 | 3.85 | 1626 |  | 2707
6771 | HALSEY 1102CB | 152241102 | HALSEY 1102 | CB | FALSE | 12882.1278 | 12682.5013 | 7.8822 | 86 | 0.00028932 | 141 | 75.4177 | 2064 | 0.022172 | 1.9068 | 1627 | 0.07 | 1701
1966 | GARBERVILLE 11011514 | 192221101 | GARBERVILLE 1101 | 1514 | FALSE | 23767.6372 | 23767.6372 | 14.7717 | 123 | 0.0005607 | 23 | 46.0416 | 2239 | 0.022168 | 2.7266 | 1628 | 0.07 | 1675
7554 | SAN LUIS OBISPO 1105512313 | 182631105 | SAN LUIS OBISPO 1105 | 512313 | TRUE | 1333.0799 | 785.9125 | 0.48845 | 10 | 3.7023e-05 | 3314 | 418.9141 | 1273 | 0.022063 | 0.22063 | 1629 |  | 3136
6120 | PUEBLO 2103895784 | 43292103 | PUEBLO 2103 | 895784 | FALSE | 16727.2163 | 12538.91 | 7.793 | 110 | 8.3743e-05 | 2101 | 275.8868 | 1483 | 0.022046 | 2.4251 | 1630 |  | 3006
63 | CORRAL 110175204 | 162991101 | CORRAL 1101 | 75204 | FALSE | 29879.1855 | 1376.4738 | 0.85548 | 130 | 8.0747e-05 | 2187 | 212.0292 | 1614 | 0.021935 | 2.8515 | 1631 | 0.01 | 2584
9574 | MONROE 2103848530 | 43302103 | MONROE 2103 | 848530 | TRUE | 2567.2359 | 715.3706 | 0.44461 | 17 | 9.0059e-05 | 1909 | 263.7059 | 1513 | 0.021849 | 0.37143 | 1632 |  | 3381
7210 | WEST POINT 110234416 | 163201102 | WEST POINT 1102 | 34416 | FALSE | 16821.5127 | 16821.5127 | 10.4546 | 113 | 8.8542e-05 | 1971 | 264.2059 | 1510 | 0.021823 | 2.466 | 1633 | 42.3 | 170
2105 | WEST POINT 1102CB | 163201102 | WEST POINT 1102 | CB | FALSE | 28620.471 | 28620.471 | 17.7877 | 195 | 0.00020845 | 368 | 153.8768 | 1765 | 0.02173 | 4.2374 | 1634 | 37.1 | 202
6954 | WYANDOTTE 1110144140 | 102911110 | WYANDOTTE 1110 | 144140 | TRUE | 2469.4129 | 417.0111 | 0.25917 | 20 | 0.00015373 | 713 | 178.8701 | 1686 | 0.021719 | 0.43439 | 1635 |  | 3076
9884 | ELK 1101311906 | 42981101 | ELK 1101 | 311906 | FALSE | 1528.1122 | 1112.4459 | 0.69139 | 12 | 0.00010712 | 1471 | 200.1105 | 1641 | 0.021675 | 0.2601 | 1636 |  | 3445
1046 | GARBERVILLE 11028652 | 192221102 | GARBERVILLE 1102 | 8652 | FALSE | 21158.9046 | 21158.9046 | 13.1503 | 114 | 0.0003142 | 113 | 77.6007 | 2059 | 0.021633 | 2.4661 | 1637 | 8.55 | 422
3164 | BRUNSWICK 11062416 | 152481106 | BRUNSWICK 1106 | 2416 | FALSE | 50020.1074 | 46563.0328 | 28.9391 | 360 | 0.00016423 | 598 | 156.2016 | 1760 | 0.021547 | 7.7569 | 1638 | 0.56 | 863
3168 | LUCERNE 1103630 | 43351103 | LUCERNE 1103 | 630 | FALSE | 21891.4244 | 20012.2615 | 12.4377 | 154 | 9.5266e-05 | 1756 | 292.7922 | 1460 | 0.021529 | 3.3154 | 1639 | 0.13 | 1357
9831 | HALF MOON BAY 1101771258 | 24101101 | HALF MOON BAY 1101 | 771258 | TRUE | 308.3578 | 308.3578 | 0.19165 | 4 | 6.8099e-05 | 2532 | 427.9894 | 1262 | 0.021484 | 0.085935 | 1640 |  | 3432
8239 | FRUITLAND 11413902 | 192311141 | FRUITLAND 1141 | 3902 | FALSE | 8223.6344 | 8223.6344 | 5.111 | 9 | 0.00018188 | 498 | 110.945 | 1907 | 0.021389 | 0.1925 | 1641 | 0.02 | 2480
4880 | CURTIS 1705CB | 163351705 | CURTIS 1705 | CB | FALSE | 22023.4026 | 21461.232 | 13.3382 | 163 | 0.00013265 | 967 | 170.2363 | 1715 | 0.021383 | 3.4854 | 1642 | 0.14 | 1316
1762 | VINEYARD 2108609690 | 14502108 | VINEYARD 2108 | 609690 | FALSE | 12043.451 | 7774.3071 | 4.8318 | 72 | 7.5587e-05 | 2321 | 321.8791 | 1411 | 0.021383 | 1.5396 | 1643 |  | 2744
7400 | CLARKSVILLE 21096502 | 153612109 | CLARKSVILLE 2109 | 6502 | FALSE | 6145.0425 | 1500.682 | 0.93268 | 52 | 0.00017025 | 561 | 88.4192 | 2012 | 0.021251 | 1.1051 | 1644 | 1.73 | 647
10207 | MONTE RIO 111159046 | 42811111 | MONTE RIO 1111 | 59046 | FALSE | 6015.5462 | 5641.1576 | 3.506 | 15 | 0.00010509 | 1522 | 101.9046 | 1945 | 0.021246 | 0.31869 | 1645 | 0.25 | 1078
4878 | PLACERVILLE 21069712 | 153082106 | PLACERVILLE 2106 | 9712 | FALSE | 39765.9579 | 39765.9579 | 24.7147 | 226 | 0.00014908 | 750 | 116.696 | 1890 | 0.021241 | 4.8004 | 1646 | 0.54 | 877
2046 | LINCOLN 11042072 | 153701104 | LINCOLN 1104 | 2072 | TRUE | 27455.5664 | 501.4668 | 0.31166 | 193 | 9.3699e-05 | 1804 | 181.6575 | 1679 | 0.021197 | 4.091 | 1647 | 0.03 | 2308
7243 | SILVERADO 2104708 | 43432104 | SILVERADO 2104 | 708 | FALSE | 7904.2269 | 6040.8568 | 3.7544 | 61 | 0.00013285 | 959 | 152.2948 | 1771 | 0.02118 | 1.292 | 1648 | 0.54 | 876
593 | BRUNSWICK 11021010 | 152481102 | BRUNSWICK 1102 | 1010 | FALSE | 71394.2707 | 71394.2707 | 44.3718 | 479 | 0.00011001 | 1412 | 172.5805 | 1708 | 0.021168 | 10.1396 | 1649 | 129.45 | 6
5896 | CHALLENGE 11015460 | 103201101 | CHALLENGE 1101 | 5460 | FALSE | 18980.3372 | 18980.3372 | 11.7964 | 91 | 0.000114 | 1322 | 193.3663 | 1657 | 0.021116 | 1.9215 | 1650 | 41.43 | 176
9400 | BELL 110880680 | 152701108 | BELL 1108 | 80680 | FALSE | 2866.5185 | 1030.5857 | 0.64051 | 24 | 0.00023396 | 265 | 175.0191 | 1697 | 0.021095 | 0.50627 | 1651 | 0.04 | 2179
6134 | CALAVERAS CEMENT 110180930 | 162211101 | CALAVERAS CEMENT 1101 | 80930 | FALSE | 29528.4888 | 29528.4888 | 18.3521 | 180 | 6.8218e-05 | 2529 | 304.5139 | 1442 | 0.021019 | 3.7835 | 1652 | 0.22 | 1126
5626 | WYANDOTTE 1103CB | 102911103 | WYANDOTTE 1103 | CB | TRUE | 11751.5136 | 394.0047 | 0.24488 | 100 | 0.00016594 | 582 | 73.1844 | 2079 | 0.021017 | 2.1017 | 1653 | 0.02 | 2416
5183 | ALTO 1125902 | 42031125 | ALTO 1125 | 902 | FALSE | 19453.8935 | 19453.8935 | 12.0907 | 83 | 9.1473e-05 | 1858 | 227.244 | 1592 | 0.020905 | 1.7351 | 1654 | 0.72 | 798
7644 | LLAGAS 2101783467 | 83182101 | LLAGAS 2101 | 783467 | FALSE | 16521.4957 | 16448.6096 | 10.2229 | 61 | 8.018e-05 | 2201 | 245.1782 | 1554 | 0.020785 | 1.2679 | 1655 |  | 3145
7011 | MOUNTAIN QUARRIES 21011180 | 152282101 | MOUNTAIN QUARRIES 2101 | 1180 | FALSE | 20847.2086 | 20847.2086 | 12.9566 | 141 | 0.00012525 | 1094 | 118.9045 | 1874 | 0.020771 | 2.9287 | 1656 | 0.11 | 1417
11063 | APPLE HILL 1104814656 | 153661104 | APPLE HILL 1104 | 814656 | TRUE | 28.1252 | 28.1252 | 0.01748 | 1 | 0.00086571 | 4 | 23.8451 | 2401 | 0.020643 | 0.020643 | 1657 |  | 3634
9926 | BUCKS CREEK 1103CB | 102211103 | BUCKS CREEK 1103 | CB | FALSE | 3707.9332 | 3707.9332 | 2.3045 | 31 | 9.4015e-05 | 1792 | 320.4886 | 1415 | 0.020623 | 0.63931 | 1658 | 0.11 | 1444
3649 | FROGTOWN 1702812366 | 163451702 | FROGTOWN 1702 | 812366 | FALSE | 4450.8969 | 4421.1038 | 2.7477 | 28 | 8.5129e-05 | 2055 | 149.7437 | 1778 | 0.020596 | 0.57668 | 1659 |  | 2843
9417 | DUNBAR 1102694641 | 43071102 | DUNBAR 1102 | 694641 | FALSE | 6527.852 | 6527.852 | 4.0571 | 49 | 7.3209e-05 | 2390 | 257.8416 | 1526 | 0.020553 | 1.0071 | 1660 |  | 3355
8194 | STANISLAUS 17017144 | 162821701 | STANISLAUS 1701 | 7144 | FALSE | 7491.0055 | 7491.0055 | 4.6557 | 52 | 8.7335e-05 | 2005 | 376.542 | 1327 | 0.020479 | 1.0649 | 1661 | 0.36 | 967
10788 | FITCH MOUNTAIN 1111752596 | 42751111 | FITCH MOUNTAIN 1111 | 752596 | TRUE | 1041.1396 | 395.1334 | 0.24558 | 6 | 0.00010963 | 1418 | 256.5638 | 1530 | 0.020465 | 0.12279 | 1662 |  | 3606
3463 | WOODACRE 1102851 | 43021102 | WOODACRE 1102 | 851 | FALSE | 2029.0984 | 2029.0984 | 1.2611 | 14 | 0.00014146 | 845 | 190.4229 | 1662 | 0.020416 | 0.28582 | 1663 | 44.15 | 161
331 | WEST POINT 11024790 | 163201102 | WEST POINT 1102 | 4790 | FALSE | 52731.0383 | 52731.0383 | 32.7726 | 305 | 0.00011374 | 1325 | 232.2083 | 1584 | 0.020377 | 6.2151 | 1664 | 47.18 | 136
8939 | STELLING 111060080 | 83481110 | STELLING 1110 | 60080 | FALSE | 16285.3103 | 15418.9407 | 9.5829 | 64 | 0.00014044 | 864 | 185.0893 | 1672 | 0.020345 | 1.3021 | 1665 | 0.24 | 1091
5387 | PLACERVILLE 210611132 | 153082106 | PLACERVILLE 2106 | 11132 | FALSE | 69633.6958 | 69633.6958 | 43.2776 | 420 | 0.00012774 | 1054 | 197.2748 | 1649 | 0.020262 | 8.5102 | 1666 | 0.54 | 875
3326 | ORO FINO 110265932 | 103031102 | ORO FINO 1102 | 65932 | FALSE | 7276.7194 | 7276.7194 | 4.5225 | 48 | 0.00012509 | 1096 | 211.5152 | 1616 | 0.020219 | 0.97052 | 1667 | 64.62 | 78
7230 | PINE GROVE 110283098 | 163751102 | PINE GROVE 1102 | 83098 | FALSE | 12739.0077 | 12739.0077 | 7.9173 | 104 | 7.5775e-05 | 2312 | 344.4746 | 1378 | 0.020137 | 2.0942 | 1668 | 45.66 | 147
2235 | MOLINO 1102318 | 42571102 | MOLINO 1102 | 318 | FALSE | 31114.0365 | 31114.0365 | 19.3375 | 228 | 0.00011669 | 1256 | 178.6742 | 1688 | 0.020097 | 4.5821 | 1669 | 88.23 | 35
9552 | JOLON 11027068 | 182981102 | JOLON 1102 | 7068 | FALSE | 6155.1451 | 6139.1207 | 3.8155 | 12 | 7.071e-05 | 2451 | 336.2364 | 1392 | 0.019995 | 0.23993 | 1670 | 0.05 | 1997
7621 | UKIAH 1115CB | 42771115 | UKIAH 1115 | CB | FALSE | 10025.1577 | 6936.1203 | 4.3108 | 73 | 0.00013127 | 993 | 100.6191 | 1952 | 0.019906 | 1.4531 | 1671 | 0.05 | 1978
5118 | SAN LUIS OBISPO 1107V60 | 182631107 | SAN LUIS OBISPO 1107 | V60 | FALSE | 25811.5583 | 25811.5583 | 16.042 | 142 | 6.4335e-05 | 2632 | 354.0238 | 1367 | 0.0199 | 2.8258 | 1672 | 0.51 | 892
1916 | MOLINO 1104368158 | 42571104 | MOLINO 1104 | 368158 | FALSE | 14121.5307 | 4484.8758 | 2.7874 | 105 | 0.0001001 | 1644 | 219.1144 | 1607 | 0.019862 | 2.0855 | 1673 |  | 2756
8812 | ANTLER 11011376 | 103271101 | ANTLER 1101 | 1376 | FALSE | 14477.8455 | 14477.8455 | 8.998 | 70 | 0.00013205 | 982 | 179.7284 | 1683 | 0.019836 | 1.3885 | 1674 | 0.02 | 2535
3393 | SILVERADO 2102714 | 43432102 | SILVERADO 2102 | 714 | FALSE | 17594.5823 | 5568.6627 | 3.4609 | 121 | 0.0001288 | 1033 | 138.0832 | 1817 | 0.019829 | 2.3993 | 1675 | 0.08 | 1672
8102 | FORESTHILL 110175340 | 152181101 | FORESTHILL 1101 | 75340 | FALSE | 7696.0179 | 7696.0179 | 4.7831 | 62 | 0.00022111 | 314 | 112.7853 | 1902 | 0.01968 | 1.2202 | 1676 | 43.45 | 168
7713 | DUNBAR 11014817 | 43071101 | DUNBAR 1101 | 4817 | FALSE | 5079.2964 | 5079.2964 | 3.1568 | 42 | 0.00011215 | 1364 | 172.256 | 1709 | 0.019666 | 0.82599 | 1677 | 8.13 | 436
6368 | EAST QUINCY 1101951424 | 102551101 | EAST QUINCY 1101 | 951424 | FALSE | 5857.3043 | 1124.2371 | 0.69872 | 49 | 6.6606e-05 | 2568 | 260.8969 | 1522 | 0.019501 | 0.95554 | 1678 |  | 3026
6762 | HOOPA 11013304 | 192401101 | HOOPA 1101 | 3304 | FALSE | 27901.6416 | 27901.6416 | 17.341 | 88 | 0.00030684 | 123 | 72.4308 | 2081 | 0.019486 | 1.7148 | 1679 | 0.14 | 1315
4845 | SAN JOAQUIN #3 110210342 | 252531102 | SAN JOAQUIN #3 1102 | 10342 | FALSE | 2930.8819 | 2930.8819 | 1.8216 | 23 | 0.00012225 | 1143 | 225.3144 | 1595 | 0.019463 | 0.44766 | 1680 | 0.23 | 1111
3381 | LUCERNE 110638436 | 43351106 | LUCERNE 1106 | 38436 | FALSE | 7699.8876 | 7253.5318 | 4.5081 | 62 | 0.00011304 | 1342 | 129.1673 | 1847 | 0.019424 | 1.2043 | 1681 | 0.17 | 1243
8990 | HALF MOON BAY 1103540991 | 24101103 | HALF MOON BAY 1103 | 540991 | FALSE | 2594.6741 | 2544.5262 | 1.5814 | 16 | 6.9859e-05 | 2477 | 260.165 | 1524 | 0.019417 | 0.31068 | 1682 |  | 3290
1522 | RIO DELL 11021504 | 192251102 | RIO DELL 1102 | 1504 | FALSE | 19432.0475 | 17454.8051 | 10.8482 | 64 | 0.00027686 | 165 | 148.5088 | 1782 | 0.019342 | 1.2379 | 1683 | 0.01 | 2608
6286 | DUNBAR 1101416 | 43071101 | DUNBAR 1101 | 416 | FALSE | 5187.8358 | 4249.986 | 2.6414 | 28 | 0.00012384 | 1122 | 177.6431 | 1689 | 0.019316 | 0.54085 | 1684 | 0.35 | 975
2445 | MC ARTHUR 11011546 | 103491101 | MC ARTHUR 1101 | 1546 | FALSE | 37312.9087 | 22193.9329 | 13.7936 | 102 | 2.0489e-05 | 3539 | 794.3875 | 945 | 0.019258 | 1.9643 | 1685 | 0.02 | 2496
2748 | HALF MOON BAY 11036018 | 24101103 | HALF MOON BAY 1103 | 6018 | FALSE | 30239.5339 | 25219.5525 | 15.6741 | 160 | 8.5245e-05 | 2048 | 248.6459 | 1544 | 0.019223 | 3.0757 | 1686 | 0.05 | 1942
4766 | CLOVERDALE 1101807953 | 42821101 | CLOVERDALE 1101 | 807953 | TRUE | 1013.1517 | 745.8215 | 0.46353 | 11 | 0.00012129 | 1161 | 149.9335 | 1777 | 0.019176 | 0.21093 | 1687 |  | 2915
3508 | CLEAR LAKE 1102223792 | 42141102 | CLEAR LAKE 1102 | 223792 | FALSE | 1426.5673 | 1262.347 | 0.78455 | 10 | 7.6537e-05 | 2293 | 237.9603 | 1572 | 0.019106 | 0.19106 | 1688 |  | 2832
3278 | KONOCTI 1108CB | 43311108 | KONOCTI 1108 | CB | FALSE | 14256.0927 | 10229.3323 | 6.3576 | 98 | 0.00010673 | 1484 | 150.89 | 1774 | 0.019021 | 1.864 | 1689 | 0.06 | 1871
218 | MADISON 21017702 | 63172101 | MADISON 2101 | 7702 | TRUE | 30606.5708 | 0 | 0 | 168 | 8.5206e-05 | 2051 | 328.4397 | 1400 | 0.018893 | 3.174 | 1690 | 0.04 | 2103
5100 | RIO DELL 110270960 | 192251102 | RIO DELL 1102 | 70960 | FALSE | 18837.8278 | 9297.8122 | 5.7786 | 103 | 0.00023998 | 245 | 91.5029 | 1995 | 0.018609 | 1.9167 | 1691 | 0 | 2636
1226 | FORT ROSS 11212987 | 42851121 | FORT ROSS 1121 | 2987 | FALSE | 3171.9583 | 3171.9583 | 1.9714 | 18 | 0.0002636 | 186 | 74.107 | 2072 | 0.018603 | 0.33485 | 1692 | 15.92 | 343
4217 | CHALLENGE 1102CB | 103201102 | CHALLENGE 1102 | CB | FALSE | 24644.898 | 24644.898 | 15.3169 | 123 | 0.00014722 | 772 | 162.3912 | 1740 | 0.0185 | 2.2755 | 1693 | 73.53 | 61
4592 | PHILO 1102928 | 42601102 | PHILO 1102 | 928 | FALSE | 24779.274 | 22468.3871 | 13.9642 | 125 | 9.505e-05 | 1765 | 208.5932 | 1622 | 0.018489 | 2.3111 | 1694 | 0.05 | 2054
4143 | MENDOCINO 1101CB | 42951101 | MENDOCINO 1101 | CB | FALSE | 6642.1904 | 4240.0548 | 2.6352 | 54 | 0.00012016 | 1183 | 144.2308 | 1793 | 0.018327 | 0.98966 | 1695 | 0.11 | 1449
5556 | WEST POINT 11021305 | 163201102 | WEST POINT 1102 | 1305 | FALSE | 18201.3708 | 18201.3708 | 11.3122 | 105 | 0.00010838 | 1442 | 197.4917 | 1648 | 0.01831 | 1.9226 | 1696 | 0.76 | 784
7818 | SONOMA 1105575872 | 42721105 | SONOMA 1105 | 575872 | FALSE | 2328.1768 | 1906.857 | 1.1851 | 12 | 0.00010594 | 1497 | 157.6636 | 1757 | 0.018279 | 0.21935 | 1697 |  | 3165
1713 | HALF MOON BAY 1103H80 | 24101103 | HALF MOON BAY 1103 | H80 | FALSE | 31889.194 | 31889.194 | 19.8193 | 164 | 9.888e-05 | 1673 | 213.2657 | 1612 | 0.018248 | 2.9927 | 1698 |  | 2739
3304 | DIAMOND SPRINGS 11039432 | 152261103 | DIAMOND SPRINGS 1103 | 9432 | FALSE | 32768.2312 | 28100.4349 | 17.4645 | 251 | 0.0001473 | 771 | 86.1349 | 2022 | 0.018233 | 4.5765 | 1699 | 0.25 | 1080
1922 | ALLEGHANY 1102CB | 152101102 | ALLEGHANY 1102 | CB | FALSE | 28981.2992 | 28981.2992 | 18.012 | 104 | 0.00012953 | 1019 | 141.7915 | 1804 | 0.018204 | 1.8932 | 1700 | 44.04 | 162
4888 | DUNBAR 110179086 | 43071101 | DUNBAR 1101 | 79086 | FALSE | 11075.7434 | 10954.594 | 6.8083 | 82 | 0.00011015 | 1408 | 169.8424 | 1717 | 0.018179 | 1.4907 | 1701 | 0.08 | 1638
1290 | FROGTOWN 170232556 | 163451702 | FROGTOWN 1702 | 32556 | TRUE | 2113.2756 | 188.0999 | 0.1169 | 19 | 0.00017313 | 540 | 58.9098 | 2162 | 0.018147 | 0.34478 | 1702 | 0.05 | 2039
4459 | CLARK ROAD 11022094 | 103091102 | CLARK ROAD 1102 | 2094 | FALSE | 5517.0419 | 5517.0419 | 3.4289 | 11 | 0.00021985 | 323 | 101.8231 | 1947 | 0.018088 | 0.19897 | 1703 | 0.01 | 2580
8596 | SAN JOAQUIN #3 1101CB | 252531101 | SAN JOAQUIN #3 1101 | CB | FALSE | 19055.2866 | 19055.2866 | 11.8429 | 80 | 8.794e-05 | 1984 | 356.7774 | 1359 | 0.018079 | 1.4463 | 1704 | 0.23 | 1117
7985 | MERCED FALLS 1102482838 | 252811102 | MERCED FALLS 1102 | 482838 | FALSE | 17714.345 | 14284.261 | 8.8777 | 52 | 6.1569e-05 | 2730 | 318.0089 | 1421 | 0.018057 | 0.93898 | 1705 |  | 3180
5651 | MOUNTAIN QUARRIES 21012422 | 152282101 | MOUNTAIN QUARRIES 2101 | 2422 | FALSE | 13951.5772 | 13951.5772 | 8.671 | 81 | 0.00012199 | 1147 | 229.8045 | 1587 | 0.018043 | 1.4615 | 1706 | 0.07 | 1676
9070 | SILVERADO 2102437194 | 43432102 | SILVERADO 2102 | 437194 | FALSE | 1741.9129 | 1702.9792 | 1.0584 | 17 | 9.4479e-05 | 1781 | 148.2733 | 1783 | 0.018026 | 0.30645 | 1707 |  | 3303
2577 | HARTLEY 110186876 | 43211101 | HARTLEY 1101 | 86876 | FALSE | 13761.5335 | 3945.9351 | 2.4524 | 110 | 6.2134e-05 | 2715 | 110.516 | 1909 | 0.018007 | 1.9808 | 1708 | 0.03 | 2303
5850 | GEYSERVILLE 1101711966 | 42891101 | GEYSERVILLE 1101 | 711966 | FALSE | 19227.2924 | 6326.045 | 3.9317 | 122 | 9.0078e-05 | 1907 | 205.4077 | 1625 | 0.017908 | 2.1848 | 1709 |  | 2982
8508 | PIKE CITY 11011720 | 152201101 | PIKE CITY 1101 | 1720 | FALSE | 9489.0848 | 9489.0848 | 5.8975 | 34 | 6.9471e-05 | 2488 | 304.935 | 1440 | 0.017864 | 0.60738 | 1710 | 23.51 | 285
4021 | GRASS VALLEY 11012766 | 152031101 | GRASS VALLEY 1101 | 2766 | FALSE | 5300.562 | 5300.562 | 3.2943 | 31 | 0.00018321 | 487 | 59.8653 | 2154 | 0.017834 | 0.55287 | 1711 | 29.29 | 242
5421 | DUNBAR 1102261774 | 43071102 | DUNBAR 1102 | 261774 | FALSE | 21761.0718 | 21761.0718 | 13.5246 | 142 | 9.9916e-05 | 1650 | 183.8239 | 1678 | 0.01783 | 2.5319 | 1712 |  | 2952
1746 | TEMPLETON 2111CB | 183052111 | TEMPLETON 2111 | CB | FALSE | 17908.5118 | 3627.2584 | 2.2544 | 118 | 9.0618e-05 | 1894 | 263.1957 | 1514 | 0.017802 | 2.1007 | 1713 | 0.7 | 809
2820 | ALTO 1124432 | 42031124 | ALTO 1124 | 432 | FALSE | 12624.3351 | 12624.3351 | 7.8461 | 72 | 0.00017278 | 544 | 132.4511 | 1841 | 0.017729 | 1.2765 | 1714 | 0.96 | 740
5452 | PUEBLO 2102850102 | 43292102 | PUEBLO 2102 | 850102 | TRUE | 3948.9067 | 287.4404 | 0.17865 | 23 | 4.4232e-05 | 3186 | 279.8882 | 1472 | 0.01772 | 0.40756 | 1715 |  | 2955
3283 | CURTIS 170390320 | 163351703 | CURTIS 1703 | 90320 | FALSE | 44849.664 | 44849.664 | 27.8742 | 282 | 7.4079e-05 | 2356 | 382.5749 | 1315 | 0.017701 | 4.9917 | 1716 | 0.1 | 1463
3501 | CRESCENT MILLS 21012232 | 103132101 | CRESCENT MILLS 2101 | 2232 | FALSE | 32508.1294 | 25513.6468 | 15.8568 | 128 | 4.4844e-05 | 3165 | 539.0362 | 1160 | 0.017667 | 2.2614 | 1717 | 4.69 | 510
10143 | GRASS VALLEY 1101750804 | 152031101 | GRASS VALLEY 1101 | 750804 | TRUE | 449.416 | 390.0676 | 0.24243 | 5 | 0.00016489 | 588 | 71.3665 | 2087 | 0.017655 | 0.088275 | 1718 |  | 3500
3289 | MONTICELLO 11011589 | 43051101 | MONTICELLO 1101 | 1589 | FALSE | 6873.0951 | 6873.0951 | 4.2717 | 52 | 8.5041e-05 | 2058 | 184.9596 | 1673 | 0.01765 | 0.91781 | 1719 | 0.08 | 1649
1138 | ELECTRA 110136816 | 162161101 | ELECTRA 1101 | 36816 | FALSE | 8023.9266 | 8023.9266 | 4.9869 | 60 | 0.00012475 | 1102 | 139.9542 | 1810 | 0.017625 | 1.0575 | 1720 | 0.09 | 1516
9331 | WILLOW CREEK 1102CB | 192171102 | WILLOW CREEK 1102 | CB | FALSE | 11789.4236 | 11789.4236 | 7.3272 | 71 | 0.00029554 | 134 | 73.697 | 2075 | 0.017606 | 1.25 | 1721 | 13.84 | 360
6284 | ANTLER 11011378 | 103271101 | ANTLER 1101 | 1378 | FALSE | 40111.5829 | 39490.7149 | 24.5436 | 201 | 0.00013379 | 948 | 148.5755 | 1780 | 0.017574 | 3.5323 | 1722 | 0.05 | 2031
8843 | HOLLISTER 2104117328 | 182492104 | HOLLISTER 2104 | 117328 | FALSE | 23158.4732 | 9894.6539 | 6.1496 | 44 | 4.0861e-05 | 3248 | 400.677 | 1296 | 0.017549 | 0.77216 | 1723 |  | 3271
106 | WYANDOTTE 11101954 | 102911110 | WYANDOTTE 1110 | 1954 | FALSE | 17187.784 | 4223.5591 | 2.625 | 132 | 0.00016112 | 630 | 102.5688 | 1939 | 0.017468 | 2.3057 | 1724 | 0.07 | 1692
7269 | CURTIS 17046060 | 163351704 | CURTIS 1704 | 6060 | FALSE | 6540.8971 | 6540.8971 | 4.0652 | 50 | 0.00014094 | 855 | 178.7675 | 1687 | 0.01746 | 0.873 | 1725 | 0.1 | 1461
4024 | MOLINO 11015042 | 42571101 | MOLINO 1101 | 5042 | FALSE | 11222.6237 | 9737.3633 | 6.0518 | 90 | 0.0001242 | 1114 | 141.9193 | 1803 | 0.01743 | 1.5687 | 1726 | 6.17 | 471
8422 | FROGTOWN 1702739858 | 163451702 | FROGTOWN 1702 | 739858 | FALSE | 8002.9028 | 7850.7225 | 4.8793 | 46 | 0.00010369 | 1557 | 204.17 | 1632 | 0.017426 | 0.80161 | 1727 |  | 3225
3353 | KANAKA 11011406 | 103221101 | KANAKA 1101 | 1406 | FALSE | 43882.3619 | 43882.3619 | 27.2731 | 204 | 9.5492e-05 | 1742 | 157.7153 | 1755 | 0.017352 | 3.5397 | 1728 | 0.18 | 1217
10623 | MORGAN HILL 2111477914 | 83242111 | MORGAN HILL 2111 | 477914 | TRUE | 388.2883 | 307.8291 | 0.19132 | 3 | 0.00012285 | 1135 | 285.164 | 1467 | 0.017329 | 0.051987 | 1729 |  | 3582
1703 | SAN LUIS OBISPO 1105796050 | 182631105 | SAN LUIS OBISPO 1105 | 796050 | TRUE | 5067.2794 | 383.7484 | 0.2385 | 45 | 4.1549e-05 | 3233 | 109.4022 | 1911 | 0.017291 | 0.7781 | 1730 |  | 2738
2587 | MENLO 11031721 | 24131103 | MENLO 1103 | 1721 | FALSE | 10927.2973 | 10927.2973 | 6.7914 | 52 | 0.0001634 | 607 | 107.9769 | 1918 | 0.01726 | 0.89751 | 1731 | 0.12 | 1367
5617 | MIRABEL 1101298 | 42091101 | MIRABEL 1101 | 298 | FALSE | 20337.8041 | 20253.8323 | 12.5878 | 123 | 0.00016852 | 572 | 115.628 | 1892 | 0.017238 | 2.1202 | 1732 | 85.76 | 39
183 | CLEAR LAKE 110192870 | 42141101 | CLEAR LAKE 1101 | 92870 | TRUE | 25931.8169 | 185.9475 | 0.11557 | 187 | 6.3919e-05 | 2649 | 163.1162 | 1739 | 0.017207 | 3.2176 | 1733 | 2.3 | 615
5761 | SAN LUIS OBISPO 1102597518 | 182631102 | SAN LUIS OBISPO 1102 | 597518 | TRUE | 2581.15 | 65.1647 | 0.0405 | 30 | 4.6337e-05 | 3129 | 233.218 | 1579 | 0.017175 | 0.51524 | 1734 | 0.07 | 1768
694 | PIT NO 1 11013312 | 103721101 | PIT NO 1 1101 | 3312 | FALSE | 14682.6253 | 12944.3529 | 8.045 | 82 | 3.1897e-05 | 3403 | 501.3484 | 1197 | 0.017169 | 1.4079 | 1735 | 0.05 | 1934
6571 | MC ARTHUR 11011488 | 103491101 | MC ARTHUR 1101 | 1488 | FALSE | 53867.328 | 3970.6557 | 2.4678 | 217 | 3.7897e-05 | 3301 | 226.8447 | 1594 | 0.01714 | 3.7195 | 1736 | 0.01 | 2597
7993 | STILLWATER 1101CB | 103561101 | STILLWATER 1101 | CB | FALSE | 6895.2449 | 6754.5413 | 4.198 | 47 | 0.00021084 | 355 | 102.4575 | 1940 | 0.017137 | 0.80543 | 1737 | 0.07 | 1698
3453 | LOS GATOS 110760114 | 82021107 | LOS GATOS 1107 | 60114 | FALSE | 39130.9882 | 39130.9882 | 24.3201 | 220 | 0.00014614 | 787 | 173.2936 | 1702 | 0.016971 | 3.7337 | 1738 | 112.13 | 13
3503 | CLAYTON 2215184604 | 12022215 | CLAYTON 2215 | 184604 | FALSE | 16467.2376 | 3361.2922 | 2.0891 | 106 | 3.7123e-05 | 3311 | 169.9457 | 1716 | 0.016935 | 1.7951 | 1739 |  | 2831
5231 | BURNEY 1101CB | 103311101 | BURNEY 1101 | CB | FALSE | 3204.0009 | 1997.9569 | 1.2417 | 29 | 5.2977e-05 | 2969 | 262.0724 | 1517 | 0.016895 | 0.48997 | 1740 | 0.03 | 2250
5033 | ALTO 11243121 | 42031124 | ALTO 1124 | 3121 | FALSE | 4501.3904 | 4501.3904 | 2.7976 | 36 | 0.0001378 | 897 | 129.4168 | 1846 | 0.016885 | 0.60788 | 1741 | 54.14 | 108
4749 | FRUITLAND 11418860 | 192311141 | FRUITLAND 1141 | 8860 | FALSE | 6108.7785 | 3211.911 | 1.9962 | 34 | 0.0001502 | 733 | 173.1129 | 1705 | 0.016867 | 0.57347 | 1742 | 0.03 | 2306
8284 | FRENCH GULCH 11011464 | 103381101 | FRENCH GULCH 1101 | 1464 | FALSE | 1371.4854 | 1371.4854 | 0.85238 | 10 | 0.00011205 | 1368 | 126.5814 | 1854 | 0.01686 | 0.1686 | 1743 | 0.09 | 1538
10232 | TIGER CREEK 0201CB | 161380201 | TIGER CREEK 0201 | CB | FALSE | 6022.6718 | 6022.6718 | 3.7431 | 20 | 0.00011138 | 1387 | 174.7898 | 1698 | 0.016801 | 0.33603 | 1744 | 22.21 | 295
5809 | TEMPLETON 2110N32 | 183052110 | TEMPLETON 2110 | N32 | FALSE | 47644.4105 | 47470.9597 | 29.5034 | 251 | 5.7034e-05 | 2860 | 298.1993 | 1451 | 0.016765 | 4.208 | 1745 | 0.14 | 1326
7289 | PLACERVILLE 111019582 | 153081110 | PLACERVILLE 1110 | 19582 | FALSE | 11698.5344 | 11698.5344 | 7.2707 | 80 | 0.0001731 | 541 | 110.8991 | 1908 | 0.016762 | 1.341 | 1746 | 0.2 | 1168
9046 | OTTER 11022166 | 182941102 | OTTER 1102 | 2166 | FALSE | 6559.0006 | 6559.0006 | 4.0764 | 41 | 0.00012787 | 1051 | 196.1831 | 1652 | 0.016743 | 0.68648 | 1747 | 0.04 | 2069
3955 | GRAYS FLAT 0401CB | 102530401 | GRAYS FLAT 0401 | CB | FALSE | 17261.1138 | 17261.1138 | 10.7279 | 77 | 6.6357e-05 | 2581 | 354.4682 | 1366 | 0.016728 | 1.2881 | 1748 | 0.09 | 1562
4383 | FRUITLAND 114195324 | 192311141 | FRUITLAND 1141 | 95324 | FALSE | 10430.483 | 10430.483 | 6.4826 | 40 | 0.00024711 | 226 | 97.4816 | 1970 | 0.016671 | 0.66685 | 1749 | 0.05 | 1990
9718 | GARBERVILLE 1101323694 | 192221101 | GARBERVILLE 1101 | 323694 | FALSE | 10298.1869 | 10298.1869 | 6.4004 | 17 | 0.00023892 | 250 | 89.5148 | 2002 | 0.016661 | 0.28324 | 1750 |  | 3406
7551 | GARBERVILLE 1101438596 | 192221101 | GARBERVILLE 1101 | 438596 | FALSE | 17736.2716 | 17736.2716 | 11.0232 | 69 | 0.00028911 | 142 | 66.1845 | 2114 | 0.016624 | 1.1471 | 1751 |  | 3135
9937 | OTTER 11022002 | 182941102 | OTTER 1102 | 2002 | FALSE | 4546.6103 | 4546.6103 | 2.8257 | 27 | 9.936e-05 | 1659 | 177.0336 | 1690 | 0.01654 | 0.44657 | 1752 | 0.03 | 2271
5432 | ALLEGHANY 1101804 | 152101101 | ALLEGHANY 1101 | 804 | FALSE | 35223.4878 | 35223.4878 | 21.8915 | 163 | 9.1106e-05 | 1878 | 209.4933 | 1620 | 0.016525 | 2.6936 | 1753 | 22.85 | 291
6356 | NORTH BRANCH 110113496 | 163231101 | NORTH BRANCH 1101 | 13496 | FALSE | 8111.7845 | 3211.8845 | 1.9962 | 58 | 8.2907e-05 | 2132 | 168.1169 | 1725 | 0.016506 | 0.95734 | 1754 | 0.04 | 2107
249 | RINCON 1103CB | 43321103 | RINCON 1103 | CB | FALSE | 6066.7415 | 3931.2505 | 2.4433 | 41 | 0.00016438 | 593 | 84.7695 | 2033 | 0.016461 | 0.67489 | 1755 | 3.87 | 532
1025 | MARIPOSA 2101439030 | 254452101 | MARIPOSA 2101 | 439030 | FALSE | 31570.1115 | 31570.1115 | 19.621 | 200 | 4.6813e-05 | 3117 | 247.3908 | 1548 | 0.016434 | 3.2868 | 1756 | 0.34 | 978
8791 | GLENN 11012012 | 102601101 | GLENN 1101 | 2012 | FALSE | 48303.6952 | 3708.2991 | 2.3047 | 73 | 4.249e-05 | 3218 | 610.7432 | 1094 | 0.016401 | 1.1972 | 1757 | 0.01 | 2617
10780 | CALPINE 1144962 | 48011144 | CALPINE 1144 | 962 | FALSE | 6465.1165 | 6465.1165 | 4.0181 | 13 | 0.00010277 | 1576 | 122.9227 | 1861 | 0.01639 | 0.21307 | 1758 | 8.51 | 424
715 | ALTO 1124430 | 42031124 | ALTO 1124 | 430 | FALSE | 11355.5979 | 11355.5979 | 7.0575 | 92 | 0.00013784 | 896 | 143.4477 | 1796 | 0.016311 | 1.5006 | 1759 | 1.14 | 709
9633 | MONTE RIO 11131067 | 42811113 | MONTE RIO 1113 | 1067 | FALSE | 1306.3843 | 1306.3843 | 0.81192 | 11 | 0.00037762 | 75 | 25.9963 | 2377 | 0.016 | 0.176 | 1760 | 0.39 | 956
1412 | PLACERVILLE 1109CB | 153081109 | PLACERVILLE 1109 | CB | FALSE | 17781.8863 | 17449.8742 | 10.8452 | 133 | 0.00028585 | 146 | 98.8838 | 1960 | 0.015996 | 2.1275 | 1761 | 0.03 | 2400
8245 | BEAR VALLEY 210513430 | 252192105 | BEAR VALLEY 2105 | 13430 | FALSE | 21106.6036 | 21106.6036 | 13.1178 | 129 | 3.9032e-05 | 3286 | 375.4366 | 1329 | 0.015945 | 2.057 | 1762 | 23.77 | 282
8966 | MORAGA 1101772781 | 13801101 | MORAGA 1101 | 772781 | FALSE | 2316.7745 | 2316.7745 | 1.4399 | 12 | 0.00017201 | 551 | 85.3434 | 2027 | 0.015766 | 0.1892 | 1763 |  | 3286
3619 | PINE GROVE 11013166 | 163751101 | PINE GROVE 1101 | 3166 | FALSE | 19778.1528 | 19778.1528 | 12.2922 | 147 | 0.00014138 | 848 | 96.7473 | 1974 | 0.015763 | 2.3172 | 1764 | 0.13 | 1348
4486 | WEST POINT 1101CB | 163201101 | WEST POINT 1101 | CB | FALSE | 7713.2869 | 7713.2869 | 4.7938 | 20 | 0.0002169 | 332 | 123.6935 | 1859 | 0.015736 | 0.31472 | 1765 | 0.28 | 1044
3894 | BONNIE NOOK 110186696 | 152301101 | BONNIE NOOK 1101 | 86696 | FALSE | 15512.3886 | 15512.3886 | 9.641 | 86 | 0.00022753 | 293 | 118.1033 | 1879 | 0.015606 | 1.3421 | 1766 | 11.17 | 386
1913 | OLEMA 1101416 | 42291101 | OLEMA 1101 | 416 | FALSE | 26082.6279 | 26031.4486 | 16.1787 | 79 | 0.00016777 | 576 | 81.2878 | 2042 | 0.015542 | 1.2278 | 1767 | 0.36 | 968
2787 | PINE GROVE 11013170 | 163751101 | PINE GROVE 1101 | 3170 | FALSE | 64049.8846 | 64049.8846 | 39.8073 | 445 | 0.00014644 | 781 | 151.3568 | 1773 | 0.015534 | 6.9125 | 1768 | 0.47 | 907
8370 | SWIFT 2110XR332 | 83392110 | SWIFT 2110 | XR332 | FALSE | 29699.1922 | 29699.1922 | 18.4582 | 83 | 7.378e-05 | 2368 | 296.6239 | 1452 | 0.015532 | 1.2892 | 1769 | 0.12 | 1374
6569 | CURTIS 17058170 | 163351705 | CURTIS 1705 | 8170 | FALSE | 12697.6373 | 12388.5528 | 7.6995 | 109 | 0.00012036 | 1178 | 138.0395 | 1818 | 0.015509 | 1.6904 | 1770 | 0.24 | 1094
9835 | SPRING GAP 1702CB | 162831702 | SPRING GAP 1702 | CB | FALSE | 11971.7401 | 11971.7401 | 7.4405 | 18 | 8.5097e-05 | 2056 | 173.0854 | 1706 | 0.015422 | 0.27759 | 1771 | 0.15 | 1279
1693 | BUCKS CREEK 1103338520 | 102211103 | BUCKS CREEK 1103 | 338520 | FALSE | 12890.8329 | 12653.3631 | 7.8641 | 87 | 0.00011206 | 1367 | 151.4662 | 1772 | 0.015412 | 1.3409 | 1772 |  | 2737
4370 | OREGON TRAIL 11021584 | 103521102 | OREGON TRAIL 1102 | 1584 | FALSE | 20998.6153 | 20998.6153 | 13.0507 | 136 | 0.00015385 | 710 | 117.4189 | 1885 | 0.015387 | 2.0926 | 1773 | 0.14 | 1331
6223 | MOLINO 1101152 | 42571101 | MOLINO 1101 | 152 | FALSE | 16493.2298 | 2668.6977 | 1.6586 | 125 | 0.0001196 | 1193 | 103.0488 | 1937 | 0.015258 | 1.9072 | 1774 | 2.09 | 621
991 | PEORIA 170413494 | 163781704 | PEORIA 1704 | 13494 | FALSE | 12093.2449 | 4454.735 | 2.7686 | 93 | 8.9665e-05 | 1924 | 170.6202 | 1712 | 0.015212 | 1.4148 | 1775 | 2.55 | 598
10392 | VINEYARD 2108383748 | 14502108 | VINEYARD 2108 | 383748 | TRUE | 582.318 | 582.318 | 0.36191 | 4 | 0.00011476 | 1303 | 237.7564 | 1575 | 0.015207 | 0.060827 | 1776 |  | 3542
5782 | GARBERVILLE 11026084 | 192221102 | GARBERVILLE 1102 | 6084 | FALSE | 24635.3535 | 24635.3535 | 15.311 | 120 | 0.00027675 | 166 | 46.9926 | 2233 | 0.015158 | 1.8189 | 1777 | 0.26 | 1064
8670 | COTATI 1102462 | 42271102 | COTATI 1102 | 462 | FALSE | 6310.2369 | 4550.7014 | 2.8283 | 40 | 9.8301e-05 | 1683 | 125.2992 | 1858 | 0.015132 | 0.6053 | 1778 | 0.04 | 2104
5839 | SOLEDAD 21027048 | 182052102 | SOLEDAD 2102 | 7048 | FALSE | 47036.8755 | 18663.2877 | 11.5993 | 173 | 4.4641e-05 | 3172 | 271.6147 | 1491 | 0.015069 | 2.607 | 1779 | 0.05 | 2050
5090 | BRIDGEVILLE 1102CB | 192461102 | BRIDGEVILLE 1102 | CB | FALSE | 19625.3536 | 4723.1827 | 2.9355 | 52 | 0.00018739 | 458 | 86.4729 | 2019 | 0.015061 | 0.78316 | 1780 | 0 | 2627
10131 | CMC 1101CB | 183111101 | CMC 1101 | CB | FALSE | 3286.0633 | 3286.0633 | 2.0423 | 16 | 7.411e-05 | 2353 | 272.3255 | 1488 | 0.014989 | 0.23983 | 1781 | 0.06 | 1879
4953 | FRENCH GULCH 11021462 | 103381102 | FRENCH GULCH 1102 | 1462 | FALSE | 16147.0874 | 16116.0676 | 10.0162 | 51 | 0.00019151 | 435 | 137.3214 | 1821 | 0.01495 | 0.76245 | 1782 | 0.07 | 1710
8365 | GRASS VALLEY 110358498 | 152031103 | GRASS VALLEY 1103 | 58498 | FALSE | 3648.0777 | 1920.6561 | 1.1937 | 34 | 0.00025665 | 200 | 43.134 | 2259 | 0.01494 | 0.50797 | 1783 | 0.03 | 2375
4523 | TIDEWATER 210665866 | 14652106 | TIDEWATER 2106 | 65866 | FALSE | 13028.5461 | 5501.1432 | 3.419 | 65 | 4.6622e-05 | 3122 | 158.5163 | 1752 | 0.014918 | 0.9697 | 1784 | 0.04 | 2201
7430 | FOOTHILL 1101549904 | 182951101 | FOOTHILL 1101 | 549904 | TRUE | 8119.1519 | 250.4434 | 0.15565 | 54 | 6.4657e-05 | 2616 | 224.282 | 1596 | 0.014902 | 0.80473 | 1785 | 1.15 | 708
10743 | ANDERSON 1101909424 | 103261101 | ANDERSON 1101 | 909424 | TRUE | 642.3156 | 642.3156 | 0.3992 | 8 | 0.00010292 | 1571 | 136.9205 | 1825 | 0.014888 | 0.1191 | 1786 |  | 3602
6685 | OCEANO 1102749231 | 182601102 | OCEANO 1102 | 749231 | FALSE | 18200.1936 | 8940.1081 | 5.5563 | 141 | 6.0256e-05 | 2765 | 210.5727 | 1619 | 0.014847 | 2.0934 | 1787 |  | 3055
2541 | BRUNSWICK 110651486 | 152481106 | BRUNSWICK 1106 | 51486 | FALSE | 91205.7549 | 91205.7549 | 56.6847 | 656 | 0.00011965 | 1191 | 123.462 | 1860 | 0.014797 | 9.7068 | 1788 | 90.93 | 31
7750 | BRUNSWICK 110765574 | 152481107 | BRUNSWICK 1107 | 65574 | TRUE | 2814.0897 | 939.5268 | 0.58392 | 23 | 0.00030901 | 119 | 33.131 | 2321 | 0.014793 | 0.34024 | 1789 | 0.01 | 2582
5279 | MC ARTHUR 110137344 | 103491101 | MC ARTHUR 1101 | 37344 | TRUE | 14261.5059 | 181.3406 | 0.1127 | 75 | 2.2098e-05 | 3519 | 310.2738 | 1432 | 0.014768 | 1.1076 | 1790 | 0.01 | 2575
7132 | ANTLER 11011612 | 103271101 | ANTLER 1101 | 1612 | FALSE | 14766.2971 | 14766.2971 | 9.1773 | 86 | 0.00012715 | 1062 | 147.1224 | 1785 | 0.014748 | 1.2683 | 1791 | 0.03 | 2352
3386 | NEWBURG 1132665674 | 192151132 | NEWBURG 1132 | 665674 | TRUE | 2469.7606 | 698.7983 | 0.43431 | 20 | 0.00016815 | 574 | 82.7929 | 2037 | 0.014722 | 0.29443 | 1792 |  | 2823
7872 | PIT NO 1 110170952 | 103721101 | PIT NO 1 1101 | 70952 | FALSE | 2749.7949 | 2724.6488 | 1.6934 | 29 | 3.988e-05 | 3272 | 320.7855 | 1414 | 0.014692 | 0.42606 | 1793 | 0.06 | 1812
5114 | DUNBAR 110147964 | 43071101 | DUNBAR 1101 | 47964 | FALSE | 12397.0354 | 10475.6408 | 6.5107 | 68 | 0.00011035 | 1405 | 129.5748 | 1845 | 0.014662 | 0.99704 | 1794 | 0.39 | 958
7691 | POINT ARENA 110198224 | 43381101 | POINT ARENA 1101 | 98224 | FALSE | 3847.8762 | 3847.8762 | 2.3915 | 23 | 7.8885e-05 | 2238 | 166.5531 | 1730 | 0.014654 | 0.33704 | 1795 |  | 3151
2530 | BRUNSWICK 111061602 | 152481110 | BRUNSWICK 1110 | 61602 | FALSE | 17974.447 | 15796.3436 | 9.8175 | 137 | 0.00027732 | 164 | 142.021 | 1802 | 0.014648 | 2.0068 | 1796 | 0.06 | 1802
7167 | FRENCH GULCH 11012905 | 103381101 | FRENCH GULCH 1101 | 2905 | FALSE | 15594.3492 | 15594.3492 | 9.692 | 83 | 0.00011324 | 1339 | 142.3421 | 1801 | 0.014648 | 1.2158 | 1797 | 0.04 | 2182
4457 | HIGGINS 11041006 | 152691104 | HIGGINS 1104 | 1006 | FALSE | 32324.6992 | 17529.4826 | 10.8946 | 266 | 0.00017105 | 556 | 184.0652 | 1676 | 0.014639 | 3.8939 | 1798 | 0.05 | 1920
7710 | CARLOTTA 11214045 | 192291121 | CARLOTTA 1121 | 4045 | TRUE | 3179.9108 | 576.108 | 0.35805 | 18 | 0.00013215 | 979 | 114.5305 | 1897 | 0.014618 | 0.26312 | 1799 | 0.03 | 2324
9405 | SILVERADO 2105861266 | 43432105 | SILVERADO 2105 | 861266 | FALSE | 3852.0148 | 2503.894 | 1.5562 | 31 | 0.00018468 | 477 | 101.2826 | 1949 | 0.014616 | 0.45311 | 1800 |  | 3353
463 | WEIMAR 11012084 | 152491101 | WEIMAR 1101 | 2084 | FALSE | 29723.3403 | 29723.3403 | 18.4732 | 219 | 0.00012877 | 1034 | 131.3983 | 1843 | 0.014579 | 3.1928 | 1801 | 0.11 | 1414
3551 | WILLOW CREEK 11014904 | 192171101 | WILLOW CREEK 1101 | 4904 | FALSE | 29337.0631 | 29337.0631 | 18.2331 | 121 | 0.00023865 | 252 | 61.1434 | 2146 | 0.014552 | 1.7608 | 1802 | 0.44 | 925
6996 | KONOCTI 1102714370 | 43311102 | KONOCTI 1102 | 714370 | FALSE | 4274.3031 | 3423.0115 | 2.1274 | 28 | 8.0252e-05 | 2198 | 368.3867 | 1342 | 0.014533 | 0.40694 | 1803 |  | 3083
1102 | MC KEE 1107XR010 | 83531107 | MC KEE 1107 | XR010 | FALSE | 22011.3924 | 4483.0278 | 2.7862 | 160 | 7.8729e-05 | 2242 | 168.0653 | 1726 | 0.014407 | 2.3052 | 1804 | 0.05 | 1996
2551 | SOLEDAD 2102823854 | 182052102 | SOLEDAD 2102 | 823854 | FALSE | 6899.0553 | 3307.4207 | 2.0556 | 33 | 3.9519e-05 | 3276 | 363.6041 | 1348 | 0.01437 | 0.47422 | 1805 |  | 2786
2101 | SAN BENITO 210488772 | 182742104 | SAN BENITO 2104 | 88772 | FALSE | 69339.2928 | 39135.7756 | 24.323 | 474 | 6.1067e-05 | 2746 | 187.0188 | 1668 | 0.014358 | 6.8057 | 1806 | 0.2 | 1160
7410 | RIO DELL 11028852 | 192251102 | RIO DELL 1102 | 8852 | FALSE | 7650.5094 | 7473.9899 | 4.6451 | 46 | 0.00028421 | 148 | 54.47 | 2184 | 0.014354 | 0.66027 | 1807 | 0.05 | 1930
5404 | PIT NO 3 21011386 | 103732101 | PIT NO 3 2101 | 1386 | FALSE | 11052.9537 | 11052.9537 | 6.8695 | 47 | 6.3474e-05 | 2661 | 296.3406 | 1453 | 0.014294 | 0.67181 | 1808 | 0.01 | 2619
4186 | MARIPOSA 210110170 | 254452101 | MARIPOSA 2101 | 10170 | FALSE | 26253.3221 | 26253.3221 | 16.3165 | 149 | 4.8216e-05 | 3089 | 256.1773 | 1532 | 0.014293 | 2.1297 | 1809 | 83.16 | 40
7884 | SONOMA 11045661 | 42721104 | SONOMA 1104 | 5661 | FALSE | 8173.4897 | 4658.2663 | 2.8951 | 66 | 8.6364e-05 | 2026 | 169.0465 | 1721 | 0.014289 | 0.94309 | 1810 | 1.66 | 657
967 | DUNBAR 1102903030 | 43071102 | DUNBAR 1102 | 903030 | FALSE | 2341.4408 | 2341.4408 | 1.4552 | 17 | 0.00011468 | 1304 | 137.2956 | 1823 | 0.014278 | 0.24273 | 1811 |  | 2699
3516 | NARROWS 21022718 | 153132102 | NARROWS 2102 | 2718 | TRUE | 11657.4654 | 495.6422 | 0.30804 | 114 | 0.00022728 | 295 | 102.6178 | 1938 | 0.014276 | 1.6275 | 1812 | 0.04 | 2074
5103 | SAN LUIS OBISPO 1107V18 | 182631107 | SAN LUIS OBISPO 1107 | V18 | FALSE | 6444.7052 | 4344.0922 | 2.6999 | 41 | 3.6107e-05 | 3335 | 204.0579 | 1633 | 0.014215 | 0.5828 | 1813 | 0.08 | 1634
177 | KING CITY 11037038 | 182031103 | KING CITY 1103 | 7038 | FALSE | 35749.3707 | 29491.4615 | 18.3291 | 186 | 5.6518e-05 | 2873 | 250.588 | 1538 | 0.014161 | 2.6339 | 1814 | 0.12 | 1392
4472 | WEST POINT 110277204 | 163201102 | WEST POINT 1102 | 77204 | FALSE | 11918.386 | 11918.386 | 7.4073 | 68 | 0.00011817 | 1226 | 128.4194 | 1848 | 0.014094 | 0.95841 | 1815 |  | 2893
8017 | PIT NO 3 2101CB | 103732101 | PIT NO 3 2101 | CB | FALSE | 7292.0294 | 7292.0294 | 4.532 | 7 | 0.00010421 | 1546 | 1059.6264 | 793 | 0.01407 | 0.098493 | 1816 | 0.03 | 2309
4764 | ALLEGHANY 1101CB | 152101101 | ALLEGHANY 1101 | CB | FALSE | 7034.6563 | 7034.6563 | 4.3721 | 40 | 0.00012824 | 1044 | 93.9669 | 1986 | 0.014057 | 0.5623 | 1817 | 38.69 | 195
2091 | STELLING 111060094 | 83481110 | STELLING 1110 | 60094 | FALSE | 15867.8413 | 15867.8413 | 9.8619 | 95 | 0.00016875 | 569 | 93.9049 | 1987 | 0.014041 | 1.3339 | 1818 | 55.68 | 102
2701 | PEORIA 170567898 | 163781705 | PEORIA 1705 | 67898 | FALSE | 9738.6344 | 6917.4777 | 4.2992 | 70 | 0.00010226 | 1597 | 138.197 | 1816 | 0.014037 | 0.98259 | 1819 | 0.06 | 1819
8037 | CAYUCOS 1102613456 | 182551102 | CAYUCOS 1102 | 613456 | FALSE | 38029.4611 | 21637.0644 | 13.4475 | 145 | 5.8725e-05 | 2815 | 256.2574 | 1531 | 0.014028 | 2.0341 | 1820 |  | 3187
4958 | WILLOW CREEK 11035012 | 192171103 | WILLOW CREEK 1103 | 5012 | FALSE | 17904.0624 | 17904.0624 | 11.1274 | 131 | 0.00021567 | 337 | 62.8252 | 2137 | 0.014012 | 1.8356 | 1821 | 0.09 | 1569
1586 | MARTELL 110111244 | 163011101 | MARTELL 1101 | 11244 | FALSE | 34513.2878 | 33294.1457 | 20.6924 | 202 | 0.00014416 | 812 | 70.2755 | 2093 | 0.01399 | 2.826 | 1822 | 0.12 | 1385
8222 | DUNBAR 1102528 | 43071102 | DUNBAR 1102 | 528 | FALSE | 6520.0631 | 5521.142 | 3.4314 | 50 | 8.1342e-05 | 2172 | 173.339 | 1701 | 0.013987 | 0.69934 | 1823 | 0.08 | 1607
6649 | SAN LUIS OBISPO 1108337126 | 182631108 | SAN LUIS OBISPO 1108 | 337126 | FALSE | 3227.6651 | 1128.521 | 0.70138 | 28 | 3.3027e-05 | 3386 | 257.5116 | 1527 | 0.013964 | 0.39101 | 1824 |  | 3051
716 | LAKEVILLE 1102280 | 43371102 | LAKEVILLE 1102 | 280 | FALSE | 10907.0769 | 1106.406 | 0.68764 | 52 | 6.7218e-05 | 2553 | 180.7486 | 1682 | 0.013918 | 0.72376 | 1825 | 0.72 | 800
1162 | DUNBAR 1101302 | 43071101 | DUNBAR 1101 | 302 | FALSE | 16561.5527 | 14104.3324 | 8.7659 | 123 | 0.00011341 | 1335 | 134.8667 | 1832 | 0.013839 | 1.7022 | 1826 | 14.9 | 352
5443 | DUNBAR 1103534 | 43071103 | DUNBAR 1103 | 534 | FALSE | 27841.2407 | 25519.0889 | 15.8602 | 162 | 9.6936e-05 | 1715 | 161.0686 | 1743 | 0.01369 | 2.2178 | 1827 | 36.61 | 206
3834 | STILLWATER 11011320 | 103561101 | STILLWATER 1101 | 1320 | FALSE | 32275.3239 | 31878.2376 | 19.8125 | 179 | 0.00033316 | 101 | 41.1443 | 2271 | 0.013687 | 2.4499 | 1828 | 0.21 | 1149
3066 | SHADY GLEN 1102CB | 152431102 | SHADY GLEN 1102 | CB | FALSE | 34051.8134 | 34051.8134 | 21.1633 | 240 | 0.00019472 | 419 | 88.9032 | 2008 | 0.01359 | 3.2616 | 1829 | 21.63 | 299
8639 | GREEN VALLEY 2101135762 | 83192101 | GREEN VALLEY 2101 | 135762 | FALSE | 4515.3768 | 1189.5286 | 0.7393 | 28 | 9.6391e-05 | 1723 | 173.1219 | 1704 | 0.013539 | 0.3791 | 1830 |  | 3246
1363 | BURNEY 11011322 | 103311101 | BURNEY 1101 | 1322 | FALSE | 30035.9017 | 25851.0688 | 16.0665 | 81 | 4.4702e-05 | 3169 | 378.0361 | 1324 | 0.01351 | 1.0943 | 1831 | 0.03 | 2289
5427 | PENRYN 1103CB | 152561103 | PENRYN 1103 | CB | FALSE | 5107.0559 | 3866.6599 | 2.4031 | 37 | 0.00013283 | 961 | 86.715 | 2017 | 0.013499 | 0.49946 | 1832 | 0.57 | 862
8202 | DUNBAR 1102861496 | 43071102 | DUNBAR 1102 | 861496 | FALSE | 7188.816 | 7188.816 | 4.4679 | 51 | 8.7717e-05 | 1993 | 163.8005 | 1737 | 0.013491 | 0.68805 | 1833 |  | 3201
3776 | ALTO 1125510 | 42031125 | ALTO 1125 | 510 | FALSE | 11861.6385 | 11861.6385 | 7.3721 | 77 | 0.00017549 | 525 | 112.7525 | 1903 | 0.013466 | 1.0369 | 1834 | 48.83 | 124
2524 | PHILO 1102920 | 42601102 | PHILO 1102 | 920 | FALSE | 42024.2659 | 28596.0082 | 17.7725 | 258 | 8.9648e-05 | 1925 | 168.9827 | 1722 | 0.013411 | 3.4601 | 1835 | 0.09 | 1572
8287 | LUCERNE 11034624 | 43351103 | LUCERNE 1103 | 4624 | TRUE | 6101.7647 | 50.6724 | 0.031493 | 42 | 0.00012548 | 1090 | 117.1975 | 1886 | 0.013292 | 0.55825 | 1836 | 0.02 | 2483
3582 | SAN RAFAEL 1108516 | 42011108 | SAN RAFAEL 1108 | 516 | FALSE | 17602.5759 | 17602.5759 | 10.9401 | 135 | 0.00019441 | 420 | 70.1443 | 2094 | 0.013281 | 1.7929 | 1837 | 1.39 | 679
6863 | GREEN VALLEY 2101942143 | 83192101 | GREEN VALLEY 2101 | 942143 | FALSE | 13604.5625 | 8138.4591 | 5.0581 | 74 | 0.00011237 | 1358 | 105.0805 | 1928 | 0.013216 | 0.97798 | 1838 |  | 3068
7880 | POINT ARENA 110183354 | 43381101 | POINT ARENA 1101 | 83354 | FALSE | 8260.8147 | 8260.8147 | 5.1341 | 36 | 5.4313e-05 | 2936 | 210.679 | 1618 | 0.013182 | 0.47457 | 1839 | 0.05 | 1967
2799 | TASSAJARA 211238868 | 14662112 | TASSAJARA 2112 | 38868 | FALSE | 6917.0797 | 3119.1276 | 1.9386 | 61 | 0.00010371 | 1555 | 103.4846 | 1934 | 0.01315 | 0.80215 | 1840 | 0.02 | 2534
10912 | TOCALOMA 0241CB | 43150241 | TOCALOMA 0241 | CB | TRUE | 26.5151 | 26.5151 | 0.016479 | 1 | 7.8863e-05 | 2240 | 166.4117 | 1731 | 0.013124 | 0.013124 | 1841 | 0.04 | 2184
6124 | ANDERSON 1101CB | 103261101 | ANDERSON 1101 | CB | FALSE | 10780.8577 | 1904.2009 | 1.1835 | 85 | 9.0041e-05 | 1911 | 158.1087 | 1753 | 0.013117 | 1.115 | 1842 | 0.05 | 2028
6165 | BRUNSWICK 1105CB | 152481105 | BRUNSWICK 1105 | CB | FALSE | 2138.4101 | 1870.8826 | 1.1628 | 21 | 0.00038645 | 70 | 21.5686 | 2432 | 0.013096 | 0.27501 | 1843 | 20.42 | 305
9119 | SONOMA 1106296492 | 42721106 | SONOMA 1106 | 296492 | FALSE | 3708.9492 | 1270.5979 | 0.78968 | 29 | 7.4532e-05 | 2344 | 198.5181 | 1644 | 0.013092 | 0.37968 | 1844 |  | 3311
3902 | SOLEDAD 2102858388 | 182052102 | SOLEDAD 2102 | 858388 | FALSE | 13234.6519 | 7717.2675 | 4.7963 | 72 | 2.6749e-05 | 3476 | 315.5206 | 1423 | 0.013047 | 0.93942 | 1845 |  | 2860
6187 | JESSUP 11013383 | 103441101 | JESSUP 1101 | 3383 | FALSE | 3031.9376 | 2267.9133 | 1.4095 | 24 | 0.00010952 | 1421 | 99.0724 | 1957 | 0.012944 | 0.31066 | 1846 | 0.05 | 2040
4407 | APPLE HILL 210297982 | 153662102 | APPLE HILL 2102 | 97982 | FALSE | 15545.7354 | 15545.7354 | 9.6617 | 104 | 8.3073e-05 | 2130 | 187.9326 | 1666 | 0.012892 | 1.3407 | 1847 | 33.04 | 223
7041 | JAMESON 1105371694 | 63801105 | JAMESON 1105 | 371694 | TRUE | 6199.8125 | 365.7311 | 0.2273 | 40 | 6.8585e-05 | 2519 | 205.0285 | 1628 | 0.012819 | 0.51277 | 1848 |  | 3089
3447 | WYANDOTTE 11031974 | 102911103 | WYANDOTTE 1103 | 1974 | FALSE | 36068.6353 | 36068.6353 | 22.4168 | 259 | 8.2005e-05 | 2154 | 157.702 | 1756 | 0.012814 | 3.3188 | 1849 | 125.77 | 11
7950 | SONOMA 11033052 | 42721103 | SONOMA 1103 | 3052 | FALSE | 25170.0534 | 20257.093 | 12.5899 | 163 | 9.5443e-05 | 1745 | 138.2678 | 1815 | 0.012795 | 2.0855 | 1850 | 0.66 | 820
5166 | LOS GATOS 1106LB48 | 82021106 | LOS GATOS 1106 | LB48 | FALSE | 23668.374 | 23668.374 | 14.71 | 142 | 0.0001412 | 849 | 89.798 | 2000 | 0.012757 | 1.8115 | 1851 | 0.79 | 776
3055 | LAS POSITAS 2108MR190 | 14402108 | LAS POSITAS 2108 | MR190 | FALSE | 18265.303 | 1336.9264 | 0.83091 | 130 | 5.632e-05 | 2880 | 303.8443 | 1444 | 0.012744 | 1.6567 | 1852 | 0.03 | 2386
8820 | HICKS 2101CB | 83432101 | HICKS 2101 | CB | FALSE | 17493.6949 | 8660.4867 | 5.3825 | 20 | 9.4687e-05 | 1773 | 120.7431 | 1868 | 0.012742 | 0.25483 | 1853 |  | 3269
987 | OAKHURST 110310140 | 254421103 | OAKHURST 1103 | 10140 | FALSE | 26724.0842 | 26724.0842 | 16.6091 | 188 | 8.934e-05 | 1937 | 119.5136 | 1871 | 0.012696 | 2.3869 | 1854 | 1.03 | 724
1124 | COARSEGOLD 210210040 | 254432102 | COARSEGOLD 2102 | 10040 | FALSE | 28379.0201 | 28379.0201 | 17.6377 | 213 | 7.3465e-05 | 2385 | 189.319 | 1665 | 0.01266 | 2.6967 | 1855 | 0.64 | 829
6998 | PUEBLO 1104640 | 43291104 | PUEBLO 1104 | 640 | FALSE | 5054.3067 | 1636.7685 | 1.0173 | 43 | 9.1535e-05 | 1857 | 103.5522 | 1933 | 0.012658 | 0.54429 | 1856 | 0.06 | 1786
2113 | HALSEY 11025739 | 152241102 | HALSEY 1102 | 5739 | FALSE | 10731.8696 | 10731.8696 | 6.6699 | 74 | 0.00014982 | 740 | 107.9805 | 1917 | 0.012582 | 0.93104 | 1857 | 0.05 | 2052
9463 | ATASCADERO 1103A06 | 182541103 | ATASCADERO 1103 | A06 | TRUE | 3295.4951 | 441.6127 | 0.27446 | 27 | 6.1339e-05 | 2740 | 154.3644 | 1764 | 0.012566 | 0.33927 | 1858 | 23.54 | 284
673 | FLINT 110140666 | 152531101 | FLINT 1101 | 40666 | TRUE | 2641.929 | 575.1734 | 0.35747 | 18 | 0.00018607 | 467 | 44.5439 | 2250 | 0.012564 | 0.22615 | 1859 | 0.03 | 2374
6086 | SONOMA 1102113082 | 42721102 | SONOMA 1102 | 113082 | FALSE | 11746.8209 | 9857.3648 | 6.1264 | 75 | 8.9487e-05 | 1932 | 142.6253 | 1799 | 0.012535 | 0.94012 | 1860 |  | 3001
4138 | ORO FINO 11022096 | 103031102 | ORO FINO 1102 | 2096 | FALSE | 22772.919 | 22772.919 | 14.1535 | 129 | 9.8802e-05 | 1675 | 133.1159 | 1838 | 0.012531 | 1.6166 | 1861 | 53.86 | 110
8669 | HORSESHOE 1101663244 | 152571101 | HORSESHOE 1101 | 663244 | TRUE | 704.8457 | 464.3934 | 0.28862 | 6 | 6.412e-05 | 2640 | 270.589 | 1495 | 0.012526 | 0.075153 | 1862 |  | 3250
1101 | HOOPA 110137202 | 192401101 | HOOPA 1101 | 37202 | FALSE | 46485.9706 | 40065.4375 | 24.9008 | 190 | 0.00062222 | 16 | 17.2008 | 2500 | 0.012512 | 2.3773 | 1863 | 0.05 | 1933
1135 | LOS GATOS 1106LB44 | 82021106 | LOS GATOS 1106 | LB44 | FALSE | 31139.8726 | 31139.8726 | 19.3536 | 213 | 0.00014639 | 783 | 100.8516 | 1950 | 0.012499 | 2.6623 | 1864 | 1.29 | 690
5450 | FORESTHILL 11011802 | 152181101 | FORESTHILL 1101 | 1802 | FALSE | 35771.0229 | 35771.0229 | 22.2318 | 259 | 0.00015681 | 674 | 79.811 | 2049 | 0.012496 | 3.2365 | 1865 | 95.5 | 25
5898 | WISE 1102465074 | 152271102 | WISE 1102 | 465074 | FALSE | 7662.1855 | 7662.1855 | 4.7621 | 57 | 0.00013238 | 976 | 95.1304 | 1981 | 0.012495 | 0.7122 | 1866 |  | 2986
7150 | FRUITLAND 1141200856 | 192311141 | FRUITLAND 1141 | 200856 | FALSE | 4144.4334 | 4144.4334 | 2.5758 | 31 | 0.00022223 | 311 | 73.6449 | 2076 | 0.012452 | 0.38602 | 1867 |  | 3102
6814 | SAN ARDO 11017632 | 182191101 | SAN ARDO 1101 | 7632 | FALSE | 13210.2353 | 3566.1023 | 2.2163 | 35 | 2.897e-05 | 3441 | 263.7953 | 1512 | 0.012428 | 0.43499 | 1868 | 0.01 | 2590
4514 | SOLEDAD 2101526864 | 182052101 | SOLEDAD 2101 | 526864 | FALSE | 5659.7355 | 5008.6837 | 3.1129 | 18 | 5.2603e-05 | 2980 | 261.8161 | 1518 | 0.012408 | 0.22335 | 1869 |  | 2901
10395 | CLARKSVILLE 2109649874 | 153612109 | CLARKSVILLE 2109 | 649874 | TRUE | 608.4651 | 608.4651 | 0.37816 | 5 | 0.00011808 | 1227 | 142.79 | 1797 | 0.012324 | 0.061618 | 1870 |  | 3543
368 | POINT MORETTI 11015078 | 82931101 | POINT MORETTI 1101 | 5078 | FALSE | 23873.1972 | 23873.1972 | 14.8373 | 154 | 0.00030756 | 121 | 41.9114 | 2267 | 0.012313 | 1.8962 | 1871 | 17.59 | 330
4025 | CARLOTTA 1121CB | 192291121 | CARLOTTA 1121 | CB | FALSE | 37542.2534 | 4224.1485 | 2.6253 | 255 | 0.00013212 | 981 | 102.3882 | 1942 | 0.012302 | 3.1369 | 1872 | 0.03 | 2408
9319 | GONZALES 11013094 | 182131101 | GONZALES 1101 | 3094 | FALSE | 14546.7613 | 6578.8406 | 4.0888 | 63 | 6.4104e-05 | 2641 | 239.8109 | 1568 | 0.012298 | 0.77477 | 1873 | 0.06 | 1850
5655 | CHALLENGE 1101CB | 103201101 | CHALLENGE 1101 | CB | FALSE | 26652.3351 | 26652.3351 | 16.5645 | 128 | 0.00011861 | 1214 | 102.4016 | 1941 | 0.012215 | 1.5636 | 1874 | 82.53 | 43
9730 | MC KEE 1108976553 | 83531108 | MC KEE 1108 | 976553 | FALSE | 3112.5676 | 1744.6035 | 1.0843 | 20 | 6.6999e-05 | 2557 | 174.5173 | 1699 | 0.012197 | 0.24394 | 1875 |  | 3407
8214 | BRUNSWICK 1106CB | 152481106 | BRUNSWICK 1106 | CB | FALSE | 14175.8367 | 14066.7084 | 8.7425 | 88 | 0.00026507 | 182 | 43.8173 | 2253 | 0.012162 | 1.0703 | 1876 | 27.97 | 254
3779 | NOTRE DAME 1103317782 | 102041103 | NOTRE DAME 1103 | 317782 | TRUE | 6689.8142 | 874.1929 | 0.54331 | 53 | 0.00012534 | 1092 | 127.094 | 1852 | 0.012141 | 0.64349 | 1877 |  | 2852
1366 | HALF MOON BAY 11036014 | 24101103 | HALF MOON BAY 1103 | 6014 | FALSE | 19985.2036 | 9962.9663 | 6.192 | 106 | 7.6568e-05 | 2291 | 149.4232 | 1779 | 0.012138 | 1.2867 | 1878 | 0.02 | 2473
7316 | HOLLISTER 2102676164 | 182492102 | HOLLISTER 2102 | 676164 | TRUE | 4417.8948 | 487.5008 | 0.30298 | 26 | 4.5549e-05 | 3152 | 245.9244 | 1551 | 0.012062 | 0.3136 | 1879 |  | 3115
2140 | BRUNSWICK 1102CB | 152481102 | BRUNSWICK 1102 | CB | FALSE | 10098.7974 | 10098.7974 | 6.2764 | 73 | 0.000256 | 203 | 35.5525 | 2306 | 0.01204 | 0.87889 | 1880 | 11.22 | 385
9978 | FROGTOWN 1702411508 | 163451702 | FROGTOWN 1702 | 411508 | TRUE | 731.3696 | 726.7977 | 0.45171 | 6 | 0.00014592 | 790 | 114.8976 | 1896 | 0.012026 | 0.072157 | 1881 |  | 3464
5364 | FULTON 1104466 | 42561104 | FULTON 1104 | 466 | TRUE | 2421.8686 | 622.9644 | 0.38717 | 21 | 0.00011297 | 1345 | 121.2049 | 1867 | 0.01202 | 0.25243 | 1882 |  | 2947
916 | WYANDOTTE 1105329930 | 102911105 | WYANDOTTE 1105 | 329930 | FALSE | 19740.5748 | 10526.1812 | 6.5421 | 137 | 0.00012563 | 1085 | 89.3966 | 2004 | 0.012012 | 1.6456 | 1883 | 0.03 | 2300
4781 | SONOMA 1105539450 | 42721105 | SONOMA 1105 | 539450 | FALSE | 3896.0108 | 2403.5482 | 1.4938 | 28 | 9.1165e-05 | 1874 | 148.5497 | 1781 | 0.011978 | 0.33537 | 1884 |  | 2917
5493 | SHADY GLEN 11012768 | 152431101 | SHADY GLEN 1101 | 2768 | FALSE | 13051.8561 | 12269.0577 | 7.6253 | 88 | 0.00012814 | 1045 | 88.7266 | 2009 | 0.011963 | 1.0528 | 1885 | 7.41 | 445
8268 | LLAGAS 2101587857 | 83182101 | LLAGAS 2101 | 587857 | TRUE | 3120.9828 | 171.8621 | 0.10681 | 28 | 8.567e-05 | 2038 | 73.8505 | 2073 | 0.011944 | 0.33442 | 1886 |  | 3211
1441 | MIWUK 170111800 | 163661701 | MIWUK 1701 | 11800 | FALSE | 15325.4468 | 15325.4468 | 9.5248 | 116 | 9.1188e-05 | 1873 | 242.093 | 1561 | 0.011866 | 1.3764 | 1887 | 49.43 | 123
2749 | ELK 1101900 | 42981101 | ELK 1101 | 900 | FALSE | 34419.9463 | 14125.5477 | 8.7791 | 185 | 5.5462e-05 | 2901 | 228.3452 | 1591 | 0.011859 | 2.1939 | 1888 | 0.01 | 2598
1288 | CALAVERAS CEMENT 11012646 | 162211101 | CALAVERAS CEMENT 1101 | 2646 | FALSE | 28413.9838 | 28413.9838 | 17.6594 | 149 | 0.00010253 | 1586 | 176.2359 | 1694 | 0.01184 | 1.7642 | 1889 |  | 2720
8429 | FOOTHILL 1101386844 | 182951101 | FOOTHILL 1101 | 386844 | TRUE | 2561.2262 | 615.6019 | 0.3826 | 19 | 4.5617e-05 | 3150 | 232.4795 | 1583 | 0.01183 | 0.22478 | 1890 |  | 3226
6057 | LLAGAS 2101XR264 | 83182101 | LLAGAS 2101 | XR264 | TRUE | 33068.0694 | 0 | 0 | 258 | 7.958e-05 | 2219 | 168.5722 | 1723 | 0.011726 | 3.0254 | 1891 | 0.77 | 783
5358 | UKIAH 1113968652 | 42771113 | UKIAH 1113 | 968652 | FALSE | 3017.7923 | 1606.1834 | 0.99825 | 25 | 0.00010466 | 1539 | 114.1474 | 1898 | 0.011684 | 0.2921 | 1892 |  | 2946
9622 | SAN RAFAEL 110863598 | 42011108 | SAN RAFAEL 1108 | 63598 | FALSE | 3076.8023 | 3076.8023 | 1.9122 | 24 | 0.0001935 | 427 | 74.3537 | 2071 | 0.011681 | 0.28035 | 1893 | 50.16 | 120
6523 | ALTO 1124870444 | 42031124 | ALTO 1124 | 870444 | FALSE | 4770.1261 | 4746.504 | 2.95 | 35 | 0.00012787 | 1050 | 122.3071 | 1864 | 0.011666 | 0.40831 | 1894 |  | 3038
4747 | SANTA ROSA A 1104716 | 42151104 | SANTA ROSA A 1104 | 716 | FALSE | 14319.9438 | 14319.9438 | 8.8999 | 109 | 0.00010523 | 1513 | 113.9799 | 1900 | 0.01165 | 1.2698 | 1895 | 14.14 | 357
9188 | HALF MOON BAY 1102350336 | 24101102 | HALF MOON BAY 1102 | 350336 | FALSE | 2699.1632 | 1936.9418 | 1.2038 | 13 | 7.7558e-05 | 2276 | 139.0255 | 1813 | 0.011629 | 0.15117 | 1896 |  | 3323
10068 | SAN LUIS OBISPO 1108809986 | 182631108 | SAN LUIS OBISPO 1108 | 809986 | FALSE | 3460.671 | 1661.0044 | 1.0323 | 18 | 4.7551e-05 | 3100 | 119.23 | 1872 | 0.011626 | 0.20927 | 1897 |  | 3484
3493 | MARTELL 110198374 | 163011101 | MARTELL 1101 | 98374 | FALSE | 6103.4021 | 1330.8093 | 0.8271 | 46 | 0.00011986 | 1189 | 56.1694 | 2175 | 0.011616 | 0.53436 | 1898 | 0.02 | 2442
3767 | HOLLISTER 210491424 | 182492104 | HOLLISTER 2104 | 91424 | TRUE | 14089.3649 | 303.1658 | 0.18842 | 95 | 6.4005e-05 | 2646 | 160.2049 | 1745 | 0.01155 | 1.0973 | 1899 | 0.02 | 2546
7603 | CLOVERDALE 1102262 | 42821102 | CLOVERDALE 1102 | 262 | FALSE | 9547.2777 | 2067.1657 | 1.2848 | 61 | 0.00010047 | 1637 | 112.2285 | 1905 | 0.011548 | 0.70445 | 1900 | 0.05 | 1983
712 | SILVERADO 2105247660 | 43432105 | SILVERADO 2105 | 247660 | FALSE | 5200.0544 | 3858.4886 | 2.3981 | 35 | 8.3565e-05 | 2111 | 144.077 | 1794 | 0.011541 | 0.40392 | 1901 |  | 2689
4631 | BRUNSWICK 11052210 | 152481105 | BRUNSWICK 1105 | 2210 | FALSE | 36938.5346 | 36938.5346 | 22.9574 | 280 | 9.2627e-05 | 1829 | 84.7902 | 2032 | 0.01151 | 3.2229 | 1902 | 105.34 | 19
1236 | OAKHURST 11035480 | 254421103 | OAKHURST 1103 | 5480 | FALSE | 27352.0687 | 27352.0687 | 16.9994 | 180 | 7.0805e-05 | 2447 | 169.2363 | 1720 | 0.011505 | 2.0709 | 1903 | 0.6 | 854
2425 | PIT NO 3 21011360 | 103732101 | PIT NO 3 2101 | 1360 | FALSE | 36445.2787 | 36106.6297 | 22.4404 | 92 | 4.8938e-05 | 3066 | 304.0594 | 1443 | 0.011504 | 1.0584 | 1904 | 0.01 | 2568
9598 | MILPITAS 1109XR044 | 82831109 | MILPITAS 1109 | XR044 | TRUE | 3013.9349 | 677.8018 | 0.42126 | 18 | 0.00010855 | 1434 | 79.5829 | 2050 | 0.011436 | 0.20585 | 1905 | 0.02 | 2555
3999 | CALAVERAS CEMENT 11011419 | 162211101 | CALAVERAS CEMENT 1101 | 1419 | FALSE | 24160.9517 | 24160.9517 | 15.0161 | 130 | 6.2459e-05 | 2706 | 145.1035 | 1792 | 0.011428 | 1.4856 | 1906 | 0.17 | 1249
3421 | HIGGINS 1104324510 | 152691104 | HIGGINS 1104 | 324510 | FALSE | 20073.6016 | 20073.6016 | 12.4758 | 154 | 6.2523e-05 | 2702 | 194.5257 | 1656 | 0.011404 | 1.7562 | 1907 | 0.14 | 1320
6037 | COARSEGOLD 210210050 | 254432102 | COARSEGOLD 2102 | 10050 | FALSE | 11290.6239 | 11290.6239 | 7.0172 | 81 | 9.8289e-05 | 1684 | 101.871 | 1946 | 0.01137 | 0.92095 | 1908 | 0.52 | 888
942 | WEST POINT 110293116 | 163201102 | WEST POINT 1102 | 93116 | FALSE | 68103.7314 | 68103.7314 | 42.3267 | 453 | 9.1189e-05 | 1872 | 118.4962 | 1875 | 0.011348 | 5.1406 | 1909 | 26.17 | 268
1810 | CABRILLO 1104CB | 183101104 | CABRILLO 1104 | CB | FALSE | 27455.7877 | 6641.9361 | 4.128 | 121 | 2.9423e-05 | 3434 | 158.5842 | 1751 | 0.011318 | 1.3695 | 1910 | 0.05 | 2010
1626 | MOLINO 110251788 | 42571102 | MOLINO 1102 | 51788 | FALSE | 20901.6945 | 8188.5748 | 5.0892 | 153 | 0.00012561 | 1087 | 89.1639 | 2005 | 0.011264 | 1.7234 | 1911 | 0.7 | 807
6259 | RISING RIVER 11019032 | 103551101 | RISING RIVER 1101 | 9032 | FALSE | 37853.3581 | 36827.5633 | 22.8885 | 175 | 3.6108e-05 | 3334 | 413.8546 | 1280 | 0.011207 | 1.9611 | 1912 | 0.02 | 2552
1825 | FORT BRAGG A 11014622 | 42761101 | FORT BRAGG A 1101 | 4622 | FALSE | 21650.6648 | 21650.6648 | 13.456 | 109 | 0.00028635 | 145 | 73.5891 | 2077 | 0.011136 | 1.2138 | 1913 | 0.1 | 1454
5920 | CASTRO VALLEY 1110MR243 | 14091110 | CASTRO VALLEY 1110 | MR243 | FALSE | 8929.805 | 8929.805 | 5.5499 | 72 | 8.9046e-05 | 1946 | 128.0484 | 1849 | 0.011084 | 0.79807 | 1914 |  | 2988
3864 | PLACER 1103429574 | 152461103 | PLACER 1103 | 429574 | FALSE | 15346.7415 | 8004.0474 | 4.9745 | 114 | 0.00019074 | 439 | 99.3413 | 1955 | 0.011083 | 1.2634 | 1915 |  | 2857
4013 | LAURELES 1111CB | 182371111 | LAURELES 1111 | CB | FALSE | 13124.836 | 11515.5312 | 7.1569 | 82 | 7.3716e-05 | 2370 | 185.6036 | 1669 | 0.011075 | 0.90815 | 1916 | 0.07 | 1709
9810 | MENLO 11028896 | 24131102 | MENLO 1102 | 8896 | FALSE | 2488.0112 | 1537.9857 | 0.95586 | 14 | 0.00022997 | 285 | 52.1302 | 2200 | 0.011065 | 0.15491 | 1917 | 2.98 | 570
8395 | CARLOTTA 112142896 | 192291121 | CARLOTTA 1121 | 42896 | FALSE | 8829.785 | 3686.5968 | 2.2912 | 71 | 0.00019577 | 414 | 80.3834 | 2046 | 0.011029 | 0.78303 | 1918 | 0.04 | 2101
5390 | SOLEDAD 2102304826 | 182052102 | SOLEDAD 2102 | 304826 | FALSE | 14243.5781 | 8398.3076 | 5.2196 | 61 | 1.8551e-05 | 3558 | 384.6024 | 1312 | 0.010995 | 0.6707 | 1919 |  | 2949
4943 | PINE GROVE 1102CB | 163751102 | PINE GROVE 1102 | CB | FALSE | 17461.9206 | 17461.9206 | 10.8527 | 136 | 0.00014936 | 745 | 159.9625 | 1746 | 0.010952 | 1.4895 | 1920 | 17.74 | 329
2277 | ORO FINO 11022560 | 103031102 | ORO FINO 1102 | 2560 | FALSE | 26913.6157 | 26913.6157 | 16.7269 | 179 | 8.9581e-05 | 1928 | 135.7772 | 1829 | 0.010913 | 1.9534 | 1921 | 75.77 | 57
8219 | CAMPHORA 1101613562 | 182071101 | CAMPHORA 1101 | 613562 | FALSE | 9602.6341 | 5945.3079 | 3.695 | 29 | 4.482e-05 | 3166 | 198.1499 | 1645 | 0.010904 | 0.31622 | 1922 |  | 3204
8001 | MOLINO 1102189602 | 42571102 | MOLINO 1102 | 189602 | FALSE | 1011.2208 | 1011.2208 | 0.62848 | 9 | 0.00010514 | 1518 | 134.7619 | 1833 | 0.010902 | 0.098117 | 1923 |  | 3183
8797 | CAMP EVERS 210533542 | 83622105 | CAMP EVERS 2105 | 33542 | FALSE | 4316.4835 | 4316.4835 | 2.6827 | 39 | 0.00031343 | 114 | 29.934 | 2346 | 0.010901 | 0.42515 | 1924 | 20.17 | 307
6026 | ROSSMOOR 110837848 | 14161108 | ROSSMOOR 1108 | 37848 | FALSE | 9580.5994 | 9580.5994 | 5.9544 | 60 | 7.1725e-05 | 2430 | 176.9482 | 1691 | 0.010901 | 0.65406 | 1925 | 39.39 | 189
9862 | MONTE RIO 11113891 | 42811111 | MONTE RIO 1111 | 3891 | FALSE | 5583.0951 | 5583.0951 | 3.4699 | 23 | 0.0002266 | 300 | 68.3151 | 2101 | 0.010887 | 0.2504 | 1926 | 21.8 | 297
9761 | HALF MOON BAY 1103341542 | 24101103 | HALF MOON BAY 1103 | 341542 | FALSE | 10584.332 | 9768.7602 | 6.0713 | 47 | 8.7167e-05 | 2009 | 161.0484 | 1744 | 0.010885 | 0.5116 | 1927 |  | 3412
6971 | WILLOW CREEK 11037514 | 192171103 | WILLOW CREEK 1103 | 7514 | FALSE | 16121.906 | 14595.7178 | 9.0713 | 118 | 0.00025507 | 206 | 51.2832 | 2206 | 0.010882 | 1.2841 | 1928 | 4.42 | 519
8324 | MONTE RIO 1112999 | 42811112 | MONTE RIO 1112 | 999 | FALSE | 1412.3755 | 1412.3755 | 0.8778 | 7 | 0.00015392 | 709 | 122.3126 | 1863 | 0.010787 | 0.075506 | 1929 | 28.44 | 250
3097 | ATASCADERO 1103492068 | 182541103 | ATASCADERO 1103 | 492068 | FALSE | 13334.8935 | 11954.6281 | 7.4298 | 75 | 6.9325e-05 | 2495 | 169.7517 | 1718 | 0.010772 | 0.80789 | 1930 |  | 2812
1425 | CLAY 110184572 | 163341101 | CLAY 1101 | 84572 | TRUE | 3629.8323 | 844.7995 | 0.52505 | 27 | 6.1461e-05 | 2735 | 146.1205 | 1788 | 0.010769 | 0.29075 | 1931 | 0.05 | 2022
8269 | COTATI 1105893 | 42271105 | COTATI 1105 | 893 | TRUE | 16957.7992 | 312.2303 | 0.19405 | 91 | 8.78e-05 | 1990 | 114.1416 | 1899 | 0.010724 | 0.9759 | 1932 | 0.02 | 2482
1839 | VOLTA 11021650 | 102541102 | VOLTA 1102 | 1650 | FALSE | 34931.9743 | 34931.9743 | 21.7104 | 154 | 4.7419e-05 | 3105 | 252.2302 | 1537 | 0.010701 | 1.6479 | 1933 | 0.12 | 1379
5835 | APPLE HILL 110497086 | 153661104 | APPLE HILL 1104 | 97086 | FALSE | 41345.0987 | 41345.0987 | 25.6961 | 301 | 7.7565e-05 | 2275 | 132.4839 | 1840 | 0.010689 | 3.2174 | 1934 | 48.08 | 132
7014 | ALTO 1122591122 | 42031122 | ALTO 1122 | 591122 | TRUE | 748.6821 | 748.6821 | 0.46531 | 7 | 0.00022033 | 319 | 51.0001 | 2207 | 0.010649 | 0.074542 | 1935 |  | 3085
1545 | MARTELL 110191216 | 163011101 | MARTELL 1101 | 91216 | FALSE | 65291.6361 | 65291.6361 | 40.579 | 380 | 8.9695e-05 | 1922 | 143.7419 | 1795 | 0.010587 | 4.0231 | 1936 | 0.25 | 1085
812 | DUNBAR 1102246 | 43071102 | DUNBAR 1102 | 246 | FALSE | 21497.7557 | 21497.7557 | 13.3609 | 148 | 0.00011216 | 1363 | 98.1055 | 1967 | 0.010561 | 1.563 | 1937 | 6.5 | 466
6481 | DEL MONTE 21043088 | 182222104 | DEL MONTE 2104 | 3088 | FALSE | 24808.0862 | 24808.0862 | 15.4183 | 175 | 7.2041e-05 | 2415 | 135.1128 | 1831 | 0.010503 | 1.8381 | 1938 | 0.12 | 1369
336 | CAMBRIA 1102CB | 182771102 | CAMBRIA 1102 | CB | FALSE | 37414.4172 | 25753.259 | 16.0058 | 153 | 5.557e-05 | 2899 | 155.1527 | 1763 | 0.010468 | 1.6015 | 1939 | 0.06 | 1833
3334 | VOLTA 110297816 | 102541102 | VOLTA 1102 | 97816 | FALSE | 8457.2763 | 8457.2763 | 5.2562 | 50 | 4.697e-05 | 3114 | 169.4239 | 1719 | 0.010402 | 0.52009 | 1940 | 0.19 | 1193
1241 | CALAVERAS CEMENT 110147968 | 162211101 | CALAVERAS CEMENT 1101 | 47968 | FALSE | 65100.4862 | 65100.4862 | 40.4602 | 306 | 5.7195e-05 | 2856 | 229.0575 | 1588 | 0.010385 | 3.1777 | 1941 | 0.12 | 1380
8572 | LOS GATOS 110760024 | 82021107 | LOS GATOS 1107 | 60024 | FALSE | 6398.0407 | 6398.0407 | 3.9764 | 27 | 8.433e-05 | 2081 | 118.0471 | 1880 | 0.010381 | 0.28029 | 1942 | 22.82 | 292
8425 | PINE GROVE 110194936 | 163751101 | PINE GROVE 1101 | 94936 | FALSE | 14750.2856 | 14750.2856 | 9.1674 | 82 | 0.00010473 | 1535 | 117.7375 | 1883 | 0.010365 | 0.84992 | 1943 | 0.07 | 1716
10220 | ALLEGHANY 1101808 | 152101101 | ALLEGHANY 1101 | 808 | FALSE | 9941.3745 | 9941.3745 | 6.1786 | 23 | 8.8814e-05 | 1958 | 107.5525 | 1920 | 0.010361 | 0.23829 | 1944 | 0.23 | 1116
7876 | PUEBLO 2103706399 | 43292103 | PUEBLO 2103 | 706399 | TRUE | 1848.7276 | 537.9717 | 0.33435 | 16 | 4.8672e-05 | 3069 | 204.8708 | 1630 | 0.010338 | 0.1654 | 1945 |  | 3173
1021 | EL DORADO PH 210119752 | 152762101 | EL DORADO PH 2101 | 19752 | FALSE | 58764.7318 | 58764.7318 | 36.5225 | 436 | 0.00017226 | 548 | 104.6256 | 1929 | 0.0103 | 4.4909 | 1946 | 119.92 | 12
5417 | SILVERADO 2105131568 | 43432105 | SILVERADO 2105 | 131568 | FALSE | 7881.7386 | 6658.8017 | 4.1385 | 57 | 0.00013576 | 921 | 77.208 | 2060 | 0.010281 | 0.58604 | 1947 |  | 2951
3018 | LUCERNE 110638632 | 43351106 | LUCERNE 1106 | 38632 | FALSE | 7538.4158 | 7535.3678 | 4.6833 | 58 | 0.00018341 | 485 | 125.725 | 1857 | 0.010245 | 0.59423 | 1948 | 0.22 | 1128
9909 | OLEMA 1101337220 | 42291101 | OLEMA 1101 | 337220 | FALSE | 8725.086 | 7959.8917 | 4.9471 | 28 | 0.00012555 | 1088 | 76.0082 | 2062 | 0.010237 | 0.28665 | 1949 |  | 3451
7162 | BIG BEND 1101CB | 103751101 | BIG BEND 1101 | CB | FALSE | 37377.2089 | 37377.2089 | 23.2301 | 171 | 0.00013678 | 910 | 60.8273 | 2149 | 0.010207 | 1.7454 | 1950 | 66.07 | 74
9067 | PEORIA 170570198 | 163781705 | PEORIA 1705 | 70198 | FALSE | 5102.4847 | 3628.2739 | 2.255 | 36 | 9.8288e-05 | 1685 | 164.1355 | 1736 | 0.010197 | 0.36709 | 1951 | 0.07 | 1763
6816 | REDBUD 1101400 | 43191101 | REDBUD 1101 | 400 | FALSE | 1650.11 | 1410.4889 | 0.87662 | 14 | 7.9738e-05 | 2214 | 97.4469 | 1971 | 0.010195 | 0.14273 | 1952 | 0.05 | 2066
5252 | POINT ARENA 110137426 | 43381101 | POINT ARENA 1101 | 37426 | FALSE | 8142.4343 | 1270.4089 | 0.78956 | 65 | 4.6458e-05 | 3126 | 164.8689 | 1735 | 0.010169 | 0.66101 | 1953 | 0.25 | 1079
7444 | HOLLISTER 21064004 | 182492106 | HOLLISTER 2106 | 4004 | FALSE | 32627.9425 | 14083.7966 | 8.7531 | 180 | 5.3736e-05 | 2948 | 159.4123 | 1748 | 0.010124 | 1.8224 | 1954 | 0.05 | 1947
2021 | WOODACRE 11021280 | 43021102 | WOODACRE 1102 | 1280 | FALSE | 13974.6466 | 13812.836 | 8.5847 | 111 | 0.00015949 | 648 | 83.4065 | 2034 | 0.010109 | 1.1221 | 1955 | 0.14 | 1310
9350 | WEST POINT 1101L3355 | 163201101 | WEST POINT 1101 | L3355 | FALSE | 3618.1853 | 3618.1853 | 2.2487 | 27 | 8.1776e-05 | 2161 | 67.8566 | 2102 | 0.010104 | 0.2728 | 1956 | 44.71 | 155
4549 | ALHAMBRA 110595016 | 14101105 | ALHAMBRA 1105 | 95016 | FALSE | 7771.8455 | 1223.0109 | 0.76011 | 69 | 5.7126e-05 | 2857 | 109.0983 | 1914 | 0.010066 | 0.69458 | 1957 | 0.02 | 2499
5052 | BIG MEADOWS 21012474 | 102812101 | BIG MEADOWS 2101 | 2474 | FALSE | 13467.3498 | 13410.8685 | 8.3349 | 83 | 3.6201e-05 | 3329 | 276.607 | 1482 | 0.010035 | 0.83287 | 1958 | 10.79 | 394
616 | SONOMA 1104414 | 42721104 | SONOMA 1104 | 414 | FALSE | 35132.3675 | 2113.8048 | 1.3137 | 260 | 5.6e-05 | 2889 | 105.7924 | 1925 | 0.009991 | 2.5977 | 1959 | 1.9 | 632
8621 | FELTON 0401CB | 83140401 | FELTON 0401 | CB | FALSE | 4118.8768 | 4062.5857 | 2.5249 | 34 | 0.00043164 | 58 | 21.0417 | 2435 | 0.0099584 | 0.33859 | 1960 | 0.39 | 952
10564 | WISE 110163199 | 152271101 | WISE 1101 | 63199 | TRUE | 1501.4082 | 989.41 | 0.61492 | 8 | 0.00018345 | 483 | 115.9454 | 1891 | 0.0099235 | 0.079388 | 1961 | 0.04 | 2215
6010 | MORGAN HILL 2111XR292 | 83242111 | MORGAN HILL 2111 | XR292 | FALSE | 19536.8147 | 17975.9221 | 11.1721 | 130 | 6.4726e-05 | 2615 | 181.5173 | 1680 | 0.0098996 | 1.287 | 1962 | 0.15 | 1292
222 | DUNBAR 1102CB | 43071102 | DUNBAR 1102 | CB | FALSE | 13834.375 | 12733.914 | 7.9142 | 113 | 0.00013093 | 994 | 85.2135 | 2029 | 0.0098816 | 1.1166 | 1963 | 0.08 | 1671
8045 | PERRY 1101W26 | 183071101 | PERRY 1101 | W26 | FALSE | 4390.419 | 4390.419 | 2.7287 | 18 | 6.7545e-05 | 2549 | 162.1198 | 1741 | 0.0098794 | 0.17783 | 1964 | 0.05 | 1956
7530 | BUCKS CREEK 11031131 | 102211103 | BUCKS CREEK 1103 | 1131 | FALSE | 4424.1224 | 4424.1224 | 2.7496 | 33 | 8.1427e-05 | 2171 | 131.8339 | 1842 | 0.0098607 | 0.3254 | 1965 | 3.76 | 535
7965 | RINCON 1103568 | 43321103 | RINCON 1103 | 568 | FALSE | 20285.8832 | 20285.8832 | 12.6078 | 129 | 0.00011941 | 1198 | 98.3927 | 1966 | 0.0098399 | 1.2694 | 1966 | 40.01 | 186
7623 | PANOCHE 11034008 | 253671103 | PANOCHE 1103 | 4008 | FALSE | 56919.5652 | 56919.5652 | 35.3757 | 138 | 4.9605e-05 | 3045 | 221.1468 | 1603 | 0.0097859 | 1.3505 | 1967 | 0.04 | 2151
1557 | WILLOW CREEK 11015002 | 192171101 | WILLOW CREEK 1101 | 5002 | FALSE | 22234.4783 | 21939.7249 | 13.6356 | 161 | 0.00029646 | 133 | 37.2556 | 2295 | 0.0097721 | 1.5733 | 1968 | 18.45 | 322
2260 | EL DORADO PH 210152456 | 152762101 | EL DORADO PH 2101 | 52456 | FALSE | 16414.576 | 16414.576 | 10.2017 | 96 | 0.00013704 | 907 | 96.4288 | 1977 | 0.0097493 | 0.93593 | 1969 | 0.06 | 1899
4474 | SPENCE 1104965598 | 182201104 | SPENCE 1104 | 965598 | FALSE | 25622.1563 | 14815.8266 | 9.2081 | 139 | 4.3766e-05 | 3194 | 205.6396 | 1624 | 0.0097442 | 1.3544 | 1970 |  | 2894
9612 | DIAMOND SPRINGS 1107203504 | 152261107 | DIAMOND SPRINGS 1107 | 203504 | TRUE | 514.0425 | 226.4943 | 0.14077 | 4 | 0.00021969 | 325 | 71.3633 | 2088 | 0.0097327 | 0.038931 | 1971 |  | 3389
7259 | SUMMIT 1101742 | 152591101 | SUMMIT 1101 | 742 | FALSE | 2084.4879 | 2084.4879 | 1.2955 | 21 | 0.00010714 | 1469 | 98.5688 | 1964 | 0.009698 | 0.20366 | 1972 | 0.02 | 2502
3486 | GRASS VALLEY 11012208 | 152031101 | GRASS VALLEY 1101 | 2208 | FALSE | 20533.4109 | 18971.647 | 11.791 | 159 | 0.0001453 | 800 | 55.2252 | 2180 | 0.0096885 | 1.5405 | 1973 | 0.15 | 1278
6926 | EL DORADO PH 210113532 | 152762101 | EL DORADO PH 2101 | 13532 | FALSE | 8576.7798 | 8576.7798 | 5.3305 | 46 | 9.988e-05 | 1652 | 99.3016 | 1956 | 0.0096754 | 0.44507 | 1974 | 0 | 2625
4034 | OAKHURST 11035120 | 254421103 | OAKHURST 1103 | 5120 | FALSE | 9912.3897 | 9912.3897 | 6.1606 | 19 | 7.7594e-05 | 2273 | 140.142 | 1809 | 0.0096488 | 0.18333 | 1975 | 15.79 | 345
3547 | RINCON 1101539980 | 43321101 | RINCON 1101 | 539980 | TRUE | 697.2903 | 474.6546 | 0.295 | 4 | 0.0001397 | 874 | 59.5974 | 2157 | 0.0096291 | 0.038517 | 1976 |  | 2837
2441 | SILVERADO 2103617828 | 43432103 | SILVERADO 2103 | 617828 | FALSE | 4970.4215 | 2303.2847 | 1.4315 | 28 | 9.4549e-05 | 1777 | 105.7723 | 1926 | 0.0096279 | 0.26958 | 1977 |  | 2776
5129 | NEWBURG 1131380686 | 192151131 | NEWBURG 1131 | 380686 | FALSE | 4931.6119 | 3014.5331 | 1.8735 | 34 | 0.00017304 | 543 | 55.7388 | 2176 | 0.0095954 | 0.32624 | 1978 |  | 2938
2275 | BUTTE 11051243 | 103081105 | BUTTE 1105 | 1243 | FALSE | 8319.7013 | 8319.7013 | 5.1707 | 50 | 9.2023e-05 | 1845 | 108.0493 | 1916 | 0.0095359 | 0.47679 | 1979 |  | 2768
4445 | PINE GROVE 1102467560 | 163751102 | PINE GROVE 1102 | 467560 | FALSE | 3279.179 | 3279.179 | 2.038 | 27 | 0.00027911 | 159 | 44.0774 | 2252 | 0.009532 | 0.25736 | 1980 |  | 2891
6213 | JESSUP 1103728460 | 103441103 | JESSUP 1103 | 728460 | FALSE | 2312.7118 | 1173.0161 | 0.72903 | 17 | 9.9769e-05 | 1653 | 103.6058 | 1932 | 0.0095302 | 0.16201 | 1981 |  | 3014
3085 | SHINGLE SPRINGS 210819622 | 153652108 | SHINGLE SPRINGS 2108 | 19622 | FALSE | 18790.8494 | 9040.145 | 5.6185 | 165 | 0.00016432 | 596 | 119.9283 | 1869 | 0.0095283 | 1.5722 | 1982 | 0.05 | 1921
9214 | SAN RAFAEL 11081250 | 42011108 | SAN RAFAEL 1108 | 1250 | FALSE | 5741.9405 | 5741.9405 | 3.5686 | 26 | 0.00015475 | 698 | 75.9474 | 2063 | 0.0094996 | 0.24699 | 1983 | 71.72 | 66
10597 | MONTE RIO 11135024 | 42811113 | MONTE RIO 1113 | 5024 | TRUE | 526.6111 | 526.6111 | 0.32729 | 4 | 0.00017161 | 552 | 35.72 | 2305 | 0.0094858 | 0.037943 | 1984 | 11.71 | 383
2882 | WILLOW PASS 2108CB | 13912108 | WILLOW PASS 2108 | CB | TRUE | 14676.6694 | 318.0802 | 0.19769 | 91 | 4.4438e-05 | 3177 | 137.3401 | 1820 | 0.0094639 | 0.86121 | 1985 |  | 2802
5172 | LOS OSITOS 2103220608 | 182082103 | LOS OSITOS 2103 | 220608 | FALSE | 3563.3452 | 1678.7883 | 1.0434 | 10 | 2.1846e-05 | 3522 | 416.4617 | 1275 | 0.009449 | 0.09449 | 1986 |  | 2941
1655 | BRUNSWICK 110750010 | 152481107 | BRUNSWICK 1107 | 50010 | FALSE | 15036.1048 | 9841.1126 | 6.1163 | 117 | 0.00024302 | 239 | 56.6031 | 2173 | 0.0094406 | 1.1046 | 1987 | 18.42 | 323
3494 | WILLITS 110434008 | 42661104 | WILLITS 1104 | 34008 | FALSE | 36886.2403 | 36886.2403 | 22.9249 | 259 | 0.00010265 | 1580 | 90.3162 | 1998 | 0.0094239 | 2.4408 | 1988 | 82.16 | 46
7626 | RESERVATION ROAD 11023030 | 182731102 | RESERVATION ROAD 1102 | 3030 | FALSE | 41820.8596 | 16131.8418 | 10.026 | 186 | 2.9058e-05 | 3440 | 203.8088 | 1634 | 0.0094083 | 1.7499 | 1989 | 0.06 | 1801
10686 | HARTLEY 110158095 | 43211101 | HARTLEY 1101 | 58095 | TRUE | 251.9158 | 251.9158 | 0.15657 | 2 | 0.00013161 | 987 | 71.4359 | 2085 | 0.0094017 | 0.018803 | 1990 | 1.66 | 656
7656 | PHILO 11022600 | 42601102 | PHILO 1102 | 2600 | FALSE | 32204.7216 | 32204.7216 | 20.0154 | 114 | 9.7968e-05 | 1692 | 92.2082 | 1992 | 0.0093006 | 1.0603 | 1991 | 6.68 | 463
7863 | SANTA ROSA A 1104642 | 42151104 | SANTA ROSA A 1104 | 642 | FALSE | 14995.9698 | 14995.9698 | 9.3201 | 127 | 0.00012083 | 1167 | 94.1376 | 1984 | 0.0092364 | 1.173 | 1992 | 16.12 | 341
581 | POINT ARENA 1101474 | 43381101 | POINT ARENA 1101 | 474 | FALSE | 14496.4925 | 14496.4925 | 9.0096 | 77 | 9.2233e-05 | 1837 | 111.515 | 1906 | 0.0092125 | 0.70936 | 1993 | 0.09 | 1510
9791 | LOS OSITOS 2103695270 | 182082103 | LOS OSITOS 2103 | 695270 | FALSE | 1764.2137 | 1116.1992 | 0.69372 | 12 | 6.659e-05 | 2569 | 184.7862 | 1675 | 0.009199 | 0.11039 | 1994 |  | 3425
9383 | CASTRO VALLEY 1110MR525 | 14091110 | CASTRO VALLEY 1110 | MR525 | TRUE | 98.2491 | 17.8831 | 0.011114 | 2 | 6.2244e-05 | 2712 | 142.6154 | 1800 | 0.0091967 | 0.018393 | 1995 |  | 3348
5023 | MC ARTHUR 11021324 | 103491102 | MC ARTHUR 1102 | 1324 | FALSE | 38651.4549 | 1638.5898 | 1.0184 | 169 | 2.205e-05 | 3520 | 325.2371 | 1405 | 0.0091756 | 1.5507 | 1996 | 0.02 | 2488
7662 | CASTRO VALLEY 1110610800 | 14091110 | CASTRO VALLEY 1110 | 610800 | FALSE | 4080.4254 | 3862.9953 | 2.4009 | 33 | 8.5461e-05 | 2042 | 102.3732 | 1943 | 0.0091096 | 0.30062 | 1997 |  | 3147
6717 | NEWBURG 1132910230 | 192151132 | NEWBURG 1132 | 910230 | FALSE | 3166.5297 | 1560.5069 | 0.96986 | 27 | 0.00023935 | 248 | 37.0091 | 2298 | 0.0090947 | 0.24556 | 1998 |  | 3058
10 | KONOCTI 1102532 | 43311102 | KONOCTI 1102 | 532 | FALSE | 15658.0016 | 15658.0016 | 9.7315 | 124 | 0.00024726 | 225 | 48.9408 | 2215 | 0.0090595 | 1.1234 | 1999 | 47.27 | 135
5170 | EL DORADO PH 2102542272 | 152762102 | EL DORADO PH 2102 | 542272 | FALSE | 12585.3616 | 12585.3616 | 7.8219 | 80 | 0.00018486 | 474 | 31.5637 | 2334 | 0.0090446 | 0.72357 | 2000 |  | 2940
8963 | MIRABEL 1101253331 | 42091101 | MIRABEL 1101 | 253331 | TRUE | 639.8394 | 107.6584 | 0.06691 | 5 | 0.0001555 | 688 | 63.3453 | 2134 | 0.0090171 | 0.045085 | 2001 |  | 3284
10053 | ROB ROY 21046577 | 83692104 | ROB ROY 2104 | 6577 | FALSE | 5581.4139 | 5581.4139 | 3.4689 | 33 | 0.00018059 | 509 | 33.2037 | 2318 | 0.0089943 | 0.29681 | 2002 |  | 3482
8505 | NEWBURG 113190242 | 192151131 | NEWBURG 1131 | 90242 | FALSE | 7016.5204 | 6652.6427 | 4.1346 | 51 | 0.00013965 | 876 | 54.8847 | 2183 | 0.0089934 | 0.45866 | 2003 | 0.05 | 1980
283 | SAN RAFAEL 1104802 | 42011104 | SAN RAFAEL 1104 | 802 | FALSE | 20585.105 | 13782.7792 | 8.5661 | 162 | 0.00013761 | 901 | 59.5964 | 2158 | 0.0089568 | 1.451 | 2004 | 0.09 | 1542
9446 | ECHO SUMMIT 1101481660 | 158031101 | ECHO SUMMIT 1101 | 481660 | FALSE | 1777.5904 | 1750.3957 | 1.0879 | 21 | 0.00013748 | 904 | 66.8278 | 2109 | 0.0089565 | 0.18809 | 2005 |  | 3360
1636 | LOS COCHES 1101625902 | 182151101 | LOS COCHES 1101 | 625902 | FALSE | 9066.5477 | 4214.4266 | 2.6193 | 26 | 5.2521e-05 | 2981 | 97.9588 | 1969 | 0.0089147 | 0.23178 | 2006 |  | 2735
8007 | SAN JUSTO 11014002 | 183181101 | SAN JUSTO 1101 | 4002 | FALSE | 30655.7932 | 29553.7891 | 18.3678 | 140 | 4.2612e-05 | 3215 | 236.2342 | 1577 | 0.0088999 | 1.246 | 2007 | 0.18 | 1202
4827 | ATASCADERO 1103A88 | 182541103 | ATASCADERO 1103 | A88 | FALSE | 4298.2003 | 1506.8203 | 0.93649 | 41 | 7.0724e-05 | 2450 | 118.2966 | 1877 | 0.008869 | 0.36363 | 2008 | 0.51 | 891
6300 | DRUM 11011602 | 152321101 | DRUM 1101 | 1602 | FALSE | 26067.9128 | 26067.9128 | 16.2013 | 121 | 7.2028e-05 | 2416 | 103.4039 | 1935 | 0.0088619 | 1.0723 | 2009 | 0.28 | 1033
7254 | ALLEGHANY 1101VR816 | 152101101 | ALLEGHANY 1101 | VR816 | FALSE | 6675.8935 | 6675.8935 | 4.1491 | 49 | 0.00021002 | 359 | 34.0265 | 2312 | 0.0088541 | 0.43385 | 2010 | 78.58 | 51
2986 | PINE GROVE 110235576 | 163751102 | PINE GROVE 1102 | 35576 | FALSE | 12676.983 | 12676.983 | 7.8788 | 77 | 9.958e-05 | 1656 | 90.2081 | 1999 | 0.0088445 | 0.68102 | 2011 | 51.58 | 114
8230 | SAN LUIS OBISPO 1102357407 | 182631102 | SAN LUIS OBISPO 1102 | 357407 | TRUE | 396.3684 | 382.6506 | 0.23782 | 5 | 5.6115e-05 | 2883 | 139.4252 | 1811 | 0.0088377 | 0.044188 | 2012 |  | 3206
1189 | PEORIA 170575274 | 163781705 | PEORIA 1705 | 75274 | TRUE | 5361.6389 | 623.7122 | 0.38764 | 43 | 7.4779e-05 | 2337 | 100.4794 | 1953 | 0.0088331 | 0.37982 | 2013 | 2.09 | 623
299 | MONTE RIO 111164758 | 42811111 | MONTE RIO 1111 | 64758 | FALSE | 16840.1197 | 16840.1197 | 10.4662 | 97 | 0.00025463 | 207 | 41.2688 | 2270 | 0.0087918 | 0.8528 | 2014 | 58.76 | 91
8131 | HARTLEY 1101534548 | 43211101 | HARTLEY 1101 | 534548 | TRUE | 825.2513 | 643.683 | 0.40005 | 7 | 8.8763e-05 | 1960 | 139.419 | 1812 | 0.008746 | 0.061222 | 2015 |  | 3194
3395 | BOLINAS 1101504 | 42261101 | BOLINAS 1101 | 504 | FALSE | 10763.1252 | 10763.1252 | 6.6893 | 53 | 0.00011675 | 1255 | 93.9031 | 1988 | 0.0087025 | 0.46123 | 2016 | 0.26 | 1063
6220 | LAKEVILLE 1102530 | 43371102 | LAKEVILLE 1102 | 530 | TRUE | 7365.5043 | 114.9911 | 0.071467 | 55 | 7.7592e-05 | 2274 | 96.695 | 1976 | 0.0087005 | 0.47853 | 2017 | 0.03 | 2248
8104 | MONTE RIO 111137520 | 42811111 | MONTE RIO 1111 | 37520 | FALSE | 3437.9631 | 3437.9631 | 2.1367 | 20 | 0.0002436 | 236 | 45.2659 | 2244 | 0.0086846 | 0.17369 | 2018 | 30.52 | 237
5024 | MONTE RIO 1113180 | 42811113 | MONTE RIO 1113 | 180 | FALSE | 3158.1165 | 3158.1165 | 1.9628 | 28 | 0.00023287 | 273 | 37.4189 | 2293 | 0.0086779 | 0.24298 | 2019 | 48.66 | 126
2418 | CLEAR LAKE 11011302 | 42141101 | CLEAR LAKE 1101 | 1302 | FALSE | 28390.9957 | 12188.0095 | 7.5749 | 189 | 9.155e-05 | 1856 | 135.9642 | 1826 | 0.0086777 | 1.6401 | 2020 | 0.07 | 1751
6344 | WEST POINT 11021303 | 163201102 | WEST POINT 1102 | 1303 | FALSE | 25207.4138 | 25207.4138 | 15.6665 | 146 | 8.2868e-05 | 2134 | 109.1634 | 1912 | 0.0086648 | 1.2651 | 2021 | 55.45 | 103
147 | SHADY GLEN 11022232 | 152431102 | SHADY GLEN 1102 | 2232 | FALSE | 16843.7265 | 16843.7265 | 10.4684 | 88 | 0.00014558 | 796 | 81.1031 | 2043 | 0.0086414 | 0.76044 | 2022 | 16.24 | 339
8652 | LOYOLA 1102725939 | 82161102 | LOYOLA 1102 | 725939 | TRUE | 1338.4571 | 150.5355 | 0.093558 | 14 | 0.0001664 | 579 | 36.2434 | 2303 | 0.0086108 | 0.12055 | 2023 |  | 3249
10013 | GREEN VALLEY 21016601 | 83192101 | GREEN VALLEY 2101 | 6601 | FALSE | 3063.6094 | 3063.6094 | 1.904 | 19 | 0.00011592 | 1271 | 66.3782 | 2113 | 0.0085862 | 0.16314 | 2024 |  | 3470
3970 | PUEBLO 1105348368 | 43291105 | PUEBLO 1105 | 348368 | FALSE | 14957.0247 | 4473.6471 | 2.7804 | 107 | 6.0549e-05 | 2762 | 137.0477 | 1824 | 0.0085797 | 0.91803 | 2025 |  | 2865
5419 | MIRABEL 11014859 | 42091101 | MIRABEL 1101 | 4859 | FALSE | 3008.5895 | 3008.5895 | 1.8699 | 22 | 0.00015733 | 670 | 65.9715 | 2116 | 0.0085572 | 0.18826 | 2026 | 30.63 | 236
3836 | PURISIMA 1101CB | 182971101 | PURISIMA 1101 | CB | FALSE | 7381.7293 | 5917.6189 | 3.6778 | 32 | 7.2016e-05 | 2418 | 150.0597 | 1776 | 0.0085315 | 0.27301 | 2027 | 0.06 | 1914
589 | EL DORADO PH 21016852 | 152762101 | EL DORADO PH 2101 | 6852 | FALSE | 40624.2727 | 40624.2727 | 25.2481 | 309 | 0.00015417 | 703 | 140.8238 | 1808 | 0.0085289 | 2.6354 | 2028 | 106.87 | 16
7704 | GOLDTREE 1107CB | 182581107 | GOLDTREE 1107 | CB | FALSE | 5578.7405 | 1480.1268 | 0.9199 | 28 | 6.1871e-05 | 2724 | 91.0203 | 1996 | 0.0085282 | 0.23879 | 2029 | 0.25 | 1074
10273 | POINT ARENA 11014923 | 43381101 | POINT ARENA 1101 | 4923 | FALSE | 4611.3164 | 4611.3164 | 2.866 | 12 | 0.00010517 | 1516 | 65.4057 | 2122 | 0.008518 | 0.10222 | 2030 | 0.06 | 1877
327 | CURTIS 170463502 | 163351704 | CURTIS 1704 | 63502 | FALSE | 16836.9835 | 16836.9835 | 10.4643 | 107 | 0.00012514 | 1095 | 60.239 | 2153 | 0.0084952 | 0.90898 | 2031 | 0.16 | 1256
7937 | CLARK ROAD 11022068 | 103091102 | CLARK ROAD 1102 | 2068 | FALSE | 17517.3264 | 17517.3264 | 10.8871 | 90 | 0.00011364 | 1328 | 80.7377 | 2044 | 0.0084897 | 0.76407 | 2032 | 0.32 | 992
4769 | WYANDOTTE 1107CB | 102911107 | WYANDOTTE 1107 | CB | FALSE | 24321.9127 | 2030.3761 | 1.2619 | 199 | 0.00016447 | 591 | 61.5586 | 2143 | 0.0084763 | 1.6868 | 2033 | 0.03 | 2311
7564 | COLUMBIA HILL 11018233 | 152471101 | COLUMBIA HILL 1101 | 8233 | FALSE | 7978.7453 | 7978.7453 | 4.9588 | 51 | 7.9873e-05 | 2208 | 109.5763 | 1910 | 0.008467 | 0.43182 | 2034 | 41.72 | 175
2536 | HALSEY 1101CB | 152241101 | HALSEY 1101 | CB | FALSE | 27644.3487 | 27644.3487 | 17.1811 | 231 | 0.00016053 | 637 | 70.3363 | 2092 | 0.0084422 | 1.9501 | 2035 | 0.21 | 1148
2174 | DIAMOND SPRINGS 1104CB | 152261104 | DIAMOND SPRINGS 1104 | CB | FALSE | 15842.0085 | 9046.8091 | 5.6226 | 127 | 0.0002078 | 373 | 65.6703 | 2119 | 0.008393 | 1.0659 | 2036 | 0.19 | 1172
4975 | EL DORADO PH 210119612 | 152762101 | EL DORADO PH 2101 | 19612 | FALSE | 14689.1647 | 14689.1647 | 9.1294 | 102 | 0.00021799 | 328 | 33.636 | 2313 | 0.0083743 | 0.85418 | 2037 | 36 | 208
7088 | SAUSALITO 11021500 | 42491102 | SAUSALITO 1102 | 1500 | FALSE | 2059.653 | 1869.3575 | 1.1618 | 8 | 8.3383e-05 | 2121 | 83.3451 | 2035 | 0.0083473 | 0.066779 | 2038 | 0.06 | 1818
4510 | CAMP EVERS 210511010 | 83622105 | CAMP EVERS 2105 | 11010 | FALSE | 3501.2634 | 3501.2634 | 2.176 | 26 | 0.00023343 | 269 | 31.1531 | 2340 | 0.0083235 | 0.21641 | 2039 | 12.24 | 375
7509 | WESTLEY 1103237522 | 162671103 | WESTLEY 1103 | 237522 | FALSE | 26805.1596 | 1485.982 | 0.92354 | 39 | 3.422e-05 | 3366 | 404.1911 | 1293 | 0.0082937 | 0.32346 | 2040 |  | 3130
2971 | CASTRO VALLEY 1111MR334 | 14091111 | CASTRO VALLEY 1111 | MR334 | FALSE | 9742.4846 | 9116.5949 | 5.666 | 80 | 8.203e-05 | 2151 | 200.4591 | 1639 | 0.0082358 | 0.65886 | 2041 |  | 2808
143 | RACETRACK 1703CB | 163761703 | RACETRACK 1703 | CB | FALSE | 28877.5917 | 25353.1416 | 15.7571 | 216 | 0.00013825 | 891 | 45.587 | 2242 | 0.008163 | 1.7632 | 2042 | 0.16 | 1262
1117 | MORGAN HILL 2104152774 | 83242104 | MORGAN HILL 2104 | 152774 | FALSE | 12406.0754 | 10319.2603 | 6.4135 | 84 | 6.212e-05 | 2716 | 152.7782 | 1769 | 0.0081314 | 0.68304 | 2043 |  | 2709
3526 | SILVERADO 2103920793 | 43432103 | SILVERADO 2103 | 920793 | FALSE | 12855.6086 | 10473.7039 | 6.5094 | 51 | 8.6884e-05 | 2016 | 85.5215 | 2025 | 0.008033 | 0.40968 | 2044 |  | 2833
7263 | FORESTHILL 11011820 | 152181101 | FORESTHILL 1101 | 1820 | FALSE | 9227.6622 | 9227.6622 | 5.735 | 51 | 7.9052e-05 | 2234 | 127.8002 | 1850 | 0.0080276 | 0.40941 | 2045 | 46.68 | 139
4807 | PLACER 1103238990 | 152461103 | PLACER 1103 | 238990 | TRUE | 9730.7173 | 65.0773 | 0.040446 | 84 | 0.00017934 | 513 | 66.7295 | 2111 | 0.0080184 | 0.67354 | 2046 |  | 2918
7786 | UPPER LAKE 11016663 | 42871101 | UPPER LAKE 1101 | 6663 | FALSE | 3787.49 | 3787.49 | 2.3539 | 17 | 7.5146e-05 | 2328 | 97.3101 | 1972 | 0.0079953 | 0.13592 | 2047 | 1.13 | 713
797 | DUNBAR 1101CB | 43071101 | DUNBAR 1101 | CB | FALSE | 23959.1283 | 5020.5865 | 3.1203 | 191 | 0.00012086 | 1166 | 54.2982 | 2185 | 0.007993 | 1.5267 | 2048 | 0.11 | 1429
1103 | HOOPA 1101CB | 192401101 | HOOPA 1101 | CB | FALSE | 63333.9358 | 37375.4287 | 23.229 | 440 | 0.00026939 | 173 | 30.0518 | 2342 | 0.0079104 | 3.4806 | 2049 | 0.19 | 1174
8668 | BIG BASIN 110211062 | 82841102 | BIG BASIN 1102 | 11062 | FALSE | 21428.2343 | 21428.2343 | 13.3177 | 88 | 0.00013572 | 922 | 71.1136 | 2090 | 0.007899 | 0.69511 | 2050 | 0.25 | 1075
7844 | ELK 11011260 | 42981101 | ELK 1101 | 1260 | FALSE | 25231.41 | 25226.838 | 15.6786 | 120 | 9.4953e-05 | 1767 | 70.6215 | 2091 | 0.0078966 | 0.94759 | 2051 | 0.04 | 2197
2387 | HALSEY 110239104 | 152241102 | HALSEY 1102 | 39104 | FALSE | 49366.035 | 49366.035 | 30.6812 | 346 | 0.00016953 | 566 | 33.5173 | 2314 | 0.007888 | 2.7292 | 2052 | 0.26 | 1066
1085 | MORAGA 1101CB | 13801101 | MORAGA 1101 | CB | FALSE | 14345.0573 | 13611.4014 | 8.4595 | 92 | 0.00011705 | 1247 | 67.2853 | 2106 | 0.0078811 | 0.72506 | 2053 | 0.43 | 926
6726 | MARTELL 110292172 | 163011102 | MARTELL 1102 | 92172 | TRUE | 5246.1471 | 190.7947 | 0.11858 | 45 | 0.00012597 | 1079 | 55.6458 | 2177 | 0.0078638 | 0.35387 | 2054 | 0.61 | 846
1984 | HALF MOON BAY 110369412 | 24101103 | HALF MOON BAY 1103 | 69412 | FALSE | 34124.5253 | 25048.7626 | 15.5679 | 150 | 9.9166e-05 | 1664 | 96.7198 | 1975 | 0.0078448 | 1.1767 | 2055 | 0.06 | 1862
2299 | VINEYARD 2107CB | 14502107 | VINEYARD 2107 | CB | FALSE | 12364.4219 | 3069.8489 | 1.9079 | 111 | 3.2822e-05 | 3389 | 173.8407 | 1700 | 0.0077955 | 0.8653 | 2056 | 0.03 | 2405
9627 | POINT ARENA 11011296 | 43381101 | POINT ARENA 1101 | 1296 | FALSE | 8913.723 | 5630.7668 | 3.4995 | 37 | 6.5385e-05 | 2603 | 134.0606 | 1835 | 0.007772 | 0.28757 | 2057 | 0.02 | 2458
2765 | FORESTHILL 1101CB | 152181101 | FORESTHILL 1101 | CB | FALSE | 14659.7522 | 14659.7522 | 9.1111 | 110 | 0.00023141 | 282 | 46.7348 | 2235 | 0.0077431 | 0.85174 | 2058 | 50.51 | 118
4087 | BURNEY 11011340 | 103311101 | BURNEY 1101 | 1340 | FALSE | 28996.5273 | 28996.5273 | 18.0215 | 144 | 3.4761e-05 | 3354 | 286.6355 | 1466 | 0.0077101 | 1.1103 | 2059 | 0.06 | 1820
8844 | MIDDLETOWN 1101614 | 43141101 | MIDDLETOWN 1101 | 614 | FALSE | 2222.7419 | 2222.7419 | 1.3814 | 18 | 0.00013751 | 902 | 52.9107 | 2196 | 0.0076984 | 0.13857 | 2060 | 47.35 | 134
3083 | MONTE RIO 1113320 | 42811113 | MONTE RIO 1113 | 320 | FALSE | 4467.496 | 4467.496 | 2.7766 | 29 | 0.00021698 | 331 | 31.2121 | 2339 | 0.0076924 | 0.22308 | 2061 | 49.68 | 122
7740 | POINT MORETTI 110136514 | 82931101 | POINT MORETTI 1101 | 36514 | FALSE | 11050.0531 | 11050.0531 | 6.8677 | 64 | 0.00015664 | 677 | 62.082 | 2141 | 0.0076624 | 0.4904 | 2062 | 0.67 | 813
898 | COTATI 11055156 | 42271105 | COTATI 1105 | 5156 | FALSE | 16018.9017 | 7784.4976 | 4.8381 | 114 | 9.9942e-05 | 1647 | 85.2613 | 2028 | 0.0076261 | 0.86938 | 2063 | 0.53 | 881
3027 | PHILO 11021308 | 42601102 | PHILO 1102 | 1308 | FALSE | 51491.5441 | 51491.5441 | 32.0022 | 245 | 8.9849e-05 | 1917 | 98.5183 | 1965 | 0.0076242 | 1.8679 | 2064 | 0.09 | 1559
10504 | KANAKA 11011036 | 103221101 | KANAKA 1101 | 1036 | TRUE | 989.4598 | 989.4598 | 0.61495 | 4 | 6.243e-05 | 2709 | 118.9656 | 1873 | 0.0076073 | 0.030429 | 2065 | 0.09 | 1531
2446 | FOOTHILL 1102V06 | 182951102 | FOOTHILL 1102 | V06 | FALSE | 10508.9376 | 3602.7995 | 2.2392 | 66 | 4.6125e-05 | 3135 | 94.4714 | 1983 | 0.007606 | 0.50199 | 2066 | 0.87 | 757
4588 | COARSEGOLD 21025722 | 254432102 | COARSEGOLD 2102 | 5722 | FALSE | 3182.5999 | 3182.5999 | 1.978 | 23 | 7.5358e-05 | 2325 | 108.5957 | 1915 | 0.0076053 | 0.17492 | 2067 | 0.29 | 1024
8714 | OTTER 1101CB | 182941101 | OTTER 1101 | CB | FALSE | 10759.8557 | 10367.8883 | 6.4437 | 54 | 7.9345e-05 | 2224 | 98.8454 | 1961 | 0.0075954 | 0.41015 | 2068 | 0.46 | 912
9866 | DUNBAR 1101343 | 43071101 | DUNBAR 1101 | 343 | FALSE | 7140.9406 | 7140.9406 | 4.4381 | 39 | 0.0001241 | 1116 | 75.0943 | 2067 | 0.0075606 | 0.29486 | 2069 | 38.93 | 192
723 | BIG BASIN 110296986 | 82841102 | BIG BASIN 1102 | 96986 | FALSE | 9497.5055 | 9497.5055 | 5.9027 | 63 | 0.00018221 | 496 | 38.932 | 2285 | 0.0075562 | 0.47604 | 2070 | 0.41 | 938
5272 | NEWBURG 1133CB | 192151133 | NEWBURG 1133 | CB | FALSE | 14786.8555 | 5089.2485 | 3.163 | 92 | 0.00018939 | 445 | 47.0523 | 2232 | 0.0075338 | 0.69311 | 2071 | 0.06 | 1839
6817 | HALF MOON BAY 1103695411 | 24101103 | HALF MOON BAY 1103 | 695411 | FALSE | 13352.973 | 13352.973 | 8.2989 | 99 | 0.00013199 | 984 | 79.3253 | 2051 | 0.0075292 | 0.74539 | 2072 |  | 3065
9735 | EEL RIVER 1103216324 | 192381103 | EEL RIVER 1103 | 216324 | FALSE | 4626.1816 | 3681.9233 | 2.2883 | 23 | 0.00013316 | 955 | 50.0452 | 2210 | 0.0075204 | 0.17297 | 2073 |  | 3409
803 | DIAMOND SPRINGS 1107CB | 152261107 | DIAMOND SPRINGS 1107 | CB | TRUE | 5946.2245 | 0 | 0 | 51 | 0.00020302 | 386 | 24.2582 | 2398 | 0.0074949 | 0.38224 | 2074 | 0.05 | 1988
2229 | EL DORADO PH 210136764 | 152762101 | EL DORADO PH 2101 | 36764 | FALSE | 7038.6749 | 5034.5882 | 3.129 | 46 | 4.659e-05 | 3123 | 107.3772 | 1922 | 0.0074941 | 0.34473 | 2075 | 0 | 2633
5945 | SANTA ROSA A 1111758024 | 42151111 | SANTA ROSA A 1111 | 758024 | FALSE | 10378.3257 | 7589.8929 | 4.7171 | 72 | 9.0405e-05 | 1901 | 69.6669 | 2097 | 0.007484 | 0.53884 | 2076 |  | 2992
726 | DIAMOND SPRINGS 1106930190 | 152261106 | DIAMOND SPRINGS 1106 | 930190 | FALSE | 30053.7833 | 27579.5424 | 17.1408 | 207 | 0.00014885 | 753 | 53.3783 | 2192 | 0.0074761 | 1.5476 | 2077 |  | 2690
353 | CURTIS 170210940 | 163351702 | CURTIS 1702 | 10940 | FALSE | 17097.711 | 13824.9592 | 8.5923 | 138 | 0.0001288 | 1032 | 78.9158 | 2055 | 0.0073788 | 1.0183 | 2078 | 0.13 | 1356
1231 | RED BLUFF 1103CB | 103541103 | RED BLUFF 1103 | CB | TRUE | 31613.0704 | 164.6636 | 0.10234 | 261 | 5.2389e-05 | 2982 | 125.9834 | 1855 | 0.0073172 | 1.9098 | 2079 |  | 2718
10001 | PANOCHE 11034036 | 253671103 | PANOCHE 1103 | 4036 | FALSE | 40366.1816 | 16000.3845 | 9.9443 | 57 | 4.3272e-05 | 3204 | 184.9055 | 1674 | 0.0073003 | 0.41612 | 2080 | 0.02 | 2455
9426 | GREEN VALLEY 2101380922 | 83192101 | GREEN VALLEY 2101 | 380922 | FALSE | 4341.3947 | 1588.6005 | 0.98732 | 30 | 5.3037e-05 | 2965 | 107.6713 | 1919 | 0.0072901 | 0.2187 | 2081 |  | 3357
1700 | LUCERNE 110676850 | 43351106 | LUCERNE 1106 | 76850 | FALSE | 5941.1146 | 3458.1261 | 2.1492 | 51 | 0.00012907 | 1026 | 65.4632 | 2120 | 0.0072691 | 0.37072 | 2082 | 0.04 | 2220
2002 | HOLLISTER 21054018 | 182492105 | HOLLISTER 2105 | 4018 | FALSE | 85010.3668 | 71470.9964 | 44.4195 | 280 | 6.7671e-05 | 2541 | 115.5373 | 1893 | 0.0072679 | 2.035 | 2083 | 0.08 | 1661
2867 | MONTE RIO 1113346 | 42811113 | MONTE RIO 1113 | 346 | FALSE | 16160.3417 | 16160.3417 | 10.0437 | 101 | 0.00015809 | 662 | 67.6609 | 2104 | 0.0072159 | 0.72881 | 2084 | 0.97 | 737
7311 | LOS OSITOS 2102258878 | 182082102 | LOS OSITOS 2102 | 258878 | FALSE | 7396.9293 | 5357.1763 | 3.3295 | 26 | 3.9953e-05 | 3270 | 107.5084 | 1921 | 0.0072141 | 0.18757 | 2085 |  | 3114
1213 | WOODACRE 1102137662 | 43021102 | WOODACRE 1102 | 137662 | FALSE | 13866.4902 | 13813.2405 | 8.585 | 104 | 0.00014441 | 806 | 94.0043 | 1985 | 0.0071841 | 0.74714 | 2086 | 0.76 | 786
2384 | BONNIE NOOK 1102CB | 152301102 | BONNIE NOOK 1102 | CB | FALSE | 54723.5805 | 54723.5805 | 34.0109 | 337 | 0.00011257 | 1353 | 93.6722 | 1990 | 0.0071702 | 2.4164 | 2087 | 71.14 | 67
324 | PLACERVILLE 1110953474 | 153081110 | PLACERVILLE 1110 | 953474 | FALSE | 17115.5789 | 17115.5789 | 10.6374 | 133 | 0.000245 | 233 | 47.063 | 2231 | 0.0071239 | 0.94748 | 2088 |  | 2666
9849 | FOOTHILL 1101722270 | 182951101 | FOOTHILL 1101 | 722270 | TRUE | 712.8056 | 283.5574 | 0.17623 | 5 | 3.323e-05 | 3380 | 133.0363 | 1839 | 0.0070957 | 0.035479 | 2089 |  | 3434
3510 | MONTE RIO 1111140 | 42811111 | MONTE RIO 1111 | 140 | FALSE | 13525.925 | 13525.925 | 8.4064 | 96 | 0.0002562 | 201 | 19.1476 | 2459 | 0.0070376 | 0.67561 | 2090 | 16.37 | 338
1551 | CARLOTTA 11214914 | 192291121 | CARLOTTA 1121 | 4914 | FALSE | 22650.1521 | 17097.4476 | 10.6261 | 138 | 0.00016776 | 577 | 39.2521 | 2282 | 0.0070374 | 0.97117 | 2091 | 0.08 | 1621
4560 | COARSEGOLD 210210330 | 254432102 | COARSEGOLD 2102 | 10330 | FALSE | 15550.3229 | 15550.3229 | 9.6646 | 90 | 7.2321e-05 | 2408 | 118.1064 | 1878 | 0.0069896 | 0.62906 | 2092 | 0.31 | 1008
6442 | PIT NO 1 11019702 | 103721101 | PIT NO 1 1101 | 9702 | FALSE | 14797.576 | 1035.9167 | 0.64383 | 91 | 3.6155e-05 | 3331 | 189.6534 | 1664 | 0.006985 | 0.63564 | 2093 | 0.01 | 2605
8877 | WILLOW CREEK 11013050 | 192171101 | WILLOW CREEK 1101 | 3050 | FALSE | 4223.7094 | 4223.7094 | 2.6251 | 18 | 0.00010688 | 1481 | 71.3502 | 2089 | 0.0069828 | 0.12569 | 2094 | 11.06 | 389
9559 | SONOMA 1103581588 | 42721103 | SONOMA 1103 | 581588 | TRUE | 1519.7137 | 313.0143 | 0.19454 | 14 | 0.00011751 | 1235 | 44.2079 | 2251 | 0.0069585 | 0.097419 | 2095 |  | 3376
2326 | BRUNSWICK 11052140 | 152481105 | BRUNSWICK 1105 | 2140 | FALSE | 55629.2693 | 55629.2693 | 34.5738 | 373 | 7.6296e-05 | 2300 | 87.1186 | 2015 | 0.0069513 | 2.5928 | 2096 | 99.53 | 20
7797 | SAUSALITO 1101331806 | 42491101 | SAUSALITO 1101 | 331806 | TRUE | 1086.2067 | 799.0558 | 0.49662 | 5 | 0.00010249 | 1590 | 66.6724 | 2112 | 0.0069274 | 0.034637 | 2097 |  | 3162
1778 | WEIMAR 11026175 | 152491102 | WEIMAR 1102 | 6175 | FALSE | 4418.4642 | 4418.4642 | 2.7461 | 30 | 7.0467e-05 | 2457 | 113.3507 | 1901 | 0.0069045 | 0.20713 | 2098 | 0.08 | 1596
2962 | CURTIS 1704803 | 163351704 | CURTIS 1704 | 803 | FALSE | 15630.8479 | 15630.8479 | 9.7146 | 93 | 8.737e-05 | 2002 | 89.4789 | 2003 | 0.0068944 | 0.64118 | 2099 | 0.14 | 1319
5429 | MIRABEL 1101228 | 42091101 | MIRABEL 1101 | 228 | FALSE | 15665.2534 | 3403.012 | 2.115 | 123 | 0.00014113 | 851 | 47.1197 | 2230 | 0.0068367 | 0.84091 | 2100 | 1.03 | 725
8011 | HORSESHOE 1101603250 | 152571101 | HORSESHOE 1101 | 603250 | TRUE | 2274.9057 | 927.3694 | 0.57636 | 21 | 0.00016094 | 631 | 57.7467 | 2167 | 0.0068337 | 0.14351 | 2101 |  | 3184
7095 | PUEBLO 2102618 | 43292102 | PUEBLO 2102 | 618 | TRUE | 16180.0386 | 742.2572 | 0.46132 | 118 | 9.7103e-05 | 1711 | 69.2887 | 2098 | 0.0068234 | 0.80516 | 2102 | 17.57 | 331
8240 | WOODSIDE 11018601 | 24251101 | WOODSIDE 1101 | 8601 | TRUE | 961.631 | 961.631 | 0.59766 | 9 | 0.00015446 | 700 | 60.8174 | 2150 | 0.0067792 | 0.061013 | 2103 | 35.86 | 209
3848 | REEDLEY 11127240 | 252341112 | REEDLEY 1112 | 7240 | FALSE | 41066.7491 | 1553.9231 | 0.96577 | 234 | 4.3626e-05 | 3198 | 175.637 | 1696 | 0.0067642 | 1.5828 | 2104 | 0.02 | 2533
4429 | SONOMA 1105138 | 42721105 | SONOMA 1105 | 138 | TRUE | 26504.92 | 104.0479 | 0.064666 | 197 | 6.5875e-05 | 2590 | 63.508 | 2131 | 0.0067556 | 1.3309 | 2105 | 0.62 | 838
1588 | CORRAL 110359770 | 162991103 | CORRAL 1103 | 59770 | FALSE | 11687.7507 | 7749.7634 | 4.8165 | 97 | 8.5709e-05 | 2037 | 89.7185 | 2001 | 0.0067467 | 0.65443 | 2106 | 0.09 | 1532
6984 | GABILAN 1101566352 | 182331101 | GABILAN 1101 | 566352 | TRUE | 1524.3755 | 680.7554 | 0.42309 | 9 | 3.3385e-05 | 3378 | 153.3762 | 1766 | 0.0067421 | 0.060679 | 2107 |  | 3079
8546 | SPENCE 1102990464 | 182201102 | SPENCE 1102 | 990464 | FALSE | 8550.7923 | 3365.9887 | 2.092 | 53 | 2.9572e-05 | 3431 | 166.8203 | 1728 | 0.0067321 | 0.3568 | 2108 |  | 3234
9813 | BOLINAS 110137034 | 42261101 | BOLINAS 1101 | 37034 | FALSE | 7287.0481 | 7287.0481 | 4.5289 | 16 | 0.00011223 | 1360 | 44.6194 | 2249 | 0.006701 | 0.10722 | 2109 | 0.31 | 1007
8495 | PENRYN 110550550 | 152561105 | PENRYN 1105 | 50550 | TRUE | 16250.0266 | 0 | 0 | 127 | 0.00012612 | 1078 | 64.7345 | 2124 | 0.0066813 | 0.84852 | 2110 | 0.74 | 790
533 | HIGHLANDS 110439458 | 43361104 | HIGHLANDS 1104 | 39458 | FALSE | 8594.1592 | 1902.6531 | 1.1825 | 72 | 7.6303e-05 | 2298 | 85.8335 | 2024 | 0.0066627 | 0.47971 | 2111 | 0.27 | 1048
6908 | MENLO 11038512 | 24131103 | MENLO 1103 | 8512 | FALSE | 39804.5313 | 39804.5313 | 24.7387 | 228 | 0.00015985 | 643 | 38.9598 | 2284 | 0.0066372 | 1.5133 | 2112 | 8.94 | 418
1455 | LAS GALLINAS A 1105904 | 42991105 | LAS GALLINAS A 1105 | 904 | FALSE | 11554.8525 | 2469.2456 | 1.5346 | 78 | 4.3101e-05 | 3208 | 64.1478 | 2127 | 0.0066274 | 0.51694 | 2113 | 0.04 | 2146
2184 | GEYSERVILLE 110289714 | 42891102 | GEYSERVILLE 1102 | 89714 | TRUE | 11363.665 | 178.2278 | 0.11077 | 71 | 8.7635e-05 | 1996 | 68.3169 | 2100 | 0.0066271 | 0.47052 | 2114 | 0.02 | 2528
2865 | MOLINO 1102344 | 42571102 | MOLINO 1102 | 344 | FALSE | 9676.0469 | 2427.2453 | 1.5085 | 77 | 0.00010403 | 1551 | 64.3203 | 2126 | 0.0066172 | 0.50953 | 2115 | 1.32 | 687
2057 | SHINGLE SPRINGS 210911092 | 153652109 | SHINGLE SPRINGS 2109 | 11092 | FALSE | 36100.2834 | 36100.2834 | 22.4365 | 239 | 0.00011036 | 1404 | 74.4691 | 2070 | 0.0066099 | 1.5798 | 2116 | 0.14 | 1314
10095 | SILVERADO 2104645 | 43432104 | SILVERADO 2104 | 645 | FALSE | 1626.8938 | 1626.8938 | 1.0111 | 13 | 9.1232e-05 | 1870 | 67.7241 | 2103 | 0.0065604 | 0.085285 | 2117 | 60.62 | 88
6812 | CLOVERDALE 1101474708 | 42821101 | CLOVERDALE 1101 | 474708 | TRUE | 1392.1284 | 422.046 | 0.2623 | 13 | 0.00016436 | 594 | 18.3674 | 2470 | 0.0065356 | 0.084962 | 2118 |  | 3063
891 | TEMPLETON 2108A64 | 183052108 | TEMPLETON 2108 | A64 | FALSE | 18905.9424 | 3242.5015 | 2.0152 | 150 | 7.5966e-05 | 2309 | 88.4837 | 2011 | 0.0065293 | 0.9794 | 2119 | 0.02 | 2493
851 | HIGGINS 1110861610 | 152691110 | HIGGINS 1110 | 861610 | FALSE | 11222.3603 | 1689.7743 | 1.0502 | 99 | 0.00027833 | 162 | 23.4916 | 2410 | 0.0065286 | 0.64633 | 2120 |  | 2695
10050 | MIRABEL 110286326 | 42091102 | MIRABEL 1102 | 86326 | FALSE | 1145.996 | 1133.0955 | 0.70422 | 5 | 8.4164e-05 | 2088 | 38.1596 | 2289 | 0.0065228 | 0.032614 | 2121 |  | 3481
1904 | SONOMA 1105404 | 42721105 | SONOMA 1105 | 404 | FALSE | 7372.5748 | 3785.8959 | 2.3529 | 63 | 6.9011e-05 | 2509 | 86.9459 | 2016 | 0.0065164 | 0.41053 | 2122 | 0.24 | 1106
4884 | PLACERVILLE 1112CB | 153081112 | PLACERVILLE 1112 | CB | FALSE | 15016.5066 | 13697.3672 | 8.513 | 117 | 0.00025615 | 202 | 34.5981 | 2310 | 0.0065148 | 0.76223 | 2123 | 0.09 | 1568
3571 | OAKHURST 110377384 | 254421103 | OAKHURST 1103 | 77384 | FALSE | 7595.6346 | 7595.6346 | 4.7207 | 61 | 0.00017011 | 562 | 62.7847 | 2138 | 0.0065145 | 0.39738 | 2124 | 0.65 | 823
2586 | VOLTA 11021504 | 102541102 | VOLTA 1102 | 1504 | FALSE | 13347.4853 | 13347.4853 | 8.2955 | 95 | 5.8288e-05 | 2825 | 84.8611 | 2031 | 0.0065125 | 0.61869 | 2125 | 45.39 | 148
5574 | PARADISE 1104920400 | 102831104 | PARADISE 1104 | 920400 | FALSE | 7975.407 | 7538.764 | 4.6854 | 66 | 0.00044142 | 53 | 18.0732 | 2478 | 0.0064968 | 0.42879 | 2126 |  | 2964
3679 | SUNOL 1101MR297 | 14241101 | SUNOL 1101 | MR297 | FALSE | 9710.6915 | 9531.5764 | 5.9239 | 66 | 6.9143e-05 | 2502 | 221.7666 | 1602 | 0.0064881 | 0.42822 | 2127 | 0.06 | 1849
3379 | GEYSERVILLE 1101354 | 42891101 | GEYSERVILLE 1101 | 354 | FALSE | 12035.3765 | 1010.2026 | 0.62784 | 79 | 9.3149e-05 | 1816 | 134.0043 | 1836 | 0.0064828 | 0.51214 | 2128 |  | 2822
5354 | FORT ROSS 1121560 | 42851121 | FORT ROSS 1121 | 560 | FALSE | 9061.7878 | 8145.5491 | 5.0625 | 31 | 9.9934e-05 | 1648 | 60.8351 | 2148 | 0.0064599 | 0.20026 | 2129 | 0.02 | 2420
1701 | CALAVERAS CEMENT 110136880 | 162211101 | CALAVERAS CEMENT 1101 | 36880 | FALSE | 13851.9467 | 9899.4771 | 6.1526 | 92 | 8.6095e-05 | 2032 | 179.7214 | 1684 | 0.0064477 | 0.59319 | 2130 | 0.08 | 1578
3076 | PLACERVILLE 21061104 | 153082106 | PLACERVILLE 2106 | 1104 | FALSE | 79643.684 | 79643.684 | 49.4989 | 462 | 0.00011856 | 1216 | 56.9205 | 2171 | 0.0064469 | 2.9785 | 2131 | 111.82 | 14
6813 | CASTRO VALLEY 111010315 | 14091110 | CASTRO VALLEY 1110 | 10315 | FALSE | 8831.8074 | 8831.8074 | 5.489 | 53 | 0.00010699 | 1472 | 59.7801 | 2155 | 0.006431 | 0.34084 | 2132 |  | 3064
7135 | MOLINO 1102982462 | 42571102 | MOLINO 1102 | 982462 | FALSE | 2320.5593 | 2320.5593 | 1.4422 | 18 | 9.629e-05 | 1726 | 75.3379 | 2065 | 0.006427 | 0.11569 | 2133 |  | 3100
8349 | BRUNSWICK 1110CB | 152481110 | BRUNSWICK 1110 | CB | TRUE | 2754.8033 | 5.4992 | 0.0034177 | 26 | 0.00020884 | 366 | 19.5341 | 2454 | 0.0064174 | 0.16685 | 2134 | 0.01 | 2596
3244 | PLACERVILLE 111219712 | 153081112 | PLACERVILLE 1112 | 19712 | FALSE | 20850.3369 | 20776.2868 | 12.9125 | 151 | 0.000145 | 801 | 90.5715 | 1997 | 0.0064118 | 0.96818 | 2135 | 0.12 | 1371
3409 | PINE GROVE 110213438 | 163751102 | PINE GROVE 1102 | 13438 | FALSE | 26618.9181 | 26618.9181 | 16.5438 | 172 | 0.00010264 | 1581 | 69.7074 | 2096 | 0.0063999 | 1.1008 | 2136 | 82.17 | 45
9640 | OLEMA 110149756 | 42291101 | OLEMA 1101 | 49756 | FALSE | 9480.1738 | 1727.7805 | 1.0738 | 40 | 7.5687e-05 | 2316 | 118.0346 | 1881 | 0.0063622 | 0.25449 | 2137 | 0.01 | 2594
5813 | PERRY 1101CB | 183071101 | PERRY 1101 | CB | FALSE | 4085.1757 | 4085.1757 | 2.539 | 27 | 6.8809e-05 | 2513 | 75.2459 | 2066 | 0.0062536 | 0.16885 | 2138 | 0.07 | 1752
5598 | FROGTOWN 170236870 | 163451702 | FROGTOWN 1702 | 36870 | TRUE | 3829.3681 | 541.2922 | 0.33642 | 29 | 0.00011992 | 1188 | 41.8373 | 2269 | 0.0062483 | 0.1812 | 2139 | 0.04 | 2157
7823 | FORT BRAGG A 11013113 | 42761101 | FORT BRAGG A 1101 | 3113 | FALSE | 16133.333 | 16133.333 | 10.0269 | 68 | 8.3643e-05 | 2106 | 76.2422 | 2061 | 0.0062347 | 0.42396 | 2140 | 0.05 | 1961
3839 | PARADISE 11052214 | 102831105 | PARADISE 1105 | 2214 | FALSE | 29878.7054 | 24265.0129 | 15.0808 | 233 | 0.00042568 | 61 | 48.0844 | 2221 | 0.0062243 | 1.4503 | 2141 | 51.75 | 113
955 | STANISLAUS 170179826 | 162821701 | STANISLAUS 1701 | 79826 | FALSE | 16584.8842 | 16584.8842 | 10.3076 | 95 | 0.00015691 | 673 | 91.848 | 1994 | 0.0062159 | 0.59051 | 2142 | 0.15 | 1290
165 | CHALLENGE 110198174 | 103201101 | CHALLENGE 1101 | 98174 | FALSE | 19681.5881 | 19681.5881 | 12.2322 | 66 | 7.9168e-05 | 2229 | 58.0357 | 2166 | 0.0062048 | 0.40952 | 2143 | 22.16 | 296
2120 | BRUNSWICK 110350070 | 152481103 | BRUNSWICK 1103 | 50070 | FALSE | 28555.3412 | 28555.3412 | 17.7473 | 201 | 0.00011083 | 1394 | 43.6964 | 2255 | 0.0062036 | 1.2469 | 2144 | 128.64 | 7
4607 | SARATOGA 1107413816 | 83371107 | SARATOGA 1107 | 413816 | FALSE | 17928.3843 | 17928.3843 | 11.1426 | 104 | 0.00011948 | 1197 | 65.9071 | 2117 | 0.0061927 | 0.64404 | 2145 | 0.87 | 760
1564 | SAN LUIS OBISPO 1101483444 | 182631101 | SAN LUIS OBISPO 1101 | 483444 | FALSE | 8714.6826 | 3311.0968 | 2.0579 | 67 | 5.4635e-05 | 2929 | 67.496 | 2105 | 0.0061552 | 0.4124 | 2146 |  | 2731
4427 | PLACERVILLE 11118582 | 153081111 | PLACERVILLE 1111 | 8582 | FALSE | 19173.6398 | 15254.7771 | 9.4809 | 163 | 0.00018689 | 463 | 41.133 | 2272 | 0.0061345 | 0.99993 | 2147 | 0.05 | 1953
9649 | LOS GATOS 1107LA60 | 82021107 | LOS GATOS 1107 | LA60 | FALSE | 13957.1729 | 13957.1729 | 8.6744 | 61 | 0.00010054 | 1636 | 81.9054 | 2041 | 0.0061263 | 0.3737 | 2148 | 41.93 | 173
3992 | VOLTA 11021502 | 102541102 | VOLTA 1102 | 1502 | FALSE | 11680.2523 | 11680.2523 | 7.2593 | 80 | 8.0915e-05 | 2184 | 65.4099 | 2121 | 0.0061144 | 0.48915 | 2149 | 27.78 | 255
4576 | VALLEY VIEW 1106CB | 14341106 | VALLEY VIEW 1106 | CB | FALSE | 8114.1348 | 6042.2888 | 3.7553 | 50 | 0.00011189 | 1369 | 66.0103 | 2115 | 0.0060781 | 0.30391 | 2150 | 0.06 | 1817
10363 | SAN LEANDRO U 1114653758 | 13111114 | SAN LEANDRO U 1114 | 653758 | TRUE | 582.3673 | 582.3673 | 0.36194 | 5 | 5.5782e-05 | 2895 | 104.6024 | 1930 | 0.0060671 | 0.030336 | 2151 |  | 3538
7007 | ORO FINO 110238698 | 103031102 | ORO FINO 1102 | 38698 | FALSE | 25178.9612 | 25178.9612 | 15.6488 | 103 | 9.2036e-05 | 1843 | 61.204 | 2145 | 0.0060349 | 0.62159 | 2152 | 4.1 | 526
3531 | HALF MOON BAY 11039112 | 24101103 | HALF MOON BAY 1103 | 9112 | FALSE | 8500.5119 | 1386.5143 | 0.86172 | 68 | 4.4335e-05 | 3182 | 101.7861 | 1948 | 0.0060009 | 0.40806 | 2153 | 0.04 | 2214
9344 | HALF MOON BAY 1101821698 | 24101101 | HALF MOON BAY 1101 | 821698 | FALSE | 1364.9269 | 1364.9269 | 0.84831 | 9 | 5.5293e-05 | 2904 | 187.6587 | 1667 | 0.0060008 | 0.054007 | 2154 |  | 3345
10526 | SANTA ROSA A 1108409621 | 42151108 | SANTA ROSA A 1108 | 409621 | TRUE | 945.4612 | 219.1314 | 0.13619 | 4 | 8.5029e-05 | 2059 | 85.5196 | 2026 | 0.0059943 | 0.023977 | 2155 |  | 3567
3796 | CAMP EVERS 210612518 | 83622106 | CAMP EVERS 2106 | 12518 | FALSE | 25177.1399 | 25177.1399 | 15.6477 | 145 | 0.00025023 | 216 | 28.5941 | 2352 | 0.0059295 | 0.85978 | 2156 | 0.8 | 774
2601 | BRUNSWICK 11062104 | 152481106 | BRUNSWICK 1106 | 2104 | FALSE | 15810.2753 | 15810.2753 | 9.8261 | 123 | 0.00020356 | 384 | 19.3883 | 2456 | 0.0059169 | 0.72777 | 2157 | 38.88 | 194
2204 | OAKHURST 11035470 | 254421103 | OAKHURST 1103 | 5470 | FALSE | 14989.8273 | 14989.8273 | 9.3162 | 104 | 0.00010143 | 1618 | 96.9488 | 1973 | 0.0059093 | 0.61457 | 2158 | 14.88 | 353
2618 | ARVIN 110194892 | 253801101 | ARVIN 1101 | 94892 | TRUE | 15531.7609 | 345.9853 | 0.21503 | 66 | 3.5047e-05 | 3351 | 201.9181 | 1637 | 0.0059064 | 0.38983 | 2159 |  | 2790
6041 | CAMP EVERS 210694770 | 83622106 | CAMP EVERS 2106 | 94770 | FALSE | 6459.1608 | 3806.5671 | 2.3658 | 55 | 0.00027047 | 172 | 16.4987 | 2510 | 0.0059058 | 0.32482 | 2160 | 0.27 | 1050
1981 | COTATI 1105328 | 42271105 | COTATI 1105 | 328 | FALSE | 22172.9748 | 2414.9476 | 1.5009 | 173 | 9.4997e-05 | 1766 | 59.7612 | 2156 | 0.0058817 | 1.0175 | 2161 | 1 | 732
519 | POINT ARENA 110147952 | 43381101 | POINT ARENA 1101 | 47952 | FALSE | 16717.6297 | 16717.6297 | 10.3901 | 88 | 0.00011754 | 1233 | 58.6557 | 2163 | 0.0058506 | 0.51485 | 2162 | 0.09 | 1517
2535 | COTATI 1102825 | 42271102 | COTATI 1102 | 825 | TRUE | 3371.6214 | 749.4567 | 0.46579 | 26 | 6.9953e-05 | 2473 | 79.9838 | 2048 | 0.0058122 | 0.15112 | 2163 |  | 2782
698 | RESERVATION ROAD 11013026 | 182731101 | RESERVATION ROAD 1101 | 3026 | FALSE | 36330.5251 | 35201.2582 | 21.8777 | 238 | 5.5886e-05 | 2892 | 99.002 | 1958 | 0.0057671 | 1.3726 | 2164 | 2.36 | 610
4296 | MORGAN HILL 2105XR494 | 83242105 | MORGAN HILL 2105 | XR494 | TRUE | 11814.5496 | 737.5052 | 0.45836 | 98 | 5.6428e-05 | 2877 | 82.0467 | 2040 | 0.0057504 | 0.56354 | 2165 | 0.04 | 2167
875 | FULTON 110777670 | 42561107 | FULTON 1107 | 77670 | FALSE | 10996.9079 | 10874.5833 | 6.7586 | 98 | 0.00011661 | 1258 | 47.4912 | 2228 | 0.0057454 | 0.56305 | 2166 | 19.77 | 309
2839 | CAMP EVERS 210510294 | 83622105 | CAMP EVERS 2105 | 10294 | FALSE | 13501.9938 | 13501.9938 | 8.3915 | 95 | 0.00023536 | 261 | 22.5874 | 2416 | 0.0057046 | 0.54194 | 2167 | 48.18 | 131
4923 | GEYSERVILLE 1101480 | 42891101 | GEYSERVILLE 1101 | 480 | FALSE | 25809.6606 | 2502.4894 | 1.5553 | 161 | 6.7656e-05 | 2543 | 89.1189 | 2006 | 0.0057021 | 0.91803 | 2168 | 0.01 | 2595
5117 | WOODSIDE 11018912 | 24251101 | WOODSIDE 1101 | 8912 | FALSE | 6310.9141 | 6268.7877 | 3.8961 | 52 | 0.000205 | 381 | 25.8096 | 2383 | 0.0056974 | 0.29627 | 2169 | 26.71 | 266
6008 | GEYSERVILLE 1101482 | 42891101 | GEYSERVILLE 1101 | 482 | TRUE | 6000.1069 | 595.0555 | 0.36983 | 38 | 6e-05 | 2775 | 118.3715 | 1876 | 0.0056711 | 0.2155 | 2170 | 0.74 | 789
3612 | BIG BASIN 110212992 | 82841102 | BIG BASIN 1102 | 12992 | FALSE | 22915.4569 | 22915.4569 | 14.242 | 160 | 0.00020519 | 379 | 28.593 | 2353 | 0.0056575 | 0.90521 | 2171 | 1.14 | 711
151 | SUMMIT 1102CB | 152591102 | SUMMIT 1102 | CB | FALSE | 1694.4122 | 1694.4122 | 1.0531 | 22 | 5.8522e-05 | 2821 | 53.0175 | 2195 | 0.0056462 | 0.12422 | 2172 | 0.02 | 2450
585 | LUCERNE 110647198 | 43351106 | LUCERNE 1106 | 47198 | FALSE | 9365.2067 | 4939.462 | 3.0699 | 70 | 0.00010692 | 1477 | 39.3397 | 2280 | 0.0056207 | 0.39345 | 2173 | 0.04 | 2116
7910 | SILVERADO 2105167360 | 43432105 | SILVERADO 2105 | 167360 | FALSE | 15830.4656 | 15413.5909 | 9.5796 | 70 | 0.0001177 | 1232 | 51.7218 | 2203 | 0.0056116 | 0.39281 | 2174 |  | 3176
1304 | CURTIS 17028000 | 163351702 | CURTIS 1702 | 8000 | FALSE | 23055.4602 | 23055.4602 | 14.3291 | 174 | 0.00011159 | 1377 | 95.7818 | 1979 | 0.0056032 | 0.97497 | 2175 | 0.55 | 871
417 | RALSTON 1101CB | 24141101 | RALSTON 1101 | CB | TRUE | 4645.037 | 606.8044 | 0.37713 | 37 | 4.6425e-05 | 3127 | 105.6404 | 1927 | 0.0055946 | 0.207 | 2176 | 0.05 | 1970
1975 | RALSTON 11022028 | 24141102 | RALSTON 1102 | 2028 | FALSE | 3747.9741 | 3373.7724 | 2.0968 | 38 | 7.449e-05 | 2345 | 86.2641 | 2021 | 0.0055851 | 0.21223 | 2177 | 0.08 | 1658
6769 | ATASCADERO 1101A50 | 182541101 | ATASCADERO 1101 | A50 | FALSE | 33669.9383 | 31118.7087 | 19.3404 | 269 | 5.5958e-05 | 2891 | 116.8319 | 1888 | 0.0055802 | 1.5011 | 2178 | 0.22 | 1131
2377 | GUALALA 11121294 | 42841112 | GUALALA 1112 | 1294 | FALSE | 32661.4744 | 31953.6798 | 19.8593 | 234 | 6.861e-05 | 2518 | 79.062 | 2054 | 0.0055387 | 1.2961 | 2179 | 0.53 | 883
5858 | FAIRVIEW 2207P150 | 13432207 | FAIRVIEW 2207 | P150 | FALSE | 3652.8381 | 3652.8381 | 2.2703 | 18 | 9.5063e-05 | 1763 | 45.0393 | 2245 | 0.0055206 | 0.09937 | 2180 | 0.03 | 2243
2861 | PIT NO 5 11011660 | 101321101 | PIT NO 5 1101 | 1660 | FALSE | 7855.6793 | 7855.6793 | 4.8823 | 43 | 0.00014039 | 865 | 43.7408 | 2254 | 0.0055185 | 0.23729 | 2181 | 0.02 | 2545
4568 | RINCON 1101CB | 43321101 | RINCON 1101 | CB | FALSE | 7739.8411 | 2580.5041 | 1.6038 | 68 | 0.00014616 | 786 | 21.7605 | 2428 | 0.0054995 | 0.37397 | 2182 | 0.06 | 1798
8511 | SAN ARDO 1101610148 | 182191101 | SAN ARDO 1101 | 610148 | FALSE | 19896.3037 | 3154.5584 | 1.9606 | 58 | 4.5598e-05 | 3151 | 102.3263 | 1944 | 0.0054812 | 0.31791 | 2183 |  | 3231
4730 | HARTLEY 110194178 | 43211101 | HARTLEY 1101 | 94178 | FALSE | 6646.4632 | 3457.4484 | 2.1488 | 57 | 7.3272e-05 | 2388 | 42.0306 | 2265 | 0.0054615 | 0.3113 | 2184 | 0.03 | 2290
1445 | BIG BASIN 1102CB | 82841102 | BIG BASIN 1102 | CB | FALSE | 9963.4073 | 9963.4073 | 6.1923 | 59 | 0.00022265 | 308 | 33.5088 | 2315 | 0.0054141 | 0.31943 | 2185 | 0.49 | 898
6388 | HALF MOON BAY 11036012 | 24101103 | HALF MOON BAY 1103 | 6012 | FALSE | 15479.7977 | 10729.2764 | 6.6683 | 79 | 9.0533e-05 | 1896 | 70.018 | 2095 | 0.0054078 | 0.42722 | 2186 | 0.08 | 1585
629 | LAURELES 11112020 | 182371111 | LAURELES 1111 | 2020 | FALSE | 55275.2572 | 55275.2572 | 34.3538 | 281 | 9.1434e-05 | 1861 | 43.1327 | 2260 | 0.005376 | 1.5107 | 2187 | 0.23 | 1114
3079 | OCEANO 1102V50 | 182601102 | OCEANO 1102 | V50 | FALSE | 16840.5394 | 11517.5193 | 7.1582 | 107 | 4.7059e-05 | 3112 | 96.3505 | 1978 | 0.005367 | 0.57427 | 2188 | 0.11 | 1428
342 | WOODACRE 1101404 | 43021101 | WOODACRE 1101 | 404 | FALSE | 19975.081 | 19975.081 | 12.4146 | 152 | 0.00018515 | 471 | 26.3611 | 2372 | 0.0053668 | 0.81576 | 2189 | 92.58 | 29
4506 | TIDEWATER 210657926 | 14652106 | TIDEWATER 2106 | 57926 | TRUE | 18926.9724 | 200.7916 | 0.12479 | 97 | 5.4965e-05 | 2914 | 62.5543 | 2139 | 0.0053561 | 0.51954 | 2190 |  | 2900
6794 | CAMP EVERS 21055188 | 83622105 | CAMP EVERS 2105 | 5188 | FALSE | 3280.6197 | 3280.6197 | 2.0389 | 19 | 0.00034885 | 92 | 16.3316 | 2511 | 0.0053482 | 0.10162 | 2191 | 7.26 | 449
4962 | MONTE RIO 1113652 | 42811113 | MONTE RIO 1113 | 652 | FALSE | 2607.8717 | 2607.8717 | 1.6208 | 25 | 0.00027854 | 161 | 20.0324 | 2448 | 0.0053427 | 0.13357 | 2192 | 55.16 | 104
5950 | COTATI 1102260 | 42271102 | COTATI 1102 | 260 | FALSE | 9537.0372 | 4317.1662 | 2.6831 | 68 | 6.2862e-05 | 2687 | 71.585 | 2084 | 0.0053405 | 0.36316 | 2193 | 0.78 | 778
2816 | HICKS 2101574315 | 83432101 | HICKS 2101 | 574315 | FALSE | 12024.0849 | 11904.9852 | 7.399 | 78 | 0.00010886 | 1429 | 65.6711 | 2118 | 0.005318 | 0.4148 | 2194 |  | 2800
4882 | NARROWS 210276952 | 153132102 | NARROWS 2102 | 76952 | FALSE | 18206.8026 | 3648.4496 | 2.2675 | 161 | 0.00026698 | 179 | 39.5343 | 2276 | 0.0052383 | 0.84337 | 2195 | 0.06 | 1785
8374 | SAN JOAQUIN #3 1103501771 | 252531103 | SAN JOAQUIN #3 1103 | 501771 | FALSE | 7891.6601 | 7891.6601 | 4.9047 | 54 | 4.0591e-05 | 3256 | 137.8049 | 1819 | 0.0052248 | 0.28214 | 2196 |  | 3217
4446 | OTTER 1101440 | 182941101 | OTTER 1101 | 440 | FALSE | 17666.8696 | 13392.7701 | 8.3237 | 107 | 5.2851e-05 | 2975 | 95.646 | 1980 | 0.0051543 | 0.5515 | 2197 | 0.05 | 1917
1813 | PUEBLO 210375612 | 43292103 | PUEBLO 2103 | 75612 | TRUE | 15618.6787 | 0 | 0 | 114 | 6.2516e-05 | 2703 | 68.7688 | 2099 | 0.0051135 | 0.58294 | 2198 |  | 2747
3962 | POINT MORETTI 110112122 | 82931101 | POINT MORETTI 1101 | 12122 | FALSE | 12740.7086 | 10570.3766 | 6.5695 | 63 | 0.00010779 | 1455 | 51.4668 | 2205 | 0.0051004 | 0.32133 | 2199 | 0.03 | 2382
6972 | BRUNSWICK 1102940 | 152481102 | BRUNSWICK 1102 | 940 | FALSE | 5636.9672 | 1911.101 | 1.1878 | 46 | 0.00018608 | 466 | 23.9825 | 2400 | 0.005067 | 0.23308 | 2200 | 7.35 | 447
2994 | SHADY GLEN 110132726 | 152431101 | SHADY GLEN 1101 | 32726 | FALSE | 19770.2597 | 19581.5665 | 12.17 | 146 | 0.00014193 | 840 | 48.5752 | 2218 | 0.00506 | 0.73876 | 2201 | 0.1 | 1475
5931 | EAST QUINCY 11012452 | 102551101 | EAST QUINCY 1101 | 2452 | TRUE | 11049.8485 | 228.5177 | 0.14202 | 87 | 5.4568e-05 | 2931 | 79.1562 | 2053 | 0.0050248 | 0.43716 | 2202 | 13.72 | 363
1799 | MORGAN HILL 2105XR578 | 83242105 | MORGAN HILL 2105 | XR578 | TRUE | 1108.6732 | 261.0602 | 0.16225 | 12 | 5.1652e-05 | 3003 | 53.5212 | 2190 | 0.0050174 | 0.060209 | 2203 | 0.02 | 2414
5416 | ANNAPOLIS 1101528344 | 42861101 | ANNAPOLIS 1101 | 528344 | FALSE | 43372.0838 | 43372.0838 | 26.9559 | 171 | 9.687e-05 | 1717 | 60.4469 | 2152 | 0.0049999 | 0.85498 | 2204 |  | 2950
7537 | LOS OSITOS 2102148504 | 182082102 | LOS OSITOS 2102 | 148504 | TRUE | 3218.0268 | 275.7602 | 0.17139 | 14 | 6.4053e-05 | 2643 | 71.3988 | 2086 | 0.0049963 | 0.069948 | 2205 |  | 3134
235 | KONOCTI 11022293 | 43311102 | KONOCTI 1102 | 2293 | FALSE | 2820.5709 | 2820.5709 | 1.753 | 21 | 6.9405e-05 | 2492 | 78.9038 | 2056 | 0.0049653 | 0.10427 | 2206 | 0.04 | 2140
3072 | ANTLER 1101CB | 103271101 | ANTLER 1101 | CB | FALSE | 2574.4725 | 2574.4725 | 1.6 | 18 | 0.00018307 | 488 | 33.0833 | 2322 | 0.0049349 | 0.088829 | 2207 | 0.05 | 1919
8410 | CAMP EVERS 210611533 | 83622106 | CAMP EVERS 2106 | 11533 | FALSE | 4249.6596 | 4249.6596 | 2.6412 | 28 | 9.1401e-05 | 1863 | 58.6478 | 2164 | 0.0048855 | 0.13679 | 2208 | 29.27 | 243
3050 | AUBERRY 1101R324 | 254151101 | AUBERRY 1101 | R324 | FALSE | 17238.3934 | 17238.3934 | 10.7137 | 119 | 3.9517e-05 | 3277 | 112.2851 | 1904 | 0.0048731 | 0.5799 | 2209 | 35.54 | 213
9906 | POINT MORETTI 110183716 | 82931101 | POINT MORETTI 1101 | 83716 | FALSE | 4275.4859 | 4027.3677 | 2.503 | 22 | 0.00011418 | 1318 | 54.1847 | 2187 | 0.0048588 | 0.10689 | 2210 | 0.02 | 2436
5631 | PARADISE 1105878870 | 102831105 | PARADISE 1105 | 878870 | FALSE | 4057.446 | 4057.446 | 2.5217 | 29 | 0.00048816 | 33 | 4.9842 | 2754 | 0.0048412 | 0.1404 | 2211 |  | 2967
1901 | MOUNTAIN QUARRIES 21011184 | 152282101 | MOUNTAIN QUARRIES 2101 | 1184 | FALSE | 18935.6341 | 18820.6068 | 11.6971 | 136 | 0.00016372 | 603 | 34.7864 | 2309 | 0.0048403 | 0.65828 | 2212 | 54.38 | 107
4871 | BRUNSWICK 11052130 | 152481105 | BRUNSWICK 1105 | 2130 | FALSE | 23180.7639 | 23180.7639 | 14.4069 | 163 | 5.7718e-05 | 2845 | 88.5821 | 2010 | 0.0048209 | 0.78581 | 2213 | 63.53 | 81
10520 | CASTRO VALLEY 1110MR273 | 14091110 | CASTRO VALLEY 1110 | MR273 | FALSE | 1164.6083 | 1164.6083 | 0.72381 | 13 | 7.8527e-05 | 2248 | 62.481 | 2140 | 0.0047919 | 0.062294 | 2214 |  | 3564
9367 | REDBUD 110244119 | 43191102 | REDBUD 1102 | 44119 | TRUE | 4510.2451 | 512.7214 | 0.31866 | 35 | 5.2979e-05 | 2968 | 87.4332 | 2013 | 0.0047623 | 0.16668 | 2215 | 0.04 | 2190
1147 | STAFFORD 11011082 | 43201101 | STAFFORD 1101 | 1082 | FALSE | 4959.0869 | 2511.2326 | 1.5607 | 36 | 3.822e-05 | 3296 | 64.7708 | 2123 | 0.0047619 | 0.17143 | 2216 | 1.65 | 659
2516 | MIWUK 17028130 | 163661702 | MIWUK 1702 | 8130 | FALSE | 15961.1359 | 15961.1359 | 9.9199 | 123 | 8.1184e-05 | 2179 | 72.5007 | 2080 | 0.0047602 | 0.5855 | 2217 | 65.59 | 76
2340 | JESSUP 1102CB | 103441102 | JESSUP 1102 | CB | TRUE | 5810.1426 | 159.6823 | 0.099243 | 47 | 0.00010848 | 1437 | 74.8868 | 2068 | 0.0047601 | 0.22372 | 2218 | 0.03 | 2307
10932 | CALPELLA 1102127462 | 43411102 | CALPELLA 1102 | 127462 | TRUE | 205.3095 | 189.2737 | 0.11763 | 2 | 0.00015962 | 647 | 47.5976 | 2225 | 0.0047158 | 0.0094316 | 2219 |  | 3622
9177 | MORAGA 1105829530 | 13801105 | MORAGA 1105 | 829530 | FALSE | 4171.4477 | 2687.7051 | 1.6704 | 32 | 7.4329e-05 | 2348 | 92.7573 | 1991 | 0.0047024 | 0.15048 | 2220 |  | 3320
1591 | SAN JOAQUIN #3 1101673480 | 252531101 | SAN JOAQUIN #3 1101 | 673480 | FALSE | 20487.8392 | 20487.8392 | 12.7333 | 88 | 0.00010713 | 1470 | 66.7652 | 2110 | 0.0046984 | 0.41346 | 2221 |  | 2733
7450 | WILLOW CREEK 1103CB | 192171103 | WILLOW CREEK 1103 | CB | FALSE | 6307.2067 | 6307.2067 | 3.92 | 54 | 0.00038312 | 73 | 17.6674 | 2486 | 0.0046671 | 0.25202 | 2222 | 0.09 | 1518
3048 | LAURELES 1111432 | 182371111 | LAURELES 1111 | 432 | FALSE | 79373.0607 | 79373.0607 | 49.3307 | 320 | 6.1723e-05 | 2728 | 74.7952 | 2069 | 0.0046501 | 1.488 | 2223 | 0.19 | 1170
9657 | PIT NO 5 1101CB | 101321101 | PIT NO 5 1101 | CB | FALSE | 1162.2395 | 1162.2395 | 0.72234 | 10 | 0.00013488 | 929 | 47.6107 | 2224 | 0.0046279 | 0.046279 | 2224 | 0.01 | 2572
2107 | MIRABEL 110238514 | 42091102 | MIRABEL 1102 | 38514 | FALSE | 17257.2473 | 17257.2473 | 10.7254 | 102 | 0.00021556 | 338 | 24.5363 | 2394 | 0.0046099 | 0.47021 | 2225 | 0.75 | 788
4382 | WOODSIDE 11011922 | 24251101 | WOODSIDE 1101 | 1922 | FALSE | 7694.4261 | 7391.7604 | 4.594 | 70 | 0.00019092 | 438 | 30.2755 | 2341 | 0.004588 | 0.32116 | 2226 | 17.29 | 334
4539 | LOS GATOS 110760118 | 82021107 | LOS GATOS 1107 | 60118 | FALSE | 44902.9478 | 44902.9478 | 27.9074 | 323 | 0.00017204 | 550 | 26.0465 | 2376 | 0.0045775 | 1.4785 | 2227 | 45.32 | 149
8332 | VINEYARD 2108MR172 | 14502108 | VINEYARD 2108 | MR172 | TRUE | 1779.1253 | 856.8002 | 0.5325 | 26 | 6.2738e-05 | 2692 | 64.6297 | 2125 | 0.0045679 | 0.11876 | 2228 | 27.77 | 256
4690 | CORRAL 1103681991 | 162991103 | CORRAL 1103 | 681991 | FALSE | 6056.3505 | 2212.0344 | 1.3748 | 50 | 6.8561e-05 | 2521 | 61.126 | 2147 | 0.0045171 | 0.22586 | 2229 |  | 2909
10188 | BOLINAS 11011232 | 42261101 | BOLINAS 1101 | 1232 | FALSE | 3935.7724 | 3637.3088 | 2.2606 | 22 | 9.124e-05 | 1868 | 55.6272 | 2178 | 0.0045024 | 0.099054 | 2230 | 3.14 | 560
4590 | REDBUD 11021212 | 43191102 | REDBUD 1102 | 1212 | TRUE | 6586.9975 | 0 | 0 | 62 | 4.464e-05 | 3173 | 87.4084 | 2014 | 0.0044984 | 0.2789 | 2231 | 0.42 | 928
6700 | TIVY VALLEY 1107CB | 252941107 | TIVY VALLEY 1107 | CB | TRUE | 35309.4801 | 290.0531 | 0.18027 | 155 | 3.607e-05 | 3336 | 256.8183 | 1529 | 0.0044835 | 0.69495 | 2232 |  | 3056
7824 | CAYUCOS 1102317156 | 182551102 | CAYUCOS 1102 | 317156 | FALSE | 18303.2443 | 3816.311 | 2.3719 | 67 | 5.1745e-05 | 3000 | 86.4803 | 2018 | 0.0044039 | 0.29506 | 2233 |  | 3166
9117 | WEST POINT 11021535 | 163201102 | WEST POINT 1102 | 1535 | FALSE | 4933.5895 | 4933.5895 | 3.0662 | 30 | 6.0964e-05 | 2749 | 63.4215 | 2132 | 0.0043786 | 0.13136 | 2234 | 52.41 | 112
1000 | MORGAN HILL 2111CB | 83242111 | MORGAN HILL 2111 | CB | TRUE | 3629.5545 | 353.0082 | 0.2194 | 38 | 5.0792e-05 | 3020 | 63.168 | 2135 | 0.0043636 | 0.16582 | 2235 | 0.22 | 1127
9339 | LAKEWOOD 2109432198 FM | 13532109 | LAKEWOOD 2109 | 432198 FM | TRUE | 3829.098 | 907.0096 | 0.56371 | 31 | 7.0176e-05 | 2467 | 53.7914 | 2188 | 0.004363 | 0.13525 | 2236 |  | 3344
420 | ARCATA 11225384 | 192021122 | ARCATA 1122 | 5384 | FALSE | 28128.0957 | 25050.2712 | 15.5688 | 202 | 0.0002103 | 356 | 21.9397 | 2426 | 0.0043604 | 0.88081 | 2237 | 0.18 | 1214
268 | MIRABEL 1102332 | 42091102 | MIRABEL 1102 | 332 | FALSE | 9174.8238 | 9174.8238 | 5.7022 | 67 | 0.00022781 | 292 | 15.3212 | 2526 | 0.0043573 | 0.29194 | 2238 | 30.76 | 235
6281 | MONTE RIO 11131989 | 42811113 | MONTE RIO 1113 | 1989 | FALSE | 1195.1936 | 1195.1936 | 0.74282 | 9 | 0.00014388 | 816 | 55.5275 | 2179 | 0.0043487 | 0.039138 | 2239 | 44.54 | 158
11081 | OAKHURST 110310723 | 254421103 | OAKHURST 1103 | 10723 | TRUE | 6.3415 | 6.3415 | 0.0039412 | 1 | 9.0549e-05 | 1895 | 47.5921 | 2226 | 0.0043094 | 0.0043094 | 2240 | 48.3 | 130
8151 | SILVERADO 2105309298 | 43432105 | SILVERADO 2105 | 309298 | FALSE | 3091.9426 | 1768.6422 | 1.0992 | 23 | 9.5445e-05 | 1744 | 39.3183 | 2281 | 0.0043094 | 0.099116 | 2241 |  | 3197
4858 | GUALALA 111223444 | 42841112 | GUALALA 1112 | 23444 | FALSE | 23380.6907 | 23380.6907 | 14.5312 | 135 | 0.00010219 | 1599 | 47.2338 | 2229 | 0.0042666 | 0.57599 | 2242 | 0.12 | 1396
2658 | CAMP EVERS 210660124 | 83622106 | CAMP EVERS 2106 | 60124 | FALSE | 36140.2282 | 36140.2282 | 22.4613 | 267 | 0.00016531 | 587 | 37.1047 | 2296 | 0.0042657 | 1.1389 | 2243 | 77.48 | 53
7144 | BELLEVUE 1102392 | 43181102 | BELLEVUE 1102 | 392 | TRUE | 10922.1116 | 404.9115 | 0.25165 | 68 | 9.4205e-05 | 1789 | 58.5408 | 2165 | 0.0042431 | 0.28853 | 2244 | 0.28 | 1035
5164 | MORAGA 1104N532R | 13801104 | MORAGA 1104 | N532R | FALSE | 7429.2796 | 5942.762 | 3.6935 | 65 | 9.0315e-05 | 1903 | 44.8885 | 2247 | 0.004228 | 0.27482 | 2245 | 0.09 | 1560
9096 | BIG BASIN 11022253 | 82841102 | BIG BASIN 1102 | 2253 | FALSE | 2335.3363 | 2335.3363 | 1.4514 | 12 | 0.00020821 | 370 | 19.8765 | 2451 | 0.0041981 | 0.050377 | 2246 | 0.17 | 1238
4580 | WEST POINT 11021341 | 163201102 | WEST POINT 1102 | 1341 | FALSE | 15927.2159 | 15927.2159 | 9.8988 | 87 | 5.9226e-05 | 2799 | 79.2605 | 2052 | 0.0041901 | 0.36454 | 2247 | 0.52 | 886
2630 | MC ARTHUR 110153120 | 103491101 | MC ARTHUR 1101 | 53120 | TRUE | 12732.032 | 173.1766 | 0.10763 | 92 | 2.9816e-05 | 3429 | 159.0093 | 1750 | 0.004183 | 0.38483 | 2248 |  | 2793
9114 | LAS GALLINAS A 1105CB | 42991105 | LAS GALLINAS A 1105 | CB | TRUE | 3345.6946 | 710.3038 | 0.44146 | 26 | 0.00011363 | 1329 | 21.0918 | 2434 | 0.0041416 | 0.10768 | 2249 | 0.02 | 2541
2500 | EL DORADO PH 2101CB | 152762101 | EL DORADO PH 2101 | CB | FALSE | 11999.4505 | 11999.4505 | 7.4577 | 74 | 0.00013448 | 935 | 29.3004 | 2350 | 0.0041406 | 0.3064 | 2250 | 69.29 | 70
2083 | ALTO 11201214 | 42031120 | ALTO 1120 | 1214 | FALSE | 7293.1721 | 5549.8668 | 3.4493 | 45 | 4.7944e-05 | 3095 | 64.0131 | 2129 | 0.004132 | 0.18594 | 2251 | 0.05 | 2016
1240 | EL DORADO PH 210126000 | 152762101 | EL DORADO PH 2101 | 26000 | FALSE | 55311.5705 | 55311.5705 | 34.3764 | 339 | 0.00010511 | 1521 | 49.7196 | 2212 | 0.0041222 | 1.3974 | 2252 | 73.15 | 63
2830 | MENLO 11029110 | 24131102 | MENLO 1102 | 9110 | FALSE | 15217.7544 | 1491.4373 | 0.92693 | 138 | 0.00014546 | 798 | 26.6167 | 2370 | 0.0040502 | 0.55893 | 2253 | 0.04 | 2097
8665 | BRUNSWICK 111094368 | 152481110 | BRUNSWICK 1110 | 94368 | TRUE | 768.9303 | 596.3821 | 0.37065 | 9 | 0.00048312 | 36 | 49.2875 | 2214 | 0.0040353 | 0.036317 | 2254 | 0.02 | 2527
2181 | MERCED FALLS 110222774 | 252811102 | MERCED FALLS 1102 | 22774 | FALSE | 5970.2453 | 1624.1247 | 1.0094 | 27 | 3.9002e-05 | 3287 | 127.212 | 1851 | 0.0040151 | 0.10841 | 2255 | 0.01 | 2610
2725 | BIG BASIN 110212124 | 82841102 | BIG BASIN 1102 | 12124 | FALSE | 7217.2962 | 7217.2962 | 4.4856 | 59 | 0.000304 | 126 | 21.0181 | 2436 | 0.0040119 | 0.2367 | 2256 | 0.28 | 1041
1448 | PARADISE 1103CB | 102831103 | PARADISE 1103 | CB | FALSE | 5575.8129 | 2217.6155 | 1.3783 | 61 | 0.0006536 | 11 | 4.7351 | 2763 | 0.0039747 | 0.24245 | 2257 | 15.11 | 350
3467 | WEIMAR 11012740 | 152491101 | WEIMAR 1101 | 2740 | FALSE | 30939.0056 | 30939.0056 | 19.2287 | 235 | 0.00018236 | 494 | 38.193 | 2288 | 0.003969 | 0.93271 | 2258 | 0.14 | 1313
497 | AUBURN 1101173014 | 152161101 | AUBURN 1101 | 173014 | FALSE | 5456.0353 | 5290.5313 | 3.2881 | 43 | 0.00018414 | 479 | 19.9675 | 2449 | 0.0039357 | 0.16924 | 2259 |  | 2680
7194 | WEST POINT 1101L373 | 163201101 | WEST POINT 1101 | L373 | FALSE | 11899.5211 | 11899.5211 | 7.3956 | 93 | 5.9702e-05 | 2784 | 62.944 | 2136 | 0.0039044 | 0.36311 | 2260 | 72.86 | 65
6474 | STAFFORD 11021048 | 43201102 | STAFFORD 1102 | 1048 | FALSE | 8484.8832 | 8484.8832 | 5.2734 | 72 | 0.00016147 | 626 | 26.1474 | 2375 | 0.0039018 | 0.28093 | 2261 | 0.13 | 1345
4378 | RESERVATION ROAD 110222136 | 182731102 | RESERVATION ROAD 1102 | 22136 | FALSE | 8542.0356 | 2842.9957 | 1.7669 | 59 | 4.541e-05 | 3155 | 51.6014 | 2204 | 0.0038829 | 0.22909 | 2262 | 0.01 | 2587
7747 | ANITA 1106552724 | 102841106 | ANITA 1106 | 552724 | FALSE | 23613.9534 | 2363.8176 | 1.4691 | 77 | 7.2387e-05 | 2405 | 63.51 | 2130 | 0.0038689 | 0.29791 | 2263 |  | 3158
6189 | PLACER 1101106534 | 152461101 | PLACER 1101 | 106534 | FALSE | 4199.7803 | 1949.2483 | 1.2115 | 38 | 0.00024793 | 223 | 15.6992 | 2522 | 0.0038425 | 0.14601 | 2264 |  | 3012
8134 | MORAGA 110518396 | 13801105 | MORAGA 1105 | 18396 | TRUE | 1851.7327 | 293.2889 | 0.18228 | 16 | 3.5702e-05 | 3339 | 53.4957 | 2191 | 0.0038298 | 0.061277 | 2265 | 4.8 | 506
2828 | PANORAMA 11019092 | 103461101 | PANORAMA 1101 | 9092 | TRUE | 15725.9351 | 255.1238 | 0.15856 | 113 | 0.0001025 | 1589 | 29.6083 | 2349 | 0.0038237 | 0.43208 | 2266 | 1.99 | 627
1451 | MIWUK 1701953336 | 163661701 | MIWUK 1701 | 953336 | FALSE | 19079.6136 | 19079.6136 | 11.8581 | 132 | 9.944e-05 | 1658 | 31.4057 | 2336 | 0.0038168 | 0.50381 | 2267 |  | 2724
8189 | CAMP EVERS 210660120 | 83622106 | CAMP EVERS 2106 | 60120 | FALSE | 6993.663 | 6993.663 | 4.3466 | 42 | 0.0001694 | 567 | 23.8386 | 2403 | 0.0038109 | 0.16006 | 2268 | 27.45 | 257
3086 | PANOCHE 11034016 | 253671103 | PANOCHE 1103 | 4016 | FALSE | 20664.9565 | 3776.8409 | 2.3473 | 59 | 4.6142e-05 | 3134 | 98.5723 | 1963 | 0.0038045 | 0.22447 | 2269 | 0.01 | 2621
3744 | FORESTHILL 110150486 | 152181101 | FORESTHILL 1101 | 50486 | FALSE | 18786.575 | 18786.575 | 11.6759 | 163 | 0.00010932 | 1425 | 43.079 | 2261 | 0.0037623 | 0.61325 | 2270 | 86.95 | 38
1371 | PINE GROVE 11021222 | 163751102 | PINE GROVE 1102 | 1222 | FALSE | 27771.0153 | 27771.0153 | 17.2598 | 218 | 0.0001881 | 453 | 22.6532 | 2414 | 0.0037571 | 0.81905 | 2271 | 105.89 | 18
2904 | MONTE RIO 111153477 | 42811111 | MONTE RIO 1111 | 53477 | FALSE | 3295.7871 | 3295.7871 | 2.0483 | 21 | 0.00016065 | 635 | 22.7228 | 2413 | 0.0037529 | 0.078812 | 2272 | 34.99 | 215
4467 | RINCON 1102CB | 43321102 | RINCON 1102 | CB | FALSE | 5699.8132 | 4772.4685 | 2.9661 | 49 | 0.00014009 | 868 | 39.048 | 2283 | 0.0037209 | 0.18233 | 2273 | 0.11 | 1423
4949 | BRENTWOOD 210598606 | 14592105 | BRENTWOOD 2105 | 98606 | TRUE | 13179.7667 | 138.4782 | 0.086065 | 88 | 8.8531e-05 | 1972 | 91.908 | 1993 | 0.0037138 | 0.32681 | 2274 |  | 2931
8946 | MIRABEL 110213597 | 42091102 | MIRABEL 1102 | 13597 | TRUE | 751.816 | 751.816 | 0.46726 | 6 | 0.00014116 | 850 | 23.8355 | 2404 | 0.0037122 | 0.022273 | 2275 | 8.42 | 427
3893 | FAIRVIEW 2207P304 | 13432207 | FAIRVIEW 2207 | P304 | FALSE | 9851.3779 | 8440.4652 | 5.2458 | 47 | 9.3563e-05 | 1809 | 31.6902 | 2333 | 0.0037077 | 0.17426 | 2276 | 0.09 | 1556
7178 | BURNEY 11019042 | 103311101 | BURNEY 1101 | 9042 | FALSE | 5080.7921 | 5080.7921 | 3.1577 | 31 | 4.1887e-05 | 3227 | 82.8476 | 2036 | 0.0036996 | 0.11469 | 2277 | 0.11 | 1447
8790 | MONTICELLO 110152910 | 43051101 | MONTICELLO 1101 | 52910 | FALSE | 5038.2048 | 3510.8305 | 2.182 | 41 | 5.3924e-05 | 2944 | 73.7782 | 2074 | 0.0036877 | 0.1512 | 2278 | 0.81 | 773
8586 | WEST POINT 1102L3733 | 163201102 | WEST POINT 1102 | L3733 | FALSE | 2820.1267 | 2820.1267 | 1.7527 | 22 | 6.6103e-05 | 2585 | 57.3124 | 2169 | 0.0036798 | 0.080956 | 2279 | 42.03 | 171
2143 | VOLTA 11029742 | 102541102 | VOLTA 1102 | 9742 | FALSE | 14685.6636 | 14685.6636 | 9.1272 | 120 | 4.1561e-05 | 3232 | 86.0041 | 2023 | 0.0036718 | 0.44061 | 2280 | 37.7 | 200
8195 | SAUSALITO 11021268 | 42491102 | SAUSALITO 1102 | 1268 | FALSE | 7937.7862 | 7937.7862 | 4.9334 | 46 | 4.2343e-05 | 3219 | 82.2871 | 2039 | 0.0036642 | 0.16855 | 2281 | 0.09 | 1520
200 | PETALUMA C 1109270 | 42631109 | PETALUMA C 1109 | 270 | FALSE | 12312.4188 | 3397.4138 | 2.1115 | 101 | 2.7315e-05 | 3467 | 46.9819 | 2234 | 0.0036568 | 0.36934 | 2282 | 0.04 | 2120
9326 | COARSEGOLD 2102383092 | 254432102 | COARSEGOLD 2102 | 383092 | TRUE | 613.1926 | 613.1926 | 0.3811 | 5 | 0.00016062 | 636 | 14.3241 | 2544 | 0.0036345 | 0.018173 | 2283 | 0.2 | 1163
10306 | SOLEDAD 1114413916 | 182051114 | SOLEDAD 1114 | 413916 | FALSE | 6367.8068 | 2275.8898 | 1.4145 | 24 | 2.8421e-05 | 3448 | 60.5803 | 2151 | 0.0036248 | 0.086994 | 2284 |  | 3529
6836 | LLAGAS 2106338878 | 83182106 | LLAGAS 2106 | 338878 | FALSE | 7522.3054 | 3300.0012 | 2.051 | 23 | 6.6373e-05 | 2579 | 72.1128 | 2083 | 0.0036203 | 0.083266 | 2285 |  | 3067
685 | MONTE RIO 1113524 | 42811113 | MONTE RIO 1113 | 524 | FALSE | 10078.6837 | 10078.6837 | 6.2639 | 76 | 0.00026116 | 193 | 18.5187 | 2467 | 0.0036171 | 0.2749 | 2286 | 109.05 | 15
3555 | DUNBAR 1103CB | 43071103 | DUNBAR 1103 | CB | FALSE | 19272.7585 | 4335.2228 | 2.6944 | 149 | 0.00011557 | 1285 | 29.7426 | 2348 | 0.0036086 | 0.53768 | 2287 | 1.01 | 729
6157 | IGNACIO 11041290 | 42481104 | IGNACIO 1104 | 1290 | FALSE | 20913.8819 | 6586.7468 | 4.0937 | 126 | 8.6173e-05 | 2030 | 27.953 | 2362 | 0.0035797 | 0.45104 | 2288 | 0.02 | 2529
1177 | ORO FINO 1101CB | 103031101 | ORO FINO 1101 | CB | FALSE | 35929.6836 | 35929.6836 | 22.3304 | 271 | 0.00017817 | 517 | 43.307 | 2257 | 0.0035789 | 0.96987 | 2289 | 173.81 | 3
3178 | PENNGROVE 1101461338 | 43471101 | PENNGROVE 1101 | 461338 | FALSE | 2872.7742 | 2872.7742 | 1.7854 | 24 | 9.4013e-05 | 1793 | 40.8144 | 2273 | 0.0035591 | 0.085418 | 2290 |  | 2814
3360 | GRASS VALLEY 1101CB | 152031101 | GRASS VALLEY 1101 | CB | FALSE | 3780.8041 | 1415.7705 | 0.87991 | 32 | 0.00022566 | 302 | 20.6051 | 2441 | 0.0035509 | 0.11363 | 2291 | 2.79 | 582
10815 | HICKS 2101949522 | 83432101 | HICKS 2101 | 949522 | TRUE | 726.8328 | 708.2171 | 0.44016 | 2 | 0.00014682 | 775 | 72.2883 | 2082 | 0.0035464 | 0.0070929 | 2292 |  | 3609
6548 | WEST POINT 110113444 | 163201101 | WEST POINT 1101 | 13444 | FALSE | 27386.8447 | 27386.8447 | 17.021 | 221 | 7.9645e-05 | 2218 | 41.9022 | 2268 | 0.0035258 | 0.77919 | 2293 | 73.64 | 59
2950 | HICKS 2101XR162 | 83432101 | HICKS 2101 | XR162 | TRUE | 14645.8548 | 989.1765 | 0.61478 | 122 | 5.6508e-05 | 2874 | 50.8473 | 2208 | 0.0035232 | 0.42983 | 2294 | 0.05 | 1985
9560 | VINEYARD 2107246084 | 14502107 | VINEYARD 2107 | 246084 | TRUE | 830.435 | 385.2443 | 0.23943 | 7 | 7.141e-05 | 2435 | 49.9181 | 2211 | 0.0035033 | 0.024523 | 2295 |  | 3377
3073 | CAMP EVERS 210510728 | 83622105 | CAMP EVERS 2105 | 10728 | FALSE | 16852.1183 | 16852.1183 | 10.4737 | 134 | 0.00034915 | 91 | 6.6304 | 2693 | 0.0034865 | 0.46719 | 2296 | 1.09 | 717
7203 | BRUNSWICK 110663124 | 152481106 | BRUNSWICK 1106 | 63124 | FALSE | 9481.8427 | 9481.8427 | 5.893 | 65 | 0.00021667 | 333 | 31.8764 | 2329 | 0.0034764 | 0.22596 | 2297 | 31.64 | 228
7594 | SHINGLE SPRINGS 2108CB | 153652108 | SHINGLE SPRINGS 2108 | CB | FALSE | 2376.1029 | 2376.1029 | 1.4768 | 18 | 0.00021932 | 326 | 147.9963 | 1784 | 0.0034725 | 0.062504 | 2298 | 0.24 | 1098
180 | HIGGINS 11041374 | 152691104 | HIGGINS 1104 | 1374 | FALSE | 13460.5941 | 12470.1527 | 7.7503 | 117 | 0.0001756 | 523 | 21.2592 | 2433 | 0.0034694 | 0.40592 | 2299 | 0.12 | 1408
8764 | TRES PINOS 1111203126 | 183221111 | TRES PINOS 1111 | 203126 | TRUE | 10848.7001 | 107.4611 | 0.066788 | 58 | 6.8097e-05 | 2533 | 54.2531 | 2186 | 0.0034419 | 0.19963 | 2300 |  | 3261
6133 | SALT SPRINGS 210237300 | 163692102 | SALT SPRINGS 2102 | 37300 | FALSE | 11208.5924 | 11208.5924 | 6.9662 | 41 | 9.1788e-05 | 1851 | 39.4946 | 2278 | 0.0034152 | 0.14002 | 2301 | 37.82 | 198
8353 | VOLTA 110254932 | 102541102 | VOLTA 1102 | 54932 | FALSE | 7042.6654 | 7042.6654 | 4.377 | 46 | 5.4607e-05 | 2930 | 80.6481 | 2045 | 0.0034144 | 0.15706 | 2302 | 25.23 | 272
1504 | HUMBOLDT BAY 1102741980 | 192341102 | HUMBOLDT BAY 1102 | 741980 | FALSE | 15211.0337 | 9241.1429 | 5.7434 | 81 | 0.00018104 | 504 | 20.6165 | 2440 | 0.0034064 | 0.27592 | 2303 |  | 2729
341 | COTATI 1102464 | 42271102 | COTATI 1102 | 464 | FALSE | 13038.4156 | 3443.5911 | 2.1402 | 103 | 8.8656e-05 | 1965 | 37.0346 | 2297 | 0.0034005 | 0.35026 | 2304 | 0.04 | 2168
1877 | FORT BRAGG A 110231304 | 42761102 | FORT BRAGG A 1102 | 31304 | FALSE | 34880.3162 | 34880.3162 | 21.6783 | 119 | 0.00010968 | 1417 | 25.8228 | 2381 | 0.0033857 | 0.40289 | 2305 | 0.23 | 1121
9731 | FITCH MOUNTAIN 1111792628 | 42751111 | FITCH MOUNTAIN 1111 | 792628 | TRUE | 1482.8091 | 365.6177 | 0.22723 | 13 | 7.1975e-05 | 2420 | 145.9054 | 1789 | 0.0033779 | 0.043913 | 2306 |  | 3408
10338 | FRANKLIN 1104P146 | 13921104 | FRANKLIN 1104 | P146 | FALSE | 5911.5651 | 5843.5425 | 3.6318 | 36 | 0.00010288 | 1572 | 24.7391 | 2392 | 0.0033674 | 0.12123 | 2307 | 0.05 | 1925
11025 | CALPINE 1144304 | 48011144 | CALPINE 1144 | 304 | TRUE | 74.6067 | 74.6067 | 0.046368 | 2 | 0.00013842 | 890 | 24.2406 | 2399 | 0.0033555 | 0.006711 | 2308 | 0.18 | 1213
7073 | RINCON 1101663641 | 43321101 | RINCON 1101 | 663641 | FALSE | 1909.334 | 1173.5613 | 0.72937 | 13 | 0.00014217 | 836 | 35.4244 | 2307 | 0.0033545 | 0.043609 | 2309 |  | 3093
37 | CURTIS 17019230 | 163351701 | CURTIS 1701 | 9230 | FALSE | 5065.9524 | 4064.6381 | 2.5262 | 41 | 0.00012174 | 1152 | 32.1288 | 2327 | 0.0033425 | 0.13704 | 2310 | 0.04 | 2191
7129 | GANSNER 1101336664 | 103021101 | GANSNER 1101 | 336664 | FALSE | 2515.571 | 1158.7417 | 0.72016 | 16 | 6.759e-05 | 2546 | 46.5783 | 2238 | 0.0033324 | 0.053319 | 2311 |  | 3098
6003 | CALPELLA 1102477890 | 43411102 | CALPELLA 1102 | 477890 | FALSE | 4846.0499 | 1726.9794 | 1.0733 | 35 | 9.2097e-05 | 1839 | 48.2183 | 2219 | 0.0033264 | 0.11642 | 2312 |  | 2995
6936 | LAMONT 11024222 | 253911102 | LAMONT 1102 | 4222 | FALSE | 26146.3036 | 4245.3884 | 2.6385 | 87 | 3.1604e-05 | 3407 | 230.387 | 1585 | 0.0033258 | 0.28934 | 2313 | 0.02 | 2510
1031 | VOLTA 110253130 | 102541102 | VOLTA 1102 | 53130 | FALSE | 22213.2961 | 22213.2961 | 13.8057 | 168 | 4.8271e-05 | 3088 | 94.8297 | 1982 | 0.0033207 | 0.55788 | 2314 | 57.28 | 97
729 | RADUM 1105806392 | 13151105 | RADUM 1105 | 806392 | FALSE | 8744.0051 | 5446.9277 | 3.3853 | 79 | 6.382e-05 | 2652 | 38.9119 | 2286 | 0.0033155 | 0.26192 | 2315 |  | 2691
6737 | POINT ARENA 1101476 | 43381101 | POINT ARENA 1101 | 476 | FALSE | 24463.8896 | 4825.127 | 2.9988 | 97 | 4.5962e-05 | 3139 | 73.5453 | 2078 | 0.0032902 | 0.31915 | 2316 | 0.02 | 2460
9971 | LOS OSITOS 2103258688 | 182082103 | LOS OSITOS 2103 | 258688 | FALSE | 5700.7117 | 1727.2951 | 1.0735 | 17 | 1.3021e-05 | 3601 | 51.8497 | 2202 | 0.0032882 | 0.0559 | 2317 |  | 3463
2467 | HARRIS 1109183860 | 192431109 | HARRIS 1109 | 183860 | FALSE | 12288.1398 | 7942.1796 | 4.9361 | 92 | 0.00018091 | 505 | 20.123 | 2446 | 0.0032843 | 0.30215 | 2318 |  | 2779
3741 | PINE GROVE 110152088 | 163751101 | PINE GROVE 1101 | 52088 | FALSE | 3986.2342 | 3986.2342 | 2.4775 | 28 | 0.00019225 | 433 | 17.8963 | 2482 | 0.0032783 | 0.091793 | 2319 | 0.06 | 1856
8487 | PIT NO 3 21011482 | 103732101 | PIT NO 3 2101 | 1482 | FALSE | 19365.2645 | 19365.2645 | 12.0356 | 43 | 0.0001494 | 744 | 53.6934 | 2189 | 0.0032735 | 0.14076 | 2320 | 0.01 | 2603
9213 | GREEN VALLEY 210197574 | 83192101 | GREEN VALLEY 2101 | 97574 | FALSE | 8779.1351 | 5743.5714 | 3.5697 | 60 | 8.4627e-05 | 2073 | 42.7148 | 2264 | 0.0032547 | 0.19528 | 2321 |  | 3327
6945 | CHOLAME 2102X06 | 182562102 | CHOLAME 2102 | X06 | TRUE | 20798.4951 | 651.9578 | 0.40519 | 40 | 5.1105e-05 | 3012 | 121.2254 | 1866 | 0.0032533 | 0.13013 | 2322 | 0.03 | 2295
1559 | PAUL SWEET 21065178 | 83252106 | PAUL SWEET 2106 | 5178 | FALSE | 11550.9267 | 11550.9267 | 7.1789 | 84 | 0.0001826 | 491 | 17.8913 | 2483 | 0.0032408 | 0.27223 | 2323 | 0.58 | 856
8048 | DEL MONTE 21042762 | 182222104 | DEL MONTE 2104 | 2762 | FALSE | 17774.3074 | 15060.1277 | 9.3599 | 138 | 9.1063e-05 | 1879 | 28.3252 | 2356 | 0.0032245 | 0.44498 | 2324 | 0.08 | 1622
394 | WOODSIDE 11049032 | 24251104 | WOODSIDE 1104 | 9032 | FALSE | 7741.5059 | 3452.7748 | 2.1459 | 72 | 0.00021411 | 342 | 20.493 | 2443 | 0.0032245 | 0.23216 | 2325 | 0.08 | 1581
3140 | BAYWOOD 1101CB | 182801101 | BAYWOOD 1101 | CB | FALSE | 46476.8109 | 7426.5465 | 4.6156 | 214 | 5.8116e-05 | 2833 | 45.5892 | 2241 | 0.003207 | 0.6863 | 2326 | 0.02 | 2421
197 | BRUNSWICK 1105733408 | 152481105 | BRUNSWICK 1105 | 733408 | FALSE | 5546.1563 | 5546.1563 | 3.447 | 45 | 0.00017527 | 527 | 18.0229 | 2479 | 0.0032065 | 0.14429 | 2327 |  | 2660
1600 | RINCON 1104786782 | 43321104 | RINCON 1104 | 786782 | FALSE | 5173.0207 | 3549.2326 | 2.2059 | 46 | 0.00014664 | 779 | 8.3437 | 2661 | 0.0032053 | 0.14745 | 2328 |  | 2734
7931 | PIT NO 5 11011658 | 101321101 | PIT NO 5 1101 | 1658 | FALSE | 7306.3402 | 7306.3402 | 4.5409 | 25 | 0.0001398 | 870 | 46.6629 | 2236 | 0.0031839 | 0.079597 | 2329 | 0.02 | 2471
4023 | DUNLAP 11037080 | 254061103 | DUNLAP 1103 | 7080 | FALSE | 17026.2434 | 17026.2434 | 10.5819 | 67 | 5.6266e-05 | 2881 | 33.4031 | 2317 | 0.0031698 | 0.21238 | 2330 | 0 | 2646
7290 | ARCATA 1121716954 | 192021121 | ARCATA 1121 | 716954 | FALSE | 18261.1322 | 11115.6995 | 6.9085 | 97 | 0.00020479 | 383 | 15.7424 | 2521 | 0.0031691 | 0.30741 | 2331 |  | 3112
8705 | CARLOTTA 112144150 | 192291121 | CARLOTTA 1121 | 44150 | FALSE | 5746.8082 | 5746.8082 | 3.5717 | 13 | 9.8025e-05 | 1689 | 54.8965 | 2182 | 0.0031685 | 0.04119 | 2332 | 0 | 2641
5063 | WOODSIDE 11043583 | 24251104 | WOODSIDE 1104 | 3583 | FALSE | 4565.0094 | 4565.0094 | 2.8372 | 38 | 0.00013592 | 920 | 25.7125 | 2385 | 0.0031615 | 0.12014 | 2333 | 0.78 | 781
8125 | PINE GROVE 1101CB | 163751101 | PINE GROVE 1101 | CB | FALSE | 6922.9717 | 6922.9717 | 4.3027 | 57 | 0.00036472 | 81 | 15.0767 | 2531 | 0.0031502 | 0.17956 | 2334 | 10.19 | 401
6730 | CAMP EVERS 210637210 | 83622106 | CAMP EVERS 2106 | 37210 | FALSE | 9746.716 | 9746.716 | 6.0576 | 65 | 0.00021978 | 324 | 16.5241 | 2509 | 0.0031442 | 0.20437 | 2335 | 0.45 | 916
82 | SNEATH LANE 1107CB | 22721107 | SNEATH LANE 1107 | CB | FALSE | 6249.0561 | 1615.0564 | 1.0038 | 45 | 3.6368e-05 | 3327 | 61.4823 | 2144 | 0.003121 | 0.14045 | 2336 | 0.03 | 2317
1487 | STAFFORD 11021258 | 43201102 | STAFFORD 1102 | 1258 | TRUE | 7855.298 | 501.9247 | 0.31195 | 65 | 3.9619e-05 | 3275 | 27.811 | 2365 | 0.0031184 | 0.2027 | 2337 |  | 2726
201 | RESERVATION ROAD 1101CB | 182731101 | RESERVATION ROAD 1101 | CB | FALSE | 15128.6127 | 8212.888 | 5.1043 | 106 | 2.9958e-05 | 3427 | 117.1254 | 1887 | 0.0031059 | 0.32923 | 2338 | 0.03 | 2246
9832 | WILLOW CREEK 1101CB | 192171101 | WILLOW CREEK 1101 | CB | TRUE | 460.8364 | 460.8364 | 0.28641 | 6 | 0.00063458 | 14 | 4.0266 | 2776 | 0.0031037 | 0.018622 | 2339 | 7.35 | 448
22 | PARADISE 1104457900 | 102831104 | PARADISE 1104 | 457900 | FALSE | 26252.3118 | 19380.7293 | 12.0452 | 208 | 0.00047135 | 40 | 18.1285 | 2474 | 0.0030985 | 0.64448 | 2340 |  | 2650
7703 | SILVERADO 21051306 | 43432105 | SILVERADO 2105 | 1306 | TRUE | 6582.7615 | 393.5916 | 0.24462 | 55 | 0.00018261 | 490 | 20.3553 | 2444 | 0.0030939 | 0.17016 | 2341 | 9.44 | 409
8415 | BIG MEADOWS 21012476 | 102812101 | BIG MEADOWS 2101 | 2476 | FALSE | 14000.8931 | 13050.7122 | 8.1111 | 75 | 7.3608e-05 | 2378 | 31.4311 | 2335 | 0.0030704 | 0.23028 | 2342 | 0.03 | 2379
2480 | REDBUD 1101CB | 43191101 | REDBUD 1101 | CB | FALSE | 11764.5735 | 5407.5285 | 3.3608 | 91 | 5.0448e-05 | 3027 | 32.7091 | 2324 | 0.0030523 | 0.27776 | 2343 | 0.09 | 1557
10178 | MAPLE CREEK 1101555034 | 192101101 | MAPLE CREEK 1101 | 555034 | FALSE | 4077.2208 | 2404.9179 | 1.4947 | 8 | 0.00031076 | 117 | 13.913 | 2553 | 0.0030461 | 0.024368 | 2344 |  | 3508
1443 | MENLO 11028952 | 24131102 | MENLO 1102 | 8952 | FALSE | 10739.4056 | 10739.4056 | 6.6746 | 82 | 0.0001072 | 1467 | 39.4973 | 2277 | 0.0030386 | 0.24916 | 2345 | 9.23 | 411
5316 | PAUL SWEET 210610424 | 83252106 | PAUL SWEET 2106 | 10424 | FALSE | 11629.4934 | 9151.9906 | 5.688 | 87 | 0.00013475 | 931 | 22.367 | 2420 | 0.0030267 | 0.26332 | 2346 | 0.25 | 1072
2267 | ELK 11011298 | 42981101 | ELK 1101 | 1298 | FALSE | 25951.4505 | 19969.5788 | 12.4112 | 119 | 7.3623e-05 | 2376 | 48.6421 | 2217 | 0.0030233 | 0.35978 | 2347 | 0.03 | 2376
6724 | CURTIS 17039210 | 163351703 | CURTIS 1703 | 9210 | FALSE | 36192.6146 | 36192.6146 | 22.4939 | 124 | 4.5003e-05 | 3160 | 67.0376 | 2108 | 0.0030209 | 0.37459 | 2348 | 0.31 | 1004
3063 | ELECTRA 1101L1697 | 162161101 | ELECTRA 1101 | L1697 | FALSE | 9283.5435 | 9283.5435 | 5.7698 | 70 | 8.7849e-05 | 1988 | 45.9015 | 2240 | 0.0030208 | 0.21145 | 2349 | 2.74 | 585
8682 | CLARKSVILLE 210951744 | 153612109 | CLARKSVILLE 2109 | 51744 | FALSE | 2867.8226 | 2099.9047 | 1.3051 | 25 | 0.00013923 | 883 | 25.8185 | 2382 | 0.0030149 | 0.075372 | 2350 | 0.2 | 1162
6410 | SILVERADO 2105616 | 43432105 | SILVERADO 2105 | 616 | TRUE | 12968.0682 | 798.8754 | 0.4965 | 103 | 0.00011091 | 1393 | 20.2831 | 2445 | 0.0030112 | 0.31016 | 2351 | 0.3 | 1020
2231 | HICKS 2103LB50 | 83432103 | HICKS 2103 | LB50 | FALSE | 18304.0568 | 18130.2581 | 11.268 | 65 | 0.00012813 | 1046 | 26.2606 | 2373 | 0.0029902 | 0.19436 | 2352 | 0.21 | 1142
1742 | MIWUK 1701CB | 163661701 | MIWUK 1701 | CB | FALSE | 26145.2982 | 26145.2982 | 16.2494 | 187 | 8.1435e-05 | 2170 | 64.1413 | 2128 | 0.0029901 | 0.55914 | 2353 | 197.3 | 2
4916 | SARATOGA 1107167792 | 83371107 | SARATOGA 1107 | 167792 | FALSE | 7540.5809 | 7540.5809 | 4.6865 | 48 | 0.00016417 | 599 | 22.3539 | 2421 | 0.0029842 | 0.14324 | 2354 | 27.41 | 258
55 | CURTIS 170234426 | 163351702 | CURTIS 1702 | 34426 | FALSE | 11062.821 | 7591.2944 | 4.718 | 81 | 0.0001041 | 1549 | 18.642 | 2465 | 0.0029697 | 0.24054 | 2355 | 0.2 | 1161
4236 | LOS GATOS 1106LA64 | 82021106 | LOS GATOS 1106 | LA64 | FALSE | 20425.5788 | 20425.5788 | 12.6946 | 152 | 0.00024137 | 243 | 12.4217 | 2580 | 0.0029684 | 0.4512 | 2356 | 0.94 | 741
6476 | PAUL SWEET 21068091 | 83252106 | PAUL SWEET 2106 | 8091 | FALSE | 9678.478 | 9678.478 | 6.0152 | 69 | 0.00018296 | 489 | 17.2834 | 2497 | 0.0029648 | 0.20457 | 2357 | 0.38 | 961
7197 | BIG BASIN 110212758 | 82841102 | BIG BASIN 1102 | 12758 | FALSE | 9624.9945 | 9624.9945 | 5.982 | 70 | 0.00033735 | 98 | 10.9337 | 2611 | 0.002947 | 0.20629 | 2358 | 6.96 | 456
2069 | BIG BASIN 11025066 | 82841102 | BIG BASIN 1102 | 5066 | FALSE | 22120.764 | 22120.764 | 13.7481 | 121 | 0.00018064 | 508 | 16.1765 | 2514 | 0.0029066 | 0.35169 | 2359 | 0.48 | 902
8715 | OLEMA 1101602 | 42291101 | OLEMA 1101 | 602 | FALSE | 38446.6728 | 26032.3379 | 16.1792 | 115 | 5.7752e-05 | 2842 | 48.2008 | 2220 | 0.0028981 | 0.33328 | 2360 | 0.08 | 1633
5548 | ANTLER 11011384 | 103271101 | ANTLER 1101 | 1384 | FALSE | 14709.9253 | 14709.9253 | 9.1423 | 106 | 0.00030207 | 128 | 17.1106 | 2502 | 0.0028857 | 0.30589 | 2361 | 0.08 | 1664
2497 | ROB ROY 210410714 | 83692104 | ROB ROY 2104 | 10714 | FALSE | 31415.1888 | 22795.5157 | 14.1675 | 212 | 8.9964e-05 | 1915 | 34.8828 | 2308 | 0.002884 | 0.61141 | 2362 | 0.2 | 1158
2343 | OCEANO 1104CB | 182601104 | OCEANO 1104 | CB | FALSE | 17856.3948 | 7352.5883 | 4.5697 | 146 | 2.5847e-05 | 3489 | 57.0849 | 2170 | 0.0028615 | 0.41777 | 2363 | 0.1 | 1489
7790 | SANTA ROSA A 1111147198 | 42151111 | SANTA ROSA A 1111 | 147198 | FALSE | 3096.6231 | 2173.9439 | 1.3511 | 24 | 0.00013298 | 958 | 27.8556 | 2363 | 0.0028527 | 0.068464 | 2364 |  | 3161
5803 | BEN LOMOND 04015206 | 83040401 | BEN LOMOND 0401 | 5206 | FALSE | 11520.3774 | 11520.3774 | 7.16 | 78 | 0.00028525 | 147 | 13.4764 | 2563 | 0.0028387 | 0.22141 | 2365 | 16.08 | 342
6276 | MONTE RIO 1113202 | 42811113 | MONTE RIO 1113 | 202 | FALSE | 8481.1425 | 8481.1425 | 5.2711 | 55 | 0.00023689 | 257 | 9.574 | 2632 | 0.0028293 | 0.15561 | 2366 | 77.47 | 54
6911 | DEL MONTE 21042624 | 182222104 | DEL MONTE 2104 | 2624 | FALSE | 30794.7642 | 29790.8638 | 18.5151 | 148 | 5.858e-05 | 2819 | 45.0109 | 2246 | 0.0028273 | 0.41844 | 2367 | 0.19 | 1182
3771 | CURTIS 170510590 | 163351705 | CURTIS 1705 | 10590 | FALSE | 26358.3376 | 26358.3376 | 16.3818 | 199 | 7.2916e-05 | 2395 | 56.6573 | 2172 | 0.0028226 | 0.56169 | 2368 | 0.28 | 1046
2714 | MIWUK 1702CB | 163661702 | MIWUK 1702 | CB | FALSE | 14569.4696 | 14569.4696 | 9.055 | 110 | 0.00015914 | 650 | 17.5722 | 2489 | 0.0028161 | 0.30977 | 2369 | 97.72 | 22
3825 | SARATOGA 1105LC14 | 83371105 | SARATOGA 1105 | LC14 | FALSE | 17935.8798 | 15879.1839 | 9.869 | 137 | 0.0001215 | 1156 | 25.9229 | 2378 | 0.0028157 | 0.38575 | 2370 | 0.15 | 1303
5150 | HAMILTON BRANCH 11012046 | 102361101 | HAMILTON BRANCH 1101 | 2046 | FALSE | 14788.0543 | 14724.19 | 9.1511 | 57 | 2.9135e-05 | 3438 | 49.5192 | 2213 | 0.0028141 | 0.1604 | 2371 | 3.25 | 552
6397 | BRUNSWICK 110584480 | 152481105 | BRUNSWICK 1105 | 84480 | FALSE | 7615.7819 | 7615.7819 | 4.7332 | 50 | 0.00012015 | 1184 | 18.1285 | 2473 | 0.0028064 | 0.14032 | 2372 | 43.55 | 166
7609 | SAN LUIS OBISPO 1107V58 | 182631107 | SAN LUIS OBISPO 1107 | V58 | FALSE | 3619.1201 | 1838.4445 | 1.1426 | 25 | 3.6836e-05 | 3317 | 42.8997 | 2262 | 0.0027879 | 0.069698 | 2373 | 0.25 | 1081
10167 | HAMILTON BRANCH 11012436 | 102361101 | HAMILTON BRANCH 1101 | 2436 | FALSE | 8535.8961 | 8535.8961 | 5.3051 | 19 | 3.5783e-05 | 3338 | 86.4703 | 2020 | 0.0027598 | 0.052436 | 2374 | 0.06 | 1878
289 | BIG BASIN 110169550 | 82841101 | BIG BASIN 1101 | 69550 | FALSE | 28222.9499 | 28222.9499 | 17.5407 | 188 | 0.00019115 | 436 | 15.1137 | 2529 | 0.0027545 | 0.51784 | 2375 | 0.88 | 753
3662 | SONOMA 1107294 | 42721107 | SONOMA 1107 | 294 | TRUE | 13929.6308 | 0 | 0 | 66 | 3.7559e-05 | 3303 | 12.2945 | 2582 | 0.002743 | 0.18104 | 2376 | 1.46 | 672
6355 | BIG RIVER 11017273 | 43081101 | BIG RIVER 1101 | 7273 | FALSE | 10648.4179 | 10648.4179 | 6.618 | 38 | 0.00010776 | 1456 | 24.4514 | 2395 | 0.0027408 | 0.10415 | 2377 |  | 3023
7672 | POINT ARENA 11012637 | 43381101 | POINT ARENA 1101 | 2637 | FALSE | 6500.6025 | 6500.6025 | 4.0402 | 28 | 7.3634e-05 | 2375 | 33.1621 | 2319 | 0.0027385 | 0.076678 | 2378 | 0.06 | 1783
1790 | CAMP EVERS 210510912 | 83622105 | CAMP EVERS 2105 | 10912 | FALSE | 7824.9032 | 7824.9032 | 4.8632 | 54 | 0.00030255 | 127 | 14.5938 | 2539 | 0.0027343 | 0.14765 | 2379 | 17.3 | 333
10750 | BOGARD 1101CB | 103301101 | BOGARD 1101 | CB | TRUE | 830.5012 | 830.5012 | 0.51616 | 7 | 2.8327e-05 | 3450 | 82.5251 | 2038 | 0.0027213 | 0.019049 | 2380 | 0 | 2645
6610 | GREEN VALLEY 210112824 | 83192101 | GREEN VALLEY 2101 | 12824 | FALSE | 19725.4463 | 1410.0846 | 0.87637 | 97 | 5.8888e-05 | 2811 | 61.7022 | 2142 | 0.0027199 | 0.26383 | 2381 | 0.19 | 1178
6375 | HOLLISTER 21054048 | 182492105 | HOLLISTER 2105 | 4048 | FALSE | 45554.4794 | 29209.8997 | 18.1541 | 157 | 5.5174e-05 | 2907 | 56.2888 | 2174 | 0.0027194 | 0.42694 | 2382 | 0.07 | 1678
317 | PARADISE 11042206 | 102831104 | PARADISE 1104 | 2206 | FALSE | 27876.5924 | 6659.3031 | 4.1388 | 227 | 0.00050121 | 31 | 12.7346 | 2573 | 0.0027 | 0.61291 | 2383 |  | 2664
6305 | WILLOW CREEK 110191926 | 192171101 | WILLOW CREEK 1101 | 91926 | FALSE | 17004.3113 | 10358.7223 | 6.438 | 48 | 0.00024845 | 221 | 9.7992 | 2628 | 0.0026935 | 0.12929 | 2384 | 0.04 | 2095
5185 | SILVERADO 21023010 | 43432102 | SILVERADO 2102 | 3010 | TRUE | 14671.2868 | 569.5009 | 0.35395 | 106 | 8.4289e-05 | 2082 | 23.6594 | 2409 | 0.0026922 | 0.28537 | 2385 | 0.03 | 2262
122 | STANISLAUS 17021888 | 162821702 | STANISLAUS 1702 | 1888 | FALSE | 30440.0056 | 30440.0056 | 18.9186 | 231 | 9.5589e-05 | 1738 | 52.6578 | 2198 | 0.0026855 | 0.62036 | 2386 | 136.25 | 4
7468 | ROB ROY 210410298 | 83692104 | ROB ROY 2104 | 10298 | FALSE | 21540.3253 | 17635.9746 | 10.9608 | 138 | 0.00011425 | 1313 | 23.0219 | 2412 | 0.0026825 | 0.37018 | 2387 | 0.67 | 817
3981 | CAMP EVERS 210510214 | 83622105 | CAMP EVERS 2105 | 10214 | FALSE | 22409.5851 | 22409.5851 | 13.9276 | 149 | 0.00015 | 735 | 18.095 | 2476 | 0.0026769 | 0.39885 | 2388 | 59.12 | 90
4982 | WEST POINT 110136674 | 163201101 | WEST POINT 1101 | 36674 | FALSE | 15144.1466 | 15144.1466 | 9.4121 | 125 | 0.00010056 | 1635 | 28.0218 | 2361 | 0.0026639 | 0.33299 | 2389 | 88.72 | 34
7345 | WILLOW CREEK 110129362 | 192171101 | WILLOW CREEK 1101 | 29362 | FALSE | 18377.6602 | 12371.5145 | 7.6889 | 74 | 0.00019406 | 424 | 17.4096 | 2493 | 0.0026559 | 0.19654 | 2390 | 0.15 | 1302
8996 | FORT ORD 210637286 | 182402106 | FORT ORD 2106 | 37286 | FALSE | 5924.4605 | 4150.8287 | 2.5798 | 25 | 7.3809e-05 | 2365 | 26.9712 | 2368 | 0.0026543 | 0.066357 | 2391 | 0.03 | 2256
8063 | COARSEGOLD 210210207 | 254432102 | COARSEGOLD 2102 | 10207 | FALSE | 5731.5328 | 5731.5328 | 3.5622 | 38 | 5.2727e-05 | 2978 | 53.21 | 2193 | 0.0026426 | 0.10042 | 2392 | 4.55 | 517
4536 | TASSAJARA 2108437582 | 14662108 | TASSAJARA 2108 | 437582 | FALSE | 3785.2974 | 1172.6243 | 0.72879 | 31 | 9.3714e-05 | 1803 | 36.8732 | 2299 | 0.0026389 | 0.081807 | 2393 |  | 2902
1013 | CASTRO VALLEY 1108MR337 | 14091108 | CASTRO VALLEY 1108 | MR337 | FALSE | 30458.1324 | 14629.5479 | 9.0923 | 193 | 2.0736e-05 | 3536 | 31.7021 | 2331 | 0.0026206 | 0.50578 | 2394 |  | 2704
1167 | BIG BASIN 110195690 | 82841101 | BIG BASIN 1101 | 95690 | FALSE | 6226.9882 | 6226.9882 | 3.8701 | 58 | 0.00043813 | 55 | 3.7552 | 2782 | 0.0026164 | 0.15175 | 2395 | 0.66 | 821
7588 | IGNACIO 1104450582 | 42481104 | IGNACIO 1104 | 450582 | FALSE | 6805.9936 | 4807.846 | 2.9881 | 50 | 8.4551e-05 | 2074 | 22.3998 | 2418 | 0.0026097 | 0.13049 | 2396 | 0.06 | 1776
976 | BRUNSWICK 1103CB | 152481103 | BRUNSWICK 1103 | CB | FALSE | 8801.7452 | 2701.0978 | 1.6787 | 82 | 0.00031315 | 115 | 15.1124 | 2530 | 0.0026094 | 0.21397 | 2397 | 0.1 | 1502
3119 | BIG BASIN 1101CB | 82841101 | BIG BASIN 1101 | CB | FALSE | 7486.7827 | 7486.7827 | 4.6531 | 45 | 0.00027461 | 168 | 11.6886 | 2594 | 0.0025849 | 0.11632 | 2398 | 26.9 | 264
8530 | MORRO BAY 1102CB | 183011102 | MORRO BAY 1102 | CB | FALSE | 8911.8997 | 7279.8498 | 4.5245 | 36 | 3.3044e-05 | 3385 | 43.2592 | 2258 | 0.0025799 | 0.092875 | 2399 | 0.04 | 2119
1372 | TASSAJARA 2112CB | 14662112 | TASSAJARA 2112 | CB | TRUE | 2118.6497 | 279.4297 | 0.17367 | 22 | 6.8306e-05 | 2527 | 21.6949 | 2429 | 0.0025794 | 0.056746 | 2400 | 0.44 | 921
1496 | BRUNSWICK 1103173934 | 152481103 | BRUNSWICK 1103 | 173934 | FALSE | 17611.7153 | 17611.7153 | 10.9458 | 125 | 0.00011937 | 1199 | 28.2053 | 2358 | 0.0025705 | 0.32131 | 2401 |  | 2727
1818 | MORRO BAY 1101V66 | 183011101 | MORRO BAY 1101 | V66 | FALSE | 26099.4541 | 5840.07 | 3.6296 | 151 | 5.4939e-05 | 2915 | 48.8236 | 2216 | 0.0025703 | 0.38811 | 2402 | 0.03 | 2264
3089 | CAMBRIA 1101CB | 182771101 | CAMBRIA 1101 | CB | TRUE | 9964.9315 | 415.9182 | 0.25849 | 45 | 5.4044e-05 | 2942 | 29.9475 | 2345 | 0.0025606 | 0.11523 | 2403 | 0.02 | 2456
3722 | BRUNSWICK 11032784 | 152481103 | BRUNSWICK 1103 | 2784 | FALSE | 24673.5503 | 23592.2379 | 14.6627 | 202 | 0.0002125 | 349 | 16.1455 | 2515 | 0.0025529 | 0.51568 | 2404 | 21.1 | 301
3654 | PENNGROVE 1101247511 | 43471101 | PENNGROVE 1101 | 247511 | FALSE | 3219.7109 | 1938.4111 | 1.2047 | 26 | 5.8722e-05 | 2816 | 39.41 | 2279 | 0.0025357 | 0.065929 | 2405 |  | 2844
2397 | MILPITAS 1109XR374 | 82831109 | MILPITAS 1109 | XR374 | TRUE | 4853.8508 | 763.9032 | 0.47477 | 29 | 5.5868e-05 | 2893 | 52.1032 | 2201 | 0.002531 | 0.073398 | 2406 | 0.04 | 2155
1430 | ANTLER 11011520 | 103271101 | ANTLER 1101 | 1520 | FALSE | 14435.9237 | 14435.9237 | 8.972 | 69 | 0.0002442 | 234 | 18.3262 | 2471 | 0.002519 | 0.17381 | 2407 | 0.04 | 2139
9020 | EAST QUINCY 1101424048 | 102551101 | EAST QUINCY 1101 | 424048 | FALSE | 1501.8611 | 1068.5882 | 0.66413 | 12 | 6.0749e-05 | 2756 | 33.0472 | 2323 | 0.002517 | 0.030204 | 2408 |  | 3298
5728 | HALF MOON BAY 1101CB | 24101101 | HALF MOON BAY 1101 | CB | FALSE | 10068.8846 | 2571.5148 | 1.5982 | 80 | 4.1301e-05 | 3240 | 78.3943 | 2057 | 0.0025158 | 0.20127 | 2409 | 0.42 | 929
2399 | MONTE RIO 1113477 | 42811113 | MONTE RIO 1113 | 477 | FALSE | 2946.6356 | 2946.6356 | 1.8313 | 25 | 0.00015508 | 692 | 16.2294 | 2513 | 0.002515 | 0.062875 | 2410 | 3.59 | 539
5291 | MIWUK 1702823548 | 163661702 | MIWUK 1702 | 823548 | FALSE | 31748.5399 | 31748.5399 | 19.7318 | 231 | 6.0776e-05 | 2755 | 41.9518 | 2266 | 0.0025098 | 0.57976 | 2411 |  | 2944
2843 | PLACERVILLE 111219742 | 153081112 | PLACERVILLE 1112 | 19742 | FALSE | 12071.9353 | 10549.7356 | 6.5567 | 92 | 0.00023207 | 278 | 8.0743 | 2669 | 0.0025093 | 0.23086 | 2412 | 0.09 | 1571
7112 | BELLEVUE 2103646 | 43182103 | BELLEVUE 2103 | 646 | FALSE | 19795.1478 | 13544.3225 | 8.4179 | 154 | 0.00011949 | 1196 | 18.0896 | 2477 | 0.0025033 | 0.3855 | 2413 | 28.71 | 246
637 | DUNBAR 1101160 | 43071101 | DUNBAR 1101 | 160 | FALSE | 10761.0163 | 4469.2889 | 2.7777 | 77 | 9.2493e-05 | 1831 | 17.9801 | 2481 | 0.0024952 | 0.19213 | 2414 | 0.04 | 2105
551 | MC KEE 1103XR028 | 83531103 | MC KEE 1103 | XR028 | FALSE | 16732.9664 | 1226.5796 | 0.76232 | 134 | 6.205e-05 | 2717 | 31.865 | 2330 | 0.0024946 | 0.33428 | 2415 | 0.03 | 2231
4532 | RESERVATION ROAD 1102CB | 182731102 | RESERVATION ROAD 1102 | CB | FALSE | 27553.0792 | 12591.5795 | 7.8257 | 180 | 4.197e-05 | 3225 | 36.6519 | 2300 | 0.0024688 | 0.44438 | 2416 | 0.03 | 2341
2736 | ROSSMOOR 110845268 | 14161108 | ROSSMOOR 1108 | 45268 | FALSE | 12405.1563 | 4400.5557 | 2.735 | 112 | 8.3437e-05 | 2119 | 27.4918 | 2366 | 0.0024458 | 0.27393 | 2417 | 0.06 | 1780
4245 | SONOMA 1104914376 | 42721104 | SONOMA 1104 | 914376 | TRUE | 11215.1853 | 862.0577 | 0.53577 | 93 | 8.1801e-05 | 2159 | 28.2406 | 2357 | 0.0024267 | 0.22569 | 2418 | 0.04 | 2227
9993 | STELLING 1109478699 | 83481109 | STELLING 1109 | 478699 | FALSE | 1763.8687 | 1328.3865 | 0.8256 | 14 | 8.2786e-05 | 2136 | 37.3598 | 2294 | 0.0024262 | 0.033967 | 2419 |  | 3466
1421 | ORO FINO 11012022 | 103031101 | ORO FINO 1101 | 2022 | FALSE | 25888.9554 | 25888.9554 | 16.0901 | 207 | 0.0001628 | 614 | 14.0752 | 2547 | 0.0024209 | 0.50113 | 2420 | 126.01 | 10
4226 | RIO DELL 1102772210 | 192251102 | RIO DELL 1102 | 772210 | FALSE | 5622.5297 | 1329.7793 | 0.82646 | 32 | 0.0003009 | 129 | 8.4673 | 2658 | 0.0023979 | 0.076733 | 2421 |  | 2876
3489 | WEIMAR 1101CB | 152491101 | WEIMAR 1101 | CB | FALSE | 14897.5939 | 14897.5939 | 9.2589 | 116 | 0.00026838 | 176 | 10.7214 | 2615 | 0.0023893 | 0.27716 | 2422 | 0.08 | 1670
9667 | NORTH TOWER 2101CB | 42042101 | NORTH TOWER 2101 | CB | FALSE | 7077.2532 | 2179.3543 | 1.3545 | 22 | 7.8614e-05 | 2246 | 23.8165 | 2407 | 0.0023847 | 0.052462 | 2423 | 0.16 | 1259
8228 | GONZALES 1104415382 | 182131104 | GONZALES 1104 | 415382 | TRUE | 1920.3588 | 97.0433 | 0.060313 | 8 | 1.7728e-05 | 3562 | 59.385 | 2159 | 0.0023723 | 0.018978 | 2424 |  | 3205
4259 | DIAMOND SPRINGS 110676088 | 152261106 | DIAMOND SPRINGS 1106 | 76088 | FALSE | 17715.9929 | 17715.9929 | 11.0106 | 124 | 8.4526e-05 | 2076 | 27.0945 | 2367 | 0.0023715 | 0.29407 | 2425 | 0.08 | 1589
9364 | MIWUK 170236888 | 163661702 | MIWUK 1702 | 36888 | TRUE | 977.9121 | 977.9121 | 0.60778 | 7 | 0.00011804 | 1228 | 17.0465 | 2504 | 0.0023702 | 0.016592 | 2426 | 28.15 | 253
5480 | PUEBLO 2102647842 | 43292102 | PUEBLO 2102 | 647842 | TRUE | 1016.9284 | 187.7325 | 0.11668 | 6 | 4.4258e-05 | 3184 | 47.9751 | 2222 | 0.0023697 | 0.014218 | 2427 |  | 2958
1607 | MONTE RIO 11133970 | 42811113 | MONTE RIO 1113 | 3970 | FALSE | 11750.7224 | 11750.7224 | 7.3031 | 87 | 0.00015476 | 697 | 11.2679 | 2601 | 0.0023638 | 0.20565 | 2428 | 0.85 | 765
4343 | BOLINAS 11011236 | 42261101 | BOLINAS 1101 | 1236 | FALSE | 6557.8129 | 5809.1133 | 3.6104 | 34 | 0.00011532 | 1292 | 31.2219 | 2338 | 0.0023633 | 0.080354 | 2429 | 0.06 | 1825
4341 | PLACERVILLE 210623190 | 153082106 | PLACERVILLE 2106 | 23190 | FALSE | 5918.813 | 5918.813 | 3.6786 | 45 | 0.00031007 | 118 | 11.1572 | 2604 | 0.0023536 | 0.10591 | 2430 | 0.09 | 1566
6831 | INDIAN FLAT 110410270 | 252691104 | INDIAN FLAT 1104 | 10270 | FALSE | 6119.8962 | 6119.8962 | 3.8035 | 39 | 3.2245e-05 | 3398 | 67.2012 | 2107 | 0.002349 | 0.091612 | 2431 | 0.07 | 1697
10358 | KONOCTI 11024421 | 43311102 | KONOCTI 1102 | 4421 | TRUE | 585.3593 | 585.3593 | 0.3638 | 5 | 8.4837e-05 | 2068 | 28.5837 | 2354 | 0.0023217 | 0.011609 | 2432 | 18.46 | 321
822 | PERRY 1101V74 | 183071101 | PERRY 1101 | V74 | FALSE | 8209.0598 | 6901.1378 | 4.2891 | 61 | 4.7405e-05 | 3107 | 40.6895 | 2274 | 0.0023119 | 0.14103 | 2433 | 0.09 | 1509
1876 | HATTON 1102CB | 182291102 | HATTON 1102 | CB | FALSE | 7725.5743 | 3167.0883 | 1.9684 | 66 | 5.6002e-05 | 2888 | 47.8787 | 2223 | 0.0022934 | 0.15136 | 2434 | 0.04 | 2137
5363 | BIG BASIN 110110720 | 82841101 | BIG BASIN 1101 | 10720 | FALSE | 7578.3102 | 7578.3102 | 4.71 | 44 | 0.00059263 | 19 | 5.4692 | 2730 | 0.002283 | 0.10045 | 2435 | 61.7 | 86
3635 | PERRY 1101V88 | 183071101 | PERRY 1101 | V88 | FALSE | 5002.7309 | 1732.6065 | 1.0768 | 48 | 3.4227e-05 | 3365 | 36.539 | 2301 | 0.002278 | 0.10934 | 2436 | 0.6 | 853
4348 | SANTA ROSA A 110432180 | 42151104 | SANTA ROSA A 1104 | 32180 | FALSE | 4085.725 | 3970.2131 | 2.4675 | 36 | 0.0001328 | 963 | 9.9964 | 2624 | 0.0022763 | 0.081948 | 2437 | 0.25 | 1076
9525 | BIG BASIN 11028403 | 82841102 | BIG BASIN 1102 | 8403 | FALSE | 7867.7292 | 7867.7292 | 4.8898 | 42 | 0.00015778 | 666 | 14.7825 | 2533 | 0.0022738 | 0.095499 | 2438 | 0.41 | 941
7227 | SAN RAFAEL 11071415 | 42011107 | SAN RAFAEL 1107 | 1415 | FALSE | 1913.2696 | 1280.0188 | 0.79554 | 14 | 0.00015384 | 711 | 13.6482 | 2558 | 0.0022706 | 0.031789 | 2439 | 2.72 | 587
649 | ORO FINO 11022090 | 103031102 | ORO FINO 1102 | 2090 | FALSE | 23726.1931 | 23726.1931 | 14.7459 | 183 | 0.00011006 | 1410 | 20.7182 | 2438 | 0.0022675 | 0.41496 | 2440 | 71.03 | 68
2752 | FULTON 1107CB | 42561107 | FULTON 1107 | CB | TRUE | 19915.785 | 875.3178 | 0.54401 | 166 | 8.6265e-05 | 2028 | 19.7079 | 2452 | 0.0022645 | 0.37591 | 2441 | 3.46 | 545
8081 | CAMP EVERS 210612840 | 83622106 | CAMP EVERS 2106 | 12840 | FALSE | 6323.0478 | 6323.0478 | 3.9298 | 50 | 0.00014417 | 811 | 15.7468 | 2520 | 0.002258 | 0.1129 | 2442 | 0.4 | 948
365 | PURISIMA 110149394 | 182971101 | PURISIMA 1101 | 49394 | FALSE | 14105.1915 | 1836.8422 | 1.1416 | 111 | 2.0592e-05 | 3538 | 59.3555 | 2160 | 0.0022509 | 0.24985 | 2443 | 0.03 | 2277
707 | DEL MONTE 21042760 | 182222104 | DEL MONTE 2104 | 2760 | FALSE | 4358.9956 | 4358.9956 | 2.7091 | 28 | 8.7661e-05 | 1995 | 28.0773 | 2360 | 0.0022393 | 0.062701 | 2444 | 0.65 | 826
7540 | LUCERNE 11062327 | 43351106 | LUCERNE 1106 | 2327 | FALSE | 2038.9698 | 1914.889 | 1.1901 | 20 | 0.00013326 | 953 | 15.5189 | 2523 | 0.0022381 | 0.044762 | 2445 | 0.08 | 1640
9432 | GUALALA 1111445166 | 42841111 | GUALALA 1111 | 445166 | FALSE | 15269.7955 | 12164.2635 | 7.5601 | 71 | 5.9661e-05 | 2785 | 28.1893 | 2359 | 0.0022354 | 0.15871 | 2446 | 0.06 | 1845
2414 | PINE GROVE 110245292 | 163751102 | PINE GROVE 1102 | 45292 | FALSE | 17350.6047 | 17350.6047 | 10.7835 | 132 | 8.1993e-05 | 2156 | 36.0802 | 2304 | 0.002235 | 0.29501 | 2447 | 129.86 | 5
7039 | IGNACIO 1101CB | 42481101 | IGNACIO 1101 | CB | FALSE | 2942.811 | 2690.5619 | 1.6722 | 19 | 0.00013353 | 951 | 20.0821 | 2447 | 0.0022279 | 0.042331 | 2448 | 0.05 | 2033
6713 | LAURELES 1112438 | 182371112 | LAURELES 1112 | 438 | FALSE | 9219.1151 | 8226.4088 | 5.1127 | 48 | 7.125e-05 | 2440 | 29.805 | 2347 | 0.0022241 | 0.10675 | 2449 | 0.05 | 2035
1808 | HARTLEY 1101738 | 43211101 | HARTLEY 1101 | 738 | FALSE | 12990.1187 | 4208.5049 | 2.6156 | 106 | 7.6101e-05 | 2304 | 26.5188 | 2371 | 0.0022159 | 0.23488 | 2450 | 0.03 | 2251
9055 | ORO FINO 1102CB | 103031102 | ORO FINO 1102 | CB | FALSE | 3376.1921 | 3376.1921 | 2.0983 | 27 | 0.00018738 | 459 | 22.0757 | 2425 | 0.0021922 | 0.059189 | 2451 | 44.75 | 154
500 | ALTO 112278672 | 42031122 | ALTO 1122 | 78672 | FALSE | 14393.4787 | 6078.7898 | 3.778 | 123 | 7.9821e-05 | 2211 | 9.5346 | 2635 | 0.0021883 | 0.26916 | 2452 | 0.15 | 1304
9919 | MONTE RIO 1113678 | 42811113 | MONTE RIO 1113 | 678 | FALSE | 3004.004 | 3004.004 | 1.867 | 17 | 0.00013325 | 954 | 26.6461 | 2369 | 0.002188 | 0.037196 | 2453 | 48.48 | 128
8710 | SUMMIT 110186658 | 152591101 | SUMMIT 1101 | 86658 | FALSE | 1081.812 | 1029.0279 | 0.63954 | 7 | 0.00024387 | 235 | 13.6494 | 2557 | 0.0021861 | 0.015303 | 2454 | 0.02 | 2563
3183 | PINE GROVE 11011021 | 163751101 | PINE GROVE 1101 | 1021 | FALSE | 6702.9103 | 6702.9103 | 4.1659 | 56 | 6.9851e-05 | 2478 | 34.4442 | 2311 | 0.0021716 | 0.12161 | 2455 | 8.36 | 430
3039 | BIG BASIN 110110296 | 82841101 | BIG BASIN 1101 | 10296 | FALSE | 23203.5804 | 23203.5804 | 14.4211 | 181 | 0.00028227 | 151 | 8.472 | 2657 | 0.0021702 | 0.3928 | 2456 | 20.94 | 303
10621 | EEL RIVER 1103987714 | 192381103 | EEL RIVER 1103 | 987714 | FALSE | 1590.9598 | 1218.9668 | 0.75759 | 6 | 0.00013453 | 933 | 18.5736 | 2466 | 0.0021699 | 0.01302 | 2457 |  | 3580
2552 | HALSEY 11022514 | 152241102 | HALSEY 1102 | 2514 | FALSE | 31420.4965 | 17648.4979 | 10.9686 | 212 | 0.00019439 | 421 | 17.5789 | 2488 | 0.0021687 | 0.45975 | 2458 | 0.04 | 2164
1900 | PLACERVILLE 1111508410 | 153081111 | PLACERVILLE 1111 | 508410 | FALSE | 8406.5825 | 7530.8771 | 4.6805 | 73 | 0.0002728 | 169 | 8.8564 | 2647 | 0.002162 | 0.15783 | 2459 |  | 2754
7805 | POINT MORETTI 11015074 | 82931101 | POINT MORETTI 1101 | 5074 | FALSE | 4940.828 | 2196.7079 | 1.3653 | 34 | 7.8643e-05 | 2245 | 54.9615 | 2181 | 0.0021548 | 0.073264 | 2460 | 0.03 | 2294
9738 | ECHO SUMMIT 1101344250 | 158031101 | ECHO SUMMIT 1101 | 344250 | FALSE | 1668.1837 | 1299.2708 | 0.8075 | 10 | 4.8899e-05 | 3068 | 38.0392 | 2290 | 0.0021484 | 0.021484 | 2461 | 0.03 | 2252
3248 | HARRIS 1109355914 | 192431109 | HARRIS 1109 | 355914 | FALSE | 14935.3832 | 13002.7807 | 8.0813 | 104 | 0.0002048 | 382 | 13.3148 | 2566 | 0.0021471 | 0.2233 | 2462 |  | 2817
5158 | MORRO BAY 1101W20 | 183011101 | MORRO BAY 1101 | W20 | FALSE | 6313.3606 | 3551.7376 | 2.2074 | 48 | 4.0736e-05 | 3252 | 28.7718 | 2351 | 0.0021357 | 0.10251 | 2463 | 0.02 | 2548
5206 | CAMP EVERS 21065020 | 83622106 | CAMP EVERS 2106 | 5020 | FALSE | 24253.1314 | 24253.1314 | 15.0734 | 185 | 0.00021261 | 348 | 14.5867 | 2540 | 0.0021265 | 0.3934 | 2464 | 82.74 | 42
8641 | PETALUMA C 1109857148 | 42631109 | PETALUMA C 1109 | 857148 | FALSE | 3180.8041 | 1503.7135 | 0.93456 | 31 | 4.5954e-05 | 3140 | 22.3402 | 2422 | 0.0021126 | 0.065491 | 2465 |  | 3247
4750 | PENNGROVE 1101554 | 43471101 | PENNGROVE 1101 | 554 | TRUE | 17322.4157 | 0 | 0 | 130 | 6.9536e-05 | 2487 | 22.3741 | 2419 | 0.0021107 | 0.2744 | 2466 | 0.33 | 985
5805 | PARADISE 110439216 | 102831104 | PARADISE 1104 | 39216 | FALSE | 5158.2623 | 2624.8047 | 1.6313 | 41 | 0.00049128 | 32 | 7.6005 | 2675 | 0.0021 | 0.086098 | 2467 | 0.31 | 998
3222 | WEST POINT 11014706 | 163201101 | WEST POINT 1101 | 4706 | FALSE | 18429.634 | 18429.634 | 11.4541 | 138 | 8.047e-05 | 2193 | 25.0428 | 2390 | 0.0020959 | 0.28923 | 2468 | 94.56 | 27
2065 | EL DORADO PH 21026645 | 152762102 | EL DORADO PH 2102 | 6645 | FALSE | 6787.3604 | 6787.3604 | 4.2184 | 52 | 9.5316e-05 | 1753 | 25.6675 | 2386 | 0.0020868 | 0.10851 | 2469 | 54.01 | 109
6903 | VINEYARD 2107MR332 | 14502107 | VINEYARD 2107 | MR332 | TRUE | 4548.7457 | 520.6629 | 0.32359 | 31 | 7.6303e-05 | 2299 | 24.407 | 2396 | 0.0020705 | 0.064186 | 2470 | 0.38 | 963
3802 | MORRO BAY 1102868170 | 183011102 | MORRO BAY 1102 | 868170 | FALSE | 15451.7071 | 14595.2194 | 9.071 | 59 | 3.81e-05 | 3298 | 52.9097 | 2197 | 0.0020479 | 0.12083 | 2471 |  | 2853
3290 | TAR FLAT 04023144 | 163240402 | TAR FLAT 0402 | 3144 | FALSE | 8269.2517 | 7828.9119 | 4.8657 | 58 | 0.00015369 | 715 | 19.1385 | 2460 | 0.0020462 | 0.11868 | 2472 | 0.09 | 1549
9541 | RINCON 1101839669 | 43321101 | RINCON 1101 | 839669 | TRUE | 1273.7836 | 989.219 | 0.6148 | 12 | 0.00010611 | 1492 | 23.2008 | 2411 | 0.0020383 | 0.02446 | 2473 |  | 3373
671 | CAMP EVERS 21045096 | 83622104 | CAMP EVERS 2104 | 5096 | FALSE | 32680.7032 | 32680.7032 | 20.3112 | 232 | 0.00019642 | 411 | 13.592 | 2561 | 0.0020379 | 0.4728 | 2474 | 12.58 | 372
6416 | PLACER 1102CB | 152461102 | PLACER 1102 | CB | FALSE | 3445.1403 | 3361.7302 | 2.0893 | 23 | 0.00019412 | 423 | 17.2869 | 2496 | 0.0020369 | 0.046849 | 2475 | 0.54 | 878
9674 | GUALALA 1112CB | 42841112 | GUALALA 1112 | CB | FALSE | 3448.2579 | 2568.9228 | 1.5966 | 22 | 5.2908e-05 | 2970 | 18.4256 | 2469 | 0.0020177 | 0.044389 | 2476 | 0.05 | 1991
1510 | MONTE RIO 1113CB | 42811113 | MONTE RIO 1113 | CB | FALSE | 7286.2366 | 7286.2366 | 4.5284 | 49 | 0.00021269 | 347 | 6.3725 | 2702 | 0.0020136 | 0.098667 | 2477 | 46.29 | 143
1572 | ECHO SUMMIT 11012500 | 158031101 | ECHO SUMMIT 1101 | 2500 | FALSE | 3521.417 | 3521.417 | 2.1886 | 26 | 4.8353e-05 | 3083 | 44.8707 | 2248 | 0.0019811 | 0.05151 | 2478 | 0.16 | 1255
808 | PEORIA 1701169700 | 163781701 | PEORIA 1701 | 169700 | FALSE | 13421.5222 | 13421.5222 | 8.3415 | 63 | 7.4011e-05 | 2357 | 25.346 | 2387 | 0.001973 | 0.1243 | 2479 |  | 2693
1792 | MORAGA 1102CB | 13801102 | MORAGA 1102 | CB | FALSE | 14982.4076 | 8539.83 | 5.3075 | 130 | 9.0885e-05 | 1886 | 25.7754 | 2384 | 0.0019722 | 0.25639 | 2480 | 0.62 | 843
6608 | FORT ROSS 1121134 | 42851121 | FORT ROSS 1121 | 134 | FALSE | 13416.4816 | 13272.5409 | 8.2489 | 99 | 9.5754e-05 | 1735 | 24.5453 | 2393 | 0.0019671 | 0.19475 | 2481 | 0.04 | 2145
5795 | HIGGINS 1103995672 | 152691103 | HIGGINS 1103 | 995672 | FALSE | 9263.8953 | 5928.6387 | 3.6847 | 79 | 0.00018258 | 492 | 13.4013 | 2564 | 0.0019604 | 0.15487 | 2482 | 0.08 | 1645
7320 | FAIRVIEW 220799096 | 13432207 | FAIRVIEW 2207 | 99096 | FALSE | 15944.165 | 15895.8244 | 9.8793 | 56 | 9.384e-05 | 1796 | 20.9972 | 2437 | 0.0019603 | 0.10978 | 2483 | 0.05 | 2008
1460 | PARADISE 1105121988 | 102831105 | PARADISE 1105 | 121988 | FALSE | 11219.1712 | 11219.1712 | 6.9728 | 92 | 0.00027094 | 171 | 5.2336 | 2742 | 0.0019488 | 0.17929 | 2484 |  | 2725
223 | ROB ROY 210410960 | 83692104 | ROB ROY 2104 | 10960 | FALSE | 45089.9597 | 30132.5387 | 18.7275 | 320 | 9.2109e-05 | 1838 | 18.2529 | 2472 | 0.0019454 | 0.62252 | 2485 | 0.12 | 1381
9882 | VOLTA 1102453266 | 102541102 | VOLTA 1102 | 453266 | TRUE | 510.1509 | 510.1509 | 0.31706 | 5 | 4.863e-05 | 3071 | 42.8367 | 2263 | 0.0019312 | 0.0096562 | 2486 |  | 3444
2825 | COTATI 1104CB | 42271104 | COTATI 1104 | CB | FALSE | 12268.6539 | 7279.3949 | 4.5242 | 93 | 7.194e-05 | 2421 | 13.0319 | 2569 | 0.0019107 | 0.17769 | 2487 | 1.2 | 702
9868 | VOLTA 110293418 | 102541102 | VOLTA 1102 | 93418 | FALSE | 4145.9232 | 4145.9232 | 2.5767 | 23 | 6.4515e-05 | 2627 | 45.5233 | 2243 | 0.0019038 | 0.043787 | 2488 | 0.16 | 1254
7915 | LOS GATOS 1106697500 | 82021106 | LOS GATOS 1106 | 697500 | FALSE | 10836.6474 | 10836.6474 | 6.735 | 74 | 0.00017368 | 536 | 8.0975 | 2667 | 0.0019029 | 0.14082 | 2489 |  | 3178
9296 | DUNBAR 1103835658 | 43071103 | DUNBAR 1103 | 835658 | TRUE | 1187.2489 | 50.0391 | 0.0311 | 11 | 7.6553e-05 | 2292 | 17.3633 | 2494 | 0.0018987 | 0.020885 | 2490 |  | 3337
6742 | ALTO 11251158 | 42031125 | ALTO 1125 | 1158 | FALSE | 8353.2531 | 3588.3989 | 2.2302 | 65 | 5.6863e-05 | 2865 | 5.9152 | 2715 | 0.0018981 | 0.12337 | 2491 | 0.17 | 1241
4000 | RINCON 1101576 | 43321101 | RINCON 1101 | 576 | FALSE | 13079.4255 | 1582.5592 | 0.98357 | 116 | 0.00012308 | 1132 | 17.5488 | 2490 | 0.0018636 | 0.21618 | 2492 | 0.15 | 1287
4995 | SOLEDAD 21027008 | 182052102 | SOLEDAD 2102 | 7008 | FALSE | 29112.5788 | 8088.7008 | 5.0272 | 122 | 2.175e-05 | 3523 | 36.2639 | 2302 | 0.0018473 | 0.22537 | 2493 | 0.03 | 2381
6887 | HATTON 1102648928 | 182291102 | HATTON 1102 | 648928 | FALSE | 7727.8743 | 6359.2353 | 3.9523 | 44 | 6.1331e-05 | 2741 | 57.7042 | 2168 | 0.0018437 | 0.081123 | 2494 | 0.04 | 2170
9513 | GREEN VALLEY 2101535998 | 83192101 | GREEN VALLEY 2101 | 535998 | FALSE | 7941.4498 | 7140.4635 | 4.4378 | 43 | 0.00012357 | 1129 | 19.4088 | 2455 | 0.0018414 | 0.079178 | 2495 |  | 3367
2632 | APPLE HILL 110412947 | 153661104 | APPLE HILL 1104 | 12947 | FALSE | 5709.2465 | 5709.2465 | 3.5483 | 49 | 0.00010562 | 1503 | 18.015 | 2480 | 0.0018388 | 0.0901 | 2496 | 10.69 | 395
7783 | MIRABEL 110257840 | 42091102 | MIRABEL 1102 | 57840 | FALSE | 4238.9331 | 4238.9331 | 2.6345 | 29 | 0.00029837 | 131 | 7.443 | 2678 | 0.0018331 | 0.053161 | 2497 | 0.36 | 971
26 | TASSAJARA 2103CB | 14662103 | TASSAJARA 2103 | CB | TRUE | 28346.0077 | 787.8623 | 0.48966 | 259 | 8.1627e-05 | 2165 | 14.0393 | 2549 | 0.0018283 | 0.47354 | 2498 | 0.05 | 1935
8978 | BIG RIVER 1101954 | 43081101 | BIG RIVER 1101 | 954 | FALSE | 13095.0592 | 12372.699 | 7.6897 | 78 | 9.4465e-05 | 1782 | 22.5908 | 2415 | 0.0018244 | 0.1423 | 2499 | 0.05 | 1972
85 | HALSEY 11011704 | 152241101 | HALSEY 1101 | 1704 | FALSE | 21239.3917 | 21231.8185 | 13.1957 | 160 | 0.00012962 | 1014 | 19.3786 | 2457 | 0.001823 | 0.29168 | 2500 | 0.18 | 1207
2388 | CAMP EVERS 21059031 | 83622105 | CAMP EVERS 2105 | 9031 | FALSE | 1741.4201 | 1741.4201 | 1.0823 | 17 | 0.00019853 | 401 | 5.6599 | 2722 | 0.0018195 | 0.030932 | 2501 | 26.99 | 262
2038 | MORAGA 1104CB | 13801104 | MORAGA 1104 | CB | FALSE | 25157.6923 | 15741.0344 | 9.7831 | 214 | 7.9295e-05 | 2226 | 25.8956 | 2379 | 0.0018118 | 0.38772 | 2502 | 0.19 | 1192
6140 | OCEANO 1106V28 | 182601106 | OCEANO 1106 | V28 | FALSE | 14462.1376 | 1958.2873 | 1.2171 | 99 | 2.0931e-05 | 3535 | 31.9058 | 2328 | 0.0018053 | 0.17873 | 2503 | 0.03 | 2284
9346 | LAURELES 11116421 | 182371111 | LAURELES 1111 | 6421 | FALSE | 2777.3682 | 2777.3682 | 1.7261 | 20 | 5.7665e-05 | 2846 | 26.2004 | 2374 | 0.0018044 | 0.036089 | 2504 | 0.14 | 1307
680 | CAMP EVERS 210612760 | 83622106 | CAMP EVERS 2106 | 12760 | FALSE | 42462.3954 | 42462.3954 | 26.3906 | 299 | 0.00019594 | 413 | 10.5604 | 2618 | 0.0017903 | 0.53531 | 2505 | 1.92 | 630
1725 | BOLINAS 1101CB | 42261101 | BOLINAS 1101 | CB | FALSE | 3500.023 | 3442.3441 | 2.1394 | 26 | 0.00012024 | 1181 | 17.4311 | 2492 | 0.0017811 | 0.04631 | 2506 | 0.23 | 1119
1486 | BEN LOMOND 1101BL 1101 | 83041101 | BEN LOMOND 1101 | BL 1101 | FALSE | 13568.3761 | 13568.3761 | 8.4328 | 101 | 0.00030613 | 124 | 6.186 | 2709 | 0.0017681 | 0.17858 | 2507 | 25.42 | 271
8439 | OAKHURST 110310190 | 254421103 | OAKHURST 1103 | 10190 | FALSE | 13591.0884 | 13591.0884 | 8.4469 | 61 | 6.3642e-05 | 2659 | 28.5039 | 2355 | 0.0017583 | 0.10725 | 2508 | 52.84 | 111
10411 | BURNEY 1102272636 | 103311102 | BURNEY 1102 | 272636 | TRUE | 431.3681 | 431.3681 | 0.2681 | 5 | 2.8514e-05 | 3445 | 33.4034 | 2316 | 0.0017542 | 0.0087708 | 2509 |  | 3545
9794 | SONOMA 1106510055 | 42721106 | SONOMA 1106 | 510055 | TRUE | 1976.5067 | 817.6203 | 0.50815 | 11 | 5.9313e-05 | 2794 | 33.1507 | 2320 | 0.0017489 | 0.019238 | 2510 |  | 3426
1870 | TEMPLETON 2110307832 | 183052110 | TEMPLETON 2110 | 307832 | FALSE | 22986.441 | 2614.1136 | 1.6247 | 133 | 5.4142e-05 | 2940 | 52.2996 | 2199 | 0.0017438 | 0.23192 | 2511 |  | 2750
4149 | EL DORADO PH 210219542 | 152762102 | EL DORADO PH 2102 | 19542 | FALSE | 15319.5774 | 15319.5774 | 9.5212 | 111 | 0.00024603 | 231 | 13.9871 | 2550 | 0.0017374 | 0.19285 | 2512 | 87.42 | 37
5394 | BRUNSWICK 11052100 | 152481105 | BRUNSWICK 1105 | 2100 | FALSE | 6391.6672 | 6391.6672 | 3.9724 | 47 | 0.00013966 | 875 | 17.2588 | 2498 | 0.0017366 | 0.081621 | 2513 | 19.6 | 310
7138 | MONTE RIO 11138299 | 42811113 | MONTE RIO 1113 | 8299 | FALSE | 1934.2169 | 1934.2169 | 1.2021 | 13 | 0.0001379 | 895 | 14.6935 | 2537 | 0.0017192 | 0.02235 | 2514 | 62.52 | 83
2315 | MORAGA 1101108540 | 13801101 | MORAGA 1101 | 108540 | FALSE | 7751.409 | 7751.409 | 4.8175 | 44 | 0.00010534 | 1511 | 10.8681 | 2613 | 0.001717 | 0.075547 | 2515 | 25 | 274
110 | RACETRACK 17038120 | 163761703 | RACETRACK 1703 | 8120 | FALSE | 14371.6326 | 14371.6326 | 8.932 | 108 | 0.00014141 | 847 | 24.2646 | 2397 | 0.0017068 | 0.18434 | 2516 | 0.12 | 1384
1996 | MORAGA 1103E510R | 13801103 | MORAGA 1103 | E510R | TRUE | 9824.475 | 807.8365 | 0.50207 | 84 | 6.4371e-05 | 2631 | 25.303 | 2388 | 0.0017029 | 0.14305 | 2517 | 0.06 | 1864
2784 | FRENCH GULCH 11022902 | 103381102 | FRENCH GULCH 1102 | 2902 | FALSE | 11242.8228 | 11242.8228 | 6.9875 | 8 | 0.00012146 | 1158 | 50.5933 | 2209 | 0.0016954 | 0.013563 | 2518 | 0.04 | 2100
4648 | HALF MOON BAY 1102863822 | 24101102 | HALF MOON BAY 1102 | 863822 | TRUE | 1030.95 | 168.7519 | 0.10488 | 8 | 3.6716e-05 | 3321 | 27.8163 | 2364 | 0.0016933 | 0.013546 | 2519 |  | 2906
4537 | LAKEWOOD 2107396264 | 13532107 | LAKEWOOD 2107 | 396264 | FALSE | 10259.9636 | 7704.2 | 4.7882 | 95 | 0.00010348 | 1560 | 21.8184 | 2427 | 0.0016927 | 0.16081 | 2520 |  | 2903
6727 | BRUNSWICK 11032200 | 152481103 | BRUNSWICK 1103 | 2200 | FALSE | 8965.9106 | 8965.9106 | 5.5723 | 64 | 0.00010183 | 1607 | 17.8909 | 2484 | 0.0016888 | 0.10808 | 2521 | 54.83 | 105
5446 | PENRYN 11052406 | 152561105 | PENRYN 1105 | 2406 | TRUE | 6309.8622 | 123.5636 | 0.076795 | 50 | 0.0001488 | 754 | 13.0398 | 2568 | 0.0016854 | 0.084272 | 2522 | 0.98 | 736
9065 | OTTER 11017611 | 182941101 | OTTER 1101 | 7611 | FALSE | 7068.0362 | 7068.0362 | 4.3928 | 42 | 8.7447e-05 | 2001 | 37.9943 | 2291 | 0.0016834 | 0.070701 | 2523 | 0.49 | 896
4321 | BRUNSWICK 110633050 | 152481106 | BRUNSWICK 1106 | 33050 | FALSE | 6143.4432 | 1793.1664 | 1.1145 | 56 | 0.000194 | 425 | 9.4021 | 2637 | 0.0016799 | 0.094072 | 2524 | 2.96 | 571
7573 | ROSSMOOR 110639424 | 14161106 | ROSSMOOR 1106 | 39424 | FALSE | 3992.9225 | 1481.6598 | 0.92086 | 36 | 9.8e-05 | 1690 | 17.4915 | 2491 | 0.0016754 | 0.060313 | 2525 |  | 3138
1005 | ROB ROY 21045082 | 83692104 | ROB ROY 2104 | 5082 | FALSE | 33362.418 | 32012.7007 | 19.896 | 215 | 0.00012065 | 1172 | 16.3155 | 2512 | 0.0016672 | 0.35844 | 2526 | 2.33 | 613
5885 | LAURELES 11122768 | 182371112 | LAURELES 1112 | 2768 | FALSE | 12969.9695 | 10109.7249 | 6.2832 | 92 | 7.5187e-05 | 2326 | 22.2701 | 2424 | 0.0016647 | 0.15315 | 2527 | 0.05 | 2021
2281 | VOLTA 110185234 | 102541101 | VOLTA 1101 | 85234 | FALSE | 12730.8347 | 12730.8347 | 7.9123 | 92 | 7.7367e-05 | 2279 | 30.0376 | 2343 | 0.0016524 | 0.15202 | 2528 | 0.02 | 2526
3545 | PACIFICA 1104230272 | 22811104 | PACIFICA 1104 | 230272 | FALSE | 1833.3676 | 1377.39 | 0.85605 | 18 | 5.0412e-05 | 3031 | 15.9138 | 2516 | 0.0016485 | 0.029673 | 2529 |  | 2836
6564 | NEWBURG 1131557468 | 192151131 | NEWBURG 1131 | 557468 | FALSE | 3768.3144 | 1423.6732 | 0.88482 | 28 | 0.0001751 | 528 | 10.813 | 2614 | 0.0016475 | 0.046129 | 2530 |  | 3042
2123 | IGNACIO 11011300 | 42481101 | IGNACIO 1101 | 1300 | FALSE | 9816.2612 | 5145.088 | 3.1977 | 84 | 0.00010467 | 1538 | 15.4386 | 2525 | 0.0016445 | 0.13814 | 2531 | 0.08 | 1580
7516 | SAN LUIS OBISPO 1107CB | 182631107 | SAN LUIS OBISPO 1107 | CB | FALSE | 1947.472 | 1251.1033 | 0.77757 | 19 | 5.3489e-05 | 2951 | 32.6064 | 2325 | 0.0016436 | 0.031229 | 2532 | 0.03 | 2359
1994 | SILVERADO 2103218894 | 43432103 | SILVERADO 2103 | 218894 | TRUE | 1856.9722 | 540.1994 | 0.33574 | 14 | 6.9371e-05 | 2494 | 15.8967 | 2518 | 0.00163 | 0.022819 | 2533 |  | 2758
10204 | DUNBAR 110113481 | 43071101 | DUNBAR 1101 | 13481 | TRUE | 1739.6965 | 0 | 0 | 14 | 0.0001142 | 1314 | 13.6321 | 2559 | 0.0016289 | 0.022805 | 2534 | 0.03 | 2380
3837 | AUBERRY 1101D4982 | 254151101 | AUBERRY 1101 | D4982 | FALSE | 4312.861 | 4312.861 | 2.6805 | 21 | 3.0625e-05 | 3421 | 38.5371 | 2287 | 0.0016248 | 0.034121 | 2535 | 33.37 | 222
586 | WEIMAR 11022038 | 152491102 | WEIMAR 1102 | 2038 | FALSE | 21510.9233 | 21510.9233 | 13.3691 | 155 | 0.00018694 | 462 | 18.4659 | 2468 | 0.0016155 | 0.2504 | 2536 | 0.06 | 1908
5218 | SYCAMORE CREEK 11112268 | 102971111 | SYCAMORE CREEK 1111 | 2268 | FALSE | 35117.3516 | 35117.3516 | 21.8256 | 217 | 8.4177e-05 | 2087 | 23.7294 | 2408 | 0.0016039 | 0.34805 | 2537 | 69.93 | 69
1040 | GANSNER 110152664 | 103021101 | GANSNER 1101 | 52664 | TRUE | 5174.4008 | 284.4033 | 0.17676 | 44 | 5.8197e-05 | 2829 | 25.8938 | 2380 | 0.0016028 | 0.070524 | 2538 |  | 2705
3804 | POINT MORETTI 110110726 | 82931101 | POINT MORETTI 1101 | 10726 | FALSE | 16936.721 | 16936.721 | 10.5262 | 124 | 0.00026294 | 188 | 7.1636 | 2683 | 0.0016007 | 0.19849 | 2539 | 15.77 | 346
1389 | STANISLAUS 17011331 | 162821701 | STANISLAUS 1701 | 1331 | FALSE | 7064.7733 | 7064.7733 | 4.3908 | 63 | 0.00010598 | 1495 | 12.1416 | 2583 | 0.0015977 | 0.10065 | 2540 | 46.2 | 144
8302 | VALLEY VIEW 1106P166 | 14341106 | VALLEY VIEW 1106 | P166 | FALSE | 7343.1285 | 7068.5222 | 4.3931 | 27 | 0.00014292 | 827 | 10.6287 | 2617 | 0.0015975 | 0.043133 | 2541 | 0.97 | 738
7677 | POINT MORETTI 110136516 | 82931101 | POINT MORETTI 1101 | 36516 | FALSE | 6699.7019 | 6699.7019 | 4.1639 | 53 | 0.00037131 | 77 | 6.3459 | 2704 | 0.0015908 | 0.08431 | 2542 | 29.13 | 244
9231 | ROB ROY 21045304 | 83692104 | ROB ROY 2104 | 5304 | FALSE | 8039.9737 | 5763.285 | 3.5819 | 60 | 9.186e-05 | 1848 | 18.674 | 2464 | 0.0015784 | 0.094707 | 2543 | 0.05 | 1963
10838 | LAS GALLINAS A 1106685852 | 42991106 | LAS GALLINAS A 1106 | 685852 | TRUE | 222.9305 | 104.9331 | 0.065216 | 3 | 0.00011257 | 1352 | 15.9116 | 2517 | 0.0015648 | 0.0046945 | 2544 |  | 3611
1125 | LAS GALLINAS A 1106CB | 42991106 | LAS GALLINAS A 1106 | CB | TRUE | 16165.5618 | 153.7468 | 0.095554 | 111 | 7.0207e-05 | 2463 | 11.081 | 2607 | 0.0015644 | 0.17365 | 2545 | 0.1 | 1466
6613 | HICKS 111660050 | 83431116 | HICKS 1116 | 60050 | FALSE | 13116.246 | 13116.246 | 8.1518 | 98 | 0.00010761 | 1461 | 16.5517 | 2508 | 0.0015546 | 0.15235 | 2546 | 0.1 | 1480
10410 | PUEBLO 2102391312 | 43292102 | PUEBLO 2102 | 391312 | TRUE | 1866.0468 | 229.6394 | 0.14272 | 13 | 5.8919e-05 | 2810 | 14.6684 | 2538 | 0.0015528 | 0.020186 | 2547 |  | 3544
3988 | SAN RAFAEL 1108322 | 42011108 | SAN RAFAEL 1108 | 322 | FALSE | 11857.5634 | 11550.5948 | 7.1787 | 88 | 0.0001706 | 560 | 11.411 | 2599 | 0.0015474 | 0.13618 | 2548 | 1.05 | 721
3811 | OAKLAND X 1106950688 | 12541106 | OAKLAND X 1106 | 950688 | FALSE | 5883.5054 | 5883.5054 | 3.6566 | 50 | 0.00010781 | 1454 | 17.1924 | 2501 | 0.0015407 | 0.077034 | 2549 |  | 2854
1254 | CURTIS 17039240 | 163351703 | CURTIS 1703 | 9240 | FALSE | 17656.496 | 17656.496 | 10.9736 | 151 | 8.9367e-05 | 1936 | 23.8246 | 2406 | 0.0015394 | 0.23246 | 2550 | 0.09 | 1524
9703 | VOLTA 110280982 | 102541102 | VOLTA 1102 | 80982 | TRUE | 836.5231 | 836.5231 | 0.5199 | 8 | 7.4451e-05 | 2347 | 11.9509 | 2588 | 0.0015382 | 0.012305 | 2551 | 41.95 | 172
8204 | BEN LOMOND 04015144 | 83040401 | BEN LOMOND 0401 | 5144 | FALSE | 6368.9288 | 6368.9288 | 3.9583 | 36 | 0.00020138 | 392 | 8.6508 | 2650 | 0.0015295 | 0.055061 | 2552 | 32.7 | 225
4922 | BIG RIVER 11013019 | 43081101 | BIG RIVER 1101 | 3019 | TRUE | 1511.5981 | 426.9368 | 0.26534 | 11 | 7.3049e-05 | 2394 | 21.6652 | 2431 | 0.0015165 | 0.016682 | 2553 |  | 2928
4844 | SANTA ROSA A 1104173590 | 42151104 | SANTA ROSA A 1104 | 173590 | FALSE | 6901.197 | 6901.197 | 4.2891 | 46 | 9.087e-05 | 1887 | 19.2098 | 2458 | 0.0015131 | 0.069603 | 2554 |  | 2921
7483 | FLINT 1101CB | 152531101 | FLINT 1101 | CB | FALSE | 4176.9151 | 1037.2766 | 0.64467 | 36 | 0.00021226 | 350 | 8.6501 | 2651 | 0.0015072 | 0.054259 | 2555 | 0.03 | 2345
6669 | DUNBAR 1101234 | 43071101 | DUNBAR 1101 | 234 | FALSE | 10290.6171 | 5584.5077 | 3.4708 | 81 | 0.0001531 | 719 | 12.3014 | 2581 | 0.0015051 | 0.12191 | 2556 | 0.04 | 2094
7886 | OAKHURST 1102CB | 254421102 | OAKHURST 1102 | CB | FALSE | 7703.9355 | 4253.8822 | 2.6438 | 61 | 0.00011905 | 1206 | 11.75 | 2592 | 0.0014997 | 0.091479 | 2557 | 1.94 | 628
1710 | ELK 110191336 | 42981101 | ELK 1101 | 91336 | FALSE | 13315.5222 | 12740.7114 | 7.9184 | 78 | 8.2847e-05 | 2135 | 14.0784 | 2546 | 0.0014969 | 0.11676 | 2558 | 0.04 | 2153
583 | MONTE RIO 1111969182 | 42811111 | MONTE RIO 1111 | 969182 | FALSE | 8578.2654 | 8578.2654 | 5.3314 | 64 | 0.00023272 | 274 | 7.8723 | 2672 | 0.0014937 | 0.095599 | 2559 |  | 2685
3182 | KONOCTI 1108950 | 43311108 | KONOCTI 1108 | 950 | FALSE | 11853.1557 | 9978.6098 | 6.2017 | 85 | 0.00011166 | 1376 | 9.5946 | 2629 | 0.0014937 | 0.12697 | 2560 | 0.09 | 1575
5332 | CLAYTON 2212CB | 12022212 | CLAYTON 2212 | CB | FALSE | 17569.8608 | 1899.4744 | 1.1805 | 140 | 3.3628e-05 | 3373 | 17.212 | 2499 | 0.0014894 | 0.20851 | 2561 | 0.55 | 873
4270 | LAS GALLINAS A 1104304 | 42991104 | LAS GALLINAS A 1104 | 304 | TRUE | 3131.1603 | 221.043 | 0.13738 | 27 | 7.2267e-05 | 2410 | 12.9614 | 2570 | 0.0014798 | 0.039953 | 2562 | 0.03 | 2304
886 | SALT SPRINGS 21024796 | 163692102 | SALT SPRINGS 2102 | 4796 | FALSE | 11571.4706 | 11571.4706 | 7.1917 | 114 | 8.3272e-05 | 2126 | 15.4981 | 2524 | 0.0014707 | 0.16766 | 2563 | 50.63 | 117
1846 | BIG RIVER 11013002 | 43081101 | BIG RIVER 1101 | 3002 | FALSE | 13206.8342 | 11656.2739 | 7.2444 | 76 | 8.5336e-05 | 2046 | 10.9995 | 2610 | 0.001464 | 0.11126 | 2564 | 0.15 | 1296
6005 | MIRABEL 1101201156 | 42091101 | MIRABEL 1101 | 201156 | FALSE | 2780.2158 | 2335.0863 | 1.4513 | 26 | 0.000132 | 983 | 11.0364 | 2609 | 0.0014632 | 0.038044 | 2565 |  | 2996
9286 | SOLEDAD 2101315500 | 182052101 | SOLEDAD 2101 | 315500 | FALSE | 5515.195 | 1783.0288 | 1.1082 | 22 | 2.1144e-05 | 3532 | 19.9522 | 2450 | 0.0014578 | 0.032073 | 2566 |  | 3335
2001 | SAN RAFAEL 110839156 | 42011108 | SAN RAFAEL 1108 | 39156 | FALSE | 7678.6279 | 5580.9258 | 3.4686 | 62 | 0.00036657 | 79 | 5.0499 | 2749 | 0.0014467 | 0.089693 | 2567 | 0.4 | 949
2593 | HIGGINS 1104533648 | 152691104 | HIGGINS 1104 | 533648 | FALSE | 10867.8258 | 10867.8258 | 6.7544 | 93 | 0.00016205 | 621 | 8.4995 | 2655 | 0.0014323 | 0.13321 | 2568 | 0.11 | 1415
2853 | EL DORADO PH 2101668674 | 152762101 | EL DORADO PH 2101 | 668674 | FALSE | 15298.6549 | 15298.6549 | 9.5082 | 112 | 0.00024869 | 220 | 8.5559 | 2654 | 0.0014289 | 0.16003 | 2569 |  | 2801
701 | CAMP EVERS 210512590 | 83622105 | CAMP EVERS 2105 | 12590 | FALSE | 8818.0631 | 8233.9726 | 5.1174 | 69 | 0.00032896 | 102 | 7.9903 | 2671 | 0.0014267 | 0.09844 | 2570 | 0.34 | 980
9206 | SISQUOC 110245261 | 182811102 | SISQUOC 1102 | 45261 | TRUE | 20192.7526 | 164.9958 | 0.10255 | 10 | 7.3888e-05 | 2362 | 8.6022 | 2652 | 0.001423 | 0.01423 | 2571 |  | 3326
6505 | MONTE RIO 11131313 | 42811113 | MONTE RIO 1113 | 1313 | FALSE | 1996.4298 | 1996.4298 | 1.2408 | 19 | 0.00014421 | 810 | 12.5764 | 2576 | 0.0014057 | 0.026709 | 2572 | 44.58 | 156
4406 | COTATI 110475972 | 42271104 | COTATI 1104 | 75972 | FALSE | 7223.394 | 5386.1403 | 3.3475 | 61 | 6.5028e-05 | 2609 | 22.3 | 2423 | 0.0013938 | 0.085021 | 2573 | 0.52 | 885
7967 | MENLO 11038982 | 24131103 | MENLO 1103 | 8982 | FALSE | 7434.3823 | 7434.3823 | 4.6205 | 50 | 0.00014907 | 751 | 11.9525 | 2587 | 0.0013928 | 0.06964 | 2574 | 0.08 | 1625
9897 | ORO FINO 110239154 | 103031102 | ORO FINO 1102 | 39154 | FALSE | 1419.8889 | 1419.8889 | 0.88247 | 11 | 0.00019824 | 403 | 21.6746 | 2430 | 0.0013923 | 0.015315 | 2575 | 62.39 | 84
5536 | GUALALA 1111CB | 42841111 | GUALALA 1111 | CB | FALSE | 6227.6638 | 6227.6638 | 3.8705 | 47 | 0.00010177 | 1608 | 5.1216 | 2747 | 0.0013913 | 0.065391 | 2576 | 0.03 | 2337
3869 | PINE GROVE 11021765 | 163751102 | PINE GROVE 1102 | 1765 | FALSE | 2336.7952 | 2336.7952 | 1.4523 | 20 | 0.00017078 | 558 | 6.0123 | 2713 | 0.0013887 | 0.027774 | 2577 | 15.71 | 348
2705 | FORT ORD 210736596 | 182402107 | FORT ORD 2107 | 36596 | FALSE | 20043.7619 | 6572.3951 | 4.0848 | 145 | 1.719e-05 | 3570 | 17.052 | 2503 | 0.0013847 | 0.20079 | 2578 | 0.03 | 2397
5302 | BIG BASIN 11015000 | 82841101 | BIG BASIN 1101 | 5000 | FALSE | 3149.0186 | 3149.0186 | 1.9571 | 23 | 0.00041733 | 64 | 2.1336 | 2834 | 0.0013814 | 0.031772 | 2579 | 24.55 | 277
10692 | ROSSMOOR 1109CB | 14161109 | ROSSMOOR 1109 | CB | TRUE | 244.7023 | 7.571 | 0.0047054 | 6 | 8.8688e-05 | 1962 | 31.698 | 2332 | 0.001321 | 0.0079259 | 2580 |  | 3593
5396 | FORT BRAGG A 11041316 | 42761104 | FORT BRAGG A 1104 | 1316 | FALSE | 22645.6685 | 22101.0688 | 13.7359 | 166 | 7.7968e-05 | 2260 | 13.3542 | 2565 | 0.0013124 | 0.21786 | 2581 | 0.12 | 1400
6380 | GUALALA 111135562 | 42841111 | GUALALA 1111 | 35562 | FALSE | 22914.0776 | 22914.0776 | 14.2412 | 147 | 0.00010505 | 1525 | 11.7038 | 2593 | 0.0013006 | 0.19119 | 2582 | 0.16 | 1270
5878 | OLEMA 11011318 | 42291101 | OLEMA 1101 | 1318 | FALSE | 16637.0018 | 13693.4076 | 8.5105 | 113 | 0.00013033 | 1004 | 8.2659 | 2664 | 0.0012974 | 0.14661 | 2583 | 9.77 | 404
7013 | SALT SPRINGS 2102L491 | 163692102 | SALT SPRINGS 2102 | L491 | FALSE | 3564.5514 | 3564.5514 | 2.2154 | 31 | 0.00010065 | 1632 | 5.4343 | 2732 | 0.0012903 | 0.039999 | 2584 | 33.77 | 219
3314 | LLAGAS 2101XR244 | 83182101 | LLAGAS 2101 | XR244 | TRUE | 22757.8317 | 0 | 0 | 157 | 6.3757e-05 | 2654 | 15.2591 | 2527 | 0.0012825 | 0.20135 | 2585 | 0.59 | 855
595 | GARBERVILLE 1103CB | 192221103 | GARBERVILLE 1103 | CB | TRUE | 3592.4976 | 971.3906 | 0.60372 | 31 | 0.0002505 | 215 | 3.3852 | 2798 | 0.0012726 | 0.039451 | 2586 | 0.05 | 1979
842 | ELK 11011272 | 42981101 | ELK 1101 | 1272 | FALSE | 36077.8728 | 35548.517 | 22.0935 | 236 | 0.00010152 | 1616 | 17.6496 | 2487 | 0.0012681 | 0.29926 | 2587 | 0.25 | 1089
3308 | SNEATH LANE 1106CB | 22721106 | SNEATH LANE 1106 | CB | FALSE | 9891.2145 | 4885.2685 | 3.0362 | 66 | 2.8183e-05 | 3454 | 23.8416 | 2402 | 0.0012656 | 0.083532 | 2588 | 0.03 | 2371
4674 | WEST POINT 110112256 | 163201101 | WEST POINT 1101 | 12256 | FALSE | 10425.1159 | 10425.1159 | 6.4793 | 86 | 9.8504e-05 | 1679 | 19.6956 | 2453 | 0.0012622 | 0.10855 | 2589 | 60.88 | 87
141 | MORRO BAY 1102W34 | 183011102 | MORRO BAY 1102 | W34 | FALSE | 15456.5208 | 12223.0154 | 7.5967 | 112 | 3.8291e-05 | 3294 | 31.2471 | 2337 | 0.0012584 | 0.14094 | 2590 |  | 2657
8023 | HOLLISTER 2105903238 | 182492105 | HOLLISTER 2105 | 903238 | FALSE | 9893.8007 | 6450.8713 | 4.0092 | 30 | 4.7333e-05 | 3108 | 30.0306 | 2344 | 0.001258 | 0.037741 | 2591 |  | 3186
53 | DUNBAR 1102448 | 43071102 | DUNBAR 1102 | 448 | FALSE | 14554.2556 | 3932.5973 | 2.4441 | 116 | 9.7296e-05 | 1707 | 15.8508 | 2519 | 0.001256 | 0.1457 | 2592 |  | 2652
5111 | ALHAMBRA 110581514 | 14101105 | ALHAMBRA 1105 | 81514 | FALSE | 7697.8392 | 4781.286 | 2.9716 | 65 | 8.7032e-05 | 2011 | 13.7396 | 2556 | 0.0012525 | 0.08141 | 2593 | 0.04 | 2121
347 | BRUNSWICK 11052204 | 152481105 | BRUNSWICK 1105 | 2204 | FALSE | 11625.6324 | 11625.6324 | 7.2254 | 84 | 9.4601e-05 | 1775 | 11.1006 | 2606 | 0.0012429 | 0.1044 | 2594 | 40.14 | 185
2860 | CAMP EVERS 210311046 | 83622103 | CAMP EVERS 2103 | 11046 | FALSE | 25866.5621 | 25866.5621 | 16.0762 | 194 | 0.00016384 | 601 | 6.3121 | 2705 | 0.0012326 | 0.23912 | 2595 | 1.33 | 683
5152 | WOODSIDE 11018522 | 24251101 | WOODSIDE 1101 | 8522 | FALSE | 15153.8377 | 3071.2008 | 1.9088 | 123 | 0.0001684 | 573 | 8.4903 | 2656 | 0.0012059 | 0.14833 | 2596 | 0.11 | 1425
10217 | PAUL SWEET 2102959032 | 83252102 | PAUL SWEET 2102 | 959032 | FALSE | 1582.9544 | 1283.5288 | 0.79772 | 11 | 0.00012885 | 1030 | 15.1847 | 2528 | 0.0012034 | 0.013238 | 2597 |  | 3517
6918 | DUNBAR 1103872066 | 43071103 | DUNBAR 1103 | 872066 | TRUE | 1285.5374 | 856.8881 | 0.53256 | 13 | 8.9931e-05 | 1916 | 14.7027 | 2535 | 0.0011906 | 0.015478 | 2598 |  | 3074
5057 | WEIMAR 11012764 | 152491101 | WEIMAR 1101 | 2764 | FALSE | 9871.3778 | 9871.3778 | 6.1351 | 68 | 0.0002671 | 178 | 5.6584 | 2724 | 0.0011906 | 0.080958 | 2599 | 0.05 | 2046
8401 | IGNACIO 11051943 | 42481105 | IGNACIO 1105 | 1943 | FALSE | 1959.963 | 1959.963 | 1.2181 | 17 | 0.00014604 | 788 | 5.6591 | 2723 | 0.0011872 | 0.020183 | 2600 |  | 3220
2098 | VOLTA 1102641544 | 102541102 | VOLTA 1102 | 641544 | FALSE | 7956.2573 | 7956.2573 | 4.9448 | 58 | 0.00010868 | 1431 | 9.0793 | 2642 | 0.0011816 | 0.068531 | 2601 |  | 2763
5971 | SANTA ROSA A 110464565 | 42151104 | SANTA ROSA A 1104 | 64565 | FALSE | 1284.2848 | 1284.2848 | 0.79819 | 13 | 0.00016067 | 634 | 14.7117 | 2534 | 0.001175 | 0.015275 | 2602 | 0.3 | 1013
1887 | NAPA 1112CB | 42021112 | NAPA 1112 | CB | TRUE | 26742.8753 | 940.9991 | 0.58483 | 226 | 4.1039e-05 | 3242 | 20.6872 | 2439 | 0.0011724 | 0.26497 | 2603 |  | 2752
5833 | DEL MONTE 21049500 | 182222104 | DEL MONTE 2104 | 9500 | FALSE | 10910.9002 | 9168.0738 | 5.698 | 71 | 6.6682e-05 | 2565 | 18.8342 | 2462 | 0.0011663 | 0.082807 | 2604 | 1.62 | 662
3301 | RALSTON 1101836528 | 24141101 | RALSTON 1101 | 836528 | FALSE | 4695.3621 | 4679.584 | 2.9084 | 39 | 3.0209e-05 | 3424 | 39.6633 | 2275 | 0.0011552 | 0.045051 | 2605 |  | 2820
1278 | LOS GATOS 1107CB | 82021107 | LOS GATOS 1107 | CB | FALSE | 25409.8546 | 24616.6476 | 15.2993 | 192 | 0.00012212 | 1146 | 9.4762 | 2636 | 0.0011504 | 0.22088 | 2606 | 0.14 | 1327
1215 | SAN RAMON 2106CB | 14232106 | SAN RAMON 2106 | CB | TRUE | 3504.1175 | 755.1177 | 0.46931 | 25 | 5.9264e-05 | 2797 | 9.8829 | 2625 | 0.001149 | 0.028724 | 2607 |  | 2717
10840 | CLOVERDALE 1101704542 | 42821101 | CLOVERDALE 1101 | 704542 | TRUE | 487.4963 | 345.9417 | 0.215 | 3 | 0.00010371 | 1556 | 10.6423 | 2616 | 0.0011475 | 0.0034424 | 2608 |  | 3612
9582 | LOS OSITOS 2102624200 | 182082102 | LOS OSITOS 2102 | 624200 | FALSE | 3744.0071 | 2491.858 | 1.5487 | 6 | 9.1262e-06 | 3614 | 78.1632 | 2058 | 0.0011432 | 0.0068593 | 2609 |  | 3383
6642 | STANISLAUS 1702L5381 | 162821702 | STANISLAUS 1702 | L5381 | FALSE | 1955.4877 | 1955.4877 | 1.2153 | 15 | 8.6227e-05 | 2029 | 11.1601 | 2603 | 0.0011429 | 0.017144 | 2610 | 63.74 | 80
10129 | VALLEY VIEW 1103218424 | 14341103 | VALLEY VIEW 1103 | 218424 | TRUE | 877.6167 | 866.5125 | 0.53854 | 4 | 6.9394e-05 | 2493 | 17.8902 | 2485 | 0.0011372 | 0.0045488 | 2611 |  | 3498
2575 | BIG RIVER 110155402 | 43081101 | BIG RIVER 1101 | 55402 | FALSE | 14989.6887 | 3994.4825 | 2.4826 | 104 | 6.4572e-05 | 2623 | 16.7266 | 2505 | 0.0011234 | 0.11683 | 2612 | 0.02 | 2517
2609 | MIRABEL 1102503000 | 42091102 | MIRABEL 1102 | 503000 | FALSE | 7554.2208 | 7373.131 | 4.5824 | 54 | 0.00017004 | 564 | 3.5877 | 2787 | 0.0011185 | 0.060401 | 2613 |  | 2789
8405 | MONTE RIO 1111240 | 42811111 | MONTE RIO 1111 | 240 | FALSE | 4953.3762 | 4953.3762 | 3.0785 | 42 | 0.00020071 | 393 | 8.5626 | 2653 | 0.0011134 | 0.046762 | 2614 | 27.15 | 261
1947 | ROB ROY 210410930 | 83692104 | ROB ROY 2104 | 10930 | FALSE | 18316.5864 | 1585.2477 | 0.98524 | 149 | 9.2072e-05 | 1841 | 11.2167 | 2602 | 0.0011126 | 0.16578 | 2615 | 0.03 | 2315
6789 | MIRABEL 11021139 | 42091102 | MIRABEL 1102 | 1139 | FALSE | 3291.1128 | 3291.1128 | 2.0454 | 25 | 0.00021661 | 335 | 5.771 | 2718 | 0.0011071 | 0.027677 | 2616 | 19.12 | 313
10452 | PIT NO 3 21011480 | 103732101 | PIT NO 3 2101 | 1480 | FALSE | 3913.3341 | 3463.9371 | 2.1529 | 20 | 6.904e-05 | 2506 | 14.3241 | 2543 | 0.0011038 | 0.022077 | 2617 | 0.02 | 2410
3881 | CORRAL 110275622 | 162991102 | CORRAL 1102 | 75622 | FALSE | 9209.8908 | 1956.9061 | 1.2162 | 78 | 8.9335e-05 | 1938 | 14.1186 | 2545 | 0.0010989 | 0.085711 | 2618 | 1.24 | 694
656 | MORAGA 1105CB | 13801105 | MORAGA 1105 | CB | FALSE | 17419.9506 | 9244.2642 | 5.7453 | 121 | 8.2774e-05 | 2137 | 22.4988 | 2417 | 0.001078 | 0.13044 | 2619 | 36.92 | 204
7044 | SALT SPRINGS 210297924 | 163692102 | SALT SPRINGS 2102 | 97924 | FALSE | 8287.4089 | 8287.4089 | 5.1507 | 49 | 8.4247e-05 | 2084 | 16.5614 | 2507 | 0.0010653 | 0.052198 | 2620 | 28.19 | 252
1866 | HIGGINS 1104842642 | 152691104 | HIGGINS 1104 | 842642 | FALSE | 9353.842 | 9353.842 | 5.8135 | 80 | 0.00015044 | 731 | 10.167 | 2622 | 0.0010503 | 0.084021 | 2621 | 0.11 | 1445
1316 | SHADY GLEN 1101CB | 152431101 | SHADY GLEN 1101 | CB | FALSE | 8798.7393 | 5676.9517 | 3.5282 | 72 | 0.00028651 | 144 | 7.3277 | 2682 | 0.0010502 | 0.075616 | 2622 | 5.26 | 492
8148 | MIWUK 1702S1547 | 163661702 | MIWUK 1702 | S1547 | FALSE | 4459.8848 | 4459.8848 | 2.7718 | 39 | 5.3114e-05 | 2964 | 14.6954 | 2536 | 0.0010487 | 0.040901 | 2623 | 82.41 | 44
4763 | SNEATH LANE 11071277 | 22721107 | SNEATH LANE 1107 | 1277 | TRUE | 3471.3767 | 0 | 0 | 30 | 4.0209e-05 | 3263 | 12.7259 | 2574 | 0.001018 | 0.030539 | 2624 | 0.04 | 2212
10287 | DUNLAP 11027290 | 254061102 | DUNLAP 1102 | 7290 | FALSE | 1075.4071 | 1075.4071 | 0.66837 | 8 | 2.8269e-05 | 3452 | 23.8308 | 2405 | 0.0010126 | 0.0081011 | 2625 | 0 | 2635
9998 | RESEARCH 2102644462 | 14692102 | RESEARCH 2102 | 644462 | TRUE | 2486.8085 | 567.6161 | 0.35278 | 24 | 0.00010098 | 1625 | 12.9287 | 2571 | 0.0010124 | 0.024298 | 2626 |  | 3468
1937 | SARATOGA 1107LC12 | 83371107 | SARATOGA 1107 | LC12 | FALSE | 12044.6481 | 12044.6481 | 7.4858 | 86 | 0.00017659 | 521 | 13.8877 | 2554 | 0.0010097 | 0.086838 | 2627 | 0.56 | 865
3 | HIGGINS 1104498932 | 152691104 | HIGGINS 1104 | 498932 | FALSE | 6861.4641 | 6024.2456 | 3.7441 | 57 | 0.00014672 | 777 | 8.6826 | 2649 | 0.0010076 | 0.057431 | 2628 | 0.09 | 1548
7928 | HALSEY 11015731 | 152241101 | HALSEY 1101 | 5731 | FALSE | 5029.6194 | 5029.6194 | 3.1259 | 41 | 0.00015547 | 690 | 3.5444 | 2790 | 0.0010067 | 0.041274 | 2629 | 0.05 | 1973
5582 | TAMARACK 1101CB | 152291101 | TAMARACK 1101 | CB | FALSE | 28734.8817 | 28123.7558 | 17.479 | 148 | 7.11e-05 | 2442 | 13.9274 | 2552 | 0.0010065 | 0.14896 | 2630 | 0.36 | 966
5935 | MORAGA 1103CB | 13801103 | MORAGA 1103 | CB | FALSE | 10346.1129 | 2141.3708 | 1.3309 | 82 | 8.1676e-05 | 2163 | 6.4364 | 2698 | 0.0010058 | 0.082476 | 2631 | 0.06 | 1846
6299 | PEORIA 170587222 | 163781705 | PEORIA 1705 | 87222 | FALSE | 8479.914 | 8240.0573 | 5.1212 | 57 | 0.00010497 | 1529 | 10.4869 | 2620 | 0.0010031 | 0.057176 | 2632 | 0.1 | 1504
2943 | PAUL SWEET 2105CB | 83252105 | PAUL SWEET 2105 | CB | FALSE | 14092.576 | 11980.8022 | 7.4461 | 86 | 0.00012586 | 1080 | 5.5912 | 2727 | 0.0010024 | 0.086208 | 2633 | 0.22 | 1132
9018 | GREEN VALLEY 2101509068 | 83192101 | GREEN VALLEY 2101 | 509068 | FALSE | 2868.1374 | 1655.4712 | 1.0289 | 22 | 0.00010648 | 1487 | 17.3491 | 2495 | 0.0010019 | 0.022042 | 2634 |  | 3297
8604 | MORGAN HILL 2105975388 | 83242105 | MORGAN HILL 2105 | 975388 | TRUE | 2101.0589 | 775.2264 | 0.48181 | 18 | 4.0105e-05 | 3265 | 13.2566 | 2567 | 0.0010016 | 0.018029 | 2635 |  | 3242
5120 | PAUL SWEET 21045394 | 83252104 | PAUL SWEET 2104 | 5394 | FALSE | 24529.1372 | 23340.3938 | 14.5061 | 180 | 0.00013063 | 998 | 7.7218 | 2674 | 0.00099214 | 0.17859 | 2636 | 43.45 | 169
6690 | GUALALA 1111887180 | 42841111 | GUALALA 1111 | 887180 | FALSE | 8692.4371 | 8589.4892 | 5.3384 | 61 | 5.5738e-05 | 2897 | 12.9178 | 2572 | 0.00098628 | 0.060163 | 2637 | 0.07 | 1715
3875 | FORT BRAGG A 11014698 | 42761101 | FORT BRAGG A 1101 | 4698 | FALSE | 12883.0062 | 12883.0062 | 8.0068 | 101 | 0.00018389 | 481 | 12.0639 | 2584 | 0.00097756 | 0.098734 | 2638 | 0.05 | 1998
8479 | SALT SPRINGS 2102L7283 | 163692102 | SALT SPRINGS 2102 | L7283 | FALSE | 1053.4945 | 1053.4945 | 0.65475 | 12 | 7.514e-05 | 2329 | 13.9335 | 2551 | 0.00097446 | 0.011693 | 2639 | 29.37 | 241
1105 | PLACER 110451732 | 152461104 | PLACER 1104 | 51732 | FALSE | 12971.5884 | 1093.5921 | 0.67967 | 110 | 0.00019845 | 402 | 3.0886 | 2809 | 0.00097323 | 0.10706 | 2640 | 0.02 | 2495
6916 | BEN LOMOND 110196738 | 83041101 | BEN LOMOND 1101 | 96738 | FALSE | 10792.8538 | 10792.8538 | 6.7078 | 84 | 0.00020283 | 387 | 5.4435 | 2731 | 0.00097276 | 0.081712 | 2641 | 21.67 | 298
5851 | SAN RAFAEL 1109692576 | 42011109 | SAN RAFAEL 1109 | 692576 | FALSE | 5517.9962 | 3874.9491 | 2.4083 | 51 | 0.0001303 | 1007 | 7.0569 | 2686 | 0.0009691 | 0.049424 | 2642 |  | 2983
1894 | HALF MOON BAY 11028848 | 24101102 | HALF MOON BAY 1102 | 8848 | FALSE | 16215.0785 | 6200.2521 | 3.8535 | 117 | 6.6972e-05 | 2558 | 11.0461 | 2608 | 0.00096385 | 0.11277 | 2643 | 0.22 | 1123
3844 | OLEMA 110150396 | 42291101 | OLEMA 1101 | 50396 | FALSE | 21037.3757 | 20827.3892 | 12.9443 | 162 | 8.5221e-05 | 2050 | 11.5065 | 2597 | 0.00096084 | 0.15566 | 2644 | 20.38 | 306
8685 | SANTA ROSA A 1111114 | 42151111 | SANTA ROSA A 1111 | 114 | TRUE | 4957.8887 | 17.4908 | 0.010871 | 40 | 8.3173e-05 | 2128 | 9.1847 | 2640 | 0.00096055 | 0.038422 | 2645 | 8.42 | 426
3877 | LOS GATOS 110660116 | 82021106 | LOS GATOS 1106 | 60116 | FALSE | 19634.1928 | 19634.1928 | 12.2027 | 151 | 0.00020011 | 397 | 4.9468 | 2757 | 0.00095505 | 0.14421 | 2646 | 0.89 | 751
46 | MONTE RIO 11111703 | 42811111 | MONTE RIO 1111 | 1703 | FALSE | 2213.9946 | 2213.9946 | 1.376 | 16 | 0.00013016 | 1008 | 6.0137 | 2712 | 0.00095446 | 0.015271 | 2647 | 43.57 | 165
2992 | EMERALD LAKE 0401CB | 24080401 | EMERALD LAKE 0401 | CB | FALSE | 21117.9549 | 15035.2163 | 9.3444 | 130 | 6.8162e-05 | 2531 | 7.7386 | 2673 | 0.00094726 | 0.12314 | 2648 | 0.52 | 887
5798 | DIAMOND SPRINGS 1107217974 | 152261107 | DIAMOND SPRINGS 1107 | 217974 | FALSE | 6862.6922 | 6593.0651 | 4.0976 | 44 | 0.00013259 | 971 | 7.0882 | 2685 | 0.00093976 | 0.04135 | 2649 |  | 2978
5351 | TEMPLETON 2113A32 | 183052113 | TEMPLETON 2113 | A32 | FALSE | 9519.6113 | 2633.3805 | 1.6367 | 76 | 6.2625e-05 | 2697 | 14.4505 | 2541 | 0.00093807 | 0.071294 | 2650 | 0.03 | 2314
5142 | STANISLAUS 17021850 | 162821702 | STANISLAUS 1702 | 1850 | FALSE | 21661.1812 | 21661.1812 | 13.4625 | 182 | 0.00013942 | 879 | 5.1605 | 2745 | 0.00093342 | 0.16988 | 2651 | 73.2 | 62
7375 | ARCATA 11224218 | 192021122 | ARCATA 1122 | 4218 | FALSE | 7931.9123 | 7690.241 | 4.7795 | 27 | 0.00022706 | 297 | 5.3463 | 2735 | 0.00093079 | 0.025131 | 2652 | 0.09 | 1526
2956 | BIG BASIN 110276752 | 82841102 | BIG BASIN 1102 | 76752 | FALSE | 4380.3192 | 4380.3192 | 2.7224 | 36 | 0.00025263 | 209 | 5.3491 | 2733 | 0.00091318 | 0.032874 | 2653 | 0.44 | 924
3629 | BRUNSWICK 11051030 | 152481105 | BRUNSWICK 1105 | 1030 | FALSE | 25567.0003 | 25567.0003 | 15.89 | 217 | 0.00014916 | 749 | 5.1044 | 2748 | 0.00090994 | 0.19746 | 2654 | 21.6 | 300
9250 | MIWUK 17021808 | 163661702 | MIWUK 1702 | 1808 | FALSE | 2949.8139 | 2949.8139 | 1.8333 | 27 | 9.0273e-05 | 1905 | 7.9905 | 2670 | 0.00090929 | 0.024551 | 2655 | 46.07 | 145
8540 | DEL MONTE 210436720 | 182222104 | DEL MONTE 2104 | 36720 | FALSE | 12840.8619 | 9577.7665 | 5.9526 | 87 | 5.288e-05 | 2972 | 18.0958 | 2475 | 0.00089535 | 0.077895 | 2656 | 0.12 | 1394
950 | JARVIS 1108MR366 | 13501108 | JARVIS 1108 | MR366 | TRUE | 15876.8969 | 0 | 0 | 134 | 1.4916e-05 | 3586 | 46.6158 | 2237 | 0.00088159 | 0.11813 | 2657 |  | 2698
1888 | ROB ROY 2104CB | 83692104 | ROB ROY 2104 | CB | FALSE | 23033.3792 | 23033.3792 | 14.3153 | 170 | 0.00010514 | 1519 | 8.871 | 2646 | 0.0008744 | 0.14865 | 2658 | 0.65 | 822
311 | SALT SPRINGS 21023142 | 163692102 | SALT SPRINGS 2102 | 3142 | FALSE | 28901.7283 | 28901.7283 | 17.9625 | 256 | 8.7499e-05 | 1999 | 11.3039 | 2600 | 0.00086175 | 0.22061 | 2659 | 128.2 | 8
978 | BRYANT 0402CB | 13090402 | BRYANT 0402 | CB | FALSE | 12456.8292 | 3768.052 | 2.3419 | 111 | 9.7026e-05 | 1713 | 9.3336 | 2638 | 0.00085884 | 0.095332 | 2660 | 0.34 | 979
7054 | STANISLAUS 1702L3151 | 162821702 | STANISLAUS 1702 | L3151 | FALSE | 1595.4085 | 1595.4085 | 0.99155 | 13 | 0.0001267 | 1068 | 7.3809 | 2679 | 0.00085242 | 0.011082 | 2661 | 25 | 273
3980 | BIG BASIN 110112838 | 82841101 | BIG BASIN 1101 | 12838 | FALSE | 3807.4911 | 3807.4911 | 2.3664 | 32 | 0.00058408 | 21 | 1.5522 | 2860 | 0.00085046 | 0.027215 | 2662 | 8.72 | 421
8804 | SILVERADO 2103403102 | 43432103 | SILVERADO 2103 | 403102 | TRUE | 2765.6183 | 788.5735 | 0.4901 | 18 | 0.00014171 | 843 | 5.3389 | 2736 | 0.00084561 | 0.015221 | 2663 |  | 3267
6283 | HATTON 11022010 | 182291102 | HATTON 1102 | 2010 | FALSE | 6409.6213 | 6409.6213 | 3.9836 | 43 | 8.8563e-05 | 1970 | 8.3553 | 2660 | 0.00084365 | 0.036277 | 2664 | 0.11 | 1409
164 | CORONA 11034446 | 43491103 | CORONA 1103 | 4446 | TRUE | 17302.7635 | 0 | 0 | 124 | 4.9277e-05 | 3056 | 12.6776 | 2575 | 0.00084052 | 0.10422 | 2665 | 0.04 | 2135
5512 | MORAGA 1101669542 | 13801101 | MORAGA 1101 | 669542 | FALSE | 5668.7589 | 5668.7589 | 3.5232 | 49 | 0.00018473 | 476 | 4.4449 | 2769 | 0.0008334 | 0.040836 | 2666 |  | 2960
5671 | CURTIS 170190120 | 163351701 | CURTIS 1701 | 90120 | FALSE | 8309.1292 | 5041.5999 | 3.1334 | 64 | 0.00010439 | 1542 | 5.6342 | 2725 | 0.00082387 | 0.052727 | 2667 | 0.04 | 2200
5328 | OROSI 11027948F | 252841102 | OROSI 1102 | 7948F | FALSE | 13813.6905 | 1712.0139 | 1.064 | 74 | 2.7103e-05 | 3472 | 53.0836 | 2194 | 0.00082174 | 0.060809 | 2668 | 0.02 | 2432
3271 | STAFFORD 1101CB | 43201101 | STAFFORD 1101 | CB | FALSE | 19644.2096 | 2188.9817 | 1.3605 | 180 | 4.3869e-05 | 3192 | 3.8934 | 2779 | 0.0008192 | 0.14746 | 2669 | 0.05 | 1928
3349 | STANISLAUS 17026028 | 162821702 | STANISLAUS 1702 | 6028 | FALSE | 13370.3026 | 13370.3026 | 8.3097 | 115 | 0.00011502 | 1298 | 6.888 | 2688 | 0.0008147 | 0.09369 | 2670 | 56.37 | 98
4063 | REDBUD 1102432 | 43191102 | REDBUD 1102 | 432 | FALSE | 18069.9686 | 1802.3639 | 1.1202 | 130 | 5.4493e-05 | 2933 | 13.5928 | 2560 | 0.00080536 | 0.1047 | 2671 | 0.03 | 2402
4207 | SPRING GAP 170210720 | 162831702 | SPRING GAP 1702 | 10720 | FALSE | 7675.033 | 7675.033 | 4.7701 | 25 | 2.2157e-05 | 3517 | 32.3965 | 2326 | 0.00079114 | 0.019779 | 2672 | 23.43 | 287
6208 | BIG MEADOWS 2101CB | 102812101 | BIG MEADOWS 2101 | CB | FALSE | 3388.6184 | 3388.6184 | 2.106 | 21 | 6.388e-05 | 2651 | 12.5128 | 2578 | 0.00079069 | 0.016605 | 2673 | 0.04 | 2209
682 | ROSSMOOR 110676468 | 14161106 | ROSSMOOR 1106 | 76468 | FALSE | 4744.0085 | 1281.0776 | 0.79619 | 35 | 9.8202e-05 | 1686 | 6.3972 | 2700 | 0.00078905 | 0.027617 | 2674 | 0.03 | 2373
5936 | OAKLAND K 1102CB | 12101102 | OAKLAND K 1102 | CB | FALSE | 4816.3453 | 4816.3453 | 2.9934 | 40 | 0.00013401 | 943 | 11.9588 | 2585 | 0.0007688 | 0.030752 | 2675 | 31.2 | 232
5479 | ROSSMOOR 1108CB | 14161108 | ROSSMOOR 1108 | CB | FALSE | 11748.8949 | 6728.9489 | 4.1821 | 92 | 9.2886e-05 | 1826 | 6.3592 | 2703 | 0.00076238 | 0.070139 | 2676 | 0.16 | 1251
3739 | WEIMAR 1102CB | 152491102 | WEIMAR 1102 | CB | FALSE | 19605.5563 | 19605.5563 | 12.1849 | 151 | 0.00013907 | 885 | 11.5584 | 2596 | 0.00075189 | 0.11354 | 2677 | 0.07 | 1772
4477 | MIWUK 170238218 | 163661702 | MIWUK 1702 | 38218 | FALSE | 17605.0564 | 17605.0564 | 10.9416 | 132 | 9.9008e-05 | 1668 | 8.1704 | 2665 | 0.00074696 | 0.098599 | 2678 | 94.05 | 28
262 | ROB ROY 21055090 | 83692105 | ROB ROY 2105 | 5090 | FALSE | 34218.6566 | 34218.6566 | 21.267 | 245 | 0.00010692 | 1476 | 6.8561 | 2689 | 0.00074249 | 0.18191 | 2679 | 1.26 | 691
459 | HARTLEY 1102824 | 43211102 | HARTLEY 1102 | 824 | TRUE | 12575.4803 | 137.5107 | 0.085463 | 103 | 0.00010133 | 1619 | 3.4457 | 2797 | 0.00072721 | 0.074902 | 2680 |  | 2674
3196 | SPRING GAP 17029280 | 162831702 | SPRING GAP 1702 | 9280 | FALSE | 10262.6071 | 10262.6071 | 6.3783 | 80 | 8.3881e-05 | 2098 | 8.09 | 2668 | 0.00072124 | 0.057699 | 2681 | 2.82 | 577
1359 | CAMP EVERS 210311056 | 83622103 | CAMP EVERS 2103 | 11056 | FALSE | 6785.5939 | 6717.0632 | 4.1747 | 48 | 0.00016442 | 592 | 4.026 | 2778 | 0.00071991 | 0.034556 | 2682 | 0.3 | 1011
2485 | EEL RIVER 1102530 | 192381102 | EEL RIVER 1102 | 530 | TRUE | 43254.3781 | 117.5277 | 0.073044 | 255 | 0.00014869 | 756 | 5.1756 | 2744 | 0.00070447 | 0.17964 | 2683 | 0.02 | 2508
6651 | PINECREST 04011818 | 163160401 | PINECREST 0401 | 1818 | FALSE | 5027.483 | 4942.4923 | 3.0718 | 26 | 4.1e-05 | 3243 | 14.3865 | 2542 | 0.00069935 | 0.018183 | 2684 | 0.72 | 799
413 | BRUNSWICK 11062796 | 152481106 | BRUNSWICK 1106 | 2796 | FALSE | 31981.5846 | 31981.5846 | 19.8767 | 253 | 0.00012583 | 1081 | 6.8299 | 2691 | 0.00069507 | 0.17585 | 2685 | 44.5 | 159
4105 | CAMP EVERS 210410442 | 83622104 | CAMP EVERS 2104 | 10442 | FALSE | 16579.0287 | 9105.2092 | 5.6589 | 133 | 0.00016483 | 589 | 3.6401 | 2786 | 0.00069444 | 0.092361 | 2686 | 0.29 | 1027
2116 | LUCERNE 1106CB | 43351106 | LUCERNE 1106 | CB | FALSE | 5806.4035 | 3043.2971 | 1.8914 | 48 | 0.00014993 | 737 | 3.6937 | 2784 | 0.00069407 | 0.033315 | 2687 | 0.04 | 2177
10094 | HARRIS 1109237791 | 192431109 | HARRIS 1109 | 237791 | FALSE | 3420.2949 | 2280.4467 | 1.4173 | 23 | 0.0001987 | 399 | 3.165 | 2804 | 0.00069283 | 0.015935 | 2688 |  | 3489
9596 | BRUNSWICK 1104285704 | 152481104 | BRUNSWICK 1104 | 285704 | FALSE | 1923.7717 | 1685.8276 | 1.0477 | 17 | 0.00023236 | 275 | 9.8522 | 2626 | 0.00068515 | 0.011648 | 2689 |  | 3385
591 | MIWUK 170110600 | 163661701 | MIWUK 1701 | 10600 | FALSE | 21367.0688 | 21367.0688 | 13.2797 | 161 | 7.3663e-05 | 2371 | 8.335 | 2662 | 0.000683 | 0.10996 | 2690 | 276.94 | 1
7040 | PAUL SWEET 2106428102 | 83252106 | PAUL SWEET 2106 | 428102 | FALSE | 20879.8446 | 19729.9421 | 12.2622 | 158 | 0.00012781 | 1053 | 4.9782 | 2755 | 0.00068264 | 0.10786 | 2691 | 0.55 | 866
9535 | HOLLISTER 2105480430 | 182492105 | HOLLISTER 2105 | 480430 | FALSE | 8153.37 | 1450.1348 | 0.90126 | 39 | 5.7435e-05 | 2851 | 18.7653 | 2463 | 0.00068138 | 0.026574 | 2692 |  | 3372
751 | GUALALA 1112662 | 42841112 | GUALALA 1112 | 662 | FALSE | 13657.9642 | 10019.7655 | 6.2273 | 104 | 6.0639e-05 | 2758 | 8.9744 | 2644 | 0.00067921 | 0.070638 | 2693 | 0.07 | 1724
9192 | PURISIMA 110154728 | 182971101 | PURISIMA 1101 | 54728 | FALSE | 7898.4984 | 1667.872 | 1.0366 | 37 | 3.3775e-05 | 3371 | 43.321 | 2256 | 0.00066262 | 0.024517 | 2694 | 0.79 | 775
6603 | MIRABEL 11027347 | 42091102 | MIRABEL 1102 | 7347 | FALSE | 1315.3758 | 1315.3758 | 0.81751 | 10 | 0.00013644 | 913 | 4.8202 | 2760 | 0.00065864 | 0.0065864 | 2695 | 43.48 | 167
6890 | CHALLENGE 110113026 | 103201101 | CHALLENGE 1101 | 13026 | FALSE | 12912.9615 | 12912.9615 | 8.0255 | 70 | 4.9241e-05 | 3058 | 11.6076 | 2595 | 0.00065269 | 0.045688 | 2696 | 8.38 | 429
4651 | PACIFICA 1102320094 | 22811102 | PACIFICA 1102 | 320094 | TRUE | 1539.8883 | 440.0576 | 0.2735 | 11 | 3.4565e-05 | 3360 | 25.2958 | 2389 | 0.00064788 | 0.0071266 | 2697 |  | 2907
7773 | MONTE RIO 111215401 | 42811112 | MONTE RIO 1112 | 15401 | FALSE | 1388.1732 | 1388.1732 | 0.86276 | 11 | 0.00019479 | 418 | 6.5489 | 2694 | 0.00064146 | 0.0070561 | 2698 | 41.15 | 179
8375 | MONTE RIO 1111256 | 42811111 | MONTE RIO 1111 | 256 | FALSE | 2415.6319 | 2415.6319 | 1.5013 | 17 | 0.00023971 | 247 | 1.4646 | 2867 | 0.00063627 | 0.010817 | 2699 | 24.25 | 279
6923 | OLEMA 1101758594 | 42291101 | OLEMA 1101 | 758594 | FALSE | 3264.6914 | 1943.4938 | 1.2079 | 21 | 0.00012955 | 1018 | 6.1576 | 2711 | 0.00062774 | 0.013182 | 2700 |  | 3075
10215 | IGNACIO 11011779 | 42481101 | IGNACIO 1101 | 1779 | TRUE | 677.0293 | 540.9099 | 0.33618 | 5 | 6.6577e-05 | 2570 | 9.5735 | 2633 | 0.00062625 | 0.0031313 | 2701 |  | 3516
4571 | TEMPLETON 2113A30 | 183052113 | TEMPLETON 2113 | A30 | TRUE | 2568.419 | 401.1046 | 0.24929 | 25 | 5.8029e-05 | 2834 | 6.399 | 2699 | 0.00062089 | 0.015522 | 2702 | 0.02 | 2500
5501 | FORT BRAGG A 11013100 | 42761101 | FORT BRAGG A 1101 | 3100 | FALSE | 23694.1727 | 19636.3272 | 12.2041 | 198 | 6.4544e-05 | 2625 | 14.9697 | 2532 | 0.00061511 | 0.12179 | 2703 | 0.06 | 1863
7330 | HAMILTON BRANCH 110190334 | 102361101 | HAMILTON BRANCH 1101 | 90334 | FALSE | 5394.0455 | 5394.0455 | 3.3524 | 44 | 3.2303e-05 | 3396 | 20.5875 | 2442 | 0.00061497 | 0.027059 | 2704 | 11.09 | 388
3053 | HIGGINS 11032194 | 152691103 | HIGGINS 1103 | 2194 | FALSE | 4329.2096 | 2142.6429 | 1.3317 | 36 | 0.00018519 | 470 | 3.3664 | 2801 | 0.00060703 | 0.021853 | 2705 | 1.88 | 634
9597 | MORGAN HILL 2105XR602 | 83242105 | MORGAN HILL 2105 | XR602 | TRUE | 1368.2778 | 391.3667 | 0.24324 | 13 | 8.4195e-05 | 2086 | 9.8269 | 2627 | 0.00060529 | 0.0078688 | 2706 | 0.03 | 2240
5378 | DIAMOND SPRINGS 1105CB | 152261105 | DIAMOND SPRINGS 1105 | CB | FALSE | 7588.8389 | 3330.3293 | 2.0698 | 47 | 0.0003055 | 125 | 1.7499 | 2851 | 0.00059825 | 0.028118 | 2707 | 0.99 | 735
1437 | HORSESHOE 110450142 | 152571104 | HORSESHOE 1104 | 50142 | FALSE | 6580.4447 | 3596.2025 | 2.2351 | 55 | 0.00011566 | 1280 | 5.2494 | 2740 | 0.00059558 | 0.032757 | 2708 | 2.21 | 618
4026 | MIRABEL 1101CB | 42091101 | MIRABEL 1101 | CB | TRUE | 8192.7885 | 792.3448 | 0.49245 | 70 | 0.00016303 | 612 | 5.4892 | 2729 | 0.00059471 | 0.04163 | 2709 | 0.06 | 1815
7798 | LOS GATOS 110712041 | 82021107 | LOS GATOS 1107 | 12041 | FALSE | 10143.7851 | 10143.7851 | 6.3044 | 65 | 0.00013198 | 985 | 5.1866 | 2743 | 0.00059297 | 0.038543 | 2710 | 30.78 | 234
1553 | MEADOW LANE 2106C558R | 14302106 | MEADOW LANE 2106 | C558R | FALSE | 23093.6755 | 1942.5032 | 1.2073 | 180 | 4.7416e-05 | 3106 | 10.0864 | 2623 | 0.00059158 | 0.10648 | 2711 | 12.02 | 377
380 | STANISLAUS 17021804 | 162821702 | STANISLAUS 1702 | 1804 | FALSE | 13482.9013 | 13482.9013 | 8.3797 | 118 | 0.00010094 | 1626 | 6.3117 | 2706 | 0.00058985 | 0.069602 | 2712 | 106.77 | 17
10645 | DIAMOND SPRINGS 1103635040 | 152261103 | DIAMOND SPRINGS 1103 | 635040 | TRUE | 340.9559 | 324.181 | 0.20148 | 2 | 9.5316e-05 | 1752 | 11.9488 | 2590 | 0.0005888 | 0.0011776 | 2713 |  | 3585
7077 | CORONA 1103776806 | 43491103 | CORONA 1103 | 776806 | TRUE | 1634.4876 | 412.4097 | 0.25631 | 15 | 4.0998e-05 | 3244 | 13.7861 | 2555 | 0.00058477 | 0.0087716 | 2714 |  | 3094
4432 | BRUNSWICK 11053611 | 152481105 | BRUNSWICK 1105 | 3611 | FALSE | 2597.3823 | 2597.3823 | 1.6143 | 23 | 5.2349e-05 | 2984 | 11.435 | 2598 | 0.00057745 | 0.013281 | 2715 | 32.3 | 226
5741 | HICKS 2101XR250 | 83432101 | HICKS 2101 | XR250 | TRUE | 9406.4624 | 0 | 0 | 80 | 6.5499e-05 | 2601 | 5.0345 | 2750 | 0.00057262 | 0.04581 | 2716 | 4.1 | 527
8362 | CASTRO VALLEY 1111CB | 14091111 | CASTRO VALLEY 1111 | CB | TRUE | 1304.8232 | 357.3361 | 0.22209 | 16 | 7.3542e-05 | 2381 | 5.012 | 2752 | 0.00057058 | 0.0091293 | 2717 |  | 3215
4792 | HALF MOON BAY 1102CB | 24101102 | HALF MOON BAY 1102 | CB | TRUE | 5451.3154 | 266.9695 | 0.16592 | 50 | 3.1382e-05 | 3410 | 8.3028 | 2663 | 0.0005603 | 0.028015 | 2718 | 0.02 | 2459
2151 | MIWUK 170153038 | 163661701 | MIWUK 1701 | 53038 | FALSE | 10729.3555 | 10729.3555 | 6.6683 | 62 | 6.9809e-05 | 2481 | 8.8864 | 2645 | 0.00055181 | 0.034212 | 2719 | 0.63 | 833
5668 | ALLEGHANY 1101978 | 152101101 | ALLEGHANY 1101 | 978 | FALSE | 47571.501 | 22458.2021 | 13.9579 | 130 | 3.6377e-05 | 3326 | 24.8644 | 2391 | 0.00055148 | 0.071692 | 2720 | 0.07 | 1680
6116 | IGNACIO 1105908 | 42481105 | IGNACIO 1105 | 908 | FALSE | 3616.7994 | 1126.3756 | 0.70005 | 42 | 6.1442e-05 | 2737 | 3.4612 | 2796 | 0.00055062 | 0.023126 | 2721 |  | 3005
2452 | OAKHURST 1103719490 | 254421103 | OAKHURST 1103 | 719490 | FALSE | 4856.6254 | 4856.6254 | 3.0184 | 44 | 6.7665e-05 | 2542 | 6.5472 | 2695 | 0.00054847 | 0.024132 | 2722 |  | 2777
1532 | HAMILTON BRANCH 1101CB | 102361101 | HAMILTON BRANCH 1101 | CB | FALSE | 5887.1186 | 3755.8808 | 2.3343 | 56 | 5.471e-05 | 2926 | 5.5819 | 2728 | 0.00054657 | 0.030608 | 2723 | 0.07 | 1682
8732 | EL CERRITO G 1112418480 | 12501112 | EL CERRITO G 1112 | 418480 | FALSE | 1216.9885 | 1216.9885 | 0.75636 | 13 | 0.00010549 | 1506 | 5.5937 | 2726 | 0.0005464 | 0.0071032 | 2724 |  | 3256
4263 | HALF MOON BAY 11038894 | 24101103 | HALF MOON BAY 1103 | 8894 | FALSE | 18146.6988 | 18102.2842 | 11.2506 | 110 | 0.00011302 | 1343 | 4.8209 | 2759 | 0.00053494 | 0.058844 | 2725 | 5.41 | 487
4900 | CHESTER 11022564 | 103181102 | CHESTER 1102 | 2564 | FALSE | 3603.0114 | 3598.4394 | 2.2364 | 21 | 3.9721e-05 | 3274 | 12.5176 | 2577 | 0.00053291 | 0.011191 | 2726 | 0.1 | 1482
1003 | SANTA ROSA A 1111CB | 42151111 | SANTA ROSA A 1111 | CB | TRUE | 9060.4473 | 490.8425 | 0.30506 | 88 | 4.3627e-05 | 3197 | 6.3791 | 2701 | 0.00052634 | 0.046318 | 2727 |  | 2703
8503 | SAN RAFAEL 11071276 | 42011107 | SAN RAFAEL 1107 | 1276 | FALSE | 6144.8964 | 6012.4282 | 3.7367 | 56 | 0.00018947 | 444 | 3.4619 | 2795 | 0.00052522 | 0.029412 | 2728 | 0.53 | 884
6580 | MIWUK 170247143 | 163661702 | MIWUK 1702 | 47143 | FALSE | 7882.6346 | 7882.6346 | 4.8991 | 67 | 0.00016052 | 638 | 2.9032 | 2815 | 0.00052216 | 0.034985 | 2729 | 0.63 | 837
4101 | LAURELES 1112562376 | 182371112 | LAURELES 1112 | 562376 | FALSE | 12962.1789 | 12746.1039 | 7.9218 | 82 | 6.0914e-05 | 2752 | 14.0412 | 2548 | 0.00052151 | 0.042763 | 2730 |  | 2872
5934 | FITCH MOUNTAIN 1113154 | 42751113 | FITCH MOUNTAIN 1113 | 154 | TRUE | 15159.6857 | 20.5741 | 0.012787 | 108 | 0.00013977 | 871 | 1.0919 | 2887 | 0.00051973 | 0.056131 | 2731 | 0.03 | 2260
5473 | EL DORADO PH 2102CB | 152762102 | EL DORADO PH 2102 | CB | FALSE | 8918.2943 | 8918.2943 | 5.5428 | 46 | 0.00023568 | 259 | 2.1334 | 2835 | 0.00051722 | 0.023792 | 2732 | 44.97 | 153
4174 | CAMP EVERS 210610718 | 83622106 | CAMP EVERS 2106 | 10718 | FALSE | 13624.5702 | 13624.5702 | 8.4677 | 98 | 0.00029137 | 138 | 2.007 | 2842 | 0.0005122 | 0.050195 | 2733 | 0.58 | 858
4155 | BRUNSWICK 110532536 | 152481105 | BRUNSWICK 1105 | 32536 | FALSE | 17537.3204 | 17537.3204 | 10.8995 | 144 | 0.00010307 | 1568 | 6.8331 | 2690 | 0.00050182 | 0.072262 | 2734 | 126.24 | 9
4857 | SEACLIFF 040112946 | 83500401 | SEACLIFF 0401 | 12946 | FALSE | 5267.6978 | 3912.0696 | 2.4314 | 41 | 7.1582e-05 | 2431 | 5.8607 | 2717 | 0.00050028 | 0.020511 | 2735 | 0.3 | 1016
3888 | PUEBLO 1105716 | 43291105 | PUEBLO 1105 | 716 | TRUE | 14760.549 | 161.153 | 0.10016 | 124 | 5.8731e-05 | 2814 | 7.5935 | 2676 | 0.00049954 | 0.061943 | 2736 | 0.53 | 880
6409 | MIWUK 1702S2247 | 163661702 | MIWUK 1702 | S2247 | FALSE | 2394.0014 | 2394.0014 | 1.4879 | 21 | 7.5118e-05 | 2331 | 9.1225 | 2641 | 0.00049228 | 0.010338 | 2737 | 96.94 | 23
9855 | DUNLAP 1102778286 | 254061102 | DUNLAP 1102 | 778286 | FALSE | 4188.0047 | 4188.0047 | 2.6029 | 5 | 3.6444e-05 | 3323 | 19.0779 | 2461 | 0.0004909 | 0.0024545 | 2738 | 0 | 2637
9129 | ROSSMOOR 1102457174 | 14161102 | ROSSMOOR 1102 | 457174 | TRUE | 1940.6507 | 925.5451 | 0.57523 | 14 | 0.00011583 | 1277 | 1.7636 | 2850 | 0.00048348 | 0.0067687 | 2739 |  | 3313
8205 | ATASCADERO 1102825520 | 182541102 | ATASCADERO 1102 | 825520 | FALSE | 2407.6531 | 1896.9242 | 1.1789 | 21 | 4.6815e-05 | 3116 | 8.3859 | 2659 | 0.00047064 | 0.0098834 | 2740 |  | 3202
2233 | IGNACIO 11011264 | 42481101 | IGNACIO 1101 | 1264 | FALSE | 5420.1776 | 3078.9362 | 1.9136 | 50 | 5.6664e-05 | 2869 | 10.5255 | 2619 | 0.00046357 | 0.023178 | 2741 | 0.61 | 847
4702 | BURNEY 110145984 | 103311101 | BURNEY 1101 | 45984 | FALSE | 7772.9197 | 7772.9197 | 4.8309 | 68 | 5.7852e-05 | 2840 | 4.9585 | 2756 | 0.00046238 | 0.031442 | 2742 | 0.06 | 1809
911 | PEORIA 170590374 | 163781705 | PEORIA 1705 | 90374 | FALSE | 7135.3675 | 6578.4615 | 4.0885 | 48 | 9.4382e-05 | 1784 | 3.531 | 2791 | 0.0004592 | 0.022042 | 2743 | 0.06 | 1794
4097 | SILVERADO 2103CB | 43432103 | SILVERADO 2103 | CB | TRUE | 22820.5615 | 0 | 0 | 197 | 8.4141e-05 | 2089 | 3.1167 | 2806 | 0.00045724 | 0.090077 | 2744 | 43.8 | 164
5992 | MIWUK 17029270 | 163661702 | MIWUK 1702 | 9270 | FALSE | 9370.6933 | 9370.6933 | 5.8239 | 68 | 0.00011547 | 1288 | 6.0072 | 2714 | 0.00045602 | 0.03101 | 2745 | 40.93 | 182
9472 | LLAGAS 2105XR234 | 83182105 | LLAGAS 2105 | XR234 | TRUE | 1908.9722 | 4.1246 | 0.0025635 | 26 | 4.1932e-05 | 3226 | 7.3799 | 2680 | 0.00045563 | 0.011846 | 2746 | 0.03 | 2236
6378 | WOODACRE 11011238 | 43021101 | WOODACRE 1101 | 1238 | FALSE | 5923.8162 | 5923.8162 | 3.6817 | 30 | 0.00026272 | 189 | 9.5821 | 2630 | 0.0004533 | 0.013599 | 2747 | 62.35 | 85
1227 | MORAGA 110381146 | 13801103 | MORAGA 1103 | 81146 | FALSE | 9033.4152 | 1226.8593 | 0.7625 | 79 | 7.3782e-05 | 2366 | 10.282 | 2621 | 0.00045161 | 0.035677 | 2748 | 0.03 | 2350
2519 | CAMPHORA 110122412 | 182071101 | CAMPHORA 1101 | 22412 | FALSE | 24417.5389 | 3680.7169 | 2.2876 | 130 | 3.6957e-05 | 3316 | 12.5116 | 2579 | 0.0004496 | 0.058447 | 2749 |  | 2781
2793 | CAMP EVERS 21065302 | 83622106 | CAMP EVERS 2106 | 5302 | FALSE | 9546.4932 | 9546.4932 | 5.9332 | 57 | 0.00026232 | 191 | 2.1517 | 2833 | 0.00044854 | 0.025567 | 2750 | 1.02 | 727
5402 | PACIFICA 1101CB | 22811101 | PACIFICA 1101 | CB | TRUE | 4340.9857 | 216.2085 | 0.13437 | 38 | 4.6882e-05 | 3115 | 6.7721 | 2692 | 0.00044808 | 0.017027 | 2751 | 8.14 | 434
6879 | SEACLIFF 0401CB | 83500401 | SEACLIFF 0401 | CB | FALSE | 9677.833 | 9246.0032 | 5.7464 | 73 | 0.00012957 | 1017 | 4.2973 | 2773 | 0.00044728 | 0.032652 | 2752 | 0.53 | 879
5244 | DUNBAR 1103440 | 43071103 | DUNBAR 1103 | 440 | FALSE | 19525.153 | 3309.7658 | 2.057 | 158 | 8.4963e-05 | 2062 | 3.5276 | 2792 | 0.00044177 | 0.0698 | 2753 | 0.17 | 1237
4679 | ROB ROY 210412596 | 83692104 | ROB ROY 2104 | 12596 | FALSE | 17025.8657 | 12925.0786 | 8.033 | 140 | 8.8891e-05 | 1955 | 5.6622 | 2721 | 0.00043371 | 0.060719 | 2754 | 0.06 | 1804
4037 | EL DORADO PH 21019759 | 152762101 | EL DORADO PH 2101 | 9759 | FALSE | 4110.5786 | 4110.5786 | 2.5547 | 32 | 0.00015886 | 653 | 4.5245 | 2765 | 0.00043106 | 0.013794 | 2755 |  | 2867
909 | TULE POWER HOUSE 1101CB | 258591101 | TULE POWER HOUSE 1101 | CB | FALSE | 6570.8 | 6570.8 | 4.0838 | 11 | 6.9646e-05 | 2484 | 248.9538 | 1542 | 0.00042329 | 0.0046561 | 2756 | 0.02 | 2523
7552 | WEST POINT 1101L2219 | 163201101 | WEST POINT 1101 | L2219 | FALSE | 5447.1163 | 5447.1163 | 3.3854 | 41 | 7.2244e-05 | 2411 | 7.0237 | 2687 | 0.00042266 | 0.017329 | 2757 | 49.71 | 121
3464 | SERRAMONTE 110412705 | 22861104 | SERRAMONTE 1104 | 12705 | TRUE | 9361.8686 | 0 | 0 | 74 | 2.2116e-05 | 3518 | 9.0486 | 2643 | 0.00042265 | 0.031276 | 2758 |  | 2827
7216 | BIG RIVER 110169032 | 43081101 | BIG RIVER 1101 | 69032 | FALSE | 13655.5842 | 13655.5842 | 8.487 | 101 | 8.8998e-05 | 1949 | 4.7713 | 2762 | 0.00041877 | 0.042296 | 2759 | 0.08 | 1653
2590 | WOODSIDE 1104520832 | 24251104 | WOODSIDE 1104 | 520832 | FALSE | 12960.7664 | 9719.2853 | 6.0406 | 90 | 0.00014149 | 844 | 3.7624 | 2781 | 0.00040636 | 0.036573 | 2760 |  | 2787
8755 | HALF MOON BAY 1101903182 | 24101101 | HALF MOON BAY 1101 | 903182 | FALSE | 1770.3755 | 1052.7078 | 0.65426 | 15 | 5.4676e-05 | 2927 | 4.2832 | 2774 | 0.00040533 | 0.0060799 | 2761 |  | 3258
4732 | BIG RIVER 11011286 | 43081101 | BIG RIVER 1101 | 1286 | FALSE | 12241.8563 | 7682.9666 | 4.775 | 92 | 6.6713e-05 | 2563 | 5.3157 | 2739 | 0.00040112 | 0.036903 | 2762 | 0.07 | 1737
3369 | ORO FINO 110276008 | 103031102 | ORO FINO 1102 | 76008 | FALSE | 25670.8015 | 25670.8015 | 15.9545 | 170 | 9.3618e-05 | 1806 | 4.261 | 2775 | 0.000401 | 0.068169 | 2763 | 96.79 | 24
9255 | LAS GALLINAS A 1106228906 | 42991106 | LAS GALLINAS A 1106 | 228906 | TRUE | 2215.3527 | 988.5949 | 0.61442 | 21 | 3.9761e-05 | 3273 | 5.3472 | 2734 | 0.00039716 | 0.0083403 | 2764 |  | 3330
2888 | FOOTHILL 110299432 | 182951102 | FOOTHILL 1102 | 99432 | FALSE | 13966.781 | 2359.0159 | 1.4661 | 115 | 2.7226e-05 | 3470 | 10.878 | 2612 | 0.00039549 | 0.045481 | 2765 | 0.07 | 1745
7168 | STANISLAUS 17024905 | 162821702 | STANISLAUS 1702 | 4905 | FALSE | 3704.1382 | 3704.1382 | 2.3021 | 35 | 8.1261e-05 | 2174 | 6.1793 | 2710 | 0.00038885 | 0.01361 | 2766 | 65.75 | 75
4177 | LOS GATOS 110760092 | 82021107 | LOS GATOS 1107 | 60092 | FALSE | 15629.1336 | 15629.1336 | 9.7136 | 108 | 0.00019731 | 408 | 2.9279 | 2813 | 0.00038814 | 0.041919 | 2767 | 0.39 | 951
9726 | SALT SPRINGS 21028442 | 163692102 | SALT SPRINGS 2102 | 8442 | FALSE | 19428.9727 | 19428.9727 | 12.0752 | 50 | 6.3912e-05 | 2650 | 8.1497 | 2666 | 0.00038233 | 0.019117 | 2768 | 0.11 | 1438
1168 | SAN RAFAEL 11081210 | 42011108 | SAN RAFAEL 1108 | 1210 | FALSE | 8832.2253 | 5252.6146 | 3.2645 | 73 | 0.00023323 | 270 | 1.6941 | 2853 | 0.00038163 | 0.027859 | 2769 | 0.29 | 1025
9856 | PUEBLO 1105419634 | 43291105 | PUEBLO 1105 | 419634 | TRUE | 1981.0133 | 165.107 | 0.10261 | 14 | 7.8094e-05 | 2255 | 6.2924 | 2707 | 0.00037832 | 0.0052965 | 2770 |  | 3436
1493 | SAN RAMON 2107CB | 14232107 | SAN RAMON 2107 | CB | TRUE | 14648.5405 | 486.1753 | 0.30216 | 107 | 1.7992e-05 | 3560 | 4.7299 | 2764 | 0.00037788 | 0.040433 | 2771 | 0.25 | 1087
531 | SAN RAFAEL 1109418 | 42011109 | SAN RAFAEL 1109 | 418 | FALSE | 19645.0637 | 8262.136 | 5.135 | 130 | 5.7927e-05 | 2837 | 5.0022 | 2753 | 0.00037742 | 0.049065 | 2772 | 0.06 | 1897
10509 | PAUL SWEET 2102337544 | 83252102 | PAUL SWEET 2102 | 337544 | TRUE | 1419.0103 | 579.0642 | 0.35989 | 13 | 0.00011348 | 1333 | 3.7153 | 2783 | 0.00037689 | 0.0048996 | 2773 |  | 3561
910 | DUNLAP 11027050 | 254061102 | DUNLAP 1102 | 7050 | FALSE | 15143.783 | 15143.783 | 9.4119 | 67 | 3.0197e-05 | 3425 | 13.5475 | 2562 | 0.0003702 | 0.024804 | 2774 | 0 | 2642
3656 | HALF MOON BAY 11038089 | 24101103 | HALF MOON BAY 1103 | 8089 | FALSE | 4528.4761 | 4528.4761 | 2.8145 | 29 | 0.00010867 | 1432 | 3.3453 | 2802 | 0.00036614 | 0.010618 | 2775 | 4.59 | 513
6207 | CAMP EVERS 210584166 | 83622105 | CAMP EVERS 2105 | 84166 | FALSE | 13898.1694 | 13231.1785 | 8.2232 | 97 | 0.0002829 | 150 | 1.5368 | 2863 | 0.00036427 | 0.035334 | 2776 |  | 3013
6326 | OLEMA 11011252 | 42291101 | OLEMA 1101 | 1252 | FALSE | 6608.6355 | 6608.6355 | 4.1073 | 50 | 0.00013383 | 946 | 3.8677 | 2780 | 0.00036141 | 0.018071 | 2777 | 11.02 | 391
872 | FAIRVIEW 2207M501R | 13432207 | FAIRVIEW 2207 | M501R | FALSE | 7503.1067 | 4016.4433 | 2.4962 | 60 | 4.6793e-05 | 3118 | 3.6463 | 2785 | 0.00035751 | 0.021451 | 2778 | 0.03 | 2319
6151 | EDENVALE 2113CB | 82952113 | EDENVALE 2113 | CB | TRUE | 2357.516 | 24.568 | 0.015269 | 24 | 1.8797e-05 | 3556 | 2.0509 | 2838 | 0.00035038 | 0.0084091 | 2779 |  | 3009
6316 | BIG RIVER 11011052 | 43081101 | BIG RIVER 1101 | 1052 | FALSE | 6204.8696 | 5356.147 | 3.3289 | 49 | 5.6569e-05 | 2870 | 5.2348 | 2741 | 0.00034866 | 0.017084 | 2780 | 0.08 | 1629
4831 | ROB ROY 2105CB | 83692105 | ROB ROY 2105 | CB | FALSE | 2115.1186 | 1181.1241 | 0.73407 | 17 | 7.5667e-05 | 2317 | 2.8608 | 2817 | 0.00034683 | 0.0058961 | 2781 | 0.04 | 2077
5876 | OAKLAND X 1106CR020 | 12541106 | OAKLAND X 1106 | CR020 | FALSE | 3932.8974 | 3932.8974 | 2.4443 | 15 | 9.3739e-05 | 1801 | 4.8237 | 2758 | 0.00034485 | 0.0051727 | 2782 | 41.15 | 180
8254 | DOLAN ROAD 1101857972 | 182381101 | DOLAN ROAD 1101 | 857972 | FALSE | 2082.0425 | 1672.4824 | 1.0395 | 18 | 4.6793e-05 | 3119 | 6.2207 | 2708 | 0.00034064 | 0.0061316 | 2783 |  | 3208
7697 | PARADISE 1103143744 | 102831103 | PARADISE 1103 | 143744 | FALSE | 1706.1115 | 1706.1115 | 1.0604 | 13 | 0.00045932 | 45 | 1.8946 | 2847 | 0.00033981 | 0.0044176 | 2784 |  | 3153
4615 | PEORIA 170184318 | 163781701 | PEORIA 1701 | 84318 | FALSE | 16486.0902 | 16486.0902 | 10.2462 | 142 | 8.547e-05 | 2041 | 8.7666 | 2648 | 0.00033804 | 0.048002 | 2785 | 0.05 | 2065
8175 | WEST POINT 1101L1969 | 163201101 | WEST POINT 1101 | L1969 | FALSE | 1768.6139 | 1768.6139 | 1.0992 | 16 | 7.7816e-05 | 2267 | 7.4947 | 2677 | 0.00032448 | 0.0051917 | 2786 | 58.12 | 93
2671 | LOS GATOS 1101LB40 | 82021101 | LOS GATOS 1101 | LB40 | FALSE | 14924.9201 | 13714.1212 | 8.5234 | 131 | 7.571e-05 | 2314 | 4.7844 | 2761 | 0.00032354 | 0.042384 | 2787 | 0.15 | 1298
1669 | SPRING GAP 17029690 | 162831702 | SPRING GAP 1702 | 9690 | FALSE | 27916.5832 | 27916.5832 | 17.3503 | 185 | 4.7987e-05 | 3093 | 9.3188 | 2639 | 0.00031402 | 0.058094 | 2788 | 45.06 | 151
1740 | GUALALA 1111402866 | 42841111 | GUALALA 1111 | 402866 | FALSE | 2560.4032 | 2560.4032 | 1.5913 | 20 | 8.0485e-05 | 2192 | 2.4422 | 2826 | 0.0003137 | 0.0062739 | 2789 | 0.02 | 2566
6457 | ATASCADERO 1103CB | 182541103 | ATASCADERO 1103 | CB | TRUE | 2195.0052 | 304.3324 | 0.18914 | 18 | 7.9462e-05 | 2222 | 3.5853 | 2789 | 0.00031227 | 0.0056208 | 2790 | 1.29 | 688
4913 | SAN LUIS OBISPO 1108CB | 182631108 | SAN LUIS OBISPO 1108 | CB | TRUE | 7402.9758 | 10.2676 | 0.0063814 | 69 | 2.9198e-05 | 3436 | 37.685 | 2292 | 0.00031202 | 0.02153 | 2791 | 1.11 | 716
3199 | EL CERRITO G 1105BR160 | 12501105 | EL CERRITO G 1105 | BR160 | FALSE | 18386.4832 | 13394.711 | 8.3249 | 132 | 6.9198e-05 | 2499 | 3.3682 | 2800 | 0.00031068 | 0.04101 | 2792 | 0.24 | 1104
7182 | EEL RIVER 1102720639 | 192381102 | EEL RIVER 1102 | 720639 | FALSE | 5844.6694 | 2660.7876 | 1.6537 | 25 | 0.00018595 | 468 | 1.9664 | 2846 | 0.0003062 | 0.0076549 | 2793 |  | 3105
6389 | PERRY 1101W10 | 183071101 | PERRY 1101 | W10 | FALSE | 3001.7775 | 2354.9644 | 1.4636 | 29 | 3.4275e-05 | 3364 | 7.1616 | 2684 | 0.00030601 | 0.0088744 | 2794 | 0.04 | 2112
5102 | DEL MONTE 21049096 | 182222104 | DEL MONTE 2104 | 9096 | FALSE | 10649.9386 | 5304.2381 | 3.2966 | 78 | 3.3536e-05 | 3375 | 6.4596 | 2697 | 0.00030601 | 0.023869 | 2795 | 0.04 | 2102
483 | EL CERRITO G 1105CB | 12501105 | EL CERRITO G 1105 | CB | FALSE | 11982.8259 | 11982.8259 | 7.4474 | 97 | 5.9625e-05 | 2786 | 4.4752 | 2768 | 0.00030421 | 0.029509 | 2796 | 0.19 | 1186
8801 | WOODSIDE 1104420146 | 24251104 | WOODSIDE 1104 | 420146 | FALSE | 5058.5239 | 4389.3602 | 2.728 | 43 | 0.00013429 | 940 | 3.382 | 2799 | 0.00030412 | 0.013077 | 2797 |  | 3266
2740 | SUNOL 1101MR650 | 14241101 | SUNOL 1101 | MR650 | FALSE | 4320.1366 | 2086.6412 | 1.2969 | 30 | 3.1219e-05 | 3411 | 6.4702 | 2696 | 0.00029523 | 0.0088568 | 2798 | 0.07 | 1706
1558 | RINCON 1103472 | 43321103 | RINCON 1103 | 472 | FALSE | 7739.1551 | 4930.8208 | 3.0645 | 71 | 9.5789e-05 | 1733 | 2.7474 | 2818 | 0.00029462 | 0.020918 | 2799 | 0.08 | 1630
1849 | FORT BRAGG A 11044690 | 42761104 | FORT BRAGG A 1104 | 4690 | FALSE | 23028.3671 | 18710.8643 | 11.6289 | 161 | 8.9068e-05 | 1944 | 4.3458 | 2772 | 0.00029439 | 0.047396 | 2800 | 0.16 | 1260
1214 | ROB ROY 21055166 | 83692105 | ROB ROY 2105 | 5166 | FALSE | 8840.5786 | 8840.5786 | 5.4945 | 81 | 9.5629e-05 | 1737 | 3.5862 | 2788 | 0.00028991 | 0.023482 | 2801 | 31.21 | 231
6981 | HALF MOON BAY 110148868 | 24101101 | HALF MOON BAY 1101 | 48868 | TRUE | 3010.868 | 0 | 0 | 21 | 2.3959e-05 | 3505 | 3.0775 | 2810 | 0.00028316 | 0.0059463 | 2802 | 0.31 | 997
5899 | VOLTA 11011640 | 102541101 | VOLTA 1101 | 1640 | FALSE | 16804.166 | 16804.166 | 10.4439 | 59 | 7.8829e-05 | 2241 | 5.7047 | 2720 | 0.00028287 | 0.016689 | 2803 | 0.01 | 2569
7108 | RESERVATION ROAD 11023032 | 182731102 | RESERVATION ROAD 1102 | 3032 | FALSE | 15762.9704 | 5799.169 | 3.6042 | 84 | 2.4376e-05 | 3503 | 5.9133 | 2716 | 0.00028141 | 0.023638 | 2804 | 0.03 | 2349
5988 | SPRING GAP 1702693441 | 162831702 | SPRING GAP 1702 | 693441 | FALSE | 6859.835 | 6859.835 | 4.2634 | 59 | 4.9575e-05 | 3046 | 4.4985 | 2767 | 0.00027928 | 0.016478 | 2805 | 0.29 | 1029
5979 | BIG RIVER 11012183 | 43081101 | BIG RIVER 1101 | 2183 | FALSE | 4246.8638 | 4246.8638 | 2.6394 | 33 | 9.4677e-05 | 1774 | 4.3864 | 2771 | 0.00027436 | 0.009054 | 2806 | 0.05 | 2047
760 | BIG RIVER 1101952 | 43081101 | BIG RIVER 1101 | 952 | FALSE | 16341.5936 | 16341.5936 | 10.1564 | 130 | 0.00010228 | 1595 | 2.9907 | 2812 | 0.00027431 | 0.03566 | 2807 | 0.36 | 970
1378 | PARADISE 1105CB | 102831105 | PARADISE 1105 | CB | FALSE | 11616.1021 | 9822.6918 | 6.1048 | 86 | 0.0005458 | 25 | 1.1717 | 2883 | 0.00026897 | 0.023131 | 2808 | 19.78 | 308
4711 | RESEARCH 2102446423 | 14692102 | RESEARCH 2102 | 446423 | FALSE | 2345.7749 | 1135.402 | 0.70566 | 23 | 0.00012326 | 1131 | 2.131 | 2836 | 0.00026534 | 0.0061027 | 2809 |  | 2912
534 | STANISLAUS 170237278 | 162821702 | STANISLAUS 1702 | 37278 | FALSE | 10929.4406 | 10929.4406 | 6.7927 | 99 | 0.00011401 | 1321 | 2.7082 | 2820 | 0.00026318 | 0.026055 | 2810 | 62.81 | 82
956 | PAUL SWEET 2106CB | 83252106 | PAUL SWEET 2106 | CB | FALSE | 18604.4746 | 8502.7441 | 5.2845 | 115 | 8.1074e-05 | 2181 | 1.4421 | 2868 | 0.00025895 | 0.029779 | 2811 | 0.23 | 1110
832 | ROSSMOOR 110168920 | 14161101 | ROSSMOOR 1101 | 68920 | FALSE | 11754.4382 | 10341.5361 | 6.4273 | 91 | 9.0413e-05 | 1900 | 5.0244 | 2751 | 0.0002577 | 0.02345 | 2812 | 0.16 | 1274
5459 | PARADISE 1106CB | 102831106 | PARADISE 1106 | CB | FALSE | 7764.6762 | 7472.667 | 4.6443 | 53 | 0.0005799 | 22 | 0.9633 | 2896 | 0.0002457 | 0.013022 | 2813 | 38.98 | 191
8168 | SAUSALITO 1102410 | 42491102 | SAUSALITO 1102 | 410 | FALSE | 3634.5971 | 2502.9293 | 1.5556 | 28 | 2.4862e-05 | 3498 | 2.3255 | 2830 | 0.00024476 | 0.0068532 | 2814 | 0.06 | 1826
2941 | DIAMOND SPRINGS 1103CB | 152261103 | DIAMOND SPRINGS 1103 | CB | TRUE | 13992.2701 | 885.5612 | 0.55038 | 109 | 0.00021179 | 353 | 2.0247 | 2841 | 0.00024231 | 0.026412 | 2815 | 0.21 | 1152
5531 | MAPLE CREEK 1101CB | 192101101 | MAPLE CREEK 1101 | CB | FALSE | 19709.1046 | 14267.6715 | 8.8674 | 60 | 0.0002127 | 346 | 1.2563 | 2877 | 0.00023784 | 0.01427 | 2816 | 0.11 | 1433
6907 | BRUNSWICK 111063100 | 152481110 | BRUNSWICK 1110 | 63100 | FALSE | 6591.8886 | 6591.8886 | 4.0969 | 55 | 0.00023384 | 266 | 1.3628 | 2873 | 0.00023675 | 0.013021 | 2817 | 5.34 | 490
2877 | MONTE RIO 11111701 | 42811111 | MONTE RIO 1111 | 1701 | FALSE | 2248.9876 | 2248.9876 | 1.3978 | 18 | 9.908e-05 | 1666 | 2.7097 | 2819 | 0.00023556 | 0.0042401 | 2818 | 29.59 | 240
6347 | PACIFICA 11015001 | 22811101 | PACIFICA 1101 | 5001 | TRUE | 2742.1134 | 0 | 0 | 25 | 3.0913e-05 | 3419 | 4.514 | 2766 | 0.00023403 | 0.0058507 | 2819 | 6.31 | 469
1625 | SAN LUIS OBISPO 1105CB | 182631105 | SAN LUIS OBISPO 1105 | CB | TRUE | 5657.7233 | 67.4906 | 0.041946 | 43 | 3.1411e-05 | 3409 | 11.8961 | 2591 | 0.000232 | 0.0099759 | 2820 | 0.04 | 2072
5409 | SAN RAFAEL 1108CB | 42011108 | SAN RAFAEL 1108 | CB | FALSE | 13792.1671 | 9469.8097 | 5.8855 | 102 | 0.00017335 | 539 | 0.99807 | 2891 | 0.00023023 | 0.023483 | 2821 | 0.21 | 1141
8271 | ROSSMOOR 1107857172 | 14161107 | ROSSMOOR 1107 | 857172 | TRUE | 1843.2099 | 152.0386 | 0.094493 | 15 | 8.7874e-05 | 1986 | 3.2284 | 2803 | 0.00022992 | 0.0034488 | 2822 |  | 3212
10147 | WINDSOR 11035060 | 43501103 | WINDSOR 1103 | 5060 | TRUE | 1113.3002 | 291.5638 | 0.18121 | 12 | 7.5643e-05 | 2319 | 1.3951 | 2871 | 0.00022663 | 0.0027196 | 2823 |  | 3502
8566 | CORONA 1103114284 | 43491103 | CORONA 1103 | 114284 | TRUE | 893.7863 | 451.7326 | 0.28075 | 11 | 8.3715e-05 | 2102 | 4.3909 | 2770 | 0.00022547 | 0.0024802 | 2824 |  | 3236
849 | STANISLAUS 170237276 | 162821702 | STANISLAUS 1702 | 37276 | FALSE | 18746.4684 | 18746.4684 | 11.651 | 168 | 0.00010311 | 1567 | 2.0474 | 2839 | 0.00022047 | 0.037039 | 2825 | 88.82 | 33
3868 | HATTON 11012026 | 182291101 | HATTON 1101 | 2026 | FALSE | 16422.8166 | 8438.7955 | 5.2447 | 126 | 4.8317e-05 | 3086 | 5.725 | 2719 | 0.00021753 | 0.027409 | 2826 | 0.07 | 1690
427 | SAUSALITO 1101688590 | 42491101 | SAUSALITO 1101 | 688590 | FALSE | 3500.4301 | 1691.536 | 1.0513 | 32 | 4.9847e-05 | 3041 | 3.0358 | 2811 | 0.00021706 | 0.0069459 | 2827 |  | 2671
4476 | CALISTOGA 1102705 | 42711102 | CALISTOGA 1102 | 705 | TRUE | 2028.0775 | 622.3172 | 0.38677 | 20 | 0.00010699 | 1473 | 4.0264 | 2777 | 0.00021298 | 0.0042596 | 2828 |  | 2895
1205 | MIWUK 17028090 | 163661702 | MIWUK 1702 | 8090 | FALSE | 6501.5338 | 6501.5338 | 4.0407 | 53 | 0.00010162 | 1614 | 1.8606 | 2848 | 0.00021162 | 0.011216 | 2829 | 58.21 | 92
61 | CAMBRIA 1102W50 | 182771102 | CAMBRIA 1102 | W50 | TRUE | 5818.6322 | 997.9458 | 0.62023 | 40 | 1.4796e-05 | 3587 | 16.6866 | 2506 | 0.00021093 | 0.0084371 | 2830 | 0.03 | 2302
189 | BIG RIVER 110179628 | 43081101 | BIG RIVER 1101 | 79628 | FALSE | 23813.9358 | 23813.9358 | 14.8005 | 156 | 7.9122e-05 | 2230 | 2.6556 | 2822 | 0.00021051 | 0.032839 | 2831 | 0.17 | 1233
3166 | ALTO 11251226 | 42031125 | ALTO 1125 | 1226 | FALSE | 12605.0062 | 12282.9745 | 7.6339 | 96 | 0.00012073 | 1171 | 0.80895 | 2902 | 0.00020916 | 0.02008 | 2832 | 1.01 | 728
6809 | OAKLAND D 1112CR192 | 12041112 | OAKLAND D 1112 | CR192 | FALSE | 6810.4625 | 3963.0316 | 2.463 | 54 | 8.0733e-05 | 2188 | 1.3873 | 2872 | 0.00020828 | 0.011247 | 2833 | 0.21 | 1135
4374 | OCEANO 1103V22 | 182601103 | OCEANO 1103 | V22 | TRUE | 810.5999 | 50.4916 | 0.031381 | 14 | 2.0015e-05 | 3542 | 3.4621 | 2794 | 0.00020377 | 0.0028528 | 2834 |  | 2885
9957 | DEL MONTE 21043066 | 182222104 | DEL MONTE 2104 | 3066 | TRUE | 26.0345 | 26.0345 | 0.016181 | 2 | 5.3309e-05 | 2953 | 11.9582 | 2586 | 0.00020359 | 0.00040718 | 2835 | 0.44 | 922
4818 | ROSSMOOR 11018132 | 14161101 | ROSSMOOR 1101 | 8132 | FALSE | 5814.9582 | 4248.014 | 2.6402 | 47 | 9.8938e-05 | 1671 | 2.0883 | 2837 | 0.00020337 | 0.0095582 | 2836 | 0.04 | 2079
2856 | SAN RAFAEL 11071166 | 42011107 | SAN RAFAEL 1107 | 1166 | FALSE | 24234.157 | 20163.1012 | 12.5314 | 213 | 0.00022306 | 307 | 0.8473 | 2900 | 0.00020294 | 0.043227 | 2837 | 1.46 | 673
445 | MONTE RIO 1112CB | 42811112 | MONTE RIO 1112 | CB | FALSE | 5679.6302 | 5679.6302 | 3.5299 | 43 | 0.00015288 | 721 | 0.6192 | 2911 | 0.00020121 | 0.0086519 | 2838 | 23.03 | 289
10280 | SAUSALITO 1102964592 | 42491102 | SAUSALITO 1102 | 964592 | TRUE | 1787.6075 | 941.9387 | 0.58542 | 15 | 2.9092e-05 | 3439 | 9.5689 | 2634 | 0.00019824 | 0.0029736 | 2839 |  | 3528
1145 | OLEMA 11011200 | 42291101 | OLEMA 1101 | 1200 | FALSE | 4658.8808 | 4658.8808 | 2.8955 | 34 | 8.1804e-05 | 2158 | 2.8623 | 2816 | 0.00019566 | 0.0066525 | 2840 | 4.42 | 520
6437 | HAMILTON BRANCH 110153192 | 102361101 | HAMILTON BRANCH 1101 | 53192 | TRUE | 3316.9892 | 889.758 | 0.55299 | 30 | 5.4105e-05 | 2941 | 5.3377 | 2737 | 0.0001937 | 0.0058109 | 2841 |  | 3032
7381 | PACIFICA 1102660408 | 22811102 | PACIFICA 1102 | 660408 | TRUE | 3217.4282 | 570.687 | 0.35468 | 26 | 3.0978e-05 | 3417 | 7.378 | 2681 | 0.00019086 | 0.0049624 | 2842 |  | 3121
5360 | ALHAMBRA 1105CB | 14101105 | ALHAMBRA 1105 | CB | FALSE | 3053.2387 | 1333.5262 | 0.82879 | 33 | 7.2893e-05 | 2396 | 1.9862 | 2843 | 0.00018865 | 0.0062254 | 2843 | 0.02 | 2444
1909 | MORAGA 1104750618 | 13801104 | MORAGA 1104 | 750618 | FALSE | 1583.7149 | 1538.3917 | 0.95612 | 13 | 5.3287e-05 | 2955 | 3.1105 | 2807 | 0.0001837 | 0.002388 | 2844 |  | 2755
7663 | SOBRANTE 1103CB | 14671103 | SOBRANTE 1103 | CB | FALSE | 6937.627 | 6745.77 | 4.1925 | 55 | 9.8691e-05 | 1677 | 3.0905 | 2808 | 0.00018024 | 0.0099135 | 2845 | 0.1 | 1500
4846 | ORINDA 0402402/2 LR | 12350402 | ORINDA 0402 | 402/2 LR | FALSE | 10638.2509 | 10545.4353 | 6.554 | 91 | 0.00012174 | 1151 | 1.633 | 2857 | 0.00017917 | 0.016305 | 2846 |  | 2922
6268 | CURTIS 1702S2123 | 163351702 | CURTIS 1702 | S2123 | FALSE | 2988.9855 | 2988.9855 | 1.8577 | 25 | 0.00012986 | 1010 | 1.9671 | 2845 | 0.00017177 | 0.0042941 | 2847 |  | 3018
1067 | DIAMOND SPRINGS 1106290705 | 152261106 | DIAMOND SPRINGS 1106 | 290705 | FALSE | 5314.0636 | 5193.0778 | 3.2275 | 38 | 0.0001966 | 410 | 2.568 | 2823 | 0.00016712 | 0.0063506 | 2848 |  | 2706
3874 | PARADISE 1105829194 | 102831105 | PARADISE 1105 | 829194 | FALSE | 18124.3826 | 18124.3826 | 11.2644 | 142 | 0.00022979 | 286 | 0.40121 | 2916 | 0.00016422 | 0.023319 | 2849 |  | 2858
1686 | CAMP EVERS 210312990 | 83622103 | CAMP EVERS 2103 | 12990 | FALSE | 21277.9249 | 21277.9249 | 13.2243 | 161 | 0.00018796 | 455 | 1.0994 | 2886 | 0.00016127 | 0.025964 | 2850 | 0.86 | 764
6595 | HIGGINS 110432747 | 152691104 | HIGGINS 1104 | 32747 | FALSE | 2820.8108 | 1047.4929 | 0.65102 | 26 | 0.00014649 | 780 | 1.2825 | 2876 | 0.00016086 | 0.0041824 | 2851 | 1.65 | 658
2910 | HALSEY 110176178 | 152241101 | HALSEY 1101 | 76178 | FALSE | 32532.3048 | 32532.3048 | 20.219 | 248 | 0.00012177 | 1150 | 3.133 | 2805 | 0.00015934 | 0.039517 | 2852 | 0.13 | 1361
2602 | PRUNEDALE 11103716 | 182961110 | PRUNEDALE 1110 | 3716 | TRUE | 21171.7372 | 690.7324 | 0.42929 | 157 | 6.4877e-05 | 2613 | 1.6769 | 2855 | 0.00015488 | 0.024316 | 2853 | 0.03 | 2321
6371 | BAY MEADOWS 210257886 | 24012102 | BAY MEADOWS 2102 | 57886 | FALSE | 8466.0843 | 6549.4745 | 4.0705 | 81 | 8.2619e-05 | 2138 | 0.94597 | 2899 | 0.00015101 | 0.012232 | 2854 | 0.08 | 1619
3718 | TEMPLETON 2108A40 | 183052108 | TEMPLETON 2108 | A40 | FALSE | 20639.8903 | 6084.3101 | 3.7814 | 174 | 4.3444e-05 | 3202 | 1.431 | 2870 | 0.00015079 | 0.026237 | 2855 | 0.03 | 2254
8208 | BRUNSWICK 11038918 | 152481103 | BRUNSWICK 1103 | 8918 | FALSE | 3457.885 | 2431.0442 | 1.5109 | 30 | 0.00022692 | 298 | 2.4426 | 2824 | 0.0001494 | 0.0044819 | 2856 | 2.79 | 579
833 | BRUNSWICK 110456468 | 152481104 | BRUNSWICK 1104 | 56468 | FALSE | 9625.3334 | 8910.5893 | 5.538 | 85 | 0.00022965 | 287 | 1.0912 | 2888 | 0.0001483 | 0.012606 | 2857 | 12.55 | 373
8651 | MORGAN HILL 2111419718 | 83242111 | MORGAN HILL 2111 | 419718 | FALSE | 3649.8042 | 3649.8042 | 2.2684 | 25 | 0.00013422 | 941 | 1.0173 | 2890 | 0.0001469 | 0.0036725 | 2858 |  | 3248
4060 | KONOCTI 11081278 | 43311108 | KONOCTI 1108 | 1278 | FALSE | 12855.1379 | 9099.8598 | 5.6556 | 96 | 9.744e-05 | 1703 | 1.5519 | 2861 | 0.00014529 | 0.013948 | 2859 | 0.05 | 1918
5993 | LAS GALLINAS A 11041220 | 42991104 | LAS GALLINAS A 1104 | 1220 | TRUE | 7829.4679 | 0 | 0 | 57 | 2.5969e-05 | 3488 | 1.1753 | 2882 | 0.00013353 | 0.0076113 | 2860 | 0.03 | 2239
1481 | SOBRANTE 1101CB | 14671101 | SOBRANTE 1101 | CB | FALSE | 24857.1517 | 22896.4557 | 14.2302 | 209 | 9.1121e-05 | 1876 | 1.2034 | 2878 | 0.00012965 | 0.027098 | 2861 | 0.08 | 1613
6330 | CURTIS 170268380 | 163351702 | CURTIS 1702 | 68380 | FALSE | 10711.9675 | 10711.9675 | 6.6575 | 88 | 0.00012793 | 1048 | 2.2263 | 2832 | 0.00012865 | 0.011322 | 2862 | 0.74 | 791
2410 | SAN LEANDRO U 1114MR544 | 13111114 | SAN LEANDRO U 1114 | MR544 | TRUE | 7120.8066 | 27.9821 | 0.017391 | 62 | 9.0189e-06 | 3615 | 1.9811 | 2844 | 0.00012274 | 0.0076101 | 2863 | 0.04 | 2154
5853 | ROB ROY 210410954 | 83692104 | ROB ROY 2104 | 10954 | FALSE | 11428.7483 | 11428.7483 | 7.103 | 90 | 9.1892e-05 | 1847 | 2.4422 | 2825 | 0.00012262 | 0.011036 | 2864 | 0.16 | 1268
4344 | NOVATO 11041282 | 42211104 | NOVATO 1104 | 1282 | TRUE | 5984.1771 | 0 | 0 | 56 | 9.973e-05 | 1654 | 1.1951 | 2881 | 0.00012029 | 0.0067363 | 2865 | 0.03 | 2326
8432 | SNEATH LANE 110715341 | 22721107 | SNEATH LANE 1107 | 15341 | TRUE | 2075.9695 | 391.2765 | 0.24318 | 18 | 3.4322e-05 | 3363 | 5.3372 | 2738 | 0.00011859 | 0.0021346 | 2866 | 0.74 | 792
6986 | RESERVATION ROAD 1102303870 | 182731102 | RESERVATION ROAD 1102 | 303870 | FALSE | 1292.4248 | 1028.4638 | 0.63919 | 7 | 5.3155e-05 | 2962 | 2.3249 | 2831 | 0.0001185 | 0.00082948 | 2867 |  | 3080
4626 | COTATI 1104426 | 42271104 | COTATI 1104 | 426 | FALSE | 6243.6329 | 3219.5011 | 2.0009 | 52 | 5.7367e-05 | 2854 | 1.7424 | 2852 | 0.00011662 | 0.0060642 | 2868 | 0.04 | 2194
8778 | PAUL SWEET 2107774760 | 83252107 | PAUL SWEET 2107 | 774760 | FALSE | 5348.863 | 5348.863 | 3.3243 | 37 | 0.00022083 | 317 | 0.70854 | 2908 | 0.00011197 | 0.0041429 | 2869 |  | 3263
4484 | FROGTOWN 170274648 | 163451702 | FROGTOWN 1702 | 74648 | TRUE | 7581.2034 | 262.1986 | 0.16296 | 63 | 8.4795e-05 | 2069 | 1.0707 | 2889 | 0.00011106 | 0.0069966 | 2870 | 0.42 | 932
6192 | PEORIA 170169124 | 163781701 | PEORIA 1701 | 69124 | FALSE | 4347.2792 | 4347.2792 | 2.7019 | 33 | 8.5315e-05 | 2047 | 1.5063 | 2864 | 0.00010917 | 0.0036026 | 2871 | 0.05 | 2055
8000 | DIAMOND SPRINGS 1107116815 | 152261107 | DIAMOND SPRINGS 1107 | 116815 | FALSE | 4074.4873 | 2540.2857 | 1.5788 | 33 | 0.00019069 | 440 | 1.5062 | 2865 | 0.00010723 | 0.0035385 | 2872 |  | 3182
8610 | HOOPA 110193038 | 192401101 | HOOPA 1101 | 93038 | FALSE | 4552.6155 | 2107.4343 | 1.3098 | 39 | 0.00019968 | 398 | 1.284 | 2875 | 0.00010645 | 0.0041517 | 2873 | 0.03 | 2241
995 | HALF MOON BAY 11022032 | 24101102 | HALF MOON BAY 1102 | 2032 | TRUE | 14427.8487 | 905.5345 | 0.56279 | 103 | 2.5379e-05 | 3492 | 0.98818 | 2894 | 0.0001063 | 0.010949 | 2874 | 0.14 | 1323
7250 | ORINDA 04013442 | 12350401 | ORINDA 0401 | 3442 | FALSE | 8430.8944 | 5599.863 | 3.4803 | 68 | 0.00011662 | 1257 | 0.7637 | 2904 | 0.00010618 | 0.0072205 | 2875 | 0.07 | 1685
367 | ARCATA 112233060 | 192021122 | ARCATA 1122 | 33060 | TRUE | 7941.0149 | 856.2789 | 0.53218 | 64 | 0.00022712 | 296 | 0.31239 | 2924 | 9.9531e-05 | 0.00637 | 2876 | 0.02 | 2560
2545 | FAIRVIEW 2207P148 | 13432207 | FAIRVIEW 2207 | P148 | FALSE | 7362.5215 | 1361.9079 | 0.84643 | 54 | 4.5868e-05 | 3143 | 1.5547 | 2859 | 9.8792e-05 | 0.0053348 | 2877 |  | 2783
5688 | STANISLAUS 170275348 | 162821702 | STANISLAUS 1702 | 75348 | FALSE | 8532.4043 | 8532.4043 | 5.3029 | 77 | 8.3581e-05 | 2110 | 1.3013 | 2874 | 9.5481e-05 | 0.0073521 | 2878 | 79.37 | 49
5946 | SALT SPRINGS 21011232 | 163692101 | SALT SPRINGS 2101 | 1232 | FALSE | 14610.263 | 12420.8061 | 7.7196 | 64 | 4.2772e-05 | 3212 | 1.5493 | 2862 | 9.0864e-05 | 0.0058153 | 2879 | 0.05 | 2007
4735 | ELK 11018779 | 42981101 | ELK 1101 | 8779 | FALSE | 6865.4129 | 6865.4129 | 4.2669 | 41 | 0.00012002 | 1187 | 1.8049 | 2849 | 8.9792e-05 | 0.0036815 | 2880 | 0.05 | 2060
744 | GABILAN 11013034 | 182331101 | GABILAN 1101 | 3034 | TRUE | 31905.8871 | 80.3377 | 0.04993 | 193 | 4.5789e-05 | 3145 | 2.3733 | 2828 | 8.716e-05 | 0.016822 | 2881 | 0.02 | 2481
8975 | SPRING GAP 170286032 | 162831702 | SPRING GAP 1702 | 86032 | FALSE | 4656.0497 | 1615.684 | 1.0042 | 23 | 2.8164e-05 | 3455 | 3.5085 | 2793 | 8.538e-05 | 0.0019637 | 2882 | 0.82 | 770
6252 | CHESTER 1101922138 | 103181101 | CHESTER 1101 | 922138 | FALSE | 3566.848 | 2524.6386 | 1.5691 | 24 | 4.9756e-05 | 3043 | 2.046 | 2840 | 8.4169e-05 | 0.00202 | 2883 |  | 3016
320 | GREEN VALLEY 210112106 | 83192101 | GREEN VALLEY 2101 | 12106 | TRUE | 19539.3367 | 556.8348 | 0.34608 | 139 | 8.3645e-05 | 2105 | 0.75016 | 2905 | 8.0919e-05 | 0.011248 | 2884 | 0.06 | 1840
390 | PETALUMA C 110856774 | 42631108 | PETALUMA C 1108 | 56774 | TRUE | 4425.2807 | 385.0871 | 0.23933 | 39 | 1.6584e-05 | 3572 | 2.9096 | 2814 | 7.8722e-05 | 0.0030702 | 2885 |  | 2668
3580 | SOBRANTE 1102CB | 14671102 | SOBRANTE 1102 | CB | FALSE | 16799.2868 | 16799.2868 | 10.4408 | 132 | 9.6671e-05 | 1719 | 1.6868 | 2854 | 7.4597e-05 | 0.0098468 | 2886 | 0.13 | 1339
5433 | HATTON 110137088 | 182291101 | HATTON 1101 | 37088 | FALSE | 18269.9988 | 11434.4875 | 7.1066 | 135 | 4.8424e-05 | 3080 | 2.354 | 2829 | 7.338e-05 | 0.0099063 | 2887 | 0.04 | 2198
2226 | FORT BRAGG A 11021226 | 42761102 | FORT BRAGG A 1102 | 1226 | FALSE | 12686.9371 | 2717.7424 | 1.6891 | 102 | 7.3175e-05 | 2391 | 0.9972 | 2892 | 7.0366e-05 | 0.0071773 | 2888 | 0.01 | 2602
7611 | DIAMOND SPRINGS 1106279670 | 152261106 | DIAMOND SPRINGS 1106 | 279670 | FALSE | 7840.1687 | 6244.093 | 3.8807 | 54 | 9.3625e-05 | 1805 | 0.35903 | 2923 | 7.0093e-05 | 0.003785 | 2889 |  | 3141
9967 | CRESTA 1101103126 | 102251101 | CRESTA 1101 | 103126 | TRUE | 487.0335 | 487.0335 | 0.30269 | 5 | 0.0010399 | 1 | 0.066432 | 2993 | 6.9083e-05 | 0.00034541 | 2890 |  | 3462
6701 | BRUNSWICK 11064639 | 152481106 | BRUNSWICK 1106 | 4639 | FALSE | 5228.1955 | 5228.1955 | 3.2493 | 44 | 0.00013355 | 950 | 1.1467 | 2885 | 6.7888e-05 | 0.0029871 | 2891 | 1.36 | 680
8130 | LAURELES 111110141 | 182371111 | LAURELES 1111 | 10141 | FALSE | 4694.7775 | 4694.7775 | 2.9178 | 21 | 5.6214e-05 | 2882 | 1.1979 | 2879 | 6.784e-05 | 0.0014246 | 2892 | 4.61 | 512
17 | SAN RAFAEL 1106910 | 42011106 | SAN RAFAEL 1106 | 910 | FALSE | 11465.6942 | 2722.6312 | 1.6921 | 89 | 0.00012024 | 1182 | 0.77728 | 2903 | 6.6955e-05 | 0.005959 | 2893 | 0.04 | 2206
428 | SOBRANTE 1102690098 | 14671102 | SOBRANTE 1102 | 690098 | FALSE | 12079.1397 | 11883.9636 | 7.3859 | 108 | 8.8852e-05 | 1957 | 0.94645 | 2898 | 6.6684e-05 | 0.0072019 | 2894 |  | 2672
6532 | PARADISE 110536656 | 102831105 | PARADISE 1105 | 36656 | TRUE | 1041.7398 | 220.7989 | 0.13723 | 14 | 0.00098372 | 2 | 0.065517 | 3361 | 6.4706e-05 | 0.00090588 | 2895 |  | 3040
1066 | JARVIS 1101MR210 | 13501101 | JARVIS 1101 | MR210 | FALSE | 12199.0798 | 1314.2646 | 0.81682 | 103 | 2.3777e-05 | 3506 | 0.99149 | 2893 | 6.2939e-05 | 0.0064828 | 2896 | 1.94 | 629
5877 | OAKLAND K 1102CR014 | 12101102 | OAKLAND K 1102 | CR014 | FALSE | 16905.8619 | 16905.8619 | 10.5071 | 137 | 0.00013845 | 889 | 0.41497 | 2915 | 6.2366e-05 | 0.0085442 | 2897 | 0.99 | 734
7339 | BIG BASIN 110165444 | 82841101 | BIG BASIN 1101 | 65444 | TRUE | 757.2593 | 757.2593 | 0.47064 | 9 | 0.00091179 | 3 | 0.066431 | 3074 | 6.0572e-05 | 0.00054514 | 2898 | 12.01 | 379
1476 | BOLINAS 1101528 | 42261101 | BOLINAS 1101 | 528 | FALSE | 4980.15 | 2865.7848 | 1.7811 | 46 | 4.0677e-05 | 3254 | 1.441 | 2869 | 5.4065e-05 | 0.002487 | 2899 | 0.21 | 1140
9601 | CAMP EVERS 2104189010 | 83622104 | CAMP EVERS 2104 | 189010 | TRUE | 84.167 | 59.0426 | 0.036695 | 4 | 0.000791 | 5 | 0.065792 | 3268 | 5.2348e-05 | 0.00020939 | 2900 |  | 3386
4401 | SILVERADO 2103507513 | 43432103 | SILVERADO 2103 | 507513 | FALSE | 8339.9553 | 4803.4 | 2.9853 | 65 | 0.00010329 | 1564 | 1.1629 | 2884 | 4.9269e-05 | 0.0032025 | 2901 |  | 2887
625 | ROSSMOOR 1101L503R | 14161101 | ROSSMOOR 1101 | L503R | FALSE | 6910.8038 | 6910.8038 | 4.2951 | 62 | 0.00010589 | 1498 | 0.83292 | 2901 | 4.8731e-05 | 0.0030213 | 2902 | 0.09 | 1547
7021 | DOLAN ROAD 1101590402 | 182381101 | DOLAN ROAD 1101 | 590402 | FALSE | 9614.0154 | 3916.034 | 2.4338 | 78 | 5.9195e-05 | 2800 | 0.67392 | 2910 | 4.8446e-05 | 0.0037788 | 2903 |  | 3086
7515 | PARADISE 1103468200 | 102831103 | PARADISE 1103 | 468200 | TRUE | 531.6801 | 531.6801 | 0.33044 | 4 | 0.00072422 | 6 | 0.066431 | 3033 | 4.8111e-05 | 0.00019244 | 2904 |  | 3132
8899 | NAPA 11025039 | 42021102 | NAPA 1102 | 5039 | TRUE | 4245.0462 | 0 | 0 | 28 | 7.2354e-05 | 2407 | 1.1951 | 2880 | 4.5334e-05 | 0.0012694 | 2905 |  | 3275
10522 | PARADISE 11042486 | 102831104 | PARADISE 1104 | 2486 | TRUE | 189.7916 | 146.4228 | 0.091002 | 2 | 0.00067148 | 8 | 0.065791 | 3270 | 4.4268e-05 | 8.8537e-05 | 2906 |  | 3565
11006 | PARADISE 1105828400 | 102831105 | PARADISE 1105 | 828400 | TRUE | 50.1094 | 50.1094 | 0.031143 | 2 | 0.00066466 | 9 | 0.066431 | 3040 | 4.4154e-05 | 8.8308e-05 | 2907 |  | 3627
10495 | CEDAR CREEK 11011362 | 103321101 | CEDAR CREEK 1101 | 1362 | TRUE | 24.9514 | 24.9514 | 0.015507 | 1 | 0.00065973 | 10 | 0.066431 | 3035 | 4.3827e-05 | 4.3827e-05 | 2908 | 0.04 | 2068
4622 | EL CERRITO G 1105BR194 | 12501105 | EL CERRITO G 1105 | BR194 | FALSE | 8491.9295 | 6148.6965 | 3.8214 | 74 | 6.6442e-05 | 2577 | 0.38709 | 2919 | 4.3185e-05 | 0.0031957 | 2909 | 0.12 | 1386
7319 | PARADISE 11061212 | 102831106 | PARADISE 1106 | 1212 | FALSE | 3248.6095 | 3232.6075 | 2.0091 | 33 | 0.00064007 | 12 | 0.066393 | 3123 | 4.2503e-05 | 0.0014026 | 2910 |  | 3117
10489 | CAMP EVERS 210510996 | 83622105 | CAMP EVERS 2105 | 10996 | FALSE | 1226.2093 | 1226.2093 | 0.76209 | 8 | 0.00063772 | 13 | 0.066431 | 3070 | 4.2365e-05 | 0.00033892 | 2911 | 3.1 | 562
7716 | PARADISE 110599226 | 102831105 | PARADISE 1105 | 99226 | FALSE | 5537.6206 | 1841.8715 | 1.1447 | 42 | 0.00062786 | 15 | 0.065639 | 3326 | 4.1187e-05 | 0.0017299 | 2912 |  | 3154
6446 | FORT BRAGG A 1102956 | 42761102 | FORT BRAGG A 1102 | 956 | FALSE | 19682.0883 | 18278.7267 | 11.3603 | 145 | 8.7665e-05 | 1994 | 0.39404 | 2918 | 4.0908e-05 | 0.0059316 | 2913 | 0.15 | 1277
2257 | BIG TREES 04025300 | 83050402 | BIG TREES 0402 | 5300 | FALSE | 15760.3239 | 15760.3239 | 9.7951 | 115 | 0.00020513 | 380 | 0.27315 | 2925 | 3.9714e-05 | 0.0045672 | 2914 |  | 2767
9775 | CAMP EVERS 210595050 | 83622105 | CAMP EVERS 2105 | 95050 | TRUE | 223.2117 | 223.2117 | 0.13873 | 5 | 0.00059508 | 17 | 0.066431 | 3081 | 3.9532e-05 | 0.00019766 | 2915 | 0.24 | 1092
2020 | DUNLAP 11037170 | 254061103 | DUNLAP 1103 | 7170 | FALSE | 8726.7127 | 8726.7127 | 5.4237 | 54 | 2.872e-05 | 3442 | 2.7066 | 2821 | 3.9493e-05 | 0.0021326 | 2916 | 0 | 2648
9147 | BEN LOMOND 04015400 | 83040401 | BEN LOMOND 0401 | 5400 | TRUE | 731.4241 | 731.4241 | 0.45458 | 4 | 0.00059378 | 18 | 0.066431 | 3083 | 3.9445e-05 | 0.00015778 | 2917 | 0.27 | 1057
2924 | ROB ROY 210538430 | 83692105 | ROB ROY 2105 | 38430 | FALSE | 10237.4777 | 6060.3575 | 3.7665 | 90 | 5.3215e-05 | 2959 | 0.59378 | 2912 | 3.7768e-05 | 0.0033991 | 2918 | 0.19 | 1175
2345 | MORGAN HILL 2106CB | 83242106 | MORGAN HILL 2106 | CB | FALSE | 6247.2514 | 1003.198 | 0.62349 | 47 | 4.8424e-05 | 3081 | 0.73812 | 2907 | 3.5184e-05 | 0.0016536 | 2919 |  | 2772
4552 | SHINGLE SPRINGS 2108449638 | 153652108 | SHINGLE SPRINGS 2108 | 449638 | TRUE | 41.9833 | 41.9833 | 0.026093 | 1 | 0.00016049 | 640 | 0.21903 | 2930 | 3.5151e-05 | 3.5151e-05 | 2920 |  | 2904
2359 | PACIFICA 1101777484 | 22811101 | PACIFICA 1101 | 777484 | FALSE | 5712.0142 | 1455.0408 | 0.90431 | 50 | 1.3219e-05 | 3597 | 5.1374 | 2746 | 3.5066e-05 | 0.0017533 | 2921 |  | 2773
6715 | PARADISE 11032534 | 102831103 | PARADISE 1103 | 2534 | FALSE | 5245.4729 | 5105.9059 | 3.1733 | 49 | 0.00050354 | 30 | 0.066327 | 3143 | 3.3375e-05 | 0.0016354 | 2922 | 0.49 | 899
416 | PACIFICA 1102CB | 22811102 | PACIFICA 1102 | CB | TRUE | 6265.5755 | 560.1275 | 0.34812 | 51 | 1.5294e-05 | 3585 | 1.6186 | 2858 | 3.2507e-05 | 0.0016578 | 2923 | 0.17 | 1234
4774 | PARADISE 11042488 | 102831104 | PARADISE 1104 | 2488 | FALSE | 5690.0714 | 5690.0714 | 3.5364 | 47 | 0.0004856 | 34 | 0.066431 | 3043 | 3.2259e-05 | 0.0015162 | 2924 |  | 2916
10872 | WILLOW CREEK 1103181562 | 192171103 | WILLOW CREEK 1103 | 181562 | TRUE | 4.572 | 4.572 | 0.0028415 | 1 | 0.00048291 | 37 | 0.066432 | 2996 | 3.208e-05 | 3.208e-05 | 2925 |  | 3615
5198 | PARADISE 1104283794 | 102831104 | PARADISE 1104 | 283794 | FALSE | 4034.8507 | 3810.7404 | 2.3684 | 37 | 0.00048267 | 38 | 0.066328 | 3142 | 3.2004e-05 | 0.0011841 | 2926 |  | 2942
2421 | FORT BRAGG A 110235592 | 42761102 | FORT BRAGG A 1102 | 35592 | FALSE | 21129.6388 | 21129.6388 | 13.1322 | 149 | 0.00014429 | 808 | 0.38535 | 2920 | 3.1961e-05 | 0.0047622 | 2927 | 0.14 | 1329
6748 | BRUNSWICK 11103907 | 152481110 | BRUNSWICK 1110 | 3907 | FALSE | 1437.9091 | 1437.9091 | 0.89367 | 16 | 0.00047789 | 39 | 0.066432 | 3009 | 3.1747e-05 | 0.00050795 | 2928 | 0.56 | 864
1323 | PEORIA 17013186 | 163781701 | PEORIA 1701 | 3186 | FALSE | 15806.1877 | 15806.1877 | 9.8236 | 143 | 7.9358e-05 | 2223 | 0.39871 | 2917 | 3.1551e-05 | 0.0045118 | 2929 | 0.04 | 2226
6182 | BERESFORD 0403435168 | 24040403 | BERESFORD 0403 | 435168 | FALSE | 2902.2955 | 2068.4077 | 1.2855 | 26 | 4.9503e-05 | 3049 | 0.97971 | 2895 | 3.1131e-05 | 0.00080941 | 2930 |  | 3011
8329 | BRUNSWICK 1104244027 | 152481104 | BRUNSWICK 1104 | 244027 | TRUE | 620.9738 | 492.7502 | 0.30625 | 6 | 0.00047101 | 41 | 0.065791 | 3272 | 3.093e-05 | 0.00018558 | 2931 |  | 3214
10464 | CAMP EVERS 210595394 | 83622105 | CAMP EVERS 2105 | 95394 | TRUE | 790.3942 | 790.3942 | 0.49123 | 8 | 0.00046445 | 43 | 0.066431 | 3075 | 3.0854e-05 | 0.00024683 | 2932 | 8.99 | 417
4342 | PARADISE 110636042 | 102831106 | PARADISE 1106 | 36042 | FALSE | 14063.6211 | 13184.5103 | 8.1942 | 119 | 0.00046491 | 42 | 0.066335 | 3138 | 3.0817e-05 | 0.0036673 | 2933 |  | 2883
9818 | ANDERSON 1101561686 | 103261101 | ANDERSON 1101 | 561686 | TRUE | 147.2029 | 147.2029 | 0.091487 | 1 | 0.00044669 | 47 | 0.066431 | 3105 | 2.9674e-05 | 2.9674e-05 | 2934 |  | 3430
2309 | BEN LOMOND 040116010 | 83040401 | BEN LOMOND 0401 | 16010 | FALSE | 2728.9115 | 2728.9115 | 1.696 | 25 | 0.00044502 | 49 | 0.066431 | 3054 | 2.9564e-05 | 0.00073909 | 2935 | 0.3 | 1015
2259 | LAKEWOOD 210738404 | 13532107 | LAKEWOOD 2107 | 38404 | FALSE | 9333.1056 | 5730.6143 | 3.5616 | 47 | 0.00010907 | 1427 | 0.73881 | 2906 | 2.9507e-05 | 0.0013868 | 2936 | 0.08 | 1611
6756 | FAIRMOUNT 0401395180 | 12650401 | FAIRMOUNT 0401 | 395180 | FALSE | 2394.7505 | 2263.8752 | 1.407 | 20 | 1.6162e-05 | 3578 | 2.4421 | 2827 | 2.9412e-05 | 0.00058824 | 2937 |  | 3059
9891 | RIO DELL 1102214052 | 192251102 | RIO DELL 1102 | 214052 | TRUE | 1011.6764 | 941.1587 | 0.58493 | 7 | 0.00044429 | 50 | 0.066065 | 3204 | 2.933e-05 | 0.00020531 | 2938 |  | 3447
9611 | DIAMOND SPRINGS 1106176130 | 152261106 | DIAMOND SPRINGS 1106 | 176130 | TRUE | 32.0737 | 32.0737 | 0.019934 | 1 | 0.00044128 | 54 | 0.066432 | 3008 | 2.9315e-05 | 2.9315e-05 | 2939 |  | 3388
9648 | CAMP EVERS 2103CB | 83622103 | CAMP EVERS 2103 | CB | TRUE | 225.7012 | 190.3788 | 0.11832 | 6 | 0.00043795 | 56 | 0.066004 | 3225 | 2.9049e-05 | 0.00017429 | 2940 | 0.17 | 1240
7669 | PARADISE 1104CB | 102831104 | PARADISE 1104 | CB | FALSE | 5993.6916 | 2211.8341 | 1.3747 | 46 | 0.0004418 | 52 | 0.065541 | 3355 | 2.9018e-05 | 0.0013348 | 2941 | 4.56 | 515
8116 | BRUNSWICK 1107969778 | 152481107 | BRUNSWICK 1107 | 969778 | FALSE | 1070.9786 | 1070.9786 | 0.66562 | 9 | 0.00042983 | 59 | 0.066432 | 3004 | 2.8554e-05 | 0.00025699 | 2942 |  | 3193
1751 | PARADISE 1104954322 | 102831104 | PARADISE 1104 | 954322 | FALSE | 6923.0973 | 6923.0973 | 4.3027 | 63 | 0.0004268 | 60 | 0.066431 | 3044 | 2.8353e-05 | 0.0017862 | 2943 |  | 2742
6559 | BIG BASIN 11015479 | 82841101 | BIG BASIN 1101 | 5479 | TRUE | 289.2777 | 289.2777 | 0.17979 | 3 | 0.00041807 | 63 | 0.066431 | 3086 | 2.7773e-05 | 8.3319e-05 | 2944 | 2.14 | 619
11110 | CAMP EVERS 2105BL 2101 | 83622105 | CAMP EVERS 2105 | BL 2101 | TRUE | 5.191 | 5.191 | 0.0032262 | 1 | 0.00041248 | 66 | 0.066431 | 3087 | 2.7401e-05 | 2.7401e-05 | 2945 | 6.05 | 475
7068 | BURNS 2101CB | 183582101 | BURNS 2101 | CB | FALSE | 2742.3098 | 2742.3098 | 1.7044 | 19 | 0.00040765 | 67 | 0.066431 | 3078 | 2.7081e-05 | 0.00051453 | 2946 | 26.67 | 267
10401 | POINT MORETTI 110110722 | 82931101 | POINT MORETTI 1101 | 10722 | TRUE | 937.9448 | 937.9448 | 0.58294 | 9 | 0.00040174 | 68 | 0.066431 | 3060 | 2.6688e-05 | 0.00024019 | 2947 | 14.01 | 358
2162 | SOBRANTE 1102L510R | 14671102 | SOBRANTE 1102 | L510R | FALSE | 15698.8958 | 15538.9501 | 9.6575 | 136 | 8.2413e-05 | 2142 | 0.24129 | 2927 | 2.6158e-05 | 0.0035575 | 2948 | 0.21 | 1146
8264 | MIRABEL 1101781318 | 42091101 | MIRABEL 1101 | 781318 | TRUE | 172.1377 | 172.1377 | 0.10698 | 3 | 0.00038201 | 74 | 0.066431 | 3034 | 2.5377e-05 | 7.6132e-05 | 2949 |  | 3210
2959 | PARADISE 110453544 | 102831104 | PARADISE 1104 | 53544 | FALSE | 1728.2043 | 1035.1182 | 0.64333 | 19 | 0.00038613 | 71 | 0.06569 | 3314 | 2.5314e-05 | 0.00048097 | 2950 |  | 2807
2047 | VALLEY VIEW 1103CB | 14341103 | VALLEY VIEW 1103 | CB | TRUE | 10480.8911 | 272.5459 | 0.16939 | 83 | 4.1439e-05 | 3235 | 0.25769 | 2926 | 2.5206e-05 | 0.0020921 | 2951 | 5.67 | 480
3341 | CAMP EVERS 21055146 | 83622105 | CAMP EVERS 2105 | 5146 | FALSE | 9534.7408 | 9534.7408 | 5.9259 | 63 | 0.00036971 | 78 | 0.066431 | 3063 | 2.4561e-05 | 0.0015473 | 2952 | 0.55 | 870
4945 | CASTRO VALLEY 1102837904 | 14091102 | CASTRO VALLEY 1102 | 837904 | FALSE | 3252.9939 | 1669.2171 | 1.0374 | 25 | 3.8294e-05 | 3293 | 0.69841 | 2909 | 2.4435e-05 | 0.00061089 | 2953 |  | 2930
5852 | PARADISE 1104961990 | 102831104 | PARADISE 1104 | 961990 | FALSE | 10972.2602 | 10972.2602 | 6.8193 | 91 | 0.00035642 | 85 | 0.066431 | 3018 | 2.3677e-05 | 0.0021547 | 2954 |  | 2984
8958 | PARADISE 1103772517 | 102831103 | PARADISE 1103 | 772517 | FALSE | 2777.244 | 2777.244 | 1.7261 | 24 | 0.00035423 | 87 | 0.066378 | 3129 | 2.3519e-05 | 0.00056446 | 2955 |  | 3281
5973 | BEN LOMOND 0401CB | 83040401 | BEN LOMOND 0401 | CB | FALSE | 12509.5528 | 12509.5528 | 7.7747 | 106 | 0.00034662 | 93 | 0.066431 | 3076 | 2.3026e-05 | 0.0024408 | 2956 | 1.58 | 665
10776 | GRASS VALLEY 1101528232 | 152031101 | GRASS VALLEY 1101 | 528232 | TRUE | 149.6502 | 149.6502 | 0.093008 | 2 | 0.00033485 | 99 | 0.066432 | 3013 | 2.2245e-05 | 4.449e-05 | 2957 |  | 3604
10760 | FLINT 1102CB | 152531102 | FLINT 1102 | CB | TRUE | 149.4178 | 149.4178 | 0.092864 | 2 | 0.00033388 | 100 | 0.066432 | 3002 | 2.218e-05 | 4.436e-05 | 2958 | 0.05 | 1937
3909 | MORRO BAY 1102V84 | 183011102 | MORRO BAY 1102 | V84 | TRUE | 15879.9521 | 369.7837 | 0.22982 | 126 | 7.2115e-06 | 3627 | 0.37923 | 2921 | 2.1832e-05 | 0.0027508 | 2959 |  | 2861
7549 | PLACERVILLE 1111CB | 153081111 | PLACERVILLE 1111 | CB | FALSE | 2249.8408 | 2245.2688 | 1.3954 | 16 | 0.00032886 | 103 | 0.066351 | 3136 | 2.1827e-05 | 0.00034924 | 2960 | 0.1 | 1487
6107 | POINT MORETTI 110139126 | 82931101 | POINT MORETTI 1101 | 39126 | FALSE | 3634.7812 | 3634.7812 | 2.259 | 31 | 0.00031627 | 110 | 0.066431 | 3079 | 2.101e-05 | 0.00065131 | 2961 | 15.84 | 344
9485 | CAMP EVERS 2106834583 | 83622106 | CAMP EVERS 2106 | 834583 | TRUE | 981.0329 | 981.0329 | 0.60972 | 7 | 0.00030071 | 130 | 0.066431 | 3073 | 1.9977e-05 | 0.00013984 | 2962 | 4.09 | 528
6136 | BIG TREES 0402737512 | 83050402 | BIG TREES 0402 | 737512 | FALSE | 11180.7593 | 10917.3933 | 6.7852 | 89 | 0.0002931 | 137 | 0.066402 | 3118 | 1.9465e-05 | 0.0017324 | 2963 |  | 3008
940 | CAMP EVERS 210511384 | 83622105 | CAMP EVERS 2105 | 11384 | FALSE | 8402.4777 | 8402.4777 | 5.2222 | 59 | 0.00028937 | 140 | 0.066431 | 3069 | 1.9223e-05 | 0.0011342 | 2964 | 13.77 | 362
8260 | DIAMOND SPRINGS 1106762780 | 152261106 | DIAMOND SPRINGS 1106 | 762780 | TRUE | 1282.4551 | 400.767 | 0.24908 | 11 | 0.0002944 | 135 | 0.065383 | 3424 | 1.9222e-05 | 0.00021145 | 2965 |  | 3209
9711 | BRUNSWICK 1103262343 | 152481103 | BRUNSWICK 1103 | 262343 | FALSE | 1232.8709 | 1232.8709 | 0.76623 | 11 | 0.00028891 | 143 | 0.066432 | 3003 | 1.9193e-05 | 0.00021112 | 2966 |  | 3404
6422 | BIG BASIN 11029741 | 82841102 | BIG BASIN 1102 | 9741 | FALSE | 1036.4661 | 1036.4661 | 0.64417 | 10 | 0.00028291 | 149 | 0.066431 | 3057 | 1.8794e-05 | 0.00018794 | 2967 | 14.27 | 356
471 | BIG BASIN 11015028 | 82841101 | BIG BASIN 1101 | 5028 | FALSE | 8087.7219 | 8087.7219 | 5.0266 | 59 | 0.00027873 | 160 | 0.066431 | 3056 | 1.8516e-05 | 0.0010925 | 2968 | 0.63 | 832
5836 | BRUNSWICK 1103851116 | 152481103 | BRUNSWICK 1103 | 851116 | TRUE | 405.8442 | 316.0008 | 0.1964 | 4 | 0.00027959 | 155 | 0.066111 | 3190 | 1.8459e-05 | 7.3835e-05 | 2969 |  | 2981
10320 | DIAMOND SPRINGS 1106926235 | 152261106 | DIAMOND SPRINGS 1106 | 926235 | TRUE | 416.1419 | 305.3669 | 0.18979 | 4 | 0.00027977 | 153 | 0.065791 | 3274 | 1.8372e-05 | 7.3487e-05 | 2970 |  | 3532
10026 | SARATOGA 1103981056 | 83371103 | SARATOGA 1103 | 981056 | TRUE | 227.7546 | 132.017 | 0.082049 | 2 | 0.00027805 | 163 | 0.065789 | 3285 | 1.8259e-05 | 3.6518e-05 | 2971 |  | 3476
7034 | DIAMOND SPRINGS 110699658 | 152261106 | DIAMOND SPRINGS 1106 | 99658 | TRUE | 4406.3905 | 0 | 0 | 39 | 0.00027979 | 152 | 0.06515 | 3578 | 1.8228e-05 | 0.0007109 | 2972 | 0.05 | 2030
4269 | BRUNSWICK 110378862 | 152481103 | BRUNSWICK 1103 | 78862 | TRUE | 1804.4635 | 123.6088 | 0.076823 | 17 | 0.00027939 | 158 | 0.065225 | 3497 | 1.8213e-05 | 0.00030962 | 2973 | 5.76 | 478
3650 | ROB ROY 210512584 | 83692105 | ROB ROY 2105 | 12584 | FALSE | 41638.8897 | 5651.1648 | 3.5122 | 297 | 5.9861e-05 | 2779 | 0.22529 | 2929 | 1.8188e-05 | 0.0054019 | 2974 | 0.03 | 2245
2640 | PERRY 1101V72 | 183071101 | PERRY 1101 | V72 | FALSE | 14155.2453 | 9610.0836 | 5.9727 | 101 | 2.6938e-05 | 3473 | 1.494 | 2866 | 1.8115e-05 | 0.0018297 | 2975 | 0.05 | 1974
7574 | CAMP EVERS 210611006 | 83622106 | CAMP EVERS 2106 | 11006 | FALSE | 3281.0215 | 3281.0215 | 2.0392 | 24 | 0.00027097 | 170 | 0.066431 | 3059 | 1.8001e-05 | 0.00043202 | 2976 | 0.37 | 965
10111 | ALLEGHANY 11011101/2 | 152101101 | ALLEGHANY 1101 | 1101/2 | TRUE | 32.8824 | 32.8824 | 0.020437 | 1 | 0.00026849 | 175 | 0.066431 | 3046 | 1.7836e-05 | 1.7836e-05 | 2977 |  | 3493
7350 | SUMMIT 1101CB | 152591101 | SUMMIT 1101 | CB | TRUE | 221.0797 | 221.0797 | 0.1374 | 2 | 0.0002671 | 177 | 0.066431 | 3047 | 1.7744e-05 | 3.5488e-05 | 2978 | 0.03 | 2339
10523 | CAMP EVERS 2104710556 | 83622104 | CAMP EVERS 2104 | 710556 | TRUE | 81.8649 | 65.863 | 0.040934 | 2 | 0.00026928 | 174 | 0.065792 | 3269 | 1.7662e-05 | 3.5324e-05 | 2979 |  | 3566
5707 | FLINT 1101958726 | 152531101 | FLINT 1101 | 958726 | FALSE | 1647.4395 | 1605.4653 | 0.9978 | 13 | 0.00026566 | 180 | 0.066333 | 3140 | 1.7619e-05 | 0.00022904 | 2980 |  | 2975
8628 | POINT MORETTI 11015401 | 82931101 | POINT MORETTI 1101 | 5401 | FALSE | 4047.5171 | 4047.5171 | 2.5155 | 34 | 0.0002635 | 187 | 0.066431 | 3064 | 1.7505e-05 | 0.00059516 | 2981 | 18.02 | 327
10455 | POTTER VALLEY P H 1104CB | 42281104 | POTTER VALLEY P H 1104 | CB | TRUE | 158.4451 | 158.4451 | 0.098474 | 2 | 0.00026209 | 192 | 0.066431 | 3100 | 1.7411e-05 | 3.4822e-05 | 2982 | 0.02 | 2438
1795 | BOLINAS 11011064 | 42261101 | BOLINAS 1101 | 1064 | FALSE | 7144.3316 | 1005.39 | 0.62485 | 51 | 5.2154e-05 | 2989 | 0.37559 | 2922 | 1.7391e-05 | 0.00088693 | 2983 | 0.02 | 2426
11067 | BRUNSWICK 1104761310 | 152481104 | BRUNSWICK 1104 | 761310 | TRUE | 43.1053 | 43.1053 | 0.02679 | 1 | 0.00026016 | 195 | 0.066432 | 3006 | 1.7283e-05 | 1.7283e-05 | 2984 | 9.94 | 403
130 | CAMP EVERS 21055232 | 83622105 | CAMP EVERS 2105 | 5232 | FALSE | 7264.9547 | 7264.9547 | 4.5152 | 50 | 0.00025977 | 196 | 0.066431 | 3065 | 1.7257e-05 | 0.00086284 | 2985 | 0.52 | 889
9051 | BRUNSWICK 1103956424 | 152481103 | BRUNSWICK 1103 | 956424 | FALSE | 2618.2583 | 1661.8272 | 1.0328 | 21 | 0.00026235 | 190 | 0.065882 | 3247 | 1.7224e-05 | 0.00036171 | 2986 |  | 3301
7122 | CAMP EVERS 210510786 | 83622105 | CAMP EVERS 2105 | 10786 | FALSE | 7392.1952 | 7392.1952 | 4.5943 | 58 | 0.00025715 | 199 | 0.066431 | 3068 | 1.7083e-05 | 0.0009908 | 2987 | 23.31 | 288
7997 | CAMP EVERS 210411048 | 83622104 | CAMP EVERS 2104 | 11048 | FALSE | 2138.5875 | 1473.7073 | 0.91592 | 19 | 0.00025575 | 204 | 0.065825 | 3261 | 1.6894e-05 | 0.00032099 | 2988 | 0.22 | 1122
10098 | RALSTON 1101100040 | 24141101 | RALSTON 1101 | 100040 | FALSE | 1340.2293 | 1324.2274 | 0.82301 | 7 | 0.00025542 | 205 | 0.065698 | 3313 | 1.6779e-05 | 0.00011745 | 2989 |  | 3490
4770 | CAMP EVERS 210574170 | 83622105 | CAMP EVERS 2105 | 74170 | FALSE | 5752.9394 | 5752.9394 | 3.5755 | 43 | 0.00025227 | 211 | 0.066431 | 3071 | 1.6759e-05 | 0.00072063 | 2990 | 54.65 | 106
10059 | POTTER VALLEY P H 1105CB | 42281105 | POTTER VALLEY P H 1105 | CB | TRUE | 89.3518 | 89.3518 | 0.055533 | 2 | 0.0002491 | 218 | 0.066431 | 3102 | 1.6548e-05 | 3.3096e-05 | 2991 | 0.02 | 2430
1470 | PLACERVILLE 210619732 | 153082106 | PLACERVILLE 2106 | 19732 | FALSE | 14898.6258 | 14898.6258 | 9.2596 | 125 | 0.00024625 | 229 | 0.066432 | 3015 | 1.6359e-05 | 0.0020448 | 2992 | 0.39 | 954
5865 | CAMP EVERS 210611044 | 83622106 | CAMP EVERS 2106 | 11044 | FALSE | 19649.9105 | 12291.7272 | 7.6394 | 144 | 0.00024668 | 228 | 0.06589 | 3246 | 1.6316e-05 | 0.0023496 | 2993 | 0.26 | 1067
4584 | BRUNSWICK 1107357568 | 152481107 | BRUNSWICK 1107 | 357568 | FALSE | 3842.9954 | 1927.7671 | 1.1981 | 35 | 0.00024621 | 230 | 0.065663 | 3320 | 1.6214e-05 | 0.0005675 | 2994 |  | 2905
4170 | SAN RAFAEL 11042651 | 42011104 | SAN RAFAEL 1104 | 2651 | FALSE | 1316.7963 | 1238.5246 | 0.76975 | 10 | 0.00024324 | 237 | 0.066303 | 3149 | 1.6143e-05 | 0.00016143 | 2995 | 0.05 | 1964
4250 | SAN RAFAEL 1106837 | 42011106 | SAN RAFAEL 1106 | 837 | FALSE | 2514.1986 | 1083.651 | 0.67349 | 22 | 0.00024512 | 232 | 0.065733 | 3299 | 1.6143e-05 | 0.00035514 | 2996 | 0.03 | 2298
8770 | MIRABEL 11027401 | 42091102 | MIRABEL 1102 | 7401 | FALSE | 1710.0336 | 1710.0336 | 1.0628 | 12 | 0.00023873 | 251 | 0.066431 | 3026 | 1.5859e-05 | 0.00019031 | 2997 | 5.59 | 483
5879 | BIG BASIN 11019773 | 82841101 | BIG BASIN 1101 | 9773 | TRUE | 724.8545 | 724.8545 | 0.4505 | 6 | 0.00023796 | 254 | 0.066431 | 3077 | 1.5808e-05 | 9.4849e-05 | 2998 | 6.09 | 473
4254 | BRUNSWICK 111095576 | 152481110 | BRUNSWICK 1110 | 95576 | TRUE | 3539.5092 | 0 | 0 | 30 | 0.00024199 | 240 | 0.06515 | 3580 | 1.5765e-05 | 0.00047296 | 2999 | 0.02 | 2521
5644 | BRUNSWICK 1103234378 | 152481103 | BRUNSWICK 1103 | 234378 | FALSE | 1230.3375 | 1030.7217 | 0.6406 | 13 | 0.00023818 | 253 | 0.065939 | 3237 | 1.5727e-05 | 0.00020445 | 3000 |  | 2969
644 | CAMP EVERS 210511004 | 83622105 | CAMP EVERS 2105 | 11004 | FALSE | 6981.3249 | 6981.3249 | 4.3389 | 60 | 0.000234 | 264 | 0.066431 | 3053 | 1.5545e-05 | 0.00093268 | 3001 | 0.81 | 772
10461 | GIRVAN 1102296428 | 103401102 | GIRVAN 1102 | 296428 | FALSE | 5326.8427 | 2768.6124 | 1.7207 | 14 | 0.00023533 | 262 | 0.065703 | 3308 | 1.5492e-05 | 0.00021689 | 3002 |  | 3554
8135 | WOODSIDE 1101CB | 24251101 | WOODSIDE 1101 | CB | TRUE | 6762.3674 | 0 | 0 | 59 | 0.00023708 | 256 | 0.065169 | 3547 | 1.545e-05 | 0.00091153 | 3003 |  | 3195
555 | BRUNSWICK 110750008 | 152481107 | BRUNSWICK 1107 | 50008 | FALSE | 7897.7178 | 1828.8508 | 1.1366 | 64 | 0.00023509 | 263 | 0.06535 | 3436 | 1.5377e-05 | 0.0009841 | 3004 | 0.7 | 810
4851 | DIAMOND SPRINGS 1106910235 | 152261106 | DIAMOND SPRINGS 1106 | 910235 | TRUE | 1774.1223 | 851.0444 | 0.52893 | 16 | 0.00023372 | 267 | 0.065631 | 3328 | 1.5283e-05 | 0.00024453 | 3005 |  | 2923
436 | SARATOGA 1107LC26 | 83371107 | SARATOGA 1107 | LC26 | FALSE | 9057.4757 | 9057.4757 | 5.6293 | 74 | 0.00022734 | 294 | 0.066432 | 2991 | 1.5103e-05 | 0.0011176 | 3006 | 0.12 | 1372
3317 | PLACERVILLE 1110CB | 153081110 | PLACERVILLE 1110 | CB | FALSE | 2889.8933 | 1390.1141 | 0.86396 | 28 | 0.0002292 | 288 | 0.065745 | 3295 | 1.5035e-05 | 0.00042097 | 3007 | 0.09 | 1554
4169 | GRASS VALLEY 1102CB | 152031102 | GRASS VALLEY 1102 | CB | TRUE | 9322.594 | 131.7629 | 0.081891 | 81 | 0.00022849 | 289 | 0.065197 | 3511 | 1.4894e-05 | 0.0012064 | 3008 |  | 2874
1767 | MONTE RIO 111264682 | 42811112 | MONTE RIO 1112 | 64682 | FALSE | 2835.1135 | 2835.1135 | 1.762 | 22 | 0.00022403 | 304 | 0.066431 | 3092 | 1.4883e-05 | 0.00032742 | 3009 | 46.82 | 138
7374 | MIRABEL 1102841 | 42091102 | MIRABEL 1102 | 841 | FALSE | 1307.0396 | 1307.0396 | 0.81233 | 12 | 0.00022352 | 305 | 0.066431 | 3027 | 1.4849e-05 | 0.00017819 | 3010 | 0.34 | 982
9494 | SAN RAFAEL 1101546438 | 42011101 | SAN RAFAEL 1101 | 546438 | FALSE | 1552.7497 | 1541.3848 | 0.95798 | 14 | 0.00022139 | 313 | 0.066248 | 3162 | 1.4698e-05 | 0.00020577 | 3011 |  | 3363
7746 | SALT SPRINGS 21014913 | 163692101 | SALT SPRINGS 2101 | 4913 | FALSE | 6065.3094 | 6065.3094 | 3.7696 | 54 | 1.9829e-05 | 3546 | 0.94688 | 2897 | 1.4645e-05 | 0.00079082 | 3012 | 0.02 | 2519
7346 | OAKLAND K 1101CR346 | 12101101 | OAKLAND K 1101 | CR346 | TRUE | 330.9469 | 330.9469 | 0.20568 | 3 | 0.00021988 | 322 | 0.066432 | 2961 | 1.4607e-05 | 4.3821e-05 | 3013 | 0.27 | 1053
112 | EL DORADO PH 210219562 | 152762102 | EL DORADO PH 2102 | 19562 | FALSE | 11663.8964 | 11663.8964 | 7.2492 | 98 | 0.00021832 | 327 | 0.066431 | 3051 | 1.4503e-05 | 0.0014213 | 3014 | 80.06 | 48
3957 | LOS GATOS 1106LA42 | 82021106 | LOS GATOS 1106 | LA42 | FALSE | 4459.4554 | 4459.4554 | 2.7716 | 35 | 0.00021752 | 329 | 0.066431 | 3062 | 1.445e-05 | 0.00050575 | 3015 | 0.48 | 904
10681 | GEYSERVILLE 1101975350 | 42891101 | GEYSERVILLE 1101 | 975350 | TRUE | 405.3394 | 73.1065 | 0.045436 | 3 | 0.00015577 | 686 | 0.090462 | 2933 | 1.4284e-05 | 4.2852e-05 | 3016 |  | 3591
10208 | SHINGLE SPRINGS 2110CB | 153652110 | SHINGLE SPRINGS 2110 | CB | FALSE | 2054.39 | 1346.787 | 0.83703 | 15 | 0.00021376 | 344 | 0.065919 | 3239 | 1.4099e-05 | 0.00021149 | 3017 | 0.16 | 1250
10739 | FORT BRAGG A 1104920850 | 42761104 | FORT BRAGG A 1104 | 920850 | TRUE | 514.6425 | 322.1994 | 0.20025 | 3 | 0.00021514 | 340 | 0.065576 | 3348 | 1.406e-05 | 4.2181e-05 | 3018 |  | 3600
9733 | AUBURN 11028611 | 152161102 | AUBURN 1102 | 8611 | FALSE | 2893.9317 | 2893.9317 | 1.7986 | 22 | 0.00020875 | 367 | 0.066432 | 3005 | 1.3867e-05 | 0.00030508 | 3019 | 0.05 | 1987
6925 | MIRABEL 11022043 | 42091102 | MIRABEL 1102 | 2043 | TRUE | 902.2238 | 902.2238 | 0.56074 | 8 | 0.00020837 | 369 | 0.066431 | 3028 | 1.3842e-05 | 0.00011074 | 3020 | 28.28 | 251
6206 | SAN RAFAEL 11081247 | 42011108 | SAN RAFAEL 1108 | 1247 | TRUE | 443.4693 | 443.4693 | 0.27562 | 3 | 0.00020644 | 376 | 0.066431 | 3039 | 1.3714e-05 | 4.1142e-05 | 3021 | 45.01 | 152
9515 | HARRIS 1109661309 | 192431109 | HARRIS 1109 | 661309 | TRUE | 2205.0428 | 453.7966 | 0.28204 | 16 | 0.00020886 | 365 | 0.065469 | 3383 | 1.3667e-05 | 0.00021867 | 3022 |  | 3369
10016 | CAMP EVERS 2104600529 | 83622104 | CAMP EVERS 2104 | 600529 | TRUE | 435.4123 | 422.8048 | 0.26277 | 4 | 0.00020229 | 388 | 0.066112 | 3188 | 1.3356e-05 | 5.3422e-05 | 3023 |  | 3471
10551 | PUEBLO 1104968601 | 43291104 | PUEBLO 1104 | 968601 | TRUE | 12.2398 | 12.2398 | 0.0076071 | 1 | 0.00020045 | 395 | 0.066431 | 3041 | 1.3316e-05 | 1.3316e-05 | 3024 |  | 3573
8097 | SARATOGA 11075696 | 83371107 | SARATOGA 1107 | 5696 | FALSE | 9835.0739 | 8152.2263 | 5.0666 | 90 | 0.00020042 | 396 | 0.066175 | 3179 | 1.3265e-05 | 0.0011939 | 3025 | 0.11 | 1418
9710 | GEYSERVILLE 1101216442 | 42891101 | GEYSERVILLE 1101 | 216442 | TRUE | 327.4361 | 327.4361 | 0.2035 | 4 | 0.00012382 | 1123 | 0.10422 | 2932 | 1.2906e-05 | 5.1625e-05 | 3026 |  | 3403
8869 | BRUNSWICK 11047181 | 152481104 | BRUNSWICK 1104 | 7181 | FALSE | 1244.1443 | 1244.1443 | 0.77324 | 11 | 0.00019333 | 428 | 0.066432 | 3010 | 1.2843e-05 | 0.00014128 | 3027 | 7.1 | 450
8464 | CAMP EVERS 21067603 | 83622106 | CAMP EVERS 2106 | 7603 | FALSE | 1527.2306 | 1527.2306 | 0.94918 | 11 | 0.00019238 | 431 | 0.066431 | 3055 | 1.278e-05 | 0.00014058 | 3028 | 0.27 | 1054
1616 | SARATOGA 1106LC24 | 83371106 | SARATOGA 1106 | LC24 | FALSE | 18535.4178 | 13258.5886 | 8.2403 | 154 | 0.00019316 | 429 | 0.066006 | 3215 | 1.2747e-05 | 0.001963 | 3029 | 0.08 | 1601
10877 | MORAGA 110183424 | 13801101 | MORAGA 1101 | 83424 | FALSE | 2603.9122 | 2600.4486 | 1.6162 | 7 | 0.00018902 | 446 | 0.066249 | 3161 | 1.2546e-05 | 8.7822e-05 | 3030 | 8.82 | 419
7661 | CAMP EVERS 210616000 | 83622106 | CAMP EVERS 2106 | 16000 | FALSE | 6212.4721 | 3353.5945 | 2.0843 | 51 | 0.000189 | 448 | 0.065804 | 3266 | 1.2496e-05 | 0.0006373 | 3031 | 13.79 | 361
11062 | KESWICK 1101CB | 103451101 | KESWICK 1101 | CB | TRUE | 26.6683 | 26.6683 | 0.016574 | 1 | 0.00018686 | 464 | 0.066431 | 3104 | 1.2413e-05 | 1.2413e-05 | 3032 | 0.2 | 1169
10730 | STAFFORD 1101344092 | 43201101 | STAFFORD 1101 | 344092 | TRUE | 131.1041 | 115.3192 | 0.071671 | 2 | 0.00018617 | 465 | 0.066431 | 3037 | 1.2368e-05 | 2.4736e-05 | 3033 |  | 3598
2899 | PLACER 1101208930 | 152461101 | PLACER 1101 | 208930 | TRUE | 1425.5587 | 187.1265 | 0.1163 | 10 | 0.00018882 | 449 | 11.1381 | 2605 | 1.2302e-05 | 0.00012302 | 3034 |  | 2804
3721 | SHINGLE SPRINGS 210511172 | 153652105 | SHINGLE SPRINGS 2105 | 11172 | FALSE | 3921.2737 | 3218.2333 | 2.0001 | 38 | 0.00018146 | 501 | 0.066162 | 3181 | 1.2003e-05 | 0.00045612 | 3035 | 0.11 | 1424
8829 | MONTE RIO 1111CB | 42811111 | MONTE RIO 1111 | CB | TRUE | 408.9065 | 408.9065 | 0.25414 | 4 | 0.0001783 | 516 | 0.066431 | 3029 | 1.1845e-05 | 4.7378e-05 | 3036 | 13.33 | 366
3789 | LOS GATOS 1106LA46 | 82021106 | LOS GATOS 1106 | LA46 | FALSE | 2411.7925 | 2411.7925 | 1.4989 | 20 | 0.00017602 | 522 | 0.066431 | 3058 | 1.1694e-05 | 0.00023387 | 3037 | 19.55 | 311
8577 | SARATOGA 1115463510 | 83371115 | SARATOGA 1115 | 463510 | FALSE | 4881.4666 | 4697.8741 | 2.9197 | 41 | 0.0001755 | 524 | 0.066369 | 3132 | 1.1648e-05 | 0.00047756 | 3038 |  | 3239
8231 | HALF MOON BAY 11038898 | 24101103 | HALF MOON BAY 1103 | 8898 | FALSE | 1034.8013 | 1034.8013 | 0.64313 | 9 | 0.00017399 | 534 | 0.066431 | 3061 | 1.1558e-05 | 0.00010403 | 3039 | 0.71 | 804
3716 | CASTRO VALLEY 1102MR359 | 14091102 | CASTRO VALLEY 1102 | MR359 | TRUE | 10891.9524 | 0 | 0 | 90 | 2.5295e-05 | 3493 | 0.41659 | 2914 | 1.1476e-05 | 0.0010328 | 3040 |  | 2849
9742 | MONROE 210392868 | 43302103 | MONROE 2103 | 92868 | TRUE | 1050.3516 | 203.5363 | 0.1265 | 14 | 0.00017449 | 531 | 0.065522 | 3360 | 1.1443e-05 | 0.0001602 | 3041 | 0.39 | 955
830 | OAKLAND X 1104391688 | 12541104 | OAKLAND X 1104 | 391688 | FALSE | 2071.721 | 2071.721 | 1.2876 | 16 | 0.00017212 | 549 | 0.066431 | 3109 | 1.1434e-05 | 0.00018295 | 3042 |  | 2694
3807 | CAMP EVERS 210355638 | 83622103 | CAMP EVERS 2103 | 55638 | FALSE | 5639.9215 | 2949.5648 | 1.8332 | 42 | 0.00017356 | 537 | 0.065698 | 3312 | 1.1416e-05 | 0.00047946 | 3043 | 0.27 | 1049
2161 | LAKEWOOD 2227W503R | 13532227 | LAKEWOOD 2227 | W503R | TRUE | 12304.5424 | 121.8736 | 0.075745 | 89 | 1.999e-05 | 3544 | 0.42059 | 2913 | 1.1363e-05 | 0.0010113 | 3044 |  | 2765
10225 | CLOVERDALE 1101409224 | 42821101 | CLOVERDALE 1101 | 409224 | TRUE | 353.3451 | 138.7205 | 0.086215 | 4 | 0.0001558 | 685 | 0.071835 | 2942 | 1.131e-05 | 4.524e-05 | 3045 |  | 3518
9704 | DEL MAR 210938684 | 152582109 | DEL MAR 2109 | 38684 | TRUE | 100.1157 | 38.3974 | 0.023864 | 1 | 0.00017305 | 542 | 0.065149 | 3581 | 1.1274e-05 | 1.1274e-05 | 3046 | 0.02 | 2437
6951 | MONTE RIO 1111506 | 42811111 | MONTE RIO 1111 | 506 | FALSE | 2021.7882 | 2021.7882 | 1.2565 | 18 | 0.00016864 | 571 | 0.066431 | 3019 | 1.1203e-05 | 0.00020165 | 3047 | 19.11 | 314
7579 | WOODSIDE 11012299 | 24251101 | WOODSIDE 1101 | 2299 | FALSE | 2927.8179 | 2927.8179 | 1.8197 | 25 | 0.00016866 | 570 | 0.06638 | 3127 | 1.1198e-05 | 0.00027996 | 3048 | 3.04 | 566
4426 | SHINGLE SPRINGS 11038752 | 153651103 | SHINGLE SPRINGS 1103 | 8752 | FALSE | 2987.795 | 2987.795 | 1.8569 | 32 | 0.00016401 | 600 | 0.066391 | 3124 | 1.0889e-05 | 0.00034845 | 3049 | 0.14 | 1308
3276 | CAMP EVERS 210310946 | 83622103 | CAMP EVERS 2103 | 10946 | FALSE | 13600.904 | 9098.3132 | 5.6546 | 112 | 0.00016435 | 595 | 0.06595 | 3235 | 1.0851e-05 | 0.0012153 | 3050 | 0.4 | 945
4220 | OAKLAND X 1104CR214 | 12541104 | OAKLAND X 1104 | CR214 | FALSE | 4637.1496 | 4637.1496 | 2.882 | 35 | 0.00016318 | 609 | 0.066431 | 3098 | 1.0841e-05 | 0.00037942 | 3051 | 26.71 | 265
3032 | OAKLAND X 1104CR288 | 12541104 | OAKLAND X 1104 | CR288 | FALSE | 4382.4988 | 4382.4988 | 2.7237 | 46 | 0.00016278 | 615 | 0.066431 | 3090 | 1.0814e-05 | 0.00049744 | 3052 | 0.78 | 779
3352 | OAKLAND X 1104CR022 | 12541104 | OAKLAND X 1104 | CR022 | FALSE | 6467.1642 | 6467.1642 | 4.0194 | 48 | 0.00016152 | 625 | 0.066431 | 3103 | 1.073e-05 | 0.00051505 | 3053 | 12.67 | 369
9828 | ALLEGHANY 11021101/2 | 152101102 | ALLEGHANY 1102 | 1101/2 | TRUE | 31.1897 | 31.1897 | 0.019385 | 1 | 0.00016141 | 627 | 0.066431 | 3050 | 1.0723e-05 | 1.0723e-05 | 3054 |  | 3431
9784 | CAMP EVERS 2104496570 | 83622104 | CAMP EVERS 2104 | 496570 | TRUE | 701.3537 | 389.3118 | 0.24196 | 8 | 0.00016262 | 617 | 0.065632 | 3327 | 1.0717e-05 | 8.5734e-05 | 3055 |  | 3421
6309 | MONTE RIO 1113250 | 42811113 | MONTE RIO 1113 | 250 | FALSE | 1985.3414 | 1985.3414 | 1.2339 | 14 | 0.0001605 | 639 | 0.066431 | 3020 | 1.0662e-05 | 0.00014927 | 3056 | 12.63 | 371
10893 | FROGTOWN 1702390720 | 163451702 | FROGTOWN 1702 | 390720 | TRUE | 218.4469 | 202.4448 | 0.12582 | 2 | 0.00015881 | 655 | 0.066432 | 2955 | 1.055e-05 | 2.11e-05 | 3057 |  | 3617
4614 | SAN RAFAEL 11081262 | 42011108 | SAN RAFAEL 1108 | 1262 | FALSE | 7115.8815 | 6311.248 | 3.9225 | 57 | 0.00015861 | 656 | 0.066252 | 3160 | 1.0529e-05 | 0.00060016 | 3058 | 0.45 | 914
9095 | LLAGAS 2107250129 | 83182107 | LLAGAS 2107 | 250129 | TRUE | 467.9989 | 401.6728 | 0.24964 | 5 | 0.00015745 | 668 | 0.066432 | 2964 | 1.046e-05 | 5.23e-05 | 3059 |  | 3307
8911 | CAMP EVERS 2106CB | 83622106 | CAMP EVERS 2106 | CB | FALSE | 3786.5637 | 1101.4532 | 0.68456 | 37 | 0.00015882 | 654 | 0.065393 | 3421 | 1.0397e-05 | 0.00038468 | 3060 | 0.08 | 1623
10545 | PASO ROBLES 1103451760 | 182611103 | PASO ROBLES 1103 | 451760 | TRUE | 98.2563 | 98.2563 | 0.061067 | 2 | 0.000155 | 694 | 0.066432 | 2956 | 1.0297e-05 | 2.0594e-05 | 3061 |  | 3571
1830 | SANTA ROSA A 1104210 | 42151104 | SANTA ROSA A 1104 | 210 | FALSE | 12611.9142 | 10477.8716 | 6.512 | 107 | 0.00015483 | 696 | 0.066181 | 3174 | 1.0255e-05 | 0.0010973 | 3062 | 0.61 | 845
10656 | MIWUK 170179118 | 163661701 | MIWUK 1701 | 79118 | TRUE | 31.1564 | 31.1564 | 0.019364 | 2 | 0.00015411 | 704 | 0.066431 | 3084 | 1.0238e-05 | 2.0475e-05 | 3063 | 13.07 | 367
7888 | MONTE RIO 1112212 | 42811112 | MONTE RIO 1112 | 212 | FALSE | 3618.1725 | 3618.1725 | 2.2487 | 27 | 0.00015405 | 705 | 0.066431 | 3024 | 1.0234e-05 | 0.00027631 | 3064 | 26.95 | 263
5285 | CAMP EVERS 21061625 | 83622106 | CAMP EVERS 2106 | 1625 | FALSE | 1400.9701 | 1400.9701 | 0.87071 | 10 | 0.00015401 | 706 | 0.066431 | 3067 | 1.0231e-05 | 0.00010231 | 3065 | 45.14 | 150
7246 | HUMBOLDT BAY 1102104220 | 192341102 | HUMBOLDT BAY 1102 | 104220 | FALSE | 5237.7249 | 1476.8749 | 0.91788 | 45 | 0.00015541 | 691 | 0.065461 | 3392 | 1.0177e-05 | 0.00045796 | 3066 |  | 3107
3485 | SAN RAFAEL 1107CB | 42011107 | SAN RAFAEL 1107 | CB | FALSE | 12682.0012 | 7810.3005 | 4.8541 | 107 | 0.00015094 | 728 | 0.065845 | 3256 | 9.9897e-06 | 0.0010689 | 3067 | 0.33 | 987
1447 | OAKLAND K 1104CR204 | 12101104 | OAKLAND K 1104 | CR204 | FALSE | 6639.5298 | 6639.5298 | 4.1265 | 49 | 0.00015005 | 734 | 0.066431 | 3107 | 9.9677e-06 | 0.00048842 | 3068 | 0.48 | 901
10822 | GRASS VALLEY 1103CB | 152031103 | GRASS VALLEY 1103 | CB | TRUE | 191.1806 | 191.1806 | 0.11882 | 2 | 0.00014987 | 738 | 0.066432 | 3011 | 9.9558e-06 | 1.9912e-05 | 3069 | 0.03 | 2348
3457 | OAKLAND K 1101CR178 | 12101101 | OAKLAND K 1101 | CR178 | TRUE | 529.8862 | 529.8862 | 0.32933 | 7 | 0.00014846 | 758 | 0.066432 | 2953 | 9.8623e-06 | 6.9036e-05 | 3070 | 0.29 | 1028
3129 | SYCAMORE CREEK 1109CB | 102971109 | SYCAMORE CREEK 1109 | CB | TRUE | 14599.8126 | 271.1511 | 0.16852 | 108 | 0.00013381 | 947 | 0.073352 | 2938 | 9.8448e-06 | 0.0010632 | 3071 | 0.04 | 2189
2013 | SHINGLE SPRINGS 210851474 | 153652108 | SHINGLE SPRINGS 2108 | 51474 | TRUE | 7519.049 | 594.1189 | 0.36925 | 68 | 0.00015085 | 730 | 0.065188 | 3526 | 9.839e-06 | 0.00066905 | 3072 | 0.02 | 2433
4677 | MIDDLETOWN 1101932140 | 43141101 | MIDDLETOWN 1101 | 932140 | TRUE | 1542.2382 | 861.7057 | 0.53555 | 15 | 0.00014685 | 774 | 0.065836 | 3258 | 9.669e-06 | 0.00014503 | 3073 |  | 2908
3638 | WOODSIDE 1104CB | 24251104 | WOODSIDE 1104 | CB | TRUE | 11988.7275 | 167.7195 | 0.10424 | 114 | 0.00014824 | 761 | 0.06517 | 3545 | 9.6632e-06 | 0.0011016 | 3074 | 0.07 | 1673
8277 | MONTE RIO 1113532 | 42811113 | MONTE RIO 1113 | 532 | TRUE | 844.3261 | 844.3261 | 0.52475 | 8 | 0.00014487 | 803 | 0.066431 | 3021 | 9.6241e-06 | 7.6993e-05 | 3075 | 27.34 | 259
854 | SHINGLE SPRINGS 1104CB | 153651104 | SHINGLE SPRINGS 1104 | CB | FALSE | 3812.8299 | 1129.2677 | 0.70184 | 32 | 0.00014601 | 789 | 0.06551 | 3366 | 9.5675e-06 | 0.00030616 | 3076 | 0.04 | 2130
6660 | HALSEY 11026129 | 152241102 | HALSEY 1102 | 6129 | FALSE | 5155.4944 | 5155.4944 | 3.2042 | 39 | 0.0001435 | 819 | 0.066432 | 3007 | 9.5328e-06 | 0.00037178 | 3077 | 0.06 | 1793
10561 | BIG RIVER 1101CB | 43081101 | BIG RIVER 1101 | CB | TRUE | 35.3815 | 35.3815 | 0.02199 | 1 | 0.00014293 | 826 | 0.066432 | 2990 | 9.4951e-06 | 9.4951e-06 | 3078 | 0.05 | 1945
4323 | GIRVAN 1102CB | 103401102 | GIRVAN 1102 | CB | FALSE | 22008.731 | 1759.2867 | 1.0934 | 102 | 0.00014538 | 799 | 0.065157 | 3559 | 9.4726e-06 | 0.0009662 | 3079 | 0.03 | 2325
5228 | MONTE RIO 11135026 | 42811113 | MONTE RIO 1113 | 5026 | FALSE | 2967.0616 | 2967.0616 | 1.844 | 23 | 0.00014253 | 832 | 0.066431 | 3023 | 9.4686e-06 | 0.00021778 | 3080 | 0.35 | 976
7379 | CALPELLA 1102379946 | 43411102 | CALPELLA 1102 | 379946 | FALSE | 2891.0032 | 1211.8313 | 0.75316 | 15 | 0.00014448 | 805 | 0.06515 | 3577 | 9.4131e-06 | 0.0001412 | 3081 |  | 3120
8927 | ELK 1101CB | 42981101 | ELK 1101 | CB | TRUE | 39.9198 | 39.9198 | 0.02481 | 1 | 0.0001444 | 807 | 0.065148 | 3597 | 9.4072e-06 | 9.4072e-06 | 3082 | 0.01 | 2574
6426 | ALTO 1125296476 | 42031125 | ALTO 1125 | 296476 | FALSE | 1196.6443 | 1061.0328 | 0.65944 | 11 | 0.00014203 | 839 | 0.065849 | 3254 | 9.3993e-06 | 0.00010339 | 3083 |  | 3030
7763 | BRUNSWICK 1105297538 | 152481105 | BRUNSWICK 1105 | 297538 | FALSE | 1703.5587 | 1703.5587 | 1.0588 | 15 | 0.000141 | 854 | 0.066432 | 3014 | 9.367e-06 | 0.0001405 | 3084 |  | 3160
6048 | SILVERADO 2105337226 | 43432105 | SILVERADO 2105 | 337226 | TRUE | 1293.8077 | 458.4827 | 0.28495 | 13 | 0.00014222 | 835 | 0.065742 | 3297 | 9.3615e-06 | 0.0001217 | 3085 |  | 2998
785 | MIRABEL 1102CB | 42091102 | MIRABEL 1102 | CB | TRUE | 10759.641 | 358.8557 | 0.22303 | 85 | 0.00014251 | 833 | 0.065166 | 3549 | 9.286e-06 | 0.00078931 | 3086 | 0.26 | 1071
10915 | CLARKSVILLE 210551478 | 153612105 | CLARKSVILLE 2105 | 51478 | TRUE | 90.198 | 81.0541 | 0.050375 | 3 | 0.00014054 | 863 | 0.065577 | 3343 | 9.2483e-06 | 2.7745e-05 | 3087 | 1.23 | 697
3642 | AUBURN 1102CB | 152161102 | AUBURN 1102 | CB | FALSE | 11489.4556 | 2237.7238 | 1.3908 | 99 | 0.00014106 | 853 | 0.065344 | 3440 | 9.2292e-06 | 0.00091369 | 3088 | 0.02 | 2562
10606 | BERKELEY F 1105BR166 | 12061105 | BERKELEY F 1105 | BR166 | TRUE | 61.4345 | 61.4345 | 0.038182 | 2 | 0.00013883 | 886 | 0.066432 | 2952 | 9.2229e-06 | 1.8446e-05 | 3089 | 0.05 | 1939
2771 | RIO DELL 1102CB | 192251102 | RIO DELL 1102 | CB | TRUE | 10445.4547 | 0 | 0 | 86 | 0.00014143 | 846 | 0.065148 | 3602 | 9.2139e-06 | 0.0007924 | 3090 | 0.28 | 1040
10346 | EEL RIVER 1103241646 | 192381103 | EEL RIVER 1103 | 241646 | TRUE | 2237.0921 | 583.4204 | 0.3626 | 13 | 0.00014029 | 866 | 0.065148 | 3600 | 9.1396e-06 | 0.00011881 | 3091 |  | 3536
964 | SAN RAFAEL 110991742 | 42011109 | SAN RAFAEL 1109 | 91742 | FALSE | 7594.7858 | 3844.7445 | 2.3895 | 67 | 0.00013708 | 906 | 0.065724 | 3302 | 9.0186e-06 | 0.00060425 | 3092 | 0.12 | 1387
5348 | EEL RIVER 11033820 | 192381103 | EEL RIVER 1103 | 3820 | TRUE | 23262.4232 | 0 | 0 | 115 | 0.0001364 | 914 | 0.065808 | 3265 | 8.9864e-06 | 0.0010334 | 3093 | 0.02 | 2422
3020 | SARATOGA 1104209146 | 83371104 | SARATOGA 1104 | 209146 | FALSE | 9672.039 | 4936.2554 | 3.0679 | 85 | 0.00013627 | 917 | 0.065797 | 3267 | 8.9692e-06 | 0.00076238 | 3094 |  | 2810
10029 | MONTICELLO 11011780 | 43051101 | MONTICELLO 1101 | 1780 | TRUE | 115.3297 | 115.3297 | 0.071678 | 1 | 0.00013489 | 928 | 0.06643 | 3113 | 8.9608e-06 | 8.9608e-06 | 3095 | 0.87 | 761
10582 | OAKLAND X 1101328808 | 12541101 | OAKLAND X 1101 | 328808 | TRUE | 186.4686 | 186.4686 | 0.11589 | 1 | 0.00013477 | 930 | 0.066432 | 2960 | 8.9528e-06 | 8.9528e-06 | 3096 |  | 3574
8839 | BIG BASIN 11026219 | 82841102 | BIG BASIN 1102 | 6219 | FALSE | 1488.6262 | 1488.6262 | 0.92519 | 11 | 0.00013222 | 978 | 0.066431 | 3066 | 8.7836e-06 | 9.662e-05 | 3097 | 7 | 455
2096 | CALISTOGA 1102184814 | 42711102 | CALISTOGA 1102 | 184814 | TRUE | 2352.3551 | 682.245 | 0.42402 | 20 | 0.00013241 | 973 | 0.065475 | 3379 | 8.707e-06 | 0.00017414 | 3098 |  | 2762
10342 | FROGTOWN 1702832694 | 163451702 | FROGTOWN 1702 | 832694 | TRUE | 477.5655 | 461.5634 | 0.28686 | 5 | 0.0001169 | 1251 | 0.073805 | 2937 | 8.7057e-06 | 4.3529e-05 | 3099 |  | 3535
2914 | EUREKA E 110435934 | 192331104 | EUREKA E 1104 | 35934 | TRUE | 5459.9113 | 78.4109 | 0.048733 | 46 | 0.00013282 | 962 | 0.065203 | 3509 | 8.6658e-06 | 0.00039863 | 3100 |  | 2806
4896 | IGNACIO 1105490728 | 42481105 | IGNACIO 1105 | 490728 | FALSE | 1414.5018 | 1044.2482 | 0.649 | 11 | 0.00013128 | 992 | 0.065966 | 3228 | 8.6628e-06 | 9.5291e-05 | 3101 |  | 2925
9315 | LAKEWOOD 2224798018 | 13532224 | LAKEWOOD 2224 | 798018 | FALSE | 1485.4108 | 1448.3137 | 0.90013 | 13 | 0.0001303 | 1006 | 0.066234 | 3166 | 8.6422e-06 | 0.00011235 | 3102 |  | 3340
9391 | WATERSHED 0402CB | 24240402 | WATERSHED 0402 | CB | TRUE | 1752.4587 | 342.98 | 0.21316 | 11 | 0.00013264 | 969 | 0.065147 | 3621 | 8.6414e-06 | 9.5055e-05 | 3103 |  | 3350
9903 | PACIFICA 1102894156 | 22811102 | PACIFICA 1102 | 894156 | TRUE | 625.3701 | 625.3701 | 0.38867 | 4 | 0.0001303 | 1005 | 0.066111 | 3196 | 8.6111e-06 | 3.4445e-05 | 3104 |  | 3450
7834 | GREENBRAE 1103718674 | 43091103 | GREENBRAE 1103 | 718674 | FALSE | 1848.6771 | 1301.8094 | 0.80908 | 16 | 0.0001305 | 1001 | 0.065951 | 3233 | 8.6092e-06 | 0.00013775 | 3105 |  | 3168
10810 | PLACERVILLE 1111610322 | 153081111 | PLACERVILLE 1111 | 610322 | TRUE | 220.6867 | 220.6867 | 0.13716 | 3 | 0.00012983 | 1012 | 0.066004 | 3217 | 8.5935e-06 | 2.578e-05 | 3106 |  | 3607
10497 | FORT ORD 21069658 | 182402106 | FORT ORD 2106 | 9658 | TRUE | 156.0125 | 156.0125 | 0.096962 | 3 | 0.00012787 | 1049 | 0.066432 | 2984 | 8.4949e-06 | 2.5485e-05 | 3107 | 0.04 | 2071
5369 | OAKLAND K 1104CR206 | 12101104 | OAKLAND K 1104 | CR206 | FALSE | 2877.1568 | 2877.1568 | 1.7882 | 22 | 0.00012717 | 1061 | 0.066431 | 3108 | 8.4479e-06 | 0.00018585 | 3108 | 0.28 | 1042
6668 | PAUL SWEET 21075291 | 83252107 | PAUL SWEET 2107 | 5291 | TRUE | 1596.261 | 50.439 | 0.031348 | 14 | 0.00012858 | 1037 | 0.065239 | 3485 | 8.4226e-06 | 0.00011792 | 3109 |  | 3053
4822 | CAMP EVERS 21035404 | 83622103 | CAMP EVERS 2103 | 5404 | FALSE | 7456.6431 | 4377.7978 | 2.7208 | 63 | 0.00012738 | 1057 | 0.065779 | 3291 | 8.4149e-06 | 0.00053014 | 3110 | 0.15 | 1284
10986 | RINCON 1101205854 | 43321101 | RINCON 1101 | 205854 | TRUE | 505.1079 | 505.1079 | 0.31393 | 5 | 0.00012714 | 1063 | 0.065923 | 3238 | 8.3652e-06 | 4.1826e-05 | 3111 |  | 3625
1364 | CAMP EVERS 21035402 | 83622103 | CAMP EVERS 2103 | 5402 | FALSE | 10826.3428 | 4595.9767 | 2.8564 | 87 | 0.0001269 | 1066 | 0.065546 | 3353 | 8.3234e-06 | 0.00072413 | 3112 | 0.19 | 1181
9661 | SARATOGA 1105431214 | 83371105 | SARATOGA 1105 | 431214 | TRUE | 794.6731 | 500.3272 | 0.31096 | 9 | 0.00012639 | 1076 | 0.065861 | 3253 | 8.308e-06 | 7.4772e-05 | 3113 |  | 3396
6999 | JESSUP 1102158468 | 103441102 | JESSUP 1102 | 158468 | FALSE | 1388.9106 | 1120.0792 | 0.69613 | 11 | 0.00012572 | 1083 | 0.066083 | 3201 | 8.3063e-06 | 9.1369e-05 | 3114 |  | 3084
7019 | FORT BRAGG A 1102816 | 42761102 | FORT BRAGG A 1102 | 816 | FALSE | 4123.7572 | 3941.7419 | 2.4498 | 29 | 0.00012427 | 1112 | 0.066299 | 3150 | 8.2407e-06 | 0.00023898 | 3115 | 0.05 | 2024
9287 | SOBRANTE 1103N510R | 14671103 | SOBRANTE 1103 | N510R | TRUE | 1403.237 | 401.7471 | 0.24969 | 15 | 0.00012562 | 1086 | 0.065412 | 3409 | 8.2224e-06 | 0.00012334 | 3116 | 0.19 | 1183
10537 | FROGTOWN 1702798032 | 163451702 | FROGTOWN 1702 | 798032 | TRUE | 259.8305 | 244.5065 | 0.15196 | 2 | 0.00012449 | 1108 | 0.065789 | 3287 | 8.1969e-06 | 1.6394e-05 | 3117 |  | 3569
7405 | HARRIS 11082062 | 192431108 | HARRIS 1108 | 2062 | FALSE | 8420.6852 | 2556.2544 | 1.5887 | 83 | 0.00012402 | 1119 | 0.065581 | 3338 | 8.1613e-06 | 0.00067739 | 3118 | 0.04 | 2221
3886 | SAN RAFAEL 11081457 | 42011108 | SAN RAFAEL 1108 | 1457 | FALSE | 1229.3805 | 1229.3805 | 0.76406 | 9 | 0.00012274 | 1137 | 0.066431 | 3025 | 8.1539e-06 | 7.3385e-05 | 3119 | 0.27 | 1047
9639 | IGNACIO 1105967039 | 42481105 | IGNACIO 1105 | 967039 | TRUE | 469.6042 | 292.9124 | 0.18205 | 3 | 0.00012406 | 1117 | 0.065578 | 3342 | 8.139e-06 | 2.4417e-05 | 3120 |  | 3394
10422 | OAKLAND J 1102CR102 | 12091102 | OAKLAND J 1102 | CR102 | TRUE | 316.3322 | 316.3322 | 0.1966 | 6 | 0.00012168 | 1153 | 0.066431 | 3101 | 8.0835e-06 | 4.8501e-05 | 3121 | 0.08 | 1651
10726 | CALISTOGA 1102960240 | 42711102 | CALISTOGA 1102 | 960240 | TRUE | 816.2732 | 816.2732 | 0.50732 | 5 | 0.00012223 | 1144 | 0.066176 | 3175 | 8.0789e-06 | 4.0394e-05 | 3122 |  | 3597
9181 | MIWUK 1702531976 | 163661702 | MIWUK 1702 | 531976 | FALSE | 2102.4835 | 2102.4835 | 1.3067 | 17 | 0.00012078 | 1169 | 0.066431 | 3080 | 8.0236e-06 | 0.0001364 | 3123 |  | 3322
10385 | ALLEGHANY 11011101/2 | 152101101 | ALLEGHANY 1101 | 1101/2 | TRUE | 36.9839 | 36.9839 | 0.022986 | 1 | 0.00012061 | 1175 | 0.066431 | 3045 | 8.0126e-06 | 8.0126e-06 | 3124 |  | 3540
9316 | FORT BRAGG A 1103284356 | 42761103 | FORT BRAGG A 1103 | 284356 | TRUE | 325.8775 | 218.127 | 0.13557 | 4 | 0.00012158 | 1155 | 0.066111 | 3192 | 7.9902e-06 | 3.1961e-05 | 3125 |  | 3341
10880 | OAKLAND X 1104CR101 | 12541104 | OAKLAND X 1104 | CR101 | TRUE | 28.3921 | 28.3921 | 0.017646 | 1 | 0.00011894 | 1208 | 0.066432 | 2948 | 7.9011e-06 | 7.9011e-06 | 3126 | 0.27 | 1055
4441 | OAKLAND X 1101CR224 | 12541101 | OAKLAND X 1101 | CR224 | TRUE | 1656.0037 | 656.3547 | 0.40793 | 17 | 0.00012031 | 1179 | 0.065676 | 3317 | 7.8938e-06 | 0.0001342 | 3127 | 0.04 | 2180
10513 | OILFIELDS 1103441010 | 182391103 | OILFIELDS 1103 | 441010 | TRUE | 1310.5118 | 592.4873 | 0.36823 | 4 | 6.8458e-05 | 2523 | 0.11315 | 2931 | 7.8772e-06 | 3.1509e-05 | 3128 |  | 3562
1793 | SAN RAFAEL 1109535284 | 42011109 | SAN RAFAEL 1109 | 535284 | TRUE | 913.1511 | 10.8615 | 0.0067505 | 9 | 0.00012012 | 1185 | 0.065436 | 3401 | 7.8608e-06 | 7.0747e-05 | 3129 |  | 2746
8925 | FRUITLAND 11418746 | 192311141 | FRUITLAND 1141 | 8746 | TRUE | 832.2162 | 645.6965 | 0.4013 | 8 | 0.00011829 | 1225 | 0.06579 | 3278 | 7.8216e-06 | 6.2573e-05 | 3130 | 0.55 | 867
8734 | LOS GATOS 110160052 | 82021101 | LOS GATOS 1101 | 60052 | FALSE | 3169.0097 | 3169.0097 | 1.9696 | 28 | 0.00011748 | 1236 | 0.066432 | 3001 | 7.8045e-06 | 0.00021853 | 3131 | 0.05 | 1976
6798 | SAN CARLOS 110475210 | 24181104 | SAN CARLOS 1104 | 75210 | TRUE | 618.926 | 618.926 | 0.38467 | 6 | 0.00011638 | 1261 | 0.066432 | 2967 | 7.7312e-06 | 4.6387e-05 | 3132 | 0.05 | 2048
6381 | OAKLAND X 1106CR008 | 12541106 | OAKLAND X 1106 | CR008 | FALSE | 7178.6151 | 7178.6151 | 4.4615 | 65 | 0.00011602 | 1269 | 0.066431 | 3099 | 7.7074e-06 | 0.00050098 | 3133 | 0.17 | 1230
10638 | SAN RAFAEL 11092213 | 42011109 | SAN RAFAEL 1109 | 2213 | TRUE | 689.8513 | 689.8513 | 0.42875 | 6 | 0.00011622 | 1265 | 0.066218 | 3167 | 7.6893e-06 | 4.6136e-05 | 3134 | 0.02 | 2454
9009 | ALTO 1124553571 | 42031124 | ALTO 1124 | 553571 | TRUE | 319.9061 | 174.9029 | 0.1087 | 4 | 0.00011616 | 1267 | 0.065791 | 3271 | 7.6617e-06 | 3.0647e-05 | 3135 |  | 3296
1292 | EEL RIVER 1103CB | 192381103 | EEL RIVER 1103 | CB | TRUE | 64360.3141 | 0 | 0 | 374 | 0.00011744 | 1237 | 0.065148 | 3603 | 7.6507e-06 | 0.0028614 | 3136 |  | 2721
2486 | LOYOLA 110260082 | 82161102 | LOYOLA 1102 | 60082 | TRUE | 6614.3058 | 0 | 0 | 57 | 0.00011735 | 1238 | 0.06517 | 3546 | 7.6477e-06 | 0.00043592 | 3137 |  | 2780
9942 | BRUNSWICK 1104327226 | 152481104 | BRUNSWICK 1104 | 327226 | TRUE | 144.3861 | 79.5833 | 0.049461 | 2 | 0.0001161 | 1268 | 0.065791 | 3273 | 7.6459e-06 | 1.5292e-05 | 3138 |  | 3458
10778 | PIT NO 5 110190846 | 101321101 | PIT NO 5 1101 | 90846 | TRUE | 149.205 | 149.205 | 0.092731 | 2 | 0.00011453 | 1306 | 0.066431 | 3082 | 7.6083e-06 | 1.5217e-05 | 3139 | 0.01 | 2578
9691 | STELLING 1109787007 | 83481109 | STELLING 1109 | 787007 | TRUE | 354.8281 | 307.1886 | 0.19092 | 5 | 0.00010238 | 1593 | 0.070735 | 2943 | 7.5915e-06 | 3.7958e-05 | 3140 |  | 3398
1439 | TAR FLAT 0402CB | 163240402 | TAR FLAT 0402 | CB | FALSE | 2354.3543 | 1281.2412 | 0.7963 | 18 | 0.00011498 | 1299 | 0.065789 | 3286 | 7.5882e-06 | 0.00013659 | 3141 | 0.02 | 2484
4239 | TAR FLAT 0401CB | 163240401 | TAR FLAT 0401 | CB | FALSE | 5901.3044 | 5623.7964 | 3.4952 | 45 | 0.00011418 | 1316 | 0.066318 | 3144 | 7.5759e-06 | 0.00034092 | 3142 | 0.06 | 1823
6173 | OAKLAND X 1104645092 | 12541104 | OAKLAND X 1104 | 645092 | FALSE | 2229.6022 | 2229.6022 | 1.3857 | 16 | 0.0001137 | 1326 | 0.066352 | 3135 | 7.5529e-06 | 0.00012085 | 3143 |  | 3010
9734 | HIGHLANDS 110484640 | 43361104 | HIGHLANDS 1104 | 84640 | TRUE | 1219.4213 | 660.5476 | 0.41053 | 14 | 0.00011439 | 1310 | 0.06579 | 3276 | 7.5307e-06 | 0.00010543 | 3144 | 0.06 | 1834
10502 | TRIDAM POWERHOUSE 2101CB | 168152101 | TRIDAM POWERHOUSE 2101 | CB | TRUE | 80.9954 | 80.9954 | 0.050339 | 3 | 0.00011256 | 1354 | 0.066431 | 3089 | 7.4775e-06 | 2.2433e-05 | 3145 | 0.03 | 2362
3266 | UKIAH 1113658899 | 42771113 | UKIAH 1113 | 658899 | TRUE | 987.2682 | 941.3759 | 0.58507 | 8 | 0.00011266 | 1349 | 0.066271 | 3156 | 7.4661e-06 | 5.9729e-05 | 3146 |  | 2819
10496 | FROGTOWN 1702814784 | 163451702 | FROGTOWN 1702 | 814784 | TRUE | 296.0572 | 280.0552 | 0.17406 | 3 | 0.00011354 | 1332 | 0.066004 | 3223 | 7.4475e-06 | 2.2342e-05 | 3147 |  | 3559
9921 | OAKLAND X 1106CR266 | 12541106 | OAKLAND X 1106 | CR266 | FALSE | 1901.6084 | 1901.6084 | 1.1819 | 8 | 0.00011171 | 1375 | 0.066431 | 3110 | 7.421e-06 | 5.9368e-05 | 3148 | 23 | 290
7361 | SARATOGA 11076867 | 83371107 | SARATOGA 1107 | 6867 | TRUE | 1328.3948 | 985.9493 | 0.61277 | 11 | 0.00011216 | 1362 | 0.066081 | 3202 | 7.4136e-06 | 8.155e-05 | 3149 | 0.06 | 1791
7276 | SAN CARLOS 11049052 | 24181104 | SAN CARLOS 1104 | 9052 | FALSE | 8315.3581 | 7722.3255 | 4.7995 | 65 | 0.00011158 | 1380 | 0.066333 | 3139 | 7.4082e-06 | 0.00048153 | 3150 | 0.1 | 1459
9123 | UKIAH 1114296894 | 42771114 | UKIAH 1114 | 296894 | TRUE | 465.5322 | 278.1636 | 0.17288 | 6 | 0.00011252 | 1355 | 0.065577 | 3344 | 7.398e-06 | 4.4388e-05 | 3151 |  | 3312
10484 | SANTA ROSA A 1111407286 | 42151111 | SANTA ROSA A 1111 | 407286 | TRUE | 98.0196 | 98.0196 | 0.06092 | 1 | 0.00011059 | 1398 | 0.066431 | 3111 | 7.3466e-06 | 7.3466e-06 | 3152 |  | 3557
6588 | HARRIS 1108705523 | 192431108 | HARRIS 1108 | 705523 | TRUE | 1068.2355 | 321.9298 | 0.20008 | 11 | 0.00011081 | 1395 | 0.065615 | 3332 | 7.293e-06 | 8.0224e-05 | 3153 |  | 3044
3678 | RESEARCH 2102183888 | 14692102 | RESEARCH 2102 | 183888 | FALSE | 4871.8577 | 1898.9745 | 1.1802 | 43 | 0.00011047 | 1402 | 0.065447 | 3396 | 7.2344e-06 | 0.00031108 | 3154 |  | 2846
9265 | ROSSMOOR 1104892332 | 14161104 | ROSSMOOR 1104 | 892332 | TRUE | 410.223 | 410.223 | 0.25496 | 4 | 0.00010843 | 1438 | 0.066432 | 2994 | 7.2035e-06 | 2.8814e-05 | 3155 |  | 3332
5151 | EDES 1112CR312 | 13681112 | EDES 1112 | CR312 | FALSE | 5934.1286 | 5934.1286 | 3.6881 | 42 | 0.00010828 | 1446 | 0.066401 | 3119 | 7.189e-06 | 0.00030194 | 3156 | 0.12 | 1375
6055 | SILVERADO 2105191725 | 43432105 | SILVERADO 2105 | 191725 | TRUE | 766.9235 | 558.1402 | 0.34689 | 8 | 0.00010854 | 1435 | 0.066111 | 3189 | 7.1671e-06 | 5.7337e-05 | 3157 |  | 2999
8973 | DIAMOND SPRINGS 1103394169 | 152261103 | DIAMOND SPRINGS 1103 | 394169 | TRUE | 962.9958 | 642.0804 | 0.39906 | 7 | 0.00010894 | 1428 | 0.065699 | 3310 | 7.1481e-06 | 5.0037e-05 | 3158 |  | 3287
9966 | MONROE 2107380760 | 43302107 | MONROE 2107 | 380760 | FALSE | 1136.5362 | 1053.0262 | 0.65446 | 12 | 0.00010812 | 1448 | 0.066113 | 3186 | 7.1451e-06 | 8.5741e-05 | 3159 |  | 3461
2463 | OAKLAND K 1103CR188 | 12101103 | OAKLAND K 1103 | CR188 | FALSE | 5760.2047 | 5760.2047 | 3.58 | 47 | 0.00010753 | 1463 | 0.066431 | 3016 | 7.1432e-06 | 0.00033573 | 3160 | 0.38 | 960
7755 | HICKS 1116983580 | 83431116 | HICKS 1116 | 983580 | FALSE | 4036.4763 | 3958.5011 | 2.4602 | 33 | 0.00010756 | 1462 | 0.066393 | 3122 | 7.1402e-06 | 0.00023563 | 3161 |  | 3159
2292 | OAKLAND K 1104CR326 | 12101104 | OAKLAND K 1104 | CR326 | FALSE | 2098.9601 | 2098.9601 | 1.3045 | 17 | 0.00010686 | 1482 | 0.066431 | 3106 | 7.0989e-06 | 0.00012068 | 3162 | 16.75 | 337
10476 | SAN RAFAEL 1106618957 | 42011106 | SAN RAFAEL 1106 | 618957 | TRUE | 394.8447 | 301.119 | 0.18715 | 4 | 0.00010843 | 1439 | 0.065151 | 3574 | 7.0643e-06 | 2.8257e-05 | 3163 |  | 3555
3538 | CORTINA 1101302192 | 63121101 | CORTINA 1101 | 302192 | TRUE | 22573.2133 | 0 | 0 | 79 | 0.00010836 | 1443 | 0.065152 | 3561 | 7.0599e-06 | 0.00055773 | 3164 | 0.74 | 793
3533 | OAKLAND K 1104432850 | 12101104 | OAKLAND K 1104 | 432850 | FALSE | 1988.3274 | 1988.3274 | 1.2358 | 26 | 0.0001052 | 1514 | 0.066431 | 3017 | 6.9884e-06 | 0.0001817 | 3165 |  | 2834
9797 | DEL MONTE 21032204 | 182222103 | DEL MONTE 2103 | 2204 | TRUE | 592.6413 | 592.6413 | 0.36833 | 8 | 0.00010504 | 1526 | 0.066432 | 2980 | 6.9782e-06 | 5.5825e-05 | 3166 | 0.04 | 2073
10205 | BERKELEY F 1103813976 | 12061103 | BERKELEY F 1103 | 813976 | TRUE | 328.1808 | 312.2978 | 0.19409 | 4 | 0.00010513 | 1520 | 0.066111 | 3194 | 6.9422e-06 | 2.7769e-05 | 3167 |  | 3515
398 | ROSSMOOR 1104CB | 14161104 | ROSSMOOR 1104 | CB | TRUE | 17820.8713 | 0 | 0 | 150 | 0.00010626 | 1491 | 0.065148 | 3591 | 6.9228e-06 | 0.0010384 | 3168 |  | 2669
465 | MOLINO 1102111666 | 42571102 | MOLINO 1102 | 111666 | TRUE | 1605.5548 | 182.6023 | 0.11349 | 13 | 0.00010584 | 1499 | 0.06525 | 3479 | 6.9214e-06 | 8.9978e-05 | 3169 |  | 2676
9817 | SUMMIT 11016627 | 152591101 | SUMMIT 1101 | 6627 | TRUE | 910.3808 | 910.3808 | 0.56581 | 8 | 0.00010404 | 1550 | 0.066431 | 3048 | 6.9114e-06 | 5.5291e-05 | 3170 | 0.03 | 2267
6657 | SAN RAFAEL 110168970 | 42011101 | SAN RAFAEL 1101 | 68970 | TRUE | 5207.2001 | 75.6257 | 0.047002 | 44 | 0.00010579 | 1501 | 0.065151 | 3565 | 6.892e-06 | 0.00030325 | 3171 | 0.08 | 1617
8713 | GANSNER 1101489276 | 103021101 | GANSNER 1101 | 489276 | TRUE | 1058.1278 | 723.7002 | 0.44978 | 9 | 0.00010344 | 1561 | 0.066147 | 3182 | 6.8546e-06 | 6.1691e-05 | 3172 |  | 3253
6405 | ROB ROY 210571630 | 83692105 | ROB ROY 2105 | 71630 | FALSE | 3041.9597 | 2182.1843 | 1.3562 | 26 | 0.00010295 | 1569 | 0.066037 | 3211 | 6.8241e-06 | 0.00017743 | 3173 | 0.21 | 1143
1284 | SARATOGA 1106LC22 | 83371106 | SARATOGA 1106 | LC22 | FALSE | 13269.3389 | 12038.7869 | 7.4822 | 114 | 0.0001028 | 1575 | 0.066274 | 3155 | 6.8223e-06 | 0.00077774 | 3174 | 0.08 | 1600
4762 | SAN RAFAEL 110668694 | 42011106 | SAN RAFAEL 1106 | 68694 | TRUE | 3377.3751 | 0 | 0 | 32 | 0.00010397 | 1554 | 0.065151 | 3573 | 6.7736e-06 | 0.00021675 | 3175 |  | 2914
9002 | PAUL SWEET 2102168368 | 83252102 | PAUL SWEET 2102 | 168368 | TRUE | 1090.7031 | 590.4471 | 0.36697 | 8 | 0.00010339 | 1562 | 0.065308 | 3460 | 6.7491e-06 | 5.3993e-05 | 3176 |  | 3294
8371 | RINCON 1102782389 | 43321102 | RINCON 1102 | 782389 | TRUE | 861.6016 | 585.9597 | 0.36418 | 8 | 0.00010151 | 1617 | 0.065955 | 3232 | 6.7151e-06 | 5.3721e-05 | 3177 |  | 3216
7829 | UKIAH 111472990 | 42771114 | UKIAH 1114 | 72990 | FALSE | 5262.4562 | 1175.6663 | 0.73068 | 38 | 0.00010233 | 1594 | 0.065487 | 3374 | 6.7147e-06 | 0.00025516 | 3178 | 0.03 | 2293
4895 | SARATOGA 1103LC16 | 83371103 | SARATOGA 1103 | LC16 | FALSE | 8170.2082 | 6889.2884 | 4.2817 | 72 | 0.00010102 | 1624 | 0.066218 | 3168 | 6.7061e-06 | 0.00048284 | 3179 | 0.17 | 1248
2902 | WAYNE 0401954811 | 13810401 | WAYNE 0401 | 954811 | TRUE | 903.9347 | 282.8935 | 0.17582 | 9 | 0.00010244 | 1591 | 0.065576 | 3345 | 6.7055e-06 | 6.0349e-05 | 3180 |  | 2805
6002 | SAN RAFAEL 1105818262 | 42011105 | SAN RAFAEL 1105 | 818262 | TRUE | 1433.202 | 292.9133 | 0.18205 | 11 | 0.00010153 | 1615 | 0.0655 | 3368 | 6.6573e-06 | 7.3231e-05 | 3181 |  | 2994
9719 | PIT NO 5 11011614 | 101321101 | PIT NO 5 1101 | 1614 | FALSE | 3000.4112 | 3000.4112 | 1.8648 | 5 | 0.00010012 | 1643 | 9.5753 | 2631 | 6.6513e-06 | 3.3257e-05 | 3182 | 0.01 | 2585
5122 | RIDGE 0401CB | 12840401 | RIDGE 0401 | CB | FALSE | 4270.3121 | 4270.3121 | 2.654 | 36 | 0.00010003 | 1646 | 0.066396 | 3120 | 6.6432e-06 | 0.00023916 | 3183 | 0.08 | 1628
1193 | FORT BRAGG A 1102418 | 42761102 | FORT BRAGG A 1102 | 418 | FALSE | 22746.3302 | 22539.2945 | 14.0083 | 178 | 9.9716e-05 | 1655 | 0.066381 | 3126 | 6.6205e-06 | 0.0011785 | 3184 | 0.17 | 1236
8138 | FRANKLIN 1101P138 | 13921101 | FRANKLIN 1101 | P138 | FALSE | 2470.0232 | 2259.003 | 1.404 | 15 | 9.8986e-05 | 1670 | 0.066089 | 3200 | 6.5684e-06 | 9.8527e-05 | 3185 | 0.04 | 2093
11032 | HIGHLANDS 1101CB | 43361101 | HIGHLANDS 1101 | CB | TRUE | 42.5019 | 42.5019 | 0.026415 | 1 | 9.8387e-05 | 1681 | 0.066432 | 2999 | 6.536e-06 | 6.536e-06 | 3186 | 0.03 | 2336
3671 | CAMP EVERS 2104CB | 83622104 | CAMP EVERS 2104 | CB | TRUE | 5967.294 | 629.206 | 0.39105 | 71 | 9.9922e-05 | 1649 | 0.065224 | 3498 | 6.5265e-06 | 0.00046338 | 3187 | 0.18 | 1209
8113 | WOODSIDE 110411555 | 24251104 | WOODSIDE 1104 | 11555 | FALSE | 1379.9837 | 1379.9837 | 0.85767 | 11 | 9.8049e-05 | 1688 | 0.066432 | 2976 | 6.5136e-06 | 7.165e-05 | 3188 | 0.16 | 1271
8611 | CAROLANDS 04018888 | 24060401 | CAROLANDS 0401 | 8888 | TRUE | 2206.3607 | 0 | 0 | 25 | 9.99e-05 | 1651 | 0.065147 | 3614 | 6.5082e-06 | 0.0001627 | 3189 |  | 3244
10705 | CLOVERDALE 1102801904 | 42821102 | CLOVERDALE 1102 | 801904 | TRUE | 22.3881 | 22.3881 | 0.013914 | 1 | 8.2208e-05 | 2146 | 0.079148 | 2934 | 6.5066e-06 | 6.5066e-06 | 3190 | 0.06 | 1865
7620 | CASTRO VALLEY 1110MR341 | 14091110 | CASTRO VALLEY 1110 | MR341 | TRUE | 1045.185 | 417.225 | 0.25931 | 11 | 9.8401e-05 | 1680 | 0.065731 | 3300 | 6.5027e-06 | 7.1529e-05 | 3191 |  | 3142
6399 | ROB ROY 21049973 | 83692104 | ROB ROY 2104 | 9973 | TRUE | 921.5182 | 921.5182 | 0.57273 | 7 | 9.7761e-05 | 1697 | 0.066431 | 3072 | 6.4944e-06 | 4.5461e-05 | 3192 |  | 3027
4710 | VIEJO 220255787 | 182852202 | VIEJO 2202 | 55787 | TRUE | 58.9251 | 58.9251 | 0.036622 | 1 | 9.7709e-05 | 1699 | 0.066432 | 2989 | 6.491e-06 | 6.491e-06 | 3193 | 0.05 | 2023
3931 | LAS AROMAS 04013342 | 13600401 | LAS AROMAS 0401 | 3342 | FALSE | 3691.7497 | 3691.7497 | 2.2944 | 30 | 9.6371e-05 | 1724 | 0.066431 | 3097 | 6.402e-06 | 0.00019206 | 3194 | 0.04 | 2113
738 | SAN RAFAEL 1104CB | 42011104 | SAN RAFAEL 1104 | CB | FALSE | 16824.5332 | 5560.2483 | 3.4557 | 140 | 9.7183e-05 | 1710 | 0.065554 | 3352 | 6.3852e-06 | 0.00089393 | 3195 | 0.06 | 1789
9201 | HICKS 1116583284 | 83431116 | HICKS 1116 | 583284 | TRUE | 404.4133 | 236.5766 | 0.14703 | 4 | 9.5521e-05 | 1741 | 0.066111 | 3197 | 6.3368e-06 | 2.5347e-05 | 3196 |  | 3325
7050 | EAST QUINCY 1101678650 | 102551101 | EAST QUINCY 1101 | 678650 | FALSE | 2024.9152 | 1808.9819 | 1.1243 | 14 | 9.5259e-05 | 1757 | 0.066065 | 3203 | 6.2788e-06 | 8.7903e-05 | 3197 |  | 3091
9107 | OAKLAND K 1103CR422 | 12101103 | OAKLAND K 1103 | CR422 | FALSE | 3299.6109 | 3238.2816 | 2.0126 | 24 | 9.4398e-05 | 1783 | 0.066378 | 3128 | 6.2703e-06 | 0.00015049 | 3198 | 0.06 | 1855
2296 | LAURELES 11112028 | 182371111 | LAURELES 1111 | 2028 | FALSE | 14061.7847 | 14048.0686 | 8.7309 | 107 | 9.4213e-05 | 1788 | 0.06642 | 3114 | 6.2585e-06 | 0.00066966 | 3199 | 0.05 | 2036
4668 | KONOCTI 11084041 | 43311108 | KONOCTI 1108 | 4041 | FALSE | 7568.2918 | 2174.4689 | 1.3514 | 54 | 9.5438e-05 | 1746 | 0.065458 | 3394 | 6.2484e-06 | 0.00033741 | 3200 | 0.04 | 2187
4517 | SILVERADO 2105CB | 43432105 | SILVERADO 2105 | CB | FALSE | 7432.6484 | 1011.6246 | 0.62873 | 66 | 9.5309e-05 | 1754 | 0.065326 | 3450 | 6.2313e-06 | 0.00041127 | 3201 | 0.17 | 1235
1407 | SAN RAFAEL 11061230 | 42011106 | SAN RAFAEL 1106 | 1230 | FALSE | 7038.4432 | 1747.5573 | 1.0861 | 57 | 9.4865e-05 | 1770 | 0.065398 | 3418 | 6.2233e-06 | 0.00035473 | 3202 | 0.02 | 2465
7332 | LOS GATOS 1101184035 | 82021101 | LOS GATOS 1101 | 184035 | TRUE | 995.7775 | 905.936 | 0.56304 | 9 | 9.1457e-05 | 1859 | 0.066289 | 3152 | 6.0721e-06 | 5.4649e-05 | 3203 |  | 3118
10579 | SAN CARLOS 11049048 | 24181104 | SAN CARLOS 1104 | 9048 | TRUE | 24.5909 | 24.5909 | 0.015283 | 1 | 9.1221e-05 | 1871 | 0.066432 | 2958 | 6.06e-06 | 6.06e-06 | 3204 | 0.06 | 1869
2032 | LUCERNE 11031663 | 43351103 | LUCERNE 1103 | 1663 | FALSE | 1947.6462 | 1947.6462 | 1.2105 | 17 | 9.1109e-05 | 1877 | 0.066432 | 3000 | 6.0525e-06 | 0.00010289 | 3205 | 0.08 | 1656
9700 | SAN RAMON 2103MR279 | 14232103 | SAN RAMON 2103 | MR279 | TRUE | 323.7748 | 4.572 | 0.0028415 | 5 | 9.2277e-05 | 1836 | 0.065405 | 3413 | 6.0521e-06 | 3.0261e-05 | 3206 |  | 3402
5325 | SAN RAFAEL 1105534 | 42011105 | SAN RAFAEL 1105 | 534 | FALSE | 2541.7011 | 1569.6662 | 0.97555 | 22 | 9.1303e-05 | 1866 | 0.065908 | 3243 | 6.0384e-06 | 0.00013284 | 3207 | 0.08 | 1668
8122 | HATTON 1101CB | 182291101 | HATTON 1101 | CB | FALSE | 2551.5911 | 2551.5911 | 1.5858 | 22 | 9.066e-05 | 1892 | 0.066432 | 2986 | 6.0227e-06 | 0.0001325 | 3208 | 0.07 | 1703
6886 | ALTO 1124526955 | 42031124 | ALTO 1124 | 526955 | TRUE | 753.5469 | 713.9611 | 0.44373 | 6 | 9.0519e-05 | 1897 | 0.066431 | 3022 | 6.0133e-06 | 3.608e-05 | 3209 |  | 3070
5909 | CAMP EVERS 210392582 | 83622103 | CAMP EVERS 2103 | 92582 | TRUE | 4514.9648 | 245.7655 | 0.15274 | 41 | 9.2095e-05 | 1840 | 0.065147 | 3619 | 5.9997e-06 | 0.00024599 | 3210 | 0.07 | 1704
6632 | SAN RAFAEL 1106588020 | 42011106 | SAN RAFAEL 1106 | 588020 | TRUE | 2885.7528 | 385.2385 | 0.23943 | 19 | 9.1832e-05 | 1849 | 0.065219 | 3500 | 5.9904e-06 | 0.00011382 | 3211 |  | 3050
763 | LOS GATOS 1108LB86 | 82021108 | LOS GATOS 1108 | LB86 | FALSE | 8620.4875 | 7270.7679 | 4.5188 | 69 | 8.9584e-05 | 1927 | 0.066208 | 3169 | 5.9458e-06 | 0.00041026 | 3212 | 0.13 | 1335
10570 | EL CERRITO G 1105BR164 | 12501105 | EL CERRITO G 1105 | BR164 | TRUE | 91.5845 | 91.5845 | 0.05692 | 2 | 8.9373e-05 | 1935 | 0.066432 | 2968 | 5.9372e-06 | 1.1874e-05 | 3213 | 0.05 | 1944
9932 | ALTO 1125291744 | 42031125 | ALTO 1125 | 291744 | TRUE | 231.1314 | 195.7909 | 0.12168 | 3 | 9.0072e-05 | 1908 | 0.066004 | 3218 | 5.9276e-06 | 1.7783e-05 | 3214 |  | 3455
8178 | DOLAN ROAD 1101156268 | 182381101 | DOLAN ROAD 1101 | 156268 | TRUE | 3622.1133 | 52.7453 | 0.032781 | 31 | 9.074e-05 | 1891 | 0.065189 | 3522 | 5.914e-06 | 0.00018333 | 3215 |  | 3199
6600 | VIEJO 2202CB | 182852202 | VIEJO 2202 | CB | FALSE | 3450.2108 | 3450.2108 | 2.1443 | 23 | 8.8928e-05 | 1953 | 0.066432 | 2985 | 5.9077e-06 | 0.00013588 | 3216 | 1.33 | 684
4067 | LAS AROMAS 0401LA401R | 13600401 | LAS AROMAS 0401 | LA401R | FALSE | 6369.4185 | 4956.3951 | 3.0804 | 55 | 8.9288e-05 | 1939 | 0.066129 | 3184 | 5.9068e-06 | 0.00032487 | 3217 | 0.06 | 1827
807 | RESEARCH 210263274 | 14692102 | RESEARCH 2102 | 63274 | TRUE | 13077.1161 | 74.3652 | 0.046218 | 119 | 8.9998e-05 | 1914 | 0.06516 | 3555 | 5.8646e-06 | 0.00069789 | 3218 | 1.68 | 654
10104 | LAKEWOOD 1102964292 | 13531102 | LAKEWOOD 1102 | 964292 | TRUE | 128.1599 | 128.1599 | 0.079652 | 2 | 8.8164e-05 | 1978 | 0.066432 | 2995 | 5.8569e-06 | 1.1714e-05 | 3219 |  | 3491
8987 | ROSSMOOR 110181770 | 14161101 | ROSSMOOR 1101 | 81770 | TRUE | 2254.8682 | 110.4225 | 0.068628 | 21 | 8.9058e-05 | 1945 | 0.065148 | 3588 | 5.8019e-06 | 0.00012184 | 3220 |  | 3289
9943 | FRANKLIN 1104P136 | 13921104 | FRANKLIN 1104 | P136 | FALSE | 9489.9011 | 7931.4997 | 4.9295 | 43 | 8.0523e-05 | 2191 | 0.07255 | 2940 | 5.7997e-06 | 0.00024939 | 3221 | 0.03 | 2269
9679 | DOBBINS 1101CB | 153741101 | DOBBINS 1101 | CB | FALSE | 1079.0936 | 1079.0936 | 0.67066 | 8 | 8.7249e-05 | 2007 | 0.066432 | 3012 | 5.7961e-06 | 4.6369e-05 | 3222 | 0.06 | 1836
734 | SILVERADO 21051308 | 43432105 | SILVERADO 2105 | 1308 | TRUE | 7407.352 | 244.9631 | 0.15225 | 60 | 8.8597e-05 | 1969 | 0.065216 | 3502 | 5.7874e-06 | 0.00034724 | 3223 | 8.14 | 435
5907 | ORINDA 0401401/2 LR | 12350401 | ORINDA 0401 | 401/2 LR | TRUE | 235.881 | 158.249 | 0.098352 | 4 | 8.7563e-05 | 1998 | 0.066112 | 3187 | 5.7731e-06 | 2.3093e-05 | 3224 |  | 2987
648 | KONOCTI 11084039 | 43311108 | KONOCTI 1108 | 4039 | FALSE | 3724.1919 | 3048.4169 | 1.8946 | 32 | 8.7081e-05 | 2010 | 0.066191 | 3171 | 5.7609e-06 | 0.00018435 | 3225 | 0.06 | 1903
5547 | KONOCTI 11084037 | 43311108 | KONOCTI 1108 | 4037 | FALSE | 2780.393 | 1840.2464 | 1.1437 | 22 | 8.7734e-05 | 1991 | 0.065616 | 3331 | 5.7543e-06 | 0.0001266 | 3226 | 0.04 | 2149
3274 | RACETRACK 170310850 | 163761703 | RACETRACK 1703 | 10850 | TRUE | 3044.0072 | 994.8842 | 0.61832 | 28 | 8.6545e-05 | 2022 | 0.065652 | 3324 | 5.704e-06 | 0.00015971 | 3227 | 0.04 | 2091
5740 | SUMMIT 110148636 | 152591101 | SUMMIT 1101 | 48636 | TRUE | 4495.7291 | 86.4222 | 0.053712 | 38 | 8.7238e-05 | 2008 | 0.065185 | 3527 | 5.6861e-06 | 0.00021607 | 3228 | 0.01 | 2615
8762 | VASONA 1102944560 | 83771102 | VASONA 1102 | 944560 | TRUE | 944.5774 | 282.6401 | 0.17566 | 9 | 8.6599e-05 | 2020 | 0.065433 | 3404 | 5.6635e-06 | 5.0971e-05 | 3229 |  | 3260
5538 | BERKELEY F 1103162952 | 12061103 | BERKELEY F 1103 | 162952 | FALSE | 3475.2506 | 2846.7585 | 1.7693 | 25 | 8.5367e-05 | 2045 | 0.066175 | 3178 | 5.6583e-06 | 0.00014146 | 3230 |  | 2962
319 | DUNBAR 1103725292 | 43071103 | DUNBAR 1103 | 725292 | TRUE | 1519.9145 | 339.5862 | 0.21105 | 13 | 8.6305e-05 | 2027 | 0.065451 | 3395 | 5.658e-06 | 7.3554e-05 | 3231 |  | 2665
5356 | SOBRANTE 110142914 | 14671101 | SOBRANTE 1101 | 42914 | TRUE | 6917.2252 | 665.6425 | 0.4137 | 51 | 8.6589e-05 | 2021 | 0.065332 | 3443 | 5.6577e-06 | 0.00028854 | 3232 | 0.03 | 2387
4656 | OAKLAND K 1104CR208 | 12101104 | OAKLAND K 1104 | CR208 | FALSE | 3895.4111 | 3895.4111 | 2.421 | 29 | 8.498e-05 | 2061 | 0.066431 | 3052 | 5.6453e-06 | 0.00016371 | 3233 | 0.19 | 1185
1498 | SAN RAFAEL 1101189400 | 42011101 | SAN RAFAEL 1101 | 189400 | FALSE | 5552.3042 | 4446.7436 | 2.7637 | 45 | 8.4949e-05 | 2063 | 0.066033 | 3212 | 5.6305e-06 | 0.00025337 | 3234 |  | 2728
9302 | NEWBURG 1131987158 | 192151131 | NEWBURG 1131 | 987158 | TRUE | 443.4139 | 397.6831 | 0.24716 | 2 | 8.4891e-05 | 2066 | 0.06579 | 3277 | 5.6215e-06 | 1.1243e-05 | 3235 |  | 3339
1260 | PALO SECO 0401CB | 13180401 | PALO SECO 0401 | CB | FALSE | 7634.7258 | 7634.7258 | 4.745 | 55 | 8.4537e-05 | 2075 | 0.066409 | 3116 | 5.6154e-06 | 0.00030885 | 3236 | 0.16 | 1263
7087 | OAKLAND K 1101CR170 | 12101101 | OAKLAND K 1101 | CR170 | FALSE | 2012.9175 | 2012.9175 | 1.251 | 17 | 8.3822e-05 | 2100 | 0.066432 | 2973 | 5.5684e-06 | 9.4663e-05 | 3237 | 0.21 | 1138
9325 | TASSAJARA 2108189700 | 14662108 | TASSAJARA 2108 | 189700 | TRUE | 2164.8558 | 306.7254 | 0.19063 | 22 | 8.5054e-05 | 2057 | 0.065265 | 3473 | 5.5512e-06 | 0.00012213 | 3238 |  | 3343
8529 | ROSSMOOR 110479146 | 14161104 | ROSSMOOR 1104 | 79146 | TRUE | 3115.0804 | 85.6157 | 0.05321 | 28 | 8.3512e-05 | 2114 | 0.065194 | 3514 | 5.451e-06 | 0.00015263 | 3239 | 0.02 | 2490
5159 | PAUL SWEET 2109634576 | 83252109 | PAUL SWEET 2109 | 634576 | FALSE | 3306.7049 | 2935.0444 | 1.8241 | 29 | 8.2017e-05 | 2152 | 0.066255 | 3159 | 5.4462e-06 | 0.00015794 | 3240 |  | 2939
176 | TASSAJARA 2108D520R | 14662108 | TASSAJARA 2108 | D520R | TRUE | 5652.8623 | 0 | 0 | 50 | 8.3586e-05 | 2109 | 0.065148 | 3583 | 5.4455e-06 | 0.00027228 | 3241 |  | 2659
2934 | LAKEWOOD 210769586 | 13532107 | LAKEWOOD 2107 | 69586 | TRUE | 9651.4745 | 688.9218 | 0.42817 | 80 | 8.3471e-05 | 2116 | 0.065228 | 3492 | 5.4423e-06 | 0.00043538 | 3242 | 0.02 | 2429
2160 | HIGHLANDS 1104CB | 43361104 | HIGHLANDS 1104 | CB | FALSE | 13332.3504 | 7661.9306 | 4.7619 | 102 | 7.7932e-05 | 2261 | 0.072303 | 2941 | 5.4342e-06 | 0.00055429 | 3243 | 0.07 | 1735
7487 | GANSNER 1101174072 | 103021101 | GANSNER 1101 | 174072 | TRUE | 172.7033 | 172.7033 | 0.10734 | 3 | 8.1758e-05 | 2162 | 0.066004 | 3219 | 5.3939e-06 | 1.6182e-05 | 3244 |  | 3129
10550 | SANTA ROSA A 1104834094 | 42151104 | SANTA ROSA A 1104 | 834094 | TRUE | 201.2345 | 155.4829 | 0.096633 | 3 | 8.2e-05 | 2155 | 0.065582 | 3337 | 5.3913e-06 | 1.6174e-05 | 3245 |  | 3572
6137 | CAROLANDS 04049024 | 24060404 | CAROLANDS 0404 | 9024 | FALSE | 6139.1912 | 5646.8015 | 3.5095 | 62 | 8.1167e-05 | 2180 | 0.066328 | 3141 | 5.3873e-06 | 0.00033401 | 3246 | 0.12 | 1406
8307 | SAN RAFAEL 11042235 | 42011104 | SAN RAFAEL 1104 | 2235 | TRUE | 1389.3312 | 296.6637 | 0.18438 | 10 | 8.163e-05 | 2164 | 0.065407 | 3411 | 5.3477e-06 | 5.3477e-05 | 3247 | 0.03 | 2392
4970 | CASTRO VALLEY 1110264914 | 14091110 | CASTRO VALLEY 1110 | 264914 | FALSE | 1490.2678 | 1396.6171 | 0.868 | 14 | 8.0285e-05 | 2197 | 0.066248 | 3164 | 5.3219e-06 | 7.4507e-05 | 3248 |  | 2934
6336 | SAN RAFAEL 1101310 | 42011101 | SAN RAFAEL 1101 | 310 | TRUE | 5801.4081 | 319.7974 | 0.19876 | 48 | 8.1312e-05 | 2173 | 0.065285 | 3466 | 5.3143e-06 | 0.00025509 | 3249 | 0.63 | 836
5625 | LAURELES 11116617 | 182371111 | LAURELES 1111 | 6617 | FALSE | 2923.677 | 2923.677 | 1.8171 | 13 | 7.8082e-05 | 2257 | 0.068388 | 2946 | 5.304e-06 | 6.8952e-05 | 3250 | 1.03 | 726
4819 | GANSNER 1101590690 | 103021101 | GANSNER 1101 | 590690 | TRUE | 383.2694 | 102.0304 | 0.063412 | 4 | 8.1235e-05 | 2176 | 0.065148 | 3587 | 5.2923e-06 | 2.1169e-05 | 3251 |  | 2919
3357 | TASSAJARA 210812712 | 14662108 | TASSAJARA 2108 | 12712 | FALSE | 5357.9341 | 1227.8521 | 0.76312 | 46 | 8.0658e-05 | 2189 | 0.065483 | 3376 | 5.2813e-06 | 0.00024294 | 3252 | 10.37 | 397
4164 | ELK 11014628 | 42981101 | ELK 1101 | 4628 | FALSE | 6688.9793 | 3975.7324 | 2.4709 | 54 | 7.9821e-05 | 2212 | 0.065813 | 3262 | 5.2551e-06 | 0.00028378 | 3253 | 0.03 | 2361
5329 | ROSSMOOR 1106L522R | 14161106 | ROSSMOOR 1106 | L522R | FALSE | 6797.2077 | 3031.8636 | 1.8843 | 56 | 7.9525e-05 | 2221 | 0.065744 | 3296 | 5.255e-06 | 0.00029428 | 3254 | 1.17 | 704
10811 | STAFFORD 1101803535 | 43201101 | STAFFORD 1101 | 803535 | TRUE | 262.4984 | 262.4984 | 0.16314 | 3 | 7.8567e-05 | 2247 | 0.066431 | 3038 | 5.2193e-06 | 1.5658e-05 | 3255 |  | 3608
7133 | DEL MONTE 21032000 | 182222103 | DEL MONTE 2103 | 2000 | FALSE | 14495.3301 | 14495.3301 | 9.0089 | 101 | 7.8422e-05 | 2249 | 0.066432 | 2979 | 5.2097e-06 | 0.00052618 | 3256 | 0.12 | 1391
5982 | SAN RAFAEL 1107434 | 42011107 | SAN RAFAEL 1107 | 434 | TRUE | 1839.9407 | 49.2215 | 0.030591 | 16 | 7.9657e-05 | 2216 | 0.065231 | 3489 | 5.2024e-06 | 8.3238e-05 | 3257 |  | 2993
7562 | IGNACIO 1105784032 | 42481105 | IGNACIO 1105 | 784032 | TRUE | 974.4826 | 863.751 | 0.53682 | 11 | 7.8303e-05 | 2251 | 0.066199 | 3170 | 5.1906e-06 | 5.7096e-05 | 3258 |  | 3137
4422 | ROSSMOOR 1106CB | 14161106 | ROSSMOOR 1106 | CB | FALSE | 7735.7733 | 2937.1415 | 1.8254 | 60 | 7.5124e-05 | 2330 | 1.6497 | 2856 | 5.1594e-06 | 0.00030957 | 3259 | 0.22 | 1133
788 | OAKLAND K 1104CR210 | 12101104 | OAKLAND K 1104 | CR210 | FALSE | 4546.547 | 4546.547 | 2.8257 | 35 | 7.7661e-05 | 2270 | 0.066431 | 3091 | 5.1591e-06 | 0.00018057 | 3260 | 0.14 | 1309
5398 | HARTLEY 1101471 | 43211101 | HARTLEY 1101 | 471 | TRUE | 2001.813 | 0 | 0 | 16 | 7.9063e-05 | 2233 | 0.06523 | 3491 | 5.1543e-06 | 8.2468e-05 | 3261 | 0.33 | 988
3021 | SAN RAFAEL 1101494 | 42011101 | SAN RAFAEL 1101 | 494 | FALSE | 14793.4066 | 9034.9185 | 5.6152 | 114 | 7.7057e-05 | 2285 | 0.06596 | 3230 | 5.1065e-06 | 0.00058215 | 3262 | 0.23 | 1112
2946 | WOODSIDE 11049116 | 24251104 | WOODSIDE 1104 | 9116 | FALSE | 6878.1556 | 1335.9769 | 0.83032 | 53 | 7.7353e-05 | 2280 | 0.065341 | 3442 | 5.0499e-06 | 0.00026765 | 3263 | 0.08 | 1597
8964 | MARIPOSA 2102527766 | 254452102 | MARIPOSA 2102 | 527766 | TRUE | 66.9649 | 66.9649 | 0.041619 | 1 | 7.5879e-05 | 2310 | 0.066432 | 2954 | 5.0408e-06 | 5.0408e-06 | 3264 |  | 3285
8147 | LAS GALLINAS A 1105648439 | 42991105 | LAS GALLINAS A 1105 | 648439 | TRUE | 225.8757 | 10.9115 | 0.0067816 | 3 | 7.7251e-05 | 2281 | 0.065151 | 3571 | 5.033e-06 | 1.5099e-05 | 3265 |  | 3196
6797 | EMERALD LAKE 04028858 | 24080402 | EMERALD LAKE 0402 | 8858 | FALSE | 3073.6226 | 3073.6226 | 1.9103 | 27 | 7.5167e-05 | 2327 | 0.066432 | 2966 | 4.9935e-06 | 0.00013482 | 3266 | 0.08 | 1631
8050 | BIG RIVER 11015065 | 43081101 | BIG RIVER 1101 | 5065 | FALSE | 3543.5774 | 3543.5774 | 2.2023 | 27 | 7.4898e-05 | 2334 | 0.066432 | 2987 | 4.9756e-06 | 0.00013434 | 3267 | 0.1 | 1465
6040 | RACETRACK 17032553 | 163761703 | RACETRACK 1703 | 2553 | FALSE | 3992.3117 | 1548.3173 | 0.96229 | 32 | 7.5372e-05 | 2324 | 0.065669 | 3318 | 4.9535e-06 | 0.00015851 | 3268 | 0.05 | 2058
4959 | VALLEY VIEW 1105305072 | 14341105 | VALLEY VIEW 1105 | 305072 | FALSE | 6216.8943 | 5044.0425 | 3.1349 | 45 | 7.4673e-05 | 2341 | 0.066118 | 3185 | 4.9532e-06 | 0.0002229 | 3269 |  | 2933
1675 | CASTRO VALLEY 1111227862 | 14091111 | CASTRO VALLEY 1111 | 227862 | TRUE | 2810.7104 | 319.3369 | 0.19847 | 26 | 7.5864e-05 | 2311 | 0.065246 | 3481 | 4.952e-06 | 0.00012875 | 3270 |  | 2736
9676 | PACIFICA 1103885952 | 22811103 | PACIFICA 1103 | 885952 | TRUE | 299.4502 | 283.4481 | 0.17616 | 4 | 7.3952e-05 | 2360 | 0.066111 | 3195 | 4.9074e-06 | 1.963e-05 | 3271 |  | 3397
8421 | EL CERRITO G 1112779030 | 12501112 | EL CERRITO G 1112 | 779030 | TRUE | 1061.942 | 827.4759 | 0.51428 | 11 | 7.3516e-05 | 2383 | 0.066315 | 3145 | 4.881e-06 | 5.3691e-05 | 3272 |  | 3224
2317 | VACAVILLE 1112CB | 63601112 | VACAVILLE 1112 | CB | TRUE | 5313.0282 | 378.608 | 0.23531 | 52 | 7.4297e-05 | 2349 | 0.065199 | 3510 | 4.847e-06 | 0.00025204 | 3273 |  | 2771
2187 | NEWBURG 1131CB | 192151131 | NEWBURG 1131 | CB | TRUE | 10978.5428 | 257.3233 | 0.15993 | 91 | 7.4003e-05 | 2358 | 0.2391 | 2928 | 4.8414e-06 | 0.00044057 | 3274 | 0.04 | 2111
8107 | EMERALD LAKE 0402CB | 24080402 | EMERALD LAKE 0402 | CB | FALSE | 3052.0291 | 3052.0291 | 1.8968 | 23 | 7.2318e-05 | 2409 | 0.066432 | 2962 | 4.8042e-06 | 0.0001105 | 3275 | 0.1 | 1457
1133 | SAN CARLOS 1103586832 | 24181103 | SAN CARLOS 1103 | 586832 | FALSE | 6692.9945 | 6145.6408 | 3.8195 | 53 | 7.2377e-05 | 2406 | 0.066311 | 3146 | 4.7995e-06 | 0.00025437 | 3276 |  | 2711
9839 | SAN RAFAEL 11073323 | 42011107 | SAN RAFAEL 1107 | 3323 | TRUE | 214.7286 | 214.7286 | 0.13345 | 2 | 7.1735e-05 | 2429 | 0.066431 | 3042 | 4.7655e-06 | 9.5309e-06 | 3277 | 0.27 | 1051
3598 | PAUL SWEET 210210290 | 83252102 | PAUL SWEET 2102 | 10290 | TRUE | 9277.251 | 4.572 | 0.0028415 | 75 | 7.2679e-05 | 2399 | 0.065164 | 3550 | 4.7388e-06 | 0.00035541 | 3278 |  | 2841
4237 | PAUL SWEET 2109687295 | 83252109 | PAUL SWEET 2109 | 687295 | FALSE | 1495.545 | 1495.545 | 0.92949 | 14 | 7.0919e-05 | 2445 | 0.066432 | 2963 | 4.7113e-06 | 6.5958e-05 | 3279 |  | 2878
4104 | GREENBRAE 1103CB | 43091103 | GREENBRAE 1103 | CB | TRUE | 6661.6605 | 0 | 0 | 61 | 7.201e-05 | 2419 | 0.065151 | 3564 | 4.6915e-06 | 0.00028618 | 3280 | 0.11 | 1448
9040 | SAN RAFAEL 1101CB | 42011101 | SAN RAFAEL 1101 | CB | TRUE | 1531.5459 | 0 | 0 | 17 | 7.1938e-05 | 2422 | 0.065151 | 3566 | 4.6868e-06 | 7.9676e-05 | 3281 | 0.25 | 1083
9787 | ATASCADERO 1103395936 | 182541103 | ATASCADERO 1103 | 395936 | TRUE | 1081.2511 | 685.7662 | 0.42621 | 6 | 7.0765e-05 | 2449 | 0.066004 | 3222 | 4.6656e-06 | 2.7994e-05 | 3282 |  | 3422
3209 | ROB ROY 210512474 | 83692105 | ROB ROY 2105 | 12474 | FALSE | 13789.0355 | 5487.3001 | 3.4104 | 105 | 7.0779e-05 | 2448 | 0.065612 | 3333 | 4.6505e-06 | 0.00048831 | 3283 | 0.04 | 2152
10084 | SAN RAFAEL 1106307651 | 42011106 | SAN RAFAEL 1106 | 307651 | TRUE | 416.3767 | 169.0436 | 0.10506 | 4 | 7.1015e-05 | 2444 | 0.065151 | 3569 | 4.6267e-06 | 1.8507e-05 | 3284 |  | 3486
8574 | BIG RIVER 1101262924 | 43081101 | BIG RIVER 1101 | 262924 | FALSE | 3139.8868 | 3032.2865 | 1.8846 | 30 | 6.9614e-05 | 2485 | 0.066389 | 3125 | 4.6224e-06 | 0.00013867 | 3285 |  | 3238
9375 | BIG MEADOWS 2101439 | 102812101 | BIG MEADOWS 2101 | 439 | FALSE | 1501.1745 | 1069.2533 | 0.66455 | 12 | 7.0104e-05 | 2470 | 0.066111 | 3191 | 4.6178e-06 | 5.5413e-05 | 3286 | 1.58 | 664
10457 | ALTO 1124319320 | 42031124 | ALTO 1124 | 319320 | TRUE | 221.6252 | 210.6172 | 0.1309 | 3 | 7.001e-05 | 2472 | 0.065578 | 3340 | 4.6148e-06 | 1.3844e-05 | 3287 |  | 3552
9137 | BERKELEY F 1103620294 | 12061103 | BERKELEY F 1103 | 620294 | TRUE | 312.2722 | 249.6637 | 0.15517 | 4 | 7.0122e-05 | 2469 | 0.065468 | 3388 | 4.6109e-06 | 1.8443e-05 | 3288 |  | 3315
10199 | SALT SPRINGS 21023116 | 163692102 | SALT SPRINGS 2102 | 3116 | TRUE | 87.1475 | 87.1475 | 0.054163 | 2 | 6.9021e-05 | 2507 | 0.066431 | 3085 | 4.5851e-06 | 9.1703e-06 | 3289 |  | 3514
7887 | EAST QUINCY 1101782320 | 102551101 | EAST QUINCY 1101 | 782320 | TRUE | 606.8883 | 340.3108 | 0.2115 | 5 | 6.9413e-05 | 2491 | 0.065662 | 3321 | 4.5524e-06 | 2.2762e-05 | 3290 |  | 3175
5305 | SAN RAFAEL 1105CB | 42011105 | SAN RAFAEL 1105 | CB | TRUE | 14121.4272 | 0 | 0 | 124 | 6.9844e-05 | 2479 | 0.065151 | 3576 | 4.5504e-06 | 0.00056425 | 3291 | 0.02 | 2434
8451 | GUALALA 11124431 | 42841112 | GUALALA 1112 | 4431 | FALSE | 2379.8246 | 2267.622 | 1.4093 | 16 | 6.857e-05 | 2520 | 0.066271 | 3158 | 4.548e-06 | 7.2768e-05 | 3292 | 2.63 | 593
2628 | EAST QUINCY 1101186938 | 102551101 | EAST QUINCY 1101 | 186938 | FALSE | 4893.222 | 2672.105 | 1.6607 | 41 | 6.8848e-05 | 2512 | 0.0659 | 3245 | 4.5458e-06 | 0.00018638 | 3293 |  | 2792
8531 | VALLEY VIEW 1106602871 | 14341106 | VALLEY VIEW 1106 | 602871 | FALSE | 1324.4478 | 1324.4478 | 0.82315 | 14 | 6.84e-05 | 2525 | 0.06634 | 3137 | 4.5365e-06 | 6.3511e-05 | 3294 |  | 3232
6262 | HIGHLANDS 110448262 | 43361104 | HIGHLANDS 1104 | 48262 | FALSE | 9974.998 | 9974.998 | 6.1995 | 74 | 6.8225e-05 | 2528 | 0.066414 | 3115 | 4.5315e-06 | 0.00033533 | 3295 | 0.16 | 1266
3513 | FLORENCE 0401CR220 | 12690401 | FLORENCE 0401 | CR220 | TRUE | 2216.0779 | 325.3992 | 0.20224 | 19 | 6.9057e-05 | 2505 | 0.065417 | 3408 | 4.51e-06 | 8.5689e-05 | 3296 | 0.06 | 1884
5570 | SAN CARLOS 11048942 | 24181104 | SAN CARLOS 1104 | 8942 | FALSE | 4451.7025 | 3407.8974 | 2.118 | 35 | 6.7999e-05 | 2536 | 0.066102 | 3198 | 4.5084e-06 | 0.00015779 | 3297 | 0.07 | 1712
5867 | ARLINGTON 0401404226 | 13700401 | ARLINGTON 0401 | 404226 | FALSE | 1578.9748 | 1403.5728 | 0.87233 | 15 | 6.7624e-05 | 2545 | 0.066004 | 3221 | 4.4777e-06 | 6.7165e-05 | 3298 |  | 2985
1380 | HARRIS 11084674 | 192431108 | HARRIS 1108 | 4674 | TRUE | 11266.4783 | 72.8 | 0.045245 | 85 | 6.8436e-05 | 2524 | 0.065148 | 3604 | 4.4584e-06 | 0.00037897 | 3299 | 0.02 | 2468
7856 | FORT BRAGG A 1102CB | 42761102 | FORT BRAGG A 1102 | CB | FALSE | 9310.1865 | 3594.4279 | 2.234 | 73 | 6.7929e-05 | 2538 | 0.065429 | 3407 | 4.4533e-06 | 0.00032509 | 3300 | 0.03 | 2291
7134 | DEL MONTE 2103617344 | 182222103 | DEL MONTE 2103 | 617344 | FALSE | 3993.4046 | 2952.1893 | 1.8348 | 34 | 6.6754e-05 | 2562 | 0.065865 | 3252 | 4.4076e-06 | 0.00014986 | 3301 |  | 3099
3773 | RINCON 1104CB | 43321104 | RINCON 1104 | CB | TRUE | 3983.613 | 901.4332 | 0.56024 | 34 | 5.1406e-05 | 3008 | 0.069389 | 2944 | 4.3928e-06 | 0.00014935 | 3302 | 0.16 | 1257
7255 | VIEJO 2203CB | 182852203 | VIEJO 2203 | CB | FALSE | 5468.4733 | 4727.7308 | 2.9383 | 42 | 6.6223e-05 | 2583 | 0.066187 | 3172 | 4.392e-06 | 0.00018447 | 3303 | 0.12 | 1373
1976 | LAURELES 111268454 | 182371112 | LAURELES 1112 | 68454 | FALSE | 17728.9798 | 13589.2158 | 8.4458 | 142 | 6.656e-05 | 2571 | 0.066016 | 3214 | 4.3912e-06 | 0.00062355 | 3304 | 0.14 | 1311
1047 | DOLAN ROAD 110122158 | 182381101 | DOLAN ROAD 1101 | 22158 | TRUE | 14506.5343 | 184.8198 | 0.11487 | 119 | 6.7278e-05 | 2552 | 0.065158 | 3557 | 4.3836e-06 | 0.00052165 | 3305 | 0.04 | 2174
4984 | PAUL SWEET 210212850 | 83252102 | PAUL SWEET 2102 | 12850 | FALSE | 6644.9449 | 1063.4476 | 0.66094 | 52 | 6.6462e-05 | 2576 | 0.065295 | 3464 | 4.3733e-06 | 0.00022741 | 3306 | 0.02 | 2487
10216 | GUALALA 1111498 | 42841111 | GUALALA 1111 | 498 | FALSE | 4821.7264 | 4596.7491 | 2.8569 | 18 | 6.582e-05 | 2593 | 0.066146 | 3183 | 4.3648e-06 | 7.8567e-05 | 3307 | 0.05 | 1926
5466 | WEST POINT 11025357 | 163201102 | WEST POINT 1102 | 5357 | FALSE | 5401.7845 | 5401.7845 | 3.3572 | 37 | 6.5663e-05 | 2599 | 0.066432 | 2965 | 4.3621e-06 | 0.0001614 | 3308 | 10.09 | 402
5373 | VIEJO 22019490 | 182852201 | VIEJO 2201 | 9490 | FALSE | 2186.2244 | 2004.014 | 1.2455 | 21 | 6.5775e-05 | 2597 | 0.066187 | 3173 | 4.3539e-06 | 9.1432e-05 | 3309 | 0.07 | 1753
3074 | GANSNER 1101480328 | 103021101 | GANSNER 1101 | 480328 | TRUE | 859.3222 | 472.375 | 0.29358 | 7 | 6.5647e-05 | 2600 | 0.065698 | 3311 | 4.3254e-06 | 3.0278e-05 | 3310 |  | 2811
2211 | DEL MONTE 21032654 | 182222103 | DEL MONTE 2103 | 2654 | FALSE | 2963.5999 | 2963.5999 | 1.8419 | 23 | 6.4898e-05 | 2612 | 0.066432 | 2988 | 4.3113e-06 | 9.916e-05 | 3311 | 0.09 | 1555
8914 | CLAYTON 2217CB | 12022217 | CLAYTON 2217 | CB | TRUE | 1021.9623 | 373.7851 | 0.23231 | 8 | 6.5789e-05 | 2595 | 0.065148 | 3585 | 4.2861e-06 | 3.4288e-05 | 3312 |  | 3278
9870 | PUEBLO 2103253312 | 43292103 | PUEBLO 2103 | 253312 | TRUE | 698.8026 | 682.8006 | 0.42436 | 2 | 6.5784e-05 | 2596 | 713.1431 | 1011 | 4.2859e-06 | 8.5718e-06 | 3313 |  | 3438
10448 | DOLAN ROAD 1101173702 | 182381101 | DOLAN ROAD 1101 | 173702 | TRUE | 213.4901 | 86.6803 | 0.053872 | 3 | 6.5664e-05 | 2598 | 0.065148 | 3599 | 4.2778e-06 | 1.2834e-05 | 3314 |  | 3550
7265 | ALTO 112265474 | 42031122 | ALTO 1122 | 65474 | FALSE | 5862.6816 | 3837.7425 | 2.3852 | 47 | 6.4376e-05 | 2630 | 0.065968 | 3227 | 4.2638e-06 | 0.0002004 | 3315 | 0.05 | 2056
6511 | PACIFICA 1103218962 | 22811103 | PACIFICA 1103 | 218962 | TRUE | 167.2894 | 86.3363 | 0.053658 | 2 | 5.4301e-05 | 2937 | 0.078474 | 2935 | 4.2591e-06 | 8.5182e-06 | 3316 |  | 3037
10670 | VACAVILLE 1111772224 | 63601111 | VACAVILLE 1111 | 772224 | TRUE | 126.2491 | 91.9583 | 0.057152 | 2 | 6.4042e-05 | 2644 | 0.06579 | 3275 | 4.2158e-06 | 8.4316e-06 | 3317 |  | 3588
5386 | CAROLANDS 040484797 | 24060404 | CAROLANDS 0404 | 84797 | TRUE | 2211.5607 | 66.6995 | 0.041454 | 21 | 6.4533e-05 | 2626 | 0.065331 | 3445 | 4.2155e-06 | 8.8525e-05 | 3318 | 0.02 | 2441
1724 | LAURELES 1112CB | 182371112 | LAURELES 1112 | CB | TRUE | 3818.0634 | 493.1815 | 0.30651 | 38 | 6.4589e-05 | 2622 | 0.065215 | 3503 | 4.2137e-06 | 0.00016012 | 3319 | 0.01 | 2579
1512 | ATASCADERO 1102CB | 182541102 | ATASCADERO 1102 | CB | TRUE | 8168.5567 | 0 | 0 | 67 | 6.4156e-05 | 2638 | 0.065525 | 3359 | 4.207e-06 | 0.00028187 | 3320 |  | 2730
557 | GREENBRAE 11021254 | 43091102 | GREENBRAE 1102 | 1254 | FALSE | 15241.9933 | 9639.5738 | 5.991 | 130 | 6.3299e-05 | 2668 | 0.06587 | 3250 | 4.1869e-06 | 0.0005443 | 3321 | 0.81 | 771
9628 | SAN CARLOS 110436864 | 24181104 | SAN CARLOS 1104 | 36864 | TRUE | 910.3949 | 889.7222 | 0.55297 | 10 | 6.2904e-05 | 2685 | 0.066303 | 3147 | 4.1763e-06 | 4.1763e-05 | 3322 | 0.03 | 2369
7091 | HATTON 11029642 | 182291102 | HATTON 1102 | 9642 | FALSE | 1925.8934 | 1925.8934 | 1.197 | 18 | 6.2785e-05 | 2690 | 0.066432 | 2983 | 4.1709e-06 | 7.5077e-05 | 3323 | 0.04 | 2171
757 | LAKEWOOD 1102CB | 13531102 | LAKEWOOD 1102 | CB | TRUE | 15331.9124 | 23.5925 | 0.014663 | 121 | 6.3977e-05 | 2647 | 0.065159 | 3556 | 4.1691e-06 | 0.00050446 | 3324 | 0.02 | 2479
10987 | ECHO SUMMIT 1101CB | 158031101 | ECHO SUMMIT 1101 | CB | TRUE | 49.1761 | 49.1761 | 0.030563 | 1 | 6.2654e-05 | 2695 | 0.066431 | 3094 | 4.1622e-06 | 4.1622e-06 | 3325 | 0 | 2628
9358 | PACIFICA 1102267868 | 22811102 | PACIFICA 1102 | 267868 | FALSE | 1937.2772 | 1363.5441 | 0.84745 | 13 | 6.31e-05 | 2676 | 0.065839 | 3257 | 4.157e-06 | 5.4041e-05 | 3326 |  | 3346
5985 | BERESFORD 04039154 | 24040403 | BERESFORD 0403 | 9154 | FALSE | 10556.7719 | 6776.6762 | 4.2117 | 95 | 6.2892e-05 | 2686 | 0.065945 | 3236 | 4.1518e-06 | 0.00039442 | 3327 | 0.03 | 2237
7732 | BIG MEADOWS 21012510 | 102812101 | BIG MEADOWS 2101 | 2510 | FALSE | 14243.477 | 12778.5068 | 7.9419 | 22 | 6.2454e-05 | 2707 | 0.066023 | 3213 | 4.1333e-06 | 9.0933e-05 | 3328 | 0.02 | 2457
3692 | LAS GALLINAS A 1107554 | 42991107 | LAS GALLINAS A 1107 | 554 | TRUE | 4453.2978 | 52.9857 | 0.032931 | 35 | 6.333e-05 | 2667 | 0.065188 | 3524 | 4.1303e-06 | 0.00014456 | 3329 |  | 2848
7653 | WOOD 0401265211 | 13380401 | WOOD 0401 | 265211 | TRUE | 282.195 | 238.1693 | 0.14802 | 4 | 6.2639e-05 | 2696 | 0.065789 | 3282 | 4.1276e-06 | 1.651e-05 | 3330 |  | 3146
7212 | VIEJO 2201CB | 182852201 | VIEJO 2201 | CB | FALSE | 8287.061 | 8183.2875 | 5.0859 | 67 | 6.1848e-05 | 2725 | 0.066374 | 3130 | 4.1068e-06 | 0.00027516 | 3331 | 0.08 | 1652
4015 | DOLAN ROAD 11013012 | 182381101 | DOLAN ROAD 1101 | 3012 | TRUE | 22106.1049 | 301.9386 | 0.18766 | 160 | 6.253e-05 | 2701 | 0.065164 | 3551 | 4.0749e-06 | 0.00065198 | 3332 | 0.04 | 2138
6661 | HICKS 2103XR248 | 83432103 | HICKS 2103 | XR248 | TRUE | 2436.8191 | 0 | 0 | 22 | 6.254e-05 | 2700 | 0.065147 | 3632 | 4.0743e-06 | 8.9634e-05 | 3333 |  | 3052
9871 | SARATOGA 1103709451 | 83371103 | SARATOGA 1103 | 709451 | TRUE | 302.4738 | 302.4738 | 0.18799 | 5 | 6.0665e-05 | 2757 | 0.066432 | 2951 | 4.0301e-06 | 2.0151e-05 | 3334 |  | 3439
3396 | SARATOGA 1107CB | 83371107 | SARATOGA 1107 | CB | TRUE | 15770.5803 | 273.8424 | 0.17019 | 135 | 6.178e-05 | 2726 | 0.065185 | 3529 | 4.0299e-06 | 0.00054404 | 3335 | 0.02 | 2453
697 | SANTA ROSA A 1107CB | 42151107 | SANTA ROSA A 1107 | CB | FALSE | 9896.0278 | 4879.3813 | 3.0326 | 92 | 6.0199e-05 | 2766 | 0.065711 | 3305 | 3.9708e-06 | 0.00036531 | 3336 | 0.35 | 974
7511 | BERKELEY F 1105189500 | 12061105 | BERKELEY F 1105 | 189500 | FALSE | 1726.2402 | 1225.686 | 0.76177 | 17 | 6.0082e-05 | 2771 | 0.065903 | 3244 | 3.9708e-06 | 6.7503e-05 | 3337 |  | 3131
5683 | OAKLAND K 1104CB | 12101104 | OAKLAND K 1104 | CB | FALSE | 2366.505 | 2366.505 | 1.4708 | 17 | 5.9542e-05 | 2787 | 0.066432 | 2992 | 3.9555e-06 | 6.7244e-05 | 3338 | 0.14 | 1312
4165 | VIEJO 22022606 | 182852202 | VIEJO 2202 | 2606 | FALSE | 4663.4326 | 1279.376 | 0.79514 | 52 | 5.9834e-05 | 2780 | 0.065394 | 3420 | 3.9158e-06 | 0.00020362 | 3339 | 0.06 | 1806
5028 | PUEBLO 21031970 | 43292103 | PUEBLO 2103 | 1970 | TRUE | 6915.717 | 0 | 0 | 60 | 6.0013e-05 | 2774 | 0.065151 | 3563 | 3.9099e-06 | 0.00023459 | 3340 | 0.06 | 1913
4499 | MORGAN HILL 2109145998 | 83242109 | MORGAN HILL 2109 | 145998 | FALSE | 4112.6069 | 4027.966 | 2.5034 | 28 | 5.8787e-05 | 2812 | 0.066294 | 3151 | 3.8997e-06 | 0.00010919 | 3341 |  | 2898
1014 | VIEJO 22019114 | 182852201 | VIEJO 2201 | 9114 | FALSE | 11036.3123 | 10977.6209 | 6.8226 | 92 | 5.8649e-05 | 2817 | 0.066404 | 3117 | 3.8947e-06 | 0.00035832 | 3342 | 0.17 | 1246
230 | CAROLANDS 04049026 | 24060404 | CAROLANDS 0404 | 9026 | FALSE | 8105.233 | 1184.1509 | 0.73595 | 71 | 5.949e-05 | 2791 | 0.065382 | 3425 | 3.8932e-06 | 0.00027642 | 3343 | 0.03 | 2274
10928 | FORT ORD 21069656 | 182402106 | FORT ORD 2106 | 9656 | TRUE | 188.9883 | 188.9883 | 0.11746 | 2 | 5.8277e-05 | 2826 | 0.066432 | 2981 | 3.8714e-06 | 7.7429e-06 | 3344 |  | 3621
5034 | OAKLAND J 1102CR184 | 12091102 | OAKLAND J 1102 | CR184 | FALSE | 5568.9906 | 5568.9906 | 3.4612 | 43 | 5.7871e-05 | 2839 | 0.066432 | 2949 | 3.8445e-06 | 0.00016531 | 3345 | 0.05 | 2043
4211 | FAIRVIEW 2207P142 | 13432207 | FAIRVIEW 2207 | P142 | FALSE | 5002.4344 | 1963.5704 | 1.2204 | 41 | 5.8204e-05 | 2828 | 0.065555 | 3351 | 3.8432e-06 | 0.00015757 | 3346 | 0.02 | 2469
10430 | BELL 1107643778 | 152701107 | BELL 1107 | 643778 | TRUE | 406.3148 | 270.3051 | 0.168 | 4 | 5.7794e-05 | 2841 | 0.06547 | 3381 | 3.7919e-06 | 1.5168e-05 | 3347 |  | 3549
9697 | DOLAN ROAD 1101882610 | 182381101 | DOLAN ROAD 1101 | 882610 | TRUE | 653.6335 | 228.3158 | 0.1419 | 8 | 5.7922e-05 | 2838 | 0.065308 | 3458 | 3.7868e-06 | 3.0295e-05 | 3348 |  | 3400
238 | LOS GATOS 1102526868 | 82021102 | LOS GATOS 1102 | 526868 | FALSE | 2061.1443 | 1780.5165 | 1.1066 | 20 | 5.6772e-05 | 2867 | 0.066239 | 3165 | 3.7614e-06 | 7.5227e-05 | 3349 |  | 2663
7260 | SUMMIT 110158642 | 152591101 | SUMMIT 1101 | 58642 | FALSE | 2892.0319 | 2892.0319 | 1.7974 | 13 | 5.6521e-05 | 2871 | 0.066431 | 3049 | 3.7548e-06 | 4.8812e-05 | 3350 | 0.02 | 2501
535 | ATASCADERO 11012379 | 182541101 | ATASCADERO 1101 | 2379 | FALSE | 1171.3689 | 1171.3689 | 0.72801 | 11 | 5.6518e-05 | 2872 | 0.066432 | 2969 | 3.7546e-06 | 4.1301e-05 | 3351 | 0.09 | 1523
4492 | DEL MONTE 2103468158 | 182222103 | DEL MONTE 2103 | 468158 | TRUE | 1565.7596 | 826.6133 | 0.51374 | 12 | 5.6983e-05 | 2862 | 0.065469 | 3384 | 3.7407e-06 | 4.4889e-05 | 3352 |  | 2897
8753 | HALF MOON BAY 1102650808 | 24101102 | HALF MOON BAY 1102 | 650808 | TRUE | 998.3572 | 843.3592 | 0.52415 | 8 | 5.3264e-05 | 2957 | 0.068808 | 2945 | 3.6894e-06 | 2.9515e-05 | 3353 |  | 3257
43 | WOODSIDE 1104555372 | 24251104 | WOODSIDE 1104 | 555372 | FALSE | 6684.5288 | 6684.5288 | 4.1545 | 54 | 5.5277e-05 | 2905 | 0.066432 | 2978 | 3.6721e-06 | 0.0001983 | 3354 | 0.13 | 1342
10659 | ECHO SUMMIT 110155262 | 158031101 | ECHO SUMMIT 1101 | 55262 | TRUE | 266.534 | 266.534 | 0.16565 | 4 | 5.499e-05 | 2911 | 0.066431 | 3095 | 3.653e-06 | 1.4612e-05 | 3355 | 0.06 | 1866
7441 | SAN LUIS OBISPO 110596874 | 182631105 | SAN LUIS OBISPO 1105 | 96874 | FALSE | 1722.0177 | 1345.5157 | 0.83624 | 16 | 5.4971e-05 | 2913 | 0.06595 | 3234 | 3.6408e-06 | 5.8253e-05 | 3356 |  | 3127
9136 | VIEJO 2204CB | 182852204 | VIEJO 2204 | CB | FALSE | 4041.5057 | 3727.5543 | 2.3167 | 24 | 5.482e-05 | 2920 | 0.066271 | 3157 | 3.64e-06 | 8.736e-05 | 3357 | 0.04 | 2207
4971 | EDES 1112CR282 | 13681112 | EDES 1112 | CR282 | FALSE | 6573.0208 | 6573.0208 | 4.0852 | 45 | 5.4739e-05 | 2924 | 0.066432 | 2977 | 3.6364e-06 | 0.00016364 | 3358 | 0.06 | 1916
7343 | ATASCADERO 1101CB | 182541101 | ATASCADERO 1101 | CB | TRUE | 1686.9104 | 61.191 | 0.03803 | 24 | 5.5357e-05 | 2902 | 0.065254 | 3478 | 3.6135e-06 | 8.6724e-05 | 3359 | 0.03 | 2342
8700 | VIEJO 22029488 | 182852202 | VIEJO 2202 | 9488 | FALSE | 2122.5518 | 1460.401 | 0.90765 | 18 | 5.4746e-05 | 2923 | 0.06579 | 3279 | 3.6034e-06 | 6.486e-05 | 3360 | 0.02 | 2561
3541 | SEACLIFF 0402558727 | 83500402 | SEACLIFF 0402 | 558727 | TRUE | 2270.5335 | 217.1494 | 0.13496 | 22 | 5.4871e-05 | 2919 | 0.065381 | 3426 | 3.5926e-06 | 7.9037e-05 | 3361 |  | 2835
7420 | DEL MONTE 210342226 | 182222103 | DEL MONTE 2103 | 42226 | TRUE | 4032.3201 | 940.1806 | 0.58433 | 32 | 5.4774e-05 | 2922 | 0.065308 | 3457 | 3.588e-06 | 0.00011482 | 3362 |  | 3126
7115 | LAS GALLINAS A 1104309087 | 42991104 | LAS GALLINAS A 1104 | 309087 | TRUE | 645.6047 | 302.4969 | 0.188 | 6 | 5.4354e-05 | 2935 | 0.065578 | 3341 | 3.575e-06 | 2.145e-05 | 3363 |  | 3096
5040 | TEMPLETON 2112238418 | 183052112 | TEMPLETON 2112 | 238418 | TRUE | 1291.252 | 331.2384 | 0.20587 | 6 | 5.4643e-05 | 2928 | 0.065361 | 3433 | 3.5615e-06 | 2.1369e-05 | 3364 |  | 2935
77 | ALTO 1124428 | 42031124 | ALTO 1124 | 428 | TRUE | 2739.6912 | 0 | 0 | 21 | 5.3944e-05 | 2943 | 0.065212 | 3505 | 3.5167e-06 | 7.3852e-05 | 3365 | 0.37 | 964
288 | MORGAN HILL 2110XR326 | 83242110 | MORGAN HILL 2110 | XR326 | TRUE | 21948.0156 | 0 | 0 | 163 | 5.3862e-05 | 2945 | 0.065147 | 3608 | 3.509e-06 | 0.00057196 | 3366 | 0.04 | 2188
1912 | SANTA ROSA A 110439786 | 42151104 | SANTA ROSA A 1104 | 39786 | TRUE | 5442.5467 | 454.7368 | 0.28262 | 44 | 5.3497e-05 | 2950 | 0.065245 | 3482 | 3.496e-06 | 0.00015383 | 3367 | 0.21 | 1145
6503 | VIEJO 22029118 | 182852202 | VIEJO 2202 | 9118 | FALSE | 4822.7839 | 1265.7827 | 0.78669 | 41 | 5.3297e-05 | 2954 | 0.065429 | 3406 | 3.4915e-06 | 0.00014315 | 3368 | 0.42 | 936
4440 | SANTA ROSA A 1104991788 | 42151104 | SANTA ROSA A 1104 | 991788 | FALSE | 5495.9742 | 1222.0634 | 0.75952 | 43 | 5.288e-05 | 2971 | 0.065395 | 3419 | 3.4631e-06 | 0.00014892 | 3369 |  | 2890
8382 | MORGAN HILL 2109XR246 | 83242109 | MORGAN HILL 2109 | XR246 | TRUE | 6374.5348 | 71.5932 | 0.044495 | 61 | 5.3027e-05 | 2967 | 0.06519 | 3521 | 3.4559e-06 | 0.00021081 | 3370 |  | 3218
8657 | OCEANO 110376678 | 182601103 | OCEANO 1103 | 76678 | TRUE | 597.8557 | 88.7522 | 0.05516 | 8 | 5.2866e-05 | 2974 | 0.065468 | 3386 | 3.4511e-06 | 2.7609e-05 | 3371 | 0.02 | 2467
9324 | ECHO SUMMIT 1101741586 | 158031101 | ECHO SUMMIT 1101 | 741586 | FALSE | 1137.7952 | 1137.7952 | 0.70714 | 9 | 5.1683e-05 | 3002 | 0.066431 | 3093 | 3.4334e-06 | 3.09e-05 | 3372 |  | 3342
392 | BELMONT 11038958 | 24031103 | BELMONT 1103 | 8958 | FALSE | 9585.6333 | 5438.9297 | 3.3803 | 73 | 5.1694e-05 | 3001 | 0.065833 | 3259 | 3.4119e-06 | 0.00024907 | 3373 | 0.04 | 2204
9058 | LOS GATOS 1101502026 | 82021101 | LOS GATOS 1101 | 502026 | TRUE | 1729.6385 | 180.5393 | 0.11221 | 17 | 5.2048e-05 | 2992 | 0.065374 | 3427 | 3.4024e-06 | 5.784e-05 | 3374 |  | 3302
2028 | HICKS 1116LB16 | 83431116 | HICKS 1116 | LB16 | FALSE | 13211.9515 | 4399.0652 | 2.734 | 97 | 5.1468e-05 | 3006 | 0.065597 | 3335 | 3.3964e-06 | 0.00032945 | 3375 | 0.03 | 2296
10450 | OAKLAND J 1102951816 | 12091102 | OAKLAND J 1102 | 951816 | TRUE | 539.1734 | 539.1734 | 0.3351 | 6 | 5.1065e-05 | 3013 | 0.066431 | 3112 | 3.3923e-06 | 2.0354e-05 | 3376 |  | 3551
3081 | SARATOGA 1103LC40 | 83371103 | SARATOGA 1103 | LC40 | TRUE | 2260.1219 | 26.7728 | 0.016639 | 28 | 5.1876e-05 | 2996 | 0.065193 | 3517 | 3.3827e-06 | 9.4717e-05 | 3377 | 0.02 | 2440
5298 | SAN LEANDRO U 1109CR182 | 13111109 | SAN LEANDRO U 1109 | CR182 | FALSE | 7768.8154 | 7768.8154 | 4.8284 | 56 | 5.0879e-05 | 3018 | 0.066432 | 2959 | 3.38e-06 | 0.00018928 | 3378 | 0.15 | 1294
9781 | SAN LUIS OBISPO 1108903036 | 182631108 | SAN LUIS OBISPO 1108 | 903036 | TRUE | 576.6112 | 306.6437 | 0.19058 | 5 | 5.0816e-05 | 3019 | 0.065404 | 3415 | 3.3474e-06 | 1.6737e-05 | 3379 |  | 3419
1847 | ALTO 1122CB | 42031122 | ALTO 1122 | CB | FALSE | 5576.1236 | 3611.6831 | 2.2447 | 46 | 5.0453e-05 | 3026 | 0.065847 | 3255 | 3.3325e-06 | 0.0001533 | 3380 | 0.18 | 1221
559 | PACIFICA 110266732 | 22811102 | PACIFICA 1102 | 66732 | TRUE | 3298.663 | 334.9483 | 0.20817 | 23 | 5.0745e-05 | 3021 | 0.065259 | 3476 | 3.3135e-06 | 7.6211e-05 | 3381 | 0.04 | 2115
7812 | LUCERNE 11062355 | 43351106 | LUCERNE 1106 | 2355 | TRUE | 1676.4836 | 644.3598 | 0.40047 | 13 | 4.9957e-05 | 3038 | 0.065643 | 3325 | 3.2963e-06 | 4.2852e-05 | 3382 | 0.06 | 1797
9811 | PACIFICA 1103119798 | 22811103 | PACIFICA 1103 | 119798 | TRUE | 129.7041 | 129.7041 | 0.080612 | 2 | 4.9475e-05 | 3051 | 0.066432 | 2975 | 3.2867e-06 | 6.5735e-06 | 3383 |  | 3428
10195 | ALTO 112081716 | 42031120 | ALTO 1120 | 81716 | TRUE | 406.7505 | 406.7505 | 0.2528 | 5 | 4.9207e-05 | 3059 | 0.066432 | 2971 | 3.2689e-06 | 1.6345e-05 | 3384 |  | 3512
6620 | LOS GATOS 1101950286 | 82021101 | LOS GATOS 1101 | 950286 | FALSE | 1710.7995 | 1710.7995 | 1.0633 | 17 | 4.911e-05 | 3061 | 0.066432 | 2974 | 3.2625e-06 | 5.5462e-05 | 3385 |  | 3046
5964 | RALSTON 1102CB | 24141102 | RALSTON 1102 | CB | FALSE | 6891.3641 | 1520.1281 | 0.94477 | 66 | 4.9607e-05 | 3044 | 0.065478 | 3378 | 3.2502e-06 | 0.00021451 | 3386 | 0.05 | 2029
8215 | GREENBRAE 1104107508 | 43091104 | GREENBRAE 1104 | 107508 | TRUE | 282.9574 | 0 | 0 | 2 | 4.9331e-05 | 3054 | 0.065151 | 3568 | 3.214e-06 | 6.4279e-06 | 3387 |  | 3203
1635 | OAKLAND K 1101CR172 | 12101101 | OAKLAND K 1101 | CR172 | TRUE | 3350.0951 | 904.9661 | 0.56244 | 30 | 4.8943e-05 | 3065 | 0.065361 | 3434 | 3.209e-06 | 9.6271e-05 | 3388 | 0.05 | 2015
3774 | PAUL SWEET 210411074 | 83252104 | PAUL SWEET 2104 | 11074 | FALSE | 4972.7567 | 4718.31 | 2.9324 | 41 | 4.8374e-05 | 3082 | 0.066275 | 3154 | 3.1905e-06 | 0.00013081 | 3389 | 0.48 | 903
8087 | SAN RAMON 2107MR441 | 14232107 | SAN RAMON 2107 | MR441 | TRUE | 350.4949 | 40.2016 | 0.024985 | 8 | 4.8606e-05 | 3074 | 0.065309 | 3456 | 3.1892e-06 | 2.5513e-05 | 3390 |  | 3190
7720 | SAN RAFAEL 1106764698 | 42011106 | SAN RAFAEL 1106 | 764698 | TRUE | 357.0375 | 133.4071 | 0.082913 | 5 | 4.8608e-05 | 3073 | 0.065407 | 3412 | 3.1867e-06 | 1.5933e-05 | 3391 |  | 3156
3736 | VALLEY VIEW 1105P126 | 14341105 | VALLEY VIEW 1105 | P126 | FALSE | 3297.3508 | 1680.8363 | 1.0446 | 25 | 4.8344e-05 | 3085 | 0.065713 | 3304 | 3.1848e-06 | 7.9621e-05 | 3392 | 0.03 | 2259
2670 | GREENBRAE 11037315 | 43091103 | GREENBRAE 1103 | 7315 | TRUE | 3607.614 | 0 | 0 | 32 | 4.8486e-05 | 3078 | 0.065151 | 3567 | 3.1589e-06 | 0.00010108 | 3393 |  | 2795
6253 | FORT BRAGG A 110233064 | 42761102 | FORT BRAGG A 1102 | 33064 | TRUE | 5902.0297 | 0 | 0 | 49 | 4.8351e-05 | 3084 | 0.065148 | 3593 | 3.15e-06 | 0.00015435 | 3394 |  | 3017
4022 | EDES 1112CR100 | 13681112 | EDES 1112 | CR100 | FALSE | 5399.0675 | 5399.0675 | 3.3555 | 40 | 4.7216e-05 | 3109 | 0.066432 | 2972 | 3.1366e-06 | 0.00012546 | 3395 | 0.04 | 2134
1730 | LOS GATOS 1101CB | 82021101 | LOS GATOS 1101 | CB | TRUE | 3679.779 | 47.6524 | 0.029616 | 34 | 4.8123e-05 | 3090 | 0.065185 | 3530 | 3.1364e-06 | 0.00010664 | 3396 | 0.03 | 2233
5067 | EL CERRITO G 1112BR178 | 12501112 | EL CERRITO G 1112 | BR178 | TRUE | 10667.1601 | 48.2003 | 0.029957 | 93 | 4.805e-05 | 3092 | 0.065161 | 3553 | 3.1309e-06 | 0.00029117 | 3397 | 0.24 | 1105
3732 | SOBRANTE 1101L534R | 14671101 | SOBRANTE 1101 | L534R | FALSE | 3066.0904 | 1291.9266 | 0.80294 | 34 | 4.7553e-05 | 3099 | 0.065526 | 3358 | 3.1282e-06 | 0.00010636 | 3398 | 0.06 | 1853
4550 | VALLEY VIEW 1106P176 | 14341106 | VALLEY VIEW 1106 | P176 | TRUE | 5384.4602 | 354.4687 | 0.2203 | 44 | 4.7444e-05 | 3104 | 0.066098 | 3199 | 3.1268e-06 | 0.00013758 | 3399 | 0.06 | 1778
7024 | VIEJO 220292792 | 182852202 | VIEJO 2202 | 92792 | TRUE | 2338.4551 | 0 | 0 | 21 | 4.7946e-05 | 3094 | 0.065148 | 3598 | 3.1236e-06 | 6.5595e-05 | 3400 | 0.04 | 2169
8774 | TULUCAY 1101504524 | 42301101 | TULUCAY 1101 | 504524 | TRUE | 2446.524 | 610.0991 | 0.37918 | 15 | 4.7542e-05 | 3101 | 0.065322 | 3452 | 3.1216e-06 | 4.6823e-05 | 3401 |  | 3262
9561 | ATASCADERO 1101747522 | 182541101 | ATASCADERO 1101 | 747522 | TRUE | 1686.5664 | 412.9409 | 0.25664 | 16 | 4.7461e-05 | 3103 | 0.065468 | 3390 | 3.1133e-06 | 4.9813e-05 | 3402 |  | 3378
1757 | OAKLAND X 1106121588 | 12541106 | OAKLAND X 1106 | 121588 | FALSE | 3050.4627 | 1356.1967 | 0.84288 | 27 | 4.7074e-05 | 3111 | 0.065623 | 3330 | 3.0983e-06 | 8.3654e-05 | 3403 |  | 2743
641 | ALTO 11251256 | 42031125 | ALTO 1125 | 1256 | FALSE | 12257.9124 | 12003.1718 | 7.46 | 88 | 4.6726e-05 | 3121 | 0.066359 | 3134 | 3.098e-06 | 0.00027263 | 3404 | 0.07 | 1720
7693 | SARATOGA 1103595689 | 83371103 | SARATOGA 1103 | 595689 | TRUE | 356.3825 | 44.7654 | 0.027822 | 4 | 4.6978e-05 | 3113 | 0.065468 | 3387 | 3.0826e-06 | 1.233e-05 | 3405 |  | 3152
1201 | RINCON 1102640 | 43321102 | RINCON 1102 | 640 | TRUE | 6850.9553 | 0 | 0 | 56 | 4.7109e-05 | 3110 | 0.065185 | 3528 | 3.0722e-06 | 0.00017204 | 3406 | 0.02 | 2509
8249 | VIEJO 22029089 | 182852202 | VIEJO 2202 | 9089 | FALSE | 2700.0603 | 2319.95 | 1.4419 | 20 | 4.6292e-05 | 3130 | 0.066175 | 3177 | 3.0684e-06 | 6.1368e-05 | 3407 | 0.03 | 2365
4500 | PACIFICA 1102968736 | 22811102 | PACIFICA 1102 | 968736 | FALSE | 1533.9821 | 1132.2658 | 0.70371 | 9 | 4.6179e-05 | 3133 | 0.065575 | 3349 | 3.0372e-06 | 2.7334e-05 | 3408 |  | 2899
5121 | BURNEY 110237284 | 103311102 | BURNEY 1102 | 37284 | TRUE | 823.8475 | 303.068 | 0.18836 | 15 | 4.5944e-05 | 3141 | 0.065918 | 3241 | 3.0199e-06 | 4.5299e-05 | 3409 |  | 2937
3124 | SAN RAFAEL 110648752 | 42011106 | SAN RAFAEL 1106 | 48752 | TRUE | 3375.7798 | 23.2085 | 0.014424 | 28 | 4.6007e-05 | 3137 | 0.065151 | 3572 | 2.9974e-06 | 8.3928e-05 | 3410 | 0.02 | 2446
292 | RIDGE 0402CB | 12840402 | RIDGE 0402 | CB | FALSE | 3860.7171 | 2930.2271 | 1.8211 | 31 | 4.5082e-05 | 3157 | 0.066059 | 3208 | 2.9927e-06 | 9.2772e-05 | 3411 | 0.06 | 1837
5812 | LAS GALLINAS A 11051218 | 42991105 | LAS GALLINAS A 1105 | 1218 | TRUE | 3546.1366 | 106.7452 | 0.066343 | 28 | 4.5839e-05 | 3144 | 0.065197 | 3512 | 2.9904e-06 | 8.3731e-05 | 3412 | 0.03 | 2368
5928 | IGNACIO 110584764 | 42481105 | IGNACIO 1105 | 84764 | TRUE | 4092.9318 | 339.9136 | 0.21126 | 33 | 4.5707e-05 | 3148 | 0.065268 | 3472 | 2.9818e-06 | 9.8398e-05 | 3413 |  | 2990
231 | PAUL SWEET 210912828 | 83252109 | PAUL SWEET 2109 | 12828 | FALSE | 7906.6719 | 1834.1595 | 1.1399 | 66 | 4.4984e-05 | 3161 | 0.065458 | 3393 | 2.9651e-06 | 0.0001957 | 3414 |  | 2662
5926 | CASTRO VALLEY 1110CB | 14091110 | CASTRO VALLEY 1110 | CB | TRUE | 2059.8957 | 523.3275 | 0.32525 | 23 | 4.4906e-05 | 3162 | 0.065538 | 3356 | 2.9632e-06 | 6.8153e-05 | 3415 |  | 2989
8452 | HARRIS 1108395498 | 192431108 | HARRIS 1108 | 395498 | TRUE | 792.3855 | 171.0291 | 0.1063 | 8 | 4.5439e-05 | 3154 | 0.065308 | 3459 | 2.9622e-06 | 2.3698e-05 | 3416 |  | 3227
8569 | IGNACIO 1105683542 | 42481105 | IGNACIO 1105 | 683542 | TRUE | 222.9115 | 222.9115 | 0.13854 | 2 | 4.4358e-05 | 3180 | 0.066431 | 3030 | 2.9468e-06 | 5.8935e-06 | 3417 |  | 3237
6289 | STAFFORD 1101405812 | 43201101 | STAFFORD 1101 | 405812 | TRUE | 695.3753 | 295.2493 | 0.1835 | 7 | 4.5015e-05 | 3158 | 0.065517 | 3362 | 2.9445e-06 | 2.0611e-05 | 3418 |  | 3019
8541 | ROSSMOOR 1106L541R | 14161106 | ROSSMOOR 1106 | L541R | TRUE | 978.5878 | 0 | 0 | 11 | 4.5011e-05 | 3159 | 0.065148 | 3586 | 2.9324e-06 | 3.2256e-05 | 3419 |  | 3233
3241 | OAKLAND K 1101CB | 12101101 | OAKLAND K 1101 | CB | TRUE | 3805.7329 | 538.4598 | 0.33465 | 40 | 4.4235e-05 | 3185 | 0.065436 | 3400 | 2.9186e-06 | 0.00011674 | 3420 | 0.04 | 2228
6045 | OAKLAND J 1105CR256 | 12091105 | OAKLAND J 1105 | CR256 | FALSE | 2967.1612 | 1965.4224 | 1.2215 | 27 | 4.4194e-05 | 3187 | 0.065813 | 3263 | 2.9181e-06 | 7.879e-05 | 3421 | 0.05 | 2053
8780 | SAN LUIS OBISPO 1108144690 | 182631108 | SAN LUIS OBISPO 1108 | 144690 | TRUE | 900.0003 | 418.942 | 0.26037 | 10 | 3.5334e-05 | 3344 | 0.075693 | 2936 | 2.905e-06 | 2.905e-05 | 3422 |  | 3264
10157 | CASTRO VALLEY 1108MR233 | 14091108 | CASTRO VALLEY 1108 | MR233 | TRUE | 1023.3374 | 370.9448 | 0.23054 | 7 | 4.4443e-05 | 3176 | 0.065331 | 3447 | 2.9035e-06 | 2.0325e-05 | 3423 |  | 3504
3481 | IGNACIO 1105318 | 42481105 | IGNACIO 1105 | 318 | FALSE | 18622.6335 | 2887.2825 | 1.7945 | 150 | 4.4269e-05 | 3183 | 0.065347 | 3439 | 2.9031e-06 | 0.00043547 | 3424 |  | 2830
1523 | HAMILTON BRANCH 110187784 | 102361101 | HAMILTON BRANCH 1101 | 87784 | FALSE | 2328.7215 | 2328.7215 | 1.4473 | 23 | 4.3587e-05 | 3199 | 0.066432 | 2997 | 2.8956e-06 | 6.6598e-05 | 3425 | 0.12 | 1383
10922 | PINECREST 0401CB | 163160401 | PINECREST 0401 | CB | TRUE | 22.2055 | 22.2055 | 0.013801 | 1 | 4.352e-05 | 3201 | 0.066431 | 3088 | 2.8911e-06 | 2.8911e-06 | 3426 | 1.9 | 633
1324 | SONOMA 11054456 | 42721105 | SONOMA 1105 | 4456 | TRUE | 8052.7827 | 0 | 0 | 62 | 4.4073e-05 | 3189 | 0.065151 | 3562 | 2.8714e-06 | 0.00017803 | 3427 | 0.03 | 2297
8419 | SAN CARLOS 1103785521 | 24181103 | SAN CARLOS 1103 | 785521 | TRUE | 292.996 | 109.0213 | 0.067757 | 3 | 4.3673e-05 | 3196 | 0.065575 | 3350 | 2.8654e-06 | 8.5962e-06 | 3428 |  | 3223
6629 | BIG MEADOWS 21012246 | 102812101 | BIG MEADOWS 2101 | 2246 | FALSE | 2937.4924 | 2937.4924 | 1.8257 | 23 | 4.2984e-05 | 3209 | 0.066432 | 2998 | 2.8555e-06 | 6.5676e-05 | 3429 | 0.1 | 1481
692 | ECHO SUMMIT 11018922 | 158031101 | ECHO SUMMIT 1101 | 8922 | FALSE | 1940.3902 | 1940.3902 | 1.206 | 11 | 4.2932e-05 | 3211 | 0.066431 | 3096 | 2.852e-06 | 3.1372e-05 | 3430 | 0.18 | 1208
5593 | SNEATH LANE 1102CB | 22721102 | SNEATH LANE 1102 | CB | FALSE | 4044.2651 | 2195.0074 | 1.3642 | 37 | 4.3121e-05 | 3206 | 0.065703 | 3309 | 2.8459e-06 | 0.0001053 | 3431 | 0.02 | 2448
7382 | VIEJO 220235388 | 182852202 | VIEJO 2202 | 35388 | TRUE | 727.2974 | 517.0139 | 0.32133 | 8 | 4.2702e-05 | 3213 | 0.066111 | 3193 | 2.8344e-06 | 2.2676e-05 | 3432 | 0.94 | 745
5265 | IGNACIO 1103CB | 42481103 | IGNACIO 1103 | CB | TRUE | 3068.5523 | 350.3296 | 0.21773 | 34 | 4.3221e-05 | 3205 | 0.065226 | 3495 | 2.8181e-06 | 9.5817e-05 | 3433 |  | 2943
9102 | HICKS 1116733078 | 83431116 | HICKS 1116 | 733078 | TRUE | 567.873 | 551.871 | 0.34299 | 7 | 4.2163e-05 | 3221 | 0.066065 | 3206 | 2.777e-06 | 1.9439e-05 | 3434 |  | 3310
199 | OAKLAND K 1103CB | 12101103 | OAKLAND K 1103 | CB | TRUE | 7954.9462 | 769.1621 | 0.47804 | 66 | 4.1996e-05 | 3224 | 0.065264 | 3474 | 2.758e-06 | 0.00018203 | 3435 | 0.02 | 2428
2072 | RALSTON 1101420730 | 24141101 | RALSTON 1101 | 420730 | FALSE | 2651.706 | 1292.6324 | 0.80338 | 21 | 4.1694e-05 | 3230 | 0.065759 | 3293 | 2.7513e-06 | 5.7777e-05 | 3436 |  | 2760
8913 | WOOD 0401880795 | 13380401 | WOOD 0401 | 880795 | TRUE | 506.0077 | 163.9752 | 0.10191 | 6 | 4.2077e-05 | 3222 | 0.065147 | 3611 | 2.7412e-06 | 1.6447e-05 | 3437 |  | 3277
7811 | VIEJO 2203947314 | 182852203 | VIEJO 2203 | 947314 | TRUE | 2331.8511 | 461.4011 | 0.28676 | 22 | 4.1433e-05 | 3236 | 0.065323 | 3451 | 2.7164e-06 | 5.9761e-05 | 3438 |  | 3163
8336 | OLEMA 110137074 | 42291101 | OLEMA 1101 | 37074 | TRUE | 506.0081 | 21.9456 | 0.013639 | 6 | 4.1439e-05 | 3234 | 0.065361 | 3435 | 2.7134e-06 | 1.628e-05 | 3439 | 0.03 | 2372
6224 | SAN CARLOS 110479774 | 24181104 | SAN CARLOS 1104 | 79774 | FALSE | 2604.0952 | 1435.8821 | 0.89241 | 24 | 4.0919e-05 | 3247 | 0.065682 | 3315 | 2.698e-06 | 6.4753e-05 | 3440 | 0.05 | 2041
2094 | ROB ROY 210512586 | 83692105 | ROB ROY 2105 | 12586 | FALSE | 10478.2506 | 3041.3304 | 1.8902 | 85 | 4.1068e-05 | 3241 | 0.065464 | 3391 | 2.697e-06 | 0.00022925 | 3441 | 0.05 | 2013
8276 | OAKLAND J 1102CR254 | 12091102 | OAKLAND J 1102 | CR254 | FALSE | 2477.3187 | 1687.0283 | 1.0485 | 20 | 4.0719e-05 | 3253 | 0.065918 | 3242 | 2.6941e-06 | 5.3882e-05 | 3442 | 0.03 | 2367
5380 | CASTROVILLE 210436922 | 182352104 | CASTROVILLE 2104 | 36922 | TRUE | 8825.2123 | 0 | 0 | 37 | 4.0991e-05 | 3245 | 0.065148 | 3595 | 2.6705e-06 | 9.8808e-05 | 3443 |  | 2948
6593 | FOOTHILL 1101798137 | 182951101 | FOOTHILL 1101 | 798137 | TRUE | 581.8228 | 68.0149 | 0.042272 | 5 | 4.0802e-05 | 3250 | 0.065404 | 3417 | 2.6637e-06 | 1.3319e-05 | 3444 |  | 3045
1687 | BIG MEADOWS 21012016 | 102812101 | BIG MEADOWS 2101 | 2016 | TRUE | 6829.6992 | 150.9724 | 0.09383 | 65 | 4.0813e-05 | 3249 | 0.065188 | 3525 | 2.6614e-06 | 0.00017299 | 3445 | 0.04 | 2208
10145 | GREENBRAE 1104317890 | 43091104 | GREENBRAE 1104 | 317890 | TRUE | 125.8315 | 125.8315 | 0.078205 | 2 | 3.9991e-05 | 3269 | 0.066431 | 3031 | 2.6567e-06 | 5.3133e-06 | 3446 |  | 3501
3009 | GREENBRAE 1102CB | 43091102 | GREENBRAE 1102 | CB | TRUE | 3469.4672 | 0 | 0 | 28 | 4.0756e-05 | 3251 | 0.065151 | 3570 | 2.6553e-06 | 7.4348e-05 | 3447 | 0.09 | 1558
9193 | LOS GATOS 1106CB | 82021106 | LOS GATOS 1106 | CB | TRUE | 1170.6003 | 164.2523 | 0.10208 | 11 | 4.0346e-05 | 3259 | 0.065497 | 3371 | 2.651e-06 | 2.9161e-05 | 3448 | 0.27 | 1059
6430 | FORT BRAGG A 110465894 | 42761104 | FORT BRAGG A 1104 | 65894 | TRUE | 1441.6391 | 0 | 0 | 12 | 4.0627e-05 | 3255 | 0.065148 | 3601 | 2.6468e-06 | 3.1761e-05 | 3449 |  | 3031
6292 | RIO DEL MAR 0401931192 | 83260401 | RIO DEL MAR 0401 | 931192 | FALSE | 11415.5971 | 3615.6701 | 2.2472 | 87 | 4.0212e-05 | 3262 | 0.065487 | 3375 | 2.6467e-06 | 0.00023026 | 3450 |  | 3020
8372 | LAURELES 11122142 | 182371112 | LAURELES 1112 | 2142 | TRUE | 2588.0177 | 151.8851 | 0.094397 | 26 | 4.0293e-05 | 3261 | 0.065246 | 3480 | 2.6301e-06 | 6.8383e-05 | 3451 | 0.08 | 1615
4353 | FLORENCE 0401CB | 12690401 | FLORENCE 0401 | CB | FALSE | 4654.0755 | 1041.2537 | 0.64714 | 39 | 4.0081e-05 | 3266 | 0.065411 | 3410 | 2.6231e-06 | 0.0001023 | 3452 | 0.04 | 2160
1560 | SANTA ROSA A 1104CB | 42151104 | SANTA ROSA A 1104 | CB | TRUE | 9581.6812 | 369.0017 | 0.22934 | 76 | 4.0032e-05 | 3268 | 0.065241 | 3484 | 2.617e-06 | 0.00019889 | 3453 | 0.16 | 1252
9790 | PAUL SWEET 2109680537 | 83252109 | PAUL SWEET 2109 | 680537 | TRUE | 1060.8184 | 362.7293 | 0.22544 | 9 | 3.9362e-05 | 3278 | 0.065433 | 3403 | 2.5979e-06 | 2.3381e-05 | 3454 |  | 3424
9764 | PACIFICA 1102512070 | 22811102 | PACIFICA 1102 | 512070 | TRUE | 481.613 | 279.6247 | 0.17379 | 5 | 3.9072e-05 | 3285 | 0.065661 | 3322 | 2.586e-06 | 1.293e-05 | 3455 |  | 3413
2324 | ALTO 1124CB | 42031124 | ALTO 1124 | CB | FALSE | 9084.5965 | 2733.348 | 1.6988 | 81 | 3.9255e-05 | 3280 | 0.065515 | 3364 | 2.5838e-06 | 0.00020929 | 3456 | 0.24 | 1096
2547 | CASTRO VALLEY 1102MR204 | 14091102 | CASTRO VALLEY 1102 | MR204 | TRUE | 4739.0907 | 326.5252 | 0.20294 | 46 | 3.9361e-05 | 3279 | 0.065259 | 3475 | 2.5759e-06 | 0.00011849 | 3457 |  | 2785
885 | EDES 1112CR308 | 13681112 | EDES 1112 | CR308 | FALSE | 5698.3231 | 5168.8003 | 3.2124 | 53 | 3.8446e-05 | 3292 | 0.066287 | 3153 | 2.5524e-06 | 0.00013527 | 3458 | 0.07 | 1769
7145 | HICKS 111512494 | 83431115 | HICKS 1115 | 12494 | TRUE | 4190.5486 | 220.1167 | 0.1368 | 35 | 3.9122e-05 | 3283 | 0.065184 | 3532 | 2.5505e-06 | 8.9268e-05 | 3459 |  | 3101
970 | CAYUCOS 1102CB | 182551102 | CAYUCOS 1102 | CB | TRUE | 8504.0553 | 0 | 0 | 41 | 3.9093e-05 | 3284 | 0.065147 | 3625 | 2.5468e-06 | 0.00010442 | 3460 | 0.18 | 1219
7960 | LOS GATOS 1101206248 | 82021101 | LOS GATOS 1101 | 206248 | TRUE | 893.3087 | 83.0039 | 0.051587 | 10 | 3.895e-05 | 3288 | 0.065404 | 3414 | 2.5435e-06 | 2.5435e-05 | 3461 |  | 3179
2461 | HAMILTON BRANCH 110137436 | 102361101 | HAMILTON BRANCH 1101 | 37436 | FALSE | 3311.0305 | 1208.0743 | 0.75082 | 33 | 3.8691e-05 | 3289 | 0.065576 | 3347 | 2.5374e-06 | 8.3735e-05 | 3462 | 0.1 | 1485
5208 | VIEJO 22029120 | 182852202 | VIEJO 2202 | 9120 | FALSE | 11903.5244 | 2858.0041 | 1.7763 | 112 | 3.8665e-05 | 3290 | 0.065446 | 3397 | 2.5361e-06 | 0.00028404 | 3463 | 0.07 | 1741
10027 | PACIFICA 1103398620 | 22811103 | PACIFICA 1103 | 398620 | TRUE | 770.3641 | 758.0837 | 0.47115 | 7 | 3.8215e-05 | 3297 | 0.066248 | 3163 | 2.531e-06 | 1.7717e-05 | 3464 |  | 3477
4053 | OAKLAND X 1105184672 | 12541105 | OAKLAND X 1105 | 184672 | FALSE | 5259.1473 | 2666.0437 | 1.657 | 46 | 3.8231e-05 | 3295 | 0.065706 | 3307 | 2.5255e-06 | 0.00011617 | 3465 |  | 2869
5327 | FAIRVIEW 2207CB | 13432207 | FAIRVIEW 2207 | CB | TRUE | 8128.5867 | 387.1496 | 0.24062 | 57 | 3.8448e-05 | 3291 | 0.065193 | 3515 | 2.5112e-06 | 0.00014314 | 3466 | 0.03 | 2279
1098 | VIEJO 22012064 | 182852201 | VIEJO 2201 | 2064 | FALSE | 1409.3976 | 1409.3976 | 0.87595 | 15 | 3.7422e-05 | 3305 | 0.066432 | 2982 | 2.486e-06 | 3.729e-05 | 3467 | 0.08 | 1660
3180 | STAFFORD 110242542 | 43201102 | STAFFORD 1102 | 42542 | TRUE | 5717.1489 | 862.3483 | 0.53595 | 52 | 3.7508e-05 | 3304 | 0.065348 | 3438 | 2.465e-06 | 0.00012818 | 3468 | 0.03 | 2335
4684 | SNEATH LANE 110134438 | 22721101 | SNEATH LANE 1101 | 34438 | FALSE | 8258.6725 | 3709.6211 | 2.3055 | 67 | 3.7308e-05 | 3309 | 0.065492 | 3373 | 2.4545e-06 | 0.00016445 | 3469 | 0.06 | 1800
5609 | BURNEY 110297318 | 103311102 | BURNEY 1102 | 97318 | TRUE | 1594.8254 | 294.9732 | 0.18333 | 18 | 3.7395e-05 | 3306 | 0.065576 | 3346 | 2.4455e-06 | 4.4019e-05 | 3470 | 0.03 | 2327
3808 | HAMILTON BRANCH 11013049 | 102361101 | HAMILTON BRANCH 1101 | 3049 | FALSE | 2682.1998 | 1650.9947 | 1.0261 | 23 | 3.708e-05 | 3312 | 0.065874 | 3249 | 2.4445e-06 | 5.6224e-05 | 3471 | 2.64 | 592
10978 | ALTO 1124965060 | 42031124 | ALTO 1124 | 965060 | TRUE | 112.5171 | 99.6543 | 0.061936 | 1 | 3.6723e-05 | 3320 | 0.066431 | 3036 | 2.4396e-06 | 2.4396e-06 | 3472 |  | 3624
10767 | SAUSALITO 1102758798 | 42491102 | SAUSALITO 1102 | 758798 | TRUE | 68.038 | 53.2652 | 0.033105 | 2 | 3.6428e-05 | 3325 | 0.065789 | 3289 | 2.4159e-06 | 4.8318e-06 | 3473 |  | 3603
2223 | PAUL SWEET 2109CB | 83252109 | PAUL SWEET 2109 | CB | TRUE | 18410.6369 | 20.7388 | 0.012889 | 171 | 3.6749e-05 | 3319 | 0.065155 | 3560 | 2.3948e-06 | 0.00040951 | 3474 | 0.28 | 1039
4848 | VALLEY VIEW 1103P160 | 14341103 | VALLEY VIEW 1103 | P160 | TRUE | 10321.2013 | 0 | 0 | 96 | 3.6431e-05 | 3324 | 0.065148 | 3582 | 2.3734e-06 | 0.00022785 | 3475 | 2.76 | 583
1157 | MORAGA 1105116034 | 13801105 | MORAGA 1105 | 116034 | TRUE | 4982.0059 | 539.5091 | 0.33531 | 41 | 3.6154e-05 | 3332 | 0.065278 | 3469 | 2.3641e-06 | 9.6928e-05 | 3476 |  | 2713
6537 | SNEATH LANE 110275844 | 22721102 | SNEATH LANE 1102 | 75844 | TRUE | 864.7167 | 272.6844 | 0.16947 | 10 | 3.5678e-05 | 3340 | 0.065275 | 3470 | 2.3271e-06 | 2.3271e-05 | 3477 | 0.02 | 2485
1692 | SAN CARLOS 11048846 | 24181104 | SAN CARLOS 1104 | 8846 | FALSE | 7060.9911 | 3588.6165 | 2.2303 | 61 | 3.5185e-05 | 3347 | 0.065737 | 3298 | 2.3218e-06 | 0.00014163 | 3478 | 0.04 | 2219
5922 | SNEATH LANE 1101CB | 22721101 | SNEATH LANE 1101 | CB | TRUE | 1584.8668 | 745.3166 | 0.46322 | 19 | 3.5327e-05 | 3345 | 0.06535 | 3437 | 2.3127e-06 | 4.3942e-05 | 3479 | 0.02 | 2415
3263 | SAN LEANDRO U 1109936988 | 13111109 | SAN LEANDRO U 1109 | 936988 | FALSE | 10891.0554 | 10891.0554 | 6.7688 | 86 | 3.4698e-05 | 3356 | 0.066432 | 2957 | 2.3051e-06 | 0.00019824 | 3480 |  | 2818
7536 | WILLITS 11021270 | 42661102 | WILLITS 1102 | 1270 | TRUE | 2454.7077 | 0 | 0 | 21 | 3.5345e-05 | 3343 | 0.06515 | 3579 | 2.3027e-06 | 4.8357e-05 | 3481 |  | 3133
2607 | WALDO 0402258792 | 13350402 | WALDO 0402 | 258792 | FALSE | 4808.6867 | 4793.9751 | 2.9795 | 36 | 3.4657e-05 | 3358 | 0.066396 | 3121 | 2.3019e-06 | 8.287e-05 | 3482 |  | 2788
2976 | STAFFORD 1101902998 | 43201101 | STAFFORD 1101 | 902998 | FALSE | 9746.2747 | 1732.2882 | 1.0766 | 81 | 3.5078e-05 | 3350 | 0.065372 | 3428 | 2.2981e-06 | 0.00018615 | 3483 |  | 2809
28 | RALSTON 110148936 | 24141101 | RALSTON 1101 | 48936 | FALSE | 9703.0008 | 7437.214 | 4.6223 | 86 | 3.4701e-05 | 3355 | 0.066043 | 3210 | 2.2943e-06 | 0.00019731 | 3484 | 0.08 | 1663
6723 | VALLEY VIEW 1106P128 | 14341106 | VALLEY VIEW 1106 | P128 | TRUE | 4067.7934 | 190.9091 | 0.11865 | 31 | 3.4672e-05 | 3357 | 0.065272 | 3471 | 2.2678e-06 | 7.0301e-05 | 3485 | 0.03 | 2403
6528 | LAS GALLINAS A 1106206332 | 42991106 | LAS GALLINAS A 1106 | 206332 | TRUE | 973.8303 | 488.8653 | 0.30383 | 7 | 3.1898e-05 | 3402 | 0.072747 | 2939 | 2.2569e-06 | 1.5798e-05 | 3486 |  | 3039
2106 | SPRUCE 0402BR304 | 13340402 | SPRUCE 0402 | BR304 | FALSE | 5760.7882 | 2392.7287 | 1.4871 | 53 | 3.4151e-05 | 3368 | 0.06568 | 3316 | 2.2492e-06 | 0.00011921 | 3487 | 0.08 | 1595
3661 | LAS GALLINAS A 1106685656 | 42991106 | LAS GALLINAS A 1106 | 685656 | FALSE | 5880.2294 | 1923.4165 | 1.1954 | 43 | 3.4111e-05 | 3369 | 0.06533 | 3449 | 2.2325e-06 | 9.5996e-05 | 3488 |  | 2845
3471 | LOS GATOS 110160136 | 82021101 | LOS GATOS 1101 | 60136 | TRUE | 6522.6172 | 0 | 0 | 57 | 3.4156e-05 | 3367 | 0.065147 | 3622 | 2.2252e-06 | 0.00012684 | 3489 |  | 2829
4292 | EMERALD LAKE 04028872 | 24080402 | EMERALD LAKE 0402 | 8872 | FALSE | 9042.2667 | 7244.0552 | 4.5022 | 77 | 3.3183e-05 | 3382 | 0.066165 | 3180 | 2.2015e-06 | 0.00016952 | 3490 | 0.09 | 1565
1116 | SNEATH LANE 110168070 | 22721101 | SNEATH LANE 1101 | 68070 | TRUE | 3445.6939 | 373.7094 | 0.23226 | 30 | 3.3642e-05 | 3372 | 0.065233 | 3488 | 2.1953e-06 | 6.5858e-05 | 3491 | 0.02 | 2503
9555 | IGNACIO 1103504941 | 42481103 | IGNACIO 1103 | 504941 | TRUE | 1025.616 | 663.24 | 0.41221 | 6 | 3.3217e-05 | 3381 | 0.065578 | 3339 | 2.194e-06 | 1.3164e-05 | 3492 |  | 3375
4494 | VIEJO 22019704 | 182852201 | VIEJO 2201 | 9704 | TRUE | 4114.9938 | 786.5986 | 0.48887 | 29 | 3.3423e-05 | 3377 | 0.065369 | 3429 | 2.1872e-06 | 6.3429e-05 | 3493 | 0.4 | 944
3505 | WOODSIDE 11049030 | 24251104 | WOODSIDE 1104 | 9030 | FALSE | 4149.4333 | 3272.4558 | 2.0338 | 37 | 3.3072e-05 | 3384 | 0.06605 | 3209 | 2.1865e-06 | 8.0902e-05 | 3494 | 0.1 | 1476
4601 | HATTON 11022070 | 182291102 | HATTON 1102 | 2070 | TRUE | 3077.1707 | 843.4628 | 0.52422 | 26 | 3.3159e-05 | 3383 | 0.065444 | 3398 | 2.1767e-06 | 5.6595e-05 | 3495 | 0.04 | 2156
10245 | GREENBRAE 1104972264 | 43091104 | GREENBRAE 1104 | 972264 | TRUE | 337.1983 | 0 | 0 | 4 | 3.3356e-05 | 3379 | 0.065151 | 3575 | 2.1732e-06 | 8.6927e-06 | 3496 |  | 3520
6525 | HAMILTON BRANCH 11012082 | 102361101 | HAMILTON BRANCH 1101 | 2082 | FALSE | 4925.5933 | 2445.1965 | 1.5197 | 46 | 3.2758e-05 | 3390 | 0.065762 | 3292 | 2.1552e-06 | 9.9139e-05 | 3497 | 0.08 | 1612
7268 | HICKS 1116203897 | 83431116 | HICKS 1116 | 203897 | TRUE | 1017.3713 | 367.9073 | 0.22866 | 9 | 3.2839e-05 | 3388 | 0.065433 | 3405 | 2.1509e-06 | 1.9358e-05 | 3498 |  | 3108
5472 | CHESTER 1101656108 | 103181101 | CHESTER 1101 | 656108 | TRUE | 1195.0984 | 838.7097 | 0.52126 | 10 | 3.2603e-05 | 3392 | 0.065918 | 3240 | 2.1478e-06 | 2.1478e-05 | 3499 |  | 2956
659 | EL CERRITO G 1112BR196 | 12501112 | EL CERRITO G 1112 | BR196 | TRUE | 5817.7228 | 0 | 0 | 51 | 3.2633e-05 | 3391 | 0.065172 | 3540 | 2.127e-06 | 0.00010848 | 3500 | 0.05 | 1940
286 | OAKLAND X 1106CB | 12541106 | OAKLAND X 1106 | CB | FALSE | 15907.2746 | 5284.9861 | 3.2846 | 136 | 3.2105e-05 | 3399 | 0.065515 | 3363 | 2.1195e-06 | 0.00028825 | 3501 | 0.06 | 1835
3401 | VIEJO 22029104 | 182852202 | VIEJO 2202 | 9104 | FALSE | 9586.0766 | 9148.567 | 5.6859 | 79 | 3.1817e-05 | 3404 | 0.066367 | 3133 | 2.113e-06 | 0.00016692 | 3502 | 0.18 | 1218
617 | OAK 0401CB | 12600401 | OAK 0401 | CB | FALSE | 8716.4726 | 5585.5806 | 3.4715 | 68 | 3.153e-05 | 3408 | 0.06596 | 3231 | 2.0871e-06 | 0.00014192 | 3503 | 0.09 | 1539
5991 | VIEJO 22019698 | 182852201 | VIEJO 2201 | 9698 | TRUE | 1062.5186 | 929.6624 | 0.57779 | 10 | 3.1068e-05 | 3415 | 0.066303 | 3148 | 2.0607e-06 | 2.0607e-05 | 3504 | 0.07 | 1771
2044 | SPRUCE 0401BR316 | 13340401 | SPRUCE 0401 | BR316 | FALSE | 6608.6922 | 6608.6922 | 4.1073 | 56 | 3.0991e-05 | 3416 | 0.066432 | 2970 | 2.0588e-06 | 0.00011529 | 3505 | 0.12 | 1388
7179 | EL CERRITO G 111257953 | 12501112 | EL CERRITO G 1112 | 57953 | TRUE | 1217.1907 | 353.2769 | 0.21956 | 11 | 3.1168e-05 | 3413 | 0.065497 | 3370 | 2.0515e-06 | 2.2566e-05 | 3506 | 0.34 | 977
5036 | FRANKLIN 1104CB | 13921104 | FRANKLIN 1104 | CB | TRUE | 8361.6686 | 466.2641 | 0.28979 | 63 | 3.1091e-05 | 3414 | 0.065209 | 3507 | 2.0367e-06 | 0.00012831 | 3507 | 0.03 | 2390
6325 | LOS GATOS 1108CB | 82021108 | LOS GATOS 1108 | CB | TRUE | 1166.6657 | 0 | 0 | 15 | 3.1212e-05 | 3412 | 0.065147 | 3617 | 2.0334e-06 | 3.0501e-05 | 3508 |  | 3022
6874 | LOS GATOS 1102CB | 82021102 | LOS GATOS 1102 | CB | TRUE | 7506.165 | 0 | 0 | 70 | 3.0936e-05 | 3418 | 0.065147 | 3616 | 2.0154e-06 | 0.00014108 | 3509 | 0.05 | 2064
1424 | PACIFICA 1103CB | 22811103 | PACIFICA 1103 | CB | TRUE | 7799.5565 | 109.5296 | 0.068073 | 62 | 3.075e-05 | 3420 | 0.065188 | 3523 | 2.0046e-06 | 0.00012428 | 3510 | 0.02 | 2475
10000 | ALTO 1125781759 | 42031125 | ALTO 1125 | 781759 | TRUE | 264.5561 | 210.4887 | 0.13082 | 4 | 3.0572e-05 | 3422 | 0.065789 | 3288 | 2.0026e-06 | 8.0105e-06 | 3511 |  | 3469
254 | HICKS 1116CB | 83431116 | HICKS 1116 | CB | TRUE | 22837.5991 | 336.1648 | 0.20893 | 165 | 2.9963e-05 | 3426 | 0.065178 | 3539 | 1.9553e-06 | 0.00032262 | 3512 | 0.04 | 2128
1238 | STAFFORD 11021019 | 43201102 | STAFFORD 1102 | 1019 | TRUE | 1173.8689 | 432.0709 | 0.26853 | 10 | 2.9828e-05 | 3428 | 0.065279 | 3468 | 1.946e-06 | 1.946e-05 | 3513 | 0.07 | 1695
10590 | CHESTER 1102546744 | 103181102 | CHESTER 1102 | 546744 | TRUE | 633.1716 | 428.8696 | 0.26654 | 7 | 2.921e-05 | 3435 | 0.065882 | 3248 | 1.934e-06 | 1.3538e-05 | 3514 |  | 3577
6891 | ALTO 1124994213 | 42031124 | ALTO 1124 | 994213 | TRUE | 860.1534 | 198.7798 | 0.12354 | 8 | 2.9167e-05 | 3437 | 0.065311 | 3455 | 1.9051e-06 | 1.5241e-05 | 3515 |  | 3071
9434 | BERKELEY F 1105849701 | 12061105 | BERKELEY F 1105 | 849701 | TRUE | 220.6039 | 213.7724 | 0.13286 | 2 | 2.8441e-05 | 3447 | 0.065789 | 3283 | 1.8894e-06 | 3.7788e-06 | 3516 |  | 3358
6092 | VIEJO 22049540 | 182852204 | VIEJO 2204 | 9540 | FALSE | 3592.089 | 2319.7097 | 1.4417 | 32 | 2.8532e-05 | 3444 | 0.06587 | 3251 | 1.8885e-06 | 6.0431e-05 | 3517 | 0.02 | 2557
9394 | ALTO 1124884949 | 42031124 | ALTO 1124 | 884949 | TRUE | 693.01 | 312.7335 | 0.19437 | 5 | 2.8569e-05 | 3443 | 0.065663 | 3319 | 1.8768e-06 | 9.3841e-06 | 3518 |  | 3352
8014 | WALDO 0401965216 | 13350401 | WALDO 0401 | 965216 | FALSE | 2651.8859 | 2642.7419 | 1.6425 | 21 | 2.8136e-05 | 3457 | 0.066371 | 3131 | 1.868e-06 | 3.9227e-05 | 3519 |  | 3185
4883 | LAS PULGAS 0401104588 | 24120401 | LAS PULGAS 0401 | 104588 | TRUE | 1238.8359 | 581.4114 | 0.36135 | 11 | 2.8291e-05 | 3451 | 0.065731 | 3301 | 1.8653e-06 | 2.0518e-05 | 3520 |  | 2924
8033 | MORAGA 110531512 | 13801105 | MORAGA 1105 | 31512 | TRUE | 3255.9931 | 0 | 0 | 29 | 2.8486e-05 | 3446 | 0.065148 | 3589 | 1.8558e-06 | 5.3819e-05 | 3521 | 6.49 | 467
4423 | SAN RAFAEL 1105344 | 42011105 | SAN RAFAEL 1105 | 344 | FALSE | 12052.7047 | 1314.7551 | 0.81713 | 97 | 2.8339e-05 | 3449 | 0.065283 | 3467 | 1.8552e-06 | 0.00017996 | 3522 | 0.06 | 1814
3011 | PERRY 1101W52 | 183071101 | PERRY 1101 | W52 | FALSE | 6677.88 | 5033.3373 | 3.1282 | 51 | 2.807e-05 | 3459 | 0.066004 | 3224 | 1.8539e-06 | 9.4548e-05 | 3523 | 0.05 | 1977
2767 | EL CERRITO G 1112BR180 | 12501112 | EL CERRITO G 1112 | BR180 | TRUE | 3108.6276 | 675.0712 | 0.41956 | 25 | 2.814e-05 | 3456 | 0.065507 | 3367 | 1.8513e-06 | 4.6282e-05 | 3524 | 3.92 | 531
7505 | EDES 1112CR306 | 13681112 | EDES 1112 | CR306 | FALSE | 1619.5833 | 1619.5833 | 1.0066 | 16 | 2.7663e-05 | 3463 | 0.066432 | 2950 | 1.8377e-06 | 2.9404e-05 | 3525 | 0.04 | 2175
349 | ALHAMBRA 1102CB | 14101102 | ALHAMBRA 1102 | CB | TRUE | 9244.1392 | 431.1151 | 0.26794 | 75 | 2.7307e-05 | 3468 | 0.065217 | 3501 | 1.7835e-06 | 0.00013376 | 3526 | 0.02 | 2558
5900 | CHESTER 1102CB | 103181102 | CHESTER 1102 | CB | TRUE | 4463.0648 | 40.2966 | 0.025045 | 38 | 2.7246e-05 | 3469 | 0.065182 | 3535 | 1.7766e-06 | 6.751e-05 | 3527 | 0.04 | 2082
6024 | WOODSIDE 11028862 | 24251102 | WOODSIDE 1102 | 8862 | TRUE | 4562.4649 | 0 | 0 | 38 | 2.7115e-05 | 3471 | 0.065147 | 3615 | 1.7665e-06 | 6.7125e-05 | 3528 | 0.02 | 2559
4122 | BURNEY 110257046 | 103311102 | BURNEY 1102 | 57046 | TRUE | 1135.0639 | 48.9091 | 0.030397 | 12 | 2.6931e-05 | 3474 | 0.065362 | 3431 | 1.7587e-06 | 2.1104e-05 | 3529 |  | 2873
2110 | CASTRO VALLEY 1108MR205 | 14091108 | CASTRO VALLEY 1108 | MR205 | TRUE | 8740.8692 | 0 | 0 | 73 | 2.6763e-05 | 3475 | 0.065182 | 3534 | 1.7478e-06 | 0.00012759 | 3530 |  | 2764
2448 | VIEJO 22029112 | 182852202 | VIEJO 2202 | 9112 | FALSE | 5302.286 | 1359.4094 | 0.84488 | 43 | 2.6492e-05 | 3480 | 0.065387 | 3422 | 1.7421e-06 | 7.4909e-05 | 3531 | 0.55 | 872
8885 | EL CERRITO G 1110BR236 | 12501110 | EL CERRITO G 1110 | BR236 | TRUE | 850.4173 | 819.8964 | 0.50957 | 7 | 2.6231e-05 | 3484 | 0.066065 | 3207 | 1.7373e-06 | 1.2161e-05 | 3532 | 0.06 | 1860
7598 | ALTO 1123820379 | 42031123 | ALTO 1123 | 820379 | TRUE | 298.2228 | 245.2911 | 0.15245 | 2 | 2.6136e-05 | 3485 | 0.066431 | 3032 | 1.7362e-06 | 3.4724e-06 | 3533 |  | 3139
1294 | VIEJO 2203573610 | 182852203 | VIEJO 2203 | 573610 | TRUE | 5029.4735 | 0 | 0 | 41 | 2.6462e-05 | 3481 | 0.065179 | 3538 | 1.7259e-06 | 7.0764e-05 | 3534 |  | 2722
2844 | SAN CARLOS 11039148 | 24181103 | SAN CARLOS 1103 | 9148 | TRUE | 6634.7635 | 0 | 0 | 51 | 2.6423e-05 | 3482 | 0.065147 | 3618 | 1.7214e-06 | 8.7791e-05 | 3535 | 0.07 | 1762
469 | VIEJO 22039094 | 182852203 | VIEJO 2203 | 9094 | TRUE | 4020.7215 | 160.2742 | 0.099611 | 32 | 2.6274e-05 | 3483 | 0.065228 | 3493 | 1.7132e-06 | 5.4823e-05 | 3536 | 0.02 | 2542
7298 | VIEJO 22032634 | 182852203 | VIEJO 2203 | 2634 | TRUE | 2692.6366 | 0 | 0 | 23 | 2.5666e-05 | 3490 | 0.065148 | 3596 | 1.6721e-06 | 3.8458e-05 | 3537 | 0.02 | 2497
8157 | OAKLAND J 1105CR150 | 12091105 | OAKLAND J 1105 | CR150 | TRUE | 755.1885 | 348.5421 | 0.21662 | 6 | 2.5203e-05 | 3494 | 0.065789 | 3290 | 1.667e-06 | 1.0002e-05 | 3538 | 0.05 | 1981
7733 | FORT BRAGG A 1103CB | 42761103 | FORT BRAGG A 1103 | CB | TRUE | 3993.2278 | 151.4693 | 0.094139 | 40 | 2.5491e-05 | 3491 | 0.06518 | 3537 | 1.6633e-06 | 6.6534e-05 | 3539 |  | 3157
9029 | MORGAN HILL 2105375239 | 83242105 | MORGAN HILL 2105 | 375239 | TRUE | 343.55 | 145.1624 | 0.090219 | 4 | 2.5051e-05 | 3495 | 0.065468 | 3385 | 1.6455e-06 | 6.5821e-06 | 3540 |  | 3299
9198 | MORGAN HILL 2105345099 | 83242105 | MORGAN HILL 2105 | 345099 | TRUE | 497.3995 | 293.3262 | 0.1823 | 5 | 2.4872e-05 | 3496 | 0.065404 | 3416 | 1.6312e-06 | 8.156e-06 | 3541 |  | 3324
8274 | SALT SPRINGS 21013116 | 163692101 | SALT SPRINGS 2101 | 3116 | FALSE | 1685.1043 | 1250.9687 | 0.77748 | 10 | 2.4549e-05 | 3500 | 0.066175 | 3176 | 1.6267e-06 | 1.6267e-05 | 3542 | 0.01 | 2592
1788 | BERKELEY F 0402502466 | 12060402 | BERKELEY F 0402 | 502466 | TRUE | 854.2839 | 226.0238 | 0.14047 | 10 | 2.4427e-05 | 3501 | 0.065532 | 3357 | 1.6151e-06 | 1.6151e-05 | 3543 |  | 2745
2459 | BERKELEY F 1105CB | 12061105 | BERKELEY F 1105 | CB | FALSE | 12969.6445 | 1669.1452 | 1.0374 | 103 | 2.4362e-05 | 3504 | 0.065322 | 3453 | 1.6033e-06 | 0.00016514 | 3544 | 0.03 | 2287
179 | EL CERRITO G 1108BR346 | 12501108 | EL CERRITO G 1108 | BR346 | TRUE | 11386.6089 | 0 | 0 | 102 | 2.4397e-05 | 3502 | 0.065147 | 3620 | 1.5894e-06 | 0.00016212 | 3545 | 0.02 | 2439
1332 | HOLLYWOOD 0401CB | 13170401 | HOLLYWOOD 0401 | CB | FALSE | 8520.938 | 4604.9325 | 2.862 | 70 | 2.3671e-05 | 3507 | 0.065808 | 3264 | 1.5619e-06 | 0.00010933 | 3546 | 0.05 | 2038
6502 | ESTUDILLO 0401850884 | 13480401 | ESTUDILLO 0401 | 850884 | FALSE | 2534.335 | 1368.1711 | 0.85032 | 19 | 2.3486e-05 | 3510 | 0.065756 | 3294 | 1.5552e-06 | 2.9549e-05 | 3547 |  | 3036
1386 | PACIFICA 1103915474 | 22811103 | PACIFICA 1103 | 915474 | TRUE | 13475.5148 | 697.4237 | 0.43345 | 98 | 2.3059e-05 | 3511 | 0.065213 | 3504 | 1.5073e-06 | 0.00014771 | 3548 |  | 2723
1210 | COTATI 110283200 | 42271102 | COTATI 1102 | 83200 | TRUE | 4654.5591 | 0 | 0 | 48 | 2.2575e-05 | 3514 | 0.065158 | 3558 | 1.471e-06 | 7.0606e-05 | 3549 |  | 2716
7453 | SNEATH LANE 110748338 | 22721107 | SNEATH LANE 1107 | 48338 | TRUE | 1760.6636 | 181.1517 | 0.11259 | 17 | 2.2364e-05 | 3515 | 0.065147 | 3613 | 1.4569e-06 | 2.4768e-05 | 3550 | 0.03 | 2329
4821 | RALSTON 11029126 | 24141102 | RALSTON 1102 | 9126 | FALSE | 3038.2902 | 1621.4045 | 1.0077 | 25 | 2.1702e-05 | 3526 | 0.065969 | 3226 | 1.4329e-06 | 3.5823e-05 | 3551 | 0.04 | 2080
7237 | PACIFIC GROVE 04222614 | 182440422 | PACIFIC GROVE 0422 | 2614 | FALSE | 3446.6772 | 1037.2147 | 0.64463 | 28 | 2.1909e-05 | 3521 | 0.065331 | 3444 | 1.4317e-06 | 4.0087e-05 | 3552 | 0.03 | 2331
1100 | DEL MONTE 210386496 | 182222103 | DEL MONTE 2103 | 86496 | FALSE | 10364.0845 | 1600.54 | 0.99474 | 94 | 2.1714e-05 | 3525 | 0.065366 | 3430 | 1.4269e-06 | 0.00013413 | 3553 | 0.02 | 2498
8851 | SAN CARLOS 1103888954 | 24181103 | SAN CARLOS 1103 | 888954 | TRUE | 504.7129 | 0 | 0 | 6 | 2.1724e-05 | 3524 | 0.065147 | 3623 | 1.4152e-06 | 8.4914e-06 | 3554 |  | 3272
2645 | OAKLAND J 1106CR164 | 12091106 | OAKLAND J 1106 | CR164 | FALSE | 10563.0436 | 2405.3877 | 1.495 | 85 | 2.1366e-05 | 3530 | 0.065434 | 3402 | 1.4079e-06 | 0.00011967 | 3555 | 0.03 | 2312
7417 | EL CERRITO G 1112209865 | 12501112 | EL CERRITO G 1112 | 209865 | TRUE | 1489.582 | 423.0102 | 0.2629 | 11 | 2.1415e-05 | 3529 | 0.065497 | 3369 | 1.4074e-06 | 1.5482e-05 | 3556 |  | 3125
45 | OAKLAND J 1105153228 | 12091105 | OAKLAND J 1105 | 153228 | TRUE | 6680.4391 | 463.496 | 0.28806 | 54 | 2.1538e-05 | 3528 | 0.065195 | 3513 | 1.4041e-06 | 7.5821e-05 | 3557 | 0.02 | 2445
8437 | SWIFT 2109XR300 | 83392109 | SWIFT 2109 | XR300 | TRUE | 1391.3933 | 526.7556 | 0.32738 | 14 | 2.1221e-05 | 3531 | 0.065331 | 3446 | 1.3951e-06 | 1.9531e-05 | 3558 | 0.04 | 2106
10517 | EL CERRITO G 1110173396 | 12501110 | EL CERRITO G 1110 | 173396 | TRUE | 265.7346 | 265.7346 | 0.16516 | 3 | 2.0973e-05 | 3534 | 0.066004 | 3220 | 1.3889e-06 | 4.1666e-06 | 3559 |  | 3563
9170 | SAN CARLOS 1103313472 | 24181103 | SAN CARLOS 1103 | 313472 | TRUE | 1178.1951 | 43.1608 | 0.026825 | 9 | 2.0676e-05 | 3537 | 0.06529 | 3465 | 1.3509e-06 | 1.2158e-05 | 3560 |  | 3319
9880 | IGNACIO 1103151462 | 42481103 | IGNACIO 1103 | 151462 | TRUE | 247.7748 | 247.7748 | 0.15399 | 3 | 2.0466e-05 | 3540 | 0.066005 | 3216 | 1.3417e-06 | 4.025e-06 | 3561 |  | 3443
8103 | WOODSIDE 1102472928 | 24251102 | WOODSIDE 1102 | 472928 | TRUE | 1622.1027 | 124.8253 | 0.077579 | 14 | 2.0412e-05 | 3541 | 0.065331 | 3448 | 1.3331e-06 | 1.8663e-05 | 3562 |  | 3192
657 | OAKLAND J 1102CR252 | 12091102 | OAKLAND J 1102 | CR252 | FALSE | 9962.669 | 1765.2604 | 1.0971 | 92 | 2.0001e-05 | 3543 | 0.065384 | 3423 | 1.3184e-06 | 0.0001213 | 3563 | 0.03 | 2364
146 | CASTRO VALLEY 1110MR379 | 14091110 | CASTRO VALLEY 1110 | MR379 | FALSE | 2535.6763 | 1749.5827 | 1.0874 | 22 | 1.987e-05 | 3545 | 0.065965 | 3229 | 1.3088e-06 | 2.8794e-05 | 3564 |  | 2658
9441 | MORRO BAY 11013487 | 183011101 | MORRO BAY 1101 | 3487 | TRUE | 2909.578 | 0 | 0 | 20 | 1.9374e-05 | 3547 | 0.065147 | 3626 | 1.2622e-06 | 2.5244e-05 | 3565 |  | 3359
5751 | FORT BRAGG A 1104CB | 42761104 | FORT BRAGG A 1104 | CB | TRUE | 4613.0306 | 118.7443 | 0.0738 | 41 | 1.9334e-05 | 3548 | 0.065148 | 3592 | 1.2596e-06 | 5.1642e-05 | 3566 | 0.02 | 2443
8075 | ALTO 1124246034 | 42031124 | ALTO 1124 | 246034 | TRUE | 413.5355 | 202.2758 | 0.12572 | 4 | 1.9193e-05 | 3549 | 0.065471 | 3380 | 1.2578e-06 | 5.0314e-06 | 3567 |  | 3188
447 | OCEANO 1105V44 | 182601105 | OCEANO 1105 | V44 | FALSE | 1767.9988 | 1259.7645 | 0.78295 | 17 | 1.8999e-05 | 3551 | 0.065827 | 3260 | 1.2575e-06 | 2.1378e-05 | 3568 | 0.03 | 2281
3262 | OAKLAND J 1106CR330 | 12091106 | OAKLAND J 1106 | CR330 | FALSE | 3874.576 | 1155.5838 | 0.7182 | 31 | 1.8986e-05 | 3552 | 0.065438 | 3399 | 1.2463e-06 | 3.8635e-05 | 3569 | 0.03 | 2322
650 | OAKLAND J 1116CR328 | 12091116 | OAKLAND J 1116 | CR328 | TRUE | 7907.5061 | 956.1241 | 0.59424 | 68 | 1.9049e-05 | 3550 | 0.065298 | 3462 | 1.2458e-06 | 8.4712e-05 | 3570 |  | 2687
4530 | VIEJO 220285904 | 182852202 | VIEJO 2202 | 85904 | FALSE | 3179.0036 | 1684.9898 | 1.0472 | 24 | 1.8827e-05 | 3555 | 0.065629 | 3329 | 1.2443e-06 | 2.9864e-05 | 3571 | 0.03 | 2340
4873 | ALHAMBRA 110213333 | 14101102 | ALHAMBRA 1102 | 13333 | TRUE | 480.3389 | 70.7861 | 0.043994 | 4 | 1.8911e-05 | 3554 | 0.065469 | 3382 | 1.2398e-06 | 4.9594e-06 | 3572 | 0.02 | 2476
5686 | MORRO BAY 1102V80 | 183011102 | MORRO BAY 1102 | V80 | TRUE | 3197.8948 | 222.7519 | 0.13844 | 28 | 1.8567e-05 | 3557 | 0.065193 | 3516 | 1.2121e-06 | 3.3939e-05 | 3573 |  | 2973
495 | BELMONT 11109090 | 24031110 | BELMONT 1110 | 9090 | TRUE | 4202.8057 | 0 | 0 | 38 | 1.848e-05 | 3559 | 0.065147 | 3627 | 1.2039e-06 | 4.5748e-05 | 3574 |  | 2679
1032 | ALTO 1123CB | 42031123 | ALTO 1123 | CB | TRUE | 9405.5468 | 893.6462 | 0.5554 | 84 | 1.7813e-05 | 3561 | 0.065258 | 3477 | 1.1648e-06 | 9.7839e-05 | 3575 | 0.03 | 2356
4356 | BELMONT 11038956 | 24031103 | BELMONT 1103 | 8956 | TRUE | 2231.1917 | 474.6132 | 0.29497 | 18 | 1.7617e-05 | 3564 | 0.065361 | 3432 | 1.1529e-06 | 2.0752e-05 | 3576 |  | 2884
3862 | GREENBRAE 1104751 | 43091104 | GREENBRAE 1104 | 751 | TRUE | 4384.8994 | 264.612 | 0.16446 | 31 | 1.7653e-05 | 3563 | 0.065234 | 3487 | 1.1521e-06 | 3.5714e-05 | 3577 | 0.02 | 2530
3522 | CHESTER 1101CB | 103181101 | CHESTER 1101 | CB | TRUE | 8238.1953 | 128.9588 | 0.080148 | 69 | 1.7565e-05 | 3565 | 0.065167 | 3548 | 1.1453e-06 | 7.9023e-05 | 3578 | 0.04 | 2203
1797 | BERKELEY F 1103BR110 | 12061103 | BERKELEY F 1103 | BR110 | TRUE | 5064.9775 | 0 | 0 | 45 | 1.7521e-05 | 3566 | 0.065147 | 3628 | 1.1415e-06 | 5.1365e-05 | 3579 | 18.55 | 320
3950 | MONTEREY 04022644 | 182090402 | MONTEREY 0402 | 2644 | FALSE | 2922.7748 | 1828.1218 | 1.1362 | 23 | 1.7252e-05 | 3567 | 0.065706 | 3306 | 1.1355e-06 | 2.6115e-05 | 3580 | 0.03 | 2385
3110 | KIRKER 2104CB | 14452104 | KIRKER 2104 | CB | TRUE | 16910.3925 | 74.5132 | 0.04631 | 140 | 1.6863e-05 | 3571 | 0.065612 | 3334 | 1.1257e-06 | 0.0001576 | 3581 |  | 2813
973 | DEL MONTE 110138582 | 182221101 | DEL MONTE 1101 | 38582 | TRUE | 8624.1276 | 853.8778 | 0.53069 | 53 | 1.7201e-05 | 3569 | 0.065245 | 3483 | 1.1245e-06 | 5.9598e-05 | 3582 |  | 2701
72 | PACIFICA 11026783 | 22811102 | PACIFICA 1102 | 6783 | TRUE | 6579.5365 | 0 | 0 | 50 | 1.7237e-05 | 3568 | 0.065147 | 3629 | 1.1229e-06 | 5.6147e-05 | 3583 | 1.8 | 643
6129 | PERRY 1101W12 | 183071101 | PERRY 1101 | W12 | FALSE | 10251.7677 | 6046.1264 | 3.7577 | 70 | 1.562e-05 | 3581 | 0.06699 | 2947 | 1.0833e-06 | 7.5829e-05 | 3584 | 0.07 | 1755
3828 | ALTO 1120500 | 42031120 | ALTO 1120 | 500 | TRUE | 5066.4275 | 426.2211 | 0.2649 | 39 | 1.6529e-05 | 3573 | 0.065312 | 3454 | 1.0777e-06 | 4.203e-05 | 3585 |  | 2856
2036 | SAN LEANDRO U 1114MR218 | 13111114 | SAN LEANDRO U 1114 | MR218 | FALSE | 18150.1664 | 10386.8132 | 6.4554 | 134 | 1.6173e-05 | 3577 | 0.065722 | 3303 | 1.0693e-06 | 0.00014329 | 3586 | 0.06 | 1868
66 | OAKLAND X 1105CB | 12541105 | OAKLAND X 1105 | CB | FALSE | 18622.3449 | 1675.1277 | 1.0411 | 153 | 1.6122e-05 | 3579 | 0.065231 | 3490 | 1.0578e-06 | 0.00016184 | 3587 | 0.03 | 2299
3740 | BERKELEY F 0402CB | 12060402 | BERKELEY F 0402 | CB | TRUE | 2575.0657 | 47.0231 | 0.029225 | 21 | 1.6197e-05 | 3575 | 0.065147 | 3630 | 1.0552e-06 | 2.2159e-05 | 3588 | 0.03 | 2266
2665 | VALLEY VIEW 1105P190 | 14341105 | VALLEY VIEW 1105 | P190 | TRUE | 3318.5959 | 0 | 0 | 28 | 1.6177e-05 | 3576 | 0.065148 | 3590 | 1.0539e-06 | 2.951e-05 | 3589 | 0.06 | 1830
62 | BAY MEADOWS 2102CB | 24012102 | BAY MEADOWS 2102 | CB | TRUE | 11158.113 | 159.3502 | 0.099037 | 95 | 1.5874e-05 | 3580 | 0.065161 | 3554 | 1.0373e-06 | 9.8546e-05 | 3590 |  | 2653
3225 | VALLEY VIEW 1105CB | 14341105 | VALLEY VIEW 1105 | CB | TRUE | 7478.2552 | 0 | 0 | 59 | 1.558e-05 | 3582 | 0.06517 | 3542 | 1.0169e-06 | 5.9995e-05 | 3591 | 0.04 | 2225
1682 | OAKLAND J 1118CR198 | 12091118 | OAKLAND J 1118 | CR198 | TRUE | 8475.9687 | 515.4771 | 0.32037 | 70 | 1.5357e-05 | 3584 | 0.065239 | 3486 | 1.006e-06 | 7.0418e-05 | 3592 | 0.02 | 2547
6551 | EL CERRITO G 1111760530 | 12501111 | EL CERRITO G 1111 | 760530 | TRUE | 2038.4891 | 342.5788 | 0.21291 | 13 | 1.4653e-05 | 3588 | 0.065542 | 3354 | 9.624e-07 | 1.2511e-05 | 3593 |  | 3041
838 | MORRO BAY 1102W22 | 183011102 | MORRO BAY 1102 | W22 | FALSE | 10106.4598 | 4174.2289 | 2.5943 | 85 | 1.451e-05 | 3590 | 0.065661 | 3323 | 9.5877e-07 | 8.1495e-05 | 3594 | 0.1 | 1467
2660 | CASTRO VALLEY 1105MR201 | 14091105 | CASTRO VALLEY 1105 | MR201 | FALSE | 13962.3911 | 2014.3888 | 1.252 | 112 | 1.4628e-05 | 3589 | 0.065296 | 3463 | 9.5698e-07 | 0.00010718 | 3595 |  | 2794
6961 | SAUSALITO 11021224 | 42491102 | SAUSALITO 1102 | 1224 | TRUE | 3249.7676 | 17.2769 | 0.010738 | 29 | 1.4357e-05 | 3591 | 0.065191 | 3519 | 9.3531e-07 | 2.7124e-05 | 3596 | 0.02 | 2522
2515 | EL CERRITO G 1113CB | 12501113 | EL CERRITO G 1113 | CB | TRUE | 6943.4772 | 158.1749 | 0.098306 | 63 | 1.4057e-05 | 3592 | 0.065208 | 3508 | 9.1814e-07 | 5.7843e-05 | 3597 | 0.06 | 1787
3037 | EL CERRITO G 1108CB | 12501108 | EL CERRITO G 1108 | CB | TRUE | 11783.4703 | 4.3429 | 0.0026991 | 99 | 1.3941e-05 | 3593 | 0.065147 | 3631 | 9.0819e-07 | 8.9911e-05 | 3598 | 0.02 | 2417
2758 | VALLEY VIEW 1105P124 | 14341105 | VALLEY VIEW 1105 | P124 | TRUE | 5089.5347 | 0 | 0 | 43 | 1.3878e-05 | 3594 | 0.065148 | 3584 | 9.0411e-07 | 3.8877e-05 | 3599 | 0.02 | 2525
3672 | EDES 1112CB | 13681112 | EDES 1112 | CB | TRUE | 911.838 | 70.4619 | 0.043792 | 16 | 1.3748e-05 | 3595 | 0.065227 | 3494 | 8.9903e-07 | 1.4384e-05 | 3600 | 0.03 | 2275
2376 | VIEJO 22049110 | 182852204 | VIEJO 2204 | 9110 | TRUE | 6943.3735 | 472.9116 | 0.29392 | 58 | 1.3463e-05 | 3596 | 0.06517 | 3544 | 8.7872e-07 | 5.0966e-05 | 3601 | 0.03 | 2318
552 | ALTO 112088190 | 42031120 | ALTO 1120 | 88190 | TRUE | 4658.7637 | 163.0348 | 0.10133 | 34 | 1.3144e-05 | 3598 | 0.065223 | 3499 | 8.5763e-07 | 2.9159e-05 | 3602 | 0.01 | 2609
5498 | VIEJO 22049440 | 182852204 | VIEJO 2204 | 9440 | TRUE | 5507.5 | 123.7395 | 0.076905 | 55 | 1.3106e-05 | 3599 | 0.065171 | 3541 | 8.5438e-07 | 4.6991e-05 | 3603 |  | 2959
10858 | SOLEDAD 2101125484 | 182052101 | SOLEDAD 2101 | 125484 | FALSE | 2451.828 | 1202.5462 | 0.74739 | 4 | 1.3036e-05 | 3600 | 11.9509 | 2589 | 8.4928e-07 | 3.3971e-06 | 3604 |  | 3614
10655 | OCEANO 1104793774 | 182601104 | OCEANO 1104 | 793774 | TRUE | 378.8633 | 111.8888 | 0.069539 | 3 | 1.2894e-05 | 3602 | 0.065147 | 3633 | 8.3998e-07 | 2.52e-06 | 3605 |  | 3586
4160 | EL CERRITO G 1110CB | 12501110 | EL CERRITO G 1110 | CB | TRUE | 4157.1829 | 423.1153 | 0.26297 | 35 | 1.2627e-05 | 3603 | 0.065184 | 3531 | 8.2339e-07 | 2.8819e-05 | 3606 | 0.04 | 2089
5087 | EDES 1112714759 | 13681112 | EDES 1112 | 714759 | TRUE | 1469.7626 | 361.9191 | 0.22493 | 11 | 1.2348e-05 | 3605 | 0.065497 | 3372 | 8.1071e-07 | 8.9178e-06 | 3607 |  | 2936
2691 | BOSTON 0401CR242 | 13320401 | BOSTON 0401 | CR242 | TRUE | 7351.3672 | 499.489 | 0.31043 | 59 | 1.2355e-05 | 3604 | 0.065191 | 3520 | 8.0537e-07 | 4.7517e-05 | 3608 | 0.02 | 2462
425 | CASTRO VALLEY 1105MR236 | 14091105 | CASTRO VALLEY 1105 | MR236 | FALSE | 13624.1451 | 2212.8784 | 1.3753 | 112 | 1.2234e-05 | 3607 | 0.065342 | 3441 | 8.0193e-07 | 8.9816e-05 | 3609 |  | 2670
5569 | MORRO BAY 1101CB | 183011101 | MORRO BAY 1101 | CB | TRUE | 3472.0335 | 0 | 0 | 28 | 1.2296e-05 | 3606 | 0.065147 | 3624 | 8.0102e-07 | 2.2429e-05 | 3610 | 0.02 | 2412
513 | OAKLAND J 1116CB | 12091116 | OAKLAND J 1116 | CB | TRUE | 30164.8941 | 0 | 0 | 253 | 1.2121e-05 | 3608 | 0.065147 | 3612 | 7.8965e-07 | 0.00019978 | 3611 |  | 2681
4433 | MONTEREY 04012642 | 182090401 | MONTEREY 0401 | 2642 | TRUE | 3637.2616 | 0 | 0 | 28 | 1.2095e-05 | 3609 | 0.065148 | 3594 | 7.8793e-07 | 2.2062e-05 | 3612 | 0.02 | 2511
1060 | SAN LEANDRO U 1114MR545 | 13111114 | SAN LEANDRO U 1114 | MR545 | FALSE | 7246.1985 | 3496.0754 | 2.1728 | 66 | 1.1654e-05 | 3610 | 0.065789 | 3280 | 7.6919e-07 | 5.0766e-05 | 3613 | 0.06 | 1782
8159 | SAN LUIS OBISPO 1103191498 | 182631103 | SAN LUIS OBISPO 1103 | 191498 | TRUE | 267.6915 | 189.8568 | 0.118 | 2 | 1.1046e-05 | 3611 | 0.065789 | 3281 | 7.2794e-07 | 1.4559e-06 | 3614 |  | 3198
749 | WALDO 0401CB | 13350401 | WALDO 0401 | CB | TRUE | 6516.7767 | 0 | 0 | 56 | 1.0513e-05 | 3612 | 0.06517 | 3543 | 6.8547e-07 | 3.8386e-05 | 3615 | 0.03 | 2378
8960 | OCEANO 1104337754 | 182601104 | OCEANO 1104 | 337754 | TRUE | 259.7315 | 97.7177 | 0.060732 | 3 | 9.3717e-06 | 3613 | 0.065147 | 3606 | 6.1054e-07 | 1.8316e-06 | 3616 |  | 3283
11035 | SOLEDAD 2101404754 | 182052101 | SOLEDAD 2101 | 404754 | FALSE | 1404.0353 | 1388.0334 | 0.86267 | 2 | 8.7569e-06 | 3616 | 0.065789 | 3284 | 5.7048e-07 | 1.141e-06 | 3617 |  | 3630
2616 | DEL MONTE 21029060 | 182222102 | DEL MONTE 2102 | 9060 | FALSE | 14415.2582 | 1524.9134 | 0.94774 | 98 | 8.4533e-06 | 3617 | 0.065226 | 3496 | 5.5361e-07 | 5.4254e-05 | 3618 | 0.58 | 857
3316 | SAN LEANDRO U 1114501762 | 13111114 | SAN LEANDRO U 1114 | 501762 | TRUE | 2438.6275 | 775.0508 | 0.4817 | 23 | 8.4178e-06 | 3618 | 0.065482 | 3377 | 5.5098e-07 | 1.2672e-05 | 3619 |  | 2821
9297 | PACIFICA 1102934870 | 22811102 | PACIFICA 1102 | 934870 | TRUE | 804.8523 | 147.5524 | 0.091704 | 7 | 8.4048e-06 | 3619 | 0.065514 | 3365 | 5.496e-07 | 3.8472e-06 | 3620 |  | 3338
7940 | SAN LEANDRO U 1109CR284 | 13111109 | SAN LEANDRO U 1109 | CR284 | FALSE | 1550.6574 | 1235.8311 | 0.76807 | 14 | 7.7666e-06 | 3623 | 0.066065 | 3205 | 5.1364e-07 | 7.191e-06 | 3621 | 0.04 | 2148
3930 | SAN LEANDRO U 1109CR002 | 13111109 | SAN LEANDRO U 1109 | CR002 | TRUE | 1715.8521 | 269.8408 | 0.16771 | 16 | 7.83e-06 | 3620 | 0.065308 | 3461 | 5.1358e-07 | 8.2173e-06 | 3622 | 0.13 | 1341
5801 | BELMONT 1110330790 | 24031110 | BELMONT 1110 | 330790 | TRUE | 714.0791 | 199.5624 | 0.12403 | 8 | 7.7899e-06 | 3621 | 0.065468 | 3389 | 5.0999e-07 | 4.0799e-06 | 3623 |  | 2979
915 | WALDO 0402CB | 13350402 | WALDO 0402 | CB | TRUE | 3475.548 | 0 | 0 | 27 | 7.7732e-06 | 3622 | 0.065147 | 3610 | 5.064e-07 | 1.3673e-05 | 3624 | 0.05 | 1955
472 | BANCROFT 0401CB | 13030401 | BANCROFT 0401 | CB | TRUE | 13277.3465 | 69.3073 | 0.043075 | 103 | 7.67e-06 | 3624 | 0.065147 | 3609 | 4.9968e-07 | 5.1467e-05 | 3625 |  | 2677
4940 | BERKELEY T 0404CB | 12660404 | BERKELEY T 0404 | CB | TRUE | 1942.0349 | 0 | 0 | 20 | 7.5209e-06 | 3625 | 0.065211 | 3506 | 4.9106e-07 | 9.8213e-06 | 3626 |  | 2929
206 | PACIFICA 110252715 | 22811102 | PACIFICA 1102 | 52715 | TRUE | 6122.4469 | 0 | 0 | 60 | 7.374e-06 | 3626 | 0.065147 | 3605 | 4.8039e-07 | 2.8824e-05 | 3627 |  | 2661
4875 | OCEANO 1105V48 | 182601105 | OCEANO 1105 | V48 | TRUE | 4125.7287 | 198.7298 | 0.12351 | 39 | 7.0816e-06 | 3628 | 0.06518 | 3536 | 4.6154e-07 | 1.8e-05 | 3628 | 0.02 | 2477
3910 | SAN LEANDRO U 1114458451 | 13111114 | SAN LEANDRO U 1114 | 458451 | FALSE | 3952.1728 | 1967.4653 | 1.2228 | 29 | 6.9026e-06 | 3629 | 0.06559 | 3336 | 4.5289e-07 | 1.3134e-05 | 3629 |  | 2862
1300 | BANCROFT 0402CB | 13030402 | BANCROFT 0402 | CB | TRUE | 7369.6347 | 597.2084 | 0.37117 | 58 | 6.6635e-06 | 3630 | 0.065191 | 3518 | 4.3467e-07 | 2.5211e-05 | 3630 | 0.02 | 2520
1186 | VIEJO 220436948 | 182852204 | VIEJO 2204 | 36948 | TRUE | 13534.0061 | 809.6273 | 0.50319 | 109 | 6.1078e-06 | 3631 | 0.065183 | 3533 | 3.9816e-07 | 4.34e-05 | 3631 |  | 2715
8981 | CASTRO VALLEY 1105132304 | 14091105 | CASTRO VALLEY 1105 | 132304 | TRUE | 1491.8996 | 118.6631 | 0.07375 | 13 | 5.8099e-06 | 3632 | 0.065147 | 3607 | 3.785e-07 | 4.9205e-06 | 3632 |  | 3288
3358 | FORT BRAGG A 110436526 | 42761104 | FORT BRAGG A 1104 | 36526 | TRUE | 10589.2357 | 72.2645 | 0.044913 | 84 | 5.5602e-06 | 3633 | 0.065163 | 3552 | 3.6398e-07 | 3.0574e-05 | 3633 | 0.02 | 2418
6760 | MORRO BAY 1101W04 | 183011101 | MORRO BAY 1101 | W04 | TRUE | 3941.4804 | 437.2441 | 0.27175 | 26 | 3.5981e-06 | 3634 | 0.065147 | 3634 | 2.344e-07 | 6.0945e-06 | 3634 |  | 3060
11118 | DIABLO CANYON 1101CB | 189001101 | DIABLO CANYON 1101 | CB | TRUE | 0 | 0 | 0 |  |  | 3635 |  | 3635 |  | 0 | 3635 |  | 3635

## Weekly Summary (hidden)
Status Summary as of 12/21/20 |  |  |  | Process Summary
Order Status | # of jobs | Miles | Notes | Document | # of jobs | % of jobs | Miles | Notes |  | Responsible Group/Party | Total Expected Days | Total Actual Days | Date Start | Date End
UNSE | 64 | 363.28 |  | AA routed & appr | 62 | 62.63% | 178.86 |  | Planning Order Request Date | Grid Design | 5 business days
ESTS/ADER/APPR | 4 | 4.38 |  | Field Scoping | 24 | 24.24% | 36.19 |  | PM Number Requested Date | Grid Design | 1 business day
PEND | 4 | 6.38 |  | CMCS | 31 | 31.31% | 50.96 |  | Create Job Package | Planning DE | # of days/mile
UNSC | 1 | 1.47 |  | Business Case | 27 | 27.27% | 43.71 |  | AA Routed | Planning DE | Date job packaged created
[9 empty] | AA Approved | Various | 1 week
CONS | 26 | 40.66 | [6 empty] | Field Scoping (scheduling) | Various | 2 weeks
TOTAL | 99 | 416.17 | [6 empty] | Adjustments to Scope/back to planning | Planning DE/Estimating | 1-2 weeks
[9 empty] | ESTS will submit CMCS to planning for approval | Estimating | # of days/mile
[9 empty] | Scheduling | Project Manager | ?????
[9 empty] | Construction (25%, 50%, 75%) | Construction Team | # of weeks/mile