## Pending Repair in 2021 WP
Pending Repair in 2021 WP
Notification | Work Description | Order | ETL Name | Structure Number | MAT | Priority | Priority Bucket | Work Approved Outside Workplan | CIRT Action | CIRT Response | Tier | Late Tag | WSIP Area | WSIP | Inspection | WM Notes | Assigned Crew/Contractor | WV Action Needed | Late Code | Late Explanation | GIS Longitude | GIS Latitude | ETL | Equipment Number | Facility | Damage | Action | Order User Status | Order Status Code | Order Status Description | Estimating Status | Notification Status | Notification type | Planner group | Resource Group | Cost Category | WTC | HQ | Land Agent | Partial RTC | Full RTC
112806346 | COOLEYLANDING/LOS ALTOS A1/38G RPL PL | 31323739 | COOLEY LANDING-LOS ALTOS | A001/038 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | Central | Non-WSIP |  | Completed |  |  |  |  | '-122.101553 | 37.4047 | ETL.6560 | 44303481 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Bay |  | Y - 1
112845022 | SONOMA-PUEBLO 8/12 REPLACE POLE | 31325180 | SONOMA-PUEBLO | 008/012 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-122.329865 | 38.3051 | ETL.3810 | 40689183 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  | 2019-04-01
113021508 | URICH TAP 000/001A REPLACE POLE | 31337142 | URICH TAP | 000/001A | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | Central | Non-WSIP |  |  |  |  | Permit/Environmental | ACOE permit | '-122.102692 | 38.0273 | ETL.6373 | 40577476 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Bay |  |  | ACOE
113118667 | HENRIETTA-LEMOORE NAS :060/006 RPLC POLE | 31343477 | HENRIETTA-LEMOORE NAS | :060/006 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP |  |  |  | Cust Outage Consideration | Had to push it out due to the loads. If the load is not down by October 1st, then we will have to push it out farther -[REDACTED] | '-119.90527 | 36.2484 | ETL.8780 | 40820773 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 2
113134079 | DIXON-VACA #1 6/148 REPLACE POLE | 31343167 | DIXON-VACA #1 | 006/148 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-121.84138 | 38.4277 | ETL.6730 | 40759893 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
113134150 | DIXON-VACA #1 9/209 REPLACE POLE | 31343167 | DIXON-VACA #1 | 009/209 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-121.810854 | 38.461 | ETL.6730 | 40665510 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  | Yes | Yes
113135608 | DIXON-VACA #2 7/173 REPLACE POLE | 31347877 | DIXON-VACA #2 | 007/173 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-121.828627 | 38.4419 | ETL.6740 | 40869019 | Structure-Wood | Rotten | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
113135639 | DIXON-VACA #2 10/227 REPLACE POLE | 31347877 | DIXON-VACA #2 | 010/227 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-121.801522 | 38.4714 | ETL.6740 | 40825232 | Structure-Wood | Rotten | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
113135777 | DIXON-VACA #2 A8/188 REPLACE POLE | 31343168 | DIXON-VACA #2 | A008/188 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Valley | Non-WSIP | [6 empty] | '-121.928517 | 38.3287 | ETL.6740 | 40665467 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
113162817 | CHRISTIE-WILLOW PASS 6/78 REPLACE POLE | 31343162 | CHRISTIE-WILLOW PASS | 006/078 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | Central | Non-WSIP | [6 empty] | '-122.107878 | 38.0261 | ETL.6370 | 40695932 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Bay |  |  | ACOE
113167060 | PEASE-MARYSVILLE-HARTER 0/010 RPL POLE | 31348031 | PEASE-MARYSVILLE-HARTER | 000/010 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-121.653255 | 39.1707 | ETL.7770 | 40610094 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
113186694 | PASO ROBLES-TEMPLETON+ 2/42 REPL POLE | 31347872 | PASO ROBLES-TEMPLETON | 002/042 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | XMPT | South | Non-WSIP | FSRP |  |  |  | Estimating |  | '-120.681075 | 35.5812 | ETL.9400 | 40754833 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Pismo Beach |  | Y - 3
113186715 | PASO ROBLES-TEMPLETON+ 2/43 REPL POLE | 31389712 | PASO ROBLES-TEMPLETON | 002/043 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.681198 | 35.5803 | ETL.9400 | 40823296 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Pismo Beach |  | Y - 3
113190216 | GLENN #3 000/010 STRW NG REPL | 31379483 | GLENN #3 | 000/010 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-122.132076 | 39.777 | ETL.6940 | 40818067 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
113220647 | LVNGSTON-LVNGSTON JCT 4/0 REPLACE POLE | 31318833 | LIVINGSTON-LIVINGSTON JCT | 004/000 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP |  |  |  |  | Clearance Denied by GCC | distribution OE has denied the clearance for this. Not able to do this in the summer will need to submit for fall. New scheduled date is Nov 1st 2019. | '-120.760577 | 37.3031 | ETL.8920 | 40584029 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno
113238411 | NICOLAUS-MARYSVILLE 17/376 RPLC POLE | 31379484 | NICOLAUS-MARYSVILLE | 017/376 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-121.54348 | 38.9145 | ETL.7690 | 40611723 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
113238417 | NICOLAUS-MARYSVILLE 17/382 RPLC POLE | 31379484 | NICOLAUS-MARYSVILLE | 017/382 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-121.543522 | 38.9104 | ETL.7690 | 40815209 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
113249375 | 7TH STANDARD-KERN REPAIR DEFLECTION | 31351241 | KERN-KERN OIL-FAMOSO |  | 93E | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | [8 empty] | ETL.8870 |  | Pole | Out of plumb | Tested | FICL | FICL | Financial closing (no labor) | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Midway
113266683 | SEQUOIA TAP (IDLE) 0/3 REPLACE POLE | 31379485 | SEQUOIA TAP (IDLE) | 000/003 | 70Y | F | Pre-2020_(1b) Lines with special commitments |  |  |  |  | LATE | Central | Non-WSIP |  |  |  |  | Permit/Environmental | Awaiting Caltrans Permit | '-122.267049 | 38.014 | ETL.6361 | 40643934 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Bay |  | Y - 1
113771862 | COLEMAN-COTTONWD 1/020 STRW ROTN REPL | 31379566 | COLEMAN-COTTONWOOD | 001/020 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Valley | Non-WSIP | [6 empty] | '-122.141392 | 40.4092 | ETL.6430 | 40601085 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain
113819272 | CORTINA #4 C21/378 RPLC GUY POLE | 31379441 | CORTINA #4 | C021/378 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-122.035808 | 39.2792 | ETL.6610 | 40609984 | Structure-Wood | Rotten | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
113819637 | CORTINA #4 A7/124 REPLACE POLE | 31379441 | CORTINA #4 | A007/124 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Valley | Non-WSIP | [6 empty] | '-122.152913 | 39.1629 | ETL.6610 | 40737571 | Structure-Wood | Rotten | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
113819688 | CORTINA #4 C23/415 REPLACE POLE | 31379441 | CORTINA #4 | C023/415 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Valley | Non-WSIP | [6 empty] | '-122.033325 | 39.3051 | ETL.6610 | 40757500 | Structure-Wood | Rotten | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
113819702 | CORTINA #4 C28/527 REPLACE POLE | 31379441 | CORTINA #4 | C028/527 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-122.017175 | 39.3847 | ETL.6610 | 40873197 | Structure-Wood | Rotten | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
113819730 | RIO OSO-WOODLAND #1 33/224 RPLC POLE | 35024467 | RIO OSO-WOODLAND #1 | 033/224 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-121.953269 | 38.671 | ETL.3460 | 40737761 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
113870534 | TABLE MTN-VACA 02/011 RPL INSULATOR | 31402249 | TABLE MTN-VACA | 002/011 | 93K | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-121.677946 | 39.5239 | ETL.6090 | 40590039 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  | Yes
114033522 | NICOLAUS-MARYSVILLE 0/4B RPLC POLE | 31381811 | NICOLAUS-MARYSVILLE | 000/004 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Valley | Non-WSIP | [8 empty] | ETL.7690 | 44296324 | Structure-Wood | Rotten | Replace | DOCC | DOCC | Job has been constructed (documentation) | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
114034270 | NICOLAUS-WILKINS SLOUGH 30/536 RPL POLE | 31379593 | NICOLAUS-WILKINS SLOUGH | 030/536 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Valley | Non-WSIP | [6 empty] | '-121.794204 | 38.8618 | ETL.7710 | 40866187 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento
114067119 | KINGSBURG-LEMOORE 017/006 RPL POLE | 31369297 | KINGSBURG-LEMOORE | 017/006 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.65501 | 36.284 | ETL.8910 | 40821414 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 7
114069612 | IGNACIO-ALTO 13/114 REPL LSP W/TSP | 31368895 | IGNACIO-ALTO | 013/114 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  | Likely MAT error - delink to correct |  | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-122.514403 | 37.9429 | ETL.7150 | 40592199 | Structure-Steel | No Good/Out of Stdrd | Replace | FICL | FICL | Financial closing (no labor) | Complete | PEND | LC | TLQ | Pole Program | Capital | 426 | Lakeville
114153550 | HUMBOLDT-BRIDGEVILLE 115/6""CTR"" REPL PL | 31373494 | HUMBOLDT-BRIDGEVILLE | 115/006 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Coast | Non-WSIP | [8 empty] | ETL.1810 | 44322752 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2019-08-13
114153555 | HUMBOLDT-BRIDGEVILLE 115/6""LFT"" REPL PL | 31373494 | HUMBOLDT-BRIDGEVILLE | 115/006 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Coast | Non-WSIP | [8 empty] | ETL.1810 | 44322751 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2019-08-13
114153556 | HUMBOLDT-BRIDGEVILLE 115/6""RT"" REPL PL | 31373494 | HUMBOLDT-BRIDGEVILLE | 115/006 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Coast | Non-WSIP | [8 empty] | ETL.1810 | 44322753 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2019-04-03
114175648 | EXCHEQUER-LE GRAND 11/010 RPLC POLE | 31419516 | EXCHEQUER-LE GRAND | 011/010 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.269099 | 37.4035 | ETL.1560 | 41130100 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 5
114175695 | EXCHEQUER-LEGRAND 2/0 repl 3 pole strctr | 31391051 | EXCHEQUER-LE GRAND | 002/000 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.26589 | 37.5532 | ETL.1560 | 40618907 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 5
114182205 | HUMBOLDT-BRIDGEVILLE 115/0 RPL PL ""LFT"" | 31373494 | HUMBOLDT-BRIDGEVILLE | 115/000 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Coast | Non-WSIP | [6 empty] | '-124.096557 | 40.7784 | ETL.1810 | 40619207 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2019-04-03
114182330 | HUMBOLDT-BRIDGEVILLE 115/0 RPL PL ""RT"" | 31373494 | HUMBOLDT-BRIDGEVILLE | 115/000 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Coast | Non-WSIP | [6 empty] | '-124.096557 | 40.7784 | ETL.1810 | 40619207 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2019-04-03
114182339 | HUMBOLDT-BRIDGEVILLE 115/0 RPL PL ""CTR"" | 31373494 | HUMBOLDT-BRIDGEVILLE | 115/000 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Coast | Non-WSIP | [6 empty] | '-124.096557 | 40.7784 | ETL.1810 | 40619207 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2019-04-03
114223195 | BUTTE-ESQUON 08/185 STRW NG REPL | 31379732 | BUTTE-ESQUON | 008/185 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-121.766473 | 39.61 | ETL.6270 | 40768755 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLZ | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
114230951 | MORRO BAY-SAN LUIS OBISPO #1 0/4 RPL TWR | 31374734 | MORRO BAY-SAN LUIS OBISPO #1 | 000/004 | 92S | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | South | Non-WSIP | [6 empty] | '-120.848954 | 35.3767 | ETL.2810 | 40752726 | Structure-Steel | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLQ | Tower | Capital | 426 | Pismo Beach
114233033 | BUTTE-ESQUON 006/133 STRW ROTN REPL | 31381841 | BUTTE-ESQUON | 006/133 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-121.743165 | 39.6431 | ETL.6270 | 40816828 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain
114239110 | SRGENT SS-HOLISTER-HOLISTR 0/4 REPL POLE | 31498606 | SARGENT SW STA-HOLLISTER (IDLE) | 000/004 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-121.550954 | 36.8955 | ETL.2870 | 44414126 | Structure-Wood | Rotten | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Moss Landing |  | Y - Prog Multi
114239114 | SRGENT SS-HOLISTER-HOLISTR 0/4 REPL POLE | 31498606 | SARGENT SW STA-HOLLISTER (IDLE) | 000/004 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-121.550954 | 36.8955 | ETL.2870 | 44414125 | Structure-Wood | Rotten | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Moss Landing |  | Y - Prog Multi
114239477 | SYCAM CK-NOTRE DAME-TBL 18/175 STRW NG | 31388889 | SYCAMORE CREEK-NOTRE DAME-TABLE MT | 018/175 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-121.803699 | 39.7611 | ETL.4314 | 40575472 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain
114239479 | SYCAM CK-NOTRE DAME-TBL 18/183 STRW ROTN | 31388889 | SYCAMORE CREEK-NOTRE DAME-TABLE MT | 018/183 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-121.805882 | 39.7646 | ETL.4314 | 40575430 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain
114271662 | BUTTE-ESQUON 005/112 STRW ROTN REPL | 31381841 | BUTTE-ESQUON | 005/112 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-121.741665 | 39.6558 | ETL.6270 | 40600592 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain
114275067 | BUTTE-CHICO #2 000/017 STRW ROTN REPL | 31381840 | BUTTE-CHICO #2 | 000/017 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-121.820657 | 39.7191 | ETL.6260 | 44190834 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain
114278847 | COLEMAN-COTTONWOOD 001/019 STRW NG RPL | 31381842 | COLEMAN-COTTONWOOD | 001/019 | 70Y | F | Pre-2020_(5b) On structure in bucket 5 |  |  |  |  | LATE | North Valley | Non-WSIP | [6 empty] | '-122.140996 | 40.4091 | ETL.6430 | 40594912 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLZ | Pole Program | Capital | 372 | Table Mountain
114286234 | HUMBOLDT-BRIDGEVILLE 105/4 RPL PL ""LFT"" | 31381808 | HUMBOLDT-BRIDGEVILLE | 105/004 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Coast | Non-WSIP | [6 empty] | '-123.944318 | 40.72 | ETL.1810 | 44322551 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2019-08-13
114286263 | HUMBOLDT-BRIDGEVILL 103/3 RPL PL ""LFT"" | 31381808 | HUMBOLDT-BRIDGEVILLE | 103/003 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Coast | Non-WSIP | [6 empty] | '-123.936211 | 40.6911 | ETL.1810 | 44322508 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2019-04-03
114286693 | CLEAR LAKE-HOPLAND 11/1 REPLACE POLE | 31379236 | CLEAR LAKE-HOPLAND | 011/001 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Coast | Non-WSIP | [6 empty] | '-122.89417 | 39.0001 | ETL.6390 | 40584501 | Structure-Wood | Rotten | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville
114309724 | KINGSBURG-LEMOORE 14/001 RPLC POLE | 31455718 | KINGSBURG-LEMOORE | 014/001 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | [6 empty] | '-119.655077 | 36.3327 | ETL.8910 | 40596429 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno
114314666 | CRAG VIEW-CASCADE 13/116 SHLS NG REPL | 43487698 | CRAG VIEW-CASCADE | 013/116 | ICS | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | North Valley | Non-WSIP |  |  |  |  | Internal Process | Scope of work is being reevaluated | '-122.306934 | 40.7633 | ETL.1350 | 40761919 | Shield Wire / OPGW-Steel | No Good/Out of Stdrd | Replace | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
114317066 | CORTINA #4 A7/127 REPLACE POLE | 31381813 | CORTINA #4 | A007/127 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Valley | Non-WSIP | [6 empty] | '-122.151855 | 39.1625 | ETL.6610 | 40737648 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  | Yes
114317067 | SAN RAMON-RADUM 2/70 REPLACE POLE | 31381844 | SAN RAMON-RADUM | 002/070 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | Central | Non-WSIP | FSRP | [5 empty] | '-121.911276 | 37.7107 | ETL.7960 | 40613244 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Bay |  | Y - Prog Multi
114329415 | GLENN #2 023/435 STRW ROTN REPL | 31388891 | GLENN #2 | 023/435 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Valley | Non-WSIP | [6 empty] | '-122.006004 | 39.5638 | ETL.6930 | 40814716 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
114339555 | LAKEVILLE #1 00/06 REFRAME POLE | 31382640 | LAKEVILLE #1 | 000/006 | 93E | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | XMPT | North Coast | Non-WSIP | FSRP | [5 empty] | '-122.581557 | 38.2532 | ETL.7360 | 41107031 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 637 | Lakeville |  |  | 2019-04-04
114352548 | ATWTR-LVNGSTN-MRCD 19/007 RPLC POLE | 31382936 | ATWATER-MERCED | 019/007 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.727367 | 37.3606 | ETL.1030 | 40805413 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno
114352660 | ATWTR-LVNGSTN-MRCD 19/008 RPLC POLE | 31382936 | ATWATER-MERCED | 019/008 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.728568 | 37.3606 | ETL.1030 | 40873506 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno
114409277 | COTTONWOOD #1 BA029/303 STRW ROTN REPL | 31391452 | COTTONWOOD #1 | BA029/303 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-122.15884 | 40.0684 | ETL.6620 | 40905992 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
114423633 | FULTON-SANTA ROSA #1 04/69 REP GUY F/S | 43541342 | FULTON-SANTA ROSA #1 NF | 004/069 | ICW | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-122.743585 | 38.4439 | ETL.1620 | 40594341 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-07-19
114434246 | CORTINA #4 A7/128 REPLACE POLE | 31386146 | CORTINA #4 | A007/128 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Valley | Non-WSIP | [6 empty] | '-122.151756 | 39.1625 | ETL.6610 | 40574906 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  | Yes
114435142 | SEQUOIA TAP 0/4 REPLACE POLE | 31386147 | SEQUOIA TAP (IDLE) | 000/004 | 70Y | F | Pre-2020_(1b) Lines with special commitments |  |  |  |  | LATE | Central | Non-WSIP |  |  |  |  | Permit/Environmental | Awaiting Caltrans Permit | '-122.26739 | 38.0151 | ETL.6361 | 40745626 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Bay |  | Y - 1
114435674 | WEST SACRAMENTO-DAVIS 10/164 RPLC POLE | 31386145 | WEST SACRAMENTO-DAVIS | 010/164 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-121.728126 | 38.5624 | ETL.4120 | 40590285 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
114438564 | COTTONWOOD #1 B024/204 STRW NG REPL | 31391452 | COTTONWOOD #1 | B024/204 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-122.233197 | 40.0791 | ETL.6620 | 40909848 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
114438945 | COTTONWOOD #1 B024/205 STRW NG REPL | 31391452 | COTTONWOOD #1 | B024/205 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-122.233195 | 40.0784 | ETL.6620 | 40909849 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
114439097 | COTTONWOOD #1 B023/195 STRW NG REPL | 31391452 | COTTONWOOD #1 | B023/195 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-122.233033 | 40.0854 | ETL.6620 | 40909839 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
114439116 | COTTONWOOD #1 B023/194 STRW NG REPL | 31391452 | COTTONWOOD #1 | B023/194 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-122.233029 | 40.0862 | ETL.6620 | 40909838 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
114439139 | COTTONWOOD #1 B023/188 STRW NG REPL | 31391452 | COTTONWOOD #1 | B023/188 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Valley | Non-WSIP | [6 empty] | '-122.232902 | 40.0905 | ETL.6620 | 40909832 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
114439155 | COTTONWOOD #1 B023/191 STRW NG REPL | 31391452 | COTTONWOOD #1 | B023/191 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-122.232952 | 40.0883 | ETL.6620 | 40909835 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
114439271 | COTTONWOOD #1 B021/160 STRW NG REPL | 31391452 | COTTONWOOD #1 | B021/160 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-122.232241 | 40.1118 | ETL.6620 | 40909804 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
114439690 | BUTTE-ESQUON 0/011 STRW NG REPL | 31388884 | BUTTE-ESQUON | 000/011 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-121.809467 | 39.7092 | ETL.6270 | 40826354 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain
114448828 | GARBERVILLE-LAYTONVILLE 60kV 34/9 NG POL | 31404618 | GARBERVILLE-LAYTONVILLE | 034/009 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Coast | Non-WSIP | [6 empty] | '-123.577342 | 39.8306 | ETL.8365 | 40875241 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2019-04-01
114448873 | GARBERVILLE-LAYTONVILLE 60kV 35/0 NG POL | 31404618 | GARBERVILLE-LAYTONVILLE | 035/000 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Coast | Non-WSIP | [6 empty] | '-123.578193 | 39.8314 | ETL.8365 | 40614542 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2019-04-01
114469839 | DINUBA ENERGY TAP 2/009 RPLC POLE | 31389710 | DINUBA ENERGY TAP | 002/009 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.408345 | 36.5714 | ETL.9051 | 40873004 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno
114469982 | DINUBA ENERGY TAP 02/008 RPLC POLE | 31389710 | DINUBA ENERGY TAP | 002/008 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.407227 | 36.5714 | ETL.9051 | 40873844 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno
114475329 | CHOWCHILLA-KERCKHOFF 31/010 RPL POLE | 31405908 | CHOWCHILLA-KERCKHOFF | 031/010 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.092917 | 37.1268 | ETL.1250 | 40584956 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Fresno |  | Y - 21
114477817 | CHOWCHILLA-KERCKHOFF 28/010 REPL POLE | 31405908 | CHOWCHILLA-KERCKHOFF | 028/010 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.035507 | 37.1266 | ETL.1250 | 40584947 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Fresno |  | Y - 21
114477857 | CHOWCHILLA-KERCKHOFF 27/008A RPLC POLE | 31405908 | CHOWCHILLA-KERCKHOFF | 027/008A | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.020386 | 37.1244 | ETL.1250 | 41109571 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Fresno |  | Y - 21
114477911 | CHOWCHILLA-KERCKHOFF 28/011 RPLC POLE | 31405908 | CHOWCHILLA-KERCKHOFF | 028/011 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.037018 | 37.1267 | ETL.1250 | 40592031 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Fresno |  | Y - 21
114491791 | SONOMA-PUEBLO 02/07 REPL OVRLD POLE | 31390594 | SONOMA-PUEBLO | 002/007 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-122.422026 | 38.2697 | ETL.3810 | 40818672 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  | 2019-08-05
114494421 | BAIR-COOLEY LNDING #1-60 kV_2/17A RPL PL | 31389708 | BAIR-COOLEY LANDING #1 | 002/017A | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | Central | Non-WSIP | [6 empty] | '-122.185119 | 37.4874 | ETL.6200 | 44378240 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLZ | Pole Program | Capital | 372 | Bay
114494798 | GEYSERS #7-EAGLE ROCK 0/002 | 43761575 | GEYSERS #7-EAGLE ROCK | 000/002 | ICS | F | Pre-2020_(5) TD tag on other lines |  |  | Likely MAT error - delink to correct |  | LATE | North Coast | Non-WSIP | [8 empty] | ETL.1680 | 44298667 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville
114494871 | GEYSERS #7-EAGLE ROCK 0/01B CANCEL | 43761575 | GEYSERS #7-EAGLE ROCK | 000/001B | ICS | F | Pre-2020_(5) TD tag on other lines |  |  | CANCEL/CNCL |  | LATE | North Coast | Non-WSIP | [6 empty] | '-122.801462 | 38.8145 | ETL.1680 | 40740487 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-07-31
114496955 | MENDOCINO-UKIAH 3/11B RPL STRW | 31391191 | MENDOCINO-UKIAH | 003/011B | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-123.192766 | 39.1973 | ETL.2420 | 40740255 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville
114498679 | KETTLEMAN HILLS TAP 0/002 RPLACE POLE | 31389711 | KETTLEMAN HILLS TAP | 000/002 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.09778 | 36.0436 | ETL.8701 | 40684781 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno
114516978 | HUMBOLDT-BRIDGEVILLE 103/3 RPL PL ""RT"" | 31381808 | HUMBOLDT-BRIDGEVILLE | 103/003 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Coast | Non-WSIP | [6 empty] | '-123.936211 | 40.6911 | ETL.1810 | 44322509 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2019-04-03
114517356 | HUMBOLDT-BRIDGEVILLE 105/4 RPL PL ""RT"" | 31381808 | HUMBOLDT-BRIDGEVILLE | 105/004 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Coast | Non-WSIP | [6 empty] | '-123.944318 | 40.72 | ETL.1810 | 44322552 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2019-08-13
114531042 | NICOLAUS-CATLETT JCT 4/086 RPL POLE | 31404628 | NICOLAUS-CATLETT JCT | 004/086 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-121.539166 | 38.8477 | ETL.7680 | 40757082 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
114531110 | NICOLAUS-CATLETT 3/080 RPL POLE | 31404628 | NICOLAUS-CATLETT JCT | 003/080 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-121.541722 | 38.8522 | ETL.7680 | 40866785 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento
114535142 | KEARNEY-BIOLA 10/005 RPLC POLE | 31391046 | KEARNEY-BIOLA | 010/005 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.956672 | 36.7933 | ETL.8810 | 40747255 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno
114535228 | KEARNEY-BIOLA 10/008 RPLC POLE | 31391046 | KEARNEY-BIOLA | 010/008 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.960108 | 36.7933 | ETL.8810 | 40873066 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno
114535242 | KEARNEY-BIOLA 10/006 RPLC POLE | 31391046 | KEARNEY-BIOLA | 010/006 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.957788 | 36.7933 | ETL.8810 | 40821355 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno
114535342 | KEARNEY-BIOLA 10/009 RPLC POLE | 31391046 | KEARNEY-BIOLA | 010/009 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.961266 | 36.7933 | ETL.8810 | 40858702 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno
114535343 | KEARNEY-BIOLA 10/010 RPLC POLE | 31391046 | KEARNEY-BIOLA | 010/010 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.962383 | 36.7933 | ETL.8810 | 40583379 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno
114535344 | KEARNEY-BIOLA 10/013 RPLC POLE | 31391047 | KEARNEY-BIOLA | 010/013 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.965779 | 36.7933 | ETL.8810 | 40661341 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno
114535362 | KEARNEY-BIOLA 10/014 RPLC POLE | 31391047 | KEARNEY-BIOLA | 010/014 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.966877 | 36.7933 | ETL.8810 | 40747274 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno
114535741 | KEARNEY-BIOLA 10/015 RPLC POLE | 31391047 | KEARNEY-BIOLA | 010/015 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.967969 | 36.7933 | ETL.8810 | 40747257 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno
114535743 | KEARNEY-BIOLA 10/016 RPLC POLE | 31391047 | KEARNEY-BIOLA | 010/016 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.969041 | 36.7933 | ETL.8810 | 40821818 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno
114535749 | KEARNEY-BIOLA 11/000 RPLC POLE | 31391047 | KEARNEY-BIOLA | 011/000 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.970139 | 36.7933 | ETL.8810 | 40583383 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno
114535838 | KEARNEY-BIOLA 11/002 RPLC POLE | 31391047 | KEARNEY-BIOLA | 011/002 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.972194 | 36.7933 | ETL.8810 | 40686134 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno
114535874 | KEARNEY-BIOLA 11/003 RPLC POLE | 31391047 | KEARNEY-BIOLA | 011/003 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.973217 | 36.7933 | ETL.8810 | 40645568 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno
114535875 | KEARNEY-BIOLA 11/001 RPLC POLE | 31391047 | KEARNEY-BIOLA | 011/001 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.971133 | 36.7933 | ETL.8810 | 40581938 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno
114535906 | KEARNEY-BIOLA 11/006 RPLC POLE | 31391047 | KEARNEY-BIOLA | 011/006 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.97625 | 36.7933 | ETL.8810 | 40805941 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno
114535942 | KEARNEY-BIOLA 11/008 RPLC POLE | 31391048 | KEARNEY-BIOLA | 011/008 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.978365 | 36.7933 | ETL.8810 | 40858812 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - Prog Multi
114535944 | KEARNEY-BIOLA 11/009 RPLC POLE | 31391048 | KEARNEY-BIOLA | 011/009 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.97935 | 36.7933 | ETL.8810 | 40872050 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno
114535946 | KEARNEY-BIOLA 11/010 RPLC POLE | 31391048 | KEARNEY-BIOLA | 011/010 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.980353 | 36.7933 | ETL.8810 | 40583386 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - Prog Multi
114535958 | KEARNEY-BIOLA 11/012 RPLC POLE | 31391048 | KEARNEY-BIOLA | 011/012 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.982477 | 36.7933 | ETL.8810 | 40686138 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - Prog Multi
114536021 | KEARNEY-BIOLA 11/013 RPLC POLE | 31391048 | KEARNEY-BIOLA | 011/013 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.983493 | 36.7933 | ETL.8810 | 40645571 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno
114536063 | KEARNEY-BIOLA 11/014 RPLC POLE | 31391048 | KEARNEY-BIOLA | 011/014 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.984586 | 36.7933 | ETL.8810 | 40747278 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - Prog Multi
114536068 | KEARNEY-BIOLA 12/004 RPLC POLE | 31391048 | KEARNEY-BIOLA | 012/004 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.991986 | 36.7933 | ETL.8810 | 40747281 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - Prog Multi
114536110 | KEARNEY-BIOLA 12/008 RPLC POLE | 31391049 | KEARNEY-BIOLA | 012/008 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.995543 | 36.7933 | ETL.8810 | 40873750 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - Prog Multi
114536112 | KEARNEY-BIOLA 12/010 RPLC POLE | 31391049 | KEARNEY-BIOLA | 012/010 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.997339 | 36.7933 | ETL.8810 | 40583389 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - Prog Multi
114536165 | KEARNEY-BIOLA 13/004 RPLC POLE | 31391049 | KEARNEY-BIOLA | 013/004 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.009898 | 36.7933 | ETL.8810 | 40747283 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - Prog Multi
114536183 | KEARNEY-BIOLA 12/018 RPLC POLE | 31391049 | KEARNEY-BIOLA | 012/018 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.00537 | 36.7933 | ETL.8810 | 40858814 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - Prog Multi
114536191 | KEARNEY-BIOLA 13/000 RPLC POLE | 31391049 | KEARNEY-BIOLA | 013/000 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.00639 | 36.7933 | ETL.8810 | 40606721 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - Prog Multi
114536194 | KEARNEY-BIOLA 13/002 RPLC POLE | 31391049 | KEARNEY-BIOLA | 013/002 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.008037 | 36.7933 | ETL.8810 | 40686142 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - Prog Multi
114536273 | KEARNEY-BIOLA 13/010 RPLC POLE | 31391049 | KEARNEY-BIOLA | 013/010 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.015618 | 36.7933 | ETL.8810 | 40583392 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - Prog Multi
114549634 | EXCHEQUER-LE GRAND 24/000 RPLC POLE | 31394006 | EXCHEQUER-LE GRAND | 024/000 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.252551 | 37.2419 | ETL.1560 | 40913270 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 5
114553087 | EXCHEQUER-LE GRAND 16/005 RPLC POLE | 31394006 | EXCHEQUER-LE GRAND | 016/005 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.2516 | 37.351 | ETL.1560 | 40762233 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 5
114557370 | MENDOCINOPHILO JCTHOPLND 10/11 RPLC POLE | 31390919 | MENDOCINO-PHILO JCT-HOPLAND | 010/011 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-123.16022 | 39.1233 | ETL.7520 | 40600784 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville
114557450 | MENDOCINOPHILO JCTHOPLAND 10/8 RPLC POLE | 31390919 | MENDOCINO-PHILO JCT-HOPLAND | 010/008 | 70Y | B | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-123.1602 | 39.125 | ETL.7520 | 40876887 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  | 2019-04-23
114562395 | EXCHEQUER-LE GRAND 05/008 RPLC POLE | 31391051 | EXCHEQUER-LE GRAND | 005/008 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.267107 | 37.4968 | ETL.1560 | 40873655 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 5
114562438 | EXCHEQUER-LE GRAND 05/009 RPLC POLE | 31391051 | EXCHEQUER-LE GRAND | 005/009 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.267127 | 37.4959 | ETL.1560 | 40865250 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 5
114570245 | EXCHEQUER-LE GRAND 008/001 RPLC POLE | 31394005 | EXCHEQUER-LE GRAND | 008/001 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.267943 | 37.457 | ETL.1560 | 40588982 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 5
114570285 | EXCHEQUER-LE GRAND 008/002 RPLC POLE | 31394005 | EXCHEQUER-LE GRAND | 008/002 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.267966 | 37.4558 | ETL.1560 | 40689666 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 5
114570315 | EXCHEQUER-LE GRAND 008/003 RPLC POLE | 31394005 | EXCHEQUER-LE GRAND | 008/003 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.267992 | 37.4545 | ETL.1560 | 40662962 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 5
114570319 | EXCHEQUER-LE GRAND 08/004 RPLC POLE | 31394005 | EXCHEQUER-LE GRAND | 008/004 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.268026 | 37.4532 | ETL.1560 | 40755522 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 5
114570393 | EXCHEQUER-LE GRAND 008/009 RPLC POLE | 31394005 | EXCHEQUER-LE GRAND | 008/009 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.268151 | 37.4466 | ETL.1560 | 40864755 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 5
114571472 | EXCHEQUER-LE GRAND 009/009 RPLC POLE | 31394005 | EXCHEQUER-LE GRAND | 009/009 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | [6 empty] | '-120.268446 | 37.4314 | ETL.1560 | 40877006 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 5
114571476 | EXCHEQUER-LE GRAND 010/002 RPLC POLE | 31394005 | EXCHEQUER-LE GRAND | 010/002 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.26853 | 37.4264 | ETL.1560 | 40669620 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 5
114572979 | EXCHEQUER-LE GRAND 010/007 RPLC POLE | 31394005 | EXCHEQUER-LE GRAND | 010/007 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.268621 | 37.4201 | ETL.1560 | 40812814 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 5
114575140 | EXCHEQUER-LE GRAND 12/000 RPLC POLE | 31394006 | EXCHEQUER-LE GRAND | 012/000 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.269177 | 37.4009 | ETL.1560 | 41130102 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 5
114575218 | EXCHEQUER-LE GRAND 12/001 RPLC POLE | 31394006 | EXCHEQUER-LE GRAND | 012/001 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.269223 | 37.3999 | ETL.1560 | 40588985 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno
114575289 | EXCHEQUER-LE GRAND 12/002 RPLC POLE | 31394006 | EXCHEQUER-LE GRAND | 012/002 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.269252 | 37.3986 | ETL.1560 | 40702433 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 5
114575295 | EXCHEQUER-LE GRAND 12/003 RPLC POLE | 31394006 | EXCHEQUER-LE GRAND | 012/003 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.269266 | 37.3978 | ETL.1560 | 40653443 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 5
114575343 | EXCHEQUER-LE GRAND 12/004 RPLC POLE | 31394006 | EXCHEQUER-LE GRAND | 012/004 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.269305 | 37.3963 | ETL.1560 | 40762493 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 5
114575815 | EXCHEQUER-LE GRAND 013/008 RPLC POLE | 31462751 | EXCHEQUER-LE GRAND | 013/008 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.26981 | 37.3763 | ETL.1560 | 40865249 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 5
114575931 | EXCHEQUER-LE GRAND 014/007 RPLC POLE | 31394006 | EXCHEQUER-LE GRAND | 014/007 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.269889 | 37.3644 | ETL.1560 | 40826573 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 5
114584230 | EXCHEQUER-LE GRAND 009/006 RPLC POLE | 31394005 | EXCHEQUER-LE GRAND | 009/006 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.268398 | 37.435 | ETL.1560 | 40813576 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 5
114595870 | ROUND MTN-TBL MTN #2 50/219 CONS NG REPA | 43621090 | ROUND MTN-TABLE MTN #2 | 050/219 | ICS | E | Pre-2020_(2) High fire spread TD |  |  |  |  | LATE | North Valley | Non-WSIP |  |  |  |  | Clearance Cancelled by GCC | 2021 - Cancelled by ISO | '-121.891019 | 40.0748 | ETL.6070 | 40863109 | Conductor-Steel | No Good/Out of Stdrd | Repair | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
114608714 | BUTTE-CHICO #2 000/016 STRW ROTN REPL | 31397866 | BUTTE-CHICO #2 | 000/016 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-121.820573 | 39.7189 | ETL.6260 | 40771361 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain
114626587 | CLEARLAKE-HOPLAND 00/10 REPL NG POLE | 31397870 | CLEAR LAKE-HOPLAND | 000/010 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-123.072631 | 38.9706 | ETL.6390 | 40587010 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville
114628867 | HUMBOLDT-BRIDGEVILLE-107/1L RPL POLE | 31404623 | HUMBOLDT-BRIDGEVILLE | 107/001 | 70Y | F | Pre-2020_(4b) On structure in bucket 4 |  |  |  |  | LATE | North Coast | Non-WSIP | [6 empty] | '-123.962404 | 40.7423 | ETL.1810 | 44322571 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2019-04-03
114636964 | SEQUOIA TAP (IDLE) 000/005 rpl pole | 31395987 | SEQUOIA TAP (IDLE) | 000/005 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  |  |  |  | LATE | Central | Non-WSIP |  |  |  |  | Permit/Environmental | Awaiting Caltrans Permit | '-122.266913 | 38.0161 | ETL.6361 | 40745606 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Bay |  | Y - 1
114641696 | KONOCTI-MIDDLETOWN ;20/9 REPL NG POLE | 31396373 | KONOCTI-MIDDLETOWN |  | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | XMPT | North Coast | Non-WSIP | FSRP | [7 empty] | ETL.6380 |  | Guy Pole-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  | Additonal Land, Biological, and/or Cultural Review Required | 2019-05-21
114644327 | ARCO-TULARE LAKE 000/006 RPL POLE | 31394816 | ARCO-TULARE LAKE | 000/006 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.915348 | 35.7809 | ETL.8460 | 40806920 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 7
114649176 | ARCO-TULARE LAKE 003/050 RPL POLE | 31394816 | ARCO-TULARE LAKE | 003/050 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.915404 | 35.8208 | ETL.8460 | 40748386 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 7
114649267 | ARCO-TULARE LAKE 003/059 RPL POLE | 31394816 | ARCO-TULARE LAKE | 003/059 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.915417 | 35.8291 | ETL.8460 | 40763112 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 7
114651739 | ARCO-TULARE LAKE 005/081 RPL POLE | 31394816 | ARCO-TULARE LAKE | 005/081 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.915423 | 35.8497 | ETL.8460 | 40748390 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 7
114653167 | HENRIETTA-LEMOORE NAS :059/011 RPL POLE | 31394819 | HENRIETTA-LEMOORE NAS | :059/011 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.905277 | 36.26 | ETL.8780 | 40595948 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 2
114653225 | HENRIETTA-LEMOORE NAS :059/012 RPL POLE | 31394819 | HENRIETTA-LEMOORE NAS | :059/012 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.905278 | 36.2591 | ETL.8780 | 40686217 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 2
114653259 | HENRIETTA-LEMOORE NAS :059/013 RPL POLE | 31394819 | HENRIETTA-LEMOORE NAS | :059/013 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.905236 | 36.258 | ETL.8780 | 40656332 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 2
114660872 | ARCO-TULARE LAKE 007/115 RPL POLE | 31394816 | ARCO-TULARE LAKE | 007/115 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.91548 | 35.8824 | ETL.8460 | 40870928 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 7
114660997 | ARCO-TULARE LAKE 008/127 RPL POLE | 31394816 | ARCO-TULARE LAKE | 008/127 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.915498 | 35.8937 | ETL.8460 | 40806924 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 7
114664927 | ARCO-TULARE LAKE 010/164 RPLC POLE | 31394816 | ARCO-TULARE LAKE | 010/164 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.920655 | 35.9271 | ETL.8460 | 40582870 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno
114667511 | EUREKA-STA A _000/002 REPLACE POLE | 31404617 | EUREKA-STA "A" (NO FLY) | 000/002 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-124.180503 | 40.793 | ETL.6820 | 40658147 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2019-06-21
114669318 | ARCO-TULARE LAKE 015/245 rpl pole | 31394816 | ARCO-TULARE LAKE | 015/245 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.946425 | 35.998 | ETL.8460 | 40763130 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 7
114679493 | PARADISE-TABLE MTN_016/134_INSUL | 31397719 | PARADISE-TABLE MTN | 016/134 | 93I | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | North Valley | Non-WSIP | [6 empty] | '-121.499399 | 39.6792 | ETL.4316 | 41176826 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 508 | Table Mountain |  |  | Yes
114691402 | BADGER HILL TAP 001/012 RPLC POLE | 31398364 | BADGER HILL TAP | 001/012 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.934887 | 35.8356 | ETL.8452 | 40595362 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno
114691793 | GARBERVILLE-LAYTONVILLE 60kV 33/0B RP PL | 31454647 | GARBERVILLE-LAYTONVILLE | 033/000B | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Coast | Non-WSIP | [6 empty] | '-123.55375 | 39.8114 | ETL.8365 | 40906580 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2019-04-01
114699493 | BRIGHTON-BELLOTA 36/249 RPR TWR | 43910331 | BRIGHTON-BELLOTA | 036/249 | ICQ | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-121.317813 | 38.4287 | ETL.4420 | 40864821 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento |  |  | Yes
114727427 | ORO LOMA-CANAL #1 001/002 RPLC POLE | 31398375 | ORO LOMA-CANAL #1 | 001/002 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.654594 | 36.9039 | ETL.9020 | 40650331 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 9
114727853 | PITTSBG-SAN MATEO 021/084A RPL POLE TSP | 31425596 | PITTSBURG-SAN MATEO | 021/084A | 70S | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | TLN/TLQ error |  |  | LATE | Central | Non-WSIP | FSRP | [5 empty] | '-121.936022 | 37.7433 | ETL.5463 | 44553742 | Structure-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Pole Program | Capital | 426 | Bay |  | Y - Prog Multi
114729264 | ORO LOMA-CANAL #1 001/014 RPLC POLE | 31398375 | ORO LOMA-CANAL #1 | 001/014 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.65476 | 36.9142 | ETL.9020 | 40747784 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 9
114729325 | ORO LOMA-CANAL #1 001/015A RPLC POLE | 31398375 | ORO LOMA-CANAL #1 | 001/015A | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.654768 | 36.9153 | ETL.9020 | 40905699 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 9
114729470 | ORO LOMA-CANAL #1 002/009 RPLC POLE | 31398375 | ORO LOMA-CANAL #1 | 002/009 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | [6 empty] | '-120.654435 | 36.925 | ETL.9020 | 40871474 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 9
114729504 | ORO LOMA-CANAL #1 002/010 RPLC POLE | 31398375 | ORO LOMA-CANAL #1 | 002/010 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | [6 empty] | '-120.654238 | 36.9261 | ETL.9020 | 40607092 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 9
114730128 | KING CITY-COBURN #1 60KV 1/24 REPL POLE | 31398372 | KING CITY-COBURN #1 | 001/024 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-121.142661 | 36.2103 | ETL.7320 | 40826679 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Moss Landing |  | Arcadis
114730295 | KING CITY-COBURN #1 6/98LFT REPL POLE | 31469910 | KING CITY-COBURN #1 | 006/098 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [7 empty] | ETL.7320 | 44405219 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Moss Landing |  | Arcadis
114730462 | KING CITY-COBURN #1 A9/132 REPLACE POLE | 31398371 | KING CITY-COBURN #1 | A009/132 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-121.194274 | 36.2875 | ETL.7320 | 40876859 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Moss Landing |  | Arcadis | 2019-03-27
114730519 | KING CITY-COBURN #1 A9/147 RPLC POLE | 31398371 | KING CITY-COBURN #1 | A009/147 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-121.2043 | 36.2952 | ETL.7320 | 40652511 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Moss Landing |  | Arcadis | 2019-03-27
114730662 | KING CITY-COBURN#1 A11/179 REPL GUY POLE | 31398371 | KING CITY-COBURN #1 | A011/179 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-121.229178 | 36.3089 | ETL.7320 | 40864463 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Moss Landing |  |  | 2019-03-27
114730687 | KING CITY-COBURN#1 A11/185 REPL POLE | 31398371 | KING CITY-COBURN #1 | A011/185 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-121.234313 | 36.3128 | ETL.7320 | 40666217 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Moss Landing |  | Arcadis | 2019-03-27
114730761 | KING CITY-COBURN #1 A13/222 REPL POLE | 31398371 | KING CITY-COBURN #1 | A013/222 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-121.246653 | 36.3312 | ETL.7320 | 40864095 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Moss Landing |  | Arcadis | 2019-03-27
114730766 | KING CITY-CBURN#1 60KV A14/243 REPL POLE | 31398371 | KING CITY-COBURN #1 | A014/243 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-121.259503 | 36.3445 | ETL.7320 | 40826694 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Moss Landing |  | Arcadis | 2019-03-27
114731290 | SALINAS-FIRESTONE #2 2/76 REPL GUY POLE | 31398376 | SALINAS-FIRESTONE #2 (NO FLY) | 002/076 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | [6 empty] | '-121.611215 | 36.6728 | ETL.7910 | 40811963 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Moss Landing |  | Y - 1
114732563 | ORO LOMA-CANAL #1 004/005 RPL POLE | 31398375 | ORO LOMA-CANAL #1 | 004/005 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.65394 | 36.95 | ETL.9020 | 40747779 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 9
114732715 | MIDWAY-WHEELER RIDGE #1 47/210 GRDE BEAM | 31401786 | MIDWAY-WHEELER RIDGE #1 | 047/210 | 70S | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-118.993464 | 35.0273 | ETL.5190 | 40586560 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLQ | Pole Program | Capital | 426 | Midway
114733713 | ORO LOMA-CANAL #1 006/002 RPLC POLE | 31398375 | ORO LOMA-CANAL #1 | 006/002 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.635808 | 36.9618 | ETL.9020 | 40686878 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 9
114733792 | ORO LOMA-CANAL #1 006/003 RPLC POLE | 31398375 | ORO LOMA-CANAL #1 | 006/003 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.635806 | 36.9627 | ETL.9020 | 40646013 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 9
114733800 | ORO LOMA-CANAL #1 006/004 RPLC POLE | 31398375 | ORO LOMA-CANAL #1 | 006/004 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.635798 | 36.9637 | ETL.9020 | 40747796 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 9
114734404 | ORO LOMA-CANAL #1 007/010 RPLC POLE | 31398375 | ORO LOMA-CANAL #1 | 007/010 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.635744 | 36.9792 | ETL.9020 | 40607101 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  |  | CalTrans
114737367 | ORO LOMA-CANAL #1 012/003 RPLC POLE | 31399014 | ORO LOMA-CANAL #1 | 012/003 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | [6 empty] | '-120.63551 | 37.0274 | ETL.9020 | 40663409 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 9 | CalTrans
114743614 | DISCOVERY TAP 0/2 POLE REPLACEMENT | 31406081 | DISCOVERY TAP | 000/002 | 92T | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | [6 empty] | '-119.01215 | 35.4266 | ETL.1921 | 40652639 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Contract | Capital | 372 | Midway
114746208 | ORO LOMA-CANAL #1 013/011 RPLC POLE | 31399014 | ORO LOMA-CANAL #1 | 013/011 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | [6 empty] | '-120.635432 | 37.0492 | ETL.9020 | 40596868 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  |  | CalTrans
114746227 | ORO LOMA-CANAL #1 013/014 RPLC POLE | 31399014 | ORO LOMA-CANAL #1 | 013/014 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | [6 empty] | '-120.635449 | 37.0516 | ETL.9020 | 40764078 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 9 | CalTrans
114746692 | ORO LOMA-CANAL #1 014/009 RPLC POLE | 31399014 | ORO LOMA-CANAL #1 | 014/009 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.644431 | 37.0545 | ETL.9020 | 40859033 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 9
114746998 | DISCOVERY TAP 115KV 0/3 SEECO SW165 REPL | 31406081 | DISCOVERY TAP | 000/003 | 92T | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | [6 empty] | '-119.01111 | 35.4266 | ETL.1921 | 40743293 | Switch-Steel | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLN | Maintenance | Capital | 435 | Midway
114747217 | DISCOVERY TAP 115KV 0/4 REPL POLE | 31406081 | DISCOVERY TAP | 000/004 | 92T | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | [6 empty] | '-119.00986 | 35.4266 | ETL.1921 | 40748726 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Contract | Capital | 372 | Midway
114747523 | ORO LOMA-CANAL #1 15/006 RPLC POLE | 31399014 | ORO LOMA-CANAL #1 | 015/006 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | [6 empty] | '-120.658442 | 37.0546 | ETL.9020 | 40806394 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 9 | CalTrans
114747683 | ORO LOMA-CANAL #1 015/013 RPLC POLE | 31399014 | ORO LOMA-CANAL #1 | 015/013 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | [6 empty] | '-120.666903 | 37.0546 | ETL.9020 | 40662495 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 9 | CalTrans
114748611 | T2 CC-MORAGA #1 024/113 HELI WASH |  | CONTRA COSTA-MORAGA #1 | 024/113 | ICI | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | Central | Non-WSIP |  |  |  |  | Sick/Capacity | Due to helo equipment constraints, work would not be completed prior to required end date. Work is being incorporated into helo wash program for Q4 2018/ Q1 2019. | '-122.120896 | 37.8621 | ETL.5452 | 44291689 | Insulator | Contaminated | Helicopter Wash |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 626 | Bay
114753000 | KING CITY-COBURN #1 A7/117 REPL POLE | 31455717 | KING CITY-COBURN #1 | A007/117 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-121.185138 | 36.276 | ETL.7320 | 40615515 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Moss Landing |  | Arcadis | 2019-03-27
114760201 | ORO LOMA-CANAL #1 016/003 RPLC POLE | 31399014 | ORO LOMA-CANAL #1 | 016/003 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.673183 | 37.0547 | ETL.9020 | 40661644 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 9 | CalTrans
114760242 | ORO LOMA-CANAL #1 016/009 RPLC POLE | 31399014 | ORO LOMA-CANAL #1 | 016/009 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.68019 | 37.0547 | ETL.9020 | 40859035 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 9 | CalTrans
114760731 | ORO LOMA-CANAL #1 017/007 RPLC POLE | 31399014 | ORO LOMA-CANAL #1 | 017/007 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.695859 | 37.0548 | ETL.9020 | 40820261 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 9 | CalTrans
114760836 | ORO LOMA-CANAL #1 018/003 RPLC POLE | 31402076 | ORO LOMA-CANAL #1 | 018/003 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.708073 | 37.0548 | ETL.9020 | 40661652 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  |  | CalTrans
114760838 | ORO LOMA-CANAL #1 018/004 RPLC POLE | 31402076 | ORO LOMA-CANAL #1 | 018/004 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.709214 | 37.0548 | ETL.9020 | 40764387 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 9 | CalTrans
114761264 | ORO LOMA-CANAL #1 018/008 RPLC POLE | 31402076 | ORO LOMA-CANAL #1 | 018/008 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.713684 | 37.0549 | ETL.9020 | 40873774 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 9 | CalTrans
114761269 | ORO LOMA-CANAL #1 019/003 RPLC POLE | 31402076 | ORO LOMA-CANAL #1 | 019/003 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.724967 | 37.0551 | ETL.9020 | 40646030 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 9 | CalTrans
114761501 | ORO LOMA-CANAL #1 019/013 RPLC POLE | 31402076 | ORO LOMA-CANAL #1 | 019/013 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.735954 | 37.0553 | ETL.9020 | 40661653 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 9 | CalTrans
114761599 | ORO LOMA-CANAL #1 019/016 RPLC POLE | 31402076 | ORO LOMA-CANAL #1 | 019/016 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.739542 | 37.0553 | ETL.9020 | 40821621 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 9 | CalTrans
114762044 | ORO LOMA-CANAL #1 020/005 RPLC POLE | 31402076 | ORO LOMA-CANAL #1 | 020/005 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | [6 empty] | '-120.745276 | 37.0554 | ETL.9020 | 40764071 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 9 | CalTrans
114768995 | ORO LOMA-CANAL #1 020/007 RPLC POLE | 31402076 | ORO LOMA-CANAL #1 | 020/007 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.747641 | 37.0555 | ETL.9020 | 40806246 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 9 | CalTrans
114769661 | ORO LOMA-CANAL #1 021/006 RPLC POLE | 31402076 | ORO LOMA-CANAL #1 | 021/006 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.764302 | 37.0558 | ETL.9020 | 40806403 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 9 | CalTrans
114769890 | ORO LOMA-CANAL #1 021/011 RPLC POLE | 31402076 | ORO LOMA-CANAL #1 | 021/011 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | [6 empty] | '-120.770073 | 37.0559 | ETL.9020 | 40582360 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 9 | CDFW
114770637 | ORO LOMA-CANAL #1 023/003 RPLC POLE | 31402077 | ORO LOMA-CANAL #1 | 023/003 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.794611 | 37.0563 | ETL.9020 | 40646037 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 9 | CalTrans
114770742 | ORO LOMA-CANAL #1 023/005 RPLC POLE | 31402077 | ORO LOMA-CANAL #1 | 023/005 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.797091 | 37.0563 | ETL.9020 | 40747805 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 9 | CalTrans
114773656 | ORO LOMA-CANAL #1 23/012 RPL STBD POLE | 31402077 | ORO LOMA-CANAL #1 | 023/012 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | [6 empty] | '-120.804896 | 37.0565 | ETL.9020 | 40688764 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 9 | CalTrans
114773706 | ORO LOMA-CANAL #1 024/004 RPL STBD POLE | 31402077 | ORO LOMA-CANAL #1 | 024/004 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.812653 | 37.0572 | ETL.9020 | 40747826 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 9
114773736 | ORO LOMA-CANAL #1 024/006 RPLC STBD POLE | 31402077 | ORO LOMA-CANAL #1 | 024/006 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.81493 | 37.0572 | ETL.9020 | 40823183 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno
114791671 | ORO LOMA-CANAL #1 013/015 RPLC POLE | 31399014 | ORO LOMA-CANAL #1 | 013/015 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | [6 empty] | '-120.635456 | 37.0526 | ETL.9020 | 40747797 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 9
114792562 | IGNACIO-S.RAFAEL#3 7/148 REPL O/L POLE | 31404626 | IGNACIO-SAN RAFAEL #3 NF | 007/148 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-122.523508 | 37.9742 | ETL.1860 | 40811035 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville
114796313 | CLEAR LAKE-KONOCTI 15/00 REPL NG POLE | 31404612 | CLEAR LAKE-KONOCTI | 015/000 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-122.856964 | 38.9822 | ETL.6852 | 40587043 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville
114800273 | EXCHEQUER-LE GRAND 027/001 RPL POLE | 31394006 | EXCHEQUER-LE GRAND | 027/001 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.270741 | 37.2115 | ETL.1560 | 40594871 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 5
114800289 | COTTONWOOD #1 B035/456 SWIW NG REPA | 43747300 | COTTONWOOD #1 | B035/456 | ICW | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-122.189412 | 39.9352 | ETL.6620 | 42578800 | Switch-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
114810459 | COLEMAN-COTTONWOOD 0/018 SWIS NG REPA | 43746654 | COLEMAN-COTTONWOOD | 000/018 | ICE | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Valley | Non-WSIP | [6 empty] | '-122.139721 | 40.4087 | ETL.6430 | 44419030 | Switch-Steel | No Good/Out of Stdrd | Repair | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 623 | Table Mountain
114837253 | TAFT-ELK HILLS 70KV 1/19 SEPARATE DISTRO | 31404130 | TAFT-ELK HILLS | 001/019 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP |  |  |  | Distribution |  | '-119.482981 | 35.1489 | ETL.9220 | 40609377 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Midway
114837692 | HUMBOLDT BAY-RIO DELL JCT 10/8 RPLC POLE | 31404621 | HUMBOLDT BAY-RIO DELL JCT | 010/008 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Coast | Non-WSIP | [6 empty] | '-124.197485 | 40.6373 | ETL.7100 | 40860998 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2019-04-16
114838107 | ATWATER-LIVINGSTON-MERCED 21/005 rplc pl | 31402129 | ATWATER-MERCED | 021/005 | 93G | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.759935 | 37.3615 | ETL.1030 | 40746673 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 401 | Fresno
114838160 | ATWATER-LIVINGSTON-MERCED 21/4A RPL POLE | 31402129 | ATWATER-MERCED | 021/004A | 93G | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.759934 | 37.3606 | ETL.1030 | 40576639 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 401 | Fresno
114838161 | ATWATER-LIVINGSTON-MERCED 21/4 RPL POLE | 31402129 | ATWATER-MERCED | 021/004 | 93G | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.759722 | 37.3605 | ETL.1030 | 40762822 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 401 | Fresno
114838162 | ATWATER-LIVINGSTON-MERCED 21/3 RPL POLE | 31402129 | ATWATER-MERCED | 021/003 | 93G | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.758757 | 37.3605 | ETL.1030 | 40644995 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 401 | Fresno
114838163 | ATWATER-LIVINGSTON-MERCED 21/2 RPL POLE | 31402129 | ATWATER-MERCED | 021/002 | 93G | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.757535 | 37.3605 | ETL.1030 | 40647809 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 401 | Fresno
114838164 | ATWATER-LIVINGSTON-MERCED 21/1 RPL POLE | 31402129 | ATWATER-MERCED | 021/001 | 93G | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.756354 | 37.3605 | ETL.1030 | 40594361 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 401 | Fresno
114838165 | ATWATER-LIVINGSTON-MERCED 21/0 RPL POLE | 31402129 | ATWATER-MERCED | 021/000 | 93G | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.755148 | 37.3605 | ETL.1030 | 40582611 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 401 | Fresno
114838166 | ATWATER-LIVINGSTON-MERCED 20/14 RPL POLE | 31402129 | ATWATER-MERCED | 020/014 | 93G | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.753925 | 37.3605 | ETL.1030 | 40764912 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 401 | Fresno
114838168 | ATWATER-LIVINGSTON-MERCED 20/13 RPL POLE | 31402128 | ATWATER-MERCED | 020/013 | 93G | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.752718 | 37.3605 | ETL.1030 | 40644992 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 401 | Fresno
114838169 | ATWATER-LIVINGSTON-MERCED 20/12 RPL POLE | 31402128 | ATWATER-MERCED | 020/012 | 93G | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.751517 | 37.3605 | ETL.1030 | 40677061 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 401 | Fresno
114838190 | ATWATER-LIVINGSTON-MERCED 20/11 RPL POLE | 31402128 | ATWATER-MERCED | 020/011 | 93G | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.750287 | 37.3605 | ETL.1030 | 40581436 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 401 | Fresno
114838191 | ATWATER-LIVINGSTON-MERCED 20/10 RPL POLE | 31402128 | ATWATER-MERCED | 020/010 | 93G | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.749111 | 37.3605 | ETL.1030 | 40608973 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 401 | Fresno
114838192 | ATWATER-LIVINGSTON-MERCED 20/9 RPL POLE | 31402128 | ATWATER-MERCED | 020/009 | 93G | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.747906 | 37.3605 | ETL.1030 | 40862991 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 401 | Fresno
114838193 | ATWATER-LIVINGSTON-MERCED 20/8 RPL POLE | 31402128 | ATWATER-MERCED | 020/008 | 93G | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.746692 | 37.3605 | ETL.1030 | 40868704 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 401 | Fresno
114838196 | ATWATER-LIVINGSTON-MERCED 20/7 RPL POLE | 31402128 | ATWATER-MERCED | 020/007 | 93G | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.745514 | 37.3605 | ETL.1030 | 40805415 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 401 | Fresno
114838198 | ATWATER-LIVINGSTON-MERCED 20/6 RPL POLE | 31402128 | ATWATER-MERCED | 020/006 | 93G | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.744294 | 37.3605 | ETL.1030 | 40817376 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 401 | Fresno
114838199 | ATWATER-LIVINGSTON-MERCED 20/4 RPL POLE | 31402128 | ATWATER-MERCED | 020/004 | 93G | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.741697 | 37.3605 | ETL.1030 | 40759520 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 401 | Fresno
114838261 | ATWATER-LIVINGSTON-MERCED 20/1 RPL POLE | 31402127 | ATWATER-MERCED | 020/001 | 93G | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.738223 | 37.3605 | ETL.1030 | 40597106 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Contract | Capital | 401 | Fresno
114838262 | ATWATER-LIVINGSTON-MERCED 20/0 RPL POLE | 31402127 | ATWATER-MERCED | 020/000 | 93G | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.736985 | 37.3606 | ETL.1030 | 40582608 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Contract | Capital | 401 | Fresno
114838263 | XTWATER-LIVINGSTON-MERCED 19/14 RPL POLE | 31402127 | ATWATER-MERCED | 019/014 | 93G | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.735788 | 37.3605 | ETL.1030 | 40759518 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Contract | Capital | 401 | Fresno
114838264 | ATWATER-LIVINGSTON-MERCED 19/13 RPL POLE | 31402127 | ATWATER-MERCED | 019/013 | 93G | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.734581 | 37.3605 | ETL.1030 | 40644988 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Contract | Capital | 401 | Fresno
114838265 | ATWATER-LIVINGSTON-MERCED 19/12 RPL POLE | 31402127 | ATWATER-MERCED | 019/012 | 93G | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.733383 | 37.3605 | ETL.1030 | 40677055 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Contract | Capital | 401 | Fresno
114838267 | ATWATER-LIVINGSTON-MERCED 19/11 RPL POLE | 31402127 | ATWATER-MERCED | 019/011 | 93G | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.732178 | 37.3605 | ETL.1030 | 40581435 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Contract | Capital | 401 | Fresno
114838268 | ATWATER-LIVINGSTON-MERCED 19/10 RPL POLE | 31402127 | ATWATER-MERCED | 019/010 | 93G | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.730979 | 37.3605 | ETL.1030 | 40600765 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Contract | Capital | 401 | Fresno
114838269 | ATWATER-LIVINGSTON-MERCED 19/09 RPL POLE | 31402127 | ATWATER-MERCED | 019/009 | 93G | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.729771 | 37.3605 | ETL.1030 | 40858289 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Contract | Capital | 401 | Fresno
114838332 | ATWATER-LIVINGSTON-MERCED 19/6 RPL POLE | 31402127 | ATWATER-MERCED | 019/006 | 93G | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.726178 | 37.3605 | ETL.1030 | 40817374 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Contract | Capital | 401 | Fresno
114838333 | ATWATER-LIVINGSTON-MERCED 19/5 RPL POLE | 31402127 | ATWATER-MERCED | 019/005 | 93G | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.72496 | 37.3605 | ETL.1030 | 40746671 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Contract | Capital | 401 | Fresno
114839337 | LIVINGSTON-LIVINGSTN JCT 13/04 RPL POLE | 31402121 | LIVINGSTON-LIVINGSTON JCT | 013/004 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.807467 | 37.2054 | ETL.8920 | 40747891 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  |  | NWR
114839338 | LIVINGSTN-LIVINGSTN JCT 012/16 RPL POLE | 31402121 | LIVINGSTON-LIVINGSTON JCT | 012/016 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.807467 | 37.2101 | ETL.8920 | 41116220 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  |  | NWR
114839598 | LIVINGSTON-LIVINGSTON JCT 03/03 RPL POLE | 31402121 | LIVINGSTON-LIVINGSTON JCT | 003/003 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.76046 | 37.3139 | ETL.8920 | 40646084 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 9
114839604 | CLEARLAKE-HOPLAND 9/12 REPL NG POLE | 31404610 | CLEAR LAKE-HOPLAND | 009/012 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-122.911522 | 38.9968 | ETL.6390 | 40699113 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  | 2019-04-30
114839613 | LIVINGSTON-LIVINGSTN JCT 04/03 RPLC POLE | 31402121 | LIVINGSTON-LIVINGSTON JCT | 004/003 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.762898 | 37.3026 | ETL.8920 | 40661955 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 9
114849117 | PANOCHE-ORO LOMA 013/009 RPLC POLE | 31402122 | PANOCHE-ORO LOMA | 013/009 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.602034 | 36.8439 | ETL.3240 | 40869997 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno
114850008 | KEARNEY-BOWLES 000/010 RPL POLE | 31403396 | KEARNEY-BOWLES | 000/010 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.872845 | 36.6982 | ETL.8820 | 40607346 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 5
114850055 | KEARNEY-BOWLES 001/004 RPLC POLE | 31403396 | KEARNEY-BOWLES | 001/004 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.866545 | 36.6902 | ETL.8820 | 40764624 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 5
114850072 | KEARNEY-BOWLES 001/001 TRUSS POLE | 31403396 | KEARNEY-BOWLES | 001/001 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.868882 | 36.6932 | ETL.8820 | 40596315 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 5
114856303 | HENRIETTA-LEMOORE NAS:059/014 RPLC POLE | 31403111 | HENRIETTA-LEMOORE NAS | :059/014 | 93I | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.905233 | 36.2568 | ETL.8780 | 40758601 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 508 | Fresno
114856539 | KEARNEY-BOWLES 002/005 RPLC POLE | 31403396 | KEARNEY-BOWLES | 002/005 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.855147 | 36.6785 | ETL.8820 | 40764291 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 5
114856566 | KEARNEY-BOWLES 002/000 RPLC POLE | 31403396 | KEARNEY-BOWLES | 002/000 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.860103 | 36.683 | ETL.8820 | 40584540 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 5
114856611 | KEARNEY-BOWLES 002/003 RPLC POLE | 31403396 | KEARNEY-BOWLES | 002/003 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.857077 | 36.6803 | ETL.8820 | 40646442 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 5
114856614 | KEARNEY-BOWLES 002/007 RPLC POLE | 31403396 | KEARNEY-BOWLES | 002/007 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.853541 | 36.6771 | ETL.8820 | 40821710 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 5
114856621 | PANOCHE-ORO LOMA 017/000 RPLC POLE | 31402122 | PANOCHE-ORO LOMA | 017/000 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.629883 | 36.8822 | ETL.3240 | 40596842 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno
114856637 | KEARNEY-BOWLES 002/009 RPLC POLE | 31403396 | KEARNEY-BOWLES | 002/009 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.851124 | 36.6749 | ETL.8820 | 40871508 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 5
114856654 | KEARNEY-BOWLES 003/007 REPLACE POLE | 31403396 | KEARNEY-BOWLES | 003/007 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.841225 | 36.6657 | ETL.8820 | 40820309 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 5
114856658 | KEARNEY-BOWLES 004/007 RPLC POLE | 31403396 | KEARNEY-BOWLES | 004/007 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.830156 | 36.6544 | ETL.8820 | 40820311 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 5
114856875 | PANOCHE-ORO LOMA 017/006 REPLACE POLE | 31402122 | PANOCHE-ORO LOMA | 017/006 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.63781 | 36.8835 | ETL.3240 | 40805693 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno
114856969 | PANOCHE-ORO LOMA 017/012 RPLC POLE | 31402122 | PANOCHE-ORO LOMA | 017/012 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.645736 | 36.8849 | ETL.3240 | 40648486 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno
114857247 | STROUD SW STA-STROUD 000/017 RPLC POLE | 31404129 | STROUD SW STA-STROUD | 000/017 | 70Y | B | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.151686 | 36.5313 | ETL.9190 | 40806067 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno
114857645 | KEARNEY-BOWLES 005/003 RPL POLE | 31402120 | KEARNEY-BOWLES | 005/003 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.823092 | 36.6473 | ETL.8820 | 40646444 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 5
114859423 | STROUD S S-SCHINDLER 06/007 RPL STB POLE | 31404128 | STROUD SW STA-SCHINDLER | 006/007 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.170488 | 36.5013 | ETL.9180 | 40815627 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno
114860644 | STROUD SW STA-SCHINDLER 006/008 RPL POLE | 31404128 | STROUD SW STA-SCHINDLER | 006/008 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.170462 | 36.5003 | ETL.9180 | 40872875 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno
114861216 | KEARNEY-BOWLES 007/010 RPLC POLE | 31402120 | KEARNEY-BOWLES | 007/010 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.791681 | 36.6184 | ETL.8820 | 40609435 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 5
114861245 | KEARNEY-BOWLES 007/000 RPLC POLE | 31402120 | KEARNEY-BOWLES | 007/000 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.801467 | 36.6269 | ETL.8820 | 40607710 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 5
114861291 | KEARNEY-BOWLES 009/001 RPLC POLE | 31402120 | KEARNEY-BOWLES | 009/001 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.775003 | 36.606 | ETL.8820 | 40596601 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 5
114863139 | STROUD S S SCHINDLER 007/007 RPL POLE | 31404128 | STROUD SW STA-SCHINDLER | 007/007 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.16797 | 36.4876 | ETL.9180 | 40819988 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno
114863796 | GLENN #3_008/163 CNDW NG REPA | 43621091 | GLENN #3 | 008/163 | ICW | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-122.00965 | 39.7474 | ETL.6940 | 40893865 | Conductor-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
114864112 | CRSCNT SW STA-SCHNDLR 009/002 RPL POLE | 31404128 | STROUD SW STA-SCHINDLER | 009/002 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.139818 | 36.4848 | ETL.9180 | 40685909 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno
114864482 | CRSCNT SW STA-SCHNDLR 009/011 RPL POLE | 31404128 | STROUD SW STA-SCHINDLER | 009/011 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.139327 | 36.4762 | ETL.9180 | 40597553 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno
114864576 | CRSNT SW STA-SCHNDLR 009/012 RPLC POLE | 31404128 | STROUD SW STA-SCHINDLER | 009/012 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.13926 | 36.4752 | ETL.9180 | 40675104 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno
114883785 | IGNACIO-ALTO 14/125 CLEAN INSULATORS | 43749531 | IGNACIO-ALTO | 014/125 | ICD | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Coast | Non-WSIP | [6 empty] | '-122.514064 | 37.9373 | ETL.7150 | 40651470 | Insulator | Contaminated | Ground Wash | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 622 | Lakeville |  |  | 2019-04-12
114883821 | IGNACIO-ALTO 14/124 CLEAN INSULATORS | 43749531 | IGNACIO-ALTO | 014/124 | ICD | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Coast | Non-WSIP | [6 empty] | '-122.514076 | 37.9375 | ETL.7150 | 40701420 | Insulator | Contaminated | Ground Wash | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 622 | Lakeville |  |  | 2019-04-12
114886826 | GLENN #3 015/275 RPL X ARM | 31409743 | GLENN #3 | 015/275 | 93E | B | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-121.919297 | 39.796 | ETL.6940 | 40587302 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 637 | Table Mountain |  |  | Yes
114887464 | MALIN-ROUND MTN #2 92/469 INSS NG REPL | 31438846 | MALIN-ROUND MTN #2 | 092/469 | 93K | F | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | Non-WSIP |  |  |  |  | Clearance Cancelled - Internal |  | '-121.911872 | 40.8342 | ETL.6020 | 40869048 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  | Yes
114893593 | GREEN VALLEY-LLAGAS 13/93 SW137 ADJ SW | 43679418 | GREEN VALLEY-LLAGAS | 013/093 | ICE | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP |  |  |  | Internal Process | This section of the line is idle and not a fire risk. This tag will be addressed as part of a future capital project. | '-121.657769 | 37.1257 | ETL.1720 | 40743276 | Switch-Wood | No Good/Out of Stdrd | Repair | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 623 | Moss Landing |  | Y - 10
114893598 | METCALF-GREEN VALLEY 9/63B BOND WIRE | 43659892 | METCALF-GREEN VALLEY | 009/063B | ICW | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP |  |  |  | Internal Process | This section of the line is idle and not a fire risk. This tag will be addressed as part of a future capital project. | '-121.657777 | 37.1258 | ETL.2540 | 44181141 | Insulator Bond Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  | Arcadis | 2019-03-20
114896321 | METCALF-GREEN VALLEY 9/63B SW147 ADJ SW | 43659892 | METCALF-GREEN VALLEY | 009/063B | ICW | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP |  |  |  | Internal Process | This section of the line is idle and not a fire risk. This tag will be addressed as part of a future capital project. | '-121.657777 | 37.1258 | ETL.2540 | 44181141 | Switch-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  | Arcadis | 2019-03-20
114907950 | GLENN #3 019/354 RPR STRW | 31410027 | GLENN #3 | 019/354 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-121.946022 | 39.8461 | ETL.6940 | 40910207 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain
114909275 | PEASE-MARYSVILLE-HARTER 004/084 INSULT | 31403990 | PEASE-MARYSVILLE-HARTER | 004/084 | 93I | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-121.580296 | 39.1699 | ETL.7770 | 40840155 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 508 | Sacramento |  |  | Yes
114910650 | Parkway-Moraga 03/24 REPL BRKN INSUL | 31414411 | PARKWAY-MORAGA | 003/024 | 93K | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-122.207411 | 38.086 | ETL.5930 | 40899171 | Insulator-Steel | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Lakeville |  |  | 2019-03-25
114911833 | GLENN #3 023/435 RPL STRW | 31410027 | GLENN #3 | 023/435 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-121.988481 | 39.8935 | ETL.6940 | 40911984 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain
114912330 | GLENN #3 025/466 RPL STRW | 31410027 | GLENN #3 | 025/466 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-122.00623 | 39.9114 | ETL.6940 | 40911560 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain
114914126 | T2 MALIN-RND MTN#2 72/364A MRKS MISS INS | 43621093 | MALIN-ROUND MTN #2 | 072/364A | ICQ | F | Pre-2020_(1b) Lines with special commitments |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-121.80103 | 41.0756 | ETL.6020 | 41111835 | Marker (i.e. signs)-Steel | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
114914140 | T2 MALIN-RND MTN#2 71/359A MRKS MISS INS | 43621093 | MALIN-ROUND MTN #2 | 071/359A | ICQ | F | Pre-2020_(1b) Lines with special commitments |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-121.788889 | 41.0846 | ETL.6020 | 40576661 | Marker (i.e. signs)-Steel | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
114914465 | BRIGHTON-GRAND ISL #1 19/14 RPR FOOTING | 43748622 | BRIGHTON-GRAND ISLAND #1 | 019/146 | ICQ | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Valley | Non-WSIP | [5 empty] | Circuit Based Scheduling | '-121.548352 | 38.3087 | ETL.1150 | 40820324 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento |  |  | Yes
114921800 | SLAC TAP 000/019 pole replacment | 31418454 | SLAC TAP (NO FLY) | 000/019 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | Central | Non-WSIP | FSRP | [5 empty] | '-122.19979 | 37.4133 | ETL.7221 | 40594869 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Bay |  | Y - 1 | 2019-03-01
114927776 | ESSEX JCT-ARCATA-FAIRHAVEN 3/20 FOOTINGS | 43720612 | ESSEX JCT-ARCATA-FAIRHAVEN | 003/020 | ICQ | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Coast | Non-WSIP | [6 empty] | '-124.147943 | 40.8655 | ETL.6800 | 40616125 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Eureka
114927782 | ESSEX JCT-ARCATA-FAIRHAVEN 3/020 STUBS | 43720612 | ESSEX JCT-ARCATA-FAIRHAVEN | 003/020 | ICQ | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Coast | Non-WSIP | [6 empty] | '-124.147943 | 40.8655 | ETL.6800 | 40616125 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Eureka |  |  | 2020-01-16
114928343 | ESSEX JCT-ARCATA-FAIRHAVEN 9/52 MEMBER | 43720612 | ESSEX JCT-ARCATA-FAIRHAVEN | 009/052 | ICQ | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-124.195692 | 40.8 | ETL.6800 | 40700344 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Eureka |  |  | 2019-07-23
114928417 | ESSEX JCT-ARCATA-FAIRHAVEN 9/051 MEMBER | 43720612 | ESSEX JCT-ARCATA-FAIRHAVEN | 009/051 | ICQ | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-124.197183 | 40.8 | ETL.6800 | 40601243 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Eureka |  |  | 2019-07-23
114928934 | MERCED #1 004/013 RPLC POLE | 31406698 | MERCED #1 | 004/013 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.488198 | 37.2022 | ETL.9000 | 40661554 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 7
114931218 | ESSEX JCT-ARCATA-FAIRHAVEN 8/042 STUBS | 43720612 | ESSEX JCT-ARCATA-FAIRHAVEN | 008/042 | ICQ | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-124.189689 | 40.8211 | ETL.6800 | 40700336 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Eureka |  |  | 2019-07-23
114937999 | CANTUA TAP 001/001 REPLACE POLE | 31405867 | CANTUA TAP | 001/001 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.355397 | 36.4285 | ETL.3251 | 40589243 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno
114938002 | CANTUA TAP 001/002 REPLACE POLE | 31405867 | CANTUA TAP | 001/002 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.354088 | 36.4285 | ETL.3251 | 40648333 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno
114938070 | CANTUA TAP 001/007 RPLC POLE | 31405867 | CANTUA TAP | 001/007 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.347105 | 36.4285 | ETL.3251 | 40818556 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno
114938072 | CANTUA TAP 001/008 RPLC POLE | 31405867 | CANTUA TAP | 001/008 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.3458 | 36.4285 | ETL.3251 | 40865582 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno
114938112 | MERCED #1 006/006 REPLACE POLE | 31406698 | MERCED #1 | 006/006 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.491972 | 37.18 | ETL.9000 | 40806318 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 7
114938596 | GLENN #3 000/009 REFRAME | 31409743 | GLENN #3 | 000/009 | 93E | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-122.132429 | 39.7767 | ETL.6940 | 40822357 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 637 | Table Mountain |  |  | Yes
114938956 | GLENN #3 001/021REPL INSUL | 31409372 | GLENN #3 | 001/021 | 93I | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-122.1145 | 39.777 | ETL.6940 | 40618588 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 508 | Table Mountain |  |  | Yes
114939258 | MERCED #1 011/002 REPLACE POLE | 31406698 | MERCED #1 | 011/002 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.473417 | 37.1283 | ETL.9000 | 40686712 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno
114941091 | ESSEX JCT-ARCATA-FAIRHAVEN 7/37 STRUT | 43720612 | ESSEX JCT-ARCATA-FAIRHAVEN | 007/037 | ICQ | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Coast | Non-WSIP | [6 empty] | '-124.177913 | 40.8273 | ETL.6800 | 40825227 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Eureka |  |  | 2019-07-23
114941598 | ESSEX JCT-ARCATA-FAIRHAVEN 6/35 STRUT | 43720612 | ESSEX JCT-ARCATA-FAIRHAVEN | 006/035 | ICQ | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-124.176047 | 40.832 | ETL.6800 | 40769538 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Eureka |  |  | 2019-07-23
114946593 | DEL MAR-ATLANTIC #2 001/028 RPL POLE | 31413325 | DEL MAR-ATLANTIC #2 | 001/028 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-121.231716 | 38.79 | ETL.6170 | 40645364 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
114946888 | LS BNOS-LIVINGSTN JCT-CNL S0/3 RPLC POLE | 31406692 | LOS BANOS-LIVINGSTON JCT-CANAL | S000/003 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-121.016346 | 37.076 | ETL.8940 | 40653025 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 5 | CDFW
114946889 | LS BNOS-LIVINGSTN JCT-CNL S0/2 RPLC POLE | 31406692 | LOS BANOS-LIVINGSTON JCT-CANAL | S000/002 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-121.016544 | 37.076 | ETL.8940 | 40667417 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 5 | CDFW
114949445 | SCHULTE SW STA-KASSON-MANTECA -115 kV_00 | 43632326 | SCHULTE SW STA-KASSON-MANTECA | 009/070 | ICQ | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | Central | Non-WSIP | [6 empty] | '-121.45152 | 37.7203 | ETL.7472 | 40579835 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - Prog Multi
114959966 | MERCED #1 012/001 RPLC POLE | 31406698 | MERCED #1 | 012/001 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.47339 | 37.1147 | ETL.9000 | 40582260 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno
114960085 | MERCED #1 012/004 RPLC POLE | 31406698 | MERCED #1 | 012/004 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.473373 | 37.112 | ETL.9000 | 40747705 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno
114960231 | SANGER-MALAGA 000/011 RPLC POLE | 31406693 | SANGER-MALAGA | 000/011 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.620579 | 36.7104 | ETL.3600 | 40582683 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno
114960286 | SANGER-MALAGA 000/016 RPLC POLE | 31406693 | SANGER-MALAGA | 000/016 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.624819 | 36.7125 | ETL.3600 | 40806741 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno
114960288 | MERCED #1 012/009 RPLC POLE | 31406698 | MERCED #1 | 012/009 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.47334 | 37.1074 | ETL.9000 | 40858983 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno
114960350 | MERCED #1 012/013 RPLC POLE | 31406698 | MERCED #1 | 012/013 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.473377 | 37.1038 | ETL.9000 | 40645941 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno
114960941 | ESSEX JCT-ARCATA-FAIRHAVEN 6/34 STRUT | 43720612 | ESSEX JCT-ARCATA-FAIRHAVEN | 006/034 | ICQ | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Coast | Non-WSIP | [6 empty] | '-124.174939 | 40.835 | ETL.6800 | 40753489 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Eureka |  |  | 2019-07-23
114961304 | KELLEY TAP 70KV 1/13 REPL POLE | 31406691 | KELLEY TAP | 001/013 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | [6 empty] | '-119.06495 | 35.0448 | ETL.9293 | 40760917 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Midway |  | Y - Prog Land | DWR
114961883 | MERCED #1 014/001 RPLC POLE | 31406698 | MERCED #1 | 014/001 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.473523 | 37.0859 | ETL.9000 | 40582265 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 7
114961888 | MERCED #1 014/000 RPLC POLE | 31406698 | MERCED #1 | 014/000 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.473348 | 37.0859 | ETL.9000 | 40583822 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 7
114962656 | WESTLANDS #18 RA TAP 002/001 RPLC POLE | 31406697 | WESTLANDS #18 RA TAP | 002/001 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.262002 | 36.3739 | ETL.3252 | 40581640 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  |  | DWR
114962708 | WESTLANDS #18 RA TAP 002/003 RPLC POLE | 31406697 | WESTLANDS #18 RA TAP | 002/003 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | [6 empty] | '-120.260861 | 36.3723 | ETL.3252 | 40645211 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 3 | DWR
114962875 | WESTLANDS #18 RA TAP 003/006 RPLC POLE | 31406697 | WESTLANDS #18 RA TAP | 003/006 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.251668 | 36.3577 | ETL.3252 | 40805651 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 3 | DWR
114963070 | SMARTVILLE-MARYSVILLE 019/385 RPL POLE | 31409909 | SMARTVILLE-MARYSVILLE | 019/385 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-121.579668 | 39.1468 | ETL.7980 | 40868724 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento
114963079 | MERCED #1 017/012 RPLC POLE | 31406720 | MERCED #1 | 017/012 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.473443 | 37.0319 | ETL.9000 | 40688748 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC crdy srdy |  |  |  | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 7
114963165 | MERCED #1 017/013 RPLC POLE | 31406720 | MERCED #1 | 017/013 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.47346 | 37.0307 | ETL.9000 | 40661923 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC crdy srdy |  |  |  | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 7
114963676 | SMARTVILLE-MARYSVILLE 17/344 RPL AUTO SP | 43760141 | SMARTVILLE-MARYSVILLE | 017/344 | ICW | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-121.55554 | 39.1699 | ETL.7980 | 40602060 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Sacramento |  |  | Yes
114963941 | SMARTVILLE-MARYSVILLE 17/336 RPL INSUL | 31409747 | SMARTVILLE-MARYSVILLE | 017/336 | 93I | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-121.55109 | 39.1735 | ETL.7980 | 40694087 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 508 | Sacramento |  |  | Yes
114965594 | CORTINA-VACA 27/176 RPR GRD STRAP | 43527394 | CORTINA-VACA | 027/176 | ICS | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-122.003028 | 38.7637 | ETL.4540 | 40689791 | Shield Wire / OPGW-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes
114967589 | TESLA-METCALF 006/025 RPL INSS | 31431935 | TESLA-METCALF | 006/025 | 93K | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | Central | Non-WSIP | FSRP |  |  |  | Internal Process | This is a 500kV line and it could not be done barehand because of the tower arm condition. The crew ruled that this w unsa | '-121.587724 | 37.6217 | ETL.6110 | 40790481 | Insulator-Steel | No Good/Out of Stdrd | Replace | CONS | CONS | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  |  | 2019-06-04
114968158 | CARIBOU-PALERMO 27/221 INSS NG REPA | 43735847 | CARIBOU-PALERMO | :027/221 | ICS | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Valley | Non-WSIP | FSRP |  |  |  | Field Operations |  | '-121.432073 | 39.8164 | ETL.3190 | 40617147 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain
114968341 | CARIBOU PALERMO 02/022 INSS NG REPL | 31413180 | CARIBOU-PALERMO | 002/022 | 93K | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Valley | Non-WSIP | FSRP |  |  |  | Field Operations |  | '-121.539982 | 39.4859 | ETL.3190 | 40726131 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  | Yes
114968786 | MERCED #1 019/011 RPLC POLE | 31406720 | MERCED #1 | 019/011 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.473635 | 37.0046 | ETL.9000 | 40582275 | Structure-Wood | Rotten | Replace | UNSC crdy srdy |  |  |  | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 7
114968803 | MERCED #1 019/009 REPLC POLE | 31406720 | MERCED #1 | 019/009 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.473667 | 37.0064 | ETL.9000 | 40871658 | Structure-Wood | Rotten | Replace | UNSC crdy srdy |  |  |  | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 7
114968825 | PEASE-MARYSVILLE-HARTER 7/150 RPL POLE | 31409617 | PEASE-MARYSVILLE-HARTER | 007/150 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-121.58322 | 39.1421 | ETL.7770 | 40766646 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Encroachment Permit Needed
114968884 | MERCED #1 019/014 REPL POLE | 31406720 | MERCED #1 | 019/014 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.473615 | 37.0019 | ETL.9000 | 40747719 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC crdy srdy |  |  |  | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 7
114968910 | ESSEX JCT-ARCATA-FAIRHAVN 4/22 RPL TOWER | 31483156 | ESSEX JCT-ARCATA-FAIRHAVEN | 004/022 | 70S | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Coast | Non-WSIP | [6 empty] | '-124.154314 | 40.8639 | ETL.6800 | 40663729 | Structure-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Pole Program | Capital | 426 | Eureka |  |  | 2019-07-23
114969488 | MERCED #1 021/005 RPLC POLE | 31406720 | MERCED #1 | 021/005 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.473817 | 36.9802 | ETL.9000 | 40763667 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC crdy srdy |  |  |  | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno
114969551 | MERCED #1 021/004 REPLC POLE | 31406720 | MERCED #1 | 021/004 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.473807 | 36.9811 | ETL.9000 | 40764358 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC crdy srdy |  |  |  | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 7
114969562 | MERCED #1 021/007 REPLC POLE | 31406720 | MERCED #1 | 021/007 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.473762 | 36.9784 | ETL.9000 | 40806190 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC crdy srdy |  |  |  | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno
114969735 | MERCED #1 022/007 RPLC POLE | 31406721 | MERCED #1 | 022/007 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.473569 | 36.9639 | ETL.9000 | 40806192 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 7
114969770 | MERCED #1 022/006 RPLC POLE | 31406721 | MERCED #1 | 022/006 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.47357 | 36.9648 | ETL.9000 | 40821545 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 7
114969916 | MERCED #1 022/014 RPLC POLE | 31406721 | MERCED #1 | 022/014 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.473442 | 36.9575 | ETL.9000 | 40747723 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 7
114969993 | MERCED #1 022/013 REPLC POLE | 31406721 | MERCED #1 | 022/013 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.473463 | 36.9585 | ETL.9000 | 40661928 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 7
114970045 | MERCED #1 022/016A REPLACE POLE | 31406721 | MERCED #1 | 022/016A | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.473424 | 36.9548 | ETL.9000 | 44400727 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 7
114970159 | MERCED #1 023/003 RPLC POLE | 31406722 | MERCED #1 | 023/003 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.473355 | 36.9521 | ETL.9000 | 40645961 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 7
114970469 | MERCED #1 023/005 RPLC POLE | 31406722 | MERCED #1 | 023/005 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.473312 | 36.9502 | ETL.9000 | 40747722 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 7
114970563 | MERCED #1 023/004 REPLACE POLE | 31406722 | MERCED #1 | 023/004 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.473337 | 36.9512 | ETL.9000 | 40747725 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 7
114970641 | MERCED #1 023/006 REPLC POLE | 31406722 | MERCED #1 | 023/006 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.473285 | 36.9493 | ETL.9000 | 40806350 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 7
114970671 | MERCED #1 023/007 RPLC POLE | 31406722 | MERCED #1 | 023/007 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.473283 | 36.9484 | ETL.9000 | 40820201 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 7
114970682 | MERCED #1 023/009 REPLC POLE | 31406722 | MERCED #1 | 023/009 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.473242 | 36.9466 | ETL.9000 | 40858991 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 7
114970722 | MERCED #1 023/011 RPLC POLE | 31406722 | MERCED #1 | 023/011 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.473203 | 36.9448 | ETL.9000 | 40582286 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 7
114970790 | MERCED #1 023/002A REPLACE POLE | 31406722 | MERCED #1 | 023/002A | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.473398 | 36.953 | ETL.9000 | 44400728 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 7
114970879 | MERCED #1 022/009 RPLC POLE | 31406721 | MERCED #1 | 022/009 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.473478 | 36.9621 | ETL.9000 | 40858989 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 7
114970946 | MERCED #1 022/011 RPLC POLE | 31406721 | MERCED #1 | 022/011 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.47352 | 36.9603 | ETL.9000 | 40582283 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno
114970962 | MERCED #1 022/008 RPLC POLE | 31406721 | MERCED #1 | 022/008 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.473507 | 36.963 | ETL.9000 | 40873086 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno
114970963 | MERCED #1 021/013 RPLC POLE | 31406720 | MERCED #1 | 021/013 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.473685 | 36.973 | ETL.9000 | 40645957 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC crdy srdy |  |  |  | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 7
114970971 | MERCED #1 022/010 RPLC POLE | 31406721 | MERCED #1 | 022/010 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.473553 | 36.9612 | ETL.9000 | 40583834 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 7
114970981 | MERCED #1 021/012 RPLCE POLE | 31406720 | MERCED #1 | 021/012 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.473688 | 36.9739 | ETL.9000 | 40650217 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC crdy srdy |  |  |  | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno
114977254 | MERCED #1 023/012 RPLC POLES | 31406722 | MERCED #1 | 023/012 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.473205 | 36.9439 | ETL.9000 | 40650229 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 7
114978090 | MERCED #1 024/006 RPLC POLE | 31406722 | MERCED #1 | 024/006 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.472502 | 36.9367 | ETL.9000 | 40806352 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno
114978112 | MERCED #1 024/008 RPLC BURNT POLE | 31406722 | MERCED #1 | 024/008 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.471177 | 36.9352 | ETL.9000 | 40859090 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 7
114978834 | MERCED #1 031/015 RPLC POLE | 31412921 | MERCED #1 | 031/015 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.207305 | 36.9238 | ETL.9000 | 40747745 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 7
114979164 | MERCED #1 032/010 REPL POLE | 31412921 | MERCED #1 | 032/010 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.220478 | 36.9238 | ETL.9000 | 40583864 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 7
114979955 | LOCKEFORD-LODI #3 001/032 rpl pole | 31418885 | LOCKEFORD-LODI #3 | 001/032 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | Central | Non-WSIP | FSRP | [5 empty] | '-121.187137 | 38.1016 | ETL.7450 | 40864302 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Victor |  | Y - 2
114980125 | MERCED #1 034/006 REPLACE POLE | 31412921 | MERCED #1 | 034/006 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.250418 | 36.9239 | ETL.9000 | 40806364 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 7
114980683 | MERCED #1 035/013 RPLC POLE | 31412921 | MERCED #1 | 035/013 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.276888 | 36.9237 | ETL.9000 | 40645978 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 7
114980824 | SANGER-MALAGA 004/007 RPLC POLE | 31406693 | SANGER-MALAGA | 004/007 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.679938 | 36.7143 | ETL.3600 | 40806523 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno
114980889 | SANGER-MALAGA 005/010 RPLC POLE | 31406693 | SANGER-MALAGA | 005/010 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.691085 | 36.7084 | ETL.3600 | 40596887 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno
114981455 | MERCED #1 037/009 RPLC POLE | 31412921 | MERCED #1 | 037/009 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.308753 | 36.9237 | ETL.9000 | 40859010 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 7
114981514 | MERCED #1 037/015 RPLC POLE | 31412921 | MERCED #1 | 037/015 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.315183 | 36.9236 | ETL.9000 | 40747755 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 7
114981598 | SANGER-MALAGA 005/016 RPLC POLE | 31406693 | SANGER-MALAGA | 005/016 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.691038 | 36.7039 | ETL.3600 | 40806753 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno
114981646 | SANGER-MALAGA 006/004 RPLC POLE | 31406693 | SANGER-MALAGA | 006/004 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.695435 | 36.7004 | ETL.3600 | 40748226 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno
114981651 | SANGER-MALAGA 006/005 RPLC POLE | 31406693 | SANGER-MALAGA | 006/005 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.696581 | 36.7004 | ETL.3600 | 40756735 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno
114981681 | MERCED #1 038/004 RPLC POLE | 31412921 | MERCED #1 | 038/004 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.321195 | 36.9236 | ETL.9000 | 40763983 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 7
114981712 | MERCED #1 038/009 RPLC POLE | 31412921 | MERCED #1 | 038/009 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.32716 | 36.9236 | ETL.9000 | 40872071 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 7
114981859 | HUMBOLDT #1 1/5 REPLACE POLE | 31409910 | HUMBOLDT #1 | 001/005 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Coast | Non-WSIP | [6 empty] | '-124.092664 | 40.7905 | ETL.7113 | 40769620 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2019-07-05
114981875 | HUMBOLDT #1 2/6 REPLACE POLE | 31409910 | HUMBOLDT #1 | 002/006 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-124.091234 | 40.8066 | ETL.7113 | 40809387 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2019-07-05
114981877 | HUMBOLDT #1 4/5 REPLACE POLE | 31409910 | HUMBOLDT #1 | 004/005 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-124.080208 | 40.832 | ETL.7113 | 40751048 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka
114981879 | HUMBOLDT #1 5/6 REPLACE POLE | 31409910 | HUMBOLDT #1 | 005/006 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-124.077988 | 40.8435 | ETL.7113 | 40827179 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2019-07-05
114982064 | HUMBOLDT BAY-HUMBOLDT #1 7/9 RPLC POLE | 31411534 | HUMBOLDT BAY-HUMBOLDT #1 | 007/009 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Coast | Non-WSIP | [6 empty] | '-124.116503 | 40.7807 | ETL.7080 | 40860888 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2019-04-23
114982250 | HUMBOLDT-EUREKA 3/22 RPLC GUY POLE | 31475440 | HUMBOLDT-EUREKA | 003/022 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Coast | Non-WSIP | [6 empty] | '-124.175959 | 40.7928 | ETL.7120 | 40658249 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2020-02-17
114982298 | HUMBOLDT BAY-EUREKA 2/16 REPLACE POLE | 31409911 | HUMBOLDT BAY-EUREKA | 002/016 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Coast | Non-WSIP | [6 empty] | '-124.177995 | 40.7591 | ETL.7070 | 40809383 | Structure-Wood | Rotten | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2019-08-12
114982320 | MERCED #1 039/010 RPLC POLE | 31412921 | MERCED #1 | 039/010 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.346317 | 36.9236 | ETL.9000 | 40606976 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 7
114982342 | HUMBOLDT BAY-EUREKA 4/4 REPLACE POLE | 31409911 | HUMBOLDT BAY-EUREKA | 004/004 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Coast | Non-WSIP | [6 empty] | '-124.180214 | 40.7742 | ETL.7070 | 40751057 | Structure-Wood | Rotten | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka
114982394 | HUMBOLDT BAY-EUREKA 4/9 REPLACE POLE | 31409911 | HUMBOLDT BAY-EUREKA | 004/009 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Coast | Non-WSIP | [6 empty] | '-124.180204 | 40.7791 | ETL.7070 | 40876284 | Structure-Wood | Rotten | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka
114982483 | HUMBOLDT BAY-EUREKA 4/12 REPLACE POLE | 31409911 | HUMBOLDT BAY-EUREKA | 004/012 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Coast | Non-WSIP | [6 empty] | '-124.178475 | 40.7806 | ETL.7070 | 40701275 | Structure-Wood | Rotten | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka
114982514 | HUMBOLDT BAY-EUREKA 4/13 REPLACE POLE | 31409911 | HUMBOLDT BAY-EUREKA | 004/013 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Coast | Non-WSIP | [6 empty] | '-124.177165 | 40.7806 | ETL.7070 | 40668002 | Structure-Wood | Rotten | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2019-08-12
114982703 | KING CITY-COBURN #1 A19/315 REPLC POLE | 31398371 | KING CITY-COBURN #1 | A019/315 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-121.311143 | 36.3961 | ETL.7320 | 40699583 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Moss Landing |  | Arcadis | 2019-03-27
114983798 | SANGER-MALAGA 008/004 RPLC POLE | 31406693 | SANGER-MALAGA | 008/004 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.727292 | 36.6984 | ETL.3600 | 40759153 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno
114983910 | SANGER-MALAGA 008/006 RPLC POLE | 31406693 | SANGER-MALAGA | 008/006 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.727292 | 36.6972 | ETL.3600 | 40806760 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno
114984988 | MERCED #1 040/007 RPLC POLE | 31412920 | MERCED #1 | 040/007 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.361878 | 36.9236 | ETL.9000 | 40806217 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 7
114985541 | MERCED #1 041/014 RPLC POLE | 31412920 | MERCED #1 | 041/014 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.388192 | 36.9235 | ETL.9000 | 40764371 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 7
114985563 | MERCED #1 042/000 RPLC POLE | 31412920 | MERCED #1 | 042/000 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.38939 | 36.9235 | ETL.9000 | 40606982 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 7
114986867 | MERCED #1 043/002 RPLC POLE | 31412920 | MERCED #1 | 043/002 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.409748 | 36.9234 | ETL.9000 | 40650296 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 7
114986885 | LOS BANOS-PACHECO 008/004 RPLC POLE | 31412756 | LOS BANOS-PACHECO | 008/004 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-121.189732 | 37.0745 | ETL.8960 | 40764182 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 5 | CDFW/ NWR
114987072 | MERCED #1 044/002 RPLC POLE | 31412920 | MERCED #1 | 044/002 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.427708 | 36.9234 | ETL.9000 | 40687524 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 7
114987101 | MERCED #1 044/005 RPLC POLE | 31412920 | MERCED #1 | 044/005 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.431312 | 36.9234 | ETL.9000 | 40763651 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 7
114987104 | MERCED #1 044/007 RPLC POLE | 31412920 | MERCED #1 | 044/007 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.433693 | 36.9234 | ETL.9000 | 40806222 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 7
114987221 | MERCED #1 044/012 RPLC POLE | 31412920 | MERCED #1 | 044/012 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.439692 | 36.9234 | ETL.9000 | 40687529 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 7
114987383 | MERCED #1 045/000 RPLC POLE | 31412920 | MERCED #1 | 045/000 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.443433 | 36.9234 | ETL.9000 | 40606985 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 7
114987447 | MERCED #1 045/005 RPLC POLE | 31412920 | MERCED #1 | 045/005 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.449241 | 36.9234 | ETL.9000 | 40763653 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 7
114994174 | T2 Cortina-Mendo#1 44/214 RPL FLSH INSL | 31414402 | CORTINA-MENDOCINO #1 | 044/214 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-122.930941 | 39.164 | ETL.1330 | 40791987 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 532 | Lakeville
114994266 | CORTINA-MENDO#1 44/213 REMOVE NEST | 43721139 | CORTINA-MENDOCINO #1 | 044/213 | ICS | E | Pre-2020_(9a) Other ignition related |  |  |  |  | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-122.926526 | 39.1593 | ETL.1330 | 40659624 | Structure-Steel | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Lakeville
114997982 | DINUBA-OROSI 011/010 RPLC POLE | 31412754 | DINUBA-OROSI | 011/010 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.250922 | 36.5362 | ETL.8610 | 44249966 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno
114998025 | DINUBA-OROSI 011/011 RPLC POLE | 31412754 | DINUBA-OROSI | 011/011 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.250926 | 36.5353 | ETL.8610 | 40591606 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno
114998093 | CENTERVILLE-TBL MTN-OROV 21/439 STRW ROT | 31418882 | CENTERVILLE-TABLE MTN-OROVILLE | 021/439 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-121.5727 | 39.5001 | ETL.6330 | 40815809 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
114998250 | DINUBA-OROSI 012/009 RPLC POLE | 31412754 | DINUBA-OROSI | 012/009 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.256412 | 36.5297 | ETL.8610 | 40871129 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno
115002646 | T2 SPAULDING-SUMMIT 011/387 RPL POLE | 31445623 | SPAULDING-SUMMIT | 011/387 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-120.453502 | 39.3179 | ETL.8060 | 40876696 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
115004849 | MONTE RIO-FULTON :00/16 REPLC POLE | 31411002 | MONTE RIO-FULTON | :000/016 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-122.842292 | 38.4337 | ETL.7630 | 40811767 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  | 2019-05-03
115005040 | T2NT IONE TAP - 60 kV_002/013 HI SGN |  | IONE TAP | 002/013 | ICW | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | Central | Non-WSIP | [6 empty] | '-120.93719 | 38.3764 | ETL.8253 | 40643631 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 9
115007714 | NICOLAUS-WILKINS SLOUGH 32/577 RPL POLE | 31410569 | NICOLAUS-WILKINS SLOUGH | 032/577 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-121.821794 | 38.8786 | ETL.7710 | 40875126 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento
115007760 | NICOLAUS-WILKINS SLOUGH 33/608 RP POLE | 31410569 | NICOLAUS-WILKINS SLOUGH | 033/608 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-121.822054 | 38.9 | ETL.7710 | 40813718 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento
115013178 | DINUBA-OROSI 018/010 RPLC POLE | 31412755 | DINUBA-OROSI | 018/010 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.357446 | 36.5237 | ETL.8610 | 40607894 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno
115013293 | DINUBA-OROSI 018/016 RPLC POLE | 31412755 | DINUBA-OROSI | 018/016 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.363544 | 36.5237 | ETL.8610 | 40821028 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno
115015387 | DINUBA-OROSI 019/002 RPLC POLE | 31412755 | DINUBA-OROSI | 019/002 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.366246 | 36.5237 | ETL.8610 | 40675083 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno
115015439 | DINUBA-OROSI 019/011 RPLC POLE | 31412755 | DINUBA-OROSI | 019/011 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | [6 empty] | '-119.37322 | 36.5237 | ETL.8610 | 40591615 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  |  | RR
115015461 | DINUBA-OROSI _019/006 RPLC POLE | 31412755 | DINUBA-OROSI | 019/006 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.369238 | 36.5238 | ETL.8610 | 40821030 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno
115015540 | DINUBA-OROSI 019/014 RPLC POLE | 31412755 | DINUBA-OROSI | 019/014 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.375626 | 36.5238 | ETL.8610 | 40771277 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno
115015605 | DINUBA-OROSI 019/018 RPLC POLE | 31412755 | DINUBA-OROSI | 019/018 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.376749 | 36.522 | ETL.8610 | 40877893 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno
115015633 | T2 CRIBOU-PLERMO:013/102 REMV/REPLC BENT | 44051480 | CARIBOU-PALERMO | :013/102 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  | Check FDA | TR2 | LATE | North Valley | Non-WSIP |  |  |  |  | Field Operations |  | '-121.276601 | 39.9638 | ETL.3190 | 40738338 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
115015692 | T2 CARIBOU-PALERMO :12/098 STRS NG REPA | 44051480 | CARIBOU-PALERMO | :012/098 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | Non-WSIP |  |  |  |  | Field Operations |  | '-121.27494 | 39.9661 | ETL.3190 | 40910337 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115015921 | DINUBA-OROSI 020/005 RPLC POLE | 31412755 | DINUBA-OROSI | 020/005 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.383193 | 36.5203 | ETL.8610 | 40770441 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno
115017828 | T2 CARIBOU-PARADISE 12/110 COND NG REPA | 43496873 | CARIBOU-PALERMO | 012/110 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | Non-WSIP |  |  |  |  | Field Operations |  | '-121.511297 | 39.6387 | ETL.3190 | 40607817 | Conductor-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
115018418 | WINDSOR-FITCH MTN 09/21 REPL POLE | 31413326 | FULTON #1 | 009/021 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Coast | Non-WSIP | [6 empty] | '-122.854528 | 38.6084 | ETL.6900 | 41119954 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  | 2019-04-23
115018482 | Lakeville-Ignacio #1 00/02 REPL INSUL | 31414403 | LAKEVILLE-IGNACIO #1 | 000/002 | 93K | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-122.57888 | 38.2513 | ETL.4940 | 40723454 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 532 | Lakeville |  |  | 2019-07-19
115019208 | CORTINA-VACA-027/177 RPR GROUND STRAP | 43527394 | CORTINA-VACA | 027/177 | ICS | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-122.001729 | 38.7621 | ETL.4540 | 40654599 | Shield Wire / OPGW-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes
115032771 | MORRO BAY-SOLAR SW STA #1 9/38 PAINT | 43769237 | MORRO BAY-SOLAR SW STA #1 | 009/038 | ICS | F | Pre-2020_(9a) Other ignition related | Budget Owner (Paint) |  |  | TR3 | LATE | South | Non-WSIP | [6 empty] | '-120.69268 | 35.3796 | ETL.5300 | 40863432 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Pismo Beach |  | Y - 10
115033144 | CARIBOU-PLUMAS JCT 018/001 SWIW NG REPA | 43538949 | CARIBOU-PLUMAS JCT | 018/001 | ICW | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Valley | Non-WSIP | [6 empty] | '-120.901554 | 39.9347 | ETL.6290 | 40591674 | Switch-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
115034121 | STONE CORRAL TAP 006/006 RPLC POLE | 31414887 | STONE CORRAL TAP | 006/006 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.211067 | 36.4718 | ETL.8611 | 40821808 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno
115034200 | STONE CORRAL TAP 006/009 RPLC POLE | 31414887 | STONE CORRAL TAP | 006/009 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.207673 | 36.4718 | ETL.8611 | 40871143 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno
115035624 | ESSEX JCT-ORICK - 60 kV_007/001 NEW GUY | 43683300 | ESSEX JCT-ORICK | 007/001 | ICW | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Coast | Non-WSIP | [6 empty] | '-124.047884 | 41.0032 | ETL.6810 | 40585285 | Guy Wire-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Eureka |  |  | 2019-09-10
115035811 | T2 CRIBOU-PLERMO:013/109 RPR STUB LWR SW | 44051480 | CARIBOU-PALERMO | :013/109 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  | Check FDA | TR2 | LATE | North Valley | Non-WSIP |  |  |  |  | Field Operations |  | '-121.288193 | 39.9584 | ETL.3190 | 40738826 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
115036370 | T2 CARIBOU-PALERMO-:013/110 B LEG BENT | 43740857 | CARIBOU-PALERMO | :013/110 | ICQ | E | Pre-2020_(2) High fire spread TD |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | Non-WSIP |  |  |  |  | Field Operations |  | '-121.290832 | 39.9582 | ETL.3190 | 40642211 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
115049768 | ESSEX JCT-ORICK 1/006 RPL INS | 31418510 | ESSEX JCT-ORICK | 001/006 | 93I | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Coast | Non-WSIP | [6 empty] | '-124.033909 | 40.9268 | ETL.6810 | 40809342 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 508 | Eureka
115052312 | VACA-BAHIA 33/182 REPL BTM BRACES | 43761053 | VACA-BAHIA | 033/182 | ICJ | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-122.137523 | 38.0822 | ETL.5810 | 40592024 | Bay Water-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 510 | Lakeville
115052467 | ESSEX JCT-ORICK-4/9 replace pole WP DMG | 31452193 | ESSEX JCT-ORICK | 004/009 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Coast | Non-WSIP | [6 empty] | '-124.038868 | 40.9712 | ETL.6810 | 40861283 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2019-09-10
115052572 | ESSEX JCT-ORICK-4/11 replace pole WP DMG | 31452193 | ESSEX JCT-ORICK | 004/011 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Coast | Non-WSIP | [6 empty] | '-124.038202 | 40.9727 | ETL.6810 | 40601263 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2019-09-10
115057175 | CENTERVILLE-TBL MTN OROV 018/357 CNDW NG | 43621288 | CENTERVILLE-TABLE MTN-OROVILLE | 018/357 | ICW | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-121.585873 | 39.5408 | ETL.6330 | 40721132 | Conductor-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
115059513 | ESSEX JCT-ORICK-5/0 replace pole WP DMG | 31452193 | ESSEX JCT-ORICK | 005/000 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Coast | Non-WSIP | [6 empty] | '-124.037336 | 40.9758 | ETL.6810 | 40616175 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2019-09-10
115059578 | ESSEX JCT-ORICK_5/2_INSTALL ANCHOR | 31418514 | ESSEX JCT-ORICK | 005/002 | 93E | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Coast | Non-WSIP | [6 empty] | '-124.037124 | 40.9777 | ETL.6810 | 40658062 | Anchor-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 637 | Eureka |  |  | 2019-09-10
115059900 | ESSEX JCT-ORICK-6/4 replace pole WP DMG | 31452193 | ESSEX JCT-ORICK | 006/004 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Coast | Non-WSIP | [6 empty] | '-124.041536 | 40.9942 | ETL.6810 | 40751020 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2019-03-14
115063155 | ESSEX JCT-ARCATA-FAIRHAVEN-:3/6 WP RPR | 43509319 | ESSEX JCT-ARCATA-FAIRHAVEN | :003/006 | ICW | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Coast | Non-WSIP | FSRP | [7 empty] | ETL.6800 | 44300540 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Eureka |  |  | 2019-06-06
115063178 | EI ESSEX JCT-ORICK 6/1 RPL PL | 31440270 | ESSEX JCT-ORICK | 006/001 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Coast | Non-WSIP | [6 empty] | '-124.040465 | 40.9909 | ETL.6810 | 40601266 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2019-03-13
115063224 | ESSEX JCT-ORICK-5/1 replace pole WP DMG | 31452193 | ESSEX JCT-ORICK | 005/001 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Coast | Non-WSIP | [6 empty] | '-124.037246 | 40.9768 | ETL.6810 | 40601264 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2019-09-10
115066698 | DIABLO-MIDWAY#3 500KV 64/262 REPL INSULS | 31414035 | DIABLO-MIDWAY #3 | 064/262 | 93K | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.770437 | 35.3225 | ETL.5980 | 40682337 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Midway |  | Y - 11
115067216 | DIABLO-MIDWAY#3 500KV 64/260 REPL INSULS | 31414035 | DIABLO-MIDWAY #3 | 064/260 | 93K | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.77672 | 35.3193 | ETL.5980 | 40586619 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Midway |  | Y - 11
115069615 | CHEVRON (LOST HILLS) TAP 2/37 REPL POLE | 31414883 | CHEVRON (LOST HILLS) TAP | 002/037 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.830054 | 35.7115 | ETL.8472 | 40702607 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Midway |  | Y - 6 | BLM
115070064 | CHEVRON (LOST HILLS)TAP 11/176 REPL POLE | 31414883 | CHEVRON (LOST HILLS) TAP | 011/176 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.742969 | 35.621 | ETL.8472 | 40602745 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Midway
115070068 | CHEVRON (LOST HILLS)TAP 11/178 REPL POLE | 31414883 | CHEVRON (LOST HILLS) TAP | 011/178 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.742938 | 35.6193 | ETL.8472 | 40669241 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Midway
115070110 | CHEVRON (LOST HILLS)TAP 11/174 REPL POLE | 31414883 | CHEVRON (LOST HILLS) TAP | 011/174 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.742999 | 35.6227 | ETL.8472 | 40826701 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Midway
115070882 | T2 CNTRVLE-TBL MTN-ORO 7/154 RPL STRW NG | 31416811 | CENTERVILLE-TABLE MTN-OROVILLE | 007/154 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-121.636215 | 39.6796 | ETL.6330 | 40824065 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
115077396 | MENDO-REDBUD 48/235 REPL FLSH INSUL | 31505573 | MENDOCINO-REDBUD | 048/235 | 93K | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-122.979702 | 39.2025 | ETL.2410 | 40778624 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Capital | 532 | Lakeville |  |  | 2019-07-19
115077617 | T2 PLACER-DEL MAR 0/017 RPL POLE | 31416815 | PLACER-DEL MAR | 000/017 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-121.095172 | 38.8924 | ETL.7800 | 40606312 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
115077693 | T2 DIABLO-MIDWAY #2 36/148 REPL INSULS | 31415341 | DIABLO-MIDWAY #2 | 036/148 | 93K | E | Pre-2020_(2) High fire spread TD |  |  |  | TR2 | LATE | South | Non-WSIP |  |  |  |  | Estimating | Diablo imposed clearance constraints; tag requires additional time to prepare a job package because it exceeds PG&E maximum standard 50kip rated insulators; | '-120.219166 | 35.1747 | ETL.5970 | 40887903 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 18
115080560 | T2 PLACER-DEL MAR-000/015 REPLACE POLE | 31416815 | PLACER-DEL MAR | 000/015 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-121.093649 | 38.8936 | ETL.7800 | 40867710 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
115080596 | T2 PLACER-DEL MAR-0/14 REPLAE LEG | 31416815 | PLACER-DEL MAR | 000/014 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-121.09321 | 38.8939 | ETL.7800 | 40822785 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
115080976 | DIABLO-MIDWAY#3 500KV 63/257 REPL INSULS | 31414035 | DIABLO-MIDWAY #3 | 063/257 | 93K | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.786776 | 35.3141 | ETL.5980 | 40807914 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Midway |  | Y - 11
115084437 | KONOCTI-EAGLE ROCK 07/15 RPL STRW | 31418884 | KONOCTI-EAGLE ROCK | 007/015 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-122.756728 | 38.9132 | ETL.6861 | 40750940 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  | 2019-04-03
115085168 | IGNACIO-ALTO 11/68 REPL FLSH INSUL | 31445562 | IGNACIO-ALTO | 011/068 | 93K | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-122.525373 | 37.9683 | ETL.7150 | 40887385 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Capital | 532 | Lakeville
115089461 | ESSEX JCT-ORICK 27/5 replace pole WP DMG | 31452193 | ESSEX JCT-ORICK | 027/005 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Coast | Non-WSIP | [6 empty] | '-124.086383 | 41.267 | ETL.6810 | 40769581 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka
115093258 | HUMBOLDT BAY-HUMBOLDT#1 001/7 BENT STEEL | 43720602 | HUMBOLDT BAY-HUMBOLDT #1 | 001/007 | ICS | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Coast | Non-WSIP | [6 empty] | '-124.188031 | 40.7408 | ETL.1800 | 40818721 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Eureka |  |  | 2019-07-09
115093363 | HUMBOLDT BAY-HUMBOLDT#1 001/00 SWAYS | 43720602 | HUMBOLDT BAY-HUMBOLDT #1 | 001/008 | ICS | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Coast | Non-WSIP | [6 empty] | '-124.184146 | 40.7423 | ETL.1800 | 40870925 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Eureka |  |  | 2019-07-11
115097562 | T2 CENTERVILLE-TBL MTN-OROV-8/166 RPL PL | 31416811 | CENTERVILLE-TABLE MTN-OROVILLE | 008/166 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-121.63629 | 39.6701 | ETL.6330 | 40585932 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
115097623 | ESSEX JCT-ORICK 29/001 RPL POLE | 31460464 | ESSEX JCT-ORICK | 029/001 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Coast | Non-WSIP | [6 empty] | '-124.070493 | 41.2891 | ETL.6810 | 40601290 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2019-09-10
115097640 | ESSEX JCT-ORICK 29/002 RPL INS | 31418510 | ESSEX JCT-ORICK | 029/002 | 93I | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Coast | Non-WSIP | [6 empty] | '-124.069234 | 41.2897 | ETL.6810 | 40700444 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 508 | Eureka |  |  | 2019-09-10
115097669 | ESSEX JCT-ORICK 23/001 RPL POLE | 31452193 | ESSEX JCT-ORICK | 023/001 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Coast | Non-WSIP | [6 empty] | '-124.103795 | 41.2034 | ETL.6810 | 40585311 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2019-09-10
115100588 | RAVENSWD-BAIR #1 006/041 HELI WASH |  | RAVENSWOOD-BAIR #1 | 006/041 | ICI | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | Central | Non-WSIP | [6 empty] | '-122.22554 | 37.4983 | ETL.3380 | 40586711 | Insulator | Contaminated | Helicopter Wash |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 626 | Bay
115100725 | VACA-TESLA 30/126 RPL FOUNDATION | 43852492 | VACA-TESLA | 030/126 | ICQ | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-121.714349 | 38.0648 | ETL.6140 | 40814936 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento
115100728 | VACA-TESLA-500kV_029/124-PILES EXPOSED | 43852492 | VACA-TESLA | 029/124 | ICQ | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-121.7222 | 38.0682 | ETL.6140 | 40756868 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento
115101318 | PITTSBURG-SAN MATEO 037/155 rust footngs |  | PITTSBURG-SAN MATEO | 037/155 | ICQ | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | Central | Non-WSIP | [6 empty] | '-122.162469 | 37.6143 | ETL.5463 | 44188722 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 10
115101343 | PITSBURG-SAN MATEO 037/156 crack foundat |  | PITTSBURG-SAN MATEO | 037/156 | ICQ | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | Central | Non-WSIP | [6 empty] | '-122.168649 | 37.6125 | ETL.5463 | 44188721 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 10
115101389 | PITSBURG-SAN MATEO 041/165 crack foundat |  | PITTSBURG-SAN MATEO | 041/165 | ICQ | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | Central | Non-WSIP | [6 empty] | '-122.224244 | 37.596 | ETL.5463 | 44188712 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 10
115101442 | PITSBURG-SAN MATEO 040/164 crack foundat |  | PITTSBURG-SAN MATEO | 040/164 | ICQ | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | Central | Non-WSIP | [6 empty] | '-122.218067 | 37.5978 | ETL.5463 | 44188713 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 10
115101449 | PITSBURG-SAN MATEO 039/159 crack foundat |  | PITTSBURG-SAN MATEO | 039/159 | ICQ | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | Central | Non-WSIP | [6 empty] | '-122.187181 | 37.607 | ETL.5463 | 44188718 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 10
115101450 | PITSBURG-SAN MATEO 040/162 crack foundat |  | PITTSBURG-SAN MATEO | 040/162 | ICQ | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | Central | Non-WSIP | [6 empty] | '-122.20571 | 37.6015 | ETL.5463 | 44188715 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 10
115101452 | PITSBURG-SAN MATEO 039/161 crack foundat |  | PITTSBURG-SAN MATEO | 039/161 | ICQ | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | Central | Non-WSIP | [6 empty] | '-122.199534 | 37.6033 | ETL.5463 | 44188716 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 10
115101460 | PITTSBURG-SAN MATEO 039/160 rust footngs |  | PITTSBURG-SAN MATEO | 039/160 | ICQ | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | Central | Non-WSIP | [6 empty] | '-122.193358 | 37.6051 | ETL.5463 | 44188717 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 10
115102458 | IGNACIO-STAFFORD A00/11 REPL NG POLE | 31469867 | ETL.1042.POLE.WOOD | A000/011 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Coast | Non-WSIP | [6 empty] | '-122.545948 | 38.0833 | ETL.1042 | 40617241 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  | 2019-09-13
115102799 | IGNACIO-STAFFORD A00/07 REPL MUD SIL | 43714573 | ETL.1042.POLE.WOOD | A000/007 | ICW | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Coast | Non-WSIP | [6 empty] | '-122.54409 | 38.0808 | ETL.1042 | 40811643 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-09-13
115131007 | TABLE MTN-PEACHTON 007/140 STRW NG REPL | 31433711 | TABLE MTN-PEACHTON | 007/140 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-121.688767 | 39.4839 | ETL.8425 | 40590274 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Table Mountain
115190209 | BIOLA-GLASS-MADERA ?002/012 RPL POLE | 31415244 | GLASS-BIOLA-MADERA | ?002/012 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.115018 | 36.831 | ETL.9350 | 40651286 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno
115190322 | MENDOTA-SN JOAQUIN-HLM 010/012 RPL POLE | 31415256 | MENDOTA-SAN JOAQUIN-HELM | 010/012 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.324008 | 36.6175 | ETL.8980 | 40685992 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno
115190542 | MERCY SPRNGS S S CNL 016/010 REFRAME | 31415257 | LOS BANOS-CANAL-ORO LOMA | 016/010 | 93I | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.819348 | 36.9939 | ETL.8930 | 40637566 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Fresno
115223165 | MRCY SPRGS SW STA-CANAL-ORO LOMA-19/18 | 31415259 | LOS BANOS-CANAL-ORO LOMA | 019/018 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.817857 | 37.0439 | ETL.8930 | 40859173 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 5
115276519 | CARTHRS-LEMRE NAS-CMDN :055/3 RPLC POLE | 31416566 | CARUTHERS-LEMOORE NAS-CAMDEN | :055/003 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.905328 | 36.3247 | ETL.8550 | 40663059 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 5
115276640 | CARTHRS-LMRE NAS-CMDN :053/13 RPLC POLE | 31416566 | CARUTHERS-LEMOORE NAS-CAMDEN | :053/013 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.905268 | 36.3453 | ETL.8550 | 40656319 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 5
115276739 | GUERNSEY-HENRIETTA 013/013 RPLC POLE | 31418450 | GUERNSEY-HENRIETTA | 013/013 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.66135 | 36.2259 | ETL.8720 | 40661432 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 4
115276830 | GUERNSEY-HENRIETTA 013/014 RPLC POLE | 31418450 | GUERNSEY-HENRIETTA | 013/014 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.662393 | 36.2259 | ETL.8720 | 40747313 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 4
115278094 | BRIGHTON-GRAND ISL #1 2/023 RPL CONN | 43742052 | BRIGHTON-GRAND ISLAND #1 | 002/023 | ICM | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-121.408907 | 38.5088 | ETL.1150 | 40690737 | Connector | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 534 | Sacramento |  |  | Yes
115279444 | GUERNSEY-HENRIETTA 016/001 RPLC POLE | 31415833 | GUERNSEY-HENRIETTA | 016/001 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.70233 | 36.2256 | ETL.8720 | 40596024 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 4
115280790 | GUERNSEY-HENRIETTA 016/002 RPLC POLE | 31415833 | GUERNSEY-HENRIETTA | 016/002 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.703541 | 36.2256 | ETL.8720 | 44190842 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 4
115318314 | GUERNSEY-HENRIETTA 017/015A RPLC POLE | 31415833 | GUERNSEY-HENRIETTA | 017/015A | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.737427 | 36.2255 | ETL.8720 | 40575820 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 4
115318323 | GUERNSEY-HENRIETTA 017/015 RPLC POLE | 31415833 | GUERNSEY-HENRIETTA | 017/015 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.736477 | 36.2255 | ETL.8720 | 40763594 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 4
115319110 | GLENN #4 002/045 STRW ROTN REPL | 31418859 | GLENN #4 | 002/045 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-122.140945 | 39.8056 | ETL.8424 | 41104769 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
115322692 | MORRO BAY-TEMPLETON 16/67 REPL INSUL | 31418426 | MORRO BAY-TEMPLETON | 016/067 | 93K | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.681305 | 35.5551 | ETL.5933 | 40835880 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 10
115322762 | GUERNSEY-HENRIETTA 018/007 RPLC POLE | 31415833 | GUERNSEY-HENRIETTA | 018/007 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.745552 | 36.2255 | ETL.8720 | 40821692 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 4
115322825 | GUERNSEY-HENRIETTA 019/004 RPLC POLE | 31415833 | GUERNSEY-HENRIETTA | 019/004 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.758979 | 36.2256 | ETL.8720 | 40747324 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 4
115322955 | GUERNSEY-HENRIETTA 019/009A rplc pole | 31415833 | GUERNSEY-HENRIETTA | 019/009A | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.765648 | 36.2257 | ETL.8720 | 40576957 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 4
115323313 | FAIRHAVEN #1 000/002 REPLACE POLE | 31418857 | FAIRHAVEN #1 NF | 000/002 | 70Y | B | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Coast | Non-WSIP | [6 empty] | '-124.196829 | 40.8008 | ETL.6850 | 40685935 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2019-10-22
115323781 | T2 CARIBOU-PALERMO :014/116 BENT LEG | 44051499 | CARIBOU-PALERMO | :014/116 | ICQ | E | Pre-2020_(2) High fire spread TD |  |  |  | TR2 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.301792 | 39.9518 | ETL.3190 | 40811629 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
115323881 | ESSEX JCT-ARCATA-FAIRHVN :3/7C RPLC POLE | 31418855 | ESSEX JCT-ARCATA-FAIRHAVEN | :003/007 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Coast | Non-WSIP | [8 empty] | ETL.6800 | 44300538 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2019-06-06
115323888 | FAIRHAVEN #1 0/1B RPLC POL | 31418858 | FAIRHAVEN #1 NF | 000/001B | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Coast | Non-WSIP | [6 empty] | '-124.195899 | 40.8007 | ETL.6850 | 40599067 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Eureka |  |  | 2019-10-22
115324839 | RAVENSWD-AMES #1 004/031 RPL INSULATOR | 31435258 | RAVENSWOOD-AMES #1 | 004/031 | 93K | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | Central | Non-WSIP | [6 empty] | '-122.077317 | 37.4481 | ETL.3360 | 40838064 | Insulator-Steel | No Good/Out of Stdrd | Replace | CONS srdy | CONS | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay
115324904 | RAVENSWD-AMES #1 004/032 RPL INSULATOR | 31435258 | RAVENSWOOD-AMES #1 | 004/032 | 93K | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | Central | Non-WSIP | [6 empty] | '-122.074483 | 37.4472 | ETL.3360 | 40813462 | Insulator-Steel | No Good/Out of Stdrd | Replace | CONS srdy | CONS | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay
115335990 | CARIBOU-PLUMAS JCT 017/003 CONN NG REPL | 43686351 | CARIBOU-PLUMAS JCT | 017/003 | ICM | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Valley | 9Lines Pre-WSIP | [6 empty] | '-120.914667 | 39.9403 | ETL.6290 | 40656478 | Connector | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 534 | Table Mountain |  |  | Yes
115342023 | T2 CARIBOU-PALERMO _015/123 RUSTED BOLTS | 44051499 | CARIBOU-PALERMO | 015/123 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.501865 | 39.6662 | ETL.3190 | 40913205 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 543 | Table Mountain
115343528 | T2 CARIBOU-PALERMO 15/123 RPL STRS |  | CARIBOU-PALERMO | 015/123 | 70S | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.501865 | 39.6662 | ETL.3190 | 40913205 | Structure-Tower | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLX | Pole Program | Capital | 426 | Table Mountain
115344265 | T2 CARIBOU-PALERMO 10/088 LOOSE BOLT | 44051499 | CARIBOU-PALERMO | 010/088 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.522492 | 39.5992 | ETL.3190 | 40867947 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
115344796 | T2 CARIBOU-PALERMO :000/008 BENT X | 44051499 | CARIBOU-PALERMO | :000/008 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.16204 | 40.0769 | ETL.3190 | 40910255 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115344798 | T2 CARIBOU-PALERMO - 005/039 RPL HRDWARE | 43735847 | CARIBOU-PALERMO | :000/001 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | 9Lines Pre-WSIP | FSRP |  |  |  | Field Operations |  | '-121.147242 | 40.0864 | ETL.3190 | 44190134 | Hardware-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain
115344799 | T2 CARIBOU-PALERMO -005/039 RPL HRDWARE | 43735847 | CARIBOU-PALERMO | :000/002 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | 9Lines Pre-WSIP | FSRP |  |  |  | Field Operations |  | '-121.149439 | 40.0846 | ETL.3190 | 44190135 | Hardware-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain
115344820 | T2 CARIBOU-PALERMO :000/008 CONCRETE CAP | 44051499 | CARIBOU-PALERMO | :000/008 | ICQ | F | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.16204 | 40.0769 | ETL.3190 | 40910255 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115344829 | T2 CARIBOU-PALERMO :003/022 D LEG BENT | 44051499 | CARIBOU-PALERMO | :003/022 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.185972 | 40.0637 | ETL.3190 | 40910266 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115344833 | T2 CARIBOU-PALERMO :001/010 SWAY A PAHSE | 44051499 | CARIBOU-PALERMO | :001/010 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.164829 | 40.0739 | ETL.3190 | 40910257 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
115344835 | CARIBOU PALERMO_003/022 HRDS NG REPL | 43735847 | CARIBOU-PALERMO | :003/022 | ICS | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Valley | 9Lines Pre-WSIP | FSRP |  |  |  | Field Operations |  | '-121.185972 | 40.0637 | ETL.3190 | 40920005 | Hardware-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
115346203 | GUERNSEY-HENRIETTA ;020/007 RPLC POLE | 31415833 | GUERNSEY-HENRIETTA | ;020/007 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.654922 | 36.239 | ETL.8720 | 41198017 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 4
115346438 | T2 CARIBOU-PALERMO :003/028 RPL BOLTS | 44051499 | CARIBOU-PALERMO | :003/028 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.201281 | 40.0609 | ETL.3190 | 40910272 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
115347116 | T2 CARIBOU-PALERMO :2/020 RPR C LEG | 44051499 | CARIBOU-PALERMO | :002/020 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.18454 | 40.065 | ETL.3190 | 40910264 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
115347117 | T2 CARIBOU-PALERMO :2/019 RPR BENT STEEL | 44051499 | CARIBOU-PALERMO | :002/019 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.182939 | 40.0665 | ETL.3190 | 40910263 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115347118 | T2 CARIBOU-PALERMO :1/012 RPL INS BOLT | 44051499 | CARIBOU-PALERMO | :001/012 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.166469 | 40.0723 | ETL.3190 | 40912339 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115347562 | T2 CARIBOU-PALERMO :4/37 BENT SWAY | 44051499 | CARIBOU-PALERMO | :004/037 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.216388 | 40.0451 | ETL.3190 | 40907002 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
115347568 | T2 CARIBOU-PALERMO :5/039 SWAY-DIG OUT | 44051499 | CARIBOU-PALERMO | :005/039 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.217637 | 40.0409 | ETL.3190 | 40910282 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
115348822 | T2 CARIBOU-PALERMO-115 kV_003/027 Steel |  | CARIBOU-PALERMO | :003/027 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.199707 | 40.0633 | ETL.3190 | 40910271 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115348823 | T2 CARIBOU-PALERMO :5/042 D LEG BENT | 44051499 | CARIBOU-PALERMO | :005/042 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.218237 | 40.0358 | ETL.3190 | 40910285 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
115350150 | CAMDEN-KINGSBURG 000/003 RPLC POLE | 31416229 | CAMDEN-KINGSBURG | 000/003 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.595015 | 36.4859 | ETL.8653 | 40652982 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 7
115350260 | CAMDEN-KINGSBURG 000/009 RPLC POLE | 31416229 | CAMDEN-KINGSBURG | 000/009 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.598153 | 36.4815 | ETL.8653 | 40864389 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno
115350320 | CAMDEN-KINGSBURG 000/012 RPLC POLE | 31416229 | CAMDEN-KINGSBURG | 000/012 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.601861 | 36.4815 | ETL.8653 | 40667299 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno
115350421 | CAMDEN-KINGSBURG 001/000 RPLC POLE | 31418233 | CAMDEN-KINGSBURG | 001/000 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.606246 | 36.4815 | ETL.8653 | 40606200 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno
115350428 | CAMDEN-KINGSBURG 001/001 RPLC POLE | 31418233 | CAMDEN-KINGSBURG | 001/001 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.607655 | 36.4816 | ETL.8653 | 40595951 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno
115350434 | CAMDEN-KINGSBURG 001/002 RPLC POLE | 31418233 | CAMDEN-KINGSBURG | 001/002 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.609065 | 36.4816 | ETL.8653 | 40667303 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno
115350500 | CAMDEN-KINGSBURG 001/005 RPL POLE | 31418233 | CAMDEN-KINGSBURG | 001/005 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.613454 | 36.4816 | ETL.8653 | 40763508 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno
115350513 | CAMDEN-KINGSBURG 001/006 RPLC POLE | 31418233 | CAMDEN-KINGSBURG | 001/006 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.61502 | 36.4816 | ETL.8653 | 40813105 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno
115350515 | CAMDEN-KINGSBURG 001/007 RPLC POLE | 31418233 | CAMDEN-KINGSBURG | 001/007 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.616495 | 36.4816 | ETL.8653 | 40820074 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno
115350532 | CAMDEN-KINGSBURG 001/008 RPLC POLE | 31418233 | CAMDEN-KINGSBURG | 001/008 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.617887 | 36.4816 | ETL.8653 | 40864858 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno
115350989 | CAMDEN-KINGSBURG 002/000 RPLC POLE | 31416230 | CAMDEN-KINGSBURG | 002/000 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.624817 | 36.4818 | ETL.8653 | 40594572 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno
115351023 | CAMDEN-KINGSBURG 002/002 RPLC POLE | 31416230 | CAMDEN-KINGSBURG | 002/002 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.626999 | 36.4819 | ETL.8653 | 40686226 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno
115351246 | CAMDEN-KINGSBURG 002/004 RPLC POLE | 31416230 | CAMDEN-KINGSBURG | 002/004 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.629794 | 36.4818 | ETL.8653 | 40755021 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno
115351258 | T2 CARIBOU-PALERMO :20/160 BENT SWAY | 43740857 | CARIBOU-PALERMO | :020/160 | ICQ | E | Pre-2020_(2) High fire spread TD |  |  |  | TR2 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.353207 | 39.9056 | ETL.3190 | 40642284 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115351279 | CARIBOU PALERMO 020/160 HRDS NG REPL | 43735847 | CARIBOU-PALERMO | :020/160 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  |  | LATE | North Valley | 9Lines Pre-WSIP | FSRP |  |  |  | Field Operations |  | '-121.353207 | 39.9056 | ETL.3190 | 40642431 | Hardware-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain
115351335 | CAMDEN-KINGSBURG 002/007 RPLC POLE | 31416230 | CAMDEN-KINGSBURG | 002/007 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | [6 empty] | '-119.633603 | 36.4819 | ETL.8653 | 40812388 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 8
115351355 | CAMDEN-KINGSBURG 002/008 RPLC POLE | 31416230 | CAMDEN-KINGSBURG | 002/008 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | [6 empty] | '-119.634726 | 36.4819 | ETL.8653 | 40872283 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno
115352894 | EAST DUBLIN (BART) TAP A003/086 RPL SWTC | 31418506 | EAST DUBLIN (BART) TAP | A003/086 | 93H | B | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | Central | Non-WSIP | FSRP | [5 empty] | '-121.901118 | 37.7041 | ETL.7962 | 41112603 | Switch-Wood | No Good/Out of Stdrd | Replace | ADER | ADER | ADE Review estimate | Not Complete | PEND | LC | TLN | Maintenance | Capital | 427 | Bay |  | Y - 1
115353654 | CARIBOU-PALERMO-002/018 REPL 4 CAPS | 44069801 | CARIBOU-PALERMO | 002/018 | ICQ | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.539864 | 39.4771 | ETL.3190 | 40867943 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
115363064 | CARIBOU-PALERMO-002/025 BENT 90 OF CAGE | 44051499 | CARIBOU-PALERMO | 002/025 | ICQ | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.539987 | 39.4918 | ETL.3190 | 40758454 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
115363101 | CARIBOU-PALERMO-001/012 RPR A/B CAPS | 44051499 | CARIBOU-PALERMO | 001/012 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.541011 | 39.4665 | ETL.3190 | 40674849 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
115363206 | CARIBOU-PALERMO 003/034 RPR FOND | 44051499 | CARIBOU-PALERMO | 003/034 | ICQ | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.539981 | 39.5072 | ETL.3190 | 40762751 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
115363271 | CARIBOU-PALERMO 003/029 RPR FOND | 44051499 | CARIBOU-PALERMO | 003/029 | ICQ | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.539991 | 39.4999 | ETL.3190 | 40864873 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
115363274 | EI CARIBOU-PALERMO 3/035 RPR FOND | 44051499 | CARIBOU-PALERMO | 003/035 | ICQ | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.539983 | 39.5093 | ETL.3190 | 40765056 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
115363354 | T2NT EI CRIBU-PLERM 4/42 INS MRKS | 44051499 | CARIBOU-PALERMO | 004/042 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.539985 | 39.5213 | ETL.3190 | 40668737 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
115363635 | T2 CARIBOU-PALERMO 5/051 RPR FOND | 44051499 | CARIBOU-PALERMO | 005/051 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.540481 | 39.5377 | ETL.3190 | 40591544 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115363694 | T2NT CARIBOU-PALERMO 005/049 INST MRKS | 44305729 | CARIBOU-PALERMO | 005/049 | ICS | F | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.540447 | 39.5329 | ETL.3190 | 40870660 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain
115363696 | T2 CARIBOU-PALERMO - 115 kV_006/053 | 43586842 | CARIBOU-PALERMO | 006/053 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.540497 | 39.5401 | ETL.3190 | 40660305 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115375395 | T2 CARIBOU-PALERMO 12/108 RPL STRS |  | CARIBOU-PALERMO | 012/108 | 70S | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.511776 | 39.637 | ETL.3190 | 40867949 | Structure-Tower | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLX | Pole Program | Capital | 426 | Table Mountain |  |  | Yes
115375775 | T2 CARIBOU-PALERMO 11/096 RPL STRS |  | CARIBOU-PALERMO | 011/096 | 70S | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.517387 | 39.6172 | ETL.3190 | 40816574 | Structure-Tower | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLX | Pole Program | Capital | 426 | Table Mountain |  |  | Yes
115375818 | T3NT CARIBOU-PALERMO 016/129 BENT SWAY | 44051499 | CARIBOU-PALERMO | 016/129 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.491351 | 39.6771 | ETL.3190 | 41162783 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115375943 | T3 CARIBOU-PALERMO :036/288 MISSING BOLT | 43725390 | CARIBOU-PALERMO | :036/288 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.482728 | 39.7047 | ETL.3190 | 40867981 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
115375963 | T3 CARIBOU-PALERMO :034/278 BOLT REPR | 43725390 | CARIBOU-PALERMO | :034/278 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.480133 | 39.7207 | ETL.3190 | 40878263 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115375966 | T3 CARIBOU-PLRMO :035/280 RPLC SWAY | 43740857 | CARIBOU-PALERMO | :035/280 | ICQ | E | Pre-2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.480864 | 39.7162 | ETL.3190 | 40618602 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
115375974 | T3NT CARIBOU-PALERMO-:034/274 BENT SWAY | 44051499 | CARIBOU-PALERMO | :034/274 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.478839 | 39.7286 | ETL.3190 | 40758638 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115375977 | T3 CARIBOU-PALERMO :034/279 REPLC BOLTS | 43725390 | CARIBOU-PALERMO | :034/279 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.480326 | 39.7195 | ETL.3190 | 40867378 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115376014 | T3 CARIBOU-PALERMO :034/276 BENT SWAY | 43725390 | CARIBOU-PALERMO | :034/276 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.479471 | 39.7247 | ETL.3190 | 40828377 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115376015 | T3 EI Caribou Plrmo 34/276 RPL CTTR KEY | 43725390 | CARIBOU-PALERMO | :034/276 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.479471 | 39.7247 | ETL.3190 | 40856088 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115376328 | BRIGHTON-GRAND ISL #2 12/100 RPR CONNECT | 43742054 | BRIGHTON-GRAND ISLAND #2 | 012/100 | ICM | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-121.482521 | 38.3823 | ETL.1160 | 40633085 | Conductor-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 534 | Sacramento
115388448 | CAMDEN-KINGSBURG 003/007 RPL POLE | 31416230 | CAMDEN-KINGSBURG | 003/007 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.642925 | 36.4746 | ETL.8653 | 40812390 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno
115388735 | T3 EI CRIBOU-PLRM :033/268 RPR STRT | 43725390 | CARIBOU-PALERMO | :033/268 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.477302 | 39.7381 | ETL.3190 | 40867979 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115388826 | T3 EI CARIBOU-PLRMO :032/260 BENTSWAY | 43725390 | CARIBOU-PALERMO | :032/260 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.474651 | 39.7549 | ETL.3190 | 40599300 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
115388828 | T3 EI CARIBOU-PLRMO :031/251A BENT SWAY | 43725390 | CARIBOU-PALERMO | :031/251A | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.460698 | 39.7661 | ETL.3190 | 41147754 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115388913 | T3 CARIBOU-PALERMO :031/256 BENT MEMB | 44051416 | CARIBOU-PALERMO | :031/256 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.467283 | 39.7595 | ETL.3190 | 40816593 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115388920 | T3 EI CARIBOU-PALERMO :031/255 BENT SWAY | 43725390 | CARIBOU-PALERMO | :031/255 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.464758 | 39.7615 | ETL.3190 | 40770937 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115388925 | GUERNSEY-HENRIETTA ;019/006 RPLC POLE | 31415833 | GUERNSEY-HENRIETTA | ;019/006 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.654918 | 36.2548 | ETL.8720 | 41198051 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 4
115389151 | GOLD HILL-BELLOTA-LOCKEFORD 35/211H CONN | 43755513 | GOLD HILL-BELLOTA-LOCKEFORD | 035/211H | ICM | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Valley | Non-WSIP | [6 empty] | '-121.13459 | 38.6546 | ETL.1690 | 40743138 | Connector | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 534 | Sacramento
115394486 | TRINITY-MPL CRK-45/6 RMV PL BTT DEBR LFT | 43683556 | TRINITY-MAPLE CREEK | 045/006 | ICW | E | Pre-2020_(9a) Other ignition related |  |  |  |  | LATE | North Coast | Non-WSIP | [6 empty] | '-123.718597 | 40.7502 | ETL.8170 | 44565516 | Structure-Wood | Debris/Nest/etc. | Remove | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Eureka |  |  | 2019-03-15
115397067 | CRTHRS-LEMOORE NAS-CMDN :049/15 RPL POLE | 31416566 | CARUTHERS-LEMOORE NAS-CAMDEN | :049/015 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.905037 | 36.3659 | ETL.8550 | 40758446 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 5
115401593 | CRTHRS-LEMOORE NAS-CMDN :044/14 RPL POLE | 31416566 | CARUTHERS-LEMOORE NAS-CAMDEN | :044/014 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.89606 | 36.434 | ETL.8550 | 40763084 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 5
115401681 | CRTHRS-LEMOORE NAS-CMDN :043/07 RPL POLE | 31416566 | CARUTHERS-LEMOORE NAS-CAMDEN | :043/007 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.896137 | 36.4538 | ETL.8550 | 40815563 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 5
115401683 | CARTHRS-LEMOORE NAS-CMDN :043/5 RPL POLE | 31416566 | CARUTHERS-LEMOORE NAS-CAMDEN | :043/005 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.896144 | 36.4559 | ETL.8550 | 40758432 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 5
115401776 | CAMDEN-KINGSBURG 008/002 RPLC POLE | 31416230 | CAMDEN-KINGSBURG | 008/002 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.726279 | 36.4745 | ETL.8653 | 40688159 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 7
115401822 | CAMDEN-KINGSBURG 008/005 RPL POLE | 31416230 | CAMDEN-KINGSBURG | 008/005 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.731631 | 36.4746 | ETL.8653 | 40763516 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 7
115402371 | GOLD HILL-BELLOTA-LOCKEFORD 41/251 CONN | 43755513 | GOLD HILL-BELLOTA-LOCKEFORD | 041/251 | ICM | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Valley | Non-WSIP | [6 empty] | '-121.143449 | 38.5698 | ETL.1690 | 40594112 | Connector | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 534 | Sacramento |  |  | Yes
115402810 | REEDLEY OROSI 009/004 RPR PT WIRING | 43959939 | REEDLEY-OROSI | 009/004 | ICE | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.251182 | 36.5711 | ETL.9060 | 44670526 | Switch-Steel | No Good/Out of Stdrd | Repair | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 623 | Fresno |  | Y - Prog Multi
115402913 | T2 CARIBOU-PALERMO :0/6 RPR STRT | 44054700 | CARIBOU-PALERMO | :000/006 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.157122 | 40.0804 | ETL.3190 | 40828375 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115402916 | T2 CARIBOU-PALERMO :3/30 RPR BENT MEMBER | 44054700 | CARIBOU-PALERMO | :003/030 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.205437 | 40.0561 | ETL.3190 | 40910274 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115402941 | T2 CARIBOU-PALERMO :003/026 BENT MEMB | 44054700 | CARIBOU-PALERMO | :003/026 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.19843 | 40.0636 | ETL.3190 | 40910270 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115402945 | T2 CARIBOU-PALERMO :1/13 RPR STRT | 44054700 | CARIBOU-PALERMO | :001/013 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.167509 | 40.072 | ETL.3190 | 40910258 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115402946 | T2 CARIBOU-PALERMO :1/016 BENT STEEL | 44054700 | CARIBOU-PALERMO | :001/016 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.173733 | 40.0701 | ETL.3190 | 40910260 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
115402980 | T2 CARIBOU-PALERMO :004/031 RPR STRT | 44054700 | CARIBOU-PALERMO | :004/031 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.206015 | 40.0557 | ETL.3190 | 40910275 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115402981 | T2 CARIBOU-PALERMO :5/43 RPR STRT | 44054700 | CARIBOU-PALERMO | :005/043 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.218331 | 40.0326 | ETL.3190 | 40907003 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115402993 | T2 EI CARIBOU-PALERMO-:006/050 RPL HRDT | 44054700 | CARIBOU-PALERMO | :006/050 | ICQ | E | Pre-2020_(2) High fire spread TD |  |  |  | TR2 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.221018 | 40.0214 | ETL.3190 | 40910292 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115402995 | T2 CARIBOU-PALERMO :04/035 RPL INS | 31426476 | CARIBOU-PALERMO | :004/035 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.214156 | 40.0482 | ETL.3190 | 40910279 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain
115403009 | T2 CARIBOU-PALERMO :3/28 RPL BENT MEMBER | 44054700 | CARIBOU-PALERMO | :003/028 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.201281 | 40.0609 | ETL.3190 | 40910272 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115403758 | CAMDEN-KINGSBURG 010/005 RPLC POLE | 31416230 | CAMDEN-KINGSBURG | 010/005 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.762395 | 36.4703 | ETL.8653 | 40764317 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 7
115403850 | CAMDEN-KINGSBURG 000/013 RPLC POLE | 31416229 | CAMDEN-KINGSBURG | 000/013 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.603305 | 36.4815 | ETL.8653 | 40652981 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno
115404327 | RESERVE OIL TAP 018/003 RPLC POLE | 31418449 | RESERVE OIL TAP | 018/003 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.654653 | 36.272 | ETL.8721 | 41217686 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno
115404561 | RESERVE OIL TAP 017/016B RPLC POLE | 31418449 | RESERVE OIL TAP | 017/016B | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.653648 | 36.2765 | ETL.8721 | 40740115 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno
115408522 | DIABLO-GATES #1 500KV 12/52 REPL INSULS | 31403823 | DIABLO-GATES #1 | 012/052 | 93K | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.773846 | 35.3629 | ETL.5960 | 40715277 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach
115409182 | CARTHRS-LEMRE NAS-CAMDN :42/15 RPL POLE | 31415834 | CARUTHERS-LEMOORE NAS-CAMDEN | :042/015 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.896167 | 36.4627 | ETL.8550 | 40763494 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 5
115409193 | CARTHRS-LEMRE NAS-CAMDN :42/12 RPLC POLE | 31415834 | CARUTHERS-LEMOORE NAS-CAMDEN | :042/012 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.896191 | 36.4656 | ETL.8550 | 40674880 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 5
115409268 | CARTHRS-LEMRE NAS-CAMDN :40/19 RPL POLE | 31415834 | CARUTHERS-LEMOORE NAS-CAMDEN | :040/019 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.887418 | 36.483 | ETL.8550 | 40872848 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 5
115409742 | CARTHRS-LEMRE NAS-CAMDN :39/9 RPLC POLE | 31415834 | CARUTHERS-LEMOORE NAS-CAMDEN | :039/009 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.881568 | 36.4988 | ETL.8550 | 40867328 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 5
115409746 | CARTHRS-LEMRE NAS-CAMDN :39/8 RPLC POLE | 31415834 | CARUTHERS-LEMOORE NAS-CAMDEN | :039/008 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.881573 | 36.4999 | ETL.8550 | 40872271 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 5
115409747 | CARTHRS-LEMRE NAS-CAMDN :39/7 RPLC POLE | 31415834 | CARUTHERS-LEMOORE NAS-CAMDEN | :039/007 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.881539 | 36.5008 | ETL.8550 | 40815557 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 5
115409748 | CARTHRS-LEMRE NAS-CAMDN :39/5 RPLC POLE | 31415834 | CARUTHERS-LEMOORE NAS-CAMDEN | :039/005 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.881527 | 36.5026 | ETL.8550 | 40758424 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 5
115410024 | GOLD HILL-BELLOTA-LOCKEFORD 48/293 CNT | 43755513 | GOLD HILL-BELLOTA-LOCKEFORD | 048/293 | ICM | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Valley | Non-WSIP | [6 empty] | '-121.141602 | 38.4779 | ETL.1690 | 40659254 | Connector | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 534 | Sacramento |  |  | Yes
115410750 | STOCKTONA-WEBER#3 AB1/057 RPLC GUY POLE | 31418888 | STOCKTON "A"-WEBER #3+ (NO FLY) | AB001/057 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | Central | Non-WSIP | FSRP | [5 empty] | '-121.267851 | 37.9605 | ETL.8140 | 40813770 | Structure-Wood | Rotten | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 7
115410752 | STOCKTON A WEBER #3 3/85 REPLACE POLE | 31418888 | STOCKTON "A"-WEBER #3+ (NO FLY) | 003/085 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | Central | Non-WSIP | FSRP | [5 empty] | '-121.25457 | 37.9219 | ETL.8140 | 40588139 | Structure-Wood | Rotten | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 7
115410753 | STOCKTON A-WEBER #3 2/70 REPLACE POLE | 31418888 | STOCKTON "A"-WEBER #3+ (NO FLY) | 002/070 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | Central | Non-WSIP | FSRP | [5 empty] | '-121.263621 | 37.923 | ETL.8140 | 40812594 | Structure-Wood | Rotten | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 7
115410754 | STOCKTON A WEBER #3 2/57 REPLACE POLE | 31418888 | STOCKTON "A"-WEBER #3+ (NO FLY) | 002/057 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | Central | Non-WSIP | FSRP | [5 empty] | '-121.268122 | 37.9286 | ETL.8140 | 40681297 | Structure-Wood | Rotten | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 7
115410755 | STOCKTON A-WEBER #3 3/76 REPLACE POLE | 31418888 | STOCKTON "A"-WEBER #3+ (NO FLY) | 003/076 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | Central | Non-WSIP | FSRP | [5 empty] | '-121.262138 | 37.9203 | ETL.8140 | 40665909 | Structure-Wood | Rotten | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 7
115410899 | T3 EI CARIBOU-PALERMO :006/054 BENT BRAC | 43725390 | CARIBOU-PALERMO | :006/054 | ICQ | E | Pre-2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.224373 | 40.0128 | ETL.3190 | 40910296 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115410955 | T3 EI CARIBOU-PALERMO :007/057 BENT SWAY | 43725390 | CARIBOU-PALERMO | :007/057 | ICQ | E | Pre-2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.226794 | 40.0078 | ETL.3190 | 40910299 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
115410957 | T3 EI CARIBOU-PALERMO :011/089 BENT SWAY | 43725390 | CARIBOU-PALERMO | :011/089 | ICQ | E | Pre-2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.279035 | 39.9862 | ETL.3190 | 40910329 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
115410959 | T3 EI CARIBOU-PALERMO :007/060 BENT LEG | 43725390 | CARIBOU-PALERMO | :007/060 | ICQ | E | Pre-2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.231928 | 40.0059 | ETL.3190 | 40910302 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
115410961 | T3 EI CARIBOU-PALERMO :008/064 RPR STRT | 43725390 | CARIBOU-PALERMO | :008/064 | ICQ | E | Pre-2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.239441 | 40.0064 | ETL.3190 | 40910306 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
115410965 | T2 CARIBOU-PALERMO :008/069 RPL INSS | 44304491 | CARIBOU-PALERMO | :008/069 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | 9Lines Pre-WSIP | FSRP |  |  |  | Field Operations |  | '-121.252392 | 40.0071 | ETL.3190 | 40920050 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain
115410966 | T3 EI CARBOU-PALERMO :011/087 BENT BRACE | 44054700 | CARIBOU-PALERMO | :011/087 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.280057 | 39.9886 | ETL.3190 | 40910327 | Structure-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 543 | Table Mountain |  |  | Yes
115410968 | T3 CARIBOU-PALERMO :009/076 RPR LEGS | 44051416 | CARIBOU-PALERMO | :009/076 | ICQ | E | Pre-2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.266062 | 40.0033 | ETL.3190 | 40910318 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115410980 | T2 CARIBOU-PALERMO :009/072 WORN EYES | 43664533 | CARIBOU-PALERMO | :009/072 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.258867 | 40.0049 | ETL.3190 | 40910314 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain
115410983 | T3 CARIBOU-PALERMO-:009/076 RPR COTT KEY | 44304458 | CARIBOU-PALERMO | :009/076 | ICS | E | Pre-2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.266062 | 40.0033 | ETL.3190 | 40910318 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain
115410986 | T3 CARIBOU-PALERMO :010/084 RPR INSS | 44304458 | CARIBOU-PALERMO | :010/084 | ICS | E | Pre-2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.276297 | 39.9925 | ETL.3190 | 40907021 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain
115411013 | T3 CARIBOU-PALERMO :010/085 RPLC ARM | 43725390 | CARIBOU-PALERMO | :010/085 | ICQ | E | Pre-2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.277044 | 39.9919 | ETL.3190 | 40910325 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
115411014 | T3 EI CARIBOU-PALERMO :009/077 BENT SWAY | 43725390 | CARIBOU-PALERMO | :009/077 | ICQ | E | Pre-2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.266703 | 40.0021 | ETL.3190 | 40910319 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
115411016 | T3 CARIBOU-PALERMO-:010/084 RPLC EYE | 44304458 | CARIBOU-PALERMO | :010/084 | ICS | E | Pre-2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.276297 | 39.9925 | ETL.3190 | 40907021 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain
115411018 | T3 CARIBOU-PALERMO :010/078 BENT MEMB | 44051416 | CARIBOU-PALERMO | :010/078 | ICQ | E | Pre-2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.267244 | 40.0011 | ETL.3190 | 40907020 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115411019 | T3 CARIBOU-PALERMO :010/078 RPL INSS |  | CARIBOU-PALERMO | :010/078 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.267244 | 40.0011 | ETL.3190 | 40916721 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain
115411026 | T3 CARIBOU-PALERMO :010/082 RPR STRUT | 44051416 | CARIBOU-PALERMO | :010/082 | ICQ | E | Pre-2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.272037 | 39.994 | ETL.3190 | 40910323 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 543 | Table Mountain |  |  | Yes
115411043 | T3 CARIBOU-PALERMO :010/079 BENT MEMB | 44051416 | CARIBOU-PALERMO | :010/079 | ICQ | E | Pre-2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.268442 | 39.9988 | ETL.3190 | 40910320 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115411519 | STOCKTON A-WEBER#3 3/80 REPLACE POLE | 31418888 | STOCKTON "A"-WEBER #3+ (NO FLY) | 003/080 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | Central | Non-WSIP | FSRP | [5 empty] | '-121.260288 | 37.9205 | ETL.8140 | 40812596 | Structure-Wood | Rotten | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 7
115411574 | STOCKTON A-WEBER#3 A001/44 RPLC POLE | 31418888 | STOCKTON "A"-WEBER #3+ (NO FLY) | A001/044 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | Central | Non-WSIP | FSRP | [5 empty] | '-121.274412 | 37.9574 | ETL.8140 | 40864344 | Structure-Wood | Rotten | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 7
115411590 | STOCKTON A-WEBER#3 AB001/49 RPLC POLE | 31418888 | STOCKTON "A"-WEBER #3+ (NO FLY) | AB001/049 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | Central | Non-WSIP | FSRP | [5 empty] | '-121.270074 | 37.9582 | ETL.8140 | 40643292 | Structure-Wood | Rotten | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 7
115411593 | SUTERHME SW ST-LKFRD-LODI 9/138 RPL PL | 31418856 | ETL.8068.POLE.WOOD | 009/138 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | Central | Non-WSIP | FSRP | [5 empty] | '-121.254066 | 38.1892 | ETL.8068 | 40807971 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 2
115411640 | SUTER HOME SWSTA-LCKFRD-LODI 3/40 RPLC | 31418856 | ETL.8068.POLE.WOOD | 003/040 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | Central | Non-WSIP | [6 empty] | '-121.17849 | 38.1596 | ETL.8068 | 40652303 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Released | CVFPB
115411643 | SUTR HME SW ST-LCKFRD-LDI 2/33 RPLC PL | 31418856 | ETL.8068.POLE.WOOD | 002/033 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | Central | Non-WSIP | FSRP | [5 empty] | '-121.175944 | 38.1519 | ETL.8068 | 40811808 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 3
115411648 | SUTER HOME SWSTA-LCKFRD-LODI 10/151 RPLC | 31418856 | ETL.8068.POLE.WOOD | 010/151 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | Central | Non-WSIP | FSRP | [5 empty] | '-121.26223 | 38.1877 | ETL.8068 | 40666052 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 2
115412411 | IGNACIO-SN RAFAEL#1 07/39 REP ACC RD | 31486234 | IGNACIO-SAN RAFAEL #1 | 007/039 | 71Y | F | Pre-2020_(5b) On structure in bucket 5 |  |  |  |  | LATE | North Coast | Non-WSIP | [6 empty] | '-122.494875 | 37.9845 | ETL.1850 | 40863149 | Road | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLR | Roads | Capital | 374 | Lakeville
115412486 | GLENN # 4 02/053_REPL INSUL | 31418507 | GLENN #4 | 002/053 | 93I | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-122.140943 | 39.8118 | ETL.8424 | 41176180 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 508 | Table Mountain |  |  | Yes
115412728 | SUTER HOME SWTA-LKFRD-LDI 10/153 RPL PL | 31418856 | ETL.8068.POLE.WOOD | 010/153 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | Central | Non-WSIP | FSRP | [5 empty] | '-121.26219 | 38.1858 | ETL.8068 | 40754293 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 2
115412756 | SUTER HOME SWSTA-LCKFRD-LODI 10/159 RPL | 31418856 | ETL.8068.POLE.WOOD | 010/159 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | Central | Non-WSIP | FSRP | [5 empty] | '-121.262044 | 38.1807 | ETL.8068 | 40588068 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 2
115412790 | SUTTER HME SW STA-LCKFRD-LODI 10/163 RPL | 31418856 | ETL.8068.POLE.WOOD | 010/163 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | Central | Non-WSIP | FSRP | [5 empty] | '-121.261969 | 38.1777 | ETL.8068 | 40754295 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 2
115412796 | SUTER HOME SW STA-LCKFRD-LODI 11/183 RPL | 31418856 | ETL.8068.POLE.WOOD | 011/183 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | Central | Non-WSIP | FSRP | [5 empty] | '-121.26152 | 38.1658 | ETL.8068 | 40665729 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 2
115412984 | T2 CARIBOU-PALERMO :006/047 RPR STRT | 44054700 | CARIBOU-PALERMO | :006/047 | ICQ | E | Pre-2020_(2) High fire spread TD |  |  |  | TR2 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.219269 | 40.0274 | ETL.3190 | 40910289 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115413018 | SUTR HME SWSTA-LCKFRD-LDI 11/186 RPL PLE | 31418856 | ETL.8068.POLE.WOOD | 011/186 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | Central | Non-WSIP | FSRP | [5 empty] | '-121.261447 | 38.164 | ETL.8068 | 40762864 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 2
115413117 | SUTER HM SWSTA-LCKFRDLODI 12/195G RPLC | 31430342 | ETL.8068.POLE.WOOD | 012/195 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | Central | Non-WSIP | FSRP | [5 empty] | '-121.26132 | 38.1587 | ETL.8068 | 40588071 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 3
115413119 | SUTERHME SW ST-LKFRD-LDI 12/199 RPLC PL | 31430342 | ETL.8068.POLE.WOOD | 012/199 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | Central | Non-WSIP | FSRP | [5 empty] | '-121.261262 | 38.1563 | ETL.8068 | 40768060 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 2
115413174 | SUTERHOME SWSTA-LCKFRD-LODI 12/203G RPLC | 31430342 | ETL.8068.POLE.WOOD | 012/203 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | Central | Non-WSIP | FSRP | [5 empty] | '-121.261171 | 38.1537 | ETL.8068 | 40863950 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 3
115413238 | SUTERHOME SWSTA-LCKFD-LDI 12/215 RPR PL | 44610158 | ETL.8068.POLE.WOOD | 012/215 | ICW | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | Central | Non-WSIP | FSRP | [5 empty] | '-121.261841 | 38.1472 | ETL.8068 | 40863952 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 3
115413303 | SUTER HM SW ST-LKFRD-LDI 12/217 RPL PL | 31430342 | ETL.8068.POLE.WOOD | 012/217 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | Central | Non-WSIP | FSRP | [5 empty] | '-121.261783 | 38.146 | ETL.8068 | 40603939 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 3
115413421 | SUTRHME SWSTALCKFRD-LDI 13/226 RPLC PL | 31430342 | ETL.8068.POLE.WOOD | 013/226 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | Central | Non-WSIP | FSRP | [5 empty] | '-121.260829 | 38.1402 | ETL.8068 | 40869735 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 3
115413424 | SUTERHOME SWSTA-LCKFRD-LODI 16/299 RPLC | 31430342 | ETL.8068.POLE.WOOD | 016/299 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | Central | Non-WSIP | [6 empty] | '-121.405537 | 38.1896 | ETL.8068 | 40655530 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - Prog Multi
115413467 | SUTERHOME SWSTA-LCKFRD-LODI 18/323 RPLC | 31430342 | ETL.8068.POLE.WOOD | 018/323 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | Central | Non-WSIP | FSRP | [5 empty] | '-121.384251 | 38.1895 | ETL.8068 | 40863912 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - Prog Multi
115413484 | T3 CARIBOU-PALERMO :010/081 SHOE BOL RPL | 43725390 | CARIBOU-PALERMO | :010/081 | ICQ | E | Pre-2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.271411 | 39.9963 | ETL.3190 | 40910322 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
115413557 | SUTERHOME SW ST-LKFRD-LDI 18/327 RPL PL | 31430342 | ETL.8068.POLE.WOOD | 018/327 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | Central | Non-WSIP | FSRP | [5 empty] | '-121.380611 | 38.1894 | ETL.8068 | 40754252 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 3
115413559 | SUTERHOME SWSTA-LCKFRD-LODI 20/380 RPLC | 31430343 | ETL.8068.POLE.WOOD | 020/380 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | Central | Non-WSIP | FSRP | [5 empty] | '-121.332588 | 38.1891 | ETL.8068 | 40768720 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 3
115413594 | SUTER HME SW ST-LKFRD-LDI 22/405 RPL PL | 31430343 | ETL.8068.POLE.WOOD | 022/405 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | Central | Non-WSIP | FSRP | [5 empty] | '-121.308395 | 38.1891 | ETL.8068 | 40588034 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - Prog Multi
115413623 | SUTER HM SWSTA-LCKFRD-LODI C17/305 RPLC | 31430343 | ETL.8068.POLE.WOOD | C017/305 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | Central | Non-WSIP | FSRP | [5 empty] | '-121.409373 | 38.197 | ETL.8068 | 40586694 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 3
115413626 | SUTER HM SWSTA-LCKFRD-LODI C21/395 RPLC | 31430343 | ETL.8068.POLE.WOOD | C021/395 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | Central | Non-WSIP | FSRP | [5 empty] | '-121.466846 | 38.2253 | ETL.8068 | 40608334 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 3
115413628 | LOCKEFORD-LODI #3 4/93 REPLACE POLE | 31418885 | LOCKEFORD-LODI #3 | 004/093 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | Central | Non-WSIP | [6 empty] | '-121.242574 | 38.1013 | ETL.7450 | 40613617 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 2
115413657 | LOCKEFORD-LODI #3 B008/164 RPLC POLE | 31418885 | LOCKEFORD-LODI #3 | B008/164 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | Central | Non-WSIP | FSRP | [5 empty] | '-121.287556 | 38.0819 | ETL.7450 | 40666111 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 2
115413703 | LOCKEFORD-LODI #3 B10/197 RPLC POLE | 31418885 | LOCKEFORD-LODI #3 | B010/197 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | Central | Non-WSIP | FSRP | [5 empty] | '-121.290093 | 38.0576 | ETL.7450 | 40593615 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - Prog Multi
115414213 | COBURN-OIL FIELDS #20 28/378 RPL POLE | 31418447 | COBURN-OIL FIELDS #2 | 028/378 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.863016 | 35.9909 | ETL.6420 | 40615517 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Moss Landing |  | Y - 5
115414269 | ARCATA-HUMBOLDT 7/5 RPLACE POLE | 31418678 | ARCATA-HUMBOLDT | 007/005 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Coast | Non-WSIP | [6 empty] | '-124.08477 | 40.8652 | ETL.7110 | 40827173 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2019-06-05
115414302 | ARCATA-HUMBOLDT 7/9 REPLACE POLE | 31418678 | ARCATA-HUMBOLDT | 007/009 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-124.08763 | 40.8667 | ETL.7110 | 40616257 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2019-06-05
115417047 | T2 EXCHEQUER-YOSEMITE 11/33 COATING | 43825051 | EXCHEQUER-YOSEMITE | 011/033 | ICS | E | Pre-2020_(9a) Other ignition related | Budget Owner (Paint) |  |  | TR2 | LATE | South | Non-WSIP | [6 empty] | '-120.179863 | 37.5902 | ETL.8650 | 40660802 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Fresno |  | Y - 42
115421866 | T2 EXCHEQUER-YOSEMITE 13/41 PAINT | 43726815 | EXCHEQUER-YOSEMITE | 013/041 | ICY | E | Pre-2020_(3) On high spread structure | Budget Owner (Paint) |  | Likely MAT error - delink to correct | TR2 | LATE | South | Non-WSIP |  |  |  |  | Program | 2021 Paint took out of program due to future project to be removed with [REDACTED] | '-120.151129 | 37.5908 | ETL.8650 | 40582619 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Fresno |  | Y - 38
115439242 | T3 EI CARIBOU-PALERMO :011/090 BENT MEMB | 44051416 | CARIBOU-PALERMO | :011/090 | ICQ | E | Pre-2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.27741 | 39.9833 | ETL.3190 | 40910330 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115439244 | T3 CARIBOU-PALERMO :11/91 RPR BENT MEMBE |  | CARIBOU-PALERMO | :011/091 | 70S | E | Pre-2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.276852 | 39.9826 | ETL.3190 | 40912111 | Structure-Tower | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Pole Program | Capital | 426 | Table Mountain
115439245 | T3 CARIBOU-PALERMO :012/095 BENT MEMB | 44051416 | CARIBOU-PALERMO | :012/095 | ICQ | E | Pre-2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.274963 | 39.9723 | ETL.3190 | 40912114 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115439247 | T2 CARIBOU-PALERMO :013/103 BENT MEMB | 44054700 | CARIBOU-PALERMO | :013/103 | ICQ | E | Pre-2020_(2) High fire spread TD |  |  |  | TR2 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.278836 | 39.963 | ETL.3190 | 40738339 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115439248 | T2 CARIBOU-PALERMO :013/106 BENT MEMB | 44054700 | CARIBOU-PALERMO | :013/106 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.283913 | 39.9602 | ETL.3190 | 40738342 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115439273 | T2 EI CARIBOU-PALERMO :14/114 RPR STRT | 44054700 | CARIBOU-PALERMO | :014/114 | ICQ | E | Pre-2020_(2) High fire spread TD |  |  |  |  | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.299352 | 39.9544 | ETL.3190 | 40738344 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115439300 | T2 EI CARIBOU-PALERMO :014/111 RPR STRT | 43725390 | CARIBOU-PALERMO | :014/111 | ICQ | E | Pre-2020_(2) High fire spread TD |  |  |  | TR2 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.293251 | 39.9571 | ETL.3190 | 40642567 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 543 | Table Mountain |  |  | Yes
115439301 | T2 CARIBOU-PALERMO :14/110A RPR STRS | 44054700 | CARIBOU-PALERMO | :014/110A | ICQ | E | Pre-2020_(2) High fire spread TD |  |  |  | TR2 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.29189 | 39.9578 | ETL.3190 | 41162771 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115439304 | T2 CARIBOU-PALERMO :16/130 INS HRDT | 44054700 | CARIBOU-PALERMO | :016/130 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.318519 | 39.9331 | ETL.3190 | 40642212 | Hardware-Tower | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115439305 | T2 EI CARIBOU-PALERMO-:014/118 RPR CONS | 44304491 | CARIBOU-PALERMO | :014/118 | ICS | E | Pre-2020_(2) High fire spread TD |  |  |  | TR2 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.304514 | 39.949 | ETL.3190 | 40738823 | Conductor-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain
115439307 | T2 EI CARIBOU-PALERMO 14/118A RPR STRT | 44054700 | CARIBOU-PALERMO | 014/118A | ICQ | E | Pre-2020_(2) High fire spread TD |  |  |  |  | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.304531 | 39.949 | ETL.3190 | 43249803 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115439365 | T3 CARIBOU-PALERMO :012/093 RPR LEG | 44051416 | CARIBOU-PALERMO | :012/093 | ICQ | E | Pre-2020_(2) High fire spread TD |  |  |  |  | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.274659 | 39.9777 | ETL.3190 | 40912112 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115439368 | T2 CARIBOU-PALERMO :012/098 BENT MEMB | 44054700 | CARIBOU-PALERMO | :012/098 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.27494 | 39.9661 | ETL.3190 | 40910337 | Crossarm-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115439383 | T3 CARIBOU-PALERMO :012/096 WRN EYE BENT | 43725390 | CARIBOU-PALERMO | :012/096 | ICQ | E | Pre-2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.274824 | 39.9695 | ETL.3190 | 40910335 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115439405 | T2 EI CARIBOU-PALERMO :014/117 RPR STRT | 44054700 | CARIBOU-PALERMO | :014/117 | ICQ | E | Pre-2020_(2) High fire spread TD |  |  |  |  | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.303758 | 39.9498 | ETL.3190 | 40738345 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 543 | Table Mountain |  |  | Yes
115439406 | T2 CARIBOU-PALERMO-:015/120 BRKN SWAY | 44054700 | CARIBOU-PALERMO | :015/120 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.30764 | 39.9455 | ETL.3190 | 40642193 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115439424 | T2 CARIBOU-PALERMO :016/128 BENT MEMB | 44054700 | CARIBOU-PALERMO | :016/128 | ICQ | E | Pre-2020_(2) High fire spread TD |  |  |  | TR2 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.317529 | 39.9366 | ETL.3190 | 40738819 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115439453 | T2 CARIBOU-PALERMO-:013/104 RPR INSS | 44304491 | CARIBOU-PALERMO | :013/104 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.280354 | 39.9626 | ETL.3190 | 40747408 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain
115439457 | T2 CARIBOU-PALERMO :13/110 RPR STRT | 44054700 | CARIBOU-PALERMO | :013/110 | ICQ | E | Pre-2020_(2) High fire spread TD |  |  |  | TR2 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.290832 | 39.9582 | ETL.3190 | 40642211 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115439471 | T2 CARIBOU-PALERMO :015/124 BENT MEMB | 44054700 | CARIBOU-PALERMO | :015/124 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.31064 | 39.9396 | ETL.3190 | 40747414 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115442251 | IGNACIO-ALTO 10/52 REPL ANCHOR |  | IGNACIO-ALTO | 010/052 |  | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Coast | Non-WSIP | [6 empty] | '-122.501014 | 37.953 | ETL.7150 | 41196488 | Anchor-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLX | Contract | Expense |  | Lakeville
115443508 | T2 COLGATE-PALERMO 007/137 RPL POLE | 31417717 | COLGATE-PALERMO | 007/137 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-121.309629 | 39.347 | ETL.6500 | 40598475 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
115443515 | SCHINDLER-COALINGA #2 004/007 RPLC POLE | 31418453 | SCHINDLER-COALINGA #2 | 004/007 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.19293 | 36.3576 | ETL.9150 | 40821791 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno
115443589 | T2 COLGATE-PALERMO 008/154 RPL POLE | 31417717 | COLGATE-PALERMO | 008/154 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-121.326412 | 39.3509 | ETL.6500 | 40866214 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
115443678 | T2 COLGATE-PALERMO 010/198 RPL STRW | 31434603 | COLGATE-PALERMO | 010/198 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-121.360994 | 39.3645 | ETL.6500 | 40598472 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
115444841 | FIVE PTS SW STA HRN GTS 01/014 RPLC POLE | 31418455 | SCHINDLER-HURON-GATES | 001/014 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.139233 | 36.3751 | ETL.9160 | 41107525 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 4
115444872 | FIVE PTS SW STA HRN GTS 01/015 RPLC POLE | 31418455 | SCHINDLER-HURON-GATES | 001/015 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.139256 | 36.3742 | ETL.9160 | 41107526 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 4
115445093 | T2 CARIBOU-PALERMO :016/136 BENT MEMB | 44056391 | CARIBOU-PALERMO | :016/136 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.318125 | 39.9254 | ETL.3190 | 40738352 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115445125 | T2 CARIBOU-PALERMO :17/144 RPR STRT | 44056391 | CARIBOU-PALERMO | :017/144 | ICQ | E | Pre-2020_(2) High fire spread TD |  |  |  | TR2 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.325693 | 39.9173 | ETL.3190 | 40738818 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115445131 | T2 CARIBOU-PALERMO :17/139 INS HRDT | 44056391 | CARIBOU-PALERMO | :017/139 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.318496 | 39.9218 | ETL.3190 | 40738353 | Hardware-Tower | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115445154 | T2 EI CARIBOU-PALERMO :018/155 RPR STRT | 44056391 | CARIBOU-PALERMO | :018/155 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.338847 | 39.909 | ETL.3190 | 40747480 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115445195 | T2 CARIBOU-PALERMO :020/165 BENT MEMB |  | CARIBOU-PALERMO | :020/165 | 70S | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.36186 | 39.8977 | ETL.3190 | 40747482 | Structure-Tower | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Pole Program | Capital | 426 | Table Mountain |  |  | Yes
115445275 | NICOLAUS-CATLETT 74/546 RPL INSS | 31457035 | NICOLAUS-CATLETT JCT | 074/546 | 93K | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Valley | Non-WSIP | [6 empty] | '-121.486874 | 38.7202 | ETL.7680 | 40643300 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 532 | Sacramento
115445292 | T2 EI CARIBOU-PALERMO :023/193 RPL HRDT | 44056391 | CARIBOU-PALERMO | :023/193 | ICQ | E | Pre-2020_(2) High fire spread TD |  |  |  | TR2 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.395764 | 39.8578 | ETL.3190 | 40668938 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
115445357 | RIO OSO-WEST SACRAMENTO 3/022 RPL INSUL | 31457038 | RIO OSO-WEST SACRAMENTO | 003/022 | 93K | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Valley | Non-WSIP | [6 empty] | '-121.515646 | 38.8701 | ETL.3450 | 40911135 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 532 | Sacramento
115445388 | T3 EI CARIBOU-PALERMO :30/242 RPR STRT | 43725390 | CARIBOU-PALERMO | :030/242 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.451805 | 39.7819 | ETL.3190 | 40702267 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115445413 | GLENN #4 006/134 STRW ROTN REPL | 31418859 | GLENN #4 | 006/134 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-122.163338 | 39.8588 | ETL.8424 | 41104681 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
115445514 | T2 EI CARIBOU-PALERMO :017/141 RPR STRT | 43725390 | CARIBOU-PALERMO | :017/141 | ICQ | E | Pre-2020_(2) High fire spread TD |  |  |  |  | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.321058 | 39.9198 | ETL.3190 | 40642499 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
115445517 | T2 CARIBOU-PALERMO-:018/150 MISS NUT SHO |  | CARIBOU-PALERMO | :018/150 | 93C | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.330456 | 39.9121 | ETL.3190 | 40642283 | Insulator-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 531 | Table Mountain
115445584 | T2 CARIBOU-PLRMO :018/153 RPL BENT MEMB |  | CARIBOU-PALERMO | :018/153 | 70S | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.334702 | 39.9097 | ETL.3190 | 40738358 | Structure-Tower | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Pole Program | Capital | 426 | Table Mountain
115445656 | T2 EI CARIBOU-PALERMO :020/169 BRKN SWAY |  | CARIBOU-PALERMO | :020/169 | 70S | E | Pre-2020_(2) High fire spread TD |  |  |  | TR2 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.362505 | 39.8917 | ETL.3190 | 40863107 | Structure-Tower | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Pole Program | Capital | 426 | Table Mountain |  |  | Yes
115445685 | T2 EI CARIBOU-PALERMO :020/169 REGRADE | 44304491 | CARIBOU-PALERMO | :020/169 | ICS | E | Pre-2020_(3) On high spread structure |  |  |  | TR2 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.362505 | 39.8917 | ETL.3190 | 40863107 | Structure-Steel | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
115445696 | T2 CARIBOU-PALERMO :021/174 BENT MEMB | 44056391 | CARIBOU-PALERMO | :021/174 | ICQ | E | Pre-2020_(2) High fire spread TD |  |  |  | TR2 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.368699 | 39.8875 | ETL.3190 | 40753390 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
115445712 | T2 EI CARIBOU-PALERMO :021/178 BENT MEMB | 44056391 | CARIBOU-PALERMO | :021/178 | ICQ | E | Pre-2020_(2) High fire spread TD |  |  |  | TR2 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.373611 | 39.881 | ETL.3190 | 40858945 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115445745 | T2 CARIBOU-PALERMO-:021/179 PAINT STRT | 44056391 | CARIBOU-PALERMO | :021/179 | ICQ | E | Pre-2020_(2) High fire spread TD |  |  |  | TR2 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.37491 | 39.8785 | ETL.3190 | 40738369 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115445762 | T2 CARIBOU-PALERMO :022/184 BENT MEMB | 44056391 | CARIBOU-PALERMO | :022/184 | ICQ | E | Pre-2020_(2) High fire spread TD |  |  |  | TR2 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.378747 | 39.8714 | ETL.3190 | 40753356 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115445816 | T2 CARIBOU-PALERMO-:024/198 RPL CTR KEY | 44304491 | CARIBOU-PALERMO | :024/198 | ICS | E | Pre-2020_(2) High fire spread TD |  |  |  | TR2 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.401589 | 39.8512 | ETL.3190 | 40867974 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain
115445847 | T2 CARIBOU-PALERMO :024/200 BENT MEMB | 44056391 | CARIBOU-PALERMO | :024/200 | ICQ | E | Pre-2020_(2) High fire spread TD |  |  |  | TR2 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.40384 | 39.85 | ETL.3190 | 40599288 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115445854 | T2 CARIBU-PALERMO :25/207 RPL BENT MEBER |  | CARIBOU-PALERMO | :025/207 | 70S | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.417991 | 39.8408 | ETL.3190 | 40826431 | Structure-Tower | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Pole Program | Capital | 426 | Table Mountain
115445911 | T2 EI CARIBOU-PALERMO :026/213 RPR STRT | 44056391 | CARIBOU-PALERMO | :026/213 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.421318 | 39.8294 | ETL.3190 | 40668942 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
115445917 | T2 CARIBOU-PALERMO :029/237 RPR INSS | 44304491 | CARIBOU-PALERMO | :029/237 | ICS | E | Pre-2020_(2) High fire spread TD |  |  |  | TR2 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.45426 | 39.7907 | ETL.3190 | 40826433 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain
115445970 | T3 EI CARIBOU-PALERMO :30/246 RPR STRT |  | CARIBOU-PALERMO | :030/246 | 70S | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.452706 | 39.7765 | ETL.3190 | 40816591 | Structure-Tower | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Pole Program | Capital | 426 | Table Mountain
115445976 | T3 CARIBOU-PALERMO :30/249A RPR STRS | 44304458 | CARIBOU-PALERMO | :030/249A | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.456308 | 39.7717 | ETL.3190 | 41162678 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
115446061 | T2 CARIBOU-PALERMO :17/140 RPR STRT | 44056391 | CARIBOU-PALERMO | :017/140 | ICQ | E | Pre-2020_(2) High fire spread TD |  |  |  | TR2 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.319376 | 39.9211 | ETL.3190 | 40642213 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115446063 | T2 CARIBOU-PALERMO :017/143 BENT MEMB | 44056391 | CARIBOU-PALERMO | :017/143 | ICQ | E | Pre-2020_(2) High fire spread TD |  |  |  | TR2 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.324088 | 39.9184 | ETL.3190 | 40738355 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115446131 | T2 CARIBOU-PALERMO :020/162 BENT MEMB | 44056391 | CARIBOU-PALERMO | :020/162 | ICQ | E | Pre-2020_(2) High fire spread TD |  |  |  | TR2 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.357958 | 39.9029 | ETL.3190 | 40738811 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115446134 | T2 CARIBOU-PALERMO :020/168 BENT MEMB | 44056391 | CARIBOU-PALERMO | :020/168 | ICQ | E | Pre-2020_(2) High fire spread TD |  |  |  | TR2 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.361944 | 39.8926 | ETL.3190 | 40858943 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
115446181 | T2 CARIBOU-PALERMO :022/185 RPR STRT | 44056391 | CARIBOU-PALERMO | :022/185 | ICQ | E | Pre-2020_(2) High fire spread TD |  |  |  | TR2 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.380738 | 39.8706 | ETL.3190 | 40738371 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115446205 | T2 CARIBOU-PALERMO :023/194 RPR FOND | 44056391 | CARIBOU-PALERMO | :023/194 | ICQ | E | Pre-2020_(2) High fire spread TD |  |  |  |  | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.396832 | 39.8566 | ETL.3190 | 40758632 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115446257 | T2 CARIBOU-PALERMO :025/209 BENT STEEL | 44056391 | CARIBOU-PALERMO | :025/209 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.420523 | 39.8364 | ETL.3190 | 40863363 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115446274 | T2 CARIBOU-PALERMO-:025/209 RPL CTTR KEY | 44304491 | CARIBOU-PALERMO | :025/209 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.420523 | 39.8364 | ETL.3190 | 40863363 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain
115446392 | T3 CARIBOU-PALERMO :030/247 BENT SWAY | 43735849 | CARIBOU-PALERMO | :030/247 | ICS | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | 9Lines Pre-WSIP |  |  |  |  | Field Operations |  | '-121.454013 | 39.7748 | ETL.3190 | 40826439 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
115447759 | T2 HUMBOLDT-TRINITY 76/0R RPL POLE | 31497850 | HUMBOLDT-TRINITY | 076/000 | 70Y | E | Pre-2020_(2) High fire spread TD |  |  |  | TR2 | LATE | North Coast | Non-WSIP |  |  |  |  | Project | 2021 HUMBOLDT-TRINITY | '-123.442836 | 40.6977 | ETL.1820 | 44565523 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2019-08-13
115448774 | IGNACIO-ALTO - 60 replace pole 12/94 | 31418881 | IGNACIO-ALTO | 012/094 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Coast | Non-WSIP | [6 empty] | '-122.508622 | 37.9569 | ETL.7150 | 40877635 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville
115448861 | IGNACIO-ALTO 13/101 REPL NG POLE | 31433716 | IGNACIO-ALTO | 013/101 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Coast | Non-WSIP | [6 empty] | '-122.509876 | 37.9524 | ETL.7150 | 40753385 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Lakeville |  |  | 2019-04-12
115451003 | IGNACIO-ALTO 014/122 CANCEL | 43762410 | IGNACIO-ALTO | 014/122 | ICQ | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  | CANCEL/CNCL |  | LATE | North Coast | Non-WSIP | [6 empty] | '-122.516055 | 37.9382 | ETL.7150 | 40863517 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville
115451102 | IGNACIO-ALTO -014/125 mud sill | 43749533 | IGNACIO-ALTO | 014/125 | ICW | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Coast | Non-WSIP | [6 empty] | '-122.514064 | 37.9373 | ETL.7150 | 40651470 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-08-06
115453212 | GLENN-DELEVAN 127/999 INSS NG REPL | 31439322 | GLENN-DELEVAN | 127/999 | 93K | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-122.263122 | 39.4204 | ETL.7042 | 40897192 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  | Yes
115454057 | GLENN-DELEVAN 104/850 INSS NG REPL | 31439322 | GLENN-DELEVAN | 104/850 | 93K | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-122.264942 | 39.7445 | ETL.7042 | 40635120 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain
115455381 | PALERMO WYANDOTTE_001/016 INSS NG REPL | 31441968 | PALERMO-WYANDOTTE | 001/016 | 93K | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-121.539547 | 39.4754 | ETL.4315 | 40843426 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  | Yes
115461120 | FIVE PTS SW STA HRN GTS 03/001 RPL POLE | 31418455 | SCHINDLER-HURON-GATES | 003/001 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.139395 | 36.357 | ETL.9160 | 41107547 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 4
115462585 | CONTRA COSTA-BALFOUR 009/226 Repl pole | 31418424 | CONTRA COSTA-BALFOUR | 009/226 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | Central | Non-WSIP | FSRP | [5 empty] | '-121.677654 | 37.9538 | ETL.8420 | 40643956 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Bay |  | Y - 1
115463683 | GLENN #2_006/118 RPL INSUL | 31418508 | GLENN #2 | 006/118 | 93I | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-122.038467 | 39.7756 | ETL.6930 | 40630386 | Insulator-Wood | No Good/Out of Stdrd | Replace | DOCC | DOCC | Job has been constructed (documentation) | Complete | PEND | LC | TLX | Contract | Capital | 508 | Table Mountain |  |  | Yes
115464060 | FIVE PTS SW STA HRN GTS 03/005 RPL POLE | 31418455 | SCHINDLER-HURON-GATES | 003/005 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.139432 | 36.3534 | ETL.9160 | 41107551 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 4
115464595 | T2 TRINITY-MAPLE CREEK 16/003C RPL POLE | 31418582 | TRINITY-MAPLE CREEK | 016/003B | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.195171 | 40.7387 | ETL.8170 | 40642840 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2019-04-19
115464915 | WEBER-FRENCH CAMP #1 2/43 REPLACE POLE |  | WEBER #1 | 002/043 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  | Will be completed under LC 120135402; can we DLFL? |  |  | LATE | Central | Non-WSIP | [6 empty] | '-121.273092 | 37.9073 | ETL.8320 | 40825591 | Structure-Wood | Rotten | Replace |  |  |  |  | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 6
115464917 | WEBER-FRENCH CAMP #1 2/50 REPLACE POLE | 31418889 | WEBER #1 | 002/050 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | Central | Non-WSIP | [6 empty] | '-121.272326 | 37.9025 | ETL.8320 | 40643597 | Structure-Wood | Rotten | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 6
115464919 | WEBER-FRENCH CAMP #1 3/81 REPLACE POLE | 31418889 | WEBER #1 | 003/081 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | Central | Non-WSIP | FSRP | [5 empty] | '-121.273306 | 37.8827 | ETL.8320 | 40875866 | Structure-Wood | Rotten | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - Prog Multi
115465061 | WEBER-FRENCH CAMP #1 4/86 REPLACE POLE | 31418889 | WEBER #1 | 004/086 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | Central | Non-WSIP | FSRP | [5 empty] | '-121.276059 | 37.8817 | ETL.8320 | 44229259 | Structure-Wood | Rotten | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 4
115469273 | GLENN #4 011/229 STRW ROTN REPL | 31418859 | GLENN #4 | 011/229 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-122.18826 | 39.9151 | ETL.8424 | 41104583 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
115469690 | GLENN #4 012/251 STRW ROTN REPL | 31418859 | GLENN #4 | 012/251 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-122.188145 | 39.9294 | ETL.8424 | 41104568 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain
115477377 | WEBER-FRENCH CAMP #2 5/122 REPLACE POLE | 31418887 | SPARE T-LINE RECORD | 005/122 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | Central | Non-WSIP | FSRP | [5 empty] | '-121.303388 | 37.881 | ETL.8321 | 40580385 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 6
115477892 | WEBER-FRENCH CAMP #2 A000/21 RPLC POLE | 31418887 | SPARE T-LINE RECORD | A000/021 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | Central | Non-WSIP | FSRP | [5 empty] | '-121.251938 | 37.9161 | ETL.8321 | 40823876 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - Prog Multi
115477894 | WEBER-FRENCH CAMP #2 A000/22 RPLC POLE | 31418887 | SPARE T-LINE RECORD | A000/022 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | Central | Non-WSIP | FSRP | [5 empty] | '-121.252803 | 37.9159 | ETL.8321 | 40875895 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - Prog Multi
115477897 | WEBER-FRENCH CAMP #2 A001/36 RPLC POLE | 31418887 | SPARE T-LINE RECORD | A001/036 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | Central | Non-WSIP | FSRP | [5 empty] | '-121.264963 | 37.9127 | ETL.8321 | 40593088 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - Prog Multi
115477919 | WEBER-FRENCH CAMP#2 AC008/137 RPLC POLE | 31418887 | SPARE T-LINE RECORD | AC008/137 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | Central | Non-WSIP | FSRP | [5 empty] | '-121.309609 | 37.881 | ETL.8321 | 40804168 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 6
115478012 | FIVE PTS SW STA HRN GTS 05/004 RPL POLE | 31418455 | SCHINDLER-HURON-GATES | 005/004 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.139571 | 36.326 | ETL.9160 | 40766105 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 4
115478055 | T2 HUMBOLDT-TRINITY 88/3A RPLC POLE | 31418580 | HUMBOLDT-TRINITY | 088/003 | 70Y | E | Pre-2020_(2) High fire spread TD |  |  |  | TR2 | LATE | North Coast | Non-WSIP |  |  |  |  | Project | 2021 HUMBOLDT-TRINITY | '-123.662205 | 40.7274 | ETL.1820 | 44562991 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2019-08-13
115478182 | FIVE PTS SW STA HRN GTS 05/009 RPL POLE | 31418455 | SCHINDLER-HURON-GATES | 005/009 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.139582 | 36.3215 | ETL.9160 | 40859327 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 4
115478213 | NICOLAUS-WILKINS SLOUGH 3/068 REFRAME T1 | 31418512 | NICOLAUS-WILKINS SLOUGH | 003/068 | 93E | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-121.582697 | 38.8838 | ETL.7710 | 40866132 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 637 | Sacramento |  |  | Yes
115478266 | NICOLAUS-WILKINS SLOUGH 3/071 RPL INSUL | 31418512 | NICOLAUS-WILKINS SLOUGH | 003/071 | 93E | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-121.584816 | 38.8824 | ETL.7710 | 40599032 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 637 | Sacramento |  |  | Yes
115478352 | NICOLAUS-PLAINFIELD 20/330 AUTO SPLICE | 43910652 | NICOLAUS-PLAINFIELD | 020/330 | ICW | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-121.721818 | 38.7128 | ETL.7700 | 40756534 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
115478542 | NICOLAUS-PLAINFIELD 25/419 RPR CONNECTOR | 43910650 | NICOLAUS-PLAINFIELD | 025/419 | ICM | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-121.752624 | 38.6555 | ETL.7700 | 43702314 | Connector | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 534 | Sacramento |  |  | Yes
115478544 | NICOLAUS-PLAINFIELD 25/416 RPR CONNECTOR | 43910650 | NICOLAUS-PLAINFIELD | 025/416 | ICM | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-121.748513 | 38.6555 | ETL.7700 | 43702323 | Connector | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 534 | Sacramento |  |  | Yes
115478896 | T2 LAYTONVILLE-WILLITS 16/01 REPL POLE | 31418219 | LAYTONVILLE-WILLITS | 016/001 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.452355 | 39.594 | ETL.8360 | 40584828 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  | 2019-05-08
115480772 | FIVE PTS SW STA HRN GTS 05/015 RPL POLE | 31418455 | SCHINDLER-HURON-GATES | 005/015 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.13961 | 36.3163 | ETL.9160 | 40765650 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 4
115480779 | FIVE PTS SW STA HRN GTS 05/017 RPL POLE | 31418455 | SCHINDLER-HURON-GATES | 005/017 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.139627 | 36.3146 | ETL.9160 | 40806535 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 4
115481587 | FIVE PTS SW STA HRN GTS 007/013 RPL POLE | 31419518 | SCHINDLER-HURON-GATES | 007/013 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.126421 | 36.2989 | ETL.9160 | 40663610 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 4
115482779 | FIVE PTS SW STA HRN GTS 009/001 RPL POLE | 31419518 | SCHINDLER-HURON-GATES | 009/001 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.121524 | 36.2844 | ETL.9160 | 40597743 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 4
115483059 | FIVE PTS SW STA HRN GTS 009/008 RPL POLE | 31419518 | SCHINDLER-HURON-GATES | 009/008 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | [6 empty] | '-120.121519 | 36.2773 | ETL.9160 | 40859398 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 4
115483231 | GLENN #4 000/004 RPR BOND WIRE | 43890231 | GLENN #4 | 000/004 | ICW | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-122.140809 | 39.7771 | ETL.8424 | 41104810 | Insulator Bond Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
115483583 | FIVE PTS SW STA HRN GTS 011/004 RPL POLE | 31419518 | SCHINDLER-HURON-GATES | 011/004 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.121597 | 36.2518 | ETL.9160 | 40766116 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 4
115483590 | FIVE PTS SW STA HRN GTS 011/005 RPL POLE | 31419518 | SCHINDLER-HURON-GATES | 011/005 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.121601 | 36.2506 | ETL.9160 | 40748252 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 4
115483620 | FIVE PTS SW STA HRN GTS 011/007 RPL POLE | 31419518 | SCHINDLER-HURON-GATES | 011/007 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.121645 | 36.2481 | ETL.9160 | 40821835 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 4
115483652 | FIVE PTS SW STA HRN GTS 011/010 REFRAME | 31419519 | SCHINDLER-HURON-GATES | 011/010 | 93E | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.12166 | 36.2445 | ETL.9160 | 40625660 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 637 | Fresno |  | Y - 4
115483655 | FIVE PTS SW STA HRN GTS 011/012 REFRAME | 31419519 | SCHINDLER-HURON-GATES | 011/012 | 93E | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.121633 | 36.2421 | ETL.9160 | 40707868 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 637 | Fresno |  | Y - 4
115483690 | FIVE PTS SW STA HRN GTS 012/004 REFRAME | 31419519 | SCHINDLER-HURON-GATES | 012/004 | 93E | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.121712 | 36.2374 | ETL.9160 | 40776864 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 637 | Fresno |  | Y - 4
115490262 | FIVE PTS SW STA HRN GTS 012/011 REFRAME | 31419519 | SCHINDLER-HURON-GATES | 012/011 | 93E | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.121693 | 36.229 | ETL.9160 | 40624363 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 637 | Fresno |  | Y - 4
115490297 | FIVE PTS SW STA HRN GTS 012/013 RPL POLE | 31419518 | SCHINDLER-HURON-GATES | 012/013 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.121677 | 36.2265 | ETL.9160 | 40663614 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 4
115490772 | FIVE PTS SW STA HRN GTS 014/006 RPL POLE | 31419518 | SCHINDLER-HURON-GATES | 014/006 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.121425 | 36.2058 | ETL.9160 | 40823327 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - 4
115490984 | T3 EI DRM-GRS VLY-WMR B17/386 RPR GYWW | 43746390 | DRUM-GRASS VALLEY-WEIMAR | B017/386 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.9653 | 39.1328 | ETL.6760 | 40814230 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Sacramento |  |  | Yes
115492434 | T3 EI DRUM-GRASS VALLEY-WEIMAR-009/221 | 43746390 | DRUM-GRASS VALLEY-WEIMAR | 009/221 | ICW | E | Pre-2020_(9a) Other ignition related |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-120.869466 | 39.1718 | ETL.6760 | 40824302 | Guy Wire-Wood | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Sacramento |  |  | Yes
115504353 | DISTRIBUTION |  | DRUM-GRASS VALLEY-WEIMAR | 020/463 | 93E | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.983208 | 39.0546 | ETL.6760 | 40766710 | Crossarm-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLX | Contract | Capital | 637 | Sacramento |  |  | Yes
115506701 | TABLE MTN-VACA 041/164 RPL INSS | 31528801 | TABLE MTN-VACA | 041/164 | 93K | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-121.847458 | 38.9902 | ETL.6090 | 40756826 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Sacramento
115506822 | TABLE MTN-TESLA 019/075 RPL INSULATOR | 31455289 | TABLE MTN-TESLA | 019/075 | 93K | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-121.752022 | 39.2951 | ETL.6080 | 40761251 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  | Yes
115507534 | T2 EI DRUM-GRASS VALLEY-WEIMAR-014/333 | 43746390 | DRUM-GRASS VALLEY-WEIMAR | 014/333 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.942933 | 39.1254 | ETL.6760 | 40867122 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Sacramento |  |  | Yes
115507579 | T2 Round Mtn_Table Mt#2_061/258 RPL INSS | 31455287 | ROUND MTN-TABLE MTN #2 | 061/258 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-121.831989 | 39.9305 | ETL.6070 | 40895430 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  | Yes
115508735 | FIVE PTS SW STA HRN GTS 015/003 REFRAME | 31419519 | SCHINDLER-HURON-GATES | 015/003 | 93E | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.120042 | 36.1957 | ETL.9160 | 40694973 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 637 | Fresno |  | Y - Prog Multi
115508851 | FIVE PTS SW STA HRN GTS 015/009 REFRAME | 31419519 | SCHINDLER-HURON-GATES | 015/009 | 93E | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.110891 | 36.1958 | ETL.9160 | 40897382 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 637 | Fresno |  | Y - Prog Multi
115508854 | FIVE PTS SW STA HRN GTS 15/10 REFRAME | 31419519 | SCHINDLER-HURON-GATES | 015/010 | 93E | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.109458 | 36.1958 | ETL.9160 | 40638624 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 637 | Fresno |  | Y - Prog Multi
115510745 | T2 RND MTN-TBLE MT#2 049/215 RPL SPAS | 43347033 | ROUND MTN-TABLE MTN #2 | 049/215 | ICS | E | Pre-2020_(2) High fire spread TD |  |  |  | TR2 | LATE | North Valley | Non-WSIP |  |  |  |  | Clearance Cancelled by GCC | 2021 - Cancelled by ISO | '-121.899595 | 40.0979 | ETL.6070 | 40759771 | Spacer-Steel | No Good/Out of Stdrd | Replace | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
115511533 | T3 EI DRUM-HIGGINS-9/87C REP ANCHOR | 31423105 | DRUM-HIGGINS | 009/087C | 93E | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.892097 | 39.1661 | ETL.4393 | 44202750 | Anchor-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Sacramento |  |  | Yes
115511566 | T3 EI DRUM-HIGGINS 009/092R RPL PL | 31423101 | DRUM-HIGGINS | 009/092 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.8925829 | 39.1723 | ETL.4393 | 44172128 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
115515465 | T3 EI DRUM-HIGGINS 3/32L REPLACE POLE | 31423101 | DRUM-HIGGINS | 003/032 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.799724 | 39.2229 | ETL.4393 | 44172142 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
115515697 | T3 EI DRUM-HIGGINS-115 KV_003/042C | 43687142 | DRUM-HIGGINS | 003/042C | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  | Likely MAT error - delink to correct | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.817605 | 39.2192 | ETL.4393 | 44313914 | Anchor-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes
115515711 | T3 EI DRUM-HIGGINS 3/042B RPL ANCHOR | 31432820 | DRUM-HIGGINS | 003/042B | 93E | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.81757 | 39.2191 | ETL.4393 | 44313913 | Anchor-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Sacramento |  |  | Yes
115515722 | T3 EI DRUM-HIGGINS-3/42A CORRODED ANCHOR | 43687142 | DRUM-HIGGINS | 003/042A | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  | Likely MAT error - delink to correct | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.817539 | 39.2191 | ETL.4393 | 44313912 | Anchor-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes
115515787 | T3 EI MIDDLE FORK-GOLD HILL 003/028 REPL | 31421211 | MIDDLE FORK-GOLD HILL | 003/028 | 70Y | E | Pre-2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP |  |  |  |  | Internal Process | 2021 - Micro pile vendor (Crux) unavailable in 2020 | '-120.630383 | 38.9995 | ETL.5140 | 44761223 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
115523853 | T2 IGNACIO-ALTO 16/162 RE-ESTAB ROW RD |  | IGNACIO-ALTO | 016/162 | CHR | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-122.51965 | 37.9151 | ETL.7150 | 40617235 | Right of Way | Encroachment | Remove |  |  |  |  | PEND | LC | TLS | Land | Expense | 931 | Lakeville
115540807 | T2 RND MT-TBL MT#2 49/216 RPR JUMS | 43621090 | ROUND MTN-TABLE MTN #2 | 049/216 | ICS | E | Pre-2020_(2) High fire spread TD |  |  |  | TR2 | LATE | North Valley | Non-WSIP |  |  |  |  | Clearance Cancelled by GCC | 2021 - Cancelled by ISO | '-121.897092 | 40.0912 | ETL.6070 | 40817857 | Jumper-Steel | No Good/Out of Stdrd | Repair | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
115541557 | T2 EI SANTA ROSA-CORONA 11/265 GYWW | 43749631 | SANTA ROSA-CORONA (NO FLY) | 011/265 | ICW | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.68236 | 38.2851 | ETL.4309 | 41104271 | Guy Wire-Wood | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-08-06
115541879 | T3 EI FULTON-CLSTG :006/004 RPL CRSW | 31424405 | FULTON-CALISTOGA | :006/004 | 93E | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.588338 | 38.675 | ETL.6880 | 40912474 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Lakeville |  |  | 2019-08-06
115542061 | T3 EI FULTON-CLSTG :006/004 RPR CNDW | 43736233 | FULTON-CALISTOGA | :006/004 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.588338 | 38.675 | ETL.6880 | 40912474 | Conductor-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-08-06
115542284 | T3 EI FULTON-CALISTOGA :008/002 INS GYWW | 43749446 | FULTON-CALISTOGA | :008/002 | ICW | E | Pre-2020_(9a) Other ignition related |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.600416 | 38.7031 | ETL.6880 | 40905729 | Guy Wire-Wood | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-08-06
115542802 | T3 EI FULTON-CALISTOGA :3/6 RPR GYWW | 43749446 | FULTON-CALISTOGA | :003/006 | ICW | E | Pre-2020_(9a) Other ignition related |  |  |  |  | LATE | North Coast | WSIP | [6 empty] | '-122.594766 | 38.6397 | ETL.6880 | 40912436 | Guy Wire-Wood | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-08-06
115543257 | T2 EI CARIBOU-WESTWD 007/140B CANCEL | 43640851 | CARIBOU-WESTWOOD | 007/140 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  | CANCEL/CNCL | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.08781 | 40.1717 | ETL.6300 | 42624246 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
115543874 | T2 EI COLGATE-PALERMO 010/199 RPL STRW | 31423185 | COLGATE-PALERMO | 010/199 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.361873 | 39.3648 | ETL.6500 | 40672059 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
115544377 | T2NT EI COLGATE-PALERMO 011/212 INS MRKW | 43910644 | COLGATE-PALERMO | 011/212 | ICW | F | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.369948 | 39.371 | ETL.6500 | 40767091 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
115544394 | T3 COLGATE-PALERMO 12/238 RPL POLE | 31417717 | COLGATE-PALERMO | 012/238 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-121.389121 | 39.3798 | ETL.6500 | 40610902 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
115544399 | T2 EI COLGATE-PALERMO 012/246 RPL POLE | 31423185 | COLGATE-PALERMO | 012/246 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.395327 | 39.382 | ETL.6500 | 40874603 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
115544561 | T2 EI COLGATE-PALERMO 012/249 RPL POLE | 31423185 | COLGATE-PALERMO | 012/249 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.397411 | 39.3832 | ETL.6500 | 40591735 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
115544562 | T2 COLGATE-PLERMO-60 kV_013/252 RPL STRW | 31417717 | COLGATE-PALERMO | 013/252 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-121.399177 | 39.3841 | ETL.6500 | 40692805 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
115544601 | T2 COLGATE-PALERMO 013/260 CONN NG REPL | 43878339 | COLGATE-PALERMO | 013/260 | ICM | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-121.403352 | 39.3876 | ETL.6500 | 40610864 | Connector | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 534 | Table Mountain |  |  | Yes
115544660 | T2 EI COLGATE-PALERMO 013/267 RPL STRW | 31423185 | COLGATE-PALERMO | 013/267 | 70Y | E | 2020_(1a) PSPS |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.407265 | 39.3898 | ETL.6500 | 40822476 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
115545480 | T2 EI LAKEVILLE #1 005/009 RMV DEB | 43749612 | LAKEVILLE #1 | 005/009 | ICW | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | WSIP | FSRP | [5 empty] | '-122.586797 | 38.3337 | ETL.7360 | 40861378 | Structure-Wood | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
115546051 | T2 EI TULUCAY-NAPA #1 007/004 RPL STRW | 31460465 | TULUCAY-NAPA #1 | 007/004 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.206128 | 38.2672 | ETL.8180 | 40763973 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  | 2019-08-09
115546193 | T2 EI TULUCAY-NAPA #1 006/017 RPR GYWW | 43740449 | TULUCAY-NAPA #1 | 006/017 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.203099 | 38.2633 | ETL.8180 | 40809019 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-08-09
115546198 | T2 EI TULUCAY-NAPA #1 007/007 RPL STRW | 31460465 | TULUCAY-NAPA #1 | 007/007 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.208458 | 38.2702 | ETL.8180 | 40809021 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  | 2019-04-12
115546737 | T3 EI FULTON-CALISTGA 000/001 INS GYWW | 43749446 | FULTON-CALISTOGA | 000/001 | ICW | E | Pre-2020_(9a) Other ignition related |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.443127 | 38.5075 | ETL.6880 | 40585438 | Guy Wire-Wood | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-06-05
115548600 | T2 EI TULUCAY-NAPA #1 007/006 RPL ANCW | 31434773 | TULUCAY-NAPA #1 | 007/006 | 93E | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.207683 | 38.2692 | ETL.8180 | 40821522 | Anchor-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Lakeville |  |  | 2019-08-09
115548602 | T2 EI TULUCAY-NAPA #1 007/008 REPL ANCW | 31506249 | TULUCAY-NAPA #1 | 007/008 | 93E | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.2101 | 38.2705 | ETL.8180 | 40872385 | Anchor-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Lakeville |  |  | 2019-08-09
115557429 | T2 EI SPLDNG #3-SPLDNG #1 00/018 REPL PL | 31445624 | SPAULDING #3-SPAULDING #1 | 000/018 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.640103 | 39.3349 | ETL.8050 | 40862188 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
115557524 | T2 EI CARIBOU-WESTWOOD 007/137C GYWW | 43640851 | CARIBOU-WESTWOOD | 007/137C | ICW | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.090679 | 40.1713 | ETL.6300 | 42624243 | Guy Wire-Wood | Missing | Install | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
115557543 | T3 EI FULTON-CALISTOGA :010/002 RPR GYWW | 43668969 | FULTON-CALISTOGA | :010/002 | ICW | E | Pre-2020_(9a) Other ignition related |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.608146 | 38.731 | ETL.6880 | 40905749 | Guy Wire-Wood | Missing | Install | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-05-06
115557642 | T3 EI FULTON-CALISTOGA 002/007 RPL POLE | 31481143 | FULTON-CALISTOGA | 002/007 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.48011 | 38.5294 | ETL.6880 | 40825320 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  | 2019-05-06
115557663 | T2 EI SPLDNG #3-SPLDNG #1 00/016 REPL PL | 31445624 | SPAULDING #3-SPAULDING #1 | 000/016 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.641346 | 39.3339 | ETL.8050 | 40810192 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
115557812 | T2 EI TULUCAY-NAPA #1 T003/000 GYWW | 43740449 | TULUCAY-NAPA #1 | T003/000 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.20938 | 38.2567 | ETL.8180 | 40603472 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-08-09
115557821 | EI WINTU TAP 000/002 RPL POLE | 31436367 | WINTU TAP | 000/002 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-122.353124 | 40.5799 | ETL.6311 | 40701918 | Structure-Wood | No Good/Out of Stdrd | Replace | MAPP srdy | MAPP | Constructed and mapped | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
115559349 | T2 EI COLGATE-PALERMO 012/239 RPL ANCW | 31456479 | COLGATE-PALERMO | 012/239 | 93E | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.389522 | 39.3799 | ETL.6500 | 40590388 | Anchor-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  | Yes
115559376 | T2 DI COLGATE-PLRMO 12/242 RPL STRW | 31423185 | COLGATE-PALERMO | 012/242 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.392142 | 39.3807 | ETL.6500 | 40767062 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
115559431 | T2 EI CARIBOU-WESTWD 005/104 RMV VEGN |  | CARIBOU-WESTWOOD | 005/104 | HNA | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.110202 | 40.1498 | ETL.6300 | 44191069 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Table Mountain |  | Yes
115559596 | T2 COLGATE-PALERMO 018/374 RPL STRW | 31417717 | COLGATE-PALERMO | 018/374 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-121.457958 | 39.4465 | ETL.6500 | 40866835 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
115582004 | CHRISTIE-WILLOW PASS-60 kV_5/72 RPR FND | 44110982 | CHRISTIE-WILLOW PASS | 005/072 | ICQ | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | Central | Non-WSIP | [6 empty] | '-122.11946 | 38.0256 | ETL.6370 | 40768258 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 8
115582245 | T3 EI FULTON-CALISTOGA :002/000 RMV STRW | 43749446 | FULTON-CALISTOGA | :002/000 | ICW | E | 2020_(1a) PSPS |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.585691 | 38.6206 | ETL.6880 | 40912423 | Structure-Wood | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-08-28
115584011 | T3 EI FULTON-CALISTOGA :002/005 RPL POLE | 31505615 | FULTON-CALISTOGA | :002/005 | 70Y | E | 2020_(1a) PSPS |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.59216 | 38.6281 | ETL.6880 | 40912428 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  | 2019-05-06
115584019 | T3 EI MONTE RIO-FORT ROSS 17/3 RPR PL | 43713924 | ETL.6979.POLE.WOOD | 017/003 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.056451 | 38.4782 | ETL.6979 | 40667838 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-07-19
115584138 | T2 EI BRIDGVILL-CTTNWD 32/265L RPL PL | 31455500 | BRIDGEVILLE-COTTONWOOD | 032/265 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Material & Equipment | Material unavailable | '-122.880879 | 40.365 | ETL.1110 | 44423882 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
115584319 | NEWARK-MILPITAS #1 004/033 RPLC INSS |  | DIXON LANDING-MCKEE | 004/033 | 93K | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | Central | Non-WSIP | [6 empty] | '-121.920375 | 37.4552 | ETL.1390 | 43242856 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Bay
115584409 | T2 EI SPAULDING-SUMMIT 000/017 RMV VEGN | 43760150 | SPAULDING-SUMMIT | 000/017 | ICW | E | Pre-2020_(1b) Lines with special commitments |  |  | Likely veg | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.638295 | 39.3231 | ETL.8060 | 40826222 | Structure-Wood | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Sacramento |  |  | Yes
115584503 | T2 EI DRUM-SPAULDING 008/217 RPL STRW | 31451875 | DRUM-SPAULDING | 008/217 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.649682 | 39.3171 | ETL.6770 | 40877168 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
115584572 | T2 EI SPLDN #3-SPLDN #1 000/012 REPL PL | 31445624 | SPAULDING #3-SPAULDING #1 | 000/012 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.642112 | 39.3319 | ETL.8050 | 40702888 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
115584583 | T2 EI SPLDNG #3-SPLDNG #1 00/014 REPL PL | 31445624 | SPAULDING #3-SPAULDING #1 | 000/014 | 70Y | E | Pre-2020_(2) High fire spread TD |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Access Issues | 2021 - Weather | '-120.641792 | 39.3329 | ETL.8050 | 40751875 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
115584798 | CASCADE-BENTON-DESCHTS 10/223 RPR JUMW | 43900811 | CASCADE-BENTON-DESCHUTES | 010/223 | ICW | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-122.379564 | 40.5631 | ETL.6310 | 40592280 | Jumper-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
115584844 | CASCADE-BENTON-DESCHUTES 010/224 REFRAME | 31460661 | CASCADE-BENTON-DESCHUTES | 010/224 | 93E | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-122.380627 | 40.5633 | ETL.6310 | 40600612 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  | Yes
115585107 | T3 EI FULTON-CALISTOGA -012/005 REPL PL | 31502249 | FULTON-CALISTOGA | '-012/005 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.521678 | 38.4069 | ETL.6880 | 40751129 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  | 2019-05-06
115586132 | T2 EI SPLDNG #3-SPLDNG #1 0/01A REPL PL | 31445624 | SPAULDING #3-SPAULDING #1 | 000/001A | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.644763 | 39.3248 | ETL.8050 | 40590201 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
115586357 | T2 COLGATE-PALERMO 013/272 RPL POLE | 31423185 | COLGATE-PALERMO | 013/272 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-121.410082 | 39.3925 | ETL.6500 | 41146789 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
115586521 | T2 EI COLGATE-PALERMO 014/289 RPL POLE | 31423185 | COLGATE-PALERMO | 014/289 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.416212 | 39.403 | ETL.6500 | 40824110 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
115587137 | T2 EI DRUM-SUMMIT #2 010/126 RPL POL | 31421446 | DRUM-SUMMIT #2 | 010/126 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.603803 | 39.3267 | ETL.1450 | 44558984 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
115587217 | T2 EI BVILLE-CTNWD 033/274 RPL PL | 31444708 | BRIDGEVILLE-COTTONWOOD | 033/274 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Material & Equipment | Material unavailable | '-122.9024672 | 40.3663 | ETL.1110 | 44424386 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
115587465 | T2 EI BRIDGVILL-CTTNWD 17/154L RPL PL | 31444708 | BRIDGEVILLE-COTTONWOOD | 017/154 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Material & Equipment | Material unavailable | '-122.583763 | 40.3819 | ETL.1110 | 44423379 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
115587587 | EI VALLEY SPRINGS #1 012/243 RPR STRW | 44290814 | VALLEY SPRINGS #1 | 012/243 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-120.921396 | 38.1031 | ETL.8210 | 40904218 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 23
115588445 | T2 EI COLGATE-PALERMO 018/358 RPL POLE | 31423185 | COLGATE-PALERMO | 018/358 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.444447 | 39.4453 | ETL.6500 | 40672083 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
115588500 | T2 EI MIDDLE FORK-GLD H 26/207R RPL PL | 31454603 | MIDDLE FORK-GOLD HILL | 026/207 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.945506 | 38.8126 | ETL.5140 | 44558315 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
115588620 | T2NT COLGATE-PALERMO 17/353 INST MRKW | 43878561 | COLGATE-PALERMO | 017/353 | ICW | F | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-121.441702 | 39.4426 | ETL.6500 | 40866833 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
115588646 | T2 EI BRDGVLE-CTTNWD 024/210L REPL PL | 31455500 | BRIDGEVILLE-COTTONWOOD | 024/210 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Material & Equipment | Material unavailable | '-122.72074 | 40.3723 | ETL.1110 | 44423242 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
115589065 | T2 EI DRUM-SUMMIT #2-9/114L RPL POLE | 31498154 | DRUM-SUMMIT #2 | 009/114 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.620933 | 39.3211 | ETL.1450 | 44553512 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS erdy | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
115589188 | T2 EI BRDGVILLE-CTNWD 023/207L RPL PL | 31444708 | BRIDGEVILLE-COTTONWOOD | 023/207 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Material & Equipment | Material unavailable | '-122.71398 | 40.3728 | ETL.1110 | 44424462 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
115589496 | T2 EI BVILLE-CTNWD 013/127C ANTI SPLIT | 43742050 | BRIDGEVILLE-COTTONWOOD | 013/127 | ICW | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.527714 | 40.3952 | ETL.1110 | 44424422 | Hardware-Wood | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
115589541 | T2 EI BVILLE-CTNWD 039/312 CANCEL | 43770771 | BRIDGEVILLE-COTTONWOOD | 039/312 | ICW | E | Pre-2020_(2) High fire spread TD |  |  | CANCEL/CNCL | TR2 | LATE | North Valley | WSIP |  |  |  |  | Clearance Denied by GCC | 2021 - Clearance conflicts w/ North Coast. |  |  | ETL.1110 | 44424595 | Ground Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
115589798 | T2 EI BRDGVLLE-CTNWD A041/332B REPL STRW | 31422962 | BRIDGEVILLE-COTTONWOOD | A041/332B | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Material & Equipment | Material unavailable | '-123.043825 | 40.3873 | ETL.1110 | 41198659 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
115589926 | T2 EI VALLEY SPRINGS #1 10/200 RPR INSW | 43830873 | VALLEY SPRINGS #1 | 010/200 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.888976 | 38.1166 | ETL.8210 | 40908285 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 23
115589927 | T2 EI HMLTN BRNCH-CHSTR 008/185 RPL STRW | 31439198 | HAMILTON BRANCH-CHESTER | 008/185 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.17314 | 40.3091 | ETL.7000 | 40758793 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  | Yes
115589928 | T2 EI KNCTI-MDLTOWN 012/003 RPR STRW | 43749609 | KONOCTI-MIDDLETOWN | 012/003 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.610385 | 38.7543 | ETL.6380 | 40666998 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-05-29
115589954 | T2 EI HMLTN BRNCH-CHSTR 009/197 RPL STRW | 31421720 | HAMILTON BRANCH-CHESTER | 009/197 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.183783 | 40.3128 | ETL.7000 | 40809579 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
115589966 | DISTRIBUTION |  | LIMESTONE TAP | 001/026 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.98146 | 38.6374 | ETL.6951 | 40875182 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLX | Contract | Expense | 630 | Sacramento
115589981 | T2 EI HMLTN BRNCH-CHSTR 007/163 RPL CRSW | 31433532 | HAMILTON BRANCH-CHESTER | 007/163 | 93E | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.154893 | 40.3037 | ETL.7000 | 40659934 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  | Yes
115589984 | T2 EI VALLEY SPRINGS #1 012/239 RPR POLE | 43831006 | VALLEY SPRINGS #1 | 012/239 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.918854 | 38.1049 | ETL.8210 | 40906501 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 23
115589985 | T2 EI VALLEY SPRINGS #1 12/238 RPL POLE | 31426054 | VALLEY SPRINGS #1 | 012/238 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.918388 | 38.1055 | ETL.8210 | 40906500 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 23
115589989 | EI VALLEY SPRINGS #1 12/242 RPR POLE | 43831011 | VALLEY SPRINGS #1 | 012/242 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-120.920581 | 38.1034 | ETL.8210 | 40904217 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 23
115590014 | T2 EI SPAULDING-SUMMIT 000/027 RPL PL | 31445623 | SPAULDING-SUMMIT | 000/027 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.632402 | 39.322 | ETL.8060 | 40809698 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
115590015 | EI VALLEY SPRINGS #1 012/241 RPR GYWW | 43831010 | VALLEY SPRINGS #1 | 012/241 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-120.919877 | 38.1037 | ETL.8210 | 40904216 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 23
115590072 | T2 EI HAMILTON BRANCH-CH 09/196 RPR POLE | 43879596 | HAMILTON BRANCH-CHESTER | 009/196 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.182692 | 40.3127 | ETL.7000 | 40827421 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
115590081 | T2 EI VALLEY SPRINGS #1 10/195 RPR POLE | 43830872 | VALLEY SPRINGS #1 | 010/195 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.885409 | 38.1181 | ETL.8210 | 40908280 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 23
115590082 | EI VALLEY SPRINGS #1 006/131 RPL STRW | 31426053 | VALLEY SPRINGS #1 | 006/131 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-120.853151 | 38.1552 | ETL.8210 | 40905594 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Not Released
115590095 | EI VALLEY SPRINGS #1 12/240 RPL POLE | 31426054 | VALLEY SPRINGS #1 | 012/240 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-120.919405 | 38.1042 | ETL.8210 | 40904215 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 23
115590110 | T2 EI KNCTI-MIDDLTWN 12/13 RPL GYWW | 43749609 | KONOCTI-MIDDLETOWN | 012/013 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.600755 | 38.7619 | ETL.6380 | 40650678 | Guy Wire-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-05-29
115590142 | T2 EI VALLEY SPRINGS #1 11/230 RPR POLE | 43831005 | VALLEY SPRINGS #1 | 011/230 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.912855 | 38.109 | ETL.8210 | 40908321 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 23
115590154 | EI VALLEY SPRINGS #1 05/100 RPR POLE | 43830786 | VALLEY SPRINGS #1 | 005/100 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-120.836587 | 38.1719 | ETL.8210 | 40905515 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 23
115590200 | EI VALLEY SPRINGS #1 11/221 RPR POLE | 43831013 | VALLEY SPRINGS #1 | 011/221 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-120.906023 | 38.1122 | ETL.8210 | 40908306 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 23
115590218 | EI VALLEY SPRINGS #1 011/218 RPR POLE | 44290815 | VALLEY SPRINGS #1 | 011/218 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-120.903569 | 38.113 | ETL.8210 | 40908303 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 23
115590224 | T2 EI SMARTVILLE-NIC #2 0/004 RPR SEAL |  | SMARTVILLE-NICOLAUS #2 | 000/004 | ICS | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.3028 | 39.2071 | ETL.8000 | 44177580 | Structure-Steel | Paint/Coating | Other |  |  |  |  | PEND | LC | TLX | Contract | Expense | 628 | Sacramento
115590232 | T2 EI BVILLE-CTNWD 015/143L RPL ANCH | 31456191 | BRIDGEVILLE-COTTONWOOD | 015/143 | 93E | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [8 empty] | ETL.1110 | 44232660 | Anchor-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Contract | Capital | 637 | Table Mountain |  |  | Yes
115590238 | T2 EI SMARTVILLE-NIC #2 0/005 RPR POLE | 43760147 | SMARTVILLE-NICOLAUS #2 | 000/005 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.30243 | 39.2064 | ETL.8000 | 40907130 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Sacramento
115590277 | T2 EI KONOCTI-MDDLTWN 013/000 RPL STRW | 31502250 | KONOCTI-MIDDLETOWN | 013/000 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.597631 | 38.7634 | ETL.6380 | 40615192 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  | 2019-04-04
115590288 | T2 EI VALLEY SPRINGS #1 009/184 RPR INSW | 43830869 | VALLEY SPRINGS #1 | 009/184 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.878384 | 38.1244 | ETL.8210 | 40908269 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 23
115590294 | T2 EI VALLEY SPRINGS #1 009/179 RPR INSW | 43830867 | VALLEY SPRINGS #1 | 009/179 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.875976 | 38.1272 | ETL.8210 | 40908264 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 23
115590332 | T2 EI KNCTI-MIDDLETWN 13/1 RPR INSW | 43749609 | KONOCTI-MIDDLETOWN | 013/001 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.595048 | 38.7643 | ETL.6380 | 40586656 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-04-04
115590410 | EI VALLEY SPRINGS #1 010/208 RPR GYWW | 43830877 | VALLEY SPRINGS #1 | 010/208 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-120.89528 | 38.1155 | ETL.8210 | 40908293 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog Multi
115590433 | T2 EI VALLEY SPRINGS #1 07/147 RPR POLE | 43830861 | VALLEY SPRINGS #1 | 007/147 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.860995 | 38.1462 | ETL.8210 | 40908230 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 23
115590438 | T2 EI KNCTI-MIDDLETWN ;23/7 RPR GYWW | 43749609 | KONOCTI-MIDDLETOWN | ;023/007 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.610015 | 38.8986 | ETL.6380 | 40810259 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-05-29
115590445 | EI VALLEY SPRINGS #1 10/203 RPL POLE | 31426054 | VALLEY SPRINGS #1 | 010/203 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-120.891032 | 38.1157 | ETL.8210 | 40908288 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 23
115590456 | T2 EI VALLEY SPRINGS #1 007/138 RPR STRW | 43830789 | VALLEY SPRINGS #1 | 007/138 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.85734 | 38.1514 | ETL.8210 | 40905601 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 23
115590461 | T2 EI KNCTI-MDLTOWN ;023/008 RPR GYWW | 43749609 | KONOCTI-MIDDLETOWN | ;023/008 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.610737 | 38.8993 | ETL.6380 | 40876736 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-05-29
115590487 | T2 EI VALLEY SPRINGS #1 007/141 RPR GYWW | 43830860 | VALLEY SPRINGS #1 | 007/141 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.858584 | 38.1497 | ETL.8210 | 40905604 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 23
115590501 | T2 EI COLEMAN-SOUTH NONCERAM 012/263 VEG |  | COLEMAN-SOUTH | 012/263 | HNA | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.10883 | 40.4037 | ETL.6450 | 40826891 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Table Mountain |  |  | Yes
115590524 | T2 EI KONOCTI-MIDDLETOWN ;024/001 RPR IN | 43749609 | KONOCTI-MIDDLETOWN | ;024/001 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.614959 | 38.9036 | ETL.6380 | 40586670 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-05-29
115590525 | T2 EI VALLEY SPRINGS #1 004/088 RPL STRW | 31425843 | VALLEY SPRINGS #1 | 004/088 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP |  |  |  |  | Access Issues | No access /land owner | '-120.830887 | 38.1786 | ETL.8210 | 40903818 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - FF
115590942 | T2 Cottonwood Glenn 066/587 INSS NG REPL | 31423197 | COTTONWOOD-GLENN | 066/587 | 93K | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-122.267917 | 40.3007 | ETL.4560 | 40846323 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  | Yes
115591518 | GUARDIAN #1 TAP 000/015 RPLC POLE | 31419918 | GUARDIAN #1 TAP | 000/015 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.581892 | 36.5406 | ETL.2301 | 40759927 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno
115593220 | GUARDIAN #2 TAP 000/003 pole replacement | 31419917 | GUARDIAN #2 TAP | 000/003 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.581756 | 36.5406 | ETL.2292 | 40656494 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno
115596051 | EI VALLEY SPRINGS #1 002/034 RPR STRW | 43830784 | VALLEY SPRINGS #1 | 002/034 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-120.791471 | 38.2048 | ETL.8210 | 40905861 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 23
115596607 | T2 EI CLEMAN-CTTNWD 0/08 RPR PL | 43743036 | COLEMAN-COTTONWOOD | 000/008 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.126777 | 40.406 | ETL.6430 | 40825004 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain
115596631 | T2NT EI CLEMAN-CTTNWD 0/08 INS MRKW | 43743036 | COLEMAN-COTTONWOOD | 000/008 | ICW | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.126777 | 40.406 | ETL.6430 | 40825004 | Marker (i.e. signs)-Wood | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain
115596672 | T2 EI VALLEY SPRINGS #1 04/079 RPL POLE | 31426053 | VALLEY SPRINGS #1 | 004/079 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.825687 | 38.1839 | ETL.8210 | 40903840 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Not Released | CalTrans
115596714 | EI CLEMAN-CTTNWD 0/11 RPR PL | 43743036 | COLEMAN-COTTONWOOD | 000/011 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-122.129304 | 40.4065 | ETL.6430 | 40598761 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain
115596739 | T2 EI VALLEY SPRINGS #1 003/070 RPL STRW | 31425843 | VALLEY SPRINGS #1 | 003/070 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP |  |  |  |  | Access Issues | No access /land owner | '-120.819703 | 38.1896 | ETL.8210 | 40903831 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - FF
115596761 | T2 EI SPAULDING-SUMMIT 1/042 RPL CRSW | 31415019 | SPAULDING-SUMMIT | 001/042 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.6257 | 39.3196 | ETL.8060 | 44420792 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Pole Program | Capital | 637 | Sacramento |  |  | Yes
115596872 | T2 EI CLMN-CTTNWD 000/013B RPR STRW | 43743036 | COLEMAN-COTTONWOOD | 000/013B | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-122.131036 | 40.4068 | ETL.6430 | 42578763 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain
115596985 | EI CLMN-CTTNWD 001/019 RPR STRW | 43743036 | COLEMAN-COTTONWOOD | 001/019 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-122.140996 | 40.4091 | ETL.6430 | 40594912 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain
115597090 | T3 EI KILARC-CEDAR C 006/142 RPR INSW | 43724327 | KILARC-CEDAR CREEK | 006/142 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.983317 | 40.7118 | ETL.7290 | 40759573 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
115597091 | T3 EI KILARC-CEDAR C 006/146 RPR INSW | 43724327 | KILARC-CEDAR CREEK | 006/146 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.985897 | 40.7125 | ETL.7290 | 40868735 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
115597799 | T3 EI MIDDLE FORK-GOLD HILL 9/79L RPL PL | 31454603 | MIDDLE FORK-GOLD HILL | 009/079 | 70Y | E | Pre-2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP |  |  |  |  | Material & Equipment | 2021 - Due to Long lead material delay | '-120.738363 | 38.9879 | ETL.5140 | 44553749 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
115597838 | EI COLEMAN-COTTONWOOD 002/056 RPR STRW | 43743036 | COLEMAN-COTTONWOOD | 002/056 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-122.173568 | 40.4155 | ETL.6430 | 40809542 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain
115597872 | T2 EI VALLEY SPRINGS #1 001/019 RPR STRW | 43830781 | VALLEY SPRINGS #1 | 001/019 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.776724 | 38.207 | ETL.8210 | 40908569 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 23
115599077 | T2 EI VOLTA-DESCHUTES 009/208 RMV VEGN |  | VOLTA-DESCHUTES | 009/208 | HNA | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.045267 | 40.5028 | ETL.8290 | 40877091 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Table Mountain
115599658 | T2 EI EL DRAD-MISRI FLAT #1 09/75 RPL PL | 31456633 | ELDORADO-MISSOURI FLAT #1 | 009/075 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.770789 | 38.7471 | ETL.1530 | 40764844 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
115599733 | T2 EI APPLE HILL #2 TAP 000/002 INS GYWW | 43740228 | APPLE HILL #2 TAP | 000/002 | ICW | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.683089 | 38.7579 | ETL.1541 | 40683627 | Guy Wire-Wood | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Sacramento |  |  | Yes
115599775 | EI DORADO-MSSRI FLAT#1 09/74 RPL STRW | 31456633 | ELDORADO-MISSOURI FLAT #1 | 009/074 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-120.770053 | 38.7477 | ETL.1530 | 40762138 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
115599778 | T2 EL DRAD-MISSRI FLAT #1 9/76 RPR INSW | 43748116 | ELDORADO-MISSOURI FLAT #1 | 009/076 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.771565 | 38.7464 | ETL.1530 | 40818661 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Sacramento |  |  | Yes
115599820 | T2 EI VALLEY SPRINGS #1 A1/023 RPL SPLW | 43831612 | VALLEY SPRINGS #1 | A001/023 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.746632 | 38.2066 | ETL.8210 | 40907082 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 23
115599876 | T2 EI APPLE HILL #1 TAP 0/03 RMV VEG |  | APPLE HILL #1 TAP | 000/003 | HNA | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-120.683236 | 38.7574 | ETL.1531 | 40654850 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  | Yes
115599932 | T2 EI COLEMAN-SOUTH 000/002 RMV VEGN |  | COLEMAN-SOUTH | 000/002 | HNA | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.879032 | 40.3957 | ETL.6450 | 40740387 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Table Mountain
115600080 | T2 EI COLEMAN-SOUTH 011/228 RPR GYWW | 43743540 | COLEMAN-SOUTH | 011/228 | ICW | E | Pre-2020_(2) High fire spread TD |  |  |  | TR2 | LATE | North Valley | WSIP | [5 empty] | 2021: FSR 12/2020 | '-122.075924 | 40.4036 | ETL.6450 | 40677122 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
115600121 | T2 EI VALLEY SPRINGS #1 A2/053 RPL POLE | 31425598 | VALLEY SPRINGS #1 | A002/053 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.723369 | 38.1992 | ETL.8210 | 40907108 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Victor |  | Y - 23
115600184 | T2 EI CLAY-MARTEL 025/349 REPL STRW | 31422461 | CLAY-MARTEL | 025/349 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.80962 | 38.3606 | ETL.8250 | 40873176 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 33
115600234 | T2 EI VALLEY SPRINGS #1 A2/055 RPL POLE | 31426055 | VALLEY SPRINGS #1 | A002/055 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.722136 | 38.1989 | ETL.8210 | 40907109 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 23 | BLM
115600629 | T2NT EI EL DRD-MISRI FT #1 10/88 STR PNT | 44585955 | ELDORADO-MISSOURI FLAT #1 | 010/088 | ICS | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-120.781625 | 38.7361 | ETL.1530 | 40862228 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes
115600687 | T2 EI VALLY SPRNGS-MRTLL#1 10/015 RPL PL | 31421728 | VALLEY SPRINGS-MARTELL #1 | 010/015 | 70Y | E | 2020_(1a) PSPS |  |  |  | TR2 | LATE | Central | WSIP |  |  |  |  | Access Issues | land owner | '-120.784316 | 38.3452 | ETL.8240 | 40758344 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 19
115600709 | T2 EI DORADO-MISSRI FLT#1 10/89 PNT STR | 44585955 | ELDORADO-MISSOURI FLAT #1 | 010/089 | ICS | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-120.782118 | 38.735 | ETL.1530 | 40861985 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes
115600737 | T2NT EI EL DRD-MISRI FLT #1 10/90 PNT ST | 44585955 | ELDORADO-MISSOURI FLAT #1 | 010/090 | ICS | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-120.782491 | 38.7343 | ETL.1530 | 40580975 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes
115600750 | T2 EI APPLE HILL #2 TAP 000/011 RPL PL | 31423866 | APPLE HILL #2 TAP | 000/011 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.683081 | 38.7521 | ETL.1541 | 40590196 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
115600754 | T2 EI VLY SPRNGS-MRTL#1 011/006 RPR STRW | 43740949 | VALLEY SPRINGS-MARTELL #1 | 011/006 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.785554 | 38.3523 | ETL.8240 | 40816463 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog Multi
115600759 | T2 EI VALLEY SPRINGS #1 A1/029 RPL POLE | 31469597 | VALLEY SPRINGS #1 | A001/029 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.741868 | 38.2053 | ETL.8210 | 40907086 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Victor |  | Y - 23
115600863 | T3 EI GOLD HILL #1 024/361 RPL CRSW | 31429371 | GOLD HILL #1 | 024/361 | 93E | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.849102 | 38.5823 | ETL.6950 | 44174895 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 637 | Sacramento |  |  | Yes
115601183 | T2 EI VLY SPRNGS-MRTL#1 010/014 RPL CNDW | 31489036 | VALLEY SPRINGS-MARTELL #1 | 010/014 | 93C | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.783152 | 38.3432 | ETL.8240 | 40768889 | Conductor-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 638 | Victor |  | Y - 24
115601223 | T2 EI VLY SPRGS-MRTL #1 007/004 INS MRKW | 43740949 | VALLEY SPRINGS-MARTELL #1 | 007/004 | ICW | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.758242 | 38.2948 | ETL.8240 | 40768887 | Hardware-Wood | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog Multi
115601322 | T2 EI VOLTA-SOUTH 001/038 RMV VEGN |  | VOLTA-SOUTH | 001/038 | HNA | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.872598 | 40.4377 | ETL.8300 | 40759554 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Table Mountain
115601366 | T2 EI VLY SPRNGS-MRTL#1 009/015 RPR SPLW | 43740949 | VALLEY SPRINGS-MARTELL #1 | 009/015 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.775398 | 38.3284 | ETL.8240 | 40753644 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 24
115601375 | T2 EI CARIBOU-PALERMO 006/059 REPL INSS | 31426491 | CARIBOU-PALERMO | 006/059 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.536845 | 39.5515 | ETL.3190 | 40867352 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC hold |  |  |  | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain
115601404 | T2 DI CARIBOU-PALERMO 007/061 RPL HRDT | 43659205 | CARIBOU-PALERMO | 007/061 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.536011 | 39.5542 | ETL.3190 | 40591546 | Hardware-Steel | No Good/Out of Stdrd | Replace | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain
115602042 | T2 EI CARIBOU-PALERMO 007/062 RPL INSS | 31426587 | CARIBOU-PALERMO | 007/062 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.535336 | 39.5565 | ETL.3190 | 40674915 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC hold |  |  |  | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain
115604728 | T2 EI VALLEY SPRINGS #2 10/183 RPL GYWW | 43843583 | VALLEY SPRINGS #2 | 010/183 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.893785 | 38.1384 | ETL.9460 | 40907512 | Guy Wire-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog Multi
115605818 | EI COLGATE-GRASS VALLEY 010/249 RPL CRSW | 31423183 | COLGATE-GRASS VALLEY | 010/249 | 93E | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-121.079193 | 39.2283 | ETL.6490 | 40823565 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 637 | Sacramento |  |  | Yes
115605839 | T2 EI VOLTA-DESCHUTES 019/433 RPL POLE | 31426666 | VOLTA-DESCHUTES | 019/433 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.218462 | 40.5501 | ETL.8290 | 40817193 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
115605845 | T2 EI VOLTA-DESCHUTES 019/439 RPL SPLW | 43736446 | VOLTA-DESCHUTES | 019/439 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.223502 | 40.5511 | ETL.8290 | 40676454 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
115605855 | T2 EI VLY SPRGS-MRTL #1 003/017 RPL STRW | 31422462 | VALLEY SPRINGS-MARTELL #1 | 003/017 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.773129 | 38.2544 | ETL.8240 | 40805165 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - Prog Multi
115606124 | T3 EI GOLD HILL #1 022/333 RPR POLE | 43708673 | GOLD HILL #1 | 022/333 | ICW | E | Pre-2020_(9a) Other ignition related |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.843256 | 38.6166 | ETL.6950 | 40768214 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Sacramento |  |  | Yes
115606198 | T3 EI KONOCTI-EGL RCK 003/000 ISTL GYWW | 43685216 | KONOCTI-EAGLE ROCK | 003/000 | ICW | E | Pre-2020_(9a) Other ignition related |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.78634 | 38.8575 | ETL.6861 | 40588400 | Guy Wire-Wood | Missing | Install | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-03-18
115607779 | T2NT EI APPLE HILL #2 TAP 0/9 RMV DEBRIS | 43740228 | APPLE HILL #2 TAP | 000/009 | ICW | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.683092 | 38.7533 | ETL.1541 | 40865547 | Structure-Wood | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Sacramento |  |  | Yes
115608069 | T2 EI APPLE HILL #2 TAP 001/028 INS GYWW | 43740228 | APPLE HILL #2 TAP | 001/028 | ICW | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.679582 | 38.7426 | ETL.1541 | 40762386 | Guy Wire-Wood | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Sacramento |  |  | Yes
115608263 | EI COLLINS PINE TAP 000/005 REPL SPLW | 43743558 | COLLINS PINE TAP | 000/005 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-121.228734 | 40.3014 | ETL.7001 | 42623453 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain
115608496 | T2NT EI VLTA-DESCHUTES 14/309 INST MRKW | 43736446 | VOLTA-DESCHUTES | 014/309 | ICW | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.13041 | 40.5274 | ETL.8290 | 40656937 | Marker (i.e. signs)-Wood | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
115608652 | T2 EI IONE TAP 002/013 RPR WDPCKR HOLE | 43844195 | IONE TAP | 002/013 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.93719 | 38.3764 | ETL.8253 | 40643631 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 9
115608674 | T2 EI VOLTA-DESCHUTES 017/370 RMV VEGN |  | VOLTA-DESCHUTES | 017/370 | HNA | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.173695 | 40.5407 | ETL.8290 | 40656945 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Table Mountain |  |  | Yes
115608717 | T2 EI IONE TAP 002/014 REPL PL | 31425589 | IONE TAP | 002/014 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.938225 | 38.3768 | ETL.8253 | 40745291 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 9
115608756 | T2 EI VOLTA-DESCHUTES 015/330 RPL POLE | 31426666 | VOLTA-DESCHUTES | 015/330 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.14795 | 40.534 | ETL.8290 | 40667449 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
115608779 | T2 EI IONE TAP 002/015 STRW | 43844195 | IONE TAP | 002/015 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.939235 | 38.3772 | ETL.8253 | 40745290 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 9
115608878 | T2 EI WEIMAR-HALSEY-5/133 REPLACE POLE | 31454601 | WEIMAR-HALSEY | 005/133 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.040222 | 38.9598 | ETL.8340 | 40674277 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento
115609078 | T2 EI PINE GROVE TAP 001/041 RPR GYWW | 43691348 | PINE GROVE TAP | 001/041 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.651834 | 38.4072 | ETL.8351 | 40864228 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 3
115609081 | T2 EI WEIMAR-HALSEY-5/136 REPLACE POLE | 31454601 | WEIMAR-HALSEY | 005/136 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.041672 | 38.9583 | ETL.8340 | 40758135 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento
115609100 | T2 EI PINE GROVE TAP 1/38 RPR GYWW | 43691348 | PINE GROVE TAP | 001/038 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.650316 | 38.4067 | ETL.8351 | 40754201 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 3
115609134 | T2 EI KILARC-DESCHUTES 000/021 RPL CRSW | 31498148 | KILARC-DESCHUTES | 000/021 | 93E | E | 2020_(1a) PSPS |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.875629 | 40.664 | ETL.7300 | 40701770 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 637 | Table Mountain |  |  | Yes
115609137 | T3 EI KONOCTI-EAGLE RCK 003/11 INST GYWW | 43685216 | KONOCTI-EAGLE ROCK | 003/011 | ICW | E | Pre-2020_(9a) Other ignition related |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.788183 | 38.8691 | ETL.6861 | 40585197 | Guy Wire-Wood | Missing | Install | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-03-18
115609139 | T3 EI KNCTI-EAGL RCK 3/012 ISTL GYWW | 43685216 | KONOCTI-EAGLE ROCK | 003/012 | ICW | E | Pre-2020_(9a) Other ignition related |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.788235 | 38.8706 | ETL.6861 | 40698955 | Guy Wire-Wood | Missing | Install | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-03-18
115609483 | T2 EI WEIMAR-HALSEY 005/124 RPL STRW | 31517752 | WEIMAR-HALSEY | 005/124 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.036378 | 38.9638 | ETL.8340 | 40656025 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
115609544 | T2 EI COLGATE-PALERMO-3/51 RPL POLE | 31506819 | COLGATE-PALERMO | 003/051 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  | REJECT: Could not complete work due to Scope Change Required. No work to verify. |  |  | '-121.246833 | 39.3217 | ETL.6500 | 40692947 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
115609559 | T2 EI WEIMAR-HALSEY 005/125 RPL PL | 31454601 | WEIMAR-HALSEY | 005/125 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.03657 | 38.9636 | ETL.8340 | 40767370 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
115609646 | T2 EI WEIMAR-HALSEY 005/128 RPL PL | 31454601 | WEIMAR-HALSEY | 005/128 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.038275 | 38.9619 | ETL.8340 | 40822758 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
115609650 | T2 EI WEIMAR-HALSEY 005/129 RPL PL | 31454601 | WEIMAR-HALSEY | 005/129 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.038527 | 38.9615 | ETL.8340 | 40874760 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
115609687 | T2 EI KESWICK-CASCADE-3/75 REMV BRUSH |  | KESWICK-CASCADE | 003/075 | HNA | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.37536 | 40.6614 | ETL.7260 | 40601921 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Table Mountain |  |  | Yes
115609694 | T2 EI SMARTVILLE-NIC #1 01/028 RMV VEGN |  | SMARTVILLE-NICOLAUS #1 | 001/028 | HNA | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.307287 | 39.1911 | ETL.7990 | 40908933 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento
115609697 | T2 EI CLR LK-KNCTI 021/006 RPR INSW | 43749310 | CLEAR LAKE-KONOCTI | 021/006 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.752875 | 38.9373 | ETL.6852 | 40826574 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-04-25
115609733 | T2 EI KESWICK-CASCADE 005/098 RMV VEGN |  | KESWICK-CASCADE | 005/098 | HNA | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.396911 | 40.6489 | ETL.7260 | 40770316 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Table Mountain |  |  | Yes
115609968 | T2 EI KESWICK-CASCADE 005/109 VEG | 43726760 | KESWICK-CASCADE | 005/109 | ICW | E | Pre-2020_(9a) Other ignition related |  |  | Likely veg | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.402665 | 40.6445 | ETL.7260 | 44811123 | Structure-Wood | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
115610063 | T2 EI WEIMAR-HALSEY 005/120 RPL PL | 31517752 | WEIMAR-HALSEY | 005/120 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.033478 | 38.9667 | ETL.8340 | 40767389 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
115610112 | T2 EI SMARTVILL-NICO #2 002/043 RPL INSW | 31451776 | SMARTVILLE-NICOLAUS #2 | 002/043 | 93K | E | Pre-2020_(5) TD tag on other lines |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.3071826 | 39.1807 | ETL.8000 | 44179489 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Sacramento
115610113 | T2 EI CLAY-MARTEL 32/485 RPR POLE | 31430278 | CLAY-MARTEL | 032/485 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.84033 | 38.4539 | ETL.8250 | 40904103 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 33
115610197 | T2 EI KESWICK-CASCADE 005/107 RMV VEGN |  | KESWICK-CASCADE | 005/107 | HNA | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.401822 | 40.6451 | ETL.7260 | 42671336 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Table Mountain |  |  | Yes
115610275 | T2 EI WEIMAR-HALSEY 002/048 RPL STRW | 31517752 | WEIMAR-HALSEY | 002/048 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.000504 | 39.0043 | ETL.8340 | 40874846 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
115610278 | T2 EI CLAY-MARTEL 32/496 REPL POLE | 31430278 | CLAY-MARTEL | 032/496 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.844423 | 38.4635 | ETL.8250 | 40912855 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 34
115610303 | T2 EI WEIMAR-HALSEY 004/108 RPR STRW | 44365514 | WEIMAR-HALSEY | 004/108 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.028822 | 38.9717 | ETL.8340 | 40693590 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 630 | Sacramento
115610332 | T2 EI CLAY-MARTEL 33/498 RPR POLE | 43792833 | CLAY-MARTEL | 033/498 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.844726 | 38.465 | ETL.8250 | 40912853 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 33
115610370 | T2 EI WEIMAR-HALSEY 004/103 RPL STRW | 31498142 | WEIMAR-HALSEY | 004/103 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.027144 | 38.9733 | ETL.8340 | 40810010 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento
115617911 | T3 EI KONOCTI-EAGLE RCK 004/009 RPR GYWW | 43685216 | KONOCTI-EAGLE ROCK | 004/009 | ICW | E | Pre-2020_(9a) Other ignition related |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.787713 | 38.878 | ETL.6861 | 40861216 | Guy Wire-Wood | Missing | Install | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-03-18
115618245 | T2 EI CLAY-MARTEL 33/501 RPR POLE | 43793200 | CLAY-MARTEL | 033/501 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.845314 | 38.4677 | ETL.8250 | 40912850 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 33
115618603 | T2 EI MTN GATE JCT-CSCADE 006/075 RPL PL | 31472704 | MTN GATE JCT-CASCADE | 006/075 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.335583 | 40.6533 | ETL.7640 | 40826105 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain
115618610 | T2 EI HALSEY-PLACER 000/006 RPL POLE | 31506123 | HALSEY-PLACER | 000/006 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.044931 | 38.9549 | ETL.6990 | 40598705 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
115618768 | T2 EI MTN GATE JCT-CSCDE 6/71 RPR POLE | 43758388 | MTN GATE JCT-CASCADE | 006/071 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.335557 | 40.6577 | ETL.7640 | 40668597 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain
115618805 | T2 EI CSCAD-BNTN-DSCHUTES 1/34 RPL PL | 31427801 | CASCADE-BENTON-DESCHUTES | 001/034 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.328658 | 40.632 | ETL.6310 | 40759460 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
115618815 | T2 EI CRBOU-PLMS JCT 014/007A RPR JMPW | 43640453 | CARIBOU-PLUMAS JCT | 014/007A | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.953736 | 39.9571 | ETL.6290 | 42601243 | Jumper-Wood | No Good/Out of Stdrd | Repair | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
115618816 | T2 EI CRBOU-PLMS JCT 014/007A RPR GYWW | 43640453 | CARIBOU-PLUMAS JCT | 014/007A | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.953736 | 39.9571 | ETL.6290 | 42601243 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
115618890 | T3 EI COLGATE-CHALLENGE 02/042 RPL POLE | 31475095 | COLGATE-CHALLENGE | 002/042 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.176289 | 39.3546 | ETL.6480 | 40594209 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento
115618891 | T3 EI COLGATE-CHALLENGE 2/043 REPL POLE | 31428954 | COLGATE-CHALLENGE | 002/043 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.17581 | 39.355 | ETL.6480 | 40590456 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
115619043 | T2NT EI FORT ROSS-GUALALA 44/4 RPR INSW | 43714574 | GUALALA-MONTE RIO | 044/004 | ICD | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.323228 | 38.6974 | ETL.6980 | 40750348 | Insulator | Contaminated | Ground Wash | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 622 | Lakeville |  |  | 2019-04-30
115619048 | EI HALSEY-PLACER 000/010 RPL POLE | 31517753 | HALSEY-PLACER | 000/010 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-121.047915 | 38.9517 | ETL.6990 | 40656028 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento
115619088 | T2 EI CASCADE-BNTN-DSCHTS 0/20 REPL PL | 31427801 | CASCADE-BENTON-DESCHUTES | 000/020 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.333157 | 40.6418 | ETL.6310 | 40759462 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain
115619089 | T2 EI MTN GATE JCT-CASC 04/047 RPL POLE | 31498057 | MTN GATE JCT-CASCADE | 004/047 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.32865 | 40.6823 | ETL.7640 | 40876601 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain
115619094 | T2 EI CASCADE-BNTN-DSCHTS 0/016 REPL PL | 31427801 | CASCADE-BENTON-DESCHUTES | 000/016 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.334906 | 40.6454 | ETL.6310 | 40868659 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
115619157 | T2 RND MT-TBL MT #2 055/236 CANCEL | 43621090 | ROUND MTN-TABLE MTN #2 | 055/236 | ICS | E | Pre-2020_(2) High fire spread TD |  |  | CANCEL/CNCL | TR2 | LATE | North Valley | Non-WSIP |  |  |  |  | Clearance Cancelled by GCC | 2021 - Cancelled by ISO | '-121.866989 | 40.013 | ETL.6070 | 40820562 | Jumper-Steel | No Good/Out of Stdrd | Repair | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
115619189 | T2 RND MT-TBLE MT#2 56/240 INST DAMS | 43740168 | ROUND MTN-TABLE MTN #2 | 056/240 | ICS | E | Pre-2020_(3) On high spread structure |  |  |  | TR2 | LATE | North Valley | Non-WSIP |  |  |  |  | Clearance Cancelled by GCC | 2021 - Cancelled by ISO | '-121.860403 | 39.9978 | ETL.6070 | 40635089 | Damper-Steel | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
115619314 | T2 EI HALSEY-PLACER 000/011 REFRAME | 31462290 | HALSEY-PLACER | 000/011 | 93E | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.048355 | 38.9513 | ETL.6990 | 40767376 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Sacramento |  |  | Yes
115619488 | EI HALSEY-PLACER 003/075 RFRM PL | 31462290 | HALSEY-PLACER | 003/075 | 93E | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-121.072356 | 38.9144 | ETL.6990 | 40611383 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 637 | Sacramento |  |  | Yes
115619614 | T3 EI COLGATE-CHALLENGE 1/031 RPR POLE | 43687147 | COLGATE-CHALLENGE | 001/031 | ICW | E | 2020_(1a) PSPS |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.184353 | 39.3483 | ETL.6480 | 40874645 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Sacramento
115619700 | T2 EI CRBOU-PLMS JCT 015/015 CLN INSS | 43729366 | CARIBOU-PLUMAS JCT | 015/015 | ICD | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-120.927219 | 39.9542 | ETL.6290 | 44163158 | Insulator | Contaminated | Ground Wash | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 622 | Table Mountain |  |  | Yes
115619800 | T2 EI PIT #7 TAP 2/24 CENT RPR GYWW | 43877044 | PIT #7 TAP | 002/024 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.94041 | 40.8282 | ETL.5442 | 44553692 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain
115619866 | T2 EI PIT #7 TAP 2/24L RPL POLE | 31432828 | PIT #7 TAP | 002/024 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.94041 | 40.8282 | ETL.5442 | 44553693 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain
115619893 | T2 EI CSCD-BNTN-DSCHTS 001/044 RPR CRSW | 43690811 | CASCADE-BENTON-DESCHUTES | 001/044 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.326293 | 40.6262 | ETL.6310 | 40759296 | Crossarm-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
115619963 | EI HALSEY-PLACER 003/077 REPL POLE | 31404619 | HALSEY-PLACER | 003/077 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-121.073228 | 38.914 | ETL.6990 | 40674286 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento
115619983 | T2 EI HALSEY-PLACER 000/015 RPR POLE | 43740262 | HALSEY-PLACER | 000/015 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.050654 | 38.9488 | ETL.6990 | 44235941 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Sacramento |  |  | Yes
115619984 | T2 EI WEIMAR-HALSEY 004/086 RPR GYWW | 44365514 | WEIMAR-HALSEY | 004/086 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.019082 | 38.9819 | ETL.8340 | 40591268 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 630 | Sacramento |  |  | Yes
115620037 | T2 EI PIT #7 TAP 003/025 RPR GYWW | 43877044 | PIT #7 TAP | 003/025 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.939086 | 40.827 | ETL.5442 | 44553738 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain
115620322 | T2 EI HALSEY-PLACER 000/016 RPR ANCW | 43852441 | HALSEY-PLACER | 000/016 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.051259 | 38.9482 | ETL.6990 | 40873793 | Anchor-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
115620435 | T2 EI HALSEY-PLACER 000/018 RPR POLE | 43740262 | HALSEY-PLACER | 000/018 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.052439 | 38.947 | ETL.6990 | 40591274 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Sacramento |  |  | Yes
115620569 | T2 EI VALLEY SPRINGS-C 5/083 RPR GYWW | 43712664 | VALLEY SPRINGS-CLAY | 005/083 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.831632 | 38.2054 | ETL.8264 | 40905032 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog Multi
115620662 | T2 EI VALLEY SPRINGS-CL 5/081 RPL SPLW | 43712664 | VALLEY SPRINGS-CLAY | 005/081 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.831266 | 38.2045 | ETL.8264 | 40904718 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog Multi
115620689 | T2 EI WEIMAR-HALSEY 04/085 REPL POLE | 31498143 | WEIMAR-HALSEY | 004/085 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.018473 | 38.9825 | ETL.8340 | 40611380 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
115621304 | T2 EI CRBOU-PLMS JCT 015/000 RPR INSW | 43640453 | CARIBOU-PLUMAS JCT | 015/000 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.942611 | 39.9571 | ETL.6290 | 40614959 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
115621336 | T2 EI CRBOU-PLMS JCT 015/007 RPR GYWW | 43640453 | CARIBOU-PLUMAS JCT | 015/007 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.934872 | 39.9571 | ETL.6290 | 40824657 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
115621811 | T3 EI COLGATE-CHALLENGE 01/024 REPL STRW | 31428954 | COLGATE-CHALLENGE | 001/024 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.188812 | 39.3449 | ETL.6480 | 40590453 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
115621857 | EI HALSEY-PLACER 001/022 RPL PL | 31404619 | HALSEY-PLACER | 001/022 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-121.055862 | 38.9433 | ETL.6990 | 40758139 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
115621940 | T2 EI CASCADE-BENTN-DES 002/054 RPL HRDW | 43690811 | CASCADE-BENTON-DESCHUTES | 002/054 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.3233 | 40.6215 | ETL.6310 | 40657147 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
115622030 | T2 EI CASCADE-BENTN-DES 002/054 RPL SPLW | 43690811 | CASCADE-BENTON-DESCHUTES | 002/054 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.3233 | 40.6215 | ETL.6310 | 40657147 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
115622034 | T2 EI VLY SPRNGS-CLY 009/127 REPL SPLW | 43712679 | VALLEY SPRINGS-CLAY | 009/127 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.850963 | 38.2553 | ETL.8264 | 40904754 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Released
115622035 | T2 EI VLY SPRNGS-CLY 009/127 RPR GYWW | 43687883 | VALLEY SPRINGS-CLAY | 009/127 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.850963 | 38.2553 | ETL.8264 | 40904754 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 15
115624626 | T2 EI PIT #7 TAP 002/019 RPR GYWW | 43877044 | PIT #7 TAP | 002/019 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.9531 | 40.8316 | ETL.5442 | 44553524 | Ground Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain
115628880 | EI CLAY-MARTEL 25/350 RPL POLE | 31422461 | CLAY-MARTEL | 025/350 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-120.809587 | 38.3609 | ETL.8250 | 40864589 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 33
115630096 | T2 EI VLY SPRNGS-CLY 009/126 REPL SPLW | 43712679 | VALLEY SPRINGS-CLAY | 009/126 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.850981 | 38.2519 | ETL.8264 | 40904753 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 12
115630488 | T2 EI VLY SPRNGS-CLY 011/156 RPR STRW | 43712679 | VALLEY SPRINGS-CLAY | 011/156 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.882948 | 38.274 | ETL.8264 | 40904771 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 12
115630489 | T2 EI VALLY SPRNGS-CLAY 11/155 RPLC INSL | 31425636 | VALLEY SPRINGS-CLAY | 011/155 | 93I | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.8821551 | 38.2735 | ETL.8264 | 40921416 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Victor |  | Y - Prog Multi
115632110 | T2 EI EGL RCK-CRTN :014/018 RPR INSW | 43730688 | EAGLE ROCK-CORTINA | :014/018 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.609317 | 38.936 | ETL.1470 | 41176321 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-05-20
115632113 | T2 EI VLY SPRNGS-CLY 009/126 RPR GUY | 43712679 | VALLEY SPRINGS-CLAY | 009/126 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.850981 | 38.2519 | ETL.8264 | 40904753 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 12
115633910 | T2 EI VLY SPRNGS-CLY 011/155 RPR POLE | 43712679 | VALLEY SPRINGS-CLAY | 011/155 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.882142 | 38.2735 | ETL.8264 | 40911610 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 12
115633918 | T2 EI EAGLE ROCK-CORTINA :14/19 RPR GYWW | 43730688 | EAGLE ROCK-CORTINA | :014/019 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.609304 | 38.9365 | ETL.1470 | 41176322 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-05-20
115634025 | T2 EI EAGLE ROCK-COR :17/017 RPR GYWW | 43730688 | EAGLE ROCK-CORTINA | :017/017 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.61258 | 38.9795 | ETL.1470 | 41176381 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-08-06
115636953 | T2 EI FORT ROSS-GUAL 054/000 RPL STRW | 31462486 | GUALALA-MONTE RIO | 054/000 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.473967 | 38.7351 | ETL.6980 | 40587401 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  | 2019-04-30
115636969 | T2 EI VLY SPRNGS-CLY 009/125 RPR GYWW | 43687883 | VALLEY SPRINGS-CLAY | 009/125 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.850969 | 38.2495 | ETL.8264 | 40904752 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 12
115637000 | T2 EI EAGLE RK-CORTINA :14/20 RPR GYWW | 43730688 | EAGLE ROCK-CORTINA | :014/020 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.609255 | 38.9368 | ETL.1470 | 41176323 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-05-20
115637003 | T2 EI EAGLE ROCK-CORT :012/003 RPL HRDW | 43730688 | EAGLE ROCK-CORTINA | :012/003 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.618203 | 38.9133 | ETL.1470 | 41176415 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-08-06
115637028 | T2 EI FORT ROSS-GUALALA 49/008 RPL ANCH | 31430306 | GUALALA-MONTE RIO | 049/008 | 93E | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.400986 | 38.7214 | ETL.6980 | 40860968 | Anchor-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 637 | Lakeville |  |  | 2019-04-30
115637029 | T2 EI VLY SPRNGS-CLY 011/153 RPR STRW | 43712679 | VALLEY SPRINGS-CLAY | 011/153 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.880443 | 38.2724 | ETL.8264 | 40904769 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog Multi
115637034 | T2 EI FORT ROSS-GUALALA 55/004 RPL SPLW | 43714438 | GUALALA-MONTE RIO | 055/004 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.495173 | 38.7428 | ETL.6980 | 40750363 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-04-30
115637044 | T2NT EI VLY SPRNGS-CLY 011/153 INST MRKW |  | VALLEY SPRINGS-CLAY | 011/153 | ICW | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.880443 | 38.2724 | ETL.8264 | 40904769 | Marker (i.e. signs)-Wood | Missing | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog Multi
115637048 | T2 EI PLACER-DEL MAR 3/81 REPL POLE | 31454612 | PLACER-DEL MAR | 003/081 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.12884 | 38.8637 | ETL.7800 | 40820912 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
115637270 | T2NT EI VLY SPRNGS-CLY 008/121 INST MRKW |  | VALLEY SPRINGS-CLAY | 008/121 | ICW | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.850908 | 38.2432 | ETL.8264 | 40906852 | Marker (i.e. signs)-Wood | Missing | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 12
115637280 | T2 EI VLY SPRNGS-CLY 008/121 ANTI SPLIT | 43712679 | VALLEY SPRINGS-CLAY | 008/121 | ICW | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.850908 | 38.2432 | ETL.8264 | 40906852 | Hardware-Wood | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 12
115637312 | T2 EI CASCADE-BENTON-D 2/055 RPL POLE | 31427801 | CASCADE-BENTON-DESCHUTES | 002/055 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.323146 | 40.6211 | ETL.6310 | 40676918 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
115637442 | T2 EI PLACER-DEL MAR 3/80 RPL POLE | 31502247 | PLACER-DEL MAR | 003/080 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.128154 | 38.8641 | ETL.7800 | 40805781 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
115637453 | T2 EI EAGLE RK-CRTINA :014/021 RPR GYWW | 43730688 | EAGLE ROCK-CORTINA | :014/021 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.609158 | 38.9373 | ETL.1470 | 41176324 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-08-06
115637458 | T2 EI PIT #7 TAP 1/12B RPR GYWW | 43877044 | PIT #7 TAP | 001/012B | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.971515 | 40.836 | ETL.5442 | 41162602 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain
115637481 | T2 EI EAGLE ROCK-CORT :018/012 RPR GYWW | 43730688 | EAGLE ROCK-CORTINA | :018/012 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.611461 | 38.9916 | ETL.1470 | 41176395 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-05-20
115637502 | T2 EI PIT #7 TAP 001/012A RPR GYWW | 43877044 | PIT #7 TAP | 001/012A | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.971536 | 40.836 | ETL.5442 | 41162601 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain
115637522 | T2 EI EAGLE ROCK-COR :18/011 RPR GYWW | 43730688 | EAGLE ROCK-CORTINA | :018/011 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.611613 | 38.9906 | ETL.1470 | 41176394 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-05-20
115637530 | T2 EI CASCADE-BENTN-DES 003/083 RPL STRW | 31427801 | CASCADE-BENTON-DESCHUTES | 003/083 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.313147 | 40.6005 | ETL.6310 | 40657141 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain
115637553 | T2 EI PIT #7 TAP 1/12C RPR GYWW | 43877044 | PIT #7 TAP | 001/012C | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.971488 | 40.836 | ETL.5442 | 40690231 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain
115637555 | T2 EI PIT #7 TAP 1/12C RPR GRWW | 43877044 | PIT #7 TAP | 001/012C | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.971488 | 40.836 | ETL.5442 | 40690231 | Ground Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain
115637557 | T2 EI VLY SPRNGS-CLY 011/154 REPL STRW | 31426450 | VALLEY SPRINGS-CLAY | 011/154 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.881326 | 38.273 | ETL.8264 | 40904770 | Structure-Wood | Rotten | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 12
115637558 | T2 EI EGL RCK-CRTN :014/004 RPR GYWW | 43730688 | EAGLE ROCK-CORTINA | :014/004 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.607913 | 38.9259 | ETL.1470 | 41176307 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-08-06
115637600 | T2 EI EAGLE ROCK-COR :18/011 RPR POLE | 43730688 | EAGLE ROCK-CORTINA | :018/011 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.611613 | 38.9906 | ETL.1470 | 41176394 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-05-20
115637607 | T2 EI EAGLE ROCK-CRTN :014/005 RPR GYWW | 43730688 | EAGLE ROCK-CORTINA | :014/005 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.608214 | 38.9267 | ETL.1470 | 41176308 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-08-06
115637617 | T2 EI FORT ROSS-GUAL 049/009 RPL ANCW | 31430306 | GUALALA-MONTE RIO | 049/009 | 93E | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.402144 | 38.722 | ETL.6980 | 40876078 | Anchor-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 637 | Lakeville |  |  | 2019-04-30
115637619 | T2 EI EAGLE RCK-CORTINA :14/001 RPR ANCH | 43730688 | EAGLE ROCK-CORTINA | :014/001 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.607904 | 38.9246 | ETL.1470 | 41176304 | Anchor-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-08-06
115637668 | T2 EI EAGLE ROCK-CORT :017/018 RPL PL | 31488227 | EAGLE ROCK-CORTINA | :017/018 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.613113 | 38.98 | ETL.1470 | 41176382 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  | 2019-09-13
115637715 | T2 EI EAGLE ROCK-CORTINA :13/2 RPR POLE | 43730688 | EAGLE ROCK-CORTINA | :013/002 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.61819 | 38.9164 | ETL.1470 | 41176282 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-09-13
115637722 | T2 EI EAGLE ROCK-C :015/000 RPR GYWW | 43730688 | EAGLE ROCK-CORTINA | :015/000 | ICW | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.608804 | 38.9378 | ETL.1470 | 41176325 | Guy Wire-Wood | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-08-06
115637729 | EI VALLEY SPRINGS-CLAY 013/189 REPL INSW | 31433173 | VALLEY SPRINGS-CLAY | 013/189 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  | Likely MAT error - delink to correct |  | LATE | Central | WSIP | [6 empty] | '-120.9094669 | 38.2899 | ETL.8264 | 40914398 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Victor |  | Y - Prog Multi
115637771 | T2 EI TESLA-SLDO-MNTCA 25/152 RPR GYWW | 43712674 | TESLA-SALADO-MANTECA | 025/152 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-121.207111 | 37.4701 | ETL.4000 | 40912757 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 7
115637789 | T2 EI TESLA-SLDO-MNTCA 25/150 RPR GYWW | 43712674 | TESLA-SALADO-MANTECA | 025/150 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-121.206138 | 37.4731 | ETL.4000 | 40912755 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 7
115637797 | T2 EI EAGLE ROCK-COR :015/001 RPR GYWW | 43730688 | EAGLE ROCK-CORTINA | :015/001 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.608649 | 38.9383 | ETL.1470 | 41176326 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-08-06
115637798 | T2 EI EAGLE ROCK-COR :015/001 RPR POLE | 43730688 | EAGLE ROCK-CORTINA | :015/001 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.608649 | 38.9383 | ETL.1470 | 41176326 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-09-13
115637993 | T2 EI PLACER-DEL MAR 3/74 RPR GYWW | 43755677 | PLACER-DEL MAR | 003/074 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.125078 | 38.8665 | ETL.7800 | 40583100 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Sacramento |  |  | Yes
115638036 | T2 EI VLY SPRNGS-CLY 011/158 RPR STRW | 43727736 | VALLEY SPRINGS-CLAY | 011/158 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.884655 | 38.2749 | ETL.8264 | 40911612 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog Multi
115638054 | T2 EI VLY SPRNGS-CLY 011/157 RPL GUYPOLE | 31501103 | VALLEY SPRINGS-CLAY | 011/157 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.883769 | 38.2745 | ETL.8264 | 41196644 | Guy Pole-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 12
115638151 | T2 EI VLY SPRNGS-CLY 006/087 REPL SPLW | 43712679 | VALLEY SPRINGS-CLAY | 006/087 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.833763 | 38.2121 | ETL.8264 | 40904722 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog Multi
115638152 | T2 EI VLY SPRNGS-CLY 006/087 RPR STRW | 43712679 | VALLEY SPRINGS-CLAY | 006/087 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.833763 | 38.2121 | ETL.8264 | 40904722 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog Multi
115638160 | T2 EI EAGLE ROCK-CRTN :013/004 RPL PL | 31488227 | EAGLE ROCK-CORTINA | :013/004 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.61817 | 38.9177 | ETL.1470 | 41176284 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  | 2019-08-06
115638219 | T2 EI CASCADE-BNTN-DES A005/114 RPR STRW | 43690811 | CASCADE-BENTON-DESCHUTES | A005/114 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.293202 | 40.5879 | ETL.6310 | 40600705 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
115638245 | T2 EI EGL RCK-CRTN :013/005 RPL PL | 31488227 | EAGLE ROCK-CORTINA | :013/005 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.61811 | 38.9177 | ETL.1470 | 41176285 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  | 2019-09-13
115638247 | T2 EI EAGLE ROCK-COR :18/013 RPL PL | 31488227 | EAGLE ROCK-CORTINA | :018/013 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.611311 | 38.9928 | ETL.1470 | 41176396 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  | 2019-05-20
115638250 | T2 EI EAGLE ROCK-CORT :018/010 RPR GYWW | 43730688 | EAGLE ROCK-CORTINA | :018/010 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.611749 | 38.9896 | ETL.1470 | 41176393 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-05-20
115638258 | T2 EI PLACER-DEL MR 002/054 RPL STRW | 31454612 | PLACER-DEL MAR | 002/054 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.117343 | 38.8767 | ETL.7800 | 40660918 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
115638296 | T2 EI EAGLE ROCK-COR :18/009 RPR GYWW | 43730688 | EAGLE ROCK-CORTINA | :018/009 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.611914 | 38.9886 | ETL.1470 | 41176392 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-05-20
115638341 | T2 EI PLACER-DEL MAR 2/55 RPL POLE | 31498224 | PLACER-DEL MAR | 002/055 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.117381 | 38.8761 | ETL.7800 | 40758280 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | 11/20: New UPRR extension or permit started. Existing to expire 12/23_cxu7
115638359 | T2 EI VLY SPRNGS-CLY 007/110 RPR GYWW | 43712679 | VALLEY SPRINGS-CLAY | 007/110 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.846018 | 38.2325 | ETL.8264 | 40904742 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 12
115638366 | T2 EI EAGLE ROCK-CORT :018/008 RPR GYWW | 43730688 | EAGLE ROCK-CORTINA | :018/008 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.612069 | 38.9875 | ETL.1470 | 41176391 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-08-06
115638369 | T2 EI EAGLE ROCK-COR :16/001 RPR GYWW | 43730688 | EAGLE ROCK-CORTINA | :016/001 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.607849 | 38.9536 | ETL.1470 | 41176347 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-08-06
115638385 | T2 EI FORT ROSS-GUAL 054/010 RPR STRS | 43714436 | GUALALA-MONTE RIO | 054/010 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.489291 | 38.74 | ETL.6980 | 40587404 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Lakeville |  |  | 2019-04-30
115638415 | T2 EI TESLA-SLDO-MNTCA 25/149 RPR GYWW | 43712674 | TESLA-SALADO-MANTECA | 025/149 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-121.205785 | 37.4741 | ETL.4000 | 40912754 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 7
115638422 | T2 EI FORT ROSS-GUALALA 56/001 RPL POLE | 31492553 | GUALALA-MONTE RIO | 056/001 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.506423 | 38.7492 | ETL.6980 | 40584667 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  | 2019-04-30
115638460 | T2 EI EAGLE ROCK-CORT :018/007 RPR GYWW | 43730688 | EAGLE ROCK-CORTINA | :018/007 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.612189 | 38.9867 | ETL.1470 | 41176390 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-08-06
115638488 | T2 EI CSCDE-BNTN-DSCHTS 004/101 REPL PL | 31431551 | CASCADE-BENTON-DESCHUTES | 004/101 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.310886 | 40.5899 | ETL.6310 | 40868647 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
115638489 | T2 EI VLY SPRNGS-CLY 007/107 RPR GYWW | 43712679 | VALLEY SPRINGS-CLAY | 007/107 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.843693 | 38.2299 | ETL.8264 | 40906848 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 12
115638491 | T2 EI VLY SPRNGS-CLY 006/092 REPL SPLW | 43712679 | VALLEY SPRINGS-CLAY | 006/092 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.835735 | 38.2184 | ETL.8264 | 40905035 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog Multi
115638516 | T2 EI FORT ROSS-GUAL 050/002 RPL STRW | 31462486 | GUALALA-MONTE RIO | 050/002 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.411617 | 38.7273 | ETL.6980 | 40700990 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  | 2019-04-30
115638543 | T2 EI CRIBOU-PLUMS JCT 15/9 RPL PL | 31455444 | CARIBOU-PLUMAS JCT | 015/009 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-120.932785 | 39.9564 | ETL.6290 | 40875447 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
115638547 | T2 EI CRBOU-PLMS JCT 015/006 RPR STRW | 43640453 | CARIBOU-PLUMAS JCT | 015/006 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.935513 | 39.9572 | ETL.6290 | 40826475 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
115638550 | T2 EI EAGLE ROCK-C :16/000 RPR GYWW | 43730688 | EAGLE ROCK-CORTINA | :016/000 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.607787 | 38.9527 | ETL.1470 | 41176346 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-08-06
115638556 | T2 EI VLY SPRNGS-CLY 007/107 REPL SPLW | 43899852 | VALLEY SPRINGS-CLAY | 007/107 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.843693 | 38.2299 | ETL.8264 | 40906848 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 12
115638557 | T2 EI VLY SPRNGS-CLY 008/111 REFRAME | 31426625 | VALLEY SPRINGS-CLAY | 008/111 | 93E | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.847418 | 38.2341 | ETL.8264 | 40906849 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Victor |  | Y - Prog Multi
115638583 | T2 EI VLY SPRNGS-CLY 007/106 RPR GYWW | 43712679 | VALLEY SPRINGS-CLAY | 007/106 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.8421 | 38.2282 | ETL.8264 | 40904739 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog Multi
115638592 | T2 EI FORT ROSS-GUAL 057/004 RPL ANCW | 31430306 | GUALALA-MONTE RIO | 057/004 | 93E | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.515513 | 38.7667 | ETL.6980 | 40770601 | Anchor-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 637 | Lakeville |  |  | 2019-08-09
115638604 | T2 EI VLY SPRNGS-CLY 007/108 RPR GYWW | 43712679 | VALLEY SPRINGS-CLAY | 007/108 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.84447 | 38.2308 | ETL.8264 | 40904740 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 12
115638609 | T2 EI EAGLE ROCK-CORTINA :14/8 RPR GYWW | 43730688 | EAGLE ROCK-CORTINA | :014/008 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.608898 | 38.9289 | ETL.1470 | 41176311 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-09-13
115638631 | T2 EI FORT ROSS-GUAL 054/004 RPL DAMW | 43714438 | GUALALA-MONTE RIO | 054/004 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.479236 | 38.7353 | ETL.6980 | 40750362 | Damper-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-04-30
115638747 | T2 EI EAGLE ROCK-CORT :018/005 RPR GYWW | 43730688 | EAGLE ROCK-CORTINA | :018/005 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.612724 | 38.9852 | ETL.1470 | 41176388 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-08-06
115638815 | T2 EI EAGLE ROCK-CORT :015/019 RPR GYWW | 43730688 | EAGLE ROCK-CORTINA | :015/019 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.607646 | 38.9511 | ETL.1470 | 41176344 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-08-06
115638831 | T2 EI VALLEY SPRINGS 7/105 INST STRUCT # |  | VALLEY SPRINGS-CLAY | 007/105 | ICW | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.841288 | 38.2273 | ETL.8264 | 40904738 | Marker (i.e. signs)-Wood | Missing | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog Multi
115638860 | T2 EI EAGLE ROCK-COR :17/014 RPR GYWW | 43730688 | EAGLE ROCK-CORTINA | :017/014 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.612526 | 38.9777 | ETL.1470 | 41176378 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-08-06
115638909 | T2 EI EAGLE ROCK-CORT :018/004 RPR GYWW | 43730688 | EAGLE ROCK-CORTINA | :018/004 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.61296 | 38.9844 | ETL.1470 | 41176387 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-09-13
115639006 | T2 EI EAGLE ROCK-CORT :017/015 RPR GYWW | 43730688 | EAGLE ROCK-CORTINA | :017/015 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.612473 | 38.9783 | ETL.1470 | 41176379 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-08-06
115639009 | T2 EI EAGLE ROCK-COR :18/003 RPR GYWW | 43730688 | EAGLE ROCK-CORTINA | :018/003 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.613086 | 38.9836 | ETL.1470 | 41176386 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-08-06
115639041 | T2 EI COTTONWOOD-PAN 000/003 RPR STRW | 43749232 | COTTONWOOD-PANORAMA | 000/003 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.267204 | 40.4019 | ETL.1340 | 40655968 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
115639063 | T2 EI EAGLE ROCK-CORT :017/015 RPL HRDW | 43730688 | EAGLE ROCK-CORTINA | :017/015 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.612473 | 38.9783 | ETL.1470 | 41176379 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-08-06
115639076 | T2 EI EAGLE ROCK-COR :18/002 RPR GYWW | 43730688 | EAGLE ROCK-CORTINA | :018/002 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.613052 | 38.9828 | ETL.1470 | 41176385 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-08-06
115639079 | T2 EI EAGLE ROCK-COR :15/018 RPR GYWW | 43730688 | EAGLE ROCK-CORTINA | :015/018 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.607675 | 38.9502 | ETL.1470 | 41176343 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-08-06
115639128 | T2 EI EAGLE ROCK-COR :015/005 RPR GYWW | 43730688 | EAGLE ROCK-CORTINA | :015/005 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.608179 | 38.9409 | ETL.1470 | 41176330 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-08-06
115639210 | T3 EI MONTE RIO-FULTON 010/003 REPL POLE | 31428882 | MONTE RIO-FULTON | 010/003 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.94677 | 38.4864 | ETL.7630 | 44178462 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  | 2019-04-30
115639216 | T2 EI PARDEE #1 TAP 009/127 RPL STRW | 31426446 | PARDEE #1 TAP | 009/127 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.851035 | 38.2554 | ETL.8231 | 40679939 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 5 | EBMUD
115639224 | T2 EI FULTON-PUEBLO 012/059B RPR STRW | 43720985 | FULTON-PUEBLO | 012/059B | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.214927 | 38.509 | ETL.1600 | 43249714 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-04-25
115639232 | T2 EI CASCADE-BENTON-D 04/100 RPL POLE | 31431551 | CASCADE-BENTON-DESCHUTES | 004/100 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.310608 | 40.59 | ETL.6310 | 40867946 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
115639264 | T2 EI EAGLE ROCK-CORT :015/017 RPR GYWW | 43730688 | EAGLE ROCK-CORTINA | :015/017 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.607722 | 38.9494 | ETL.1470 | 41176342 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-08-06
115639280 | T2 EI EAGLE ROCK-CORT :015/006 RPR GYWW | 43730688 | EAGLE ROCK-CORTINA | :015/006 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.608192 | 38.9419 | ETL.1470 | 41176331 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-08-06
115639285 | T2 E1 TSLA-SLD-MNTCA 024/134 RPR GYWW | 43712674 | TESLA-SALADO-MANTECA | 024/134 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-121.21818 | 37.4914 | ETL.4000 | 40912743 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 7
115639505 | T2 EI VLY SPRNGS-CLY 007/109 RPR GYWW | 43727736 | VALLEY SPRINGS-CLAY | 007/109 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.84561 | 38.2321 | ETL.8264 | 40904741 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 12
115639506 | T2 EI VLY SPRNGS-CLY 007/108 RPR STRW | 43712679 | VALLEY SPRINGS-CLAY | 007/108 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.84447 | 38.2308 | ETL.8264 | 40904740 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 12
115639507 | T2 EI VLY SPRNGS-CLY 007/110 RPR STRW | 43712679 | VALLEY SPRINGS-CLAY | 007/110 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.846018 | 38.2325 | ETL.8264 | 40904742 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 12
115639580 | EI BN VST BMSS PWR TP 000/008 INST DAMW | 43712666 | BUENA VISTA BIOMASS POWER TAP | 000/008 | ICW | E | Pre-2020_(9a) Other ignition related |  |  |  |  | LATE | Central | WSIP | FSRP | [5 empty] | '-120.911483 | 38.2812 | ETL.8252 | 40857199 | Damper-Wood | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Released
115639618 | T2 EI KILARC-DESCHUTES 011/249 RPL STRW | 31423831 | KILARC-DESCHUTES | 011/249 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.031697 | 40.5686 | ETL.7300 | 40600393 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
115639619 | T2 EI KILARC-DESCHUTES 011/247 RPL STRW | 31423831 | KILARC-DESCHUTES | 011/247 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.030005 | 40.5691 | ETL.7300 | 40868569 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
115639680 | T2 EI KILARC-DESCHUTES 011/246 RPL STRW | 31423831 | KILARC-DESCHUTES | 011/246 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.029125 | 40.5693 | ETL.7300 | 40816232 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
115639683 | T2 EI KILARC-DESCHUTES 011/245 RPL STRW | 31423831 | KILARC-DESCHUTES | 011/245 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.028085 | 40.5695 | ETL.7300 | 40810441 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
115639705 | T2 EI CASCADE-BENTN-DES 004/096 REFRAME | 31486305 | CASCADE-BENTON-DESCHUTES | 004/096 | 93E | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.30836 | 40.5906 | ETL.6310 | 40600710 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  | Yes
115639980 | T2 EI VLY SPRNGS-CLY 007/107 RPR STRW | 43712679 | VALLEY SPRINGS-CLAY | 007/107 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.843693 | 38.2299 | ETL.8264 | 40906848 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 12
115640972 | T2 EI CASCDE-BENTN-DES A004/098 RPL STRW | 31427801 | CASCADE-BENTON-DESCHUTES | A004/098 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.307173 | 40.5898 | ETL.6310 | 40868676 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain
115641025 | T2 EI FORT ROSS-GUALALA 49/003 RPL POLE | 31492553 | GUALALA-MONTE RIO | 049/003 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.395777 | 38.7218 | ETL.6980 | 40648495 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  | 2019-04-30
115641084 | EI VALLEY SPRINGS-CLAY 013/180 RPR STRW | 43727736 | VALLEY SPRINGS-CLAY | 013/180 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-120.904357 | 38.2851 | ETL.8264 | 40904785 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog Multi
115641248 | T2 EI PIT #5-ROUD MTN #2 11/111 RMV VEGN |  | PIT #5-ROUND MTN #2 | 011/111 | HNA | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.933528 | 40.8221 | ETL.5430 | 44561309 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Table Mountain |  |  | Yes
115641308 | T2 EI EAGLE ROCK-COR :015/008 RPR GYWW | 43730688 | EAGLE ROCK-CORTINA | :015/008 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.608154 | 38.9434 | ETL.1470 | 41176333 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-05-20
115641527 | T2 EI EGLE ROCK-REDBUD :012/003 RPL STRW | 31502251 | EAGLE ROCK-REDBUD | :012/003 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.618032 | 38.9133 | ETL.1480 | 40648900 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  | 2019-06-05
115641609 | T2 EI HAT CRK #1-WSTWD 003/073 REFRAME | 31471575 | HAT CREEK #1-WESTWOOD | 003/073 | 93E | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.4757 | 40.9175 | ETL.7030 | 40591002 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  | Yes
115641750 | EI VALLY SPRGS-MRTLL #1 004/008 RPR STRW | 43740949 | VALLEY SPRINGS-MARTELL #1 | 004/008 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-120.768506 | 38.2603 | ETL.8240 | 40876087 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Victor |  | Y - Prog Multi | Yes
115642050 | T2 EI DLTA-MTN GTE JCT 001/037 RPL STRW | 31456311 | DELTA-MOUNTAIN GATE JCT | 001/037 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.397335 | 40.9159 | ETL.6750 | 40771404 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
115642147 | EI VALLEY SPRGS-MRTLL #1 003/014 RPL STR | 31422462 | VALLEY SPRINGS-MARTELL #1 | 003/014 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-120.774555 | 38.2525 | ETL.8240 | 40768883 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - Prog Multi
115642184 | EI VALLEY SPRGS-MRTLL #1 004/009 RPL STR | 31422462 | VALLEY SPRINGS-MARTELL #1 | 004/009 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-120.767795 | 38.2612 | ETL.8240 | 40864366 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 16
115642283 | T2 EI ELK-GUALALA 065/002 RMV VEGN |  | ELK-GUALALA | 065/002 | HNA | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.530769 | 38.7997 | ETL.8410 | 40684567 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Lakeville
115642338 | T2 EI EGLE RCK-CRTN :015/016 RPL STRW | 31502252 | EAGLE ROCK-CORTINA | :015/016 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.607747 | 38.9486 | ETL.1470 | 41176341 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  | 2019-08-06
115642546 | T2 EI PIT #5-RND MTN #2 8/83 RPR GYWW | 43755674 | PIT #5-ROUND MTN #2 | 008/083 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.929556 | 40.8715 | ETL.5430 | 44561259 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
115642555 | T2 EI EAGLE ROCK-REDBUD :13/6 RPL POLE | 31492608 | EAGLE ROCK-REDBUD | :013/006 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.616438 | 38.9176 | ETL.1480 | 40809077 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  | 2019-06-05
115643406 | T2 EI KILARC-DESCHUTES 011/251 RPL STRW | 31423831 | KILARC-DESCHUTES | 011/251 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.033329 | 40.5682 | ETL.7300 | 40676511 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
115643407 | T2 EI KILARC-DESCHUTES 012/259 RPL STRW | 31423831 | KILARC-DESCHUTES | 012/259 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.040326 | 40.5665 | ETL.7300 | 40826000 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
115643409 | T2 EI KILARC-DESCHUTES 012/252 RPL STRW | 31423831 | KILARC-DESCHUTES | 012/252 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.034268 | 40.568 | ETL.7300 | 40617703 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
115643428 | T2NT EI VLY SPRNGS-CLY 011/160 MRKW |  | VALLEY SPRINGS-CLAY | 011/160 | ICW | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.886319 | 38.2758 | ETL.8264 | 40904773 | Marker (i.e. signs)-Wood | Missing | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog Multi
115643443 | T2 EI EGLE RCK RDBD :013/010 RPL PL | 31488228 | EAGLE ROCK-REDBUD | :013/010 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.613373 | 38.9176 | ETL.1480 | 40588093 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  | 2019-06-05
115643586 | T2 EI VLY SPRNGS-CLY 011/160 RPR STRW | 43712893 | VALLEY SPRINGS-CLAY | 011/160 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.886319 | 38.2758 | ETL.8264 | 40904773 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 12
115644088 | T2 EI KILARC-DESCHUTES A025/530 RPL PL | 31440586 | KILARC-DESCHUTES | A025/530 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.285286 | 40.5711 | ETL.7300 | 40702809 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
115644207 | T2 EI KILARC-DESCHUTES 012/254 RPL STRW | 31423831 | KILARC-DESCHUTES | 012/254 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.036153 | 40.5675 | ETL.7300 | 40676515 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
115644972 | T2 EI HAT CREK #1-WSTWD 005/115 RPL POLE | 31504344 | HAT CREEK #1-WESTWOOD | 005/115 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.43772 | 40.9036 | ETL.7030 | 40816098 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Need New ERTC
115645090 | EI CSCD-BTN-DSCHTS A009/188 RPR CRSW | 43690811 | CASCADE-BENTON-DESCHUTES | A009/188 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-122.239968 | 40.5556 | ETL.6310 | 40868661 | Crossarm-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
115645097 | T2 EI CSCD-BTN-DSCHTS A008/171 RPL PL | 31427802 | CASCADE-BENTON-DESCHUTES | A008/171 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.255309 | 40.5579 | ETL.6310 | 40868663 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain
115645126 | T2 EI CSCD-BTN-DSCHTS A008/176 RPR STRW | 43690811 | CASCADE-BENTON-DESCHUTES | A008/176 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.25055 | 40.5569 | ETL.6310 | 41177755 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain
115645147 | T2 EI CSCDE-BNTN-DSCHUTS A009/184 RPL PL | 31427802 | CASCADE-BENTON-DESCHUTES | A009/184 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.2435 | 40.5557 | ETL.6310 | 40676943 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
115645154 | T2 EI CSCDE-BNTN-DSCHUTS A008/166 RPL PL | 31427802 | CASCADE-BENTON-DESCHUTES | A008/166 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.259242 | 40.5591 | ETL.6310 | 40650234 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
115645179 | T2 EI EGLE RCK-CRTINA :019/011 RPR GYWW | 43730688 | EAGLE ROCK-CORTINA | :019/011 | ICW | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.611403 | 39.0063 | ETL.1470 | 41176409 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-05-20
115645198 | T2 EI FORT ROSS-GUALALA 58/11 RPL PL | 31462486 | GUALALA-MONTE RIO | 058/012 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.521627 | 38.7866 | ETL.6980 | 40686400 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  | 2019-08-21
115645271 | T2NT EI PLRMO-ORVILLE #2 A6/076 INS GMKW | 43724470 | PALERMO-OROVILLE #2 | A006/076 | ICW | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.502701 | 39.5111 | ETL.7740 | 40824100 | Guy Wire Mark /Indic-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
115645287 | T2NT EI PLRMO-ORVILLE #2 A6/076 INS MRKW | 43724470 | PALERMO-OROVILLE #2 | A006/076 | ICW | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.502701 | 39.5111 | ETL.7740 | 40824100 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain
115645289 | T2 EI CORDELIA #2 TAP 003/067 RPL SPLW | 43743931 | CORDELIA #2 TAP | 003/067 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.154242 | 38.2508 | ETL.8184 | 40599323 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Sacramento |  |  | Yes
115645305 | T2 EI PLRMO-ORVILLE #2 A006/082 RPR STRW | 43724470 | PALERMO-OROVILLE #2 | A006/082 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.502582 | 39.5195 | ETL.7740 | 40585852 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain
115645330 | T2 EI CSCDE-BNTN-DSCHTS A006/125 RPL PL | 31427802 | CASCADE-BENTON-DESCHUTES | A006/125 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.285091 | 40.5829 | ETL.6310 | 41177763 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
115645335 | T2 EI PALERMO-OROVILLE #2 A7/85 RPR GYWW | 43724470 | PALERMO-OROVILLE #2 | A007/085 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.502255 | 39.523 | ETL.7740 | 40599877 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
115645342 | T2 EI PLRMO-ORVILLE #2 A007/092 RPL ANCW | 31431544 | PALERMO-OROVILLE #2 | A007/092 | 93E | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.494537 | 39.5297 | ETL.7740 | 40664690 | Anchor-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain
115645346 | T2 EI PLRMO-ORVILLE #2 A007/084 RPR GYWW | 43724470 | PALERMO-OROVILLE #2 | A007/084 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.5026 | 39.5221 | ETL.7740 | 44196306 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
115645350 | T2 EI PLRMO-ORVILLE #2 A007/092 RPR GYWW | 43724470 | PALERMO-OROVILLE #2 | A007/092 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.494537 | 39.5297 | ETL.7740 | 40664690 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain
115645392 | T2 EI PALRMO-ORVILLE #1 1/24 REFRAME PLE | 31474478 | PALERMO-OROVILLE #1 | 001/024 | 93E | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-121.533728 | 39.4592 | ETL.7730 | 40598414 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 637 | Table Mountain |  |  | Yes
115645405 | T2 EI CSCD-BTN-DSCHTS A007/161 RPL PL | 31427802 | CASCADE-BENTON-DESCHUTES | A007/161 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.260352 | 40.5614 | ETL.6310 | 40590319 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
115645406 | T2 EI CSCD-BTN-DSCHTS A007/160 RPL PL | 31427802 | CASCADE-BENTON-DESCHUTES | A007/160 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.260419 | 40.562 | ETL.6310 | 40586274 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
115645414 | T2 EI EAGL RCK-CRTINA :20/001 RPR GYWR | 43730688 | EAGLE ROCK-CORTINA | :020/001 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.611978 | 39.0104 | ETL.1470 | 41176412 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-05-20
115645418 | T2 EI CSCD-BTN-DSCHTS A006/144 RPR STRW | 43690811 | CASCADE-BENTON-DESCHUTES | A006/144 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.270148 | 40.5724 | ETL.6310 | 40600697 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain
115645469 | T2 EI HTCRK #1-WSTWD 013/261 RPR CRSW | 43736796 | HAT CREEK #1-WESTWOOD | 013/261 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.359967 | 40.8109 | ETL.7030 | 40676252 | Crossarm-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
115645481 | T2 EI HAT CRK #1-WESTWD 13/265 RPR CRSW | 43736796 | HAT CREEK #1-WESTWOOD | 013/265 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.357193 | 40.8086 | ETL.7030 | 40616862 | Crossarm-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
115645483 | T2 EI HAT CRK #1-WESTWD 13/265 RPL SPLW | 43736796 | HAT CREEK #1-WESTWOOD | 013/265 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.357193 | 40.8086 | ETL.7030 | 40616862 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
115645495 | T2 EI HAT CREK #1-WSTWD 13/265 RPR STRW | 43736796 | HAT CREEK #1-WESTWOOD | 013/265 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.357193 | 40.8086 | ETL.7030 | 40616862 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
115645505 | T2 EI HTCRK #1-WSTWD 013/267 RPL STRW | 31426976 | HAT CREEK #1-WESTWOOD | 013/267 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.355795 | 40.8075 | ETL.7030 | 40759174 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain
115645591 | T2 EI CSCD-BTN-DSCHTS A007/147 RPL PL | 31427802 | CASCADE-BENTON-DESCHUTES | A007/147 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.267637 | 40.5706 | ETL.6310 | 40759308 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
115645597 | T2 EI HAT CRK #1-WESTWD 14/274 RPR STRW | 43736796 | HAT CREEK #1-WESTWOOD | 014/274 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.350953 | 40.8036 | ETL.7030 | 40600202 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
115645599 | T2 EI HTCRK #1-WSTWD 014/271 RPR STRW | 43736796 | HAT CREEK #1-WESTWOOD | 014/271 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.352952 | 40.8053 | ETL.7030 | 40759176 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
115645676 | T3 EI ORO FINO TAP 000/015 INS GYWW | 43758390 | ORO FINO TAP | 000/015 | ICW | E | Pre-2020_(9a) Other ignition related |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.615663 | 39.8698 | ETL.6721 | 40751729 | Guy Wire-Wood | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
115645715 | T2 EI HAT CREK #1-WSTWD 14/272 RPL STRW | 31426976 | HAT CREEK #1-WESTWOOD | 014/272 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.352368 | 40.8047 | ETL.7030 | 40817107 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain
115645770 | T2 EI CSCDE-BNTN-DSCHTES A005/123 RPL PL | 31427801 | CASCADE-BENTON-DESCHUTES | A005/123 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-122.286632 | 40.584 | ETL.6310 | 40600702 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
115645785 | T2 EI CSCDE-BNTN-DSCHUTS A006/135 RPL PL | 31421915 | CASCADE-BENTON-DESCHUTES | A006/135 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.277243 | 40.5774 | ETL.6310 | 40868669 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
115645786 | T2 EI CSCDE-BNTN-DSCHTES A6/131 RPPL PL | 31427802 | CASCADE-BENTON-DESCHUTES | A006/131 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.280549 | 40.5797 | ETL.6310 | 44630141 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
115645928 | T2 EI COLGATE-PALERMO 13/256 REPL POLE | 31423185 | COLGATE-PALERMO | 013/256 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.40152 | 39.3863 | ETL.6500 | 40815258 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
115645929 | T2 EI COLGATE-PALERMO 13/257 RPl POLE | 31517754 | COLGATE-PALERMO | 013/257 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.40212 | 39.3868 | ETL.6500 | 40822478 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
115645930 | T2 EI COLGATE-PALERMO-13/254 RPL POLE | 31517754 | COLGATE-PALERMO | 013/254 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.400295 | 39.3854 | ETL.6500 | 40757199 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
115647683 | T2 EI HT CRK #1-WSTWD 010/198 REPL STRW | 31426976 | HAT CREEK #1-WESTWOOD | 010/198 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.396302 | 40.8495 | ETL.7030 | 40825661 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain
115647837 | T2 EI CRBOU-PLMS JCT 014/015 RPR JMPW | 43640453 | CARIBOU-PLUMAS JCT | 014/015 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.9445 | 39.9571 | ETL.6290 | 40768906 | Jumper-Wood | No Good/Out of Stdrd | Repair | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
115647913 | T2 EI CARIBOU-PLUMAS JCT 14/14 RPR JUMW | 43640453 | CARIBOU-PLUMAS JCT | 014/014 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.944982 | 39.9571 | ETL.6290 | 40758743 | Jumper-Wood | No Good/Out of Stdrd | Repair | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
115648012 | T2NT EI PALRM-ORVILL #2 A6/79 INS MRKW | 43724470 | PALERMO-OROVILLE #2 | A006/079 | ICW | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.502572 | 39.5141 | ETL.7740 | 40767027 | Marker (i.e. signs)-Wood | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
115648018 | T2 EI PALRM-ORVILL #2 A6/79 RPR GYWW | 43724470 | PALERMO-OROVILLE #2 | A006/079 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.502572 | 39.5141 | ETL.7740 | 40767027 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
115649647 | T2 EI HT CRK #1-WSTWD 012/239 RPL STRW | 31504344 | HAT CREEK #1-WESTWOOD | 012/239 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.375418 | 40.8233 | ETL.7030 | 40827604 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Need New ERTC
115649649 | T2 EI HT CRK #1-WSTWD 011/224 RPL POLE | 31504344 | HAT CREEK #1-WESTWOOD | 011/224 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.384298 | 40.8322 | ETL.7030 | 40770717 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Need New ERTC
115649666 | T2 EI HT CRK #1-WSTWD 012/236 REPL STRW | 31426976 | HAT CREEK #1-WESTWOOD | 012/236 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.377247 | 40.8248 | ETL.7030 | 40600155 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain
115649667 | T2 EI HT CRK #1-WSTWD 012/235 REPL STRW | 31426976 | HAT CREEK #1-WESTWOOD | 012/235 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.378 | 40.8254 | ETL.7030 | 40868436 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain
115649729 | T2 EI HT CRK #1-WSTWD 014/277 REFRAME | 31471575 | HAT CREEK #1-WESTWOOD | 014/277 | 93E | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.348833 | 40.8019 | ETL.7030 | 40817109 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  | Yes
115649801 | T2 EI PARADISE-TABLE MTN 24/185 RPL POLE | 31453760 | PARADISE-TABLE MTN | 024/185 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.639516 | 39.6996 | ETL.4316 | 40656378 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
115649804 | T2 EI HT CRK #1-WSTWD 014/277 RPR STRW | 43736796 | HAT CREEK #1-WESTWOOD | 014/277 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.348833 | 40.8019 | ETL.7030 | 40817109 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
115649820 | T2 EI HT CRK #1-WSTWD 014/276 RPR GYWW | 43736796 | HAT CREEK #1-WESTWOOD | 014/276 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.349582 | 40.8025 | ETL.7030 | 40770724 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
115649821 | T2 EI HT CRK #1-WSTWD 014/279 REPL STRW | 31426976 | HAT CREEK #1-WESTWOOD | 014/279 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.347463 | 40.8008 | ETL.7030 | 40617047 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain
115649978 | T2 EI COLGATE-PALERMO-8/156 REPLACE POLE | 31423185 | COLGATE-PALERMO | 008/156 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.327757 | 39.3513 | ETL.6500 | 40598487 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
115649979 | T2 EI PARADISE-BUTTE 06/066 RPR PL | 43758389 | PARADISE-BUTTE | 006/066 | ICS | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.680342 | 39.7039 | ETL.4396 | 40758512 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
115650228 | T2 EI PARADISE-BUTTE 06/066 INSTL MRKS | 43758389 | PARADISE-BUTTE | 006/066 | ICS | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.680342 | 39.7039 | ETL.4396 | 40758512 | Marker (i.e. signs)-Steel | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
115650255 | T2 EI COLGATE-PALERMO-12/232 RPL POLE | 31472009 | COLGATE-PALERMO | 012/232 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.383509 | 39.3791 | ETL.6500 | 40767117 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
115650317 | T3 EI PRDSE-TBLE MTN 022/172L RPR GYWW | 43724325 | PARADISE-TABLE MTN | 022/172 | ICW | E | 2020_(1a) PSPS |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.599544 | 39.6936 | ETL.4316 | 44383223 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
115650404 | T2 EI KILARC-DESCHUTES A023/489 RPL PL | 31440586 | KILARC-DESCHUTES | A023/489 | 70Y | E | 2020_(1a) PSPS |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.250632 | 40.5639 | ETL.7300 | 40594917 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
115650529 | T2 EI PARADISE-TABLE MTN 24/182L REPL PL | 31453760 | PARADISE-TABLE MTN | 024/182 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [8 empty] | ETL.4316 | 44383234 | Structure-Wood | Rotten | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
115650539 | T2 EI PARADISE-TABLE MTN 24/182C REPL PL | 31453760 | PARADISE-TABLE MTN | 024/182 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [8 empty] | ETL.4316 | 44383235 | Structure-Wood | Rotten | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
115650555 | T2 EI COLCATE-PALERMO-012/235 RPL POLE | 31472009 | COLGATE-PALERMO | 012/235 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.38614 | 39.3794 | ETL.6500 | 40822495 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
115650557 | T2 EI COLGATE-PALERMO-12/234 REPAIR INSL | 43728969 | COLGATE-PALERMO | 012/234 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.385235 | 39.3793 | ETL.6500 | 40824152 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
115650558 | T2 EI COLGATE-PALERMO-12/234 RPL POLE | 31517754 | COLGATE-PALERMO | 012/234 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.385235 | 39.3793 | ETL.6500 | 40824152 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
115650561 | T2 EI COLGATE-PALERMO-12/233 RPL POLE | 31472009 | COLGATE-PALERMO | 012/233 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.384355 | 39.3792 | ETL.6500 | 40766476 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
115650569 | T2 EI PARADISE-TABLE MTN 25/192L RPL PL | 31453760 | PARADISE-TABLE MTN | 025/192 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.6579093 | 39.7015 | ETL.4316 | 44383250 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
115650650 | T2 EI PARADISE-BUTTE 5/058 PAINT STRS | 43758389 | PARADISE-BUTTE | 005/058 | ICS | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.669565 | 39.7109 | ETL.4396 | 41127253 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
115650721 | T2NT EI DUNLAP TAP 15/014 INST HV |  | DUNLAP TAP | 015/014 | ICW | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-119.031207 | 36.7075 | ETL.9061 | 40747119 | Marker (i.e. signs)-Wood | Missing | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Fresno |  | Y - 9
115650723 | T2 EI PARADISE-BUTTE 8/078 RPR GYWW | 43758389 | PARADISE-BUTTE | 008/078 | ICS | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.707534 | 39.7064 | ETL.4396 | 40618590 | Ground Wire-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
115650729 | T2 EI PARADISE-BUTTE 8/078 INSTL GMKS | 43758389 | PARADISE-BUTTE | 008/078 | ICS | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.707534 | 39.7064 | ETL.4396 | 40618590 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
115650814 | T2 EI PARADISE-BUTTE 8/078 INSTL MRKS | 43758389 | PARADISE-BUTTE | 008/078 | ICS | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.707534 | 39.7064 | ETL.4396 | 40618590 | Marker (i.e. signs)-Steel | No Good/Out of Stdrd | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
115650889 | T3 EI PRDSE-TBLE MTN 21/167 MRKR BALL | 43724325 | PARADISE-TABLE MTN | 021/167 | ICW | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.591285 | 39.6921 | ETL.4316 | 44712236 | FAA Lighting-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
115651060 | T2 EI PARADISE-TABLE MTN 24/188L RPL PL | 31453760 | PARADISE-TABLE MTN | 024/188 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.6518538 | 39.7009 | ETL.4316 | 44383247 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
115651176 | T2 EI KILARC-DESCHUTES A023/488 RPL PL | 31440586 | KILARC-DESCHUTES | A023/488 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.249914 | 40.5639 | ETL.7300 | 40864633 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
115651503 | MANTECA-LOUISE 001/037 REPLACE POLE | 31425591 | MANTECA-LOUISE | 001/037 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | Central | Non-WSIP | FSRP | [5 empty] | '-121.248711 | 37.812 | ETL.7470 | 40768622 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 5
115652279 | VALLEY SPRINGS #2 2/32 REPLACE POLE | 31431649 | VALLEY SPRINGS #2 | 002/032 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | Central | Non-WSIP | FSRP | [5 empty] | '-120.791403 | 38.2134 | ETL.9460 | 40907391 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 16
115652301 | VALLEY SPRINGS #2 2/46 REPLACE POLE | 31431649 | VALLEY SPRINGS #2 | 002/046 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | Central | Non-WSIP | FSRP | [5 empty] | '-120.800546 | 38.206 | ETL.9460 | 40907401 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 16
115652350 | T2 EI COLGATE-PALERMO-12/230 CANCEL | 43728969 | COLGATE-PALERMO | 012/230 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  | CANCEL/CNCL | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.381802 | 39.379 | ETL.6500 | 40672067 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
115652392 | T2 EI ELK-GUALALA 59/003 RPR GYWW | 43735921 | ELK-GUALALA | 059/003 | ICW | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.590239 | 38.8683 | ETL.8410 | 40667888 | Guy Wire-Wood | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-03-21
115652396 | T2 EI PARADISE-BUTTE 06/068 RPR PL | 43758389 | PARADISE-BUTTE | 006/068 | ICS | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.683961 | 39.7043 | ETL.4396 | 41127267 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
115652581 | T2 EI ELK-GUALALA 39/6 RPR SPLC | 43735736 | ELK-GUALALA | 039/006 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.698819 | 39.0933 | ETL.8410 | 40820732 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-03-21
115652582 | T2 EI ELK-GUALALA 39/8 RPL ANCH | 31431175 | ELK-GUALALA | 039/008 | 93E | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.698251 | 39.0922 | ETL.8410 | 40877405 | Anchor-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Lakeville |  |  | 2019-03-21
115653473 | T2 EI COLGATE-PALERMO 10/203 RPL POLE | 31506096 | COLGATE-PALERMO | 010/203 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.364803 | 39.3666 | ETL.6500 | 40815251 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
115655299 | T2 EI COLGATE-PALERMO 010/197 RPL STRW | 31423185 | COLGATE-PALERMO | 010/197 | 70Y | E | 2020_(1a) PSPS |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.360004 | 39.3641 | ETL.6500 | 40611003 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
115655434 | T2 EI MNDCNO-PHL JCT-HPLND 00/4 INS GYWW | 43731263 | MENDOCINO-PHILO JCT-HOPLAND | 000/004 | ICW | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | WSIP | FSRP | [5 empty] | '-123.194151 | 39.2497 | ETL.7520 | 40769897 | Guy Wire-Wood | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville
115655463 | T2 EI PARADISE-BUTTE 7/76B RPR GYWS | 43881381 | PARADISE-BUTTE | 007/076B | ICS | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.701932 | 39.7059 | ETL.4396 | 40758514 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
115655520 | T2 EI PRDS-BTT 007/076C RPR GYWS | 43758389 | PARADISE-BUTTE | 007/076C | ICS | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.701948 | 39.7058 | ETL.4396 | 44382704 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
115655526 | T2 EI PARADISE-BUTTE 007/076A RPR GYWS | 43758389 | PARADISE-BUTTE | 007/076A | ICS | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.7019 | 39.706 | ETL.4396 | 44382703 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
115655530 | T2NT EI PARADISE-BUTTE 007/076A INS GMKS | 43758389 | PARADISE-BUTTE | 007/076A | ICS | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.7019 | 39.706 | ETL.4396 | 44382703 | Marker (i.e. signs)-Steel | No Good/Out of Stdrd | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
115655671 | T3 EI PARADISE-TABLE MTN 16/134 RPR GYWW | 43724325 | PARADISE-TABLE MTN | 016/134 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.4994124 | 39.6792 | ETL.4316 | 44552419 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
115655714 | T3 EI PARADISE-TABLE MTN 16/134 CANCEL | 43724325 | PARADISE-TABLE MTN | 016/134 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  | CANCEL/CNCL | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.4994124 | 39.6792 | ETL.4316 | 44552419 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
115655779 | T2 EI CORDELIA #2 TAP 5/110 RPL POLE | 31433523 | CORDELIA #2 TAP | 005/110 | 93I | E | Pre-2020_(5) TD tag on other lines |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.187984 | 38.2523 | ETL.8184 | 40768057 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 372 | Sacramento |  |  | Yes
115655908 | T3 EI PARADISE-TABLE MTN 16/136R RPL PL | 31459421 | PARADISE-TABLE MTN | 016/136 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.50381 | 39.6798 | ETL.4316 | 44552464 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
115655966 | T3 EI PARADISE-TABLE MTN 16/136L RPL PL | 31459421 | PARADISE-TABLE MTN | 016/136 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.5038231 | 39.6798 | ETL.4316 | 44552371 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
115656021 | T3 EI GYSRS #7-EGLE RCK 00/005A RPR GRWW | 43693045 | GEYSERS #7-EAGLE ROCK | 000/005A | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.808631 | 38.8157 | ETL.1680 | 40576079 | Ground Wire-Wood | No Good/Out of Stdrd | Repair | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-07-19
115656151 | T2 DI CARIBOU-PALERMO 8/73 PAINT TOWER | 44056495 | CARIBOU-PALERMO | 008/073 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.52867 | 39.5783 | ETL.3190 | 40656339 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
115656186 | T2 DI CARIBOU PALERMO 14/118 PAINT TOWER | 44056495 | CARIBOU-PALERMO | 014/118 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.506733 | 39.6548 | ETL.3190 | 40913200 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
115656267 | T2 EI JEFFERSON-STANFORD 1/036 REPL POLE | 31426911 | JEFFERSON-STANFORD (NO FLY) | 001/036 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.261563 | 37.4615 | ETL.7220 | 40755284 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC erdy srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Bay |  | Y - 6
115656590 | T2 DI CARIBOU PALERMO 15/119 CORROSION S | 44056495 | CARIBOU-PALERMO | 015/119 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  |  | Check FDA | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.506565 | 39.6554 | ETL.3190 | 40913201 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
115656687 | T2 EI JEFFERSON-STANFORD 1/23 RPR INSW | 43752127 | JEFFERSON-STANFORD (NO FLY) | 001/023 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.269243 | 37.4614 | ETL.7220 | 40599123 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Bay |  | Y - Prog Multi | 2019-07-31
115656747 | T2 DI CARIBOU-PALERMO 5/51 RPL INS | 31423830 | CARIBOU-PALERMO | 005/051 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP |  |  |  | Field Operations |  | '-121.540459 | 39.5419 | ETL.3190 | 40617124 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC hold |  |  |  | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain
115656861 | T2 EI MENDCIN-PHL JCT-HPLND 4/0 RMV STUB | 43762361 | MENDOCINO-PHILO JCT-HOPLAND | 004/000 | ICW | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | WSIP | FSRP | [5 empty] | '-123.15516 | 39.2122 | ETL.7520 | 44140502 | Structure-Wood | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
115656863 | EI GLENN #2 026/486 RPR STRW | 43748401 | GLENN #2 | 026/486 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-122.012339 | 39.5284 | ETL.6930 | 44421367 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
115656903 | T2 DI CARIBOU-PALERMO 5/46 RPR INS | 31426498 | CARIBOU-PALERMO | 005/046 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.54042 | 39.5282 | ETL.3190 | 40816564 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain
115656910 | T2 EI COLGATE-PALERMO 12/244 RPL POLE | 31472009 | COLGATE-PALERMO | 012/244 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.393863 | 39.3813 | ETL.6500 | 40815255 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
115656911 | DISTRIBUTION RPL POLE |  | COLGATE-PALERMO | 013/259 | 70Y | E | 2020_(1a) PSPS |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.403219 | 39.3875 | ETL.6500 | 40873550 | Structure-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
115656971 | T2 DI CARIBOU-PALERMO- 5/45 RPL FNDTN |  | CARIBOU-PALERMO | 005/045 | 70S | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.540407 | 39.526 | ETL.3190 | 40755507 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLX | Pole Program | Capital | 426 | Table Mountain
115656975 | T2 DI CARIBOU PALERMO 12/101 RPL INS | 31426499 | CARIBOU-PALERMO | 012/101 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.515151 | 39.6251 | ETL.3190 | 41162739 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  | Yes
115657042 | T2 EI MNDCNO-PHL JCT-HPLND 1/11 INS GYWW | 43731263 | MENDOCINO-PHILO JCT-HOPLAND | 001/011 | ICW | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | WSIP | FSRP | [5 empty] | '-123.165327 | 39.2387 | ETL.7520 | 40584524 | Guy Wire-Wood | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville
115657146 | T2 DI CARIBOU-PALERMO 5/49 RPL INS | 31425651 | CARIBOU-PALERMO | 005/049 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.540447 | 39.5329 | ETL.3190 | 40870660 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain
115657177 | T2 DI CARIBOU PALERMO 15/122 RPL BOLTS | 43735847 | CARIBOU-PALERMO | 015/122 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.50374 | 39.6632 | ETL.3190 | 40913204 | Hardware-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
115657205 | T2 EI MNDCNO-PHL JCT-HPLND 1/9 INS GYWW | 43731263 | MENDOCINO-PHILO JCT-HOPLAND | 001/009 | ICW | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | WSIP | FSRP | [5 empty] | '-123.16894 | 39.2391 | ETL.7520 | 40875541 | Guy Wire-Wood | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville
115657364 | T2 DI CARIBOU PALERMO 10/90 RPL INS | 31426588 | CARIBOU-PALERMO | 010/090 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.521192 | 39.6038 | ETL.3190 | 40599266 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC hold |  |  |  | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  | Yes
115657366 | T2 DI CARIBOU PALERMO 12/105 RPL INS | 31426498 | CARIBOU-PALERMO | 012/105 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.51301 | 39.6326 | ETL.3190 | 40765166 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  | Yes
115657534 | T2 DI CARIBOU-PALERMO-8/66 TWR RPL FNDTN |  | CARIBOU-PALERMO | 008/066 | 70S | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.532889 | 39.5648 | ETL.3190 | 40816568 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLX | Pole Program | Capital | 426 | Table Mountain
115657726 | T2 DI CARIBOU-PALERMO TWR 10/86 RPL HRDW | 43659205 | CARIBOU-PALERMO | 010/086 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.523581 | 39.5954 | ETL.3190 | 40816572 | Hardware-Steel | No Good/Out of Stdrd | Replace | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
115657896 | T2 DI CARIBOU-PALERMO 08/66 RPR STUB | 44056495 | CARIBOU-PALERMO | 008/066 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  | Check FDA | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.532889 | 39.5648 | ETL.3190 | 40816568 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115657933 | T2 DI CARIBOU-PALERMO 15/122 RPR FNDTN | 44056495 | CARIBOU-PALERMO | 015/122 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.50374 | 39.6632 | ETL.3190 | 40913204 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
115657936 | T2 DI CARIBOU-PALERMO 11/97 RPL AUT SPL | 43659205 | CARIBOU-PALERMO | 011/097 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.516966 | 39.6187 | ETL.3190 | 40815580 | Conductor-Steel | No Good/Out of Stdrd | Repair | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
115657991 | T2 DI CARIBOU PALERMO 10/88 RPL INS | 31425651 | CARIBOU-PALERMO | 010/088 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.522492 | 39.5992 | ETL.3190 | 40867947 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  | Yes
115658016 | T2 DI CARIBOU PALERMO 11/95 RPL HRDWR | 43659205 | CARIBOU-PALERMO | 011/095 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.518138 | 39.6146 | ETL.3190 | 40755509 | Hardware-Steel | No Good/Out of Stdrd | Replace | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
115658030 | T2 DI CARIBOU PALERMO 11/93 RPR FNDTN | 44056495 | CARIBOU-PALERMO | 011/093 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.519401 | 39.6101 | ETL.3190 | 40656343 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
115658033 | T2 DI CARIBOU PALERMO 10/91 RPL HRDWR | 43659205 | CARIBOU-PALERMO | 010/091 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.520902 | 39.6048 | ETL.3190 | 40591547 | Hardware-Steel | No Good/Out of Stdrd | Replace | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
115658045 | T2 DI CARIBOU PALERMO 10/92 RPL HRDWR | 43659205 | CARIBOU-PALERMO | 010/092 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.520289 | 39.607 | ETL.3190 | 40689954 | Hardware-Steel | No Good/Out of Stdrd | Replace | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
115658156 | T2 EI KILARC-DESCHUTES A024/506 RFRM | 31498148 | KILARC-DESCHUTES | A024/506 | 93E | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.265184 | 40.5669 | ETL.7300 | 40878612 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 637 | Table Mountain |  |  | Yes
115659152 | T2 EI PARADISE-BUTTE 7/76B INS MRKS | 43758389 | PARADISE-BUTTE | 007/076B | ICS | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.701932 | 39.7059 | ETL.4396 | 40758514 | Marker (i.e. signs)-Steel | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
115659159 | T2 EI KILARC-DESCHUTES A024/509 RPL PL | 31440586 | KILARC-DESCHUTES | A024/509 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.267598 | 40.5678 | ETL.7300 | 40602862 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
115659399 | T3 DI CARIBOU PALERMO 16/128 RPR HRDWR | 43735847 | CARIBOU-PALERMO | 016/128 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.493962 | 39.6754 | ETL.3190 | 41162782 | Hardware-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain
115659423 | T2 DI CARIBOU-PALERMO-011/100 RPL INSUL | 31426588 | CARIBOU-PALERMO | 011/100 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.515658 | 39.6233 | ETL.3190 | 40599269 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC hold |  |  |  | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  | Yes
115659468 | T2 DI CARIBOU-PALERMO 10/85 RPL INS | 31426498 | CARIBOU-PALERMO | 010/085 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.523861 | 39.5944 | ETL.3190 | 40761090 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  | Yes
115659580 | T3 DI CARIBOU-PALERMO 16/128 RPR INS | 43735847 | CARIBOU-PALERMO | 016/128 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.493962 | 39.6754 | ETL.3190 | 41162782 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain
115659705 | T2 DI CARIBOU PALERMO 11/100 RPL INS | 31423830 | CARIBOU-PALERMO | 011/100 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.515658 | 39.6233 | ETL.3190 | 40599269 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC hold |  |  |  | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  | Yes
115659733 | T2 EI CRDLA #2 TAP 003/057 RPL POLE | 31460585 | CORDELIA #2 TAP | 003/057 | 70Y | E | 2020_(1a) PSPS |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.147225 | 38.2411 | ETL.8184 | 40612468 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento
115659873 | T2 EI COTTONWOOD-DELEVAN #1 007/049 DMP | 43726632 | COTTONWOOD-DELEVAN #1 | 007/049 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.268085 | 40.2928 | ETL.4550 | 44233320 | Damper-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
115659923 | T2 DI CARIBOU-PALERMO TWR 14/117 RPL HRW | 43735847 | CARIBOU-PALERMO | 014/117 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.507554 | 39.6519 | ETL.3190 | 40913199 | Hardware-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
115660084 | T2 EI OCEANO-CAL 19/127 RPR GYWW | 43689786 | OCEANO-CALLENDAR SW STA | 019/127 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | South | WSIP | FSRP | Completed |  |  |  |  | '-120.57744 | 35.1003 | ETL.2394 | 40809743 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - 6 | 00/00/0000
115660416 | T2 EI MENDOCINO-PHILO 11/8 RPL POLE | 31471950 | MENDOCINO-PHILO JCT-HOPLAND | 011/008 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.156625 | 39.106 | ETL.7520 | 40860850 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  | 2020-06-04
115660713 | T2 DI DRM-GRSS VLLY WMR 14/333 RPR WPH | 43746391 | DRUM-GRASS VALLEY-WEIMAR | 014/333 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-120.942933 | 39.1254 | ETL.6760 | 40867122 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Sacramento |  |  | Yes
115661151 | T2 EI OCEANO-CAL 21/154 RPL POLE | 31426920 | OCEANO-CALLENDAR SW STA | 021/154 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | South | WSIP | FSRP | [5 empty] | '-120.582418 | 35.0761 | ETL.2394 | 40590137 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Pismo Beach |  | Y - 6
115661368 | T2 EI CLGTE-PLRMO 019/381 RPL SPLW | 43728970 | COLGATE-PALERMO | 019/381 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.464652 | 39.4466 | ETL.6500 | 40757211 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
115661772 | T2 EI CLLNDR SW STA-MSA 004/073 RPL STRW | 31426164 | CALLENDAR SW STA-MESA | 004/073 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | South | WSIP | FSRP | [5 empty] | '-120.512083 | 35.0528 | ETL.1210 | 40751944 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC crdy srdy |  |  |  | PEND | LC | TLX | Pole Program | Capital | 372 | Pismo Beach |  | Y - 4
115662162 | T2 EI CLGTE-PLRMO 017/353 RPR STRW | 43728970 | COLGATE-PALERMO | 017/353 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.441702 | 39.4426 | ETL.6500 | 40866833 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
115662321 | EI CALLENDER SS-MESA 1/21 REPL SPLICE | 43686102 | CALLENDAR SW STA-MESA | 001/021 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | South | WSIP | [6 empty] | '-120.570748 | 35.051 | ETL.1210 | 40618576 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - 4
115670784 | T2 DI DRM-GRSS VLLY-WMR 15/348 RPL SPLCE | 43746394 | DRUM-GRASS VALLEY-WEIMAR | 015/348 | ICW | E | 2020_(1a) PSPS |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.950421 | 39.1183 | ETL.6760 | 40598931 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Sacramento |  |  | Yes
115671028 | T2 EI COTTONWD-RED BLF 014/286 RPR STRW | 43744380 | COTTONWOOD-RED BLUFF | 014/286 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.255555 | 40.2195 | ETL.6660 | 40909622 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
115671126 | T2 EI COTTONWOOD-PAN 000/015 REPR INSW | 43881008 | COTTONWOOD-PANORAMA | 000/015 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.267411 | 40.4131 | ETL.1340 | 40600908 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
115671221 | T2 EI SN LUS OBSPO-OCNO 019/113 WSH INSW | 44585464 | SAN LUIS OBISPO-OCEANO | 019/113 | ICD | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-120.5731258 | 35.0983 | ETL.3530 | 40678317 | Insulator | Contaminated | Ground Wash | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 622 | Pismo Beach
115671290 | T2 EI DUNLAP TAP 12/2 RPLC CRSW | 31426901 | DUNLAP TAP | 012/002 | 93E | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-119.090968 | 36.6812 | ETL.9061 | 40685439 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Fresno |  | Y - 9 | LNW
115671291 | T2 EI COTTONWOOD-PAN 000/003 RPR INSW | 43881008 | COTTONWOOD-PANORAMA | 000/003 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.267204 | 40.4019 | ETL.1340 | 40655968 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
115671459 | T2NT DI DRM-GRS VLY-WMR B016/368 RPR MKR | 43746394 | DRUM-GRASS VALLEY-WEIMAR | B016/368 | ICW | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.958042 | 39.121 | ETL.6760 | 40767280 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Sacramento |  |  | Yes
115671668 | T2 EI COTTONWOOD-PAN 000/002 RPR INSW | 43881008 | COTTONWOOD-PANORAMA | 000/002 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.267306 | 40.401 | ETL.1340 | 40674162 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
115672588 | T2 DI CARIBOU-PALERMO 13/114 RPR CNDCTR | 43659205 | CARIBOU-PALERMO | 013/114 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.509255 | 39.6459 | ETL.3190 | 40762753 | Conductor-Steel | No Good/Out of Stdrd | Repair | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
115672614 | T2 DI CARIBOU-PALERMO 13/114 RPR INSL CP | 43659205 | CARIBOU-PALERMO | 013/114 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.509255 | 39.6459 | ETL.3190 | 40762753 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
115672736 | T2NT EI COLGATE-PALRMO 20/409 RPL PL | 31505737 | COLGATE-PALERMO | 020/409 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.489608 | 39.4531 | ETL.6500 | 40664454 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Need New ERTC
115672763 | T2 DI CARIBOU-PALERMO 13/113 RPR INSULTR | 43659205 | CARIBOU-PALERMO | 013/113 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.509591 | 39.6447 | ETL.3190 | 40656347 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
115672764 | T2 EI COLGATE-PALERMO 020/408 REPL PL | 31423185 | COLGATE-PALERMO | 020/408 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.488785 | 39.4529 | ETL.6500 | 40672097 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
115672784 | T2 EI COLGATE-PALERMO 017/346 RPL POLE | 31423185 | COLGATE-PALERMO | 017/346 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.43732 | 39.4388 | ETL.6500 | 40590395 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
115672805 | T2 EI COTTONWOOD-PAN 001/021 REPR INSW | 43881008 | COTTONWOOD-PANORAMA | 001/021 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.26533 | 40.4178 | ETL.1340 | 40804914 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
115672809 | T2 DI CARIBOU-PALERMO 11/97 RPR BUR FOOT | 44056495 | CARIBOU-PALERMO | 011/097 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.516966 | 39.6187 | ETL.3190 | 40815580 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
115672994 | T3 DI CARIBOU-PALMERO 16/127 RPL STRCTUR |  | CARIBOU-PALERMO | 016/127 | 70S | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.495461 | 39.6739 | ETL.3190 | 41162781 | Structure-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLX | Pole Program | Capital | 426 | Table Mountain
115673089 | T2NT DI CRBOU-PALERMO TWR 14/118 RPL SGN | 43659209 | CARIBOU-PALERMO | 014/118 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.506733 | 39.6548 | ETL.3190 | 40913200 | Marker (i.e. signs)-Steel | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115673220 | T2 EI COTTONWOOD-PAN 002/032 RPR INSW | 43881008 | COTTONWOOD-PANORAMA | 002/032 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-122.266086 | 40.4272 | ETL.1340 | 40591236 | Insulator Bond Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
115673236 | T2 DI CARIBOU-PALERMO 11/100 RPR STRCTUR | 43725390 | CARIBOU-PALERMO | 011/100 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  |  | Check FDA | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.515658 | 39.6233 | ETL.3190 | 40599269 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
115673332 | EI PALERMO-WYANDOTTE 001/015 REPL HRDS | 43754992 | PALERMO-WYANDOTTE | 001/015 | ICS | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-121.539609 | 39.4733 | ETL.4315 | 40757544 | Hardware-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
115673434 | T2 EI PARADISE-TBL MTN 006/057 REPL SPLS | 43727174 | PARADISE-TABLE MTN | 006/057 | ICS | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.537029 | 39.5503 | ETL.4316 | 40821426 | Splice-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
115673475 | T2 DI CARIBOU-PALERMO 13/112 RPR TWR | 44056495 | CARIBOU-PALERMO | 013/112 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.510109 | 39.6429 | ETL.3190 | 40668745 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
115673587 | STOCKTON A-WEBER#2 A005/157 RPL POLE | 31476291 | STOCKTON "A"-WEBER #2+ (NO FLY) | A005/157 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | Central | Non-WSIP | [6 empty] | '-121.29758 | 37.9668 | ETL.8130 | 40613380 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 2
115673628 | T2 DI CARIBOU-PALERMO TWR 15/121 RPL INS | 31426499 | CARIBOU-PALERMO | 015/121 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.505729 | 39.6583 | ETL.3190 | 40913203 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  | Yes
115673640 | T2NT DI DRM-GRSS VALLY-MR B16/362 RPL HV | 43746394 | DRUM-GRASS VALLEY-WEIMAR | B016/362 | ICW | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.956069 | 39.1183 | ETL.6760 | 40874756 | Marker (i.e. signs)-Wood | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Sacramento |  |  | Yes
115673654 | T3 DI CARIBOU-PALMERO 16/128 RPR FNDTN | 43735848 | CARIBOU-PALERMO | 016/128 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.493962 | 39.6754 | ETL.3190 | 41162782 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115673657 | T2 DI CARIBOU-PALERMO TWR 15/121 RPL | 31426499 | CARIBOU-PALERMO | 015/121 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.505729 | 39.6583 | ETL.3190 | 40913203 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  | Yes
115673674 | T2 EI COTTONWOOD-PAN 001/026 RPR INSW | 43881008 | COTTONWOOD-PANORAMA | 001/026 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.264002 | 40.4222 | ETL.1340 | 40591235 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
115673682 | T2 DI CARIBOU-PALERMO TWR 15/121 RPR FND | 44056495 | CARIBOU-PALERMO | 015/121 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.505729 | 39.6583 | ETL.3190 | 40913203 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
115673683 | T2 DI CARIBOU-PALERMO 5/48 RPL INS | 31426491 | CARIBOU-PALERMO | 005/048 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.540439 | 39.5316 | ETL.3190 | 40865368 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC hold |  |  |  | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain
115673686 | T2 DI CARIBOU-PALERMO TWR 15/121 RPL HRD | 43735847 | CARIBOU-PALERMO | 015/121 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.505729 | 39.6583 | ETL.3190 | 40913203 | Hardware-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
115673930 | T2 COTTONWOOD-PAN 001/027 RPR INSW | 43881008 | COTTONWOOD-PANORAMA | 001/027 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.263981 | 40.4235 | ETL.1340 | 40683759 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
115673951 | T2 DI CARIBOU-PALERMO TWR 15/121 RPL HRD | 44056495 | CARIBOU-PALERMO | 015/121 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  |  | Check FDA | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.505729 | 39.6583 | ETL.3190 | 40913203 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
115673952 | T3 DI CARIBOU-PALMERO 16/130 RPL INSS | 31426499 | CARIBOU-PALERMO | 016/130 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.491961 | 39.6772 | ETL.3190 | 41162784 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain
115673989 | T2 DI CARIBOU-PALERMO 6/57 RPL INS | 31426498 | CARIBOU-PALERMO | 006/057 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.537334 | 39.5499 | ETL.3190 | 40815577 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  | Yes
115674142 | T2 DI CARIBOU-PALERMO 6/58 RPL SPLICES | 43659205 | CARIBOU-PALERMO | 006/058 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.537213 | 39.5503 | ETL.3190 | 40873686 | Splice-Steel | No Good/Out of Stdrd | Replace | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
115674167 | T2 DI CARIBOU-PALERMO 13/113 RPR HRDWARE | 44056495 | CARIBOU-PALERMO | 013/113 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.509591 | 39.6447 | ETL.3190 | 40656347 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
115675198 | T3 EI CNTRVLL-TBL MTN 003/057 RPL COND | 43724228 | CENTERVILLE-TABLE MTN | 003/057 | ICS | E | Pre-2020_(5) TD tag on other lines |  |  | Likely MAT error - delink to correct | TR3 | LATE | North Valley | WSIP |  |  |  |  | Material & Equipment | Material unavailable | '-121.691357 | 39.7468 | ETL.6320 | 44673294 | Conductor-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
115675932 | T2 EI COTTONWOOD-PAN 001/022 RPR GYWW | 43881008 | COTTONWOOD-PANORAMA | 001/022 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.264065 | 40.4184 | ETL.1340 | 40819247 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
115676366 | T2 DI CARIBOU-PALERMO 4/43 RMV VEG | 43659205 | CARIBOU-PALERMO | 004/043 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  | Likely veg | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.540099 | 39.5226 | ETL.3190 | 40656338 | Structure-Steel | Debris/Nest/etc. | Remove | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
115676555 | T2 EI CRIBU-PLERM 4/42 RPR INSS | 44304495 | CARIBOU-PALERMO | 004/042 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.539985 | 39.5213 | ETL.3190 | 40668737 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
115676582 | T2 EI CRIBU-PLERM 4/42 RPR FOND | 44057199 | CARIBOU-PALERMO | 004/042 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.539985 | 39.5213 | ETL.3190 | 40668737 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
115676592 | T2 EI CRIBU-PLERM 4/42 RPR STRT | 44057199 | CARIBOU-PALERMO | 004/042 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.539985 | 39.5213 | ETL.3190 | 40668737 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
115676601 | T2NT EI CRIBU-PLERM 4/42 RPR STRT | 44057199 | CARIBOU-PALERMO | 004/042 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.539985 | 39.5213 | ETL.3190 | 40668737 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
115676611 | T2 EI CARIBOU-PALERMO 4/041 RPR FOND | 44057199 | CARIBOU-PALERMO | 004/041 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.539984 | 39.5205 | ETL.3190 | 40595036 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
115676688 | T2 DI CARIBOU-PALERMO 8/73 RPL ANTIGRD | 31460573 | CARIBOU-PALERMO | 008/073 | 93A | F | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.52867 | 39.5783 | ETL.3190 | 40656339 | Structure-Tower | Anti-Climbing Guard | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Capital | 988 | Table Mountain |  |  | Yes
115676812 | T2 DI CARIBOU-PALERMO 8/66 RPR XARM | 43659205 | CARIBOU-PALERMO | 008/066 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.532889 | 39.5648 | ETL.3190 | 40816568 | Crossarm-Steel | No Good/Out of Stdrd | Repair | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain
115676818 | T2 DI CARIBOU-PALERMO TWR 4/41 RPL NSLTR | 31423830 | CARIBOU-PALERMO | 004/041 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.539984 | 39.5205 | ETL.3190 | 40595036 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC hold |  |  |  | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  | Yes
115676873 | T2 DI CARIBOU-PALERMO 9/81 RPL TWR NO | 43725390 | CARIBOU-PALERMO | 009/081 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.52542 | 39.5889 | ETL.3190 | 40597207 | Hardware-Tower | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
115676876 | T2 DI CARIBOU-PALERMO 9/81 RPL ANTIGRD | 31460573 | CARIBOU-PALERMO | 009/081 | 93A | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.52542 | 39.5889 | ETL.3190 | 40597207 | Structure-Tower | Anti-Climbing Guard | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Capital | 988 | Table Mountain |  |  | Yes
115676991 | T2 EI CARIBOU-PALERMO 11/96 RPR MEMBER | 44057199 | CARIBOU-PALERMO | 011/096 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.517387 | 39.6172 | ETL.3190 | 40816574 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
115676999 | T2 DI CARIBOU-PALERMO TWR 5/46 PNT TWR | 44056495 | CARIBOU-PALERMO | 005/046 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.54042 | 39.5282 | ETL.3190 | 40816564 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115677053 | T3 EI CRIBU-PLERM :36/295 SRTT-RMV SOIL | 44051417 | CARIBOU-PALERMO | :036/295 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  | Likely MAT error - delink to correct | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.484689 | 39.6927 | ETL.3190 | 40755760 | Structure-Tower | Soil | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 543 | Table Mountain |  |  | Yes
115677070 | T2 EI CARIBOU-PALERMO 4/43 RPR STRT | 44057199 | CARIBOU-PALERMO | 004/043 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.540099 | 39.5226 | ETL.3190 | 40656338 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
115677221 | T2 DI CARIBOU-PALERMO 9/78 RPR HW INSLTR | 44056495 | CARIBOU-PALERMO | 009/078 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.526702 | 39.5847 | ETL.3190 | 40871570 | Hardware-Tower | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
115677251 | T2 EI NEWARK-LIVERMORE 17/110 RPR SPLC | 43752138 | NEWARK-LIVERMORE | 017/110 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | Central | WSIP | FSRP | [5 empty] | '-121.783096 | 37.6462 | ETL.7660 | 40580692 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Bay |  | Y - 8
115677354 | T2 DI CARIBOU-PALERMO 8/73 RPR CORROSION | 44056495 | CARIBOU-PALERMO | 008/073 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.52867 | 39.5783 | ETL.3190 | 40656339 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
115677389 | T2 DI CARIBOU-PALERMO 11/93 RPL HRDWR | 44056495 | CARIBOU-PALERMO | 011/093 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.519401 | 39.6101 | ETL.3190 | 40656343 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
115677391 | T2 EI CBRLL-SNT YNZ SW STA 7/63 RPL INSS | 31498014 | CABRILLO-SANTA YNEZ SW STA | 007/063 | 93I | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | South | WSIP | FSRP | [5 empty] | '-120.3073412 | 34.6499 | ETL.1200 | 40836545 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Pismo Beach |  | Y - 9
115677403 | T2 DI CARIBOU-PALERMO 5/46 INSTL CL GR | 31460573 | CARIBOU-PALERMO | 005/046 | 93A | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.54042 | 39.5282 | ETL.3190 | 40816564 | Structure-Tower | Anti-Climbing Guard | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Capital | 988 | Table Mountain
115677449 | T2 EI CARIBOU-PALERMO 004/044 INST HRDT | 44057199 | CARIBOU-PALERMO | 004/044 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.540274 | 39.5245 | ETL.3190 | 40758609 | Hardware-Tower | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
115677464 | T2 DI CARIBOU-PALERMO 12/110 RPR STRCTR | 43725390 | CARIBOU-PALERMO | 012/110 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.511297 | 39.6387 | ETL.3190 | 40607817 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
115677597 | T2CARIBOU-PALERMO 011/097 RPR CONDUCTOR | 44304495 | CARIBOU-PALERMO | 011/097 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.516966 | 39.6187 | ETL.3190 | 40815580 | Conductor-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
115677603 | T2 DI CARIBOU-PALERMO 0/3 RPL INSULATOR | 31426591 | CARIBOU-PALERMO | 000/003 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.523682 | 39.4544 | ETL.3190 | 40663305 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  | Yes
115677606 | T2 DI CARIBOU-PALERMO 6/55 RPL ANTIGRD | 31460573 | CARIBOU-PALERMO | 006/055 | 93A | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.538613 | 39.5459 | ETL.3190 | 40765164 | Structure-Tower | Anti-Climbing Guard | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Capital | 988 | Table Mountain
115677609 | T2 DI CARIBOU-PALERMO 4/42 REMOVE VEG | 44056495 | CARIBOU-PALERMO | 004/042 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  |  | Likely veg | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.539985 | 39.5213 | ETL.3190 | 40668737 | Structure-Steel | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
115677627 | T2 EI CARIBOU-PALERMO 11/97 REPL INSS |  | CARIBOU-PALERMO | 011/097 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.516966 | 39.6187 | ETL.3190 | 40815580 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  | Yes
115677676 | T3 EI CARIBOU-PLRMO :036/294 RPL INSS | 31426498 | CARIBOU-PALERMO | :036/294 | 93K | E | Pre-2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.484451 | 39.6942 | ETL.3190 | 40771762 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  | Yes
115677841 | T2 EI PARADISE-TABLE MTN 5/44 RPR SPLC | 43727174 | PARADISE-TABLE MTN | 005/044 | ICS | E | 2020_(1a) PSPS |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.540219 | 39.526 | ETL.4316 | 41101723 | Splice-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
115677860 | T2 EI PARADISE-TABLE MTN 5/44 RPL INSS | 31451270 | PARADISE-TABLE MTN | 005/044 | 93K | E | 2020_(1a) PSPS |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.5402324 | 39.526 | ETL.4316 | 40785398 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  | Yes
115677903 | T2 DI CARIBOU-PALERMO 12/106 RPL HRDWR | 44056495 | CARIBOU-PALERMO | 012/106 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.512607 | 39.6341 | ETL.3190 | 40813695 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
115677979 | EI CNTRVLLE TBL MTN 10/196 RPL INSW | 31431540 | CENTERVILLE-TABLE MTN-OROVILLE | 010/196 | 93I | F | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.6344857 | 39.6494 | ETL.6330 | 40634482 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 508 | Table Mountain |  |  | Yes
115678063 | EI CNTRVILE-TBL MTN-ORVLL 9/195 CANCEL | 43721205 | CENTERVILLE-TABLE MTN-OROVILLE | 009/195 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  | CANCEL/CNCL |  | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.634668 | 39.6501 | ETL.6330 | 40873516 | Conductor-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
115678091 | EI CNTVLLE TBL-MTN 9/195 RPL INSW | 31431540 | CENTERVILLE-TABLE MTN-OROVILLE | 009/195 | 93I | F | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.6346792 | 39.6501 | ETL.6330 | 40897922 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 508 | Table Mountain |  |  | Yes
115678170 | T2 DI CARIBOU-PALERMO 12/110 RPL SPLICE | 43659205 | CARIBOU-PALERMO | 012/110 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.511297 | 39.6387 | ETL.3190 | 40607817 | Splice-Steel | No Good/Out of Stdrd | Replace | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
115678490 | T2 EI TRNTY-MPL CRK 17/001C RPL STRW | 31471999 | TRINITY-MAPLE CREEK | 017/001C | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.209491 | 40.7416 | ETL.8170 | 41115572 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2020-04-23
115678990 | T3 EI CARIBOU-PALERMO :037/299 FOND | 44051417 | CARIBOU-PALERMO | :037/299 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.486332 | 39.6826 | ETL.3190 | 40913194 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
115678991 | T3 EI CARIBOU-PLRMO :037/300A RPR JUMP | 43659205 | CARIBOU-PALERMO | :037/300A | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.486615 | 39.6812 | ETL.3190 | 40913195 | Jumper-Steel | No Good/Out of Stdrd | Repair | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
115678992 | T3 EI CARIBOU-PALERMO :37/300A RPR GYWS | 43659205 | CARIBOU-PALERMO | :037/300A | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.486615 | 39.6812 | ETL.3190 | 40913195 | Guy Wire-Steel | Missing | Install | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
115679173 | T3 EI CRBOU-PLRMO 016/130 RPL INSS | 31426499 | CARIBOU-PALERMO | 016/130 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.491961 | 39.6772 | ETL.3190 | 41162784 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain
115679180 | T3NT EI CRBOU-PLRMO 016/130 INS MRKS | 44057199 | CARIBOU-PALERMO | 016/130 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  |  | Likely MAT error - delink to correct | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.491961 | 39.6772 | ETL.3190 | 41162784 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
115679202 | T2 EI CNTRVLL-TBL MTN-RVLL 9/189 RPR PL | 43721205 | CENTERVILLE-TABLE MTN-OROVILLE | 009/189 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.635872 | 39.6542 | ETL.6330 | 40664419 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
115679243 | T3NT EI CRBOU-PLRMO 016/130 INS GMKS | 44070463 | CARIBOU-PALERMO | 016/130 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.491961 | 39.6772 | ETL.3190 | 41162784 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
115679417 | T2 EI CARIBOU-PALERMO 7/065 RPR SPLS | 44304495 | CARIBOU-PALERMO | 007/065 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.533674 | 39.5619 | ETL.3190 | 40758457 | Splice-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain
115679439 | T2 EI CARIBOU-PALERMO 7/065 RPR SHIELD | 44304495 | CARIBOU-PALERMO | 007/065 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.533674 | 39.5619 | ETL.3190 | 40758457 | Shield Wire / OPGW-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Table Mountain |  |  | Yes
115679447 | T2 EI PARADISE-TABLE MTN 05/045 RPL HRDT | 43727174 | PARADISE-TABLE MTN | 005/045 | ICS | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.54023 | 39.528 | ETL.4316 | 40765159 | Hardware-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
115679448 | T2 EI CARIBOU-PALERMO 7/065 RPL INSS |  | CARIBOU-PALERMO | 007/065 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.533674 | 39.5619 | ETL.3190 | 40758457 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  | Yes
115679455 | T2 EI CARIBOU-PALERMO 7/065 RPR FOND | 44057199 | CARIBOU-PALERMO | 007/065 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.533674 | 39.5619 | ETL.3190 | 40758457 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
115679474 | T2 EI PARADISE-TABLE 005/046 RPR COND | 43727174 | PARADISE-TABLE MTN | 005/046 | ICS | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.540244 | 39.5301 | ETL.4316 | 40816518 | Conductor-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
115679534 | T3NT EI CARIBOU-PALERMO 16/128 INS MRKS | 44057199 | CARIBOU-PALERMO | 016/128 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  |  | Likely MAT error - delink to correct | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.493962 | 39.6754 | ETL.3190 | 41162782 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115679692 | DISTRIBUTION SLO SM | 31427096 | SAN LUIS OBISPO-SANTA MARIA (IDLE) | 012/226 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  |  |  |  | LATE | South | WSIP | FSRP | [5 empty] | '-120.50648 | 35.1337 | ETL.9100 | 44191938 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Pismo Beach
115679699 | T2 EI POE-RIO OSO 026/169 RPL INSS | 31431911 | POE-RIO OSO | 026/169 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.516909 | 39.6212 | ETL.5540 | 40889529 | Insulator-Steel | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  | Yes
115679767 | DISTRIBUTION GUY |  | SAN LUIS OBISPO-SANTA MARIA (IDLE) | 012/225 | ICW | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | South | WSIP | FSRP | [5 empty] | '-120.506109 | 35.1344 | ETL.9100 | 44191207 | Guy Wire-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach
115679818 | T2 EI PARADISE-TABLE MTN 5/047 RPR INSS | 43727174 | PARADISE-TABLE MTN | 005/047 | ICS | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.540254 | 39.5316 | ETL.4316 | 40815542 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
115679823 | T2 EI CARIBOU-PALERMO 005/048 RPR FOND | 44057199 | CARIBOU-PALERMO | 005/048 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.540439 | 39.5316 | ETL.3190 | 40865368 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115679825 | T2 EI PARADISE-TABLE 005/046 RPL INSS | 43727174 | PARADISE-TABLE MTN | 005/046 | ICS | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.540244 | 39.5301 | ETL.4316 | 40816518 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
115679842 | T2NT EI CARIBOU-PALERMO 005/048 REPAINT | 44302715 | CARIBOU-PALERMO | 005/048 | ICS | F | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.540439 | 39.5316 | ETL.3190 | 40865368 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Table Mountain
115679919 | T3NT EI CARIBOU-PALERMO 16/127 INST MRKS | 44302715 | CARIBOU-PALERMO | 016/127 | ICS | F | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.495461 | 39.6739 | ETL.3190 | 41162781 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Table Mountain
115680074 | T2 EI CARIBOU-PALERMO 05/049 RPR FOND | 44057199 | CARIBOU-PALERMO | 005/049 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.540447 | 39.5329 | ETL.3190 | 40870660 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115680165 | T2 EI PARADISE-TABLE MTN 5/048 RPR CONS | 43727174 | PARADISE-TABLE MTN | 005/048 | ICS | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.54026 | 39.5329 | ETL.4316 | 40871564 | Conductor-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
115680182 | T2 EI CARIBOU-PALERMO 005/050 RPL MEMBER | 44057199 | CARIBOU-PALERMO | 005/050 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.540468 | 39.5359 | ETL.3190 | 40599254 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115680192 | T2 EI CARIBOU-PALERMO 005/050 RPL INSS |  | CARIBOU-PALERMO | 005/050 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.540468 | 39.5359 | ETL.3190 | 40599254 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain
115680197 | T2 EI CARIBOU-PALERMO 006/057 RPR FOND |  | CARIBOU-PALERMO | 006/057 | 70S | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.537334 | 39.5499 | ETL.3190 | 40815577 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Pole Program | Capital | 426 | Table Mountain |  |  | Yes
115680222 | T2 PARADISE-TABLE MTN 005/049 RPR INSS | 43727174 | PARADISE-TABLE MTN | 005/049 | ICS | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.54028 | 39.5358 | ETL.4316 | 40867305 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
115680228 | T2 EI CARIBOU-PALERMO 006/057 RPR SHIELD | 44304495 | CARIBOU-PALERMO | 006/057 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.537334 | 39.5499 | ETL.3190 | 40815577 | Shield Wire / OPGW-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Table Mountain |  |  | Yes
115680354 | DISTRIBUTION RPR BNDW | 43686013 | SAN LUIS OBISPO-SANTA MARIA (IDLE) | 012/220 | ICW | E | Pre-2020_(1b) Lines with special commitments |  |  |  |  | LATE | South | WSIP | FSRP | [5 empty] | '-120.509786 | 35.1347 | ETL.9100 | 42574223 | Ground Wire-Wood | No Good/Out of Stdrd | Repair | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - 4
115680358 | T2 HUMBOLDT_TRINITY 060/001 RPR HRDW | 43729542 | HUMBOLDT-TRINITY | 060/001 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.1679194 | 40.7509 | ETL.1820 | 44565330 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2019-08-09
115680371 | T2 EI CNTRVILLE-TBLE MTN 4/70 RPR SPLC | 43724253 | CENTERVILLE-TABLE MTN | 004/070 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.70393 | 39.7365 | ETL.6320 | 40758778 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
115680377 | T2 EI TRINITY-MAPLE C 014/005 RPL POLE | 31440262 | TRINITY-MAPLE CREEK | 014/005 | 70Y | E | Pre-2020_(2) High fire spread TD |  |  |  | TR2 | LATE | North Coast | WSIP |  |  |  |  | Weather | AT RISK - weather impacts | '-123.166325 | 40.7523 | ETL.8170 | 40761910 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2019-11-14
115680395 | T3 EI CARIBOU-PALERMO :032/259 INST HRDT | 44051417 | CARIBOU-PALERMO | :032/259 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.473027 | 39.7568 | ETL.3190 | 40876880 | Hardware-Tower | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
115680401 | T3 EI CARIBOU-PLERMO :032/259 RPL INSS | 31425651 | CARIBOU-PALERMO | :032/259 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.473027 | 39.7568 | ETL.3190 | 40876880 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  | Yes
115680643 | T2 EI CNTRVL-TBL MTN-RVL 10/200 RPR COND | 43721205 | CENTERVILLE-TABLE MTN-OROVILLE | 010/200 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.633663 | 39.6467 | ETL.6330 | 40767069 | Conductor-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
115680659 | T3NT EI CLOVER CREEK TAP A005/128 INS PN | 43743031 | CLOVER CREEK TAP | A005/128 | ICW | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.972443 | 40.7083 | ETL.7291 | 42712147 | Marker (i.e. signs)-Wood | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
115680776 | T2 EI CTTNWD-RD BLFF 8/165 REGRADE | 43744380 | COTTONWOOD-RED BLUFF | 008/165 | ICW | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.258715 | 40.3032 | ETL.6660 | 40747092 | Structure-Wood | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
115680802 | T2 EI CARIBOU #2 - 002/012 RPL ANCH | 31456236 | CARIBOU #2 | 002/012 | 93E | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.179159 | 40.068 | ETL.6280 | 40675373 | Anchor-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 637 | Table Mountain |  | Yes
115680803 | T2 EI CNTRVILLE-TBLE MTN 4/74 RPL PL | 31431548 | CENTERVILLE-TABLE MTN | 004/074 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.70584 | 39.7337 | ETL.6320 | 40874595 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
115680969 | T2 EI HAT CRK #1-WSTWD 13/251 RPLC SPLW | 43736796 | HAT CREEK #1-WESTWOOD | 013/251 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.366893 | 40.8165 | ETL.7030 | 40701217 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
115681000 | T2 EI HAT CREEK #1-WSTWD 13/251 RPR GYWW | 43736796 | HAT CREEK #1-WESTWOOD | 013/251 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.366893 | 40.8165 | ETL.7030 | 40701217 | Ground Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
115681029 | T2 EI HAT CREEK #1-WSTWD 12/247 RPR GYWW | 43736796 | HAT CREEK #1-WESTWOOD | 012/247 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.369665 | 40.8186 | ETL.7030 | 40676248 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
115681031 | T2 EI HAT CRK #1-WSTWD 12/248 RPLC STRW | 31426976 | HAT CREEK #1-WESTWOOD | 012/248 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.368945 | 40.8181 | ETL.7030 | 40759172 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain
115681035 | T2 EI PIT #3-PIT #1 009/075 RPR STRT | 43685976 | PIT #3-PIT #1 | 009/075 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Internal Process | Circuit Based Scheduling | '-121.640618 | 40.9154 | ETL.5400 | 40759437 | Structure-Tower | No Good/Out of Stdrd | Repair | CONS srdy | CONS | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
115681675 | T3 EI CRB-PLRM :032/262 INST HRDT | 44051417 | CARIBOU-PALERMO | :032/262 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.475245 | 39.7512 | ETL.3190 | 40702274 | Hardware-Tower | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115681697 | T3 EI CARIBOU-PALERMO :032/263 RPR STRT | 44051417 | CARIBOU-PALERMO | :032/263 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.475573 | 39.7491 | ETL.3190 | 40656367 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115681737 | T2 EI CARIBOU #2 002/014 CANCEL | 31456236 | CARIBOU #2 | 002/014 | 93E | E | Pre-2020_(4) TD tag on high spread line |  |  | CANCEL/CNCL | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.180647 | 40.0673 | ETL.6280 | 40769462 | Anchor-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 637 | Table Mountain |  | Yes
115681745 | T3 EI CARIBOU-PALERMO :33/266 RPL INSS | 31426491 | CARIBOU-PALERMO | :033/266 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.476538 | 39.743 | ETL.3190 | 40816595 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC hold |  |  |  | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain
115681747 | T3 EI CRESTA-RIO OSO 016/130 PNT TWR | 43708860 | CRESTA-RIO OSO | 016/130 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  | Likely MAT error - delink to correct | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.477186 | 39.7418 | ETL.4590 | 40910147 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
115681750 | T2 EI HAT CREEK #1-WSTWD 13/254 RPL SPLW | 43736796 | HAT CREEK #1-WESTWOOD | 013/254 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.364833 | 40.8147 | ETL.7030 | 40877470 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
115681761 | T3 EI CARIBOU-PALERMO :033/267 WASH INSS |  | CARIBOU-PALERMO | :033/267 | ICI | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.476775 | 39.7415 | ETL.3190 | 40826427 | Insulator | Contaminated | Helicopter Wash |  |  |  |  | PEND | LC | TLX | Contract | Expense | 626 | Table Mountain
115681802 | T3 EI DRM-HGGNS 013/124 RMV NEST | 43687142 | DRUM-HIGGINS | 013/124 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  | Likely MAT error - delink to correct | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.95086 | 39.1636 | ETL.4393 | 41162645 | Structure-Steel | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento |  |  | Yes
115681969 | T2 DI CARIBOU-PALERMO 12/104 RPL HRDWR | 44056495 | CARIBOU-PALERMO | 012/104 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.513479 | 39.631 | ETL.3190 | 40758615 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
115682061 | T2 DI CARIBOU-PALERMO 12/103 RPL HRDWR | 44056495 | CARIBOU-PALERMO | 012/103 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.513986 | 39.6292 | ETL.3190 | 40656345 | Structure-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 543 | Table Mountain |  |  | Yes
115682226 | T2 EI PHILO JCT-ELK 002/011 INS GYWW | 43762377 | PHILO JCT-ELK | 002/011 | ICW | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.20463 | 39.0983 | ETL.7780 | 40595265 | Guy Wire-Wood | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-06-17
115682765 | T2 EI LAYTONVILLE-WIL 12/000 RPR GYWW | 43761787 | LAYTONVILLE-WILLITS | 012/000 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | FSRP | [5 empty] | '-123.418734 | 39.5438 | ETL.8360 | 40614438 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville
115682808 | T2 EI LAYTONVILLE-WI 11/005 RPL POLE | 31490917 | LAYTONVILLE-WILLITS | 011/005 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | FSRP | [5 empty] | '-123.4172 | 39.5428 | ETL.8360 | 40750468 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  | 2019-05-08
115683042 | T2 DI CARIBOU-PALERMO 6/55 RPR CORROSION | 44056495 | CARIBOU-PALERMO | 006/055 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.538613 | 39.5459 | ETL.3190 | 40765164 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115683313 | T2 DI CARIBOU-PALERMO 8/66 RPR SHACKLES | 44056495 | CARIBOU-PALERMO | 008/066 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.532889 | 39.5648 | ETL.3190 | 40816568 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115683490 | T2 EI KESWICK-TRINITY 029/502 RMV BUTT | 43661466 | KESWICK-TRINITY | 029/502 | ICW | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.910589 | 40.7127 | ETL.7270 | 40911329 | Structure-Wood | Debris/Nest/etc. | Remove | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
115684155 | T2 DI CARIBOU-PALERMO 7/60 PAINT TOWER |  | CARIBOU-PALERMO | 007/060 |  | F | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.53662 | 39.5522 | ETL.3190 | 40599257 | Structure-Tower | Paint/Coating | Repaint |  |  |  |  | PEND | LC | TLX | Contract | Expense |  | Table Mountain
115684353 | T2 DI CARIBOU-PALERMO 7/60 RPL SHLD WIRE | 44304495 | CARIBOU-PALERMO | 007/060 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.53662 | 39.5522 | ETL.3190 | 40599257 | Shield Wire / OPGW-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
115684418 | T2 DI CARIBOU-PALERMO 7/60 RPL HRDS | 44057199 | CARIBOU-PALERMO | 007/060 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.53662 | 39.5522 | ETL.3190 | 40599257 | Hardware-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain
115684491 | T2 EI LAYTONVILLE-WIL 9/000 RPL POLE | 31434842 | LAYTONVILLE-WILLITS | 009/000 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | FSRP | [5 empty] | '-123.384385 | 39.5146 | ETL.8360 | 40614431 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  | 2019-05-08
115684574 | T2 EI LAYTONVILLE-W 13/000E RPL POLE | 31490917 | LAYTONVILLE-WILLITS | 013/000E | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | FSRP | [5 empty] | '-123.428494 | 39.5548 | ETL.8360 | 40905764 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville
115684673 | T3 EI DRUM-RIO OSO #1 001/010 REPAINT | 43685808 | DRUM-RIO OSO #1 | 001/010 | ICQ | F | Pre-2020_(9a) Other ignition related |  |  | Likely MAT error - delink to correct | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.786336 | 39.2566 | ETL.1420 | 40596150 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento |  |  | Yes
115684755 | T3NT CARIBU-PALRMO :031/256A INS MRKW | 44304495 | CARIBOU-PALERMO | :031/256A | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.467758 | 39.7593 | ETL.3190 | 44374354 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain
115684762 | T3NT EI TCRB-PLRM :031/256AC GMKS | 44304495 | CARIBOU-PALERMO | :031/256C | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.467814 | 39.7593 | ETL.3190 | 44374356 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain
115685176 | T2 EI PRDSE-TBLE MTN 006/056 RPL INSS | 31451270 | PARADISE-TABLE MTN | 006/056 | 93K | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.5378359 | 39.5477 | ETL.4316 | 40844441 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  | Yes
115685193 | T3 EI CARIBOU-PLERMO :031/256 RPL HRDT | 44051417 | CARIBOU-PALERMO | :031/256 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.467283 | 39.7595 | ETL.3190 | 40816593 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115685231 | T2 EI PRDSE-TBLE MTN 006/055BA RPL STRW | 31453760 | PARADISE-TABLE MTN | 006/055BA | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.537173 | 39.5471 | ETL.4316 | 41184210 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
115685241 | T2 EI PRDSE-TBLE MTN 006/055BB INS GYWW | 43724325 | PARADISE-TABLE MTN | 006/055BB | ICW | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.537116 | 39.5472 | ETL.4316 | 41184212 | Guy Wire-Wood | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
115685286 | T2 EI PRDSE-TBLE MTN 006/055BC RPR GYWW | 43724325 | PARADISE-TABLE MTN | 006/055BC | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.537064 | 39.5472 | ETL.4316 | 41184213 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
115685289 | T3 EI CARIBU-PALRMO :031/256A RPL GYYS | 43659205 | CARIBOU-PALERMO | :031/256A | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.467758 | 39.7593 | ETL.3190 | 44374354 | Guy Wire-Steel | No Good/Out of Stdrd | Replace | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain
115685536 | STOCKTON""A""-WEBER#2 A4/113 RPL POLE | 31476291 | STOCKTON "A"-WEBER #2+ (NO FLY) | A003/113 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | Central | Non-WSIP | FSRP | [5 empty] | '-121.278047 | 37.9701 | ETL.8130 | 40754502 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Victor |  | Y - 2
115685938 | T3 EI CARIBOU-PLERMO :031/257 RPR STRT | 44051417 | CARIBOU-PALERMO | :031/257 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.468506 | 39.759 | ETL.3190 | 40826429 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115685939 | T3 EI CARIBOU-PLERMO :031/257 REPAINT | 44051417 | CARIBOU-PALERMO | :031/257 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  |  | Check FDA | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.468506 | 39.759 | ETL.3190 | 40826429 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115686158 | T2 EI HT CRK #1-WSTWD-21/414 INST MRKW | 43736797 | HAT CREEK #1-WESTWOOD | 021/414 | ICW | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.2546 | 40.7258 | ETL.7030 | 40601696 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
115686280 | T3 EI CRESTA-RIO OSO 13/110 REPL INSS | 31435732 | CRESTA-RIO OSO | 013/110 | 93K | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.4567151 | 39.7717 | ETL.4590 | 40919872 | Insulator-Steel | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  | Yes
115686282 | T3 EI CARIBOU-PLRMO :031/256 RPL INSS | 31426491 | CARIBOU-PALERMO | :031/256 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.467283 | 39.7595 | ETL.3190 | 40816593 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC hold |  |  |  | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain
115687732 | T3 KESWICK-TRINITY 002/041 RPR CNDW | 43939188 | KESWICK-TRINITY | 002/041 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-122.498022 | 40.6169 | ETL.7270 | 40650304 | Conductor-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
115688019 | T2 EI JEFFER-HILL JCT 006/035C RPR GYWW | 43752126 | JEFFERSON-HILLSDALE JCT | 006/035C | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.35638 | 37.5251 | ETL.7190 | 41162633 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Bay |  | Y - 5 | SFPUC (4)
115688046 | DISTRIBUTION AUTO SPLICE | 43766561 | ATASCADERO-SAN LUIS OBISPO | 006/118 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | South | WSIP |  |  |  |  | Safety Reason | PAR SSD from 23-30 June, no work performed | '-120.62473 | 35.3841 | ETL.8490 | 42699985 | Conductor-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Pismo Beach |  | Y - 7
115688106 | T2 EI JEFFER-HILL JCT 006/035A RPR GYWW | 43752126 | JEFFERSON-HILLSDALE JCT | 006/035A | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.356328 | 37.5249 | ETL.7190 | 40577459 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Bay |  | Y - 5 | SFPUC (4)
115688168 | T2 EI PARADISE-TABLE MTN 5/051 RPR CONDS | 43727174 | PARADISE-TABLE MTN | 005/051 | ICS | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.540302 | 39.5393 | ETL.4316 | 40596669 | Conductor-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
115688175 | T2 EI PRDSE-TBLE MTN 006/056 RMV NEST | 43727174 | PARADISE-TABLE MTN | 006/056 | ICS | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.537823 | 39.5477 | ETL.4316 | 40816520 | Structure-Steel | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
115688232 | T2NT EI CARIBOU-PALERMO 12/101 INS MRKS | 44070463 | CARIBOU-PALERMO | 012/101 | ICS | F | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.515151 | 39.6251 | ETL.3190 | 41162739 | Marker (i.e. signs)-Steel | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Table Mountain |  |  | Yes
115688437 | T2 EI HAT CREEK #1-WEST 015/294 RPR STRW | 43736796 | HAT CREEK #1-WESTWOOD | 015/294 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.337078 | 40.7924 | ETL.7030 | 40616868 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
115688457 | T2 EI HT CREEK #1-WEST 015/301 INST MRKW | 43736796 | HAT CREEK #1-WESTWOOD | 015/301 | ICW | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.332242 | 40.7885 | ETL.7030 | 40770727 | Marker (i.e. signs)-Wood | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
115688459 | T2 EI HAT CREEK #1-WEST 15/295 RPL STRW | 31505374 | HAT CREEK #1-WESTWOOD | 015/295 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.336412 | 40.7918 | ETL.7030 | 40676268 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Need New ERTC
115688495 | T2 EI HAT CREEK #1-WEST 015/301 REFRAME | 31471575 | HAT CREEK #1-WESTWOOD | 015/301 | 93E | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.332242 | 40.7885 | ETL.7030 | 40770727 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  | Yes
115688496 | T2 EI HAT CREK #1-WSTWD 015/299 RPR STRW | 43736796 | HAT CREEK #1-WESTWOOD | 015/299 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.333618 | 40.7896 | ETL.7030 | 40617092 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
115688550 | T2 EI CARIBOU-PALERMO 006/053 RPR FOND | 44057199 | CARIBOU-PALERMO | 006/053 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.540497 | 39.5401 | ETL.3190 | 40660305 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115688557 | T2 EI HAT CREEK #1-WEST 15/289 INST MRKW | 43736796 | HAT CREEK #1-WESTWOOD | 015/289 | ICW | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.34057 | 40.7952 | ETL.7030 | 40616865 | Marker (i.e. signs)-Wood | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
115688620 | T2 EI LYTONVILLE-WILL 013/000G INST GMKW |  | LAYTONVILLE-WILLITS | 013/000G | ICW | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.427169 | 39.5556 | ETL.8360 | 40905766 | Guy Wire Mark /Indic-Wood | Missing | Install |  |  |  |  | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-07-29
115688621 | T2 EI LYTONVILLE-WILL 013/000G RPR GYWW | 43761787 | LAYTONVILLE-WILLITS | 013/000G | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | FSRP | [5 empty] | '-123.427169 | 39.5556 | ETL.8360 | 40905766 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville
115688627 | T2 EI HAT CREEK #1-WEST 16/309 INS HRDW | 43904280 | HAT CREEK #1-WESTWOOD | 016/309 | ICW | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.326777 | 40.784 | ETL.7030 | 44311020 | Hardware-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
115688733 | T2 EI SANTA YNEZ TAP 3/30 REPL POLE | 31423339 | SANTA YNEZ TAP | 003/030 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-120.13458 | 34.6311 | ETL.3701 | 40649603 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Pismo Beach |  | Y - 3
115688768 | T2 EI HAT CREEK #1-WEST 14/284 RPL INSW | 31456189 | HAT CREEK #1-WESTWOOD | 014/284 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.3440784 | 40.798 | ETL.7030 | 40634668 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 508 | Table Mountain |  |  | Yes
115691214 | T3 DI IGNACIO-BOLINAS #1 08/84 RPL POLE | 31428896 | IGNACIO-BOLINAS #1 | 008/084 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.653683 | 38.0123 | ETL.7140 | 40861141 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  | 2019-04-01
115691953 | T2 DI CARIBOU-PALERMO 11/100 RPR CNDCTR | 43659205 | CARIBOU-PALERMO | 011/100 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.515658 | 39.6233 | ETL.3190 | 40599269 | Conductor-Steel | No Good/Out of Stdrd | Repair | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
115691990 | T2 DI CARIBOU-PALERMO 1/8 RPR STRCTR | 44056495 | CARIBOU-PALERMO | 001/008 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.536625 | 39.4611 | ETL.3190 | 40867924 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
115691991 | T2 DI CARIBOU-PALERMO 12/108 RPR INS | 43659205 | CARIBOU-PALERMO | 012/108 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.511776 | 39.637 | ETL.3190 | 40867949 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
115691994 | T2 DI CARIBOU-PALERMO 12/110 REPL INS | 43659205 | CARIBOU-PALERMO | 012/110 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.511297 | 39.6387 | ETL.3190 | 40607817 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
115692046 | T2 DI CARIBOU-PALERMO 9/82 REPAIR STRCT | 44056495 | CARIBOU-PALERMO | 009/082 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.525145 | 39.5899 | ETL.3190 | 40674920 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
115692353 | T2 EI OCNO-CLLNDR SW 19/126 RPR GYWW | 43588178 | OCEANO-CALLENDAR SW STA | 019/126 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | South | WSIP | FSRP | [5 empty] | '-120.579354 | 35.1011 | ETL.2394 | 40812254 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - 7
115692871 | T2 EI CARIBOU-PALERMO 6/054 RPR FOND | 44057199 | CARIBOU-PALERMO | 006/054 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.540063 | 39.5414 | ETL.3190 | 40758611 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115692968 | T2 EI FULTON JCT-VACA 050/312 RPR MEMBER | 43749475 | FULTON JCT-VACA | 050/312 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | TLN/TLQ error | Recommend delinking prior to editing | TR2 | LATE | North Valley | WSIP |  |  |  | REJECT: Could not complete work due to a clearance, materials or access issue. |  |  | '-121.9893434 | 38.4183 | ETL.1590 | 44238422 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes
115693287 | T2 DI CARIBOU-PALERMO 5/47 PNT TWR |  | CARIBOU-PALERMO | 005/047 |  | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.540432 | 39.5304 | ETL.3190 | 40815575 | Structure-Tower | Paint/Coating | Repaint |  |  |  |  | PEND | LC | TLX | Contract | Expense |  | Table Mountain
115693633 | T2 DI CARIBOU-PALERMO 15/119 INS MRKR | 44056495 | CARIBOU-PALERMO | 015/119 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.506565 | 39.6554 | ETL.3190 | 40913201 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115693783 | T2 DI CARIBOU-PALERMO 00/02 RPL HRDWR | 43659205 | CARIBOU-PALERMO | 000/002 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.521449 | 39.4545 | ETL.3190 | 40689941 | Hardware-Steel | No Good/Out of Stdrd | Replace | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
115693849 | DISTRIBUTION INSL | 31430822 | SAN LUIS OBISPO-SANTA MARIA (IDLE) | 008/150 | 93I | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | South | WSIP | FSRP | [5 empty] | '-120.5386611 | 35.1776 | ETL.9100 | 44189771 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Pismo Beach
115694533 | T2 DI CARIBOU-PALERMO 10/87 RPR INSULTOR | 43659205 | CARIBOU-PALERMO | 010/087 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.522843 | 39.598 | ETL.3190 | 40819278 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
115697024 | T2 EI HUMBOLDT-TRINITY 61/5 INST HV | 43729518 | HUMBOLDT-TRINITY | 061/005 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Coast | WSIP | [8 empty] | ETL.1820 | 44324177 | Marker (i.e. signs)-Steel | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Eureka |  |  | 2019-08-09
115698144 | T2 EI MNDCNO-WLTS-FRT BRG 041/005 WASH | 43731269 | MENDOCINO-WILLITS-FORT BRAGG | 041/005 | ICD | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.782483 | 39.4304 | ETL.7550 | 40750988 | Insulator | Contaminated | Ground Wash | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 622 | Lakeville |  |  | 2019-04-07
115698403 | T2 EI MNDCNO-WLTS-FRT BRG 041/008 WASH | 43731269 | MENDOCINO-WILLITS-FORT BRAGG | 041/008 | ICD | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.786946 | 39.431 | ETL.7550 | 40861439 | Insulator | Contaminated | Ground Wash | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 622 | Lakeville |  |  | 2019-04-07
115698513 | T2 EI MNDCNO-WLTS-FT BRG 041/002 SPLICE | 43731276 | MENDOCINO-WILLITS-FORT BRAGG | 041/002 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.776542 | 39.4295 | ETL.7550 | 40657967 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-04-07
115698579 | T3NT EI ATASCADERO-SLO 8/134 CLIMB STEPS | 44589040 | ATASCADERO-SAN LUIS OBISPO | 008/134 | ICW | F | Pre-2020_(9a) Other ignition related |  |  |  | TR3 | LATE | South | WSIP |  |  |  |  | Safety Reason | PAR SSD from 23-30 June, no work performed | '-120.631192 | 35.3688 | ETL.8490 | 42700021 | Hardware-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - 1 | 2019-03-15
115698852 | T3NT EI ATSCDR-SN L OBISPO 008/134 STEPS | 44589040 | ATASCADERO-SAN LUIS OBISPO | 008/133 | ICW | F | Pre-2020_(9a) Other ignition related |  |  |  | TR3 | LATE | South | WSIP |  |  |  |  | Safety Reason | PAR SSD from 23-30 June, no work performed | '-120.630633 | 35.3701 | ETL.8490 | 42700019 | Hardware-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - 7
115698995 | T3NT EI ATSCDR-SN L OBISPO 008/134 STEPS | 44589040 | ATASCADERO-SAN LUIS OBISPO | 008/132 | ICW | F | Pre-2020_(9a) Other ignition related |  |  |  | TR3 | LATE | South | WSIP |  |  |  |  | Safety Reason | PAR SSD from 23-30 June, no work performed | '-120.630338 | 35.3707 | ETL.8490 | 42700017 | Hardware-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - 7
115699194 | T2 EI ATSCDR-SN L OBISPO 008/134 STEPS | 44589040 | ATASCADERO-SAN LUIS OBISPO | 007/127 | ICW | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | South | WSIP | FSRP |  |  |  | Safety Reason | PAR SSD from 23-30 June, no work performed | '-120.628315 | 35.3753 | ETL.8490 | 42700003 | Hardware-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - 7
115699639 | T2 DI CARIBOU-PALERMO 07/65 RPR PAINT |  | CARIBOU-PALERMO | 007/065 |  | F | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.533674 | 39.5619 | ETL.3190 | 40758457 | Structure-Tower | Paint/Coating | Repaint |  |  |  |  | PEND | LC | TLX | Contract | Expense |  | Table Mountain
115702749 | T2 EI LYTNVLLE-WLLTS 007/003 INS GYWW | 43761787 | LAYTONVILLE-WILLITS | 007/003 | ICW | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | WSIP | FSRP | [5 empty] | '-123.363436 | 39.4952 | ETL.8360 | 40648647 | Guy Wire-Wood | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-05-08
115703026 | T2 DI CARIBOU-PALERMO 14/115 RPR CORRSN | 44056495 | CARIBOU-PALERMO | 014/115 | ICQ | F | Pre-2020_(4) TD tag on high spread line |  |  | Check FDA | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.508354 | 39.6491 | ETL.3190 | 40913197 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
115703110 | T2 EI VACA-SUISUN-JMSN 003/031 RPR CONS | 44175847 | VACA-SUISUN-JAMESON | 003/031 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.990026 | 38.4012 | ETL.4080 | 40614338 | Conductor-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes
115703179 | T3 EI KESWICK-TRINITY 004/070 RPL ANCW | 31430073 | KESWICK-TRINITY | 004/070 | 93E | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [8 empty] | ETL.7270 | 44421135 | Anchor-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 637 | Table Mountain |  |  | Yes
115703180 | T3 EI DRM-HGGNS 005/052 PNT TWR | 43687142 | DRUM-HIGGINS | 005/052 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  | Likely MAT error - delink to correct | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.836325 | 39.2145 | ETL.4393 | 40682536 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Sacramento
115703292 | T3 EI KESWICK-TRINITY 004/070C RPR PL | 43661466 | KESWICK-TRINITY | 004/070 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [8 empty] | ETL.7270 | 44421136 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
115703293 | T2 EI KESWICK-TRINITY 006/088A REPL ANCW | 31471077 | KESWICK-TRINITY | 006/088A | 93E | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.573205 | 40.6421 | ETL.7270 | 44649291 | Anchor-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  | Yes
115703299 | T3 EI KESWICK-TRINITY 004/070L RPR CNDW | 43661466 | KESWICK-TRINITY | 004/070 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [8 empty] | ETL.7270 | 44421135 | Conductor-Wood | No Good/Out of Stdrd | Repair | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
115703647 | T2 EI MNDC-WLTS-FRT BRG 040/000 RPL STRW | 31438704 | MENDOCINO-WILLITS-FORT BRAGG | 040/000 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.757435 | 39.4196 | ETL.7550 | 40588514 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  | 2019-04-07
115703675 | T3 EI KESWICK-TRINITY 004/069 RPR GYWW | 43939188 | KESWICK-TRINITY | 004/069 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  | Likely veg | TR3 | LATE | North Valley | WSIP | [6 empty] | '-122.537899 | 40.6275 | ETL.7270 | 44164727 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
115703884 | T3 EI KESWICK-TRINITY 004/069 RPR CONW | 43939188 | KESWICK-TRINITY | 004/069 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-122.537899 | 40.6275 | ETL.7270 | 44164727 | Conductor-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
115703981 | T2 EI MNDC-WLTS-FRT BRG 040/002 RPR INSW | 43731269 | MENDOCINO-WILLITS-FORT BRAGG | 040/002 | ICD | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.759983 | 39.4213 | ETL.7550 | 40697902 | Insulator | Contaminated | Ground Wash | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 622 | Lakeville |  |  | 2019-04-07
115704027 | T2 EI VACA-PARKWAY 006/035 INST HRDT | 43760159 | VACA-PARKWAY | 006/035 | ICQ | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP |  |  |  |  | Priority Bucket 9 | '-122.018743 | 38.3895 | ETL.5850 | 40756444 | Hardware-Tower | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento |  |  | Yes
115704032 | T2 EI MENDOCINO-WILLITS-FB 29/5 RPL POLE | 31490869 | MENDOCINO-WILLITS-FORT BRAGG | 029/005 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.592351 | 39.3474 | ETL.7550 | 40750969 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville
115704064 | T2 EI MNDC-WLTS-FRT BRG 040/003 RPR INSW | 43731269 | MENDOCINO-WILLITS-FORT BRAGG | 040/003 | ICD | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.761326 | 39.4222 | ETL.7550 | 40666502 | Insulator | Contaminated | Ground Wash | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 622 | Lakeville |  |  | 2019-04-07
115704086 | T2 EI HUMBOLDT-TRINITY 98/1L RPL PL | 31474285 | HUMBOLDT-TRINITY | 098/001 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.829449 | 40.7658 | ETL.1820 | 44562866 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2019-03-30
115704178 | T3 EI KESWICK-TRINITY 004/066 RPR GYWW | 43661466 | KESWICK-TRINITY | 004/066 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-122.531553 | 40.6241 | ETL.7270 | 40701679 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
115704733 | T3 EI DRM-HGGNS 005/059 PNT TWR | 43687142 | DRUM-HIGGINS | 005/059 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  | Likely MAT error - delink to correct | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.841496 | 39.2058 | ETL.4393 | 40861968 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Sacramento
115704967 | EI VACA-SUISUN-JAMESON 005/043 REPL INSS | 31457373 | VACA-SUISUN-JAMESON | 005/043 | 93K | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-122.000921 | 38.376 | ETL.4080 | 40690656 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 532 | Sacramento |  |  | Yes
115705266 | T2 EI MNDC-WLTS-FRT BRG 040/005 RPR INSW | 43731269 | MENDOCINO-WILLITS-FORT BRAGG | 040/005 | ICD | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.763427 | 39.4236 | ETL.7550 | 40750986 | Insulator | Contaminated | Ground Wash | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 622 | Lakeville |  |  | 2019-04-07
115705469 | T2 EI MNDC-WLTS-FRT BRG 040/007 RPL MRKW |  | MENDOCINO-WILLITS-FORT BRAGG | 040/007 | ICW | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.76669 | 39.4258 | ETL.7550 | 40808842 | Marker (i.e. signs)-Wood | Missing | Install |  |  |  |  | PEND | LC | TLX | Contract | Expense | 630 | Lakeville
115705580 | T3 EI DRM-HGGNS 007/073 REPAINT | 43687142 | DRUM-HIGGINS | 007/073 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  | Likely MAT error - delink to correct | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.861567 | 39.1864 | ETL.4393 | 40650082 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Sacramento |  |  | Yes
115705611 | T2 EI MNDC-WLTS-FRT BRG 040/007 RPL SPLW | 43731276 | MENDOCINO-WILLITS-FORT BRAGG | 040/007 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.76669 | 39.4258 | ETL.7550 | 40808842 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville
115705753 | T2 EI PRDSE-TBL MTN 006/055D RPL POLE | 31453760 | PARADISE-TABLE MTN | 006/055D | 70Y | E | 2020_(1a) PSPS |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.535982 | 39.546 | ETL.4316 | 41184125 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
115705759 | T2 EI PARADISE-TABLE MTN 6/55CB RPL PL | 31453760 | PARADISE-TABLE MTN | 006/055CB | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.536857 | 39.5464 | ETL.4316 | 41184220 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
115705799 | T2 EI MORAG-CSTR VLLY 01/08 RPL INSS | 31427542 | MORAGA-CASTRO VALLEY | 001/008 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-122.1412126 | 37.8506 | ETL.5250 | 40890551 | Insulator-Steel | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - 5 | 2019-04-01
115706786 | DISTRIBUTION RPR STRW |  | SAN LUIS OBISPO-SANTA MARIA (IDLE) | 009/170 | ICW | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | South | WSIP | FSRP | [5 empty] | '-120.526 | 35.1641 | ETL.9100 | 44191873 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach
115706997 | T3 EI DRM-HGGNS 008/082 PNT TWR | 43687142 | DRUM-HIGGINS | 008/082 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  | Likely MAT error - delink to correct | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.881084 | 39.1718 | ETL.4393 | 40660213 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Sacramento |  |  | Yes
115707025 | T2 EI MNDC-WLTS-FRT BRG 040/008 RPR INSW | 43731269 | MENDOCINO-WILLITS-FORT BRAGG | 040/008 | ICD | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.768016 | 39.4267 | ETL.7550 | 40876277 | Insulator | Contaminated | Ground Wash | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 622 | Lakeville
115707034 | T2 EI MNDC-WLTS-FRT BRG 040/008 RPL MRKW |  | MENDOCINO-WILLITS-FORT BRAGG | 040/008 | ICW | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.768016 | 39.4267 | ETL.7550 | 40876277 | Marker (i.e. signs)-Wood | Missing | Install |  |  |  |  | PEND | LC | TLX | Contract | Expense | 630 | Lakeville
115707171 | T3 EI DRUM-RIO OSO #1 004/050 CANCEL | 43685808 | DRUM-RIO OSO #1 | 004/050 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  | CANCEL/CNCL | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.836556 | 39.2248 | ETL.1420 | 40596153 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento |  |  | Yes
115707208 | T3 EI DRM-RI S#2 004/049 PAINT | 43685734 | DRUM-RIO OSO #2 | 004/049 | ICS | F | Pre-2020_(9a) Other ignition related |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.835339 | 39.2258 | ETL.1430 | 40866278 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes
115707339 | T2 EI KESWICK-TRINITY 011/136 REPL CRSW | 31471077 | KESWICK-TRINITY | 011/136 | 93E | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.634596 | 40.676 | ETL.7270 | 40598899 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 637 | Table Mountain |  |  | Yes
115707403 | EI VC-VCVLL-JMSN-NTWR 6/48 PNT TWR | 43740701 | VACA-VACAVILLE-JAMESON-NTH TWR | 006/048 | ICS | E | Pre-2020_(9a) Other ignition related |  |  |  |  | LATE | North Valley | WSIP | [5 empty] | Priority Bucket 9 | '-122.008861 | 38.367 | ETL.4100 | 40864914 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Sacramento |  |  | Yes
115707549 | T2 EI CARIBOU-PALERMO 008/069 RPR FOND | 43727173 | CARIBOU-PALERMO | 008/069 | ICQ | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.53135 | 39.5695 | ETL.3190 | 40867354 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
115707581 | T3 EI DRUM-HIGGINS 007/078 PNT TWR | 43687142 | DRUM-HIGGINS | 007/078 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  | Likely MAT error - delink to correct | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.870652 | 39.1765 | ETL.4393 | 40862209 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento
115707606 | EI MRAG-CSTR VLLY 02/15 RPR FOND |  | MORAGA-CASTRO VALLEY | 002/015 | ICQ | F | Pre-2020_(9a) Other ignition related |  |  |  |  | LATE | Central | WSIP | FSRP | [5 empty] | '-122.122246 | 37.839 | ETL.5250 | 40762326 | Foundation/Concrete-Tower | Earth Covered Tower | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  | 2019-04-01
115707938 | T3 EI DRM-HGGNS 008/083 PNT TWR | 43687142 | DRUM-HIGGINS | 008/083 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  | Likely MAT error - delink to correct | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.882213 | 39.1713 | ETL.4393 | 40653945 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento |  |  | Yes
115708119 | T2 EI CARIBOU-PALERMO 12/104 RPR FOND | 44069597 | CARIBOU-PALERMO | 012/104 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.513479 | 39.631 | ETL.3190 | 40758615 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
115708148 | T2 EI CARIBOU-PALERMO 12/104 RPL SPLS | 44304495 | CARIBOU-PALERMO | 012/104 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.513479 | 39.631 | ETL.3190 | 40758615 | Splice-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
115711510 | T2 EI CORTINA-MEND #1 25/118 RPL HRDS | 43721180 | CORTINA-MENDOCINO #1 | 025/118 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.641704 | 39.0268 | ETL.1330 | 40861151 | Hardware-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville
115711512 | T2 EI VACA-PARKWAY 18/95 RPL DAMS | 43760157 | VACA-PARKWAY | 018/095 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Internal Process | 4/6: Too windy for the helicopter, no new scheduled date yet - V1KSCircuit Based Scheduling | '-122.140981 | 38.2427 | ETL.5850 | 40814594 | Damper-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes
115712279 | T2 EI EXCHEQUER-YOSEMITE 01/009 RPR STRT | 43709740 | EXCHEQUER-YOSEMITE | 001/009 | ICQ | E | Pre-2020_(4) TD tag on high spread line | Project efficiency (capital work) | DLFL; Completed on project 74001200 |  | TR2 | LATE | South | WSIP | [6 empty] | '-120.253778 | 37.5758 | ETL.8650 | 40859233 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - Prog Multi
115712539 | T2 EI DRUM-RIO OSO #1 014/123 REPL INSS | 43687117 | DRUM-RIO OSO #1 | 014/123 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | FSRP |  |  | REJECT: Could not complete work due to a clearance, materials or access issue. |  |  | '-120.979874 | 39.1518 | ETL.1420 | 44337165 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes
115713224 | T2 EI DRM-HGGNS 015/137 PNT STRT | 43687142 | DRUM-HIGGINS | 015/137 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.982432 | 39.1506 | ETL.4393 | 40751902 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Sacramento |  |  | Yes
115713608 | T2 EI DRM-HGGNS 015/138 RPL SPLS | 43687142 | DRUM-HIGGINS | 015/138 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.984931 | 39.1497 | ETL.4393 | 40764843 | Splice-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes
115713740 | T2 EI DRM-HGGNS 015/138 RPR COND | 43687142 | DRUM-HIGGINS | 015/138 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.984931 | 39.1497 | ETL.4393 | 40764843 | Jumper-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes
115713834 | T2 EI CARIBOU-PALERMO :028/233 RPR STRT | 44069597 | CARIBOU-PALERMO | :028/233 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.450558 | 39.8014 | ETL.3190 | 40656365 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115713835 | T2NT EI CARIBOU-PALERMO :28/233 INS MRKS | 44069597 | CARIBOU-PALERMO | :028/233 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.450558 | 39.8014 | ETL.3190 | 40656365 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
115713836 | T2NT EI CARIBOU-PALERMO :28/233 RPR FOND | 44069597 | CARIBOU-PALERMO | :028/233 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.450558 | 39.8014 | ETL.3190 | 40656365 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
115713837 | T2NT EI CARIBOU-PALERMO :28/232 INS MRKT | 44069597 | CARIBOU-PALERMO | :028/232 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  |  | Check FDA | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.450104 | 39.8023 | ETL.3190 | 40702269 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
115713838 | T2 EI CARIBOU-PALERMO :028/232 RPR FOND | 44069597 | CARIBOU-PALERMO | :028/232 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.450104 | 39.8023 | ETL.3190 | 40702269 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115713868 | T2 EI CARIBOU-PALERMO :028/233 RPR STRT | 44069597 | CARIBOU-PALERMO | :028/233 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.450558 | 39.8014 | ETL.3190 | 40656365 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115713870 | T2 EI CARIBOU-PALERMO :028/232 RPR STRT | 44069597 | CARIBOU-PALERMO | :028/232 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.450104 | 39.8023 | ETL.3190 | 40702269 | Structure-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 543 | Table Mountain
115716122 | T3 DI DRM-GRSS VLLY WMR B17/386 RPL CRSW | 31431045 | DRUM-GRASS VALLEY-WEIMAR | B017/386 | 93E | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.9653 | 39.1328 | ETL.6760 | 40814230 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 637 | Sacramento |  |  | Yes
115716177 | T2 EI BALCH-SANGER 000/002 RPR CONS | 43684626 | BALCH-SANGER | 000/002 | ICS | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-119.090382 | 36.9083 | ETL.1050 | 40682223 | Jumper-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  | Y - 17
115716181 | T2 EI BALCH-SANGER 000/003 RPR CONS | 43684626 | BALCH-SANGER | 000/003 | ICS | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-119.091491 | 36.9082 | ETL.1050 | 40646819 | Conductor-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  | Y - 17
115716200 | T2 EI BALCH-SANGER 000/001 REPL GYWS | 43684626 | BALCH-SANGER | 000/001 | ICS | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-119.088691 | 36.9085 | ETL.1050 | 40583096 | Guy Wire-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  | Y - 17
115716253 | T2 EI BALCH-SANGER 002/014 FOND CVRD | 43709595 | BALCH-SANGER | 002/014 | ICQ | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-119.1220496 | 36.8981 | ETL.1050 | 40946399 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 16
115718349 | T2 EI CARIBOU-PALERMO :28/229 RPR STUS | 44069801 | CARIBOU-PALERMO | :028/229 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.444868 | 39.8042 | ETL.3190 | 40867374 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115718465 | T2 EI POE-RIO OSO 022/148 RPR INSS | 43737420 | POE-RIO OSO | 022/148 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.503661 | 39.6655 | ETL.5540 | 40873673 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
115718475 | T2 EI CARIBOU-PALERMO :28/234 INS MRKS | 44069801 | CARIBOU-PALERMO | :028/234 | ICQ | F | Pre-2020_(4b) On structure in bucket 4 |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.451472 | 39.7995 | ETL.3190 | 40771764 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115718497 | T2 EI CARIBOU-PALERMO :027/221 RPL INSS |  | CARIBOU-PALERMO | :027/221 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.432073 | 39.8164 | ETL.3190 | 40591568 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain
115718499 | T2 EI CARIBOU-PALERMO :027/221 MRKS | 44069454 | CARIBOU-PALERMO | :027/221 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  |  | Check FDA | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.432073 | 39.8164 | ETL.3190 | 40591568 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115718508 | T2 EI CARIBOU-PLERMO :027/221 RPR MEMBER | 44069454 | CARIBOU-PALERMO | :027/221 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  | Check FDA | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.432073 | 39.8164 | ETL.3190 | 40591568 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115718514 | T2 EI CARIBOU-PALERMO :29/237 RPR STRT | 44069801 | CARIBOU-PALERMO | :029/237 | ICQ | E | Pre-2020_(2) High fire spread TD |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.45426 | 39.7907 | ETL.3190 | 40826433 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115718520 | T2 EI CARIBOU-PALERMO :28/229 RPR FOND | 44069801 | CARIBOU-PALERMO | :028/229 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.444868 | 39.8042 | ETL.3190 | 40867374 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115718523 | T2 EI CARIBOU-PALERMO :28/230 RPR STRT | 44069801 | CARIBOU-PALERMO | :028/230 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.447747 | 39.8034 | ETL.3190 | 40618605 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115718524 | T2 EI CARIBOU-PALERMO :28/230 INST MRKS | 44069801 | CARIBOU-PALERMO | :028/230 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.447747 | 39.8034 | ETL.3190 | 40618605 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
115718536 | T2 EI CARIBOU-PALERMO :28/230 REPL INSS |  | CARIBOU-PALERMO | :028/230 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.447747 | 39.8034 | ETL.3190 | 40618605 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  | Yes
115718627 | T2NT EI CARIBOU-PALRMO :27/225 INST MRKS | 44302715 | CARIBOU-PALERMO | :027/225 | ICS | F | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.437982 | 39.8092 | ETL.3190 | 40758496 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Table Mountain
115718628 | T2 EI CARIBOU-PALRMO :27/225 BURIED MEMB | 44069801 | CARIBOU-PALERMO | :027/225 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.437982 | 39.8092 | ETL.3190 | 40758496 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115718676 | DI ATLANTIC-GOLD HILL 27/115 INS MRKS | 43742042 | ATLANTIC-GOLD HILL | 027/115 | ICS | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-121.140216 | 38.6831 | ETL.4330 | 40750992 | Marker (i.e. signs)-Steel | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes
115718679 | DI ATLANTIC-GOLD HILL 27/115 RPL HRDT | 43742041 | ATLANTIC-GOLD HILL | 027/115 | ICQ | E | Pre-2020_(5) TD tag on other lines |  | TLN/TLQ error |  |  | LATE | North Valley | WSIP | [6 empty] | '-121.140216 | 38.6831 | ETL.4330 | 40750992 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento
115718830 | T2 EI CARIBOU-PALERMO :27/227 RPL INSS |  | CARIBOU-PALERMO | :027/227 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP |  |  |  | Field Operations |  | '-121.441037 | 39.8063 | ETL.3190 | 40853816 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain
115718831 | T2NT CARIBOU-PALERMO :28/228 INS MRKS | 44302715 | CARIBOU-PALERMO | :028/228 | ICS | F | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.442288 | 39.805 | ETL.3190 | 40878267 | Marker (i.e. signs)-Steel | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Table Mountain
115718941 | EI DRUM-HIGGINS 014/134 CANCEL | 43687142 | DRUM-HIGGINS | 014/134 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  | CANCEL/CNCL |  | LATE | North Valley | WSIP | [6 empty] | '-120.974288 | 39.1539 | ETL.4393 | 40597230 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Sacramento |  |  | Yes
115719113 | T2 EI VACA-SUISUN-JAMS 007/056 REPL INSS | 31457373 | VACA-SUISUN-JAMESON | 007/056 | 93K | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.0211708 | 38.3524 | ETL.4080 | 40841333 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 532 | Sacramento |  |  | Yes
115719123 | T3 EI DRM-HGGNS 015/139 PNT STRT | 43687142 | DRUM-HIGGINS | 015/139 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  | Likely MAT error - delink to correct | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.987124 | 39.1488 | ETL.4393 | 40814105 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento |  |  | Yes
115719398 | T3 EI DRM-HGGNS 015/140 PNT STRT | 43687142 | DRUM-HIGGINS | 015/140 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  | Likely MAT error - delink to correct | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.989908 | 39.1477 | ETL.4393 | 40809704 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Sacramento |  |  | Yes
115719433 | T2 EI CORTINA-MEND #1 31/150 RPR FOND | 43721180 | CORTINA-MENDOCINO #1 | 031/150 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.745575 | 39.0608 | ETL.1330 | 40608370 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  | 2019-04-04
115719738 | T2 EI CORTINA-MENDO #1 31/149 RPR FOND | 43721180 | CORTINA-MENDOCINO #1 | 031/149 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.744034 | 39.0585 | ETL.1330 | 40860981 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville
115719757 | T2 EI EXCHEQUER-YSMTE 000/001A HV SIGN |  | EXCHEQUER-YOSEMITE | 000/001A | ICS | E | Pre-2020_(4b) On structure in bucket 4 | Project efficiency (capital work) | DLFL; Completed on project 74001200 |  | TR2 | LATE | South | WSIP | [6 empty] | '-119.986024 | 37.5935 | ETL.8650 | 43250171 | Marker (i.e. signs)-Steel | Missing | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  | Y - 36
115719837 | T3 EI DRM-HGGNS 016/141 RPR INSS | 43687117 | DRUM-HIGGINS | 016/141 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  | Likely MAT error - delink to correct | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.992547 | 39.1467 | ETL.4393 | 40862213 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Sacramento |  |  | Yes
115719851 | T2 EI CTTNWD-DELEVAN #1 10/069 REPL DAMS | 43726632 | COTTONWOOD-DELEVAN #1 | 010/069 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.267785 | 40.2442 | ETL.4550 | 40870759 | Damper-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
115719852 | T2 EI CORTINA-MENDO #1 031/148 RPR FOND | 43721181 | CORTINA-MENDOCINO #1 | 031/148 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.742882 | 39.0568 | ETL.1330 | 40870421 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  | 2019-04-04
115719902 | T2 EI CORTINA-MENDO #1 32/155 RPR FOND | 43721180 | CORTINA-MENDOCINO #1 | 032/155 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.753577 | 39.0725 | ETL.1330 | 40750577 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  | 2019-04-04
115720141 | T2 EI CARIBOU-PALERMO :018/156 RPR FOND | 44069597 | CARIBOU-PALERMO | :018/156 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.340824 | 39.9089 | ETL.3190 | 40738360 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115720161 | T2 EI VACA-PARKWAY 019/099 RPR JUMS | 43760157 | VACA-PARKWAY | 019/099 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Internal Process | 4/6: Too windy for the helicopter, no new scheduled date yet - V1KSCircuit Based Scheduling | '-122.143978 | 38.2345 | ETL.5850 | 40603696 | Jumper-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes
115720521 | T2 EI EXCHEQUER-YOSEMITE 2/14 RPR STRT | 43709740 | EXCHEQUER-YOSEMITE | 002/014 | ICQ | E | Pre-2020_(4) TD tag on high spread line | Project efficiency (capital work) | DLFL; Completed on project 74001200 |  | TR2 | LATE | South | WSIP | [6 empty] | '-120.237689 | 37.5777 | ETL.8650 | 40748149 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - Prog Multi
115720529 | EI DELEVAN-VACA #2 161/1223 INST HRDT | 43910525 | DELEVAN-VACA #2 | 161/1223 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  |  | LATE | North Valley | WSIP | FSRP |  |  |  |  | Priority Bucket 9 | '-122.116488 | 38.949 | ETL.4231 | 40650665 | Hardware-Tower | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento |  |  | Yes
115720578 | T2 EI CARIBOU-PALERMO :006/051 REPL INSS |  | CARIBOU-PALERMO | :006/051 | 93K | E | Pre-2020_(2) High fire spread TD |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.221517 | 40.0202 | ETL.3190 | 40910293 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  | Yes
115720602 | T2 EI VACA-PARKWAY 017/091 RPR JUMS | 43760157 | VACA-PARKWAY | 017/091 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Internal Process | 4/6: Too windy for the helicopter, no new scheduled date yet - V1KSCircuit Based Scheduling | '-122.138664 | 38.2565 | ETL.5850 | 40664069 | Jumper-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes
115720617 | T2 EI CARIBOU-PALERMO :06/53 BURIED MEMB | 44059014 | CARIBOU-PALERMO | :006/053 | ICQ | E | Pre-2020_(2) High fire spread TD |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.223574 | 40.0149 | ETL.3190 | 40910295 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115720646 | T2 EI CARIBOU-PALERMO :06/053 BENT MEMB | 44059014 | CARIBOU-PALERMO | :006/053 | ICQ | E | Pre-2020_(2) High fire spread TD |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.223574 | 40.0149 | ETL.3190 | 40910295 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115720648 | T3 EI MORAGA-SAN LE #2 0/006 RPL SPLS | 43708450 | MORAGA-SAN LEANDRO #2 | 000/006 | ICS | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.164492 | 37.8361 | ETL.2780 | 40850662 | Splice-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - 1 | 2019-03-17
115720668 | T2 EI HIGGINS-BELL 028/217 RPR SPLS | 43740275 | HIGGINS-BELL | 028/217 | ICS | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.08214 | 39.0318 | ETL.1412 | 40593236 | Splice-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes
115720784 | T2 EI CORTINA-MENDO #1 32/157 RPR FOND | 43721180 | CORTINA-MENDOCINO #1 | 032/157 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.756031 | 39.0761 | ETL.1330 | 40818158 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  | 2019-04-04
115721009 | T2 EI CSCD-BNTN-DSCHTS A7/155 RPR GYWW | 43690811 | CASCADE-BENTON-DESCHUTES | A007/155 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.260844 | 40.5657 | ETL.6310 | 40816322 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
115721021 | T2 EI CARIBOU-PALERMO :26/212 RPL INSS |  | CARIBOU-PALERMO | :026/212 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.42118 | 39.8307 | ETL.3190 | 40674984 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  | Yes
115721051 | DI PLACER-GOLD HILL #1 16/112 RMV DEBRIS | 43932211 | PLACER-GOLD HILL #1 | 016/112 | ICS | E | Pre-2020_(9a) Other ignition related |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-121.147436 | 38.6832 | ETL.3340 | 40906513 | Conductor-Steel | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento
115721295 | T2 EI PIT#3-CARBERY SW ST 0/9 REPL SPLS | 43755519 | PIT #3-CARBERRY SW STA | 000/009 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.747005 | 40.9782 | ETL.5450 | 40870261 | Splice-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
115721368 | T2NT EI CRESTA-RIO OSO 008/072A PAINT | 43708739 | CRESTA-RIO OSO | 008/072A | ICS | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.421964 | 39.8293 | ETL.4590 | 41162726 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
115721609 | T2 EI CARIBOU-PALERMO :018/156 INST HRDT | 44069597 | CARIBOU-PALERMO | :018/156 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.340824 | 39.9089 | ETL.3190 | 40738360 | Hardware-Tower | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115721736 | T2 EI CORTINA-MENDO #1 35/170 RPR FOND | 43721180 | CORTINA-MENDOCINO #1 | 035/170 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.796553 | 39.1051 | ETL.1330 | 40587897 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville
115722109 | T2 DI PLACER-GOLD HILL #1 8/61 CANCEL | 43910532 | PLACER-GOLD HILL #1 | 008/061 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  | CANCEL/CNCL | TR2 | LATE | North Valley | WSIP | FSRP |  |  |  | Internal Process |  | '-121.134416 | 38.7852 | ETL.3340 | 40911171 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento |  |  | Yes
115722178 | T2 EI BALCH-SANGER 003/022 REPL DAMS | 43684626 | BALCH-SANGER | 003/022 | ICS | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-119.124367 | 36.8788 | ETL.1050 | 40652360 | Damper-Steel | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  | Y - 17
115734569 | T2 EI CARIBOU-PALERMO :28/231 RPR STRT | 44069801 | CARIBOU-PALERMO | :028/231 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.449917 | 39.8027 | ETL.3190 | 40591569 | Structure-Tower | Anti-Climbing Guard | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115734822 | T2 EI CARIBOU-PALERMO :28/231 RPR GYWS | 44304495 | CARIBOU-PALERMO | :028/231 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.449917 | 39.8027 | ETL.3190 | 40591569 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
115734824 | T2 EI CARIBOU-PALERMO :28/231 INST MRKS | 44069801 | CARIBOU-PALERMO | :028/231 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  |  | Check FDA | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.449917 | 39.8027 | ETL.3190 | 40591569 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
115734962 | T2NT EI CARIBOU-PALRMO :26/218 INST MRKS | 44302715 | CARIBOU-PALERMO | :026/218 | ICS | F | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.427709 | 39.8217 | ETL.3190 | 40867976 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Table Mountain
115734967 | T2 EI BALCH-SANGER 0/6 CVRD FOUNDATION | 43709595 | BALCH-SANGER | 000/006 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | South | WSIP | FSRP | [5 empty] | '-119.0984223 | 36.9076 | ETL.1050 | 40954394 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 17
115734970 | T2 EI CARIBOU-PALERMO :26/218 RPL SPLS | 44070463 | CARIBOU-PALERMO | :026/218 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.427709 | 39.8217 | ETL.3190 | 40867976 | Splice-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain
115734971 | T2 EI CARIBOU-PALERMO :26/218 BENT MEMB | 44304495 | CARIBOU-PALERMO | :026/218 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.427709 | 39.8217 | ETL.3190 | 40867976 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Table Mountain
115735145 | T2 EI CARIBOU-PALERMO :026/220 INST MRKS | 44069454 | CARIBOU-PALERMO | :026/220 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  |  | Check FDA | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.429893 | 39.8191 | ETL.3190 | 40618608 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115735192 | T2 EI CARIBOU-PALERMO :026/220 RPR ST | 44069454 | CARIBOU-PALERMO | :026/220 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.429893 | 39.8191 | ETL.3190 | 40618608 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115735194 | T2 EI CARIBOU-PALERMO :26/220 REPL INSS |  | CARIBOU-PALERMO | :026/220 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.429893 | 39.8191 | ETL.3190 | 40618608 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain
115735242 | T2 EI CRESTA-RIO OSO 008/072B RPR JUMP | 43708739 | CRESTA-RIO OSO | 008/072B | ICS | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.421963 | 39.8294 | ETL.4590 | 41162727 | Jumper-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
115735555 | T3 EI DRUM-HIGGINS 016/142 CONS | 43738143 | DRUM-HIGGINS | 016/142 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.996523 | 39.1451 | ETL.4393 | 40865240 | Conductor-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes
115735639 | T3 EI DRUM-HIGGINS 016/142 RPL SPLS | 43687142 | DRUM-HIGGINS | 016/142 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  | Likely MAT error - delink to correct | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.996523 | 39.1451 | ETL.4393 | 40865240 | Splice-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes
115735721 | T3 EI DRUM-HIGGINS 016/142 CANCEL | 43687142 | DRUM-HIGGINS | 016/142 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  | CANCEL/CNCL | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.996523 | 39.1451 | ETL.4393 | 40865240 | Splice-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes
115735747 | T3 EI DRUM-HIGGINS 016/142 RPR CONS | 43687142 | DRUM-HIGGINS | 016/142 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  | Likely MAT error - delink to correct | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.996523 | 39.1451 | ETL.4393 | 40865240 | Conductor-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes
115735921 | T2 EI CORTINA-MENDO #1 33/159 RPR FOND | 43721180 | CORTINA-MENDOCINO #1 | 033/159 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.761358 | 39.0803 | ETL.1330 | 40870087 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  | 2019-04-04
115736166 | T2 EI RND MT-CTNWD #3-R001/016 INST MRKW | 43755804 | ROUND MTN-COTTONWOOD #3 | R001/016 | ICW | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.935935 | 40.7985 | ETL.5650 | 40811269 | Marker (i.e. signs)-Wood | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
115736171 | T2 EI RND MTN-CTTNWD #3 R1/15L MRKW | 43755804 | ROUND MTN-COTTONWOOD #3 | R001/015 | ICW | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.935829 | 40.7997 | ETL.5650 | 44737543 | Marker (i.e. signs)-Wood | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
115736500 | T2 EI RND MTN-CTTNWD #3 R001/017 REPAINT | 43755803 | ROUND MTN-COTTONWOOD #3 | R001/017 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.936067 | 40.797 | ETL.5650 | 40810238 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
115736520 | T2 EI RND MTN-CTTNWD #3 R001/017 JUMS | 43755803 | ROUND MTN-COTTONWOOD #3 | R001/017 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.936067 | 40.797 | ETL.5650 | 40810238 | Jumper-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
115736566 | T2 EI VC-VCVLL-JAMESON-NTH TWR INST HRDT | 43740642 | VACA-VACAVILLE-JAMESON-NTH TWR | 008/062 | ICQ | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP |  |  |  |  | Priority Bucket 9 | '-122.030828 | 38.3414 | ETL.4100 | 40650934 | Hardware-Tower | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento |  |  | Yes
115736630 | T2 EI CARIBOU-PALERMO :4/034 RPR STRT | 44059014 | CARIBOU-PALERMO | :004/034 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.210326 | 40.0495 | ETL.3190 | 40910278 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115736694 | T3 EI DRM-HGGNS 016/145 RPR CONS | 43687142 | DRUM-HIGGINS | 016/145 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  | Likely MAT error - delink to correct | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.006557 | 39.1411 | ETL.4393 | 40913041 | Conductor-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes
115736909 | T2NT EI RND MTN-CTNWD#3 R1/18L INS MRKW | 43755804 | ROUND MTN-COTTONWOOD #3 | R001/018 | ICW | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.936725 | 40.7957 | ETL.5650 | 44737545 | Marker (i.e. signs)-Wood | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
115737014 | EI TRINITY-COTTONWOOD 11/87R REPL PL | 31455647 | TRINITY-COTTONWOOD | 011/087 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-122.420759 | 40.5099 | ETL.4040 | 44558225 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
115737088 | T2 EI RND MTN-CTTNWD #2 039/317 RPR INSS | 43876311 | ROUND MTN-COTTONWOOD #2 | 039/317 | ICS | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.2023539 | 40.4885 | ETL.5640 | 40839652 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain
115737186 | T2 EI CARIBOU-TABLE MTN 012/093 RPR STRT | 31454671 | CARIBOU-TABLE MTN | 012/093 | 70S | F | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP |  |  | REJECT: Crew reported work not needed. Please confirm(approve) or reject if disagree. |  |  | '-121.21733 | 40.0432 | ETL.4440 | 40662309 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Pole Program | Capital | 426 | Table Mountain |  | Yes
115737189 | T2 EI RND MTN-CTTNWD #3 027/222 RPR JUMS | 43755803 | ROUND MTN-COTTONWOOD #3 | 027/222 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.939278 | 40.7909 | ETL.5650 | 40668261 | Jumper-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
115737271 | EI DLVAN-VCA #2 162/1229 INS RPTR GRD | 31436101 | DELEVAN-VACA #2 | 162/1229 | 93R | F | Pre-2020_(9a) Other ignition related |  |  |  |  | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.109652 | 38.9377 | ETL.4231 | 40870217 | Raptor Guard-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 530 | Sacramento |  |  | Yes
115737403 | T2 EI CARIBOU-PALERMO :5/040 RPR CONS | 44070463 | CARIBOU-PALERMO | :005/040 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.21813 | 40.0392 | ETL.3190 | 40910283 | Conductor-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
115737407 | T2 EI CORTINA-MENDO #1 39/190 RPL SPLT | 43721139 | CORTINA-MENDOCINO #1 | 039/190 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.860251 | 39.1368 | ETL.1330 | 40587903 | Splice-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Lakeville |  |  | 2019-04-04
115737441 | EI HIGGINS-BELL 035/263 RMV VEGN |  | HIGGINS-BELL | 035/263 | HNA | E | Pre-2020_(9a) Other ignition related |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-121.056345 | 38.9398 | ETL.1412 | 40816901 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  | Yes
115737534 | T2 EI RND MTN-CTTNWD #3 R2/20 RPL INSS | 31431455 | ROUND MTN-COTTONWOOD #3 | R002/020 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.937705 | 40.7928 | ETL.5650 | 40604759 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  | Yes
115737558 | T2 EI CORTINA-MENDO #1 36/173 RPR FOND | 43721180 | CORTINA-MENDOCINO #1 | 036/173 | ICQ | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.80423 | 39.1092 | ETL.1330 | 40648767 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville
115737981 | T2 EI CARIBOU-PALERMO :25/208 BENT MEMB | 44069454 | CARIBOU-PALERMO | :025/208 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.419325 | 39.8395 | ETL.3190 | 40878271 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115738355 | T2 EI CARIBOU-PALERMO :24/204 REPAINT | 44302715 | CARIBOU-PALERMO | :024/204 | ICS | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.414213 | 39.8445 | ETL.3190 | 40771768 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Table Mountain
115738356 | T2 EI BALCH-SANGER 001/011 RUST REPAINT | 43848550 | BALCH-SANGER | 001/011 | ICS | E | Pre-2020_(9a) Other ignition related | Budget Owner (Paint) |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-119.116429 | 36.903 | ETL.1050 | 40583098 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Fresno |  | Y - 17
115738361 | T2 EI BALCH-SANGER 001/009 RPR CONS | 43684626 | BALCH-SANGER | 001/009 | ICS | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-119.110094 | 36.9046 | ETL.1050 | 40859624 | Conductor-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  | Y - 17
115738406 | T2 EI CARIBOU-PALERMO :24/202 RPL INSS |  | CARIBOU-PALERMO | :024/202 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.409795 | 39.8476 | ETL.3190 | 40674980 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain
115738407 | T2 EI CARIBOU-PALRMO :024/201 RPR MEMBER | 44069454 | CARIBOU-PALERMO | :024/201 | ICQ | E | Pre-2020_(2) High fire spread TD |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.408343 | 39.8486 | ETL.3190 | 40591566 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115739270 | T2 EI CARIBOU-PALERMO :024/203 BENT MEMB | 44069454 | CARIBOU-PALERMO | :024/203 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  | Check FDA | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.413518 | 39.8449 | ETL.3190 | 40651675 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115739280 | T2 EI ROCK CREEK-POE 006/046 RPAINT STRT | 43724472 | ROCK CREEK-POE | 006/046 | ICQ | F | Pre-2020_(9a) Other ignition related |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.415344 | 39.8446 | ETL.5630 | 40820423 | Structure-Tower | Paint/Coating | Repaint | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
115739295 | T2 EI HUMBOLDT-TRINITY 63/03C RPR GYWW | 43729542 | HUMBOLDT-TRINITY | 063/003 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.220224 | 40.7425 | ETL.1820 | 44562966 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Eureka |  |  | 2019-08-09
115739301 | T2NT EI HUMBOLDT-TRINITY 63/3C INST MRKW | 43729542 | HUMBOLDT-TRINITY | 063/003 | ICW | F | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.220224 | 40.7425 | ETL.1820 | 44562966 | Marker (i.e. signs)-Wood | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Eureka |  |  | 2019-08-09
115739302 | T2 EI HUMBOLDT-TRINITY 063/003 REPL SPLW | 43729542 | HUMBOLDT-TRINITY | 063/003 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.220224 | 40.7425 | ETL.1820 | 44562966 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Eureka |  |  | 2019-08-09
115739518 | T3 EI DRUM-HIGGINS 016/143 PNT STRT | 43687142 | DRUM-HIGGINS | 016/143 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) |  | Likely MAT error - delink to correct | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.999826 | 39.1438 | ETL.4393 | 40604652 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes
115739548 | T2 EI CRESTA-RIO OSO 8/74 RPL SPLS | 43708739 | CRESTA-RIO OSO | 008/074 | ICS | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.424997 | 39.8255 | ETL.4590 | 40907013 | Splice-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
115739608 | T2 EI CARIBOU-PALERMO :27/226 RPR SPLS | 44304495 | CARIBOU-PALERMO | :027/226 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.438961 | 39.8082 | ETL.3190 | 40828380 | Splice-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain
115739640 | T2 EI CRESTA-RIO OSO 8/74 RPR INSS | 43708739 | CRESTA-RIO OSO | 008/074 | ICS | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.4236839 | 39.8273 | ETL.4590 | 40916714 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
115739641 | T2 CARIBOU-PALERMO :24/197 RPR STRT | 44304495 | CARIBOU-PALERMO | :024/197 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.400639 | 39.8521 | ETL.3190 | 40815588 | Crossarm-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Table Mountain
115739645 | T2 EI CRESTA-RIO OSO 9/75 RPR INSS | 43708739 | CRESTA-RIO OSO | 009/075 | ICS | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.425452 | 39.825 | ETL.4590 | 40907014 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
115739653 | T2 EI ROCK CREEK-POE 009/065 RPL HRDT | 43724474 | ROCK CREEK-POE | 009/065 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.438985 | 39.8092 | ETL.5630 | 40762480 | Hardware-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
115739654 | T2 EI CRESTA-RIO OSO 9/75 RPL SPLS | 43708739 | CRESTA-RIO OSO | 009/075 | ICS | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.425452 | 39.825 | ETL.4590 | 40907014 | Splice-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
115739670 | T3 EI DRUM-HIGGINS 016/143 RPL SPLS | 43687142 | DRUM-HIGGINS | 016/143 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  | Likely MAT error - delink to correct | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.999826 | 39.1438 | ETL.4393 | 40604652 | Splice-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes
115739868 | EI HIGGINS-BELL 035/260 SPLS | 43740275 | HIGGINS-BELL | 035/260 | ICS | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-121.052019 | 38.9444 | ETL.1412 | 40762907 | Splice-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes
115740348 | T2 EI CORTINA-MENDO #1 38/182 RPL INSS | 31432492 | CORTINA-MENDOCINO #1 | 038/182 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.832153 | 39.1232 | ETL.1330 | 40710766 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 532 | Lakeville |  |  | 2019-04-04
115740506 | T2 EI CORTINA-MENDO #1 040/192 RPR INSS | 43761282 | CORTINA-MENDOCINO #1 | 040/192 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.863152 | 39.1377 | ETL.1330 | 40657074 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Lakeville
115740641 | T2 EI CORTINA-MENDO #1 060/296 RPR FOND | 43721181 | CORTINA-MENDOCINO #1 | 060/296 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.18768 | 39.2459 | ETL.1330 | 40809308 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville
115740702 | EI RNDMTN-CTNWD#2 036/301 RPR CNDS | 43947332 | ROUND MTN-COTTONWOOD #2 | 036/301 | ICS | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-122.184579 | 40.5241 | ETL.5640 | 40594962 | Conductor-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain
115740854 | T2 EI HUMBOLDT-TRINITY 091/004 RPR GYWW | 43729543 | HUMBOLDT-TRINITY | 091/004 | ICW | E | Pre-2020_(2) High fire spread TD |  |  |  | TR2 | LATE | North Coast | WSIP |  |  |  |  | Project | 2021 HUMBOLDT-TRINITY | '-123.70711 | 40.7485 | ETL.1820 | 44560531 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Eureka |  |  | 2019-03-30
115740916 | T3 EI RND MTN-CTTNWD #3 028/235 RPL INSS | 31424180 | ROUND MTN-COTTONWOOD #3 | 028/235 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.9517036 | 40.7761 | ETL.5650 | 40792333 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  | Yes
115740942 | T2 EI METCALF-GREEN VLY 009/057 REPAINT | 44300668 | METCALF-GREEN VALLEY | 009/057 | ICS | F | Pre-2020_(9a) Other ignition related | Budget Owner (Paint) |  |  | TR2 | LATE | South | WSIP | FSRP | [5 empty] | '-121.666854 | 37.1338 | ETL.2540 | 40808555 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Moss Landing
115741211 | T2 EI CARIBOU-PALERMO :004/032 REPL INSS | 31426590 | CARIBOU-PALERMO | :004/032 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.206261 | 40.0532 | ETL.3190 | 40910276 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain
115741219 | T2 EI VACA-SUISUN 10/078 REPAINT | 43740501 | VACA-SUISUN | 010/078 | ICD | F | Pre-2020_(3) On high spread structure | Budget Owner (Paint) |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Program | 2021 | '-122.052407 | 38.307 | ETL.4070 | 40865461 | Structure-Tower | Paint/Coating | Repaint | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense |  | Sacramento |  |  | Yes
115741287 | T2 EI MEDOCNO-RDBD 60/295 RPL SPLS | 43721139 | MENDOCINO-REDBUD | 060/295 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.185825 | 39.2447 | ETL.2410 | 40779105 | Splice-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Lakeville |  |  | 2019-04-04
115741288 | T2 EI CARIBOU-PALERMO :05/045 REPAINT | 44302715 | CARIBOU-PALERMO | :005/045 | ICS | F | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.218992 | 40.0312 | ETL.3190 | 40910287 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain
115741375 | T2 EI CORTINA-MENDO #1 59/294 RPR MEMBER | 43721181 | CORTINA-MENDOCINO #1 | 059/294 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.184946 | 39.2442 | ETL.1330 | 40750616 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 543 | Lakeville |  |  | 2019-04-04
115741402 | T2 EI HIGGINS-BELL 035/259 RPL SPLS | 43740275 | HIGGINS-BELL | 035/259 | ICS | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.049846 | 38.9467 | ETL.1412 | 40663157 | Splice-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes
115741530 | T2 EI KRKHF-CLVS-SNGR #1 06/045 RPR FOND | 43709693 | KERCKHOFF-CLOVIS-SANGER #1 | 006/045 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | South | WSIP | FSRP | [5 empty] | '-119.603319 | 36.972 | ETL.1890 | 40764698 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - Prog Multi
115741588 | T2 EI KRKHF-CLVS-SNGR #1 06/046 RPL RPTS | 43709695 | KERCKHOFF-CLOVIS-SANGER #1 | 006/046 | ICB | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | South | WSIP | FSRP | [5 empty] | '-119.60245 | 36.97 | ETL.1890 | 40807006 | Raptor Guard-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 593 | Fresno |  | Y - Prog Multi
115741598 | T2 CARIBOU-PALERMO :4/036 RPR HRDT | 44069455 | CARIBOU-PALERMO | :004/036 | ICQ | F | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.21611 | 40.0461 | ETL.3190 | 40910280 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115741725 | EI PHILO JCT-ELK - 019/000B RPL POLE | 31501453 | PHILO JCT-ELK | 019/000B | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | North Coast | WSIP | [6 empty] | '-123.437957 | 39.0639 | ETL.7780 | 40740541 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC erdy srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  | 2019-04-04
115741762 | WEIMAR-HALSEY - 60 kV_003/072 | 31454601 | WEIMAR-HALSEY | 003/072 | 70Y | F | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-121.00979 | 38.9916 | ETL.8340 | 40822754 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento
115741900 | T2 EI MTCLF-MSS LNDNG #1 33/151 PNT STRT | 44300665 | METCALF-MOSS LANDING #1 | 033/151 | ICS | E | Pre-2020_(9a) Other ignition related | Budget Owner (Paint) |  |  | TR2 | LATE | South | WSIP | FSRP | [5 empty] | '-121.680147 | 37.1433 | ETL.5100 | 40587032 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Moss Landing
115741934 | T2 EI VACA-PARKWAY 14/77 INS HDWT | 43760159 | VACA-PARKWAY | 014/077 | ICQ | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP |  |  |  |  | Priority Bucket 9 | '-122.132055 | 38.2958 | ETL.5850 | 40821356 | Hardware-Tower | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento |  |  | Yes
115742010 | T2 EI CARIBOU-PALERMO :06/046 RPL HRDS | 44070463 | CARIBOU-PALERMO | :006/046 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.219048 | 40.0305 | ETL.3190 | 40910288 | Hardware-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain
115742325 | T2 EI CORTINA-MENDO #1 059/293 RPR FOND | 43760958 | CORTINA-MENDOCINO #1 | 059/293 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.180753 | 39.2418 | ETL.1330 | 40659631 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville
115742470 | T2 EI CORTINA-MENDOCINO #1 046/228 CONS | 43721139 | CORTINA-MENDOCINO #1 | 046/228 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.957677 | 39.1928 | ETL.1330 | 40861163 | Conductor-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Lakeville
115742589 | T2 EI CORTINA-MEND #1 59/287 RPL HRDT | 43721181 | CORTINA-MENDOCINO #1 | 059/287 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.168048 | 39.2418 | ETL.1330 | 40808543 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  | 2019-04-04
115742700 | T2 EI CORTINA-MEND #1 59/287 RPR STRT | 43721181 | CORTINA-MENDOCINO #1 | 059/287 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.168048 | 39.2418 | ETL.1330 | 40808543 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 543 | Lakeville |  |  | 2019-04-04
115742703 | T2 EI CORTINA-MEND #1 59/287 WASH INSS | 43720999 | CORTINA-MENDOCINO #1 | 059/287 | ICD | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.168048 | 39.2418 | ETL.1330 | 40808543 | Insulator | Contaminated | Ground Wash | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 622 | Lakeville |  |  | 2019-04-04
115742708 | T2 EI CTTNWD-DELEVN #2 067/591 STRT | 43730227 | COTTONWOOD-DELEVAN #2 | 067/591 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.267862 | 40.2929 | ETL.4580 | 40597356 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
115754392 | T2 EI BCKS-RCK-CRSTA :0/6 INSTL MRKS | 43742056 | BUCKS CREEK-ROCK CREEK-CRESTA | :000/006 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.355287 | 39.9047 | ETL.4430 | 40816401 | Marker (i.e. signs)-Steel | No Good/Out of Stdrd | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
115754583 | T2 EI CARIBOU-PALERMO :016/131 RPR STRT | 44304495 | CARIBOU-PALERMO | :016/131 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.318389 | 39.9316 | ETL.3190 | 40642565 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
115754585 | T2 EI BCKS CRK-RCK CRK-CRST 006/054 INSS | 31450543 | BUCKS CREEK-ROCK CREEK-CRESTA | 006/054 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.4182442 | 39.8411 | ETL.4430 | 40788518 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  | Yes
115754597 | T2 EI CARIBOU-PALERMO :016/131 RPR STRT | 44069597 | CARIBOU-PALERMO | :016/131 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.318389 | 39.9316 | ETL.3190 | 40642565 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
115754612 | T2 EI CARIBOU-PALERMO :021/181 RPR STRT | 44304495 | CARIBOU-PALERMO | :021/181 | ICS | E | Pre-2020_(2) High fire spread TD |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.37771 | 39.873 | ETL.3190 | 40642568 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
115754656 | T2 EI CARIBOU-PALERMO :22/182 RPL HRDT | 44304495 | CARIBOU-PALERMO | :022/182 | ICS | E | Pre-2020_(2) High fire spread TD |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.37803 | 39.8724 | ETL.3190 | 40738807 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain
115754659 | T2 EI DRM-HGGNS 020/161 PNT TWR | 43687142 | DRUM-HIGGINS | 020/161 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.056277 | 39.1196 | ETL.4393 | 40913057 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes
115754697 | T2 EI CARIBOU-PALERMO :021/181 RPNT TWR | 44304495 | CARIBOU-PALERMO | :021/181 | ICS | E | Pre-2020_(3) On high spread structure |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.37771 | 39.873 | ETL.3190 | 40642568 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
115754783 | T2NT EI HAT CRK #1-WSTWD 13/265 INS MRKW | 43736796 | HAT CREEK #1-WESTWOOD | 013/265 | ICW | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.357193 | 40.8086 | ETL.7030 | 40616862 | Marker (i.e. signs)-Wood | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
115754794 | T2 Mendocino Red Bud_032/157 | 43919493 | MENDOCINO-REDBUD | 032/157 | ICS | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-122.756226 | 39.0764 | ETL.2410 | 40844454 | Damper-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville |  |  | 2019-08-06
115754799 | T2 EI HIGGINS-BELL 031/232 RPR SPLS | 43740275 | HIGGINS-BELL | 031/232 | ICS | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.061476 | 38.9999 | ETL.1412 | 40824195 | Splice-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes
115754802 | T2 EI DRM-HGGNS 020/162 RPR JUMS | 43687142 | DRUM-HIGGINS | 020/162 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.057427 | 39.1183 | ETL.4393 | 40913058 | Jumper-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes
115754813 | T2 EI VACA-SUISUN 10/075 REPL INSS | 31457373 | VACA-SUISUN-JAMESON | 010/075 | 93K | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.0477539 | 38.3146 | ETL.4080 | 40773365 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 532 | Sacramento |  |  | Yes
115754863 | T3 EI RND MT-CTTNWD #3 33/281 RPL INSS | 31431455 | ROUND MTN-COTTONWOOD #3 | 033/281 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.9989165 | 40.7191 | ETL.5650 | 40617505 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  | Yes
115754982 | T2 EI VACA-SUISUN-JAMS 10/074 REPL INSS | 31457373 | VACA-SUISUN-JAMESON | 010/074 | 93K | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.046683 | 38.3163 | ETL.4080 | 40785519 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 532 | Sacramento |  |  | Yes
115754995 | T2 EI VACA-SUISUN-JAMS 10/73 REPL INSS | 31457373 | VACA-SUISUN-JAMESON | 010/073 | 93K | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.0458736 | 38.3176 | ETL.4080 | 40682755 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 532 | Sacramento |  |  | Yes
115755025 | T2 EI DRM-HGGNS 020/164 RPL INSS | 31499112 | DRUM-HIGGINS | 020/164 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.0624766 | 39.116 | ETL.4393 | 40922904 | Insulator-Steel | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Sacramento |  |  | Yes
115755047 | T2 EI ROUND MTN-CO #2 42/335 INSTL MRKS | 43877040 | ROUND MTN-COTTONWOOD #2 | 042/335 | ICS | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-122.225125 | 40.4478 | ETL.5640 | 40765343 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
115755063 | T2 EI BALCH-SANGER 001/012 RUST REPAINT | 43848550 | BALCH-SANGER | 001/012 | ICS | E | Pre-2020_(9a) Other ignition related | Budget Owner (Paint) |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-119.120545 | 36.902 | ETL.1050 | 40682227 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Fresno |  | Y - 17
115755066 | T2 EI CARIBOU-PALERMO :002/019 RPR STRT | 44070463 | CARIBOU-PALERMO | :002/019 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.182939 | 40.0665 | ETL.3190 | 40910263 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain
115755085 | T2 EI CORTINA-MENDO #1 47/230 RPR FOND | 43721181 | CORTINA-MENDOCINO #1 | 047/230 | ICQ | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.962089 | 39.1968 | ETL.1330 | 40608372 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  | 2019-04-04
115755141 | T2 EI DRUM-HIGGINS 020/165 PNT TWR | 43687142 | DRUM-HIGGINS | 020/165 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.066296 | 39.1157 | ETL.4393 | 40913061 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes
115755224 | T2 EI PT #5-RND MTN #1 3/32 PAINT STRT | 44322478 | PIT #5-ROUND MTN #1 | 003/032 | ICS | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.946484 | 40.9497 | ETL.5420 | 40660954 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
115755232 | T2 EI PIT #5-RNDMTN #1 000/005 PNT TWR | 44322478 | PIT #5-ROUND MTN #1 | 000/005 | ICS | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.968361 | 40.9803 | ETL.5420 | 40752302 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
115755246 | T2 EI CHC-SAL-SOL #2 :10/55 RPL CNDS | 31511873 | MOSS LANDING-SALINAS-SOLEDAD #2 | :010/055 | 93C | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-121.475392 | 36.6263 | ETL.2910 | 40781230 | Conductor-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 531 | Moss Landing |  | Y - SS | 2019-04-17
115755249 | T2 EI CORTINA-MENDO #1 048/235 RPR FOND | 43721181 | CORTINA-MENDOCINO #1 | 048/235 | ICQ | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.979693 | 39.2025 | ETL.1330 | 40750593 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  | 2019-04-04
115755283 | T2 EI ROUND MTN-CO #2 27/241 RPL SPLS | 43947333 | ROUND MTN-COTTONWOOD #2 | 027/241 | ICS | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.0882 | 40.6386 | ETL.5640 | 40595020 | Splice-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
115755296 | T2 EI ROUND MTN-CO #2 13/142 RPR INSS | 43876311 | ROUND MTN-COTTONWOOD #2 | 013/142 | ICS | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.937628 | 40.7945 | ETL.5640 | 40674336 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
115755361 | T2 EI CHC-SAL-SOL #2 :010/056 RPL CNDS | 31511873 | MOSS LANDING-SALINAS-SOLEDAD #2 | :010/056 | 93C | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-121.4712728 | 36.6259 | ETL.2910 | 40838080 | Conductor-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 531 | Moss Landing |  | Y - SS | 2019-04-17
115755449 | T2 EI CARIBOU-PALERMO :016/132 REPL INSS |  | CARIBOU-PALERMO | :016/132 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.318489 | 39.9304 | ETL.3190 | 40738350 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  | Yes
115755450 | T2 EI CARIBOU-PALERMO :016/132 REPL HRDT | 44304495 | CARIBOU-PALERMO | :016/132 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.318489 | 39.9304 | ETL.3190 | 40738350 | Hardware-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
115755451 | T2 EI RO DLL JT-BRDGVLLE 33/06 RPL CONW | 31473341 | RIO DELL JCT-BRIDGEVILLE | 033/006 | 93C | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.896831 | 40.4848 | ETL.7850 | 40808722 | Conductor-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 638 | Eureka |  |  | 2019-08-01
115755516 | T2 EI BRIDGEVILLE-CTNWD 036/292 RPR FOND | 43706644 | BRIDGEVILLE-COTTONWOOD | 036/292 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.95442 | 40.3675 | ETL.1110 | 40762887 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
115755545 | T2 EI CARIBOU-PALRMO :16/135 BURIED MEMB | 44069583 | CARIBOU-PALERMO | :016/135 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.318466 | 39.9265 | ETL.3190 | 40753307 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115755687 | T2 EI CARIBOU-PALERMO :020/160 RPR STRT | 44069454 | CARIBOU-PALERMO | :020/160 | ICQ | E | Pre-2020_(2) High fire spread TD |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.353207 | 39.9056 | ETL.3190 | 40642284 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115756260 | T2 EI BALCH-SANGER 003/023 RPR FOND | 43700488 | BALCH-SANGER | 003/023 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-119.127419 | 36.879 | ETL.1050 | 40657794 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 17
115756391 | T2 EI CARIBOU-PALERMO :21/177 INS HRDT | 44304495 | CARIBOU-PALERMO | :021/177 | ICS | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.372498 | 39.8832 | ETL.3190 | 40738367 | Hardware-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain
115756392 | T2 EI CARIBOU-PALERMO :21/177 PAINT STRT | 44302715 | CARIBOU-PALERMO | :021/177 | ICS | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.372498 | 39.8832 | ETL.3190 | 40738367 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain
115756460 | T2 EI HIGGINS-BELL 33/251 RPL SPLS | 43740275 | HIGGINS-BELL | 033/251 | ICS | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.042373 | 38.9618 | ETL.1412 | 40762676 | Splice-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento
115756598 | T2 EI CARIBOU-PALERMO :2/021 RPL HRDT | 44062862 | CARIBOU-PALERMO | :002/021 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.189644 | 40.0629 | ETL.3190 | 40910265 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115756680 | T2 EI HMBLDT-BRDGVLL 113/7 RPR INSW | 43749687 | HUMBOLDT-BRIDGEVILLE | 113/007 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | FSRP | [5 empty] | '-124.073848 | 40.7722 | ETL.1810 | 40854183 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Eureka |  |  | 2019-04-03
115756799 | T2 EI VACA-SUISUN-JAMS 11/081 REPL INSS | 31457373 | VACA-SUISUN-JAMESON | 011/081 | 93K | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.057467 | 38.2989 | ETL.4080 | 40614350 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 532 | Sacramento
115756813 | T2 EI VAC-VAC-JAM-N T 009/072 INST HRDT | 43740642 | VACA-VACAVILLE-JAMESON-NTH TWR | 009/072 | ICQ | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP |  |  |  |  | Priority Bucket 9 | '-122.044556 | 38.3201 | ETL.4100 | 40653589 | Hardware-Tower | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento |  |  | Yes
115756942 | T2 EI STANISLAUS-MAN #2 10/64 INST MRKS | 43713081 | STANISLAUS-MANTECA #2 | 010/064 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.534547 | 38.0589 | ETL.3820 | 40744466 | Marker (i.e. signs)-Steel | No Good/Out of Stdrd | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Victor |  | Y - Prog Multi
115756947 | T2 EI HIGGINS-BELL 031/236 RPR JUMS | 43740275 | HIGGINS-BELL | 031/236 | ICS | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.056654 | 38.9925 | ETL.1412 | 40602396 | Jumper-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes
115757104 | T2 EI RND MTN-CTTN #2 014/145 INST HRDT | 43876311 | ROUND MTN-COTTONWOOD #2 | 014/145 | ICS | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.941499 | 40.7901 | ETL.5640 | 40758125 | Hardware-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
115757343 | T2 EI STANISLAUS-MAN #2 04/027 RPL HRDT | 43713081 | STANISLAUS-MANTECA #2 | 004/027 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.441921 | 38.1088 | ETL.3820 | 40809072 | Hardware-Steel | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Victor |  | Y - Prog Multi
115757379 | T2 EI CORTINA-MENDO #1 54/266 RPR FOND | 43721181 | CORTINA-MENDOCINO #1 | 054/266 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.081093 | 39.2201 | ETL.1330 | 40808943 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  | 2019-04-04
115757666 | T2 EI PIT#5-RUND MTN#2 12/121 REPAINT | 44343738 | PIT #5-ROUND MTN #2 | 012/121 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.938059 | 40.8092 | ETL.5430 | 40595120 | Structure-Tower | Paint/Coating | Repaint | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 543 | Table Mountain
115757962 | T2 EI STAN-MEL S S-M #1 :007/041 PAINT | 43712830 | STANISLAUS-MELONES SS-MANTECA #1+ | :007/041 | ICS | E | Pre-2020_(9a) Other ignition related | Budget Owner (Paint) |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.640332 | 37.9847 | ETL.3830 | 40579597 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - 9
115758143 | T2 EI CORTINA-MENDO #1 054/270 RPR FOND | 43721181 | CORTINA-MENDOCINO #1 | 054/270 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.094164 | 39.224 | ETL.1330 | 40587921 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  | 2019-04-04
115758199 | T2 EI ROUND MTN-CO #2 014/148 RPL DAMP | 43876311 | ROUND MTN-COTTONWOOD #2 | 014/148 | ICS | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.946273 | 40.7866 | ETL.5640 | 40867698 | Conductor-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
115758409 | T2 EI RND MTN-COTTON #2 014/149 RPL INSS | 31435968 | ROUND MTN-COTTONWOOD #2 | 014/149 | 93K | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.9486176 | 40.7849 | ETL.5640 | 40879341 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  | Yes
115758888 | T2 EI CARIBOU-PALERMO :002/017 RPR STRT | 44062862 | CARIBOU-PALERMO | :002/017 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.177753 | 40.0689 | ETL.3190 | 40910261 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115759055 | T2 EI ROUND MTN-COT #3 038/333 RPL INSS | 31431455 | ROUND MTN-COTTONWOOD #3 | 038/333 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.0520811 | 40.6559 | ETL.5650 | 40686374 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  | Yes
115759184 | T2 EI PT#5-RUND MTN#1 6/71 REPL DAM | 43758395 | PIT #5-ROUND MTN #1 | 006/071 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.929593 | 40.8996 | ETL.5420 | 40677517 | Damper-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
115759210 | T2 EI DRUM-RIO OSO #1 020/157 RPL HRDT | 43685808 | DRUM-RIO OSO #1 | 020/157 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.081707 | 39.1116 | ETL.1420 | 40805287 | Hardware-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes
115759960 | T2 EI STANSLUS-MLNS-MNTC#1 3/19 INST MRK | 43712830 | STANISLAUS-MELONES SS-MANTECA #1+ | 003/019 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  | TLN/TLQ error |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.420247 | 38.1209 | ETL.3830 | 40872686 | Marker (i.e. signs)-Steel | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - Prog Multi
115760351 | T2 EI ROUND MTN-CO #2 28/246 RPR INSS | 43947334 | ROUND MTN-COTTONWOOD #2 | 028/246 | ICS | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.095257 | 40.6302 | ETL.5640 | 40816301 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
115760352 | T2 EI CARIBOU-PALERMO :003/028 BIRD CAGI | 43659205 | CARIBOU-PALERMO | :003/028 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.201281 | 40.0609 | ETL.3190 | 40910272 | Conductor-Steel | No Good/Out of Stdrd | Repair | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain
115760355 | T2 EI CARIBOU-PALERMO :3/28 LACING BENT | 44062862 | CARIBOU-PALERMO | :003/028 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.201281 | 40.0609 | ETL.3190 | 40910272 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
115760392 | T2 EI CORTINA-MENDO #1 14/067 CANCEL | 44306522 | CORTINA-MENDOCINO #1 | 014/067 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  | CANCEL/CNCL | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.451374 | 39.0308 | ETL.1330 | 40808518 | Hardware-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville
115760452 | T2 EI BRIDGEVILLE-CTNWD 019/178 FOND | 43706644 | BRIDGEVILLE-COTTONWOOD | 019/178 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.634902 | 40.3783 | ETL.1110 | 40759346 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
115760927 | T2 EI CARIBOU-PALERMO :20/169 HANGER | 44304495 | CARIBOU-PALERMO | :020/169 | ICS | E | Pre-2020_(2) High fire spread TD |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.362505 | 39.8917 | ETL.3190 | 40863107 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
115760954 | T2 EI CARIBOU-PALERMO :20/169 RESAG CONS | 44304495 | CARIBOU-PALERMO | :020/169 | ICS | E | Pre-2020_(2) High fire spread TD |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.362505 | 39.8917 | ETL.3190 | 40863107 | Conductor-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain
115760958 | T2 EI HUMBOLDT-TRINITY 86/6 (L) RPL STRW | 31497850 | HUMBOLDT-TRINITY | 086/006 | 70Y | E | Pre-2020_(2) High fire spread TD |  |  |  | TR2 | LATE | North Coast | WSIP |  |  |  |  | Project | 2021 HUMBOLDT-TRINITY | '-123.626189 | 40.7198 | ETL.1820 | 44560566 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2019-03-30
115760960 | T2 EI CARIBOU-PALERMO :20/169 RPR JUMP | 44304495 | CARIBOU-PALERMO | :020/169 | ICS | E | Pre-2020_(2) High fire spread TD |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.362505 | 39.8917 | ETL.3190 | 40863107 | Jumper-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
115760968 | T2 EI CARIBOU-PALERMO :018/154 INST MRKS | 44302715 | CARIBOU-PALERMO | :018/154 | ICS | F | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.335942 | 39.9091 | ETL.3190 | 40753358 | Marker (i.e. signs)-Steel | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain
115760981 | T2 EI HUMBOLDT-TRINITY 86/6 (R) RPL STRW | 31497850 | HUMBOLDT-TRINITY | 086/006 | 70Y | E | Pre-2020_(2) High fire spread TD |  |  |  | TR2 | LATE | North Coast | WSIP |  |  |  |  | Project | 2021 HUMBOLDT-TRINITY | '-123.626189 | 40.7198 | ETL.1820 | 44560567 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2019-03-30
115760989 | T2 EI CARIBOU-PALERMO :018/154 RPR JUMS | 44304495 | CARIBOU-PALERMO | :018/154 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.335942 | 39.9091 | ETL.3190 | 40753358 | Jumper-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain
115760991 | T2 CARIBOU-PALERMO :23/196 RPL HRDT | 44304495 | CARIBOU-PALERMO | :023/196 | ICS | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.399908 | 39.853 | ETL.3190 | 40828384 | Hardware-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain
115761006 | T2 EI CARIBOU-PALERMO :018/154 RPR STRT | 44304495 | CARIBOU-PALERMO | :018/154 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.335942 | 39.9091 | ETL.3190 | 40753358 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain
115761013 | T2 EI CARIBOU-PALERMO :18/157 REPAINT | 44302715 | CARIBOU-PALERMO | :018/157 | ICS | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.345372 | 39.9086 | ETL.3190 | 40810968 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain
115761027 | T2 EI CARIBOU-PALERMO :17/139 RPR STUBS | 44069583 | CARIBOU-PALERMO | :017/139 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.318496 | 39.9218 | ETL.3190 | 40738353 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115761040 | T3 EI EGL-RCK CORTINA 17/083 RPL INSS | 31432492 | EAGLE ROCK-CORTINA | 017/083 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.5057491 | 39.0088 | ETL.1470 | 40676658 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 532 | Lakeville
115761049 | T2 EI CARIBOU-PALERMO :20/168 INST HRDT | 44069454 | CARIBOU-PALERMO | :020/168 | ICQ | E | Pre-2020_(3) On high spread structure |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.361944 | 39.8926 | ETL.3190 | 40858943 | Hardware-Tower | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
115761053 | T2 EI CARIBOU-PALERMO :023/193 RPR CRST | 44069454 | CARIBOU-PALERMO | :023/193 | ICQ | E | Pre-2020_(2) High fire spread TD |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.395764 | 39.8578 | ETL.3190 | 40668938 | Crossarm-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
115761065 | T2 EI CARIBOU-PALERMO :023/193 RPR INST |  | CARIBOU-PALERMO | :023/193 | 93K | E | Pre-2020_(2) High fire spread TD |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.395764 | 39.8578 | ETL.3190 | 40668938 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  | Yes
115761078 | T2 EI STNSLS-MLNS SS-MNTC #1 5/32 BLT MI | 43712830 | STANISLAUS-MELONES SS-MANTECA #1+ | 005/032 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.453437 | 38.1026 | ETL.3830 | 40642821 | Hardware-Steel | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Victor |  | Y - Prog Multi
115761084 | T2 EI STNSLS-MS-MNTC #1 :6/35 RPR FOND | 43712827 | STANISLAUS-MELONES SS-MANTECA #1+ | :006/035 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.624725 | 37.9743 | ETL.3830 | 40744455 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - Prog Multi
115761102 | T2 EI DRUM-HIGGINS 021/174 RPR STRT | 43687117 | DRUM-HIGGINS | 021/174 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.089435 | 39.1084 | ETL.4393 | 40913070 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento |  |  | Yes
115761110 | T2 EI VACA-SUISUN-JAMESON 8/66 RPL INSS | 31499779 | VACA-SUISUN-JAMESON | 008/066 | 93K | E | Pre-2020_(2) High fire spread TD |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Clearance Denied by GCC | 2021 | '-122.037278 | 38.3318 | ETL.4080 | 44266984 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Sacramento |  |  | Yes
115761152 | T2 EI RND MTN-CTNWD #3 40/344 RPR SPLS | 43755803 | ROUND MTN-COTTONWOOD #3 | 040/344 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.074882 | 40.6285 | ETL.5650 | 40764770 | Splice-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
115761155 | T2 EI RND MTN-CTNWD #2 22/205 INSTL MRKS | 43877040 | ROUND MTN-COTTONWOOD #2 | 022/205 | ICS | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.041266 | 40.7007 | ETL.5640 | 40765145 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
115761197 | T2 EI RND MTN-CTNWD #2 22/206 INSTL DAMS | 43877040 | ROUND MTN-COTTONWOOD #2 | 022/206 | ICS | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.042248 | 40.6993 | ETL.5640 | 40816295 | Damper-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
115761211 | T2 EI SBRNT-GRZL-CLRMT #2 7/51 RPR STRT | 44146666 | SOBRANTE-GRIZLY-CLARMNT #2+ | 007/051 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.2282 | 37.8476 | ETL.3750 | 40804878 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 8 | 2019-04-25
115761216 | T2 EI DRUM-HIGGINS 022/175 PNT TWR | 43687142 | DRUM-HIGGINS | 022/175 | ICQ | F | Pre-2020_(9a) Other ignition related |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.093165 | 39.1069 | ETL.4393 | 40913071 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes
115761236 | T2 EI DRUM-HIGGINS 022/176 REPL INSS | 31499112 | DRUM-HIGGINS | 022/176 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.094955 | 39.1062 | ETL.4393 | 40913072 | Insulator-Steel | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Sacramento |  |  | Yes
115761291 | T3 EI RND MTN-CTNWD #3 34/293 INST HRDT | 43755801 | ROUND MTN-COTTONWOOD #3 | 034/293 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-122.011598 | 40.7044 | ETL.5650 | 40656719 | Hardware-Tower | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
115761295 | T2 EI HIGGINS-BELL 32/244 RPL MRKS | 43740275 | HIGGINS-BELL | 032/244 | ICS | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.045848 | 38.9759 | ETL.1412 | 40869245 | Marker (i.e. signs)-Steel | No Good/Out of Stdrd | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes
115761299 | T2 EI HIGGINS-BELL 32/244 RPR INSS | 43740275 | HIGGINS-BELL | 032/244 | ICS | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.045848 | 38.9759 | ETL.1412 | 40869245 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento
115761340 | T2 EI CARIBOU-PALERMO :06/47 BURIED MEMB | 44059014 | CARIBOU-PALERMO | :006/047 | ICQ | E | Pre-2020_(2) High fire spread TD |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.219269 | 40.0274 | ETL.3190 | 40910289 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115761343 | T2 EI CARIBOU-PALERMO :002/020 RPR STRT | 44070463 | CARIBOU-PALERMO | :002/020 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.18454 | 40.065 | ETL.3190 | 40910264 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
115761389 | T2 EI RND MTN-CTTND #3 41/352 RPR SPLCT | 43755803 | ROUND MTN-COTTONWOOD #3 | 041/352 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.084637 | 40.6167 | ETL.5650 | 40675864 | Splice-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain
115761393 | T2 EI DRUM-HIGGINS 022/177 REPL INSS | 31499112 | DRUM-HIGGINS | 022/177 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.097356 | 39.1052 | ETL.4393 | 40913073 | Insulator-Steel | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Sacramento |  |  | Yes
115761427 | T2 EI DRUM-HIGGINS 022/178 PNT TWR | 43687142 | DRUM-HIGGINS | 022/178 | ICQ | F | Pre-2020_(9a) Other ignition related |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.101735 | 39.1035 | ETL.4393 | 40913074 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes
115761507 | T3 EI GEYSERS #13 TAP 00/004 PNT TWR | 43693051 | GEYSERS #13 TAP | 000/004 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  | Likely MAT error - delink to correct | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.73642 | 38.7741 | ETL.4781 | 40750673 | Structure-Steel | Paint/Coating | Other | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Lakeville
115761513 | T2 EI STNSLS-MS-MNTC #1 5/34 RPR STRT | 43712827 | STANISLAUS-MELONES SS-MANTECA #1+ | 005/034 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.460805 | 38.0985 | ETL.3830 | 40764242 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - Prog Multi
115762140 | T2 CARIBOU-PALERMO :20/170 INS HRDT | 44069454 | CARIBOU-PALERMO | :020/170 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.363578 | 39.8908 | ETL.3190 | 40642282 | Hardware-Tower | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
115763532 | T3 EI CARIBOU-PLERMO :030/245 RPR STRT | 43659208 | CARIBOU-PALERMO | :030/245 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.452493 | 39.7774 | ETL.3190 | 40758500 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115763533 | T3 EI CARIBOU-PLERMO :030/245 RPR FOND | 44051417 | CARIBOU-PALERMO | :030/245 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.452493 | 39.7774 | ETL.3190 | 40758500 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115763534 | T3 EI CARIBOU-PLERMO :030/245 INST HRDT | 44051417 | CARIBOU-PALERMO | :030/245 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.452493 | 39.7774 | ETL.3190 | 40758500 | Hardware-Tower | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
115763543 | T2 EI TULACAY-VACA 3/17 RPL INSS | 31453344 | TULACAY-VACA | 003/017 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.1914106 | 38.2652 | ETL.5800 | 40633788 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Sacramento |  |  | Yes
115763570 | T2 EI PIT #7 TAP 1/12C RPR SHLW | 43877044 | PIT #7 TAP | 001/012C | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.971488 | 40.836 | ETL.5442 | 40690231 | Shield Wire / OPGW-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain
115763573 | T2 EI PIT #7 TAP 001/012A RPR GRWW | 43877044 | PIT #7 TAP | 001/012A | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.971536 | 40.836 | ETL.5442 | 41162601 | Ground Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain
115763579 | T2 EI CARIBOU-PALERMO :1/11 RPR STUBS | 44062862 | CARIBOU-PALERMO | :001/011 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.165487 | 40.0733 | ETL.3190 | 40912340 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115763585 | T2 EI CARIBOU-PALERMO :1/011 INS HRDT | 44062862 | CARIBOU-PALERMO | :001/011 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.165487 | 40.0733 | ETL.3190 | 40912340 | Hardware-Tower | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115764020 | T2 EI SBRNT-GRZL-CLRMT #2 7/51 RPR FOND | 44146666 | SOBRANTE-GRIZLY-CLARMNT #2+ | 007/051 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.2282 | 37.8476 | ETL.3750 | 40804878 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 8 | 2019-04-25
115764148 | T2 EI CARIBOU-PALERMO :20/164 BENT MEMB | 44069454 | CARIBOU-PALERMO | :020/164 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.361945 | 39.8992 | ETL.3190 | 40753366 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
115764149 | T2 EI CARIBOU-PALERMO :20/164 RPL HRDS | 44304495 | CARIBOU-PALERMO | :020/164 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.361945 | 39.8992 | ETL.3190 | 40753366 | Hardware-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
115764416 | T2 EI STANISLAUS-MNTCA #2 12/70 RPR STRT | 43712838 | STANISLAUS-MANTECA #2 | 012/070 | ICQ | F | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.556368 | 38.0484 | ETL.3820 | 40607307 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - 14
115764562 | T2 EI DRUM-RIO OSO #1 021/166 RPR COND | 43685808 | DRUM-RIO OSO #1 | 021/166 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.107424 | 39.1014 | ETL.1420 | 40805297 | Conductor-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes
115764947 | T2 EI STNSLS-MLNS-MNTCA 007/043 RPR STRT | 43712830 | STANISLAUS-MELONES SS-MANTECA #1+ | 007/043 | ICS | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.481878 | 38.0869 | ETL.3830 | 40642774 | Hardware-Steel | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Victor |  | Y - Prog Multi
115765040 | T2 EI MENDOCINO-UKIAH 037/003 REGRADE | 44306674 | MENDOCINO-UKIAH | 037/003 | ICQ | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.159175 | 39.1564 | ETL.2420 | 40662784 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  | 2019-05-01
115765066 | T2 EI BRVILLE-CTNWD 045/353C RMV DBRS | 43862800 | BRIDGEVILLE-COTTONWOOD | 045/353C | ICW | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-123.108201 | 40.3967 | ETL.1110 | 42603429 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
115765166 | T2 EI STNSLS-MLNS-MNTCA 008/051 RPR STRT | 43712827 | STANISLAUS-MELONES SS-MANTECA #1+ | 008/051 | ICQ | F | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.498942 | 38.0776 | ETL.3830 | 40594247 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - Prog Multi
115765254 | T2 EI PLRM-CLGT C000/004 RPR SHLS | 43724331 | PALERMO-COLGATE | C000/004 | ICS | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.203441 | 39.3281 | ETL.5360 | 40757606 | Shield Wire / OPGW-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes
115765282 | T2 EI ROUND MTN-CO #3 44/377 RPL HRDT | 43755803 | ROUND MTN-COTTONWOOD #3 | 044/377 | ICS | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.109681 | 40.5866 | ETL.5650 | 40819296 | Hardware-Steel | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Table Mountain
115765304 | T2 EI PLRM-CLGT C000/004 RPR COND | 43724331 | PALERMO-COLGATE | C000/004 | ICS | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.203441 | 39.3281 | ETL.5360 | 40757606 | Conductor-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes
115765333 | T2 EI DRM-HGGNS 023/182 WSH INSS | 43687141 | DRUM-HIGGINS | 023/182 | ICD | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.113179 | 39.0989 | ETL.4393 | 40913078 | Insulator | Contaminated | Helicopter Wash | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 626 | Sacramento |  |  | Yes
115765437 | T2 EI RND MTN-CTTNWD #2 23/210 REM VEGT |  | ROUND MTN-COTTONWOOD #2 | 023/210 | HNA | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.049281 | 40.69 | ETL.5640 | 40605362 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Table Mountain |  |  | Yes
115765460 | T2 EI DRUM-RIO OSO #1 22/168 RPR CONS | 43685808 | DRUM-RIO OSO #1 | 022/168 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.113258 | 39.0991 | ETL.1420 | 40871377 | Conductor-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes
115765504 | T2 EI PLRM-CLGTE 014/070 RPR COND | 43727762 | PALERMO-COLGATE | 014/070 | ICS | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.502239 | 39.4438 | ETL.5360 | 40605320 | Conductor-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
115765546 | T2 EI RND MTN-CTTNWD #2 23/210 INS DAMS | 43877040 | ROUND MTN-COTTONWOOD #2 | 023/210 | ICS | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.049281 | 40.69 | ETL.5640 | 40605362 | Damper-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
115765811 | T2 EI SBRNT-GRZLY-CLRMT #1 1/13 RPR STRT | 44146666 | SOBRANTE-GRIZLY-CLARMNT #2+ | 001/013 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.20084 | 37.8936 | ETL.3750 | 40857796 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 8
115765829 | T2 EI PALERMO-COLGATE 015/071 INST MRKS | 43727762 | PALERMO-COLGATE | 015/071 | ICS | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.502196 | 39.4408 | ETL.5360 | 40590999 | Marker (i.e. signs)-Steel | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
115765922 | T2 EI ROUND MTN-CO #3 45/391 RPL INSS | 31431455 | ROUND MTN-COTTONWOOD #3 | 045/391 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.1235853 | 40.5699 | ETL.5650 | 40617514 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  | Yes
115765944 | T2 EI PALERMO-COLGATE 015/071 RMV VEGN | 43727762 | PALERMO-COLGATE | 015/071 | ICS | E | Pre-2020_(5b) On structure in bucket 5 |  |  | Likely veg | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.502196 | 39.4408 | ETL.5360 | 40590999 | Structure-Steel | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Table Mountain
115765988 | EI DELEVAN-VACA #1 017/109 RPL INSS | 31434839 | DELEVAN-VACA #1 | 017/109 | 93K | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-122.0851952 | 38.8969 | ETL.5010 | 40785859 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 532 | Sacramento |  |  | Yes
115766217 | T2 EI CARIBOU-PALERMO :1/13 INS HRDT | 44070463 | CARIBOU-PALERMO | :001/013 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.167509 | 40.072 | ETL.3190 | 40910258 | Hardware-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain
115766445 | T2 EI RND MTN-CTTNWD #3 40/342 RPL SPLS | 43755803 | ROUND MTN-COTTONWOOD #3 | 040/342 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.069865 | 40.6345 | ETL.5650 | 40675860 | Splice-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
115766450 | T2 EI PALERMO-COLGATE 015/071 RPL INSS | 31438849 | PALERMO-COLGATE | 015/071 | 93K | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.5022092 | 39.4408 | ETL.5360 | 40616516 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain
115766497 | T2 EI DRUM-HIGGINS 023/180 PNT TWR | 43687142 | DRUM-HIGGINS | 023/180 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.107618 | 39.1012 | ETL.4393 | 40913076 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes
115766646 | T2 EI DRM-HGGNS 027/209 RPR INSS | 31499112 | DRUM-HIGGINS | 027/209 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.090998 | 39.0454 | ETL.4393 | 40760630 | Insulator-Steel | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Sacramento |  |  | Yes
115766680 | T2 EI DRM-HGGNS 027/209 PNT TWR | 43687142 | DRUM-HIGGINS | 027/209 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.090998 | 39.0454 | ETL.4393 | 40760630 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes
115766850 | T2 EI DRUM-HIGGINS 023/182 RPL SPLS | 43687142 | DRUM-HIGGINS | 023/182 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.113179 | 39.0989 | ETL.4393 | 40913078 | Splice-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes
115766855 | T2 EI DRM-HGGNS 027/208 REPL SPLS | 43687142 | DRUM-HIGGINS | 027/208 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.092139 | 39.0472 | ETL.4393 | 40658224 | Splice-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes
115766935 | T2 DI CARIBOU-PALERMO :003/025 RPR STRT | 44062862 | CARIBOU-PALERMO | :003/025 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.19718 | 40.0635 | ETL.3190 | 40910269 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115767492 | T2NT EI BRVILLE-CTNWD 045/353A INS GMKS | 43742049 | BRIDGEVILLE-COTTONWOOD | 045/353A | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-123.108232 | 40.3966 | ETL.1110 | 40676657 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
115767493 | T2 EI BRVILLE-CTNWD 045/353A RPL DMPS | 43742049 | BRIDGEVILLE-COTTONWOOD | 045/353A | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-123.108232 | 40.3966 | ETL.1110 | 40676657 | Damper-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
115767759 | T2 EI CARIBOU-PALERMO :0/8 INS HRDT | 44304495 | CARIBOU-PALERMO | :000/008 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.16204 | 40.0769 | ETL.3190 | 40910255 | Hardware-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain
115767926 | T2 EI STANISLAUS-MNTCA #2 13/77 RPR STRT | 43712838 | STANISLAUS-MANTECA #2 | 013/077 | ICQ | F | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.574547 | 38.0372 | ETL.3820 | 40809198 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - 14
115768103 | T2 EI CBRN-PNCHE 34/148 RPR SPLS | 43749767 | COBURN-PANOCHE | 034/148 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-121.189501 | 36.6915 | ETL.4460 | 40873622 | Shield Wire / OPGW-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Moss Landing |  | Y - 6
115768278 | T2 EI PALERMO-COL C001/007 RPR OPGW | 43724331 | PALERMO-COLGATE | C001/007 | ICS | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.216462 | 39.3219 | ETL.5360 | 40814791 | Shield Wire / OPGW-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes
115768402 | T2 EI DELTA-MTN GATE JCT 11/151 PNT TWR | 43708883 | DELTA-MOUNTAIN GATE JCT | 011/151 | ICS | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-122.317284 | 40.7991 | ETL.6750 | 40660676 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
115768909 | T2 EI STNSLS-MLNS-MNTCA 007/047 RPR STRT | 43727720 | STANISLAUS-MELONES SS-MANTECA #1+ | 007/047 | ICQ | F | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.488883 | 38.083 | ETL.3830 | 40803314 | Structure-Tower | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - Prog Multi
115768973 | T2 EI CBRN-LAS AGUILAS 33/146 RPL INSS | 31509323 | MOSS LANDING-PANOCHE #2 | 033/146 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-121.1964373 | 36.6941 | ETL.5340 | 40848455 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Moss Landing |  | Arcadis
115769081 | T2 EI BRDGVILLE-CTTONWD 050/380 RP DAM | 43862286 | BRIDGEVILLE-COTTONWOOD | 050/380 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-123.199218 | 40.4182 | ETL.1110 | 40676665 | Dampers | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
115770555 | T2 EI CARIBOU-PALERMO :018/151 RPR JUMP | 44304495 | CARIBOU-PALERMO | :018/151 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.331069 | 39.9114 | ETL.3190 | 40642500 | Jumper-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
115770635 | T2 EI CARIBOU-PALERMO :018/151 RPL INSS |  | CARIBOU-PALERMO | :018/151 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.331069 | 39.9114 | ETL.3190 | 40642500 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  | Yes
115770637 | T2 EI CARIBOU-PALERMO :018/151 RPR FOND | 44069454 | CARIBOU-PALERMO | :018/151 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.331069 | 39.9114 | ETL.3190 | 40642500 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115770756 | T2 EI PALERMO-COLGATE 15/073 RPL MRKS | 43727762 | PALERMO-COLGATE | 015/073 | ICS | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.502108 | 39.4348 | ETL.5360 | 40655736 | Marker (i.e. signs)-Steel | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
115770833 | T2 EI DRM-HGGNS 026/203 RPL SPLT | 43687142 | DRUM-HIGGINS | 026/203 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.09986 | 39.0591 | ETL.4393 | 40869575 | Splice-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes
115771016 | T2 EI ROUND MTN-CO #3 46/395 RPR CONS | 43755803 | ROUND MTN-COTTONWOOD #3 | 046/395 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.126958 | 40.5658 | ETL.5650 | 40762510 | Conductor-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
115771119 | EI TULACAY-VACA 0/4 REPL INSS | 31453344 | TULACAY-VACA | 000/004 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | North Valley | WSIP |  |  |  | REJECT: Could not complete work due to a clearance, materials or access issue. |  |  | '-122.2546171 | 38.2498 | ETL.5800 | 40690891 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Sacramento |  |  | Yes
115771185 | T2 EI STNISLS-MNTECA #2 013/078 RPR FOND | 43712838 | STANISLAUS-MANTECA #2 | 013/078 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.576991 | 38.0357 | ETL.3820 | 40856498 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - Prog Multi
115771187 | T2 EI STNISLS-MNTCA #2 013/078 RPR STRT | 43712838 | STANISLAUS-MANTECA #2 | 013/078 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.576991 | 38.0357 | ETL.3820 | 40856498 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - Prog Multi
115771188 | T2 EI STNISS-MNTEC #2 019/113 RPR FOND | 43712838 | STANISLAUS-MANTECA #2 | 019/113 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.655182 | 37.9774 | ETL.3820 | 40651748 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - Prog Multi
115771230 | T3 EI GEYSERS #16 TAP 01/005 PNT TWR | 43693047 | GEYSERS #16 TAP | 001/005 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  | Likely MAT error - delink to correct | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.721515 | 38.7614 | ETL.4760 | 40761823 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Lakeville |  |  | 2019-07-19
115771610 | T2 EI STNSLS-MNTC #2 015/087 INS MRKT |  | STANISLAUS-MANTECA #2 | 015/087 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.595814 | 38.0239 | ETL.3820 | 40803363 | Marker (i.e. signs)-Steel | Missing | Install |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 628 | Victor |  | Y - Prog Multi
115771625 | T2 EI DRUM-RIO OSO #1 024/179 RPL INSS | 31426654 | DRUM-RIO OSO #1 | 024/179 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.1456915 | 39.0861 | ETL.1420 | 40888194 | Insulator-Steel | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Contract | Capital | 532 | Sacramento |  |  | Yes
115771653 | T2 EI STANISLS-MNTC #2 019/111 RPR FOND | 43712838 | STANISLAUS-MANTECA #2 | 019/111 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.651388 | 37.9802 | ETL.3820 | 40579603 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - Prog Multi
115771658 | T2 EI STNSLS-MNTC #2 13/079 RPR STRT | 43712838 | STANISLAUS-MANTECA #2 | 013/079 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.579216 | 38.0344 | ETL.3820 | 40856501 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - Prog Multi
115771710 | T2 EI STNSLS-MNTC #2 13/079 RPR FOND | 43712838 | STANISLAUS-MANTECA #2 | 013/079 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.579216 | 38.0344 | ETL.3820 | 40856501 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - Prog Multi
115771767 | T2 EI CARIBOU-PALERMO :21/176 RPR STUBS | 44069454 | CARIBOU-PALERMO | :021/176 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.371524 | 39.8851 | ETL.3190 | 40811626 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115771803 | T2 EI CARIBOU-PALERMO :21/175 BENT MEMB | 44069454 | CARIBOU-PALERMO | :021/175 | ICQ | E | Pre-2020_(2) High fire spread TD |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.370077 | 39.8867 | ETL.3190 | 40738366 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
115771832 | T2 EI CARIBOU-PALERMO :21/176 PAINT STRT | 44302715 | CARIBOU-PALERMO | :021/176 | ICS | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.371524 | 39.8851 | ETL.3190 | 40811626 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain
115771887 | T2 EI ROUND MTN-CO #2 24/217 WASH INSS | 43876310 | ROUND MTN-COTTONWOOD #2 | 024/217 | ICI | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.05913 | 40.6769 | ETL.5640 | 40815315 | Insulator | Contaminated | Helicopter Wash | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 626 | Table Mountain
115771889 | T2 EI ROUND MTN-CO #2 24/217 INST GUANO | 43877040 | ROUND MTN-COTTONWOOD #2 | 024/217 | ICS | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.05913 | 40.6769 | ETL.5640 | 40815315 | Raptor Guard-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 593 | Table Mountain |  |  | Yes
115771929 | EI DELEVAN-VACA #2 167/1258 REPAINT | 44305192 | DELEVAN-VACA #2 | 167/1258 | ICS | F | Pre-2020_(9a) Other ignition related |  |  |  |  | LATE | North Valley | WSIP | FSRP |  |  |  |  | Priority Bucket 9 | '-122.071726 | 38.875 | ETL.4231 | 40868397 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes
115772006 | T2 EI STNSLS-MNTC #2 14/083 RPR STRT | 43712838 | STANISLAUS-MANTECA #2 | 014/083 | ICQ | F | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.590206 | 38.0276 | ETL.3820 | 40651746 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - Prog Multi
115772017 | T2 EI ROUND MTN-CO #3 46/395 RPR INSS | 43755803 | ROUND MTN-COTTONWOOD #3 | 046/395 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.126958 | 40.5658 | ETL.5650 | 40762510 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
115772165 | T2 EI PALERMO-COLG C009/041 RPR COND | 43724331 | PALERMO-COLGATE | C009/041 | ICS | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.356287 | 39.3053 | ETL.5360 | 40581360 | Conductor-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes
115772264 | T2 EI STISLS-MNTC#2 019/112 RPR FOND | 43712838 | STANISLAUS-MANTECA #2 | 019/112 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.653289 | 37.9788 | ETL.3820 | 40658900 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - Prog Multi
115772291 | T2 EI CARIBOU-PALERMO :000/007 RPR SPLS | 44070463 | CARIBOU-PALERMO | :000/007 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.159561 | 40.079 | ETL.3190 | 40910254 | Splice-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain
115772298 | T2 EI DRM-HGGNS 027/207 RPL SPLS | 43687142 | DRUM-HIGGINS | 027/207 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.094618 | 39.051 | ETL.4393 | 40684239 | Splice-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes
115772340 | T2 EI STNL-MLN ST-MNT#1 013/081 RPL STRT | 43712827 | STANISLAUS-MELONES SS-MANTECA #1+ | 013/081 | ICQ | F | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.583283 | 38.032 | ETL.3830 | 40585655 | Structure-Tower | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - Prog Multi
115772403 | T2 EI CARIBOU-PALERMO :000/007 RPR FOND | 44062862 | CARIBOU-PALERMO | :000/007 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.159561 | 40.079 | ETL.3190 | 40910254 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115772416 | T2 EI DRM-HGGNS 027/207 RPL INSS | 31499112 | DRUM-HIGGINS | 027/207 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.094618 | 39.051 | ETL.4393 | 40684239 | Insulator-Steel | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Sacramento |  |  | Yes
115772457 | T2 EI DRM-HGGNS 027/207 PNT TWR | 43687142 | DRUM-HIGGINS | 027/207 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.094618 | 39.051 | ETL.4393 | 40684239 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes
115772473 | T2 EI STNSLS-MNTC #2 13/080 RPR FOND | 43712838 | STANISLAUS-MANTECA #2 | 013/080 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.583198 | 38.0319 | ETL.3820 | 40579640 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - Prog Multi
115772516 | T2 EI VACA-SUISUN-JAMS 009/069 REPL INSS | 31457373 | VACA-SUISUN-JAMESON | 009/069 | 93K | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.0407546 | 38.3259 | ETL.4080 | 40878857 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 532 | Sacramento |  |  | Yes
115772525 | T2 EI CARIBOU-PALERMO :0/6 INS HRDT | 44062862 | CARIBOU-PALERMO | :000/006 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.157122 | 40.0804 | ETL.3190 | 40828375 | Hardware-Tower | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115772584 | T2 EI STNSLS-MNTC #2 015/090 RPL HRDT | 43712838 | STANISLAUS-MANTECA #2 | 015/090 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.602797 | 38.0178 | ETL.3820 | 40587253 | Hardware-Tower | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - Prog Multi
115772642 | T3 DI MDLE FRK-GLD HLL 000/001 REPL STRW | 31421211 | MIDDLE FORK-GOLD HILL | 000/001 | 70Y | E | Pre-2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP |  |  |  |  | Internal Process | 2021 - Micro pile vendor ([REDACTED]) unavailable in 2020 | '-120.597324 | 39.0239 | ETL.5140 | 44552336 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
115772718 | T2 EI ROUND MTN-CO #3 43/368 RPL HRDT | 43755801 | ROUND MTN-COTTONWOOD #3 | 043/368 | ICQ | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.100824 | 40.5973 | ETL.5650 | 40873484 | Hardware-Tower | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
115772913 | T2 EI STANSLAUS-MNTC#2 20/118 RUSTD LADR | 43713081 | STANISLAUS-MANTECA #2 | 020/118 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.665353 | 37.9698 | ETL.3820 | 40856502 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Victor |  | Y - Prog Multi
115773005 | T2 EI STNSLS-MNTC #2 027/159 RPR STRT | 43712838 | STANISLAUS-MANTECA #2 | 027/159 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-120.768306 | 37.9235 | ETL.3820 | 40871571 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - Prog Multi
115773031 | T2 EI STNSLS-MLNS SS-MNTC#1 20/125 LACNG | 43712827 | STANISLAUS-MELONES SS-MANTECA #1+ | 020/125 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.665458 | 37.9699 | ETL.3830 | 40744438 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - Prog Multi
115773036 | T2 EI RND MTN-COTTN #3 043/369 INST HRDT | 43755801 | ROUND MTN-COTTONWOOD #3 | 043/369 | ICQ | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.101727 | 40.5962 | ETL.5650 | 40862343 | Hardware-Tower | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
115773076 | T2 EI VACA-SUISUN-JAMS 009/070 REPL INSS | 31457373 | VACA-SUISUN-JAMESON | 009/070 | 93K | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.0411836 | 38.3252 | ETL.4080 | 40636762 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 532 | Sacramento |  |  | Yes
115773391 | T2 EI DRUM-RIO OSO #1 22/169 RPR CONS | 43685808 | DRUM-RIO OSO #1 | 022/169 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.117202 | 39.0975 | ETL.1420 | 40858169 | Conductor-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes
115773399 | T2 RND MTN-CTNWD #3 043/371 RPR INSS | 43755803 | ROUND MTN-COTTONWOOD #3 | 043/371 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.104095 | 40.5933 | ETL.5650 | 40595049 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
115773510 | T2 EI ROUND MTN-CO #3 43/370 RPR INSS | 43755803 | ROUND MTN-COTTONWOOD #3 | 043/370 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.102794 | 40.5949 | ETL.5650 | 40599924 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
115773558 | T2 EI STNSLS-MLNS SS-MNTC#1 20/124 LACNG | 43712827 | STANISLAUS-MELONES SS-MANTECA #1+ | 020/124 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.663785 | 37.9711 | ETL.3830 | 40649583 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - Prog Multi
115773630 | T2 EI STN-MLNS S-MNTCA#1 26/167 RPL HRDT | 43712827 | STANISLAUS-MELONES SS-MANTECA #1+ | 026/167 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-120.768366 | 37.9236 | ETL.3830 | 40751408 | Hardware-Tower | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - Prog Multi
115773711 | T2 EI RND MTN-CTTON #3 043/372 INST HRDT | 43755801 | ROUND MTN-COTTONWOOD #3 | 043/372 | ICQ | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.105156 | 40.5921 | ETL.5650 | 40675873 | Hardware-Tower | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
115773783 | T2 EI ROUND MTN-CO #3 44/373 RPL SPLS | 43755803 | ROUND MTN-COTTONWOOD #3 | 044/373 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.10593 | 40.5911 | ETL.5650 | 40656727 | Splice-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
115773872 | T2 EI STNSLS-MNTC #2 020/116 RPL HRDT | 43712838 | STANISLAUS-MANTECA #2 | 020/117 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.66385 | 37.9709 | ETL.3820 | 40811286 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - Prog Multi
115773894 | T2 EI STNSLS-MLNS SS-MNTC#1 19/123 MEMBR | 43712827 | STANISLAUS-MELONES SS-MANTECA #1+ | 019/123 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.661438 | 37.9729 | ETL.3830 | 40642845 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - Prog Multi
115774021 | T3 DI CARIBOU-PALERMO :037/301 RPR STRT | 44069801 | CARIBOU-PALERMO | :037/301 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.487314 | 39.6808 | ETL.3190 | 40913196 | Structure-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 543 | Table Mountain |  |  | Yes
115774097 | T2 EI ROUND MTN-CO #3 44/373 RPR INSS | 43755803 | ROUND MTN-COTTONWOOD #3 | 044/373 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.10593 | 40.5911 | ETL.5650 | 40656727 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
115774149 | T2 EI PIT #4 TAP 000/006 HRDT | 43756947 | PIT #4 TAP | 000/006 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Internal Process | Circuit Based Scheduling | '-121.86403 | 40.9852 | ETL.5432 | 40810520 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115774224 | T3 DI CARIBOU-PALERMO :11/86 RPR FOND | 44051417 | CARIBOU-PALERMO | :011/086 | ICQ | E | Pre-2020_(3) On high spread structure |  |  |  | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.278179 | 39.9897 | ETL.3190 | 40910326 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115774226 | T3 DI CARIBOU-PALRMO-:11/086 RPAINT STRT | 44051417 | CARIBOU-PALERMO | :011/086 | ICQ | E | Pre-2020_(3) On high spread structure |  |  |  | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.278179 | 39.9897 | ETL.3190 | 40910326 | Structure-Tower | Paint/Coating | Repaint | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 543 | Table Mountain |  |  | Yes
115774228 | T3 DI CARIBOU-PALERMO-:11/086 RPL INSS | 31468828 | CARIBOU-PALERMO | :011/086 | 93K | E | Pre-2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.278179 | 39.9897 | ETL.3190 | 40910326 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  | Yes
115774412 | T2 EI STN MNTC 9/59 RPR STRT | 43712838 | STANISLAUS-MANTECA #2 | 009/059 | ICQ | F | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.522145 | 38.0649 | ETL.3820 | 40861464 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - Prog Multi
115774492 | T3 DI CARIBOU-PALERMO-:11/086 RPL SPLS | 44070463 | CARIBOU-PALERMO | :011/086 | ICS | E | Pre-2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.278179 | 39.9897 | ETL.3190 | 40910326 | Splice-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
115775477 | T2 EI CARIBOU-PALERMO :18/150 RPR FOND | 44069454 | CARIBOU-PALERMO | :018/150 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.330456 | 39.9121 | ETL.3190 | 40642283 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115775478 | T2 EI CARIBOU-PALERMO :018/153 RPR FOND | 44069597 | CARIBOU-PALERMO | :018/153 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.334702 | 39.9097 | ETL.3190 | 40738358 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115776697 | T2 EI PTR VLY-MNDCN 000/002 RMV NEST | 43720856 | POTTER VALLEY-MENDOCINO | 000/002 | ICS | E | Pre-2020_(9a) Other ignition related |  | DLFL | CIRT needs more background on request | TR2 | LATE | North Coast | WSIP | FSRP | [5 empty] | '-123.128962 | 39.3598 | ETL.7810 | 40698151 | Structure-Steel | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Lakeville
115776740 | T2 EI CARIBOU-PALERMO :15/125 RPR CRSS | 44304495 | CARIBOU-PALERMO | :015/125 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.311915 | 39.9394 | ETL.3190 | 40753327 | Crossarm-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain
115776741 | T2 EI CARIBOU-PALERMO :015/125 RPL SPLS | 44304495 | CARIBOU-PALERMO | :015/125 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.311915 | 39.9394 | ETL.3190 | 40753327 | Splice-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain
115776827 | T2 EI BCK CRK-RCK CRK-CRST 4/41 RPL SPLS | 43742056 | BUCKS CREEK-ROCK CREEK-CRESTA | 004/041 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.3995285 | 39.8542 | ETL.4430 | 40612544 | Splice-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
115777118 | T2 EI CARIBOU-PALRMO :17/142 BURIED MEMB | 44069583 | CARIBOU-PALERMO | :017/142 | ICQ | E | Pre-2020_(2) High fire spread TD |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.321942 | 39.9192 | ETL.3190 | 40738354 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115777524 | T2 EI VACA-LAKEVILLE#1 4/23 INST HV | 43740456 | VACA-LAKEVILLE #1 | 004/023 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.999083 | 38.4069 | ETL.5840 | 40663082 | Marker (i.e. signs)-Steel | No Good/Out of Stdrd | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes
115777543 | T2 EI DRUM-HIGGINS 23/184 RPL SPLS | 43687142 | DRUM-HIGGINS | 023/184 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.120282 | 39.0961 | ETL.4393 | 40913080 | Splice-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes
115777560 | T2 EI DRUM-HIGGINS 023/184 PNT TWR | 43687142 | DRUM-HIGGINS | 023/184 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.120282 | 39.0961 | ETL.4393 | 40913080 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes
115777585 | T2 EI VACA-PARKWAY 4/26 INST HV | 43760157 | VACA-PARKWAY | 004/026 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.998866 | 38.4067 | ETL.5850 | 40814586 | Marker (i.e. signs)-Steel | No Good/Out of Stdrd | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes
115777707 | T2 EI STNSLS-MNTC #2 21/121 BENT STEEL | 43712838 | STANISLAUS-MANTECA #2 | 021/121 | ICQ | F | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.673322 | 37.9639 | ETL.3820 | 40579604 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - Prog Multi
115777709 | T2 EI STNSLS-MLNS SS-MNTC 16/99 CANCEL | 43727720 | STANISLAUS-MELONES SS-MANTECA #1+ | 016/099 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  | CANCEL/CNCL | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.611253 | 38.0105 | ETL.3830 | 40871565 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - Prog Multi
115778018 | T2 EI DRUM-HIGGINS 024/185B RPR INSS | 43687142 | DRUM-HIGGINS | 024/185B | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.121414 | 39.0955 | ETL.4393 | 41184219 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes
115778392 | T2 EI CARIBOU-PALERMO :004/035 RPR STRT | 44059014 | CARIBOU-PALERMO | :004/035 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.214156 | 40.0482 | ETL.3190 | 40910279 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
115778428 | T2 EI CARIBOU-PALERMO :000/001 INST HRDT | 44062862 | CARIBOU-PALERMO | :000/001 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.147281 | 40.0864 | ETL.3190 | 41162785 | Hardware-Tower | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115778485 | T2 EI CARIBOU-PALERMO :000/001 RPL GYWS | 44070463 | CARIBOU-PALERMO | :000/001 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.147281 | 40.0864 | ETL.3190 | 41162785 | Guy Wire-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain
115778517 | T2 EI BRIDGEVILLE-CTNWD 070/503 FOND | 43723480 | BRIDGEVILLE-COTTONWOOD | 070/503 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.504896 | 40.4571 | ETL.1110 | 40598650 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Eureka |  |  | 2019-04-05
115778661 | T2 EI VACA-SUISUN-JAMS 7/055 REPL INSS | 31457373 | VACA-SUISUN-JAMESON | 007/055 | 93K | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.019913 | 38.3539 | ETL.4080 | 40795680 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 532 | Sacramento
115778712 | T2 EI DRUM-HIGGINS 024/185C RPL INSS | 31426789 | DRUM-HIGGINS | 024/185C | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.12161 | 39.0959 | ETL.4393 | 41184218 | Insulator-Steel | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Sacramento |  |  | Yes
115778891 | T2 EI CARIBOU-PALERMO :004/035 RPL INSS | 31425603 | CARIBOU-PALERMO | :004/035 | 93K | F | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.214156 | 40.0482 | ETL.3190 | 40910279 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  | Yes
115778900 | T2N EI PLRM-CLGT 017/083 INS MRKS | 43727762 | PALERMO-COLGATE | 017/083 | ICS | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.501889 | 39.4043 | ETL.5360 | 40660242 | Marker (i.e. signs)-Steel | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
115778904 | T2 EI RND MTN-CTTNWD #3 52/462 RPL INSS | 31431455 | ROUND MTN-COTTONWOOD #3 | 052/462 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.1908373 | 40.4888 | ETL.5650 | 40705901 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  | Yes
115778965 | T2 EI HAT CRK #1-WESTWD 54/1050 REFRAME | 31459855 | HAT CREEK #1-WESTWOOD | 054/1050 | 93E | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-121.000115 | 40.3133 | ETL.7030 | 40815904 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  | Yes
115779092 | T2 EI CARIBOU-PALERMO :012/100 BENT MEMB | 44059014 | CARIBOU-PALERMO | :012/100 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.275001 | 39.9644 | ETL.3190 | 40910339 | Crossarm-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115779094 | T2 EI CARIBOU-PALERMO :12/099 RPR STRT | 44059014 | CARIBOU-PALERMO | :012/099 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.274973 | 39.9652 | ETL.3190 | 40910338 | Crossarm-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
115779097 | T2 EI CARIBOU-PALERMO :012/100 RPL HRDT | 44059014 | CARIBOU-PALERMO | :012/100 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.275001 | 39.9644 | ETL.3190 | 40910339 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115779098 | T2 EI CARIBOU-PALERMO :012/100 RPR INSS | 44304495 | CARIBOU-PALERMO | :012/100 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP |  |  |  | Field Operations |  | '-121.275001 | 39.9644 | ETL.3190 | 40920078 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain
115779101 | T2 EI CARIBOU-PALERMO :13/102 RPR STRT | 44069583 | CARIBOU-PALERMO | :013/102 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.276601 | 39.9638 | ETL.3190 | 40738338 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115779140 | T2 EI DRUM-HIGGINS 024/187 RPL INSS | 31499112 | DRUM-HIGGINS | 024/187 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.121138 | 39.0919 | ETL.4393 | 40668699 | Insulator-Steel | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Sacramento |  |  | Yes
115779171 | T2 EI HAT CRK#1-WSTWD 53/1038 RPR STRW | 43736798 | HAT CREEK #1-WESTWOOD | 053/1038 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.001793 | 40.3208 | ETL.7030 | 40751794 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
115779173 | T2 EI HAT CRK #1-WSTWD 53/1040 RPR GYWW | 43736798 | HAT CREEK #1-WESTWOOD | 053/1040 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.001067 | 40.3193 | ETL.7030 | 40827560 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
115779201 | T2 EI HAT CRK #1-WESTWD 53/1040 RPR STRW | 43736798 | HAT CREEK #1-WESTWOOD | 053/1040 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.001067 | 40.3193 | ETL.7030 | 40827560 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
115779305 | T2 EI HAT CRK #1-WSTWD 053/1041 RPR GYWW | 43736798 | HAT CREEK #1-WESTWOOD | 053/1041 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.000848 | 40.3185 | ETL.7030 | 40825645 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
115779316 | T2 EI HAT CRK #1-WESTWD 53/1039 RPR STRW | 43736798 | HAT CREEK #1-WESTWOOD | 053/1039 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.001493 | 40.32 | ETL.7030 | 40770001 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
115779795 | T2 DI SMARTVILLE TAP 000/000A RPR GYWW | 43910267 | SMARTVILLE TAP | 000/000A | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.302657 | 39.2088 | ETL.6522 | 40576676 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 630 | Sacramento
115779920 | T2 EI PTTR VLLY-MENDCIN 6/2 RPR GYWS | 43720856 | POTTER VALLEY-MENDOCINO | 006/002 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.146195 | 39.2662 | ETL.7810 | 40698142 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Lakeville |  |  | 2019-04-30
115780144 | T2 EI CARIBOU-PALERMO :3/023 RPR STRT | 44062862 | CARIBOU-PALERMO | :003/023 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.192208 | 40.0629 | ETL.3190 | 40910267 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115781622 | T2 EI RND MTN-CTTNWD #3 47/415 RPR SPLS | 43755803 | ROUND MTN-COTTONWOOD #3 | 047/415 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.146685 | 40.5421 | ETL.5650 | 40762512 | Splice-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain
115781769 | T2 EI CARIBOU-PALERMO 10/086 RPR SPLS | 44304495 | CARIBOU-PALERMO | 010/086 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.523581 | 39.5954 | ETL.3190 | 40816572 | Splice-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
115781771 | T2 EI CARIBOU-PALERMO 15/123 RPR FOND | 44069597 | CARIBOU-PALERMO | 015/123 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.501865 | 39.6662 | ETL.3190 | 40913205 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115781772 | T2 EI CARIBOU-PALERMO 15/123 STRS PAINT | 44302715 | CARIBOU-PALERMO | 015/123 | ICS | F | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | <15D | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.501865 | 39.6662 | ETL.3190 | 40913205 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain
115781778 | T2 EI PALERMO-COLG 018/085 INST MRKS | 43727762 | PALERMO-COLGATE | 018/085 | ICS | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.50178 | 39.3981 | ETL.5360 | 40757847 | Marker (i.e. signs)-Steel | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
115781835 | T2 EI DRUM-HIGGINS 024/189 RPL INSS | 31499112 | DRUM-HIGGINS | 024/189 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.11869 | 39.0881 | ETL.4393 | 40765809 | Insulator-Steel | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Sacramento |  |  | Yes
115781895 | T2 EI CARIBOU-PALERMO 10/87 RPR STRT | 44304495 | CARIBOU-PALERMO | 010/087 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.522843 | 39.598 | ETL.3190 | 40819278 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
115781948 | T2 EI CRIBOU-TBLE MTN 007/056 RPR FOND | 43729340 | CARIBOU-TABLE MTN | 007/056 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Internal Process | Circuit Based Scheduling | '-121.149342 | 40.0851 | ETL.4440 | 40815780 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  | Yes
115782106 | T2 EI BRIDGEVILLE-CTNWD 059/431 FOND | 43722519 | BRIDGEVILLE-COTTONWOOD | 059/431 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.349751 | 40.3738 | ETL.1110 | 40657064 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Eureka |  |  | 2019-08-02
115782162 | T2 EI RND MTN-CTNWD #3 054/486 RPR INSS | 43755803 | ROUND MTN-COTTONWOOD #3 | 054/486 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.211829 | 40.4634 | ETL.5650 | 40819089 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain
115782209 | T2 EI CARIBOU-PALERMO :1/16 RPR STRT | 44062862 | CARIBOU-PALERMO | :001/016 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.173733 | 40.0701 | ETL.3190 | 40910260 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115782213 | T2 EI CARIBOU-PALERMO :1/16 RPL HRDT | 44062862 | CARIBOU-PALERMO | :001/016 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.173733 | 40.0701 | ETL.3190 | 40910260 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115782221 | T2 EI CARIBOU-PALERMO :20/172A INST HRDT | 44069455 | CARIBOU-PALERMO | :020/172A | ICQ | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | <15D | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.365436 | 39.8895 | ETL.3190 | 43203008 | Hardware-Tower | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
115782279 | T2 EI CARIBOU-PALERMO :18/149 RPL SPLS | 44304495 | CARIBOU-PALERMO | :018/149 | ICS | E | Pre-2020_(2) High fire spread TD |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.330177 | 39.9125 | ETL.3190 | 40863125 | Splice-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain
115782376 | T2 EI CARIBOU-PALERMO :18/148 RPR STUBS | 44069454 | CARIBOU-PALERMO | :018/148 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.329706 | 39.9131 | ETL.3190 | 44188831 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115782767 | T2 EI TULE-SPRINGVILLE 011/010 RPR STRW | 43690974 | TULE-SPRINGVILLE | 011/010 | ICW | B | Pre-2020_(5) TD tag on other lines | Travel Efficiency |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-118.939557 | 36.1091 | ETL.9040 | 40905728 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE srdy |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Midway |  | Y - 23
115782786 | T2 EI CARIBOU-PALERMO :13/103A RPR CONS | 44304495 | CARIBOU-PALERMO | :013/103A | ICS | E | Pre-2020_(2) High fire spread TD |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.278738 | 39.9631 | ETL.3190 | 41162770 | Conductor-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain
115783354 | T2 EI VACA-SUISUN 012/087 REPL INSS | 31435971 | VACA-SUISUN | 012/087 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.066737 | 38.2839 | ETL.4070 | 40838458 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 532 | Sacramento |  |  | Yes
115783373 | T2 EI CARIBOU-PALRMO :13/103 BURIED STUB | 44069583 | CARIBOU-PALERMO | :013/103 | ICQ | E | Pre-2020_(2) High fire spread TD |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.278836 | 39.963 | ETL.3190 | 40738339 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115783409 | T2 EI CARIBOU-PALERMO :18/147 RPR COND |  | CARIBOU-PALERMO | :018/147 | ICW | E | Pre-2020_(2) High fire spread TD |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.3290391 | 39.9139 | ETL.3190 | 44549940 | Conductor-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
115783671 | T2 EI CARIBOU-PALRMO :18/152 BURIED STUB | 44069454 | CARIBOU-PALERMO | :018/152 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.332107 | 39.9109 | ETL.3190 | 40738834 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115783691 | T2 EI RND MTN-CTTNWD #3 054/489 RPR SPLS | 43755803 | ROUND MTN-COTTONWOOD #3 | 054/489 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.214495 | 40.4601 | ETL.5650 | 40868134 | Splice-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain
115783698 | T2 EI DRUM-HIGGINS 026/199 REPL INSS | 31499112 | DRUM-HIGGINS | 026/199 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.1048066 | 39.0667 | ETL.4393 | 40793900 | Insulator-Steel | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Sacramento |  |  | Yes
115783741 | EI CARIBOU-PALERMO 000/001 HRDT | 44304495 | CARIBOU-PALERMO | 000/001 | ICS | E | Pre-2020_(9a) Other ignition related |  |  |  |  | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.519606 | 39.4545 | ETL.3190 | 40589081 | Hardware-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
115783795 | T2 EI DRUM-RIO OSO #1 023/177 RPR COND | 43685808 | DRUM-RIO OSO #1 | 023/177 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.139728 | 39.0885 | ETL.1420 | 40821610 | Conductor-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes
115783812 | T2 EI RND MTN-CTTNWD #3 052/464 INSS | 31431455 | ROUND MTN-COTTONWOOD #3 | 052/464 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.1927051 | 40.4865 | ETL.5650 | 40789796 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  | Yes
115783825 | T2 EI CRBU-PLRM 001/010 RPR FOND | 44069801 | CARIBOU-PALERMO | 001/010 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.542374 | 39.4642 | ETL.3190 | 40599223 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
115783837 | T2 EI CARIBOU-PALERMO 011/093 RPL SPLS | 44304495 | CARIBOU-PALERMO | 011/093 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.519401 | 39.6101 | ETL.3190 | 40656343 | Splice-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
115783854 | T2 EI DRM-HGGNS 026/200 RPL SPLS | 43687142 | DRUM-HIGGINS | 026/200 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.103517 | 39.0647 | ETL.4393 | 40760333 | Splice-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes
115783867 | T2 TRINITY-MAPLE CREEK 8/013 RELOCATE P | 31433769 | TRINITY-MAPLE CREEK | 008/013 | 70Y | E | Pre-2020_(2) High fire spread TD |  |  |  | TR2 | LATE | North Coast | Non-WSIP |  |  |  |  | Weather | AT RISK - weather impacts | '-123.069141 | 40.7619 | ETL.8170 | 40906374 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Eureka |  |  | 2019-06-03
115783923 | T3 EI EAGLE ROCK-CORTINA :9/53 REPL INSL | 31437310 | EAGLE ROCK-CORTINA | :009/053 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.668401 | 38.888 | ETL.1470 | 40676867 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 532 | Lakeville |  |  | 2019-04-04
115783941 | T2 EI CARIBOU-PALERMO 15/119 RPR FOND | 44069597 | CARIBOU-PALERMO | 015/119 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.506565 | 39.6554 | ETL.3190 | 40913201 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
115783996 | T2 EI RND MTN-CTNWD #3 052/471 RPR CONS | 43755803 | ROUND MTN-COTTONWOOD #3 | 052/471 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.197781 | 40.4803 | ETL.5650 | 40595104 | Conductor-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
115784006 | T2 EI RND MTN-CTTNWD #3 052/466 RPL INSS | 31431455 | ROUND MTN-COTTONWOOD #3 | 052/466 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.1938781 | 40.4851 | ETL.5650 | 40845458 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  | Yes
115784024 | T2 EI DRM-HGGNS 026/200 REPL INSS | 31426789 | DRUM-HIGGINS | 026/200 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.1035305 | 39.0647 | ETL.4393 | 40789827 | Insulator-Steel | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Contract | Capital | 532 | Sacramento |  |  | Yes
115784135 | T2 EI RND MTN-CTNWD#3 059/534 RPL INSS | 31431455 | ROUND MTN-COTTONWOOD #3 | 059/534 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.259875 | 40.4052 | ETL.5650 | 40762838 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  | Yes
115784136 | T2NT EI CRIBU-PLERM 9/83 RPR FOND | 44069597 | CARIBOU-PALERMO | 009/083 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.525035 | 39.5903 | ETL.3190 | 40656341 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
115784217 | T2 EI CARIBOU-PALERMO 14/118 RPR FOND | 44069597 | CARIBOU-PALERMO | 014/118 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.506733 | 39.6548 | ETL.3190 | 40913200 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
115784228 | T2 EI COTTONWOOD #1 :003/028 RPL INSS | 31450547 | COTTONWOOD #1 | 003/028 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.267857 | 40.3411 | ETL.6620 | 40920715 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  | Yes
115784254 | T2 EI CARIBOU-PALERMO 009/082 RPR FOND | 44069597 | CARIBOU-PALERMO | 009/082 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.525145 | 39.5899 | ETL.3190 | 40674920 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
115784561 | T2 EI CARIBOU-PALERMO 009/082 RPR INST | 44304495 | CARIBOU-PALERMO | 009/082 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.525145 | 39.5899 | ETL.3190 | 40674920 | Conductor-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
115784568 | T2 EI CARIBOU-PALERMO 10/091 REPL INSS |  | CARIBOU-PALERMO | 010/091 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.520902 | 39.6048 | ETL.3190 | 40591547 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  | Yes
115784596 | T2 EI CARIBOU-PALERMO 009/082 RPR STRT | 44304495 | CARIBOU-PALERMO | 009/082 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.525145 | 39.5899 | ETL.3190 | 40674920 | Hardware-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
115784600 | T2 EI PIT #1-COTTONWD 54/484 INST COTTER |  | PIT #1-COTTONWOOD | 054/484 | ICS | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.209652 | 40.4657 | ETL.5390 | 40759701 | Insulator-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
115784606 | T2 EI CARIBOU-PALERMO 9/080 REPL INSS |  | CARIBOU-PALERMO | 009/080 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.525656 | 39.5881 | ETL.3190 | 40599263 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  | Yes
115784659 | T2 EI CARIBOU-PALERMO 9/83 RPR INSS | 44304495 | CARIBOU-PALERMO | 009/083 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.525035 | 39.5903 | ETL.3190 | 40656341 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
115784751 | T2 EI CRIBU-PLERM 9/83 RPL HRDT | 43727174 | CARIBOU-PALERMO | 009/083 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.525035 | 39.5903 | ETL.3190 | 40656341 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
115784764 | T2 CARIBOU-PALERMO 12/109 RPR INSS | 44304495 | CARIBOU-PALERMO | 012/109 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.511691 | 39.6373 | ETL.3190 | 40864877 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain
115784775 | T2 EI CARIBOU-PALERMO 10/92 RPR SPLC | 44304495 | CARIBOU-PALERMO | 010/092 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.520289 | 39.607 | ETL.3190 | 40689954 | Splice-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
115784780 | T2 EI CARIBOU-PALERMO 10/92 RPR FOND | 44069597 | CARIBOU-PALERMO | 010/092 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.520289 | 39.607 | ETL.3190 | 40689954 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
115784791 | T2 EI CARIBOU-PALERMO 10/92 RPR STRT | 44069597 | CARIBOU-PALERMO | 010/092 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.520289 | 39.607 | ETL.3190 | 40689954 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
115784797 | T2 EI CARIBOU PALERMO 13/112 REPL SPLS | 43727174 | CARIBOU-PALERMO | 013/112 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.510109 | 39.6429 | ETL.3190 | 40668745 | Splice-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
115784806 | EI POE-RIO OSO 036/242 REPL INSS | 31431911 | POE-RIO OSO | 036/242 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-121.5255773 | 39.4652 | ETL.5540 | 40719834 | Insulator-Steel | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  | Yes
115785011 | T2 EI CARIBOU-PALERMO 14/118 RPL HRDT |  | CARIBOU-PALERMO | 014/118 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.506733 | 39.6548 | ETL.3190 | 40913200 | Hardware-Tower | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
115785013 | T2 EI CARIBO-PALRMO 13/113 REPL SPLICE | 44304495 | CARIBOU-PALERMO | 013/113 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.509591 | 39.6447 | ETL.3190 | 40656347 | Splice-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
115785018 | T2 EI CARIBOU-PALERMO 1/8 INS HRDT | 44069801 | CARIBOU-PALERMO | 001/008 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.536625 | 39.4611 | ETL.3190 | 40867924 | Hardware-Tower | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
115785042 | T2 EI POE-RIO OSO 037/245 REPL DAMS | 43737421 | POE-RIO OSO | 037/245 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.52412 | 39.458 | ETL.5540 | 40762421 | Damper-Steel | No Good/Out of Stdrd | Replace | DOCC srdy | DOCC | Job has been constructed (documentation) | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
115785045 | T2 EI PIT #1-CTTNWD 55/495 RPR STRT | 43755354 | PIT #1-COTTONWOOD | 055/495 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.22057 | 40.4525 | ETL.5390 | 40759493 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115785204 | T2 EI PALERMO-WYANDOTTE 1/008 REPL DAMS | 43754988 | PALERMO-WYANDOTTE | 000/008 | ICQ | E | Pre-2020_(5) TD tag on other lines |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.536394 | 39.4612 | ETL.4315 | 40867155 | Damper-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
115785282 | T2 EI CRESTA-RIO OSO 30/243 RMV NEST | 43708739 | CRESTA-RIO OSO | 030/243 | ICS | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.535087 | 39.5443 | ETL.4590 | 41083103 | Structure-Steel | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain
115785333 | T2 EI PALERMO-NICOLAUS 1/008 RPL INSS |  | PALERMO-NICOLAUS | 001/008 | 93K | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.536759 | 39.461 | ETL.3210 | 40870592 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  | Yes
115785519 | T2 EI CARIBOU-PALERMO 8/72 RPR SPLC | 44304495 | CARIBOU-PALERMO | 008/072 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.529027 | 39.5771 | ETL.3190 | 40689950 | Splice-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
115785631 | T2 EI PALERMO-WYANDOTTE 0/004 RPR INSS |  | PALERMO-WYANDOTTE | 000/004 | ICS | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Internal Process |  | '-121.525448 | 39.4555 | ETL.4315 | 40750691 | Insulator-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
115785646 | EI PALERMO-WYANDOTTE 0/7 INST HRDT | 43754988 | PALERMO-WYANDOTTE | 000/007 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  |  | LATE | North Valley | WSIP | [5 empty] | Priority Bucket 9 | '-121.533336 | 39.4596 | ETL.4315 | 40819206 | Hardware-Tower | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
115785852 | T2 EI CARIBOU-PALERMO 8/071 INST HRDT | 44304495 | CARIBOU-PALERMO | 008/071 | ICS | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.52966 | 39.575 | ETL.3190 | 40595038 | Hardware-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
115785931 | T3 EI ROUND MTN-COTTONWD #3 033/287 HRDT | 43755803 | ROUND MTN-COTTONWOOD #3 | 033/287 | ICS | E | Pre-2020_(9a) Other ignition related |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-122.004973 | 40.7123 | ETL.5650 | 40810666 | Hardware-Steel | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Table Mountain |  |  | Yes
115786156 | T2 EI TULE-SPRINGVILLE 24/006 RPL SPLW | 43708992 | TULE-SPRINGVILLE | 024/006 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-118.748093 | 36.1519 | ETL.9040 | 40823415 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Midway |  | Y - 23 | USFS
115786208 | T2 EI TULE-SPRINGVILLE 24/006 RPR GYWW | 43708346 | TULE-SPRINGVILLE | 024/006 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-118.748093 | 36.1519 | ETL.9040 | 40823415 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Midway |  | Y - 23 | USFS
115786245 | T2 EI TULE-SPRINGVILLE 17/005 RPL SPLW | 43708992 | TULE-SPRINGVILLE | 017/005 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-118.841934 | 36.1076 | ETL.9040 | 40765668 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Midway |  | Y - 23
115786276 | T2 DI CARIBOU-PALERMO :002/019 RPR STRS | 44070463 | CARIBOU-PALERMO | :002/019 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.182939 | 40.0665 | ETL.3190 | 40910263 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain
115786277 | T2 DI CARIBOU-PALERMO :002/019 RPR FOND | 44062862 | CARIBOU-PALERMO | :002/019 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.182939 | 40.0665 | ETL.3190 | 40910263 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115786517 | T2 DI CARIBOU-PALERMO :13/108 RPR STRT | 44069583 | CARIBOU-PALERMO | :013/108 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.286412 | 39.9586 | ETL.3190 | 40858895 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115786518 | T2 DI CARIBOU-PALERMO :13/108 RPL INSS |  | CARIBOU-PALERMO | :013/108 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP |  |  |  | Field Operations |  | '-121.286412 | 39.9586 | ETL.3190 | 40739402 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain
115786600 | T2 DI CARIBOU-PALERMO :14/110A RPR FOND | 44069583 | CARIBOU-PALERMO | :014/110A | ICQ | E | Pre-2020_(3) On high spread structure |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.29189 | 39.9578 | ETL.3190 | 41162771 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115786601 | T2 DI CARIBOU-PALERMO :14/110A RPR SPLS | 44304495 | CARIBOU-PALERMO | :014/110A | ICS | E | Pre-2020_(2) High fire spread TD |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.29189 | 39.9578 | ETL.3190 | 41162771 | Splice-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain
115786705 | T2 EI CARIBOU-PALERMO :14/112 BURID MEMB | 44069583 | CARIBOU-PALERMO | :014/112 | ICQ | E | Pre-2020_(2) High fire spread TD |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.295392 | 39.956 | ETL.3190 | 40738828 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115786868 | T2 EI TL-SPRGVL 026/011 RPR CNDS | 43709292 | TULE-SPRINGVILLE | 026/011 | ICS | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-118.710904 | 36.162 | ETL.9040 | 43604138 | Conductor-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Midway |  | Y - 23
115786878 | T2 EI TULE-SPRINGVILLE 24/005 RPL SPLW | 43708992 | TULE-SPRINGVILLE | 024/005 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-118.750358 | 36.1508 | ETL.9040 | 40765682 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Midway |  | Y - 23 | USFS
115786895 | T2NT EI TL-SPRGVL 026/011 INS GMRK |  | TULE-SPRINGVILLE | 026/011 | ICW | F | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-118.710904 | 36.162 | ETL.9040 | 43604138 | Guy Wire Mark /Indic-Wood | Missing | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Midway |  | Y - 23
115787027 | T2 EI CARIBOU-PALERMO 8/72 RPR STRT | 44069597 | CARIBOU-PALERMO | 008/072 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.529027 | 39.5771 | ETL.3190 | 40689950 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
115787278 | DISTRIBUTION MARKER |  | SAN LUIS OBISPO-SANTA MARIA (IDLE) | 007/136 | ICW | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-120.553222 | 35.1847 | ETL.9100 | 42574213 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - 4
115787400 | T2 EI PIT #4 TAP 000/006 RPR STRT | 43756947 | PIT #4 TAP | 000/006 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.86403 | 40.9852 | ETL.5432 | 40810520 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115787514 | T2 EI ROUND MTN-CTNWD#3 58/529 INST HV | 43755803 | ROUND MTN-COTTONWOOD #3 | 058/529 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.254417 | 40.4118 | ETL.5650 | 40868138 | Marker (i.e. signs)-Steel | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
115787592 | T2 EI ROUND MTN-CTNWD#3 58/529 REPL INSS | 31431455 | ROUND MTN-COTTONWOOD #3 | 058/529 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.254431 | 40.4118 | ETL.5650 | 40891152 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain
115787642 | T2 EI VACA-PARKWAY 005/031 RPL HRDT | 43760159 | VACA-PARKWAY | 005/031 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP |  |  |  |  | Priority Bucket 9 | '-122.010778 | 38.3978 | ETL.5850 | 40589768 | Hardware-Tower | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento |  |  | Yes
115787805 | T2 EI TULACAY-VACA 5/29 RPL INSS | 31453344 | TULACAY-VACA | 005/029 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.0128086 | 38.3963 | ETL.5800 | 40890665 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 532 | Sacramento |  |  | Yes
115787892 | DISTRIBUTION RPR STRW |  | SAN LUIS OBISPO-SANTA MARIA (IDLE) | 009/166 | ICW | E | Pre-2020_(1b) Lines with special commitments |  |  |  |  | LATE | South | WSIP | FSRP | [5 empty] | '-120.525517 | 35.1673 | ETL.9100 | 42574216 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach
115788129 | T2 EI RUND MTN-CTTNWD#3 58/532 REPL INSS | 31431455 | ROUND MTN-COTTONWOOD #3 | 058/532 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.2574953 | 40.4081 | ETL.5650 | 40722092 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  | Yes
115788141 | T2 EI DRUM-HIGGINS 025/196 RPL INSS | 31499112 | DRUM-HIGGINS | 025/196 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.108772 | 39.0728 | ETL.4393 | 40592845 | Insulator-Steel | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Sacramento |  |  | Yes
115788211 | T2 EI RUND MTN-CTTNWD#3 58/532 RPR STRT | 43755801 | ROUND MTN-COTTONWOOD #3 | 058/532 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Internal Process | Circuit Based Scheduling | '-122.257482 | 40.4081 | ETL.5650 | 40677349 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
115788303 | T2 EI DRUM-HIGGINS 025/197 RPL INSS | 31499112 | DRUM-HIGGINS | 025/197 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.107493 | 39.0709 | ETL.4393 | 40690102 | Insulator-Steel | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Sacramento |  |  | Yes
115788343 | T2 EI RUND MTN-CTTNWD#3 59/533 REPL INSS | 31431455 | ROUND MTN-COTTONWOOD #3 | 059/533 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.2584617 | 40.4069 | ETL.5650 | 40687107 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  | Yes
115788368 | T2 EI VACA-PARKWAY 005/032 INS HRDT | 43760157 | VACA-PARKWAY | 005/032 | ICS | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.012418 | 38.3961 | ETL.5850 | 40670590 | Hardware-Steel | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Sacramento |  |  | Yes
115789930 | T2 EI TDWTR-SBRNTE 021/102 RPR FOND |  | TIDEWATER-SOBRANTE | 021/102 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.199442 | 37.9246 | ETL.5770 | 40661712 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 2 | EBMUD
115799835 | T2 EI VALLEY SPRINGS #1 A000/009 RPL PL | 31427931 | VALLEY SPRINGS #1 | A000/009 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.759075 | 38.2117 | ETL.8210 | 40907071 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Not Released | CalTrans
115805225 | T2NT EI PALERMO-COLGATE 017/084 INS MRKS | 43727762 | PALERMO-COLGATE | 017/084 | ICS | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.501832 | 39.401 | ETL.5360 | 40757913 | Marker (i.e. signs)-Steel | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
115817702 | T2 EI DRUM-HIGGINS 025/192 RPL INSS | 31499112 | DRUM-HIGGINS | 025/192 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.114983 | 39.0824 | ETL.4393 | 40817267 | Insulator-Steel | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Sacramento |  |  | Yes
115817713 | T2 EI DRUM-HIGGINS 025/192 PNT TWR | 43687117 | DRUM-HIGGINS | 025/192 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.114983 | 39.0824 | ETL.4393 | 40817267 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes
115817807 | T2 EI CNTRVLL-TBL MTN 5/89 RPL SPLW | 43724228 | CENTERVILLE-TABLE MTN | 005/089 | ICS | E | Pre-2020_(5) TD tag on other lines |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.706768 | 39.7159 | ETL.6320 | 43702495 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
115817927 | EI ELECTRA-BELLOTA 19/137 CANCEL | 43727727 | ELECTRA-BELLOTA | 019/137 | ICQ | E | Pre-2020_(5) TD tag on other lines |  |  | CANCEL/CNCL |  | LATE | Central | WSIP | FSRP | [5 empty] | '-120.898999 | 38.1147 | ETL.4670 | 40658990 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - Prog Multi
115817955 | T2 EI DRUM-HIGGINS 024/191 RPL INSS | 31499112 | DRUM-HIGGINS | 024/191 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.116017 | 39.084 | ETL.4393 | 40818401 | Insulator-Steel | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Sacramento |  |  | Yes
115817990 | T2 EI TBL MTN-PLRMO 014/065 RPL INSS | 31452983 | TABLE MTN-PALERMO | 014/065 | 93K | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.5025727 | 39.4566 | ETL.5690 | 40787140 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  | Yes
115818074 | EI MOSS LNDNG-CBRN C027/105 RPR STRT | 43766044 | MOSS LANDING-COBURN | C027/105 | ICS | E | Pre-2020_(9a) Other ignition related | Budget Owner (Paint) |  |  |  | LATE | South | WSIP | [6 empty] | '-121.233921 | 36.39 | ETL.5330 | 40762040 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Moss Landing |  | Y - 7
115818208 | T2 DI SMRTVLE-NCOLUS #2 0/002 WASH INSS | 43852598 | SMARTVILLE-NICOLAUS #2 | 000/002 | ICD | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.303527 | 39.2084 | ETL.8000 | 44177570 | Insulator | Contaminated | Ground Wash | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 622 | Sacramento
115818515 | T3 DI CARIBOU-PALERMO :037/299 RPL INSS | 31426499 | CARIBOU-PALERMO | :037/299 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.486332 | 39.6826 | ETL.3190 | 40913194 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  | Yes
115818519 | T3 DI CARIBOU-PALERMO :037/299 RPR STRT | 44051417 | CARIBOU-PALERMO | :037/299 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.486332 | 39.6826 | ETL.3190 | 40913194 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
115818629 | T2 DI CARIBOU-PALERMO :0/6 RPR STUBS | 44062862 | CARIBOU-PALERMO | :000/006 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.157122 | 40.0804 | ETL.3190 | 40828375 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115818669 | T3 DI CARIBOU-PALERMO :011/089 RPL SPLS | 43735847 | CARIBOU-PALERMO | :011/089 | ICS | E | Pre-2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.279035 | 39.9862 | ETL.3190 | 40910329 | Splice-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
115818810 | T3 DI CARIBOU-PALERMO :011/089 RPR FOND | 44051417 | CARIBOU-PALERMO | :011/089 | ICQ | E | Pre-2020_(3) On high spread structure |  |  |  | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.279035 | 39.9862 | ETL.3190 | 40910329 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115818837 | T2 EI TIDEWATER-SBRNTE 21/101 RPR STRT |  | TIDEWATER-SOBRANTE | 021/101 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.19826 | 37.9263 | ETL.5770 | 40586685 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 2 | EBMUD
115818873 | DISTRIBUTION INSL | 43715793 | SPARE T-LINE RECORD | T098 | ICS | E | Pre-2020_(2) High fire spread TD |  |  | Midway-Santa Maria | TR3 | LATE | South | WSIP | [6 empty] | '-120.172272 | 35.0597 | ETL.9240 | 43249717 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Pismo Beach
115819082 | T3 DI CARIBOU-PALMERO 16/127 RPR FOND | 44051417 | CARIBOU-PALERMO | 016/127 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.495461 | 39.6739 | ETL.3190 | 41162781 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115819359 | T2 EI POE-RIO OSO 31/204 RPR JUMS | 43737420 | POE-RIO OSO | 031/204 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.535652 | 39.5479 | ETL.5540 | 40762687 | Jumper-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
115819539 | T2 DI CARIBOU-PALERMO :24/199 RPR FOND | 44069454 | CARIBOU-PALERMO | :024/199 | ICQ | E | Pre-2020_(3) On high spread structure |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.402334 | 39.8505 | ETL.3190 | 40867369 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115819628 | T2 EI POE-RIO OSO 23/151 REPAINT | 43737420 | POE-RIO OSO | 023/151 | ICS | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.506199 | 39.6588 | ETL.5540 | 40590429 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
115820006 | EI VACA-PARKWAY 7/041 INSTL MRKS | 43760157 | VACA-PARKWAY | 007/041 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-122.030442 | 38.3744 | ETL.5850 | 40589769 | Marker (i.e. signs)-Steel | No Good/Out of Stdrd | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes
115820077 | T2 CARIBOU-PALERMO 12/107 RPR SPLS | 44304495 | CARIBOU-PALERMO | 012/107 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.511898 | 39.6366 | ETL.3190 | 40815581 | Splice-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
115820100 | T2 EI DRUM-HIGGINS 024/188 RPL INSS | 31499112 | DRUM-HIGGINS | 024/188 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.119279 | 39.089 | ETL.4393 | 40658220 | Insulator-Steel | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Sacramento |  |  | Yes
115820161 | T2 EICOTTONWOOD #1 006/047 CANCEL | 43760649 | COTTONWOOD #1 | 006/047 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  | CANCEL/CNCL | TR2 | LATE | North Valley | WSIP | [5 empty] | Priority Bucket 9 | '-122.267638 | 40.2988 | ETL.6620 | 40910988 | Hardware-Tower | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
115820269 | T2 EI PALERMO-COLGATE C005/026 RPR CONS | 43724331 | PALERMO-COLGATE | C005/026 | ICS | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.286576 | 39.3076 | ETL.5360 | 40815685 | Conductor-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento
115820312 | T2 DI CARIBOU-PALERMO :001/12 RPR FOND | 44062862 | CARIBOU-PALERMO | :001/012 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.166469 | 40.0723 | ETL.3190 | 40912339 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115820329 | T2 EI ELECTRA-BELLOTA 15/110 RPR FOND | 43727727 | ELECTRA-BELLOTA | 015/110 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.848636 | 38.1635 | ETL.4670 | 40819238 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - Prog Multi
115820513 | EI VACA-PARKWAY 7/042 INSTL MRKS | 43760157 | VACA-PARKWAY | 007/042 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-122.031888 | 38.3719 | ETL.5850 | 40670594 | Marker (i.e. signs)-Steel | No Good/Out of Stdrd | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes
115820565 | T2 EI PIT#1-CTNWD 045/394 RPR FOND | 43755354 | PIT #1-COTTONWOOD | 045/394 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Internal Process | Circuit Based Scheduling | '-122.125884 | 40.5668 | ETL.5390 | 41107597 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
115820568 | T2 EI POE-RIO OSO 028/185 RPR INSS |  | POE-RIO OSO | 028/185 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.526702 | 39.5882 | ETL.5540 | 40757647 | Insulator-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
115820640 | T2 EI POE-RIO OSO 039/257 PAINT | 43737421 | POE-RIO OSO | 039/257 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.518365 | 39.4294 | ETL.5540 | 40814853 | Structure-Steel | Paint/Coating | Other | DOCC srdy | DOCC | Job has been constructed (documentation) | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
115820689 | T2 EI TBLE MTN-PLRMO 10/47 INS MRKS | 43760152 | TABLE MTN-PALERMO | 010/047 | ICS | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.502385 | 39.5124 | ETL.5690 | 40813461 | Marker (i.e. signs)-Steel | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
115820721 | T2 EI OLEUM-MARTINEZ 4/029 REPL INSS | 31457825 | OLEUM-MARTINEZ | 004/029 | 93K | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.1874362 | 38.0211 | ETL.3170 | 40830466 | Insulator-Steel | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - Prog Multi
115820747 | EI HUMBOLDT BAY-HU #1 5/026 RPR FOND | 43720604 | HUMBOLDT BAY-HUMBOLDT #1 | 005/026 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  |  | LATE | North Coast | WSIP | [6 empty] | '-124.122675 | 40.771 | ETL.1800 | 40808915 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Eureka |  |  | 2019-07-09
115820774 | T2 EI POE-RIO OSO 28/184 RPR CONS | 43737420 | POE-RIO OSO | 028/184 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.526576 | 39.5899 | ETL.5540 | 40757650 | Conductor-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
115820791 | T2 EI DRUM-RIO OSO #1 20/158 RMV FENCE | 43685812 | DRUM-RIO OSO #1 | 020/158 | CHR | F | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | <15D | North Valley | WSIP | [6 empty] | '-121.083934 | 39.1107 | ETL.1420 | 40866022 | Right of Way | Encroachment | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLS | Land | Expense | 931 | Sacramento |  |  | Yes
115820802 | T2 EI DRUM-RIO OSO #1 20/158 RPL SPLS | 43685808 | DRUM-RIO OSO #1 | 020/158 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.083934 | 39.1107 | ETL.1420 | 40866022 | Splice-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes
115820973 | T2 EI POE-RIO OSO 027/181 RMV NEST | 43737420 | POE-RIO OSO | 027/181 | ICS | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.524391 | 39.5947 | ETL.5540 | 40596655 | Structure-Steel | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
115821350 | T2 EI EAGLE ROCK-RED :010/058 RPR FOND | 43730052 | EAGLE ROCK-REDBUD | :010/058 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | WSIP | FSRP | [5 empty] | '-122.654685 | 38.892 | ETL.1480 | 40861253 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  | 2019-05-15
115821457 | DISTRIBUTION BENT MEMBER | 43715795 | SPARE T-LINE RECORD | T-124 | ICQ | E | Pre-2020_(2) High fire spread TD |  |  | Midway-Santa Maria | TR3 | LATE | South | WSIP | FSRP | [5 empty] | '-120.092924 | 35.1099 | ETL.9240 | 43249615 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Pismo Beach
115826622 | T2 EI PITTSBURG-CLAY #3 004/023 REGRADE | 43753159 | PITTSBURG-CLAYTON #3 | 004/023 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-121.910066 | 37.9819 | ETL.3290 | 40648855 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 2
115833035 | T2 EI STNSLAS-MNTCA #2 025/149 RPR STRT | 43712838 | STANISLAUS-MANTECA #2 | 025/149 | ICQ | F | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.739235 | 37.9321 | ETL.3820 | 40856515 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - Prog Multi
115834266 | T2 EI CRESTA-RIO OSO 022/179 REPAINT | 43708739 | CRESTA-RIO OSO | 022/179 | ICS | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.507798 | 39.6518 | ETL.4590 | 40910187 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
115844527 | T2 EI CRESTA-RIO OSO 27/220 REPL INSS | 31435732 | CRESTA-RIO OSO | 027/220 | 93K | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.5281191 | 39.5809 | ETL.4590 | 40921279 | Insulator-Steel | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  | Yes
115844556 | T2 EI PIT #1-COTTON 026/213 PAINT | 43879413 | PIT #1-COTTONWOOD | 026/213 | ICS | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.923298 | 40.7957 | ETL.5390 | 40657405 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
115844787 | T2NT EI PIT #1-COTTONWD 26/214 PNT TWR | 43755354 | PIT #1-COTTONWOOD | 026/214 | ICQ | F | Pre-2020_(4) TD tag on high spread line | Superintendent Approved work efficiency |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.925499 | 40.7951 | ETL.5390 | 40762975 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
115852532 | T2 EI PARADISE-TABLE MTN 24/188R RPL PL | 31453760 | PARADISE-TABLE MTN | 024/188 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.651841 | 39.7009 | ETL.4316 | 44383248 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
115858136 | T3 EI EAGLE ROCK-FUL-SIL 001/010 PAINT | 43730698 | EAGLE ROCK-FULTON-SILVERADO | 001/010 | ICS | E | Pre-2020_(9a) Other ignition related |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.800903 | 38.8166 | ETL.4392 | 40605188 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Lakeville |  |  | 2019-05-21
115858431 | T2 DI CARIBOU-PALERMO :1/015 RPR STUB | 44062862 | CARIBOU-PALERMO | :001/015 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.172958 | 40.0703 | ETL.3190 | 40912341 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115858437 | T2 EI VACA-PARKWAY 8/045 INSTL MRKS | 43760157 | VACA-PARKWAY | 008/045 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.035832 | 38.3639 | ETL.5850 | 40756446 | Marker (i.e. signs)-Steel | No Good/Out of Stdrd | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes
115858438 | T2 DI CARIBOU-PALERMO :001/015 RPR STRT | 44062862 | CARIBOU-PALERMO | :001/015 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.172958 | 40.0703 | ETL.3190 | 40912341 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
115858632 | T2 DI SMRTVLLE-NICOLS #2 00/18 WASH INSS | 43852598 | SMARTVILLE-NICOLAUS #2 | 000/018 | ICD | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.301104 | 39.1972 | ETL.8000 | 44177598 | Insulator | Contaminated | Ground Wash | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 622 | Sacramento |  |  | Yes
115858659 | T2 EI CRESTA-RIO OSO 27/220 RMV NEST | 43708739 | CRESTA-RIO OSO | 027/220 | ICS | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.528106 | 39.5809 | ETL.4590 | 40911510 | Structure-Steel | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
115858694 | T2 DI CARIBOU-PALERMO :026/215 RPLC HRPS | 44304495 | CARIBOU-PALERMO | :026/215 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.42411 | 39.8261 | ETL.3190 | 40758494 | Hardware-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
115858736 | T2NT DI CRIBOU-PLRMO :026/215 INST MRKS | 44304495 | CARIBOU-PALERMO | :026/215 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.42411 | 39.8261 | ETL.3190 | 40758494 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
115858744 | T2 DI CARIBOU-PALERMO :026/215 REPL GYWS | 44304495 | CARIBOU-PALERMO | :026/215 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.42411 | 39.8261 | ETL.3190 | 40758494 | Guy Wire-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
116117878 | T2 EI CBRN-LS AGLS-PNCH 45/192 REPL DAMS | 43749767 | COBURN-PANOCHE | 045/192 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-121.000483 | 36.6492 | ETL.4460 | 40681263 | Damper-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Moss Landing |  | Y - 6
116153199 | T2 EI COBURN-PANOCHE 44/191 RPR FOND | 43749766 | COBURN-PANOCHE | 044/191 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | South | WSIP | [8 empty] | ETL.4460 | 40925417 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Moss Landing |  | Y - 5
116153237 | EI PARKWAY-MORAGA 008/050 RPL HRDT | 43683430 | PARKWAY-MORAGA | 008/050 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-122.233688 | 38.0174 | ETL.5930 | 40758941 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog Multi
116153239 | T2 PALERMO-OROVILLE #2 A007/093 INSW | 31431545 | PALERMO-OROVILLE #2 | A007/093 | 93I | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.4936306 | 39.5304 | ETL.7740 | 41123112 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 508 | Table Mountain
116153288 | T2 EI PALERMO-COLGATE C006/028 CONS | 43724331 | PALERMO-COLGATE | C006/028 | ICS | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.294425 | 39.3075 | ETL.5360 | 40867219 | Conductor-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento
116153395 | T2NT EI RND MTN-CTWD #2 025/226 RPR STRT | 43877040 | ROUND MTN-COTTONWOOD #2 | 025/226 | ICS | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.071887 | 40.6598 | ETL.5640 | 40816297 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain
116153462 | T2NT EI RND MTN-CTWD #2 025/225 RPR STRT | 43877040 | ROUND MTN-COTTONWOOD #2 | 025/225 | ICS | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.071009 | 40.6611 | ETL.5640 | 40758166 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain
116153766 | T2 DI CARIBOU-PALRMO :001/016 RPR FOND | 44062862 | CARIBOU-PALERMO | :001/016 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.173733 | 40.0701 | ETL.3190 | 40910260 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
116153811 | T2 EI VACA-LAKEVILLE#1 8/43 INST HV | 43740456 | VACA-LAKEVILLE #1 | 008/043 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.037092 | 38.3617 | ETL.5840 | 40656087 | Marker (i.e. signs)-Steel | No Good/Out of Stdrd | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes
116153954 | T2 EI HMBLDT-BRDGVLL 109/005L RPL PL | 31440336 | HUMBOLDT-BRIDGEVILLE | 109/005 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | FSRP | [7 empty] | ETL.1810 | 44322613 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2019-08-27
116154237 | T2 EI MELONES-WILSON 0/1INS MRKS | 43727741 | MELONES-WILSON | 000/001 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.537403 | 37.9443 | ETL.5080 | 40586992 | Marker (i.e. signs)-Steel | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Victor |  | Y - 4
116155381 | T2 EI STNISLUS-MNTCA#2 18/106 INST HV |  | STANISLAUS-MANTECA #2 | 018/106 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.639255 | 37.9892 | ETL.3820 | 40808614 | Marker (i.e. signs)-Steel | Missing | Install |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 628 | Victor |  | Y - Prog Multi
116155383 | T3 EI CARIBOU-PALERMO :033/265 INST HRDT | 44051418 | CARIBOU-PALERMO | :033/265 | ICQ | E | Pre-2020_(3) On high spread structure |  |  |  | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.475991 | 39.7465 | ETL.3190 | 40770933 | Hardware-Tower | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
116155760 | EI POE-RIO OSO 042/279 REPL INSS | 31431911 | POE-RIO OSO | 042/279 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-121.5090803 | 39.3801 | ETL.5540 | 40889566 | Insulator-Steel | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  | Yes
116155857 | T2 EI ELECTRA-BELLOTA 0/010 RPR HRDT | 43727727 | ELECTRA-BELLOTA | 001/011 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.672768 | 38.3166 | ETL.4670 | 40863018 | Hardware-Tower | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - Prog Multi
116156059 | T2 EI NRTH TWR-MRTINZ JCT #1 :32/207 PNT | 43753295 | NORTH TOWER-MARTINEZ JCT #1 (21KV) | :032/207 | ICS | F | Pre-2020_(5b) On structure in bucket 5 | Budget Owner (Paint) |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.203827 | 38.0292 | ETL.3130 | 40804760 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  | Y - Prog Multi
116156070 | EI ELECTRA-BELLOTA 14/105 RPR STRT | 43727727 | ELECTRA-BELLOTA | 014/105 | ICQ | F | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | Central | WSIP | FSRP | [5 empty] | '-120.839334 | 38.1725 | ETL.4670 | 40593871 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - Prog Multi
116156119 | T2 DI CARIBOU-PALERMO :5/39 BURIED MEMB | 44059014 | CARIBOU-PALERMO | :005/039 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.217637 | 40.0409 | ETL.3190 | 40910282 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
116156299 | T3 EI DRUM-HIGGINS B009/088 REPAINT | 43738143 | DRUM-HIGGINS | B009/088 | ICS | E | Pre-2020_(9a) Other ignition related |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.894598 | 39.1647 | ETL.4393 | 40867206 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes
116156301 | T2 EI POE-RIO OSO 41/269 REPL HRDS | 31431911 | POE-RIO OSO | 041/269 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.51312 | 39.4029 | ETL.5540 | 40870609 | Hardware-Steel | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Contract | Capital | 628 | Table Mountain |  |  | Yes
116156489 | T2 EI OLEUM-MARTINEZ 7/48 REPAINT | 43753565 | OLEUM-MARTINEZ | 007/048 | ICS | F | Pre-2020_(9a) Other ignition related | Budget Owner (Paint) |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-122.136149 | 37.993 | ETL.3170 | 40804606 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  | Y - Prog Multi
116156508 | T2 DI CARIBOU-PALERMO :5/40 INSTL STRT | 44059014 | CARIBOU-PALERMO | :005/040 | ICQ | F | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.21813 | 40.0392 | ETL.3190 | 40910283 | Structure-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
116156532 | T2 DI CARIBOU-PALERMO :5/40 RMV SRT |  | CARIBOU-PALERMO | :005/040 |  | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.21813 | 40.0392 | ETL.3190 | 40910283 | Structure-Tower | Soil | Remove |  |  |  |  | PEND | LC | TLX | Contract | Expense |  | Table Mountain |  |  | Yes
116156552 | T2 EI POE-RIO OSO 42/276 RPR INSS | 43737421 | POE-RIO OSO | 042/276 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.510326 | 39.3872 | ETL.5540 | 40815741 | Insulator-Steel | No Good/Out of Stdrd | Repair | DOCC srdy | DOCC | Job has been constructed (documentation) | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
116156617 | T2 EI POE-RIO OSO 41/270 RPR INSS | 43737421 | POE-RIO OSO | 041/270 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.512926 | 39.4018 | ETL.5540 | 40598084 | Insulator-Steel | No Good/Out of Stdrd | Repair | DOCC srdy | DOCC | Job has been constructed (documentation) | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
116156642 | T2 DI CARIBOU-PALERMO :5/41 INSTL HRDT | 44059014 | CARIBOU-PALERMO | :005/041 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.218194 | 40.0372 | ETL.3190 | 40910284 | Hardware-Tower | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
116156670 | T2 DI CARIBOU-PALERMO :5/41 RPR FOND | 44059014 | CARIBOU-PALERMO | :005/041 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.218194 | 40.0372 | ETL.3190 | 40910284 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
116156801 | T2 EI DRUM-RIO OSO #1 32/235 WSH INSS | 43746397 | DRUM-RIO OSO #1 | 032/235 | ICD | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.290097 | 39.0274 | ETL.1420 | 40762571 | Insulator | Contaminated | Helicopter Wash | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 626 | Sacramento |  |  | Yes
116156843 | T3 DI TGR CRK-VLLY SPRNG 3/025 RPNT STRT | 43727745 | TIGER CREEK-VALLEY SPRINGS | 003/025 | ICS | E | Pre-2020_(9a) Other ignition related | Budget Owner (Paint) |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-120.543879 | 38.4337 | ETL.5790 | 40823048 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - Prog Multi
116156983 | EI ELECTRA-BELLOTA 14/107 RPR FOND | 43727727 | ELECTRA-BELLOTA | 014/107 | ICQ | F | Pre-2020_(9a) Other ignition related |  |  |  |  | LATE | Central | WSIP | FSRP | [5 empty] | '-120.843224 | 38.1687 | ETL.4670 | 40659318 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - Prog Multi
116157031 | T2 EI TEMBLOR-SLO 26/160 REPL BIRD GARDS | 43740614 | TEMBLOR-SAN LUIS OBISPO | 026/160 | ICS | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | South | WSIP | FSRP |  |  |  | Clearance Cancelled - External | Aug clearance was cancelled, rescheduled for Nov | '-120.155757 | 35.3869 | ETL.3960 | 40604669 | Raptor Guard-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 593 | Pismo Beach |  | Y - 4 | 2019-04-16
116157476 | T2 DI CARIBOU-PALERMO :003/023 INS HRDT | 44062862 | CARIBOU-PALERMO | :003/023 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.192208 | 40.0629 | ETL.3190 | 40910267 | Hardware-Tower | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
116157502 | T2 DI CARIBOU-PALERMO :003/023 RPR FOND | 44062862 | CARIBOU-PALERMO | :003/023 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.192208 | 40.0629 | ETL.3190 | 40910267 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
116157558 | T2 DI CARIBOU-PALERMO :002/017 INST HRDT | 44062862 | CARIBOU-PALERMO | :002/017 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.177753 | 40.0689 | ETL.3190 | 40910261 | Hardware-Tower | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
116157582 | T2 EI OLM-NRTH TWR-CHRSTI 3/22 PAINT | 43752229 | OLEUM-NORTH TOWER-CHRISTIE | 003/022 | ICS | E | Pre-2020_(5b) On structure in bucket 5 | Budget Owner (Paint) |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.203721 | 38.0286 | ETL.3180 | 40646332 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay
116157631 | T2 DI CARIBOU-PALERMO :002/021 RPR FOND | 44062862 | CARIBOU-PALERMO | :002/021 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.189644 | 40.0629 | ETL.3190 | 40910265 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
116157634 | T2 DI CARIBOU-PALERMO :002/018 RPR STRT | 44062862 | CARIBOU-PALERMO | :002/018 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.179456 | 40.0683 | ETL.3190 | 40910262 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
116309697 | T2 EI HUMBOLDT-TRINITY 066/001C RPR GYWW | 43729542 | HUMBOLDT-TRINITY | 066/001 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.268289 | 40.7213 | ETL.1820 | 44562793 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Eureka |  |  | 2019-08-09
116309761 | T2 EI OLEUM-MARTINEZ 007/047 REPAINT | 43753565 | OLEUM-MARTINEZ | 007/047 | ICS | F | Pre-2020_(9a) Other ignition related | Budget Owner (Paint) |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-122.13698 | 37.9936 | ETL.3170 | 40857601 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay
116319204 | T3 EI DRUM-HIGGINS 6/069 PNT TWR | 43738143 | DRUM-HIGGINS | 006/069 | ICS | E | Pre-2020_(9a) Other ignition related |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.854985 | 39.1918 | ETL.4393 | 40865238 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes
116319208 | T2 EI NTH TWR-MRTNZ JCT 1 :32/204 RP DAM | 43753295 | NORTH TOWER-MARTINEZ JCT #1 (21KV) | :032/204 | ICS | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.205106 | 38.0367 | ETL.3130 | 40747004 | Damper-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - 2
116319495 | T2 EI NRT TWR-MRTNZ JT 1 :32/204 RPL INS | 31455159 | NORTH TOWER-MARTINEZ JCT #1 (21KV) | :032/204 | 93K | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.205106 | 38.0367 | ETL.3130 | 40775615 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - 2
116319619 | T3 EI DRUM-HIGGINS 6/067 PNT TWR | 43738143 | DRUM-HIGGINS | 006/067 | ICS | E | Pre-2020_(9a) Other ignition related |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.850524 | 39.1935 | ETL.4393 | 40813294 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes
116319776 | T2 EI OLEUM-MARTINEZ 007/046 RPR FOND | 43753569 | OLEUM-MARTINEZ | 007/046 | ICQ | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.13989 | 37.996 | ETL.3170 | 40857606 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 3
116319795 | T3 DI TIGR CRK-ELECTRA 5/043 REPAINT | 43691537 | TIGER CREEK-ELECTRA | 005/043 | ICS | E | Pre-2020_(9a) Other ignition related | Budget Owner (Paint) |  |  | TR3 | LATE | Central | WSIP |  |  |  |  | Clearance Denied by GCC | unable to take out line | '-120.581694 | 38.4245 | ETL.5780 | 40662764 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Released
116319921 | T2 DI CARIBOU-PALERMO :003/30 RPR STUBS | 44059014 | CARIBOU-PALERMO | :003/030 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.205437 | 40.0561 | ETL.3190 | 40910274 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
116319924 | T2 DI CARIBOU-PALERMO :3/29 BURIED MEMB | 44062862 | CARIBOU-PALERMO | :003/029 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.202237 | 40.0585 | ETL.3190 | 40910273 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
116319941 | T2 EI CARIBOU-PALERMO :013/106 INST HRDT | 44069583 | CARIBOU-PALERMO | :013/106 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.283913 | 39.9602 | ETL.3190 | 40738342 | Hardware-Tower | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
116319944 | T2 EI PARKWAY-MORAGA 07/043 RPR OPGW | 43683436 | PARKWAY-MORAGA | 007/043 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.233575 | 38.0337 | ETL.5930 | 40863055 | Shield Wire / OPGW-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - Prog Multi
116319994 | T2 EI POE-RIO OSO 41/271 RPR INSS | 43737421 | POE-RIO OSO | 041/271 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.512201 | 39.3977 | ETL.5540 | 40590801 | Insulator-Steel | No Good/Out of Stdrd | Repair | DOCC srdy | DOCC | Job has been constructed (documentation) | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
116321151 | T2 HMBLDT-BRDGVLLE 99/06L RPL POLE | 31497841 | HUMBOLDT-BRIDGEVILLE | 099/006 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | North Coast | WSIP | [8 empty] | ETL.1810 | 44322423 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2019-07-10
116321157 | T3 EI DRUM-HIGGINS 006/068 REPAINT | 43738143 | DRUM-HIGGINS | 006/068 | ICS | E | Pre-2020_(9a) Other ignition related |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.852654 | 39.1926 | ETL.4393 | 40862207 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes
116322417 | T2 EI PIT #1-COTTON 037/318 RPR STRT | 43755354 | PIT #1-COTTONWOOD | 037/318 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Internal Process | Circuit Based Scheduling | '-122.034545 | 40.6766 | ETL.5390 | 40868299 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
116322451 | T3 EI DRUM-HIGGINS 006/065 REPAINT | 43738143 | DRUM-HIGGINS | 006/065 | ICS | E | Pre-2020_(9a) Other ignition related |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.846431 | 39.1953 | ETL.4393 | 40751949 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento
116324229 | T2 EI DRUM-HIGGINS B010/093 RPT TWR | 43738143 | DRUM-HIGGINS | B010/093 | ICS | E | Pre-2020_(3) On high spread structure | Budget Owner (Paint) |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Program | 2021 Paint took out of program due to future project to be removed with [REDACTED] | '-120.910715 | 39.158 | ETL.4393 | 41196106 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes
116324828 | T3 EI DRUM-HIGGINS 6/066 PNT TWR | 43738143 | DRUM-HIGGINS | 006/066 | ICS | E | Pre-2020_(9a) Other ignition related |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.848575 | 39.1943 | ETL.4393 | 40822536 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes
116326609 | T3 EI DRUM-HIGGINS 6/064 PNT TWR | 43738143 | DRUM-HIGGINS | 006/064 | ICS | E | Pre-2020_(9a) Other ignition related |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.845725 | 39.1968 | ETL.4393 | 40762134 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes
116327425 | T2 EI PIT #1-CTNWD 37/319 REPLUMB STRT | 43755354 | PIT #1-COTTONWOOD | 037/319 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.035637 | 40.6753 | ETL.5390 | 40867664 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
116327631 | T2 DI CARIBOU-PALERMO :16/133 RPR FOND | 44069583 | CARIBOU-PALERMO | :016/133 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.318623 | 39.9288 | ETL.3190 | 40738821 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
116328489 | T2 EI TIG CRK-VAL SPR 012/123 INST MRKS |  | TIGER CREEK-VALLEY SPRINGS | 015/123 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.679707 | 38.3105 | ETL.5790 | 40590026 | Marker (i.e. signs)-Steel | No Good/Out of Stdrd | Install |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 628 | Victor |  | Y - Prog Multi
116328803 | T2 EI TIGER CREEK-VLY SP 15/124 RPL MRKS |  | TIGER CREEK-VALLEY SPRINGS | 015/124 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.680275 | 38.31 | ETL.5790 | 40648161 | Marker (i.e. signs)-Steel | Missing | Install |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 628 | Victor |  | Y - Prog Multi
116329924 | T2 EI PIT#1-CTNWD 040/345 RPNT TWR | 43879413 | PIT #1-COTTONWOOD | 041/345 | ICS | F | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.077931 | 40.6245 | ETL.5390 | 40758862 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
116330146 | T2 EI TIGR CRK-VAL SPR 013/101 RPR FOND | 43727746 | TIGER CREEK-VALLEY SPRINGS | 013/101 | ICQ | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.665017 | 38.34 | ETL.5790 | 40682058 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Released
116332004 | T3 EI PIT #1-COTTONW 28/228 PNT TWR | 43735854 | PIT #1-COTTONWOOD | 028/228 | ICS | F | Pre-2020_(9a) Other ignition related |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.944772 | 40.7841 | ETL.5390 | 40868810 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
116340801 | T3 DRUM-HIGGINS 005/060 REPAINT STRT | 43738143 | DRUM-HIGGINS | 005/060 | ICS | E | Pre-2020_(9a) Other ignition related |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.842668 | 39.2033 | ETL.4393 | 40595827 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento
116342755 | T2 EI TGR CRK-VAL SPR 012/099 PAINT | 43727745 | TIGER CREEK-VALLEY SPRINGS | 012/099 | ICS | F | Pre-2020_(9a) Other ignition related | Budget Owner (Paint) |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.664014 | 38.3423 | ETL.5790 | 40582783 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Released
116343050 | T2 EI TIGER CREEK-ELEC 012/099 PAINT | 43727728 | TIGER CREEK-ELECTRA | 012/099 | ICS | E | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.663897 | 38.3432 | ETL.5780 | 40862695 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Released
116347915 | T2 DI CARIBOU-PALERMO :005/042 RPR STUB | 44059014 | CARIBOU-PALERMO | :005/042 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.218237 | 40.0358 | ETL.3190 | 40910285 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
116348034 | T2 EI TIG CRK-VAL SPR 015/125 INST MRKS |  | TIGER CREEK-VALLEY SPRINGS | 015/125 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.682415 | 38.3082 | ETL.5790 | 40645140 | Marker (i.e. signs)-Steel | No Good/Out of Stdrd | Install |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 628 | Victor |  | Y - Prog Multi
116348037 | T2 EI CRBU-TBL MTN 020/139B RPR GYWS | 43729346 | CARIBOU-TABLE MTN | 020/139B | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.277149 | 39.9655 | ETL.4440 | 44190879 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Table Mountain |  |  | Yes
116348770 | T2 EI ELECTRA-BELLOTA 001/016 RPR FOND | 43727727 | ELECTRA-BELLOTA | 001/016 | ICQ | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.682611 | 38.3084 | ETL.4670 | 40659832 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - Prog Multi
116355588 | T2 DI CARIBOU-PALERMO :003/022 RPR STRT | 44062862 | CARIBOU-PALERMO | :003/022 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.185972 | 40.0637 | ETL.3190 | 40910266 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
116357902 | T2 DI CARIBOU-PALERMO :014/111 RPR FOND | 44069583 | CARIBOU-PALERMO | :014/111 | ICQ | E | Pre-2020_(3) On high spread structure |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.293251 | 39.9571 | ETL.3190 | 40642567 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
116357906 | T2 DI CARIBOU-PALERMO :014/112 INST HRDT | 44069583 | CARIBOU-PALERMO | :014/112 | ICQ | E | Pre-2020_(3) On high spread structure |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.295392 | 39.956 | ETL.3190 | 40738828 | Hardware-Tower | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
116360562 | T2 DI CARIBOU-PALERMO :014/113 BENT MEMB | 44069583 | CARIBOU-PALERMO | :014/113 | ICQ | E | Pre-2020_(2) High fire spread TD |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.297639 | 39.9554 | ETL.3190 | 40738825 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
116360569 | T3 DI CRESTA RIO OSO 014/114 RPR INSS | 43708739 | CRESTA-RIO OSO | 014/114 | ICS | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.461694 | 39.7654 | ETL.4590 | 40910136 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
116397299 | T2 EI CARIBOU #2 20/022 RPL SPLW | 43742128 | CARIBOU #2 | 020/022 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.015388 | 40.032 | ETL.6280 | 40675452 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
116416870 | T2 DI CARIBOU-PALRMO :14/116 BURIED MEMB | 44069583 | CARIBOU-PALERMO | :014/116 | ICQ | E | Pre-2020_(2) High fire spread TD |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.301792 | 39.9518 | ETL.3190 | 40811629 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
116457907 | T3 DI TIGER CREEK-ELECTRA 4/36 PNT STRT | 43691537 | TIGER CREEK-ELECTRA | 004/036 | ICS | E | Pre-2020_(9a) Other ignition related | Budget Owner (Paint) |  |  | TR3 | LATE | Central | WSIP |  |  |  |  | Clearance Denied by GCC | unable to take out line | '-120.568418 | 38.4278 | ETL.5780 | 40811159 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Released
116459983 | T2 EI PIT #1-COTTON 040/344 REPAINT | 43930183 | PIT #1-COTTONWOOD | 040/344 | ICX | E | Pre-2020_(4b) On structure in bucket 4 |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.074673 | 40.6284 | ETL.5390 | 40758994 | Structure-Tower | Paint/Coating | Repaint | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense |  | Table Mountain |  |  | Yes
116459987 | T2 EI CARIBOU-PALERMO :015/121 RPR STRT | 44069583 | CARIBOU-PALERMO | :015/121 | ICQ | E | Pre-2020_(2) High fire spread TD |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.308198 | 39.9429 | ETL.3190 | 40642566 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
116460026 | T3 EI DRUM-HIGGINS 005/062 REPAINT | 43738143 | DRUM-HIGGINS | 005/062 | ICS | E | Pre-2020_(9a) Other ignition related |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.844544 | 39.1993 | ETL.4393 | 40660208 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes
116460051 | T2 DI CARIBOU-PALERMO :26/216 BENT MEMB | 44069454 | CARIBOU-PALERMO | :026/216 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.425086 | 39.8249 | ETL.3190 | 40816589 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
116460053 | T2 DI CARIBOU-PALERMO :26/216 INST HRDS | 44302715 | CARIBOU-PALERMO | :026/216 | ICS | F | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.425086 | 39.8249 | ETL.3190 | 40816589 | Hardware-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain
116460057 | T2 DI CARBU-PALRM-TWR :26/217 RPR STUB | 44069454 | CARIBOU-PALERMO | :026/217 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.425857 | 39.8239 | ETL.3190 | 40815590 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
116460062 | T2 DI CARIBOU-PALERMO :003/024 RPR STRT | 44062862 | CARIBOU-PALERMO | :003/024 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.195411 | 40.0633 | ETL.3190 | 40910268 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
116460065 | T2 DI CARIBOU-PALERMO :003/024 INST HRDT | 44062862 | CARIBOU-PALERMO | :003/024 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.195411 | 40.0633 | ETL.3190 | 40910268 | Hardware-Tower | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
116460066 | T2 DI CARIBOU-PALERMO :015/119 INST HRDT | 44069583 | CARIBOU-PALERMO | :015/119 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.305695 | 39.9478 | ETL.3190 | 40738346 | Hardware-Tower | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
116460099 | T2 DI CARIBOU-PALERMO :015/119 RPR STUBS | 44069583 | CARIBOU-PALERMO | :015/119 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.305695 | 39.9478 | ETL.3190 | 40738346 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
116460170 | T2 DI CARIBOU-PALERMO :003/027 RPR FOND | 44062862 | CARIBOU-PALERMO | :003/027 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.199707 | 40.0633 | ETL.3190 | 40910271 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
116460186 | T2 DI CARIBOU-PALERMO :027/223 RRP FOND | 44069801 | CARIBOU-PALERMO | :027/223 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.435652 | 39.8119 | ETL.3190 | 40668940 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
116460187 | T2 DI CARIBOU-PALERMO :27/223 RPR INSS | 44304495 | CARIBOU-PALERMO | :027/223 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.435652 | 39.8119 | ETL.3190 | 40668940 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain
116460231 | T2 EI MIDDLE FORK-GOLD 036/26 PAINT | 44302265 | MIDDLE FORK-GOLD HILL | 036/262 | ICS | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.044457 | 38.6999 | ETL.5140 | 40683779 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes
116460283 | T2 EI VALLEY SPRINGS-CL 005/077 RPR STRW | 43727736 | VALLEY SPRINGS-CLAY | 005/077 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.83005 | 38.2007 | ETL.8264 | 44255306 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 12
116460304 | T2 DI CARIBOU-PALERMO :27/226 REPR FOND | 44069801 | CARIBOU-PALERMO | :027/226 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.438961 | 39.8082 | ETL.3190 | 40828380 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
116460315 | T2 EI VALLEY SPRINGS-CL 005/077 RPL SPLW | 43727736 | VALLEY SPRINGS-CLAY | 005/077 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [8 empty] | ETL.8264 | 44255307 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog Multi
116460334 | T2 EI OLEUM-MARTINEZ 006/042 RPR FOND | 43753569 | OLEUM-MARTINEZ | 006/042 | ICQ | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.148856 | 38.0027 | ETL.3170 | 40644165 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 3
116460445 | T2 EI PARKWAY-MORAGA 009/053 RPL HRDT | 43683430 | PARKWAY-MORAGA | 009/053 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.233747 | 38.0084 | ETL.5930 | 40868354 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog Multi
116460467 | T2 EI PLCR-GLD HLL#1 2/022 RPR STRT |  | PLACER-GOLD HILL #1 | 002/022 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.097404 | 38.8703 | ETL.3340 | 40911874 | Structure-Steel | Paint/Coating | Other |  |  |  |  | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes
116460477 | T2 DI CARIBOU-PALERMO :4/33 RPL HRDT | 44059014 | CARIBOU-PALERMO | :004/033 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.208362 | 40.051 | ETL.3190 | 40910277 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
116460511 | EI PLACER-GOLD HILL #1 9/066 CANCEL | 43910271 | PLACER-GOLD HILL #1 | 009/066 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  | CANCEL/CNCL |  | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.141863 | 38.7729 | ETL.3340 | 40905619 | Conductor-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes
116460571 | T2 DI CARIBOU-PALERMO :024/198 REGRADE | 44304495 | CARIBOU-PALERMO | :024/198 | ICS | E | Pre-2020_(3) On high spread structure |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.401589 | 39.8512 | ETL.3190 | 40867974 | Structure-Steel | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain
116460578 | T2 DI CARIBOU-PALERMO :024/200 REPAINT | 44302715 | CARIBOU-PALERMO | :024/200 | ICS | F | Pre-2020_(3) On high spread structure |  |  |  | TR2 | <15D | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.40384 | 39.85 | ETL.3190 | 40599288 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain
116460626 | T2 EI CARIBOU-PALERMO :024/202 RPR FOND | 44069454 | CARIBOU-PALERMO | :024/202 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.409795 | 39.8476 | ETL.3190 | 40674980 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
116460628 | T2 DI CARIBOU-PALERMO :024/202 RPR STRS | 44304495 | CARIBOU-PALERMO | :024/202 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.409795 | 39.8476 | ETL.3190 | 40674980 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain
116460641 | T2 DI CARIBOU-PALERMO :024/203 RPR FOND | 44069454 | CARIBOU-PALERMO | :024/203 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.413518 | 39.8449 | ETL.3190 | 40651675 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
116460710 | T2 DI COLGATE SMRTVL#1 007/079 REGRADE | 44097455 | COLGATE-SMARTVILLE #1 | 007/079 | ICW | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.284116 | 39.2647 | ETL.6510 | 40659535 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
116460715 | T2 DI CARIBOU-PALERMO :008/066 RPR INSS | 44304495 | CARIBOU-PALERMO | 008/066 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP |  |  |  | Field Operations |  | '-121.24349 | 40.0068 | ETL.3190 | 40920047 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain
116460719 | T3NT DI CARIBOU-PALRMO :33/267 INST MRKS | 44304495 | CARIBOU-PALERMO | :033/267 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.476775 | 39.7415 | ETL.3190 | 40826427 | Marker (i.e. signs)-Steel | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain
116460778 | T2 EI CARIBOU #2 23/021 RPL POLE | 31455203 | CARIBOU #2 | 023/021 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.968705 | 40.0406 | ETL.6280 | 40591777 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  | Yes
116460893 | T3 DI CARIBOU PALERMO :033/270 INST HRDT | 44051417 | CARIBOU-PALERMO | :033/270 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.477905 | 39.7343 | ETL.3190 | 40599303 | Hardware-Tower | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
116460894 | T3 DI CARIBOU PALERMO :033/270 RPR FOND | 44051417 | CARIBOU-PALERMO | :033/270 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.477905 | 39.7343 | ETL.3190 | 40599303 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
116460900 | T2 DI CARIBOU-PALERMO :025/206 RPR STRT |  | CARIBOU-PALERMO | :025/206 |  | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.416443 | 39.8424 | ETL.3190 | 40828382 | Structure-Tower | Soil | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense |  | Table Mountain
116460903 | T2 DI CRIBOU-PLERMO :025/210 RPR BURIED | 44069454 | CARIBOU-PALERMO | :025/210 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.42085 | 39.8336 | ETL.3190 | 40599291 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
116460907 | T2 DI CARIBOU-PALERMO :25/211 BENT MEMB | 44069454 | CARIBOU-PALERMO | :025/211 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.421047 | 39.8318 | ETL.3190 | 40602486 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
116460923 | T2 EI HAT CREEK #1-WES 28/546 RPL CRSW | 31471926 | HAT CREEK #1-WESTWOOD | 028/546 | 93E | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.170675 | 40.6496 | ETL.7030 | 40868486 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  | Yes
116460930 | T2 EI RO DLL JCT-BRDGVLLE 33/8 RPL CONW | 31473341 | RIO DELL JCT-BRIDGEVILLE | 033/008 | 93C | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.894189 | 40.4835 | ETL.7850 | 44360011 | Conductor-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 638 | Eureka |  |  | 2019-04-09
116460932 | T2 EI MESA-STA MARIA 21/102D REPL INSS | 31500464 | MESA-SANTA MARIA | 021/102D | 93K | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | South | WSIP | FSRP | [5 empty] | '-120.4463564 | 35.0078 | ETL.2450 | 44283859 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 6
116460941 | T2 EI HAT CREEK #1-WES 32/617 RPR INSW | 43736797 | HAT CREEK #1-WESTWOOD | 032/617 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.116032 | 40.6144 | ETL.7030 | 40656905 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
116460963 | T2 EI HAT CREEK #1-WES 28/539 RPL STRW | 31426976 | HAT CREEK #1-WESTWOOD | 028/539 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.175737 | 40.6528 | ETL.7030 | 40601704 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain
116460964 | T2 EI HAT CREEK #1-WES 28/538 RPL STRW | 31426976 | HAT CREEK #1-WESTWOOD | 028/538 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.176543 | 40.6532 | ETL.7030 | 40616913 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain
116460972 | T2 EI CARIBOU-TABLE MTN 21/145A PNT TWR | 43729346 | CARIBOU-TABLE MTN | 021/145A | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.286625 | 39.959 | ETL.4440 | 40758277 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
116460976 | T2 EI HAT CREEK #1-WEST 026/515 RPR INSW | 43736797 | HAT CREEK #1-WESTWOOD | 026/515 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.191028 | 40.6667 | ETL.7030 | 40825588 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
116460977 | T2 EI HAT CREEK #1-WE 26/514 RPR STRW | 43736797 | HAT CREEK #1-WESTWOOD | 026/514 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.191597 | 40.6673 | ETL.7030 | 40817133 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
116460979 | T2 EI HAT CREEK #1-WES 26/517 RPL STRW | 31426976 | HAT CREEK #1-WESTWOOD | 026/517 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.189843 | 40.6654 | ETL.7030 | 40876192 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain
116460986 | T2 EI HAT CREEK #1-WES 28/547 RPL STRW | 31426976 | HAT CREEK #1-WESTWOOD | 028/547 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.169887 | 40.6491 | ETL.7030 | 40876194 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain
116461038 | T2NT EI CARIBOU #2 23/620 INST GMKW | 43742128 | CARIBOU #2 | 023/620 | ICW | F | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.970462 | 40.0393 | ETL.6280 | 44259137 | Guy Wire Mark /Indic-Wood | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
116461105 | T2 DI CARIBOU-PALERMO :021/179 RPR FOND | 44069454 | CARIBOU-PALERMO | :021/179 | ICQ | E | Pre-2020_(3) On high spread structure |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.37491 | 39.8785 | ETL.3190 | 40738369 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
116461108 | T2 DI CARIBOU-PALERMO :021/179 RPR INSS |  | CARIBOU-PALERMO | :021/179 | 93K | E | Pre-2020_(2) High fire spread TD |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.37491 | 39.8785 | ETL.3190 | 40738369 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain
116461109 | T2 DI CARIBOU-PALERMO :17/146 BURY MEMB | 44069583 | CARIBOU-PALERMO | :017/146 | ICQ | E | Pre-2020_(2) High fire spread TD |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.327474 | 39.9159 | ETL.3190 | 40811612 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
116469448 | T3 DI CARIBOU-PALERMO :011/091 RPR FOND | 44051417 | CARIBOU-PALERMO | :011/091 | ICQ | E | Pre-2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.276852 | 39.9826 | ETL.3190 | 40912111 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
116469450 | T2 DI CARIBOU-PALERMO :020/162 RPL HRDT | 44069454 | CARIBOU-PALERMO | :020/162 | ICQ | E | Pre-2020_(2) High fire spread TD |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.357958 | 39.9029 | ETL.3190 | 40738811 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
116469456 | T2 DI CARIBOU-PALRMO :17/143 BURIED MEMB | 44069583 | CARIBOU-PALERMO | :017/143 | ICQ | E | Pre-2020_(2) High fire spread TD |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.324088 | 39.9184 | ETL.3190 | 40738355 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
116469459 | T2 DI CARIBOU-PALERMO :17/143 RPL INSS |  | CARIBOU-PALERMO | :017/143 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP |  |  |  | Field Operations |  | '-121.324088 | 39.9184 | ETL.3190 | 40739414 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain
116469471 | T2 DI CARIBOU-PALERMO :17/143 INST HRDT | 44069583 | CARIBOU-PALERMO | :017/143 | ICQ | E | Pre-2020_(3) On high spread structure |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.324088 | 39.9184 | ETL.3190 | 40738355 | Hardware-Tower | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
116469474 | T2 DI CARIBOU-PALERMO :17/140 RPR FOND | 44069583 | CARIBOU-PALERMO | :017/140 | ICQ | E | Pre-2020_(3) On high spread structure |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.319376 | 39.9211 | ETL.3190 | 40642213 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
116469476 | T2 DI CARIBOU-PALERMO :17/141 RPR FOND | 44069583 | CARIBOU-PALERMO | :017/141 | ICQ | E | Pre-2020_(3) On high spread structure |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.321058 | 39.9198 | ETL.3190 | 40642499 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
116469488 | T2 DI CARIBOU-PALERMO :17/137 RPR STUB | 44069583 | CARIBOU-PALERMO | :017/137 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.317946 | 39.9235 | ETL.3190 | 40806063 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
116469764 | T2 DI CARIBOU-PALERMO :013/104 RPR STRT | 44069583 | CARIBOU-PALERMO | :013/104 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.280354 | 39.9626 | ETL.3190 | 40747408 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
116469765 | T2NT DI CARIBOU-PLRM :013/104 RPNT STRT |  | CARIBOU-PALERMO | :013/104 |  | F | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.280354 | 39.9626 | ETL.3190 | 40747408 | Structure-Tower | Paint/Coating | Repaint |  |  |  |  | PEND | LC | TLN | Maintenance | Expense |  | Table Mountain
116469911 | T2 DI CARIBOU-PALERMO :013/105 RPR STUBS | 44069583 | CARIBOU-PALERMO | :013/105 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.282785 | 39.961 | ETL.3190 | 40747389 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
116469912 | T2 DI CARIBOU-PALERMO :013/105 RPR HRDT | 44069583 | CARIBOU-PALERMO | :013/105 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.282785 | 39.961 | ETL.3190 | 40747389 | Hardware-Tower | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
116469919 | T2 DI CARIBOU-PALRMO :13/106 BURIED MEMB | 44069583 | CARIBOU-PALERMO | :013/106 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.283913 | 39.9602 | ETL.3190 | 40738342 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
116470379 | T2 DI CARIBOU-PALRMO :15/125 BURIED MEMB | 44069583 | CARIBOU-PALERMO | :015/125 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.311915 | 39.9394 | ETL.3190 | 40753327 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
116470380 | T2 DI CARIBOU-PALERMO :009/71 RPR FOND | 44059014 | CARIBOU-PALERMO | :009/071 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.257827 | 40.0052 | ETL.3190 | 40910313 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
116470410 | T3 DI CARIBOU-PLRM :032/264 RPR JUMP | 43659205 | CARIBOU-PALERMO | :032/264 | ICS | E | Pre-2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.475885 | 39.7472 | ETL.3190 | 40771771 | Jumper-Steel | No Good/Out of Stdrd | Repair | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain
116470465 | T3 DI CARIBOU-PALERMO :011/092 REPL CONN |  | CARIBOU-PALERMO | :011/092 | ICM | E | Pre-2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.27547 | 39.9808 | ETL.3190 | 40910331 | Connector | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLX | Contract | Expense | 534 | Table Mountain |  |  | Yes
116470596 | T3 DI CARIBOU-PLRM :032/262 RPR FOND | 44051417 | CARIBOU-PALERMO | :032/262 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.475245 | 39.7512 | ETL.3190 | 40702274 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
116470618 | T2 DI CARIBOU-PALERMO :028/233 RPR HRDT | 44069597 | CARIBOU-PALERMO | :028/233 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.450558 | 39.8014 | ETL.3190 | 40656365 | Hardware-Tower | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
116470643 | T3 DI CARIBOU-PLERMO :037/300B REPL CONN |  | CARIBOU-PALERMO | :037/300B | ICM | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.486563 | 39.6812 | ETL.3190 | 41162692 | Connector | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLX | Contract | Expense | 534 | Table Mountain |  |  | Yes
116470894 | T3 EI FULTON-PUEBLO 41/214 INS DAMS | 44306529 | FULTON-PUEBLO | 041/214 | ICS | E | Pre-2020_(9a) Other ignition related |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.736557 | 38.4973 | ETL.1600 | 40762053 | Damper-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville |  |  | 2019-09-03
116471084 | T2 EI OLM-NRTH TWR-CHRST 1/10 PNT STRS | 43752229 | OLEUM-NORTH TOWER-CHRISTIE | 001/010 | ICS | E | Pre-2020_(9a) Other ignition related | Budget Owner (Paint) |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-122.233799 | 38.0389 | ETL.3180 | 40580267 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  | Y - Prog Multi
116471211 | T2 EI CARIBOU-PALERMO :013/109 RPL HRDT | 44069583 | CARIBOU-PALERMO | :013/109 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.288193 | 39.9584 | ETL.3190 | 40738826 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
116471213 | T2 CARIBOU-PALERMO :13/110 INS HRDT | 44069583 | CARIBOU-PALERMO | :013/110 | ICQ | E | Pre-2020_(3) On high spread structure |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.290832 | 39.9582 | ETL.3190 | 40642211 | Hardware-Tower | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
116471214 | T2 EI CARIBOU-PALERMO :014/111 RPR STRT | 44069583 | CARIBOU-PALERMO | :014/111 | ICQ | E | Pre-2020_(2) High fire spread TD |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.293251 | 39.9571 | ETL.3190 | 40642567 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
116471218 | T2 EI CARIBOU-PALERMO :013/109 RPR STRT | 44069583 | CARIBOU-PALERMO | :013/109 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.288193 | 39.9584 | ETL.3190 | 40738826 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
116471227 | T2 EI CARIBOU-PALERMO :13/108 RPR JUMS | 44304495 | CARIBOU-PALERMO | :013/108 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.286412 | 39.9586 | ETL.3190 | 40858895 | Jumper-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain
116471265 | T2 EI PIT #1-COTTONWOOD 38/331 RPR STRT | 43755354 | PIT #1-COTTONWOOD | 038/331 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Internal Process | Circuit Based Scheduling | '-122.048237 | 40.6602 | ETL.5390 | 40579862 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
116471317 | T2 EI CARIBOU-TABLE MTN 20/144A PNT STRT | 43729346 | CARIBOU-TABLE MTN | 020/144A | ICS | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.28548 | 39.9599 | ETL.4440 | 40758423 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
116471357 | PLCR-GLD HILL#1 2/23 PAINT TOWER |  | PLACER-GOLD HILL #1 | 002/023 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  |  | LATE | North Valley | WSIP |  |  |  |  | Internal Process | Circuit Based Scheduling | '-121.097232 | 38.8664 | ETL.3340 | 40911183 | Structure-Steel | Paint/Coating | Other |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 628 | Sacramento
116471432 | T3 DI CARIBOU-PLRM :030/248 RPR JUMS | 43659205 | CARIBOU-PALERMO | :030/248 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.455372 | 39.773 | ETL.3190 | 40878269 | Jumper-Steel | No Good/Out of Stdrd | Repair | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain
116471514 | T3 EI DRUM-HIGGINS B010/105 CANCEL | 43738143 | DRUM-HIGGINS | B010/105 | ICS | E | Pre-2020_(9a) Other ignition related |  |  | CANCEL/CNCL | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.94385 | 39.1514 | ETL.4393 | 41162657 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes
116471648 | T2 EI RND MTN-TBL MTN #2 81/328 INS MRKT | 44302501 | ROUND MTN-TABLE MTN #2 | 081/328 | ICS | E | Pre-2020_(4b) On structure in bucket 4 | Superintendent Approved work efficiency |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.701904 | 39.6591 | ETL.6070 | 40865961 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Table Mountain
116471845 | T3 DI CARIBOU-PALERMO :012/093 RMV FOND | 44051417 | CARIBOU-PALERMO | :012/093 | ICQ | E | Pre-2020_(3) On high spread structure |  |  |  | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.274659 | 39.9777 | ETL.3190 | 40912112 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
116471848 | T3 DI CARIBOU-PALERMO :012/094 RPR FOND | 44051417 | CARIBOU-PALERMO | :012/094 | ICQ | E | Pre-2020_(3) On high spread structure |  |  |  | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.27516 | 39.9756 | ETL.3190 | 40912113 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
116471874 | T2 EI PIT #1-COTTONWOOD 39/334 RPR FOND | 43879412 | PIT #1-COTTONWOOD | 039/334 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Internal Process | Circuit Based Scheduling | '-122.055336 | 40.6516 | ETL.5390 | 40758992 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
116471883 | T3 EI DRUM-HIGGINS B010/106 REPAINT | 43738143 | DRUM-HIGGINS | B010/106 | ICS | E | Pre-2020_(9a) Other ignition related |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.945249 | 39.153 | ETL.4393 | 41162660 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes
116471943 | T2 EI HTCRK#1-WSTWD 020/398 RPR STRW | 43736797 | HAT CREEK #1-WESTWOOD | 020/398 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.265607 | 40.7347 | ETL.7030 | 40770737 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
116471975 | T2 EI PIT #1-COTTONWOOD 39/335 | 43879412 | PIT #1-COTTONWOOD | 039/335 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Internal Process | Circuit Based Scheduling | '-122.056317 | 40.6505 | ETL.5390 | 40762514 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
116471987 | T3 EI ELDORADO-MISOR FLT#1 3/24 REPAINT | 44585955 | ELDORADO-MISSOURI FLAT #1 | 003/024 | ICS | E | Pre-2020_(9a) Other ignition related |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.667428 | 38.7631 | ETL.1530 | 40751922 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes
116472004 | T2 EI RNDMTN-TBLMTN #2 079/322 INS GMKS | 44302501 | ROUND MTN-TABLE MTN #2 | 079/322 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.714977 | 39.6828 | ETL.6070 | 40670019 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
116472036 | T2 EI HTCRK#1-WSTWD 020/400 RPL SPLW | 43736797 | HAT CREEK #1-WESTWOOD | 020/400 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.264272 | 40.7336 | ETL.7030 | 40827479 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
116472073 | T2 EI PALERMO-WYANDOTTE 0/6 CANCEL | 44586169 | PALERMO-WYANDOTTE | 000/006 | ICX | E | Pre-2020_(9a) Other ignition related |  |  | CANCEL/CNCL | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.530622 | 39.4582 | ETL.4315 | 40815620 | Structure-Tower | Paint/Coating | Repaint | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense |  | Table Mountain
116472075 | T3 EI FULTON-PUEBLO 41/212 REPAINT | 43720980 | FULTON-PUEBLO | 041/212 | ICS | E | Pre-2020_(9a) Other ignition related |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.729755 | 38.497 | ETL.1600 | 40648150 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Lakeville |  |  | 2019-04-25
116472105 | T3 DI CARIBOU-PLERMO :12/095 BURIED MEMB | 44051418 | CARIBOU-PALERMO | :012/095 | ICQ | E | Pre-2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.274963 | 39.9723 | ETL.3190 | 40912114 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
116472114 | T3 DI CARIBOU-PALERMO :012/096 RPR STRT | 44051417 | CARIBOU-PALERMO | :012/096 | ICQ | E | Pre-2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.274824 | 39.9695 | ETL.3190 | 40910335 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
116472165 | T3 DI CARIBOU-PLRM :031/253 RPR FOND | 44051417 | CARIBOU-PALERMO | :031/253 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.463429 | 39.763 | ETL.3190 | 40668944 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
116472192 | T3 DI CARIBOU-PLRM :031/253 RPR STRT | 44051417 | CARIBOU-PALERMO | :031/253 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.463429 | 39.763 | ETL.3190 | 40668944 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
116472230 | T2 DI CARIBOU-PALERMO :28/231 REPL HRDT | 44069801 | CARIBOU-PALERMO | :028/231 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.449917 | 39.8027 | ETL.3190 | 40591569 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
116472232 | T2 DI CARIBOU-PALERMO :28/231 RMV FOOT |  | CARIBOU-PALERMO | :028/231 |  | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.449917 | 39.8027 | ETL.3190 | 40591569 | Structure-Tower | Soil | Remove |  |  |  |  | PEND | LC | TLX | Contract | Expense |  | Table Mountain
116472375 | T2 EI PLACER-GOLD HILL 1/13 PNT STRT | 44586177 | PLACER-GOLD HILL #1 | 001/013 | ICS | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP |  |  |  |  | Priority Bucket 9 | '-121.098103 | 38.8861 | ETL.3340 | 40906515 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Sacramento
116472433 | T3 DI CARIBOU-PLRM :031/257 RPL HRDT | 44051418 | CARIBOU-PALERMO | :031/257 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.468506 | 39.759 | ETL.3190 | 40826429 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
116472461 | T2 DI CARIBOU-PALERMO :27/221 FOND | 44069454 | CARIBOU-PALERMO | :027/221 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.432073 | 39.8164 | ETL.3190 | 40591568 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
116472543 | T2 EI HAT CRK #1-WSTWD 21/406 RPR STRW | 43736797 | HAT CREEK #1-WESTWOOD | 021/406 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.260183 | 40.7302 | ETL.7030 | 40667944 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
116472544 | T2 EI HAT CRK #1-WSTWD 20/401 RPR STRW | 43736797 | HAT CREEK #1-WESTWOOD | 020/401 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.263613 | 40.733 | ETL.7030 | 40816134 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
116472564 | T2 EI HAT CRK #1-WSTWD 20/399 CANCEL | 43736797 | HAT CREEK #1-WESTWOOD | 020/399 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  | CANCEL/CNCL | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.264958 | 40.7341 | ETL.7030 | 40759025 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
116472574 | T2 DI CARIBOU-PALERMO :012/099 RPR FOND | 44059014 | CARIBOU-PALERMO | :012/099 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.274973 | 39.9652 | ETL.3190 | 40910338 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
116472586 | T2 EI ROUND MTN-TM #1 079/322 INST GMKS | 44305409 | ROUND MTN-TABLE MTN #1 | 079/322 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.715343 | 39.6824 | ETL.6060 | 40670052 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Table Mountain |  |  | Yes
116472622 | T2 DI CARIBOU PLERMO :28/234 BURIED MEMB | 44069801 | CARIBOU-PALERMO | :028/234 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.451472 | 39.7995 | ETL.3190 | 40771764 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
116472634 | T2 EI OLM-NRTH TWR-CHRST 1/13 PNT STRS | 43752229 | OLEUM-NORTH TOWER-CHRISTIE | 001/013 | ICS | E | Pre-2020_(5b) On structure in bucket 5 | Budget Owner (Paint) |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.228899 | 38.0353 | ETL.3180 | 40644346 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  | Y - Prog Multi
116472683 | T3 DI CARIBOU-PLRM :031/256 REPNT STRT | 44051417 | CARIBOU-PALERMO | :031/256 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.467283 | 39.7595 | ETL.3190 | 40816593 | Structure-Tower | Paint/Coating | Repaint | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 543 | Table Mountain
116472784 | T2 EI TGR CRK-ELECT 010/083 RPR STRT | 43727728 | TIGER CREEK-ELECTRA | 010/083 | ICS | E | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.643348 | 38.369 | ETL.5780 | 40651017 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - Prog Multi
116472792 | T2 DI CARIBOU-PALERMO :012/101 RPR STRT | 44069583 | CARIBOU-PALERMO | :012/101 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.275177 | 39.9642 | ETL.3190 | 40910340 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
116472797 | T2 DI CARIBOU-PALERMO :012/101 RPR STUBS | 44069583 | CARIBOU-PALERMO | :012/101 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.275177 | 39.9642 | ETL.3190 | 40910340 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
116472816 | T2 DI CRBOU PLRMO :28/235 STRT RMV SOIL |  | CARIBOU-PALERMO | :028/235 |  | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.452416 | 39.7976 | ETL.3190 | 40758498 | Structure-Tower | Soil | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense |  | Table Mountain
116472871 | T2 EI RND MTN-TBL MTN #2 82/332 INS GMKS | 44302501 | ROUND MTN-TABLE MTN #2 | 082/332 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.695052 | 39.6471 | ETL.6070 | 40680197 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
116472940 | T2 EI PARKWAY-MORAGA 09/057 PNT TWR | 43683436 | PARKWAY-MORAGA | 009/057 | ICS | E | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.233292 | 38.0015 | ETL.5930 | 40676028 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay
116472960 | T2 DI CARIBOU-PALERMO :000/004 RPR FOND | 44062862 | CARIBOU-PALERMO | :000/004 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.153193 | 40.0836 | ETL.3190 | 41162787 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
116473048 | T2 EI OLM-NRTH TWR-CHRST 3/21 PNT STRS | 43752229 | OLEUM-NORTH TOWER-CHRISTIE | 003/021 | ICS | E | Pre-2020_(5b) On structure in bucket 5 | Budget Owner (Paint) |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.204908 | 38.0291 | ETL.3180 | 40579964 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  | Y - Prog Multi
116473137 | T2 EI HAT CREEK #1-WSTWD 19/366 RPR STRW | 43736797 | HAT CREEK #1-WESTWOOD | 019/366 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.287155 | 40.752 | ETL.7030 | 40601707 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
116473243 | T2 EI HAT CRK #1-WESTWD 33/636 RPR STRW | 43736797 | HAT CREEK #1-WESTWOOD | 033/636 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.104913 | 40.6024 | ETL.7030 | 40667962 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
116473298 | T2 EI HAT CREEK #1-WSTWD 19/367 RPL STRW | 31505374 | HAT CREEK #1-WESTWOOD | 019/367 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.286462 | 40.7515 | ETL.7030 | 40676303 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Need New ERTC
116473335 | T2 EI HAT CRK #1-WSTWD 19/365 RPL STRW | 31505374 | HAT CREEK #1-WESTWOOD | 019/365 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.287853 | 40.7526 | ETL.7030 | 40600214 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Need New ERTC
116473517 | T2 DI FORT ROSS-GUALALA 31/1 RPR GYWW | 43714438 | GUALALA-MONTE RIO | 031/001 | ICW | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.253394 | 38.5527 | ETL.6980 | 40601533 | Guy Wire-Wood | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-04-30
116473545 | T2 EI HT CRK #1-WESTWD 027/529 RPR GYWW | 43736797 | HAT CREEK #1-WESTWOOD | 027/529 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.18311 | 40.6579 | ETL.7030 | 40600238 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
116473582 | T3 DI CARIBOU-PLRM :032/258 RPL HRDT | 44051417 | CARIBOU-PALERMO | :032/258 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.471155 | 39.7577 | ETL.3190 | 40867978 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
116473720 | T2 EI HAT CRK #1-WSTWD 32/625 RPR GYWW | 31471926 | HAT CREEK #1-WESTWOOD | 032/625 | 93E | E | Pre-2020_(4) TD tag on high spread line |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.111218 | 40.6092 | ETL.7030 | 40592108 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  | Yes
116473726 | T2 EI HT CRK #1-WSTWD 026/518 RPL STRW | 31504344 | HAT CREEK #1-WESTWOOD | 026/518 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.189327 | 40.6647 | ETL.7030 | 40600235 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Need New ERTC
116473727 | T2 EI HT CRK #1 WESTWD 027/525 RPR STRW | 43736797 | HAT CREEK #1-WESTWOOD | 027/525 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.185418 | 40.6604 | ETL.7030 | 40817135 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
116473741 | T3 DI CARIBOU-PLRM :009/074 RPR FON | 44051418 | CARIBOU-PALERMO | :009/074 | ICQ | E | Pre-2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.264125 | 40.0035 | ETL.3190 | 40910316 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
116473743 | T3 DI CARIBOU-PLRM :009/074 RPR STRT | 44059014 | CARIBOU-PALERMO | :009/074 | ICQ | E | Pre-2020_(2) High fire spread TD |  |  | Check FDA | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.264125 | 40.0035 | ETL.3190 | 40910316 | Structure-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 543 | Table Mountain |  |  | Yes
116473761 | T2 EI HT CRK #1-WSTWD 028/554 RPR GYWW | 43736797 | HAT CREEK #1-WESTWOOD | 028/554 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.164383 | 40.6457 | ETL.7030 | 40827489 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
116473793 | T2 EI HT CRK #1-WSTWD 028/553 RPR GYWW | 43736797 | HAT CREEK #1-WESTWOOD | 028/553 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.165163 | 40.6462 | ETL.7030 | 40759039 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
116473813 | T3 DI CARIBOU-PALERM :31/252 RPR FOND | 44051418 | CARIBOU-PALERMO | :031/252 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.461095 | 39.7655 | ETL.3190 | 40674989 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
116473821 | T3 DI CARIBOU-PLRM :009/73 RPR STRT | 44051417 | CARIBOU-PALERMO | :009/073 | ICQ | E | Pre-2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.263216 | 40.0035 | ETL.3190 | 40910315 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
116473823 | T3 DI CARIBOU-PLRM :009/73 RPL INSS | 31468828 | CARIBOU-PALERMO | :009/073 | 93K | E | Pre-2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.263216 | 40.0035 | ETL.3190 | 40910315 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  | Yes
116473829 | T2 DI CARIBOU-PALERMO :013/107 RPL SPLS | 44304495 | CARIBOU-PALERMO | :013/107 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.285231 | 39.9593 | ETL.3190 | 40810977 | Splice-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain
116473872 | T3 DI CARIBOU PALERMO :30/242 RPR FOND | 44051418 | CARIBOU-PALERMO | :030/242 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.451805 | 39.7819 | ETL.3190 | 40702267 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
116473873 | T3 DI CARIBOU PALERMO :30/242 RPR INSS | 43659205 | CARIBOU-PALERMO | :030/242 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.451805 | 39.7819 | ETL.3190 | 40702267 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
116473876 | T3 DI CRBOU PLRMO :30/245 RPL INSS | 31426498 | CARIBOU-PALERMO | :030/245 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.452493 | 39.7774 | ETL.3190 | 40758500 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  | Yes
116473999 | T2 EI CARIBOU-PALERMO :20/163 PAINT STRT |  | CARIBOU-PALERMO | :020/163 | ICH | F | Pre-2020_(9a) Other ignition related |  |  | Check FDA | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.359437 | 39.9021 | ETL.3190 | 40738362 | Structure-Tower | Paint/Coating | Repaint |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 625 | Table Mountain
116474054 | T2 EI CARIBOU-PALERMO :20/162 RPR FOND | 44069455 | CARIBOU-PALERMO | :020/162 | ICQ | F | Pre-2020_(2) High fire spread TD |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.357958 | 39.9029 | ETL.3190 | 40738811 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
116474203 | T2 EI HAT CRK #1-WSTWD 19/375 RPL PL | 31505374 | HAT CREEK #1-WESTWOOD | 019/375 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.280927 | 40.747 | ETL.7030 | 40616895 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Need New ERTC
116474235 | T2 EI HAT CRK #1-WESTWD 34/655 RPR GYWW | 43736797 | HAT CREEK #1-WESTWOOD | 034/655 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.093897 | 40.5905 | ETL.7030 | 40667965 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
116474237 | T2 EI HTCRK#1-WSTWD 031/613 RPR GYWW | 43736797 | HAT CREEK #1-WESTWOOD | 031/613 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.11826 | 40.6168 | ETL.7030 | 40877608 | Ground Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
116474238 | T2 EI HTCRK#1-WSTWD 034/659 RPR GYWW | 43736797 | HAT CREEK #1-WESTWOOD | 034/659 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.091532 | 40.5881 | ETL.7030 | 40816155 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
116474336 | T2 DI SMARTVLL NICLAUS # 2 0/4 WASH INSS | 43852598 | SMARTVILLE-NICOLAUS #2 | 000/004 | ICD | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.3028 | 39.2071 | ETL.8000 | 44177580 | Insulator | Contaminated | Ground Wash | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 622 | Sacramento
116474594 | T3 DI CRBOU-PLRMO :035/286 REPL INSS | 31426498 | CARIBOU-PALERMO | :035/286 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.482382 | 39.7069 | ETL.3190 | 40813911 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  | Yes
116474700 | T3 DI CARIBOU-PALERMO :035/286 RPR FOND | 44051418 | CARIBOU-PALERMO | :035/286 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.482382 | 39.7069 | ETL.3190 | 40813911 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
116475174 | T2 EI PARKWAY-MORAGA 009/058 REPAINT | 43683436 | PARKWAY-MORAGA | 009/058 | ICS | E | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.232569 | 37.9998 | ETL.5930 | 40651053 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay
116475178 | T2 POE-RIO OSO 037/248 RPR INSS |  | POE-RIO OSO | 037/248 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.522667 | 39.4508 | ETL.5540 | 40867267 | Insulator-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
116475235 | T2 EI MTCLF-L PT #1 003/018 RPR FOND | 44277393 | METCALF-EL PATIO #1 | 003/018 | ICQ | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-121.804171 | 37.223 | ETL.2500 | 40867596 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 2
116475328 | T2 EI RND MTN-TBL MTN#2 079/321 INS GMKS | 44302501 | ROUND MTN-TABLE MTN #2 | 079/321 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.716734 | 39.6859 | ETL.6070 | 40589550 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
116475351 | T2 EI HAT CRK #1-WESTWD 18/360 RPL PL | 31495723 | HAT CREEK #1-WESTWOOD | 018/360 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.29132 | 40.7555 | ETL.7030 | 40868466 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
116475371 | T2 EI HTCRK #1-WSTWD 018/359 RPL STRW | 31505374 | HAT CREEK #1-WESTWOOD | 018/359 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.291997 | 40.756 | ETL.7030 | 40825575 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Need New ERTC
116475423 | T2 EI LM-NTH TWR-CHRST 002/014 RPR STRT | 43752229 | OLEUM-NORTH TOWER-CHRISTIE | 002/014 | ICS | E | Pre-2020_(5b) On structure in bucket 5 | Budget Owner (Paint) |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.224957 | 38.0347 | ETL.3180 | 40744890 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  | Y - Prog Multi
116475633 | T2 EI HAT CRK #1-WSTWD 18/355 RPL PL | 31426976 | HAT CREEK #1-WESTWOOD | 018/355 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.294783 | 40.7583 | ETL.7030 | 40667938 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain
116475680 | T2 EI PIT#1-COTTONWD 039/336 RPR STRT | 43755354 | PIT #1-COTTONWOOD | 039/336 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.057646 | 40.6489 | ETL.5390 | 40816946 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
116475688 | T3 EI DRUM-HIGGINS B010/107 CANCEL | 43738143 | DRUM-HIGGINS | B010/107 | ICS | E | Pre-2020_(9a) Other ignition related |  |  | CANCEL/CNCL | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.94692 | 39.155 | ETL.4393 | 41196118 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento
116475713 | T3 EI EGL RCK-FTN-SLVRD 020/086 REPAINT | 43713428 | EAGLE ROCK-FULTON-SILVERADO | 020/086 | ICS | E | Pre-2020_(9a) Other ignition related |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.608562 | 38.4989 | ETL.4392 | 41129388 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Lakeville |  |  | 2019-09-19
116475723 | T2 DRUM-RIO OSO #1 031/229 REPAINT STRT | 44304427 | DRUM-RIO OSO #1 | 031/229 | ICS | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.272175 | 39.0347 | ETL.1420 | 40864701 | Structure-Steel | Paint/Coating | Other | CONS crdy | CONS | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes
116475726 | T2 DI CARIBOU-PLRM :028/228 RPR JUMPER | 44070463 | CARIBOU-PALERMO | :028/228 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.442288 | 39.805 | ETL.3190 | 40878267 | Jumper-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain
116475772 | T2 DI CARIBOU-PLRM :028/228RPR STUBS | 44069801 | CARIBOU-PALERMO | :028/228 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.442288 | 39.805 | ETL.3190 | 40878267 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
116475839 | T2 EI PIT#1-COTTONWD 039/337 RPR FOND | 43637398 | PIT #1-COTTONWOOD | 039/337 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Internal Process | Circuit Based Scheduling | '-122.060957 | 40.6449 | ETL.5390 | 40817903 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | CONS | CONS | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
116475851 | T2 EI LKVL-GNC #1 IG002/009 RPR FOND | 43761675 | LAKEVILLE-IGNACIO #1 | IG002/009 | ICQ | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | WSIP | FSRP | [5 empty] | '-122.521366 | 38.1105 | ETL.4940 | 40868872 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  | 2019-08-06
116475894 | T2 EI LKVL-GNC IG002/010 RPR FOND | 43761675 | LAKEVILLE-IGNACIO #1 | IG002/010 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | WSIP | FSRP | [5 empty] | '-122.522131 | 38.1071 | ETL.4940 | 40602349 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  | 2019-08-06
116475931 | T2 EI LKVL-GNC #1 IG002/010 RPR STRT | 43761674 | LAKEVILLE-IGNACIO #1 | IG002/010 | ICX | E | Pre-2020_(9a) Other ignition related |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Coast | WSIP | FSRP | [5 empty] | '-122.522131 | 38.1071 | ETL.4940 | 40602349 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Lakeville |  |  | 2019-08-26
116475967 | T2 EI MTCLF-DNVL #1 003/017D RPR FOND |  | METCALF-EDENVALE #1 | 003/017D | ICQ | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-121.803579 | 37.2225 | ETL.2480 | 40742457 | Foundation/Concrete-Tower | Earth Covered Tower | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 3
116476056 | EI CORDELIA #2 TAP 003/066 RPR ANCW | 43743931 | CORDELIA #2 TAP | 003/066 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-122.152884 | 38.2504 | ETL.8184 | 40612471 | Anchor-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Sacramento |  |  | Yes
116476211 | T2 EI PARKWAY-MORAGA 10/060 PNT TWR | 43683436 | PARKWAY-MORAGA | 010/060 | ICS | F | Pre-2020_(9a) Other ignition related | Budget Owner (Paint) |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-122.229498 | 37.9948 | ETL.5930 | 40758934 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay
116476465 | T2 EI CARIBOU-PALERMO :006/051 RPR STRT | 44059014 | CARIBOU-PALERMO | :006/051 | ICQ | E | Pre-2020_(2) High fire spread TD |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.221517 | 40.0202 | ETL.3190 | 40910293 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
116480380 | T2 EI HT CRK #1-WSTWD 031/600 RPR CRSW | 43736797 | HAT CREEK #1-WESTWOOD | 031/600 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.128433 | 40.6232 | ETL.7030 | 40759041 | Crossarm-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
116480390 | T2 EI HT CRK #1-WSTWD 030/583 RPR GYWW | 43736797 | HAT CREEK #1-WESTWOOD | 030/583 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.141767 | 40.6315 | ETL.7030 | 40825592 | Guy Wire-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  | Yes
116481062 | T2 EI LM-NTH TWR-CHRST 002/018 RPR STRT | 43752229 | OLEUM-NORTH TOWER-CHRISTIE | 002/018 | ICS | E | Pre-2020_(5b) On structure in bucket 5 | Budget Owner (Paint) |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.213934 | 38.0325 | ETL.3180 | 40857757 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay
116481118 | T2 EI HT CRK #1-WSTWD 033/651 INS MRKW | 43736797 | HAT CREEK #1-WESTWOOD | 033/651 | ICW | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.096175 | 40.5931 | ETL.7030 | 40868494 | Marker (i.e. signs)-Wood | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
116481119 | T2 EI HT CRK #1-WSTWD 033/649 RPR GYWW | 43736797 | HAT CREEK #1-WESTWOOD | 033/649 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.09734 | 40.5943 | ETL.7030 | 40827600 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
116481180 | T2 EI HT CRK #1-WSTWD 033/651 RPL HRDW | 43736797 | HAT CREEK #1-WESTWOOD | 033/651 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.096175 | 40.5931 | ETL.7030 | 40868494 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
116481181 | T2 EI HT CRK #1-WSTWD 033/650 RPL HRDW | 43736797 | HAT CREEK #1-WESTWOOD | 033/650 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.096788 | 40.5936 | ETL.7030 | 40825597 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
116481187 | T2 EI LM-NTH TWR-CHRST 002/019 RPR STRT | 43752229 | OLEUM-NORTH TOWER-CHRISTIE | 002/019 | ICS | E | Pre-2020_(5b) On structure in bucket 5 | Budget Owner (Paint) |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.211346 | 38.0315 | ETL.3180 | 40856876 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay
116481230 | T2 EI CARIBOU-WESTWD 007/140B RPR GYWW | 43640851 | CARIBOU-WESTWOOD | 007/140 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.08781 | 40.1717 | ETL.6300 | 42624246 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
116481348 | T2NT EI STNSLS-MLNS SW ST-MTC #1 REPAINT | 43712830 | STANISLAUS-MELONES SS-MANTECA #1+ | 023/146 | ICS | F | Pre-2020_(3) On high spread structure | Budget Owner (Paint) |  |  | TR2 | <15D | Central | WSIP |  |  |  |  | Program | 2021 Paint took out of program due to future project to be removed with [REDACTED] | '-120.708163 | 37.9415 | ETL.3830 | 40756196 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - Prog Multi
116481495 | T2 DI CARIBOU-PALERMO :018/154 RMV SOIL | 44069597 | CARIBOU-PALERMO | :018/154 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.335942 | 39.9091 | ETL.3190 | 40753358 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
116481750 | T2 EI STNSLS-MNTC#2 015/087 RPL HRDT | 43712838 | STANISLAUS-MANTECA #2 | 015/087 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP |  |  |  | REJECT: WV received email stating this tag was submit in error. Corrected submission has not yet been received. |  |  | '-120.595814 | 38.0239 | ETL.3820 | 40803363 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - Prog Multi
116481836 | T2 EI HAT CRK #1-WSTWD 35/675 RPL PL | 31426976 | HAT CREEK #1-WESTWOOD | 035/675 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.082302 | 40.578 | ETL.7030 | 40770865 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain
116481889 | T2 EI HT CRK #1-WSTWD 026/503 RPR ANCW | 43736797 | HAT CREEK #1-WESTWOOD | 026/503 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.197668 | 40.6739 | ETL.7030 | 40759035 | Anchor-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
116481893 | T2 EI HAT CRK #1-WESTWD 32/631 RPR GYWW | 43736797 | HAT CREEK #1-WESTWOOD | 032/631 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.107808 | 40.6055 | ETL.7030 | 40825595 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
116481894 | T2 EI HT CRK #1-WSTWD 034/665 RPR GYWW | 43736797 | HAT CREEK #1-WESTWOOD | 034/665 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.088112 | 40.5843 | ETL.7030 | 40667967 | Ground Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
116481895 | T2 EI HT CRK #1-WSTWD 034/665 INS MRKW | 43736797 | HAT CREEK #1-WESTWOOD | 034/665 | ICW | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.088112 | 40.5843 | ETL.7030 | 40667967 | Marker (i.e. signs)-Wood | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
116481897 | T2 EI HT CRK #1-WSTWD 034/670 RPR STRW | 43736797 | HAT CREEK #1-WESTWOOD | 034/670 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.085213 | 40.5812 | ETL.7030 | 40877593 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
116481932 | EI HTCRK#1-WSTWD 026/508 RPL SPLW | 43736797 | HAT CREEK #1-WESTWOOD | 026/508 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-121.194835 | 40.6708 | ETL.7030 | 40616910 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
116481933 | T2 EI HT CRK #1-WSTWD 026/503 RPR GYWW | 43736797 | HAT CREEK #1-WESTWOOD | 026/503 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.197668 | 40.6739 | ETL.7030 | 40759035 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
116481935 | EI HAT CRK #1-WSTWD 26/505 RPR GYWW | 43736797 | HAT CREEK #1-WESTWOOD | 026/505 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-121.196537 | 40.6726 | ETL.7030 | 40816141 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
116481999 | T3 DI CARIBOU PALERMO :034/279 RMV SOIL | 44051418 | CARIBOU-PALERMO | :034/279 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.480326 | 39.7195 | ETL.3190 | 40867378 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
116482127 | T3 DI CARIBOU PALERMO :035/285 RPR FOND | 44051417 | CARIBOU-PALERMO | :035/285 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.482144 | 39.7083 | ETL.3190 | 40758502 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
116482213 | T3 DI CARIBOU PALERMO :036/289 RPR STRT | 44051417 | CARIBOU-PALERMO | :036/289 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.483288 | 39.7013 | ETL.3190 | 40867380 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
116482218 | T3 EI CARIBOU PALERMO :036/292 RPR FOND | 44051418 | CARIBOU-PALERMO | :036/292 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.483711 | 39.6987 | ETL.3190 | 40702278 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
116482233 | T2 DI POE RIO OSO 39/257 INST RPTS | 43878128 | POE-RIO OSO | 039/257 | ICB | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.518365 | 39.4294 | ETL.5540 | 40814853 | Raptor Guard-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 593 | Table Mountain |  |  | Yes
116482236 | T2 EI HT CRK #1-WSTWD 022/423 RPR GYWW | 43736797 | HAT CREEK #1-WESTWOOD | 022/423 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.248295 | 40.7206 | ETL.7030 | 40601613 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
116482238 | T2 EI HT CRK #1-WSTWD 022/422 RPR GYWW | 43736797 | HAT CREEK #1-WESTWOOD | 022/422 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.249035 | 40.7213 | ETL.7030 | 40600217 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
116482879 | T2 HT CRK #1-WSTWD 025/480 INS MRKW | 43736797 | HAT CREEK #1-WESTWOOD | 025/480 | ICW | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.211493 | 40.6868 | ETL.7030 | 40592100 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
116483266 | T2 EI CRTNA MENDO #1 26/125 FOND RPR | 43760958 | CORTINA-MENDOCINO #1 | 026/125 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.661167 | 39.0292 | ETL.1330 | 40750575 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  | 2019-05-08
116483899 | T2 EI HT CRK #1-WSTWD 027/532 RPR GYWW | 43736797 | HAT CREEK #1-WESTWOOD | 027/532 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.181282 | 40.6562 | ETL.7030 | 40656896 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
116484028 | T2 EI HT CRK #1-WSTWD 027/531 RPR GYWW | 43736797 | HAT CREEK #1-WESTWOOD | 027/531 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.181957 | 40.6566 | ETL.7030 | 40676354 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
116486948 | T2 EI CHRISTIE-SOBRANTE 11/065 CANCEL | 44598163 | CHRISTIE-SOBRANTE | 011/065 | ICI | E | Pre-2020_(4) TD tag on high spread line |  |  | CANCEL/CNCL | TR2 | LATE | Central | WSIP | FSRP |  |  | REJECT: Crew reported work not needed. Please confirm(approve) or reject if disagree. Recommend : Wash all insulators. |  |  | '-122.194254 | 37.9792 | ETL.1260 | 40761571 | Insulator | Contaminated | Helicopter Wash | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 626 | Bay |  | Y - 5
116487342 | T2 EI HTCRK #1-WSTWD 018/354 RPL STRW | 31505374 | HAT CREEK #1-WESTWOOD | 018/354 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.295552 | 40.7588 | ETL.7030 | 40701337 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Need New ERTC
116487343 | T2 EI HAT CRK #1-WESTWD 18/360 CANCEL | 43736796 | HAT CREEK #1-WESTWOOD | 018/360 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  | CANCEL/CNCL | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.29132 | 40.7555 | ETL.7030 | 40868466 | Crossarm-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
116487609 | EI STAN-NEWARK #1 093/616 RPR STRT |  | STANISLAUS-NEWARK #1 (12KV) | 093/619 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-121.88565 | 37.5729 | ETL.3850 | 40877299 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 5
116487982 | T2 EI RVILL-THRMLIT-TBL #3 1/4 RPL DAMP | 43739693 | MTN #3 (CDWR) | 001/004 | ICS | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.507875 | 39.5359 | ETL.6622 | 42580949 | Damper-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain
116488076 | T2 EI PALERMO-COLG C000/002 RPR COND | 43724331 | PALERMO-COLGATE | C000/002 | ICS | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.193937 | 39.3315 | ETL.5360 | 40683681 | Conductor-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento
116488109 | T2 EI PALERMO-COLG C000/002 COTTER KEY | 43724332 | PALERMO-COLGATE | C000/002 | ICQ | E | Pre-2020_(5) TD tag on other lines |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.193937 | 39.3315 | ETL.5360 | 40683681 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento
116488123 | T2 EI ROUND MTN-TM #1 077/314 RPR STRT | 44003357 | ROUND MTN-TABLE MTN #1 | 077/314 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Internal Process | Circuit Based Scheduling | '-121.729577 | 39.708 | ETL.6060 | 40761463 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
116488142 | T2 EI COLGATE-PALERMO 021/433 RPL SPLW | 43728970 | COLGATE-PALERMO | 021/433 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.510802 | 39.4581 | ETL.6500 | 40822490 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
116488289 | T2 EI IGNCIO ALT SLT #1 16/114 INTL GMKW |  | IGNACIO-ALTO-SAUSALITO #1 | 016/114 | ICW | F | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.503941 | 37.8577 | ETL.7160 | 40576349 | Guy Wire Mark /Indic-Wood | Missing | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
116488314 | T2 ORO-TH-TA MT #1 2/12 INST COTTER | 44630965 | MTN #1(CDWR) | 002/012 | ICS | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Internal Process |  | '-121.528307 | 39.5467 | ETL.6621 | 42580635 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
116488614 | T2 EI IGNACIO-SAN RAF #1 7/039 RMV VEGN | 43715549 | IGNACIO-SAN RAFAEL #1 | 007/039 | ICQ | E | Pre-2020_(5b) On structure in bucket 5 |  |  | Likely veg | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.494875 | 37.9845 | ETL.1850 | 40863149 | Structure-Steel | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLV | Vegetation | Expense | 628 | Lakeville
116488831 | T2 DI CARIBOU-PALERMO :009/072 RPR FOND |  | CARIBOU-PALERMO | :009/072 |  | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.258867 | 40.0049 | ETL.3190 | 40910314 | Foundation/Concrete-Tower | Earth Covered Tower | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense |  | Table Mountain |  |  | Yes
116489057 | T2 EI RV-THRL-TBL MT #1 004/17 REPL INSS | 31528386 | MTN #1(CDWR) | 004/017 | 93K | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.550773 | 39.5469 | ETL.6621 | 42580646 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  | Yes
116490031 | T3 EI CARIBOU-PALERMO :008/064 REPL HRDT | 44051418 | CARIBOU-PALERMO | :008/064 | ICQ | E | Pre-2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.239441 | 40.0064 | ETL.3190 | 40910306 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
116490032 | T3 EI CARIBOU-PALERMO :008/064 RPL HRDT | 44051418 | CARIBOU-PALERMO | :008/064 | ICQ | E | Pre-2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.239441 | 40.0064 | ETL.3190 | 40910306 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
116491927 | T2 EI OLM-NTH TWR-CHRST A03/027 PAINT | 43752229 | OLEUM-NORTH TOWER-CHRISTIE | A03/027 | ICS | E | Pre-2020_(5b) On structure in bucket 5 | Budget Owner (Paint) |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.201786 | 38.0173 | ETL.3180 | 40818337 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay
116492256 | T2 EI RND MTN-TBL M #2 077/314 RPR STRT | 43755806 | ROUND MTN-TABLE MTN #2 | 077/314 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Internal Process | Circuit Based Scheduling | '-121.729021 | 39.7081 | ETL.6070 | 40765458 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
116492432 | T3 DI CARIBOU-PALERMO :008/063 RPR STRT | 44051418 | CARIBOU-PALERMO | :008/063 | ICQ | E | Pre-2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.238849 | 40.0064 | ETL.3190 | 40910305 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
116492438 | T3 DI CARIBOU-PALERMO :008/063 RPR STRT | 44051418 | CARIBOU-PALERMO | :008/063 | ICQ | E | Pre-2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.238849 | 40.0064 | ETL.3190 | 40910305 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
116492462 | T3 DI CARIBOU-PALERMO :008/063 REPL CONS |  | CARIBOU-PALERMO | :008/063 | 93C | E | Pre-2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.238849 | 40.0064 | ETL.3190 | 40910305 | Conductor-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLX | Contract | Capital | 531 | Table Mountain |  |  | Yes
116492467 | T3 DI CARBOU-PALERMO :008/063 REPNT STRS | 44051418 | CARIBOU-PALERMO | :008/063 | ICQ | E | Pre-2020_(3) On high spread structure | Budget Owner (Paint) |  | Check FDA | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.238849 | 40.0064 | ETL.3190 | 40910305 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
116492551 | T2 EI MILLBRAE-SNTH LNE 14/98 RPR STRT | 44278027 | MILLBRAE-SNEATH LANE | 014/098 | ICS | E | Pre-2020_(5) TD tag on other lines |  |  | Likely MAT error - delink to correct | TR2 | LATE | Central | WSIP | [6 empty] | '-122.445905 | 37.6219 | ETL.7570 | 41162747 | Structure-Tower | Anti-Climbing Guard | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  | Y - 3 | SFPUC
116492575 | T2 EI PITTSBURG-TESLA #1 016/073 HRDT | 44238805 | PITTSBURG-TESLA #1 | 016/073 | ICS | E | Pre-2020_(5) TD tag on other lines |  |  | Likely MAT error - delink to correct | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-121.72794 | 37.8908 | ETL.5510 | 40650652 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 5
116492817 | T2 EI CARIBOU #2 17/025 RPR GYWW | 43742132 | CARIBOU #2 | 017/025 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.062773 | 40.022 | ETL.6280 | 40768837 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
116492961 | T2 EI CARIBOU #2 17/026 RPL SPLW | 43742136 | CARIBOU #2 | 017/026 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.06235 | 40.0214 | ETL.6280 | 40826407 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
116493267 | T2 EI OLM-NRTH TWR-CHRSTE A004/029 RPNT | 43752229 | OLEUM-NORTH TOWER-CHRISTIE | A04/029 | ICS | E | Pre-2020_(5b) On structure in bucket 5 | Budget Owner (Paint) |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.20133 | 38.0146 | ETL.3180 | 40857608 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay
116493357 | T2 EI CARIBOU #2 15/020 INST STEP | 43742127 | CARIBOU #2 | 015/020 | ICS | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.102045 | 40.018 | ETL.6280 | 40614875 | Hardware-Steel | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
116493735 | T2 EI POE-RIO OSO 027/174 RMV NEST | 43737420 | POE-RIO OSO | 027/174 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.519979 | 39.6103 | ETL.5540 | 40762685 | Structure-Steel | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Table Mountain |  |  | Yes
116493796 | T2 EI POE-RIO OSO 027/174 SPLS | 43737420 | POE-RIO OSO | 027/174 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.519979 | 39.6103 | ETL.5540 | 40762685 | Splice-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
116493799 | T2 EI OLM-NTH TWR-CHRST A03/026 PAINT | 43752229 | OLEUM-NORTH TOWER-CHRISTIE | A03/026 | ICS | E | Pre-2020_(5b) On structure in bucket 5 | Budget Owner (Paint) |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.20233 | 38.0205 | ETL.3180 | 40804617 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay
116493893 | T3 DI CARIBOU-PALERMO :034/273 RPR STRS | 44051418 | CARIBOU-PALERMO | :034/273 | ICQ | E | Pre-2020_(2) High fire spread TD |  |  | Check FDA | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.478516 | 39.7306 | ETL.3190 | 40668936 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
116493937 | T2 EI OLM-N TWR-CH A3/26 HANGER GUEST | 44323394 | OLEUM-NORTH TOWER-CHRISTIE | A03/026 | ICS | E | Pre-2020_(5) TD tag on other lines |  | TLN/TLQ error |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.20233 | 38.0205 | ETL.3180 | 40804617 | Hardware-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  | Y - 4
116494207 | T3 DI CARIBOU PALERMO :33/272 RPR STRT | 44051418 | CARIBOU-PALERMO | :033/272 | ICQ | E | Pre-2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.478424 | 39.7311 | ETL.3190 | 40702276 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
116494807 | T2 DI CARIBOU #2 015/023 INS GYWW | 43742132 | CARIBOU #2 | 015/023 | ICW | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.100345 | 40.017 | ETL.6280 | 40656556 | Guy Wire-Wood | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
116494944 | T2 EI PITTSBURG-TESLA #1 017/079 HRDT |  | PITTSBURG-TESLA #1 | 017/079 | ICQ | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-121.706942 | 37.8775 | ETL.5510 | 40862428 | Hardware-Tower | Missing | Install |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 5
116495010 | T2 EI PINE GROVE TAP 002/049 INS GYWW | 43687879 | PINE GROVE TAP | 002/049 | ICW | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.653296 | 38.4121 | ETL.8351 | 40596137 | Guy Wire-Wood | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 3
116495826 | T2 EI METCALF-EL PATIO #1 003/015 REPAIN | 43753585 | METCALF-EL PATIO #1 | 003/015 | ICS | F | Pre-2020_(9a) Other ignition related | Budget Owner (Paint) |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-121.794203 | 37.2217 | ETL.2500 | 40757994 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay
116496057 | T2 EI BAHIA-MORAGA 12/071 PNT TWR | 43683412 | BAHIA-MORAGA | 012/071 | ICS | E | Pre-2020_(5b) On structure in bucket 5 | Budget Owner (Paint) |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.233619 | 38.0051 | ETL.4340 | 40740004 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  | Y - 3 | 2019-03-22
116496141 | T2 EI CARIBOU #2 017/029 RPL SPLW | 43742127 | CARIBOU #2 | 017/029 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.061624 | 40.0201 | ETL.6280 | 40875420 | Splice-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
116496184 | T2 EI VASONA-METCALF 5/025 PRR FOND |  | VASONA-METCALF | 005/025 | ICQ | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-121.838709 | 37.2274 | ETL.5932 | 40764929 | Foundation/Concrete-Tower | Earth Covered Tower | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog Multi
116496230 | T2 EI VASONA-METCALF 5/25 RPR STRT |  | VASONA-METCALF | 005/025 | ICQ | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-121.838709 | 37.2274 | ETL.5932 | 40764929 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog Multi
116496409 | T2 EI MRR BY-SN LS OBSP #1 0/3 REPAINT | 43751755 | MORRO BAY-SAN LUIS OBISPO #1 | 000/003 | ICS | F | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | South | WSIP | FSRP | [5 empty] | '-120.850948 | 35.3766 | ETL.2810 | 40650851 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Pismo Beach |  | Y - 12 | 2019-04-08
116497177 | T2 EI HAT CREEK #1-WSTWD 22/436 RPR STRW | 43736797 | HAT CREEK #1-WESTWOOD | 022/436 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.239995 | 40.713 | ETL.7030 | 40770741 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
116497262 | T2 EI HAT CRK #1-WSTWD 22/431 RPR STRW | 43736797 | HAT CREEK #1-WESTWOOD | 022/431 | ICW | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.243248 | 40.7159 | ETL.7030 | 40876186 | Structure-Wood | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
116497263 | T2 EI HT CRK #1-WSTWD 24/477 RPR CRSW | 43736797 | HAT CREEK #1-WESTWOOD | 024/477 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.213393 | 40.6886 | ETL.7030 | 40825584 | Crossarm-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
116497382 | T2NT EI RND MTN-TBL M #2 74/305 INS MRKS | 44302501 | ROUND MTN-TABLE MTN #2 | 074/305 | ICS | E | Pre-2020_(4b) On structure in bucket 4 | Superintendent Approved work efficiency |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.74984 | 39.7443 | ETL.6070 | 40765376 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Table Mountain |  |  | Yes
116497461 | T2 EI OLEUM-G #2 0/9 RPL INSS | 31508069 | OLEUM-G #2 | 000/009 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-122.2388294 | 38.0393 | ETL.3160 | 40893373 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - 8
116497562 | T2 EI PITTSBURG-CLMB STL 3/19 REPL HRDS | 44609766 | PITTSBURG-COLUMBIA STEEL | 003/019 | ICS | E | Pre-2020_(5) TD tag on other lines |  | Hanger Plates Within Tag; separate |  | TR2 | LATE | Central | WSIP | [6 empty] | '-121.903161 | 37.9932 | ETL.3300 | 40872692 | Hardware-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - Prog Multi
116497841 | T2 EI HT CRK #1-WSTWD 36/695 RPL STRW | 31426976 | HAT CREEK #1-WESTWOOD | 036/695 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.07107 | 40.5659 | ETL.7030 | 40751788 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain
116498015 | T2 EI HAT CREEK #1-WSTWD 23/444 RPR STRW | 43736797 | HAT CREEK #1-WESTWOOD | 023/444 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.234585 | 40.708 | ETL.7030 | 40656890 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
116498023 | T2 EI HAT CREEK #1-WSTWD 23/442 RPR STRW | 43736797 | HAT CREEK #1-WESTWOOD | 023/442 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.236194 | 40.7095 | ETL.7030 | 40592097 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
116498084 | T2 EI HAT CREEK #1-WSTWD 23/445 RPR STRW | 43736797 | HAT CREEK #1-WESTWOOD | 023/445 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.233885 | 40.7074 | ETL.7030 | 40770862 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
116498091 | T2 EI HAT CRK #1-WSTWD 17/328 RPR SPLC | 43736796 | HAT CREEK #1-WESTWOOD | 017/328 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.313593 | 40.7735 | ETL.7030 | 40676295 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
116498094 | T2 EI HAT CREEK #1-WSTWD 23/447 CANCEL | 43736797 | HAT CREEK #1-WESTWOOD | 023/447 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  | CANCEL/CNCL | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.232648 | 40.7062 | ETL.7030 | 40827485 | Anchor-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
116498129 | T2 EI HAT CREEK #1-WSTWD 19/383 RPR STRW | 43736797 | HAT CREEK #1-WESTWOOD | 019/383 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.276137 | 40.7431 | ETL.7030 | 40816132 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
116498148 | T2 EI RND MT-TBL MT #2 074/304 INST GMKS | 44302501 | ROUND MTN-TABLE MTN #2 | 074/304 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.751526 | 39.7474 | ETL.6070 | 40756244 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
116498207 | T2 EI HAT CRK #1-WSTWD 23/454 RPR STRW | 43736797 | HAT CREEK #1-WESTWOOD | 023/454 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.22812 | 40.7021 | ETL.7030 | 40656892 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
116498208 | T2 EI HAT CREEK #1-WSTWD 23/448 RPR STRW | 43736797 | HAT CREEK #1-WESTWOOD | 023/448 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.232052 | 40.7056 | ETL.7030 | 40816136 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
116498262 | T2 EI ROUND MTN-TM #1 74/304 RPL GYMK | 44305409 | ROUND MTN-TABLE MTN #1 | 074/304 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  | TLN/TLQ error |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.752028 | 39.7473 | ETL.6060 | 40764703 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Table Mountain |  |  | Yes
116498477 | T2 EI HT CRK #1-WSTWD 35/685 RPL STRW | 31426976 | HAT CREEK #1-WESTWOOD | 035/685 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.076825 | 40.5721 | ETL.7030 | 40758921 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain
116498502 | T2 EI HT CRK #1-WSTWD 26/512 RPL STRW | 31504344 | HAT CREEK #1-WESTWOOD | 026/512 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.192853 | 40.6685 | ETL.7030 | 40759206 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Need New ERTC
116498503 | T2 EI HT CRK #1-WSTWD 26/511 RPL STRW | 31504344 | HAT CREEK #1-WESTWOOD | 026/511 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.19338 | 40.6692 | ETL.7030 | 40667950 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Need New ERTC
116498621 | T2 EI HAT CRK #1-WSTWD 23/447 RPR GYWW | 43736797 | HAT CREEK #1-WESTWOOD | 023/447 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.232648 | 40.7062 | ETL.7030 | 40827485 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
116498835 | T2 DI BAHIA-MORAGA 16/93 INS HRDT | 43683410 | BAHIA-MORAGA | 016/093 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.203898 | 37.9596 | ETL.4340 | 40740005 | Hardware-Tower | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 5
116499456 | T2 EI JEFRSON-HLSDL JCT 0/3 RPR INSS | 43752125 | JEFFERSON-HILLSDALE JCT | 000/003 | ICS | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.287319 | 37.4596 | ETL.7190 | 40653159 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - 2 | SMCPD
116499660 | T2 EI JEFRSON-HLSDLE JCT 0/4 RPR INSS | 43752125 | JEFFERSON-HILLSDALE JCT | 000/004 | ICS | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.287928 | 37.4614 | ETL.7190 | 40755213 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - 2 | SMCPD
116499786 | T2 EI JEFFRSON-HLLSDLE JCT 1/7 RPR INSS | 43752125 | JEFFERSON-HILLSDALE JCT | 001/007 | ICS | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-122.291131 | 37.4703 | ETL.7190 | 40812553 | Conductor-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - 3
116499877 | T3 EI PIT #1-COTTONWOOD 028/234 PNT STRT | 43735854 | PIT #1-COTTONWOOD | 028/234 | ICS | F | Pre-2020_(9a) Other ignition related |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.950614 | 40.7771 | ETL.5390 | 40759682 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
116499936 | EI HAT CRK #1-WESTWD 048/935 RPL POLE | 31426976 | HAT CREEK #1-WESTWOOD | 048/935 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-121.018443 | 40.3973 | ETL.7030 | 40701262 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain
116500139 | T2 EI JEFFERSON-STANFORD 0/05 RPR GYWW | 43752127 | JEFFERSON-STANFORD (NO FLY) | 000/005 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.280174 | 37.4598 | ETL.7220 | 40767172 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Bay |  | Y - 6 | EPNP
116500147 | T2 EI JEFFERSON-STANFORD 0/05 RPL ANCW | 31504281 | JEFFERSON-STANFORD (NO FLY) | 000/005 | 93E | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.280174 | 37.4598 | ETL.7220 | 40767172 | Anchor-Wood | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Bay |  | Y - 6 | EPNP
116500328 | T2 EI JEFRSON-HLSDL JCT 0/5 REPL INSS | 31453027 | JEFFERSON-HILLSDALE JCT | 000/005 | 93K | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-122.2887529 | 37.464 | ETL.7190 | 40783987 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - 2 | SMCPD
116500338 | T2 EI JEFRSON-HLSDL JCT 0/5 REPL HRDS | 44218329 | JEFFERSON-HILLSDALE JCT | 000/005 | ICS | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.28874 | 37.464 | ETL.7190 | 40755137 | Hardware-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - 2 | SMCPD
116500402 | T2 EI CRBRY S S-RND MTN 27/220A REPAINT | 43897848 | CARBERRY SW STA-ROUND MTN | 027/220A | ICS | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.936552 | 40.7924 | ETL.5410 | 40577033 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
116500410 | T2 EI CHRISTIE-FRANKLIN #2 0/12 RPR GYWW | 43753117 | CHRISTIE-FRANKLIN #2 | 000/012 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.225912 | 38.0041 | ETL.6360 | 40581068 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Bay |  | Y - 2
116500450 | T2 EI SMRTVLLE-NICLS #2 1/25 RPR GYWS | 43760145 | SMARTVILLE-NICOLAUS #2 | 001/025 | ICS | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.301457 | 39.1925 | ETL.8000 | 44177820 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento
116500563 | T2 EI ROUND MTN-TM #1 74/305 RPL GYMK | 44305409 | ROUND MTN-TABLE MTN #1 | 074/305 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  | TLN/TLQ error |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.750201 | 39.7439 | ETL.6060 | 40756160 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Table Mountain |  |  | Yes
116500583 | T2 EI MALIN-ROUND MTN#2 61/305 REPAINT | 43621093 | MALIN-ROUND MTN #2 | 061/305 | ICQ | F | Pre-2020_(1b) Lines with special commitments |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.663711 | 41.1947 | ETL.6020 | 40759606 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
116500845 | T2 EI POE-RIO OSO 027/178 RPR INSS | 43737420 | POE-RIO OSO | 027/178 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.522617 | 39.601 | ETL.5540 | 40867261 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
116500940 | EI OLEUM-G #1 000/005 RPNT TWR | 43752220 | OLEUM-G #1 | 000/005 | ICS | E | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) |  |  |  | LATE | Central | WSIP | [6 empty] | '-122.249283 | 38.0411 | ETL.3150 | 40746013 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  | Y - 8
116501725 | T2 PF SMARTVILLE-NICLS #2 2/46 RPR GYWW | 43760146 | SMARTVILLE-NICOLAUS #2 | 002/046 | ICS | E | Pre-2020_(5) TD tag on other lines |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.308226 | 39.1787 | ETL.8000 | 44179467 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Sacramento
116501853 | T2 EI MALIN-ROUND MTN #2 61/306 REPAINT | 43621093 | MALIN-ROUND MTN #2 | 061/306 | ICQ | F | Pre-2020_(1b) Lines with special commitments |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.665552 | 41.1924 | ETL.6020 | 40818808 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
116502480 | T2 DI CARIBOU-PALERMO 006/054 RPL HRDT | 44069597 | CARIBOU-PALERMO | 006/054 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.540063 | 39.5414 | ETL.3190 | 40758611 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
116502749 | T2 EI JEFFERSON-STNFRD 2/47 RPR GYWW | 43752127 | JEFFERSON-STANFORD (NO FLY) | 002/047 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.256905 | 37.465 | ETL.7220 | 40694686 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Bay |  | Y - Prog Multi | 2019-07-31
116503045 | T2 EI HAT CRK #1-WESTWD 040/780 RPL SPLW | 43736798 | HAT CREEK #1-WESTWOOD | 040/780 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.030857 | 40.5095 | ETL.7030 | 40770769 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
116503079 | T2 EI HAT CRK #1-WESTWD 040/780 REFRAME | 31471926 | HAT CREEK #1-WESTWOOD | 040/780 | 93E | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.0308704 | 40.5095 | ETL.7030 | 40802346 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  | Yes
116503414 | EI HAT CRK #1-WSTWD 048/925 RPL STRW | 31509530 | HAT CREEK #1-WESTWOOD | 048/925 | 70Y | E | Pre-2020_(2) High fire spread TD |  |  |  |  | LATE | North Valley | WSIP |  |  |  |  | Access Issues | 2021 - Snow . FSR 12/2020 | '-121.019675 | 40.4042 | ETL.7030 | 40675746 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
116503497 | EI HAT CRK #1-WSTWD 048/924 RPR STRW | 43736798 | HAT CREEK #1-WESTWOOD | 048/924 | ICW | E | Pre-2020_(2) High fire spread TD |  |  |  |  | LATE | North Valley | WSIP |  |  |  |  | Access Issues | 2021 - Snow. FSR 7/2020 | '-121.019768 | 40.405 | ETL.7030 | 40591894 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
116503506 | T3NT EI PRDISE-TBL MTN 021/167 MRK BALL | 43727174 | PARADISE-TABLE MTN | 021/167 | ICS | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.591285 | 39.6921 | ETL.4316 | 44712238 | Marker (i.e. signs)-Steel | No Good/Out of Stdrd | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
116503520 | EI HAT CRK #1-WSTWD 048/924 RPR GYWW | 43736798 | HAT CREEK #1-WESTWOOD | 048/924 | ICW | E | Pre-2020_(2) High fire spread TD |  |  |  |  | LATE | North Valley | WSIP |  |  |  |  | Access Issues | 2021 - Snow . FSR 7/2020 | '-121.019768 | 40.405 | ETL.7030 | 40591894 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
116503581 | T2 EI LOS ESTEROS-MET 003/016 PAINT | 43753289 | LOS ESTEROS-METCALF | 003/016 | ICS | E | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-121.724722 | 37.27 | ETL.5353 | 40811285 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay
116503745 | T2 EI MONTA VISTA-J #1 06/24 RPL INSS | 31443073 | MONTA VISTA-JEFFERSON #1 | 006/024 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-122.1760102 | 37.3307 | ETL.5220 | 40782415 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - 7
116503959 | EI HAT CRK #1-WSTWD 049/944 COA | 43736798 | HAT CREEK #1-WESTWOOD | 049/944 | ICW | E | Pre-2020_(2) High fire spread TD |  |  |  |  | LATE | North Valley | WSIP |  |  |  |  | Access Issues | 2021 - Snow . FSR 12/2020. Work is complete. Tag to be cancelled | '-121.017228 | 40.3902 | ETL.7030 | 40599863 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
116504082 | EI STNSLS-NWRK #1 092/613 RPR STR |  | STANISLAUS-NEWARK #1 (12KV) | 092/613 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-121.87434 | 37.5814 | ETL.3850 | 40669429 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 6 | SFPUC
116504154 | T2 EI BELDEN TAP 000/001C RPR CONS | 43742043 | BELDEN TAP | 000/001C | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.250771 | 40.0077 | ETL.4441 | 43198034 | Conductor-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain
116504580 | T2 EI OLEUM-G #1 001/012 RPR FOND | 43752139 | OLEUM-G #1 | 001/012 | ICQ | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-122.234041 | 38.0362 | ETL.3150 | 40688523 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 8
116504946 | T2 EI TESLA-METCALF 008/033 RPR SPLS | 43753282 | TESLA-METCALF | 008/033 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-121.593192 | 37.5918 | ETL.6110 | 40659433 | Splice-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - Prog Multi
116504954 | T2 EI CTNWD-BNTN #2 014/125 RPR GYWW | 43939217 | COTTONWOOD-BENTON #2 | 014/125 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.39459 | 40.56 | ETL.6650 | 44560580 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
116504965 | T2NT EI TESLA-METCALF 008/033 INS GYWS |  | TESLA-METCALF | 008/033 | ICS | F | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-121.593192 | 37.5918 | ETL.6110 | 40659433 | Guy Wire Mark /Indic-Steel | Missing | Install |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  | Y - 3
116505057 | HAMMER-COUNTRY CLUB C3/69 STUB POLE | 43691346 | HAMMER-COUNTRY CLUB (NO FLY) | C003/069 | GAR | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | Central | Non-WSIP | [6 empty] | '-121.286381 | 37.9914 | ETL.7010 | 40652366 | Structure-Wood | Rotten | Stub | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 586 | Victor |  | Released
116505059 | HAMMER-COUNTRY CLUB B3/76 STUB POLE | 43691346 | HAMMER-COUNTRY CLUB (NO FLY) | B003/076 | GAR | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | Central | Non-WSIP | [6 empty] | '-121.27947 | 38.0307 | ETL.7010 | 42634555 | Structure-Wood | Rotten | Stub | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 586 | Victor |  | Y - Prog Multi
116505376 | EI HAT CRK #1-WSTWD 048/924 REFRAME | 31471609 | HAT CREEK #1-WESTWOOD | 048/924 | 93E | E | Pre-2020_(2) High fire spread TD |  |  |  |  | LATE | North Valley | WSIP |  |  |  |  | Access Issues | 2021 - Snow . FSR 12/2020 | '-121.0197813 | 40.405 | ETL.7030 | 40617470 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  | Yes
116577574 | T2 EI PIT #7 TAP 003/026 RPR GYWW | 43877044 | PIT #7 TAP | 003/026 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.937735 | 40.8259 | ETL.5442 | 44553659 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain
116577965 | T3 DI CRBOU PLRMO :32/260 RPR STRT | 43725390 | CARIBOU-PALERMO | :032/260 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.474651 | 39.7549 | ETL.3190 | 40599300 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
116578064 | T2 EI KONOCTI-MIDDLETOWN 013/004 INSW | 43761672 | KONOCTI-MIDDLETOWN | 013/004 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.590443 | 38.7663 | ETL.6380 | 40769709 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-05-29
116578116 | T2 EI KONOCTI-MIDDLETWN 015/009 RPR STRW | 43761672 | KONOCTI-MIDDLETOWN | 015/009 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.56713 | 38.7951 | ETL.6380 | 40875482 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-07-26
116578123 | T3 DI CRBOU PLRMO :034/274 SPLS RPL | 43659205 | CARIBOU-PALERMO | :034/274 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.478839 | 39.7286 | ETL.3190 | 40758638 | Splice-Steel | No Good/Out of Stdrd | Replace | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
116578126 | T3 DI CRBOU PLRMO :034/274 STRT SOIL |  | CARIBOU-PALERMO | :034/274 |  | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.478839 | 39.7286 | ETL.3190 | 40758638 | Structure-Tower | Soil | Remove |  |  |  |  | PEND | LC | TLX | Contract | Expense |  | Table Mountain |  |  | Yes
116578333 | T2 VALLEY SPRINGS-CLAY - 60 _012/164 HS | 43848457 | VALLEY SPRINGS-CLAY | 012/164 | ICW | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | Central | Non-WSIP | [6 empty] | '-120.890535 | 38.2778 | ETL.8264 | 40904774 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog Multi
116578422 | T2 EI VLLY SPRINGS-CLAY 006/085 RPR GYWW | 43687883 | VALLEY SPRINGS-CLAY | 006/085 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.833081 | 38.2099 | ETL.8264 | 40904721 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog Multi
116578484 | T2 EI TESLA-METCALF 032/133 RPR STRT |  | TESLA-METCALF | 032/133 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-121.726393 | 37.2656 | ETL.6110 | 40651772 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 3
116578492 | T2 VALLEY SPRINGS-CLAY 11/157 INST MRKW | 43848456 | VALLEY SPRINGS-CLAY | 011/157 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | Central | Non-WSIP | [6 empty] | '-120.883769 | 38.2745 | ETL.8264 | 41196644 | Marker (i.e. signs)-Steel | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - Prog Multi
116578495 | T2 EI KONOCTI-MIDDLETOWN 016/013 GYWW | 43761672 | KONOCTI-MIDDLETOWN | 016/013 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.573239 | 38.8077 | ETL.6380 | 40650686 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-05-29
116578509 | T2 EI DRM-HGGNS 24/186 INSTL HRDT | 43687117 | DRUM-HIGGINS | 024/186 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.122275 | 39.0941 | ETL.4393 | 40594579 | Hardware-Tower | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento |  |  | Yes
116578542 | T2 EI KONOCTI-MIDDLETOWN 016/014 GYWW | 43761672 | KONOCTI-MIDDLETOWN | 016/014 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.573231 | 38.8085 | ETL.6380 | 40752528 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-05-29
116578685 | T2 EI BRY SW ST-RND MTN 26/211 RPL INSS | 31502961 | CARBERRY SW STA-ROUND MTN | 026/211 | 93K | F | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.9189922 | 40.797 | ETL.5410 | 40621072 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  | Yes
116578800 | EI HAT CREEK #1-WESTWD 049/957 RPR SPLW | 43736798 | HAT CREEK #1-WESTWOOD | 049/957 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-121.015575 | 40.3804 | ETL.7030 | 40656682 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
116578809 | EI HAT CREEK #1-WESTWD 049/956 REFRAME | 31471609 | HAT CREEK #1-WESTWOOD | 049/956 | 93E | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-121.01565 | 40.3809 | ETL.7030 | 40701264 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  | Yes
116578908 | T2 EI CARIBOU-PALERMO :09/070 BENT MEMB | 44059014 | CARIBOU-PALERMO | :009/070 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.254842 | 40.0061 | ETL.3190 | 40910312 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
116578950 | EI HAT CREEK #1-WESTWD 049/948 COA | 43736798 | HAT CREEK #1-WESTWOOD | 049/948 | ICW | E | Pre-2020_(2) High fire spread TD |  |  |  |  | LATE | North Valley | WSIP |  |  |  |  | Access Issues | 2021 - Snow . | '-121.016715 | 40.3871 | ETL.7030 | 40770781 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
116578969 | EI HAT CREEK #1-WESTWD 049/951 REFRAME | 31471609 | HAT CREEK #1-WESTWOOD | 049/951 | 93E | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-121.01634 | 40.3847 | ETL.7030 | 40825620 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  | Yes
116578989 | T3 EI SAN RAMON-MORAGA 002/014 REPAINT | 43715783 | SAN RAMON-MORAGA | 002/014 | ICS | F | Pre-2020_(9a) Other ignition related | Budget Owner (Paint) |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-121.971073 | 37.7239 | ETL.5660 | 40857926 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay
116578995 | T2 EI PLACER-DEL MAR 002/058 RPL POLE | 31498224 | PLACER-DEL MAR | 002/058 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.117367 | 38.8744 | ETL.7800 | 40815283 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
116579007 | T2 EI TESLA-METCALF 008/031 RPR STRT |  | TESLA-METCALF | 008/031 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-121.591356 | 37.5981 | ETL.6110 | 40581119 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 3
116579112 | T2 EI CARIBOU-PALERMO :004/033 BENT MEMB | 44070463 | CARIBOU-PALERMO | :004/033 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.208362 | 40.051 | ETL.3190 | 40910277 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Table Mountain
116579750 | T2 EI BRY SW ST-RND MTN 25/204 RPL INSS | 31502961 | CARBERRY SW STA-ROUND MTN | 025/204 | 93K | F | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.9028642 | 40.8013 | ETL.5410 | 40785136 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  | Yes
116579950 | T2 EI KONOCTI-MIDDLETOWN 014/004 GYWW | 43761672 | KONOCTI-MIDDLETOWN | 014/004 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.580041 | 38.7774 | ETL.6380 | 44370572 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-05-29
116580010 | T3 EI KESWICK-TRINITY 005/072 INST GYWW | 43661466 | KESWICK-TRINITY | 005/072 | ICW | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-122.545832 | 40.6308 | ETL.7270 | 40617597 | Guy Wire-Wood | Missing | Install | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
116580455 | T2 EI LAKEVILLE #1 009/000 RPR GYWW | 44310678 | LAKEVILLE #1 | 009/000 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.551883 | 38.3676 | ETL.7360 | 40588835 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-04-04
116580587 | T2 EI MALIN-RND MTN #2 060/302 INST HRDT | 43754878 | MALIN-ROUND MTN #2 | 060/302 | ICQ | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.657825 | 41.2019 | ETL.6020 | 40677663 | Hardware-Tower | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 543 | Table Mountain |  |  | Yes
116580613 | T2 EI MALIN-RND MTN #2 060/303 RPR COND | 43621093 | MALIN-ROUND MTN #2 | 060/303 | ICQ | E | Pre-2020_(1b) Lines with special commitments |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.65996 | 41.1993 | ETL.6020 | 40663113 | Conductor-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
116580712 | EI HAT CREEK #1-WESTWD 049/952 REFRAME | 31471609 | HAT CREEK #1-WESTWOOD | 049/952 | 93E | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-121.016208 | 40.384 | ETL.7030 | 40868255 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  | Yes
116580714 | T2 EI MLIN-ROUND MTN #2 062/311 RPL INSS | 31439323 | MALIN-ROUND MTN #2 | 062/311 | 93K | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.67461 | 41.1813 | ETL.6020 | 40619337 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  | Yes
116580717 | EI HAT CREEK #1-WESTWD 047/912 RPL STRW | 31509530 | HAT CREEK #1-WESTWOOD | 047/912 | 70Y | E | Pre-2020_(2) High fire spread TD |  |  |  |  | LATE | North Valley | WSIP |  |  |  |  | Access Issues | 2021 - Snow . FSR 12/2020 | '-121.021323 | 40.414 | ETL.7030 | 40877513 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Need New ERTC
116580811 | T2 EI MALIN ROUND 060/301 RPL HRDT | 31439323 | MALIN-ROUND MTN #2 | 060/301 | 93K | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.6561256 | 41.2041 | ETL.6020 | 40619336 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  | Yes
116581549 | T2 EI CARIBOU-PALERMO :09/070 RPR FOND | 44059014 | CARIBOU-PALERMO | :009/070 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.254842 | 40.0061 | ETL.3190 | 40910312 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
116581610 | T2 EI CARIBOU #2 018/000 RPL SPLW | 43742136 | CARIBOU #2 | 018/000 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.061181 | 40.0195 | ETL.6280 | 40599711 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
116582733 | T2 EI ROUND MTN-TM #1 33/160 RPR STRT | 43848514 | ROUND MTN-TABLE MTN #1 | 033/160 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Internal Process | Circuit Based Scheduling | '-121.934379 | 40.3267 | ETL.6060 | 40601337 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
116582818 | T3 EI FULTON-PUEBLO 30/147 REPAINT | 43720980 | FULTON-PUEBLO | 030/147 | ICS | F | Pre-2020_(9a) Other ignition related |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.537064 | 38.4876 | ETL.1600 | 40810374 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Lakeville |  |  | 2019-04-25
116582853 | T2 EI KNCT-MDDLTWN 22/6 RPR GYWS | 43760955 | KONOCTI-MIDDLETOWN | 022/006 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.737662 | 38.9303 | ETL.6380 | 44244858 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Lakeville |  |  | 2019-05-29
116582859 | T2 EI DBL-MDWY #3 12/48 RPR INSS | 43756129 | DIABLO-MIDWAY #3 | 012/048 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | South | WSIP |  |  |  |  | Clearance Delayed | Diablo imposed clearance constraints, tag scheduled for 10/6-16 | '-120.634937 | 35.1789 | ETL.5980 | 40863917 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Pismo Beach |  | Y - 4
116582881 | T2 EI GNC-LT-SSLT #1 6/47 PNT | 43714149 | IGNACIO-ALTO-SAUSALITO #1 | 006/047 | ICS | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.495152 | 37.9877 | ETL.7160 | 40601837 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville
116584028 | T2 EI GNC-LT-SSLT #1 6/48 PNT | 43714149 | IGNACIO-ALTO-SAUSALITO #1 | 006/048 | ICS | F | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.495136 | 37.987 | ETL.7160 | 40701449 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Lakeville
116584972 | T2 EI DRUM-HIGGINS 17/150 REPL SPLS | 43738143 | DRUM-HIGGINS | 017/150 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.024284 | 39.1341 | ETL.4393 | 40913046 | Splice-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes
116586307 | T2 EI DBL-MDWY #3 19/77 RPL INSS | 31456686 | DIABLO-MIDWAY #3 | 019/077 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | South | WSIP |  |  |  |  | Clearance Delayed | Diablo imposed clearance constraints, tag scheduled for 10/6-16 | '-120.528026 | 35.174 | ETL.5980 | 40836750 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 4
116586702 | T2 EI IGNCIO-ALT-SSLITO #1 6/44 PNT MEMB | 43714149 | IGNACIO-ALTO-SAUSALITO #1 | 006/044 | ICS | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.495338 | 37.9969 | ETL.7160 | 40864746 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Lakeville
116586703 | EI NEWARK-LIVERMORE 005/040 PNT STRT | 43752137 | NEWARK-LIVERMORE | 005/040 | ICS | E | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) |  |  |  | LATE | Central | WSIP | [6 empty] | '-121.894996 | 37.5431 | ETL.7660 | 40613171 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  | Y - 11
116586937 | T2 EI RND MTN-TBL MTN #1 32/157 BENT STL | 43848514 | ROUND MTN-TABLE MTN #1 | 032/157 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Internal Process | Circuit Based Scheduling | '-121.934125 | 40.3358 | ETL.6060 | 40813092 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
116587108 | T2 EI RND MTN-TBL MTN#2 67/278 INST GMKS | 44302501 | ROUND MTN-TABLE MTN #2 | 067/278 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.798731 | 39.8518 | ETL.6070 | 40865966 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
116587174 | T2 EI TIGER CRK-VALY 12/97 SPRGS REPAINT | 43727745 | TIGER CREEK-VALLEY SPRINGS | 012/097 | ICS | E | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.662218 | 38.3464 | ETL.5790 | 40858494 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Released
116587255 | T2 EI RNDMTN-TBLMTN#1 067/278 INS GMKT | 43848514 | ROUND MTN-TABLE MTN #1 | 067/278 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP | [5 empty] | Priority Bucket 9 | '-121.799305 | 39.8519 | ETL.6060 | 40865978 | Hardware-Tower | Missing | Install | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
116587355 | T2 EI KNCT-MDDLTWN 15/8 RPR GYWW | 43761672 | KONOCTI-MIDDLETOWN | 015/008 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.566537 | 38.7943 | ETL.6380 | 44141955 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-05-29
116587410 | T2 EI IGNACIO-ALTO-SAUS #1 6/49 PNT TWR | 43714149 | IGNACIO-ALTO-SAUSALITO #1 | 006/049 | ICS | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.495096 | 37.9847 | ETL.7160 | 40668225 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Lakeville
116587457 | T2 EI KNCT-MDDLTWN 15/1 RPR GYWW | 43761672 | KONOCTI-MIDDLETOWN | 015/001 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.573546 | 38.7841 | ETL.6380 | 44370574 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-05-29
116587513 | T2 EI DIABLO-MIDWAY #2 14/055 RPL INSS | 31526468 | DIABLO-MIDWAY #2 | 014/055 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | South | WSIP |  |  |  |  | Clearance Delayed | Diablo imposed clearance constraintsk; tag scheduled for 9/23-10/5 | '-120.607601 | 35.1675 | ETL.5970 | 40753809 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 18
116587715 | T2 EI RND MT-TBL MT #2 72/297 REPAINT | 44302501 | ROUND MTN-TABLE MTN #2 | 072/297 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.762773 | 39.7684 | ETL.6070 | 40813483 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain
116587806 | T2 EI VINYRD-NEWRK 38/223A RPL HRDT |  | VINEYARD-NEWARK | 038/223A | ICQ | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-121.895761 | 37.5431 | ETL.4536 | 41196096 | Hardware-Tower | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog Multi
116587817 | T2 EI VINYRD-NEWRK 38/223A PNT STRT | 43753288 | VINEYARD-NEWARK | 038/223A | ICS | E | Pre-2020_(5b) On structure in bucket 5 | Budget Owner (Paint) |  |  |  | LATE | Central | WSIP | [6 empty] | '-121.895761 | 37.5431 | ETL.4536 | 41196096 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  | Y - Prog Multi
116588326 | T2 EI TIGER CRK-ELECTRA 9/70 REPAINT | 43727728 | TIGER CREEK-ELECTRA | 009/070 | ICS | E | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.634276 | 38.3898 | ETL.5780 | 40591468 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - Prog Multi
116588515 | T2 EI RO DL JCT-BRDGE 027/004 RPL CONW | 31473341 | RIO DELL JCT-BRIDGEVILLE | 027/004 | 93C | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.9838 | 40.4935 | ETL.7850 | 40769406 | Conductor-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 638 | Eureka |  |  | 2019-08-01
116588630 | T2 EI RO DLL JCT-BDGVLE 027/003 RPR ANCS | 43749702 | RIO DELL JCT-BRIDGEVILLE | 027/003 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.985802 | 40.4941 | ETL.7850 | 40648546 | Anchor-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Eureka |  |  | 2019-07-15
116588698 | T2 EI RO DLL JCT-BRDGV027/ 005 RPL CONW | 31473341 | RIO DELL JCT-BRIDGEVILLE | 027/005 | 93C | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.982194 | 40.493 | ETL.7850 | 40750366 | Conductor-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 638 | Eureka |  |  | 2019-08-01
116588744 | T2 EI RO DL JCT-BRDGVLE 027/007 RPL CONW | 31473341 | RIO DELL JCT-BRIDGEVILLE | 027/007 | 93C | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.97713 | 40.4914 | ETL.7850 | 40824509 | Conductor-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 638 | Eureka |  |  | 2019-08-01
116588818 | HAT CREEK #1-WESTWOOD 46/898 RPL STRW | 31509530 | HAT CREEK #1-WESTWOOD | 046/898 | 70Y | E | Pre-2020_(2) High fire spread TD |  |  |  |  | LATE | North Valley | WSIP |  |  |  |  | Access Issues | 2021 - Snow . FSR 12/2020 | '-121.023102 | 40.4243 | ETL.7030 | 40758929 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Need New ERTC
116588903 | EI HT CRK #1-WSTWD 46/903 RPL STRW | 31509530 | HAT CREEK #1-WESTWOOD | 046/903 | 70Y | E | Pre-2020_(2) High fire spread TD |  |  |  |  | LATE | North Valley | WSIP |  |  |  |  | Access Issues | 2021 - Snow . FSR 12/2020 | '-121.022455 | 40.4207 | ETL.7030 | 40876215 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Need New ERTC
116588904 | EI HT CRK #1-WSTWD 47/906 RPL SPLW | 43736798 | HAT CREEK #1-WESTWOOD | 047/906 | ICW | E | Pre-2020_(2) High fire spread TD |  |  |  |  | LATE | North Valley | WSIP |  |  |  |  | Access Issues | 2021 - Snow . FSR 7/2020 | '-121.022087 | 40.4185 | ETL.7030 | 40675741 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
116588910 | DI HT CRK #1-WSTWD 47/904 REPL POLE | 31475080 | HAT CREEK #1-WESTWOOD | 047/904 | 70Y | E | Pre-2020_(2) High fire spread TD |  |  |  |  | LATE | North Valley | WSIP |  |  |  |  | Access Issues | 2021 - Snow . FSR 12/2020 | '-121.022305 | 40.4199 | ETL.7030 | 40617035 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
116589420 | T2 EI PTSBRG-SN MTEO 020/081 RPR FOND | 44238800 | PITTSBURG-SAN MATEO | 020/081 | ICQ | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-121.925992 | 37.7526 | ETL.5463 | 40805085 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog Multi
116589508 | T2 EI LS ESTRS-MTCLF 013/061 RPR FOND |  | LOS ESTEROS-METCALF | 013/061 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-121.777067 | 37.399 | ETL.5353 | 40587062 | Foundation/Concrete-Tower | Earth Covered Tower | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog Multi
116589589 | EI LAS POSITAS-NEWARK 14/092 REPAINT | 43753291 | LAS POSITAS-NEWARK | 014/092 | ICS | F | Pre-2020_(9a) Other ignition related | Budget Owner (Paint) |  |  |  | LATE | Central | WSIP | FSRP | [5 empty] | '-121.89351 | 37.5459 | ETL.4980 | 40593918 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay
116589664 | T2 EI DIABLO-MIDWAY#2 18/071 RPL INSS | 31526468 | DIABLO-MIDWAY #2 | 018/071 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | South | WSIP |  |  |  |  | Clearance Delayed | Diablo imposed clearance constraintsk; tag scheduled for 9/23-10/5 | '-120.54761 | 35.1746 | ETL.5970 | 40593632 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 18
116589702 | T2 EI RND MTN-TM #2 059/250 PAINT TWR | 44305720 | ROUND MTN-TABLE MTN #2 | 059/250 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Internal Process | Circuit Based Scheduling | '-121.845287 | 39.9619 | ETL.6070 | 40601383 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Table Mountain
116589772 | EI NEWARK-LIVERMORE 5/041 REPAINT | 43752137 | NEWARK-LIVERMORE | 005/041 | ICS | E | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) |  |  |  | LATE | Central | WSIP | [6 empty] | '-121.892899 | 37.5455 | ETL.7660 | 40580687 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay
116589965 | T2 EI DIABLO-MIDWAY #3 021/088A RPL SPCS | 43756129 | DIABLO-MIDWAY #3 | 021/088A | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | South | WSIP |  |  |  |  | Clearance Delayed | Diablo imposed clearance constraints, tag scheduled for 10/6-16 | '-120.477877 | 35.1638 | ETL.5980 | 40577051 | Spacer-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Pismo Beach |  | Y - 4
116589966 | T2 EI RND MTN-TM #2 059/251 PAINT TWR | 44305720 | ROUND MTN-TABLE MTN #2 | 059/251 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Internal Process | Circuit Based Scheduling | '-121.842922 | 39.9563 | ETL.6070 | 40592714 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Table Mountain
116589985 | T2 EI QNTO SW STA-WSTLY 24/110 INST HRDT | 43727740 | LOS BANOS-WESTLEY | 024/110 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-121.215521 | 37.489 | ETL.5070 | 40591723 | Hardware-Tower | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - Prog Multi
116590125 | T2 EI COLGATE-PALERMO 17/341 RPL INSW | 43728970 | COLGATE-PALERMO | 017/341 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.434739 | 39.4361 | ETL.6500 | 40824128 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
116590199 | T2 EI TESLA-NEWARK #1 022/115 RPR FOND | 43753786 | TESLA-NEWARK #1 | 022/115 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-121.892251 | 37.5459 | ETL.5720 | 40761984 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog Multi
116590252 | T3 EI DIABLO UNIT #2 005/006 RPR GYWS | 43921577 | DIABLO UNIT #2 (NF) | 005/006 | ICS | E | Pre-2020_(5) TD tag on other lines |  |  | Tower guy | TR3 | LATE | South | WSIP |  |  |  |  | Clearance Delayed | Diablo imposed clearance constraints; tag scheduled for 10/8-13 | '-120.85021 | 35.2134 | ETL.5950 | 40819287 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Pismo Beach |  | Y - 1
116590298 | T2 EI RND MTN-TBLE MTN#1 33/159 INS GMKT | 43848514 | ROUND MTN-TABLE MTN #1 | 033/159 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP | [5 empty] | Priority Bucket 9 | '-121.934297 | 40.3297 | ETL.6060 | 40868413 | Hardware-Tower | Missing | Install | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
116590352 | T2 EI QNTO SW STA-WSTLY 25/112 RPR FOND | 43727740 | LOS BANOS-WESTLEY | 025/112 | ICQ | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-121.21049 | 37.4796 | ETL.5070 | 40662928 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - Prog Multi
116590382 | T2 EI DIABLO-MIDWAY#2 17/70 RPL INSS | 31526468 | DIABLO-MIDWAY #2 | 017/070 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | South | WSIP |  |  |  |  | Clearance Delayed | Diablo imposed clearance constraintsk; tag scheduled for 9/23-10/5 | '-120.549816 | 35.1746 | ETL.5970 | 40592838 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 18
116590396 | T2 EI DIABLO-MIDWAY #3 29/118 RPR INSS | 43756129 | DIABLO-MIDWAY #3 | 029/118 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | South | WSIP |  |  |  |  | Clearance Delayed | Diablo imposed clearance constraints, tag scheduled for 10/6-16 | '-120.348391 | 35.1675 | ETL.5980 | 40871725 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Pismo Beach |  | Y - 4
116590429 | T2 EI DIABLO-MIDWAY #2 29/119 RPL INSS | 31526468 | DIABLO-MIDWAY #2 | 029/119 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | South | WSIP |  |  |  |  | Clearance Delayed | Diablo imposed clearance constraintsk; tag scheduled for 9/23-10/5 | '-120.343918 | 35.1673 | ETL.5970 | 40863567 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 18
116590472 | T2 EI PITTSBURG-TESLA #1 10/47 RPR FOND | 44238805 | PITTSBURG-TESLA #1 | 010/047 | ICS | E | Pre-2020_(5) TD tag on other lines |  |  | Likely MAT error - delink to correct | TR2 | LATE | Central | WSIP | [6 empty] | '-121.815699 | 37.9248 | ETL.5510 | 40804252 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog Multi
116590487 | T2 EI RND MTN-TBL MTN#2 70/288 RPR CONS | 44305720 | ROUND MTN-TABLE MTN #2 | 070/288 | ICS | E | Pre-2020_(2) High fire spread TD |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Clearance Cancelled by GCC | 2021 - Cancelled by ISO | '-121.780121 | 39.8077 | ETL.6070 | 40871367 | Conductor-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain
116590528 | EI NEWARK-LIVERMORE 10/063 REPAINT | 43752137 | NEWARK-LIVERMORE | 010/063 | ICS | F | Pre-2020_(3) On high spread structure | Budget Owner (Paint) |  |  |  | <30D | Central | WSIP |  |  |  |  | Program | 2021 Paint took out of program due to future project to be removed with [REDACTED] | '-121.845808 | 37.5933 | ETL.7660 | 40644060 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay
116590695 | T2 EI DIABLO-MIDWAY#3 18/071 RPLC INSS | 43756129 | DIABLO-MIDWAY #3 | 018/071 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | South | WSIP |  |  |  |  | Clearance Delayed | Diablo imposed clearance constraints, tag scheduled for 10/6-16 | '-120.546895 | 35.1752 | ETL.5980 | 40612740 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Pismo Beach |  | Y - 4
116591833 | EI KILARC-DESCHUTES A25/539 RPL STRW | 31440586 | KILARC-DESCHUTES | A025/539 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-122.293359 | 40.5711 | ETL.7300 | 41118632 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
116591964 | T2 EI GNC-LT-SSLT #1 5/42 RPL HRDT | 43693608 | IGNACIO-ALTO-SAUSALITO #1 | 005/042 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.498316 | 38.0045 | ETL.7160 | 40827694 | Hardware-Tower | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville
116592597 | T3 EI TGR CRK-LCTR 008/062 REPAINT | 43727728 | TIGER CREEK-ELECTRA | 008/062 | ICS | E | Pre-2020_(9a) Other ignition related | Budget Owner (Paint) |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-120.617524 | 38.4018 | ETL.5780 | 40681643 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Released
116592628 | T2 EI RND MTN-CTTNWD #3 41/348 RPR INSS | 44624619 | ROUND MTN-COTTONWOOD #3 | 041/348 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.081169 | 40.6209 | ETL.5650 | 40873283 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain
116592644 | T2 EI KNCT-MDDLTWN 027/006 RPL PL | 31490901 | KONOCTI-MIDDLETOWN | 027/006 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.655546 | 38.9071 | ETL.6380 | 40826576 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  | 2019-05-29
116592661 | T3 EI TGR CRK-VLY SPG 007/061 REPAINT | 43727745 | TIGER CREEK-VALLEY SPRINGS | 007/061 | ICS | E | Pre-2020_(9a) Other ignition related |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-120.617342 | 38.4016 | ETL.5790 | 40681626 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - Prog Multi
116592913 | T3 EI TGR CRK-VLY SPG 008/063 REPAINT | 43727745 | TIGER CREEK-VALLEY SPRINGS | 008/063 | ICS | E | Pre-2020_(9a) Other ignition related |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-120.621343 | 38.3988 | ETL.5790 | 40753070 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - Prog Multi
116592932 | T3 EI TGR CRK-LCTR 008/064 REPAINT | 43727728 | TIGER CREEK-ELECTRA | 008/064 | ICS | E | Pre-2020_(9a) Other ignition related |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-120.621524 | 38.3989 | ETL.5780 | 40752893 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - Prog Multi
116592938 | EI JFFRSON-HLLSDLE JCT-007/044 RPL INSS | 31453027 | JEFFERSON-HILLSDALE JCT | 007/044 | 93K | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | Central | WSIP | FSRP | [5 empty] | '-122.3647585 | 37.5443 | ETL.7190 | 40793293 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - 5 | SFPUC (4)
116592958 | T3 EI TGR CRK-LCTR 008/063 REPAINT | 43727728 | TIGER CREEK-ELECTRA | 008/063 | ICS | E | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-120.620505 | 38.3997 | ETL.5780 | 40651012 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Released
116593024 | T2 EI JEFFERSON-HILLSDLE J 6/35 RPL DAMP | 43752125 | JEFFERSON-HILLSDALE JCT | 006/035 | ICS | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.356591 | 37.5248 | ETL.7190 | 40755149 | Damper-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - 5 | SFPUC (4)
116593026 | T2 EI KNCTI-MDDLTWN 28/08 RPL STRW | 31490901 | KONOCTI-MIDDLETOWN | 028/008 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.632127 | 38.9123 | ETL.6380 | 40876780 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  | 2019-04-04
116593074 | T3 EI KNCTI-MDDLTWN 28/03L RPR GYWW | 43749609 | KONOCTI-MIDDLETOWN | 028/003 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Coast | WSIP | [8 empty] | ETL.6380 | 44235467 | Ground Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-04-04
116593253 | T2 EI KNCT-MDDLTWN 024/012 RPR GYWW | 43761672 | KONOCTI-MIDDLETOWN | 024/012 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.617814 | 38.9108 | ETL.6380 | 40661672 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-05-29
116593360 | T2 EI JFFRSN-HILLSDL JCT 06/35E PNT STRS | 43752125 | JEFFERSON-HILLSDALE JCT | 006/035E | ICS | E | Pre-2020_(5b) On structure in bucket 5 | Budget Owner (Paint) |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.35663 | 37.5251 | ETL.7190 | 44384034 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  |  | SFWL
116593816 | T2 EI TESLA-METCALF 032/136 INS HRDT |  | TESLA-METCALF | 032/136 | ICQ | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-121.730295 | 37.2552 | ETL.6110 | 40818974 | Hardware-Tower | Missing | Install |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay
116593822 | T2 EI TESLA-METCALF 033/137 RPL HRDT |  | TESLA-METCALF | 033/137 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-121.732281 | 37.2492 | ETL.6110 | 40817822 | Hardware-Tower | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 3
116594053 | T2 EI RND MTN-CTTNWD #3 48/419 RPR INSS | 44624619 | ROUND MTN-COTTONWOOD #3 | 048/416 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.147551 | 40.541 | ETL.5650 | 40816944 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain
116594182 | T2NT EI VLY SPRNGS-CLY 007/109 INS MRKW |  | VALLEY SPRINGS-CLAY | 007/109 | ICW | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.84561 | 38.2321 | ETL.8264 | 40904741 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 12
116594221 | T2 EI VLLY SPRNGS-CLY 9/126 INS MRKW |  | VALLEY SPRINGS-CLAY | 009/126 | ICW | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.850981 | 38.2519 | ETL.8264 | 40904753 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 12
116594366 | T2 EI RND MTN-CTTNWD #3 44/379 RPL HRDS | 43755803 | ROUND MTN-COTTONWOOD #3 | 044/379 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.111416 | 40.5845 | ETL.5650 | 40858192 | Hardware-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
116594602 | T2 EI VLY SPRNGS-CLY 007/108 RPR GND | 43712679 | VALLEY SPRINGS-CLAY | 007/108 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.84447 | 38.2308 | ETL.8264 | 40904740 | Ground Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 12
116594657 | T2 EI VLY SPRNGS-CLY 007/108 INS MRKW |  | VALLEY SPRINGS-CLAY | 007/108 | ICW | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.84447 | 38.2308 | ETL.8264 | 40904740 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 12
116594721 | DI POE-RIO OSO 36/241 INS HRDS | 43737421 | POE-RIO OSO | 036/241 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-121.525947 | 39.4671 | ETL.5540 | 40596663 | Hardware-Steel | Missing | Install | DOCC srdy | DOCC | Job has been constructed (documentation) | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
116595458 | T2 EI HT CRK #1-WSTWD 046/884 RPR GYWW | 43736798 | HAT CREEK #1-WESTWOOD | 046/884 | ICW | E | Pre-2020_(2) High fire spread TD |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Access Issues | 2021 - Snow . | '-121.023065 | 40.4339 | ETL.7030 | 40589877 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
116595578 | T3 EI DRM-HGGNS 008/084 PNT STRT | 43738143 | DRUM-HIGGINS | 008/084 | ICS | E | Pre-2020_(9a) Other ignition related |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.884168 | 39.1703 | ETL.4393 | 40751900 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Sacramento |  |  | Yes
116607344 | T2 EI VLLEY SPRNGS-CLY 7/106 RPL ANCH | 31426625 | VALLEY SPRINGS-CLAY | 007/106 | 93E | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.8421 | 38.2282 | ETL.8264 | 40904739 | Anchor-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Victor |  | Y - Prog Multi
116607442 | T2 EI HT CRK #1-WSTWD 045/874 RPL STRW | 31426976 | HAT CREEK #1-WESTWOOD | 045/874 | 70Y | E | Pre-2020_(2) High fire spread TD |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Access Issues | 2021 - Snow . | '-121.022883 | 40.4423 | ETL.7030 | 40876260 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain
116607514 | T2NT EI VLY SPRNGS-CLY 006/088 INS MRKW |  | VALLEY SPRINGS-CLAY | 006/088 | ICW | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.834348 | 38.2139 | ETL.8264 | 40904723 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog Multi
116607744 | T2 ELECTRA-BELLOTA 000/001 INS GMKW | 43727726 | ELECTRA-BELLOTA | 000/001 | ICS | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.66894 | 38.3315 | ETL.4670 | 40911503 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - 6
116608191 | T2 EI EAGLE ROCK CORTINA :17/0 INS GYWW | 43730688 | EAGLE ROCK-CORTINA | :017/000 | ICW | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.609974 | 38.967 | ETL.1470 | 41176364 | Guy Wire-Wood | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-08-06
116608356 | T2 EI TESLA-METCALF 21/89 RPL ANCS |  | TESLA-METCALF | 021/089 |  | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-121.659318 | 37.4123 | ETL.6110 | 40869059 | Anchor-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLQ | Tower | Expense |  | Bay |  | Y - 3 | 2019-06-04
116608425 | T3 EI ORO FINO TAP 0/1 INS GYWW | 43758390 | ORO FINO TAP | 000/001 | ICW | E | Pre-2020_(9a) Other ignition related |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.62919 | 39.8652 | ETL.6721 | 40591915 | Guy Wire-Wood | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
116609171 | T2 EI MLLBRE-SNTHLN 014/095 RPNT STRT | 43753781 | MILLBRAE-SNEATH LANE | 014/095 | ICS | F | Pre-2020_(5b) On structure in bucket 5 | Budget Owner (Paint) |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.44173 | 37.6175 | ETL.7570 | 44384516 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  |  | SFWL
116609584 | T3 EI DRUM-RIO OSO #1 1/13 CANCEL | 43746396 | DRUM-RIO OSO #1 | 001/013 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  | CANCEL/CNCL | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.791076 | 39.2564 | ETL.1420 | 40654181 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento |  |  | Yes
116609858 | T2 EI JEFFERSON-STANFORD 1/28 ANTI-SPLIT | 43752127 | JEFFERSON-STANFORD (NO FLY) | 001/028 | ICW | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.266038 | 37.4618 | ETL.7220 | 40824885 | Hardware-Wood | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Bay |  | Y - Prog Multi | 2019-07-31
116609932 | T2 EI VLLY SPRINGS-CLAY 006/087 RPR GYWW | 43712893 | VALLEY SPRINGS-CLAY | 006/087 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.833763 | 38.2121 | ETL.8264 | 40904722 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog Multi
116611958 | T2 EI CORDELIA #2 TAP 3/67 RPR GYWW | 43743931 | CORDELIA #2 TAP | 003/067 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.154242 | 38.2508 | ETL.8184 | 40599323 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Sacramento |  |  | Yes
116614661 | T2 EI KONOCTI-MIDDLE 025/005 RPR GYWW | 43761672 | KONOCTI-MIDDLETOWN | 025/005 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.689236 | 38.9149 | ETL.6380 | 40750138 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-05-29
116614807 | T2 EI PTTSBURG-SN MATEO 006/028 RPL INSS | 31457508 | PITTSBURG-SAN MATEO | 006/028 | 93K | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-121.8929165 | 37.9538 | ETL.5463 | 40671963 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - 8
116615248 | T2 EI BALCH-SANGER 006/037 FOOTINGS | 43709595 | BALCH-SANGER | 006/037 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-119.167301 | 36.8889 | ETL.1050 | 40806877 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 17
116615901 | T2 EI KNCTI-MDDLTWN 025/009 RPR GYWW | 43761672 | KONOCTI-MIDDLETOWN | 025/009 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.68291 | 38.9128 | ETL.6380 | 40875484 | Ground Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-05-29
116616141 | T2 EI VLLY SPRNGS-CLY 8/121 RPR GYWW | 43712893 | VALLEY SPRINGS-CLAY | 008/121 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.850908 | 38.2432 | ETL.8264 | 40906852 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 12
116616163 | T2 EI PITT-TESLA #1 012/056 RPR FOND | 44238805 | PITTSBURG-TESLA #1 | 012/056 | ICS | E | Pre-2020_(5) TD tag on other lines |  |  | Likely MAT error - delink to correct | TR2 | LATE | Central | WSIP | [6 empty] | '-121.786902 | 37.9139 | ETL.5510 | 40810772 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog Multi
116616177 | T3 EI CSTR VLY-NWRK -002/020 RPR FOND |  | CASTRO VALLEY-NEWARK | 002/020 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.027178 | 37.6745 | ETL.4450 | 40670684 | Foundation/Concrete-Tower | Earth Covered Tower | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 10 | 2018-04-17
116616202 | T2 EI CSCDE-BNTN-DSCHTS A08/182 RPR GYWW | 43690811 | CASCADE-BENTON-DESCHUTES | A008/182 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.244996 | 40.5557 | ETL.6310 | 40600686 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
116616290 | T2 EI IGNA-ALTO-SAU #1 011/077 RPR FOND | 43693608 | IGNACIO-ALTO-SAUSALITO #1 | 011/077 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.514491 | 37.9139 | ETL.7160 | 40601773 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  | 2019-06-28
116616555 | T2 EI TESLA-RVNSWOOD 018/096 RPL INSS | 31454851 | TESLA-RAVENSWOOD | 018/096 | 93K | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-121.8471563 | 37.5922 | ETL.5730 | 40837846 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - 2 | SFPUC
116616694 | T2 EI NEWARK-LAW LAB 10/062 HANGER EYE | 44392611 | NEWARK-LAWRENCE LAB | 010/062 | ICS | E | Pre-2020_(5) TD tag on other lines |  | TLN/TLQ error |  | TR2 | LATE | Central | WSIP | [6 empty] | '-121.847264 | 37.5924 | ETL.3060 | 40732585 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  | Y - 7 | SFPUC
116616819 | T2 EI TESLA-NEWARK #2 017/118 REPAINT | 43753285 | TESLA-NEWARK #2 | 017/118 | ICS | E | Pre-2020_(3) On high spread structure | Budget Owner (Paint) |  |  | TR2 | LATE | Central | WSIP |  |  |  |  | Readiness | 2021 Paint Program - SFPUC - Permit Delay | '-121.847617 | 37.5924 | ETL.5354 | 41152664 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  |  | SFWL
116616959 | T2 EI EGL RCK-CRTNA :020/003 RPR GYWW | 43730688 | EAGLE ROCK-CORTINA | :020/003 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.612153 | 39.0118 | ETL.1470 | 41176414 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-05-20
116617048 | T2 EI DRUM-RIO OSO #1 21/163 RPNT STRS | 43746398 | DRUM-RIO OSO #1 | 021/163 | ICS | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.097305 | 39.1054 | ETL.1420 | 40659461 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes
116617095 | T2 EI VALLEY SPRINGS-CLY 11/160 RPL HRDD | 43712893 | VALLEY SPRINGS-CLAY | 011/160 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.886319 | 38.2758 | ETL.8264 | 40904773 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog Multi
116617541 | T2 EI CARIBOU #2 020/021 RPL PL | 31425844 | CARIBOU #2 | 020/021 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.018718 | 40.0319 | ETL.6280 | 40600626 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  | Yes
116617542 | T2 CARIBOU #2 020/019 RPL PL | 31455203 | CARIBOU #2 | 020/019 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.019303 | 40.0316 | ETL.6280 | 40867545 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  | Yes
116617547 | T2 EI CARIBOU #2 - 20/017 RPL ANCH | 31456236 | CARIBOU #2 | 020/017 | 93E | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.020452 | 40.031 | ETL.6280 | 40824619 | Anchor-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 637 | Table Mountain |  |  | Yes
116617555 | T2 EI CARIBOU #2 20/20 RPL SPLCW | 43742136 | CARIBOU #2 | 020/020 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.017555 | 40.032 | ETL.6280 | 40614863 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
116617613 | T3 EI FLTN-PBL 031/152 RPR FOND | 43720989 | FULTON-PUEBLO | 031/152 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.5503 | 38.4856 | ETL.1600 | 40656848 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville
116617719 | T2 EI RND MTN-TM #2 032/157 RPR STRT | 43755806 | ROUND MTN-TABLE MTN #2 | 032/157 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Internal Process | Circuit Based Scheduling | '-121.933589 | 40.3358 | ETL.6070 | 40816747 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
116618132 | T2 EI TESLA-NEWARK #2 018/121 PAINT | 43753285 | TESLA-NEWARK #2 | 018/121 | ICS | E | Pre-2020_(3) On high spread structure | Budget Owner (Paint) |  |  | TR2 | LATE | Central | WSIP |  |  |  |  | Readiness | 2021 Paint Program - SFPUC - Permit Delay | '-121.855783 | 37.5875 | ETL.5354 | 41152667 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  |  | SFWL
116618210 | T2 EI TESLA-NEWARK #2 018/119 PAINT | 43753285 | TESLA-NEWARK #2 | 018/119 | ICS | E | Pre-2020_(3) On high spread structure | Budget Owner (Paint) |  |  | TR2 | LATE | Central | WSIP |  |  |  |  | Readiness | 2021 Paint Program - SFPUC - Permit Delay | '-121.85126 | 37.5903 | ETL.5354 | 41152665 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  |  | SFWL
116618330 | T2 EI MALIN-RND MTN #2 94/478 RPR INSS | 43621093 | MALIN-ROUND MTN #2 | 094/479 | ICQ | E | Pre-2020_(1b) Lines with special commitments |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.93149 | 40.8118 | ETL.6020 | 40870788 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain
116618484 | T2 EI BRENTWOOD-KELSO 008/042 HANGER | 44378559 | BRENTWOOD-KELSO | 008/042 | ICS | E | Pre-2020_(5) TD tag on other lines |  | TLN/TLQ error | Recommend delinking prior to editing | TR2 | LATE | Central | WSIP | [6 empty] | '-121.679961 | 37.8453 | ETL.4410 | 40661446 | Hardware-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - 4
116618551 | T2 EI RND MTN-TM # 055/238 PAINT TWR |  | ROUND MTN-TABLE MTN #2 | 055/238 | ICS | E | Pre-2020_(3) On high spread structure | Budget Owner (Paint) |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Program | 2021 Paint took out of program due to future project to be removed with [REDACTED] | '-121.864177 | 40.0064 | ETL.6070 | 40869938 | Structure-Steel | Paint/Coating | Other |  |  |  |  | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain
116618555 | T2 EI IGNCO-ALTO-SSLTO #1 7/50 PNT MEMB | 43714149 | IGNACIO-ALTO-SAUSALITO #1 | 007/050 | ICS | F | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.495047 | 37.9824 | ETL.7160 | 40770977 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Lakeville
116618670 | T2NT EI NEWARK-LIVERMORE 10/059 RPR STRT | 43752137 | NEWARK-LIVERMORE | 010/059 | ICS | F | Pre-2020_(3) On high spread structure | Budget Owner (Paint) |  |  | TR2 | <30D | Central | WSIP |  |  |  |  | Program | 2021- Paint Program | '-121.855598 | 37.5874 | ETL.7660 | 40857516 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  |  | SFWL
116618718 | T2 EI MLN-RND MTN #2 093/478 PAINT | 43621093 | MALIN-ROUND MTN #2 | 094/478 | ICQ | E | Pre-2020_(1b) Lines with special commitments |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.92932 | 40.8138 | ETL.6020 | 40816663 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
116618829 | T2 EI BRENTWOOD-KELSO 7/038 RPL HRDS | 44378559 | BRENTWOOD-KELSO | 007/038 | ICS | E | Pre-2020_(5) TD tag on other lines |  | TLN/TLQ error | Recommend delinking prior to editing | TR2 | LATE | Central | WSIP | [6 empty] | '-121.692067 | 37.8599 | ETL.4410 | 40873285 | Hardware-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - 4
116618832 | T2 EI TESLA-NEWARK #2 018/120 PAINT | 43753285 | TESLA-NEWARK #2 | 018/120 | ICS | E | Pre-2020_(3) On high spread structure | Budget Owner (Paint) |  |  | TR2 | LATE | Central | WSIP |  |  |  |  | Readiness | 2021 Paint Program - SFPUC - Permit Delay | '-121.854345 | 37.5884 | ETL.5354 | 41152666 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  |  | SFWL
116618861 | T2 EI ROUND MTN-TM #1 063/265 RPNT STRT | 44305409 | ROUND MTN-TABLE MTN #1 | 063/265 | ICS | E | Pre-2020_(3) On high spread structure | Budget Owner (Paint) |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Program | 2021 Paint took out of program due to future project to be removed with [REDACTED] | '-121.821048 | 39.9034 | ETL.6060 | 40759748 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
116619034 | T3 EI FLTN-IGNCO #1 007/041 RPR FOND | 43720617 | FULTON-IGNACIO #1 | 007/041 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.628332 | 38.498 | ETL.4680 | 40597134 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  | 2019-04-30
116619380 | T2 EI FLTN-GNC #1 013/070 RPR FOND | 43720617 | FULTON-IGNACIO #1 | 013/070 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | WSIP | FSRP | [5 empty] | '-122.592307 | 38.4312 | ETL.4680 | 40592338 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville
116619561 | T2 EI PITSBRG-SAN MATEO 007/032 RPR STRT | 44238800 | PITTSBURG-SAN MATEO | 007/032 | ICQ | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-121.892572 | 37.9403 | ETL.5463 | 40805051 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 8
116619611 | T2 EI CARBERRY SS-RO MTN 019/156 PNT TWR | 43897851 | CARBERRY SW STA-ROUND MTN | 019/156 | ICX | F | Pre-2020_(9a) Other ignition related |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.787667 | 40.8255 | ETL.5410 | 40811302 | Structure-Tower | Paint/Coating | Repaint | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense |  | Table Mountain |  |  | Yes
116619683 | T2 EI SOBRANTE-R #1 004/029 REPL HRDT | 43727738 | SOBRANTE-R #1 | 004/029 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.283829 | 37.9197 | ETL.3770 | 40857827 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 8
116619696 | T2 EI HT CRK #1 WSTWD 012/249 RPR GYWW | 43736796 | HAT CREEK #1-WESTWOOD | 012/249 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.368238 | 40.8175 | ETL.7030 | 40817101 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
116619798 | EI FULTON-IGNACIO #1 013/069 RPR FOND | 43720617 | FULTON-IGNACIO #1 | 013/069 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  |  | LATE | North Coast | WSIP | [6 empty] | '-122.589229 | 38.4354 | ETL.4680 | 40863253 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  | 2019-04-30
116619918 | T3 EI FLTN-GNC #1 007/044 RPR FOND | 43720617 | FULTON-IGNACIO #1 | 007/044 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.618773 | 38.4975 | ETL.4680 | 40762364 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  | 2019-04-30
116619948 | T2 EI NEWARK-LIVER 009/058 REPAINT | 43752137 | NEWARK-LIVERMORE | 009/058 | ICS | E | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-121.857195 | 37.5856 | ETL.7660 | 40875785 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  |  | SFWL
116620007 | T2 EI HT CRK #1 WSTWD 013/252 RPR GYWW | 43736796 | HAT CREEK #1-WESTWOOD | 013/252 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.366153 | 40.8159 | ETL.7030 | 40770721 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
116620008 | T2 EI TESLA-NEWARK #1 018/100 RPR FOND |  | TESLA-NEWARK #1 | 018/100 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-121.857665 | 37.5847 | ETL.5720 | 40604780 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 5 | SFPUC
116620009 | T3 EI FLTN-IGNCO #1 006/035 RPR FOND | 43720617 | FULTON-IGNACIO #1 | 006/035 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.647285 | 38.4973 | ETL.4680 | 40762100 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville
116620016 | T2 EI RND MTN-TM #2 056/242 RPR COND | 44305720 | ROUND MTN-TABLE MTN #2 | 056/242 | ICS | E | Pre-2020_(2) High fire spread TD |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Clearance Cancelled by GCC | 2021 - Cancelled by ISO | '-121.858213 | 39.9923 | ETL.6070 | 40678044 | Conductor-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain
116620185 | T2 EI BRENT-KELSO 008/040 HANGER | 44378559 | BRENTWOOD-KELSO | 008/040 | ICS | E | Pre-2020_(5) TD tag on other lines |  | TLN/TLQ error | Recommend delinking prior to editing | TR2 | LATE | Central | WSIP | [6 empty] | '-121.685141 | 37.8515 | ETL.4410 | 40580985 | Hardware-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - 4
116620354 | T2 EI DIABLO-MIDWAY #3 35/143 RPL INSS | 31526449 | DIABLO-MIDWAY #3 | 035/143 | 93K | E | Pre-2020_(2) High fire spread TD |  |  |  | TR2 | LATE | South | WSIP |  |  |  |  | Clearance Delayed | Diablo imposed clearance constraints | '-120.239079 | 35.1742 | ETL.5980 | 40680790 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 4
116620439 | T2 EI TESLA-NEWARK #1 018/100 RPL HRDT |  | TESLA-NEWARK #1 | 018/100 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-121.857665 | 37.5847 | ETL.5720 | 40604780 | Hardware-Tower | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 5 | SFPUC
116620463 | EI NEWARK-LIVERMORE 17/110 RPR GYWW | 43752138 | NEWARK-LIVERMORE | 017/110 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | Central | WSIP | FSRP | [5 empty] | '-121.783096 | 37.6462 | ETL.7660 | 40580692 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Bay |  | Y - 8
116622227 | T3 EI FLTN-GNC #1 008/046 RPR FOND | 43720617 | FULTON-IGNACIO #1 | 008/046 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.610977 | 38.4975 | ETL.4680 | 40811753 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville
116622390 | T2 EI BRENTWOOD-KELSO 06/034 RPL INSS | 31457314 | BRENTWOOD-KELSO | 006/034 | 93K | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-121.701857 | 37.8718 | ETL.4410 | 40781544 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - 4
116622541 | T2 EI SANTA YNEZ TAP 03/029 RPL SPLW | 43763687 | SANTA YNEZ TAP | 003/029 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | South | WSIP |  |  |  | REJECT |  |  | '-120.135504 | 34.6315 | ETL.3701 | 40659083 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - 3
116622623 | T3 EI FLTN-GNC #1 008/047 RPT STRT | 43720618 | FULTON-IGNACIO #1 | 008/047 | ICS | E | Pre-2020_(9a) Other ignition related |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.607677 | 38.4975 | ETL.4680 | 40811138 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Lakeville |  |  | 2019-04-30
116622693 | T2 EI TESLA-NEWARK #2 019/126 PAINT STRT | 43753285 | TESLA-NEWARK #2 | 019/126 | ICS | F | Pre-2020_(9a) Other ignition related | Budget Owner (Paint) |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-121.864475 | 37.5778 | ETL.5354 | 41152672 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  |  | SFWL
116622726 | T2 EI BRENTWOOD-KELSO 6/033 RPL INSS | 31457314 | BRENTWOOD-KELSO | 006/033 | 93K | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-121.704074 | 37.8744 | ETL.4410 | 40659787 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - 4
116622819 | T2 EI BRENTWOOD-KELSO 06/032 HANGER | 44378559 | BRENTWOOD-KELSO | 006/032 | ICS | E | Pre-2020_(5) TD tag on other lines |  | TLN/TLQ error | Recommend delinking prior to editing | TR2 | LATE | Central | WSIP | [6 empty] | '-121.706676 | 37.8776 | ETL.4410 | 40661442 | Hardware-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - 4
116622828 | T2 EI BRENTWOOD-KELSO 06/032 RPL INSS | 31452001 | BRENTWOOD-KELSO | 006/032 | 93K | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-121.7066892 | 37.8776 | ETL.4410 | 40713188 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - 4
116623157 | T2 EI LAS POSITS-NWRK 13/85 RPL INSLS | 31457507 | LAS POSITAS-NEWARK | 013/085 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-121.878895 | 37.5619 | ETL.4980 | 40796488 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - 4 | SFPUC
116623165 | T2 EI ROUND-TABLE #1 46/206 RPR FOND | 43848514 | ROUND MTN-TABLE MTN #1 | 046/206 | ICQ | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP |  |  |  |  | Priority Bucket 9 | '-121.912243 | 40.1304 | ETL.6060 | 40817835 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
116623408 | T2NT EI MALIN-RND MT #2 92/470 INST MRKS | 43621093 | MALIN-ROUND MTN #2 | 092/470 | ICQ | F | Pre-2020_(1b) Lines with special commitments |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.910941 | 40.831 | ETL.6020 | 40868384 | Marker (i.e. signs)-Steel | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Table Mountain |  |  | Yes
116623526 | T3NT EI CSTR VLY-NWK 005/031 RPR FOND |  | CASTRO VALLEY-NEWARK | 005/031 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-121.996988 | 37.6451 | ETL.4450 | 40654450 | Foundation/Concrete-Tower | Earth Covered Tower | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 10
116623538 | T2 EI ROUND-TABLE #1 45/201 RPR FOND | 43848514 | ROUND MTN-TABLE MTN #1 | 045/201 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP |  |  |  |  | Priority Bucket 9 | '-121.917559 | 40.1508 | ETL.6060 | 40581219 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
116623614 | T2 EI VALLEY SPRINGS #1 007/137 RPR GYWW | 43727732 | VALLEY SPRINGS #1 | 007/137 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.856946 | 38.1519 | ETL.8210 | 40905600 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 23
116623662 | T2 EI OCEANO-CALLNDR SW 19/125 RPR GYWW | 43588178 | OCEANO-CALLENDAR SW STA | 019/125 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | South | WSIP | FSRP | [5 empty] | '-120.579929 | 35.1008 | ETL.2394 | 40752018 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - 7
116623674 | T2 EI MALIN-ROUND MTN#2 91/466 RPR OPGW | 43621093 | MALIN-ROUND MTN #2 | 091/466 | ICQ | E | Pre-2020_(1b) Lines with special commitments |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.91373 | 40.8436 | ETL.6020 | 40817798 | Shield Wire / OPGW-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain
116623883 | T2 EI HMLTN BRNCH-CHSTR 0/004 RPR STRW | 31453005 | HAMILTON BRANCH-CHESTER | 000/004 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.08705 | 40.2698 | ETL.7000 | 40675667 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
116623934 | T2 EI NRTH DBLN-VINEYARD 0/003 INS HRDS | 43753297 | NORTH DUBLIN-VINEYARD | 000/003 | ICS | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-121.8474031 | 37.7449 | ETL.4501 | 42572237 | Hardware-Steel | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - Prog Multi
116623983 | T2 EI TESLA-LOS BANOS#1 27/125 INST ZENA | 44598405 | TESLA-LOS BANOS #1 | 027/125 | ICB | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-121.193908 | 37.446 | ETL.6100 | 40753727 | Raptor Guard-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 593 | Victor |  | Y - Prog Multi
116624072 | T2 EI TESLA-LOS BANOS #1 27/124 RPR STRT | 43727730 | TESLA-LOS BANOS #1 | 027/124 | ICQ | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-121.195786 | 37.4496 | ETL.6100 | 40762394 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - 1
116624166 | T2 EI RD MN-TBLE MN #2 056/241 RPR CONS | 44305720 | ROUND MTN-TABLE MTN #2 | 056/241 | ICS | E | Pre-2020_(2) High fire spread TD |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Clearance Cancelled by GCC | 2021 - Cancelled by ISO | '-121.859275 | 39.9948 | ETL.6070 | 40592713 | Conductor-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
116624408 | T2 EI LAYTONVILLE-WIL 12/000 RPR JUMW | 43761787 | LAYTONVILLE-WILLITS | 012/000 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | FSRP | [5 empty] | '-123.418734 | 39.5438 | ETL.8360 | 40614438 | Jumper-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville
116624636 | T2 EI CONTRA CSTA-LS PSTS 8/54 REPAINT | 43753151 | CONTRA COSTA-LAS POSITAS | 008/054 | ICS | F | Pre-2020_(9a) Other ignition related | Budget Owner (Paint) |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-121.740407 | 37.8965 | ETL.4510 | 40650444 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay
116624900 | T2 EI DIABLO-MDWY#3 38/153 REPL JUMS | 43756129 | DIABLO-MIDWAY #3 | 038/153 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | South | WSIP |  |  |  |  | Clearance Delayed | Diablo imposed clearance constraints, tag scheduled for 10/6-16 | '-120.192643 | 35.1825 | ETL.5980 | 40651899 | Jumper-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Pismo Beach |  | Y - 15
116625067 | BELL-PLACER 004/035 RMV VEGN |  | BELL-PLACER | 004/035 | HNA | E | Pre-2020_(9a) Other ignition related |  |  |  |  | LATE | North Valley | Non-WSIP | [6 empty] | '-121.087971 | 38.9033 | ETL.4395 | 40869585 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  | Yes
116626838 | T2 EI FULTON-PUEBLO 12/059A RPR GYWW | 43720985 | FULTON-PUEBLO | 012/059A | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.21417 | 38.5089 | ETL.1600 | 43249554 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-04-11
116626921 | T2 EI CBRY SW ST-RND MT 021/172 INS MRKS | 43742123 | CARBERRY SW STA-ROUND MTN | 021/172 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.827346 | 40.8224 | ETL.5410 | 40668265 | Marker (i.e. signs)-Steel | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
116627266 | T2 EI BRENTWOOD-KELSO 8/039 REPL INSS | 31452001 | BRENTWOOD-KELSO | 008/039 | 93K | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-121.688556 | 37.8557 | ETL.4410 | 40870203 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - 4
116627314 | T2 EI DIABLO-MDWY#3 39/158 REPAINT | 43756129 | DIABLO-MIDWAY #3 | 039/158 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | South | WSIP |  |  |  |  | Clearance Delayed | Diablo imposed clearance constraints, tag scheduled for 10/6-16 | '-120.17316 | 35.1902 | ETL.5980 | 40870004 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Pismo Beach |  | Y - 5
116627366 | T2 EI TULE-SPRINGVILLE 17/013 REPL SPLW | 43709294 | TULE-SPRINGVILLE | 017/013 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-118.836992 | 36.1117 | ETL.9040 | 40663638 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Midway |  | Y - 23
116627408 | T2 EI FULTON-PUEBLO 23/108 RPR FOND | 43720989 | FULTON-PUEBLO | 023/108 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | WSIP | FSRP | [5 empty] | '-122.413403 | 38.5057 | ETL.1600 | 40858491 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  | 2019-09-03
116627470 | T2 EI TULE-SPRINGVILLE 17/012 RPL SPLW | 43709294 | TULE-SPRINGVILLE | 017/012 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-118.837228 | 36.1115 | ETL.9040 | 40655023 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Midway |  | Y - 23
116627524 | T2 EI TESLA-LOS BANS#1 27/123 REPL RPTS | 44598404 | TESLA-LOS BANOS #1 | 027/123 | ICB | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-121.197147 | 37.4521 | ETL.6100 | 40658774 | Raptor Guard-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 593 | Victor |  | Y - Prog Multi
116627636 | T2 EI HAT CRK #1-WSTWD 009/175 RPL STRW | 31426976 | HAT CREEK #1-WESTWOOD | 009/175 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.407008 | 40.8648 | ETL.7030 | 40667929 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain
116627768 | T2 EI RND MT-TB MT #2 030/147 REPL INSS |  | ROUND MTN-TABLE MTN #2 | 030/147 | 93K | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP |  |  |  |  | Priority Bucket 9 | '-121.9353687 | 40.3663 | ETL.6070 | 40843696 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  | Yes
116628301 | EI CHRISTIE-WILLOW PASS 3/43 RPL PL | 31431652 | CHRISTIE-WILLOW PASS | 003/043 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-122.147009 | 38.0206 | ETL.6370 | 40645283 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Bay |  | Y - 6
116628302 | EI CHRISTIE-WILLOW PASS 3/44 RPL STRW | 31431652 | CHRISTIE-WILLOW PASS | 003/044 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-122.146351 | 38.0204 | ETL.6370 | 40643864 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Bay |  | Y - 7
116629662 | T2 EI IGNCIO-ALTO-SSLTO #1 015/109 STEPS | 43693608 | IGNACIO-ALTO-SAUSALITO #1 | 015/109 | ICQ | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.50651 | 37.8544 | ETL.7160 | 40601775 | Hardware-Tower | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville
116630236 | T2 EI TULE-SPRINGVILLE 13/4 RPR INSW | 43709222 | TULE-SPRINGVILLE | 013/004 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-118.913638 | 36.1096 | ETL.9040 | 40766132 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Midway |  | Y - 23
116630237 | T2 EI TULE-SPRINGVILLE 013/004 RPL SPLW | 43709294 | TULE-SPRINGVILLE | 013/004 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-118.913638 | 36.1096 | ETL.9040 | 40766132 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Midway |  | Y - 23
116630632 | T2 EI HAT CRK #1 WSTWD 018/363 RPL STRW | 31426976 | HAT CREEK #1-WESTWOOD | 018/363 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.28891 | 40.7535 | ETL.7030 | 40601610 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain
116630895 | T2 EI MRR BAY-SLR SW STA #1 0/4 REPAINT | 43760751 | MORRO BAY-SOLAR SW STA #1 | 000/004 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | South | WSIP | FSRP | [5 empty] | '-120.847476 | 35.3758 | ETL.5300 | 40762339 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Pismo Beach |  | Y - 10
116631065 | DI MORRO BAY-SLO #1 115KV 0/2 INST BOLTS | 43751755 | MORRO BAY-SAN LUIS OBISPO #1 | 000/002 | ICS | E | Pre-2020_(9a) Other ignition related |  |  |  |  | LATE | South | WSIP | [6 empty] | '-120.853292 | 35.376 | ETL.2810 | 40662103 | Hardware-Steel | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Pismo Beach |  | Y - 12
116631066 | T2 EI COLGATE-PALERMO 17/342 RPL STRW | 31423185 | COLGATE-PALERMO | 017/342 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.435171 | 39.4366 | ETL.6500 | 40814371 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
116631682 | T2 EI BRDGVL-CTNWD 064/466 RPR FOND | 43723480 | BRIDGEVILLE-COTTONWOOD | 064/466 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.439682 | 40.4048 | ETL.1110 | 40764797 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Eureka |  |  | 2019-05-31
116631926 | T2 EI OLEUM-G #1 006/042 RPNT TWR | 43752220 | OLEUM-G #1 | 006/042 | ICS | E | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.258787 | 37.9713 | ETL.3150 | 40646300 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  | Y - 8
116631964 | T2 EI TSL-LS BNS #1 026/120 INST ZEENA | 44598403 | TESLA-LOS BANOS #1 | 026/120 | ICB | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-121.203623 | 37.4642 | ETL.6100 | 40592674 | Raptor Guard-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 593 | Victor |  | Y - Prog Multi
116632198 | T2 EI TULE-SPRINGVILLE 18/013 RPL INSS | 31430415 | TULE-SPRINGVILLE | 018/013 | 93I | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-118.8254706 | 36.1184 | ETL.9040 | 40694902 | Insulator-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Midway |  | Y - 23
116632265 | T2 TSL-MTCLF 018/074 INS HRDT |  | TESLA-METCALF | 018/074 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-121.63959 | 37.4526 | ETL.6110 | 40761170 | Hardware-Tower | Missing | Install |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 3
116632501 | T2 DI SOBRANTE R #1 4/29 RPR STRT | 43727738 | SOBRANTE-R #1 | 004/029 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.283829 | 37.9197 | ETL.3770 | 40857827 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 1
116632525 | T2 EI RND MT-TBL MT #2 62/261 REPAINT | 44302501 | ROUND MTN-TABLE MTN #2 | 062/261 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.827893 | 39.921 | ETL.6070 | 40595252 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
116632535 | T2 EI RND MT-TBL MT #2 62/261 RPL SPLS | 44305720 | ROUND MTN-TABLE MTN #2 | 062/261 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.827893 | 39.921 | ETL.6070 | 40595252 | Splice-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
116632538 | T2 EI TULE-SPRINGV 026/005 RPR ANCHOR | 43795035 | TULE-SPRINGVILLE | 026/005 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  | CANCEL/CNCL | TR2 | LATE | South | WSIP | [6 empty] | '-118.71664 | 36.1602 | ETL.9040 | 40749766 | Anchor-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Midway |  | Y - 23 | USFS
116632539 | T2 EI TULE-SPRINGVILLE 26/010 RPL POLE | 31429415 | TULE-SPRINGVILLE | 026/010 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-118.711853 | 36.1615 | ETL.9040 | 40586486 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Midway |  | Y - 23
116632593 | T2 EI RND MT-TBL MT #2 40/183 RPL SPLS | 44305720 | ROUND MTN-TABLE MTN #2 | 040/183 | ICS | E | Pre-2020_(2) High fire spread TD |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Clearance Cancelled by GCC | 2021 - Cancelled by ISO | '-121.927069 | 40.2273 | ETL.6070 | 40658606 | Splice-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Released
116632903 | T2 EI TESLA-NEWARK #1 11/063 RPR FOND |  | TESLA-NEWARK #1 | 011/063 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-121.749816 | 37.6477 | ETL.5720 | 40650721 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog Multi
116633187 | T2 EI RND MT-TBL MT #2 53/231 RPR CONS | 44305720 | ROUND MTN-TABLE MTN #2 | 053/231 | ICS | E | Pre-2020_(2) High fire spread TD |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Clearance Cancelled by GCC | 2021 - Cancelled by ISO | '-121.876613 | 40.036 | ETL.6070 | 40595135 | Conductor-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
116633216 | T2 EI TESLA-NEWARK #2 11/076 RPR FOND |  | TESLA-NEWARK #2 | 011/076 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-121.750427 | 37.6479 | ETL.5354 | 41152621 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog Multi
116633254 | EI TESLA-NEWARK #1 012/067 RPR FOND |  | TESLA-NEWARK #1 | 012/067 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-121.76233 | 37.641 | ETL.5720 | 40810297 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog Multi
116633336 | T2 EI RND MTN-TBL MTN#2 53/230 RPR CONS | 43790346 | ROUND MTN-TABLE MTN #2 | 053/230 | ICS | E | Pre-2020_(2) High fire spread TD |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Clearance Cancelled by GCC | 2021 - Cancelled by ISO | '-121.877867 | 40.0394 | ETL.6070 | 40592104 | Conductor-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
116633458 | T2 EI TESLA-NEWARK #2 11/076 PNT TWR | 43753285 | TESLA-NEWARK #2 | 011/076 | ICS | E | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-121.750427 | 37.6479 | ETL.5354 | 41152621 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  | Y - Prog Multi
116634405 | T2 EI TULE-SPRINGVILLE 25/010 RPR GYWW | 43708346 | TULE-SPRINGVILLE | 025/010 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-118.727579 | 36.1569 | ETL.9040 | 40609662 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Midway |  | Y - 23 | USFS
116634411 | T2 EI TULE-SPRINGVILLE 25/007 RPR GYWW | 43708346 | TULE-SPRINGVILLE | 025/007 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-118.730133 | 36.1563 | ETL.9040 | 40807811 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Midway |  | Y - Prog Multi
116634712 | T2 EI BRDGVL-CTNWD 060/435 RPR FOND | 43722519 | BRIDGEVILLE-COTTONWOOD | 060/435 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.361221 | 40.3718 | ETL.1110 | 40586445 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Eureka |  |  | 2019-05-31
116634835 | T2 EI TULE-SPRINGVILLE 25/002 RPL POLE | 31429415 | TULE-SPRINGVILLE | 025/002 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-118.73622 | 36.1544 | ETL.9040 | 40655176 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Midway |  | Y - 23 | USFS
116635408 | T2 EI BRDGVLE-CTNWD 063/455 RPR FOND | 43722519 | BRIDGEVILLE-COTTONWOOD | 063/455 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.414395 | 40.3894 | ETL.1110 | 40586447 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Eureka |  |  | 2019-05-31
116635652 | T2 EI RO MTN-T MTN #2 30/145 BENT STEEL | 44003390 | ROUND MTN-TABLE MTN #2 | 030/145 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Internal Process | Circuit Based Scheduling | '-121.936194 | 40.374 | ETL.6070 | 40759760 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
116635848 | T3 EI FULTON-IGNAC #1 011/062 PAINT | 43720618 | FULTON-IGNACIO #1 | 011/062 | ICS | E | Pre-2020_(9a) Other ignition related |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.586556 | 38.4527 | ETL.4680 | 40681566 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Lakeville |  |  | 2019-04-30
116635974 | T2 EI PITTS-TESLA #1 007/032 HANGER | 44238805 | PITTSBURG-TESLA #1 | 007/032 | ICS | E | Pre-2020_(5) TD tag on other lines |  | TLN/TLQ error |  | TR2 | LATE | Central | WSIP | [6 empty] | '-121.86573 | 37.9503 | ETL.5510 | 40661559 | Hardware-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  | Y - Prog Multi
116636070 | T2 EI BRDGVLE-CTNWD 063/458 RPR FOND | 43722519 | BRIDGEVILLE-COTTONWOOD | 063/458 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.419145 | 40.3914 | ETL.1110 | 40759382 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Eureka |  |  | 2019-05-31
116636118 | T2 EI MLN-RND MT #2 059/294 RPL INSS | 31439323 | MALIN-ROUND MTN #2 | 059/294 | 93K | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.6425341 | 41.2208 | ETL.6020 | 40792520 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  | Yes
116636427 | T2 EI MIDWAY-WHIRL 51/209 PNT MMBR | 44637106 | MIDWAY-WHIRLWIND | 051/209 | ICS | E | Pre-2020_(1b) Lines with special commitments | Budget Owner (Paint) |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-118.702835 | 35.0797 | ETL.6030 | 40871795 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Midway |  | Y - 4
116637200 | EI TESLA-NEWARK #1 012/066 RPR FOND |  | TESLA-NEWARK #1 | 012/066 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-121.75969 | 37.6424 | ETL.5720 | 40810878 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog Multi
116637214 | EI TESLA-NEWARK #1 012/066 RPL HRDT |  | TESLA-NEWARK #1 | 012/066 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-121.75969 | 37.6424 | ETL.5720 | 40810878 | Hardware-Tower | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog Multi
116637408 | T2 EI OLEUM-G 001/010 RPR STRT | 44229259 | OLEUM-G #1 | 001/010A | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.23422 | 38.0385 | ETL.3150 | 40577230 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 6
116637461 | T2 EI OLEUM-G 001/010 RPL ANCS |  | OLEUM-G #1 | 001/010A |  | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.23422 | 38.0385 | ETL.3150 | 40577230 | Anchor-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLQ | Tower | Expense |  | Bay |  | Y - 6
116637623 | T2 EI NORTH DUBLIN-VNYD 2/013 RPR CONS | 43753297 | NORTH DUBLIN-VINEYARD | 002/013 | ICS | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-121.8049387 | 37.752 | ETL.4501 | 42572250 | Conductor-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - Prog Multi
116637700 | T2 EI TESLA-NEWARK #1 11/065 RPR FOND |  | TESLA-NEWARK #1 | 011/065 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-121.756349 | 37.6442 | ETL.5720 | 40761982 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog Multi
116637710 | T2 EI OLEUM-G #1 1/010B REPLUMB STRT | 44103087 | OLEUM-G #1 | 001/010B | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.234157 | 38.0385 | ETL.3150 | 40740544 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 6
116637752 | T2 EI TESLA-NEWARK #2 12/086 RPR FOND | 43753286 | TESLA-NEWARK #2 | 012/086 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-121.776642 | 37.6338 | ETL.5354 | 41152631 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 7
116637958 | T2NT EI MALIN-RND MTN #2 090/460B CANCEL | 44305271 | MALIN-ROUND MTN #2 | 090/460B | ICS | F | Pre-2020_(1b) Lines with special commitments | Budget Owner (Paint) |  | CANCEL/CNCL | TR2 | WECC | North Valley | WSIP | [6 empty] | '-121.91631 | 40.8563 | ETL.6020 | 41162773 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
116638298 | EI TESLA-NEWARK #2 020/130 RPR FOND |  | TESLA-NEWARK #2 | 020/130 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-121.874932 | 37.566 | ETL.5354 | 41152676 | Foundation/Concrete-Tower | Earth Covered Tower | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 10
116638323 | T2 EI HAT CRK #1-WSTWD 033/643 RPL STRW | 31456189 | HAT CREEK #1-WESTWOOD | 033/643 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.100832 | 40.598 | ETL.7030 | 40600253 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain
116638553 | T2 EI LAS POSITAS-NEWARK 4/032 RPR FOND |  | LAS POSITAS-NEWARK | 004/032 | ICQ | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-121.754265 | 37.646 | ETL.4980 | 40595240 | Foundation/Concrete-Tower | Earth Covered Tower | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog Multi
116638800 | DISTRIBUTION | 43749776 | LONE STAR TAP | 000/005 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-122.191842 | 37.0257 | ETL.6231 | 40770680 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing
116638911 | T2 DI CARIBOU-PALERMO :22/182 BURY MEMB | 44069454 | CARIBOU-PALERMO | :022/182 | ICQ | E | Pre-2020_(2) High fire spread TD |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.37803 | 39.8724 | ETL.3190 | 40738807 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
116638983 | T2 DI SOBRANTE G #1 3/28 HRDD INST |  | SOBRANTE-"G" #1 | 003/028 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-122.283917 | 37.9199 | ETL.3720 | 40857869 | Hardware-Tower | Missing | Install |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  | 2019-05-15
116639510 | T2 EI TULE-SPRING 013/013 RPL SPLW | 43709294 | TULE-SPRINGVILLE | 013/013 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-118.903194 | 36.1099 | ETL.9040 | 40663629 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Midway |  | Y - 23
116639744 | T2 DI KRKHFF-CLVS-SNGER #1 4/28 RPR FOND | 43709693 | KERCKHOFF-CLOVIS-SANGER #1 | 004/028 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | South | WSIP | FSRP | [5 empty] | '-119.576041 | 37.0105 | ETL.1890 | 40863764 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - Prog Multi
116639746 | T2 DI KRKHFF-CLVS-SNGER #1 4/27 RPR FOND | 43709693 | KERCKHOFF-CLOVIS-SANGER #1 | 004/027 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | South | WSIP | FSRP | [5 empty] | '-119.5752 | 37.0117 | ETL.1890 | 40806740 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - Prog Multi
116640876 | T2 EI TULE-SPRINGVILLE 018/020 REPL STRW | 31429415 | TULE-SPRINGVILLE | 018/020 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-118.822913 | 36.1184 | ETL.9040 | 40609654 | Structure-Wood | Rotten | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Midway |  |  | VRF (4-5 Months)
116640928 | T2 TULE-SPRINGVILLE 024/007 REPL STRW | 31429415 | TULE-SPRINGVILLE | 024/007 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-118.747395 | 36.152 | ETL.9040 | 40821823 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Midway |  | Y - 23 | USFS
116640932 | T2 EI BRDGVLE-CTNWD 067/486 RPR FOND | 43723480 | BRIDGEVILLE-COTTONWOOD | 067/486 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.472681 | 40.4331 | ETL.1110 | 40765586 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Eureka |  |  | 2019-05-31
116640964 | T2 DI CLAY-MARTEL 32/488 RPL CRSW | 31429424 | CLAY-MARTEL | 032/488 | 93E | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.84163 | 38.4568 | ETL.8250 | 40904100 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Victor |  | Y - 33
116641832 | T3 DI GOLD HILL #1 024/359 RPL STRW | 31494685 | GOLD HILL #1 | 024/359 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.848809 | 38.5855 | ETL.6950 | 40876097 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
116642749 | T2 TESLA-NEWARK #2 013/087 REPL HRDT |  | TESLA-NEWARK #2 | 013/087 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-121.778911 | 37.6326 | ETL.5354 | 41152632 | Hardware-Tower | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 7
116653026 | T3 DI CARIBOU-PALERMO :030/244 RPR FOND | 44051417 | CARIBOU-PALERMO | :030/244 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.452619 | 39.7784 | ETL.3190 | 40758634 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
116654973 | T3NT DI CRIBU-PLERMO :030/244 PAINT STRT | 44304458 | CARIBOU-PALERMO | :030/244 | ICS | F | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.452619 | 39.7784 | ETL.3190 | 40758634 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
116671395 | T2 EI TESLA-NEWARK #1 011/064 RPR FOND |  | TESLA-NEWARK #1 | 011/064 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-121.752542 | 37.6462 | ETL.5720 | 40761431 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog Multi
116673129 | EI CRAZ CAN-SAL-SO #2 39/247 RPL SPLS | 43766021 | MOSS LANDING-SALINAS-SOLEDAD #2 | 039/247 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | South | WSIP | FSRP | [5 empty] | '-121.6038721 | 36.7471 | ETL.2910 | 40843949 | Splice-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Moss Landing |  | Y - 8 | 2019-07-15
116673297 | T3 DI CARIBOU-PALERMO 034/276 RPL INSS |  | CARIBOU-PALERMO | :034/276 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.479471 | 39.7247 | ETL.3190 | 40856088 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  | Yes
116673325 | T3NT DI DISTRIBUTION |  | LIMESTONE TAP | 001/023 | ICW | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR3 | LATE | North Valley | WSIP |  |  |  |  | Distribution |  | '-120.981012 | 38.6394 | ETL.6951 | 40827787 | Marker (i.e. signs)-Wood | Missing | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
116673373 | T2 EI BRDGVLE-CTNWD 066/476 RPR FOND | 43723480 | BRIDGEVILLE-COTTONWOOD | 066/476 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.45757 | 40.4165 | ETL.1110 | 40592244 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Eureka |  |  | 2019-05-31
116673392 | T3 DI CARIBOU-PLERMO :34/277 BURIED MEMB | 44051418 | CARIBOU-PALERMO | :034/277 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.479702 | 39.7233 | ETL.3190 | 40815592 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
116673576 | T3NT DI DISTRIBUTION |  | LIMESTONE TAP | 001/026 | ICW | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR3 | LATE | North Valley | WSIP |  |  |  |  | Distribution |  | '-120.98146 | 38.6374 | ETL.6951 | 40875182 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
116674182 | T2 EI TEJON-LEBEC 009/154 RPL POLE | 31469596 | TEJON-LEBEC | 009/154 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-118.918712 | 34.8935 | ETL.9250 | 40654418 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Midway |  | Y - 10
116674269 | T2 DI KRCKHOF-CLVS-SNGR #1 5/34 RPR FOND | 43709693 | KERCKHOFF-CLOVIS-SANGER #1 | 005/034 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | South | WSIP | FSRP | [5 empty] | '-119.585899 | 36.997 | ETL.1890 | 40753732 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - Prog Multi
116674392 | T2 EI TRACY-LOS BANOS 31/148 RPL RPTS |  | TRACY-LOS BANOS | 031/148 | ICB | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-121.209138 | 37.4756 | ETL.6130 | 40873336 | Raptor Guard-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 593 | Victor |  | Y - Prog Multi
116676006 | DI CLAY-MARTEL 031/481 R INS GYW | 43727747 | CLAY-MARTEL | 031/481 | ICW | E | Pre-2020_(9a) Other ignition related |  |  |  |  | LATE | Central | WSIP | FSRP | [7 empty] | ETL.8250 | 44270320 | Guy Wire-Wood | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 33
116676043 | T2 EI TESLA-NEWARK #1 010/060 RPR FOND |  | TESLA-NEWARK #1 | 010/060 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-121.739044 | 37.6535 | ETL.5720 | 40591031 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog Multi
116676340 | DI CLAY-MARTEL 031/481C S GYWW | 43727747 | CLAY-MARTEL | 031/481 | ICW | E | Pre-2020_(9a) Other ignition related |  |  |  |  | LATE | Central | WSIP | FSRP | [7 empty] | ETL.8250 | 44270319 | Guy Wire-Wood | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 33
116678973 | T2 EI TESLA-METCALF 26/108 INST HRDT |  | TESLA-METCALF | 026/108 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-121.676142 | 37.3434 | ETL.6110 | 40863783 | Hardware-Tower | Missing | Install |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog Multi
116678974 | T2 EI TESLA-METCALF 26/108 RPR FOND |  | TESLA-METCALF | 026/108 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-121.676142 | 37.3434 | ETL.6110 | 40863783 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Multi Prog
116679131 | T2 MALIN-ROUND MTN #2 64/322 RPR HRDS | 43621093 | MALIN-ROUND MTN #2 | 064/322 | ICQ | E | Pre-2020_(1b) Lines with special commitments |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.697954 | 41.1566 | ETL.6020 | 40684085 | Hardware-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
116679904 | T2 DI CARIBOU-PLRM :008/68 RPR FOND | 44059014 | CARIBOU-PALERMO | :008/068 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.247789 | 40.0076 | ETL.3190 | 40910310 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
116680308 | T3 DI DRUM-HIGGINS 17/148 PNT STRS | 43738143 | DRUM-HIGGINS | 017/148 | ICS | E | Pre-2020_(9a) Other ignition related |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.017625 | 39.1368 | ETL.4393 | 40913044 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes
116680648 | T2 EI MALIN-RND MT #2 57/284 WASH INSS | 43754876 | MALIN-ROUND MTN #2 | 057/284 | ICD | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.624443 | 41.2431 | ETL.6020 | 40759857 | Insulator | Contaminated | Helicopter Wash | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 626 | Table Mountain |  |  | Yes
116680671 | T3 DI CRSTA-RIO OSO 012/99 PNT TWR | 43708739 | CRESTA-RIO OSO | 012/099 | ICS | E | Pre-2020_(9a) Other ignition related |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.451302 | 39.7859 | ETL.4590 | 40910125 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
116680913 | T2 EI TSLA-MTCLF 016/068 RPR GYWS | 43753282 | TESLA-METCALF | 016/068 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  | Tower guy | TR2 | LATE | Central | WSIP | [6 empty] | '-121.629322 | 37.4785 | ETL.6110 | 40863776 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  | Y - 3 | 2019-06-04
116680958 | T3NT EI MB-SOLAR SS #1 26/115 REPA FOND | 43685817 | MORRO BAY-SOLAR SW STA #1 | 026/115 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  | TR3 | LATE | South | WSIP | [6 empty] | '-120.391434 | 35.3676 | ETL.5300 | 40753271 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Pismo Beach |  | Y - 11
116681160 | SAN MATO-HILLSLE JCT 001/026 rmv splices | 44574935 | SAN MATEO-HILLSDALE JCT | 001/026 | ICK | B | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) |  |  |  |  | LATE | Central | Non-WSIP | [6 empty] | '-122.318544 | 37.5659 | ETL.7950 | 40865014 | Auto Guy Wire Splice-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 515 | Bay |  | Y - 6
116681164 | T2 HUMBOLDT-TRINITY 092/001L REPL STRW | 31433540 | HUMBOLDT-TRINITY | 092/001 | 70Y | E | Pre-2020_(2) High fire spread TD |  |  |  | TR2 | LATE | North Coast | WSIP |  |  |  |  | Project | 2021 HUMBOLDT-TRINITY | '-123.725388 | 40.7504 | ETL.1820 | 44769615 | Structure-Wood | Rotten | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka
116681232 | T2 EI MALIN-ROUND MTN#2 56/279 CLN INSS | 43754876 | MALIN-ROUND MTN #2 | 056/279 | ICD | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.615265 | 41.2544 | ETL.6020 | 40870730 | Insulator | Contaminated | Helicopter Wash | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 626 | Table Mountain |  |  | Yes
116681396 | T2 EI CONTRA CST-LS PSTS 14/91 INST HRDT |  | CONTRA COSTA-LAS POSITAS | 014/091 | ICQ | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-121.725024 | 37.792 | ETL.4510 | 40590632 | Hardware-Tower | Missing | Install |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 6
116681465 | T2 EI TRCY-LS BNS 031/146 RPL ANMS | 43844594 | TRACY-LOS BANOS | 031/146 | ICB | F | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-121.211204 | 37.4791 | ETL.6130 | 40812029 | Raptor Guard-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 593 | Victor |  | Released
116681904 | EI STNSLUS-NWRK#1(12KV)92/611 INST ATCG | 31454925 | STANISLAUS-NEWARK #1 (12KV) | 092/611 | 93A | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-121.872223 | 37.5855 | ETL.3850 | 40602897 | Structure-Tower | Anti-Climbing Guard | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Capital | 988 | Bay |  | Y - 6
116681935 | T3 EI MNT VT-JFRSN #1 014/060 RPR FOND |  | MONTA VISTA-JEFFERSON #1 | 014/060 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.290554 | 37.3945 | ETL.5220 | 40602700 | Foundation/Concrete-Tower | Earth Covered Tower | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog Multi
116682008 | T2 DI CLAY-MARTEL 32/490 RPL STRW | 31430278 | CLAY-MARTEL | 032/490 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.842238 | 38.4581 | ETL.8250 | 40904098 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 33
116682310 | T2 DI CLAY-MARTEL 32/493 RPL STRW | 31498114 | CLAY-MARTEL | 032/493 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.843471 | 38.4608 | ETL.8250 | 40904095 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 33
116682464 | T2 DI BALCH SANGER 6/40 INS HRDT | 43709727 | BALCH-SANGER | 006/040 | ICS | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-119.17294 | 36.886 | ETL.1050 | 40585030 | Hardware-Steel | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Fresno |  | Y - 17
116682552 | T2 EI MALIN-RND MTN#2 064/321 RPR INSS | 43621093 | MALIN-ROUND MTN #2 | 064/321 | ICQ | E | Pre-2020_(1b) Lines with special commitments |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.696342 | 41.1579 | ETL.6020 | 40592575 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
116682616 | T2 EI IGNACIO-SOBRANTE 045/216 RMV NEST | 44598164 | IGNACIO-SOBRANTE | 045/216 | ICS | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-122.20315 | 37.9385 | ETL.4920 | 40818338 | Structure-Steel | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  |  | EBMUD
116682646 | T2 DI CARIBOU-PLRM :022/185 RPR INSS | 44304495 | CARIBOU-PALERMO | :022/185 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP |  |  |  | Field Operations |  | '-121.380738 | 39.8706 | ETL.3190 | 40757284 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain
116682750 | T2 DI CARIBOU-PLRM :022/186 RPR STRT | 44069454 | CARIBOU-PALERMO | :022/186 | ICQ | E | Pre-2020_(2) High fire spread TD |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.385577 | 39.8688 | ETL.3190 | 40806164 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
116682767 | T2 EI MALIN-ROUND MTN #2 65/326 RPR INSS | 43621093 | MALIN-ROUND MTN #2 | 065/326 | ICQ | E | Pre-2020_(1b) Lines with special commitments |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.708607 | 41.1482 | ETL.6020 | 40822888 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
116682815 | T2 DI CARIBOU-PLRM :022/186 RPR FOND | 44069454 | CARIBOU-PALERMO | :022/186 | ICQ | E | Pre-2020_(3) On high spread structure |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.385577 | 39.8688 | ETL.3190 | 40806164 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
116683111 | T2 DI CLAY-MARTEL 18/263 STRW REPLACE | 31460367 | CLAY-MARTEL | 018/263 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.919062 | 38.3409 | ETL.8250 | 40663970 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 33
116683171 | T2 EI MALIN-ROUND MTN#2 89/453 COMPLETE | 43621093 | MALIN-ROUND MTN #2 | 089/453 | ICQ | E | Pre-2020_(1b) Lines with special commitments |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.913202 | 40.8756 | ETL.6020 | 40657564 | Hardware-Steel | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
116683191 | T2 EI MALIN-ROUND MTN#2 89/453 CANCEL | 43754876 | MALIN-ROUND MTN #2 | 089/453 | ICD | E | Pre-2020_(1b) Lines with special commitments |  |  | CANCEL/CNCL | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.913202 | 40.8756 | ETL.6020 | 40657564 | Insulator | Contaminated | Helicopter Wash | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 626 | Table Mountain |  |  | Yes
116683302 | T2 DI CLAY-MARTEL 024/346 RPL STRW | 31422461 | CLAY-MARTEL | 024/346 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.814502 | 38.3602 | ETL.8250 | 40691770 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 33
116683309 | T2 DI CLAY-MARTEL 27/408 RPL POLE | 31460367 | CLAY-MARTEL | 027/408 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP |  |  |  | REJECT: Crew reported they were unable to complete work. Scope of work has been changed. Pleae resubmit once new scope of work has been completed. |  |  | '-120.81329 | 38.394 | ETL.8250 | 40904047 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 33
116683867 | T2 EI OLEUM-G #1 10/066 REPAINT | 43752220 | OLEUM-G #1 | 010/066 | ICS | E | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.284407 | 37.92 | ETL.3150 | 40804791 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  | Y - 8
116684126 | T3 EI TGR CRK-VLLY SPRNGS 12/98 PNT STRS | 43708739 | CRESTA-RIO OSO | 012/098 | ICS | E | Pre-2020_(9a) Other ignition related |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.451798 | 39.7874 | ETL.4590 | 40910124 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
116684136 | T3 EI SBRNT-G #2 003/019 WSH INSS | 43895436 | SOBRANTE-"G" #2 | 003/019 | ICS | E | Pre-2020_(5) TD tag on other lines |  |  | Likely MAT error - delink to correct | TR3 | LATE | Central | WSIP | [6 empty] | '-122.259498 | 37.9137 | ETL.3730 | 40878764 | Insulator | Contaminated | Ground Wash | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 622 | Bay
116685114 | DI IONE TAP 3/12 RPR STRW | 43844198 | IONE TAP | 003/012 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-120.952317 | 38.3746 | ETL.8253 | 40644753 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 9
116685590 | T2 EI MALIN-RND MT #2 65/325 WASH INSS | 43754876 | MALIN-ROUND MTN #2 | 065/325 | ICD | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.705665 | 41.1505 | ETL.6020 | 40759608 | Insulator | Contaminated | Helicopter Wash | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 626 | Table Mountain |  |  | Yes
116685718 | T3NT DI ROCK CRK-POE 16/112L INS MRKS | 43724474 | ROCK CREEK-POE | 016/112 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.479277 | 39.7199 | ETL.5630 | 44727542 | Marker (i.e. signs)-Steel | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
116685829 | T2 DI PLACER-DEL MAR 4/90 RMV VEGN |  | PLACER-DEL MAR | 004/090 | HNA | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.136978 | 38.8621 | ETL.7800 | 40809982 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  | Yes
116686117 | T2 VOLTA-SOUTH 001/040 REFRAME | 31471616 | VOLTA-SOUTH | 001/040 | 93E | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-121.8726 | 40.4359 | ETL.8300 | 40826968 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  | Yes
116686163 | T2 DI VOLTA-SOUTH 4/100 REFRAME | 31453744 | VOLTA-SOUTH | 004/100 | 93E | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.878295 | 40.399 | ETL.8300 | 40667414 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  | Yes
116686173 | T2 COLEMAN-SOUTH 005/108 RPL POLE | 31515568 | COLEMAN-SOUTH | 005/108 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-121.967732 | 40.4031 | ETL.6450 | 40817388 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Need New ERTC
116686272 | T3 DI TIGR CREK-VLLY SPRNG 8/62 PAINT | 43830095 | TIGER CREEK-VALLEY SPRINGS | 008/062 | ICS | E | Pre-2020_(9a) Other ignition related | Budget Owner (Paint) |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-120.620443 | 38.3994 | ETL.5790 | 40651153 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - Prog Multi
116686377 | T2 EI ROCK CREEK-POE 1/11 RPL INSS | 31431457 | ROCK CREEK-POE | 001/011 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.3628 | 39.8992 | ETL.5630 | 40616276 | Insulator-Steel | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  | Yes
116686380 | T2NT EI MTCLF-GRN VLLY 8/055 REPAINT | 44300678 | METCALF-GREEN VALLEY | 008/055 | ICS | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | South | WSIP | FSRP | [5 empty] | '-121.673354 | 37.1399 | ETL.2540 | 40761851 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Moss Landing |  | Y - 10
116686386 | EI MORAGA-LAKEWOOD 008/063 REPR FOND |  | MORAGA-LAKEWOOD | 008/063 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-122.107483 | 37.8796 | ETL.3741 | 40659422 | Foundation/Concrete-Tower | Earth Covered Tower | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 7
116686760 | T2 EI MLIN-RND MTN #2 048/236 RPL HRDS | 43621093 | MALIN-ROUND MTN #2 | 048/236 | ICQ | E | Pre-2020_(1b) Lines with special commitments |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.529495 | 41.3597 | ETL.6020 | 40817693 | Hardware-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
116687073 | T3 EI MNT VST-JFFRSN #1 15/64 RPR FOND |  | MONTA VISTA-JEFFERSON #1 | 015/064 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.293752 | 37.4037 | ETL.5220 | 40760857 | Foundation/Concrete-Tower | Earth Covered Tower | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog Multi
116687201 | T2 EI RND MTN-TBL MTN #1 33/161 RPR STRT | 43848514 | ROUND MTN-TABLE MTN #1 | 033/161 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Internal Process | Circuit Based Scheduling | '-121.934487 | 40.3228 | ETL.6060 | 40581216 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
116687486 | EI TESLA-LOS BANOS #1 24/109 RPR FOND | 43844591 | TESLA-LOS BANOS #1 | 024/109 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  |  | LATE | Central | WSIP | FSRP | [5 empty] | '-121.22292 | 37.4941 | ETL.6100 | 40863461 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - Prog Multi
116687579 | T2 EI RND MN-TBLE MTN #2 000/006 RMV VEG |  | ROUND MTN-TABLE MTN #2 | 000/006 | HNA | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.928734 | 40.7936 | ETL.6070 | 40817840 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Table Mountain |  |  | Yes
116687671 | T2 EI OLEUM-G #1 010/068 RPNT TWR | 43752220 | OLEUM-G #1 | 010/068 | ICS | E | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.288972 | 37.9192 | ETL.3150 | 40857750 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  | Y - 8
116687779 | T2 EI VACA-SUISUN 11/082 PNT/COATNG STRS | 43740515 | VACA-SUISUN | 011/082 | ICS | F | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.058581 | 38.2971 | ETL.4070 | 40668976 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento
116688254 | T3 EI OLEUM-G #1 010/065 RPNT STRT | 43726138 | OLEUM-G #1 | 010/065 | ICS | E | Pre-2020_(9a) Other ignition related | Budget Owner (Paint) |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.283518 | 37.9207 | ETL.3150 | 40746019 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - 8 | 2019-04-24
116688441 | T2 DI SOBRANTE-MORAGA 000/008 RPR FOND | 44261935 | SOBRANTE-MORAGA | 000/008 | ICQ | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.202084 | 37.9027 | ETL.3742 | 41135450 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 7
116688650 | T2 EI MALIN-ROUND MTN #2 89/455 COMPLETE | 43621093 | MALIN-ROUND MTN #2 | 089/455 | ICQ | E | Pre-2020_(1b) Lines with special commitments |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.914529 | 40.8672 | ETL.6020 | 40752315 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
116688801 | T2 DI IONE TAP 0/005 RPR CRSW | 43844195 | IONE TAP | 000/005 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.918855 | 38.3446 | ETL.8253 | 40765829 | Crossarm-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 10
116688826 | T2 DI PARKWAY-MORAGA 010/059 RPR STRT | 43753156 | PARKWAY-MORAGA | 010/059 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  | Likely MAT error - delink to correct | TR2 | LATE | Central | WSIP | [6 empty] | '-122.23148 | 37.9973 | ETL.5930 | 40763001 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 7
116689190 | DI VALLEY SPRINGS #1 3/057 RPR STRW | 43831016 | VALLEY SPRINGS #1 | 003/057 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-120.813024 | 38.1959 | ETL.8210 | 40909217 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 23
116689191 | DI VALLEY SPRINGS #1 3/058 RPR STRW | 43831082 | VALLEY SPRINGS #1 | 003/058 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-120.813671 | 38.1953 | ETL.8210 | 40909218 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 23
116689194 | T2 DI METCALF-HICKS 5/027 RPL CONN | 43753590 | METCALF-HICKS 1 & 2 (IDLE) | 005/027 | ICM | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-121.830672 | 37.2261 | ETL.4317 | 41167702 | Connector | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 534 | Bay |  | Y - Prog Multi
116689197 | T2 EI RND MTN-CTTNWD#3 046/397 RPR CONS | 43755803 | ROUND MTN-COTTONWOOD #3 | 046/397 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.128712 | 40.5637 | ETL.5650 | 40815940 | Conductor-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
116689214 | T3 EI TEMBLOR-SLO+ 42/241 REPA STUCTURE | 43763689 | TEMBLOR-SAN LUIS OBISPO | 042/241 | ICQ | E | Pre-2020_(9a) Other ignition related | Budget Owner (Paint) |  |  | TR3 | LATE | South | WSIP | [6 empty] | '-120.411638 | 35.3687 | ETL.3960 | 40585711 | Structure-Tower | Paint/Coating | Repaint | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Pismo Beach
116689348 | T2 EI MLN-RND MTN #2 078/395B INS MRKS | 43621093 | MALIN-ROUND MTN #2 | 078/395B | ICQ | F | Pre-2020_(1b) Lines with special commitments |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.890339 | 41.0353 | ETL.6020 | 41162682 | Marker (i.e. signs)-Steel | No Good/Out of Stdrd | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Table Mountain |  |  | Yes
116690543 | T2 EI MLN-RND MTN #2 078/395A INS MRKS | 43621093 | MALIN-ROUND MTN #2 | 078/395A | ICQ | F | Pre-2020_(1b) Lines with special commitments |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.890182 | 41.0353 | ETL.6020 | 41162685 | Marker (i.e. signs)-Steel | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Table Mountain |  |  | Yes
116690545 | T2 EI TESLA-METCALF 023/099 RPR GYWS | 43753282 | TESLA-METCALF | 023/099 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  | Tower guy | TR2 | LATE | Central | WSIP | [6 empty] | '-121.674756 | 37.3789 | ETL.6110 | 40863439 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  | Y - Prog Multi
116690554 | T2 EI TESLA-METCALF 023/099 BENT MEMBER |  | TESLA-METCALF | 023/099 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-121.674756 | 37.3789 | ETL.6110 | 40863439 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Multi Prog
116690568 | T2 EI CRESTA-RIO OSO 23/182 PNT STRT | 43708739 | CRESTA-RIO OSO | 023/182 | ICS | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.509488 | 39.6459 | ETL.4590 | 40910190 | Structure-Steel | Paint/Coating | Repaint | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
116690598 | T2 EI ROUND MTN-CO #2 32/276 RPL INSS | 31435968 | ROUND MTN-COTTONWOOD #2 | 032/276 | 93K | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.14216 | 40.5744 | ETL.5640 | 40844224 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  | Yes
116690606 | T2 DI MORAGA-LAKEWOOD 10/078 RPL SPLS | 43752130 | MORAGA-LAKEWOOD | 010/078 | ICS | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.134703 | 37.8653 | ETL.3741 | 40857633 | Splice-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - 6
116690607 | T2 DI MORAGA-LAKEWOOD 10/078 RPL INSS | 31451424 | MORAGA-LAKEWOOD | 010/078 | 93K | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.134703 | 37.8653 | ETL.3741 | 40880140 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - 6
116690608 | T2 DI MORAGA-LAKEWOOD 10/078 RPR CONS | 43752130 | MORAGA-LAKEWOOD | 010/078 | ICS | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.134703 | 37.8653 | ETL.3741 | 40857633 | Conductor-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - 6
116690749 | T2 EI HIGGINS-BELL 33/251 RPR INSS | 43740275 | HIGGINS-BELL | 033/251 | ICS | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.042373 | 38.9618 | ETL.1412 | 40762676 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento
116690786 | EI TSL-NWRK #1 013/074 RPR FOND | 43753786 | TESLA-NEWARK #1 | 013/074 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-121.785225 | 37.6287 | ETL.5720 | 40761433 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 3
116690799 | T2 DI PKWY-MORAGA 8/046 RPR HRDT | 43683430 | PARKWAY-MORAGA | 008/046 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.233619 | 38.0277 | ETL.5930 | 40592005 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog Multi
116690926 | T2 EI HIGGINS-BELL 34/254 RPR INSS | 43740275 | HIGGINS-BELL | 034/254 | ICS | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.04283 | 38.9542 | ETL.1412 | 40869579 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes
116691031 | T2 DI SBRNT-GRZLY-CLRMT #1 1/14 RPR FOND |  | SOBRNTE-GRIZZLY-CLARMNT #1+ | 001/014 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-122.20099 | 37.8935 | ETL.3740 | 40857132 | Foundation/Concrete-Tower | Earth Covered Tower | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  | 2019-04-09
116691256 | T2 DI MORAGA-SN LEANDRO #1 8/58 RPR STRT | 44294404 | MORAGA-SAN LEANDRO #1 | 008/058 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.11931 | 37.7372 | ETL.2770 | 40857652 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 7
116691292 | T2 EI TSCDR-SN LS BSP 14/177 RPR FOND | 43766560 | ATASCADERO-SAN LUIS OBISPO | 014/177 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | South | WSIP | FSRP | [5 empty] | '-120.633657 | 35.275 | ETL.8490 | 40602390 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Pismo Beach |  | Y - 7
116691324 | T2 EI MLN-RD MTN #2 047/234 RPL INSS | 31439323 | MALIN-ROUND MTN #2 | 047/234 | 93K | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.5259319 | 41.3641 | ETL.6020 | 40789955 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  | Yes
116691357 | T2 DI IONE TAP 2/1 CRWS RPR | 43844195 | IONE TAP | 002/001 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.927115 | 38.3689 | ETL.8253 | 40580314 | Crossarm-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog Multi
116691359 | DI IONE TAP 3/14 INSW RPLC | 31430408 | IONE TAP | 003/014 | 93I | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-120.95451 | 38.3741 | ETL.8253 | 40773360 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Victor |  | Y - 9
116691493 | T2 DI IONE TAP 1/7 RPR GYWW | 43844195 | IONE TAP | 001/007 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.925828 | 38.3617 | ETL.8253 | 40804110 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog Multi
116691495 | T2 DI IONE TAP 1/7 RPR GWSW | 43844195 | IONE TAP | 001/007 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.925828 | 38.3617 | ETL.8253 | 40804110 | Auto Guy Wire Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog Multi
116691496 | T2 DI IONE TAP 1/7 RPR STRW | 43844195 | IONE TAP | 001/007 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.925828 | 38.3617 | ETL.8253 | 40804110 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog Multi
116691570 | DI IONE TAP 1/9 RPR STRW | 43796670 | IONE TAP | 001/009 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-120.926922 | 38.3645 | ETL.8253 | 40857174 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 9
116691837 | T2 DI PARKWAY-MORAGA 009/055 RPL HRDT | 43683430 | PARKWAY-MORAGA | 009/055 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  | Likely MAT error - delink to correct | TR2 | LATE | Central | WSIP | [6 empty] | '-122.233796 | 38.0051 | ETL.5930 | 40576197 | Hardware-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  | Y - Prog Multi
116691870 | T2 EI MALIN-RD MTN #2 066/330 RPL INSS | 31439323 | MALIN-ROUND MTN #2 | 066/330 | 93K | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.7173586 | 41.1412 | ETL.6020 | 40635012 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  | Yes
116691930 | T2 EI ATSCDRO-SLO 014/174 INST HRDT | 43766560 | ATASCADERO-SAN LUIS OBISPO | 014/174 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | South | WSIP | FSRP |  |  |  | Safety Reason | PAR SSD from 23-30 June, no work performed | '-120.630444 | 35.2813 | ETL.8490 | 40668420 | Hardware-Tower | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Pismo Beach |  | Y - 7
116692006 | T2 DI IONE TAP 2/002 RPL INSS | 31430408 | IONE TAP | 002/002 | 93I | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.92712 | 38.3694 | ETL.8253 | 40704123 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Victor |  | Y - 9
116692019 | T2 EI BCKS CRKRCK CRKC :000/001 RPR JUMS | 43742056 | BUCKS CREEK-ROCK CREEK-CRESTA | :000/001 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.346983 | 39.9057 | ETL.4430 | 40595003 | Jumper-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
116692175 | T2 EI TRACY-LOS BAN 30/143 INST CORONA | 43844596 | TRACY-LOS BANOS | 030/143 | ICS | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-121.218474 | 37.4895 | ETL.6130 | 40651827 | Conductor-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - Prog Multi
116692383 | T3 EI SOBRANTE-R #1 002/016 PAINT | 43727737 | SOBRANTE-R #1 | 002/016 | ICS | E | Pre-2020_(9a) Other ignition related | Budget Owner (Paint) |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.249227 | 37.9104 | ETL.3770 | 40804940 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay
116692486 | T2 EI MLIN-ROUND MTN #2 66/333 COMPLETE | 43754876 | MALIN-ROUND MTN #2 | 066/333 | ICD | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.724272 | 41.1358 | ETL.6020 | 40660397 | Insulator | Contaminated | Helicopter Wash | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 626 | Table Mountain |  |  | Yes
116692522 | T2 EI MALIN-RD MTN #2 067/336 RPL HRDT | 43621093 | MALIN-ROUND MTN #2 | 067/336 | ICQ | E | Pre-2020_(1b) Lines with special commitments |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.731535 | 41.13 | ETL.6020 | 40817705 | Hardware-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
116692525 | T2 EI MALIN-ROUND MTN #2 66/334 RPR STRT | 44110806 | MALIN-ROUND MTN #2 | 066/334 | ICS | E | 2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.726216 | 41.1342 | ETL.6020 | 40762173 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
116692559 | T2 EI MLN-RND MTN #2 050/250 RPR OPGW | 44305271 | MALIN-ROUND MTN #2 | 050/250 | ICS | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.557085 | 41.3259 | ETL.6020 | 40605576 | Shield Wire / OPGW-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
116693063 | T2 DI DVDE-VNDNBRG #1 2/018 RMV DBRW | 43769296 | DIVIDE-VANDENBERG #1 | 002/018 | ICW | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | South | WSIP | FSRP | [5 empty] | '-120.478655 | 34.8005 | ETL.8620 | 40576372 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - 4
116693274 | T2 EI POE-RIO OSO 38/252 RPL INSS | 31431911 | POE-RIO OSO | 038/252 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.520605 | 39.4406 | ETL.5540 | 40729675 | Insulator-Steel | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  | Yes
116693330 | T2 EI POE-RIO OSO 38/253 RPL INSS | 31431911 | POE-RIO OSO | 038/253 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.520329 | 39.4392 | ETL.5540 | 40685030 | Insulator-Steel | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  | Yes
116693373 | T2 EI RUND MTN-CTTNWD #3 58/531 RPL INSS | 31431455 | ROUND MTN-COTTONWOOD #3 | 058/531 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.256284 | 40.4095 | ETL.5650 | 40619627 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain
116693378 | T2 EI CRESTA-RIO OSO 38/254 RPL INSS | 31435732 | CRESTA-RIO OSO | 038/254 | 93K | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.519716 | 39.4361 | ETL.4590 | 40787727 | Insulator-Steel | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  | Yes
116693677 | T2 DI CTRA CSTA-MRGA #1 26/124 PAINT | 43753199 | CONTRA COSTA-MORAGA #1 | 026/124 | ICS | F | Pre-2020_(9a) Other ignition related | Budget Owner (Paint) |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-122.155519 | 37.8538 | ETL.5452 | 40804949 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  |  | 2019-04-16
116693678 | T2 DI CTRA CSTA-MRGA #1 26/125 RPR FOND |  | CONTRA COSTA-MORAGA #1 | 026/125 | ICQ | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-122.157489 | 37.852 | ETL.5452 | 40857894 | Foundation/Concrete-Tower | Earth Covered Tower | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 7 | 2019-04-16
116694303 | T2 EI RND MTN-TBL MTN #1 18/98 RMV VEGN | 44305409 | ROUND MTN-TABLE MTN #1 | 018/098 | ICS | F | Pre-2020_(9a) Other ignition related |  |  | Likely veg | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.943992 | 40.5342 | ETL.6060 | 40871647 | Structure-Steel | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
116704821 | T2 DI SBRNTE-GRZZLY-CLRMNT 1/15 REPAINT | 43752392 | SOBRNTE-GRIZZLY-CLARMNT #1+ | 001/015 | ICS | E | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.199121 | 37.8919 | ETL.3740 | 40580680 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  |  | 2019-04-09
116704830 | T2 DI CLAY-MARTEL 33/497 RPL STRW | 31498114 | CLAY-MARTEL | 033/497 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.844528 | 38.464 | ETL.8250 | 40912854 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 33
116704833 | T2 DI CLAY-MARTEL 33/499 RPR STRW | 43793351 | CLAY-MARTEL | 033/499 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.844892 | 38.4659 | ETL.8250 | 40912852 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 33
116704837 | T2 DI CLAY-MARTEL 33/500 RPR GYWW | 43793353 | CLAY-MARTEL | 033/500 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.845091 | 38.4667 | ETL.8250 | 40912851 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 33
116704838 | T2 DI CLAY-MARTEL 33/500 RPR STRW | 43793354 | CLAY-MARTEL | 033/500 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.845091 | 38.4667 | ETL.8250 | 40912851 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 33
116704839 | T2 DI CLAY-MARTEL 33/513 RPL STRW | 31430278 | CLAY-MARTEL | 033/513 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.844917 | 38.4759 | ETL.8250 | 40908884 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 33
116705040 | T2 DI CLAY-MARTEL 33/515 RPL PL | 31430278 | CLAY-MARTEL | 033/515 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.84474 | 38.4768 | ETL.8250 | 40908882 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 33
116705042 | T2 DI CLAY-MARTEL 33/516 RPL STRW | 31430278 | CLAY-MARTEL | 033/516 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.844608 | 38.4771 | ETL.8250 | 40908881 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 33
116705094 | T3 EI MRAGA-SN LNDRO 004/036 RPR FOND | 43753783 | MORAGA-SAN LEANDRO #1 | 004/036 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.126399 | 37.7877 | ETL.2770 | 40804654 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 10
116705301 | DI CRESTA-RIO OSO 40/262 RPL INSS | 31435732 | CRESTA-RIO OSO | 040/262 | 93K | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-121.516195 | 39.4186 | ETL.4590 | 40719840 | Insulator-Steel | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  | Yes
116705307 | DI POE-RIO OSO 040/264 WASH INSS | 43724322 | POE-RIO OSO | 040/264 | ICD | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-121.515393 | 39.4147 | ETL.5540 | 40761322 | Insulator | Contaminated | Ground Wash | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 622 | Table Mountain |  |  | Yes
116705371 | T3 DI ROCK CREEK-POE 11/79 RPR INSS | 43724474 | ROCK CREEK-POE | 011/079 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.451784 | 39.784 | ETL.5630 | 40866645 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
116705372 | T3NT DI ROCK CREEK-POE 11/79 INS MRKS | 43724474 | ROCK CREEK-POE | 011/079 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.451784 | 39.784 | ETL.5630 | 40866645 | Marker (i.e. signs)-Steel | No Good/Out of Stdrd | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
116705376 | T2 DI PARKWAY-MORAGA 10/63 RPL HRDT | 43683430 | PARKWAY-MORAGA | 010/063 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.224315 | 37.9882 | ETL.5930 | 40871592 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 7
116705789 | T2 DI VALLEY SPRINGS #1 7/134 STRW REPAI | 43831014 | VALLEY SPRINGS #1 | 007/134 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.855017 | 38.1536 | ETL.8210 | 40905597 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 23
116706970 | T2NT EI MALIN-RD MTN #2 067/338 RPL INSS | 31439323 | MALIN-ROUND MTN #2 | 067/338 | 93K | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.7368133 | 41.1258 | ETL.6020 | 40893466 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  | Yes
116706971 | T2 EI MALIN-RD MTN #2 066/332 COMPLETE | 31439323 | MALIN-ROUND MTN #2 | 066/332 | 93K | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.7222803 | 41.1373 | ETL.6020 | 40722246 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  | Yes
116706996 | T2 EI TESLA-MET 027/114 INST HRDT |  | TESLA-METCALF | 027/114 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-121.686896 | 37.3239 | ETL.6110 | 40753750 | Hardware-Tower | Missing | Install |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 3
116707001 | T3 EI DIABLO-GATES #1 1/012 RPR STUB | 43756059 | DIABLO-GATES #1 | 001/012 | ICS | E | Pre-2020_(9a) Other ignition related | Budget Owner (Paint) |  |  | TR3 | LATE | South | WSIP | [6 empty] | '-120.821032 | 35.2256 | ETL.5960 | 40664670 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Pismo Beach
116707154 | T3 EI RD MN-TBL MN #2 021/106 CANCEL | 43740169 | ROUND MTN-TABLE MTN #2 | 021/106 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  | CANCEL/CNCL | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.945532 | 40.5037 | ETL.6070 | 40818832 | Conductor-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
116707947 | T2 DI OLEUM-G #1 3/025 RPR FOND |  | OLEUM-G #1 | 003/025 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-122.234233 | 38.0074 | ETL.3150 | 40761585 | Foundation/Concrete-Tower | Earth Covered Tower | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 8
116707948 | T2 DI OLEUM-G #1 3/027 RPR FOND |  | OLEUM-G #1 | 003/027 | ICQ | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-122.234251 | 38.0048 | ETL.3150 | 40820388 | Foundation/Concrete-Tower | Earth Covered Tower | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 8
116708507 | T3 EI RND MTN-TBL MTN #1 21/109 CANCEL | 31440201 | ROUND MTN-TABLE MTN #1 | 021/109 | 93Z | E | Pre-2020_(4) TD tag on high spread line |  |  | CANCEL/CNCL | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.946912 | 40.4936 | ETL.6060 | 40868406 | Anchor-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Capital |  | Table Mountain |  |  | Yes
116708580 | DI IONE TAP 001/011 RPL STRW | 31425589 | IONE TAP | 001/011 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-120.927073 | 38.3671 | ETL.8253 | 40596264 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 9
116708747 | T2 DI PLACER-DEL MAR 3/75 RMV VEGN |  | PLACER-DEL MAR | 003/075 | HNA | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.125626 | 38.866 | ETL.7800 | 40591289 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  | Yes
116709406 | T2 DI CNTR COSTA-MORAGA #1 6/33 RPR FOND |  | CONTRA COSTA-MORAGA #1 | 006/033 | ICQ | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-121.854426 | 37.977 | ETL.5452 | 40659436 | Foundation/Concrete-Tower | Earth Covered Tower | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 7 | 2019-04-16
116709487 | T2 EI MLN-RND MTN #2 051/255 RPR INSS | 43621093 | MALIN-ROUND MTN #2 | 051/255 | ICQ | E | Pre-2020_(1b) Lines with special commitments |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.567116 | 41.3136 | ETL.6020 | 40746557 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
116709571 | T2 EI MALIN-RD MTN #2 066/335 COMPLETE | 31439323 | MALIN-ROUND MTN #2 | 066/335 | 93K | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.7290863 | 41.132 | ETL.6020 | 40782045 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  | Yes
116709807 | T2NT EI MLN-RND MTN #2 087/444B INS MRKS | 43621093 | MALIN-ROUND MTN #2 | 087/444B | ICQ | F | Pre-2020_(1b) Lines with special commitments |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.919367 | 40.8987 | ETL.6020 | 41162673 | Marker (i.e. signs)-Steel | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Table Mountain |  |  | Yes
116709969 | EI KESWICK-TRINITY 22/160 RPL DAMP | 43740171 | KESWICK-TRINITY | 022/160 | ICS | E | Pre-2020_(9a) Other ignition related |  |  |  |  | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.5547142 | 40.6339 | ETL.7270 | 40699794 | Damper-Steel | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
116710129 | T2 DI TGR CRK-VLY SPRNGS 14/113 RPR FOND | 43830086 | TIGER CREEK-VALLEY SPRINGS | 014/113 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.670384 | 38.3246 | ETL.5790 | 40581567 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - 10
116710537 | T2 EI PARADISE-TBL MTN 9/80 HELIWSH INSU | 43724324 | PARADISE-TABLE MTN | 009/080 | ICD | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.524229 | 39.5924 | ETL.4316 | 40608928 | Insulator | Contaminated | Helicopter Wash | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 626 | Table Mountain |  |  | Yes
116710636 | NEWARK-LIVERMORE 013/082 REPAINT MEMB |  | NEWARK-LIVERMORE | 013/082 | ICS | F | Pre-2020_(9a) Other ignition related |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-121.805195 | 37.6177 | ETL.7660 | 40696213 | Structure-Steel | Paint/Coating | Other |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Bay
116711231 | T2 EI RND MTN-TBL MT #1 016/084 RPR STRT | 43848514 | ROUND MTN-TABLE MTN #1 | 016/084 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Internal Process | Circuit Based Scheduling | '-121.944979 | 40.5715 | ETL.6060 | 40759982 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
116711649 | T3 DI ROCK CREEK-POE 015/102 PAINT | 43724474 | ROCK CREEK-POE | 015/102 | ICS | E | Pre-2020_(9a) Other ignition related |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.478783 | 39.734 | ETL.5630 | 40674525 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
116711686 | T2 EI STNSLS-MLNS-MNTC#1 18/112 PNT STRS | 43712830 | STANISLAUS-MELONES SS-MANTECA #1+ | 018/112 | ICS | E | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.638792 | 37.9897 | ETL.3830 | 40669923 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - Prog Multi
116711752 | T2 DI IONE TAP 001/004 RPL STRW | 31499906 | IONE TAP | 001/004 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.924383 | 38.3582 | ETL.8253 | 40745287 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 9
116711754 | T2 DI VALLEY SPRINGS #1 5/93 RPR STRW | 43831084 | VALLEY SPRINGS #1 | 005/093 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.833271 | 38.1756 | ETL.8210 | 40905508 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 23
116711788 | T2 DI VALLEY SPRINGS #1 007/151 RPR GYWW | 43831083 | VALLEY SPRINGS #1 | 007/151 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.862603 | 38.144 | ETL.8210 | 40908234 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 23
116711876 | T3 DI POE-RIO OSO 16/112 RPR INSS | 43724474 | ROCK CREEK-POE | 016/112 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.48222 | 39.7127 | ETL.5630 | 40723992 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
116712066 | T2 DI CHRISTIE SOBRANTE 9/53 RPL INSL | 31446629 | CHRISTIE-SOBRANTE | 009/053 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.199235 | 38.0024 | ETL.1260 | 40669433 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - Prog Land
116712072 | T2NT EI MLN-RND MTN #2 087/444A INS MRKS | 43621093 | MALIN-ROUND MTN #2 | 087/444A | ICQ | F | Pre-2020_(1b) Lines with special commitments |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.919147 | 40.8987 | ETL.6020 | 41162672 | Marker (i.e. signs)-Steel | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Table Mountain |  |  | Yes
116712174 | T2 DI CHRISTIE-SOBRANTE 010/057 RPR FOND | 44344852 | CHRISTIE-SOBRANTE | 010/057 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.198648 | 37.9939 | ETL.1260 | 40804613 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 5
116712303 | T2 DI PARKWAY MORAGA 9/54 HRDT INST | 43683430 | PARKWAY-MORAGA | 009/054 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.233759 | 38.0065 | ETL.5930 | 40867736 | Hardware-Tower | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog Multi
116713023 | T2 DI ELECTRA-BELLOTA 18/132 RPR FOND | 43844906 | ELECTRA-BELLOTA | 018/132 | ICQ | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.889431 | 38.1257 | ETL.4670 | 40863029 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - Prog Multi
116713046 | T2 DI PLACER-DEL MAR 5/115 RPL STRW | 31454612 | PLACER-DEL MAR | 005/115 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.158216 | 38.8504 | ETL.7800 | 40747059 | Structure-Wood | Rotten | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
116713308 | T2 DI TIGER CRK-VLLY SP 14/112 INST MRKS | 43830601 | TIGER CREEK-VALLEY SPRINGS | 014/112 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.669879 | 38.3267 | ETL.5790 | 40582785 | Marker (i.e. signs)-Steel | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Victor |  | Y - Prog Multi
116713592 | T2 DI TIGER CREEK-VLY SP 15/124 RPR FOND | 43830085 | TIGER CREEK-VALLEY SPRINGS | 015/124 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.680275 | 38.31 | ETL.5790 | 40648161 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - Prog Multi
116713596 | T2 DI ELECTRA-BELLOTA 18/133 CANCEL | 43844906 | ELECTRA-BELLOTA | 018/133 | ICQ | E | Pre-2020_(5) TD tag on other lines |  |  | CANCEL/CNCL | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.891218 | 38.1237 | ETL.4670 | 40862711 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - Prog Multi
116713874 | EI COTTON-DELE #2 061/555 RPL INSS | 31450548 | COTTONWOOD-DELEVAN #2 | 061/555 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-122.2683139 | 40.3685 | ETL.4580 | 40789122 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  | Yes
116713996 | T2 EI MALIN-RND MTN#2 67/341 COMPLETE | 43754876 | MALIN-ROUND MTN #2 | 067/341 | ICD | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.742692 | 41.1212 | ETL.6020 | 40597344 | Insulator | Contaminated | Helicopter Wash | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 626 | Table Mountain |  |  | Yes
116714036 | T2 CRAG VIEW-CASCADE 000/009 REPL INSS | 31462721 | CRAG VIEW-CASCADE | 000/009 | 93K | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-122.412241 | 40.9212 | ETL.1350 | 41166982 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  | Yes
116714290 | EI MELONES-CURTIS 14/000L RPL POLE | 31485152 | MELONES-CURTIS | 014/000 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | Central | WSIP |  |  |  | REJECT: Crew reported they were unable to complete work. Scope of work has been changed. Pleae resubmit once new scope of work has been completed. |  |  | '-120.329469 | 37.9718 | ETL.2390 | 44391011 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 12
116714308 | T2 EI MLIN-RND MTN #2 078/398A INS MRKS | 43621093 | MALIN-ROUND MTN #2 | 078/398A | ICQ | F | Pre-2020_(1b) Lines with special commitments |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.890795 | 41.0251 | ETL.6020 | 41162694 | Marker (i.e. signs)-Steel | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Table Mountain |  |  | Yes
116714346 | EI COTTONWOOD-DEL #2 61/556 RPL INSS | 31450548 | COTTONWOOD-DELEVAN #2 | 061/556 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-122.2683017 | 40.3667 | ETL.4580 | 40845800 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  | Yes
116714363 | EI MELONES-CURTIS 14/000R RPL POLE | 31485152 | MELONES-CURTIS | 014/000 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | Central | WSIP |  |  |  | REJECT: Crew reported they were unable to complete work. Scope of work has been changed. Pleae resubmit once new scope of work has been completed. |  |  | '-120.329469 | 37.9718 | ETL.2390 | 44391012 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 12
116714447 | T2 DI PARKWAY-MORAGA 7/44 RPL SHLS | 43753156 | PARKWAY-MORAGA | 007/044 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.233594 | 38.0313 | ETL.5930 | 40872756 | Shield Wire / OPGW-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - Prog Multi
116714461 | T2 EI MLN-RND MTN #2 080/406 RPL INSS | 31439323 | MALIN-ROUND MTN #2 | 080/406 | 93K | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.8952165 | 41.0042 | ETL.6020 | 40852031 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  | Yes
116714695 | T2 EI RND MTN-CTTNWD #2 021/197 RPR SHLS | 43877040 | ROUND MTN-COTTONWOOD #2 | 021/197 | ICS | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.028558 | 40.7175 | ETL.5640 | 40805139 | Shield Wire / OPGW-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
116714835 | EI NEWARK-LAWRENCE LAB 14/088 RPR FOND |  | NEWARK-LIVERMORE | 014/088 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-121.789525 | 37.6266 | ETL.7660 | 40875752 | Foundation/Concrete-Tower | Earth Covered Tower | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog Multi
116714904 | T2 EI MALIN-RND MTN#2 82/416 RPR OPGW | 43621093 | MALIN-ROUND MTN #2 | 082/416 | ICQ | E | Pre-2020_(1b) Lines with special commitments |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.909489 | 40.9783 | ETL.6020 | 40817711 | Shield Wire / OPGW-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
116714963 | EI STANIS-NEW #1 088/583 PAINT | 43753192 | STANISLAUS-NEWARK #1 (12KV) | 088/583 | ICS | E | Pre-2020_(9a) Other ignition related | Budget Owner (Paint) |  |  |  | LATE | Central | WSIP | [6 empty] | '-121.809238 | 37.6187 | ETL.3850 | 41196254 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay
116715215 | T2 EI DIABLO-GATES #1 58/239A REPAINT | 43756059 | DIABLO-GATES #1 | 058/239A | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-120.300477 | 35.8934 | ETL.5960 | 41130203 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Pismo Beach |  | Y - 4
116715248 | T2 EI RND MT-TBL MT #1 15/080 RMV VEGN | 43877023 | ROUND MTN-TABLE MTN #1 | 015/080 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  | Likely veg | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.945298 | 40.5827 | ETL.6060 | 40601327 | Structure-Steel | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
116715320 | EI TSLA-RVNSWD 017/092 REPL INSS | 31454851 | TESLA-RAVENSWOOD | 017/092 | 93K | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-121.8359257 | 37.599 | ETL.5730 | 40704316 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - 1
116715353 | T2 EI MALIN-RND MTN#2 82/419A INST MRKS | 43621093 | MALIN-ROUND MTN #2 | 082/419A | ICQ | F | Pre-2020_(1b) Lines with special commitments |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.913876 | 40.9704 | ETL.6020 | 41162607 | Marker (i.e. signs)-Steel | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Table Mountain |  |  | Yes
116715433 | T2 DI VALLEY SPRINGS #1 7/147 RPR SPLW | 43831019 | VALLEY SPRINGS #1 | 007/147 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.860995 | 38.1462 | ETL.8210 | 40908230 | Conductor-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 23
116715488 | T2 EI RND MT-TBL MT #1 16/87 RPL SPLS | 44305409 | ROUND MTN-TABLE MTN #1 | 016/087 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.944718 | 40.5628 | ETL.6060 | 40816705 | Splice-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
116715669 | T2 EI TEMPLETON-GATES 48/204A REPAINT | 43923645 | TEMPLETON-GATES | 048/204A | ICS | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | South | WSIP | FSRP | [5 empty] | '-120.295703 | 35.8973 | ETL.5934 | 40911555 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Pismo Beach |  | Y - 4
116715725 | T2 DI PARKWAY-MORAGA 9/56 RPR STRT | 43753156 | PARKWAY-MORAGA | 009/056 | ICS | E | Pre-2020_(9a) Other ignition related | Budget Owner (Paint) |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-122.233783 | 38.0027 | ETL.5930 | 40587012 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  | Y - 9
116716039 | T2 EI ROCK CREEK-POE 007/052 PAINT | 43724473 | ROCK CREEK-POE | 007/052 | ICS | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.422719 | 39.8302 | ETL.5630 | 40683788 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
116716062 | T2 EI MALIN-ROUND MTN #2 72/368 RPL HRDT |  | MALIN-ROUND MTN #2 | 072/368 | ICQ | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.81068 | 41.0702 | ETL.6020 | 40868974 | Hardware-Tower | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
116716068 | T2 EI MALIN-RND MTN#2 86/438 RPR OPGW | 43621093 | MALIN-ROUND MTN #2 | 086/438 | ICQ | E | Pre-2020_(1b) Lines with special commitments |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.918181 | 40.913 | ETL.6020 | 40871639 | Shield Wire / OPGW-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
116716300 | EI COTTONWOOD-GLENN 61/554 RPL INSS | 31451261 | COTTONWOOD-GLENN | 061/554 | 93K | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-122.2683097 | 40.3703 | ETL.4560 | 40796993 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  | Yes
116716557 | T2 EI MALIN-ROUND MTN#2 68/343 RPLC INSS | 43754876 | MALIN-ROUND MTN #2 | 068/343 | ICD | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.7465291 | 41.1182 | ETL.6020 | 40680148 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 532 | Table Mountain |  |  | Yes
116718001 | T2 DI MRGA-SN LNDRO #3 8/057 RPR FOND | 43753784 | MORAGA-SAN LEANDRO #3 | 008/057 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-122.119193 | 37.737 | ETL.2790 | 40804673 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 7
116718601 | T2 DI CHRISTIE-SOBRNTE 10/054 RPL HRDS | 43751914 | CHRISTIE-SOBRANTE | 010/054 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.199192 | 38.0017 | ETL.1260 | 40745844 | Hardware-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - Prog Land
116718782 | T2 DI CC-MORAGA #1 24/113 RPR STRT | 44358165 | CONTRA COSTA-MORAGA #1 | 024/113 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  | Likely MAT error - delink to correct | TR2 | LATE | Central | WSIP | [6 empty] | '-122.120888 | 37.8621 | ETL.5452 | 40822239 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 5 | 2019-04-16
116718842 | T2 EI TESLA-MET 027/114 BENT MBR |  | TESLA-METCALF | 027/114 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-121.686896 | 37.3239 | ETL.6110 | 40753750 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 3
116718880 | T2 DI TGR CRK-VLY SPRNGS 15/125 RPR FOND | 43830091 | TIGER CREEK-VALLEY SPRINGS | 015/125 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.682415 | 38.3082 | ETL.5790 | 40645140 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - 10
116718884 | T2 DI TGR CRK-ELCTR 13/102 RPR FOND | 43830099 | TIGER CREEK-ELECTRA | 013/102 | ICQ | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.665266 | 38.3401 | ETL.5780 | 40662458 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - 11
116718933 | T2 EI HAT CRK #1-WESTWD 026/514 RPL SPLW | 43736797 | HAT CREEK #1-WESTWOOD | 026/514 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.191597 | 40.6673 | ETL.7030 | 40817133 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
116719413 | T2 EI TESLA-METCALF 25/105 RPR GYWS | 43753282 | TESLA-METCALF | 025/105 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  | Tower guy | TR2 | LATE | Central | WSIP | [6 empty] | '-121.679879 | 37.3551 | ETL.6110 | 40753703 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  | Y - 3
116719414 | T2 EI TESLA-METCALF 029/119 RPR GYWS | 43753282 | TESLA-METCALF | 029/119 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  | Tower guy | TR2 | LATE | Central | WSIP | [6 empty] | '-121.699665 | 37.3098 | ETL.6110 | 40870373 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  | Y - 3
116719415 | T2 EI TESLA-METCALF 28/118 RPR GYWS | 43753282 | TESLA-METCALF | 028/118 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  | Tower guy | TR2 | LATE | Central | WSIP | [6 empty] | '-121.697323 | 37.3124 | ETL.6110 | 40863785 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  | Y - 3
116719427 | T2 EI TESLA-METCALF 026/109 RPR FOND |  | TESLA-METCALF | 026/109 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-121.676346 | 37.3394 | ETL.6110 | 40863441 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Multi Prog
116719479 | T2 EI MALIN-RND MTN #2 74/376 RPLC INSS | 43754876 | MALIN-ROUND MTN #2 | 074/376 | ICD | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.8422022 | 41.0674 | ETL.6020 | 40837368 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 532 | Table Mountain |  |  | Yes
116719494 | CORCORAN GUERNSEY 03/009 RPL TIED | 31430405 | CORCORAN-GUERNSEY | 003/009 | 93I | B | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.6220034 | 36.1088 | ETL.9360 | 40895352 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Fresno
116719572 | T2 EI TULE-SPRINGVLLE 021/010A RPR SPLS | 43709294 | TULE-SPRINGVILLE | 021/010A | ICW | E | Pre-2020_(5) TD tag on other lines |  |  | Likely MAT error - delink to correct | TR2 | LATE | South | WSIP | [8 empty] | ETL.9040 | 44264400 | Splice-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Midway |  | Y - 23
116720048 | DI VALLEY SPRINGS #1 5/099 RPR STRW | 43831086 | VALLEY SPRINGS #1 | 005/099 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-120.836202 | 38.1723 | ETL.8210 | 40905514 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 23
116721200 | T3 QC MORAGA SN LEANDRO#1 4/33 STRT PNT | 43708450 | MORAGA-SAN LEANDRO #1 | 004/033 | ICS | E | Pre-2020_(9a) Other ignition related | Budget Owner (Paint) |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.127977 | 37.7936 | ETL.2770 | 40644209 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - 10
116721226 | EI CLR LKE-HPLND 000/014 RPL STRW | 31483756 | CLEAR LAKE-HOPLAND | 000/014 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | North Coast | WSIP | FSRP | [5 empty] | '-123.067538 | 38.9699 | ETL.6390 | 40769721 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  | 2019-07-19
116721435 | T2 EI MT GT JCT-CSCDE 000/006 RPL INSW | 31471612 | MTN GATE JCT-CASCADE | 000/006 | 93I | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.31083 | 40.7367 | ETL.7640 | 40845236 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 508 | Table Mountain |  |  | Yes
116721471 | T2 EI MT GT JCT-CSCD 000/006 RPL HRDW | 43758388 | MTN GATE JCT-CASCADE | 000/006 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.31083 | 40.7367 | ETL.7640 | 44565484 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
116721481 | EI TESLA-NEWARK #2 015/100 RPR FOND |  | TESLA-NEWARK #2 | 015/100 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-121.80855 | 37.6159 | ETL.5354 | 41152645 | Foundation/Concrete-Tower | Earth Covered Tower | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 11
116721496 | T2 EI CARIBOU PALERMO :5/40 SPLS RPR | 44070463 | CARIBOU-PALERMO | :005/040 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.21813 | 40.0392 | ETL.3190 | 40910283 | Splice-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain
116721719 | T2 EI RND MTN-TBL MTN #2 9/52 REPL GYWS | 44156943 | ROUND MTN-TABLE MTN #2 | 009/052 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  | Tower guy | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.939259 | 40.6665 | ETL.6070 | 40663401 | Guy Wire-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Table Mountain |  |  | Yes
116721744 | T2 EI TESLA-METCALF 034/142 RPR FOND |  | TESLA-METCALF | 034/142 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-121.737798 | 37.2324 | ETL.6110 | 40664359 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 3
116721826 | T2 EI TESLA-METCALF 034/142 ZENA GRD |  | TESLA-METCALF | 034/142 | ICB | F | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-121.737798 | 37.2324 | ETL.6110 | 40664359 | Raptor Guard-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 593 | Bay |  | Y - 3
116721862 | T3 EI RND MT-TBL MT #2 008/047 RPR STRT | 43755806 | ROUND MTN-TABLE MTN #2 | 008/047 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP |  |  |  |  | Internal Process | Scheduling by circuit based. | '-121.939766 | 40.6829 | ETL.6070 | 40816729 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
116722029 | T2 EI MTN GATE JCT-CSCD 0/8 (L) RPL STRW | 31498056 | MTN GATE JCT-CASCADE | 000/008 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.312045 | 40.7331 | ETL.7640 | 44565485 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain
116722144 | T2 EI MLN-RND MTN #2 72/367A RPR INSS | 43621093 | MALIN-ROUND MTN #2 | 072/367A | ICQ | E | Pre-2020_(1b) Lines with special commitments |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.809236 | 41.0711 | ETL.6020 | 40576756 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
116722146 | T2 EI MLN-RND MT #2 072/367 RPL INSS | 31439323 | MALIN-ROUND MTN #2 | 072/367 | 93K | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.8081859 | 41.0716 | ETL.6020 | 40846155 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  | Yes
116722318 | T2 SANTA YNEZ TAP 115KV 0/3 REPL INSULS | 31434029 | SANTA YNEZ TAP | 000/003 | 93I | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | South | Non-WSIP | [6 empty] | '-120.181979 | 34.6468 | ETL.3701 | 40711948 | Insulator-Wood | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Pismo Beach |  | Y - Prog Multi
116722522 | T2 DI TIDEWATER-SOBRANTE 16/80 RMV NEST | 43753287 | TIDEWATER-SOBRANTE | 016/080 | ICS | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-122.118018 | 37.9627 | ETL.5770 | 40609117 | Structure-Steel | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - 3
116722933 | T2 EI MLN-RND MT #2 072/365 RPL INSS | 31439323 | MALIN-ROUND MTN #2 | 072/365 | 93K | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.8033481 | 41.0743 | ETL.6020 | 40782037 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  | Yes
116722963 | EI COALINGA #1-SAN MIGUEL 19/1 RMV SOIL | 44300672 | COALINGA #1-SAN MIGUEL | 019/001 | ICY | E | Pre-2020_(9a) Other ignition related |  |  | Likely MAT error - delink to correct |  | LATE | South | WSIP | [6 empty] | '-120.59577 | 35.9967 | ETL.8580 | 40597698 | Structure-Tower | Soil | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense |  | Pismo Beach |  |  | BLM
116723165 | T2 SANTA YNEZ TAP 115KV 1/10 RPR INSW |  | SANTA YNEZ TAP | 001/010 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.167932 | 34.6422 | ETL.3701 | 40712630 | Insulator-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - Prog 401
116723290 | T2 EI MLN-RND MT #2 072/364B INS MRKS | 43621093 | MALIN-ROUND MTN #2 | 072/364B | ICQ | F | Pre-2020_(1b) Lines with special commitments |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.801869 | 41.0751 | ETL.6020 | 41162772 | Marker (i.e. signs)-Steel | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Table Mountain |  |  | Yes
116723379 | T2 EI CRESTA-RIO OSO 9/76 RPR SPLCS |  | CRESTA-RIO OSO | 009/076 | ICS | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.426171 | 39.8241 | ETL.4590 | 40910105 | Splice-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
116723413 | EI CLR LKE-HPLND 002/001 RPL PL | 31488229 | CLEAR LAKE-HOPLAND | 002/001 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | North Coast | WSIP | FSRP | [5 empty] | '-123.045335 | 38.9674 | ETL.6390 | 40584491 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  | 2019-07-19
116723421 | T2NT EI BCKS CRK-RCK CRK-CRST 5/50 REPNT | 43897315 | BUCKS CREEK-ROCK CREEK-CRESTA | 005/050 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.410283 | 39.8477 | ETL.4430 | 40608902 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
116723560 | EI CLR LKE-HPLND 002/002 RPL PL | 31488229 | CLEAR LAKE-HOPLAND | 002/002 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | North Coast | WSIP | FSRP | [5 empty] | '-123.043967 | 38.9675 | ETL.6390 | 40699137 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  | 2019-07-19
116724350 | T2NT EI HT CRK #1-WSTWD 022/436 INS MRKW | 43736797 | HAT CREEK #1-WESTWOOD | 022/436 | ICW | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.239995 | 40.713 | ETL.7030 | 40770741 | Marker (i.e. signs)-Wood | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
116724352 | T2NT EI HT CRK #1-WSTWD 022/438 INS MRKW | 43736797 | HAT CREEK #1-WESTWOOD | 022/438 | ICW | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.238727 | 40.7118 | ETL.7030 | 40827483 | Marker (i.e. signs)-Wood | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
116724355 | T2NT EI HT CRK #1-WSTWD 023/442 INS MRKW | 43736797 | HAT CREEK #1-WESTWOOD | 023/442 | ICW | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.236194 | 40.7095 | ETL.7030 | 40592097 | Marker (i.e. signs)-Wood | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
116724359 | T2NT EI HT CRK #1-WSTWD 023/443 INS MRKW | 43736797 | HAT CREEK #1-WESTWOOD | 023/443 | ICW | F | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.235233 | 40.7086 | ETL.7030 | 40676328 | Marker (i.e. signs)-Wood | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
116724490 | T2NT EI HT CRK #1-WSTWD 023/445 COMPLETE | 43736797 | HAT CREEK #1-WESTWOOD | 023/445 | ICW | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.233885 | 40.7074 | ETL.7030 | 40770862 | Marker (i.e. signs)-Wood | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
116725980 | T2 EI RD MTN-TBL MTN #2 77/313 REPL ANCS | 31474558 | ROUND MTN-TABLE MTN #2 | 077/313 | 93E | E | Pre-2020_(4) TD tag on high spread line |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.731925 | 39.713 | ETL.6070 | 40660100 | Anchor-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Capital |  | Table Mountain |  |  | Yes
116727675 | T2 EI MLIN-RND MT #2 068/345A COMPLETE | 43621093 | MALIN-ROUND MTN #2 | 068/345A | ICQ | E | Pre-2020_(1b) Lines with special commitments |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.754181 | 41.1121 | ETL.6020 | 40576895 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
116731426 | T2 MALIN-ROUND MTN #2 -76/385 RPR GYWS | 43621093 | MALIN-ROUND MTN #2 | 076/385 | ICQ | E | Pre-2020_(1b) Lines with special commitments |  |  | Tower guy | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.86893 | 41.0574 | ETL.6020 | 40765410 | Guy Wire-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Table Mountain |  |  | Yes
116731428 | T2 EI MLN-ROUND MTN #2 76/385A RPL INSS | 31439323 | MALIN-ROUND MTN #2 | 076/385A | 93K | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.869056 | 41.0575 | ETL.6020 | 41162684 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  | Yes
116731500 | T2 EI MALIN-ROUND MTN #2 76/386 RPL INSS | 31439323 | MALIN-ROUND MTN #2 | 076/386 | 93K | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.871248 | 41.0554 | ETL.6020 | 40817709 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  | Yes
116731501 | T2 EI MALIN-RND MTN #2 76/385B RPL INSS | 31439323 | MALIN-ROUND MTN #2 | 076/385B | 93K | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.8692 | 41.0576 | ETL.6020 | 41162686 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  | Yes
116731616 | T2 EI MLN-RND MT #2 068/347 RPL INSS | 31439323 | MALIN-ROUND MTN #2 | 068/347 | 93K | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.7574349 | 41.1095 | ETL.6020 | 40843690 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  | Yes
116732149 | T2 DI TGR CRK-VLLY SPRGS 14/112 RPR FOND | 43836755 | TIGER CREEK-VALLEY SPRINGS | 014/112 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.669879 | 38.3267 | ETL.5790 | 40582785 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - 10
116732725 | T2 EI CARB SW ST-RD MT R000/001 PAINT | 43897849 | CARBERRY SW STA-ROUND MTN | R000/001 | ICS | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.937479 | 40.7918 | ETL.5410 | 40586641 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
116732886 | T2 EI MB-CALIF FLATS SS 40/167B RPR INSU | 43763692 | MORRO BAY-GATES #2 | 040/167B | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-120.394973 | 35.8059 | ETL.5280 | 40740430 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Pismo Beach |  | Y - 1
116732964 | T2 EI CARB SW ST-RO MT R000/002 PAINT | 43897849 | CARBERRY SW STA-ROUND MTN | R000/002 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.937428 | 40.7929 | ETL.5410 | 40661608 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
116733071 | T2 EI VOLTA-DESCHUTES-014/312 RMV VEG | 43939089 | VOLTA-DESCHUTES | 014/312 | ICW | F | Pre-2020_(9a) Other ignition related |  |  | Likely veg | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.133119 | 40.5284 | ETL.8290 | 44186906 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
116733110 | T2 SPAULDING #3-SPAULDING #1 - 60 kV_000 | 31445624 | SPAULDING #3-SPAULDING #1 | 000/009 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-120.642653 | 39.3294 | ETL.8050 | 40861958 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
116733243 | T2 EI CARB SW ST-RO MT R000/002 RMV VEGN |  | CARBERRY SW STA-ROUND MTN | R000/002 | HNA | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.937428 | 40.7929 | ETL.5410 | 40661608 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Table Mountain |  |  | Yes
116733549 | T2 EI PLRMO-COLGATE C008/036 INST DAMS | 43724331 | PALERMO-COLGATE | C008/036 | ICS | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.333546 | 39.3066 | ETL.5360 | 40822161 | Damper-Steel | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento
116733618 | T2 EI CARBERRY SS-R MTN R0/3 RPL INSS | 31450544 | CARBERRY SW STA-ROUND MTN | R000/003 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.937014 | 40.7944 | ETL.5410 | 40693159 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  | Yes
116733782 | T3NT EI RUND MTN-T MTN #1 5/031 RPL GYMK | 43740167 | ROUND MTN-TABLE MTN #1 | 005/031 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  | TLN/TLQ error |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.942109 | 40.7275 | ETL.6060 | 40592679 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Table Mountain |  |  | Yes
116733787 | T2 EI MALIN-RND MTN #2 079/401 RPL HRDT | 43621093 | MALIN-ROUND MTN #2 | 079/401 | ICQ | E | Pre-2020_(1b) Lines with special commitments | Superintendent Approved work efficiency |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.891762 | 41.0179 | ETL.6020 | 40587306 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
116733828 | T2 EI MALIN-RND MTN #2 079/401 RPL INSS | 31439323 | MALIN-ROUND MTN #2 | 079/401 | 93K | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.8917754 | 41.0179 | ETL.6020 | 40612253 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  | Yes
116733829 | T2 EI MALIN-RND MTN #2 079/400 RPL INSS | 31439323 | MALIN-ROUND MTN #2 | 079/400 | 93K | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.8913259 | 41.0203 | ETL.6020 | 40635018 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  | Yes
116734004 | EI TESLA-NEWARK #2 014/097 REPAINT | 43753285 | TESLA-NEWARK #2 | 014/097 | ICS | E | Pre-2020_(9a) Other ignition related | Budget Owner (Paint) |  |  |  | LATE | Central | WSIP | [6 empty] | '-121.802733 | 37.6194 | ETL.5354 | 41152642 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay
116734035 | EI DIABLO-GATES #1 54/220 INST STEPS | 43756059 | DIABLO-GATES #1 | 054/220 | ICS | E | Pre-2020_(9a) Other ignition related |  |  |  |  | LATE | South | WSIP | FSRP | [5 empty] | '-120.3536 | 35.844 | ETL.5960 | 40603335 | Hardware-Steel | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Pismo Beach |  | Y - 4
116734038 | EI LAS POSITAS-NEWARK 7/050 PNT LADDER | 43753291 | LAS POSITAS-NEWARK | 007/050 | ICS | F | Pre-2020_(9a) Other ignition related | Budget Owner (Paint) |  |  |  | LATE | Central | WSIP | FSRP | [5 empty] | '-121.799276 | 37.6218 | ETL.4980 | 40862260 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - Prog Multi
116734569 | T2 EI MALIN-ROUND MTN #2 69/349A COTTER | 43621093 | MALIN-ROUND MTN #2 | 069/349A | ICQ | E | Pre-2020_(1b) Lines with special commitments |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.76361 | 41.1046 | ETL.6020 | 40576896 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
116734588 | T2 EI RND MT-TBL MT #2 011/063 RPL ANCS | 31488209 | ROUND MTN-TABLE MTN #2 | 011/063 | 93Z | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.939001 | 40.6349 | ETL.6070 | 40651392 | Anchor-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Capital |  | Table Mountain |  |  | Yes
116734599 | T3 EI ROUND MTN-T MTN #1 8/45 RPL BOLT | 43790345 | ROUND MTN-TABLE MTN #1 | 008/045 | ICS | E | Pre-2020_(9a) Other ignition related |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.940575 | 40.6894 | ETL.6060 | 40746375 | Hardware-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Table Mountain |  |  | Yes
116734695 | T2 EI MALIN-RND MTN #2 69/351 RPL INSS | 31527915 | MALIN-ROUND MTN #2 | 069/351 | 93K | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.7674293 | 41.1016 | ETL.6020 | 40610988 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  | Yes
116734738 | T2 EI MALIN-RND MTN #2 069/348 RPL INSS | 31439323 | MALIN-ROUND MTN #2 | 069/348 | 93K | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.7602167 | 41.1073 | ETL.6020 | 40893468 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  | Yes
116734760 | T2 EI MALIN-ROUND MTN #2 69/350 RPL INSS | 31439323 | MALIN-ROUND MTN #2 | 069/350 | 93K | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.7653229 | 41.1033 | ETL.6020 | 40635014 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  | Yes
116734967 | T3 EI RND MTN-T M #1 008/044 INST HRDT | 43790345 | ROUND MTN-TABLE MTN #1 | 008/044 | ICS | E | Pre-2020_(9a) Other ignition related |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.940651 | 40.6913 | ETL.6060 | 40762867 | Hardware-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Table Mountain |  |  | Yes
116734977 | T2 EI MALIN-RND MTN #2 070/352 RPL INSS | 31439323 | MALIN-ROUND MTN #2 | 070/352 | 93K | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.7702866 | 41.0994 | ETL.6020 | 40722250 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  | Yes
116735272 | T2 SANTA YNEZ TAP 115KV 2/21 REPL POLE | 31435800 | SANTA YNEZ TAP | 002/021 | 70Y | F | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | South | Non-WSIP | [6 empty] | '-120.146922 | 34.6354 | ETL.3701 | 40765581 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Pismo Beach |  | Y - 3
116735568 | T2 DI TIGER CRK-VLY SPRG 15/123 RPR FOND | 43836745 | TIGER CREEK-VALLEY SPRINGS | 015/123 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.679707 | 38.3105 | ETL.5790 | 40590026 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - Prog Multi
116736170 | EI DIABLO-GATES #1 008/036 PAINT | 43756059 | DIABLO-GATES #1 | 008/036 | ICS | E | Pre-2020_(9a) Other ignition related |  |  |  |  | LATE | South | WSIP | FSRP | [5 empty] | '-120.798075 | 35.3088 | ETL.5960 | 40820161 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Pismo Beach |  | Y - 4
116736287 | T2 SANTA YNEZ TAP 115KV 3/32 REPL POLE | 31435800 | SANTA YNEZ TAP | 003/032 | 70Y | F | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | South | Non-WSIP | [6 empty] | '-120.130278 | 34.6294 | ETL.3701 | 40751453 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Pismo Beach |  | Y - 3
116737553 | T2 EI MALIN-RND MTN #2 69/350A RPL HRDT | 43621093 | MALIN-ROUND MTN #2 | 069/350A | ICQ | E | Pre-2020_(1b) Lines with special commitments |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.766673 | 41.1022 | ETL.6020 | 41111833 | Hardware-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
116737554 | T2 EI MALIN-ROUND MTN #2 69/350A COTTER | 43621093 | MALIN-ROUND MTN #2 | 069/350A | ICQ | E | Pre-2020_(1b) Lines with special commitments |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.766673 | 41.1022 | ETL.6020 | 41111833 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
116737566 | T2 EI MALIN-RD MTN #2 071/358B INST MRKS | 43621093 | MALIN-ROUND MTN #2 | 071/358B | ICQ | F | Pre-2020_(1b) Lines with special commitments |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.787573 | 41.0856 | ETL.6020 | 41191648 | Marker (i.e. signs)-Steel | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Table Mountain |  |  | Yes
116739774 | T2 EI MALIN-RND MTN #2 71/362B RPL SPLS | 43621093 | MALIN-ROUND MTN #2 | 071/362B | ICQ | E | Pre-2020_(1b) Lines with special commitments |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.797676 | 41.0777 | ETL.6020 | 40740258 | Splice-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
116739805 | T2 EI MALIN-RND MTN #2 70/356 RPL INSS | 31439323 | MALIN-ROUND MTN #2 | 070/356 | 93K | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.7792949 | 41.0922 | ETL.6020 | 40837366 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  | Yes
116740294 | T2NT DI TGR CRK-VLLY SPRNG 13/111 MRKS | 43830610 | TIGER CREEK-VALLEY SPRINGS | 013/111 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.669424 | 38.3286 | ETL.5790 | 40858406 | Marker (i.e. signs)-Steel | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Victor |  | Y - Prog Multi
116740440 | T2 DI TGR CRK-VLLY SPRNG 13/111 RPL HRDT | 43836757 | TIGER CREEK-VALLEY SPRINGS | 013/111 | ICQ | F | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.669424 | 38.3286 | ETL.5790 | 40858406 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - 10
116740642 | T2 DI TGR CRK-VLLY SPRNG 13/111 RPR FOND | 43836758 | TIGER CREEK-VALLEY SPRINGS | 013/111 | ICQ | F | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.669424 | 38.3286 | ETL.5790 | 40858406 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - 10
116741111 | T2 EI MTN GTE JCT-CSCDE 001/14R INS HRDW | 43758388 | MTN GATE JCT-CASCADE | 001/014 | ICW | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.315194 | 40.7236 | ETL.7640 | 44566782 | Hardware-Wood | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
116741286 | T2 EI MTN GTE JCT-CSCDE 001/15L RPR GYWW | 43758388 | MTN GATE JCT-CASCADE | 001/015 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.315653 | 40.7222 | ETL.7640 | 44565486 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
116741423 | T2 DI CARIBOU-PALERMO :9/70 RMV SOIL | 44070463 | CARIBOU-PALERMO | :009/070 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.254842 | 40.0061 | ETL.3190 | 40910312 | Structure-Steel | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain
116741438 | EI LAS POSITAS-NEWARK 7/049 PNT TWR | 43753291 | LAS POSITAS-NEWARK | 007/049 | ICS | F | Pre-2020_(9a) Other ignition related | Budget Owner (Paint) |  |  |  | LATE | Central | WSIP | FSRP | [5 empty] | '-121.797571 | 37.6228 | ETL.4980 | 40872287 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  | Y - Prog Multi
116741511 | T2 EI MTN GTE JCT-CSCDE 001/16L RPR GYWW | 43758388 | MTN GATE JCT-CASCADE | 001/016 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.316125 | 40.7208 | ETL.7640 | 44565343 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
116741512 | T2 EI PARADISE-BUTTE 9/89L RPR GYWS | 43881381 | PARADISE-BUTTE | 009/089 | ICS | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [8 empty] | ETL.4396 | 44382927 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
116741518 | T2 EI MTN GTE JCT-CSCDE 001/016 RPL SPLW | 43758388 | MTN GATE JCT-CASCADE | 001/016 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.316125 | 40.7208 | ETL.7640 | 44565343 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
116741792 | T3 EI CARIBOU-PALERMO :012/096 RPL GYWS | 44304491 | CARIBOU-PALERMO | :012/096 | ICS | E | Pre-2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.274824 | 39.9695 | ETL.3190 | 40910335 | Guy Wire-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
116741872 | T3 EI CRIBOU-PLRMO :11/92 RPL BENT MMBER | 44304491 | CARIBOU-PALERMO | :011/092 | ICS | E | Pre-2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.27547 | 39.9808 | ETL.3190 | 40910331 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain
116741890 | T3 EI CARIBOU-PALERMO :11/092 RPR JUMPER | 44304491 | CARIBOU-PALERMO | :011/092 | ICS | E | Pre-2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.27547 | 39.9808 | ETL.3190 | 40910331 | Jumper-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain
116742108 | T2 EI ROUND MTN-TAB #2 013/070 RPL INSS | 31455288 | ROUND MTN-TABLE MTN #2 | 013/070 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.942807 | 40.6148 | ETL.6070 | 40635756 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain
116742120 | T3 EI CARIBOU-PALERMO :012/097 BENT MEMB | 44051418 | CARIBOU-PALERMO | :012/097 | ICQ | E | Pre-2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.274864 | 39.9683 | ETL.3190 | 40910336 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
116742489 | EI NEWARK-LIVERMORE 012/075 RPR FOND |  | NEWARK-LIVERMORE | 012/075 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-121.819147 | 37.6093 | ETL.7660 | 40767814 | Foundation/Concrete-Tower | Earth Covered Tower | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay
116742683 | T3 EI CARIBOU-PALERMO :10/084 RPR CONS | 44304491 | CARIBOU-PALERMO | :010/084 | ICS | E | Pre-2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.276297 | 39.9925 | ETL.3190 | 40907021 | Jumper-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain
116742904 | T3 EI CRIBOU-PALERMO :10/84 RPR BENT MEM | 44051418 | CARIBOU-PALERMO | :010/084 | ICQ | E | Pre-2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.276297 | 39.9925 | ETL.3190 | 40907021 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
116742933 | T3NT EI CARIBOU-PALERMO :10/82 RPNT MEMB | 44302715 | CARIBOU-PALERMO | :010/082 | ICS | F | Pre-2020_(3) On high spread structure |  |  |  | TR3 | <60D | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.272037 | 39.994 | ETL.3190 | 40910323 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain
116742951 | T3 EI CARIBOU-PALERMO :010/082 RPL INSS |  | CARIBOU-PALERMO | :010/082 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.272037 | 39.994 | ETL.3190 | 40920062 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain
116743221 | T3 EI CARIBOU-PALERMO :010/078 RPL HRDS | 44304491 | CARIBOU-PALERMO | :010/078 | ICS | E | Pre-2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.267244 | 40.0011 | ETL.3190 | 40907020 | Hardware-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain
116743258 | T2 EI CTNWD-DLVN #2 070/614 RPNT TWR | 43730227 | COTTONWOOD-DELEVAN #2 | 070/614 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.267538 | 40.2386 | ETL.4580 | 40762881 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
116743385 | T3 EI SNTH LN-HLF MN BY?010/8 WASH INSW |  | SNEATH LANE-HALF MOON BAY | ?010/008 | ICI | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.419356 | 37.4821 | ETL.7212 | 40901218 | Insulator | Contaminated | Helicopter Wash |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 626 | Bay |  | Y - 29
116743470 | T3NT EI CARIBOU-PALERMO :10/079 REPAINT | 44302715 | CARIBOU-PALERMO | :010/079 | ICS | F | Pre-2020_(3) On high spread structure |  |  |  | TR3 | <60D | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.268442 | 39.9988 | ETL.3190 | 40910320 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain
116743881 | T2 EI MTN GTE JCT-CSCDE 002/22L RPL STRW | 31439163 | MTN GATE JCT-CASCADE | 002/022 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.318722 | 40.713 | ETL.7640 | 44565341 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC erdy srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain
116744255 | MTN GTE JCT-CSCDE 002/28L RPR GYWW | 43758388 | MTN GATE JCT-CASCADE | 002/028 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.321548 | 40.7046 | ETL.7640 | 44565534 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
116744475 | T2 EI HT CRK #1-PT #1 000/003 PNT STRT | 43749468 | HAT CREEK #1-PIT #1 | 000/003 | ICQ | E | Pre-2020_(5) TD tag on other lines | Budget Owner (Paint) |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.501721 | 40.9872 | ETL.7020 | 40657262 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
116744477 | T3NT EI CARIBOU-PALERMO :32/263 REPAINT | 44304495 | CARIBOU-PALERMO | :032/263 | ICS | F | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.475573 | 39.7491 | ETL.3190 | 40656367 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain
116744487 | T3 EI RNDMTN-CTNWD#3 029/239 RPNT TWR | 43755803 | ROUND MTN-COTTONWOOD #3 | 029/239 | ICS | E | Pre-2020_(9a) Other ignition related |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.955659 | 40.7713 | ETL.5650 | 40870436 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
116744503 | T2 EI CARIBOU-PALERMO 005/045 REPAINT | 44302715 | CARIBOU-PALERMO | 005/045 | ICS | F | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.540407 | 39.526 | ETL.3190 | 40755507 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain
116744508 | T2 EI SNTH LN-HLFMNBY ?011/8 RPNT STRS | 43752382 | SNEATH LANE-HALF MOON BAY | ?011/008 | ICS | F | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-122.424086 | 37.4718 | ETL.7212 | 40591479 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  | Y - 30
116744510 | T2 EI HT CRK #1-PT #1 000/005 PNT STRT | 43749468 | HAT CREEK #1-PIT #1 | 000/005 | ICQ | E | Pre-2020_(5) TD tag on other lines | Budget Owner (Paint) |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.50641 | 40.9834 | ETL.7020 | 40769927 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
116744514 | T3 EI CRST-RO OSO 017/139 PNT STRT | 43708860 | CRESTA-RIO OSO | 017/139 | ICQ | E | Pre-2020_(5) TD tag on other lines | Budget Owner (Paint) |  |  | TR3 | LATE | North Valley | WSIP |  |  |  |  | Internal Process | Circuit Based Scheduling | '-121.479492 | 39.7275 | ETL.4590 | 40910155 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
116744515 | T2 EI PT #1-CTTNWD 009/075 RPR FOND | 43930183 | PIT #1-COTTONWOOD | 009/075 | ICX | E | Pre-2020_(9a) Other ignition related |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.640715 | 40.9151 | ETL.5390 | 40759514 | Structure-Tower | Paint/Coating | Repaint | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense |  | Table Mountain |  |  | Yes
116744518 | T2 EI CARIBOU-PALERMO 6/53 PAINT STRT |  | CARIBOU-PALERMO | 006/053 |  | F | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.540497 | 39.5401 | ETL.3190 | 40660305 | Structure-Steel | Paint/Coating | Other |  |  |  |  | PEND | LC | TLN | Maintenance | Expense |  | Table Mountain
116744524 | T3 EI POE-RIO OSO 020/139 RPNT TWR | 43737420 | POE-RIO OSO | 020/139 | ICS | E | Pre-2020_(9a) Other ignition related |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.486317 | 39.6878 | ETL.5540 | 40870586 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
116744527 | T2 EI PRDS-TBL MTN 005/049 PNT STRT | 43727174 | PARADISE-TABLE MTN | 005/049 | ICS | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.54028 | 39.5358 | ETL.4316 | 40867305 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
116744532 | T2 EI HT CRK #1-PT #1 001/008 PNT STRT | 43749468 | HAT CREEK #1-PIT #1 | 001/008 | ICQ | E | Pre-2020_(5) TD tag on other lines | Budget Owner (Paint) |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.51109 | 40.9794 | ETL.7020 | 40877442 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
116744538 | T2 EI CARIBOU-PALERMO 004/044 REPAINT | 44302715 | CARIBOU-PALERMO | 004/044 | ICS | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.540274 | 39.5245 | ETL.3190 | 40758609 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
116744553 | T2 EI CLINGA#1-SAN MIGUEL 30/03 RPNT TWR | 43763703 | COALINGA #1-SAN MIGUEL | 030/003 | ICS | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | South | WSIP | FSRP | [5 empty] | '-120.63867 | 35.8507 | ETL.8580 | 40663679 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Pismo Beach |  | Y - 15
116744561 | T3 EI DRUM-HIGGINS 005/055 RPNT TWR | 43738143 | DRUM-HIGGINS | 005/055 | ICS | E | Pre-2020_(9a) Other ignition related |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.839155 | 39.2099 | ETL.4393 | 40751947 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento
116744573 | T2 EI DRM-HGGNS 15/135 PNT STRT | 43738143 | DRUM-HIGGINS | 015/135 | ICS | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-120.976913 | 39.1528 | ETL.4393 | 40690223 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes
116744576 | T2 EI CORTINA-VACA 011/076 RPNT TWR | 44304829 | CORTINA-VACA | 011/076 | ICS | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.126187 | 38.9646 | ETL.4540 | 40689900 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes
116744579 | T2 EI CORTINA-VACA 012/077 PAINT | 44304829 | CORTINA-VACA | 012/077 | ICS | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.125102 | 38.9628 | ETL.4540 | 40655809 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes
116744584 | T2 EI CORTINA-VACA 012/079 PAINT | 44304829 | CORTINA-VACA | 012/079 | ICS | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.121487 | 38.9568 | ETL.4540 | 40757914 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes
116744586 | T3 EI DRM-HGGNS 016/141 PNT STRT | 43738143 | DRUM-HIGGINS | 016/141 | ICS | E | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.992547 | 39.1467 | ETL.4393 | 40862213 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes
116744589 | T2 EI CARIBOU-PALERMO :6/051 PAINT STRT |  | CARIBOU-PALERMO | :006/051 |  | F | Pre-2020_(3) On high spread structure | Budget Owner (Paint) |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.221517 | 40.0202 | ETL.3190 | 40910293 | Structure-Tower | Paint/Coating | Repaint |  |  |  |  | PEND | LC | TLQ | Tower | Expense |  | Table Mountain
116744594 | T3 EI MRGA-OAKLND#3 000/004 RPNT TWR | 43725286 | MORAGA-OAKLAND #3 | 000/004 | ICS | E | Pre-2020_(9a) Other ignition related | Budget Owner (Paint) |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.169892 | 37.8468 | ETL.2740 | 40745871 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay
116744601 | T2 EI CARIBOU-PALEMO :26/220 BURIED MEMB | 44069454 | CARIBOU-PALERMO | :026/220 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.429893 | 39.8191 | ETL.3190 | 40618608 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
116744603 | T2 EI CRIBOU-PALRMO :27/222 PAINT STRT |  | CARIBOU-PALERMO | :027/222 |  | F | Pre-2020_(3) On high spread structure |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.433688 | 39.8145 | ETL.3190 | 40702271 | Structure-Tower | Paint/Coating | Repaint |  |  |  |  | PEND | LC | TLN | Maintenance | Expense |  | Table Mountain
116744606 | EI CORTINA-VACA 013/085 CANCEL | 44304829 | CORTINA-VACA | 013/085 | ICS | E | Pre-2020_(9a) Other ignition related |  |  | CANCEL/CNCL |  | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.114486 | 38.9453 | ETL.4540 | 40591070 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes
116744608 | EI CORTINA-VACA 013/084 CANCEL | 43729335 | CORTINA-VACA | 013/084 | ICS | E | Pre-2020_(9a) Other ignition related |  |  | CANCEL/CNCL |  | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.115552 | 38.947 | ETL.4540 | 40598512 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes
116744616 | T2 EI CORTNA-MNDCINO #1 025/122 RPNT STR | 43721139 | CORTINA-MENDOCINO #1 | 025/122 | ICS | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.654517 | 39.0287 | ETL.1330 | 40657052 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Lakeville |  |  | 2019-05-08
116744617 | T3 EI DRUM-HIGGINS 016/144 PNT STRT | 43738143 | DRUM-HIGGINS | 016/144 | ICS | E | Pre-2020_(9a) Other ignition related |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.002818 | 39.1426 | ETL.4393 | 40913040 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes
116744625 | T3 EI RND MTN-CTNWD #3 028/234 CANCEL | 43755803 | ROUND MTN-COTTONWOOD #3 | 028/234 | ICS | F | Pre-2020_(9a) Other ignition related |  |  | CANCEL/CNCL | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.950791 | 40.7772 | ETL.5650 | 40755449 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
116744638 | T3 EI RCK CRK-PE 011/082 PNT STRT | 43724473 | ROCK CREEK-POE | 011/082 | ICS | E | Pre-2020_(9a) Other ignition related |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.453946 | 39.7785 | ETL.5630 | 40690317 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Table Mountain |  |  | Yes
116744645 | T3 EI DRM-HGGNS 016/145 PNT STRT | 43738143 | DRUM-HIGGINS | 016/145 | ICS | E | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.006557 | 39.1411 | ETL.4393 | 40913041 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes
116744646 | T2 EI MTCLF-GRN VLLY 007/048 PNT STRT | 44300700 | METCALF-GREEN VALLEY | 007/048 | ICS | F | Pre-2020_(9a) Other ignition related |  |  |  |  | LATE | South | WSIP | FSRP | [5 empty] | '-121.682866 | 37.1535 | ETL.2540 | 40861181 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Moss Landing
116744649 | T2 EI CARIBOU-PALERMO :25/208 REPAINT | 44302715 | CARIBOU-PALERMO | :025/208 | ICS | F | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.419325 | 39.8395 | ETL.3190 | 40878271 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain
116744650 | T3 RNDMTN-CTNWD#3 28/232 CANCEL | 43900105 | ROUND MTN-COTTONWOOD #3 | 028/232 | ICS | E | Pre-2020_(9a) Other ignition related |  |  | CANCEL/CNCL | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.948693 | 40.7797 | ETL.5650 | 40662733 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
116744651 | T3 EI RND MTN-CTTNWD #3 028/233 CANCEL | 43755801 | ROUND MTN-COTTONWOOD #3 | 028/233 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  | CANCEL/CNCL | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.949661 | 40.7785 | ETL.5650 | 40653356 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
116744660 | T2 EI MTCLF-MSSLNDING #1 33/150 RPNT TWR | 44300679 | METCALF-MOSS LANDING #1 | 033/150 | ICS | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | South | WSIP | FSRP | [5 empty] | '-121.681472 | 37.1455 | ETL.5100 | 40596466 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Moss Landing
116744661 | EI DLVN-VC #2 163/1239 PNT STRT | 44452822 | DELEVAN-VACA #2 | 163/1239 | ICX | F | Pre-2020_(9a) Other ignition related |  |  | Likely MAT error - delink to correct |  | LATE | North Valley | WSIP | FSRP |  |  |  |  | Priority Bucket 9 | '-122.097185 | 38.9171 | ETL.4231 | 40869552 | Structure-Tower | Paint/Coating | Repaint | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense |  | Sacramento |  |  | Yes
116744664 | T2 EI DRM-HGGNS 019/159 PNT STRT | 43738143 | DRUM-HIGGINS | 019/159 | ICS | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.053528 | 39.1226 | ETL.4393 | 40913055 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes
116744674 | T2 EI CARIBOU-PALERMO :05/38 BURIED MEMB | 44059014 | CARIBOU-PALERMO | :005/038 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.216968 | 40.0432 | ETL.3190 | 40910281 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
116744675 | T3 EI RND MTN-CTTNWD #3 029/240 CANCEL | 43755801 | ROUND MTN-COTTONWOOD #3 | 029/240 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  | CANCEL/CNCL | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.957067 | 40.7696 | ETL.5650 | 40594999 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
116744677 | EI CORTINA-VACA 015/096 PAINT | 44304830 | CORTINA-VACA | 015/096 | ICS | F | Pre-2020_(3) On high spread structure | Budget Owner (Paint) |  |  |  | LATE | North Valley | WSIP |  |  |  |  | Program | 2021 Paint took out of program due to future project to be removed with S6B7 | '-122.100678 | 38.9225 | ETL.4540 | 40670968 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes
116744680 | T2 EI DRUM-HIGGINS 020/162 RPNT TWR | 43738143 | DRUM-HIGGINS | 020/162 | ICS | E | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.057427 | 39.1183 | ETL.4393 | 40913058 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes
116744681 | T2 EI DRUM-RIO OSO #1 018/149 RPNT TWR | 43746398 | DRUM-RIO OSO #1 | 018/149 | ICS | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.060911 | 39.1198 | ETL.1420 | 40865480 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes
116744682 | EI DLVN-VC #2 164/1240 PNT STRT | 44452824 | DELEVAN-VACA #2 | 164/1240 | ICX | F | Pre-2020_(9a) Other ignition related |  |  | Likely MAT error - delink to correct |  | LATE | North Valley | WSIP | FSRP |  |  |  |  | Priority Bucket 9 | '-122.096088 | 38.9153 | ETL.4231 | 40608953 | Structure-Tower | Paint/Coating | Repaint | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense |  | Sacramento |  |  | Yes
116744685 | T3 EI RNDMTN-CTNWD#3 032/271 CANCEL | 43755803 | ROUND MTN-COTTONWOOD #3 | 032/271 | ICS | E | Pre-2020_(9a) Other ignition related |  |  | CANCEL/CNCL | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.98802 | 40.7326 | ETL.5650 | 40594853 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
116744687 | T2NT EI PT #6 JCT-RND MTN14/129 PNT STRT | 43854766 | PIT #6 JCT-ROUND MTN | 014/129 | ICQ | F | Pre-2020_(9a) Other ignition related | Budget Owner (Paint) |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.938408 | 40.8088 | ETL.5440 | 40868192 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
116744688 | T3 EI RND MTN-CTTNWD #3 032/270 CANCEL | 43755801 | ROUND MTN-COTTONWOOD #3 | 032/270 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  | CANCEL/CNCL | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.986851 | 40.734 | ETL.5650 | 40605780 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Table Mountain |  |  | Yes
116744691 | T2 EI MRR BY-MS 020/091 PNT STRT | 43769287 | MORRO BAY-MESA | 020/091 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-120.592536 | 35.1733 | ETL.5290 | 40587104 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Pismo Beach |  |  | 2019-04-08
116744699 | T2 CARIBOU-PALERMO :4/37 RPR FOND | 44059014 | CARIBOU-PALERMO | :004/037 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.216388 | 40.0451 | ETL.3190 | 40907002 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
116744701 | T2 EI PIT #5-ROUND MTN #1 0/002 RPNT TWR | 44322478 | PIT #5-ROUND MTN #1 | 000/002 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.973862 | 40.9838 | ETL.5420 | 40660950 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
116744703 | T2 CARIBOU-PALERMO :4/32 RPR FOND | 44059014 | CARIBOU-PALERMO | :004/032 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.206261 | 40.0532 | ETL.3190 | 40910276 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
116744717 | T2 EI PT #5-RND MTN #2 000/006 PNT STRT | 43755669 | PIT #5-ROUND MTN #2 | 000/006 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | FSRP |  |  |  |  | Priority Bucket 9 | '-121.966566 | 40.9795 | ETL.5430 | 40810526 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
116744723 | T3 EI RNDMTN-CTNWD #3 032/268 RPNT TWR | 43755803 | ROUND MTN-COTTONWOOD #3 | 032/268 | ICS | E | Pre-2020_(9a) Other ignition related |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.984819 | 40.7364 | ETL.5650 | 40863128 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
116744727 | T2 EI PIT #5-ROUND MTN #2 0/004 RPNT TWR | 43755672 | PIT #5-ROUND MTN #2 | 000/004 | ICS | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.969026 | 40.9809 | ETL.5430 | 40752235 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
116744745 | T2 STAN MELONES SS :007/040 PAINT | 43712830 | STANISLAUS-MELONES SS-MANTECA #1+ | :007/040 | ICS | F | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.6377616 | 37.9827 | ETL.3830 | 40639678 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - Prog Multi
116744751 | T2NT EI PT #5-RND MTN #1 8/082 PNT STRT | 43758397 | PIT #5-ROUND MTN #1 | 008/082 | ICQ | F | Pre-2020_(2) High fire spread TD | Budget Owner (Paint) |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Program | 2021 | '-121.93003 | 40.878 | ETL.5420 | 40657422 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
116744755 | EI CORTINA-VACA 016/104 RPR PAINT CANCEL | 44304829 | CORTINA-VACA | 016/104 | ICS | E | Pre-2020_(9a) Other ignition related |  |  | CANCEL/CNCL |  | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.09058 | 38.9058 | ETL.4540 | 40596757 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes
116744756 | T2 EI DRUM-HIGGINS 022/176 RPNT TWR | 43738143 | DRUM-HIGGINS | 022/176 | ICS | E | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.094955 | 39.1062 | ETL.4393 | 40913072 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes
116744763 | T2NT EI PT #5-RND MTN #1 9/091 PNT STRT | 43758397 | PIT #5-ROUND MTN #1 | 009/091 | ICQ | F | Pre-2020_(4) TD tag on high spread line | Budget Owner (Paint) |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Internal Process | Circuit Based Scheduling | '-121.931538 | 40.8615 | ETL.5420 | 40660391 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
116744775 | T2 CARIBOU-PALERMO :23/196 REPAINT | 44302715 | CARIBOU-PALERMO | :023/196 | ICS | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.399908 | 39.853 | ETL.3190 | 40828384 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain
116744781 | T2 EI BCKS CRK-RCK CRK-CRST 1/11 PAINT | 43897313 | BUCKS CREEK-ROCK CREEK-CRESTA | 001/011 | ICS | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.345489 | 39.9088 | ETL.4430 | 40586032 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
116744782 | EI DELEVAN-VACA #2 164/1243 PAINT CANCEL | 44305192 | DELEVAN-VACA #2 | 164/1243 | ICS | E | Pre-2020_(9a) Other ignition related |  |  | CANCEL/CNCL |  | LATE | North Valley | WSIP | FSRP |  |  |  |  | Priority Bucket 9 | '-122.091479 | 38.9076 | ETL.4231 | 40656796 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes
116744783 | EI CORTINA-VACA 016/105 RPR PAINT | 44304830 | CORTINA-VACA | 016/105 | ICS | F | Pre-2020_(3) On high spread structure | Budget Owner (Paint) |  |  |  | LATE | North Valley | WSIP |  |  |  |  | Program | 2021 Paint took out of program due to future project to be removed with [REDACTED] | '-122.089838 | 38.9045 | ETL.4540 | 40589935 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes
116744785 | EI DELEVAN-VACA #2 164/1244 PAINT CANCEL | 44305192 | DELEVAN-VACA #2 | 164/1244 | ICS | E | Pre-2020_(9a) Other ignition related |  |  | CANCEL/CNCL |  | LATE | North Valley | WSIP | FSRP |  |  |  |  | Priority Bucket 9 | '-122.090391 | 38.9058 | ETL.4231 | 40759070 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes
116744791 | T2 EI RND MTN-CTTNWD #2 022/206 PNT STRT | 43691533 | ROUND MTN-COTTONWOOD #2 | 022/206 | ICQ | E | Pre-2020_(5) TD tag on other lines | Budget Owner (Paint) |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Internal Process | Circuit Based Scheduling | '-122.042248 | 40.6993 | ETL.5640 | 40816295 | Structure-Tower | No Good/Out of Stdrd | Repair | CONS srdy | CONS | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
116744795 | T2 EI STNL-MLN SW ST-MTC#1 :5/29PNT STRT | 43712827 | STANISLAUS-MELONES SS-MANTECA #1+ | :005/029 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.607476 | 37.9675 | ETL.3830 | 40856491 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - Prog Multi
116744797 | T2 EI DRM-HGGNS 022/177 PNT STRT | 43738143 | DRUM-HIGGINS | 022/177 | ICS | E | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.097356 | 39.1052 | ETL.4393 | 40913073 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes
116744800 | EI CORTINA-VACA -016/107 PAINT | 44304830 | CORTINA-VACA | 016/107 | ICS | F | Pre-2020_(3) On high spread structure | Budget Owner (Paint) |  |  |  | LATE | North Valley | WSIP |  |  |  |  | Program | 2021 Paint took out of program due to future project to be removed with [REDACTED] | '-122.08668 | 38.8993 | ETL.4540 | 40654590 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes
116744806 | T2 EI DRUM-RIO OSO #1 020/162 RPNT TWR | 43746398 | DRUM-RIO OSO #1 | 020/162 | ICS | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.094698 | 39.1064 | ETL.1420 | 40670155 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes
116744807 | T2 EI STNSLS-MLNS SW-MNTCA #1 :4/28 RPNT | 43712830 | STANISLAUS-MELONES SS-MANTECA #1+ | :004/028 | ICS | E | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.605922 | 37.9669 | ETL.3830 | 40875487 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - Prog Multi
116744808 | T2 EI STNSLS-MLN SW ST-MTC #1 PNT STRT | 43712827 | STANISLAUS-MELONES SS-MANTECA #1+ | :003/022 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) |  | Likely MAT error - delink to correct | TR2 | LATE | Central | WSIP | [6 empty] | '-120.589068 | 37.9602 | ETL.3830 | 40642906 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Victor |  | Y - Prog Multi
116744811 | T2NT EI CARIBOU-PLRMO :20/170 PAINT STRT |  | CARIBOU-PALERMO | :020/170 |  | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.363578 | 39.8908 | ETL.3190 | 40642282 | Structure-Tower | Paint/Coating | Repaint |  |  |  |  | PEND | LC | TLN | Maintenance | Expense |  | Table Mountain |  |  | Yes
116744814 | T3 EI MSRIFLT-GLDHLL#1 19/158 RPNT TWR | 44305273 | MISSOURI FLAT-GOLD HILL #1 | 019/158 | ICS | E | Pre-2020_(9a) Other ignition related |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.892042 | 38.6645 | ETL.2660 | 40862234 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes
116744816 | T2 EI DRUM-HIGGINS 027/208 RPNT TWR | 43738143 | DRUM-HIGGINS | 027/208 | ICS | E | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.092139 | 39.0472 | ETL.4393 | 40658224 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes
116744818 | T2 EI PIT #4 TAP 000/005 RPNT TWR | 43756947 | PIT #4 TAP | 000/005 | ICQ | F | Pre-2020_(9a) Other ignition related |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.862076 | 40.9854 | ETL.5432 | 40752299 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain
116744819 | EI CORTINA-VACA -017/113 PAINT | 44304829 | CORTINA-VACA | 017/113 | ICS | F | Pre-2020_(9a) Other ignition related |  |  |  |  | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.079737 | 38.8878 | ETL.4540 | 40865836 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes
116744820 | EI CORTINA-VACA -017/109 PAINT | 44304829 | CORTINA-VACA | 017/109 | ICS | E | Pre-2020_(9a) Other ignition related |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-122.085182 | 38.8968 | ETL.4540 | 40756643 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes
116744824 | T3 EI GYSRS #13 TP 000/005 PNT STRT | 43761567 | GEYSERS #13 TAP | 000/005 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  | Likely MAT error - delink to correct | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.73934 | 38.775 | ETL.4781 | 40746212 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville
116744825 | T2 EI DRUM-RIO OSO #1 021/166 RPNT TWR | 43746398 | DRUM-RIO OSO #1 | 021/166 | ICS | F | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.107424 | 39.1014 | ETL.1420 | 40805297 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes
116744834 | T2 EI CNTRA CSTA-MRG#1 024/111 PAINT | 43753199 | CONTRA COSTA-MORAGA #1 | 024/111 | ICS | F | Pre-2020_(9a) Other ignition related | Budget Owner (Paint) |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-122.117104 | 37.8602 | ETL.5452 | 40746201 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay
116744835 | T3 EI SNTAFEGTHERMAL TAP 0/3 RPNT TWR | 43729334 | SANTA FE GEOTHERMAL TAP | 000/003 | ICS | E | Pre-2020_(9a) Other ignition related |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.746969 | 38.7871 | ETL.4782 | 40659183 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Lakeville
116744836 | T3 EI MRG-SN LNDR #1 000/004 PNT STRT | 43715763 | MORAGA-SAN LEANDRO #1 | 000/004 | ICS | E | Pre-2020_(9a) Other ignition related | Budget Owner (Paint) |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.164395 | 37.8407 | ETL.2770 | 40764851 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  | Y - 10
116744837 | EI CORTINA-VACA 017/110 CANCEL | 44304829 | CORTINA-VACA | 017/110 | ICS | E | Pre-2020_(9a) Other ignition related |  |  | CANCEL/CNCL |  | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.083906 | 38.8947 | ETL.4540 | 40814753 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento
116744844 | EI CORTINA-VACA 018/118 CANCEL | 44304829 | CORTINA-VACA | 018/118 | ICS | E | Pre-2020_(9a) Other ignition related |  |  | CANCEL/CNCL |  | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.071843 | 38.8748 | ETL.4540 | 40756707 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes
116744847 | T2 EI STNSLS-MNS-MNTCA#1 20/125 RPNT TWR | 43712830 | STANISLAUS-MELONES SS-MANTECA #1+ | 020/125 | ICS | E | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.665458 | 37.9699 | ETL.3830 | 40744438 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - Prog Multi
116744848 | T3 EI MSRIFLT-GLDHLL#1 18/155 RPNT TWR | 44305273 | MISSOURI FLAT-GOLD HILL #1 | 018/155 | ICS | E | Pre-2020_(9a) Other ignition related |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.880254 | 38.6669 | ETL.2660 | 40761892 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes
116744852 | T3 EI MSSRIFLT-GLDHILL#1 18/154 RPNT TWR | 44305273 | MISSOURI FLAT-GOLD HILL #1 | 018/154 | ICS | E | Pre-2020_(9a) Other ignition related |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.875671 | 38.6678 | ETL.2660 | 40753623 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes
116744853 | T2 EI PT #4 TP 000/001 PNT STRT | 43756947 | PIT #4 TAP | 000/001 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP |  |  |  |  | Internal Process | Circuit Based Scheduling | '-121.849746 | 40.987 | ETL.5432 | 40592506 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Table Mountain
116744855 | T2 EI BCK CR-RK CR-CR 007/063 PAINT | 43897315 | BUCKS CREEK-ROCK CREEK-CRESTA | 007/063 | ICS | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.419304 | 39.8293 | ETL.4430 | 40656157 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
116744860 | T2 EI STNSLS-MLNSSW-MNTC#1 :0/1 RPNT TWR | 43712830 | STANISLAUS-MELONES SS-MANTECA #1+ | :000/001 | ICS | E | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.528009 | 37.9459 | ETL.3830 | 40599421 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - 9
116744861 | EI CORTINA-VACA -018/117 PAINT | 44304830 | CORTINA-VACA | 018/117 | ICS | F | Pre-2020_(3) On high spread structure | Budget Owner (Paint) |  |  |  | LATE | North Valley | WSIP |  |  |  |  | Program | 2021 Paint took out of program due to future project to be removed with [REDACTED] | '-122.073865 | 38.8781 | ETL.4540 | 40654591 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento
116744864 | EI CORTINA-VACA 18/116 PAINT | 44304830 | CORTINA-VACA | 018/116 | ICS | F | Pre-2020_(3) On high spread structure | Budget Owner (Paint) |  |  |  | LATE | North Valley | WSIP |  |  |  |  | Program | 2021 Paint took out of program due to future project to be removed with [REDACTED] | '-122.074727 | 38.8795 | ETL.4540 | 40670976 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes
116744865 | T3 EI MSRIFLT-GLDHLL#1 17/148 RPNT TWR | 44305273 | MISSOURI FLAT-GOLD HILL #1 | 017/148 | ICS | E | Pre-2020_(9a) Other ignition related |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.860207 | 38.6752 | ETL.2660 | 40873254 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes
116744866 | EI MORAGA-SAN LEANDRO #3 009/064 PAINT | 43728142 | MORAGA-SAN LEANDRO #3 | 009/064 | ICS | F | Pre-2020_(9a) Other ignition related | Budget Owner (Paint) |  |  |  | LATE | Central | WSIP | FSRP | [5 empty] | '-122.133778 | 37.7251 | ETL.2790 | 40745897 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  | Y - Prog Multi
116744869 | T2 DRUM-RIO OSO #1 024/180 PNT STRT | 44304427 | DRUM-RIO OSO #1 | 024/180 | ICS | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.148176 | 39.0851 | ETL.1420 | 40596161 | Structure-Steel | Paint/Coating | Other | CONS crdy | CONS | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes
116744872 | EI STANISLAUS-MANTECA#2 027/158 PAINT | 43713081 | STANISLAUS-MANTECA #2 | 027/158 | ICS | F | Pre-2020_(3) On high spread structure | Budget Owner (Paint) |  |  |  | LATE | Central | WSIP |  |  |  |  | Program | 2021 Paint took out of program due to future project to be removed with [REDACTED] | '-120.766736 | 37.9239 | ETL.3820 | 40856504 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - Prog Multi
116744876 | EI STAN-MEL SW ST-MA #1 026/166 PAINT | 43712830 | STANISLAUS-MELONES SS-MANTECA #1+ | 026/166 | ICS | E | Pre-2020_(9a) Other ignition related | Budget Owner (Paint) |  |  |  | LATE | Central | WSIP | [6 empty] | '-120.766791 | 37.924 | ETL.3830 | 40744440 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - Prog Multi
116744881 | T2 EI DRM-HGGNS 027/205 PNT STRT | 43738143 | DRUM-HIGGINS | 027/205 | ICS | E | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.096126 | 39.0533 | ETL.4393 | 40602393 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes
116744882 | T3 EI GYSRS #13 TP 001/009 PNT STRT | 43761567 | GEYSERS #13 TAP | 001/009 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  | Likely MAT error - delink to correct | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.755376 | 38.7783 | ETL.4781 | 40869699 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville
116744883 | EI STAN-MEL SW ST-MA #1 026/167 PAINT | 43712830 | STANISLAUS-MELONES SS-MANTECA #1+ | 026/167 | ICS | E | Pre-2020_(9a) Other ignition related | Budget Owner (Paint) |  |  |  | LATE | Central | WSIP | [6 empty] | '-120.768366 | 37.9236 | ETL.3830 | 40751408 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - Prog Multi
116744892 | T2 EI DRUM-RIO OSO #1 025/186 RPNT TWR | 43746398 | DRUM-RIO OSO #1 | 025/186 | ICS | F | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.163684 | 39.0789 | ETL.1420 | 40814362 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes
116744893 | T2 EI DRM-RIO OSO #1 025/187 PNT STRT | 44304427 | DRUM-RIO OSO #1 | 025/187 | ICS | F | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.165884 | 39.078 | ETL.1420 | 40813555 | Structure-Steel | Paint/Coating | Other | CONS crdy | CONS | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes
116744894 | T2 EI CARIBOU-PALERMO :23/195 REPAINT | 44302715 | CARIBOU-PALERMO | :023/195 | ICS | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.399102 | 39.8539 | ETL.3190 | 40758490 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain
116744898 | T3 EI GEYSERS #13 TAP 001/010 RPNT TWR | 43693054 | GEYSERS #13 TAP | 001/010 | ICS | E | Pre-2020_(9a) Other ignition related |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.759345 | 38.7788 | ETL.4781 | 40588014 | Structure-Steel | Paint/Coating | Other | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Lakeville
116744904 | T2 EI BALCH-SANGER 016/084 PAINT | 43709727 | BALCH-SANGER | 016/084 | ICS | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-119.319731 | 36.8237 | ETL.1050 | 40748595 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  | Y - 17
116744905 | T2 EI HS-MCCLL 019/103 PNT STRT | 43709743 | HAAS-MCCALL | 019/103 | ICQ | F | Pre-2020_(9a) Other ignition related |  |  | Likely MAT error - delink to correct | TR2 | LATE | South | WSIP | FSRP | [5 empty] | '-119.319818 | 36.8239 | ETL.4850 | 40657755 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Fresno
116744911 | T2 EI VCA-PRKWY 004/027 RPNT TWR | 44305724 | VACA-PARKWAY | 004/027 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.001644 | 38.4046 | ETL.5850 | 40813753 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes
116744913 | T2 EI DRUM-RIO OSO #1 024/181 RPNT STRT | 43746398 | DRUM-RIO OSO #1 | 024/181 | ICS | F | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.151287 | 39.0839 | ETL.1420 | 40587527 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes
116744918 | T2 EI DRM-RIO OSO #1 024/183 PNT STRT | 44304427 | DRUM-RIO OSO #1 | 024/183 | ICS | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.156721 | 39.0817 | ETL.1420 | 40654198 | Structure-Steel | Paint/Coating | Other | CONS crdy | CONS | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes
116744919 | EI STANISLAUS-MANTECA#2 026/156 PAINT | 43713081 | STANISLAUS-MANTECA #2 | 026/156 | ICS | F | Pre-2020_(3) On high spread structure | Budget Owner (Paint) |  |  |  | LATE | Central | WSIP |  |  |  |  | Program | 2021 Paint took out of program due to future project to be removed with S6B7 | '-120.759524 | 37.9261 | ETL.3820 | 40803378 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - Prog Multi
116744920 | EI STANISLAUS-MANTECA#2 026/153 PAINT | 43713081 | STANISLAUS-MANTECA #2 | 026/153 | ICS | E | Pre-2020_(9a) Other ignition related | Budget Owner (Paint) |  |  |  | LATE | Central | WSIP | [6 empty] | '-120.751638 | 37.9284 | ETL.3820 | 40651750 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - Prog Multi
116744921 | T2 CARIBOU-PALERMO :4/35 REPAINT STRT |  | CARIBOU-PALERMO | :004/035 |  | F | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.214156 | 40.0482 | ETL.3190 | 40910279 | Structure-Tower | Paint/Coating | Repaint |  |  |  |  | PEND | LC | TLN | Maintenance | Expense |  | Table Mountain
116744922 | T2 EI STNSLS-MLS-MNTC#1 20/131 CANCEL | 43712830 | STANISLAUS-MELONES SS-MANTECA #1+ | 020/131 | ICS | E | Pre-2020_(9a) Other ignition related | Budget Owner (Paint) |  | CANCEL/CNCL | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.677445 | 37.961 | ETL.3830 | 40604620 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - Prog Multi
116744926 | EI STANISLAUS-MANTECA #2 026/154 PAINT | 43713081 | STANISLAUS-MANTECA #2 | 026/154 | ICS | E | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) |  |  |  | LATE | Central | WSIP | [6 empty] | '-120.753705 | 37.9278 | ETL.3820 | 40750272 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - 14
116744929 | EI STANISLAUS-MANTECA #2 028/168 PAINT | 43713081 | STANISLAUS-MANTECA #2 | 028/168 | ICS | E | Pre-2020_(9a) Other ignition related | Budget Owner (Paint) |  |  |  | LATE | Central | WSIP | [6 empty] | '-120.791685 | 37.9165 | ETL.3820 | 40861754 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - 25
116744930 | EI STAN-MANTECA #2 026/155 PAINT | 43713081 | STANISLAUS-MANTECA #2 | 026/155 | ICS | E | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) |  |  |  | LATE | Central | WSIP | [6 empty] | '-120.756662 | 37.9269 | ETL.3820 | 40744469 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - 14
116744931 | T2NT EI STNSLS-MNTC #2 021/125 PNT STRT | 43712838 | STANISLAUS-MANTECA #2 | 021/125 | ICQ | F | Pre-2020_(4) TD tag on high spread line | Budget Owner (Paint) |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.682195 | 37.9573 | ETL.3820 | 40753678 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - Prog Multi
116744933 | T2 EI CRBU PALERMO :00/002 BENT STEEL | 43742125 | CARIBOU-PALERMO | :000/002 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.149439 | 40.0846 | ETL.3190 | 44188832 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
116744935 | T2 EI HAAS-MCCALL 021/114 RPNT TWR | 43709744 | HAAS-MCCALL | 021/114 | ICS | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | South | WSIP | FSRP | [5 empty] | '-119.360659 | 36.8153 | ETL.4850 | 40760132 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Fresno
116744938 | T2 EI BALCH-SANGER 007/044 PAINT | 43709727 | BALCH-SANGER | 007/044 | ICS | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-119.186531 | 36.8777 | ETL.1050 | 44307581 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  | Y - 17
116744952 | T2 EI CTTNWD #1 005/034 CANCEL | 44585953 | COTTONWOOD #1 | 005/034 | ICX | E | Pre-2020_(9a) Other ignition related |  |  | CANCEL/CNCL | TR2 | LATE | North Valley | WSIP | [5 empty] | Priority Bucket 9 | '-122.267813 | 40.3261 | ETL.6620 | 40910978 | Structure-Tower | Paint/Coating | Repaint | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense |  | Table Mountain |  |  | Yes
116744953 | T2NT EI PIT #1-CTTNWD 53/481 REPAINT | 43879363 | PIT #1-COTTONWOOD | 053/481 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.206769 | 40.4692 | ETL.5390 | 40592475 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Table Mountain |  |  | Yes
116744954 | T3 EI EGL RCK-FLTN-SLVRD 4/18 REPAINT | 43730698 | EAGLE ROCK-FULTON-SILVERADO | 004/018 | ICS | E | Pre-2020_(9a) Other ignition related |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.764133 | 38.671 | ETL.4392 | 41129321 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Lakeville
116744955 | T2 EI CTTNWD #1 :005/036 CANCEL | 44585953 | COTTONWOOD #1 | 005/036 | ICX | E | Pre-2020_(9a) Other ignition related |  |  | CANCEL/CNCL | TR2 | LATE | North Valley | WSIP | [5 empty] | Priority Bucket 9 | '-122.267779 | 40.3221 | ETL.6620 | 40910979 | Structure-Tower | Paint/Coating | Repaint | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense |  | Table Mountain |  |  | Yes
116744960 | T2 EI BALCH-SANGER 007/043 PAINT | 43709727 | BALCH-SANGER | 007/043 | ICS | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-119.184727 | 36.878 | ETL.1050 | 40646826 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  | Y - 17
116744961 | T2 EI DRUM-RIO OS #1 24/185 REPAINT STRT | 44304427 | DRUM-RIO OSO #1 | 024/185 | ICS | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.162231 | 39.0794 | ETL.1420 | 40746548 | Structure-Steel | Paint/Coating | Other | CONS crdy | CONS | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes
116744962 | T3 EI EAGLE ROCK-REDBUD :8/048 REPAINT | 43730053 | EAGLE ROCK-REDBUD | :008/048 | ICS | E | Pre-2020_(9a) Other ignition related |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.685011 | 38.8871 | ETL.1480 | 40861251 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Lakeville |  |  | 2019-06-04
116744973 | T2 EI DRUM-RIO OSO #1 26/194 REPNT STRT | 44304427 | DRUM-RIO OSO #1 | 026/194 | ICS | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.185517 | 39.07 | ETL.1420 | 40764902 | Structure-Steel | Paint/Coating | Other | CONS crdy | CONS | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Sacramento |  |  | Yes
116744974 | T2 EI PT #4 TP 000/004 PNT STRT | 43756947 | PIT #4 TAP | 000/004 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.859918 | 40.9857 | ETL.5432 | 40765746 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain
116744976 | T2 EI PIT #4 TAP 001/010 RPNT TWR | 43756947 | PIT #4 TAP | 001/010 | ICQ | F | Pre-2020_(9a) Other ignition related |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.875509 | 40.982 | ETL.5432 | 40601048 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain
116744977 | T2 EI PIT #4 TAP 000/002 RPNT TWR | 43756947 | PIT #4 TAP | 000/002 | ICQ | F | Pre-2020_(9a) Other ignition related |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.85332 | 40.9866 | ETL.5432 | 40688058 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain
116744978 | T2 EI DRUM-RIO OSO #1 26/195 REPAINT | 44304427 | DRUM-RIO OSO #1 | 026/195 | ICS | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.188222 | 39.0689 | ETL.1420 | 40762307 | Structure-Steel | Paint/Coating | Other | CONS crdy | CONS | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Sacramento |  |  | Yes
116744979 | T2 EI DRUM-HIGGINS 025/194 REPAINT | 43738143 | DRUM-HIGGINS | 025/194 | ICS | E | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.11171 | 39.0774 | ETL.4393 | 40868884 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes
116744981 | T2 EI VACA-LAKEVILLE #1 005/029 RPNT TWR | 43740456 | VACA-LAKEVILLE #1 | 005/029 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.012795 | 38.3963 | ETL.5840 | 40867684 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes
116744982 | T2NT EI DRUM-HIGGINS 25/196 REPAINT | 43738143 | DRUM-HIGGINS | 025/196 | ICS | E | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.108772 | 39.0728 | ETL.4393 | 40592845 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes
116744983 | T3 EI MSSR FLT-GLD #1 17/151 REPAINT | 44305273 | MISSOURI FLAT-GOLD HILL #1 | 017/151 | ICS | E | Pre-2020_(9a) Other ignition related |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.867462 | 38.6708 | ETL.2660 | 40913117 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes
116744984 | T3 EI POE-RIO OSO 19/131A REPAINT | 43737420 | POE-RIO OSO | 019/131A | ICS | E | Pre-2020_(9a) Other ignition related |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.482894 | 39.7089 | ETL.5540 | 43202197 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
116744985 | T3 EI EAGLE ROCK-REDBUD :5/30 REPAINT | 43730053 | EAGLE ROCK-REDBUD | :005/030 | ICS | E | Pre-2020_(9a) Other ignition related |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.743442 | 38.8779 | ETL.1480 | 40604567 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Lakeville |  |  | 2019-06-04
116744987 | T3 EI EAGLE ROCK-REDBUD :04/27 REPAINT | 43730053 | EAGLE ROCK-REDBUD | :004/027 | ICS | E | Pre-2020_(9a) Other ignition related |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.752407 | 38.8754 | ETL.1480 | 40808633 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Lakeville |  |  | Yes
116744992 | T2 EI DRUM-HIGGINS 025/197 REPAINT | 43738143 | DRUM-HIGGINS | 025/197 | ICS | E | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.107493 | 39.0709 | ETL.4393 | 40690102 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes
116744993 | T3 EI EAGLE ROCK-FN-SO 13/58 REPAINT | 43713428 | EAGLE ROCK-FULTON-SILVERADO | 013/058 | ICS | E | Pre-2020_(9a) Other ignition related |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.696251 | 38.5642 | ETL.4392 | 41129360 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Lakeville |  |  | 2019-09-19
116744995 | T3NT EI POE-RIO OSO 19/129 REPAINT | 43737420 | POE-RIO OSO | 019/129 | ICS | E | Pre-2020_(9a) Other ignition related |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.481635 | 39.716 | ETL.5540 | 40866272 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
116745003 | T2 EI DRUM-HIGGINS 024/191 REPAINT | 43738143 | DRUM-HIGGINS | 024/191 | ICS | E | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.116017 | 39.084 | ETL.4393 | 40818401 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes
116745005 | T2 EI DRUM-RIO OSO #1 27/199 REPANT STRT | 44304427 | DRUM-RIO OSO #1 | 027/199 | ICS | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.197637 | 39.0651 | ETL.1420 | 40865486 | Structure-Steel | Paint/Coating | Other | CONS crdy | CONS | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes
116745006 | T2 EI DRUM-RIO OSO #1 027/198 REPAINT | 44304427 | DRUM-RIO OSO #1 | 027/198 | ICS | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.195289 | 39.066 | ETL.1420 | 40858245 | Structure-Steel | Paint/Coating | Other | CONS crdy | CONS | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes
116745008 | T2 EI DRUM-RIO OSO #1 27/204 REPNT STRT | 44304427 | DRUM-RIO OSO #1 | 027/204 | ICS | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.208088 | 39.0608 | ETL.1420 | 40746585 | Structure-Steel | Paint/Coating | Other | CONS crdy | CONS | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes
116745016 | T3NT EI GEYSERS #12-FLTN 1/6 REPAINT | 43749452 | GEYSERS #12-FULTON | 001/006 | ICS | F | Pre-2020_(9a) Other ignition related |  |  |  | TR3 | <15D | North Coast | WSIP | [6 empty] | '-122.767206 | 38.7958 | ETL.4750 | 41129171 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Lakeville |  |  | 2019-09-03
116745018 | EI CRAG VIEW-CASCADE 11/96 CANCEL | 44406337 | CRAG VIEW-CASCADE | 011/096 | ICX | E | Pre-2020_(9a) Other ignition related |  |  | CANCEL/CNCL |  | LATE | North Valley | WSIP | [6 empty] | '-122.317514 | 40.7996 | ETL.1350 | 40808603 | Structure-Tower | Paint/Coating | Repaint | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense |  | Table Mountain
116745021 | T2NT EI DRUM-HIGGINS 24/188 REPAINT | 43738143 | DRUM-HIGGINS | 024/188 | ICS | E | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.119279 | 39.089 | ETL.4393 | 40658220 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes
116745023 | T2 EI DRUM-HIGGINS 021/172 REPAINT | 43738143 | DRUM-HIGGINS | 021/172 | ICS | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.083852 | 39.1106 | ETL.4393 | 40913068 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes
116745025 | T3 EI EGLE ROCK-REDBUD :06/38 REPNT STRT | 43730053 | EAGLE ROCK-REDBUD | :006/038 | ICS | E | Pre-2020_(9a) Other ignition related |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.721842 | 38.8817 | ETL.1480 | 40861249 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Lakeville
116745027 | T2 EI ELECTRA-BELLOTA 016/120 REPAINT | 43727726 | ELECTRA-BELLOTA | 016/120 | ICS | F | Pre-2020_(9a) Other ignition related | Budget Owner (Paint) |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.86647 | 38.1461 | ETL.4670 | 40822055 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - 2
116745028 | T2 EI DRUM-HIGGINS B010/101 REPAINT | 43738143 | DRUM-HIGGINS | B010/101 | ICS | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-120.928987 | 39.1487 | ETL.4393 | 41196114 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes
116745040 | T2 EI OLEUM-MARTINEZ 4/032 REPAINT | 43753565 | OLEUM-MARTINEZ | 004/032 | ICS | E | Pre-2020_(5b) On structure in bucket 5 | Budget Owner (Paint) |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.1795 | 38.0173 | ETL.3170 | 40644167 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  | Y - Prog Multi
116745042 | T3NT EI EAGL RCK-FLTN-SLVRD 03/16 REPANT | 43730698 | EAGLE ROCK-FULTON-SILVERADO | 003/016 | ICS | E | Pre-2020_(9a) Other ignition related |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.802137 | 38.8015 | ETL.4392 | 40814648 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Lakeville
116745044 | T2 EI CNTR CST-MRG #1 14/70 REPAINT | 43753199 | CONTRA COSTA-MORAGA #1 | 014/070 | ICS | E | Pre-2020_(9a) Other ignition related | Budget Owner (Paint) |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-121.977795 | 37.9161 | ETL.5452 | 40746195 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  |  | 2019-04-16
116745045 | T2 EI VC-LKVLL #1 008/043 REPAINT | 43705009 | VACA-LAKEVILLE #1 | 008/043 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP |  |  |  |  | Internal Process | Circuit Based Scheduling | '-122.037092 | 38.3617 | ETL.5840 | 40656087 | Structure-Steel | Paint/Coating | Other | CONS | CONS | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Sacramento |  |  | Yes
116745049 | T3 EI DRUM-HIGGINS 006/070 REPAINT | 43738143 | DRUM-HIGGINS | 006/070 | ICS | E | Pre-2020_(9a) Other ignition related |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.856996 | 39.191 | ETL.4393 | 40590064 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes
116745052 | T2 EI TIGER CREEK-ELCTRA 13/105 RPR FOND | 43713222 | TIGER CREEK-ELECTRA | 013/105 | ICQ | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.667127 | 38.3359 | ETL.5780 | 40752892 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - Prog Multi
116745055 | T3 EI DRUM-HIGGINS B09/87 REPAINT | 43738143 | DRUM-HIGGINS | B009/087 | ICS | E | Pre-2020_(9a) Other ignition related |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.893645 | 39.1652 | ETL.4393 | 40809702 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes
116745056 | T3 EI DRUM-HIGGINS 07/72 REPAINT | 43738143 | DRUM-HIGGINS | 007/072 | ICS | E | Pre-2020_(9a) Other ignition related |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.859746 | 39.1897 | ETL.4393 | 40682540 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento
116745057 | T3 EI EGL RCK-FLTN-SLVRD 2/14 REPAINT | 43730698 | EAGLE ROCK-FULTON-SILVERADO | 002/014 | ICS | E | Pre-2020_(9a) Other ignition related |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.797954 | 38.8065 | ETL.4392 | 40756573 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Lakeville |  |  | 2019-09-19
116745059 | T2 EI VACA-LAKEVILLE #1 10/051A RPNT TWR | 43740456 | VACA-LAKEVILLE #1 | 010/051A | ICS | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.052995 | 38.3397 | ETL.5840 | 40576568 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Sacramento |  |  | Yes
116745062 | T2 EI DRUM-RIO OSO #1 028/208 REPAINT | 44304427 | DRUM-RIO OSO #1 | 028/208 | ICS | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.219334 | 39.0563 | ETL.1420 | 40866026 | Structure-Steel | Paint/Coating | Other | CONS crdy | CONS | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes
116745067 | T2 EI DRUM-RIO OSO #1 28/209 REPNT STRT | 44304427 | DRUM-RIO OSO #1 | 028/209 | ICS | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.222266 | 39.0551 | ETL.1420 | 40870513 | Structure-Steel | Paint/Coating | Other | CONS crdy | CONS | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes
116745077 | T2 EI PIT#1-COTTONWD 42/358 REPAINT | 43879413 | PIT #1-COTTONWOOD | 042/358 | ICS | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.089058 | 40.6111 | ETL.5390 | 40868303 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
116745350 | T2 EI MTN GTE JCT-CSCDE 05/060 RPL STRW | 31498054 | MTN GATE JCT-CASCADE | 005/060 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.332241 | 40.6695 | ETL.7640 | 40770563 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain
116745614 | T2 EI MTN GTE JCT-CSCDE 003/32R RPR GYWW | 43758388 | MTN GATE JCT-CASCADE | 003/032 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.323652 | 40.6989 | ETL.7640 | 44565356 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
116746860 | T3 EI CARIBOU-PALERMO :10/83 RPL JUMPERS | 44304491 | CARIBOU-PALERMO | :010/083 | ICS | E | Pre-2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.272689 | 39.9931 | ETL.3190 | 40910324 | Jumper-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain
116746976 | T2 DI CLNGA #1-SAN MGL 032/001 REPL GYWS | 43763703 | COALINGA #1-SAN MIGUEL | 032/001 | ICS | E | Pre-2020_(4) TD tag on high spread line | Superintendent Approved work efficiency |  |  | TR2 | LATE | South | WSIP | FSRP | [5 empty] | '-120.635677 | 35.8254 | ETL.8580 | 40592554 | Guy Wire-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Pismo Beach |  | Y - 15
116747078 | T3 EI CRBRY SW ST-RND MT 24/198 PNT STRS | 43742123 | CARBERRY SW STA-ROUND MTN | 024/198 | ICS | E | Pre-2020_(9a) Other ignition related |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.887973 | 40.8052 | ETL.5410 | 40865167 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Table Mountain |  |  | Yes
116747134 | T3 EI KNCTI-MDDLTWN 28/003C RPR GYWW | 43761672 | KONOCTI-MIDDLETOWN | 028/003 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | North Coast | WSIP | [8 empty] | ETL.6380 | 44235468 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-05-29
116747181 | T3 EI KNCTI-MDDLTWN 28/003R RPR GYWW | 43761672 | KONOCTI-MIDDLETOWN | 028/003 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | North Coast | WSIP | [8 empty] | ETL.6380 | 44235469 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Lakeville |  |  | 2019-05-29
116747242 | T2 DI OLEUM-MARTINEZ 4/29 REPAINT | 43753565 | OLEUM-MARTINEZ | 004/029 | ICS | E | Pre-2020_(5b) On structure in bucket 5 | Budget Owner (Paint) |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.187423 | 38.0211 | ETL.3170 | 40804609 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  | Y - Prog Multi
116747380 | T2 EI PIT #1-COTTONWOOD 018/143 RPR SPLS |  | PIT #1-COTTONWOOD | 018/143 | ICS | E | Pre-2020_(2) High fire spread TD |  |  |  | TR2 | LATE | North Valley | WSIP | [5 empty] | 2021 | '-121.769035 | 40.8356 | ETL.5390 | 40657389 | Splice-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
116747392 | T2 METCALF-MOSS LANDNG #1 34/157 REPAINT | 44300674 | METCALF-MOSS LANDING #1 | 035/157 | ICS | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | South | WSIP | FSRP | [5 empty] | '-121.670918 | 37.1264 | ETL.5100 | 40810613 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Moss Landing
116747612 | EI MB-CALIF FLATS SS 33/142 REPL INSULS | 31439887 | MORRO BAY-GATES #2 | 033/142 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | South | WSIP | [6 empty] | '-120.4716251 | 35.7433 | ETL.5280 | 40714275 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - MCF
116747842 | T2 METCALF-MOSS LANDNG #1 34/156 REPAINT | 44300677 | METCALF-MOSS LANDING #1 | 034/156 | ICS | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | South | WSIP | FSRP | [5 empty] | '-121.670806 | 37.1291 | ETL.5100 | 40822603 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Moss Landing
116747864 | T2 EI PITTSBURG-TSLA #2 0/03 RMV NEST | 43753188 | PITTSBURG-TESLA #2 | 000/003 | ICS | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-121.66101 | 37.8221 | ETL.5520 | 43203982 | Structure-Steel | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay
116748174 | T2 EI HT CRK #1-WSTWD 046/887 RPL STRW | 31426976 | HAT CREEK #1-WESTWOOD | 046/887 | 70Y | E | Pre-2020_(2) High fire spread TD |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Access Issues | 2021 - Snow. | '-121.02308 | 40.4324 | ETL.7030 | 40656677 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain
116748212 | T2 EI MALIN-ROUND MTN #2 61/304 RPL INSS | 31439323 | MALIN-ROUND MTN #2 | 061/304 | 93K | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.661637 | 41.1972 | ETL.6020 | 40793838 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Capital | 532 | Table Mountain |  |  | Yes
116748618 | T2 EI MOSS LANDING-COBURN C07/31 REPAINT | 44300676 | MOSS LANDING-COBURN | C007/031 | ICS | E | Pre-2020_(9a) Other ignition related | Budget Owner (Paint) |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-121.276613 | 36.6223 | ETL.5330 | 40587144 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Moss Landing |  | Y - 7
116748699 | T3 EI EAGLE ROCK-REDBD :01/10 PAINT STRS | 43730053 | EAGLE ROCK-REDBUD | :001/010 | ICS | E | Pre-2020_(9a) Other ignition related |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.785141 | 38.8386 | ETL.1480 | 40588081 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 628 | Lakeville
116748815 | T2 EI MOSS LANDING-COBURN C08/32 REPAINT | 44300675 | MOSS LANDING-COBURN | C008/032 | ICS | E | Pre-2020_(9a) Other ignition related | Budget Owner (Paint) |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-121.275795 | 36.6209 | ETL.5330 | 40689404 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Moss Landing |  | Y - 7
116748864 | T2 EI MORRO BAY-TEMPLETN 13/55 RMV DBRS | 43735698 | MORRO BAY-TEMPLETON | 013/055 | ICS | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | South | WSIP | FSRP | [5 empty] | '-120.709847 | 35.5225 | ETL.5933 | 40762765 | Structure-Steel | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Pismo Beach |  | Y - 4
116748931 | T2 EI CARIBOU-PALERMO :3/030 INS HRDT | 44070463 | CARIBOU-PALERMO | :003/030 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.205437 | 40.0561 | ETL.3190 | 40910274 | Hardware-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain
116749686 | T3 EI CARIBOU-PALERMO :10/081 RPR HRDT | 44304491 | CARIBOU-PALERMO | :010/081 | ICS | E | Pre-2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.271411 | 39.9963 | ETL.3190 | 40910322 | Hardware-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain
116749687 | T3 EI CARIBOU-PALERMO :10/081 RPR CONDS | 44304491 | CARIBOU-PALERMO | :010/081 | ICS | E | Pre-2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.271411 | 39.9963 | ETL.3190 | 40910322 | Conductor-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain
116749708 | T2 EI CLGTE-PLRMO 011/212 RPR STRW | 43728969 | COLGATE-PALERMO | 011/212 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.369948 | 39.371 | ETL.6500 | 40767091 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
116749915 | T2 EI PIT #1-COTTONWOOD 49/426 RMV NEST | 43735854 | PIT #1-COTTONWOOD | 049/426 | ICS | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.156454 | 40.53 | ETL.5390 | 40819063 | Structure-Steel | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
116750089 | T2 DI CHRSTIE-SBRNTE 11/059 PNT STRS | 43751914 | CHRISTIE-SOBRANTE | 011/059 | ICS | E | Pre-2020_(9a) Other ignition related | Budget Owner (Paint) |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-122.197314 | 37.9898 | ETL.1260 | 40857610 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay
116753201 | T2 EI BLACK TAP 000/003 RPR ANCS | 44070470 | BLACK TAP | 000/003 | ICS | E | Pre-2020_(4) TD tag on high spread line | Superintendent Approved work efficiency |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.978299 | 40.9876 | ETL.5431 | 44188817 | Anchor-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Table Mountain
116753918 | DI SAN RAMON-MORAGA 20/88 RPL INSS | 31459455 | SAN RAMON-MORAGA | 020/088 | 93K | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-122.134955 | 37.8478 | ETL.5660 | 40633222 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - 4
116753919 | T3NT CARIBOU-PALERMO :30/248 PAINT STRT | 44302715 | CARIBOU-PALERMO | :030/248 | ICS | F | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR3 | <60D | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.455372 | 39.773 | ETL.3190 | 40878269 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
116754581 | EI FULTON-PUEBLO 040/208 RPR FOND | 43720989 | FULTON-PUEBLO | 040/208 | ICQ | F | Pre-2020_(9a) Other ignition related |  |  |  |  | LATE | North Coast | WSIP | FSRP | [5 empty] | '-122.719875 | 38.4968 | ETL.1600 | 40870811 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  | 2019-04-25
116755505 | T2 EI MS LNDNG-CBRN C006/026A RPR FOND | 44102662 | MOSS LANDING-COBURN | C006/026A | ICQ | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | South | WSIP | FSRP | [5 empty] | '-121.285723 | 36.6388 | ETL.5330 | 44149207 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Moss Landing |  | Y - 1 | 2019-04-15
116756134 | T2 EI MS LNDNG-CBRN C006/026 RPR FOND | 44102662 | MOSS LANDING-COBURN | C006/026 | ICQ | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | South | WSIP | FSRP | [5 empty] | '-121.28701 | 36.6437 | ETL.5330 | 40819514 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Moss Landing |  | Y - 1 | 2019-04-15
116756249 | EI SBRNTE-GRZLY-CLRMNT #1 A3/18 RPR FOND | 43752388 | SOBRNTE-GRIZZLY-CLARMNT #1+ | A003/018 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  | Likely MAT error - delink to correct |  | LATE | Central | WSIP | [6 empty] | '-122.245297 | 37.876 | ETL.3740 | 40857836 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 1 | 2019-04-08
116757531 | T2NT EI PIT#1-COTTONWD 17/137 REPAINT | 43879413 | PIT #1-COTTONWOOD | 017/137 | ICS | F | Pre-2020_(3) On high spread structure | Budget Owner (Paint) |  |  | TR2 |  | North Valley | WSIP |  |  |  |  | Program | 2021 Paint took out of program due to future project to be removed with [REDACTED] | '-121.762685 | 40.8439 | ETL.5390 | 40816505 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
116757726 | T2 EI DIABLO-MIDWAY #3 41/168 REPL INSS | 31443715 | DIABLO-MIDWAY #3 | 041/168 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | South | WSIP |  |  |  |  | Clearance Delayed | Diablo imposed clearance constraints, tag scheduled for 10/6-16 | '-120.136018 | 35.2052 | ETL.5980 | 44668416 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 15
116761592 | T3 DI PINE GROVE TAP 0/2 REPL PL | 31430351 | PINE GROVE TAP | 000/002 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-120.629911 | 38.3933 | ETL.8351 | 40665504 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 8
116762128 | EI FITCH MTN #1 TAP 00/04 RPR GYWW | 43761311 | FITCH MTN #1 TAP | 000/004 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | North Coast | WSIP | [6 empty] | '-122.845202 | 38.606 | ETL.6891 | 40750566 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  | 2019-07-19
116762247 | EI FITCH MTN #1 TAP 00/05 RPR GYWW | 43761311 | FITCH MTN #1 TAP | 000/005 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | North Coast | WSIP | [6 empty] | '-122.845713 | 38.6054 | ETL.6891 | 40750532 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  | 2019-07-19
116763686 | DI VLY SPRNGS #1 10/207 REPL SPLW | 43780878 | VALLEY SPRINGS #1 | 010/207 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-120.894428 | 38.1155 | ETL.8210 | 40908292 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 23
116764336 | T2 MORROBAY-SLO#2 4/26 RPL FLASHD INSULS | 31457244 | MORRO BAY-SAN LUIS OBISPO #2 | 004/026 | 93K | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.790436 | 35.3418 | ETL.2820 | 40835553 | Insulator-Steel | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  |  | 2019-04-08
116764620 | T2 EI RND MTN-T MTN #1 19/99 RPL INSS | 31455288 | ROUND MTN-TABLE MTN #1 | 019/099 | 93K | E | Pre-2020_(2) High fire spread TD |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Clearance Cancelled by GCC | 2021 - Cancelled by ISO | '-121.9439225 | 40.5248 | ETL.6060 | 40893009 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  | Yes
116764720 | T2 DI VLY SPRNGS #1 9/180 RPR STRW | 43831092 | VALLEY SPRINGS #1 | 009/180 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.87651 | 38.1266 | ETL.8210 | 40908265 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 23
116765400 | T2 DI CNTRA CSTA-MRAGA 024/114 RPR FOND |  | CONTRA COSTA-MORAGA #1 | 024/114 | ICQ | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-122.123696 | 37.8634 | ETL.5452 | 40818035 | Foundation/Concrete-Tower | Earth Covered Tower | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 7 | 2019-04-16
116766299 | T2 DI VALLY SPRINGS #1 7/146 RPR GYWW | 43831087 | VALLEY SPRINGS #1 | 007/146 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.860587 | 38.1468 | ETL.8210 | 40908229 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog Multi
116766368 | T3 EI TEMBLOR-SLO+51/288 REPAINT MEMBERS | 43740614 | TEMBLOR-SAN LUIS OBISPO | 051/288 | ICS | E | Pre-2020_(9a) Other ignition related |  |  |  | TR3 | LATE | South | WSIP | [6 empty] | '-120.550032 | 35.3151 | ETL.3960 | 40856740 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Pismo Beach
116766767 | T3 EI PT #1-CTTNWD 029/245 RPR FOND | 43930183 | PIT #1-COTTONWOOD | 029/245 | ICX | F | Pre-2020_(9a) Other ignition related |  |  | Likely MAT error - delink to correct | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.962249 | 40.7631 | ETL.5390 | 40744729 | Structure-Tower | Paint/Coating | Repaint | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense |  | Table Mountain |  |  | Yes
116766838 | EI MORR BY-SAN LUS OBSP #1 1/7 REPAINT | 43751755 | MORRO BAY-SAN LUIS OBISPO #1 | 001/007 | ICS | E | Pre-2020_(9a) Other ignition related |  |  |  |  | LATE | South | WSIP | [6 empty] | '-120.839462 | 35.3738 | ETL.2810 | 40810411 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Pismo Beach |  | Y - 4 | 2019-04-08
116766905 | DI VALLEY SPRINGS #1 12/241 RPL SPLW | 43831565 | VALLEY SPRINGS #1 | 012/241 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-120.919877 | 38.1037 | ETL.8210 | 40904216 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 23
116767246 | T2 DI MELONES-WILSON 000/001 INS GMKS | 43844901 | MELONES-WILSON | 000/001 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.537403 | 37.9443 | ETL.5080 | 40586992 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Released
116767314 | EI LKVLE-IGNACIO #1 IG002/011 RPNT STRS | 43761676 | LAKEVILLE-IGNACIO #1 | IG002/011 | ICS | F | Pre-2020_(9a) Other ignition related |  |  |  |  | LATE | North Coast | WSIP | FSRP | [5 empty] | '-122.522675 | 38.1054 | ETL.4940 | 40593209 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville |  |  | 2019-08-26
116767448 | T2 EI JFFRSN-HLLSDLE J 6/35 CANCEL | 44598165 | JEFFERSON-HILLSDALE JCT | 006/035 | ICI | E | Pre-2020_(5) TD tag on other lines |  |  | CANCEL/CNCL | TR2 | LATE | Central | WSIP | [6 empty] | '-122.356591 | 37.5248 | ETL.7190 | 40755149 | Insulator | Contaminated | Helicopter Wash | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 626 | Bay |  |  | SFWL
116767714 | T2 DI PNE GRV TAP 2/59 RPR GYWW | 43749302 | PINE GROVE TAP | 002/059 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.659255 | 38.4133 | ETL.8351 | 40587998 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 3
116767794 | T2 DI STANISLAUS-MNTC 9/56 BENT STEEL | 43842120 | STANISLAUS-MANTECA #2 | 009/056 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.516414 | 38.068 | ETL.3820 | 40809563 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - Prog Multi
116767807 | EI MR BY-SN LS BSP #1 000/006 PAINT | 43751755 | MORRO BAY-SAN LUIS OBISPO #1 | 000/006 | ICS | E | Pre-2020_(9a) Other ignition related |  |  |  |  | LATE | South | WSIP | [6 empty] | '-120.841416 | 35.3744 | ETL.2810 | 40811024 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Pismo Beach |  | Y - 12 | 2019-04-08
116788698 | T2 DI PN GRV TAP 2/55 RPR GYWW | 43749302 | PINE GROVE TAP | 002/055 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.656532 | 38.4132 | ETL.8351 | 40811754 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 3
116788722 | T2 DI OLEUM-MRTNZ 5/36 PNT STRT | 43753565 | OLEUM-MARTINEZ | 005/036 | ICS | E | Pre-2020_(5b) On structure in bucket 5 | Budget Owner (Paint) |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.166232 | 38.0109 | ETL.3170 | 40868916 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  | Y - Prog Multi
116788877 | DI VALLEY SPRINGS #1 000/003 RPR STRW | 43831323 | VALLEY SPRINGS #1 | 000/003 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-120.763949 | 38.2144 | ETL.8210 | 40904179 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 23
116789057 | T2 EI OLEUM-G #1 001/010 RPL INSS HRD | 44103166 | OLEUM-G #1 | 001/010 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.234025 | 38.0385 | ETL.3150 | 40622200 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - 6
116789270 | DI VLLY SPRNGS-CLAY 5/77 RPR GYWW | 43844012 | VALLEY SPRINGS-CLAY | 005/077 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | Central | WSIP | [8 empty] | ETL.8264 | 44255307 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 12
116789343 | DI VALLEY SPRINGS #1 0/9 RPR GYWW | 43831326 | VALLEY SPRINGS #1 | 000/009 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-120.769115 | 38.2106 | ETL.8210 | 40904185 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 23
116789361 | DI VLLY SPRNGS-CLAY 5/77 RPR GYWW | 43844012 | VALLEY SPRINGS-CLAY | 005/077 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | Central | WSIP | [8 empty] | ETL.8264 | 44255308 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 12
116789392 | DI VLLY SPRNGS-CLAY 5/77 RPR STRW | 43844012 | VALLEY SPRINGS-CLAY | 005/077 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | Central | WSIP | [8 empty] | ETL.8264 | 44255308 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 12
116789396 | T2 DI VLY SPRNGS 6/86 RPR GYWW | 43844012 | VALLEY SPRINGS-CLAY | 006/086 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.833612 | 38.2116 | ETL.8264 | 40905033 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog Multi
116789501 | T2 DI VLLY SPRNGS-CLAY 5/78 RPL STRW | 31501102 | VALLEY SPRINGS-CLAY | 005/078 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.830224 | 38.201 | ETL.8264 | 40904716 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 12
116789651 | T2 DI VLLY SPRNGS-CLAY 5/79 RPR STRW | 43844012 | VALLEY SPRINGS-CLAY | 005/079 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.830564 | 38.2022 | ETL.8264 | 40905031 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 12
116789755 | T2 MTN GATE JCT-CASCADE 3/35L INS MRKW | 43758388 | MTN GATE JCT-CASCADE | 003/035 | ICW | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.32463 | 40.6951 | ETL.7640 | 44565379 | Marker (i.e. signs)-Wood | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
116789772 | T2 EI MTN GT JCT-CASCADE 3/35L RPR INSW | 43758388 | MTN GATE JCT-CASCADE | 003/035 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.32463 | 40.6951 | ETL.7640 | 40855887 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
116789809 | T2 DI VLY SPRNGS-CLY 6/88 RPR GYWW | 43844012 | VALLEY SPRINGS-CLAY | 006/088 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.834348 | 38.2139 | ETL.8264 | 40904723 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog Multi
116789827 | EI KILARC-DESCHUTES A026/547 RPL STRW | 31431892 | KILARC-DESCHUTES | A026/547 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-122.30127 | 40.5711 | ETL.7300 | 40828782 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
116789842 | EI IGNACIO-STAFFORD A005/104 REPL STRW | 31469870 | ETL.1042.POLE.WOOD | A005/104 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | North Coast | WSIP | [6 empty] | '-122.608792 | 38.1177 | ETL.1042 | 40585464 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  | 2019-07-19
116789947 | EI KILARC-DESCHUTES A026/548 REPL STRW | 31431892 | KILARC-DESCHUTES | A026/548 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-122.302175 | 40.5711 | ETL.7300 | 40826841 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
116789960 | T2 DI PINE GRV TAP 2/57 RPL STRW | 31430351 | PINE GROVE TAP | 002/057 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.658161 | 38.4132 | ETL.8351 | 40863882 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Victor |  | 2020-09-24
116789964 | T2 DI PINE GROVE TAP 2/60 RPR GYWW | 43749302 | PINE GROVE TAP | 002/060 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.659412 | 38.4129 | ETL.8351 | 40754205 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 3
116789980 | T2 DI VLY SPRNGS-CLY 6/88 RPR GRWW | 43844012 | VALLEY SPRINGS-CLAY | 006/088 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.834348 | 38.2139 | ETL.8264 | 40904723 | Ground Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog Multi
116790111 | T2 DI VLY SPRNGS-CLY 6/85 CANCEL |  | VALLEY SPRINGS-CLAY | 006/085 | ICW | E | Pre-2020_(4b) On structure in bucket 4 |  |  | CANCEL/CNCL | TR2 | LATE | Central | WSIP | [6 empty] | '-120.833081 | 38.2099 | ETL.8264 | 40904721 | Marker (i.e. signs)-Wood | Missing | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog Multi
116790114 | T2 DI VLY SPRNGS-CLY 6/85 RPR STRW | 43844012 | VALLEY SPRINGS-CLAY | 006/085 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.833081 | 38.2099 | ETL.8264 | 40904721 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog Multi
116790295 | T2 DI VALLEY SPRINGS 006/090 RPL STRW | 31426450 | VALLEY SPRINGS-CLAY | 006/090 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.834766 | 38.2154 | ETL.8264 | 40904724 | Structure-Wood | Rotten | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - Prog Multi
116790447 | T3 DI GROVE TAP 001/029 RPR STRW | 43749302 | PINE GROVE TAP | 001/029 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-120.644002 | 38.4053 | ETL.8351 | 40812438 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 3
116790570 | EI TESLA-NEWARK #2 9/68 RPR STRT |  | TESLA-NEWARK #2 | 009/068 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-121.732718 | 37.6573 | ETL.5354 | 41152613 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 7
116790672 | T2 DI OLEUM-MARTINEZ 6/42 RPR INSS HRD | 44326132 | OLEUM-MARTINEZ | 006/042 | ICS | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.148856 | 38.0027 | ETL.3170 | 40671259 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - 3
116790835 | T2 DI VLLY SPRNGS 7/106 RPR STRW | 43844187 | VALLEY SPRINGS-CLAY | 007/106 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.8421 | 38.2282 | ETL.8264 | 40904739 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 12
116790836 | T2 DI VALLEY SPRINGS #1 8/164 RPR STRW | 43831090 | VALLEY SPRINGS #1 | 008/164 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.868271 | 38.1361 | ETL.8210 | 40908247 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 23
116791051 | EI TESLA-NEWARK #2 010/070 PAINT STRS | 43753285 | TESLA-NEWARK #2 | 010/070 | ICS | E | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) |  |  |  | LATE | Central | WSIP | [6 empty] | '-121.735992 | 37.6556 | ETL.5354 | 41152615 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay
116791510 | T2 EI TRCY-LS BANOS 31/148 RPR GYWS | 43844596 | TRACY-LOS BANOS | 031/148 | ICS | E | Pre-2020_(5) TD tag on other lines |  |  | Tower guy | TR2 | LATE | Central | WSIP | [6 empty] | '-121.209138 | 37.4756 | ETL.6130 | 40873336 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Victor |  | Y - Prog Multi
116791828 | T2 DI VLLY SPRNGS-CLAY 7/108 RPL GMKW | 43844187 | VALLEY SPRINGS-CLAY | 007/108 | ICW | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.84447 | 38.2308 | ETL.8264 | 40904740 | Guy Wire Mark /Indic-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 12
116791848 | T2 DI SOBRANTE-STD OIL 003/019 RPR FOND |  | SOBRANTE-STANDARD OIL SW STA #2 | 003/019 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-122.205863 | 37.9483 | ETL.3800 | 40857808 | Foundation/Concrete-Tower | Earth Covered Tower | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 5
116791879 | T2 EI PIT #3-PIT #1 000/000B INST MRKS | 43877630 | PIT #3-PIT #1 | 000/000B | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.498067 | 40.9916 | ETL.5400 | 41184138 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
116791955 | T2 EI PIT #3-PIT #1 000/000B RPR GYWS | 43877630 | PIT #3-PIT #1 | 000/000B | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.498067 | 40.9916 | ETL.5400 | 41184138 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Table Mountain |  |  | Yes
116792003 | T2 EI PT #3-PT #1 000/000A INST GMKS | 43877630 | PIT #3-PIT #1 | 000/000A | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.498029 | 40.9917 | ETL.5400 | 41184137 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
116792115 | T3 DI MORAGA-CASTRO VLLEY 10/46 CANCEL | 43744386 | MORAGA-CASTRO VALLEY | 010/046 | ICS | E | Pre-2020_(9a) Other ignition related | Budget Owner (Paint) |  | CANCEL/CNCL | TR3 | LATE | Central | WSIP | [6 empty] | '-122.066475 | 37.7321 | ETL.5250 | 40816974 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay
116792381 | T2 DI VALLEY SPRINGS-CLAY 6/84 RPL GYWW | 43844012 | VALLEY SPRINGS-CLAY | 006/084 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.832294 | 38.2077 | ETL.8264 | 40904720 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog Multi
116792653 | T2 DI STNSLS-MANTECA #2 8/50 CANCEL | 43842120 | STANISLAUS-MANTECA #2 | 008/050 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  | CANCEL/CNCL | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.498855 | 38.0775 | ETL.3820 | 40579634 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - Prog Multi
116792855 | T2 EI FULTON-PUEBLO 14/068 PAINT STRS | 43720980 | FULTON-PUEBLO | 014/068 | ICS | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.252392 | 38.5068 | ETL.1600 | 40870813 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville |  |  | 2019-04-25
116793205 | T2 DI VLLEY SPRNGS-CLY 007/110 INST GMKW | 43844187 | VALLEY SPRINGS-CLAY | 007/110 | ICW | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.846018 | 38.2325 | ETL.8264 | 40904742 | Guy Wire Mark /Indic-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 12
116793208 | T2 DI VLLEY SPRNGS-CLY 007/110 RPR GWSW | 43844187 | VALLEY SPRINGS-CLAY | 007/110 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.846018 | 38.2325 | ETL.8264 | 40904742 | Auto Guy Wire Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 12
116794356 | EI TESLA-NEWARK #2 19/129 PAINT STRS | 43753285 | TESLA-NEWARK #2 | 019/129 | ICS | E | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) |  |  |  | LATE | Central | WSIP | [6 empty] | '-121.872042 | 37.5693 | ETL.5354 | 41152675 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  |  | SFWL
116802155 | T2 DI OLEUM-MRTNZ 005/037 RPNT STRT | 43753565 | OLEUM-MARTINEZ | 005/037 | ICS | E | Pre-2020_(9a) Other ignition related | Budget Owner (Paint) |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-122.163536 | 38.0096 | ETL.3170 | 40857603 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  | Y - Prog Multi
116802386 | T2 DI MTCLF-GRN VLY 007/051 RPR STRT | 44140745 | METCALF-GREEN VALLEY | 007/051 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-121.679262 | 37.1472 | ETL.2540 | 40585522 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Moss Landing |  | Y - 9
116802626 | T2 DI VLLY SPRNGS-CLAY 7/104 RPR GYWW | 43844187 | VALLEY SPRINGS-CLAY | 007/104 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.840996 | 38.2269 | ETL.8264 | 40904737 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog Multi
116802673 | T2 DI VALLEY SPRINGS #1 009/189 RPR GYWW | 43831094 | VALLEY SPRINGS #1 | 009/189 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.881616 | 38.1209 | ETL.8210 | 40908274 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog Multi
116803110 | EI KONOCTI-MIDDLETOWN_;023/006 REPL GUY | 43760955 | KONOCTI-MIDDLETOWN | ;023/006 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  | Likely MAT error - delink to correct |  | LATE | North Coast | WSIP | FSRP | [5 empty] | '-122.609077 | 38.8978 | ETL.6380 | 40810828 | Guy Pole-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 637 | Lakeville |  |  | 2019-05-29
116803343 | T2 EI OLEUM-G #1 6/43 REPAINT | 44586166 | OLEUM-G #1 | 006/043 | ICS | E | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.260076 | 37.9695 | ETL.3150 | 40659401 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  | Y - 8
116803523 | T2 FULTON-HOPLAND 037/005 RPL POLE | 31510603 | FULTON-HOPLAND | 037/005 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.063025 | 38.9428 | ETL.6890 | 40769687 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  | 2019-06-18
116803566 | T2NT EI OLEUM-G #1 7/45 PAINT STRS | 43752220 | OLEUM-G #1 | 007/045 | ICS | F | Pre-2020_(3) On high spread structure | Budget Owner (Paint) |  |  | TR2 | <60D | Central | WSIP |  |  |  |  | Program | 2021 Paint took out of program due to future project to be removed with [REDACTED] | '-122.263942 | 37.9641 | ETL.3150 | 40746017 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  | Y - 8
116803721 | T3 EI RND MTN-TBL MTN #1 5/29 RPL SPLS | 43790345 | ROUND MTN-TABLE MTN #1 | 005/029 | ICS | E | Pre-2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP |  |  |  |  | Clearance Cancelled by GCC | 2021 - Cancelled by ISO | '-121.941773 | 40.7323 | ETL.6060 | 40868400 | Splice-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
116803923 | T2 EI SMARTVILLE-MARY 8/156 RPR GYWW | 43760141 | SMARTVILLE-MARYSVILLE | 008/156 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.422903 | 39.2262 | ETL.7980 | 40767569 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | CalTrans
116803934 | EI KONOCTI-MIDDLETOWN_012/005 RPR INSW | 43761672 | KONOCTI-MIDDLETOWN | 012/005 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | North Coast | WSIP | FSRP | [5 empty] | '-122.608451 | 38.7563 | ETL.6380 | 40768995 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  | 2019-05-29
116804088 | EI KONOCTI-MIDDLETOWN_012/008 CANCEL | 43761672 | KONOCTI-MIDDLETOWN | 012/008 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  | CANCEL/CNCL |  | LATE | North Coast | WSIP | FSRP | [5 empty] | '-122.605367 | 38.7579 | ETL.6380 | 40876752 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  | 2019-05-29
116804501 | T3 EI SOBRANTE-R 2/019 #1 PAINT STRS | 43727737 | SOBRANTE-R #1 | 002/019 | ICS | E | Pre-2020_(9a) Other ignition related | Budget Owner (Paint) |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.258062 | 37.9131 | ETL.3770 | 40857825 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay
116804818 | EI BRDGVLL-CTTNWD 45/355 CANCEL COA | 43742049 | BRIDGEVILLE-COTTONWOOD | 045/355 | ICS | E | Pre-2020_(2) High fire spread TD |  |  | CANCEL/CNCL |  | LATE | North Valley | WSIP | [5 empty] | 2021 - Snow . FSR 12/2020. Work is complete. Tag to be Cancelled. |  |  | ETL.1110 | 44424624 | Damper-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
116804987 | T2 EI SOBRANTE-MORAGA 000/004 INSW | 44388405 | SOBRANTE-MORAGA | 000/004 | ICS | E | Pre-2020_(5) TD tag on other lines |  |  | Likely MAT error - delink to correct | TR2 | LATE | Central | WSIP | [6 empty] | '-122.206472 | 37.9045 | ETL.3742 | 41135445 | Insulator | Contaminated | Ground Wash | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 622 | Bay |  | Y - 7
116805069 | T2 DI VLLEY SPRINGS-CLAY 13/172 RPL STRW | 31426450 | VALLEY SPRINGS-CLAY | 013/172 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.897389 | 38.2816 | ETL.8264 | 40904778 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 12
116805120 | T2 DI VLLEY SPRNGS-CLAY 6/91 RPR GYWW | 43844012 | VALLEY SPRINGS-CLAY | 006/091 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.835072 | 38.2161 | ETL.8264 | 40904725 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog Multi
116805131 | EI KONOCTI-MIDDLETOWN_016/001 RPL STRW | 31456914 | KONOCTI-MIDDLETOWN | 016/001 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | North Coast | WSIP | FSRP | [5 empty] | '-122.568817 | 38.7975 | ETL.6380 | 40600741 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  | 2019-05-29
116805216 | EI BRDGVLL-CTTNWD 45/355C CANCEL COA | 44143775 | BRIDGEVILLE-COTTONWOOD | 045/355 | ICS | E | Pre-2020_(2) High fire spread TD |  |  | CANCEL/CNCL |  | LATE | North Valley | WSIP | [5 empty] | 2021 - Snow . FSR 12/2020. Work is complete. Tag to be Cancelled. |  |  | ETL.1110 | 44424623 | Damper-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
116805609 | EI KONOCTI-MIDDLETOWN_016/012 RPR GYWW | 43761672 | KONOCTI-MIDDLETOWN | 016/012 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | North Coast | WSIP | FSRP | [5 empty] | '-122.572714 | 38.8069 | ETL.6380 | 40699007 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  | 2019-07-26
116805697 | T3 DI MSSR FLT-GLD HL #1 19/160 RPL INSS | 31451775 | MISSOURI FLAT-GOLD HILL #1 | 019/160 | 93K | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.900523 | 38.6629 | ETL.2660 | 40636540 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Sacramento |  |  | Yes
116805824 | T2 DI VLLY SPRNGS-CLAY 007/105 RPR HRDD | 43844187 | VALLEY SPRINGS-CLAY | 007/105 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.841288 | 38.2273 | ETL.8264 | 40904738 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog Multi
116806126 | T2 DI VLLY SPRNGS-CLAY 013/179 RPR STRW | 43844187 | VALLEY SPRINGS-CLAY | 013/179 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.903365 | 38.2847 | ETL.8264 | 41167566 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog Multi
116808493 | T2NT DI VLY SPRGS-CLY 12/171 INST MRKW | 43844187 | VALLEY SPRINGS-CLAY | 012/171 | ICW | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.896517 | 38.2811 | ETL.8264 | 40904777 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog Multi
116808495 | T2 DI VLLEY SPRGS-CLAY 12/171 RPR GYWW | 43844187 | VALLEY SPRINGS-CLAY | 012/171 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.896517 | 38.2811 | ETL.8264 | 40904777 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog Multi
116808505 | T2 DI CLAY-MARTEL 23/327 RPL STRW | 31422461 | CLAY-MARTEL | 023/327 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.835885 | 38.3523 | ETL.8250 | 40812116 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Victor |  | Y - 33
116808704 | T2 EI RND MTN-CTTNWD #3 35/296 RPR INSS | 44624619 | ROUND MTN-COTTONWOOD #3 | 035/296 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.015054 | 40.7002 | ETL.5650 | 40816921 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
116810212 | DISTRIBUTION BENT MEMBER |  | SPARE T-LINE RECORD | T095 | ICQ | E | Pre-2020_(2) High fire spread TD |  |  | Midway-Santa Maria | TR3 | LATE | South | WSIP | [6 empty] | '-120.17661 | 35.0542 | ETL.9240 | 43249571 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Midway
116810592 | T2 DI VLLY SPRNGS-CLY 17/247 STP BLT | 43844010 | VALLEY SPRINGS-CLAY | 017/247 | ICS | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.935049 | 38.3395 | ETL.8264 | 40904838 | Hardware-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - Prog Multi
116810756 | T2 DI PLACER-DEL MAR 0/21 RPR GYWW | 43755677 | PLACER-DEL MAR | 000/021 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.097344 | 38.8904 | ETL.7800 | 40758278 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
116811515 | EI IGNACIO-SAN RAFAEL #1 002/014 FOND | 43715549 | IGNACIO-SAN RAFAEL #1 | 002/014 | ICQ | F | Pre-2020_(9a) Other ignition related |  |  |  |  | LATE | North Coast | WSIP | FSRP | [5 empty] | '-122.533646 | 38.0488 | ETL.1850 | 40753422 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville |  |  | 2019-04-29
116813128 | DI VLLY SPRNGS-CLY 013/178 RPR GYWW | 43844187 | VALLEY SPRINGS-CLAY | 013/178 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-120.902332 | 38.2843 | ETL.8264 | 40904784 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog Multi
116813186 | EI KONOCTI-MIDDLETOWN 029/002 GYWW | 43761672 | KONOCTI-MIDDLETOWN | 029/002 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | North Coast | WSIP | FSRP | [5 empty] | '-122.626008 | 38.9122 | ETL.6380 | 40656001 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  | 2019-05-29
116813198 | EI KONOCTI-MIDDLETOWN 29/2 RPL STRW | 43761672 | KONOCTI-MIDDLETOWN | 029/002 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  | Likely MAT error - delink to correct |  | LATE | North Coast | WSIP | FSRP | [5 empty] | '-122.626008 | 38.9122 | ETL.6380 | 40656001 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  | 2019-05-29
116814498 | T3 EI GRIZZLY TAP 3/12 RPR GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 003/012 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.322423 | 39.9075 | ETL.2395 | 44551439 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
116814647 | T3 EI GRIZZLY TAP 003/017L RPR GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 003/017 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.323704 | 39.9096 | ETL.2395 | 44551421 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
116814648 | T3 EI GRIZZLY TAP 004/001L RPR GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 004/001 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.326678 | 39.911 | ETL.2395 | 44551404 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
116814672 | T3 EI GRIZZLY TAP 003/020L RPR GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 003/020 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.325883 | 39.9106 | ETL.2395 | 44551441 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
116814748 | T3 EI GRIZZLY TAP 003/016 (L) RPR ANCW | 43760153 | TAP (CITY OF SANTA CLARA) | 003/016 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.3233411 | 39.9089 | ETL.2395 | 44551359 | Anchor-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
116814749 | T3 EI GRIZZLY TAP 3/15 RPR CONW | 43760153 | TAP (CITY OF SANTA CLARA) | 003/015 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.323076 | 39.9087 | ETL.2395 | 40782201 | Conductor-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
116814753 | T3NT EI GRIZZLY TAP 3/16 INST GMKW | 43760153 | TAP (CITY OF SANTA CLARA) | 003/016 | ICW | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.3233411 | 39.9089 | ETL.2395 | 44551359 | Guy Wire Mark /Indic-Wood | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
116814806 | T2 DI VLLY SPRGS-CLAY 9/125 RPL SPLW | 43844187 | VALLEY SPRINGS-CLAY | 009/125 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.850969 | 38.2495 | ETL.8264 | 40904752 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 12
116815113 | T2 DI OLEUM-MARTINEZ 004/031 RPL SPLS | 43753565 | OLEUM-MARTINEZ | 004/031 | ICS | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.18146 | 38.0182 | ETL.3170 | 40745836 | Splice-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - Prog Multi
116815141 | DISTRIBUTION INSL | 31431489 | SAN LUIS OBISPO-SANTA MARIA (IDLE) | 010/173 | 93E | E | Pre-2020_(1b) Lines with special commitments |  |  | Likely MAT error - delink to correct | TR2 | LATE | South | WSIP | FSRP | [5 empty] | '-120.526441 | 35.1615 | ETL.9100 | 44188919 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Pismo Beach |  | Y - 4
116815208 | T3 DI CNTR CST-MRG #1 20/96 RPNT STRT | 43744389 | CONTRA COSTA-MORAGA #1 | 020/096 | ICS | E | Pre-2020_(9a) Other ignition related | Budget Owner (Paint) |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.057676 | 37.8593 | ETL.5452 | 40604247 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  |  | 2019-04-16
116815221 | T2 DI VLLY SPRNGS 010/193 RPR STRW | 43831093 | VALLEY SPRINGS #1 | 010/193 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.884174 | 38.119 | ETL.8210 | 40908278 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 23
116815826 | T2 DI STNSLS-MNTCA #2 014/084 RPR FND | 43842120 | STANISLAUS-MANTECA #2 | 014/084 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.592282 | 38.0263 | ETL.3820 | 40764248 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - Prog Multi
116815828 | T2 DI STNSLS-MNTCA #2 014/082 RPR FOND | 43842120 | STANISLAUS-MANTECA #2 | 014/082 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.588337 | 38.0288 | ETL.3820 | 40642926 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - Prog Multi
116815861 | T2 DI VLY SPRNGS-CLY 13/180 GRD/WSH INSU | 43844009 | VALLEY SPRINGS-CLAY | 013/180 | ICD | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-120.904357 | 38.2851 | ETL.8264 | 40904785 | Insulator | Contaminated | Ground Wash | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 622 | Victor |  | Y - Prog Multi
116816365 | EI PTTR VLLY-MNDCNO 000/006 RPL STRT |  | POTTER VALLEY-MENDOCINO | 000/006 | 70S | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | North Coast | WSIP | [6 empty] | '-123.131392 | 39.3527 | ETL.7810 | 40826196 | Structure-Tower | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLQ | Pole Program | Capital | 426 | Lakeville |  |  | 2019-04-30
116816552 | T2 DI STNSLS-MANTECA #2 014/082 RPR FOND | 43842120 | STANISLAUS-MANTECA #2 | 015/087 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.595814 | 38.0239 | ETL.3820 | 40803363 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - Prog Multi
116816725 | EI MONTE RIO-FULTON 007/009 RPL SPLW | 43762371 | MONTE RIO-FULTON | :007/009 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | North Coast | WSIP | [6 empty] | '-122.894206 | 38.4897 | ETL.7630 | 40863278 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  | 2019-04-30
116816733 | EI MONTE RIO-FULTON 007/009 RPR GYWW | 43762371 | MONTE RIO-FULTON | :007/009 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | North Coast | WSIP | [6 empty] | '-122.894206 | 38.4897 | ETL.7630 | 40863278 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  | 2019-04-30
116817008 | T2 DI STNSLS-MLS MNTCA 011/070 RPR STRT | 43841828 | STANISLAUS-MELONES SS-MANTECA #1+ | 011/070 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.553433 | 38.0499 | ETL.3830 | 40604155 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - 9
116817152 | T2 DI STNS-MLN MTC #1 011/067 RPNT STRT | 43841835 | STANISLAUS-MELONES SS-MANTECA #1+ | 011/067 | ICS | F | Pre-2020_(9a) Other ignition related | Budget Owner (Paint) |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.541885 | 38.0558 | ETL.3830 | 40803318 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - Prog Multi
116817319 | EI UKIAH-HPLND-CLVRDLE 03/30 INST GUY | 43737337 | UKIAH-HOPLAND-CLOVERDALE | 003/030 | ICW | E | Pre-2020_(9a) Other ignition related |  |  |  |  | LATE | North Coast | WSIP | FSRP | [5 empty] | '-123.15001 | 39.1396 | ETL.4050 | 40772250 | Guy Wire-Wood | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  | 2019-05-10
116817752 | EI CLEAR LAKE-HOPLAND 009/008 RPL PL | 31488229 | CLEAR LAKE-HOPLAND | 009/008 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | North Coast | WSIP | FSRP | [5 empty] | '-122.915678 | 38.9959 | ETL.6390 | 40860816 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  | 2019-04-30
116818178 | DI MELONES-CURTIS 9/3 RPR GYWW CMPLTD | 44623078 | MELONES-CURTIS | 009/003 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-120.403585 | 37.9428 | ETL.2390 | 44391060 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 18
116818396 | DISTRIBUTION RPL INSS |  | SPARE T-LINE RECORD | T-139 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  | Midway-Santa Maria |  | LATE | South | WSIP | FSRP | [5 empty] | '-120.050759 | 35.1133 | ETL.9240 | 43249651 | Hardware-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Pismo Beach |  | Y - 4
116818401 | DI MELONES-CURTIS 9/3 SPLW RPR | 43842664 | MELONES-CURTIS | 009/003 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-120.403585 | 37.9428 | ETL.2390 | 44391060 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 12
116818598 | DISTRIBUTION BENT MEMBER |  | SPARE T-LINE RECORD | T-144 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  | Midway-Santa Maria |  | LATE | South | WSIP | FSRP | [5 empty] | '-120.036975 | 35.1199 | ETL.9240 | 43249807 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Pismo Beach
116819432 | EI FITCH MTN #1 TAP 00/05 REMOVE STRW | 31470929 | FITCH MTN #1 TAP | 000/005 | 93J | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | North Coast | WSIP | [6 empty] | '-122.845713 | 38.6054 | ETL.6891 | 40750532 | Structure-Wood | Idle | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 673 | Lakeville |  |  | 2019-07-19
116819460 | EI FITCH MTN #1 TAP 00/007 RPR GYWW | 43761311 | FITCH MTN #1 TAP | 000/007 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | North Coast | WSIP | [6 empty] | '-122.848043 | 38.6047 | ETL.6891 | 40808480 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  | 2019-07-19
116819621 | T2 EI SLT SPRNGS-TGR CRK 3/31 RPR FOND | 43842263 | SALT SPRINGS-TIGER CREEK | 003/031 | ICQ | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.274897 | 38.4781 | ETL.3500 | 40579794 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - 17
116821597 | EI KONOCTI-MIDDLETOWN 012/008 CANCEL | 43761672 | KONOCTI-MIDDLETOWN | 012/008 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  | CANCEL/CNCL |  | LATE | North Coast | WSIP | FSRP | [5 empty] | '-122.605367 | 38.7579 | ETL.6380 | 40876752 | Anchor-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  | 2019-05-29
116821753 | T2 EI MNTN GATE JCT-CSCDE 2/027 RPL POLE | 31526991 | MTN GATE JCT-CASCADE | 002/027 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.32104 | 40.706 | ETL.7640 | 44565519 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC erdy srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
116822571 | T2 DI VLLY SPRINGS-CLAY 005/081 RPR GYWW | 43844012 | VALLEY SPRINGS-CLAY | 005/081 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.831266 | 38.2045 | ETL.8264 | 40904718 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog Multi
116823557 | T2 EI SALT SPRNGS-TGR CRK 04/36 RPR FOND | 43842263 | SALT SPRINGS-TIGER CREEK | 004/036 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.284185 | 38.477 | ETL.3500 | 40803565 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - 17
116824075 | T2 DI COBURN-PANCH 33/145 RPL SPLS | 43749767 | COBURN-PANOCHE | 033/145 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-121.200649 | 36.6953 | ETL.4460 | 40753411 | Shield Wire / OPGW-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Moss Landing |  | Y - 5
116824112 | T2 DI VLLY SPRNGS-CLY 008/121 REFRAME | 31501104 | VALLEY SPRINGS-CLAY | 008/121 | 93E | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.850908 | 38.2432 | ETL.8264 | 40906852 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Victor |  | Y - 12
116825033 | EI LAYTONVILLE-WILLITS 4/4 RPL STRW | 31434842 | LAYTONVILLE-WILLITS | 004/004 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | North Coast | WSIP | FSRP | [5 empty] | '-123.338624 | 39.4587 | ETL.8360 | 40750488 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville
116825209 | T2 EI SALT SPRINGS-TGR CRK 6/51 REPAINT | 43842276 | SALT SPRINGS-TIGER CREEK | 006/051 | ICS | E | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.314895 | 38.4779 | ETL.3500 | 40579797 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Released
116825220 | T2 EI SALT SPRINGS-TGR CRK 6/51 INST HRD | 43842265 | SALT SPRINGS-TIGER CREEK | 006/051 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.314895 | 38.4779 | ETL.3500 | 40579797 | Hardware-Tower | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - 13
116825231 | T2 EI SALT SPRINGS-TGR CRK 6/51 BENT STL | 43842265 | SALT SPRINGS-TIGER CREEK | 006/051 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.314895 | 38.4779 | ETL.3500 | 40579797 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - 13
116825232 | T2 EI SALT SPRINGS-TGR CRK 6/51 RPR FOND | 43842265 | SALT SPRINGS-TIGER CREEK | 006/051 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.314895 | 38.4779 | ETL.3500 | 40579797 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - 13
116825551 | EI MENDOCINO-UKIAH 39/007 RPR FOND | 43762362 | MENDOCINO-UKIAH | 039/007 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  |  | LATE | North Coast | WSIP | [6 empty] | '-123.18243 | 39.1447 | ETL.2420 | 40810781 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville
116825725 | T2 DI PINE GROVE TAP 1/38 INST HRDD | 43749302 | PINE GROVE TAP | 001/038 | ICW | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.650316 | 38.4067 | ETL.8351 | 40754201 | Hardware-Wood | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 3
116825813 | DISTRIBUTION BIRD GUARD | 31432273 | SPARE T-LINE RECORD | T-147 | 93R | E | Pre-2020_(9a) Other ignition related |  |  | Midway-Santa Maria |  | LATE | South | WSIP | FSRP | [5 empty] | '-120.029612 | 35.1253 | ETL.9240 | 43249723 | Raptor Guard-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 530 | Midway
116826231 | T2 EI HT CRK #1-WSTWD 025/480 RPL SPLW | 43736797 | HAT CREEK #1-WESTWOOD | 025/480 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.211493 | 40.6868 | ETL.7030 | 40592100 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
116826385 | T3 EI MORRO BAY-TEMPLETON 10/41 REPAINT | 43735698 | MORRO BAY-TEMPLETON | 010/041 | ICS | F | Pre-2020_(9a) Other ignition related |  |  |  | TR3 | LATE | South | WSIP | [6 empty] | '-120.74269 | 35.4771 | ETL.5933 | 40593891 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Pismo Beach |  | Y - 14
116826431 | T3 DI MORAGA-OKALAND 1/12 PNT STRS | 43744382 | MORAGA-OAKLAND #1 | 001/012 | ICS | E | Pre-2020_(9a) Other ignition related | Budget Owner (Paint) |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.189143 | 37.8371 | ETL.2720 | 40648544 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  | Y - 9
116826450 | DISTRIBUTION BENT MEMBER |  | SPARE T-LINE RECORD | T-148 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  | Midway-Santa Maria |  | LATE | South | WSIP | FSRP | [5 empty] | '-120.027986 | 35.1266 | ETL.9240 | 43249581 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 543 | Midway
116826880 | T3 EI MORRO BAY-TEMPLETON 9/40 REPAINT | 43735698 | MORRO BAY-TEMPLETON | 009/040 | ICS | E | Pre-2020_(9a) Other ignition related |  |  |  | TR3 | LATE | South | WSIP | [6 empty] | '-120.743958 | 35.4741 | ETL.5933 | 40591874 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Pismo Beach |  | Y - 14
116826892 | T2 DI PINE GROVE TAP 1/42 RPR GYWW | 43749302 | PINE GROVE TAP | 001/042 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.651409 | 38.4082 | ETL.8351 | 40874901 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 3
116826982 | T2 DI PINE GROVE TAP 1/44 RPR GYWW | 43749302 | PINE GROVE TAP | 001/044 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.651468 | 38.4098 | ETL.8351 | 40587997 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 3
116826983 | T2 DI PINE GROVE TAP 1/44 RPR STRW | 43749302 | PINE GROVE TAP | 001/044 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.651468 | 38.4098 | ETL.8351 | 40587997 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 3
116827281 | T3 EI MRRO BY-TMPLTN 09/39 RPNT MEMB | 43735698 | MORRO BAY-TEMPLETON | 009/039 | ICS | E | Pre-2020_(9a) Other ignition related |  |  |  | TR3 | LATE | South | WSIP | [6 empty] | '-120.745533 | 35.4704 | ETL.5933 | 40862971 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Pismo Beach |  | Y - 14
116827888 | DISTRIBUTION MARKER |  | SPARE T-LINE RECORD | T-163 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  | Midway-Santa Maria |  | LATE | South | WSIP | [6 empty] | '-119.993002 | 35.1575 | ETL.9240 | 43249693 | Marker (i.e. signs)-Steel | Missing | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Midway
116827928 | DISTRIBUTION BIRD GUARD |  | SPARE T-LINE RECORD | T-151 | ICB | E | Pre-2020_(4b) On structure in bucket 4 |  |  | Midway-Santa Maria |  | LATE | South | WSIP | FSRP | [5 empty] | '-120.020557 | 35.1329 | ETL.9240 | 43249813 | Raptor Guard-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 593 | Midway
116828058 | DISTRIBUTION INSL |  | SPARE T-LINE RECORD | T-167 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  | Midway-Santa Maria |  | LATE | South | WSIP | FSRP | [5 empty] | '-119.984147 | 35.1655 | ETL.9240 | 43249773 | Insulator-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Pismo Beach |  | Y - 4
116828222 | DISTRIBUTION HARDWARE |  | SPARE T-LINE RECORD | T-162 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  | Midway-Santa Maria |  | LATE | South | WSIP | FSRP | [5 empty] | '-119.994769 | 35.156 | ETL.9240 | 43249695 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Midway
116828257 | DISTRIBUTION BENT MEMBER |  | SPARE T-LINE RECORD | T-164 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  | Midway-Santa Maria |  | LATE | South | WSIP | FSRP | [5 empty] | '-119.990449 | 35.1598 | ETL.9240 | 43249593 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Midway
116829652 | T2 EI ELECT-BELLOTA 00/006 PAINT STRS | 43844907 | ELECTRA-BELLOTA | 000/006 | ICS | E | Pre-2020_(5b) On structure in bucket 5 | Budget Owner (Paint) |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.670029 | 38.3219 | ETL.4670 | 40659003 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - Prog Multi
116833055 | T2 EI SALT SPRNGS-TGR CRK 4/037 RPR FOND | 43842263 | SALT SPRINGS-TIGER CREEK | 004/037 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.286165 | 38.4775 | ETL.3500 | 40803566 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - 17
116833392 | DI VALLEY SPRINGS #1 005/101 RPR GYWW | 43831339 | VALLEY SPRINGS #1 | 005/101 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-120.837009 | 38.1715 | ETL.8210 | 40905516 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 23
116833552 | T3 EI MORRO BAY-TEMPLETON 9/38 REPAINT | 43735698 | MORRO BAY-TEMPLETON | 009/038 | ICS | E | Pre-2020_(9a) Other ignition related |  |  |  | TR3 | LATE | South | WSIP | [6 empty] | '-120.747245 | 35.4665 | ETL.5933 | 40863323 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Pismo Beach |  | Y - 14
116836120 | T2 DI PINE GROVE TAP 001/045 RPR GYWW | 43749302 | PINE GROVE TAP | 001/045 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.651712 | 38.4101 | ETL.8351 | 40697081 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 3
116837954 | T2 EI SALT SPRNGS-TGER CRK 6/53 INS MRKS | 43842276 | SALT SPRINGS-TIGER CREEK | 006/053 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.324482 | 38.4771 | ETL.3500 | 40643018 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - 13
116838418 | EI BELL-PLACER 002/022 RPL INSS | 31434830 | BELL-PLACER | 002/022 | 93K | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-121.068137 | 38.9272 | ETL.4395 | 44139230 | Insulator-Steel | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Sacramento
116839961 | T2 DI PINE GROVE TAP 001/027 RPR GYWW | 43749302 | PINE GROVE TAP | 001/027 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.642614 | 38.4043 | ETL.8351 | 40754253 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 3
116840529 | T3 DI CNTR CSTA-MRG #1 22/104 RPR STRT | 43744389 | CONTRA COSTA-MORAGA #1 | 022/104 | ICS | E | Pre-2020_(9a) Other ignition related | Budget Owner (Paint) |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.08189 | 37.8566 | ETL.5452 | 40804947 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay
116840737 | T2 DI EXCHEQUER-YSMTE 0/003 RPR STRT | 43825050 | EXCHEQUER-YOSEMITE | 000/003 | ICQ | E | Pre-2020_(4) TD tag on high spread line | Project efficiency (capital work) | DLFL; Completed on project 74001200 |  | TR2 | LATE | South | WSIP | [6 empty] | '-120.26811 | 37.5821 | ETL.8650 | 40646331 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - Prog Multi
116841024 | T2 DI VALLEY SPRINGS #1 3/69 RPL SPLW | 43831099 | VALLEY SPRINGS #1 | 003/069 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.819224 | 38.1901 | ETL.8210 | 40903830 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 23
116841025 | T2 DI VALLEY SPRINGS #1 3/69 RPL CRSW | 31431490 | VALLEY SPRINGS #1 | 003/069 | 93E | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.819224 | 38.1901 | ETL.8210 | 40903830 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Victor |  | Y - 23
116841763 | LOS BANOS MIDWAY #2 28/119 RPL INS |  | LOS BANOS-MIDWAY #2 | 028/119 | 93K | E | Pre-2020_(1b) Lines with special commitments | Director approved | DLFL once tag is confirmed complete PM | Email CIRT when complete |  | LATE | South | Non-WSIP | [6 empty] | '-120.7148718 | 36.7372 | ETL.6010 | 40886107 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - Prog Multi
116841775 | LOS BANOS MIDWAY #2 28/121 RPL INS |  | LOS BANOS-MIDWAY #2 | 028/121 | 93K | E | Pre-2020_(1b) Lines with special commitments | Director approved | DLFL once tag is confirmed complete PM | Email CIRT when complete |  | LATE | South | Non-WSIP | [6 empty] | '-120.711745 | 36.7315 | ETL.6010 | 40612781 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 23
116841787 | LOS BANOS MIDWAY #2 29/123 RPL INS |  | LOS BANOS-MIDWAY #2 | 029/123 | 93K | E | Pre-2020_(1b) Lines with special commitments | Director approved | DLFL once tag is confirmed complete PM | Email CIRT when complete |  | LATE | South | Non-WSIP | [6 empty] | '-120.7079111 | 36.7245 | ETL.6010 | 40680825 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - Prog Multi
116841792 | LOS BANOS MIDWAY #2 46/196 RPL INS | 31433912 | LOS BANOS-MIDWAY #2 | 046/196 | 93K | E | Pre-2020_(1b) Lines with special commitments | Director approved | DLFL once tag is confirmed complete PM | Email CIRT when complete |  | LATE | South | Non-WSIP | [6 empty] | '-120.512674 | 36.5232 | ETL.6010 | 40839570 | Insulator-Steel | No Good/Out of Stdrd | Replace | srdy DCNL |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 23
116842078 | T2 EI FULTON-PUEBLO 009/044 RPNT TWR | 43761418 | FULTON-PUEBLO | 009/044 | ICS | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.159755 | 38.5183 | ETL.1600 | 40765287 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville
116846448 | T2 DI BUELL TON TAP 000/001 RPL STRW | 31508010 | BUELLTON TAP | 000/001 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | South | WSIP |  |  |  |  | Estimating | LC rtn'd to CIRT for pole replacement | '-120.184809 | 34.6476 | ETL.1201 | 40588594 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Pismo Beach |  | Y - 2
116846685 | DI EXCHEQUER-YOSEMITE 000/012 PAINT | 43825051 | EXCHEQUER-YOSEMITE | 001/012 | ICS | E | Pre-2020_(9a) Other ignition related | Budget Owner (Paint) |  |  |  | LATE | South | WSIP | [6 empty] | '-120.243402 | 37.5757 | ETL.8650 | 40651165 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Fresno |  | Y - 38
116847018 | T2 DI PINE GROVE TAP 002/053 RPR GYWW | 43749302 | PINE GROVE TAP | 002/053 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.655617 | 38.4132 | ETL.8351 | 40754203 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 3
116847089 | T2 DI WST PNT-VLLY SPRNGS 6/69 RPL POLE | 31519841 | WEST POINT-VALLEY SPRINGS | 006/069 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP |  |  |  | REJECT: Could not complete work due to Scope Change Required. No work to verify. |  |  | '-120.636063 | 38.3842 | ETL.8350 | 40579957 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - Prog Multi
116847304 | T2 DI PINE GROVE TAP 002/053 RPL HRDD | 43749302 | PINE GROVE TAP | 002/049 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.653296 | 38.4121 | ETL.8351 | 40596137 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 3
116847602 | DI IONE TAP 003/009 RPR STRW | 43844198 | IONE TAP | 003/009 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-120.949885 | 38.3745 | ETL.8253 | 40871541 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 9
116847622 | T2 EI DRUM-RIO OSO #2 023/176 RPR CONDS | 43746398 | DRUM-RIO OSO #2 | 023/176 | ICS | E | Pre-2020_(2) High fire spread TD |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Project | 2021 - Drum Rio Oso Project | '-121.1363757 | 39.0899 | ETL.1430 | 40851887 | Conductor-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes
116848127 | T2 DI PINE GROVE TAP 001/046 REPR GYWW | 43749302 | PINE GROVE TAP | 001/046 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.652218 | 38.4106 | ETL.8351 | 40661588 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 3
116848560 | T2 DI STNSLS-MNTC #2 012/075 RPR STRT | 43842120 | STANISLAUS-MANTECA #2 | 012/075 | ICQ | F | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.569779 | 38.0402 | ETL.3820 | 40744463 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - Prog Multi
116848617 | T2 DI STNSLS-MNTC #2 009/054 CANCEL | 43842132 | STANISLAUS-MANTECA #2 | 009/054 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  | CANCEL/CNCL | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.510481 | 38.0713 | ETL.3820 | 40744464 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - Prog Multi
116848925 | T2 DI CHRISTI-WIL PS 3/042 RPL STRW | 31431652 | CHRISTIE-WILLOW PASS | 003/042 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-122.147667 | 38.0208 | ETL.6370 | 40599513 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Bay |  | Y - 3 | 2019-08-05
116849532 | T2 PLACER-DEL MAR 000/007 RPL POLE | 31478099 | PLACER-DEL MAR | 000/007 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-121.089297 | 38.8979 | ETL.7800 | 40583103 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
116850302 | T2 DI STNSLAS-MNTCA #2 9/52 RPR STRT | 43842120 | STANISLAUS-MANTECA #2 | 009/052 | ICQ | F | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.505766 | 38.0738 | ETL.3820 | 40642922 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - 14
116852182 | T3 EI GRIZZLY TAP 3/12 RPR GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 003/012 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-121.322423 | 39.9075 | ETL.2395 | 44551471 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
116852497 | T3NT EI GRIZZLY TAP 3/16 INST GMKW | 43760153 | TAP (CITY OF SANTA CLARA) | 003/016 | ICW | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-121.323328 | 39.9089 | ETL.2395 | 44551420 | Guy Wire Mark /Indic-Wood | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
116852541 | T3 EI GRIZZLY TAP 3/16 RPR GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 003/016 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-121.323328 | 39.9089 | ETL.2395 | 44551420 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
116852661 | T2 DI STNSLS-MNTCA #2 12/74 RPR STRT | 43842120 | STANISLAUS-MANTECA #2 | 012/074 | ICQ | F | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.568207 | 38.0411 | ETL.3820 | 40751359 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - Prog Multi
116852759 | T2 PLACER-DEL MAR 000/018 RPL POLE | 31478099 | PLACER-DEL MAR | 000/018 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-121.095685 | 38.892 | ETL.7800 | 40591283 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
116853486 | T3NT EI GRIZZLY TAP 3/16 INST GMKW | 43760153 | TAP (CITY OF SANTA CLARA) | 003/016 | ICW | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-121.323328 | 39.9089 | ETL.2395 | 44551472 | Guy Wire Mark /Indic-Wood | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
116853487 | T3 EI GRIZZLY TAP 3/16 RPR GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 003/016 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-121.323328 | 39.9089 | ETL.2395 | 44551472 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
116854043 | T2 EI SLT SPRNGS-TGR CRK 2/25 BENT STEEL | 43842263 | SALT SPRINGS-TIGER CREEK | 002/025 | ICQ | F | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.26242 | 38.4856 | ETL.3500 | 40744655 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - 13
116854127 | T2 EI CRESTA-RIO OSO 40/265 RPR INSS |  | CRESTA-RIO OSO | 040/265 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.51486 | 39.412 | ETL.4590 | 40786932 | Insulator-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
116854278 | T2 EI SLT SPRNGS-TGR CRK 02/024 RPNT TWR | 43842275 | SALT SPRINGS-TIGER CREEK | 002/024 | ICS | E | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.261269 | 38.4866 | ETL.3500 | 40744661 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Released
116854449 | T2 DI STNSLAUS-MNTCA #2 20/116 RPR STRT | 43842120 | STANISLAUS-MANTECA #2 | 020/116 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.66317 | 37.9715 | ETL.3820 | 40803372 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - Prog Multi
116854603 | DI BRIONES TAP 2/37 GRD WASH |  | BRIONES TAP | 002/037 | ICD | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-121.752 | 37.9043 | ETL.7055 | 40695869 | Insulator | Contaminated | Ground Wash |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 622 | Bay |  | Y - 7
116855000 | T2 EI VCA-VVL-JMSN-NRTHTWR 8/63 CANCEL | 43740701 | VACA-VACAVILLE-JAMESON-NTH TWR | 008/063 | ICS | F | Pre-2020_(3) On high spread structure | Budget Owner (Paint) |  | CANCEL/CNCL | TR2 | <60D | North Valley | WSIP |  |  |  |  | Program | 2021 Paint took out of program due to future project to be removed with [REDACTED] | '-122.032541 | 38.3394 | ETL.4100 | 40765438 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes
116855641 | T2 EI MTCLF-GRN VLY 07/051 PAINT STRS | 44300701 | METCALF-GREEN VALLEY | 007/051 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | South | WSIP | FSRP | [5 empty] | '-121.679262 | 37.1472 | ETL.2540 | 40585522 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Moss Landing
116856263 | DI VLLY SPRNGS-MRTL #1 003/013 RPR STRW | 43740949 | VALLEY SPRINGS-MARTELL #1 | 003/013 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-120.775375 | 38.2517 | ETL.8240 | 40644751 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Released
116856780 | T2 DI STNSLS-MANTCA #2 009/053 BNT MEM | 43842132 | STANISLAUS-MANTECA #2 | 009/053 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.507839 | 38.0727 | ETL.3820 | 40663252 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Victor |  | Y - Prog Multi
116856926 | T2 EI SALT SPGS-TGR CRK 11/90 PAINT STRS | 43842278 | SALT SPRINGS-TIGER CREEK | 011/090 | ICS | F | Pre-2020_(3) On high spread structure | Budget Owner (Paint) |  |  | TR2 | <60D | Central | WSIP |  |  |  |  | Program | 2021- Paint Program | '-120.406127 | 38.4796 | ETL.3500 | 40579974 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Released
116857329 | T2 DI MELONES-CURTIS 9/2A RMV NEST | 43842416 | MELONES-CURTIS | 009/002A | ICS | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.404871 | 37.9422 | ETL.2390 | 40575680 | Structure-Steel | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - 18
116858371 | T2 DI VLLY SPRNGS-MRTLL #1 8/11 RPR GYWW | 43740949 | VALLEY SPRINGS-MARTELL #1 | 008/011 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.768549 | 38.3124 | ETL.8240 | 40600041 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog Multi
116858631 | EI T2 GARCIA TAP -002/007 RPR GYWW | 43761564 | GARCIA TAP | 002/007 | ICW | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | WSIP | FSRP | [5 empty] | '-123.55612 | 38.8908 | ETL.8411 | 40825504 | Guy Wire-Wood | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  | 2019-07-10
116858641 | T2 DI VLY SPRNG-MRTL #1 005/006 RPR SPLW | 43740949 | VALLEY SPRINGS-MARTELL #1 | 005/006 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.76161 | 38.2685 | ETL.8240 | 40813064 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog Multi
116858642 | T2 DI VLY SPRNG-MRTL #1 005/006 INS MRKW |  | VALLEY SPRINGS-MARTELL #1 | 005/006 | ICW | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.76161 | 38.2685 | ETL.8240 | 40813064 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog Multi
116860956 | T2 DI CNTRA CSTA-LS PSTS 17/108 RPR SHLS | 43753328 | CONTRA COSTA-LAS POSITAS | 017/108 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-121.73308 | 37.7511 | ETL.4510 | 40818780 | Ground Wire-Tower | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 6
116861088 | T2 DI STNSLS-MANTEC 20/119 RPL HRDT | 43842120 | STANISLAUS-MANTECA #2 | 020/119 | ICQ | F | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.667927 | 37.9679 | ETL.3820 | 40860787 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - Prog Multi
116861200 | T2 DI STNSLS-MANTEC 20/119 BNT MEM | 43842120 | STANISLAUS-MANTECA #2 | 020/119 | ICQ | F | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.667927 | 37.9679 | ETL.3820 | 40860787 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - Prog Multi
116861356 | T2 DI CRESTA-RIO OSO 27/220 PAINT | 43708739 | CRESTA-RIO OSO | 027/220 | ICS | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.528106 | 39.5809 | ETL.4590 | 40911510 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
116861506 | T2NT DI VLY SPRGS MRTL#1 9/4 MRKR INST |  | VALLEY SPRINGS-MARTELL #1 | 009/004 | ICW | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.772084 | 38.3195 | ETL.8240 | 40753696 | Marker (i.e. signs)-Wood | Missing | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog Multi
116861685 | T2 EI TEMBLOR-SLO 056/310 RPNT TWR | 43740614 | TEMBLOR-SAN LUIS OBISPO | 056/310 | ICS | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | South | WSIP | FSRP | [5 empty] | '-120.608084 | 35.2686 | ETL.3960 | 40580080 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Pismo Beach
116861893 | DI VLLY SPGS-MRTLL #1 3/013A RPR STRW | 43740949 | VALLEY SPRINGS-MARTELL #1 | 003/013A | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-120.77474 | 38.2524 | ETL.8240 | 44183841 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Released
116862153 | T3 EI GROVE TAP 001/029 RPR GYWW | 43736449 | PINE GROVE TAP | 001/029 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR3 | LATE | Central | WSIP |  |  |  |  | Clearance Delayed | Clearance in September on section not able to take out due to summer loading and West Point Valley Springs shoo fly. | '-120.644002 | 38.4053 | ETL.8351 | 40812438 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 3
116862252 | T2 DI VLY SPRGS MRTL#1 9/4 STRW RPR | 43740949 | VALLEY SPRINGS-MARTELL #1 | 009/004 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.772084 | 38.3195 | ETL.8240 | 40753696 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog Multi
116862379 | T2 DI CRESTA-RIO OSO 28/225 INS DAMS | 43729877 | CRESTA-RIO OSO | 028/225 | ICS | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.530592 | 39.5728 | ETL.4590 | 40911511 | Damper-Steel | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
116862640 | T3 EI TEMBLOR-SLO 054/301 RPNT TWR | 43740614 | TEMBLOR-SAN LUIS OBISPO | 054/301 | ICS | E | Pre-2020_(9a) Other ignition related |  |  |  | TR3 | LATE | South | WSIP | [6 empty] | '-120.58198 | 35.283 | ETL.3960 | 40585669 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Pismo Beach
116863145 | T2 DI BRCEBURG JCT-MRPS 005/013 RPR IBWW | 43825046 | BRICEBURG JCT-MARIPOSA TAP | 005/013 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | South | WSIP | FSRP | [5 empty] | '-119.986205 | 37.5216 | ETL.8651 | 40660791 | Insulator Bond Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Fresno |  | Y - 12
116866950 | T2 DI VLY SPRNGS-MRTL #1 12/6 RPL STRW | 31434031 | VALLEY SPRINGS-MARTELL #1 | 012/006 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.793235 | 38.3636 | ETL.8240 | 40805072 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - Prog Multi
116867200 | T2 DI VLY SPRNG-MRTL #1 012/004 RPL STRW | 31434031 | VALLEY SPRINGS-MARTELL #1 | 012/004 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.792255 | 38.3626 | ETL.8240 | 40755069 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - Prog Multi
116867228 | T2 DI DUNLAP TAP 7/4 RPR GWSS | 43709735 | DUNLAP TAP | 007/004 | ICS | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-119.158766 | 36.6458 | ETL.9061 | 40763449 | Auto Guy Wire Splice-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  | Y - 9
116867330 | T2 DI VLLY SPRGS-MRT #1 10/010 RPR STRW | 43740949 | VALLEY SPRINGS-MARTELL #1 | 010/010 | ICW | E | 2020_(1a) PSPS |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.781872 | 38.3412 | ETL.8240 | 40599122 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 24
116868486 | T2 DI CHRISTIE-SOBRNTE 012/069 RPR JMPS | 44621446 | CHRISTIE-SOBRANTE | 012/069 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.195397 | 37.9695 | ETL.1260 | 40871959 | Jumper-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - Prog Land
116870394 | T2 EI KONOCTI-MIDDLETOWN 23/011 RPR GYWW | 43761672 | KONOCTI-MIDDLETOWN | 023/011 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.614309 | 38.9027 | ETL.6380 | 40586668 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  | 2019-05-29
116870752 | DI STNSLS-MNTC #2 027/163 PNT TWR | 43842132 | STANISLAUS-MANTECA #2 | 027/163 | ICS | E | Pre-2020_(3) On high spread structure | Budget Owner (Paint) |  |  |  | LATE | Central | WSIP |  |  |  |  | Program | 2021 Paint took out of program due to future project to be removed with [REDACTED] | '-120.778921 | 37.9203 | ETL.3820 | 40642820 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - Prog Multi
116871007 | PLACER-DEL MAR 1/042 RPL POLE | 31502069 | PLACER-DEL MAR | 001/042 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | North Valley | Non-WSIP | [6 empty] | '-121.111263 | 38.8821 | ETL.7800 | 40660920 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
116871562 | T3 EI DRUM-RIO OSO #1 000/001 PNT STRT | 43746398 | DRUM-RIO OSO #1 | 000/001 | ICS | F | Pre-2020_(3) On high spread structure | Budget Owner (Paint) |  |  | TR3 | LATE | North Valley | WSIP |  |  |  |  | Program | 2021 Paint took out of program due to future project to be removed with [REDACTED] | '-120.769665 | 39.2571 | ETL.1420 | 40594929 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes
116873540 | T2 DI VLY SPNGS-MRTL #1 12/3 RPL STRW | 31434031 | VALLEY SPRINGS-MARTELL #1 | 012/003 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.791702 | 38.3621 | ETL.8240 | 40666222 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - Prog Multi
116873586 | T2 DI VLY SPNGS-MRTL #1 12/1 RPL STRW | 31434031 | VALLEY SPRINGS-MARTELL #1 | 012/001 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-120.790336 | 38.3608 | ETL.8240 | 40600035 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - Prog Multi
116876142 | T3 EI DRUM-HIGGINS 009/092L RPL STRW | 31432822 | DRUM-HIGGINS | 009/092 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.892639 | 39.1723 | ETL.4393 | 44172126 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
116876143 | T3 EI DRUM-HIGGINS 009/092C RPL STRW | 31432822 | DRUM-HIGGINS | 009/092 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.892639 | 39.1723 | ETL.4393 | 44172127 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
116876728 | LAYTONVILLE-COVELO 13/04 REPL NG POLE | 31451876 | LAYTONVILLE-COVELO | 013/004 | 70Y | B | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) |  |  |  |  | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-123.266864 | 39.7573 | ETL.7390 | 40750461 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  | 2019-06-19
116878160 | T2 Mendocino/Redbud_030/145 RPLC INSS | 31478190 | MENDOCINO-REDBUD | 030/145 | 93K | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-122.735888 | 39.0466 | ETL.2410 | 40791768 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Lakeville |  |  | 2019-07-19
116878861 | T2 EI SLT SPRNGS-TGR CRK 04/044 INS MRKS | 43842276 | SALT SPRINGS-TIGER CREEK | 004/044 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.303406 | 38.4779 | ETL.3500 | 40744666 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Victor |  | Y - 13
116880142 | T2 DI CHRISTIE-FRNKLIN #2 0/12 REPL POLE | 31499910 | CHRISTIE-FRANKLIN #2 | 000/012 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.225912 | 38.0041 | ETL.6360 | 40581068 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Bay |  | Y - 2
116880732 | EI PALERMO-WYANDOTTE 001/015 RPR STRS | 43754992 | PALERMO-WYANDOTTE | 001/015 | ICS | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-121.539609 | 39.4733 | ETL.4315 | 40757544 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain
116882290 | EI DRUM-RIO OSO #1 33/236 PAINT STRS | 43746398 | DRUM-RIO OSO #1 | 033/236 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-121.291893 | 39.0266 | ETL.1420 | 40817486 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes
116883769 | T2 DI MRG-SN LNDR 008/057 BENT STEEL | 44294404 | MORAGA-SAN LEANDRO #1 | 008/057 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.117419 | 37.7394 | ETL.2770 | 40804655 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 7
116883826 | DISTRIBUTION JUMPER |  | SPARE T-LINE RECORD | T-165 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  | Midway-Santa Maria |  | LATE | South | WSIP | FSRP | [5 empty] | '-119.989252 | 35.1609 | ETL.9240 | 43249631 | Conductor-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Midway
116884682 | T2 DI MORAGA-OAKLAND #1 3/27 RMV SOIL | 43752132 | MORAGA-OAKLAND #1 | 003/027 | ICS | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-122.210798 | 37.816 | ETL.2720 | 40804633 | Structure-Steel | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - 7
116884688 | T2 DI CLEAR LAKE-HOPLAND 1/0 CANCEL | 43734956 | CLEAR LAKE-HOPLAND | 001/000 | ICD | E | Pre-2020_(4) TD tag on high spread line |  |  | CANCEL/CNCL | TR2 | LATE | North Coast | WSIP | FSRP | [5 empty] | '-123.064436 | 38.9695 | ETL.6390 | 40587013 | Insulator | Contaminated | Ground Wash | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 622 | Lakeville |  |  | 2019-07-19
116885043 | T2 DI PITTSBURG-EASTSHORE 5/22 RPR FOND | 44238518 | PITTSBURG-EASTSHORE | 005/022 | ICQ | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-121.90117 | 37.9749 | ETL.5462 | 40680966 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog Multi
116885142 | T2 DI PITTSBURG-SN MTO 006/029 INS HRDT |  | PITTSBURG-SAN MATEO | 006/029 | ICQ | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-121.893848 | 37.9515 | ETL.5463 | 40761887 | Hardware-Tower | Missing | Install |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 10
116885233 | T2 DI PTTSBRG-SN MTEO 008/034 INS HRDT |  | PITTSBURG-SAN MATEO | 008/034 | ICQ | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-121.888931 | 37.9278 | ETL.5463 | 40862985 | Hardware-Tower | Missing | Install |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 10
116899610 | T2 TW DI PTTSBG-TSL #1 021/093 RPR FOND | 43753186 | PITTSBURG-TESLA #1 | 021/093 | ICQ | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-121.667467 | 37.8298 | ETL.5510 | 40658971 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 5
116899611 | T2 DI PITTSBUG-EASTSHORE 21/082 RPR JUMS | 43753182 | PITTSBURG-EASTSHORE | 021/082 | ICS | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-121.927405 | 37.7487 | ETL.5462 | 41135612 | Jumper-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - Prog Multi
116899615 | T2 DI VACA PARKWAY 017/089 RPL SHLS | 43760157 | VACA-PARKWAY | 017/089 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.138005 | 38.2604 | ETL.5850 | 40603687 | Shield Wire / OPGW-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes
116899721 | T2 DI CLR LAKE-HOPLAND 0/15 RPL POLE | 31501678 | CLEAR LAKE-HOPLAND | 000/015 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | FSRP | [5 empty] | '-123.066037 | 38.9697 | ETL.6390 | 40750112 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  | 2019-07-19
116903296 | T2 HAT CREEK #1-WESTWD 13/251 REFRAME | 31471576 | HAT CREEK #1-WESTWOOD | 013/251 | 93I | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-121.366886 | 40.8165 | ETL.7030 | 40735035 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Table Mountain |  |  | Yes
116905339 | T2 DELTA-MTN GATE JCT 13/171 REPL INSS | 31454737 | DELTA-MOUNTAIN GATE JCT | 013/171 | 93K | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-122.310277 | 40.7722 | ETL.6750 | 41115165 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  | Yes
116920659 | DISTRIBUTION RPL POLE | 31383233 | SPARE T-LINE RECORD | T018 | 70Y | F | Pre-2020_(2) High fire spread TD |  |  | Midway-Santa Maria |  | <60D | South | Non-WSIP | [6 empty] | '-120.335532 | 34.9327 | ETL.9240 | 43250119 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Pismo Beach
116922941 | T2 DI NEWARK-VLECITOS 95/620 BNT MEM | 43753293 | NEWARK-VALLECITOS | 095/620 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-121.894258 | 37.5681 | ETL.7670 | 40613250 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 7
116927011 | T3 EI PARADISE-TABLE MTN 16/134 RPR GYWW | 43724325 | PARADISE-TABLE MTN | 016/134 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-121.499399 | 39.6792 | ETL.4316 | 44552318 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
116927013 | T3 EI PARADISE-TABLE MTN 16/134 RPR GYWW | 43724325 | PARADISE-TABLE MTN | 016/134 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.499399 | 39.6792 | ETL.4316 | 44552501 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
116937011 | T2 MENDOCINO-WLTS-FT BRG 23/7 RMV VEG |  | MENDOCINO-WILLITS-FORT BRAGG | 023/007 | HNA | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | WSIP | FSRP | [7 empty] | ETL.7550 | 44211135 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Lakeville
116937655 | EI CTTNWD-DLEVN #1 30/207A RPLC DAMS | 43726632 | COTTONWOOD-DELEVAN #1 | 030/207A | ICS | E | Pre-2020_(9a) Other ignition related |  |  |  |  | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.266328 | 39.9558 | ETL.4550 | 40577001 | Damper-Steel | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
116939014 | T2 DI CRZY HRS CYN SL SL#1 :13/70 STRT | 43775531 | CRZY HORSE CYN-SALNS-SOLDAD#1 | :013/070 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-121.432541 | 36.5952 | ETL.2900 | 40591359 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Moss Landing |  | Y - 8 | 2019-07-15
116939245 | DI LAS POSITAS NEWARK 13/89 STRS PAINT | 43753291 | LAS POSITAS-NEWARK | 013/089 | ICS | F | Pre-2020_(9a) Other ignition related | Budget Owner (Paint) |  |  |  | LATE | Central | WSIP | FSRP | [5 empty] | '-121.889356 | 37.5504 | ETL.4980 | 40862566 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay
116939362 | T2 EI CRESTA-RIO OSO 29/235 PAINT STRS | 43729877 | CRESTA-RIO OSO | 029/235 | ICS | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.535578 | 39.5565 | ETL.4590 | 41083096 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
116939533 | T2 EI STNSLS-MNTCA #2 014/084 RPR STRT | 43842120 | STANISLAUS-MANTECA #2 | 014/084 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.592282 | 38.0263 | ETL.3820 | 40764248 | Hardware-Tower | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - Prog Multi
116939545 | T3 DI SLT SPRGS-TGR CRK 15/118 PNT STRT | 43842402 | SALT SPRINGS-TIGER CREEK | 015/118 | ICS | E | Pre-2020_(9a) Other ignition related | Budget Owner (Paint) |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-120.477709 | 38.4532 | ETL.3500 | 40856680 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Released
116950347 | T2 EI MALIN-ROUND MTN #2 50/251 RPR SHLS | 43621093 | MALIN-ROUND MTN #2 | 050/251 | ICQ | E | Pre-2020_(1b) Lines with special commitments |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.559088 | 41.3234 | ETL.6020 | 40587309 | Shield Wire / OPGW-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
116952426 | T2 EI CBRN-LS AGLS SW ST 41/177 RPL CONN | 43749765 | COBURN-PANOCHE | 041/177 | ICM | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-121.069279 | 36.6644 | ETL.4460 | 40809321 | Connector | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 534 | Moss Landing |  | Y - 5
116953844 | EI GREEN VALLY-LLAGS :12/076 PAINT STRS | 43766025 | GREEN VALLEY-LLAGAS | :012/076 | ICS | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  |  | LATE | South | WSIP | [6 empty] | '-121.644717 | 37.0923 | ETL.1720 | 40819873 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Moss Landing |  | Y - 10
116954236 | T2 DI CAYUCOS-CAMBRIA 16/119 RPR GYWW | 43753055 | CAYUCOS-CAMBRIA | 016/119 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | South | WSIP |  |  |  | REJECT |  |  | '-121.087542 | 35.5891 | ETL.8560 | 40819707 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - 1
116957168 | POE-RIO OSO 032/216 RPR JUMS | 43875009 | POE-RIO OSO | 032/216 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | North Valley | Non-WSIP | [6 empty] | '-121.536668 | 39.524 | ETL.5540 | 40843579 | Jumper-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
116958507 | T2 DI CASTRO VLY-NWK 10/54 RPR STRT PNT | 43751913 | CASTRO VALLEY-NEWARK | 010/054 | ICS | E | Pre-2020_(3) On high spread structure | Budget Owner (Paint) |  |  | TR2 | LATE | Central | WSIP |  |  |  |  | Program | 2021- Paint Program | '-121.9237 | 37.5914 | ETL.4450 | 40819387 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  |  | SFWL
116958605 | T2 DI COLGATE-PALERMO 011/226 RPL STRW | 31472009 | COLGATE-PALERMO | 011/226 | 70Y | E | 2020_(1a) PSPS |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.378773 | 39.3783 | ETL.6500 | 40874601 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
116959302 | T2 DI WISHON COPPERMINE 0/1 RPL ANCS | 31433444 | WISHON-COPPERMINE | 000/001 | 93E | E | Pre-2020_(4) TD tag on high spread line | Superintendent Approved work efficiency |  | Likely MAT error - delink to correct | TR2 | LATE | South | WSIP | FSRP | [5 empty] | '-119.505707 | 37.147 | ETL.9330 | 40591637 | Anchor-Steel | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLQ | Tower | Capital |  | Fresno |  | Y - Prog Multi
116959303 | T2 DI WISHON COPPERMINE 0/1 RPL GYWS | 43711388 | WISHON-COPPERMINE | 000/001 | ICS | E | Pre-2020_(4) TD tag on high spread line | Superintendent Approved work efficiency |  |  | TR2 | LATE | South | WSIP | FSRP | [5 empty] | '-119.505707 | 37.147 | ETL.9330 | 40591637 | Guy Wire-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Fresno |  | Y - Prog Multi
116960675 | DI CLR LK HOPELAND 0/13 CANCEL | 43734956 | CLEAR LAKE-HOPLAND | 000/013 | ICD | E | Pre-2020_(4) TD tag on high spread line |  |  | CANCEL/CNCL |  | LATE | North Coast | WSIP | FSRP | [5 empty] | '-123.0691 | 38.9701 | ETL.6390 | 40667038 | Insulator | Contaminated | Ground Wash | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 622 | Lakeville
116960679 | T2 EI CRESTA-RIO OSO 008/072A RPL CONN | 43844645 | CRESTA-RIO OSO | 008/072A | ICM | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.421964 | 39.8293 | ETL.4590 | 41162726 | Connector | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 534 | Table Mountain |  |  | Yes
116960915 | T3 EI DRUM-RIO OSO #1 08/88 PAINT STRS | 43746398 | DRUM-RIO OSO #1 | 008/088 | ICS | E | Pre-2020_(9a) Other ignition related |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.889062 | 39.1876 | ETL.1420 | 40873409 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes
116967225 | T2 DI WISHON-COPPERMNE 007/050 REPR FOND | 43711311 | WISHON-COPPERMINE | 007/050 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | South | WSIP | FSRP | [5 empty] | '-119.540751 | 37.0606 | ETL.9330 | 40606324 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 12
116967637 | T2 EI OLEUM-G #1 001/013 RPL HRDT | 43752139 | OLEUM-G #1 | 001/013 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.234061 | 38.0334 | ETL.3150 | 40644329 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 8
116968968 | T2 DI STS-MLNS SS MTCA #1 4/29 RPR FOND | 43841828 | STANISLAUS-MELONES SS-MANTECA #1+ | 004/029 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.443839 | 38.1079 | ETL.3830 | 40856453 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - 9
116970741 | T2 DI MERCED FALLS-EXQR 3/4 STRT RPR | 44300846 | MERCED FALLS-EXCHEQUER | 003/004 | ICQ | E | Pre-2020_(4) TD tag on high spread line | Superintendent Approved work efficiency |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-120.319222 | 37.5726 | ETL.8990 | 40748141 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - Prog Multi
116970995 | T2 DI EAGLE RCK-CRTINA :15/001 REPL INSW | 31498400 | EAGLE ROCK-CORTINA | :015/001 | 93I | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.608649 | 38.9383 | ETL.1470 | 40629350 | Insulator-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Lakeville |  |  | 2019-08-06
116971051 | T2 DI WISHON-COPPERMINE 9/71 RPR FOND | 43711311 | WISHON-COPPERMINE | 009/071 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | South | WSIP | FSRP | [5 empty] | '-119.566407 | 37.0243 | ETL.9330 | 40595600 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - Prog Multi
116971811 | T2 DI HELMS-GREGG #1 022/150 REMOVE NEST | 43825460 | HELMS-GREGG #1 | 022/150 | ICS | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | South | WSIP | FSRP | [5 empty] | '-119.33215 | 36.947 | ETL.4870 | 40602723 | Structure-Steel | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  | Y - 13
116971812 | T2 DI STNSLS-MNS-MNTCA#1 24/149 RPR STRT | 43841828 | STANISLAUS-MELONES SS-MANTECA #1+ | 024/149 | ICQ | F | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.719805 | 37.938 | ETL.3830 | 40820374 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - 9
116972003 | T2 DI VLLY SPRG-MRTL #1 010/004 RPR SPLW | 43740949 | VALLEY SPRINGS-MARTELL #1 | 010/004 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.778439 | 38.3358 | ETL.8240 | 40758491 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog Multi
116972119 | DI STNSLS-MLNS-MNTCA #2 26/152 RPR SPLS | 43842132 | STANISLAUS-MANTECA #2 | 026/152 | ICS | E | Pre-2020_(4) TD tag on high spread line |  | TLN/TLQ error |  |  | LATE | Central | WSIP | [6 empty] | '-120.748745 | 37.9293 | ETL.3820 | 40642939 | Splice-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - Prog Multi
116976706 | T2 DI WISHON-COPPERMINE 11/85 RPR FOND | 44571732 | WISHON-COPPERMINE | 011/085 | ICQ | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | South | WSIP | FSRP | [5 empty] | '-119.586578 | 36.9968 | ETL.9330 | 40765443 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - Prog Multi
116977523 | T2 DI STNLS-MLNS SS-MNTCA 2/17 PNT STRT | 43841832 | STANISLAUS-MELONES SS-MANTECA #1+ | 002/017 | ICS | F | Pre-2020_(9a) Other ignition related | Budget Owner (Paint) |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.414321 | 38.1241 | ETL.3830 | 40803312 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - Prog Multi
116978773 | T2 VOLTA-DESCHUTES 20/445 REFRAME | 31475775 | VOLTA-DESCHUTES | 020/445 | 93E | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-122.227783 | 40.5521 | ETL.8290 | 40676458 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  | Yes
116979755 | T2 DI IONE TAP 001/005 REPL CRSW | 31434028 | IONE TAP | 001/005 | 93E | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.925042 | 38.3598 | ETL.8253 | 40745286 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Victor |  | Y - Prog Multi
116981376 | T2 DI STSL-MNS SS-MTCA #1 10/61 CANCEL | 43841828 | STANISLAUS-MELONES SS-MANTECA #1+ | 010/061 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  | CANCEL/CNCL | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.524244 | 38.0639 | ETL.3830 | 40594248 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - Prog Multi
116982050 | T2 DI STSL-MNS SS-MTCA #1 07/45 PNT STRS | 43841835 | STANISLAUS-MELONES SS-MANTECA #1+ | 007/045 | ICS | F | Pre-2020_(9a) Other ignition related | Budget Owner (Paint) |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.485992 | 38.0846 | ETL.3830 | 40745910 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - Prog Multi
116982052 | T2 DI STSL-MNS SS-MTCA #1 07/44 RPR STRT | 43841828 | STANISLAUS-MELONES SS-MANTECA #1+ | 007/044 | ICQ | F | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.483591 | 38.0859 | ETL.3830 | 40744429 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - Prog Multi
116982474 | T2 DI EAGLE ROCK-REDBUD :18/001 RPR GYWW | 43760959 | EAGLE ROCK-REDBUD | :018/001 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.612467 | 38.9824 | ETL.1480 | 40602600 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  | 2019-06-05
116983334 | T2 DI EAGLE ROCK-REDBUD :18/000 RPR GYWW | 43760959 | EAGLE ROCK-REDBUD | :018/000 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.612459 | 38.9816 | ETL.1480 | 40618884 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  | 2019-06-05
116984351 | T2 DI STN-MLN SW ST-MNT#1 11/69 RPR STRS | 43841835 | STANISLAUS-MELONES SS-MANTECA #1+ | 011/069 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.549164 | 38.0521 | ETL.3830 | 40871563 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Victor |  | Y - 16
116984398 | T2 VOLTA-DESCHUTES 019/427 RPL POLE | 35163206 | VOLTA-DESCHUTES | 019/427 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-122.214873 | 40.5493 | ETL.8290 | 40615948 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
116984689 | T3 EI BRUNSWICK #2 TAP 000/007 RPL INSS | 31453336 | BRUNSWICK #2 TAP | 000/007 | 93K | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.013336 | 39.1521 | ETL.1431 | 40834391 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Sacramento |  |  | Yes
116985048 | T3 DI CARIBOU-PALERMO :008/063 REPR FOND | 44051418 | CARIBOU-PALERMO | :008/063 | ICQ | E | Pre-2020_(3) On high spread structure |  |  |  | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.238849 | 40.0064 | ETL.3190 | 40910305 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
116985801 | T2 DI EXCHEQUER-YSMITE 01/07 PNT/CT STRS | 43709741 | EXCHEQUER-YOSEMITE | 001/007 | ICS | E | Pre-2020_(9a) Other ignition related | Budget Owner (Paint) |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-120.258318 | 37.5758 | ETL.8650 | 40806452 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  | Y - 42
116986060 | T2 DI STN-MLN SW -MNT#1 18/114 PNT STRT | 43841835 | STANISLAUS-MELONES SS-MANTECA #1+ | 018/114 | ICS | E | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.642037 | 37.9873 | ETL.3830 | 40744436 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - Prog Multi
116986189 | T2 DI CLEAR LAKE-HOPLND 9/2 RPR GYWS | 43734957 | CLEAR LAKE-HOPLAND | 009/002 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | FSRP | [5 empty] | '-122.923367 | 38.9937 | ETL.6390 | 44639194 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville
116986500 | T2 DI EAGLE ROCK-CORTINA :15/14 RPR GYWW | 43761301 | EAGLE ROCK-CORTINA | :015/014 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.607779 | 38.9472 | ETL.1470 | 41176339 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  | 2019-08-06
116986504 | T2 DI EAGLE ROCK-CORTINA :15/14 RPL INSW | 31469921 | EAGLE ROCK-CORTINA | :015/014 | 93I | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.607779 | 38.9472 | ETL.1470 | 40779607 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Lakeville |  |  | 2019-08-06
116986869 | T2 DI IGNACIO-SN RFAEL #1 7/38 PNT STRS | 43761667 | IGNACIO-SAN RAFAEL #1 | 007/038 | ICS | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.494925 | 37.9868 | ETL.1850 | 40858036 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville
116988973 | T2 DI EAGLE ROCK-CORTINA :15/08 DUP CNCL | 31461430 | EAGLE ROCK-CORTINA | :015/008 | 93E | E | Pre-2020_(4b) On structure in bucket 4 |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.608154 | 38.9434 | ETL.1470 | 41176333 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 630 | Lakeville |  |  | 2019-08-06
116991107 | T2 DI STN-MLN SW STA-MNT#1 6/38 PNT STRS | 43841832 | STANISLAUS-MELONES SS-MANTECA #1+ | 006/038 | ICS | E | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.469087 | 38.0939 | ETL.3830 | 40856452 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Victor |  | Y - Prog Multi
116991476 | T2 DI HELMS-GREGG #1 22/148 RMV NEST | 43825460 | HELMS-GREGG #1 | 022/148 | ICS | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | South | WSIP | FSRP | [5 empty] | '-119.32174 | 36.9503 | ETL.4870 | 40858331 | Structure-Steel | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Fresno |  | Y - 13
117000185 | HEINZ TAP - 115 KV 000/014 | 43846573 | HEINZ TAP IDLE | 000/014 | ICW | E | Pre-2020_(1b) Lines with special commitments |  |  |  |  | LATE | Central | Non-WSIP | [6 empty] | '-121.412231 | 37.7449 | ETL.2193 | 40758883 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog Multi
117000638 | HEINZ TAP 000/006 INST MRKW | 43846573 | HEINZ TAP IDLE | 000/006 | ICW | F | Pre-2020_(1b) Lines with special commitments |  |  |  |  | LATE | Central | Non-WSIP | FSRP | [5 empty] | '-121.415472 | 37.7479 | ETL.2193 | 40828533 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Released
117000670 | HEINZ TAP 000/006 RMV IDLE SWITCH | 43853810 | HEINZ TAP IDLE | 000/006 | ICW | F | Pre-2020_(1b) Lines with special commitments |  |  |  |  | LATE | Central | Non-WSIP | FSRP | [5 empty] | '-121.415472 | 37.7479 | ETL.2193 | 40828533 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Released
117001123 | T2 DI STNS-MELN SW MANT 3/24 PNT STRT | 43841832 | STANISLAUS-MELONES SS-MANTECA #1+ | 003/024 | ICS | E | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.432942 | 38.1139 | ETL.3830 | 40756401 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - Prog Multi
117005727 | T2 DI IGNACIO-ALTO 016/157 RPL STRW | 31492618 | IGNACIO-ALTO | 016/157 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.51668 | 37.9168 | ETL.7150 | 40770115 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville
117006596 | T2 DI EAGLE ROCK-REDBD :15/11 RPL HRDD | 43760959 | EAGLE ROCK-REDBUD | :015/011 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.607986 | 38.9446 | ETL.1480 | 40585046 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  | 2019-06-05
117006648 | T2 DI EAGLE ROCK-REDBD :15/11 RPL SWIW | 31472116 | EAGLE ROCK-REDBUD | :015/011 | 93H | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.607986 | 38.9446 | ETL.1480 | 40585046 | Switch-Wood | No Good/Out of Stdrd | Replace | erdy ADER | ADER | With ADE for Review | Not Complete | PEND | LC | TLN | Maintenance | Capital | 427 | Lakeville |  |  | 2019-06-05
117006683 | DI LAS POSITAS-NEWRK 015/097 RPNT STRS | 43753291 | LAS POSITAS-NEWARK | 015/097 | ICS | E | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) |  |  |  | LATE | Central | WSIP | [6 empty] | '-121.902364 | 37.5355 | ETL.4980 | 40819290 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  | Y - Prog Multi
117007683 | T2 DI STNSLS-MANTECA #2 015/094 RPR FOND | 44460414 | STANISLAUS-MANTECA #2 | 015/094 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.611092 | 38.0105 | ETL.3820 | 40744468 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - Prog Multi
117007708 | T2 DI STNSLS-MNTCA #2 15/94 PAINT | 43842132 | STANISLAUS-MANTECA #2 | 015/094 | ICS | E | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.611092 | 38.0105 | ETL.3820 | 40744468 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - 14
117008010 | T2 DI VLLY SPRNG-MRTL #1 12/7 RPL STRW | 31434031 | VALLEY SPRINGS-MARTELL #1 | 012/007 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.793805 | 38.3643 | ETL.8240 | 40805044 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - Prog Multi
117008204 | T2 DI SALINAS-LAURELES 08/186 RMV VEGN |  | SALINAS-LAURELES | 008/186 | HNA | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | South | WSIP | [5 empty] | Per Cal Trans District 5, unless the trees are dead, the removal of the trees as a scenic resource will require Coastal Development Permit or some other kind of locally driven approval that complies with CEQA. | '-121.707892 | 36.5908 | ETL.7930 | 40666632 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Moss Landing
117008414 | T2 DI COLGATE-PALERMO 017/340 RPL STRW | 31495724 | COLGATE-PALERMO | 017/340 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.434258 | 39.4356 | ETL.6500 | 40766440 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
117008583 | T2 DI STANISLS-MANTECA #2 15/94 RPR STRT | 43842120 | STANISLAUS-MANTECA #2 | 015/094 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.611092 | 38.0105 | ETL.3820 | 40744468 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - 14
117009591 | T2 DI EAGLE ROCK-REDBUD :15/04 REMV ROW1 |  | EAGLE ROCK-REDBUD | :015/004 | CHR | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.608031 | 38.9403 | ETL.1480 | 40750731 | Right of Way | Encroachment | Remove |  |  |  |  | PEND | LC | TLS | Land | Expense | 931 | Lakeville
117009756 | T2 EI DRUM-HIGGINS 013/125 RPR GYWS | 43852138 | DRUM-HIGGINS | 013/125 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.954779 | 39.1613 | ETL.4393 | 44172096 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes
117013071 | T2 DI CLGTE-SMRTVILE #2 002/026 RPL SPLW | 43851744 | COLGATE-SMARTVILLE #2 | 002/026 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.223185 | 39.3183 | ETL.6520 | 40594294 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117013092 | T3 DI PARADISE-BUTTE 001/015 RPR GRWS | 43758389 | PARADISE-BUTTE | 001/015 | ICS | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.62906 | 39.7507 | ETL.4396 | 41127211 | Ground Wire-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117014198 | T2 DI JFFERSON-STNFORD 001/032 RPR GYWW | 43752127 | JEFFERSON-STANFORD (NO FLY) | 001/032 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.263139 | 37.4614 | ETL.7220 | 40612107 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Bay |  | Y - 6
117014201 | DI JEFFERSON-STANFORD 002/064 RPL STRW | 31434138 | JEFFERSON-STANFORD (NO FLY) | 002/064 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-122.248261 | 37.4641 | ETL.7220 | 40874147 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Bay |  | Y - 6
117014673 | T2 DI STNS-MNS SS MTCA #1 14/84 INS HRDT | 43841828 | STANISLAUS-MELONES SS-MANTECA #1+ | 014/084 | ICQ | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.587666 | 38.0293 | ETL.3830 | 40744435 | Hardware-Tower | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - Prog Multi
117015686 | T2 DI EAGLE ROCK-CORTINA :14/7 GYWW RPR | 43761301 | EAGLE ROCK-CORTINA | :014/007 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.608519 | 38.9279 | ETL.1470 | 41176310 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  | 2019-08-06
117016775 | T3 EI DRUM-HIGGINS 3/32R REPLACE POLE | 31453426 | DRUM-HIGGINS | 003/032 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.799724 | 39.2229 | ETL.4393 | 44172143 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
117017109 | T2 DI JEFFERSON-STANFORD 1/25 RPR STRW | 43752127 | JEFFERSON-STANFORD (NO FLY) | 001/025 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.268239 | 37.462 | ETL.7220 | 40653218 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Bay |  | Y - 6
117017484 | T2 DI JEFFERSON-STANFORD 1/30 RPR GYWW | 43752127 | JEFFERSON-STANFORD (NO FLY) | 001/030 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.264748 | 37.4617 | ETL.7220 | 40875244 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Bay |  | Y - 6
117017489 | T2 DI JEFFERSON-STANFORD 1/23 RPR GYWW | 43752127 | JEFFERSON-STANFORD (NO FLY) | 001/023 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.269243 | 37.4614 | ETL.7220 | 40599123 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Bay |  | Y - 6
117017751 | T2 DI JEFFERSON-STANFORD 1/39 RPR GYWW | 43752127 | JEFFERSON-STANFORD (NO FLY) | 001/039 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.259769 | 37.4623 | ETL.7220 | 40812607 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Bay |  | Y - 6
117018286 | T2 DI COLGATE-PALERMO 012/245 RPL POLE | 31505737 | COLGATE-PALERMO | 012/245 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.394683 | 39.3815 | ETL.6500 | 40814365 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Need New ERTC
117018623 | T2 DI JEFFERSON-STANFORD 2/61 RPR GYWW | 43752127 | JEFFERSON-STANFORD (NO FLY) | 002/061 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.250489 | 37.4639 | ETL.7220 | 40813364 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Bay |  | Y - 6
117018673 | T2 DI COLGATE-PALERMO 13/255 RPR GYWW | 43728969 | COLGATE-PALERMO | 013/255 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.400932 | 39.3857 | ETL.6500 | 40766446 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117018860 | DI LAYTONVILLE-WILLITS 4/2 WASH INSU | 43761785 | LAYTONVILLE-WILLITS | 004/002 | ICD | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | North Coast | WSIP | FSRP | [5 empty] | '-123.336224 | 39.4567 | ETL.8360 | 40733598 | Insulator | Contaminated | Ground Wash | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 622 | Lakeville
117019218 | T2 DI BRCBRG JCT MRPOSA 4/18 RPR STRW | 43825046 | BRICEBURG JCT-MARIPOSA TAP | 004/018 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | South | WSIP | FSRP | [5 empty] | '-119.985987 | 37.532 | ETL.8651 | 40872665 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Fresno |  | Y - 12
117020075 | T2 DI COLGATE-PALERMO 13/257 RPR GYWW | 43728969 | COLGATE-PALERMO | 013/257 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.40212 | 39.3868 | ETL.6500 | 40822478 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117020854 | T2 DI BRCBG JCT-MRPSA TAP 4/18 INST MRKW |  | BRICEBURG JCT-MARIPOSA TAP | 004/018 | ICW | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-119.985987 | 37.532 | ETL.8651 | 40872665 | Marker (i.e. signs)-Wood | Missing | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Fresno |  | Y - 12
117023346 | T2 EI VACA-SUISUN-JAMS 12/085 RPL INSS | 31457373 | VACA-SUISUN-JAMESON | 012/085 | 93K | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.063155 | 38.2897 | ETL.4080 | 40773369 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Sacramento |  |  | Yes
117023770 | T2 RINCON #2 00/02 REPL FLSH INSUL | 31447732 | RINCON #2 TAP | 000/002 | 93K | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-122.667734 | 38.4939 | ETL.1611 | 40710645 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Lakeville |  |  | 2019-07-19
117023813 | T2 DI JEFFERSON-STANDFORD 1/43 RPR GYWW | 43752127 | JEFFERSON-STANFORD (NO FLY) | 001/043 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.259104 | 37.4636 | ETL.7220 | 40599124 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Bay |  | Y - Prog Multi | 2019-07-31
117023877 | T2 DI JEFFERSON-STNFRD 2/46 RPR GYWW | 43744381 | JEFFERSON-STANFORD (NO FLY) | 002/046 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.257373 | 37.4645 | ETL.7220 | 40588808 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Bay |  | Y - 6
117023956 | T2 DI JEFFERSON-STAND 2/063 RPR GYWW | 43744381 | JEFFERSON-STANFORD (NO FLY) | 002/063 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-122.248805 | 37.4636 | ETL.7220 | 40865046 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Bay |  | Y - 6
117024006 | T2 DI JEFFERSON-STANDFORD 2/60 RPL GYWW | 43752127 | JEFFERSON-STANFORD (NO FLY) | 002/060 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.251591 | 37.4641 | ETL.7220 | 40767166 | Guy Wire-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Bay |  | Y - 6
117024017 | T2 DI JEFFERSON-STANDFORD 2/45 RPR GYWW | 43752127 | JEFFERSON-STANFORD (NO FLY) | 002/045 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.257687 | 37.4642 | ETL.7220 | 40612133 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Bay |  | Y - Prog Multi | 2019-07-31
117024149 | T2 DI JEFFERSON-STANFORD 1/28 RPR GYWW | 43744381 | JEFFERSON-STANFORD (NO FLY) | 001/028 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.266038 | 37.4618 | ETL.7220 | 40824885 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Bay |  | Y - 6
117024366 | T2 DI STSLS-MNS SS-MTC #1 9/60 REPAINT | 43841835 | STANISLAUS-MELONES SS-MANTECA #1+ | 009/060 | ICS | F | Pre-2020_(9a) Other ignition related | Budget Owner (Paint) |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.522057 | 38.0651 | ETL.3830 | 40581586 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - Prog Multi
117025363 | T3 EI MDDL FRK-GLD HLL 008/072 RPNT STRT | 44302263 | MIDDLE FORK-GOLD HILL | 008/072 | ICS | F | Pre-2020_(9a) Other ignition related |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.729152 | 38.9963 | ETL.5140 | 40681075 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento
117028282 | T2 EI BCKS CRK-RCK CRK-CRST :001/013 RPL | 43897313 | BUCKS CREEK-ROCK CREEK-CRESTA | :001/013 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.362328 | 39.895 | ETL.4430 | 40656150 | Splice-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117028283 | T2 EI BCKS CRK-RCK CRK-CRST :001/013 INS | 43897313 | BUCKS CREEK-ROCK CREEK-CRESTA | :001/013 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.362328 | 39.895 | ETL.4430 | 40656150 | Marker (i.e. signs)-Steel | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117030161 | T2 DI EXCHQUER-YOSEMITE 021/078 PNT STRS | 44300705 | EXCHEQUER-YOSEMITE | 021/078 | ICS | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-120.009093 | 37.5832 | ETL.8650 | 40859318 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Fresno |  | Y - 42
117030406 | T2 DI STNSLS-MANTECA #2 24/141 PNT STRS | 43842132 | STANISLAUS-MANTECA #2 | 024/141 | ICS | F | Pre-2020_(9a) Other ignition related | Budget Owner (Paint) |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.719798 | 37.9379 | ETL.3820 | 40584588 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - Prog Multi
117031770 | T2 DI EAGLE RCK-CRTNA :18/000 RPR HRDD | 43761301 | EAGLE ROCK-CORTINA | :018/000 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.613115 | 38.981 | ETL.1470 | 41176383 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  | 2019-08-06
117033850 | DI CLEAR LAKE-HOPLAND 001/010 REPL STRW | 31483756 | CLEAR LAKE-HOPLAND | 001/010 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | North Coast | WSIP | FSRP | [5 empty] | '-123.052193 | 38.9667 | ETL.6390 | 40587016 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  | 2019-07-19
117034416 | T2 DI JFFERSON-STNFORD 001/040 RPR GYWW | 43752127 | JEFFERSON-STANFORD (NO FLY) | 001/040 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.260037 | 37.4626 | ETL.7220 | 40875242 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Bay |  | Y - 6
117034472 | T2 EI TABLE MTN-RIO OSO 15/071 RPL INSS | 31453343 | TABLE MTN-RIO OSO | 015/071 | 93K | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.502326 | 39.4406 | ETL.5700 | 40616517 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  | Yes
117034784 | T2 DI JEFFERSON-STANFORD 01/35 REPR GYWW | 43752127 | JEFFERSON-STANFORD (NO FLY) | 001/035 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.261461 | 37.4621 | ETL.7220 | 40653216 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Bay |  | Y - 6
117034968 | T2 EI CHOWCHILLA-KERCKHOFF 0/4 RPR FOND | 43795032 | CHOWCHILLA-KERCKHOFF | 000/004 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | South | WSIP | FSRP | [5 empty] | '-119.559507 | 37.0915 | ETL.1250 | 40748514 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 17 | BLM
117035238 | T3 DI CNTRVLLE-TBLE MTN 02/35 RPL STRW | 31495727 | CENTERVILLE-TABLE MTN | 002/035 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.677948 | 39.7628 | ETL.6320 | 40598384 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
117035485 | T2 DI JEFFERSON-STANFORD 2/50 REPR GYWW | 43752127 | JEFFERSON-STANFORD (NO FLY) | 002/050 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.255614 | 37.4656 | ETL.7220 | 40767168 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Bay |  | Y - Prog Multi | 2019-07-31
117035489 | T2 DI JEFFERSON-STANFORD 2/50 INST GMKW |  | JEFFERSON-STANFORD (NO FLY) | 002/050 | ICW | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.255614 | 37.4656 | ETL.7220 | 40767168 | Guy Wire Mark /Indic-Wood | Missing | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Bay |  | Y - 6
117035538 | T2 DI KONOCTI-MIDDLETOWN 17/01 RPL STRW | 31490901 | KONOCTI-MIDDLETOWN | 017/001 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.573671 | 38.812 | ETL.6380 | 40600743 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  | 2019-05-29
117035609 | T2 DI SPAULDING-SUMMIT 004/149 INS MRKW | 43947948 | SPAULDING-SUMMIT | 004/149 | ICW | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.576488 | 39.3073 | ETL.8060 | 40586084 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117036603 | T2 EI LKVLL-IGNC #1 IG002/012 RPNT STRS | 43761676 | LAKEVILLE-IGNACIO #1 | IG002/012 | ICS | F | Pre-2020_(9a) Other ignition related |  |  |  |  | LATE | North Coast | WSIP | FSRP | [5 empty] | '-122.522296 | 38.1032 | ETL.4940 | 40679207 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville |  |  | 2019-08-26
117038746 | T2 DI CLEAR LAKE-HOPLAND 01/03 REPL STRW | 31434604 | CLEAR LAKE-HOPLAND | 001/003 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | FSRP | [5 empty] | '-123.059435 | 38.9693 | ETL.6390 | 40667033 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville
117039552 | T2 DI CRYSTAL SPRINGS TAP 0/03 RPR GYWW | 43751917 | CRYSTAL SPRINGS TAP (NO FLY) | 000/003 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.361887 | 37.5325 | ETL.7211 | 40653176 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Bay |  |  | CalTrans, SFPUC
117043755 | T2 DI TULACAY-VACA 017/084 RPL INSS | 31453344 | TULACAY-VACA | 017/084 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.167899 | 38.2774 | ETL.5800 | 40789159 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Sacramento |  |  | Yes
117044116 | T2 DI CPPRMN-TIVY VLLY 22/09 RPR GYWW | 43746875 | COPPERMINE-TIVY VALLEY | 022/009 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | South | WSIP | [8 empty] | ETL.8590 | 44307721 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Fresno |  | Y - 5
117044556 | T2 DI STSLS-NLNS S-MT#1 024/153 BNT MMBR | 43841828 | STANISLAUS-MELONES SS-MANTECA #1+ | 024/153 | ICQ | F | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.730233 | 37.9349 | ETL.3830 | 40585652 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - Prog Multi
117044558 | T2 DI STNLS-NLNS S-MNT#1 24/151 RPR STRT | 43841828 | STANISLAUS-MELONES SS-MANTECA #1+ | 024/151 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.724688 | 37.9366 | ETL.3830 | 40856465 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - Prog Multi
117044600 | DI STNLS-MLNS SS-MNT#1 28/175 PAINT STRS | 43841835 | STANISLAUS-MELONES SS-MANTECA #1+ | 028/175 | ICS | E | Pre-2020_(3) On high spread structure | Budget Owner (Paint) |  |  |  | LATE | Central | WSIP |  |  |  |  | Program | 2021 Paint took out of program due to future project to be removed with [REDACTED] | '-120.78929 | 37.9173 | ETL.3830 | 40654076 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - 9
117044794 | T2 DI CNTRVL TM ORVIL 5/105 SPLW RPL | 43903760 | CENTERVILLE-TABLE MTN-OROVILLE | 005/105 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.645877 | 39.7187 | ETL.6330 | 40692711 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117044922 | T2NT DI TBLE MTN-PLRM 010/045 INST MRKS | 43760152 | TABLE MTN-PALERMO | 010/045 | ICS | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.502379 | 39.517 | ETL.5690 | 40756130 | Marker (i.e. signs)-Steel | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117047443 | T2 DI COLGATE-PALERMO 09/185 INST MRKW | 43910644 | COLGATE-PALERMO | 009/185 | ICW | F | 2020_(1a) PSPS |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.350666 | 39.3602 | ETL.6500 | 40873587 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117047597 | GOLD HILL-BELLOTA-LCKFRD 43/262 REPL INS | 31457033 | GOLD HILL-BELLOTA-LOCKEFORD | 043/262 | 93K | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  |  | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-121.142969 | 38.5429 | ETL.1690 | 44596104 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Sacramento
117048028 | T2 DI CRYSTL SPRNGS TAP 000/002 RPL POLE | 31507608 | CRYSTAL SPRINGS TAP (NO FLY) | 000/002 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.361106 | 37.533 | ETL.7211 | 40667847 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Bay |  | Y - Prog Multi
117048368 | T2 DI TULACAY-VACA 017/083 RPL INSS | 31453344 | TULACAY-VACA | 017/083 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.165047 | 38.2789 | ETL.5800 | 44639228 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Sacramento |  |  | Yes
117049106 | T3 DI GRIZZLY TAP 002/001L REPR GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 002/001 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.302584 | 39.8958 | ETL.2395 | 44550829 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117049107 | T3 DI GRIZZLY TAP 002/001C REPR GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 002/001 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.302584 | 39.8958 | ETL.2395 | 44550813 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117049108 | T3 DI GRIZZLY TAP 002/001R REPR GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 002/001 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.302584 | 39.8958 | ETL.2395 | 44550741 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117049400 | T3 DI GRIZZLY TAP 002/007 REPR GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 002/007 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-121.312669 | 39.8973 | ETL.2395 | 44550815 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117049402 | T3 DI GRIZZLY TAP 002/007 REPR GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 002/007 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-121.312669 | 39.8973 | ETL.2395 | 44550837 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117049404 | T3 DI GRIZZLY TAP 002/007 REPR GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 002/007 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-121.312669 | 39.8973 | ETL.2395 | 44550835 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117050486 | T3 DI GRIZZLY TAP 002/009 REPR GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 002/009 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-121.316036 | 39.8978 | ETL.2395 | 44550784 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117050539 | T2 EI CHOWCHILLA-KERCKHOFF 0/2 RPR FOND | 43795032 | CHOWCHILLA-KERCKHOFF | 000/002 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | South | WSIP | FSRP | [5 empty] | '-119.556809 | 37.0916 | ETL.1250 | 40652116 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 17 | BLM
117050553 | T3 DI GRIZZLY TAP 002/009 REPR GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 002/009 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-121.316036 | 39.8978 | ETL.2395 | 44550836 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117050574 | T3 DI GRIZZLY TAP 002/009 REPR GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 002/009 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-121.316036 | 39.8978 | ETL.2395 | 44550816 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117050576 | T3 DI GRIZZLY TAP 002/010 REPR GYWW |  | TAP (CITY OF SANTA CLARA) | 002/010 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.317667 | 39.8978 | ETL.2395 | 44550769 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117050577 | T3 DI GRIZZLY TAP 002/010 REPR GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 002/010 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.317667 | 39.8978 | ETL.2395 | 44550744 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117050579 | T3 DI GRIZZLY TAP 002/010 REPR GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 002/010 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.317667 | 39.8978 | ETL.2395 | 44550770 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117050904 | T2 DI JEFFERSON-STANFORD 02/49 REPR GYWW | 43752127 | JEFFERSON-STANFORD (NO FLY) | 002/049 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.256033 | 37.4656 | ETL.7220 | 40755288 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Bay |  | Y - Prog Multi | 2019-07-31
117050907 | T2 DI JEFFERSON-STANFORD 2/49 INS HRDW | 43752127 | JEFFERSON-STANFORD (NO FLY) | 002/049 | ICW | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.256033 | 37.4656 | ETL.7220 | 40755288 | Hardware-Wood | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Bay |  | Y - Prog Multi | 2019-07-31
117050908 | T2 DI JEFFERSON-STANFORD 2/49 REPL INSW | 31435407 | JEFFERSON-STANFORD (NO FLY) | 002/049 | 93I | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.256033 | 37.4656 | ETL.7220 | 40755288 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Bay |  | Y - 6
117052163 | T2 DI VLY SPRNGS-MRTL#1 010/014 REFRAME | 31488020 | VALLEY SPRINGS-MARTELL #1 | 010/014 | 93E | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.783152 | 38.3432 | ETL.8240 | 40768889 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Victor |  | Y - 24
117052200 | T2 DI VEDDER TAP 8/93 RPR GYWW | 43860163 | VEDDER TAP | 008/093 | ICW | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | South | WSIP | FSRP | [5 empty] | '-118.960257 | 35.5598 | ETL.2141 | 40669197 | Guy Wire-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Midway
117052915 | T3 DI GRIZZLY TAP 002/005 REPR GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 002/005 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.309307 | 39.8969 | ETL.2395 | 44550834 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117052930 | T3 DI GRIZZLY TAP 002/005 REPR GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 002/005 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.309307 | 39.8969 | ETL.2395 | 44550751 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117052940 | T3 DI GRIZZLY TAP 002/005 REPR GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 002/005 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.309307 | 39.8969 | ETL.2395 | 44550792 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117053049 | T3 DI GRIZZLY TAP 002/008 REPR GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 002/008 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.314116 | 39.8975 | ETL.2395 | 44550743 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117053240 | T3 DI GRIZZLY TAP 002/008 REPR GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 002/008 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.314116 | 39.8975 | ETL.2395 | 44550783 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117054182 | EI LAKEVILLE-IGNACIO#1 IG002/013 REPAINT | 43761676 | LAKEVILLE-IGNACIO #1 | IG002/013 | ICS | E | Pre-2020_(9a) Other ignition related |  |  |  |  | LATE | North Coast | WSIP | [6 empty] | '-122.521914 | 38.101 | ETL.4940 | 40663153 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville |  |  | 2019-08-26
117054477 | DI CNTRVL-TBLMTN-ORVL 010/200 RPR CRSW | 43903760 | CENTERVILLE-TABLE MTN-OROVILLE | 010/200 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.633663 | 39.6467 | ETL.6330 | 40767069 | Crossarm-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117055166 | T2 DI JEFFERSON-STANFORD 2/53 RPR GYWW | 43752127 | JEFFERSON-STANFORD (NO FLY) | 002/053 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.254149 | 37.4651 | ETL.7220 | 40875257 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Bay |  | Y - Prog Multi | 2019-07-31
117055786 | T2 DI SPAULDING-SUMMIT 013/435 RPR GYWW | 43876247 | SPAULDING-SUMMIT | 013/435 | ICW | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.426063 | 39.327 | ETL.8060 | 40771515 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117055936 | T3 EI CLGTE ALLGHNY 21/591 RMV VEG | 43881184 | COLGATE-ALLEGHANY | 021/591 | ICW | E | Pre-2020_(9a) Other ignition related |  |  | Likely veg | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.876021 | 39.4713 | ETL.6470 | 40760454 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117057262 | T2 DI CRTNA-MENDCNO #1 47/229 INST MRKS |  | CORTINA-MENDOCINO #1 | 047/229 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.958405 | 39.1934 | ETL.1330 | 40870093 | Marker (i.e. signs)-Steel | Missing | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville |  |  | 2019-07-29
117060352 | EI CRESTA-RIO OSO 42/279 REPL INSS | 31435732 | CRESTA-RIO OSO | 042/279 | 93K | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-121.5087 | 39.3776 | ETL.4590 | 40889564 | Insulator-Steel | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  | Yes
117062729 | DI STANISLS-NEWARK #1 092/611 RPR STRT |  | STANISLAUS-NEWARK #1 (12KV) | 092/611 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-121.872223 | 37.5855 | ETL.3850 | 40602897 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 7 | SFPUC
117063042 | T2 EI DRUM-RIO OSO #2 20/158 RPL INSS | 31453342 | DRUM-RIO OSO #2 | 020/158 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.083934 | 39.1107 | ETL.1430 | 40890248 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Sacramento |  |  | CalTrans
117063389 | T3 EI EGL-RCK CORTINA 20/095 RPL INSS | 31437310 | EAGLE ROCK-CORTINA | 020/095 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Coast | WSIP | [8 empty] | ETL.1470 | 40795319 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Lakeville |  |  | 2019-09-13
117063475 | T3 EI EAGLE ROCK-CORTINA 14/68 RPL INSS | 31437310 | EAGLE ROCK-CORTINA | 014/068 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.62768 | 38.9028 | ETL.1470 | 40884478 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Lakeville |  |  | 2019-08-06
117063963 | T3 DI EAGLE ROCK-CORTINA :6/039 RPR SPLS | 43762411 | EAGLE ROCK-CORTINA | :006/039 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-120.268619 | 34.7995 | ETL.1470 | 40878317 | Splice-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville |  |  | 2019-05-20
117064150 | T2 DI DRUM-SUMMIT #1 21/250 RPL POLE | 31453474 | DRUM-SUMMIT #1 | 021/250 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.428095 | 39.3169 | ETL.1440 | 40663004 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
117066097 | T2 DI STS-MNS SS-RB JT SS 11/65 PNT STRS | 43841480 | STAN MEL SW STA-RVERBNK JCT SW STA | 011/065 | ICS | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.537881 | 38.0574 | ETL.3840 | 41196636 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - Prog Multi
117066287 | T2 EI VACA-SUISUN JAM 3/031 RPL INSS | 31457373 | VACA-SUISUN-JAMESON | 003/031 | 93K | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.990026 | 38.4012 | ETL.4080 | 40614338 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Sacramento |  |  | Yes
117066420 | T2 EI VACA-SUISUN JAM 04/032 RPL INSS | 31457373 | VACA-SUISUN-JAMESON | 004/032 | 93K | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.99012 | 38.3991 | ETL.4080 | 40717502 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Sacramento |  |  | Yes
117066658 | T2 DI SPAULDING-SUMMIT 015/484 RPLC STRW | 31518243 | SPAULDING-SUMMIT | 015/484 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.388553 | 39.3287 | ETL.8060 | 40828181 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
117069255 | T2 EI BALCH-SANGER 009/054 RPR FOND | 43867621 | BALCH-SANGER | 009/054 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-119.216836 | 36.8724 | ETL.1050 | 40760187 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 17
117075091 | DI LAKEVLLE-IGNCIO #1 IG01/005 INST MRKS | 43761676 | LAKEVILLE-IGNACIO #1 | IG001/005 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  |  | LATE | North Coast | WSIP | [6 empty] | '-122.511705 | 38.1196 | ETL.4940 | 40760307 | Marker (i.e. signs)-Steel | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville |  |  | 2019-07-29
117075167 | T2 POE-RIO OSO 029/192 RPL INSS | 31434829 | POE-RIO OSO | 029/192 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-121.531131 | 39.5723 | ETL.5540 | 40719817 | Insulator-Steel | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  | Yes
117075240 | T2 POE-RIO OSO 029/197 RPL INSS | 31434829 | POE-RIO OSO | 029/197 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-121.534783 | 39.5606 | ETL.5540 | 40840546 | Insulator-Steel | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  | Yes
117077277 | T2 DI SPAULDING-SUMMIT 015/482 RPL INSW | 31463883 | SPAULDING-SUMMIT | 015/482 | 93I | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.390021 | 39.329 | ETL.8060 | 40771519 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Sacramento |  |  | Yes
117077333 | T2 DI SPAULDING-SUMMIT 015/482 REPR GYWW | 43876251 | SPAULDING-SUMMIT | 015/482 | ICW | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.390021 | 39.329 | ETL.8060 | 40771519 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117077534 | T2 POE-RIO OSO 28/186 REPL INSS | 31434829 | POE-RIO OSO | 028/186 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-121.526797 | 39.5865 | ETL.5540 | 40843568 | Insulator-Steel | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  | Yes
117078005 | T2 DI VOLTA-SOUTH 002/069 RPR STRW | 44309960 | VOLTA-SOUTH | 002/069 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.871647 | 40.4198 | ETL.8300 | 40601122 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117079525 | T2 DI COLGATE-PALERMO 11/217 REPL POLE | 31417717 | COLGATE-PALERMO | 011/217 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-121.372696 | 39.3733 | ETL.6500 | 40873585 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
117079659 | T2 DI SPAULDING-SUMMIT 011/396 RPLC STRW | 31453471 | SPAULDING-SUMMIT | 011/396 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.448904 | 39.3176 | ETL.8060 | 40862168 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
117079841 | T2 DI COLGATE-PALERMO 22/442 RPR GYWW | 43728969 | COLGATE-PALERMO | 022/442 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.51824 | 39.458 | ETL.6500 | 43690666 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117081788 | T2 DI KONOCTI-MDLTWN 13/6 RPR GYWW | 43761672 | KONOCTI-MIDDLETOWN | 013/006 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.587482 | 38.7682 | ETL.6380 | 40810812 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  | 2019-05-29
117082112 | T2 DI COLGATE-PLRMO 012/231 RPL STRW | 31495724 | COLGATE-PALERMO | 012/231 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.382606 | 39.379 | ETL.6500 | 40664499 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
117082467 | DI CLEAR LAKE-HOPLAND 001/009 RPL STRW | 31483756 | CLEAR LAKE-HOPLAND | 001/009 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | North Coast | WSIP | FSRP | [5 empty] | '-123.053571 | 38.9666 | ETL.6390 | 40875508 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  | 2019-07-19
117086544 | DI VINEYARD-NEWARK 38/223A INSTALL MRKS |  | VINEYARD-NEWARK | 038/223A | ICS | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-121.895761 | 37.5431 | ETL.4536 | 41196096 | Marker (i.e. signs)-Steel | No Good/Out of Stdrd | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - Prog Multi
117086668 | T2 POE-RIO OSO 26/172 RPL INSS | 31434829 | POE-RIO OSO | 026/172 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-121.518546 | 39.6154 | ETL.5540 | 40723994 | Insulator-Steel | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  | Yes
117086981 | T2 DI TABLE MTN-PLRMO 13/59 MRKS INST | 43760152 | TABLE MTN-PALERMO | 013/059 | ICS | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.502682 | 39.4763 | ETL.5690 | 40865401 | Marker (i.e. signs)-Steel | No Good/Out of Stdrd | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117087209 | T2 DI KONOCTI-MIDDLETOWN 16/14 RPR INSW | 43761672 | KONOCTI-MIDDLETOWN | 016/014 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | FSRP | [5 empty] | '-122.573231 | 38.8085 | ETL.6380 | 40781665 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  | 2019-05-29
117087379 | T2 DI TULACAY-VACA 5/28 REPL INSS | 31453344 | TULACAY-VACA | 005/028 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.147796 | 38.2878 | ETL.5800 | 40892776 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Sacramento |  |  | Yes
117088303 | T2 DI VOLTA-SOUTH 001/033 RPR GYWW | 43827513 | VOLTA-SOUTH | 001/033 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.872792 | 40.4408 | ETL.8300 | 40875798 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117088318 | T3 DI GRIZZLY TAP 001/008C RPR GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 001/008 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-121.292472 | 39.8972 | ETL.2395 | 44550738 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117088319 | T3 DI GRIZZLY TAP 001/008R RPR GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 001/008 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-121.292472 | 39.8972 | ETL.2395 | 44550788 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117088590 | T3 DI GRIZZLY TAP 001/008L RPR GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 001/008 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-121.292472 | 39.8972 | ETL.2395 | 44550789 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117088592 | T3 DI GRIZZLY TAP 001/007 REPR GYWW | 31475737 | TAP (CITY OF SANTA CLARA) | 001/007 | 93E | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.292148 | 39.898 | ETL.2395 | 44550724 | Guy Pole-Wood | No Good/Out of Stdrd | Replace | ESTS erdy | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain
117088594 | T3 DI GRIZZLY TAP 001/007 REPR GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 001/007 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.292148 | 39.898 | ETL.2395 | 44550786 | Guy Stub-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117088595 | T3 DI GRIZZLY TAP 001/007 REPR GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 001/007 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.292148 | 39.898 | ETL.2395 | 44550787 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117088781 | T3 DI GRIZZLY TAP 001/011 RPR GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 001/011 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.295465 | 39.8954 | ETL.2395 | 44550727 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117088784 | T3 DI GRIZZLY TAP 001/011 RPR GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 001/011 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.295465 | 39.8954 | ETL.2395 | 44550762 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117088785 | T3 DI GRIZZLY TAP 001/011 RPR GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 001/011 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.295465 | 39.8954 | ETL.2395 | 44550806 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117089684 | T3 DI GRIZZLY TAP 001/009 RPR GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 001/009 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.293436 | 39.8962 | ETL.2395 | 44550725 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117089685 | T3 DI GRIZZLY TAP 001/009 RPR GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 001/009 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.293436 | 39.8962 | ETL.2395 | 44550726 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117089686 | T3 DI GRIZZLY TAP 001/009 RPR GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 001/009 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.293436 | 39.8962 | ETL.2395 | 44550748 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117089688 | T3NT DI GRIZZLY TAP 001/009 INST MRKW |  | TAP (CITY OF SANTA CLARA) | 001/009 | ICW | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.293436 | 39.8962 | ETL.2395 | 44550725 | Marker (i.e. signs)-Wood | Missing | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117089916 | T3 DI GRIZZLY TAP 3/007 RPR GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 003/007 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.321358 | 39.9031 | ETL.2395 | 44551437 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117090100 | T3 DI GRIZZLY TAP 001/006 RPR GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 001/006 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.290928 | 39.8991 | ETL.2395 | 44550759 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117090101 | T3 DI GRIZZLY TAP 001/006 RPR GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 001/006 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.290928 | 39.8991 | ETL.2395 | 44550776 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117090103 | T3 DI GRIZZLY TAP 001/006 RPR GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 001/006 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.290928 | 39.8991 | ETL.2395 | 44550821 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117090105 | T3 DI GRIZZLY TAP 001/006 RPR SPLW | 43760153 | TAP (CITY OF SANTA CLARA) | 001/006 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.290928 | 39.8991 | ETL.2395 | 44550759 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117090106 | T3 DI GRIZZLY TAP 001/005 RPR GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 001/005 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-121.289561 | 39.8998 | ETL.2395 | 44550757 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117090108 | T3 DI GRIZZLY TAP 001/005 RPR GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 001/005 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-121.289561 | 39.8998 | ETL.2395 | 44550758 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117090320 | T3 DI GRIZZLY TAP 001/005 RPR GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 001/005 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-121.289561 | 39.8998 | ETL.2395 | 44550805 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117092105 | T2 DI JEFFERSON-STANFORD 0/11 RPR INSW | 43877613 | JEFFERSON-STANFORD (NO FLY) | 000/011 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.276791 | 37.4619 | ETL.7220 | 40625778 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Bay |  | Y - 6
117092109 | T2NT DI VC-LKVLL #1 020/095 INS MRKS | 43740456 | VACA-LAKEVILLE #1 | 020/095 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.215082 | 38.2546 | ETL.5840 | 40762416 | Marker (i.e. signs)-Steel | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes
117092710 | DI DRUM-SUMMIT#2 025/305R INS MRKW | 43889098 | DRUM-SUMMIT #2 | 025/305 | ICW | E | Pre-2020_(1b) Lines with special commitments |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-120.366028 | 39.3102 | ETL.1450 | 44558975 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117092713 | T2NT DI DRUM-SUMMIT#2 025/307 INS MRKW | 43889098 | DRUM-SUMMIT #2 | 025/307 | ICW | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.36187 | 39.3099 | ETL.1450 | 40869623 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117093180 | T2NT DI DRUM SUMMIT#2 025/301L INS MRKS | 43888819 | DRUM-SUMMIT #2 | 025/301 | ICS | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.37153 | 39.3113 | ETL.1450 | 44553704 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes
117093189 | T2NT DI DRUM-SUMMIT#2 025/301R INS MRKS | 43888819 | DRUM-SUMMIT #2 | 025/301 | ICS | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.37153 | 39.3113 | ETL.1450 | 44553703 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes
117093668 | T2 DI COLGATE-PALERMO 13/254 GYWW CNCL | 43728969 | COLGATE-PALERMO | 013/254 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  | CANCEL/CNCL | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.400295 | 39.3854 | ETL.6500 | 40757199 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117094215 | T2 DI VACA-LAKEVIL #1 021/098 INSTL MRKS | 43740456 | VACA-LAKEVILLE #1 | 021/098 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.228798 | 38.2523 | ETL.5840 | 40867192 | Marker (i.e. signs)-Steel | No Good/Out of Stdrd | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes
117094240 | T2 DI SPAULDING-SUMMIT 13/450 RPLC STRW | 31522645 | SPAULDING-SUMMIT | 013/450 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.414309 | 39.3282 | ETL.8060 | 40826204 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
117095556 | T3 DI GRIZZLY TAP 001/014 RPR GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 001/014 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.299459 | 39.8956 | ETL.2395 | 44550827 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117095594 | T2 DI JEFFERSON-STANFORD 0/6 RPL STRW | 31434138 | JEFFERSON-STANFORD (NO FLY) | 000/006 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.279413 | 37.4604 | ETL.7220 | 40824854 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Bay |  | Y - 6 | EPNP
117096867 | T2 DI SPAULDING-SUMMIT 010/360 RPR GYWW | 43876247 | SPAULDING-SUMMIT | 010/360 | ICW | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.466578 | 39.319 | ETL.8060 | 40650055 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117096948 | T2 DI SPAULDING-SUMMIT 010/360 INST GMKW | 43876247 | SPAULDING-SUMMIT | 010/360 | ICW | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.466578 | 39.319 | ETL.8060 | 40650055 | Guy Wire Mark /Indic-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117097094 | T2 EI BRENTWOOD-KELSO 007/037 RPL INSS | 31452001 | BRENTWOOD-KELSO | 007/037 | 93K | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-121.693537 | 37.8617 | ETL.4410 | 44815096 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - 4
117097231 | T2 PORT COSTA BRICK TAP 000/006B access |  | PORT COSTA BRICK TAP | 000/006B | CHS | F | Pre-2020_(5b) On structure in bucket 5 | Budget Owner (Veg/Land/Road) |  |  | TR2 | <90D | Central | Non-WSIP | [6 empty] | '-122.171306 | 38.0279 | ETL.6371 | 40742009 | Road | Brush Fuel | Remove |  |  |  |  | PEND | LC | TLR | Roads | Expense | 932 | Bay
117098808 | T2 DI DRUM-RIO OSO 020/161 REPAINT | 44304427 | DRUM-RIO OSO #1 | 020/161 | ICS | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.093121 | 39.1071 | ETL.1420 | 40594933 | Structure-Steel | Paint/Coating | Other | CONS crdy | CONS | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes
117099258 | T2 EI CHC-SL-SD #2 :21/110 RPR INSS | 43766021 | MOSS LANDING-SALINAS-SOLEDAD #2 | :021/110 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-121.351488 | 36.5058 | ETL.2910 | 40624139 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Moss Landing |  | Y - 8 | 2019-07-15
117099911 | T2 PARADISE-TABLE MTN 23/181 REPL ANCS | 31456796 | PARADISE-TABLE MTN | 023/181 | 93E | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-121.626914 | 39.6982 | ETL.4316 | 40758646 | Anchor-Wood | No Good/Out of Stdrd | Replace | ESTS erdy | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  | Yes
117099940 | T2 EI COBURN-PANOCHE 44/191 RPL CONN | 43765619 | COBURN-PANOCHE | 044/191 | ICM | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-121.006405 | 36.6508 | ETL.4460 | 40585737 | Connector | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 534 | Moss Landing |  | Y - 5
117100050 | T2 DI CORTINA-MDCN 46/227 INSTL MRKS | 43761282 | CORTINA-MENDOCINO #1 | 046/227 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.954389 | 39.1898 | ETL.1330 | 40808534 | Marker (i.e. signs)-Steel | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville |  |  | 2019-07-19
117101218 | T2 DI JEFFERSON-STANFORD 0/9 GYWW RPR | 43877613 | JEFFERSON-STANFORD (NO FLY) | 000/009 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.277851 | 37.4615 | ETL.7220 | 40874138 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Bay |  | Y - 6
117101239 | T2 DI VOLTA-SOUTH 001/047 RPL STRW | 31470529 | VOLTA-SOUTH | 001/047 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.871742 | 40.432 | ETL.8300 | 40677148 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain
117101306 | T2 EI BK CRK-RK CRK-CRT 00/04A RPNT STRT | 43897313 | BUCKS CREEK-ROCK CREEK-CRESTA | 000/004A | ICS | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.351399 | 39.9066 | ETL.4430 | 40655542 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117101423 | T3 EI GRIZZLY TAP 003/006 RPR GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 003/006 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.321281 | 39.9023 | ETL.2395 | 44551400 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117101428 | T3 EI GRIZZLY TAP 003/006 RPR GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 003/006 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.321281 | 39.9023 | ETL.2395 | 44551467 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117101430 | T3 DI GRIZZLY TAP 001/015 RPR GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 001/015 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.300829 | 39.8957 | ETL.2395 | 44550812 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117101431 | T3 DI GRIZZLY TAP 001/015 REPR GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 001/015 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.300829 | 39.8957 | ETL.2395 | 44550828 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117101543 | T3 EI GRIZZLY TAP 003/008 RPR GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 003/008 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.321709 | 39.9042 | ETL.2395 | 44551357 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117101594 | T3 EI GRIZZLY TAP 003/008 RPR GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 003/008 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.321709 | 39.9042 | ETL.2395 | 44551451 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117101782 | T2 EI SLT SPNGS-TIGER CREK 11/91 REPAINT | 43842278 | SALT SPRINGS-TIGER CREEK | 011/091 | ICS | F | Pre-2020_(3) On high spread structure | Budget Owner (Paint) |  |  | TR2 | <90D | Central | WSIP |  |  |  |  | Program | 2021- Paint Program | '-120.413491 | 38.4788 | ETL.3500 | 40579800 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Released
117103496 | T3 EI GRIZZLY TAP 3/007 RPR GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 003/007 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-121.321358 | 39.9031 | ETL.2395 | 44551416 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117103719 | T3 DI FULTON-HOPLAND 26/03 RPL STRW | 31453752 | FULTON-HOPLAND | 026/003 | 70Y | E | 2020_(1a) PSPS |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.98844 | 38.8019 | ETL.6890 | 40664532 | Structure-Wood | Rotten | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  | 2019-05-15
117104788 | T2 PARADISE-TABLE MTN 20/165 RPR GYWS | 43727174 | PARADISE-TABLE MTN | 020/165 | ICS | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-121.577357 | 39.6897 | ETL.4316 | 44383208 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117104885 | T2 PARADISE-TABLE MTN 20/164 RPR POLE | 43724325 | PARADISE-TABLE MTN | 020/164 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-121.575878 | 39.6894 | ETL.4316 | 40758508 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117105377 | T2 DI DRUM-SUMMIT #1 23/273 INSTL MRKW | 43910114 | DRUM-SUMMIT #1 | 023/273 | ICW | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.395358 | 39.311 | ETL.1440 | 44768882 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117105672 | T2 EI PRDS-TBL MT 20/159C RPL POLE | 31453760 | PARADISE-TABLE MTN | 020/159 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.561014 | 39.6874 | ETL.4316 | 44383201 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
117106034 | T3 DI DRUM-HIGGINS 010/095C RPR GYWW | 43852139 | DRUM-HIGGINS | 010/095C | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.889585 | 39.1785 | ETL.4393 | 44202753 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
117106073 | T3 DI DRUM-HIGGINS 010/095B RPR GYWW | 43852139 | DRUM-HIGGINS | 010/095B | ICW | E | Pre-2020_(9a) Other ignition related |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.88969 | 39.1785 | ETL.4393 | 44202752 | Guy Wire-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
117106136 | T3 DI DRUM-HIGGINS 010/095A RPR GYWW | 43852139 | DRUM-HIGGINS | 010/095A | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.889809 | 39.1785 | ETL.4393 | 44202751 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
117106280 | T3 DI GRIZZLY TAP 003/010R CMPLETED | 43760153 | TAP (CITY OF SANTA CLARA) | 003/010 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.322034 | 39.9061 | ETL.2395 | 44551469 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117106281 | T3 DI GRIZZLY TAP 003/010C CMPLETED | 43760153 | TAP (CITY OF SANTA CLARA) | 003/010 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.322034 | 39.9061 | ETL.2395 | 44551470 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117106282 | T3NT DI GRIZZLY TAP 003/010L INST GMKW |  | TAP (CITY OF SANTA CLARA) | 003/010 | ICW | F | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.322034 | 39.9061 | ETL.2395 | 44551372 | Guy Wire Mark /Indic-Wood | Missing | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117106284 | T3NT DI GRIZZLY TAP 003/010R INST GMKW |  | TAP (CITY OF SANTA CLARA) | 003/010 | ICW | F | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.322034 | 39.9061 | ETL.2395 | 44551469 | Guy Wire Mark /Indic-Wood | Missing | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117106285 | T3NT DI GRIZZLY TAP 003/010C INST GMKW |  | TAP (CITY OF SANTA CLARA) | 003/010 | ICW | F | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.322034 | 39.9061 | ETL.2395 | 44551470 | Guy Wire Mark /Indic-Wood | Missing | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117106330 | T2 DI VOLTA- SOUTH 001/042 RPR STRW | 43827513 | VOLTA-SOUTH | 001/042 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.872548 | 40.4348 | ETL.8300 | 40877069 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117106336 | T2 DI VOLTA-SOUTH 001/043 RPR INSW | 43827513 | VOLTA-SOUTH | 001/043 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.872337 | 40.4341 | ETL.8300 | 40868019 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117106338 | T2NT DI VOLTA-SOUTH 002/051 INST MRKW | 44309960 | VOLTA-SOUTH | 002/051 | ICW | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.871603 | 40.4301 | ETL.8300 | 40650375 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117106348 | T2 DI COLEMAN-CTTNWD 003/069 RPR STRW | 44309976 | COLEMAN-COTTONWOOD | 003/069 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.185657 | 40.4169 | ETL.6430 | 40615792 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117106370 | T2 DI DRUM-SUMMIT#2 025/305L INS MRKW | 43889098 | DRUM-SUMMIT #2 | 025/305 | ICW | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.366028 | 39.3102 | ETL.1450 | 44558954 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117106497 | DI GRIZZLY TAP 000/001C RPR GYWW |  | TAP (CITY OF SANTA CLARA) | 000/001 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-121.279937 | 39.8898 | ETL.2395 | 44549998 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117106512 | T2 DI VOLTA-SOUTH 002/051 RPR STRW | 44309960 | VOLTA-SOUTH | 002/051 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.871603 | 40.4301 | ETL.8300 | 40650375 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117106515 | T2 DI VOLTA-SOUTH 002/052 RPR SPLW | 44309960 | VOLTA-SOUTH | 002/052 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.871613 | 40.4296 | ETL.8300 | 40752210 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117106539 | DI GRIZZLY TAP 000/001A RPR GYWW |  | TAP (CITY OF SANTA CLARA) | 000/001 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-121.279937 | 39.8898 | ETL.2395 | 44549954 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117106650 | T2NT DI VOLTA-SOUTH 002/052 INS MRKW | 44309960 | VOLTA-SOUTH | 002/052 | ICW | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.871613 | 40.4296 | ETL.8300 | 40752210 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117106777 | T2NT DI COLEMAN-CTTNWD 003/069 INS MRKW | 44309976 | COLEMAN-COTTONWOOD | 003/069 | ICW | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.185657 | 40.4169 | ETL.6430 | 40615792 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117107573 | DI JFFRSN-HLLSDLE #1 000/002B RPR GYWW | 43877610 | JEFFERSON-HILLSDALE JCT | 000/002B | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-122.286953 | 37.4587 | ETL.7190 | 40740530 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Bay |  | Y - 5 | SMCPD
117107684 | T3 DI GRIZZLY TAP 000/001B RPR GYWW |  | TAP (CITY OF SANTA CLARA) | 000/001 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-121.279937 | 39.8898 | ETL.2395 | 44550027 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117107994 | T3 DI GRIZZLY TAP 3/13 RPR GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 003/013 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.322523 | 39.9081 | ETL.2395 | 44551402 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117108554 | T2 DI COLEMAN-CTTWD 3/71 RPR GYWW | 44309976 | COLEMAN-COTTONWOOD | 003/071 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.18741 | 40.4172 | ETL.6430 | 40669940 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117108863 | T2 PARADISE-TABLE MTN 14/118 RPL INSS | 31456702 | PARADISE-TABLE MTN | 014/118 | 93K | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-121.506631 | 39.6548 | ETL.4316 | 41176898 | Insulator-Steel | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  | Yes
117109624 | T2 DI SPAULDING-SUMMIT 015/502 RPL STRW | 31453471 | SPAULDING-SUMMIT | 015/502 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.379169 | 39.3222 | ETL.8060 | 40771531 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
117110031 | T2 DI COLGATE-PALERMO 11/221 RPL STRW | 31517754 | COLGATE-PALERMO | 011/221 | 70Y | E | 2020_(1a) PSPS |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.37601 | 39.3755 | ETL.6500 | 40664501 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
117110034 | T2 DI COLGATE-PALERMO 11/222 RPL STRW | 31423185 | COLGATE-PALERMO | 011/222 | 70Y | E | 2020_(1a) PSPS |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.376563 | 39.3761 | ETL.6500 | 40757197 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
117110548 | T2 DI MTN GATE JCT-CASCADE 4/44 RPR STRW | 43758388 | MTN GATE JCT-CASCADE | 004/044 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.32778 | 40.6854 | ETL.7640 | 40817290 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117110774 | T2 EI PHILO JCT-ELK 07/003 RPR GYWW | 43762377 | PHILO JCT-ELK | 007/003 | ICW | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.251039 | 39.0476 | ETL.7780 | 40666580 | Guy Wire-Wood | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  | 2019-06-17
117111552 | T2 DI KONOCTI-MIDDLETWN ;23/8 INST HRDW | 43761672 | KONOCTI-MIDDLETOWN | ;023/008 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.610737 | 38.8993 | ETL.6380 | 40876736 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  | 2019-05-29
117112359 | T2 DI BTTE VLLY-CRIBOU 007/054D RPR GYWW | 43930734 | BUTT VALLEY-CARIBOU | 007/054D | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.147461 | 40.0865 | ETL.1180 | 44399900 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117113374 | T2 DI PARADISE-BUTTE 5/060 RPL INSS | 31454860 | PARADISE-BUTTE | 005/060 | 93K | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.672185 | 39.7072 | ETL.4396 | 41127255 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  | Yes
117113824 | T2 DI VOLTA-SOUTH 002/049 INST MRKW | 44309960 | VOLTA-SOUTH | 002/049 | ICW | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.871633 | 40.4312 | ETL.8300 | 40592380 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117113825 | T2 DI VOLTA-SOUTH 002/049 RPR GYWW | 44309960 | VOLTA-SOUTH | 002/049 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.871633 | 40.4312 | ETL.8300 | 40592380 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117114514 | T3 DI GRIZZLY TAP 000/002 RPR GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 000/002 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.279382 | 39.8901 | ETL.2395 | 44403544 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117114581 | T2 DI STLS-MLS SS-MTCA 22/140 PAINT STRS | 43841835 | STANISLAUS-MELONES SS-MANTECA #1+ | 022/140 | ICS | F | Pre-2020_(9a) Other ignition related | Budget Owner (Paint) |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.695711 | 37.9474 | ETL.3830 | 40856463 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - Prog Multi
117114584 | T2 DI STLS-MLS SS-MTCA 22/139 PAINT STRS | 43841835 | STANISLAUS-MELONES SS-MANTECA #1+ | 022/139 | ICS | E | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.693845 | 37.9488 | ETL.3830 | 40865916 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - Prog Multi
117114925 | T2NT DI TESLA-METCALF 025/105 INS MRKS |  | TESLA-METCALF | 025/105 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-121.679879 | 37.3551 | ETL.6110 | 40753703 | Marker (i.e. signs)-Steel | Missing | Install |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  | Y - Prog Multi | 2019-07-31
117115053 | T2 DI MTN GTE JCT-CSCDE 4/54 RPL STRW | 31471015 | MTN GATE JCT-CASCADE | 004/054 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.330268 | 40.6765 | ETL.7640 | 40771396 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
117115077 | DI HARTLEY-CLEARLAKE 027/003 REMV DEBRIS | 43760950 | HARTLEY-CLEARLAKE | 027/003 | ICW | E | Pre-2020_(9a) Other ignition related |  |  |  |  | LATE | North Coast | WSIP | FSRP | [5 empty] | '-122.925384 | 39.0217 | ETL.7515 | 40667031 | Structure-Wood | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  | 2019-06-05
117115191 | T2 EI PALERMO-COLGATE C004/020 RPR CONS | 43900094 | PALERMO-COLGATE | C004/020 | ICS | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.27042 | 39.3082 | ETL.5360 | 40582434 | Conductor-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes
117116835 | DI GRIZZLY TAP 000/005 A RPR GYWW |  | TAP (CITY OF SANTA CLARA) | 000/005 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-121.278587 | 39.893 | ETL.2395 | 44549955 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117116836 | DI GRIZZLY TAP 000/005C RPR GYWW |  | TAP (CITY OF SANTA CLARA) | 000/005 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-121.278587 | 39.893 | ETL.2395 | 44550028 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117116838 | DI GRIZZLY TAP 000/005B RPR GYWW |  | TAP (CITY OF SANTA CLARA) | 000/005 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-121.278587 | 39.893 | ETL.2395 | 44549899 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117117756 | DI PALERMO-WYANDOTTE 001/012 REP GYWW | 43952543 | PALERMO-WYANDOTTE | 001/012 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-121.540179 | 39.4673 | ETL.4315 | 41162776 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117117870 | DI PALERMO-WYANDOTTE 001/012 INS MRKW | 43952543 | PALERMO-WYANDOTTE | 001/012 | ICW | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-121.540179 | 39.4673 | ETL.4315 | 41162776 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117117961 | T2 DI KILARC-DSCHTS 2/42 RMV VEG | 43930137 | KILARC-DESCHUTES | 002/042 | ICW | F | Pre-2020_(9a) Other ignition related |  |  | Likely veg | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.88718 | 40.6516 | ETL.7300 | 40600363 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117119180 | PARADISE-TABLE MTN 022/173 RPR ANCS | 31456797 | PARADISE-TABLE MTN | 022/173 | 93E | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | North Valley | Non-WSIP | [6 empty] | '-121.606588 | 39.6948 | ETL.4316 | 44712231 | Anchor-Wood | No Good/Out of Stdrd | Replace | ESTS erdy | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  | Yes
117119189 | PARADISE-TABLE MTN 22/171 INST DAMPS | 43875188 | PARADISE-TABLE MTN | 022/171 | ICS | E | Pre-2020_(9a) Other ignition related |  |  |  |  | LATE | North Valley | Non-WSIP | [6 empty] | '-121.597896 | 39.6933 | ETL.4316 | 44712215 | Damper-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117119285 | T2 DI VOLTA-SOUTH 002/067 RPR SPLW | 44309960 | VOLTA-SOUTH | 002/067 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.871649 | 40.4209 | ETL.8300 | 40868021 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117120652 | T2 DI PALERMO-OROVILLE 001/029 REP CRSW | 31474478 | PALERMO-OROVILLE #1 | 001/029 | 93E | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.538288 | 39.4599 | ETL.7730 | 40809918 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  | Yes
117121349 | T2 DI SPAULDING-SUMMIT 003/124 REPL POLE | 31453471 | SPAULDING-SUMMIT | 003/124 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.58876 | 39.3137 | ETL.8060 | 40771415 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
117121362 | T2 DI VOLTA-SOUTH 001/032 RPR GYWW | 43827513 | VOLTA-SOUTH | 001/032 | ICW | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.872563 | 40.4414 | ETL.8300 | 40877110 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117121947 | T3 POE-RIO OSO 019/130 RPL INSS | 31434829 | POE-RIO OSO | 019/130 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | Non-WSIP | [6 empty] | '-121.481858 | 39.7147 | ETL.5540 | 40633646 | Insulator-Steel | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  | Yes
117122025 | T3 POE-RIO OSO 19/133 RPL INSS | 31434829 | POE-RIO OSO | 019/133 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | Non-WSIP | [6 empty] | '-121.483534 | 39.705 | ETL.5540 | 40684587 | Insulator-Steel | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  | Yes
117122665 | T2 DI SPAULDING-SUMMIT 004/150 INST MRKW | 43947948 | SPAULDING-SUMMIT | 004/150 | ICW | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.576016 | 39.3072 | ETL.8060 | 40681444 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117123534 | T2 DI SPAULDING-SUMMIT 004/142 INST MRKW | 43947948 | SPAULDING-SUMMIT | 004/142 | ICW | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.579866 | 39.3083 | ETL.8060 | 40771499 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117123537 | T2 DI SPAULDING-SUMMIT 015/495 RPR GYWW | 43876251 | SPAULDING-SUMMIT | 015/495 | ICW | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.379842 | 39.3259 | ETL.8060 | 40826216 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117123777 | T2 DI VOLTA-SOUTH 003/089 RPR STRW | 44309963 | VOLTA-SOUTH | 003/089 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.876855 | 40.4088 | ETL.8300 | 40826966 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117123779 | T2 DI COLEMAN-SOUTH 7/146 INSTL HRDD | 43743540 | COLEMAN-SOUTH | 007/146 | ICW | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.000332 | 40.4045 | ETL.6450 | 40699986 | Hardware-Wood | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117123801 | T3NT DI DRUM-RIO OSO #2 001/018 REPAINT |  | DRUM-RIO OSO #2 | 001/018 | ICS | E | Pre-2020_(9a) Other ignition related |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.800608 | 39.2549 | ETL.1430 | 40858251 | Structure-Steel | Paint/Coating | Other |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes
117123804 | T2NT DI CRG VEW-CSCDE 000/009 INS MRKS | 43881016 | CRAG VIEW-CASCADE | 000/009 | ICS | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.412229 | 40.9212 | ETL.1350 | 41166981 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117123830 | T2 DI SPAULDING-SUMMIT 004/143 INST MRKW | 43947948 | SPAULDING-SUMMIT | 004/143 | ICW | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.579404 | 39.3081 | ETL.8060 | 40751907 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117123838 | T2 DI SPAULDING-SUMMIT 004/147 INST MRKW | 43947948 | SPAULDING-SUMMIT | 004/147 | ICW | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.577561 | 39.3075 | ETL.8060 | 40876679 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117123841 | T2 DI VOLTA-SOUTH 003/089 INS MRKW | 44309963 | VOLTA-SOUTH | 003/089 | ICW | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.876855 | 40.4088 | ETL.8300 | 40826966 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117123940 | T2 DI BTTE VLLEY-CRBU 007/054D RPL ANCW | 31471617 | BUTT VALLEY-CARIBOU | 007/054D | 93E | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.147461 | 40.0865 | ETL.1180 | 44399900 | Anchor-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain
117123942 | T2NT DI BTE VLY-CRBU 007/054D INS GMKW | 43930732 | BUTT VALLEY-CARIBOU | 007/054D | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.147461 | 40.0865 | ETL.1180 | 44399900 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain
117124612 | T2 DI VOLTA-SOUTH 003/076 RPR STRW | 44309963 | VOLTA-SOUTH | 003/076 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.87376 | 40.4169 | ETL.8300 | 40657235 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117124613 | T2NT DI VOLTA-SOUTH 003/076 INST MRKW | 44309963 | VOLTA-SOUTH | 003/076 | ICW | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.87376 | 40.4169 | ETL.8300 | 40657235 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117124811 | T2 DI CHOWCHILLA-KERCKHF 1/008 RPR STRS | 43795033 | CHOWCHILLA-KERCKHOFF | 001/008 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-119.582894 | 37.0906 | ETL.1250 | 44191727 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  | Y - 21
117125198 | T2 DI SPAULDING-SUMMIT 003/135 INST MRKW | 43947948 | SPAULDING-SUMMIT | 003/135 | ICW | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.583262 | 39.3094 | ETL.8060 | 40819457 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117125300 | T2 DI COLEMAN-SOUTH 007/155 RPR HRDD | 43930460 | COLEMAN-SOUTH | 007/155 | ICW | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.008259 | 40.4032 | ETL.6450 | 40601114 | Hardware-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117125357 | T3 DI GRIZZLY TAP 003/001 RPR GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 003/001 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.320267 | 39.8983 | ETL.2395 | 44551370 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117125514 | T3NT DI KESWICK-TRINITY 04/066 INST MRKW | 43661466 | KESWICK-TRINITY | 004/066 | ICW | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-122.531553 | 40.6241 | ETL.7270 | 40701679 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  | Yes
117125983 | T2 DI COLEMAN-COTTONWOOD 03/72 RPR GYWW | 44309976 | COLEMAN-COTTONWOOD | 003/072 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.188207 | 40.4172 | ETL.6430 | 40667368 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117125984 | T2 DI CLMN-CTTNWD 003/072 RPR SPLW | 44309976 | COLEMAN-COTTONWOOD | 003/072 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.188207 | 40.4172 | ETL.6430 | 40667368 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117125988 | T2NT DI CLMN-CTTNWD 003/072 INST MRKW | 44309976 | COLEMAN-COTTONWOOD | 003/072 | ICW | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.188207 | 40.4172 | ETL.6430 | 40667368 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117126534 | T2 DI TABLE MTN-PLRMO 7/32 INSTL MRKS | 43760152 | TABLE MTN-PALERMO | 007/032 | ICS | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.516766 | 39.5453 | ETL.5690 | 40670002 | Marker (i.e. signs)-Steel | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117127050 | T2 DI SPAULDING-SMMT 4/156 RPL STRW | 31519330 | SPAULDING-SUMMIT | 004/156 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.573525 | 39.3067 | ETL.8060 | 40862154 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
117128876 | DI SPAULDING-SUMMIT 008/268 INST MRKW | 43876243 | SPAULDING-SUMMIT | 008/268 | ICW | E | Pre-2020_(1b) Lines with special commitments |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-120.519991 | 39.3102 | ETL.8060 | 40590021 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117129203 | T2 DI SLT SPRNG-TGRCRK 006/052 RPR FOND | 43842265 | SALT SPRINGS-TIGER CREEK | 006/052 | ICQ | F | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.320465 | 38.4774 | ETL.3500 | 40643393 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - 13
117129501 | T2 DI MTN GATE JCT-CASCDE 6/71 INST MRKW | 43758388 | MTN GATE JCT-CASCADE | 006/071 | ICW | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.335557 | 40.6577 | ETL.7640 | 40668597 | Marker (i.e. signs)-Wood | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117129564 | T2 DI COLEMAN-SOUTH 7/145 INSTL HRDD | 43939301 | COLEMAN-SOUTH | 007/145 | ICW | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.99943 | 40.4046 | ETL.6450 | 40592368 | Hardware-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117129585 | T2 DI KESWICK-CASCADE 03/065 REMOVE STRW | 43859605 | KESWICK-CASCADE | 003/065 | ICW | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.365805 | 40.6672 | ETL.7260 | 40577346 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117129689 | T3 DI KILARC-CDR CREEK 06/151 RPL STRW | 31452939 | KILARC-CEDAR CREEK | 006/151 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.989997 | 40.7138 | ETL.7290 | 40657252 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
117129863 | T2 DI VOLTA-SOUTH 03/073 RPL CRSW | 31453744 | VOLTA-SOUTH | 003/073 | 93E | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.871663 | 40.4175 | ETL.8300 | 40600820 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  | Yes
117134374 | T2 FORT BRAGG-ELK 04/01 REP ACC ROAD | 43837882 | FORT BRAGG-ELK | 004/001 | CHS | F | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 |  | North Coast | Non-WSIP | [6 empty] | '-123.747387 | 39.1781 | ETL.2060 | 40584446 | Road | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLR | Roads | Expense | 932 | Lakeville
117135999 | T2 DI VOLTA-SOUTH 003/080 RPR SPLW | 44309963 | VOLTA-SOUTH | 003/080 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.876908 | 40.4165 | ETL.8300 | 40825105 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117136141 | T2 DI VOLTA-SOUTH 003/090 RPR STRW | 44309963 | VOLTA-SOUTH | 003/090 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.876868 | 40.4076 | ETL.8300 | 40809981 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117136149 | T2 DI VOLTA-SOUTH 003/090 INST MRKW | 44309963 | VOLTA-SOUTH | 003/090 | ICW | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.876868 | 40.4076 | ETL.8300 | 40809981 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117136308 | T2 DI VOLTA-SOUTH 003/083 RPR SPLW | 44309963 | VOLTA-SOUTH | 003/083 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.876902 | 40.414 | ETL.8300 | 40615850 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117136368 | T2 DI VOLTA-SOUTH 003/093 RPL INSW | 31483881 | VOLTA-SOUTH | 003/093 | 93I | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.876857 | 40.4043 | ETL.8300 | 40615853 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Table Mountain |  |  | Yes
117136453 | EI DRUM-SUMMIT #2 16/189B INST MRKW | 43900106 | DRUM-SUMMIT #2 | 016/189B | ICW | E | Pre-2020_(1b) Lines with special commitments |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-120.520693 | 39.3099 | ETL.1450 | 42572817 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117137049 | T3NT DI MORAGA-OAKLAND #3 00/06 PNT STRT | 43725286 | MORAGA-OAKLAND #3 | 000/006 | ICS | E | Pre-2020_(9a) Other ignition related | Budget Owner (Paint) |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.17228 | 37.8458 | ETL.2740 | 40804648 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay
117138079 | T2 DI SMARTVILLE-NICOLAS #2 0/6 RPR STRW | 43852590 | SMARTVILLE-NICOLAUS #2 | 000/006 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.302217 | 39.2055 | ETL.8000 | 44177581 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
117142697 | T3NT DI DRUM-RIO OSO #1 002/027 CANCEL | 44304427 | DRUM-RIO OSO #1 | 002/027 | ICS | E | Pre-2020_(9a) Other ignition related |  |  | CANCEL/CNCL | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.811856 | 39.2479 | ETL.1420 | 40821341 | Structure-Steel | Paint/Coating | Other | CONS crdy | CONS | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes
117146256 | T3 DI GRIZZLY TAP 000/11R RPR GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 000/011 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.279468 | 39.8976 | ETL.2395 | 44549929 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117146382 | T3 EI GRIZZLY TAP 3/13L RPR GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 003/013 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.322523 | 39.9081 | ETL.2395 | 44551440 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117146633 | T3 EI KESWICK-TRINITY 004/066 RPR STRW | 43661466 | KESWICK-TRINITY | 004/066 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-122.531553 | 40.6241 | ETL.7270 | 40701679 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  | Yes
117146778 | T3 DI GRIZZLY TAP 3/13L RPR GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 003/013 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.322523 | 39.9081 | ETL.2395 | 44551418 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117146801 | T3 DI GRIZZLY TAP 000/003 RPR GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 000/013 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.284071 | 39.8978 | ETL.2395 | 44549884 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117146941 | T3 DI GRIZZLY TAP 3/13L RPR STRW | 43760153 | TAP (CITY OF SANTA CLARA) | 003/013 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.322523 | 39.9081 | ETL.2395 | 44551418 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117146978 | T3 DI GRIZZLY TAP 001/001 REP GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 001/001 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.286359 | 39.8997 | ETL.2395 | 44549982 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117147211 | T3 DI GRIZZLY TAP 001/001 REP GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 001/001 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.286359 | 39.8997 | ETL.2395 | 44550004 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117147212 | T3 DI GRIZZLY TAP 001/001 REP GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 001/001 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.286359 | 39.8997 | ETL.2395 | 44550038 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117147414 | T3 DI GRIZZLY TAP 001/002R RPR GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 001/002 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.287584 | 39.8998 | ETL.2395 | 44549860 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117147419 | T3 DI GRIZZLY TAP 001/002L RPR GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 001/002 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.287584 | 39.8998 | ETL.2395 | 44549933 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117147644 | T3 DI KILARC-CEDAR CRK 008/184 REPL STRW | 31452939 | KILARC-CEDAR CREEK | 008/184 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.990518 | 40.7291 | ETL.7290 | 40759577 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
117148302 | T3 EI BRUNSWICK #1 000/003 RPL INSS | 31451763 | BRUNSWICK #1 TAP | 000/003 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.008684 | 39.1445 | ETL.1422 | 40678231 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Sacramento |  |  | Yes
117148781 | T3 DI GRIZZLY TAP 000/012 RPR GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 000/012 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.281573 | 39.8977 | ETL.2395 | 44550036 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117149046 | T2 DI VOLTA-SOUTH 004/097 REPAIR STRW | 44309963 | VOLTA-SOUTH | 004/097 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.877577 | 40.4008 | ETL.8300 | 40615856 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  | Yes
117149114 | T2 DI VOLTA-SOUTH 002/053 RPR STRW | 44309960 | VOLTA-SOUTH | 002/053 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.871648 | 40.429 | ETL.8300 | 40759365 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117149341 | T2 DI VACA-PARKWAY 018/096 REPL HRDS | 43760157 | VACA-PARKWAY | 018/096 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.141373 | 38.2404 | ETL.5850 | 40818166 | Hardware-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes
117149509 | T3 DI CRESTA-RIO OSO 13/111 INST HRDT | 43844884 | CRESTA-RIO OSO | 013/111 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  | TR3 | LATE | North Valley | WSIP | [5 empty] | reprioritization of work - E/F tags pushed to 2020 | '-121.45864 | 39.7688 | ETL.4590 | 40911293 | Hardware-Tower | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
117149670 | T2 DI CNTRVLLE-TBLE MTN 04/072 RPL STRW | 31453747 | CENTERVILLE-TABLE MTN | 004/072 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.705002 | 39.735 | ETL.6320 | 40809988 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
117149679 | T2 EI RND MTN-TBL MTN#2 016/086 RPR OPGW |  | ROUND MTN-TABLE MTN #2 | 016/086 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.944335 | 40.5683 | ETL.6070 | 40820554 | Shield Wire / OPGW-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117151393 | T3NT DI EGL-RCK FTN-SVRD 001/008 REPAINT | 44310477 | EAGLE ROCK-FULTON-SILVERADO | 001/008 | ICS | E | Pre-2020_(9a) Other ignition related |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.802834 | 38.8216 | ETL.4392 | 40871409 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville |  |  | 2019-05-21
117152650 | T2 DI VC-VCVLL-JMSN-N TWR 11/80 PNT STRS | 44305728 | VACA-VACAVILLE-JAMESON-NTH TWR | 011/080 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.055628 | 38.3022 | ETL.4100 | 40589119 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes
117152862 | T3 DI DRUM-HIGGINS 011/108 RPL POLE | 31497888 | DRUM-HIGGINS | 011/108 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.918022 | 39.1758 | ETL.4393 | 44172300 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC erdy srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
117152866 | T3NT DI DRUM-HIGGINS 011/108 CANCEL |  | DRUM-HIGGINS | 011/108 | ICW | E | Pre-2020_(4b) On structure in bucket 4 |  |  | CANCEL/CNCL | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.918022 | 39.1758 | ETL.4393 | 44172300 | Marker (i.e. signs)-Wood | Missing | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117153290 | T2 DI MTN GTE JCT-CSCDE 4/43 RPL STRW | 31498057 | MTN GATE JCT-CASCADE | 004/043 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.327516 | 40.6863 | ETL.7640 | 40770562 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
117154831 | T2 DI KESWICK-TRINITY 026/439 RPL INSW | 31471572 | KESWICK-TRINITY | 026/439 | 93I | E | Pre-2020_(2) High fire spread TD |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Access Issues | 2021 - FSR 12/2020 | '-122.862768 | 40.6956 | ETL.7270 | 40915768 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Table Mountain |  |  | Yes
117154913 | T2 DI COLEMAN-SOUTH 011/227 RPR GYWW | 43939301 | COLEMAN-SOUTH | 011/227 | ICW | E | Pre-2020_(2) High fire spread TD |  |  |  | TR2 | LATE | North Valley | WSIP | [5 empty] | 2021 - FSR | '-122.075103 | 40.4035 | ETL.6450 | 40601081 | Ground Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117155363 | T2 DI COLEMAN-SOUTH 011/226 RPR GYWW | 43939301 | COLEMAN-SOUTH | 011/226 | ICW | E | Pre-2020_(2) High fire spread TD |  |  |  | TR2 | LATE | North Valley | WSIP | [5 empty] | 2021 - FSR | '-122.074287 | 40.4035 | ETL.6450 | 40615771 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117155368 | T2NT DI ORVL-THM-TB MT #1 2/10 INST MRKS | 43932170 | MTN #1(CDWR) | 002/010 | ICS | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.519455 | 39.5466 | ETL.6621 | 42580633 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117155466 | T2 DI DELTA -MTN GATE 4/20 PNT STRT | 43866628 | DELTA-MOUNTAIN GATE JCT | 004/080 | ICS | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.374078 | 40.8902 | ETL.6750 | 40618038 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117156110 | T2 DI MTN GTE JCT-CSCDE 5/62 REFRAME | 31471920 | MTN GATE JCT-CASCADE | 005/062 | 93E | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.332915 | 40.6671 | ETL.7640 | 40816279 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  | Yes
117156118 | T3NT DI KESWICK-TRINITY 005/072 INST MRK | 43661466 | KESWICK-TRINITY | 005/072 | ICW | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-122.545832 | 40.6308 | ETL.7270 | 40617597 | Marker (i.e. signs)-Wood | Missing | Install | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  | Yes
117156311 | T3 DI KESWICK-TRINITY 005/072 RPR STRW | 43661466 | KESWICK-TRINITY | 005/072 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-122.545832 | 40.6308 | ETL.7270 | 40617597 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  | Yes
117156660 | T2 DI BUCKS CRK-RCK-CRST :1/8 REPAINT | 43897313 | BUCKS CREEK-ROCK CREEK-CRESTA | :001/008 | ICS | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.359405 | 39.9025 | ETL.4430 | 40863666 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117156666 | T2 DI MTN GATE JCT-CSCD 0/8 (R) RPL STRW | 31498056 | MTN GATE JCT-CASCADE | 000/008 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.312031 | 40.7331 | ETL.7640 | 44565563 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain
117156757 | T3 DI KILRC-CEDAR CREEK 013/282 RPL STRW | 31452939 | KILARC-CEDAR CREEK | 013/282 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.939555 | 40.7901 | ETL.7290 | 40657260 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
117156765 | T2 HUMBOLDT-TRINITY-115 kV 49/1 pol butt | 43729541 | HUMBOLDT-TRINITY | 049/001 | ICW | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | Non-WSIP | FSRP | [7 empty] | ETL.1820 | 44324189 | Structure-Wood | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2019-08-09
117156813 | T2 DI TRINITY-MAPLE CRK 53/07 RPR GYWW | 43749708 | TRINITY-MAPLE CREEK | 053/007 | ICW | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.869921 | 40.7685 | ETL.8170 | 40808971 | Guy Wire-Wood | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2019-07-26
117158236 | T2 DI VLTA-DESCHUTES 14/309 RPL CRSW | 31440331 | VOLTA-DESCHUTES | 014/309 | 93E | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.13041 | 40.5274 | ETL.8290 | 40656937 | Crossarm-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  | Yes
117158237 | T2 DI VLTA-DESCHUTES 14/309 RPR GYWW | 43939089 | VOLTA-DESCHUTES | 014/309 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.13041 | 40.5274 | ETL.8290 | 40656937 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117158594 | DI POE-RIO OSO 39/258 RPL INSS | 31454862 | POE-RIO OSO | 039/258 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-121.517957 | 39.4273 | ETL.5540 | 40896918 | Insulator-Steel | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  | Yes
117158598 | T2 DI SBRTE-STDRD OIL SS #2 0/3 CANCEL | 31484431 | SOBRANTE-STANDARD OIL SW STA #1 | 000/003 | 93K | E | Pre-2020_(5) TD tag on other lines |  |  | CANCEL/CNCL | TR2 | LATE | Central | WSIP | [6 empty] | '-122.209755 | 37.9086 | ETL.3790 | 40671682 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - 1
117158708 | T2 DI CSCD-BNTN-DSCHTS 3/82 RPR STRW | 43690811 | CASCADE-BENTON-DESCHUTES | 003/082 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.313488 | 40.6012 | ETL.6310 | 40759450 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117158751 | T2 DI PORT COSTA BRICK TAP 0/7 REPL STRW | 31438719 | PORT COSTA BRICK TAP | 000/007 | 70Y | B | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-122.171622 | 38.0283 | ETL.6371 | 40857377 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Bay |  | Y - 5
117159073 | T2NT DI VOLTA-SOUTH 4/100 INST MRKW | 44309963 | VOLTA-SOUTH | 004/100 | ICW | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.878295 | 40.399 | ETL.8300 | 40667414 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  | Yes
117160743 | T2 DI COLEMAN-SOUTH 10/223 RPR GYWW | 43939301 | COLEMAN-SOUTH | 010/223 | ICW | E | Pre-2020_(2) High fire spread TD |  |  |  | TR2 | LATE | North Valley | WSIP | [5 empty] | 2021 - FSR | '-122.071645 | 40.4035 | ETL.6450 | 40816370 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117160748 | DI MTN GTE JCT-CASCADE 01/014R RPL STRW | 31439163 | MTN GATE JCT-CASCADE | 001/014 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.315194 | 40.7236 | ETL.7640 | 44566782 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC erdy srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain
117161245 | T3 DI DIABLO UNIT #1 005/003A INST HRDT | 43908768 | DIABLO UNIT #1 (NF) | 005/003A | ICQ | E | Pre-2020_(9a) Other ignition related |  |  | Likely MAT error - delink to correct | TR3 | LATE | South | WSIP |  |  |  |  | Clearance Delayed | Per DCPP Unit#1 Outage is October 2020 | '-120.847725 | 35.2145 | ETL.5940 | 40575759 | Hardware-Tower | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 543 | Pismo Beach |  | Y - 4
117161998 | T2 DI PLACER=GOLD HILL #1 9/65 INST HRDS | 43910532 | PLACER-GOLD HILL #1 | 009/065 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.148471 | 38.7611 | ETL.3340 | 40920924 | Hardware-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Sacramento
117162276 | T2 DI CLMN SOUTH 10/224 RPR GYWW | 43939301 | COLEMAN-SOUTH | 010/224 | ICW | E | Pre-2020_(2) High fire spread TD |  |  |  | TR2 | LATE | North Valley | WSIP | [5 empty] | 2021 - FSR | '-122.072646 | 40.4035 | ETL.6450 | 40877023 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117162278 | T2 DI CLMN SOUTH 10/224 REFRAME | 31521652 | COLEMAN-SOUTH | 010/224 | 93E | E | Pre-2020_(2) High fire spread TD |  |  |  | TR2 | LATE | North Valley | WSIP | [5 empty] | 2021 - FSR | '-122.072646 | 40.4035 | ETL.6450 | 40877023 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  | Yes
117162965 | T2 DI MDCNO-PHLO JCT-HPLD 07/01 RPR INSS | 43831064 | MENDOCINO #1 | 007/001 | ICS | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.161188 | 39.1678 | ETL.7530 | 41118206 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville |  |  | 2019-08-06
117164963 | T3 DI KILARC-CEDAR CREEK 7/170 STRW RPL | 31452939 | KILARC-CEDAR CREEK | 007/170 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.997387 | 40.7208 | ETL.7290 | 40592395 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
117165002 | T2 DI COLEMAN-SOUTH 10/222 GYWW RPR | 43939301 | COLEMAN-SOUTH | 010/222 | ICW | E | Pre-2020_(2) High fire spread TD |  |  |  | TR2 | LATE | North Valley | WSIP | [5 empty] | 2021 - FSR | '-122.070748 | 40.4035 | ETL.6450 | 40826899 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117165040 | T3 DI KILARC-CEDAR CREEK 10/227 SPLW RPR | 43685209 | KILARC-CEDAR CREEK | 010/227 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.969525 | 40.7542 | ETL.7290 | 40766568 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117165043 | T2 DI KILARC-DESCHUTES 10/226 STRW RPR | 43826337 | KILARC-DESCHUTES | 010/226 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.017692 | 40.5758 | ETL.7300 | 40876516 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117165521 | T3 DI KILARC-CEDAR CREEK 11/252 RPR GYWW | 43685209 | KILARC-CEDAR CREEK | 011/252 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.95676 | 40.7695 | ETL.7290 | 40592403 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117166491 | T2 DI SPAULDING-SUMMIT 3/137 INS MRKW | 43947948 | SPAULDING-SUMMIT | 003/137 | ICW | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.582241 | 39.3091 | ETL.8060 | 40878092 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117166660 | DI MTN GATE JCT-CASCADE 02/024L RPL STRW | 31439163 | MTN GATE JCT-CASCADE | 002/024 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.319553 | 40.7105 | ETL.7640 | 44565517 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC erdy srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
117167297 | T2 HILLSDLE JCT-HMB ?011/002 RPL INSS | 31485117 | HILLSDALE JCT-HALF MOON BAY | ?011/002 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | Non-WSIP | FSRP | [5 empty] | '-122.419086 | 37.4772 | ETL.7060 | 40784163 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - 9
117167434 | T2 HILLSDLE JCT-HMB ?011/004 rpl insulat | 31485117 | HILLSDALE JCT-HALF MOON BAY | ?011/004 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | Non-WSIP | FSRP | [5 empty] | '-122.420323 | 37.4743 | ETL.7060 | 40838053 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - 9
117167459 | T2 HILLSDLE JCT-HMB ?011/005 rpl insulat | 31485117 | HILLSDALE JCT-HALF MOON BAY | ?011/005 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | Non-WSIP | FSRP | [5 empty] | '-122.420819 | 37.4734 | ETL.7060 | 40889141 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - 9
117167527 | T2 DI JEFFERSON HILL 0/1 RPR GYWW | 43877610 | JEFFERSON-HILLSDALE JCT | 000/001 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.284343 | 37.4566 | ETL.7190 | 40588758 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Bay |  | Y - 2 | SMCPD
117167745 | T2 HILLSDLE JCT-HMB ?011/006 rpl insulat | 31485117 | HILLSDALE JCT-HALF MOON BAY | ?011/006 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | Non-WSIP | FSRP | [5 empty] | '-122.421867 | 37.4728 | ETL.7060 | 40639569 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - 9
117167782 | T2 HILLSDLE JCT-HMB ?011/007 rpl insulat | 31485117 | HILLSDALE JCT-HALF MOON BAY | ?011/007 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | Non-WSIP | FSRP | [5 empty] | '-122.42336 | 37.4721 | ETL.7060 | 40625862 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - 9
117167997 | T2NT DI SMRTVLE-CMP FR WST 0/1 INS MRKW | 43852551 | SMARTVILLE-CAMP FAR WEST | 000/001 | ICW | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.303172 | 39.2088 | ETL.7970 | 42549744 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117167998 | T2 DI KILARC-DESCHUTES A023/494 RPR GYWW | 43682103 | KILARC-DESCHUTES | A023/494 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.255163 | 40.5639 | ETL.7300 | 40755256 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117168111 | T2 DI KILARC-DESCHTES A023/494 INST MRKW | 43826337 | KILARC-DESCHUTES | A023/494 | ICW | F | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.255163 | 40.5639 | ETL.7300 | 40755256 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117169303 | T2 DI FITCH MTN#1 0/3 RPL STRW | 31492619 | FITCH MTN #1 TAP | 000/003 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.844027 | 38.6064 | ETL.6891 | 40648712 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  | 2019-07-19
117169515 | DI SBRNT-GZZLY-CLRMNT#1 002/026 PNT STRS | 44586187 | SOBRNTE-GRIZZLY-CLARMNT #1+ | 002/026 | ICS | F | Pre-2020_(9a) Other ignition related | Budget Owner (Paint) |  |  |  | LATE | Central | WSIP | [6 empty] | '-122.183441 | 37.876 | ETL.3740 | 40604230 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  | Y - Prog Multi
117169925 | DI MTN GATE JCT-CASCADE 002/021 RPR STRW | 43758388 | MTN GATE JCT-CASCADE | 002/021 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.318313 | 40.7142 | ETL.7640 | 44565370 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117169953 | T2 DI CORTINA-MNDCNO #1 45/222 RPL INSS | 31439888 | CORTINA-MENDOCINO #1 | 045/222 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.943192 | 39.1797 | ETL.1330 | 40681091 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Lakeville |  |  | 2019-07-19
117170489 | DI MTN GATE JCT-CSCDE 1/17 INS GMKW | 43758388 | MTN GATE JCT-CASCADE | 001/017 | ICW | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-122.316544 | 40.7195 | ETL.7640 | 44565508 | Guy Wire Mark /Indic-Wood | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117170642 | DI MTN GATE JCT-CSCDE 1/17 INS MRKW | 43758388 | MTN GATE JCT-CASCADE | 001/017 | ICW | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-122.316544 | 40.7195 | ETL.7640 | 44565508 | Marker (i.e. signs)-Wood | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117170706 | T2 DI SISQUC-SNT YNZ SS 018/257 RPR GYWW | 43763696 | SISQUOC-SANTA YNEZ SW STA | 018/257 | ICW | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | South | WSIP | FSRP | [5 empty] | '-120.153972 | 34.6833 | ETL.3700 | 40751454 | Guy Wire-Wood | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - 12
117170818 | T2 DI STL-MNS SS-MTC #1 018/112 RPR STRT | 43841828 | STANISLAUS-MELONES SS-MANTECA #1+ | 018/112 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.638792 | 37.9897 | ETL.3830 | 40669923 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - Prog Multi
117171443 | T2NT DI TSLA-SLDD-MNTC 025/152 INS MRKW | 43841364 | TESLA-SALADO-MANTECA | 025/152 | ICW | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-121.207111 | 37.4701 | ETL.4000 | 40912757 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 7
117171524 | T2NT DI TSLA-SLDD-MNTC 025/152 INS GMKW | 43841365 | TESLA-SALADO-MANTECA | 025/152 | ICW | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-121.207111 | 37.4701 | ETL.4000 | 40912757 | Guy Wire Mark /Indic-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog Multi
117171739 | T2 DI PITTSBURG-TESLA #1 20/091 RPL HRDT | 43753186 | PITTSBURG-TESLA #1 | 020/091 | ICQ | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-121.674361 | 37.8381 | ETL.5510 | 40586628 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 5
117173620 | T2 DI CLNGA #1-SAN MGUEL 30/00 RPR GYWS | 43763703 | COALINGA #1-SAN MIGUEL | 030/000 | ICS | E | Pre-2020_(4) TD tag on high spread line | Superintendent Approved work efficiency |  |  | TR2 | LATE | South | WSIP | FSRP | [5 empty] | '-120.639635 | 35.8584 | ETL.8580 | 40594402 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Pismo Beach |  | Y - 15
117175032 | T2 DI COLGATE-PALERMO 19/379 RPR STRW | 43728969 | COLGATE-PALERMO | 019/379 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.462708 | 39.4466 | ETL.6500 | 40672092 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117175526 | T2 DI COTTONWOOD #1 005/037 RPR INSS | 44155926 | COTTONWOOD #1 | 005/037 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.267769 | 40.3198 | ETL.6620 | 40920723 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117175710 | T2 DI COTTONWOOD #1 005/037 INST MRKS | 44155926 | COTTONWOOD #1 | 005/037 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.267769 | 40.3198 | ETL.6620 | 40910980 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117176290 | T2NT DI TSLA-SLDO-MNTC 024/134 INS MRKW | 43841274 | TESLA-SALADO-MANTECA | 024/134 | ICW | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-121.21818 | 37.4914 | ETL.4000 | 40912743 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 7
117176295 | T2 DI TESLA-SALADO-MNTCA 24/140 INS GMKW | 43841277 | TESLA-SALADO-MANTECA | 024/140 | ICW | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-121.210875 | 37.4821 | ETL.4000 | 40903941 | Guy Wire Mark /Indic-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog Multi
117176442 | T2 DI STN-MLN-SS-MNTC#1 019/123 RPR STRT | 43841835 | STANISLAUS-MELONES SS-MANTECA #1+ | 019/123 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.661438 | 37.9729 | ETL.3830 | 40642845 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Victor |  | Y - 16
117176857 | T2 DI STANLIUS-NEWARK 094/624 RPR STRT |  | STANISLAUS-NEWARK #1 (12KV) | 094/624 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-121.896632 | 37.567 | ETL.3850 | 40772241 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 5
117176902 | T2 DI KONOCTI-MIDDLETOWN 27/000 RPL STRW | 31490901 | KONOCTI-MIDDLETOWN | 027/000 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.666201 | 38.9055 | ETL.6380 | 40587058 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  | 2019-05-29
117178730 | T2 DI WST PNT-VLLY SPRNGS 5/64 REPR STRW | 43843753 | WEST POINT-VALLEY SPRINGS | 005/064 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [8 empty] | ETL.8350 | 44405870 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 24
117178736 | T2 DI WST PNT-VLLY SPRNGS 5/64 RPR STRW | 43843753 | WEST POINT-VALLEY SPRINGS | 005/064 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [8 empty] | ETL.8350 | 44405869 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 24
117179252 | T2NT DI CORTINA-MDCN #1 46/224 INST MRKS | 43908929 | CORTINA-MENDOCINO #1 | 046/224 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.947692 | 39.1838 | ETL.1330 | 40762065 | Marker (i.e. signs)-Steel | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville |  |  | 2019-07-19
117179350 | T2 DI DRUM SUMMIT #2 27/330 RPR GYWW | 43876485 | DRUM-SUMMIT #2 | 027/330 | ICW | E | Pre-2020_(1b) Lines with special commitments |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-120.330512 | 39.315 | ETL.1450 | 44553539 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117179393 | T2 DI DRUM SUMMIT #2 27/330 INSTL MRKW | 43876485 | DRUM-SUMMIT #2 | 027/330 | ICW | F | Pre-2020_(1b) Lines with special commitments |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-120.330512 | 39.315 | ETL.1450 | 44553539 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117179878 | T2 DI DRUM SUMMIT #2 27/328 RPR GYWW | 43876485 | DRUM-SUMMIT #2 | 027/328 | ICW | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.331645 | 39.3131 | ETL.1450 | 44552402 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117179939 | T2 DI HUMBOLDT-MPLE CRK 13/5L RPL STRW | 31485371 | HUMBOLDT-MAPLE CREEK | 013/005 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.885342 | 40.7679 | ETL.7130 | 44859704 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS erdy | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2020-02-24
117180202 | T2 DI DRUM SUMMIT #2 27/328 RPR GYWW | 43876485 | DRUM-SUMMIT #2 | 027/328 | ICW | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.331645 | 39.3131 | ETL.1450 | 44552449 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117180367 | T2 DI KILARC-DESCHUTES 10/228 RPR STRW | 43930440 | KILARC-DESCHUTES | 010/228 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.018676 | 40.5748 | ETL.7300 | 40602020 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117180381 | DI NEWARK-LIVCERMORE 014/087 PNT/CT STRS | 43752137 | NEWARK-LIVERMORE | 014/087 | ICS | E | Pre-2020_(9a) Other ignition related | Budget Owner (Paint) |  |  |  | LATE | Central | WSIP | [6 empty] | '-121.792401 | 37.6251 | ETL.7660 | 40823795 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  | Y - 11
117180383 | T2 DI VOLTA-DESCHUTES 014/314 REPL STRW | 31453473 | VOLTA-DESCHUTES | 014/314 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.134202 | 40.5288 | ETL.8290 | 40868541 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
117180805 | T2 DI DRUM SUMMIT 27/328 RPR GYWW | 43876485 | DRUM-SUMMIT #2 | 027/328 | ICW | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.331645 | 39.3131 | ETL.1450 | 44552309 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117181042 | T2 DI STANISLAUS-MNTECA#2 18/99 RPR STRT | 43842120 | STANISLAUS-MANTECA #2 | 018/106 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.639255 | 37.9892 | ETL.3820 | 40808614 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - Prog Multi
117181062 | T2 DI DRUM-SUMMIT #2 27/327R RPR GYWW | 43876485 | DRUM-SUMMIT #2 | 027/327 | ICW | E | Pre-2020_(1b) Lines with special commitments |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-120.331828 | 39.3128 | ETL.1450 | 44552406 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117181063 | T2 DI DRUM-SUMMIT #2 27/327 RPR GYWW | 43876485 | DRUM-SUMMIT #2 | 027/327 | ICW | E | Pre-2020_(1b) Lines with special commitments |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-120.331828 | 39.3128 | ETL.1450 | 44552405 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117181064 | T2 DI DRUM-SUMMIT #2 27/327 RPR GYWW | 43876485 | DRUM-SUMMIT #2 | 027/327 | ICW | E | Pre-2020_(1b) Lines with special commitments |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-120.331828 | 39.3128 | ETL.1450 | 44552314 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117181166 | DI COPPERMINE-TIVY VALLEY 22/9 RPR GYWW | 43746875 | COPPERMINE-TIVY VALLEY | 022/009 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | South | WSIP | [8 empty] | ETL.8590 | 44307722 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Fresno |  | Y - 5
117181167 | DI COPPERMINE-TIVY VALLEY 22/9 RPR GYWW | 43746875 | COPPERMINE-TIVY VALLEY | 022/009 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | South | WSIP | [8 empty] | ETL.8590 | 44307723 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Fresno |  | Y - 5
117181351 | T2 EI MTN GTE JCT-CSCDE 001/014 RPL STRW | 31439163 | MTN GATE JCT-CASCADE | 001/014 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-122.315194 | 40.7236 | ETL.7640 | 44566781 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC erdy srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain
117181570 | T2NT DI MLIN-RND MT #2 080/411 INS GMKS | 43939115 | MALIN-ROUND MTN #2 | 080/411 | ICS | F | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.901398 | 40.993 | ETL.6020 | 40593552 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117182826 | T2 DI LOWR LAKE-HOMESTAKE 0/1G RPLC STRW | 31460373 | LOWER LAKE-HOMESTAKE TAP | 000/001G | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | FSRP | [5 empty] | '-122.617429 | 38.9111 | ETL.1481 | 40743010 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  | 2019-07-02
117184163 | T2 DI MTN GATE JCT-CSCDE 1/15 CANCEL | 43758388 | MTN GATE JCT-CASCADE | 001/015 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  | CANCEL/CNCL | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.315653 | 40.7222 | ETL.7640 | 44565592 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117184345 | T2NT DI MTN GT JCT-CSCDE 1/15 INST MRKW | 43758388 | MTN GATE JCT-CASCADE | 001/015 | ICW | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.315653 | 40.7222 | ETL.7640 | 44565592 | Marker (i.e. signs)-Wood | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117184370 | T2 DI WISHON-COPPERMINE 5/42 RPR FOND | 44571732 | WISHON-COPPERMINE | 005/042 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | South | WSIP | FSRP | [5 empty] | '-119.534881 | 37.0701 | ETL.9330 | 40675160 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 12
117184753 | T2 HILLSDALE JCT-HMB 005/052A road acces | 44305491 | HILLSDALE JCT-HALF MOON BAY | 005/052A | CHS | F | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Veg/Land/Road) |  |  | TR2 |  | Central | Non-WSIP | [6 empty] | '-122.414828 | 37.483 | ETL.7060 | 40695020 | Road | Brush Fuel | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLR | Roads | Expense | 932 | Bay
117185074 | T2 DI COLEMAN-SOUTH 005/111 RPR GYWW | 43939301 | COLEMAN-SOUTH | 005/111 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.969318 | 40.4043 | ETL.6450 | 40867993 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117186236 | T2NT DI MLIN-RND MTN #2 093/473 INS GMKS | 43939115 | MALIN-ROUND MTN #2 | 093/473 | ICS | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.916797 | 40.8251 | ETL.6020 | 40663427 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117186539 | T2 DI COLGATE-PALERMO 021/431 RPL STRW | 31423185 | COLGATE-PALERMO | 021/431 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.50906 | 39.4579 | ETL.6500 | 40757148 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
117187247 | T2 DI COLGATE-PALERMO 012/230 RPL POLE | 31472009 | COLGATE-PALERMO | 012/230 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.381802 | 39.379 | ETL.6500 | 40672067 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
117187575 | T2 DI DRUM-SUMMIT#2 27/326B RPR GYWW | 43876488 | DRUM-SUMMIT #2 | 027/326B | ICS | E | Pre-2020_(1b) Lines with special commitments |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.332239 | 39.3121 | ETL.1450 | 42572856 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117187872 | GATES-PANOCHE #2_009/040 RPLC HRDS | 43863017 | GATES-PANOCHE #2 | 009/040 | ICS | E | Pre-2020_(1b) Lines with special commitments |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.2040028 | 36.2405 | ETL.4730 | 44402089 | Hardware-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno
117187927 | T2 DI MENDOCINO-WILLITS 12/1 RMV BUTT | 43877953 | MENDOCINO-WILLITS | 012/001 | ICW | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | WSIP | FSRP | [5 empty] | '-123.319308 | 39.3738 | ETL.7540 | 40584899 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  | 2019-07-01
117188094 | T2 DI CARBERRY SS-RND MTN 26/215 REPAINT | 43897848 | CARBERRY SW STA-ROUND MTN | 026/215 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.927349 | 40.7948 | ETL.5410 | 40755336 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117188263 | T2 DI KONOCTI-MIDDLETOWN ;13/1A WASH INS | 43919388 | KONOCTI-MIDDLETOWN | ;013/001A | ICD | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.593613 | 38.7647 | ETL.6380 | 41198418 | Insulator | Contaminated | Ground Wash | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 622 | Lakeville |  |  | 2019-05-29
117188782 | T2 DI SPAULDING-SUMMIT 012/414 RPL POLE | 31495368 | SPAULDING-SUMMIT | 012/414 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.441125 | 39.3196 | ETL.8060 | 40810175 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
117189368 | T2 DI TRACY-LOS BAN 30/143 RPR GYWS | 43844596 | TRACY-LOS BANOS | 030/143 | ICS | E | Pre-2020_(5) TD tag on other lines |  |  | Tower guy | TR2 | LATE | Central | WSIP | [6 empty] | '-121.218474 | 37.4895 | ETL.6130 | 40651827 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Victor |  | Y - Prog Multi
117190584 | DI KONOCTI-MIDDLETOWN 29/2 CANCEL | 43919877 | KONOCTI-MIDDLETOWN | 029/002 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  | CANCEL/CNCL |  | LATE | North Coast | WSIP | FSRP | [5 empty] | '-122.626008 | 38.9122 | ETL.6380 | 40656001 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  | 2019-05-29
117191321 | T2 DI FORT ROSS-GUALALA 058/02 RPL HRDD | 43920743 | GUALALA-MONTE RIO | 058/002 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.512932 | 38.7766 | ETL.6980 | 40656433 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  | 2019-08-21
117191435 | T2 DI CAPE HRN TAP 0/3 RPR SLPW | 43909975 | CAPE HORN TAP | 000/003 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.94638 | 39.1197 | ETL.6761 | 40649981 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117191538 | T2 DI TESLA-LOS BANOS#1 027/123 RPR GYWS | 43844592 | TESLA-LOS BANOS #1 | 027/123 | ICS | E | Pre-2020_(5) TD tag on other lines |  |  | Tower guy | TR2 | LATE | Central | WSIP | [6 empty] | '-121.197147 | 37.4521 | ETL.6100 | 40658774 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Victor |  | Y - Prog Multi
117191685 | T2 DI TESLA-LOS BANOS#1 027/125 RPR GYWS | 43844592 | TESLA-LOS BANOS #1 | 027/125 | ICS | E | Pre-2020_(5) TD tag on other lines |  |  | Tower guy | TR2 | LATE | Central | WSIP | [6 empty] | '-121.193908 | 37.446 | ETL.6100 | 40753727 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Victor |  | Y - Prog Multi
117191788 | DI FULTON-PUEBLO 040/207 RPR STRT | 43893848 | FULTON-PUEBLO | 040/207 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | North Coast | WSIP | [6 empty] | '-122.714941 | 38.4968 | ETL.1600 | 40808458 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 543 | Lakeville |  |  | 2019-07-12
117192261 | PITTS-COL STL 004/027 ajust SW 197 | 44609768 | PITTSBURG-COLUMBIA STEEL | 004/027 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | Central | Non-WSIP | [6 empty] | '-121.876313 | 37.9869 | ETL.3300 | 40743393 | Switch-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Bay |  | Y - Prog Multi
117192537 | T2 DI TESLA-METCALF 25/104 RPL INSS | 31460740 | TESLA-METCALF | 025/104 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-121.680962 | 37.3587 | ETL.6110 | 40783376 | Insulator-Steel | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - Prog Multi
117192915 | T2 DI EAGLE ROCK-CORTINA :20/1 RPR HRDD | 43918877 | EAGLE ROCK-CORTINA | :020/001 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.611978 | 39.0104 | ETL.1470 | 41176412 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  | 2019-07-17
117194464 | T2 DI TESLA-LOS BANOS 027/125 REMV NEST | 43844592 | TESLA-LOS BANOS #1 | 027/125 | ICS | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-121.193908 | 37.446 | ETL.6100 | 40753727 | Structure-Steel | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - 4
117196522 | T2 HUMBOLDT-TRINITY 50/6 RMV DEBRIS | 43729541 | HUMBOLDT-TRINITY | 050/006 | ICW | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | Non-WSIP | FSRP | [7 empty] | ETL.1820 | 44194944 | Structure-Wood | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
117196809 | T3NT DI YNK (NRTH FRK) TAP 0/3 INST MRKW |  | YANKE (NORTH FORK) TAP (IDLE) | 000/003 | ICW | E | Pre-2020_(1b) Lines with special commitments |  | DLFL upon completion of 30878389 |  | TR3 | LATE | South | WSIP | [6 empty] | '-119.499698 | 37.2312 | ETL.9341 | 40646693 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Fresno
117197049 | T3 DI YANKE (NORTH FRK) TAP 0/8 RPR GYWW | 44301879 | YANKE (NORTH FORK) TAP (IDLE) | 000/008 | ICW | E | Pre-2020_(1b) Lines with special commitments |  | DLFL upon completion of 30878389 |  | TR3 | LATE | South | WSIP | [6 empty] | '-119.496938 | 37.2329 | ETL.9341 | 40872695 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Fresno
117197182 | T3NT DI YNK (NRTH FRK) TP 0/8 INST MRKW |  | YANKE (NORTH FORK) TAP (IDLE) | 000/008 | ICW | E | Pre-2020_(1b) Lines with special commitments |  | DLFL upon completion of 30878389 |  | TR3 | LATE | South | WSIP | [6 empty] | '-119.496938 | 37.2329 | ETL.9341 | 40872695 | Marker (i.e. signs)-Wood | Missing | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Fresno
117197183 | T3NT DI YNK (NRTH FRK) TAP 0/9 INST MRKW |  | YANKE (NORTH FORK) TAP (IDLE) | 000/009 | ICW | E | Pre-2020_(1b) Lines with special commitments |  | DLFL upon completion of 30878389 |  | TR3 | LATE | South | WSIP | [6 empty] | '-119.495373 | 37.2328 | ETL.9341 | 40871107 | Marker (i.e. signs)-Wood | Missing | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Fresno
117197184 | T3NT DI YNK (NRTH FRK) TP 0/9 RPL GMKW |  | YANKE (NORTH FORK) TAP (IDLE) | 000/009 | ICW | E | Pre-2020_(1b) Lines with special commitments |  | DLFL upon completion of 30878389 |  | TR3 | LATE | South | WSIP | [6 empty] | '-119.495373 | 37.2328 | ETL.9341 | 40871107 | Guy Wire Mark /Indic-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Fresno
117197185 | T3 DI YANKE (NORTH FRK) TAP 0/9 RPR GYWW | 44301879 | YANKE (NORTH FORK) TAP (IDLE) | 000/009 | ICW | E | Pre-2020_(1b) Lines with special commitments |  | DLFL upon completion of 30878389 |  | TR3 | LATE | South | WSIP | [6 empty] | '-119.495373 | 37.2328 | ETL.9341 | 40871107 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Fresno |  | Released
117197297 | DI EVERGREEN ALMADEN 005/101 RPL INSW | 31440368 | EVERGREEN-ALMADEN | 005/101 | 93E | E | Pre-2020_(5) TD tag on other lines |  |  | Likely MAT error - delink to correct |  | LATE | Central | WSIP | [6 empty] | '-121.886589 | 37.2604 | ETL.6830 | 40633975 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Bay |  | Y - 2
117205244 | T2 HUMBOLDT-TRINITY 115kV 50/3L RMV DEBR | 43729541 | HUMBOLDT-TRINITY | 050/003 | ICW | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-123.024657 | 40.7294 | ETL.1820 | 44562267 | Structure-Wood | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
117205818 | T2NT DI BCK CRK-RK CRK-CRT 0/8 INST MRKS | 43897313 | BUCKS CREEK-ROCK CREEK-CRESTA | 000/008 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.335965 | 39.9095 | ETL.4430 | 40862115 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117207174 | T2 DI MALIN-RND MTN #2 92/471B INST GMKS | 43939115 | MALIN-ROUND MTN #2 | 092/471B | ICS | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.912495 | 40.8291 | ETL.6020 | 41162595 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117207177 | T2 DI MALIN-RND MTN #2 92/471B INST MRKS | 43939115 | MALIN-ROUND MTN #2 | 092/471B | ICS | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.912495 | 40.8291 | ETL.6020 | 41162595 | Marker (i.e. signs)-Steel | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117207847 | T2NT DI CRTNA-MNDCNO #1 046/228 INS MRKS |  | CORTINA-MENDOCINO #1 | 046/228 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.957677 | 39.1928 | ETL.1330 | 40861163 | Marker (i.e. signs)-Steel | Missing | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville |  |  | 2019-07-29
117208940 | T3 EI CARIBOU-PALERMO :31/250 RPR STRT | 44304491 | CARIBOU-PALERMO | :031/250 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.458195 | 39.7687 | ETL.3190 | 40599297 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117208942 | T3 EI CARIBOU-PALERMO :31/250 RPR STUBS | 44304491 | CARIBOU-PALERMO | :031/250 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  | Check FDA | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.458195 | 39.7687 | ETL.3190 | 40599297 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117208980 | T2 DI FORT ROSS-GUALALA 55/001 RPR SPLW | 43920743 | GUALALA-MONTE RIO | 055/001 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.491448 | 38.741 | ETL.6980 | 40584666 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  | 2019-05-30
117209863 | T2 EI MTN GATE JCT-CSCDE 1/17 RPR GYWW | 43758388 | MTN GATE JCT-CASCADE | 001/017 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.316544 | 40.7195 | ETL.7640 | 44565508 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117211108 | T2NT DI CRDLIA #1 TAP 006/112 INST MRKW | 43852387 | CORDELIA #1 TAP | 006/112 | ICW | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.215557 | 38.2473 | ETL.8182 | 40825084 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117211216 | T2 DI CORDELIA #1 TAP 006/112 INST GMKW | 43852387 | CORDELIA #1 TAP | 006/112 | ICW | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.215557 | 38.2473 | ETL.8182 | 40825084 | Guy Wire Mark /Indic-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117211487 | T2 DI CORDELIA #1 TAP 006/114 INST MRKW | 43852387 | CORDELIA #1 TAP | 006/114 | ICW | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.219055 | 38.2478 | ETL.8182 | 40768082 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117212890 | T3 EI KESWICK-TRINITY 004/070C RPR CNDW | 43661466 | KESWICK-TRINITY | 004/070 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [8 empty] | ETL.7270 | 44421136 | Conductor-Wood | No Good/Out of Stdrd | Repair | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  | Yes
117212891 | T3 EI KESWICK-TRINITY 004/070R RPR CNDW | 43661466 | KESWICK-TRINITY | 004/070 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [8 empty] | ETL.7270 | 44421137 | Conductor-Wood | No Good/Out of Stdrd | Repair | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  | Yes
117212897 | T2 EI MTN GTE JCT-CSCDE 02/28R RPR GYWW | 43758388 | MTN GATE JCT-CASCADE | 002/028 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.321548 | 40.7046 | ETL.7640 | 44565551 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117212898 | T2 EI MTN GTE JCT-CSCDE 002/22R RPL STRW | 31439163 | MTN GATE JCT-CASCADE | 002/022 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.318722 | 40.713 | ETL.7640 | 44565532 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC erdy srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
117212899 | T2 EI MTN GTE JCT-CSCDE 001/16R RPR GYWW | 43758388 | MTN GATE JCT-CASCADE | 001/016 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.316125 | 40.7208 | ETL.7640 | 44565470 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117212980 | T2 EI MTN GTE JCT-CSCDE 2/20R RPL POLE | 31526991 | MTN GATE JCT-CASCADE | 002/020 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.317788 | 40.7156 | ETL.7640 | 40676813 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC erdy srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
117212981 | T2 EI MTN GTE JCT-CSCDE 003/32L RPR GYWW | 43758388 | MTN GATE JCT-CASCADE | 003/032 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.323652 | 40.6989 | ETL.7640 | 44565574 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117212982 | T2 EI MTN GTE JCT-CSCDE 001/15R RPR GYWW | 43758388 | MTN GATE JCT-CASCADE | 001/015 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.315653 | 40.7222 | ETL.7640 | 44565592 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117212984 | T2 EI MTN GTE JCT-CSCDE 003/31R RPR GYWW | 43758388 | MTN GATE JCT-CASCADE | 003/031 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.323047 | 40.7005 | ETL.7640 | 44565388 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117212985 | T2 EI MTN GATE JCT-CASC 3/35R INS MRKW | 43758388 | MTN GATE JCT-CASCADE | 003/035 | ICW | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.32463 | 40.6951 | ETL.7640 | 44565327 | Marker (i.e. signs)-Wood | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117212986 | T3 EI GRIZZLY TAP 004/001R RPR GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 004/001 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.326678 | 39.911 | ETL.2395 | 44551405 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117212987 | T3 EI GRIZZLY TAP 004/001C RPR GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 004/001 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.326678 | 39.911 | ETL.2395 | 44551385 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117212989 | T3 EI GRIZZLY TAP 003/017C RPR GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 003/017 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.323704 | 39.9096 | ETL.2395 | 44551452 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117213080 | T3 EI GRIZZLY TAP 003/017R RPR GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 003/017 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.323704 | 39.9096 | ETL.2395 | 44551473 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117213249 | T2 EI HUMBOLDT-TRINITY 98/1R RPL STRW | 31474285 | HUMBOLDT-TRINITY | 098/001 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.829449 | 40.7658 | ETL.1820 | 44562684 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2019-08-09
117213280 | T2 EI HUMBOLDT-TRINITY 98/1C RPL STRW | 31474285 | HUMBOLDT-TRINITY | 098/001 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.829449 | 40.7658 | ETL.1820 | 44562917 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2019-08-09
117213281 | T2 EI HMBLDT-BRDGVLL 109/005R RPL STRW | 31440336 | HUMBOLDT-BRIDGEVILLE | 109/005 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | FSRP | [7 empty] | ETL.1810 | 44322614 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2019-08-27
117213410 | T2 EI HALSEY-PLACER 000/016 INST GMKW | 43852441 | HALSEY-PLACER | 000/016 | ICW | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.051259 | 38.9482 | ETL.6990 | 40873793 | Guy Wire Mark /Indic-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117213411 | T2 EI HALSEY-PLACER 000/016 INST MRKW | 43852441 | HALSEY-PLACER | 000/016 | ICW | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.051259 | 38.9482 | ETL.6990 | 40873793 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117213899 | T2 DI PINE GROVE TAP 2/50 GYWW RPR | 43843745 | PINE GROVE TAP | 002/050 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.65385 | 38.4125 | ETL.8351 | 40690803 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 4
117215066 | T2NT DI HALSEY-PLACER 1/33 INST MRKW | 43852441 | HALSEY-PLACER | 001/033 | ICW | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.061588 | 38.9373 | ETL.6990 | 40598873 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117216142 | T2 DI HALSEY-PLACER 2/42 RPL POLE | 31517753 | HALSEY-PLACER | 002/042 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.067105 | 38.9315 | ETL.6990 | 40873801 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
117220542 | T2 DI TESLA-NEWARK #2 020/133 RPR STRT |  | TESLA-NEWARK #2 | 020/133 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-121.875917 | 37.5639 | ETL.5354 | 41152679 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 10 | SFPUC
117220686 | T2 DI PALERMO-OROVLL #2 A006/76 RPL HRDD | 31475471 | PALERMO-OROVILLE #2 | A006/076 | 93I | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.502701 | 39.5111 | ETL.7740 | 40824100 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC hold erdy |  |  |  | PEND | LC | TLN | Maintenance | Capital | 508 | Table Mountain
117221236 | T3 DI DRM-GRSS VLY-WMR B017/388 RPL STRW | 31454605 | DRUM-GRASS VALLEY-WEIMAR | B017/388 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.966014 | 39.134 | ETL.6760 | 40873749 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
117221419 | T2 DI HELMS-GREGG #1 020/135 RMV NEST | 43825460 | HELMS-GREGG #1 | 020/135 | ICS | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | South | WSIP | FSRP | [5 empty] | '-119.287874 | 36.9624 | ETL.4870 | 40760551 | Structure-Steel | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  | Y - 13
117221592 | T2 DI DRUM-SUMMIT#2 023/274L RPR GYWW | 43900106 | DRUM-SUMMIT #2 | 023/274 | ICW | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.393972 | 39.3291 | ETL.1450 | 44552576 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117221899 | T3NT DI EGLE RCK-REDBD :001/008 REPAINT | 43730053 | EAGLE ROCK-REDBUD | :001/008 | ICS | F | Pre-2020_(9a) Other ignition related |  |  |  | TR3 | <90D | North Coast | WSIP | [6 empty] | '-122.788895 | 38.8368 | ETL.1480 | 40872960 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville
117222183 | T2 DI DRUM-SUMMIT#2 021/260C RPR GYWW | 43900106 | DRUM-SUMMIT #2 | 021/260 | ICW | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.416796 | 39.3283 | ETL.1450 | 44559031 | Guy Wire-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117222189 | T2 DI EAGLE ROCK-CRTN :013/011 RPR GYWW | 43918877 | EAGLE ROCK-CORTINA | :013/011 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.613404 | 38.9177 | ETL.1470 | 41176291 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  | 2019-08-06
117222419 | T2 DI DRUM-SUMMIT#2 21/260R RPR GYWW | 43900106 | DRUM-SUMMIT #2 | 021/260 | ICW | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.416796 | 39.3283 | ETL.1450 | 44558990 | Guy Wire-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117222638 | T2 DI DRUM-RIO OSO #1 021/165 REPAINT | 44304427 | DRUM-RIO OSO #1 | 021/165 | ICS | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.104121 | 39.1027 | ETL.1420 | 40756217 | Structure-Steel | Paint/Coating | Other | CONS crdy | CONS | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes
117225785 | DI HALSEY-PLACER 003/065 RPR STRS | 43852435 | HALSEY-PLACER | 003/065 | ICS | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-121.065467 | 38.9181 | ETL.6990 | 40602429 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes
117226096 | T2 DI SPAULDING-SUMMIT 14/461 RPR STRW | 43876251 | SPAULDING-SUMMIT | 014/461 | ICW | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.406206 | 39.3285 | ETL.8060 | 40770674 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117226255 | OLIVE SW STA-SMYRNA 066/513 RMV NEST | 44301120 | OLIVE SW STA-SMYRNA | 066/513 | ICS | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  |  | LATE | South | Non-WSIP | [6 empty] | '-119.454797 | 35.7194 | ETL.1923 | 41127960 | Structure-Steel | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  | Y - 7
117226341 | T2 DI SPAULDING-SUMMIT 014/471 RPR STRW | 43876251 | SPAULDING-SUMMIT | 014/471 | ICW | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.397813 | 39.3288 | ETL.8060 | 40770676 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117226346 | T2NT DI ELE ROCK-CRTINA :19/12 INST MRKW |  | EAGLE ROCK-CORTINA | :019/012 | ICW | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.611592 | 39.0076 | ETL.1470 | 41176410 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  | 2019-07-17
117226347 | T2 DI EAGLE ROCK-CORTINA :19/12 RPR GYWW | 43918877 | EAGLE ROCK-CORTINA | :019/012 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.611592 | 39.0076 | ETL.1470 | 41176410 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  | 2019-07-17
117226384 | T2NT DI HIGGINS-BELL 028/216 INS MRKS | 43905781 | HIGGINS-BELL | 028/216 | ICS | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.08292 | 39.033 | ETL.1412 | 40609049 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes
117226385 | T2 DI HIGGINS-BELL 028/216 BNT MMBR | 43905781 | HIGGINS-BELL | 028/216 | ICS | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.08292 | 39.033 | ETL.1412 | 40609049 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes
117226748 | T2 DI HIGGINS-BELL 030/228 RPR SPLS | 43905781 | HIGGINS-BELL | 030/228 | ICS | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.066524 | 39.0077 | ETL.1412 | 40679272 | Splice-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes
117226860 | T2 DI DRUM-SUMMIT #2 021/260L RPR GYWW | 43900106 | DRUM-SUMMIT #2 | 021/260 | ICW | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.416796 | 39.3283 | ETL.1450 | 44558923 | Guy Wire-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117228819 | DI CPPERMINE-TVY VLLY 022/008R RPR GYWW | 43746875 | COPPERMINE-TIVY VALLEY | 022/008 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | South | WSIP | [8 empty] | ETL.8590 | 44307727 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Fresno |  | Y - 5
117228943 | DI CPPERMINE-TVY VLLY 022/008L RPR GYWW | 43746875 | COPPERMINE-TIVY VALLEY | 022/008 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | South | WSIP | [8 empty] | ETL.8590 | 44307725 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Fresno |  | Y - 5
117229337 | T2 DI KILARC-DESCHUTES A026/542 RPL STRW | 31440586 | KILARC-DESCHUTES | A026/542 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.296332 | 40.5711 | ETL.7300 | 40702811 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
117229687 | T2 DI KILARC-DESCHUTES A024/503 RPL STRW | 31478597 | KILARC-DESCHUTES | A024/503 | 70Y | E | 2020_(1a) PSPS |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.262771 | 40.566 | ETL.7300 | 40771353 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
117230172 | T2NT DI TESLA-METCALF 018/075 INST GMKS | 43877602 | TESLA-METCALF | 018/075 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-121.640804 | 37.4503 | ETL.6110 | 40755175 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  | Y - 3 | 2019-06-04
117230953 | T2 DI SPAULDING-SUMMIT 013/437 RPL STRW | 31453471 | SPAULDING-SUMMIT | 013/437 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.424355 | 39.3273 | ETL.8060 | 40828148 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
117230958 | T2 DI SPAULDING-SUMMIT 014/465 RPR STRW | 43876251 | SPAULDING-SUMMIT | 014/465 | ICW | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.40278 | 39.3286 | ETL.8060 | 40861952 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117231163 | T2 DI COTTONWOD-RD BLFF 013/274 RPL HRDD | 43939201 | COTTONWOOD-RED BLUFF | 013/274 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.259097 | 40.2279 | ETL.6660 | 40909610 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117231310 | T2 DI SPAULDING-SUMMIT 013/440 RPL STRW | 31453471 | SPAULDING-SUMMIT | 013/440 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.421713 | 39.3276 | ETL.8060 | 40876737 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
117234284 | T2 DI SPAULDING-SUMMIT 015/494B RPR GYWW | 43876251 | SPAULDING-SUMMIT | 015/494B | ICW | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.380046 | 39.3274 | ETL.8060 | 42571859 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117234285 | T2 DI SPAULDING-SUMMIT 015/494A RPR GYWW | 43876251 | SPAULDING-SUMMIT | 015/494A | ICW | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.380083 | 39.3274 | ETL.8060 | 40810183 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117234286 | T2 DI SPAULDING-SUMMIT 015/494A CANCEL | 43876251 | SPAULDING-SUMMIT | 015/494A | ICW | E | Pre-2020_(1b) Lines with special commitments |  |  | CANCEL/CNCL | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.380083 | 39.3274 | ETL.8060 | 40810183 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117235232 | T2 DI EAGLE ROCK-CORTINA :17/13 RPR GYWW | 43918877 | EAGLE ROCK-CORTINA | :017/013 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.612304 | 38.977 | ETL.1470 | 44668641 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  | 2019-08-06
117237172 | T2 DI COTTLE-MELONES 043/253 RPLC SPLC | 43841261 | COTTLE-MELONES | 043/253 | ICS | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.537552 | 37.9444 | ETL.4530 | 40576190 | Splice-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Released
117237414 | T2 DI MNTA VSTA LS GTOS 8/158 RMV VEGN |  | MONTA VISTA-LOS GATOS | 008/158 | HNA | E | Pre-2020_(5b) On structure in bucket 5 | Budget Owner (Veg/Land/Road) |  |  | TR2 | LATE | Central | WSIP | [5 empty] | [REDACTED] - applying for Cal Trans District 4 scenic highway permmit; eta 8/15/2020 | '-122.01346 | 37.2459 | ETL.7610 | 40767246 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Bay
117237736 | T2 DI CASCAD-BTN-DSHTS A004/102 RPL INSW | 31475472 | CASCADE-BENTON-DESCHUTES | A004/102 | 93I | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.303803 | 40.589 | ETL.6310 | 40789625 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Table Mountain |  |  | Yes
117238398 | T2 DI DRUM-SUMMIT #2 020/243C RPL POLE | 31506920 | DRUM-SUMMIT #2 | 020/243C | 70Y | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.44124 | 39.3198 | ETL.1450 | 42572833 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
117238470 | T2 DI SPAULDING-SUMMIT 013/436 RPL STRW | 31495368 | SPAULDING-SUMMIT | 013/436 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.425214 | 39.3271 | ETL.8060 | 40751929 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
117238471 | T2 DI DRUM-SUMMIT #2 020/243B RPL POLE | 31506920 | DRUM-SUMMIT #2 | 020/243B | 70Y | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.441271 | 39.3198 | ETL.1450 | 42572832 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
117238474 | T2 DI DRUM-SUMMIT #2 020/243A RPL POLE | 31506920 | DRUM-SUMMIT #2 | 020/243A | 70Y | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.441308 | 39.3199 | ETL.1450 | 40761259 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
117238685 | DI DIABLO-MIDWAY #2 050/203 CANCEL | 44112153 | DIABLO-MIDWAY #2 | 050/203 | ICS | F | Pre-2020_(9a) Other ignition related |  |  | CANCEL/CNCL |  | LATE | South | WSIP | FSRP | [5 empty] | '-119.994665 | 35.2461 | ETL.5970 | 40648038 | Structure-Steel | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Midway
117238726 | T2 DI TESLA-METCALF 18/73 INS HRDS | 43888841 | TESLA-METCALF | 018/073 | ICS | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-121.63738 | 37.4571 | ETL.6110 | 40653183 | Hardware-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  | Y - Prog Multi
117239253 | T2NT DI MALIN-RND MTN#2 87/444 INS GMKS | 43621093 | MALIN-ROUND MTN #2 | 087/444 | ICQ | F | Pre-2020_(1b) Lines with special commitments |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.918917 | 40.8987 | ETL.6020 | 40753362 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117239384 | T2 DI CASCD-BTN-DSHTS A008/172 RPR INSW | 43690811 | CASCADE-BENTON-DESCHUTES | A008/172 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.254291 | 40.5577 | ETL.6310 | 40842151 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117239465 | T2 DI COTTONWOOD-RD BLFF 14/288 RPR STRW | 43939201 | COTTONWOOD-RED BLUFF | 014/288 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.254988 | 40.218 | ETL.6660 | 40909624 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117239468 | T2NT DI COTNWOD-RD BLFF 14/288 INST MRKW | 43939201 | COTTONWOOD-RED BLUFF | 014/288 | ICW | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.254988 | 40.218 | ETL.6660 | 40909624 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117239869 | T2 DI KILARC-DESCHUTES 012/255 RPR STRW | 43930440 | KILARC-DESCHUTES | 012/255 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.037095 | 40.5673 | ETL.7300 | 40656984 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117240054 | T2NT DI MALIN-RND MTN#2 87/444B INS GMKS | 43621093 | MALIN-ROUND MTN #2 | 087/444B | ICQ | F | Pre-2020_(1b) Lines with special commitments |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.919367 | 40.8987 | ETL.6020 | 41162673 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117240149 | T2 HAT CREEK #1-WESTWD 024/478 RPR ANCW | 44340173 | HAT CREEK #1-WESTWOOD | 024/478 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-121.212768 | 40.688 | ETL.7030 | 40868478 | Anchor-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  | Yes
117240986 | T2NT DI DRUM-SUMMIT#2 020/247C RPL GMKW | 43900109 | DRUM-SUMMIT #2 | 020/247C | ICW | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.436594 | 39.3235 | ETL.1450 | 42572836 | Guy Wire Mark /Indic-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117242014 | T2 DI SPAULDING-SUMMIT 016/509 RPL SPLW | 43876251 | SPAULDING-SUMMIT | 016/509 | ICW | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.378637 | 39.3181 | ETL.8060 | 40770682 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117243142 | T2NT DI DRUM-SMIT #2 020/247B RPLC GMKW | 43900109 | DRUM-SUMMIT #2 | 020/247B | ICW | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.43662 | 39.3236 | ETL.1450 | 42572835 | Guy Wire Mark /Indic-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117243251 | T2 DI TRINITY-MAPLE-CREEK 8/007 RPR SPLW | 43749708 | TRINITY-MAPLE CREEK | 008/007 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.065517 | 40.7569 | ETL.8170 | 40906368 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
117245009 | DI KNCTI-MDLTWN ;23/1 RPL BOND WIRE | 43919877 | KONOCTI-MIDDLETOWN | ;023/001 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | North Coast | WSIP | FSRP | [5 empty] | '-122.605848 | 38.8921 | ETL.6380 | 40586667 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  | 2019-07-26
117247795 | T2 DI CENTERVLLE-TBL MTN 4/67 RPR SPLICE | 43792089 | CENTERVILLE-TABLE MTN | 004/067 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.702353 | 39.7386 | ETL.6320 | 40591722 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117247797 | T2 DI CENTERVLLE-TBL MTN 4/67 RPR STRW | 43792089 | CENTERVILLE-TABLE MTN | 004/067 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.702353 | 39.7386 | ETL.6320 | 40591722 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117247986 | T2 DI CASCADE-BENTN-DSCHTS 1/33 RPL POLE | 31427801 | CASCADE-BENTON-DESCHUTES | 001/033 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.328975 | 40.6327 | ETL.6310 | 40759298 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
117248045 | DI MTN QUARRIES TAP 0/13 RPL POLE | 31456752 | MTN QUARRIES TAP | 000/013 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-121.056673 | 38.9158 | ETL.6991 | 40747065 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento
117248878 | DI DRUM-SUMMIT #1 023/278L RPL STRW | 31498145 | DRUM-SUMMIT #1 | 023/278 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-120.38842 | 39.3113 | ETL.1440 | 44767635 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS erdy | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Sacramento |  |  | Yes
117250216 | T3 DI KILARC-CEDAR CREEK 13/284 RPR GYWW | 43685209 | KILARC-CEDAR CREEK | 013/284 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.93861 | 40.791 | ETL.7290 | 40752222 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117250219 | T3NT DI KILARC-CEDAR CRK 13/284 INST MRK | 43826337 | KILARC-CEDAR CREEK | 013/284 | ICW | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.93861 | 40.791 | ETL.7290 | 40752222 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117250928 | T2 EI MNTA VSTA-LOS GTS 9/171 RMV VEGN |  | MONTA VISTA-LOS GATOS | 009/171 | HNA | E | Pre-2020_(5b) On structure in bucket 5 | Budget Owner (Veg/Land/Road) |  |  | TR2 | LATE | Central | WSIP | [5 empty] | [REDACTED] - applying for Cal Trans District 4 scenic highway permmit; eta 8/15/2020 | '-122.00102 | 37.2416 | ETL.7610 | 40597932 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Bay
117251222 | T2 EI SPAULDING-SUMMIT 015/494C CANCEL | 31453471 | SPAULDING-SUMMIT | 015/494C | 70Y | E | Pre-2020_(1b) Lines with special commitments |  |  | CANCEL/CNCL | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.380026 | 39.3275 | ETL.8060 | 44204517 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
117251343 | T2NT DI CTTNWD-PNRMA 000/001 INS MRKW | 43881008 | COTTONWOOD-PANORAMA | 000/001 | ICW | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.267408 | 40.4001 | ETL.1340 | 40591230 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117251385 | T2 DI CTTNWD-PNRM 000/001 RPR GYWW | 43881008 | COTTONWOOD-PANORAMA | 000/001 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.267408 | 40.4001 | ETL.1340 | 40591230 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117251419 | T2 DI CTTNWD-PNRMA 000/001 RPR STRW | 43881008 | COTTONWOOD-PANORAMA | 000/001 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.267408 | 40.4001 | ETL.1340 | 40591230 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117252864 | T2NT DI DRUM-SMMT #2 018/217L INS MRKW | 43888819 | DRUM-SUMMIT #2 | 018/217 | ICS | E | Pre-2020_(1b) Lines with special commitments |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.480702 | 39.3174 | ETL.1450 | 44552291 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117252867 | T2NT DI DRUM-SMMT#2 18/216 INSTL MRKW | 43888819 | DRUM-SUMMIT #2 | 018/216 | ICS | E | Pre-2020_(1b) Lines with special commitments |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.481913 | 39.3173 | ETL.1450 | 44552256 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117252894 | T2 DI PALERMO-COLGATE 17/81 INSTL MRKS | 43727762 | PALERMO-COLGATE | 017/081 | ICS | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.502015 | 39.4113 | ETL.5360 | 40590994 | Marker (i.e. signs)-Steel | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117253004 | T2 DI FORT BRAGG-ELK 012/008 RMV VEGN |  | FORT BRAGG-ELK | 012/008 | HNA | E | Pre-2020_(9a) Other ignition related |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.789375 | 39.285 | ETL.2060 | 40876312 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Lakeville
117253159 | T2 DI PALERMO-COLGATE 14/70 INST MRKS | 43727762 | PALERMO-COLGATE | 014/070 | ICS | F | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.502239 | 39.4438 | ETL.5360 | 40605320 | Marker (i.e. signs)-Steel | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117254556 | T2 DI CRIBOU-PLUMAS JCT 015/007 RPL STRW | 31455444 | CARIBOU-PLUMAS JCT | 015/007 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.934872 | 39.9571 | ETL.6290 | 40824657 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
117254850 | T2 DI SPALDING-SUMT 013/434 RPR STRW | 43876247 | SPAULDING-SUMMIT | 013/434 | ICW | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.426888 | 39.3268 | ETL.8060 | 40650059 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117255195 | T2NT DI MALIN-ROND MTN#2 55/275 INS GMKS | 43939115 | MALIN-ROUND MTN #2 | 055/275 | ICS | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.607129 | 41.2644 | ETL.6020 | 40759602 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117255225 | T2NT DI MALIN-ROND MTN#2 55/274 INS GMKS | 43939115 | MALIN-ROUND MTN #2 | 055/274 | ICS | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.605329 | 41.2666 | ETL.6020 | 40761017 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117255271 | T2NT DI MALIN-ROND MTN#2 55/276 INS GMKS | 43939115 | MALIN-ROUND MTN #2 | 055/276 | ICS | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.609368 | 41.2616 | ETL.6020 | 40805303 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117255386 | T2NT DI MALIN-ROND MTN#2 57/282 INS GMKS | 43939115 | MALIN-ROUND MTN #2 | 057/282 | ICS | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.620299 | 41.2482 | ETL.6020 | 40663432 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117255494 | T2NT DI MALIN-ROND MTN#2 56/277 INS GMKS | 43939115 | MALIN-ROUND MTN #2 | 056/277 | ICS | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.611518 | 41.259 | ETL.6020 | 40816575 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117255616 | T2NT DI MALIN-ROND MTN#2 58/291 INS GMKS | 43939115 | MALIN-ROUND MTN #2 | 058/291 | ICS | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.637086 | 41.2275 | ETL.6020 | 40595121 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117255669 | T2NT DI DRUM-SUMMIT #2 024/297R INS MRKW | 43888819 | DRUM-SUMMIT #2 | 024/297 | ICS | E | Pre-2020_(1b) Lines with special commitments |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.376394 | 39.3146 | ETL.1450 | 44553508 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117255680 | T2NT DI MALIN-ROND MTN#2 58/286 INS GMKS | 43939115 | MALIN-ROUND MTN #2 | 058/286 | ICS | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.628407 | 41.2382 | ETL.6020 | 40820537 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117255684 | T2NT DI MALIN-ROND MTN#2 57/283 INS GMKS | 43939115 | MALIN-ROUND MTN #2 | 057/283 | ICS | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.62244 | 41.2455 | ETL.6020 | 40657481 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117255767 | T2 DI MALIN-ROUND MTN#2 65/329A INS GMKS | 43939115 | MALIN-ROUND MTN #2 | 065/329 | ICS | F | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.7157 | 41.1425 | ETL.6020 | 41111817 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117255802 | T2NT DI DRUM-SUMMIT #2 024/297L INS MRKW | 43888819 | DRUM-SUMMIT #2 | 024/297 | ICS | E | Pre-2020_(1b) Lines with special commitments |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.376394 | 39.3146 | ETL.1450 | 44553706 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117255808 | T2NT DI DRUM-SUMMIT #2 21/256R INST MRKW | 43888819 | DRUM-SUMMIT #2 | 021/256 | ICS | E | Pre-2020_(1b) Lines with special commitments |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.422532 | 39.3277 | ETL.1450 | 44558951 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117255821 | T2NT DI MALIN-ROND MTN#2 60/300 INS GMKS | 43939115 | MALIN-ROUND MTN #2 | 060/300 | ICS | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.654152 | 41.2065 | ETL.6020 | 40607839 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117255863 | T2NT DI MALIN-ROND MTN#2 57/285 INS GMKS | 43939115 | MALIN-ROUND MTN #2 | 057/285 | ICS | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.626242 | 41.2409 | ETL.6020 | 40764366 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117256015 | T2NT DI MALIN-ROND MTN#2 58/288 INS GMKS | 43939115 | MALIN-ROUND MTN #2 | 058/288 | ICS | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.631941 | 41.2338 | ETL.6020 | 40868961 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117256914 | T2 DI COTTONWOOD-DELVN#2 65/583 PNT STRS | 44305182 | COTTONWOOD-DELEVAN #2 | 065/583 | ICS | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.267916 | 40.3096 | ETL.4580 | 40657668 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117257188 | T2NT DI DRUM-SUMMIT #2 025/299R INS MRKW | 43900106 | DRUM-SUMMIT #2 | 025/299 | ICW | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.373902 | 39.3129 | ETL.1450 | 44557612 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117257659 | T2NT DI DRUM-SUMMIT #2 025/298 INST MRKW | 43900106 | DRUM-SUMMIT #2 | 025/298 | ICW | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.375207 | 39.3138 | ETL.1450 | 44553540 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117257787 | T2NT DI DRUM-SUMMIT #2 025/298 INST MRKW | 43888819 | DRUM-SUMMIT #2 | 025/298 | ICS | E | Pre-2020_(1b) Lines with special commitments |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.375207 | 39.3138 | ETL.1450 | 44553674 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117258443 | T2NT DI DRUM-SUMMIT #2 025/299L INS MRKW | 43888819 | DRUM-SUMMIT #2 | 025/299 | ICS | E | Pre-2020_(1b) Lines with special commitments |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.373902 | 39.3129 | ETL.1450 | 44557724 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117259518 | T2NT DI DRUM-SUMMIT #2 24/295L INST MRKW | 43890227 | DRUM-SUMMIT #2 | 024/295 | ICW | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.377882 | 39.3165 | ETL.1450 | 44565822 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117259857 | T2NT DI DRUM-SUMMIT #2 024/295 INST MRKW | 43890227 | DRUM-SUMMIT #2 | 024/295 | ICW | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.377882 | 39.3165 | ETL.1450 | 44565768 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117259858 | T2NT DI DRUM-SUMMIT #2 24/292R INST MRKW | 43890227 | DRUM-SUMMIT #2 | 024/292 | ICW | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.378222 | 39.3193 | ETL.1450 | 44558993 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117259906 | T2 DI MALIN-ROUND MTN#2 92/470 INS GMKS | 43939115 | MALIN-ROUND MTN #2 | 092/470 | ICS | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.910941 | 40.831 | ETL.6020 | 40868384 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117259971 | T2NT DI DRUM-SUMMIT #2 24/292L INST MRKW | 43890227 | DRUM-SUMMIT #2 | 024/292 | ICW | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.378222 | 39.3193 | ETL.1450 | 44558932 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117260299 | T2 DI MALIN-ROUND MTN#2 88/446 INST GMKS | 43621093 | MALIN-ROUND MTN #2 | 088/446 | ICQ | F | Pre-2020_(1b) Lines with special commitments |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.917832 | 40.8939 | ETL.6020 | 40819948 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117260484 | T2 DI DRUM-SUMMIT #2 023/281R RPL STRW | 31451466 | DRUM-SUMMIT #2 | 023/281 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.383287 | 39.3281 | ETL.1450 | 44552351 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
117260569 | T2NT DI DRUM-SUMMIT #2 24/284R INST MRKW | 43890227 | DRUM-SUMMIT #2 | 024/284 | ICW | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.381681 | 39.3251 | ETL.1450 | 44552282 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117260759 | T2NT DI RND-MT-TBL-M #2 72/295 INST GMKS | 44302501 | ROUND MTN-TABLE MTN #2 | 072/295 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.767701 | 39.7785 | ETL.6070 | 40756156 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117261010 | T2 DI SPLDNG-SMMT 14/458 RPR STRW | 43876251 | SPAULDING-SUMMIT | 014/458 | ICW | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.408805 | 39.3284 | ETL.8060 | 40702026 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117261019 | T2 DI SPLDNG-SMMT 14/468 REPL PL | 31453471 | SPAULDING-SUMMIT | 014/468 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.400114 | 39.3287 | ETL.8060 | 40660165 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
117261974 | T2NT DI DRUM-SUMMIT #2 24/284L INST MRKW | 43890227 | DRUM-SUMMIT #2 | 024/284 | ICW | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.381681 | 39.3251 | ETL.1450 | 44552590 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117262459 | T2 DI SPAULDING-SUMMIT 015/500 REPL POLE | 31453471 | SPAULDING-SUMMIT | 015/500 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.37936 | 39.3236 | ETL.8060 | 40702061 | Structure-Wood | Rotten | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
117262728 | T2 DI DRUM-SUMMIT #2 023/281L RPL STRW | 31451466 | DRUM-SUMMIT #2 | 023/281 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.383287 | 39.3281 | ETL.1450 | 44552584 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
117263419 | T2NT DI HIGGINS-BELL 031/237 PAINT STRS | 43905781 | HIGGINS-BELL | 031/237 | ICS | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.055396 | 38.9906 | ETL.1412 | 40593237 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes
117265862 | T2NT DI DRUM-SUMMIT #2 024/285 INST MRKW | 43900109 | DRUM-SUMMIT #2 | 020/248 | ICW | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.435468 | 39.324 | ETL.1450 | 44552308 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117266723 | T2 DI PALERMO-COLGATE C005/021 INST MRKS | 43900094 | PALERMO-COLGATE | C005/021 | ICS | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.274122 | 39.3081 | ETL.5360 | 40582214 | Marker (i.e. signs)-Steel | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes
117266725 | T2 DI PALERMO-COLGATE C004/020 INST MRKS | 43900094 | PALERMO-COLGATE | C004/020 | ICS | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.27042 | 39.3082 | ETL.5360 | 40582434 | Marker (i.e. signs)-Steel | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes
117266728 | T2 DI PALERMO-COLGATE C005/022 INST MRKS | 43900094 | PALERMO-COLGATE | C005/022 | ICS | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.276801 | 39.308 | ETL.5360 | 40672939 | Marker (i.e. signs)-Steel | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes
117266895 | T2NT DI DRUM-SUMMIT #2 023/280 INST MRKS | 43900107 | DRUM-SUMMIT #2 | 023/280 | ICS | F | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.384786 | 39.3285 | ETL.1450 | 44553871 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes
117266896 | T2 DI DRUM-SUMMIT #2 020/248 INST MRKW | 43900109 | DRUM-SUMMIT #2 | 020/248 | ICW | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.435468 | 39.324 | ETL.1450 | 44552276 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117266897 | T2NT DI DRUM-SUMMIT #2 020/246L INS MRKW | 43900109 | DRUM-SUMMIT #2 | 020/246 | ICW | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.437634 | 39.3228 | ETL.1450 | 44550019 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117266985 | DI RND MTN-COOTONWOOD #2 34/287 RPL DAMS | 43877040 | ROUND MTN-COTTONWOOD #2 | 034/287 | ICS | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-122.161075 | 40.552 | ETL.5640 | 40815318 | Damper-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain
117267072 | T2 DI TABLE MTN-PALERMO 13/60 INST MRKS | 43755803 | TABLE MTN-PALERMO | 013/060 | ICS | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.502679 | 39.4739 | ETL.5690 | 40608778 | Marker (i.e. signs)-Steel | No Good/Out of Stdrd | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117268120 | T2 DI RND MTN-CTTNWD #2 14/144 INST MRKS | 43876311 | ROUND MTN-COTTONWOOD #2 | 014/144 | ICS | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.93942 | 40.7916 | ETL.5640 | 40762721 | Marker (i.e. signs)-Steel | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117268167 | T2 DI HAT CRK #1 WSTWOOD 36/709 RPL STRW | 31504344 | HAT CREEK #1-WESTWOOD | 036/709 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.062987 | 40.5571 | ETL.7030 | 40877501 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Need New ERTC
117268600 | T2 DI MALIN-RND MTN 84/429 INST GMKS | 43939115 | MALIN-ROUND MTN #2 | 084/429 | ICS | F | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.916103 | 40.9408 | ETL.6020 | 40870732 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117268925 | T2NT DI MALIN-RND MTN 83/424 INST GMKS | 43939115 | MALIN-ROUND MTN #2 | 083/424 | ICS | F | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.915016 | 40.9553 | ETL.6020 | 40762175 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117268959 | T2 DI ROCK CRK-POE :06/49 RPR INSS | 43878132 | ROCK CREEK-POE | :006/049 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.312566 | 39.9395 | ETL.5630 | 40867230 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117268985 | T2 DI MALIN-RND MTN 88/448 INST GMKS | 43939115 | MALIN-ROUND MTN #2 | 088/448 | ICS | F | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.915843 | 40.8871 | ETL.6020 | 40871641 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117269026 | T2 DI MALIN-RND MTN 86/436 INST GMKS | 43939115 | MALIN-ROUND MTN #2 | 086/436 | ICS | F | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.917628 | 40.9203 | ETL.6020 | 40810540 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117269071 | T2 DI FORT ROSS-GUALALA 43/008 GYWW RPR | 43920743 | GUALALA-MONTE RIO | 043/008 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.316065 | 38.6937 | ETL.6980 | 40860962 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  | 2019-08-06
117269271 | T2 DI MALIN-RND MTN #2 085/432 INST GMKS | 43939115 | MALIN-ROUND MTN #2 | 085/432 | ICS | F | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.916716 | 40.9326 | ETL.6020 | 40690041 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117270049 | T2 DI PALERMO-COLGATE C004/018 INST MRKS | 43900094 | PALERMO-COLGATE | C004/018 | ICS | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.262215 | 39.3086 | ETL.5360 | 40871485 | Marker (i.e. signs)-Steel | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes
117270086 | T2 DI PALERMO-COLGATE 17/79 INST MRKS | 43727762 | PALERMO-COLGATE | 017/079 | ICS | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.502078 | 39.4173 | ETL.5360 | 40866796 | Marker (i.e. signs)-Steel | No Good/Out of Stdrd | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117270171 | T2 DI MALIN-RND MTN #2 087/443 INST GMKS | 43939115 | MALIN-ROUND MTN #2 | 087/443 | ICS | F | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.919127 | 40.8994 | ETL.6020 | 40660400 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117270222 | T2NT DI DRUM-SUMMIT #2 24/288 INST MRKW | 43900109 | DRUM-SUMMIT #2 | 024/288 | ICW | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.381621 | 39.3226 | ETL.1450 | 44552397 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117270223 | T2NT DI DRUM-SUMMIT #2 24/288 INST MRKW | 43900109 | DRUM-SUMMIT #2 | 024/288 | ICW | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.381621 | 39.3226 | ETL.1450 | 44552445 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117270226 | T2NT DI MALIN-RND MT #2 84/425 INST GMKS | 43939115 | MALIN-ROUND MTN #2 | 084/425 | ICS | F | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.91521 | 40.9528 | ETL.6020 | 40759616 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117270790 | T2 DI PIT #1-COTTONWOOD 24/195 REPL SPLS | 43879413 | PIT #1-COTTONWOOD | 024/195 | ICS | E | Pre-2020_(2) High fire spread TD |  |  |  | TR2 | LATE | North Valley | WSIP | [5 empty] | 2021 | '-121.879873 | 40.8072 | ETL.5390 | 40762590 | Splice-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117270948 | T2 DI MLN-RND MTN #2 92/469 INST GMKS | 43939115 | MALIN-ROUND MTN #2 | 092/469 | ICS | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.911872 | 40.8342 | ETL.6020 | 40869048 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117271076 | T2NT DI TESLA-METCALF 20/86 INST GMKS | 43888841 | TESLA-METCALF | 020/086 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-121.654678 | 37.4218 | ETL.6110 | 40811955 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  | Y - Prog Multi
117272250 | T2NT DI DRUM-SUMMIT #2 18/217R INST MRKW | 43888819 | DRUM-SUMMIT #2 | 018/217 | ICS | E | Pre-2020_(1b) Lines with special commitments |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.480702 | 39.3174 | ETL.1450 | 44552421 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117272254 | T2 DI PALERMO-COLGATE C003/013 INST MRKS | 43900094 | PALERMO-COLGATE | C003/013 | ICS | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.244732 | 39.3093 | ETL.5360 | 40660219 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes
117272660 | T2 DI PALERMO-COLGATE C003/015 INST MRKS | 43900094 | PALERMO-COLGATE | C003/015 | ICS | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.250569 | 39.3091 | ETL.5360 | 40757597 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes
117272664 | T2 DI PALERMO-COLGATE C003/014 INST MRKS | 43900094 | PALERMO-COLGATE | C003/014 | ICS | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.248188 | 39.3092 | ETL.5360 | 40757610 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes
117274614 | T2 DI PALERMO-COLGATE C003/016 INST MRKS | 43900094 | PALERMO-COLGATE | C003/016 | ICS | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.253743 | 39.3089 | ETL.5360 | 40819344 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes
117274763 | T2NT DI MT GT JCT-CSCD 001/012L RPL POLE | 31498056 | MTN GATE JCT-CASCADE | 001/012 | 70Y | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.314285 | 40.7263 | ETL.7640 | 44565504 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
117274981 | T2 DI VOLTA-DESCHUTES 019/439 INST MRKW | 43939089 | VOLTA-DESCHUTES | 019/439 | ICW | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.223502 | 40.5511 | ETL.8290 | 40676454 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117274983 | T2 DI DRUM-SUMMIT #2 019/225C RPL PL | 31506920 | DRUM-SUMMIT #2 | 019/225C | 70Y | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.467422 | 39.3193 | ETL.1450 | 42572829 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
117274986 | T2 DI MT GT JCT-CSCD 001/012R RPL STRW | 31498056 | MTN GATE JCT-CASCADE | 001/012 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.314285 | 40.7263 | ETL.7640 | 44565418 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain
117275037 | T2NT DI DRUM-SMMT #2 023/273R RPL POLE | 31527827 | DRUM-SUMMIT #2 | 023/273 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.395033 | 39.3291 | ETL.1450 | 44553711 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
117275094 | T2 DI VOLTA-DESCHUTES 015/319 RMV STUB | 43939089 | VOLTA-DESCHUTES | 015/319 | ICW | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.138413 | 40.5304 | ETL.8290 | 40700090 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117275168 | T2NT DI SLT SPRNGS-TGER CRK 6/52 INST M | 43842276 | SALT SPRINGS-TIGER CREEK | 006/052 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.320465 | 38.4774 | ETL.3500 | 40643393 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Victor |  | Y - Prog USFS
117275482 | T2NT DI RND MTN-TBLE MTN 67/279 INS GMKS | 44302501 | ROUND MTN-TABLE MTN #2 | 067/279 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.797139 | 39.8481 | ETL.6070 | 40867695 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117275626 | T2 DI DRUM-RIO OSO 25/189 PAINT STRS | 44304427 | DRUM-RIO OSO #1 | 025/189 | ICS | F | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.171175 | 39.0758 | ETL.1420 | 40870511 | Structure-Steel | Paint/Coating | Other | CONS crdy | CONS | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes
117275798 | T3 MAPLE CREEK-HPA 22/11 INS CRSBY CL | 43747047 | MAPLE CREEK-HOOPA | 022/011 | ICW | F | Pre-2020_(9a) Other ignition related |  |  |  | TR3 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.640275 | 40.986 | ETL.7490 | 44660734 | Guy Wire-Wood | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
117276184 | T3 EI DRUM-HIGGINS 2/29L RPL POLE | 31423101 | DRUM-HIGGINS | 002/029 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.796776 | 39.2267 | ETL.4393 | 44172228 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
117276185 | T3 EI DRUM-HIGGINS 3/36R RPL POLE | 31423101 | DRUM-HIGGINS | 003/036 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.807961 | 39.2199 | ETL.4393 | 44172267 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
117276326 | T2 DI MALIN-RND MTN #2 65/329B RPL INSS | 31439323 | MALIN-ROUND MTN #2 | 065/329B | 93K | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.716489 | 41.1419 | ETL.6020 | 41111818 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  | Yes
117276532 | T2NT DI MALIN-RD MTN #2 87/441 INST GMKS | 43939115 | MALIN-ROUND MTN #2 | 087/441 | ICS | F | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.918645 | 40.9068 | ETL.6020 | 40592584 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117277191 | T2 DI PIT #1-COTTONWOD 20/164 PAINT STRS | 44157589 | PIT #1-COTTONWOOD | 020/164 | ICS | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.810666 | 40.8239 | ETL.5390 | 40759727 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117277285 | T2 DI DRUM-RIO OSO #1 024/184 PAINT STRS | 44304427 | DRUM-RIO OSO #1 | 024/184 | ICS | F | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.159682 | 39.0805 | ETL.1420 | 40756314 | Structure-Steel | Paint/Coating | Other | CONS crdy | CONS | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes
117277312 | T2NT DI COTTNWD-DLVAN #1 7/049 INST MRKS | 44305028 | COTTONWOOD-DELEVAN #1 | 007/049 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.268076 | 40.2928 | ETL.4550 | 40868519 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117277432 | T2 DI DRUM-RIO OSO #1 024/179 REPL INSS | 31431453 | DRUM-RIO OSO #1 | 024/179 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.145678 | 39.0861 | ETL.1420 | 40865484 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Sacramento |  |  | Yes
117277716 | T2 DI UKIAH-HPLND-CLVRDL 14/135 RPR STRW | 44306677 | UKIAH-HOPLAND-CLOVERDALE | 014/135 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  | TLN/TLQ error |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.096378 | 38.996 | ETL.4050 | 40772132 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville
117279131 | T2NT DI COTTNWD-PANORMA 0/2 INST MRKW | 43881008 | COTTONWOOD-PANORAMA | 000/002 | ICW | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.267306 | 40.401 | ETL.1340 | 40674162 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117280454 | T3 EI MIDDLE FORK-GOLD HILL 9/79R RPL PL | 31454603 | MIDDLE FORK-GOLD HILL | 009/079 | 70Y | E | Pre-2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP |  |  |  |  | Material & Equipment | 2021 - Due to Long lead material delay | '-120.738363 | 38.9879 | ETL.5140 | 44553750 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
117281300 | T2 DI MORAGA-LAKEWOOD 009/067 RPR FOND |  | MORAGA-LAKEWOOD | 009/067 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-122.113852 | 37.8762 | ETL.3741 | 40804925 | Foundation/Concrete-Tower | Earth Covered Tower | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 7
117281307 | DI RIO DELL JCT-BRDGVLLE 40/02 REPR GYWW | 43749703 | RIO DELL JCT-BRIDGEVILLE | 040/002 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | North Coast | WSIP | [6 empty] | '-123.789129 | 40.4762 | ETL.7850 | 40656598 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2019-08-01
117281675 | T2 DI RND MTN-CTTNWOOD#2 15/156 INS MRKS | 43876311 | ROUND MTN-COTTONWOOD #2 | 015/156 | ICS | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.963522 | 40.7741 | ETL.5640 | 40816237 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117281802 | T2 DI MTN GATE JCT-CSCD 2/20 RPL POLE | 31526991 | MTN GATE JCT-CASCADE | 002/020 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [7 empty] | ETL.7640 | 44294293 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC erdy srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain
117281952 | T2 DI MTN GTE JCT-CSCD 2/020 RPL POLE | 31526991 | MTN GATE JCT-CASCADE | 002/020 | 70Y | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.317841 | 40.7156 | ETL.7640 | 42671353 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC erdy srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
117283050 | T2 DI KILARC-DSCHTS 11/231 RPR GYWW | 43682103 | KILARC-DESCHUTES | 011/231 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.020167 | 40.5733 | ETL.7300 | 40676507 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117284729 | T2NT DI BS CRK RK CK CRTA :0/1 INST MRKS | 43897313 | BUCKS CREEK-ROCK CREEK-CRESTA | :000/001 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.346983 | 39.9057 | ETL.4430 | 40595003 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117284759 | T2 EI ROLLINS TAP 0/11 INS ANCHOR EXT | 43790320 | ROLLINS TAP | 000/011 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.955117 | 39.1339 | ETL.6762 | 40751887 | Anchor-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117284811 | T2 DI DRUM-SUMMIT #2 19/225A RPL PL | 31506920 | DRUM-SUMMIT #2 | 019/225A | 70Y | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.46742 | 39.3194 | ETL.1450 | 40586209 | Structure-Wood | Rotten | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
117284873 | T2 DI CLMN CTTNWOOD 000/001 RPR GYWW | 44309976 | COLEMAN-COTTONWOOD | 000/001 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.121614 | 40.4053 | ETL.6430 | 40598764 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117284905 | T2NT DI MLIN-RND MTN#2 87/444A INS GMKS | 43939115 | MALIN-ROUND MTN #2 | 087/444A | ICS | F | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.919147 | 40.8987 | ETL.6020 | 41162672 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117284934 | DI DRUM-SUMMIT #2 19/227 INST MRKW | 43900109 | DRUM-SUMMIT #2 | 019/227 | ICW | E | Pre-2020_(1b) Lines with special commitments |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-120.465203 | 39.3193 | ETL.1450 | 44557576 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117285784 | T3 DI DRUM-RIO OSO #2 9/91 HRDS RPL | 43852540 | DRUM-RIO OSO #2 | 009/091 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [8 empty] | ETL.1430 | 44304984 | Hardware-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes
117286602 | T2NT DI MRLN-RND MTN #2 84/428 INST GMKS | 43939115 | MALIN-ROUND MTN #2 | 084/428 | ICS | F | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.91587 | 40.9439 | ETL.6020 | 40873267 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117287167 | T2 DI MALIN-ROUND MTN#2 65/329 INST GMKS | 43939115 | MALIN-ROUND MTN #2 | 065/329A | ICS | F | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.716422 | 41.1418 | ETL.6020 | 40868287 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117288238 | T2 BCKS CRK-RCK CRK-CRSTA 0/10 RPL DAMS | 43897311 | BUCKS CREEK-ROCK CREEK-CRESTA | 000/010 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-121.341079 | 39.9091 | ETL.4430 | 40603364 | Damper-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117288270 | T2 BUCKS CREEK-RCK CRK-CRST 0/9 REPL INS | 31462237 | BUCKS CREEK-ROCK CREEK-CRESTA | 000/009 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-121.339367 | 39.9093 | ETL.4430 | 40892650 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  | Yes
117288370 | T2 DI WST PNT-VLLY SPRGS 5/65A RPR GYWW | 43843753 | WEST POINT-VALLEY SPRINGS | 005/065A | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.633935 | 38.3896 | ETL.8350 | 40824062 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog BLM
117288404 | T2 DI PIT #1 CTTNWD 21/171 STRS PNT | 44157589 | PIT #1-COTTONWOOD | 021/171 | ICS | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.825979 | 40.8226 | ETL.5390 | 40592501 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117290764 | T2 DI INDAN FLT-YOSEMITE 37/220 RPR FOND | 43938847 | ETL.1112.POLE.NWOD | 037/220 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-119.808976 | 37.676 | ETL.1112 | 44420221 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  |  | NPS
117290810 | T2NT DI MALIN-RND MT #2 75/379 INST GMKS | 43939115 | MALIN-ROUND MTN #2 | 075/379 | ICS | F | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.8494 | 41.0633 | ETL.6020 | 40868293 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117291029 | T2NT DI MLIN-RND MTN #2 83/421 INST GMKS | 43939115 | MALIN-ROUND MTN #2 | 083/421 | ICS | F | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.914326 | 40.9646 | ETL.6020 | 40595124 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117291136 | T2NT DI MLN-RND MTN #2 090/458 INST GMKS | 43962821 | MALIN-ROUND MTN #2 | 090/458 | ICS | F | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.915505 | 40.861 | ETL.6020 | 40862531 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117291217 | T2NT DI MALIN-RND MTN 76/387 INSTL GMKS | 43939115 | MALIN-ROUND MTN #2 | 076/387 | ICS | F | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.87322 | 41.0533 | ETL.6020 | 40816580 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117291311 | T2NT DI MALIN-RND MTN#2 90/456 INST GMKS | 43939115 | MALIN-ROUND MTN #2 | 090/456 | ICS | F | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.914806 | 40.8654 | ETL.6020 | 40818822 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117291486 | T2 DI DRUM-SUMMIT #2 019/225B RPL PL | 31506920 | DRUM-SUMMIT #2 | 019/225B | 70Y | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.467419 | 39.3193 | ETL.1450 | 42572828 | Structure-Wood | Rotten | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
117291591 | T2NT DI MALIN-RND MTN 81/412 INSTL GMKS | 43939115 | MALIN-ROUND MTN #2 | 081/412 | ICS | F | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.902189 | 40.9915 | ETL.6020 | 40684098 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117291762 | T2 DI PLACER-GOLD HILL A004/037 RPL SPLW | 43910272 | PLACER-GOLD HILL #1 | A004/037 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.095847 | 38.8349 | ETL.3340 | 41123051 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
117292032 | T2NT DI MALN-RD MTN #2 091/463 INST GMKS | 43939115 | MALIN-ROUND MTN #2 | 091/463 | ICS | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.91528 | 40.8514 | ETL.6020 | 40657565 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117292119 | T2 DI FORT ROSS-GUALALA 57/9 RPR GYWW | 43920743 | GUALALA-MONTE RIO | 057/009 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.516209 | 38.7716 | ETL.6980 | 40876082 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  | 2019-08-06
117292226 | T2NT DI MALIN-RND MTN 90/461 INSTL GMKS | 43939115 | MALIN-ROUND MTN #2 | 090/461 | ICS | F | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.915988 | 40.855 | ETL.6020 | 40592655 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117292326 | T2NT DI MALIN-RND MTN 89/453A INSTL MRKS | 43939115 | MALIN-ROUND MTN #2 | 089/453A | ICS | F | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.912926 | 40.8754 | ETL.6020 | 41111837 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117292337 | T2 DI DRUM-SUMMIT #2 023/273L RPL POLE | 31497848 | DRUM-SUMMIT #2 | 023/273 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.395033 | 39.3291 | ETL.1450 | 44553712 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
117292366 | T2NT DI MLIN-RND MTN#2 77/391 INS GMKS | 43939115 | MALIN-ROUND MTN #2 | 077/391 | ICS | F | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.882376 | 41.0436 | ETL.6020 | 40586430 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117292427 | T2NT DI MALIN-RND MTN 89/451 INST GMKS | 43939115 | MALIN-ROUND MTN #2 | 089/451 | ICS | F | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.91347 | 40.879 | ETL.6020 | 40587307 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117292474 | T2NT DI MALIN-RND MTN#2 85/434 INS GMKS | 43939115 | MALIN-ROUND MTN #2 | 085/434 | ICS | F | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.9172 | 40.9261 | ETL.6020 | 40752247 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117292528 | T2NT DI MALIN-RND MTN#2 75/383 INS GMKS | 43939115 | MALIN-ROUND MTN #2 | 075/383 | ICS | F | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.863086 | 41.0591 | ETL.6020 | 40663117 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117292567 | T2NT DI MALIN-RND MTN#2 78/399 INST GMKS | 43939115 | MALIN-ROUND MTN #2 | 078/399 | ICS | F | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.890912 | 41.024 | ETL.6020 | 40868296 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117292649 | T2NT DI MALIN-RND MTN#2 78/398A INS GMKS | 43939115 | MALIN-ROUND MTN #2 | 078/398A | ICS | F | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.890795 | 41.0251 | ETL.6020 | 41162694 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117292768 | T2NT DI MALN-RND MTN #2 78/397 INST GMKS | 43939115 | MALIN-ROUND MTN #2 | 078/397 | ICS | F | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.890402 | 41.031 | ETL.6020 | 40816582 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117292965 | DI MONTE RIO-FULTON :007/009 INST MRKW |  | MONTE RIO-FULTON | :007/009 | ICW | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  |  | LATE | North Coast | WSIP | [6 empty] | '-122.894206 | 38.4897 | ETL.7630 | 40863278 | Marker (i.e. signs)-Wood | Missing | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  | 2019-07-11
117292970 | T2NT DI MLIN-RND MTN #2 76/388 INST GMKS | 43939115 | MALIN-ROUND MTN #2 | 076/388 | ICS | F | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.875852 | 41.0505 | ETL.6020 | 40862527 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117293029 | T2NT DI MALN-RD MTN#2 092/471A INST GMKS | 43939115 | MALIN-ROUND MTN #2 | 092/471A | ICS | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.912347 | 40.8289 | ETL.6020 | 41162594 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117293065 | T2NT DI MALN-RD MTN#2 092/471A INST MRKS | 43939115 | MALIN-ROUND MTN #2 | 092/471A | ICS | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.912347 | 40.8289 | ETL.6020 | 41162594 | Marker (i.e. signs)-Steel | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117293068 | T2 EI BALCH-SANGER 000/001 RPL CONN | 43845830 | BALCH-SANGER | 000/001 | ICM | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-119.088691 | 36.9085 | ETL.1050 | 40583096 | Connector | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 534 | Fresno |  | Y - 17
117293079 | T3 DI KESWICK-TRINITY 4/70 RPR STRW | 43661466 | KESWICK-TRINITY | 004/070 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [8 empty] | ETL.7270 | 44421135 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  | Yes
117293174 | T2NT DI RUND MTN-COTTON 25/224 INST MRKS | 43877040 | ROUND MTN-COTTONWOOD #2 | 025/224 | ICS | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.068898 | 40.6639 | ETL.5640 | 40761256 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117293190 | T2 DI TRINITY MPL CRK 5/2 RPR GYWW | 43749708 | TRINITY-MAPLE CREEK | 005/002 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.0264 | 40.733 | ETL.8170 | 40906319 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
117293455 | T2NT DI MALIN-RND MTN 73/372 INSTL GMKS | 43939115 | MALIN-ROUND MTN #2 | 073/372 | ICS | F | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.823127 | 41.07 | ETL.6020 | 40684090 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117293466 | T2 DI BCKS CRK-RCK CRK-CRST 0/9 INS MRKS | 43897313 | BUCKS CREEK-ROCK CREEK-CRESTA | 000/009 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.339357 | 39.9093 | ETL.4430 | 40869388 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117293533 | T2 DI BCKS CRK-RCK CRK-CRST 0/10INS MRKS | 43897313 | BUCKS CREEK-ROCK CREEK-CRESTA | 000/010 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.341079 | 39.9091 | ETL.4430 | 40603364 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117293625 | T2 DI CTTNWD-DLVN 066/587 REPAINT | 44305182 | COTTONWOOD-DELEVAN #2 | 066/587 | ICS | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.267909 | 40.3007 | ETL.4580 | 40819493 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117293721 | DI PALERMO-OROVILLE #2 A005/070 RPR GYWW | 43724470 | PALERMO-OROVILLE #2 | A005/070 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-121.504552 | 39.5078 | ETL.7740 | 40610831 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117293724 | DI PALERMO-OROVILLE #2 A005/070 RPR STRW | 43724470 | PALERMO-OROVILLE #2 | A005/070 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-121.504552 | 39.5078 | ETL.7740 | 40610831 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117293726 | DI PALERMO-OROVILLE #2 A05/070 INST MRKW | 43724470 | PALERMO-OROVILLE #2 | A005/070 | ICW | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-121.504552 | 39.5078 | ETL.7740 | 40610831 | Marker (i.e. signs)-Wood | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117294106 | T3 EI DIABLO UNIT #1 5/01 RPL HRDS | 43908329 | DIABLO UNIT #1 (NF) | 005/001 | ICS | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR3 | LATE | South | WSIP |  |  |  |  | Clearance Delayed | Per DCPP Unit#1 Outage is October 2020 | '-120.852759 | 35.2135 | ETL.5940 | 40593206 | Hardware-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Pismo Beach |  | Y - 4
117294232 | T2 EI TESLA-METCALF 20/86 RPR GYWS | 43888756 | TESLA-METCALF | 020/086 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  | Tower guy | TR2 | LATE | Central | WSIP | [6 empty] | '-121.654678 | 37.4218 | ETL.6110 | 40811955 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  | Y - Prog Multi
117294236 | T2NT EI TESLA-METCALF 20/86 INST MRKS | 43888756 | TESLA-METCALF | 020/086 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-121.654678 | 37.4218 | ETL.6110 | 40811955 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  | Y - Prog Multi
117295083 | T2NT DI MLN-RND MTN#2 076/385B INST GMKS | 44110674 | MALIN-ROUND MTN #2 | 076/385B | ICS | F | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.8692 | 41.0576 | ETL.6020 | 41162686 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117295118 | T2NT DI RND MTN-CTNWD#3 59/533 INST MRKS | 43876249 | ROUND MTN-COTTONWOOD #3 | 059/533 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.258448 | 40.4069 | ETL.5650 | 40657354 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117295187 | T2NT DI MALN-RD MTN#2 076/385A INST MRKS | 43939115 | MALIN-ROUND MTN #2 | 076/385A | ICS | F | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.869056 | 41.0575 | ETL.6020 | 41162684 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117295234 | T2NT DI MLN-RND MTN#2 076/385A INST GMKS | 43939115 | MALIN-ROUND MTN #2 | 076/385A | ICS | F | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.869056 | 41.0575 | ETL.6020 | 41162684 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117295256 | T2NT DI EL DRDO-MRI FLT #1 8/61 INS MRKS | 43869447 | ELDORADO-MISSOURI FLAT #1 | 008/061 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.76225 | 38.7561 | ETL.1530 | 40581059 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes
117295362 | T2NT DI MLN-RND MTN#2 076/385 INST GMKS | 43939115 | MALIN-ROUND MTN #2 | 076/385 | ICS | F | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.86893 | 41.0574 | ETL.6020 | 40765410 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117295777 | T2 DI DRUM-HIGGINS 023/182 RPR STRS | 43852138 | DRUM-HIGGINS | 023/182 | ICS | E | Pre-2020_(4) TD tag on high spread line | Superintendent Approved work efficiency |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.113179 | 39.0989 | ETL.4393 | 40913078 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Sacramento |  |  | Yes
117296163 | T2NT DI RND MTN-CTNWD #2 46/357 INS MRKS | 43876311 | ROUND MTN-COTTONWOOD #2 | 046/357 | ICS | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.263374 | 40.4014 | ETL.5640 | 40817901 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117296206 | T2 DI DRUM-SUMMIT #1 23/276 INST MRKW | 43910108 | DRUM-SUMMIT #1 | 023/276 | ICW | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.391738 | 39.3112 | ETL.1440 | 44767657 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117296268 | T2 DI RND MTN-CTTNWD#2 13/137L RPL STRW | 31501584 | ROUND MTN-COTTONWOOD #2 | 013/137 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.935975 | 40.8011 | ETL.5640 | 44771100 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
117296334 | T2NT DI RND MTN-CTND #3 R02/20 INST MRKS | 43876249 | ROUND MTN-COTTONWOOD #3 | R002/020 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.937705 | 40.7928 | ETL.5650 | 40604759 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117296421 | DI DRUM-SUMMIT #1 23/281R RPL POLE | 31498145 | DRUM-SUMMIT #1 | 023/281 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-120.382895 | 39.3113 | ETL.1440 | 44767638 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS erdy | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
117296598 | T2NT DI ROUND MTN-COT#2 28/246 INST MRKS | 43876311 | ROUND MTN-COTTONWOOD #2 | 028/246 | ICS | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.095257 | 40.6302 | ETL.5640 | 40816301 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117296641 | T2NT DI RND MTN-COT #2 26/231 INST MRKS | 43877040 | ROUND MTN-COTTONWOOD #2 | 026/231 | ICS | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.077023 | 40.652 | ETL.5640 | 40591310 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117296805 | DI HAT CRK #1-WESTWOOD 48/930 RPL STRW | 31456189 | HAT CREEK #1-WESTWOOD | 048/930 | 70Y | E | Pre-2020_(2) High fire spread TD |  |  |  |  | LATE | North Valley | WSIP |  |  |  |  | Access Issues | 2021 - Snow . FSR 12/2020 | '-121.019002 | 40.4004 | ETL.7030 | 40825618 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain
117296916 | T2NT DI MALIN-RND MTN 74/378 INSTL GMKS | 43939115 | MALIN-ROUND MTN #2 | 074/378 | ICS | F | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.847379 | 41.0644 | ETL.6020 | 40863447 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117297020 | DI HIGGINS-BELL 035/265 RPR SPLS | 43740275 | HIGGINS-BELL | 035/265 | ICS | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-121.059021 | 38.9369 | ETL.1412 | 40894680 | Splice-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes
117297125 | T3NT DI CARIBOU-PALERMO :36/291 RMV VEGN |  | CARIBOU-PALERMO | :036/291 | ICS | F | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR3 |  | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.48355 | 39.6997 | ETL.3190 | 40589241 | Structure-Steel | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117297127 | T3 DI CARIBOU-PALRMO :36/291 BURIED MEMB | 44051418 | CARIBOU-PALERMO | :036/291 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.48355 | 39.6997 | ETL.3190 | 40589241 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
117297348 | T2 DI WST PNT VLLY SPRGS 5/065B RPR GYWW | 43843753 | WEST POINT-VALLEY SPRINGS | 005/065B | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.633906 | 38.3896 | ETL.8350 | 42833790 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog BLM
117297392 | T2 DI WST PNT VLLY SPRGS 5/065C RPR GYWW | 43843753 | WEST POINT-VALLEY SPRINGS | 005/065C | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.633879 | 38.3896 | ETL.8350 | 42833791 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog BLM
117297475 | T2 DI RND MTN CTTNWD #2 23/210 INST MRKS | 43877040 | ROUND MTN-COTTONWOOD #2 | 023/210 | ICS | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.049281 | 40.69 | ETL.5640 | 40605362 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117298533 | T2 DI DRUM-SUMMIT #2 21/251 INST MRKW | 43900106 | DRUM-SUMMIT #2 | 021/251 | ICW | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.430864 | 39.3256 | ETL.1450 | 44553709 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117298769 | T2NT DI MLIN-RND MTN #2 92/470B INS MRKS | 43939115 | MALIN-ROUND MTN #2 | 092/470B | ICS | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.911384 | 40.831 | ETL.6020 | 41162775 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117298941 | T2NT DI MLIN-RND MTN #2 92/470B RPL GMKS | 43939115 | MALIN-ROUND MTN #2 | 092/470B | ICS | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.911384 | 40.831 | ETL.6020 | 41162775 | Guy Wire Mark /Indic-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117299069 | T2 DI MALIN-ROUND MTN#2 81/414 INST GMKS | 43939115 | MALIN-ROUND MTN #2 | 081/414 | ICS | F | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.905929 | 40.9848 | ETL.6020 | 40753360 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117299285 | T2NT DI MLN-RND MTN#2 055/271 INST GMKS | 43939115 | MALIN-ROUND MTN #2 | 055/271 | ICS | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.59905 | 41.2743 | ETL.6020 | 40587310 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117299300 | T2NT DI BK CRK-RK CRK-CRT 06/53 INS MRKS | 43897315 | BUCKS CREEK-ROCK CREEK-CRESTA | 006/053 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.416685 | 39.8427 | ETL.4430 | 40656154 | Marker (i.e. signs)-Steel | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117299303 | T2 DI BCK CRK-RCK CRK-CRST 6/52 RPR STRT | 43897310 | BUCKS CREEK-ROCK CREEK-CRESTA | 006/052 | ICQ | B | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.415007 | 39.8445 | ETL.4430 | 40683792 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
117299434 | T2 HUMBOLDT-TRINITY 56/2 RMV DEBRIS | 44311174 | HUMBOLDT-TRINITY | 056/002 | ICW | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | Non-WSIP | FSRP | [7 empty] | ETL.1820 | 44324186 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2019-08-30
117299512 | T2 HUMBOLDT-TRINITY 056/003 RMV BUTT | 44311174 | HUMBOLDT-TRINITY | 056/003 | ICW | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-123.10637 | 40.7687 | ETL.1820 | 44562215 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2019-08-30
117299845 | T3NT DI KESWICK-TRINITY 4/70 INST GMKW | 43661466 | KESWICK-TRINITY | 004/070 | ICW | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR3 | LATE | North Valley | WSIP | [8 empty] | ETL.7270 | 44421135 | Guy Wire Mark /Indic-Wood | Missing | Install | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  | Yes
117299924 | T2 EI EXCHEQUER-YOSMITE 14/43 PAINT STRS | 43863013 | EXCHEQUER-YOSEMITE | 014/043 | ICS | E | Pre-2020_(3) On high spread structure | Project efficiency (capital work) | DLFL; Completed on project 74001200 |  | TR2 | LATE | South | WSIP |  |  |  |  | Program | 2021 Paint took out of program due to future project to be removed with [REDACTED] | '-120.142658 | 37.5893 | ETL.8650 | 40646335 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  | Y - 38
117299925 | T2 EI EXCHEQUER-YOSMITE 15/49 PAINT STRS | 44585956 | EXCHEQUER-YOSEMITE | 015/049 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-120.117402 | 37.585 | ETL.8650 | 40859241 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  | Y - 42
117300353 | T2 DI TRINITY-MAPLE CREEK 20/5 REPL PL | 31456286 | TRINITY-MAPLE CREEK | 020/005 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.26918 | 40.7208 | ETL.8170 | 40765322 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2019-11-14
117300723 | T2 DI MALIN-ROUND MT #2 92/471 INST GMKS | 43939115 | MALIN-ROUND MTN #2 | 092/471 | ICS | F | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.912107 | 40.8289 | ETL.6020 | 40605581 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117300920 | T2NT DI RND MTN-CTNWD#2 16/163 INS MRKS | 43876311 | ROUND MTN-COTTONWOOD #2 | 016/163 | ICS | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.972187 | 40.7678 | ETL.5640 | 40656013 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117301321 | T2 DI COTTONWOOD-BENTON#1 1/25 RPL STRW | 31487865 | COTTONWOOD-BENTON #1 | 001/025 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.283176 | 40.4053 | ETL.6640 | 40615969 | Structure-Wood | Rotten | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
117302007 | T2 DI COTTONWOOD-BTN #1 1/26 RPL PL | 31487865 | COTTONWOOD-BENTON #1 | 001/026 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.282328 | 40.4057 | ETL.6640 | 40586298 | Structure-Wood | Rotten | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
117302323 | T2 DI BALCH-SANGER 002/014 REPL DAMS | 43845834 | BALCH-SANGER | 002/014 | ICS | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-119.122037 | 36.8981 | ETL.1050 | 40748591 | Damper-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  | Y - 17
117302331 | T2 DI BALCH-SANGER 002/014 REPR STRT | 43845831 | BALCH-SANGER | 002/014 | ICQ | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-119.122037 | 36.8981 | ETL.1050 | 40748591 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 16
117302645 | T2 DELTA MTN GATE JCT 012/164 RPL INSS | 31454737 | DELTA-MOUNTAIN GATE JCT | 012/164 | 93K | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-122.314871 | 40.7808 | ETL.6750 | 42711806 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  | Yes
117303344 | T2NT DI RND MTN-CTNWD#2 13/142 INS MRKS | 43876311 | ROUND MTN-COTTONWOOD #2 | 013/142 | ICS | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.937628 | 40.7945 | ETL.5640 | 40674336 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117303363 | T2 DI TESLA-SALADO #1 056/249 RPL INSS | 31462205 | TESLA-SALADO #1 | 056/249 | 93K | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-121.213969 | 37.4855 | ETL.3990 | 41137687 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Victor |  | Y - 1 | 2020-01-08
117303365 | T2 DI EL DORD-MO FLAT #1 10/93B RPR GYWW | 43748116 | ELDORADO-MISSOURI FLAT #1 | 010/093B | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.783738 | 38.7305 | ETL.1530 | 40740000 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117303366 | T2NT DI EL DRD-MO FLT#1 10/93B INST GMKW | 43748116 | ELDORADO-MISSOURI FLAT #1 | 010/093B | ICW | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.783738 | 38.7305 | ETL.1530 | 40740000 | Guy Wire Mark /Indic-Wood | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117303368 | T3 DI ROUND MTN-CTNWD #3 28/228 RPL INSS | 31454792 | ROUND MTN-COTTONWOOD #3 | 028/228 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.944952 | 40.7841 | ETL.5650 | 40889188 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  | Yes
117303494 | T2 DI VALLEY SPRINGS#1 12/232 RPR PL | 43836742 | VALLEY SPRINGS #1 | 012/232 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.914316 | 38.1082 | ETL.8210 | 40908316 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 23
117303554 | T2 DI LKEVILLE SNMA #1 002/028 WASH INSS | 43919384 | LAKEVILLE-SONOMA #2 | 002/028 | ICD | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Coast | WSIP | FSRP | [5 empty] | '-122.537991 | 38.2683 | ETL.2070 | 42629068 | Insulator | Contaminated | Ground Wash | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 622 | Lakeville |  |  | 2019-07-19
117303739 | T2NT DI RND MTN-CTNWD#2 16/162 INS MRKS | 43876311 | ROUND MTN-COTTONWOOD #2 | 016/162 | ICS | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.970886 | 40.7687 | ETL.5640 | 40674239 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117303881 | T2 DI VALLEY SPRINGS#1 12/234 REPL PL | 31454707 | VALLEY SPRINGS #1 | 012/234 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.915693 | 38.1074 | ETL.8210 | 40906499 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 23
117303960 | T2 DI RND MTN-CTTNWOOD#2 16/164 INS MRKS | 43876311 | ROUND MTN-COTTONWOOD #2 | 016/164 | ICS | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.974949 | 40.7657 | ETL.5640 | 40758252 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117303961 | T2NT DI RND MT-CTNWD#2 016/161 INS MRKS | 43876311 | ROUND MTN-COTTONWOOD #2 | 016/161 | ICS | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.969776 | 40.7695 | ETL.5640 | 40591302 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117304734 | T2NT DI BKS CRK RK CK CRS 6/056 INS MRKS | 43897315 | BUCKS CREEK-ROCK CREEK-CRESTA | 006/056 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.421024 | 39.8365 | ETL.4430 | 40811850 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117305112 | T2 DI RND MTN CTTNWD #3 52/469 INST MRKS | 43876249 | ROUND MTN-COTTONWOOD #3 | 052/469 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.196048 | 40.4824 | ETL.5650 | 40868130 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117305207 | T2 DI LAYTONVILLE-WILLITS 12/0 INST GMKW |  | LAYTONVILLE-WILLITS | 012/000 | ICW | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.418734 | 39.5438 | ETL.8360 | 40614438 | Guy Wire Mark /Indic-Wood | Missing | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
117305235 | T2NT DI RNC-MN-CTNWD#3 52/462 INSTL MRKS | 43876249 | ROUND MTN-COTTONWOOD #3 | 052/462 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.190824 | 40.4888 | ETL.5650 | 40647537 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117305330 | T2NT DI MALIN-RND MT#2 52/257 INST GMKS | 43939115 | MALIN-ROUND MTN #2 | 052/257 | ICS | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.571243 | 41.3085 | ETL.6020 | 40821634 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117305417 | T2NT DI MLN-RND MTN#2 052/261 INST GMKS | 43939115 | MALIN-ROUND MTN #2 | 052/261 | ICS | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.579031 | 41.2989 | ETL.6020 | 40595189 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117305519 | T2 DI MALIN-RND MTN#2 54/268 INST GMKS | 43939115 | MALIN-ROUND MTN #2 | 054/268 | ICS | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.593043 | 41.2817 | ETL.6020 | 40868959 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117305753 | T2 DI MALIN-RND MTN#2 54/268 INST HV | 43939115 | MALIN-ROUND MTN #2 | 054/268 | ICS | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.593043 | 41.2817 | ETL.6020 | 40868959 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117305823 | T2 DI MALIN-RND MTN#2 53/265 INST GMKS | 43939115 | MALIN-ROUND MTN #2 | 053/265 | ICS | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.586929 | 41.2892 | ETL.6020 | 40760689 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117305902 | T2NT DI MALIN-RND MTN#2 54/267 INST GMKS | 43939115 | MALIN-ROUND MTN #2 | 054/267 | ICS | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.591022 | 41.2842 | ETL.6020 | 40816573 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117305909 | T2 DI MALIN RND MTN #2 59/297 INST GMKS | 43939115 | MALIN-ROUND MTN #2 | 059/297 | ICS | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.64818 | 41.2138 | ETL.6020 | 40819378 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117306024 | T2 DI RND MTN CTTNWD #3 52/467 INST MRKS | 43876249 | ROUND MTN-COTTONWOOD #3 | 052/467 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.194423 | 40.4844 | ETL.5650 | 40820617 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117306172 | T2 DI ROUND MT-CTNWD #2 21/197 INST MRKS | 43877040 | ROUND MTN-COTTONWOOD #2 | 021/197 | ICS | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.028558 | 40.7175 | ETL.5640 | 40805139 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117306176 | T2 DI ROUND MT-CTNWD #2 21/198 INST MRKS | 43877040 | ROUND MTN-COTTONWOOD #2 | 021/198 | ICS | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.029517 | 40.7163 | ETL.5640 | 40867737 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117306714 | T2NT DI TESLA-METCALF 018/074 PR GYWS | 43888841 | TESLA-METCALF | 018/074 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  | Tower guy | TR2 | LATE | Central | WSIP | [6 empty] | '-121.63959 | 37.4526 | ETL.6110 | 40761170 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  | Y - Prog Multi
117306766 | T2NT DI MALIN-RND MT#2 54/269 INST GMKS | 43939115 | MALIN-ROUND MTN #2 | 054/269 | ICS | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.595077 | 41.2792 | ETL.6020 | 40868277 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117307083 | T2 HUMBOLDT-TRINITY 057/001L RMV BUTT | 44311174 | HUMBOLDT-TRINITY | 057/001 | ICW | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-123.119308 | 40.7687 | ETL.1820 | 44562714 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2019-08-30
117307114 | T2 DI MTN GATE JCT-CASCAD 4/041 RPR GYWW | 43758388 | MTN GATE JCT-CASCADE | 004/041 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.326714 | 40.6873 | ETL.7640 | 40668575 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117307132 | T2NT DI MTN GATE JCT-CASC 4/041 INS MRKW | 43758388 | MTN GATE JCT-CASCADE | 004/041 | ICW | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.326714 | 40.6873 | ETL.7640 | 40668575 | Marker (i.e. signs)-Wood | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117307588 | T2 DI PINE GROVE TAP 002/054 RPR GYWW | 43843745 | PINE GROVE TAP | 002/054 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.655952 | 38.4132 | ETL.8351 | 40825780 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor
117307650 | T2 DI PINE GROVE TAP 2/54 INST MRKW | 43843743 | PINE GROVE TAP | 002/054 | ICS | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.655952 | 38.4132 | ETL.8351 | 40825780 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - 11
117307721 | T2NT DI RND MT-CTNWD #2 21/200 INST MRKS | 43877040 | ROUND MTN-COTTONWOOD #2 | 021/200 | ICS | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.032923 | 40.7117 | ETL.5640 | 40605359 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117307757 | T2 DI CORDELIA #2 TAP 3/61B RPL STRW | 31454608 | CORDELIA #2 TAP | 003/061B | 70Y | E | 2020_(1a) PSPS |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.147892 | 38.2446 | ETL.8184 | 40740308 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento
117307905 | T2 DI CORDELIA #2 TAP 3/61C RPL STRW | 31454608 | CORDELIA #2 TAP | 003/061C | 70Y | E | 2020_(1a) PSPS |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.147812 | 38.2446 | ETL.8184 | 40741886 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento
117307975 | T2NT DI RD MT CTNWD #2 027/241 INST MRKS | 43947334 | ROUND MTN-COTTONWOOD #2 | 027/241 | ICS | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.0882 | 40.6386 | ETL.5640 | 40595020 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117308586 | T2NT DI MLN-RND MNTN #2 51/256 INST GMKS | 43939115 | MALIN-ROUND MTN #2 | 051/256 | ICS | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.569179 | 41.311 | ETL.6020 | 40817697 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117308720 | T2NT DI MALIN-RND MTN#2 52/259 INST GMKS | 43939115 | MALIN-ROUND MTN #2 | 052/259 | ICS | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.57513 | 41.3037 | ETL.6020 | 40872626 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117308814 | T2NT DI MLN-RND MNTN #2 58/287 INST GMKS | 43939115 | MALIN-ROUND MTN #2 | 058/287 | ICS | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.62971 | 41.2366 | ETL.6020 | 40816577 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117308826 | T2 DI MALIN-ROUND MTN#2 52/258 INS GMKS | 43939115 | MALIN-ROUND MTN #2 | 052/258 | ICS | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.573254 | 41.306 | ETL.6020 | 40868957 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117308939 | T2NT DI CRBY SW ST-RD MN 16/130 INS MRKS | 43897848 | CARBERRY SW STA-ROUND MTN | 016/130 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.753191 | 40.8567 | ETL.5410 | 40600949 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117309035 | DI VLY-SRPGS-MRTL#1 12/8 RPR STRW | 43844293 | VALLEY SPRINGS-MARTELL #1 | 012/008 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-120.794106 | 38.3649 | ETL.8240 | 40864905 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Released
117309037 | T2 DI ROUND MT-CTNWD #3 53/474 INST MRKS | 43876249 | ROUND MTN-COTTONWOOD #3 | 053/474 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.200252 | 40.4774 | ETL.5650 | 40762834 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117309564 | T2 DI MORAGA-OAKLAND #1 003/026 RPR FOND |  | MORAGA-OAKLAND #1 | 003/026 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-122.209839 | 37.8166 | ETL.2720 | 40804644 | Foundation/Concrete-Tower | Earth Covered Tower | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 7
117309739 | T2NT DI MALIN-RND MT#2 82/417 INST GMKS | 43939115 | MALIN-ROUND MTN #2 | 082/417 | ICS | F | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.910768 | 40.976 | ETL.6020 | 40816584 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117309977 | T3 DI TRINITY-CTTONWD 20/149B RPR GYWW | 43861284 | TRINITY-COTTONWOOD | 020/149B | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-122.523343 | 40.6191 | ETL.4040 | 42622427 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117310112 | T2 DI MTN GTE JCT-CSCDE 6/78 RPR GYWW | 43758388 | MTN GATE JCT-CASCADE | 006/078 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.334135 | 40.6532 | ETL.7640 | 40876605 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117310115 | T2 DI MTN GTE JCT-CSCDE 6/78 RPL STRW | 31498057 | MTN GATE JCT-CASCADE | 006/078 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.334135 | 40.6532 | ETL.7640 | 40876605 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
117310144 | T3 DI TRINITY-CTTONWD 20/149C RPR GYWW | 43861284 | TRINITY-COTTONWOOD | 020/149C | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-122.523297 | 40.6191 | ETL.4040 | 42622428 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117310301 | T2 DI COTTONWOOD-DLVN#2 64/574 PNT STRT | 44305182 | COTTONWOOD-DELEVAN #2 | 064/574 | ICS | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.268073 | 40.3285 | ETL.4580 | 40760052 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117310380 | T2 DI MALIN-ROND MT #2 78/395A INST GMKS | 43939115 | MALIN-ROUND MTN #2 | 078/395A | ICS | F | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.890182 | 41.0353 | ETL.6020 | 41162685 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117310385 | T2 DI ROUND MT-CTNWD #3 52/464 INST MRKS | 43876249 | ROUND MTN-COTTONWOOD #3 | 052/464 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.192692 | 40.4865 | ETL.5650 | 40759672 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117310388 | DI MTN GATE JCT-CASCADE 001/011 RPR GYWW | 43758388 | MTN GATE JCT-CASCADE | 001/011 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.313793 | 40.7278 | ETL.7640 | 44565309 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117310481 | NT DI MTN GATE JCT-CASC 01/011 INST MRKW | 43758388 | MTN GATE JCT-CASCADE | 001/011 | ICW | F | Pre-2020_(5b) On structure in bucket 5 |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-122.313793 | 40.7278 | ETL.7640 | 44565309 | Marker (i.e. signs)-Wood | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117310488 | T2 DI PIT #7 TAP 003/025 RPR GYWW | 43877044 | PIT #7 TAP | 003/025 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.939086 | 40.827 | ETL.5442 | 44553527 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117310540 | T2 DI PIT #7 TAP 003/025 RPR GYWW | 43877044 | PIT #7 TAP | 003/025 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.939086 | 40.827 | ETL.5442 | 44553737 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117311044 | T2 DI HUMB TRIN 66/1C RPR SPLW | 43729541 | HUMBOLDT-TRINITY | 066/001 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.268289 | 40.7213 | ETL.1820 | 44562793 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2019-08-30
117311046 | T2 DI HUMB TRIN 66/1R RPR GYWW | 43729541 | HUMBOLDT-TRINITY | 066/001 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.268289 | 40.7213 | ETL.1820 | 44563018 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2019-08-30
117311048 | T2 DI HUMB TRIN 66/1R RPR SPLW | 43729541 | HUMBOLDT-TRINITY | 066/001 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.268289 | 40.7213 | ETL.1820 | 44563018 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2019-08-30
117311120 | T2 DI HUMBOLDT-TRINITY 062/000R RPR GYWW | 43729541 | HUMBOLDT-TRINITY | 062/000 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.196663 | 40.7375 | ETL.1820 | 44560520 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
117311123 | T2 DI HUMB TRIN 66/1L RPR GYWW | 43729541 | HUMBOLDT-TRINITY | 066/001 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.268289 | 40.7213 | ETL.1820 | 44562899 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2019-08-30
117311128 | T2 DI HUMBOLDT-TRINITY 062/000C RPR GYWW | 43729541 | HUMBOLDT-TRINITY | 062/000 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.196663 | 40.7375 | ETL.1820 | 44560577 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
117311129 | T2 DI HUMBOLDT-TRINITY 062/000L RPR GYWW | 43729541 | HUMBOLDT-TRINITY | 062/000 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.196663 | 40.7375 | ETL.1820 | 44560488 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
117311210 | T2 DI HUMBOLDT TRINITY 062/000L RPR STRW | 44298744 | HUMBOLDT-TRINITY | 062/000 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.196663 | 40.7375 | ETL.1820 | 44560488 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
117311214 | T2 DI MALIN RND MTN #2 59/295 INST GMKS | 43939115 | MALIN-ROUND MTN #2 | 059/295 | ICS | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.644795 | 41.218 | ETL.6020 | 40759604 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117311217 | T2NT DI MAL RND MT#2 59/296 INST GMKS | 43939115 | MALIN-ROUND MTN #2 | 059/296 | ICS | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.646236 | 41.2162 | ETL.6020 | 40817701 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117311232 | T2 DI BRDGVLLE-CTTNWD 042/339B REPL DAMS | 43862285 | BRIDGEVILLE-COTTONWOOD | 042/339B | ICS | E | Pre-2020_(2) High fire spread TD |  |  |  | TR2 | LATE | North Valley | WSIP | [5 empty] | 2021 - FSR | '-123.064259 | 40.3909 | ETL.1110 | 42603424 | Damper-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117311245 | T2 DI FORT ROSS-GUALALA 048/007 RPL INSW | 31462492 | GUALALA-MONTE RIO | 048/007 | 93H | E | Pre-2020_(4) TD tag on high spread line |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.386039 | 38.7183 | ETL.6980 | 40808309 | Insulator-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Lakeville |  |  | 2019-07-11
117311263 | T2NT DI CTTNWD-PANORMA 001/021 INST MRKW | 43881008 | COTTONWOOD-PANORAMA | 001/021 | ICW | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.26533 | 40.4178 | ETL.1340 | 40804914 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117311333 | T2NT DI CBY SW ST RD MT 000/002 INS MRKS | 43897849 | CARBERRY SW STA-ROUND MTN | R000/002 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.937428 | 40.7929 | ETL.5410 | 40661608 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117311363 | T2 DI CLEAR LAKE-HOPLAND 03/0L RPL POLE | 31471833 | CLEAR LAKE-HOPLAND | 003/000 | 70Y | B | 2020_(0) A and B Tags |  |  |  | TR2 | LATE | North Coast | WSIP | FSRP | [7 empty] | ETL.6390 | 44224591 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville
117313432 | T2 DI FORT ROSS-GUALALA 054/005 RPR SPLW | 43920743 | GUALALA-MONTE RIO | 054/005 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.481105 | 38.7362 | ETL.6980 | 40763641 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  | 2019-07-19
117313464 | T2 DI PIT #7 TAP 003/026L RPL STRW | 31501365 | PIT #7 TAP | 003/026 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.937735 | 40.8259 | ETL.5442 | 44553659 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain
117313466 | T2 DI PIT #7 TAP 003/026C RPL STRW | 31501365 | PIT #7 TAP | 003/026 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.937735 | 40.8259 | ETL.5442 | 44553558 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain
117313501 | T2 DI PIT #7 TAP 003/026 CANCEL |  | PIT #7 TAP | 003/026 | ICW | E | Pre-2020_(5b) On structure in bucket 5 |  |  | CANCEL/CNCL | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.937735 | 40.8259 | ETL.5442 | 44553741 | Marker (i.e. signs)-Wood | Missing | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117313746 | T2 DI LAYTONVILLE-WILLITS 12/3 RPL POLE | 31490917 | LAYTONVILLE-WILLITS | 012/003 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | FSRP | [5 empty] | '-123.42253 | 39.5454 | ETL.8360 | 40666646 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville
117313868 | IGNACIO-ALTO-SAUSLTO #1 13/94 RPLMB STRT | 44310662 | IGNACIO-ALTO-SAUSALITO #1 | 013/094 | ICQ | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | North Coast | Non-WSIP | [6 empty] | '-122.526547 | 37.8773 | ETL.7160 | 40864752 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville
117314157 | T2NT DI TESLA-SALD-MNTCA 25/149 INS MRKW | 43841362 | TESLA-SALADO-MANTECA | 025/149 | ICW | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-121.205785 | 37.4741 | ETL.4000 | 40912754 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 7
117314328 | T2 DI CTTNWD BNTN #2 14/123 GYWW RPR | 43939217 | COTTONWOOD-BENTON #2 | 014/123 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-122.397108 | 40.5581 | ETL.6650 | 44386695 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117314493 | T2 DI CTTNWD BNTN #2 14/123 GYWW RPR | 43939217 | COTTONWOOD-BENTON #2 | 014/123 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-122.397108 | 40.5581 | ETL.6650 | 44386696 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117314764 | T2NT DI PIT#3-PIT#1 3/30 INST MRKS | 43877631 | PIT #3-PIT #1 | 003/030 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.554544 | 40.9589 | ETL.5400 | 40591617 | Marker (i.e. signs)-Steel | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117314787 | DI NEWARK-LIVERMORE 16/106 GYWW RPR | 43877617 | NEWARK-LIVERMORE | 016/106 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | Central | WSIP | FSRP | [5 empty] | '-121.78301 | 37.6422 | ETL.7660 | 40599748 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Bay |  | Y - 8
117314860 | T2 DI PTTSBRG-CLYTN #1 004/25B BNT MMBR | 44230505 | PITTSBURG-CLAYTON #1 | 004/025B | ICQ | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-121.907547 | 37.9829 | ETL.3280 | 40739984 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog Multi
117314900 | T2 DI HMBLDT-BRIDGEVILL 113/7R RPL STRW | 31471941 | HUMBOLDT-BRIDGEVILLE | 113/007 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | FSRP | [7 empty] | ETL.1810 | 44322726 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC erdy srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2019-08-27
117315075 | T2 DI DRUM-SUMMIT #1 019/222L RPL STRW | 31453474 | DRUM-SUMMIT #1 | 019/222 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.465171 | 39.3191 | ETL.1440 | 44764253 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
117315989 | T2 DI CTRA CSTA-LS PSTS 11/74 RMV NEST | 43877325 | CONTRA COSTA-LAS POSITAS | 011/074 | ICS | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-121.720782 | 37.8371 | ETL.4510 | 40659760 | Structure-Steel | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  |  | LVW
117316169 | T2 DI CONTRA CST LSPOSTS 10/72 RMV STRS | 43841164 | CONTRA COSTA-LAS POSITAS | 010/072 | ICS | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-121.727463 | 37.8418 | ETL.4510 | 40593917 | Structure-Steel | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - 6
117316218 | T2 DI CASCDE-BNTN-DSCHTS 8/176 INS MRKW | 43690811 | CASCADE-BENTON-DESCHUTES | A008/176 | ICW | F | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.25055 | 40.5569 | ETL.6310 | 41177755 | Marker (i.e. signs)-Wood | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117316554 | T2NT DI MLIN-RND MTN #2 53/263 INST GMKS | 43939115 | MALIN-ROUND MTN #2 | 053/263 | ICS | F | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.582904 | 41.2942 | ETL.6020 | 40657477 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117316569 | T2 DI HUMBOLDT-BRIDGEVILL 99/6R RPL POLE | 31497841 | HUMBOLDT-BRIDGEVILLE | 099/006 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [8 empty] | ETL.1810 | 44322424 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2019-07-10
117317137 | T2 DI HAAS-WOODCHUCK 000/015 RPR GYWW | 43825054 | HAAS-WOODCHUCK | 000/015 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-119.017879 | 36.9341 | ETL.8730 | 42717460 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Fresno |  | Y - 9
117317443 | T2 DI PORT COSTA BRICK TAP 0/4B STRW RPR | 44621448 | PORT COSTA BRICK TAP | 000/004B | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.16845 | 38.024 | ETL.6371 | 41101663 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Bay
117317455 | T2 DI MTN GTE JCT-CSCD 01/10L RPR GYWW | 43758388 | MTN GATE JCT-CASCADE | 001/010 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.313451 | 40.7289 | ETL.7640 | 44566779 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117317456 | T2NT DI MTN GTE JCT-CSCD 1/10L INST MRKW | 43758388 | MTN GATE JCT-CASCADE | 001/010 | ICW | F | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.313451 | 40.7289 | ETL.7640 | 44566779 | Marker (i.e. signs)-Wood | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117317641 | T2 DI MTN GTE JCT-CSCD 01/10R RPR GYWW | 43758388 | MTN GATE JCT-CASCADE | 001/010 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.313451 | 40.7289 | ETL.7640 | 44566780 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117317644 | T2NT DI MTN GTE JCT-CSCD 1/10R INST MRKW | 43758388 | MTN GATE JCT-CASCADE | 001/010 | ICW | F | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.313451 | 40.7289 | ETL.7640 | 44566780 | Marker (i.e. signs)-Wood | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117317678 | T2 DI CBRY SW ST-RND MTN 25/206 INS MRKS | 43897848 | CARBERRY SW STA-ROUND MTN | 025/206 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.907497 | 40.8001 | ETL.5410 | 40820237 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117318366 | T2 DI TULE-SPRINGVILLE 18/012 GDWSH INSU | 43844570 | TULE-SPRINGVILLE | 018/012 | ICD | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-118.826526 | 36.1185 | ETL.9040 | 40691214 | Insulator | Contaminated | Ground Wash | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 622 | Midway |  | Y - 23
117318533 | T2 DI TULE-SPRINGVILLE 21/014 RPR STRW | 43844575 | TULE-SPRINGVILLE | 021/014 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-118.786832 | 36.1344 | ETL.9040 | 40766145 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Midway |  | Y - 23
117318617 | T2 DI MTN GATE JCT-CASCAD 2/28R INST GMK | 43758388 | MTN GATE JCT-CASCADE | 002/028 | ICW | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.321548 | 40.7046 | ETL.7640 | 44565551 | Guy Wire Mark /Indic-Wood | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117318671 | T2 DI TULE-SPRINGVILLE 22/018 RPL STRW | 31453078 | TULE-SPRINGVILLE | 022/018 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-118.769833 | 36.1396 | ETL.9040 | 40873924 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Midway |  | Y - 23
117318673 | T2 DI TULE-SPRINGVILLE 24/006 INST GMKW | 43844571 | TULE-SPRINGVILLE | 024/006 | ICW | F | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-118.748093 | 36.1519 | ETL.9040 | 40823415 | Guy Wire Mark /Indic-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Midway |  | Y - 23 | USFS
117318686 | T2NT DI RND MTN-CTTNWD#3 27/222 INS MRKS | 43876249 | ROUND MTN-COTTONWOOD #3 | 027/222 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.939278 | 40.7909 | ETL.5650 | 40668261 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117318687 | T2NT DI RD MT-CTNWD#3 058/532 INST MRKS | 43876249 | ROUND MTN-COTTONWOOD #3 | 058/532 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.257482 | 40.4081 | ETL.5650 | 40677349 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117318819 | T2 DI MTN GATE JCT-CASCAD 2/28L INST GMK | 43758388 | MTN GATE JCT-CASCADE | 002/028 | ICW | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.321548 | 40.7046 | ETL.7640 | 44565534 | Guy Wire Mark /Indic-Wood | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117319213 | T2NT DI RND MT-CTNWD#2 35/295 INST MRKS | 43876311 | ROUND MTN-COTTONWOOD #2 | 035/295 | ICS | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.174218 | 40.5364 | ETL.5640 | 40756677 | Marker (i.e. signs)-Steel | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117319586 | T2NT DI RD MT-CTNWD#3 052/471 INST MRKS | 43876249 | ROUND MTN-COTTONWOOD #3 | 052/471 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.197781 | 40.4803 | ETL.5650 | 40595104 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117319990 | T2 DI DRUM-SUMMIT #2 11/132L CANCEL | 43900300 | DRUM-SUMMIT #2 | 011/132 | ICW | E | Pre-2020_(1b) Lines with special commitments |  |  | CANCEL/CNCL | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.59569 | 39.3304 | ETL.1450 | 44559003 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117321309 | T2 DI COLEMAN-SO 5/119B GYWW RPR | 43939301 | COLEMAN-SOUTH | 005/119B | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.974453 | 40.4051 | ETL.6450 | 42578774 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117321407 | T2 HUMBOLDT-TRINITY 057/003B RMV DEBRIS | 43729541 | HUMBOLDT-TRINITY | 057/003B | ICW | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-123.124049 | 40.7716 | ETL.1820 | 40653711 | Structure-Wood | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2019-08-30
117321470 | T2 DI COLEMAN-SO 5/119B GMKW INST | 43939303 | COLEMAN-SOUTH | 005/119B | ICW | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.974453 | 40.4051 | ETL.6450 | 42578774 | Guy Wire Mark /Indic-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117321471 | T2 DI COLEMAN-SO 5/119A GYWW RPR | 43939301 | COLEMAN-SOUTH | 005/119A | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.974428 | 40.4051 | ETL.6450 | 40825097 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117321472 | T2 DI COLEMAN-SO 5/119A GMKW INST | 43939303 | COLEMAN-SOUTH | 005/119A | ICW | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.974428 | 40.4051 | ETL.6450 | 40825097 | Guy Wire Mark /Indic-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117321473 | T2 DI COLEMAN-SO 5/119C GYWW RPR | 43939301 | COLEMAN-SOUTH | 005/119C | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.974473 | 40.4051 | ETL.6450 | 42578775 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117321474 | T2 DI COLEMAN-SO 5/119C GMKW INST | 43939301 | COLEMAN-SOUTH | 005/119C | ICW | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.974473 | 40.4051 | ETL.6450 | 42578775 | Guy Wire Mark /Indic-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117321669 | T2 DI MT GATE JCT-CCD 3/30L RPR STRW | 43758388 | MTN GATE JCT-CASCADE | 003/030 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.322462 | 40.7021 | ETL.7640 | 44565325 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117321800 | T2NT DI MT GATE JCT-CSCD 3/30L INST MRKW | 43758388 | MTN GATE JCT-CASCADE | 003/030 | ICW | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.322462 | 40.7021 | ETL.7640 | 44565325 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117322960 | T2NT DI PIT #3-PIT #1 8/71 ANTI CLB GRD | 43877628 | PIT #3-PIT #1 | 008/071 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.633315 | 40.9191 | ETL.5400 | 40576227 | Hardware-Tower | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
117323362 | T2 DI HUMBOLDT-TRINITY 63/3 RPR GYWW | 43729541 | HUMBOLDT-TRINITY | 063/003 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.220224 | 40.7425 | ETL.1820 | 44562915 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
117323364 | T2 DI HUMBOLDT-TRINITY 63/3 RPR GYWW | 43729541 | HUMBOLDT-TRINITY | 063/003 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.220224 | 40.7425 | ETL.1820 | 44562809 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
117323365 | T2NT DI HUMBOLDT-TRINITY 63/3L INST MRKW | 43729541 | HUMBOLDT-TRINITY | 063/003 | ICW | F | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.220224 | 40.7425 | ETL.1820 | 44562915 | Marker (i.e. signs)-Wood | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
117323632 | T2NT DI MALIN-RND MT#2 78/396 INST GMKS | 43939115 | MALIN-ROUND MTN #2 | 078/396 | ICS | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.890323 | 41.0336 | ETL.6020 | 40820539 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117323710 | DI LAKEVILLE-IGNACIO #1 IG2/11 RMV NEST | 43919486 | LAKEVILLE-IGNACIO #1 | IG002/011 | ICS | F | Pre-2020_(9a) Other ignition related |  |  |  |  | LATE | North Coast | WSIP | FSRP | [5 empty] | '-122.522675 | 38.1054 | ETL.4940 | 40593209 | Structure-Steel | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville |  |  | 2019-08-26
117323713 | T2 DI RND MTN-CTTNWD #3 R1/16R RPR STRW | 43946912 | ROUND MTN-COTTONWOOD #3 | R001/016 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.935935 | 40.7985 | ETL.5650 | 44765642 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117326078 | DI CORDELIA #2 TAP 003/066 RPR GYWW | 43852763 | CORDELIA #2 TAP | 003/066 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-122.152884 | 38.2504 | ETL.8184 | 40612471 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117326087 | T2 DI PIT #7 TAP 2/19 RPR GYWW | 43877044 | PIT #7 TAP | 002/019 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.9531 | 40.8316 | ETL.5442 | 44553526 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117326406 | T2NT DI CRDLIA #1 TAP 004/094A INST GMKW | 43852387 | CORDELIA #1 TAP | 004/094A | ICW | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.190299 | 38.2383 | ETL.8182 | 40577179 | Guy Wire Mark /Indic-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117326464 | T2NT DI CRDLIA #1 TAP 004/094C INST GMKW | 43852387 | CORDELIA #1 TAP | 004/094C | ICW | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.190355 | 38.2383 | ETL.8182 | 40595181 | Guy Wire Mark /Indic-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117327313 | EI VALLEY SPRINGS-MARTELL #12/8 RPR GYWW | 43853791 | VALLEY SPRINGS-MARTELL #1 | 012/008 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-120.794106 | 38.3649 | ETL.8240 | 40864905 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Released
117327674 | T2 DI KRCKHF #1-KRCKHF #2 0/006 RPR FOND | 44571489 | KERCKHOFF #1-KERCKHOFF #2 | 000/006 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-119.553113 | 37.084 | ETL.1880 | 40807000 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  |  | BLM
117328150 | T2 DI PIT#5-RND MTN#2 008/083R RPL HRDD | 43877097 | PIT #5-ROUND MTN #2 | 008/083 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.929556 | 40.8715 | ETL.5430 | 44561331 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117328688 | T2NT DI SLT SPG-TGR CRK 006/051 INS MRKS | 43842276 | SALT SPRINGS-TIGER CREEK | 006/051 | ICS | F | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.314895 | 38.4779 | ETL.3500 | 40579797 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Victor |  | Y - Prog USFS
117329198 | DI BELL-PLACER 2/22 INST MRKS | 43910337 | BELL-PLACER | 002/022 | ICS | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-121.068124 | 38.9272 | ETL.4395 | 40759929 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes
117329547 | T2 DI PIT#5-RND MTN#2 008/083R RPR GYWW | 43877097 | PIT #5-ROUND MTN #2 | 008/083 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.929556 | 40.8715 | ETL.5430 | 44561331 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117329674 | T2 DI DELTA-MTN GATE JCT 01/29 RPR GYWW | 43866629 | DELTA-MOUNTAIN GATE JCT | 001/029 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.402848 | 40.9194 | ETL.6750 | 40828038 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117329677 | T2 DI DELTA-MTN GATE JCT 01/29 RPR STRW | 43866629 | DELTA-MOUNTAIN GATE JCT | 001/029 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.402848 | 40.9194 | ETL.6750 | 40828038 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117329710 | T2 DI DELTA-MTN GATE JCT 01/29 INST MRKW | 43866629 | DELTA-MOUNTAIN GATE JCT | 001/029 | ICW | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.402848 | 40.9194 | ETL.6750 | 40828038 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117329817 | T2NT DI COTTONWOOD#1 7/51 INS MRKS | 44155926 | COTTONWOOD #1 | 007/051 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.267565 | 40.2896 | ETL.6620 | 40910992 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117329886 | DI TRINITY-COTTONWOOD 11/87L RPL STRW | 31455647 | TRINITY-COTTONWOOD | 011/087 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-122.420759 | 40.5099 | ETL.4040 | 44558367 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
117329995 | STOCKTON ""A""-WEBER #2 A4/115 RPLC POLE | 31454638 | STOCKTON "A"-WEBER #2+ (NO FLY) | A004/115 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | Central | Non-WSIP | FSRP | [5 empty] | '-121.279372 | 37.9699 | ETL.8130 | 40754576 | Structure-Wood | Rotten | Replace | erdy ADER | ADER | With ADE for Review | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 2
117330136 | T2 DI STNSLS-MLNS SS-MNCA 6/041 RPR STRT | 43841828 | STANISLAUS-MELONES SS-MANTECA #1+ | 006/041 | ICQ | F | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.475973 | 38.0901 | ETL.3830 | 40589673 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - 9
117330211 | LOCKEFORD #1 8/146 REPLACE POLE | 31454621 | LOCKEFORD #1 | 008/146 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | Central | Non-WSIP | FSRP | [5 empty] | '-121.252301 | 38.0373 | ETL.9461 | 41185187 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Released
117330213 | STOCKTON """"A""""-WEBER #3 1/31 RPLC POLE | 31455757 | STOCKTON "A"-WEBER #3+ (NO FLY) | 001/031 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | Central | Non-WSIP | [6 empty] | '-121.27324 | 37.9473 | ETL.8140 | 40864347 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | None
117330277 | T2 DI SALT SPRINGS-TGR CRK 6/55 CANCEL | 43842265 | SALT SPRINGS-TIGER CREEK | 006/055 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  | CANCEL/CNCL | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.327523 | 38.4769 | ETL.3500 | 40745438 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - 13
117330278 | T2NT DI SALT SPGS-TGR CRK 6/55 INST MRKS | 43842276 | SALT SPRINGS-TIGER CREEK | 006/055 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.327523 | 38.4769 | ETL.3500 | 40745438 | Marker (i.e. signs)-Steel | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Victor |  | Y - Prog USFS
117330514 | T2 DI TULE-SPRINGVILLE 23/14 INST MRKW | 43844569 | TULE-SPRINGVILLE | 023/014 | ICW | F | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-118.757135 | 36.1463 | ETL.9040 | 40766149 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Midway |  | Y - 23
117330601 | SALINAS-FIRESTONE #2 A2/99 RPLC POLE | 31455749 | SALINAS-FIRESTONE #2 (NO FLY) | A002/099 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | [6 empty] | '-121.625753 | 36.6548 | ETL.7910 | 40754306 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Moss Landing |  | Y - 8
117330602 | SALINAS-FIRESTONE#2 A2/98 REPLACE POLE | 31455749 | SALINAS-FIRESTONE #2 (NO FLY) | A002/098 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | [6 empty] | '-121.625365 | 36.6552 | ETL.7910 | 40754358 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Moss Landing |  | Y - 8
117330796 | T2 DI COLEMAN-SOUTH 8/166 RPR SPLW | 43939301 | COLEMAN-SOUTH | 008/166 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.018229 | 40.4031 | ETL.6450 | 40634876 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117330882 | T2 DI MTN GT-CSCDE 1/9R RPR GYWW | 43758388 | MTN GATE JCT-CASCADE | 001/009 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.312654 | 40.7312 | ETL.7640 | 44565591 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117330883 | T2NT DI MTN GT-CSCDE 1/9R INST MRKW | 43758388 | MTN GATE JCT-CASCADE | 001/009 | ICW | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.312654 | 40.7312 | ETL.7640 | 44565591 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117331605 | T2NT DI DRUM-SUMMIT#1 024/290A INST MRKW | 43910105 | DRUM-SUMMIT #1 | 024/290A | ICW | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.370402 | 39.3105 | ETL.1440 | 40814122 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117333720 | T2 DI BALCH-SANGER 04/26 INST HRDS | 43845834 | BALCH-SANGER | 004/026 | ICS | E | Pre-2020_(5b) On structure in bucket 5 | Superintendent Approved work efficiency |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-119.142525 | 36.8801 | ETL.1050 | 40807127 | Hardware-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Fresno |  | Y - 16
117334451 | T2 DI MTN GTE-CSCSDE 1/9 RPR GYWW | 43758388 | MTN GATE JCT-CASCADE | 001/009 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.312654 | 40.7312 | ETL.7640 | 44565564 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117334452 | T2NT DI MTN GTE-CSCSDE 1/9 INST MRKW | 43758388 | MTN GATE JCT-CASCADE | 001/009 | ICW | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.312654 | 40.7312 | ETL.7640 | 44565564 | Marker (i.e. signs)-Wood | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117334520 | T2NT DI CTTNWD-PNRMA 0/15 INST MRKW | 43881008 | COTTONWOOD-PANORAMA | 000/015 | ICW | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.267411 | 40.4131 | ETL.1340 | 40600908 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117335262 | T2NT DI MLN RND MTN #2 60/299 INST GMKS | 43939115 | MALIN-ROUND MTN #2 | 060/299 | ICS | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.652215 | 41.2089 | ETL.6020 | 40870331 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117335349 | T2 DI DRUM-SUMMIT#1 25/299A RPL STRW | 31498145 | DRUM-SUMMIT #1 | 025/299A | 70Y | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.355473 | 39.3094 | ETL.1440 | 40756925 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS erdy | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Sacramento |  |  | Yes
117335542 | T2 DI MALIN-ROUND MTN #2 54/270 INST GMK | 43939115 | MALIN-ROUND MTN #2 | 054/270 | ICS | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.59706 | 41.2768 | ETL.6020 | 40605717 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117335547 | T2 DI MALIN-ROUND MTN #2 59/293 INST GMK | 43939115 | MALIN-ROUND MTN #2 | 059/293 | ICS | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.640829 | 41.2229 | ETL.6020 | 40657482 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117335650 | SALINAS-FIRESTONE #1 2/78 REPLACE POLE | 31454629 | SALINAS-FIRESTONE #1 (NO FLY) | 002/078 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | [6 empty] | '-121.630179 | 36.6547 | ETL.7900 | 40826029 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Moss Landing |  | Y - 4
117335952 | LOCKEFORD-LODI #3 2/48 REPLACE POLE | 31454622 | LOCKEFORD-LODI #3 | 002/048 | 70Y | F | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | Central | Non-WSIP | FSRP | [5 empty] | '-121.201095 | 38.1015 | ETL.7450 | 40666094 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 2
117336108 | T2 DI EL DRDO-MSSRI FLT#1 7/50 RPL SPLS | 43749467 | ELDORADO-MISSOURI FLAT #1 | 007/050 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.732031 | 38.7584 | ETL.1530 | 40581937 | Splice-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes
117336234 | T2 DI WEIMAR-HALSEY 2/43 RPL STRW | 31498141 | WEIMAR-HALSEY | 002/043 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.998442 | 39.0072 | ETL.8340 | 40656021 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
117336367 | T2 DI TULE-SPRINGVILLE 22/12 RPL STRW | 31453078 | TULE-SPRINGVILLE | 022/012 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-118.773194 | 36.1357 | ETL.9040 | 40691226 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Midway |  | Y - 23
117337090 | T2 DI CTTNWD BNTN 06/65 RPR STRW | 43939217 | COTTONWOOD-BENTON #2 | 006/065 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.356988 | 40.47 | ETL.6650 | 44561405 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117337909 | GREEN VALLEY-LLAGAS :010/070 RPR STRT | 44571488 | GREEN VALLEY-LLAGAS | :010/070 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-121.651331 | 37.1038 | ETL.1720 | 40589047 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Moss Landing
117338427 | T2 DI DRUM-SUMMIT#1 10/116 RPL STRW | 31508705 | DRUM-SUMMIT #1 | 010/116 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.615826 | 39.3218 | ETL.1440 | 44765214 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
117338469 | T2 DI DRUM-SUMMIT#1 10/116 RPL STRW | 31508705 | DRUM-SUMMIT #1 | 010/116 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.615826 | 39.3218 | ETL.1440 | 44765215 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
117338870 | T2 DI COLEMAN-SOUTH 10/221 RPR GYWW | 43939303 | COLEMAN-SOUTH | 010/221 | ICW | E | Pre-2020_(2) High fire spread TD |  |  |  | TR2 | LATE | North Valley | WSIP | [5 empty] | 2021 - FSR | '-122.069819 | 40.4035 | ETL.6450 | 40759353 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117339944 | T2 DI PIT#7 TAP 002/024 (R) RPL STRW | 31432828 | PIT #7 TAP | 002/024 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.94041 | 40.8282 | ETL.5442 | 44553735 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain
117340029 | T2 DI COTTONWOOD-BENTN #2 6/058 RPR POLE | 43939217 | COTTONWOOD-BENTON #2 | 006/058 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-122.346937 | 40.4627 | ETL.6650 | 44561230 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117340075 | T2 DI HAT CRK#-WSTWD 035/673 RPL STRW | 31456189 | HAT CREEK #1-WESTWOOD | 035/673 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.083455 | 40.5793 | ETL.7030 | 40676386 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain
117340079 | T2NT DI MALIN-RND MT #2 50/252 INST GMKS | 43939115 | MALIN-ROUND MTN #2 | 050/252 | ICS | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.561061 | 41.321 | ETL.6020 | 40677650 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117340173 | T2 DI COTTONWD-BENTN #2 6/58R INST MRKW | 43939217 | COTTONWOOD-BENTON #2 | 006/058 | ICW | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.346937 | 40.4627 | ETL.6650 | 44561230 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117340176 | T2 DI COTTONWD-BENTN #2 6/58L INST MRKW | 43939217 | COTTONWOOD-BENTON #2 | 006/058 | ICW | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.346937 | 40.4627 | ETL.6650 | 44561250 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117340377 | T2 DI PIT#1-COTTONWOOD 24/194 PNT STRS | 44157589 | PIT #1-COTTONWOOD | 024/194 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.875518 | 40.8083 | ETL.5390 | 40759731 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117340600 | T2 DI DRUM-SMMIT#1 022/264 RPL POLE | 31498145 | DRUM-SUMMIT #1 | 022/264 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.410339 | 39.3111 | ETL.1440 | 44767646 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS erdy | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
117340618 | T2 DI PIT #1-COTTONWOOD 9/76 RMV NEST | 43735854 | PIT #1-COTTONWOOD | 009/076 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.642918 | 40.914 | ETL.5390 | 40817594 | Structure-Steel | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117340705 | T2 PARADISE-TABLE MTN 6/53 RPR CONS | 43727174 | PARADISE-TABLE MTN | 006/053 | ICS | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-121.539917 | 39.5412 | ETL.4316 | 40691000 | Conductor-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117340968 | T2 DI RND MTN-CTTNWD#2 39/317 INS MRKS | 43876311 | ROUND MTN-COTTONWOOD #2 | 039/317 | ICS | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.20234 | 40.4885 | ETL.5640 | 40813970 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117341575 | T2 DI MTN GATE JCT-CASCADE 1/10 RMV IDLE | 31475739 | MTN GATE JCT-CASCADE | 001/010 | 93J | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.313451 | 40.7289 | ETL.7640 | 44566779 | Structure-Wood | Idle | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 673 | Table Mountain
117341576 | T2 DI MTN GATE JCT-CASCADE 1/10 RMV IDLE | 31475739 | MTN GATE JCT-CASCADE | 001/010 | 93J | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.313451 | 40.7289 | ETL.7640 | 44566780 | Structure-Wood | Idle | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 673 | Table Mountain
117341592 | T2 DI MTN GATE JCT-CASCDE 3/30R RPR STRW | 43758388 | MTN GATE JCT-CASCADE | 003/030 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.322462 | 40.7021 | ETL.7640 | 44565396 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117341595 | T2NT DI MTN GAT JCT-CASC 3/30R INST MRKW | 43758388 | MTN GATE JCT-CASCADE | 003/030 | ICW | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.322462 | 40.7021 | ETL.7640 | 44565396 | Marker (i.e. signs)-Wood | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117341713 | T2 EI BRDGEVLLE-COTTONWD 13/124R RPL PL | 31451465 | BRIDGEVILLE-COTTONWOOD | 013/124 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.520412 | 40.3946 | ETL.1110 | 44424062 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
117341936 | T2 DI TRINITY-MPE CRK 015/002R RPR GYWW | 43749708 | TRINITY-MAPLE CREEK | 015/002 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.177053 | 40.7465 | ETL.8170 | 44769593 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
117341940 | T2 DI PIT #7 TAP 001/012C RPR STRW | 43877044 | PIT #7 TAP | 001/012C | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.971488 | 40.836 | ETL.5442 | 40690231 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117342082 | T2 EI HUMBOLDT-TRINITY 63/03R INST MRKW | 43729541 | HUMBOLDT-TRINITY | 063/003 | ICW | F | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.220224 | 40.7425 | ETL.1820 | 44562809 | Marker (i.e. signs)-Wood | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
117342185 | T2 EI HUMBOLDT-TRINITY 66/01 CANCEL | 43729541 | HUMBOLDT-TRINITY | 066/001 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  | CANCEL/CNCL |  | LATE | North Coast | WSIP | [6 empty] | '-123.268289 | 40.7213 | ETL.1820 | 44562899 | Conductor-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2019-08-09
117342340 | T2 EI HUMBOLDT-TRNTY 89/9L RMV POLE BUTT | 43729541 | HUMBOLDT-TRINITY | 089/009 | ICW | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | WSIP | FSRP | [5 empty] | '-123.678463 | 40.7322 | ETL.1820 | 44562758 | Structure-Wood | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2019-08-30
117342342 | T2 EI HUMBOLDT-TRNTY 89/9R RMV POLE BUTT | 43729541 | HUMBOLDT-TRINITY | 089/009 | ICW | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | WSIP | FSRP | [5 empty] | '-123.678463 | 40.7322 | ETL.1820 | 44562896 | Structure-Wood | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2019-08-30
117342394 | T2 EI HUMBOLDT-BRIDGVLL 113/07L RPL STRW | 31471941 | HUMBOLDT-BRIDGEVILLE | 113/007 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | FSRP | [7 empty] | ETL.1810 | 44322725 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC erdy srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2019-08-27
117342959 | T2 DI LAYTONVILLE-WILLITS 010/4 RPL STRW | 31469638 | LAYTONVILLE-WILLITS | 010/004 | 70Y | F | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | FSRP | [5 empty] | '-123.401411 | 39.5293 | ETL.8360 | 40769335 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville
117343103 | T2 DI TULE-SPRINGVILLE 013/006 RPR SPLW | 43844707 | TULE-SPRINGVILLE | 013/006 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-118.910839 | 36.1097 | ETL.9040 | 40808056 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Midway |  | Y - 23
117343428 | T2 DI PARADISE-TBL MTN 24/182R RPL STRW | 31453760 | PARADISE-TABLE MTN | 024/182 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [8 empty] | ETL.4316 | 44383236 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
117343575 | T2 DI PIT #5-ROUND MTN #2 2/26R RPL STRW | 31495386 | PIT #5-ROUND MTN #2 | 002/026 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.951078 | 40.9569 | ETL.5430 | 44561410 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
117343698 | T2 DI PIT #5-ROUND MTN #2 2/26L RPL STRW | 31495386 | PIT #5-ROUND MTN #2 | 002/026 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.951078 | 40.9569 | ETL.5430 | 44561296 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
117344386 | T2NT DI CRBY SW S-RD MT 16/129 INST MRKS | 43897848 | CARBERRY SW STA-ROUND MTN | 016/129 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.752192 | 40.858 | ETL.5410 | 40862817 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117344395 | T2 DI DIABLO-MIDWAY 036/145 INST HRDT | 43756121 | DIABLO-MIDWAY #2 | 036/145 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | South | WSIP | FSRP |  |  |  | Clearance Delayed | Diablo imposed clearance constraintsk; tag scheduled for 9/23-10/5 | '-120.232126 | 35.174 | ETL.5970 | 40760791 | Hardware-Tower | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Pismo Beach |  | Y - 19
117344568 | T2 DI TULE-SPRINGVILLE 17/14 RPR STRW | 43844627 | TULE-SPRINGVILLE | 017/014 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-118.836407 | 36.1122 | ETL.9040 | 40749733 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Midway |  | Y - 23
117344627 | T2 DI TULE-SPRINGVILLE 21/12 RPR POLE | 43844625 | TULE-SPRINGVILLE | 021/012 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-118.787997 | 36.1354 | ETL.9040 | 40690993 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Midway |  | Y - 23
117344649 | T2 DI TULE-SPRINGVILLE 21/12 RPR GYWW | 43844623 | TULE-SPRINGVILLE | 021/012 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-118.787997 | 36.1354 | ETL.9040 | 40690993 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Midway |  | Y - 23
117344994 | T2 DI MALIN-RND MTN#2 048/238 INST GMKS | 43939115 | MALIN-ROUND MTN #2 | 048/238 | ICS | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.533307 | 41.3551 | ETL.6020 | 40868953 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117345096 | T2 DI KONOCTI-MIDDLETOWN 016/013 RPR STR | 43919877 | KONOCTI-MIDDLETOWN | 016/013 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.573239 | 38.8077 | ETL.6380 | 40650686 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  | 2019-07-26
117345295 | T2 DI TESLA-LOS BANOS #1 26/120 RPR GYWS | 43844592 | TESLA-LOS BANOS #1 | 026/120 | ICS | E | Pre-2020_(5) TD tag on other lines |  |  | Tower guy | TR2 | LATE | Central | WSIP | [6 empty] | '-121.203623 | 37.4642 | ETL.6100 | 40592674 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Victor |  | Y - Prog Multi
117345326 | T2 DI MALIN-ROUND MTN#2 47/234 INST GMKS | 43939115 | MALIN-ROUND MTN #2 | 047/234 | ICS | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.525918 | 41.3641 | ETL.6020 | 40759851 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117345328 | T2 DI RND MTN-CTTNWD#3 47/408 RPL INSS | 31454792 | ROUND MTN-COTTONWOOD #3 | 047/408 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.140197 | 40.5499 | ETL.5650 | 40886136 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  | Yes
117345333 | EI IGNACIO-SBRNTE IG001/006 RPL DAMS | 43919486 | IGNACIO-SOBRANTE | IG001/006 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | North Coast | WSIP | [6 empty] | '-122.5158216 | 38.1175 | ETL.4920 | 44652090 | Damper-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville |  |  | 2019-08-26
117345656 | T2 CLAY-MARTEL - 60 kV_018/264 RPR INSL | 43846569 | CLAY-MARTEL | 018/264 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | Non-WSIP | [6 empty] | '-120.917603 | 38.341 | ETL.8250 | 40577086 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - 33
117345947 | T2 DI MALIN-ROUND MTN#2 77/392 INST GMKS | 43939115 | MALIN-ROUND MTN #2 | 077/392 | ICS | F | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.884255 | 41.0417 | ETL.6020 | 40682646 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117346139 | T2 DI MALIN-RND MTN#2 048/241 INST GMKS | 43939115 | MALIN-ROUND MTN #2 | 048/241 | ICS | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.539425 | 41.3476 | ETL.6020 | 40592574 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117346177 | T2 DI MALIN-ROUND MTN#2 78/395 INST GMKS | 43939115 | MALIN-ROUND MTN #2 | 078/395 | ICS | F | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.890067 | 41.0353 | ETL.6020 | 40759612 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117346220 | T2 DI MALIN-ROUND MTN#2 74/377 INST GMKS | 43939115 | MALIN-ROUND MTN #2 | 074/377 | ICS | F | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.843971 | 41.0664 | ETL.6020 | 40819384 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117346574 | T2 DI DRUM SMMT#1 020/024A RPL STRW | 31453474 | DRUM-SUMMIT #1 | 020/243A | 70Y | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.435004 | 39.3211 | ETL.1440 | 40595349 | Structure-Wood | Rotten | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
117347192 | T2 DI MALIN-RND MTN#2 49/244 INS GMKS | 43939115 | MALIN-ROUND MTN #2 | 049/244 | ICS | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.545267 | 41.3404 | ETL.6020 | 40759853 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117347194 | T2 DI PIT#7 TAP 001/011 RPR INSW | 43877044 | PIT #7 TAP | 001/011 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.972763 | 40.8367 | ETL.5442 | 44553089 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117347644 | T2 DI TUL SPVL 23/8 RPL STRW | 31453078 | TULE-SPRINGVILLE | 023/008 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-118.7633 | 36.1445 | ETL.9040 | 40873956 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Midway |  | Y - 23
117347854 | T2 DI MALIN-RND MTN #2 50/249 INST GMKS | 43939115 | MALIN-ROUND MTN #2 | 050/249 | ICS | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.554875 | 41.3286 | ETL.6020 | 40868275 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117348005 | T2NT DI DRUM-SUMMIT #1 20/237R INST MRKW | 43910108 | DRUM-SUMMIT #1 | 020/237 | ICW | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.443387 | 39.319 | ETL.1440 | 44762484 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117348917 | T2 DI RND MTN-CTTNWD #2 39/319 INST MRKS | 43876311 | ROUND MTN-COTTONWOOD #2 | 039/319 | ICS | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.203908 | 40.4845 | ETL.5640 | 40865864 | Marker (i.e. signs)-Steel | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117349323 | T2 DI MALIN-RND MTN #2 048/240 INST GMKS | 43939115 | MALIN-ROUND MTN #2 | 048/240 | ICS | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.537312 | 41.3501 | ETL.6020 | 40605573 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117349651 | T2 DI MALIN-RND MTN #2 50/250 GMKS INSTL | 43939115 | MALIN-ROUND MTN #2 | 050/250 | ICS | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.557085 | 41.3259 | ETL.6020 | 40605576 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117362642 | T2 DI HUMBOLDT-TRINITY 57/7R RPR GYWW | 43729541 | HUMBOLDT-TRINITY | 057/007 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.135291 | 40.7676 | ETL.1820 | 44560508 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
117362643 | T2 DI HUMBOLDT-TRINITY 57/7C RPR GYWW | 43729541 | HUMBOLDT-TRINITY | 057/007 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.135291 | 40.7676 | ETL.1820 | 44560630 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
117362644 | T2 DI HUMBOLDT-TRINITY 57/7L RPR GYWW | 43729541 | HUMBOLDT-TRINITY | 057/007 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.135291 | 40.7676 | ETL.1820 | 44560664 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
117362647 | T2 DI RND MTN-CTTNWD 3 38/333 INSTL MRKS | 43876249 | ROUND MTN-COTTONWOOD #3 | 038/333 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.052068 | 40.6559 | ETL.5650 | 40656723 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117363311 | T3NT DI DRUM-HIGGINS 5/54 REPAINT | 43738143 | DRUM-HIGGINS | 005/054 | ICS | E | Pre-2020_(9a) Other ignition related |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.838345 | 39.2112 | ETL.4393 | 40751895 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento
117363371 | T2 DI STNSLAUS-MANTECA #2 7/042 BENT MBR | 43842120 | STANISLAUS-MANTECA #2 | 007/042 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.481849 | 38.0867 | ETL.3820 | 40656228 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - Prog Multi
117363426 | T2 EI TGR CRK-VLLY SPRNGS 10/80 PNT STRS | 43844598 | TIGER CREEK-VALLEY SPRINGS | 010/080 | ICS | E | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.641077 | 38.372 | ETL.5790 | 40581561 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - Prog Multi
117363787 | T2 DI CRBRY SW ST-RD MT 24/194 PAIN STRS | 43897848 | CARBERRY SW STA-ROUND MTN | 024/194 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.875352 | 40.8086 | ETL.5410 | 40765417 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117364153 | T2 DI COTTONWOOD-DELEVN#1 10/69 INST HV | 44305028 | COTTONWOOD-DELEVAN #1 | 010/069 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.267785 | 40.2442 | ETL.4550 | 40870759 | Marker (i.e. signs)-Steel | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117364786 | T2NT DI MALIN-RND MT #2 51/255 INST GMKS | 43939115 | MALIN-ROUND MTN #2 | 051/255 | ICS | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.567116 | 41.3136 | ETL.6020 | 40746557 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117365081 | DI VALLEY SPRINGS #1 002/035 RPR STRW | 43844341 | VALLEY SPRINGS #1 | 002/035 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-120.793474 | 38.2045 | ETL.8210 | 40904201 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 23
117365554 | T2NT DI MLN-RND MTN #2 48/236 INST GMKS | 43939115 | MALIN-ROUND MTN #2 | 048/236 | ICS | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.529495 | 41.3597 | ETL.6020 | 40817693 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117365898 | DI RND MTN-COTTONWOOD#2 39/316 RPR INSS | 43876311 | ROUND MTN-COTTONWOOD #2 | 039/316 | ICS | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-122.201386 | 40.4909 | ETL.5640 | 40842586 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain
117365914 | T2NT DI MLN-RND MTN #2 48/239 INST GMKS | 43939115 | MALIN-ROUND MTN #2 | 048/239 | ICS | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.535213 | 41.3527 | ETL.6020 | 40868273 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117365999 | T2NT DI CTTNWD-PNRMA 000/003 INST MRKW | 43881008 | COTTONWOOD-PANORAMA | 000/003 | ICW | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.267204 | 40.4019 | ETL.1340 | 40655968 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117366050 | NT DI RND MTN-COTTON #2 39/316 INS MRKS | 43876311 | ROUND MTN-COTTONWOOD #2 | 039/316 | ICS | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-122.201386 | 40.4909 | ETL.5640 | 40814788 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117366121 | T3NT DI DRUM-HIGGINS 005/056 REPAINT | 43738143 | DRUM-HIGGINS | 005/056 | ICS | E | Pre-2020_(9a) Other ignition related |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.839844 | 39.2087 | ETL.4393 | 40819914 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento
117366791 | T2 DI DRM SMMT #1 11/136C RPL POLE | 31521943 | DRUM-SUMMIT #1 | 011/136C | 70Y | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.587778 | 39.3332 | ETL.1440 | 42572738 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
117366815 | T2 HUMBOLDT-TRINITY 053/004L RMV DEBRIS | 44298596 | HUMBOLDT-TRINITY | 053/004 | ICW | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.059793 | 40.7514 | ETL.1820 | 44260937 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2019-08-30
117366864 | T2 HUMBOLDT-TRINITY 053/004L RPR GYWS | 43958295 | HUMBOLDT-TRINITY | 053/004 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.059793 | 40.7514 | ETL.1820 | 44260937 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Eureka |  |  | 2019-08-30
117366990 | T2NT DI DRM SMMT #2 11/138 INST GMKW (R) | 43939697 | DRUM-SUMMIT #2 | 011/138 | ICW | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.585881 | 39.3334 | ETL.1450 | 44565756 | Guy Wire Mark /Indic-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117367013 | T2NT DI DRM SMMT #2 11/138 INST GMKW (L) | 43939697 | DRUM-SUMMIT #2 | 011/138 | ICW | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.585881 | 39.3334 | ETL.1450 | 44565766 | Guy Wire Mark /Indic-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117367020 | T2NT DI MLN-RND MTN #2 75/380B INST GMKS | 43939115 | MALIN-ROUND MTN #2 | 075/380B | ICS | F | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.852096 | 41.0619 | ETL.6020 | 41162688 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117367045 | T2NT DI DRM SMMT #2 11/138 INST GMKW (C) | 43939697 | DRUM-SUMMIT #2 | 011/138 | ICW | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.585881 | 39.3334 | ETL.1450 | 44565795 | Guy Wire Mark /Indic-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117367088 | T2NT DI MLN-RND MTN #2 75/380 INST GMKS | 43939115 | MALIN-ROUND MTN #2 | 075/380 | ICS | F | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.851868 | 41.0616 | ETL.6020 | 40601184 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117367101 | T2 HUMBOLDT-TRINITY 59/00L RMV BUTT | 44086433 | HUMBOLDT-TRINITY | 059/000 | ICW | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-123.150165 | 40.7618 | ETL.1820 | 44559974 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
117367317 | T2 DI DRM SMMT #1 11/136B REPL PL | 31521943 | DRUM-SUMMIT #1 | 011/136B | 70Y | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.587778 | 39.3332 | ETL.1440 | 42572737 | Structure-Wood | Rotten | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
117367435 | T2 DI DRM SMMT #1 11/137 RPL POLE (L) | 31453338 | DRUM-SUMMIT #1 | 011/137 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [8 empty] | ETL.1440 | 44162397 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
117367436 | T2 DI DRM SMMT #1 11/137 RPL POLE (C) | 31453338 | DRUM-SUMMIT #1 | 011/137 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [8 empty] | ETL.1440 | 44162398 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
117367437 | T2 DI DRM SMMT #1 11/137 RPL POLE (R) | 31453338 | DRUM-SUMMIT #1 | 011/137 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.585934 | 39.3332 | ETL.1440 | 44162399 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
117367850 | T3NT DI RND-MTN-CTTNWD#2 19/182 INS MRKS | 43876311 | ROUND MTN-COTTONWOOD #2 | 019/182 | ICS | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-122.005506 | 40.7416 | ETL.5640 | 40674340 | Marker (i.e. signs)-Steel | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117367929 | T2 DI RND MTN-CTTNWOOD#2 30/262 INS MRKS | 43876311 | ROUND MTN-COTTONWOOD #2 | 030/262 | ICS | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.118895 | 40.6019 | ETL.5640 | 40674359 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117368022 | T2 DI RND MTN-CTTNWOOD#2 30/262 RPR STRT | 43876309 | ROUND MTN-COTTONWOOD #2 | 030/262 | ICQ | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.118895 | 40.6019 | ETL.5640 | 40674359 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
117368271 | DI PIT#1-CTTNWD 50/446 INF ENG | 31474087 | PIT #1-COTTONWOOD | 050/446 | 70S | E | Pre-2020_(2) High fire spread TD |  |  |  |  | LATE | North Valley | WSIP |  |  |  |  | Program | 2021 - Late due to project not having funding for 2020. | '-122.174879 | 40.5077 | ETL.5390 | 40817552 | Structure-Tower | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Pole Program | Capital | 426 | Table Mountain |  |  | Yes
117368300 | T2 DI DRM SMMT #1 11/136A RPL POLE | 31521943 | DRUM-SUMMIT #1 | 011/136A | 70Y | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.587773 | 39.3332 | ETL.1440 | 40870568 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
117368334 | T2NT DI RND MT-TBL MT#2 65/273 INST GMKS | 44302501 | ROUND MTN-TABLE MTN #2 | 065/273 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.809947 | 39.8764 | ETL.6070 | 40654134 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117368462 | T2 DI CHWCLLA-KRCHF 0/7 RPR FOND | 43845838 | CHOWCHILLA-KERCKHOFF | 000/007 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | South | WSIP | FSRP | [5 empty] | '-119.569417 | 37.0911 | ETL.1250 | 40806771 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 21
117368483 | T2NT DI MALIN-RND MTN#2 51/254 INST GMKS | 43939115 | MALIN-ROUND MTN #2 | 051/254 | ICS | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.565106 | 41.316 | ETL.6020 | 40759855 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117368487 | T2NT DI MALN-RND MTN #2 80/405B INS MRKS | 43939115 | MALIN-ROUND MTN #2 | 080/405B | ICS | F | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.89427 | 41.0064 | ETL.6020 | 41162609 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117368542 | DI COLEMAN-COTTONWOOD 0/10 RPR STRW | 44309976 | COLEMAN-COTTONWOOD | 000/010 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-122.128437 | 40.4063 | ETL.6430 | 40875720 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117368566 | T2NT DI MLN-RND MNTN #2 94/480 GMKS INST | 43939115 | MALIN-ROUND MTN #2 | 094/480 | ICS | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.934128 | 40.8104 | ETL.6020 | 40868386 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117368582 | T2NT DI MALIN-RND MTN#2 52/260 INST GMKS | 43939115 | MALIN-ROUND MTN #2 | 052/260 | ICS | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.577014 | 41.3014 | ETL.6020 | 40592107 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117368631 | T2 DI DRUM-SUMMIT #1 026/308R INST GMKW | 43910106 | DRUM-SUMMIT #1 | 026/308 | ICW | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [8 empty] | ETL.1440 | 44149472 | Guy Wire Mark /Indic-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117368632 | T2 DI DRUM-SUMMIT #1 026/308L INST GMKW | 43910109 | DRUM-SUMMIT #1 | 026/308 | ICW | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [8 empty] | ETL.1440 | 44149470 | Guy Wire Mark /Indic-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117368832 | T2 DI KILARC-DSCHTS A025/527 RPL STRW | 31478597 | KILARC-DESCHUTES | A025/527 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.282326 | 40.5712 | ETL.7300 | 40869368 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
117370081 | T2NT DI COLEMAN-CTTNWD 0/13B INST GMKW | 44309976 | COLEMAN-COTTONWOOD | 000/013B | ICW | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.131036 | 40.4068 | ETL.6430 | 42578763 | Guy Wire Mark /Indic-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117370212 | T2 DI CTTNWD-DLVN #2 71/619 REPAINT | 44305182 | COTTONWOOD-DELEVAN #2 | 071/619 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.267464 | 40.2265 | ETL.4580 | 40868467 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117370586 | T2 DI DRUM-SUMMIT #1 19/222R RPL PL | 31453474 | DRUM-SUMMIT #1 | 019/222 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.465171 | 39.3191 | ETL.1440 | 44764252 | Structure-Wood | Rotten | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
117370673 | T2 DI DRUM-SUMMIT #1 20/243B RPL PL | 31453474 | DRUM-SUMMIT #1 | 020/243B | 70Y | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.435024 | 39.3211 | ETL.1440 | 42572712 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
117370675 | T2 DI DRUM-SUMMIT #1 20/243C RPL PL | 31453474 | DRUM-SUMMIT #1 | 020/243C | 70Y | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.435043 | 39.3211 | ETL.1440 | 42572714 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
117370763 | T2NT DI DRUM-SUMMIT #1 22/262R INST MRKW | 43910105 | DRUM-SUMMIT #1 | 022/262 | ICW | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.413147 | 39.3118 | ETL.1440 | 44762491 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117370921 | T2 DI CLAY-MARTEL 033/505 RPR SPLS | 43853794 | CLAY-MARTEL | 033/505 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.845874 | 38.4703 | ETL.8250 | 40912846 | Splice-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - 33
117370950 | T2 EI RND MTN-COTTNWD #3 53/474 RPR INSS | 43755803 | ROUND MTN-COTTONWOOD #3 | 053/474 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.200252 | 40.4774 | ETL.5650 | 40762834 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117370953 | T2 DI RND MTN-TBL MTN #2 81/328 INS GMKS | 44156945 | ROUND MTN-TABLE MTN #2 | 081/328 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.701904 | 39.6591 | ETL.6070 | 40865961 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117371127 | T2NT DI RND MTN-CTTNWD 015/153 INST MRKS | 43876311 | ROUND MTN-COTTONWOOD #2 | 015/153 | ICS | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.957139 | 40.7787 | ETL.5640 | 40660258 | Marker (i.e. signs)-Steel | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117371163 | DI RIO DELL JCT-BRDGVLLE 39/4 RPR GYWW | 43749703 | RIO DELL JCT-BRIDGEVILLE | 039/004 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | North Coast | WSIP | [6 empty] | '-123.801747 | 40.4704 | ETL.7850 | 40750417 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2019-07-15
117371170 | T2 DI SPAULDING#3&#1 0/25 RPL STRW | 31445624 | SPAULDING #3-SPAULDING #1 | 000/025 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.635875 | 39.3373 | ETL.8050 | 44190838 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
117371301 | T3NT DI DRUM-HIGGINS 5/58 REPAINT | 43738143 | DRUM-HIGGINS | 005/058 | ICS | E | Pre-2020_(9a) Other ignition related |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.841083 | 39.2067 | ETL.4393 | 40862205 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento
117371708 | T2 DI PALERMO-COLGATE 016/078 INST MRKS | 43727762 | PALERMO-COLGATE | 016/078 | ICS | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.50205 | 39.421 | ETL.5360 | 40867432 | Marker (i.e. signs)-Steel | No Good/Out of Stdrd | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117371839 | T2 DI PIT #1-COTONWOD 021/174 REPAINT | 44157589 | PIT #1-COTTONWOOD | 021/174 | ICS | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.831553 | 40.8208 | ETL.5390 | 40762850 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117371885 | T2NT DI CBRY SW S-RD MT 24/193 INST MRKS | 43897848 | CARBERRY SW STA-ROUND MTN | 024/193 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.87365 | 40.809 | ETL.5410 | 40651116 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117371922 | T2 DI PIT #1-COTONWOD 023/191 PAINT STRS | 44157589 | PIT #1-COTTONWOOD | 023/191 | ICS | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.86936 | 40.8099 | ETL.5390 | 40579857 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117371950 | T2 DI PALERMO-COLGATE C09/041 INST MRKS | 43900094 | PALERMO-COLGATE | C009/041 | ICS | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.356287 | 39.3053 | ETL.5360 | 40581360 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes
117371962 | T2 DI PIT #1-COTONWOD 022/185 PAINT STRS | 44157589 | PIT #1-COTTONWOOD | 022/185 | ICS | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.853583 | 40.8141 | ETL.5390 | 40760963 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117372116 | T2 DI KILARC-CDR CRK 6/148 STRW RPR | 43845231 | KILARC-CEDAR CREEK | 006/148 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.987757 | 40.7131 | ETL.7290 | 40600832 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 630 | Table Mountain |  |  | Yes
117374554 | T2NT DI MLN-RND MTN #2 075/381 INST GMKS | 43939115 | MALIN-ROUND MTN #2 | 075/381 | ICS | F | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.856483 | 41.0607 | ETL.6020 | 40592581 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117374578 | T2 DI DRUM-SUMMIT #1 024/292 RPL STRW | 31498145 | DRUM-SUMMIT #1 | 024/292 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.367486 | 39.3102 | ETL.1440 | 44762498 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS erdy | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
117374610 | T2 DI DRUM-SUMMIT #1 024/292 RPL STRW | 31498145 | DRUM-SUMMIT #1 | 024/292 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.367486 | 39.3102 | ETL.1440 | 44762499 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS erdy | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
117374616 | T2NT DI SPAULDING-SUMMIT 10/360 INS MRKW | 43923448 | SPAULDING-SUMMIT | 010/360 | ICW | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.466578 | 39.319 | ETL.8060 | 40650055 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117374740 | T3NT DI RND MTN-CTNWD #3 31/262 PNT TWR | 43755801 | ROUND MTN-COTTONWOOD #3 | 031/262 | ICQ | F | Pre-2020_(9a) Other ignition related |  |  | Likely MAT error - delink to correct | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.979159 | 40.7432 | ETL.5650 | 40683282 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117374743 | T2NT DI MLN-RND MTN #2 47/235 INST GMKS | 43939115 | MALIN-ROUND MTN #2 | 047/235 | ICS | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.527493 | 41.3622 | ETL.6020 | 40762610 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117374766 | T2NT DI DRUM-SUMMIT #2 18/216R INST MRKW | 43939699 | DRUM-SUMMIT #2 | 018/216 | ICW | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.481913 | 39.3173 | ETL.1450 | 44552319 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117374790 | T2NT DI DRUM-SUMMIT #2 18/215R INST MRKW | 43939699 | DRUM-SUMMIT #2 | 018/215 | ICW | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.482787 | 39.3172 | ETL.1450 | 44552502 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117374793 | T2NT DI LN-RND MTN #2 053/266 INST GMKS | 43939115 | MALIN-ROUND MTN #2 | 053/266 | ICS | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.588992 | 41.2867 | ETL.6020 | 40817699 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117374796 | DI DRUM-SUMMIT #2 21/250 RPL STRW | 31453742 | DRUM-SUMMIT #2 | 021/250 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-120.432381 | 39.3251 | ETL.1450 | 44558931 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
117374798 | T2 DI DRUM-SUMMIT #2 21/250 RPL STRW | 31453742 | DRUM-SUMMIT #2 | 021/250 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.432381 | 39.3251 | ETL.1450 | 44559076 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
117374802 | T2NT DI MLN-ROND MTN #2 50/247 INST GMKS | 43939115 | MALIN-ROUND MTN #2 | 050/247 | ICS | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.551137 | 41.3332 | ETL.6020 | 40819376 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117374855 | T2 DI DRUM-SUMMIT #2 021/257L REPL PL | 31453742 | DRUM-SUMMIT #2 | 021/257 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.42131 | 39.3278 | ETL.1450 | 44552535 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
117374857 | T2 DI DRUM-SUMMIT #2 021/257R REPL STRW | 31453742 | DRUM-SUMMIT #2 | 021/257 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.42131 | 39.3278 | ETL.1450 | 44552275 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
117374916 | T3 EI GRIZZLY TAP 3/1 RPR GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 003/001 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.3202807 | 39.8983 | ETL.2395 | 44551462 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117374928 | T3 EI GRIZZLY TAP 1/14 RPR GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 001/014 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.299472 | 39.8956 | ETL.2395 | 44550731 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117374951 | T3 EI GRIZZLY TAP 000/012 RPR GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 000/012 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.281573 | 39.8977 | ETL.2395 | 44550003 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117374952 | T3 EI GRIZZLY TAP 0/13 RPR GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 000/013 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.2840844 | 39.8978 | ETL.2395 | 44549880 | Guy Wire-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117374985 | T2 EI COLEMAN-SOUTH 005/122 INST DAMS | 43939301 | COLEMAN-SOUTH | 005/122 | ICW | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.979633 | 40.4037 | ETL.6450 | 44733425 | Damper-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117375171 | T3 EI GRIZZLY TAP 0/2 RPR GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 000/002 | ICW | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.2793956 | 39.8901 | ETL.2395 | 44403545 | Guy Wire-Wood | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117375226 | T3 EI GRIZZLY TAP 3/11 RPR SPLW | 43760153 | TAP (CITY OF SANTA CLARA) | 003/011 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.322234 | 39.9069 | ETL.2395 | 44551417 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117375228 | T3 EI GRIZZLY TAP 3/13 RPR ANCW | 43760153 | TAP (CITY OF SANTA CLARA) | 003/013 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.3225367 | 39.9081 | ETL.2395 | 44551402 | Anchor-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117375256 | T3 EI GRIZZLY TAP 4/1 RPR ANCW | 43760153 | TAP (CITY OF SANTA CLARA) | 004/001 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.326678 | 39.911 | ETL.2395 | 44551404 | Anchor-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117375258 | T3 EI GRIZZLY TAP 003/014 RPR ANCW | 43760153 | TAP (CITY OF SANTA CLARA) | 003/014 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.3225909 | 39.9083 | ETL.2395 | 44551403 | Anchor-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117375285 | T3 EI GRIZZLY TAP 003/017L RPR ANCW | 43760153 | TAP (CITY OF SANTA CLARA) | 003/017 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.323704 | 39.9096 | ETL.2395 | 44551421 | Anchor-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117375386 | T2 DI DRUM-SUMMT #1 8/93 RPR GYWW | 43910106 | DRUM-SUMMIT #1 | 008/093 | ICW | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.654494 | 39.3133 | ETL.1440 | 40603734 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117375407 | T2 DI BRDGVLLE-CTTNWD 001/019R RPL STRW | 31451465 | BRIDGEVILLE-COTTONWOOD | 001/019 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.302767 | 40.3956 | ETL.1110 | 44424500 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
117375456 | T2 DI DRUM-SUMMIT 10/127 RPL POLE | 31451466 | DRUM-SUMMIT #2 | 010/127 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.602768 | 39.3272 | ETL.1450 | 44212267 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
117375457 | T2 DI SPAUL SMM 16/506 RPL CRSW | 31454618 | SPAULDING-SUMMIT | 016/506 | 93E | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.378867 | 39.3194 | ETL.8060 | 44841031 | Crossarm-Wood | No Good/Out of Stdrd | Replace | ESTS erdy | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Sacramento |  |  | Yes
117375458 | T2 DI SPAUL SMM 16/506R RPL CRSW | 31454618 | SPAULDING-SUMMIT | 016/506 | 93E | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.378867 | 39.3194 | ETL.8060 | 44841030 | Crossarm-Wood | No Good/Out of Stdrd | Replace | ESTS erdy | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Sacramento |  |  | Yes
117375459 | T2 DI DRUM-SUMMIT #2 10/127 RPL POLE | 31451466 | DRUM-SUMMIT #2 | 010/127 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [8 empty] | ETL.1450 | 44212220 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
117375818 | T3 DI SLT SPRGS-TGR CRK 15/114 INST HRDS | 43842402 | SALT SPRINGS-TIGER CREEK | 015/114 | ICS | E | Pre-2020_(9a) Other ignition related |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-120.470277 | 38.4556 | ETL.3500 | 40745466 | Hardware-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Victor |  | Y - 17
117376077 | T2NT DI PIT#-COTTONWOOD 27/220 PNT STRS | 44157589 | PIT #1-COTTONWOOD | 027/220 | ICS | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.936099 | 40.7923 | ETL.5390 | 40601045 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117376230 | T3NT DI RND MTN-CTTNWD#3 33/278 CANCEL | 43755801 | ROUND MTN-COTTONWOOD #3 | 033/278 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  | CANCEL/CNCL | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.995076 | 40.7242 | ETL.5650 | 40868286 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117376367 | T2 DI DRUM-SUMMIT #1 021/255 RPL STRW | 31453474 | DRUM-SUMMIT #1 | 021/255 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.422919 | 39.3144 | ETL.1440 | 40821389 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
117376401 | T2NT DI MALN-RND MTN #2 49/242 INST GMKS | 44110674 | MALIN-ROUND MTN #2 | 049/242 | ICS | F | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.541315 | 41.3452 | ETL.6020 | 40677646 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117376408 | T2 DI DRUM-SUMMIT #1 026/309 INST MRKS | 43910103 | DRUM-SUMMIT #1 | 026/309 | ICS | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.338273 | 39.3103 | ETL.1440 | 40654788 | Marker (i.e. signs)-Steel | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes
117376708 | NT DI RND MTN-COTTONWOOD 36/301 INS MRKS | 43876311 | ROUND MTN-COTTONWOOD #2 | 036/301 | ICS | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-122.184579 | 40.5241 | ETL.5640 | 40594962 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117376842 | T2 DI CRTNA-MNDCNO#1 058/284 INS HRDT | 44306522 | CORTINA-MENDOCINO #1 | 058/284 | ICS | E | Pre-2020_(9a) Other ignition related |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.147742 | 39.2368 | ETL.1330 | 40762067 | Hardware-Tower | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville
117377053 | T2 DI BRDGVLL-CTTNWOOD 056/414 INST HRDT | 43742048 | BRIDGEVILLE-COTTONWOOD | 056/414 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-123.296704 | 40.3877 | ETL.1110 | 40592236 | Hardware-Tower | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
117377492 | T2NT DI MALIN-RND MTN#2 49/246 INST GMKS | 43939115 | MALIN-ROUND MTN #2 | 049/246 | ICS | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.549317 | 41.3354 | ETL.6020 | 40817695 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117377616 | DI HAT CREEK #1 WESTWD 052/1012 REPL PL | 31456189 | HAT CREEK #1-WESTWOOD | 052/1012 | 70Y | E | Pre-2020_(2) High fire spread TD |  |  |  |  | LATE | North Valley | WSIP |  |  |  |  | Access Issues | 2021 - Snow . FSR 12/2020 | '-121.008713 | 40.34 | ETL.7030 | 40877517 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
117377735 | T2 DI BRDGVIL-CTTNWD 054/403 INST HRDT | 43742048 | BRIDGEVILLE-COTTONWOOD | 054/403 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-123.265348 | 40.3949 | ETL.1110 | 40676678 | Hardware-Tower | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
117377941 | T2 DI DRUM-SUMMIT #2 21/254L RPL STRW | 31453742 | DRUM-SUMMIT #2 | 021/254 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.42614 | 39.3272 | ETL.1450 | 44553572 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
117377942 | T2 DI DRUM-SUMMIT #2 021/254R RPL STRW | 31453742 | DRUM-SUMMIT #2 | 021/254 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.42614 | 39.3272 | ETL.1450 | 44553637 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
117377979 | T2NT DI RND MTN CTTN #2 32/276 INST MRKS | 43877040 | ROUND MTN-COTTONWOOD #2 | 032/276 | ICS | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.142192 | 40.5743 | ETL.5640 | 40816305 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117378114 | T2NT DI MLN-RND MTN #2 51/253 INST GMKS | 43939115 | MALIN-ROUND MTN #2 | 051/253 | ICS | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.563022 | 41.3186 | ETL.6020 | 40663111 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117378308 | T2 DI COLEMAN-COTTONWOOD 3/76 RPR GYWW | 44309976 | COLEMAN-COTTONWOOD | 003/076 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [8 empty] | ETL.6430 | 44274855 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117378322 | T2 DI COLEMAN-COTTONWOOD 3/76 RPR GYWW | 44309976 | COLEMAN-COTTONWOOD | 003/076 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [8 empty] | ETL.6430 | 44274853 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117378323 | T2 DI COLEMAN-COTTONWOOD 3/76 RPR GYWW | 44309976 | COLEMAN-COTTONWOOD | 003/076 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | North Valley | WSIP | [8 empty] | ETL.6430 | 44274854 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117378325 | T2 DI COLEMAN-COTTONWOOD 3/76 RPR STRW | 44309976 | COLEMAN-COTTONWOOD | 003/076 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [8 empty] | ETL.6430 | 44274855 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117378417 | EI STANISLAUS-MANTECA #2 026/152 REPAINT |  | STANISLAUS-MANTECA #2 | 026/152 |  | E | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) |  |  |  | LATE | Central | WSIP | [6 empty] | '-120.748745 | 37.9293 | ETL.3820 | 40642939 | Structure-Tower | Paint/Coating | Repaint |  |  |  |  | PEND | LC | TLN | Maintenance | Expense |  | Victor |  | Y - Prog Multi
117378636 | EI STLS-MLN SW ST-MCA #1 025/161 REPAINT | 43841835 | STANISLAUS-MELONES SS-MANTECA #1+ | 025/161 | ICS | E | Pre-2020_(9a) Other ignition related | Budget Owner (Paint) |  |  |  | LATE | Central | WSIP | [6 empty] | '-120.751449 | 37.9286 | ETL.3830 | 40871567 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - Prog Multi
117378968 | T3 DI DRUM-HIGGINS 011/103L RPL STRW | 31504775 | DRUM-HIGGINS | 011/103 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.910423 | 39.1788 | ETL.4393 | 44172208 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
117379075 | DI HT CRK #1-WSTWD 049/956 INST MRKW | 43904280 | HAT CREEK #1-WESTWOOD | 049/956 | ICW | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-121.01565 | 40.3809 | ETL.7030 | 40701264 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117379370 | T3 DI DRUM-HIGGINS 011/103R RPL STRW | 31504775 | DRUM-HIGGINS | 011/103 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.910423 | 39.1788 | ETL.4393 | 44172209 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
117379373 | T2 DI RND MTN-TBLE MTN #2 56/241 REPAINT |  | ROUND MTN-TABLE MTN #2 | 056/241 | ICS | E | Pre-2020_(3) On high spread structure | Budget Owner (Paint) |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Program | 2021 Paint took out of program due to future project to be removed with S6B7 | '-121.859275 | 39.9948 | ETL.6070 | 40592713 | Structure-Steel | Paint/Coating | Other |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain
117379586 | T2 DI DRUM SMMT#1 8/96 RPR GYWW | 43910107 | DRUM-SUMMIT #1 | 008/096 | ICW | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.649594 | 39.3141 | ETL.1440 | 40654770 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117379617 | T2 DI DRUM SMMT #1 8/96 RPL GMKW | 43910106 | DRUM-SUMMIT #1 | 008/096 | ICW | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.649594 | 39.3141 | ETL.1440 | 40654770 | Guy Wire Mark /Indic-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117380003 | T2 DI RND MTN-CTNWD#2 40/322 INSTL MRKS | 43877040 | ROUND MTN-COTTONWOOD #2 | 040/322 | ICS | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.206751 | 40.4769 | ETL.5640 | 40674332 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117380422 | T2NT DI MALIN-RND MTN 2 49/245 INST GMKS | 43939115 | MALIN-ROUND MTN #2 | 049/245 | ICS | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.547007 | 41.3383 | ETL.6020 | 40753305 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117380460 | T2 DI HAT CRK #1-WESTWD 36/700 RPR PL | 43939292 | HAT CREEK #1-WESTWOOD | 036/700 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.068123 | 40.5627 | ETL.7030 | 40867621 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117380561 | T2 DI CSCD BENT DECH 0/6 RPR GYWW | 43690811 | CASCADE-BENTON-DESCHUTES | 000/006 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.338071 | 40.6519 | ETL.6310 | 40592314 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117380565 | T2 DI CSCD BENT DECH 0/6 INST MRKW | 43690811 | CASCADE-BENTON-DESCHUTES | 000/006 | ICW | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.338071 | 40.6519 | ETL.6310 | 40592314 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117383038 | T2 PARADISE-TABLE MTN 19/158 RPR GYWS | 43727174 | PARADISE-TABLE MTN | 019/158 | ICS | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-121.556682 | 39.6868 | ETL.4316 | 40828363 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117383078 | T2 DI CSCD BENT DESCH 2/58 REPL PL | 31427801 | CASCADE-BENTON-DESCHUTES | 002/058 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.321791 | 40.6194 | ETL.6310 | 41177773 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
117383092 | T2 PARADISE-TBL MTN 019/158 RPR JUMS | 43727174 | PARADISE-TABLE MTN | 019/158 | ICS | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-121.556747 | 39.6868 | ETL.4316 | 40856081 | Jumper-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117383178 | T2 DI BRDGVL-CTTNWD 39/312L RPL STRW | 31451465 | BRIDGEVILLE-COTTONWOOD | 039/312 | 70Y | E | Pre-2020_(2) High fire spread TD |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Clearance Denied by GCC | 2021 - Clearance conflicts w/ North Coast. |  |  | ETL.1110 | 44424595 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
117383283 | T2 DI BRDGVL-CTTNWD 39/312R RPL STRW | 31451465 | BRIDGEVILLE-COTTONWOOD | 039/312 | 70Y | E | Pre-2020_(2) High fire spread TD |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Clearance Denied by GCC | 2021 - Clearance conflicts w/ North Coast. |  |  | ETL.1110 | 44424597 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
117383361 | T2 DI BRDGVL-CTTNWD 39/312C RPL STRW | 31451465 | BRIDGEVILLE-COTTONWOOD | 039/312 | 70Y | E | Pre-2020_(2) High fire spread TD |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Clearance Denied by GCC | 2021 - Clearance conflicts w/ North Coast. | '-121.628227 | 37.9501 | ETL.1110 | 44424596 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
117383680 | T2NT DI BCKS CK-RK CK-CT :00/2 INST MRKS | 43897313 | BUCKS CREEK-ROCK CREEK-CRESTA | :000/002 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.347817 | 39.9056 | ETL.4430 | 40673166 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117383763 | T2 DI DRUM-SUMMIT #1 009/113R RPR GYWW | 43910109 | DRUM-SUMMIT #1 | 009/113 | ICW | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.620904 | 39.3209 | ETL.1440 | 44765181 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117383905 | T2 DI PALERMO-COLGATE C010/047 INST MRKS | 43900094 | PALERMO-COLGATE | C010/047 | ICS | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.379787 | 39.2999 | ETL.5360 | 40814787 | Marker (i.e. signs)-Steel | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes
117383916 | STN-MLNS SW STA-MNTC #1 25/163 RPR STRT | 43852841 | STANISLAUS-MELONES SS-MANTECA #1+ | 025/163 | ICS | E | Pre-2020_(9a) Other ignition related | Budget Owner (Paint) |  |  |  | LATE | Central | WSIP | [6 empty] | '-120.756719 | 37.927 | ETL.3830 | 40579579 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - 9
117383926 | DI COLEMAN-COTTONWOOD 000/011 INST MRKW | 44309976 | COLEMAN-COTTONWOOD | 000/011 | ICW | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-122.129304 | 40.4065 | ETL.6430 | 40598761 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117384009 | T2NT DI DRUM-SUMMIT #2 021/256 INST MRKW | 43947609 | DRUM-SUMMIT #2 | 021/256 | ICW | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.422532 | 39.3277 | ETL.1450 | 44558952 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117384225 | T2 DI MALIN-ROUND MT #2 60/302 INST GMKS | 43939115 | MALIN-ROUND MTN #2 | 060/302 | ICS | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.657825 | 41.2019 | ETL.6020 | 40677663 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117384248 | STNSS-MELNES SW-STA-MN#1 19/121 RPR STRT |  | STANISLAUS-MELONES SS-MANTECA #1+ | 019/121 |  | E | Pre-2020_(9a) Other ignition related | Budget Owner (Paint) |  |  |  | LATE | Central | WSIP | [6 empty] | '-120.657175 | 37.9761 | ETL.3830 | 41136914 | Structure-Tower | Paint/Coating | Repaint |  |  |  |  | PEND | LC | TLN | Maintenance | Expense |  | Victor |  | Y - 9
117384344 | T2NT DI PALERMO-COLGATE C05/26 INST MRKS | 43900094 | PALERMO-COLGATE | C005/026 | ICS | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.286576 | 39.3076 | ETL.5360 | 40815685 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento
117384371 | T3NT DI RND MTN-CTTNWD#3 31/263 CANCEL | 43755801 | ROUND MTN-COTTONWOOD #3 | 031/263 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  | CANCEL/CNCL | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.979721 | 40.7425 | ETL.5650 | 40653348 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117384397 | DI PIT #1-COTTONWOOD 013/111B PNT STRS | 43879413 | PIT #1-COTTONWOOD | 013/111B | ICS | F | Pre-2020_(9a) Other ignition related |  |  |  |  | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.715711 | 40.8771 | ETL.5390 | 41162765 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117384436 | T2 DI TULE-SPRINGVILLE 015/003 RPL POLE | 31454783 | TULE-SPRINGVILLE | 015/003 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-118.878181 | 36.1088 | ETL.9040 | 40647888 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Midway |  | Y - 23
117384509 | T3NT DI PIT #1-COTTNWOOD 31/266 CANCEL | 43735854 | PIT #1-COTTONWOOD | 031/266 | ICS | E | Pre-2020_(9a) Other ignition related |  |  | CANCEL/CNCL | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.982458 | 40.739 | ETL.5390 | 40803640 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117384542 | T2 DI NEWARK-LIVER 16/108 RPR GYWW | 43877617 | NEWARK-LIVERMORE | 016/108 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-121.782978 | 37.6451 | ETL.7660 | 40665818 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Bay |  | Y - 8
117384560 | T2 DI MNDCNO-WLLTS-FRT BRGG 5/4 RPL POLE | 31490868 | MENDOCINO-WILLITS-FORT BRAGG | 005/004 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.275139 | 39.2926 | ETL.7550 | 40649095 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville
117385853 | T2 TESLA-SALADO-MANTECA -_026/159 HS | 43848440 | TESLA-SALADO-MANTECA | 026/159 | ICW | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | Central | Non-WSIP | [6 empty] | '-121.206644 | 37.4624 | ETL.4000 | 40912763 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 7
117385912 | T2 TESLA-SALADO-MANTECA -_025/150 HS | 43848440 | TESLA-SALADO-MANTECA | 025/150 | ICW | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | Central | Non-WSIP | [6 empty] | '-121.206138 | 37.4731 | ETL.4000 | 40912755 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 7
117385925 | T2 DI SPAULDING-SUMMIT 016/504 RPR GYWW | 43923448 | SPAULDING-SUMMIT | 016/504 | ICW | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.379007 | 39.3208 | ETL.8060 | 40602277 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117385983 | T2 DI DRUM-SUMMIT #1 010/120C RPL STRW | 31508705 | DRUM-SUMMIT #1 | 010/120C | 70Y | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.611602 | 39.3236 | ETL.1440 | 42572657 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
117386191 | T2 DI DRUM-SUMMIT #1 010/120A RPL STRW | 31508705 | DRUM-SUMMIT #1 | 010/120A | 70Y | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.611681 | 39.3237 | ETL.1440 | 40756804 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
117386282 | T2 DI DRUM-SUMMIT #1 010/120B RPL STRW | 31508705 | DRUM-SUMMIT #1 | 010/120B | 70Y | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.611641 | 39.3237 | ETL.1440 | 42572656 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
117386354 | T3 DI RD MT-TBL MT#2 020/103 CANCEL | 43790346 | ROUND MTN-TABLE MTN #2 | 020/103 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  | CANCEL/CNCL | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.94473 | 40.5135 | ETL.6070 | 40657629 | Structure-Steel | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain
117386526 | T2 DI DRUM-SUMMIT #2 023/272 RPL STRW | 31497848 | DRUM-SUMMIT #2 | 023/272 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.396444 | 39.329 | ETL.1450 | 44558953 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
117386684 | T2 DI WEIMAR-HALSEY 005/138 REPL STRW | 31454601 | WEIMAR-HALSEY | 005/138 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.042332 | 38.9575 | ETL.8340 | 40822775 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento
117387387 | DI HAT CRK#1-WESTWOOD 46/902 RPL STRW | 31456189 | HAT CREEK #1-WESTWOOD | 046/902 | 70Y | E | Pre-2020_(2) High fire spread TD |  |  |  |  | LATE | North Valley | WSIP |  |  |  |  | Access Issues | 2021 - Snow . FSR 12/2020 | '-121.022618 | 40.4214 | ETL.7030 | 40868252 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain
117387961 | T2 DI BRIDGEVILLE-CTNWD 17/154R RPL STRW | 31444708 | BRIDGEVILLE-COTTONWOOD | 017/154 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Material & Equipment | Material unavailable | '-122.583763 | 40.3819 | ETL.1110 | 44423380 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
117388013 | T2NT DI MLIN-RND MTN #2 78/395B INS GMKS | 43939115 | MALIN-ROUND MTN #2 | 078/395B | ICS | F | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.890339 | 41.0353 | ETL.6020 | 41162682 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117388043 | DI CTTN DELE 61/556 INST MRKS | 44305182 | COTTONWOOD-DELEVAN #2 | 061/556 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-122.268287 | 40.3667 | ETL.4580 | 40817877 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117388133 | T2 DI TULE-SPRNGVIL 22/003 RPR STRW | 44323596 | TULE-SPRINGVILLE | 022/003 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-118.779342 | 36.1324 | ETL.9040 | 40663647 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Midway |  | Y - 23 | USFS
117388300 | T2 DI TULE-SPRNGVIL 22/009 HOLD | 31453078 | TULE-SPRINGVILLE | 022/009 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-118.77482 | 36.1336 | ETL.9040 | 40872990 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Midway |  | Y - 23 | USFS
117388302 | T2 DI TULE-SPRNGVIL 22/014 RPL POLE | 31453078 | TULE-SPRINGVILLE | 022/014 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-118.772154 | 36.1371 | ETL.9040 | 40766147 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Midway |  | Y - 23
117388370 | DI CTTNWD-DLVN#2 61/555 INS MRKS | 44305184 | COTTONWOOD-DELEVAN #2 | 061/555 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-122.268296 | 40.3685 | ETL.4580 | 40759784 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117388426 | LOS BANOS-NIDWAY #2 102/425 RPLC INSL | 31455040 | LOS BANOS-MIDWAY #2 | 102/425 | 93K | E | Pre-2020_(1b) Lines with special commitments |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.8828858 | 35.9146 | ETL.6010 | 40782786 | Insulator-Steel | No Good/Out of Stdrd | Replace | CONS | CONS | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - Prog Multi
117388428 | LOS BANOS-MIDWAY #2 099/413 RPLC INSL | 31455040 | LOS BANOS-MIDWAY #2 | 099/413 | 93K | E | Pre-2020_(1b) Lines with special commitments | Director approved | DLFL once tag is confirmed complete PM | Email CIRT when complete |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.9145249 | 35.9491 | ETL.6010 | 40680859 | Insulator-Steel | No Good/Out of Stdrd | Replace | CONS | CONS | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - Prog Multi
117388434 | T2 DI TULE-SPRNGVILLE 020/006 RPR GYWW | 44323597 | TULE-SPRINGVILLE | 020/006 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-118.807757 | 36.1354 | ETL.9040 | 40808165 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Midway |  | Y - 23
117388435 | T2 DI TULE-SPRNGVILLE 020/006 RPR STRW | 44323598 | TULE-SPRINGVILLE | 020/006 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-118.807757 | 36.1354 | ETL.9040 | 40808165 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Midway |  | Y - 23
117388438 | T2 DI TULE-SPRNGVILLE 019/008 RPR STRW | 44323599 | TULE-SPRINGVILLE | 019/008 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-118.816131 | 36.1262 | ETL.9040 | 40860497 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Midway |  | Y - 23
117388635 | T2 DI PALERMO-COLGATE C000/001 INST MRKS | 43900094 | PALERMO-COLGATE | C000/001 | ICS | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.193041 | 39.331 | ETL.5360 | 40593157 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento
117388644 | LOS BANOS-GATES #1 001/006 RPL INSL | 31418847 | LOS BANOS-GATES #1 | 001/006 | 93K | E | Pre-2020_(1b) Lines with special commitments | Director approved | DLFL once tag is confirmed complete PM 74008747 | Email CIRT when complete |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-121.011446 | 37.035 | ETL.6000 | 40843810 | Insulator-Steel | No Good/Out of Stdrd | Replace | srdy DCNL |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 16
117388711 | T2NT DI TULE-SPRNGVILLE 019/008 INST HV | 44323680 | TULE-SPRINGVILLE | 019/008 | ICW | F | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-118.816131 | 36.1262 | ETL.9040 | 40860497 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Midway |  | Y - 23
117388717 | T2 DI TULE-SPRNGVIL 21/018 RPR GYWW | 43844730 | TULE-SPRINGVILLE | 021/018 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-118.783408 | 36.1323 | ETL.9040 | 40859566 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Midway |  | Y - 23
117388770 | T2 DI TULE-SPRNGVIL 21/018 RPR POLE | 43844759 | TULE-SPRINGVILLE | 021/018 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-118.783408 | 36.1323 | ETL.9040 | 40859566 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Midway |  | Y - 23
117388877 | T2 DI BRDGEVLLE-CTTNWOOD 14/129R REPL PL | 31455500 | BRIDGEVILLE-COTTONWOOD | 014/129 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.531514 | 40.3943 | ETL.1110 | 44423276 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
117388901 | T2 DI BRDGEVLLE-CTTNWOOD 14/129L REPL PL | 31455500 | BRIDGEVILLE-COTTONWOOD | 014/129 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.531514 | 40.3943 | ETL.1110 | 44423275 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
117388925 | T2 DI LAYTONVILLE-WILLITS 13/0A INS MRKW | 43877949 | LAYTONVILLE-WILLITS | 013/000A | ICW | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.427093 | 39.5555 | ETL.8360 | 40905761 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
117388940 | T2 DI LAYTONVILLE-WILLITS 13/0A INS GMKW | 43877949 | LAYTONVILLE-WILLITS | 013/000A | ICW | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.427093 | 39.5555 | ETL.8360 | 40905761 | Guy Wire Mark /Indic-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  | 2019-07-29
117388946 | T2 DI TULE-SPRNGVIL 16/002 RPR GYWW | 43844734 | TULE-SPRINGVILLE | 016/002 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-118.861836 | 36.1083 | ETL.9040 | 40691138 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Midway |  | Y - 23
117389198 | T2 DI TULE-SPRINGVILLE 22/4 RPL POLE | 31453078 | TULE-SPRINGVILLE | 022/004 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-118.778455 | 36.1325 | ETL.9040 | 40749787 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Midway |  | Y - 23 | USFS
117389213 | T2NT DI DRUM-SUMMIT #2 10/122A INS GMKW | 43939697 | DRUM-SUMMIT #2 | 010/122A | ICW | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.60952 | 39.3247 | ETL.1450 | 40810272 | Guy Wire Mark /Indic-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117392042 | T2 EI BRDGVLLE-COTTNWOOD 1/19L RPL STRW | 31451465 | BRIDGEVILLE-COTTONWOOD | 001/019 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.302767 | 40.3956 | ETL.1110 | 44424499 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
117392043 | T3 EI GRIZZLY TAP 03/14 RPR GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 003/014 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-121.322578 | 39.9083 | ETL.2395 | 44551383 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117392044 | T3 EI GRIZZLY TAP 03/14 RPR GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 003/014 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-121.322578 | 39.9083 | ETL.2395 | 44551384 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117392264 | T2 DI TULE-SPRINGVILLE 022/002 RPR STRW | 44323681 | TULE-SPRINGVILLE | 022/002 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-118.780278 | 36.1323 | ETL.9040 | 40691222 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Midway |  | Y - 23 | USFS
117392304 | T2 DI TULE-SPRINGVILLE 022/006 RPR STRW | 44323682 | TULE-SPRINGVILLE | 022/006 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-118.776665 | 36.1329 | ETL.9040 | 40808181 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Midway |  | Y - 23 | USFS
117392442 | T2 DI BALCH-SANGER 000/002 RPL INSS | 31443424 | BALCH-SANGER | 000/002 | 93K | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-119.090382 | 36.9083 | ETL.1050 | 40725024 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 17
117392559 | T2 DI DLTA-MTN GATE JCT 002/065 RPL POLE | 31456311 | DELTA-MOUNTAIN GATE JCT | 002/065 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.386445 | 40.9022 | ETL.6750 | 40828048 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
117392620 | T2 DI DRUM-SUMMIT#1 26/306L RPL POLE | 31498145 | DRUM-SUMMIT #1 | 026/306 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.34313 | 39.3091 | ETL.1440 | 44768880 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS erdy | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
117392622 | T2 DI DRUM-SUMMIT#1 26/306R RPL POLE | 31498145 | DRUM-SUMMIT #1 | 026/306 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.34313 | 39.3091 | ETL.1440 | 44768881 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS erdy | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
117392645 | T2 DI TULE-SPRINGVILLE 21/16 RPR STRW | 44323683 | TULE-SPRINGVILLE | 021/016 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-118.78525 | 36.1332 | ETL.9040 | 40823385 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Midway |  | Y - 23
117392710 | T2 DI DRUM-SUMMIT#2 27/330 RPR GYWW | 43947611 | DRUM-SUMMIT #2 | 027/330 | ICW | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.330512 | 39.315 | ETL.1450 | 44553673 | Guy Wire-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117392714 | T2 DI DRUM-SUMMIT#2 27/330 RPL STRW | 31497848 | DRUM-SUMMIT #2 | 027/330 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.330512 | 39.315 | ETL.1450 | 44553705 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
117392719 | T2NT DI DRUM-SUMMIT#2 27/330 INS MRKW | 43947608 | DRUM-SUMMIT #2 | 027/330 | ICW | F | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.330512 | 39.315 | ETL.1450 | 44553673 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117392874 | T2 DI DRUM-SMMT#2 9/112R INS MRKW | 43939697 | DRUM-SUMMIT #2 | 009/112 | ICW | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.622018 | 39.321 | ETL.1450 | 44553509 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117393075 | EI IGNACIO-ALTO-SALSLTO#1 1/15 RMV VEGN |  | IGNACIO-ALTO-SAUSALITO #1 | 001/015 | HNA | E | Pre-2020_(9a) Other ignition related |  |  |  |  | LATE | North Coast | Non-WSIP | [6 empty] | '-122.526711 | 38.0597 | ETL.7160 | 40594360 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Lakeville
117393108 | T2 DI TULE-SPRINGVILLE 23/4 RPR STRW | 44323685 | TULE-SPRINGVILLE | 023/004 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-118.76644 | 36.1424 | ETL.9040 | 40749793 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Midway |  | Y - 23
117393153 | T2 DI TULE-SPRINGVILLE 023/007 RPL STRW | 31455199 | TULE-SPRINGVILLE | 023/007 | 70Y | B | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-118.764266 | 36.144 | ETL.9040 | 40821819 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Midway |  | Y - 23
117393304 | T2 DI DRUM-SUMMIT #2 027/331L CANCEL | 43947611 | DRUM-SUMMIT #2 | 027/331 | ICW | E | Pre-2020_(1b) Lines with special commitments |  |  | CANCEL/CNCL | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.329839 | 39.3159 | ETL.1450 | 44553636 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117393446 | T2 DI DRUM-SUMMIT #1 023/273R INST MRKW | 43910107 | DRUM-SUMMIT #1 | 023/273 | ICW | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.395358 | 39.311 | ETL.1440 | 44768883 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117393661 | T2NT DI DRUM-SUMMIT #2 10/122C INS GMKW | 43939697 | DRUM-SUMMIT #2 | 010/122C | ICW | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.609477 | 39.3246 | ETL.1450 | 42572872 | Guy Wire Mark /Indic-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117393705 | T2 DI TULE-SPRINGVILLE 23/2 RPLC STRW | 31454783 | TULE-SPRINGVILLE | 023/002 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-118.767867 | 36.1414 | ETL.9040 | 40690997 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Midway |  | Y - 23
117394452 | T2 DI MNDN-WLT-FT BRG 041/001 RPL CRSW | 31456470 | MENDOCINO-WILLITS-FORT BRAGG | 041/001 | 93E | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.775088 | 39.4291 | ETL.7550 | 40600287 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Lakeville
117394453 | T2 DI MNDN-WLT-FT BRG 041/001 RPR INSW | 43877954 | MENDOCINO-WILLITS-FORT BRAGG | 041/001 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.775088 | 39.4291 | ETL.7550 | 40626981 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
117394744 | T2 DI MNDCN-WLLTS-FRT BRGG 1/1 RPR GYWW | 43877954 | MENDOCINO-WILLITS-FORT BRAGG | 001/001 | ICW | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | WSIP | FSRP | [5 empty] | '-123.212959 | 39.2549 | ETL.7550 | 40585211 | Guy Wire-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
117394752 | T2 DI TULE-SPRINGVILE 026/003 RPR CNDW | 44323686 | TULE-SPRINGVILLE | 026/003 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-118.718374 | 36.1597 | ETL.9040 | 40663677 | Conductor-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Midway |  | Y - 23 | USFS
117394874 | T3 DI KIL CED CRE 8/199 RPR GYWW | 43685209 | KILARC-CEDAR CREEK | 008/199 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.983077 | 40.738 | ETL.7290 | 40868039 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117394913 | T2 DI TULE-SPRINGVILLE 025/007 RPR STRW | 44323687 | TULE-SPRINGVILLE | 025/007 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-118.730133 | 36.1563 | ETL.9040 | 40807811 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Midway |  | Y - 23
117395289 | T2 DI ROCK CREEK-POE 000/001 PAINT STRS | 43878132 | ROCK CREEK-POE | 000/001 | ICS | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.34688 | 39.9058 | ETL.5630 | 40590786 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  | Yes
117395303 | T2 DI COTTONWOOD #1 002/020 RMV NEST | 44155926 | COTTONWOOD #1 | 002/020 | ICS | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.267978 | 40.3575 | ETL.6620 | 40910964 | Structure-Steel | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117395338 | T2 DI SPAULDING#3-SPAULDNG#1 0/1B RPL PL | 31445624 | SPAULDING #3-SPAULDING #1 | 000/001B | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.644787 | 39.3248 | ETL.8050 | 42568604 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
117395467 | T2 DI MNDCN-WLLTS-FRT BRGG 39/2 WSH INSW | 43878161 | MENDOCINO-WILLITS-FORT BRAGG | 039/002 | ICD | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.746993 | 39.4136 | ETL.7550 | 40697974 | Insulator | Contaminated | Ground Wash | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 622 | Lakeville
117395515 | T2NT DI MALIN-RND MTN#2 75/380A INS GMKS | 43939115 | MALIN-ROUND MTN #2 | 075/380A | ICS | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.851997 | 41.0618 | ETL.6020 | 41162689 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117395670 | T2 DI BALCH-SANGER 3/21 RPR CONS | 43845834 | BALCH-SANGER | 003/021 | ICS | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-119.121034 | 36.8785 | ETL.1050 | 40583099 | Conductor-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  | Y - 17
117395729 | T2 DI TULE-SPRINGVILLE 25/12 RPR GYWW | 43844637 | TULE-SPRINGVILLE | 025/012 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-118.725504 | 36.1569 | ETL.9040 | 40691009 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Midway |  | Y - 23 | USFS
117395914 | T2NT DI CARB SW-RND MTN R1/11 INST MRKS | 43897849 | CARBERRY SW STA-ROUND MTN | R001/011 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.938708 | 40.806 | ETL.5410 | 40586643 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117395977 | T2 DI SPULDNG#3-SPULDNG#1 0/1C RPL PL | 31445624 | SPAULDING #3-SPAULDING #1 | 000/001C | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.644736 | 39.3248 | ETL.8050 | 42568605 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
117396085 | T2 EI BRDGVILLE-CTTNWD 4/42L RPL STRW | 31455500 | BRIDGEVILLE-COTTONWOOD | 004/042 | 70Y | E | 2020_(1a) PSPS |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.352025 | 40.3908 | ETL.1110 | 44424012 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
117396086 | T2 EI BRDGVILLE-CTTNWD 4/42R RPL STRW | 31455500 | BRIDGEVILLE-COTTONWOOD | 004/042 | 70Y | E | 2020_(1a) PSPS |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.352025 | 40.3908 | ETL.1110 | 44424013 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
117396256 | T2 DI TULE-SPRINGVILLE 25/10 RPR CNDW | 43844704 | TULE-SPRINGVILLE | 025/010 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-118.727579 | 36.1569 | ETL.9040 | 40609662 | Conductor-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Midway |  | Y - Prog Multi
117396632 | DI COLEMAN-COTTONWOOD 2/56 INST MRKW | 44309976 | COLEMAN-COTTONWOOD | 002/056 | ICW | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-122.173568 | 40.4155 | ETL.6430 | 40809542 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117396773 | T3 DI POE-RIO OSO 020/136 REPL INSS | 31454862 | POE-RIO OSO | 020/136 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.485151 | 39.695 | ETL.5540 | 40815306 | Insulator-Steel | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  | Yes
117396774 | T2NT DI CRBRY SW S-RD-MT R1/12 INST MRKS | 43897849 | CARBERRY SW STA-ROUND MTN | R001/012 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.938402 | 40.8075 | ETL.5410 | 40661613 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117396914 | T2 DI BRDGVLL-CTTNWOOD 024/210R REPL PL | 31455500 | BRIDGEVILLE-COTTONWOOD | 024/210 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.72074 | 40.3723 | ETL.1110 | 44423243 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
117396999 | DI CARIBOU-PALERMO 4/39 REPR STRT | 44070463 | CARIBOU-PALERMO | 004/039 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.54005 | 39.5163 | ETL.3190 | 40867350 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117399033 | T2NT DI DRUM-SMMT#2 9/110L RPL POLE | 31527827 | DRUM-SUMMIT #2 | 009/110 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.624533 | 39.321 | ETL.1450 | 44553634 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
117399204 | T2NT DI DRM-SUMMT #2 008/100B INST MRKW | 43939697 | DRUM-SUMMIT #2 | 008/100 | ICW | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.64029 | 39.3209 | ETL.1450 | 44553719 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117399290 | T2NT DI DRUM-SUMMIT#2 9/114R RPL POLE | 31498154 | DRUM-SUMMIT #2 | 009/114 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.620933 | 39.3211 | ETL.1450 | 44553635 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS erdy | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
117399406 | T2 DI KESWICK-TRINITY 11/136 INST GMKW | 43661466 | KESWICK-TRINITY | 011/136 | ICW | F | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-122.634596 | 40.676 | ETL.7270 | 40598899 | Guy Wire Mark /Indic-Wood | Missing | Install | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  | Yes
117399408 | T2 DI KESWICK-TRINITY 11/136 INST MRKW | 43661466 | KESWICK-TRINITY | 011/136 | ICW | F | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-122.634596 | 40.676 | ETL.7270 | 40598899 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  | Yes
117399658 | T2 DI BRDGEVLLE-CTTNWOOD 23/207R REPL PL | 31444708 | BRIDGEVILLE-COTTONWOOD | 023/207 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.71398 | 40.3728 | ETL.1110 | 44424463 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
117400350 | T3 DI VLTA-STH 0/5 RPR SPLW | 43827513 | VOLTA-SOUTH | 000/005 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.865728 | 40.4574 | ETL.8300 | 40769405 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117400351 | T3 DI VLTA-STH 0/5 RPR GYWW | 43827513 | VOLTA-SOUTH | 000/005 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.865728 | 40.4574 | ETL.8300 | 40769405 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117400352 | T3NT DI VLTA-STH 0/5 INST MRKW | 43827513 | VOLTA-SOUTH | 000/005 | ICW | F | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.865728 | 40.4574 | ETL.8300 | 40769405 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117400443 | T2 DI DRUM-SUMMIT #2 018/215R RPR STRW | 43939699 | DRUM-SUMMIT #2 | 018/215 | ICW | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.482787 | 39.3172 | ETL.1450 | 44552502 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117400448 | T2 DI DRUM-SUMMIT #2 018/215R RPL POLE | 31527827 | DRUM-SUMMIT #2 | 018/215 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.482787 | 39.3172 | ETL.1450 | 44552502 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
117401310 | T2 DI DDRUM-SUMMIT#1 26/310 INS MRKS | 43910103 | DRUM-SUMMIT #1 | 026/310 | ICS | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.337943 | 39.3104 | ETL.1440 | 40756927 | Marker (i.e. signs)-Steel | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes
117401418 | T2 DI TULE-SPRINGVILLE 26/5 RPL STRW | 31453078 | TULE-SPRINGVILLE | 026/005 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-118.71664 | 36.1602 | ETL.9040 | 40749766 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Midway |  | Y - 23 | USFS
117401522 | T2 DI CSCDE-BNTN-DESCHTES 4/102 RPL STRW | 31431551 | CASCADE-BENTON-DESCHUTES | 004/102 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.311325 | 40.5898 | ETL.6310 | 40816304 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
117401540 | T2 DI MNDO-WILTS-FRT BRAGG 40/9 RPL STRW | 31456136 | MENDOCINO-WILLITS-FORT BRAGG | 040/009 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.769486 | 39.4277 | ETL.7550 | 40861258 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville
117401597 | T2 DI PIT #7 TAP 0/4R RPL POLE | 31432828 | PIT #7 TAP | 000/004 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.985004 | 40.8433 | ETL.5442 | 44553523 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain
117401670 | T2 DI PIT #7 TAP 0/4L RPL POLE | 31432828 | PIT #7 TAP | 000/004 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.985004 | 40.8433 | ETL.5442 | 44553734 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain
117401955 | T2 DI DRUM-SUMMIT#1 26/311 INS MRKW | 43910105 | DRUM-SUMMIT #1 | 026/311 | ICW | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.334944 | 39.3112 | ETL.1440 | 40756820 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117402299 | T2 DI PALERMO-COLGATE C011/51 INST MRKS | 43900094 | PALERMO-COLGATE | C011/051 | ICS | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.39715 | 39.2958 | ETL.5360 | 40593965 | Marker (i.e. signs)-Steel | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes
117402464 | T2 DI MLN-RND MUNTAIN #2 47/233 INS GMKS | 43939115 | MALIN-ROUND MTN #2 | 047/233 | ICS | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.524441 | 41.3659 | ETL.6020 | 40657475 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117402546 | T2NT DI RND MN-CTTNWD#2 14/145 INST MRKS | 43876311 | ROUND MTN-COTTONWOOD #2 | 014/145 | ICS | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.941499 | 40.7901 | ETL.5640 | 40758125 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117402666 | T2 CLAY-MARTEL 23/326 REPL POLE | 31455189 | CLAY-MARTEL | 023/326 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | Non-WSIP | [6 empty] | '-120.836026 | 38.3525 | ETL.8250 | 40874170 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 33
117402750 | T2NT DI PIT#1 CTTNWD 17/135 PNT TWR | 43879413 | PIT #1-COTTONWOOD | 017/135 | ICS | F | Pre-2020_(3) On high spread structure | Budget Owner (Paint) |  |  | TR2 |  | North Valley | WSIP |  |  |  |  | Program | 2021 Paint took out of program due to future project to be removed with S6B7 | '-121.760596 | 40.8466 | ETL.5390 | 40760961 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117402887 | T2 DI SOB-R #1 4/32 REPAINT | 43727737 | SOBRANTE-R #1 | 004/032 | ICS | F | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) |  |  | TR2 |  | Central | WSIP | [6 empty] | '-122.289103 | 37.9187 | ETL.3770 | 40646648 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay
117403245 | T2 DI TULE-SPRINGVILLE 21/17 RPR GYWW | 43844741 | TULE-SPRINGVILLE | 021/017 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-118.78438 | 36.1327 | ETL.9040 | 40807793 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Midway |  | Y - 23
117403248 | T2 DI TULE-SPRINGVILLE 21/17 RPR STRW | 43844754 | TULE-SPRINGVILLE | 021/017 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-118.78438 | 36.1327 | ETL.9040 | 40807793 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Midway |  | Y - 23
117403599 | T2 EI BRIDGVILL-COTTNWD 33/274 RPL STRW | 31444708 | BRIDGEVILLE-COTTONWOOD | 033/274 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.902454 | 40.3663 | ETL.1110 | 44424385 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
117403742 | T2NT DI DRUM-SUMMIT #2 020/240 INST MRKW | 43947609 | DRUM-SUMMIT #2 | 020/240 | ICW | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.446359 | 39.3183 | ETL.1450 | 44559082 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117403749 | T2NT DI DRUM-SUMMIT #2 020/240 INST MRKW | 43947609 | DRUM-SUMMIT #2 | 020/240 | ICW | E | Pre-2020_(1b) Lines with special commitments |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-120.446359 | 39.3183 | ETL.1450 | 44559084 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117404160 | T2NT DI DRUM-SUMMIT #2 020/238 INS MRKW | 43947609 | DRUM-SUMMIT #2 | 020/238 | ICW | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.449412 | 39.3179 | ETL.1450 | 44559066 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117404386 | T2 DI ROCK CREEK-POE 1/11 INST MRKS | 43878132 | ROCK CREEK-POE | 001/011 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.362689 | 39.8992 | ETL.5630 | 40590787 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117404412 | T2 DI ROCK CREEK-POE 006/045 INS MRKS | 43878133 | ROCK CREEK-POE | :006/045 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.30877 | 39.9421 | ETL.5630 | 40758306 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117404670 | T2 DI TULE-SPRINGVILLE 24/4 RPL STRW | 31454783 | TULE-SPRINGVILLE | 024/004 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-118.751137 | 36.1503 | ETL.9040 | 40749803 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Midway |  | Y - 23 | USFS
117405390 | T2NT DI MN-RND MTN #2 082/419A INS GMKS | 43939115 | MALIN-ROUND MTN #2 | 082/419A | ICS | F | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.913876 | 40.9704 | ETL.6020 | 41162607 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117405417 | T2NT DI MLIN-RD MTN #2 082/419B INS GMKS | 43939115 | MALIN-ROUND MTN #2 | 082/419B | ICS | F | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.914197 | 40.9704 | ETL.6020 | 41162606 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117407843 | T3 DI MORAGA-OAKLAND #1 000/004 RPR STRT | 44169721 | MORAGA-OAKLAND #1 | 000/004 | ICQ | E | Pre-2020_(2) High fire spread TD |  |  |  | TR3 | LATE | Central | WSIP |  |  |  | REJECT: Crew reported work not needed. Engineer reviewed and disagreed. Please complete work required and resubmit. | Project | 2021- Late due to project not being funded for 2020 | '-122.170377 | 37.8467 | ETL.2720 | 40745865 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 6
117407845 | T2 DI PIT #3-PIT #1 000/005 RPR SPLS | 43877630 | PIT #3-PIT #1 | 000/005 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.505227 | 40.9873 | ETL.5400 | 40762212 | Splice-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117408003 | T2 DI COT BEN #1 8/216 RPR GYWW | 43895726 | COTTONWOOD-BENTON #1 | 008/216 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.364132 | 40.4926 | ETL.6640 | 40616024 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117408039 | T2 DI CSCDE-BNTON-DSCHTS A8/167 RPR GYWW | 43690811 | CASCADE-BENTON-DESCHUTES | A008/167 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.258917 | 40.5586 | ETL.6310 | 40660592 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117408195 | T2 DI TESLA-METCALF 21/89 INST GMKS |  | TESLA-METCALF | 021/089 | ICS | F | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-121.659318 | 37.4123 | ETL.6110 | 40869059 | Marker (i.e. signs)-Steel | Missing | Install |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  | Y - Prog Multi
117408505 | T3 DI PARADISE-TBL MTN 19/156L RPL POLE | 31453760 | PARADISE-TABLE MTN | 019/156 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.553285 | 39.6864 | ETL.4316 | 44383197 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
117408507 | T2 DI PARADISE-TBL MTN 6/55CC RPL STRW | 31453760 | PARADISE-TABLE MTN | 006/055CC | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.536794 | 39.5465 | ETL.4316 | 41184209 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
117408508 | T3 DI PARADISE-TBL MTN 19/156R RPL STRW | 31453760 | PARADISE-TABLE MTN | 019/156 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.553285 | 39.6864 | ETL.4316 | 44383198 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
117408587 | T2 DI CARIBOU#2 16/11 INST HRDD | 43854201 | CARIBOU #2 | 016/011 | ICW | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.089685 | 40.0149 | ETL.6280 | 44217550 | Hardware-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117408588 | T2 DI HAT CRK #1 WES 18/351 RPR GYWW | 43939287 | HAT CREEK #1-WESTWOOD | 018/351 | ICW | E | Pre-2020_(2) High fire spread TD |  | Email request sent to [REDACTED] to [REDACTED] . The down guys are attched by a 3rd party. Reference the placement of the down guys in the photos | CIRT can convert to LR if needed. | TR2 | LATE | North Valley | WSIP |  |  |  |  | CIRT | Tag to be DLFG. Non pge down guys. | '-121.297518 | 40.7605 | ETL.7030 | 40876270 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117408671 | T2 DI PRDS-TBL MT 20/159L RPL POLE | 31453760 | PARADISE-TABLE MTN | 020/159 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.561043 | 39.6874 | ETL.4316 | 44383200 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
117408673 | T2 DI PRDS-TBL MT 20/159R RPL POLE | 31453760 | PARADISE-TABLE MTN | 020/159 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.561043 | 39.6874 | ETL.4316 | 44383202 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
117408720 | T2 DI ROCK CREEK-POE 003/030 REPAINT | 43878133 | ROCK CREEK-POE | 003/030 | ICS | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.381175 | 39.8713 | ETL.5630 | 40608900 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117408916 | T2 HUMBOLDT-TRINITY 059/002 RMV DEBRIS | 44311171 | HUMBOLDT-TRINITY | 059/002 | ICW | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.154046 | 40.7579 | ETL.1820 | 44560547 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
117408951 | T2 HUMBOLDT-TRINITY 060/001 RMV BUTTS | 43729542 | HUMBOLDT-TRINITY | 060/001 | ICW | F | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.167925 | 40.7509 | ETL.1820 | 44565330 | Structure-Wood | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2019-08-30
117408952 | T2 HUMBOLDT-TRINITY 52/04L RMV BUTT | 44311174 | HUMBOLDT-TRINITY | 052/004 | ICW | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-123.054245 | 40.7433 | ETL.1820 | 44557451 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2019-08-30
117409006 | T3 DI PARADISE-TBL MTN 22/172 RPL PL | 31453760 | PARADISE-TABLE MTN | 022/172 | 70Y | E | 2020_(1a) PSPS |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.599544 | 39.6936 | ETL.4316 | 44383223 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
117409007 | T3 DI PARADISE-TBL MTN 22/172 RPL PL | 31453760 | PARADISE-TABLE MTN | 022/172 | 70Y | E | 2020_(1a) PSPS |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.599544 | 39.6936 | ETL.4316 | 44383224 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
117409031 | T2 BUCKS CRK-RCK CRK-CRSTA 6/52 RPL INSS | 31462237 | BUCKS CREEK-ROCK CREEK-CRESTA | 006/052 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-121.416699 | 39.8427 | ETL.4430 | 40726097 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  | Yes
117409052 | T2 DI WEIMAR-HALSEY 2/46 RPL STRW | 31454601 | WEIMAR-HALSEY | 002/046 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.999683 | 39.0055 | ETL.8340 | 40824414 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
117409102 | T3 DI PARADISE-TBL MTN 22/172 RPL PL | 31453760 | PARADISE-TABLE MTN | 022/172 | 70Y | E | 2020_(1a) PSPS |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.599544 | 39.6936 | ETL.4316 | 44383225 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
117409104 | T3 DI MIDDLE FORK#1 8/112 INS GYWW | 43852560 | MIDDLE FORK #1 | 008/112 | ICW | E | Pre-2020_(9a) Other ignition related |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.721797 | 39.0022 | ETL.8405 | 40611426 | Guy Wire-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117409142 | DI CSCDE-BNTN-DSCHUTS A009/188 RPR GYWW | 43690811 | CASCADE-BENTON-DESCHUTES | A009/188 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-122.239968 | 40.5556 | ETL.6310 | 40868661 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117409159 | T2 DI TULE-SPRINGVILLE 017/010 RPR STRW | 44323688 | TULE-SPRINGVILLE | 017/010 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-118.838617 | 36.1104 | ETL.9040 | 40609770 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Midway |  | Y - 23
117409294 | T2 DI TEJON-LEBEC 011/195 RPR GYWW | 43862364 | TEJON-LEBEC | 011/195 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-118.889078 | 34.8712 | ETL.9250 | 40764570 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Midway |  | Y - Prog Multi
117409596 | T2 DI PARADISE-TBL MTN 25/192R RPL POLE | 31453760 | PARADISE-TABLE MTN | 025/192 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.657896 | 39.7015 | ETL.4316 | 44383251 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
117409721 | T2 DI PARADISE-TBL MT 006/055BB RPL POLE | 31453760 | PARADISE-TABLE MTN | 006/055BB | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.537116 | 39.5472 | ETL.4316 | 41184212 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
117409914 | T2NT DI DRUM-SUMMIT #2 020/238 INS MRKW | 43947609 | DRUM-SUMMIT #2 | 020/238 | ICW | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.449412 | 39.3179 | ETL.1450 | 44558961 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117413170 | T2 DI PARADISE-TBL MT 006/055BC RPL POLE | 31453760 | PARADISE-TABLE MTN | 006/055BC | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.537064 | 39.5472 | ETL.4316 | 41184213 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
117416156 | T2 DI TESLA-METCALF 32/135 RPL INSS | 31460740 | TESLA-METCALF | 032/135 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-121.729081 | 37.2585 | ETL.6110 | 40782565 | Insulator-Steel | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - Prog Multi
117416167 | T2 DI PARADISE-TABLE MTN 6/55CA RPL STRW | 31453760 | PARADISE-TABLE MTN | 006/055CA | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.536926 | 39.5464 | ETL.4316 | 41184214 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
117416486 | T2 EI SLT SPRGS-TGR CRK 000/002 PNT STRS | 43852651 | SALT SPRINGS-TIGER CREEK | 000/002 | ICS | F | Pre-2020_(3) On high spread structure | Budget Owner (Paint) |  |  | TR2 |  | Central | WSIP |  |  |  |  | Program | 2021- Paint Program | '-120.220393 | 38.4965 | ETL.3500 | 40643380 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Released
117416506 | T2 DI MALIN-RND MTN#2 92/470A INST GMKS | 43621093 | MALIN-ROUND MTN #2 | 092/470A | ICQ | F | Pre-2020_(1b) Lines with special commitments |  |  | Likely MAT error - delink to correct | TR2 | WECC | North Valley | WSIP | [6 empty] | '-121.911181 | 40.831 | ETL.6020 | 41162774 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117416607 | DI CARIBOU-PALERMO 1/12 BEMT MEMBER | 44069801 | CARIBOU-PALERMO | 001/012 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.541011 | 39.4665 | ETL.3190 | 40674849 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
117416620 | T2 DI DRUM-SMMT 8/101L RPL POLE | 31508705 | DRUM-SUMMIT #1 | 008/101 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.641466 | 39.3178 | ETL.1440 | 44768891 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
117416622 | 008/101 RIGHT SINGLE WOOD POLE | 31508705 | DRUM-SUMMIT #1 | 008/101 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.641466 | 39.3178 | ETL.1440 | 44768892 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
117416687 | EI HAT CRK #1-WESTWOOD 026/506 REPL STRW | 31456189 | HAT CREEK #1-WESTWOOD | 026/506 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | North Valley | Non-WSIP | [6 empty] | '-121.195935 | 40.672 | ETL.7030 | 40868480 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain
117417103 | T2NT DI PALERMO COLG C10/48 INST MRKS | 43900094 | PALERMO-COLGATE | C010/048 | ICS | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.38447 | 39.2988 | ETL.5360 | 40870439 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes
117417148 | T2NT DI POE-RIO OSO 024/162 PNT TWR | 43875008 | POE-RIO OSO | 024/162 | ICS | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.512229 | 39.6377 | ETL.5540 | 40673042 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117417247 | T2 DI PALERMO-COLGATE C10/46 INST MRKS | 43900094 | PALERMO-COLGATE | C010/046 | ICS | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.376645 | 39.3006 | ETL.5360 | 40815687 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes
117418273 | DI DRUM-SUMMIT #1 023/278R RPL PL | 31498145 | DRUM-SUMMIT #1 | 023/278 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-120.388359 | 39.3113 | ETL.1440 | 44767636 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS erdy | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
117418464 | T2 EXCHEQUER-YOSEMITE 000/001A INST GMKS | 43863013 | EXCHEQUER-YOSEMITE | 000/001A | ICS | F | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-119.986024 | 37.5935 | ETL.8650 | 43250171 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  | Y - 36
117418499 | EI VALLEY SPRINGS #1 010/212 RPR STRW | 44290816 | VALLEY SPRINGS #1 | 010/212 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-120.8986 | 38.1147 | ETL.8210 | 40908297 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 23
117418853 | T2 EI DRUM-SUMMIT #1 023/276 INST MRKW | 43910107 | DRUM-SUMMIT #1 | 023/276 | ICW | E | Pre-2020_(1b) Lines with special commitments |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-120.391738 | 39.3112 | ETL.1440 | 44767658 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117418939 | T3 DI CARIBOU-PALERMO :031/251 HANGER | 44304491 | CARIBOU-PALERMO | :031/251 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.460406 | 39.7663 | ETL.3190 | 40591572 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain
117418972 | T3 DI CARIBOU-PALERMO :031/251 REPR STRT | 44056495 | CARIBOU-PALERMO | :031/251 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.460406 | 39.7663 | ETL.3190 | 40591572 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
117419112 | T2 DI BALCH-SANGER 006/036 RPR STRS | 43845834 | BALCH-SANGER | 006/036 | ICS | E | Pre-2020_(5) TD tag on other lines | Superintendent Approved work efficiency |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-119.165481 | 36.8888 | ETL.1050 | 40807129 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Fresno |  | Y - 16
117427006 | T2 DI DRUM-SUMMIT #2 009/112 INS MRKW | 43939697 | DRUM-SUMMIT #2 | 009/112 | ICW | E | Pre-2020_(1b) Lines with special commitments |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-120.622018 | 39.321 | ETL.1450 | 44553510 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117427060 | DI CARIBOU-PALERMO 1/14 RPL HRDS | 44069801 | CARIBOU-PALERMO | 001/014 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | North Valley | WSIP | FSRP |  |  |  | Field Operations |  | '-121.540504 | 39.4726 | ETL.3190 | 40793708 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
117427062 | DI PALERMO-OROVILLE #2 1/17 RPL INSS | 31486385 | PALERMO-OROVILLE #2 | 001/017 | 93K | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-121.539763 | 39.4683 | ETL.7740 | 42577600 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  | Yes
117427063 | T2NT DI PARADISE-TBL MTN 12/107 PNT TWR | 43727174 | PARADISE-TABLE MTN | 012/107 | ICS | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.511181 | 39.6384 | ETL.4316 | 40819272 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117427064 | DI CARIBOU-PALERMO 1/14 RMV VEGN | 44070463 | CARIBOU-PALERMO | 001/014 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  | Likely veg |  | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.539763 | 39.4683 | ETL.3190 | 40762749 | Structure-Steel | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117427066 | DI CARIBOU-PALERMO 1/14 INS HRDS | 44070463 | CARIBOU-PALERMO | 001/014 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  |  | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.539763 | 39.4683 | ETL.3190 | 40762749 | Hardware-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117427069 | DI CARIBOU-PALERMO 1/14 RPR STRT | 44069801 | CARIBOU-PALERMO | 001/014 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.539763 | 39.4683 | ETL.3190 | 40762749 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
117427071 | T2NT DI MLN-RND MTN #2 060/298 INST GMKS | 44305271 | MALIN-ROUND MTN #2 | 060/298 | ICS | F | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | WECC | North Valley | WSIP | [6 empty] | '-121.650135 | 41.2114 | ETL.6020 | 40868963 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117427085 | T2NT DI DRUM-SUMMIT #2 010/127 RPL POLE | 31451466 | DRUM-SUMMIT #2 | 010/127 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [8 empty] | ETL.1450 | 44212219 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
117427321 | T2 DI WEIMAR-HALSEY 005/118 RPL STRW | 31509756 | WEIMAR-HALSEY | 005/118 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.032831 | 38.9675 | ETL.8340 | 40693594 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
117427435 | DI CSCD-BNTN-DSCHTS A005/109 RPR STRW | 43690811 | CASCADE-BENTON-DESCHUTES | A005/109 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-122.297935 | 40.5886 | ETL.6310 | 40759316 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117427711 | DI CLEAR LAKE-HOPLAND 0/1 REPL PL | 31471834 | CLEAR LAKE-HOPLAND | 000/001 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | North Coast | WSIP | FSRP | [5 empty] | '-123.080952 | 38.973 | ETL.6390 | 40584484 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville
117427728 | T2 DI DRUM-SUMMIT #2 021/254C REPL POLE | 31453742 | DRUM-SUMMIT #2 | 021/254 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-120.42614 | 39.3272 | ETL.1450 | 44553513 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
117428019 | T2NT DI CARIBOU #2 023/620 INST MRKW | 43854201 | CARIBOU #2 | 023/620 | ICW | F | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.970462 | 40.0393 | ETL.6280 | 44259137 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117428416 | T2NT DI TABLE MTN-PALERMO 9/44 INST HV | 44154424 | TABLE MTN-PALERMO | 009/044 | ICS | F | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.502375 | 39.5196 | ETL.5690 | 40753651 | Marker (i.e. signs)-Steel | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117428419 | T3 DI KILARC-CEDAR CRK 7/163 RPL PL | 31496893 | KILARC-CEDAR CREEK | 007/163 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-122.000577 | 40.717 | ETL.7290 | 40759575 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
117428613 | T2 DI MNDCN-WLLTS-FRT BRGG 39/4 RPR INSW | 43877954 | MENDOCINO-WILLITS-FORT BRAGG | 039/004 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.749607 | 39.4148 | ETL.7550 | 40750970 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
117428619 | T2 DI MNDCN-WLLTS-FRT BRGG 39/4 RPR CRSW | 43877954 | MENDOCINO-WILLITS-FORT BRAGG | 039/004 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.749607 | 39.4148 | ETL.7550 | 40750970 | Crossarm-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
117428878 | T2 DI APPLE HILL #2 TAP 000/016 RPL STRW | 31423866 | APPLE HILL #2 TAP | 000/016 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-120.682448 | 38.7491 | ETL.1541 | 40804792 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
117429017 | T2NT DI SMRTVLLE-NICLS #2 2/43 INST MRKS | 43938537 | SMARTVILLE-NICOLAUS #2 | 002/043 | ICS | F | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.307169 | 39.1807 | ETL.8000 | 44179464 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento
117429241 | T2 DI SBRNT-GRZZL-CLRMNT#1 6/54 BENT MBR | 43752388 | SOBRNTE-GRIZZLY-CLARMNT #1+ | 006/054 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  | Likely MAT error - delink to correct | TR2 | LATE | Central | WSIP | [6 empty] | '-122.228018 | 37.8479 | ETL.3740 | 40580980 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog Multi
117429345 | T3 DI DEER CREEK-DRUM 5/137 REM VEG |  | DEER CREEK-DRUM | 005/137 | HNA | E | Pre-2020_(9a) Other ignition related |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.776436 | 39.2601 | ETL.6690 | 40874914 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  | Yes
117429391 | T2 DI HAT CRK#1-PIT#1 6/82 RPR GYWW | 43685158 | HAT CREEK #1-PIT #1 | 006/082 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.544773 | 40.9291 | ETL.7020 | 41149286 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117429411 | T3NT DI TGER CRK-VLLY SPRNGS 0/1 REPAINT | 43852921 | TIGER CREEK-VALLEY SPRINGS | 000/001 | ICS | F | Pre-2020_(9a) Other ignition related |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-120.493507 | 38.4517 | ETL.5790 | 40596593 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - 11
117429470 | T2NT DI MALIN-RND MTN #2 79/404 INS GMKW | 43621093 | MALIN-ROUND MTN #2 | 079/404 | ICQ | F | Pre-2020_(1b) Lines with special commitments |  |  | Likely MAT error - delink to correct | TR2 | WECC | North Valley | WSIP | [6 empty] | '-121.893581 | 41.0085 | ETL.6020 | 40745485 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117429554 | T2NT DI MALIN-RND MTN #2 80/407 INS GMKS | 43621093 | MALIN-ROUND MTN #2 | 080/407 | ICQ | F | Pre-2020_(1b) Lines with special commitments |  |  | Likely MAT error - delink to correct | TR2 | WECC | North Valley | WSIP | [6 empty] | '-121.896068 | 41.0026 | ETL.6020 | 40810966 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117430095 | T3 DI CARIBOU-PALERMO :011/087 REPR INSS | 44304491 | CARIBOU-PALERMO | :011/087 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.280057 | 39.9886 | ETL.3190 | 40910327 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain
117430536 | T2NT DI OLEUM-G #1 2/16 REPAINT | 44586166 | OLEUM-G #1 | 002/016 | ICS | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-122.234101 | 38.0277 | ETL.3150 | 40804783 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay
117430539 | T3 DI DRUM-HIGGINS 009/093 REPR GYWW | 43852139 | DRUM-HIGGINS | 009/093 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.8911 | 39.1763 | ETL.4393 | 44172115 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117430585 | T3NT DI DRUM-HIGGINS 009/093 INST GMKW | 43852139 | DRUM-HIGGINS | 009/093 | ICW | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.8911 | 39.1763 | ETL.4393 | 44172115 | Guy Wire Mark /Indic-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117430611 | T2 EI CORDELIA #2 003/061A REPL STRW | 31454608 | CORDELIA #2 TAP | 003/061A | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.147987 | 38.2445 | ETL.8184 | 40577175 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento
117430834 | T2 DI MTN QUARRIES TAP 0/19 RPR GYWW | 43869988 | MTN QUARRIES TAP | 000/019 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.049617 | 38.9145 | ETL.6991 | 40589600 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
117431485 | T2NT DI MLN-RND MTN#2 72/363 INST GMKS | 44305271 | MALIN-ROUND MTN #2 | 072/363 | ICS | F | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | WECC | North Valley | WSIP | [6 empty] | '-121.798404 | 41.0772 | ETL.6020 | 40663115 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117431594 | T2 HMILTON BRNCH-CHSTER 0/014 RPL STRW | 31454645 | HAMILTON BRANCH-CHESTER | 000/014 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-121.083582 | 40.2744 | ETL.7000 | 40701185 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
117431622 | T2 DI CLEAR LAKE-HOPLAND 1/4 RPL PL | 31501061 | CLEAR LAKE-HOPLAND | 001/004 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | FSRP | [5 empty] | '-123.058481 | 38.9685 | ETL.6390 | 40750154 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  | 2019-07-19
117431690 | T3NT DI MRGA-SN LNDRO #3 003/021 REPAINT | 43728142 | MORAGA-SAN LEANDRO #3 | 003/021 | ICS | F | Pre-2020_(9a) Other ignition related | Budget Owner (Paint) |  |  | TR3 |  | Central | WSIP | [6 empty] | '-122.138206 | 37.8142 | ETL.2790 | 40580824 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay
117432050 | T2 DI COLEMAN-SOUTH 7/156 RPR JUMW | 43930460 | COLEMAN-SOUTH | 007/156 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.008965 | 40.4031 | ETL.6450 | 40721962 | Jumper-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117432432 | T3NT DI DESABLA-CENTERVILLE 0/0 PNT STRS | 43854279 | DESABLA-CENTERVILLE | 000/000 | ICS | F | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.631584 | 39.8689 | ETL.6720 | 44181036 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117432457 | NT DI HALSEY-PLACER 000/011 INST MRKW | 43869582 | HALSEY-PLACER | 000/011 | ICW | F | Pre-2020_(5b) On structure in bucket 5 | [5 empty] | North Valley | WSIP | [6 empty] | '-121.048355 | 38.9513 | ETL.6990 | 40767376 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117432704 | DI SPAULDING-SUMMIT 8/269 INST MRKW | 43923448 | SPAULDING-SUMMIT | 008/269 | ICW | E | Pre-2020_(1b) Lines with special commitments |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-120.519483 | 39.3113 | ETL.8060 | 40586093 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117432757 | DI TRACY-LOS BANOS 008/043 RPL RPTS | 43851677 | TRACY-LOS BANOS | 008/043 | ICB | E | Pre-2020_(9a) Other ignition related |  |  |  |  | LATE | Central | WSIP | FSRP | [5 empty] | '-121.532636 | 37.6926 | ETL.6130 | 40651814 | Raptor Guard-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 593 | Victor |  | Released
117432773 | T2 DI KONOCTI-MIDDLETOWN 12/1A RPR GYWW | 43919877 | KONOCTI-MIDDLETOWN | 012/001A | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.609195 | 38.7532 | ETL.6380 | 44371580 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  | 2019-07-19
117432814 | T2 DI LWR LK-HMSTK 13/13 BOND SPLIT BOLT | 43865623 | LOWER LAKE-HOMESTAKE TAP | 013/013 | ICW | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | WSIP | FSRP | [5 empty] | '-122.411565 | 38.8623 | ETL.1481 | 40648971 | Hardware-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  | 2019-07-02
117432947 | T2 DI SMRTVLL-CMP FR WST 14/272 RMV STRW | 43852549 | SMARTVILLE-CAMP FAR WEST | 014/272 | ICW | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.307871 | 39.0325 | ETL.7970 | 40673317 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117433130 | T2NT DI ORL-TT-TBL MT#1 002/009 INS MRKS | 43932169 | MTN #1(CDWR) | 002/009 | ICS | F | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.512072 | 39.5465 | ETL.6621 | 42580632 | Marker (i.e. signs)-Steel | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117433133 | T2 DI CSCD-BNTN-DSCHTES 2/57 INS GYWW | 43690811 | CASCADE-BENTON-DESCHUTES | 002/057 | ICW | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.322291 | 40.6194 | ETL.6310 | 40600665 | Guy Wire-Wood | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117433135 | T2 DI CSCD-BNTN-DSCHTES 2/57 RPR SPLW | 43690811 | CASCADE-BENTON-DESCHUTES | 002/057 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.322291 | 40.6194 | ETL.6310 | 40600665 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117433163 | T2 DI FLTN-MOLNO-COTATI 16/309 INS BOND | 43920595 | FULTON-MOLINO-COTATI | 016/309 | ICW | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | WSIP | FSRP | [5 empty] | '-122.732804 | 38.3098 | ETL.6910 | 40877338 | Hardware-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  | 2019-08-05
117433194 | T2 DI MALIN-RND MTN #2 66/331 INST GMKS | 44305271 | MALIN-ROUND MTN #2 | 066/331 | ICS | F | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | WECC | North Valley | WSIP | [6 empty] | '-121.719174 | 41.1398 | ETL.6020 | 40586427 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117433382 | T2 DI LOWER LAKE-HOMESTAKE 3/11 INS HRDW | 43865623 | LOWER LAKE-HOMESTAKE TAP | 003/011 | ICW | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | WSIP | FSRP | [5 empty] | '-122.566579 | 38.8991 | ETL.1481 | 44401312 | Hardware-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  | 2019-07-02
117433446 | T2 DI KONOCTI-MIDDLETOWN 24/5 RPL STRW | 31490901 | KONOCTI-MIDDLETOWN | 024/005 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.708489 | 38.9205 | ETL.6380 | 40747632 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  | 2019-07-26
117433580 | DI TRACY-LOS BANOS 008/045 RPR GYWS | 43851678 | TRACY-LOS BANOS | 008/045 | ICS | E | Pre-2020_(5) TD tag on other lines |  |  | Tower guy |  | LATE | Central | WSIP | [6 empty] | '-121.526956 | 37.6901 | ETL.6130 | 40753747 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Victor |  | Y - Prog Multi
117433617 | T2 DI TULE-SPRINGVILLE 20/9 INST GYWW | 44323689 | TULE-SPRINGVILLE | 020/009 | ICW | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | South | WSIP | FSRP | [5 empty] | '-118.804742 | 36.137 | ETL.9040 | 40873006 | Guy Wire-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Midway |  | Y - 23
117433951 | T2 DI DRUM-SUMMIT#2 19/236 INS MRKW | 43947609 | DRUM-SUMMIT #2 | 019/236 | ICW | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.453362 | 39.3182 | ETL.1450 | 44558995 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117434241 | T2 DI RND MTN-CTTNWOOD#3 43/371 PNT STRS | 43755801 | ROUND MTN-COTTONWOOD #3 | 043/371 | ICQ | F | Pre-2020_(4b) On structure in bucket 4 |  |  | Likely MAT error - delink to correct | TR2 |  | North Valley | WSIP | [6 empty] | '-122.104095 | 40.5933 | ETL.5650 | 40595049 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117434309 | T2 DI KONOCTI-MIDDLETOWN 24/3 RPR GYWS | 43908958 | KONOCTI-MIDDLETOWN | 024/003 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.712219 | 38.9215 | ETL.6380 | 44244869 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville |  |  | 2019-07-26
117434640 | T2 DI IGN ALT SAU #2 16/114 GRND WSH INS | 43919392 | IGNACIO-ALTO-SAUSALITO #2 | 016/114 | ICD | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.502237 | 37.8598 | ETL.7170 | 40740661 | Insulator | Contaminated | Ground Wash | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 622 | Lakeville |  |  | 2019-07-12
117434748 | DI CASCADE-BNTN-DSCHTS A5/110 RPR INSW | 43690811 | CASCADE-BENTON-DESCHUTES | A005/110 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-122.296814 | 40.5886 | ETL.6310 | 40759477 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117434830 | DI CASCADE-BNTN-DSCHTS A5/110 INS MRKW | 43690811 | CASCADE-BENTON-DESCHUTES | A005/110 | ICW | F | Pre-2020_(5b) On structure in bucket 5 | [5 empty] | North Valley | WSIP | [6 empty] | '-122.296814 | 40.5886 | ETL.6310 | 40759477 | Marker (i.e. signs)-Wood | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117434936 | T2NT DI RND MTN-CTTNWD 024/217 INST MRKS | 43877040 | ROUND MTN-COTTONWOOD #2 | 024/217 | ICS | F | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.05913 | 40.6769 | ETL.5640 | 40815315 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117434993 | T3 DI DRUM-HIGGINS 2/24L RPL PL | 31509929 | DRUM-HIGGINS | 002/024 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.790597 | 39.2305 | ETL.4393 | 44172164 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE erdy | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
117434995 | T3 DI DRUM-HIGGINS 2/24R RPL PL | 31509929 | DRUM-HIGGINS | 002/024 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.790597 | 39.2305 | ETL.4393 | 44172165 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE erdy | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
117435035 | T2 DI COLGATE-PALERMO 010/201 RPR GYWW | 43878561 | COLGATE-PALERMO | 010/201 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.363655 | 39.3656 | ETL.6500 | 40767115 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117435038 | T2NT DI COLGATE-PALERMO 010/201 INS MRKW | 43878563 | COLGATE-PALERMO | 010/201 | ICW | F | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.363655 | 39.3656 | ETL.6500 | 40767115 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117435170 | T2 DI EL DRD-MSSR FLT #1 10/084 RPR GYWW | 43748116 | ELDORADO-MISSOURI FLAT #1 | 010/084 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.77909 | 38.7399 | ETL.1530 | 40760877 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117435306 | T2 DI SPAULDING-SUMMIT 002/108 RPL POLE | 31453471 | SPAULDING-SUMMIT | 002/108 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.59853 | 39.3138 | ETL.8060 | 40618288 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
117435564 | T2 DI CTTNWOD-RED BLUFF014/290 RPR STRW | 43939201 | COTTONWOOD-RED BLUFF | 014/290 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.254537 | 40.217 | ETL.6660 | 40909626 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117435567 | T2 DI CTTNWOD-RED BLUFF 14/290 INST MRKW | 43744380 | COTTONWOOD-RED BLUFF | 014/290 | ICW | F | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.254537 | 40.217 | ETL.6660 | 40909626 | Marker (i.e. signs)-Wood | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117435772 | T3 DI KILARC-CDR CRK 13/285 RPL PL | 31459424 | KILARC-CEDAR CREEK | 013/285 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.937812 | 40.7911 | ETL.7290 | 40810437 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
117435865 | T2NT DI MLN-RND MTN#2 079/403 INST GMKS | 43621093 | MALIN-ROUND MTN #2 | 079/403 | ICQ | F | Pre-2020_(1b) Lines with special commitments |  |  | Likely MAT error - delink to correct | TR2 | WECC | North Valley | WSIP | [6 empty] | '-121.893136 | 41.0108 | ETL.6020 | 40650409 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117436101 | T2 DI SPAULDING-SUMMIT 001/074 INST GMKW | 43923456 | SPAULDING-SUMMIT | 001/074 | ICW | F | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.615578 | 39.3106 | ETL.8060 | 40652032 | Guy Wire Mark /Indic-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117436102 | T2 DI SPAULDING-SUMMIT 001/074 INST MRKW | 43923456 | SPAULDING-SUMMIT | 001/074 | ICW | F | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.615578 | 39.3106 | ETL.8060 | 40652032 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117436509 | T2 DI SPAULDING-SUMMIT 0/10 INS MRKW | 43923456 | SPAULDING-SUMMIT | 000/010 | ICW | F | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.640687 | 39.3238 | ETL.8060 | 40589998 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117436556 | T2 EI TRINITY-MAPLE CRK 014/004 RPL INSW | 31472111 | TRINITY-MAPLE CREEK | 014/004 | 93I | E | Pre-2020_(2) High fire spread TD |  |  |  | TR2 | LATE | North Coast | WSIP |  |  |  |  | Weather | AT RISK - weather impacts | '-123.306668 | 40.7074 | ETL.8170 | 40781218 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Eureka |  |  | 2019-10-23
117436625 | DI CARIBOU-PALERMO 1/12 RPR STRT | 43932153 | CARIBOU-PALERMO | 001/012 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.541011 | 39.4665 | ETL.3190 | 40674849 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
117436626 | T2 DI KONOCTI-MIDDLETON 20/0 RPR GYWW | 43919877 | KONOCTI-MIDDLETOWN | 020/000 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.586176 | 38.8518 | ETL.6380 | 40615071 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  | 2019-07-26
117436967 | T2NT DI SPAULDING-SMMT 000/035 INST MRKW | 43923456 | SPAULDING-SUMMIT | 000/035 | ICW | F | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.628119 | 39.3213 | ETL.8060 | 40746162 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117437029 | T2 DI SBRNT-GRZZLY-CLRMT#1 0/10 RPR FOND | 43752388 | SOBRNTE-GRIZZLY-CLARMNT #1+ | 000/010 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  | Likely MAT error - delink to correct | TR2 | LATE | Central | WSIP | [6 empty] | '-122.204643 | 37.9015 | ETL.3740 | 40770752 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 7
117437064 | T2 EI IGNCO-ALTO-SSLTO #1 11/80 RMV VEGN |  | IGNACIO-ALTO-SAUSALITO #1 | 011/080 | HNA | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.516967 | 37.9081 | ETL.7160 | 40754844 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Lakeville
117437105 | T2 DI SPAULDING-SUMMIT 0/34 INST MRKW | 43923456 | SPAULDING-SUMMIT | 000/034 | ICW | F | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.628689 | 39.3214 | ETL.8060 | 40751892 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117437273 | T2 DI TULE-SPRINGVILLE 013/009 WASH INSW | 44637082 | TULE-SPRINGVILLE | 013/009 | ICD | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-118.907348 | 36.1098 | ETL.9040 | 40872985 | Insulator | Contaminated | Ground Wash | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 622 | Midway |  | Y - 23
117437393 | T2NT DI SPLDNG-SMMT 002/079 INST MRKW | 43923456 | SPAULDING-SUMMIT | 002/079 | ICW | F | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.613407 | 39.311 | ETL.8060 | 40603894 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117437417 | T2 DI SPAULDING-SUMMIT 10/351 RPL STRW | 31495368 | SPAULDING-SUMMIT | 010/351 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.473081 | 39.3179 | ETL.8060 | 44224995 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
117437984 | T2 DI TULE-SPRINGVILLE 018/010 WASH INSW | 44637082 | TULE-SPRINGVILLE | 018/010 | ICD | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-118.828597 | 36.1185 | ETL.9040 | 40586429 | Insulator | Contaminated | Ground Wash | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 622 | Midway |  | Y - 23
117437986 | T2NT DI TULE-SPRINGVLL 018/010 INST MRKW | 44323690 | TULE-SPRINGVILLE | 018/010 | ICW | F | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-118.828597 | 36.1185 | ETL.9040 | 40586429 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Midway |  | Y - 23
117438076 | T2 DI TGR CRK-VLY SPRNG 015/126 RPR FOND | 43852924 | TIGER CREEK-VALLEY SPRINGS | 015/126 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.684586 | 38.3064 | ETL.5790 | 40765491 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - 10
117438192 | T2 DI LAYTNVLLE-WLLTS 016/004 RPL POLE | 31490917 | LAYTONVILLE-WILLITS | 016/004 | 70Y | F | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | FSRP | [5 empty] | '-123.453977 | 39.5991 | ETL.8360 | 44356041 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville
117438308 | T2 DI TULE-SPRINGVILLE 026/009 RPR SPLS | 44323595 | TULE-SPRINGVILLE | 026/009 | ICS | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-118.712372 | 36.1612 | ETL.9040 | 43604137 | Splice-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Midway |  | Y - Prog Multi
117438445 | DI DRUM-SUMMIT#2 17/211L RPL PL | 31521949 | DRUM-SUMMIT #2 | 017/211 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-120.489779 | 39.3159 | ETL.1450 | 44549869 | Structure-Wood | Rotten | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
117438525 | DI DRUM-SUMMIT#2 17/211R REPL PL | 31521949 | DRUM-SUMMIT #2 | 017/211 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-120.489779 | 39.3159 | ETL.1450 | 44549967 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Sacramento |  |  | Yes
117438541 | DI DRUM-SUMMIT#2 17/211C REPL PL | 31521949 | DRUM-SUMMIT #2 | 017/211 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-120.489779 | 39.3159 | ETL.1450 | 44549943 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
117438582 | T3 DI KLARC-CDR CRK 9/210 RPR STRW | 43685209 | KILARC-CEDAR CREEK | 009/210 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.977905 | 40.7441 | ETL.7290 | 40868041 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117438587 | T2 DI CNTRVL-TBL MTN-RVLL 10/198 INS MRK | 43903760 | CENTERVILLE-TABLE MTN-OROVILLE | 010/198 | ICW | F | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.634085 | 39.6481 | ETL.6330 | 40675499 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117438633 | T2 DI TULE-SPRINGVILLE 013/007 WASH INSW | 44637082 | TULE-SPRINGVILLE | 013/007 | ICD | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-118.909662 | 36.1097 | ETL.9040 | 40807680 | Insulator | Contaminated | Ground Wash | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 622 | Midway |  | Y - 23
117438945 | T2NT DI POE-RIO OSO 29/192 INST MRKS | 43875009 | POE-RIO OSO | 029/192 | ICS | F | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.53113 | 39.5723 | ETL.5540 | 40673050 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117439085 | T2 DI HAT CREEK #1-W WD 20/385 RPR STRW | 43736798 | HAT CREEK #1-WESTWOOD | 020/385 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.274675 | 40.742 | ETL.7030 | 40592092 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117439504 | T2 DI COLGT-PALRM 10/200 RPL STRW | 31517754 | COLGATE-PALERMO | 010/200 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.362776 | 39.3652 | ETL.6500 | 40664525 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
117439540 | T2 DI DRUM-SUMMIT#1 22/269 RPL POLE | 31498145 | DRUM-SUMMIT #1 | 022/269 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-120.402117 | 39.3104 | ETL.1440 | 40597039 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS erdy | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
117439601 | T2 DI TDEWATER-SOBRANTE 022/104 RPR FOND | 44509425 | TIDEWATER-SOBRANTE | 022/104 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.203201 | 37.9169 | ETL.5770 | 40745891 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 2 | EBMUD
117439678 | T2NT DI MI-WUK-CURTIS 023/001L CANCEL |  | ETL.1073.POLE.WDPS | 023/001 | ICW | F | Pre-2020_(4b) On structure in bucket 4 |  |  | CANCEL/CNCL | TR2 |  | Central | WSIP | [6 empty] | '-120.26918 | 38.0053 | ETL.1073 | 44774786 | Marker (i.e. signs)-Wood | Missing | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog Multi
117439727 | T2 DI TUL SPR 20/14 RPR GYWW | 44323693 | TULE-SPRINGVILLE | 020/014 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-118.801146 | 36.1375 | ETL.9040 | 40749767 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Midway |  | Y - 23
117439768 | DI KONOCTI-MIDDLETOWN 28/4 RPR STRW | 43919877 | KONOCTI-MIDDLETOWN | 028/004 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | North Coast | WSIP | [8 empty] | ETL.6380 | 44235471 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  | 2019-07-26
117439795 | DI KONOCTI-MIDDLETOWN 28/4 RPR STRW | 43919877 | KONOCTI-MIDDLETOWN | 028/004 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | North Coast | WSIP | [8 empty] | ETL.6380 | 44235473 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  | 2019-07-26
117439810 | T2 DI TUL SPR 20/14 RPR SPLW | 44323697 | TULE-SPRINGVILLE | 020/014 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-118.801146 | 36.1375 | ETL.9040 | 40749767 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Midway |  | Y - 23
117439880 | DI KONOCTI-MIDDLETOWN 28/4 RPR GYWW | 43919877 | KONOCTI-MIDDLETOWN | 028/004 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | North Coast | WSIP | [8 empty] | ETL.6380 | 44235471 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  | 2019-07-26
117439916 | DI KONOCTI-MIDDLETOWN 28/4 RPR GYWW | 43919877 | KONOCTI-MIDDLETOWN | 028/004 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | North Coast | WSIP | [8 empty] | ETL.6380 | 44235472 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  | 2019-07-26
117439934 | DI KONOCTI-MIDDLETOWN 28/4 RPR GYWW | 43919877 | KONOCTI-MIDDLETOWN | 028/004 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | North Coast | WSIP | [8 empty] | ETL.6380 | 44235473 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  | 2019-07-26
117439935 | DI KONOCTI-MIDDLETOWN 28/4 GRD WSH INSU | 43919388 | KONOCTI-MIDDLETOWN | 028/004 | ICD | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | North Coast | WSIP | [8 empty] | ETL.6380 | 44235471 | Insulator | Contaminated | Ground Wash | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 622 | Lakeville |  |  | 2019-07-26
117440045 | DI KONOCTI-MIDDLETOWN 28/4 GRD WSH INSU | 43919388 | KONOCTI-MIDDLETOWN | 028/004 | ICD | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | North Coast | WSIP | [8 empty] | ETL.6380 | 44235472 | Insulator | Contaminated | Ground Wash | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 622 | Lakeville |  |  | 2019-07-26
117440178 | T2 DI MNDCN-WLLTS-FRT BRGG 20/4 RPR GYWW | 43891087 | MENDOCINO-WILLITS-FORT BRAGG | 020/004 | ICW | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | WSIP | FSRP | [5 empty] | '-123.456285 | 39.3933 | ETL.7550 | 40769233 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
117440834 | T2 DI COLLINS PN TAP 000/027 RPR GYWW | 43919591 | COLLINS PINE TAP | 000/027 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.242703 | 40.2994 | ETL.7001 | 42623475 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117440925 | T2 SPAULDING-SUMMIT 000/011 RPL INSW | 31463883 | SPAULDING-SUMMIT | 000/011 | 93I | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-120.640432 | 39.3237 | ETL.8060 | 40610596 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Sacramento |  |  | Yes
117441193 | T2NT DI COLGATE-PALMO 004/078 INST MRKW | 43910642 | COLGATE-PALERMO | 004/078 | ICW | F | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.264242 | 39.333 | ETL.6500 | 40874639 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117441565 | DI VALLEY SPRINGS-CLAY 14/194 RPR STRW | 43853795 | VALLEY SPRINGS-CLAY | 014/194 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-120.911201 | 38.2945 | ETL.8264 | 40904795 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 12
117442542 | DI JEFFERSON-STNFRD 2/67 RPL PL | 31434138 | JEFFERSON-STANFORD (NO FLY) | 002/067 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-122.246559 | 37.4654 | ETL.7220 | 40694682 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Bay |  | Y - Prog Multi
117442609 | DI CLEAR LAKE-HOPLAND 1/7 RPL PL | 31488229 | CLEAR LAKE-HOPLAND | 001/007 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | North Coast | WSIP | FSRP | [5 empty] | '-123.055913 | 38.9663 | ETL.6390 | 40808130 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  | 2019-07-19
117442652 | T2 DI MTN GTE JCT CAS 5/57 RPR STRW | 43758388 | MTN GATE JCT-CASCADE | 005/057 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.331275 | 40.673 | ETL.7640 | 40676826 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117442699 | T2 DI WINTU TAP 001/038 RPR GYWW | 43760225 | WINTU TAP | 001/038 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.368724 | 40.5928 | ETL.6311 | 40828032 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117442840 | T2NT DI WINTU TAP 001/038 INST MRKW | 43760225 | WINTU TAP | 001/038 | ICW | F | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.368724 | 40.5928 | ETL.6311 | 40828032 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117442866 | T2 DI MAL RND MTN #2 64/323 INST GMKS | 43939115 | MALIN-ROUND MTN #2 | 064/323 | ICS | F | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.700588 | 41.1545 | ETL.6020 | 40651401 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117442940 | T2 DI JEFFERSON-STANFORD 1/42 RPR GYWW | 43877613 | JEFFERSON-STANFORD (NO FLY) | 001/042 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.259654 | 37.4634 | ETL.7220 | 40612104 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Bay |  | Y - 6
117443014 | T2 DI DRUM-SPAULDING 07/188 RPL STRW | 31502001 | DRUM-SPAULDING | 007/188 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-120.664223 | 39.3093 | ETL.6770 | 40825229 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
117443137 | T2NT DI SPAULDING-SUMMIT 1/40 INST MRKW | 43923456 | SPAULDING-SUMMIT | 001/040 | ICW | F | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.62615 | 39.3202 | ETL.8060 | 40650035 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117443276 | T2 DI DRUM-SPAULDING 08/218 RPL POLE | 31502001 | DRUM-SPAULDING | 008/218 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-120.649472 | 39.3174 | ETL.6770 | 40869678 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
117443376 | T2 DRUM-SUMMIT #2 023/276L RPL STRW | 31451466 | DRUM-SUMMIT #2 | 023/276 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-120.390765 | 39.3292 | ETL.1450 | 44557732 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Sacramento |  |  | Yes
117443385 | T3 DI GOLD HILL #1 25/368 RPL STRW | 31502809 | GOLD HILL #1 | 025/368 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.847953 | 38.5749 | ETL.6950 | 40768907 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
117443546 | T2 DI COLGATE-PALERMO 3/56 RPL PL | 31457073 | COLGATE-PALERMO | 003/056 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.250392 | 39.3241 | ETL.6500 | 40814347 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
117443558 | T3 DI FRNCH MDWS-MDL FRK 4/82 RPL POLE | 31504550 | FRENCH MEADOWS-MIDDLE FORK | 004/082 | 70Y | E | Pre-2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations | 2021 - Rock hole was not deep enough to set the pole | '-120.466787 | 39.0446 | ETL.6870 | 40751842 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
117443655 | T2 DI JEFFERSON-STANFORD 2/59 RPR GYWW | 43877613 | JEFFERSON-STANFORD (NO FLY) | 002/059 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.251859 | 37.4643 | ETL.7220 | 40767836 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Bay |  | Y - Prog Multi | 2019-07-31
117443659 | DI PITTSBURG-MARTINEZ#1 003/020 RPR FOND | 44238519 | PITTSBURG-MARTINEZ #1 | 003/020 | ICQ | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-121.915192 | 37.9986 | ETL.3320 | 40581782 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog Multi
117444561 | T3 DI FRE MEA MID FRK 4/79 RMV VEG |  | FRENCH MEADOWS-MIDDLE FORK | 004/079 | HNA | F | Pre-2020_(9a) Other ignition related |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.46371 | 39.0448 | ETL.6870 | 40693729 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  | Yes
117445285 | T2 DI CSCAD-BNTN-DESCHTS 2/57 INST MRKW | 43690811 | CASCADE-BENTON-DESCHUTES | 002/057 | ICW | F | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.322291 | 40.6194 | ETL.6310 | 40600665 | Marker (i.e. signs)-Wood | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117445449 | T3 DI DRUM-HIGGINS 010/094 RPL HRDT | 43903301 | DRUM-HIGGINS | 010/094 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.890562 | 39.1778 | ETL.4393 | 40586122 | Hardware-Tower | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento |  |  | Yes
117445504 | T2 DI KNCTI-MDDLTWN 015/000 RPR GYWW | 43919877 | KONOCTI-MIDDLETOWN | 015/000 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.574752 | 38.7821 | ETL.6380 | 44370573 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  | 2019-07-26
117445660 | T2 DI SPAULDING-SUMMIT 011/372 RPL STRW | 31495368 | SPAULDING-SUMMIT | 011/372 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.460245 | 39.3189 | ETL.8060 | 40761663 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
117445747 | T2NT DI TGR CRK-VLY SPRG 010/078 REPAINT | 43852921 | TIGER CREEK-VALLEY SPRINGS | 010/078 | ICS | F | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) |  |  | TR2 |  | Central | WSIP | [6 empty] | '-120.639514 | 38.376 | ETL.5790 | 40858394 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Released
117445751 | T2NT DI TABL MTN-PALERMO 14/65 INST MRKS | 44154424 | TABLE MTN-PALERMO | 014/065 | ICS | F | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.502559 | 39.4565 | ETL.5690 | 40757849 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117445806 | T2 DI PLCR-DL MR 5/110 RPR STRW | 43912223 | PLACER-DEL MAR | 005/110 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.15477 | 38.8523 | ETL.7800 | 40763994 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117446814 | T2 DI COLGATE-PALERMO 010/202 RPR SPLW | 43878561 | COLGATE-PALERMO | 010/202 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.364245 | 39.3661 | ETL.6500 | 40766515 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117447047 | T2NT DI PIT #5 RND MTN #1 8/81 PNT TWR | 44322478 | PIT #5-ROUND MTN #1 | 008/081 | ICS | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.92994 | 40.8824 | ETL.5420 | 40680602 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117447351 | T2 DI CLEAR LAKE-HPLND 1/2 RPL POLE | 31501313 | CLEAR LAKE-HOPLAND | 001/002 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | FSRP | [5 empty] | '-123.061092 | 38.9693 | ETL.6390 | 40699068 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  | 2019-07-19
117447352 | SAN MIGUEL-PASO ROBLES 9/150 RPL POLE | 31454632 | SAN MIGUEL-PASO ROBLES | 009/150 | 70Y | E | Pre-2020_(9b) Time-dependent non-HFTD tags, (prior to last year) |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.680402 | 35.6251 | ETL.9390 | 40754894 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Pismo Beach |  | Y - 7
117447450 | T2 DI SPAULDING-SUMMIT 015/491 INS MRKW | 43923456 | SPAULDING-SUMMIT | 015/491 | ICW | F | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.383007 | 39.3283 | ETL.8060 | 40650067 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117447457 | T2 DI HAT CREEK #1 020/398 INS MRKW | 43904280 | HAT CREEK #1-WESTWOOD | 020/398 | ICW | F | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.265607 | 40.7347 | ETL.7030 | 40770737 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117447486 | T3 DI DRUM-HIGGINS 2/27R REPL PL | 31423108 | DRUM-HIGGINS | 002/027 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.795057 | 39.2286 | ETL.4393 | 44172274 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
117447627 | T2NT DI HT CRK #1-WSTWD 21/406 INST MRKW | 43904280 | HAT CREEK #1-WESTWOOD | 021/406 | ICW | F | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.260183 | 40.7302 | ETL.7030 | 40667944 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117447776 | T2NT DI DRM SUM #2 28/333 INST GMKW | 43947608 | DRUM-SUMMIT #2 | 028/333 | ICW | F | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | WECC | North Valley | WSIP | [8 empty] | ETL.1450 | 44420820 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117447779 | T2NT DI DRM SUM #2 28/333 RPR GYWW | 43947611 | DRUM-SUMMIT #2 | 028/333 | ICW | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [8 empty] | ETL.1450 | 44420820 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117447947 | T2 DI SPAULDING-SUMMIT 001/045 INST GMKW | 43923456 | SPAULDING-SUMMIT | 001/045 | ICW | F | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.625174 | 39.3189 | ETL.8060 | 40878046 | Guy Wire Mark /Indic-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117447995 | T2 DI BRCBRG JCT-MRPSA TAP 5/14 RPR STRW | 43825046 | BRICEBURG JCT-MARIPOSA TAP | 005/014 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | South | WSIP | FSRP | [5 empty] | '-119.986086 | 37.521 | ETL.8651 | 40748193 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Fresno |  | Y - 12
117448144 | T2 DI MNDCN-WLTS-FRT-BRG 41/5 INST MRKW |  | MENDOCINO-WILLITS-FORT BRAGG | 041/005 | ICW | F | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.782483 | 39.4304 | ETL.7550 | 40750988 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
117448209 | T3NT DI MORAGA-SAN LEAND #3 4/32 PNT TWR | 43728142 | MORAGA-SAN LEANDRO #3 | 004/032 | ICS | F | Pre-2020_(9a) Other ignition related |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-122.127777 | 37.7936 | ETL.2790 | 40657111 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay
117448341 | DI HAT CREEK #1-WESTWOOD 49/952 RPL POLE | 31454829 | HAT CREEK #1-WESTWOOD | 049/952 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-121.016208 | 40.384 | ETL.7030 | 40868255 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain
117448488 | T2 DI HAT CRK #1 WWD 53/1038 INST MRKW | 43904280 | HAT CREEK #1-WESTWOOD | 053/1038 | ICW | F | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.001793 | 40.3208 | ETL.7030 | 40751794 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117448508 | T2 DI OLEUM-G #1 000/007 REPR STRT | 44229259 | OLEUM-G #1 | 000/007 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.243946 | 38.0399 | ETL.3150 | 40804762 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog Multi
117448554 | T2 DI HAT CREEK#1 WSTWOOD 2/61 RPR GYWW | 43939287 | HAT CREEK #1-WESTWOOD | 002/061 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.487518 | 40.9194 | ETL.7030 | 41198412 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117448570 | T2 DI OLEUM-G #1 000/007 PAINT STRS | 44586166 | OLEUM-G #1 | 000/007 | ICS | E | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.243946 | 38.0399 | ETL.3150 | 40804762 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  | Y - Prog Multi
117448578 | T2 DI SPAULDING-SUMMIT 001/043 REPL POLE | 31415019 | SPAULDING-SUMMIT | 001/043 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.625593 | 39.3195 | ETL.8060 | 40828117 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
117448832 | T3 DI FRNCH MDWS-MDL FRK 8/158 RPR GYWW | 43870412 | FRENCH MEADOWS-MIDDLE FORK | 008/158 | ICW | E | Pre-2020_(9a) Other ignition related |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.539137 | 39.0231 | ETL.6870 | 40611462 | Guy Wire-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117449068 | T2 DI SMTVLE-NICUS #2 0/3 GRD WASH INSS | 43938536 | SMARTVILLE-NICOLAUS #2 | 000/003 | ICD | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.303105 | 39.2076 | ETL.8000 | 44177579 | Insulator | Contaminated | Ground Wash | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 622 | Sacramento
117449644 | T2 DI HAT CRK#1 WESTWOOD 8/166 REPL PL | 31456189 | HAT CREEK #1-WESTWOOD | 008/166 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.411245 | 40.8709 | ETL.7030 | 40601695 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain
117450658 | DI TRINITY-MAPLE CREEK 0/9 RPL STRW | 31471999 | TRINITY-MAPLE CREEK | 000/009 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | North Coast | WSIP | [6 empty] | '-122.938732 | 40.7229 | ETL.8170 | 40906228 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2020-04-14
117450667 | T2 DI HAT-CREEK #1-WSTWOOD 0/20 RPL PL | 31456189 | HAT CREEK #1-WESTWOOD | 000/020 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.527695 | 40.9256 | ETL.7030 | 40815030 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain
117450687 | T2 EI TULE-SPRVILLE 026/007 RPL POLE | 31455758 | TULE-SPRINGVILLE | 026/007 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-118.71499 | 36.1606 | ETL.9040 | 40807817 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Midway |  | Y - 23 | USFS
117450762 | T3 DI FULTON-IGNACIO 1/9 CANCEL | 43761412 | FULTON-IGNACIO #1 | 001/009 | ICS | E | Pre-2020_(9a) Other ignition related |  |  | CANCEL/CNCL | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.736555 | 38.4975 | ETL.4680 | 40863245 | Structure-Steel | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville
117450983 | T2NT DI COLGATE-CHALLENGE 0/14 INS MRKW | 43910648 | COLGATE-CHALLENGE | 000/014 | ICS | F | 2020_(1a) PSPS |  |  | Likely MAT error - delink to correct | TR2 |  | North Valley | WSIP | [6 empty] | '-121.190891 | 39.3398 | ETL.6480 | 42549793 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
117450987 | T2NT DI PITTSBURG-TESLA#1 4/19 PNT TWR | 44586176 | PITTSBURG-TESLA #1 | 004/019 | ICS | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-121.908272 | 37.9831 | ETL.5510 | 40862418 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  | Y - Prog Multi
117451220 | T2 DI SPAULDING-SUMMIT 0/31 RPR STRW | 43923456 | SPAULDING-SUMMIT | 000/031 | ICW | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.630442 | 39.3217 | ETL.8060 | 40581014 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117451227 | T2 DI SPAULDING-SUMMIT 000/033 INS MRKW | 43923456 | SPAULDING-SUMMIT | 000/033 | ICW | F | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.629201 | 39.3215 | ETL.8060 | 40668714 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117451255 | T2 DI HT CRK #1 WW 14/276 INST MRKW | 43904280 | HAT CREEK #1-WESTWOOD | 014/276 | ICW | F | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.349582 | 40.8025 | ETL.7030 | 40770724 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117451430 | T2 DI HAAS-MCCALL 3/24 RPR SPLS | 43863061 | HAAS-MCCALL | 003/024 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-119.06837 | 36.9061 | ETL.4850 | 40761914 | Shield Wire / OPGW-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  | Y - 11
117451477 | T2 DI HAAS-MCCALL 3/29 RPR STRT | 44140314 | HAAS-MCCALL | 003/029 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | South | WSIP | FSRP | [5 empty] | '-119.079558 | 36.9103 | ETL.4850 | 40858142 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 11
117452457 | DI VALLEY SPRINGS #1 005/091 REPR STRW | 43853790 | VALLEY SPRINGS #1 | 005/091 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-120.832255 | 38.1766 | ETL.8210 | 40905506 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog Multi
117452498 | T2 DI HAAS-MCCLL 5/37 RPR FOND | 43863061 | HAAS-MCCALL | 005/037 | ICS | F | Pre-2020_(9a) Other ignition related |  |  | Likely MAT error - delink to correct | TR2 | LATE | South | WSIP | FSRP | [5 empty] | '-119.106287 | 36.905 | ETL.4850 | 40813914 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno
117452632 | T2 DI MTN GTE JCT CAS 2/27 RPL PL (L) | 31526991 | MTN GATE JCT-CASCADE | 002/027 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.32104 | 40.706 | ETL.7640 | 44565518 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC erdy srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
117452687 | T3 DI DRUM SPAULD 1/39 BOND HRDW | 43921229 | DRUM-SPAULDING | 001/039 | ICW | E | Pre-2020_(9a) Other ignition related |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.743018 | 39.258 | ETL.6770 | 40809630 | Hardware-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117452727 | T2 DI HAAS-MC CALL 001/013 RPR INSS | 43863061 | HAAS-MCCALL | 001/013 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-119.044071 | 36.9127 | ETL.4850 | 40689789 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  | Y - 11
117453156 | T2 DI DELTA-MTN GT JCT 15/187 INST HRDW | 43866636 | DELTA-MOUNTAIN GATE JCT | 015/187 | ICW | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.308376 | 40.7443 | ETL.6750 | 44564933 | Hardware-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117453201 | T2 DI DELTA-MTN GT JCT 15/187R INST HRDW | 43866636 | DELTA-MOUNTAIN GATE JCT | 015/187 | ICW | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.308376 | 40.7443 | ETL.6750 | 44564934 | Hardware-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117455368 | T2 DI SPAULDING-SUMMIT 00/25 INST MRKW | 43923458 | SPAULDING-SUMMIT | 000/025 | ICW | F | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.633724 | 39.3223 | ETL.8060 | 40751891 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117455699 | T2 DI MTN QRS 2/27A RPR STRS | 43869988 | MTN QUARRIES TAP | 002/027A | ICW | E | Pre-2020_(5) TD tag on other lines |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.027394 | 38.9127 | ETL.6991 | 44191124 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento
117455820 | T2 DI COLGATE-CHALLENGE 1/23 RPR STRW | 43910648 | COLGATE-CHALLENGE | 001/023 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.189466 | 39.3444 | ETL.6480 | 40594206 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117455824 | T2NT DI COLGATE-CHALLENGE 1/23 INS MRKW | 43910648 | COLGATE-CHALLENGE | 001/023 | ICS | F | Pre-2020_(4b) On structure in bucket 4 |  |  | Likely MAT error - delink to correct | TR2 |  | North Valley | WSIP | [6 empty] | '-121.189466 | 39.3444 | ETL.6480 | 40594206 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117455826 | T2 DI PITTSBURG-TESLA#1 7/34 RPR STRT | 43753186 | PITTSBURG-TESLA #1 | 007/034 | ICQ | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-121.859374 | 37.9467 | ETL.5510 | 40752491 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 5
117455848 | T2 DI HT CRK #1 WW 36/702 RPL PL | 31456280 | HAT CREEK #1-WESTWOOD | 036/702 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.066967 | 40.5614 | ETL.7030 | 40601708 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain
117455898 | T2 DI HATCRK#1 WSTWOOD 14/277 INST MRKW | 43904280 | HAT CREEK #1-WESTWOOD | 014/277 | ICW | F | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.348833 | 40.8019 | ETL.7030 | 40817109 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117455991 | T2 DI SPAULDING-SUMMIT 15/498 RPR GYWW | 43923458 | SPAULDING-SUMMIT | 015/498 | ICW | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.379556 | 39.3244 | ETL.8060 | 40618286 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117456059 | DI IGNACIO-ALTO 15/151 RPL PL | 31471947 | IGNACIO-ALTO | 015/151 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | North Coast | WSIP | [6 empty] | '-122.513036 | 37.921 | ETL.7150 | 40876331 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville
117456158 | DI DRUM-SUMMIT #1 017/205L INST MRKW | 43910104 | DRUM-SUMMIT #1 | 017/205 | ICW | F | Pre-2020_(1b) Lines with special commitments |  |  |  |  | WECC | North Valley | WSIP | [6 empty] | '-120.490905 | 39.3154 | ETL.1440 | 44769591 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117456170 | T3 DI COLGATE-CHALLENGE 1/27 RPR STRW | 43910648 | COLGATE-CHALLENGE | 001/027 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  | Likely MAT error - delink to correct | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.186917 | 39.3464 | ETL.6480 | 40767123 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117456191 | T2 DI TESLA-NEWARK #2 012/085 RPR FOND |  | TESLA-NEWARK #2 | 012/085 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-121.772939 | 37.6358 | ETL.5354 | 41152630 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 7
117456289 | T2 DI COLGATE-PALRMO 19/380 GRD WSH INSU | 43878259 | COLGATE-PALERMO | 019/380 | ICD | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.463647 | 39.4466 | ETL.6500 | 40664457 | Insulator | Contaminated | Ground Wash | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 622 | Table Mountain |  |  | Yes
117456421 | T2NT DI COLGATE-PALRMO 19/380 INS MRKS | 43878258 | COLGATE-PALERMO | 019/380 | ICS | F | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.463647 | 39.4466 | ETL.6500 | 40664457 | Marker (i.e. signs)-Steel | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117456429 | T2 DI VOLTA-DESCHUTES 19/436 RPR STRW | 43939089 | VOLTA-DESCHUTES | 019/436 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.220937 | 40.5506 | ETL.8290 | 40877249 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117456432 | T2NT DI HT CRK #1 WW 28/546 INST MRKW | 43904280 | HAT CREEK #1-WESTWOOD | 028/546 | ICW | F | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.170675 | 40.6496 | ETL.7030 | 40868486 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117456493 | T2 DI HT CRK #1 WW 25/488 RPL PL | 31456280 | HAT CREEK #1-WESTWOOD | 025/488 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.206318 | 40.6821 | ETL.7030 | 40876190 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain
117456522 | T2 DI HAAS-MCL 5/34 RPR STRT | 44140314 | HAAS-MCCALL | 005/034 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | South | WSIP | FSRP | [5 empty] | '-119.097322 | 36.9073 | ETL.4850 | 40746545 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 11
117456571 | NT DI HAT CRK#1-WESTWD 49/951 INST MRKW | 43904280 | HAT CREEK #1-WESTWOOD | 049/951 | ICW | F | Pre-2020_(4b) On structure in bucket 4 | [5 empty] | North Valley | WSIP | [6 empty] | '-121.01634 | 40.3847 | ETL.7030 | 40825620 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117456574 | DI HAT CRK#1-WESTWOOD 47/907 RPL STRW | 31456189 | HAT CREEK #1-WESTWOOD | 047/907 | 70Y | E | Pre-2020_(2) High fire spread TD |  |  |  |  | LATE | North Valley | WSIP |  |  |  |  | Access Issues | 2021 - Snow . FSR 7/2020 | '-121.021968 | 40.4177 | ETL.7030 | 40667988 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain
117456576 | T2NT DI RND MTN CTTNWD R002/19 PNT STRS | 43755801 | ROUND MTN-COTTONWOOD #3 | R002/019 | ICQ | F | Pre-2020_(9a) Other ignition related |  |  | Likely MAT error - delink to correct | TR2 |  | North Valley | WSIP | [6 empty] | '-121.93736 | 40.7945 | ETL.5650 | 40857973 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117456604 | T2 DI HT CRK #1 WW 24/467 REPL PL | 31456280 | HAT CREEK #1-WESTWOOD | 024/467 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.219798 | 40.6945 | ETL.7030 | 40825679 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain
117456726 | T2NT DI CTTNWD-DLVN#2 67/596 PNT TWR | 44305184 | COTTONWOOD-DELEVAN #2 | 067/596 | ICS | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.267777 | 40.2787 | ETL.4580 | 40822896 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117456785 | T2 HUMBOLDT-TRINITY 057/1R REMV BUTT | 44311174 | HUMBOLDT-TRINITY | 057/001 | ICW | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-123.119316 | 40.7687 | ETL.1820 | 44562713 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2019-08-30
117456787 | T2 DI HT CRK #1 WW 24/477 INST MRKW | 43904280 | HAT CREEK #1-WESTWOOD | 024/477 | ICW | F | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.213393 | 40.6886 | ETL.7030 | 40825584 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117456834 | T2 HUMBOLDT-TRINITY 52/004R REMV BUTT | 44311174 | HUMBOLDT-TRINITY | 052/004 | ICW | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-123.054248 | 40.7434 | ETL.1820 | 44557692 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2019-08-30
117456876 | T2 DI FORT BRAGG-ELK 12/2 RPR GYWW | 43877649 | FORT BRAGG-ELK | 012/002 | ICW | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.784752 | 39.283 | ETL.2060 | 40697824 | Guy Wire-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  | 2019-07-29
117456927 | DI HAT CRK#1-WESTWOOD 47/906 RPR STRW | 43939293 | HAT CREEK #1-WESTWOOD | 047/906 | ICW | E | Pre-2020_(2) High fire spread TD |  |  |  |  | LATE | North Valley | WSIP |  |  |  |  | Access Issues | 2021 - Snow . FSR 12/2020 | '-121.022087 | 40.4185 | ETL.7030 | 40675741 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117457044 | T2 DI TRI MPLE CRK 16/11 RPR GYWW | 43749708 | TRINITY-MAPLE CREEK | 016/011 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.207492 | 40.741 | ETL.8170 | 44628450 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
117457071 | T2 DI HAT CREEK #1-WSTWD 2/44 RPR GYWW | 43736795 | HAT CREEK #1-WESTWOOD | 002/044 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.50444 | 40.922 | ETL.7030 | 40596892 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117457075 | T2 DI HAT CREEK #1-WESTWOD 3/77 RPL STRW | 31504344 | HAT CREEK #1-WESTWOOD | 003/077 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.471672 | 40.9169 | ETL.7030 | 40770080 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Need New ERTC
117457798 | T2 DI HAT CREEK #1-WSTWD 11/213 RPL STRW | 31504344 | HAT CREEK #1-WESTWOOD | 011/213 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.389475 | 40.8397 | ETL.7030 | 40701209 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Need New ERTC
117458003 | T2 DI HAT CRK#1-WESTWOOD 20/400 RPR PL | 43939287 | HAT CREEK #1-WESTWOOD | 020/400 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.264272 | 40.7336 | ETL.7030 | 40827479 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117458007 | T2 DI HAT CRK#1-WESTWOOD 20/400 RPL HRDD | 43939292 | HAT CREEK #1-WESTWOOD | 020/400 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.264272 | 40.7336 | ETL.7030 | 40827479 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117458050 | T2NT DI HAT CRK#1-WSTWD 20/400 INST MRKW | 43904280 | HAT CREEK #1-WESTWOOD | 020/400 | ICW | F | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.264272 | 40.7336 | ETL.7030 | 40827479 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117458142 | T2 DI HT CRK #1 WW 2/49 RPL PL | 31504344 | HAT CREEK #1-WESTWOOD | 002/049 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.499562 | 40.9212 | ETL.7030 | 40814026 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Need New ERTC
117458144 | T2 DI HAT CRK#1-WESTWD 19/373 RPL PL | 31505374 | HAT CREEK #1-WESTWOOD | 019/373 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.282277 | 40.7482 | ETL.7030 | 40877585 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Need New ERTC
117458163 | T2NT DI STNL-MLNS-MNTC#1 002/016 PAINT | 43852843 | STANISLAUS-MELONES SS-MANTECA #1+ | 002/016 | ICQ | F | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-120.41139 | 38.1258 | ETL.3830 | 40804662 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - Prog Multi
117458208 | T2NT DI HATCRK#1 WSTWD 19/366 INST MRKW | 43904280 | HAT CREEK #1-WESTWOOD | 019/366 | ICW | F | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.287155 | 40.752 | ETL.7030 | 40601707 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117458269 | T3 DI CEN TAB MTN 2/41 RPR STRW | 43724253 | CENTERVILLE-TABLE MTN | 002/041 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.681033 | 39.7575 | ETL.6320 | 40822423 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117458343 | T2 DI DUNLAP TAP 015/014 RPR PL | 43709736 | DUNLAP TAP | 015/014 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-119.031207 | 36.7075 | ETL.9061 | 40747119 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Fresno |  | Y - 9
117458381 | T2 DI HAT CRK 1-WSTWD 30/583 INST MRKW | 43904280 | HAT CREEK #1-WESTWOOD | 030/583 | ICW | F | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.141767 | 40.6315 | ETL.7030 | 40825592 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  | Yes
117458400 | DI CAYUCOS-CAMBRIA 13/84 RPL INSW | 31502978 | CAYUCOS-CAMBRIA | 013/084 | 93I | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | South | WSIP | FSRP | [7 empty] | ETL.8560 | 44271584 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Pismo Beach |  | Y - Prog 401
117458497 | T2 DI CBRY SW ST-RD MTN 21/168 INST MRKS | 43897848 | CARBERRY SW STA-ROUND MTN | 021/168 | ICS | F | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.82031 | 40.8241 | ETL.5410 | 40868794 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117458600 | T2 DI SPLDNG-SMMT 1/48 INS MRKW | 43923458 | SPAULDING-SUMMIT | 001/048 | ICW | F | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.624686 | 39.3183 | ETL.8060 | 40586118 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117458658 | T2 DI SPAULDING-SUMMIT 0/3 RPR GYWW | 43923458 | SPAULDING-SUMMIT | 000/003 | ICW | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.643808 | 39.3247 | ETL.8060 | 40652035 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117458748 | DI ROUND MTN-COTTONWOOD 22/204 INS MRKS | 43877040 | ROUND MTN-COTTONWOOD #2 | 022/204 | ICS | F | Pre-2020_(5b) On structure in bucket 5 | [5 empty] | North Valley | WSIP | [6 empty] | '-122.038895 | 40.7038 | ETL.5640 | 40746411 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117458784 | T2 DI HAT CREEK 1-WESTWOOD 0/13 RPL PL | 31504344 | HAT CREEK #1-WESTWOOD | 000/013 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.534698 | 40.9267 | ETL.7030 | 40616826 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Need New ERTC
117458805 | T2 DI PIT#1 COTTNWOOD 21/170 PNT STRS | 44586171 | PIT #1-COTTONWOOD | 021/170 | ICS | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.823958 | 40.8233 | ETL.5390 | 40580083 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117458833 | DI COLGATE-CHALLANGE 0/2 RPR GYWS | 43910648 | COLGATE-CHALLENGE | 000/002 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-121.189756 | 39.3323 | ETL.6480 | 44695457 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento
117458921 | T2 DI HAT CREEK #1-WSTWD 20/395 RPL STRW | 31456280 | HAT CREEK #1-WESTWOOD | 020/395 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.267768 | 40.7364 | ETL.7030 | 40592094 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain
117458922 | T2NT DI HAT CRK #1-WSTWD 20/401 INS MRKW | 43904280 | HAT CREEK #1-WESTWOOD | 020/401 | ICW | F | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.263613 | 40.733 | ETL.7030 | 40816134 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117458949 | DI VLLY SPRNGS#1 12/246 RPR GYWW | 43857861 | VALLEY SPRINGS #1 | 012/246 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-120.923895 | 38.1021 | ETL.8210 | 40904221 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 23
117459024 | T2 DI HAT CREEK #1-WSTWD 20/402 RPR PL | 43939292 | HAT CREEK #1-WESTWOOD | 020/402 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.262903 | 40.7325 | ETL.7030 | 40877481 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117459228 | T2 DI MONTA VSTA-LOS GATS 8/167 RMV VEG |  | MONTA VISTA-LOS GATOS | 008/167 | HNA | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | Central | WSIP | FSRP |  |  |  |  | [REDACTED] - applying for Cal Trans District 4 scenic highway permmit; eta 8/15/2020 | '-122.004522 | 37.2419 | ETL.7610 | 40766368 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Bay
117459267 | T2 DI HAT CREEK #1-WSTWD 28/542 RPL STRW | 31456280 | HAT CREEK #1-WESTWOOD | 028/542 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.173778 | 40.6515 | ETL.7030 | 40770751 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain
117459325 | T2 DI HAT CRK#1-WESTWOOD 25/494 RPR HRDW | 43939292 | HAT CREEK #1-WESTWOOD | 025/494 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.20251 | 40.6786 | ETL.7030 | 40759033 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117459400 | T2NT DI HAT CRK#1-WESTWD 25/494 INS MRKW | 43904280 | HAT CREEK #1-WESTWOOD | 025/494 | ICW | F | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.20251 | 40.6786 | ETL.7030 | 40759033 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117459523 | T2 DI MTN GT JCT-CASCADE 5/55 RPR STRW | 43758388 | MTN GATE JCT-CASCADE | 005/055 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.330603 | 40.6753 | ETL.7640 | 40600604 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117459539 | T2 TULUCAY-NAPA #1 006/014 REPL POLE | 31471954 | TULUCAY-NAPA #1 | 006/014 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-122.200994 | 38.2605 | ETL.8180 | 40751190 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  | 2019-08-09
117459567 | T2 DI SOB STA OIL SW S#1 7/42 RPR FOND |  | SOBRANTE-STANDARD OIL SW STA #2 | 007/042 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.230683 | 37.9967 | ETL.3800 | 40681223 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 3
117459569 | T2NT DI SOB STA OIL SW S#1 7/42 REPAINT | 44586185 | SOBRANTE-STANDARD OIL SW STA #2 | 007/042 | ICS | F | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) |  |  | TR2 |  | Central | WSIP | [6 empty] | '-122.230683 | 37.9967 | ETL.3800 | 40681223 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay
117459571 | T2NT DI HAT CRK #1-WSTWD 33/636 INS MRKW | 43904280 | HAT CREEK #1-WESTWOOD | 033/636 | ICW | F | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.104913 | 40.6024 | ETL.7030 | 40667962 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117459695 | T2NT DI HAT CRK #1-WTWD 33/650 INST MRKW | 43904280 | HAT CREEK #1-WESTWOOD | 033/650 | ICW | F | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.096788 | 40.5936 | ETL.7030 | 40825597 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117459855 | T2 DI HAT CRK#1 23/443 RPR STRW | 43939292 | HAT CREEK #1-WESTWOOD | 023/443 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.235233 | 40.7086 | ETL.7030 | 40676328 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117459860 | T2 DI HT CRK #1 WW 6/130 RPL POLE | 31504344 | HAT CREEK #1-WESTWOOD | 006/130 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.428357 | 40.8953 | ETL.7030 | 40658523 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Need New ERTC
117460065 | T2 DI VAL SPR CLA 16/226 RPR GYWW | 43857873 | VALLEY SPRINGS-CLAY | 016/226 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.926816 | 38.3232 | ETL.8264 | 40904822 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog Multi
117460067 | T2NT DI VAL SPR CLA 16/226 INST MRKW | 43857873 | VALLEY SPRINGS-CLAY | 016/226 | ICW | F | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-120.926816 | 38.3232 | ETL.8264 | 40904822 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog Multi
117460384 | T2 HUMBOLDT-TRINITY 90/4 RMV POLE BUTT | 44311171 | HUMBOLDT-TRINITY | 090/004 | ICW | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.689461 | 40.7396 | ETL.1820 | 44562640 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
117460477 | T2 HUMBOLDT-TRINITY 89/7 RMV PL BUTTS | 44311171 | HUMBOLDT-TRINITY | 089/007 | ICW | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-123.675507 | 40.7306 | ETL.1820 | 44560497 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
117460489 | T2 HUMBOLDT-TRINITY 89/6 RMV POLE BUTTS | 44285711 | HUMBOLDT-TRINITY | 089/006A | ICW | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.674455 | 40.7302 | ETL.1820 | 44553939 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
117460615 | T2 HUMBOLDT-TRINITY 88/4 RMV DEBRIS | 43729541 | HUMBOLDT-TRINITY | 088/004 | ICW | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-123.664978 | 40.728 | ETL.1820 | 44560494 | Structure-Wood | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2019-08-30
117460715 | T2 DI HATCRK#1 WSTWD 10/209 RPL STRW | 31495723 | HAT CREEK #1-WESTWOOD | 010/209 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.391318 | 40.8423 | ETL.7030 | 40877575 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
117460739 | T2 HUMBOLDT-TRINITY 88/2 RMV DEBR | 43729541 | HUMBOLDT-TRINITY | 088/002 | ICW | F | Pre-2020_(3) On high spread structure |  |  |  | TR2 | LATE | North Coast | Non-WSIP |  |  |  |  | Project | 2021 HUMBOLDT-TRINITY | '-123.658695 | 40.7266 | ETL.1820 | 44562193 | Structure-Wood | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2019-10-04
117460942 | DI VAL SPR CLA 13/193 RPL INSS | 31433173 | VALLEY SPRINGS-CLAY | 013/193 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-120.910789 | 38.2936 | ETL.8264 | 40906858 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Victor |  | Y - Prog Multi
117460944 | T2NT DI CHRISTIE-SOBRANTE 010/058 PAINT | 43751914 | CHRISTIE-SOBRANTE | 010/058 | ICS | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-122.198532 | 37.9922 | ETL.1260 | 40869614 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay
117460946 | T2NT DI HT CRK #1 WW 14/274 INST MRKW | 43904280 | HAT CREEK #1-WESTWOOD | 014/274 | ICW | F | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.350953 | 40.8036 | ETL.7030 | 40600202 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117460953 | T2NT DI RND MTN-CTTN #3 58/531 INS MRKS | 43876249 | ROUND MTN-COTTONWOOD #3 | 058/531 | ICS | F | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.256284 | 40.4095 | ETL.5650 | 40593783 | Marker (i.e. signs)-Steel | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117461030 | T2 HUMBOLDT-TRINITY 88/1 RMV DEBR | 43729541 | HUMBOLDT-TRINITY | 088/001 | ICW | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-123.653024 | 40.7253 | ETL.1820 | 44562990 | Structure-Wood | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2019-10-04
117461155 | T2 DI HATCRK#1 WSTWD #1 14/280 RPLC POLE | 31456189 | HAT CREEK #1-WESTWOOD | 014/280 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.34681 | 40.8002 | ETL.7030 | 40701333 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain
117461237 | T2NT DI HTCRK#1 WSTWD #1 14/271 INS MRKW | 43904280 | HAT CREEK #1-WESTWOOD | 014/271 | ICW | F | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.352952 | 40.8053 | ETL.7030 | 40759176 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117461357 | T2NT DI HAT CRK#1 WSTWD 17/328 INS MRKW | 43904280 | HAT CREEK #1-WESTWOOD | 017/328 | ICW | F | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.313593 | 40.7735 | ETL.7030 | 40676295 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117461377 | T2 DI SPAULDING-SUMMIT 000/005 RPL HRDD | 43923458 | SPAULDING-SUMMIT | 000/005 | ICW | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.643267 | 39.3247 | ETL.8060 | 40770692 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117461582 | T2 DI HATCRK#1 WSTWD 13/256 RPL STRW | 31505374 | HAT CREEK #1-WESTWOOD | 013/256 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.36344 | 40.8137 | ETL.7030 | 40701219 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Need New ERTC
117461595 | T2 DI HAT CRK#1 WSTWD 24/460 RPR STRW | 43736795 | HAT CREEK #1-WESTWOOD | 024/460 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.224298 | 40.6986 | ETL.7030 | 40600226 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117461693 | T2 DI SPAULDING-SUMMIT 000/019 INS MRKW | 43923458 | SPAULDING-SUMMIT | 000/019 | ICW | F | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.637176 | 39.3229 | ETL.8060 | 40861966 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117461766 | T2 DI VLLY SPRNGS-CLAY 13/173 RPR STRW | 43857873 | VALLEY SPRINGS-CLAY | 013/173 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.898455 | 38.2822 | ETL.8264 | 40904779 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 12
117461796 | T2 DI COLGATE-PALERMO 0/2 RPL STRW | 31457073 | COLGATE-PALERMO | 000/002 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.19024 | 39.3316 | ETL.6500 | 40672039 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
117462099 | T2NT DI HAT CRK#1 WSTWD 20/399 CANCEL | 43904280 | HAT CREEK #1-WESTWOOD | 020/399 | ICW | F | Pre-2020_(4b) On structure in bucket 4 |  |  | CANCEL/CNCL | TR2 |  | North Valley | WSIP | [6 empty] | '-121.264958 | 40.7341 | ETL.7030 | 40759025 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117462118 | T2 DI STA MEL SW STA MA 15/95 RPR STRS | 43852841 | STANISLAUS-MELONES SS-MANTECA #1+ | 015/095 | ICS | F | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.602914 | 38.0179 | ETL.3830 | 40751416 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Victor |  | Y - Prog Multi
117462290 | T2 DI MTN GTE JCRT CAS 3/37 RPR STRW (R) | 43758388 | MTN GATE JCT-CASCADE | 003/037 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [7 empty] | ETL.7640 | 44158968 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117462292 | T2 DI MTN GTE JCRT CAS 3/37 RPR STRW (L) | 43758388 | MTN GATE JCT-CASCADE | 003/037 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [7 empty] | ETL.7640 | 44158967 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117462325 | T2 DI VALLEY SPRNGS-CLAY 12/164 RPR STRW | 43857873 | VALLEY SPRINGS-CLAY | 012/164 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.890535 | 38.2778 | ETL.8264 | 40904774 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 12
117462326 | T2 DI VALLEY SPRNGS-CLAY 12/164 RPR GYWW | 43857873 | VALLEY SPRINGS-CLAY | 012/164 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.890535 | 38.2778 | ETL.8264 | 40904774 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog Multi
117462460 | T2 DI HAT CRK#1 WSTWD :15/300 RPR STRW | 43939287 | HAT CREEK #1-WESTWOOD | 015/300 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.332935 | 40.7891 | ETL.7030 | 40701335 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117462462 | T2NT DI HAT CRK#1 WSTWD :15/300 INS MRKW | 43736797 | HAT CREEK #1-WESTWOOD | 015/300 | ICW | F | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.332935 | 40.7891 | ETL.7030 | 40701335 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117462488 | T2NT DI SPAULDING-SUMMIT 1/68 INST MRKW | 43923458 | SPAULDING-SUMMIT | 001/068 | ICW | F | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.618417 | 39.3114 | ETL.8060 | 40811570 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117462640 | DI MERCED FALLS-EXCH 6/14 RPR RUST MBER | 44300717 | MERCED FALLS-EXCHEQUER | 006/014 | ICQ | E | Pre-2020_(4) TD tag on high spread line | Superintendent Approved work efficiency |  |  |  | LATE | South | WSIP | [6 empty] | '-120.274276 | 37.5845 | ETL.8990 | 40748143 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - Prog Multi
117463277 | T2NT DI HT CRK 1-WSTWD 53/1039 INST MRKW | 43904280 | HAT CREEK #1-WESTWOOD | 053/1039 | ICW | F | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP | [5 empty] | reprioritization of work - noncritical facility | '-121.001493 | 40.32 | ETL.7030 | 40770001 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117463317 | T2 DI HATCRK#1 -WSTD 15/294 RPR HOLE | 43736796 | HAT CREEK #1-WESTWOOD | 015/294 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.337078 | 40.7924 | ETL.7030 | 40616868 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117463350 | T2NT DI HATCRK#1 -WSTD 15/294 INST MRKW | 43904280 | HAT CREEK #1-WESTWOOD | 015/294 | ICW | F | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP | [5 empty] | reprioritization of work - noncritical facility | '-121.337078 | 40.7924 | ETL.7030 | 40616868 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117463448 | T3 DI COLGATE-CHALLENGE 1/29 RPR STRW | 43910648 | COLGATE-CHALLENGE | 001/029 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  | Likely MAT error - delink to correct | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.18562 | 39.3473 | ETL.6480 | 40824182 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
117463486 | T2NT DI HATCRK#1 -WSTD 13/254 INST MRKW | 43904280 | HAT CREEK #1-WESTWOOD | 013/254 | ICW | F | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP | [5 empty] | reprioritization of work - noncritical facility | '-121.364833 | 40.8147 | ETL.7030 | 40877470 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117463672 | T2NT DI SPA SUM 0/26 INST MRKW | 43923458 | SPAULDING-SUMMIT | 000/026 | ICW | F | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.633016 | 39.3222 | ETL.8060 | 40810198 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117463796 | T2 DI HATCRK#1 -WSTD 17/327 RPL STRW | 31495723 | HAT CREEK #1-WESTWOOD | 017/327 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.314315 | 40.774 | ETL.7030 | 40617050 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
117463857 | T2 DI MORAGA-LAKEWOOD 010/080 RPR SPLS | 43877251 | MORAGA-LAKEWOOD | 010/080 | ICS | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.138722 | 37.8632 | ETL.3741 | 40604203 | Splice-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - Prog Multi
117464721 | T2NT DI MALIN-RND MTN#2 70/353 INS GMKS | 43621093 | MALIN-ROUND MTN #2 | 070/353 | ICQ | F | Pre-2020_(1b) Lines with special commitments |  |  | Likely MAT error - delink to correct | TR2 | WECC | North Valley | WSIP | [6 empty] | '-121.772887 | 41.0973 | ETL.6020 | 40660399 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117464805 | T2NT DI VACA-LAKEVILL #1 13/66 INST MRKS | 43908800 | VACA-LAKEVILLE #1 | 013/066 | ICS | F | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.103094 | 38.3111 | ETL.5840 | 40816985 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes
117464833 | T2 DI MALIN-RND MTN#2 67/340 INS GMKS | 43621093 | MALIN-ROUND MTN #2 | 067/340 | ICQ | F | Pre-2020_(1b) Lines with special commitments |  |  | Likely MAT error - delink to correct | TR2 | WECC | North Valley | WSIP | [6 empty] | '-121.740654 | 41.1228 | ETL.6020 | 40605579 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117465244 | T2 DI HATCRK#1 -WSTD 33/637 RPR GYWW | 43939292 | HAT CREEK #1-WESTWOOD | 033/637 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.104343 | 40.6017 | ETL.7030 | 40759225 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117465312 | T2 DI STANISLAUS-MNTCA #2 BENT STEEL | 44460416 | STANISLAUS-MANTECA #2 | 019/114 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.656686 | 37.9763 | ETL.3820 | 40744470 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - Prog Multi
117465372 | T2 DI HAT CRK #1-WSTWOOD 21/414 RPR STRW | 43736797 | HAT CREEK #1-WESTWOOD | 021/414 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.2546 | 40.7258 | ETL.7030 | 40601696 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117465390 | T2 DI SLNS-LRLS A12/268 RMV VEG |  | SALINAS-LAURELES | A012/268 | HNA | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | South | WSIP | [5 empty] | Per Cal Trans District 5, unless the trees are dead, the removal of the trees as a scenic resource will require Coastal Development Permit or some other kind of locally driven approval that complies with CEQA. | '-121.771939 | 36.5701 | ETL.7930 | 40768981 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Moss Landing
117465399 | T2 DI HATCRK#1 -WSTD 22/424 RPR STRW | 43939292 | HAT CREEK #1-WESTWOOD | 022/424 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.247742 | 40.7201 | ETL.7030 | 40676320 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117465425 | T2 DI HAT CRK #1-WSTWOOD 21/418 RPL POLE | 31456280 | HAT CREEK #1-WESTWOOD | 021/418 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.251847 | 40.7235 | ETL.7030 | 40769954 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain
117465458 | T2 DI HAT CREK #1 WESTWD 15/296 RPL POLE | 31505374 | HAT CREEK #1-WESTWOOD | 015/296 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.33568 | 40.7913 | ETL.7030 | 40759180 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Need New ERTC
117465475 | T2NT DI HATCRK#1 -WSTD 22/424 INST MRKW | 43904280 | HAT CREEK #1-WESTWOOD | 022/424 | ICW | F | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP | [5 empty] | reprioritization of work - noncritical facility | '-121.247742 | 40.7201 | ETL.7030 | 40676320 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117465583 | T2 DI HATCRK#1 -WSTD 19/368 RPL STRW | 31456280 | HAT CREEK #1-WESTWOOD | 019/368 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.285798 | 40.7509 | ETL.7030 | 40656881 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain
117465690 | T2 DI HT CRK #1 WW 14/287 RPR STRW | 43939287 | HAT CREEK #1-WESTWOOD | 014/287 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.341957 | 40.7964 | ETL.7030 | 40827468 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117466312 | T2 DI HAT CRK #1-WSTWOOD 22/440 INST HV | 43904280 | HAT CREEK #1-WESTWOOD | 022/440 | ICW | F | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP | [5 empty] | reprioritization of work - noncritical facility | '-121.237517 | 40.7106 | ETL.7030 | 40877483 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117466445 | T2 DI HT CRK #1 WW 22/438 RPR STRW | 43939292 | HAT CREEK #1-WESTWOOD | 022/438 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.238727 | 40.7118 | ETL.7030 | 40827483 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117466502 | T2 DI MALIN-RND MTN#2 68/345 INS GMKS | 43621093 | MALIN-ROUND MTN #2 | 068/345 | ICQ | F | Pre-2020_(1b) Lines with special commitments |  |  | Likely MAT error - delink to correct | TR2 | WECC | North Valley | WSIP | [6 empty] | '-121.752349 | 41.1135 | ETL.6020 | 40764368 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117466510 | T2 DI HT CRK #1 WW 29/565 RPR GYWW | 43939292 | HAT CREEK #1-WESTWOOD | 029/565 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.155908 | 40.6403 | ETL.7030 | 40868488 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  | Yes
117466512 | T2NT DI HT CRK #1 WW 29/565 INST HV | 43904280 | HAT CREEK #1-WESTWOOD | 029/565 | ICW | F | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP | [5 empty] | reprioritization of work - noncritical facility | '-121.155908 | 40.6403 | ETL.7030 | 40868488 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  | Yes
117466513 | T2 DI HT CRK #1 WESTWD 27/519 RPL POLE | 31504344 | HAT CREEK #1-WESTWOOD | 027/519 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.188762 | 40.6641 | ETL.7030 | 40617071 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Need New ERTC
117466604 | T2 DI HAT CRK #1-WSTWOOD 23/448 INS MRKW | 43904280 | HAT CREEK #1-WESTWOOD | 023/448 | ICW | F | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP | [5 empty] | reprioritization of work - noncritical facility | '-121.232052 | 40.7056 | ETL.7030 | 40816136 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117466780 | T2 DI HAT CRK #1-WSTWOOD 23/450 RPR POLE | 43939292 | HAT CREEK #1-WESTWOOD | 023/450 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.230683 | 40.7044 | ETL.7030 | 40876274 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117466782 | T2 DI HAT CRK #1-WSTWOOD 23/450 INST HV | 43904280 | HAT CREEK #1-WESTWOOD | 023/450 | ICW | F | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP | [5 empty] | reprioritization of work - noncritical facility | '-121.230683 | 40.7044 | ETL.7030 | 40876274 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117466787 | T2 DI HAT CRK #1-WSTWOOD 24/473 CANCEL | 31471926 | HAT CREEK #1-WESTWOOD | 024/473 | 93E | E | Pre-2020_(4) TD tag on high spread line |  |  | CANCEL/CNCL | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.21593 | 40.6909 | ETL.7030 | 40667946 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  | Yes
117466890 | T2NT DI HAT CRK #1-WSWD 24/473 CANCEL | 43904280 | HAT CREEK #1-WESTWOOD | 024/473 | ICW | F | Pre-2020_(4b) On structure in bucket 4 |  |  | CANCEL/CNCL | TR2 |  | North Valley | WSIP | [5 empty] | reprioritization of work - noncritical facility | '-121.21593 | 40.6909 | ETL.7030 | 40667946 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117467341 | T2 DI HAT CRK #1-WSTWOOD 27/529 RPR STRW | 43736797 | HAT CREEK #1-WESTWOOD | 027/529 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.18311 | 40.6579 | ETL.7030 | 40600238 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117467374 | T2NT DI VOLTA-SOUTH 001/040 INST MRKW | 43827513 | VOLTA-SOUTH | 001/040 | ICW | F | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 |  | North Valley | WSIP | [5 empty] | reprioritization of work - noncritical facility | '-121.8726 | 40.4359 | ETL.8300 | 40826968 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117467451 | T2 DI HAT CRK #1-WSTWOD 29/559 RPR GYWW | 43939292 | HAT CREEK #1-WESTWOOD | 029/559 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.16055 | 40.6433 | ETL.7030 | 40701230 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117467513 | T2 DI HAT CRK #1-WSTWD 31/607 RPR GYWW | 43939292 | HAT CREEK #1-WESTWOOD | 031/607 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.122963 | 40.6197 | ETL.7030 | 40676370 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117467519 | T2 DI HAT CRK #1-WSTWOOD 31/607 INS MRKW | 43904280 | HAT CREEK #1-WESTWOOD | 031/607 | ICW | F | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP | [5 empty] | reprioritization of work - noncritical facility | '-121.122963 | 40.6197 | ETL.7030 | 40676370 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117467543 | T2NT DI HT CRK #1 WESTWD 34/655 INST HV | 43904280 | HAT CREEK #1-WESTWOOD | 034/655 | ICW | F | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP | [5 empty] | reprioritization of work - noncritical facility | '-121.093897 | 40.5905 | ETL.7030 | 40667965 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117467676 | T2 DI HAT CRK #1-WESTWD 18/349 REPL STRW | 31505374 | HAT CREEK #1-WESTWOOD | 018/349 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.298903 | 40.7616 | ETL.7030 | 40816128 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Need New ERTC
117467683 | T2 DI SLNS-LRLS A12/261 RMV VEGN |  | SALINAS-LAURELES | A012/261 | HNA | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-121.765932 | 36.5705 | ETL.7930 | 40812151 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Moss Landing
117467745 | EI DRUM-SUMMIT #1 017/205R INST MRKW | 43910102 | DRUM-SUMMIT #1 | 017/205 | ICW | F | Pre-2020_(1b) Lines with special commitments |  |  |  |  | WECC | North Valley | Non-WSIP | [6 empty] | '-120.490905 | 39.3154 | ETL.1440 | 44769592 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117467835 | T2 DI HAT CRK #1-WESTWD 32/618 RPL INSW | 31474040 | HAT CREEK #1-WESTWOOD | 032/618 | 93I | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.115338 | 40.6136 | ETL.7030 | 44144300 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Table Mountain |  |  | Yes
117467913 | T2 DI HT CRK #1 WW 32/620 RPR STRW | 43939292 | HAT CREEK #1-WESTWOOD | 032/620 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.11417 | 40.6123 | ETL.7030 | 40817143 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117467970 | T2 DI MLN-RND MTN #2 70/354 INS GMKS | 44305271 | MALIN-ROUND MTN #2 | 070/354 | ICS | F | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | WECC | North Valley | WSIP | [6 empty] | '-121.774762 | 41.0958 | ETL.6020 | 40753370 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117468057 | T2 DI HAT CRK #1-WSTWOOD 24/472 RPR GYWW | 43939292 | HAT CREEK #1-WESTWOOD | 024/472 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.216593 | 40.6915 | ETL.7030 | 40676335 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  | Yes
117468058 | T2 DI HAT CRK #1-WSTWOOD 24/472 INS MRKW | 43904280 | HAT CREEK #1-WESTWOOD | 024/472 | ICW | F | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP | [5 empty] | reprioritization of work - noncritical facility | '-121.216593 | 40.6915 | ETL.7030 | 40676335 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  | Yes
117468059 | T2 DI HAT CRK #1-WSTWOOD 24/472 RPL INSW | 31456189 | HAT CREEK #1-WESTWOOD | 024/472 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.216593 | 40.6915 | ETL.7030 | 40721586 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Pole Program | Capital | 508 | Table Mountain |  | Yes
117468069 | DI PALERMO-OROVILLE #2 000/004 RPR GYWW | 43724470 | PALERMO-OROVILLE #2 | 000/004 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-121.519202 | 39.4546 | ETL.7740 | 41123116 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117468116 | T2 DI HAT CRK 1-WESTWOOD 38/744 RPL STRW | 31456280 | HAT CREEK #1-WESTWOOD | 038/744 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.042957 | 40.5355 | ETL.7030 | 40769987 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain
117470128 | T2 EI BALCH-SANGER 05/31 RPL CONN | 43862937 | BALCH-SANGER | 005/031 | ICM | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-119.156996 | 36.8885 | ETL.1050 | 40583101 | Connector | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 534 | Fresno |  | Y - Prog USFS
117470133 | T2NT DI SPAULDNG-SUMMT 001/049 INS MRKW | 43923458 | SPAULDING-SUMMIT | 001/049 | ICW | F | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.624547 | 39.3181 | ETL.8060 | 40660203 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117470327 | T2 DI HT CRK #1-WSTWD 15/289 RPR POLE | 43736796 | HAT CREEK #1-WESTWOOD | 015/289 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.34057 | 40.7952 | ETL.7030 | 40616865 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117470386 | DI STA NEW #1 84/558 EXPOSE STB | 44505634 | STANISLAUS-NEWARK #1 (12KV) | 084/558 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-121.749736 | 37.6512 | ETL.3850 | 41195978 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog Multi
117470434 | DI STA NEW #1 84/558 RPR STRT | 44505634 | STANISLAUS-NEWARK #1 (12KV) | 084/558 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-121.749736 | 37.6512 | ETL.3850 | 41195978 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 5
117470436 | T2 DI HT CRK #1-WSTWD 31/600 RPR PL | 43939292 | HAT CREEK #1-WESTWOOD | 031/600 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.128433 | 40.6232 | ETL.7030 | 40759041 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117470490 | T2 DI HT CRK #1-WSTWD 31/600 INST MRKW | 43904280 | HAT CREEK #1-WESTWOOD | 031/600 | ICW | F | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP | [5 empty] | reprioritization of work - noncritical facility | '-121.128433 | 40.6232 | ETL.7030 | 40759041 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117470591 | T2 DI PLRM-RVILLE #2 A007/93 RPR STRW | 43724470 | PALERMO-OROVILLE #2 | A007/093 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.493617 | 39.5304 | ETL.7740 | 41123124 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117470595 | T2 DI PLRM-RVILLE #2 A007/93 INST MRKW | 43724470 | PALERMO-OROVILLE #2 | A007/093 | ICW | F | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.493617 | 39.5304 | ETL.7740 | 41123124 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117470599 | T2 DI COLGATE-PALERMO 7/135 RMV VEGN |  | COLGATE-PALERMO | 007/135 | HNA | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.307753 | 39.3463 | ETL.6500 | 40873598 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  | Yes
117470632 | DI COTTNWD-DELVN #2 000/001 RPR SPLS | 44305184 | COTTONWOOD-DELEVAN #2 | 000/001 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-122.263005 | 40.3968 | ETL.4580 | 40651417 | Splice-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117470636 | DI CLEAR LAKE-HPLND 1/8 RPL STRW | 31483756 | CLEAR LAKE-HOPLAND | 001/008 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | North Coast | WSIP | FSRP | [5 empty] | '-123.054987 | 38.9664 | ETL.6390 | 40860806 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  | 2019-07-19
117470852 | DI JFFRSON-STANFORD 0/1 RPR GYWW | 43877613 | JEFFERSON-STANFORD (NO FLY) | 000/001 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-122.285318 | 37.4558 | ETL.7220 | 40588805 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Bay |  | Y - Prog Multi
117470907 | T3 DI DRUM-HIGGINS 4/48 RPR GYWW | 43903303 | DRUM-HIGGINS | 004/048 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.831684 | 39.2144 | ETL.4393 | 44172173 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
117470909 | T2 DI VOLTA-SOUTH 2/48 RPR PL | 44309960 | VOLTA-SOUTH | 002/048 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.871635 | 40.4316 | ETL.8300 | 40615862 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117470951 | DI TESLA NEWARK #2 13/89 PAINT COATING | 43753285 | TESLA-NEWARK #2 | 013/089 | ICS | F | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) |  |  |  |  | Central | WSIP | [6 empty] | '-121.783442 | 37.6301 | ETL.5354 | 41152634 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay
117470971 | T2 DI HAT CRK #1-WSTWD 25/486 RPL STRW | 31456280 | HAT CREEK #1-WESTWOOD | 025/486 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.207628 | 40.6832 | ETL.7030 | 40825586 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain
117471106 | DI PALERMO-WYANDTT 000/000B RPR GYWW | 43952543 | PALERMO-WYANDOTTE | 000/000B | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-121.519468 | 39.4548 | ETL.4315 | 44190800 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117471108 | DI PALERMO-WYANDOTTE 000/000B RPR STRW | 43952543 | PALERMO-WYANDOTTE | 000/000B | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-121.519468 | 39.4548 | ETL.4315 | 44190800 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117471197 | T2 DI CENTERVLL-TBL MTN 004/075 RPR SPLW | 43792089 | CENTERVILLE-TABLE MTN | 004/075 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.705885 | 39.7329 | ETL.6320 | 40867505 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117471201 | T2NT DI DRUM-SUMMIT #2 28/333 INST MRKW | 43947608 | DRUM-SUMMIT #2 | 028/333 | ICW | F | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | WECC | North Valley | WSIP | [8 empty] | ETL.1450 | 44420819 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117471245 | T2 DI PITTSBURG-CLAYTON #3 3/18 RPR INSS | 44609772 | PITTSBURG-CLAYTON #4 | 003/018 | ICS | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-121.907509 | 37.9921 | ETL.3291 | 41132713 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - Prog Multi
117471319 | T2 DI CNTRVLL-TBL MTN 6/106 RPR INSS | 31457914 | CENTERVILLE-TABLE MTN | 006/106 | 93I | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.712818 | 39.7012 | ETL.6320 | 44417895 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Table Mountain |  |  | Yes
117471400 | T2 DI RND MTN-CTTNWD #2 27/240 INS MRKS | 43877040 | ROUND MTN-COTTONWOOD #2 | 027/240 | ICS | F | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.087126 | 40.6398 | ETL.5640 | 40598920 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117471491 | T2 DI MONTA VST-LS GATOS 9/182 RMV VEGN |  | MONTA VISTA-LOS GATOS | 009/182 | HNA | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-121.991958 | 37.2363 | ETL.7610 | 40597933 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Bay
117471525 | T3 DI COLGATE-CHALLENGE 7/135 RPL STRW | 31462967 | COLGATE-CHALLENGE | 007/135 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.195678 | 39.4181 | ETL.6480 | 40611341 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento
117471743 | T2 DI CARIBOU-WSTWD 7/140C RPL STRW | 31473384 | CARIBOU-WESTWOOD | 007/140C | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  | REJECT: Crew reported they were unable to complete work. Scope of work has been changed. Pleae resubmit once new scope of work has been completed. |  |  | '-121.087819 | 40.1717 | ETL.6300 | 42624247 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
117471913 | T2NT DI SPA SUM 14/466 INS MRKW | 43923458 | SPAULDING-SUMMIT | 014/466 | ICW | F | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.4019 | 39.3286 | ETL.8060 | 40590032 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117472003 | DI SPAULDING-SUMMIT 004/159 RPL STRW | 31495368 | SPAULDING-SUMMIT | 004/159 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-120.571981 | 39.3064 | ETL.8060 | 40602304 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
117472047 | DI HELMS-GREGG #1 5/40 REM NEST | 44301795 | HELMS-GREGG #1 | 005/040A | ICS | E | Pre-2020_(9a) Other ignition related |  |  |  |  | LATE | South | WSIP | FSRP | [5 empty] | '-119.03554 | 37.0007 | ETL.4870 | 40576885 | Structure-Steel | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  | Y - 13
117472276 | T2NT DI DRU SUM 22/263 INST MRKW (R) | 43947608 | DRUM-SUMMIT #2 | 022/263 | ICW | F | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.411689 | 39.3285 | ETL.1450 | 44557730 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117472283 | T2 DI CARIBOU-PALERMO :18/147 RMV DEBRIS |  | CARIBOU-PALERMO | :018/147 | ICW | F | Pre-2020_(3) On high spread structure |  |  |  | TR2 |  | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.329026 | 39.9139 | ETL.3190 | 44549940 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117472284 | T2 DI HAT CREEK #1-WSTWD 31/601 RPR GYWW | 43939292 | HAT CREEK #1-WESTWOOD | 031/601 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.127653 | 40.6227 | ETL.7030 | 40827493 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117472287 | T2NT DI HAT CRK #1-WTWD 31/601 INST MRKW | 43904280 | HAT CREEK #1-WESTWOOD | 031/601 | ICW | F | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP | [5 empty] | reprioritization of work - noncritical facility | '-121.127653 | 40.6227 | ETL.7030 | 40827493 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117472296 | T2 DI SLNS-LRLS A12/269 RMV VEGN |  | SALINAS-LAURELES | A012/269 | HNA | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-121.772494 | 36.5698 | ETL.7930 | 40754673 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Moss Landing
117472340 | T2NT DI DRU SUM 22/263 INST MRKW (L) | 43947608 | DRUM-SUMMIT #2 | 022/263 | ICW | F | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.411689 | 39.3285 | ETL.1450 | 44557783 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117472396 | T2 DI JFFRSN-HILLSDALE JCT 7/41 INS MRKS |  | JEFFERSON-HILLSDALE JCT | 007/041 | ICS | F | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-122.363099 | 37.5387 | ETL.7190 | 44384035 | Marker (i.e. signs)-Steel | No Good/Out of Stdrd | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - Prog Multi | SFPUC (4)
117472401 | T2 DI HAT CRK#1-WSTD 33/649 INST MRKW | 43904280 | HAT CREEK #1-WESTWOOD | 033/649 | ICW | F | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP | [5 empty] | reprioritization of work - noncritical facility | '-121.09734 | 40.5943 | ETL.7030 | 40827600 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117472671 | T3NT DI CAR PAL :31/256B INST MRKS |  | CARIBOU-PALERMO | :031/256B | ICW | F | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR3 |  | North Valley | WSIP |  |  |  |  | Field Operations | reprioritization of work - noncritical facility | '-121.467788 | 39.7593 | ETL.3190 | 44374355 | Marker (i.e. signs)-Wood | Missing | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117473386 | T2 DI HT CRK#1-WSTWD 007/142 RPR GYWW | 43939287 | HAT CREEK #1-WESTWOOD | 007/142 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.422642 | 40.8872 | ETL.7030 | 40758997 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117473595 | DI CASTRO VLY NWRK 13/69 RPL DAMS | 43900133 | TASSAJARA-NEWARK | 023/108 | ICS | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-121.877409 | 37.5668 | ETL.5920 | 40923052 | Damper-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - 1 | SFPUC
117473612 | DI TESLA-LS BNS#1 2/13 RPR GYWS | 43866683 | TESLA-LOS BANOS #1 | 002/013 | ICS | E | Pre-2020_(5) TD tag on other lines |  |  | Tower guy |  | LATE | Central | WSIP | [6 empty] | '-121.526971 | 37.6897 | ETL.6100 | 40651778 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Victor |  | Y - Prog Multi
117473728 | DI PARADISE-BUTTE 009/094A RPR GYWS | 43881381 | PARADISE-BUTTE | 009/094A | ICS | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-121.737332 | 39.7094 | ETL.4396 | 43249546 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117473755 | DI PARADISE-BUTTE 009/094A INST MRKS | 43881381 | PARADISE-BUTTE | 009/094A | ICS | F | Pre-2020_(5b) On structure in bucket 5 | [5 empty] | North Valley | WSIP | [5 empty] | reprioritization of work - noncritical facility | '-121.737332 | 39.7094 | ETL.4396 | 43249546 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117473946 | T2 DI COLGATE-PALERMO 019/377 RPR PL | 43878561 | COLGATE-PALERMO | 019/377 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.460948 | 39.4465 | ETL.6500 | 40599632 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117474078 | DI PALERMO-OROVILLE #2 000/001 RPR GYWW | 43724470 | PALERMO-OROVILLE #2 | 000/001 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-121.517922 | 39.4551 | ETL.7740 | 41123113 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117474312 | DI CARIBOU-PLUMAS JCT 14/6 RPR GYWW | 43920793 | CARIBOU-PLUMAS JCT | 014/006 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-120.954807 | 39.9576 | ETL.6290 | 40810058 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117474387 | T2 DI KESWICK-TRINITY 015/190 REPR STRW | 43939188 | KESWICK-TRINITY | 015/190 | ICW | E | Pre-2020_(2) High fire spread TD |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Access Issues | 2021 - FSR 12/2020 | '-122.672176 | 40.7145 | ETL.7270 | 40668396 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117474570 | T3 DI CLOVER CREEK TAP A5/128 RPR GYWW | 43901760 | CLOVER CREEK TAP | A005/128 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR3 | LATE | North Valley | WSIP | [5 empty] | reprioritization of work - E/F tags pushed to 2020 | '-121.972443 | 40.7083 | ETL.7291 | 42712147 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117474573 | T3NT DI CLOVER CRK TAP A5/128 INST GMKW | 43901760 | CLOVER CREEK TAP | A005/128 | ICW | F | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR3 |  | North Valley | WSIP | [5 empty] | reprioritization of work - noncritical facility | '-121.972443 | 40.7083 | ETL.7291 | 42712147 | Guy Wire Mark /Indic-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117474750 | T2 DI CRBOU-PLRMO :01/10 RPR FOND | 44062862 | CARIBOU-PALERMO | :001/010 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.164829 | 40.0739 | ETL.3190 | 40910257 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
117474816 | T2 DI VOLTA-SOUTH 1/37 RPR STRW | 43827513 | VOLTA-SOUTH | 001/037 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.872648 | 40.4384 | ETL.8300 | 40667419 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117475108 | T2 DI CORDELIA #2 TAP 3/68 RPR GYWW | 43901135 | CORDELIA #2 TAP | 003/068 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.154799 | 38.2509 | ETL.8184 | 40695236 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117476381 | T2 DI VALLEY SPRINGS #1 9/176 RPR GYWW | 43863111 | VALLEY SPRINGS #1 | 009/176 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.874433 | 38.1291 | ETL.8210 | 40908259 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 23
117476382 | T2 DI VALLEY SPRINGS #1 9/184 RPR GYWW | 43863113 | VALLEY SPRINGS #1 | 009/184 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.878384 | 38.1244 | ETL.8210 | 40908269 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 23
117476383 | T2 DI COLGATE-PALERMO 011/210 RPL POLE | 31457073 | COLGATE-PALERMO | 011/210 | 70Y | E | 2020_(1a) PSPS |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.368872 | 39.3701 | ETL.6500 | 40692901 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
117476541 | T2 DI COLGATE-PALERMO 8/159 RPL PL | 31506096 | COLGATE-PALERMO | 008/159 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.330109 | 39.352 | ETL.6500 | 40664523 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
117476619 | DI CENTERVILLE TBL MTN 7/120 RPR GYWS | 43724228 | CENTERVILLE-TABLE MTN | 007/120 | ICS | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-121.718552 | 39.6872 | ETL.6320 | 44648728 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117476674 | DI CENTERVILLE TBL MTN 7/120 INST MRKS | 43878257 | CENTERVILLE-TABLE MTN | 007/120 | ICS | F | Pre-2020_(5b) On structure in bucket 5 | [5 empty] | North Valley | WSIP | [5 empty] | reprioritization of work - noncritical facility | '-121.718552 | 39.6872 | ETL.6320 | 44648728 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117476785 | T2 DI CRESTA-RIO OSO 30/243 RPL HRDT | 43708739 | CRESTA-RIO OSO | 030/243 | ICS | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.535087 | 39.5443 | ETL.4590 | 41083103 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain
117476817 | T2 DI NEWARK-LIVERMORE 16/96 RPR STRW | 43877617 | NEWARK-LIVERMORE | 016/096 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-121.776232 | 37.6342 | ETL.7660 | 40580690 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Bay |  | Y - 8
117476869 | T2 DI VALLEY SPRINGS #1 8/167 RPR PL | 43863106 | VALLEY SPRINGS #1 | 008/167 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.869751 | 38.1343 | ETL.8210 | 40908250 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 23
117476879 | T2 DI SPAULDING-SUMMIT 13/453 RPR PL | 43923458 | SPAULDING-SUMMIT | 013/453 | ICW | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.411649 | 39.3283 | ETL.8060 | 40603905 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117476935 | T2 DI LAYTONVILLE-WILL 17/9 RPL POLE | 31490917 | LAYTONVILLE-WILLITS | 017/009 | 70Y | F | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | FSRP | [5 empty] | '-123.46341 | 39.6176 | ETL.8360 | 40860923 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville
117476952 | T2 DI SALINAS-LAURELES A017/359 RMV VEGN |  | SALINAS-LAURELES | A017/359 | HNA | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | South | WSIP | [5 empty] | Per Cal Trans District 5, unless the trees are dead, the removal of the trees as a scenic resource will require Coastal Development Permit or some other kind of locally driven approval that complies with CEQA. | '-121.842795 | 36.582 | ETL.7930 | 40600163 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Moss Landing
117476962 | T3NT DI DRUM-RIO OSO #1 004/047 PAINT | 43908283 | DRUM-RIO OSO #1 | 004/047 | ICS | F | Pre-2020_(9a) Other ignition related |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.83335 | 39.228 | ETL.1420 | 40819129 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes
117476975 | T2 DI SPAULDING-SUMMIT 12/428 MRKW CNCL | 43923458 | SPAULDING-SUMMIT | 012/428 | ICW | F | Pre-2020_(1b) Lines with special commitments |  |  | CANCEL/CNCL | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.431857 | 39.325 | ETL.8060 | 40618259 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117477116 | T2 DI IGNACIO-ALTO 15/155 RPL STRW | 31492618 | IGNACIO-ALTO | 015/155 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.51466 | 37.918 | ETL.7150 | 40668130 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville
117477161 | T2 DI STANISLAUS-MANTECA 2 5/29 RPR FOND | 44460412 | STANISLAUS-MANTECA #2 | 005/029 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.4463 | 38.1064 | ETL.3820 | 40856495 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - Prog Multi
117477177 | T2 DI VALLEY SPRINGS #1 8/165 RPR PL | 43863105 | VALLEY SPRINGS #1 | 008/165 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.868789 | 38.1355 | ETL.8210 | 40908248 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 23
117477263 | DI STANISLAUS-NEW #1 83/552 RPR FOND |  | STANISLAUS-NEWARK #1 (12KV) | 083/552 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-121.73798 | 37.6571 | ETL.3850 | 41196042 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog Multi
117477264 | T2 DI SPAULDING-SUMMIT 16/503 INS MRKW | 43923458 | SPAULDING-SUMMIT | 016/503 | ICW | F | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.379091 | 39.3215 | ETL.8060 | 40603910 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117477265 | DI STANISLAUS-NEW #1 83/552 RPR STRT |  | STANISLAUS-NEWARK #1 (12KV) | 083/552 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-121.73798 | 37.6571 | ETL.3850 | 41196042 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 5
117477464 | T2 DI SPAULDING-SUMMIT 18/586 INS MRKW | 43923458 | SPAULDING-SUMMIT | 018/586 | ICW | F | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.340594 | 39.3096 | ETL.8060 | 40577367 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117477639 | T2 DI HT CRK #1-WESTWOOD 23/454 CANCEL | 43904280 | HAT CREEK #1-WESTWOOD | 023/454 | ICW | F | Pre-2020_(4b) On structure in bucket 4 |  |  | CANCEL/CNCL | TR2 |  | North Valley | WSIP | [5 empty] | reprioritization of work - noncritical facility | '-121.22812 | 40.7021 | ETL.7030 | 40656892 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117477656 | T2 DI COLGATE-PALERMO 019/377 INST MRKW | 43878563 | COLGATE-PALERMO | 019/377 | ICW | F | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP | [5 empty] | reprioritization of work - noncritical facility | '-121.460948 | 39.4465 | ETL.6500 | 40599632 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117477755 | T2 DI HT CRK #1-WESTWOOD 37/716 RPL PL | 31456280 | HAT CREEK #1-WESTWOOD | 037/716 | 70Y | E | Pre-2020_(2) High fire spread TD |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Access Issues | 2021 - Snow . FSR 12/2020 | '-121.059193 | 40.5531 | ETL.7030 | 40816880 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain
117478052 | DI STANISLAUS-NEWARK #1 84/556 RPR STRT |  | STANISLAUS-NEWARK #1 (12KV) | 084/556 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-121.746267 | 37.653 | ETL.3850 | 41195974 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 5
117478053 | DI STA NEW #1 83/553 RPR STUBS |  | STANISLAUS-NEWARK #1 (12KV) | 083/553 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-121.739502 | 37.6564 | ETL.3850 | 41196044 | Foundation/Concrete-Tower | Earth Covered Tower | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 7
117478144 | T2NT DI HAT CRK#1 WSTWD 26/503 INST MRKW | 43904280 | HAT CREEK #1-WESTWOOD | 026/503 | ICW | F | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP | [5 empty] | reprioritization of work - noncritical facility | '-121.197668 | 40.6739 | ETL.7030 | 40759035 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117478191 | T2NT DI HAT CRK#1 WSTWD 28/553 INST GMKW | 43904280 | HAT CREEK #1-WESTWOOD | 028/553 | ICW | F | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP | [5 empty] | reprioritization of work - noncritical facility | '-121.165163 | 40.6462 | ETL.7030 | 40759039 | Guy Wire Mark /Indic-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117478197 | DI POE RIO OSO 32/217 PAINT | 43875009 | POE-RIO OSO | 032/217 | ICS | F | Pre-2020_(4b) On structure in bucket 4 | [5 empty] | North Valley | WSIP | [6 empty] | '-121.536853 | 39.5214 | ETL.5540 | 40814851 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117478595 | DI VOLTA-DESCHUTES 20/464 RPL POLE | 31453473 | VOLTA-DESCHUTES | 020/464 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.239761 | 40.5556 | ETL.8290 | 42607768 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
117478638 | DI POE RIO OSO 32/216 RPR HRDS | 43875009 | POE-RIO OSO | 032/216 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-121.536684 | 39.524 | ETL.5540 | 40815733 | Hardware-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117478649 | T2NT DI HAT CRK#1 WSTWD 24/466 INST MRKW | 43904280 | HAT CREEK #1-WESTWOOD | 024/466 | ICW | F | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP | [5 empty] | reprioritization of work - noncritical facility | '-121.220435 | 40.6951 | ETL.7030 | 40817129 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117478826 | DI RND MTN-CTTNWD#3 51/458 INS MRKS | 43876249 | ROUND MTN-COTTONWOOD #3 | 051/458 | ICS | F | Pre-2020_(4b) On structure in bucket 4 | [5 empty] | North Valley | WSIP | [5 empty] | reprioritization of work - noncritical facility | '-122.186793 | 40.4936 | ETL.5650 | 40862659 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117478838 | DI IGNC SN RFL #3 1/26 RPR GYWW | 43919193 | IGNACIO-SAN RAFAEL #3 NF | 001/026 | ICW | E | Pre-2020_(9a) Other ignition related |  |  |  |  | LATE | North Coast | WSIP | FSRP | [5 empty] | '-122.532067 | 38.0594 | ETL.1860 | 44680761 | Guy Wire-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
117478950 | T2 DI DRUM-RIO OSO#1 30/219 RPL EYE-PLAT | 43908283 | DRUM-RIO OSO #1 | 030/219 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.248194 | 39.0445 | ETL.1420 | 40864699 | Hardware-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Sacramento |  |  | Yes
117478952 | DI POE-RIO OSO 33/220 INS HRDT | 43854765 | POE-RIO OSO | 033/220 | ICQ | F | Pre-2020_(9a) Other ignition related |  |  |  |  | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.536481 | 39.5156 | ETL.5540 | 40605303 | Hardware-Tower | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
117479219 | DI STANISLAUS-NEWARK#2 88/579 RPR FOND |  | STANISLAUS-NEWARK #2 (12KV) | 088/579 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-121.80416 | 37.6219 | ETL.3860 | 44188781 | Foundation/Concrete-Tower | Earth Covered Tower | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog Multi
117479452 | T2 DI SMA MAR 2/48 REFRAME | 31499716 | SMARTVILLE-MARYSVILLE | 002/048 | 93E | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.343103 | 39.2009 | ETL.7980 | 40602028 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Sacramento
117480449 | T3 DI VOLTA-SOUTH 000/020 REPL SPLW | 43827513 | VOLTA-SOUTH | 000/020 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR3 | LATE | North Valley | WSIP | [5 empty] | reprioritization of work - E/F tags pushed to 2020 | '-121.867703 | 40.4494 | ETL.8300 | 40615951 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117480549 | T3 EI DRUM-HIGGINS 02/27 RPL POLE | 31423108 | DRUM-HIGGINS | 002/027 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-120.795057 | 39.2286 | ETL.4393 | 44172273 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
117480559 | T2 DI HMLTON BRNCH-CHSTR 9/194 REPL STRW | 31439198 | HAMILTON BRANCH-CHESTER | 009/194 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.18056 | 40.3124 | ETL.7000 | 40770669 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
117480600 | T2 DI HMLTON BRNCH-CHSTR 7/168 REPR GYWW | 43879596 | HAMILTON BRANCH-CHESTER | 007/168 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.160822 | 40.3029 | ETL.7000 | 40815860 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117480752 | T2 EI SPAULDING-SUMMIT 003/126 RPL POLE | 31453471 | SPAULDING-SUMMIT | 003/126 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.58706 | 39.3141 | ETL.8060 | 40809649 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
117480756 | EI FULTON-IGNACIO #1 1/8 RPR FOND | 44310541 | FULTON-IGNACIO #1 | 001/008 | ICQ | F | Pre-2020_(9a) Other ignition related | [5 empty] | North Coast | Non-WSIP | [6 empty] | '-122.739923 | 38.4975 | ETL.4680 | 40863589 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville
117480833 | T2NT EI SPAULDING-SUMMIT 3/123 RMV SIGN | 43923458 | SPAULDING-SUMMIT | 003/123 | ICW | F | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.589626 | 39.3135 | ETL.8060 | 40771495 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117480857 | T2 EI SPAULDING-SUMMIT 3/121 RMV VEGN | 43923458 | SPAULDING-SUMMIT | 003/121 | ICW | E | Pre-2020_(1b) Lines with special commitments |  |  | Likely veg | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.591299 | 39.3131 | ETL.8060 | 40701997 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117480870 | T2NT DI VACA-LAKEVILLE #1 8/40 INST MRKS | 43908800 | VACA-LAKEVILLE #1 | 008/040 | ICS | F | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.034111 | 38.3684 | ETL.5840 | 40598949 | Marker (i.e. signs)-Steel | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes
117481009 | T2 EI SPAULDING-SUMMIT 2/111 RPL PL | 31453471 | SPAULDING-SUMMIT | 002/111 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.597406 | 39.3134 | ETL.8060 | 40668658 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
117481014 | T2 EI SPAULDING-SUMMIT 2/112 RMV VEGN | 43923458 | SPAULDING-SUMMIT | 002/112 | ICW | E | Pre-2020_(1b) Lines with special commitments |  |  | Likely veg | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.596911 | 39.3132 | ETL.8060 | 40771550 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117481124 | T2 DI SALINAS-LAURELES A016/353 RMV VEGN |  | SALINAS-LAURELES | A016/353 | HNA | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | South | WSIP | [5 empty] | Per Cal Trans District 5, unless the trees are dead, the removal of the trees as a scenic resource will require Coastal Development Permit or some other kind of locally driven approval that complies with CEQA. | '-121.837614 | 36.5808 | ETL.7930 | 40876152 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Moss Landing
117481197 | T2 EI SPAULDING-SUMMIT 003/130 INST MRKW | 43923458 | SPAULDING-SUMMIT | 003/130 | ICW | F | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.585377 | 39.3106 | ETL.8060 | 40602286 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117481227 | T2 DI HAT CRK #1-WESTWD 34/659 INST MRKW | 43904280 | HAT CREEK #1-WESTWOOD | 034/659 | ICW | F | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.091532 | 40.5881 | ETL.7030 | 40816155 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117481230 | T2 DI SALINAS-LAURELES A16/350 RMV VEGN |  | SALINAS-LAURELES | A016/350 | HNA | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | South | WSIP | [5 empty] | Per Cal Trans District 5, unless the trees are dead, the removal of the trees as a scenic resource will require Coastal Development Permit or some other kind of locally driven approval that complies with CEQA. | '-121.834939 | 36.581 | ETL.7930 | 40754679 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Moss Landing
117481239 | DI VOLTA-DESCHUTES 020/459 REPR GYWW | 43939089 | VOLTA-DESCHUTES | 020/459 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.238568 | 40.555 | ETL.8290 | 40816205 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117481269 | T2 DI MIDDLE FRK-GLD HILL 26/207L RPL PL | 31471246 | MIDDLE FORK-GOLD HILL | 026/207 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.945506 | 38.8126 | ETL.5140 | 44558401 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS erdy | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
117481271 | DI VOLTA-DESCHUTES 020/459 INST MRKW | 43939089 | VOLTA-DESCHUTES | 020/459 | ICW | F | Pre-2020_(4b) On structure in bucket 4 | [5 empty] | North Valley | WSIP | [6 empty] | '-122.238568 | 40.555 | ETL.8290 | 40816205 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117481787 | DI NEWARK-VALLECITOS 93/607 RPR FOND |  | NEWARK-VALLECITOS | 093/607 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-121.869978 | 37.5863 | ETL.7670 | 44883851 | Foundation/Concrete-Tower | Earth Covered Tower | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 9
117481788 | T2 DI VALLEY SPRINGS #1 A01/30 RPR STRW | 43865295 | VALLEY SPRINGS #1 | A001/030 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.741193 | 38.2051 | ETL.8210 | 40907087 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog Multi
117481810 | T2 DI VALLEY SPRINGS #1 A01/35 RPR STRW | 43865298 | VALLEY SPRINGS #1 | A001/035 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.736974 | 38.2039 | ETL.8210 | 40907092 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog Multi
117481861 | T2 DI STNSLS-MELNS SS-MNTC 8/49 RPR FOND | 44460417 | STANISLAUS-MELONES SS-MANTECA #1+ | 008/049 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.492825 | 38.0808 | ETL.3830 | 40857653 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - Prog Multi
117481929 | DI VALLEY SPRINGS #1 010/210 RPR GYWW | 43857861 | VALLEY SPRINGS #1 | 010/210 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | Central | WSIP |  |  |  |  | Clearance Denied by GCC | Clearance denied due to heat, Tman checked structure and feels it is safe to perform work in Nov under new clearance. [REDACTED] | '-120.897144 | 38.1152 | ETL.8210 | 40908295 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 23
117482376 | T2 DI MTN GTE JCT CAS 2/24 RPL PL (R) | 31439163 | MTN GATE JCT-CASCADE | 002/024 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.319553 | 40.7105 | ETL.7640 | 44565548 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC erdy srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
117482468 | T2 DI STLS-MLS SS-MTC #1 25/159 REPAINT | 43878406 | STANISLAUS-MELONES SS-MANTECA #1+ | 025/159 | ICS | F | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) |  |  | TR2 |  | Central | WSIP | [6 empty] | '-120.745475 | 37.9304 | ETL.3830 | 40803332 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - Prog Multi
117482471 | T2 DI STSLS-MLS SS-MTC #1 :6/35 PNT STRS | 43878406 | STANISLAUS-MELONES SS-MANTECA #1+ | :006/035 | ICS | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.624725 | 37.9743 | ETL.3830 | 40744455 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - Prog Multi
117482645 | DI PALERMO-OROVILLE 0/3 RPR GYWW | 43724470 | PALERMO-OROVILLE #2 | 000/003 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-121.519024 | 39.455 | ETL.7740 | 41123115 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117482647 | DI PALERMO-OROVILLE 0/3 INST MRKW | 43724470 | PALERMO-OROVILLE #2 | 000/003 | ICW | F | Pre-2020_(5b) On structure in bucket 5 | [5 empty] | North Valley | WSIP | [6 empty] | '-121.519024 | 39.455 | ETL.7740 | 41123115 | Marker (i.e. signs)-Wood | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117482855 | T3 DI RND MTN-CTTNWD 033/280 RMV VEGN |  | ROUND MTN-COTTONWOOD #2 | 033/280 | HNA | E | Pre-2020_(9a) Other ignition related |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-122.149449 | 40.5658 | ETL.5640 | 40598925 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Table Mountain |  |  | Yes
117483039 | T3 DI PARADISE-TBL MTN 016/134C RPR POLE | 43724325 | PARADISE-TABLE MTN | 016/134 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR3 | LATE | North Valley | WSIP | [5 empty] | reprioritization of work - E/F tags pushed to 2020 | '-121.499399 | 39.6792 | ETL.4316 | 44552318 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117483096 | T3 DI PARADISE-TBL MTN 016/134R RPR POLE | 43724325 | PARADISE-TABLE MTN | 016/134 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR3 | LATE | North Valley | WSIP | [5 empty] | reprioritization of work - E/F tags pushed to 2020 | '-121.499399 | 39.6792 | ETL.4316 | 44552501 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117483129 | T3NT DI PRDS-TBL MTN 016/134C INST MRKW | 43724325 | PARADISE-TABLE MTN | 016/134 | ICW | F | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR3 |  | North Valley | WSIP | [5 empty] | reprioritization of work - noncritical facility | '-121.499399 | 39.6792 | ETL.4316 | 44552318 | Marker (i.e. signs)-Wood | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117483150 | T3NT DI PRDS-TBL MTN 016/134R INST MRKW | 43724325 | PARADISE-TABLE MTN | 016/134 | ICW | F | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR3 |  | North Valley | WSIP | [5 empty] | reprioritization of work - noncritical facility | '-121.499399 | 39.6792 | ETL.4316 | 44552501 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117483192 | DI LAS POSITAS-NEWARK 014/090 PAINT STRT | 43753291 | LAS POSITAS-NEWARK | 014/090 | ICS | F | Pre-2020_(9a) Other ignition related | [5 empty] | Central | WSIP | [6 empty] | '-121.890686 | 37.549 | ETL.4980 | 40870183 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay
117483210 | T2 DI VLY SPRNGS-CLY 12/165 RPR WP HOLES | 43866744 | VALLEY SPRINGS-CLAY | 012/165 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.890851 | 38.278 | ETL.8264 | 40911614 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog Multi
117483215 | T2 DI NEWARK-LIVERMORE 016/101 RPL POLE | 31455746 | NEWARK-LIVERMORE | 016/101 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-121.77932 | 37.6379 | ETL.7660 | 40804524 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Bay |  | Y - 9 | Sycamore Grove Park
117483384 | T2 DI TRINITY-MAPLE CRK 10/17R RPR GYWW | 43749708 | TRINITY-MAPLE CREEK | 010/017 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [8 empty] | ETL.8170 | 44420597 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2019-10-23
117483575 | T3 DI DRUM-HIGGING 10/96L RPR GYWW | 43903303 | DRUM-HIGGINS | 010/096 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-120.893154 | 39.1785 | ETL.4393 | 44202756 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
117483579 | T3 DI DRUM-HIGGING 10/96C RPR GYWW | 43903303 | DRUM-HIGGINS | 010/096 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-120.893154 | 39.1785 | ETL.4393 | 44202757 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
117483582 | T3 DI DRUM-HIGGING 10/96R RPR GYWW | 43903303 | DRUM-HIGGINS | 010/096 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-120.893154 | 39.1785 | ETL.4393 | 44202755 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
117483592 | DI STA MEL SW SRA MAN 26/169 PNT STRS | 43878406 | STANISLAUS-MELONES SS-MANTECA #1+ | 026/169 | ICS | F | Pre-2020_(9a) Other ignition related | [5 empty] | Central | WSIP | [6 empty] | '-120.773529 | 37.922 | ETL.3830 | 40803334 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - Prog Multi
117483595 | T2NT DI HAT CRK#1 WSTWD 40/780 INST MRKW | 43904280 | HAT CREEK #1-WESTWOOD | 040/780 | ICW | F | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP | [5 empty] | reprioritization of work - noncritical facility | '-121.030857 | 40.5095 | ETL.7030 | 40770769 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117483865 | T2 DI COL CHA 0/19 RPR GYWW | 43910648 | COLGATE-CHALLENGE | 000/019 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.19143 | 39.3421 | ETL.6480 | 40866889 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
117483867 | T2NT DI COL CHA 0/19 INST MRKW | 43910648 | COLGATE-CHALLENGE | 000/019 | ICS | F | Pre-2020_(4b) On structure in bucket 4 |  |  | Likely MAT error - delink to correct | TR2 |  | North Valley | WSIP | [6 empty] | '-121.19143 | 39.3421 | ETL.6480 | 40866889 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
117484173 | T2 DI HT CRK #1 WW 32/625 RPR PL | 43736798 | HAT CREEK #1-WESTWOOD | 032/625 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.111218 | 40.6092 | ETL.7030 | 40592108 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117484197 | T2 DI VALLEY SPRINGS A002/043 RPR STRW | 43865299 | VALLEY SPRINGS #1 | A002/043 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.730492 | 38.2018 | ETL.8210 | 40907100 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog Multi
117484320 | T2 CLAY-MARTEL 31/475R REPR LOOSE GUYS | 43857870 | CLAY-MARTEL | 031/475 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | Non-WSIP | [6 empty] | '-120.844654 | 35.4243 | ETL.8250 | 44254765 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 33
117484400 | T2 DI ORVLLE-TERLO-TBLE#3 2/11 INST MRKS | 43933021 | MTN #3 (CDWR) | 002/011 | ICS | F | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 |  | North Valley | WSIP | [5 empty] | reprioritization of work - noncritical facility | '-121.522945 | 39.5464 | ETL.6622 | 42580956 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117484494 | T2 DI STA MEL SW STA 0/1 PNT STRS | 43878406 | STANISLAUS-MELONES SS-MANTECA #1+ | 000/001 | ICS | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-120.373847 | 38.1395 | ETL.3830 | 40579566 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - 9
117484515 | T3 DI KLRC-CEDAR CRK 11/245 RPR STRW | 43724328 | KILARC-CEDAR CREEK | 011/245 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [5 empty] | reprioritization of work - E/F tags pushed to 2020 | '-121.960302 | 40.7653 | ETL.7290 | 40650325 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117484544 | T2 DI SPAULDING-SUMMIT 000/021 RPR GYWW | 43923459 | SPAULDING-SUMMIT | 000/021 | ICW | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.636447 | 39.3228 | ETL.8060 | 40586116 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117484573 | DI RND MTN-COTTONWD #3 55/496 REPAINT | 43755801 | ROUND MTN-COTTONWOOD #3 | 055/496 | ICQ | F | Pre-2020_(9a) Other ignition related |  |  | Likely MAT error - delink to correct |  |  | North Valley | WSIP | [6 empty] | '-122.223248 | 40.4495 | ETL.5650 | 40817529 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain
117484596 | T2NT DI ORVL-TRT-TBL MT 002/011 INS MRKS | 43932169 | MTN #1(CDWR) | 002/011 | ICS | F | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 |  | North Valley | WSIP | [5 empty] | reprioritization of work - noncritical facility | '-121.522911 | 39.5466 | ETL.6621 | 42580634 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117484661 | T2 EI DRUM-SUMMIT #2 18/213 INSTL GMKW | 43947607 | DRUM-SUMMIT #2 | 018/213 | ICW | F | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.485723 | 39.3167 | ETL.1450 | 44550043 | Guy Wire Mark /Indic-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117484674 | T2 DI SPAULDING-SUMMIT 015/483 RPR STRW | 43923459 | SPAULDING-SUMMIT | 015/483 | ICW | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.389485 | 39.3289 | ETL.8060 | 40770708 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117484750 | T2 DI ORVL-TRTO-TBE MTN#3 2/10 INST MRKS | 43933021 | MTN #3 (CDWR) | 002/010 | ICS | F | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 |  | North Valley | WSIP | [5 empty] | reprioritization of work - noncritical facility | '-121.519462 | 39.5464 | ETL.6622 | 42580955 | Marker (i.e. signs)-Steel | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117484900 | T2 EI DRUM-SUMMIT #2 18/214L REPL PL | 31521949 | DRUM-SUMMIT #2 | 018/214 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.483627 | 39.3171 | ETL.1450 | 44552369 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
117485040 | T2 DI PITTSBRG-SN MTEO 006/028 RPR FOND | 44238800 | PITTSBURG-SAN MATEO | 006/028 | ICQ | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-121.892903 | 37.9538 | ETL.5463 | 40644625 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 8
117485042 | DI VAC-VACAVILLE-CORDELIA 3/26 RPR SPLS | 43910119 | VACA-VACAVILLE-CORDELIA | 003/026 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | North Valley | WSIP |  |  |  | REJECT: Crew reported work not needed. Please confirm(approve) or reject if disagree. Please create a new tag per field note. |  |  | '-121.981896 | 38.4049 | ETL.4090 | 40841249 | Splice-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes
117485181 | T2 EI DRUM-SUMMIT #2 18/214 REPL PL | 31521949 | DRUM-SUMMIT #2 | 018/214 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.483627 | 39.3171 | ETL.1450 | 44552495 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
117485291 | T2 EI DRUM-SUMMIT #2 18/217 INSTL GMKW | 43947607 | DRUM-SUMMIT #2 | 018/217 | ICW | F | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.480702 | 39.3174 | ETL.1450 | 44552421 | Guy Wire Mark /Indic-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117485389 | NT EI OLEUM-NRTH TWR-CHRIST 0/6 PNT TWR | 43752229 | OLEUM-NORTH TOWER-CHRISTIE | 000/006 | ICS | F | Pre-2020_(5b) On structure in bucket 5 | Budget Owner (Paint) |  |  |  |  | Central | WSIP | [6 empty] | '-122.24671 | 38.0407 | ETL.3180 | 40804798 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  | Y - Prog Multi
117485598 | NT EI OLEUM-NRTH TWR-CHRIST 0/4 PNT TWR | 43752229 | OLEUM-NORTH TOWER-CHRISTIE | 000/004 | ICS | F | Pre-2020_(5b) On structure in bucket 5 | Budget Owner (Paint) |  |  |  |  | Central | WSIP | [6 empty] | '-122.251731 | 38.0418 | ETL.3180 | 40746018 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  | Y - Prog Multi
117486289 | T2 EI RND MTN-COTTNWD #3 R1/16L RPR STRW | 43946912 | ROUND MTN-COTTONWOOD #3 | R001/016 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-121.935935 | 40.7985 | ETL.5650 | 44765641 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117486350 | T2 EI RND MTN-COTTNWD #3 R01/16 INS MRKW | 43755804 | ROUND MTN-COTTONWOOD #3 | R001/016 | ICW | F | Pre-2020_(4b) On structure in bucket 4 | [5 empty] | North Valley | WSIP | [5 empty] | reprioritization of work - noncritical facility | '-121.935935 | 40.7985 | ETL.5650 | 44765641 | Marker (i.e. signs)-Wood | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117486867 | DI NEWARK-LIVERMORE 008/052 PAINT STRS | 43752137 | NEWARK-LIVERMORE | 008/052 | ICS | E | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) |  |  |  | LATE | Central | WSIP | [6 empty] | '-121.868233 | 37.5732 | ETL.7660 | 40645722 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay
117487171 | T2 HUMBOLDT-TRINITY 67/0 RMV BUTT | 44311171 | HUMBOLDT-TRINITY | 067/000 | ICW | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-123.279785 | 40.7163 | ETL.1820 | 44562262 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
117487179 | T2 HUMBOLDT-TRINITY 069/005 RMV BUTT | 44311171 | HUMBOLDT-TRINITY | 069/005 | ICW | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-123.328789 | 40.7053 | ETL.1820 | 44562218 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2019-10-04
117487649 | T2 DRUM-SUMMIT #2 023/276R REPL STRW | 31451466 | DRUM-SUMMIT #2 | 023/276 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-120.390804 | 39.3292 | ETL.1450 | 44557684 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
117487732 | T2 DI MADISON-VACA 50/312 RMV NEST | 43910328 | MADISON-VACA | 050/312 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.98933 | 38.4183 | ETL.2170 | 40643367 | Structure-Steel | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento
117487865 | T2 DI SPAULDING-SUMMIT 3/120 RPL STRW | 31453471 | SPAULDING-SUMMIT | 003/120 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.592151 | 39.3129 | ETL.8060 | 40586083 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
117488140 | T2NT DI BLACK TAP 0/3 INS GMKS | 44304022 | BLACK TAP | 000/003 | ICS | F | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP | [5 empty] | reprioritization of work - noncritical facility | '-121.978299 | 40.9876 | ETL.5431 | 44188817 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain
117488204 | T2 DI HT CRK #1-WSTWD 024/466 RPR GYWW | 43939292 | HAT CREEK #1-WESTWOOD | 024/466 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.220435 | 40.6951 | ETL.7030 | 40817129 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117488269 | T2NT DI MAL RD MT #2 70/357 RPL GMKS | 44305271 | MALIN-ROUND MTN #2 | 070/357 | ICS | F | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | WECC | North Valley | WSIP | [6 empty] | '-121.781686 | 41.0903 | ETL.6020 | 40819380 | Guy Wire Mark /Indic-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117488292 | T2 DI SPALDNG-SUMMIT 10/344 RPL PL | 31495368 | SPAULDING-SUMMIT | 010/344 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.476602 | 39.3175 | ETL.8060 | 40809667 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
117488375 | T2NT DI MLIN-RND MTN #2 71/359 INST GMKS | 43621093 | MALIN-ROUND MTN #2 | 071/359 | ICQ | F | Pre-2020_(1b) Lines with special commitments |  |  | Likely MAT error - delink to correct | TR2 | WECC | North Valley | WSIP | [6 empty] | '-121.788067 | 41.0852 | ETL.6020 | 40858177 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117488402 | T2 DI SNTH LN-PCFCA 004/050R RPL ANCW | 31488021 | SNEATH LANE-PACIFICA | 004/050 | 93E | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | Central | WSIP | [8 empty] | ETL.7575 | 44384744 | Anchor-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Bay |  | Y - 6
117488415 | T2NT DI MAL RD MT #2 68/342 INST GMKS | 43621093 | MALIN-ROUND MTN #2 | 068/342 | ICQ | F | Pre-2020_(1b) Lines with special commitments |  |  | Likely MAT error - delink to correct | TR2 | WECC | North Valley | WSIP | [6 empty] | '-121.744196 | 41.12 | ETL.6020 | 40660987 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117488541 | T2 EI SPAULDING-SUMMIT 010/347 RPL POLE | 31453471 | SPAULDING-SUMMIT | 010/347 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.475127 | 39.3177 | ETL.8060 | 40618206 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
117488625 | EI OLEUM-G #1 003/022 REPAINT | 44586166 | OLEUM-G #1 | 003/022 | ICS | F | Pre-2020_(9a) Other ignition related | [5 empty] | Central | Non-WSIP | [6 empty] | '-122.234184 | 38.0152 | ETL.3150 | 40646292 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay
117488632 | EI OLEUM-G #1 003/022 INST HRDT |  | OLEUM-G #1 | 003/022 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  |  | LATE | Central | Non-WSIP | [6 empty] | '-122.234184 | 38.0152 | ETL.3150 | 40646292 | Hardware-Tower | Missing | Install |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 8
117488912 | DI COLGATE-PALERMO 022/445 RPL POLE | 31501100 | COLGATE-PALERMO | 022/445 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-121.518207 | 39.4555 | ETL.6500 | 40822466 | Structure-Wood | Rotten | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
117489149 | EI OLEUM-G #1 002/021 REPAINT | 44586166 | OLEUM-G #1 | 002/021 | ICS | F | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) |  |  |  |  | Central | Non-WSIP | [6 empty] | '-122.234171 | 38.0172 | ETL.3150 | 40580895 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay
117489216 | T2 EI SPAULDING-SUMMIT 010/353 RPL POLE | 31453471 | SPAULDING-SUMMIT | 010/353 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.472145 | 39.318 | ETL.8060 | 40828144 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
117489532 | T2 DI VALLEY SPRINGS#1 5/94 RPL POLE | 31455760 | VALLEY SPRINGS #1 | 005/094 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.833891 | 38.1748 | ETL.8210 | 40905509 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 23
117489608 | DI CONTRA COSTA-LS POSITAS 7/49 CANCEL | 44587767 | CONTRA COSTA-LAS POSITAS | 007/049 | ICS | F | Pre-2020_(5b) On structure in bucket 5 | Budget Owner (Paint) |  | CANCEL/CNCL |  |  | Central | WSIP | [6 empty] | '-121.745519 | 37.9105 | ETL.4510 | 40872899 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  | Y - Prog Multi
117489715 | DI MORAGA-LAKEWOOD 009/073 RPR SPLS | 43877251 | MORAGA-LAKEWOOD | 009/073 | ICS | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-122.12562 | 37.8701 | ETL.3741 | 40644192 | Splice-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - Prog Multi
117489745 | EI MORAGA-SAN LEANDRO #1 09/67 REPAINT | 43708450 | MORAGA-SAN LEANDRO #1 | 009/067 | ICS | E | Pre-2020_(9a) Other ignition related |  |  |  |  | LATE | Central | Non-WSIP | [6 empty] | '-122.135162 | 37.7234 | ETL.2770 | 40804658 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - Prog Multi
117489817 | EI SOBRANTE-STNDD OL SW #1 7/46 RPR JUMS | 43877550 | SOBRANTE-STANDARD OIL SW STA #2 | 007/046 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | Central | Non-WSIP | [6 empty] | '-122.23903 | 37.9999 | ETL.3800 | 40810740 | Jumper-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - Prog Multi
117489828 | T2NT DI COT DEL #1 7/48 PNT STRS | 44305035 | COTTONWOOD-DELEVAN #1 | 007/048 | ICS | F | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.268088 | 40.2948 | ETL.4550 | 40869183 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117490001 | T2 DI SPAULDING-SUMMIT 11/370 RPL STRW | 31495368 | SPAULDING-SUMMIT | 011/370 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.461299 | 39.3189 | ETL.8060 | 40702059 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
117490304 | DI NEWARK-LIVERMORE 006/043 RPL INSS | 31479060 | NEWARK-LIVERMORE | 006/043 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-121.890098 | 37.5486 | ETL.7660 | 40671135 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - Prog Multi
117490533 | EI MORAGA-SAN LEANDRO #1 9/69 REPAINT | 43708450 | MORAGA-SAN LEANDRO #1 | 009/069 | ICS | E | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) |  |  |  | LATE | Central | Non-WSIP | [6 empty] | '-122.136011 | 37.7222 | ETL.2770 | 40861002 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay
117490656 | DI CORDELLA #2 2/50 RPL POLE | 31454608 | CORDELIA #2 TAP | 002/050 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-122.144643 | 38.2348 | ETL.8184 | 40595149 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento
117490668 | T2 DI VALLEY SPRINGS #1 009/177 RPR STRW | 43863112 | VALLEY SPRINGS #1 | 009/177 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.874985 | 38.1285 | ETL.8210 | 40908262 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 23
117490693 | T2 DI CNTRVLL-TBL MTN 006/095 RPL STRW | 31495728 | CENTERVILLE-TABLE MTN | 006/095 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.708983 | 39.7105 | ETL.6320 | 40766975 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
117490697 | T2NT DI CNTRVLL-TBL MTN 6/095 MRKW CNCL | 43878256 | CENTERVILLE-TABLE MTN | 006/095 | ICS | F | Pre-2020_(5b) On structure in bucket 5 |  |  | Likely MAT error - delink to correct | TR2 |  | North Valley | WSIP | [5 empty] | reprioritization of work - noncritical facility | '-121.708983 | 39.7105 | ETL.6320 | 40766975 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117490726 | T2 EI SPAULDING-SUMMIT 010/360 RPL INSW | 31463883 | SPAULDING-SUMMIT | 010/360 | 93I | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.4665911 | 39.319 | ETL.8060 | 40678214 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Sacramento |  |  | Yes
117490728 | T2 DI STNISLS-MNTCA #2 12/73 RPR FOND |  | STANISLAUS-MANTECA #2 | 012/073 | ICQ | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.567115 | 38.0418 | ETL.3820 | 40642813 | Foundation/Concrete-Tower | Earth Covered Tower | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - 27
117490754 | T2 DI STNISLS-MNTCA #2 004/025 RPR FOND |  | STANISLAUS-MANTECA #2 | 004/025 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.43658 | 38.1117 | ETL.3820 | 40750233 | Foundation/Concrete-Tower | Earth Covered Tower | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - Prog Multi
117490815 | T2 DI CHR SOB 10/56 RPR CONDS | 43877470 | CHRISTIE-SOBRANTE | 010/056 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.198877 | 37.9972 | ETL.1260 | 40819643 | Shield Wire / OPGW-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - Prog Land
117490953 | EI MORAGA-SAN LEANDRO #1 09/70 REPAINT | 43708450 | MORAGA-SAN LEANDRO #1 | 009/070 | ICS | E | Pre-2020_(9a) Other ignition related |  |  |  |  | LATE | Central | Non-WSIP | [6 empty] | '-122.136636 | 37.7212 | ETL.2770 | 40581580 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - Prog Multi
117491002 | DI TGR CRK-VLLEY SPRINGS 23/185 RMV NEST | 43878409 | TIGER CREEK-VALLEY SPRINGS | 023/185 | ICS | E | Pre-2020_(9a) Other ignition related |  |  |  |  | LATE | Central | WSIP | FSRP | [5 empty] | '-120.766409 | 38.2194 | ETL.5790 | 40906780 | Structure-Steel | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - 11
117491273 | EI SOBRANTE-G #1 5/40 REPAINT | 44586182 | SOBRANTE-"G" #1 | 005/040 | ICS | F | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) |  |  |  |  | Central | Non-WSIP | [6 empty] | '-122.300432 | 37.9169 | ETL.3720 | 40607984 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay
117491321 | DI NEWARK-LIVERMORE 8/51 REPAINT | 43752137 | NEWARK-LIVERMORE | 008/051 | ICS | F | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) |  |  |  |  | Central | WSIP | [6 empty] | '-121.871832 | 37.5692 | ETL.7660 | 40599751 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay
117491327 | T2 DI VALLEY SPRINGS#1 9/192 RPR STRW | 43866693 | VALLEY SPRINGS #1 | 009/192 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.883575 | 38.1194 | ETL.8210 | 40908277 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 23
117491969 | T2 PALERMO-OROVILLE #2 A6/077 REPL INSW | 31431545 | PALERMO-OROVILLE #2 | A006/077 | 93I | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-121.502618 | 39.512 | ETL.7740 | 41123111 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Table Mountain |  |  | Yes
117491970 | EI PLACER-DEL MAR 000/002 RPL POLE | 31485413 | PLACER-DEL MAR | 000/002 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | North Valley | Non-WSIP | [6 empty] | '-121.086567 | 38.9006 | ETL.7800 | 40872008 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
117492782 | T2 DI CLAY-MARTTEL 22/316 RPR STRW | 43865457 | CLAY-MARTEL | 022/316 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.847056 | 38.3496 | ETL.8250 | 40666544 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 33
117492945 | DI GLENN #2 026/486 RPR GYWW | 43939404 | GLENN #2 | 026/486 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-122.012339 | 39.5284 | ETL.6930 | 44421367 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117492956 | T3NT DI TGR CRK-VLLY SPRNGS 4/37 REPAINT | 43878409 | TIGER CREEK-VALLEY SPRINGS | 004/037 | ICS | F | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) |  |  | TR3 |  | Central | WSIP | [6 empty] | '-120.57122 | 38.4269 | ETL.5790 | 40863675 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Released
117492984 | T2NT DI TIG CRK VAL SPR 11/89 RPR FOND |  | TIGER CREEK-VALLEY SPRINGS | 011/089 | ICQ | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-120.652116 | 38.3583 | ETL.5790 | 40582765 | Foundation/Concrete-Tower | Earth Covered Tower | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Released
117493044 | T3 DI CARIBOU-PALERMO :031/256C RPR GYWS | 44304491 | CARIBOU-PALERMO | :031/256C | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.467814 | 39.7593 | ETL.3190 | 44374356 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain
117493045 | T3NT DI CRBU-PALERMO :031/256C INST MRKS |  | CARIBOU-PALERMO | :031/256C | ICW | F | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR3 |  | North Valley | WSIP |  |  |  |  | Field Operations | reprioritization of work - noncritical facility | '-121.467814 | 39.7593 | ETL.3190 | 44374356 | Marker (i.e. signs)-Wood | Missing | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117493053 | T2NT DI SPAULDING-SUMMT 17/530 INST MRKW | 43923459 | SPAULDING-SUMMIT | 017/530 | ICW | F | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.368198 | 39.3101 | ETL.8060 | 40771535 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117493378 | DI HALSEY-PLACER 004/098 RPL STRW | 31404619 | HALSEY-PLACER | 004/098 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-121.082619 | 38.9046 | ETL.6990 | 40858683 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
117493584 | DI STANISLAUS-NEWARK #1 090/599 RPR STRT |  | STANISLAUS-NEWARK #1 (12KV) | 090/599 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-121.843614 | 37.5973 | ETL.3850 | 41196133 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 5
117493731 | DI STANISLAUS-NEWARK #2 084/549 PNT STRS | 44586189 | STANISLAUS-NEWARK #2 (12KV) | 084/549 | ICS | F | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) |  |  |  |  | Central | WSIP | [6 empty] | '-121.736048 | 37.6576 | ETL.3860 | 41196037 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  | Y - Prog Multi
117493753 | T2 DI VALLEY SPRINGS #1 004/086 RPR GYWW | 43862279 | VALLEY SPRINGS #1 | 004/086 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.829894 | 38.1801 | ETL.8210 | 40903817 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 23
117493759 | T2 HUMBOLDT-TRINITY 070/002 RMV PL BUTT | 44311174 | HUMBOLDT-TRINITY | 070/002 | ICW | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-123.337232 | 40.7056 | ETL.1820 | 44562220 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2019-08-30
117493770 | T2 HUMBOLDT-TRINITY 070/004 RMV BUTT | 44311174 | HUMBOLDT-TRINITY | 070/004 | ICW | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-123.344548 | 40.7057 | ETL.1820 | 44559976 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2019-08-30
117493775 | T2 HUMBOLDT-TRINITY 070/006 RMV VEG |  | HUMBOLDT-TRINITY | 070/006 | HNA | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-123.348875 | 40.7049 | ETL.1820 | 44562315 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Eureka
117493777 | T2 HUMBOLDT-TRINITY 070/006 RMV PL BUTT | 44311174 | HUMBOLDT-TRINITY | 070/006 | ICW | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.348875 | 40.7049 | ETL.1820 | 44562315 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2019-08-30
117493870 | T2 DI PARKWAY-MORAGA 007/041 RPL HRDS | 43877573 | PARKWAY-MORAGA | 007/041 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.233527 | 38.0404 | ETL.5930 | 40811223 | Hardware-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - Prog Multi
117493874 | T2 DI PARKWAY-MORAGA 007/041 RPR SPLS | 43877573 | PARKWAY-MORAGA | 007/041 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.233527 | 38.0404 | ETL.5930 | 40811223 | Splice-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - Prog Multi
117494040 | T2 EI SPAULDING-SUMMIT 011/369 RPL POLE | 31453471 | SPAULDING-SUMMIT | 011/369 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.461854 | 39.3189 | ETL.8060 | 40594097 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
117494126 | T2 HUMBOLDT-TRINITY 71/002B COMPLETE | 44311173 | HUMBOLDT-TRINITY | 071/002B | CHS | F | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.362283 | 40.7038 | ETL.1820 | 44562953 | Road | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLR | Roads | Expense | 932 | Eureka
117494177 | T2 HUMBOLDT-TRINITY 70/5 RMV POLE BUTTS | 44311174 | HUMBOLDT-TRINITY | 070/005 | ICW | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-123.346627 | 40.7054 | ETL.1820 | 44560626 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2019-08-30
117494184 | NT DI NEWARK-VALLECITOS 91/596 PNT TWR | 44586165 | NEWARK-VALLECITOS | 091/596 | ICS | F | Pre-2020_(9a) Other ignition related | [5 empty] | Central | WSIP | [6 empty] | '-121.843542 | 37.5972 | ETL.7670 | 40825462 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  | Y - Prog Multi
117494228 | T2 HUMBOLDT-TRINITY 066/004 RMV BUTT | 44311171 | HUMBOLDT-TRINITY | 066/004 | ICW | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-123.277202 | 40.7175 | ETL.1820 | 44560480 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2019-10-04
117494231 | T2 HUMBOLDT-TRINITY 67/005 RMV BUTT | 44311171 | HUMBOLDT-TRINITY | 067/005 | ICW | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.293287 | 40.7093 | ETL.1820 | 44560642 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2019-10-04
117494273 | EI PITTSBURG-COLMBA STEEL 02/17 REPAINT | 44586174 | PITTSBURG-COLUMBIA STEEL | 002/017 | ICS | E | Pre-2020_(5b) On structure in bucket 5 | Budget Owner (Paint) |  |  |  | LATE | Central | Non-WSIP | [6 empty] | '-121.907031 | 37.9976 | ETL.3300 | 40804805 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay
117494281 | DI GREEN VALLEY-LLAGAS :009/064 RPR FOND | 44140504 | GREEN VALLEY-LLAGAS | :009/064 | ICQ | F | Pre-2020_(5) TD tag on other lines | [5 empty] | South | WSIP | [6 empty] | '-121.656829 | 37.1203 | ETL.1720 | 40761140 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Moss Landing |  | Y - 9
117494493 | EI PITTSBURG-COLUMBIA STEEL 2/16 REPAINT | 44586174 | PITTSBURG-COLUMBIA STEEL | 002/016 | ICS | F | Pre-2020_(9a) Other ignition related |  |  |  |  | LATE | Central | Non-WSIP | FSRP | [5 empty] | '-121.907 | 38.0015 | ETL.3300 | 40804817 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay
117494496 | EI PITTSBURG-COLUMBIA STL 2/16 RPL BOLT | 43877546 | PITTSBURG-COLUMBIA STEEL | 002/016 | ICS | F | Pre-2020_(9a) Other ignition related |  |  | Likely MAT error - delink to correct |  | LATE | Central | Non-WSIP | FSRP | [5 empty] | '-121.907 | 38.0015 | ETL.3300 | 40804817 | Hardware-Tower | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog Multi
117494647 | EI PITTSBURG-CLAYTON #1 2/18 REPAINT | 44586173 | PITTSBURG-CLAYTON #1 | 002/018 | ICS | E | Pre-2020_(5b) On structure in bucket 5 | Budget Owner (Paint) |  |  |  | LATE | Central | Non-WSIP | [6 empty] | '-121.907414 | 38.0018 | ETL.3280 | 40870490 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay
117494908 | T2 DI TASSAJARA-NEWARK 21/97 RPL INSS | 31484762 | TASSAJARA-NEWARK | 021/097 | 93K | E | Pre-2020_(5) TD tag on other lines |  | Need to separate out Hanger Tag |  | TR2 | LATE | Central | WSIP | [6 empty] | '-121.916547 | 37.586 | ETL.5920 | 40633240 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - Prog Multi
117495300 | DI COR #2 TAP 2/44 RMV STRS | 43901134 | CORDELIA #2 TAP | 002/044 | ICS | E | Pre-2020_(9a) Other ignition related |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-122.142331 | 38.2315 | ETL.8184 | 40825086 | Structure-Steel | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento
117495336 | DI PITTSBURG-TESLA #1 3/16 PAINT STRS | 44586176 | PITTSBURG-TESLA #1 | 003/016 | ICS | F | Pre-2020_(9a) Other ignition related | [5 empty] | Central | WSIP | [6 empty] | '-121.909028 | 37.9969 | ETL.5510 | 40819981 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay
117495421 | T2 DI SPA SUM 3/119 INST MRKW | 43923459 | SPAULDING-SUMMIT | 003/119 | ICW | F | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.592894 | 39.3128 | ETL.8060 | 40618180 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117495701 | DI TESLA-NEWARK#1 12/68 RPR FOND |  | TESLA-NEWARK #1 | 012/068 | ICQ | F | Pre-2020_(4) TD tag on high spread line | [5 empty] | Central | WSIP | [6 empty] | '-121.76556 | 37.6393 | ETL.5720 | 40862796 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog Multi
117495792 | DI LOS ESTEROS-METCALF 00/002 PAINT STRS | 43753289 | LOS ESTEROS-METCALF | 000/002 | ICS | E | Pre-2020_(9a) Other ignition related |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-121.741128 | 37.227 | ETL.5353 | 40662696 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay
117495939 | T2 DI PIT #1-COTTONWOD 39/337 RMV VEG |  | PIT #1-COTTONWOOD | 039/337 | HNA | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.060957 | 40.6449 | ETL.5390 | 40817903 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Table Mountain
117496029 | T2 DI FORT ROSS-GUALALA 30/10 REPL GRD | 43908953 | GUALALA-MONTE RIO | 030/010 | ICB | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.249438 | 38.5508 | ETL.6980 | 40587345 | Raptor Guard-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 593 | Lakeville |  |  | 2019-07-19
117496726 | EI HELMS-GREGG #2 003/030B RPR FOND | 44104288 | HELMS-GREGG #2 | 003/030B | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.015864 | 37.0132 | ETL.4880 | 40740049 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 11
117497091 | T2 HUMBOLDT-TRINITY 073/2B RMV BUTT | 44311171 | HUMBOLDT-TRINITY | 073/002B | ICW | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.395038 | 40.7056 | ETL.1820 | 40642991 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2019-10-04
117497093 | T2 HUMBOLDT-TRINITY 72/004 RPR ROAD | 44311173 | HUMBOLDT-TRINITY | 072/004 | CHS | F | Pre-2020_(3) On high spread structure | Budget Owner (Veg/Land/Road) |  |  | TR2 | LATE | North Coast | Non-WSIP |  |  |  |  | Program | 2021 - ROADS | '-123.386005 | 40.7051 | ETL.1820 | 44562210 | Road | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLR | Roads | Expense | 932 | Eureka
117497715 | T2 DI SANTA YNEZ TAP 002/022 RPR STRW | 44371037 | SANTA YNEZ TAP | 002/022 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-120.145584 | 34.6349 | ETL.3701 | 40751451 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - Prog Multi
117497952 | DI SOBRANT-STD OIL SWS#1 7/47 PAINT STRS | 44586185 | SOBRANTE-STANDARD OIL SW STA #2 | 007/047 | ICS | F | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) |  |  |  |  | Central | WSIP | [6 empty] | '-122.240676 | 37.9992 | ETL.3800 | 40804898 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay
117498003 | DI ELECTRA-BELLOTA 020/141 RPR FOND | 44460411 | ELECTRA-BELLOTA | 020/141 | ICQ | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-120.905515 | 38.1071 | ETL.4670 | 40818353 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - Prog Multi
117498005 | DI ELECTRA-BELLOTA 020/141 PAINT STRS | 43878408 | ELECTRA-BELLOTA | 020/141 | ICS | F | Pre-2020_(5b) On structure in bucket 5 | Budget Owner (Paint) |  |  |  |  | Central | WSIP | [6 empty] | '-120.905515 | 38.1071 | ETL.4670 | 40818353 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - 2
117498174 | DI PALERMO-OROVILLE #2 000/002 RPR GYWW | 43724470 | PALERMO-OROVILLE #2 | 000/002 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-121.51857 | 39.4553 | ETL.7740 | 41123114 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117498176 | DI PALERMO-OROVILL #2 0/2 INST MRKW | 43724470 | PALERMO-OROVILLE #2 | 000/002 | ICW | F | Pre-2020_(5b) On structure in bucket 5 | [5 empty] | North Valley | WSIP | [6 empty] | '-121.51857 | 39.4553 | ETL.7740 | 41123114 | Marker (i.e. signs)-Wood | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117498219 | DI NEWARK-JARVIS #1 005/037 RPR INSS | 43877252 | NEWARK-JARVIS #1 | 005/037 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-121.902169 | 37.5354 | ETL.3020 | 44361554 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - Prog Multi
117498793 | T2 DI CARIBOU-PALERMO :5/45 BURIED STUB | 44059014 | CARIBOU-PALERMO | :005/045 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.218992 | 40.0312 | ETL.3190 | 40910287 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
117498880 | T2 DI SPAULDING-SUMMIT 000/012 RPR GYWW | 43923459 | SPAULDING-SUMMIT | 000/012 | ICW | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.640116 | 39.3235 | ETL.8060 | 40660103 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117498925 | T2 EI SPAULDING-SUMMIT 011/392 INS MRKW | 43923459 | SPAULDING-SUMMIT | 011/392 | ICW | F | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.450839 | 39.3177 | ETL.8060 | 44156122 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117499113 | EI SOBRNTE-GRIZY-CLRMNT #2 02/20 REPAINT | 44586183 | SOBRANTE-GRIZLY-CLARMNT #2+ | 002/020 | ICS | E | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) |  |  |  | LATE | Central | Non-WSIP | [6 empty] | '-122.188205 | 37.882 | ETL.3750 | 40810738 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  | Y - 10
117499147 | DI ELECTRA-BELLOTA 019/139 RPL HRDS | 43865530 | ELECTRA-BELLOTA | 019/139 | ICS | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-120.902842 | 38.1102 | ETL.4670 | 40752910 | Hardware-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - Prog Multi
117499170 | T2 DI FRT RSS GUA 44/7 RPR GYWW | 43920743 | GUALALA-MONTE RIO | 044/007 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.331007 | 38.7016 | ETL.6980 | 40808302 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  | 2019-07-19
117499279 | DI SOBRANTE-GRIZ-CLARE #2 2/23 REPL INSS | 31492386 | SOBRANTE-GRIZLY-CLARMNT #2+ | 002/023 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-122.1836763 | 37.8769 | ETL.3750 | 40896427 | Insulator-Steel | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - 9
117499291 | DI ELECTRA-BELLOTA 019/139 REPAINT | 43878408 | ELECTRA-BELLOTA | 019/139 | ICS | F | Pre-2020_(5b) On structure in bucket 5 | Budget Owner (Paint) |  |  |  |  | Central | WSIP | [6 empty] | '-120.902842 | 38.1102 | ETL.4670 | 40752910 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - 2
117499550 | T3 DI CARIBOU-PALERMO :32/263 BURID STUB | 44056495 | CARIBOU-PALERMO | :032/263 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations | Circuit Based Scheduling | '-121.475573 | 39.7491 | ETL.3190 | 40656367 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
117499682 | DI MEN PHI JCT HOP 14/8 RMV VEGN |  | MENDOCINO-PHILO JCT-HOPLAND | 014/008 | HNA | E | Pre-2020_(9a) Other ignition related |  |  |  |  | LATE | North Coast | WSIP | FSRP | [5 empty] | '-123.143457 | 39.0649 | ETL.7520 | 40871979 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Lakeville
117500113 | T2 DI CARIBOU-PLUMAS JCT 14/16 RPR GYWW | 43920793 | CARIBOU-PLUMAS JCT | 014/016 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.94371 | 39.9571 | ETL.6290 | 40810060 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117500274 | T2 DI SPAULDING-SUMMIT 011/406 RPL POLE | 31453471 | SPAULDING-SUMMIT | 011/406 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.444875 | 39.3184 | ETL.8060 | 40862170 | Structure-Wood | Rotten | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
117500693 | 5 POINTS SW STA-HURON-GATES 15/1 RPLC PL | 31455753 | SCHINDLER-HURON-GATES | 015/001 | 70Y | B | 2020_(0) A and B Tags | [5 empty] | South | Non-WSIP | [6 empty] | '-120.121315 | 36.1966 | ETL.9160 | 40582725 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Fresno |  | Y - Prog Multi
117501263 | T2 EI VALLEY SPRNGS #1 A0/21A C RPR GYWW | 43878410 | VALLEY SPRINGS #1 | A000/021A | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [8 empty] | ETL.8210 | 44291411 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog Multi
117501751 | T2 DI CARIBOU#2 20/15 INST MRKW | 43854201 | CARIBOU #2 | 020/015 | ICW | F | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.021227 | 40.0301 | ETL.6280 | 40768829 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117501813 | T2NT DI SPAULDING-SUMMT 14/464 INST MRKW | 43923459 | SPAULDING-SUMMIT | 014/464 | ICW | F | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.403677 | 39.3286 | ETL.8060 | 40878098 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117501816 | T2 DI SPAULDING-SUMMT 11/397 INST MRKW | 43923459 | SPAULDING-SUMMIT | 011/397 | ICW | F | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.448486 | 39.3175 | ETL.8060 | 40876698 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117501819 | T2 DI TESLA-METCALF 32/133 RPR FOND |  | TESLA-METCALF | 032/133 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-121.726393 | 37.2656 | ETL.6110 | 40651772 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Multi Prog
117501851 | T2 DI BLACK TAP 000/002 REPAINT | 44304021 | BLACK TAP | 000/002 | ICS | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.976527 | 40.9899 | ETL.5431 | 44188818 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain
117501977 | T2 DI VALLEY SPRINGS #1 10/197 RPR GYWW | 43875774 | VALLEY SPRINGS #1 | 010/197 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.88683 | 38.1173 | ETL.8210 | 40908282 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Not Released | CalTrans
117502396 | T2 EI CARIBOU-PALERMO 15/123 RPR STRT | 44069597 | CARIBOU-PALERMO | 015/123 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.501865 | 39.6662 | ETL.3190 | 40913205 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
117502430 | T2 DI CARIBOU-PALERMO 15/123 RPL INSS |  | CARIBOU-PALERMO | 015/123 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.501865 | 39.6662 | ETL.3190 | 40913205 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain
117502488 | T2 DI MLN-RND MTN #2 68/344 INS MRKS | 43621093 | MALIN-ROUND MTN #2 | 068/344 | ICQ | F | Pre-2020_(1b) Lines with special commitments |  |  | Likely MAT error - delink to correct | TR2 | WECC | North Valley | WSIP | [6 empty] | '-121.748645 | 41.1165 | ETL.6020 | 40759865 | Marker (i.e. signs)-Steel | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117502527 | DI BEL PLA 1/16 RMV VEGN |  | BELL-PLACER | 001/016 | HNA | E | Pre-2020_(9a) Other ignition related |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-121.05913 | 38.9368 | ETL.4395 | 40577450 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  | Yes
117502947 | T2NT DI SPAULDING-SUMMT 16/512 INST MRKW | 43923459 | SPAULDING-SUMMIT | 016/512 | ICW | F | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.378387 | 39.3163 | ETL.8060 | 40878079 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117503278 | EI KONOCTI-MIDDLETOWN ;24/6 RPR GYWW | 43919877 | KONOCTI-MIDDLETOWN | ;024/006 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-122.61734 | 38.9073 | ETL.6380 | 44667817 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  | 2019-07-26
117503425 | T3NT DI ROUND MTN-TBL MT#2 4/24 REPAINT | 44586179 | ROUND MTN-TABLE MTN #2 | 004/024 | ICS | F | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.93821 | 40.7493 | ETL.6070 | 40762873 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117504021 | DI NEWARK-LAW LAB 006/042 RPL INSS | 31455147 | NEWARK-LAWRENCE LAB | 006/042 | 93K | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-121.891898 | 37.5466 | ETL.3060 | 40732589 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC hold srdy |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - Prog Multi
117504069 | DI RND MTN-COTTNWD #3 57/523 INST MRKS | 43876249 | ROUND MTN-COTTONWOOD #3 | 057/523 | ICS | F | Pre-2020_(4b) On structure in bucket 4 | [5 empty] | North Valley | WSIP | [5 empty] | reprioritization of work - noncritical facility | '-122.248626 | 40.4188 | ETL.5650 | 40657352 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117504146 | DI NEWARK-JARVIS #1 5/39 RPR GYWS | 43877252 | NEWARK-JARVIS #1 | 005/039 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-121.89713 | 37.5411 | ETL.3020 | 40857702 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - Prog Multi
117504207 | T2NT DI RND MNTN-TBL MNTN 44/197 PNT TWR | 44586179 | ROUND MTN-TABLE MTN #2 | 044/197 | ICS | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.919231 | 40.1677 | ETL.6070 | 40816753 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain
117504453 | T2NT DI RND MTN-TBL MTN 64/269 INST GMKS | 44305720 | ROUND MTN-TABLE MTN #2 | 064/269 | ICS | F | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP | [5 empty] | reprioritization of work - noncritical facility | '-121.814772 | 39.8898 | ETL.6070 | 40872477 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117504459 | T2 DI PARDSE-TBL MTN 6/55AB (L) RPR GYWW | 43724325 | PARADISE-TABLE MTN | 006/055AB | ICW | E | 2020_(1a) PSPS |  |  |  | TR2 | LATE | North Valley | WSIP | [8 empty] | ETL.4316 | 44383158 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117504551 | T2 DI PARDSE-TBL MTN 6/55AB (C) RPR GYWW | 43724325 | PARADISE-TABLE MTN | 006/055AB | ICW | E | 2020_(1a) PSPS |  |  |  | TR2 | LATE | North Valley | WSIP | [8 empty] | ETL.4316 | 44383159 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117504555 | T2 DI PARDSE-TBL MTN 6/55AB (R) RPR GYWW | 43724325 | PARADISE-TABLE MTN | 006/055AB | ICW | E | 2020_(1a) PSPS |  |  |  | TR2 | LATE | North Valley | WSIP | [8 empty] | ETL.4316 | 44383160 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117504556 | T2 DI PARDSE-TBL MTN 6/55AB (C) RPR PL | 43724325 | PARADISE-TABLE MTN | 006/055AB | ICW | E | 2020_(1a) PSPS |  |  |  | TR2 | LATE | North Valley | WSIP | [8 empty] | ETL.4316 | 44383159 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117504647 | T2 CAYUCOS-CAMBRIA 016/119 REPL INSW | 31456903 | CAYUCOS-CAMBRIA | 016/119 | 93I | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | South | Non-WSIP |  |  |  | REJECT |  |  | '-121.087555 | 35.5891 | ETL.8560 | 40846544 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Pismo Beach |  | Y - 2
117505062 | EI HELMS-GREGG #2 3/26B RPR FOND | 44104289 | HELMS-GREGG #2 | 003/026B | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.008252 | 37.0181 | ETL.4880 | 40740443 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 11
117506189 | T3 DI GRIZZLY TAP 0/13 RPR GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 000/013 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-121.284071 | 39.8978 | ETL.2395 | 44549881 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117506346 | T2 EI SPAULDING-SUMMIT 12/426 INSTL MRKW | 43923459 | SPAULDING-SUMMIT | 012/426 | ICW | F | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.43338 | 39.3245 | ETL.8060 | 40862172 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117506384 | T2 EI SPAULDING-SUMMIT 13/435 INSTL GMKW | 43923459 | SPAULDING-SUMMIT | 013/435 | ICW | F | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.426063 | 39.327 | ETL.8060 | 40771515 | Guy Wire Mark /Indic-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117506385 | T2 EI SPAULDING-SUMMIT 13/435 INSTL MRKW | 43923459 | SPAULDING-SUMMIT | 013/435 | ICW | F | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.426063 | 39.327 | ETL.8060 | 40771515 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117506410 | T3 DI GRIZZLY TAP 1/3 REM VEGN |  | TAP (CITY OF SANTA CLARA) | 001/003 | HNA | E | Pre-2020_(9a) Other ignition related |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-121.28805 | 39.8998 | ETL.2395 | 44550803 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Table Mountain
117506415 | T3 DI GRIZZLY TAP 1/3 REM VEGN |  | TAP (CITY OF SANTA CLARA) | 001/003 | HNA | E | Pre-2020_(9a) Other ignition related |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.28805 | 39.8998 | ETL.2395 | 44550737 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Table Mountain
117506473 | T2 DI RNDMTN-TBLMTN 64/270 INST GMKS | 44305720 | ROUND MTN-TABLE MTN #2 | 064/270 | ICS | F | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP | [5 empty] | reprioritization of work - noncritical facility | '-121.813862 | 39.8876 | ETL.6070 | 40596118 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117506640 | T2NT DI MALIN-RND MTN#2 69/349 INST GMKS | 44305271 | MALIN-ROUND MTN #2 | 069/349 | ICS | F | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | WECC | North Valley | WSIP | [6 empty] | '-121.762555 | 41.1055 | ETL.6020 | 40870333 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117506750 | EI HELMS-GREGG #1 000/007A INST HRDT | 43908764 | HELMS-GREGG #1 | 000/007A | ICQ | F | Pre-2020_(9a) Other ignition related |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-118.977902 | 37.0362 | ETL.4870 | 40576731 | Hardware-Tower | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 13
117506825 | EI IGNCO-ALTO-SASLTO #1 10/072 PNT STRT | 44585959 | IGNACIO-ALTO-SAUSALITO #1 | 010/072 | ICX | F | Pre-2020_(5b) On structure in bucket 5 |  |  | Likely MAT error - delink to correct |  |  | North Coast | Non-WSIP | [6 empty] | '-122.509311 | 37.926 | ETL.7160 | 40827698 | Structure-Tower | Paint/Coating | Repaint | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense |  | Lakeville
117507284 | EI PITTSBURG-COLUMBIA STL :0/1A RPR GYWS | 43886420 | PITTSBURG-COLUMBIA STEEL | :000/001A | ICS | F | Pre-2020_(5) TD tag on other lines | [5 empty] | Central | Non-WSIP | [6 empty] | '-121.872831 | 37.9873 | ETL.3300 | 40576381 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - Prog Multi
117507405 | EI PITTSBURG-CLMBIA STL :0/1A INSTL GMKS |  | PITTSBURG-COLUMBIA STEEL | :000/001A | ICS | F | Pre-2020_(5b) On structure in bucket 5 | [5 empty] | Central | Non-WSIP | [6 empty] | '-121.872831 | 37.9873 | ETL.3300 | 40576381 | Guy Wire Mark /Indic-Steel | Missing | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - Prog Multi | 2019-07-31
117507407 | EI PTSBRG-CLMBA STL :0/1A INSTL CLMB GRD | 31494704 | PITTSBURG-COLUMBIA STEEL | :000/001A | 93A | F | Pre-2020_(5b) On structure in bucket 5 | [5 empty] | Central | Non-WSIP | [6 empty] | '-121.872831 | 37.9873 | ETL.3300 | 40576381 | Structure-Tower | Anti-Climbing Guard | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Capital | 988 | Bay |  | Y - Prog Multi
117544824 | T3 DI GRIZZLY TAP 1/6L RPR PL | 43760153 | TAP (CITY OF SANTA CLARA) | 001/006 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.290928 | 39.8991 | ETL.2395 | 44550759 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117544969 | T2 DI MTN GT JCT CAS 3/29 RPR STRW (R) | 43758388 | MTN GATE JCT-CASCADE | 003/029 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.321993 | 40.7034 | ETL.7640 | 44565378 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117545071 | T2 DI MTN GT JCT CAS 3/29 RPR STRW (L) | 43758388 | MTN GATE JCT-CASCADE | 003/029 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.321993 | 40.7034 | ETL.7640 | 44565552 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117545075 | T2 DI MT GT JCT CAS 3/29 INST MRKW (R) | 43758388 | MTN GATE JCT-CASCADE | 003/029 | ICW | F | Pre-2020_(5b) On structure in bucket 5 | [5 empty] | North Valley | WSIP | [5 empty] | reprioritization of work - noncritical facility | '-122.321993 | 40.7034 | ETL.7640 | 44565378 | Marker (i.e. signs)-Wood | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117545076 | T2 DI MT GT JCT CAS 3/29 INST MRKW (L) | 43758388 | MTN GATE JCT-CASCADE | 003/029 | ICW | F | Pre-2020_(5b) On structure in bucket 5 | [5 empty] | North Valley | WSIP | [5 empty] | reprioritization of work - noncritical facility | '-122.321993 | 40.7034 | ETL.7640 | 44565552 | Marker (i.e. signs)-Wood | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117545138 | DI NEWARK-JARVIS #1 5/35 RMV NEST | 43877252 | NEWARK-JARVIS #1 | 005/035 | ICS | E | Pre-2020_(9a) Other ignition related |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-121.906426 | 37.5321 | ETL.3020 | 40745974 | Structure-Steel | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay
117545273 | T2 HUMBOLDT-TRINITY 073/003 RMV BUTT | 44311171 | HUMBOLDT-TRINITY | 073/003 | ICW | F | Pre-2020_(9a) Other ignition related |  |  |  |  | LATE | North Coast | Non-WSIP | [6 empty] | '-123.399021 | 40.7035 | ETL.1820 | 44562968 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2019-10-04
117545278 | T2 HUMBOLDT-TRINITY 62/0 RMV BUTT | 44298745 | HUMBOLDT-TRINITY | 062/000 | ICW | F | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.196663 | 40.7375 | ETL.1820 | 44560488 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
117545351 | DI PLACER-DEL MAR 000/003 RPR PL | 43912223 | PLACER-DEL MAR | 000/003 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-121.087149 | 38.9 | ETL.7800 | 40867079 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117545463 | T2 DI HEL GREG #2 9/70B RMV NEST | 43825465 | HELMS-GREGG #2 | 009/070B | ICS | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | South | WSIP | FSRP | [5 empty] | '-119.111955 | 36.9887 | ETL.4880 | 40740538 | Structure-Steel | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  | Y - 11
117545492 | T3 DI GRIZZLY TAP 0/6 INST HRDW | 43760153 | TAP (CITY OF SANTA CLARA) | 000/006 | ICW | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.278706 | 39.8937 | ETL.2395 | 44549956 | Hardware-Wood | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117545516 | EI BRDGVLLE-CTTNWOOD 000/003 REMV VEGN |  | BRIDGEVILLE-COTTONWOOD | 000/003 | HNA | E | Pre-2020_(9a) Other ignition related | Budget Owner (Veg/Land/Road) |  |  |  | LATE | North Valley | Non-WSIP | [8 empty] | ETL.1110 | 44423422 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Table Mountain
117545578 | T3NT DI GRIZZLY TAP 0/8 INST MRKW |  | TAP (CITY OF SANTA CLARA) | 000/008 | ICW | F | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.278691 | 39.8949 | ETL.2395 | 44550034 | Marker (i.e. signs)-Wood | Missing | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117545714 | T3 DI GRIZZLY TAP 003/001 RPR GYWW | 43760153 | TAP (CITY OF SANTA CLARA) | 003/001 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-121.320267 | 39.8983 | ETL.2395 | 44551382 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117545838 | T2NT DI STNSLS-MNTCA #2 018/105 REPAINT | 43878405 | STANISLAUS-MANTECA #2 | 018/105 | ICS | F | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) |  |  | TR2 |  | Central | WSIP | [6 empty] | '-120.637983 | 37.9901 | ETL.3820 | 40744467 | Structure-Steel | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - Prog Multi
117545955 | T3 DI GRIZ TAP 3/4R RMV DEBRIS | 43760153 | TAP (CITY OF SANTA CLARA) | 003/004 | ICW | F | Pre-2020_(9a) Other ignition related |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-121.320922 | 39.901 | ETL.2395 | 44551436 | Structure-Wood | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117545958 | T3 DI GRIZ TAP 3/4 RMV DEBRIS | 43760153 | TAP (CITY OF SANTA CLARA) | 003/004 | ICW | F | Pre-2020_(9a) Other ignition related |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-121.320922 | 39.901 | ETL.2395 | 44551415 | Structure-Wood | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117546891 | T2 DI CARIBOU #2 017/028 RPR GYWW | 43742132 | CARIBOU #2 | 017/028 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.061832 | 40.0205 | ETL.6280 | 40862055 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117547473 | T2 DI PALERMO-COLGATE C001/7 INST MRKS | 43900095 | PALERMO-COLGATE | C001/007 | ICS | F | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.216462 | 39.3219 | ETL.5360 | 40814791 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes
117547621 | T2 DI CARIBOU #2 024/628 INS MRKS | 43854201 | CARIBOU #2 | 024/628 | ICW | F | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | SCHD | North Valley | WSIP | [5 empty] | reprioritization of work - noncritical facility | '-120.965067 | 40.0393 | ETL.6280 | 44259148 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117548712 | EI IGNACIO-ALTO 000/001 INS MRKW |  | IGNACIO-ALTO | 000/001 | ICW | F | Pre-2020_(5b) On structure in bucket 5 | [5 empty] | North Coast | Non-WSIP | [6 empty] | '-122.540334 | 38.0755 | ETL.7150 | 44574866 | Marker (i.e. signs)-Wood | Missing | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
117548732 | EI IGNACIO-ALTO 000/001 RPR GYWW | 43920745 | IGNACIO-ALTO | 000/001 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | North Coast | Non-WSIP | [6 empty] | '-122.540334 | 38.0755 | ETL.7150 | 44574866 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
117552999 | T2 DI MI-WUK-CURTIS 23/01 CANCEL |  | ETL.1073.POLE.WDPS | 023/001 | ICW | F | Pre-2020_(4b) On structure in bucket 4 |  |  | CANCEL/CNCL | TR2 |  | Central | WSIP | [6 empty] | '-120.26918 | 38.0053 | ETL.1073 | 44774785 | Marker (i.e. signs)-Wood | Missing | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog Multi
117554026 | T2 DI DRM-GRSS VLLY-WMR B16/380 REPL PL | 31500646 | DRUM-GRASS VALLEY-WEIMAR | B016/380 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP |  |  | REJECT: Could not complete work due to a clearance, materials or access issue. |  |  | '-120.962544 | 39.1283 | ETL.6760 | 40590232 | Structure-Wood | No Good/Out of Stdrd | Replace | DOCC | DOCC | Job has been constructed (documentation) | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
117554128 | T2 DI RND MTN-TBL MTN 74/305 INST GMKS | 44305720 | ROUND MTN-TABLE MTN #2 | 074/305 | ICS | F | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP | [5 empty] | reprioritization of work - noncritical facility | '-121.74984 | 39.7443 | ETL.6070 | 40765376 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117554303 | T2 DI VALLEY SPRNGS #1 A001/033 RPR POLE | 43878410 | VALLEY SPRINGS #1 | A001/033 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.73895 | 38.2044 | ETL.8210 | 40907090 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog Multi
117554305 | T2NT DI VLLY SPRNGS#1 A001/033 INST MRKW | 43878410 | VALLEY SPRINGS #1 | A001/033 | ICW | F | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-120.73895 | 38.2044 | ETL.8210 | 40907090 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog Multi
117554352 | T2 DI MALIN-RND MTN #2 078/398 INS GMKS | 43621093 | MALIN-ROUND MTN #2 | 078/398 | ICQ | F | Pre-2020_(1b) Lines with special commitments |  |  | Likely MAT error - delink to correct | TR2 | WECC | North Valley | WSIP | [6 empty] | '-121.890488 | 41.0279 | ETL.6020 | 40868976 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117554417 | EI CLEAR LAKE-HOPLAND 02/009 RPR GYWW | 43919879 | CLEAR LAKE-HOPLAND | 002/009 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | North Coast | Non-WSIP | FSRP | [7 empty] | ETL.6390 | 44224595 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  | 2019-08-06
117554425 | T2 DI DRUM-SUMMIT #2 27/326A CANCEL | 43947611 | DRUM-SUMMIT #2 | 027/326A | ICW | E | Pre-2020_(1b) Lines with special commitments |  |  | CANCEL/CNCL | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.33228 | 39.3122 | ETL.1450 | 40752050 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117554461 | T2 DI RND MTN CTTNWD #3 52/466 INST MRKS | 43876249 | ROUND MTN-COTTONWOOD #3 | 052/466 | ICS | F | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP | [5 empty] | reprioritization of work - noncritical facility | '-122.193865 | 40.4851 | ETL.5650 | 40817527 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117554663 | T2 DI DRUM-SUMMIT #2 27/326C RPR GYWW | 43947611 | DRUM-SUMMIT #2 | 027/326C | ICW | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.332213 | 39.3121 | ETL.1450 | 42572857 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117555078 | T2 DI CNTERVILLE-TBL MTN 4/76 REPR SPLW | 43939207 | CENTERVILLE-TABLE MTN | 004/076 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.705945 | 39.7319 | ETL.6320 | 44384785 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117555081 | T2 DI RND MTN-CTNWD #3 R001/15L RPR STRW | 43946912 | ROUND MTN-COTTONWOOD #3 | R001/015 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.935829 | 40.7997 | ETL.5650 | 44737543 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117555082 | T2 DI RND MTN-CTWD #3 R001/15R RPR STRW | 43946912 | ROUND MTN-COTTONWOOD #3 | R001/015 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.935829 | 40.7997 | ETL.5650 | 44737544 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117555085 | T2 DI RND MTN-CTWD #3 R001/015 INS MRKW | 43755804 | ROUND MTN-COTTONWOOD #3 | R001/015 | ICW | F | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP | [5 empty] | reprioritization of work - noncritical facility | '-121.935829 | 40.7997 | ETL.5650 | 44737544 | Marker (i.e. signs)-Wood | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117555692 | T2NT DI MLN-RND MTN #2 064/320 INST GMKS | 43621093 | MALIN-ROUND MTN #2 | 064/320 | ICQ | F | Pre-2020_(1b) Lines with special commitments |  |  | Likely MAT error - delink to correct | TR2 | WECC | North Valley | WSIP | [6 empty] | '-121.694345 | 41.1595 | ETL.6020 | 40601164 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117555697 | T2NT DI MLN-RND MTN #2 062/312 INS GMKS | 44305271 | MALIN-ROUND MTN #2 | 062/312 | ICS | F | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | WECC | North Valley | WSIP | [6 empty] | '-121.676937 | 41.1784 | ETL.6020 | 40660983 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117555751 | T2 DI FORT ROSS-GUALALA 058/000 RPR GYWW | 43920743 | GUALALA-MONTE RIO | 058/000 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.514432 | 38.7749 | ETL.6980 | 40606947 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  | 2019-07-19
117556001 | T2NT DI DRUM-SUMMIT #2 026/317 INS GMKW | 43947608 | DRUM-SUMMIT #2 | 026/317 | ICW | F | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.345206 | 39.3088 | ETL.1450 | 44557479 | Guy Wire Mark /Indic-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117556002 | T2NT DI DRUM-SUMMIT #2 026/317 INS GMKW | 43947608 | DRUM-SUMMIT #2 | 026/317 | ICW | F | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.345206 | 39.3088 | ETL.1450 | 44557784 | Guy Wire Mark /Indic-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117556003 | T2NT DI DRUM-SUMMIT #2 026/317 INS GMKW | 43947608 | DRUM-SUMMIT #2 | 026/317 | ICW | F | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.345206 | 39.3088 | ETL.1450 | 44557646 | Guy Wire Mark /Indic-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117556006 | T2NT DI DRUM-SUMMIT #1 024/290C INS GMKW | 43910101 | DRUM-SUMMIT #1 | 024/290C | ICW | F | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.370392 | 39.3104 | ETL.1440 | 42572726 | Guy Wire Mark /Indic-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117556007 | T2NT DI DRUM-SUMMIT #1 024/290C INS MRKW | 43910101 | DRUM-SUMMIT #1 | 024/290C | ICW | F | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.370392 | 39.3104 | ETL.1440 | 42572726 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117556548 | T2NT DI DRM-SUMMIT #1 023/274B INST GMKW | 43910102 | DRUM-SUMMIT #1 | 023/274B | ICW | F | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.394185 | 39.3112 | ETL.1440 | 42572723 | Guy Wire Mark /Indic-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117556831 | T2 DI CARIBOU-PALERMO :15/122 REPR STUBS | 44069583 | CARIBOU-PALERMO | :015/122 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.308374 | 39.9421 | ETL.3190 | 40738347 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
117558205 | T2 DI TULE-SPRINGVILLE 13/16 RPR GYWW | 44323707 | TULE-SPRINGVILLE | 013/016 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-118.899482 | 36.1099 | ETL.9040 | 40823413 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Midway |  | Y - 23
117558329 | T2 DI BCKS CK-RCK CRK-CRST 2/25 PNT STRS | 43897313 | BUCKS CREEK-ROCK CREEK-CRESTA | 002/025 | ICS | F | Pre-2020_(3) On high spread structure | Budget Owner (Paint) |  |  | TR2 |  | North Valley | WSIP |  |  |  |  | Program | 2021 Paint took out of program due to future project to be removed with S6B7 | '-121.37416 | 39.8811 | ETL.4430 | 40758269 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Table Mountain |  |  | Yes
117559046 | T2 DI CSCDE-BNTN-DSCHTS 4/90 RPR GYWS | 44370533 | CASCADE-BENTON-DESCHUTES | 004/090 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.310589 | 40.5951 | ETL.6310 | 40817322 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117559050 | EI NT IGNCI-ALT-SSLT #1 000/007 CANCEL | 44310665 | IGNACIO-ALTO-SAUSALITO #1 | 000/007 | ICS | F | Pre-2020_(9a) Other ignition related |  |  | CANCEL/CNCL |  |  | North Coast | Non-WSIP | [6 empty] | '-122.535807 | 38.0749 | ETL.7160 | 40701499 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville
117559505 | EI NT IGNC-ALT-SSLT #1 000/06 STRT PAINT | 44310665 | IGNACIO-ALTO-SAUSALITO #1 | 000/006 | ICS | F | Pre-2020_(9a) Other ignition related | [5 empty] | North Coast | Non-WSIP | [6 empty] | '-122.537918 | 38.0762 | ETL.7160 | 40588462 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville
117559986 | EI STNISLAUS-NWARK #2 84/548 PAINT STRT | 44586189 | STANISLAUS-NEWARK #2 (12KV) | 084/548 | ICS | F | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) |  |  |  |  | Central | Non-WSIP | [6 empty] | '-121.733988 | 37.6581 | ETL.3860 | 41196036 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay
117560068 | DI ELECTRA-BELLOTA 20/140 RPR FOND | 44460410 | ELECTRA-BELLOTA | 020/140 | ICQ | F | Pre-2020_(5) TD tag on other lines | [5 empty] | Central | WSIP | [6 empty] | '-120.904178 | 38.1087 | ETL.4670 | 40819257 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - Prog Multi
117560134 | T2 DI TEJON-LEBEC 011/184 RMV VEGN |  | TEJON-LEBEC | 011/184 | HNA | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | South | WSIP | FSRP | [5 empty] | '-118.895745 | 34.8765 | ETL.9250 | 40662630 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Midway
117560177 | T2 MORRO BAY-SLO#2 3/020 RPR INSS |  | MORRO BAY-SAN LUIS OBISPO #2 | 003/020 | ICS | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.806646 | 35.3537 | ETL.2820 | 40638126 | Insulator-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Pismo Beach
117560197 | EI STNISLUS-NEWARK #2 84/549 RPL HRDT |  | STANISLAUS-NEWARK #2 (12KV) | 084/549 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | Central | Non-WSIP | [6 empty] | '-121.736048 | 37.6576 | ETL.3860 | 41196037 | Hardware-Tower | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog Multi
117560210 | EI STNISLUS-NEWARK #2 84/549 RPR STRT |  | STANISLAUS-NEWARK #2 (12KV) | 084/549 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | Central | Non-WSIP | [6 empty] | '-121.736048 | 37.6576 | ETL.3860 | 41196037 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 2
117560377 | EI STANISLAUS-NEWARK #1 83/5 INS ANTCLMB | 31493857 | STANISLAUS-NEWARK #1 (12KV) | 083/551 | 93A | F | Pre-2020_(4b) On structure in bucket 4 | [5 empty] | Central | Non-WSIP | [6 empty] | '-121.736104 | 37.6577 | ETL.3850 | 41196040 | Structure-Tower | Anti-Climbing Guard | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Capital | 988 | Bay |  | Y - Prog Multi
117560379 | EI STANISLAUS-NEWARK #1 83/5 PAINT STRT |  | STANISLAUS-NEWARK #1 (12KV) | 083/551 |  | F | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) |  |  |  |  | Central | Non-WSIP | [6 empty] | '-121.736104 | 37.6577 | ETL.3850 | 41196040 | Structure-Tower | Paint/Coating | Repaint |  |  |  |  | PEND | LC | TLQ | Tower | Expense |  | Bay
117560424 | EI STANISLAUS-NEWARK #1 83/5 RPL HRDT |  | STANISLAUS-NEWARK #1 (12KV) | 083/551 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | Central | Non-WSIP | [6 empty] | '-121.736104 | 37.6577 | ETL.3850 | 41196040 | Hardware-Tower | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog Multi
117560599 | EI STNISLUS-NWARK #2 84/550 PAINT STRT | 44586189 | STANISLAUS-NEWARK #2 (12KV) | 084/550 | ICS | F | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) |  |  |  |  | Central | Non-WSIP | [6 empty] | '-121.737918 | 37.657 | ETL.3860 | 41196038 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay
117560691 | EI STNISLUS-NWARK #2 84/550 RPL HRDT |  | STANISLAUS-NEWARK #2 (12KV) | 084/550 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | Central | Non-WSIP | [6 empty] | '-121.737918 | 37.657 | ETL.3860 | 41196038 | Hardware-Tower | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog Multi
117560696 | EI STNISLUS-NWARK #2 84/550 RPL BENT MEM |  | STANISLAUS-NEWARK #2 (12KV) | 084/550 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | Central | Non-WSIP | [6 empty] | '-121.737918 | 37.657 | ETL.3860 | 41196038 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog Multi
117560818 | EI STANISLAUS-NWRK #1 83/552 INS ANTCLMB | 31493857 | STANISLAUS-NEWARK #1 (12KV) | 083/552 | 93A | F | Pre-2020_(4b) On structure in bucket 4 | [5 empty] | Central | Non-WSIP | [6 empty] | '-121.73798 | 37.6571 | ETL.3850 | 41196042 | Structure-Tower | Anti-Climbing Guard | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Capital | 988 | Bay |  | Y - Prog Multi
117560819 | EI STANISLAUS-NEWARK #1 83/552 RPL HRDT |  | STANISLAUS-NEWARK #1 (12KV) | 083/552 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | Central | Non-WSIP | [6 empty] | '-121.73798 | 37.6571 | ETL.3850 | 41196042 | Hardware-Tower | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog Multi
117560872 | T2 MRR-BY SN LUS OBSP #2 05/029 RPL INSS | 31457244 | MORRO BAY-SAN LUIS OBISPO #2 | 005/029 | 93K | F | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.783413 | 35.3365 | ETL.2820 | 40884613 | Insulator-Steel | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach
117560931 | EI STANISLAUS-NWRK #2 84/551 PAINT STRT | 44586189 | STANISLAUS-NEWARK #2 (12KV) | 084/551 | ICS | F | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) |  |  |  |  | Central | Non-WSIP | [6 empty] | '-121.739423 | 37.6562 | ETL.3860 | 41196039 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay
117560936 | EI STANISLUS-NWRK #2 84/551 RPL BENT MEM |  | STANISLAUS-NEWARK #2 (12KV) | 084/551 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | Central | Non-WSIP | [6 empty] | '-121.739423 | 37.6562 | ETL.3860 | 41196039 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog Multi
117560989 | EI STANISLAUS-NWRK #2 84/551 RPL HRDT |  | STANISLAUS-NEWARK #2 (12KV) | 084/551 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | Central | Non-WSIP | [6 empty] | '-121.739423 | 37.6562 | ETL.3860 | 41196039 | Hardware-Tower | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog Multi
117561078 | T2 MORRO BAY-SLO #2 5/31 REPL INSS | 31457244 | MORRO BAY-SAN LUIS OBISPO #2 | 005/031 | 93K | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.777633 | 35.3322 | ETL.2820 | 40611534 | Insulator-Steel | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach
117561102 | EI STANISLAUS-NEWARK #1 83/552 STR PAINT | 44586188 | STANISLAUS-NEWARK #1 (12KV) | 083/552 | ICS | F | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) |  |  |  |  | Central | Non-WSIP | [6 empty] | '-121.73798 | 37.6571 | ETL.3850 | 41196042 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay
117561106 | EI STANISLAUS-NEWARK #1 83/553 RPL HRDT | 43877551 | STANISLAUS-NEWARK #1 (12KV) | 083/553 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | Central | Non-WSIP | [6 empty] | '-121.739502 | 37.6564 | ETL.3850 | 41196044 | Hardware-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  | Y - Prog Multi
117561109 | EI STANISLAUS-NEWARK #1 83/553 STR PAINT | 44586188 | STANISLAUS-NEWARK #1 (12KV) | 083/553 | ICS | F | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) |  |  |  |  | Central | Non-WSIP | [6 empty] | '-121.739502 | 37.6564 | ETL.3850 | 41196044 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay
117561114 | EI STANISLAUS-NWRK #1 83/553 INS ANTCLMB | 31493857 | STANISLAUS-NEWARK #1 (12KV) | 083/553 | 93A | F | Pre-2020_(4b) On structure in bucket 4 | [5 empty] | Central | Non-WSIP | [6 empty] | '-121.739502 | 37.6564 | ETL.3850 | 41196044 | GO95 / Anti Climb | Ground / Clearance | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Capital | 988 | Bay |  | Y - Prog Multi
117561183 | T2 MRR BY-SN LUIS OBSP #2 06/34 RPL HRDS |  | MORRO BAY-SAN LUIS OBISPO #2 | 006/034 | ICS | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.770526 | 35.327 | ETL.2820 | 40781930 | Hardware-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Pismo Beach
117561249 | T2NT DI RD MT COT #3 R1/18 INST MRKW (R) | 43755804 | ROUND MTN-COTTONWOOD #3 | R001/018 | ICW | F | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP | [5 empty] | reprioritization of work - noncritical facility | '-121.936725 | 40.7957 | ETL.5650 | 44737546 | Marker (i.e. signs)-Wood | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117562157 | T3NT EI GYSRS #16 TAP 000/003 PAINT STRT | 44310547 | GEYSERS #16 TAP | 000/003 | ICS | F | Pre-2020_(9a) Other ignition related |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.715252 | 38.7649 | ETL.4760 | 40659179 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville |  |  | 2019-07-19
117562799 | EI STNSLAUS-NEWRK #2 084/552 PAINT TOWER | 44586189 | STANISLAUS-NEWARK #2 (12KV) | 084/552 | ICS | F | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) |  |  |  |  | Central | Non-WSIP | [6 empty] | '-121.741173 | 37.6554 | ETL.3860 | 41196041 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay
117562852 | EI STANISLAUS-NEWARK #2 084/552 RPL HRDT |  | STANISLAUS-NEWARK #2 (12KV) | 084/552 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | Central | Non-WSIP | [6 empty] | '-121.741173 | 37.6554 | ETL.3860 | 41196041 | Hardware-Tower | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog Multi
117562857 | EI STANSLUS-NEWARK #1 83/554 PAINT TOWER | 44586188 | STANISLAUS-NEWARK #1 (12KV) | 083/554 | ICS | F | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) |  |  |  |  | Central | Non-WSIP | [6 empty] | '-121.741256 | 37.6555 | ETL.3850 | 41196046 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay
117562862 | EI STANISLUS-NEWARK #1 83/554 ANTI-CLIMB | 31493857 | STANISLAUS-NEWARK #1 (12KV) | 083/554 | 93A | F | Pre-2020_(4b) On structure in bucket 4 | [5 empty] | Central | Non-WSIP | [6 empty] | '-121.741256 | 37.6555 | ETL.3850 | 41196046 | Structure-Tower | Anti-Climbing Guard | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Capital | 988 | Bay |  | Y - Prog Multi
117562865 | EI STANISLAUS-NEWARK #1 83/554 RPL HRDT |  | STANISLAUS-NEWARK #1 (12KV) | 083/554 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | Central | Non-WSIP | [6 empty] | '-121.741256 | 37.6555 | ETL.3850 | 41196046 | Hardware-Tower | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog Multi
117562934 | EI STANISLAUS-NEWARK #2 084/552 RPR STRT |  | STANISLAUS-NEWARK #2 (12KV) | 084/552 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | Central | Non-WSIP | [6 empty] | '-121.741173 | 37.6554 | ETL.3860 | 41196041 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 2
117562936 | NT EI STANISLAUS-NWK #2 85/554 PNT TWR | 44586189 | STANISLAUS-NEWARK #2 (12KV) | 085/554 | ICS | F | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) |  |  |  |  | Central | WSIP | [6 empty] | '-121.746183 | 37.6529 | ETL.3860 | 41196045 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  | Y - Prog Multi
117562938 | NT EI STANISLAUS-NWK #2 85/554 INST ACG |  | STANISLAUS-NEWARK #2 (12KV) | 085/554 | 93A | F | Pre-2020_(4b) On structure in bucket 4 | [5 empty] | Central | WSIP | [6 empty] | '-121.746183 | 37.6529 | ETL.3860 | 41196045 | Structure-Tower | Anti-Climbing Guard | Install |  |  |  |  | PEND | LC | TLQ | Tower | Capital | 988 | Bay |  | Y - Prog Multi
117562951 | EI STANISLAUS-NWK #2 85/554 RPL HRDT |  | STANISLAUS-NEWARK #2 (12KV) | 085/554 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | Central | Non-WSIP | [6 empty] | '-121.746183 | 37.6529 | ETL.3860 | 41196045 | Hardware-Tower | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog Multi
117562954 | EI STANISLAUS-NEWARK #1 84/556 RPR FOND |  | STANISLAUS-NEWARK #1 (12KV) | 084/556 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  |  | LATE | Central | Non-WSIP | [6 empty] | '-121.746267 | 37.653 | ETL.3850 | 41195974 | Foundation/Concrete-Tower | Earth Covered Tower | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog Multi
117562956 | EI STANISLAUS-NEWARK #1 84/556 CLMB GRD | 31493857 | STANISLAUS-NEWARK #1 (12KV) | 084/556 | 93A | F | Pre-2020_(4b) On structure in bucket 4 | [5 empty] | Central | Non-WSIP | [6 empty] | '-121.746267 | 37.653 | ETL.3850 | 41195974 | Structure-Tower | Anti-Climbing Guard | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Capital | 988 | Bay |  | Y - Prog Multi
117563001 | EI STANISLAUS-NEWARK #2 85/555 RPR STRT |  | STANISLAUS-NEWARK #2 (12KV) | 085/555 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | Central | Non-WSIP | [6 empty] | '-121.748168 | 37.6519 | ETL.3860 | 41195973 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 2
117563007 | EI STANISLAUS-NEWARK #2 85/556 RPR FOND |  | STANISLAUS-NEWARK #2 (12KV) | 085/556 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  |  | LATE | Central | Non-WSIP | [6 empty] | '-121.749562 | 37.6511 | ETL.3860 | 41195975 | Foundation/Concrete-Tower | Earth Covered Tower | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog Multi
117563032 | EI STANISLAUS-NEWARK #1 84/558 CLMB GRD | 31493857 | STANISLAUS-NEWARK #1 (12KV) | 084/558 | 93A | F | Pre-2020_(4b) On structure in bucket 4 | [5 empty] | Central | Non-WSIP | [6 empty] | '-121.749736 | 37.6512 | ETL.3850 | 41195978 | Structure-Tower | Anti-Climbing Guard | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Capital | 988 | Bay |  | Y - Prog Multi
117563784 | T2 TRINITY-MAPLE CREEK 15/2 RPL POLE | 31490924 | TRINITY-MAPLE CREEK | 015/002 | 70Y | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.177053 | 40.7465 | ETL.8170 | 40660828 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2019-11-14
117563785 | T2 TRINITY-MAPLE CREEK 15/001 RPL POLE | 31490924 | TRINITY-MAPLE CREEK | 015/001 | 70Y | E | 2020_(2) High fire spread TD |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.176107 | 40.7469 | ETL.8170 | 40579624 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2019-11-14
117563802 | T2 TRINITY-MAPLE CREEK 14/9 RPL POLE | 31490924 | TRINITY-MAPLE CREEK | 014/009 | 70Y | F | 2020_(2) High fire spread TD |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.172152 | 40.7486 | ETL.8170 | 40862185 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2019-11-14
117564607 | EI JEFFERSON-HILLSDALE JCT 00/0 RPL POLE | 31456783 | JEFFERSON-HILLSDALE JCT | 000/000 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | Central | Non-WSIP | [6 empty] | '-122.285275 | 37.4559 | ETL.7190 | 40594770 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Bay |  | Y - 5 | SMCPD
117565276 | T2 HUMBOLDT-TRINITY 59/3 RMV BUTT | 44311171 | HUMBOLDT-TRINITY | 059/003 | ICW | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.160155 | 40.7536 | ETL.1820 | 44562699 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2019-10-04
117565321 | T2 HUMBOLDT-TRINITY 91/0 RMV BUTT | 44311171 | HUMBOLDT-TRINITY | 091/000 | ICW | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-123.699446 | 40.746 | ETL.1820 | 44562981 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
117565323 | T2 HUMBOLDT-TRINITY 091/003 RMV BUTT | 44311171 | HUMBOLDT-TRINITY | 091/003 | ICW | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-123.705149 | 40.7479 | ETL.1820 | 44565445 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
117565324 | T2 HUMBOLDT-TRINITY 091/004 REPL ANCW | 31472098 | HUMBOLDT-TRINITY | 091/004 | 93E | E | Pre-2020_(2) High fire spread TD |  |  |  | TR2 | LATE | North Coast | Non-WSIP |  |  |  |  | Project | 2021 HUMBOLDT-TRINITY | '-123.70711 | 40.7485 | ETL.1820 | 44560505 | Anchor-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Eureka
117565332 | T2 HUMBOLDT-TRINITY 090/010 RMV BUTT | 44311171 | HUMBOLDT-TRINITY | 090/010 | ICW | F | Pre-2020_(9a) Other ignition related |  |  |  |  | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-123.697578 | 40.7453 | ETL.1820 | 44395233 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
117566100 | EI MONTA VISTA-PERMANENTE 0/9 RPL CRSW | 31457590 | MONTA VISTA-PERMANENTE | 000/009 | 93E | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | Central | Non-WSIP | [6 empty] | '-122.086618 | 37.3148 | ETL.7620 | 40612246 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Bay
117567103 | T3 DI GRIZZLY TAP 0/10 RPR GYWW (L) |  | TAP (CITY OF SANTA CLARA) | 000/010 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.294599 | 39.8956 | ETL.2395 | 44550777 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117567104 | T3 DI GRIZZLY TAP 000/010 RPR GYWW (C) |  | TAP (CITY OF SANTA CLARA) | 000/010 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.294599 | 39.8956 | ETL.2395 | 44550761 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117567105 | T3 DI GRIZZLY TAP 000/010 RPR GYWW (R) |  | TAP (CITY OF SANTA CLARA) | 000/010 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.294599 | 39.8956 | ETL.2395 | 44550760 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117567137 | T2 DI SPA SUM 0/2 RPR GYWW | 43923459 | SPAULDING-SUMMIT | 000/002 | ICW | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.644199 | 39.3246 | ETL.8060 | 40660099 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117567655 | T3 DI GRI TAO 0/11 RPR GYWW (L) |  | TAP (CITY OF SANTA CLARA) | 000/011 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.279468 | 39.8976 | ETL.2395 | 44549959 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117567657 | T3 DI GRI TAO 0/11 RPR GYWW (C) |  | TAP (CITY OF SANTA CLARA) | 000/011 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.279468 | 39.8976 | ETL.2395 | 44550035 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117567783 | HAMMER-COUNTRY CLUB 02/56 RPL GYWW | 43878418 | HAMMER-COUNTRY CLUB (NO FLY) | 002/056 | ICW | B | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) |  |  |  |  | LATE | Central | Non-WSIP | FSRP | [5 empty] | '-121.290704 | 38.0025 | ETL.7010 | 40613620 | Guy Wire-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Released
117567795 | MONTA VISTA-LOS GATOS 010/201 TRM VEGN |  | MONTA VISTA-LOS GATOS | 010/201 | HNA | E | Pre-2020_(5b) On structure in bucket 5 | Budget Owner (Veg/Land/Road) |  |  |  | LATE | Central | Non-WSIP | [5 empty] | [REDACTED] - Need for Hwy 9 permit; inquiry w/ Cal Trans District 4 on 6/11/20; [REDACTED] - applying for Cal Trans District 4 scenic highway permit; eta 8/15/2020 | '-121.977472 | 37.2276 | ETL.7610 | 40694893 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Bay
117567955 | T2 DI COLGATE-PALERMO 009/167 RPL STRW | 31457073 | COLGATE-PALERMO | 009/167 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.336983 | 39.3546 | ETL.6500 | 40598473 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
117567968 | T2 EI SPAULDING-SUMMIT 014/464 REFRAME | 43923459 | SPAULDING-SUMMIT | 014/464 | ICW | E | Pre-2020_(1b) Lines with special commitments |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.403677 | 39.3286 | ETL.8060 | 40878098 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117567991 | T2 EI DRUM-SUMMIT #2 21/260 RPL POLE | 31471241 | DRUM-SUMMIT #2 | 021/260 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.4168094 | 39.3283 | ETL.1450 | 44558923 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Sacramento |  |  | Yes
117568219 | T2 DI RD MT CTNWD #3 R1/18 RPR STRW (R) | 43946912 | ROUND MTN-COTTONWOOD #3 | R001/018 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.936725 | 40.7957 | ETL.5650 | 44737546 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117568370 | T2 DI RDMT CTNWD #3 R1/18 RPR STRW (L) | 43946912 | ROUND MTN-COTTONWOOD #3 | R001/018 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.936725 | 40.7957 | ETL.5650 | 44737545 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117568443 | T2 DI MT GT JCT CAS 3/36 RPR STRW (R) | 43758388 | MTN GATE JCT-CASCADE | 003/036 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.324986 | 40.6935 | ETL.7640 | 44565398 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117568461 | T2 EI SPAULDING-SUMMIT 014/459 RPR STRW | 43923459 | SPAULDING-SUMMIT | 014/459 | ICW | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.407944 | 39.3284 | ETL.8060 | 40650061 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117568490 | T3NT DI GRIZZLY TAP 003/020 INST MRKW |  | TAP (CITY OF SANTA CLARA) | 003/020 | ICW | F | Pre-2020_(5b) On structure in bucket 5 | [5 empty] | North Valley | WSIP | [6 empty] | '-121.325883 | 39.9106 | ETL.2395 | 44551441 | Marker (i.e. signs)-Wood | Missing | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117568584 | T2 EI SPLDING-SMMIT 014/470 RPL STRW | 31495368 | SPAULDING-SUMMIT | 014/470 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.398613 | 39.3287 | ETL.8060 | 40751873 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
117568758 | T2 DI DRUM-SUMMIT #2 021/253L RPL POLE | 31471241 | DRUM-SUMMIT #2 | 021/253 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.428125 | 39.3265 | ETL.1450 | 44557473 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
117568759 | T2 DI SNEATH LANE-PACIFICA 4/52 RPR GYWW | 43877619 | SNEATH LANE-PACIFICA | 004/052 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.456143 | 37.6142 | ETL.7575 | 40864576 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Bay |  | Y - 6
117568793 | T2 DI DRUM-SUMMIT #2 021/253R RPL POLE | 31471241 | DRUM-SUMMIT #2 | 021/253 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.428125 | 39.3265 | ETL.1450 | 44557671 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
117568853 | DI NEWARK-VALLECITOS 94/616 BENT MBR | 43753293 | NEWARK-VALLECITOS | 094/616 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-121.885566 | 37.5728 | ETL.7670 | 40825455 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 9
117568856 | DI NEWARK-VALLECITOS 94/616 GRDWASH INSS | 43753293 | NEWARK-VALLECITOS | 094/616 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  | Likely MAT error - delink to correct |  | LATE | Central | WSIP | [6 empty] | '-121.885566 | 37.5728 | ETL.7670 | 40854583 | Insulator | Contaminated | Ground Wash | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 622 | Bay |  | Y - 9
117568897 | T2 EI DRUM-SUMMIT #2 23/274R RPR GYWW | 43947611 | DRUM-SUMMIT #2 | 023/274 | ICW | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.3939853 | 39.3291 | ETL.1450 | 44552299 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117569010 | T2 EI DRUM-SUMMIT #2 23/274C RPL STRW | 31497848 | DRUM-SUMMIT #2 | 023/274 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.3939853 | 39.3291 | ETL.1450 | 44552298 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
117570049 | T2 DI CAR PAL :20/160 RPL HRDT | 44069454 | CARIBOU-PALERMO | :020/160 | ICQ | E | Pre-2020_(2) High fire spread TD |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.353207 | 39.9056 | ETL.3190 | 40642284 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
117570097 | T2NT DI CAR PAL 20/160 RPL INSS |  | CARIBOU-PALERMO | :020/160 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP |  |  |  | Field Operations |  | '-121.353207 | 39.9056 | ETL.3190 | 40642431 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain
117572217 | T2 DI FT RSS GUA 49/9 BOND GYWW HRDD | 43920743 | GUALALA-MONTE RIO | 049/009 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.402144 | 38.722 | ETL.6980 | 40876078 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  | 2019-07-19
117572583 | T2NT EI SPALDNG-SMMT 015/492 REMV VEG |  | SPAULDING-SUMMIT | 015/492 | HNA | F | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.381998 | 39.328 | ETL.8060 | 40771521 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  | Yes
117572628 | T2 DI CARIBOU-PALERMO :6/048 RPR FOND | 44059014 | CARIBOU-PALERMO | :006/048 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.219155 | 40.0264 | ETL.3190 | 40910290 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
117572775 | EI T2NT SPLDING-SUMMIT 15/479 RPR INSW | 43924041 | SPAULDING-SUMMIT | 015/479 | ICW | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-120.392076 | 39.3289 | ETL.8060 | 40602263 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117572800 | T2NT EI DRUM-SUMMIT #1 21/252 INS STR ID | 43910103 | DRUM-SUMMIT #1 | 021/252 | ICS | F | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.4264296 | 39.3159 | ETL.1440 | 44338240 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes
117572822 | EI NT NWARK - LIVERMORE 008/050 REPAINT | 43752137 | NEWARK-LIVERMORE | 008/050 | ICS | F | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) |  |  |  |  | Central | Non-WSIP | [6 empty] | '-121.874509 | 37.5661 | ETL.7660 | 40613235 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  | Y - Prog Multi
117572996 | T2NT EI SPLDNG-SMMIT 015/493 INST MRKW | 43924041 | SPAULDING-SUMMIT | 015/493 | ICW | F | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.380982 | 39.3277 | ETL.8060 | 40770700 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117573324 | T2 SPAULDING-SUMMIT 015/489 RMV VEG |  | SPAULDING-SUMMIT | 015/489 | HNA | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.384793 | 39.3287 | ETL.8060 | 40602265 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento |  |  | Yes
117573568 | T2 SPAULDING-SUMMIT 015/487 RPL ANCW | 31463885 | SPAULDING-SUMMIT | 015/487 | 93E | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.386916 | 39.3286 | ETL.8060 | 44349562 | Anchor-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Sacramento |  |  | Yes
117573615 | EI NT NEWRK - LIVERMORE 005/037 REPAINT | 43752137 | NEWARK-LIVERMORE | 005/037 | ICS | F | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) |  |  |  |  | Central | Non-WSIP | [6 empty] | '-121.901972 | 37.5353 | ETL.7660 | 40804508 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  | Y - Prog Multi
117573760 | MIDWAY-WHEELER RIDGE #1 19/89 INS SHIELD | 31462807 | MIDWAY-WHEELER RIDGE #1 | 019/089 | 70S | F | Pre-2020_(5b) On structure in bucket 5 | [5 empty] | South | Non-WSIP | [6 empty] | '-119.359772 | 35.1945 | ETL.5190 | 40860421 | Shield Wire / OPGW-Steel | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Pole Program | Capital | 426 | Midway |  |  | DWR
117573859 | T2 MORRO BAY-SLO#2 010/058 REPL INSS | 31457244 | MORRO BAY-SAN LUIS OBISPO #2 | 010/058 | 93K | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.705446 | 35.2872 | ETL.2820 | 40884352 | Insulator-Steel | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach
117574043 | EI NEWARK-LIVERMORE 005/039 CANCEL | 43752137 | NEWARK-LIVERMORE | 005/039 | ICS | F | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) |  | CANCEL/CNCL |  |  | Central | Non-WSIP | [6 empty] | '-121.89639 | 37.5416 | ETL.7660 | 40857512 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay
117574069 | DI STANISLAUS-NWK #2 85/554 RPR FOND |  | STANISLAUS-NEWARK #2 (12KV) | 085/554 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-121.746183 | 37.6529 | ETL.3860 | 41196045 | Foundation/Concrete-Tower | Earth Covered Tower | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog Multi
117574143 | T2 MRR BY-SN LUS OBSP #2 10/57 RPL INSS | 31457244 | MORRO BAY-SAN LUIS OBISPO #2 | 010/057 | 93K | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.707306 | 35.2891 | ETL.2820 | 40835299 | Insulator-Steel | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach
117574220 | DI STANISLAUS-NWK #2 85/554 BENT MBR |  | STANISLAUS-NEWARK #2 (12KV) | 085/554 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-121.746183 | 37.6529 | ETL.3860 | 41196045 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog Multi
117574409 | T2 MRR BY-SN LUS OBSP #2 10/55 RPL INSS | 31457244 | MORRO BAY-SAN LUIS OBISPO #2 | 010/055 | 93K | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.711131 | 35.2928 | ETL.2820 | 40778639 | Insulator-Steel | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach
117574441 | T2 EI DRUM-SUMMIT #2 26/311A REPL PL | 31521951 | DRUM-SUMMIT #2 | 026/311A | 70Y | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.355394 | 39.3095 | ETL.1450 | 40590181 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
117574525 | T2 MORRO BAY-SLO#2 9/52 REPL INSS | 31457244 | MORRO BAY-SAN LUIS OBISPO #2 | 009/052 | 93K | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.717714 | 35.297 | ETL.2820 | 40713610 | Insulator-Steel | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach
117574546 | T2 EI DRUM-SUMMIT #2 26/311B REPL PL | 31521951 | DRUM-SUMMIT #2 | 026/311B | 70Y | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.355409 | 39.3095 | ETL.1450 | 42572851 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
117574668 | T2 MRR BY-SN LUS OBSP #2 09/051 RPL INSS | 31457244 | MORRO BAY-SAN LUIS OBISPO #2 | 009/051 | 93K | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.720181 | 35.2982 | ETL.2820 | 40609263 | Insulator-Steel | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach
117574814 | T2 EI DRUM-SUMMIT #2 26/311C REPL PL | 31521951 | DRUM-SUMMIT #2 | 026/311C | 70Y | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.355434 | 39.3094 | ETL.1450 | 42572852 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
117575033 | T2 MORRO BAY-SLO #2 8/43 REPL INSS | 31457244 | MORRO BAY-SAN LUIS OBISPO #2 | 008/043 | 93K | F | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.739234 | 35.3078 | ETL.2820 | 40676695 | Insulator-Steel | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach
117575107 | EI HELMS-GREGG #2 0/1B REPAINT TOWER | 44300721 | HELMS-GREGG #2 | 000/001B | ICX | F | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) |  | Likely MAT error - delink to correct |  |  | South | Non-WSIP | [6 empty] | '-118.964024 | 37.0388 | ETL.4880 | 40740028 | Structure-Tower | Paint/Coating | Repaint | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense |  | Fresno |  | Y - 12 | Released
117575225 | T2 SNETH LNE-HLF MN BY ?011/05 REPAINT | 44586181 | SNEATH LANE-HALF MOON BAY | ?011/005 | ICS | F | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) |  |  | TR2 |  | Central | Non-WSIP | [6 empty] | '-122.420738 | 37.4734 | ETL.7212 | 40875342 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay
117575226 | T2 SNEATH LANE-HLF MN BY ?11/4 REPAINT | 44586181 | SNEATH LANE-HALF MOON BAY | ?011/004 | ICS | F | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) |  |  | TR2 |  | Central | Non-WSIP | [6 empty] | '-122.420313 | 37.4744 | ETL.7212 | 40823350 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay
117575230 | SNEATH LANE-HALF MN BY ?11/14 REPAINT | 44586181 | SNEATH LANE-HALF MOON BAY | ?011/014 | ICS | F | Pre-2020_(9a) Other ignition related | [5 empty] | Central | Non-WSIP | [6 empty] | '-122.429996 | 37.4693 | ETL.7212 | 40823354 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay
117575231 | SNEATH LANE-HLF MN BY ?011/012 REPAINT | 44586181 | SNEATH LANE-HALF MOON BAY | ?011/012 | ICS | F | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) |  |  |  |  | Central | Non-WSIP | [6 empty] | '-122.429256 | 37.4703 | ETL.7212 | 40813440 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay
117575232 | SNEATH LANE-HALF MOON BAY ?11/11 REPAINT | 44586181 | SNEATH LANE-HALF MOON BAY | ?011/011 | ICS | F | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) |  |  |  |  | Central | Non-WSIP | [6 empty] | '-122.428389 | 37.4705 | ETL.7212 | 43250631 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay
117575236 | SNEATH LANE-HLF MN BY ?11/10 REPAINT | 44586181 | SNEATH LANE-HALF MOON BAY | ?011/010 | ICS | F | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) |  |  |  |  | Central | Non-WSIP | [6 empty] | '-122.427063 | 37.4709 | ETL.7212 | 40656255 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay
117575238 | T2 SNEATH LNE-HLF MN BY ?11/01 REPAINT | 44586181 | SNEATH LANE-HALF MOON BAY | ?011/001 | ICS | F | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) |  |  | TR2 |  | Central | Non-WSIP | [6 empty] | '-122.418584 | 37.4788 | ETL.7212 | 40768024 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay
117583170 | EI HELMS-GREGG #2 0/001B RPR CONS | 43825465 | HELMS-GREGG #2 | 000/001B | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | South | WSIP | [6 empty] | '-118.964024 | 37.0388 | ETL.4880 | 40740028 | Conductor-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  | Y - 11
117583755 | T2 MRR BY-SN LUS OBSP #2 12/68 RPL INSS | 31457244 | MORRO BAY-SAN LUIS OBISPO #2 | 012/068 | 93K | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.684904 | 35.2676 | ETL.2820 | 40884355 | Insulator-Steel | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach
117583822 | T2 MORRO BAY-SLO #2 12/067 REPL INSS | 31457244 | MORRO BAY-SAN LUIS OBISPO #2 | 012/067 | 93K | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.68678 | 35.2693 | ETL.2820 | 40835303 | Insulator-Steel | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach
117583835 | T2 EI DRUM-SUMMIT #2 27/323 INS ANTCLMB | 31462463 | DRUM-SUMMIT #2 | 027/323 | 93A | F | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.338006 | 39.3108 | ETL.1450 | 40671557 | Structure-Steel | Anti-Climbing Guard | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Capital | 988 | Sacramento |  |  | Yes
117583873 | T2 MRR BY-SN LUS OBSP #2 12/66 RPL INSS | 31457244 | MORRO BAY-SAN LUIS OBISPO #2 | 012/066 | 93K | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.68856 | 35.271 | ETL.2820 | 40838024 | Insulator-Steel | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach
117583893 | T2 TRINITY-MAPLE CREEK 15/7 RMV PL BUTT | 43749708 | TRINITY-MAPLE CREEK | 015/007 | ICW | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [8 empty] | ETL.8170 | 44370545 | Structure-Wood | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
117583921 | T2 MRR BY-SN LS OBSP #1 12/68 RPR ROAD | 44635170 | MORRO BAY-SAN LUIS OBISPO #1 | 012/068 | CHS | F | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | South | Non-WSIP | [6 empty] | '-120.685057 | 35.2675 | ETL.2810 | 40861171 | Road | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLR | Roads | Expense | 932 | Pismo Beach
117583936 | T3 SNEATH LANE-HALF MN BY ?10/2 CLR ROAD |  | SNEATH LANE-HALF MOON BAY | ?010/002 | CHS | F | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Veg/Land/Road) |  |  | TR3 |  | Central | Non-WSIP | [6 empty] | '-122.424481 | 37.4906 | ETL.7212 | 40695077 | Road | Brush Fuel | Remove |  |  |  |  | PEND | LC | TLR | Roads | Expense | 932 | Bay
117583963 | T2 TRINITY-MAPLE CREEK 17/014 RMV BUTTS | 43749708 | TRINITY-MAPLE CREEK | 017/014 | ICW | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.223948 | 40.7396 | ETL.8170 | 40744513 | Structure-Wood | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2019-10-23
117584020 | T2NT EI DRM-SUMMIT #2 27/322 INS ANTCLMB | 31462463 | DRUM-SUMMIT #2 | 027/322 | 93A | F | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.338353 | 39.3107 | ETL.1450 | 40590184 | Structure-Steel | Anti-Climbing Guard | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Capital | 988 | Sacramento |  |  | Yes
117584038 | T2 TRINITY-MAPLE CREEK 18/3 RPL POLE | 31472080 | TRINITY-MAPLE CREEK | 018/003B | 70Y | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.230054 | 40.7365 | ETL.8170 | 40650354 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2019-11-14
117584327 | T2 TRINITY-MAPLE CREEK 018/004 RPL POLE | 31472080 | TRINITY-MAPLE CREEK | 018/004 | 70Y | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.230526 | 40.7365 | ETL.8170 | 40744515 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2019-11-14
117585155 | T2 TRINITY-MAPLE CREEK 018/5 RPL POLE | 31472080 | TRINITY-MAPLE CREEK | 018/005 | 70Y | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.23111 | 40.7365 | ETL.8170 | 40761915 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2019-11-14
117585230 | T2 HUMBOLDT-TRINITY 062/004 CANCEL | 44311174 | HUMBOLDT-TRINITY | 062/004 | ICW | E | Pre-2020_(9a) Other ignition related |  |  | CANCEL/CNCL | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.212105 | 40.7436 | ETL.1820 | 44562275 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2019-08-30
117585419 | T2 DI HATCRK#1-WSTWD 026/500 RPR GYWW | 43939292 | HAT CREEK #1-WESTWOOD | 026/500 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.198738 | 40.6751 | ETL.7030 | 40676346 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117585592 | T2 MRR BY-SN LUS OBSP #2 15/85 RPL INSS | 31457244 | MORRO BAY-SAN LUIS OBISPO #2 | 015/085 | 93K | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.647688 | 35.2542 | ETL.2820 | 40778645 | Insulator-Steel | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach
117585702 | EI HUMBOLDT-BRIDGEVILLE 108/1 LFT RPL PL | 31496089 | HUMBOLDT-BRIDGEVILLE | 108/001 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | North Coast | Non-WSIP | [6 empty] | '-123.9737185 | 40.7487 | ETL.1810 | 44322586 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka
117585892 | EI MTN GTE JCT-CSCD 003/035 RPR STRW (R) | 43758388 | MTN GATE JCT-CASCADE | 003/035 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.32463 | 40.6951 | ETL.7640 | 44565327 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117585913 | T3 DI CARIBOU-PALERMO :007/056 BENT MEMB | 44057199 | CARIBOU-PALERMO | :007/056 | ICQ | E | Pre-2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations | Circuit Based Scheduling | '-121.226084 | 40.0084 | ETL.3190 | 40910298 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
117585932 | DI MTN GATE JCT-CSCD 003/035 RPR STRW(L) | 43758388 | MTN GATE JCT-CASCADE | 003/035 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.32463 | 40.6951 | ETL.7640 | 44565379 | Switch-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117586096 | EI PARADISE-BUTTE 009/093L RPR GYWS | 43881381 | PARADISE-BUTTE | 009/093 | ICS | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | North Valley | Non-WSIP | [6 empty] | '-121.731853 | 39.7086 | ETL.4396 | 44382923 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117586107 | DI MTN GATE JCT-CSCD 004/038R CANCEL | 43758388 | MTN GATE JCT-CASCADE | 004/038 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  | CANCEL/CNCL |  | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.325896 | 40.6902 | ETL.7640 | 44565420 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117586601 | T2 MRR BY-SN LUS OBSP #2 07/41 RPL INSS | 31457244 | MORRO BAY-SAN LUIS OBISPO #2 | 007/041 | 93K | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.746952 | 35.3117 | ETL.2820 | 40611537 | Insulator-Steel | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach
117586693 | T2 TRINITY-MAPLE CREEK 44/007 RMV BUTT | 43749708 | TRINITY-MAPLE CREEK | 044/007 | ICW | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.703384 | 40.7471 | ETL.8170 | 40808963 | Structure-Wood | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
117586730 | T2 TRINITY-MAPLE CREEK 044/008 RMV BUTT | 43749708 | TRINITY-MAPLE CREEK | 044/008 | ICW | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.704593 | 40.7475 | ETL.8170 | 40877937 | Structure-Wood | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
117586870 | T3 DI CARIBOU PALERMO :10/83 RPR FOND | 44057199 | CARIBOU-PALERMO | :010/083 | ICQ | E | Pre-2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations | Circuit Based Scheduling | '-121.272689 | 39.9931 | ETL.3190 | 40910324 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
117588202 | T2 DI FRT RSS-GLLA 55/2 RPR GYWW | 43920743 | GUALALA-MONTE RIO | 055/002 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.492903 | 38.7416 | ETL.6980 | 40656424 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  | 2019-07-19
117588209 | T2 DI FORT ROSS-GUALALA 056/002 CANCEL | 43920743 | GUALALA-MONTE RIO | 056/002 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  | CANCEL/CNCL | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.507076 | 38.7502 | ETL.6980 | 40686563 | Conductor-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville |  |  | 2019-07-19
117588670 | T2 DI CASCD-BNTN-DSCHTS 004/104 RPR GYWW | 43690811 | CASCADE-BENTON-DESCHUTES | 004/104 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.311551 | 40.5888 | ETL.6310 | 40759287 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117588672 | T2 DI MALIN-ROUND MTN#2 62/310 INST GMKS | 44110674 | MALIN-ROUND MTN #2 | 062/310 | ICS | F | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | WECC | North Valley | WSIP | [6 empty] | '-121.672844 | 41.1834 | ETL.6020 | 40608604 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117588726 | T2 EI SPAULDING-SUMMIT 015/497 RMV VEGN | 43924041 | SPAULDING-SUMMIT | 015/497 | ICW | E | Pre-2020_(1b) Lines with special commitments |  |  | Likely veg | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.379673 | 39.3248 | ETL.8060 | 40876711 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117588842 | T3 DI CARIBOU-PALERMO :009/075 RPR STUBS | 44057199 | CARIBOU-PALERMO | :009/075 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations | Priority Bucket 9 | '-121.26518 | 40.0035 | ETL.3190 | 40910317 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
117588843 | DI COTTONWOOD-DELEVAN#2 72/623 PNT STRS | 44305184 | COTTONWOOD-DELEVAN #2 | 072/623 | ICS | F | Pre-2020_(9a) Other ignition related | [5 empty] | North Valley | WSIP | [6 empty] | '-122.267023 | 40.2184 | ETL.4580 | 40660417 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117588848 | DI CASCADE-BNTN-DSCHTS A007/156 RPR STRW | 43690811 | CASCADE-BENTON-DESCHUTES | A007/156 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | North Valley | WSIP | [8 empty] | ETL.6310 | 44416908 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117588953 | T3 DI CARIBOU PALERMO :10/79 UNBURY MEMB | 44070463 | CARIBOU-PALERMO | :010/079 | ICS | E | Pre-2020_(3) On high spread structure |  |  |  | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.268442 | 39.9988 | ETL.3190 | 40910320 | Structure-Steel | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain
117589019 | EI NT CSTR VLLY - NWRK 014/073 RPR FOND |  | CASTRO VALLEY-NEWARK | 014/073 | ICQ | F | Pre-2020_(9a) Other ignition related | [5 empty] | Central | Non-WSIP | [6 empty] | '-121.874511 | 37.5654 | ETL.4450 | 40675940 | Foundation/Concrete-Tower | Earth Covered Tower | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 11
117589525 | T2 HUMBOLDT-TRINITY 092/000C RPL STRW | 31471992 | HUMBOLDT-TRINITY | 092/000 | 70Y | E | Pre-2020_(2) High fire spread TD |  |  |  | TR2 | LATE | North Coast | WSIP |  |  |  |  | Project | 2021 HUMBOLDT-TRINITY | '-123.716509 | 40.7504 | ETL.1820 | 44560655 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka
117589528 | T2 HUMBOLDT-TRINITY 092/00R RPL STRW | 31471992 | HUMBOLDT-TRINITY | 092/000 | 70Y | E | Pre-2020_(2) High fire spread TD |  |  |  | TR2 | LATE | North Coast | Non-WSIP |  |  |  |  | Project | 2021 HUMBOLDT-TRINITY | '-123.716509 | 40.7504 | ETL.1820 | 44560462 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka
117589529 | T2 HUMBOLDT-TRINITY 92/00L RPL STRW | 31471992 | HUMBOLDT-TRINITY | 092/000 | 70Y | E | Pre-2020_(2) High fire spread TD |  |  |  | TR2 | LATE | North Coast | Non-WSIP |  |  |  |  | Project | 2021 HUMBOLDT-TRINITY | '-123.716509 | 40.7504 | ETL.1820 | 44560498 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka
117590020 | T2 EI SPALDING-SUMMIT 016/525 RPL STRW | 31495368 | SPAULDING-SUMMIT | 016/525 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.37069 | 39.3104 | ETL.8060 | 40593593 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
117590346 | T2 DI MNTA VSTA-LOS GTOS 8/169 REMV VEG |  | MONTA VISTA-LOS GATOS | 008/169 | HNA | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-122.003495 | 37.2417 | ETL.7610 | 40824938 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Bay
117591093 | DI POE-RIO OSO 029/195 INST MRKS | 43875009 | POE-RIO OSO | 029/195 | ICS | F | Pre-2020_(4b) On structure in bucket 4 | [5 empty] | North Valley | WSIP | [6 empty] | '-121.532712 | 39.5674 | ETL.5540 | 40757649 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain
117591143 | T2 DI HT CREEK#1-WESTWOOD 0/6 RPR GYWW | 43939287 | HAT CREEK #1-WESTWOOD | 000/006 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.541173 | 40.9279 | ETL.7030 | 44190884 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117591695 | T2 HUMBOLDT-TRINITY 091/004 RMV DEBRIS | 44298757 | HUMBOLDT-TRINITY | 091/004 | ICW | F | Pre-2020_(3) On high spread structure |  |  |  | TR2 | LATE | North Coast | Non-WSIP |  |  |  |  | Project | 2021 HUMBOLDT-TRINITY | '-123.707111 | 40.7485 | ETL.1820 | 44560531 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
117591701 | T2 SNEATH LANE-HLF MN BY ?11/06 REPAINT | 44586181 | SNEATH LANE-HALF MOON BAY | ?011/006 | ICS | F | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) |  |  | TR2 |  | Central | Non-WSIP | [6 empty] | '-122.421761 | 37.4729 | ETL.7212 | 40867272 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay
117591703 | T2 HUMBOLDT-TRINITY 090/009 RMV DBRS | 44311171 | HUMBOLDT-TRINITY | 090/009 | ICW | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-123.696271 | 40.7444 | ETL.1820 | 44562641 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
117591706 | T2 HUMBOLDT-TRINITY 066/000 RMV BUTTS | 44311174 | HUMBOLDT-TRINITY | 066/000 | ICW | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.263163 | 40.7249 | ETL.1820 | 44562918 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2019-08-30
117591708 | T2 HUMBOLDT-TRINITY 066/000 RMV VEGN |  | HUMBOLDT-TRINITY | 066/000 | HNA | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-123.263163 | 40.7249 | ETL.1820 | 44562918 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Eureka
117591830 | T2 HUMBOLDT-TRINITY 066/001X RMV BUTT | 44311174 | HUMBOLDT-TRINITY | 066/001X | ICW | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.269842 | 40.7206 | ETL.1820 | 44557449 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2019-10-04
117591831 | T2 HUMBOLDT-TRINTY 066/01 RMV POLE BUTTS | 44298750 | HUMBOLDT-TRINITY | 066/001 | ICW | F | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.268289 | 40.7213 | ETL.1820 | 44562899 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2019-10-04
117591985 | T2 DI HUMBOLT-BRIDGEVILE 112/4L RPL POLE | 31497841 | HUMBOLDT-BRIDGEVILLE | 112/004 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | FSRP | [7 empty] | ETL.1810 | 44322682 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2019-08-27
117592028 | T2 HUMBOLDT-TRINITY 064/001 RMV BUTT | 44311174 | HUMBOLDT-TRINITY | 064/001 | ICW | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-123.237982 | 40.7371 | ETL.1820 | 44560554 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2019-10-04
117592101 | T2 HUMBOLDT-TRINITY 065/001 RMV BUTT | 44311174 | HUMBOLDT-TRINITY | 065/001 | ICW | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.254854 | 40.7316 | ETL.1820 | 44562900 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2019-10-04
117592122 | HUMBOLDT-TRINITY 65/004 RMV POLE BUTTS | 44311174 | HUMBOLDT-TRINITY | 065/004 | ICW | E | Pre-2020_(9a) Other ignition related |  |  |  |  | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-123.261915 | 40.726 | ETL.1820 | 44557501 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2019-10-04
117592192 | HUMBOLDT-TRINITY 063/003 RMV PL BUTTS | 44298746 | HUMBOLDT-TRINITY | 063/003 | ICW | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  |  | LATE | North Coast | Non-WSIP | [6 empty] | '-123.220224 | 40.7425 | ETL.1820 | 44562915 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
117592194 | T2 HUMBOLDT-TRINITY 061/004 RMV BUTTS | 44311171 | HUMBOLDT-TRINITY | 061/004 | ICW | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-123.190398 | 40.7403 | ETL.1820 | 44560670 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
117592196 | T2 DI HMBOLDT-BRIDGEVILLE 110/1 RPR DAMW | 43749687 | HUMBOLDT-BRIDGEVILLE | 110/001 | ICW | E | Pre-2020_(9a) Other ignition related |  |  |  |  | LATE | North Coast | WSIP | FSRP | [7 empty] | ETL.1810 | 44322629 | Damper-Wood | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2020-01-16
117592200 | HUMBOLDT-TRINITY 064/000 RPL POLE | 31494734 | HUMBOLDT-TRINITY | 064/000 | 70Y | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.230802 | 40.7363 | ETL.1820 | 44562406 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Eureka |  |  | 2019-10-04
117592211 | HUMBOLDT-TRINITY 063/003 CLR ROAD | 43878519 | HUMBOLDT-TRINITY | 063/003 | CHS | F | Pre-2020_(4b) On structure in bucket 4 | [5 empty] | North Coast | Non-WSIP | [6 empty] | '-123.220224 | 40.7425 | ETL.1820 | 44562915 | Road | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLR | Roads | Expense | 932 | Eureka
117592964 | T3 EI GRIZZLY TAP 000/001 RPL STRW (C) | 31495730 | TAP (CITY OF SANTA CLARA) | 000/001 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.279937 | 39.8898 | ETL.2395 | 44550027 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS erdy | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain
117594223 | T2 DI HAT CRK#1-WESTWD 034/664 RPR GYWW | 43939292 | HAT CREEK #1-WESTWOOD | 034/664 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.088658 | 40.5849 | ETL.7030 | 40701239 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117594541 | T2 DI HAT CREEK#1-WESTWD 28/555 RPR STRW | 43939292 | HAT CREEK #1-WESTWOOD | 028/555 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.163668 | 40.6452 | ETL.7030 | 40816147 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117594545 | T3 DI CARIBOU-PALERMO :10/78 BURIED STUB | 44057199 | CARIBOU-PALERMO | :010/078 | ICQ | E | Pre-2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations | Circuit Based Scheduling | '-121.267244 | 40.0011 | ETL.3190 | 40907020 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
117594762 | T2 DI HAT CREEK#1-WSTWD 040/777 RPR STRW | 44388736 | HAT CREEK #1-WESTWOOD | 040/777 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.031802 | 40.5117 | ETL.7030 | 40586012 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117594765 | T2 DI HAT CRK#1-WSTWD 027/535 RPLC HRDD | 43939292 | HAT CREEK #1-WESTWOOD | 027/535 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.17898 | 40.6548 | ETL.7030 | 40827594 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117594909 | T2 DI HUMBOLT-TRINITY 110/2 RPL STRW (L) | 31476190 | HUMBOLDT-TRINITY | 110/002 | 70Y | B | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-124.051873 | 40.7615 | ETL.1820 | 44562299 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka
117595142 | EI LAS POSITAS - NEWARK 002/020 RPR STRT |  | LAS POSITAS-NEWARK | 002/020 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  |  | LATE | Central | Non-WSIP | [6 empty] | '-121.732669 | 37.66 | ETL.4980 | 40870181 | Hardware-Tower | Missing | Install |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 4
117595251 | T2 DI HUMBOLT-TRINITY 110/2 RPL STRW (C) | 31476190 | HUMBOLDT-TRINITY | 110/002 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-124.051873 | 40.7615 | ETL.1820 | 44562261 | Structure-Wood | Rotten | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka
117595253 | T2 DI HUMBOLT-TRINITY 110/2 RPL STRW (R) | 31476190 | HUMBOLDT-TRINITY | 110/002 | 70Y | B | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-124.051873 | 40.7615 | ETL.1820 | 44562178 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka
117595407 | EI LAS POSITAS - NEWARK 002/021 RPR FOND |  | LAS POSITAS-NEWARK | 002/021 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  |  | LATE | Central | Non-WSIP | [6 empty] | '-121.73264 | 37.6581 | ETL.4980 | 40590641 | Foundation/Concrete-Tower | Earth Covered Tower | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 4
117595427 | EI LAS POSITAS-NEWARK 002/021 RPR STRT |  | LAS POSITAS-NEWARK | 002/021 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  |  | LATE | Central | Non-WSIP | [6 empty] | '-121.73264 | 37.6581 | ETL.4980 | 40590641 | Hardware-Tower | Missing | Install |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 4
117596032 | T2 EI BRIDGVILL-CTTNWD 32/265R RPL PL | 31444708 | BRIDGEVILLE-COTTONWOOD | 032/265 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Material & Equipment | Material unavailable | '-122.880879 | 40.365 | ETL.1110 | 44423883 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
117596447 | T2 DI HUMBLT-BRGEVLLE 110/0 RPR GYWW (L) | 43749687 | HUMBOLDT-BRIDGEVILLE | 110/000 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | FSRP | [7 empty] | ETL.1810 | 44322626 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2019-08-27
117596492 | T2 DI HUMBLT-BRGEVLLE 110/0 RPR GYWW (R) | 43749687 | HUMBOLDT-BRIDGEVILLE | 110/000 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | FSRP | [7 empty] | ETL.1810 | 44322627 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2019-08-27
117596560 | T2 DI COLGATE-CHALLENGE 0/17 RPL STRW | 31462967 | COLGATE-CHALLENGE | 000/017 | 70Y | E | 2020_(1a) PSPS |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.191419 | 39.3408 | ETL.6480 | 40824180 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento
117596883 | T2 DI HT CRK #1-WESTWD 023/451 RPR STRT | 43736797 | HAT CREEK #1-WESTWOOD | 023/451 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.230127 | 40.7039 | ETL.7030 | 40616904 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117597101 | T2 DI HMLTN-BRNCH-CHSTR 009/195 RPR STRW | 43908598 | HAMILTON BRANCH-CHESTER | 009/195 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.181558 | 40.3125 | ETL.7000 | 40758795 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117597140 | T2NT DI MLN-RND MTN # 2 72/366 INST GMKS | 44305271 | MALIN-ROUND MTN #2 | 072/366 | ICS | F | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | WECC | North Valley | WSIP | [6 empty] | '-121.80575 | 41.073 | ETL.6020 | 40811608 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117597770 | T2NT EI SPLDNG-SMMT 019/603 INST GMKW | 43924041 | SPAULDING-SUMMIT | 019/603 | ICW | F | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.332025 | 39.3118 | ETL.8060 | 40771558 | Guy Wire Mark /Indic-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117597895 | EI NT MORRO BAY - MESA 000/005 STRT PNT | 44300723 | MORRO BAY-MESA | 000/005 | ICS | F | Pre-2020_(4b) On structure in bucket 4 | [5 empty] | South | Non-WSIP | [6 empty] | '-120.839561 | 35.3735 | ETL.5290 | 40753053 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Pismo Beach
117598005 | EI NT PALERMO - NICOLS 000/007 STRT PNT | 44586168 | PALERMO-NICOLAUS | 000/007 | ICS | F | Pre-2020_(9a) Other ignition related | [5 empty] | North Valley | Non-WSIP | [6 empty] | '-121.533677 | 39.4594 | ETL.3210 | 40818313 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117598486 | T2 TRINITY-MAPLE CREEK 010/017 RMV BUTT | 43749708 | TRINITY-MAPLE CREEK | 010/017 | ICW | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.108183 | 40.7689 | ETL.8170 | 44420595 | Structure-Wood | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2019-10-30
117598487 | T2 TRINITY-MAPLE CREEK 11/0 RMV DEBRIS | 43749708 | TRINITY-MAPLE CREEK | 011/000 | ICW | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.111874 | 40.768 | ETL.8170 | 40906413 | Structure-Wood | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2019-10-23
117599007 | T2NT DI PLRM-ORVLL #2 A007/090 INS MRKW | 43724470 | PALERMO-OROVILLE #2 | A007/090 | ICW | F | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.498408 | 39.5273 | ETL.7740 | 40766680 | Marker (i.e. signs)-Wood | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117599008 | T2 DI PLRMO-ORV#2 A7/090 BOND GYWW HRDD | 43724470 | PALERMO-OROVILLE #2 | A007/090 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.498408 | 39.5273 | ETL.7740 | 40766680 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117599085 | T2NT DI CNTR CST-MRG #1 009/046 REPAINT | 44587769 | CONTRA COSTA-MORAGA #1 | 009/046 | ICS | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-121.903407 | 37.9579 | ETL.5452 | 40857837 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay
117599502 | DI DELTA-MTN GATE JCT 004/081 REPAINT | 43708883 | DELTA-MOUNTAIN GATE JCT | 004/081 | ICS | F | Pre-2020_(5) TD tag on other lines | [5 empty] | North Valley | WSIP | [6 empty] | '-122.370515 | 40.888 | ETL.6750 | 40602175 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117599539 | T2 DI MNT VISTA-LOS GATOS 9/184 RMV VEG |  | MONTA VISTA-LOS GATOS | 009/184 | HNA | E | Pre-2020_(5b) On structure in bucket 5 | Budget Owner (Veg/Land/Road) |  |  | TR2 | LATE | Central | WSIP | [5 empty] | [REDACTED]- applying for Cal Trans District 4 scenic highway permmit; eta 8/15/2020 | '-121.990117 | 37.2348 | ETL.7610 | 40665276 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Bay
117599836 | T2 TRINITY-MAPLE CREEK -012/004 RPL STRW | 31471998 | TRINITY-MAPLE CREEK | 012/004 | 70Y | E | Pre-2020_(2) High fire spread TD |  |  |  | TR2 | LATE | North Coast | Non-WSIP |  |  |  |  | Weather | AT RISK - weather impacts | '-123.138954 | 40.7656 | ETL.8170 | 40744498 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2019-11-14
117599945 | T3 EI GRIZZLY TAP 002/001L RPR ANCW |  | TAP (CITY OF SANTA CLARA) | 002/001 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.302584 | 39.8958 | ETL.2395 | 44550829 | Anchor-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117599956 | T2 DI SPAULDING-SUMMIT 13/449 REFRAME PL | 43924041 | SPAULDING-SUMMIT | 013/449 | ICW | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.414746 | 39.3282 | ETL.8060 | 42571856 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117599961 | T2 DI DRUM-SUMMIT #1 021/252 INST MRKS | 43910101 | DRUM-SUMMIT #1 | 021/252 | ICW | F | Pre-2020_(1b) Lines with special commitments |  |  |  |  | WECC | North Valley | WSIP | [6 empty] | '-120.426416 | 39.3159 | ETL.1440 | 44338241 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117599977 | EI NT POE-RIO OSO 032/215 STRT PAINT | 43875009 | POE-RIO OSO | 032/215 | ICS | F | Pre-2020_(4b) On structure in bucket 4 | [5 empty] | North Valley | Non-WSIP | [6 empty] | '-121.536562 | 39.5259 | ETL.5540 | 40757659 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain
117600082 | EI POE-RIO OSO 032/215 RPR CONS | 43875009 | POE-RIO OSO | 032/215 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | North Valley | Non-WSIP | [6 empty] | '-121.536562 | 39.5259 | ETL.5540 | 40757659 | Conductor-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117600136 | T3NT EI GRIZZLY TAP 002/007L INST MRKW |  | TAP (CITY OF SANTA CLARA) | 002/007 | ICW | F | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.312669 | 39.8973 | ETL.2395 | 44550815 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117600137 | T3NT EI GRIZZLY TAP 002/007C INST MRKW |  | TAP (CITY OF SANTA CLARA) | 002/007 | ICW | F | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.312669 | 39.8973 | ETL.2395 | 44550837 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117600549 | NT EI TESLA-NEWARK #1 011/062 INST ACG | 31451420 | TESLA-NEWARK #1 | 011/062 | 93A | F | Pre-2020_(4b) On structure in bucket 4 | [5 empty] | Central | WSIP | [6 empty] | '-121.746129 | 37.6497 | ETL.5720 | 40661746 | Structure-Tower | Anti-Climbing Guard | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Capital | 988 | Bay |  | Y - Prog Multi
117600608 | EI POE-RIO OSO 32/217 RPR COND | 43875009 | POE-RIO OSO | 032/217 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | North Valley | Non-WSIP | [6 empty] | '-121.536853 | 39.5214 | ETL.5540 | 40814851 | Conductor-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117600645 | T2 DI MALIN-RND MTN#2 063/317 INS GMKS | 44305271 | MALIN-ROUND MTN #2 | 063/317 | ICS | F | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | WECC | North Valley | WSIP | [6 empty] | '-121.686599 | 41.1664 | ETL.6020 | 40820723 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117600822 | T2 DI MALIN-ROUND MTN 63/308 INST GMKS | 44305271 | MALIN-ROUND MTN #2 | 061/308 | ICS | F | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | WECC | North Valley | WSIP | [6 empty] | '-121.669095 | 41.188 | ETL.6020 | 40862525 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117601367 | T2NT DI MAL-RND MTN #2 61/307 INST GMKS | 43621093 | MALIN-ROUND MTN #2 | 061/307 | ICQ | F | Pre-2020_(1b) Lines with special commitments |  |  | Likely MAT error - delink to correct | TR2 | WECC | North Valley | WSIP | [6 empty] | '-121.66772 | 41.1897 | ETL.6020 | 40816579 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117601381 | T3 DI DESABLA-CENTERVLL 004/047 RPR GYWW | 43913825 | DESABLA-CENTERVILLE | 004/047 | ICW | E | Pre-2020_(9a) Other ignition related |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.646249 | 39.8082 | ETL.6720 | 40770242 | Guy Wire-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117601455 | T2NT DI HUMBO-TRINI 61/5 INST MRKS (R) | 43729518 | HUMBOLDT-TRINITY | 061/005 | ICS | F | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Coast | WSIP | [8 empty] | ETL.1820 | 44324178 | Marker (i.e. signs)-Steel | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Eureka |  |  | 2019-08-30
117601587 | T2 DI MALIN-ROUND MTN 62/309 STRT PAINT | 44305271 | MALIN-ROUND MTN #2 | 062/309 | ICS | F | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | WECC | North Valley | WSIP | [6 empty] | '-121.671008 | 41.1857 | ETL.6020 | 40868281 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117601611 | T2 DI MALIN-ROUND MTN 62/309 INST MRKS | 44110807 | MALIN-ROUND MTN #2 | 062/309 | ICS | F | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | WECC | North Valley | WSIP | [6 empty] | '-121.671008 | 41.1857 | ETL.6020 | 40868281 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117601963 | NT EI POE-RIO OSO 33/220 PNT TWR | 43875009 | POE-RIO OSO | 033/220 | ICS | F | Pre-2020_(9a) Other ignition related | [5 empty] | North Valley | WSIP | [6 empty] | '-121.536481 | 39.5156 | ETL.5540 | 40605303 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117603718 | T2 DI HAT CREK #1-WESTWD 1/24 RPL POLE | 31504344 | HAT CREEK #1-WESTWOOD | 001/024 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.523727 | 40.925 | ETL.7030 | 40668055 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Need New ERTC
117604003 | DI HUMBOLDT-TRINITY 80/0 RMV VEG |  | HUMBOLDT-TRINITY | 080/000 | HNA | F | Pre-2020_(9a) Other ignition related |  |  |  |  | LATE | North Coast | WSIP | FSRP | [5 empty] | '-123.513173 | 40.7039 | ETL.1820 | 44565615 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Eureka
117604015 | HUMBOLDT-TRINITY 057/007 RMV POLE BUTTS | 43729541 | HUMBOLDT-TRINITY | 057/007 | ICW | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  |  | LATE | North Coast | Non-WSIP | [6 empty] | '-123.135296 | 40.7676 | ETL.1820 | 44560664 | Structure-Wood | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2019-10-04
117604123 | T2 DI PIT#1-COTTONWOOD 8/73A RPR STRT | 43900587 | PIT #1-COTTONWOOD | 008/073A | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.638364 | 40.9163 | ETL.5390 | 40576864 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
117604167 | T2 DI SPAULDING-SUMMIT 1/77 INST MRKW | 43924041 | SPAULDING-SUMMIT | 001/077 | ICW | F | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.614465 | 39.3108 | ETL.8060 | 40810155 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117604453 | EI TESLA-NEWARK #2 12/83 RPR FOND |  | TESLA-NEWARK #2 | 012/083 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | Central | Non-WSIP | [6 empty] | '-121.766193 | 37.6394 | ETL.5354 | 41152628 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog Multi
117604643 | T2 DI SPAULDING-SUMMIT 1/37 INS MRKS | 43930393 | SPAULDING-SUMMIT | 001/037 | ICS | F | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.626915 | 39.321 | ETL.8060 | 44349478 | Marker (i.e. signs)-Steel | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes
117604703 | EI NT CLNG #1-SN MGL 014/000 STRT PAINT | 44301011 | COALINGA #1-SAN MIGUEL | 014/000 | ICS | F | Pre-2020_(9a) Other ignition related | [5 empty] | South | WSIP | [6 empty] | '-120.511294 | 36.0246 | ETL.8580 | 40609549 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Pismo Beach
117604903 | T2 DI SPAULDING-SUMMIT 1/76 INS MRKW | 43924041 | SPAULDING-SUMMIT | 001/076 | ICW | F | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.614798 | 39.3108 | ETL.8060 | 40770649 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117604959 | T2 DI HUMBOLDT-BRIDGE 111/5L RPL POLE | 31497841 | HUMBOLDT-BRIDGEVILLE | 111/005 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | FSRP | [7 empty] | ETL.1810 | 44322669 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2019-08-27
117605313 | T2 TRINITY-MAPLE CREEK 002/000 RMV BUTT | 43749708 | TRINITY-MAPLE CREEK | 002/000 | ICW | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-122.965366 | 40.7319 | ETL.8170 | 40906262 | Structure-Wood | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2019-10-30
117605324 | T2 TRINITY-MAPLE CREEK 001/018 RMV BUTT | 43749708 | TRINITY-MAPLE CREEK | 001/018 | ICW | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-122.964397 | 40.7316 | ETL.8170 | 40906261 | Structure-Wood | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2019-10-30
117605402 | T2 DI BRIGHTON-CLAYTON#2 51/384 RPL INSS | 31451899 | BRIGHTON-CLAYTON #2 IDLE | 051/384 | 93K | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-121.903186 | 37.9837 | ETL.1130 | 40782188 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - 2
117605404 | T2 DI BRIGHTON-CLAYTON#2 51/384 HANGER | 43918839 | BRIGHTON-CLAYTON #2 IDLE | 051/384 | ICS | E | Pre-2020_(5) TD tag on other lines |  | TLN/TLQ error | Likely MAT error - delink to correct | TR2 | LATE | Central | WSIP | [6 empty] | '-121.903186 | 37.9837 | ETL.1130 | 40782188 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog Multi
117605831 | T3 EI GRIZZLY TAP 1/11R RMV VEGN |  | TAP (CITY OF SANTA CLARA) | 001/011 | HNA | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.295465 | 39.8954 | ETL.2395 | 44550727 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Table Mountain
117605880 | EI NT COLNG #1-SN MIGL 014/001 STR PNT | 44301011 | COALINGA #1-SAN MIGUEL | 014/001 | ICS | F | Pre-2020_(4b) On structure in bucket 4 | [5 empty] | South | WSIP | [6 empty] | '-120.51189 | 36.0228 | ETL.8580 | 40588488 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Pismo Beach
117606027 | EI T2 CLNG #1-SN MGL 014/002 STRT PNT | 44301011 | COALINGA #1-SAN MIGUEL | 014/002 | ICS | F | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | South | Non-WSIP | [6 empty] | '-120.51245 | 36.0223 | ETL.8580 | 40691147 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Pismo Beach
117606138 | EI T2NT CLNGA #1-SN MGL 015/00 STRT PNT | 44301011 | COALINGA #1-SAN MIGUEL | 015/001 | ICS | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-120.53244 | 36.0109 | ETL.8580 | 40588490 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Pismo Beach
117606569 | EI NT COLINGA #1-SN MGL 015/002 STRT PNT | 44301011 | COALINGA #1-SAN MIGUEL | 015/002 | ICS | F | Pre-2020_(9a) Other ignition related | [5 empty] | South | Non-WSIP | [6 empty] | '-120.53354 | 36.0104 | ETL.8580 | 40666972 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Pismo Beach |  | Y - 15
117607999 | EI TESLA-NEWARK #2 13/088 RPR FOND |  | TESLA-NEWARK #2 | 013/088 | ICQ | F | Pre-2020_(4) TD tag on high spread line | [5 empty] | Central | Non-WSIP | [6 empty] | '-121.781421 | 37.6312 | ETL.5354 | 41152633 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 8
117608281 | T2 DI WEIMAR-HALSEY 5/126 RPL POLE | 31509756 | WEIMAR-HALSEY | 005/126 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.037119 | 38.963 | ETL.8340 | 40766755 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
117609004 | EI CARIBOU-PALERMO 001/013 RPR JUMS | 44304488 | CARIBOU-PALERMO | 001/013 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | North Valley | Non-WSIP |  |  |  |  | Field Operations |  | '-121.540308 | 39.4674 | ETL.3190 | 40656294 | Jumper-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117609122 | EI NT CLNGA #1-SAN MIGL 015/004 STRT PNT | 44301011 | COALINGA #1-SAN MIGUEL | 015/004 | ICS | F | Pre-2020_(4b) On structure in bucket 4 | [5 empty] | South | WSIP | [6 empty] | '-120.53669 | 36.009 | ETL.8580 | 40754875 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Pismo Beach |  | Y - 15
117609460 | EI TESLA-NEWARK #1 12/68 INSTL ACG | 31477901 | TESLA-NEWARK #1 | 012/068 | 93A | F | Pre-2020_(4b) On structure in bucket 4 | [5 empty] | Central | Non-WSIP | [6 empty] | '-121.76556 | 37.6393 | ETL.5720 | 40862796 | Structure-Tower | Anti-Climbing Guard | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Capital | 988 | Bay |  | Y - Prog Multi
117610631 | EI CARIBOU-PALERMO 001/014 BURIED MEMB | 44069801 | CARIBOU-PALERMO | 001/014 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | North Valley | Non-WSIP |  |  |  |  | Field Operations |  | '-121.539763 | 39.4683 | ETL.3190 | 40762749 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
117610636 | EI CARIBOU-PALERMO 001/014 INST MRKS | 44302345 | CARIBOU-PALERMO | 001/014 | ICS | F | Pre-2020_(4b) On structure in bucket 4 | [5 empty] | North Valley | Non-WSIP |  |  |  |  | Field Operations | reprioritization of work - noncritical facility | '-121.539763 | 39.4683 | ETL.3190 | 40762749 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117610647 | EI CARIBOU-PALERMO 001/014 INST ACG | 31460573 | CARIBOU-PALERMO | 001/014 | 93A | F | Pre-2020_(4b) On structure in bucket 4 | [5 empty] | North Valley | Non-WSIP |  |  |  |  | Field Operations |  | '-121.539763 | 39.4683 | ETL.3190 | 40762749 | Structure-Tower | Anti-Climbing Guard | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Capital | 988 | Table Mountain |  |  | Yes
117610650 | EI CARIBOU-PALERMO 001/014 REPAINT | 44302345 | CARIBOU-PALERMO | 001/014 | ICS | F | Pre-2020_(4b) On structure in bucket 4 | [5 empty] | North Valley | Non-WSIP |  |  |  |  | Field Operations |  | '-121.539763 | 39.4683 | ETL.3190 | 40762749 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117610694 | EI CARIBOU-PALERMO 001/014 RPL JUMS | 44304488 | CARIBOU-PALERMO | 001/014 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | North Valley | Non-WSIP |  |  |  |  | Field Operations |  | '-121.539763 | 39.4683 | ETL.3190 | 40762749 | Jumper-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117610971 | T2 DI BRDGVILLE-COTTNWOD 11/102 RPR PL | 43939216 | BRIDGEVILLE-COTTONWOOD | 011/102 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-122.475337 | 40.389 | ETL.1110 | 44423204 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117611221 | EI TESLA-NEWARK #2 13/89 RPR FOND |  | TESLA-NEWARK #2 | 013/089 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | Central | Non-WSIP | [6 empty] | '-121.783442 | 37.6301 | ETL.5354 | 41152634 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 7
117611367 | EI CARIBOU-PALERMO 1/015 INS HRDT | 44069801 | CARIBOU-PALERMO | 001/015 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  |  | LATE | North Valley | Non-WSIP |  |  |  |  | Field Operations |  | '-121.539783 | 39.4704 | ETL.3190 | 40755505 | Hardware-Tower | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
117612125 | EI TESLA-NEWARK #2 13/090 INSTL ACG | 31477903 | TESLA-NEWARK #2 | 013/090 | 93A | F | Pre-2020_(4b) On structure in bucket 4 | [5 empty] | Central | Non-WSIP | [6 empty] | '-121.785374 | 37.6291 | ETL.5354 | 41152635 | Structure-Tower | Anti-Climbing Guard | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Capital | 988 | Bay |  | Y - 8
117612154 | EI TESLA-NEWARK #2 13/090 RPR FOND |  | TESLA-NEWARK #2 | 013/090 | ICQ | F | Pre-2020_(4) TD tag on high spread line | [5 empty] | Central | Non-WSIP | [6 empty] | '-121.785374 | 37.6291 | ETL.5354 | 41152635 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 8
117613502 | T2 CASCADE-BENTN-DSCHTS A9/185 REPL PL | 31427802 | CASCADE-BENTON-DESCHUTES | A009/185 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-122.242295 | 40.5557 | ETL.6310 | 40586277 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
117613524 | EI CONTRA CST-LS POSITAS 7/48 PNT STRT | 44587767 | CONTRA COSTA-LAS POSITAS | 007/048 | ICS | F | Pre-2020_(5b) On structure in bucket 5 | Budget Owner (Paint) |  |  |  |  | Central | Non-WSIP | [6 empty] | '-121.746603 | 37.9135 | ETL.4510 | 40810026 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  | Y - Prog Multi
117613782 | T2 VOLTA-SOUTH 003/074 RPL POLE | 31470529 | VOLTA-SOUTH | 003/074 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-121.871677 | 40.4168 | ETL.8300 | 40586400 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain
117613825 | CARIBOU-PLUMAS JCT 015/010 REPL POLE | 31455444 | CARIBOU-PLUMAS JCT | 015/010 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | North Valley | Non-WSIP | [6 empty] | '-120.931812 | 39.956 | ETL.6290 | 40599541 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
117613863 | EI CARIBOU-PALERMO 008/068 REPAINT | 44302345 | CARIBOU-PALERMO | 008/068 | ICS | F | Pre-2020_(9a) Other ignition related | [5 empty] | North Valley | Non-WSIP |  |  |  |  | Field Operations |  | '-121.53181 | 39.568 | ETL.3190 | 40865370 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain
117613868 | T2 CENTERVILLE-TABLE MTN 6/93 RPR POLE | 43939208 | CENTERVILLE-TABLE MTN | 006/093 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-121.70821 | 39.7125 | ETL.6320 | 40675330 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117614221 | T2 TRINITY-MAPLE CREEK 2/11 RMV BUTT | 43749708 | TRINITY-MAPLE CREEK | 002/011 | ICW | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-122.974642 | 40.7347 | ETL.8170 | 40906273 | Structure-Wood | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2019-10-23
117614466 | T2 DI CRTNA-MNOCNO #1 36/171 INST HRDT | 44306522 | CORTINA-MENDOCINO #1 | 036/171 | ICS | E | Pre-2020_(9a) Other ignition related |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.799896 | 39.1069 | ETL.1330 | 40584925 | Hardware-Tower | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville
117614558 | T2 TRINITY-MAPLE CREEK 003/003 RMV BUTT | 43749708 | TRINITY-MAPLE CREEK | 003/003 | ICW | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-122.985621 | 40.7319 | ETL.8170 | 40906283 | Structure-Wood | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2019-10-23
117614562 | T2NT DI WEIMAR-HALSEY 2/60 RMV STRW | 43938294 | WEIMAR-HALSEY | 002/060 | ICW | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.004307 | 38.9991 | ETL.8340 | 40758131 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117614652 | T3 EI CRESTA-RIO OSO 15/127 RPL INSS | 31435732 | CRESTA-RIO OSO | 015/127 | 93K | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.47636 | 39.7473 | ETL.4590 | 40910145 | Insulator-Steel | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain
117614843 | T2 TRINITY-MAPLE CREEK 003/006 RMV BUTT | 43749708 | TRINITY-MAPLE CREEK | 003/006 | ICW | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-122.988451 | 40.7317 | ETL.8170 | 40906286 | Structure-Wood | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
117614844 | T2 TRINITY-MAPLE CREEK 3/8 RMV POLE BUTT | 43749708 | TRINITY-MAPLE CREEK | 003/008 | ICW | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-122.989807 | 40.7311 | ETL.8170 | 40906288 | Structure-Wood | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
117614871 | T2 TRINITY-MAPLE CREEK 003/009 RMV BUTT | 43749708 | TRINITY-MAPLE CREEK | 003/009 | ICW | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-122.990322 | 40.7309 | ETL.8170 | 40906289 | Structure-Wood | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
117614980 | T2 TRINITY-MAPLE CREEK 003/012 RMV BUTT | 43749708 | TRINITY-MAPLE CREEK | 003/012 | ICW | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-122.993108 | 40.7303 | ETL.8170 | 40906291 | Structure-Wood | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
117615012 | T2 TRINITY-MAPLE CREEK 3/14 RMV PL BUTT | 43749708 | TRINITY-MAPLE CREEK | 003/014 | ICW | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-122.994751 | 40.7307 | ETL.8170 | 40906293 | Structure-Wood | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
117615015 | T2 TRINITY-MAPLE CREEK 003/015 RMV BUTT | 43749708 | TRINITY-MAPLE CREEK | 003/015 | ICW | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-122.995333 | 40.7309 | ETL.8170 | 40906294 | Structure-Wood | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
117615168 | T2 TRINITY-MAPLE CREEK 3/10 RMV PL BUTT | 43749708 | TRINITY-MAPLE CREEK | 003/010 | ICW | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-122.991412 | 40.7304 | ETL.8170 | 40906290 | Structure-Wood | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
117615246 | T2 EI CNTR CST-LS PSTS 10/70 PNT STRT | 43899985 | CONTRA COSTA-LAS POSITAS | 010/070 | ICS | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-121.726121 | 37.8514 | ETL.4510 | 40857287 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay
117615735 | T2 TRINITY-MAPLE CREEK 3/0 RMV POLE BUTT | 43749708 | TRINITY-MAPLE CREEK | 003/000 | ICW | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-122.983195 | 40.733 | ETL.8170 | 40906280 | Structure-Wood | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2019-10-23
117616066 | T2 TRINITY-MAPLE CREEK 4/4A RMV PL BUTT | 43749708 | TRINITY-MAPLE CREEK | 004/004A | ICW | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.008531 | 40.7348 | ETL.8170 | 40906305 | Structure-Wood | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2019-10-30
117616432 | T2 TRINITY-MAPLE CREEK 4/1 RMV POLE BUTT | 43749708 | TRINITY-MAPLE CREEK | 004/001 | ICW | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.004666 | 40.7336 | ETL.8170 | 40906301 | Structure-Wood | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2019-10-30
117616511 | T2 TRINITY-MAPLE CREEK 004/002 RMV BUTT | 43749708 | TRINITY-MAPLE CREEK | 004/002 | ICW | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.005132 | 40.7337 | ETL.8170 | 40906302 | Structure-Wood | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2019-10-30
117617232 | T2 EI CNTR CSTA-LS PSTS 10/72 INST HRDT |  | CONTRA COSTA-LAS POSITAS | 010/072 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-121.727463 | 37.8418 | ETL.4510 | 40593917 | Hardware-Tower | Missing | Install |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 6
117617288 | T3 EI CRESTA-RIO OSO 15/127 RPR CONS | 43947257 | CRESTA-RIO OSO | 015/127 | ICS | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.47636 | 39.7473 | ETL.4590 | 40910145 | Conductor-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain
117617666 | EI CARIBOU-PALERMO 4/39 INS ANTCLMB | 31460573 | CARIBOU-PALERMO | 004/039 | 93A | F | Pre-2020_(4b) On structure in bucket 4 | [5 empty] | North Valley | Non-WSIP |  |  |  |  | Field Operations |  | '-121.54005 | 39.5163 | ETL.3190 | 40867350 | Structure-Tower | Anti-Climbing Guard | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Capital | 988 | Table Mountain |  |  | Yes
117617693 | EI CARIBOU-PALERMO 4/39 PAINT STRT | 44302345 | CARIBOU-PALERMO | 004/039 | ICS | F | Pre-2020_(4b) On structure in bucket 4 |  |  | Check FDA |  |  | North Valley | Non-WSIP |  |  |  |  | Field Operations |  | '-121.54005 | 39.5163 | ETL.3190 | 40867350 | Structure-Tower | Paint/Coating | Repaint | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense |  | Table Mountain |  |  | Yes
117617696 | CARIBOU-PALERMO 4/039 RMV WOOD PLANKS | 44070463 | CARIBOU-PALERMO | 004/039 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  |  | LATE | North Valley | Non-WSIP |  |  |  |  | Field Operations |  | '-121.54005 | 39.5163 | ETL.3190 | 40867350 | Structure-Steel | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117617697 | EI CARIBOU-PALERMO 4/39 RPL SPLICES | 44304488 | CARIBOU-PALERMO | 004/039 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | North Valley | Non-WSIP |  |  |  |  | Field Operations |  | '-121.54005 | 39.5163 | ETL.3190 | 40867350 | Splice-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117617788 | EI CARIBOU-PALERMO 4/39 RPR HRDT | 44069801 | CARIBOU-PALERMO | 004/039 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | North Valley | Non-WSIP |  |  |  |  | Field Operations |  | '-121.54005 | 39.5163 | ETL.3190 | 40867350 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
117619175 | NT EI BELL-PLACER 1/16 PNT TWR | 44303813 | BELL-PLACER | 001/016 | ICS | F | Pre-2020_(9a) Other ignition related | [5 empty] | North Valley | WSIP | [6 empty] | '-121.05913 | 38.9368 | ETL.4395 | 40577450 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes
117619628 | T2 EI CNTR CST-LS PSTS 10/71 PNT STRT | 43899985 | CONTRA COSTA-LAS POSITAS | 010/071 | ICS | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-121.727017 | 37.845 | ETL.4510 | 40590628 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  |  | LVW
117619882 | EI TESLA-SALADO #1 59/259 INST HRDT | 44460801 | TESLA-SALADO #1 | 059/259 | ICQ | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  |  | LATE | Central | Non-WSIP | [6 empty] | '-121.192974 | 37.4463 | ETL.3990 | 41136336 | Hardware-Tower | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - Prog Multi
117620259 | T2 TRINITY-MAPLE CREEK 1/14 RMV PL BUTT | 43749708 | TRINITY-MAPLE CREEK | 001/014 | ICW | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-122.961111 | 40.7304 | ETL.8170 | 44356510 | Structure-Wood | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2019-10-30
117620302 | T2 TRINITY-MAPLE CREEK 001/015 RMV DBRIS | 43749708 | TRINITY-MAPLE CREEK | 001/015 | ICW | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-122.961474 | 40.7307 | ETL.8170 | 40906258 | Structure-Wood | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2019-10-23
117620470 | T2 EI CNTR CST-LS POSITAS 10/73 PNT STRT | 44587767 | CONTRA COSTA-LAS POSITAS | 010/073 | ICS | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-121.723992 | 37.8393 | ETL.4510 | 40911563 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay
117620779 | T2 TRINITY-MAPLE CREEK 004/010 RMV BUTT | 43749708 | TRINITY-MAPLE CREEK | 004/010 | ICW | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.013497 | 40.7347 | ETL.8170 | 40906311 | Structure-Wood | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2019-10-30
117620803 | T2 TRINITY-MAPLE CREEK 4/5 RMV PL BUTT | 43749708 | TRINITY-MAPLE CREEK | 004/005 | ICW | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.009752 | 40.7352 | ETL.8170 | 40906306 | Structure-Wood | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2019-10-30
117620979 | T2 TRINITY-MAPLE CREEK 004/015 RMV BUTT | 43749708 | TRINITY-MAPLE CREEK | 004/015 | ICW | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.018614 | 40.7341 | ETL.8170 | 44420579 | Structure-Wood | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2019-10-23
117621989 | EI MORAGA-OAKLAND #3 005/037 RPR HRDT | 44293744 | MORAGA-OAKLAND #3 | 005/037 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-122.226863 | 37.8069 | ETL.2740 | 40804643 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 8
117622980 | EI MORAGA-OAKLAND #3 005/038 RPR FOND |  | MORAGA-OAKLAND #3 | 005/038 |  | E | Pre-2020_(9a) Other ignition related |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-122.229105 | 37.8058 | ETL.2740 | 40857643 | Structure-Tower | Soil | Remove |  |  |  |  | PEND | LC | TLQ | Tower | Expense |  | Bay |  | Y - 9
117622981 | EI MORAGA-OAKLAND #3 005/038 INST HRDT |  | MORAGA-OAKLAND #3 | 005/038 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-122.229105 | 37.8058 | ETL.2740 | 40857643 | Hardware-Tower | Missing | Install |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 9
117623854 | T2NT EI CNTR CST-LS PSTS 11/80 PNT TWR | 43899985 | CONTRA COSTA-LAS POSITAS | 011/080 | ICS | F | Pre-2020_(5b) On structure in bucket 5 | Budget Owner (Paint) |  |  | TR2 |  | Central | WSIP | [6 empty] | '-121.713182 | 37.8196 | ETL.4510 | 40911564 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay
117623912 | T2NT EI CNTR CST-LS PSTS 12/83 PNT TWR | 43899985 | CONTRA COSTA-LAS POSITAS | 012/083 | ICS | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-121.70943 | 37.8092 | ETL.4510 | 40681623 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay
117625163 | T2 TRINITY-MAPLE CREEK 004/014 RPL POLE | 31471998 | TRINITY-MAPLE CREEK | 004/014 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.017932 | 40.7342 | ETL.8170 | 40906315 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2019-10-23
117625194 | T2 TRINITY-MAPLE CREEK 3/5 RMV PL BUTT | 43749708 | TRINITY-MAPLE CREEK | 003/005 | ICW | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-122.987254 | 40.7318 | ETL.8170 | 40906285 | Structure-Wood | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
117625230 | T2 TRINITY-MAPLE CREEK 3/20 RMV PL BUTT | 43749708 | TRINITY-MAPLE CREEK | 003/020 | ICW | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [8 empty] | ETL.8170 | 44420575 | Structure-Wood | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2019-10-23
117626523 | T2 EI SBRT-GRZZY-CLRMNT #1 6/54 RPR FOND | 43752388 | SOBRNTE-GRIZZLY-CLARMNT #1+ | 006/054 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  | Likely MAT error - delink to correct | TR2 | LATE | Central | WSIP | [6 empty] | '-122.228018 | 37.8479 | ETL.3740 | 40580980 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog Multi
117626759 | NT EI CASTRO VALLEY-NEWARK 2/16 PNT TWR | 44585912 | CASTRO VALLEY-NEWARK | 002/016 | ICS | F | Pre-2020_(9a) Other ignition related | [5 empty] | Central | WSIP | [6 empty] | '-122.036043 | 37.6797 | ETL.4450 | 40866263 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay
117627229 | T2 DI WEIMAR-HALSEY 1/39 RPL STRW | 31454601 | WEIMAR-HALSEY | 001/039 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.997127 | 39.009 | ETL.8340 | 40873791 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
117627429 | T2 DI SBRT-GRZY-CLMNT #1 A0/2 WASH INSS | 43752388 | SOBRNTE-GRIZZLY-CLARMNT #1+ | A000/002 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  | Likely MAT error - delink to correct | TR2 | LATE | Central | WSIP | [6 empty] | '-122.212805 | 37.9041 | ETL.3740 | 40577689 | Insulator | Contaminated | Helicopter Wash | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 626 | Bay |  |  | EBMUD
117627507 | EI MORAGA-OAKLAND #1 5/36 RPR FOND | 44392608 | MORAGA-OAKLAND #1 | 005/036 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-122.229135 | 37.8059 | ETL.2720 | 40804646 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 6
117627603 | EI MORAGA-OAKLAND #1 5/36 RPR STRT | 44392608 | MORAGA-OAKLAND #1 | 005/036 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-122.229135 | 37.8059 | ETL.2720 | 40804646 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 6
117627609 | EI MORAGA-OAKLAND #1 5/36 RPL HRDT | 44392608 | MORAGA-OAKLAND #1 | 005/036 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-122.229135 | 37.8059 | ETL.2720 | 40804646 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 6
117628165 | DI NT MORAGA-OAKLAND #3 5/39 RPR FOND |  | MORAGA-OAKLAND #3 | 005/039 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-122.230287 | 37.8058 | ETL.2740 | 41196337 | Foundation/Concrete-Tower | Earth Covered Tower | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 9
117629694 | DI MORAGA-OAKLAND #1 4/34 RMV DEBRIS | 44598133 | MORAGA-OAKLAND #1 | 004/034 | ICS | E | Pre-2020_(9a) Other ignition related |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-122.224179 | 37.8094 | ETL.2720 | 40745869 | Structure-Steel | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay
117629859 | EI MORAGA-OAKLAND #1 4/34 RPR FOND |  | MORAGA-OAKLAND #1 | 004/034 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-122.224179 | 37.8094 | ETL.2720 | 40745869 | Foundation/Concrete-Tower | Earth Covered Tower | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay
117629900 | EI MORAGA-OAKLAND #2 4/33 RPR CONS | 43909784 | MORAGA-OAKLAND #2 | 004/033 | ICS | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-122.221382 | 37.8113 | ETL.2730 | 44668643 | Conductor-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - Prog Multi | 2019-07-31
117631802 | T2 EI CHOWCHILLA-KERCKHOFF 2/1 RMV BUTTS | 43912702 | CHOWCHILLA-KERCKHOFF | 002/001 | ICW | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | South | WSIP | FSRP | [5 empty] | '-119.586009 | 37.0905 | ETL.1250 | 44191704 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Fresno |  | Y - 21
117632537 | T2 SOBRANTE-GRZLY-CLRMNT#2 A0/1 RPR CONS | 43914263 | SOBRANTE-GRIZLY-CLARMNT #2+ | A000/001 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | Non-WSIP | FSRP | [5 empty] | '-122.210483 | 37.9054 | ETL.3750 | 44359726 | Conductor-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - 10
117633025 | DI HUMBOLDT-BRIDGEVILLE 114/5 RPR GYWW | 43749687 | HUMBOLDT-BRIDGEVILLE | 114/005 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | North Coast | WSIP | FSRP | [7 empty] | ETL.1810 | 44322747 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
117634305 | T3 DI GRIZZLY TAP (SVP) 4/2 RPR STRT | 43930737 | GRIZZLY TAP (SVP) | 004/002 | ICQ | E | Pre-2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations | 2021 | '-121.327512 | 39.9113 | ETL.1231 | 44188701 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
117635491 | T2 SOBRNT-GRZZLY-CLRMNT#1 02/23 RPL INSS | 31484739 | SOBRNTE-GRIZZLY-CLARMNT #1+ | 002/023 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | Non-WSIP | [6 empty] | '-122.186646 | 37.8798 | ETL.3740 | 40898589 | Insulator-Steel | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - 13
117635619 | T2 SOBRANTE-GRZLY-CLRMNT#1 2/24 REPL INS | 31484739 | SOBRNTE-GRIZZLY-CLARMNT #1+ | 002/024 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | Non-WSIP | [6 empty] | '-122.185476 | 37.8783 | ETL.3740 | 40884326 | Insulator-Steel | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - 13 | CalTrans
117636475 | DI HUMBOLDT-BRIDGEVILLE 114/5 RPR GYWW | 43749687 | HUMBOLDT-BRIDGEVILLE | 114/005 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | North Coast | WSIP | FSRP | [7 empty] | ETL.1810 | 44322749 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2019-08-27
117636478 | DI HUMBOLDT-BRIDGEVILLE 114/5 RPR GYWW | 43749687 | HUMBOLDT-BRIDGEVILLE | 114/005 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | North Coast | WSIP | FSRP | [7 empty] | ETL.1810 | 44322748 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2019-08-27
117636501 | DI HUMBOLDT-BRIDGEVILLE 114/5 RPL INSW | 31472113 | HUMBOLDT-BRIDGEVILLE | 114/005 | 93I | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | North Coast | WSIP | FSRP | [7 empty] | ETL.1810 | 44322749 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC erdy srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Eureka
117639163 | T2 DI PIT #1-COTTONWOOD 038/328 RPR FOND | 43637398 | PIT #1-COTTONWOOD | 038/328 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.044765 | 40.6643 | ETL.5390 | 40871584 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | CONS | CONS | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | Yes
117639169 | T2 DI PIT #3-PIT #1 001/012 REPL SPLS | 43877630 | PIT #3-PIT #1 | 001/012 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.515038 | 40.9767 | ETL.5400 | 40668278 | Splice-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117639263 | T2 DI PIT #3-PIT #1 001/012 INSTALL MRKS | 43877630 | PIT #3-PIT #1 | 001/012 | ICS | F | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.515038 | 40.9767 | ETL.5400 | 40668278 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117639528 | T2 DI FULTON-HOPLAND 017/002 RPL STRW | 31478308 | FULTON-HOPLAND | 017/002 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.865708 | 38.7062 | ETL.6890 | 40692939 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville |  |  | 2019-08-15
117640648 | T2 DI EL DRDO-MSSR FLT#2 12/112 RPL INSS | 31462723 | ELDORADO-MISSOURI FLAT #2 | 012/112 | 93K | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.804806 | 38.7147 | ETL.1540 | 40724797 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Sacramento |  |  | Yes
117640834 | T2 DI TULE-SPRINGVILLE 14/1 RPR GYWW | 44323713 | TULE-SPRINGVILLE | 014/001 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-118.899227 | 36.1099 | ETL.9040 | 40584057 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Midway |  | Y - 23
117643795 | T2NT DI VOLTA-DESCHUTES 20/445 INST MRKW | 43939089 | VOLTA-DESCHUTES | 020/445 | ICW | F | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.227783 | 40.5521 | ETL.8290 | 40676458 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117645216 | DI RND MTN-COTTONWOOD #3 35/302 RPR SPLS | 43755803 | ROUND MTN-COTTONWOOD #3 | 035/302 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-122.019568 | 40.6948 | ETL.5650 | 40675852 | Splice-Steel | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117646483 | DI TESLA-LOS BNS #1 28/126 INST ZENA | 43939159 | TESLA-LOS BANOS #1 | 028/126 | ICS | F | Pre-2020_(5b) On structure in bucket 5 |  |  |  |  | LATE | Central | WSIP | FSRP | [5 empty] | '-121.192398 | 37.4432 | ETL.6100 | 40811974 | Raptor Guard-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 593 | Victor |  | Y - Prog Multi
117646634 | DI TESLA-LOS BANOS #1 28/126 WASH INSS | 44598406 | TESLA-LOS BANOS #1 | 028/126 | ICI | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-121.192398 | 37.4432 | ETL.6100 | 40839391 | Insulator | Contaminated | Helicopter Wash | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 626 | Victor |  | None
117647940 | T2 TRINITY-MAPLE CREEK 47/12 RMV PL BUTT | 43683558 | TRINITY-MAPLE CREEK | 047/012 | ICW | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.758649 | 40.7506 | ETL.8170 | 40701836 | Structure-Wood | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2019-10-23
117648492 | T2 TRINITY-MAPLE CREEK 42/0 RMV PL BUTT | 43683558 | TRINITY-MAPLE CREEK | 042/000 | ICW | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.663121 | 40.7284 | ETL.8170 | 40617900 | Structure-Wood | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2019-11-14
117649423 | T2 TRINITY-MAPLE CRK 41/11A RMV PL BUTT | 43683558 | TRINITY-MAPLE CREEK | 041/011A | ICW | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-123.660398 | 40.7278 | ETL.8170 | 44948556 | Structure-Wood | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2019-11-14
117649880 | T2 DI GRIZZLY TAP 2/4L RPR PL |  | TAP (CITY OF SANTA CLARA) | 002/004 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-121.308071 | 39.8967 | ETL.2395 | 44550057 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117654249 | T2 DRUM-SUMMIT #2 24/296B REPL POLE | 31521951 | DRUM-SUMMIT #2 | 024/296B | 70Y | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-120.377716 | 39.3155 | ETL.1450 | 42572847 | Structure-Wood | Rotten | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
117654284 | T2 DRUM-SUMMIT #2 25/302A REPL POLE | 31521951 | DRUM-SUMMIT #2 | 025/302A | 70Y | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-120.370508 | 39.3106 | ETL.1450 | 40756991 | Structure-Wood | Rotten | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
117654296 | T2 DRUM-SUMMIT #2 24/296C REPL POLE | 31521951 | DRUM-SUMMIT #2 | 024/296C | 70Y | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-120.377675 | 39.3155 | ETL.1450 | 42572848 | Structure-Wood | Rotten | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
117654297 | T2 DRUM-SUMMIT #2 25/302B REPL POLE | 31521951 | DRUM-SUMMIT #2 | 025/302B | 70Y | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-120.370536 | 39.3106 | ETL.1450 | 42572849 | Structure-Wood | Rotten | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
117654301 | T2 DRUM-SUMMIT #2 24/296A REPL POLE | 31521951 | DRUM-SUMMIT #2 | 024/296A | 70Y | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-120.377795 | 39.3154 | ETL.1450 | 40594971 | Structure-Wood | Rotten | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
117654302 | T2 DRUM-SUMMIT #2 25/302C REPL POLE | 31521951 | DRUM-SUMMIT #2 | 025/302C | 70Y | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-120.370575 | 39.3105 | ETL.1450 | 42572850 | Structure-Wood | Rotten | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
117654685 | T2 SPAULDING-SUMMIT 12/429 REPL POLE | 31453471 | SPAULDING-SUMMIT | 012/429 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-120.430958 | 39.3253 | ETL.8060 | 40586101 | Structure-Wood | Rotten | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento
117654686 | T2 SPAULDING-SUMMIT 15/481 REFRAME | 31463885 | SPAULDING-SUMMIT | 015/481 | 93E | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-120.390725 | 39.329 | ETL.8060 | 40650064 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Sacramento |  |  | Yes
117655702 | DI TABLE MTN-PALERMO 5/27 INST MRKS | 44154424 | TABLE MTN-PALERMO | 005/027 | ICS | F | Pre-2020_(5b) On structure in bucket 5 | [5 empty] | North Valley | WSIP | [6 empty] | '-121.543912 | 39.5456 | ETL.5690 | 40814381 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117657953 | DRUM-SUMMIT #2 15/176L REPL POLE | 31521945 | DRUM-SUMMIT #2 | 015/176 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  |  |  |  | LATE | North Valley | Non-WSIP | [6 empty] | '-120.537147 | 39.3098 | ETL.1450 | 44559040 | Structure-Wood | Rotten | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
117657954 | DRUM-SUMMIT #2 17/204 REPL POLE | 31521949 | DRUM-SUMMIT #2 | 017/204 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  |  |  |  | LATE | North Valley | Non-WSIP | [6 empty] | '-120.498895 | 39.3143 | ETL.1450 | 44557615 | Structure-Wood | Rotten | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
117658094 | DRUM-SUMMIT #2 14/164R REPL POLE | 31521945 | DRUM-SUMMIT #2 | 014/164 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  |  |  |  | LATE | North Valley | Non-WSIP | [6 empty] | '-120.550965 | 39.318 | ETL.1450 | 44561431 | Structure-Wood | Rotten | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
117658230 | DRUM-SUMMIT #2 13/155L REPL POLE | 31498154 | DRUM-SUMMIT #2 | 013/155 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  |  |  |  | LATE | North Valley | Non-WSIP | [6 empty] | '-120.563451 | 39.3252 | ETL.1450 | 44561321 | Structure-Wood | Rotten | Replace | ESTS erdy | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
117665794 | T3 DRUM-HIGGINS 0/3 RPR CONW | 43918680 | DRUM-HIGGINS | 000/003 | ICW | E | Pre-2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | Non-WSIP |  |  |  |  | Clearance Denied by GCC | 2021 - Clearance denied due to work on the Drum powerhouse. | '-120.766933 | 39.2541 | ETL.4393 | 44552302 | Conductor-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117665982 | T3NT EI MORAGA-OAKLAND#3 0/8 PAINT STRS | 43725286 | MORAGA-OAKLAND #3 | 000/008 | ICS | F | Pre-2020_(9a) Other ignition related |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-122.176756 | 37.8441 | ETL.2740 | 40872587 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay
117666210 | T3 DI MRAGA-OKLND#2 000/002 RPL INSS | 31461003 | MORAGA-OAKLAND #2 | 000/002 | 93K | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.166133 | 37.8478 | ETL.2730 | 40728506 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - Prog Multi
117666219 | T3 DI MORAGA-OAKLAND #4 001/009 RPL INSS | 31461002 | MORAGA-OAKLAND #4 | 001/009 | 93K | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.177789 | 37.8431 | ETL.2750 | 40878740 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - 1
117666328 | T3 SOBRANTE-GRZLY-CLRMNT#2 A1/9 RPR JUMS | 44221597 | SOBRANTE-GRIZLY-CLARMNT #2+ | A001/009 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | Central | Non-WSIP | [6 empty] | '-122.224573 | 37.8895 | ETL.3750 | 40878965 | Jumper-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - 10
117667063 | T2 DI TESLA-METCALF 011/045 INST HRDT |  | TESLA-METCALF | 011/045 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-121.605177 | 37.551 | ETL.6110 | 40764502 | Hardware-Tower | Missing | Install |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog Multi
117667313 | T2 SNEATH LANE-HALF MN BY ;0/8 RMV VEGN |  | SNEATH LANE-HALF MOON BAY | ;000/008 | HNA | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | Central | Non-WSIP | FSRP | [5 empty] | '-122.455446 | 37.6145 | ETL.7212 | 40875330 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Bay
117667376 | T2 SNEATH LANE-HLF MN BY ;1/13 RMV VEGN |  | SNEATH LANE-HALF MOON BAY | ;001/013 | HNA | E | Pre-2020_(3) On high spread structure |  |  |  | TR2 | LATE | Central | Non-WSIP |  |  |  |  | Access Issues | 2021 - Access issues | '-122.456784 | 37.6077 | ETL.7212 | 40695033 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Bay
117667383 | T2 SNEATH LANE-HALF MN BY ;1/14 RMV VEGN |  | SNEATH LANE-HALF MOON BAY | ;001/014 | HNA | E | Pre-2020_(3) On high spread structure |  |  |  | TR2 | LATE | Central | Non-WSIP |  |  |  |  | Access Issues | 2021 - Access issues | '-122.457322 | 37.6069 | ETL.7212 | 40665322 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Bay
117668498 | T3 EI MORAGA-OAKLAND #4 1/10 RPL INSS | 31461002 | MORAGA-OAKLAND #4 | 001/010 | 93K | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.181803 | 37.8409 | ETL.2750 | 40621986 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - 1
117668751 | T3 EI MORAGA-OAKLAND #3 2/20 RPR STRT | 44293744 | MORAGA-OAKLAND #3 | 002/020 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.201996 | 37.8297 | ETL.2740 | 40581560 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 8
117669359 | T2 TRINITY-MAPLE CREEK 49/6 RMV PL BUTT | 44167431 | TRINITY-MAPLE CREEK | 049/006 | ICW | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.78975 | 40.7572 | ETL.8170 | 40809442 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2019-10-23
117671064 | T3 EI MORAGA-OAKLAND#3 2/24 RPL INSS | 31461014 | MORAGA-OAKLAND #3 | 002/024 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.203794 | 37.823 | ETL.2740 | 40775600 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - Prog Multi
117671140 | T3 DI MORAGA-OAKLAND#4 2/24 RPL INSS | 31461002 | MORAGA-OAKLAND #4 | 002/024 | 93K | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.203794 | 37.823 | ETL.2750 | 40775602 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - 1
117671391 | T2 DI TULE-SPRINGVILLE 23/17 RPR STRW | 44323716 | TULE-SPRINGVILLE | 023/017 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-118.754825 | 36.1479 | ETL.9040 | 40821821 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Midway |  | Y - 23 | USFS
117671611 | T2 TRINITY-MAPLE CREEK 5/5 RMV PL BUTT | 43749708 | TRINITY-MAPLE CREEK | 005/005 | ICW | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-123.030801 | 40.7332 | ETL.8170 | 40906322 | Structure-Wood | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2019-10-30
117671814 | DRUM-SUMMIT#2 13/155R RPL POLE | 31498154 | DRUM-SUMMIT #2 | 013/155 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-120.563451 | 39.3252 | ETL.1450 | 44561486 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS erdy | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  | Yes
117671816 | DRUM-SUMMIT#2 15/176 RPL POLE | 31521945 | DRUM-SUMMIT #2 | 015/176 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-120.537147 | 39.3098 | ETL.1450 | 44558996 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
117672055 | DRUM-SUMMIT#2 13/155C RPL POLE | 31498154 | DRUM-SUMMIT #2 | 013/155 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-120.563451 | 39.3252 | ETL.1450 | 44561342 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS erdy | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  | Yes
117672056 | DRUM-SUMMIT#2 14/164 RPL POLE | 31521945 | DRUM-SUMMIT #2 | 014/164 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-120.550965 | 39.318 | ETL.1450 | 44561377 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
117672440 | DRUM-SUMMIT#2 15/176 RPL POLE | 31521945 | DRUM-SUMMIT #2 | 015/176 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-120.537147 | 39.3098 | ETL.1450 | 44558938 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
117672474 | EI MORAGA-OAKLAND 5-37 RPR INSS | 44371832 | MORAGA-OAKLAND #3 | 005/037 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  |  | LATE | Central | Non-WSIP | FSRP | [5 empty] | '-122.226863 | 37.8069 | ETL.2740 | 40828536 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - 9
117672477 | T3 EI MORAGA-OAKLAND #2 0/2 RPL HRDs | 44303393 | MORAGA-OAKLAND #2 | 000/002 | ICS | E | Pre-2020_(5) TD tag on other lines |  |  | Likely MAT error - delink to correct | TR3 | LATE | Central | WSIP | [6 empty] | '-122.166133 | 37.8478 | ETL.2730 | 40728506 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  | Y - Prog Multi
117673090 | DRUM-SUMMIT#2 17/204 RPL POLE | 31521949 | DRUM-SUMMIT #2 | 017/204 | 70Y | E | Pre-2020_(1b) Lines with special commitments |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-120.498895 | 39.3143 | ETL.1450 | 44557737 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
117673232 | T3 PARADISE TABLE MTN 16/134L RPL POLE | 31461179 | PARADISE-TABLE MTN | 016/134 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR3 | LATE | North Valley | Non-WSIP | [6 empty] | '-121.499399 | 39.6792 | ETL.4316 | 44552419 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain
117697271 | T2 TRINITY-MAPLE CRK 20/8 RMV POLE BUTT | 44299848 | TRINITY-MAPLE CREEK | 020/008 | ICW | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.276437 | 40.7169 | ETL.8170 | 40873263 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2019-11-14
117697715 | NT EI LAS POSITAS-NEWARK 12/81 PNT TWR | 43753291 | LAS POSITAS-NEWARK | 012/081 | ICS | F | Pre-2020_(9a) Other ignition related | [5 empty] | Central | WSIP | [6 empty] | '-121.868653 | 37.5734 | ETL.4980 | 40604725 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay
117697719 | NT EI TESLA-NEWARK #2 19/128 PNT TWR | 43753285 | TESLA-NEWARK #2 | 019/128 | ICS | F | Pre-2020_(9a) Other ignition related | [5 empty] | Central | WSIP | [6 empty] | '-121.868441 | 37.5733 | ETL.5354 | 41152674 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay
117698565 | T2 TRINITY-MAPLE CREEK 10/6 RMV PL BUTT | 44299848 | TRINITY-MAPLE CREEK | 010/006 | ICW | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.097229 | 40.7669 | ETL.8170 | 40906400 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2019-10-30
117700453 | T2 TRINITY-MAPLE CREEK 16/6 REPL POLE | 31471998 | TRINITY-MAPLE CREEK | 016/006 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.202233 | 40.7399 | ETL.8170 | 40810476 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2019-11-14
117700495 | T2 TRINITY-MAPLE CREEK 9/004 RMV PL BUTT | 43749708 | TRINITY-MAPLE CREEK | 009/004 | ICW | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.076825 | 40.7661 | ETL.8170 | 40906382 | Structure-Wood | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2019-10-23
117707071 | T2 Eagle Rock/Redbud 026/125 RPL SWTCH |  | MENDOCINO-REDBUD | 026/125 | 93S | E | Pre-2020_(2) High fire spread TD |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-122.661419 | 39.0292 | ETL.2410 | 41119845 | Switch-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 435 | Lakeville |  |  | 2019-09-13
117708697 | EI LAS POSITAS-NEWARK 12/83 REPAINT | 43753291 | LAS POSITAS-NEWARK | 012/083 | ICS | F | Pre-2020_(9a) Other ignition related | [5 empty] | Central | Non-WSIP | [6 empty] | '-121.875144 | 37.5661 | ETL.4980 | 40661097 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay
117709065 | EI GREEN VALLEY-LLAGAS :010/070 REPAINT | 43766025 | GREEN VALLEY-LLAGAS | :010/070 | ICS | F | Pre-2020_(9a) Other ignition related | [5 empty] | South | Non-WSIP | [6 empty] | '-121.651331 | 37.1038 | ETL.1720 | 40589047 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Moss Landing |  | Y - 10
117710060 | EI DIABLO-GATES #1 7/33 PNT TWR | 43756059 | DIABLO-GATES #1 | 007/033 | ICS | F | Pre-2020_(9a) Other ignition related | [5 empty] | South | WSIP | [6 empty] | '-120.80207 | 35.298 | ETL.5960 | 40651918 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Pismo Beach
117710837 | NT EI METCALF-MOSS LND #1 26/111 PNT TWR | 43910751 | METCALF-MOSS LANDING #1 | 026/111 | ICS | F | Pre-2020_(9a) Other ignition related | [5 empty] | South | WSIP | [6 empty] | '-121.737849 | 37.2255 | ETL.5100 | 40587029 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Moss Landing
117712709 | T3 EI MIDDLE FORK-GLD HLL 2/027 RPL STRW | 31454603 | MIDDLE FORK-GOLD HILL | 002/027 | 70Y | E | Pre-2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP |  |  |  |  | Material & Equipment | 2021 - Due to Long lead material delay | '-120.6282 | 39.0004 | ETL.5140 | 44552528 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento
117713813 | EI COALINGA #1-SAN MIGUL 15/5 REPNT MEMB | 44301011 | COALINGA #1-SAN MIGUEL | 015/005 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  |  | LATE | South | WSIP | [6 empty] | '-120.53864 | 36.0081 | ETL.8580 | 40754810 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Pismo Beach |  | Y - 15
117714165 | EI LAS POSITAS-NEWARK 14/091 PAINT STRT | 43753291 | LAS POSITAS-NEWARK | 014/091 | ICS | F | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) |  |  |  |  | Central | Non-WSIP | [6 empty] | '-121.891631 | 37.548 | ETL.4980 | 40590657 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay
117715706 | T3 EI SNEATH LANE-HMB ?010/2 WASH INSW |  | SNEATH LANE-HALF MOON BAY | ?010/002 | ICD | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.424481 | 37.4906 | ETL.7212 | 40695077 | Insulator | Contaminated | Ground Wash |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 622 | Bay |  | Y - 29
117715707 | T3 DI SNTH LN-HMB ?010/3 GRND WASH INSW |  | SNEATH LANE-HALF MOON BAY | ?010/003 | ICD | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.423577 | 37.4891 | ETL.7212 | 40656253 | Insulator | Contaminated | Ground Wash |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 622 | Bay |  | Y - 29
117715761 | T2 EI MELONES-CURTIS 9/4 RPR POLE | 44392489 | MELONES-CURTIS | 009/004 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.401446 | 37.944 | ETL.2390 | 44391167 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 12
117715766 | T2 EI MELONES-CURTIS 10/6 RPL POLE | 31462761 | MELONES-CURTIS | 010/006 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.384587 | 37.953 | ETL.2390 | 44391219 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC erdy srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 12
117715783 | T2 EI MELONES-CURTIS 9/5 RPL POLE | 31462760 | MELONES-CURTIS | 009/005 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.399508 | 37.945 | ETL.2390 | 44391192 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC erdy srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 12
117715786 | T2 EI MELONES-CURTIS 13/6 RPL POLE | 31462763 | MELONES-CURTIS | 013/006 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.337952 | 37.9698 | ETL.2390 | 44391226 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC erdy srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 12
117715789 | T2 EI MELONES-CURTIS 12/1 RPL POLE | 31462762 | MELONES-CURTIS | 012/001 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.362702 | 37.9622 | ETL.2390 | 44391034 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC erdy srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 12
117715797 | T2 DI HAT CREEK #1 WSTWD 7/140 RPL STRW | 31471016 | HAT CREEK #1-WESTWOOD | 007/140 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.423578 | 40.8886 | ETL.7030 | 40668057 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
117715920 | T2 CARIBOU #2 014/011 RPL POLE | 31519914 | CARIBOU #2 | 014/011 | 70Y | E | Pre-2020_(2) High fire spread TD |  |  |  | TR2 | LATE | North Valley | Non-WSIP |  |  |  |  | Access Issues | 2021 - Tag was created to stub pole and location was inaccessible for stubbing equp. Tag converted from GAR to 70Y. FSR 12/2020 | '-121.122393 | 40.0266 | ETL.6280 | 40600614 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
117717945 | EI TESLA-NEWARK #2 22/142 INST HRDT |  | TESLA-NEWARK #2 | 022/142 | ICQ | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  |  | LATE | Central | Non-WSIP | [6 empty] | '-121.895011 | 37.5411 | ETL.5354 | 40870328 | Hardware-Tower | Missing | Install |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 8
117721321 | T3 DRUM-RIO OSO #2 005/059A INST LADDERS | 43937827 | DRUM-RIO OSO #2 | 005/059A | ICS | F | Pre-2020_(9a) Other ignition related |  |  |  | TR3 | LATE | North Valley | Non-WSIP | [6 empty] | '-120.850634 | 39.216 | ETL.1430 | 40576825 | Hardware-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes
117721358 | T2 EI CLAY-MARTEL 32/492 RPL POLE | 31461360 | CLAY-MARTEL | 032/492 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.842849 | 38.4595 | ETL.8250 | 40904096 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 33
117722378 | T2 DI CARIBOU-PALERMO :20/170 RPR FOND | 44069454 | CARIBOU-PALERMO | :020/170 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.363578 | 39.8908 | ETL.3190 | 40642282 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
117722443 | T2 DI CARIBOU-PALERMO :14/118 RMV SOIL |  | CARIBOU-PALERMO | :014/118 | ICS | E | Pre-2020_(3) On high spread structure |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.304514 | 39.949 | ETL.3190 | 40738823 | Structure-Steel | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain
117723283 | DI PALERMO-WYANDOTTE 1/14 RMV DEBRIS | 43952544 | PALERMO-WYANDOTTE | 001/014 | ICS | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-121.539627 | 39.4704 | ETL.4315 | 40757545 | Structure-Steel | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain
117723286 | DI PALERMO-WYANDOTTE 1/14 INST MRKS | 43952544 | PALERMO-WYANDOTTE | 001/014 | ICS | F | Pre-2020_(5b) On structure in bucket 5 | [5 empty] | North Valley | WSIP | [6 empty] | '-121.539627 | 39.4704 | ETL.4315 | 40757545 | Marker (i.e. signs)-Steel | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain
117723288 | DI PALERMO-WYANDOTTE 1/14 RPL INSS | 31462731 | PALERMO-WYANDOTTE | 001/014 | 93K | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-121.539638 | 39.4678 | ETL.4315 | 40787574 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain
117723827 | T2 EI MELONES-CURTIS 12/5 RPL POLE | 31462766 | MELONES-CURTIS | 012/005 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.355756 | 37.9652 | ETL.2390 | 44391175 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC erdy srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 12
117723837 | T2EI MELONES-CURTIS 12/2 RPL POLE | 31462765 | MELONES-CURTIS | 012/002 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | Non-WSIP | [6 empty] | '-120.360319 | 37.9632 | ETL.2390 | 44391080 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC erdy srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 12
117724468 | T2 EI MELONES-CURTIS 11/0 REFRAME | 31483848 | MELONES-CURTIS | 011/000 | 93E | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [8 empty] | ETL.2390 | 44391007 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Victor |  | Y - Multi
117725507 | T2 OCNO-CALLNDR SW ST 020/132 RPR GYWW | 44391517 | OCEANO-CALLENDAR SW STA | 020/132 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.57673 | 35.0964 | ETL.2394 | 40652046 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - 7
117725787 | T2 COBURN-PANOCHE 041/176 RPR FOND | 43930664 | COBURN-PANOCHE | 041/176 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | South | Non-WSIP | [6 empty] | '-121.0742767 | 36.6654 | ETL.4460 | 40959338 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Moss Landing |  | Y - Prog Multi
117727313 | EI PEASE-HARTER A014/308 RPR ANCW | 43932090 | PEASE-HARTER | A014/308 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-121.907684 | 39.145 | ETL.7760 | 40874304 | Anchor-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117728905 | T2 DI BLLT-RVRBK-MLNS SWS :09/1 RPL STRW | 31509462 | BELLOTA-RIVERBANK-MELONES SW STA | :009/001 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.639239 | 37.8769 | ETL.1070 | 40580431 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 7
117730044 | T2 DI HAAS-MCCALL 000/006 RPL INSS | 44299317 | HAAS-MCCALL | 000/006 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-119.0313 | 36.9224 | ETL.4850 | 40805256 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  | Y - 11
117730290 | T3 MIDDLE FORK-GOLD HILL 0/6L RPL POLE | 31454603 | MIDDLE FORK-GOLD HILL | 000/006 | 70Y | E | Pre-2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | Non-WSIP |  |  |  |  | Material & Equipment | 2021 - Due to Long lead material delay | '-120.598509 | 39.018 | ETL.5140 | 44552438 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento
117732227 | T2 DI VOLTA-SOUTH 4/106 RPR GYWW | 44309963 | VOLTA-SOUTH | 004/106 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.878408 | 40.3955 | ETL.8300 | 40868025 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117732252 | T2 DI VOLTA-SOUTH 4/106 RPR STRW | 44309963 | VOLTA-SOUTH | 004/106 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.878408 | 40.3955 | ETL.8300 | 40868025 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117732287 | EI PITTSBURG-SAN RAMON 002/015 REPAINT | 44586175 | PITTSBURG-SAN RAMON | 002/015 | ICX | F | Pre-2020_(9a) Other ignition related |  |  | Likely MAT error - delink to correct |  |  | Central | Non-WSIP | [6 empty] | '-121.908141 | 38.0019 | ETL.5490 | 40761606 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense |  | Bay
117733042 | EI PITTSBURG-TESLA #1 017/077 RPR FOND | 43753186 | PITTSBURG-TESLA #1 | 017/077 | ICQ | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | Central | Non-WSIP | [6 empty] | '-121.711114 | 37.8826 | ETL.5510 | 40810220 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 5
117733057 | EI PITTSBURG-TESLA #1 017/077 INS ACLG | 31494705 | PITTSBURG-TESLA #1 | 017/077 | 93A | F | Pre-2020_(5b) On structure in bucket 5 | [5 empty] | Central | Non-WSIP | [6 empty] | '-121.711114 | 37.8826 | ETL.5510 | 40810220 | Structure-Tower | Anti-Climbing Guard | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Capital | 988 | Bay |  | Y - 5
117733132 | T3 MORAGA-OAKLAND #3 000/005 RPL STRT | 31484160 | MORAGA-OAKLAND #3 | 000/005 | 70S | E | Pre-2020_(2) High fire spread TD |  |  |  | TR3 | LATE | Central | Non-WSIP |  |  |  | REJECT: Long text calls for Tower Replacement, Field notes from crew state they inspected tower, This notification is for replacing the tower. Please resubmit once tower has been replaced. | Project | 2021- Late due to project not being funded for 2020 | '-122.170315 | 37.8466 | ETL.2740 | 40764476 | Structure-Tower | No Good/Out of Stdrd | Replace | POST | POST | POST Estimate | Not Complete | PEND | LC | TLQ | Pole Program | Capital | 426 | Bay |  | Y - 9
117733163 | T2 DI CSCD-BNTN-DSCHUTS A007/148 RPR PL | 43690811 | CASCADE-BENTON-DESCHUTES | A007/148 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.266714 | 40.5699 | ETL.6310 | 40759470 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117733166 | T2 DI CSCD-BNTN-DSCHUTS A008/163 RPR PL | 43962090 | CASCADE-BENTON-DESCHUTES | A008/163 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.26014 | 40.5605 | ETL.6310 | 40810350 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117733314 | EI T2 DRM-SMMT #2_023/279 RPL GYM TAPE | 43947604 | DRUM-SUMMIT #2 | 023/279 | ICS | F | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | WECC | North Valley | Non-WSIP | [6 empty] | '-120.386811 | 39.3284 | ETL.1450 | 44565808 | Guy Wire Mark /Indic-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento |  |  | Yes
117733454 | T2NT DI MNDC-WLT-FT BRAG 37/004 INS MRKW |  | MENDOCINO-WILLITS-FORT BRAGG | 037/004 | ICW | F | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.718406 | 39.4012 | ETL.7550 | 40769239 | Marker (i.e. signs)-Wood | Missing | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
117743508 | EI SBRNT-GRZL-CLRMNT #1 3/33 PNT STRT | 44586187 | SOBRNTE-GRIZZLY-CLARMNT #1+ | 003/033 | ICS | F | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) |  |  |  |  | Central | Non-WSIP | [6 empty] | '-122.176491 | 37.8649 | ETL.3740 | 40607957 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay
117745284 | T3 DI CARIBOU-PALERMO :007/058 RPR INSS | 44304495 | CARIBOU-PALERMO | :007/058 | ICS | E | Pre-2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | FSRP |  |  |  | Field Operations |  | '-121.227908 | 40.0074 | ETL.3190 | 44399888 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain
117745286 | T3 DI CARIBOU-PALERMO :007/058 RPR STUBS | 44059014 | CARIBOU-PALERMO | :007/058 | ICQ | E | Pre-2020_(3) On high spread structure |  |  |  | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations | Circuit Based Scheduling | '-121.227908 | 40.0074 | ETL.3190 | 40910300 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
117745288 | T3 DI CARIBOU-PALERMO :07/058 RMV DEBRIS | 44070463 | CARIBOU-PALERMO | :007/058 | ICS | E | Pre-2020_(3) On high spread structure |  |  |  | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.227908 | 40.0074 | ETL.3190 | 40910300 | Structure-Steel | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain
117745312 | T2 EI PARADISE-TABLE MTN 20/160 RPL ANCS | 31519801 | PARADISE-TABLE MTN | 020/160 | 93E | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.564124 | 39.6878 | ETL.4316 | 44712240 | Anchor-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain
117745313 | T2 EI PARADISE-TABLE MTN 20/160 RPL ANCS | 31519801 | PARADISE-TABLE MTN | 020/160 | 93E | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.564124 | 39.6878 | ETL.4316 | 44712241 | Anchor-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain
117745363 | T3NT DI CARIBOU-PALERMO :07/57 INST HRDS | 44304825 | CARIBOU-PALERMO | :007/057 | ICS | F | Pre-2020_(3) On high spread structure |  |  |  | TR3 |  | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.226794 | 40.0078 | ETL.3190 | 40910299 | Hardware-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain
117745874 | EI SOBRANTE-MORAGA 001/015 REPAINT | 44586184 | SOBRANTE-MORAGA | 001/015 | ICS | F | Pre-2020_(5b) On structure in bucket 5 | Budget Owner (Paint) |  |  |  |  | Central | Non-WSIP | [6 empty] | '-122.189352 | 37.8874 | ETL.3742 | 41135458 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay
117745972 | T2 DI CARIBOU-PALERMO :026/212 RPR FOND | 44069454 | CARIBOU-PALERMO | :026/212 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.42118 | 39.8307 | ETL.3190 | 40674984 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
117745978 | T3 EI PARADISE-TABLE MTN 22/173 RPL ANCS | 31519801 | PARADISE-TABLE MTN | 022/173 | 93E | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR3 | LATE | North Valley | WSIP |  |  |  |  | Internal Process | Circuit Based Scheduling | '-121.606593 | 39.6948 | ETL.4316 | 44712233 | Anchor-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  | Yes
117746323 | T3 EI PARADISE-TABLE MTN 21/167 RPL GYWS | 43939113 | PARADISE-TABLE MTN | 021/167 | ICS | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.591285 | 39.6921 | ETL.4316 | 44712237 | Guy Wire-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117746324 | T2 DI VOLTA-DESCHUTES 019/430 RPR GYWW | 43939089 | VOLTA-DESCHUTES | 019/430 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.216505 | 40.5497 | ETL.8290 | 40667427 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117746944 | T3 EI PARADISE-TABLE MTN 22/173 CANCEL | 31519801 | PARADISE-TABLE MTN | 022/173 | 93E | E | Pre-2020_(5) TD tag on other lines |  |  | CANCEL/CNCL | TR3 | LATE | North Valley | WSIP |  |  |  |  | Internal Process | Circuit Based Scheduling | '-121.606593 | 39.6948 | ETL.4316 | 44712231 | Anchor-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  | Yes
117747655 | T3 EI PARADISE-TABLE MTN 21/167 RPL GYWS | 43939113 | PARADISE-TABLE MTN | 021/167 | ICS | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.591285 | 39.6921 | ETL.4316 | 44712238 | Guy Wire-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117747756 | T3 EI PARADISE-TABLE MTN 21/167 RPL GYWS | 43939113 | PARADISE-TABLE MTN | 021/167 | ICS | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.591285 | 39.6921 | ETL.4316 | 44712236 | Guy Wire-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117751614 | T3 DI CARIBOU-PALERMO :7/59 RPR FOND | 44059014 | CARIBOU-PALERMO | :007/059 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations | Priority Bucket 9 | '-121.230422 | 40.0064 | ETL.3190 | 40910301 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
117752587 | T2 DI MNCN-WLLTS-FRT BRG 37/4 RPR JUMW | 44283900 | MENDOCINO-WILLITS-FORT BRAGG | 037/004 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.718406 | 39.4012 | ETL.7550 | 40769239 | Jumper-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
117754468 | DI ROUND MTN-TBL MTN #2 73/300 INST GMKS | 44305720 | ROUND MTN-TABLE MTN #2 | 073/300 | ICS | F | Pre-2020_(4b) On structure in bucket 4 | [5 empty] | North Valley | WSIP | [6 empty] | '-121.757757 | 39.7589 | ETL.6070 | 40602996 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain
117755224 | T2NT DI CARIBOU-PALERMO :00/01 INST MRKS |  | CARIBOU-PALERMO | :000/001 | ICS | F | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.147281 | 40.0864 | ETL.3190 | 41162785 | Marker (i.e. signs)-Steel | Missing | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain
117755301 | T2 FORT BRAGG-ELK 14/8A RPL INSS | 31490902 | FORT BRAGG-ELK | 014/008A | 93K | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.786747 | 39.311 | ETL.2060 | 40577238 | Insulator-Steel | No Good/Out of Stdrd | Replace | DOCC srdy | DOCC | Job has been constructed (documentation) | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Lakeville
117761621 | LOS BANOS-MIDWAY #2 072/304 RPR SPLS | 43974863 | LOS BANOS-MIDWAY #2 | 072/304 | ICS | E | Pre-2020_(1b) Lines with special commitments |  | DLFL once tag is confirmed complete PM | Email CIRT when complete |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.209626 | 36.2458 | ETL.6010 | 40753988 | Splice-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  | Y - Prog Multi
117762000 | T2 DI BLT-RVRBNK-MLNS SS :5/2 RMV NEST | 43938937 | BELLOTA-RIVERBANK-MELONES SW STA | :005/002 | ICW | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-120.569427 | 37.8874 | ETL.1070 | 44727555 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 7
117762452 | EI HUMBOLDT-TRINITY 112/5 CANCEL | 31470672 | HUMBOLDT-TRINITY | 112/005 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  | CANCEL/CNCL |  | LATE | North Coast | Non-WSIP | [6 empty] | '-124.088591 | 40.7763 | ETL.1820 | 44560586 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2020-05-21
117768126 | T3 KILARC-CEDAR CREEK 6/138 RPR SPLW | 43939119 | KILARC-CEDAR CREEK | 006/138 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | Non-WSIP | [6 empty] | '-121.98035 | 40.7109 | ETL.7290 | 40617662 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117769453 | LOS BANOS-MIDWAY#2 41/173 RPL INSS | 31455040 | LOS BANOS-MIDWAY #2 | 041/173 | 93K | E | Pre-2020_(1b) Lines with special commitments | Director approved | DLFL once tag is confirmed complete PM | Email CIRT when complete |  | LATE | South | Non-WSIP | [6 empty] | '-120.586538 | 36.5718 | ETL.6010 | 40651937 | Insulator-Steel | No Good/Out of Stdrd | Replace | CONS | CONS | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 23
117769455 | LOS BANOS-MIDWAY#2 51/214 BENT STL | 44300848 | LOS BANOS-MIDWAY #2 | 051/214 | ICQ | E | Pre-2020_(1b) Lines with special commitments |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.462157 | 36.4793 | ETL.6010 | 40753976 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 26
117769901 | T2 DI ST-ML SW ST-MN #1 10/63 PNT STRT | 43939154 | STANISLAUS-MELONES SS-MANTECA #1+ | 010/063 | ICS | F | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) |  |  | TR2 |  | Central | WSIP | [6 empty] | '-120.528849 | 38.0615 | ETL.3830 | 40654276 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - Prog Multi
117770100 | MAPLE CREEK-HOOPA 27/011 RMV VEGN | 44311201 | MAPLE CREEK-HOOPA | 027/011 | ICW | E | Pre-2020_(9a) Other ignition related |  |  | Likely veg |  | LATE | North Coast | Non-WSIP | [6 empty] | '-123.67229 | 41.0436 | ETL.7490 | 40586872 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
117773530 | EI VASONA-METCALF 6/29 INSTL ACG |  | VASONA-METCALF | 006/029 | 93A | F | Pre-2020_(5b) On structure in bucket 5 | [5 empty] | Central | Non-WSIP | [6 empty] | '-121.853873 | 37.2294 | ETL.5932 | 40862837 | Structure-Tower | Anti-Climbing Guard | Install |  |  |  |  | PEND | LC | TLQ | Tower | Capital | 988 | Bay |  | Y - Prog Multi
117773558 | EI VASONA-METCALF 6/029 RPR STRT |  | VASONA-METCALF | 006/029 | ICQ | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | Central | Non-WSIP | [6 empty] | '-121.853873 | 37.2294 | ETL.5932 | 40862837 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 1
117773752 | T3 MIDDLE FORK-GOLD HILL 7/63A REPL PL | 31454603 | MIDDLE FORK-GOLD HILL | 007/063A | 70Y | E | Pre-2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | Non-WSIP |  |  |  |  | Material & Equipment | 2021 - Due to Long lead material delay | '-120.716065 | 39.0032 | ETL.5140 | 40656767 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento
117773761 | T3 MIDDLE FORK-GOLD HILL 7/63B REPL PL | 31454603 | MIDDLE FORK-GOLD HILL | 007/063B | 70Y | E | Pre-2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | Non-WSIP |  |  |  |  | Material & Equipment | 2021 - Due to Long lead material delay | '-120.716038 | 39.0033 | ETL.5140 | 42569829 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento
117773762 | T3 MIDDLE FORK-GOLD HILL 7/63C REPL PL | 31454603 | MIDDLE FORK-GOLD HILL | 007/063C | 70Y | E | Pre-2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | Non-WSIP |  |  |  |  | Material & Equipment | 2021 - Due to Long lead material delay | '-120.716011 | 39.0033 | ETL.5140 | 42569831 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento
117776550 | LOS BANOS-MIDWAY #2 051/215 RPL INSS | 31455040 | LOS BANOS-MIDWAY #2 | 051/215 | 93K | E | Pre-2020_(1b) Lines with special commitments | Director approved | DLFL once tag is confirmed complete PM | Email CIRT when complete |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.459327 | 36.4764 | ETL.6010 | 40762145 | Insulator-Steel | No Good/Out of Stdrd | Replace | CONS | CONS | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 23
117776653 | LOS BANOS-GATES #1 053/226 INS HRDT | 44300851 | LOS BANOS-GATES #1 | 053/226 | ICQ | E | Pre-2020_(1b) Lines with special commitments |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.433131 | 36.4479 | ETL.6000 | 40815948 | Hardware-Tower | Missing | Install | CLSD | CLSD | Closed | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 17
117776936 | LOS BANOS-MIDWAY #2 042/178 RPL INSS | 31455040 | LOS BANOS-MIDWAY #2 | 042/178 | 93K | E | Pre-2020_(1b) Lines with special commitments | Director approved | DLFL once tag is confirmed complete PM | Email CIRT when complete |  | LATE | South | Non-WSIP | [6 empty] | '-120.570655 | 36.5622 | ETL.6010 | 40863974 | Insulator-Steel | No Good/Out of Stdrd | Replace | CONS | CONS | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 23
117777100 | LOS BANOS-GATES #1 053/224A RPR FOND | 44300851 | LOS BANOS-GATES #1 | 053/224A | ICQ | F | Pre-2020_(1b) Lines with special commitments |  |  |  |  | WECC | South | Non-WSIP | [6 empty] | '-120.435958 | 36.4511 | ETL.6000 | 40576724 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | CLSD | CLSD | Closed | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 17
117777761 | LOS BANOS-MIDWAY#2 41/171 RPL INSS |  | LOS BANOS-MIDWAY #2 | 041/171 | 93K | E | Pre-2020_(1b) Lines with special commitments | Director approved | DLFL once tag is confirmed complete PM | Email CIRT when complete |  | LATE | South | Non-WSIP | [6 empty] | '-120.592915 | 36.5756 | ETL.6010 | 40587748 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 23
117780020 | LOS BANOS-MIDWAY#2 081/343 RPR STRT | 44300848 | LOS BANOS-MIDWAY #2 | 081/343 | ICQ | F | Pre-2020_(1b) Lines with special commitments |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.11652 | 36.1329 | ETL.6010 | 40651958 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 26
117780538 | T2 PARKWAY-MORAGA 7/040 RPR OPGW | 43974750 | PARKWAY-MORAGA | 007/040 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | Non-WSIP | [6 empty] | '-122.233506 | 38.0434 | ETL.5930 | 40752935 | Shield Wire / OPGW-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  | Y - Prog Multi
117780714 | T2 JEFFERSON-HILLSDALE JCT 6/37 CLR RD |  | JEFFERSON-HILLSDALE JCT | 006/037 | CHS | F | Pre-2020_(5b) On structure in bucket 5 | Budget Owner (Veg/Land/Road) |  |  | TR2 |  | Central | Non-WSIP | [6 empty] | '-122.357579 | 37.5278 | ETL.7190 | 40804838 | Road | Brush Fuel | Remove |  |  |  |  | PEND | LC | TLR | Roads | Expense | 932 | Bay |  |  | SFWL
117780796 | LOS BANOS-GATES #1 080/337 RPR FOND | 44300851 | LOS BANOS-GATES #1 | 080/337 | ICQ | F | Pre-2020_(1b) Lines with special commitments |  |  |  |  | WECC | South | Non-WSIP | [6 empty] | '-120.13035 | 36.1484 | ETL.6000 | 40815026 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | CLSD | CLSD | Closed | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - Prog Multi
117782645 | T2 DI POE-RIO OSO 029/191 INS MRKS |  | POE-RIO OSO | 029/191 | ICS | F | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.530297 | 39.575 | ETL.5540 | 40590790 | Marker (i.e. signs)-Steel | No Good/Out of Stdrd | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117783996 | LOS BANOS-GATES #1 080/338 RPR FOND | 44300851 | LOS BANOS-GATES #1 | 080/338 | ICQ | F | Pre-2020_(1b) Lines with special commitments |  |  |  |  | WECC | South | Non-WSIP | [6 empty] | '-120.130005 | 36.148 | ETL.6000 | 40867440 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | CLSD | CLSD | Closed | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 17
117785007 | T2 DI RND MTN-TBL MTN#2 66/275 RPR STRT | 44156941 | ROUND MTN-TABLE MTN #2 | 066/275 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.80417 | 39.8647 | ETL.6070 | 40756153 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
117785143 | T2 DI RND MTN-TBL MTN#2 66/275 INST HV | 44305720 | ROUND MTN-TABLE MTN #2 | 066/275 | ICS | F | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.80417 | 39.8647 | ETL.6070 | 40756153 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain
117785181 | SAN MATEO-MARTIN #6 0/3 RPL INSS | 31475502 | SAN MATEO-MARTIN #6 | 000/003 | 93K | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-122.2414 | 37.3721 | ETL.3590 | 40840835 | Insulator-Steel | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - Prog Multi
117786339 | LOS BANOS-GATES#1 27/118 RPR FOND | 44300851 | LOS BANOS-GATES #1 | 027/118 | ICQ | F | Pre-2020_(1b) Lines with special commitments |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.717215 | 36.7405 | ETL.6000 | 40870042 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | CLSD | CLSD | Closed | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 17
117786653 | T2 DI IGNACIO-SOBRANTE 44/213 RMV NEST | 44598162 | IGNACIO-SOBRANTE | 044/213 | ICS | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-122.201343 | 37.9464 | ETL.4920 | 40658169 | Structure-Steel | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  |  | EBMUD
117786680 | T2 DI STNL-MLN SST-MNTC#1 12/72 RPR FOND | 44460419 | STANISLAUS-MELONES SS-MANTECA #1+ | 012/072 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.560497 | 38.046 | ETL.3830 | 40642829 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - 9
117786945 | CALLENDAR SS-MESA 1/21 RECONDUCT | 31470273 | CALLENDAR SW STA-MESA | 001/021 | 93C | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | South | Non-WSIP | [6 empty] | '-120.570748 | 35.051 | ETL.1210 | 40618576 | Conductor-Wood | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLN | Maintenance | Capital | 638 | Pismo Beach |  | Y - 12
117787255 | LOS BANOS-MIDWAY#2 42/176 ZENA GUARD | 43848355 | LOS BANOS-MIDWAY #2 | 042/176 | ICS | E | Pre-2020_(1b) Lines with special commitments |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.576372 | 36.5656 | ETL.6010 | 40817172 | Raptor Guard-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 593 | Fresno |  | Y - 26
117787550 | LOS BANOS-MIDWAY#2 42/176 RPL INSS |  | LOS BANOS-MIDWAY #2 | 042/176 | 93K | E | Pre-2020_(1b) Lines with special commitments | Director approved | DLFL once tag is confirmed complete PM | Email CIRT when complete |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.57665 | 36.5658 | ETL.6010 | 40845125 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 23
117788588 | T3 EAGLE RK-FULTON-SLVRD 6/29 RPL JUMS | 44074003 | GEYSERS #17-FULTON | 006/029 | IBE | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.79012 | 38.7576 | ETL.4770 | 40888471 | Jumper-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville
117788593 | T3 DI CENTERVLLE-TABLE MTN 2/43 RPR PL | 44408859 | CENTERVILLE-TABLE MTN | 002/043 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.682223 | 39.7555 | ETL.6320 | 40867501 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117788635 | T2 DI SMARTVILLE-MARYSVILLE 0/1 INS HV | 43947944 | SMARTVILLE-MARYSVILLE | 000/001 | ICW | F | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.303381 | 39.2093 | ETL.7980 | 40598936 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
117789338 | T2 EI DRUM-SUMMIT #2 27/326A REPL POLE | 31471241 | DRUM-SUMMIT #2 | 027/326A | 70Y | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.33228 | 39.3122 | ETL.1450 | 40752050 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento
117789489 | LOS BANOS-MIDWAY #2 50/212 RPL INSS | 31455040 | LOS BANOS-MIDWAY #2 | 050/212 | 93K | E | Pre-2020_(1b) Lines with special commitments | Director approved | DLFL once tag is confirmed complete PM | Email CIRT when complete |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.4658578 | 36.483 | ETL.6010 | 40715335 | Insulator-Steel | No Good/Out of Stdrd | Replace | CONS | CONS | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 23
117789600 | LOS BANOS-MIDWAY #2 001/007 RPL INSS | 31455040 | LOS BANOS-MIDWAY #2 | 001/007 | 93K | E | Pre-2020_(1b) Lines with special commitments | Director approved | DLFL once tag is confirmed complete PM | Email CIRT when complete |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-121.007925 | 37.0305 | ETL.6010 | 40841992 | Insulator-Steel | No Good/Out of Stdrd | Replace | CONS | CONS | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 23
117789766 | T2 EI DRUM-SUMMIT #2 27/326C RPL PL | 31471241 | DRUM-SUMMIT #2 | 027/326C | 70Y | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.332213 | 39.3121 | ETL.1450 | 42572857 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento
117793381 | LOS BANOS-MIDWAY#2 25/108 RPL INSS | 31526476 | LOS BANOS-MIDWAY #2 | 025/108 | 93K | E | Pre-2020_(1b) Lines with special commitments | Director approved | DLFL once tag is confirmed complete PM | Email CIRT when complete |  | LATE | South | Non-WSIP | [6 empty] | '-120.745593 | 36.7634 | ETL.6010 | 40896529 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 23
117794063 | LOS BANOS-MIDWAY #2 30/129 INST ACG | 31469966 | LOS BANOS-MIDWAY #2 | 030/129 | 93A | F | Pre-2020_(1b) Lines with special commitments |  |  |  |  | WECC | South | Non-WSIP | [6 empty] | '-120.696705 | 36.7039 | ETL.6010 | 40863645 | Structure-Tower | Anti-Climbing Guard | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Capital | 988 | Fresno |  | Y - 26
117794325 | T3 MAPLE CREEK-HOOPA 22/011 RMV PL BUTT | 44311201 | MAPLE CREEK-HOOPA | 022/011 | ICW | F | Pre-2020_(9a) Other ignition related |  |  |  | TR3 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.640275 | 40.986 | ETL.7490 | 44660734 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
117794331 | T2 DI DRUM-SUMMIT#2 27/326B RPL PL | 31471241 | DRUM-SUMMIT #2 | 027/326B | 70Y | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.332239 | 39.3121 | ETL.1450 | 42572856 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento
117794382 | T3 MAPLE CREEK-HOOPA 021/011 RMV DBR | 44311201 | MAPLE CREEK-HOOPA | 021/011 | ICW | F | Pre-2020_(9a) Other ignition related |  |  |  | TR3 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.641365 | 40.9725 | ETL.7490 | 40586862 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
117794653 | T3 MAPLE CREEK-HOOPA 021/009 RMV DEBRIS | 44311201 | MAPLE CREEK-HOOPA | 021/009 | ICW | E | Pre-2020_(9a) Other ignition related |  |  |  | TR3 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.642194 | 40.9694 | ETL.7490 | 44429888 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
117794994 | T2 DI PIT #1-COTTONWOOD 5/45 RMV NEST | 43879413 | PIT #1-COTTONWOOD | 005/045 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.579854 | 40.9459 | ETL.5390 | 40759512 | Structure-Steel | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain
117795105 | LOS BANOS-MIDWAY #2 035/148 RPL INSS |  | LOS BANOS-MIDWAY #2 | 035/148 | 93K | E | Pre-2020_(1b) Lines with special commitments | Director approved | DLFL once tag is confirmed complete PM | Email CIRT when complete |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.657631 | 36.6408 | ETL.6010 | 40863972 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 23
117795642 | T2 VALLEY SPRINGS #1 000/012 RPL POLE | 31469727 | VALLEY SPRINGS #1 | 000/012 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | Non-WSIP | [6 empty] | '-120.769068 | 38.2081 | ETL.8210 | 40904188 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 23
117808329 | LOS BNS-MDWY#2 035/147 INST HRDS | 43848355 | LOS BANOS-MIDWAY #2 | 035/147 | ICS | E | Pre-2020_(1b) Lines with special commitments |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.660518 | 36.644 | ETL.6010 | 40811493 | Hardware-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Fresno |  | Y - 26
117808519 | T2 DI PIT#1 COTTONWOOD 012/097 RMV NEST | 43879413 | PIT #1-COTTONWOOD | 012/097 | ICS | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.689241 | 40.8905 | ETL.5390 | 40803635 | Structure-Steel | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain
117808604 | DI FULTON-PUEBLO 012/058 GRD WAS INSS | 44306538 | FULTON-PUEBLO | 012/058 | ICD | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | North Coast | WSIP | [6 empty] | '-122.205231 | 38.5097 | ETL.1600 | 40862869 | Insulator | Contaminated | Helicopter Wash | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 626 | Lakeville
117809120 | T2 DI PIT#1 COTTONWOOD 5/46 RMV NEST | 43879413 | PIT #1-COTTONWOOD | 005/046 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.581665 | 40.945 | ETL.5390 | 40803648 | Structure-Steel | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain
117809127 | T3 DI VOLTA-SOUTH 0/3 RPR PL | 43827513 | VOLTA-SOUTH | 000/003 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.866115 | 40.4583 | ETL.8300 | 40667465 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117809212 | T3NT DI VOLTA-SOUTH 0/3 INST MRKW | 43827513 | VOLTA-SOUTH | 000/003 | ICW | F | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.866115 | 40.4583 | ETL.8300 | 40667465 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117812458 | LOS BANOS-GATES#1 079/334 RPR FOND | 44300851 | LOS BANOS-GATES #1 | 079/334 | ICQ | F | Pre-2020_(1b) Lines with special commitments |  |  |  |  | WECC | South | Non-WSIP | [6 empty] | '-120.138045 | 36.1575 | ETL.6000 | 40757925 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | CLSD | CLSD | Closed | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 17
117812538 | LOS BANOS-MIDWAY#2 27/115 INST ACG | 31469966 | LOS BANOS-MIDWAY #2 | 027/115 | 93A | F | Pre-2020_(1b) Lines with special commitments |  |  |  |  | WECC | South | Non-WSIP | [6 empty] | '-120.722139 | 36.7489 | ETL.6010 | 40753892 | Structure-Tower | Anti-Climbing Guard | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Capital | 988 | Fresno |  | Y - 26
117813218 | T3 EI DRUM-RIO OSO#2 1/17 INST ANCS | 31471216 | DRUM-RIO OSO #2 | 001/017 | 93Z | E | Pre-2020_(9a) Other ignition related |  |  |  | TR3 | LATE | North Valley | WSIP | [5 empty] | Priority Bucket 9 | '-120.798755 | 39.256 | ETL.1430 | 40814408 | Anchor-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Capital |  | Sacramento |  |  | Yes
117813491 | T3 EI DRUM-RIO OSO#1 1/17 INST ANCS | 31497813 | DRUM-RIO OSO #1 | 001/017 | 93E | E | Pre-2020_(9a) Other ignition related |  |  | Likely MAT error - delink to correct | TR3 | LATE | North Valley | WSIP | [5 empty] | Priority Bucket 9 | '-120.798822 | 39.2562 | ETL.1420 | 40811218 | Anchor-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Capital |  | Sacramento |  |  | Yes
117813909 | LOS BANOS-MIDWAY #2 035/149 RPL INSS |  | LOS BANOS-MIDWAY #2 | 035/149 | 93K | E | Pre-2020_(1b) Lines with special commitments | Director approved | DLFL once tag is confirmed complete PM | Email CIRT when complete |  | LATE | South | Non-WSIP | [6 empty] | '-120.654745 | 36.6375 | ETL.6010 | 40863647 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 23
117814115 | EI SMARTVILLE-NICOLAUS #2 6/115 RPR CONS | 43947946 | SMARTVILLE-NICOLAUS #2 | 006/115 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | North Valley | Non-WSIP | [6 empty] | '-121.32417 | 39.1273 | ETL.8000 | 44646201 | Conductor-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
117814293 | LOS BANOS-MIDWAY #2 035/147 RPL INSS |  | LOS BANOS-MIDWAY #2 | 035/147 | 93K | E | Pre-2020_(1b) Lines with special commitments | Director approved | DLFL once tag is confirmed complete PM | Email CIRT when complete |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.660518 | 36.644 | ETL.6010 | 40811493 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 23
117814368 | T2 VALLEY SPRINGS-CLAY 6/92 INST RPTR PL | 31471034 | VALLEY SPRINGS-CLAY | 006/092 | 93B | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | Central | Non-WSIP | [6 empty] | '-120.835735 | 38.2184 | ETL.8264 | 40905035 | Raptor Guard-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 672 | Victor |  | Y - 12
117814584 | T3 POE-RIO OSO 19/127 CANCEL | 43737421 | POE-RIO OSO | 019/127 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  | CANCEL/CNCL | TR3 | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-121.48118 | 39.7202 | ETL.5540 | 44383620 | Hardware-Steel | No Good/Out of Stdrd | Replace | DOCC srdy | DOCC | Job has been constructed (documentation) | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117814895 | T2 DRUM-SUMMIT #1 18/218A RPL PL | 31453338 | DRUM-SUMMIT #1 | 018/218A | 70Y | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-120.471139 | 39.3184 | ETL.1440 | 40595348 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento
117814896 | T2 DRUM-SUMMIT #1 18/218B RPL PL | 31453338 | DRUM-SUMMIT #1 | 018/218B | 70Y | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-120.47111 | 39.3183 | ETL.1440 | 42572702 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento
117814909 | T2 DRUM-SUMMIT #1 18/218C RPL PL | 31453338 | DRUM-SUMMIT #1 | 018/218C | 70Y | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-120.471096 | 39.3183 | ETL.1440 | 42572703 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento
117816180 | T2 DI BRCBURG JCT-MARIPOSA 4/15 RPL HRDD | 44301835 | BRICEBURG JCT-MARIPOSA TAP | 004/015 | ICW | F | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | South | WSIP | FSRP | [5 empty] | '-119.985828 | 37.534 | ETL.8651 | 40748170 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Fresno |  | Y - 12
117816289 | LOS BANOS-MIDWAY #2 045/190 RPL HRDT | 44300848 | LOS BANOS-MIDWAY #2 | 045/190 | ICQ | E | Pre-2020_(1b) Lines with special commitments |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.529588 | 36.5358 | ETL.6010 | 40600326 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 26
117816949 | LOS BANOS-MIDWAY#2 36/153 RPL INSS |  | LOS BANOS-MIDWAY #2 | 036/153 | 93K | E | Pre-2020_(1b) Lines with special commitments | Director approved | DLFL once tag is confirmed complete PM | Email CIRT when complete |  | LATE | South | Non-WSIP | [6 empty] | '-120.643683 | 36.6252 | ETL.6010 | 40656930 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 23
117817292 | LOS BANOS-MIDWAY#2 28/120 RPL INSS |  | LOS BANOS-MIDWAY #2 | 028/120 | 93K | E | Pre-2020_(1b) Lines with special commitments | Director approved | DLFL once tag is confirmed complete PM | Email CIRT when complete |  | LATE | South | Non-WSIP | [6 empty] | '-120.713526 | 36.7347 | ETL.6010 | 40600295 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 23
117817296 | LOS BANOS-MIDWAY#2 23/99 RPL INSS |  | LOS BANOS-MIDWAY #2 | 023/099 | 93K | E | Pre-2020_(1b) Lines with special commitments | Director approved | DLFL once tag is confirmed complete PM | Email CIRT when complete |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.777723 | 36.7825 | ETL.6010 | 40863639 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 23
117817298 | T3 DI VOLTA-SOUTH 0/3 RPL CRSW | 31471616 | VOLTA-SOUTH | 000/003 | 93E | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.866115 | 40.4583 | ETL.8300 | 40667465 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  | Yes
117817299 | LOS BANOS-MIDWAY#2 40/170 RPL INSS |  | LOS BANOS-MIDWAY #2 | 040/170 | 93K | E | Pre-2020_(1b) Lines with special commitments | Director approved | DLFL once tag is confirmed complete PM | Email CIRT when complete |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.596147 | 36.5776 | ETL.6010 | 40592924 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 23
117817507 | LOS BNS-GATES#1 46/195 INST CLMBG GUARD | 31480609 | LOS BANOS-GATES #1 | 046/195 | 93A | F | Pre-2020_(1b) Lines with special commitments |  |  |  |  | WECC | South | Non-WSIP | [6 empty] | '-120.514911 | 36.5242 | ETL.6000 | 40758969 | Structure-Tower | Anti-Climbing Guard | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Capital | 988 | Fresno |  | Y - 17
117817539 | LOS BANOS-MIDWAY#2 TWR 34/144 RPL INSS |  | LOS BANOS-MIDWAY #2 | 034/144 | 93K | E | Pre-2020_(1b) Lines with special commitments | Director approved | DLFL once tag is confirmed complete PM | Email CIRT when complete |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.668031 | 36.6527 | ETL.6010 | 40753968 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 23
117817610 | T2 DI PALERMO-COLGATE C001/008 INS MRKS | 43978676 | PALERMO-COLGATE | C001/008 | ICS | F | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.221242 | 39.3196 | ETL.5360 | 40871483 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento
117818503 | LOS BANOS-MIDWAY#2 45/191 INST HRDT | 44300848 | LOS BANOS-MIDWAY #2 | 045/191 | ICQ | E | Pre-2020_(1b) Lines with special commitments |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.525311 | 36.5328 | ETL.6010 | 40587749 | Hardware-Tower | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 26
117819724 | LOS BANOS-GATES #1 075/316 INS SHLD HRDT | 44300851 | LOS BANOS-GATES #1 | 075/316 | ICQ | E | Pre-2020_(1b) Lines with special commitments |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.18186 | 36.2105 | ETL.6000 | 40822824 | Hardware-Tower | Missing | Install | CLSD | CLSD | Closed | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 17
117820552 | T3 MAPLE CREEK-HOOPA 19/10 RMV BUTT | 44311201 | MAPLE CREEK-HOOPA | 019/010 | ICW | E | Pre-2020_(9a) Other ignition related |  |  |  | TR3 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.644742 | 40.9475 | ETL.7490 | 40617823 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
117820602 | T3 MAPLE CREEK-HOOPA 19/9 RMV BUTT | 44311201 | MAPLE CREEK-HOOPA | 019/009 | ICW | E | Pre-2020_(9a) Other ignition related |  |  |  | TR3 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.645365 | 40.9476 | ETL.7490 | 44963391 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
117820920 | LOS BANOS-MIDWAY#2 32/138 RPL INSS |  | LOS BANOS-MIDWAY #2 | 032/138 | 93K | E | Pre-2020_(1b) Lines with special commitments | Director approved | DLFL once tag is confirmed complete PM | Email CIRT when complete |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.679608 | 36.6726 | ETL.6010 | 40863970 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 23
117821397 | T2 DI PIT#1-CTTNWD 42/362 RMV VEGN |  | PIT #1-COTTONWOOD | 042/362 | HNA | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.093226 | 40.6061 | ETL.5390 | 40689979 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Table Mountain
117821633 | LOS BANOS-MIDWAY#2 138/567 REPL INSS | 74008748 | LOS BANOS-MIDWAY #2 | 138/567 | 93K | E | Pre-2020_(1b) Lines with special commitments | Director approved |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.519143 | 35.4829 | ETL.6010 | 40811546 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE idoc idcr |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Midway |  | Y - 26 | CDFW
117821837 | LOS BANOS-MIDWAY#2 33/140 RPL INSS |  | LOS BANOS-MIDWAY #2 | 033/140 | 93K | E | Pre-2020_(1b) Lines with special commitments | Director approved | DLFL once tag is confirmed complete PM | Email CIRT when complete |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.675757 | 36.6656 | ETL.6010 | 40608671 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 23
117821899 | LOS BANOS-MIDWAY #2 027/115 RPL INSS |  | LOS BANOS-MIDWAY #2 | 027/115 | 93K | E | Pre-2020_(1b) Lines with special commitments | Director approved | DLFL once tag is confirmed complete PM | Email CIRT when complete |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.722139 | 36.7489 | ETL.6010 | 40753892 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 23
117821964 | LOS BANOS-MIDWAY #2 044/187 RPL INSS | 31455040 | LOS BANOS-MIDWAY #2 | 044/187 | 93K | E | Pre-2020_(1b) Lines with special commitments | Director approved | DLFL once tag is confirmed complete PM | Email CIRT when complete |  | LATE | South | Non-WSIP | [6 empty] | '-120.540226 | 36.5428 | ETL.6010 | 40818982 | Insulator-Steel | No Good/Out of Stdrd | Replace | CONS | CONS | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 23
117822020 | LOS BANOS-MIDWAY#2 37/155 RPL INSS |  | LOS BANOS-MIDWAY #2 | 037/155 | 93K | E | Pre-2020_(1b) Lines with special commitments | Director approved | DLFL once tag is confirmed complete PM | Email CIRT when complete |  | LATE | South | Non-WSIP | [6 empty] | '-120.638957 | 36.6199 | ETL.6010 | 40753898 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 23
117822093 | LOS BANOS-MIDWAY #2 044/187 INS HRDT | 44300848 | LOS BANOS-MIDWAY #2 | 044/187 | ICQ | E | Pre-2020_(1b) Lines with special commitments |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.540226 | 36.5428 | ETL.6010 | 40818982 | Hardware-Tower | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 26
117822162 | LOS BANOS-MIDWAY #2 045/189 RPL INSS |  | LOS BANOS-MIDWAY #2 | 045/189 | 93K | E | Pre-2020_(1b) Lines with special commitments | Director approved | DLFL once tag is confirmed complete PM | Email CIRT when complete |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.533571 | 36.5385 | ETL.6010 | 40863655 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 23
117822288 | T3 MAPLE CREEK-HOOPA 16/001 RMV BUTT | 44311201 | MAPLE CREEK-HOOPA | 016/001 | ICW | F | Pre-2020_(9a) Other ignition related |  |  |  | TR3 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.699263 | 40.9199 | ETL.7490 | 40602068 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
117824932 | T2 Fulton Calistoga 010/004 RPR SWTCH WD | 43944406 | FULTON-CALISTOGA | 010/004 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-122.578187 | 38.5923 | ETL.6880 | 43242522 | Switch-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
117825720 | T3 MAPLE CREEK-HOOPA 10/12 RMV BUTT | 44311201 | MAPLE CREEK-HOOPA | 010/012 | ICW | E | Pre-2020_(9a) Other ignition related |  |  |  | TR3 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.771116 | 40.8935 | ETL.7490 | 40662154 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
117825752 | LOS BANOS-GATES #1 004/019 RPL BOLT | 44300851 | LOS BANOS-GATES #1 | 004/019 | ICQ | E | Pre-2020_(1b) Lines with special commitments |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.985831 | 36.9973 | ETL.6000 | 40867746 | Hardware-Tower | No Good/Out of Stdrd | Replace | CLSD | CLSD | Closed | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 17
117825759 | LOS BANOS-MIDWAY #2 046/193 RPL INSS | 31455040 | LOS BANOS-MIDWAY #2 | 046/193 | 93K | E | Pre-2020_(1b) Lines with special commitments | Director approved | DLFL once tag is confirmed complete PM | Email CIRT when complete |  | LATE | South | Non-WSIP | [6 empty] | '-120.520415 | 36.5287 | ETL.6010 | 40651941 | Insulator-Steel | No Good/Out of Stdrd | Replace | CONS | CONS | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 23
117825922 | LOS BANOS-MIDWAY #2 045/190 RPL INSS | 31455040 | LOS BANOS-MIDWAY #2 | 045/190 | 93K | E | Pre-2020_(1b) Lines with special commitments | Director approved | DLFL once tag is confirmed complete PM | Email CIRT when complete |  | LATE | South | Non-WSIP | [6 empty] | '-120.529588 | 36.5358 | ETL.6010 | 40600326 | Insulator-Steel | No Good/Out of Stdrd | Replace | CONS | CONS | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 23
117825971 | EI STNSLS-MNTECA #2 12/71 INST CLMB GRD | 31471073 | STANISLAUS-MANTECA #2 | 012/071 | 93A | F | Pre-2020_(4b) On structure in bucket 4 | [5 empty] | Central | Non-WSIP | [6 empty] | '-120.560399 | 38.0459 | ETL.3820 | 40597023 | Structure-Tower | Anti-Climbing Guard | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Capital | 988 | Victor |  | Y - 14
117825982 | EI STANISLAUS-MANTECA #2 12/71 RPR FOND | 44460413 | STANISLAUS-MANTECA #2 | 012/071 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | Central | Non-WSIP | [6 empty] | '-120.560399 | 38.0459 | ETL.3820 | 40597023 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - 14
117835623 | T2 EI BALCH-SANGER 003/025 INS HRDT | 44190547 | BALCH-SANGER | 003/025 | ICQ | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-119.138379 | 36.8798 | ETL.1050 | 40765310 | Hardware-Tower | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 16
117835624 | T2 EI BALCH-SANGER 003/025 RPR STRT | 44139817 | BALCH-SANGER | 003/025 | ICQ | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-119.138379 | 36.8798 | ETL.1050 | 40765310 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 16
117837462 | T2 DI LOS ESTERS-METCLF 22/99 RMV VEGN |  | LOS ESTEROS-METCALF | 022/099 | HNA | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-121.855545 | 37.5229 | ETL.5353 | 40862410 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Bay
117837472 | T2 DI LOS ESTRS-MTCLF 25/107 RMV VEGN |  | LOS ESTEROS-METCALF | 025/107 | HNA | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-121.868393 | 37.5521 | ETL.5353 | 40810199 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Bay
117837522 | T2 DI LOS ESTRS-METCLF 23/101 RMV VEGN |  | LOS ESTEROS-METCALF | 023/101 | HNA | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-121.858978 | 37.5307 | ETL.5353 | 40586608 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Bay
117837987 | T2 DI LOS ESTERS-METCLAF 23/100 RPR FOND |  | LOS ESTEROS-METCALF | 023/100 | ICQ | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-121.856964 | 37.5261 | ETL.5353 | 40590872 | Foundation/Concrete-Tower | Earth Covered Tower | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 4
117838191 | T2 DI CARIBOU-PALERMO :20/168 RPL INSS |  | CARIBOU-PALERMO | :020/168 | 93K | E | Pre-2020_(2) High fire spread TD |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.361944 | 39.8926 | ETL.3190 | 40858943 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain
117838457 | T2 DI EXCHEQUER-YOSEMITE 16/59 REPAINT | 44585956 | EXCHEQUER-YOSEMITE | 016/059 | ICS | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-120.087221 | 37.5865 | ETL.8650 | 40871684 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  | Y - 42
117838814 | T2 DI IGNCO-ALTO-SSLT #1 16/114 RPR GYWW | 44310666 | IGNACIO-ALTO-SAUSALITO #1 | 016/114 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.503941 | 37.8577 | ETL.7160 | 40576349 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
117838819 | T2 DI IGNCO-ALTO-SSLT #1 16/114 WSH INSW | 44310668 | IGNACIO-ALTO-SAUSALITO #1 | 016/114 | ICD | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.503941 | 37.8577 | ETL.7160 | 40576349 | Insulator | Contaminated | Ground Wash | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 622 | Lakeville
117840288 | T2 FULTON-CALISTOGA 10/4 S19 RPR SWITCH | 43944407 | FULTON-CALISTOGA | 010/004 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-122.578072 | 38.5923 | ETL.6880 | 40743693 | Switch-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
117843402 | T3 MAPLE CREEK-HOOPA 015/001 RMV DBR | 44311201 | MAPLE CREEK-HOOPA | 015/001 | ICW | F | Pre-2020_(9a) Other ignition related |  |  |  | TR3 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.708747 | 40.9091 | ETL.7490 | 40586852 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
117844626 | TABLE MTN-PALERMO 010/048 RPR CONS | 44154429 | TABLE MTN-PALERMO | 010/048 | ICS | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | North Valley | Non-WSIP | [6 empty] | '-121.502309 | 39.5069 | ETL.5690 | 40871778 | Conductor-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain
117844892 | T2 KONOCTI-MIDDLETOWN 25/7 RPL POLE | 31471948 | KONOCTI-MIDDLETOWN | 025/007 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-122.685926 | 38.9138 | ETL.6380 | 40808153 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville
117845880 | T2 OLEUM-MARTINEZ 5/034 CHANGE INSULAT | 31484429 | OLEUM-MARTINEZ | 005/034 | 93K | E | Pre-2020_(5) TD tag on other lines |  | Please verify if work was completed uner LC 116802249 |  | TR2 | LATE | Central | Non-WSIP | [6 empty] | '-122.171788 | 38.0136 | ETL.3170 | 40623126 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - Prog Multi
117851982 | T2 MALIN-ROUND MTN #2 93/474 RPL INSS | 31475177 | MALIN-ROUND MTN #2 | 093/474 | 93K | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-121.918783 | 40.8233 | ETL.6020 | 40657568 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain
117852167 | T2 MTN GATE JCT-CASCADE 0/2 RPL SPLW | 43758388 | MTN GATE JCT-CASCADE | 000/002 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-122.309537 | 40.7406 | ETL.7640 | 40576637 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117853986 | LOS BANOS-GATES #1 019/082 CANCEL | 44300852 | LOS BANOS-GATES #1 | 019/082 | ICQ | E | Pre-2020_(1b) Lines with special commitments |  |  | CANCEL/CNCL |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.833344 | 36.8192 | ETL.6000 | 40676062 | Hardware-Tower | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 17
117854771 | T3 MAPLE CREEK-HOOPA 11/1 RMV DBRS | 44311201 | MAPLE CREEK-HOOPA | 011/001 | ICW | E | Pre-2020_(9a) Other ignition related |  |  |  | TR3 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.7711518 | 40.8981 | ETL.7490 | 44815580 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
117854988 | T2 EI CHOWCHILLA-KERCKHOFF 0/3 RPR FOND | 43958150 | CHOWCHILLA-KERCKHOFF | 000/003 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | South | WSIP | FSRP | [5 empty] | '-119.558441 | 37.0916 | ETL.1250 | 40646739 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 17 | BLM
117855073 | MORRO BAY-MESA 0/1 REPAINT | 44300723 | MORRO BAY-MESA | 000/001 | ICS | F | Pre-2020_(9a) Other ignition related | [5 empty] | South | Non-WSIP | [6 empty] | '-120.853705 | 35.3744 | ETL.5290 | 40587100 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Pismo Beach
117855299 | LOS BANOS-MIDWAY #2 027/116 RPL INSS |  | LOS BANOS-MIDWAY #2 | 027/116 | 93K | E | Pre-2020_(1b) Lines with special commitments | Director approved | DLFL once tag is confirmed complete PM | Email CIRT when complete |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.720047 | 36.7467 | ETL.6010 | 40839566 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 24
117855435 | T3 MAPLE CREEK-HOOPA 12/005 BTT CNCL | 44311201 | MAPLE CREEK-HOOPA | 012/005 | ICW | E | Pre-2020_(9a) Other ignition related |  |  | CANCEL/CNCL | TR3 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.75827 | 40.9067 | ETL.7490 | 40770516 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
117855863 | T3 MORAGA-OAKLAND #1 1/9 INS RETAIN WALL |  | MORAGA-OAKLAND #1 | 001/009 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  | TR3 | LATE | Central | Non-WSIP | [6 empty] | '-122.182487 | 37.841 | ETL.2720 | 40857632 | Foundation/Concrete-Tower | Earth Covered Tower | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  | SVRPR
117855868 | T3 MAPLE CREEK-HOOPA 12/11 RMV BUTT | 44311201 | MAPLE CREEK-HOOPA | 012/011 | ICW | E | Pre-2020_(9a) Other ignition related |  |  |  | TR3 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.751572 | 40.9074 | ETL.7490 | 40602067 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
117855971 | LOS BANOS-MIDWAY #2 024/103 RPL INSS | 31526476 | LOS BANOS-MIDWAY #2 | 024/103 | 93K | E | Pre-2020_(1b) Lines with special commitments | Director approved | DLFL once tag is confirmed complete PM | Email CIRT when complete |  | LATE | South | Non-WSIP | [6 empty] | '-120.764055 | 36.7742 | ETL.6010 | 40680823 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 24
117856562 | T2 MAPLE CREEK-HOOPA 16/005 RMV DEBRIS | 44311201 | MAPLE CREEK-HOOPA | 016/005 | ICW | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.690788 | 40.9239 | ETL.7490 | 40770464 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
117857008 | T3 MAPLE CREEK-HOOPA 10/13 RMV BUTT | 44311201 | MAPLE CREEK-HOOPA | 010/013 | ICW | F | Pre-2020_(9a) Other ignition related |  |  |  | TR3 | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-123.770896 | 40.895 | ETL.7490 | 44769635 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
117866031 | T2NT DI CTTNWD-PANORAMA 0/4 INST MRKW | 43881008 | COTTONWOOD-PANORAMA | 000/004 | ICW | F | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.267097 | 40.4029 | ETL.1340 | 40758209 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117866035 | T2 DI CTTNWD-PANORAMA 000/004 RPR GRWW | 43881008 | COTTONWOOD-PANORAMA | 000/004 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.267097 | 40.4029 | ETL.1340 | 40758209 | Ground Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117866766 | T2 DI CARIBOU-PALERMO :0/2 RPR STRS |  | CARIBOU-PALERMO | :000/002 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.149439 | 40.0846 | ETL.3190 | 44188832 | Structure-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain
117868111 | T2 DI TULE-SPRINGVILLE 021/002 RPL PL | 31471491 | TULE-SPRINGVILLE | 021/002 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-118.795542 | 36.1365 | ETL.9040 | 40655107 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Midway |  | Y - 23
117870598 | GATES-MIDWAY 006/025 RPL INSS | 31473303 | GATES-MIDWAY | 006/025 | 93K | E | Pre-2020_(5) TD tag on other lines |  | DLFL once tag is confirmed complete PM 74008740 | Email CIRT when complete |  | LATE | South | WSIP | [6 empty] | '-120.066072 | 36.0729 | ETL.5990 | 40691195 | Insulator-Steel | No Good/Out of Stdrd | Replace | CLSD | CLSD | Closed | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - Prog Multi
117870951 | T3NT DIABLO-MESA X0/1 INS MKBLS | 31514438 | DIABLO-MESA | X000/001 | 93P | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | South | Non-WSIP | [6 empty] | '-120.851119 | 35.2175 | ETL.4620 | 40587023 | FAA Lighting-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 671 | Pismo Beach |  | Y - 12
117871038 | T2 EI CHOWCHILLA-KERCKHOFF 1/2 RPR FOND | 44140481 | CHOWCHILLA-KERCKHOFF | 001/002 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | South | WSIP | FSRP | [5 empty] | '-119.572565 | 37.091 | ETL.1250 | 40652120 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 17
117871139 | T2 EI CHOWCHILLA-KERCKHOFF 1/1 RPR FOND | 44140481 | CHOWCHILLA-KERCKHOFF | 001/001 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | South | WSIP | FSRP | [5 empty] | '-119.570722 | 37.0911 | ETL.1250 | 44327115 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 17
117871277 | T2 PARKWAY-MORAGA 10/059 INSTL ACG | 43683430 | PARKWAY-MORAGA | 010/059 | ICQ | F | Pre-2020_(4b) On structure in bucket 4 |  |  | Likely MAT error - delink to correct | TR2 |  | Central | Non-WSIP | [6 empty] | '-122.23148 | 37.9973 | ETL.5930 | 40763001 | Structure-Tower | Anti-Climbing Guard | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 988 | Bay |  | Y - 9
117871908 | T3 MORRO BAY-DIABLO X4/20 RPR CNDS |  | MORRO BAY-DIABLO | X004/020 | ICS | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR3 | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.8068035 | 35.2479 | ETL.5260 | 44330047 | Conductor-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Pismo Beach |  | Y - 4
117872019 | T3 MORRO BAY-DIABLO X3/19 RPR CNDS |  | MORRO BAY-DIABLO | X003/019 | ICS | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR3 | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.806356 | 35.2443 | ETL.5260 | 44767309 | Conductor-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Pismo Beach |  | Y - 4
117872382 | T3 MORRO BAY-DIABLO X4/21 RPR CNDS | 44498739 | MORRO BAY-DIABLO | X004/021 | ICS | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR3 | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.8073602 | 35.252 | ETL.5260 | 40611783 | Conductor-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Pismo Beach |  | Y - 4
117872557 | T3 DIABLO-MESA X5/23 RPL INSS | 31479418 | DIABLO-MESA | X005/023 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | South | Non-WSIP | [6 empty] | '-120.8083999 | 35.2596 | ETL.4620 | 40686660 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 12
117872597 | T2 DIABLO-MESA X5/24 RPL INSS | 31479418 | DIABLO-MESA | X005/024 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | South | Non-WSIP | [6 empty] | '-120.8099962 | 35.2653 | ETL.4620 | 40782272 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 12
117873529 | LOS BANOS-MIDWAY#2 119/488 INST HRDT | 44284322 | LOS BANOS-MIDWAY #2 | 119/488 | ICQ | F | Pre-2020_(1b) Lines with special commitments |  |  |  |  | LATE | South | WSIP | FSRP | [5 empty] | '-119.714568 | 35.7182 | ETL.6010 | 40870076 | Hardware-Tower | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Midway |  | Y - 26
117874306 | T3 KILARC-CEDAR CREEK 010/226 REFRAME | 31471799 | KILARC-CEDAR CREEK | 010/226 | 93E | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | Non-WSIP | [6 empty] | '-121.970125 | 40.7535 | ETL.7290 | 40759581 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  | Yes
117874872 | T2 DIABLO-MESA X007/032 RPL INSS | 31479418 | DIABLO-MESA | X007/032 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | South | Non-WSIP | [6 empty] | '-120.80426 | 35.2934 | ETL.4620 | 40725429 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 12
117874948 | LOS BANOS-MIDWAY #2 093/388 RPR STRT | 44300848 | LOS BANOS-MIDWAY #2 | 093/388 | ICQ | E | Pre-2020_(1b) Lines with special commitments |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.983152 | 36.015 | ETL.6010 | 40864000 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 26
117875667 | LOS BANOS-MIDWAY #2 088/372 INS DAMS | 43848355 | LOS BANOS-MIDWAY #2 | 088/372 | ICS | E | Pre-2020_(1b) Lines with special commitments |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.042592 | 36.0526 | ETL.6010 | 40664842 | Damper-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  | Y - 26
117876261 | T2NT DI PIT #3-PIT #1 0/0A PAINT TWR | 44586172 | PIT #3-PIT #1 | 000/000A | ICS | F | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.498029 | 40.9917 | ETL.5400 | 41184137 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain
117879845 | DI COTTONWOOD-BENTON#2 0/2 RPR GYWW | 43939217 | COTTONWOOD-BENTON #2 | 000/002 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-122.266115 | 40.3973 | ETL.6650 | 41147732 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117879846 | DI COTTONWOOD-BENTON#2 0/2 INST GMKW | 43939217 | COTTONWOOD-BENTON #2 | 000/002 | ICW | F | Pre-2020_(5b) On structure in bucket 5 | [5 empty] | North Valley | WSIP | [6 empty] | '-122.266115 | 40.3973 | ETL.6650 | 41147732 | Guy Wire Mark /Indic-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117879952 | T3 DI VOLTA-SOUTH 0/1 RPR GYWW | 43827513 | VOLTA-SOUTH | 000/001 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.866227 | 40.4594 | ETL.8300 | 40592377 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117879972 | T2 DI CLAY-MARTEL 032/489 RPL POLE | 31461360 | CLAY-MARTEL | 032/489 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.841814 | 38.4572 | ETL.8250 | 40904099 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 33 | BLM
117880051 | T3 DI VOLTA-SOUTH 0/1 RPR INSW | 43827513 | VOLTA-SOUTH | 000/001 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR3 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.866292 | 40.4594 | ETL.8300 | 40618010 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117880085 | LOS BANOS-MIDWAY#2 097/408 RPLC INSS |  | LOS BANOS-MIDWAY #2 | 097/408 | 93K | E | Pre-2020_(1b) Lines with special commitments | Director approved | DLFL once tag is confirmed complete PM | Email CIRT when complete |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.926875 | 35.9629 | ETL.6010 | 40871735 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 24
117880148 | LOS BANOS-MIDWAY#2 110/455 RPL INSS | 31527043 | LOS BANOS-MIDWAY #2 | 110/455 | 93K | F | Pre-2020_(1b) Lines with special commitments | Director approved | DLFL once tag is confirmed complete PM | Email CIRT when complete |  | WECC | South | Non-WSIP | [6 empty] | '-119.795882 | 35.822 | ETL.6010 | 40764995 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 23
117880361 | LOS BANOS-MIDWAY#2 117/484 RPL INSS |  | LOS BANOS-MIDWAY #2 | 117/484 | 93K | F | Pre-2020_(1b) Lines with special commitments | Director approved |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.72383 | 35.7306 | ETL.6010 | 40793250 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Midway |  | Y - 26
117880616 | GATES-MIDWAY 020/085 RPL INSS | 31473303 | GATES-MIDWAY | 020/085 | 93K | E | Pre-2020_(5) TD tag on other lines |  | DLFL once tag is confirmed complete PM 74008740 | Email CIRT when complete |  | LATE | South | WSIP | [6 empty] | '-119.88914 | 35.9205 | ETL.5990 | 40688341 | Insulator-Steel | No Good/Out of Stdrd | Replace | CLSD | CLSD | Closed | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - Prog Multi
117880617 | GATES-MIDWAY 020/085 TRIM VEGN |  | GATES-MIDWAY | 020/085 | HNA | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  |  | LATE | South | Non-WSIP | [6 empty] | '-119.88914 | 35.9205 | ETL.5990 | 40658397 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Fresno
117880936 | T2 HAT CREEK #1-PIT #1 4/46 REPL CRSW | 31472892 | HAT CREEK #1-PIT #1 | 004/046 | 93E | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-121.550796 | 40.9507 | ETL.7020 | 40600855 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain
117880947 | LOS BANOS-MIDWAY #2 100/418 RPLC INSS |  | LOS BANOS-MIDWAY #2 | 100/418 | 93K | E | Pre-2020_(1b) Lines with special commitments | Director approved | DLFL once tag is confirmed complete PM | Email CIRT when complete |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.902909 | 35.9359 | ETL.6010 | 40894409 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 24
117881763 | T2 EI CORDELIA #2 TAP 004/095 RPL PL | 31472910 | CORDELIA #2 TAP | 004/095 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.174453 | 38.2527 | ETL.8184 | 40665400 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento
117882687 | T2 HELMS-GREGG #1 29/178 INST RPT GUARD | 44301794 | HELMS-GREGG #1 | 029/178 | ICB | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.451899 | 36.9428 | ETL.4870 | 40869772 | Raptor Guard-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 593 | Fresno |  | Y - 13
117883960 | EI DIVIDE-CABRILLO #1 011/136 RPL INSW | 31472118 | DIVIDE-CABRILLO #1 | 011/136 | 93I | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | South | WSIP | [6 empty] | '-120.45284 | 34.6732 | ETL.1380 | 42574031 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Pismo Beach |  | Y - 16
117884417 | LOS BANOS-MIDWAY#2 102/426 RPL INSS |  | LOS BANOS-MIDWAY #2 | 102/426 | 93K | E | Pre-2020_(1b) Lines with special commitments | Director approved | DLFL once tag is confirmed complete PM | Email CIRT when complete |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.880844 | 35.9122 | ETL.6010 | 40839600 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 24
117885327 | LOS BANOS-MIDWAY #2 102/425B RPR GYWS | 44301006 | LOS BANOS-MIDWAY #2 | 102/425B | ICS | E | Pre-2020_(1b) Lines with special commitments |  |  | Tower guy |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.882017 | 35.9139 | ETL.6010 | 40740439 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Fresno |  | Y - 26
117886611 | LOS BANOS-GATES #1 050/213 RPR FOND | 44300852 | LOS BANOS-GATES #1 | 050/213 | ICQ | F | Pre-2020_(1b) Lines with special commitments |  |  |  |  | WECC | South | Non-WSIP | [6 empty] | '-120.464786 | 36.4813 | ETL.6000 | 40656821 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 17
117887835 | EI CORDELIA #2 TAP 004/078 RPL POLE | 31472910 | CORDELIA #2 TAP | 004/078 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | North Valley | Non-WSIP | [6 empty] | '-122.161449 | 38.2535 | ETL.8184 | 40823386 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento
117888472 | T2 EI STNSLS-MLNS SWST-MNTC #1 :3/20 PNT |  | STANISLAUS-MELONES SS-MANTECA #1+ | :003/020 | ICS | F | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) |  |  | TR2 |  | Central | WSIP | [6 empty] | '-120.584325 | 37.9569 | ETL.3830 | 40612628 | Structure-Steel | Paint/Coating | Other |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - Prog Multi
117889129 | T2 EI STNSLS-MLNS SS-MNTC #1 17/108_PNT |  | STANISLAUS-MELONES SS-MANTECA #1+ | 017/108 | ICS | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-120.634408 | 37.9929 | ETL.3830 | 40856462 | Structure-Steel | Paint/Coating | Other |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - Prog Multi
117889282 | EI STNSL-MLNS SS-MNTC 1 - 19/122 RPR FND | 44460800 | STANISLAUS-MELONES SS-MANTECA #1+ | 019/122 | ICQ | F | Pre-2020_(4) TD tag on high spread line | [5 empty] | Central | Non-WSIP | [6 empty] | '-120.659151 | 37.9746 | ETL.3830 | 40579574 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - Prog Multi
117890163 | T3 KILARC-CEDAR CREEK 008/180 RPL POLE | 31475774 | KILARC-CEDAR CREEK | 008/180 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | Non-WSIP | [6 empty] | '-121.992672 | 40.7265 | ETL.7290 | 40617747 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
117890616 | MARTIN-SF AIRPORT 001/014 RPL HRDT | 44579150 | MARTIN-SF AIRPORT | 001/014 | ICQ | B | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) |  |  |  |  | LATE | Central | Non-WSIP | [6 empty] | '-122.408976 | 37.6809 | ETL.2240 | 40779502 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 8 | SMCPD
117890643 | DI IGNACIO-SAN RFL #1 0/1 GRND WASH INSU | 44304493 | IGNACIO-SAN RAFAEL #1 | 000/001 | ICD | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | North Coast | WSIP | [6 empty] | '-122.54015 | 38.0761 | ETL.1850 | 40597447 | Insulator | Contaminated | Ground Wash | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 622 | Lakeville
117890691 | LOS BANOS-MIDWAY #2 048/202 RPLC INSS | 31526476 | LOS BANOS-MIDWAY #2 | 048/202 | 93K | E | Pre-2020_(1b) Lines with special commitments | Director approved | DLFL once tag is confirmed complete PM | Email CIRT when complete |  | LATE | South | Non-WSIP | [6 empty] | '-120.495782 | 36.5099 | ETL.6010 | 40715333 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 24
117890912 | LOS BANOS-GATES #1 048/203 CANCEL | 44300852 | LOS BANOS-GATES #1 | 048/203 | ICQ | E | Pre-2020_(1b) Lines with special commitments |  |  | CANCEL/CNCL |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.493759 | 36.5072 | ETL.6000 | 40656819 | Hardware-Tower | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 17
117892512 | LOS BANOS-MIDWAY #2 048/205 RPLC INSS |  | LOS BANOS-MIDWAY #2 | 048/205 | 93K | E | Pre-2020_(1b) Lines with special commitments | Director approved | DLFL once tag is confirmed complete PM | Email CIRT when complete |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.488231 | 36.5026 | ETL.6010 | 40782758 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 24
117892757 | T2 PALERMO PEASE 1/10 RPR JUMS | 44103306 | CARIBOU-PALERMO | 001/010 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | Non-WSIP |  |  |  |  | Field Operations |  | '-121.542374 | 39.4642 | ETL.3190 | 40599223 | Jumper-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain
117892967 | LOS BANOS-MIDWAY #2 049/206 RPL INSS | 31527043 | LOS BANOS-MIDWAY #2 | 049/206 | 93K | F | Pre-2020_(1b) Lines with special commitments | Director approved | DLFL once tag is confirmed complete PM | Email CIRT when complete |  | WECC | South | Non-WSIP | [6 empty] | '-120.484689 | 36.4995 | ETL.6010 | 40839572 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 24
117893957 | LOS BANOS-MIDWAY #2 105/437 RPR GYWS | 43848355 | LOS BANOS-MIDWAY #2 | 105/437 | ICS | E | Pre-2020_(1b) Lines with special commitments |  |  | Tower guy |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.848334 | 35.8781 | ETL.6010 | 40818987 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Fresno |  | Y - 26
117894167 | T2 EI SPAULDING-SUMMIT 14/466 REFRAME | 31453006 | SPAULDING-SUMMIT | 014/466 | 93E | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.4019 | 39.3286 | ETL.8060 | 40590032 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Sacramento
117894274 | T2 FLTN-CLSTGA 10/4 SWITCH 19 REPL SWTCH | 31472157 | FULTON-CALISTOGA | 010/004 | 93S | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-122.578072 | 38.5923 | ETL.6880 | 40743693 | Switch-Steel | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Maintenance | Capital | 435 | Lakeville
117894361 | T2 FLTN-CLSTGA 10/4 SWITCH 17 REPL SWTCH | 31472157 | FULTON-CALISTOGA | 010/004 | 93S | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-122.578187 | 38.5923 | ETL.6880 | 43242522 | Switch-Steel | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Maintenance | Capital | 435 | Lakeville
117896954 | LOS BANOS-MIDWAY #2 048/204 RPL INSS | 31526476 | LOS BANOS-MIDWAY #2 | 048/204 | 93K | E | Pre-2020_(1b) Lines with special commitments | Director approved | DLFL once tag is confirmed complete PM | Email CIRT when complete |  | LATE | South | Non-WSIP | [6 empty] | '-120.491104 | 36.5056 | ETL.6010 | 40789395 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 24
117897551 | LOS BANOS-GATES#1 50/209 RPR GYWS | 44301004 | LOS BANOS-GATES #1 | 050/209 | ICS | E | Pre-2020_(1b) Lines with special commitments |  |  | Tower guy |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.4757 | 36.4912 | ETL.6000 | 40872601 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Fresno |  | Y - 17
117899355 | T2 EI HUMBOLDT-MAPLE CRK 85/0 REPL ANCW | 31472098 | HUMBOLDT-TRINITY | 085/000 | 93E | E | Pre-2020_(2) High fire spread TD |  |  |  | TR2 | LATE | North Coast | WSIP |  |  |  |  | Project | 2021 HUMBOLDT-TRINITY | '-123.596672 | 40.7118 | ETL.1820 | 44562970 | Anchor-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Eureka
117899435 | T2 EI TESLA-NEWARK #2 20/134 RMV NEST | 44598167 | TESLA-NEWARK #2 | 020/134 | ICS | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-121.875165 | 37.5635 | ETL.5354 | 41152680 | Conductor-Steel | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay
117899617 | T2 RIO DELL JCT-BRDIGEVILLE 29/2 RPL PL | 31472992 | RIO DELL JCT-BRIDGEVILLE | 029/002 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.960114 | 40.4765 | ETL.7850 | 40733677 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2019-12-09
117899618 | T2 DI BRIDGEVLE-COTNWD 83/583L REPL POLE | 31473704 | BRIDGEVILLE-COTTONWOOD | 083/583 | 70Y | E | Pre-2020_(2) High fire spread TD |  |  |  | TR2 | LATE | North Coast | WSIP |  |  |  |  | Weather | AT RISK - weather impacts | '-123.728935 | 40.484 | ETL.1110 | 44424588 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC erdy srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka
117900444 | LOS BANOS-GATES #1 058/245 RPR STRT | 44300852 | LOS BANOS-GATES #1 | 058/245 | ICQ | F | Pre-2020_(1b) Lines with special commitments |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.386038 | 36.3962 | ETL.6000 | 40757866 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 17
117900445 | LOS BANOS-MIDWAY #2 100/419 RPL INSS |  | LOS BANOS-MIDWAY #2 | 100/419 | 93K | E | Pre-2020_(1b) Lines with special commitments | Director approved | DLFL once tag is confirmed complete PM | Email CIRT when complete |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.900484 | 35.9332 | ETL.6010 | 40886147 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 24
117901510 | T2 EI BRDGVILLE-CTTNWD 083/583R RPL STRW | 31473704 | BRIDGEVILLE-COTTONWOOD | 083/583 | 70Y | E | Pre-2020_(2) High fire spread TD |  |  |  | TR2 | LATE | North Coast | Non-WSIP |  |  |  |  | Weather | AT RISK - weather impacts | '-123.728935 | 40.484 | ETL.1110 | 44424589 | Structure-Wood | Rotten | Replace | UNSC erdy srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka
117901674 | LOS BANOS-GATES#1 70/296 BENT MEMB | 44300852 | LOS BANOS-GATES #1 | 070/296 | ICQ | F | Pre-2020_(1b) Lines with special commitments |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.234813 | 36.2647 | ETL.6000 | 40815939 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 17
117902879 | T2 DI KILARC-DESCHUTES A025/532 INS MRKW | 43930440 | KILARC-DESCHUTES | A025/532 | ICW | F | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.286894 | 40.5711 | ETL.7300 | 40772210 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117903693 | T2 DI KILARC-DESCHUTES A025/533 INS MRKW | 43930440 | KILARC-DESCHUTES | A025/533 | ICW | F | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.28782 | 40.5711 | ETL.7300 | 44825413 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117905171 | T3NT EI TGR CRK-VLLY SPRNGS 0/2 RPT STRT | 43878409 | TIGER CREEK-VALLEY SPRINGS | 000/002 | ICS | F | Pre-2020_(9a) Other ignition related |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-120.493319 | 38.4516 | ETL.5790 | 40664027 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - 11
117906871 | LOS BANOS-MIDWAY #2 102/425B RPL INSS | 31527043 | LOS BANOS-MIDWAY #2 | 102/425B | 93K | F | Pre-2020_(1b) Lines with special commitments | Director approved | DLFL once tag is confirmed complete PM | Email CIRT when complete |  | WECC | South | Non-WSIP | [6 empty] | '-119.882142 | 35.9133 | ETL.6010 | 40741309 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 23
117907168 | T2 EI METCALF-EDNVLE #1 003/017 INS MRKS | 44598166 | METCALF-EDENVALE #1 | 003/017 | ICS | F | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-121.794216 | 37.2212 | ETL.2480 | 40819260 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - 3
117907451 | T2 DI SOBRANTE-R #1 004/031 RMV VEGN |  | SOBRANTE-R #1 | 004/031 | HNA | E | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Veg/Land/Road) |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.286632 | 37.9192 | ETL.3770 | 40581013 | Vegetation-Tower | Overgrown | Cage Clearing |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Bay
117907504 | T2 EI METCLF-EDNVLE #1 003/017D RPL HRDS |  | METCALF-EDENVALE #1 | 003/017D | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-121.803579 | 37.2225 | ETL.2480 | 40742457 | Hardware-Tower | Missing | Install |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 3
117908366 | T2 DI MOSS LANDING-METCLF 12/59 RPR FOND | 44113810 | MOSS LANDING-METCALF | 012/059 | ICQ | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | South | WSIP | FSRP | [5 empty] | '-121.652183 | 36.9302 | ETL.6050 | 40863484 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Moss Landing
117908367 | T2 DI MSS LNDNG-METCLF 12/59 RPR ANC FND | 44113810 | MOSS LANDING-METCALF | 012/059 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | South | WSIP | FSRP | [5 empty] | '-121.652183 | 36.9302 | ETL.6050 | 40863484 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Moss Landing
117908447 | T2NT DI RND MT-CTNWD#3 41/345 PAINT STRS | 43755801 | ROUND MTN-COTTONWOOD #3 | 041/345 | ICQ | F | Pre-2020_(4b) On structure in bucket 4 |  |  | Likely MAT error - delink to correct | TR2 |  | North Valley | WSIP | [6 empty] | '-122.078079 | 40.6246 | ETL.5650 | 40758852 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain
117908449 | T2 DI ROUND MTN-CTNWD #3 41/345 RPL INSS | 31454792 | ROUND MTN-COTTONWOOD #3 | 041/345 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-122.078079 | 40.6246 | ETL.5650 | 40788172 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain
117908857 | T2 DIABLO-MESA 009/041 RPL INSS | 31479418 | DIABLO-MESA | 009/041 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.7353612 | 35.2932 | ETL.4620 | 40623551 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 12
117909233 | T2 HUMBOLDT-TRINITY 074/002 INS DAMW | 44311171 | HUMBOLDT-TRINITY | 074/002 | ICW | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-123.417097 | 40.6994 | ETL.1820 | 44562663 | Damper-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
117911202 | T2 DI CLAY-MARTEL 33/504 RPL POLE | 31461360 | CLAY-MARTEL | 033/504 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.845788 | 38.4699 | ETL.8250 | 40912847 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 33
117911231 | T3NT DI KILARC-CEDAR CRK 5/130 INST GMKW | 43826337 | KILARC-CEDAR CREEK | 005/130 | ICW | F | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.974468 | 40.7092 | ETL.7290 | 40759371 | Guy Wire Mark /Indic-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117911238 | T3 DI KILARC-CEDAR CREEK 5/130 RPR STRW | 44406464 | KILARC-CEDAR CREEK | 005/130 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.974468 | 40.7092 | ETL.7290 | 40759371 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117911301 | T3NT DI KILARC-CEDAR CRK 5/130 INST MRKW | 43826337 | KILARC-CEDAR CREEK | 005/130 | ICW | F | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.974468 | 40.7092 | ETL.7290 | 40759371 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
117911339 | T2NT DI PIT#1-COTTONWOOD 11/93 INST MRKS | 43879413 | PIT #1-COTTONWOOD | 011/093 | ICS | F | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.681045 | 40.8947 | ETL.5390 | 40657385 | Marker (i.e. signs)-Steel | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain
117911403 | T2 HUMBOLDT-TRINITY 088/002 RPL ANCW | 31473759 | HUMBOLDT-TRINITY | 088/002 | 93E | E | Pre-2020_(2) High fire spread TD |  |  |  | TR2 | LATE | North Coast | Non-WSIP |  |  |  |  | Project | 2021 HUMBOLDT-TRINITY | '-123.658695 | 40.7266 | ETL.1820 | 44562229 | Anchor-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Eureka |  |  | 2020-05-27
117911629 | T2 HUMBOLDT-TRINITY 074/002 INST DAMW | 44311171 | HUMBOLDT-TRINITY | 074/002 | ICW | E | Pre-2020_(9a) Other ignition related |  |  |  |  | LATE | North Coast | WSIP | FSRP | [5 empty] | '-123.417097 | 40.6994 | ETL.1820 | 44562889 | Damper-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
117912010 | T2 HUMBOLDT-TRINITY 074/002 INST DAMW | 44311171 | HUMBOLDT-TRINITY | 074/002 | ICW | E | Pre-2020_(9a) Other ignition related |  |  |  |  | LATE | North Coast | WSIP | FSRP | [5 empty] | '-123.417097 | 40.6994 | ETL.1820 | 44562664 | Damper-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
117912540 | T2 DIABLO-MESA 012/053 RPL INSS | 31479418 | DIABLO-MESA | 012/053 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.7092547 | 35.2603 | ETL.4620 | 40679735 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 12
117913029 | T2 DIABLO-MESA 013/058 RPL INSS | 31479418 | DIABLO-MESA | 013/058 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.695995 | 35.2449 | ETL.4620 | 40895395 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 12
117913057 | T2 DIABLO-MESA 012/057 RPL INSS | 31479418 | DIABLO-MESA | 012/057 | 93K | F | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.6973473 | 35.2466 | ETL.4620 | 40835733 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 12
117913118 | T2 DIABLO-MESA 013/059 RPL INSS | 31479418 | DIABLO-MESA | 013/059 | 93K | F | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.6945523 | 35.2432 | ETL.4620 | 40885002 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 12
117913245 | T2NT DI ELECTRA-BELLOTA 2/019 INST MRKS | 44631102 | ELECTRA-BELLOTA | 002/019 | ICS | F | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-120.687829 | 38.304 | ETL.4670 | 40811165 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - 6
117913696 | T2 DIABLO-MESA 013/061 RPL INSS | 31479418 | DIABLO-MESA | 013/061 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.6870284 | 35.2368 | ETL.4620 | 40614927 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 12
117913997 | T3 DI SBNT-GRZL-CLMNT#1 04/041 RPR FOND | 43752388 | SOBRNTE-GRIZZLY-CLARMNT #1+ | 004/041 | ICS | F | Pre-2020_(4) TD tag on high spread line |  |  | Likely MAT error - delink to correct | TR3 | LATE | Central | WSIP | [6 empty] | '-122.198441 | 37.8612 | ETL.3740 | 40764494 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 6
117914044 | T3NT DI SBNT-GRZL-CLNT#1 04/041 REPAINT | 44586187 | SOBRNTE-GRIZZLY-CLARMNT #1+ | 004/041 | ICS | F | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) |  |  | TR3 |  | Central | WSIP | [6 empty] | '-122.198441 | 37.8612 | ETL.3740 | 40764494 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay
117914294 | T2 DIABLO-MESA 014/065 RPL INSS | 31479418 | DIABLO-MESA | 014/065 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.6755136 | 35.2291 | ETL.4620 | 40781614 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 12
117914800 | T2 DIABLO-MESA 017/075 RPL INSS | 31479418 | DIABLO-MESA | 017/075 | 93K | F | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.6410185 | 35.2062 | ETL.4620 | 40781618 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 12
117914808 | T2 DIABLO-MESA 017/077 RPL INSS | 31479418 | DIABLO-MESA | 017/077 | 93K | F | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.6356157 | 35.2021 | ETL.4620 | 40839156 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 12
117915083 | T2 DIABLO-MESA 018/081 RPL INSS | 31479418 | DIABLO-MESA | 018/081 | 93K | F | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.6246755 | 35.1956 | ETL.4620 | 40605048 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 12
117917093 | T2 DI MOSS LANDING-METCLF 12/61 RPR GYWS | 44190551 | MOSS LANDING-METCALF | 012/061 | ICS | E | Pre-2020_(4) TD tag on high spread line | Superintendent Approved work efficiency |  | Tower guy | TR2 | LATE | South | WSIP | FSRP | [5 empty] | '-121.651656 | 36.9349 | ETL.6050 | 40597456 | Guy Wire-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Moss Landing |  | Y - 6
117917371 | T2 DI OLEUM-N-TWR-CHRST A03/24 RPR STRT | 43752227 | OLEUM-NORTH TOWER-CHRISTIE | A03/024 | ICQ | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.203463 | 38.0271 | ETL.3180 | 40745842 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 4
117917676 | T3 DI CARIBOU-PALERMO :35/283 BENT MEMB | 44069801 | CARIBOU-PALERMO | :035/283 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.481438 | 39.7126 | ETL.3190 | 40656368 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
117917740 | T2 DI HT CRK #1 WSTWD 19/376 RPR STRW | 43904280 | HAT CREEK #1-WESTWOOD | 019/376 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.280287 | 40.7465 | ETL.7030 | 40601612 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117917819 | DI BRIONES TAP 001/026 WASH INSU |  | BRIONES TAP | 001/026 | ICD | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | Central | WSIP | FSRP | [5 empty] | '-121.742222 | 37.9083 | ETL.7055 | 40850931 | Insulator | Contaminated | Ground Wash |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 622 | Bay |  | Y - 7
117917906 | T2 DI HT CRK #1-WSTWD 8/163 RPR GYWW | 43904280 | HAT CREEK #1-WESTWOOD | 008/163 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.412648 | 40.8729 | ETL.7030 | 40868428 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117917941 | T2 DI KILARC-DESCHUTES 007/148 REGRADE | 43930440 | KILARC-DESCHUTES | 007/148 | ICW | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.964289 | 40.6073 | ETL.7300 | 40771289 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Released
117918286 | T2 DIABLO-MESA 019/084 RPL INSS | 31479418 | DIABLO-MESA | 019/084 | 93K | F | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.6130087 | 35.1895 | ETL.4620 | 40792003 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 12
117918335 | T2 DI MSS LNDING-LOS BNS 37/163 RPL GYWS | 44190496 | MOSS LANDING-LOS BANOS | 037/163 | ICS | E | Pre-2020_(4) TD tag on high spread line | Superintendent Approved work efficiency |  | Tower guy | TR2 | LATE | South | WSIP | FSRP | [5 empty] | '-121.197632 | 36.9139 | ETL.6040 | 40658768 | Guy Wire-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Moss Landing |  | Y - 6
117918580 | T2 MORRO BAY-MESA 034/153 RPL INSS | 31479415 | MORRO BAY-MESA | 034/153 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | South | Non-WSIP | [6 empty] | '-120.4479419 | 35.0179 | ETL.5290 | 44330044 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 12
117918682 | T2 DIABLO-MESA 034/152 RPL INSLS | 31479418 | DIABLO-MESA | 034/152 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.4483778 | 35.0202 | ETL.4620 | 40724300 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 12
117918704 | T2 DIABLO-MESA 020/088 RPL INSS | 31479418 | DIABLO-MESA | 020/088 | 93K | F | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.6006774 | 35.1788 | ETL.4620 | 40886906 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 12
117918839 | T2 DIABLO-MESA 033/147 RPL INSS | 31479418 | DIABLO-MESA | 033/147 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.4550119 | 35.0309 | ETL.4620 | 40845445 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 12
117918854 | T2 EI MORAGA-LAKEWOOD 011/082 INS HRDT |  | MORAGA-LAKEWOOD | 011/082 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | Central | WSIP | FSRP | [5 empty] | '-122.143622 | 37.8606 | ETL.3741 | 44376928 | Hardware-Tower | Missing | Install |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 7
117918874 | T2 DI CHRISTIE-SOBRANTE 11/64 PNT STRS | 43751914 | CHRISTIE-SOBRANTE | 011/064 | ICS | F | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) |  |  | TR2 |  | Central | WSIP | [6 empty] | '-122.194183 | 37.9814 | ETL.1260 | 40760658 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  | Y - Prog 402
117918912 | T2 DIABLO-MESA 020/090 RPL INSS | 31479418 | DIABLO-MESA | 020/090 | 93K | F | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 |  | South | Non-WSIP | FSRP | [5 empty] | '-120.5956527 | 35.1754 | ETL.4620 | 40638414 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 12
117918924 | T2 DI VALLEY SPRINGS #1 A000/013 RPR STR | 44290817 | VALLEY SPRINGS #1 | A000/013 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.756422 | 38.2094 | ETL.8210 | 40911570 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 23
117918929 | T2 DI VALLEY SPRINGS #1 001/030 RPR STRW | 44290818 | VALLEY SPRINGS #1 | 001/030 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.787994 | 38.2053 | ETL.8210 | 40904197 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 23
117918970 | T2 DIABLO-MESA 033/146 RPL INSS | 31479418 | DIABLO-MESA | 033/146 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.4567713 | 35.0333 | ETL.4620 | 40838488 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 12
117919107 | T3NT EI ROCK CREEK-POE 012/085 PNT STRT | 44586178 | ROCK CREEK-POE | 012/085 | ICX | F | Pre-2020_(4b) On structure in bucket 4 |  |  | Likely MAT error - delink to correct | TR3 |  | North Valley | WSIP | [6 empty] | '-121.457984 | 39.7724 | ETL.5630 | 40757655 | Structure-Tower | Paint/Coating | Repaint | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense |  | Table Mountain
117919382 | T2 DIABLO-MESA 033/145 RPL INSS | 31479418 | DIABLO-MESA | 033/145 | 93K | F | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.4588826 | 35.0362 | ETL.4620 | 40781634 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 12
117919687 | T2 KERCKHOFF-CLVS-SNGR #1 0/7 RPL TOWER | 31473355 | KERCKHOFF-CLOVIS-SANGER #1 | 000/007 | 70S | F | Pre-2020_(4) TD tag on high spread line | Superintendent Approved work efficiency |  |  | TR2 |  | South | Non-WSIP | [6 empty] | '-119.565054 | 37.053 | ETL.1890 | 40806738 | Structure-Tower | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLQ | Pole Program | Capital | 426 | Fresno |  |  | Project
117919732 | T2 DIABLO-MESA 022/098 RPL INSS | 31479418 | DIABLO-MESA | 022/098 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.573342 | 35.1585 | ETL.4620 | 40899410 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 12
117921552 | T2 DI OLEUM-MARTINEZ 004/033 RPL HRDs | 44326132 | OLEUM-MARTINEZ | 004/033 | ICS | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.17407 | 38.0147 | ETL.3170 | 40645947 | Hardware-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - 3
117921555 | T2 DI OLEUM-MARTINEZ 004/033 RPL INSS | 31457825 | OLEUM-MARTINEZ | 004/033 | 93K | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.17407 | 38.0147 | ETL.3170 | 40704788 | Insulator-Steel | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - 3
117921594 | T2 DI OLEUM-MARTINEZ 004/033 REPAINT | 44586167 | OLEUM-MARTINEZ | 004/033 | ICS | F | Pre-2020_(5b) On structure in bucket 5 | Budget Owner (Paint) |  |  | TR2 |  | Central | WSIP | [6 empty] | '-122.17407 | 38.0147 | ETL.3170 | 40645947 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay
117921598 | T2 DI CARIBOU-PALERMO 008/070 RPL INSS |  | CARIBOU-PALERMO | 008/070 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP |  |  |  | Field Operations |  | '-121.529001 | 39.5781 | ETL.3190 | 40634312 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain
117922191 | T2 DI NARROWS#1 TAP 0/9 RPL POLE | 31505367 | NARROWS #1 TAP | 000/009 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.291809 | 39.2144 | ETL.6511 | 40757183 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento
117922910 | EI VACA-PARKWAY 024/133 RPL SHLS | 44299272 | VACA-PARKWAY | 024/133 | ICS | E | Pre-2020_(2) High fire spread TD |  |  |  |  | LATE | North Coast | Non-WSIP |  |  |  |  | Field Operations | Cannot complete without Line support out of Lakeville | '-122.198202 | 38.1687 | ETL.5850 | 40783264 | Shield Wire / OPGW-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Lakeville
117925479 | T2 DI VALLEY SPRINGS #1 008/170 RPR STRW | 44292020 | VALLEY SPRINGS #1 | 008/170 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.871035 | 38.1328 | ETL.8210 | 40908253 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 23
117926336 | T3NT DI SOBRANTE-R-#1 1/12 REPAINT | 43727737 | SOBRANTE-R #1 | 001/012 | ICS | F | Pre-2020_(9a) Other ignition related |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-122.240263 | 37.908 | ETL.3770 | 40646639 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay
117926600 | T2 DI TIDEWATER-SOBRANTE 22/105 RPR FOND |  | TIDEWATER-SOBRANTE | 022/105 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.204163 | 37.912 | ETL.5770 | 40752591 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 2 | EBMUD
117926730 | T3 DI SBT-GRZLY-CLRMNT#1 04/040 RPR FOND | 43752388 | SOBRNTE-GRIZZLY-CLARMNT #1+ | 004/040 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  | Likely MAT error - delink to correct | TR3 | LATE | Central | WSIP | [6 empty] | '-122.195233 | 37.8618 | ETL.3740 | 40761864 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 7
117926908 | T3 DI DRUM-RIO OSO #1 009/096 INST HRDT | 43977711 | DRUM-RIO OSO #1 | 009/096 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.912623 | 39.1783 | ETL.1420 | 40814354 | Hardware-Tower | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento |  |  | Yes
117927234 | T3 KILARC-CEDAR CREEK 7/166 RPL POLE | 31473906 | KILARC-CEDAR CREEK | 007/166 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | Non-WSIP | [6 empty] | '-121.99944 | 40.7185 | ETL.7290 | 40809931 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
117927460 | T2 DIABLO-MESA 023/103 RPL INSS | 31479418 | DIABLO-MESA | 023/103 | 93K | F | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.558845 | 35.1462 | ETL.4620 | 40691295 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 12
117927463 | T2 DIABLO-MESA 023/104 RPL INSS | 31479418 | DIABLO-MESA | 023/104 | 93K | F | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.5567449 | 35.1443 | ETL.4620 | 40797208 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 12
117931109 | RND MTN-CTTNWD #3 035/304 RPL INSS | 31478747 | ROUND MTN-COTTONWOOD #3 | 035/304 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | North Valley | Non-WSIP | [6 empty] | '-122.0215326 | 40.6925 | ETL.5650 | 40789061 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain
117931257 | T2NT DI STLS-MLNS-SS-MTC 17/110 REPAINT |  | STANISLAUS-MELONES SS-MANTECA #1+ | 017/110 | ICS | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-120.636639 | 37.9913 | ETL.3830 | 40579611 | Structure-Steel | Paint/Coating | Other |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - 9
117931300 | T2 DI STNNLS-MNTCA #2 019/110 RPR STRT | 44460415 | STANISLAUS-MANTECA #2 | 019/110 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-120.648263 | 37.9825 | ETL.3820 | 40579645 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - 14
117931431 | T2 PALERMO-COLGATE C003/016 RPL INSS | 31473816 | PALERMO-COLGATE | C003/016 | 93K | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-121.253743 | 39.3089 | ETL.5360 | 40847730 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Sacramento
117931610 | T2 EI LOS ESTROS-MTCALF 17/78 PAINT STRT | 43753289 | LOS ESTEROS-METCALF | 017/078 | ICS | F | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) |  |  | TR2 |  | Central | WSIP | [6 empty] | '-121.82071 | 37.4494 | ETL.5353 | 40863120 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  |  | SFWL
117931678 | T2 PARADISE-BUTTE 4/46 RPL INSS | 31478630 | PARADISE-BUTTE | 004/046 | 93K | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-121.6569745 | 39.7258 | ETL.4396 | 41127313 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain
117931731 | T2 MORRO BAY-MESA 23/105 RPL INSS | 31479418 | DIABLO-MESA | 023/105 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.5529869 | 35.1411 | ETL.4620 | 40792450 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 12
117931736 | T2 DIABLO-MESA 24/106 RPL INSS | 31479418 | DIABLO-MESA | 024/106 | 93K | F | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.5496043 | 35.1382 | ETL.4620 | 40838476 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 12
117931737 | T3 DIABLO-MESA 25/109 RPL INSS | 31479418 | DIABLO-MESA | 025/109 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.5378851 | 35.1278 | ETL.4620 | 40893972 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 12
117931751 | EI COALINGA #1-SAN MIGUEL 16/2 PNT STRS | 44301011 | COALINGA #1-SAN MIGUEL | 016/002 | ICS | F | Pre-2020_(9a) Other ignition related | [5 empty] | South | Non-WSIP | [6 empty] | '-120.54436 | 36.0065 | ETL.8580 | 40690794 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Pismo Beach
117931755 | EI VACA-PARKWAY 003/022 REPAINT STRS | 43978210 | VACA-PARKWAY | 003/022 | ICS | F | Pre-2020_(9a) Other ignition related |  |  |  |  | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-121.985702 | 38.4107 | ETL.5850 | 40681095 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento
117931756 | EI COALINGA #1-SAN MIGUEL 16/1 PNT STRS | 44301011 | COALINGA #1-SAN MIGUEL | 016/001 | ICS | F | Pre-2020_(9a) Other ignition related | [5 empty] | South | Non-WSIP | [6 empty] | '-120.54101 | 36.0071 | ETL.8580 | 40597831 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Pismo Beach
117931789 | T2 MORRO BAY-MESA 034/154 RPL INSS | 31479415 | MORRO BAY-MESA | 034/154 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | South | Non-WSIP | [6 empty] | '-120.4504151 | 35.0148 | ETL.5290 | 40782431 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 12
117931843 | T3 DIABLO-MESA 26/113 RPL INSS | 31479418 | DIABLO-MESA | 026/113 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.5236248 | 35.1156 | ETL.4620 | 40672027 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 12
117931994 | T3 DIABLO-MESA 27/117 RPL INSS | 31479418 | DIABLO-MESA | 027/117 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.512393 | 35.1059 | ETL.4620 | 40835745 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 12
117932222 | T2 DI PTTSBRG-TESLA #1 008/038 RPL HRDT | 43753186 | PITTSBURG-TESLA #1 | 008/038 | ICQ | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-121.846949 | 37.9365 | ETL.5510 | 40873706 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 5
117932412 | T2 DIABLO-MESA 28/124 RPL INSS | 31479418 | DIABLO-MESA | 028/124 | 93K | F | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.4945118 | 35.0871 | ETL.4620 | 40782425 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 12
117932548 | T2 DIABLO-MESA 29/128 RPL INSS | 31479418 | DIABLO-MESA | 029/128 | 93K | F | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.4877866 | 35.0759 | ETL.4620 | 40895401 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 12
117932673 | DRUM PH #2 TAP 0/TERM1 RPR INSS | 43976856 | DRUM PH #2 TAP | 000/001C | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | Non-WSIP | [6 empty] | '-120.766333 | 39.2571 | ETL.6375 | 43196977 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento
117932908 | T2 DI HIGGINS-BELL 31/234 RPR INSS | 43978209 | HIGGINS-BELL | 031/234 | ICS | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.05851 | 38.9955 | ETL.1412 | 40899328 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento
117935388 | T2NT EI SOBRANTE-MRGA 00/01A RPR GYWS | 44621660 | SOBRANTE-MORAGA | 000/001A | ICS | F | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-122.162935 | 37.8489 | ETL.3742 | 40575706 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - 7
117935399 | T2 EI SOBRANTE-MORAGA 00/001A RPL ANCS | 31475815 | SOBRANTE-MORAGA | 000/001A | 93Z | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.162935 | 37.8489 | ETL.3742 | 40575706 | Anchor-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Capital |  | Bay |  | Y - 7
117935776 | T2 EI MARTINEZ-SOBRANTE 5/32 RPL INSS | 31453033 | MARTINEZ-SOBRANTE | 005/032 | 93K | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.173567 | 38.0144 | ETL.2270 | 40704790 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - OM3
117936490 | LOS BANOS-MIDWAY #2 047/199 RPL INSS |  | LOS BANOS-MIDWAY #2 | 047/199 | 93K | E | Pre-2020_(1b) Lines with special commitments | Director approved | DLFL once tag is confirmed complete PM | Email CIRT when complete |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.50504 | 36.5177 | ETL.6010 | 40890872 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 23
117937333 | T2 TEJON-LEBEC 11/196 RPL CONN | 44226977 | TEJON-LEBEC | 011/196 | ICM | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | South | Non-WSIP | [6 empty] | '-118.888407 | 34.8715 | ETL.9250 | 40749552 | Connector | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 534 | Midway |  | Y - 10
117937435 | T2 DI MTN GATE JCT-CASCADE 5/61 RPR STRW | 43758388 | MTN GATE JCT-CASCADE | 005/061 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-122.332563 | 40.6683 | ETL.7640 | 40828054 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117941008 | LOS BANOS-MIDWAY #2 139/570 CANCEL | 44284329 | LOS BANOS-MIDWAY #2 | 139/570 | ICS | E | Pre-2020_(1b) Lines with special commitments |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.511767 | 35.4739 | ETL.6010 | 40592993 | Hardware-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Midway |  | Y - 26
117941074 | LOS BANOS-MIDWAY #2 144/594 RPL INSS | 74008748 | LOS BANOS-MIDWAY #2 | 144/594 | 93K | F | Pre-2020_(1b) Lines with special commitments | Director approved |  |  |  | WECC | South | Non-WSIP | [6 empty] | '-119.45614 | 35.4056 | ETL.6010 | 40797042 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE idoc idcr |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Midway |  | Y - 26
117941338 | DI PIT#7 TAP 0/7L RPL STRW | 31501365 | PIT #7 TAP | 000/007 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-121.980088 | 40.8407 | ETL.5442 | 44553612 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain
117941350 | DI PIT#7 TAP 0/7R RPL STRW | 31501365 | PIT #7 TAP | 000/007 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-121.980088 | 40.8407 | ETL.5442 | 44553592 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain
117941672 | DI SMARTVILLE-NICOLAS #1 20/410 RPR SPLW | 43983792 | SMARTVILLE-NICOLAUS #1 | 020/410 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-121.428751 | 38.9554 | ETL.7990 | 40909207 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117942122 | T2 TEJON-LEBEC 12/204 RPL CONNECTORS | 44226979 | TEJON-LEBEC | 012/204 | ICM | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | South | Non-WSIP | [6 empty] | '-118.886676 | 34.8684 | ETL.9250 | 40654747 | Connector | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 534 | Midway |  | Y - 10
117942163 | T3 DI DRM-GRSS VLY-WMR B017/387 RPR SPLW | 43983614 | DRUM-GRASS VALLEY-WEIMAR | B017/387 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.965608 | 39.1333 | ETL.6760 | 40874781 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
117942281 | T2 DI DBLO-MDWY #3 013/051 REMV DEBRIS |  | DIABLO-MIDWAY #3 | 013/051 | ICS | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | South | WSIP | FSRP | [5 empty] | '-120.623079 | 35.1706 | ETL.5980 | 40593641 | Structure-Steel | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Pismo Beach
117942438 | T2 DIABLO-MESA 028/121 RPL INSS | 31479418 | DIABLO-MESA | 028/121 | 93K | F | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.4992223 | 35.0937 | ETL.4620 | 40611915 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 12
117942620 | T3 DI CARIBOU-PALERMO :036/293 RPR FOND | 44069455 | CARIBOU-PALERMO | :036/293 | ICQ | F | Pre-2020_(2) High fire spread TD |  |  |  | TR3 |  | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.484237 | 39.6955 | ETL.3190 | 40656370 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
117943182 | PALERMO-WYANDOTTE 004/037 RPL INSS | 31478468 | PALERMO-WYANDOTTE | 004/037 | 93K | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | North Valley | Non-WSIP | [6 empty] | '-121.539795 | 39.5145 | ETL.4315 | 40841302 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain
117955088 | LOS BANOS-MIDWAY #2 133/549 RPL INSS | 74008748 | LOS BANOS-MIDWAY #2 | 133/549 | 93K | F | Pre-2020_(1b) Lines with special commitments | Director approved |  |  |  | WECC | South | Non-WSIP | [6 empty] | '-119.562198 | 35.5358 | ETL.6010 | 40886169 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE idoc idcr |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Midway |  | Y - 26
117955455 | T2 EI RIO DELL JCT-BRDGVL 25/13 RPL COND | 31475455 | RIO DELL JCT-BRIDGEVILLE | 025/013 | 93C | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.987331 | 40.5108 | ETL.7850 | 40648543 | Conductor-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 638 | Eureka |  |  | 2019-12-09
117955786 | T3 DIABLO-MIDWAY #2 026/107 RPR GYWS | 44571720 | DIABLO-MIDWAY #2 | 026/107 | ICS | E | Pre-2020_(9a) Other ignition related |  |  | Tower guy | TR3 | LATE | South | Non-WSIP | [6 empty] | '-120.395742 | 35.1633 | ETL.5970 | 40818969 | Guy Wire-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Pismo Beach |  | Y - 19
117955810 | T3 DIABLO-MIDWAY #3 026/106 RPR GYWS | 44571721 | DIABLO-MIDWAY #3 | 026/106 | ICS | E | Pre-2020_(9a) Other ignition related |  |  | Tower guy | TR3 | LATE | South | Non-WSIP | [6 empty] | '-120.398713 | 35.1636 | ETL.5980 | 40818892 | Guy Wire-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Pismo Beach |  | Y - 15
117956027 | T3NT DI TGR CRK-VLY SPRNGS 5/44 REPAINT | 43878409 | TIGER CREEK-VALLEY SPRINGS | 005/044 | ICS | F | Pre-2020_(9a) Other ignition related |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-120.58546 | 38.4234 | ETL.5790 | 40756083 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - 11
117956041 | T3 EI BRUNSWICK #1 TAP 000/003 RPL INSS | 31474523 | BRUNSWICK #1 TAP | 000/003 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.008695 | 39.1443 | ETL.1422 | 40650072 | Insulator-Steel | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Sacramento |  |  | Yes
117956601 | DI WASTONVILLE-SALINAS 5/76 RPL POLE | 31511435 | WATSONVILLE-SALINAS | 005/076 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | South | WSIP | [6 empty] | '-121.68963 | 36.8782 | ETL.8310 | 40645486 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Moss Landing |  | Y - 11
117957244 | T2 DI RIO DELL JCT-BRDGVL 38/2 RPL PL(R) | 31475456 | RIO DELL JCT-BRIDGEVILLE | 038/002 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.8216277 | 40.4691 | ETL.7850 | 44403585 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Eureka |  |  | 2019-12-09
117957264 | LOS BANOS-MIDWAY #2 123/507A RPL INSS | 74008748 | LOS BANOS-MIDWAY #2 | 123/507A | 93K | F | Pre-2020_(1b) Lines with special commitments | Director approved |  |  |  | WECC | South | Non-WSIP | [6 empty] | '-119.663856 | 35.6612 | ETL.6010 | 40578867 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE idoc idcr |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Midway |  | Y - 26
117957426 | T2 DI RND MTN-TBL MTN#2 73/299 INST GMKS | 44305720 | ROUND MTN-TABLE MTN #2 | 073/299 | ICS | F | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.759893 | 39.7628 | ETL.6070 | 40865419 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain
117959262 | LOS BANOS-MIDWAY #2 111/460 RPL INSS | 31527048 | LOS BANOS-MIDWAY #2 | 111/460 | 93K | F | Pre-2020_(1b) Lines with special commitments | Director approved | DLFL once tag is confirmed complete PM | Email CIRT when complete |  | WECC | South | Non-WSIP | [6 empty] | '-119.781842 | 35.8061 | ETL.6010 | 40635851 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 23
117959294 | LOS BANOS-MIDWAY#2 122/504 CANCEL |  | LOS BANOS-MIDWAY #2 | 122/504 | ICS | E | Pre-2020_(1b) Lines with special commitments |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.673088 | 35.6727 | ETL.6010 | 40754008 | Hardware-Steel | Missing | Install |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 628 | Midway |  | Y - 26
117959344 | T2 EI BALCH-SANGER 012/065B RPR ANC FOND | 44589311 | BALCH-SANGER | 012/065B | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-119.267889 | 36.8413 | ETL.1050 | 44191341 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 17 | USFS
117959348 | LOS BANOS-MIDWAY#2 126/521 PNT STRS | 44284331 | LOS BANOS-MIDWAY #2 | 126/521 | ICS | F | Pre-2020_(1b) Lines with special commitments | Director approved |  |  |  | WECC | South | Non-WSIP | [6 empty] | '-119.63008 | 35.62 | ETL.6010 | 40593354 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Midway |  | Y - 26
117959461 | LOS BANOS-MIDWAY#2 123/507B RPL INSS | 74008748 | LOS BANOS-MIDWAY #2 | 123/507B | 93K | F | Pre-2020_(1b) Lines with special commitments | Director approved |  |  |  | WECC | South | Non-WSIP | [6 empty] | '-119.663606 | 35.6613 | ETL.6010 | 41132665 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE idoc idcr |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Midway |  | Y - 26
117959466 | LOS BANOS-GATES #1 027/115A RPL INSS | 31527294 | LOS BANOS-GATES #1 | 027/115A | 93K | F | Pre-2020_(1b) Lines with special commitments | Director approved | DLFL once tag is confirmed complete PM 74008747 | Email CIRT when complete |  | WECC | South | Non-WSIP | [6 empty] | '-120.721685 | 36.748 | ETL.6000 | 40578881 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 16
117959652 | LOS BANOS-GATES #1 027/115B RPL INSS | 31527294 | LOS BANOS-GATES #1 | 027/115B | 93K | F | Pre-2020_(1b) Lines with special commitments | Director approved | DLFL once tag is confirmed complete PM 74008747 | Email CIRT when complete |  | WECC | South | Non-WSIP | [6 empty] | '-120.721952 | 36.7478 | ETL.6000 | 40740401 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 16
117959854 | T2 DI DUNLAP TAP 03/001 RPR FOND | 44301877 | DUNLAP TAP | 003/001 | ICQ | E | Pre-2020_(5) TD tag on other lines |  |  | Likely MAT error - delink to correct | TR2 | LATE | South | WSIP | [6 empty] | '-119.213701 | 36.5965 | ETL.9061 | 44669787 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 543 | Fresno |  | Y - 9
117960064 | T2 DI WISHN-COPPERMINE 5/038 INST MRKS | 44278154 | WISHON-COPPERMINE | 005/038 | ICS | F | Pre-2020_(4b) On structure in bucket 4 | Superintendent Approved work efficiency |  |  | TR2 |  | South | WSIP | [6 empty] | '-119.53096 | 37.077 | ETL.9330 | 40868036 | Marker (i.e. signs)-Steel | No Good/Out of Stdrd | Install | UNSE crdy |  |  |  | PEND | LC | TLQ | Tower | Expense | 628 | Fresno |  | Y - 12
117960590 | DI HT CRK #1 WSTWD 49/955 RPR STRW | 43904280 | HAT CREEK #1-WESTWOOD | 049/955 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-121.015807 | 40.3816 | ETL.7030 | 40601694 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117961327 | LOS BANOS-GATES #1 033/141 RPLC INSS |  | LOS BANOS-GATES #1 | 033/141 | 93K | E | Pre-2020_(1b) Lines with special commitments | Director approved | DLFL once tag is confirmed complete PM 74008747 | Email CIRT when complete |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.67428 | 36.6618 | ETL.6000 | 40617621 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 16
117961341 | T3 DI GRIZZLY TAP 3/9L RPR GYWW |  | TAP (CITY OF SANTA CLARA) | 003/009 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.321883 | 39.9052 | ETL.2395 | 44551401 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117961392 | T3 GRIZZLY TAP 003/009 RPR GYWW |  | TAP (CITY OF SANTA CLARA) | 003/009 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR3 | LATE | North Valley | Non-WSIP | [6 empty] | '-121.321883 | 39.9052 | ETL.2395 | 44551438 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117961396 | T3 GRIZZLY TAP 3/9 RPR GYWW |  | TAP (CITY OF SANTA CLARA) | 003/009 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR3 | LATE | North Valley | Non-WSIP | [6 empty] | '-121.321883 | 39.9052 | ETL.2395 | 44551468 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
117961843 | T2 EI BALCH-SANGER 007/045 INS ATCG | 31431430 | BALCH-SANGER | 007/045 | 93A | F | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-119.187861 | 36.8774 | ETL.1050 | 40751518 | Structure-Tower | Anti-Climbing Guard | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Capital | 988 | Fresno |  | Y - 16 | USFS
117966587 | T2 CRESTA-RIO OSO 008/067 RPL CONN | 43844645 | CRESTA-RIO OSO | 008/067 | ICM | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-121.412336 | 39.8281 | ETL.4590 | 40815415 | Connector | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 534 | Table Mountain
117966680 | T2 CRESTA-RIO OSO 008/071 RPL CONN | 43844645 | CRESTA-RIO OSO | 008/071 | ICM | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-121.421164 | 39.8293 | ETL.4590 | 40591398 | Connector | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 534 | Table Mountain
117966783 | T3 CRESTA-RIO OSO 014/117 RPL INSS | 31475914 | CRESTA-RIO OSO | 014/117 | 93K | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR3 | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-121.478503 | 39.7336 | ETL.4590 | 40919877 | Insulator-Steel | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  | Yes
117966829 | LOS BANOS-MIDWAY #2 108/449 RPL INSS | 31527048 | LOS BANOS-MIDWAY #2 | 108/449 | 93K | F | Pre-2020_(1b) Lines with special commitments | Director approved | DLFL once tag is confirmed complete PM | Email CIRT when complete |  | WECC | South | Non-WSIP | [6 empty] | '-119.813134 | 35.8413 | ETL.6010 | 40886153 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 23
117967357 | T2 DI RIO DL JCT-BRDGVL 38/2 RPL POLE(L) | 31475456 | RIO DELL JCT-BRIDGEVILLE | 038/002 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | North Coast | WSIP | [8 empty] | ETL.7850 | 44403583 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2019-12-09
117967410 | DI RIO DL JCT-BRDGVL 38/2 RPLC POLE(C) | 31475456 | RIO DELL JCT-BRIDGEVILLE | 038/002 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | North Coast | WSIP | [8 empty] | ETL.7850 | 44403584 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2019-12-09
117969898 | EI DEL MONTE-FORT ORD #1 3/52 REPNT | 44585954 | DEL MONTE-FORT ORD #1 (NO FLY) | 003/052 | ICX | F | Pre-2020_(5b) On structure in bucket 5 |  |  | Likely MAT error - delink to correct |  |  | South | Non-WSIP | [6 empty] | '-121.817637 | 36.6217 | ETL.8400 | 40754623 | Structure-Tower | Paint/Coating | Repaint | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense |  | Moss Landing |  | Y - 4
117970378 | T2 CARIBOU #2 :0/011 RPL POLE UNMAPPED | 31474479 | CARIBOU #2 | 000/011 | 70Y | F | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-121.149185 | 40.0849 | ETL.6280 | 40600559 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  | Yes
117970897 | LOS BANOS-MIDWAY#2 7/34 ZENA GUARD | 43848355 | LOS BANOS-MIDWAY #2 | 007/034 | ICS | F | Pre-2020_(1b) Lines with special commitments |  |  |  |  | WECC | South | Non-WSIP | [6 empty] | '-120.954813 | 36.958 | ETL.6010 | 40753952 | Raptor Guard-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 593 | Fresno |  | Y - 26
117971048 | LOS BANOS-MIDWAY#2 106/441 RPL INSS | 31527047 | LOS BANOS-MIDWAY #2 | 106/441 | 93K | F | Pre-2020_(1b) Lines with special commitments | Director approved | DLFL once tag is confirmed complete PM | Email CIRT when complete |  | WECC | South | Non-WSIP | [6 empty] | '-119.836638 | 35.8662 | ETL.6010 | 40619485 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 23
117973505 | LOS BANOS-GATES #1 036/150 RPR STRT | 44300852 | LOS BANOS-GATES #1 | 036/150 | ICQ | E | Pre-2020_(1b) Lines with special commitments |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.652417 | 36.6342 | ETL.6000 | 40600078 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 17
117973641 | LOS BANOS-MIDWAY #2 103/431 RPLC INSS |  | LOS BANOS-MIDWAY #2 | 103/431 | 93K | E | Pre-2020_(1b) Lines with special commitments | Director approved | DLFL once tag is confirmed complete PM | Email CIRT when complete |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.866001 | 35.8968 | ETL.6010 | 40612813 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 23
117973838 | T2 DI RIO-DL JCT-BRDVL 27/5 RPR STRW | 43749702 | RIO DELL JCT-BRIDGEVILLE | 027/005 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.982194 | 40.493 | ETL.7850 | 40750366 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2019-12-09
117973867 | T3 DIABLO-MIDWAY #2 008/032 RPL INSS | 31487951 | DIABLO-MIDWAY #2 | 008/032 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | South | Non-WSIP | [6 empty] | '-120.6993804 | 35.2011 | ETL.5970 | 40726391 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 19 | CalTrans
117973868 | T3 DIABLO-MIDWAY #2 009/033 RPL INSS | 31487951 | DIABLO-MIDWAY #2 | 009/033 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | South | Non-WSIP | [6 empty] | '-120.6933401 | 35.2006 | ETL.5970 | 40680766 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 19 | CalTrans
117974030 | T2 EI TGR CRK-VLLY SPRGS 14/116 REPAINT | 43878409 | TIGER CREEK-VALLEY SPRINGS | 014/116 | ICS | F | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) |  |  | TR2 |  | Central | WSIP | [6 empty] | '-120.669473 | 38.3207 | ETL.5790 | 40765241 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - 11
117974367 | LOS BANOS-MIDWAY #2 102/425A RPLC INSS | 31527047 | LOS BANOS-MIDWAY #2 | 102/425A | 93K | F | Pre-2020_(1b) Lines with special commitments | Director approved | DLFL once tag is confirmed complete PM | Email CIRT when complete |  | WECC | South | Non-WSIP | [6 empty] | '-119.882252 | 35.9137 | ETL.6010 | 40578712 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 23
117974402 | LOS BANOS-MIDWAY #2 103/432 RPL INSS | 31527047 | LOS BANOS-MIDWAY #2 | 103/432 | 93K | F | Pre-2020_(1b) Lines with special commitments | Director approved | DLFL once tag is confirmed complete PM | Email CIRT when complete |  | WECC | South | Non-WSIP | [6 empty] | '-119.86307 | 35.8936 | ETL.6010 | 40715362 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 23
117974403 | LOS BANOS-MIDWAY #2 104/435 RPL INSS | 31527047 | LOS BANOS-MIDWAY #2 | 104/435 | 93K | F | Pre-2020_(1b) Lines with special commitments | Director approved | DLFL once tag is confirmed complete PM | Email CIRT when complete |  | WECC | South | Non-WSIP | [6 empty] | '-119.854424 | 35.8845 | ETL.6010 | 40795590 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 23
117974405 | LOS BANOS-MIDWAY #2 105/438 RPL INSS |  | LOS BANOS-MIDWAY #2 | 105/438 | 93K | E | Pre-2020_(1b) Lines with special commitments | Director approved | DLFL once tag is confirmed complete PM | Email CIRT when complete |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.845447 | 35.8752 | ETL.6010 | 40888001 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 23
117974474 | LOS BANOS-MIDWAY#2 99/415 RPL INSS | 31527048 | LOS BANOS-MIDWAY #2 | 099/415 | 93K | F | Pre-2020_(1b) Lines with special commitments | Director approved | DLFL once tag is confirmed complete PM | Email CIRT when complete |  | WECC | South | Non-WSIP | [6 empty] | '-119.910686 | 35.9442 | ETL.6010 | 40790433 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 23
117974514 | LOS BANOS-MIDWAY #2 107/446 RPLC INSS | 31527047 | LOS BANOS-MIDWAY #2 | 107/446 | 93K | F | Pre-2020_(1b) Lines with special commitments | Director approved | DLFL once tag is confirmed complete PM | Email CIRT when complete |  | WECC | South | Non-WSIP | [6 empty] | '-119.822384 | 35.8507 | ETL.6010 | 40839605 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 23
117975285 | T2 CARIBOU #2 002/108 REPLACE P | 31474479 | CARIBOU #2 | ;002/017 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-120.95132 | 39.9959 | ETL.6280 | 44172015 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  | Yes
117975289 | LOS BANOS-MIDWAY #2 064/268 RPL INSS |  | LOS BANOS-GATES #1 | 064/268 | 93K | E | Pre-2020_(1b) Lines with special commitments | Director approved | DLFL once tag is confirmed complete PM 74008747 | Email CIRT when complete |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.315381 | 36.3318 | ETL.6000 | 40891892 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 17
117975441 | T2 DI CC-LAS POS 008/056 RPLC RPTS | 44609769 | CONTRA COSTA-LAS POSITAS | 008/056 | ICB | F | Pre-2020_(5b) On structure in bucket 5 |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-121.73819 | 37.8905 | ETL.4510 | 40762775 | Raptor Guard-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 593 | Bay |  | Y - 6
117975671 | LOS BANOS-MIDWAY #2 045/188 RPR FOND | 44300848 | LOS BANOS-MIDWAY #2 | 045/188 | ICQ | F | Pre-2020_(1b) Lines with special commitments |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.536008 | 36.54 | ETL.6010 | 40863976 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 26
117975994 | T2 CARIBOU #2 007/017 RPLC POLE | 31474479 | CARIBOU #2 | 007/017 | 70Y | E | Pre-2020_(2) High fire spread TD |  |  |  | TR2 | LATE | North Valley | Non-WSIP |  |  |  |  | Clearance Denied by GCC | 2021 - Per FLS, Bucks 1102 needs to be out to replace pole. 230kv needs to be out | '-121.223427 | 40.0161 | ETL.6280 | 40815734 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
117983870 | LOS BANOS-MIDWAY #2 013/058 RPL INSS | 31527048 | LOS BANOS-MIDWAY #2 | 013/058 | 93K | F | Pre-2020_(1b) Lines with special commitments | Director approved | DLFL once tag is confirmed complete PM | Email CIRT when complete |  | WECC | South | Non-WSIP | [6 empty] | '-120.893769 | 36.8866 | ETL.6010 | 40887957 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 23
117984295 | LOS BANOS-MIDWAY #2 011/051 RPL INSS | 31527048 | LOS BANOS-MIDWAY #2 | 011/051 | 93K | F | Pre-2020_(1b) Lines with special commitments |  |  |  |  | WECC | South | Non-WSIP | [6 empty] | '-120.909839 | 36.9054 | ETL.6010 | 40612775 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - LBG17
117984296 | LOS BANOS-MIDWAY #2 020/087 RPL INSS | 31527047 | LOS BANOS-MIDWAY #2 | 020/087 | 93K | F | Pre-2020_(1b) Lines with special commitments | Director approved | DLFL once tag is confirmed complete PM | Email CIRT when complete |  | WECC | South | Non-WSIP | [6 empty] | '-120.817562 | 36.8065 | ETL.6010 | 40848344 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 23
117984297 | LOS BANOS-MIDWAY #2 025/109 RPL INSS | 31527048 | LOS BANOS-MIDWAY #2 | 025/109 | 93K | F | Pre-2020_(1b) Lines with special commitments | Director approved | DLFL once tag is confirmed complete PM | Email CIRT when complete |  | WECC | South | Non-WSIP | [6 empty] | '-120.742358 | 36.7614 | ETL.6010 | 40886105 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 23
117984326 | T2 DI PIT#1-COTTONWOOD 4/42 RMV NEST | 43879413 | PIT #1-COTTONWOOD | 004/042 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.5736 | 40.949 | ETL.5390 | 40677448 | Structure-Steel | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
117984381 | LOS BANOS-MIDWAY#2 20/86 RPL INSS | 31527047 | LOS BANOS-MIDWAY #2 | 020/086 | 93K | F | Pre-2020_(1b) Lines with special commitments | Director approved | DLFL once tag is confirmed complete PM | Email CIRT when complete |  | WECC | South | Non-WSIP | [6 empty] | '-120.82056 | 36.8083 | ETL.6010 | 40839562 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 23
117984626 | T3 CRESTA-RIO OSO 017/145 RPL INSS | 31475914 | CRESTA-RIO OSO | 017/145 | 93K | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR3 | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-121.496592 | 39.6722 | ETL.4590 | 40919899 | Insulator-Steel | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  | Yes
117984690 | T2 DIABLO-MIDWAY #2 038/156 RPL INSS | 31487951 | DIABLO-MIDWAY #2 | 038/156 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | South | Non-WSIP | [6 empty] | '-120.1832063 | 35.1851 | ETL.5970 | 40839495 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 19
117985082 | T3 DRUM-HIGGINS 001/023L RPL LDSP | 31509929 | DRUM-HIGGINS | 001/023 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | Non-WSIP | [6 empty] | '-120.787451 | 39.2317 | ETL.4393 | 44172117 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE erdy | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento
117985483 | LOS BANOS-GATES #1 067/281 RPLC DAMS | 43848347 | LOS BANOS-GATES #1 | 067/281 | ICS | E | Pre-2020_(1b) Lines with special commitments | Director approved | DLFL once tag is confirmed complete PM 74008747 | Email CIRT when complete |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.278443 | 36.298 | ETL.6000 | 40591011 | Damper-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  | Y - 17
117985729 | LOS BANOS-MIDWAY#2 023/101 PAINT STRS | 44301828 | LOS BANOS-MIDWAY #2 | 023/101 | ICS | F | Pre-2020_(1b) Lines with special commitments |  |  |  |  | WECC | South | Non-WSIP | [6 empty] | '-120.770143 | 36.7779 | ETL.6010 | 40587740 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  | Y - 26
117986003 | LOS BANOS-MIDWAY#2 020/088 RPLC INSS | 31527047 | LOS BANOS-MIDWAY #2 | 020/088 | 93K | F | Pre-2020_(1b) Lines with special commitments | Director approved | DLFL once tag is confirmed complete PM | Email CIRT when complete |  | WECC | South | Non-WSIP | [6 empty] | '-120.814796 | 36.8049 | ETL.6010 | 40887961 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 23
117986132 | LOS BANOS-MIDWAY#2 020/089 RPLC INSS | 31527047 | LOS BANOS-MIDWAY #2 | 020/089 | 93K | F | Pre-2020_(1b) Lines with special commitments | Director approved | DLFL once tag is confirmed complete PM | Email CIRT when complete |  | WECC | South | Non-WSIP | [6 empty] | '-120.811705 | 36.803 | ETL.6010 | 40886100 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 23
117986218 | LOS BANOS-MIDWAY#2 021/093 RPLC INSS | 31527048 | LOS BANOS-MIDWAY #2 | 021/093 | 93K | F | Pre-2020_(1b) Lines with special commitments | Director approved | DLFL once tag is confirmed complete PM | Email CIRT when complete |  | WECC | South | Non-WSIP | [6 empty] | '-120.798213 | 36.7949 | ETL.6010 | 40680821 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 23
117986529 | T2 CARIBOU-TABLE MTN 20/139A INS ATCG | 31462236 | CARIBOU-TABLE MTN | 020/139A | 93A | F | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | Non-WSIP | [6 empty] | '-121.27706 | 39.9655 | ETL.4440 | 40867202 | Structure-Tower | Anti-Climbing Guard | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Capital | 988 | Table Mountain
117989723 | LOS BANOS-MIDWAY#2 25/107 RPL INSS | 31527140 | LOS BANOS-MIDWAY #2 | 025/107 | 93K | F | Pre-2020_(1b) Lines with special commitments | Director approved | DLFL once tag is confirmed complete PM | Email CIRT when complete |  | WECC | South | Non-WSIP | [6 empty] | '-120.749368 | 36.7657 | ETL.6010 | 40836795 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 23
117989868 | LOS BANOS-MIDWAY #2 022/096 RPL INSS | 31527140 | LOS BANOS-MIDWAY #2 | 022/096 | 93K | F | Pre-2020_(1b) Lines with special commitments | Director approved | DLFL once tag is confirmed complete PM | Email CIRT when complete |  | WECC | South | Non-WSIP | [6 empty] | '-120.788277 | 36.7889 | ETL.6010 | 40839564 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 23
117989994 | LOS BANOS-MIDWAY #2 028/118 RPL INSS | 31527050 | LOS BANOS-MIDWAY #2 | 028/118 | 93K | F | Pre-2020_(1b) Lines with special commitments | Director approved | DLFL once tag is confirmed complete PM | Email CIRT when complete |  | WECC | South | Non-WSIP | [6 empty] | '-120.716572 | 36.7406 | ETL.6010 | 40896531 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 23
117990043 | LOS BANOS-MIDWAY#2 29/125 RPL INSS | 31527050 | LOS BANOS-MIDWAY #2 | 029/125 | 93K | F | Pre-2020_(1b) Lines with special commitments | Director approved | DLFL once tag is confirmed complete PM | Email CIRT when complete |  | WECC | South | Non-WSIP | [6 empty] | '-120.703957 | 36.7175 | ETL.6010 | 40782749 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 23
117990676 | LOS BANOS-MIDWAY#2 051/217 RPLC INSS |  | LOS BANOS-MIDWAY #2 | 051/217 | 93K | E | Pre-2020_(1b) Lines with special commitments | Director approved | DLFL once tag is confirmed complete PM | Email CIRT when complete |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.455086 | 36.4719 | ETL.6010 | 40836809 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 23
117990677 | LOS BANOS-MIDWAY#2 031/130 RPLC INSS | 31527050 | LOS BANOS-MIDWAY #2 | 031/130 | 93K | F | Pre-2020_(1b) Lines with special commitments | Director approved | DLFL once tag is confirmed complete PM | Email CIRT when complete |  | WECC | South | Non-WSIP | [6 empty] | '-120.694469 | 36.7001 | ETL.6010 | 40634700 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 23
117990772 | LOS BANOS-MIDWAY #2 031/131 RPL INSS | 31527050 | LOS BANOS-MIDWAY #2 | 031/131 | 93K | F | Pre-2020_(1b) Lines with special commitments | Director approved | DLFL once tag is confirmed complete PM | Email CIRT when complete |  | WECC | South | Non-WSIP | [6 empty] | '-120.692538 | 36.6965 | ETL.6010 | 40612783 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 23
117991656 | T2 EI TULUCAY-NAPA #1 008/011 RPL POL | 31475457 | TULUCAY-NAPA #1 | 008/011 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.227287 | 38.2806 | ETL.8180 | 40602331 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville
117992852 | T2 HUMBOLDT-BRIDGEVILLE 114/003 RPR INSS | 44107184 | HUMBOLDT-BRIDGEVILLE | 114/003 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-124.0860955 | 40.7753 | ETL.1810 | 44378065 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2020-01-16
117992944 | T2 EI PITTSB-KRKR-COL STL 4/24 RPR INSS | 44379346 | PITTSBRG-KIRKER-COLUMBIA STEEL | 004/024 | ICS | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-121.884568 | 37.9878 | ETL.3310 | 44705831 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - 1
117992963 | T2 HUMBOLDT-BRIDGEVILLE 113/002 RPR INSS | 44107184 | HUMBOLDT-BRIDGEVILLE | 113/002 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  | Likely MAT error - delink to correct | TR2 | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-124.0651527 | 40.7677 | ETL.1810 | 43691653 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Eureka |  |  | 2020-01-16
117992966 | T2 HUMBOLDT-BRIDGEVILLE 113/000 RPL INSW | 44107184 | HUMBOLDT-BRIDGEVILLE | 113/000 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-124.0627207 | 40.7658 | ETL.1810 | 43691652 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2020-01-16
117992995 | T2 HUMBOLDT-BRIDGEVILLE 112/006 RPR INSS | 44107184 | HUMBOLDT-BRIDGEVILLE | 112/006 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-124.056485 | 40.7627 | ETL.1810 | 44322688 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2020-01-16
117993030 | T2 HUMBOLDT-BRIDGEVILLE 112/001 RPR INSS | 44107184 | HUMBOLDT-BRIDGEVILLE | 112/001 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-124.0478205 | 40.7611 | ETL.1810 | 43691647 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2020-01-16
117993773 | T2 EI ROCK CREEK-POE 010/074 INST MRKS |  | ROCK CREEK-POE | 010/074 | ICS | F | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.45337 | 39.7977 | ETL.5630 | 40762731 | Marker (i.e. signs)-Steel | Missing | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain
117994454 | LOS BANOS-MIDWAY #2 022/094 RPL INSS | 31527048 | LOS BANOS-MIDWAY #2 | 022/094 | 93K | F | Pre-2020_(1b) Lines with special commitments | Director approved | DLFL once tag is confirmed complete PM | Email CIRT when complete |  | WECC | South | Non-WSIP | [6 empty] | '-120.794953 | 36.7929 | ETL.6010 | 40796671 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 23
117994552 | LOS BANOS-MIDWAY#2 41/172 RPL INSS | 31527050 | LOS BANOS-MIDWAY #2 | 041/172 | 93K | F | Pre-2020_(1b) Lines with special commitments | Director approved | DLFL once tag is confirmed complete PM | Email CIRT when complete |  | WECC | South | Non-WSIP | [6 empty] | '-120.589858 | 36.5738 | ETL.6010 | 40721628 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 23
117994888 | LOS BANOS-MIDWAY #2 039/165 RPL INSS | 31527050 | LOS BANOS-MIDWAY #2 | 039/165 | 93K | F | Pre-2020_(1b) Lines with special commitments | Director approved | DLFL once tag is confirmed complete PM | Email CIRT when complete |  | WECC | South | Non-WSIP | [6 empty] | '-120.611265 | 36.5911 | ETL.6010 | 40782754 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 23
117995154 | LOS BANOS-MIDWAY #2 028/122 RPR GYWS | 44301006 | LOS BANOS-MIDWAY #2 | 028/122 | ICS | E | Pre-2020_(1b) Lines with special commitments |  |  | Tower guy |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.709873 | 36.7281 | ETL.6010 | 40664769 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Fresno |  | Y - 26
117995204 | T2 HUMBOLDT-BRIDGEVILLE 111/3 RPR STRW | 43749687 | HUMBOLDT-BRIDGEVILLE | 111/003 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-124.0323913 | 40.7609 | ETL.1810 | 44322664 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2020-01-16
117995207 | T2 HUMBLDT-BRIDGVLLE 110/8 RPR INSS | 44228080 | HUMBOLDT-BRIDGEVILLE | 110/008 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-124.0243664 | 40.7609 | ETL.1810 | 43691645 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Eureka |  |  | 2020-01-16
117995285 | T2 HUMBOLDT-BRIDGEVILLE 110/7 RPR INSS | 44208366 | HUMBOLDT-BRIDGEVILLE | 110/007 | ICS | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-124.0220046 | 40.7609 | ETL.1810 | 43691644 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Eureka |  |  | 2020-01-16
117995801 | T2 HUMBOLDT-BRIDGEVILLE 110/3 RPR INSS | 44107184 | HUMBOLDT-BRIDGEVILLE | 110/003 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-124.0137893 | 40.7607 | ETL.1810 | 43691640 | Crossarm-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2020-01-16
117995861 | T2 HMBLDT-BRIDGEVILLE 109/8 RPR INSW | 43749687 | HUMBOLDT-BRIDGEVILLE | 109/008 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-124.0035206 | 40.7586 | ETL.1810 | 43691639 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2020-01-16
117996513 | T2 HUMBOLDT-BRIDGEVILLE 108/5 RPR INSS | 44107184 | HUMBOLDT-BRIDGEVILLE | 108/005 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-123.982845 | 40.7519 | ETL.1810 | 40802245 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2020-01-16
117997183 | T3 DRUM-HIGGINS 001/023R RPL POLE | 31509929 | DRUM-HIGGINS | 001/023 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | Non-WSIP | [6 empty] | '-120.787451 | 39.2317 | ETL.4393 | 44172118 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE erdy | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento
117997580 | T2 CRESTA-RIO OSO 28/231 rpl inss | 31475914 | CRESTA-RIO OSO | 028/231 | 93K | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-121.533148 | 39.5647 | ETL.4590 | 41140701 | Insulator-Steel | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain |  |  | Yes
117997882 | COLLINS PINE TAP 000/005 STUB POLE | 44155694 | COLLINS PINE TAP | 000/005 | GAR | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  |  | LATE | North Valley | Non-WSIP | [6 empty] | '-121.228734 | 40.3014 | ETL.7001 | 42623453 | Structure-Wood | Rotten | Stub | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 586 | Table Mountain
118000753 | HUMBOLDT-BRIDGEVILLE 095/005 RMV DEBRIS | 43749687 | HUMBOLDT-BRIDGEVILLE | 095/005 | ICW | E | Pre-2020_(9a) Other ignition related |  |  |  |  | LATE | North Coast | Non-WSIP | [8 empty] | ETL.1810 | 44322361 | Structure-Wood | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2020-01-16
118000754 | HUMBOLDT-BRIDGEVILLE 095/001 RMV DEBRIS | 43749687 | HUMBOLDT-BRIDGEVILLE | 095/001 | ICW | E | Pre-2020_(9a) Other ignition related |  |  |  |  | LATE | North Coast | Non-WSIP | [8 empty] | ETL.1810 | 44322348 | Structure-Wood | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2020-01-16
118000755 | HUMBOLDT-BRIDGEVILLE 095/000 RMV DEBRIS | 43749687 | HUMBOLDT-BRIDGEVILLE | 095/000 | ICW | F | Pre-2020_(9a) Other ignition related |  |  |  |  | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-123.854368 | 40.5948 | ETL.1810 | 44322344 | Structure-Wood | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2020-01-16
118003309 | HUMBOLDT-BRIDGEVILLE 089/000 RMV DEBRIS | 43749687 | HUMBOLDT-BRIDGEVILLE | 089/000 | ICW | E | Pre-2020_(9a) Other ignition related |  |  |  |  | LATE | North Coast | Non-WSIP | [8 empty] | ETL.1810 | 44322253 | Structure-Wood | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2020-01-16
118004148 | HUMBOLDT-BRIDGEVILLE 090/002 RMV DEBRIS | 43749687 | HUMBOLDT-BRIDGEVILLE | 090/002 | ICW | E | Pre-2020_(9a) Other ignition related |  |  |  |  | LATE | North Coast | Non-WSIP | [8 empty] | ETL.1810 | 44322276 | Structure-Wood | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2020-01-16
118005746 | HUMBOLDT-BRIDGEVILLE 091/003 RMV DEBRIS | 43749687 | HUMBOLDT-BRIDGEVILLE | 091/003 | ICW | E | Pre-2020_(9a) Other ignition related |  |  |  |  | LATE | North Coast | Non-WSIP | [8 empty] | ETL.1810 | 44322300 | Structure-Wood | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2020-01-16
118007987 | LOS BANOS-MIDWAY#2 28/122 RPL INSS | 31527140 | LOS BANOS-MIDWAY #2 | 028/122 | 93K | F | Pre-2020_(1b) Lines with special commitments | Director approved | DLFL once tag is confirmed complete PM | Email CIRT when complete |  | WECC | South | Non-WSIP | [6 empty] | '-120.709616 | 36.7279 | ETL.6010 | 40715321 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 23
118008063 | DI CARIBOU #2 ;005/016 CANCEL | 31475564 | CARIBOU #2 | ;005/016 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  | CANCEL/CNCL |  | LATE | North Valley | WSIP | FSRP | [5 empty] | '-120.954754 | 39.9577 | ETL.6280 | 40813525 | Structure-Wood | No Good/Out of Stdrd | Replace | MAPP srdy | MAPP | Constructed and mapped | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain
118008289 | LOS BANOS-MIDWAY #2 046/192 RPL INSS | 31527140 | LOS BANOS-MIDWAY #2 | 046/192 | 93K | F | Pre-2020_(1b) Lines with special commitments | Director approved | DLFL once tag is confirmed complete PM | Email CIRT when complete |  | WECC | South | Non-WSIP | [6 empty] | '-120.523115 | 36.531 | ETL.6010 | 40715331 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 23
118008308 | LOS BANOS-MIDWAY #2 047/200 RPL INSS | 31527140 | LOS BANOS-MIDWAY #2 | 047/200 | 93K | F | Pre-2020_(1b) Lines with special commitments | Director approved | DLFL once tag is confirmed complete PM | Email CIRT when complete |  | WECC | South | Non-WSIP | [6 empty] | '-120.50173 | 36.5146 | ETL.6010 | 40638200 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 23
118008456 | LOS BANOS-MIDWAY #2 054/231A RPL INSS | 31527141 | LOS BANOS-MIDWAY #2 | 054/231A | 93K | F | Pre-2020_(1b) Lines with special commitments | Director approved | DLFL once tag is confirmed complete PM | Email CIRT when complete |  | WECC | South | Non-WSIP | [6 empty] | '-120.420863 | 36.4355 | ETL.6010 | 40578217 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 23
118008458 | LOS BANOS-MIDWAY #2 054/231B RPL INSS | 31527041 | LOS BANOS-MIDWAY #2 | 054/231B | 93K | E | Pre-2020_(1b) Lines with special commitments | Director approved | DLFL once tag is confirmed complete PM | Email CIRT when complete |  | WECC | South | Non-WSIP | [6 empty] | '-120.421441 | 36.4352 | ETL.6010 | 40741133 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 23
118008703 | MARTIN-MILLBRAE#1 1/15 RPR BENT MEMBERS | 44273546 | MARTIN-MILLBRAE #1 | 001/015 | ICQ | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-122.40837 | 37.6771 | ETL.2230 | 40755337 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 1 | SMCPD
118009204 | SAN MATEO-MARTIN#3 9/74 RPR FOND | 44483397 | SAN MATEO-MARTIN #3 | 009/074 | ICQ | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-122.408463 | 37.6767 | ETL.3580 | 40755309 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 5 | SMCPD
118010598 | T2 HUMBOLDT-BRIDGEVILL 112/004R RPL POLE | 31497841 | HUMBOLDT-BRIDGEVILLE | 112/004 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | Non-WSIP | FSRP | [7 empty] | ETL.1810 | 44322683 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2020-01-16
118010697 | T2 HUMBOLDT-BRIDGLE 111/005R RPL POLE | 31497841 | HUMBOLDT-BRIDGEVILLE | 111/005 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | Non-WSIP | FSRP | [7 empty] | ETL.1810 | 44322670 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2020-01-16
118010755 | LOS BANOS-GATES#1 69/290 RPL INSS |  | LOS BANOS-GATES #1 | 069/290 | 93K | E | Pre-2020_(1b) Lines with special commitments | Director approved | DLFL once tag is confirmed complete PM 74008747 | Email CIRT when complete |  | LATE | South | Non-WSIP | [6 empty] | '-120.254091 | 36.2788 | ETL.6000 | 40633994 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 16
118010994 | LOS BANOS-MIDWAY#2 48/201 RPL INSS | 31527140 | LOS BANOS-MIDWAY #2 | 048/201 | 93K | F | Pre-2020_(1b) Lines with special commitments | Director approved | DLFL once tag is confirmed complete PM | Email CIRT when complete |  | WECC | South | Non-WSIP | [6 empty] | '-120.498531 | 36.512 | ETL.6010 | 40612790 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 23
118011030 | LOS BANOS-MIDWAY#2 48/201 RPL HRDT | 44300848 | LOS BANOS-MIDWAY #2 | 048/201 | ICQ | E | Pre-2020_(1b) Lines with special commitments |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.498212 | 36.5121 | ETL.6010 | 40587751 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 26
118011326 | HUMBOLDT-BRIDGEVILLE 110/8 PAINT CRSM | 44107184 | HUMBOLDT-BRIDGEVILLE | 110/008 | ICW | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  |  | LATE | North Coast | Non-WSIP | [6 empty] | '-124.024353 | 40.7609 | ETL.1810 | 44322650 | Crossarm-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2020-01-16
118011415 | EI HUMBOLDT-BRIDGEVILLE 112/006 PNT STRW | 44107184 | HUMBOLDT-BRIDGEVILLE | 112/006 | ICW | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  |  | LATE | North Coast | WSIP | [8 empty] | ETL.1810 | 44322689 | Crossarm-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2020-01-16
118011416 | HUMBOLDT-BRIDGEVILLE 110/7 PAINT STRS | 44208367 | HUMBOLDT-BRIDGEVILLE | 110/007 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  |  | LATE | North Coast | Non-WSIP | [6 empty] | '-124.021991 | 40.7609 | ETL.1810 | 44322647 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Eureka |  |  | 2020-01-16
118011419 | HUMBOLDT-BRIDGEVILLE 112/001 PNT CRSAM | 44107184 | HUMBOLDT-BRIDGEVILLE | 112/001 | ICW | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  |  | LATE | North Coast | WSIP | [8 empty] | ETL.1810 | 44322672 | Crossarm-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2020-01-16
118011452 | LOS BANOS-MIDWAY#2 37/157 RPL INSS | 31527140 | LOS BANOS-MIDWAY #2 | 037/157 | 93K | F | Pre-2020_(1b) Lines with special commitments | Director approved | DLFL once tag is confirmed complete PM | Email CIRT when complete |  | WECC | South | Non-WSIP | [6 empty] | '-120.63318 | 36.6134 | ETL.6010 | 40836799 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 23
118011453 | HUMBOLDT-BRIDGEVILLE 88/001 PAINT STRS | 44208367 | HUMBOLDT-BRIDGEVILLE | 088/001 | ICS | E | Pre-2020_(9a) Other ignition related |  |  |  |  | LATE | North Coast | WSIP | [6 empty] | '-123.811986 | 40.5032 | ETL.1810 | 44322238 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Eureka |  |  | 2020-01-16
118011457 | HUMBOLDT-BRIDGEVILLE 113/000 PNT STR | 44107184 | HUMBOLDT-BRIDGEVILLE | 113/000 | ICW | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  |  | LATE | North Coast | WSIP | [8 empty] | ETL.1810 | 44322701 | Crossarm-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2020-01-16
118011561 | HUMBOLDT-BRIDGEVILLE 115/001 PNT STRS | 44311169 | HUMBOLDT-BRIDGEVILLE | 115/001 | ICS | E | Pre-2020_(9a) Other ignition related |  |  |  |  | LATE | North Coast | WSIP | [6 empty] | '-124.09794 | 40.7788 | ETL.1810 | 43691598 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Eureka |  |  | 2020-01-16
118011564 | HUMBOLDT-BRIDGEVILLE 113/002 PNT STRS | 44107184 | HUMBOLDT-BRIDGEVILLE | 113/002 | ICW | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  |  | LATE | North Coast | WSIP | [8 empty] | ETL.1810 | 44322709 | Crossarm-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2020-01-16
118014089 | T2 EI PITTSBURG-CLMBIA STL 4/24 RPR INSS | 44379347 | PITTSBURG-COLUMBIA STEEL | 004/024 | ICS | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-121.884568 | 37.9878 | ETL.3300 | 44761258 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - 1
118016814 | GLENN #5 005/112 RPL POLE | 31475727 | GLENN #5 | 005/112 | 70Y | B | Pre-2020_(9c) Time-dependent non-HFTD tags, (last year and later) |  |  |  |  | LATE | North Valley | Non-WSIP | FSRP | [5 empty] | '-122.197462 | 39.7421 | ETL.8427 | 40738645 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain
118017378 | T2 BUTTE VALLEY-CARIBOU 7/053A RPL L PL | 31479584 | BUTT VALLEY-CARIBOU | 007/053A | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | Non-WSIP | [8 empty] | ETL.1180 | 44399493 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS erdy | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain
118021920 | T2NT VALLEY SPRINGS #1 007/137 INST MRKW | 44292021 | VALLEY SPRINGS #1 | 007/137 | ICW | F | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | Central | Non-WSIP | [6 empty] | '-120.856946 | 38.1519 | ETL.8210 | 40905600 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 23
118021996 | T2NT VALLEY SPRINGS #1 04/086 INST MRKW | 44292023 | VALLEY SPRINGS #1 | 004/086 | ICW | F | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | Central | Non-WSIP | [6 empty] | '-120.829894 | 38.1801 | ETL.8210 | 40903817 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 23
118026607 | T2 TULUCAY-NAPA #1 007/005 RPR POLE | 44310753 | TULUCAY-NAPA #1 | 007/005 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-122.206774 | 38.268 | ETL.8180 | 40751173 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
118057983 | HUMBOLDT-BRIDGEVILLE 107/002 RPR WP HOLE | 43749687 | HUMBOLDT-BRIDGEVILLE | 107/002 | ICW | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  |  | LATE | North Coast | Non-WSIP | [8 empty] | ETL.1810 | 44322575 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2020-01-16
118057985 | HUMBOLDT-BRIDGEVILLE 107/002 RPR GYWW | 43749687 | HUMBOLDT-BRIDGEVILLE | 107/002 | ICW | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  |  | LATE | North Coast | Non-WSIP | [8 empty] | ETL.1810 | 44322575 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2020-01-16
118057992 | HUMBOLDT-BRIDGEVILLE 107/002 RPL HRDD | 43749687 | HUMBOLDT-BRIDGEVILLE | 107/002 | ICW | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  |  | LATE | North Coast | Non-WSIP | [8 empty] | ETL.1810 | 44322576 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2020-01-16
118058011 | HUMBOLDT-BRIDGEVILLE 107/002 RPL INSW | 31498302 | HUMBOLDT-BRIDGEVILLE | 107/002 | 93I | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  |  | LATE | North Coast | Non-WSIP | [6 empty] | '-123.964884 | 40.7452 | ETL.1810 | 40720047 | Insulator-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Eureka |  |  | 2020-01-16
118058083 | HUMBOLDT-BRIDGEVILLE 107/001R RPL POLE | 31404623 | HUMBOLDT-BRIDGEVILLE | 107/001 | 70Y | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  |  | LATE | North Coast | Non-WSIP | [8 empty] | ETL.1810 | 44322573 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2020-01-16
118058602 | HUMBOLDT-BRIDGEVILLE 105/002 RPR GYWW | 43749687 | HUMBOLDT-BRIDGEVILLE | 105/002 | ICW | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  |  | LATE | North Coast | Non-WSIP | [8 empty] | ETL.1810 | 44322544 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2020-01-16
118060048 | HUMBOLDT-BRIDGEVILLE 096/004 RMV DEBRIS | 44378879 | HUMBOLDT-BRIDGEVILLE | 096/004 | ICW | E | Pre-2020_(9a) Other ignition related |  |  |  |  | LATE | North Coast | Non-WSIP | [6 empty] | '-123.863309 | 40.6183 | ETL.1810 | 44324153 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2020-01-16
118060261 | HUMBOLDT-BRIDGEVILLE 096/003 RMV DEBRIS | 44378879 | HUMBOLDT-BRIDGEVILLE | 096/003 | ICW | E | Pre-2020_(9a) Other ignition related |  |  | Likely MAT error - delink to correct |  | LATE | North Coast | Non-WSIP | [6 empty] | '-123.861664 | 40.6165 | ETL.1810 | 44324147 | Structure-Steel | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Eureka |  |  | 2020-01-16
118060521 | HUMBOLDT-BRIDGEVILLE 098/001 RPR GYWW | 43749687 | HUMBOLDT-BRIDGEVILLE | 098/001 | ICW | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  |  | LATE | North Coast | Non-WSIP | [8 empty] | ETL.1810 | 44322385 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2020-01-16
118069310 | CLAY MARTEL 31/12 RPR SWITCH | 44073627 | CLAY-MARTEL | 031/012 | ICE | E | Pre-2020_(9a) Other ignition related |  |  |  |  | LATE | Central | Non-WSIP | FSRP | [5 empty] | '-120.845487 | 38.4828 | ETL.8250 | 40744160 | Switch | Out of Adjustment | Repair | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 623 | Victor |  | Y - 39
118069451 | T2 DI COLGATE-PALERMO 022/440 RPR STRW | 43728969 | COLGATE-PALERMO | 022/440 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.516851 | 39.458 | ETL.6500 | 40692851 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
118069464 | LOS BANOS-GATES #1 80/339 RPR GYWS | 43848347 | LOS BANOS-GATES #1 | 080/338A | ICS | E | Pre-2020_(1b) Lines with special commitments |  |  | Tower guy |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.129484 | 36.1454 | ETL.6000 | 40576536 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Fresno |  | Y - 17
118075840 | LOS BANOS-GATES #1 79/332 RPR STRT | 44300852 | LOS BANOS-GATES #1 | 079/332 | ICQ | E | Pre-2020_(1b) Lines with special commitments |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.14335 | 36.1637 | ETL.6000 | 40673627 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 17
118083452 | HUMBOLDT-BRIDGEVILLE 105/2 RPR GYWW | 43749687 | HUMBOLDT-BRIDGEVILLE | 105/002 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | North Coast | WSIP | [8 empty] | ETL.1810 | 44322546 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2020-01-16
118084193 | HUMBOLDT-BRIDGEVILLE 098/001 RPR GYWW | 43749687 | HUMBOLDT-BRIDGEVILLE | 098/001 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | North Coast | WSIP | [8 empty] | ETL.1810 | 44322386 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2020-01-16
118084195 | HUMBOLDT-BRIDGEVILLE 098/001 RPR GYWW | 43749687 | HUMBOLDT-BRIDGEVILLE | 098/001 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | North Coast | WSIP | [8 empty] | ETL.1810 | 44322387 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2020-01-16
118084196 | HUMBOLDT-BRIDGEVILLE 105/002 RPR GYWW | 43749687 | HUMBOLDT-BRIDGEVILLE | 105/002 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | North Coast | WSIP | [8 empty] | ETL.1810 | 44322545 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2020-01-16
118084407 | T2 EI FORT BRAGG-ELK 13/8 RPL COND | 31482836 | FORT BRAGG-ELK | 013/008 | 93C | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.78927 | 39.3052 | ETL.2060 | 40860782 | Conductor-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 638 | Lakeville
118084828 | HUMBOLDT-BRIDGEVILLE 107/2 RPR GYWW | 43749687 | HUMBOLDT-BRIDGEVILLE | 107/002 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | North Coast | WSIP | [8 empty] | ETL.1810 | 44322576 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2020-01-16
118084829 | HUMBOLDT-BRIDGEVILLE 107/2 RPR WP HOLE | 43749687 | HUMBOLDT-BRIDGEVILLE | 107/002 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | North Coast | WSIP | [8 empty] | ETL.1810 | 44322577 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2020-01-16
118085072 | HUMBOLDT-BRIDGEVILLE 108/005 PNT STRS | 44107184 | HUMBOLDT-BRIDGEVILLE | 108/005 | ICW | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  |  | LATE | North Coast | Non-WSIP | [6 empty] | '-123.982845 | 40.7519 | ETL.1810 | 44324318 | Crossarm-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2020-01-16
118085073 | HUMBOLDT-BRIDGEVILLE 109/008 PNT CRSM | 44107184 | HUMBOLDT-BRIDGEVILLE | 109/008 | ICW | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  |  | LATE | North Coast | Non-WSIP | [6 empty] | '-124.003507 | 40.7586 | ETL.1810 | 44322623 | Crossarm-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2020-01-16
118085074 | HUMBOLDT-BRIDGEVILLE 110/003 PNT CRSM | 44107184 | HUMBOLDT-BRIDGEVILLE | 110/003 | ICW | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  |  | LATE | North Coast | Non-WSIP | [6 empty] | '-124.013775 | 40.7607 | ETL.1810 | 44322635 | Crossarm-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2020-01-16
118085664 | HUMBOLDT-BRIDGEVILLE 099/008 RMV DEBRIS | 43749687 | HUMBOLDT-BRIDGEVILLE | 099/008 | ICW | E | Pre-2020_(9a) Other ignition related |  |  |  |  | LATE | North Coast | Non-WSIP | [8 empty] | ETL.1810 | 44322429 | Structure-Wood | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2020-01-16
118085859 | HMBLDT-BRDGVL 107/002 RPR GYWW | 43749687 | HUMBOLDT-BRIDGEVILLE | 107/002 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | North Coast | WSIP | [8 empty] | ETL.1810 | 44322577 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2020-01-16
118085991 | LOS BANOS-GATES #1 77/326 RPR INSS | 44301827 | LOS BANOS-GATES #1 | 077/326 | ICS | E | Pre-2020_(1b) Lines with special commitments |  | DLFL once tag is confirmed complete PM 74008747 | Email CIRT when complete |  | LATE | South | Non-WSIP | [6 empty] | '-120.158573 | 36.1815 | ETL.6000 | 40820405 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  | Y - 16
118086072 | HUMBOLDT-BRIDGEVILLE 107/001C RPL POLE | 31404623 | HUMBOLDT-BRIDGEVILLE | 107/001 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | North Coast | WSIP | [8 empty] | ETL.1810 | 44322572 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2020-01-16
118086075 | HUMBOLDT-BRIDGEVILLE 107/002 RPR WP HOLE | 43749687 | HUMBOLDT-BRIDGEVILLE | 107/002 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | North Coast | WSIP | [8 empty] | ETL.1810 | 44322576 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2020-01-16
118090554 | LOS BANOS-GATES #1 75/317 RPR STRT | 44300852 | LOS BANOS-GATES #1 | 075/317 | ICQ | F | Pre-2020_(1b) Lines with special commitments |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.179424 | 36.2074 | ETL.6000 | 40817423 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 17
118090993 | HUMBOLDT-BRIDGEVILL 100/003L RPL POLE | 31497841 | HUMBOLDT-BRIDGEVILLE | 100/003 | 70Y | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  |  | LATE | North Coast | Non-WSIP | [8 empty] | ETL.1810 | 44322441 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2020-01-16
118092122 | T2 WISHON-COPPERMINE 07/056 REGRADE | 44300844 | WISHON-COPPERMINE | 007/056 | ICQ | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.55012 | 37.047 | ETL.9330 | 40816710 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 12
118092358 | HUMBOLDT-BRIDGEVILLE 102/001L RPL POLE | 31497841 | HUMBOLDT-BRIDGEVILLE | 102/001 | 70Y | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  |  | LATE | North Coast | Non-WSIP | [8 empty] | ETL.1810 | 44322484 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2020-01-16
118092846 | T2NT ARCO-PLNIO PSS PP 15/256 RMV DBRIS | 44609889 | ARCO-POLONIO PASS PP | 015/256 | ICW | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 |  | South | Non-WSIP | [6 empty] | '-120.113399 | 35.7083 | ETL.8450 | 41148788 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Midway |  | Y - 7
118098389 | T3 EI MDL FRK-GOLD HILL 33/241 PNT STRS | 44082912 | MIDDLE FORK-GOLD HILL | 033/241 | ICS | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  |  | LATE | North Valley | WSIP | [6 empty] | '-120.995025 | 38.7311 | ETL.5140 | 44377466 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento
118098415 | HMBLDT-BRDGVL 102/001R RPL STRW | 31497841 | HUMBOLDT-BRIDGEVILLE | 102/001 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | North Coast | WSIP | [8 empty] | ETL.1810 | 44322485 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2020-01-16
118098461 | HMBLDT-BRDGVL 100/003R RPLC STRW | 31497841 | HUMBOLDT-BRIDGEVILLE | 100/003 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | North Coast | WSIP | [8 empty] | ETL.1810 | 44322443 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2020-01-16
118098464 | HMBLDT-BRDGVL 100/003C RPLC STRW | 31497841 | HUMBOLDT-BRIDGEVILLE | 100/003 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | North Coast | WSIP | [8 empty] | ETL.1810 | 44322442 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2020-01-16
118104065 | HMBLDT-BRDGVILLE 114/003 PAINT CRSARM | 44107184 | HUMBOLDT-BRIDGEVILLE | 114/003 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | North Coast | Non-WSIP | FSRP | [7 empty] | ETL.1810 | 44322742 | Crossarm-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2020-01-16
118104377 | T2 COALINGA #1-SAN MIGUEL 22/1 RPR STRT | 44140483 | COALINGA #1-SAN MIGUEL | 022/001 | ICQ | E | Pre-2020_(4) TD tag on high spread line |  |  | Likely MAT error - delink to correct | TR2 | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.63573 | 35.9682 | ETL.8580 | 40597797 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Pismo Beach |  | Y - 15
118106502 | T2 CHRISTIE-WILLOW PASS 3/37 INS DAMW | 44221598 | CHRISTIE-WILLOW PASS | 003/037 | ICW | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | Central | Non-WSIP | FSRP | [5 empty] | '-122.156699 | 38.0185 | ETL.6370 | 40825343 | Damper-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Bay |  |  | CSRS
118106551 | T2 CHRISTIE-WILLOW PASS 2/029 INS DAMW | 44221598 | CHRISTIE-WILLOW PASS | 002/029 | ICW | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | Central | Non-WSIP | FSRP | [5 empty] | '-122.163387 | 38.0206 | ETL.6370 | 40599510 | Damper-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Bay |  |  | CSRS
118106651 | T2 HASS-MCCALL 014/080 INST INSS | 31480611 | HAAS-MCCALL | 014/080 | 93K | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | South | Non-WSIP | FSRP | [5 empty] | '-119.2495056 | 36.8627 | ETL.4850 | 40633389 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno
118107045 | T2 CAYUCOS-CAMBRIA 11/073 INSTL DAMW | 43753055 | CAYUCOS-CAMBRIA | 011/073 | ICW | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | South | Non-WSIP | [6 empty] | '-121.015154 | 35.5451 | ETL.8560 | 40754943 | Damper-Wood | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - 13
118107112 | T2 CAYUCOS-CAMBRIA 12/082 INSTL DAMW | 43753055 | CAYUCOS-CAMBRIA | 012/082 | ICW | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | South | Non-WSIP | [6 empty] | '-121.031851 | 35.5562 | ETL.8560 | 40812347 | Damper-Wood | Missing | Install | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - 13
118115376 | LOS BANOS-GATES #1 055/234 INST ACG | 31480609 | LOS BANOS-GATES #1 | 055/234 | 93A | F | Pre-2020_(1b) Lines with special commitments |  |  |  |  | WECC | South | Non-WSIP | [6 empty] | '-120.415851 | 36.4288 | ETL.6000 | 40757937 | Structure-Tower | Anti-Climbing Guard | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Capital | 988 | Fresno |  | Y - 17
118116425 | LOS BANOS-GATES #1 054/229 INST HRDT | 44300852 | LOS BANOS-GATES #1 | 054/229 | ICQ | E | Pre-2020_(1b) Lines with special commitments |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.427434 | 36.4416 | ETL.6000 | 40866820 | Hardware-Tower | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 17
118117045 | T2 BRIDGEVILLE-COTTONWOO 13/124A STUB P | 44143774 | BRIDGEVILLE-COTTONWOOD | 013/124 | GAR | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-122.520412 | 40.3946 | ETL.1110 | 44424060 | Structure-Wood | Rotten | Stub | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Contract | Expense | 586 | Table Mountain |  |  | Yes
118118571 | CNTRVLLE-TBLE MTN-ORVLLE 9/190 RPL PL | 31478313 | CENTERVILLE-TABLE MTN-OROVILLE | 009/190 | 70Y | F | Pre-2020_(5) TD tag on other lines | [5 empty] | North Valley | Non-WSIP | [6 empty] | '-121.635677 | 39.6535 | ETL.6330 | 40758836 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
118118847 | TRACY-LOS BANOS 50/227 INST RPTS |  | TRACY-LOS BANOS | 050/227 | ICB | E | Pre-2020_(9a) Other ignition related |  |  |  |  | LATE | Central | WSIP | FSRP | [5 empty] | '-121.106254 | 37.2127 | ETL.6130 | 40811400 | Raptor Guard-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 593 | Victor
118118890 | TRACY-LOS BANOS 42/191 INST RPTS |  | TRACY-LOS BANOS | 042/191 | ICB | F | Pre-2020_(9a) Other ignition related |  |  |  |  | LATE | Central | WSIP | FSRP | [5 empty] | '-121.145839 | 37.3314 | ETL.6130 | 40587649 | Raptor Guard-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 593 | Victor
118118891 | TRACY-LOS BANOS 38/178 INST RPTS |  | TRACY-LOS BANOS | 038/178 | ICB | E | Pre-2020_(9a) Other ignition related |  |  |  |  | LATE | Central | WSIP | FSRP | [5 empty] | '-121.162545 | 37.3813 | ETL.6130 | 40863863 | Raptor Guard-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 593 | Victor
118119027 | TRACY-LOS BANOS 021/103 INST RPTS |  | TRACY-LOS BANOS | 021/103 | ICB | E | Pre-2020_(9a) Other ignition related |  |  |  |  | LATE | Central | WSIP | FSRP | [5 empty] | '-121.333564 | 37.5775 | ETL.6130 | 40662852 | Raptor Guard-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 593 | Victor
118123322 | DRM-GRSS VLLY-WIMR B16/361 INS GMKW | 44090176 | DRUM-GRASS VALLEY-WEIMAR | B016/361 | ICW | F | Pre-2020_(4b) On structure in bucket 4 | [5 empty] | North Valley | Non-WSIP | [6 empty] | '-120.955831 | 39.118 | ETL.6760 | 40822707 | Guy Wire Mark /Indic-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento |  |  | Yes
118123781 | T2NT VALLEY SPRINGS #1 01/30 INST MRKW | 44292024 | VALLEY SPRINGS #1 | 001/030 | ICW | F | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | Central | Non-WSIP | [6 empty] | '-120.787994 | 38.2053 | ETL.8210 | 40904197 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 23
118124179 | HUMBOLDT-TRINITY 076/000LFT RPL POLE | 31497850 | HUMBOLDT-TRINITY | 076/000 | 70Y | E | Pre-2020_(2) High fire spread TD |  |  |  |  | LATE | North Coast | Non-WSIP |  |  |  |  | Project | 2021 HUMBOLDT-TRINITY | '-123.442836 | 40.6977 | ETL.1820 | 44565478 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2020-05-21
118124411 | HUMBOLDT-TRINITY 076/000CNTR RPL POLE | 31497850 | HUMBOLDT-TRINITY | 076/000 | 70Y | E | Pre-2020_(2) High fire spread TD |  |  |  |  | LATE | North Coast | Non-WSIP |  |  |  |  | Project | 2021 HUMBOLDT-TRINITY | '-123.442836 | 40.6977 | ETL.1820 | 44565611 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2020-05-21
118126037 | LOS BANOS-GATES #1 035/147 BENT MEMB | 44300852 | LOS BANOS-GATES #1 | 035/147 | ICQ | F | Pre-2020_(1b) Lines with special commitments |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.660935 | 36.6438 | ETL.6000 | 40816033 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 17
118126552 | LOS BANOS-GATES #1 033/142 BENT MEMB | 44300852 | LOS BANOS-GATES #1 | 033/142 | ICQ | E | Pre-2020_(1b) Lines with special commitments |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.672518 | 36.6586 | ETL.6000 | 40680385 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 17
118134718 | TULUCAY-NAPA #1 9/2 RPR STRW | 44310753 | TULUCAY-NAPA #1 | 009/002 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | North Coast | Non-WSIP | [6 empty] | '-122.227382 | 38.2844 | ETL.8180 | 40658491 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
118134767 | TULUCAY-NAPA #1 9/2 INST GATE |  | TULUCAY-NAPA #1 | 009/002 | 71Y | F | Pre-2020_(4b) On structure in bucket 4 | [5 empty] | North Coast | Non-WSIP | [6 empty] | '-122.227382 | 38.2844 | ETL.8180 | 40658491 | Fence / Gate | Missing | Install |  |  |  |  | PEND | LC | TLR | Roads | Capital | 374 | Lakeville
118138629 | LOS BANOS-GATES #1 31/132 RPR FOND | 44300852 | LOS BANOS-GATES #1 | 031/132 | ICQ | F | Pre-2020_(1b) Lines with special commitments |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.691267 | 36.6929 | ETL.6000 | 40676067 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 17
118138697 | LOS BANOS-GATES #1 31/131 RPR STRT | 44300852 | LOS BANOS-GATES #1 | 031/131 | ICQ | E | Pre-2020_(1b) Lines with special commitments |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.693225 | 36.6965 | ETL.6000 | 40592015 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 17
118139036 | LOS BANOS-GATES #1 29/124 RPR STRT | 44300852 | LOS BANOS-GATES #1 | 029/124 | ICQ | F | Pre-2020_(1b) Lines with special commitments |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.70645 | 36.7208 | ETL.6000 | 40759096 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 17
118139534 | LOS BANOS-GATES #1 28/120 RPR STRT | 44300852 | LOS BANOS-GATES #1 | 028/120 | ICQ | F | Pre-2020_(1b) Lines with special commitments |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.713992 | 36.7346 | ETL.6000 | 40600075 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 17
118165045 | WEBER-FRENCH CAMP #1 001/026 INS MRKW | 44623405 | WEBER #1 | 001/026 | ICW | F | Pre-2020_(5b) On structure in bucket 5 | [5 empty] | Central | Non-WSIP | [6 empty] | '-121.255521 | 37.9122 | ETL.8320 | 40804098 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 4
118165078 | WEBER-FRENCH CAMP #1 001/026 RPL ANCW | 44595064 | WEBER #1 | 001/026 | ICW | E | Pre-2020_(5b) On structure in bucket 5 |  |  |  |  | LATE | Central | Non-WSIP | [6 empty] | '-121.255521 | 37.9122 | ETL.8320 | 40804098 | Anchor-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 4
118165702 | WEBER-FRENCH CAMP #1 002/045 INS MRKW | 44595065 | WEBER #1 | 002/045 | ICW | F | Pre-2020_(5b) On structure in bucket 5 | [5 empty] | Central | Non-WSIP | [6 empty] | '-121.27385 | 37.9063 | ETL.8320 | 40857166 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 4
118165943 | T2 EI TULUCAY-NAPA #1 7/6 INST HRDW | 44310753 | TULUCAY-NAPA #1 | 007/006 | ICW | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.207683 | 38.2692 | ETL.8180 | 40821522 | Hardware-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
118167074 | WEBER-FRENCH CAMP #1 001/026 RPR GYWW | 44631075 | WEBER #1 | 001/026 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-121.255521 | 37.9122 | ETL.8320 | 40804098 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 4
118176637 | T2 BUTTE VALLEY-CARIBOU 7/53A C RPL POLE | 31479584 | BUTT VALLEY-CARIBOU | 007/053A | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [8 empty] | ETL.1180 | 44399494 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS erdy | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain
118176639 | T2 BUTTE VALLEY-CARIBOU 7/53A RPL R POLE | 31479584 | BUTT VALLEY-CARIBOU | 007/053A | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [8 empty] | ETL.1180 | 44399495 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS erdy | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain
118177783 | T2 BRIDGEVILLE-CTTNWD 66/481 RMV DEBRIS | 44143776 | BRIDGEVILLE-COTTONWOOD | 066/481 | ICS | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.465033 | 40.4234 | ETL.1110 | 44424646 | Structure-Steel | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Eureka
118178177 | CORDELIA #2 TAP 03/064 RPL POLE | 31472910 | CORDELIA #2 TAP | 003/064 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | North Valley | Non-WSIP | [6 empty] | '-122.151767 | 38.2491 | ETL.8184 | 40576417 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento
118179195 | T2 BRIDGEVILLE-CTTNWD 079/561 RMV DEBRIS | 44106807 | BRIDGEVILLE-COTTONWOOD | 079/561 | ICS | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | Non-WSIP | FSRP | [5 empty] | '-123.65761 | 40.4784 | ETL.1110 | 44512081 | Structure-Steel | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Eureka |  |  | 2020-01-17
118185065 | BRIDGEVILLE-COTTONWOOD 76/545 RMV BUTT | 44299811 | BRIDGEVILLE-COTTONWOOD | 076/545 | ICW | F | Pre-2020_(9a) Other ignition related |  |  |  |  | LATE | North Coast | Non-WSIP | [6 empty] | '-120.11496 | 36.8181 | ETL.1110 | 44424608 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2020-01-17
118185921 | T2 BRIDGEVILLE-CTTNWD 73/530 RMV BUTT | 44310757 | BRIDGEVILLE-COTTONWOOD | 073/530 | ICS | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.566011 | 40.4804 | ETL.1110 | 44744836 | Structure-Steel | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Eureka |  |  | 2020-01-17
118185922 | T2 BRIDGEVLLE-CTTNWD 73/531 RMV BUTT | 44310757 | BRIDGEVILLE-COTTONWOOD | 073/531 | ICS | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.568275 | 40.4815 | ETL.1110 | 44553105 | Structure-Steel | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Eureka |  |  | 2020-01-17
118186213 | HUMBOLDT-BRIDGEVILLE 99/7 RPR INSS | 44107184 | HUMBOLDT-BRIDGEVILLE | 099/007 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | North Coast | Non-WSIP | [6 empty] | '-120.117321 | 36.0931 | ETL.1810 | 43691636 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2020-01-16
118186218 | T2 BRIDGEVILLE-CTTNWD 73/528 RMV BUTT | 44299811 | BRIDGEVILLE-COTTONWOOD | 073/528 | ICW | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.5595578 | 40.4772 | ETL.1110 | 44423942 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
118186266 | T2 BRIDGEVILLE-CTTNWD 73/527 RMV BUTT | 44143777 | BRIDGEVILLE-COTTONWOOD | 073/527 | ICW | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.5574395 | 40.4762 | ETL.1110 | 44423352 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
118186305 | T2 BRIDGEVILLE-CTTNWD 72/525 RMV BUTT | 44143777 | BRIDGEVILLE-COTTONWOOD | 072/525 | ICW | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.5525556 | 40.4738 | ETL.1110 | 44740684 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
118186334 | T2 BRIDGEVILLE-CTTNWD 72/524 RMV DEBRIS | 44143777 | BRIDGEVILLE-COTTONWOOD | 072/524 | ICW | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.5511086 | 40.4731 | ETL.1110 | 44424508 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
118186385 | T2 BRIDGEVILLE-CTTNWD 72/523 RMV DBRIS | 44299811 | BRIDGEVILLE-COTTONWOOD | 072/523 | ICW | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.5485371 | 40.4718 | ETL.1110 | 44424376 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2020-01-17
118186695 | HAT CREEK #1-WESTWOOD 26/508 RPL POLE | 31504249 | HAT CREEK #1-WESTWOOD | 026/508 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  | Likely MAT error - delink to correct |  | LATE | North Valley | Non-WSIP | [6 empty] | '-121.194835 | 40.6708 | ETL.7030 | 40616910 | Structure-Wood | Rotten | Stub | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Table Mountain
118186698 | T2 PARADISE-TABLE MTN 6/56AB STUB POLE |  | PARADISE-TABLE MTN | 006/055AB | GAR | E | 2020_(1a) PSPS |  |  |  | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-121.537939 | 39.5476 | ETL.4316 | 44383157 | Structure-Wood | Rotten | Stub |  |  |  |  | PEND | LC | TLX | Contract | Expense | 586 | Table Mountain
118187329 | HUMBOLDT-BRIDGEVILLE 99/02C INST IBWW | 43749687 | HUMBOLDT-BRIDGEVILLE | 099/002 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | North Coast | Non-WSIP | [6 empty] | '-123.8932644 | 40.6441 | ETL.1810 | 44322410 | Insulator Bond Wire-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2020-01-16
118187369 | HUMBOLDT-BRIDGEVILLE 99/02C RPR WP HOLE | 43749687 | HUMBOLDT-BRIDGEVILLE | 099/002 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | North Coast | Non-WSIP | [6 empty] | '-123.8932644 | 40.6441 | ETL.1810 | 44322410 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2020-01-16
118187390 | HUMBOLDT-BRIDGEVILLE 99/02L RPR JUMW | 43749687 | HUMBOLDT-BRIDGEVILLE | 099/002 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | North Coast | Non-WSIP | [6 empty] | '-123.8932644 | 40.6441 | ETL.1810 | 44322409 | Jumper-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2020-01-16
118187763 | HUMBOLDT-BRIDGEVILLE 96/04 INST DAMS | 44107184 | HUMBOLDT-BRIDGEVILLE | 096/004 | ICW | E | Pre-2020_(9a) Other ignition related |  |  |  |  | LATE | North Coast | Non-WSIP | [6 empty] | '-123.863309 | 40.6183 | ETL.1810 | 44324153 | Damper-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2020-01-16
118187929 | HUMBOLDT-BRIDGEVILLE 099/007 PNT CRSM | 44107184 | HUMBOLDT-BRIDGEVILLE | 099/007 | ICW | E | Pre-2020_(4b) On structure in bucket 4 |  |  |  |  | LATE | North Coast | Non-WSIP | [6 empty] | '-123.901921 | 40.6479 | ETL.1810 | 44322426 | Crossarm-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2020-01-16
118188951 | T2 BRIDGEVILLE-CTTNWD 71/515 RMV DEBRIS | 44143776 | BRIDGEVILLE-COTTONWOOD | 071/515 | ICS | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.528872 | 40.4681 | ETL.1110 | 44814455 | Structure-Steel | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Eureka
118189071 | T2 BRIDGEVILLE-CTTNWD 03/29L RPL POLE | 31485141 | BRIDGEVILLE-COTTONWOOD | 003/029 | 70Y | E | 2020_(1a) PSPS |  |  |  | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-122.325294 | 40.391 | ETL.1110 | 44423198 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
118190056 | T2 BRIDGEVILLE-CTTNWD 69/501 RMV BUTT | 44299811 | BRIDGEVILLE-COTTONWOOD | 069/501 | ICW | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.498437 | 40.4519 | ETL.1110 | 44510516 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2020-01-17
118190143 | T2 BRIDGEVILLE-CTTNWD 69/498 RMV BUTT | 44299811 | BRIDGEVILLE-COTTONWOOD | 069/498 | ICW | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.494471 | 40.4487 | ETL.1110 | 44510553 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2020-01-17
118190241 | T2 BRIDGEVILLE-CTNWD 69/497 RMV BUTT | 44299811 | BRIDGEVILLE-COTTONWOOD | 069/497 | ICW | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.493193 | 40.4476 | ETL.1110 | 44510624 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2020-01-17
118195339 | BRIDGEVILLE-COTTONWOOD 03/29R RPL POLE | 31485141 | BRIDGEVILLE-COTTONWOOD | 003/029 | 70Y | E | 2020_(1a) PSPS |  |  |  |  | LATE | North Valley | Non-WSIP | [6 empty] | '-122.325294 | 40.391 | ETL.1110 | 44423199 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Yes
118195719 | HUMBOLDT-BRIDGEVILLE 99/2R RPR JUMW | 43749687 | HUMBOLDT-BRIDGEVILLE | 099/002 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | North Coast | Non-WSIP | [6 empty] | '-123.842729 | 40.5606 | ETL.1810 | 44322411 | Jumper-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2020-01-16
118195881 | HUMBOLDT-BRIDGEVILLE 99/2C RPR JUMW | 43749687 | HUMBOLDT-BRIDGEVILLE | 099/002 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  |  | LATE | North Coast | Non-WSIP | [8 empty] | ETL.1810 | 44322410 | Jumper-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2020-01-16
118196173 | T2 SMARTVILLE-CAMP FR WST A1/18 RPL POLE | 31479591 | SMARTVILLE-CAMP FAR WEST | A001/018 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-121.301809 | 39.0412 | ETL.7970 | 40666683 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
118199811 | IGNCIO-ALTO-SUSLITO #1 12/82 PAINT STRT | 44586160 | IGNACIO-ALTO-SAUSALITO #1 | 012/082 | ICX | E | Pre-2020_(9a) Other ignition related |  |  | Likely MAT error - delink to correct |  | LATE | North Coast | Non-WSIP | [6 empty] | '-122.519722 | 37.9017 | ETL.7160 | 40812969 | Structure-Tower | Paint/Coating | Repaint | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense |  | Lakeville
118199814 | T2 BRIDGEVILLE-CTNWD 70/505 RMV DEBRIS | 44299811 | BRIDGEVILLE-COTTONWOOD | 070/505 | ICW | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.5076161 | 40.4592 | ETL.1110 | 44510576 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2020-01-17
118199818 | T2 BRIDGEVILLE-CTNWD 70/504 RMV BUTT | 44299811 | BRIDGEVILLE-COTTONWOOD | 070/504 | ICW | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.5062419 | 40.4581 | ETL.1110 | 44423343 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2020-01-17
118199861 | T2 BRIDGEVILLE-CTNWD 70/510 RMV BUTT | 44299811 | BRIDGEVILLE-COTTONWOOD | 070/510 | ICW | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.5156462 | 40.4657 | ETL.1110 | 44510621 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2020-01-17
118199874 | T2 BRIDGEVILLE-CTNWD 70/506 RMV DEBRIS | 44299811 | BRIDGEVILLE-COTTONWOOD | 070/506 | ICW | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.5107748 | 40.4618 | ETL.1110 | 44510607 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2020-01-17
118200367 | T2 BRIDGEVILLE-CTTNWD 82/575 CANCEL | 44143776 | BRIDGEVILLE-COTTONWOOD | 082/575 | ICS | E | Pre-2020_(9a) Other ignition related |  |  | CANCEL/CNCL | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.7081052 | 40.478 | ETL.1110 | 44425587 | Structure-Steel | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Eureka
118200431 | T2 BRIDGEVILLE-CTNWD 82/578 RMV BUTT | 44143776 | BRIDGEVILLE-COTTONWOOD | 082/578 | ICS | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.7164328 | 40.4804 | ETL.1110 | 44425590 | Structure-Steel | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Eureka
118200480 | T2 BRIDGEVILLE-CTNWD 83/583 RMV BUTT | 44143777 | BRIDGEVILLE-COTTONWOOD | 083/583 | ICW | E | Pre-2020_(3) On high spread structure |  |  |  | TR2 | LATE | North Coast | Non-WSIP |  |  |  |  | Weather | AT RISK - weather impacts | '-123.7289484 | 40.484 | ETL.1110 | 44424588 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
118200675 | T2 DI CARIBOU-WSTWD 7/140A RPL STRW | 31473384 | CARIBOU-WESTWOOD | 007/140A | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.087797 | 40.1717 | ETL.6300 | 40873904 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Table Mountain
118201058 | T2 DI CARIBOU-WSTWD 7/140B RPL STRW | 31473384 | CARIBOU-WESTWOOD | 007/140 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.08781 | 40.1717 | ETL.6300 | 42624246 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Table Mountain
118201861 | DIABLO-MIDWAY #3 49/198 RPL ZENA | 44112307 | DIABLO-MIDWAY #3 | 049/198 | ICB | F | Pre-2020_(9a) Other ignition related | [5 empty] | South | Non-WSIP | [6 empty] | '-120.017141 | 35.2412 | ETL.5980 | 40860585 | Raptor Guard-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 593 | Midway |  | Y - 11
118201870 | DIABLO-MIDWAY #2 49/199 RPL RPTS | 44112388 | DIABLO-MIDWAY #2 | 049/199 | ICB | E | Pre-2020_(9a) Other ignition related |  |  |  |  | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.011524 | 35.242 | ETL.5970 | 40872180 | Raptor Guard-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 593 | Midway |  | Y - 5
118202022 | T2 BRIDGEVILLE-COTTONWD 83/586 RMV DEBRS | 44143777 | BRIDGEVILLE-COTTONWOOD | 083/586 | ICW | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.7398388 | 40.4866 | ETL.1110 | 44424000 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
118202203 | T2 BRIDGEVILLE-COTTONWD 84/588 RMV DEBRS | 44143777 | BRIDGEVILLE-COTTONWOOD | 084/588 | ICW | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.7447937 | 40.4869 | ETL.1110 | 44424569 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
118202242 | T2 BRIDGEVILLE-CTNWD 84/593 RMV DEBRIS | 44143777 | BRIDGEVILLE-COTTONWOOD | 084/593 | ICW | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.7558897 | 40.4862 | ETL.1110 | 44424554 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
118202273 | T2 BRIDGEVILLE-CTNWD 84/591 RMV DEBRIS | 44143777 | BRIDGEVILLE-COTTONWOOD | 084/591 | ICW | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.751597 | 40.4864 | ETL.1110 | 44424575 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
118202461 | T2 BRIDGEVLLE-CTNWD 84/590 RMV DEBRIS | 44143777 | BRIDGEVILLE-COTTONWOOD | 084/590 | ICW | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.7495506 | 40.4866 | ETL.1110 | 44424572 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
118202543 | T3 BRIDGEVILLE-COTTOND 85/598 RMV DEBRIS | 44143777 | BRIDGEVILLE-COTTONWOOD | 085/598 | ICW | F | Pre-2020_(9a) Other ignition related |  |  |  | TR3 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.766643 | 40.4843 | ETL.1110 | 44424563 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
118202924 | T2 HAT CREEK #1-WESTWOOD 26/509 RPLC P | 31495723 | HAT CREEK #1-WESTWOOD | 026/509 | 70Y | F | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Valley | Non-WSIP | [6 empty] | '-121.194428 | 40.6704 | ETL.7030 | 40601697 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain
118207765 | T2 KILARC-DESCHUTES 5/108 RPL POLE | 31482714 | KILARC-DESCHUTES | 005/108 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-121.929089 | 40.6182 | ETL.7300 | 40759294 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Released
118220134 | T2 WV SNG-SMIT 0/013 BOND GUY HRDW | 44111976 | SPAULDING-SUMMIT | 000/013 | ICW | E | Pre-2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.639723 | 39.3233 | ETL.8060 | 40650034 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
118223348 | SAN BRUNO TAP 000/001 RPR SWIW | 44588133 | SAN BRUNO TAP | 000/001 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  |  | LATE | Central | Non-WSIP | [6 empty] | '-122.439223 | 37.6159 | ETL.7572 | 40588793 | Switch-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Bay |  | Y - 5
118223985 | T2 CALNDER SW STA-MESA 015/068 RPL INSS | 31481083 | CALLENDAR SW STA-MESA | 015/068 | 93K | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | South | Non-WSIP | FSRP | [5 empty] | '-120.495546 | 35.0895 | ETL.1210 | 41178097 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 12
118224339 | T2 EL DORADO-MSRI FLAT #1 9/76 RPL POLE | 31482715 | ELDORADO-MISSOURI FLAT #1 | 009/076 | 70Y | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-120.771565 | 38.7464 | ETL.1530 | 40818661 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | Yes
118224398 | T2 CHRISTIE-SOBRANTE 000/003 REPAINT | 43751914 | CHRISTIE-SOBRANTE | 000/003 | ICS | F | Pre-2020_(4b) On structure in bucket 4 | Budget Owner (Paint) |  |  | TR2 |  | Central | Non-WSIP | [6 empty] | '-122.205649 | 38.0025 | ETL.1260 | 41146800 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay
118224581 | T2 CONTRA COSTA-DLT SW YD 14/68 RPL INSS | 31511122 | CONTRA COSTA-DELTA SWITCHING YARD | 014/068 | 93K | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | Central | Non-WSIP | FSRP | [5 empty] | '-121.659199 | 37.8204 | ETL.4490 | 40884341 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay
118238966 | CALLENDER SW STA-MESA 4/70 RMV IDLE | 44226578 | CALLENDAR SW STA-MESA | 004/070 | ICW | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 |  | South | Non-WSIP | [6 empty] | '-120.515695 | 35.0527 | ETL.1210 | 40736121 | Conductor-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - 12
118239340 | T2 DI BELE AFB (WAPA) 2 TAP 0/1 RPR GYWW | 44119803 | BEALE AFB (WAPA) #2 TAP | 000/001 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.332321 | 39.1139 | ETL.7971 | 40741836 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
118239486 | T2 FULTON-CALISTOGA 32/8 RPR STRW | 44305659 | FULTON-CALISTOGA | 032/008 | ICW | E | Pre-2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-122.447606 | 38.5084 | ETL.6880 | 40905814 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
118241771 | T2 DI BEALE AFB (WAPA) #1 INST HRDS | 44119801 | BEALE AFB (WAPA) #1 TAP | 000/002 | ICS | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP | FSRP | [5 empty] | '-121.332562 | 39.1136 | ETL.8001 | 40740418 | Hardware-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento
118241960 | DI OLEUM-NRTH TWR-CHRSTE 0/5 PAINT STRS | 43752229 | OLEUM-NORTH TOWER-CHRISTIE | 000/005 | ICS | F | Pre-2020_(5b) On structure in bucket 5 | Budget Owner (Paint) |  |  |  |  | Central | WSIP | [6 empty] | '-122.249236 | 38.0412 | ETL.3180 | 40746026 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay
118241964 | DI OLEUM-NRTH TWR-CHRSTE 0/5 RPL HRDT | 44323369 | OLEUM-NORTH TOWER-CHRISTIE | 000/005 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  | Likely MAT error - delink to correct |  | LATE | Central | WSIP | [6 empty] | '-122.249236 | 38.0412 | ETL.3180 | 40746026 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 630 | Bay |  | Y - 4
118241968 | T2 DI BEALE AFB (WAPA)#2 0/2 RMV NEST | 44119801 | BEALE AFB (WAPA) #2 TAP | 000/002 | ICS | E | Pre-2020_(9a) Other ignition related |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.33242 | 39.1137 | ETL.7971 | 40576711 | Structure-Steel | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento
118242213 | T2 DI BRDGVLLE-COTTNWD 31/260 RMV DEBRIS | 43939216 | BRIDGEVILLE-COTTONWOOD | 031/260 | ICW | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.855024 | 40.3636 | ETL.1110 | 44423926 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
118242536 | T2 DI OLM-NO TWR-CHRST 0/8 RPR STRT | 43752227 | OLEUM-NORTH TOWER-CHRISTIE | 000/008 | ICQ | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-122.241671 | 38.0396 | ETL.3180 | 40857755 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 6
118242641 | DI T2 SURF TAP 10/175 RMV VEGN |  | SURF TAP | 010/175 | HNA | F | Pre-2020_(9a) Other ignition related |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-120.586005 | 34.6843 | ETL.1381 | 40864675 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Pismo Beach
118243901 | T2 DI SMRTVL-NICOLAUS#2 6/135 RPR GYWW | 44123655 | SMARTVILLE-NICOLAUS #2 | 006/135 | ICW | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.331823 | 39.1136 | ETL.8000 | 40912141 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
118247801 | AGNEW TAP 0/11 RPR GYWW | 44303608 | AGNEW TAP | 000/011 | ICW | E | Pre-2020_(1b) Lines with special commitments |  |  |  |  | LATE | Central | Non-WSIP | FSRP | [5 empty] | '-121.941618 | 37.4345 | ETL.3122 | 40585505 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Bay |  | Y - 1
118248218 | T2 PIT #7 TAP 2/17R RPL POLE | 31432828 | PIT #7 TAP | 002/017 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-121.956949 | 40.8326 | ETL.5442 | 44553739 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Table Mountain
118248223 | T2 PIT #7 TAP 2/17L RPL POLE | 31432828 | PIT #7 TAP | 002/017 | 70Y | E | Pre-2020_(5) TD tag on other lines |  |  |  | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-121.956949 | 40.8326 | ETL.5442 | 44553553 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Table Mountain
118260498 | T3 FULTON-CALISTOGA -13/4 RPR PL | 44305659 | FULTON-CALISTOGA | '-013/004 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Coast | Non-WSIP | [6 empty] | '-122.515425 | 38.4197 | ETL.6880 | 40751147 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
118263098 | T2 HUMBOLDT-TRINITY 91/4L RPL STRW | 31497850 | HUMBOLDT-TRINITY | 091/004 | 70Y | E | 2020_(2) High fire spread TD |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.7071239 | 40.7486 | ETL.1820 | 44560531 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Eureka |  |  | 2020-05-21
118264284 | T3 GEYSERS #12-FULTON 1/6 RPR STRT | 44239025 | GEYSERS #12-FULTON | 001/006 | ICQ | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Coast | Non-WSIP | [6 empty] | '-122.767206 | 38.7958 | ETL.4750 | 41129171 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville
118264643 | T2 RIO DELL JCT-BRIDGEVILL 32/5L RPL PL | 31423103 | RIO DELL JCT-BRIDGEVILLE | 032/005 | 70Y | E | 2020_(2) High fire spread TD |  |  |  | TR2 | LATE | North Coast | Non-WSIP | [6 empty] | '-123.913305 | 40.4881 | ETL.7850 | 44779574 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Eureka |  |  | 2020-01-09
118266568 | T3 FULTON-CALISTOGA -014/004 RPL POLE | 31482772 | FULTON-CALISTOGA | '-014/004 | 93E | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Coast | Non-WSIP | [6 empty] | '-122.505863 | 38.4335 | ETL.6880 | 40751149 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Lakeville
118266611 | T3 FULTON-CALISTOGA -015/001 RPR STRW |  | FULTON-CALISTOGA | '-015/001 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Coast | Non-WSIP | [6 empty] | '-122.495961 | 38.4394 | ETL.6880 | 40585421 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
118267516 | EI RIO DELL JCT-BRIDGEVLE 32/5C RPL STRW | 31423103 | RIO DELL JCT-BRIDGEVILLE | 032/005 | 70Y | E | 2020_(2) High fire spread TD |  |  |  |  | LATE | North Coast | Non-WSIP | [6 empty] | '-123.913305 | 40.4881 | ETL.7850 | 44779575 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2020-01-09
118267610 | EI RIO DELL JCT-BRIDGEVLE 32/5R RPL STRW | 31423103 | RIO DELL JCT-BRIDGEVILLE | 032/005 | 70Y | E | 2020_(2) High fire spread TD |  |  |  |  | LATE | North Coast | Non-WSIP | [6 empty] | '-123.913305 | 40.4881 | ETL.7850 | 44779576 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2020-01-09
118268097 | T2 EI HMBLDT-TRNTY 91/04C RPL STRW | 31497849 | HUMBOLDT-TRINITY | 091/004 | 70Y | E | 2020_(2) High fire spread TD |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.70711 | 40.7485 | ETL.1820 | 44560505 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2020-05-21
118268375 | T2 EI HMBLDT-TRNTY 91/04R RPL STRW | 31497849 | HUMBOLDT-TRINITY | 091/004 | 70Y | E | 2020_(2) High fire spread TD |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.70711 | 40.7485 | ETL.1820 | 44560532 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2020-05-21
118268916 | T3 DRUM-RIO OSO #2 010/100 RMV VEG |  | DRUM-RIO OSO #2 | 010/100 | HNA | E | 2020_(3) On high spread structure |  |  |  | TR3 | LATE | North Valley | Non-WSIP | [6 empty] | '-120.919028 | 39.1756 | ETL.1430 | 40608843 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento
118269745 | T2 CARIBOU #2 ;002/010 RPR STRS | 44144219 | CARIBOU #2 | ;002/010 | ICS | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-120.954713 | 39.9989 | ETL.6280 | 44688355 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | Yes
118278684 | T2 BELDEN TAP 0/1A CANCEL | 44170043 | BELDEN TAP | 000/001A | ICQ | E | 2020_(2) High fire spread TD |  |  | CANCEL/CNCL | TR2 | LATE | North Valley | Non-WSIP | [6 empty] | '-121.250817 | 40.0077 | ETL.4441 | 43198032 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
118279869 | T2 DI CARIBOU-PLUMAS JCT 0/1 RPL POLE | 31498402 | CARIBOU-PLUMAS JCT | 000/001 | 70Y | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.14748 | 40.0855 | ETL.6290 | 40600690 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain
118280663 | T2 DI HUMBOLDT-MAPLE CRK 13/5C RPL STRW | 31485371 | HUMBOLDT-MAPLE CREEK | 013/005 | 70Y | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.8853558 | 40.7679 | ETL.7130 | 44859705 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS erdy | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Eureka |  |  | 2020-01-29
118280672 | T2 DI HUMBOLDT-MAPLE CRK 13/5R RPL STRW | 31485371 | HUMBOLDT-MAPLE CREEK | 013/005 | 70Y | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.8853558 | 40.7679 | ETL.7130 | 44859706 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS erdy | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Eureka |  |  | 2020-01-29
118284857 | T2 EI CARIBOU-TABLE MTN 7/056 RPR ANCHOR |  | CARIBOU-TABLE MTN | 007/056 | ICS | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.149342 | 40.0851 | ETL.4440 | 40815780 | Anchor-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain |  |  | released 7-13-20
118316604 | T2 DI COLGATE-SMARTVIL#2 3/36 BOND GUY | 44135957 | COLGATE-SMARTVILLE #2 | 003/036 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.237627 | 39.3101 | ETL.6520 | 40602842 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
118369993 | T2 EI TRINITY-MAPLE CREEK 7/8 REFRAME | 31489366 | TRINITY-MAPLE CREEK | 007/008 | 93E | E | 2020_(2) High fire spread TD |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.056467 | 40.7467 | ETL.8170 | 40906351 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Eureka |  |  | 2020-04-14
118388637 | T2 EI CASTRO VALLEY-NWRK 05/033 RPL DAMS | 44144892 | CASTRO VALLEY-NEWARK | 005/033 | ICS | E | 2020_(2) High fire spread TD |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | 121.9918 | 37.6408 | ETL.4450 | 40788240 | Damper-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - 10
118388683 | T2 EI CSTRO VLY-NWRK 5/33 INST JUMS INSS | 44144892 | CASTRO VALLEY-NEWARK | 005/033 | ICS | E | 2020_(2) High fire spread TD |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | 121.9918 | 37.6408 | ETL.4450 | 40788240 | Jumper-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - 10
118388885 | T3 EI BRUNSWICK #2 TAP 0/3 RPL INSS | 31433277 | BRUNSWICK #2 TAP | 000/003 | 93K | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.008684 | 39.1445 | ETL.1431 | 40678233 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Sacramento
118390408 | T2 EI DRUM-RIO OSO #1 31/224 BENT MEMB | 44144912 | DRUM-RIO OSO #1 | 031/224 | ICQ | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-121.262626 | 39.0386 | ETL.1420 | 40746096 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento
118395911 | EI SALINAS-LAURELES A018/383 RMV VEGN |  | SALINAS-LAURELES | A018/383 | HNA | E | 2020_(4b) On structure in bucket 4 | Budget Owner (Veg/Land/Road) |  |  |  | LATE | South | Non-WSIP | [6 empty] | '-121.862366 | 36.5857 | ETL.7930 | 40680327 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Moss Landing
118395982 | DI SALINAS-LAURELES A017/374 REPL POLE | 31478032 | SALINAS-LAURELES | A017/374 | 70Y | E | 2020_(4) TD tag on high spread line |  |  |  |  | LATE | South | WSIP | [6 empty] | '-121.854788 | 36.5833 | ETL.7930 | 40825953 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Moss Landing |  |  | Caltrans (DSDD)
118396324 | DI SALINAS-LAURELES A16/348 TIGHTEN BOLT | 44391519 | SALINAS-LAURELES | A016/348 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  |  | LATE | South | WSIP | [6 empty] | '-121.833233 | 36.5815 | ETL.7930 | 40658683 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing
118399557 | T2 SPAULDING-SUMMIT 0/006 RPR GYWW | 44146289 | SPAULDING-SUMMIT | 000/006 | ICW | E | 2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.642656 | 39.3248 | ETL.8060 | 40810153 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
118400020 | T2 HUMBOLDT-TRINITY 64/0 REPL GYWW | 44298747 | HUMBOLDT-TRINITY | 064/000 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.230802 | 40.7363 | ETL.1820 | 44562748 | Guy Wire-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2020-05-27
118428982 | T3NT FULTON-CALISTOGA :0/8 INSTL MRKS | 31487688 | FULTON-CALISTOGA | :000/008 | 93C | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.58119 | 38.6037 | ETL.6880 | 44647598 | Marker (i.e. signs)-Steel | Missing | Install | ESTS erdy | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Maintenance | Capital | 531 | Lakeville
118437940 | HUMBOLDT-BRIDGEVILLE 92/6 RPL PL LEFT | 31486487 | HUMBOLDT-BRIDGEVILLE | 092/006 | 70Y | E | 2020_(4) TD tag on high spread line |  |  |  |  | LATE | North Coast | WSIP | [8 empty] | ETL.1810 | 44322322 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Eureka |  |  | 2020-03-23
118440911 | GEYSERS #7-EAGLE ROCK 1/10 REPL CROSSING | 31487105 | GEYSERS #7-EAGLE ROCK | 001/010 | 71Y | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.811077 | 38.8232 | ETL.1680 | 40588203 | Road | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLR | Roads | Capital | 374 | Lakeville
118447822 | EI HUMBOLDT-BRIDGEVILLE 92/6R RPL STRW | 31486487 | HUMBOLDT-BRIDGEVILLE | 092/006 | 70Y | E | 2020_(4) TD tag on high spread line |  |  |  |  | LATE | North Coast | WSIP | [8 empty] | ETL.1810 | 44322323 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Eureka |  |  | 2020-03-23
118450415 | T2NT KESWICK-TRINITY 20/290 INST MRKS | 44406439 | KESWICK-TRINITY | 020/290 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.752348 | 40.7163 | ETL.7270 | 44649299 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Yes
118453527 | T2 SNEATH LANE-PFCA 4/50 TST POLE CMPLTD | 44162132 | SNEATH LANE-PACIFICA | 004/050 | ICH | E | 2020_(4) TD tag on high spread line |  |  | CANCEL/CNCL | TR2 | LATE | Central | WSIP | [6 empty] | '-122.4549992 | 37.615 | ETL.7575 | 44384746 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Bay
118454334 | T2 DI TRINITY-MAPLE CREEK 02/10 RPL ANCW | 31488022 | TRINITY-MAPLE CREEK | 002/010 | 93E | E | 2020_(2) High fire spread TD |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.973681 | 40.7346 | ETL.8170 | 40906272 | Anchor-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Eureka |  |  | 2020-04-14
118455543 | T3 EGLE RCK-FLTN-SLVDO 3/16A RPL INSS | 31485176 | EAGLE ROCK-FULTON-SILVERADO | 003/016A | 93K | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.802181 | 38.8015 | ETL.4392 | 40578874 | Insulator-Steel | No Good/Out of Stdrd | Replace | POST | POST | POST Estimate | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Lakeville
118477236 | T2 LAKEVILLE-SOBRANTE #2 44/211 RPL INSS | 31431937 | LAKEVILLE-SOBRANTE #2 | 044/211 | 93K | E | 2020_(2) High fire spread TD |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-122.2039344 | 37.9529 | ETL.4960 | 40618899 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Lakeville
118484703 | T2 NEWARK-LIVERMORE 16/99 RPL PL | 31489034 | NEWARK-LIVERMORE | 016/099 | 70Y | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | Central | WSIP | [6 empty] | '-121.77775 | 37.636 | ETL.7660 | 40745742 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Bay
118486847 | MELONES-CURTIS 5/6 RPR GYWW | 44623079 | MELONES-CURTIS | 005/006 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-120.4567661 | 37.9131 | ETL.2390 | 44195243 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 18
118499120 | OLEUM-G #1 0/6 RPR FOND |  | OLEUM-G #1 | 000/006 | ICQ | E | 2020_(4) TD tag on high spread line |  |  |  |  | <15D | Central | WSIP | [6 empty] | '-122.246756 | 38.0405 | ETL.3150 | 40804781 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 9
118499883 | T2 DIVIDE-VANDENBERG #2 5/42 RPL ANCW | 31490364 | DIVIDE-VANDENBERG #2 | 005/042 | 93E | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 | <15D | South | WSIP | [6 empty] | '-120.510648 | 34.7691 | ETL.8630 | 40754920 | Anchor-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Pismo Beach |  | Y - 12
118500086 | MELONES-CURTIS 5/6 RPR GYWW | 44623200 | MELONES-CURTIS | 005/006 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  |  | SCHD | Central | WSIP | [6 empty] | '-120.4567697 | 37.9131 | ETL.2390 | 44195244 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 18
118502119 | T2 HAAS-MCCALL 15/085 RPR JUMS | 44301790 | HAAS-MCCALL | 015/085 | ICS | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 | <15D | South | WSIP | [6 empty] | '-119.266507 | 36.8466 | ETL.4850 | 40762656 | Jumper-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno
118505099 | EI T3NT ROSSMOOR #1 TAP 0/003 RPR FOND |  | ROSSMOOR #1 TAP | 000/003 | ICQ | F | 2020_(4) TD tag on high spread line |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-122.07906 | 37.86 | ETL.5451 | 40659428 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog 402
118506108 | T2 HAT CREEK #1-WESTWOOD 44/863 REFRAME | 31469738 | HAT CREEK #1-WESTWOOD | 044/863 | 93E | E | 2020_(2) High fire spread TD |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.022952 | 40.4504 | ETL.7030 | 40877507 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain
118506297 | T2 VACA-SUISUN-JAMESON 5/40 RPL INSS | 31457373 | VACA-SUISUN-JAMESON | 005/040 | 93K | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.9959972 | 38.3818 | ETL.4080 | 40632749 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Sacramento
118506415 | T2 CORTINA-MENDOCINO #1 28/137 RPR FOND | 44302218 | CORTINA-MENDOCINO #1 | 028/137 | ICS | E | 2020_(2) High fire spread TD |  |  | Likely MAT error - delink to correct | TR2 |  | North Coast | WSIP | [6 empty] | '-122.708607 | 39.0337 | ETL.1330 | 40808527 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville
118506416 | T2 CORTINA-MENDOCINO #1 23/107 RPR FOND | 44302218 | CORTINA-MENDOCINO #1 | 023/107 | ICS | E | 2020_(4) TD tag on high spread line |  |  | Likely MAT error - delink to correct | TR2 | <15D | North Coast | WSIP | [6 empty] | '-122.607196 | 39.011 | ETL.1330 | 40813110 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville
118506417 | T2 MORAGA-CASTRO VALLEY 1/8 RPR FOND |  | MORAGA-CASTRO VALLEY | 001/008 | ICQ | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 | <15D | Central | WSIP | [6 empty] | '-122.141199 | 37.8506 | ETL.5250 | 40866253 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 7
118506419 | T2 CORTINA-MENDOCINO #1 15/72 RPR FOND | 44238817 | CORTINA-MENDOCINO #1 | 015/072 | ICQ | E | 2020_(2) High fire spread TD |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.469953 | 39.0228 | ETL.1330 | 40657040 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville
118519915 | T2 STNSLS-MLNS SS-MNTCA 5/32 RPR STRT |  | STANISLAUS-MELONES SS-MANTECA #1+ | 005/032 | ICQ | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 | <15D | Central | WSIP | [6 empty] | '-120.453437 | 38.1026 | ETL.3830 | 40642821 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - 9
118519938 | T2 STNSLS-MLNS SS-MNTCA :5/32 RPR STRT |  | STANISLAUS-MELONES SS-MANTECA #1+ | :005/032 | ICQ | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 | <15D | Central | WSIP | [6 empty] | '-120.617206 | 37.9714 | ETL.3830 | 40642910 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - 9
118519948 | T2 SALINAS-LAURELES A012/270 RPR STRW | 44294541 | SALINAS-LAURELES | A012/270 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | South | WSIP | [6 empty] | '-121.773189 | 36.5693 | ETL.7930 | 40825940 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing
118521765 | T2 CORTINA-MENDOCINO #1 20/96 RPR FOND | 44238817 | CORTINA-MENDOCINO #1 | 020/096 | ICQ | E | 2020_(2) High fire spread TD |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.563714 | 39.0039 | ETL.1330 | 40808919 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville
118522125 | T2 EI NEWARK-LIVMORE 009/056 CANCEL | 44621454 | NEWARK-LIVERMORE | 009/056 | ICS | E | 2020_(2) High fire spread TD |  |  | CANCEL/CNCL | TR2 | <15D | Central | WSIP | [6 empty] | '-121.860387 | 37.582 | ETL.7660 | 40830360 | Splice-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  |  | SFWL
118522380 | T2 CORTINA-MENDOCINO #1 51/252 RPR FOND | 44238817 | CORTINA-MENDOCINO #1 | 051/252 | ICQ | E | 2020_(2) High fire spread TD |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.041805 | 39.207 | ETL.1330 | 40657091 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville
118524639 | T2 CLEAR LAKE-HOPLAND 2/0 RPL POLE | 31488229 | CLEAR LAKE-HOPLAND | 002/000 | 70Y | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 | <15D | North Coast | WSIP | [6 empty] | '-123.046297 | 38.9673 | ETL.6390 | 40587019 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville
118527459 | T3 EI SNEATH LANE-HMB ?10/5 RPL ANCW | 31490660 | SNEATH LANE-HALF MOON BAY | ?010/005 | 93E | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.422274 | 37.4871 | ETL.7212 | 40758359 | Anchor-Wood | No Good/Out of Stdrd | Replace | MAPP srdy | MAPP | Constructed and mapped | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Bay
118529067 | T2 DIABLO-MIDWAY #3 21/088A RPL INSS | 31500490 | DIABLO-MIDWAY #3 | 021/088A | 93K | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 | <15D | South | WSIP | [6 empty] | '-120.477877 | 35.1638 | ETL.5980 | 40577051 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 15
118532302 | T3 EI SNEATH LANE-HMB ;2/21 RPL ANCW | 31490660 | SNEATH LANE-HALF MOON BAY | ;002/021 | 93E | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.469905 | 37.6016 | ETL.7212 | 40599236 | Anchor-Wood | No Good/Out of Stdrd | Replace | MAPP srdy | MAPP | Constructed and mapped | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Bay |  | Y - Prog 402
118532589 | T3 EI SNEATH LANE-HMB ?9/4 RPL ANCW | 31490660 | SNEATH LANE-HALF MOON BAY | ?009/004 | 93E | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.42395 | 37.503 | ETL.7212 | 40768020 | Anchor-Wood | No Good/Out of Stdrd | Replace | MAPP srdy | MAPP | Constructed and mapped | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Bay
118537816 | T2 BRDEVLLE-CTTNWD 72/522L RPL POLE | 31497846 | BRIDGEVILLE-COTTONWOOD | 072/522 | 70Y | E | 2020_(2) High fire spread TD |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.545146 | 40.4703 | ETL.1110 | 44512064 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka
118537866 | TRINITY-MAPLE CREEK 50/8 RPL ANCW | 31492622 | TRINITY-MAPLE CREEK | 050/008 | 93E | E | 2020_(2) High fire spread TD |  |  |  |  | SCHD | North Coast | WSIP | [6 empty] | '-123.8123315 | 40.7617 | ETL.8170 | 44752436 | Anchor-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Eureka |  |  | 2020-04-23
118543518 | T2 CORTINA-MENDOCINO #1 51/248 RPR FOND | 44238817 | CORTINA-MENDOCINO #1 | 051/248 | ICQ | E | 2020_(2) High fire spread TD |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.031889 | 39.2075 | ETL.1330 | 40870938 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville
118543556 | T2 CORTINA-MENDOCINO #1 34/165 RPR FOND | 44302218 | CORTINA-MENDOCINO #1 | 034/165 | ICS | E | 2020_(4) TD tag on high spread line |  |  | Likely MAT error - delink to correct | TR2 | <30D | North Coast | WSIP | [6 empty] | '-122.775849 | 39.0916 | ETL.1330 | 40750579 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville
118544026 | BRIDGEVILE-COTTONWOOD 72/522R RPL POLE | 31497846 | BRIDGEVILLE-COTTONWOOD | 072/522 | 70Y | E | 2020_(2) High fire spread TD |  |  |  |  | SCHD | North Coast | WSIP | [6 empty] | '-123.545146 | 40.4703 | ETL.1110 | 44512065 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka
118545246 | HUMBOLDT-MAPLE CREEK 11/006 RPL PL | 31492615 | HUMBOLDT-MAPLE CREEK | 011/006 | 70Y | E | 2020_(4) TD tag on high spread line |  |  |  |  | SCHD | North Coast | WSIP | [6 empty] | '-123.918768 | 40.7613 | ETL.7130 | 40809422 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka
118546043 | EI HUMBOLDT-BRIDGEVILE 108/1 RGT RPL PL | 31496089 | HUMBOLDT-BRIDGEVILLE | 108/001 | 70Y | E | 2020_(4) TD tag on high spread line |  |  |  |  | LATE | North Coast | WSIP | [6 empty] | '-118.863225 | 35.2965 | ETL.1810 | 44322587 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2020-03-23
118551837 | T2 JOLON TAP 3/37 RPR STRW FENCE | 44575318 | JOLON TAP | 003/037 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR2 | SCHD | South | WSIP | [6 empty] | '-121.171572 | 36.1679 | ETL.7321 | 40649734 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing
118552444 | T2 TRINITY-MAPLE CREEK 6/13 RPL POLE | 31492616 | TRINITY-MAPLE CREEK | 006/013 | 70Y | E | 2020_(2) High fire spread TD |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.053455 | 40.7384 | ETL.8170 | 40906340 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2020-04-14
118553390 | Vinyard-Newark 34/198 RPL INSS | 31526486 | VINEYARD-NEWARK | 034/198 | 93K | E | 2020_(2) High fire spread TD | [5 empty] | Central | WSIP | [6 empty] | '-121.8432959 | 37.5953 | ETL.4536 | 41170813 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y-2
118558616 | T2 DI CRTNA-MENDOCINO #1 59/293 RPL INSS | 31439888 | CORTINA-MENDOCINO #1 | 059/293 | 93K | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.181329 | 39.2418 | ETL.1330 | 40690027 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Lakeville
118558637 | BLLT-RVRBNK-MLNS SW ST :15/8 RPL POLE | 31492502 | BELLOTA-RIVERBANK-MELONES SW STA | :015/008 | 70Y | E | 2020_(2) High fire spread TD |  |  |  |  | SCHD | Central | WSIP | [6 empty] | '-120.760854 | 37.8701 | ETL.1070 | 40857288 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 13
118558695 | T2 DI MNDOCINO-RDBD #1 59/293 RPL INSS |  | MENDOCINO-REDBUD | 059/293 | 93K | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 | <30D | North Coast | WSIP | [6 empty] | '-123.181329 | 39.2418 | ETL.2410 | 40690028 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Lakeville
118559044 | T3 MONTE RIO-FULTON 10/0 RPL INSS | 31492628 | MONTE RIO-FULTON | 010/000 | 93I | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.9391902 | 38.4872 | ETL.7630 | 40628712 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Lakeville
118575868 | T2 PARKWAY-MORAGA 011/064 RPL HRDT |  | PARKWAY-MORAGA | 011/064 | ICQ | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 | <30D | Central | WSIP | [6 empty] | '-122.22211 | 37.9854 | ETL.5930 | 44768968 | Hardware-Tower | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  | EBMUD
118575961 | T2 BAHIA-MORAGA 14/82 RPLC HRDT | 43683410 | BAHIA-MORAGA | 014/082 | ICQ | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 | <30D | Central | WSIP | [6 empty] | '-122.217859 | 37.9801 | ETL.4340 | 40611761 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  | EBMUD
118575962 | T2 PARKWAY-MORAGA 11/66 RPLC HRDT |  | PARKWAY-MORAGA | 011/066 | ICQ | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 | <30D | Central | WSIP | [6 empty] | '-122.217859 | 37.9801 | ETL.5930 | 40611760 | Hardware-Tower | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  | EBMUD
118575964 | T2 BAHIA-MORAGA 14/82 RPR SHLS/OPGW | 44245153 | BAHIA-MORAGA | 014/082 | ICS | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 | SCHD | Central | WSIP | [6 empty] | '-122.217859 | 37.9801 | ETL.4340 | 40611761 | Shield Wire / OPGW-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - 7
118575990 | T2 PARKWAY-MORAGA 011/064 RPR SHLS | 44245151 | PARKWAY-MORAGA | 011/064 | ICS | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 | <30D | Central | WSIP | [6 empty] | '-122.22211 | 37.9854 | ETL.5930 | 44768968 | Shield Wire / OPGW-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - 11
118576042 | T2 PARKWAY-MORAGA 011/064 INSTL DAMS | 44609773 | PARKWAY-MORAGA | 011/064 | ICS | E | 2020_(4b) On structure in bucket 4 |  |  |  | TR2 | <30D | Central | WSIP | [6 empty] | '-122.22211 | 37.9854 | ETL.5930 | 44768968 | Damper-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - 11
118576241 | T2 BAHIA-MORAGA 14/82 RPLC DAMS | 44621442 | BAHIA-MORAGA | 014/082 | ICS | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 | SCHD | Central | WSIP | [6 empty] | '-122.217859 | 37.9801 | ETL.4340 | 40611761 | Damper-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - 7
118576242 | T2 PARKWAY-MORAGA 11/66 RPLC DAMS | 44332287 | PARKWAY-MORAGA | 011/066 | ICS | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 | <30D | Central | WSIP | [6 empty] | '-122.217859 | 37.9801 | ETL.5930 | 40611760 | Damper-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - 11
118576243 | T2 PARKWAY-MORAGA 11/67 RPLC HRDT |  | PARKWAY-MORAGA | 011/067 | ICQ | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 | <30D | Central | WSIP | [6 empty] | '-122.216207 | 37.978 | ETL.5930 | 40713873 | Hardware-Tower | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  | EBMUD
118576244 | T2 BAHIA-MORAGA 14/83 RPLC HRDT | 43683410 | BAHIA-MORAGA | 014/083 | ICQ | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 | <30D | Central | WSIP | [6 empty] | '-122.216207 | 37.978 | ETL.4340 | 40713875 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  | EBMUD
118576245 | T2 PARKWAY-MORAGA 14/84 RPL HRDT | 44298735 | PARKWAY-MORAGA | 014/084 | ICQ | E | 2020_(2) High fire spread TD |  |  |  | TR2 | SCHD | Central | WSIP | [6 empty] | '-122.205301 | 37.943 | ETL.5930 | 40890767 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 9
118576248 | T2 PARKWAY-MORAGA 14/84 RPR SHLS | 44245151 | PARKWAY-MORAGA | 014/084 | ICS | E | 2020_(2) High fire spread TD |  |  |  | TR2 | <30D | Central | WSIP | [6 empty] | '-122.205301 | 37.943 | ETL.5930 | 40890767 | Shield Wire / OPGW-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - 9
118576596 | T2 BAHIA-MORAGA 14/83 RPR SHLS/OPGW | 44245153 | BAHIA-MORAGA | 014/083 | ICS | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 | SCHD | Central | WSIP | [6 empty] | '-122.216207 | 37.978 | ETL.4340 | 40713875 | Shield Wire / OPGW-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - 7
118576900 | T2 BAHIA-MORAGA 14/83 RPLC DAMS |  | BAHIA-MORAGA | 014/083 | ICS | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 | SCHD | Central | WSIP | [6 empty] | '-122.216207 | 37.978 | ETL.4340 | 40713875 | Damper-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - 7
118581796 | T2 DRUM-RIO OSO # 212/114 RPR INSS | 44228282 | DRUM-RIO OSO #2 | 012/114 | ICS | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-120.957397 | 39.1609 | ETL.1430 | 40786138 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento
118585608 | T2 CNTRA CSTA-MORAGA#1 023/110 RPL INSS | 31526487 | CONTRA COSTA-MORAGA #1 | 023/110 | 93K | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 | SCHD | Central | WSIP | [6 empty] | '-122.113779 | 37.8585 | ETL.5452 | 44291683 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - Prog 402
118585758 | T2 ROND MTN-TABLE MTN #2 55/236 RPR SPLS | 44305720 | ROUND MTN-TABLE MTN #2 | 055/236 | ICS | E | 2020_(2) High fire spread TD |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.866989 | 40.013 | ETL.6070 | 40820562 | Splice-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain
118590002 | T2 JOLON TAP 2/026 RPL ANCW | 31460019 | JOLON TAP | 002/026 | 93E | E | 2020_(2) High fire spread TD |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-121.172475 | 36.1874 | ETL.7321 | 40585799 | Anchor-Wood | No Good/Out of Stdrd | Replace | MAPP erdy srdy |  |  |  | PEND | LC | TLN | Maintenance | Capital | 637 | Moss Landing
118593945 | T2 DI PIT#1-COTTONWOOD 11/94 RPR CONS | 43879413 | PIT #1-COTTONWOOD | 011/094 | ICS | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 | <30D | North Valley | WSIP | [6 empty] | '-121.684753 | 40.8928 | ETL.5390 | 40762844 | Conductor-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain
118598941 | T3 DI MIDDLE FORK #1 9/126 RPLC INSW | 31493812 | MIDDLE FORK #1 | 009/126 | 93I | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.737811 | 39.0039 | ETL.8405 | 44650051 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Sacramento |  |  | Yes
118600451 | T3 EI MORAGA-OAKLAND #2 00/07 RPL INSS | 31506692 | MORAGA-OAKLAND #2 | 000/007 | 93K | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.1768427 | 37.8442 | ETL.2730 | 40828515 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - 3
118600509 | T3 EI MORAGA-OAKLAND #4 0/8 REPL INSS | 31508630 | MORAGA-OAKLAND #4 | 000/008 | 93K | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.176291 | 37.844 | ETL.2750 | 40898131 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y- 3
118600893 | T3 EI MORAGA-OAKLAND #3 1/9 REPL INSS | 31504796 | MORAGA-OAKLAND #3 | 001/009 | 93K | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.177789 | 37.8431 | ETL.2740 | 40878738 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - 12
118601460 | T2 COLGATE-SMARTVILLE #2 08/100 RPL POLE | 31493813 | COLGATE-SMARTVILLE #2 | 008/100 | 70Y | E | 2020_(1a) PSPS |  |  |  | TR2 | <30D | North Valley | WSIP | [6 empty] | '-121.295814 | 39.2389 | ETL.6520 | 40594280 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento
118602344 | T3 EI MORAGA-OAKLAND #3 1/9 REPAINT | 43725286 | MORAGA-OAKLAND #3 | 001/009 | ICS | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-122.178464 | 37.8431 | ETL.2740 | 40857636 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay
118602558 | T2 KESWICK-TRINITY 15/183A REPL ANCHOR | 31494691 | KESWICK-TRINITY | 015/183A | 93E | E | 2020_(2) High fire spread TD |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-122.67028 | 40.7103 | ETL.7270 | 40827887 | Anchor-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain
118602596 | T2 KESWICK-TRINITY 15/193 REPL ANCHOR | 31494691 | KESWICK-TRINITY | 015/193 | 93E | E | 2020_(2) High fire spread TD |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-122.673623 | 40.7154 | ETL.7270 | 40827889 | Anchor-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain
118602997 | EI T3NT MORAGA-OAKLAND #1 001/008 REPAIN | 43744382 | MORAGA-OAKLAND #1 | 001/008 | ICS | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-122.178678 | 37.8431 | ETL.2720 | 40870714 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay
118603025 | T3 EI MORAGA-OAKLAND #1 001/008 RPL INSS | 31504785 | MORAGA-OAKLAND #1 | 001/008 | 93K | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.178195 | 37.8435 | ETL.2720 | 40895764 | Insulator-Steel | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - 9
118603242 | T2 SAN LUIS OBISPO-CAYUCOS 5/33 REPL PL | 31494257 | SAN LUIS OBISPO-CAYUCOS | 005/033 | 70Y | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 | <60D | South | WSIP | [6 empty] | '-120.654282 | 35.3142 | ETL.9090 | 44565351 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Pismo Beach |  | Y - 12
118603403 | EI T3NT MORAGA-OAKLAND #1 001/010 REPAIN | 43744382 | MORAGA-OAKLAND #1 | 001/010 | ICS | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-122.187276 | 37.8382 | ETL.2720 | 40581554 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay
118603454 | T2 SAN LUIS OBISPO-CYCS 5/37 REPL POLE | 31494257 | SAN LUIS OBISPO-CAYUCOS | 005/037 | 70Y | E | 2020_(2) High fire spread TD |  |  |  | TR2 | <60D | South | WSIP | [6 empty] | '-120.658954 | 35.3161 | ETL.9090 | 44565337 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Pismo Beach |  | Y - 12
118603530 | T3 DONNELLS-MI-WUK 018/003L RPL POLE | 31494673 | DONNELLS-CURTIS | 018/003 | 70Y | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-120.21401 | 38.0548 | ETL.1400 | 44774113 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Victor |  | Y - 40
118604143 | T2 CARIBOU #2 15/016 REPL ANCW | 31494689 | CARIBOU #2 | 015/016 | 93E | E | 2020_(2) High fire spread TD |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.103577 | 40.0194 | ETL.6280 | 40826420 | Anchor-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain
118604263 | T2 SAN LUIS OBISPO-CYCS 5/37 REPL POLE | 31494257 | SAN LUIS OBISPO-CAYUCOS | 005/037 | 70Y | E | 2020_(2) High fire spread TD |  |  |  | TR2 | <60D | South | WSIP | [6 empty] | '-120.658954 | 35.3161 | ETL.9090 | 44565369 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Pismo Beach |  | Y - 12
118604856 | LOS BANOS-GATES #1 74/314 REPL DAMP | 44434283 | LOS BANOS-GATES #1 | 074/314 | ICS | E | 2020_(1b) Lines with special commitments | Director approved | DLFL once tag is confirmed complete PM 74008747 | Email CIRT when complete |  | WECC | South | WSIP | [6 empty] | '-120.186514 | 36.2164 | ETL.6000 | 40765647 | Damper-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  | Y - 17
118604906 | LOS BANOS-GATES #1 68/285 REPL DAMPS | 44301827 | LOS BANOS-GATES #1 | 068/285 | ICS | E | 2020_(1b) Lines with special commitments | Director approved | DLFL once tag is confirmed complete PM 74008747 | Email CIRT when complete |  | WECC | South | WSIP | [6 empty] | '-120.268235 | 36.2892 | ETL.6000 | 40765394 | Damper-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  | Y - 17
118604994 | T2 CAYUCOS-CAMBRIA 11/070 BOND GUYS |  | CAYUCOS-CAMBRIA | 011/070 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 | <60D | South | WSIP | [6 empty] | '-121.009485 | 35.5409 | ETL.8560 | 40588563 | Hardware-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - 13
118605416 | T3 DONNELLS-MI-WUK 11/00L RPL POLE | 31494253 | DONNELLS-CURTIS | 011/000 | 70Y | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-120.125168 | 38.1249 | ETL.1400 | 44770788 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 40
118605706 | DONNELLS-MI-WUK 018/003R RPLC STRW | 31494673 | DONNELLS-CURTIS | 018/003 | 70Y | E | 2020_(2) High fire spread TD |  |  |  |  | SCHD | Central | WSIP | [6 empty] | '-120.21401 | 38.0548 | ETL.1400 | 44774119 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 40
118605707 | T3 MORAGA-OAKLAND#2 1/8 RPLC INSS | 31506692 | MORAGA-OAKLAND #2 | 001/008 | 93K | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.178195 | 37.8435 | ETL.2730 | 40895766 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - 3
118606093 | T2 SAN LUIS OBISPO-CAYUCOS 5/33 REPL PL | 31494257 | SAN LUIS OBISPO-CAYUCOS | 005/033 | 70Y | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 | <60D | South | WSIP | [6 empty] | '-120.654282 | 35.3142 | ETL.9090 | 44565529 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Pismo Beach |  | Y - 12
118615220 | IGNACIO-MARE ISLAND #1 10/77 RPR BAYW | 44176145 | IGNACIO-MARE ISLAND #1 | 010/077 | ICJ | B | 2020_(0) A and B Tags | [5 empty] | North Coast | WSIP | [6 empty] | '-122.380093 | 38.1526 | ETL.1830 | 43249843 | Bay Water-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 510 | Lakeville
118640162 | T3 DONNELLS-MI-WUK 11/00L RPL POLE | 31494253 | DONNELLS-CURTIS | 011/000 | 70Y | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-120.125168 | 38.1249 | ETL.1400 | 44770789 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 40
118676332 | T2 GARBERVILLE-LAYTONVILLE 25/7 RPR STRW | 44311204 | GARBERVILLE-LAYTONVILLE | 025/007 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.492136 | 39.7247 | ETL.8365 | 40808444 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka |  |  | 2020-03-12
118676861 | `2 ROUND MTN-TABLE MTN #1 17/93 RPR FOND | 43848514 | ROUND MTN-TABLE MTN #1 | 017/093 | ICQ | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 | <60D | North Valley | WSIP | [6 empty] | '-121.944379 | 40.5511 | ETL.6060 | 40663121 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
118677432 | T2 MELONES-CURTIS 9/3 RPR GYWW | 44623201 | MELONES-CURTIS | 009/003 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-120.403585 | 37.9428 | ETL.2390 | 44391058 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 18
118679100 | HUMBOLDT-TRINITY 064/000 RPL POLE | 31494734 | HUMBOLDT-TRINITY | 064/000 | 70Y | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.230802 | 40.7363 | ETL.1820 | 44562888 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Eureka |  |  | 2020-05-27
118679102 | HUMBOLDT-TRINITY 064/000 RPL POLE | 31494734 | HUMBOLDT-TRINITY | 064/000 | 70Y | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.230802 | 40.7363 | ETL.1820 | 44562936 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Eureka |  |  | 2020-05-27
118679805 | T3 EAGLE ROCK-CORTINA :7/40 RPL INSS | 31479500 | EAGLE ROCK-CORTINA | :007/040 | 93K | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.7128763 | 38.8816 | ETL.1470 | 40629623 | Insulator-Steel | No Good/Out of Stdrd | Replace | DOCC srdy | DOCC | Job has been constructed (documentation) | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Lakeville
118679828 | T3 EAGLE ROCK-CORTINA :7/42 RPL INSS | 31479500 | EAGLE ROCK-CORTINA | :007/042 | 93K | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.7072807 | 38.8815 | ETL.1470 | 40716617 | Insulator-Steel | No Good/Out of Stdrd | Replace | DOCC srdy | DOCC | Job has been constructed (documentation) | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Lakeville
118679877 | T2 ROCK CREEK-POE 5/042 RPL INSS | 31454863 | ROCK CREEK-POE | 005/042 | 93K | E | 2020_(2) High fire spread TD |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.402278 | 39.8516 | ETL.5630 | 40671054 | Insulator-Steel | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain
118681268 | T3 MIDDLE FORK #1 2/043B RPR GYWW | 44261830 | MIDDLE FORK #1 | 002/043B | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.625071 | 39.0014 | ETL.8405 | 42569704 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
118681295 | T3 MIDDLE FORK #1 2/43A RPR GYWW | 44261830 | MIDDLE FORK #1 | 002/043A | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.625074 | 39.0014 | ETL.8405 | 40822833 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
118681702 | T3 SNEATH LANE-HMB ?7/1 RPL ANCW | 31475188 | SNEATH LANE-HALF MOON BAY | ?007/001 | 93E | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.436739 | 37.5331 | ETL.7212 | 40599243 | Anchor-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Bay |  |  | Scarper Ridge
118682727 | T2 RIO DELL JCT-BRIDGEVILL 33/7 RPR STRW | 44261478 | RIO DELL JCT-BRIDGEVILLE | 033/007 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.895707 | 40.4842 | ETL.7850 | 40808358 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
118715724 | T3 OLEUM-G #1 8/55 RPL INSS | 31503752 | OLEUM-G #1 | 008/055 | 93K | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.2717968 | 37.9449 | ETL.3150 | 40774775 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - 9
118715784 | T2 KESWICK-TRINITY 17/223 RPL PL | 31422860 | KESWICK-TRINITY | 017/223 | 70Y | E | 2020_(2) High fire spread TD |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-122.697592 | 40.7214 | ETL.7270 | 40770390 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain
118724076 | T2 SNEATH LANE-PACIFICA 4/52 REPL POLE | 31497878 | SNEATH LANE-PACIFICA | 004/052 | 70Y | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 | SCHD | Central | WSIP | [6 empty] | '-122.456143 | 37.6142 | ETL.7575 | 40864576 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Bay
118725649 | EI T3NT SNEATH LANE-PACFCA 5/60 RMV VEGN |  | SNEATH LANE-PACIFICA | 005/060 | CHS | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-122.460381 | 37.6047 | ETL.7575 | 40825064 | Road | Brush Fuel | Remove |  |  |  |  | PEND | LC | TLR | Roads | Expense | 932 | Bay
118729892 | T2 SALINAS-LAURELES 15/310 RPL ANCW | 44294574 | SALINAS-LAURELES | 015/310 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR2 | SCHD | South | WSIP | [6 empty] | '-121.73949 | 36.5101 | ETL.7930 | 40809891 | Anchor-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  | Y - 11
118734897 | DONNELLS-CURTIS 7/6 RPR GYWW | 44303617 | DONNELLS-CURTIS | 007/006 | ICW | E | 2020_(2) High fire spread TD |  |  |  |  | SCHD | Central | WSIP | [6 empty] | '-120.100016 | 38.1685 | ETL.1400 | 44402507 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 40
118735041 | DONNELLS-CURTIS 7/6 RPR GYWW | 44303617 | DONNELLS-CURTIS | 007/006 | ICW | E | 2020_(2) High fire spread TD |  |  |  |  | SCHD | Central | WSIP | [6 empty] | '-120.100016 | 38.1685 | ETL.1400 | 44560756 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 40
118736659 | T2 SPAULDING-SUMMIT 1/47 REFRAME | 31498188 | SPAULDING-SUMMIT | 001/047 | 93E | E | 2020_(1b) Lines with special commitments |  |  |  | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.624789 | 39.3184 | ETL.8060 | 40618280 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Sacramento
118738216 | T2 DIABLO-MIDWAY #2 40/163 RPL INSS | 31500466 | DIABLO-MIDWAY #2 | 040/163 | 93K | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 | <60D | South | WSIP | [6 empty] | '-120.155834 | 35.1958 | ETL.5970 | 40694500 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 19
118738521 | T3 EI SNEATH LANE-HMB ?9/1 RPL STRW | 31498311 | SNEATH LANE-HALF MOON BAY | ?009/001 | 70Y | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.424373 | 37.5067 | ETL.7212 | 40599265 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Bay |  | Y - 29
118742291 | DI MORAGA-OAKLAND #3 004/033 RPLC HRDT |  | MORAGA-OAKLAND #3 | 004/033 | ICQ | E | 2020_(4) TD tag on high spread line |  |  |  |  | <60D | Central | WSIP | [6 empty] | '-122.218923 | 37.8128 | ETL.2740 | 40645288 | Hardware-Tower | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 11
118743451 | T3 SNEATH LANE-HMB ?9/0 RPL ANCW | 31498312 | SNEATH LANE-HALF MOON BAY | ?009/000 | 93E | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | Central | WSIP | [8 empty] | ETL.7212 | 44384379 | Anchor-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Bay |  | Y - 29
118743554 | T3 SNEATH LANE-HMB ?9/0 RPL ANCW | 31498312 | SNEATH LANE-HALF MOON BAY | ?009/000 | 93E | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | Central | WSIP | [8 empty] | ETL.7212 | 44384377 | Anchor-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Bay |  | Y - 29
118743556 | T3 SNEATH LANE-HMB ?9/0 RPL ANCW | 31498312 | SNEATH LANE-HALF MOON BAY | ?009/000 | 93E | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | Central | WSIP | [8 empty] | ETL.7212 | 44384378 | Anchor-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Bay |  | Y - 29
118744621 | T3 EI CRESTA-RIO OSO 15/123 RPL INSS | 31500129 | CRESTA-RIO OSO | 015/123 | 93K | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.475167 | 39.7551 | ETL.4590 | 40910142 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain
118744622 | T3 EI ROCK CREEK-POE 13/095 RPL CONN |  | ROCK CREEK-POE | 013/095 | ICM | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.475511 | 39.7552 | ETL.5630 | 40762419 | Connector | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | GDP | Maintenance | Expense | 534 | Table Mountain
118745474 | T2 PIT #1-COTTONWOOD 42/360 RPR INSS | 43879413 | PIT #1-COTTONWOOD | 042/360 | ICS | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 | <60D | North Valley | WSIP | [6 empty] | '-122.0909851 | 40.6088 | ETL.5390 | 40636928 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain
118745996 | HUMBOLDT-BRIDGEVILLE 99/5L RPL POLE | 31497841 | HUMBOLDT-BRIDGEVILLE | 099/005 | 70Y | E | 2020_(2) High fire spread TD |  |  |  |  | SCHD | North Coast | WSIP | [6 empty] | '-119.777778 | 36.7846 | ETL.1810 | 44322419 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka
118747283 | T3 EI ROCK CREEK-POE 14/97 RPR SOIL |  | ROCK CREEK-POE | 014/097 | ICQ | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.476379 | 39.7492 | ETL.5630 | 40815393 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
118747469 | EI T3NT ROCK CREEK-POE 14/098 INST MRKS |  | ROCK CREEK-POE | 014/098 | ICS | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.47665 | 39.7474 | ETL.5630 | 40871538 | Marker (i.e. signs)-Steel | Missing | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain
118747750 | T2 HAT CREEK #1-WESTWOOD 4/96 RPR HRDW | 43904280 | HAT CREEK #1-WESTWOOD | 004/096 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.453323 | 40.9126 | ETL.7030 | 40815933 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
118747950 | T2 HAT CREEK #1-WESTWOOD 0/4 RPR POLE | 43904280 | HAT CREEK #1-WESTWOOD | 000/004 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.542565 | 40.9283 | ETL.7030 | 44741489 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
118748010 | T3 GEYSERS #17-FULTON 13/056 RPL INSS | 31505661 | GEYSERS #17-FULTON | 013/056 | 93K | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.760611 | 38.6653 | ETL.4770 | 44859240 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Lakeville
118748366 | HUMBOLDT-BRIDGEVILLE 099/005R RPL STRW | 31497841 | HUMBOLDT-BRIDGEVILLE | 099/005 | 70Y | E | 2020_(2) High fire spread TD |  |  |  |  | SCHD | North Coast | WSIP | [6 empty] | '-122.224337 | 38.0042 | ETL.1810 | 44322420 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka
118748701 | T3 EI CRESTA-RIO OSO 16/130 RPL INSS | 31500129 | CRESTA-RIO OSO | 016/130 | 93K | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.477186 | 39.7418 | ETL.4590 | 40910147 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain
118753058 | EI T3NT CRESTA-RIO OSO 16/137 INST MRKS | 44305193 | CRESTA-RIO OSO | 016/137 | ICS | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.479098 | 39.7299 | ETL.4590 | 40910153 | Marker (i.e. signs)-Steel | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain
118753236 | T3 FULTON-PUEBLO 31/153 RPR FOND | 44306536 | FULTON-PUEBLO | 031/153 | ICQ | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.552458 | 38.4861 | ETL.1600 | 40648677 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville
118755973 | T3 EI CRESTA-RIO OSO 17/140 RPR CNDS | 44305195 | CRESTA-RIO OSO | 017/140 | ICS | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.48005 | 39.7241 | ETL.4590 | 40910156 | Conductor-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain
118756013 | T3 EI ROCK CREEK-POE 15/107 RPL INSS | 31500380 | ROCK CREEK-POE | 015/107 | 93K | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.480524 | 39.7234 | ETL.5630 | 40821648 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain
118758386 | T2 TGER CRK-VLLY SPRINGS 11/90 RPR STRS | 44631103 | TIGER CREEK-VALLEY SPRINGS | 011/090 | ICS | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 | <60D | Central | WSIP | [6 empty] | '-120.653421 | 38.3568 | ETL.5790 | 40585747 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - 11
118761449 | T3NT TIGER CREEK-ELECTRA 6/50 RPR FOND |  | TIGER CREEK-ELECTRA | 006/050 | ICQ | F | 2020_(2) High fire spread TD |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-120.595035 | 38.4179 | ETL.5780 | 40604806 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - 9
118763749 | T2 WEST POINT-VLY SPRINGS 9/107 RPL STRW | 31498708 | WEST POINT-VALLEY SPRINGS | 009/107 | 70Y | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 | <60D | Central | WSIP | [6 empty] | '-120.662012 | 38.3464 | ETL.8350 | 44907040 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Victor
118764774 | T3 EI CRESTA-RIO OSO 14/121 RPR CNDS | 44305195 | CRESTA-RIO OSO | 014/121 | ICS | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.471118 | 39.7587 | ETL.4590 | 40910140 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain
118767180 | T2 WEST POINT-VLLY SPRNGS 5/65C RPL POLE | 31498708 | WEST POINT-VALLEY SPRINGS | 005/065C | 70Y | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 | <60D | Central | WSIP | [6 empty] | '-120.633879 | 38.3896 | ETL.8350 | 42833791 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor
118767184 | T2 BLTA-RIVERBANK-MLNS SS :2/6 RPR STRW | 44303610 | BELLOTA-RIVERBANK-MELONES SW STA | :002/006 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-120.533318 | 37.9089 | ETL.1070 | 40822207 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 15
118767331 | T3 MORAGA-SAN LEANDRO #2 0/6 RPL INSS | 31505512 | MORAGA-SAN LEANDRO #2 | 000/006 | 93K | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.1644898 | 37.8361 | ETL.2780 | 40850662 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - Prog 402
118770952 | T3 DI CASTRO VALLEY-NEWARK 5/29 RPL INSS | 31504845 | CASTRO VALLEY-NEWARK | 005/029 | 93K | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-121.97615 | 37.01 | ETL.4450 | 44394311 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - 13
118771614 | T2 SNEATH LANE-HMB ?11/4 RPL INSS |  | SNEATH LANE-HALF MOON BAY | ?011/004 | 93K | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 | SCHD | Central | WSIP | [6 empty] | '-122.4203129 | 37.4744 | ETL.7212 | 40850594 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - 29
118771916 | CORTINA-VACA 17/113 RPL LADDER | 44295441 | CORTINA-VACA | 017/113 | ICQ | E | 2020_(2) High fire spread TD | [5 empty] | North Valley | WSIP | [6 empty] | '-122.079737 | 38.8878 | ETL.4540 | 40865836 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento
118773113 | T3NT DI TGR CRK-VLY SPNGS 8/063 RPR FOND |  | TIGER CREEK-VALLEY SPRINGS | 008/063 | ICQ | F | 2020_(4) TD tag on high spread line |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-120.621343 | 38.3988 | ETL.5790 | 40753070 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - 11
118774528 | T2 DI CSTRO VALLY-NEWARK 12/063 RPR FOND | 44344849 | CASTRO VALLEY-NEWARK | 012/063 | ICQ | F | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-121.899746 | 37.5759 | ETL.4450 | 40761292 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 12
118775137 | PIT #1-COTTONWOOD 50/447 RPL TOWER | 31474087 | PIT #1-COTTONWOOD | 050/447 | 70S | E | 2020_(2) High fire spread TD | [5 empty] | North Valley | WSIP | [6 empty] | '-122.175877 | 40.5065 | ETL.5390 | 40816480 | Structure-Tower | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Pole Program | Capital | 426 | Table Mountain
118775787 | T3 EI CRESTA-RIO OSO 14/116 RPL INSS | 31500129 | CRESTA-RIO OSO | 014/116 | 93K | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.465144 | 39.7629 | ETL.4590 | 40910137 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain
118778522 | T3 DI MRAGA-SAN LEANDRO #3 3/29 RPR FOND |  | MORAGA-SAN LEANDRO #3 | 003/029 | ICQ | F | 2020_(4) TD tag on high spread line |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-122.130327 | 37.802 | ETL.2790 | 40861007 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  | EBMUD
118778524 | T3 DI MRAGA-SAN LEANDRO #3 3/29 INS HRDT |  | MORAGA-SAN LEANDRO #3 | 003/029 | ICQ | E | 2020_(4b) On structure in bucket 4 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.130327 | 37.802 | ETL.2790 | 40861007 | Hardware-Tower | Missing | Install |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  | EBMUD
118778932 | T3 DI TIGER CRK 8/064 RPR STRT |  | TIGER CREEK-ELECTRA | 008/064 | ICQ | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-120.621524 | 38.3989 | ETL.5780 | 40752893 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - 11
118779405 | T3 FULTON-CALISTOGA :6/7 RPR GYWW | 44305659 | FULTON-CALISTOGA | :006/007 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.589498 | 38.6794 | ETL.6880 | 40912477 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
118779421 | T3 FULTON-CALISTOGA :6/3 RPR GYWW | 44305659 | FULTON-CALISTOGA | :006/003 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.587414 | 38.6737 | ETL.6880 | 40912473 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
118779666 | T2 VACA-PARKWAY 10/056 RPR INSS | 44295444 | VACA-PARKWAY | 010/056 | ICS | E | 2020_(2) High fire spread TD |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.059057 | 38.334 | ETL.5850 | 40852141 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento
118780058 | T2 DRUM-RIO OSO #1 20/161 INST JMPS | 44295442 | DRUM-RIO OSO #1 | 020/161 | ICS | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.093121 | 39.1071 | ETL.1420 | 40594933 | Jumper-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento
118781666 | T3 DI MORAGA-OAKLAND #1 2/16 RPR SPLS | 44621662 | MORAGA-OAKLAND #1 | 002/016 | ICS | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.198084 | 37.832 | ETL.2720 | 40822215 | Splice-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - 8
118781667 | T3 DI MORAGA-OAKLAND #1 2/16 RPR STRS |  | MORAGA-OAKLAND #1 | 002/016 | ICS | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.198084 | 37.832 | ETL.2720 | 40822215 | Structure-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - 8
118782271 | T3 EI KESWICK-TRINITY 3/57 RPR STRW | 43939188 | KESWICK-TRINITY | 003/057 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-122.520258 | 40.6163 | ETL.7270 | 40770362 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
118782304 | T3 DI MORAGA-OAKLAND #1 1/9 RPL INSS | 31504785 | MORAGA-OAKLAND #1 | 001/009 | 93K | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.182487 | 37.841 | ETL.2720 | 40878730 | Insulator-Steel | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - 9
118782507 | T3 EI KESWICK-TRINITY 2/46 REFRAME | 31499732 | KESWICK-TRINITY | 002/046 | 93E | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-122.504841 | 40.6163 | ETL.7270 | 40741744 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain
118782579 | T3 DI TASSAJARA-NEWARK 18/087 RPL INSS | 31484762 | TASSAJARA-NEWARK | 018/087 | 93K | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-121.952408 | 37.61 | ETL.5920 | 40634572 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - Prog 402
118782732 | DI CASTRO VALLEY-NEWARK 015/080 RPR INSS | 44144893 | CASTRO VALLEY-NEWARK | 015/080 | ICS | E | 2020_(4) TD tag on high spread line |  |  |  |  | SCHD | Central | WSIP | [6 empty] | '-121.891078 | 37.5459 | ETL.4450 | 40870674 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - 13
118782793 | T3 EI KESWICK-TRINITY 2/43 RPL CRSW | 31499732 | KESWICK-TRINITY | 002/043 | 93E | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-122.50221 | 40.6165 | ETL.7270 | 40752197 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain
118786361 | EI T3NT CRESTA-RIO OSO 14/114 INST MRKS | 44305193 | CRESTA-RIO OSO | 014/114 | ICS | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.461694 | 39.7654 | ETL.4590 | 40910136 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain
118786797 | T3 DI MORAGA-SAN LEANDRO #3 0/3 RPL INSS | 31504873 | MORAGA-SAN LEANDRO #3 | 000/003 | 93K | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.162805 | 37.8426 | ETL.2790 | 40671359 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - 8
118786798 | T3 DI MORAGA-OAKLAND ""J"" 0/3 RPL INSS | 31511127 | MORAGA-OAKLAND "J" | 000/003 | 93K | E | 2020_(2) High fire spread TD |  | Split Tag - Hanger and Insulator |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.162805 | 37.8426 | ETL.2760 | 40671361 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - Prog 402
118795568 | T2 DI TSSJR-NWRK 10/053 RPLC CONN | 44621453 | TASSAJARA-NEWARK | 020/092 | ICM | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 | <90D | Central | WSIP | [6 empty] | '-121.926362 | 37.5934 | ETL.5920 | 40791096 | Connector | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 534 | Bay |  |  | SFWL
118795593 | T3NT DI MORAGA-SAN LENDR #1 0/3 PNT STRS | 43708450 | MORAGA-SAN LEANDRO #1 | 000/003 | ICS | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-122.163595 | 37.8423 | ETL.2770 | 40644205 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - Prog 402
118795594 | T3 DI EGL RCK-FLTN-SLVRDO 4/18 INS MRKS |  | EAGLE ROCK-FULTON-SILVERADO | 004/018 | ICS | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.764133 | 38.671 | ETL.4392 | 41129321 | Marker (i.e. signs)-Steel | Missing | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville
118796372 | T3 EI KESWICK-TRINITY 0/1 RPL CRSW | 31499718 | KESWICK-TRINITY | 000/001 | 93E | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-122.462303 | 40.6239 | ETL.7270 | 40586337 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain
118796470 | T3 EI KESWICK-TRINITY 0/12 RPL STRW | 31499719 | KESWICK-TRINITY | 000/012 | 70Y | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-122.464214 | 40.6191 | ETL.7270 | 40867097 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain
118796892 | T2 BRIDGEVILLE-COTTONWOOD 22/195L RPL PL | 31499714 | BRIDGEVILLE-COTTONWOOD | 022/195 | 70Y | E | 2020_(2) High fire spread TD |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.685083 | 40.3748 | ETL.1110 | 44423403 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain
118796899 | T3 EI KESWICK-TRINITY 1/26 RPL PL | 31499719 | KESWICK-TRINITY | 001/026 | 70Y | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-122.478112 | 40.6185 | ETL.7270 | 40668374 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain
118797383 | T2 GARBERVILLE-LYTNVL 32/0 RPR GYWW | 44311204 | GARBERVILLE-LAYTONVILLE | 032/000 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.542347 | 39.801 | ETL.8365 | 40587729 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
118897663 | T3NT DI EGL RCK-FLTN-SLVR 3/16B INS MRKS |  | EAGLE ROCK-FULTON-SILVERADO | 003/016B | ICS | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.803694 | 38.8034 | ETL.4392 | 40740504 | Marker (i.e. signs)-Steel | Missing | Install |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 628 | Lakeville
118899344 | T3 DI GEYSERS #12-FULTON 15/64 RPL INSS | 31505664 | GEYSERS #12-FULTON | 015/064 | 93K | E | 2020_(1a) PSPS |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.75472 | 38.6369 | ETL.4750 | 40792278 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Lakeville
118900119 | T3 EI EAGLE ROCK-FULTON-SLVRD 1/10 RPR S | 44310477 | EAGLE ROCK-FULTON-SILVERADO | 001/010 | ICS | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.800903 | 38.8166 | ETL.4392 | 40605188 | Shield Wire / OPGW-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville
118909625 | T2 BELDEN TAP 0/1A RPL STRT | 31500088 | BELDEN TAP | 000/001A | 70S | F | 2020_(2) High fire spread TD |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.250817 | 40.0077 | ETL.4441 | 43198032 | Structure-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Pole Program | Capital | 426 | Table Mountain
118910096 | T3 DI GEYSERS#12-FULTON 0/02 RPR SHLS | 44310544 | GEYSERS #12-FULTON | 000/002 | ICS | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.781607 | 38.8042 | ETL.4750 | 41129167 | Shield Wire / OPGW-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville
118911013 | T3 EI COLGATE-ALLEGHANY A5/134 RPL POLE | 31509242 | COLGATE-ALLEGHANY | A005/134 | 70Y | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.101517 | 39.3319 | ETL.6470 | 42568584 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS erdy | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento
118911578 | T3 DI MORAGA-SN LNDRO#1 01/11 RPR CONS | 44621664 | MORAGA-SAN LEANDRO #1 | 001/011 | ICS | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.155406 | 37.8289 | ETL.2770 | 40594276 | Conductor-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - Prog 402
118911727 | GARBERVILLE-LAYTONVILLE 39/8 RPL STRW | 31500085 | GARBERVILLE-LAYTONVILLE | 039/008 | 70Y | E | 2020_(2) High fire spread TD |  |  |  |  | SCHD | North Coast | WSIP | [6 empty] | '-123.580915 | 39.8901 | ETL.8365 | 40906634 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka
118912485 | T3 EI CRESTA-RIO OSO 20/167 RPL INSS | 31500129 | CRESTA-RIO OSO | 020/167 | 93K | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.494387 | 39.674 | ETL.4590 | 40910178 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain
118912486 | T3 EI CRESTA-RIO OSO 20/167 RMV NEST | 44305195 | CRESTA-RIO OSO | 020/167 | ICS | E | 2020_(4b) On structure in bucket 4 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.494387 | 39.674 | ETL.4590 | 40910178 | Structure-Steel | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain
118913232 | DRUM-SUMMIT #2 16/194A RPL POLE | 31451466 | DRUM-SUMMIT #2 | 016/194A | 70Y | E | 2020_(1b) Lines with special commitments |  |  |  |  | WECC | North Valley | WSIP | [6 empty] | '-120.516404 | 39.3147 | ETL.1450 | 40822544 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento
118913261 | DRUM-SUMMIT #2 14/169A RPL POLE | 31521945 | DRUM-SUMMIT #2 | 014/169A | 70Y | E | 2020_(1b) Lines with special commitments |  |  |  |  | WECC | North Valley | WSIP | [6 empty] | '-120.544928 | 39.3145 | ETL.1450 | 40878359 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento
118913262 | DRUM-SUMMIT #2 14/169B RPL POLE | 31521945 | DRUM-SUMMIT #2 | 014/169B | 70Y | E | 2020_(1b) Lines with special commitments |  |  |  |  | WECC | North Valley | WSIP | [6 empty] | '-120.54497 | 39.3144 | ETL.1450 | 42572802 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento
118913263 | DRUM-SUMMIT #2 14/169C RPL POLE | 31521945 | DRUM-SUMMIT #2 | 014/169C | 70Y | E | 2020_(1b) Lines with special commitments |  |  |  |  | WECC | North Valley | WSIP | [6 empty] | '-120.545019 | 39.3144 | ETL.1450 | 42572803 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento
118913264 | DRUM-SUMMIT #2 16/194B RPL STRW | 31451466 | DRUM-SUMMIT #2 | 016/194B | 70Y | E | 2020_(1b) Lines with special commitments |  |  |  |  | WECC | North Valley | WSIP | [6 empty] | '-120.516427 | 39.3147 | ETL.1450 | 42572822 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento
118913265 | DRUM-SUMMIT #2 16/194C RPL STRW | 31451466 | DRUM-SUMMIT #2 | 016/194C | 70Y | E | 2020_(1b) Lines with special commitments |  |  |  |  | WECC | North Valley | WSIP | [6 empty] | '-120.516471 | 39.3148 | ETL.1450 | 42572823 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento
118913773 | T2 MNT RIO-FRT RSS 25/3 RPL ANCW | 31500206 | ETL.6979.POLE.WOOD | 025/003 | 93E | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 | <90D | North Coast | WSIP | [6 empty] | '-123.181729 | 38.4936 | ETL.6979 | 40648464 | Anchor-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Lakeville
118914363 | T3 MONTA VISTA-JFFRSN #1 15/61 RPL INSS | 44621678 | MONTA VISTA-JEFFERSON #1 | 015/061 | ICS | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | 122.2175 | 37.3239 | ETL.5220 | 40619159 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - 10 | RROSP
118914525 | T3 EI BRIDGEVILLE-GARBERVILLE 9/17 RPR J | 44300097 | BRIDGEVILLE-GARBERVILLE | 009/017 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.731007 | 40.3669 | ETL.6220 | 40810333 | Jumper-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
118914526 | T3 EI BRIDGEVILLE-GARBERVILLE 9/17 RPR S | 44299806 | BRIDGEVILLE-GARBERVILLE | 009/017 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.731007 | 40.3669 | ETL.6220 | 40810333 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
118914527 | EI T3NT BRIDGEVILLE-GRBRVLE 9/17 RMV DEB | 44299809 | BRIDGEVILLE-GARBERVILLE | 009/017 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-123.731007 | 40.3669 | ETL.6220 | 40810333 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
118914829 | T3 DI MORAGA-CASTR VLY 10/43 INST HRDT | 44623422 | MORAGA-CASTRO VALLEY | 010/043 | ICQ | E | 2020_(3) On high spread structure |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.068756 | 37.7381 | ETL.5250 | 40654421 | Hardware-Tower | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 9 | EBMUD
118914941 | T2 DI MENDOCINO-REDBUD 53/264 RPL INSS |  | MENDOCINO-REDBUD | 053/264 | 93K | E | 2020_(2) High fire spread TD |  |  |  | TR2 | <90D | North Coast | WSIP | [6 empty] | '-123.076535 | 39.217 | ETL.2410 | 40797178 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Lakeville
118915571 | PITTSBURG-SAN RAMON 16/064 RPR FOND |  | PITTSBURG-SAN RAMON | 016/064 | ICQ | E | 2020_(4) TD tag on high spread line |  |  |  |  | <90D | Central | WSIP | [6 empty] | '-121.902887 | 37.8174 | ETL.5490 | 40746315 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay
118915975 | T2 DI CORTIN-MNDCNO #1 54/266 RPR STRT | 44302218 | CORTINA-MENDOCINO #1 | 054/266 | ICS | E | 2020_(4) TD tag on high spread line |  |  | Likely MAT error - delink to correct | TR2 | <90D | North Coast | WSIP | [6 empty] | '-123.081093 | 39.2201 | ETL.1330 | 40808943 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville
118916842 | T2 LOWER LAKE-HOMESTAKE 4/6 RPR STRW | 44306528 | LOWER LAKE-HOMESTAKE TAP | 004/006 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-122.554064 | 38.8966 | ETL.1481 | 40809121 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
118917010 | T3 DI SOBRANTE-""R"" #1 1/12 RPR STRT | 44624391 | SOBRANTE-R #1 | 001/012 | ICQ | E | 2020_(3) On high spread structure |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.240263 | 37.908 | ETL.3770 | 40646639 | Structure-Steel | Anti-Climbing Guard | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  |  | EBMUD
118917339 | T2 COALINGA #1-SAN MIGUEL 26/0A RPL STRW | 31455598 | COALINGA #1-SAN MIGUEL | 026/000A | 70Y | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-120.640835 | 35.915 | ETL.8580 | 44190887 | Structure-Wood | No Good/Out of Stdrd | Replace | DOCC srdy | DOCC | Job has been constructed (documentation) | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Pismo Beach |  | Y - 15
118917383 | T2 WST PNT-VLY SPRNGS 5/65A INST MRKW | 44595509 | WEST POINT-VALLEY SPRINGS | 005/065A | ICW | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-120.633935 | 38.3896 | ETL.8350 | 40824062 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor
118917409 | T2 MONTE RIO-FORT ROSS 27/4C RPR GYWW | 44310654 | ETL.6979.POLE.WOOD | 027/004C | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR2 | <90D | North Coast | WSIP | [6 empty] | '-123.204031 | 38.5202 | ETL.6979 | 40741910 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
118917521 | T3 EI MAPLE CREEK-HOOPA 10/5 RPR GYWS | 44178090 | MAPLE CREEK-HOOPA | 010/005 | ICS | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.771942 | 40.8863 | ETL.7490 | 44735733 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Eureka
118917698 | T3 DI FULTON-PUEBLO 33/167 RPR STRT | 44306536 | FULTON-PUEBLO | 033/167 | ICQ | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.593966 | 38.495 | ETL.1600 | 40808453 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville
118918356 | T3 MAPLE CREEK-HOOPA 10/0 RPR GYWW | 44178090 | MAPLE CREEK-HOOPA | 010/000 | ICS | E | 2020_(4) TD tag on high spread line |  |  | Likely MAT error - delink to correct | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.779061 | 40.8803 | ETL.7490 | 44324520 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
118918358 | T3 MAPLE CREEK-HOOPA 10/0 RMV BUTT | 31504608 | MAPLE CREEK-HOOPA | 010/000 | 93J | F | 2020_(4) TD tag on high spread line |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-123.779061 | 40.8803 | ETL.7490 | 44324520 | Structure-Wood | Idle | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 673 | Eureka
118918390 | EI T3NT MAPLE CREEK-HOOPA 9/10 RMV BUTT | 44311200 | MAPLE CREEK-HOOPA | 009/010 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-123.779855 | 40.8799 | ETL.7490 | 40617814 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
118920723 | T3 DI PITTSBURG-SAN MATEO 11/45 RPL INSS | 31504797 | PITTSBURG-SAN MATEO | 011/045 | 93K | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-121.879024 | 37.8838 | ETL.5463 | 40582079 | Insulator-Steel | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - 10
118921552 | T3 DI MONTE RIO-FORT ROSS 20/3 RPR CNDW | 44310656 | ETL.6979.POLE.WOOD | 020/003 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.103783 | 38.4818 | ETL.6979 | 40648460 | Conductor-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
118921769 | T3 EI KESWICK-TRINITY 5/72 RPL ANCW | 31500438 | KESWICK-TRINITY | 005/072 | 93E | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-122.545832 | 40.6308 | ETL.7270 | 40617597 | Anchor-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain
118921855 | T2 DI LAKEVILLE #1 009/005 RPR GYWW | 44310740 | LAKEVILLE #1 | 009/005 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-122.542543 | 38.3739 | ETL.7360 | 40751124 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
118922133 | T3 DI MNT VST-JFRSN #1 18/79 RPR STRT |  | MONTA VISTA-JEFFERSON #1 | 018/079 | ICQ | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.294628 | 37.4457 | ETL.5220 | 40869051 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  | Huddart Park
118922208 | T3 DI MNT VST-JFRSN #1 18/79 RPLC INSS | 31507365 | MONTA VISTA-JEFFERSON #1 | 018/079 | 93K | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | 122.2177 | 37.4268 | ETL.5220 | 40892241 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  |  | Huddart Park
118923337 | T2 DI FULTON-IGNACIO #1 21/107 RPR FOND | 44310479 | FULTON-IGNACIO #1 | 021/107 | ICQ | F | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.591582 | 38.3119 | ETL.4680 | 40811146 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville
118923807 | T2 DI MENDOCINO-REDBUD 53/262 RPLC INSS |  | MENDOCINO-REDBUD | 053/262 | 93K | E | 2020_(2) High fire spread TD |  |  |  | TR2 | <90D | North Coast | WSIP | [6 empty] | '-123.07556 | 39.2154 | ETL.2410 | 40726475 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Lakeville
118925341 | DI METCALF-GREEN VALLEY 9/65 INST MRKW | 44571490 | METCALF-GREEN VALLEY | 009/065 | ICW | F | 2020_(4b) On structure in bucket 4 |  |  | Likely MAT error - delink to correct |  |  | South | WSIP | [6 empty] | '-121.654254 | 37.1218 | ETL.2540 | 40751284 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 630 | Moss Landing |  | Y - 2
118925780 | T3NT DI MORAGA-SAN LNDR #3 2/20 RPR FOND | 44303862 | MORAGA-SAN LEANDRO #3 | 002/020 | ICQ | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-122.139234 | 37.8158 | ETL.2790 | 40587930 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  | EBMUD
118925984 | T3 EI ROCK CREEK-POE :2/15 RPR FOND |  | ROCK CREEK-POE | :002/015 | ICQ | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.281704 | 39.9881 | ETL.5630 | 40905953 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
118926078 | T3 EI CARIBOU-TABLE MTN 18/132 RPR FOND |  | CARIBOU-TABLE MTN | 018/132 | ICQ | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.279929 | 39.983 | ETL.4440 | 40674583 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
118926143 | DI SOBRANTE-""""G"""" #1"" 5/40 RPR STRT |  | SOBRANTE-"G" #1 | 005/040 | ICQ | E | 2020_(4) TD tag on high spread line |  |  |  |  | <90D | Central | WSIP | [6 empty] | '-122.300432 | 37.9169 | ETL.3720 | 40607984 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay
118926761 | T3 EI SNEATH LANE-HMB ?8/5 RPL INSW | 31500745 | SNEATH LANE-HALF MOON BAY | ?008/005 | 93I | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.425079 | 37.5152 | ETL.7212 | 44384387 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Bay |  | Y - 29
118927308 | T3 DI MORAGA-SAN LEANDRO#1 3/22 RPL INSS | 31504872 | MORAGA-SAN LEANDRO #1 | 003/022 | 93K | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.137432 | 37.8128 | ETL.2770 | 40704861 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  |  | EBMUD
118927335 | T2 HUMBOLDT-TRINITY 112/2 RPL POLE | 31500770 | HUMBOLDT-TRINITY | 112/002 | 70Y | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-124.078645 | 40.7734 | ETL.1820 | 44560679 | Structure-Wood | Rotten | Replace | UNSC erdy srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2020-05-21
118927442 | T3 DI MORAGA-SAN LEANDRO#1 3/22 RMV VEG |  | MORAGA-SAN LEANDRO #1 | 003/022 | HNA | E | 2020_(3) On high spread structure |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.137501 | 37.8128 | ETL.2770 | 40646045 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Bay
118927805 | T2 CLEAR LAKE-KONOCTI 19/5 RPR GYWW | 44310559 | CLEAR LAKE-KONOCTI | 019/005 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-122.789985 | 38.948 | ETL.6852 | 40747630 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
118927834 | T3 DRM-GRS VLY-WEIMR B022/491 RPL PL | 31500477 | DRUM-GRASS VALLEY-WEIMAR | B022/491 | 70Y | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.01182 | 39.1908 | ETL.6760 | 40815106 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento |  |  | County
118927854 | T2 BRIDGEVILLE-COTTONWD 22/195R RPL POLE | 31499714 | BRIDGEVILLE-COTTONWOOD | 022/195 | 70Y | E | 2020_(2) High fire spread TD |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.685083 | 40.3748 | ETL.1110 | 44423404 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain
118927878 | T2 CARIBOU #2 2/22 RPR GYWW |  | CARIBOU #2 | ;002/022 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-120.948522 | 39.9941 | ETL.6280 | 40698759 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
118928808 | T3NT DI MNTE RIO-FORT ROSS 21/4 INS MRKW |  | ETL.6979.POLE.WOOD | 021/004 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-123.120014 | 38.477 | ETL.6979 | 40770583 | Marker (i.e. signs)-Wood | Missing | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
118928838 | T2 HUMBOLDT-TRINITY 112/2 RPL POLE | 31500770 | HUMBOLDT-TRINITY | 112/002 | 70Y | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-124.078645 | 40.7734 | ETL.1820 | 44560641 | Structure-Wood | Rotten | Replace | UNSC erdy srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2020-05-21
118928839 | T2 HUMBOLDT-TRINITY 112/2 RPL POLE | 31500770 | HUMBOLDT-TRINITY | 112/002 | 70Y | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-124.078645 | 40.7734 | ETL.1820 | 44560612 | Structure-Wood | Rotten | Replace | UNSC erdy srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka |  |  | 2020-05-21
118929251 | T3 EI SANTA FE GEOTHERMAL TAP 0/1 RPR FO | 44310549 | SANTA FE GEOTHERMAL TAP | 000/001 | ICQ | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.743451 | 38.7878 | ETL.4782 | 40584987 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville
118930189 | T2 COALINGA #1-SAN MIGUEL 32/0 RPL HRDS |  | COALINGA #1-SAN MIGUEL | 032/000 | ICS | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 | <90D | South | WSIP | [6 empty] | '-120.636155 | 35.8293 | ETL.8580 | 40601112 | Hardware-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Pismo Beach |  | Y - 14
118930321 | T3 EI SNEATH LANE-HMB ?3/7 RPL POLE | 31500744 | SNEATH LANE-HALF MOON BAY | ?003/007 | 70Y | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.477939 | 37.5569 | ETL.7212 | 43249686 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Bay |  |  | RCDT
118931751 | T3 EI GEYSERS #12-FULTON 0/3 RPR SHLS | 44310544 | GEYSERS #12-FULTON | 000/003 | ICS | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.778493 | 38.8017 | ETL.4750 | 41129168 | Shield Wire / OPGW-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville
118933116 | T2 CARIBOU-PLUMAS JCT 0/6 INST DAMW | 44304459 | CARIBOU-PLUMAS JCT | 000/006 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.140699 | 40.0839 | ETL.6290 | 40826471 | Damper-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
118933190 | T3 DRUM-RIO OSO #2 5/063 RPR JUMPER | 44300640 | DRUM-RIO OSO #2 | 005/063 | ICS | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.855862 | 39.213 | ETL.1430 | 40655122 | Jumper-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento
118933234 | T2 CARIBOU #2 0/017 REFRAME | 31500636 | CARIBOU #2 | ;000/017 | 93E | E | 2020_(2) High fire spread TD |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-120.962288 | 40.0205 | ETL.6280 | 40824669 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain
118933422 | T2 WEST POINT-VALLY SPRNGS 5/68 RPL POLE | 31498708 | WEST POINT-VALLEY SPRINGS | 005/068 | 70Y | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 | <90D | Central | WSIP | [6 empty] | '-120.63505 | 38.3866 | ETL.8350 | 40580256 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor
118933491 | T3NT DIABLO-GATES #1 0/2C INST MRKS |  | DIABLO-GATES #1 | 000/002C | ICS | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR3 |  | South | WSIP | [6 empty] | '-120.845766 | 35.2207 | ETL.5960 | 40741756 | Marker (i.e. signs)-Steel | No Good/Out of Stdrd | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Pismo Beach |  | Y - 17
118933579 | T3 EI FULTON-PUEBLO 27/130 RPR FOND | 44306536 | FULTON-PUEBLO | 027/130 | ICQ | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.475879 | 38.4904 | ETL.1600 | 40582771 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville
118933594 | T3 EAGLE ROCK-FULTN-SLVRD 4/23 RPR JUMS | 44310477 | EAGLE ROCK-FULTON-SILVERADO | 004/023 | ICS | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.798086 | 38.7769 | ETL.4392 | 40660132 | Jumper-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville
118936241 | T3 OLEUM-G #1 9/060 RPL INSS | 31503752 | OLEUM-G #1 | 009/060 | 93K | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-121.362728 | 38.0283 | ETL.3150 | 43601234 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - 8 | EBRPD
118936478 | EI T3NT CARIBOU-TABLE MTN 38/280 INST HV |  | CARIBOU-TABLE MTN | 038/280 | ICS | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.483791 | 39.7696 | ETL.4440 | 40604591 | Marker (i.e. signs)-Steel | No Good/Out of Stdrd | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain
118937286 | IGNACIO-MARE ISLAND#1 13/93 REPL TOWER |  | IGNACIO-MARE ISLAND #1 | 013/093 | 70S | B | 2020_(0) A and B Tags | [5 empty] | North Coast | WSIP |  |  |  |  | System Inspection | Tower did not FSR this structure; upgraded by SI; in project to replace. | '-122.337826 | 38.1525 | ETL.1830 | 40760246 | Bay Water-Tower | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLQ | Pole Program | Capital | 426 | Lakeville
118937557 | T3 DI SOBRANTE-""""R"""" #2 2/16 RPL INSS | 31510378 | SOBRANTE-R #2 | 002/016 | 93K | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.249227 | 37.9104 | ETL.3780 | 40830934 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay
118937817 | T3 EI BRIDGEVILLE-GARBERVI 11/5 RPR WDPK | 44299806 | BRIDGEVILLE-GARBERVILLE | 011/005 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.71576 | 40.3508 | ETL.6220 | 40752659 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
118937891 | T3 EI BRIDGEVILLE-GARBERVILL 10/17 RPR C | 44300097 | BRIDGEVILLE-GARBERVILLE | 010/017 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.719665 | 40.3566 | ETL.6220 | 40810335 | Conductor-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
118937892 | T3 EI BRIDGEVILLE-GRBRVILL 10/17 RMV DEB | 31504607 | BRIDGEVILLE-GARBERVILLE | 010/017 | 93J | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.719665 | 40.3566 | ETL.6220 | 40810335 | Structure-Wood | Idle | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 673 | Eureka
118937899 | T3 EI BRIDGEVILLE-GARBERVILLE 11/5 RPL S | 44300097 | BRIDGEVILLE-GARBERVILLE | 011/005 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.71576 | 40.3508 | ETL.6220 | 40752659 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
118937901 | T3 EI BRIDGEVILLE-GARBERVILL 10/13 RPL P | 31500972 | BRIDGEVILLE-GARBERVILLE | 010/013 | 70Y | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.721445 | 40.3592 | ETL.6220 | 40650758 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka
118938516 | T2 DI DRUM-SUMMIT#1 25/299B RPL POLE | 31498145 | DRUM-SUMMIT #1 | 025/299B | 70Y | E | 2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.355483 | 39.3093 | ETL.1440 | 42572727 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS erdy | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento
118938517 | T2 DI DRUM-SUMMIT#1 25/299C RPL POLE | 31498145 | DRUM-SUMMIT #1 | 025/299C | 70Y | E | 2020_(1b) Lines with special commitments |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.355498 | 39.3093 | ETL.1440 | 42572728 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS erdy | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento
118939119 | T3 EI GEYSERS #17-FULTON 2/14 RPR SPLS | 44624745 | GEYSERS #17-FULTON | 002/014 | ICS | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.7979 | 38.8065 | ETL.4770 | 40786522 | Splice-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville
118939606 | T3 DI SOBRANTE ""R"" #2 1/13 REPL INSS | 31510378 | SOBRANTE-R #2 | 001/013 | 93K | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.244409 | 37.9091 | ETL.3780 | 44396595 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  |  | EBMUD
118940192 | T3 DI SOBRANTE-""G"" #2"" 2/15 RPL INSS |  | SOBRANTE-"G" #2 | 002/015 | 93K | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.248716 | 37.9108 | ETL.3730 | 40773243 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  |  | EBMUD
118940222 | ROUND MTN-COTTONWD #3 49/433 RPR FOND | 43932111 | ROUND MTN-COTTONWOOD #3 | 049/433 | ICQ | E | 2020_(2) High fire spread TD | [5 empty] | North Valley | WSIP | [6 empty] | '-122.162628 | 40.5228 | ETL.5650 | 40657340 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
118940787 | T3 EI BRIDGEVILLE-GARBRVILL 9/5 RPR STRW | 44299806 | BRIDGEVILLE-GARBERVILLE | 009/005 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.738576 | 40.3741 | ETL.6220 | 40752655 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
118940794 | T3 EI BRIDGEVILLE-GARBERVLE 9/15 RPR JUM | 44300097 | BRIDGEVILLE-GARBERVILLE | 009/015 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.733536 | 40.3687 | ETL.6220 | 40768709 | Jumper-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
118940795 | T3 EI BRIDGEVILLE-GARBERVLE 9/15 RPR PL | 44299806 | BRIDGEVILLE-GARBERVILLE | 009/015 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.733536 | 40.3687 | ETL.6220 | 40768709 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
118940798 | EI T3NT BRIDGEVILLE-GARBRVL 9/16 RMV VEG |  | BRIDGEVILLE-GARBERVILLE | 009/016 | HNA | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-123.732711 | 40.3682 | ETL.6220 | 40826271 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Eureka
118940803 | T3 EI GEYSERS #12 - FULTON 3/14A RPR STR | 44631264 | GEYSERS #12-FULTON | 003/014A | ICS | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.761708 | 38.7679 | ETL.4750 | 44469284 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Lakeville
118940804 | EI T3NT GEYSERS #12-FULTON 3/14A INST MR |  | GEYSERS #12-FULTON | 003/014A | ICS | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.761708 | 38.7679 | ETL.4750 | 44469284 | Marker (i.e. signs)-Steel | Missing | Install |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 628 | Lakeville
118940882 | T3 EI GEYSERS #12-FULTON 3/14B RPR STRS | 44631264 | GEYSERS #12-FULTON | 003/014B | ICS | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.761772 | 38.7678 | ETL.4750 | 44468539 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Lakeville
118941208 | T3 EI BRIDGEVILLE-GARBRVILL 10/7 RMV DEB | 31504607 | BRIDGEVILLE-GARBERVILLE | 010/007 | 93J | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.725967 | 40.363 | ETL.6220 | 44814412 | Structure-Wood | Idle | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 673 | Eureka
118941962 | T2 CORTINA-MENDOCINO #1 54/266 RPL ROAD | 31516303 | CORTINA-MENDOCINO #1 | 054/266 | 71Y | E | 2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.081093 | 39.2201 | ETL.1330 | 40808943 | Road | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLR | Roads | Capital | 374 | Lakeville
118942751 | T3 DI MRAGA-SN LNDRO #1 4/32 RPR STRT | 44303861 | MORAGA-SAN LEANDRO #1 | 004/032 | ICQ | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.1285 | 37.7953 | ETL.2770 | 40657121 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 9
118942979 | EI T3NT CARIBOU-TABLE MTN 40/295 RPR FON |  | CARIBOU-TABLE MTN | 040/295 | ICQ | F | 2020_(4) TD tag on high spread line |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.497857 | 39.7439 | ETL.4440 | 40758293 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain |  |  | released 7-13-20
118943309 | T2 VACA-PARKWAY 3/23 RPL INSS | 44305727 | VACA-PARKWAY | 003/023 | ICS | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.989066 | 38.4108 | ETL.5850 | 40660123 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento
118943649 | T3 DI FULTON-CALISTOGA ;8/1 RPL HRDT | 44306735 | FULTON-CALISTOGA | ;008/001 | ICQ | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.6019 | 38.4965 | ETL.6880 | 40593317 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville
118944195 | T3 DI FULTON-CALISTOGA ;5/7 RPR INSS |  | FULTON-CALISTOGA | ;005/007 | ICS | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.645247 | 38.497 | ETL.6880 | 40825316 | Insulator-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville
118944860 | T3NT DI YANKE (NORTH FORK) 0/6 INST MRKW |  | YANKE (NORTH FORK) TAP (IDLE) | 000/006 | ICW | F | 2020_(1b) Lines with special commitments |  | DLFL upon completion of 30878389 |  | TR3 |  | South | WSIP | [6 empty] | '-119.499558 | 37.2336 | ETL.9341 | 40823135 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Fresno |  | Y - Prog 401
118946262 | T3 MONTE RIO-FULTON 13/1 RPL POLE | 31501349 | MONTE RIO-FULTON | 013/001 | 70Y | E | 2020_(4b) On structure in bucket 4 |  |  |  | TR3 | LATE | North Coast | WSIP | [8 empty] | ETL.7630 | 44315964 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Lakeville
118946338 | T3 DI SLT SPRGS-TGR CRK 16/127 RPLC INSS | 31502542 | SALT SPRINGS-TIGER CREEK | 016/127 | 93K | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-120.492046 | 38.4481 | ETL.3500 | 40827321 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Victor |  | Y - 17
118946429 | T3 DI SAN RAMON-MORAGA 5/22 RPLC INSS | 31504799 | SAN RAMON-MORAGA | 005/022 | 93K | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.002386 | 37.7013 | ETL.5660 | 40852159 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - 10
118946523 | T2 DI SLT SPRNGS-TGR CRK 7/60 RPR INSS | 44631104 | SALT SPRINGS-TIGER CREEK | 007/060 | ICS | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 | <90D | Central | WSIP | [6 empty] | '-120.335805 | 38.4767 | ETL.3500 | 40620104 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - 17
118946601 | T3 MONTE RIO-FULTON 13/1L REPL POLE | 31501349 | MONTE RIO-FULTON | 013/001 | 70Y | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Coast | WSIP | [8 empty] | ETL.7630 | 44315962 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville
118946994 | T2 VOLTA-DESCHUTES 15/328 REFRAME | 31416186 | VOLTA-DESCHUTES | 015/328 | 93E | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.14629 | 40.5334 | ETL.8290 | 40592140 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain
118947031 | T2 VOLTA-DESCHUTES 14/302 REFRAME | 31416186 | VOLTA-DESCHUTES | 014/302 | 93E | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.124928 | 40.5254 | ETL.8290 | 40817183 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain
118947136 | T2 STNSLS-MLNS SW ST-MNT :5/29 INST MRKS |  | STANISLAUS-MELONES SS-MANTECA #1+ | :005/029 | ICS | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-120.607476 | 37.9675 | ETL.3830 | 40856491 | Marker (i.e. signs)-Steel | No Good/Out of Stdrd | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - 22
118947138 | T3 VOLTA-DESCHUTES 003/084 REFRAME | 31416186 | VOLTA-DESCHUTES | 003/084 | 93E | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.937202 | 40.4772 | ETL.8290 | 40868506 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain
118947140 | T3 VOLTA-DESCHUTES 3/083 REFRAME | 31416186 | VOLTA-DESCHUTES | 003/083 | 93E | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.936385 | 40.477 | ETL.8290 | 40825124 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain
118947143 | T3 VOLTA-DESCHUTES 1/036 REFRAME | 31416186 | VOLTA-DESCHUTES | 001/036 | 93E | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.896662 | 40.4672 | ETL.8290 | 40656909 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain
118947144 | T3 VOLTA-DESCHUTES 0/020 REFRAME | 31416186 | VOLTA-DESCHUTES | 000/020 | 93E | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.882562 | 40.4637 | ETL.8290 | 40868500 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain
118947152 | T3 VOLTA-DESCHUTES 0/016 REFRAME | 31416186 | VOLTA-DESCHUTES | 000/016 | 93E | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.879192 | 40.4629 | ETL.8290 | 40759234 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain
118947264 | T3NT DI SAN RAMON-MORAGA 3/18 PNT STRS | 44586180 | SAN RAMON-MORAGA | 003/018 | ICS | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-121.990765 | 37.7098 | ETL.5660 | 40644606 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - Prog 402
118947644 | T3 EI GEYSERS #7-EAGLE ROCK 0/8 RPR FOND | 44306736 | GEYSERS #7-EAGLE ROCK | 000/008 | ICQ | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.810963 | 38.8191 | ETL.1680 | 40861322 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville
118947777 | T3 DI MORAGA-CSTR VALLEY 9/40 RPLC INSS | 44609775 | MORAGA-CASTRO VALLEY | 009/040 | ICS | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.072319 | 37.7479 | ETL.5250 | 40596226 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - 9 | EBMUD
118947800 | T3 DI WSHN-SN JOAQUIN #3 1/14 REPL PL | 31501721 | WISHON-SAN JOAQUIN #3 | 001/014 | 70Y | E | 2020_(1a) PSPS |  |  |  | TR3 | LATE | South | WSIP | [6 empty] | '-119.502722 | 37.2312 | ETL.9340 | 40748452 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Fresno |  |  | USFS
118947848 | T3 FULTON-HOPLAND 27/012 REPLACE POLE | 31478309 | FULTON-HOPLAND | 027/012 | 70Y | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.998643 | 38.8228 | ETL.6890 | 40700692 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville
118948201 | T3 EI BRIDGEVILLE-GARBERVILLE 9/3 REFRAM | 31501358 | BRIDGEVILLE-GARBERVILLE | 009/003 | 93E | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.739792 | 40.3756 | ETL.6220 | 40666708 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Eureka
118948207 | EI T3NT EAGL RCK-FLTN-SLVRD :0/1 PNT STR | 44304081 | EAGLE ROCK-FULTON-SILVERADO | :000/001 | ICQ | F | 2020_(4b) On structure in bucket 4 |  |  | Likely MAT error - delink to correct | TR3 |  | North Coast | WSIP | [6 empty] | '-122.761291 | 38.7405 | ETL.4392 | 41129397 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Lakeville
118948274 | T3 EI BRIDGEVILLE-GARBERVILLE 8/17 RPR G | 44300097 | BRIDGEVILLE-GARBERVILLE | 008/017 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.741361 | 40.3803 | ETL.6220 | 44813261 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
118948275 | T3 EI BRIDGEVILLE-GARBERVILLE 8/8 RPR IN | 44300097 | BRIDGEVILLE-GARBERVILLE | 008/008 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.742444 | 40.3862 | ETL.6220 | 40876486 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
118948278 | T3 EI BRIDGEVILLE-GARBERVILLE 8/10 REPL | 44300097 | BRIDGEVILLE-GARBERVILLE | 008/010 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.742211 | 40.3847 | ETL.6220 | 40591068 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
118948305 | T3 EI BRIDGEVILLE-GARBERVILLE 8/4 REPL S | 44300097 | BRIDGEVILLE-GARBERVILLE | 008/004 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.742729 | 40.3894 | ETL.6220 | 40769368 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
118948306 | T3 EI BRIDGEVILLE-GARBERVILL 7/4 RMV PL | 44299809 | BRIDGEVILLE-GARBERVILLE | 007/004 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.743556 | 40.403 | ETL.6220 | 40769379 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
118948307 | T3 EI BRIDGEVILLE-GARBERVILLE 7/4 RPL ST | 31522167 | BRIDGEVILLE-GARBERVILLE | 007/004 | 70Y | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.743556 | 40.403 | ETL.6220 | 40769379 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka
118948380 | T3 EI BRIDGEVILLE-GARBERVILL 7/5 RMV PL | 44299809 | BRIDGEVILLE-GARBERVILLE | 007/005 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.743198 | 40.4022 | ETL.6220 | 40752653 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
118948384 | T3 EI BRIDGEVILLE-GARBERVILL 7/6 RMV PL | 31504607 | BRIDGEVILLE-GARBERVILLE | 007/006 | 93J | F | 2020_(3) On high spread structure |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.742725 | 40.4012 | ETL.6220 | 40826273 | Structure-Wood | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 630 | Eureka
118948407 | T3 EI BRIDGEVILLE-GARBERVILL 7/7 RPR JUM | 44300097 | BRIDGEVILLE-GARBERVILLE | 007/007 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.7421734 | 40.3999 | ETL.6220 | 40835203 | Jumper-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
118948412 | T3 EI BRIDGEVILLE-GARBERVILL 7/9 RMV PL | 31504607 | BRIDGEVILLE-GARBERVILLE | 007/009 | 93J | F | 2020_(3) On high spread structure |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.741214 | 40.3978 | ETL.6220 | 40862511 | Structure-Wood | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 630 | Eureka
118948416 | T3 EI BRIDGEVILLE-GARBERVL 7/12 RMV PL B | 44299809 | BRIDGEVILLE-GARBERVILLE | 007/012 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.74209 | 40.3949 | ETL.6220 | 40698417 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
118948450 | EI T3NT BRIDGEVILLE-GARBERVL 7/14 INST V | 44300097 | BRIDGEVILLE-GARBERVILLE | 007/014 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-123.742608 | 40.3932 | ETL.6220 | 40752608 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
118948452 | T3 EI BRIDGEVILLE-GARBERVILLE 8/0 RPR GY | 44300097 | BRIDGEVILLE-GARBERVILLE | 008/000 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.742979 | 40.392 | ETL.6220 | 40614599 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
118949765 | T3 EI EAGL RCK-FLTN-SLVRD :3/15 RMV NEST |  | EAGLE ROCK-FULTON-SILVERADO | :003/015 | ICS | E | 2020_(3) On high spread structure |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.766466 | 38.6857 | ETL.4392 | 41129318 | Structure-Steel | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville
118949767 | T3 EI EAGL RCK-FLTN-SLVRD :3/13 RPR FOND | 44304081 | EAGLE ROCK-FULTON-SILVERADO | :003/013 | ICQ | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.76376 | 38.6931 | ETL.4392 | 41129316 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville
118949768 | EI T3NT EAGL RCK-FLTN-SLVRD :3/15 PNT ST | 43730698 | EAGLE ROCK-FULTON-SILVERADO | :003/015 | ICS | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.766466 | 38.6857 | ETL.4392 | 41129318 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville
118950503 | T3 DI FULTON-CALISTOGA ;007/1 BENT STL | 44306735 | FULTON-CALISTOGA | ;007/001 | ICQ | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.619841 | 38.4971 | ETL.6880 | 40593315 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville
118950870 | T2 EI DORADO-MISSR FLT#2 5/42 RMV DRBRIS | 44310642 | ELDORADO-MISSOURI FLAT #2 | 005/042 | ICS | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-120.711813 | 38.7584 | ETL.1540 | 40712536 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento
118950973 | T3 DIMONTE RIO-FULTON 14/14 RPLC SPLW |  | MONTE RIO-FULTON | 014/014 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.011995 | 38.4716 | ETL.7630 | 44401983 | Splice-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
118951405 | T3 EI GEYSERS #17-FULTON 10/46 RPR INSS | 44630990 | GEYSERS #17-FULTON | 010/046 | ICS | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.76156 | 38.7052 | ETL.4770 | 40842350 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville
118951891 | T2 MAPLE CREEK-HPA 8/5 REVIEW POLE DEPTH | 44497905 | MAPLE CREEK-HOOPA | 008/005 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.801362 | 40.8638 | ETL.7490 | 44707296 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
118952420 | T2 DI CRTN-MENDOCINO #1 26/126 RPL INSS | 31518808 | CORTINA-MENDOCINO #1 | 026/126 | 93K | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.664634 | 39.0293 | ETL.1330 | 40835490 | Insulator-Steel | No Good/Out of Stdrd | Replace | srdy DCNL |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Lakeville
118952421 | T2 DI MENDOCINO-REDBUD 26/126 RPL INSS |  | MENDOCINO-REDBUD | 026/126 | 93K | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 | <90D | North Coast | WSIP | [6 empty] | '-122.664634 | 39.0293 | ETL.2410 | 40835492 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Lakeville
118952480 | T3NT DI SBRNT-GRZLY-CLNT #1 5/48 RPR FND |  | SOBRNTE-GRIZZLY-CLARMNT #1+ | 005/048 | ICQ | F | 2020_(4) TD tag on high spread line |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-122.214609 | 37.8494 | ETL.3740 | 40646528 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 9
118952863 | T3 DI GEYSERS#3-CLVRDLE 8/98 RPR POLE | 44580896 | GEYSERS #3-CLOVERDALE | 008/098 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.956213 | 38.7974 | ETL.1650 | 40818244 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
118952923 | T2 DI CORTINA-MNDCNO#1 41/197 RPR FOND |  | CORTINA-MENDOCINO #1 | 041/197 | ICQ | F | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.880086 | 39.1435 | ETL.1330 | 40809331 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville
118953078 | T2 SPAULDING-SUMMIT 15/485 RPR GYWW | 44310649 | SPAULDING-SUMMIT | 015/485 | ICW | E | 2020_(1b) Lines with special commitments |  |  |  | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.387676 | 39.3284 | ETL.8060 | 40826237 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
118953080 | T2 DI CORTINA-MNDCNO#1 36/174 BENT STL |  | CORTINA-MENDOCINO #1 | 036/174 | ICQ | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 | <90D | North Coast | WSIP | [6 empty] | '-122.80641 | 39.1103 | ETL.1330 | 40762063 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville
118953081 | T2 DI CORTINA-MNDCNO#1 36/174 RPR FOND |  | CORTINA-MENDOCINO #1 | 036/174 | ICQ | F | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.80641 | 39.1103 | ETL.1330 | 40762063 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville
118953082 | T2 DI CORTINA-MNDCNO#1 34/164 RPR FOND | 44238817 | CORTINA-MENDOCINO #1 | 034/164 | ICQ | F | 2020_(2) High fire spread TD |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.773948 | 39.0901 | ETL.1330 | 40762061 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville
118953120 | T3 DI DONNELLS-MI-WUK 18/1 REPL POLE | 31501612 | DONNELLS-CURTIS | 018/001 | 70Y | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-120.210896 | 38.0558 | ETL.1400 | 40579920 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 40
118954291 | T2 SALMON CREEK TAP 7/8 RPR GYWW |  | SALMON CREEK TAP | 007/008 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 | <90D | North Coast | WSIP | [6 empty] | '-123.070343 | 38.378 | ETL.6981 | 40860986 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
118954685 | EI T3NT YANKE (NORTH FORK) TP 0/3 CANCEL |  | YANKE (NORTH FORK) TAP (IDLE) | 000/003 | ICW | F | 2020_(1b) Lines with special commitments |  | DLFL upon completion of 30878389 | CANCEL/CNCL | TR3 |  | South | WSIP | [6 empty] | '-119.499698 | 37.2312 | ETL.9341 | 40646693 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Fresno |  | Y - Prog 401
118954686 | T3 EI YANKE (NORTH FORK) TAP 0/3 RPR GYW | 44321420 | YANKE (NORTH FORK) TAP (IDLE) | 000/003 | ICW | E | 2020_(1b) Lines with special commitments |  | DLFL upon completion of 30878389 |  | TR3 | LATE | South | WSIP | [6 empty] | '-119.499698 | 37.2312 | ETL.9341 | 40646693 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Fresno |  | Y - Prog 401
118955392 | T3 WEST POINT-VLLY SPRINGS 0/13 RPR GYWW | 44631105 | WEST POINT-VALLEY SPRINGS | 000/013 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-120.563855 | 38.4253 | ETL.8350 | 40643809 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor
118955469 | T3 DI GEYSERS #3-CLOVERDALE RPR GYWW | 44580896 | GEYSERS #3-CLOVERDALE | 005/068 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.91411 | 38.815 | ETL.1650 | 40603859 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
118955472 | T3 MIDDLE FORK #1 4/64 REFRAME | 31471244 | MIDDLE FORK #1 | 004/064 | 93E | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.652003 | 38.9981 | ETL.8405 | 40649998 | Crossarm-Wood | No Good/Out of Stdrd | Replace | DOCC srdy | DOCC | Job has been constructed (documentation) | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Sacramento
118955743 | T2 DI EAGLE ROCK-CORTINA 15/74 RPL INSS | 31505513 | EAGLE ROCK-CORTINA | 015/074 | 93K | E | 2020_(2) High fire spread TD |  |  |  | TR2 |  | North Coast | WSIP | [8 empty] | ETL.1470 | 40792690 | Insulator-Steel | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Lakeville
118956550 | T3 SPRING GAP TAP 1/5A RPL POLE | 31501619 | SPRING GAP TAP | 001/005A | 70Y | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-120.103043 | 38.1679 | ETL.1402 | 44550064 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 12
118956576 | T3 SPRING GAP TAP 1/5B RPL POLE | 31501619 | SPRING GAP TAP | 001/005B | 70Y | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-120.103072 | 38.1678 | ETL.1402 | 44549850 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 12
118956666 | T3 SPRING GAP TAP 1/5C RPL POLE | 31501619 | SPRING GAP TAP | 001/005C | 70Y | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-120.103016 | 38.1679 | ETL.1402 | 44549849 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 12
118956825 | T3 EI BRIDGEVILLE-GARBERVILL 5/11 INST I | 31501770 | BRIDGEVILLE-GARBERVILLE | 005/011 | 93I | E | 2020_(2) High fire spread TD |  |  | Likely MAT error - delink to correct | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.7617139 | 40.4226 | ETL.6220 | 40611404 | Jumper-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Eureka
118956862 | T3 EI BRIDGEVILLE-GARBERVILLE 5/2 RPR ST | 44299806 | BRIDGEVILLE-GARBERVILLE | 005/002 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.763432 | 40.4282 | ETL.6220 | 40698435 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
118956964 | T3 EI BRIDGEVILLE-GARBERVILLE 5/19 JUMPW | 44300097 | BRIDGEVILLE-GARBERVILLE | 005/019 | ICW | F | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.7599506 | 40.4165 | ETL.6220 | 40899732 | Jumper-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
118956976 | T3 DI GEYSERS#3-CLVRDL 9/109 RPL POLE | 31501745 | GEYSERS #3-CLOVERDALE | 009/109 | 70Y | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.970607 | 38.8007 | ETL.1650 | 40761633 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville
118957031 | T3 DI SALMON CREEK TAP 0/8 RPR POLE |  | SALMON CREEK TAP | 000/008 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.12086 | 38.4681 | ETL.6981 | 40872229 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
118957081 | EI T3NT EAGLE RCK-FLTN-SLVRD 5/20 INST M |  | EAGLE ROCK-FULTON-SILVERADO | 005/020 | ICS | F | 2020_(3) On high spread structure |  |  | Likely MAT error - delink to correct | TR3 |  | North Coast | WSIP | [6 empty] | '-122.760343 | 38.6653 | ETL.4392 | 41129323 | Marker (i.e. signs)-Steel | No Good/Out of Stdrd | Install |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 628 | Lakeville
118957082 | T3 EI EAGLE ROCK-FLTN-SLVRD 6/23 RMV NES |  | EAGLE ROCK-FULTON-SILVERADO | 006/023 | ICS | E | 2020_(4b) On structure in bucket 4 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.757907 | 38.6543 | ETL.4392 | 41129326 | Structure-Steel | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville
118957102 | T3 EI BRIDGEVILLE-GARBVLE 5/13 RMV PL BU | 44299809 | BRIDGEVILLE-GARBERVILLE | 005/013 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.761394 | 40.4211 | ETL.6220 | 40666716 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
118957142 | T2 DI FORT ROSS-GUALALA 35/6 RPR POLE |  | GUALALA-MONTE RIO | 035/006 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.301782 | 38.5932 | ETL.6980 | 40827357 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
118957182 | T2 DI FORT ROSS-GUALALAN 35/3 RPR POLE |  | GUALALA-MONTE RIO | 035/003 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.302714 | 38.5894 | ETL.6980 | 40648473 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
118957189 | T2 DI FORT ROSS-GUALALA 34/7 REPL POLE | 31501748 | GUALALA-MONTE RIO | 034/007 | 70Y | E | 2020_(2) High fire spread TD |  |  |  | TR2 | <90D | North Coast | WSIP | [6 empty] | '-123.295014 | 38.5839 | ETL.6980 | 40808290 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville
118957190 | T3 EI BRIDGEVILLE-GRBRVLL 5/8 RMV PL BUT | 31504607 | BRIDGEVILLE-GARBERVILLE | 005/008 | 93J | F | 2020_(3) On high spread structure |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.762225 | 40.4244 | ETL.6220 | 40862826 | Structure-Wood | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 630 | Eureka
118957235 | T2 DI CORTINA-MENDCNO #1 32/153 RPR FOND | 44238817 | CORTINA-MENDOCINO #1 | 032/153 | ICQ | F | 2020_(2) High fire spread TD |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.751365 | 39.0693 | ETL.1330 | 40659078 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville
118957394 | T2 DI FULTON-HOPLAND 30/11 RPR POLE | 44579280 | FULTON-HOPLAND | 030/011 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 | <90D | North Coast | WSIP | [6 empty] | '-123.030567 | 38.8553 | ETL.6890 | 40601400 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
118957442 | T2 DI CORTINA-MNDCNO#1 15/72 INST HRDT | 44238817 | CORTINA-MENDOCINO #1 | 015/072 | ICQ | E | 2020_(3) On high spread structure |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.469953 | 39.0228 | ETL.1330 | 40657040 | Hardware-Tower | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville
118957451 | T2 DI FULTON-HOPLAND 30/11 TIGHTN HRDW | 44579280 | FULTON-HOPLAND | 030/011 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 | <90D | North Coast | WSIP | [6 empty] | '-123.030567 | 38.8553 | ETL.6890 | 40601400 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
118957452 | T2 DI FULTON-HOPLAND 30/11 RMV PL BUTT | 44579280 | FULTON-HOPLAND | 030/011 | ICW | E | 2020_(4b) On structure in bucket 4 |  |  |  | TR2 | <90D | North Coast | WSIP | [6 empty] | '-123.030567 | 38.8553 | ETL.6890 | 40601400 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
118957455 | T2 DI FULTON-HOPLAND 30/11 INST NUMBR |  | FULTON-HOPLAND | 030/011 | ICW | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.030567 | 38.8553 | ETL.6890 | 40601400 | Marker (i.e. signs)-Wood | Missing | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
118958220 | T2 DI FRT RSS-GUALALA 31/11 RPL INSW | 31501747 | GUALALA-MONTE RIO | 031/011 | 93I | E | 2020_(2) High fire spread TD |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.26558 | 38.5556 | ETL.6980 | 40596034 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Lakeville
118959091 | T2 DI CORTINA-MNDCNO #1 34/165 RMV NEST | 44610540 | CORTINA-MENDOCINO #1 | 034/165 | ICS | E | 2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.775849 | 39.0916 | ETL.1330 | 40750579 | Structure-Steel | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville
118959097 | T2 DI CORTINA-MNDCNO #1 59/289 RPL INSS | 31518808 | CORTINA-MENDOCINO #1 | 059/289 | 93K | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.174529 | 39.2398 | ETL.1330 | 40860995 | Insulator-Steel | No Good/Out of Stdrd | Replace | srdy DCNL |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Lakeville
118959099 | T2 DI MENDOCINO-REDBUD 59/289 RPL INSS |  | MENDOCINO-REDBUD | 059/289 | 93K | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 | <90D | North Coast | WSIP | [6 empty] | '-123.175263 | 39.2397 | ETL.2410 | 40882695 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Lakeville
118959203 | T2 DI CORTINA-MNDCNO #1 59/289 RPR HRDT |  | CORTINA-MENDOCINO #1 | 059/289 | ICQ | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 | <90D | North Coast | WSIP | [6 empty] | '-123.174529 | 39.2398 | ETL.1330 | 40860995 | Hardware-Tower | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville
118959209 | T2 DI FORT ROSS-GUALALA 37/3 RPR POLE | 44589099 | GUALALA-MONTE RIO | 037/003 | ICW | E | 2020_(1a) PSPS |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.291245 | 38.6156 | ETL.6980 | 40667852 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
118959342 | T2 DI FORT ROSS-GUALALA 37/3 RPR GYWW | 44589099 | GUALALA-MONTE RIO | 037/003 | ICW | E | 2020_(1a) PSPS |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.291245 | 38.6156 | ETL.6980 | 40667852 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
118959417 | T3 MIDDLE FORK #1 1/024 REFRAME | 31471244 | MIDDLE FORK #1 | 001/024 | 93E | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.603124 | 39.0062 | ETL.8405 | 40824458 | Crossarm-Wood | No Good/Out of Stdrd | Replace | DOCC srdy | DOCC | Job has been constructed (documentation) | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Sacramento
118959828 | T2 DI CRTNA-MNDCNO#1 56/277 RPR STRT |  | CORTINA-MENDOCINO #1 | 056/277 | ICQ | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 | <90D | North Coast | WSIP | [6 empty] | '-123.12171 | 39.2311 | ETL.1330 | 40808541 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville
118959974 | DRUM-SPAULDING 0/9 DUP CNCL | 44310644 | DRUM-SPAULDING | 000/009 | ICW | F | 2020_(3) On high spread structure |  |  | CANCEL/CNCL |  |  | North Valley | WSIP | [6 empty] | '-120.760093 | 39.2553 | ETL.6770 | 40875888 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
118960040 | T2 DI CRTNA-MNDCNO#1 46/225 RPR FOND |  | CORTINA-MENDOCINO #1 | 046/225 | ICQ | F | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.949414 | 39.1853 | ETL.1330 | 40750591 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville
118960062 | DI SNTH LN-HLF MN BY ?11/14 RPL INSS |  | SNEATH LANE-HALF MOON BAY | ?011/014 | 93K | E | 2020_(4) TD tag on high spread line | [5 empty] | Central | WSIP | [6 empty] | '-122.429996 | 37.4693 | ETL.7212 | 40823354 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - 29
118960135 | T3 EI SNEATH LANE-HALF MN BAY ?5/0 REPL | 31501618 | SNEATH LANE-HALF MOON BAY | ?005/000 | 93E | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.463429 | 37.5509 | ETL.7212 | 40601801 | Anchor-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Bay |  |  | RCDT
118960202 | EI T3NT SNEATH LAN-ALF MN BY ?4/5 RMV DE | 44598227 | SNEATH LANE-HALF MOON BAY | ?004/005 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-122.467012 | 37.5509 | ETL.7212 | 40767323 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Bay
118960259 | EI T3NT SNEATH LN-HALF MN BY ?4/2 INST N |  | SNEATH LANE-HALF MOON BAY | ?004/002 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-122.473858 | 37.5509 | ETL.7212 | 44264949 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Bay |  |  | RCDT
118960394 | T3 EI EAGLE ROCK-FULTON-SLVRD 6/27 RMV N |  | EAGLE ROCK-FULTON-SILVERADO | 006/027 | ICS | E | 2020_(4b) On structure in bucket 4 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.758519 | 38.6423 | ETL.4392 | 41129330 | Structure-Steel | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville
118960668 | T3 DI WEST PNT-VLY SPRNGS 5/63A RPR GYWW | 44631077 | WEST POINT-VALLEY SPRINGS | 005/063A | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-120.62912 | 38.393 | ETL.8350 | 40768204 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor
118960724 | T2 DI CRTNA-MNDCNO#1 34/163 RPR FOND | 44238817 | CORTINA-MENDOCINO #1 | 034/163 | ICQ | F | 2020_(2) High fire spread TD |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.772383 | 39.0889 | ETL.1330 | 40659706 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville
118960726 | T3 DI SNTH LN-HLF MN BY ?6/9 RPR PL | 44621672 | SNEATH LANE-HALF MOON BAY | ?006/009 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.441814 | 37.5374 | ETL.7212 | 40874256 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Bay |  |  | Scarper Ridge
118960788 | T2 CARIBOU #2 4/5 RPL POLE | 31489363 | CARIBOU #2 | ;004/005 | 70Y | E | 2020_(2) High fire spread TD |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-120.94644 | 39.975 | ETL.6280 | 40751776 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain
118960793 | T3 DI SNTH LN-HF MN BY ?9/4 BOND GUY | 44621667 | SNEATH LANE-HALF MOON BAY | ?009/004 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.42395 | 37.503 | ETL.7212 | 40768020 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Bay |  | Y - 29
118960795 | T3NT DI EAGL RCK-FLTN-SLD :3/14 RPR FOND | 44326457 | EAGLE ROCK-FULTON-SILVERADO | :003/014 | ICQ | F | 2020_(2) High fire spread TD |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.764599 | 38.6908 | ETL.4392 | 41129317 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville
118960879 | T2 DI CRTNA-MNDCNO#1 33/162 INST HRDT | 44238817 | CORTINA-MENDOCINO #1 | 033/162 | ICQ | E | 2020_(3) On high spread structure |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.768955 | 39.0862 | ETL.1330 | 40689169 | Hardware-Tower | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville
118960992 | T2 DI CRTNA-MNDCNO#1 33/162 RPR FOND | 44238817 | CORTINA-MENDOCINO #1 | 033/162 | ICQ | F | 2020_(2) High fire spread TD |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.768955 | 39.0862 | ETL.1330 | 40689169 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville
118961065 | T2 DI FORT ROSS-GUALALAN 36/0 BOND GUY |  | GUALALA-MONTE RIO | 036/000 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.301436 | 38.5992 | ETL.6980 | 40606896 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
118961069 | T3 DI TGR CRK-VLY SPRNGS 2/22 RPR STRT |  | TIGER CREEK-VALLEY SPRINGS | 002/022 | ICQ | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-120.538898 | 38.4352 | ETL.5790 | 40651656 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Victor
118961073 | T3 EI BRIDGEVILLE-GARBERVILLE 6/0 RPL PO | 31501746 | BRIDGEVILLE-GARBERVILLE | 006/000 | 70Y | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.759736 | 40.4158 | ETL.6220 | 40614612 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka
118961074 | T3 EI BRIDGEVILLE-GARBERVLL 6/2 RMV PL B | 31504607 | BRIDGEVILLE-GARBERVILLE | 006/002 | 93J | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.759331 | 40.4146 | ETL.6220 | 40661824 | Structure-Wood | Idle | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 673 | Eureka
118961076 | T3 EI BRIDGEVILLE-GARBERVILLE 6/0 RMV VE | 44311404 | BRIDGEVILLE-GARBERVILLE | 006/000 | CHS | F | 2020_(3) On high spread structure |  |  |  | TR3 | SCHD | North Coast | WSIP | [6 empty] | '-123.759736 | 40.4158 | ETL.6220 | 40614612 | Road | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLR | Roads | Expense | 932 | Eureka
118961111 | T3 DI TGR CRK-VLY SPRNGS 2/22 INST HRDT |  | TIGER CREEK-VALLEY SPRINGS | 002/022 | ICQ | E | 2020_(3) On high spread structure |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-120.538898 | 38.4352 | ETL.5790 | 40651656 | Hardware-Tower | Missing | Install |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Victor
118961211 | T3 DI MI-WUK-CURTIS 22/05 RPL POLE | 31501637 | ETL.1073.POLE.WOOD | 022/005B | 70Y | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-120.261518 | 38.0128 | ETL.1073 | 40744856 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor
118961214 | DI CORTINA-MNDCN#1 4/25 RPL INSS | 31502267 | CORTINA-MENDOCINO #1 | 004/025 | 93K | E | 2020_(4) TD tag on high spread line | [5 empty] | North Valley | WSIP | [6 empty] | '-122.306158 | 39.111 | ETL.1330 | 40757308 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Sacramento
118961221 | T3 EI BRIDGEVILLE-GARBERVILLE 06/03 RPL | 31501746 | BRIDGEVILLE-GARBERVILLE | 006/003 | 70Y | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.758161 | 40.4138 | ETL.6220 | 40666732 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka
118961228 | T3 EI BRIDGEVILLE-GARBERVILLE 6/6 INST J | 31501770 | BRIDGEVILLE-GARBERVILLE | 006/006 | 93I | E | 2020_(2) High fire spread TD |  |  | Likely MAT error - delink to correct | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.754982 | 40.4117 | ETL.6220 | 40810915 | Jumper-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Eureka
118961263 | T3 EI BRIDGEVILLE-GARBERVLL 6/9 RMV PL B | 31504607 | BRIDGEVILLE-GARBERVILLE | 006/009 | 93J | F | 2020_(3) On high spread structure |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.752625 | 40.4102 | ETL.6220 | 40875285 | Structure-Wood | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 630 | Eureka
118961266 | T3 EI BRIDGEVILLE-GARBRVLL 6/10 RMV PL B | 31504607 | BRIDGEVILLE-GARBERVILLE | 006/010 | 93J | F | 2020_(3) On high spread structure |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.751232 | 40.4092 | ETL.6220 | 40614602 | Structure-Wood | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 630 | Eureka
118961268 | T3 EI BRIDGEVILLE-GARBRVLL 6/10 RPR STRW | 44299806 | BRIDGEVILLE-GARBERVILLE | 006/010 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.751232 | 40.4092 | ETL.6220 | 40614602 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
118961269 | T3 EI BRIDGEVILLE-GARBERVILL 6/11 INST I | 31501770 | BRIDGEVILLE-GARBERVILLE | 006/011 | 93I | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.7504177 | 40.4087 | ETL.6220 | 40611405 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Eureka
118961307 | T3 EI BRIDGEVILLE-GARBERVILL 7/0 RPL POL | 31501746 | BRIDGEVILLE-GARBERVILLE | 007/000 | 70Y | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.745763 | 40.4056 | ETL.6220 | 40591061 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka
118962320 | T3 DI SALMON CREEK TAP 0/7 RPR POLE |  | SALMON CREEK TAP | 000/007 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.121415 | 38.4694 | ETL.6981 | 40808321 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
118962529 | T3 EI BRIDGEVILLE-GARBERVLL 6/1 RMV PL B | 31504607 | BRIDGEVILLE-GARBERVILLE | 006/001 | 93J | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.75954 | 40.4153 | ETL.6220 | 40600515 | Structure-Wood | Idle | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 673 | Eureka
118963034 | DI SALMON CREEK TAP 1/9 RPR GYWW |  | SALMON CREEK TAP | 001/009 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  |  | <90D | North Coast | WSIP | [6 empty] | '-123.113506 | 38.4536 | ETL.6981 | 40876106 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
118963250 | T3 DI SNTH LN-HLF MN BY ?6/0 RPR POLE | 44621672 | SNEATH LANE-HALF MOON BAY | ?006/000 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.448776 | 37.5454 | ETL.7212 | 40601798 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Bay |  |  | Scarper Ridge
118963274 | T3NT DI GEYSERS#7-EGL RCK 1/10 RPR FOND | 44306736 | GEYSERS #7-EAGLE ROCK | 001/010 | ICQ | F | 2020_(2) High fire spread TD |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.811077 | 38.8232 | ETL.1680 | 40588203 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville
118963297 | IGNACIO-MARE ISLAND #1 13/94 RPL TOWER |  | IGNACIO-MARE ISLAND #1 | 013/094 | 70S | B | 2020_(0) A and B Tags | [5 empty] | North Coast | WSIP | [6 empty] | '-122.335038 | 38.1526 | ETL.1830 | 40752805 | Bay Water-Tower | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLQ | Pole Program | Capital | 426 | Lakeville
118963308 | T3 DI GEYSERS#3-EGL RCK 1/10 RPLC INSS | 31506602 | GEYSERS #3-EAGLE ROCK | 001/010 | 93K | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Coast | WSIP | [8 empty] | ETL.1660 | 44298581 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Lakeville
118963854 | T3NT TIGER CREEK-VALLEY 3/026 RPR FOND |  | TIGER CREEK-VALLEY SPRINGS | 003/026 | ICQ | F | 2020_(2) High fire spread TD |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-120.546224 | 38.4331 | ETL.5790 | 40818343 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - Prog 402
118964152 | T3 MI-WUK-CURTIS 22/7R RPL POLE | 31501639 | ETL.1073.POLE.WDPS | 022/007 | 70Y | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-120.26501 | 38.0094 | ETL.1073 | 44774783 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor
118964239 | T2 FULTON-HOPLAND 34/12 RPL POLE | 31501771 | FULTON-HOPLAND | 034/012 | 70Y | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 | <90D | North Coast | WSIP | [6 empty] | '-123.053797 | 38.9089 | ETL.6890 | 44203655 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville
118964377 | T2 DI FT ROSS-GUALALA 35/7 RPR GYWW |  | GUALALA-MONTE RIO | 035/007 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.301886 | 38.5945 | ETL.6980 | 40808292 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
118964381 | T2 RIO DELL JCT-BRIDGEVLE 38/8 RMV STEP | 44311233 | RIO DELL JCT-BRIDGEVILLE | 038/008 | ICS | E | 2020_(2) High fire spread TD |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.811502 | 40.4702 | ETL.7850 | 40876500 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Eureka
118964508 | T3 EI BRIDGEVLL-GRBRVLL 4/15 RMV PL BUTT | 44572647 | BRIDGEVILLE-GARBERVILLE | 004/015 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.764972 | 40.4334 | ETL.6220 | 40752644 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
118964509 | T3 EI BRIDGEVILL-GRBRVLL 4/15 INST INSW | 44300097 | BRIDGEVILLE-GARBERVILLE | 004/015 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.764972 | 40.4334 | ETL.6220 | 40752644 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
118964580 | T3 EI BRIDGEVILLE-GARBRVLL 4/17 RMV PL B | 31504607 | BRIDGEVILLE-GARBERVILLE | 004/017 | 93J | F | 2020_(3) On high spread structure |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.764562 | 40.432 | ETL.6220 | 40810324 | Structure-Wood | Debris/Nest/etc. | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 630 | Eureka
118964581 | T3 EI BRIDGEVILLE-GRBRVLL 4/17 INST INSW | 44300097 | BRIDGEVILLE-GARBERVILLE | 004/017 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.764562 | 40.432 | ETL.6220 | 40810324 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
118964587 | T3 DRUM-RIO OSO #2 6/64 INST INSS | 31471215 | DRUM-RIO OSO #2 | 006/064 | 93K | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.8572323 | 39.2121 | ETL.1430 | 44319605 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Sacramento
118964641 | T3 EAGLE ROCK-FLTN-SLVRD 4/24 INST DMPS |  | EAGLE ROCK-FULTON-SILVERADO | 004/024 | ICS | E | 2020_(4b) On structure in bucket 4 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.7975192 | 38.7748 | ETL.4392 | 40786528 | Damper-Steel | Missing | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville
118964671 | T2 DI CORTINA-MNDCN#1 35/167 RPR FOND |  | CORTINA-MENDOCINO #1 | 035/167 | ICQ | F | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.785776 | 39.0993 | ETL.1330 | 40808529 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville
118964674 | T2 DI CORTINA-MNDCN#1 36/175 RPLC HRDT |  | CORTINA-MENDOCINO #1 | 036/175 | ICQ | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 | <90D | North Coast | WSIP | [6 empty] | '-122.812717 | 39.1135 | ETL.1330 | 40750581 | Hardware-Tower | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville
118964882 | T3 DI KONOCTI-EGL RCK 5/5 RPR GYWW | 44610613 | KONOCTI-EAGLE ROCK | 005/005 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.785935 | 38.8888 | ETL.6861 | 40750936 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
118964887 | T3 DI MONTE RIO-FORT ROSS 20/0C RPL POLE | 31437439 | ETL.6979.POLE.WOOD | 020/000C | 70Y | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.094753 | 38.4844 | ETL.6979 | 40741868 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville
118965020 | T3 DI UKH-HPLN-CLVR 16/7 RPR GYWW | 44610690 | UKIAH-HOPLAND-CLOVERDALE | 016/007 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.034138 | 38.8801 | ETL.4050 | 40808567 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
118966234 | T2 DI TGR CREEK-ELCTR 9/72 RPR FOND |  | TIGER CREEK-ELECTRA | 009/072 | ICQ | F | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-120.635156 | 38.3877 | ETL.5780 | 40662450 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - 12
118966235 | T3 DI SNTH LN-HLF MN BAY 10/3 BOND GUY | 44621667 | SNEATH LANE-HALF MOON BAY | ?010/003 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.423577 | 37.4891 | ETL.7212 | 40656253 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Bay |  | Y - 29
118966441 | T3 DI EGL RCK-REDBUD 9/51 RPR FOND |  | EAGLE ROCK-REDBUD | :009/051 | ICQ | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.674745 | 38.8878 | ETL.1480 | 40585029 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville
118966444 | T2 DI VLY SPRNGS-MRTL#1 11/4 REPL POLE | 31502070 | VALLEY SPRINGS-MARTELL #1 | 011/004 | 70Y | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 | <90D | Central | WSIP | [6 empty] | '-120.785084 | 38.3504 | ETL.8240 | 40758493 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 24
118966446 | T3 DI EAGLE RCK-FLTN-SLVRD :4/16 RPR FND | 44326454 | EAGLE ROCK-FULTON-SILVERADO | :004/016 | ICQ | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.766287 | 38.6808 | ETL.4392 | 41129319 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville
118967135 | DI SNTH LN-HLF MN BY ?/14 RPR SPLW |  | SNEATH LANE-HALF MOON BAY | ?000/014 | ICW | E | 2020_(4) TD tag on high spread line | [5 empty] | Central | WSIP | [6 empty] | '-122.494372 | 37.5882 | ETL.7212 | 40758495 | Splice-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Bay |  | Y - 29
118967518 | T2 DI VLY SPRNGS-MRTL#1 6/5 RPR SPLW | 44631106 | VALLEY SPRINGS-MARTELL #1 | 006/005 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR2 | <90D | Central | WSIP | [6 empty] | '-120.756577 | 38.2786 | ETL.8240 | 40768196 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 24
118968201 | T3 DI SANTA FE GTHRML TP 0/2 RPR FOND |  | SANTA FE GEOTHERMAL TAP | 000/002 | ICQ | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.745884 | 38.7875 | ETL.4782 | 40681309 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville
118969167 | DI GEYSERS#3-CLOVERDALE 9/114 RPR SPLW | 44580896 | GEYSERS #3-CLOVERDALE | 009/114 | ICW | E | 2020_(2) High fire spread TD | [5 empty] | North Coast | WSIP | [6 empty] | '-122.976162 | 38.8007 | ETL.1650 | 44258747 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
118969168 | T3NT DI SANTA FE GEOTHERMAL 0/6 RPR FOND | 44310549 | SANTA FE GEOTHERMAL TAP | 000/006 | ICQ | F | 2020_(2) High fire spread TD |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.750111 | 38.7837 | ETL.4782 | 40809008 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville
118971594 | T3 DI MNDOCNO-WLLITS 7/13 BOND GUY | 44610679 | MENDOCINO-WILLITS | 007/013 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.294351 | 39.3147 | ETL.7540 | 41113148 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
118971739 | T2 EI MONTA VISTA-BURNS 4/038 RPR POLE |  | MONTA VISTA-BURNS | 004/038 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR2 | <90D | South | WSIP | [6 empty] | '-122.111076 | 37.2734 | ETL.7590 | 40581859 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing
118971836 | T3 DI KONOCTI-EAGLE ROCK 7/006 REPL GYPL | 31502700 | KONOCTI-EAGLE ROCK | 007/006 | 70Y | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.765993 | 38.9101 | ETL.6861 | 40809250 | Guy Pole-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville
118971895 | T2 DI VLY SPRNGS-MRTL#1 12/9 REPL POLE | 31502070 | VALLEY SPRINGS-MARTELL #1 | 012/009 | 70Y | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 | <90D | Central | WSIP | [6 empty] | '-120.794515 | 38.3661 | ETL.8240 | 40874927 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 24
118971993 | T3NT DI SANTA FE GTHRML TAP 0/8 RPR FOND | 44310549 | SANTA FE GEOTHERMAL TAP | 000/008 | ICQ | F | 2020_(2) High fire spread TD |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.751249 | 38.78 | ETL.4782 | 40870523 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville
118971994 | DI KONOCTI-EAGLE ROCK 0/1 INST MRKW | 44610613 | KONOCTI-EAGLE ROCK | 001/000 | ICW | F | 2020_(4b) On structure in bucket 4 | [5 empty] | North Coast | WSIP | [6 empty] | '-122.795393 | 38.8358 | ETL.6861 | 44679459 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
118971995 | T3NT DI EGL RCK-FLTN-SLVR 1/7 PNT STRS | 43730698 | EAGLE ROCK-FULTON-SILVERADO | :001/007 | ICS | F | 2020_(1a) PSPS |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.760246 | 38.7174 | ETL.4392 | 41129310 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville
118971999 | DI SAN RAMON-MORAGA 0/7 RPR FOND |  | SAN RAMON-MORAGA | 000/007 | ICQ | E | 2020_(4) TD tag on high spread line |  |  |  |  | <90D | Central | WSIP | [6 empty] | '-121.950425 | 37.7378 | ETL.5660 | 40664048 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 10
118972150 | T2 DI FORT ROSS-GUALALA 52/10 RPR SPLW |  | GUALALA-MONTE RIO | 052/010 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.450963 | 38.7387 | ETL.6980 | 40616647 | Splice-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
118972217 | T3 EI GEYSERS #12-FULTON 017/071 REPL IN | 31505663 | GEYSERS #12-FULTON | 017/071 | 93K | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.74122 | 38.6203 | ETL.4750 | 40620228 | Insulator-Steel | No Good/Out of Stdrd | Replace | srdy DCNL |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Lakeville
118972247 | T2 DI CRTINA-MNDCINO#1 59/292 RPR FOND |  | CORTINA-MENDOCINO #1 | 059/292 | ICQ | F | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.178026 | 39.2409 | ETL.1330 | 40657103 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville
118975651 | T3 DI MENDOCINO-WILLITS 9/5L RPR POLE | 44610681 | MENDOCINO-WILLITS-FORT BRAGG | 009/005 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Coast | WSIP | [8 empty] | ETL.7550 | 44211126 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
118975739 | T2 DI FORT ROSS-GUALALA 47/03 BOND GUY |  | GUALALA-MONTE RIO | 047/003 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.364316 | 38.7171 | ETL.6980 | 40648489 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
118975813 | T2 DI CTRA CSTA-MRGA #1 26/121 RPL HRDT |  | CONTRA COSTA-MORAGA #1 | 026/121 | ICQ | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 | <90D | Central | WSIP | [6 empty] | '-122.149228 | 37.8574 | ETL.5452 | 40746203 | Hardware-Tower | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog 404
118975864 | T2 DI CORTINA-MNDOCINO#1 25/119 INS HRDT |  | CORTINA-MENDOCINO #1 | 025/119 | ICQ | E | 2020_(4b) On structure in bucket 4 |  |  |  | TR2 | <90D | North Coast | WSIP | [6 empty] | '-122.64441 | 39.0272 | ETL.1330 | 40870083 | Hardware-Tower | Missing | Install |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville
118975865 | T2 DI CORTINA-MNDOCINO#1 25/119 RPR FOND |  | CORTINA-MENDOCINO #1 | 025/119 | ICQ | F | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.64441 | 39.0272 | ETL.1330 | 40870083 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville
118975957 | T2 DI CORTINA-MENDO #1 33/158 RPR FOND | 44238817 | CORTINA-MENDOCINO #1 | 033/158 | ICQ | F | 2020_(2) High fire spread TD |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.760214 | 39.0794 | ETL.1330 | 40861155 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville
118975983 | T2 DI CRTNA-MDCNO #1-TWR 39/191 RPR FOND |  | CORTINA-MENDOCINO #1 | 039/191 | ICQ | F | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.862113 | 39.1374 | ETL.1330 | 40593956 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville
118975986 | T2 DI FORT ROSS-GUALALA 36/03 REPR GYWW |  | GUALALA-MONTE RIO | 036/003 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.297975 | 38.6031 | ETL.6980 | 40661457 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
118976411 | T3 DI EAGLE ROCK-REDBUD 8/47 RPR FOND | 44637023 | EAGLE ROCK-REDBUD | :008/047 | ICQ | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.687963 | 38.8866 | ETL.1480 | 40812433 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville
118976421 | DI GATES MSTANG SW STA #1 5/24 RPR FOND | 44321035 | SPARE T-LINE RECORD | 005/024 | ICQ | F | 2020_(1b) Lines with special commitments | [5 empty] | South | WSIP | [6 empty] | '-120.040001 | 36.1733 | ETL.2604 | 40761924 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 7
118976527 | T3NT DI MISSO FLAT-GH#1 19/159 RPR FOND | 44320717 | MISSOURI FLAT-GOLD HILL #1 | 019/159 | ICQ | F | 2020_(4) TD tag on high spread line |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.895974 | 38.6638 | ETL.2660 | 40861989 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento
118976605 | DI GTS-MSTNG SW STA #1 5/25 REPR FOND | 44321035 | SPARE T-LINE RECORD | 005/025 | ICQ | F | 2020_(1b) Lines with special commitments | [5 empty] | South | WSIP | [6 empty] | '-120.035996 | 36.1753 | ETL.2604 | 40752363 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 9
118976831 | T3 EI EAGLE ROCK-FLTN-SLVRD 19/83 RPR FO | 44326454 | EAGLE ROCK-FULTON-SILVERADO | 019/083 | ICQ | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.616154 | 38.5119 | ETL.4392 | 41129385 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville
118976832 | EI T3NT EAGLE RCK-FLTN-SLVRD 19/81 RPR F | 44326457 | EAGLE ROCK-FULTON-SILVERADO | 019/081 | ICQ | F | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.62029 | 38.5149 | ETL.4392 | 41129383 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville
118977248 | DI MONTE RIO-FORT ROSS 23/2C BOND GUY |  | ETL.6979.POLE.WDPS | 023/002 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  |  | <90D | North Coast | WSIP | [8 empty] | ETL.6979 | 44312236 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
118977358 | T3 EI BRIDGEVILLE-GARBERVLE 03/12 INST I | 31502608 | BRIDGEVILLE-GARBERVILLE | 003/012 | 93I | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.779721 | 40.4427 | ETL.6220 | 40698471 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Eureka
118977359 | EI T3NT BRIDGEVILLE-GARBERVLL 3/12 RMV B | 44299809 | BRIDGEVILLE-GARBERVILLE | 003/012 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-123.779721 | 40.4427 | ETL.6220 | 40698471 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
118977360 | EI T3NT BRIDGEVILLE-GARBERVIL 3/11 RMV B | 44299809 | BRIDGEVILLE-GARBERVILLE | 003/011 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-123.780372 | 40.4431 | ETL.6220 | 40600517 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
118977369 | T3 EI BRIDGEVILLE-GARBERVLE 03/07 INST I | 31502608 | BRIDGEVILLE-GARBERVILLE | 003/007 | 93I | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.784318 | 40.4455 | ETL.6220 | 40824514 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Eureka
118977370 | T3 EI BRIDGEVILLE-GARBERVLE 03/07 RPR PO | 44299806 | BRIDGEVILLE-GARBERVILLE | 003/007 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.784318 | 40.4455 | ETL.6220 | 40824514 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
118977378 | T3 EI BRIDGEVILLE-GARBERVLE 3/4 INST INS | 31502608 | BRIDGEVILLE-GARBERVILLE | 003/004 | 93I | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.787035 | 40.4471 | ETL.6220 | 40769398 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Eureka
118977379 | T3 EI BRIDGEVILLE-GARBERVLE 03/04 RPR CO | 44300097 | BRIDGEVILLE-GARBERVILLE | 003/004 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.787035 | 40.4471 | ETL.6220 | 40769398 | Conductor-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
118977392 | T3 EI BRIDGEVILLE-GARBERVLE 03/03 INST I | 31502608 | BRIDGEVILLE-GARBERVILLE | 003/003 | 93I | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.788371 | 40.4478 | ETL.6220 | 40666741 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Eureka
118977397 | EI T3NT BRIDGEVILLE-GARBERVLL 3/13 RMV B | 44299809 | BRIDGEVILLE-GARBERVILLE | 003/013 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-123.778624 | 40.4423 | ETL.6220 | 40650748 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
118977399 | EI T3NT BRIDGEVILLE-GARBERVIL 3/14 RMV B | 44299809 | BRIDGEVILLE-GARBERVILLE | 003/014 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-123.777473 | 40.442 | ETL.6220 | 40769396 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
118977410 | T3 EI BRIDGEVILLE-GARBERVLE 03/14 INST I | 31502608 | BRIDGEVILLE-GARBERVILLE | 003/014 | 93I | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.777473 | 40.442 | ETL.6220 | 40769396 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Eureka
118977412 | T3 EI BRIDGEVILLE-GARBERVLE 03/15 INST I | 31502608 | BRIDGEVILLE-GARBERVILLE | 003/015 | 93I | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.775959 | 40.4415 | ETL.6220 | 40752640 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Eureka
118977416 | EI T3NT BRIDGEVILLE-GARBERVIL 4/1 RMV BU | 44299809 | BRIDGEVILLE-GARBERVILLE | 004/001 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-123.773857 | 40.4409 | ETL.6220 | 40600519 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
118977426 | EI T3NT BRIDGEVILLE-GARBERVIL 4/4 RMV BU | 44299809 | BRIDGEVILLE-GARBERVILLE | 004/004 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-123.772392 | 40.4399 | ETL.6220 | 40769394 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
118977436 | EI T3NT BRIDGEVILLE-GARBERVIL 4/9 RMV BU | 44299809 | BRIDGEVILLE-GARBERVILLE | 004/009 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-123.769526 | 40.4376 | ETL.6220 | 40862507 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
118977705 | T2 TRINITY-MAPLE CREEK 36/4 REPL POLE | 31471998 | TRINITY-MAPLE CREEK | 036/004 | 70Y | E | 2020_(2) High fire spread TD |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.564376 | 40.7207 | ETL.8170 | 40771342 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka
118977707 | T2 TRINITY-MAPLE CREEK 34/002 REPL POLE | 31471998 | TRINITY-MAPLE CREEK | 034/002 | 70Y | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.528055 | 40.7115 | ETL.8170 | 40701884 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka
118978719 | T2 DI VLY SPRNGS-MRTLL #1 12/7 RPR SPLW |  | VALLEY SPRINGS-MARTELL #1 | 012/007 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 | <90D | Central | WSIP | [6 empty] | '-120.793805 | 38.3643 | ETL.8240 | 40805044 | Splice-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 24
118978959 | T2 UKIAH-HOPLAND-CLOVERDL 10/92 RPL POLE | 31490866 | UKIAH-HOPLAND-CLOVERDALE | 010/092 | 70Y | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.125452 | 39.0458 | ETL.4050 | 40755571 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville
118979053 | DI STNSLS-MLNS SS-MTC #1 25/163 RPR STRT |  | STANISLAUS-MELONES SS-MANTECA #1+ | 025/163 | ICQ | E | 2020_(4) TD tag on high spread line |  |  |  |  | <90D | Central | WSIP | [6 empty] | '-120.756719 | 37.927 | ETL.3830 | 40579579 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - 22
118979300 | T3 EI BRIDGEVILLE-GARBERVIL 1/5 JUMP INS | 31502608 | BRIDGEVILLE-GARBERVILLE | 001/005 | 93I | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.801234 | 40.4661 | ETL.6220 | 40752634 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Eureka
118979416 | EI T3NT BRIDGEVILLE-GARBERVIL 1/10 RMV B | 44299809 | BRIDGEVILLE-GARBERVILLE | 001/010 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-123.801697 | 40.4622 | ETL.6220 | 40591052 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
118979419 | T3 EI BRIDGEVILLE-GARBERVIL 1/10 RPR GYW | 44300097 | BRIDGEVILLE-GARBERVILLE | 001/010 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.801697 | 40.4622 | ETL.6220 | 40591052 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
118979606 | T3 EI BRIDGEVILLE-GARBERVIL 2/2 JUMP SUP | 31502608 | BRIDGEVILLE-GARBERVILLE | 002/002 | 93I | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.800513 | 40.4576 | ETL.6220 | 40661797 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Eureka
118979607 | EI T3NT BRIDGEVILLE-GARBERVIL 2/2 RMV BU | 44299809 | BRIDGEVILLE-GARBERVILLE | 002/002 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-123.800513 | 40.4576 | ETL.6220 | 40661797 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
118979699 | T3 EI BRIDGEVILLE-GARBERVIL 2/4 JMPR INS | 31502608 | BRIDGEVILLE-GARBERVILLE | 002/004 | 93I | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.799065 | 40.4563 | ETL.6220 | 40752604 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Eureka
118979762 | T3 EI BRIDGEVILLE-GARBERVIL 2/7 JMPR INS | 31504243 | BRIDGEVILLE-GARBERVILLE | 002/007 | 93I | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.794955 | 40.4526 | ETL.6220 | 40810322 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Eureka
118979763 | EI T3NT BRIDGEVILLE-GARBERVIL 2/7 RMV BU | 44299809 | BRIDGEVILLE-GARBERVILLE | 002/007 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-123.794955 | 40.4526 | ETL.6220 | 40810322 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
118979788 | T3 EI BRIDGEVILLE-GARBERVILLE 2/8 RPR PO | 44321287 | BRIDGEVILLE-GARBERVILLE | 002/008 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.794134 | 40.4518 | ETL.6220 | 44650667 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
118979835 | EI T3NT BRIDGEVILLE-GARBERVIL 2/9 RMV BU | 44299809 | BRIDGEVILLE-GARBERVILLE | 002/009 | ICW | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-123.79362 | 40.4513 | ETL.6220 | 40875306 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
118979913 | T3 EI BRIDGEVILLE-GARBERVIL 2/11 JMPR IN | 31504243 | BRIDGEVILLE-GARBERVILLE | 002/011 | 93I | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.792487 | 40.4503 | ETL.6220 | 40586717 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Eureka
118979983 | EI T3NT BRIDGEVILLE-GARBERVIL 3/0 RMV BU | 44299809 | BRIDGEVILLE-GARBERVILLE | 003/000 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-123.790644 | 40.4492 | ETL.6220 | 40614661 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
118980508 | T2 DI FORT ROSS-GUALALA 38/6 BOND GUY |  | GUALALA-MONTE RIO | 038/006 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.309053 | 38.6265 | ETL.6980 | 40821470 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
118980617 | T3 DI KONOCTI-EGL ROCK 4/14 RPR STRW | 44610613 | KONOCTI-EAGLE ROCK | 004/014 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.784463 | 38.8832 | ETL.6861 | 40750917 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
118980717 | DI MORAGA-SAN LEANDRO #1 9/66 REPR FOND |  | MORAGA-SAN LEANDRO #1 | 009/066 | ICQ | F | 2020_(4) TD tag on high spread line | [5 empty] | Central | WSIP | [6 empty] | '-122.133961 | 37.7252 | ETL.2770 | 40804657 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog 402
118980719 | DI GATES-MUSTANG SW STA #1 7/33 RPR FOND | 44321035 | SPARE T-LINE RECORD | 007/033 | ICQ | F | 2020_(1b) Lines with special commitments | [5 empty] | South | WSIP | [6 empty] | '-120.004224 | 36.1906 | ETL.2604 | 40650482 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 9
118981593 | T2 DI CRTINA-MNDOCINO #1 34/166 INS HRDT | 44238817 | CORTINA-MENDOCINO #1 | 034/166 | ICQ | E | 2020_(3) On high spread structure |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.78187 | 39.0962 | ETL.1330 | 40808931 | Hardware-Tower | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville
118981597 | T2 DI CRTINA-MNDOCINO #1 34/166 RPR STRS | 44610540 | CORTINA-MENDOCINO #1 | 034/166 | ICS | E | 2020_(2) High fire spread TD |  |  |  | TR2 | <90D | North Coast | WSIP | [6 empty] | '-122.78187 | 39.0962 | ETL.1330 | 40808931 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville
118981599 | T2 DI CRTINA-MNDOCINO #1 34/166 RPR SPLS | 44610540 | MENDOCINO-REDBUD | 034/166 | ICS | E | 2020_(2) High fire spread TD |  |  |  | TR2 | <90D | North Coast | WSIP | [6 empty] | '-122.78187 | 39.0962 | ETL.2410 | 40835508 | Splice-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville
118981678 | T3 EI FULTON-PUEBLO 030/143 RMV HRDT | 44310479 | FULTON-PUEBLO | 030/143 | ICQ | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.52288 | 38.4918 | ETL.1600 | 40650803 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville
118981679 | T3 EI FULTON-PUEBLO 029/141 RMV HRDT |  | FULTON-PUEBLO | 029/141 | ICQ | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.516951 | 38.4931 | ETL.1600 | 40586782 | Hardware-Tower | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville
118981720 | T2 DI CRTINA-MNDOCINO #1 34/166 RPR FOND | 44238817 | CORTINA-MENDOCINO #1 | 034/166 | ICQ | F | 2020_(2) High fire spread TD |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.78187 | 39.0962 | ETL.1330 | 40808931 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville
118981723 | T3 DI PITTSBURG-SAN MATEO 24/96 INS MRKS |  | PITTSBURG-SAN MATEO | 024/096 | ICS | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-121.970879 | 37.7238 | ETL.5463 | 40581163 | Marker (i.e. signs)-Steel | Missing | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - 10
118981741 | T3 EI FULTON-PUEBLO 030/144 RMV HRDT | 44310479 | FULTON-PUEBLO | 030/144 | ICQ | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.526891 | 38.4906 | ETL.1600 | 40746839 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville
118981807 | T3NT DI PTTSBRG-SAN MATO 11/146 RPR FOND |  | PITTSBURG-SAN RAMON | 011/046 | ICQ | F | 2020_(4) TD tag on high spread line |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-121.880363 | 37.8816 | ETL.5490 | 40805062 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog 402
118981998 | EI GATES-MUSTANG SW STA #2 4/22B RPR FON | 44331648 | ETL.2605.TOWR | 004/022B | ICQ | E | 2020_(1b) Lines with special commitments | [5 empty] | South | WSIP | [6 empty] | '-120.047735 | 36.1704 | ETL.2605 | 40740272 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno
118982218 | T2 TRINITY-MAPLE CREEK 12/005 RPL POLE | 31471998 | TRINITY-MAPLE CREEK | 012/005 | 70Y | E | 2020_(2) High fire spread TD |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.139367 | 40.7654 | ETL.8170 | 40752252 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka
118982309 | T2 DI PHILO JCT-ELK 31/5 RPR GYWW | 44610684 | PHILO JCT-ELK | 031/005 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.619461 | 39.1263 | ETL.7780 | 40762851 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
118983818 | T3 EI MAPLE CREEK-HOOPA 11/005 RMV PLE B | 44301081 | MAPLE CREEK-HOOPA | 011/005 | ICW | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-123.770848 | 40.9011 | ETL.7490 | 40770458 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
118983847 | DI GATES-GREGG 3/18 INST HRDT | 44321035 | SPARE T-LINE RECORD | 003/018 | ICQ | E | 2020_(1b) Lines with special commitments | [5 empty] | South | WSIP | [6 empty] | '-120.064615 | 36.1641 | ETL.2604 | 40858294 | Hardware-Tower | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 7
118983896 | T3 EI MAPLE CREEK-HPA 11/3 INS JMPR | 44178090 | MAPLE CREEK-HOOPA | 011/003 | ICS | E | 2020_(4) TD tag on high spread line |  |  | Likely MAT error - delink to correct | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.771222 | 40.9001 | ETL.7490 | 40668473 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
118983915 | T2 EI DIVIDE-VNDNBRG #1 003/024 RPR GYWW |  | DIVIDE-VANDENBERG #1 | 003/024 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-120.487918 | 34.7917 | ETL.8620 | 40667198 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach
118984169 | T3 DI MORRO BAY-TEMPLETON 8/37 RPR OPGW |  | MORRO BAY-TEMPLETON | 008/037 | ICS | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | South | WSIP | [6 empty] | '-120.749602 | 35.4613 | ETL.5933 | 40810829 | Shield Wire / OPGW-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Pismo Beach |  | Y - 10
118984297 | T2 WEST POINT-VALLEY SPRNG 6/076 RPL POL | 31504956 | WEST POINT-VALLEY SPRINGS | 006/076 | 70Y | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-120.639628 | 38.3753 | ETL.8350 | 40876055 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor
118985369 | T2 WEST POINT-VALLEY SPRINGS 8/97 RPL PL | 31504957 | WEST POINT-VALLEY SPRINGS | 008/097 | 70Y | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-120.654212 | 38.3556 | ETL.8350 | 40825790 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor
118988217 | T3 DI GYSRS#3-CLVERDL 9/106C RPR GYWW | 44580896 | GEYSERS #3-CLOVERDALE | 009/106C | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.965766 | 38.7962 | ETL.1650 | 44298419 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
118988322 | T2 DRUM-SPAULDING 8/219 RPL POLE | 31503704 | DRUM-SPAULDING | 008/219 | 70Y | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-120.649263 | 39.3178 | ETL.6770 | 40616092 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento
118988981 | T3 DI MENDONCINO-WILLETS 7/9 RPR GYWW | 44610681 | MENDOCINO-WILLITS-FORT BRAGG | 007/009 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.29421 | 39.3148 | ETL.7550 | 40875210 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
118989050 | T3 DI SOBRANTE-""R"" #1-TWR 2/16 RPL INSS | 31503751 | SOBRANTE-R #1 | 002/016 | 93K | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.249227 | 37.9104 | ETL.3770 | 40830932 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  |  | Tilden RP
118989320 | T3NT DI EAGLE ROCK-REDBUD 7/41 RPR FOND |  | EAGLE ROCK-REDBUD | :007/041 | ICQ | F | 2020_(2) High fire spread TD |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.710229 | 38.8816 | ETL.1480 | 40585028 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville
118990112 | DI HUMBOLDT #1 8/6 REPL INSS | 31503644 | HUMBOLDT #1 | 008/006 | 93K | E | 2020_(2) High fire spread TD | [5 empty] | North Coast | WSIP | [6 empty] | '-124.055902 | 40.8762 | ETL.7113 | 40809330 | Insulator-Steel | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Eureka
118990485 | T3 DI PTTBRGH-SANMATEO 11/46 REPL INSS | 31504797 | PITTSBURG-SAN MATEO | 011/046 | 93K | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-121.880119 | 37.8815 | ETL.5463 | 40618853 | Insulator-Steel | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - 10
118990592 | NT DI MORRO BAY-TEMPLETON 0/5 RPNT STRS | 44586162 | MORRO BAY-TEMPLETON | 000/005 | ICS | F | 2020_(4b) On structure in bucket 4 | [5 empty] | South | WSIP | [6 empty] | '-120.842897 | 35.3763 | ETL.5933 | 40753139 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Pismo Beach
118991021 | T3 EI MAPLE CREEK-HOOPA 9/3 INST JUMPR I | 31504242 | MAPLE CREEK-HOOPA | 009/003 | 93I | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.788591 | 40.8747 | ETL.7490 | 40650870 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Eureka
118991419 | T3 DI SOBRANTE R #1 02/14 RPL SPLS | 44614167 | SOBRANTE-R #1 | 002/014 | ICS | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.24587 | 37.9095 | ETL.3770 | 40746169 | Splice-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  |  | EBMUD
118991435 | T2 DI FORT ROSS-GUALALA 47/3 RPR POLE |  | GUALALA-MONTE RIO | 047/003 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.364316 | 38.7171 | ETL.6980 | 40648489 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
118991488 | DI GATES-MSTNG SW STA#1 3/38 RPR FOND | 44321035 | SPARE T-LINE RECORD | 008/038 | ICQ | F | 2020_(1b) Lines with special commitments | [5 empty] | South | WSIP | [6 empty] | '-119.984413 | 36.2001 | ETL.2604 | 40862579 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 9
118992043 | T3 DI MORAGA-OAKLAND #1 2/15 RPR SPLS | 44621662 | MORAGA-OAKLAND #1 | 002/015 | ICS | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.195719 | 37.8334 | ETL.2720 | 40745884 | Splice-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - 8
118992051 | T3NT DI TGR CRK-VLLY SPRGS 2/16 RPR FOND |  | TIGER CREEK-VALLEY SPRINGS | 002/016 | ICQ | F | 2020_(2) High fire spread TD |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-120.525765 | 38.44 | ETL.5790 | 40811205 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Victor
118993036 | T3 EI COLGATE-ALLEGHANY 15/400 INST SPLT | 44339048 | COLGATE-ALLEGHANY | 015/400 | ICW | E | 2020_(3) On high spread structure |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.995281 | 39.4428 | ETL.6470 | 40590441 | Hardware-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
118993080 | T3 DI EAGLE ROCK-CORTINA 15/71 RPL INSS | 31505513 | EAGLE ROCK-CORTINA | 015/071 | 93K | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Coast | WSIP | [8 empty] | ETL.1470 | 40609219 | Insulator-Steel | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Lakeville
118993094 | T2 SPAULDING-SUMMIT 10/350 RPL POLE | 31495368 | SPAULDING-SUMMIT | 010/350 | 70Y | E | 2020_(1b) Lines with special commitments |  |  |  | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.473431 | 39.3179 | ETL.8060 | 40668705 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento
118993324 | T3 DI MNT VST-JFFERSON #2 16/69 RPL INSS | 31503450 | MONTA VISTA-JEFFERSON #2 | 016/069 | 93K | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.300736 | 37.4217 | ETL.5230 | 40884747 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - 3
118993325 | T3 DI CORTINA-MENDOCNO #1 17/83 RPL INSS | 44610540 | CORTINA-MENDOCINO #1 | 017/083 | ICS | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.505736 | 39.0087 | ETL.1330 | 40648755 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville
118993326 | T3 DI MUR FLT-GLD HLL #1 17/151 RPL INSS | 31502729 | MISSOURI FLAT-GOLD HILL #1 | 017/151 | 93K | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.867462 | 38.6708 | ETL.2660 | 40913117 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Sacramento
118993362 | T3 DI EAGLE ROCK-CORTINA 20/94 RPL INSS | 31505513 | EAGLE ROCK-CORTINA | 020/094 | 93K | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Coast | WSIP | [8 empty] | ETL.1470 | 40792694 | Insulator-Steel | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Lakeville
118993541 | T3NT DI SBRNT-GZLY-CLMT #2 7/48 RPR FOND |  | SOBRANTE-GRIZLY-CLARMNT #2+ | 007/048 | ICQ | F | 2020_(4) TD tag on high spread line |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-122.221725 | 37.8476 | ETL.3750 | 40746130 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 10
118993602 | T3NT DI MONTE RIO-FULTON 14/7 INST MRKW |  | MONTE RIO-FULTON | 014/007 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-123.009298 | 38.4779 | ETL.7630 | 40825469 | Marker (i.e. signs)-Wood | Missing | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
118993630 | DI GATES-MUSTANG SW STA #1 1/7 BENT STL | 44331647 | SPARE T-LINE RECORD | 001/007 | ICQ | E | 2020_(1b) Lines with special commitments | [5 empty] | South | WSIP | [6 empty] | '-120.108956 | 36.1479 | ETL.2604 | 40805347 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 9
118993749 | T3 DI MORAGA-CLAREMT #1 3/24 RPLC CONCTR | 44621661 | MORAGA-CLAREMONT #1 | 003/024 | ICM | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.209114 | 37.8509 | ETL.2700 | 40745853 | Connector | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 534 | Bay
118993773 | T3 DI CRTNA-MNDCINO#1 17/83 INST HRDT | 44238817 | CORTINA-MENDOCINO #1 | 017/083 | ICQ | E | 2020_(3) On high spread structure |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.505736 | 39.0087 | ETL.1330 | 40648755 | Hardware-Tower | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville
118993836 | T3NT DI PARKWAY-MORAGA 20/113 RPR FOND | 44298735 | PARKWAY-MORAGA | 020/113 | ICQ | F | 2020_(2) High fire spread TD |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-122.19896 | 37.8762 | ETL.5930 | 40868391 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  | EBMUD
118993843 | T2 DI SAN LS OBSPO-CYCS 11/105 RPLC CRSW | 31505054 | SAN LUIS OBISPO-CAYUCOS | 011/105 | 93E | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-120.752372 | 35.3149 | ETL.9090 | 40589825 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Pismo Beach |  | Y - 12
118995077 | T3 DI PITTSBURGûSAN MATEO 10/40 RPR FOND | 44623139 | PITTSBURG-SAN MATEO | 010/040 | ICQ | F | 2020_(2) High fire spread TD |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-121.880704 | 37.8997 | ETL.5463 | 40746309 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  | MDSP
118995441 | DI GATES-MUSTANG SW STA #1 5/23 RPR FOND | 44321035 | SPARE T-LINE RECORD | 005/023 | ICQ | F | 2020_(1b) Lines with special commitments | [5 empty] | South | WSIP | [6 empty] | '-120.043543 | 36.1718 | ETL.2604 | 40644918 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 7
118995444 | DI GATES-MUSTANG SW STA #1 5/23 BENT STL | 44321035 | SPARE T-LINE RECORD | 005/023 | ICQ | E | 2020_(1b) Lines with special commitments | [5 empty] | South | WSIP | [6 empty] | '-120.043543 | 36.1718 | ETL.2604 | 40644918 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 7
118995447 | T3 DI SBRNTûGRZLYûCLRMT#1 3/34 RPR SPLS | 44621665 | SOBRNTE-GRIZZLY-CLARMNT #1+ | 003/034 | ICS | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.174892 | 37.862 | ETL.3740 | 40861013 | Splice-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay
118995448 | DI GATES-MUSTAND SW STA#1 3/17 RPR FOND | 44341601 | SPARE T-LINE RECORD | 003/017 | ICQ | E | 2020_(1b) Lines with special commitments | [5 empty] | South | WSIP | [6 empty] | '-120.068815 | 36.1626 | ETL.2604 | 40805349 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 11
118996319 | T3 DI SRMNT-GRZLY-CLRMT#1 3/35 RPR STRS | 44624393 | SOBRNTE-GRIZZLY-CLARMNT #1+ | 003/035 | ICQ | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.173894 | 37.8601 | ETL.3740 | 40857621 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay
118997052 | T3 DI EL DRD-MISSOU FLT #1 2/22 RPR STRS | 44332237 | ELDORADO-MISSOURI FLAT #1 | 002/022 | ICS | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.65948 | 38.7681 | ETL.1530 | 44722642 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento
118997476 | LOS BANOS-MIDWAY #2 125/517 RMV DEBRIS | 44637107 | LOS BANOS-MIDWAY #2 | 125/517 | ICS | E | 2020_(1b) Lines with special commitments | Director approved |  | Tower guy |  | WECC | South | WSIP | [6 empty] | '-119.639999 | 35.6321 | ETL.6010 | 40811544 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Midway |  | Y - 26
118997954 | T2 DI SAN LS OBSPO-CYCS 14/136C RPR STRW |  | SAN LUIS OBISPO-CAYUCOS | 014/136 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-120.802772 | 35.3511 | ETL.9090 | 44565321 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - 12
118999616 | T3 DI MORAGA-OAKLAND #3 2/17 RPLC INSS | 31504796 | MORAGA-OAKLAND #3 | 002/017 | 93K | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.19539 | 37.8331 | ETL.2740 | 40828528 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - 11
118999617 | T3 DI MORAGA-OAKLAND #4 2/17 RPLC INSS | 31508629 | MORAGA-OAKLAND #4 | 002/017 | 93K | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.19539 | 37.8331 | ETL.2750 | 40828530 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - 2
119000339 | T3 DI MORAGA-OAKLAND #1 2/14 RPLC INSS | 31504785 | MORAGA-OAKLAND #1 | 002/014 | 93K | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.194 | 37.8345 | ETL.2720 | 40775596 | Insulator-Steel | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - 8
119000428 | T3 DI DRUM-RIO OSO#2 3/31 REPL INSS | 31502784 | DRUM-RIO OSO #2 | 003/031 | 93K | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.817735 | 39.2434 | ETL.1430 | 40594983 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Sacramento
119000451 | T3 DI MORAGA-OAKLAND #2 2/14 RPLC INSS | 31461003 | MORAGA-OAKLAND #2 | 002/014 | 93K | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.194 | 37.8345 | ETL.2730 | 40775598 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - 2
119001057 | T3 DI ATASCADERO-CAYUCOS 3/32 REPL POLE | 31502804 | ATASCADERO-CAYUCOS | 003/032 | 70Y | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | South | WSIP | [6 empty] | '-120.729454 | 35.4645 | ETL.8480 | 40760575 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Pismo Beach |  | Y - 12
119001877 | DI HUMBOLDT#1 9/006 RPLC INSS | 31503644 | HUMBOLDT #1 | 009/006 | 93K | E | 2020_(2) High fire spread TD | [5 empty] | North Coast | WSIP | [6 empty] | '-124.054634 | 40.8916 | ETL.7113 | 40809332 | Insulator-Steel | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Eureka
119002581 | T2 DI SAN LS OBISPO-CYCS 6/39 RPR GYWW |  | SAN LUIS OBISPO-CAYUCOS | 006/039 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-120.663511 | 35.3133 | ETL.9090 | 40602151 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - 12
119002584 | T3 DI SAN RAMON-MORAGA 6/27 RPLC INSS | 31504799 | SAN RAMON-MORAGA | 006/027 | 93K | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.018436 | 37.6879 | ETL.5660 | 40605001 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - 10
119002657 | T3 DI GYSRS #17-FLTN 2/15 REPL INSS | 31505662 | GEYSERS #17-FULTON | 002/015 | 93K | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.800769 | 38.8027 | ETL.4770 | 40785661 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Lakeville
119003006 | T3 DI SN LS OBIS-SNT MAR 13/236 RMV BUTT |  | SAN LUIS OBISPO-SANTA MARIA (IDLE) | 013/236 | ICW | F | 2020_(1b) Lines with special commitments |  |  |  | TR3 |  | South | WSIP | [6 empty] | '-120.510879 | 35.1255 | ETL.9100 | 44191949 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - 4
119003116 | T3 DI PARKWAY-MORAGA 020/110 REPL INSS | 31503747 | PARKWAY-MORAGA | 020/110 | 93K | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.203444 | 37.8788 | ETL.5930 | 40788335 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - 11
119003303 | T2 DI ELK-GUALALA 62/004 RPLC INSW | 31502611 | ELK-GUALALA | 062/004 | 93I | E | 2020_(2) High fire spread TD |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.561674 | 38.831 | ETL.8410 | 40763065 | Insulator-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Lakeville
119003306 | DI BEARDSLEY TAP 2/1 RPLC INSW | 31502805 | BEARDSLEY TAP | 002/001 | 93I | E | 2020_(2) High fire spread TD |  |  |  |  | <90D | Central | WSIP | [6 empty] | '-120.060335 | 38.1826 | ETL.1401 | 44390868 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Victor |  | Y - 15
119003619 | DI GATES-MUSTANG SW STA#1 9/42 INS HRDT | 44321500 | SPARE T-LINE RECORD | 009/042 | ICQ | E | 2020_(1b) Lines with special commitments | [5 empty] | South | WSIP | [6 empty] | '-119.968562 | 36.2078 | ETL.2604 | 40647633 | Hardware-Tower | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 7
119004448 | DI GATES-MSTNG SW STA #1 6/27 RPR FOND | 44322513 | SPARE T-LINE RECORD | 006/027 | ICQ | F | 2020_(1b) Lines with special commitments | [5 empty] | South | WSIP | [6 empty] | '-120.02802 | 36.1791 | ETL.2604 | 40810057 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 9
119004507 | T3 DI SBRNTE-GRZLY-CLRMNT 6/41 RPL HRDT | 44326313 | SOBRANTE-GRIZLY-CLARMNT #2+ | 006/041 | ICQ | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.203615 | 37.8567 | ETL.3750 | 40818449 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 10
119004560 | DI GATES-MUSTANG SW STA#1 9/42 RPR FOND | 44321500 | SPARE T-LINE RECORD | 009/042 | ICQ | E | 2020_(1b) Lines with special commitments | [5 empty] | South | WSIP | [6 empty] | '-119.968562 | 36.2078 | ETL.2604 | 40647633 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 7
119004600 | T3 DI DRUM-RIO OSO #2 2/26 RPR FOND | 44326624 | DRUM-RIO OSO #2 | 002/026 | ICQ | F | 2020_(2) High fire spread TD |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.810444 | 39.2486 | ETL.1430 | 40805324 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento
119004605 | T3 DI PITTSBURG-SAN MATEO 10/41 RPR FOND |  | PITTSBURG-SAN MATEO | 010/041 | ICQ | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-121.879973 | 37.8978 | ETL.5463 | 40819140 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  | MDSP
119004607 | T3 DI MORAGA-OAKLAND #1 1/12 BENT STL |  | MORAGA-OAKLAND #1 | 001/012 | ICQ | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.189143 | 37.8371 | ETL.2720 | 40648544 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 7
119004609 | T3 DI MORAGA-OAKLAND #1 1/12 RPL SPLS | 44621662 | MORAGA-OAKLAND #1 | 001/012 | ICS | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.189143 | 37.8371 | ETL.2720 | 40648544 | Splice-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - 8
119004620 | T3 DI ATASCADERO-CAYUCOS 6/58 RPR POLE | 44392280 | ATASCADERO-CAYUCOS | 006/058 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | South | WSIP | [6 empty] | '-120.782201 | 35.4611 | ETL.8480 | 40819611 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - 11
119004730 | T3 DI MORAGA-OAKLAND #3 1/12 RPLC INSS | 31504796 | MORAGA-OAKLAND #3 | 001/012 | 93K | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.18779 | 37.8378 | ETL.2740 | 40704844 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - 9
119004836 | T2 DI DIABLO-MESA 20/91 REPL INSS | 31503711 | DIABLO-MESA | 020/091 | 93K | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-120.592536 | 35.1733 | ETL.4620 | 40611912 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 12
119004847 | DI GATES-MSTNG SW STA #1 7/32 RPR FOND | 44331647 | SPARE T-LINE RECORD | 007/032 | ICQ | E | 2020_(1b) Lines with special commitments | [5 empty] | South | WSIP | [6 empty] | '-120.008201 | 36.1887 | ETL.2604 | 40647629 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 9
119004875 | T3 EI DRUM-SPAULDING 1/33 RPL POLE | 31504201 | DRUM-SPAULDING | 001/033 | 70Y | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.745074 | 39.2545 | ETL.6770 | 40586058 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento
119004885 | T3 DI ATASCADERO-CAYUCOS 7/61 RPR GYWW | 44392212 | ATASCADERO-CAYUCOS | 007/061 | ICW | E | 2020_(2) High fire spread TD |  |  |  |  | LATE | South | WSIP | [8 empty] | ETL.8480 | 44319828 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - Prog 401
119004888 | T3 DI ATASCADERO-CAYUCOS 7/61 RPR GYWW | 44392211 | ATASCADERO-CAYUCOS | 007/061 | ICW | E | 2020_(2) High fire spread TD |  |  |  |  | LATE | South | WSIP | [8 empty] | ETL.8480 | 44319829 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - Prog 401
119004889 | T3 DI ATASCADERO-CAYUCOS 7/61 RPR GYWW | 44392217 | ATASCADERO-CAYUCOS | 007/061 | ICW | E | 2020_(2) High fire spread TD |  |  |  |  | LATE | South | WSIP | [8 empty] | ETL.8480 | 44319830 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - Prog 401
119004902 | T3 DI PARKWAY-MORAGA 020/112 INST BOLT | 44298735 | PARKWAY-MORAGA | 020/112 | ICQ | E | 2020_(3) On high spread structure |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.201294 | 37.8781 | ETL.5930 | 40816009 | Hardware-Tower | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  | EBMUD
119004903 | T3NT DI PARKWAY-MORAGA 020/111 REPR FOND | 44298735 | PARKWAY-MORAGA | 020/111 | ICQ | F | 2020_(2) High fire spread TD |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-122.202125 | 37.8784 | ETL.5930 | 40819377 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  | EBMUD
119004909 | T3 DI MNTE RIO-FORT ROSS 19/004 RPR STRW |  | ETL.6979.POLE.WOOD | 019/004 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.086718 | 38.4826 | ETL.6979 | 40770580 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
119004981 | T3 DI DRUM-RIO OSO #2 2/29 RPLC INSS | 31502784 | DRUM-RIO OSO #2 | 002/029 | 93K | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.81607 | 39.2451 | ETL.1430 | 40896820 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Sacramento
119004989 | T3 DI MORAGA-OAKLAND #1 0/6 RPR SPLS | 44621662 | MORAGA-OAKLAND #1 | 000/006 | ICS | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.174207 | 37.8454 | ETL.2720 | 40830509 | Splice-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - 9
119005003 | DI GATES-MSTNG SW STA#1 8/37 RPR FOND | 44331647 | SPARE T-LINE RECORD | 008/037 | ICQ | E | 2020_(1b) Lines with special commitments | [5 empty] | South | WSIP | [6 empty] | '-119.988362 | 36.1982 | ETL.2604 | 40805351 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 9
119005128 | T3 DI POTTER VALLEY-WILLITS 9/0 RPR POLE | 44610689 | POTTER VALLEY-WILLITS | 009/000 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.2749 | 39.3733 | ETL.7820 | 40587664 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
119005135 | T2 DI PHILO JCT-ELK 031/006 RPL ANCW | 31504605 | PHILO JCT-ELK | 031/006 | 93E | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.622913 | 39.1289 | ETL.7780 | 40826087 | Anchor-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Lakeville
119005169 | DI SAN LUIS OBSPO-CYCOS 15/138 RPR STRW |  | SAN LUIS OBISPO-CAYUCOS | 015/138 | ICW | E | 2020_(4) TD tag on high spread line | [5 empty] | South | WSIP | [6 empty] | '-120.811272 | 35.3574 | ETL.9090 | 40597749 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach
119005193 | T3 DI MORAGA-CLAREMONT #1 3/22 RPR FOND | 44631266 | MORAGA-CLAREMONT #1 | 003/022 | ICQ | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.203444 | 37.8566 | ETL.2700 | 40645976 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 7
119005199 | T3 DI ELDORADO-MIS FLT #1 1/10 RPR SPLS | 44339704 | ELDORADO-MISSOURI FLAT #1 | 001/010 | ICS | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.636483 | 38.7824 | ETL.1530 | 40590079 | Splice-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento
119005245 | DI GATES-MSTNG SW STA#1 10/46 RPR FOND | 44323385 | SPARE T-LINE RECORD | 010/046 | ICQ | F | 2020_(1b) Lines with special commitments | [5 empty] | South | WSIP | [6 empty] | '-119.95275 | 36.2154 | ETL.2604 | 40805362 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 9
119005263 | T3 DI DRUM-RIO OSO #1 2/21 RPR SPLS | 44326626 | DRUM-RIO OSO #1 | 002/021 | ICS | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.804424 | 39.2526 | ETL.1420 | 40589593 | Splice-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento
119005264 | T3 DI DRUM-RIO OSO #1 2/21 RPR STRS | 44326627 | DRUM-RIO OSO #1 | 002/021 | ICS | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.804424 | 39.2526 | ETL.1420 | 40589593 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento
119005372 | T3 EI DRUM-SPAULDING 1/36 RPL POLE | 31504201 | DRUM-SPAULDING | 001/036 | 70Y | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.744002 | 39.2564 | ETL.6770 | 40751829 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento
119005394 | T3 DI DRUM-RIO OSO #1 2/25 RPR SPLS | 44326629 | DRUM-RIO OSO #1 | 002/025 | ICS | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.809339 | 39.2495 | ETL.1420 | 40756201 | Splice-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento
119005736 | DI GATES-MUSTANG SW STA #1 0/3 INS MRKS | 44323214 | SPARE T-LINE RECORD | 000/003 | ICS | F | 2020_(1b) Lines with special commitments | [5 empty] | South | WSIP | [6 empty] | '-120.12269 | 36.1428 | ETL.2604 | 40662283 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  | Y - 11
119005832 | T2 DI CRTNA-MNDCINO#1 33/159 RPR SPLS | 44610540 | CORTINA-MENDOCINO #1 | 033/159 | ICS | E | 2020_(2) High fire spread TD |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.761358 | 39.0803 | ETL.1330 | 40870087 | Splice-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville
119005833 | T2 DI CRTNA-MNDCINO#1 33/159 INST HRDT | 44238817 | CORTINA-MENDOCINO #1 | 033/159 | ICQ | E | 2020_(3) On high spread structure |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.761358 | 39.0803 | ETL.1330 | 40870087 | Hardware-Tower | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville
119005902 | T2NT DI EXCHEQUER-INDIN FLT 1/9 PNT STRT | 44341671 | EXCHEQUER-YOSEMITE | 001/009 | ICS | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-120.253778 | 37.5758 | ETL.8650 | 40859233 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  | Y - 42
119013664 | T2 DI CORTINA-MENDO#1 59/287 INST HRDT |  | CORTINA-MENDOCINO #1 | 059/287 | ICQ | E | 2020_(4b) On structure in bucket 4 |  |  |  | TR2 | <90D | North Coast | WSIP | [6 empty] | '-123.168048 | 39.2418 | ETL.1330 | 40808543 | Hardware-Tower | Missing | Install |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville
119013685 | T3NT DI FULTON-IGNACIO #1 1/10 RPR FOND | 44310479 | FULTON-IGNACIO #1 | 001/010 | ICQ | F | 2020_(4) TD tag on high spread line |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.733963 | 38.4975 | ETL.4680 | 40592327 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville
119013760 | T2 DI CORTINA-MENDO#1 59/288 RPR STRS | 44610540 | CORTINA-MENDOCINO #1 | 059/288 | ICS | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.171651 | 39.2418 | ETL.1330 | 40861445 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville
119014465 | T2 DI CORTNA-MENDOCNO #1 35/168 RPR FOND |  | CORTINA-MENDOCINO #1 | 035/168 | ICQ | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 | <90D | North Coast | WSIP | [6 empty] | '-122.787096 | 39.1 | ETL.1330 | 40861157 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville
119014589 | T3 DI EAGLE ROCK-REDBUD :1/6 RPR FOND |  | EAGLE ROCK-REDBUD | :001/006 | ICQ | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.795296 | 38.8357 | ETL.1480 | 40809066 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville
119014640 | T2 DI CORTNA-MENDOCNO #1 36/171 RPR STRT |  | CORTINA-MENDOCINO #1 | 036/171 | ICQ | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 | <90D | North Coast | WSIP | [6 empty] | '-122.799896 | 39.1069 | ETL.1330 | 40584925 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville
119015279 | T3 DI MISSOURI FLAT-GLD HL#1 RPR FOND | 44339849 | MISSOURI FLAT-GOLD HILL #1 | 019/161 | ICQ | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.902231 | 38.6625 | ETL.2660 | 40586140 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento
119015476 | DI GATES-GREGG 7/34 RPR STRT | 44341601 | SPARE T-LINE RECORD | 007/034 | ICQ | E | 2020_(1b) Lines with special commitments | [5 empty] | South | WSIP | [6 empty] | '-120.000248 | 36.1925 | ETL.2604 | 40746628 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 11
119015591 | DI GATES-GREGG 7/34 RPR FOND | 44341601 | SPARE T-LINE RECORD | 007/034 | ICQ | E | 2020_(1b) Lines with special commitments | [5 empty] | South | WSIP | [6 empty] | '-120.000248 | 36.1925 | ETL.2604 | 40746628 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 11
119016121 | DI RIO DELL JCT-BRIDGEVLLE 37/4 RPL POLE | 31503085 | RIO DELL JCT-BRIDGEVILLE | 037/004 | 70Y | E | 2020_(4) TD tag on high spread line | [5 empty] | North Coast | WSIP | [6 empty] | '-123.836218 | 40.4665 | ETL.7850 | 40769400 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka
119016211 | T3 DI EAGLE ROCK-REDBUD :9/53 RPR FOND |  | EAGLE ROCK-REDBUD | :009/053 | ICQ | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.66868 | 38.8881 | ETL.1480 | 40648896 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville
119016272 | T2 DI SAN LS OBISPO-CYCS 9/67 RPR SPLW |  | SAN LUIS OBISPO-CAYUCOS | 009/067 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-120.693562 | 35.3166 | ETL.9090 | 40760560 | Splice-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - 12
119016315 | T2 DI FORT ROSS-GUALALA 038/008 RPR GYWW |  | GUALALA-MONTE RIO | 038/008 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.31194 | 38.6258 | ETL.6980 | 40860960 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
119016549 | T2 DI FORT ROSS-GUALALA 51/000 REPR GYWW |  | GUALALA-MONTE RIO | 051/000 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.4223 | 38.7298 | ETL.6980 | 40606927 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
119016620 | T2 DI CORTNA-MENDOCNO #1 40/196 RPR FOND |  | CORTINA-MENDOCINO #1 | 040/196 | ICQ | F | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.876013 | 39.1421 | ETL.1330 | 40822489 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville
119016680 | T2 DI FORT ROSS-GUALALA 51/000 REPL INSW | 31502792 | GUALALA-MONTE RIO | 051/000 | 93I | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.422878 | 38.73 | ETL.6980 | 40637492 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Lakeville
119016688 | DI RIO DLL JCT-BRDGVLE 39/04 RMV BUTT | 44326491 | RIO DELL JCT-BRIDGEVILLE | 039/004 | ICW | F | 2020_(4b) On structure in bucket 4 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.801747 | 40.4704 | ETL.7850 | 40750417 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
119016690 | T3 EAGLE RCK-FLTN-SLVRDO 11/45 RPR SLEEV |  | EAGLE ROCK-FULTON-SILVERADO | 011/045 | ICS | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.727002 | 38.595 | ETL.4392 | 41129347 | Splice-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville
119016734 | DI FORT ROSS-GUALALA 042/000 RPR GYWW |  | GUALALA-MONTE RIO | 042/000 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  |  | SCHD | North Coast | WSIP | [8 empty] | ETL.6980 | 44312229 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
119016735 | T2 PHILO JCT ELK 011/000 REPAIR POLEW | 44610684 | PHILO JCT-ELK | 011/000 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.311373 | 39.0274 | ETL.7780 | 44799552 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
119016736 | DI FORT ROSS-GUALALA 042/000 BOND GUY |  | GUALALA-MONTE RIO | 042/000 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  |  | SCHD | North Coast | WSIP | [8 empty] | ETL.6980 | 44312228 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
119016750 | DI GATES-MSTNG SW STA#1 10/45 RPR STRT | 44571491 | SPARE T-LINE RECORD | 010/045 | ICQ | E | 2020_(1b) Lines with special commitments | [5 empty] | South | WSIP | [6 empty] | '-119.95683 | 36.2134 | ETL.2604 | 40746598 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 11
119016752 | DI GATES-MSTNG SW STA#1 10/45 INST HRDT | 44328897 | SPARE T-LINE RECORD | 010/045 | ICQ | E | 2020_(1b) Lines with special commitments | [5 empty] | South | WSIP | [6 empty] | '-119.95683 | 36.2134 | ETL.2604 | 40746598 | Hardware-Tower | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 7
119016775 | T3 DI FULTON-LAKEVILLE 027/121 REPL INSS | 31506378 | FULTON-LAKEVILLE | 027/121 | 93K | E | 2020_(1a) PSPS |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.592944 | 38.4655 | ETL.4950 | 41130060 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Lakeville
119016778 | T3 DI DRUM-RIO OSO #2 2/28 RPR STRT | 44326630 | DRUM-RIO OSO #2 | 002/028 | ICQ | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.815381 | 39.2455 | ETL.1430 | 40866872 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento
119017125 | T2NT DI CORTNA-MNDCNO #1 48/234 RPR FOND |  | CORTINA-MENDOCINO #1 | 048/234 | ICQ | F | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.976271 | 39.2013 | ETL.1330 | 40750610 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville
119017159 | DI ELK-GUALALA 052/001 REPL INSW | 31504606 | ELK-GUALALA | 052/001 | 93I | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.6763 | 38.9269 | ETL.8410 | 40621651 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Lakeville
119019640 | T2 EAGLE ROCK-CORTINA 13/062 RPL HANGER | 44346063 | EAGLE ROCK-CORTINA | 013/062 | ICQ | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.437368 | 39.0383 | ETL.1470 | 44941620 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento
119019649 | T2 EAGLE ROCK-CORTINA 11/056 RPL HANGER | 44346063 | EAGLE ROCK-CORTINA | 011/056 | ICQ | E | 2020_(2) High fire spread TD |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.412288 | 39.0525 | ETL.1470 | 44941619 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento
119019697 | T2 SOBRNTE-GRZLY-CLRMNT #2 A0/1 RPR SWTC | 44621458 | SOBRANTE-GRIZLY-CLARMNT #2+ | A000/001 | ICE | E | 2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-122.21048 | 37.9048 | ETL.3750 | 40705186 | Switch | Out of Adjustment | Repair | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 623 | Bay |  |  | EBMUD
119019961 | T3 DI OLEUM-G #2 8/55 RPLC INSS |  | OLEUM-G #2 | 008/055 | 93K | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.271784 | 37.9449 | ETL.3160 | 40774777 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  |  | WCRP
119020768 | DRUM-GRASS VLLY-WMR B025/567 REWORK | 31454660 | DRUM-GRASS VALLEY-WEIMAR | B025/567 | 93E | E | 2020_(4) TD tag on high spread line | [5 empty] | North Valley | WSIP | [6 empty] | '-121.061376 | 39.2042 | ETL.6760 | 40866687 | Crossarm-Wood | No Good/Out of Stdrd | Replace | DOCC srdy | DOCC | Job has been constructed (documentation) | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Sacramento
119021011 | T3 DI ATASCADERO-CAYUCOS 6/54 RPR POLE | 44392282 | ATASCADERO-CAYUCOS | 006/054 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | South | WSIP | [6 empty] | '-120.774927 | 35.4617 | ETL.8480 | 40658199 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - 11
119021013 | T3 DI ATASCADERO-CAYUCOS 6/59 REFRAME | 31504190 | ATASCADERO-CAYUCOS | 006/059 | 93E | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | South | WSIP | [6 empty] | '-120.784285 | 35.4603 | ETL.8480 | 40872891 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Pismo Beach |  | Y - 11
119021662 | T2 DI SAN LUIS OBSPO-CYCS 14/127 RPR PL |  | SAN LUIS OBISPO-CAYUCOS | 014/127 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-120.788506 | 35.3404 | ETL.9090 | 40596531 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - 12
119021667 | T2 DI SLO-CAYUCOS 14/128 RPR GUY HRDD |  | SAN LUIS OBISPO-CAYUCOS | 014/128 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-120.790368 | 35.3418 | ETL.9090 | 40597794 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - 12
119022412 | T2 DI SLO-CAYUCOS 14/128 RPR STRW |  | SAN LUIS OBISPO-CAYUCOS | 014/128 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-120.790368 | 35.3418 | ETL.9090 | 40597794 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - 12
119023441 | T2 DI SAN LS OBISPO-CYCS 7/49 RPR INSW |  | SAN LUIS OBISPO-CAYUCOS | 007/049 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-120.676223 | 35.3161 | ETL.9090 | 40717170 | Insulator-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - 12
119024393 | T2 DI SAN LS OBISPO-CYCS 7/51 RPLC SPLW |  | SAN LUIS OBISPO-CAYUCOS | 007/051 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | South | WSIP | [8 empty] | ETL.9090 | 44376815 | Splice-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - Prog 401
119024394 | T2NT DI SAN LS OBSPO-CYCS 7/51 INST MRKW |  | SAN LUIS OBISPO-CAYUCOS | 007/051 | ICW | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-120.679338 | 35.3176 | ETL.9090 | 40755496 | Marker (i.e. signs)-Wood | Missing | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - 12
119024695 | T3 DI DRUM-RIO OSO #1 2/29 RPR FOND | 44339678 | DRUM-RIO OSO #1 | 002/029 | ICQ | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.816209 | 39.2452 | ETL.1420 | 40870507 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento
119024972 | T3 DI EAGLE RK-FLTN-SLVRDO 7/36 RPR STRT | 44326454 | EAGLE ROCK-FULTON-SILVERADO | 007/036 | ICQ | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.76483 | 38.7442 | ETL.4392 | 40814652 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville
119026416 | T3 DI MORAGA-SN LEANDRO #1 3/29 RPR FOND |  | MORAGA-SAN LEANDRO #1 | 003/029 | ICQ | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.130524 | 37.802 | ETL.2770 | 40870097 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  | EBMUD
119026447 | T3 DI TIGR CRK-VLLY SPGS 8/65 REPL INSS | 31512319 | TIGER CREEK-VALLEY SPRINGS | 008/065 | 93K | E | 2020_(4) TD tag on high spread line |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-120.624676 | 38.3964 | ETL.5790 | 40718480 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Victor |  | Y - Prog 402
119026564 | T2 DI ELK-GUALALA 055/008 RPR GYWW |  | ELK-GUALALA | 055/008 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.637946 | 38.9031 | ETL.8410 | 40871841 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
119026673 | T3 DI FULTON-PUEBLO 029/141 REPR FOND |  | FULTON-PUEBLO | 029/141 | ICQ | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.516951 | 38.4931 | ETL.1600 | 40586782 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville
119026754 | DI WEST PONT-VLY SPRNGS 4/55 RMV PL BUTT |  | WEST POINT-VALLEY SPRINGS | 004/055 | GAR | F | 2020_(4) TD tag on high spread line | [5 empty] | Central | WSIP | [8 empty] | ETL.8350 | 44405873 | Structure-Wood | Rotten | Stub |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 586 | Victor
119026758 | T2 DI MONTA VSTA-JFFRSN #1 6/25 RPL HRDT |  | MONTA VISTA-JEFFERSON #1 | 006/025 | ICQ | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-122.180639 | 37.3299 | ETL.5220 | 40760553 | Hardware-Tower | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 10 | LTOSP
119026759 | T2NT DI MNT VSTA-JFFRSN #1 6/25 RPR FOND |  | MONTA VISTA-JEFFERSON #1 | 006/025 | ICQ | F | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-122.180639 | 37.3299 | ETL.5220 | 40760553 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 10 | LTOSP
119027090 | T2 DI VLY SPRNGS-MRTL#1 10/14 RPR STRW |  | VALLEY SPRINGS-MARTELL #1 | 010/014 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-120.783152 | 38.3432 | ETL.8240 | 40768889 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 24
119027252 | DI MUSTANG SW STA-GRGG X056/238 RPR FOND | 44346364 | GATES-GREGG | X056/238 | ICQ | E | 2020_(1b) Lines with special commitments |  |  |  |  | WECC | South | WSIP | [6 empty] | '-119.900693 | 36.8259 | ETL.4700 | 40858326 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 5
119027258 | DI MUSTANG SW STA-GRGG X055/236 RPR STRT | 44342028 | GATES-GREGG | X055/236 | ICQ | E | 2020_(1b) Lines with special commitments |  |  |  |  | WECC | South | WSIP | [6 empty] | '-119.900705 | 36.8198 | ETL.4700 | 40805390 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 5
119027344 | DI MUSTANG SW STA-GRGG X055/236 RPR FOND | 44342028 | GATES-GREGG | X055/236 | ICQ | E | 2020_(1b) Lines with special commitments |  |  |  |  | WECC | South | WSIP | [6 empty] | '-119.900705 | 36.8198 | ETL.4700 | 40805390 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 5
119027349 | DI MUSTNG SW STA-GRGG X49/206 RMV DEBRIS | 44341661 | GATES-GREGG | X049/206 | ICS | E | 2020_(1b) Lines with special commitments |  |  |  |  | WECC | South | WSIP | [6 empty] | '-119.897204 | 36.7298 | ETL.4700 | 40815319 | Structure-Steel | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  | Y - 5
119028433 | DI SNEATH LN-HALF MOON BY ?0/2 RPR INSW | 31503553 | SNEATH LANE-HALF MOON BAY | ?000/002 | 93I | E | 2020_(4) TD tag on high spread line | [5 empty] | Central | WSIP | [6 empty] | 122.4893 | 37.5942 | ETL.7212 | 40714078 | Insulator-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Bay |  | Y - 29
119028435 | T3 DI MORAGA-OAKLAND #4 1/12 RPLC INSS | 31508629 | MORAGA-OAKLAND #4 | 001/012 | 93K | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.187282 | 37.8378 | ETL.2750 | 40704846 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - 2
119029024 | T3 EI MIDDLE FORK #1 7/105 RPR GWSW | 44339848 | MIDDLE FORK #1 | 007/105 | ICK | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.711017 | 39.0029 | ETL.8405 | 40810143 | Auto Guy Wire Splice-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 515 | Sacramento
119029025 | T3 EI MIDDLE FORK #1 7/105 RPR ANCW | 44339029 | MIDDLE FORK #1 | 007/105 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.711017 | 39.0029 | ETL.8405 | 40810143 | Anchor-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119029026 | T3 EI MIDDLE FORK #1 7/105 RMV VEGN |  | MIDDLE FORK #1 | 007/105 | HNA | E | 2020_(3) On high spread structure |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.711017 | 39.0029 | ETL.8405 | 40810143 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento
119029112 | T2 ROUND MTN-COTTNWD #3 46/3 RPL INSS | 31504993 | ROUND MTN-COTTONWOOD #3 | 046/399 | 93K | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.1314537 | 40.5604 | ETL.5650 | 40884291 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain
119029325 | T3 EI MIDDLE FORK #1 7/107 RPR ANCW | 44339029 | MIDDLE FORK #1 | 007/107 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.713808 | 39.003 | ETL.8405 | 40874900 | Anchor-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119029389 | T3 EI MIDDLE FORK #1 7/106 BOND GUY | 44339029 | MIDDLE FORK #1 | 007/106 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.712705 | 39.003 | ETL.8405 | 40822815 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119029406 | T3 EI ORO FINO TAP - 60 kV_000/012 RPR S | 43758390 | ORO FINO TAP | 000/012 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.620065 | 39.8688 | ETL.6721 | 40700244 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119029671 | T3 LAURELES-OTTER 013/013 RPR STRW | 31475444 | LAURELES-OTTER | 013/013 | 93I | E | 2020_(4) TD tag on high spread line |  |  | Likely MAT error - delink to correct | TR3 | LATE | South | WSIP | [6 empty] | '-121.868232 | 36.3862 | ETL.7380 | 40668280 | Structure-Wood | No Good/Out of Stdrd | Repair | POST | POST | POST Estimate | Not Complete | PEND | LC | TLN | Maintenance | Capital | 630 | Moss Landing |  | Y - 12
119029767 | T2 VLY SPRGS-MARTELL #1 003/019 RPL PL T | 31503164 | VALLEY SPRINGS-MARTELL #1 | 003/019 | 70Y | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 | <90D | Central | WSIP | [6 empty] | '-120.772185 | 38.2556 | ETL.8240 | 40874931 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 24
119030082 | T2 PHILO JCT-ELK 007/000 RPR CONDW | 44610684 | PHILO JCT-ELK | 007/000 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.24797 | 39.0515 | ETL.7780 | 40614234 | Conductor-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
119030163 | T2 DI CORTINA-MENDCINO #1 13/63 RPL INSS | 31502267 | CORTINA-MENDOCINO #1 | 013/063 | 93K | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.441222 | 39.0362 | ETL.1330 | 40655208 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Sacramento
119030178 | T3 WEST POINT-VLY SPRGS 2/31 RPL POLE - | 31502979 | WEST POINT-VALLEY SPRINGS | 002/031 | 70Y | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-120.589974 | 38.421 | ETL.8350 | 40825786 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor
119030244 | T2 DI 10245 OLEUM-G #1 10/68 RPL INSS |  | OLEUM-G #1 | 010/068 | 93K | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 | SCHD | Central | WSIP | [6 empty] | '-122.288972 | 37.9192 | ETL.3150 | 40857750 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - 9
119030320 | T2 DI 10245 OLEUM-G #1 10/68 RMV VEG |  | OLEUM-G #1 | 010/068 | HNA | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-122.288972 | 37.9192 | ETL.3150 | 40857750 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Bay
119030323 | T2 DI 10245 OLEUM-G #2 010/066 RPR SPLS | 44621444 | OLEUM-G #2 | 010/066 | ICS | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 | SCHD | Central | WSIP | [6 empty] | '-122.284407 | 37.92 | ETL.3160 | 44377341 | Splice-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - 9
119030324 | DI SOBRANTE-GRLY-CLRMNT #2 3/27 RPR STRT |  | SOBRANTE-GRIZLY-CLARMNT #2+ | 003/027 | ICQ | E | 2020_(4b) On structure in bucket 4 | [5 empty] | Central | WSIP | [6 empty] | '-122.178209 | 37.8681 | ETL.3750 | 40659418 | Structure-Tower | Anti-Climbing Guard | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 10
119030327 | DI SOBRANTE-GRLY-CLRMNT #2 3/27 RPR FOND |  | SOBRANTE-GRIZLY-CLARMNT #2+ | 003/027 | ICQ | E | 2020_(4) TD tag on high spread line | [5 empty] | Central | WSIP | [6 empty] | '-122.178209 | 37.8681 | ETL.3750 | 40659418 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 10
119030365 | T2 LOWER LKE-HMSTAKE 10/9 REFRAME STRS |  | LOWER LAKE-HOMESTAKE TAP | 010/009 |  | E | 2020_(2) High fire spread TD |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.457499 | 38.8846 | ETL.1481 | 44917331 | Crossarm-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLQ | Tower | Expense |  | Lakeville
119030458 | T3 EAGLE ROCK-REDBUD :004/023 RPL INSS | 31506377 | EAGLE ROCK-REDBUD | :004/023 | 93K | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Coast | WSIP | [8 empty] | ETL.1480 | 40739312 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Lakeville
119030586 | T2 DI FORT ROSS-GUALALA 050/006 RPR GYWW |  | GUALALA-MONTE RIO | 050/006 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.414692 | 38.7259 | ETL.6980 | 40821495 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
119031184 | T2 DI ELK-GUALALA 65/0 RPL POLE | 31504604 | ELK-GUALALA | 065/000 | 70Y | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.531802 | 38.8014 | ETL.8410 | 40605939 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville
119033840 | T3 EI MIDDLE FORK #1 1/019 RPR GYWW | 44339029 | MIDDLE FORK #1 | 001/019 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.600028 | 39.0092 | ETL.8405 | 40598765 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119033944 | T3 EI MIDDLE FORK #1 7/105 BOND GUY | 44339029 | MIDDLE FORK #1 | 007/105 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.711017 | 39.0029 | ETL.8405 | 40810143 | Ground Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119033961 | DI WST PNT-VLY SPRG 4/54C RPL STRW | 31503556 | WEST POINT-VALLEY SPRINGS | 004/054 | 70Y | E | 2020_(4) TD tag on high spread line | [5 empty] | Central | WSIP | [8 empty] | ETL.8350 | 44405860 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor
119033980 | T3 EI MIDDLE FORK #1 7/105 INST DAMPER | 44339029 | MIDDLE FORK #1 | 007/105 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.711017 | 39.0029 | ETL.8405 | 40810143 | Damper-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119034175 | DI WST PNT-VLY SPRG 4/54L RPL POLE | 31503556 | WEST POINT-VALLEY SPRINGS | 004/054 | 70Y | E | 2020_(4) TD tag on high spread line | [5 empty] | Central | WSIP | [8 empty] | ETL.8350 | 44405861 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor
119034245 | DI WST PNT-VLY SPRG 4/54R RPL POLE | 31503556 | WEST POINT-VALLEY SPRINGS | 004/054 | 70Y | E | 2020_(4) TD tag on high spread line | [5 empty] | Central | WSIP | [8 empty] | ETL.8350 | 44405862 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor
119035354 | T2 DI STNSLS-MLNS-MNTC 22/137 BENT STL |  | STANISLAUS-MELONES SS-MANTECA #1+ | 022/137 | ICQ | E | 2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-120.688977 | 37.9524 | ETL.3830 | 40803333 | Structure-Tower | Anti-Climbing Guard | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - 22
119035414 | T2 DI STNSLS-MLNS-MNTC 22/137 RPR FOND |  | STANISLAUS-MELONES SS-MANTECA #1+ | 022/137 | ICQ | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-120.688977 | 37.9524 | ETL.3830 | 40803333 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - 22
119035416 | T2 DI STNSLS-MLNS-MNTC 22/137 INST BOLT |  | STANISLAUS-MELONES SS-MANTECA #1+ | 022/137 | ICQ | E | 2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-120.688977 | 37.9524 | ETL.3830 | 40803333 | Hardware-Tower | Missing | Install |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - 22
119035575 | T3 DI GYSRS#3-CLVRDL 8/94 RPR POLE | 44580896 | GEYSERS #3-CLOVERDALE | 008/094 | ICW | E | 2020_(1a) PSPS |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.951033 | 38.7998 | ETL.1650 | 40659189 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
119035578 | T3 DI GYSRS#3-CLVRDL 8/94 BOND GUY | 44580896 | GEYSERS #3-CLOVERDALE | 008/094 | ICW | E | 2020_(1a) PSPS |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.951033 | 38.7998 | ETL.1650 | 40659189 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
119035719 | T3 DI GEYSERS#9-LAKVLLE 01/07 RPR INSS |  | GEYSERS #9-LAKEVILLE | 001/007 | ICS | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.76768 | 38.7909 | ETL.4780 | 40710885 | Insulator-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville
119036191 | T3NT DI MORAGA-CLRMNT #1 3/23 RPR FOND | 44631266 | MORAGA-CLAREMONT #1 | 003/023 | ICQ | F | 2020_(2) High fire spread TD |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-122.207804 | 37.852 | ETL.2700 | 40644184 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay
119036192 | T3NT DI MORAGA-CLAREMNT #1 3/23 PNT STRS | 44586161 | MORAGA-CLAREMONT #1 | 003/023 | ICS | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-122.207804 | 37.852 | ETL.2700 | 40644184 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Bay
119036207 | T3 DI FULTON-HOPLAND :027/003 RPR POLE | 44579280 | FULTON-HOPLAND | :027/003 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.988001 | 38.8012 | ETL.6890 | 40664531 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
119036216 | T3 DI FULTON-PUEBLO 18/86 RPL INSS | 31505500 | FULTON-PUEBLO | 018/086 | 92E | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.327374 | 38.5023 | ETL.1600 | 40831855 | Insulator-Steel | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Lakeville
119036237 | T3 FULTON-CALISTOGA_:003/000 REFRAME | 31505209 | FULTON-CALISTOGA | :003/000 | 93E | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.595056 | 38.6326 | ETL.6880 | 40912430 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Lakeville
119036275 | T2 DI CRTNA-MENDOCINO #1 57/281 RPR FOND |  | CORTINA-MENDOCINO #1 | 057/281 | ICQ | F | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.133708 | 39.2342 | ETL.1330 | 40584934 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville
119036276 | T2 DI CRTNA-MNDOCINO #1 57/281 INST HRDT |  | CORTINA-MENDOCINO #1 | 057/281 | ICQ | E | 2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.133708 | 39.2342 | ETL.1330 | 40584934 | Hardware-Tower | Missing | Install |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville
119036288 | T2 DI STNSLS-MLNS-MNTC 19/123 RPR STRT |  | STANISLAUS-MELONES SS-MANTECA #1+ | 019/123 | ICQ | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-120.661438 | 37.9729 | ETL.3830 | 40642845 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - 22
119036337 | T2 DI ELK-GUALALA 59/3 RPLC INSW | 31503233 | ELK-GUALALA | 059/003 | 93I | E | 2020_(2) High fire spread TD |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.590581 | 38.8685 | ETL.8410 | 40699290 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Lakeville
119036551 | T2 DI CLEAR LAKE-HOPLAND 01/03 RMV BUTT | 44610498 | CLEAR LAKE-HOPLAND | 001/003 | ICW | E | 2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.059435 | 38.9693 | ETL.6390 | 40667033 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
119036773 | T2 DI ELK-GUALALA 39/8 RPR GYWW | 44610591 | ELK-GUALALA | 039/008 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.698251 | 39.0922 | ETL.8410 | 40877405 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
119036828 | DI GATES-MUSTANGS SS #1 11/048 REPR FOND | 44326364 | SPARE T-LINE RECORD | 011/048 | ICQ | F | 2020_(1b) Lines with special commitments | [5 empty] | South | WSIP | [6 empty] | '-119.944735 | 36.2192 | ETL.2604 | 40858298 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 9
119036996 | T3 EI DRUM-SUMMIT #1 001/021 RPL STRW | 31508705 | DRUM-SUMMIT #1 | 001/021 | 70Y | E | 2020_(1b) Lines with special commitments |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.740703 | 39.2612 | ETL.1440 | 44765187 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento
119038110 | DI MUSTANG SW STA-GREGG 19/83 RMV DEBRIS | 44342033 | GATES-GREGG | 019/083 | ICS | E | 2020_(1b) Lines with special commitments |  |  |  |  | WECC | South | WSIP | [6 empty] | '-119.879357 | 36.2955 | ETL.4700 | 40659466 | Structure-Steel | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  | Y - 5
119038118 | DI PARKWAY-MORAGA 021/119 RPR FOND |  | PARKWAY-MORAGA | 021/119 | ICQ | F | 2020_(4) TD tag on high spread line | [5 empty] | Central | WSIP | [6 empty] | '-122.180554 | 37.8657 | ETL.5930 | 40759114 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 11
119038128 | T3 DI PITTSBURG-SAN MATEO 22/90 RPR FOND |  | PITTSBURG-SAN MATEO | 022/090 | ICQ | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-121.95457 | 37.7359 | ETL.5463 | 40764506 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 10
119038695 | T3 SBTE-GRZLY-CLRMNT #2 6/40 RPL ARMS | 44326313 | SOBRANTE-GRIZLY-CLARMNT #2+ | 006/040 | ICQ | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.200555 | 37.8595 | ETL.3750 | 40804897 | Structure-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  | SVRPR
119038776 | T3 MONTE RIO-FULTON 13/1C REPL POLE | 31501349 | MONTE RIO-FULTON | 013/001 | 70Y | E | 2020_(4) TD tag on high spread line |  |  |  |  | LATE | North Coast | WSIP | [8 empty] | ETL.7630 | 44315963 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville
119038864 | DI LAKEVILLE#1 10/6 GRD WSH INSW |  | LAKEVILLE #1 | 010/006 | ICD | E | 2020_(4) TD tag on high spread line |  |  |  |  | SCHD | North Coast | WSIP | [6 empty] | '-122.527872 | 38.3826 | ETL.7360 | 40836118 | Insulator | Contaminated | Ground Wash |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 622 | Lakeville
119039186 | T3 EI MIDDLE FORK #1 0/004 CTTR KEY | 44332282 | MIDDLE FORK #1 | 000/004 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.597476 | 39.0218 | ETL.8405 | 40767429 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119039187 | T3 EI MIDDLE FORK #1 000/004 ARMR ROD | 44332282 | MIDDLE FORK #1 | 000/004 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.597476 | 39.0218 | ETL.8405 | 40767429 | Conductor-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119039200 | T2 EI DIABLO-GATES #1 023/095 RPL INST | 31526479 | DIABLO-GATES #1 | 023/095 | 93K | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-120.7175886 | 35.5145 | ETL.5960 | 40792242 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 17
119039479 | T2 EI DIABLO-GATES #1 023/096 RPL INST | 31526479 | DIABLO-GATES #1 | 023/096 | 93K | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-120.7151653 | 35.5175 | ETL.5960 | 40839529 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 17
119039521 | EI T2NT DIABLO-GATES #1 023/096 RMV DEBR | 44298383 | DIABLO-GATES #1 | 023/096 | CHS | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-120.715153 | 35.5175 | ETL.5960 | 40812113 | Road | Encroachment | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLR | Roads | Expense | 931 | Pismo Beach
119039645 | DI EAGLE ROCK-REDBUD :12/73 RPR FOND |  | EAGLE ROCK-REDBUD | :012/073 | ICQ | E | 2020_(4) TD tag on high spread line | [5 empty] | North Coast | WSIP | [6 empty] | '-122.619932 | 38.9102 | ETL.1480 | 40659642 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville
119039807 | T2 DI ELK-GUALALA 053/000 RPL INSS | 31528733 | ELK-GUALALA | 053/000 | 93K | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.680323 | 38.9137 | ETL.8410 | 40616755 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Lakeville
119039817 | T3 MISSRI FLT-GLD HLL #1 17/148 RPL INSS | 31504275 | MISSOURI FLAT-GOLD HILL #1 | 017/148 | 93K | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.8602221 | 38.6752 | ETL.2660 | 40898939 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Sacramento
119039867 | T2 DI ELK-GUALALA 053/000 RPR FOND |  | ELK-GUALALA | 053/000 | ICQ | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.680323 | 38.9137 | ETL.8410 | 40616755 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville
119040036 | T2 EI DIABLO-GATES #1 022/091 RPL INSS | 31526479 | DIABLO-GATES #1 | 022/091 | 93K | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-120.7269204 | 35.503 | ETL.5960 | 40614760 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 17
119040150 | T2 DI SN LS OBSP-SNT MRA 11/195 RPL GYWW |  | SAN LUIS OBISPO-SANTA MARIA (IDLE) | 011/195 | ICW | E | 2020_(1b) Lines with special commitments |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-120.530481 | 35.1434 | ETL.9100 | 44191360 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - 4
119040155 | T2 DI SN LS OBSP-SNT MRA 11/195 INS MRKW |  | SAN LUIS OBISPO-SANTA MARIA (IDLE) | 011/195 | ICW | F | 2020_(1b) Lines with special commitments |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-120.530481 | 35.1434 | ETL.9100 | 44191360 | Marker (i.e. signs)-Wood | Missing | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - 4
119040158 | T2 DI SN LS OBSP-SNT MRA 11/195 RPR SPLW |  | SAN LUIS OBISPO-SANTA MARIA (IDLE) | 011/195 | ICW | E | 2020_(1b) Lines with special commitments |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-120.530481 | 35.1434 | ETL.9100 | 44191360 | Splice-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - 4
119040276 | T3 MONTE RIO-FORT ROSS 15/004 RPR GYWW |  | ETL.6979.POLE.WOOD | 015/004 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.01231 | 38.4779 | ETL.6979 | 40750316 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
119040460 | T3 FULTON-PUEBLO 038/197 INS INSS | 31505500 | FULTON-PUEBLO | 038/197 | 92E | E | 2020_(4b) On structure in bucket 4 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.68717 | 38.4965 | ETL.1600 | 40818390 | Emergency | Fire | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLN | Maintenance | Capital | 437 | Lakeville
119041041 | T2 DI EAGLE RCK-CORTINA 11/54 REPL INS | 31503642 | EAGLE ROCK-CORTINA | 011/054 | 93K | E | 2020_(2) High fire spread TD |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.664351 | 38.8885 | ETL.1470 | 40796412 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Sacramento
119041215 | T3NT DI PARKWAY-MORAGA 19/109 RPR FOND | 44298735 | PARKWAY-MORAGA | 019/109 | ICQ | F | 2020_(2) High fire spread TD |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-122.205925 | 37.8796 | ETL.5930 | 40762788 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  | EBMUD
119041217 | DI STNS-MLNS SWSTA-MN#1 19/121 RPLC HRDT |  | STANISLAUS-MELONES SS-MANTECA #1+ | 019/121 | ICQ | E | 2020_(4) TD tag on high spread line | [5 empty] | Central | WSIP | [6 empty] | '-120.657175 | 37.9761 | ETL.3830 | 41136914 | Hardware-Tower | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - 22
119041252 | T2 EI DIABLO-GATES #1 022/090 RPL INSS | 31526479 | DIABLO-GATES #1 | 022/090 | 93K | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-120.7298248 | 35.4994 | ETL.5960 | 40631779 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 17
119041352 | T2 DI FORT ROSS-GUALALA 039/012 RPL SPLW |  | GUALALA-MONTE RIO | 039/012 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.314846 | 38.6402 | ETL.6980 | 40656371 | Splice-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
119041430 | DI BRIGHTON-DAVIS 23/238 RPR GWYS | 44332239 | BRIGHTON-DAVIS | 023/238 | ICS | B | 2020_(9c) Time-dependent non-HFTD tags, (last year and later) | [5 empty] | North Valley | WSIP | [6 empty] | '-121.695352 | 38.5155 | ETL.1140 | 40862318 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento
119041518 | DI STNS-MLNS SWSTA-MN#1 19/121 RPR STRT |  | STANISLAUS-MELONES SS-MANTECA #1+ | 019/121 | ICQ | E | 2020_(4) TD tag on high spread line | [5 empty] | Central | WSIP | [6 empty] | '-120.657175 | 37.9761 | ETL.3830 | 41136914 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - 22
119041519 | DI STNS-MLNS SWSTA-MN#1 19/121 STRS RPNT |  | STANISLAUS-MELONES SS-MANTECA #1+ | 019/121 | ICS | F | 2020_(4b) On structure in bucket 4 | [5 empty] | Central | WSIP | [6 empty] | '-120.657175 | 37.9761 | ETL.3830 | 41136914 | Structure-Steel | Paint/Coating | Other |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - 22
119043946 | T3 DI DRUM-RIO OSO #2 004/049 RPL INSS | 31503652 | DRUM-RIO OSO #2 | 004/049 | 93K | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.834864 | 39.2256 | ETL.1430 | 40889166 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Sacramento
119044022 | T3 DI DRUM-RIO OSO #2 10/107 RPL INSS | 31503652 | DRUM-RIO OSO #2 | 010/107 | 93K | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.934059 | 39.1694 | ETL.1430 | 40829297 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Sacramento
119044080 | T3 DI SBRNT-GRZLY-CLRMT #1 1/18 RPR FOND |  | SOBRNTE-GRIZZLY-CLARMNT #1+ | 001/018 | ICQ | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.194661 | 37.8882 | ETL.3740 | 40644699 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog 402
119044733 | T3 DI SAN RAMON-MORAGA 6/30 RPLC INSS | 31504799 | SAN RAMON-MORAGA | 006/030 | 93K | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.0255 | 37.6852 | ETL.5660 | 40782564 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  |  | GRP
119044736 | T3 DI TIGER CREEK-ELECTRA 6/47 RPL HRDS |  | TIGER CREEK-ELECTRA | 006/047 | ICS | F | 2020_(2) High fire spread TD |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-120.589632 | 38.4217 | ETL.5780 | 40819485 | Hardware-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - 11
119045503 | T3 DI DRUM-RIO OSO #2 008/083 RPR SPLS | 44332280 | DRUM-RIO OSO #2 | 008/083 | ICS | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.880357 | 39.1909 | ETL.1430 | 40655211 | Splice-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento
119045596 | T3NT DI MORAGA-SAN LNDRO #1 7/52 RPR FND |  | MORAGA-SAN LEANDRO #1 | 007/052 | ICQ | F | 2020_(4) TD tag on high spread line |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-122.114006 | 37.7494 | ETL.2770 | 40646049 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  | ACRP
119045799 | T3 DI SBRNT-GRZLY-CLRMT #1 4/40 RPL STEP |  | SOBRNTE-GRIZZLY-CLARMNT #1+ | 004/040 | ICQ | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.195233 | 37.8618 | ETL.3740 | 40761864 | Hardware-Tower | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  | EBMUD
119045830 | T3 DI MONTE RIO-FULTON 14/5 RPL POLE | 31428882 | MONTE RIO-FULTON | 014/005 | 70Y | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.00761 | 38.4779 | ETL.7630 | 40750287 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville
119045862 | T3 DI FULTON-CALISTOGA 7/1 RPLC STRW | 31504258 | FULTON-CALISTOGA | 007/001 | 70Y | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.519836 | 38.5774 | ETL.6880 | 40585443 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville
119045884 | T2 DI BRDGVLL-CTTNWD 11/106 RPR GYWW | 43939216 | BRIDGEVILLE-COTTONWOOD | 011/106 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.482862 | 40.389 | ETL.1110 | 44424030 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119045885 | T2 DI BRDGVLL-CTTNWD 11/106 RPR GYWW | 43939216 | BRIDGEVILLE-COTTONWOOD | 011/106 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.482862 | 40.389 | ETL.1110 | 44424031 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119045888 | T2 DI BRDGVLL-CTTNWD 11/106 RPR GYWW | 43939216 | BRIDGEVILLE-COTTONWOOD | 011/106 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.482862 | 40.389 | ETL.1110 | 44424032 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119046302 | T2 DI PARKWAY-MORAGA 21/116 RMV HRDT |  | PARKWAY-MORAGA | 021/116 | ICS | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-122.188459 | 37.8703 | ETL.5930 | 40597321 | Hardware-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 628 | Bay |  | Y - 11
119046303 | T2 DI PARKWAY-MORAGA 21/116 REPAINT | 44586170 | PARKWAY-MORAGA | 021/116 | ICS | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-122.188459 | 37.8703 | ETL.5930 | 40597321 | Structure-Steel | Paint/Coating | Other | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay
119046630 | T2 DI MRGA-SAN LEANDRO #1 8/58 RPR FOND |  | MORAGA-SAN LEANDRO #1 | 008/058 | ICQ | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-122.11931 | 37.7372 | ETL.2770 | 40857652 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  | ACRP
119046631 | T3 DI FULTON-CALISTOGA -17/4 BOND GUY |  | FULTON-CALISTOGA | '-017/004 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.478148 | 38.4674 | ETL.6880 | 44140231 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
119046750 | T3 DI ROUND MTN-CTWND #3 28/234 RPL INSS |  | ROUND MTN-COTTONWOOD #3 | 028/234 | 93I | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.950635 | 40.7775 | ETL.5650 | 40785142 | Insulator-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 508 | Table Mountain
119047101 | T2NT DI MRG-SN LNDR #1 8/57 RPR FOND |  | MORAGA-SAN LEANDRO #1 | 008/057 | ICQ | F | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-122.117419 | 37.7394 | ETL.2770 | 40804655 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  | ACRP
119047321 | DI MORAGA-SAN LEANDRO #1 10/67 RPR FOND |  | MORAGA-SAN LEANDRO #3 | 010/067 | ICQ | F | 2020_(4) TD tag on high spread line | [5 empty] | Central | WSIP | [6 empty] | '-122.136471 | 37.7212 | ETL.2790 | 40818439 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog 402
119047328 | DI MORAGA-SAN LEANDRO #3 9/65 RPR FOND |  | MORAGA-SAN LEANDRO #3 | 009/065 | ICQ | F | 2020_(4) TD tag on high spread line | [5 empty] | Central | WSIP | [6 empty] | '-122.134982 | 37.7233 | ETL.2790 | 40745921 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog 402
119047357 | T3 DI DRUM-RIO OSO #2 5/59 RPLC INSS | 31503652 | DRUM-RIO OSO #2 | 005/059 | 93K | E | 2020_(1a) PSPS |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.850964 | 39.2154 | ETL.1430 | 40894424 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Sacramento
119047571 | T2 DI FULTON-HOPLAND 013/003 RPL POLE | 31503986 | FULTON-HOPLAND | 013/003 | 70Y | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 | <90D | North Coast | WSIP | [6 empty] | '-122.854065 | 38.6572 | ETL.6890 | 40648705 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville
119047693 | T3 DI ROUND MTN-CTWD #3 29/241 RPR FOND | 43932111 | ROUND MTN-COTTONWOOD #3 | 029/241 | ICQ | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.959149 | 40.7672 | ETL.5650 | 40588925 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
119047990 | T3 DI GEYSERS #12-FULTON 15/66 RPR FOND | 44631264 | GEYSERS #12-FULTON | 015/066 | ICS | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.752571 | 38.6312 | ETL.4750 | 40814644 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville
119048211 | T3 DI EAGLE ROCK-CORTINA 18/88 RPL INSS | 31505513 | EAGLE ROCK-CORTINA | 018/088 | 93K | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Coast | WSIP | [8 empty] | ETL.1470 | 40884304 | Insulator-Steel | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Lakeville
119049439 | T3 EI DIABLO-GATES #1 22/089 RPR ROAD | 44298383 | DIABLO-GATES #1 | 022/089 | CHS | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR3 |  | South | WSIP | [6 empty] | '-120.732485 | 35.4961 | ETL.5960 | 40869355 | Road | Brush Fuel | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLR | Roads | Expense | 932 | Pismo Beach
119049470 | T3 EI DIABLO-GATES #1 22/89 RPL INSS | 31526471 | DIABLO-GATES #1 | 022/089 | 93K | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | South | WSIP | [6 empty] | '-120.732485 | 35.4961 | ETL.5960 | 40869355 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 17
119049540 | T3 DI DRUM-RIO OSO #2 8/84 RPR SPLS | 44332280 | DRUM-RIO OSO #2 | 008/084 | ICS | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.881811 | 39.1903 | ETL.1430 | 40761902 | Splice-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento
119049747 | DI PIT #1-COTTONWOOD 11/90 RPL SPLS | 43879413 | PIT #1-COTTONWOOD | 011/090 | ICS | E | 2020_(4) TD tag on high spread line | [5 empty] | North Valley | WSIP | [6 empty] | '-121.673215 | 40.8987 | ETL.5390 | 40607833 | Splice-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain
119049832 | T2 EI FORT ROSS-GUALALA 48/08 RPL POLE | 31492553 | GUALALA-MONTE RIO | 048/008 | 70Y | E | 2020_(2) High fire spread TD |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.387318 | 38.7183 | ETL.6980 | 40872364 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville
119049834 | T2 EI FORT ROSS-GUALALA 56/02 RPL POLE | 31492553 | GUALALA-MONTE RIO | 056/002 | 70Y | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Coast | WSIP | [6 empty] | '-123.507076 | 38.7502 | ETL.6980 | 40686563 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville
119051704 | T3 DI MIDDLE FORK-GLD HILL 6/53 RPR SHLW | 44332286 | MIDDLE FORK-GOLD HILL | 006/053 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.692485 | 39.0025 | ETL.5140 | 44552279 | Shield Wire / OPGW-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119051964 | T2 EI MIDWAY-WHIRLWIND 052/213 RMV NEST | 44516056 | MIDWAY-WHIRLWIND | 052/213 | ICS | E | 2020_(1b) Lines with special commitments |  |  |  | TR2 | WECC | South | WSIP | [6 empty] | '-118.691465 | 35.0698 | ETL.6030 | 40648048 | Structure-Steel | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Midway
119051965 | T2 EI MIDWAY-WHIRLWIND 052/214 RPLC INSS | 31514956 | MIDWAY-WHIRLWIND | 052/214 | 93K | E | 2020_(1b) Lines with special commitments |  |  |  | TR2 | WECC | South | WSIP | [6 empty] | '-118.6893721 | 35.0674 | ETL.6030 | 40794031 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Midway
119052227 | T2 DI PIT #1-COTTONWOOD 55/495 INST MRKS | 43879413 | PIT #1-COTTONWOOD | 055/495 | ICS | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.22057 | 40.4525 | ETL.5390 | 40759493 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain
119052356 | T2 DI EL DRD-MSR FLT #1 12/112 RPR FOND | 44332236 | ELDORADO-MISSOURI FLAT #1 | 012/112 | ICQ | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-120.804806 | 38.7149 | ETL.1530 | 40681898 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento
119052816 | T3 EI DIABLO-GATES #1 21/88 REPL INSS | 31526471 | DIABLO-GATES #1 | 021/088 | 93K | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | South | WSIP | [6 empty] | '-120.7361866 | 35.4914 | ETL.5960 | 40899077 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 17
119054538 | T3 SNEATH LANE-HMB ?2/4 RPR INSS | 44621946 | SNEATH LANE-HALF MOON BAY | ?002/004 | ICS | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.494878 | 37.5682 | ETL.7212 | 44384390 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  |  | MSB
119054869 | T2 DI BRDGVL-CTNWD 10/93 RPR OPGW | 43939216 | BRIDGEVILLE-COTTONWOOD | 010/093 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.456683 | 40.389 | ETL.1110 | 44423223 | Shield Wire / OPGW-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119056348 | T2 DI PARKWAY-MORAGA 10/59 RPLC DAMS | 44245151 | PARKWAY-MORAGA | 010/059 | ICS | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-122.23148 | 37.9973 | ETL.5930 | 40763001 | Damper-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  |  | JMLT
119057076 | T2 DI EAGLE ROCK-REDBUD :14/20 RPLC INSW | 31503989 | EAGLE ROCK-REDBUD | :014/020 | 93I | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.608891 | 38.9362 | ETL.1480 | 40629651 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Lakeville
119057301 | T2 DI WEIMAR #1 0/17 RPLC HRDD | 44362372 | WEIMAR #1 | 000/017 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-120.977205 | 39.034 | ETL.7560 | 40923014 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119057307 | T2 DI WEIMAR #1 0/17 REPULL GUY | 44332294 | WEIMAR #1 | 000/017 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-120.977205 | 39.034 | ETL.7560 | 40913169 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119059348 | T3 EI SBRNT-GRZZLY-CLRMNT #2 6/43 WSH IN |  | SOBRANTE-GRIZLY-CLARMNT #2+ | 006/043 | ICD | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.209237 | 37.851 | ETL.3750 | 40857800 | Insulator | Contaminated | Ground Wash |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 622 | Bay
119059370 | T3 DRUM-GRASS VLLY-WMR B21/465 RPL POLE | 31504330 | DRUM-GRASS VALLEY-WEIMAR | B021/465 | 70Y | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.998654 | 39.1775 | ETL.6760 | 40913019 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento
119059471 | T3 DI GEYSERS #12-FULTON 24/99 RPR FOND |  | GEYSERS #12-FULTON | 024/099 | ICQ | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.753242 | 38.5199 | ETL.4750 | 40870878 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville
119059474 | DI STLS-MLN SW ST-MCA #1 25/160 RPR STRT |  | STANISLAUS-MELONES SS-MANTECA #1+ | 025/160 | ICQ | E | 2020_(4) TD tag on high spread line | [5 empty] | Central | WSIP | [6 empty] | '-120.748795 | 37.9294 | ETL.3830 | 40856466 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - 22
119059477 | DI STLS-MLN SW ST-MCA #1 25/162 RPR STRT |  | STANISLAUS-MELONES SS-MANTECA #1+ | 025/162 | ICQ | E | 2020_(4) TD tag on high spread line | [5 empty] | Central | WSIP | [6 empty] | '-120.753763 | 37.9279 | ETL.3830 | 40596056 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - 22
119059996 | T3 DI DRUM-RIO OSO #1 7/75 RPR FOND | 44339678 | DRUM-RIO OSO #1 | 007/075 | ICQ | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.870217 | 39.198 | ETL.1420 | 40756207 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento
119059998 | T3NT DI DRUM-RIO OSO #1 7/75 INST MRKS | 44345617 | DRUM-RIO OSO #1 | 007/075 | ICS | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.870217 | 39.198 | ETL.1420 | 40756207 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento
119060141 | T2 DI ELK-GUALALA 41/09 RPL INSW | 31506140 | ELK-GUALALA | 041/009 | 93I | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.685355 | 39.067 | ETL.8410 | 40900605 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Lakeville
119060225 | T3 DI EGL RCK-FLTN-SLVRDO 9/37 RPR FOND |  | EAGLE ROCK-FULTON-SILVERADO | 009/037 | ICQ | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.741752 | 38.6162 | ETL.4392 | 41129339 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville
119060227 | T3 DI EGL RCK-FLTN-SLVRDO :0/1 RPR FOND |  | EAGLE ROCK-FULTON-SILVERADO | :000/001 | ICQ | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.761291 | 38.7405 | ETL.4392 | 41129397 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville
119060607 | T2 DI EAGLE ROCK-CORTINA :14/2 REPL POLE | 31503965 | EAGLE ROCK-CORTINA | :014/002 | 70Y | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.607624 | 38.9249 | ETL.1470 | 41176305 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC hold srdy |  |  |  | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville
119060678 | T3NT DI DRUM-SUMMIT #1 000/006 INST MRKW | 44345829 | DRUM-SUMMIT #1 | 000/006 | ICW | F | 2020_(1b) Lines with special commitments |  |  |  | TR3 | WECC | North Valley | WSIP | [6 empty] | '-120.761918 | 39.2548 | ETL.1440 | 44338092 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119060852 | T3NT DI DRUM-RIO OSO #2 00/09 REGRADE | 44356575 | DRUM-RIO OSO #2 | 000/009 | ICQ | F | 2020_(1a) PSPS |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.784973 | 39.2565 | ETL.1430 | 40866282 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento
119060905 | T3 DI SBRNT-GRZLY-CLRMT #2 6/39 RPR FOND | 44326313 | SOBRANTE-GRIZLY-CLARMNT #2+ | 006/039 | ICQ | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.199539 | 37.8609 | ETL.3750 | 40746118 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  | SVRPR
119061030 | T3NT DI TGR CRK-VLY SPRNGS 5/46 RPR FOND |  | TIGER CREEK-VALLEY SPRINGS | 005/046 | ICQ | F | 2020_(2) High fire spread TD |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-120.589465 | 38.4216 | ETL.5790 | 40811207 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - Prog 402
119061031 | DI DIVIDE-CABRILLO #1 011/136 RPR GYWW |  | DIVIDE-CABRILLO #1 | 011/136 | ICW | E | 2020_(4) TD tag on high spread line | [5 empty] | South | WSIP | [8 empty] | ETL.1380 | 44283834 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - 15
119061032 | T2NT DI SBRT-GRZLY-CLRMT#1 2/23 RPR FOND |  | SOBRNTE-GRIZZLY-CLARMNT #1+ | 002/023 | ICQ | F | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-122.186631 | 37.8798 | ETL.3740 | 40872983 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay
119061035 | T3 DI TIGER CREEK-ELECTRA 5/46 RMV STEP |  | TIGER CREEK-ELECTRA | 005/046 | ICQ | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-120.587925 | 38.423 | ETL.5780 | 40811161 | Hardware-Tower | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - 11
119061079 | T3 EI SBRNT-GRZZLY-CLRMNT #2 6/42 WSH IN |  | SOBRANTE-GRIZLY-CLARMNT #2+ | 006/042 | ICD | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.208075 | 37.852 | ETL.3750 | 40857842 | Insulator | Contaminated | Ground Wash |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 622 | Bay |  |  | SVRPR
119061232 | T3 DI DRUM-RIO OSO #2 004/053 RPL INSS | 31503652 | DRUM-RIO OSO #2 | 004/053 | 93K | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.840426 | 39.2214 | ETL.1430 | 40690865 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Sacramento
119061233 | T3 DI DRUM-RIO OSO #2 006/070 RPL INSS | 31503652 | DRUM-RIO OSO #2 | 006/070 | 93K | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.864024 | 39.2041 | ETL.1430 | 40633685 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Sacramento
119061712 | T2 EI WEIMAR #1 000/017 RPLC POLE | 31506502 | WEIMAR #1 | 000/017 | 70Y | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-120.977205 | 39.034 | ETL.7560 | 40913169 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento
119061768 | T2 EI WEIMAR #1 001/022 RPLC POLE | 31506502 | WEIMAR #1 | 001/022 | 70Y | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-120.973471 | 39.0313 | ETL.7560 | 40824441 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento
119061842 | T2 EI WEIMAR #1 001/025 RPR STRW | 44362373 | WEIMAR #1 | 001/025 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-120.97133 | 39.0304 | ETL.7560 | 40650014 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119061870 | T2 EI WEIMAR #1 001/027 RPL INSS | 31506503 | WEIMAR #1 | 001/027 | 93I | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-120.9696774 | 39.0297 | ETL.7560 | 40610576 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Sacramento
119061871 | T2 EI WEIMAR #1 001/027 INS DAMPER | 44362373 | WEIMAR #1 | 001/027 | ICW | E | 2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-120.969664 | 39.0297 | ETL.7560 | 40586055 | Damper-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119062818 | T3 DI IGNCIO-BOLINS #1 10/114 RPR CRSW | 31504329 | IGNACIO-BOLINAS #1 | 010/114 | 93E | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.662603 | 37.9709 | ETL.7140 | 40750704 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Lakeville
119063050 | T3 DI IGNCIO-BOLINS #1 10/114 RMV DEBRIS |  | IGNACIO-BOLINAS #1 | 010/114 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.662603 | 37.9709 | ETL.7140 | 40750704 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
119063069 | T3 DI DRUM-RIO OSO #2 007/079 RPL INSS | 31503652 | DRUM-RIO OSO #2 | 007/079 | 93K | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [8 empty] | ETL.1430 | 44308041 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Sacramento
119064030 | T3 DI TIGER CRK-VLY SPRNGS 5/45 RPR FOND |  | TIGER CREEK-VALLEY SPRINGS | 005/045 | ICQ | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-120.587791 | 38.4228 | ETL.5790 | 40805570 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - Prog 402
119064040 | T3 MONTE RIO-FORT ROSS 20/0B REPL PL | 31437439 | ETL.6979.POLE.WOOD | 020/000B | 70Y | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.094753 | 38.4843 | ETL.6979 | 44225239 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville
119065773 | DI GATES-PANOCHE #1 2/12 RPR FOND | 44341603 | GATES-PANOCHE #1 | 002/012 | ICQ | E | 2020_(1b) Lines with special commitments |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.146013 | 36.1682 | ETL.4720 | 40663918 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 10
119066694 | T3 DI EGL RCK-FLTN-SLVRD :000/4 RPR FOND |  | EAGLE ROCK-FULTON-SILVERADO | :000/004 | ICQ | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.759729 | 38.7298 | ETL.4392 | 40750668 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville
119067461 | T2 DI PARKWAY-MORAGA 11/66 REPL INSS | 31503747 | PARKWAY-MORAGA | 011/066 | 93K | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-122.217859 | 37.9801 | ETL.5930 | 40611760 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - 11
119067641 | T2 DI PARKWAY-MORAGA 11/67 RPR FOND |  | PARKWAY-MORAGA | 011/067 | ICQ | F | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-122.216353 | 37.9782 | ETL.5930 | 40662572 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  | EBMUD
119067873 | DI GATES-MUSTANG #1 6/30 RPR FOND | 44341601 | SPARE T-LINE RECORD | 006/030 | ICQ | E | 2020_(1b) Lines with special commitments | [5 empty] | South | WSIP | [6 empty] | '-120.016122 | 36.1848 | ETL.2604 | 40582480 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 11
119068399 | T3 GEYSERS #17-FULTON 3/16 REPL HARDWARE |  | GEYSERS #17-FULTON | 003/016 | ICS | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.802144 | 38.8015 | ETL.4770 | 40842366 | Hardware-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville
119068463 | T3 DI EAGLE RCK-FLTN-SLVRD 1/9 RPR FOND | 44326457 | EAGLE ROCK-FULTON-SILVERADO | 001/009 | ICQ | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.802166 | 38.8199 | ETL.4392 | 40869826 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville
119068861 | T3 DI SANTA FE GHRML TAP 0/1 RPLC INSS | 31506603 | SANTA FE GEOTHERMAL TAP | 000/001 | 93K | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Coast | WSIP | [8 empty] | ETL.4782 | 40609331 | Insulator-Steel | No Good/Out of Stdrd | Replace | CONS | CONS | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Lakeville
119069021 | T2 UKIAH-HOPLAND-CLVRDLE 13/12 RPR COND | 44610690 | UKIAH-HOPLAND-CLOVERDALE | 013/127 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.101489 | 39.0073 | ETL.4050 | 40669327 | Conductor-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
119069691 | DI STNSLS-MLNS MNTCA #1 26/169 RPR STRS |  | STANISLAUS-MELONES SS-MANTECA #1+ | 026/169 | ICS | E | 2020_(2) High fire spread TD | [5 empty] | Central | WSIP | [6 empty] | '-120.773529 | 37.922 | ETL.3830 | 40803334 | Structure-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - 22
119069693 | DI STNSLS-MLNS MNTCA #1 26/169 RPL SPLS | 44566007 | STANISLAUS-MELONES SS-MANTECA #1+ | 026/169 | ICS | E | 2020_(2) High fire spread TD | [5 empty] | Central | WSIP | [6 empty] | '-120.773529 | 37.922 | ETL.3830 | 40803334 | Splice-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - 22
119070232 | T3 DI MIDDLE FORK #1 3/54C RPLC HRDW | 44339029 | MIDDLE FORK #1 | 003/054C | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.638812 | 38.9959 | ETL.8405 | 42569707 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119070251 | T3 DI DRUM-RIO OSO #1 007/076 INST STEP | 44339678 | DRUM-RIO OSO #1 | 007/076 | ICQ | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.871402 | 39.1966 | ETL.1420 | 40820316 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento
119070474 | DI SBRNT-GRZLY-CLRMNT #2 3/30 RPR STRT |  | SOBRANTE-GRIZLY-CLARMNT #2+ | 003/030 | ICQ | E | 2020_(4) TD tag on high spread line | [5 empty] | Central | WSIP | [6 empty] | '-122.176264 | 37.8649 | ETL.3750 | 40608060 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay
119070840 | T2 VACA-SUISUN 9/71 RPR CRST | 44339850 | VACA-SUISUN | 009/071 | ICS | E | 2020_(2) High fire spread TD |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.043055 | 38.3221 | ETL.4070 | 40597218 | Crossarm-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento
119070846 | T2 VACA-SUISUN-JAMESON 9/71 RPL INSS | 31499779 | VACA-SUISUN-JAMESON | 009/071 | 93K | E | 2020_(2) High fire spread TD |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.0430679 | 38.3221 | ETL.4080 | 40623721 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Sacramento
119073187 | T3 DI GEYSERS #12-FULTN 009/040 RPR INSS | 44630990 | GEYSERS #12-FULTON | 009/040 | ICS | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.75988 | 38.7297 | ETL.4750 | 40637090 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville
119074322 | DI GATES-PANOCHE #1 0/3 RPR INSS | 44341662 | GATES-PANOCHE #1 | 000/003 | ICS | E | 2020_(1b) Lines with special commitments |  |  |  |  | WECC | South | WSIP | [8 empty] | ETL.4720 | 44402020 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  | Y - 10
119074484 | DI GATES-PANOCHE #1 0/3 RPR FOND | 44341603 | GATES-PANOCHE #1 | 000/003 | ICQ | E | 2020_(1b) Lines with special commitments |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.126384 | 36.1451 | ETL.4720 | 40651593 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 10
119074800 | DI GATES-PANOCHE #1 0/3 RPR STRT | 44341603 | GATES-PANOCHE #1 | 000/003 | ICQ | E | 2020_(1b) Lines with special commitments |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.126384 | 36.1451 | ETL.4720 | 40651593 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 10
119075662 | DI GATES-PANOCHE #1 1/6 RPR FOND | 44341603 | GATES-PANOCHE #1 | 001/006 | ICQ | E | 2020_(1b) Lines with special commitments |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.132941 | 36.1528 | ETL.4720 | 40814247 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 10
119075843 | T3 DI EGL RCK-FLTN-SLVRD 1/7 RPR FOND | 44326457 | EAGLE ROCK-FULTON-SILVERADO | 001/007 | ICQ | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.799363 | 38.8259 | ETL.4392 | 40813815 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville
119076057 | DI ATASCADERO-CAYUCOS 009/076 RPR GYWW | 44392213 | ATASCADERO-CAYUCOS | 009/076 | ICW | E | 2020_(4) TD tag on high spread line | [5 empty] | South | WSIP | [8 empty] | ETL.8480 | 44319783 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - Prog 401
119076058 | DI ATASCADERO-CAYUCOS 009/076 RPR GYWW | 44392218 | ATASCADERO-CAYUCOS | 009/076 | ICW | E | 2020_(4) TD tag on high spread line | [5 empty] | South | WSIP | [8 empty] | ETL.8480 | 44319784 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - Prog 401
119076059 | DI ATASCADERO-CAYUCOS 009/076 RPR GYWW | 44392284 | ATASCADERO-CAYUCOS | 009/076 | ICW | E | 2020_(4) TD tag on high spread line | [5 empty] | South | WSIP | [8 empty] | ETL.8480 | 44319785 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - Prog 401
119076280 | DI ATASCADERO-CAYUCOS 009/076 RPL CRSW | 31504668 | ATASCADERO-CAYUCOS | 009/076 | 93E | E | 2020_(4) TD tag on high spread line | [5 empty] | South | WSIP | [8 empty] | ETL.8480 | 44319784 | Crossarm-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Pismo Beach |  | Y - 12
119077871 | T3 DI EAGLE RCK-FLTN-SLVRD 5/26 RPL INSS | 31505662 | EAGLE ROCK-FULTON-SILVERADO | 005/026 | 93K | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.79536 | 37.7692 | ETL.4392 | 40842372 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Lakeville
119077873 | T3 DI EAGLE RCK-FLTN-SLVRD 5/26 RPR FOND | 44326457 | EAGLE ROCK-FULTON-SILVERADO | 005/026 | ICQ | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.795407 | 38.7692 | ETL.4392 | 40814650 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville
119078255 | T3 DI GEYSERS #17-FULTON 5/25 RPL INSS | 31505662 | GEYSERS #17-FULTON | 005/025 | 93K | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.79683 | 38.7723 | ETL.4770 | 40791331 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Lakeville
119080148 | T3 DI DRUM-GRS VLY-WMR 0/7 RMV BUTT | 44361666 | DRUM-GRASS VALLEY-WEIMAR | 000/007 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.761669 | 39.2563 | ETL.6760 | 44809295 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119080149 | T3 DI DRUM-GRS VLY-WMR 0/7 RPR SPLW | 44339676 | DRUM-GRASS VALLEY-WEIMAR | 000/007 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.761669 | 39.2563 | ETL.6760 | 44809295 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119080874 | T2 DI BAHIA-MORAGA 16/93 RPR FOND | 44245153 | BAHIA-MORAGA | 016/093 | ICS | E | 2020_(2) High fire spread TD |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-122.203898 | 37.9596 | ETL.4340 | 40740005 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 10 | EBMUD
119080990 | T3 WEST POINT-VALLEY SPRINGS 5/59 RPL PL | 31506822 | WEST POINT-VALLEY SPRINGS | 005/059 | 70Y | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-120.624538 | 38.3963 | ETL.8350 | 40579954 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor
119081013 | T2 DI PARKWAY-MORAGA 011/064 RPL INSS | 31526488 | PARKWAY-MORAGA | 011/064 | 93K | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-122.22211 | 37.9854 | ETL.5930 | 44768968 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  |  | EBMUD
119081112 | T3 WEST POINT-VALLEY SPRINGS 1/21 RPL PL | 31506820 | WEST POINT-VALLEY SPRINGS | 001/021 | 70Y | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-120.576977 | 38.4253 | ETL.8350 | 40803750 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor
119081209 | T3 DI DONNELLS-MI-WUK 4/3 RPLC INSW | 31504671 | DONNELLS-CURTIS | 004/003 | 93I | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-120.044861 | 38.1865 | ETL.1400 | 40670178 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Victor |  | Y - Prog 401
119081253 | T3 DI DRUM-GRASS VLY-WMR 2/46 RPR SPLW | 44339676 | DRUM-GRASS VALLEY-WEIMAR | 002/046 | ICW | E | 2020_(1a) PSPS |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.771911 | 39.2394 | ETL.6760 | 40693316 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119081265 | T3 DI EGL RCK-FLTN-SILVRD 19/81 RPL HRDT | 44326457 | EAGLE ROCK-FULTON-SILVERADO | 019/081 | ICQ | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.62029 | 38.5149 | ETL.4392 | 41129383 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville
119081266 | T3 DI EGL RCK-FLTN-SLVRD 19/81 RPL INSS | 31515212 | EAGLE ROCK-FULTON-SILVERADO | 019/081 | 92E | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.62037 | 38.5148 | ETL.4392 | 41129275 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Lakeville
119081290 | T3 DI MIDDLE FORK #1 1/21 RPR POLE | 44365338 | MIDDLE FORK #1 | 001/021 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.601286 | 39.0079 | ETL.8405 | 40664820 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119081294 | T3 DI DUM-GRS VLY-WMR 2/49 RPLC POLE | 31518244 | DRUM-GRASS VALLEY-WEIMAR | 002/049 | 70Y | E | 2020_(1a) PSPS |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.773734 | 39.2377 | ETL.6760 | 40756128 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento
119081383 | T3 DI FULTON-PUEBLO 036/183 RPR FOND | 44306536 | FULTON-PUEBLO | 036/183 | ICQ | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.644933 | 38.4972 | ETL.1600 | 40645131 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville
119081475 | T3NT DI WST PNT-VLY SPRN 1/26 RMV PL BUT | 44595070 | WEST POINT-VALLEY SPRINGS | 001/026 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-120.584396 | 38.4235 | ETL.8350 | 40579948 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor
119081477 | T3 DI WST PNT-VLY SPRNGS 1/26 REPL INSW | 31504741 | WEST POINT-VALLEY SPRINGS | 001/026 | 93I | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-120.584597 | 38.4229 | ETL.8350 | 40603542 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Victor
119081478 | DI MORRO BAY-DIABLO X7/033 RPLC INSS | 31507782 | MORRO BAY-DIABLO | X007/033 | 93K | E | 2020_(4) TD tag on high spread line | [5 empty] | South | WSIP | [6 empty] | '-120.801552 | 35.2982 | ETL.5260 | 40679556 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 4
119081489 | T3NT DI FULTON-PUEBLO 031/152 RMV DEBRIS |  | FULTON-PUEBLO | 031/152 | ICS | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.5503 | 38.4856 | ETL.1600 | 40656848 | Structure-Steel | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville
119081572 | T3 DI DRUM-GRS VLY-WMR 1/25 RPR SPLW | 44339676 | DRUM-GRASS VALLEY-WEIMAR | 001/025 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.758432 | 39.2485 | ETL.6760 | 40693452 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119081774 | T3 DI DEER CREEK-DRUM 004/106 RPR STRW | 44339658 | DEER CREEK-DRUM | 004/106 | ICW | E | 2020_(1a) PSPS |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.797361 | 39.2564 | ETL.6690 | 40822856 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119081866 | T3NT DI DRM-GRS VLY-WMR 7/181 RMV PL BUT | 44361666 | DRUM-GRASS VALLEY-WEIMAR | 007/181 | ICW | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.84619 | 39.1931 | ETL.6760 | 40664750 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119082157 | T3 DI DRM GRS VLL WEI 006/150 RPR SPLW | 44345839 | DRUM-GRASS VALLEY-WEIMAR | 006/150 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.830137 | 39.2076 | ETL.6760 | 40767243 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119082158 | T3NT DI DRM GRS VLL WEI 006/150 INS MRKW | 44364845 | DRUM-GRASS VALLEY-WEIMAR | 006/150 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.830137 | 39.2076 | ETL.6760 | 40767243 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119082160 | DI DONNELLS-MI-WUK 0/1 RPLC SPLS |  | DONNELLS-CURTIS | 000/001 | ICS | E | 2020_(2) High fire spread TD | [5 empty] | Central | WSIP | [6 empty] | '-120.034255 | 38.2458 | ETL.1400 | 44379625 | Splice-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - 40
119082167 | T2 DI SN LS OBSPO-SNT MR 10/176 RPL POLE | 31506798 | SAN LUIS OBISPO-SANTA MARIA (IDLE) | 010/176 | 70Y | E | 2020_(1b) Lines with special commitments |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-120.527107 | 35.1577 | ETL.9100 | 44191865 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Pismo Beach |  | Y - 5
119082168 | T2 DI SLO-SNT MAR 10/176 RMV PL BUTT |  | SAN LUIS OBISPO-SANTA MARIA (IDLE) | 010/176 | ICW | E | 2020_(1b) Lines with special commitments |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-120.527107 | 35.1577 | ETL.9100 | 44191865 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - 5
119082250 | T3 DI DRM GRASS-VLL WEI 006/163 RPL SPLW | 44345839 | DRUM-GRASS VALLEY-WEIMAR | 006/163 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.837226 | 39.2012 | ETL.6760 | 40822654 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119082252 | T3NT DI DRM-GRSS VLLY WEI 6/163 INS MRKW | 44364845 | DRUM-GRASS VALLEY-WEIMAR | 006/163 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.837226 | 39.2012 | ETL.6760 | 40822654 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119082514 | T2 DI FRT RSS-GLA-GLA 57/3 RPR GYWW |  | GUALALA-MONTE RIO | 057/003 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.515304 | 38.765 | ETL.6980 | 40661492 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
119082735 | T2 DI FRT RSS-GLALA-GLALA 41/6 RPR GYWW |  | GUALALA-MONTE RIO | 041/006 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.308692 | 38.6623 | ETL.6980 | 40821477 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
119082763 | T3NT DI DRM-GRSS VLLY-WMR 8/209 INS MRKW | 44364845 | DRUM-GRASS VALLEY-WEIMAR | 008/209 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.860133 | 39.1808 | ETL.6760 | 40824298 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119082765 | T3NT DI DRM-GRS VLY-WMR 8/209 RMV PL BUT | 44364845 | DRUM-GRASS VALLEY-WEIMAR | 008/209 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.860133 | 39.1808 | ETL.6760 | 40824298 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119082766 | T3 DI DRM-GRSS VLLY-WMR 8/209 RPR INSW | 44345839 | DRUM-GRASS VALLEY-WEIMAR | 008/209 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.860138 | 39.1808 | ETL.6760 | 40853538 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119082769 | T3 DI DRM-GRSS VLLY-WEI 9/215 RPR GYWW | 44361667 | DRUM-GRASS VALLEY-WEIMAR | 009/215 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.864528 | 39.1766 | ETL.6760 | 44178361 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119082809 | T3 DI MRGA-SN LNDRO #1 6/44 RPR FOND |  | MORAGA-SAN LEANDRO #1 | 006/044 | ICQ | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.117688 | 37.7663 | ETL.2770 | 40745881 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  | ACRP
119082971 | T3 DI CRESTA-RIO OSO 19/156 RPR FOND |  | CRESTA-RIO OSO | 019/156 | ICQ | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.484984 | 39.6938 | ETL.4590 | 40910169 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
119082974 | T3 DI DRM-GRS VLY-WMR 2/50 RPLS SPLW | 44345839 | DRUM-GRASS VALLEY-WEIMAR | 002/050 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.774035 | 39.2375 | ETL.6760 | 40853527 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119083011 | T2 DI ELK-GUALALA 53/6 RPR GROUND WIREW | 44610591 | ELK-GUALALA | 053/006 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.674224 | 38.9098 | ETL.8410 | 40820744 | Ground Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
119083075 | T2 DI CRTNA-MNDCN#1 47/229 RPR FOUND |  | CORTINA-MENDOCINO #1 | 047/229 | ICQ | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.958405 | 39.1934 | ETL.1330 | 40870093 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville
119083129 | T2 DI ELK-GUALALA 59/2 COMPLETED | 31506142 | ELK-GUALALA | 059/002 | 93E | E | 2020_(2) High fire spread TD |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.591298 | 38.869 | ETL.8410 | 40684541 | Crossarm-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Lakeville
119083161 | T3 DI KILARC-CEDAR CREEK 8/196 RPLS SPLW | 43939119 | KILARC-CEDAR CREEK | 008/196 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.984632 | 40.7361 | ETL.7290 | 40845369 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119083162 | T3NT DI KILARC-CDR CREK 8/196 INST MRKW | 43939119 | KILARC-CEDAR CREEK | 008/196 | ICW | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.984653 | 40.7361 | ETL.7290 | 40817416 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119083174 | T2 DI FRT RSS-GLALA-GLALA 49/0 RPR GYWW |  | GUALALA-MONTE RIO | 049/000 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.393641 | 38.72 | ETL.6980 | 40587389 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
119083182 | T3 DI PTTSBRG-SAN MATEO 12/51 RPR FOUND | 44623139 | PITTSBURG-SAN MATEO | 012/051 | ICQ | F | 2020_(2) High fire spread TD |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-121.886554 | 37.864 | ETL.5463 | 40819688 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 13
119083188 | T2 DI FRT RSS-GLALA-GLALA 48/13 PRP GYWW |  | GUALALA-MONTE RIO | 048/013 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.393053 | 38.7182 | ETL.6980 | 40648493 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
119083221 | T2 DI FULTON-PUEBLO 38/194 RPLC INSS | 31430878 | FULTON-PUEBLO | 038/194 | 93K | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.675248 | 38.4967 | ETL.1600 | 40779344 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Lakeville
119083222 | T2 DI EGL RCK-FLTN-SLVD 38/194 RPLC INSS | 31515212 | EAGLE ROCK-FULTON-SILVERADO | 038/194 | 92E | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.67503 | 38.497 | ETL.4392 | 40779346 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Lakeville
119083223 | T2 DI FULTON-PUEBLO 38/194 RPR FOND |  | FULTON-PUEBLO | 038/194 | ICQ | E | 2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.67506 | 38.497 | ETL.1600 | 40750539 | Foundation/Concrete-Tower | Earth Covered Tower | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville
119083250 | T3 DI DEER CREEK-DRUM 1/23 BOND HARDWARE | 44345900 | DEER CREEK-DRUM | 001/023 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.839196 | 39.2856 | ETL.6690 | 40590222 | Insulator Bond Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119083255 | T3 DI IGNACIO-BOLINAS #1 004/04 RPR SPLW |  | IGNACIO-BOLINAS #1 | 004/044 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.598813 | 38.0483 | ETL.7140 | 40657316 | Splice-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
119083257 | T3 DI DRM-GRSS VLLY-WEI 009/232 RPL SPLW | 44345839 | DRUM-GRASS VALLEY-WEIMAR | 009/232 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.874621 | 39.1666 | ETL.6760 | 40822662 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119083311 | T3 DI DEER CREEK-DRUM 2/67 RMV POLE BUTT | 44345900 | DEER CREEK-DRUM | 002/067 | ICW | E | 2020_(1a) PSPS |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.823692 | 39.2634 | ETL.6690 | 40597182 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119083472 | T3 DI KILARC-CEDAR CREEK 11/247 RPR SPLW | 43939119 | KILARC-CEDAR CREEK | 011/247 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.959539 | 40.7661 | ETL.7290 | 44175308 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119083473 | T3 DI KILARC-CEDAR CRK 11/247 RMV DEBRIS | 43939119 | KILARC-CEDAR CREEK | 011/247 | ICW | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.959539 | 40.7661 | ETL.7290 | 44175308 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119083477 | T3 DI KILARC-CEDAR CRK 11/251 RPR POLE | 43939119 | KILARC-CEDAR CREEK | 011/251 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.95717 | 40.7689 | ETL.7290 | 40600840 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119083478 | T3 DI KILARC-CEDAR CRK 11/251 RMV BUTT | 43939119 | KILARC-CEDAR CREEK | 011/251 | ICW | E | 2020_(4b) On structure in bucket 4 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.95717 | 40.7689 | ETL.7290 | 40600840 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119083479 | T3 DI KILARC-CEDAR CRK 11/251 RPR SPLW | 43939119 | KILARC-CEDAR CREEK | 011/251 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.95717 | 40.7689 | ETL.7290 | 40600840 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119083602 | T3 DI DRM-GRSS VLY-WEI 11/256 REFRAME | 31504765 | DRUM-GRASS VALLEY-WEIMAR | 011/256 | 93E | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.892147 | 39.1537 | ETL.6760 | 40853610 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Sacramento
119083603 | T3 DI DRM-GRSS VLY-WEI 11/256 RMV VEGN |  | DRUM-GRASS VALLEY-WEIMAR | 011/256 | HNA | E | 2020_(3) On high spread structure |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.89217 | 39.1538 | ETL.6760 | 40824368 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Sacramento
119083648 | T3 DI RND MTN-CTTNWD #3 331/264 RPL HRWT | 43932111 | ROUND MTN-COTTONWOOD #3 | 031/264 | ICQ | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.980338 | 40.7418 | ETL.5650 | 40755441 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
119083652 | T3 DI RND MTN-CTTNWD #3 331/264 RPL INSS | 31504993 | ROUND MTN-COTTONWOOD #3 | 031/264 | 93K | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.98013 | 40.7419 | ETL.5650 | 40785134 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain
119083662 | T3 DI FULTON-PUEBLO 34/174 RPL INSS | 31505500 | FULTON-PUEBLO | 034/174 | 92E | E | 2020_(2) High fire spread TD |  |  | Likely MAT error - delink to correct | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.613722 | 38.4972 | ETL.1600 | 40796382 | Insulator-Steel | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Lakeville
119083664 | T3 DI EGL RCK-FLTN-SLVDO 34/174 RPL INSS | 31515212 | EAGLE ROCK-FULTON-SILVERADO | 034/174 | 92E | E | 2020_(2) High fire spread TD |  |  | Likely MAT error - delink to correct | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.61378 | 38.4972 | ETL.4392 | 40796384 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Lakeville
119083788 | T2 DI FT RSS-GLA-GLA 58/5 RPR GYWW |  | GUALALA-MONTE RIO | 058/005 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.514383 | 38.7801 | ETL.6980 | 40750323 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
119083796 | T3 DI FRCH MDWS-MDDL FRK 12/220 RPR POLE | 44345881 | FRENCH MEADOWS-MIDDLE FORK | 012/220 | ICW | E | 2020_(1a) PSPS |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.59986 | 39.0093 | ETL.6870 | 40603361 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119083797 | T3NT DI FRH MDS-ML FRK 12/220 RMV PL BUT | 44365647 | FRENCH MEADOWS-MIDDLE FORK | 012/220 | ICW | F | 2020_(1a) PSPS |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.59986 | 39.0093 | ETL.6870 | 40603361 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119083823 | T2 DI FT RSS-GLA-GLA 41/000 RPR GYWW |  | GUALALA-MONTE RIO | 041/000 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.311665 | 38.6556 | ETL.6980 | 40587370 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
119083825 | T2 DI PHILO JCT-ELK-ELK 5/6 RPR STRW | 44610684 | PHILO JCT-ELK | 005/006 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.232137 | 39.0626 | ETL.7780 | 40826126 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
119084502 | T3 DI DONNELLS-MI-WUK 5/5 RPR INSW | 44623205 | DONNELLS-CURTIS | 005/005 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-120.060762 | 38.1793 | ETL.1400 | 40794327 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog 401
119084504 | T3 DI DONNELLS-MI-WUK 5/5 RMV PLE BUTT | 44623206 | DONNELLS-CURTIS | 005/005 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-120.060762 | 38.1793 | ETL.1400 | 40763958 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  |  | FERC
119084505 | T3NT DI DONNELLS-MI-WUK 5/5 INST MRKW | 44623207 | DONNELLS-CURTIS | 005/005 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-120.060762 | 38.1793 | ETL.1400 | 40763958 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog 401
119084508 | T3 DI TIGR CRK-ELCTRA 0/1 RPR FOND | 44467326 | TIGER CREEK-ELECTRA | 000/001 | ICQ | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-120.493042 | 38.4514 | ETL.5780 | 40594677 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - 12 | BLM
119084516 | T3 DI DONNELLS-MI-WUK 6/3 RPL INSW | 31506059 | DONNELLS-CURTIS | 006/003 | 93I | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-120.077285 | 38.173 | ETL.1400 | 40670182 | Insulator-Wood | No Good/Out of Stdrd | Replace | APPR | APPR | Awaiting Supervisor Approval | Not Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Victor |  | Y - Prog 401
119084518 | T3 DI DONNELLS-MI-WUK 6/3 RMV DEBRIS | 44623208 | DONNELLS-CURTIS | 006/003 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-120.077853 | 38.1729 | ETL.1400 | 40643189 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  |  | FERC
119084535 | DISTRIBUTION SLO-SM RPL STRW |  | SAN LUIS OBISPO-SANTA MARIA (IDLE) | 008/157 | 70Y | E | 2020_(1b) Lines with special commitments | [5 empty] | South | WSIP | [6 empty] | '-120.528655 | 35.1725 | ETL.9100 | 44191321 | Structure-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLX | Pole Program | Capital | 372 | Pismo Beach |  | Y - 5
119084536 | T3NT DI MIDDLEFORK #1 7/105 INST MRKW | 44365334 | MIDDLE FORK #1 | 007/105 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.711017 | 39.0029 | ETL.8405 | 40810143 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119084544 | T2 DI OLEUM G #1 5/34 BURIED STUB | 44621447 | OLEUM-G #1 | 005/034 | ICS | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-122.24541 | 37.9899 | ETL.3150 | 40761781 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - Prog 402
119084546 | T3 DI MIDDLEFORK #1 8/125 BOND GUY | 44365338 | MIDDLE FORK #1 | 008/125 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.736021 | 39.0036 | ETL.8405 | 40669382 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119084547 | T3 DI MIDDLEFORK #1 8/125 RMV DEBRIS | 44365334 | MIDDLE FORK #1 | 008/125 | ICW | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.736021 | 39.0036 | ETL.8405 | 40669382 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119084548 | T2 DI DIABLO-MESA 15/66 RPL INSS | 31503711 | DIABLO-MESA | 015/066 | 93K | E | 2020_(2) High fire spread TD |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-120.671748 | 35.2266 | ETL.4620 | 40847722 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 12
119084563 | T3 DI DRM-GRSS VLY-WMAR 3/89 RPL POLE | 31506387 | DRUM-GRASS VALLEY-WEIMAR | 003/089 | 70Y | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.798286 | 39.2251 | ETL.6760 | 40669964 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento
119084577 | T3 DI DRM-GRSS VLY-WMAR 0/8 BOND GUY | 44361667 | DRUM-GRASS VALLEY-WEIMAR | 000/008 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.760374 | 39.2554 | ETL.6760 | 40874723 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119084610 | T3 DI KILARC-CEDAR CREEK 3/78 RMV STUB | 43939119 | KILARC-CEDAR CREEK | 003/078 | ICW | E | 2020_(3) On high spread structure |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.935372 | 40.6975 | ETL.7290 | 40876497 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119084611 | T3 DI KILARC-CEDAR CREEK 3/78 RPR SPLW | 43939119 | KILARC-CEDAR CREEK | 003/078 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.935372 | 40.6975 | ETL.7290 | 40876497 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119084614 | T3 DI GYSRS #3-CLOVERDALE 8/92 RPR GYWW | 44580896 | GEYSERS #3-CLOVERDALE | 008/092 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.948579 | 38.8009 | ETL.1650 | 40594505 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
119084619 | T3 DI MRGA-CSTRO VLLY 5/23 RPR STRT | 44623422 | MORAGA-CASTRO VALLEY | 005/023 | ICQ | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.104971 | 37.8044 | ETL.5250 | 40654420 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 9 | EBMUD
119084631 | T3 DI MRGA-CSTRO VLLY 5/23 RPL HRDT | 44623422 | MORAGA-CASTRO VALLEY | 005/023 | ICQ | F | 2020_(2) High fire spread TD |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-122.104971 | 37.8044 | ETL.5250 | 40654420 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 9 | EBMUD
119084646 | T2 DI MORRO BAY-MSA 19/86 RPL INSS | 31501671 | MORRO BAY-MESA | 019/086 | 93K | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-120.606856 | 35.1832 | ETL.5290 | 40838469 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 15
119084648 | T2 DI DIABLO-MSA 19/86 RPL INSS | 31503711 | DIABLO-MESA | 019/086 | 93K | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-120.606856 | 35.1832 | ETL.4620 | 40838471 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 12
119084653 | T3 DI SRNTE-GZLY-CLRMT#2 A1/10 RPL INSS | 31511124 | SOBRANTE-GRIZLY-CLARMNT #2+ | A001/010 | 93K | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.226721 | 37.8863 | ETL.3750 | 40622389 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  |  | Tilden RP
119084656 | T3NT DI SRNTE-GLY-CLT T#1 A1/10 RPR FOND | 44624393 | SOBRNTE-GRIZZLY-CLARMNT #1+ | A001/010 | ICQ | F | 2020_(2) High fire spread TD |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-122.226805 | 37.8862 | ETL.3740 | 40581836 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 13
119084734 | T3 DI DRM-GRSS VLY-WMAR B17/386 RPL STRW | 31506387 | DRUM-GRASS VALLEY-WEIMAR | B017/386 | 70Y | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.9653 | 39.1328 | ETL.6760 | 40814230 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento
119084803 | T3 DI CRESTA-RIO OSO 18/149 RPR FOND |  | CRESTA-RIO OSO | 018/149 | ICQ | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.483116 | 39.7053 | ETL.4590 | 40910164 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
119084804 | T3 DI CRESTA-RIO OSO 18/149 RPL INSS | 31500129 | CRESTA-RIO OSO | 018/149 | 93K | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.504838 | 39.6623 | ETL.4590 | 40919903 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain
119084969 | T3 DI DEER CREEK-DRUM 0/1 RMV BUTT | 44345900 | DEER CREEK-DRUM | 000/001 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.843824 | 39.2983 | ETL.6690 | 40590220 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119085060 | T3 DI DEER CREEK-DRUM 0/1 RPR INSW | 44345900 | DEER CREEK-DRUM | 000/001 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.843881 | 39.2982 | ETL.6690 | 40615660 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119085113 | T2 DI ELK-GUALALA 56/8 RPR GYWW |  | ELK-GUALALA | 056/008 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.625267 | 38.8934 | ETL.8410 | 40871843 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
119085120 | T3 DI MIDDLEFORK #1 1/20 REMV BUTT | 44361892 | MIDDLE FORK #1 | 001/020 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.600654 | 39.0086 | ETL.8405 | 40660027 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119085121 | T3 DI MIDDLEFORK #1 1/20 CANCEL | 44361892 | MIDDLE FORK #1 | 001/020 | ICW | F | 2020_(2) High fire spread TD |  |  | CANCEL/CNCL | TR3 |  | North Valley | WSIP | [6 empty] | '-120.600654 | 39.0086 | ETL.8405 | 40660027 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119085129 | T3 DI DESABL-CENTERVI 3/37A RPR STRW | 44356201 | DESABLA-CENTERVILLE | 003/037A | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.641054 | 39.8229 | ETL.6720 | 40700256 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119085250 | T2 DI FORT ROSS-GUALALA 47/6 RPR GYWW |  | GUALALA-MONTE RIO | 047/006 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.368614 | 38.7191 | ETL.6980 | 40821493 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
119085321 | T3 DI MORRO BAY-MESA 26/114 RPLC INSS | 31501671 | MORRO BAY-MESA | 026/114 | 93K | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | South | WSIP | [6 empty] | '-120.520641 | 35.1138 | ETL.5290 | 40792005 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 15
119085325 | T3 DI DIABLO-MESA 26/114 RPLC INSS | 31510098 | DIABLO-MESA | 026/114 | 93K | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | South | WSIP | [6 empty] | '-120.520641 | 35.1138 | ETL.4620 | 40792007 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 13
119085435 | T3 DI SOBRANTE R #1 3/25 RPR FOND | 44624391 | SOBRANTE-R #1 | 003/025 | ICQ | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.272951 | 37.9171 | ETL.3770 | 40746157 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  | Tilden RP
119085451 | T3NT DI DRM-GSS VLY-WEI 4/92 RMV PL BUTT | 44371581 | DRUM-GRASS VALLEY-WEIMAR | 004/092 | GAR | F | 2020_(2) High fire spread TD |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.799606 | 39.2233 | ETL.6760 | 40589534 | Structure-Wood | Rotten | Stub | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 586 | Sacramento
119085677 | T3 DI DESABLA-CNTRVLLE 003/040B RPR GYWW | 44356201 | DESABLA-CENTERVILLE | 003/040 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.64257 | 39.8187 | ETL.6720 | 42578833 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119086150 | T3NT DI DESABLA-CNTRVILLE 3/40B RMV BUTT |  | DESABLA-CENTERVILLE | 003/040 | ICW | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.64257 | 39.8187 | ETL.6720 | 42578833 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119086214 | T2NT DI CRTN-MENDCINO #1 52/256 RPR FOND |  | CORTINA-MENDOCINO #1 | 052/256 | ICQ | F | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.060306 | 39.2042 | ETL.1330 | 40819332 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville
119086574 | T3 DI DONNELLS-MI-WUK 005/007 RPL POLE | 31506668 | DONNELLS-CURTIS | 005/007 | 70Y | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-120.065563 | 38.1776 | ETL.1400 | 44922055 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 40 | USFS
119086657 | T3 DI DESABLA-CENTERVILLE 3/40C RPR GYWW | 44356201 | DESABLA-CENTERVILLE | 003/040C | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.642608 | 39.8187 | ETL.6720 | 42578834 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119086716 | T3NT DI DESABLA-CNTERVLLE 3/40C RMV BUTT |  | DESABLA-CENTERVILLE | 003/040C | ICW | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.642608 | 39.8187 | ETL.6720 | 42578834 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119086719 | T3 DI DESABLA-CNTERVLLE 3/40C RPR STRW | 44356201 | DESABLA-CENTERVILLE | 003/040C | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.642608 | 39.8187 | ETL.6720 | 42578834 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119086864 | T3 DI DONNELLS-MI-WUK 005/007 RPL POLE | 31506668 | DONNELLS-CURTIS | 005/007 | 70Y | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-120.065563 | 38.1776 | ETL.1400 | 44922056 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 40 | USFS
119087047 | T3 DI ATASCADERO-CAYUCOS 3/34 RPL POLE | 31505562 | ATASCADERO-CAYUCOS | 003/034 | 70Y | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | South | WSIP | [6 empty] | '-120.732339 | 35.4645 | ETL.8480 | 40820812 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Pismo Beach |  | Y - 12
119087084 | T2 DI FORT ROSS-GUALALA 49/8 RPR GYWW |  | GUALALA-MONTE RIO | 049/008 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.400986 | 38.7214 | ETL.6980 | 40860968 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
119087274 | T2 DI FORT ROSS-GUALALA 31/9 RPR GYWW |  | GUALALA-MONTE RIO | 031/009 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.263887 | 38.5549 | ETL.6980 | 40876070 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
119087548 | T3 DI KILARC-DESCHUTES 0/11 RMV DEBRIS | 43930440 | KILARC-DESCHUTES | 000/011 | ICW | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.874123 | 40.6709 | ETL.7300 | 40676461 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Released
119087572 | T3 DI DESABLA-CENTERVILLE 000/2 RPL SPLW | 44356201 | DESABLA-CENTERVILLE | 000/002 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.630873 | 39.8674 | ETL.6720 | 40659712 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119087603 | T3 DI DESABLA-CENTERVILLE 0/2 RMV BUTT | 44356201 | DESABLA-CENTERVILLE | 000/002 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.630873 | 39.8674 | ETL.6720 | 40659712 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119087623 | T3 DI KILARC-DESCHUTES 0/11 REPL CRSW | 31504926 | KILARC-DESCHUTES | 000/011 | 93E | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.874123 | 40.6709 | ETL.7300 | 40676461 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  | Released
119087890 | T2 DI KONOCTI-MIDDLETOWN 13/3 RPR GYWW | 44610651 | KONOCTI-MIDDLETOWN | 013/003 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.591673 | 38.7654 | ETL.6380 | 40666996 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
119087897 | T2 DI KONOCTI-MIDDLETOWN 13/3 RPR STRW | 44610651 | KONOCTI-MIDDLETOWN | 013/003 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.591673 | 38.7654 | ETL.6380 | 40666996 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
119087930 | T2 DI KONOCTI-MIDDLETOWN 13/3 RPLC HRDW | 44610651 | KONOCTI-MIDDLETOWN | 013/003 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.591673 | 38.7654 | ETL.6380 | 40666996 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
119088059 | T3 DI DESABLA-CNTRVLL 4/57 RPR SPLW | 44356201 | DESABLA-CENTERVILLE | 004/057 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.650768 | 39.8002 | ETL.6720 | 44324212 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119088152 | T3 DI FULTON-PUEBLO 027/129 RPL INSS | 31505500 | FULTON-PUEBLO | 027/129 | 92E | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.473851 | 38.4908 | ETL.1600 | 40884574 | Insulator-Steel | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Lakeville
119088468 | T3 DI SOBRANTE- ""G"" #1 3/21 RPR FOND | 44624390 | SOBRANTE-"G" #1 | 003/021 | ICQ | F | 2020_(2) High fire spread TD |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-122.265319 | 37.9153 | ETL.3720 | 40581007 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 9
119088469 | T3 DI TMBLR-SLO 45/255 RPR SPLS |  | TEMBLOR-SAN LUIS OBISPO | 045/255 | ICS | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | South | WSIP | [6 empty] | '-120.461633 | 35.3653 | ETL.3960 | 40744735 | Splice-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Pismo Beach |  | Y - 18
119088482 | T3 DI TMBLR-SLO 54/301 RPR FOND | 44346363 | TEMBLOR-SAN LUIS OBISPO | 054/301 | ICQ | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | South | WSIP | [6 empty] | '-120.58198 | 35.283 | ETL.3960 | 40585669 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Pismo Beach |  | Y - Prog 402
119088581 | T3 DI MORAGA-OAKLAND #1 3/22 RPL INSS | 31504785 | MORAGA-OAKLAND #1 | 003/022 | 93K | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.204736 | 37.8227 | ETL.2720 | 40727887 | Insulator-Steel | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay
119088586 | T3NT DI MORAGA-OAKLAND #1 3/22 INST MRKS |  | MORAGA-OAKLAND #1 | 003/022 | ICS | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-122.204736 | 37.8227 | ETL.2720 | 40687322 | Marker (i.e. signs)-Steel | No Good/Out of Stdrd | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Bay
119088588 | T3 DI MRAGA-SAN LEANDRO #1 5/40 RMV STEP |  | MORAGA-SAN LEANDRO #1 | 005/040 | ICQ | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.124378 | 37.7785 | ETL.2770 | 40609137 | Hardware-Tower | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  | ACRP
119088660 | T3NT DI FULTON-CALSTGA 8/7 RMV PL BUTT | 44597303 | FULTON-CALISTOGA | :008/007 | ICW | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.604341 | 38.7085 | ETL.6880 | 40905734 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
119088661 | T3 DI SLO-OCEANO 13/61 RPR FOND | 44346362 | SAN LUIS OBISPO-OCEANO | 013/061 | ICQ | F | 2020_(2) High fire spread TD |  |  |  | TR3 |  | South | WSIP | [6 empty] | '-120.501188 | 35.1112 | ETL.3530 | 40585566 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Pismo Beach |  | Y - 12
119088667 | T3 DI DRUM-GRSS VLY-WMR B17/383 RPL POLE | 31506387 | DRUM-GRASS VALLEY-WEIMAR | B017/383 | 70Y | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.964024 | 39.1307 | ETL.6760 | 40757030 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento
119088678 | T3 DI COLGATE-ALLEGHANY 5/146 REPL POLE | 31507442 | COLGATE-ALLEGHANY | 005/146 | 70Y | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.093931 | 39.3363 | ETL.6470 | 40817333 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento
119088712 | T2 DI ELK-GLALA 54/009 INS GROUND WASH | 44610595 | ELK-GUALALA | 054/009 | ICD | E | 2020_(2) High fire spread TD |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.653609 | 38.9058 | ETL.8410 | 40894863 | Insulator | Contaminated | Ground Wash | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 622 | Lakeville
119088716 | T3 DI SANTA FE GEOTHERMAL 000/3 RPR FOND |  | SANTA FE GEOTHERMAL TAP | 000/003 | ICQ | F | 2020_(4) TD tag on high spread line |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.746969 | 38.7871 | ETL.4782 | 40659183 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville
119088820 | T3 DI PTTSBRG-SAN MATEO 12/50 RPR FOND | 44623139 | PITTSBURG-SAN MATEO | 012/050 | ICQ | F | 2020_(2) High fire spread TD |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-121.886021 | 37.8655 | ETL.5463 | 40760262 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 13
119088825 | T2 DI ELK-GUALALA 054/008 GRD WAS INSU | 44610595 | ELK-GUALALA | 054/008 | ICD | E | 2020_(2) High fire spread TD |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.654891 | 38.9055 | ETL.8410 | 40897367 | Insulator | Contaminated | Ground Wash | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 622 | Lakeville
119088860 | T3 DI MRGA-SN LNDRO #1 6/49 RPR FOND |  | MORAGA-SAN LEANDRO #1 | 006/049 | ICQ | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.113987 | 37.7576 | ETL.2770 | 40861001 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  | ACRP
119088891 | T2 DI ELK-GUALALA 056/010 RPL INSW | 31506140 | ELK-GUALALA | 056/010 | 93I | E | 2020_(2) High fire spread TD |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.623769 | 38.8924 | ETL.8410 | 40641076 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Lakeville
119088892 | T3 DI DRUM-RIO OSO #1 006/068 RPL SPLS | 44339679 | DRUM-RIO OSO #1 | 006/068 | ICS | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.861616 | 39.2076 | ETL.1420 | 40866011 | Splice-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento
119088957 | T3 DI IGNACIO-BOLINAS #1 2/32 RPR POLE |  | IGNACIO-BOLINAS #1 | 002/032 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.583547 | 38.0691 | ETL.7140 | 40762994 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
119088959 | DI DIVIDE-CABRILLO #2 006/076 RPR STRW |  | DIVIDE-CABRILLO #2 | 006/076 | ICW | E | 2020_(4) TD tag on high spread line | [5 empty] | South | WSIP | [8 empty] | ETL.1370 | 44283610 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach
119091224 | T2NT DI PHILO JCT-ELK 010/000 INS MRKW |  | PHILO JCT-ELK | 010/000 | ICW | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.293795 | 39.0272 | ETL.7780 | 40614228 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
119091225 | T2 DI PHILO JCT-ELK 010/000 RPR STRW | 44610684 | PHILO JCT-ELK | 010/000 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.293795 | 39.0272 | ETL.7780 | 40614228 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
119091884 | T3 DI SOBRANTE-""G"" #1 2/18 RPR FOND | 44624390 | SOBRANTE-"G" #1 | 002/018 | ICQ | F | 2020_(2) High fire spread TD |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-122.258275 | 37.9134 | ETL.3720 | 40857867 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 9
119091999 | T3 DI MORRO BY-SLR STA #1 21/91 RPR FOND | 44346367 | MORRO BAY-SOLAR SW STA #1 | 021/091 | ICQ | F | 2020_(4) TD tag on high spread line |  |  |  | TR3 |  | South | WSIP | [6 empty] | '-120.477886 | 35.3557 | ETL.5300 | 40587537 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Pismo Beach |  | Y - Prog 402
119092245 | T3 DI TMBLR-SLO 51/287 RPLC INSS | 31514502 | TEMBLOR-SAN LUIS OBISPO | 051/287 | 93K | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | South | WSIP | [6 empty] | '-120.297619 | 35.3696 | ETL.3960 | 40833915 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach
119093764 | T3 DI FULTON-CALISTOGA :6/9 RPR SHLW | 44597303 | FULTON-CALISTOGA | :006/009 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.59049 | 38.6807 | ETL.6880 | 44922946 | Shield Wire / OPGW-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
119093826 | T3NT DI FULTON-CALISTOGA :6/9 RMV DEBRIS | 44597303 | FULTON-CALISTOGA | :006/009 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.59049 | 38.6807 | ETL.6880 | 44922946 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
119094029 | DI GATES-PANOCHE #1 001/008 INST HRDT | 44361571 | GATES-PANOCHE #1 | 001/008 | ICQ | E | 2020_(1b) Lines with special commitments |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.137272 | 36.1579 | ETL.4720 | 40863626 | Hardware-Tower | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 10
119094122 | T2 DI FORT ROSS-GUALAL 56/11 INST DAMPRS |  | GUALALA-MONTE RIO | 056/011 | ICW | E | 2020_(4b) On structure in bucket 4 |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.51306 | 38.7601 | ETL.6980 | 40584669 | Damper-Wood | Missing | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
119094123 | T3 DI TMBLR-SN LS OBISPO 41/239 RPR SPLS |  | TEMBLOR-SAN LUIS OBISPO | 041/239 | ICS | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | South | WSIP | [6 empty] | '-120.406668 | 35.3677 | ETL.3960 | 40856781 | Splice-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Pismo Beach |  | Y - 18
119094125 | T3 DI TMBLR-SN LS OBISPO 41/239 RPL INSS | 31514502 | TEMBLOR-SAN LUIS OBISPO | 041/239 | 93K | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | South | WSIP | [6 empty] | '-120.134823 | 35.3846 | ETL.3960 | 40877812 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - Prog 402
119094127 | T3 DI DIABLO-MESA X2/13 RPLC DAMS |  | DIABLO-MESA | X002/013 | ICS | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | South | WSIP | [6 empty] | '-120.81805 | 35.2275 | ETL.4620 | 40651062 | Damper-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Pismo Beach |  | Y - 13
119094280 | T3 DI FULTON-CALISTOGA 1/5 RPLC HRDW |  | FULTON-CALISTOGA | 001/005 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.462797 | 38.5225 | ETL.6880 | 40751150 | Hardware-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
119094300 | T3 DI PIT #1-COTTONWOOD 30/255 RPR FOND | 44051409 | PIT #1-COTTONWOOD | 030/255 | ICQ | E | 2020_(4b) On structure in bucket 4 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.971856 | 40.7516 | ETL.5390 | 40744731 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
119094332 | T3 DI PIT #1-COTTONWOOD 30/255 BENT STL | 43879413 | PIT #1-COTTONWOOD | 030/255 | ICS | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.971856 | 40.7516 | ETL.5390 | 40744731 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain
119094684 | T3NT DI MORAGA-CASTRO VALL 6/27 RPR FOND |  | MORAGA-CASTRO VALLEY | 006/027 | ICQ | F | 2020_(4) TD tag on high spread line |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-122.095526 | 37.7927 | ETL.5250 | 40813796 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  | EBMUD
119094752 | T2 EI KILARC-DESCHUTES 021/454 INST MRK | 43930440 | KILARC-DESCHUTES | 021/454 | ICW | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.222322 | 40.564 | ETL.7300 | 40617679 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119094782 | T2 EI KILARC-DESCHUTES 022/455 RPL ANCHO | 31510881 | KILARC-DESCHUTES | 022/455 | 93E | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.222974 | 40.5638 | ETL.7300 | 40600426 | Anchor-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  | Released
119094930 | T3 DI VOLTA-DESCHUTES 2/57 RPR SPLW | 43939089 | VOLTA-DESCHUTES | 002/057 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.914102 | 40.4715 | ETL.8290 | 42607771 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | released 7-13-20
119094932 | T3 T2 DI VOLTA-DESCHUTES 2/56 REFRAME | 31504879 | VOLTA-DESCHUTES | 002/056 | 93E | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.913358 | 40.4713 | ETL.8290 | 40601159 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  | released 7-13-20
119095027 | T3 DI VOLTA-DESCHUTES 4/87 RPR SPLW | 43939089 | VOLTA-DESCHUTES | 004/087 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.939948 | 40.4779 | ETL.8290 | 40615924 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | released 7-13-20
119095053 | T3 DI VOLTA-DESCHUTES 7/149 RPR SPLW | 43939089 | VOLTA-DESCHUTES | 007/149 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.993258 | 40.4911 | ETL.8290 | 40600298 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119095055 | T3 DI VOLTA-DESCHUTES 7/149 REPL POLE | 31504923 | VOLTA-DESCHUTES | 007/149 | 70Y | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.993258 | 40.4911 | ETL.8290 | 40600298 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain
119095225 | T3 DI VOLTA-DESCHUTES 6/136 RPLC POLE | 31504923 | VOLTA-DESCHUTES | 006/136 | 70Y | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.982465 | 40.4886 | ETL.8290 | 40868514 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain
119095241 | T3 DI KILARC-CEDAR CREEK 3/68 REFRAME | 31505020 | KILARC-CEDAR CREEK | 003/068 | 93E | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.926527 | 40.6949 | ETL.7290 | 40617668 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain
119095246 | T3NT DI KILARC-CDR CRK 3/68 RMV PL BUTT | 43939119 | KILARC-CEDAR CREEK | 003/068 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.926527 | 40.6949 | ETL.7290 | 40617668 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119095585 | T2 DI ELK-GUALALA 47/9 RPL HRDW | 44610591 | ELK-GUALALA | 047/009 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.679365 | 38.9859 | ETL.8410 | 40894857 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
119095636 | T2 EI SPAULDING-SUMMIT 12/428 RPL POLE | 31507079 | SPAULDING-SUMMIT | 012/428 | 70Y | E | 2020_(1b) Lines with special commitments |  |  |  | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.431857 | 39.325 | ETL.8060 | 40618259 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento
119095755 | T3 DI MIDDLE FORK #1 3/54A RPL HRDD | 44356683 | MIDDLE FORK #1 | 003/054A | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.638821 | 38.9959 | ETL.8405 | 40810139 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119095862 | T3 DI MIDDLE FORK #1 3/54B RPL HRDD | 44356683 | MIDDLE FORK #1 | 003/054B | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.638818 | 38.9959 | ETL.8405 | 42569706 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119095867 | T3 DI DRUM-RIO OSO#1 16/135 RPLC HRDT | 44345989 | DRUM-RIO OSO #1 | 016/135 | ICQ | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.01754 | 39.137 | ETL.1420 | 40765091 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento
119096105 | DI IGNACIO-BOLINAS#2 24/269R BOND GYWW |  | IGNACIO-BOLINAS #2 | 024/269 | ICW | E | 2020_(4) TD tag on high spread line | [5 empty] | North Coast | WSIP | [8 empty] | ETL.7180 | 44360930 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
119096109 | DI IGNACIO-BOLINAS#2 24/269L BOND GYWW |  | IGNACIO-BOLINAS #2 | 024/269 | ICW | E | 2020_(4) TD tag on high spread line | [5 empty] | North Coast | WSIP | [8 empty] | ETL.7180 | 44360929 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
119096119 | T3 DI DRUM-GRAS VALLE-WEI 6/155 RMV STUB | 44361670 | DRUM-GRASS VALLEY-WEIMAR | 006/155 | GAR | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.833218 | 39.2048 | ETL.6760 | 40865385 | Structure-Wood | Rotten | Stub | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 586 | Sacramento
119096197 | T3 DI VOLTA-DESCHUTES 2/58 RPR SPLW | 43939089 | VOLTA-DESCHUTES | 002/058 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.914993 | 40.4717 | ETL.8290 | 40650371 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | released 7-13-20
119096215 | T3 DI VOLTA-DESCHUTES 5/115 RPR SPLW | 43939089 | VOLTA-DESCHUTES | 005/115 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.96353 | 40.4838 | ETL.8290 | 40825144 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | released 7-13-20
119096301 | T3 FULTON-CALISTOGA -019/000 RPL STRW | 31507073 | FULTON-CALISTOGA | '-019/000 | 70Y | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.476947 | 38.4896 | ETL.6880 | 40588871 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville
119096489 | T3 DI DRUM-RIO OSO #2 5/59A RPL INSW | 31506135 | DRUM-RIO OSO #2 | 005/59A | 93I | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.851765 | 39.215 | ETL.1430 | 40578817 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Sacramento
119096490 | T2 DRUM-SPAULDING 7/183 RPL POLE | 31502001 | DRUM-SPAULDING | 007/183 | 70Y | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-120.667594 | 39.3077 | ETL.6770 | 40660095 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento
119096512 | T2 DRUM-SPAULDING 7/186 RPL POLE | 31502001 | DRUM-SPAULDING | 007/186 | 70Y | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-120.66539 | 39.3088 | ETL.6770 | 40751884 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento
119096558 | T2 DI VLY SPRGS-MTL #1 10/10 RMV PL BUTT |  | VALLEY SPRINGS-MARTELL #1 | 010/010 | ICW | F | 2020_(1a) PSPS |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-120.781872 | 38.3412 | ETL.8240 | 40599122 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 24
119096571 | T2 DRUM-SPAULDING 7/185 RPL POLE | 31502001 | DRUM-SPAULDING | 007/185 | 70Y | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-120.666126 | 39.3084 | ETL.6770 | 40751837 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento
119096610 | T3 DI DRUM-RIO OSO #2 5/59A RPR STRW | 44356578 | DRUM-RIO OSO #2 | 005/059A | ICW | F | 2020_(2) High fire spread TD |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.850634 | 39.216 | ETL.1430 | 40576825 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119096615 | T3 DI FULTON-CALISTOGA :5/2 RPR STRW | 44597303 | FULTON-CALISTOGA | :005/002 | ICW | E | 2020_(1a) PSPS |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.591305 | 38.6621 | ETL.6880 | 40912459 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
119096616 | T3 DI FULTON-CALISTOGA :5/2 RMV PL BUTT | 44597303 | FULTON-CALISTOGA | :005/002 | ICW | F | 2020_(1a) PSPS |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.591305 | 38.6621 | ETL.6880 | 40912459 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
119096618 | T3 DI SAN RAMON-MORAGA 14/64 RPL INSS | 31504799 | SAN RAMON-MORAGA | 014/064 | 93K | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.085837 | 37.7678 | ETL.5660 | 40786486 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  |  | EBMUD
119096635 | T2 FULTON-HOPLAND 35/8 RPL POLE | 31478309 | FULTON-HOPLAND | 035/008 | 70Y | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.053247 | 38.9219 | ETL.6890 | 40877330 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville
119096694 | T2 DI VLY SPRGS-MTL #1 10/10 RPL POLE | 31505055 | VALLEY SPRINGS-MARTELL #1 | 010/010 | 70Y | E | 2020_(1a) PSPS |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-120.781872 | 38.3412 | ETL.8240 | 40599122 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 24
119096714 | T3 IGNACIO-BOLINAS #1 001/027 RPL PL | 31488037 | IGNACIO-BOLINAS #1 | 001/027 | 70Y | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.57555 | 38.0737 | ETL.7140 | 40617116 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville
119096822 | T3 DI MORAGA-CASTRO VALLE 7/34 RPL INSS | 31511128 | MORAGA-CASTRO VALLEY | 007/034 | 93K | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.085837 | 37.7678 | ETL.5250 | 40786488 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - 9 | EBMUD
119096826 | T3NT DI GEYSERS#3-CLVRDALE 8/93 RPL GMKW |  | GEYSERS #3-CLOVERDALE | 008/093 | ICW | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.949468 | 38.8005 | ETL.1650 | 40657192 | Guy Wire Mark /Indic-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
119096828 | T3 DI DRUM-RIO OSO #2 1/13 RPR INSS | 44356576 | DRUM-RIO OSO #2 | 001/013 | ICS | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.791625 | 39.2555 | ETL.1430 | 40684600 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento
119096830 | T2 CLEAR LAKE-KONOCTI 020/001 RPL PL | 31490846 | CLEAR LAKE-KONOCTI | 020/001 | 70Y | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.779208 | 38.9453 | ETL.6852 | 40584516 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville
119096898 | T3 DI VOLTA-DESCHUTES 0/6 RPLC POLE | 31504923 | VOLTA-DESCHUTES | 000/006 | 70Y | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.871087 | 40.4606 | ETL.8290 | 40759232 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | released 7-13-20
119096920 | T3NT DI GEYS#3-CLDLE 8/93 RMV PL BUTT | 44580896 | GEYSERS #3-CLOVERDALE | 008/093 | ICW | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.949468 | 38.8005 | ETL.1650 | 40657192 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
119096921 | T3 DI DRUM-RIO OSO #2 1/13 RPLC HRDT | 44356575 | DRUM-RIO OSO #2 | 001/013 | ICQ | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.791034 | 39.2563 | ETL.1430 | 40655126 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento
119096922 | DI TESLA-NEWARK #2 17/117 RMV HRDT | 44226389 | TESLA-NEWARK #2 | 017/117 | ICQ | E | 2020_(2) High fire spread TD | [5 empty] | Central | WSIP | [6 empty] | '-121.845963 | 37.5934 | ETL.5354 | 41152663 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y-15
119096923 | T3 DI GEYSERS#3-CLOVERDALE 8/93 RPR SPLW | 44580896 | GEYSERS #3-CLOVERDALE | 008/093 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.949468 | 38.8005 | ETL.1650 | 40657192 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
119096926 | T3 DI VOLTA-DESCHUTES 2/52 RPR SPLW | 43939089 | VOLTA-DESCHUTES | 002/052 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.909583 | 40.4704 | ETL.8290 | 40816161 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119097018 | T2 DI TRINITY-MAPLE CREEK 9/3 RPR GYWW | 44273074 | TRINITY-MAPLE CREEK | 009/003 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.076219 | 40.7659 | ETL.8170 | 40906381 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
119097064 | T2 VACA-SUISUN 009/071 RPL INSS | 31507028 | VACA-SUISUN | 009/071 | 93K | E | 2020_(2) High fire spread TD |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.0430682 | 38.3221 | ETL.4070 | 40623720 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Sacramento
119097074 | T3NT DI DRUM-RIO OSO #1 10/102 RMV DEBRS | 44345615 | DRUM-RIO OSO #1 | 010/102 | ICS | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | North Valley | WSIP | [8 empty] | ETL.1420 | 44337068 | Structure-Steel | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento
119097076 | T3 DI DRUM-RIO OSO #1 10/102 REPL XARM | 31505601 | DRUM-RIO OSO #1 | 010/102 | 93Z | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [8 empty] | ETL.1420 | 44337148 | Crossarm-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Capital |  | Sacramento
119097093 | T2 DI TRINITY-MAPLE CREEK 9/3 RPR SPLW | 44273074 | TRINITY-MAPLE CREEK | 009/003 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.076219 | 40.7659 | ETL.8170 | 40906381 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
119097153 | T3NT DI DRUM-RIO OSO #1 10/102 INST MRKS | 44345615 | DRUM-RIO OSO #1 | 010/102 | ICS | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | North Valley | WSIP | [8 empty] | ETL.1420 | 44337069 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento
119097154 | T3NT DI DRM-GRS VLY-WMR 8/193 RMV PL BUT | 44361669 | DRUM-GRASS VALLEY-WEIMAR | 008/193 | GAR | F | 2020_(1a) PSPS |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.851925 | 39.1881 | ETL.6760 | 40611224 | Structure-Wood | Rotten | Stub | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 586 | Sacramento
119097155 | DI TESLA-NEWARK #2 12/105B RPR FONDT | 44226389 | TESLA-NEWARK #2 | 015/105B | ICQ | F | 2020_(2) High fire spread TD | [5 empty] | Central | WSIP | [6 empty] | '-121.819481 | 37.6093 | ETL.5354 | 41152651 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y-15
119097162 | T3 DI MDLE FORK-GOLD HILL 5/47 RPR GRWW | 44356684 | MIDDLE FORK-GOLD HILL | 005/047 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.678791 | 39.0021 | ETL.5140 | 44551683 | Ground Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119097167 | T3 DI DRUM-RIO OSO #2 9/98 RPR FOND | 44356575 | DRUM-RIO OSO #2 | 009/098 | ICQ | F | 2020_(2) High fire spread TD |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.915529 | 39.177 | ETL.1430 | 40871471 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento
119097246 | DI ATASCADERO-CAYUCOS 0/3 RPR STRW |  | ATASCADERO-CAYUCOS | 000/003 | ICW | E | 2020_(4) TD tag on high spread line | [5 empty] | South | WSIP | [6 empty] | '-120.67346 | 35.4661 | ETL.8480 | 40669485 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - 11
119097249 | DI ATASCADERO-CAYUCOS 0/3 INSTALL MRKW |  | ATASCADERO-CAYUCOS | 000/003 | ICW | F | 2020_(4b) On structure in bucket 4 | [5 empty] | South | WSIP | [6 empty] | '-120.67346 | 35.4661 | ETL.8480 | 40669485 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - 11
119097266 | T3 DI DRUM-RIO OSO#2 9/92 RPR FOND | 44356575 | DRUM-RIO OSO #2 | 009/092 | ICQ | F | 2020_(2) High fire spread TD |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.904248 | 39.1815 | ETL.1430 | 40672397 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento
119097277 | T3 DI SOBRANTE-""G"" #1 3/19 RPR FOND | 44624390 | SOBRANTE-"G" #1 | 003/019 | ICQ | F | 2020_(2) High fire spread TD |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-122.259485 | 37.9137 | ETL.3720 | 40857649 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 9
119097279 | T3 DI MIDDLE FRK-GLD HL 9/80 RPLC INSW | 31506134 | MIDDLE FORK-GOLD HILL | 009/080 | 93I | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.739895 | 38.9874 | ETL.5140 | 40636078 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Sacramento
119097460 | T3NT DI DRUM-RIO OSO#2 6/65 RPR FOND | 44356575 | DRUM-RIO OSO #2 | 006/065 | ICQ | F | 2020_(2) High fire spread TD |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.858508 | 39.2109 | ETL.1430 | 40757182 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento
119097463 | DI DRUM- RIO OSO#2 009/094 RPR FONDT | 44361674 | DRUM-RIO OSO #2 | 009/094 | ICQ | F | 2020_(2) High fire spread TD |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.907128 | 39.1803 | ETL.1430 | 40757351 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento
119097486 | T3 DI IGNACIO-BOLINAS #1 13/143 RPR INSW |  | IGNACIO-BOLINAS #1 | 013/143 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.698253 | 37.9424 | ETL.7140 | 40778792 | Insulator-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
119097515 | T3 DI MTF-GRVLY 16/112 RPR STRW | 44392287 | METCALF-GREEN VALLEY | 016/112 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | South | WSIP | [6 empty] | '-121.662117 | 37.0351 | ETL.2540 | 44401453 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  | Y - 10
119097568 | T2 DI PIT #1-CTNWD 54/489 RPR FOND | 44051409 | PIT #1-COTTONWOOD | 054/489 | ICQ | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.214369 | 40.46 | ETL.5390 | 40868155 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
119097570 | T3 DI DSBLA-CNTRVLLE 1/26A RMV PL BUTT |  | DESABLA-CENTERVILLE | 001/026A | ICW | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.633102 | 39.8452 | ETL.6720 | 40809994 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119097571 | T3 DI DSBLA-CNTRVLLE 1/26A RPR GYWW | 44356201 | DESABLA-CENTERVILLE | 001/026A | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.633102 | 39.8452 | ETL.6720 | 40809994 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119097573 | T3 DI DRUM-RIO OSO #2 1/10 RPR STRT | 44345992 | DRUM-RIO OSO #2 | 001/010 | ICQ | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.786353 | 39.2564 | ETL.1430 | 40597545 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento
119097576 | T3 DI RND MTN CTTNWD #3 28/226 RPL INSS | 31504993 | ROUND MTN-COTTONWOOD #3 | 028/226 | 93K | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.942401 | 40.7872 | ETL.5650 | 40813496 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain
119097595 | DI PIT #1-COTTONWOOD 13/106 RPR STRT | 44051409 | PIT #1-COTTONWOOD | 013/106 | ICQ | E | 2020_(4) TD tag on high spread line | [5 empty] | North Valley | WSIP | [6 empty] | '-121.707815 | 40.8811 | ETL.5390 | 40817578 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
119097621 | T2 DI BRDGVLL-CTTNWD 10/95 RPL HRDW | 43939216 | BRIDGEVILLE-COTTONWOOD | 010/095 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.460955 | 40.389 | ETL.1110 | 44423873 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119097622 | DI PIT #1-COTTONWOOD 58/525 RPR STRT | 44051409 | PIT #1-COTTONWOOD | 058/525 | ICQ | E | 2020_(4) TD tag on high spread line | [5 empty] | North Valley | WSIP | [6 empty] | '-122.250398 | 40.4163 | ETL.5390 | 40759495 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
119097628 | T3 DI WEIMAR #1 11/163 RMV BUTT | 44362375 | WEIMAR #1 | 011/163 | ICW | E | 2020_(1a) PSPS |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.805138 | 39.0121 | ETL.7560 | 40824475 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119097629 | T3 DI WEIMAR #1 11/163 REFRAME | 31506098 | WEIMAR #1 | 011/163 | 93E | E | 2020_(1a) PSPS |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.805138 | 39.0121 | ETL.7560 | 40824475 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Sacramento
119097848 | T3 DI SBRNT-GRZLY-CLRMNT #1 A0/4 RPR FND | 44624393 | SOBRNTE-GRIZZLY-CLARMNT #1+ | A000/004 | ICQ | F | 2020_(2) High fire spread TD |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-122.213556 | 37.8989 | ETL.3740 | 40765711 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 13
119097849 | T3NT DI SBRNT-GRZLY-CLRMNT #1 A0/4 ATCG | 44624393 | SOBRNTE-GRIZZLY-CLARMNT #1+ | A000/004 | ICQ | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-122.213556 | 37.8989 | ETL.3740 | 40765711 | Structure-Tower | Anti-Climbing Guard | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 988 | Bay |  | Y - 13
119098458 | T2 DI COLGATE-SMRTVL #2 9/114 RPLC SPLW | 44345892 | COLGATE-SMARTVILLE #2 | 009/114 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.29803 | 39.2298 | ETL.6520 | 40644594 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119098581 | T2 DI BRDGVLL-COTTONWD 30/253 RPR GYWW | 43939216 | BRIDGEVILLE-COTTONWOOD | 030/253 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.836544 | 40.3641 | ETL.1110 | 44561190 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119098597 | T3 DI KILARC-CEDAR CREEK 5/131 RPR STRW | 43939119 | KILARC-CEDAR CREEK | 005/131 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.975193 | 40.7093 | ETL.7290 | 44837767 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119098687 | T3 DI DRUM-RIO OSO #2 8/86 RPR SPLICE | 44356576 | DRUM-RIO OSO #2 | 008/086 | ICS | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.884581 | 39.1892 | ETL.1430 | 40822812 | Splice-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento
119098829 | T3 DI PITTSBURG-SAN RAMON 13/52 RPR FOND | 44623420 | PITTSBURG-SAN RAMON | 013/052 | ICQ | F | 2020_(2) High fire spread TD |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-121.886824 | 37.864 | ETL.5490 | 40646929 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay
119099090 | T2 DI COLGATE-SMRTVL #2 9/105 RPLC SPLS | 44345893 | COLGATE-SMARTVILLE #2 | 009/105 | ICS | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.295597 | 39.2355 | ETL.6520 | 40668767 | Splice-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento
119099093 | T2 DI COLGATE-SMRTVL #2 9/105 RMV BUTT | 44345892 | COLGATE-SMARTVILLE #2 | 009/105 | ICW | E | 2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.295597 | 39.2355 | ETL.6520 | 40668767 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119099372 | T2 DI COLGATE-SMRTVL #2 7/78 RPR SPLW | 44345892 | COLGATE-SMARTVILLE #2 | 007/078 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.284506 | 39.2633 | ETL.6520 | 40771603 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119099938 | T2 DI BRDGVL-CTNWOOD 31/261 RPR FOND | 43706644 | BRIDGEVILLE-COTTONWOOD | 031/261 | ICQ | E | 2020_(2) High fire spread TD |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.857568 | 40.3637 | ETL.1110 | 40657032 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
119100178 | T2 DI COLGATE-SMRTVI #2 4/54 RPR SPLW | 44345892 | COLGATE-SMARTVILLE #2 | 004/054 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.256375 | 39.2898 | ETL.6520 | 44231831 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119100627 | T3 EAGL RCK-FLTN-SLVD 4/23 INST JMP INSS | 31515212 | EAGLE ROCK-FULTON-SILVERADO | 004/023 | 92E | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.7980828 | 38.7769 | ETL.4392 | 40690781 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Lakeville
119100725 | DI GREEN VALLEY-LLAGAS 6/51 RPL CSRW | 31506197 | GREEN VALLEY-LLAGAS | 006/051 | 93E | E | 2020_(4) TD tag on high spread line | [5 empty] | South | WSIP | [6 empty] | '-121.713752 | 37.034 | ETL.1720 | 44401059 | Crossarm-Wood | No Good/Out of Stdrd | Replace | MAPP srdy | MAPP | Constructed and mapped | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Moss Landing |  | Y - 10
119100763 | T3 DI POE-RIO OSO-RIO 19/134 RPL HRDT |  | POE-RIO OSO | 019/134 | ICQ | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.484173 | 39.701 | ETL.5540 | 40757242 | Hardware-Tower | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
119100983 | T3 DI CRESTA-RIO OSO-TW 020/166 RPL HRDT |  | CRESTA-RIO OSO | 020/166 | ICQ | F | 2020_(4) TD tag on high spread line |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.492615 | 39.6754 | ETL.4590 | 40906789 | Hardware-Tower | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
119101064 | T2 TRINITY-MAPLE CREEK 030/003 REFRAME | 31472099 | TRINITY-MAPLE CREEK | 030/003 | 93E | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.463254 | 40.6926 | ETL.8170 | 40906460 | Crossarm-Wood | No Good/Out of Stdrd | Replace | CONS srdy | CONS | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Eureka
119101533 | T2 DI WEIMAR #1 4/64 REPL SPLW | 44362373 | WEIMAR #1 | 004/064 | ICW | E | 2020_(4) TD tag on high spread line |  |  | CANCEL/CNCL | TR2 |  | North Valley | WSIP | [6 empty] | '-120.925046 | 39.0204 | ETL.7560 | 40696105 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119101937 | T2 FULTON-HOPLAND 29/9 RPL POLE | 31478309 | FULTON-HOPLAND | 029/009 | 70Y | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.016792 | 38.8449 | ETL.6890 | 40868390 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville
119101974 | FULTON-HOPLAND 10/6 RPL POLE | 31478308 | FULTON-HOPLAND | 010/006 | 70Y | E | 2020_(2) High fire spread TD | [5 empty] | North Coast | WSIP | [6 empty] | '-122.845103 | 38.6206 | ETL.6890 | 40827228 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville
119102039 | T2 FULTON-HOPLAND 30/7 RPL POLE | 31478309 | FULTON-HOPLAND | 030/007 | 70Y | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.02736 | 38.852 | ETL.6890 | 40825342 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville
119102114 | T3 DI DRUM-RIO OSO #2 1/15 RPR FOND | 44356575 | DRUM-RIO OSO #2 | 001/015 | ICQ | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.794213 | 39.2562 | ETL.1430 | 40765123 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento
119102208 | T2 COLGATE-SMARTVILLE #2 10/117 RPL POLE | 31485386 | COLGATE-SMARTVILLE #2 | 010/117 | 70Y | E | 2020_(1a) PSPS |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.300744 | 39.2241 | ETL.6520 | 40618357 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento
119102540 | T2 DI BRDGVL-COTTONWOOD 9/91 RPR STRW | 43939216 | BRIDGEVILLE-COTTONWOOD | 009/091 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.452629 | 40.3891 | ETL.1110 | 44424551 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119102710 | T3 DI DIABLO-MESA 26/112 RPLC INSS | 31510098 | DIABLO-MESA | 026/112 | 93K | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | South | WSIP | [6 empty] | '-120.525487 | 35.1183 | ETL.4620 | 40714102 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 13
119102717 | T3 DI MORRO BAY-MESA 26/112 RPLC INSS | 31501671 | MORRO BAY-MESA | 026/112 | 93K | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | South | WSIP | [6 empty] | '-120.525487 | 35.1183 | ETL.5290 | 40714100 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 16
119102783 | T3NT DI FULTN-PUBLO-TWER 41/210 RPR FOND |  | FULTON-PUEBLO | 041/210 | ICQ | F | 2020_(4) TD tag on high spread line |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.723757 | 38.4968 | ETL.1600 | 40587750 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville
119102914 | T3 DI RND MTN-CTNWOOD #3 33/280 RPL INSS | 31504993 | ROUND MTN-COTTONWOOD #3 | 033/280 | 93K | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.997653 | 40.721 | ETL.5650 | 40634534 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain
119102929 | T3 DI WEIMAR #1 7/105 RPR GYWW | 44362375 | WEIMAR #1 | 007/105 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.86999 | 39.02 | ETL.7560 | 40874873 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119102952 | T3 DI VOLTA-DESCHUTES 1/36 RMV BUTT | 43939089 | VOLTA-DESCHUTES | 001/036 | ICW | E | 2020_(4b) On structure in bucket 4 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.896662 | 40.4672 | ETL.8290 | 40656909 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | released 7-13-20
119102957 | T3 DI COLGATE-ALLEGHNY 9/264 RMV PL BUTT | 44345667 | COLGATE-ALLEGHANY | 009/264 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.036797 | 39.3781 | ETL.6470 | 40818482 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119103032 | T3 DI MIDDLE FORK #1 9/129 RPR GYWW | 44365338 | MIDDLE FORK #1 | 009/129 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.740752 | 39.0054 | ETL.8405 | 40653602 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119103050 | T3 DI FRNCH MEADW-MDLE FORK 0/2 RPR IBWW | 44361677 | FRENCH MEADOWS-MIDDLE FORK | 000/002 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.407465 | 39.0777 | ETL.6870 | 40693741 | Insulator Bond Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119103070 | T3 DI VOLTA-DESCHUTES 3/83 RMV BUTT | 43939089 | VOLTA-DESCHUTES | 003/083 | ICW | E | 2020_(4b) On structure in bucket 4 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.936385 | 40.477 | ETL.8290 | 40825124 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | released 7-13-20
119103080 | T3 DI CARIBOU-PALERMO :31/255 RPR INSS |  | CARIBOU-PALERMO | 031/255 | ICS | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.464758 | 39.7615 | ETL.3190 | 40801850 | Insulator-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain
119103113 | T3 DI DRM GRS VLY-WMR 2/67 RPR SHLW | 44361667 | DRUM-GRASS VALLEY-WEIMAR | 002/067 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.785792 | 39.2326 | ETL.6760 | 40654108 | Shield Wire / OPGW-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119103115 | T3 DI DRM GRS VLY-WMR 2/67 RMV PL BUTT | 44361666 | DRUM-GRASS VALLEY-WEIMAR | 002/067 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.785792 | 39.2326 | ETL.6760 | 40654108 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119103144 | T2 DI COLGTE-SMARTVLE #2 3/43 RPL POLE | 31507078 | COLGATE-SMARTVILLE #2 | 003/043 | 70Y | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.244787 | 39.3032 | ETL.6520 | 40864694 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento
119103160 | T3 DI IGNACIO-BOLINAS #1 9/104B RMV STUB |  | IGNACIO-BOLINAS #1 | 009/104 | ICW | E | 2020_(4b) On structure in bucket 4 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.657464 | 37.9899 | ETL.7140 | 41118222 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
119103162 | T3NT DI KLRC-CDR CRK 9/210 RMV DEBRIS | 43939119 | KILARC-CEDAR CREEK | 009/210 | ICW | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.977905 | 40.7441 | ETL.7290 | 40868041 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119103181 | T3 DI SOBRANTE-""""R"""" #1 3/021 RPR FOND | 44624391 | SOBRANTE-R #1 | 003/021 | ICQ | F | 2020_(2) High fire spread TD |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-122.263779 | 37.9147 | ETL.3770 | 40581011 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  | Tilden RP
119103267 | T3NT DI VOLTA-DESCHUTES 2/64 RMV BUTT | 43939089 | VOLTA-DESCHUTES | 002/064 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.920258 | 40.473 | ETL.8290 | 40867824 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119103290 | T3 DI VOLTA-DESCHUTES 2/64 REFRAME CRSW | 31505200 | VOLTA-DESCHUTES | 002/064 | 93E | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.920258 | 40.473 | ETL.8290 | 40867824 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain
119103297 | T3 DI DSBLA-CNTRVLLE 0/12 RPR GYWW | 44356201 | DESABLA-CENTERVILLE | 000/012 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.629187 | 39.8642 | ETL.6720 | 40700298 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119103357 | T2 DI FT RS-GLA-GLA 32/0 GRND WASH INSW |  | GUALALA-MONTE RIO | 032/000 | ICD | E | 2020_(2) High fire spread TD |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.2676 | 38.5568 | ETL.6980 | 40606887 | Insulator | Contaminated | Ground Wash |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 622 | Lakeville
119103389 | T2 DI PHILO JCT-ELK-ELK 5/4 RPR STRW | 44610684 | PHILO JCT-ELK | 005/004 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.228235 | 39.0644 | ETL.7780 | 40763009 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
119103436 | T3 DI MORAGA-SAN LENDRO #3 6/45 RPR FOND |  | MORAGA-SAN LEANDRO #3 | 006/045 | ICQ | F | 2020_(4) TD tag on high spread line |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-122.115846 | 37.7634 | ETL.2790 | 40745916 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  | ACRP
119103754 | T3 DI VOLTA-DESCHUTES 6/135 REFRAME | 31505200 | VOLTA-DESCHUTES | 006/135 | 93E | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.98168 | 40.4883 | ETL.8290 | 40825136 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain
119103759 | T2 DI CLGT-SMRTVL #2 7/74 RMV PL BUTT | 44345892 | COLGATE-SMARTVILLE #2 | 007/074 | ICW | E | 2020_(1a) PSPS |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.283314 | 39.2653 | ETL.6520 | 40618345 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119103812 | DI GOLDTREE 001/018 RMV DEBRIS |  | GOLDTREE TAP | 001/018 | ICW | F | 2020_(3) On high spread structure | [5 empty] | South | WSIP | [6 empty] | '-120.702442 | 35.3046 | ETL.2821 | 40657975 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach
119103953 | T3 DI FULTON-PUEBLO 033/166 RPL INSS | 31505500 | FULTON-PUEBLO | 033/166 | 92E | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.590748 | 38.4943 | ETL.1600 | 40835394 | Insulator-Steel | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Lakeville
119103972 | T2 DI KILARC-DESCHUTES 4/90 RPLC SPLW | 43930440 | KILARC-DESCHUTES | 004/090 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.918251 | 40.6274 | ETL.7300 | 40816213 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Released
119103973 | T2 DI KILARC-DESCHUTES 9/196 RPLC POLE | 31505204 | KILARC-DESCHUTES | 009/196 | 70Y | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.997468 | 40.5865 | ETL.7300 | 40592171 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Released
119104213 | T3 DI MORAGA-CASTRO VLLY 4/22 RPR FOND | 44623422 | MORAGA-CASTRO VALLEY | 004/022 | ICQ | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.106985 | 37.8086 | ETL.5250 | 40670657 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 9 | EBMUD
119104214 | T3NT DI MORAGA-CASTRO VALY 4/22 PNT STRS | 43744386 | MORAGA-CASTRO VALLEY | 004/022 | ICS | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-122.106985 | 37.8086 | ETL.5250 | 40670657 | Structure-Steel | Paint/Coating | Other | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  |  | EBMUD
119104420 | T3 DI DRUM-RIO OSO #2 01/016 RPR SPLS | 44356576 | DRUM-RIO OSO #2 | 001/016 | ICS | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.796389 | 39.2561 | ETL.1430 | 40820377 | Splice-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento
119104428 | T2 DI BRIDGVLLE-CTTNWD 10/99L RMV PL BUT | 43939216 | BRIDGEVILLE-COTTONWOOD | 010/099 | ICW | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.469683 | 40.389 | ETL.1110 | 44424496 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119104607 | T3 DI KONOCTI-MDLTWN 28/3 RPR INSS | 44610651 | KONOCTI-MIDDLETOWN | 028/003 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.644696 | 38.909 | ETL.6380 | 44433446 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
119104731 | T3NT DI DRUM-RIO OSO #2 8/89 RMV DEBRIS | 44345661 | DRUM-RIO OSO #2 | 008/089 | ICW | F | 2020_(4b) On structure in bucket 4 |  |  | Likely MAT error - delink to correct | TR3 |  | North Valley | WSIP | [8 empty] | ETL.1430 | 44304980 | Structure-Steel | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento
119104736 | T3NT DI DRUM-RIO OSO #2 8/89R INST MRKS | 44345661 | DRUM-RIO OSO #2 | 008/089 | ICW | F | 2020_(4b) On structure in bucket 4 |  |  | Likely MAT error - delink to correct | TR3 |  | North Valley | WSIP | [8 empty] | ETL.1430 | 44304981 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento
119104767 | DI CAYUCOS-CAMBRIA 7/47 RPR HRDW |  | CAYUCOS-CAMBRIA | 007/047 | ICW | E | 2020_(2) High fire spread TD | [5 empty] | South | WSIP | [6 empty] | '-120.963397 | 35.5105 | ETL.8560 | 40752359 | Hardware-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - Prog 401
119105264 | T3NT DI DRUM-SUMMIT#2 0/5L RMV DEBRIS | 44345830 | DRUM-SUMMIT #2 | 000/005 | ICW | F | 2020_(1b) Lines with special commitments |  |  |  | TR3 | WECC | North Valley | WSIP | [6 empty] | '-120.761868 | 39.2549 | ETL.1450 | 44549915 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119105267 | T2 DI WEIMAR#1 1/27 RMV PL BUTT | 44362374 | WEIMAR #1 | 001/027 | ICW | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-120.969664 | 39.0297 | ETL.7560 | 40586055 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119105302 | T2NT DI GARCIA TAP 1/1 INST MRKW |  | GARCIA TAP | 001/001 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.578937 | 38.8813 | ETL.8411 | 40601539 | Marker (i.e. signs)-Wood | Missing | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
119105305 | T2 DI GARCIA TAP 1/1 RPR INSW | 44610601 | GARCIA TAP | 001/001 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.578985 | 38.8805 | ETL.8411 | 40628230 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
119105307 | T2 DI GARCIA TAP 1/1 RPR SPLW | 44610601 | GARCIA TAP | 001/001 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.578937 | 38.8813 | ETL.8411 | 40601539 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
119105433 | T3 DI MIDDLE FRK-GLD HL 7/60R RPR STRW | 44361893 | MIDDLE FORK-GOLD HILL | 007/060 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.711104 | 39.0031 | ETL.5140 | 44565762 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119105441 | T3 DI PITTSBURG-SAN RAMON 12/51 RPR FOND | 44623420 | PITTSBURG-SAN RAMON | 012/051 | ICQ | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-121.886302 | 37.8655 | ETL.5490 | 40581142 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  | CCR
119105772 | T3 DI GREEN VALLEY-LLAGAS 3/28 SPLIT BLT | 44392293 | GREEN VALLEY-LLAGAS | 003/028 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | South | WSIP | [6 empty] | '-121.729801 | 36.9938 | ETL.1720 | 44401072 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  | Y - 10
119105919 | T2 DI KILARC-DESCHUTES 021/452 RPL SPLW | 43930440 | KILARC-DESCHUTES | 021/452 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.220619 | 40.5642 | ETL.7300 | 40877870 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Released
119105971 | T2 DI KILARC-DESCHUTES 4/95 RPL INSW | 31506150 | KILARC-DESCHUTES | 004/095 | 93I | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.921461 | 40.6246 | ETL.7300 | 40735599 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Table Mountain |  |  | Released
119106181 | T2 DI KILARC-DESCHUTES 021/452 INS NMBR | 43930440 | KILARC-DESCHUTES | 021/452 | ICW | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.220619 | 40.5642 | ETL.7300 | 40877870 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Released
119106183 | T2 DI KILARC-DESCHUTES 22/455 RMV BUTT | 43930440 | KILARC-DESCHUTES | 022/455 | ICW | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.222974 | 40.5638 | ETL.7300 | 40600426 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Released
119106522 | T2 HUMBOLDT-TRINITY 58/1 RPL INSW | 31509856 | HUMBOLDT-TRINITY | 058/001 | 93I | E | 2020_(2) High fire spread TD |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.139448 | 40.7656 | ETL.1820 | 44553876 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSE erdy | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Eureka
119106533 | T2 DI COLGATE-GRASS VLY 7/180 REFRAME | 31507018 | COLGATE-GRASS VALLEY | 007/180 | 93E | E | 2020_(1a) PSPS |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.090593 | 39.2704 | ETL.6490 | 40760395 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Sacramento
119106534 | T2 DI KILARC-DESCHUTES 4/92 RPR SPLW | 43930440 | KILARC-DESCHUTES | 004/092 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.919549 | 40.6263 | ETL.7300 | 40867886 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Released
119106537 | T2 DI CLGT-SMRTVL #2 9/104 CANCEL | 44345892 | COLGATE-SMARTVILLE #2 | 009/104 | ICW | E | 2020_(1a) PSPS |  |  | CANCEL/CNCL | TR2 |  | North Valley | WSIP | [6 empty] | '-121.295651 | 39.2364 | ETL.6520 | 40702105 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119106543 | T2 DI TRNTY-MPL CRK 024/000 RPR SPLW | 44273074 | TRINITY-MAPLE CREEK | 024/000 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.335753 | 40.7057 | ETL.8170 | 40590531 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
119106822 | T2 DI CLGT-SMRTVL #2 9/104 RPLC POLE | 31505202 | COLGATE-SMARTVILLE #2 | 009/104 | 70Y | E | 2020_(1a) PSPS |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.295651 | 39.2364 | ETL.6520 | 40702105 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento
119106863 | T2 DI KILARC-DESCHUTES 9/200 RMV BUTT | 43930440 | KILARC-DESCHUTES | 009/200 | ICW | E | 2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.000248 | 40.5856 | ETL.7300 | 40759124 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Released
119106865 | T2 DI KILARC-DESCHUTES 9/200 RPR SPLW | 43930440 | KILARC-DESCHUTES | 009/200 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.000248 | 40.5856 | ETL.7300 | 40759124 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Released
119107011 | T2 DI SALINAS-LAURELES 14/298 RPLC POLE | 31505565 | SALINAS-LAURELES | 014/298 | 70Y | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-121.746674 | 36.5268 | ETL.7930 | 40697439 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Moss Landing |  | Y - 12
119107038 | T2 DI SALINAS-LAURLS 13/283 GRWASH INSU |  | SALINAS-LAURELES | 013/283 | ICD | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-121.753169 | 36.5422 | ETL.7930 | 40630294 | Insulator | Contaminated | Ground Wash |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 622 | Moss Landing
119107141 | T2 DI TRINITY-MAPLE CREEK 5/7 BOND GUY | 44273074 | TRINITY-MAPLE CREEK | 005/007 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.031816 | 40.732 | ETL.8170 | 40906324 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
119107311 | T3 DI WEIMAR #1 5/80 RPR GYWS | 44362376 | WEIMAR #1 | 005/080 | ICS | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.899512 | 39.0191 | ETL.7560 | 40589969 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento
119107783 | T3 DI SOBRANT-GRZZ-CLR #1 5/51 RPR FOND |  | SOBRNTE-GRIZZLY-CLARMNT #1+ | 005/051 | ICQ | F | 2020_(4) TD tag on high spread line |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-122.221722 | 37.8478 | ETL.3740 | 40746108 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog 404
119107789 | T2 DI KILARC-DESCHUTES A025/520 RPR SPLW | 43930440 | KILARC-DESCHUTES | A025/520 | ICW | E | 2020_(1b) Lines with special commitments |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.276592 | 40.5712 | ETL.7300 | 44825404 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Released
119107833 | T3 DI GRN VLY-LLAGAS 5/42L RMV BUTT | 44578798 | GREEN VALLEY-LLAGAS | 005/042 | ICW | F | 2020_(4b) On structure in bucket 4 | [5 empty] | South | WSIP | [6 empty] | '-121.721726 | 37.0221 | ETL.1720 | 44565746 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  | Y - 10
119107834 | T3 DI GRN VLY-LLAGAS 5/42L RPR POLE | 44578798 | GREEN VALLEY-LLAGAS | 005/042 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | South | WSIP | [6 empty] | '-121.721726 | 37.0221 | ETL.1720 | 44565746 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  | Y - 10
119107836 | T3 DI GRN VLY-LLAGAS 5/42R RPR POLE | 44578798 | GREEN VALLEY-LLAGAS | 005/042 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | South | WSIP | [6 empty] | '-121.721726 | 37.0221 | ETL.1720 | 44565816 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  | Y - 10
119107839 | T3 DI GRN VLY-LLAGAS 5/42L RPR BOND | 44578798 | GREEN VALLEY-LLAGAS | 005/042 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  |  | LATE | South | WSIP | [6 empty] | '-121.721726 | 37.0221 | ETL.1720 | 44565746 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  | Y - 10
119107984 | T3 DI WEIMAR #1 012/170R RPL POLE | 31505365 | WEIMAR #1 | 012/170 | 70Y | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.784859 | 39.0146 | ETL.7560 | 44947129 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento
119107987 | T3 DI WEIMAR #1 012/170L RPL POLE | 31505365 | WEIMAR #1 | 012/170 | 70Y | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.784859 | 39.0146 | ETL.7560 | 44947119 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento
119108001 | T2 DI SN LS OBSP-SNT MAR 10/180 RMV VEG |  | SAN LUIS OBISPO-SANTA MARIA (IDLE) | 010/180 | HNA | E | 2020_(1b) Lines with special commitments |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-120.527967 | 35.1547 | ETL.9100 | 44191884 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Pismo Beach
119108078 | T3 DI DRUM-RIO OSO #1 10/100 BENT MEMB | 44356574 | DRUM-RIO OSO #1 | 010/100 | ICQ | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.919362 | 39.1757 | ETL.1420 | 40588543 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento
119108139 | T3 DI PTSBURG-SAN MTO-TWR 11/43 REP FOND |  | PITTSBURG-SAN MATEO | 011/043 | ICQ | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-121.876532 | 37.8891 | ETL.5463 | 40870770 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog 402
119108365 | T2 DI SN LIS OBSPO-CAYCS 15/137 RPR IBWW |  | SAN LUIS OBISPO-CAYUCOS | 015/137 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-120.806262 | 35.3536 | ETL.9090 | 44565348 | Insulator Bond Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - 12
119108420 | T2 DI SN LIS OBSPO-CAYCS 15/137 RPR IBWW |  | SAN LUIS OBISPO-CAYUCOS | 015/137 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-120.806262 | 35.3536 | ETL.9090 | 44565513 | Insulator Bond Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - 12
119108607 | T2NT DI WEIMAR #1 1/25 INST MRKW | 44362374 | WEIMAR #1 | 001/025 | ICW | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-120.97133 | 39.0304 | ETL.7560 | 40650014 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119108635 | T3 DI KLRC-CEDAR CREEK 4/109 RPL STRW | 31506712 | KILARC-CEDAR CREEK | 004/109 | 70Y | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.957883 | 40.7042 | ETL.7290 | 42615554 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain
119108730 | T3 DI DRUM-GRSS VALY-WEIMR 2/65 RPR STRW | 44361667 | DRUM-GRASS VALLEY-WEIMAR | 002/065 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.784317 | 39.2331 | ETL.6760 | 40589537 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119108840 | T3 DI GEYSRS #3-CLVRDLE 007/081 RPL INSW | 31506240 | GEYSERS #3-CLOVERDALE | 007/081 | 93I | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.934694 | 38.8063 | ETL.1650 | 40700670 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Lakeville
119108843 | T3 DI GEYSRS #3-CLVRDLE 007/081 RPL ANCW | 31506241 | GEYSERS #3-CLOVERDALE | 007/081 | 93E | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.934694 | 38.8063 | ETL.1650 | 40700670 | Anchor-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Lakeville
119108847 | T3 DI MIDDL FRK-GLD HL 6/56L RPLC HRDD | 44356684 | MIDDLE FORK-GOLD HILL | 006/056 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.701453 | 39.0028 | ETL.5140 | 44552539 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119108848 | T3NT DI MNDOCINO-WILLITS 9/4A RPL POLE | 31514050 | MENDOCINO-WILLITS | 009/004A | 70Y | F | 2020_(2) High fire spread TD |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-123.303156 | 39.3367 | ETL.7540 | 40577241 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville
119108849 | T3 DI MIDDL FRK-GLD HL 6/56R RPLC HRDD | 44356684 | MIDDLE FORK-GOLD HILL | 006/056 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.701453 | 39.0028 | ETL.5140 | 44552407 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119108917 | T3 DI EAGLE ROCK-REDBUD :8/46 RPR FOND |  | EAGLE ROCK-REDBUD | :008/046 | ICQ | F | 2020_(2) High fire spread TD |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.691637 | 38.8861 | ETL.1480 | 40809073 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville
119108991 | T2 DI ELK-GUALALA 049/001 RPR GYWW | 44610591 | ELK-GUALALA | 049/001 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.680698 | 38.9688 | ETL.8410 | 40601575 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
119109025 | T2 DI CLGT-GRSS VLLY 10/246 RPR SPLW | 44371196 | COLGATE-GRASS VALLEY | 010/246 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.079202 | 39.2296 | ETL.6490 | 40760648 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119109067 | T3NT DI MRAGA-CASTRO VALLY 4/21 RPR FOND | 44623422 | MORAGA-CASTRO VALLEY | 004/021 | ICQ | F | 2020_(2) High fire spread TD |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-122.109219 | 37.8133 | ETL.5250 | 40589807 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 9 | EBMUD
119109251 | T2 DI FORT ROSS-GUALALA 49/4 RPR GYWW |  | GUALALA-MONTE RIO | 049/004 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.396437 | 38.7223 | ETL.6980 | 40770597 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
119109259 | T2 DI ELK-GUALALA 063/005 RPR STRW | 44610591 | ELK-GUALALA | 063/005 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.549584 | 38.8193 | ETL.8410 | 40762845 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
119109292 | T3 DI FULTON-CALISTOGA :006/000 BOND GUY | 44597303 | FULTON-CALISTOGA | :006/000 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.586577 | 38.6712 | ETL.6880 | 40912470 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
119109354 | T3 DI MDL FRK-GLD HL 4/41R RPR STRW | 44361893 | MIDDLE FORK-GOLD HILL | 004/041 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.65868 | 38.9995 | ETL.5140 | 44552450 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119109369 | T3NT DI MRGA-CASTRO VALLEY 5/25 RPR FOND | 44623422 | MORAGA-CASTRO VALLEY | 005/025 | ICQ | F | 2020_(2) High fire spread TD |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-122.101988 | 37.7981 | ETL.5250 | 40756483 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 9 | EBMUD
119109371 | T3NT DI MORAGA-OAKLND #3 0/1 RPR FOND | 44623421 | MORAGA-OAKLAND #3 | 000/001 | ICQ | F | 2020_(2) High fire spread TD |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-122.16193 | 37.8471 | ETL.2740 | 40580802 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay
119109376 | DI GATES-PANOCHE #1 1/9 INSTALL HRDT | 44361571 | GATES-PANOCHE #1 | 001/009 | ICQ | E | 2020_(1b) Lines with special commitments |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.139353 | 36.1603 | ETL.4720 | 40863280 | Hardware-Tower | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 10
119109464 | T2 DI VLLY SPRNGS-MRTEL #1 8/5 INST GMKW |  | VALLEY SPRINGS-MARTELL #1 | 008/005 | ICW | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-120.765147 | 38.3082 | ETL.8240 | 40753638 | Guy Wire Mark /Indic-Wood | Missing | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 24
119109465 | T2 DI VLLY SPRNGS-MRTEL #1 8/5 RPR GYWW |  | VALLEY SPRINGS-MARTELL #1 | 008/005 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-120.765147 | 38.3082 | ETL.8240 | 40753638 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 24
119109512 | T2 DI CARIBOU-PALERMO 8/69 INST STEPS |  | CARIBOU-PALERMO | 008/069 | ICQ | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.53135 | 39.5695 | ETL.3190 | 40867354 | Hardware-Tower | Missing | Install |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
119109517 | T3 DI WEIMAR #1 12/170C RPL POLE | 31505365 | WEIMAR #1 | 012/170 | 70Y | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.784859 | 39.0146 | ETL.7560 | 44947120 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento
119109574 | T2 DI VLLY SPRNGS-MRTL #1 10/5 RPL SPLC |  | VALLEY SPRINGS-MARTELL #1 | 010/005 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-120.779866 | 38.338 | ETL.8240 | 40767359 | Splice-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 24
119109576 | T2 DI VLLY SPRNGS-MRTL #1 10/5 INST MRKW |  | VALLEY SPRINGS-MARTELL #1 | 010/005 | ICW | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-120.779866 | 38.338 | ETL.8240 | 40767359 | Marker (i.e. signs)-Wood | Missing | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog 401
119110319 | T2 DI COLGATE-GRSS VLLY 9/218 BUTT CNCL | 44365323 | COLGATE-GRASS VALLEY | 009/218 | ICW | F | 2020_(4b) On structure in bucket 4 |  |  | CANCEL/CNCL | TR2 |  | North Valley | WSIP | [6 empty] | '-121.083132 | 39.2466 | ETL.6490 | 40818423 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119110349 | T3 DI FULTON-PUEBLO 36/182 RPL INSS | 31505500 | FULTON-PUEBLO | 036/182 | 92E | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.641108 | 38.497 | ETL.1600 | 40712064 | Insulator-Steel | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Lakeville
119110368 | DI SBRNTE-GRZZLY-CLMNT #1 3/033 RPR FOND |  | SOBRNTE-GRIZZLY-CLARMNT #1+ | 003/033 | ICQ | F | 2020_(4) TD tag on high spread line | [5 empty] | Central | WSIP | [6 empty] | '-122.176491 | 37.8649 | ETL.3740 | 40607957 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay
119110381 | T3 DI EGL RCK-FLTN-SLVDO 36/182 RPL INSS | 31515212 | EAGLE ROCK-FULTON-SILVERADO | 036/182 | 92E | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.64095 | 38.4971 | ETL.4392 | 40712066 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Lakeville
119110424 | T3 DI RND MTN-CTTONWD #3 31/257 RPR FOND | 43932111 | ROUND MTN-COTTONWOOD #3 | 031/257 | ICQ | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.974225 | 40.7491 | ETL.5650 | 40810664 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
119110446 | T3 DI BEARDSLEY TAP 2/5C RPR GYWW |  | BEARDSLEY TAP | 002/005C | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-120.060421 | 38.1793 | ETL.1401 | 42834637 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog 401
119110480 | T3 DI EGL RCK-FLTN-SLVRD 38/192 RPL INSS | 31515212 | EAGLE ROCK-FULTON-SILVERADO | 038/192 | 92E | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.66908 | 38.497 | ETL.4392 | 40724682 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Lakeville
119110483 | T3 DI FULTON PUEBLO 38/192 RPL INSS | 31505500 | FULTON-PUEBLO | 038/192 | 92E | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.669118 | 38.4968 | ETL.1600 | 40724680 | Insulator-Steel | No Good/Out of Stdrd | Replace | PEND srdy | PEND | Out of Estimating, release date retracted due to expired/updated permit | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Lakeville
119110545 | T3 DI RND MTN-CTTONWD #3 29/240 RPR FOND | 43932111 | ROUND MTN-COTTONWOOD #3 | 029/240 | ICQ | F | 2020_(4) TD tag on high spread line |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.957067 | 40.7696 | ETL.5650 | 40594999 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
119110606 | T2 DI DIABLO-MESA X7/32 RMV HRDT | 44361566 | DIABLO-MESA | X007/032 | ICQ | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-120.804247 | 35.2934 | ETL.4620 | 40682856 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Pismo Beach |  | Y - 13
119110636 | DI BEARDSLEY TAP 000/006 INS GMKW |  | BEARDSLEY TAP | 000/006 | ICW | F | 2020_(3) On high spread structure | [5 empty] | Central | WSIP | [6 empty] | '-120.067372 | 38.2004 | ETL.1401 | 44889239 | Guy Wire Mark /Indic-Wood | Missing | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Victor
119110637 | DI BEARDSLEY TAP 000/006 RMV DEBRIS |  | BEARDSLEY TAP | 000/006 | ICW | F | 2020_(3) On high spread structure | [5 empty] | Central | WSIP | [6 empty] | '-120.067372 | 38.2004 | ETL.1401 | 44889239 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Victor
119110638 | DI BEARDSLEY TAP 000/006 RPL HRDD |  | BEARDSLEY TAP | 000/006 | ICW | E | 2020_(2) High fire spread TD |  |  |  |  | SCHD | Central | WSIP | [6 empty] | '-120.067372 | 38.2004 | ETL.1401 | 44889239 | Hardware-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Victor
119110658 | T3 DI MI-WUK-CURTIS 19/5R RPL STRW | 31505692 | ETL.1073.POLE.WDPS | 019/005 | 70Y | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-120.2343 | 38.0479 | ETL.1073 | 44837668 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 41
119110768 | DI SAN LUIS OBISPO-OCNO 16/79 RPL HRDW |  | SAN LUIS OBISPO-OCEANO | 016/079 | ICW | E | 2020_(2) High fire spread TD | [5 empty] | South | WSIP | [6 empty] | '-120.521409 | 35.0979 | ETL.3530 | 40810258 | Hardware-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - Prog 401
119110864 | DI GTS-MSTNG SW STA #1 1/10 RPR FOUND | 44361564 | SPARE T-LINE RECORD | 001/010 | ICQ | F | 2020_(1b) Lines with special commitments | [5 empty] | South | WSIP | [6 empty] | '-120.09719 | 36.1522 | ETL.2604 | 40582474 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - Prog 402
119110889 | DI MUSTANG SW STA-GREGG 21/91 RPR FOUND | 44361567 | GATES-GREGG | 021/091 | ICQ | F | 2020_(1b) Lines with special commitments |  |  |  |  | WECC | South | WSIP | [6 empty] | '-119.889514 | 36.3226 | ETL.4700 | 40581133 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 5
119110898 | T3 DI WEIMAR #1 9/137 RPLC STRW | 31506097 | WEIMAR #1 | 009/137 | 70Y | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.835468 | 39.0201 | ETL.7560 | 40913138 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento
119111137 | DI PIT #1-COTTONWOOD 009/078A RPR FOND | 44051409 | PIT #1-COTTONWOOD | 009/078A | ICQ | E | 2020_(4) TD tag on high spread line | [5 empty] | North Valley | WSIP | [6 empty] | '-121.648089 | 40.9114 | ETL.5390 | 40576647 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
119111138 | T2 DI KILARC-DESCHUTES A23/494 REFRAME | 31507071 | KILARC-DESCHUTES | A023/494 | 93E | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.255163 | 40.5639 | ETL.7300 | 40755256 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain
119111255 | T2 DI KILARC-DESCHUTS A23/494 RMV PL BUT | 43930440 | KILARC-DESCHUTES | A023/494 | ICW | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.255163 | 40.5639 | ETL.7300 | 40755256 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119111258 | T2 DI KILARC-DESCHUTS A23/494 CANCEL | 43930440 | KILARC-DESCHUTES | A023/494 | ICW | F | 2020_(4b) On structure in bucket 4 |  |  | CANCEL/CNCL | TR2 |  | North Valley | WSIP | [6 empty] | '-122.255163 | 40.5639 | ETL.7300 | 40755256 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119111295 | DI GATES-PANOCHE #1 0/4 RPR STRT | 44361571 | GATES-PANOCHE #1 | 000/004 | ICQ | E | 2020_(1b) Lines with special commitments |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.12857 | 36.1477 | ETL.4720 | 40753571 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 10
119111328 | DI GATES-PANOCHE #1 0/4 RPR SHLS | 44361501 | GATES-PANOCHE #1 | 000/004 | ICS | E | 2020_(1b) Lines with special commitments |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.12857 | 36.1477 | ETL.4720 | 40753571 | Shield Wire / OPGW-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  | Y - 10
119111345 | T3 DI CARIBOU-PALERMO :010/083 RPR STRT |  | CARIBOU-PALERMO | :010/083 | ICQ | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.272689 | 39.9931 | ETL.3190 | 40910324 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
119111347 | T3 DI CARIBOU-PALERMO :010/083 RPL INSS |  | CARIBOU-PALERMO | :010/083 | 93K | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.272689 | 39.9931 | ETL.3190 | 40920063 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain
119111436 | T3NT DI MIDDLE FRK-GLD HLL 2/20 RPR FOND | 44371599 | MIDDLE FORK-GOLD HILL | 002/020 | ICQ | F | 2020_(2) High fire spread TD |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.612675 | 39.0016 | ETL.5140 | 40597516 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento
119111532 | T3 DI UKH-HPLND-CLVRDL 13/4 RMV PLE BUTT | 44610700 | UKIAH-HOPLAND-CLOVERDALE | 013/004 | ICS | F | 2020_(4b) On structure in bucket 4 |  |  | Likely MAT error - delink to correct | TR3 |  | North Coast | WSIP | [6 empty] | '-122.99799 | 38.8444 | ETL.4050 | 44838830 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville
119111541 | T3 DI MIDDLE FORK-GOLD HLL 2/20 RPR SHDW | 44371780 | MIDDLE FORK-GOLD HILL | 002/020 | ICS | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.612675 | 39.0016 | ETL.5140 | 40597516 | Shield Wire / OPGW-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento
119111578 | T3NT DI VOLTA-DESCHUTES 3/070 INST MRKW | 43939089 | VOLTA-DESCHUTES | 003/070 | ICW | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.925362 | 40.4743 | ETL.8290 | 40759238 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | released 7-13-20
119111603 | T2 DI BRDGVLL-CTTONWD 10/100 RMV PL BUT | 43939216 | BRIDGEVILLE-COTTONWOOD | 010/100 | ICW | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.471567 | 40.389 | ETL.1110 | 44424541 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119111713 | T3 DI VOLTA-DESCHUTES 003/070 RPL HRDW | 43939089 | VOLTA-DESCHUTES | 003/070 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.925362 | 40.4743 | ETL.8290 | 40759238 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | released 7-13-20
119111785 | T2 DI VLY SPRGS-MRTL #1 4/4 REFRAME | 31506807 | VALLEY SPRINGS-MARTELL #1 | 004/004 | 93E | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-120.770398 | 38.2579 | ETL.8240 | 40754958 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Victor |  | Y - 24
119111810 | T2 DI CLGATE-GRASS VLY 3/073 RMV PL BUTT | 44365323 | COLGATE-GRASS VALLEY | 003/073 | ICW | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.134833 | 39.3212 | ETL.6490 | 40695676 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119111821 | T3 DI DRUM-RIO OSO #2 0/6 BENT MEMB | 44356575 | DRUM-RIO OSO #2 | 000/006 | ICQ | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.780496 | 39.2566 | ETL.1430 | 40815323 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento
119111823 | T2 DI VLY SPRGS-MRTL #1 4/4 RPR SPLICE |  | VALLEY SPRINGS-MARTELL #1 | 004/004 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-120.770398 | 38.2579 | ETL.8240 | 40754958 | Splice-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog 401
119111874 | 006/013 LIGHT DUTY STEEL POLE | 44610613 | KONOCTI-EAGLE ROCK | 006/013 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.772283 | 38.9058 | ETL.6861 | 44933137 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
119111953 | T3 DI DRM-GRS VLY-WMAR 4/109 RPR GYWW | 44364856 | DRUM-GRASS VALLEY-WEIMAR | 004/109 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.8033 | 39.2162 | ETL.6760 | 40693324 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119111992 | T3 DI DRM-GRS VLY-WMR 2/57 RMV BUTT | 44361666 | DRUM-GRASS VALLEY-WEIMAR | 002/057 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.778266 | 39.2355 | ETL.6760 | 40654105 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119112003 | T3NT DI DRM-GRS VLY-WMAR 4/109 RMV DBRIS | 44364845 | DRUM-GRASS VALLEY-WEIMAR | 004/109 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.8033 | 39.2162 | ETL.6760 | 40693324 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119112040 | T2 DI VLY SPRNGS-MRTL #1 6/4 RMV PL BUT |  | VALLEY SPRINGS-MARTELL #1 | 006/004 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-120.756621 | 38.2783 | ETL.8240 | 40768897 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 24
119112090 | T3 DI DRM-GRS VLY-WMR 2/57 RPR POLE | 44361667 | DRUM-GRASS VALLEY-WEIMAR | 002/057 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.778266 | 39.2355 | ETL.6760 | 40654105 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119112099 | T2 DI VLY SPRINGS-MRTL #1 6/4 RPL SPLICE |  | VALLEY SPRINGS-MARTELL #1 | 006/004 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-120.756621 | 38.2783 | ETL.8240 | 40768897 | Splice-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 24
119112103 | T2NT DI DIVIDE-CABRILLO #2 6/74 RMV STUB |  | DIVIDE-CABRILLO #2 | 006/074 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-120.433366 | 34.7434 | ETL.1370 | 40618728 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach
119112109 | T2 DI WEIMAR #1 3/45 RPR STRW | 44362373 | WEIMAR #1 | 003/045 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-120.95 | 39.0206 | ETL.7560 | 40913164 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119112116 | T3 ATASCADERO-CAYUCOS 3/035 RPL POLE | 31507005 | ATASCADERO-CAYUCOS | 003/035 | 70Y | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | South | WSIP | [6 empty] | '-120.732913 | 35.4645 | ETL.8480 | 40817233 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Pismo Beach |  | Y - 12
119112124 | T2 DI VLY SPRINGS-MRTL #1 6/4 INST MRKW |  | VALLEY SPRINGS-MARTELL #1 | 006/004 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-120.756621 | 38.2783 | ETL.8240 | 40768897 | Marker (i.e. signs)-Wood | Missing | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 24
119112251 | T2 DI MDDL FRK-GLD HILL 022/177 RPR GYWW | 44361893 | MIDDLE FORK-GOLD HILL | 022/177 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-120.904212 | 38.859 | ETL.5140 | 44557467 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119112252 | T2 DI MDDL FRK-GLD HILL 022/177 RPR GYWW | 44361893 | MIDDLE FORK-GOLD HILL | 022/177 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-120.904212 | 38.859 | ETL.5140 | 44557466 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119112256 | T3NT DI MORAGA-CLARE #1 2/21 INST MRKS |  | MORAGA-CLAREMONT #1 | 002/021 | ICS | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-122.200386 | 37.8595 | ETL.2700 | 40580781 | Marker (i.e. signs)-Steel | Missing | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - 7
119112260 | T2 DI CLGTE-GRS VLY 6/147 RMV DEBRIS | 44365323 | COLGATE-GRASS VALLEY | 006/147 | ICW | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.102287 | 39.294 | ETL.6490 | 40603839 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119112363 | T2 DI KILARC-DESCHUTES 4/99 RPR SPLW | 43930440 | KILARC-DESCHUTES | 004/099 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.923997 | 40.6225 | ETL.7300 | 44809991 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Released
119112535 | T2 DI ELK-GUALALA 64/1 RPR STRW |  | ELK-GUALALA | 064/001 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.542173 | 38.8121 | ETL.8410 | 40601544 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
119112559 | T2 DI CARIBOU-WSTWD 8/159 RMV PL BUTT |  | CARIBOU-WESTWOOD | 008/159 | HNA | F | 2020_(3) On high spread structure | Budget Owner (Veg/Land/Road) |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.07989 | 40.181 | ETL.6300 | 40591698 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Table Mountain
119112576 | T3 DI DRUM-SUMMIT#2 004/055A RPR INSW | 44365659 | DRUM-SUMMIT #2 | 004/055A | ICW | E | 2020_(1b) Lines with special commitments |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.704355 | 39.2924 | ETL.1450 | 40893025 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119112597 | T3 DI MORAGA-CLARE #1 2/21 INST HRDS | 44621674 | MORAGA-CLAREMONT #1 | 002/021 | ICS | E | 2020_(3) On high spread structure |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.200386 | 37.8595 | ETL.2700 | 40580781 | Hardware-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  |  | SVRPR
119112614 | T2 DI CARIBOU-WESTWOOD 8/159 RPR WDPKR |  | CARIBOU-WESTWOOD | 008/159 | HNA | E | 2020_(2) High fire spread TD | Budget Owner (Veg/Land/Road) |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.07989 | 40.181 | ETL.6300 | 40591698 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Table Mountain
119112659 | T3 DI IGNACIO-BOLINAS #1 8/88 RPL POLE |  | IGNACIO-BOLINAS #1 | 008/088 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.654775 | 38.0115 | ETL.7140 | 40657320 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
119112717 | T2 DI PARKWAY-MORAGA 9/54 RPR SHLS | 44609770 | PARKWAY-MORAGA | 009/054 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-122.233759 | 38.0065 | ETL.5930 | 40867736 | Shield Wire / OPGW-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Bay |  | Y - Prog 402
119112761 | T3 DI MORAGA-CLARE #1 2/21 RPL SPLS | 44621674 | MORAGA-CLAREMONT #1 | 002/021 | ICS | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.200386 | 37.8595 | ETL.2700 | 40580781 | Splice-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  |  | SVRPR
119112821 | T3 DI VOLTA-DESCHUTES 5/120 RPR STRW | 43939089 | VOLTA-DESCHUTES | 005/120 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.967662 | 40.4849 | ETL.8290 | 40700143 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | released 7-13-20
119112857 | T3 MIDDLE FORK-GLD HILL 033/240 RPL INSW | 31506654 | MIDDLE FORK-GOLD HILL | 033/240 | 93I | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.993412 | 38.7332 | ETL.5140 | 44316300 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Sacramento
119112928 | T3 DI MDDLE FRK-GLD HLL 20/160C RPL INSW | 31506651 | MIDDLE FORK-GOLD HILL | 020/160C | 93I | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.877038 | 38.8846 | ETL.5140 | 42569861 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Sacramento
119112930 | T3 DI WST PT VLLY SPNGS 4/56 RPL POLE | 31505998 | WEST POINT-VALLEY SPRINGS | 004/056 | 70Y | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-120.620975 | 38.3988 | ETL.8350 | 40803754 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor
119112931 | T3 DI FRNCH MDWS-MDL FRK 12/224 RPR POLE | 44365646 | FRENCH MEADOWS-MIDDLE FORK | 012/224 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.599252 | 39.0124 | ETL.6870 | 40751819 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119112953 | T3NT DI MIDL FRK-GLD HIL 33/240 INS MRKW | 44361895 | MIDDLE FORK-GOLD HILL | 033/240 | ICW | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.993412 | 38.7332 | ETL.5140 | 44558208 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119112966 | DI GTS-MSTNG SW STA #1 4/20 RPR FOUND | 44361564 | SPARE T-LINE RECORD | 004/020 | ICQ | F | 2020_(1b) Lines with special commitments | [5 empty] | South | WSIP | [6 empty] | '-120.056169 | 36.1672 | ETL.2604 | 40582477 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - Prog 402
119112978 | T3 DI DRUM-RIO OSO #1 0/8 RPL HRDT | 44371587 | DRUM-RIO OSO #1 | 000/008 | ICQ | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.783149 | 39.2567 | ETL.1420 | 40866001 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento
119112991 | T3 DI MDLE FRK-GLD HILL 8/67 SHIELD WIRE | 44371780 | MIDDLE FORK-GOLD HILL | 008/067 | ICS | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.723288 | 39.0018 | ETL.5140 | 40815981 | Shield Wire / OPGW-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento
119113026 | T3NT DI MDLE FRK-GLD HILL 8/67 INST MRKS | 44371782 | MIDDLE FORK-GOLD HILL | 008/067 | ICS | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.723288 | 39.0018 | ETL.5140 | 40815981 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento
119113140 | T3 DI MDLE FRK-GLD HILL 8/67 RPL BOLT | 44371783 | MIDDLE FORK-GOLD HILL | 008/067 | ICQ | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.723288 | 39.0018 | ETL.5140 | 40815981 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento
119113159 | DI STANISLAUS-MANTECA #2 26/153 RPR STRT |  | STANISLAUS-MANTECA #2 | 026/153 | ICQ | E | 2020_(4) TD tag on high spread line | [5 empty] | Central | WSIP | [6 empty] | '-120.751638 | 37.9284 | ETL.3820 | 40651750 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - 26
119113184 | T2 DI TRINITY-MAPLE CREEK 41/6 RPL INSW | 31507478 | TRINITY-MAPLE CREEK | 041/006 | 93I | E | 2020_(2) High fire spread TD |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.651528 | 40.7256 | ETL.8170 | 40855869 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Eureka
119113187 | T2 DI TRINITY-MPL CREEK 41/6 RMV DEBRIS | 44299848 | TRINITY-MAPLE CREEK | 041/006 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.652448 | 40.7258 | ETL.8170 | 40827993 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
119113233 | T3NT DI MORAGA-SN LEAND #3 5/41 RPR FOND |  | MORAGA-SAN LEANDRO #3 | 005/041 | ICQ | F | 2020_(4) TD tag on high spread line |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-122.121509 | 37.7737 | ETL.2790 | 40580825 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  | ACRP
119113235 | T3 DI MORAGA-SAN LEAND #3 5/41 RPR STRS |  | MORAGA-SAN LEANDRO #3 | 005/041 | ICS | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.121509 | 37.7737 | ETL.2790 | 40580825 | Structure-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  |  | ACRP
119113292 | T2 DI COLGATE-GRASS VLY 008/195 REFRAME | 31507018 | COLGATE-GRASS VALLEY | 008/195 | 93E | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.08744 | 39.2616 | ETL.6490 | 40868932 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Sacramento
119113313 | T3 DI DIABLO-MESA 03/016 RPR DAMS |  | DIABLO-MESA | X003/016 | ICS | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | South | WSIP | [6 empty] | '-120.808287 | 35.2327 | ETL.4620 | 40811237 | Damper-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Pismo Beach |  | Y - 13
119113356 | T3 DI BEARDSLEY TAP 02/05A RPR GYWW |  | BEARDSLEY TAP | 002/005A | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-120.060358 | 38.1794 | ETL.1401 | 40760580 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog 401
119113424 | T2 DI VLY SPRNGS-MRTL #1 9/15 RMV PL BUT |  | VALLEY SPRINGS-MARTELL #1 | 009/015 | ICW | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-120.775398 | 38.3284 | ETL.8240 | 40753644 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 24
119113458 | T2 DI BDGVL CTTNWD 12/117 RPR ADSS | 43939216 | BRIDGEVILLE-COTTONWOOD | 012/117 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.506113 | 40.393 | ETL.1110 | 44424455 | Shield Wire / OPGW-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119113495 | T3 DI DRM-GRSS VLLY-WMR B017/384 BUTT | 44361666 | DRUM-GRASS VALLEY-WEIMAR | B017/384 | ICW | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.964434 | 39.1314 | ETL.6760 | 40756938 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119113497 | T3 DI DRM-GRSS VLLY-WMR B17/384 RPR PL | 44361667 | DRUM-GRASS VALLEY-WEIMAR | B017/384 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.964434 | 39.1314 | ETL.6760 | 40756938 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119113517 | T3 DI IGNACIO-BOLINAS #1 9/104A RMV STUB |  | IGNACIO-BOLINAS #1 | 009/104A | ICW | E | 2020_(3) On high spread structure |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.657499 | 37.9899 | ETL.7140 | 40584912 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
119113583 | T3 DI MDDLFRK #1 1/18 RPL RPR POLE | 44361891 | MIDDLE FORK #1 | 001/018 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.599864 | 39.01 | ETL.8405 | 40589936 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119113588 | T3NT DI MDDLFRK #1 1/18 INSTALL NUMBR | 44361892 | MIDDLE FORK #1 | 001/018 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.599864 | 39.01 | ETL.8405 | 40589936 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119113635 | T3 DI MORAGA-OAKLAND J 5/41 RPL INSS | 31504873 | MORAGA-OAKLAND "J" | 005/041 | 93K | E | 2020_(4) TD tag on high spread line |  | Split Tag - Hanger and Insulator |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.121509 | 37.7737 | ETL.2760 | 40604525 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  |  | ACRP
119113771 | T3NT DI DRM-GSS VLY-WEI 4/96 RMV PL BUTT | 31507845 | DRUM-GRASS VALLEY-WEIMAR | 004/096 | 93J | F | 2020_(2) High fire spread TD |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.800939 | 39.2216 | ETL.6760 | 40756119 | Structure-Wood | Idle | Remove | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 673 | Sacramento
119113803 | T3 DI DRM-GRS VLY-WMAR 001/027A RPR PL | 44361667 | DRUM-GRASS VALLEY-WEIMAR | 001/027A | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.760277 | 39.2478 | ETL.6760 | 40766643 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119113861 | T3 DI DSBLA CNTRVL 3/40A RPR GYWW | 44356201 | DESABLA-CENTERVILLE | 003/040A | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.64251 | 39.8187 | ETL.6720 | 40751702 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119113881 | T3NT DI DSBLA CNTRVL 3/40A RMV BUTT |  | DESABLA-CENTERVILLE | 003/040A | ICW | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.64251 | 39.8187 | ETL.6720 | 40751702 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119113975 | T3 DI DRM-GRSS VLLY-WMAR 1/39 RPL POLE | 31418518 | DRUM-GRASS VALLEY-WEIMAR | 001/039 | 70Y | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.767674 | 39.2432 | ETL.6760 | 40813457 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento
119114033 | T3 DI GRN VLY-LLAGAS 5/45L RPR STRW | 44381541 | GREEN VALLEY-LLAGAS | 005/045 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | South | WSIP | [6 empty] | '-121.719251 | 37.0266 | ETL.1720 | 44513677 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  | Y - 10
119114036 | T3NT DI MORAGA-CASTR VLLY 4/20 RPR FOND |  | MORAGA-CASTRO VALLEY | 004/020 | ICQ | F | 2020_(4) TD tag on high spread line |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-122.111109 | 37.8173 | ETL.5250 | 40596489 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  | EBMUD
119114069 | DI KILARC-CEDAR CREEK 12/269 RPR GYWW | 43939119 | KILARC-CEDAR CREEK | 012/269 | ICW | E | 2020_(4) TD tag on high spread line | [5 empty] | North Valley | WSIP | [6 empty] | '-121.947718 | 40.7803 | ETL.7290 | 44774788 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119114079 | T3NT DI FULTON-PUEBLO 38/197 RPR FOUND |  | FULTON-PUEBLO | 038/197 | ICQ | F | 2020_(4) TD tag on high spread line |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.68717 | 38.4965 | ETL.1600 | 40818390 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville
119114164 | T3 DI DRUM-RIO OSO #1 07/79 REPL INSS | 31505600 | DRUM-RIO OSO #1 | 007/079 | 93K | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.874606 | 39.1945 | ETL.1420 | 40888171 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Sacramento
119114390 | T3 DI EGL RCK-REDBUD :8/46 RMV DEBRIS |  | EAGLE ROCK-REDBUD | :008/046 | ICS | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.691637 | 38.8861 | ETL.1480 | 40809073 | Structure-Steel | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville
119114497 | T3 DI BRDVLLE GRBRVLLE 7/2 RPR GYWW | 44300097 | BRIDGEVILLE-GARBERVILLE | 007/002 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.744254 | 40.4046 | ETL.6220 | 40661833 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
119114507 | T3 DI MNTA VSTA-JFFRSN#1 17/73 RPR FOND |  | MONTA VISTA-JEFFERSON #1 | 017/073 | ICQ | F | 2020_(4) TD tag on high spread line |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-122.304999 | 37.4307 | ETL.5220 | 40658426 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  | Huddart Park
119114510 | T3NT DI DRM-GS VL-WMR B17/396 RMV PL BUT | 44364845 | DRUM-GRASS VALLEY-WEIMAR | B017/396 | ICW | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.969701 | 39.1378 | ETL.6760 | 40814232 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119114530 | T3 DI DONNELLS-MI-WUK 0/2 RPR GYWW | 44623211 | DONNELLS-CURTIS | 000/002 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-120.034319 | 38.2449 | ETL.1400 | 44379629 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog 401
119114547 | T3 DI DONNELLS-MI-WUK 3/7 RPL HRDW | 44623212 | DONNELLS-CURTIS | 003/007 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-120.038515 | 38.1934 | ETL.1400 | 44922053 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog 401
119114572 | T3 DI FULTON-CALISTOGA 000/009 RPR STRW |  | FULTON-CALISTOGA | 000/009 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.445538 | 38.5144 | ETL.6880 | 40861400 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
119114578 | T3 DI MIDDLEFORK #1 002/041 REPAIR POLE | 44361891 | MIDDLE FORK #1 | 002/041 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.62107 | 39.0014 | ETL.8405 | 40766809 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119114579 | T3 DI MIDDLEFORK #1 002/041 REPULL GUY | 44361891 | MIDDLE FORK #1 | 002/041 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.62107 | 39.0014 | ETL.8405 | 40766809 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119114604 | T3 DI DONNELLS-MI-WUK 3/7 RPR STRW | 44623213 | DONNELLS-CURTIS | 003/007 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-120.038515 | 38.1934 | ETL.1400 | 44922053 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 40 | USFS
119114688 | T3 DI KILARC-CEDAR CREEK RPL STRW | 31506712 | KILARC-CEDAR CREEK | 002/065 | 70Y | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.923795 | 40.6941 | ETL.7290 | 40862151 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain
119114742 | T3 DI LAURELES-OTTER 13/11 RPR GYWW | 44392340 | LAURELES-OTTER | 013/011 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | South | WSIP | [6 empty] | '-121.866357 | 36.3866 | ETL.7380 | 40601872 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  | Y - 13
119114743 | T3NT DI LAURELES-OTTER 13/11 INST MRKW | 44392341 | LAURELES-OTTER | 013/011 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | South | WSIP | [6 empty] | '-121.866357 | 36.3866 | ETL.7380 | 40601872 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  | Y - 13
119114756 | T2NT DI MORRO BAY-MESA 7/32 RPR FOND | 44361574 | MORRO BAY-MESA | 007/032 | ICQ | F | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-120.754699 | 35.3153 | ETL.5290 | 40662879 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Pismo Beach |  | Y - 16
119114760 | T3 DI ATASCADERO-CAYUCOS 4/38 RPR CONDW |  | ATASCADERO-CAYUCOS | 004/038 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | South | WSIP | [6 empty] | '-120.742267 | 35.4644 | ETL.8480 | 40684718 | Conductor-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - 11
119114766 | DI LAURELES-OTTER 8/2 RPR WDPKR | 44392348 | LAURELES-OTTER | 008/002 | ICW | E | 2020_(2) High fire spread TD | [5 empty] | South | WSIP | [6 empty] | '-121.78934 | 36.4182 | ETL.7380 | 40701557 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  | Y - Prog 402
119114772 | T3 DI FLTN-CLSTG 6/4 RPR LADDER |  | FULTON-CALISTOGA | 006/004 | ICS | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.510496 | 38.5696 | ETL.6880 | 43599322 | Hardware-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville
119114828 | T3 DI DRUM-SPAULDING 005/120 RPR STRW | 44364850 | DRUM-SPAULDING | 005/120 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.703647 | 39.2945 | ETL.6770 | 40862144 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119114855 | T2 DI PHILO JCT-ELK 26/4 RPR STRW | 44610684 | PHILO JCT-ELK | 026/004 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.553037 | 39.0857 | ETL.7780 | 44751914 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
119114865 | T3 DI MDDLFK #1 1/29 RPL POLE | 31506388 | MIDDLE FORK #1 | 001/029 | 70Y | E | 2020_(1a) PSPS |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.606706 | 39.0025 | ETL.8405 | 40586047 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento
119114872 | T3 DI PIT #1-COTTONWOOD 34/286 RPR FOND | 44051409 | PIT #1-COTTONWOOD | 034/286 | ICQ | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-122.003937 | 40.7132 | ETL.5390 | 40817542 | Foundation/Concrete-Tower | Earth Covered Tower | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
119114879 | T3 DI DRUM-RIO OSO #1 1/020 RPR FOND | 44361671 | DRUM-RIO OSO #1 | 001/020 | ICQ | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.802754 | 39.2537 | ETL.1420 | 40582451 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento
119114892 | T3 DI DRUM-RIO OSO#2 1/12 RPL INSS | 31528394 | DRUM-RIO OSO #2 | 001/012 | 93K | E | 2020_(1a) PSPS |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.78987 | 39.2563 | ETL.1430 | 40683652 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Sacramento
119114893 | T3 DI DRUM-RIO OSO#2 1/12 INS BOLT | 44356575 | DRUM-RIO OSO #2 | 001/012 | ICQ | E | 2020_(1a) PSPS |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.78987 | 39.2563 | ETL.1430 | 40683652 | Hardware-Tower | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento
119114894 | T3 DI DRUM-RIO OSO#2 1/12 RPR FOND | 44356575 | DRUM-RIO OSO #2 | 001/012 | ICQ | E | 2020_(1a) PSPS |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.78987 | 39.2563 | ETL.1430 | 40683652 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento
119114895 | T3 DI FULTON-PUEBLO 021/097 RPR FOND |  | FULTON-PUEBLO | 021/097 | ICQ | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.377894 | 38.5012 | ETL.1600 | 40818829 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville
119114898 | T3 DI DRUM-RIO OSO#2 10/106A RPR SPLS | 44356576 | DRUM-RIO OSO #2 | 010/106A | ICS | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.933276 | 39.17 | ETL.1430 | 40913104 | Splice-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento
119114900 | T3 DI DRUM-RIO OSO #1 1/020 RPR SPLS | 44361672 | DRUM-RIO OSO #1 | 001/020 | ICS | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.802754 | 39.2537 | ETL.1420 | 40582451 | Splice-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento
119114903 | T2 DI TRINITY-MAPLE CRK 11/00 RPR GYWW | 44273074 | TRINITY-MAPLE CREEK | 011/000 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.111874 | 40.768 | ETL.8170 | 40906413 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
119114904 | T2 DI GARCIA TAP 0/4 RPR STRW | 44610601 | GARCIA TAP | 000/004 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.587777 | 38.8701 | ETL.8411 | 40770611 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
119114990 | T3NT DI W PNT-VLY SPRNGS 1/22 RMV PL BUT |  | WEST POINT-VALLEY SPRINGS | 001/022 | GAR | F | 2020_(2) High fire spread TD |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-120.578149 | 38.425 | ETL.8350 | 44911778 | Structure-Wood | Rotten | Stub |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 586 | Victor
119114991 | T3NT DI W PNT-VLY SPRNGS 1/23 RMV PL BUT |  | WEST POINT-VALLEY SPRINGS | 001/023 | GAR | F | 2020_(2) High fire spread TD |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-120.579364 | 38.4247 | ETL.8350 | 40856862 | Structure-Wood | Rotten | Stub |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 586 | Victor
119114992 | T3NT DI DONNELLS-MI-WUK 3/8 RMV PL BUTT |  | DONNELLS-CURTIS | 003/008 | GAR | F | 2020_(2) High fire spread TD |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-120.04049 | 38.1913 | ETL.1400 | 40869936 | Structure-Wood | Rotten | Stub |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 586 | Victor |  |  | FERC
119114997 | T3 DI PIT #1-COTTONWOOD 34/288 RPR FOND | 44051409 | PIT #1-COTTONWOOD | 034/288 | ICQ | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-122.005944 | 40.7108 | ETL.5390 | 40868818 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
119115009 | T3 DI MIDDLE FORK #1 8/121 RPR GYWW | 44365338 | MIDDLE FORK #1 | 008/121 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.728332 | 39.0038 | ETL.8405 | 40873841 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119115022 | T3NT DI MIDDLE FORK #1 8/122A INST GMKW | 44365334 | MIDDLE FORK #1 | 008/122A | ICW | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.729357 | 39.0046 | ETL.8405 | 40595340 | Guy Wire Mark /Indic-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119115023 | T3 DI MIDDLE FORK #1 8/122B RPR GYWW | 44365338 | MIDDLE FORK #1 | 008/122B | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.729369 | 39.0046 | ETL.8405 | 42569712 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119115053 | T3NT DI CLGATE-GRSS VLLY 5/134 RMV BUTT | 44361616 | COLGATE-GRASS VALLEY | 005/134 | ICW | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.107078 | 39.301 | ETL.6490 | 40874470 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119115056 | T3NT DI KILARC-CEDAR CRK 6/148 RMV STUB | 43939119 | KILARC-CEDAR CREEK | 006/148 | ICW | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.987757 | 40.7131 | ETL.7290 | 40600832 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119115058 | T3NT DI COLGATE-ALLGHANY 6/174 INST MRKW | 44356570 | COLGATE-ALLEGHANY | 006/174 | ICW | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.078334 | 39.3451 | ETL.6470 | 40905847 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119115059 | T3 DI COLGATE-ALLEGHANY 006/174 RPR POLE | 44345667 | COLGATE-ALLEGHANY | 006/174 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.078334 | 39.3451 | ETL.6470 | 40905847 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119115067 | T3 DI BEARDSLEY TAP 001/009 RPL X-BRACE | 31506058 | BEARDSLEY TAP | 001/009 | 93E | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-120.060243 | 38.1875 | ETL.1401 | 44390917 | Crossarm-Wood | No Good/Out of Stdrd | Replace | MAPP srdy | MAPP | Constructed and mapped | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Victor
119115084 | T2 DI TRINITY-MAPLE CREEK 8/15 RPR GYWW | 44273074 | TRINITY-MAPLE CREEK | 008/015 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.070906 | 40.7637 | ETL.8170 | 40906376 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
119115158 | T3 DI KILARC-CEDAR CREEK 8/190 RPR SPLW | 43939119 | KILARC-CEDAR CREEK | 008/190 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.987742 | 40.7325 | ETL.7290 | 40611087 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119115190 | T3 DI LAURELES-OTTER 008/000 RPR STRW | 44392342 | LAURELES-OTTER | 008/000 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | South | WSIP | [6 empty] | '-121.787395 | 36.4188 | ETL.7380 | 40617420 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  | Y - 13
119115192 | T3NT DI KILARC-CEDAR CRK 8/198 RMV STUB | 43939119 | KILARC-CEDAR CREEK | 008/198 | ICW | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.983625 | 40.7373 | ETL.7290 | 40877889 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119115193 | T3 DI KILARC-CEDAR CREEK 8/198 RPR GYWW | 43939119 | KILARC-CEDAR CREEK | 008/198 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.983625 | 40.7373 | ETL.7290 | 40877889 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119115194 | T3 DI DRM-GRSS VLLY-WEIMR 8/207 RPR STRW | 44361667 | DRUM-GRASS VALLEY-WEIMAR | 008/207 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.858097 | 39.1826 | ETL.6760 | 40756216 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119115199 | T3 DI IGNACIO-BOLINAS #1 010/109 RPR SPL |  | IGNACIO-BOLINAS #1 | 010/109 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.659423 | 37.9785 | ETL.7140 | 40809050 | Splice-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
119115240 | T2 DI BRDGEVLE-GRBRVLE 21/4 RMV PL BUTT | 44299809 | BRIDGEVILLE-GARBERVILLE | 021/004 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.759815 | 40.2279 | ETL.6220 | 40769355 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
119115267 | T3 DI KILARC-CEDAR CREEK 10/224 RPR GYWW | 43939119 | KILARC-CEDAR CREEK | 010/224 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.971115 | 40.7523 | ETL.7290 | 40677185 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119115466 | T3 DI LAURELES-OTTER WASH INSW | 44610149 | LAURELES-OTTER | 013/016 | ICW | E | 2020_(4) TD tag on high spread line |  |  | Likely MAT error - delink to correct | TR3 | LATE | South | WSIP | [6 empty] | '-121.87131 | 36.386 | ETL.7380 | 40855776 | Insulator | Contaminated | Ground Wash | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 622 | Moss Landing
119115673 | T3 DI RND MTN-CTNWD #3 34/288 RPR FOND | 43932111 | ROUND MTN-COTTONWOOD #3 | 034/288 | ICQ | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-122.005991 | 40.7111 | ETL.5650 | 40868288 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
119115772 | T3NT DI KILARC-CEDAR CRK 11/252 RMV STUB | 43939119 | KILARC-CEDAR CREEK | 011/252 | ICW | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.95676 | 40.7695 | ETL.7290 | 40592403 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119115774 | T3 DI LAURELES-OTTER 014/001 RPR STRW | 44610149 | LAURELES-OTTER | 014/001 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | South | WSIP | [6 empty] | '-121.873744 | 36.3858 | ETL.7380 | 40601881 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  | Y - 13
119115937 | T2 DI WEIMAR #1 000/008 RPR SPLW | 44345834 | WEIMAR #1 | 000/008 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-120.983034 | 39.0355 | ETL.7560 | 44913366 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119115992 | T3 DI CRESTA-RIO OSO 018/151 RPR FOND |  | CRESTA-RIO OSO | 018/151 | ICQ | E | 2020_(4b) On structure in bucket 4 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.483761 | 39.7013 | ETL.4590 | 40910166 | Foundation/Concrete-Tower | Earth Covered Tower | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
119115994 | T3 DI CRESTA-RIO OSO 018/151 RPL INSS | 31500129 | CRESTA-RIO OSO | 018/151 | 93K | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.483761 | 39.7013 | ETL.4590 | 40919905 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain
119116003 | DI GATES-PANOCHE #1 1/7 RPR FOND | 44361571 | GATES-PANOCHE #1 | 001/007 | ICQ | E | 2020_(1b) Lines with special commitments |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.135091 | 36.1553 | ETL.4720 | 40811166 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 10
119116004 | DI GATES-MUSTNG SW STA #1 4/22A RPR FOND | 44361564 | SPARE T-LINE RECORD | 004/022A | ICQ | F | 2020_(1b) Lines with special commitments | [5 empty] | South | WSIP | [6 empty] | '-120.047671 | 36.1702 | ETL.2604 | 40576158 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - Prog 402
119116008 | T3 DI BEARDSLEY TAP 002/005B RPR GYWW |  | BEARDSLEY TAP | 002/005B | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-120.060391 | 38.1793 | ETL.1401 | 42834636 | Guy Wire-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog 401
119116061 | T3 DI FULTON-PUEBLO 039/199 REPAIR STRS |  | FULTON-PUEBLO | 039/199 | ICS | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.693585 | 38.4969 | ETL.1600 | 40872212 | Structure-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville
119116074 | DI MUSTANG SW STA-GREGG 18/80A RPR FOND | 44361567 | GATES-GREGG | 018/080A | ICQ | F | 2020_(1b) Lines with special commitments |  |  |  |  | WECC | South | WSIP | [6 empty] | '-119.875068 | 36.2854 | ETL.4700 | 40575766 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 5
119116080 | T2 DI PHILO JCT-ELK-ELK 27/7 RPL INSW | 31506299 | PHILO JCT-ELK | 027/007 | 93I | E | 2020_(2) High fire spread TD |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.568018 | 39.0989 | ETL.7780 | 40819527 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSE erdy | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Lakeville
119116081 | T2 DI PHILO JCT-ELK-ELK 27/7 RPL XARM | 31506500 | PHILO JCT-ELK | 027/007 | 93E | E | 2020_(2) High fire spread TD |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.568018 | 39.0989 | ETL.7780 | 40819527 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSE erdy | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Lakeville
119116116 | T3 DI IGNACIO-BOLINAS#1 011/116 RPR GYWW |  | IGNACIO-BOLINAS #1 | 011/116 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.665735 | 37.9671 | ETL.7140 | 40827632 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
119116174 | T3NT DI GYSRS #3 CLVRDL 7/85 RMV DEBRIS | 44580896 | GEYSERS #3-CLOVERDALE | 007/085 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.940542 | 38.803 | ETL.1650 | 40808559 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
119116175 | T3 DI GYSRS #3 CLVRDL 7/85 RPR GYWW | 44580896 | GEYSERS #3-CLOVERDALE | 007/085 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.940542 | 38.803 | ETL.1650 | 40808559 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
119116194 | T2 DI CORTINA-MENDCNO #1 57/283 RPR FOND |  | CORTINA-MENDOCINO #1 | 057/283 | ICQ | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.141714 | 39.2363 | ETL.1330 | 40648772 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville
119116200 | T3 DI MDDLFK GLD HILL 16/135 RPR STRW | 44361894 | MIDDLE FORK-GOLD HILL | 016/135 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.848375 | 38.9152 | ETL.5140 | 40761211 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119116223 | T3 DI LAURELES-OTTER 12/0 RPR GYWW | 44392343 | LAURELES-OTTER | 012/000 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | South | WSIP | [6 empty] | '-121.843052 | 36.3947 | ETL.7380 | 40617443 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  | Y - 13
119116224 | T3 DI KILARC-CEDAR CRK 9/204 RPR STRW | 43939119 | KILARC-CEDAR CREEK | 009/204 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.980802 | 40.7407 | ETL.7290 | 40657254 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119116225 | T3 DI KILARC-CEDAR CRK 9/204 RPLC HRDW | 43939119 | KILARC-CEDAR CREEK | 009/204 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.980802 | 40.7407 | ETL.7290 | 40657254 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119116226 | T3 DI IGNACIO-BOLINAS #1 9/101 RPLC CRSW | 31506711 | IGNACIO-BOLINAS #1 | 009/101 | 93E | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.656368 | 37.9967 | ETL.7140 | 40861143 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Lakeville
119116228 | T3 DI DRUM-SPAULDING 4/100 RPL STRW | 31529083 | DRUM-SPAULDING | 004/100 | 70Y | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.71124 | 39.2856 | ETL.6770 | 40616116 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE erdy | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Sacramento
119116252 | T3 DI DRM-GRSS VLY-WR 6/167 REFRAME | 31506292 | DRUM-GRASS VALLEY-WEIMAR | 006/167 | 93E | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.83942 | 39.1992 | ETL.6760 | 40598631 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Sacramento
119116258 | T3NT DI DRM-GRSS VLY-WR 6/167 RMV PL BUT | 44361666 | DRUM-GRASS VALLEY-WEIMAR | 006/167 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.83942 | 39.1992 | ETL.6760 | 40598631 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119116264 | T3NT DI WST PNT-VLY SPG 2/29 RMV PL BUTT |  | WEST POINT-VALLEY SPRINGS | 002/029 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-120.588619 | 38.422 | ETL.8350 | 40768863 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Victor
119116270 | T3 DI COLGATE-ALLEGHANY 6/161 RPR POLE | 44346134 | COLGATE-ALLEGHANY | 006/161 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.085966 | 39.3408 | ETL.6470 | 40766590 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119116272 | T3 DI IGNACIO-BOLINAS #1 10/110 RMV STUB |  | IGNACIO-BOLINAS #1 | 010/110 | ICW | E | 2020_(3) On high spread structure |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.659548 | 37.9782 | ETL.7140 | 40588059 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
119116275 | T3 DI SLY CREEK TAP 1/10A RPR POLE | 44391954 | SLY CREEK TAP | 001/010A | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.137836 | 39.5697 | ETL.4221 | 40658758 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119116298 | T3 DI KILARC-DESCHUTES 0/1 RMV BUTT | 43930440 | KILARC-DESCHUTES | 000/001 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.872795 | 40.6778 | ETL.7300 | 40701858 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119116312 | T3 DI DEER CREEK-DRUM 001/030 RPR GRDWW | 44364857 | DEER CREEK-DRUM | 001/030 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.837432 | 39.2812 | ETL.6690 | 40874928 | Ground Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119116317 | T3 DI KILARC-CEDAR CREEK 9/206 RPLC HRDW | 43939119 | KILARC-CEDAR CREEK | 009/206 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.979987 | 40.7417 | ETL.7290 | 40770427 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119116320 | T3NT DI KILARC-CDR CRK 10/226 RMV PL BUT | 43939119 | KILARC-CEDAR CREEK | 010/226 | ICW | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.970125 | 40.7535 | ETL.7290 | 40759581 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119116340 | T3 DI KILARC-CEDAR CREEK 9/201 RPR INSW | 43939119 | KILARC-CEDAR CREEK | 009/201 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.9823 | 40.7389 | ETL.7290 | 40641432 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119116341 | T3NT DI KILARC-CEDAR CRK 9/201 RMV BUTT | 44406464 | KILARC-CEDAR CREEK | 009/201 | ICW | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.9823 | 40.7389 | ETL.7290 | 40617738 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119116346 | T3 DI LAURELES-OTTER 7/5 RPR STRW | 44392344 | LAURELES-OTTER | 007/005 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | South | WSIP | [6 empty] | '-121.77766 | 36.4231 | ETL.7380 | 40770243 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  | Y - 13
119116349 | T3 DI GEYSERS #3-CLOVRDALE 7/84 RPR STRW | 44580896 | GEYSERS #3-CLOVERDALE | 007/084 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.939793 | 38.8033 | ETL.1650 | 40819430 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
119116437 | T3 DI DRM-RIO OSO #1 3/31 RPR FOUNDATION | 44361671 | DRUM-RIO OSO #1 | 003/031 | ICQ | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.817876 | 39.2435 | ETL.1420 | 40581364 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento
119116444 | T3 DI DRM-GRS VLLY-WMR 8/208 RPR STRW | 44361667 | DRUM-GRASS VALLEY-WEIMAR | 008/208 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.859366 | 39.1815 | ETL.6760 | 40766735 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119116468 | T3 DI MIDDLE FORK #1 7/110 RPR INSW | 44365338 | MIDDLE FORK #1 | 007/110 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.717933 | 39.0037 | ETL.8405 | 40602856 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119116471 | T3 DI COLGATE-GRSS VALLY 7/167 RPL POLE | 31506254 | COLGATE-GRASS VALLEY | 007/167 | 70Y | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.09406 | 39.2793 | ETL.6490 | 40695701 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento
119116476 | T3 DI DRM-GRS VLY-WMR 4/104 RPLC POLE | 31506387 | DRUM-GRASS VALLEY-WEIMAR | 004/104 | 70Y | E | 2020_(1a) PSPS |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.802644 | 39.2183 | ETL.6760 | 40654100 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento
119116477 | T3 DI DRM-GRS VLY-WMR 4/104 RMV DEBRIS | 44361666 | DRUM-GRASS VALLEY-WEIMAR | 004/104 | ICW | F | 2020_(1a) PSPS |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.802644 | 39.2183 | ETL.6760 | 40654100 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119116484 | T3 DI MAPLE CRK-HOOPA 11/008B RPR GYWW | 44178090 | MAPLE CREEK-HOOPA | 011/008 | ICS | E | 2020_(4) TD tag on high spread line |  |  | Likely MAT error - delink to correct | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.769416 | 40.9017 | ETL.7490 | 44735735 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
119116507 | T3NT DI FULTON-PUEBLO 36/185 RPR FOUND |  | FULTON-PUEBLO | 036/185 | ICQ | F | 2020_(4) TD tag on high spread line |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.649733 | 38.4971 | ETL.1600 | 40750505 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville
119116516 | T3NT DI MORAGA-CASTRO VLLY 6/28 RPR FOND | 44623422 | MORAGA-CASTRO VALLEY | 006/028 | ICQ | F | 2020_(2) High fire spread TD |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-122.092321 | 37.79 | ETL.5250 | 40866247 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 9 | EBMUD
119116561 | T3 DI DRM-GRS VLY-WMR 3/75 REFRAME | 31506292 | DRUM-GRASS VALLEY-WEIMAR | 003/075 | 93E | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.791339 | 39.2304 | ETL.6760 | 40900625 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Sacramento
119116565 | T3 DI FRNCH MDWS-MDL FRK 12/237 RPL HRDW | 44365646 | FRENCH MEADOWS-MIDDLE FORK | 012/237 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.597109 | 39.023 | ETL.6870 | 40826825 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119116580 | T3 DI LAURELES-OTTER 8/3 RPR STRW | 44392345 | LAURELES-OTTER | 008/003 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | South | WSIP | [6 empty] | '-121.790198 | 36.4177 | ETL.7380 | 40668266 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  | Y - 13
119116651 | T3NT DI DRM GRS-GRSVLY WMR 0/23 RMV BUTT | 44361666 | DRUM-GRASS VALLEY-WEIMAR | 000/023 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.757064 | 39.2491 | ETL.6760 | 42549841 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119116732 | T3 DI KESWICK-TRINITY 0/22 RMV PL BUTT | 43661466 | KESWICK-TRINITY | 000/022 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-122.473438 | 40.6189 | ETL.7270 | 40576552 | Structure-Wood | Debris/Nest/etc. | Remove | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119116739 | T3NT DI MIDDLE FORK #1 2/43C INST NUMBR | 44361892 | MIDDLE FORK #1 | 002/043C | ICW | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.625059 | 39.0014 | ETL.8405 | 42569705 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119116741 | T3NT DI PTTSBRG-SAN RMN 10/41 RPR FOUND |  | PITTSBURG-SAN RAMON | 010/041 | ICQ | F | 2020_(4) TD tag on high spread line |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-121.880246 | 37.8978 | ETL.5490 | 40581140 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay
119116746 | T3 DI PTTSBRG-SAN RMN 10/41 RMV VEG |  | PITTSBURG-SAN RAMON | 010/041 | HNA | E | 2020_(4b) On structure in bucket 4 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-121.880246 | 37.8978 | ETL.5490 | 40581140 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Bay
119116753 | T3 DI ROND MTN-CTTNWD #3 33/281 CANCEL | 31504993 | ROUND MTN-COTTONWOOD #3 | 033/281 | 93K | E | 2020_(4) TD tag on high spread line |  |  | CANCEL/CNCL | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.999171 | 40.7193 | ETL.5650 | 40617505 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Table Mountain
119116763 | T3 DI DRM GRS-GRSVY WMR B18/402 RPL POLE | 31515654 | DRUM-GRASS VALLEY-WEIMAR | B018/402 | 70Y | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.971814 | 39.1413 | ETL.6760 | 40664712 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento
119116768 | T3 DI MDDL FRK-GLD HILL 6/131A RPR STRW | 44361894 | MIDDLE FORK-GOLD HILL | 016/131A | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.839252 | 38.9202 | ETL.5140 | 40593947 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119116794 | T3 DI ROND MTN-CTTNWD #3 33/281 RPL HRDT | 43932111 | ROUND MTN-COTTONWOOD #3 | 033/281 | ICQ | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.999325 | 40.7191 | ETL.5650 | 40591930 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
119116801 | T3 DI MIDDLE FORK #1 2/43C CANCEL | 44361891 | MIDDLE FORK #1 | 002/043C | ICW | E | 2020_(2) High fire spread TD |  |  | CANCEL/CNCL | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.625059 | 39.0014 | ETL.8405 | 42569705 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119116809 | T3 DI MIDDLE FORK #1 2/43B DUP CNCL | 44361891 | MIDDLE FORK #1 | 002/043B | ICW | E | 2020_(2) High fire spread TD |  |  | CANCEL/CNCL | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.625071 | 39.0014 | ETL.8405 | 42569704 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119116824 | T3NT DI GEYSERS #12-FULTON 0/3 RPR FOND | 44631264 | GEYSERS #12-FULTON | 000/003 | ICS | F | 2020_(2) High fire spread TD |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.778493 | 38.8017 | ETL.4750 | 41129168 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville
119116860 | T3NT DI MIDDLE FK #1 2/43B INST VIS STRP | 44361892 | MIDDLE FORK #1 | 002/043B | ICW | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.625071 | 39.0014 | ETL.8405 | 42569704 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119116861 | T2 DI KILARC-DESCHUTES 19/406 INST MRKW | 43930440 | KILARC-DESCHUTES | 019/406 | ICW | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.181682 | 40.5638 | ETL.7300 | 40817238 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119116862 | T2 DI KILARC-DESCHTES 19/406 RMV PL BUTT | 43930440 | KILARC-DESCHUTES | 019/406 | ICW | E | 2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.181682 | 40.5638 | ETL.7300 | 40817238 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119116863 | T2 DI KILARC-DESCHUTES 19/406 RPL SPLW | 43930440 | KILARC-DESCHUTES | 019/406 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.181682 | 40.5638 | ETL.7300 | 40817238 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119116866 | T3 DI VOLTA-DESCHTES 5/119 REFRAME CRSW | 31505200 | VOLTA-DESCHUTES | 005/119 | 93E | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.966973 | 40.4847 | ETL.8290 | 40592118 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  | released 7-13-20
119116869 | T3NT DI DRM-GRSS VLY-WIMR 0/18 INST MRKW | 44361666 | DRUM-GRASS VALLEY-WEIMAR | 000/018 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.755581 | 39.2504 | ETL.6760 | 40813455 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119116897 | T3 DI VOLTA-DESCHUTES 5/125 REFRAME CRSW | 31505200 | VOLTA-DESCHUTES | 005/125 | 93E | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.97269 | 40.4861 | ETL.8290 | 40816165 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  | released 7-13-20
119116915 | T3 DI VOLTA-DESCHUTES 0/8 RMV STUB | 43939089 | VOLTA-DESCHUTES | 000/008 | ICW | E | 2020_(4b) On structure in bucket 4 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.87309 | 40.4612 | ETL.8290 | 40827011 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | released 7-13-20
119116920 | T3 DI VOLTA-DESCHUTES 0/8 RPR STRW | 43939089 | VOLTA-DESCHUTES | 000/008 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.87309 | 40.4612 | ETL.8290 | 40827011 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | released 7-13-20
119116937 | T3NT DI MDDLE FRK #1 007/107 INST GMKW | 44365334 | MIDDLE FORK #1 | 007/107 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.713808 | 39.003 | ETL.8405 | 40874900 | Guy Wire Mark /Indic-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119116943 | DI UKIAH-HPAND-CLOVERDALE 11/9 RPR GYWW | 44610690 | UKIAH-HOPLAND-CLOVERDALE | 011/009 | ICW | E | 2020_(2) High fire spread TD | [5 empty] | North Coast | WSIP | [6 empty] | '-122.993389 | 38.8192 | ETL.4050 | 44310999 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
119116945 | T3 DI MORRO BAY-MESA 24/108 RPL INSS | 31501671 | MORRO BAY-MESA | 024/108 | 93K | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | South | WSIP | [6 empty] | '-120.541329 | 35.131 | ETL.5290 | 40886908 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 16
119116947 | T3 DI DIABLO-MESA 24/108 RPL INSS | 31510098 | DIABLO-MESA | 024/108 | 93K | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | South | WSIP | [6 empty] | '-120.541329 | 35.131 | ETL.4620 | 40886910 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 13
119116950 | DI UKIAH-HPLND-CLOVERDALE 11/9 INST MRKW |  | UKIAH-HOPLAND-CLOVERDALE | 011/009 | ICW | F | 2020_(3) On high spread structure | [5 empty] | North Coast | WSIP | [6 empty] | '-122.993389 | 38.8192 | ETL.4050 | 44310999 | Marker (i.e. signs)-Wood | Missing | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
119116990 | T3 DI DRM-GRSS VLY-WEIMR 000/018 RP GYWW | 44361667 | DRUM-GRASS VALLEY-WEIMAR | 000/018 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.755581 | 39.2504 | ETL.6760 | 40813455 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119116991 | T3NT DI DRM-GRSS VLY-WMR 0/018 RMV DBR | 44361666 | DRUM-GRASS VALLEY-WEIMAR | 000/018 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.755581 | 39.2504 | ETL.6760 | 40813455 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119116992 | T3 DI DRUM-SPAULDING 1/37 RMV PL BUTT | 44346133 | DRUM-SPAULDING | 001/037 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.743482 | 39.2574 | ETL.6770 | 40751870 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119116993 | T3 DI DRUM-SPAULDING 1/37 RPR SPLW | 44346133 | DRUM-SPAULDING | 001/037 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.743482 | 39.2574 | ETL.6770 | 40751870 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119116994 | T3 DI VOLTA-DESCHUTES 1/25 RPR GYWW | 43939089 | VOLTA-DESCHUTES | 001/025 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.88842 | 40.4652 | ETL.8290 | 40660881 | Guy Wire-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119116995 | T3NT DI VOLTA-DESCHUTES 1/25 RMV STUB | 43939089 | VOLTA-DESCHUTES | 001/025 | ICW | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.88842 | 40.4652 | ETL.8290 | 40660881 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119117021 | T3 DI FULTON-CALISTOGA 0/8 RPR INSS | 44597303 | FULTON-CALISTOGA | :000/008 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.58119 | 38.6037 | ETL.6880 | 44860477 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville
119117066 | T2 DI KILARC-DESCHUTES 2/56 RPL POLE | 31505377 | KILARC-DESCHUTES | 002/056 | 70Y | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.89531 | 40.6446 | ETL.7300 | 40577361 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Released
119117092 | T3 DI VOLTA DESCHUTES 5/127 RPR STRW | 43939089 | VOLTA-DESCHUTES | 005/127 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.974627 | 40.4866 | ETL.8290 | 40867830 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | released 7-13-20
119117118 | T3 DI CARIBOU-PALERMO :011/088 RMV STEP |  | CARIBOU-PALERMO | :011/088 | ICQ | F | 2020_(2) High fire spread TD |  |  |  | TR3 |  | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.280178 | 39.9882 | ETL.3190 | 40910328 | Hardware-Tower | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
119117153 | T3 DI KILARC-CDR CRK 11/246 RPR CNDW | 43939119 | KILARC-CEDAR CREEK | 011/246 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.959958 | 40.7656 | ETL.7290 | 40771266 | Conductor-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119117165 | T3 DI DRUM-HIGGINS 002/028C RPL STRW | 31508014 | DRUM-HIGGINS | 002/028C | 70Y | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.79575 | 39.2282 | ETL.4393 | 42550184 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento
119117175 | T3NT DI MIDDLEFORK #1 008/122B RMV STUB | 44365334 | MIDDLE FORK #1 | 008/122B | ICW | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.729369 | 39.0046 | ETL.8405 | 42569712 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119117178 | T3NT DI MIDDLEFORK #1 8/122B INST GMKW | 44365334 | MIDDLE FORK #1 | 008/122B | ICW | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.729369 | 39.0046 | ETL.8405 | 42569712 | Guy Wire Mark /Indic-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119117184 | T3 DI KILARC-CDR CRK 11/246 RMV DEBRIS | 43939119 | KILARC-CEDAR CREEK | 011/246 | ICW | E | 2020_(4b) On structure in bucket 4 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.959958 | 40.7656 | ETL.7290 | 40771266 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119117201 | T3 DI DRM-GRS VLY-WMAR B17/385 REPL POLE | 31515653 | DRUM-GRASS VALLEY-WEIMAR | B017/385 | 70Y | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.964823 | 39.1321 | ETL.6760 | 40824332 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE erdy | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento
119117216 | T3NT DI DESABLA-CENTERVLE 0/14 RMV BUTT |  | DESABLA-CENTERVILLE | 000/014 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.628197 | 39.8623 | ETL.6720 | 40751698 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119117219 | T3 DI DRM-GRS VLY-WMAR B17/385 RMV STUB | 44364852 | DRUM-GRASS VALLEY-WEIMAR | B017/385 | ICW | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.964823 | 39.1321 | ETL.6760 | 40824332 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119117226 | T3 DI CARIBOU-PALERMO :011/088 RPR SPLS |  | CARIBOU-PALERMO | :011/088 | ICS | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.280178 | 39.9882 | ETL.3190 | 40910328 | Splice-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain
119117234 | T3 DI DESABLA-CENTERVLE 0/14 RPR STRW |  | DESABLA-CENTERVILLE | 000/014 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.628197 | 39.8623 | ETL.6720 | 40751698 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119117243 | T3 DI MIDDLEFORK #1 8/122A RPR GYWW | 44365338 | MIDDLE FORK #1 | 008/122A | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.729357 | 39.0046 | ETL.8405 | 40595340 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119117267 | T3 DI KILARC-CEDAR CREEK 1/27 RPLC HRDW | 43939119 | KILARC-CEDAR CREEK | 001/027 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.893275 | 40.6852 | ETL.7290 | 44159598 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119117268 | T3 DI DESABLA-CENTERVILLE 4/45 RPR STRW | 44356201 | DESABLA-CENTERVILLE | 004/045 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.646132 | 39.8084 | ETL.6720 | 40700318 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119117274 | T3 DI VOLTA DESCHUTES 6/146 RPL STRW | 31506865 | VOLTA-DESCHUTES | 006/146 | 70Y | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.991033 | 40.4906 | ETL.8290 | 40862488 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain
119117290 | T2 BRDGVL-CTTNWD 30/251 RPR FOND | 43706644 | BRIDGEVILLE-COTTONWOOD | 030/251 | ICQ | F | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.830245 | 40.3645 | ETL.1110 | 40600474 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
119117299 | T3 DI VOLTA DESCHUTES 6/138 REFRAME CRSW | 31505200 | VOLTA-DESCHUTES | 006/138 | 93E | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.984325 | 40.4889 | ETL.8290 | 40615918 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  | released 7-13-20
119117318 | T3 DI KILARC-CEDAR CRK 010/237 RPR STRW | 43939119 | KILARC-CEDAR CREEK | 010/237 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.964302 | 40.7605 | ETL.7290 | 40752215 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119117333 | DI GATES-MUSTANG SW STA #1 2/21 RPR FOND | 44361564 | SPARE T-LINE RECORD | 002/011 | ICQ | F | 2020_(1b) Lines with special commitments | [5 empty] | South | WSIP | [6 empty] | '-120.093333 | 36.1536 | ETL.2604 | 40581379 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - Prog 402
119117334 | T3NT DI MIDDLE FORK #1 2/43A INST NUMBR | 44361892 | MIDDLE FORK #1 | 002/043A | ICW | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.625074 | 39.0014 | ETL.8405 | 40822833 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119117380 | T3 DI KILARC-CEDAR CRK 10/237 RMV STUB | 43939119 | KILARC-CEDAR CREEK | 010/237 | ICW | E | 2020_(4b) On structure in bucket 4 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.964302 | 40.7605 | ETL.7290 | 40752215 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119117408 | T3NT DI PITTSBURG-SN MAT 27/106 RPR FOND | 44623139 | PITTSBURG-SAN MATEO | 027/106 | ICQ | F | 2020_(2) High fire spread TD |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-122.00977 | 37.694 | ETL.5463 | 40581165 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 13
119117447 | T2 DI VLY SPRGS-MARTELL#1 3/18 RPR WDPKR |  | VALLEY SPRINGS-MARTELL #1 | 003/018 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-120.772631 | 38.255 | ETL.8240 | 40876069 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 24
119117522 | T3 DI VOLTA-DESCHUTES 3/86 RMV BUTT | 43939089 | VOLTA-DESCHUTES | 003/086 | ICW | E | 2020_(4b) On structure in bucket 4 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.939017 | 40.4777 | ETL.8290 | 40600280 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | released 7-13-20
119117537 | T3NT DI KILARC-CEDAR CRK 7/179 RMV STUB | 43939119 | KILARC-CEDAR CREEK | 007/179 | ICW | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.99317 | 40.7259 | ETL.7290 | 40873627 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119117538 | T3 DI KILARC-CEDAR CREEK 007/179 RPR INS | 43939119 | KILARC-CEDAR CREEK | 007/179 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.99317 | 40.7259 | ETL.7290 | 40898034 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119117539 | T3 DI COLGATE-ALLGHANY 007/192 RPR POLE | 44346106 | COLGATE-ALLEGHANY | 007/192 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.069579 | 39.351 | ETL.6470 | 40868948 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119117543 | T2NT DI SBNTGRZLYCLRMNT #1 2/24 RPR FOND |  | SOBRNTE-GRIZZLY-CLARMNT #1+ | 002/024 | ICQ | F | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-122.185475 | 37.8783 | ETL.3740 | 40862369 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay
119117548 | T3 DI DRUM-GRASS VLLY-WMR 1/44 RPR POLE | 44361667 | DRUM-GRASS VALLEY-WEIMAR | 001/044 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.770683 | 39.2405 | ETL.6760 | 44260558 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119117655 | T3 DI DRUM-RIO OSO #2 016/133 RPL INSS | 31503652 | DRUM-RIO OSO #2 | 016/133 | 93K | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.011487 | 39.1393 | ETL.1430 | 40683428 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Sacramento
119117671 | T3NT DI DSBL-CENTERVILLE 0/8 RMV PL BUTT |  | DESABLA-CENTERVILLE | 000/008 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.629918 | 39.8655 | ETL.6720 | 40862027 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119117686 | T3NT DI MIDDLEFK #1 6/88 INST VIS STRIP | 44365334 | MIDDLE FORK #1 | 006/088 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.686971 | 39.0022 | ETL.8405 | 40598766 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119117688 | T3 DI MIDDLEFORK #1 6/88 REPL HRDW | 44365338 | MIDDLE FORK #1 | 006/088 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.686971 | 39.0022 | ETL.8405 | 40598766 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119117691 | T3NT DI DEER CREEK-DRUM 2/61 RMV PL BUT | 44364857 | DEER CREEK-DRUM | 002/061 | ICW | F | 2020_(1a) PSPS |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.827108 | 39.2636 | ETL.6690 | 40757020 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119117715 | T3 DI VOLTA-DESCHUTES 4/100 RMV BUTT | 43939089 | VOLTA-DESCHUTES | 004/100 | ICW | E | 2020_(3) On high spread structure |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.950823 | 40.4806 | ETL.8290 | 40660889 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | released 7-13-20
119117716 | T3 DI VOLTA-DESCHUTES 4/100 RPR STRW | 43939089 | VOLTA-DESCHUTES | 004/100 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.950823 | 40.4806 | ETL.8290 | 40660889 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | released 7-13-20
119117737 | T3NT DI FULTON-IGNAC #1 016/085 RPR FOND | 44310479 | FULTON-IGNACIO #1 | 016/085 | ICQ | F | 2020_(4) TD tag on high spread line |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.592332 | 38.3898 | ETL.4680 | 40765347 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville
119117742 | T3NT DI MDLE FRK-GLD HILL 5/44 RPR FOND | 44371599 | MIDDLE FORK-GOLD HILL | 005/044 | ICQ | F | 2020_(2) High fire spread TD |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.668234 | 39.0011 | ETL.5140 | 40759034 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento
119117746 | T3 DI DRUM-RIO OSO #1 0/9 RPL SPLS | 44346102 | DRUM-RIO OSO #1 | 000/009 | ICS | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.78502 | 39.2562 | ETL.1420 | 40888163 | Splice-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento
119117766 | T3 DI CARIBOU-PALERMO :30/245 REPLC HRDS |  | CARIBOU-PALERMO | :030/245 | ICS | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.452493 | 39.7774 | ETL.3190 | 40787815 | Hardware-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain
119117768 | T3 DI CARIBOU-PALERMO :034/276 RPR FOND |  | CARIBOU-PALERMO | :034/276 | ICQ | E | 2020_(4b) On structure in bucket 4 |  |  |  | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.479471 | 39.7247 | ETL.3190 | 40828377 | Foundation/Concrete-Tower | Earth Covered Tower | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
119117790 | T3 DI DRUM-RIO OSO #1 1/14 RPR SPLS | 44346102 | DRUM-RIO OSO #1 | 001/014 | ICS | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.793092 | 39.256 | ETL.1420 | 40786128 | Splice-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento
119117810 | T3 DI COLGATE-ALLEGHANY 5/132 RPR POLE | 44346104 | COLGATE-ALLEGHANY | 005/132 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.101984 | 39.3318 | ETL.6470 | 40760699 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119117839 | T3 DI PIT #1-COTTONWOOD 33/283 RPR FOND | 44051409 | PIT #1-COTTONWOOD | 033/283 | ICQ | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-122.000886 | 40.7169 | ETL.5390 | 40657358 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
119117878 | T3NT DI VOLTA-DESCHUTES 6/131 RMV BUTT | 43939089 | VOLTA-DESCHUTES | 006/131 | ICW | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.978162 | 40.4875 | ETL.8290 | 40656917 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | released 7-13-20
119117918 | T2 DI TRINITY MAPLE CREEK 36/6 RPL SPLW | 44273074 | TRINITY-MAPLE CREEK | 036/006 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.571679 | 40.7183 | ETL.8170 | 40837327 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
119117921 | T2 DI TRINITY MAPLE CRK 36/6 RMV PL BUTT | 44299848 | TRINITY-MAPLE CREEK | 036/006 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.571679 | 40.7183 | ETL.8170 | 40810498 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
119117949 | T2 DI TRINITY MAPLE CRK 36/6 RPR GYWW | 44273074 | TRINITY-MAPLE CREEK | 036/006 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.571679 | 40.7183 | ETL.8170 | 40810498 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
119117958 | T3NT DI DRUM HIGGINS A5/51B RMV PL BUTT | 44365656 | DRUM-HIGGINS | A005/051B | ICW | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.835753 | 39.2151 | ETL.4393 | 42550227 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119118018 | T3 DI MDLE FRK-GLD HL 8/66 REPA SHLS | 44371780 | MIDDLE FORK-GOLD HILL | 008/066 | ICS | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.721857 | 39.0023 | ETL.5140 | 40820687 | Shield Wire / OPGW-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento
119118020 | T3 DI MDLE FRK-GLD HL 8/66 RPR INSS | 44371780 | MIDDLE FORK-GOLD HILL | 008/066 | ICS | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.721857 | 39.0023 | ETL.5140 | 40849542 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento
119118026 | T2 DI BRIDGEVILLE-CTNWD 31/258 RPR FOND | 43706644 | BRIDGEVILLE-COTTONWOOD | 031/258 | ICQ | F | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.84947 | 40.3633 | ETL.1110 | 40605507 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
119118052 | T3 DI IGNCO-BLINS #1 10/111A RPR GYWW |  | IGNACIO-BOLINAS #1 | 010/111A | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.660175 | 37.9765 | ETL.7140 | 40585009 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
119118054 | T3 DI IGNCO-BLINS #1 10/111B RPR GYWW |  | IGNACIO-BOLINAS #1 | 010/111 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.660207 | 37.9765 | ETL.7140 | 41111795 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
119118147 | T3 DI DIABLO-MESA X005/023 RPR JUMPER |  | DIABLO-MESA | X005/023 | ICS | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | South | WSIP | [6 empty] | '-120.808344 | 35.2595 | ETL.4620 | 40686660 | Jumper-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Pismo Beach |  | Y - 13
119118173 | T3 DI DIABLO-MESA X005/023 RPR SHLS |  | DIABLO-MESA | X005/023 | ICS | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | South | WSIP | [6 empty] | '-120.808344 | 35.2595 | ETL.4620 | 40656939 | Shield Wire / OPGW-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Pismo Beach |  | Y - 13
119118191 | T3 DI MORRO BAY-DIABL X005/023 RPL INSS | 31507782 | MORRO BAY-DIABLO | X005/023 | 93K | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | South | WSIP | [6 empty] | '-120.808344 | 35.2595 | ETL.5260 | 44690748 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 4
119118206 | T2 DI CLGATE-GRASS VALEY 3/76 RPR WDPKR | 44365328 | COLGATE-GRASS VALLEY | 003/076 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.132677 | 39.3211 | ETL.6490 | 40760389 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119118207 | T3NT DI CLGTE ALLGHNY 6/175 INST MRKW | 44356570 | COLGATE-ALLEGHANY | 006/175 | ICW | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.078039 | 39.3453 | ETL.6470 | 40875293 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119118214 | T3 DI CLGTE ALLGHNY 6/175 RPR POLE | 44346079 | COLGATE-ALLEGHANY | 006/175 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.078039 | 39.3453 | ETL.6470 | 40875293 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119118240 | T3 DI DIABLO-MESA X004/022 RPR OPGW |  | DIABLO-MESA | X004/022 | ICS | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | South | WSIP | [6 empty] | '-120.807354 | 35.2523 | ETL.4620 | 40682852 | Shield Wire / OPGW-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Pismo Beach |  | Y - 13
119118256 | T3NT DI CLGTE ALLGHNY 6/162 RMV STUB | 44356570 | COLGATE-ALLEGHANY | 006/162 | ICW | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.085202 | 39.3412 | ETL.6470 | 40824244 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119118260 | T3NT DI CLGTE ALLGHNY 6/162 INST MRKW | 44356570 | COLGATE-ALLEGHANY | 006/162 | ICW | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.085202 | 39.3412 | ETL.6470 | 40824244 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119118261 | T2 DI SALINAS-LAURELES 17/323 RPL INSW | 31507341 | SALINAS-LAURELES | 017/323 | 93I | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-121.73109 | 36.4965 | ETL.7930 | 40640126 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Moss Landing |  | Y - Prog 401
119118262 | T3 DI CLGTE ALLGHNY 6/162 RPR POLE | 44346079 | COLGATE-ALLEGHANY | 006/162 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.085202 | 39.3412 | ETL.6470 | 40824244 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119118263 | T2 DI CLGTE-SMARTVILLE #2 4/47 RPL POLE | 31507078 | COLGATE-SMARTVILLE #2 | 004/047 | 70Y | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.248594 | 39.2987 | ETL.6520 | 40594297 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento
119118265 | T2 DI CLGT-GRASS VLY 5/125 RPR GYWW | 44365328 | COLGATE-GRASS VALLEY | 005/125 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.110397 | 39.3058 | ETL.6490 | 40603836 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119118297 | T3 DI KILARC-CEDAR CRK 8/199 RPR STRW | 43939119 | KILARC-CEDAR CREEK | 008/199 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.983077 | 40.738 | ETL.7290 | 40868039 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119118311 | T3NT DI KILARC-CEDAR CRK 8/199 RMV STUB | 43939119 | KILARC-CEDAR CREEK | 008/199 | ICW | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.983077 | 40.738 | ETL.7290 | 40868039 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119118332 | T3 DI COLGATE-GRASS VALLY 5/137 RPL CRSW | 31506252 | COLGATE-GRASS VALLEY | 005/137 | 93E | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.106155 | 39.2996 | ETL.6490 | 40679384 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Sacramento
119118333 | T3NT DI CLGTE-GRSS VLLY 6/163 INST MRKW | 44361616 | COLGATE-GRASS VALLEY | 006/163 | ICW | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.094973 | 39.2815 | ETL.6490 | 40825362 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119118334 | T3 DI CLGTE-GRSS VLLY 6/163 RPR OPGW | 44361619 | COLGATE-GRASS VALLEY | 006/163 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.094973 | 39.2815 | ETL.6490 | 40825362 | Shield Wire / OPGW-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119118335 | T3NT DI FULTON IGNACI #1 17/86 RPR FOUND | 44310479 | FULTON-IGNACIO #1 | 017/086 | ICQ | F | 2020_(4) TD tag on high spread line |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.592421 | 38.3835 | ETL.4680 | 40811759 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville
119118424 | T3NT DI COLGATE-GRSS VLY 6/157 RMV BUTT | 44361616 | COLGATE-GRASS VALLEY | 006/157 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.096818 | 39.2859 | ETL.6490 | 40612744 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119118450 | T3 DI COLGATE-GRSS VLY 5/142 RPL INSW | 31506253 | COLGATE-GRASS VALLEY | 005/142 | 93I | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.103753 | 39.2961 | ETL.6490 | 40851085 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Sacramento
119118451 | T3NT DI COLGATE-GRSS VLY 5/142 RMV BUTTS | 44361616 | COLGATE-GRASS VALLEY | 005/142 | ICW | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.103753 | 39.2961 | ETL.6490 | 40823818 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119118529 | T2 DI COLGTE-GRSS VLLY 002/063 INST MRKW | 44365323 | COLGATE-GRASS VALLEY | 002/063 | ICW | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.141927 | 39.3219 | ETL.6490 | 40869622 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119118602 | T2 DI TRINITY-MAPLE CREEK 4/5 RPR GYWW | 44273074 | TRINITY-MAPLE CREEK | 004/005 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.009752 | 40.7352 | ETL.8170 | 40906306 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
119118607 | T2 DI CLGTE-SMARTVILLE #2 4/55 RPR GYWW | 44365320 | COLGATE-SMARTVILLE #2 | 004/055 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.256871 | 39.2892 | ETL.6520 | 40864696 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119118608 | T2 DI CLGTE-SMARTVILLE #2 7/85 RPR GYWW | 44371197 | COLGATE-SMARTVILLE #2 | 007/085 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.287464 | 39.2569 | ETL.6520 | 40602839 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119118621 | T3NT DI DONNELLS-MI-WUK 7/1 INST MRKW | 44623214 | DONNELLS-CURTIS | 007/001 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-120.090118 | 38.1706 | ETL.1400 | 40579646 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog 401
119118623 | T3 DI DONNELLS-MI-WUK 7/1 RMV PL BUTT | 44623215 | DONNELLS-CURTIS | 007/001 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-120.090118 | 38.1706 | ETL.1400 | 40579646 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  |  | FERC
119118624 | T3 DI DONNELLS-MI-WUK 7/1 RPR INSW | 44623216 | DONNELLS-CURTIS | 007/001 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-120.090118 | 38.1706 | ETL.1400 | 40603180 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog 401
119118627 | T2 DI COLGATE-GRASS VLLY 3/84 RPL POLE | 31514628 | COLGATE-GRASS VALLEY | 003/084 | 70Y | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.127437 | 39.3206 | ETL.6490 | 40760678 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento
119118642 | T3NT DI DRUM-SUMMIT #2 4/50A RMV DEBRIS | 44371595 | DRUM-SUMMIT #2 | 004/050A | ICW | F | 2020_(1b) Lines with special commitments |  |  |  | TR3 | WECC | North Valley | WSIP | [6 empty] | '-120.708729 | 39.2871 | ETL.1450 | 40761541 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119118684 | T2 DI CARIBOU #2 000/027 RPR GYWW |  | CARIBOU #2 | 000/027 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.156424 | 40.0796 | ETL.6280 | 40815719 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119118687 | T3NT DI COLGATE-ALGHANY 8/232 INST MRKW | 44356570 | COLGATE-ALLEGHANY | 008/232 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.04869 | 39.3654 | ETL.6470 | 40598545 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119118688 | T3 DI COLGATE-ALLGHANY 008/232 RPR POLE | 44356570 | COLGATE-ALLEGHANY | 008/232 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.04869 | 39.3654 | ETL.6470 | 40598545 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119118710 | T2 DI KILARC-DESCHUTES 005/113 RPL POLE | 31507070 | KILARC-DESCHUTES | 005/113 | 70Y | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.933605 | 40.6173 | ETL.7300 | 40876550 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain
119118721 | T2 DI TRINITY-MAPLE CREEK 3/6 INST MRKW | 44273074 | TRINITY-MAPLE CREEK | 003/006 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.988451 | 40.7317 | ETL.8170 | 40906286 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
119118762 | T3NT DI LAURELES OTTER 10/0 RMV PL BUTT | 44392350 | LAURELES-OTTER | 010/000 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | South | WSIP | [6 empty] | '-121.819478 | 36.415 | ETL.7380 | 44563002 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  | Y - 13
119118766 | T3 DI LAURELES OTTER 10/0 RMV PL BUTT | 44392351 | LAURELES-OTTER | 010/000 | ICW | E | 2020_(3) On high spread structure |  |  |  | TR3 |  | South | WSIP | [6 empty] | '-121.819478 | 36.415 | ETL.7380 | 44562891 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  | Y - 13
119118769 | T3 DI VOLTA-DESCHUTES 7/159 REFRAME CRSW | 31505200 | VOLTA-DESCHUTES | 007/159 | 93E | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-122.003277 | 40.4934 | ETL.8290 | 40601160 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain
119118770 | T2 DI TRINITY-MAPLE CRK 010/015 RPR GYWW | 44273074 | TRINITY-MAPLE CREEK | 010/015 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.105256 | 40.7681 | ETL.8170 | 43950784 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
119118777 | T2 DI CAYUCOS-CAMBRIA 015/110 RPR WDPKR |  | CAYUCOS-CAMBRIA | 015/110 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-121.074404 | 35.582 | ETL.8560 | 40871956 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - 13
119118786 | T2 DI TRINITY-MPLE CREEK 8/7 RMV DEBRIS | 44299848 | TRINITY-MAPLE CREEK | 008/007 | ICW | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.065517 | 40.7569 | ETL.8170 | 40906368 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
119118797 | T2 DI COLGAT-SMTVLL #2 8/99 RMV PL BUTT | 44371197 | COLGATE-SMARTVILLE #2 | 008/099 | ICW | E | 2020_(1a) PSPS |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.29558 | 39.2393 | ETL.6520 | 40876773 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119118801 | T2 DI CARIBOU #2 3/26 RPLC INSW | 31505337 | CARIBOU #2 | 003/026 | 93I | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.20228 | 40.0593 | ETL.6280 | 40855024 | Insulator-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Table Mountain
119118811 | T3NT DI KLRC CDR CRK 6/156 RMV PL BUTT | 43939119 | KILARC-CEDAR CREEK | 006/156 | ICW | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.994445 | 40.7152 | ETL.7290 | 40877862 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119118817 | T2 DI CRNA MNDCNO 31 27/133 RPR FOUND |  | CORTINA-MENDOCINO #1 | 027/133 | ICQ | F | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.692826 | 39.0301 | ETL.1330 | 40648763 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville
119118839 | T3 DI ROND MTN-CTTNWD #3 33/285 RPL HRDT | 43932111 | ROUND MTN-COTTONWOOD #3 | 033/285 | ICQ | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-122.003174 | 40.7145 | ETL.5650 | 40758845 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
119118853 | T2 DI SLNS LRLS LRLS 16/316B RPL POLE | 31507415 | SALINAS-LAURELES | 016/316B | 70Y | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-121.744762 | 36.5043 | ETL.7930 | 42564785 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Moss Landing |  | Y - 12
119118869 | T2 DI PARKWAY-MORAGA 9/55 RMV IDLE | 44609771 | PARKWAY-MORAGA | 009/055 | ICS | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-122.233796 | 38.0051 | ETL.5930 | 40576197 | Structure-Steel | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay
119118870 | T3NT DI W PNT-VLY SPRNGS 1/27 RMV PL BUT | 44595071 | WEST POINT-VALLEY SPRINGS | 001/027 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-120.586356 | 38.423 | ETL.8350 | 40697166 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor
119118877 | T2 DI KILARC-DESCHUTES 8/169 RMV PL BUTT | 43930440 | KILARC-DESCHUTES | 008/169 | ICW | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.978156 | 40.5972 | ETL.7300 | 40771367 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Released
119118890 | T2 DI CLGT GRSS VLLY 9/217B RMV PL BUTT | 44365323 | COLGATE-GRASS VALLEY | 009/217 | ICW | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.083287 | 39.2471 | ETL.6490 | 44975418 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119118901 | T2 DI COLGATE-GRASS VLY 3/72 RMV PL BUTT | 44371194 | COLGATE-GRASS VALLEY | 003/072 | ICW | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.135423 | 39.3213 | ETL.6490 | 40590716 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119118902 | T2 DI CARIBOU #2 4/16 RMV STEP |  | CARIBOU #2 | 004/016 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.20692 | 40.053 | ETL.6280 | 40816768 | Hardware-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119118906 | T2 DI TRINITY-MAPLE CREK 21/7 RMV PL BUT | 44299848 | TRINITY-MAPLE CREEK | 021/007 | ICW | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.293377 | 40.7094 | ETL.8170 | 40803410 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
119118931 | T2 DI CLGT GRSS VLLY 9/217A RPR GYWW | 44365328 | COLGATE-GRASS VALLEY | 009/217 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.083241 | 39.2471 | ETL.6490 | 44975419 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119118942 | T2 DI KILARC-DESCHUTES 2/55 RMV PL BUTT | 43930440 | KILARC-DESCHUTES | 002/055 | ICW | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.895151 | 40.6447 | ETL.7300 | 40656957 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Released
119118952 | T2 DI COLGTE-GRSS VLLY 003/075 INST MRKW | 44365323 | COLGATE-GRASS VALLEY | 003/075 | ICW | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.133715 | 39.3211 | ETL.6490 | 40768368 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119118953 | T2 DI CLGTE-GRSS VLLY 03/075 RMV PL BUTT | 44365323 | COLGATE-GRASS VALLEY | 003/075 | ICW | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.133715 | 39.3211 | ETL.6490 | 40768368 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119118955 | T3 DI VOLTA-DESCHUTES 003/081 RMV BUTT | 43939089 | VOLTA-DESCHUTES | 003/081 | ICW | E | 2020_(4b) On structure in bucket 4 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.93473 | 40.4767 | ETL.8290 | 40769424 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119118960 | T2 DI KESWICK-TRINITY 025/417 RPR GYWW | 43939188 | KESWICK-TRINITY | 025/417 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-122.851102 | 40.7024 | ETL.7270 | 40909460 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119118961 | T2 DI KSWICK-TRINITY 025/417 RMV PL BUTT | 43939188 | KESWICK-TRINITY | 025/417 | ICW | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.851102 | 40.7024 | ETL.7270 | 40909460 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119118996 | T2 DI COLGATE-GRASS VLY 2/61 REFRAME | 31507018 | COLGATE-GRASS VALLEY | 002/061 | 93E | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.143277 | 39.322 | ETL.6490 | 40818452 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Sacramento
119119002 | T2 DI KLRC DSCHTS 7/151 RPL POLE | 31507070 | KILARC-DESCHUTES | 007/151 | 70Y | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.966776 | 40.6064 | ETL.7300 | 40816220 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Released
119119003 | T2 DI KLRC DSCHTS 7/151 RMV PL BUTT | 43930440 | KILARC-DESCHUTES | 007/151 | ICW | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.966776 | 40.6064 | ETL.7300 | 40816220 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Released
119119005 | T2 DI KLRC DSCHTS A23/493 RPR GYWW | 43930440 | KILARC-DESCHUTES | A023/493 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.253713 | 40.5639 | ETL.7300 | 44141990 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119119038 | T3 DI VOLTA-DESCHUTES 004/090 RPR STRW | 43939089 | VOLTA-DESCHUTES | 004/090 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.942033 | 40.4784 | ETL.8290 | 40669476 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | released 7-13-20
119119050 | T2 DI CLGT SMTVLL #2 8/97 RPL POLE | 31511059 | COLGATE-SMARTVILLE #2 | 008/097 | 70Y | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.293653 | 39.2435 | ETL.6520 | 40826284 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento
119119058 | T2 DI LAURELES-OTTER 1/4 RPR WDPKR | 44587870 | LAURELES-OTTER | 001/004 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-121.713582 | 36.4656 | ETL.7380 | 40769033 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  | Y - 13
119119059 | T2 DI CLGT GRSS VLLY 0/10 RPL POLE | 31507019 | COLGATE-GRASS VALLEY | 000/010 | 70Y | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.181937 | 39.3278 | ETL.6490 | 40868924 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento
119119078 | T2 DI TRINITY-MAPLE CRK 15/1 RMV PL BUTT | 44299848 | TRINITY-MAPLE CREEK | 015/001 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.176107 | 40.7469 | ETL.8170 | 40579624 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
119119084 | T2 DI COLGTE-GRSS VLY 004/109 RPR SPLICE | 44365328 | COLGATE-GRASS VALLEY | 004/109 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.114985 | 39.3144 | ETL.6490 | 40696032 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119119089 | T3 DI COLGATE-ALLEGHANY 004/119 RPR POLE | 44346079 | COLGATE-ALLEGHANY | 004/119 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.108663 | 39.328 | ETL.6470 | 40874807 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119119092 | T3NT DI DRM-GRSS VLY-WIM 8/201 RMV BUTT | 44364845 | DRUM-GRASS VALLEY-WEIMAR | 008/201 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.855296 | 39.185 | ETL.6760 | 40874779 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119119110 | T3NT DI KILARC-DESCHUTES 0/12 INST MRKW | 43930440 | KILARC-DESCHUTES | 000/012 | ICW | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.87414 | 40.6701 | ETL.7300 | 40656952 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Released
119119111 | T3 DI KILARC-DESCHUTES 0/12 REFRAME CRSW | 43930440 | KILARC-DESCHUTES | 000/012 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.87414 | 40.6701 | ETL.7300 | 40656952 | Crossarm-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Released
119119118 | T2 DI LAURELES-OTTER 1/3 RPL INSW | 31507239 | LAURELES-OTTER | 001/003 | 93I | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-121.712631 | 36.4665 | ETL.7380 | 40697709 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Moss Landing |  | Y - 13
119119126 | T2 DI DIABLO MESA 5/27 RPL INSS | 31510098 | DIABLO-MESA | 005/027 | 93K | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-120.772358 | 35.3274 | ETL.4620 | 40835757 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 13
119119132 | T3 DI VOLTA-DESCHUTES 006/130 RPL CRSW | 31505200 | VOLTA-DESCHUTES | 006/130 | 93E | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.97745 | 40.4873 | ETL.8290 | 40700066 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  | released 7-13-20
119119139 | T3 DI FULTON-CALISTOGA :8/0 RPR STRW | 44597303 | FULTON-CALISTOGA | :008/000 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.59817 | 38.6996 | ETL.6880 | 40912490 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
119119149 | T2 DI CAYUCOS-CAMBRIA 18/131 RPR GYWW |  | CAYUCOS-CAMBRIA | 018/131 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-121.107473 | 35.5977 | ETL.8560 | 40606220 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - Prog 401
119119162 | T3 DI BRUNSWICK #1 TAP 0/6 RPR FOND | 44370736 | BRUNSWICK #1 TAP | 000/006 | ICQ | F | 2020_(4) TD tag on high spread line |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.012471 | 39.1503 | ETL.1422 | 40822534 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento
119119163 | T3NT DI DRUM-SPAULDING 3/82 RMV BUTT | 44364848 | DRUM-SPAULDING | 003/082 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.724231 | 39.281 | ETL.6770 | 40769530 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119119164 | T3 DI DRUM-SPAULDING 3/82 RPR STRW | 44364850 | DRUM-SPAULDING | 003/082 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.724231 | 39.281 | ETL.6770 | 40769530 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119119184 | T3 DI VOLTA DESCHUTES 3/69 RPR STRW | 43939089 | VOLTA-DESCHUTES | 003/069 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.924482 | 40.4741 | ETL.8290 | 40667432 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119119186 | T2 DI CLGT SMTVLL #2 8/98 RPL POLE | 31511059 | COLGATE-SMARTVILLE #2 | 008/098 | 70Y | E | 2020_(1a) PSPS |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.294848 | 39.2409 | ETL.6520 | 40864688 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento
119119189 | T2 DI TRNTY-MPLE CRK 18/5 CANCEL | 44299848 | TRINITY-MAPLE CREEK | 018/005 | ICW | F | 2020_(4b) On structure in bucket 4 |  |  | CANCEL/CNCL | TR2 |  | North Coast | WSIP | [6 empty] | '-123.23111 | 40.7365 | ETL.8170 | 40761915 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
119119210 | T3 DI DRUM-SPAULDING 2/65 RPL STRW | 31529083 | DRUM-SPAULDING | 002/065 | 70Y | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.733517 | 39.273 | ETL.6770 | 40616113 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE erdy | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Sacramento
119119221 | DI CAYUCOS-CAMBRIA 009/057 RPl XARM | 31507414 | CAYUCOS-CAMBRIA | 009/057 | 93E | E | 2020_(4) TD tag on high spread line | [5 empty] | South | WSIP | [8 empty] | ETL.8560 | 44171797 | Crossarm-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Pismo Beach
119119222 | T2 DI COLGTE-GRSS VLLY 9/225 RMV PL BUTT | 44365323 | COLGATE-GRASS VALLEY | 009/225 | ICW | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.08203 | 39.2426 | ETL.6490 | 40665609 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119119224 | T2 DI COLGTE-GRSS VLLY 9/226 RPR WDPKR | 44365328 | COLGATE-GRASS VALLEY | 009/226 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.08186 | 39.2421 | ETL.6490 | 40760646 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119119239 | T3 DI DRUM-RIO OSO #2 003/032 RMV HRDT | 44361673 | DRUM-RIO OSO #2 | 003/032 | ICS | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.818817 | 39.2423 | ETL.1430 | 40672175 | Hardware-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento
119119243 | T3 DI VOLTA DESCHUTES 5/122 RPL STRW | 31507067 | VOLTA-DESCHUTES | 005/122 | 70Y | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.969607 | 40.4853 | ETL.8290 | 40770155 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | released 7-13-20
119119253 | T3 DI DRUM-HIGGINS 07/72 RPL INSL | 31506971 | DRUM-HIGGINS | 007/072 | 93K | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.85979 | 39.1898 | ETL.4393 | 40725218 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Sacramento
119119294 | T3 DI MORAGA-SN LEANDRO #3 7/50 RPR FOND |  | MORAGA-SAN LEANDRO #3 | 007/050 | ICQ | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.113789 | 37.7534 | ETL.2790 | 40587933 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  | ACRP
119119330 | T2 DI TRNTY-MPLE CRK 31/4 RMV PL BUTT | 44299848 | TRINITY-MAPLE CREEK | 031/004 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.484549 | 40.6899 | ETL.8170 | 40906467 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
119119333 | T3 DI VOLTA DESCHUTES 6/143 RPR STRW | 43939089 | VOLTA-DESCHUTES | 006/143 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.988507 | 40.49 | ETL.8290 | 40769428 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | released 7-13-20
119119335 | T3 DI VOLTA DESCHUTES 1/35 REFRAME CRSW | 31505200 | VOLTA-DESCHUTES | 001/035 | 93E | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.895788 | 40.467 | ETL.8290 | 40660885 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  | released 7-13-20
119119336 | T3 DI VOLTA DESCHUTES 1/35 RPR STRW | 43939089 | VOLTA-DESCHUTES | 001/035 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.895788 | 40.467 | ETL.8290 | 40660885 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | released 7-13-20
119119358 | T2 DI CARIBOU-PALERMO 015/121 RPR STRS |  | CARIBOU-PALERMO | 015/121 | ICS | E | 2020_(2) High fire spread TD |  |  |  | TR2 |  | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.505729 | 39.6583 | ETL.3190 | 40913203 | Structure-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain
119119359 | T2 DI CARIBOU-PALERMO 015/121 RPLC HRDS |  | CARIBOU-PALERMO | 015/121 | ICS | E | 2020_(2) High fire spread TD |  |  |  | TR2 |  | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.505729 | 39.6583 | ETL.3190 | 40913203 | Hardware-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain
119119411 | T3NT DI DONNELLS-MI-WUK 8/0 RMV BUTT | 44467328 | DONNELLS-CURTIS | 008/000 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-120.102319 | 38.1641 | ETL.1400 | 40580189 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor
119119412 | T3 DI DONNELLS-MI-WUK 8/0 RPR STRW | 44623218 | DONNELLS-CURTIS | 008/000 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-120.102319 | 38.1641 | ETL.1400 | 40580189 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 40 | USFS
119119414 | T3 DI PIT #1-CTTONWOD 034/293 RMV DEBRIS | 43879413 | PIT #1-COTTONWOOD | 034/293 | ICS | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-122.01155 | 40.7041 | ETL.5390 | 40657359 | Structure-Steel | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain
119119419 | T2 DI COLGATE-GRASS VALLY 1/44 RPR WDPKR | 44365328 | COLGATE-GRASS VALLEY | 001/044 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.155927 | 39.3232 | ETL.6490 | 40599479 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119119420 | T2NT DI CARIBOU-PALRMO 15/121 RMV DEBRIS |  | CARIBOU-PALERMO | 015/121 | ICS | F | 2020_(3) On high spread structure |  |  |  | TR2 |  | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.505729 | 39.6583 | ETL.3190 | 40913203 | Structure-Steel | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain
119119436 | T3NT DI CLGT-ALLGHNY 8/231 RMV BUTT | 44356570 | COLGATE-ALLEGHANY | 008/231 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.049275 | 39.365 | ETL.6470 | 40602502 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119119437 | T3NT DI CLGT ALLGHNY 8/231 INST MRKW | 44356570 | COLGATE-ALLEGHANY | 008/231 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.049275 | 39.365 | ETL.6470 | 40602502 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119119510 | T3NT DI CARIBOU-PLRMO :30/247 RMV DEBRIS |  | CARIBOU-PALERMO | :030/247 | ICS | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR3 |  | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.454013 | 39.7748 | ETL.3190 | 40826439 | Structure-Steel | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain
119119631 | T2 DI TRINITY-MAPLE CREEK 7/7 RPR WDPKER | 44295371 | TRINITY-MAPLE CREEK | 007/007 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.055824 | 40.746 | ETL.8170 | 40906350 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
119119672 | T2 DI KILARC-DESCHUTES 2/51 RPL POLE | 31507070 | KILARC-DESCHUTES | 002/051 | 70Y | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.892542 | 40.6468 | ETL.7300 | 40876595 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Released
119119714 | T3 DI DRUM-SPAULDING 1/31 RPL STRW | 31529083 | DRUM-SPAULDING | 001/031 | 70Y | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.746034 | 39.2533 | ETL.6770 | 40861931 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE erdy | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento
119119813 | T2 DI COLGATE-SMARTVLL #2 7/77 RPL POLE | 31511059 | COLGATE-SMARTVILLE #2 | 007/077 | 70Y | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.284237 | 39.2638 | ETL.6520 | 40668758 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento
119119817 | T2 DI SLNS-LRLS-LRLS 5/126 RPR WDPKR | 44578873 | SALINAS-LAURELES | 005/126 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-121.68841 | 36.6246 | ETL.7930 | 40828858 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  | Y - 12
119119818 | T2 DI SALINAS-LAURELES 008/174 RPR GYWW | 44610150 | SALINAS-LAURELES | 008/174 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-121.701152 | 36.5956 | ETL.7930 | 40613943 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  | Y - 12 | CalTrans
119119819 | T2 DI SALINAS-LAURELES 008/174 RPR WDPKR | 44610150 | SALINAS-LAURELES | 008/174 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-121.701152 | 36.5956 | ETL.7930 | 40613943 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  | Y - 12 | CalTrans
119119843 | T3NT DI KESWICK-TRINITY 2/39 RMV BUTT | 43939188 | KESWICK-TRINITY | 002/039 | ICW | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-122.495793 | 40.617 | ETL.7270 | 40660731 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119119903 | T3 DI KESWICK-TRINITY 1/27 RPR GYWW | 43939188 | KESWICK-TRINITY | 001/027 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-122.479404 | 40.6184 | ETL.7270 | 40771192 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119119962 | T2 DI LAURELES-OTTER 000/011 RPR GYWW | 44587870 | LAURELES-OTTER | 000/011 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-121.719199 | 36.4757 | ETL.7380 | 40600142 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  | Y - Prog 401
119119964 | T2 DI LAURELES-OTTER 000/011 RMV PL BUTT | 44587870 | LAURELES-OTTER | 000/011 | ICW | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-121.719199 | 36.4757 | ETL.7380 | 40600142 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing
119119972 | T2 DI KILARC-DESCHUTES 1/28 REFRAME | 31507189 | KILARC-DESCHUTES | 001/028 | 93E | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.879428 | 40.6598 | ETL.7300 | 40817199 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  | Released
119119974 | T2 DI KILARC-DESCHUTES 1/28 RMV PL BUTT | 43930440 | KILARC-DESCHUTES | 001/028 | ICW | E | 2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.879428 | 40.6598 | ETL.7300 | 40817199 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Released
119120007 | T3 DI KESWICK-TRINITY 1/27 REMV BUTT | 43939188 | KESWICK-TRINITY | 001/027 | ICW | E | 2020_(3) On high spread structure |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-122.479404 | 40.6184 | ETL.7270 | 40771192 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119120028 | T2 DI LAURELES-OTTER 2/0 RPR WDPKER | 44587870 | LAURELES-OTTER | 002/000 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-121.709893 | 36.4588 | ETL.7380 | 40589527 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  | Y - 13
119120045 | T2 DI SALINAS-LAURELES 007/154 RPR WDPKR | 44578873 | SALINAS-LAURELES | 007/154 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-121.690779 | 36.609 | ETL.7930 | 40594149 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  | Y - 12
119120046 | T2 DI TRINITY-MAPLE CREK 47/18 RPR WDPKR | 44295371 | TRINITY-MAPLE CREEK | 047/018 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.765662 | 40.7517 | ETL.8170 | 40861543 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
119120136 | T2 DI KILARC-DESCHUTES 3/65 RPR WDPKR | 43930440 | KILARC-DESCHUTES | 003/065 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.901174 | 40.6398 | ETL.7300 | 40676474 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Released
119120369 | T2 DI TRINITY-MPL CRK 52/0(C) RPL POLE | 31508602 | TRINITY-MAPLE CREEK | 052/000B | 70Y | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.838427 | 40.7673 | ETL.8170 | 40588804 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka
119121210 | T2 DI CARIBOU #2 4/21 REMV DEBRIS |  | CARIBOU #2 | 004/021 | ICW | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.2105 | 40.0512 | ETL.6280 | 44738173 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119122053 | T2 DI CARIBOU #2 4/21 RMV STEP |  | CARIBOU #2 | 004/021 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.2105 | 40.0512 | ETL.6280 | 44738173 | Hardware-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119122056 | T3 DI KILARC-CEDAR CRK 4/105 RPR GYWW | 43939119 | KILARC-CEDAR CREEK | 004/105 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.955008 | 40.7033 | ETL.7290 | 40677172 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119122059 | T3NT DI KILARC-CEDR 4/105 RPL GMKW | 43939119 | KILARC-CEDAR CREEK | 004/105 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.955008 | 40.7033 | ETL.7290 | 40677172 | Guy Wire Mark /Indic-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119122094 | T2 DI COLGATE-GRS VLLY 8/186 RMV PL BUTT | 44365323 | COLGATE-GRASS VALLEY | 008/186 | ICW | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.089112 | 39.2665 | ETL.6490 | 40613018 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119122144 | T2 DI CLGTE-GRSS VLLY 8/201 REFRAME | 31507018 | COLGATE-GRASS VALLEY | 008/201 | 93E | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.086527 | 39.2584 | ETL.6490 | 40767728 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Sacramento
119122146 | T2 DI CLGTE-GRSS VLLY 8/201 RMV DEBRIS | 44371194 | COLGATE-GRASS VALLEY | 008/201 | ICW | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.086527 | 39.2584 | ETL.6490 | 40767728 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119122234 | T3 DI KILARC-CEDAR CREEK 4/105 REMV STUB | 43939119 | KILARC-CEDAR CREEK | 004/105 | ICW | E | 2020_(3) On high spread structure |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.955008 | 40.7033 | ETL.7290 | 40677172 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119122255 | T3 MI-WUK-CURTIS 19/005L RPL POLE | 31505692 | ETL.1073.POLE.WDPS | 019/005 | 70Y | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-120.2343 | 38.0479 | ETL.1073 | 44837637 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 41
119122909 | DI MORRO BAY-SN LS OBSP #2 0/6 RPL INSS | 31527000 | MORRO BAY-SAN LUIS OBISPO #2 | 000/006 | 93K | E | 2020_(4) TD tag on high spread line | [5 empty] | South | WSIP | [6 empty] | '-120.844636 | 35.3752 | ETL.2820 | 40838015 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - 7
119123514 | T2 DI KILARC-DESCHUTES 10/220 INS MRKW | 44406469 | KILARC-DESCHUTES | 010/220 | ICW | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.015041 | 40.5785 | ETL.7300 | 40656983 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119123959 | DI GRBRVLL-LYTNVLLE 52/7B RPL INSW | 31505611 | GARBERVILLE-LAYTONVILLE | 052/007B | 93I | E | 2020_(2) High fire spread TD | [5 empty] | North Coast | WSIP | [6 empty] | '-123.639329 | 40.0584 | ETL.8365 | 40922396 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Eureka
119124061 | DI GRBRVLL-LYTNVLLE 52/7B BOND GUY | 44311204 | GARBERVILLE-LAYTONVILLE | 052/007B | ICW | E | 2020_(3) On high spread structure | [5 empty] | North Coast | WSIP | [6 empty] | '-123.639329 | 40.0584 | ETL.8365 | 40912587 | Hardware-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
119124064 | DI GRBRVLL-LYTNVLLE 052/007C RPR CNDW | 44311204 | GARBERVILLE-LAYTONVILLE | 052/007C | ICW | E | 2020_(2) High fire spread TD | [5 empty] | North Coast | WSIP | [6 empty] | '-123.639287 | 40.0584 | ETL.8365 | 44404873 | Conductor-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
119124066 | DI GRBRVLL-LYTNVLLE 052/007C BOND GUY | 44311204 | GARBERVILLE-LAYTONVILLE | 052/007C | ICW | E | 2020_(3) On high spread structure | [5 empty] | North Coast | WSIP | [6 empty] | '-123.639287 | 40.0584 | ETL.8365 | 44404873 | Hardware-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
119124241 | T2 DI KILARC-DSCHUTES 10/222 RMV PL BUTT | 43930440 | KILARC-DESCHUTES | 010/222 | ICW | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.01582 | 40.5777 | ETL.7300 | 40770437 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Released
119124269 | DI GRBRVLL-LYTNVLLE 053/009A RPR SPLW | 44311204 | GARBERVILLE-LAYTONVILLE | 053/009A | ICW | E | 2020_(4) TD tag on high spread line | [5 empty] | North Coast | WSIP | [6 empty] | '-123.650305 | 40.0705 | ETL.8365 | 40912599 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
119124411 | DI GRBRVLL-LYTNVLLE 053/009A BOND | 44311204 | GARBERVILLE-LAYTONVILLE | 053/009A | ICW | E | 2020_(4b) On structure in bucket 4 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.650305 | 40.0705 | ETL.8365 | 40912599 | Hardware-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
119124414 | DI GRBRVLL-LYTNVLLE 053/009A RPR GYWW | 44311204 | GARBERVILLE-LAYTONVILLE | 053/009A | ICW | E | 2020_(4) TD tag on high spread line | [5 empty] | North Coast | WSIP | [6 empty] | '-123.650305 | 40.0705 | ETL.8365 | 40912599 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
119124416 | DI GRBRVLL-LYTNVLLE 053/009A INS NUMBR | 44311204 | GARBERVILLE-LAYTONVILLE | 053/009A | ICW | F | 2020_(4b) On structure in bucket 4 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.650305 | 40.0705 | ETL.8365 | 40912599 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
119124873 | T2 DI TRINITY-MPLE CREK 27/3 RPR WDPKR | 44295371 | TRINITY-MAPLE CREEK | 027/003 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.401149 | 40.7025 | ETL.8170 | 40906430 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
119124875 | T2 DI TRINITY-MPLE CREK 024/003 RPL SWIW | 31507468 | TRINITY-MAPLE CREEK | 024/003 | 93H | E | 2020_(2) High fire spread TD |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.340098 | 40.7058 | ETL.8170 | 40906416 | Switch-Wood | No Good/Out of Stdrd | Replace | UNSE erdy | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 427 | Eureka
119125060 | T2 TRNTY-MPL CRK 17/1 INST CUTOUT BOX | 44470713 | TRINITY-MAPLE CREEK | 017/001 | ICS | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.20901 | 40.7414 | ETL.8170 | 43242519 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Eureka
119125063 | T2 TRNTy-MPL CRK 17/1B INST CUTOUT BOX | 44470713 | TRINITY-MAPLE CREEK | 017/001B | ICS | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.209853 | 40.7416 | ETL.8170 | 43242518 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Eureka
119125500 | T3NT DI DRM-GRS VLY-WMR 8/195 RMV PL BUT | 44361666 | DRUM-GRASS VALLEY-WEIMAR | 008/195 | ICW | F | 2020_(1a) PSPS |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.852785 | 39.1873 | ETL.6760 | 40669956 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119125558 | T2 DI KILARC-DESCHUTES 1/24 RMV PL BUTT | 43930440 | KILARC-DESCHUTES | 001/024 | ICW | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.877247 | 40.6622 | ETL.7300 | 40676466 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Released
119125559 | T2 DI KILARC-DESCHUTES 1/24 RPR WDPKR | 43930440 | KILARC-DESCHUTES | 001/024 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.877247 | 40.6622 | ETL.7300 | 40676466 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Released
119125649 | T2 DI KLRC-DSCHTS 6/134 RPR WDPKR | 43930440 | KILARC-DESCHUTES | 006/134 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.952508 | 40.6118 | ETL.7300 | 40617779 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Released
119125661 | T2 DI KILARC-DESCHUTES 4/96 REFRAME | 31507071 | KILARC-DESCHUTES | 004/096 | 93E | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.922205 | 40.624 | ETL.7300 | 40656965 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  | Released
119125680 | T2 DI KILARC-DESCHUTS A24/512 RMV PL BUT | 43930440 | KILARC-DESCHUTES | A024/512 | ICW | F | 2020_(1b) Lines with special commitments |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.270045 | 40.5687 | ETL.7300 | 42614961 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Released
119125681 | T2 DI KLRC-DSCHTS 6/134 RPR DEBRIS | 43930440 | KILARC-DESCHUTES | 006/134 | ICW | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.952508 | 40.6118 | ETL.7300 | 40617779 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Released
119125697 | T2 DI KLRC-DSCHTS 19/390 RMV PL BUTT | 43930440 | KILARC-DESCHUTES | 019/390 | ICW | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.166579 | 40.5638 | ETL.7300 | 40617685 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119125699 | T2 DI KLRC-DSCHTS 19/390 RPL POLE | 31507070 | KILARC-DESCHUTES | 019/390 | 70Y | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.166579 | 40.5638 | ETL.7300 | 40617685 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain
119125725 | T3NT DI CRBU-PALERMO :031/256C INST GMKW |  | CARIBOU-PALERMO | :031/256C | ICW | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR3 |  | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.467814 | 39.7593 | ETL.3190 | 44374356 | Guy Wire Mark /Indic-Wood | Missing | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119125753 | T3 DI MAPLE CREEK-HOOPA 27/6 RPR CNDW | 44178090 | MAPLE CREEK-HOOPA | 027/006 | ICS | E | 2020_(4) TD tag on high spread line |  |  | Likely MAT error - delink to correct | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.671397 | 41.0387 | ETL.7490 | 44645848 | Conductor-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
119125770 | T3 DI KLRC-CEDAR CREEK 8/197 RPL STRW | 31506712 | KILARC-CEDAR CREEK | 008/197 | 70Y | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.984088 | 40.7367 | ETL.7290 | 40816384 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Table Mountain
119125792 | T2 DI KILARC-DSCHTS 10/207 RPL POLE | 31507070 | KILARC-DESCHUTES | 010/207 | 70Y | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.005468 | 40.5839 | ETL.7300 | 40600387 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Released
119125822 | T2 DI CARIBOU #2 001/004 INST MRKW |  | CARIBOU #2 | 001/004 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.1632 | 40.0765 | ETL.6280 | 40769460 | Marker (i.e. signs)-Wood | Missing | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119125825 | T2 DI CARIBOU #2 001/004 RMV STEPS |  | CARIBOU #2 | 001/004 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.1632 | 40.0765 | ETL.6280 | 40769460 | Hardware-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119125919 | T3 DI SLY CREEK TAP A0/7B RPR STRW | 44391954 | SLY CREEK TAP | A000/007B | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.12828 | 39.5725 | ETL.4221 | 44388061 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119125933 | T2 DI KLRC-DSCHTS 7/161 RPR WDPKR | 43930440 | KILARC-DESCHUTES | 007/161 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.97324 | 40.6015 | ETL.7300 | 40816221 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Released
119125936 | T2 DI KLRC-DSCHTS 7/161 INSTALL HRDW | 43930440 | KILARC-DESCHUTES | 007/161 | ICW | E | 2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.97324 | 40.6015 | ETL.7300 | 40816221 | Hardware-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Released
119125961 | T3 DI DEER CREEK-DRUM 002/058 RPR GYWW | 44361664 | DEER CREEK-DRUM | 002/058 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.829188 | 39.264 | ETL.6690 | 40598802 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119125964 | T2 DI CARIBOU #2 003/015 RMV STEPS |  | CARIBOU #2 | 003/015 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.197265 | 40.0634 | ETL.6280 | 40768765 | Hardware-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119125965 | T3 DI MIDDLEFORK #1 004/067 RPR POLE | 44361891 | MIDDLE FORK #1 | 004/067 | ICW | E | 2020_(1a) PSPS |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.654916 | 38.9986 | ETL.8405 | 40824479 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119126033 | T3 DI LAURELES-OTTER 13/17 WASH INSW | 44610149 | LAURELES-OTTER | 013/017 | ICW | E | 2020_(4) TD tag on high spread line |  |  | Likely MAT error - delink to correct | TR3 | LATE | South | WSIP | [6 empty] | '-121.871747 | 36.3854 | ETL.7380 | 40853162 | Insulator | Contaminated | Ground Wash | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 622 | Moss Landing
119126060 | T2 DI CARIBOU #2 RMV STEP |  | CARIBOU #2 | 004/028 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.213725 | 40.0494 | ETL.6280 | 40868117 | Hardware-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119126068 | T2 DI KLRC-DSCHTS 11/230 RMV PL BUTT | 43930440 | KILARC-DESCHUTES | 011/230 | ICW | E | 2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.019579 | 40.5739 | ETL.7300 | 40602021 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Released
119126082 | T2 DI KLRC-DSCHTS A25/519 RPR WDPKR | 43930440 | KILARC-DESCHUTES | A025/519 | ICW | E | 2020_(1b) Lines with special commitments |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.276034 | 40.571 | ETL.7300 | 44370512 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Released
119126116 | T2 DI KLRC-DSCHTS A25/525 INSTALL MRKW | 43930440 | KILARC-DESCHUTES | A025/525 | ICW | F | 2020_(1b) Lines with special commitments |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.280805 | 40.5712 | ETL.7300 | 40826839 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Released
119126147 | T2 DI COLGATE-GRASS VLLY 0/4 RMV PL BUTT | 44365323 | COLGATE-GRASS VALLEY | 000/004 | ICW | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.187827 | 39.3292 | ETL.6490 | 40655407 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119126190 | T2 DI KLARC-DSCHUTES A025/535 RMV DEBRIS | 43930440 | KILARC-DESCHUTES | A025/535 | ICW | E | 2020_(1b) Lines with special commitments |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.289595 | 40.5711 | ETL.7300 | 41118628 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Released
119126191 | T2 DI KILARC-DSCHUTES A025/535 INST MRKW | 43930440 | KILARC-DESCHUTES | A025/535 | ICW | F | 2020_(1b) Lines with special commitments |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.289595 | 40.5711 | ETL.7300 | 41118628 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Released
119126198 | T2 DI TRNTY-MPLE CRK 019/012 RPR WDPKR | 44295371 | TRINITY-MAPLE CREEK | 019/012 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.259723 | 40.728 | ETL.8170 | 40660845 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
119126199 | T2 DI TRNTY-MPLE CRK 019/012 RMV PL BUTT | 44299848 | TRINITY-MAPLE CREEK | 019/012 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.259723 | 40.728 | ETL.8170 | 40660845 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
119126209 | T2 DI LAURELES-OTTER 0/15 RMV PL BUTT | 44587870 | LAURELES-OTTER | 000/015 | ICW | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-121.717132 | 36.4721 | ETL.7380 | 40768326 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing
119126221 | T3NT DI RAGA-SAN LEAND #3 7/53 RPR FOND |  | MORAGA-SAN LEANDRO #1 | 007/053 | ICQ | F | 2020_(4) TD tag on high spread line |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-122.114008 | 37.7479 | ETL.2770 | 40644212 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  | ACRP
119126226 | T2 DI ELK-GUALALA 42/001 ANTI-SPLIT | 44610591 | ELK-GUALALA | 042/001 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.67961 | 39.0638 | ETL.8410 | 40595299 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
119126423 | DI GARBERVILLE-LAYTNVLLE 53/9C BOND INSW | 44311204 | GARBERVILLE-LAYTONVILLE | 053/009C | ICW | E | 2020_(4b) On structure in bucket 4 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.650266 | 40.0706 | ETL.8365 | 40912601 | Hardware-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
119126424 | DI GARBERVILLE-LAYTNVLLE 53/9C RPR GYWW | 44311204 | GARBERVILLE-LAYTONVILLE | 053/009C | ICW | E | 2020_(4) TD tag on high spread line | [5 empty] | North Coast | WSIP | [6 empty] | '-123.650266 | 40.0706 | ETL.8365 | 40912601 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
119126425 | DI GARBERVILLE-LAYTNVLLE 53/9C INS NUMBR | 44311204 | GARBERVILLE-LAYTONVILLE | 053/009C | ICW | F | 2020_(4b) On structure in bucket 4 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.650266 | 40.0706 | ETL.8365 | 40912601 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
119126488 | T2 PIT #5-ROUND MTN #1 000/002 RPL SPLS | 44345514 | PIT #5-ROUND MTN #1 | 000/002 | ICS | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.973862 | 40.9838 | ETL.5420 | 44148492 | Splice-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain
119126797 | T3 DI VOLTA-DESCHUTES 1/32 REFRAME | 31505200 | VOLTA-DESCHUTES | 001/032 | 93E | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.89359 | 40.4664 | ETL.8290 | 40875808 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  | released 7-13-20
119126898 | T3 DI CRESTA-RIO OSO 012/100 RPR FOND |  | CRESTA-RIO OSO | 012/100 | ICQ | E | 2020_(4b) On structure in bucket 4 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.451228 | 39.7844 | ETL.4590 | 40910126 | Foundation/Concrete-Tower | Earth Covered Tower | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
119126985 | T3 DI BRUNSWICK #2 004/027 RPL INSS | 31506897 | BRUNSWICK #2 TAP | 004/027 | 93K | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.033621 | 39.189 | ETL.1431 | 40834399 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Sacramento
119127025 | T3NT DI BRUNSWICK #1 001/014 RPR FOND | 44370736 | BRUNSWICK #1 TAP | 001/014 | ICQ | F | 2020_(4) TD tag on high spread line |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.02581 | 39.1634 | ETL.1422 | 40751877 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento
119127027 | T2 DI KILARC-DESCHUTES 5/115 RMV PL BUTT | 43930440 | KILARC-DESCHUTES | 005/115 | ICW | E | 2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.935512 | 40.6167 | ETL.7300 | 40602045 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Released
119127395 | T2 DI KILARC-DSCHUTES 10/226 RMV PL BUTT | 43930440 | KILARC-DESCHUTES | 010/226 | ICW | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.017692 | 40.5758 | ETL.7300 | 40876516 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119127396 | T2 DI KILARC-DESCHUTES 10/226 REFRAME | 31507189 | KILARC-DESCHUTES | 010/226 | 93E | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.017692 | 40.5758 | ETL.7300 | 40876516 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain
119127402 | T3NT DI DRUM-RIO #2 10/106 INST ACG | 31507030 | DRUM-RIO OSO #2 | 010/106 | 93A | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.931791 | 39.1706 | ETL.1430 | 40815440 | Structure-Tower | Anti-Climbing Guard | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Capital | 988 | Sacramento
119127403 | T3NT DI DRUM-RIO OSO #2 10/106 RPR FOND | 44365329 | DRUM-RIO OSO #2 | 010/106 | ICQ | F | 2020_(2) High fire spread TD |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.931791 | 39.1706 | ETL.1430 | 40815440 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento
119127900 | DI GARBERVL-LYTNVL 46/9A RPR SPLW | 44311204 | GARBERVILLE-LAYTONVILLE | 046/009A | ICW | E | 2020_(4) TD tag on high spread line | [5 empty] | North Coast | WSIP | [6 empty] | '-123.625712 | 39.9779 | ETL.8365 | 40912520 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
119127901 | DI GARBERVL-LYTNVL 46/9A REPL POLE | 31506024 | GARBERVILLE-LAYTONVILLE | 046/009A | 70Y | E | 2020_(4) TD tag on high spread line | [5 empty] | North Coast | WSIP | [6 empty] | '-123.625712 | 39.9779 | ETL.8365 | 40912520 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka
119127906 | DI GARBERVL-LYTNVL 46/9B REPL POLE | 31506024 | GARBERVILLE-LAYTONVILLE | 046/009B | 70Y | E | 2020_(4) TD tag on high spread line | [5 empty] | North Coast | WSIP | [6 empty] | '-123.625675 | 39.9778 | ETL.8365 | 40912521 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka
119127983 | DI GARBERVIL-LYTNVL 46/9C REPL POLE | 31506024 | GARBERVILLE-LAYTONVILLE | 046/009C | 70Y | E | 2020_(4) TD tag on high spread line | [5 empty] | North Coast | WSIP | [6 empty] | '-123.625644 | 39.9778 | ETL.8365 | 40912522 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka
119128221 | T3NT DI BRUNSWICK #1 TAP 2/15 RPR FOND | 44370736 | BRUNSWICK #1 TAP | 002/015 | ICQ | F | 2020_(4) TD tag on high spread line |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.028432 | 39.1644 | ETL.1422 | 40761881 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento
119128448 | T2 PHILO JCT-ELK 33/1 RPL ANCHOR | 31507982 | PHILO JCT-ELK | 033/001 | 93E | E | 2020_(2) High fire spread TD |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.646385 | 39.1331 | ETL.7780 | 40595293 | Anchor-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Lakeville
119128506 | T2 PHILO JCT-ELK 30/8 RPL POLE | 31507793 | PHILO JCT-ELK | 030/008B | 70Y | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.610159 | 39.1238 | ETL.7780 | 40876300 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville
119128588 | T2 LAYTONVILLE-WILLITS 8/0 RPL POLE | 31507792 | LAYTONVILLE-WILLITS | 008/000 | 70Y | E | 2020_(2) High fire spread TD |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.373378 | 39.5027 | ETL.8360 | 40613352 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville
119128616 | T2 HUMBOLDT-MAPLE CREEK 7/7 RPL SWITCH | 31508148 | HUMBOLDT-MAPLE CREEK | 007/007 | 93S | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.989915 | 40.7576 | ETL.7130 | 40825283 | Switch-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 435 | Eureka
119129092 | T2 DI KESWICK-CASCADE A025/526 RPL POLE | 31507070 | KILARC-DESCHUTES | A025/526 | 70Y | E | 2020_(1b) Lines with special commitments |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.281421 | 40.5712 | ETL.7300 | 40870146 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Released
119129094 | T2 DI KESWICK-CSCADE A025/526 RMV PL BUT | 43930440 | KILARC-DESCHUTES | A025/526 | ICW | F | 2020_(1b) Lines with special commitments |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.281421 | 40.5712 | ETL.7300 | 40870146 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Released
119129381 | T3NT DI MRGA-SAN LENDRO #3 7/52 RPR FOND |  | MORAGA-SAN LEANDRO #3 | 007/052 | ICQ | F | 2020_(4) TD tag on high spread line |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-122.113802 | 37.7479 | ETL.2790 | 40646083 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  | ACRP
119129384 | DI GARBERVILLE-LYTNVLL 45/8 RPR GYWW | 44311204 | GARBERVILLE-LAYTONVILLE | 045/008 | ICW | E | 2020_(4) TD tag on high spread line | [5 empty] | North Coast | WSIP | [6 empty] | '-123.617512 | 39.967 | ETL.8365 | 40912509 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
119129387 | DI GARBERVILLE-LYTNVLL 46/2 RPR GYWW | 44311204 | GARBERVILLE-LAYTONVILLE | 046/002 | ICW | E | 2020_(4) TD tag on high spread line | [5 empty] | North Coast | WSIP | [6 empty] | '-123.620364 | 39.9704 | ETL.8365 | 40912512 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
119129482 | T2 DI CLGT-SMRTVLL#2 7/75 RMV BUTT | 44356572 | COLGATE-SMARTVILLE #2 | 007/075 | ICW | E | 2020_(1a) PSPS |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.283702 | 39.265 | ETL.6520 | 40602344 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119129576 | T2 DI KILARC-DESCHUTES 7/146 REFRAME | 31507071 | KILARC-DESCHUTES | 007/146 | 93E | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.962545 | 40.608 | ETL.7300 | 40701866 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  | Released
119129835 | T2 TRINITY-MAPLE CREEK 37/10 INST DAMPER | 44273074 | TRINITY-MAPLE CREEK | 037/010 | ICW | E | 2020_(3) On high spread structure |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.588286 | 40.7115 | ETL.8170 | 40617876 | Damper-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
119129967 | T2 DI KILARC-DESCHUTS A24/502 RMV PL BUT | 43930440 | KILARC-DESCHUTES | A024/502 | ICW | F | 2020_(1b) Lines with special commitments |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.262354 | 40.5658 | ETL.7300 | 44141993 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Released
119130039 | T2 DI TRINITY-MPLE CRK 2/12 RPR WDPKR | 44295371 | TRINITY-MAPLE CREEK | 002/012 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-122.976392 | 40.7347 | ETL.8170 | 40906274 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
119130144 | T3NT DI KESWICK-TRINITY 2/43 RMV BUTT | 43939188 | KESWICK-TRINITY | 002/043 | ICW | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-122.50221 | 40.6165 | ETL.7270 | 40752197 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119130232 | T3 DI KESWICK-TRINITY 2/43 RPR GYWW | 43939188 | KESWICK-TRINITY | 002/043 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-122.50221 | 40.6165 | ETL.7270 | 40752197 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119130276 | T2 DI KILARC-DESCHUTS A24/511 RMV PL BUT | 43930440 | KILARC-DESCHUTES | A024/511 | ICW | E | 2020_(1b) Lines with special commitments |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.26923 | 40.5684 | ETL.7300 | 40669390 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Released
119130280 | T2 DI KILARC-DESCHUTES 19/401 RMV PL BUT | 43930440 | KILARC-DESCHUTES | 019/401 | ICW | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.176237 | 40.5638 | ETL.7300 | 40602004 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119130281 | T2 DI KILARC-DESCHUTES 19/401 RPR WDPKR | 43930440 | KILARC-DESCHUTES | 019/401 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.176237 | 40.5638 | ETL.7300 | 40602004 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119130344 | T2 EI DIVIDE-CABRILLO #2 10/131 RPL INS | 31507662 | DIVIDE-CABRILLO #2 | 010/131 | 93I | E | 2020_(2) High fire spread TD |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-120.4365167 | 34.6784 | ETL.1370 | 40901477 | Insulator-Wood | No Good/Out of Stdrd | Replace | ADER | ADER | ADE Review estimate | Not Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Pismo Beach |  | Y - Prog 401
119130433 | T3 DI DRUM-RIO OSO #1 0/5 RPL HRDT | 44371587 | DRUM-RIO OSO #1 | 000/005 | ICQ | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.778322 | 39.2568 | ETL.1420 | 40756197 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento
119130529 | T2 DI CARIBOU-PALERMO 012/106 RPR SPLS |  | CARIBOU-PALERMO | 012/106 | ICS | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.510269 | 39.6405 | ETL.3190 | 40841210 | Splice-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain
119130667 | T2 DI KLRC-DSCHTS A25/521 INS MRKW | 43930440 | KILARC-DESCHUTES | A025/521 | ICW | F | 2020_(1b) Lines with special commitments |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.277172 | 40.5712 | ETL.7300 | 44843914 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Released
119130676 | T3 DI CRESTA-RIO OSO 016/138 BURIED STUB |  | CRESTA-RIO OSO | 016/138 | ICQ | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.479364 | 39.7282 | ETL.4590 | 40910154 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
119130800 | T3 DI CRESTA-RIO OSO 016/138 RMV STEPS |  | CRESTA-RIO OSO | 016/138 | ICQ | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.479364 | 39.7282 | ETL.4590 | 40910154 | Hardware-Tower | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
119130809 | T3NT DI DRUM-RIO OSO #2 4/046 RPR FOND | 44365329 | DRUM-RIO OSO #2 | 004/046 | ICQ | F | 2020_(2) High fire spread TD |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.832295 | 39.2289 | ETL.1430 | 40815312 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento
119130951 | T2 DI KILARC-DESCHUTS A24/504 RMV PL BUT | 43930440 | KILARC-DESCHUTES | A024/504 | ICW | F | 2020_(1b) Lines with special commitments |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.263563 | 40.5663 | ETL.7300 | 44141994 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Released
119130970 | T3 DI DRUM-RIO OSO #2 004/046 INST HRDT | 44371591 | DRUM-RIO OSO #2 | 004/046 | ICQ | E | 2020_(3) On high spread structure |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.832295 | 39.2289 | ETL.1430 | 40815312 | Hardware-Tower | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento
119131164 | T2 DI KILARC-DESCHUTS 10/228 RMV PL BUTT | 43930440 | KILARC-DESCHUTES | 010/228 | ICW | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.018676 | 40.5748 | ETL.7300 | 40602020 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Released
119131349 | T2 DI KILARC-DESCHUT 18/387 RMV PL BUTT | 43930440 | KILARC-DESCHUTES | 018/387 | ICW | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.163639 | 40.5638 | ETL.7300 | 40868583 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119131404 | T3 DI SBRNT-GRZLY-CRMT #2 5/35F RPL INSS | 31511124 | SOBRANTE-GRIZLY-CLARMNT #2+ | 005/035F | 93K | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.189586 | 37.8587 | ETL.3750 | 42582067 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - 12
119132014 | T2 MI-WUK-CURTIS 023/001 RPL POLE | 31516010 | ETL.1073.POLE.WDPS | 023/001 | 70Y | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-120.26918 | 38.0053 | ETL.1073 | 44774786 | Structure-Wood | No Good/Out of Stdrd | Replace | ADER | ADER | ADE Review estimate | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 41
119132043 | T2 CRIBU-PLUMS JCT 11/012 RPL ANCHOR | 31507980 | CARIBOU-PLUMAS JCT | 011/012 | 93E | E | 2020_(2) High fire spread TD |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-120.993768 | 39.9803 | ETL.6290 | 40675220 | Anchor-Wood | No Good/Out of Stdrd | Replace | ESTS erdy | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain
119132055 | DI GRBRVLLE-LYTNVLL 33/000A REPL POLE | 31454647 | GARBERVILLE-LAYTONVILLE | 033/000A | 70Y | E | 2020_(4) TD tag on high spread line | [5 empty] | North Coast | WSIP | [6 empty] | '-123.553759 | 39.8113 | ETL.8365 | 40906579 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka
119132074 | T3NT DI DRUM-SPAULDING 001/035 RMV BUTT | 44364848 | DRUM-SPAULDING | 001/035 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.744388 | 39.2557 | ETL.6770 | 40667536 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119132075 | T3 DI DRUM-SPAULDING 001/035 RPL STRW | 31529083 | DRUM-SPAULDING | 001/035 | 70Y | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.744388 | 39.2557 | ETL.6770 | 40667536 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE erdy | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Sacramento
119132076 | T2 DI LAURELES-OTTER 2/14 RMV PL BUTT | 44587870 | LAURELES-OTTER | 002/014 | ICW | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-121.715685 | 36.4489 | ETL.7380 | 40758134 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing
119132078 | T3 DI BRUNSWICK #1 TAP 002/019 RPR INSS | 44370738 | BRUNSWICK #1 TAP | 002/019 | ICS | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.034465 | 39.1705 | ETL.1422 | 40878323 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento
119132079 | T3 DI VOLTA-DESCHUTES 2/53 RMV BUTT | 43939089 | VOLTA-DESCHUTES | 002/053 | ICW | E | 2020_(4b) On structure in bucket 4 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.910683 | 40.4706 | ETL.8290 | 40877079 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119132125 | DI GRBRVLLE-LYTNVLL 33/000C REPL POLE | 31454647 | GARBERVILLE-LAYTONVILLE | 033/000C | 70Y | E | 2020_(4) TD tag on high spread line | [5 empty] | North Coast | WSIP | [6 empty] | '-123.553734 | 39.8114 | ETL.8365 | 40906581 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka
119132170 | T3 DI VOLTA-DESCHUTES 2/53 REFRAME XARM | 31505200 | VOLTA-DESCHUTES | 002/053 | 93E | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.910683 | 40.4706 | ETL.8290 | 40877079 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain
119132173 | T2 DI KILARC-DESCHUTES 3/082 RPR WDPKR | 43930440 | KILARC-DESCHUTES | 003/082 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.912913 | 40.6311 | ETL.7300 | 40876560 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119132174 | T2 DI COLGTE-SMRTVLLE #2 4/48 RMV DEBRIS | 44365321 | COLGATE-SMARTVILLE #2 | 004/048 | ICW | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.249613 | 39.2975 | ETL.6520 | 40602850 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119132175 | T2 DI COLGTE-SMRTVLLE #2 4/48 INST MRKW | 44365321 | COLGATE-SMARTVILLE #2 | 004/048 | ICW | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.249613 | 39.2975 | ETL.6520 | 40602850 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119132176 | T2 DI COLGTE-SMRTVLLE #2 4/48 RPR GYWW | 44365320 | COLGATE-SMARTVILLE #2 | 004/048 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.249613 | 39.2975 | ETL.6520 | 40602850 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119132178 | T2 DI CLGTE-SMARTVILL #2 4/53 RPR GYWW | 44365320 | COLGATE-SMARTVILLE #2 | 004/053 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.25539 | 39.2909 | ETL.6520 | 40828771 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119132301 | T2 DI KILARC-DESCHUTES 004/101 REFRAME | 31507189 | KILARC-DESCHUTES | 004/101 | 93E | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.924884 | 40.6218 | ETL.7300 | 40576630 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  | Released
119132309 | T3 DI SBRNTE-GRZLY-CLRMNT #2 RPL INSS | 31511124 | SOBRANTE-GRIZLY-CLARMNT #2+ | 005/035G | 93K | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.191071 | 37.8599 | ETL.3750 | 42582069 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - 12
119132424 | T2 DI KILARC-DSCHUTS A024/505 RMV PL BUT | 43930440 | KILARC-DESCHUTES | A024/505 | ICW | F | 2020_(1b) Lines with special commitments |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.264401 | 40.5666 | ETL.7300 | 44141995 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Released
119132426 | T2 DI KILARC-DESCHUTES A023/490 INS MRKW | 43930440 | KILARC-DESCHUTES | A023/490 | ICW | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.251558 | 40.5639 | ETL.7300 | 40588852 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119132427 | T2 DI KILARC-DESCHUTES 04/102 INS MRKW | 43930440 | KILARC-DESCHUTES | 004/102 | ICW | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.925319 | 40.6214 | ETL.7300 | 40877898 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Released
119132550 | T3 DI VOLTA-DESCHTS 5/113 REFRAME CRSW | 31505200 | VOLTA-DESCHUTES | 005/113 | 93E | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.961882 | 40.4834 | ETL.8290 | 40759051 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain
119132590 | T3NT DI DRUM-SPAULDING 5/128 RMV DEBRIS | 44364848 | DRUM-SPAULDING | 005/128 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.702731 | 39.2971 | ETL.6770 | 40810149 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119132592 | T3 DI DRUM-SPAULDING 005/128 RPL HRDW | 44364850 | DRUM-SPAULDING | 005/128 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.702731 | 39.2971 | ETL.6770 | 40810149 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119132596 | T3 DI PITTSBURG-SAN MATEO 11/47 PRL INSS | 31511125 | PITTSBURG-SAN MATEO | 011/047 | 93K | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-121.881233 | 37.8771 | ETL.5463 | 40724040 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - Prog 402
119140015 | T2 DI TRINITY-MAPLE CREEK 45/1 RPL POLE | 31506143 | TRINITY-MAPLE CREEK | 045/001 | 70Y | E | 2020_(2) High fire spread TD |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.711755 | 40.749 | ETL.8170 | 40585387 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka
119140060 | T3NT DI FULTON-IGNACIO #1 16/84 RPR FOND | 44310479 | FULTON-IGNACIO #1 | 016/084 | ICQ | F | 2020_(4) TD tag on high spread line |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.592277 | 38.3936 | ETL.4680 | 40753541 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville
119140103 | T2 DI TRINITY-MAPLE CRK 27/2A RPR GYWW | 44364310 | TRINITY-MAPLE CREEK | 027/002A | ICS | E | 2020_(2) High fire spread TD |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.399461 | 40.7034 | ETL.8170 | 40906429 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Eureka
119141021 | T2 DI TRINITY-MAPLE CREEK 24/7 RPR GYWW | 44273074 | TRINITY-MAPLE CREEK | 024/007 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.348963 | 40.705 | ETL.8170 | 40906418 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
119141085 | T3NT DI VOLTA-DESCHUTES 3/84 RMV PL BUTT | 43939089 | VOLTA-DESCHUTES | 003/084 | ICW | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.937202 | 40.4772 | ETL.8290 | 40868506 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | released 7-13-20
119141269 | T2 DI TRINITY-MPL CRK 35/2 RPL HRDW | 44273074 | TRINITY-MAPLE CREEK | 035/002 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.546067 | 40.7204 | ETL.8170 | 40701816 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
119141328 | GARBERVILLE-LAYTONVILLE 52/005 RPL POLE | 31462488 | GARBERVILLE-LAYTONVILLE | 052/005 | 93E | E | 2020_(2) High fire spread TD | [5 empty] | North Coast | WSIP | [6 empty] | '-123.6394 | 40.0563 | ETL.8365 | 40912585 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Eureka
119141558 | T2NT DI TRINITY-MAPLE CRK 27/2 INS MRKW | 44273074 | TRINITY-MAPLE CREEK | 027/002 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.398882 | 40.7037 | ETL.8170 | 40903784 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
119141671 | T2DI TRINITY-MAPLE CRK 27/2 REPLACE POLE | 31507467 | TRINITY-MAPLE CREEK | 027/002 | 93E | E | 2020_(2) High fire spread TD |  |  |  | TR2 |  | North Coast | WSIP | [8 empty] | ETL.8170 | 40913390 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Eureka
119141811 | T2 DI TRINITY-MAPLE CRK 27/2 RMV PL BUTT | 44299848 | TRINITY-MAPLE CREEK | 027/002 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.398882 | 40.7037 | ETL.8170 | 40903784 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
119142129 | DI GARBRVILLE-LAYTONVLL 61/5 RMV PL BUTT | 44311203 | GARBERVILLE-LAYTONVILLE | 061/005 | ICW | F | 2020_(4b) On structure in bucket 4 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.767368 | 40.1126 | ETL.8365 | 40912694 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
119142479 | DI GARBRVILLE-LAYTONVLLE 53/9B RPL HRDW | 44311204 | GARBERVILLE-LAYTONVILLE | 053/009B | ICW | E | 2020_(4b) On structure in bucket 4 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.650284 | 40.0706 | ETL.8365 | 40912600 | Hardware-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
119142537 | DI GARBRVILLE-LAYTONVLLE 53/9B RPR GYWW | 44311204 | GARBERVILLE-LAYTONVILLE | 053/009B | ICW | E | 2020_(4) TD tag on high spread line | [5 empty] | North Coast | WSIP | [6 empty] | '-123.650284 | 40.0706 | ETL.8365 | 40912600 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
119142551 | EI T3NT SLO-SANTA MARIA 14/249 IDLE | 31510921 | SAN LUIS OBISPO-SANTA MARIA (IDLE) | 014/249 | 93J | F | 2020_(2) High fire spread TD |  | TLN/TLQ error |  | TR3 |  | South | WSIP | [6 empty] | '-120.507827 | 35.1122 | ETL.9100 | 44191390 | Structure-Wood | Idle | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Capital | 673 | Pismo Beach
119142571 | DI GARBRVILLE-LAYTONVLLE 53/9B INS MRKW | 44311204 | GARBERVILLE-LAYTONVILLE | 053/009B | ICW | F | 2020_(4b) On structure in bucket 4 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.650284 | 40.0706 | ETL.8365 | 40912600 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
119142774 | EI T3NT SLO-SANTA MARIA 14/248 IDLE | 31510921 | SAN LUIS OBISPO-SANTA MARIA (IDLE) | 014/248 | 93J | F | 2020_(2) High fire spread TD |  | TLN/TLQ error |  | TR3 |  | South | WSIP | [6 empty] | '-120.508072 | 35.1131 | ETL.9100 | 44191389 | Structure-Wood | Idle | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Capital | 673 | Pismo Beach
119142858 | DI HUMBOLDT-BRIDGEVILLE 89/1 RPR FOND | 44623121 | HUMBOLDT-BRIDGEVILLE | 089/001 | ICQ | F | 2020_(2) High fire spread TD | [5 empty] | North Coast | WSIP | [6 empty] | '-123.82476 | 40.5127 | ETL.1810 | 44321392 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Eureka
119142972 | DI GARBERVILLE-LAYTONVILLE 34/4 INS MRKW | 44311204 | GARBERVILLE-LAYTONVILLE | 034/004 | ICW | F | 2020_(4b) On structure in bucket 4 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.570625 | 39.8278 | ETL.8365 | 40761558 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
119142976 | DI GARBERVILLE-LAYTONVILLE 34/4 RPR GYWW | 44311204 | GARBERVILLE-LAYTONVILLE | 034/004 | ICW | E | 2020_(4) TD tag on high spread line | [5 empty] | North Coast | WSIP | [6 empty] | '-123.570625 | 39.8278 | ETL.8365 | 40761558 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
119143033 | DI DRUM-GRSS VLLY-WMR B18/412 CANCEL | 44379030 | DRUM-GRASS VALLEY-WEIMAR | B018/412 | ICW | E | 2020_(4) TD tag on high spread line |  |  | CANCEL/CNCL |  |  | North Valley | WSIP | [6 empty] | '-120.973599 | 39.1486 | ETL.6760 | 40757033 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119143042 | EI T3NT SLO-SANTA MARIA 14/247 IDLE | 31510921 | SAN LUIS OBISPO-SANTA MARIA (IDLE) | 014/247 | 93J | F | 2020_(2) High fire spread TD |  | TLN/TLQ error |  | TR3 |  | South | WSIP | [6 empty] | '-120.508518 | 35.1147 | ETL.9100 | 44191392 | Structure-Wood | Idle | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Capital | 673 | Pismo Beach
119143912 | T2 DI CORTINA-MENDO #1 28/137 INST STEP | 44238817 | CORTINA-MENDOCINO #1 | 028/137 | ICQ | E | 2020_(3) On high spread structure |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.708607 | 39.0337 | ETL.1330 | 40808527 | Hardware-Tower | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville
119144575 | T2 DI KILARC-DESCHUTES 2/59 RPR WDPKR | 43930440 | KILARC-DESCHUTES | 002/059 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.897062 | 40.6432 | ETL.7300 | 40828003 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119144644 | T2 DI KLRC-DESCHUTES A024/501 RPR GYWW | 43930440 | KILARC-DESCHUTES | A024/501 | ICW | E | 2020_(1b) Lines with special commitments |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.261792 | 40.5656 | ETL.7300 | 40651306 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Released
119144673 | T2 DI KILARC-DESCHUTES A02/487 REFRAME | 31507071 | KILARC-DESCHUTES | A023/487 | 93E | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.249152 | 40.5638 | ETL.7300 | 40865088 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  | Released
119144701 | T2 DI KILARC-DSCHUTES 11/232 CANCEL | 43930440 | KILARC-DESCHUTES | 011/232 | ICW | F | 2020_(4b) On structure in bucket 4 |  |  | CANCEL/CNCL | TR2 |  | North Valley | WSIP | [6 empty] | '-122.020382 | 40.5726 | ETL.7300 | 40668435 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119144743 | T2 DI TRINITY-MPLE CREEK 19/13 RPR WDPKR | 44295371 | TRINITY-MAPLE CREEK | 019/013 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.260686 | 40.7273 | ETL.8170 | 40650357 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
119144745 | T2 DI KILARC-DESCHUTS 20/414 RMV PL BUT | 43930440 | KILARC-DESCHUTES | 020/414 | ICW | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.189564 | 40.5637 | ETL.7300 | 40771242 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119144885 | T2 DI CNTRVL TBL MTN ORO 8/158 RPL POLE | 31507074 | CENTERVILLE-TABLE MTN-OROVILLE | 008/158 | 70Y | E | 2020_(1a) PSPS |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.636302 | 39.6755 | ETL.6330 | 40664412 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain
119144906 | DI STANISLAUS-MANTECA %2 27/162 RPR STRT |  | STANISLAUS-MANTECA #2 | 027/162 | ICQ | E | 2020_(2) High fire spread TD | [5 empty] | Central | WSIP | [6 empty] | '-120.776389 | 37.9211 | ETL.3820 | 40683083 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - 26
119145635 | T2 DI TRINITY-MAPLE CRK 5/2 INST MRKW | 44273074 | TRINITY-MAPLE CREEK | 005/002 | ICW | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.0264 | 40.733 | ETL.8170 | 40906319 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
119145637 | T2 DI TRINITY-MAPLE CRK 5/2 RPL HRDW | 44273074 | TRINITY-MAPLE CREEK | 005/002 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.0264 | 40.733 | ETL.8170 | 40906319 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
119145936 | EI T3NT SLO-SANTA MARIA 14/245 IDLE | 31510921 | SAN LUIS OBISPO-SANTA MARIA (IDLE) | 014/245 | 93J | F | 2020_(2) High fire spread TD |  | TLN/TLQ error |  | TR3 |  | South | WSIP | [6 empty] | '-120.509191 | 35.1172 | ETL.9100 | 44191387 | Structure-Wood | Idle | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Capital | 673 | Pismo Beach
119146000 | EI T3NT SLO-SANTA MARIA 14/246 IDLE | 31510921 | SAN LUIS OBISPO-SANTA MARIA (IDLE) | 014/246 | 93J | F | 2020_(2) High fire spread TD |  | TLN/TLQ error |  | TR3 |  | South | WSIP | [6 empty] | '-120.509095 | 35.1169 | ETL.9100 | 44191391 | Structure-Wood | Idle | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Capital | 673 | Pismo Beach
119146173 | T2 DI SN LUS OBSPO-CYUCS 17/154 RPR GYWW |  | SAN LUIS OBISPO-CAYUCOS | 017/154 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-120.819742 | 35.3787 | ETL.9090 | 40597837 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - 12
119146256 | DI SALINAS-LAURELES 5/133 RPR GYWW | 44578873 | SALINAS-LAURELES | 005/133 | ICW | E | 2020_(4) TD tag on high spread line | [5 empty] | South | WSIP | [6 empty] | '-121.684318 | 36.6233 | ETL.7930 | 40697410 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  | Y - Prog 401
119146632 | T2 DI FORT ROSS-GUALLA 50/6 RMV PLE BUTT |  | GUALALA-MONTE RIO | 050/006 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.414692 | 38.7259 | ETL.6980 | 40821495 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
119146774 | T2 EI DIVIDE-CABRILLO #2 6/074 RPL INSW | 31506526 | DIVIDE-CABRILLO #2 | 006/074 | 93I | E | 2020_(2) High fire spread TD |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-120.4333782 | 34.7434 | ETL.1370 | 40641796 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Pismo Beach |  | Y - Prog 401
119146834 | T2 EI DIVIDE-CABRILLO #2 5/072 RPL INSW | 31506526 | DIVIDE-CABRILLO #2 | 005/072 | 93I | E | 2020_(2) High fire spread TD |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-120.43325 | 34.7472 | ETL.1370 | 40828426 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Pismo Beach |  | Y - Prog 401
119147087 | T2 EI DIVIDE-CABRILLO #2 5/071 RPL INSW | 31506526 | DIVIDE-CABRILLO #2 | 005/071 | 93I | E | 2020_(2) High fire spread TD |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-120.433227 | 34.748 | ETL.1370 | 40757950 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Pismo Beach |  | Y - Prog 401
119147633 | T3NT DI DRUM-SPAULDING 4/106 INS MRKW | 44364848 | DRUM-SPAULDING | 004/106 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.707529 | 39.2879 | ETL.6770 | 40810147 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119147977 | EI T3NT SLO-SANTA MARIA 13/234 IDLE | 31510921 | SAN LUIS OBISPO-SANTA MARIA (IDLE) | 013/234 | 93J | F | 2020_(2) High fire spread TD |  | TLN/TLQ error |  | TR3 |  | South | WSIP | [6 empty] | '-120.51055 | 35.1261 | ETL.9100 | 44191937 | Structure-Wood | Idle | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Capital | 673 | Pismo Beach
119148118 | EI T3NT SLO-SANTA MARIA 13/235 IDLE | 31510921 | SAN LUIS OBISPO-SANTA MARIA (IDLE) | 013/235 | 93J | F | 2020_(2) High fire spread TD |  | TLN/TLQ error |  | TR3 |  | South | WSIP | [6 empty] | '-120.510605 | 35.126 | ETL.9100 | 44772564 | Structure-Wood | Idle | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Capital | 673 | Pismo Beach
119148251 | T2 EI DIVIDE-CABRILLO #2 09/108 RPL POLE | 31508019 | DIVIDE-CABRILLO #2 | 009/108 | 70Y | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-120.436466 | 34.6985 | ETL.1370 | 40673885 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Pismo Beach
119148330 | EI T3NT SLO-SANTA MARIA 13/236 IDLE | 31510921 | SAN LUIS OBISPO-SANTA MARIA (IDLE) | 013/236 | 93J | F | 2020_(2) High fire spread TD |  | TLN/TLQ error |  | TR3 |  | South | WSIP | [6 empty] | '-120.510879 | 35.1255 | ETL.9100 | 44191949 | Structure-Wood | Idle | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Capital | 673 | Pismo Beach
119148396 | T2 DI KILARC-DESCHUTES 18/385 RPL POLE | 31507070 | KILARC-DESCHUTES | 018/385 | 70Y | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.161748 | 40.5638 | ETL.7300 | 40817236 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | Released
119148398 | T2 DI KILARC-DSCHTS 18/385 RMV BUTT CNCL | 43930440 | KILARC-DESCHUTES | 018/385 | ICW | F | 2020_(4b) On structure in bucket 4 |  |  | CANCEL/CNCL | TR2 |  | North Valley | WSIP | [6 empty] | '-122.161748 | 40.5638 | ETL.7300 | 40817236 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | Released
119148469 | T3 DI DRUM-SPAULDING 4/106 RPL STRW | 31529083 | DRUM-SPAULDING | 004/106 | 70Y | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.707529 | 39.2879 | ETL.6770 | 40810147 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE erdy | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Sacramento
119148610 | EI T3NT SLO-SANTA MARIA 13/237 IDLE | 31510921 | SAN LUIS OBISPO-SANTA MARIA (IDLE) | 013/237 | 93J | F | 2020_(2) High fire spread TD |  | TLN/TLQ error |  | TR3 |  | South | WSIP | [6 empty] | '-120.51069 | 35.1246 | ETL.9100 | 44191897 | Structure-Wood | Idle | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Capital | 673 | Pismo Beach
119148945 | T3 EAGL RCK-FLTN-SLVRD 1/10 RPR MEMBER |  | EAGLE ROCK-FULTON-SILVERADO | 001/010 | ICQ | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.800903 | 38.8166 | ETL.4392 | 40605188 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville
119148978 | EI T3NT SLO-SANTA MARIA 13/238 IDLE | 31510921 | SAN LUIS OBISPO-SANTA MARIA (IDLE) | 013/238 | 93J | F | 2020_(2) High fire spread TD |  | TLN/TLQ error |  | TR3 |  | South | WSIP | [6 empty] | '-120.510343 | 35.1233 | ETL.9100 | 44191410 | Structure-Wood | Idle | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Capital | 673 | Pismo Beach
119149184 | EI T3NT SLO-SANTA MARIA 13/239 IDLE | 31510921 | SAN LUIS OBISPO-SANTA MARIA (IDLE) | 013/239 | 93J | F | 2020_(2) High fire spread TD |  | TLN/TLQ error |  | TR3 |  | South | WSIP | [6 empty] | '-120.510261 | 35.1229 | ETL.9100 | 44191403 | Structure-Wood | Idle | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Capital | 673 | Pismo Beach
119149213 | DI DIVIDE-CABRILLO #2 01/26 RPL POLE | 31507527 | DIVIDE-CABRILLO #2 | 001/026 | 70Y | E | 2020_(4) TD tag on high spread line | [5 empty] | South | WSIP | [6 empty] | '-120.444748 | 34.8057 | ETL.1370 | 40618677 | Structure-Wood | No Good/Out of Stdrd | Replace | ADER | ADER | ADE Review estimate | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Pismo Beach
119149854 | DI STNSLS-MEL SS-MNT#1 28/178 RPR SPLS | 44566008 | STANISLAUS-MELONES SS-MANTECA #1+ | 028/178 | ICS | E | 2020_(2) High fire spread TD | [5 empty] | Central | WSIP | [6 empty] | '-120.796253 | 37.9153 | ETL.3830 | 40803339 | Splice-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - 22
119149955 | T3 DI MORAGA-SAN LEANDR #3 7/52 RPL INSS | 31511126 | MORAGA-SAN LEANDRO #3 | 007/052 | 93K | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.113802 | 37.7479 | ETL.2790 | 40704892 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  |  | ACRP
119149967 | T3 EI SLO-SANTA MARIA 13/2 RMV IDLE | 31506239 | SAN LUIS OBISPO-SANTA MARIA (IDLE) | 013/241 | 93J | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | South | WSIP | [6 empty] | '-120.510259 | 35.1213 | ETL.9100 | 44191413 | Structure-Wood | Idle | Remove | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Maintenance | Capital | 673 | Pismo Beach |  | Y - 4
119149982 | T3 EI SLO-SANTA MARIA 13/2 RMV VEGN |  | SAN LUIS OBISPO-SANTA MARIA (IDLE) | 013/241 | HNA | F | 2020_(1b) Lines with special commitments |  |  |  | TR3 |  | South | WSIP | [6 empty] | '-120.510259 | 35.1213 | ETL.9100 | 44191413 | Vegetation | Overgrown | Trim |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Pismo Beach
119149985 | T3 EI SLO-SANTA MARIA 13/2 REPL POLE | 31506239 | SAN LUIS OBISPO-SANTA MARIA (IDLE) | 013/241 | 93J | E | 2020_(1b) Lines with special commitments |  |  |  | TR3 | LATE | South | WSIP | [6 empty] | '-120.510259 | 35.1213 | ETL.9100 | 44191413 | Structure-Wood | Rotten | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Contract | Capital | 372 | Pismo Beach |  | Y - 4
119150124 | EI T3NT SLO-SANTA MARIA 13/242 IDLE | 31510921 | SAN LUIS OBISPO-SANTA MARIA (IDLE) | 013/242 | 93J | F | 2020_(2) High fire spread TD |  | TLN/TLQ error |  | TR3 |  | South | WSIP | [6 empty] | '-120.510188 | 35.121 | ETL.9100 | 44191411 | Structure-Wood | Idle | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Capital | 673 | Pismo Beach
119150267 | EI T3NT SLO-SANTA MARIA 13/243 IDLE | 31510921 | SAN LUIS OBISPO-SANTA MARIA (IDLE) | 013/243 | 93J | F | 2020_(2) High fire spread TD |  | TLN/TLQ error |  | TR3 |  | South | WSIP | [6 empty] | '-120.510034 | 35.1203 | ETL.9100 | 44191412 | Structure-Wood | Idle | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Capital | 673 | Pismo Beach
119150469 | EI T3NT SLO-SANTA MARIA 14/244 IDLE | 31510921 | SAN LUIS OBISPO-SANTA MARIA (IDLE) | 014/244 | 93J | F | 2020_(2) High fire spread TD |  | TLN/TLQ error |  | TR3 |  | South | WSIP | [6 empty] | '-120.509424 | 35.1181 | ETL.9100 | 44191388 | Structure-Wood | Idle | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Capital | 673 | Pismo Beach
119150581 | T2 DI TRINITY-MAPLE CREK 26/6 RMV PL BUT | 44299848 | TRINITY-MAPLE CREEK | 026/006 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.390041 | 40.7056 | ETL.8170 | 40906426 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
119150584 | T2 DI TRINITY-MAPLE CREK 31/2 RMV PL BUT | 44299848 | TRINITY-MAPLE CREEK | 031/002 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.478088 | 40.6898 | ETL.8170 | 40906465 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
119150589 | T3NT DI CARIBOU-PLRMO :31/256A INST GMKW |  | CARIBOU-PALERMO | :031/256A | ICW | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR3 |  | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.467758 | 39.7593 | ETL.3190 | 44374354 | Guy Wire Mark /Indic-Wood | Missing | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119150826 | T2 DI SLNS LRLS LRLS 15/307 RPL POLE | 31507340 | SALINAS-LAURELES | 015/307 | 70Y | E | 2020_(2) High fire spread TD |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-121.737689 | 36.5139 | ETL.7930 | 40649765 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Moss Landing |  | Y - 13
119151050 | T3 DI VOLTA-DESCHUTES 2/54 RMV STUBB | 43939089 | VOLTA-DESCHUTES | 002/054 | ICW | E | 2020_(4b) On structure in bucket 4 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.911555 | 40.4709 | ETL.8290 | 40875829 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119151051 | T3 DI VOLTA-DESCHUTES 2/54 RPL HRDD | 43939089 | VOLTA-DESCHUTES | 002/054 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.911555 | 40.4709 | ETL.8290 | 40875829 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119151056 | T3 DI VOLTA-DESCHUTES 6/133 RPL STRW | 31506865 | VOLTA-DESCHUTES | 006/133 | 70Y | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.980092 | 40.4879 | ETL.8290 | 40759053 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | released 7-13-20
119151317 | T3 DI CLGT ALLGHNY 10/273 RPR INS | 44365653 | COLGATE-ALLEGHANY | 010/273 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.034708 | 39.3834 | ETL.6470 | 40894335 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119151319 | T3 DI CLGT ALLGHNY 5/144 RPR STRW | 44365653 | COLGATE-ALLEGHANY | 005/144 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.095128 | 39.3357 | ETL.6470 | 40766588 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119151375 | DI TRINITY-MAPLE CREEK 0/1 RPR GYWW | 44273074 | TRINITY-MAPLE CREEK | 000/001 | ICW | E | 2020_(4b) On structure in bucket 4 | [5 empty] | North Coast | WSIP | [6 empty] | '-122.934888 | 40.7183 | ETL.8170 | 40906220 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
119151600 | T3NT DI CLGT ALLGHNY 5/141 RMV BUTT | 44365654 | COLGATE-ALLEGHANY | 005/141 | ICW | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.096941 | 39.3346 | ETL.6470 | 40693506 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119151601 | T3 DI CLGT ALLGHNY 5/141 RPR STRW | 44365653 | COLGATE-ALLEGHANY | 005/141 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.096941 | 39.3346 | ETL.6470 | 40693506 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119151869 | T3 DI DRUM-SUMMIT #2 5/61C RPR GYWW | 44365659 | DRUM-SUMMIT #2 | 005/061C | ICW | E | 2020_(1b) Lines with special commitments |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.698813 | 39.2971 | ETL.1450 | 44212211 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119152261 | T3 DI CRESTA-RIO OSO 16/136 BURIED STUB |  | CRESTA-RIO OSO | 016/136 | ICQ | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.478996 | 39.7305 | ETL.4590 | 40910152 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
119153522 | T3 DI DRM RIO OSO #1 1/16 RPR BNT MEM | 44371588 | DRUM-RIO OSO #1 | 001/016 | ICS | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.796441 | 39.2562 | ETL.1420 | 40820312 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento
119155639 | DI STANISLAUS-MNTC #2 27/158 RPR SPLS | 44566011 | STANISLAUS-MANTECA #2 | 027/158 | ICS | E | 2020_(2) High fire spread TD | [5 empty] | Central | WSIP | [6 empty] | '-120.766736 | 37.9239 | ETL.3820 | 40856504 | Splice-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - 26
119155641 | LOS BANOS-MIDWAY #2 144/591 RPL INSS |  | LOS BANOS-MIDWAY #2 | 144/591 | 93K | E | 2020_(1b) Lines with special commitments | Director approved |  |  |  | WECC | South | WSIP | [6 empty] | '-119.461368 | 35.4118 | ETL.6010 | 44668392 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Midway |  | Y - 26
119155834 | T3 DI DRUM-RIO OSO #1 6/64 RPLC INSS | 31505600 | DRUM-RIO OSO #1 | 006/064 | 93K | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [8 empty] | ETL.1420 | 44319610 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Sacramento
119155984 | T3NT DI POE-RIO OSO 21/141 RPR FOND |  | POE-RIO OSO | 021/141 | ICQ | F | 2020_(4) TD tag on high spread line |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.488993 | 39.6836 | ETL.5540 | 40590427 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
119156006 | DI DRUM-RIO OSO #1 33/241 RPL HANGER | 44380501 | DRUM-RIO OSO #1 | 033/241 | ICQ | E | 2020_(2) High fire spread TD | [5 empty] | North Valley | WSIP | [6 empty] | '-121.302869 | 39.0222 | ETL.1420 | 40597503 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento
119156013 | DI HUMBOLDT-TRINITY 102/2 RPLC POLE (R) |  | HUMBOLDT-TRINITY | 102/002 | 70Y | E | 2020_(2) High fire spread TD | [5 empty] | North Coast | WSIP | [6 empty] | '-123.905065 | 40.7644 | ETL.1820 | 44562924 | Structure-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka
119156075 | DI DRUM-RIO OSO #2 33/241 RPL INSS | 31503652 | DRUM-RIO OSO #2 | 033/241 | 93K | E | 2020_(2) High fire spread TD | [5 empty] | North Valley | WSIP | [6 empty] | '-121.30286 | 39.0221 | ETL.1430 | 40624114 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Sacramento
119156138 | DI GARBERVILLE-LAYTONVILLE 60/5 RPR SPLW | 44311204 | GARBERVILLE-LAYTONVILLE | 060/005 | ICW | E | 2020_(2) High fire spread TD | [5 empty] | North Coast | WSIP | [6 empty] | '-123.757467 | 40.1153 | ETL.8365 | 40912683 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
119156221 | T3NT DI SBNT-GRZLY-CLRT #1 A0/5 RPR FOND | 44624393 | SOBRNTE-GRIZZLY-CLARMNT #1+ | A000/005 | ICQ | F | 2020_(2) High fire spread TD |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-122.213431 | 37.8979 | ETL.3740 | 40746110 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 13
119156754 | T2 DI TRNTY-MPL CRK 46/8 REPL PL (RIGHT) | 31506143 | TRINITY-MAPLE CREEK | 046/008 | 70Y | E | 2020_(2) High fire spread TD | [5 empty] | North Coast | WSIP | [6 empty] | '-123.739655 | 40.7483 | ETL.8170 | 44771070 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka
119156756 | T2 DI TRNTY-MPL CRK 46/8 RPLC STRW (C) | 31506143 | TRINITY-MAPLE CREEK | 046/008 | 70Y | E | 2020_(2) High fire spread TD | [5 empty] | North Coast | WSIP | [6 empty] | '-123.739655 | 40.7483 | ETL.8170 | 44771071 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka
119156759 | T2 DI TRNTY-MPL CRK 46/8 REPL PL (LEFT) | 31506143 | TRINITY-MAPLE CREEK | 046/008 | 70Y | E | 2020_(2) High fire spread TD | [5 empty] | North Coast | WSIP | [6 empty] | '-123.739655 | 40.7483 | ETL.8170 | 44771069 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka
119157523 | T3 DI COLGATE-ALLGHANY 9/259 RPR INSW | 31506710 | COLGATE-ALLEGHANY | 009/259 | 93I | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.03776 | 39.3758 | ETL.6470 | 40619049 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Sacramento
119157552 | T2 DI TRINITY-MAPLE CRK 12/2 RPR WP HOLE | 44295371 | TRINITY-MAPLE CREEK | 012/002 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Coast | WSIP | [8 empty] | ETL.8170 | 44420607 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
119157583 | T3NT DI COLG-ALLHNY 9/259 RMV PL BUTT | 44365654 | COLGATE-ALLEGHANY | 009/259 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.03776 | 39.3758 | ETL.6470 | 40593288 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119158050 | T2 DI CLGT SMRTVLLE #2 3/41 RPL POLE | 31511059 | COLGATE-SMARTVILLE #2 | 003/041 | 70Y | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.244049 | 39.3039 | ETL.6520 | 40828765 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento
119158164 | T2 EI LAURELES-OTTER 0/012 RPR GYWW | 44587870 | LAURELES-OTTER | 000/012 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-121.718525 | 36.4747 | ETL.7380 | 40659509 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  | Y - Prog 402
119158215 | EI GARBERVILLE-LYTNVL 47/4C RPL POLE | 31506024 | GARBERVILLE-LAYTONVILLE | 047/004 | 70Y | E | 2020_(4) TD tag on high spread line | [5 empty] | North Coast | WSIP | [6 empty] | '-123.617733 | 39.9881 | ETL.8365 | 44403653 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka
119158217 | EI GARBERVILLE-LYTNVL 47/4L RPL POLE | 31506024 | GARBERVILLE-LAYTONVILLE | 047/004 | 70Y | E | 2020_(4) TD tag on high spread line | [5 empty] | North Coast | WSIP | [6 empty] | '-123.617733 | 39.9881 | ETL.8365 | 44403652 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka
119158234 | T3 DI COLGATE-CHALLENGE 5/105 RPR INSW | 44365653 | COLGATE-CHALLENGE | 005/105 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.168533 | 39.3982 | ETL.6480 | 40843183 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119158356 | T2 MNDCN-WLLITS-FRT BRGG 6/0 RPR WDPKR | 44610681 | MENDOCINO-WILLITS-FORT BRAGG | 006/000 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.282843 | 39.2969 | ETL.7550 | 44676880 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
119158481 | EI GARBERVILLE-LYTNVL 47/4R RPL POLE | 31506024 | GARBERVILLE-LAYTONVILLE | 047/004 | 70Y | E | 2020_(4) TD tag on high spread line | [5 empty] | North Coast | WSIP | [6 empty] | '-123.617733 | 39.9881 | ETL.8365 | 44403654 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka
119158518 | T2 MNDCN-WLITS-FRT BRG 17/010 RPL POLE | 31508092 | MENDOCINO-WILLITS-FORT BRAGG | 017/010 | 70Y | E | 2020_(2) High fire spread TD |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.408618 | 39.3916 | ETL.7550 | 40588460 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville
119158607 | T2 DI TRNTY-MPL CRK 13/0 INS MRKW | 44273074 | TRINITY-MAPLE CREEK | 013/000 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.143431 | 40.7646 | ETL.8170 | 40605815 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
119158777 | T2 DI CNTRVLL TBLMTN ORO 8/172 RPL POLE | 31507074 | CENTERVILLE-TABLE MTN-OROVILLE | 008/172 | 70Y | E | 2020_(1a) PSPS |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.636354 | 39.6656 | ETL.6330 | 40822499 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain
119158796 | T2 DI TRNTY-MPL CRK 13/0 RPR GYWW | 44273074 | TRINITY-MAPLE CREEK | 013/000 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.143431 | 40.7646 | ETL.8170 | 40605815 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
119158799 | T2 DI TRNTY-MPL CRK 13/0 RPR WDPKR | 44299848 | TRINITY-MAPLE CREEK | 013/000 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.143431 | 40.7646 | ETL.8170 | 40605815 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
119158864 | T3 DI CRESTA-RIO OSO 15/123 RPR CONNS |  | CRESTA-RIO OSO | 015/123 | ICM | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.475167 | 39.7551 | ETL.4590 | 40910142 | Connector | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 534 | Table Mountain
119158865 | T3 DI CRESTA-RIO OSO 15/123 BURIED STUB |  | CRESTA-RIO OSO | 015/123 | ICQ | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.475167 | 39.7551 | ETL.4590 | 40910142 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
119158880 | T2 DI TRINITY-MAPLE CREEK 20/6R RPL POLE | 31509757 | TRINITY-MAPLE CREEK | 020/006 | 70Y | E | 2020_(4) TD tag on high spread line | [5 empty] | North Coast | WSIP | [6 empty] | '-123.27023 | 40.7201 | ETL.8170 | 44761229 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka
119158881 | T2 DI TRINITY-MAPLE CREEK 20/6C REPL POL | 31509757 | TRINITY-MAPLE CREEK | 020/006 | 70Y | E | 2020_(4) TD tag on high spread line | [5 empty] | North Coast | WSIP | [6 empty] | '-123.27023 | 40.7201 | ETL.8170 | 44761230 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka
119158882 | T2 DI TRINITY-MAPLE CREEK 20/6L RPL POLE | 31509757 | TRINITY-MAPLE CREEK | 020/006 | 70Y | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.27023 | 40.7201 | ETL.8170 | 44761228 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka
119158921 | T2 EI LAURELES-OTTER 000/014 RPR GYWW | 44587870 | LAURELES-OTTER | 000/014 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-121.717479 | 36.4728 | ETL.7380 | 40751601 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  | Y - Prog 402
119159313 | T2 DI KILARC-DESCHUTS 10/212 RMV PL BUTT | 43930440 | KILARC-DESCHUTES | 010/212 | ICW | E | 2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.009581 | 40.5828 | ETL.7300 | 40759126 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | released 7-13-20
119159315 | T2 DI KILARC-DESCHUTES 10/212 REFRAME | 31507071 | KILARC-DESCHUTES | 010/212 | 93E | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.009581 | 40.5828 | ETL.7300 | 40759126 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  | released 7-13-20
119159316 | DI DRUM-GRASS VALL-WEI B18/411 RMV BUTT | 44379030 | DRUM-GRASS VALLEY-WEIMAR | B018/411 | ICW | E | 2020_(4b) On structure in bucket 4 | [5 empty] | North Valley | WSIP | [6 empty] | '-120.973245 | 39.148 | ETL.6760 | 40664757 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119159317 | DI DRUM-GRASS VALL-WEI B18/411 RPR CONW | 44379030 | DRUM-GRASS VALLEY-WEIMAR | B018/411 | ICW | E | 2020_(4) TD tag on high spread line | [5 empty] | North Valley | WSIP | [6 empty] | '-120.973245 | 39.148 | ETL.6760 | 40664757 | Conductor-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119160235 | T2 DI PHILO JCT-ELK 18/2 RPR CRSW | 31507080 | PHILO JCT-ELK | 018/002 | 93E | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.425168 | 39.0607 | ETL.7780 | 40684472 | Crossarm-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Lakeville
119160419 | DI GARBERVLL-LAYTONVLLE 050/010 RPR GYWW | 44311204 | GARBERVILLE-LAYTONVILLE | 050/010 | ICW | E | 2020_(4) TD tag on high spread line | [5 empty] | North Coast | WSIP | [6 empty] | '-123.638632 | 40.0323 | ETL.8365 | 44141971 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
119160510 | DI GARBERVLL-LAYTONVLL 050/010 INST MRKW | 44311204 | GARBERVILLE-LAYTONVILLE | 050/010 | ICW | F | 2020_(4b) On structure in bucket 4 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.638632 | 40.0323 | ETL.8365 | 44141971 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
119160646 | DI HUMBOLDT-BRIDGEVILLE 104/3 RPL DAMW | 44107184 | HUMBOLDT-BRIDGEVILLE | 104/003 | ICW | E | 2020_(4) TD tag on high spread line | [5 empty] | North Coast | WSIP | [8 empty] | ETL.1810 | 44322522 | Damper-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
119160647 | DI HUMBOLDT-BRIDGEVILLE 104/3 RPR POLE | 44379658 | HUMBOLDT-BRIDGEVILLE | 104/003 | ICW | E | 2020_(4) TD tag on high spread line | [5 empty] | North Coast | WSIP | [8 empty] | ETL.1810 | 44322523 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
119160720 | T3 DI MAPLE CRK-HOOPA 19/000R RPL POLE | 31437835 | MAPLE CREEK-HOOPA | 019/000 | 70Y | E | 2020_(4) TD tag on high spread line |  |  |  |  | LATE | North Coast | WSIP | [6 empty] | '-123.658724 | 40.9464 | ETL.7490 | 44145868 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka
119160768 | T3NT DI CLGTE ALLGHNY 13/346 RMV BUTT | 44365654 | COLGATE-ALLEGHANY | 013/346 | ICW | F | 2020_(1a) PSPS |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.010129 | 39.4188 | ETL.6470 | 40760435 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119160898 | NT DI LYTNVLLE CVLO 8/11 INSTALL MRKW |  | LAYTONVILLE-COVELO | 008/011 | ICW | F | 2020_(3) On high spread structure | [5 empty] | North Coast | WSIP | [6 empty] | '-123.331813 | 39.7257 | ETL.7390 | 40600467 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
119161022 | T3 DI CRESTA RIO OSO 17/139 INST STEPS |  | CRESTA-RIO OSO | 017/139 | ICQ | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.479492 | 39.7275 | ETL.4590 | 40910155 | Hardware-Tower | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
119161332 | T3 DI MDDL FRK-GLD HLL 1/18 RPL HRDWW | 44365655 | MIDDLE FORK-GOLD HILL | 001/018 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.608923 | 39.0023 | ETL.5140 | 40871784 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119161350 | T3 DI MDDL FRK-GLD HLL 1/18 RPR STRW | 44365655 | MIDDLE FORK-GOLD HILL | 001/018 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.608923 | 39.0023 | ETL.5140 | 40871784 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119161451 | T3 DI CARIBOU-PALERMO :11/89 RPR GYWW |  | CARIBOU-PALERMO | :011/089 | ICS | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP |  |  |  |  | Field Operations |  | '-121.279035 | 39.9862 | ETL.3190 | 40910329 | Guy Wire-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain
119161575 | DI HUMBOLDT-TRINITY 102/2 RPLC POLE (L) |  | HUMBOLDT-TRINITY | 102/002 | 70Y | E | 2020_(2) High fire spread TD | [5 empty] | North Coast | WSIP | [6 empty] | '-123.905065 | 40.7644 | ETL.1820 | 44562822 | Structure-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka
119161578 | DI HUMBOLDT-TRINITY 102/2 RPLC POLE (C) |  | HUMBOLDT-TRINITY | 102/002 | 70Y | E | 2020_(2) High fire spread TD | [5 empty] | North Coast | WSIP | [6 empty] | '-123.905065 | 40.7644 | ETL.1820 | 44562872 | Structure-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka
119161603 | DI HUMBOLDT-BRIDGEVILLE 97/6 RPR FOND | 44623121 | HUMBOLDT-BRIDGEVILLE | 097/006 | ICQ | F | 2020_(2) High fire spread TD | [5 empty] | North Coast | WSIP | [6 empty] | '-123.874134 | 40.6297 | ETL.1810 | 44321411 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Eureka
119161692 | T2 DI KILARC-DESCHUTES 014/309 RPR GYWW | 43930440 | KILARC-DESCHUTES | 014/309 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.088143 | 40.5642 | ETL.7300 | 40825996 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119161721 | T3 DI ROCK CREEK-POE :2/16 INST HRDT |  | ROCK CREEK-POE | :002/016 | ICQ | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.279562 | 39.983 | ETL.5630 | 40804249 | Hardware-Tower | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
119161722 | DI GARBRVLLE-LYTNVLLE 61/0A INS MRKW | 44311204 | GARBERVILLE-LAYTONVILLE | 061/000A | ICW | F | 2020_(3) On high spread structure | [5 empty] | North Coast | WSIP | [6 empty] | '-123.761084 | 40.1163 | ETL.8365 | 40912687 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
119162032 | T3NT DI CLGT-ALLGHNY 012/314 RMV PL BUTT | 44371190 | COLGATE-ALLEGHANY | 012/314 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.024112 | 39.4074 | ETL.6470 | 40693206 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119162215 | T3NT DI COLGATE-ALLGHANY 14/372 RMV BUTT | 44371791 | COLGATE-ALLEGHANY | 014/372 | GAR | F | 2020_(2) High fire spread TD |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.002667 | 39.4307 | ETL.6470 | 40693234 | Structure-Wood | Rotten | Stub | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 586 | Sacramento
119162219 | T3NT DI DRUM-RIO OSO #2 3/39 RPR FOND | 44365329 | DRUM-RIO OSO #2 | 003/039 | ICQ | F | 2020_(2) High fire spread TD |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.826001 | 39.2352 | ETL.1430 | 40866276 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento
119162253 | DI BRIDGEVILLE-GARBRVILLE 15/8R RPL POLE | 31508168 | BRIDGEVILLE-GARBERVILLE | 015/008 | 70Y | E | 2020_(2) High fire spread TD |  |  |  |  | SCHD | North Coast | WSIP | [8 empty] | ETL.6220 | 44402635 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka
119162257 | DI BRIDGEVILLE-GARBRVILLE 15/8C RPL POLE | 31508168 | BRIDGEVILLE-GARBERVILLE | 015/008 | 70Y | E | 2020_(2) High fire spread TD |  |  |  |  | SCHD | North Coast | WSIP | [8 empty] | ETL.6220 | 44402634 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka
119162321 | DI BRIDGEVILLE-GARBRVILLE 15/8L RPL POLE | 31508168 | BRIDGEVILLE-GARBERVILLE | 015/008 | 70Y | E | 2020_(2) High fire spread TD |  |  |  |  | SCHD | North Coast | WSIP | [8 empty] | ETL.6220 | 44402633 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka
119162324 | DI BRIDGEVLLE-GRBERVILLE 15/8 RMV BUTT | 44299809 | BRIDGEVILLE-GARBERVILLE | 015/008 | ICW | F | 2020_(3) On high spread structure | [5 empty] | North Coast | WSIP | [8 empty] | ETL.6220 | 44402633 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
119162394 | T3 DI MDDLE FORK-GOLD HILL 6/52 RPL DAMS | 44371780 | MIDDLE FORK-GOLD HILL | 006/052 | ICS | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.691027 | 39.0025 | ETL.5140 | 44690646 | Damper-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento
119162395 | T2 DI IGNACIO-BLNS #2 15/176 RMV BUTT |  | IGNACIO-BOLINAS #2 | 015/176 | ICW | E | 2020_(3) On high spread structure |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.743056 | 38.0483 | ETL.7180 | 40827646 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
119162397 | T3 DI MDDLE FORK-GOLD HILL 6/52 RPR SHLS | 44371780 | MIDDLE FORK-GOLD HILL | 006/052 | ICS | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.691027 | 39.0025 | ETL.5140 | 44690646 | Shield Wire / OPGW-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento
119162470 | T2 DI TRINITY-MAPLE CRK 54/0 RPL INSW | 31510698 | TRINITY-MAPLE CREEK | 054/000 | 93I | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.873257 | 40.7679 | ETL.8170 | 40641469 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Eureka
119162549 | T2 MNT VST-JFFRSN #1 8/3 RPL INSS | 31513842 | MONTA VISTA-JEFFERSON #1 | 008/033 | 93K | E | 2020_(2) High fire spread TD |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-122.21436 | 37.3305 | ETL.5220 | 40658429 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - 10 | RROSP
119162576 | T2 COLGATE-GRASS VALLEY 10/239 RPL POLE | 31506254 | COLGATE-GRASS VALLEY | 010/239 | 70Y | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.079235 | 39.2332 | ETL.6490 | 40869595 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento
119162622 | T2 MNDCN-WLLTS-FRT BRGG 38/0 RPL INSW | 31508139 | MENDOCINO-WILLITS-FORT BRAGG | 038/000 | 93I | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.7262785 | 39.4046 | ETL.7550 | 40629898 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Lakeville
119162631 | DI HUMBOLDT-BRIDGEVILLE 93/5 RPR GYWW | 44107184 | HUMBOLDT-BRIDGEVILLE | 093/005 | ICW | E | 2020_(2) High fire spread TD | [5 empty] | North Coast | WSIP | [8 empty] | ETL.1810 | 44322335 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
119162632 | DI HUMBOLDT-BRIDGEVILLE 93/5 RPR GYWW | 44107184 | HUMBOLDT-BRIDGEVILLE | 093/005 | ICW | E | 2020_(2) High fire spread TD | [5 empty] | North Coast | WSIP | [8 empty] | ETL.1810 | 44322336 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
119162699 | T2 COLGATE-GRASS VALLEY 10/246 RPR INSW | 44388662 | COLGATE-GRASS VALLEY | 010/246 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.079202 | 39.2296 | ETL.6490 | 40760648 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119162799 | T2 ATASCADERO-CAYUCOS 2/21 RPL POLE | 31508522 | ATASCADERO-CAYUCOS | 002/021 | 70Y | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | South | WSIP | [8 empty] | ETL.8480 | 44319815 | Structure-Wood | No Good/Out of Stdrd | Replace | ADER | ADER | ADE Review estimate | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Pismo Beach |  | Y - 12
119162899 | T3NT DI DONNELLS-MI-WUK 14/0L RMV BUTT | 44467328 | DONNELLS-CURTIS | 014/000 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-120.151592 | 38.0908 | ETL.1400 | 44776441 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor
119162900 | T3 KILARC-CEDAR CREEK 001/022 RPR STRW | 43939119 | KILARC-CEDAR CREEK | 001/022 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.889052 | 40.6837 | ETL.7290 | 40600823 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119162939 | DI HUMBOLDT-BRIDGEVILLE 9/3 RPL INSW | 31506838 | HUMBOLDT-BRIDGEVILLE | 090/003 | 93I | E | 2020_(2) High fire spread TD | [5 empty] | North Coast | WSIP | [6 empty] | '-123.832529 | 40.5294 | ETL.1810 | 40685195 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC erdy srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Eureka
119162985 | T2 DI KILARC-DESCHUTES 21/454 CANCEL | 43930440 | KILARC-DESCHUTES | 021/454 | ICW | F | 2020_(4b) On structure in bucket 4 |  |  | CANCEL/CNCL | TR2 |  | North Valley | WSIP | [6 empty] | '-122.222322 | 40.564 | ETL.7300 | 40617679 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119163061 | DI HUMBOLDT-BRIDGEVLLE 9/3 RPL ADSS BOLT | 44107184 | HUMBOLDT-BRIDGEVILLE | 090/003 | ICW | E | 2020_(2) High fire spread TD | [5 empty] | North Coast | WSIP | [8 empty] | ETL.1810 | 44322279 | Shield Wire / OPGW-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
119163180 | T3NT DI DONNELLS-MI-WUK 14/0R RMV BUTT | 44467328 | DONNELLS-CURTIS | 014/000 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-120.151592 | 38.0908 | ETL.1400 | 44776440 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor
119163182 | T3 DI DONNELLS-MI-WUK 14/0L RPR STRW | 44467328 | DONNELLS-CURTIS | 014/000 | ICW | E | 2020_(2) High fire spread TD |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-120.151592 | 38.0908 | ETL.1400 | 44776441 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor
119163258 | T3 DI MDL FRK-GLD HLL 6/50 RPR SHLS | 44371780 | MIDDLE FORK-GOLD HILL | 006/050 | ICS | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.684499 | 39.0023 | ETL.5140 | 44690644 | Shield Wire / OPGW-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento
119163263 | T3 DI MDL FRK-GLD HLL 6/50 RPR SHLS | 44371780 | MIDDLE FORK-GOLD HILL | 006/050 | ICS | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.684499 | 39.0023 | ETL.5140 | 44690645 | Shield Wire / OPGW-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento
119163280 | T3NT DI MDL FRK-GLD HLL 6/50 INST MRKS | 44371782 | MIDDLE FORK-GOLD HILL | 006/050 | ICS | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.684499 | 39.0023 | ETL.5140 | 44690644 | Marker (i.e. signs)-Steel | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento
119163287 | T3 DI DRUM-RIO OSO #1 3/38 RPR FOND | 44371587 | DRUM-RIO OSO #1 | 003/038 | ICQ | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.82519 | 39.2362 | ETL.1420 | 40871371 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento
119163487 | T3 DI DRUM-RIO OSO #1 3/39 RPR SPLS | 44371588 | DRUM-RIO OSO #1 | 003/039 | ICS | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.826141 | 39.2352 | ETL.1420 | 40865466 | Splice-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento
119163507 | T3 DI COLGATE-ALLEGHANY 13/351 RPR STRW | 44365653 | COLGATE-ALLEGHANY | 013/351 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.008723 | 39.421 | ETL.6470 | 40611332 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119163561 | T3 DI IGNACIO-BOLINAS #1 11/121 RPR STRW |  | IGNACIO-BOLINAS #1 | 011/121 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.67241 | 37.9592 | ETL.7140 | 40750706 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
119163662 | DI HUMBOLDT-BRIDGEVILLE 98/2 RPR FIBER | 44356653 | HUMBOLDT-BRIDGEVILLE | 098/002 | ICS | E | 2020_(4) TD tag on high spread line | [5 empty] | North Coast | WSIP | [8 empty] | ETL.1810 | 44322390 | Shield Wire / OPGW-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Eureka
119163671 | DI HUMBOLDT-BRIDGEVILLE 090/6 RPR ADSS | 44107184 | HUMBOLDT-BRIDGEVILLE | 099/006 | ICW | E | 2020_(4) TD tag on high spread line | [5 empty] | North Coast | WSIP | [8 empty] | ETL.1810 | 44322423 | Damper-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
119163777 | DI HUMBOLDT-BRIDGEVILLE 100/4 RPR GYWS | 44356920 | HUMBOLDT-BRIDGEVILLE | 100/004 | ICS | E | 2020_(2) High fire spread TD | [5 empty] | North Coast | WSIP | [8 empty] | ETL.1810 | 44322445 | Guy Wire-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Eureka
119163796 | T3 DI KILARC-CEDAR CREEK 4/95 RPR GYWW | 43939119 | KILARC-CEDAR CREEK | 004/095 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.94599 | 40.7006 | ETL.7290 | 40677168 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119163799 | T3NT DI KILARC-CEDAR CREEK 4/95 RMV BUTT | 43939119 | KILARC-CEDAR CREEK | 004/095 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.94599 | 40.7006 | ETL.7290 | 40677168 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119163866 | DI HUMBOLDT-BRDGEVILLE 105/5 RMV PL BUTT | 44398571 | HUMBOLDT-BRIDGEVILLE | 105/005 | ICW | F | 2020_(4b) On structure in bucket 4 | [5 empty] | North Coast | WSIP | [8 empty] | ETL.1810 | 44322554 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
119164291 | T2 MENDO-WLLTS-FT BRAGG 29/11 RPL DAMPER | 44610681 | MENDOCINO-WILLITS-FORT BRAGG | 029/011 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.6016724 | 39.3483 | ETL.7550 | 40627066 | Damper-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
119164310 | T3 COLGATE-GRASS VALLEY 007/168 RPL ANCW | 44371196 | COLGATE-GRASS VALLEY | 007/168 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.093922 | 39.2788 | ETL.6490 | 40665605 | Anchor-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119164320 | T2 HUMBOLDT-TRINITY 58/001 RPR GYWW | 44299237 | HUMBOLDT-TRINITY | 058/001 | ICW | E | 2020_(3) On high spread structure |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.139448 | 40.7656 | ETL.1820 | 44553876 | Guy Wire-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
119164323 | T2 TRINITY-MAPLE CREEK 44/3 INST DAMPER | 44273074 | TRINITY-MAPLE CREEK | 044/003 | ICW | E | 2020_(3) On high spread structure |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.697538 | 40.7451 | ETL.8170 | 40699975 | Damper-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
119164324 | T3 FRNCH MDWS-MDDLE FORK 9/170 INST DMPW | 44371596 | FRENCH MEADOWS-MIDDLE FORK | 009/170 | ICW | E | 2020_(3) On high spread structure |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.549678 | 39.0178 | ETL.6870 | 40664828 | Damper-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119164328 | T2 CAYUCOS-CAMBRIA 12/077 RPLC POLE | 31508524 | CAYUCOS-CAMBRIA | 012/077 | 70Y | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-121.022758 | 35.5506 | ETL.8560 | 40667163 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Pismo Beach |  | Y - 14
119164331 | T2 TRINITY-MAPLE CREEK 39/5L RPL POLE | 31509758 | TRINITY-MAPLE CREEK | 039/005 | 70Y | E | 2020_(2) High fire spread TD |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.618915 | 40.7192 | ETL.8170 | 44769576 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka
119164994 | T3 DI KILARC-CEDAR CRK 5/135 RPR STRW | 43939119 | KILARC-CEDAR CREEK | 005/135 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.978012 | 40.7102 | ETL.7290 | 40617665 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119165285 | DI HUMBOLDT-BRIDGEVIL 95/0 RMV PL BUTT | 44378879 | HUMBOLDT-BRIDGEVILLE | 095/000 | ICW | E | 2020_(3) On high spread structure | [5 empty] | North Coast | WSIP | [8 empty] | ETL.1810 | 44322345 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
119165433 | T3 DI DRUM-RIO OSO #1 3/40 RPR FOND | 44371587 | DRUM-RIO OSO #1 | 003/040 | ICQ | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.827061 | 39.2343 | ETL.1420 | 40582454 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento
119165494 | T3 DI DRUM-RIO OSO #1 3/40 RPR SPLS | 44371588 | DRUM-RIO OSO #1 | 003/040 | ICS | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.827061 | 39.2343 | ETL.1420 | 40623352 | Splice-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento
119165533 | T3NT DI MORGA-SN LNDRO #3 4/36 RPR FOND |  | MORAGA-SAN LEANDRO #3 | 004/036 | ICQ | F | 2020_(4) TD tag on high spread line |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-122.125781 | 37.7858 | ETL.2790 | 40804668 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  | EBMUD
119165615 | T3 DI COLGATE-CHALLENGE 8/143 RPLC SPLW | 44361610 | COLGATE-CHALLENGE | 008/143 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.1984 | 39.4255 | ETL.6480 | 40824215 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119165683 | T3 DI FULTON-PUEBLO 37/191A RPR SWITCH |  | FULTON-PUEBLO | 037/191A | ICE | E | 2020_(4b) On structure in bucket 4 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.66591 | 38.4968 | ETL.1600 | 40743260 | Switch | Out of Adjustment | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 623 | Lakeville
119165684 | T3 DI COLGATE-CHALLENGE 7/135 RMV BUTT | 44361612 | COLGATE-CHALLENGE | 007/135 | ICW | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.195678 | 39.4181 | ETL.6480 | 40611341 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119165686 | T3 DI COLGATE-CHALLENGE 7/135 RPR SPLW | 44361610 | COLGATE-CHALLENGE | 007/135 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.195678 | 39.4181 | ETL.6480 | 40611341 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119165687 | T3 DI LAURELES-OTTER 4/4 RPR GYWW | 44381542 | LAURELES-OTTER | 004/004 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | South | WSIP | [6 empty] | '-121.735825 | 36.431 | ETL.7380 | 44562656 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  | Y - Prog 401
119165689 | T3 DI LAURELES-OTTER 4/4 RPR GYWW | 44381542 | LAURELES-OTTER | 004/004 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | South | WSIP | [6 empty] | '-121.735825 | 36.431 | ETL.7380 | 44562780 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  | Y - Prog 401
119165751 | T3 DI COLGATE-CHALLENGE 8/143 RPR BOND | 44361610 | COLGATE-CHALLENGE | 008/143 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.1984 | 39.4255 | ETL.6480 | 40824215 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119165910 | T3 DI LAURELES-OTTER 4/4 RPR GYWW | 44381542 | LAURELES-OTTER | 004/004 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | South | WSIP | [6 empty] | '-121.735825 | 36.431 | ETL.7380 | 44562832 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  | Y - Prog 401
119165929 | T3 DI DEER CREEK-DRUM 3/83 RMV BUTT | 44361665 | DEER CREEK-DRUM | 003/083 | ICW | F | 2020_(1a) PSPS |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.809966 | 39.2617 | ETL.6690 | 40866658 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119165974 | T3 DI DEER CREEK-DRUM 3/83 RPR POLE | 44361664 | DEER CREEK-DRUM | 003/083 | ICW | E | 2020_(1a) PSPS |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.809966 | 39.2617 | ETL.6690 | 40866658 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119166010 | T3 DI DEER CREEK-DRUM 3/83 RPR SPLW | 44361664 | DEER CREEK-DRUM | 003/083 | ICW | E | 2020_(1a) PSPS |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.809966 | 39.2617 | ETL.6690 | 40866658 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119166110 | T3 DI MORAGA-SAN LEAND #3 5/41 RPL INSS | 31511126 | MORAGA-SAN LEANDRO #3 | 005/041 | 93K | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.121509 | 37.7737 | ETL.2790 | 40604524 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  |  | ACRP
119166113 | T3NT DI COLGATE-CHALLENGE 4/83 RMV BUTT | 44371193 | COLGATE-CHALLENGE | 004/083 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.162487 | 39.3822 | ETL.6480 | 40655138 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119166116 | T3NT DI COLGATE-CHALLENGE 2/55 RMV BUTT | 44371193 | COLGATE-CHALLENGE | 002/055 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.167405 | 39.3629 | ETL.6480 | 40664548 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119166126 | T3 VOLTA-DESCHUTES 0/5 RPL POLE | 31507081 | VOLTA-DESCHUTES | 000/005 | 70Y | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.87047 | 40.4603 | ETL.8290 | 40656907 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | released 7-13-20
119166143 | T2 VOLTA-DESCHUTES 11/249 RPLC POLE | 31508171 | VOLTA-DESCHUTES | 011/249 | 70Y | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.081207 | 40.5109 | ETL.8290 | 40825156 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | released 7-13-20
119166149 | T2 VOLTA-DESCHUTES 13/276 RPLC POLE | 31508171 | VOLTA-DESCHUTES | 013/276 | 70Y | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.104063 | 40.5176 | ETL.8290 | 40669479 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | released 7-13-20
119166161 | DI HUMBOLDT-TRINITY 045/005A REPL PL | 31506039 | HUMBOLDT-TRINITY | 045/005 | 70Y | E | 2020_(4) TD tag on high spread line | [5 empty] | North Coast | WSIP | [6 empty] | '-122.937207 | 40.7193 | ETL.1820 | 44560583 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS erdy | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka
119166200 | T2 KILARC-DESCHUTES 9/203 RPLC POLE | 31507647 | KILARC-DESCHUTES | 009/203 | 70Y | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.002473 | 40.5846 | ETL.7300 | 40877958 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain |  |  | released 7-13-20
119166217 | T2 KILARC-DESCHUTES 2/050 REFRAME | 31510881 | KILARC-DESCHUTES | 002/050 | 93E | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.891824 | 40.6474 | ETL.7300 | 40868553 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  | released 7-13-20
119166263 | T2 KILARC-DESCHUTES 2/48 RPL POLE | 31507647 | KILARC-DESCHUTES | 002/048 | 70Y | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.890636 | 40.6483 | ETL.7300 | 40817202 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain
119166346 | T3 KILARC-DESCHUTES 0/5 REFRAME CRSW | 31507069 | KILARC-DESCHUTES | 000/005 | 93E | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.873104 | 40.6752 | ETL.7300 | 40827951 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  | released 7-13-20
119166488 | T2 TRINITY-MAPLE CREEK 000/00A RPL POLE | 31505649 | TRINITY-MAPLE CREEK | 000/000A | 70Y | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.530267 | 40.7126 | ETL.8170 | 44966204 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE erdy | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka
119166503 | T2 TRINITY-MAPLE CREEK 000/001 RPL POLE | 31505649 | TRINITY-MAPLE CREEK | 000/001 | 70Y | E | 2020_(4) TD tag on high spread line |  | DLFL | Placeholder notification | TR2 |  | North Coast | WSIP | [6 empty] | '-123.530512 | 40.7124 | ETL.8170 | 44966205 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE erdy | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka
119166530 | T2 TRINITY-MAPLE CREEK 000/002 RPL POLE | 31505649 | TRINITY-MAPLE CREEK | 000/002 | 70Y | E | 2020_(4) TD tag on high spread line |  | DLFL | Placeholder notification | TR2 |  | North Coast | WSIP | [6 empty] | '-123.531045 | 40.7122 | ETL.8170 | 44966206 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE erdy | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka
119166584 | T3 FULTON-CALISTOGA 3/005 RPL POLE | 31507363 | FULTON-CALISTOGA | 003/005 | 70Y | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.485897 | 38.5386 | ETL.6880 | 40769769 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville
119166709 | T2 DI CARIBOU#2 ;1/22 RMV PL BUTT |  | CARIBOU #2 | ;001/022 | ICW | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-120.960768 | 40.0033 | ETL.6280 | 40659831 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119166724 | T2 DI TRINITY-MAPLE CRK 45/4 BOND GUY | 44273074 | TRINITY-MAPLE CREEK | 045/004 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.716487 | 40.7502 | ETL.8170 | 44565336 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
119166802 | DI BRDGVLL-CTTNWD 0/4 RPR GYWW | 43939216 | BRIDGEVILLE-COTTONWOOD | 000/004 | ICW | E | 2020_(4) TD tag on high spread line | [5 empty] | North Valley | WSIP | [8 empty] | ETL.1110 | 44424591 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119166809 | DI BRDGVLL-CTTNWD 0/4 RPR GYWW | 43939216 | BRIDGEVILLE-COTTONWOOD | 000/004 | ICW | E | 2020_(4) TD tag on high spread line | [5 empty] | North Valley | WSIP | [8 empty] | ETL.1110 | 44424592 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119166844 | DI BRDGVLL-CTTNWD 0/4 RPR GYWW | 43939216 | BRIDGEVILLE-COTTONWOOD | 000/004 | ICW | E | 2020_(4) TD tag on high spread line | [5 empty] | North Valley | WSIP | [8 empty] | ETL.1110 | 44424593 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119166881 | T2 DI CARIBOU #2 ;1/5 RMV PL BUTT |  | CARIBOU #2 | ;001/005 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-120.96705 | 40.0099 | ETL.6280 | 40768896 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119166894 | DI BRDGVLL-CTTNWD 0/4 RPL CRSW | 43939216 | BRIDGEVILLE-COTTONWOOD | 000/004 | ICW | E | 2020_(4) TD tag on high spread line | [5 empty] | North Valley | WSIP | [6 empty] | '-122.272785 | 40.3994 | ETL.1110 | 44424590 | Crossarm-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119166896 | DI BRDGVLL-CTTNWD 0/4 RMV PL BUTT | 43939216 | BRIDGEVILLE-COTTONWOOD | 000/004 | ICW | F | 2020_(4b) On structure in bucket 4 | [5 empty] | North Valley | WSIP | [8 empty] | ETL.1110 | 44424592 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119167031 | T3NT DI COLGT-CHALLENGE 6/111 INS NUMBR | 44361612 | COLGATE-CHALLENGE | 006/111 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.177967 | 39.3997 | ETL.6480 | 44695497 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119167128 | T2 DRM-GRSS VLLY-WMR B016/366 INST MRKW | 44389587 | DRUM-GRASS VALLEY-WEIMAR | B016/366 | ICS | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-120.957249 | 39.1199 | ETL.6760 | 44922916 | Structure-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento
119167178 | T2 PHILO JCT-ELK 31/6 RPL INSW | 31469922 | PHILO JCT-ELK | 031/006 | 93I | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.622913 | 39.1289 | ETL.7780 | 40826087 | Insulator-Wood | No Good/Out of Stdrd | Replace | CONS srdy | CONS | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Lakeville
119167282 | T2 DI CARIBOU #2 :6/2 RPLC SPLW |  | CARIBOU #2 | :006/002 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-120.979528 | 39.9694 | ETL.6280 | 40659889 | Splice-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119167455 | T2 DI MORRO BAY-TEMPLETON 5/24 RPR OPGW |  | MORRO BAY-TEMPLETON | 005/024 | ICS | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-120.78575 | 35.4179 | ETL.5933 | 40753216 | Shield Wire / OPGW-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Pismo Beach |  | Y - 10
119167813 | T2 WV HMBLDT-TRNTY 95/12 INS INSW | 31509856 | HUMBOLDT-TRINITY | 095/012 | 93I | E | 2020_(2) High fire spread TD |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.787614 | 40.7576 | ETL.1820 | 44924629 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSE erdy | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Eureka
119167938 | T2 DI CARIBOU #2 ;1/10 REFRAME | 31507060 | CARIBOU #2 | ;001/010 | 93E | E | 2020_(2) High fire spread TD |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-120.966952 | 40.0079 | ETL.6280 | 40593017 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain
119167982 | LAYTONVILLE-WILLITS 0/8 REPLUMB POLE | 44610677 | LAYTONVILLE-WILLITS | 000/008 | ICW | E | 2020_(4) TD tag on high spread line | [5 empty] | North Coast | WSIP | [6 empty] | '-123.321934 | 39.4108 | ETL.8360 | 40876424 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
119168083 | T3 DI KILARC-CEDAR CREEK 3/87 RPR STRW | 43939119 | KILARC-CEDAR CREEK | 003/087 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.940665 | 40.6991 | ETL.7290 | 40577356 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119168092 | T2NT DI MI-WUK-CURTIS 25/2 RMV BUTT |  | ETL.1073.POLE.WOOD | 025/002 | ICW | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-120.294848 | 37.9855 | ETL.1073 | 40643775 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Victor
119168096 | T2 DI MI-WUK-CURTIS 25/2 RPR GYWW | 44623240 | ETL.1073.POLE.WOOD | 025/002 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-120.294848 | 37.9855 | ETL.1073 | 40643775 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog 401
119168124 | T2 DI KILARC-DESCHUTES 11/244 RMV BUTT | 43930440 | KILARC-DESCHUTES | 011/244 | ICW | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.027281 | 40.5697 | ETL.7300 | 40770435 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119168126 | T2 DI KILARC-DESCHUTES 11/244 RPR GYWW | 43930440 | KILARC-DESCHUTES | 011/244 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.027281 | 40.5697 | ETL.7300 | 40770435 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119168385 | T2 DI TRINITY-MAPLE CRK 5/5A RMV BUTT | 44299848 | TRINITY-MAPLE CREEK | 005/005A | ICW | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.030752 | 40.7331 | ETL.8170 | 44859212 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
119168822 | DI HUMBOLDT-BRDGVLL 103/1R RMV PL BUTT | 44398571 | HUMBOLDT-BRIDGEVILLE | 103/001 | ICW | F | 2020_(4b) On structure in bucket 4 | [5 empty] | North Coast | WSIP | [8 empty] | ETL.1810 | 44322502 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
119169335 | T2 DI CARIBOU #2 0/17 RMV PL BUTT |  | CARIBOU #2 | ;000/017 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-120.962288 | 40.0205 | ETL.6280 | 40824669 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119169383 | T2 DI CARIBOU #2 16/9 RMV PL BUTT |  | CARIBOU #2 | 016/009 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.090562 | 40.0152 | ETL.6280 | 40867537 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119169488 | T3 DI PTTSURG-SN MTO 27/109 RPR SHLS | 44609776 | PITTSBURG-SAN MATEO | 027/109 | ICS | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.017937 | 37.6879 | ETL.5463 | 40764882 | Shield Wire / OPGW-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - Prog 402
119169580 | T2 DI KILARC-DESCHUTS 11/239 RMV PL BUTT | 44406469 | KILARC-DESCHUTES | 011/239 | ICW | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.022578 | 40.5709 | ETL.7300 | 40617697 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119169584 | T2 DI CARIBOU #2 1/14 REFRAME | 31507060 | CARIBOU #2 | ;001/014 | 93E | E | 2020_(2) High fire spread TD |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-120.964812 | 40.0063 | ETL.6280 | 40751748 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain
119169619 | T2 DI CARIBOU #2 1/14 RMV PL BUTT |  | CARIBOU #2 | ;001/014 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-120.964812 | 40.0063 | ETL.6280 | 40751748 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119169743 | T2 DI TRINITY-MAPLE CREEK 36/1 RPR GYWW | 44273074 | TRINITY-MAPLE CREEK | 036/001 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Coast | WSIP | [8 empty] | ETL.8170 | 44271138 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
119169744 | T2 DI TRINITY-MAPLE CREEK 36/1 RPL ANCW | 31507467 | TRINITY-MAPLE CREEK | 036/001 | 93E | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Coast | WSIP | [8 empty] | ETL.8170 | 44271139 | Anchor-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Eureka
119169800 | T2 DI MAPLE CREEK-HOOPA 25/2 RPR WDPKR | 44192340 | MAPLE CREEK-HOOPA | 015/007 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.700172 | 40.9165 | ETL.7490 | 44145856 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
119169801 | T2NT DI MAPLE CREEK-HOOPA 25/2 INS GMKW | 44394730 | MAPLE CREEK-HOOPA | 015/007 | ICW | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.700172 | 40.9165 | ETL.7490 | 44145859 | Guy Wire Mark /Indic-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
119169802 | T2 DI MAPLE CREEK-HOOPA 25/2 INS MRKW | 44394730 | MAPLE CREEK-HOOPA | 015/007 | ICW | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.700172 | 40.9165 | ETL.7490 | 44145859 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
119169803 | DI HUMBOLDT-TRINITY 103/3 RPL HRDD | 44299237 | HUMBOLDT-TRINITY | 103/003 | ICW | E | 2020_(4) TD tag on high spread line | [5 empty] | North Coast | WSIP | [6 empty] | '-123.924835 | 40.7646 | ETL.1820 | 44560559 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
119169805 | T2NT DI TRNTY-MAPLE CREEK 44/3 INS MRKW | 44273074 | TRINITY-MAPLE CREEK | 044/003 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.697538 | 40.7451 | ETL.8170 | 44565345 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
119169806 | DI HUMBOLDT-TRINITY 102/000 RPL INSW | 31509856 | HUMBOLDT-TRINITY | 102/000 | 93I | E | 2020_(2) High fire spread TD | [5 empty] | North Coast | WSIP | [6 empty] | '-123.898598 | 40.7663 | ETL.1820 | 40630995 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSE erdy | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Eureka
119169826 | DI HUMBOLDT-BRIDGEVILLE 88/3R RPL STRW | 31508093 | HUMBOLDT-BRIDGEVILLE | 088/003 | 70Y | E | 2020_(4) TD tag on high spread line | [5 empty] | North Coast | WSIP | [8 empty] | ETL.1810 | 44322245 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka
119169829 | DI GRBRVLL LYTNVLL 45/6 RPR GYWW | 44311204 | GARBERVILLE-LAYTONVILLE | 045/006 | ICW | E | 2020_(4) TD tag on high spread line | [5 empty] | North Coast | WSIP | [6 empty] | '-123.613537 | 39.9661 | ETL.8365 | 44403647 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
119169840 | DI GRBRVLL LYTNVLL 45/6 RMV PL BUTT | 44311203 | GARBERVILLE-LAYTONVILLE | 045/006 | ICW | F | 2020_(4b) On structure in bucket 4 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.613537 | 39.9661 | ETL.8365 | 44403647 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
119169857 | NT DI HUMBOLDT-BRIDGEVILLE 88/1 INS MRKW | 44107184 | HUMBOLDT-BRIDGEVILLE | 088/001 | ICW | F | 2020_(4b) On structure in bucket 4 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.811986 | 40.5032 | ETL.1810 | 44322238 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
119169858 | NT DI HUMBOLDT-BRIDGEVILLE 88/1 INS MRKW | 44107184 | HUMBOLDT-BRIDGEVILLE | 088/001 | ICW | F | 2020_(4b) On structure in bucket 4 | [5 empty] | North Coast | WSIP | [6 empty] | '-123.811986 | 40.5032 | ETL.1810 | 44322239 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
119169903 | T3 DI CLGTE CHLLNGE 5/103 RPL HRDD | 44371192 | COLGATE-CHALLENGE | 005/103 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.165737 | 39.3969 | ETL.6480 | 44695492 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119169925 | DI RIO DELL JCT-BRDGVLL 38/1L RPL STRW | 31508280 | RIO DELL JCT-BRIDGEVILLE | 038/001 | 70Y | E | 2020_(4) TD tag on high spread line | [5 empty] | North Coast | WSIP | [8 empty] | ETL.7850 | 44403575 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka
119169929 | DI RIO DELL JCT-BRDGVLL 38/1 RMV PL BUTT | 44326491 | RIO DELL JCT-BRIDGEVILLE | 038/001 | ICW | F | 2020_(4b) On structure in bucket 4 | [5 empty] | North Coast | WSIP | [8 empty] | ETL.7850 | 44403575 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
119170000 | DI HMBLDT-BRIDGEVILLE 105/7 RPL BRACKET | 44107184 | HUMBOLDT-BRIDGEVILLE | 105/007 | ICW | E | 2020_(4) TD tag on high spread line | [5 empty] | North Coast | WSIP | [8 empty] | ETL.1810 | 44322562 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
119170001 | NT DI HMBLDT-BRIDGEVILLE 105/7 INS MRKW | 44398571 | HUMBOLDT-BRIDGEVILLE | 105/007 | ICW | F | 2020_(4b) On structure in bucket 4 | [5 empty] | North Coast | WSIP | [8 empty] | ETL.1810 | 44322562 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
119170188 | T3 DI COLGATE-CHALLENGE 3/76 RPL POLE | 31506352 | COLGATE-CHALLENGE | 003/076 | 70Y | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.163586 | 39.3777 | ETL.6480 | 40822734 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento
119170299 | T3 DI COLGATE-CHALLENGE 004/093 RPR SPLW | 44361610 | COLGATE-CHALLENGE | 004/093 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.160785 | 39.3892 | ETL.6480 | 44695490 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119170552 | T3NT DI COLGTE-CHALLENGE 5/110 INST MRKW | 44361608 | COLGATE-CHALLENGE | 005/110 | ICS | F | 2020_(3) On high spread structure |  |  | Likely MAT error - delink to correct | TR3 |  | North Valley | WSIP | [6 empty] | '-121.176135 | 39.3994 | ETL.6480 | 44695496 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119170619 | T3 DI LAURELES-OTTER 3/5 RPLC HRDW | 44392359 | LAURELES-OTTER | 003/005 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | South | WSIP | [6 empty] | '-121.722848 | 36.438 | ETL.7380 | 44838826 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  | Y - Prog 401
119170659 | T2 DI SLO-SM 15/66 RPL INSS | 31510359 | SAN LUIS OBISPO-SANTA MARIA | 015/066 | 93K | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | South | WSIP | [6 empty] | 120.4982 | 35.0942 | ETL.3540 | 40836331 | Insulator-Steel | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - Prog 402
119170700 | T3 DI LAURELES-OTTER 3/5 RPLC HRDW | 44392360 | LAURELES-OTTER | 003/005 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | South | WSIP | [6 empty] | '-121.722848 | 36.438 | ETL.7380 | 44838831 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  | Y - Prog 401
119170703 | T2 DI TRINITY-MAPLE CRK 5/0 RPLC HRDW | 44273074 | TRINITY-MAPLE CREEK | 005/000 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Coast | WSIP | [8 empty] | ETL.8170 | 44420585 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
119170818 | T3 DI COLGATE-CHALLENGE 6/14 RPR SPLW | 44361610 | COLGATE-CHALLENGE | 006/114 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.18301 | 39.4004 | ETL.6480 | 40664715 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119171142 | T2 DI CARIBOU #2 :6/5 RPLC INSW | 31506251 | CARIBOU #2 | :006/005 | 93I | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-120.977264 | 39.968 | ETL.6280 | 40799668 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSE erdy | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Table Mountain
119171236 | DI HUMDOLDT-TRINITY 102/3R RPR STRW | 44299237 | HUMBOLDT-TRINITY | 102/003 | ICW | E | 2020_(2) High fire spread TD | [5 empty] | North Coast | WSIP | [6 empty] | '-123.915197 | 40.7614 | ETL.1820 | 44560443 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
119171317 | T2 EI BRIDGEVILLE-GARBERVILLE 36/0 RPL P | 31515485 | BRIDGEVILLE-GARBERVILLE | 036/000 | 70Y | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.792536 | 40.103 | ETL.6220 | 40591160 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS hold | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka
119171365 | T2 DI CARIBOU #2 15/22 RPR STRW |  | CARIBOU #2 | 015/022 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.101143 | 40.0172 | ETL.6280 | 40698677 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119171367 | T2 DI CARIBOU #2 15/22 RPR CRSW |  | CARIBOU #2 | 015/022 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.101143 | 40.0172 | ETL.6280 | 40698677 | Crossarm-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119171534 | T2 DI CARIBOU #2 018/000 BOND GUY |  | CARIBOU #2 | 018/000 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.061181 | 40.0195 | ETL.6280 | 40599711 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119171763 | T2 EI BRIDGEVILLE-GARBERVILLE 35/8 RPL P | 31508614 | BRIDGEVILLE-GARBERVILLE | 035/008 | 70Y | E | 2020_(2) High fire spread TD |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.788093 | 40.1043 | ETL.6220 | 40862861 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka
119171785 | T2 EI BRIDGEVILLE-GARBERVILLE 35/7 RPL P | 31508614 | BRIDGEVILLE-GARBERVILLE | 035/007 | 70Y | E | 2020_(2) High fire spread TD |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.786773 | 40.1046 | ETL.6220 | 40810360 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka
119171813 | T3NT DI DRUM-RIO OSO #1 9/96 RPR FOND | 44371589 | DRUM-RIO OSO #1 | 009/096 | ICQ | F | 2020_(2) High fire spread TD |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.912623 | 39.1783 | ETL.1420 | 40814354 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento
119171986 | T2 DI TRINITY-MPL CRK 21/1 RMV PL BUTT | 44299848 | TRINITY-MAPLE CREEK | 021/001 | ICW | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Coast | WSIP | [8 empty] | ETL.8170 | 44420623 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
119172195 | DI HUMBOLDT-BRIDGEVILLE 102/3C RPL STRW | 31508093 | HUMBOLDT-BRIDGEVILLE | 102/003 | 70Y | E | 2020_(2) High fire spread TD | [5 empty] | North Coast | WSIP | [8 empty] | ETL.1810 | 44322491 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka
119172297 | T3 DI COLGATE-ALLGHNY 11/298 RMV BUTT | 44365654 | COLGATE-ALLEGHANY | 011/298 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.027924 | 39.4002 | ETL.6470 | 40818486 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119172342 | T3NT DI COLGATE-ALLGHNY 11/298 INST MRKW | 44365654 | COLGATE-ALLEGHANY | 011/298 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.027924 | 39.4002 | ETL.6470 | 40818486 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119172345 | T3 DI COLGATE-ALLGHNY 11/298 RPLC HRDD | 44365653 | COLGATE-ALLEGHANY | 011/298 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.027924 | 39.4002 | ETL.6470 | 40818486 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119172447 | DI HUMBOLDT-BRIDGEVILLE 101/1 RPR STRW | 44379658 | HUMBOLDT-BRIDGEVILLE | 101/001 | ICW | E | 2020_(2) High fire spread TD | [5 empty] | North Coast | WSIP | [8 empty] | ETL.1810 | 44322466 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
119172449 | T3 DI IGNACIO-BOLINAS #2 24/270 RPR GYWW |  | IGNACIO-BOLINAS #2 | 024/270 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  |  | LATE | North Coast | WSIP | [8 empty] | ETL.7180 | 44360905 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
119172461 | T2 EI BRIDGEVILLE-GARBERVILLE 35/5 RPL P | 31508614 | BRIDGEVILLE-GARBERVILLE | 035/005 | 70Y | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.783442 | 40.1053 | ETL.6220 | 40752680 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka
119172462 | T2 EI BRIDGEVILLE-GARBERVILLE 35/6 RPL P | 31508614 | BRIDGEVILLE-GARBERVILLE | 035/006 | 70Y | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.784561 | 40.1051 | ETL.6220 | 41088039 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka
119172586 | T2 DI TRINITY-MAPLE CRK 31/1 RPR GYWW | 44273074 | TRINITY-MAPLE CREEK | 031/001 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.474761 | 40.6902 | ETL.8170 | 44565314 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
119172587 | T2 DI TRINITY-MAPLE CRK 31/1 RPR GYWW | 44273074 | TRINITY-MAPLE CREEK | 031/001 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.474761 | 40.6902 | ETL.8170 | 44565602 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
119172588 | T2 DI TRINITY-MAPLE CRK 31/1 RPR GYWW | 44273074 | TRINITY-MAPLE CREEK | 031/001 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.474761 | 40.6902 | ETL.8170 | 44565619 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
119172589 | T2 DI TRINITY-MAPLE CRK 35/8L RPL POLE | 31506143 | TRINITY-MAPLE CREEK | 035/008 | 70Y | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.556324 | 40.7222 | ETL.8170 | 44565511 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka
119172701 | T2 DI TRINITY-MAPLE CREEK 35/8C RPL POLE | 31506143 | TRINITY-MAPLE CREEK | 035/008 | 70Y | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.556324 | 40.7222 | ETL.8170 | 44565596 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka
119172702 | T2 DI TRINITY-MAPLE CREEK 35/8R RPL POLE | 31506143 | TRINITY-MAPLE CREEK | 035/008 | 70Y | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.556324 | 40.7222 | ETL.8170 | 44565510 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka
119172885 | T2NT DI PTTSBRG-SAN MATEO 21/82 RPR FOND |  | PITTSBURG-SAN MATEO | 021/082 | ICQ | F | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-121.927405 | 37.7487 | ETL.5463 | 40817953 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog 402
119172888 | T3 DI DONNELLS-MI-WUK 3/4 RPR STRW | 44623241 | DONNELLS-CURTIS | 003/004 | ICW | E | 2020_(2) High fire spread TD |  |  |  |  | LATE | Central | WSIP | [6 empty] | '-120.036818 | 38.1959 | ETL.1400 | 44775188 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 40 | USFS
119173396 | T3 DESABLA-CENTERVILLE 0/8 REPLUMB POLE | 44356201 | DESABLA-CENTERVILLE | 000/008 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.629918 | 39.8655 | ETL.6720 | 40862027 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119173412 | T2 DI BRDGVL-CTNWD 30/253 RPR GYWW | 43939216 | BRIDGEVILLE-COTTONWOOD | 030/253 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.836544 | 40.3641 | ETL.1110 | 44561191 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119173518 | T3 DI MAPLE CREEK-HOOPA 12/7 RMV BUTT | 44301081 | MAPLE CREEK-HOOPA | 012/007B | ICW | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-123.754332 | 40.9086 | ETL.7490 | 40810432 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
119173689 | T2 EI MDDL FRK-GLD HLL 19/151R REPL STRW | 31497889 | MIDDLE FORK-GOLD HILL | 019/151 | 70Y | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 | LATE | North Valley | WSIP | [6 empty] | '-120.869235 | 38.8917 | ETL.5140 | 44557760 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC erdy srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Sacramento
119173831 | T2 HUMBOLDT-TRINITY 50/0 RPL INSW | 31509856 | HUMBOLDT-TRINITY | 050/000 | 93I | E | 2020_(2) High fire spread TD |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.010925 | 40.7284 | ETL.1820 | 40635182 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSE erdy | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Eureka
119174176 | T2 DI KILARC-DESCHUTES 012/263 RPL SPLW | 43930440 | KILARC-DESCHUTES | 012/263 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.043839 | 40.5656 | ETL.7300 | 40592179 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | released 7-13-20
119174177 | T2 DI KILARC-DSCHUTES 011/247 RMV BUTT | 43930440 | KILARC-DESCHUTES | 011/247 | ICW | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.030005 | 40.5691 | ETL.7300 | 40868569 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119174201 | T3NT DI LAURELES-OTTER 5/2 RMV BUTTS | 44392361 | LAURELES-OTTER | 005/002 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | South | WSIP | [6 empty] | '-121.745012 | 36.4271 | ETL.7380 | 44562931 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing
119174221 | T3 DI COLGATE-CHALLENGE 4/91 RPR STRW | 44361610 | COLGATE-CHALLENGE | 004/091 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.161096 | 39.3878 | ETL.6480 | 40598504 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119174320 | T3 DI LAURELES-OTTER 5/2 RPR HRDW | 44392362 | LAURELES-OTTER | 005/002 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | South | WSIP | [6 empty] | '-121.745012 | 36.4271 | ETL.7380 | 44562931 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  | Y - Prog 401
119174385 | T3 DI PITTSBURG-SAN MATO 23/092 RPR HRDT | 44623139 | PITTSBURG-SAN MATEO | 023/092 | ICQ | E | 2020_(3) On high spread structure |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-121.963067 | 37.7326 | ETL.5463 | 40805061 | Hardware-Tower | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 10
119174593 | T2 EXCHEQUER-INDIAN FLAT 20/73 REPL TOWR | 31508860 | EXCHEQUER-YOSEMITE | 020/073 | 70S | E | 2020_(2) High fire spread TD |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-120.028244 | 37.5843 | ETL.8650 | 40660804 | Structure-Tower | No Good/Out of Stdrd | Replace | PROD | PROD | Prod Special (No Labor) | Complete | PEND | LC | TLQ | Pole Program | Capital | 426 | Fresno |  |  | BLM
119174669 | T2 DI CARIBOU #2 ;001/015 RMV PL BUTT |  | CARIBOU #2 | ;001/015 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-120.964265 | 40.0058 | ETL.6280 | 40768847 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119174726 | T2 DI TRINITY-MAPLE CRK 25/1 RMV PL BUTT | 44299848 | TRINITY-MAPLE CREEK | 025/001 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR2 |  | North Coast | WSIP | [8 empty] | ETL.8170 | 44420631 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
119174727 | T2 DI TRINITY-MAPLE CRK 25/1 RMV PL BUTT | 44299848 | TRINITY-MAPLE CREEK | 025/001 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR2 |  | North Coast | WSIP | [8 empty] | ETL.8170 | 44420632 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
119174728 | T2 DI TRINITY-MAPLE CRK 25/1 RMV PL BUTT | 44299848 | TRINITY-MAPLE CREEK | 025/001 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR2 |  | North Coast | WSIP | [8 empty] | ETL.8170 | 44420633 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
119174824 | T3NT DI CARIBOU #2 8/2 RMV POLE BUTT |  | CARIBOU #2 | 008/002 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.221982 | 40.0135 | ETL.6280 | 40675402 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119174891 | T2 DI CLNDR SW STA-MESA 19/90 RPL HANGR | 44388365 | SAN LUIS OBISPO-SANTA MARIA | 019/090 | ICQ | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-120.458676 | 35.0363 | ETL.3540 | 40636618 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Pismo Beach |  | Y - Prog 402
119174892 | T2 DI SLO-SM 19/90 RPL INSS | 31510359 | SAN LUIS OBISPO-SANTA MARIA | 019/090 | 93K | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-120.458676 | 35.0363 | ETL.3540 | 40636618 | Insulator-Steel | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - Prog 402
119174898 | T2 DI TRINITY-MAPLE CREEK 12/0 RPLC INSW | 31509759 | TRINITY-MAPLE CREEK | 012/000 | 93I | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.129279 | 40.77 | ETL.8170 | 40638093 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Eureka
119174913 | T2 DI CARIBOU #2 1/7 RMV PL BUTT |  | CARIBOU #2 | ;001/007 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-120.96714 | 40.0089 | ETL.6280 | 40811553 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119174917 | T2 DI CARIBOU #2 0/16 RMV PL BUTT |  | CARIBOU #2 | ;000/016 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-120.962593 | 40.021 | ETL.6280 | 40826432 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119174991 | DI HUMBOLDT-BRIDGEVILLE 91/3R RPL STRW | 31508093 | HUMBOLDT-BRIDGEVILLE | 091/003 | 70Y | E | 2020_(2) High fire spread TD | [5 empty] | North Coast | WSIP | [8 empty] | ETL.1810 | 44322301 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka
119174994 | T2 DI DIVIDE-CABRILLO #2 5/67 INST DAMW |  | DIVIDE-CABRILLO #2 | 005/067 | ICW | E | 2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-120.436737 | 34.756 | ETL.1370 | 44296268 | Damper-Wood | Missing | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - 12
119174998 | T3 EI EAGLE RK-FLTN-SLRD 37/187 RPL INSS | 31515212 | EAGLE ROCK-FULTON-SILVERADO | 037/187 | 92E | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.65456 | 38.4971 | ETL.4392 | 40832918 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Lakeville
119175041 | DI TRINITY-MAPLE CREEK 31/0R RPL POLE | 31508602 | TRINITY-MAPLE CREEK | 031/000 | 70Y | E | 2020_(4) TD tag on high spread line | [5 empty] | North Coast | WSIP | [8 empty] | ETL.8170 | 44420661 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka
119175070 | T2 DI KILARC-DESCHUTES 16/337 RPR SPLW | 43930440 | KILARC-DESCHUTES | 016/337 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.115211 | 40.5635 | ETL.7300 | 40770409 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119175071 | T2 DI KILARC-DESCHUTES 16/337 RMV BUTT | 43930440 | KILARC-DESCHUTES | 016/337 | ICW | E | 2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.115211 | 40.5635 | ETL.7300 | 40770409 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119175075 | T2 DI TRNTY-MAPLE CRK 27/5 RPL DAMW | 44364310 | TRINITY-MAPLE CREEK | 027/005 | ICS | E | 2020_(2) High fire spread TD |  |  |  | TR2 |  | North Coast | WSIP | [8 empty] | ETL.8170 | 44420645 | Damper-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Eureka
119175079 | T2 DI TRNTY-MAPLE CRK 27/5 RMV PL BUTT | 44299848 | TRINITY-MAPLE CREEK | 027/005 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR2 |  | North Coast | WSIP | [8 empty] | ETL.8170 | 44420645 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
119175093 | DI HMBLDT-BRDGVLLE 98/1 RPL INSW | 31506838 | HUMBOLDT-BRIDGEVILLE | 098/001 | 93I | E | 2020_(4) TD tag on high spread line | [5 empty] | North Coast | WSIP | [6 empty] | '-123.879136 | 40.635 | ETL.1810 | 40616432 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC erdy srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Eureka
119175138 | T2 DI CARIBOU #2 14/5 RMV DEBRIS |  | CARIBOU #2 | 014/005 | ICW | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.126589 | 40.0284 | ETL.6280 | 40768815 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119175174 | T2NT DI CARIBOU #2 1/15 INST MRKW |  | CARIBOU #2 | :001/015 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.046575 | 40.0047 | ETL.6280 | 40751799 | Marker (i.e. signs)-Wood | Missing | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119176141 | T2 DI CARIBOU #2 :7/4 RPR WDPKR |  | CARIBOU #2 | :007/004 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-120.96202 | 39.9602 | ETL.6280 | 40769638 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119176156 | T2 DI CARIBOU #2 015/000 RPR GYWW |  | CARIBOU #2 | 015/000 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.111573 | 40.0239 | ETL.6280 | 40614872 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119176369 | T3 DI IGNACIO-BLINS #2 024/269 RPR GYWW |  | IGNACIO-BOLINAS #2 | 024/269 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.722347 | 37.9698 | ETL.7180 | 44360928 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
119176429 | T2 DI TRINITY-MAPLE CRK 31/3 RMV PL BUTT | 44299848 | TRINITY-MAPLE CREEK | 031/003 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.481094 | 40.6893 | ETL.8170 | 44769573 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
119176487 | T2NT DI CRTINA-MNDCNO #1 56/278 RPR FOND |  | CORTINA-MENDOCINO #1 | 056/278 | ICQ | F | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.126379 | 39.2323 | ETL.1330 | 40861443 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville
119176695 | T3 DI GYSRS #7-EGL RK-TWR 0/7 RPR FOND |  | GEYSERS #7-EAGLE ROCK | 000/007 | ICQ | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.810737 | 38.8173 | ETL.1680 | 40818237 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville
119176781 | T3 DI VOLTA-DESCHUTES 7/151A RPL CRSW | 31507066 | VOLTA-DESCHUTES | 007/151A | 93E | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.996325 | 40.4918 | ETL.8290 | 43682177 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain
119176875 | T2 DI KILARC-DESCHUTES 16/332 RMV BUTT | 43930440 | KILARC-DESCHUTES | 016/332 | ICW | E | 2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.110418 | 40.5635 | ETL.7300 | 40617694 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119176879 | T2 DI KILARC-DESCHUTES 16/332 RPR SPLW | 43930440 | KILARC-DESCHUTES | 016/332 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.110418 | 40.5635 | ETL.7300 | 40617694 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119176886 | T3 DI MORAGA-SAN LEAN #1 1/12 RPR SPLS | 44621663 | MORAGA-SAN LEANDRO #1 | 001/012 | ICS | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.153424 | 37.8274 | ETL.2770 | 40704858 | Splice-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - Prog 402
119176888 | T3NT DI MRGA-SAN LEAN #1 1/12 INST MRKS |  | MORAGA-SAN LEANDRO #1 | 001/012 | ICS | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-122.153424 | 37.8274 | ETL.2770 | 40646040 | Marker (i.e. signs)-Steel | No Good/Out of Stdrd | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Bay
119176981 | T2 DI TRINITY-MAPLE CRK 17/12C RPL POLE | 31509757 | TRINITY-MAPLE CREEK | 017/012 | 70Y | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Coast | WSIP | [8 empty] | ETL.8170 | 44420620 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka
119177089 | T2 DI CARIBOU #2 1/12 RMV BUTT |  | CARIBOU #2 | ;001/012 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-120.965895 | 40.0072 | ETL.6280 | 40664906 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119177168 | T3 DI KESWICK-TRINITY 0/1 RMV BUTT | 43939188 | KESWICK-TRINITY | 000/001 | ICW | E | 2020_(4b) On structure in bucket 4 |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-122.462303 | 40.6239 | ETL.7270 | 40586337 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119177385 | T2NT DI KILARC-DESCHUTES 12/252 RMV BUTT | 44406469 | KILARC-DESCHUTES | 012/252 | ICW | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.034268 | 40.568 | ETL.7300 | 40617703 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119177602 | T3 DI CORTINA-MENDOCNO #1 14/69 RPR FOND |  | CORTINA-MENDOCINO #1 | 014/069 | ICQ | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.457354 | 39.0282 | ETL.1330 | 40860975 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville
119177658 | T3 DI DESABLA-CENTERVILLE 0/13 RPR GYWW | 44356201 | DESABLA-CENTERVILLE | 000/013 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.628393 | 39.8627 | ETL.6720 | 44751924 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119177901 | T2NT DI CRTN-MNDCINO #1 29/139 RPR FOND | 44238817 | CORTINA-MENDOCINO #1 | 029/139 | ICQ | F | 2020_(2) High fire spread TD |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.718333 | 39.038 | ETL.1330 | 40872726 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville
119177906 | T3 DI BTTLE RCK TAP D.W.R. 0/2 RPR SHLDW |  | BOTTLE ROCK TAP D.W.R. | 000/002 | ICS | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.772374 | 38.833 | ETL.4771 | 40661119 | Shield Wire / OPGW-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville
119178161 | T2 DI CARIBOU #2 012/001 RPL SPLW |  | CARIBOU #2 | 012/001 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.163964 | 40.0234 | ETL.6280 | 40585968 | Splice-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119178165 | T2 DI CARIBOU #2 011/013 RPL INSW | 31506251 | CARIBOU #2 | 011/013 | 93I | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.166781 | 40.0216 | ETL.6280 | 40698208 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSE erdy | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Table Mountain
119178273 | T2 DI KILARC-DESCHUTES 17/353 RMV BUTT | 43930440 | KILARC-DESCHUTES | 017/353 | ICW | E | 2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.130379 | 40.5636 | ETL.7300 | 40602026 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119178275 | T2 DI KILARC-DESCHUTES 17/353 RPR SPLW | 43930440 | KILARC-DESCHUTES | 017/353 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.130379 | 40.5636 | ETL.7300 | 40602026 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119178336 | T2 DI CARIBOU #2 017/014 FILL HOLE |  | CARIBOU #2 | 017/014 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.070987 | 40.021 | ETL.6280 | 40769559 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119178424 | DI LAURELES-OTTER 003/004 WDPKR | 44392379 | LAURELES-OTTER | 003/004 | ICW | E | 2020_(2) High fire spread TD | [5 empty] | South | WSIP | [6 empty] | '-121.718817 | 36.4418 | ETL.7380 | 44562654 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  | Y - 13
119178427 | DI LAURELES-OTTER 003/004 WDPKR | 44392380 | LAURELES-OTTER | 003/004 | ICW | E | 2020_(2) High fire spread TD | [5 empty] | South | WSIP | [6 empty] | '-121.718817 | 36.4418 | ETL.7380 | 44562655 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing |  | Y - 13
119178552 | T3 EI WISHON-SAN JOAQUIN #3 4/5 RPL POLE | 31507342 | WISHON-SAN JOAQUIN #3 | 004/005 | 70Y | E | 2020_(1a) PSPS |  |  |  | TR3 | LATE | South | WSIP | [6 empty] | '-119.496555 | 37.1976 | ETL.9340 | 40763117 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Fresno |  | Y - 17
119178672 | T2NT DI CARIBOU #2 016/018 RMV PL BUTT |  | CARIBOU #2 | 016/018 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.08645 | 40.0168 | ETL.6280 | 40868139 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119178742 | T2 DI CARIBOU #2 016/018 REFRAME CRSW | 31507060 | CARIBOU #2 | 016/018 | 93E | E | 2020_(2) High fire spread TD |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.08645 | 40.0168 | ETL.6280 | 40868139 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain
119178743 | T2NT DI CARIBOU #2 017/028 RMV PL BUTT |  | CARIBOU #2 | 017/028 | ICW | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.061832 | 40.0205 | ETL.6280 | 40862055 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119178748 | T2NT DI KILARC-DESCHUTS 12/255 RMV DEBRI | 44406469 | KILARC-DESCHUTES | 012/255 | ICW | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.037095 | 40.5673 | ETL.7300 | 40656984 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119178749 | T2 DI MI-WUK-CURTIS 023/000 RPL POLE | 31508526 | ETL.1073.POLE.WOOD | 023/000 | 70Y | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-120.268287 | 38.0062 | ETL.1073 | 40580228 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor
119178908 | T2 DI TRINITY-MAPLE CRK 20/3 RMV PL BUTT | 44299848 | TRINITY-MAPLE CREEK | 020/003 | ICW | E | 2020_(3) On high spread structure |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.264976 | 40.724 | ETL.8170 | 44564200 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
119178983 | T2NT DI KILARC-DSCHUTS 12/266 RMV BUTT | 44406469 | KILARC-DESCHUTES | 012/266 | ICW | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.046501 | 40.5649 | ETL.7300 | 40771246 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119179064 | T2 DI MORRO BAY-TEMPLETON 12/51 RPL INSS | 31527001 | MORRO BAY-TEMPLETON | 012/051 | 93K | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-120.716774 | 35.5147 | ETL.5933 | 40612025 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - Prog 402
119179067 | T3 EI MDL FRK-GLD HL 16/131B RPR WDPK | 44361894 | MIDDLE FORK-GOLD HILL | 016/131B | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.839312 | 38.9202 | ETL.5140 | 42569842 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119179068 | T3 EI MDL FRK-GLD HL 16/131C RPR STRW | 44361894 | MIDDLE FORK-GOLD HILL | 016/131C | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.839394 | 38.9203 | ETL.5140 | 42569844 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119179072 | T2NT DI KILARC-DESCHUTES 12/266 RPR STRW | 44406469 | KILARC-DESCHUTES | 012/266 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.046501 | 40.5649 | ETL.7300 | 40771246 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119179079 | T2 DI CARIBOU #2 :002/017 RPR STRW |  | CARIBOU #2 | :002/017 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.02556 | 39.999 | ETL.6280 | 40809572 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119179162 | T3 EI WISHON-SAN JOAQUIN #3 4/4 RPL POLE | 31507342 | WISHON-SAN JOAQUIN #3 | 004/004 | 70Y | E | 2020_(1a) PSPS |  |  |  | TR3 | LATE | South | WSIP | [6 empty] | '-119.496547 | 37.1988 | ETL.9340 | 40764489 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Fresno |  | Y - 17
119179256 | T2NT DI KILARC-DESCHUTES 17/367 RMV BUTT | 44406469 | KILARC-DESCHUTES | 017/367 | ICW | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.145169 | 40.5636 | ETL.7300 | 40827912 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119179259 | T2 DI KILARC-DESCHUTES 17/354 RMV BUTT | 44406469 | KILARC-DESCHUTES | 017/354 | ICW | E | 2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.131304 | 40.5636 | ETL.7300 | 40676539 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119179362 | T2 DI KILARC-DESCHUTES 17/354 RPR STRW | 44406469 | KILARC-DESCHUTES | 017/354 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.131304 | 40.5636 | ETL.7300 | 40676539 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119179367 | T2 DI KILARC-DESCHUTES 16/342 RMV BUTT | 44406469 | KILARC-DESCHUTES | 016/342 | ICW | E | 2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.120023 | 40.5635 | ETL.7300 | 40617715 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119179396 | T3NT DI DRUM-SPAULDING 01/027 RMV BUTT | 44371592 | DRUM-SPAULDING | 001/027 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.74982 | 39.2533 | ETL.6770 | 44874802 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119179399 | T3 DI DRUM-SPAULDING 01/027 RRL INSW | 31507364 | DRUM-SPAULDING | 001/027 | 93I | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.74982 | 39.2533 | ETL.6770 | 44874817 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Sacramento
119179487 | T2NT DI KILARC-DESCHUTES 11/246 BTT | 44406469 | KILARC-DESCHUTES | 011/246 | ICW | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.029125 | 40.5693 | ETL.7300 | 40816232 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119179489 | T2 DI KILARC-DESCHUTES 15/325 RPR STRW | 44406469 | KILARC-DESCHUTES | 015/325 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.103894 | 40.5636 | ETL.7300 | 40668429 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119179600 | T3 EI WISHON-SAN JQN #3 004/004 CANCEL | 31521754 | WISHON-SAN JOAQUIN #3 | 004/004 | 71Y | E | 2020_(1a) PSPS |  |  | CANCEL/CNCL | TR3 | LATE | South | WSIP | [6 empty] | '-119.496547 | 37.1988 | ETL.9340 | 40764489 | Road | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLR | Roads | Capital | 374 | Fresno
119179635 | T3NT DI DEER CREEK-DRUM 3/80 RMV BUTT | 44371580 | DEER CREEK-DRUM | 003/080 | ICW | F | 2020_(1a) PSPS |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.8133 | 39.2626 | ETL.6690 | 40756928 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119179685 | T2 DI MORRO BAY-MESA 019/087 WSH INSU |  | MORRO BAY-MESA | 019/087 | ICD | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-120.60551 | 35.1823 | ETL.5290 | 40844460 | Insulator | Contaminated | Ground Wash |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 622 | Pismo Beach |  | Y - 13
119179879 | T3 DI MORAGA-OAKLND #1 1/13 WAS INSU | 44598173 | MORAGA-OAKLAND #1 | 001/013 | ICD | F | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.19172 | 37.8357 | ETL.2720 | 40689688 | Insulator | Contaminated | Ground Wash | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 622 | Bay
119179992 | T3 DI MORAGA-OAKLND #1 1/13 RMV DEBRIS | 44598172 | MORAGA-OAKLAND #1 | 001/013 | ICW | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.19172 | 37.8357 | ETL.2720 | 40659393 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Bay
119179997 | T2 DI KILARC-DESCHUTES 15/320 RPR POLE | 43930440 | KILARC-DESCHUTES | 015/320 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.099207 | 40.5638 | ETL.7300 | 40868575 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119180127 | T2 DI KILARC-DESCHUTES 013/283 RPLC STRW | 31507647 | KILARC-DESCHUTES | 013/283 | 70Y | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.063947 | 40.5645 | ETL.7300 | 40617709 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain
119180185 | T3 MORAGA-OAKLAND #1 2/017 RPR FOND |  | MORAGA-OAKLAND #1 | 002/017 | ICQ | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.200509 | 37.8306 | ETL.2720 | 40805690 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog 402
119180242 | T2 DI KILARC-DESCHUTES 013/287 RPL STRW | 31507647 | KILARC-DESCHUTES | 013/287 | 70Y | E | 2020_(2) High fire spread TD |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.067342 | 40.5646 | ETL.7300 | 41118604 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain
119180349 | T3 PARKWAY-MORAGA 20/112 RPR INSS | 44609779 | PARKWAY-MORAGA | 020/112 | ICS | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.2013071 | 37.8781 | ETL.5930 | 40841800 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Bay
119180383 | T2 DI KILARC-DESCHUTES 015/328 RPLC STRW | 31507647 | KILARC-DESCHUTES | 015/328 | 70Y | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.106836 | 40.5635 | ETL.7300 | 40827922 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain
119180387 | T2 DI KILARC-DESCHUTES 15/328 CANCEL | 44406469 | KILARC-DESCHUTES | 015/328 | ICW | E | 2020_(4b) On structure in bucket 4 |  |  | CANCEL/CNCL | TR2 |  | North Valley | WSIP | [6 empty] | '-122.106836 | 40.5635 | ETL.7300 | 40827922 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119180427 | T2 DI KILARC-DESCHUTES 16/338 RPL STRW | 31507647 | KILARC-DESCHUTES | 016/338 | 70Y | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.116166 | 40.5635 | ETL.7300 | 40817230 | Structure-Wood | Rotten | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain
119180506 | T2 HUMBOLDT-TRINITY 93/009L RPR STRW | 44356920 | HUMBOLDT-TRINITY | 093/009 | ICS | E | 2020_(2) High fire spread TD |  |  | Likely MAT error - delink to correct | TR2 |  | North Coast | WSIP | [6 empty] | '-123.74829 | 40.7493 | ETL.1820 | 44926653 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Eureka
119180552 | T3NT DI MAPLE CREEK-HPA 10/11 RMV BUTTS | 44301081 | MAPLE CREEK-HOOPA | 010/011 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-123.771278 | 40.8921 | ETL.7490 | 40602127 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
119180587 | T2 DRUM-SUMMIT #1 7/089L INST DAMPERS | 44391347 | DRUM-SUMMIT #1 | 007/089 | ICW | E | 2020_(1b) Lines with special commitments |  |  |  | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.660649 | 39.3115 | ETL.1440 | 44767650 | Damper-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119180644 | T3 EI COLGATE-ALLEGHANY 19/513 REPL SPLW | 44365653 | COLGATE-ALLEGHANY | 019/513 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.923791 | 39.4532 | ETL.6470 | 40611344 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119180647 | T3 EI COLGATE-ALLEGHANY 017/481 RPR ADSS | 44371190 | COLGATE-ALLEGHANY | 017/481 | ICW | F | 2020_(2) High fire spread TD |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.945089 | 39.4509 | ETL.6470 | 40767336 | Shield Wire / OPGW-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119180726 | T3 FULTON-CALISTOGA :008/001 INST DAMPER | 44597303 | FULTON-CALISTOGA | :008/001 | ICW | E | 2020_(4b) On structure in bucket 4 |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.599351 | 38.7014 | ETL.6880 | 40912491 | Damper-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
119180832 | T2 DI KILARC-DESCHUTES 15/326 RPR STRW | 44406469 | KILARC-DESCHUTES | 015/326 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.104936 | 40.5636 | ETL.7300 | 40771255 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119180899 | T2 DI CARIBOU #2 9/6 RMV BUTT |  | CARIBOU #2 | 009/006 | ICW | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.203507 | 40.0136 | ETL.6280 | 40826361 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119180900 | T2NT DI KILARC-DSCHUTS 13/282 RMV DEBRIS | 44406469 | KILARC-DESCHUTES | 013/282 | ICW | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.062375 | 40.5644 | ETL.7300 | 40876526 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119180908 | T2 DI KILARC-DESCHUTES 15/327 RMV BUTT | 44406469 | KILARC-DESCHUTES | 015/327 | ICW | E | 2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.10587 | 40.5635 | ETL.7300 | 40770411 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119180951 | T2 DI KILARC-DESCHUTES 15/327 RPR STRW | 44406469 | KILARC-DESCHUTES | 015/327 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.10587 | 40.5635 | ETL.7300 | 40770411 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119180968 | T2 KILARC-DESCHUTES 13/284 RMV BUTT | 44406470 | KILARC-DESCHUTES | 013/284 | ICW | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.064963 | 40.5645 | ETL.7300 | 40602027 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119180976 | T2NT DI CARIBOU #2 14/26 REFRAME | 31507060 | CARIBOU #2 | 014/026 | 93E | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.11309 | 40.0244 | ETL.6280 | 40816778 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain
119180984 | T3 DI COLGATE-CHALLENGE 4/82 RPL STRW | 31515208 | COLGATE-CHALLENGE | 004/082 | 70Y | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.16265 | 39.3815 | ETL.6480 | 40693047 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento
119180985 | T3 DI W. PNT-VLY SPRNGS 3/48 RPL POLE | 31506674 | WEST POINT-VALLEY SPRINGS | 003/048 | 70Y | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-120.608384 | 38.4078 | ETL.8350 | 40603877 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor
119181022 | T2 DI CARIBOU #2 8/19 RMV PL BUTT |  | CARIBOU #2 | 008/019 | ICW | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.21292 | 40.0165 | ETL.6280 | 40861853 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119181033 | T2 DI CARIBOU #2 9/14 RMV BUTT |  | CARIBOU #2 | 009/014 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.198082 | 40.0137 | ETL.6280 | 40769477 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119181045 | T2 DI TIGER CREEK-ELECTRA 9/70 RMV STEP |  | TIGER CREEK-ELECTRA | 009/070 | ICQ | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-120.634276 | 38.3898 | ETL.5780 | 40591468 | Hardware-Tower | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - 15
119181080 | T2 DI CARIBOU #2 9/19 RMV PL BUTT |  | CARIBOU #2 | 009/019 | ICW | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.194881 | 40.0133 | ETL.6280 | 44217537 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119181081 | T2 DI CARIBOU #2 9/19 RPR GYWW |  | CARIBOU #2 | 009/019 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.194881 | 40.0133 | ETL.6280 | 44217537 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119181088 | T2 DI MI-WUK-CURTIS 25/1 RPLC STRW | 31508526 | ETL.1073.POLE.WDPS | 025/001 | 70Y | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-120.294459 | 37.9858 | ETL.1073 | 44774791 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 41
119181093 | T2 DI CARIBOU #2 :4/12 RPL STRW | 31508138 | CARIBOU #2 | :004/012 | 70Y | E | 2020_(2) High fire spread TD |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-120.999276 | 39.9826 | ETL.6280 | 40675658 | Structure-Wood | No Good/Out of Stdrd | Replace | ESTS erdy | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain
119181484 | T2 DI CARIBOU #2 9/7 RMV PL BUTT |  | CARIBOU #2 | 009/007 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.202621 | 40.0137 | ETL.6280 | 40824568 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119181489 | T2 DI CARIBOU #2 9/7 REFRAME | 31507060 | CARIBOU #2 | 009/007 | 93E | E | 2020_(2) High fire spread TD |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.202621 | 40.0137 | ETL.6280 | 40824568 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain
119181504 | T3 DI COLGATE-CHALLENGE 4/97 RMV BUTT | 44371192 | COLGATE-CHALLENGE | 004/097 | ICW | E | 2020_(3) On high spread structure |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.159607 | 39.3936 | ETL.6480 | 40866891 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119181506 | T3NT DI BRUNSWICK #1 005/041 RPR FOND | 44370736 | BRUNSWICK #1 TAP | 005/041 | ICQ | F | 2020_(2) High fire spread TD |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.034153 | 39.2124 | ETL.1422 | 40586112 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Sacramento
119181545 | T2 DI CARIBOU #2 9/11 RMV PL BUTT |  | CARIBOU #2 | 009/011 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.200047 | 40.014 | ETL.6280 | 40591750 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119181548 | T2 DI CARIBOU #2 9/11 REFRAME | 31507060 | CARIBOU #2 | 009/011 | 93E | E | 2020_(2) High fire spread TD |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.200047 | 40.014 | ETL.6280 | 40591750 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain
119181617 | T2 DI KILARC-DESCHUTES 16/343 RMV BUTT | 44406469 | KILARC-DESCHUTES | 016/343 | ICW | E | 2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.120968 | 40.5635 | ETL.7300 | 40602009 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119181671 | T2 DI KILARC-DESCHUTES 16/343 RPR STRW | 44406469 | KILARC-DESCHUTES | 016/343 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.120968 | 40.5635 | ETL.7300 | 40602009 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119181678 | T2 DI KILARC-DESCHUTES 15/330 RMV BUTT | 44406469 | KILARC-DESCHUTES | 015/330 | ICW | E | 2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.108495 | 40.5635 | ETL.7300 | 40877874 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119181757 | T3 DI COLGATE-ALLEGHANY 15/407 RPR GYWW | 44371191 | COLGATE-ALLEGHANY | 015/407 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.9934 | 39.4455 | ETL.6470 | 40874813 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119181826 | T2 EI FRT RS-GUALALA 30/9 RPLC POLE | 31506296 | GUALALA-MONTE RIO | 030/009 | 70Y | E | 2020_(2) High fire spread TD |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.247692 | 38.5502 | ETL.6980 | 40871392 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville
119181860 | T2 DI FORT ROSS-GUALALA 32/5 RPR GYWW |  | GUALALA-MONTE RIO | 032/005 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.271491 | 38.5616 | ETL.6980 | 40750297 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
119181900 | T3NT DI GEYSERS #17-FULTON 0/3 RPR FOND | 44637021 | GEYSERS #17-FULTON | 000/003 | ICQ | F | 2020_(2) High fire spread TD |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.785374 | 38.824 | ETL.4770 | 40654446 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville
119182232 | T3 DI MORAGA-OAKLND #2 1/13 WAS INSS | 44598173 | MORAGA-OAKLAND #2 | 001/013 | ICD | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.19172 | 37.8357 | ETL.2730 | 40689689 | Insulator | Contaminated | Ground Wash | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 622 | Bay
119182371 | T2 DI FORT ROSS-GUALALA 035/1 RPR GYWW |  | GUALALA-MONTE RIO | 035/001 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.300814 | 38.5879 | ETL.6980 | 40584647 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
119182464 | T2 DI TRINITY-MAPLE CRK 20/3 RPR STRW | 44273074 | TRINITY-MAPLE CREEK | 020/003 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.264976 | 40.724 | ETL.8170 | 44564200 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
119182832 | T3 DI TGR CRK-ELCTR-TWR 7/61 RMV HRDS |  | TIGER CREEK-ELECTRA | 007/061 | ICS | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-120.614207 | 38.4042 | ETL.5780 | 40593868 | Hardware-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - 12
119182864 | T2 DI CRTN-MNDCN #1-TWR 16/77 RPR FOND | 44238817 | CORTINA-MENDOCINO #1 | 016/077 | ICQ | F | 2020_(2) High fire spread TD |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.483577 | 39.0169 | ETL.1330 | 40809327 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville
119182902 | T2 DI FORT ROSS-GUALALA 035/9 RPL POLE | 31508619 | GUALALA-MONTE RIO | 035/009 | 70Y | E | 2020_(2) High fire spread TD |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.302503 | 38.597 | ETL.6980 | 40876072 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville
119183107 | T3NT DI PTSBRG-SN RMN-TWR 12/47 RPR FOND |  | PITTSBURG-SAN RAMON | 012/047 | ICQ | F | 2020_(4) TD tag on high spread line |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-121.882078 | 37.8769 | ETL.5490 | 40805035 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog 402
119183191 | MSTNG SW STA-GRGG X52/219 RMV DEBRIS | 44389951 | GATES-GREGG | X052/219 | ICS | E | 2020_(1b) Lines with special commitments |  |  |  |  | WECC | South | WSIP | [6 empty] | '-119.897184 | 36.768 | ETL.4700 | 40866280 | Shield Wire / OPGW-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  | Y - 5
119183246 | EI T3NT COLGATE-ALLEGHANY 018/489 INST M | 44371190 | COLGATE-ALLEGHANY | 018/489 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.940167 | 39.4515 | ETL.6470 | 40664633 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119183553 | T3NT DI MRG-SN LNDR #3-TWR 2/16 RPR FOND | 44303862 | MORAGA-SAN LEANDRO #3 | 002/016 | ICQ | F | 2020_(2) High fire spread TD |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-122.146351 | 37.822 | ETL.2790 | 40822221 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  | EBMUD
119183632 | T2 DI CARIBOU #2 17/26 RPR GYWW |  | CARIBOU #2 | 017/026 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.06235 | 40.0214 | ETL.6280 | 40826407 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119183687 | T3 DI MORAGA-OAKLAND #2 2/17A RPLC INSS |  | MORAGA-OAKLAND #2 | 002/017A | 93K | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.201135 | 37.8304 | ETL.2730 | 40577583 | Insulator-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - Prog 402
119184250 | T3 DI DONNELLS-MI-WUK 0/2 RPR GYWW | 44623242 | DONNELLS-CURTIS | 000/002 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-120.034319 | 38.2449 | ETL.1400 | 44379630 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog 401
119184252 | T3 DI DONNELLS-MI-WUK 0/2 RPR GYWW | 44623243 | DONNELLS-CURTIS | 000/002 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-120.034319 | 38.2449 | ETL.1400 | 44379631 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - Prog 401
119184254 | T2 DI KILARC-DESCHUTES 13/276 RPR STRW | 44406469 | KILARC-DESCHUTES | 013/276 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.055104 | 40.5641 | ETL.7300 | 40668432 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119184469 | T3 DI MORAGA-OAKLAND J 1/13 HANGER | 44611129 | MORAGA-OAKLAND "J" | 001/013 | ICQ | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.151492 | 37.8261 | ETL.2760 | 40676704 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog 402
119184574 | T3 DI MORAGA-OAKLAND ""J"" 1/13 RPL INSS | 31511127 | MORAGA-OAKLAND "J" | 001/013 | 93K | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.151055 | 37.8265 | ETL.2760 | 40676704 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - Prog 402
119184796 | T2NT DI KILARC-DSCHUTS 11/249 RMV DEBRIS | 44406469 | KILARC-DESCHUTES | 011/249 | ICW | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.031697 | 40.5686 | ETL.7300 | 40600393 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119184995 | T2 DI KILARC-DESCHUTS 17/366A RMV BUTT | 44406469 | KILARC-DESCHUTES | 017/366A | ICW | E | 2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.144097 | 40.5637 | ETL.7300 | 44416928 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119185025 | T2 DI KILARC-DESCHUTES 17/352 RPR SPLW | 43930440 | KILARC-DESCHUTES | 017/352 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.129414 | 40.5636 | ETL.7300 | 40590493 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119185070 | T2 DI KILARC-DESCHUTES 17/352 RMV PL BUT | 43930440 | KILARC-DESCHUTES | 017/352 | ICW | E | 2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.129414 | 40.5636 | ETL.7300 | 40590493 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119185096 | T3 DI SOBRANTE""R"" #1+ 0/7 RMV STEP | 44624391 | SOBRANTE-R #1 | 000/007 | ICQ | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.225265 | 37.904 | ETL.3770 | 40804917 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  | EBMUD
119185113 | T3NT DI EGL RCK-FLTN-SLVRD 6/32 RPR FOND | 44326457 | EAGLE ROCK-FULTON-SILVERADO | 006/032 | ICQ | F | 2020_(2) High fire spread TD |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.781832 | 38.7513 | ETL.4392 | 40683484 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville
119185429 | T3 FRNCH MDWS-MDDLE FRK 9/182 INST DAMP | 44371596 | FRENCH MEADOWS-MIDDLE FORK | 009/182 | ICW | E | 2020_(3) On high spread structure |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.561664 | 39.0162 | ETL.6870 | 40751850 | Damper-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119185791 | DI GATES-PANOCHE #1 3/18 MASTIC | 44389944 | GATES-PANOCHE #1 | 003/018 | ICQ | F | 2020_(1b) Lines with special commitments |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.158512 | 36.1828 | ETL.4720 | 40863628 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 10
119185837 | T3 DI MNTA VSTA-CYT SS 17/84 RPL INSS | 31507834 | MONTA VISTA-COYOTE SW STA | 017/084 | 93K | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | South | WSIP | [6 empty] | '-122.017352 | 37.2068 | ETL.5090 | 40782451 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Moss Landing |  | Y - Prog 402
119185860 | T2 DI MI-WUK-CURTIS 26/000 RPR STRW | 44623244 | ETL.1073.POLE.WDPS | 026/000 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-120.307425 | 37.9761 | ETL.1073 | 44770809 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 41
119185862 | DI FULTON-HOPLAND 10/1 RPR GYWW | 44579280 | FULTON-HOPLAND | 010/001 | ICW | E | 2020_(4) TD tag on high spread line | [5 empty] | North Coast | WSIP | [6 empty] | '-122.843602 | 38.6156 | ETL.6890 | 40601387 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
119185866 | DI FULTON-HOPLAND 10/1 GROUNDWASH | 44592820 | FULTON-HOPLAND | 010/001 | ICD | E | 2020_(4) TD tag on high spread line | [5 empty] | North Coast | WSIP | [6 empty] | '-122.843602 | 38.6156 | ETL.6890 | 40628076 | Insulator | Contaminated | Ground Wash | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 622 | Lakeville
119185895 | T2 DI MORAGA-CSTRO VALLEY 12/55 RPL INSS | 31526489 | MORAGA-CASTRO VALLEY | 012/055 | 93K | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-122.049622 | 37.7084 | ETL.5250 | 40788236 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Bay |  | Y - 7
119185898 | T2 DI CRTA MDCN #1 54/270 RMV HRDT |  | CORTINA-MENDOCINO #1 | 054/270 | ICQ | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.094164 | 39.224 | ETL.1330 | 40587921 | Hardware-Tower | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville
119185913 | T3 DI GEYSERS #12-FULTON 20/84 RPR FOUND | 44631264 | GEYSERS #12-FULTON | 020/084 | ICS | F | 2020_(2) High fire spread TD |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.742383 | 38.5727 | ETL.4750 | 40761390 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville
119185936 | DI GATES PANOCHE #1 5/28 RMV DEBRIS | 44389953 | GATES-PANOCHE #1 | 005/028 | ICS | E | 2020_(1b) Lines with special commitments |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.179501 | 36.2089 | ETL.4720 | 40863630 | Structure-Steel | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  | Y - 10
119185981 | T3 DI ORAGA-SAN LEANDRO #1 0/1 WASH INSS | 44598174 | MORAGA-SAN LEANDRO #1 | 000/001 | ICD | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.160858 | 37.8469 | ETL.2770 | 40604490 | Insulator | Contaminated | Ground Wash | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 622 | Bay |  | Y - 15
119186030 | T3 DI TIGER CREEK-ELECTRA 7/60 RPL INSS | 31511365 | TIGER CREEK-ELECTRA | 007/060 | 93K | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-120.613317 | 38.4049 | ETL.5780 | 40631086 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Victor |  | Y - 12
119186031 | T3 DI TIGER CREEK-ELECTRA 7/60 RPL HRDS |  | TIGER CREEK-ELECTRA | 007/060 | ICS | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-120.612794 | 38.4052 | ETL.5780 | 40591465 | Hardware-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - 12
119186816 | T3 DI SOBRANTE-""""R"""" #1 1/8 RPR STRT | 44624391 | SOBRANTE-R #1 | 001/008 | ICQ | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.229863 | 37.9052 | ETL.3770 | 40857873 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  | EBMUD
119186878 | T3 DI KILARC-CEDAR CREEK 7/165 BOND GUY | 43930440 | KILARC-DESCHUTES | 000/001 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.872795 | 40.6778 | ETL.7300 | 40701858 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119186901 | DI SLO-SM 17/76B RPLC INSS | 31510359 | SAN LUIS OBISPO-SANTA MARIA | 017/076B | 93K | E | 2020_(4) TD tag on high spread line | [5 empty] | South | WSIP | [6 empty] | '-120.480763 | 35.0667 | ETL.3540 | 40741416 | Insulator-Steel | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - Prog 402
119187190 | T3NT DI GYRS #12-FLTN-TWR 23/96 RPR FOND |  | GEYSERS #12-FULTON | 023/096 | ICQ | F | 2020_(4) TD tag on high spread line |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.7518 | 38.5299 | ETL.4750 | 40814636 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville
119187191 | T3 DI SOBRANTE""G""#1""-TWR 2/16 RPR FOND | 44624390 | SOBRANTE-"G" #1 | 002/016 | ICQ | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.252525 | 37.9116 | ETL.3720 | 40804931 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 9
119187205 | T2 PIT #5-ROUND MTN #1 11/112 RPL INSW | 31526971 | PIT #5-ROUND MTN #1 | 011/112 | 93I | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.93282 | 40.8344 | ETL.5420 | 40792848 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Table Mountain
119187515 | T2 DI CRESTA-RIO OSO 29/235 RPR INSS |  | CRESTA-RIO OSO | 029/235 | ICS | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.535578 | 39.5565 | ETL.4590 | 41140730 | Insulator-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain
119187519 | T3NT DI SNTH LN-HLF ;2/21 RMV BUTT | 44621950 | SNEATH LANE-HALF MOON BAY | ;002/021 | ICW | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-122.469905 | 37.6016 | ETL.7212 | 40599236 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Bay
119187540 | T2 DI CARIBOU #2 016/027 BACKFILL HOLE |  | CARIBOU #2 | 016/027 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.081523 | 40.0189 | ETL.6280 | 40815753 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119187676 | T3 DI FULTON-IGNACIO#1 3/18 RPR FOND | 44310479 | FULTON-IGNACIO #1 | 003/018 | ICQ | F | 2020_(4) TD tag on high spread line |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.705789 | 38.4971 | ETL.4680 | 40863592 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville
119187803 | T3 DI MTCLF-MOSS LNDG 41/181 RMV STEP | 44571497 | METCALF-MOSS LANDING #1 | 041/181 | ICS | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | South | WSIP | [6 empty] | '-121.667191 | 37.0394 | ETL.5100 | 40594684 | Hardware-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 628 | Moss Landing
119187805 | T2 DI CARIBOU#2 ;1/16 RMV BUTT |  | CARIBOU #2 | ;001/016 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-120.963747 | 40.0055 | ETL.6280 | 40812209 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119188144 | T3 DI TIGER CREEK-ELECTRA 2/17 RPR STRT |  | TIGER CREEK-ELECTRA | 002/017 | ICQ | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-120.5258 | 38.4402 | ETL.5780 | 40821587 | Structure-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - 12
119188147 | T3 DI GEYSERS #9-LAKEVILL :4/23 RPR INSS |  | GEYSERS #9-LAKEVILLE | :004/023 | ICS | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.76287 | 38.7431 | ETL.4780 | 40676810 | Insulator-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville
119188149 | T2NT DI CARIBOU#2 ;1/21 RMV BUTT |  | CARIBOU #2 | ;001/021 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-120.961303 | 40.0037 | ETL.6280 | 40600644 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119188432 | DI GTS-MSTNG SW ST #1 2/14 BENT STL | 44389942 | SPARE T-LINE RECORD | 002/014 | ICQ | E | 2020_(1b) Lines with special commitments | [5 empty] | South | WSIP | [6 empty] | '-120.081367 | 36.158 | ETL.2604 | 40746626 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - Prog 402
119188436 | T3NT DI TGR CRK-VLY SPRNGS 5/42 RPR FOND |  | TIGER CREEK-VALLEY SPRINGS | 005/042 | ICQ | F | 2020_(2) High fire spread TD |  |  |  | TR3 |  | Central | WSIP | [6 empty] | '-120.581218 | 38.4244 | ETL.5790 | 40645135 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Victor |  | Y - Prog 402
119188449 | T2 EI BRIDGEVILLE-GARBERVILLE 22/4 REFRA | 31511889 | BRIDGEVILLE-GARBERVILLE | 022/004 | 93E | E | 2020_(2) High fire spread TD |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.751177 | 40.2152 | ETL.6220 | 40752629 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Eureka
119188460 | EI T2NT BRDGVLLE-GRBRVLLE 22/4 RMV PL BU | 44299809 | BRIDGEVILLE-GARBERVILLE | 022/004 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.751177 | 40.2152 | ETL.6220 | 40752629 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
119188471 | T2 EI BRIDGEVILLE-GARBERVILLE 22/4 RPL A | 31508615 | BRIDGEVILLE-GARBERVILLE | 022/004 | 93E | E | 2020_(2) High fire spread TD |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.751177 | 40.2152 | ETL.6220 | 40752629 | Anchor-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Eureka
119188478 | T2 DRUM-RIO OSO #2 22/170 RPR INSLS | 44391340 | DRUM-RIO OSO #2 | 022/170 | ICS | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.120263 | 39.0963 | ETL.1430 | 44934901 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Sacramento
119188623 | T2 MONTE RIO-FORT ROSS 26/5 RPL POLE | 31509661 | ETL.6979.POLE.WOOD | 026/005 | 70Y | E | 2020_(2) High fire spread TD |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.195356 | 38.5074 | ETL.6979 | 40750295 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville
119188626 | T2 EI BRIDGEVILLE-GARBERVILLE - CANCEL |  | BRIDGEVILLE-GARBERVILLE | 022/003 | 93E | E | 2020_(2) High fire spread TD |  |  | CANCEL/CNCL | TR2 |  | North Coast | WSIP | [6 empty] | '-123.751942 | 40.2159 | ETL.6220 | 40650770 | Anchor-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 637 | Eureka
119188665 | T2 DI CORTIN-MENDOCINO#1 26/123 MASTIC |  | CORTINA-MENDOCINO #1 | 026/123 | ICQ | F | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.657504 | 39.0291 | ETL.1330 | 40648761 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville
119188712 | MONTE RIO-FORT ROSS 22/008 INS DAMPER |  | ETL.6979.POLE.WOOD | 022/008 | ICW | E | 2020_(4) TD tag on high spread line | [5 empty] | North Coast | WSIP | [6 empty] | '-123.141168 | 38.4753 | ETL.6979 | 40860942 | Damper-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
119188913 | T2 STANISLAUS-MANTECA #2 9/59 RPR INSLS | 44566009 | STANISLAUS-MANTECA #2 | 009/059 | ICS | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-120.5221576 | 38.0649 | ETL.3820 | 40883236 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - 26
119188949 | T2 DI KILARC-DESCHUTES 14/292 RMV BUTT | 44406469 | KILARC-DESCHUTES | 014/292 | ICW | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.072216 | 40.5647 | ETL.7300 | 40600402 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119189046 | T2 MELONES-CURTIS 9/3 RMV DEBRIS | 44623245 | MELONES-CURTIS | 009/003 | ICW | E | 2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | Central | WSIP | [6 empty] | '-120.403585 | 37.9428 | ETL.2390 | 44391057 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Victor |  | Y - 18
119189076 | T2 DRUM-SUMMIT #2 7/086 RPR GYWW | 44391349 | DRUM-SUMMIT #2 | 007/086B | ICW | E | 2020_(1b) Lines with special commitments |  |  |  | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.662314 | 39.3112 | ETL.1450 | 44159090 | Insulator Bond Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119189097 | T3 DI CORTINA-MENDOCINO#1 18/89 RPR OPGW | 44610540 | CORTINA-MENDOCINO #1 | 018/089 | ICS | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.533151 | 39.0039 | ETL.1330 | 40860979 | Shield Wire / OPGW-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville
119189101 | T3NT DI COLGATE-CHALLENGE 1/29 RMV BUTT | 44371193 | COLGATE-CHALLENGE | 001/029 | ICW | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.18562 | 39.3473 | ETL.6480 | 40824182 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119189102 | T3 DI COLGATE-CHALLENGE 1/29 RPR SPLW | 44365653 | COLGATE-CHALLENGE | 001/029 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.18562 | 39.3473 | ETL.6480 | 40824182 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119189164 | T2 EI BRIDGEVILLE-GARBERVLLE 21/12 RPL S | 31508614 | BRIDGEVILLE-GARBERVILLE | 021/012 | 70Y | E | 2020_(2) High fire spread TD |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.756258 | 40.2198 | ETL.6220 | 40661882 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Eureka
119189213 | T2 TRNTY-MPL CRK 18/015 RPR CONDUCTOR | 44364310 | TRINITY-MAPLE CREEK | 018/015 | ICS | E | 2020_(2) High fire spread TD |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.242441 | 40.7371 | ETL.8170 | 40752260 | Conductor-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Eureka
119189513 | T3 DI SOBRANTE ""R"" 1/10 RMV STEP | 44624391 | SOBRANTE-R #1 | 001/010 | ICQ | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.236906 | 37.9071 | ETL.3770 | 40581867 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  | EBMUD
119189637 | T2 LAKEVILLE #2 12/257 INS DAMPER |  | LAKEVILLE #2 | 012/257 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.697764 | 38.2902 | ETL.7340 | 40825816 | Damper-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
119190165 | T3NT DI CLGTE-ALLGHNY 9/262 RMV PL BUTT | 44371191 | COLGATE-ALLEGHANY | 009/262 | ICW | E | 2020_(3) On high spread structure |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.037237 | 39.3772 | ETL.6470 | 40767334 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119190286 | T2 TRINITY-MPL CRK 42/002A INST DAMPER | 44364310 | TRINITY-MAPLE CREEK | 042/002A | ICS | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.66822 | 40.7289 | ETL.8170 | 44947102 | Damper-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Eureka
119190308 | T2 VACA-SUISUN-JAMESON 12/087 | 31508566 | VACA-SUISUN-JAMESON | 012/087 | 93K | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.066737 | 38.2839 | ETL.4080 | 40838460 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Sacramento
119190325 | T2 VACA-SUISUN 007/059 RPL INSS CMPLT | 31507028 | VACA-SUISUN | 007/059 | 93K | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.025925 | 38.3469 | ETL.4070 | 40887573 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Sacramento
119190327 | T2 VACA-SUISUN-JAMESON 7/59 RPL INSULS | 31508566 | VACA-SUISUN-JAMESON | 007/059 | 93K | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.025925 | 38.3469 | ETL.4080 | 40887575 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Sacramento
119190471 | T3 EI SBRNTE-GRZZLY-CLRMNT #1 5/46 WSH I |  | SOBRNTE-GRIZZLY-CLARMNT #1+ | 005/046 | ICD | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.2093721 | 37.8512 | ETL.3740 | 40638423 | Insulator | Contaminated | Ground Wash |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 622 | Bay |  | Y - 12
119191490 | T2 COLGATE-GRASS VALLEY 3/75 REFRAME | 31512499 | COLGATE-GRASS VALLEY | 003/075 | 93E | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.133715 | 39.3211 | ETL.6490 | 40768368 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Sacramento
119193758 | T3 DI COLGATE-ALLGHNY 20/553 RMV BUTT | 44365654 | COLGATE-ALLEGHANY | 020/553 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.899907 | 39.4628 | ETL.6470 | 40658312 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119193771 | T3 DI SOBRANTE-""G""#1"" 1/11 RPR INSS |  | SOBRANTE-"G" #1 | 001/011 | ICS | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.240035 | 37.9081 | ETL.3720 | 44762556 | Insulator-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Bay |  | Y - 9
119193856 | T3 DI SOBRANTE-""G""#1""-TWR 0/6 RPR HRDT | 44624390 | SOBRANTE-"G" #1 | 000/006 | ICQ | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.225199 | 37.9042 | ETL.3720 | 40804930 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - 9
119193947 | DI GATES-PANOCHE #1 4/21 RPR FOND | 44389944 | GATES-PANOCHE #1 | 004/021 | ICQ | F | 2020_(1b) Lines with special commitments |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.165097 | 36.1905 | ETL.4720 | 40587468 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 10
119193948 | DI GATES-PANOCHE #1 4/21 RPR STRT | 44389944 | GATES-PANOCHE #1 | 004/021 | ICQ | E | 2020_(1b) Lines with special commitments |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.165097 | 36.1905 | ETL.4720 | 40587468 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 10
119194018 | T3 DI TGR CRK-VLY SPGS TWR 4/35 RPC HRDT |  | TIGER CREEK-VALLEY SPRINGS | 004/035 | ICS | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-120.568314 | 38.4276 | ETL.5790 | 40811845 | Hardware-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Victor |  | Y - Prog 402
119194025 | T3 DI COLGATE-ALLGHNY 20/553 RPLC SPLW | 44365653 | COLGATE-ALLEGHANY | 020/553 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.899907 | 39.4628 | ETL.6470 | 40658312 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119194330 | DI GATES-PANOCHE #1 10/49 RPR INSS | 44389952 | GATES-PANOCHE #1 | 010/049 | ICS | E | 2020_(1b) Lines with special commitments |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.221806 | 36.2635 | ETL.4720 | 40885696 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  | Y - 10
119194332 | DI GATES-PANOCHE #2 10/49 RPR INSS | 44389954 | GATES-PANOCHE #2 | 010/049 | ICS | E | 2020_(1b) Lines with special commitments |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.221806 | 36.2635 | ETL.4730 | 40885697 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  | Y - Prog 402
119194335 | DI GATES-PANOCHE #1 10/49 RPR FOND | 44571495 | GATES-PANOCHE #1 | 010/049 | ICQ | E | 2020_(1b) Lines with special commitments |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.222238 | 36.264 | ETL.4720 | 40863288 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 10
119194338 | DI GATES-PANOCHE #1 10/49 RPR STRT | 44389944 | GATES-PANOCHE #1 | 010/049 | ICQ | E | 2020_(1b) Lines with special commitments |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.222238 | 36.264 | ETL.4720 | 40863288 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 10
119194422 | T2 DI CARIBOU #2 ;0/30 RMV BUTT |  | CARIBOU #2 | ;000/030 | ICW | E | 2020_(3) On high spread structure |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-120.965898 | 40.0154 | ETL.6280 | 40614890 | Structure-Wood | Debris/Nest/etc. | Remove |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119194432 | T3 DI COLGATE-ALLGHNY 16/453 REPL POLE | 31506658 | COLGATE-ALLEGHANY | 016/453 | 70Y | E | 2020_(1a) PSPS |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.962817 | 39.449 | ETL.6470 | 40767328 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento
119194435 | T3 DI COLGATE-ALLEGHANY 16/432 RPLC SPLW | 44365653 | COLGATE-ALLEGHANY | 016/432 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.976701 | 39.4475 | ETL.6470 | 40665267 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119194554 | T3NT DI COLGATE-ALLGHNY 17/482 RMV BUTTS | 44374175 | COLGATE-ALLEGHANY | 017/482 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.944581 | 39.451 | ETL.6470 | 44918014 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119194555 | T3 DI COLGATE-ALLGHNY 17/482 RPLC INSW | 44365653 | COLGATE-ALLEGHANY | 017/482 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.944581 | 39.451 | ETL.6470 | 44918022 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119194575 | T3NT DI COLGATE-ALLGHANY 23/636 RMV BUTT | 44371190 | COLGATE-ALLEGHANY | 023/636 | ICW | F | 2020_(1a) PSPS |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.851108 | 39.4769 | ETL.6470 | 40822723 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119194764 | T3 DI COLGATE-ALLGHANY 23/651 RPR INSW | 44379091 | COLGATE-ALLEGHANY | 023/651 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.848494 | 39.4716 | ETL.6470 | 40696054 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119194767 | T3 DI COLGATE-ALLGHANY 19/525 RPR HRDW | 44379095 | COLGATE-ALLEGHANY | 019/525 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.9159 | 39.4541 | ETL.6470 | 40693271 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119194768 | T3NT DI COLGATE-ALLGHANY 19/525 RMV BUTT | 44378839 | COLGATE-ALLEGHANY | 019/525 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.9159 | 39.4541 | ETL.6470 | 40693271 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119194809 | T3 DI COLGATE-ALLGHNY 16/432 RMV DEBRIS | 44365654 | COLGATE-ALLEGHANY | 016/432 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.976701 | 39.4475 | ETL.6470 | 40665267 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119194834 | T3NT DI COLGTE-ALLGHNY 23/634 RMV BUTT | 44371190 | COLGATE-ALLEGHANY | 023/634 | ICW | F | 2020_(2) High fire spread TD |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.8515 | 39.4776 | ETL.6470 | 40760458 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119194839 | T3 DI COLGATE-ALLGHNY 18/491 RPR STRW | 44379095 | COLGATE-ALLEGHANY | 018/491 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.938863 | 39.4516 | ETL.6470 | 40766624 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119194909 | T3 DI COLGATE-ALLEGHANY 23/639 RPR POLE | 44365653 | COLGATE-ALLEGHANY | 023/639 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.850608 | 39.4759 | ETL.6470 | 40611347 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119195015 | T3 DI COLGATE-ALLGHANY 17/474 REFRAME | 31507062 | COLGATE-ALLEGHANY | 017/474 | 93E | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.94944 | 39.4504 | ETL.6470 | 40843349 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Sacramento
119195020 | T3NT DI COLGATE-ALLGHNY 18/491 RMV BUTT | 44378839 | COLGATE-ALLEGHANY | 018/491 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.938863 | 39.4516 | ETL.6470 | 40766624 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119195023 | T3NT DI COLGATE-ALLGHNY 20/558 RMV BUTT | 44378839 | COLGATE-ALLEGHANY | 020/558 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.89639 | 39.464 | ETL.6470 | 40874718 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119195025 | T3 DI COLGATE-ALLGHNY 20/558 RPR STRW | 44379097 | COLGATE-ALLEGHANY | 020/558 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.89639 | 39.464 | ETL.6470 | 40874718 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119195027 | T3NT DI COLGATE-ALLGHNY 20/540 RMV BUTT | 44378839 | COLGATE-ALLEGHANY | 020/540 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.908346 | 39.4599 | ETL.6470 | 40611174 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119195028 | T3 DI COLGATE-ALLGHNY 20/540 RPR STRW | 44379095 | COLGATE-ALLEGHANY | 020/540 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.908346 | 39.4599 | ETL.6470 | 40611174 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119195171 | T3 DI COLGATE-ALLGHANY 18/505 RPL STRW | 31507362 | COLGATE-ALLEGHANY | 018/505 | 70Y | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.928714 | 39.4527 | ETL.6470 | 40868967 | Structure-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento
119195175 | T3NT DI COLGATE-ALLGHANY 18/505 RMV BUTT | 44378839 | COLGATE-ALLEGHANY | 018/505 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.928714 | 39.4527 | ETL.6470 | 40868967 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119195179 | T3 DI COLGATE-ALLGHANY 12/329 RPLC PLE | 31507362 | COLGATE-ALLEGHANY | 012/329 | 70Y | E | 2020_(1a) PSPS |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.017899 | 39.4125 | ETL.6470 | 40817339 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento
119195356 | T3 DI COLGATE-ALLGHANY 24/658 RPR SPLW | 44379097 | COLGATE-ALLEGHANY | 024/658 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.847187 | 39.4693 | ETL.6470 | 40824282 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119195364 | T3 DI COLGATE-ALLGHNY 17/478 RMV BUTTS | 44378720 | COLGATE-ALLEGHANY | 017/478 | ICW | E | 2020_(3) On high spread structure |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.947012 | 39.4507 | ETL.6470 | 40593293 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119195365 | T3 DI COLGATE-ALLGHNY 17/478 RPR SHLW | 44378479 | COLGATE-ALLEGHANY | 017/478 | ICW | F | 2020_(2) High fire spread TD |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.947012 | 39.4507 | ETL.6470 | 40593293 | Shield Wire / OPGW-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119195543 | T3 DI COLGATE-ALLGHNY 16/431 RPR STRW | 44379095 | COLGATE-ALLEGHANY | 016/431 | ICW | E | 2020_(1a) PSPS |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.97729 | 39.4474 | ETL.6470 | 40693247 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119195544 | T3 DI KILARC-CEDAR CRK 12/274 RPLC POLE | 31506712 | KILARC-CEDAR CREEK | 012/274 | 70Y | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.943525 | 40.7853 | ETL.7290 | 40816392 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain
119195549 | T3NT DI CLGTE-ALLGHNY 17/468 RMV PL BUTT | 44378839 | COLGATE-ALLEGHANY | 017/468 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.953394 | 39.45 | ETL.6470 | 40598665 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119195593 | T3 DI COLGATE-ALLGHNY 18/487 RPLC SPLW | 44365653 | COLGATE-ALLEGHANY | 018/487 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.941079 | 39.4513 | ETL.6470 | 40598646 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119195596 | T3 DI COLGATE-ALLGHNY 18/487 RPR BUTT | 44365654 | COLGATE-ALLEGHANY | 018/487 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.941079 | 39.4513 | ETL.6470 | 40598646 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119195734 | MONTE RIO-FORT ROSS 23/2 INST DAMPER |  | ETL.6979.INSL.NCER | 023/002 | ICW | E | 2020_(4) TD tag on high spread line | [5 empty] | North Coast | WSIP | [6 empty] | '-123.1487726 | 38.4765 | ETL.6979 | 40741433 | Damper-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
119195920 | T3 DI COLGATE-ALLGHANY 18/489 RPR STRW | 44379095 | COLGATE-ALLEGHANY | 018/489 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.940167 | 39.4515 | ETL.6470 | 40664633 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119195921 | T3NT DI CLGTE-ALLGHNY 18/489 RMV PL BUTT | 44378839 | COLGATE-ALLEGHANY | 018/489 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.940167 | 39.4515 | ETL.6470 | 40664633 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119195923 | T3NT DI COLGATE-ALLGHANY 17/481 RMV BUTT | 44378839 | COLGATE-ALLEGHANY | 017/481 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.945089 | 39.4509 | ETL.6470 | 40767336 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119195925 | T3NT DI COLGATE-ALLGHANY 17/481 INS MRKW | 44378839 | COLGATE-ALLEGHANY | 017/481 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.945089 | 39.4509 | ETL.6470 | 40767336 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119195926 | T3 DI COLGATE-ALLGHANY 17/481 RPR INSW | 44379091 | COLGATE-ALLEGHANY | 017/481 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.945125 | 39.4509 | ETL.6470 | 40798833 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119195927 | T3 DI COLGATE-ALLGHANY 16/430 RPR STRW | 44378720 | COLGATE-ALLEGHANY | 016/430 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.978493 | 39.4473 | ETL.6470 | 40590443 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119195928 | T3NT DI COLGATE-ALLGHANY 16/430 RMV BUTT | 44378479 | COLGATE-ALLEGHANY | 016/430 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.978493 | 39.4473 | ETL.6470 | 40590443 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119195929 | T3 DI COLGATE-ALLGHANY 19/538 RPR STRW | 44365653 | COLGATE-ALLEGHANY | 019/538 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.909522 | 39.459 | ETL.6470 | 40760451 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119195940 | T3 DI COLGATE-ALLEGHANY 17/468 RPLC HRDW | 44379095 | COLGATE-ALLEGHANY | 017/468 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.953394 | 39.45 | ETL.6470 | 40598665 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119195942 | T3 DI COLGATE-ALLEGHANY 17/485 RPR STRW | 44379097 | COLGATE-ALLEGHANY | 017/485 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.94261 | 39.4512 | ETL.6470 | 40874815 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119195943 | T3NT DI CLGTE-ALLGHNY 17/485 RMV PL BUTT | 44378839 | COLGATE-ALLEGHANY | 017/485 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.94261 | 39.4512 | ETL.6470 | 40874815 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119196152 | T3NT DI COLGT-ALLGHANY 19/538 RMV DEBRIS | 44365654 | COLGATE-ALLEGHANY | 019/538 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.909522 | 39.459 | ETL.6470 | 40760451 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119196153 | T3 DI COLGATE-ALLGHANY 19/538 RPR INSW | 44379091 | COLGATE-ALLEGHANY | 019/538 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.909504 | 39.4589 | ETL.6470 | 40789964 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119196157 | T3NT DI CLGTE-ALLGHANY 017/464 INS MRKW | 44378839 | COLGATE-ALLEGHANY | 017/464 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.956019 | 39.4498 | ETL.6470 | 40817357 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119196158 | T3 DI COLGATE-ALLGHANY 017/464 RPR STRW | 44379301 | COLGATE-ALLEGHANY | 017/464 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.956019 | 39.4498 | ETL.6470 | 40817357 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119196210 | T3 DI COLGATE-ALLEGHANY 16/436 RPR STRW | 44379095 | COLGATE-ALLEGHANY | 016/436 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.973553 | 39.4478 | ETL.6470 | 40817354 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119196212 | T3NT DI CLGTE-ALLGHNY 16/436 RMV PL BUTT | 44378839 | COLGATE-ALLEGHANY | 016/436 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.973553 | 39.4478 | ETL.6470 | 40817354 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119196213 | T3 DI COLGATE-ALLEGHANY 20/548 RPR STRW | 44379097 | COLGATE-ALLEGHANY | 020/548 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.90335 | 39.4622 | ETL.6470 | 40874720 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119196215 | T3NT DI CLGTE-ALLGHNY 20/548 RMV PL BUTT | 44378839 | COLGATE-ALLEGHANY | 020/548 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.90335 | 39.4622 | ETL.6470 | 40874720 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119196218 | T3NT DI CLGTE-ALLGHNY 20/547 RMV PL BUTT | 44378839 | COLGATE-ALLEGHANY | 020/547 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.904382 | 39.462 | ETL.6470 | 40817363 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119196219 | T3 DI COLGATE-ALLEGHANY 20/547 RPR STRW | 44379097 | COLGATE-ALLEGHANY | 020/547 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.904382 | 39.462 | ETL.6470 | 40817363 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119196242 | EI T3NT SAN LUIS OBPO-OCEANO 13/57 RPR R | 44378910 | SAN LUIS OBISPO-OCEANO | 013/057 | CHS | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR3 |  | South | WSIP | [6 empty] | '-120.504774 | 35.121 | ETL.3530 | 40809128 | Road | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLR | Roads | Expense | 932 | Pismo Beach
119196360 | T3 DI COLGATE-ALLGHANY 019/529 RPR STRW | 44379097 | COLGATE-ALLEGHANY | 019/529 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.914146 | 39.4554 | ETL.6470 | 40824272 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119196361 | T3NT DI CLGTE-ALLGHNY 19/529 RMV PL BUTT | 44378839 | COLGATE-ALLEGHANY | 019/529 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.914146 | 39.4554 | ETL.6470 | 40824272 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119196362 | T3NT DI CLGTE-ALLGHNY 20/549 RMV PL BUTT | 44378839 | COLGATE-ALLEGHANY | 020/549 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.902698 | 39.4623 | ETL.6470 | 40873773 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119196363 | T3 DI COLGATE-ALLGHANY 20/549 RPR STRW | 44379097 | COLGATE-ALLEGHANY | 020/549 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.902698 | 39.4623 | ETL.6470 | 40873773 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119196367 | T3 DI MNDCN-WLLTS-FRT BRGG 10/3 RPR STRW | 44610681 | MENDOCINO-WILLITS-FORT BRAGG | 010/003 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Coast | WSIP | [8 empty] | ETL.7550 | 44211132 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
119196561 | T3NT DI CLGTE-ALLGHNY 18/490 RMV PL BUTT | 44378839 | COLGATE-ALLEGHANY | 018/490 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.939619 | 39.4515 | ETL.6470 | 40760735 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119196563 | T3 DI COLGATE-ALLGHANY 18/490 RPR STRW | 44379095 | COLGATE-ALLEGHANY | 018/490 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.939619 | 39.4515 | ETL.6470 | 40760735 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119196664 | T3NT DI CLGTE-ALLGHNY 18/488 RMV PL BUTT | 44378839 | COLGATE-ALLEGHANY | 018/488 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.940687 | 39.4514 | ETL.6470 | 40693263 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119196665 | T3 DI COLGATE-ALLGHNY 18/488 RPLC HRDD | 44378839 | COLGATE-ALLEGHANY | 018/488 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.940687 | 39.4514 | ETL.6470 | 40693263 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119196805 | T3 DI COLGATE-ALLGHNY 18/493 RPR STRW | 44379097 | COLGATE-ALLEGHANY | 018/493 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.937371 | 39.4517 | ETL.6470 | 40822631 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119196870 | T2 MNDCN-WLTS-FRT BRG 36/3 RPR GYWW | 44610681 | MENDOCINO-WILLITS-FORT BRAGG | 036/003 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.704516 | 39.3898 | ETL.7550 | 40669455 | Guy Wire-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
119197081 | T3 DI COLGATE-ALLGHNY 20/556 RPR STRW | 44379097 | COLGATE-ALLEGHANY | 020/556 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.897851 | 39.4635 | ETL.6470 | 40824276 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119197083 | T3NT DI CLGTE-ALLGHNY 20/556 RMV PL BUTT | 44378839 | COLGATE-ALLEGHANY | 020/556 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.897851 | 39.4635 | ETL.6470 | 40824276 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119197439 | T2 HUMBOLDT-TRINITY 77/0 RPL ANCHOR |  | HUMBOLDT-TRINITY | 077/000 | 93E | E | 2020_(2) High fire spread TD |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.461601 | 40.6928 | ETL.1820 | 44554017 | Anchor-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Capital | 637 | Eureka
119197541 | T2 CARIBOU-PLUMAS JCT 07/013 RPL PL | 31508658 | CARIBOU-PLUMAS JCT | 007/013 | 70Y | E | 2020_(2) High fire spread TD |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.057484 | 40.0102 | ETL.6290 | 40656462 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain
119197554 | T3 DI COLGATE-ALLEGHANY 15/425 RPR STRW | 44379097 | COLGATE-ALLEGHANY | 015/425 | ICW | E | 2020_(1a) PSPS |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.981287 | 39.4469 | ETL.6470 | 40818495 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119197556 | T3 DI MTCLF-GRN VLLY 18/126L REPL POLE | 31506808 | METCALF-GREEN VALLEY | 018/126 | 70Y | E | 2020_(2) High fire spread TD |  |  |  |  | LATE | South | WSIP | [6 empty] | '-121.691285 | 37.0146 | ETL.2540 | 44769618 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Moss Landing
119197785 | T3 DI COLGATE-ALLEGHANY 17/469 RPR SPLW | 44379095 | COLGATE-ALLEGHANY | 017/469 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.952807 | 39.4501 | ETL.6470 | 40693259 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119197811 | T3NT DI CLGTE-ALLGHNY 17/469 RMV PL BUTT | 44379095 | COLGATE-ALLEGHANY | 017/469 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.952807 | 39.4501 | ETL.6470 | 40693259 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119197813 | T3 DI COLGATE-ALLEGHANY 17/483 RPR STRW | 44379097 | COLGATE-ALLEGHANY | 017/483 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.944128 | 39.451 | ETL.6470 | 40818503 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119197815 | T3 DI COLGATE-ALLEGHANY 17/484 RPR STRW | 44379097 | COLGATE-ALLEGHANY | 017/484 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.943136 | 39.4511 | ETL.6470 | 40822630 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119197831 | T3NT DI CLGTE-ALLEGHANY 19/536 RMV BUTT | 44379095 | COLGATE-ALLEGHANY | 019/536 | ICW | F | 2020_(2) High fire spread TD |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.910532 | 39.4582 | ETL.6470 | 40658308 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119197867 | T3 DI COLGATE-ALLEGHANY 17/476 RPR STRW | 44379097 | COLGATE-ALLEGHANY | 017/476 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.948167 | 39.4506 | ETL.6470 | 40868966 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119197868 | T3NT DI CLGTE-ALLGHNY 17/476 RMV PL BUTT | 44379097 | COLGATE-ALLEGHANY | 017/476 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.948167 | 39.4506 | ETL.6470 | 40868966 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119197903 | T3 DI COLGATE-ALLEGHANY 16/448 RPR STRW | 44379097 | COLGATE-ALLEGHANY | 016/448 | ICW | E | 2020_(1a) PSPS |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.966334 | 39.4486 | ETL.6470 | 40868964 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119197905 | T3 DI COLGATE-ALLEGHANY 17/465 RPR STRW | 44379097 | COLGATE-ALLEGHANY | 017/465 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.955344 | 39.4498 | ETL.6470 | 40874710 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119197909 | T3 DI COLGATE-ALLEGHANY 17/471 RPR INSW | 44379091 | COLGATE-ALLEGHANY | 017/471 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.951562 | 39.4502 | ETL.6470 | 40790973 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119197921 | T3NT DI COLGATE-ALLEGHNY 17/471 RMV BUTT | 44379095 | COLGATE-ALLEGHANY | 017/471 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.951546 | 39.4502 | ETL.6470 | 40760733 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119197926 | T3 DI COLGATE-ALLEGHANY 18/499 RPR STRW | 44379095 | COLGATE-ALLEGHANY | 018/499 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.933458 | 39.4522 | ETL.6470 | 40664635 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119197927 | T3NT DI CLGTE-ALLGHNY 18/499 RMV PL BUTT | 44379095 | COLGATE-ALLEGHANY | 018/499 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.933458 | 39.4522 | ETL.6470 | 40664635 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119197928 | T3NT DI CLGTE-ALLEGHANY 18/499 INST MRKW | 44379095 | COLGATE-ALLEGHANY | 018/499 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.933458 | 39.4522 | ETL.6470 | 40664635 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119197969 | T3 DI COLGATE-ALLEGHANY 20/541 RPR STRW | 44378720 | COLGATE-ALLEGHANY | 020/541 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.907877 | 39.4602 | ETL.6470 | 40590447 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119197980 | T3NT DI CLGTE-ALLGHNY 20/541 RMV PL BUTT | 44378479 | COLGATE-ALLEGHANY | 020/541 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.907877 | 39.4602 | ETL.6470 | 40590447 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119197989 | T3 DI CLGTE-ALLEGHANY 23/645 RPR STRW | 44379097 | COLGATE-ALLEGHANY | 023/645 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.849519 | 39.4737 | ETL.6470 | 40822738 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119198000 | T3 DI CLGTE-ALLEGHANY 23/646 RPR STRW | 44379097 | COLGATE-ALLEGHANY | 023/646 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.849336 | 39.4734 | ETL.6470 | 40869677 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119198019 | T3 DI CLGTE-ALLEGHANY 19/524 RPR STRW | 44378720 | COLGATE-ALLEGHANY | 019/524 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.916426 | 39.454 | ETL.6470 | 40593296 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119198031 | T3NT DI CLGTE-ALLGHNY 19/524 RMV PL BUTT | 44378479 | COLGATE-ALLEGHANY | 019/524 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.916426 | 39.454 | ETL.6470 | 40593296 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119198033 | T3NT DI CLGT-ALLGHNY 17/462 RMV PL BUTT | 44371190 | COLGATE-ALLEGHANY | 017/462 | ICW | F | 2020_(1a) PSPS |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.957324 | 39.4496 | ETL.6470 | 40766725 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119198326 | T3 DI COLGATE-ALLEGHANY 20/554 RPR STRW | 44379095 | COLGATE-ALLEGHANY | 020/554 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.899329 | 39.463 | ETL.6470 | 40760743 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119198328 | T3NT DI CLGTE-ALLGHNY 20/554 RMV PL BUTT | 44379095 | COLGATE-ALLEGHANY | 020/554 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.899329 | 39.463 | ETL.6470 | 40760743 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119198513 | T2 DI KILARC-DESCHUTES 17/356 RMV PL BUT | 44406469 | KILARC-DESCHUTES | 017/356 | ICW | E | 2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.133522 | 40.5636 | ETL.7300 | 40771273 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119198514 | T2 DI KILARC-DESCHUTES 17/356 RPR STRW | 44406469 | KILARC-DESCHUTES | 017/356 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.133522 | 40.5636 | ETL.7300 | 40771273 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119198551 | T3 DI COLGATE-ALLGHANY 24/653 RPR STRW | 44378720 | COLGATE-ALLEGHANY | 024/653 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.848017 | 39.471 | ETL.6470 | 40598570 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119198753 | T3 DI COLGATE-ALLGHANY 22/600 RPL INSW | 31507063 | COLGATE-ALLEGHANY | 022/600 | 93I | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.869588 | 39.4722 | ETL.6470 | 40849862 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Sacramento
119198818 | T3NT DI CLGTE-ALLGHNY 14/394 RMV PL BUTT | 44378479 | COLGATE-ALLEGHANY | 014/394 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.995732 | 39.4401 | ETL.6470 | 40767326 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119198834 | T3 DI COLGATE-ALLGHNY 14/394 RPR STRW | 31507062 | COLGATE-ALLEGHANY | 014/394 | 93E | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.995732 | 39.4401 | ETL.6470 | 40767326 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Sacramento
119198837 | T3NT DI CLGTE-ALLGHNY 20/253 RMV PL BUTT | 44378466 | COLGATE-ALLEGHANY | 020/543 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.906941 | 39.461 | ETL.6470 | 40658311 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119198839 | T3 DI COLGATE-ALLEGHANY 20/253 RPR STRW | 44378465 | COLGATE-ALLEGHANY | 020/543 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.906941 | 39.461 | ETL.6470 | 40658311 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119198880 | T3 DI COLGATE-ALLGHNY 14/395 RPR STRW | 44378465 | COLGATE-ALLEGHANY | 014/395 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.995697 | 39.4405 | ETL.6470 | 40766614 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119198881 | T3 DI COLGATE-ALLEGHANY 20/253 RPR INSW | 44378808 | COLGATE-ALLEGHANY | 020/543 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.907001 | 39.4608 | ETL.6470 | 40688243 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119198882 | T3NT DI CLGTE-ALLGHNY 14/395 RMV PL BUTT | 44378466 | COLGATE-ALLEGHANY | 014/395 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.995697 | 39.4405 | ETL.6470 | 40766614 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119198960 | T3NT DI COLGATE-CHALLENGE 2/45 INS MRKW | 44379099 | COLGATE-CHALLENGE | 002/045 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.173941 | 39.3564 | ETL.6480 | 40655133 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119198966 | T3NT DI COLGATE-CHLENGE 2/45 RMV PL BUTT | 44379099 | COLGATE-CHALLENGE | 002/045 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.173941 | 39.3564 | ETL.6480 | 40655133 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119198968 | T3 DI COLGATE-ALLGHNY 24/665 REPL POLE | 31507362 | COLGATE-ALLEGHANY | 024/665 | 70Y | E | 2020_(1a) PSPS |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.846157 | 39.4671 | ETL.6470 | 40664652 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento
119199063 | T3NT DI CLGTE-ALLGHNY 21/590 RMV PL BUTT | 44378479 | COLGATE-ALLEGHANY | 021/590 | ICW | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.876683 | 39.4713 | ETL.6470 | 40767224 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119199067 | T3 DI COLGATE-ALLGHNY 21/590 RPR INSW | 44378807 | COLGATE-ALLEGHANY | 021/590 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.876683 | 39.4713 | ETL.6470 | 40798721 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119199134 | T3NT DI CLGTE-ALLGHNY 22/618 RMV PL BUTT | 44378466 | COLGATE-ALLEGHANY | 022/618 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.858726 | 39.4765 | ETL.6470 | 40760456 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119199135 | T3 DI COLGATE-ALLGHNY 22/618 RPR STRW | 44378465 | COLGATE-ALLEGHANY | 022/618 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.858726 | 39.4765 | ETL.6470 | 40760456 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119199199 | T3 DI COLGATE-ALLEGHANY 21/577 RPR STRW | 44365653 | COLGATE-ALLEGHANY | 021/577 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.885747 | 39.4699 | ETL.6470 | 40598668 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119199320 | T3 DI COLGATE-ALLEGHANY 21/577 RPL INSW | 31507063 | COLGATE-ALLEGHANY | 021/577 | 93I | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.885752 | 39.4699 | ETL.6470 | 40625292 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Sacramento
119199323 | T3 DI COLGTE-ALLEGHANY 19/513 RMV DEBRIS | 44365654 | COLGATE-ALLEGHANY | 019/513 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.923791 | 39.4532 | ETL.6470 | 40611344 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119199325 | T3 DI COLGATE-ALLEGHANY 15/409 RPR IBWW | 44365653 | COLGATE-ALLEGHANY | 015/409 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.992785 | 39.4456 | ETL.6470 | 40602523 | Insulator Bond Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119199326 | T3 DI COLGATE-ALLEGHANY 14/397 RPR SPLW | 44365653 | COLGATE-ALLEGHANY | 014/397 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.99565 | 39.4414 | ETL.6470 | 40817348 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119199328 | T3NT DI CLGTE-ALLGHNY 23/621 RMV PL BUTT | 44378466 | COLGATE-ALLEGHANY | 023/621 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.856994 | 39.4773 | ETL.6470 | 40672230 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119199329 | T3 DI CLGATE-ALLEGHANY 23/621 RPR STRW | 44378465 | COLGATE-ALLEGHANY | 023/621 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.856994 | 39.4773 | ETL.6470 | 40672230 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119199471 | T3 DI COLGATE-ALLGHNY 21/583 REPL INSW | 31507063 | COLGATE-ALLEGHANY | 021/583 | 93I | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.881516 | 39.4707 | ETL.6470 | 40822634 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Sacramento
119199479 | T3NT DI COLGATE-ALLGHNY 21/583 INS MRKW | 44378479 | COLGATE-ALLEGHANY | 021/583 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.881516 | 39.4707 | ETL.6470 | 40822634 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119199512 | T3NT DI CLGTE-ALLGHNY 21/583 RMV PL BUTT | 44378479 | COLGATE-ALLEGHANY | 021/583 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.881516 | 39.4707 | ETL.6470 | 40822634 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119199514 | T3 DI COLGATE-ALLGHNY 23/622 RPL SPLW | 44365653 | COLGATE-ALLEGHANY | 023/622 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.856373 | 39.4777 | ETL.6470 | 44686508 | Splice-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119199516 | DI GATES-PANOCHE #1 3/14 RPR FOND | 44394839 | GATES-PANOCHE #1 | 003/014 | ICQ | F | 2020_(1b) Lines with special commitments |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.150378 | 36.1733 | ETL.4720 | 40753573 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 10
119199541 | T3 DI CLGATE-ALLEGHANY 21/592 RPR INSW | 44378807 | COLGATE-ALLEGHANY | 021/592 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.875293 | 39.4715 | ETL.6470 | 40853519 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119199545 | T3 DI CLGATE-ALLEGHANY 21/580 RPR INSW | 44378807 | COLGATE-ALLEGHANY | 021/580 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.883708 | 39.4704 | ETL.6470 | 40790985 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119199546 | T3NT DI CLGTE-ALLGHNY 21/580 RMV PL BUT | 44378466 | COLGATE-ALLEGHANY | 021/580 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.883743 | 39.4704 | ETL.6470 | 40760745 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119199547 | T3 DI CLGATE-ALLEGHANY 21/580 RPR STRW | 44378465 | COLGATE-ALLEGHANY | 021/580 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.883743 | 39.4704 | ETL.6470 | 40760745 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119199548 | T3 DI CLGATE-ALLEGHANY 21/578 RMV BUTT | 44378465 | COLGATE-ALLEGHANY | 021/578 | ICW | E | 2020_(3) On high spread structure |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.885139 | 39.4702 | ETL.6470 | 40679468 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119199591 | T3 DI COLGATE-ALLGHNY 21/566 RPR STRW | 44378465 | COLGATE-ALLEGHANY | 021/566 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.892165 | 39.4665 | ETL.6470 | 40611189 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119199592 | T3 DI COLGATE-ALLGHNY 21/566 RPR HRDW | 44378465 | COLGATE-ALLEGHANY | 021/566 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.892165 | 39.4665 | ETL.6470 | 40611189 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119199598 | T3 DI COLGATE-ALLGHNY 23/648 RPR STRW | 44378465 | COLGATE-ALLEGHANY | 023/648 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.848966 | 39.4727 | ETL.6470 | 40602540 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119199841 | T3 DI CLGATE-ALLEGHANY 21/578 RPR POLE | 44378465 | COLGATE-ALLEGHANY | 021/578 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.885139 | 39.4702 | ETL.6470 | 40679468 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119199884 | T3NT DI CLGATE-ALLGHNY 21/575 RMV DEBRIS | 44378479 | COLGATE-ALLEGHANY | 021/575 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.886847 | 39.4693 | ETL.6470 | 40868973 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119199886 | T3 DI COLGATE-ALLGHNY 21/575 RPR INSW | 44378807 | COLGATE-ALLEGHANY | 021/575 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.886881 | 39.4693 | ETL.6470 | 40892148 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119199888 | T3NT DI CLGTE-ALLGHNY 22/595 RMV PL BUTT | 44378466 | COLGATE-ALLEGHANY | 022/595 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.873134 | 39.4717 | ETL.6470 | 40693300 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119200018 | T3 DI COLGATE-ALLEGHANY 22/594 RPR POLE | 44378465 | COLGATE-ALLEGHANY | 022/594 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.873829 | 39.4717 | ETL.6470 | 40590450 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119200081 | T3 DI COLGATE-ALLGHNY 22/595 RPR POLE | 44378465 | COLGATE-ALLEGHANY | 022/595 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.873134 | 39.4717 | ETL.6470 | 40693300 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119200087 | T3 DI COLGATE-ALLGHNY 20/559 RPR INSW | 44365653 | COLGATE-ALLEGHANY | 020/559 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.896048 | 39.4644 | ETL.6470 | 40892146 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119200193 | T3 DI COLGATE-ALLGHNY 15/412 RMV BUTT | 44378466 | COLGATE-ALLEGHANY | 015/412 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.990618 | 39.4459 | ETL.6470 | 40664628 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119200199 | T3 DI COLGATE-ALLGHNY 15/412 REPL POLE | 31507362 | COLGATE-ALLEGHANY | 015/412 | 70Y | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.990618 | 39.4459 | ETL.6470 | 40664628 | Structure-Wood | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento
119200211 | T2 EI BRIDGEVILLE-GARBERVIL 21/9 RPL ANC | 31508615 | BRIDGEVILLE-GARBERVILLE | 021/009 | 93E | E | 2020_(2) High fire spread TD |  |  |  | TR2 | SCHD | North Coast | WSIP | [6 empty] | '-123.757631 | 40.222 | ETL.6220 | 40875290 | Anchor-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Eureka
119200314 | T3NT DI COLGATE-ALLGHNY 15/406 INST MRKW | 44378479 | COLGATE-ALLEGHANY | 015/406 | ICW | F | 2020_(1a) PSPS |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.993666 | 39.4452 | ETL.6470 | 40817350 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119200315 | T3 DI COLGATE-ALLGHNY 20/559 BOND GUY | 44365653 | COLGATE-ALLEGHANY | 020/559 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.896056 | 39.4644 | ETL.6470 | 40868971 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119200327 | T3 DI CLGATE-ALLEGHANY 22/617 RPR POLE | 44378720 | COLGATE-ALLEGHANY | 022/617 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.859291 | 39.4762 | ETL.6470 | 40767226 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119200495 | T3 T2 DI COLGATE-ALLEGHANY 22/604 RPR PL | 44378465 | COLGATE-ALLEGHANY | 022/604 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.867098 | 39.4725 | ETL.6470 | 40593302 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119200497 | T3 DI CLGATE-ALLEGHANY 22/604 RMV DEBRIS | 44378466 | COLGATE-ALLEGHANY | 022/604 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.867098 | 39.4725 | ETL.6470 | 40593302 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119200662 | T3 DI CLGATE-ALLEGHANY 20/546 RPR STRW | 44379097 | COLGATE-ALLEGHANY | 020/546 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.905058 | 39.4619 | ETL.6470 | 40824274 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119200831 | T2 EI DIVIDE-CABRILLO #2 08/098 RPL JUMP |  | DIVIDE-CABRILLO #2 | 008/098 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-120.4362935 | 34.71 | ETL.1370 | 40685429 | Jumper-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - 12
119200857 | T2 EI DIVIDE-CABRILLO #2 08/097 RPL INSW | 31508886 | DIVIDE-CABRILLO #2 | 008/097 | 93I | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-120.4362902 | 34.7111 | ETL.1370 | 40720300 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Pismo Beach |  | Y - 402
119200896 | T3 DI CLGATE-ALLEGHANY 23/629 RPL HRDD | 44374175 | COLGATE-ALLEGHANY | 023/629 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.852302 | 39.4793 | ETL.6470 | 44684327 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119200898 | T3NT DI CLGT-ALLGHNY 23/629 RMV PL BUT | 44374175 | COLGATE-ALLEGHANY | 023/629 | ICW | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.852302 | 39.4793 | ETL.6470 | 44684327 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119200986 | T2 EI DIVIDE-CABRILLO #2 08/096 RPL INSW | 31508886 | DIVIDE-CABRILLO #2 | 008/096 | 93I | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-120.4363033 | 34.7121 | ETL.1370 | 40629304 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Pismo Beach
119200994 | T3 DI COLGATE-ALLGHNY 20/563 INST NUMBR | 44378466 | COLGATE-ALLEGHANY | 020/563 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.893733 | 39.4656 | ETL.6470 | 40658314 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119200995 | T3NT DI FULTON-LAKEVILLE 33/145 RPR FOND |  | FULTON-LAKEVILLE | 033/145 | ICQ | F | 2020_(4) TD tag on high spread line |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.592176 | 38.3835 | ETL.4950 | 40681705 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville
119200997 | T3 DI COLGATE-ALLGHNY 20/563 RPR POLE | 44378465 | COLGATE-ALLEGHANY | 020/563 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.893733 | 39.4656 | ETL.6470 | 40658314 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119201058 | T3 DI CLGATE-ALLEGHANY 15/405 RPR POLE | 44378720 | COLGATE-ALLEGHANY | 015/405 | ICW | E | 2020_(1a) PSPS |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.994007 | 39.4446 | ETL.6470 | 40824270 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119201119 | T2 EI DIVIDE-CABRILLO #2 07/094 RPL HRD |  | DIVIDE-CABRILLO #2 | 007/094 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-120.436267 | 34.7142 | ETL.1370 | 40702312 | Hardware-Wood | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach
119201238 | T2 EI DIVIDE-CABRILLO #2 07/092 RPL INSW | 31508886 | DIVIDE-CABRILLO #2 | 007/092 | 93I | E | 2020_(2) High fire spread TD |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-120.4362818 | 34.7164 | ETL.1370 | 40634062 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Pismo Beach |  | Y - 402
119201271 | DI GATES-PANOCHE #1 012/058 RPL INSS | 31514618 | GATES-PANOCHE #1 | 012/058 | 93K | E | 2020_(1b) Lines with special commitments |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.239982 | 36.2868 | ETL.4720 | 40887587 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - 10
119201273 | DI GATES-PANOCHE #2 012/058 RPL INSS | 31514619 | GATES-PANOCHE #2 | 012/058 | 93K | E | 2020_(1b) Lines with special commitments |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.239982 | 36.2868 | ETL.4730 | 40887589 | Insulator-Steel | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Fresno |  | Y - Prog 402
119201275 | DI GATES-PANOCHE #1 012/058 RPR FOND | 44364838 | GATES-PANOCHE #1 | 012/058 | ICQ | F | 2020_(1b) Lines with special commitments |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.240683 | 36.2877 | ETL.4720 | 40863636 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 10
119201342 | T3 DI COLGATE-ALLEG 15/420 REFRAME | 31507062 | COLGATE-ALLEGHANY | 015/420 | 93E | E | 2020_(1a) PSPS |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.984493 | 39.4466 | ETL.6470 | 40598662 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Sacramento
119201362 | T2 EI DIVIDE-CABRILLO #2 007/091 RPL INS | 31508886 | DIVIDE-CABRILLO #2 | 007/091 | 93I | E | 2020_(2) High fire spread TD |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-120.4362986 | 34.7172 | ETL.1370 | 40889870 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Pismo Beach |  | Y - 402
119201415 | T3 DI COLGATE-ALLEGHANY 21/589 RPR INSW | 44378462 | COLGATE-ALLEGHANY | 021/589 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.877358 | 39.4712 | ETL.6470 | 40696051 | Insulator-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119201631 | T2 EI DIVIDE-CABRILLO #2 7/89 RPL INSW | 31508886 | DIVIDE-CABRILLO #2 | 007/089 | 93I | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-120.4363077 | 34.7195 | ETL.1370 | 40840883 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Pismo Beach |  | Y - 402
119201795 | T2 EI DIVIDE-CABRILLO #2 07/088 RPR GYWW |  | DIVIDE-CABRILLO #2 | 007/088 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-120.436271 | 34.72 | ETL.1370 | 40828430 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - 12
119201796 | T2 EI DIVIDE-CABRILLO #2 07/088 RPR JUMP |  | DIVIDE-CABRILLO #2 | 007/088 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-120.436271 | 34.72 | ETL.1370 | 40828430 | Jumper-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Pismo Beach |  | Y - 11
119201797 | T2 EI DIVIDE-CABRILLO #2 07/088 RPL INSW | 31508886 | DIVIDE-CABRILLO #2 | 007/088 | 93I | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-120.436284 | 34.72 | ETL.1370 | 40856116 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Pismo Beach |  | Y - 12
119202131 | T2 DI CRTN-MNDCN #1 29/140 RPR FOND | 44238817 | CORTINA-MENDOCINO #1 | 029/140 | ICQ | F | 2020_(2) High fire spread TD |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.722833 | 39.0399 | ETL.1330 | 40587891 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville
119203305 | T2 DI FULTON-HOPLAND 18/9 CANCEL | 31509679 | FULTON-HOPLAND | 018/009 | 93E | E | 2020_(4) TD tag on high spread line |  |  | CANCEL/CNCL | TR2 |  | North Coast | WSIP | [6 empty] | '-122.882493 | 38.7234 | ETL.6890 | 40860943 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Lakeville
119203308 | T3 DI MTCLF-GRN VLLY 18/126R REPL POLE | 31506808 | METCALF-GREEN VALLEY | 018/126 | 70Y | E | 2020_(2) High fire spread TD |  |  |  |  | LATE | South | WSIP | [6 empty] | '-121.691285 | 37.0146 | ETL.2540 | 44769619 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Moss Landing
119203414 | T3NT DI KILARC-CDAR CRK 5/130 RMV DEBRIS | 43939119 | KILARC-CEDAR CREEK | 005/130 | ICW | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.974468 | 40.7092 | ETL.7290 | 40759371 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119204332 | T3 DI COLGATE-ALLEGHANY 24/668 RPR POLE | 44378720 | COLGATE-ALLEGHANY | 024/668 | ICW | E | 2020_(1a) PSPS |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.845474 | 39.4658 | ETL.6470 | 40818519 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119204427 | DI GATES-PANOCHE#1 4/23 RPR STRT | 44394839 | GATES-PANOCHE #1 | 004/023 | ICQ | E | 2020_(1b) Lines with special commitments |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.169263 | 36.1957 | ETL.4720 | 40658944 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 10
119204461 | T3 DI COLGATE-ALLGHNY 21/585 RPR POLE | 44378720 | COLGATE-ALLEGHANY | 021/585 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.880096 | 39.4709 | ETL.6470 | 40873687 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119204462 | T3 DI COLGATE-ALLGHNY 21/585 INST HV | 44378479 | COLGATE-ALLEGHANY | 021/585 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.880096 | 39.4709 | ETL.6470 | 40873687 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119204465 | T3 DI COLGATE-ALLEGHANY 015/415 RPR STRW | 44378465 | COLGATE-ALLEGHANY | 015/415 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.98812 | 39.4461 | ETL.6470 | 40818493 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119204468 | T3 DI COLGATE-ALLEGHANY 015/415 RMV BUTT | 44378465 | COLGATE-ALLEGHANY | 015/415 | ICW | E | 2020_(3) On high spread structure |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.98812 | 39.4461 | ETL.6470 | 40818493 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119204469 | DI GATES-MUSTANG SW STA #1 1/9 RPR FOND | 44389942 | SPARE T-LINE RECORD | 001/009 | ICQ | F | 2020_(1b) Lines with special commitments | [5 empty] | South | WSIP | [6 empty] | '-120.101328 | 36.1507 | ETL.2604 | 40858216 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - Prog 402
119204722 | DI GATES-PANOCHE #1 6/29 RPR FOND | 44394839 | GATES-PANOCHE #1 | 006/029 | ICQ | F | 2020_(1b) Lines with special commitments |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.181547 | 36.2116 | ETL.4720 | 40863284 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 10
119204723 | T3 DI COLGATE-ALLGHNY 14/393 BOND GUY | 44378465 | COLGATE-ALLEGHANY | 014/393 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.995771 | 39.4395 | ETL.6470 | 40664626 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119204726 | T3 DI COLGATE-ALLGHNY 14/393 RMV BUTT | 44378466 | COLGATE-ALLEGHANY | 014/393 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.995771 | 39.4395 | ETL.6470 | 40664626 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119204894 | DI MONTE RIO-FORT ROSS 16/2 RPR GYWW |  | ETL.6979.POLE.WDPS | 016/002 | ICW | E | 2020_(2) High fire spread TD | [5 empty] | North Coast | WSIP | [6 empty] | '-123.030487 | 38.4803 | ETL.6979 | 44762512 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
119204895 | DI GATES-PANOCHE #1 007/037 RPR FOND | 44394839 | GATES-PANOCHE #1 | 007/037 | ICQ | E | 2020_(1b) Lines with special commitments |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.19787 | 36.2326 | ETL.4720 | 40811170 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 10
119204897 | DI MONTE RIO-FORT ROSS 16/2 RPR GYWW |  | ETL.6979.POLE.WDPS | 016/002 | ICW | E | 2020_(2) High fire spread TD | [5 empty] | North Coast | WSIP | [6 empty] | '-123.030487 | 38.4803 | ETL.6979 | 44762511 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
119204898 | DI MONTE RIO-FORT ROSS 16/2 RPR GYWW |  | ETL.6979.POLE.WDPS | 016/002 | ICW | E | 2020_(2) High fire spread TD | [5 empty] | North Coast | WSIP | [6 empty] | '-123.030487 | 38.4803 | ETL.6979 | 44762510 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
119204945 | DI GATES-PANOCHE #1 14/67 RPR FOND | 44394839 | GATES-PANOCHE #1 | 014/067 | ICQ | E | 2020_(1b) Lines with special commitments |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.258654 | 36.3108 | ETL.4720 | 40818932 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 10
119205128 | DI FULTON-HOPLAND 9/10 RPR GYWW | 44579280 | FULTON-HOPLAND | 009/010 | ICW | E | 2020_(4) TD tag on high spread line | [5 empty] | North Coast | WSIP | [6 empty] | '-122.844125 | 38.6132 | ETL.6890 | 40587771 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
119205475 | DI GATES-PANOCHE #1 9/40 RPR FOND | 44394839 | GATES-PANOCHE #1 | 009/040 | ICQ | E | 2020_(1b) Lines with special commitments |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.203989 | 36.2405 | ETL.4720 | 40604957 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 10
119205584 | DI GATES-PANOCHE #1 011/057 RPR STRT | 44394839 | GATES-PANOCHE #1 | 011/057 | ICQ | E | 2020_(1b) Lines with special commitments |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.238632 | 36.2851 | ETL.4720 | 40817992 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 10
119205707 | T2 DI JOLON TAP 012/168 RPR HRDD | 44578863 | JOLON TAP | 012/168 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-121.174717 | 36.0557 | ETL.7321 | 44212731 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing
119205721 | T2 WEST POINT-VALLEY SPRINGS 6/76 STUB P |  | WEST POINT-VALLEY SPRINGS | 006/076 | GAR | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 | <60D | Central | WSIP | [6 empty] | '-120.639628 | 38.3753 | ETL.8350 | 40876055 | Structure-Wood | Rotten | Stub |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 586 | Victor
119205853 | T2 DI JOLON TAP 012/168 BOND HRDD | 44575318 | JOLON TAP | 012/168 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-121.174717 | 36.0557 | ETL.7321 | 44212731 | Insulator Bond Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Moss Landing
119205991 | DI GATES-PANOCHE#1 13/62 RPR STRT | 44394839 | GATES-PANOCHE #1 | 013/062 | ICQ | E | 2020_(1b) Lines with special commitments |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.24886 | 36.2982 | ETL.4720 | 40663938 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 10
119206192 | DI GATES-PANOCHE #1 008/039 RPR FOND | 44394839 | GATES-PANOCHE #1 | 008/039 | ICQ | F | 2020_(1b) Lines with special commitments |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.201933 | 36.2378 | ETL.4720 | 40863286 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 10
119206361 | T2 HUMBOLDT-TRINITY 93/7 INST WEIGHTS | 44356920 | HUMBOLDT-TRINITY | 093/007 | ICS | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.744908 | 40.7488 | ETL.1820 | 44395220 | Conductor-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Eureka
119206450 | EI T3NT FULTON-IGNACIO #1 016/083 RPR FO | 44310479 | FULTON-IGNACIO #1 | 016/083 | ICQ | F | 2020_(4) TD tag on high spread line |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.592244 | 38.3959 | ETL.4680 | 40651563 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville
119206491 | T3 DI FRH MDW-MDL FRK 10/189 REPL POLE | 31507072 | FRENCH MEADOWS-MIDDLE FORK | 010/189 | 70Y | E | 2020_(1a) PSPS |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.567083 | 39.0135 | ETL.6870 | 40761240 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento
119206917 | T2 FULTON-HOPLAND 32/006 RPLC STRW | 31478309 | FULTON-HOPLAND | 032/006 | 70Y | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.042755 | 38.8749 | ETL.6890 | 40824189 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville
119207104 | T3 CRESTA-RIO OSO 12/100 INST DAMPER |  | CRESTA-RIO OSO | 012/100 | ICS | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.451228 | 39.7844 | ETL.4590 | 40910126 | Damper-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain
119207350 | T3 EI KILARC-CEDAR CREEK 6/156 RPR GYWW | 43939119 | KILARC-CEDAR CREEK | 006/156 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.994445 | 40.7152 | ETL.7290 | 40877862 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119208013 | T3 EI KILARC-CEDAR CREEK 012/264 RPR STR | 43939119 | KILARC-CEDAR CREEK | 012/264 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.950282 | 40.7772 | ETL.7290 | 40693125 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119208043 | DI FULTON-HOPLAND 9/11 RPL INSS | 31528322 | FULTON-HOPLAND | 009/011 | 93I | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.843587 | 38.6133 | ETL.6890 | 40609155 | Insulator-Wood | No Good/Out of Stdrd | Replace | ESTS erdy | ESTS | Assigned to Estimator | Not Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Lakeville
119208045 | DI FULTON-HOPLAND 9/11 INST MRKW |  | FULTON-HOPLAND | 009/011 | ICW | F | 2020_(4b) On structure in bucket 4 | [5 empty] | North Coast | WSIP | [6 empty] | '-122.84371 | 38.6134 | ETL.6890 | 40584860 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
119208354 | DI GATES-PANOCHE #1 14/69 RPR FOND | 44371519 | GATES-PANOCHE #1 | 014/069 | ICQ | E | 2020_(1b) Lines with special commitments |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.263044 | 36.3159 | ETL.4720 | 40863292 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 10
119208358 | T3 DI FRNCH MDWS-MDL FRK 9/182 RPR STRW | 44379165 | FRENCH MEADOWS-MIDDLE FORK | 009/182 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.561664 | 39.0162 | ETL.6870 | 40751850 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119208574 | T3 DI KESWICK-CASCADE 6/120 RPR CNDS |  | CRESTA-RIO OSO | 016/133 | ICS | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-122.411538 | 40.6395 | ETL.4590 | 44237870 | Conductor-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain
119208600 | T3NT DI FNCH MDWS-MDL FRK 9/182 RMV BUTT | 44379165 | FRENCH MEADOWS-MIDDLE FORK | 009/182 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-120.561664 | 39.0162 | ETL.6870 | 40751850 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119208601 | T2 DI COLGATE-CHALLENGE 0/22 RPR GYWW | 44394872 | COLGATE-CHALLENGE | 000/022 | ICW | E | 2020_(1a) PSPS |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.19013 | 39.3438 | ETL.6480 | 40598490 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119208887 | BLTA-RVRBNK-MLNES SWSTA :5/0 RPLC POLE | 31507102 | BELLOTA-RIVERBANK-MELONES SW STA | :005/000 | 70Y | E | 2020_(4) TD tag on high spread line | [5 empty] | Central | WSIP | [6 empty] | '-120.563946 | 37.8882 | ETL.1070 | 40602879 | Structure-Wood | Rotten | Replace | PEND erdy | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Victor |  | Y - 15
119208920 | DI PHILO JCT-ELK 30/3L RPR ANCW | 44610684 | PHILO JCT-ELK | 030/003 | ICW | E | 2020_(4) TD tag on high spread line | [5 empty] | North Coast | WSIP | [6 empty] | '-123.600897 | 39.1191 | ETL.7780 | 44744317 | Anchor-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
119209053 | T2 EI KESWICK-TRINITY 16/204 RMV DEBRIS |  | KESWICK-TRINITY | 016/204 | ICS | F | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.682609 | 40.719 | ETL.7270 | 44649334 | Anchor-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain
119209109 | EI T3NT FULTON-IGNACIO #1 2/13 RPR FOND | 44310479 | FULTON-IGNACIO #1 | 002/013 | ICQ | F | 2020_(4) TD tag on high spread line |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.723758 | 38.497 | ETL.4680 | 40651555 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville
119209112 | DI GATES-PANOCHE #1 013/064 RPR FOND | 44394839 | GATES-PANOCHE #1 | 013/064 | ICQ | F | 2020_(1b) Lines with special commitments |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.252957 | 36.3035 | ETL.4720 | 40753579 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 10
119209223 | T3 EI FULTON-LAKEVILLE 028/126 RPR COND |  | FULTON-LAKEVILLE | 028/126 | ICS | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.585331 | 38.4514 | ETL.4950 | 40658046 | Conductor-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville
119209224 | T3 EI FULTON-LAKEVILLE 028/126 RPR FOND |  | FULTON-LAKEVILLE | 028/126 | ICQ | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.585331 | 38.4514 | ETL.4950 | 40658046 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville
119209249 | T3 DI COLGATE-ALLEGHANY 21/591 RPR STRW | 44378465 | COLGATE-ALLEGHANY | 021/591 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.876021 | 39.4713 | ETL.6470 | 40760454 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119209415 | EI T3NT ROUND MTN-TABLE MTN #2 0/8 INST | 31507391 | ROUND MTN-TABLE MTN #2 | 000/008 | 93A | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.929764 | 40.7885 | ETL.6070 | 40871656 | Structure-Tower | Anti-Climbing Guard | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Capital | 988 | Table Mountain
119209622 | DI GATES-PANOCHE #1 9/45 RPR STRT | 44394839 | GATES-PANOCHE #1 | 009/045 | ICQ | E | 2020_(1b) Lines with special commitments |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.214345 | 36.2538 | ETL.4720 | 40753529 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 10
119209623 | DI GATES-PANOCHE #1 9/45 RPR FOND | 44394839 | GATES-PANOCHE #1 | 009/045 | ICQ | E | 2020_(1b) Lines with special commitments |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.214345 | 36.2538 | ETL.4720 | 40753529 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 10
119209687 | T2NT DI CTNWD #1 5/36 RPR FOND | 44406038 | COTTONWOOD #1 | 005/036 | ICQ | F | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.267779 | 40.3221 | ETL.6620 | 40910979 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
119209858 | T2 DRUM-SUMMIT #1 26/311 INST DAMPER | 44394772 | DRUM-SUMMIT #1 | 026/311 | ICW | E | 2020_(1b) Lines with special commitments |  |  |  | TR2 | WECC | North Valley | WSIP | [6 empty] | '-120.334944 | 39.3112 | ETL.1440 | 40756820 | Damper-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119209870 | T3NT DI MR BY-SLR SW ST #1 9/39 INS MRKS |  | MORRO BAY-SOLAR SW STA #1 | 009/039 | ICS | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | South | WSIP | [6 empty] | '-120.68926 | 35.3797 | ETL.5300 | 40870329 | Marker (i.e. signs)-Steel | Missing | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Pismo Beach
119210073 | EI T3NT FULTON-LAKEVILLE 027/121 RPR FON | 44636937 | FULTON-LAKEVILLE | 027/121 | ICQ | F | 2020_(1a) PSPS |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.592944 | 38.4655 | ETL.4950 | 40864660 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville
119210253 | T3 EI VOLTA-DESCHUTES 4/101 REFRAME CRSW | 31507464 | VOLTA-DESCHUTES | 004/101 | 93E | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.95167 | 40.4808 | ETL.8290 | 40667436 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  | released 7-13-20
119210255 | EI VOLTA-DESCHUTES 17/368 RPR POLE |  | VOLTA-DESCHUTES | 017/368 | ICW | E | 2020_(4) TD tag on high spread line | [5 empty] | North Valley | WSIP | [6 empty] | '-122.172168 | 40.5404 | ETL.8290 | 44949902 | Structure-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119210289 | DI SN LS OBSP-SNT 22/103 RPL INSS | 31510359 | SAN LUIS OBISPO-SANTA MARIA | 022/103 | 93K | E | 2020_(4) TD tag on high spread line | [5 empty] | South | WSIP | [6 empty] | '-120.44473 | 35.0026 | ETL.3540 | 40677651 | Insulator-Steel | No Good/Out of Stdrd | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLN | Maintenance | Capital | 532 | Pismo Beach |  | Y - Prog 402
119210452 | T3 EI MONTA VISTA-JFFRSN #1 18/76 RPR ST | 44614659 | MONTA VISTA-JEFFERSON #1 | 018/076 | ICQ | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.305533 | 37.4384 | ETL.5220 | 40818634 | Structure-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  |  | Huddart Park
119210790 | T3 EI ROUND MTN-TABLE MTN #2 1/11 RPL HR | 44156941 | ROUND MTN-TABLE MTN #2 | 001/011 | ICQ | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.931564 | 40.7796 | ETL.6070 | 40595194 | Hardware-Tower | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
119210911 | T2 EI HAT CRK #1-WSTWD 53/1025 RPL POLE | 31508285 | HAT CREEK #1-WESTWOOD | 053/1025 | 70Y | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.005555 | 40.3306 | ETL.7030 | 40601645 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain
119210977 | T3 EI KILARC-CEDAR CREEK 11/246 RPR CON | 43939119 | KILARC-CEDAR CREEK | 011/246 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.959958 | 40.7656 | ETL.7290 | 40771266 | Splice-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119210979 | EI T3NT FULTON-IGNACIO #1 018/093 INST A |  | FULTON-IGNACIO #1 | 018/093 | 93A | F | 2020_(3) On high spread structure |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.592662 | 38.3592 | ETL.4680 | 40651565 | Structure-Steel | Anti-Climbing Guard | Install |  |  |  |  | PEND | LC | TLQ | Tower | Capital | 988 | Lakeville
119211146 | T2 EI KESWICK-TRINITY 6/214 RMV VEGN |  | KESWICK-TRINITY | 016/214 | HNA | E | 2020_(3) On high spread structure |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.69117 | 40.7204 | ETL.7270 | 40668383 | Vegetation | Overgrown | Remove |  |  |  |  | PEND | LC | TLV | Vegetation | Expense | 564 | Table Mountain
119211456 | EI T3NT FULTON-IGNACIO #1 018/091 RPR F | 44310479 | FULTON-IGNACIO #1 | 018/091 | ICQ | F | 2020_(2) High fire spread TD |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.592571 | 38.3672 | ETL.4680 | 40594162 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville
119211546 | EI T3NT FULTON-LAKEVILLE 033/145 INST AC |  | FULTON-LAKEVILLE | 033/145 | 93A | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.592176 | 38.3835 | ETL.4950 | 40681705 | Structure-Tower | Anti-Climbing Guard | Install |  |  |  |  | PEND | LC | TLQ | Tower | Capital | 988 | Lakeville
119211576 | T3 EI KILARC-CEDAR CREEK 11/248 RPR STRW | 43939119 | KILARC-CEDAR CREEK | 011/248 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.958837 | 40.7669 | ETL.7290 | 40822571 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119211577 | EI T3NT KILARC-CEDAR CRK 11/248 RMV PL B | 43939119 | KILARC-CEDAR CREEK | 011/248 | ICW | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR3 |  | North Valley | WSIP | [6 empty] | '-121.958837 | 40.7669 | ETL.7290 | 40822571 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119211738 | T3 EI KILARC-CEDAR CREEK 4/104 RPR STRW | 43939119 | KILARC-CEDAR CREEK | 004/104 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.954213 | 40.7031 | ETL.7290 | 40602035 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119211889 | T2 EI KESWICK-TRINITY 16/215 RPL POLE | 31509665 | KESWICK-TRINITY | 016/215 | 70Y | E | 2020_(2) High fire spread TD |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-122.692062 | 40.7206 | ETL.7270 | 40758301 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain
119212112 | DI PHILO JCT-ELK 25/3C RPR GYWW | 44587877 | PHILO JCT-ELK | 025/003C | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.531376 | 39.0829 | ETL.7780 | 44976167 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
119212483 | SONOMA-PUEBLO 6/010 RPL POLE | 31508659 | SONOMA-PUEBLO | 006/010 | 70Y | E | 2020_(2) High fire spread TD | [5 empty] | North Coast | WSIP | [6 empty] | '-122.355308 | 38.296 | ETL.3810 | 40588275 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville
119212488 | EI MENDOCINO-FORT BRAGG 10/07 RPR GYWW | 44610681 | MENDOCINO-WILLITS-FORT BRAGG | 010/007 | ICW | E | 2020_(2) High fire spread TD | [5 empty] | North Coast | WSIP | [6 empty] | '-123.312409 | 39.36 | ETL.7550 | 44211145 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
119212585 | EI MENDOCINO-FORT BRAGG 10/007 RPR GYWW | 44610681 | MENDOCINO-WILLITS-FORT BRAGG | 010/007 | ICW | E | 2020_(2) High fire spread TD | [5 empty] | North Coast | WSIP | [6 empty] | '-123.312409 | 39.36 | ETL.7550 | 44211146 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
119212587 | EI MENDOCINO-FORT BRAGG 10/007 RPR GYWW | 44610681 | MENDOCINO-WILLITS-FORT BRAGG | 010/007 | ICW | E | 2020_(2) High fire spread TD | [5 empty] | North Coast | WSIP | [6 empty] | '-123.312409 | 39.36 | ETL.7550 | 44211147 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
119212602 | T3 EI KILARC-CEDAR CREEK 10/236 RPR GYWW | 43939119 | KILARC-CEDAR CREEK | 010/236 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.964835 | 40.7598 | ETL.7290 | 44837802 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119212917 | T2 EI GARCIA TAP 001/000 RPL ANCW | 31509677 | GARCIA TAP | 001/000A | 93E | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.579512 | 38.8804 | ETL.8411 | 40577441 | Anchor-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Lakeville
119213090 | LAYTONVILLE-COVELO 10/001 INST DAMPER | 44579513 | LAYTONVILLE-COVELO | 010/001 | ICW | E | 2020_(3) On high spread structure | [5 empty] | North Coast | WSIP | [6 empty] | '-123.309999 | 39.7323 | ETL.7390 | 44931536 | Damper-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
119213130 | T3 EI DESABLA-CENTERVILLE 005/067 RPR GY | 44356201 | DESABLA-CENTERVILLE | 005/067 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.653684 | 39.7951 | ETL.6720 | 44324217 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119213231 | T3 EAGLE RCK-FULTN-SLVRDO 6/31 INST INSS |  | EAGLE ROCK-FULTON-SILVERADO | 006/031 | ICS | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.7857857 | 38.7536 | ETL.4392 | 40620217 | Insulator-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville
119213247 | DI RIO BRAVO-KERN OIL 17/0 INS NUMBR | 44609890 | RIO BRAVO-KERN OIL (IDLE) | 017/000 | ICS | F | 2020_(1b) Lines with special commitments | [5 empty] | South | WSIP | [6 empty] | '-119.17341 | 35.4415 | ETL.1922 | 44182587 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Midway
119213266 | T3 EAGLE RCK-FLTON-SLVRDO 4/17 RPR INSS |  | EAGLE ROCK-FULTON-SILVERADO | 004/017 | ICS | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.7648931 | 38.6743 | ETL.4392 | 40833091 | Insulator-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville
119213304 | T3 EAGLE ROCK-FLTN-SLVRDO 3/17 RPL INSS |  | EAGLE ROCK-FULTON-SILVERADO | 003/017 | ICS | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.7993835 | 38.7982 | ETL.4392 | 40839420 | Insulator-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Lakeville
119213630 | DI GATES-PANOCHE#1 12/59 RPR FOND | 44371519 | GATES-PANOCHE #1 | 012/059 | ICQ | F | 2020_(1b) Lines with special commitments |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.242715 | 36.2903 | ETL.4720 | 40863290 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 10
119213631 | DI GATES-PANOCHE#1 12/59 RPR SHLS | 44371620 | GATES-PANOCHE #1 | 012/059 | ICS | E | 2020_(1b) Lines with special commitments |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.242715 | 36.2903 | ETL.4720 | 40863290 | Shield Wire / OPGW-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno |  | Y - 10
119218629 | DI RIO BRAVO-KERN OIL 19/0 RPR INSS | 44609891 | RIO BRAVO-KERN OIL (IDLE) | 019/000 | ICS | E | 2020_(1b) Lines with special commitments | [5 empty] | South | WSIP | [6 empty] | '-119.1408 | 35.4414 | ETL.1922 | 44182785 | Insulator-Steel | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Midway |  | Y - Prog 402
119219039 | DI GATES-PANOCHE #1 9/48 RPR FOND | 44394839 | GATES-PANOCHE #1 | 009/048 | ICQ | F | 2020_(1b) Lines with special commitments |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.220207 | 36.2614 | ETL.4720 | 40863634 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Fresno |  | Y - 10
119219132 | EI T3NT FULTON-IGNACIO #1 6/035 CANCEL | 44310479 | FULTON-IGNACIO #1 | 006/035 | ICQ | F | 2020_(2) High fire spread TD |  |  | CANCEL/CNCL | TR3 |  | North Coast | WSIP | [6 empty] | '-122.647285 | 38.4973 | ETL.4680 | 40762100 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville
119219201 | T2 EI KESWICK-TRINITY 17/222 RPL POLE | 31509665 | KESWICK-TRINITY | 017/222 | 70Y | E | 2020_(2) High fire spread TD |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-122.696921 | 40.7213 | ETL.7270 | 40771210 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain
119219277 | T2 EI KESWICK-TRINITY 15/186 RMV BUTT | 44406439 | KESWICK-TRINITY | 015/186 | ICW | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.670049 | 40.7135 | ETL.7270 | 40876483 | Structure-Wood | Debris/Nest/etc. | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119219295 | EI T3NT FULTON-IGNACIO #1 17/089 RPR FON | 44310479 | FULTON-IGNACIO #1 | 017/089 | ICQ | F | 2020_(2) High fire spread TD |  |  |  | TR3 |  | North Coast | WSIP | [6 empty] | '-122.592508 | 38.3739 | ETL.4680 | 40872361 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLQ | Tower | Expense | 543 | Lakeville
119219525 | T2 IGNACIO-BOLINAS #2 18/205 RPL GUY PL | 31507534 | IGNACIO-BOLINAS #2 | 018/205 | 70Y | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.786068 | 38.042 | ETL.7180 | 40585481 | Guy Pole-Wood | Rotten | Replace | PEND | PEND | Out of Estimating, awaiting Enviro review | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Lakeville
119219700 | T2 EI KESWICK-TRINITY 17/224 RPR GYWW | 44406439 | KESWICK-TRINITY | 017/224 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-122.698281 | 40.7215 | ETL.7270 | 40827893 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119219813 | T3 EI VOLTA-DESCHUTES 6/147 RPL STRW | 31507081 | VOLTA-DESCHUTES | 006/147 | 70Y | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.991777 | 40.4908 | ETL.8290 | 40867834 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain
119220467 | T2 CARIBOU-PLUMAS JCT 5/0 |  | CARIBOU-PLUMAS JCT | 005/000 | ICS | E | 2020_(2) High fire spread TD |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-121.078105 | 40.0408 | ETL.6290 | 44399524 | Damper-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain
119220587 | T2 EI KESWICK-TRINITY 17/226 RPR GYWW | 44406439 | KESWICK-TRINITY | 017/226 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-122.699964 | 40.7218 | ETL.7270 | 40809923 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119220651 | T3 EI MIDDLE FORK-GOLD HILL 9/78C RPR CO | 44371784 | MIDDLE FORK-GOLD HILL | 009/078C | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.736619 | 38.9886 | ETL.5140 | 42569836 | Conductor-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Sacramento
119220699 | T2 EI MALIN-ROUND MTN #2 93/477 INS GMKR | 44408444 | MALIN-ROUND MTN #2 | 094/478 | ICS | F | 2020_(1b) Lines with special commitments |  |  |  | TR2 | WECC | North Valley | WSIP | [6 empty] | '-121.92932 | 40.8138 | ETL.6020 | 40816663 | Guy Wire Mark /Indic-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain
119220788 | T2 BRIDGEVILLE-COTTONWD 71/513L REFRAME |  | BRIDGEVILLE-COTTONWOOD | 071/513 |  | E | 2020_(2) High fire spread TD |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.525613 | 40.468 | ETL.1110 | 44424638 | Crossarm-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense |  | Eureka
119220904 | EI MENDOCINO-FORT BRAGG 10/004 RPR PL | 44610681 | MENDOCINO-WILLITS-FORT BRAGG | 010/004 | ICW | E | 2020_(2) High fire spread TD | [5 empty] | North Coast | WSIP | [6 empty] | '-123.3091851 | 39.353 | ETL.7550 | 44211109 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
119220921 | EI MENDOCINO-FORT BRAGG 10/4 RPR PL | 44610681 | MENDOCINO-WILLITS-FORT BRAGG | 010/004 | ICW | E | 2020_(2) High fire spread TD | [5 empty] | North Coast | WSIP | [6 empty] | '-123.3091851 | 39.353 | ETL.7550 | 44211110 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
119221007 | T3 EI MIDDLE FORK-GOLD HILL_013/114 RPL | 31510070 | MIDDLE FORK-GOLD HILL | 013/114 | 70Y | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-120.8101286 | 38.9489 | ETL.5140 | 44553583 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento
119221045 | T2 HAT CREEK #1-WESTWD 1/41 RPL POLE | 31527026 | HAT CREEK #1-WESTWOOD | 001/041 | 70Y | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.507355 | 40.9225 | ETL.7030 | 40671148 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain
119221091 | T2 SAN LUIS OBISPO-OCEANO 18/1 COMPLETED |  | SAN LUIS OBISPO-OCEANO | 018/102 | ICS | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | South | WSIP | [6 empty] | '-120.551777 | 35.0979 | ETL.3530 | 40586174 | Conductor-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Pismo Beach |  | Y - Prog 402
119221126 | T2 EI KILARC-DESCHUTES 8/169 REFRAME | 31507189 | KILARC-DESCHUTES | 008/169 | 93E | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.978156 | 40.5972 | ETL.7300 | 40771367 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain
119221233 | T2 BRIDGEVILLE-COTTONWD 71/513R REFRAME |  | BRIDGEVILLE-COTTONWOOD | 071/513 |  | E | 2020_(2) High fire spread TD |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.5256011 | 40.468 | ETL.1110 | 44424640 | Crossarm-Steel | No Good/Out of Stdrd | Replace |  |  |  |  | PEND | LC | TLN | Maintenance | Expense |  | Eureka
119221244 | T3 MONTA VISTA-JEFERSON #1 16/67 RMV VEG | 44627168 | MONTA VISTA-JEFFERSON #1 | 016/067 | CHS | E | 2020_(3) On high spread structure |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.298797 | 37.4167 | ETL.5220 | 40819489 | Road | Brush Fuel | Remove | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLR | Roads | Expense | 932 | Bay
119221300 | T3 EI VOLTA-DESCHUTES 6/131 RPL CRSW | 31507464 | VOLTA-DESCHUTES | 006/131 | 93E | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.978162 | 40.4875 | ETL.8290 | 40656917 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain |  |  | released 7-13-20
119221347 | DI RIO BRAVO-KERN OIL 16/7 RPLC DAMS | 44609892 | RIO BRAVO-KERN OIL (IDLE) | 016/007 | ICS | E | 2020_(1b) Lines with special commitments | [5 empty] | South | WSIP | [6 empty] | '-119.176163 | 35.4415 | ETL.1922 | 44182586 | Damper-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Midway |  | Y - Prog 402
119221486 | T2 CARIBOU-TABLE MTN 33/244 INST INSS |  | CARIBOU-TABLE MTN | 033/244 | ICS | E | 2020_(2) High fire spread TD |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.444897 | 39.827 | ETL.4440 | 40758433 | Insulator-Steel | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain
119221528 | T2 EI KESWICK-TRINITY 17/231 INST GMKR |  | KESWICK-TRINITY | 017/231 | ICS | F | 2020_(3) On high spread structure |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.703544 | 40.7223 | ETL.7270 | 40752207 | Guy Wire Mark /Indic-Steel | Missing | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain
119221531 | T2 EI KESWICK-TRINITY 17/231 RPR GYWW | 44406439 | KESWICK-TRINITY | 017/231 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-122.703544 | 40.7223 | ETL.7270 | 40752207 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119221563 | T2 EI IGNACIO-BOLINAS #2 0/2 RPR GYWW |  | IGNACIO-BOLINAS #2 | 000/002 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.543051 | 38.075 | ETL.7180 | 40701427 | Guy Wire-Wood | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
119221585 | T2NT DI IGNACIO-BLINAS #2 7/97 INST MRKW |  | IGNACIO-BOLINAS #2 | 007/097 | ICW | F | 2020_(3) On high spread structure |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-122.651806 | 38.1155 | ETL.7180 | 40658520 | Marker (i.e. signs)-Wood | Missing | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
119221621 | DI RIO BRAVO-KERN OIL 18/0 INST MRKS | 44609893 | RIO BRAVO-KERN OIL (IDLE) | 018/000 | ICS | F | 2020_(1b) Lines with special commitments | [5 empty] | South | WSIP | [6 empty] | '-119.156209 | 35.4415 | ETL.1922 | 44182665 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Midway
119221623 | DI RIO BRAVO-KERN OIL 19/1 INST MRKS | 44609894 | RIO BRAVO-KERN OIL (IDLE) | 019/001 | ICS | F | 2020_(1b) Lines with special commitments | [5 empty] | South | WSIP | [6 empty] | '-119.138397 | 35.4414 | ETL.1922 | 44182673 | Marker (i.e. signs)-Steel | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Midway
119221625 | DI RIO BRAVO-KERN OIL 16/6 INST MRKS | 44609895 | RIO BRAVO-KERN OIL (IDLE) | 016/006 | ICS | F | 2020_(1b) Lines with special commitments | [5 empty] | South | WSIP | [6 empty] | '-119.178334 | 35.4415 | ETL.1922 | 44182584 | Marker (i.e. signs)-Steel | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Midway
119221627 | T3 DI MORAGA-OAKLAND #1 2/18 RPR FOND |  | MORAGA-OAKLAND #1 | 002/018 | ICQ | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | Central | WSIP | [6 empty] | '-122.202108 | 37.8297 | ETL.2720 | 40857637 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Bay |  | Y - Prog 402
119221732 | T3 FULTON-CALISTOGA - 16/003 RPL INSW | 31507466 | FULTON-CALISTOGA | '-016/003 | 93I | E | 2020_(2) High fire spread TD |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-122.488228 | 38.4578 | ETL.6880 | 40677327 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Lakeville
119221873 | DI RIO BRAVO-KERN OIL 14/6 INST MRKS | 44609896 | RIO BRAVO-KERN OIL (IDLE) | 014/006 | ICS | F | 2020_(1b) Lines with special commitments | [5 empty] | South | WSIP | [6 empty] | '-119.214072 | 35.4416 | ETL.1922 | 44182531 | Marker (i.e. signs)-Steel | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Midway
119221981 | T2 EI KESWICK-TRINITY 17/233 RPR GYWW | 44406439 | KESWICK-TRINITY | 017/233 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-122.704582 | 40.7224 | ETL.7270 | 40824079 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119221984 | T2 DRUM-SPAULDING 7/182 RPL POLE | 31508495 | DRUM-SPAULDING | 007/182 | 70Y | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-120.668049 | 39.3075 | ETL.6770 | 40601226 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Sacramento
119222169 | T3 EI KILARC-CEDAR CREEK 9/203 RPL POLE | 31507465 | KILARC-CEDAR CREEK | 009/203 | 70Y | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.981383 | 40.74 | ETL.7290 | 40701755 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain
119222326 | T2 EI KESWICK-TRINITY 14/177 INS MRKW | 44406439 | KESWICK-TRINITY | 014/177 | ICW | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-122.663504 | 40.7034 | ETL.7270 | 40825945 | Marker (i.e. signs)-Wood | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119222382 | DI RO BRV-KRN OIL-KRN OL 13/2 INS MRKS | 44609897 | RIO BRAVO-KERN OIL (IDLE) | 013/002 | ICS | F | 2020_(1b) Lines with special commitments | [5 empty] | South | WSIP | [6 empty] | '-119.240634 | 35.4416 | ETL.1922 | 44182506 | Marker (i.e. signs)-Steel | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Midway |  | Y - Prog 402
119222393 | T2 EI KESWICK-TRINITY 17/236 RPR GYWW | 44406439 | KESWICK-TRINITY | 017/236 | ICW | E | 2020_(2) High fire spread TD |  |  |  | TR2 | SCHD | North Valley | WSIP | [6 empty] | '-122.706245 | 40.7227 | ETL.7270 | 40590478 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain
119222426 | T3 EI UKIAH-HOPLAND-CLVERDALE 17/4 RPL H | 44610690 | UKIAH-HOPLAND-CLOVERDALE | 017/004 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Coast | WSIP | [6 empty] | '-123.03921 | 38.8875 | ETL.4050 | 40750650 | Hardware-Wood | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Lakeville
119222551 | DI RIO BVO-KRN OIL-KRN OIL 19/4 INS MRKS | 44609898 | RIO BRAVO-KERN OIL (IDLE) | 019/004 | ICS | F | 2020_(1b) Lines with special commitments | [5 empty] | South | WSIP | [6 empty] | '-119.131839 | 35.4414 | ETL.1922 | 44183127 | Marker (i.e. signs)-Steel | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Midway |  | Y - Prog 402
119222686 | T2 EI HAT CREEK #1-WESTWOOD 53/1031REFRA | 31508175 | HAT CREEK #1-WESTWOOD | 053/1031 | 93E | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.003802 | 40.3262 | ETL.7030 | 40815902 | Crossarm-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 637 | Table Mountain
119222704 | DI GATES-PANOCHE #2 3/20 RPLC DAMPER | 44394924 | GATES-PANOCHE #2 | 003/020 | ICS | E | 2020_(1b) Lines with special commitments |  |  |  |  | WECC | South | WSIP | [6 empty] | '-120.162908 | 36.188 | ETL.4730 | 44402080 | Damper-Steel | No Good/Out of Stdrd | Replace | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Fresno
119222762 | T3 EI VOLTA-DESCHUTES 3/073 RPR STRW | 43939089 | VOLTA-DESCHUTES | 003/073 | ICW | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.927898 | 40.4749 | ETL.8290 | 40825122 | Structure-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Table Mountain |  |  | released 7-13-20
119222765 | T3 EI VOLTA-DESCHUTES 3/68 RPL POLE | 31507081 | VOLTA-DESCHUTES | 003/068 | 70Y | E | 2020_(4) TD tag on high spread line |  |  |  | TR3 | LATE | North Valley | WSIP | [6 empty] | '-121.923615 | 40.4739 | ETL.8290 | 40700104 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLX | Pole Program | Capital | 372 | Table Mountain
119222878 | T2 DI CRESTA-RIO OSO 29/240 INS MRKS |  | CRESTA-RIO OSO | 029/240 | ICS | F | 2020_(4b) On structure in bucket 4 |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.53482 | 39.5491 | ETL.4590 | 41083101 | Marker (i.e. signs)-Steel | No Good/Out of Stdrd | Install |  |  |  |  | PEND | LC | TLN | Maintenance | Expense | 628 | Table Mountain
119222956 | T2 DI CRESTA-RIO OSO 29/236 RPR FOND |  | CRESTA-RIO OSO | 029/236 | ICQ | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Valley | WSIP | [6 empty] | '-121.536297 | 39.5541 | ETL.4590 | 41083097 | Foundation/Concrete-Tower | No Good/Out of Stdrd | Repair |  |  |  |  | PEND | LC | TLQ | Tower | Expense | 543 | Table Mountain
119222959 | DI RIP BRAVO-KERN OIL 13/5 INS MRKS | 44609899 | RIO BRAVO-KERN OIL (IDLE) | 013/005 | ICS | F | 2020_(1b) Lines with special commitments | [5 empty] | South | WSIP | [6 empty] | '-119.233907 | 35.4416 | ETL.1922 | 44182516 | Marker (i.e. signs)-Steel | No Good/Out of Stdrd | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 628 | Midway |  | Y - Prog 402
119222997 | DI LIGHTNER TAP 0/12 INST MRKW | 44610120 | LIGHTNER TAP (IDLE) | 000/012 | ICW | F | 2020_(1b) Lines with special commitments | [5 empty] | South | WSIP | [6 empty] | '-118.867481 | 35.3108 | ETL.8542 | 41170555 | Marker (i.e. signs)-Wood | Missing | Install | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Midway
119222999 | DI LIGHTNER TAP 0/12 RPLC INSW | 31509578 | LIGHTNER TAP (IDLE) | 000/012 | 93I | E | 2020_(1b) Lines with special commitments | [5 empty] | South | WSIP | [8 empty] | ETL.8542 | 44169334 | Insulator-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Maintenance | Capital | 508 | Midway
119224709 | EI TRINITY-MAPLE CREEK 43/12 RPR GYWW | 44273074 | TRINITY-MAPLE CREEK | 043/012 | ICW | E | 2020_(2) High fire spread TD | [5 empty] | North Coast | WSIP | [6 empty] | '-123.6916913 | 40.7409 | ETL.8170 | 44812835 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
119224815 | EI TRINITY-MAPLE CREEK 43/12 RPR GYWW | 44273074 | TRINITY-MAPLE CREEK | 043/012 | ICW | E | 2020_(2) High fire spread TD | [5 empty] | North Coast | WSIP | [6 empty] | '-123.6916913 | 40.7409 | ETL.8170 | 44812833 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
119224816 | EI TRINITY-MAPLE CREEK 43/12 RPR GYWW | 44273074 | TRINITY-MAPLE CREEK | 043/012 | ICW | E | 2020_(2) High fire spread TD | [5 empty] | North Coast | WSIP | [6 empty] | '-123.6916913 | 40.7409 | ETL.8170 | 44812834 | Guy Wire-Wood | No Good/Out of Stdrd | Repair | UNSE | UNSE | In Estimating, Unassigned | Not Complete | PEND | LC | TLN | Maintenance | Expense | 630 | Eureka
119224924 | T2 TRINITY-MAPLE CREEK 48/4C RPL POLE | 31508602 | TRINITY-MAPLE CREEK | 048/004C | 70Y | E | 2020_(4) TD tag on high spread line |  |  |  | TR2 |  | North Coast | WSIP | [6 empty] | '-123.769287 | 40.7522 | ETL.8170 | 44948570 | Structure-Wood | No Good/Out of Stdrd | Replace | UNSC srdy | UNSC | Out of Estimating and Environmental - construction ready | Complete | PEND | LC | TLN | Pole Program | Capital | 372 | Eureka